# LCLS Project Deliverables/Pre-requisites for Critical Decisions

- Mission Need Document – 6/01

- Acquisition Strategy (part of Mission Need Document) – 6/01

# CD-0 Mission Need Approval - June 2001

- Project Data Sheet for PED funding in FY04 – 4/02

- Complete CDR – 4/02

- Preliminary scope, cost and schedule baseline – 4/02

- CD-1 Lehman Review (Based on CDR) – 4/02

- Preliminary Hazard Analysis Report – 7/02

- Approve Acquisition Execution Plan – 8/02

- Approve Preliminary Project Execution Plan – 8/02

# CD-1 Preliminary Baseline Approval – August 2002

- Input project information into PARS – 9/02

- PED PMCS Implemented – 9/02

- Authorized FY03 PED funds – 10/02

- Complete NEPA Documentation – 11/02

- Approve CD-2a, FY05 Long Lead Procurement (LLP) – 2/03

- Project Data Sheet for PED and LLP funding in FY05 - 4/03

- Finalize PEP – 2/04

- Complete Draft Preliminary Safety Assessment Document (PSAD) – 2/04

- Title I Design – 2/04

- Risk Analysis Plan – 4/04

- Develop Performance scope, cost and schedule baseline – 4/04

- Independent Cost Estimate – 3/04

- External Independent Review (combine with ICE) – 3/04

- Construction Project Data Sheet for FY06 – 4/04

# CD-2b Performance Baseline Approval – April 2004

- CD-3a Approval of LLP authority – 8/04

- Construction Project Data Sheet for FY07 – 4/05

- Construction PMCS implemented – 4/05

- Certify construction PMCS – 5/05

- Finalize and approve PSAD – 6/05

- Update PEP and performance baseline for construction – 6/05

- Independent Project Review (verify readiness for construction) – 6/05

# CD-3 Start Construction Approval – August 2005

- Authorize funds to start construction – 10/05

- Construction Project Data Sheet for FY08 – 4/06

- Final Safety Analysis Document Approved – 3/08

- Complete Construction – 9/08

- Complete Commissioning – 9/08

- Complete Phased Accelerator Readiness Review – 9/08

# CD-4 Approve Start of Operations – October 2008