{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["PDATA","1.XX SPA","SPA_Chart_Data"],"not_rendered":{"charts":1,"images":0,"macros":1,"external_links":1,"defined_names":6,"comments":0,"pivot_tables":0},"unopened":[{"sheet":"1.XX SPA","index":1,"reason":"not_a_worksheet"}],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"PDATA","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"SPA_Chart_Data","index":2,"n_rows":30,"n_cols":45,"rows_kept":30,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["LCLS PROJECT - PED & CONSTRUCTION                           ",1,"CTD","2007-05-31","2007-06-30","2007-07-31","2007-08-31","2007-09-30","2007-10-31","2007-11-30","2007-12-31","2008-01-31","2008-02-29","2008-03-31","2008-04-30","2008-05-31","2008-06-30","2008-07-31","2008-08-31","2008-09-30","2008-10-31","2008-11-30","2008-12-31","2009-01-31","2009-02-28","2009-03-31","2009-04-30","2009-05-31","2009-06-30","2009-07-31","2009-08-31","2009-09-30","2009-10-31","2009-11-30","2009-12-31","2010-01-31","2010-02-28","2010-03-31","2010-04-30","2010-05-31"]
[null,"Mo S+O",154.78,17.15662,12.199179,12.159891,17.843595,14.586862,15.241671,8.957152,7.555849,8.087256,5.563208,4.089921,5.547645,2.670906,1.590559,1.565527,1.331306,1.171723,10.549377,1.073114,0.959242,0.558731,0.577495,0.654773,0.564909,0.50964,0.566071,0.686107,0.54059,0.554216,0.342497,0.309849,0.307222,0.232376,0.208946,0.240288,0.212185,0.197839]
[null,"Mo S",154.78,13.12035,11.104686,11.924705,16.833486,15.695658,15.37107,10.983777,8.932553,6.962179,6.247903,5.030145,6.243933,2.951022,1.751173,1.460951,1.423065,1.263482,2.915707,2.175237,2.015645,1.638528,1.55045,1.743223,1.426148,1.253958,1.148218,0.679498,0.626024,0.621264,0.316697,0.316177,0.313851,0.238703,0.214972,0.247218,0.218814,0.203865]
[null,"FY BA"]
[null,"Cum S+O",154.78,171.93662,184.13579900000002,196.29569,214.139285,228.726147,243.967818,252.92497,260.480819,268.568075,274.131283,278.221204,283.768849,286.439755,288.030314,289.59584099999995,290.92714699999993,292.0988699999999,302.6482469999999,303.7213609999999,304.6806029999999,305.23933399999993,305.8168289999999,306.4716019999999,307.0365109999999,307.5461509999999,308.1122219999999,308.7983289999999,309.3389189999999,309.8931349999999,310.2356319999999,310.5454809999999,310.8527029999999,311.0850789999999,311.2940249999999,311.53431299999994,311.7464979999999,311.9443369999999]
[null,"Cum S",154.78,167.90035,179.005036,190.92974099999998,207.76322699999997,223.45888499999998,238.82995499999998,249.813732,258.746285,265.708464,271.956367,276.986512,283.23044500000003,286.18146700000005,287.93264000000005,289.3935910000001,290.8166560000001,292.0801380000001,294.9958450000001,297.17108200000007,299.1867270000001,300.8252550000001,302.3757050000001,304.1189280000001,305.5450760000001,306.7990340000001,307.9472520000001,308.62675000000013,309.2527740000001,309.8740380000001,310.1907350000001,310.50691200000006,310.82076300000006,311.05946600000004,311.27443800000003,311.521656,311.74047,311.944335]
[null,"CUM BA",147.74,248.74,248.74,248.74,248.74,248.74,300.1,300.1,300.1,300.1,300.1,300.1,300.1,300.1,300.1,300.1,300.1,300.1,331.6,331.6,331.6,331.6,331.6,331.6,331.6,331.6,331.6,331.6,331.6,331.6,339,339,339,339,339,339,339,339]
[]
[]
[]
[]
[]
[]
[null,null,"CTD","MAY_07","JUN_07","JUL_07","AUG_07","SEP_07","OCT_07","NOV_07","DEC_07","JAN_08","FEB_08","MAR_08","APR_08","MAY_08","JUN_08","JUL_08","AUG_08","SEP_08","OCT_08","NOV_08","DEC_08","JAN_09","FEB_09","MAR_09","APR_09","MAY_09","JUN_09","JUL_09","AUG_09","SEP_09","OCT_09","NOV_09","DEC_09","JAN_10","FEB_10","MAR_10","APR_10","MAY_10","JUN_10","JUL_10","AUG_10","SEP_10","Cumulative"]
["REPORT \"CAP\" Filter \"OBLGCUM\" WBS1, BCWS and OBLG","BCWS (less Oblg)",null,12460348,10287972,9847438,13477327,13574235,11931523,8799352,7555849,5382938,4847441,3864151,5547645,2593224,1590559,1329306,1331306,1171723,1431857,1073114,859348,558731,555495,654773,564909,509640,566071,577091,540590,554216,292218,309849,307222,232376,208946,240288,212185,197839,0,0,0,0,126039095]
[null,"OBLG",0,4696272,1911207,2312453,4366268,1012627,3310148,157800,0,2704318,715767,225770,0,77682,0,236221,0,0,9117520,0,99894,0,22000,0,0,0,0,109016,0,0,50279,0,0,0,0,0,0,0,0,0,0,0,31125241]
[]
[null,null,null,17056159]
[null,null,null,17056.159]
[]
[null,"BA_APR07",147.74]
[null,"BA_REM07",101]
[null,"BA_FY08",51.36]
[null,"BA_FY09",31.5]
[null,"BA_FY10",7.4]
[]
[]
[]
[]
["Report \"CAP\" No Filter Monthly, WBS1,BCWS","BCWS",null,13120350,11104686,11924705,16833486,15695658,15371070,10983777,8932553,6962179,6247903,5030145,6243933,2951022,1751173,1460951,1423065,1263482,2915707,2175237,2015645,1638528,1550450,1743223,1426148,1253958,1148218,679498,626024,621264,316697,316177,313851,238703,214972,247218,218814,203865,0,0,0,0,157164336]