{"text_format":"2","workbook":"xls","n_sheets":11,"sheets":["lclsrate","opcclc","tecclc","Master","April-2007 DCE","Detailed Cost Estimate","No CT Comparison","CT Only Comparison","WBS-CN-PP","ResDes","Indirect"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":1,"defined_names":19,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"lclsrate","index":0,"n_rows":846,"n_cols":7,"rows_kept":846,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["RATEFILE","DESCRIP","RATE_TABLE","RATE_DESCRIP","COMBO","RATE","RATE_DATE"]
["LCLSRAT4","LCLS RATES","AA_MSEG","RTDESC","AA_MSEG37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AA_MSEG1","RTDESC","AA_MSEG138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AA_MSEG2","RTDESC","AA_MSEG238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AA_MSEQ","RTDESC","AA_MSEQ37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AA_MSEQ1","RTDESC","AA_MSEQ138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AA_MSEQ2","RTDESC","AA_MSEQ238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AA_MSSC","RTDESC","AA_MSSC37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AA_MSSC1","RTDESC","AA_MSSC138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AA_MSSC2","RTDESC","AA_MSSC238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AA_MSSF","RTDESC","AA_MSSF37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AA_MSSF1","RTDESC","AA_MSSF138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AA_MSSF2","RTDESC","AA_MSSF238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AESCL2","RTDESC","AESCL238991",0,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AESCL2","RTDESC","AESCL239356",0.045,"2007-10-01"]
["LCLSRAT4","LCLS RATES","AESCL2","RTDESC","AESCL239722",0.092025,"2008-10-01"]
["LCLSRAT4","LCLS RATES","AESCL2","RTDESC","AESCL240087",0.141166125,"2009-10-01"]
["LCLSRAT4","LCLS RATES","AESCL2","RTDESC","AESCL240452",0.192518601,"2010-10-01"]
["LCLSRAT4","LCLS RATES","AN_ADMN","RTDESC","AN_ADMN37895",63.24,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AN_ADMN1","RTDESC","AN_ADMN138626",83.51,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_ADMN2","RTDESC","AN_ADMN238991",83.51,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AN_AW1","RTDESC","AN_AW138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_AW2","RTDESC","AN_AW238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AN_AWARD","RTDESC","AN_AWARD37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AN_CCA","RTDESC","AN_CCA37895",67.43,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AN_CCA1","RTDESC","AN_CCA138626",83.51,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_CCA2","RTDESC","AN_CCA238991",83.51,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AN_CE","RTDESC","AN_CE37895",67.43,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AN_CE1","RTDESC","AN_CE138626",83.51,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_CE2","RTDESC","AN_CE238991",83.51,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AN_CP","RTDESC","AN_CP37895",67.43,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AN_CP1","RTDESC","AN_CP138626",83.51,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_CP2","RTDESC","AN_CP238991",83.51,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AN_CS1","RTDESC","AN_CS138626",0.257,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_CS2","RTDESC","AN_CS238626",0.196,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_CS2","RTDESC","AN_CS238991",0.257,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AN_CS4","RTDESC","AN_CS438626",0.292,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_CS5","RTDESC","AN_CS538626",0.196,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_CS6","RTDESC","AN_CS638626",0.064,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_CT","RTDESC","AN_CT37895",42.99,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AN_CT1","RTDESC","AN_CT138626",49.03,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_CT2","RTDESC","AN_CT238991",49.03,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AN_EE","RTDESC","AN_EE37895",67.43,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AN_EE1","RTDESC","AN_EE138626",83.51,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_EE2","RTDESC","AN_EE238991",83.51,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AN_GA1","RTDESC","AN_GA138626",0.026,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_GA2","RTDESC","AN_GA238991",0.026,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AN_GA2","RTDESC","AN_GA238626",0.027,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_MDD","RTDESC","AN_MDD37895",42.99,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AN_MDD1","RTDESC","AN_MDD138626",49.03,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_MDD2","RTDESC","AN_MDD238991",49.03,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AN_ME","RTDESC","AN_ME37895",63.24,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AN_ME1","RTDESC","AN_ME138626",83.51,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_ME2","RTDESC","AN_ME238991",83.51,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AN_MES","RTDESC","AN_MES37895",67.43,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AN_MES1","RTDESC","AN_MES138626",83.51,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_MES2","RTDESC","AN_MES238991",83.51,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AN_MFAT","RTDESC","AN_MFAT37895",42.51,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AN_MFAT1","RTDESC","AN_MFAT138626",49.03,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_MFAT2","RTDESC","AN_MFAT238991",49.03,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AN_MFMS","RTDESC","AN_MFMS37895",53.97,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AN_MFMS1","RTDESC","AN_MFMS138626",81,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_MFMS2","RTDESC","AN_MFMS238991",81,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AN_MSCS","RTDESC","AN_MSCS37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AN_MSCS1","RTDESC","AN_MSCS138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_MSCS2","RTDESC","AN_MSCS238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AN_MSEG","RTDESC","AN_MSEG37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AN_MSEG1","RTDESC","AN_MSEG138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_MSEG2","RTDESC","AN_MSEG238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AN_MSEQ","RTDESC","AN_MSEQ37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AN_MSEQ1","RTDESC","AN_MSEQ138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_MSEQ2","RTDESC","AN_MSEQ238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AN_MSPS","RTDESC","AN_MSPS37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AN_MSPS1","RTDESC","AN_MSPS138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_MSPS2","RTDESC","AN_MSPS238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AN_MSSC","RTDESC","AN_MSSC37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AN_MSSC1","RTDESC","AN_MSSC138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_MSSC2","RTDESC","AN_MSSC238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AN_MSSF","RTDESC","AN_MSSF37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AN_MSSF1","RTDESC","AN_MSSF138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_MSSF2","RTDESC","AN_MSSF238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AN_MSTR","RTDESC","AN_MSTR37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AN_MSTR1","RTDESC","AN_MSTR138626",1.29,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_MSTR2","RTDESC","AN_MSTR238991",1.29,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AN_MSXX","RTDESC","AN_MSXX37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AN_MSXX1","RTDESC","AN_MSXX138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_MSXX2","RTDESC","AN_MSXX238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AN_MTRL","RTDESC","AN_MTRL37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AN_MTRL1","RTDESC","AN_MTRL138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_MTRL2","RTDESC","AN_MTRL238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AN_MVE","RTDESC","AN_MVE37895",63.24,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AN_MVE1","RTDESC","AN_MVE138626",83.51,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_MVE2","RTDESC","AN_MVE238991",83.51,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AN_OH1","RTDESC","AN_OH137895",0.3224,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AN_OH2","RTDESC","AN_OH237895",0.2598,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AN_OH2","RTDESC","AN_OH238991",0.3224,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AN_OH3","RTDESC","AN_OH337895",0,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AN_OH4","RTDESC","AN_OH437895",0,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AN_PHH","RTDESC","AN_PHH37895",45.68,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AN_PHH1","RTDESC","AN_PHH138626",45.68,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_PHH2","RTDESC","AN_PHH238991",45.68,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AN_PHPD","RTDESC","AN_PHPD37895",33.95,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AN_PHPD1","RTDESC","AN_PHPD138626",37.26,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_PHPD2","RTDESC","AN_PHPD238991",37.26,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AN_PHS","RTDESC","AN_PHS37895",63.24,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AN_PHS1","RTDESC","AN_PHS138626",83.51,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_PHS2","RTDESC","AN_PHS238991",83.51,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AN_PHSS","RTDESC","AN_PHSS37895",63.24,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AN_PHSS1","RTDESC","AN_PHSS138626",63.24,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_PHSS2","RTDESC","AN_PHSS238991",63.24,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AN_PM","RTDESC","AN_PM37895",63.24,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AN_PM1","RTDESC","AN_PM138626",83.51,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_PM2","RTDESC","AN_PM238991",83.51,"2006-10-01"]
["LCLSRAT4","LCLS RATES","AN_SEE","RTDESC","AN_SEE37895",85,"2003-10-01"]
["LCLSRAT4","LCLS RATES","AN_SEE1","RTDESC","AN_SEE138626",83.51,"2005-10-01"]
["LCLSRAT4","LCLS RATES","AN_SEE2","RTDESC","AN_SEE238991",83.51,"2006-10-01"]
["LCLSRAT4","LCLS RATES","BA","RTDESC","BA37500",1,"2002-09-01"]
["LCLSRAT4","LCLS RATES","BASE","RTDESC","BASE37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","ESC","RTDESC","ESC37895",0,"2003-10-01"]
["LCLSRAT4","LCLS RATES","ESC","RTDESC","ESC38261",0.029,"2004-10-01"]
["LCLSRAT4","LCLS RATES","ESC","RTDESC","ESC38626",0.057812,"2005-10-01"]
["LCLSRAT4","LCLS RATES","ESC","RTDESC","ESC38991",0.085315,"2006-10-01"]
["LCLSRAT4","LCLS RATES","ESC","RTDESC","ESC39356",0.113533,"2007-10-01"]
["LCLSRAT4","LCLS RATES","ESC","RTDESC","ESC39722",0.142485,"2008-10-01"]
["LCLSRAT4","LCLS RATES","ESC1","RTDESC","ESC138626",0,"2005-10-01"]
["LCLSRAT4","LCLS RATES","ESC1","RTDESC","ESC138991",0.026,"2006-10-01"]
["LCLSRAT4","LCLS RATES","ESC1","RTDESC","ESC139356",0.052676,"2007-10-01"]
["LCLSRAT4","LCLS RATES","ESC1","RTDESC","ESC139722",0.08004558,"2008-10-01"]
["LCLSRAT4","LCLS RATES","ESC2","RTDESC","ESC238991",0.023,"2006-10-01"]
["LCLSRAT4","LCLS RATES","ESC2","RTDESC","ESC239356",0.046529,"2007-10-01"]
["LCLSRAT4","LCLS RATES","ESC2","RTDESC","ESC239722",0.070599,"2008-10-01"]
["LCLSRAT4","LCLS RATES","ESC2","RTDESC","ESC240087",0.095223,"2009-10-01"]
["LCLSRAT4","LCLS RATES","ESC2","RTDESC","ESC240452",0.120413,"2010-10-01"]
["LCLSRAT4","LCLS RATES","ESC2","RTDESC","ESC240817",0.120413,"2011-10-01"]
["LCLSRAT4","LCLS RATES","ESCL2","RTDESC","ESCL238991",0,"2006-10-01"]
["LCLSRAT4","LCLS RATES","ESCL2","RTDESC","ESCL239356",0.04,"2007-10-01"]
["LCLSRAT4","LCLS RATES","ESCL2","RTDESC","ESCL239722",0.0816,"2008-10-01"]
["LCLSRAT4","LCLS RATES","ESCL2","RTDESC","ESCL240087",0.124864,"2009-10-01"]
["LCLSRAT4","LCLS RATES","ESCL2","RTDESC","ESCL240452",0.1698586,"2010-10-01"]
["LCLSRAT4","LCLS RATES","ESCL2","RTDESC","ESCL240817",0.2166529,"2011-10-01"]
["LCLSRAT4","LCLS RATES","ESC_CF","RTDESC","ESC_CF38261",0,"2004-10-01"]
["LCLSRAT4","LCLS RATES","ESC_CF","RTDESC","ESC_CF38626",0.03,"2005-10-01"]
["LCLSRAT4","LCLS RATES","ESC_CF","RTDESC","ESC_CF38991",0.08,"2006-10-01"]
["LCLSRAT4","LCLS RATES","ESC_CF","RTDESC","ESC_CF39356",0.19,"2007-10-01"]
["LCLSRAT4","LCLS RATES","ESC_CF","RTDESC","ESC_CF39722",0.3,"2008-10-01"]
["LCLSRAT4","LCLS RATES","ESC_CF","RTDESC","ESC_CF40087",0.41,"2009-10-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE37803",0.005434782608695652,"2003-07-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE37895",0.005434782608695652,"2003-10-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE37956",0.005434782608695652,"2003-12-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38047",0.005434782608695652,"2004-03-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38412",0.005434782608695652,"2005-03-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38565",0.005434782608695652,"2005-08-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38777",0.005434782608695652,"2006-03-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38930",0.005434782608695652,"2006-08-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39295",0.005434782608695652,"2007-08-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39356",0.005434782608695652,"2007-10-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39722",0.005434782608695652,"2008-10-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39995",0.005434782608695652,"2009-07-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE40056",0.005434782608695652,"2009-08-31"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE37712",0.005681818181818182,"2003-04-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE37742",0.005681818181818182,"2003-05-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE37865",0.005681818181818182,"2003-09-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38078",0.005681818181818182,"2004-04-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38139",0.005681818181818182,"2004-06-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38200",0.005681818181818182,"2004-08-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38504",0.005681818181818182,"2005-06-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38838",0.005681818181818182,"2006-05-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38869",0.005681818181818182,"2006-06-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38991",0.005681818181818182,"2006-10-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39142",0.005681818181818182,"2007-03-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39203",0.005681818181818182,"2007-05-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39539",0.005681818181818182,"2008-04-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39630",0.005681818181818182,"2008-07-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39783",0.005681818181818182,"2008-12-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39873",0.005681818181818182,"2009-03-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39904",0.005681818181818182,"2009-04-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39965",0.005681818181818182,"2009-06-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE40087",0.005681818181818182,"2009-10-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE40148",0.005681818181818182,"2009-12-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE37681",0.005952380952380952,"2003-03-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE37773",0.005952380952380952,"2003-06-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE37834",0.005952380952380952,"2003-08-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38169",0.005952380952380952,"2004-07-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38231",0.005952380952380952,"2004-09-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38261",0.005952380952380952,"2004-10-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38443",0.005952380952380952,"2005-04-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38473",0.005952380952380952,"2005-05-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38596",0.005952380952380952,"2005-09-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38626",0.005952380952380952,"2005-10-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38687",0.005952380952380952,"2005-12-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39083",0.005952380952380952,"2007-01-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39173",0.005952380952380952,"2007-04-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39234",0.005952380952380952,"2007-06-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39264",0.005952380952380952,"2007-07-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39448",0.005952380952380952,"2008-01-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39508",0.005952380952380952,"2008-03-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39569",0.005952380952380952,"2008-05-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39600",0.005952380952380952,"2008-06-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39661",0.005952380952380952,"2008-08-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39692",0.005952380952380952,"2008-09-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39814",0.005952380952380952,"2009-01-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39934",0.005952380952380952,"2009-05-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE40118",0.005952380952380952,"2009-11-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE37653",0.00625,"2003-02-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE37926",0.00625,"2003-11-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE37987",0.00625,"2004-01-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38108",0.00625,"2004-05-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38292",0.00625,"2004-11-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38322",0.00625,"2004-12-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38353",0.00625,"2005-01-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38534",0.00625,"2005-07-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38657",0.00625,"2005-11-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38718",0.00625,"2006-01-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38808",0.00625,"2006-04-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38899",0.00625,"2006-07-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38961",0.00625,"2006-09-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39022",0.00625,"2006-11-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39052",0.00625,"2006-12-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39387",0.00625,"2007-11-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39417",0.00625,"2007-12-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39479",0.00625,"2008-02-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39845",0.00625,"2009-02-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE40026",0.00625,"2009-08-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38018",0.006578947368421052,"2004-02-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38384",0.006578947368421052,"2005-02-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE38749",0.006578947368421052,"2006-02-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39114",0.006578947368421052,"2007-02-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39326",0.006578947368421052,"2007-09-01"]
["LCLSRAT4","LCLS RATES","FTE","RTDESC","FTE39753",0.006944444444444444,"2008-11-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO37803",0.005434782608695652,"2003-07-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO37895",0.005434782608695652,"2003-10-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38047",0.005434782608695652,"2004-03-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38412",0.005434782608695652,"2005-03-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38565",0.005434782608695652,"2005-08-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38777",0.005434782608695652,"2006-03-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38930",0.005434782608695652,"2006-08-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39295",0.005434782608695652,"2007-08-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39356",0.005434782608695652,"2007-10-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39722",0.005434782608695652,"2008-10-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38078",0.005681818181818182,"2004-04-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38139",0.005681818181818182,"2004-06-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38200",0.005681818181818182,"2004-08-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38504",0.005681818181818182,"2005-06-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38838",0.005681818181818182,"2006-05-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38869",0.005681818181818182,"2006-06-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38991",0.005681818181818182,"2006-10-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39142",0.005681818181818182,"2007-03-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39203",0.005681818181818182,"2007-05-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39539",0.005681818181818182,"2008-04-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39630",0.005681818181818182,"2008-07-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39873",0.005681818181818182,"2009-03-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39904",0.005681818181818182,"2009-04-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39965",0.005681818181818182,"2009-06-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39995",0.005681818181818182,"2009-07-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO40087",0.005681818181818182,"2009-10-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO37560",0.005952380952380952,"2002-10-31"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO37834",0.005952380952380952,"2003-08-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO37865",0.005952380952380952,"2003-09-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO37956",0.005952380952380952,"2003-12-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38169",0.005952380952380952,"2004-07-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38231",0.005952380952380952,"2004-09-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38261",0.005952380952380952,"2004-10-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38443",0.005952380952380952,"2005-04-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38473",0.005952380952380952,"2005-05-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38596",0.005952380952380952,"2005-09-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38626",0.005952380952380952,"2005-10-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39083",0.005952380952380952,"2007-01-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39173",0.005952380952380952,"2007-04-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39234",0.005952380952380952,"2007-06-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39264",0.005952380952380952,"2007-07-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39448",0.005952380952380952,"2008-01-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39508",0.005952380952380952,"2008-03-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39569",0.005952380952380952,"2008-05-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39600",0.005952380952380952,"2008-06-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39661",0.005952380952380952,"2008-08-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39692",0.005952380952380952,"2008-09-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39783",0.005952380952380952,"2008-12-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO40026",0.005952380952380952,"2009-08-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO40056",0.005952380952380952,"2009-08-31"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO40148",0.005952380952380952,"2009-12-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO37500",0.00625,"2002-09-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO37530",0.00625,"2002-10-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO37987",0.00625,"2004-01-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38108",0.00625,"2004-05-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38292",0.00625,"2004-11-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38322",0.00625,"2004-12-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38353",0.00625,"2005-01-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38534",0.00625,"2005-07-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38657",0.00625,"2005-11-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38687",0.00625,"2005-12-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38718",0.00625,"2006-01-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38808",0.00625,"2006-04-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38899",0.00625,"2006-07-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38961",0.00625,"2006-09-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39022",0.00625,"2006-11-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39387",0.00625,"2007-11-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39479",0.00625,"2008-02-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39814",0.00625,"2009-01-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39934",0.00625,"2009-05-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38018",0.006578947368421052,"2004-02-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38384",0.006578947368421052,"2005-02-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO38749",0.006578947368421052,"2006-02-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39052",0.006578947368421052,"2006-12-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39114",0.006578947368421052,"2007-02-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39326",0.006578947368421052,"2007-09-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39417",0.006578947368421052,"2007-12-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39845",0.006578947368421052,"2009-02-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO40118",0.006578947368421052,"2009-11-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO37926",0.006944444444444444,"2003-11-01"]
["LCLSRAT4","LCLS RATES","FTE_MO","RTDESC","FTE_MO39753",0.006944444444444444,"2008-11-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO37803",0.00625,"2003-07-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO37895",0.00625,"2003-10-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38047",0.00625,"2004-03-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38412",0.00625,"2005-03-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38565",0.00625,"2005-08-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38777",0.00625,"2006-03-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38930",0.00625,"2006-08-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39295",0.00625,"2007-08-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39356",0.00625,"2007-10-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39722",0.00625,"2008-10-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38078",0.0065340909090909095,"2004-04-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38139",0.0065340909090909095,"2004-06-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38200",0.0065340909090909095,"2004-08-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38504",0.0065340909090909095,"2005-06-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38838",0.0065340909090909095,"2006-05-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38869",0.0065340909090909095,"2006-06-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38991",0.0065340909090909095,"2006-10-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39142",0.0065340909090909095,"2007-03-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39203",0.0065340909090909095,"2007-05-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39539",0.0065340909090909095,"2008-04-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39630",0.0065340909090909095,"2008-07-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39873",0.0065340909090909095,"2009-03-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39904",0.0065340909090909095,"2009-04-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39965",0.0065340909090909095,"2009-06-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39995",0.0065340909090909095,"2009-07-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO40087",0.0065340909090909095,"2009-10-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO37560",0.006845238095238095,"2002-10-31"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO37834",0.006845238095238095,"2003-08-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO37865",0.006845238095238095,"2003-09-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO37956",0.006845238095238095,"2003-12-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38169",0.006845238095238095,"2004-07-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38231",0.006845238095238095,"2004-09-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38261",0.006845238095238095,"2004-10-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38443",0.006845238095238095,"2005-04-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38473",0.006845238095238095,"2005-05-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38596",0.006845238095238095,"2005-09-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38626",0.006845238095238095,"2005-10-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39083",0.006845238095238095,"2007-01-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39173",0.006845238095238095,"2007-04-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39234",0.006845238095238095,"2007-06-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39264",0.006845238095238095,"2007-07-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39448",0.006845238095238095,"2008-01-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39508",0.006845238095238095,"2008-03-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39569",0.006845238095238095,"2008-05-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39600",0.006845238095238095,"2008-06-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39661",0.006845238095238095,"2008-08-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39692",0.006845238095238095,"2008-09-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39783",0.006845238095238095,"2008-12-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO40026",0.006845238095238095,"2009-08-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO40056",0.006845238095238095,"2009-08-31"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO40148",0.006845238095238095,"2009-12-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO37500",0.0071875,"2002-09-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO37530",0.0071875,"2002-10-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO37987",0.0071875,"2004-01-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38108",0.0071875,"2004-05-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38292",0.0071875,"2004-11-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38322",0.0071875,"2004-12-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38353",0.0071875,"2005-01-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38534",0.0071875,"2005-07-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38657",0.0071875,"2005-11-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38687",0.0071875,"2005-12-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38718",0.0071875,"2006-01-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38808",0.0071875,"2006-04-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38899",0.0071875,"2006-07-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38961",0.0071875,"2006-09-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39022",0.0071875,"2006-11-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39387",0.0071875,"2007-11-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39479",0.0071875,"2008-02-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39814",0.0071875,"2009-01-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39934",0.0071875,"2009-05-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38018",0.00756578947368421,"2004-02-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38384",0.00756578947368421,"2005-02-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38749",0.00756578947368421,"2006-02-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39052",0.00756578947368421,"2006-12-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39114",0.00756578947368421,"2007-02-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39326",0.00756578947368421,"2007-09-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39417",0.00756578947368421,"2007-12-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39845",0.00756578947368421,"2009-02-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO40118",0.00756578947368421,"2009-11-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO37926",0.00798611111111111,"2003-11-01"]
["LCLSRAT4","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39753",0.00798611111111111,"2008-11-01"]
["LCLSRAT4","LCLS RATES","LABOR","RTDESC","LABOR38231",0,"2004-09-01"]
["LCLSRAT4","LCLS RATES","LA_MSEG","RTDESC","LA_MSEG37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","LA_MSEG1","RTDESC","LA_MSEG138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","LA_MSEG2","RTDESC","LA_MSEG238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","LA_MSEQ","RTDESC","LA_MSEQ37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","LA_MSEQ1","RTDESC","LA_MSEQ138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","LA_MSEQ2","RTDESC","LA_MSEQ238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","LA_MSSC","RTDESC","LA_MSSC37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","LA_MSSC1","RTDESC","LA_MSSC138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","LA_MSSC2","RTDESC","LA_MSSC238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","LA_MSXX","RTDESC","LA_MSXX37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","LA_MSXX1","RTDESC","LA_MSXX138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","LA_MSXX2","RTDESC","LA_MSXX238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","LL_ADMN","RTDESC","LL_ADMN37895",134.15048076923077,"2003-10-01"]
["LCLSRAT4","LCLS RATES","LL_ADMN1","RTDESC","LL_ADMN138626",134.15048076923077,"2005-10-01"]
["LCLSRAT4","LCLS RATES","LL_ADMN2","RTDESC","LL_ADMN238991",134.15048076923077,"2006-10-01"]
["LCLSRAT4","LCLS RATES","LL_AW1","RTDESC","LL_AW138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","LL_AW2","RTDESC","LL_AW238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","LL_AWARD","RTDESC","LL_AWARD37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","LL_AWXX","RTDESC","LL_AWXX37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","LL_AWXX1","RTDESC","LL_AWXX138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","LL_AWXX2","RTDESC","LL_AWXX238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","LL_CE","RTDESC","LL_CE37895",176.59423076923076,"2003-10-01"]
["LCLSRAT4","LCLS RATES","LL_CE1","RTDESC","LL_CE138626",176.59423076923076,"2005-10-01"]
["LCLSRAT4","LCLS RATES","LL_CE2","RTDESC","LL_CE238991",176.59423076923076,"2006-10-01"]
["LCLSRAT4","LCLS RATES","LL_CP","RTDESC","LL_CP37895",189.60865384615386,"2003-10-01"]
["LCLSRAT4","LCLS RATES","LL_CP1","RTDESC","LL_CP138626",189.60865384615386,"2005-10-01"]
["LCLSRAT4","LCLS RATES","LL_CP2","RTDESC","LL_CP238991",189.60865384615386,"2006-10-01"]
["LCLSRAT4","LCLS RATES","LL_CT","RTDESC","LL_CT37895",137.21778846153848,"2003-10-01"]
["LCLSRAT4","LCLS RATES","LL_CT1","RTDESC","LL_CT138626",137.21778846153848,"2005-10-01"]
["LCLSRAT4","LCLS RATES","LL_CT2","RTDESC","LL_CT238991",137.21778846153848,"2006-10-01"]
["LCLSRAT4","LCLS RATES","LL_EE","RTDESC","LL_EE37895",176.59423076923076,"2003-10-01"]
["LCLSRAT4","LCLS RATES","LL_EE1","RTDESC","LL_EE138626",176.59423076923076,"2005-10-01"]
["LCLSRAT4","LCLS RATES","LL_EE2","RTDESC","LL_EE238991",176.59423076923076,"2006-10-01"]
["LCLSRAT4","LCLS RATES","LL_LABOR","RTDESC","LL_LABOR37865",0,"2003-09-01"]
["LCLSRAT4","LCLS RATES","LL_MDD","RTDESC","LL_MDD37895",162.0105769230769,"2003-10-01"]
["LCLSRAT4","LCLS RATES","LL_MDD1","RTDESC","LL_MDD138626",162.0105769230769,"2005-10-01"]
["LCLSRAT4","LCLS RATES","LL_MDD2","RTDESC","LL_MDD238991",162.0105769230769,"2006-10-01"]
["LCLSRAT4","LCLS RATES","LL_ME","RTDESC","LL_ME37895",176.59423076923076,"2003-10-01"]
["LCLSRAT4","LCLS RATES","LL_ME1","RTDESC","LL_ME138626",176.59423076923076,"2005-10-01"]
["LCLSRAT4","LCLS RATES","LL_ME2","RTDESC","LL_ME238991",176.59423076923076,"2006-10-01"]
["LCLSRAT4","LCLS RATES","LL_MFAT","RTDESC","LL_MFAT37895",137.21778846153848,"2003-10-01"]
["LCLSRAT4","LCLS RATES","LL_MFAT1","RTDESC","LL_MFAT138626",137.21778846153848,"2005-10-01"]
["LCLSRAT4","LCLS RATES","LL_MFAT2","RTDESC","LL_MFAT238991",137.21778846153848,"2006-10-01"]
["LCLSRAT4","LCLS RATES","LL_MSCS","RTDESC","LL_MSCS37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","LL_MSCS1","RTDESC","LL_MSCS138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","LL_MSCS2","RTDESC","LL_MSCS238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","LL_MSEG","RTDESC","LL_MSEG37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","LL_MSEG1","RTDESC","LL_MSEG138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","LL_MSEG2","RTDESC","LL_MSEG238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","LL_MSEQ","RTDESC","LL_MSEQ37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","LL_MSEQ1","RTDESC","LL_MSEQ138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","LL_MSEQ2","RTDESC","LL_MSEQ238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","LL_MSPS","RTDESC","LL_MSPS37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","LL_MSPS1","RTDESC","LL_MSPS138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","LL_MSPS2","RTDESC","LL_MSPS238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","LL_MSSC","RTDESC","LL_MSSC37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","LL_MSSC1","RTDESC","LL_MSSC138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","LL_MSSC2","RTDESC","LL_MSSC238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","LL_MSTR","RTDESC","LL_MSTR37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","LL_MSTR1","RTDESC","LL_MSTR138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","LL_MSTR2","RTDESC","LL_MSTR238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","LL_MSXX","RTDESC","LL_MSXX37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","LL_MSXX1","RTDESC","LL_MSXX138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","LL_MSXX2","RTDESC","LL_MSXX238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","LL_MTRL","RTDESC","LL_MTRL37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","LL_MTRL1","RTDESC","LL_MTRL138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","LL_MTRL2","RTDESC","LL_MTRL238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","LL_OH","RTDESC","LL_OH37895",0.19,"2003-10-01"]
["LCLSRAT4","LCLS RATES","LL_OH2","RTDESC","LL_OH238930",0.11,"2006-08-01"]
["LCLSRAT4","LCLS RATES","LL_PCCA","RTDESC","LL_PCCA37895",158.32548076923078,"2003-10-01"]
["LCLSRAT4","LCLS RATES","LL_PCCA1","RTDESC","LL_PCCA138626",158.32548076923078,"2005-10-01"]
["LCLSRAT4","LCLS RATES","LL_PCCA2","RTDESC","LL_PCCA238991",158.32548076923078,"2006-10-01"]
["LCLSRAT4","LCLS RATES","LL_PHS","RTDESC","LL_PHS37895",188.69326923076923,"2003-10-01"]
["LCLSRAT4","LCLS RATES","LL_PHS1","RTDESC","LL_PHS138626",188.69326923076923,"2005-10-01"]
["LCLSRAT4","LCLS RATES","LL_PHS2","RTDESC","LL_PHS238991",188.69326923076923,"2006-10-01"]
["LCLSRAT4","LCLS RATES","LL_PHSS","RTDESC","LL_PHSS37895",208.3653846153846,"2003-10-01"]
["LCLSRAT4","LCLS RATES","LL_PHSS1","RTDESC","LL_PHSS138626",208.3653846153846,"2005-10-01"]
["LCLSRAT4","LCLS RATES","LL_PHSS2","RTDESC","LL_PHSS238991",208.3653846153846,"2006-10-01"]
["LCLSRAT4","LCLS RATES","LL_PRC","RTDESC","LL_PRC37895",162.0105769230769,"2003-10-01"]
["LCLSRAT4","LCLS RATES","LL_PRC1","RTDESC","LL_PRC138626",162.0105769230769,"2005-10-01"]
["LCLSRAT4","LCLS RATES","LL_PRC2","RTDESC","LL_PRC238991",162.0105769230769,"2006-10-01"]
["LCLSRAT4","LCLS RATES","LL_PRE","RTDESC","LL_PRE37895",176.59423076923076,"2003-10-01"]
["LCLSRAT4","LCLS RATES","LL_PRE1","RTDESC","LL_PRE138626",176.59423076923076,"2005-10-01"]
["LCLSRAT4","LCLS RATES","LL_PRE2","RTDESC","LL_PRE238991",176.59423076923076,"2006-10-01"]
["LCLSRAT4","LCLS RATES","LL_SEE","RTDESC","LL_SEE37895",176.59423076923076,"2003-10-01"]
["LCLSRAT4","LCLS RATES","LL_SEE1","RTDESC","LL_SEE138626",176.59423076923076,"2005-10-01"]
["LCLSRAT4","LCLS RATES","LL_SEE2","RTDESC","LL_SEE238991",176.59423076923076,"2006-10-01"]
["LCLSRAT4","LCLS RATES","NON_LABOR","RTDESC","NON_LABOR38231",0,"2004-09-01"]
["LCLSRAT4","LCLS RATES","SA_GCFX1","RTDESC","SA_GCFX138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SA_GCFX2","RTDESC","SA_GCFX238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SA_GCSS","RTDESC","SA_GCSS38625",1,"2005-09-30"]
["LCLSRAT4","LCLS RATES","SA_GCSS1","RTDESC","SA_GCSS138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SA_GCSS2","RTDESC","SA_GCSS238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SA_GCSX","RTDESC","SA_GCSX38625",1,"2005-09-30"]
["LCLSRAT4","LCLS RATES","SA_GCSX1","RTDESC","SA_GCSX138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SA_GCSX2","RTDESC","SA_GCSX238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SA_MSEG","RTDESC","SA_MSEG37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SA_MSEG1","RTDESC","SA_MSEG138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SA_MSEG2","RTDESC","SA_MSEG238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SA_MSEQ","RTDESC","SA_MSEQ37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SA_MSEQ1","RTDESC","SA_MSEQ138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SA_MSEQ2","RTDESC","SA_MSEQ238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SA_MSPF","RTDESC","SA_MSPF37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SA_MSPF1","RTDESC","SA_MSPF138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SA_MSPF2","RTDESC","SA_MSPF238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SA_MSPS","RTDESC","SA_MSPS37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SA_MSPS1","RTDESC","SA_MSPS138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SA_MSPS2","RTDESC","SA_MSPS238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SA_MSPX","RTDESC","SA_MSPX37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SA_MSPX1","RTDESC","SA_MSPX138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SA_MSPX2","RTDESC","SA_MSPX238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SA_MSPY","RTDESC","SA_MSPY37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SA_MSPY1","RTDESC","SA_MSPY138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SA_MSPY2","RTDESC","SA_MSPY238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SA_MSSC","RTDESC","SA_MSSC37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SA_MSSC1","RTDESC","SA_MSSC138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SA_MSSC2","RTDESC","SA_MSSC238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SA_MSSF","RTDESC","SA_MSSF37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SA_MSSF1","RTDESC","SA_MSSF138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SA_MSSF2","RTDESC","SA_MSSF238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SA_MSSY","RTDESC","SA_MSSY37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SA_MSSY1","RTDESC","SA_MSSY138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SA_MSSY2","RTDESC","SA_MSSY238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SA_MSXX","RTDESC","SA_MSXX37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SA_MSXX1","RTDESC","SA_MSXX138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SA_MSXX2","RTDESC","SA_MSXX238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_ADMN","RTDESC","SL_ADMN37895",30.1731,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_ADMN1","RTDESC","SL_ADMN138626",30.1731,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_ADMN2","RTDESC","SL_ADMN238991",30.1731,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_AW1","RTDESC","SL_AW138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_AW2","RTDESC","SL_AW238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_AWARD","RTDESC","SL_AWARD37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_AWFX","RTDESC","SL_AWFX37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_AWFX1","RTDESC","SL_AWFX138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_AWFX2","RTDESC","SL_AWFX238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_AWFY","RTDESC","SL_AWFY37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_AWFY1","RTDESC","SL_AWFY138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_AWFY2","RTDESC","SL_AWFY238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_AWGC","RTDESC","SL_AWGC38625",1,"2005-09-30"]
["LCLSRAT4","LCLS RATES","SL_AWGC1","RTDESC","SL_AWGC138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_AWGC2","RTDESC","SL_AWGC238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_AWGX","RTDESC","SL_AWGX38625",1,"2005-09-30"]
["LCLSRAT4","LCLS RATES","SL_AWGX1","RTDESC","SL_AWGX138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_AWGX2","RTDESC","SL_AWGX238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_AWXX","RTDESC","SL_AWXX37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_AWXX1","RTDESC","SL_AWXX138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_AWXX2","RTDESC","SL_AWXX238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_CCA","RTDESC","SL_CCA37895",33.86,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_CCA1","RTDESC","SL_CCA138626",33.86,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_CCA2","RTDESC","SL_CCA238991",33.86,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_CE","RTDESC","SL_CE37895",58.14,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_CE1","RTDESC","SL_CE138626",58.14,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_CE2","RTDESC","SL_CE238991",58.14,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_CP","RTDESC","SL_CP37895",47.01,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_CP1","RTDESC","SL_CP138626",42.39,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_CP2","RTDESC","SL_CP238991",42.39,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_CPM","RTDESC","SL_CPM37895",30.93,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_CPM1","RTDESC","SL_CPM138626",30.93,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_CPM2","RTDESC","SL_CPM238991",30.93,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_CRA","RTDESC","SL_CRA37895",24.14,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_CRA1","RTDESC","SL_CRA138626",27.19,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_CRA2","RTDESC","SL_CRA238991",27.19,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_CRM","RTDESC","SL_CRM37895",30.93,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_CRM1","RTDESC","SL_CRM138626",30.93,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_CRM2","RTDESC","SL_CRM239203",59.74,"2007-05-01"]
["LCLSRAT4","LCLS RATES","SL_CT","RTDESC","SL_CT37895",31.83,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_CT1","RTDESC","SL_CT138626",31.83,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_CT2","RTDESC","SL_CT238991",31.83,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_EE","RTDESC","SL_EE37895",58.14,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_EE1","RTDESC","SL_EE138626",47.95,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_EE2","RTDESC","SL_EE238991",47.95,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_ESH2","RTDESC","SL_ESH238991",65.71,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_FA","RTDESC","SL_FA37895",40.7,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_FA","RTDESC","SL_FA38687",45.37,"2005-12-01"]
["LCLSRAT4","LCLS RATES","SL_FA1","RTDESC","SL_FA138626",46.24,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_FA2","RTDESC","SL_FA238991",46.24,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_FRING1","RTDESC","SL_FRING137904",1,"2003-10-10"]
["LCLSRAT4","LCLS RATES","SL_FRING2","RTDESC","SL_FRING238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_FRNG1","RTDESC","SL_FRNG138626",0.305,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_FRNG2","RTDESC","SL_FRNG238991",0.305,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_FRNGE","RTDESC","SL_FRNGE37895",0.29,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_FRNGX","RTDESC","SL_FRNGX37895",0,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_GCFX1","RTDESC","SL_GCFX138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_GCFX2","RTDESC","SL_GCFX238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_GCSS","RTDESC","SL_GCSS38625",1,"2005-09-30"]
["LCLSRAT4","LCLS RATES","SL_GCSS1","RTDESC","SL_GCSS138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_GCSS2","RTDESC","SL_GCSS238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_GCSX","RTDESC","SL_GCSX38625",1,"2005-09-30"]
["LCLSRAT4","LCLS RATES","SL_GCSX1","RTDESC","SL_GCSX138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_GCSX2","RTDESC","SL_GCSX238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS37803",0.00624687656171914,"2003-07-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS37895",0.00624687656171914,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS37956",0.00624687656171914,"2003-12-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38047",0.00624687656171914,"2004-03-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38412",0.00624687656171914,"2005-03-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38565",0.00624687656171914,"2005-08-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38777",0.00624687656171914,"2006-03-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38930",0.00624687656171914,"2006-08-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39295",0.00624687656171914,"2007-08-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39356",0.00624687656171914,"2007-10-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39722",0.00624687656171914,"2008-10-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39995",0.00624687656171914,"2009-07-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS40056",0.00624687656171914,"2009-08-31"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS37712",0.006530825496342738,"2003-04-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS37742",0.006530825496342738,"2003-05-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS37865",0.006530825496342738,"2003-09-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38078",0.006530825496342738,"2004-04-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38139",0.006530825496342738,"2004-06-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38200",0.006530825496342738,"2004-08-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38504",0.006530825496342738,"2005-06-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38838",0.006530825496342738,"2006-05-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38869",0.006530825496342738,"2006-06-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38991",0.006530825496342738,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39142",0.006530825496342738,"2007-03-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39203",0.006530825496342738,"2007-05-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39539",0.006530825496342738,"2008-04-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39630",0.006530825496342738,"2008-07-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39783",0.006530825496342738,"2008-12-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39873",0.006530825496342738,"2009-03-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39904",0.006530825496342738,"2009-04-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39965",0.006530825496342738,"2009-06-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS40087",0.006530825496342738,"2009-10-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS40148",0.006530825496342738,"2009-12-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS37681",0.006841817186644773,"2003-03-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS37773",0.006841817186644773,"2003-06-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS37834",0.006841817186644773,"2003-08-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38169",0.006841817186644773,"2004-07-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38231",0.006841817186644773,"2004-09-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38261",0.006841817186644773,"2004-10-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38443",0.006841817186644773,"2005-04-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38473",0.006841817186644773,"2005-05-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38596",0.006841817186644773,"2005-09-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38626",0.006841817186644773,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38687",0.006841817186644773,"2005-12-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39083",0.006841817186644773,"2007-01-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39173",0.006841817186644773,"2007-04-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39234",0.006841817186644773,"2007-06-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39264",0.006841817186644773,"2007-07-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39448",0.006841817186644773,"2008-01-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39508",0.006841817186644773,"2008-03-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39569",0.006841817186644773,"2008-05-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39600",0.006841817186644773,"2008-06-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39661",0.006841817186644773,"2008-08-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39692",0.006841817186644773,"2008-09-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39814",0.006841817186644773,"2009-01-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39934",0.006841817186644773,"2009-05-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS40118",0.006841817186644773,"2009-11-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS37653",0.007183908045977012,"2003-02-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS37926",0.007183908045977012,"2003-11-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS37987",0.007183908045977012,"2004-01-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38108",0.007183908045977012,"2004-05-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38292",0.007183908045977012,"2004-11-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38322",0.007183908045977012,"2004-12-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38353",0.007183908045977012,"2005-01-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38534",0.007183908045977012,"2005-07-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38657",0.007183908045977012,"2005-11-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38718",0.007183908045977012,"2006-01-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38808",0.007183908045977012,"2006-04-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38899",0.007183908045977012,"2006-07-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38961",0.007183908045977012,"2006-09-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39022",0.007183908045977012,"2006-11-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39052",0.007183908045977012,"2006-12-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39387",0.007183908045977012,"2007-11-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39417",0.007183908045977012,"2007-12-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39479",0.007183908045977012,"2008-02-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39845",0.007183908045977012,"2009-02-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS40026",0.007183908045977012,"2009-08-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38018",0.007562008469449486,"2004-02-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38384",0.007562008469449486,"2005-02-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38749",0.007562008469449486,"2006-02-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39114",0.007562008469449486,"2007-02-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39326",0.007562008469449486,"2007-09-01"]
["LCLSRAT4","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39753",0.007982120051085569,"2008-11-01"]
["LCLSRAT4","LCLS RATES","SL_IPM","RTDESC","SL_IPM37895",54.62,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_IPM1","RTDESC","SL_IPM138626",54.62,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_IPM2","RTDESC","SL_IPM238991",54.62,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_KCA","RTDESC","SL_KCA37895",33.86,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_KCA1","RTDESC","SL_KCA138626",33.86,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_KCA2","RTDESC","SL_KCA238991",33.86,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_KE","RTDESC","SL_KE37895",58.14,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_KE1","RTDESC","SL_KE138626",58.14,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_KE2","RTDESC","SL_KE238991",58.14,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_KT","RTDESC","SL_KT37895",31.83,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_KT1","RTDESC","SL_KT138626",31.83,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_KT2","RTDESC","SL_KT238991",31.83,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_LEAV1","RTDESC","SL_LEAV137895",0,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_LEAV2","RTDESC","SL_LEAV238626",0.21,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_LEAVE","RTDESC","SL_LEAVE37895",0.215,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_LEAVX","RTDESC","SL_LEAVX37895",0,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_LPM","RTDESC","SL_LPM37895",54.62,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_LPM1","RTDESC","SL_LPM138626",54.62,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_LPM2","RTDESC","SL_LPM238991",54.62,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_MDD","RTDESC","SL_MDD37895",32.42,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_MDD1","RTDESC","SL_MDD138626",43.07,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_MDD2","RTDESC","SL_MDD238991",43.07,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_ME","RTDESC","SL_ME37895",54.62,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_ME1","RTDESC","SL_ME138626",51.37,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_ME2","RTDESC","SL_ME238991",51.37,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_MES","RTDESC","SL_MES37895",46.68,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_MES1","RTDESC","SL_MES138626",41.3,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_MES2","RTDESC","SL_MES238991",41.3,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_MFAT","RTDESC","SL_MFAT37895",66.3,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_MFAT1","RTDESC","SL_MFAT138626",70,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_MFAT2","RTDESC","SL_MFAT238991",70,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_MFMS","RTDESC","SL_MFMS37895",81.3,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_MFMS1","RTDESC","SL_MFMS138626",89.59,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_MFMS2","RTDESC","SL_MFMS238991",89.59,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_MFPC","RTDESC","SL_MFPC37895",129.8,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_MFPC1","RTDESC","SL_MFPC138626",140.65,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_MFPC2","RTDESC","SL_MFPC238991",140.65,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSCS","RTDESC","SL_MSCS37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSCS1","RTDESC","SL_MSCS138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSCS2","RTDESC","SL_MSCS238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSEG","RTDESC","SL_MSEG37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSEG1","RTDESC","SL_MSEG138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSEG2","RTDESC","SL_MSEG238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSEQ","RTDESC","SL_MSEQ37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSEQ1","RTDESC","SL_MSEQ138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSEQ2","RTDESC","SL_MSEQ238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSPF","RTDESC","SL_MSPF37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSPF1","RTDESC","SL_MSPF138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSPF2","RTDESC","SL_MSPF238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSPS","RTDESC","SL_MSPS37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSPS1","RTDESC","SL_MSPS138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSPS2","RTDESC","SL_MSPS238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSPX","RTDESC","SL_MSPX37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSPX1","RTDESC","SL_MSPX138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSPX2","RTDESC","SL_MSPX238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSPY","RTDESC","SL_MSPY37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSPY1","RTDESC","SL_MSPY138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSPY2","RTDESC","SL_MSPY238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSSC","RTDESC","SL_MSSC37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSSC1","RTDESC","SL_MSSC138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSSC2","RTDESC","SL_MSSC238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSSF","RTDESC","SL_MSSF37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSSF1","RTDESC","SL_MSSF138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSSF2","RTDESC","SL_MSSF238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSSY","RTDESC","SL_MSSY37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSSY1","RTDESC","SL_MSSY138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSSY2","RTDESC","SL_MSSY238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSTR","RTDESC","SL_MSTR37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSTR1","RTDESC","SL_MSTR138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSTR2","RTDESC","SL_MSTR238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSXX","RTDESC","SL_MSXX37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSXX1","RTDESC","SL_MSXX138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_MSXX2","RTDESC","SL_MSXX238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_MTRL","RTDESC","SL_MTRL37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_MTRL1","RTDESC","SL_MTRL138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_MTRL2","RTDESC","SL_MTRL238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_MVE","RTDESC","SL_MVE37895",54.62,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_MVE1","RTDESC","SL_MVE138626",54.62,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_MVE2","RTDESC","SL_MVE238991",54.62,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_OE","RTDESC","SL_OE37895",58.14,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_OE1","RTDESC","SL_OE138626",58.14,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_OE2","RTDESC","SL_OE238991",58.14,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_OH1","RTDESC","SL_OH137895",0.2,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_OH2","RTDESC","SL_OH237895",0.06,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_OH2","RTDESC","SL_OH238991",0.2,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_OH3","RTDESC","SL_OH337895",0.36,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_OH4","RTDESC","SL_OH437895",0.068,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_OHN","RTDESC","SL_OHN37904",0,"2003-10-10"]
["LCLSRAT4","LCLS RATES","SL_OHN1","RTDESC","SL_OHN137895",0.2,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_OHN2","RTDESC","SL_OHN237895",0.048,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_OHN2","RTDESC","SL_OHN238991",0.2,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_OHN3","RTDESC","SL_OHN337895",0.38,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_OHN4","RTDESC","SL_OHN437895",0.0552,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_OT","RTDESC","SL_OT37895",31.83,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_OT1","RTDESC","SL_OT138626",31.83,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_OT2","RTDESC","SL_OT238991",31.83,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_PCCA","RTDESC","SL_PCCA37895",33.86,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_PCCA1","RTDESC","SL_PCCA138626",33.86,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_PCCA2","RTDESC","SL_PCCA238991",33.86,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_PCE","RTDESC","SL_PCE37895",58.14,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_PCE1","RTDESC","SL_PCE138626",58.14,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_PCE2","RTDESC","SL_PCE238991",58.14,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_PCEF","RTDESC","SL_PCEF37895",31.83,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_PCEF1","RTDESC","SL_PCEF138626",31.83,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_PCEF2","RTDESC","SL_PCEF238991",31.83,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_PCT","RTDESC","SL_PCT37895",31.83,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_PCT1","RTDESC","SL_PCT138626",31.83,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_PCT2","RTDESC","SL_PCT238991",31.83,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_PEX","RTDESC","SL_PEX37895",40.7,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_PEX1","RTDESC","SL_PEX138626",40.7,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_PEX2","RTDESC","SL_PEX238991",40.7,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_PHH","RTDESC","SL_PHH37895",45.68,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_PHH1","RTDESC","SL_PHH138626",49.4,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_PHH2","RTDESC","SL_PHH238991",49.4,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_PHPD","RTDESC","SL_PHPD37895",36.17,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_PHPD1","RTDESC","SL_PHPD138626",36.17,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_PHPD2","RTDESC","SL_PHPD238991",36.17,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_PHPU","RTDESC","SL_PHPU38626",63.33,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_PHPU2","RTDESC","SL_PHPU238991",63.33,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_PHS","RTDESC","SL_PHS37895",37.62,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_PHS1","RTDESC","SL_PHS138626",37.62,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_PHS2","RTDESC","SL_PHS238991",37.62,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_PHSS","RTDESC","SL_PHSS37895",47.88,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_PHSS1","RTDESC","SL_PHSS138626",47.88,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_PHSS2","RTDESC","SL_PHSS238991",47.88,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_PM","RTDESC","SL_PM37895",63.8,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_PM","RTDESC","SL_PM38687",83.63,"2005-12-01"]
["LCLSRAT4","LCLS RATES","SL_PM1","RTDESC","SL_PM138626",83.63,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_PM2","RTDESC","SL_PM238991",83.63,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_POWB","RTDESC","SL_POWB37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_POWB1","RTDESC","SL_POWB138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_POWB2","RTDESC","SL_POWB238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_QAO","RTDESC","SL_QAO37895",54.62,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_QAO1","RTDESC","SL_QAO138626",35.53,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_QAO2","RTDESC","SL_QAO239203",59.74,"2007-05-01"]
["LCLSRAT4","LCLS RATES","SL_SEE","RTDESC","SL_SEE37895",54.62,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_SEE1","RTDESC","SL_SEE138626",54.62,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_SEE2","RTDESC","SL_SEE238991",54.62,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_SEEM","RTDESC","SL_SEEM37895",54.62,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_SEEM1","RTDESC","SL_SEEM138626",54.62,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_SEEM2","RTDESC","SL_SEEM238991",54.62,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_SEL","RTDESC","SL_SEL37895",38,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_SEL1","RTDESC","SL_SEL138626",38,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_SEL2","RTDESC","SL_SEL238991",38,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_SEPM","RTDESC","SL_SEPM37895",32.28,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_SEPM1","RTDESC","SL_SEPM138626",32.28,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_SEPM2","RTDESC","SL_SEPM238991",32.28,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_SRA","RTDESC","SL_SRA37895",20.83,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_SRA1","RTDESC","SL_SRA138626",20.83,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_SRA2","RTDESC","SL_SRA238991",20.83,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_STUP","RTDESC","SL_STUP37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_STUP1","RTDESC","SL_STUP138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_STUP2","RTDESC","SL_STUP238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_TMUC","RTDESC","SL_TMUC37895",60.55,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_TMUC1","RTDESC","SL_TMUC138626",60.55,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_TMUC2","RTDESC","SL_TMUC238991",60.55,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_TMUE","RTDESC","SL_TMUE37895",77.99,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_TMUE1","RTDESC","SL_TMUE138626",77.99,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_TMUE2","RTDESC","SL_TMUE238991",77.99,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_TMUI","RTDESC","SL_TMUI37895",61.62,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_TMUI1","RTDESC","SL_TMUI138626",61.62,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_TMUI2","RTDESC","SL_TMUI238991",61.62,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_TMUO","RTDESC","SL_TMUO37895",64.45,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_TMUO1","RTDESC","SL_TMUO138626",64.45,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_TMUO2","RTDESC","SL_TMUO238991",64.45,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_TMUP","RTDESC","SL_TMUP37895",74.69,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_TMUP1","RTDESC","SL_TMUP138626",74.69,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_TMUP2","RTDESC","SL_TMUP238991",74.69,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_TMUW","RTDESC","SL_TMUW37895",61.62,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_TMUW1","RTDESC","SL_TMUW138626",61.62,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_TMUW2","RTDESC","SL_TMUW238991",61.62,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_TSM","RTDESC","SL_TSM37895",54.62,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_TSM1","RTDESC","SL_TSM138626",54.62,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_TSM2","RTDESC","SL_TSM238991",54.62,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_UPGR","RTDESC","SL_UPGR37895",1,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_UPGR1","RTDESC","SL_UPGR138626",1,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_UPGR2","RTDESC","SL_UPGR238991",1,"2006-10-01"]
["LCLSRAT4","LCLS RATES","SL_UTR","RTDESC","SL_UTR37895",54.62,"2003-10-01"]
["LCLSRAT4","LCLS RATES","SL_UTR1","RTDESC","SL_UTR138626",54.62,"2005-10-01"]
["LCLSRAT4","LCLS RATES","SL_UTR2","RTDESC","SL_UTR238991",54.62,"2006-10-01"]
["LCLSRAT4","LCLS RATES","TRAVEL","RTDESC","TRAVEL38231",0,"2004-09-01"]

{"sheet":"opcclc","index":1,"n_rows":2609,"n_cols":14,"rows_kept":2609,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["OPC4CLC ","OPC4CLC ","OPC4CLC ","OPC4CLC ","OPC4CLC ","OPC4CLC ","OPC4CLC ","OPC4CLC ","OPC4CLC ","OPC4CLC ","OPC4CLC ","OPC4CLC ","OPC4CLC ","OPC4CLC "]
["AA_MSEG","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AA_MSEG","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AA_MSEG","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AA_MSEG","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AA_MSEG","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AA_MSEG","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AA_MSEG1","ESC1","AN_CS6","AN_GA2",null,"2005-10-01","ESC138626",null,1,0,0.064,0.026,null,1.0916640000000002]
["AA_MSEG1","ESC1","AN_CS6","AN_GA2",null,"2006-10-01","ESC138991",null,1,0.026,0.064,0.026,null,1.1200472640000003]
["AA_MSEG1","ESC1","AN_CS6","AN_GA2",null,"2007-10-01","ESC139356",null,1,0.052676,0.064,0.026,null,1.149168492864]
["AA_MSEG1","ESC1","AN_CS6","AN_GA2",null,"2008-10-01","ESC139722",null,1,0.08004558,0.064,0.026,null,1.17904687804512]
["AA_MSEG2","ESC2","AN_CS6","AN_GA2",null,"2006-10-01","ESC238991",null,1,0.023,0.064,0.026,null,1.116772272]
["AA_MSEG2","ESC2","AN_CS6","AN_GA2",null,"2007-10-01","ESC239356",null,1,0.046529,0.064,0.026,null,1.1424580342560002]
["AA_MSEG2","ESC2","AN_CS6","AN_GA2",null,"2008-10-01","ESC239722",null,1,0.070599,0.064,0.026,null,1.1687343867360003]
["AA_MSEG2","ESC2","AN_CS6","AN_GA2",null,"2009-10-01","ESC240087",null,1,0.095223,0.064,0.026,null,1.195615521072]
["AA_MSEG2","ESC2","AN_CS6","AN_GA2",null,"2010-10-01","ESC240452",null,1,0.120413,0.064,0.026,null,1.2231145372320003]
["AA_MSEG2","ESC2","AN_CS6","AN_GA2",null,"2011-10-01","ESC240817",null,1,0.120413,0.064,0.026,null,1.2231145372320003]
["AA_MSEG2","ESC2","AN_CS6","AN_GA2",null,"2012-10-01","ESC241183",null,1,null,0.064,0.026,null,1.0916640000000002]
["AA_MSEQ","ESC","AN_OH4",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AA_MSEQ","ESC","AN_OH4",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AA_MSEQ","ESC","AN_OH4",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AA_MSEQ","ESC","AN_OH4",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AA_MSEQ","ESC","AN_OH4",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AA_MSEQ","ESC","AN_OH4",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AA_MSEQ1","ESC1","AN_CS6","AN_GA2",null,"2005-10-01","ESC138626",null,1,0,0.064,0.026,null,1.0916640000000002]
["AA_MSEQ1","ESC1","AN_CS6","AN_GA2",null,"2006-10-01","ESC138991",null,1,0.026,0.064,0.026,null,1.1200472640000003]
["AA_MSEQ1","ESC1","AN_CS6","AN_GA2",null,"2007-10-01","ESC139356",null,1,0.052676,0.064,0.026,null,1.149168492864]
["AA_MSEQ1","ESC1","AN_CS6","AN_GA2",null,"2008-10-01","ESC139722",null,1,0.08004558,0.064,0.026,null,1.17904687804512]
["AA_MSEQ2","ESC2","AN_CS6","AN_GA2",null,"2006-10-01","ESC238991",null,1,0.023,0.064,0.026,null,1.116772272]
["AA_MSEQ2","ESC2","AN_CS6","AN_GA2",null,"2007-10-01","ESC239356",null,1,0.046529,0.064,0.026,null,1.1424580342560002]
["AA_MSEQ2","ESC2","AN_CS6","AN_GA2",null,"2008-10-01","ESC239722",null,1,0.070599,0.064,0.026,null,1.1687343867360003]
["AA_MSEQ2","ESC2","AN_CS6","AN_GA2",null,"2009-10-01","ESC240087",null,1,0.095223,0.064,0.026,null,1.195615521072]
["AA_MSEQ2","ESC2","AN_CS6","AN_GA2",null,"2010-10-01","ESC240452",null,1,0.120413,0.064,0.026,null,1.2231145372320003]
["AA_MSEQ2","ESC2","AN_CS6","AN_GA2",null,"2011-10-01","ESC240817",null,1,0.120413,0.064,0.026,null,1.2231145372320003]
["AA_MSEQ2","ESC2","AN_CS6","AN_GA2",null,"2012-10-01","ESC241183",null,1,null,0.064,0.026,null,1.0916640000000002]
["AA_MSPS","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,null,0,0,null,null,0]
["AA_MSPS","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,null,0.029,0,null,null,0]
["AA_MSPS","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,null,0.057812,0,null,null,0]
["AA_MSPS","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,null,0.085315,0,null,null,0]
["AA_MSPS","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,null,0.113533,0,null,null,0]
["AA_MSPS","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,null,0.142485,0,null,null,0]
["AA_MSSC","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AA_MSSC","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AA_MSSC","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AA_MSSC","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AA_MSSC","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AA_MSSC","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AA_MSSC1","ESC1","AN_CS6","AN_GA2",null,"2005-10-01","ESC138626",null,1,0,0.064,0.026,null,1.0916640000000002]
["AA_MSSC1","ESC1","AN_CS6","AN_GA2",null,"2006-10-01","ESC138991",null,1,0.026,0.064,0.026,null,1.1200472640000003]
["AA_MSSC1","ESC1","AN_CS6","AN_GA2",null,"2007-10-01","ESC139356",null,1,0.052676,0.064,0.026,null,1.149168492864]
["AA_MSSC1","ESC1","AN_CS6","AN_GA2",null,"2008-10-01","ESC139722",null,1,0.08004558,0.064,0.026,null,1.17904687804512]
["AA_MSSC2","ESC2","AN_CS6","AN_GA2",null,"2006-10-01","ESC238991",null,1,0.023,0.064,0.026,null,1.116772272]
["AA_MSSC2","ESC2","AN_CS6","AN_GA2",null,"2007-10-01","ESC239356",null,1,0.046529,0.064,0.026,null,1.1424580342560002]
["AA_MSSC2","ESC2","AN_CS6","AN_GA2",null,"2008-10-01","ESC239722",null,1,0.070599,0.064,0.026,null,1.1687343867360003]
["AA_MSSC2","ESC2","AN_CS6","AN_GA2",null,"2009-10-01","ESC240087",null,1,0.095223,0.064,0.026,null,1.195615521072]
["AA_MSSC2","ESC2","AN_CS6","AN_GA2",null,"2010-10-01","ESC240452",null,1,0.120413,0.064,0.026,null,1.2231145372320003]
["AA_MSSC2","ESC2","AN_CS6","AN_GA2",null,"2011-10-01","ESC240817",null,1,0.120413,0.064,0.026,null,1.2231145372320003]
["AA_MSSC2","ESC2","AN_CS6","AN_GA2",null,"2012-10-01","ESC241183",null,1,null,0.064,0.026,null,1.0916640000000002]
["AA_MSSF","AN_OH3",{"$nulls":4},"AN_OH3",null,1,{"$nulls":4},1]
["AA_MSSF1","AN_OH3",{"$nulls":4},"AN_OH3",null,1,{"$nulls":4},1]
["AA_MSSF2","AN_CS6","AN_GA2",null,null,null,"AN_CS6",null,1,0.064,0.026,null,null,1.0916640000000002]
["AA_MSXX","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["AA_MSXX","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["AA_MSXX","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["AA_MSXX","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["AA_MSXX","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["AA_MSXX","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["AN_ADMN","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,63.24,0,0.3224,null,null,83.62857600000001]
["AN_ADMN","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,63.24,0.029,0.3224,null,null,86.053804704]
["AN_ADMN","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,63.24,0.057812,0.3224,null,null,88.463311235712]
["AN_ADMN","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,63.24,0.085315,0.3224,null,null,90.76334796144]
["AN_ADMN","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,63.24,0.113533,0.3224,null,null,93.12317911900799]
["AN_ADMN","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,63.24,0.142485,0.3224,null,null,95.54439365136]
["AN_ADMN1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.292,0.026,0,110.70018792000002]
["AN_ADMN1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.292,0.026,0,113.57839280592002]
["AN_ADMN1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.292,0.026,0,116.53143101887393]
["AN_ADMN1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.292,0.026,0,119.5612486681654]
["AN_ADMN2","ESC2","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC238991",null,83.51,0.023,0.292,0.026,0,113.24629224216]
["AN_ADMN2","ESC2","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC239356",null,83.51,0.046529,0.292,0.026,0,115.8509569637297]
["AN_ADMN2","ESC2","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC239722",null,83.51,0.070599,0.292,0.026,0,118.51551048696412]
["AN_ADMN2","ESC2","AN_CS4","AN_GA2","AN_OH4","2009-10-01","ESC240087",null,83.51,0.095223,0.292,0.026,0,121.24139191430619]
["AN_ADMN2","ESC2","AN_CS4","AN_GA2","AN_OH4","2010-10-01","ESC240452",null,83.51,0.120413,0.292,0.026,0,124.02992964801098]
["AN_ADMN2","ESC2","AN_CS4","AN_GA2","AN_OH4","2011-10-01","ESC240817",null,83.51,0.120413,0.292,0.026,0,124.02992964801098]
["AN_ADMN2","ESC2","AN_CS4","AN_GA2","AN_OH4","2012-10-01","ESC241183",null,83.51,null,0.292,0.026,0,110.70018792000002]
["AN_AW1","ESC1","AN_CS6","AN_GA2",null,"2005-10-01","ESC138626",null,1,0,0.064,0.026,null,1.0916640000000002]
["AN_AW1","ESC1","AN_CS6","AN_GA2",null,"2006-10-01","ESC138991",null,1,0.026,0.064,0.026,null,1.1200472640000003]
["AN_AW1","ESC1","AN_CS6","AN_GA2",null,"2007-10-01","ESC139356",null,1,0.052676,0.064,0.026,null,1.149168492864]
["AN_AW1","ESC1","AN_CS6","AN_GA2",null,"2008-10-01","ESC139722",null,1,0.08004558,0.064,0.026,null,1.17904687804512]
["AN_AW2","ESC2","AN_CS6","AN_GA2",null,"2006-10-01","ESC238991",null,1,0.023,0.064,0.026,null,1.116772272]
["AN_AW2","ESC2","AN_CS6","AN_GA2",null,"2007-10-01","ESC239356",null,1,0.046529,0.064,0.026,null,1.1424580342560002]
["AN_AW2","ESC2","AN_CS6","AN_GA2",null,"2008-10-01","ESC239722",null,1,0.070599,0.064,0.026,null,1.1687343867360003]
["AN_AW2","ESC2","AN_CS6","AN_GA2",null,"2009-10-01","ESC240087",null,1,0.095223,0.064,0.026,null,1.195615521072]
["AN_AW2","ESC2","AN_CS6","AN_GA2",null,"2010-10-01","ESC240452",null,1,0.120413,0.064,0.026,null,1.2231145372320003]
["AN_AW2","ESC2","AN_CS6","AN_GA2",null,"2011-10-01","ESC240817",null,1,0.120413,0.064,0.026,null,1.2231145372320003]
["AN_AW2","ESC2","AN_CS6","AN_GA2",null,"2012-10-01","ESC241183",null,1,null,0.064,0.026,null,1.0916640000000002]
["AN_AWARD","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AN_AWARD","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AN_AWARD","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AN_AWARD","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AN_AWARD","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AN_AWARD","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AN_AWFX","AN_OH3",{"$nulls":4},"AN_OH3",{"$nulls":6},0]
["AN_AWXX","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["AN_AWXX","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["AN_AWXX","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["AN_AWXX","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["AN_AWXX","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["AN_AWXX","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["AN_CCA","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,67.43,0,0.3224,null,null,89.16943200000001]
["AN_CCA","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,67.43,0.029,0.3224,null,null,91.75534552799999]
["AN_CCA","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,67.43,0.057812,0.3224,null,null,94.32449520278401]
["AN_CCA","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,67.43,0.085315,0.3224,null,null,96.77692209108002]
["AN_CCA","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,67.43,0.113533,0.3224,null,null,99.293105123256]
["AN_CCA","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,67.43,0.142485,0.3224,null,null,101.87473851852002]
["AN_CCA1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.292,0.026,0,110.70018792000002]
["AN_CCA1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.292,0.026,0,113.57839280592002]
["AN_CCA1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.292,0.026,0,116.53143101887393]
["AN_CCA1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.292,0.026,0,119.5612486681654]
["AN_CCA2","ESC2","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC238991",null,83.51,0.023,0.292,0.026,0,113.24629224216]
["AN_CCA2","ESC2","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC239356",null,83.51,0.046529,0.292,0.026,0,115.8509569637297]
["AN_CCA2","ESC2","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC239722",null,83.51,0.070599,0.292,0.026,0,118.51551048696412]
["AN_CCA2","ESC2","AN_CS4","AN_GA2","AN_OH4","2009-10-01","ESC240087",null,83.51,0.095223,0.292,0.026,0,121.24139191430619]
["AN_CCA2","ESC2","AN_CS4","AN_GA2","AN_OH4","2010-10-01","ESC240452",null,83.51,0.120413,0.292,0.026,0,124.02992964801098]
["AN_CCA2","ESC2","AN_CS4","AN_GA2","AN_OH4","2011-10-01","ESC240817",null,83.51,0.120413,0.292,0.026,0,124.02992964801098]
["AN_CCA2","ESC2","AN_CS4","AN_GA2","AN_OH4","2012-10-01","ESC241183",null,83.51,null,0.292,0.026,0,110.70018792000002]
["AN_CE","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,67.43,0,0.3224,null,null,89.16943200000001]
["AN_CE","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,67.43,0.029,0.3224,null,null,91.75534552799999]
["AN_CE","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,67.43,0.057812,0.3224,null,null,94.32449520278401]
["AN_CE","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,67.43,0.085315,0.3224,null,null,96.77692209108002]
["AN_CE","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,67.43,0.113533,0.3224,null,null,99.293105123256]
["AN_CE","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,67.43,0.142485,0.3224,null,null,101.87473851852002]
["AN_CE1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.292,0.026,0,110.70018792000002]
["AN_CE1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.292,0.026,0,113.57839280592002]
["AN_CE1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.292,0.026,0,116.53143101887393]
["AN_CE1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.292,0.026,0,119.5612486681654]
["AN_CE2","ESC2","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC238991",null,83.51,0.023,0.292,0.026,0,113.24629224216]
["AN_CE2","ESC2","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC239356",null,83.51,0.046529,0.292,0.026,0,115.8509569637297]
["AN_CE2","ESC2","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC239722",null,83.51,0.070599,0.292,0.026,0,118.51551048696412]
["AN_CE2","ESC2","AN_CS4","AN_GA2","AN_OH4","2009-10-01","ESC240087",null,83.51,0.095223,0.292,0.026,0,121.24139191430619]
["AN_CE2","ESC2","AN_CS4","AN_GA2","AN_OH4","2010-10-01","ESC240452",null,83.51,0.120413,0.292,0.026,0,124.02992964801098]
["AN_CE2","ESC2","AN_CS4","AN_GA2","AN_OH4","2011-10-01","ESC240817",null,83.51,0.120413,0.292,0.026,0,124.02992964801098]
["AN_CE2","ESC2","AN_CS4","AN_GA2","AN_OH4","2012-10-01","ESC241183",null,83.51,null,0.292,0.026,0,110.70018792000002]
["AN_CP","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,67.43,0,0.3224,null,null,89.16943200000001]
["AN_CP","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,67.43,0.029,0.3224,null,null,91.75534552799999]
["AN_CP","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,67.43,0.057812,0.3224,null,null,94.32449520278401]
["AN_CP","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,67.43,0.085315,0.3224,null,null,96.77692209108002]
["AN_CP","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,67.43,0.113533,0.3224,null,null,99.293105123256]
["AN_CP","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,67.43,0.142485,0.3224,null,null,101.87473851852002]
["AN_CP1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.292,0.026,0,110.70018792000002]
["AN_CP1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.292,0.026,0,113.57839280592002]
["AN_CP1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.292,0.026,0,116.53143101887393]
["AN_CP1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.292,0.026,0,119.5612486681654]
["AN_CP2","ESC2","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC238991",null,83.51,0.023,0.292,0.026,0,113.24629224216]
["AN_CP2","ESC2","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC239356",null,83.51,0.046529,0.292,0.026,0,115.8509569637297]
["AN_CP2","ESC2","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC239722",null,83.51,0.070599,0.292,0.026,0,118.51551048696412]
["AN_CP2","ESC2","AN_CS4","AN_GA2","AN_OH4","2009-10-01","ESC240087",null,83.51,0.095223,0.292,0.026,0,121.24139191430619]
["AN_CP2","ESC2","AN_CS4","AN_GA2","AN_OH4","2010-10-01","ESC240452",null,83.51,0.120413,0.292,0.026,0,124.02992964801098]
["AN_CP2","ESC2","AN_CS4","AN_GA2","AN_OH4","2011-10-01","ESC240817",null,83.51,0.120413,0.292,0.026,0,124.02992964801098]
["AN_CP2","ESC2","AN_CS4","AN_GA2","AN_OH4","2012-10-01","ESC241183",null,83.51,null,0.292,0.026,0,110.70018792000002]
["AN_CT","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,42.99,0,0.3224,null,null,56.849976000000005]
["AN_CT","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,42.99,0.029,0.3224,null,null,58.498625303999994]
["AN_CT","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,42.99,0.057812,0.3224,null,null,60.136586812512]
["AN_CT","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,42.99,0.085315,0.3224,null,null,61.70013170244001]
["AN_CT","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,42.99,0.113533,0.3224,null,null,63.30432432520799]
["AN_CT","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,42.99,0.142485,0.3224,null,null,64.95024483036]
["AN_CT1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,49.03,0,0.292,0.026,0,64.99377576]
["AN_CT1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,49.03,0.026,0.292,0.026,0,66.68361392976001]
["AN_CT1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,49.03,0.052676,0.292,0.026,0,68.41738789193376]
["AN_CT1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,49.03,0.08004558,0.292,0.026,0,70.19624023709915]
["AN_CT2","ESC2","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC238991",null,49.03,0.023,0.292,0.026,0,66.48863260248]
["AN_CT2","ESC2","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC239356",null,49.03,0.046529,0.292,0.026,0,68.01787115233705]
["AN_CT2","ESC2","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC239722",null,49.03,0.070599,0.292,0.026,0,69.58227133488025]
["AN_CT2","ESC2","AN_CS4","AN_GA2","AN_OH4","2009-10-01","ESC240087",null,49.03,0.095223,0.292,0.026,0,71.1826780691945]
["AN_CT2","ESC2","AN_CS4","AN_GA2","AN_OH4","2010-10-01","ESC240452",null,49.03,0.120413,0.292,0.026,0,72.81987128058888]
["AN_CT2","ESC2","AN_CS4","AN_GA2","AN_OH4","2011-10-01","ESC240817",null,49.03,0.120413,0.292,0.026,0,72.81987128058888]
["AN_CT2","ESC2","AN_CS4","AN_GA2","AN_OH4","2012-10-01","ESC241183",null,49.03,null,0.292,0.026,0,64.99377576]
["AN_EE","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,67.43,0,0.3224,null,null,89.16943200000001]
["AN_EE","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,67.43,0.029,0.3224,null,null,91.75534552799999]
["AN_EE","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,67.43,0.057812,0.3224,null,null,94.32449520278401]
["AN_EE","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,67.43,0.085315,0.3224,null,null,96.77692209108002]
["AN_EE","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,67.43,0.113533,0.3224,null,null,99.293105123256]
["AN_EE","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,67.43,0.142485,0.3224,null,null,101.87473851852002]
["AN_EE1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.292,0.026,0,110.70018792000002]
["AN_EE1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.292,0.026,0,113.57839280592002]
["AN_EE1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.292,0.026,0,116.53143101887393]
["AN_EE1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.292,0.026,0,119.5612486681654]
["AN_EE2","ESC2","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC238991",null,83.51,0.023,0.292,0.026,0,113.24629224216]
["AN_EE2","ESC2","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC239356",null,83.51,0.046529,0.292,0.026,0,115.8509569637297]
["AN_EE2","ESC2","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC239722",null,83.51,0.070599,0.292,0.026,0,118.51551048696412]
["AN_EE2","ESC2","AN_CS4","AN_GA2","AN_OH4","2009-10-01","ESC240087",null,83.51,0.095223,0.292,0.026,0,121.24139191430619]
["AN_EE2","ESC2","AN_CS4","AN_GA2","AN_OH4","2010-10-01","ESC240452",null,83.51,0.120413,0.292,0.026,0,124.02992964801098]
["AN_EE2","ESC2","AN_CS4","AN_GA2","AN_OH4","2011-10-01","ESC240817",null,83.51,0.120413,0.292,0.026,0,124.02992964801098]
["AN_EE2","ESC2","AN_CS4","AN_GA2","AN_OH4","2012-10-01","ESC241183",null,83.51,null,0.292,0.026,0,110.70018792000002]
["AN_MDD","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,42.99,0,0.3224,null,null,56.849976000000005]
["AN_MDD","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,42.99,0.029,0.3224,null,null,58.498625303999994]
["AN_MDD","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,42.99,0.057812,0.3224,null,null,60.136586812512]
["AN_MDD","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,42.99,0.085315,0.3224,null,null,61.70013170244001]
["AN_MDD","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,42.99,0.113533,0.3224,null,null,63.30432432520799]
["AN_MDD","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,42.99,0.142485,0.3224,null,null,64.95024483036]
["AN_MDD1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,49.03,0,0.292,0.026,0,64.99377576]
["AN_MDD1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,49.03,0.026,0.292,0.026,0,66.68361392976001]
["AN_MDD1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,49.03,0.052676,0.292,0.026,0,68.41738789193376]
["AN_MDD1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,49.03,0.08004558,0.292,0.026,0,70.19624023709915]
["AN_MDD2","ESC2","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC238991",null,49.03,0.023,0.292,0.026,0,66.48863260248]
["AN_MDD2","ESC2","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC239356",null,49.03,0.046529,0.292,0.026,0,68.01787115233705]
["AN_MDD2","ESC2","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC239722",null,49.03,0.070599,0.292,0.026,0,69.58227133488025]
["AN_MDD2","ESC2","AN_CS4","AN_GA2","AN_OH4","2009-10-01","ESC240087",null,49.03,0.095223,0.292,0.026,0,71.1826780691945]
["AN_MDD2","ESC2","AN_CS4","AN_GA2","AN_OH4","2010-10-01","ESC240452",null,49.03,0.120413,0.292,0.026,0,72.81987128058888]
["AN_MDD2","ESC2","AN_CS4","AN_GA2","AN_OH4","2011-10-01","ESC240817",null,49.03,0.120413,0.292,0.026,0,72.81987128058888]
["AN_MDD2","ESC2","AN_CS4","AN_GA2","AN_OH4","2012-10-01","ESC241183",null,49.03,null,0.292,0.026,0,64.99377576]
["AN_ME","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,63.24,0,0.3224,null,null,83.62857600000001]
["AN_ME","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,63.24,0.029,0.3224,null,null,86.053804704]
["AN_ME","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,63.24,0.057812,0.3224,null,null,88.463311235712]
["AN_ME","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,63.24,0.085315,0.3224,null,null,90.76334796144]
["AN_ME","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,63.24,0.113533,0.3224,null,null,93.12317911900799]
["AN_ME","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,63.24,0.142485,0.3224,null,null,95.54439365136]
["AN_ME1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.292,0.026,0,110.70018792000002]
["AN_ME1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.292,0.026,0,113.57839280592002]
["AN_ME1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.292,0.026,0,116.53143101887393]
["AN_ME1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.292,0.026,0,119.5612486681654]
["AN_ME2","ESC2","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC238991",null,83.51,0.023,0.292,0.026,0,113.24629224216]
["AN_ME2","ESC2","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC239356",null,83.51,0.046529,0.292,0.026,0,115.8509569637297]
["AN_ME2","ESC2","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC239722",null,83.51,0.070599,0.292,0.026,0,118.51551048696412]
["AN_ME2","ESC2","AN_CS4","AN_GA2","AN_OH4","2009-10-01","ESC240087",null,83.51,0.095223,0.292,0.026,0,121.24139191430619]
["AN_ME2","ESC2","AN_CS4","AN_GA2","AN_OH4","2010-10-01","ESC240452",null,83.51,0.120413,0.292,0.026,0,124.02992964801098]
["AN_ME2","ESC2","AN_CS4","AN_GA2","AN_OH4","2011-10-01","ESC240817",null,83.51,0.120413,0.292,0.026,0,124.02992964801098]
["AN_ME2","ESC2","AN_CS4","AN_GA2","AN_OH4","2012-10-01","ESC241183",null,83.51,null,0.292,0.026,0,110.70018792000002]
["AN_MES","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,67.43,0,0.3224,null,null,89.16943200000001]
["AN_MES","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,67.43,0.029,0.3224,null,null,91.75534552799999]
["AN_MES","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,67.43,0.057812,0.3224,null,null,94.32449520278401]
["AN_MES","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,67.43,0.085315,0.3224,null,null,96.77692209108002]
["AN_MES","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,67.43,0.113533,0.3224,null,null,99.293105123256]
["AN_MES","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,67.43,0.142485,0.3224,null,null,101.87473851852002]
["AN_MES1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.292,0.026,0,110.70018792000002]
["AN_MES1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.292,0.026,0,113.57839280592002]
["AN_MES1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.292,0.026,0,116.53143101887393]
["AN_MES1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.292,0.026,0,119.5612486681654]
["AN_MES2","ESC2","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC238991",null,83.51,0.023,0.292,0.026,0,113.24629224216]
["AN_MES2","ESC2","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC239356",null,83.51,0.046529,0.292,0.026,0,115.8509569637297]
["AN_MES2","ESC2","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC239722",null,83.51,0.070599,0.292,0.026,0,118.51551048696412]
["AN_MES2","ESC2","AN_CS4","AN_GA2","AN_OH4","2009-10-01","ESC240087",null,83.51,0.095223,0.292,0.026,0,121.24139191430619]
["AN_MES2","ESC2","AN_CS4","AN_GA2","AN_OH4","2010-10-01","ESC240452",null,83.51,0.120413,0.292,0.026,0,124.02992964801098]
["AN_MES2","ESC2","AN_CS4","AN_GA2","AN_OH4","2011-10-01","ESC240817",null,83.51,0.120413,0.292,0.026,0,124.02992964801098]
["AN_MES2","ESC2","AN_CS4","AN_GA2","AN_OH4","2012-10-01","ESC241183",null,83.51,null,0.292,0.026,0,110.70018792000002]
["AN_MFAT","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,42.51,0,0.2598,null,null,53.554097999999996]
["AN_MFAT","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,42.51,0.029,0.2598,null,null,55.10716684199999]
["AN_MFAT","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,42.51,0.057812,0.2598,null,null,56.650167513575994]
["AN_MFAT","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,42.51,0.085315,0.2598,null,null,58.12306587087]
["AN_MFAT","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,42.51,0.113533,0.2598,null,null,59.634255408234]
["AN_MFAT","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,42.51,0.142485,0.2598,null,null,61.18475365353]
["AN_MFAT1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,49.03,0,0.292,0.026,0,64.99377576]
["AN_MFAT1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,49.03,0.026,0.292,0.026,0,66.68361392976001]
["AN_MFAT1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,49.03,0.052676,0.292,0.026,0,68.41738789193376]
["AN_MFAT1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,49.03,0.08004558,0.292,0.026,0,70.19624023709915]
["AN_MFAT2","ESC2","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC238991",null,49.03,0.023,0.292,0.026,0,66.48863260248]
["AN_MFAT2","ESC2","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC239356",null,49.03,0.046529,0.292,0.026,0,68.01787115233705]
["AN_MFAT2","ESC2","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC239722",null,49.03,0.070599,0.292,0.026,0,69.58227133488025]
["AN_MFAT2","ESC2","AN_CS4","AN_GA2","AN_OH4","2009-10-01","ESC240087",null,49.03,0.095223,0.292,0.026,0,71.1826780691945]
["AN_MFAT2","ESC2","AN_CS4","AN_GA2","AN_OH4","2010-10-01","ESC240452",null,49.03,0.120413,0.292,0.026,0,72.81987128058888]
["AN_MFAT2","ESC2","AN_CS4","AN_GA2","AN_OH4","2011-10-01","ESC240817",null,49.03,0.120413,0.292,0.026,0,72.81987128058888]
["AN_MFAT2","ESC2","AN_CS4","AN_GA2","AN_OH4","2012-10-01","ESC241183",null,49.03,null,0.292,0.026,0,64.99377576]
["AN_MFMS","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,53.97,0,0.2598,null,null,67.991406]
["AN_MFMS","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,53.97,0.029,0.2598,null,null,69.963156774]
["AN_MFMS","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,53.97,0.057812,0.2598,null,null,71.92212516367199]
["AN_MFMS","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,53.97,0.085315,0.2598,null,null,73.79209280289001]
["AN_MFMS","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,53.97,0.113533,0.2598,null,null,75.71067429739799]
["AN_MFMS","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,53.97,0.142485,0.2598,null,null,77.67916148391001]
["AN_MFMS1","ESC1","AN_CS5","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,81,0,0.196,0.026,0,99.394776]
["AN_MFMS1","ESC1","AN_CS5","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,81,0.026,0.196,0.026,0,101.97904017600001]
["AN_MFMS1","ESC1","AN_CS5","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,81,0.052676,0.196,0.026,0,104.630495220576]
["AN_MFMS1","ESC1","AN_CS5","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,81,0.08004558,0.196,0.026,0,107.35088849389007]
["AN_MFMS2","ESC2","AN_CS5","AN_GA2","AN_OH4","2006-10-01","ESC238991",null,81,0.023,0.196,0.026,0,101.680855848]
["AN_MFMS2","ESC2","AN_CS5","AN_GA2","AN_OH4","2007-10-01","ESC239356",null,81,0.046529,0.196,0.026,0,104.019515532504]
["AN_MFMS2","ESC2","AN_CS5","AN_GA2","AN_OH4","2008-10-01","ESC239722",null,81,0.070599,0.196,0.026,0,106.411947790824]
["AN_MFMS2","ESC2","AN_CS5","AN_GA2","AN_OH4","2009-10-01","ESC240087",null,81,0.095223,0.196,0.026,0,108.859444755048]
["AN_MFMS2","ESC2","AN_CS5","AN_GA2","AN_OH4","2010-10-01","ESC240452",null,81,0.120413,0.196,0.026,0,111.36319916248802]
["AN_MFMS2","ESC2","AN_CS5","AN_GA2","AN_OH4","2011-10-01","ESC240817",null,81,0.120413,0.196,0.026,0,111.36319916248802]
["AN_MFMS2","ESC2","AN_CS5","AN_GA2","AN_OH4","2012-10-01","ESC241183",null,81,null,0.196,0.026,0,99.394776]
["AN_MFPC","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.2598,null,null,0]
["AN_MFPC","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.2598,null,null,0]
["AN_MFPC","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.2598,null,null,0]
["AN_MFPC","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.2598,null,null,0]
["AN_MFPC","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.2598,null,null,0]
["AN_MFPC","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.2598,null,null,0]
["AN_MSCS","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AN_MSCS","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AN_MSCS","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AN_MSCS","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AN_MSCS","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AN_MSCS","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AN_MSCS1","ESC1","AN_CS6","AN_GA2",null,"2005-10-01","ESC138626",null,1,0,0.064,0.026,null,1.0916640000000002]
["AN_MSCS1","ESC1","AN_CS6","AN_GA2",null,"2006-10-01","ESC138991",null,1,0.026,0.064,0.026,null,1.1200472640000003]
["AN_MSCS1","ESC1","AN_CS6","AN_GA2",null,"2007-10-01","ESC139356",null,1,0.052676,0.064,0.026,null,1.149168492864]
["AN_MSCS1","ESC1","AN_CS6","AN_GA2",null,"2008-10-01","ESC139722",null,1,0.08004558,0.064,0.026,null,1.17904687804512]
["AN_MSCS2","ESC2","AN_CS6","AN_GA2",null,"2006-10-01","ESC238991",null,1,0.023,0.064,0.026,null,1.116772272]
["AN_MSCS2","ESC2","AN_CS6","AN_GA2",null,"2007-10-01","ESC239356",null,1,0.046529,0.064,0.026,null,1.1424580342560002]
["AN_MSCS2","ESC2","AN_CS6","AN_GA2",null,"2008-10-01","ESC239722",null,1,0.070599,0.064,0.026,null,1.1687343867360003]
["AN_MSCS2","ESC2","AN_CS6","AN_GA2",null,"2009-10-01","ESC240087",null,1,0.095223,0.064,0.026,null,1.195615521072]
["AN_MSCS2","ESC2","AN_CS6","AN_GA2",null,"2010-10-01","ESC240452",null,1,0.120413,0.064,0.026,null,1.2231145372320003]
["AN_MSCS2","ESC2","AN_CS6","AN_GA2",null,"2011-10-01","ESC240817",null,1,0.120413,0.064,0.026,null,1.2231145372320003]
["AN_MSCS2","ESC2","AN_CS6","AN_GA2",null,"2012-10-01","ESC241183",null,1,null,0.064,0.026,null,1.0916640000000002]
["AN_MSEG","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AN_MSEG","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AN_MSEG","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AN_MSEG","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AN_MSEG","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AN_MSEG","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AN_MSEG1","ESC1","AN_CS6","AN_GA2",null,"2005-10-01","ESC138626",null,1,0,0.064,0.026,null,1.0916640000000002]
["AN_MSEG1","ESC1","AN_CS6","AN_GA2",null,"2006-10-01","ESC138991",null,1,0.026,0.064,0.026,null,1.1200472640000003]
["AN_MSEG1","ESC1","AN_CS6","AN_GA2",null,"2007-10-01","ESC139356",null,1,0.052676,0.064,0.026,null,1.149168492864]
["AN_MSEG1","ESC1","AN_CS6","AN_GA2",null,"2008-10-01","ESC139722",null,1,0.08004558,0.064,0.026,null,1.17904687804512]
["AN_MSEG2","ESC2","AN_CS6","AN_GA2",null,"2006-10-01","ESC238991",null,1,0.023,0.064,0.026,null,1.116772272]
["AN_MSEG2","ESC2","AN_CS6","AN_GA2",null,"2007-10-01","ESC239356",null,1,0.046529,0.064,0.026,null,1.1424580342560002]
["AN_MSEG2","ESC2","AN_CS6","AN_GA2",null,"2008-10-01","ESC239722",null,1,0.070599,0.064,0.026,null,1.1687343867360003]
["AN_MSEG2","ESC2","AN_CS6","AN_GA2",null,"2009-10-01","ESC240087",null,1,0.095223,0.064,0.026,null,1.195615521072]
["AN_MSEG2","ESC2","AN_CS6","AN_GA2",null,"2010-10-01","ESC240452",null,1,0.120413,0.064,0.026,null,1.2231145372320003]
["AN_MSEG2","ESC2","AN_CS6","AN_GA2",null,"2011-10-01","ESC240817",null,1,0.120413,0.064,0.026,null,1.2231145372320003]
["AN_MSEG2","ESC2","AN_CS6","AN_GA2",null,"2012-10-01","ESC241183",null,1,null,0.064,0.026,null,1.0916640000000002]
["AN_MSEQ","ESC","AN_OH4",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AN_MSEQ","ESC","AN_OH4",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AN_MSEQ","ESC","AN_OH4",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AN_MSEQ","ESC","AN_OH4",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AN_MSEQ","ESC","AN_OH4",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AN_MSEQ","ESC","AN_OH4",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AN_MSEQ1","ESC1","AN_CS6","AN_GA2",null,"2005-10-01","ESC138626",null,1,0,0.064,0.026,null,1.0916640000000002]
["AN_MSEQ1","ESC1","AN_CS6","AN_GA2",null,"2006-10-01","ESC138991",null,1,0.026,0.064,0.026,null,1.1200472640000003]
["AN_MSEQ1","ESC1","AN_CS6","AN_GA2",null,"2007-10-01","ESC139356",null,1,0.052676,0.064,0.026,null,1.149168492864]
["AN_MSEQ1","ESC1","AN_CS6","AN_GA2",null,"2008-10-01","ESC139722",null,1,0.08004558,0.064,0.026,null,1.17904687804512]
["AN_MSEQ2","ESC2","AN_CS6","AN_GA2",null,"2006-10-01","ESC238991",null,1,0.023,0.064,0.026,null,1.116772272]
["AN_MSEQ2","ESC2","AN_CS6","AN_GA2",null,"2007-10-01","ESC239356",null,1,0.046529,0.064,0.026,null,1.1424580342560002]
["AN_MSEQ2","ESC2","AN_CS6","AN_GA2",null,"2008-10-01","ESC239722",null,1,0.070599,0.064,0.026,null,1.1687343867360003]
["AN_MSEQ2","ESC2","AN_CS6","AN_GA2",null,"2009-10-01","ESC240087",null,1,0.095223,0.064,0.026,null,1.195615521072]
["AN_MSEQ2","ESC2","AN_CS6","AN_GA2",null,"2010-10-01","ESC240452",null,1,0.120413,0.064,0.026,null,1.2231145372320003]
["AN_MSEQ2","ESC2","AN_CS6","AN_GA2",null,"2011-10-01","ESC240817",null,1,0.120413,0.064,0.026,null,1.2231145372320003]
["AN_MSEQ2","ESC2","AN_CS6","AN_GA2",null,"2012-10-01","ESC241183",null,1,null,0.064,0.026,null,1.0916640000000002]
["AN_MSPS","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AN_MSPS","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AN_MSPS","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AN_MSPS","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AN_MSPS","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AN_MSPS","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AN_MSPS1","ESC1","AN_CS6","AN_GA2",null,"2005-10-01","ESC138626",null,1,0,0.064,0.026,null,1.0916640000000002]
["AN_MSPS1","ESC1","AN_CS6","AN_GA2",null,"2006-10-01","ESC138991",null,1,0.026,0.064,0.026,null,1.1200472640000003]
["AN_MSPS1","ESC1","AN_CS6","AN_GA2",null,"2007-10-01","ESC139356",null,1,0.052676,0.064,0.026,null,1.149168492864]
["AN_MSPS1","ESC1","AN_CS6","AN_GA2",null,"2008-10-01","ESC139722",null,1,0.08004558,0.064,0.026,null,1.17904687804512]
["AN_MSPS2","ESC2","AN_CS6","AN_GA2",null,"2006-10-01","ESC238991",null,1,0.023,0.064,0.026,null,1.116772272]
["AN_MSPS2","ESC2","AN_CS6","AN_GA2",null,"2007-10-01","ESC239356",null,1,0.046529,0.064,0.026,null,1.1424580342560002]
["AN_MSPS2","ESC2","AN_CS6","AN_GA2",null,"2008-10-01","ESC239722",null,1,0.070599,0.064,0.026,null,1.1687343867360003]
["AN_MSPS2","ESC2","AN_CS6","AN_GA2",null,"2009-10-01","ESC240087",null,1,0.095223,0.064,0.026,null,1.195615521072]
["AN_MSPS2","ESC2","AN_CS6","AN_GA2",null,"2010-10-01","ESC240452",null,1,0.120413,0.064,0.026,null,1.2231145372320003]
["AN_MSPS2","ESC2","AN_CS6","AN_GA2",null,"2011-10-01","ESC240817",null,1,0.120413,0.064,0.026,null,1.2231145372320003]
["AN_MSPS2","ESC2","AN_CS6","AN_GA2",null,"2012-10-01","ESC241183",null,1,null,0.064,0.026,null,1.0916640000000002]
["AN_MSSC","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AN_MSSC","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AN_MSSC","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AN_MSSC","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AN_MSSC","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AN_MSSC","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AN_MSSC1","ESC1","AN_CS6","AN_GA2",null,"2005-10-01","ESC138626",null,1,0,0.064,0.026,null,1.0916640000000002]
["AN_MSSC1","ESC1","AN_CS6","AN_GA2",null,"2006-10-01","ESC138991",null,1,0.026,0.064,0.026,null,1.1200472640000003]
["AN_MSSC1","ESC1","AN_CS6","AN_GA2",null,"2007-10-01","ESC139356",null,1,0.052676,0.064,0.026,null,1.149168492864]
["AN_MSSC1","ESC1","AN_CS6","AN_GA2",null,"2008-10-01","ESC139722",null,1,0.08004558,0.064,0.026,null,1.17904687804512]
["AN_MSSC2","ESC2","AN_CS6","AN_GA2",null,"2006-10-01","ESC238991",null,1,0.023,0.064,0.026,null,1.116772272]
["AN_MSSC2","ESC2","AN_CS6","AN_GA2",null,"2007-10-01","ESC239356",null,1,0.046529,0.064,0.026,null,1.1424580342560002]
["AN_MSSC2","ESC2","AN_CS6","AN_GA2",null,"2008-10-01","ESC239722",null,1,0.070599,0.064,0.026,null,1.1687343867360003]
["AN_MSSC2","ESC2","AN_CS6","AN_GA2",null,"2009-10-01","ESC240087",null,1,0.095223,0.064,0.026,null,1.195615521072]
["AN_MSSC2","ESC2","AN_CS6","AN_GA2",null,"2010-10-01","ESC240452",null,1,0.120413,0.064,0.026,null,1.2231145372320003]
["AN_MSSC2","ESC2","AN_CS6","AN_GA2",null,"2011-10-01","ESC240817",null,1,0.120413,0.064,0.026,null,1.2231145372320003]
["AN_MSSC2","ESC2","AN_CS6","AN_GA2",null,"2012-10-01","ESC241183",null,1,null,0.064,0.026,null,1.0916640000000002]
["AN_MSSF","AN_OH3",{"$nulls":4},"AN_OH3",null,1,{"$nulls":4},1]
["AN_MSSF1","AN_CS6","AN_GA2",null,null,null,"AN_CS6",null,1,0.064,0.026,null,null,1.0916640000000002]
["AN_MSSF2","AN_CS6","AN_GA2",null,null,null,"AN_CS6",null,1,0.064,0.026,null,null,1.0916640000000002]
["AN_MSTR","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,1,0,0.3224,null,null,1.3224]
["AN_MSTR","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,1,0.029,0.3224,null,null,1.3607496]
["AN_MSTR","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.3224,null,null,1.3988505888]
["AN_MSTR","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.3224,null,null,1.435220556]
["AN_MSTR","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.3224,null,null,1.4725360392]
["AN_MSTR","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.3224,null,null,1.510822164]
["AN_MSTR1","ESC1","AN_OH1",null,null,"2005-10-01","ESC138626",null,1.29,0,0.3224,null,null,1.705896]
["AN_MSTR1","ESC1","AN_OH1",null,null,"2006-10-01","ESC138991",null,1.29,0.026,0.3224,null,null,1.7502492960000002]
["AN_MSTR1","ESC1","AN_OH1",null,null,"2007-10-01","ESC139356",null,1.29,0.052676,0.3224,null,null,1.795755777696]
["AN_MSTR1","ESC1","AN_OH1",null,null,"2008-10-01","ESC139722",null,1.29,0.08004558,0.3224,null,null,1.84244543473968]
["AN_MSTR2","ESC2","AN_OH1",null,null,"2006-10-01","ESC238991",null,1.29,0.023,0.3224,null,null,1.745131608]
["AN_MSTR2","ESC2","AN_OH1",null,null,"2007-10-01","ESC239356",null,1.29,0.046529,0.3224,null,null,1.785269634984]
["AN_MSTR2","ESC2","AN_OH1",null,null,"2008-10-01","ESC239722",null,1.29,0.070599,0.3224,null,null,1.8263305517040003]
["AN_MSTR2","ESC2","AN_OH1",null,null,"2009-10-01","ESC240087",null,1.29,0.095223,0.3224,null,null,1.868336534808]
["AN_MSTR2","ESC2","AN_OH1",null,null,"2010-10-01","ESC240452",null,1.29,0.120413,0.3224,null,null,1.9113080550480004]
["AN_MSTR2","ESC2","AN_OH1",null,null,"2011-10-01","ESC240817",null,1.29,0.120413,0.3224,null,null,1.9113080550480004]
["AN_MSTR2","ESC2","AN_OH1",null,null,"2012-10-01","ESC241183",null,1.29,null,0.3224,null,null,1.705896]
["AN_MSXX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["AN_MSXX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["AN_MSXX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["AN_MSXX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["AN_MSXX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["AN_MSXX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["AN_MSXX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["AN_MSXX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["AN_MSXX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["AN_MSXX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["AN_MSXX2","ESC2",null,null,null,"2006-10-01","ESC238991",null,1,0.023,null,null,null,1.023]
["AN_MSXX2","ESC2",null,null,null,"2007-10-01","ESC239356",null,1,0.046529,null,null,null,1.046529]
["AN_MSXX2","ESC2",null,null,null,"2008-10-01","ESC239722",null,1,0.070599,null,null,null,1.070599]
["AN_MSXX2","ESC2",null,null,null,"2009-10-01","ESC240087",null,1,0.095223,null,null,null,1.095223]
["AN_MSXX2","ESC2",null,null,null,"2010-10-01","ESC240452",null,1,0.120413,null,null,null,1.120413]
["AN_MSXX2","ESC2",null,null,null,"2011-10-01","ESC240817",null,1,0.120413,null,null,null,1.120413]
["AN_MSXX2","ESC2",null,null,null,"2012-10-01","ESC241183",null,1,{"$nulls":4},1]
["AN_MTRL","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AN_MTRL","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AN_MTRL","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AN_MTRL","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AN_MTRL","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AN_MTRL","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AN_MTRL1","ESC1","AN_CS6","AN_GA2",null,"2005-10-01","ESC138626",null,1,0,0.064,0.026,null,1.0916640000000002]
["AN_MTRL1","ESC1","AN_CS6","AN_GA2",null,"2006-10-01","ESC138991",null,1,0.026,0.064,0.026,null,1.1200472640000003]
["AN_MTRL1","ESC1","AN_CS6","AN_GA2",null,"2007-10-01","ESC139356",null,1,0.052676,0.064,0.026,null,1.149168492864]
["AN_MTRL1","ESC1","AN_CS6","AN_GA2",null,"2008-10-01","ESC139722",null,1,0.08004558,0.064,0.026,null,1.17904687804512]
["AN_MTRL2","ESC2","AN_CS6","AN_GA2",null,"2006-10-01","ESC238991",null,1,0.023,0.064,0.026,null,1.116772272]
["AN_MTRL2","ESC2","AN_CS6","AN_GA2",null,"2007-10-01","ESC239356",null,1,0.046529,0.064,0.026,null,1.1424580342560002]
["AN_MTRL2","ESC2","AN_CS6","AN_GA2",null,"2008-10-01","ESC239722",null,1,0.070599,0.064,0.026,null,1.1687343867360003]
["AN_MTRL2","ESC2","AN_CS6","AN_GA2",null,"2009-10-01","ESC240087",null,1,0.095223,0.064,0.026,null,1.195615521072]
["AN_MTRL2","ESC2","AN_CS6","AN_GA2",null,"2010-10-01","ESC240452",null,1,0.120413,0.064,0.026,null,1.2231145372320003]
["AN_MTRL2","ESC2","AN_CS6","AN_GA2",null,"2011-10-01","ESC240817",null,1,0.120413,0.064,0.026,null,1.2231145372320003]
["AN_MTRL2","ESC2","AN_CS6","AN_GA2",null,"2012-10-01","ESC241183",null,1,null,0.064,0.026,null,1.0916640000000002]
["AN_MVE","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,63.24,0,0.3224,null,null,83.62857600000001]
["AN_MVE","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,63.24,0.029,0.3224,null,null,86.053804704]
["AN_MVE","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,63.24,0.057812,0.3224,null,null,88.463311235712]
["AN_MVE","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,63.24,0.085315,0.3224,null,null,90.76334796144]
["AN_MVE","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,63.24,0.113533,0.3224,null,null,93.12317911900799]
["AN_MVE","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,63.24,0.142485,0.3224,null,null,95.54439365136]
["AN_MVE1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.292,0.026,0,110.70018792000002]
["AN_MVE1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.292,0.026,0,113.57839280592002]
["AN_MVE1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.292,0.026,0,116.53143101887393]
["AN_MVE1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.292,0.026,0,119.5612486681654]
["AN_MVE2","ESC2","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC238991",null,83.51,0.023,0.292,0.026,0,113.24629224216]
["AN_MVE2","ESC2","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC239356",null,83.51,0.046529,0.292,0.026,0,115.8509569637297]
["AN_MVE2","ESC2","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC239722",null,83.51,0.070599,0.292,0.026,0,118.51551048696412]
["AN_MVE2","ESC2","AN_CS4","AN_GA2","AN_OH4","2009-10-01","ESC240087",null,83.51,0.095223,0.292,0.026,0,121.24139191430619]
["AN_MVE2","ESC2","AN_CS4","AN_GA2","AN_OH4","2010-10-01","ESC240452",null,83.51,0.120413,0.292,0.026,0,124.02992964801098]
["AN_MVE2","ESC2","AN_CS4","AN_GA2","AN_OH4","2011-10-01","ESC240817",null,83.51,0.120413,0.292,0.026,0,124.02992964801098]
["AN_MVE2","ESC2","AN_CS4","AN_GA2","AN_OH4","2012-10-01","ESC241183",null,83.51,null,0.292,0.026,0,110.70018792000002]
["AN_PHH","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,45.68,0,0.3224,null,null,60.407232]
["AN_PHH","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,45.68,0.029,0.3224,null,null,62.159041728]
["AN_PHH","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,45.68,0.057812,0.3224,null,null,63.899494896384006]
["AN_PHH","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,45.68,0.085315,0.3224,null,null,65.56087499808]
["AN_PHH","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,45.68,0.113533,0.3224,null,null,67.265446270656]
["AN_PHH","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,45.68,0.142485,0.3224,null,null,69.01435645152]
["AN_PHH1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,45.68,0,0.292,0.026,0,60.55304256]
["AN_PHH1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,45.68,0.026,0.292,0.026,0,62.127421666560004]
["AN_PHH1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,45.68,0.052676,0.292,0.026,0,63.742734629890556]
["AN_PHH1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,45.68,0.08004558,0.292,0.026,0,65.40004597247989]
["AN_PHH2","ESC2","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC238991",null,45.68,0.023,0.292,0.026,0,61.94576253888]
["AN_PHH2","ESC2","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC239356",null,45.68,0.046529,0.292,0.026,0,63.37051507727425]
["AN_PHH2","ESC2","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC239722",null,45.68,0.070599,0.292,0.026,0,64.82802681169345]
["AN_PHH2","ESC2","AN_CS4","AN_GA2","AN_OH4","2009-10-01","ESC240087",null,45.68,0.095223,0.292,0.026,0,66.31908493169088]
["AN_PHH2","ESC2","AN_CS4","AN_GA2","AN_OH4","2010-10-01","ESC240452",null,45.68,0.120413,0.292,0.026,0,67.84441607377728]
["AN_PHH2","ESC2","AN_CS4","AN_GA2","AN_OH4","2011-10-01","ESC240817",null,45.68,0.120413,0.292,0.026,0,67.84441607377728]
["AN_PHH2","ESC2","AN_CS4","AN_GA2","AN_OH4","2012-10-01","ESC241183",null,45.68,null,0.292,0.026,0,60.55304256]
["AN_PHPD","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,33.95,0,0.3224,null,null,44.895480000000006]
["AN_PHPD","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,33.95,0.029,0.3224,null,null,46.19744892]
["AN_PHPD","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,33.95,0.057812,0.3224,null,null,47.490977489760006]
["AN_PHPD","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,33.95,0.085315,0.3224,null,null,48.72573787620001]
["AN_PHPD","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,33.95,0.113533,0.3224,null,null,49.992598530840006]
["AN_PHPD","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,33.95,0.142485,0.3224,null,null,51.2924124678]
["AN_PHPD1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,37.26,0,0.292,0.026,0,49.39155792]
["AN_PHPD1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,37.26,0.026,0.292,0.026,0,50.67573842592]
["AN_PHPD1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,37.26,0.052676,0.292,0.026,0,51.993307624993925]
["AN_PHPD1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,37.26,0.08004558,0.292,0.026,0,53.345133820809984]
["AN_PHPD2","ESC2","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC238991",null,37.26,0.023,0.292,0.026,0,50.52756375216]
["AN_PHPD2","ESC2","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC239356",null,37.26,0.046529,0.292,0.026,0,51.689697718459676]
["AN_PHPD2","ESC2","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC239722",null,37.26,0.070599,0.292,0.026,0,52.87855251759408]
["AN_PHPD2","ESC2","AN_CS4","AN_GA2","AN_OH4","2009-10-01","ESC240087",null,37.26,0.095223,0.292,0.026,0,54.09477023981616]
["AN_PHPD2","ESC2","AN_CS4","AN_GA2","AN_OH4","2010-10-01","ESC240452",null,37.26,0.120413,0.292,0.026,0,55.33894358382096]
["AN_PHPD2","ESC2","AN_CS4","AN_GA2","AN_OH4","2011-10-01","ESC240817",null,37.26,0.120413,0.292,0.026,0,55.33894358382096]
["AN_PHPD2","ESC2","AN_CS4","AN_GA2","AN_OH4","2012-10-01","ESC241183",null,37.26,null,0.292,0.026,0,49.39155792]
["AN_PHS","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,63.24,0,0.3224,null,null,83.62857600000001]
["AN_PHS","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,63.24,0.029,0.3224,null,null,86.053804704]
["AN_PHS","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,63.24,0.057812,0.3224,null,null,88.463311235712]
["AN_PHS","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,63.24,0.085315,0.3224,null,null,90.76334796144]
["AN_PHS","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,63.24,0.113533,0.3224,null,null,93.12317911900799]
["AN_PHS","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,63.24,0.142485,0.3224,null,null,95.54439365136]
["AN_PHS1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.292,0.026,0,110.70018792000002]
["AN_PHS1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.292,0.026,0,113.57839280592002]
["AN_PHS1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.292,0.026,0,116.53143101887393]
["AN_PHS1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.292,0.026,0,119.5612486681654]
["AN_PHS2","ESC2","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC238991",null,83.51,0.023,0.292,0.026,0,113.24629224216]
["AN_PHS2","ESC2","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC239356",null,83.51,0.046529,0.292,0.026,0,115.8509569637297]
["AN_PHS2","ESC2","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC239722",null,83.51,0.070599,0.292,0.026,0,118.51551048696412]
["AN_PHS2","ESC2","AN_CS4","AN_GA2","AN_OH4","2009-10-01","ESC240087",null,83.51,0.095223,0.292,0.026,0,121.24139191430619]
["AN_PHS2","ESC2","AN_CS4","AN_GA2","AN_OH4","2010-10-01","ESC240452",null,83.51,0.120413,0.292,0.026,0,124.02992964801098]
["AN_PHS2","ESC2","AN_CS4","AN_GA2","AN_OH4","2011-10-01","ESC240817",null,83.51,0.120413,0.292,0.026,0,124.02992964801098]
["AN_PHS2","ESC2","AN_CS4","AN_GA2","AN_OH4","2012-10-01","ESC241183",null,83.51,null,0.292,0.026,0,110.70018792000002]
["AN_PHSS","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,63.24,0,0.3224,null,null,83.62857600000001]
["AN_PHSS","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,63.24,0.029,0.3224,null,null,86.053804704]
["AN_PHSS","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,63.24,0.057812,0.3224,null,null,88.463311235712]
["AN_PHSS","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,63.24,0.085315,0.3224,null,null,90.76334796144]
["AN_PHSS","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,63.24,0.113533,0.3224,null,null,93.12317911900799]
["AN_PHSS","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,63.24,0.142485,0.3224,null,null,95.54439365136]
["AN_PHSS1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,63.24,0,0.292,0.026,0,83.83043808000001]
["AN_PHSS1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,63.24,0.026,0.292,0.026,0,86.01002947008001]
["AN_PHSS1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,63.24,0.052676,0.292,0.026,0,88.2462902363021]
["AN_PHSS1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,63.24,0.08004558,0.292,0.026,0,90.54069411776769]
["AN_PHSS2","ESC2","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC238991",null,63.24,0.023,0.292,0.026,0,85.75853815584]
["AN_PHSS2","ESC2","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC239356",null,63.24,0.046529,0.292,0.026,0,87.73098453342433]
["AN_PHSS2","ESC2","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC239722",null,63.24,0.070599,0.292,0.026,0,89.74878317800992]
["AN_PHSS2","ESC2","AN_CS4","AN_GA2","AN_OH4","2009-10-01","ESC240087",null,63.24,0.095223,0.292,0.026,0,91.81302388529186]
["AN_PHSS2","ESC2","AN_CS4","AN_GA2","AN_OH4","2010-10-01","ESC240452",null,63.24,0.120413,0.292,0.026,0,93.92471262052705]
["AN_PHSS2","ESC2","AN_CS4","AN_GA2","AN_OH4","2011-10-01","ESC240817",null,63.24,0.120413,0.292,0.026,0,93.92471262052705]
["AN_PHSS2","ESC2","AN_CS4","AN_GA2","AN_OH4","2012-10-01","ESC241183",null,63.24,null,0.292,0.026,0,83.83043808000001]
["AN_PM","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,63.24,0,0.3224,null,null,83.62857600000001]
["AN_PM","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,63.24,0.029,0.3224,null,null,86.053804704]
["AN_PM","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,63.24,0.057812,0.3224,null,null,88.463311235712]
["AN_PM","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,63.24,0.085315,0.3224,null,null,90.76334796144]
["AN_PM","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,63.24,0.113533,0.3224,null,null,93.12317911900799]
["AN_PM","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,63.24,0.142485,0.3224,null,null,95.54439365136]
["AN_PM1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.292,0.026,0,110.70018792000002]
["AN_PM1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.292,0.026,0,113.57839280592002]
["AN_PM1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.292,0.026,0,116.53143101887393]
["AN_PM1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.292,0.026,0,119.5612486681654]
["AN_PM2","ESC2","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC238991",null,83.51,0.023,0.292,0.026,0,113.24629224216]
["AN_PM2","ESC2","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC239356",null,83.51,0.046529,0.292,0.026,0,115.8509569637297]
["AN_PM2","ESC2","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC239722",null,83.51,0.070599,0.292,0.026,0,118.51551048696412]
["AN_PM2","ESC2","AN_CS4","AN_GA2","AN_OH4","2009-10-01","ESC240087",null,83.51,0.095223,0.292,0.026,0,121.24139191430619]
["AN_PM2","ESC2","AN_CS4","AN_GA2","AN_OH4","2010-10-01","ESC240452",null,83.51,0.120413,0.292,0.026,0,124.02992964801098]
["AN_PM2","ESC2","AN_CS4","AN_GA2","AN_OH4","2011-10-01","ESC240817",null,83.51,0.120413,0.292,0.026,0,124.02992964801098]
["AN_PM2","ESC2","AN_CS4","AN_GA2","AN_OH4","2012-10-01","ESC241183",null,83.51,null,0.292,0.026,0,110.70018792000002]
["AN_SEE","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,85,0,0.3224,null,null,112.404]
["AN_SEE","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,85,0.029,0.3224,null,null,115.663716]
["AN_SEE","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,85,0.057812,0.3224,null,null,118.90230004799999]
["AN_SEE","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,85,0.085315,0.3224,null,null,121.99374726000002]
["AN_SEE","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,85,0.113533,0.3224,null,null,125.16556333199999]
["AN_SEE","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,85,0.142485,0.3224,null,null,128.41988394]
["AN_SEE1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.292,0.026,0,110.70018792000002]
["AN_SEE1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.292,0.026,0,113.57839280592002]
["AN_SEE1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.292,0.026,0,116.53143101887393]
["AN_SEE1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.292,0.026,0,119.5612486681654]
["AN_SEE2","ESC2","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC238991",null,83.51,0.023,0.292,0.026,0,113.24629224216]
["AN_SEE2","ESC2","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC239356",null,83.51,0.046529,0.292,0.026,0,115.8509569637297]
["AN_SEE2","ESC2","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC239722",null,83.51,0.070599,0.292,0.026,0,118.51551048696412]
["AN_SEE2","ESC2","AN_CS4","AN_GA2","AN_OH4","2009-10-01","ESC240087",null,83.51,0.095223,0.292,0.026,0,121.24139191430619]
["AN_SEE2","ESC2","AN_CS4","AN_GA2","AN_OH4","2010-10-01","ESC240452",null,83.51,0.120413,0.292,0.026,0,124.02992964801098]
["AN_SEE2","ESC2","AN_CS4","AN_GA2","AN_OH4","2011-10-01","ESC240817",null,83.51,0.120413,0.292,0.026,0,124.02992964801098]
["AN_SEE2","ESC2","AN_CS4","AN_GA2","AN_OH4","2012-10-01","ESC241183",null,83.51,null,0.292,0.026,0,110.70018792000002]
["AN_SEL","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,null,0,0.3224,null,null,0]
["AN_SEL","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,null,0.029,0.3224,null,null,0]
["AN_SEL","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.3224,null,null,0]
["AN_SEL","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.3224,null,null,0]
["AN_SEL","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.3224,null,null,0]
["AN_SEL","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.3224,null,null,0]
["AN_SEPM","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,null,0,0.3224,null,null,0]
["AN_SEPM","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,null,0.029,0.3224,null,null,0]
["AN_SEPM","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.3224,null,null,0]
["AN_SEPM","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.3224,null,null,0]
["AN_SEPM","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.3224,null,null,0]
["AN_SEPM","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.3224,null,null,0]
["AN_TMUC","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.2598,null,null,0]
["AN_TMUC","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.2598,null,null,0]
["AN_TMUC","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.2598,null,null,0]
["AN_TMUC","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.2598,null,null,0]
["AN_TMUC","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.2598,null,null,0]
["AN_TMUC","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.2598,null,null,0]
["AN_TMUE","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.2598,null,null,0]
["AN_TMUE","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.2598,null,null,0]
["AN_TMUE","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.2598,null,null,0]
["AN_TMUE","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.2598,null,null,0]
["AN_TMUE","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.2598,null,null,0]
["AN_TMUE","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.2598,null,null,0]
["AN_TMUI","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.2598,null,null,0]
["AN_TMUI","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.2598,null,null,0]
["AN_TMUI","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.2598,null,null,0]
["AN_TMUI","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.2598,null,null,0]
["AN_TMUI","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.2598,null,null,0]
["AN_TMUI","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.2598,null,null,0]
["AN_TMUO","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.2598,null,null,0]
["AN_TMUO","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.2598,null,null,0]
["AN_TMUO","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.2598,null,null,0]
["AN_TMUO","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.2598,null,null,0]
["AN_TMUO","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.2598,null,null,0]
["AN_TMUO","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.2598,null,null,0]
["AN_TMUP","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.2598,null,null,0]
["AN_TMUP","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.2598,null,null,0]
["AN_TMUP","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.2598,null,null,0]
["AN_TMUP","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.2598,null,null,0]
["AN_TMUP","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.2598,null,null,0]
["AN_TMUP","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.2598,null,null,0]
["AN_TMUW","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.2598,null,null,0]
["AN_TMUW","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.2598,null,null,0]
["AN_TMUW","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.2598,null,null,0]
["AN_TMUW","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.2598,null,null,0]
["AN_TMUW","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.2598,null,null,0]
["AN_TMUW","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.2598,null,null,0]
["BA",{"$nulls":5},"",null,1,{"$nulls":4},1]
["BASE",{"$nulls":5},"",null,1,{"$nulls":4},1]
["CNST",{"$nulls":5},"",{"$nulls":6},0]
["COMM",{"$nulls":5},"",{"$nulls":6},0]
["LA_MSCS","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,null,0,0.19,null,null,0]
["LA_MSCS","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,null,0.029,0.19,null,null,0]
["LA_MSCS","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.19,null,null,0]
["LA_MSCS","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.19,null,null,0]
["LA_MSCS","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.19,null,null,0]
["LA_MSCS","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.19,null,null,0]
["LA_MSCS1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,null,0,0.11,null,null,0]
["LA_MSCS1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,null,0.026,0.11,null,null,0]
["LA_MSCS1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,null,0.052676,0.11,null,null,0]
["LA_MSCS1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,null,0.08004558,0.11,null,null,0]
["LA_MSCS2","ESC2","LL_OH2",null,null,"2006-10-01","ESC238991",null,null,0.023,0.11,null,null,0]
["LA_MSCS2","ESC2","LL_OH2",null,null,"2007-10-01","ESC239356",null,null,0.046529,0.11,null,null,0]
["LA_MSCS2","ESC2","LL_OH2",null,null,"2008-10-01","ESC239722",null,null,0.070599,0.11,null,null,0]
["LA_MSCS2","ESC2","LL_OH2",null,null,"2009-10-01","ESC240087",null,null,0.095223,0.11,null,null,0]
["LA_MSCS2","ESC2","LL_OH2",null,null,"2010-10-01","ESC240452",null,null,0.120413,0.11,null,null,0]
["LA_MSCS2","ESC2","LL_OH2",null,null,"2011-10-01","ESC240817",null,null,0.120413,0.11,null,null,0]
["LA_MSCS2","ESC2","LL_OH2",null,null,"2012-10-01","ESC241183",null,null,null,0.11,null,null,0]
["LA_MSEG","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LA_MSEG","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LA_MSEG","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LA_MSEG","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LA_MSEG","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LA_MSEG","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LA_MSEG1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LA_MSEG1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LA_MSEG1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LA_MSEG1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LA_MSEG2","ESC2","LL_OH2",null,null,"2006-10-01","ESC238991",null,1,0.023,0.11,null,null,1.13553]
["LA_MSEG2","ESC2","LL_OH2",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.11,null,null,1.16164719]
["LA_MSEG2","ESC2","LL_OH2",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.11,null,null,1.1883648900000001]
["LA_MSEG2","ESC2","LL_OH2",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.11,null,null,1.2156975300000001]
["LA_MSEG2","ESC2","LL_OH2",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LA_MSEG2","ESC2","LL_OH2",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LA_MSEG2","ESC2","LL_OH2",null,null,"2012-10-01","ESC241183",null,1,null,0.11,null,null,1.11]
["LA_MSEQ","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LA_MSEQ","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LA_MSEQ","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LA_MSEQ","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LA_MSEQ","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LA_MSEQ","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LA_MSEQ1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LA_MSEQ1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LA_MSEQ1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LA_MSEQ1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LA_MSEQ2","ESC2","LL_OH2",null,null,"2006-10-01","ESC238991",null,1,0.023,0.11,null,null,1.13553]
["LA_MSEQ2","ESC2","LL_OH2",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.11,null,null,1.16164719]
["LA_MSEQ2","ESC2","LL_OH2",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.11,null,null,1.1883648900000001]
["LA_MSEQ2","ESC2","LL_OH2",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.11,null,null,1.2156975300000001]
["LA_MSEQ2","ESC2","LL_OH2",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LA_MSEQ2","ESC2","LL_OH2",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LA_MSEQ2","ESC2","LL_OH2",null,null,"2012-10-01","ESC241183",null,1,null,0.11,null,null,1.11]
["LA_MSPS","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,null,0,0.19,null,null,0]
["LA_MSPS","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,null,0.029,0.19,null,null,0]
["LA_MSPS","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.19,null,null,0]
["LA_MSPS","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.19,null,null,0]
["LA_MSPS","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.19,null,null,0]
["LA_MSPS","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.19,null,null,0]
["LA_MSSC","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LA_MSSC","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LA_MSSC","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LA_MSSC","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LA_MSSC","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LA_MSSC","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LA_MSSC1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LA_MSSC1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LA_MSSC1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LA_MSSC1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LA_MSSC2","ESC2","LL_OH2",null,null,"2006-10-01","ESC238991",null,1,0.023,0.11,null,null,1.13553]
["LA_MSSC2","ESC2","LL_OH2",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.11,null,null,1.16164719]
["LA_MSSC2","ESC2","LL_OH2",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.11,null,null,1.1883648900000001]
["LA_MSSC2","ESC2","LL_OH2",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.11,null,null,1.2156975300000001]
["LA_MSSC2","ESC2","LL_OH2",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LA_MSSC2","ESC2","LL_OH2",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LA_MSSC2","ESC2","LL_OH2",null,null,"2012-10-01","ESC241183",null,1,null,0.11,null,null,1.11]
["LA_MSSF","LL_OH",{"$nulls":4},"LL_OH",{"$nulls":6},0]
["LA_MSSX","LL_OH",{"$nulls":4},"LL_OH",{"$nulls":6},0]
["LA_MSXX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["LA_MSXX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["LA_MSXX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["LA_MSXX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["LA_MSXX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["LA_MSXX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["LA_MSXX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["LA_MSXX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["LA_MSXX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["LA_MSXX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["LA_MSXX2","ESC2",null,null,null,"2006-10-01","ESC238991",null,1,0.023,null,null,null,1.023]
["LA_MSXX2","ESC2",null,null,null,"2007-10-01","ESC239356",null,1,0.046529,null,null,null,1.046529]
["LA_MSXX2","ESC2",null,null,null,"2008-10-01","ESC239722",null,1,0.070599,null,null,null,1.070599]
["LA_MSXX2","ESC2",null,null,null,"2009-10-01","ESC240087",null,1,0.095223,null,null,null,1.095223]
["LA_MSXX2","ESC2",null,null,null,"2010-10-01","ESC240452",null,1,0.120413,null,null,null,1.120413]
["LA_MSXX2","ESC2",null,null,null,"2011-10-01","ESC240817",null,1,0.120413,null,null,null,1.120413]
["LA_MSXX2","ESC2",null,null,null,"2012-10-01","ESC241183",null,1,{"$nulls":4},1]
["LLNL_LABOR","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LLNL_LABOR","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LLNL_LABOR","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LLNL_LABOR","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LLNL_LABOR","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LLNL_LABOR","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LLNL_NON-LABOR","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,null,0,0.19,null,null,0]
["LLNL_NON-LABOR","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,null,0.029,0.19,null,null,0]
["LLNL_NON-LABOR","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.19,null,null,0]
["LLNL_NON-LABOR","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.19,null,null,0]
["LLNL_NON-LABOR","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.19,null,null,0]
["LLNL_NON-LABOR","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.19,null,null,0]
["LLNL_SHOPS","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LLNL_SHOPS","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LLNL_SHOPS","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LLNL_SHOPS","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LLNL_SHOPS","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LLNL_SHOPS","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LLNL_TRAVEL","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,null,0,0.19,null,null,0]
["LLNL_TRAVEL","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,null,0.029,0.19,null,null,0]
["LLNL_TRAVEL","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.19,null,null,0]
["LLNL_TRAVEL","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.19,null,null,0]
["LLNL_TRAVEL","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.19,null,null,0]
["LLNL_TRAVEL","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.19,null,null,0]
["LL_ADMN","ESC",null,null,null,"2003-10-01","ESC37895",null,134.15048076923077,0,null,null,null,134.15048076923077]
["LL_ADMN","ESC",null,null,null,"2004-10-01","ESC38261",null,134.15048076923077,0.029,null,null,null,138.04084471153845]
["LL_ADMN","ESC",null,null,null,"2005-10-01","ESC38626",null,134.15048076923077,0.057812,null,null,null,141.90598836346155]
["LL_ADMN","ESC",null,null,null,"2006-10-01","ESC38991",null,134.15048076923077,0.085315,null,null,null,145.59552903605768]
["LL_ADMN","ESC",null,null,null,"2007-10-01","ESC39356",null,134.15048076923077,0.113533,null,null,null,149.38098730240384]
["LL_ADMN","ESC",null,null,null,"2008-10-01","ESC39722",null,134.15048076923077,0.142485,null,null,null,153.26491202163461]
["LL_ADMN1","ESC1",null,null,null,"2005-10-01","ESC138626",null,134.15048076923077,0,null,null,null,134.15048076923077]
["LL_ADMN1","ESC1",null,null,null,"2006-10-01","ESC138991",null,134.15048076923077,0.026,null,null,null,137.63839326923076]
["LL_ADMN1","ESC1",null,null,null,"2007-10-01","ESC139356",null,134.15048076923077,0.052676,null,null,null,141.21699149423077]
["LL_ADMN1","ESC1",null,null,null,"2008-10-01","ESC139722",null,134.15048076923077,0.08004558,null,null,null,144.8886338096827]
["LL_ADMN2","ESC2",null,null,null,"2006-10-01","ESC238991",null,134.15048076923077,0.023,null,null,null,137.23594182692307]
["LL_ADMN2","ESC2",null,null,null,"2007-10-01","ESC239356",null,134.15048076923077,0.046529,null,null,null,140.3923684889423]
["LL_ADMN2","ESC2",null,null,null,"2008-10-01","ESC239722",null,134.15048076923077,0.070599,null,null,null,143.6213705610577]
["LL_ADMN2","ESC2",null,null,null,"2009-10-01","ESC240087",null,134.15048076923077,0.095223,null,null,null,146.92469199951924]
["LL_ADMN2","ESC2",null,null,null,"2010-10-01","ESC240452",null,134.15048076923077,0.120413,null,null,null,150.30394261009616]
["LL_ADMN2","ESC2",null,null,null,"2011-10-01","ESC240817",null,134.15048076923077,0.120413,null,null,null,150.30394261009616]
["LL_ADMN2","ESC2",null,null,null,"2012-10-01","ESC241183",null,134.15048076923077,{"$nulls":4},134.15048076923077]
["LL_AW1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LL_AW1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LL_AW1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LL_AW1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LL_AW2","ESC2","LL_OH2",null,null,"2006-10-01","ESC238991",null,1,0.023,0.11,null,null,1.13553]
["LL_AW2","ESC2","LL_OH2",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.11,null,null,1.16164719]
["LL_AW2","ESC2","LL_OH2",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.11,null,null,1.1883648900000001]
["LL_AW2","ESC2","LL_OH2",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.11,null,null,1.2156975300000001]
["LL_AW2","ESC2","LL_OH2",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LL_AW2","ESC2","LL_OH2",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LL_AW2","ESC2","LL_OH2",null,null,"2012-10-01","ESC241183",null,1,null,0.11,null,null,1.11]
["LL_AWARD","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LL_AWARD","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LL_AWARD","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LL_AWARD","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LL_AWARD","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LL_AWARD","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LL_AWFX",{"$nulls":5},"",{"$nulls":6},0]
["LL_AWFX1",{"$nulls":5},"",{"$nulls":6},0]
["LL_AWFX2",{"$nulls":5},"",{"$nulls":6},0]
["LL_AWFY",{"$nulls":5},"",{"$nulls":6},0]
["LL_AWFY1",{"$nulls":5},"",{"$nulls":6},0]
["LL_AWFY2",{"$nulls":5},"",{"$nulls":6},0]
["LL_AWXX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["LL_AWXX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["LL_AWXX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["LL_AWXX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["LL_AWXX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["LL_AWXX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["LL_AWXX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["LL_AWXX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["LL_AWXX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["LL_AWXX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["LL_AWXX2","ESC2",null,null,null,"2006-10-01","ESC238991",null,1,0.023,null,null,null,1.023]
["LL_AWXX2","ESC2",null,null,null,"2007-10-01","ESC239356",null,1,0.046529,null,null,null,1.046529]
["LL_AWXX2","ESC2",null,null,null,"2008-10-01","ESC239722",null,1,0.070599,null,null,null,1.070599]
["LL_AWXX2","ESC2",null,null,null,"2009-10-01","ESC240087",null,1,0.095223,null,null,null,1.095223]
["LL_AWXX2","ESC2",null,null,null,"2010-10-01","ESC240452",null,1,0.120413,null,null,null,1.120413]
["LL_AWXX2","ESC2",null,null,null,"2011-10-01","ESC240817",null,1,0.120413,null,null,null,1.120413]
["LL_AWXX2","ESC2",null,null,null,"2012-10-01","ESC241183",null,1,{"$nulls":4},1]
["LL_CCA","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_CCA","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_CCA","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_CCA","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_CCA","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_CCA","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_CE","ESC",null,null,null,"2003-10-01","ESC37895",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_CE","ESC",null,null,null,"2004-10-01","ESC38261",null,176.59423076923076,0.029,null,null,null,181.71546346153843]
["LL_CE","ESC",null,null,null,"2005-10-01","ESC38626",null,176.59423076923076,0.057812,null,null,null,186.80349643846154]
["LL_CE","ESC",null,null,null,"2006-10-01","ESC38991",null,176.59423076923076,0.085315,null,null,null,191.6603675673077]
["LL_CE","ESC",null,null,null,"2007-10-01","ESC39356",null,176.59423076923076,0.113533,null,null,null,196.64350357115381]
["LL_CE","ESC",null,null,null,"2008-10-01","ESC39722",null,176.59423076923076,0.142485,null,null,null,201.7562597403846]
["LL_CE1","ESC1",null,null,null,"2005-10-01","ESC138626",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_CE1","ESC1",null,null,null,"2006-10-01","ESC138991",null,176.59423076923076,0.026,null,null,null,181.18568076923077]
["LL_CE1","ESC1",null,null,null,"2007-10-01","ESC139356",null,176.59423076923076,0.052676,null,null,null,185.89650846923075]
["LL_CE1","ESC1",null,null,null,"2008-10-01","ESC139722",null,176.59423076923076,0.08004558,null,null,null,190.72981839580768]
["LL_CE2","ESC2",null,null,null,"2006-10-01","ESC238991",null,176.59423076923076,0.023,null,null,null,180.65589807692305]
["LL_CE2","ESC2",null,null,null,"2007-10-01","ESC239356",null,176.59423076923076,0.046529,null,null,null,184.8109837326923]
["LL_CE2","ESC2",null,null,null,"2008-10-01","ESC239722",null,176.59423076923076,0.070599,null,null,null,189.0616068673077]
["LL_CE2","ESC2",null,null,null,"2009-10-01","ESC240087",null,176.59423076923076,0.095223,null,null,null,193.41006320576923]
["LL_CE2","ESC2",null,null,null,"2010-10-01","ESC240452",null,176.59423076923076,0.120413,null,null,null,197.85847187884616]
["LL_CE2","ESC2",null,null,null,"2011-10-01","ESC240817",null,176.59423076923076,0.120413,null,null,null,197.85847187884616]
["LL_CE2","ESC2",null,null,null,"2012-10-01","ESC241183",null,176.59423076923076,{"$nulls":4},176.59423076923076]
["LL_CP","ESC",null,null,null,"2003-10-01","ESC37895",null,189.60865384615386,0,null,null,null,189.60865384615386]
["LL_CP","ESC",null,null,null,"2004-10-01","ESC38261",null,189.60865384615386,0.029,null,null,null,195.10730480769232]
["LL_CP","ESC",null,null,null,"2005-10-01","ESC38626",null,189.60865384615386,0.057812,null,null,null,200.5703093423077]
["LL_CP","ESC",null,null,null,"2006-10-01","ESC38991",null,189.60865384615386,0.085315,null,null,null,205.7851161490385]
["LL_CP","ESC",null,null,null,"2007-10-01","ESC39356",null,189.60865384615386,0.113533,null,null,null,211.13549314326923]
["LL_CP","ESC",null,null,null,"2008-10-01","ESC39722",null,189.60865384615386,0.142485,null,null,null,216.62504288942307]
["LL_CP1","ESC1",null,null,null,"2005-10-01","ESC138626",null,189.60865384615386,0,null,null,null,189.60865384615386]
["LL_CP1","ESC1",null,null,null,"2006-10-01","ESC138991",null,189.60865384615386,0.026,null,null,null,194.53847884615385]
["LL_CP1","ESC1",null,null,null,"2007-10-01","ESC139356",null,189.60865384615386,0.052676,null,null,null,199.59647929615386]
["LL_CP1","ESC1",null,null,null,"2008-10-01","ESC139722",null,189.60865384615386,0.08004558,null,null,null,204.78598851628846]
["LL_CP2","ESC2",null,null,null,"2006-10-01","ESC238991",null,189.60865384615386,0.023,null,null,null,193.96965288461539]
["LL_CP2","ESC2",null,null,null,"2007-10-01","ESC239356",null,189.60865384615386,0.046529,null,null,null,198.43095490096155]
["LL_CP2","ESC2",null,null,null,"2008-10-01","ESC239722",null,189.60865384615386,0.070599,null,null,null,202.99483519903848]
["LL_CP2","ESC2",null,null,null,"2009-10-01","ESC240087",null,189.60865384615386,0.095223,null,null,null,207.66375869134617]
["LL_CP2","ESC2",null,null,null,"2010-10-01","ESC240452",null,189.60865384615386,0.120413,null,null,null,212.4400006817308]
["LL_CP2","ESC2",null,null,null,"2011-10-01","ESC240817",null,189.60865384615386,0.120413,null,null,null,212.4400006817308]
["LL_CP2","ESC2",null,null,null,"2012-10-01","ESC241183",null,189.60865384615386,{"$nulls":4},189.60865384615386]
["LL_CT","ESC",null,null,null,"2003-10-01","ESC37895",null,137.21778846153848,0,null,null,null,137.21778846153848]
["LL_CT","ESC",null,null,null,"2004-10-01","ESC38261",null,137.21778846153848,0.029,null,null,null,141.19710432692307]
["LL_CT","ESC",null,null,null,"2005-10-01","ESC38626",null,137.21778846153848,0.057812,null,null,null,145.15062324807693]
["LL_CT","ESC",null,null,null,"2006-10-01","ESC38991",null,137.21778846153848,0.085315,null,null,null,148.92452408413465]
["LL_CT","ESC",null,null,null,"2007-10-01","ESC39356",null,137.21778846153848,0.113533,null,null,null,152.79653563894232]
["LL_CT","ESC",null,null,null,"2008-10-01","ESC39722",null,137.21778846153848,0.142485,null,null,null,156.76926505048078]
["LL_EE","ESC",null,null,null,"2003-10-01","ESC37895",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_EE","ESC",null,null,null,"2004-10-01","ESC38261",null,176.59423076923076,0.029,null,null,null,181.71546346153843]
["LL_EE","ESC",null,null,null,"2005-10-01","ESC38626",null,176.59423076923076,0.057812,null,null,null,186.80349643846154]
["LL_EE","ESC",null,null,null,"2006-10-01","ESC38991",null,176.59423076923076,0.085315,null,null,null,191.6603675673077]
["LL_EE","ESC",null,null,null,"2007-10-01","ESC39356",null,176.59423076923076,0.113533,null,null,null,196.64350357115381]
["LL_EE","ESC",null,null,null,"2008-10-01","ESC39722",null,176.59423076923076,0.142485,null,null,null,201.7562597403846]
["LL_EE1","ESC1",null,null,null,"2005-10-01","ESC138626",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_EE1","ESC1",null,null,null,"2006-10-01","ESC138991",null,176.59423076923076,0.026,null,null,null,181.18568076923077]
["LL_EE1","ESC1",null,null,null,"2007-10-01","ESC139356",null,176.59423076923076,0.052676,null,null,null,185.89650846923075]
["LL_EE1","ESC1",null,null,null,"2008-10-01","ESC139722",null,176.59423076923076,0.08004558,null,null,null,190.72981839580768]
["LL_EE2","ESC2",null,null,null,"2006-10-01","ESC238991",null,176.59423076923076,0.023,null,null,null,180.65589807692305]
["LL_EE2","ESC2",null,null,null,"2007-10-01","ESC239356",null,176.59423076923076,0.046529,null,null,null,184.8109837326923]
["LL_EE2","ESC2",null,null,null,"2008-10-01","ESC239722",null,176.59423076923076,0.070599,null,null,null,189.0616068673077]
["LL_EE2","ESC2",null,null,null,"2009-10-01","ESC240087",null,176.59423076923076,0.095223,null,null,null,193.41006320576923]
["LL_EE2","ESC2",null,null,null,"2010-10-01","ESC240452",null,176.59423076923076,0.120413,null,null,null,197.85847187884616]
["LL_EE2","ESC2",null,null,null,"2011-10-01","ESC240817",null,176.59423076923076,0.120413,null,null,null,197.85847187884616]
["LL_EE2","ESC2",null,null,null,"2012-10-01","ESC241183",null,176.59423076923076,{"$nulls":4},176.59423076923076]
["LL_KCA","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_KCA","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_KCA","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_KCA","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_KCA","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_KCA","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_KE","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_KE","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_KE","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_KE","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_KE","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_KE","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_KT","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_KT","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_KT","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_KT","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_KT","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_KT","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_MDD","ESC",null,null,null,"2003-10-01","ESC37895",null,162.0105769230769,0,null,null,null,162.0105769230769]
["LL_MDD","ESC",null,null,null,"2004-10-01","ESC38261",null,162.0105769230769,0.029,null,null,null,166.70888365384613]
["LL_MDD","ESC",null,null,null,"2005-10-01","ESC38626",null,162.0105769230769,0.057812,null,null,null,171.37673239615384]
["LL_MDD","ESC",null,null,null,"2006-10-01","ESC38991",null,162.0105769230769,0.085315,null,null,null,175.83250929326923]
["LL_MDD","ESC",null,null,null,"2007-10-01","ESC39356",null,162.0105769230769,0.113533,null,null,null,180.40412375288457]
["LL_MDD","ESC",null,null,null,"2008-10-01","ESC39722",null,162.0105769230769,0.142485,null,null,null,185.0946539759615]
["LL_MDD1","ESC1",null,null,null,"2005-10-01","ESC138626",null,162.0105769230769,0,null,null,null,162.0105769230769]
["LL_MDD1","ESC1",null,null,null,"2006-10-01","ESC138991",null,162.0105769230769,0.026,null,null,null,166.22285192307692]
["LL_MDD1","ESC1",null,null,null,"2007-10-01","ESC139356",null,162.0105769230769,0.052676,null,null,null,170.5446460730769]
["LL_MDD1","ESC1",null,null,null,"2008-10-01","ESC139722",null,162.0105769230769,0.08004558,null,null,null,174.9788075190192]
["LL_MDD2","ESC2",null,null,null,"2006-10-01","ESC238991",null,162.0105769230769,0.023,null,null,null,165.73682019230768]
["LL_MDD2","ESC2",null,null,null,"2007-10-01","ESC239356",null,162.0105769230769,0.046529,null,null,null,169.54876705673075]
["LL_MDD2","ESC2",null,null,null,"2008-10-01","ESC239722",null,162.0105769230769,0.070599,null,null,null,173.44836164326924]
["LL_MDD2","ESC2",null,null,null,"2009-10-01","ESC240087",null,162.0105769230769,0.095223,null,null,null,177.43771008942306]
["LL_MDD2","ESC2",null,null,null,"2010-10-01","ESC240452",null,162.0105769230769,0.120413,null,null,null,181.51875652211538]
["LL_MDD2","ESC2",null,null,null,"2011-10-01","ESC240817",null,162.0105769230769,0.120413,null,null,null,181.51875652211538]
["LL_MDD2","ESC2",null,null,null,"2012-10-01","ESC241183",null,162.0105769230769,{"$nulls":4},162.0105769230769]
["LL_ME","ESC",null,null,null,"2003-10-01","ESC37895",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_ME","ESC",null,null,null,"2004-10-01","ESC38261",null,176.59423076923076,0.029,null,null,null,181.71546346153843]
["LL_ME","ESC",null,null,null,"2005-10-01","ESC38626",null,176.59423076923076,0.057812,null,null,null,186.80349643846154]
["LL_ME","ESC",null,null,null,"2006-10-01","ESC38991",null,176.59423076923076,0.085315,null,null,null,191.6603675673077]
["LL_ME","ESC",null,null,null,"2007-10-01","ESC39356",null,176.59423076923076,0.113533,null,null,null,196.64350357115381]
["LL_ME","ESC",null,null,null,"2008-10-01","ESC39722",null,176.59423076923076,0.142485,null,null,null,201.7562597403846]
["LL_ME1","ESC1",null,null,null,"2005-10-01","ESC138626",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_ME1","ESC1",null,null,null,"2006-10-01","ESC138991",null,176.59423076923076,0.026,null,null,null,181.18568076923077]
["LL_ME1","ESC1",null,null,null,"2007-10-01","ESC139356",null,176.59423076923076,0.052676,null,null,null,185.89650846923075]
["LL_ME1","ESC1",null,null,null,"2008-10-01","ESC139722",null,176.59423076923076,0.08004558,null,null,null,190.72981839580768]
["LL_ME2","ESC2",null,null,null,"2006-10-01","ESC238991",null,176.59423076923076,0.023,null,null,null,180.65589807692305]
["LL_ME2","ESC2",null,null,null,"2007-10-01","ESC239356",null,176.59423076923076,0.046529,null,null,null,184.8109837326923]
["LL_ME2","ESC2",null,null,null,"2008-10-01","ESC239722",null,176.59423076923076,0.070599,null,null,null,189.0616068673077]
["LL_ME2","ESC2",null,null,null,"2009-10-01","ESC240087",null,176.59423076923076,0.095223,null,null,null,193.41006320576923]
["LL_ME2","ESC2",null,null,null,"2010-10-01","ESC240452",null,176.59423076923076,0.120413,null,null,null,197.85847187884616]
["LL_ME2","ESC2",null,null,null,"2011-10-01","ESC240817",null,176.59423076923076,0.120413,null,null,null,197.85847187884616]
["LL_ME2","ESC2",null,null,null,"2012-10-01","ESC241183",null,176.59423076923076,{"$nulls":4},176.59423076923076]
["LL_MES","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_MES","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_MES","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_MES","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_MES","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_MES","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_MFAT","ESC",null,null,null,"2003-10-01","ESC37895",null,137.21778846153848,0,null,null,null,137.21778846153848]
["LL_MFAT","ESC",null,null,null,"2004-10-01","ESC38261",null,137.21778846153848,0.029,null,null,null,141.19710432692307]
["LL_MFAT","ESC",null,null,null,"2005-10-01","ESC38626",null,137.21778846153848,0.057812,null,null,null,145.15062324807693]
["LL_MFAT","ESC",null,null,null,"2006-10-01","ESC38991",null,137.21778846153848,0.085315,null,null,null,148.92452408413465]
["LL_MFAT","ESC",null,null,null,"2007-10-01","ESC39356",null,137.21778846153848,0.113533,null,null,null,152.79653563894232]
["LL_MFAT","ESC",null,null,null,"2008-10-01","ESC39722",null,137.21778846153848,0.142485,null,null,null,156.76926505048078]
["LL_MFAT1","ESC1",null,null,null,"2005-10-01","ESC138626",null,137.21778846153848,0,null,null,null,137.21778846153848]
["LL_MFAT1","ESC1",null,null,null,"2006-10-01","ESC138991",null,137.21778846153848,0.026,null,null,null,140.7854509615385]
["LL_MFAT1","ESC1",null,null,null,"2007-10-01","ESC139356",null,137.21778846153848,0.052676,null,null,null,144.44587268653848]
["LL_MFAT1","ESC1",null,null,null,"2008-10-01","ESC139722",null,137.21778846153848,0.08004558,null,null,null,148.2014659252596]
["LL_MFAT2","ESC2",null,null,null,"2006-10-01","ESC238991",null,137.21778846153848,0.023,null,null,null,140.37379759615385]
["LL_MFAT2","ESC2",null,null,null,"2007-10-01","ESC239356",null,137.21778846153848,0.046529,null,null,null,143.6023949408654]
["LL_MFAT2","ESC2",null,null,null,"2008-10-01","ESC239722",null,137.21778846153848,0.070599,null,null,null,146.90522710913464]
["LL_MFAT2","ESC2",null,null,null,"2009-10-01","ESC240087",null,137.21778846153848,0.095223,null,null,null,150.28407793221157]
["LL_MFAT2","ESC2",null,null,null,"2010-10-01","ESC240452",null,137.21778846153848,0.120413,null,null,null,153.74059402355772]
["LL_MFAT2","ESC2",null,null,null,"2011-10-01","ESC240817",null,137.21778846153848,0.120413,null,null,null,153.74059402355772]
["LL_MFAT2","ESC2",null,null,null,"2012-10-01","ESC241183",null,137.21778846153848,{"$nulls":4},137.21778846153848]
["LL_MFMS","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_MFMS","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_MFMS","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_MFMS","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_MFMS","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_MFMS","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_MFPC","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_MFPC","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_MFPC","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_MFPC","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_MFPC","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_MFPC","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_MSCS","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LL_MSCS","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LL_MSCS","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LL_MSCS","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LL_MSCS","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LL_MSCS","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LL_MSCS1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LL_MSCS1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LL_MSCS1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LL_MSCS1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LL_MSCS2","ESC2","LL_OH2",null,null,"2006-10-01","ESC238991",null,1,0.023,0.11,null,null,1.13553]
["LL_MSCS2","ESC2","LL_OH2",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.11,null,null,1.16164719]
["LL_MSCS2","ESC2","LL_OH2",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.11,null,null,1.1883648900000001]
["LL_MSCS2","ESC2","LL_OH2",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.11,null,null,1.2156975300000001]
["LL_MSCS2","ESC2","LL_OH2",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LL_MSCS2","ESC2","LL_OH2",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LL_MSCS2","ESC2","LL_OH2",null,null,"2012-10-01","ESC241183",null,1,null,0.11,null,null,1.11]
["LL_MSEG","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LL_MSEG","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LL_MSEG","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LL_MSEG","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LL_MSEG","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LL_MSEG","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LL_MSEG1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LL_MSEG1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LL_MSEG1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LL_MSEG1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LL_MSEG2","ESC2","LL_OH2",null,null,"2006-10-01","ESC238991",null,1,0.023,0.11,null,null,1.13553]
["LL_MSEG2","ESC2","LL_OH2",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.11,null,null,1.16164719]
["LL_MSEG2","ESC2","LL_OH2",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.11,null,null,1.1883648900000001]
["LL_MSEG2","ESC2","LL_OH2",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.11,null,null,1.2156975300000001]
["LL_MSEG2","ESC2","LL_OH2",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LL_MSEG2","ESC2","LL_OH2",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LL_MSEG2","ESC2","LL_OH2",null,null,"2012-10-01","ESC241183",null,1,null,0.11,null,null,1.11]
["LL_MSEQ","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LL_MSEQ","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LL_MSEQ","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LL_MSEQ","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LL_MSEQ","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LL_MSEQ","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LL_MSEQ1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LL_MSEQ1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LL_MSEQ1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LL_MSEQ1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LL_MSEQ2","ESC2","LL_OH2",null,null,"2006-10-01","ESC238991",null,1,0.023,0.11,null,null,1.13553]
["LL_MSEQ2","ESC2","LL_OH2",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.11,null,null,1.16164719]
["LL_MSEQ2","ESC2","LL_OH2",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.11,null,null,1.1883648900000001]
["LL_MSEQ2","ESC2","LL_OH2",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.11,null,null,1.2156975300000001]
["LL_MSEQ2","ESC2","LL_OH2",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LL_MSEQ2","ESC2","LL_OH2",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LL_MSEQ2","ESC2","LL_OH2",null,null,"2012-10-01","ESC241183",null,1,null,0.11,null,null,1.11]
["LL_MSPS","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LL_MSPS","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LL_MSPS","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LL_MSPS","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LL_MSPS","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LL_MSPS","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LL_MSPS1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LL_MSPS1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LL_MSPS1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LL_MSPS1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LL_MSPS2","ESC2","LL_OH2",null,null,"2006-10-01","ESC238991",null,1,0.023,0.11,null,null,1.13553]
["LL_MSPS2","ESC2","LL_OH2",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.11,null,null,1.16164719]
["LL_MSPS2","ESC2","LL_OH2",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.11,null,null,1.1883648900000001]
["LL_MSPS2","ESC2","LL_OH2",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.11,null,null,1.2156975300000001]
["LL_MSPS2","ESC2","LL_OH2",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LL_MSPS2","ESC2","LL_OH2",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LL_MSPS2","ESC2","LL_OH2",null,null,"2012-10-01","ESC241183",null,1,null,0.11,null,null,1.11]
["LL_MSSC","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LL_MSSC","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LL_MSSC","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LL_MSSC","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LL_MSSC","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LL_MSSC","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LL_MSSC1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LL_MSSC1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LL_MSSC1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LL_MSSC1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LL_MSSC2","ESC2","LL_OH2",null,null,"2006-10-01","ESC238991",null,1,0.023,0.11,null,null,1.13553]
["LL_MSSC2","ESC2","LL_OH2",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.11,null,null,1.16164719]
["LL_MSSC2","ESC2","LL_OH2",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.11,null,null,1.1883648900000001]
["LL_MSSC2","ESC2","LL_OH2",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.11,null,null,1.2156975300000001]
["LL_MSSC2","ESC2","LL_OH2",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LL_MSSC2","ESC2","LL_OH2",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LL_MSSC2","ESC2","LL_OH2",null,null,"2012-10-01","ESC241183",null,1,null,0.11,null,null,1.11]
["LL_MSTR","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LL_MSTR","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LL_MSTR","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LL_MSTR","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LL_MSTR","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LL_MSTR","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LL_MSTR1","ESC1","LL_OH",null,null,"2005-10-01","ESC138626",null,1,0,0.19,null,null,1.19]
["LL_MSTR1","ESC1","LL_OH",null,null,"2006-10-01","ESC138991",null,1,0.026,0.19,null,null,1.22094]
["LL_MSTR1","ESC1","LL_OH",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.19,null,null,1.25268444]
["LL_MSTR1","ESC1","LL_OH",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.19,null,null,1.2852542401999998]
["LL_MSTR2","ESC2","LL_OH",null,null,"2006-10-01","ESC238991",null,1,0.023,0.19,null,null,1.2173699999999998]
["LL_MSTR2","ESC2","LL_OH",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.19,null,null,1.24536951]
["LL_MSTR2","ESC2","LL_OH",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.19,null,null,1.27401281]
["LL_MSTR2","ESC2","LL_OH",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.19,null,null,1.30331537]
["LL_MSTR2","ESC2","LL_OH",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.19,null,null,1.33329147]
["LL_MSTR2","ESC2","LL_OH",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.19,null,null,1.33329147]
["LL_MSTR2","ESC2","LL_OH",null,null,"2012-10-01","ESC241183",null,1,null,0.19,null,null,1.19]
["LL_MSXX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["LL_MSXX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["LL_MSXX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["LL_MSXX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["LL_MSXX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["LL_MSXX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["LL_MSXX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["LL_MSXX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["LL_MSXX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["LL_MSXX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["LL_MSXX2","ESC2",null,null,null,"2006-10-01","ESC238991",null,1,0.023,null,null,null,1.023]
["LL_MSXX2","ESC2",null,null,null,"2007-10-01","ESC239356",null,1,0.046529,null,null,null,1.046529]
["LL_MSXX2","ESC2",null,null,null,"2008-10-01","ESC239722",null,1,0.070599,null,null,null,1.070599]
["LL_MSXX2","ESC2",null,null,null,"2009-10-01","ESC240087",null,1,0.095223,null,null,null,1.095223]
["LL_MSXX2","ESC2",null,null,null,"2010-10-01","ESC240452",null,1,0.120413,null,null,null,1.120413]
["LL_MSXX2","ESC2",null,null,null,"2011-10-01","ESC240817",null,1,0.120413,null,null,null,1.120413]
["LL_MSXX2","ESC2",null,null,null,"2012-10-01","ESC241183",null,1,{"$nulls":4},1]
["LL_MTRL","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LL_MTRL","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LL_MTRL","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LL_MTRL","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LL_MTRL","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LL_MTRL","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LL_MTRL1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LL_MTRL1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LL_MTRL1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LL_MTRL1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LL_MTRL2","ESC2","LL_OH2",null,null,"2006-10-01","ESC238991",null,1,0.023,0.11,null,null,1.13553]
["LL_MTRL2","ESC2","LL_OH2",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.11,null,null,1.16164719]
["LL_MTRL2","ESC2","LL_OH2",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.11,null,null,1.1883648900000001]
["LL_MTRL2","ESC2","LL_OH2",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.11,null,null,1.2156975300000001]
["LL_MTRL2","ESC2","LL_OH2",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LL_MTRL2","ESC2","LL_OH2",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LL_MTRL2","ESC2","LL_OH2",null,null,"2012-10-01","ESC241183",null,1,null,0.11,null,null,1.11]
["LL_MVE","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_MVE","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_MVE","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_MVE","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_MVE","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_MVE","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_PCCA","ESC",null,null,null,"2003-10-01","ESC37895",null,158.32548076923078,0,null,null,null,158.32548076923078]
["LL_PCCA","ESC",null,null,null,"2004-10-01","ESC38261",null,158.32548076923078,0.029,null,null,null,162.91691971153847]
["LL_PCCA","ESC",null,null,null,"2005-10-01","ESC38626",null,158.32548076923078,0.057812,null,null,null,167.47859346346155]
["LL_PCCA","ESC",null,null,null,"2006-10-01","ESC38991",null,158.32548076923078,0.085315,null,null,null,171.8330191610577]
["LL_PCCA","ESC",null,null,null,"2007-10-01","ESC39356",null,158.32548076923078,0.113533,null,null,null,176.30064757740385]
["LL_PCCA","ESC",null,null,null,"2008-10-01","ESC39722",null,158.32548076923078,0.142485,null,null,null,180.88448689663463]
["LL_PCCA1","ESC1",null,null,null,"2005-10-01","ESC138626",null,158.32548076923078,0,null,null,null,158.32548076923078]
["LL_PCCA1","ESC1",null,null,null,"2006-10-01","ESC138991",null,158.32548076923078,0.026,null,null,null,162.4419432692308]
["LL_PCCA1","ESC1",null,null,null,"2007-10-01","ESC139356",null,158.32548076923078,0.052676,null,null,null,166.66543379423078]
["LL_PCCA1","ESC1",null,null,null,"2008-10-01","ESC139722",null,158.32548076923078,0.08004558,null,null,null,170.99873570618269]
["LL_PCCA2","ESC2",null,null,null,"2006-10-01","ESC238991",null,158.32548076923078,0.023,null,null,null,161.96696682692308]
["LL_PCCA2","ESC2",null,null,null,"2007-10-01","ESC239356",null,158.32548076923078,0.046529,null,null,null,165.69220706394233]
["LL_PCCA2","ESC2",null,null,null,"2008-10-01","ESC239722",null,158.32548076923078,0.070599,null,null,null,169.50310138605772]
["LL_PCCA2","ESC2",null,null,null,"2009-10-01","ESC240087",null,158.32548076923078,0.095223,null,null,null,173.40170802451925]
["LL_PCCA2","ESC2",null,null,null,"2010-10-01","ESC240452",null,158.32548076923078,0.120413,null,null,null,177.38992688509617]
["LL_PCCA2","ESC2",null,null,null,"2011-10-01","ESC240817",null,158.32548076923078,0.120413,null,null,null,177.38992688509617]
["LL_PCCA2","ESC2",null,null,null,"2012-10-01","ESC241183",null,158.32548076923078,{"$nulls":4},158.32548076923078]
["LL_PCE","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_PCE","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_PCE","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_PCE","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_PCE","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_PCE","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_PCEF","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_PCEF","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_PCEF","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_PCEF","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_PCEF","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_PCEF","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_PCT","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_PCT","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_PCT","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_PCT","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_PCT","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_PCT","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_PHPD","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_PHPD","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_PHPD","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_PHPD","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_PHPD","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_PHPD","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_PHPD2","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_PHPD2","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_PHPD2","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_PHPD2","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_PHPD2","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_PHPD2","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_PHS","ESC",null,null,null,"2003-10-01","ESC37895",null,188.69326923076923,0,null,null,null,188.69326923076923]
["LL_PHS","ESC",null,null,null,"2004-10-01","ESC38261",null,188.69326923076923,0.029,null,null,null,194.16537403846152]
["LL_PHS","ESC",null,null,null,"2005-10-01","ESC38626",null,188.69326923076923,0.057812,null,null,null,199.60200451153847]
["LL_PHS","ESC",null,null,null,"2006-10-01","ESC38991",null,188.69326923076923,0.085315,null,null,null,204.7916354951923]
["LL_PHS","ESC",null,null,null,"2007-10-01","ESC39356",null,188.69326923076923,0.113533,null,null,null,210.11618216634614]
["LL_PHS","ESC",null,null,null,"2008-10-01","ESC39722",null,188.69326923076923,0.142485,null,null,null,215.57922969711538]
["LL_PHS1","ESC1",null,null,null,"2005-10-01","ESC138626",null,188.69326923076923,0,null,null,null,188.69326923076923]
["LL_PHS1","ESC1",null,null,null,"2006-10-01","ESC138991",null,188.69326923076923,0.026,null,null,null,193.59929423076923]
["LL_PHS1","ESC1",null,null,null,"2007-10-01","ESC139356",null,188.69326923076923,0.052676,null,null,null,198.63287588076923]
["LL_PHS1","ESC1",null,null,null,"2008-10-01","ESC139722",null,188.69326923076923,0.08004558,null,null,null,203.7973314084423]
["LL_PHS2","ESC2",null,null,null,"2006-10-01","ESC238991",null,188.69326923076923,0.023,null,null,null,193.0332144230769]
["LL_PHS2","ESC2",null,null,null,"2007-10-01","ESC239356",null,188.69326923076923,0.046529,null,null,null,197.4729783548077]
["LL_PHS2","ESC2",null,null,null,"2008-10-01","ESC239722",null,188.69326923076923,0.070599,null,null,null,202.01482534519232]
["LL_PHS2","ESC2",null,null,null,"2009-10-01","ESC240087",null,188.69326923076923,0.095223,null,null,null,206.6612084067308]
["LL_PHS2","ESC2",null,null,null,"2010-10-01","ESC240452",null,188.69326923076923,0.120413,null,null,null,211.41439185865386]
["LL_PHS2","ESC2",null,null,null,"2011-10-01","ESC240817",null,188.69326923076923,0.120413,null,null,null,211.41439185865386]
["LL_PHS2","ESC2",null,null,null,"2012-10-01","ESC241183",null,188.69326923076923,{"$nulls":4},188.69326923076923]
["LL_PHSS","ESC",null,null,null,"2003-10-01","ESC37895",null,208.3653846153846,0,null,null,null,208.3653846153846]
["LL_PHSS","ESC",null,null,null,"2004-10-01","ESC38261",null,208.3653846153846,0.029,null,null,null,214.40798076923076]
["LL_PHSS","ESC",null,null,null,"2005-10-01","ESC38626",null,208.3653846153846,0.057812,null,null,null,220.41140423076922]
["LL_PHSS","ESC",null,null,null,"2006-10-01","ESC38991",null,208.3653846153846,0.085315,null,null,null,226.14207740384614]
["LL_PHSS","ESC",null,null,null,"2007-10-01","ESC39356",null,208.3653846153846,0.113533,null,null,null,232.02173182692306]
["LL_PHSS","ESC",null,null,null,"2008-10-01","ESC39722",null,208.3653846153846,0.142485,null,null,null,238.05432644230768]
["LL_PHSS1","ESC1",null,null,null,"2005-10-01","ESC138626",null,208.3653846153846,0,null,null,null,208.3653846153846]
["LL_PHSS1","ESC1",null,null,null,"2006-10-01","ESC138991",null,208.3653846153846,0.026,null,null,null,213.78288461538463]
["LL_PHSS1","ESC1",null,null,null,"2007-10-01","ESC139356",null,208.3653846153846,0.052676,null,null,null,219.3412396153846]
["LL_PHSS1","ESC1",null,null,null,"2008-10-01","ESC139722",null,208.3653846153846,0.08004558,null,null,null,225.04411267884615]
["LL_PHSS2","ESC2",null,null,null,"2006-10-01","ESC238991",null,208.3653846153846,0.023,null,null,null,213.15778846153844]
["LL_PHSS2","ESC2",null,null,null,"2007-10-01","ESC239356",null,208.3653846153846,0.046529,null,null,null,218.06041759615385]
["LL_PHSS2","ESC2",null,null,null,"2008-10-01","ESC239722",null,208.3653846153846,0.070599,null,null,null,223.07577240384617]
["LL_PHSS2","ESC2",null,null,null,"2009-10-01","ESC240087",null,208.3653846153846,0.095223,null,null,null,228.20656163461538]
["LL_PHSS2","ESC2",null,null,null,"2010-10-01","ESC240452",null,208.3653846153846,0.120413,null,null,null,233.45528567307693]
["LL_PHSS2","ESC2",null,null,null,"2011-10-01","ESC240817",null,208.3653846153846,0.120413,null,null,null,233.45528567307693]
["LL_PHSS2","ESC2",null,null,null,"2012-10-01","ESC241183",null,208.3653846153846,{"$nulls":4},208.3653846153846]
["LL_PM","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_PM","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_PM","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_PM","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_PM","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_PM","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_PRC","ESC",null,null,null,"2003-10-01","ESC37895",null,162.0105769230769,0,null,null,null,162.0105769230769]
["LL_PRC","ESC",null,null,null,"2004-10-01","ESC38261",null,162.0105769230769,0.029,null,null,null,166.70888365384613]
["LL_PRC","ESC",null,null,null,"2005-10-01","ESC38626",null,162.0105769230769,0.057812,null,null,null,171.37673239615384]
["LL_PRC","ESC",null,null,null,"2006-10-01","ESC38991",null,162.0105769230769,0.085315,null,null,null,175.83250929326923]
["LL_PRC","ESC",null,null,null,"2007-10-01","ESC39356",null,162.0105769230769,0.113533,null,null,null,180.40412375288457]
["LL_PRC","ESC",null,null,null,"2008-10-01","ESC39722",null,162.0105769230769,0.142485,null,null,null,185.0946539759615]
["LL_PRC1","ESC1",null,null,null,"2005-10-01","ESC138626",null,162.0105769230769,0,null,null,null,162.0105769230769]
["LL_PRC1","ESC1",null,null,null,"2006-10-01","ESC138991",null,162.0105769230769,0.026,null,null,null,166.22285192307692]
["LL_PRC1","ESC1",null,null,null,"2007-10-01","ESC139356",null,162.0105769230769,0.052676,null,null,null,170.5446460730769]
["LL_PRC1","ESC1",null,null,null,"2008-10-01","ESC139722",null,162.0105769230769,0.08004558,null,null,null,174.9788075190192]
["LL_PRC2","ESC2",null,null,null,"2006-10-01","ESC238991",null,162.0105769230769,0.023,null,null,null,165.73682019230768]
["LL_PRC2","ESC2",null,null,null,"2007-10-01","ESC239356",null,162.0105769230769,0.046529,null,null,null,169.54876705673075]
["LL_PRC2","ESC2",null,null,null,"2008-10-01","ESC239722",null,162.0105769230769,0.070599,null,null,null,173.44836164326924]
["LL_PRC2","ESC2",null,null,null,"2009-10-01","ESC240087",null,162.0105769230769,0.095223,null,null,null,177.43771008942306]
["LL_PRC2","ESC2",null,null,null,"2010-10-01","ESC240452",null,162.0105769230769,0.120413,null,null,null,181.51875652211538]
["LL_PRC2","ESC2",null,null,null,"2011-10-01","ESC240817",null,162.0105769230769,0.120413,null,null,null,181.51875652211538]
["LL_PRC2","ESC2",null,null,null,"2012-10-01","ESC241183",null,162.0105769230769,{"$nulls":4},162.0105769230769]
["LL_PRE","ESC",null,null,null,"2003-10-01","ESC37895",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_PRE","ESC",null,null,null,"2004-10-01","ESC38261",null,176.59423076923076,0.029,null,null,null,181.71546346153843]
["LL_PRE","ESC",null,null,null,"2005-10-01","ESC38626",null,176.59423076923076,0.057812,null,null,null,186.80349643846154]
["LL_PRE","ESC",null,null,null,"2006-10-01","ESC38991",null,176.59423076923076,0.085315,null,null,null,191.6603675673077]
["LL_PRE","ESC",null,null,null,"2007-10-01","ESC39356",null,176.59423076923076,0.113533,null,null,null,196.64350357115381]
["LL_PRE","ESC",null,null,null,"2008-10-01","ESC39722",null,176.59423076923076,0.142485,null,null,null,201.7562597403846]
["LL_PRE1","ESC1",null,null,null,"2005-10-01","ESC138626",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_PRE1","ESC1",null,null,null,"2006-10-01","ESC138991",null,176.59423076923076,0.026,null,null,null,181.18568076923077]
["LL_PRE1","ESC1",null,null,null,"2007-10-01","ESC139356",null,176.59423076923076,0.052676,null,null,null,185.89650846923075]
["LL_PRE1","ESC1",null,null,null,"2008-10-01","ESC139722",null,176.59423076923076,0.08004558,null,null,null,190.72981839580768]
["LL_PRE2","ESC2",null,null,null,"2006-10-01","ESC238991",null,176.59423076923076,0.023,null,null,null,180.65589807692305]
["LL_PRE2","ESC2",null,null,null,"2007-10-01","ESC239356",null,176.59423076923076,0.046529,null,null,null,184.8109837326923]
["LL_PRE2","ESC2",null,null,null,"2008-10-01","ESC239722",null,176.59423076923076,0.070599,null,null,null,189.0616068673077]
["LL_PRE2","ESC2",null,null,null,"2009-10-01","ESC240087",null,176.59423076923076,0.095223,null,null,null,193.41006320576923]
["LL_PRE2","ESC2",null,null,null,"2010-10-01","ESC240452",null,176.59423076923076,0.120413,null,null,null,197.85847187884616]
["LL_PRE2","ESC2",null,null,null,"2011-10-01","ESC240817",null,176.59423076923076,0.120413,null,null,null,197.85847187884616]
["LL_PRE2","ESC2",null,null,null,"2012-10-01","ESC241183",null,176.59423076923076,{"$nulls":4},176.59423076923076]
["LL_RP","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_RP","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_RP","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_RP","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_RP","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_RP","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_SEE","ESC",null,null,null,"2003-10-01","ESC37895",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_SEE","ESC",null,null,null,"2004-10-01","ESC38261",null,176.59423076923076,0.029,null,null,null,181.71546346153843]
["LL_SEE","ESC",null,null,null,"2005-10-01","ESC38626",null,176.59423076923076,0.057812,null,null,null,186.80349643846154]
["LL_SEE","ESC",null,null,null,"2006-10-01","ESC38991",null,176.59423076923076,0.085315,null,null,null,191.6603675673077]
["LL_SEE","ESC",null,null,null,"2007-10-01","ESC39356",null,176.59423076923076,0.113533,null,null,null,196.64350357115381]
["LL_SEE","ESC",null,null,null,"2008-10-01","ESC39722",null,176.59423076923076,0.142485,null,null,null,201.7562597403846]
["LL_SEE1","ESC1",null,null,null,"2005-10-01","ESC138626",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_SEE1","ESC1",null,null,null,"2006-10-01","ESC138991",null,176.59423076923076,0.026,null,null,null,181.18568076923077]
["LL_SEE1","ESC1",null,null,null,"2007-10-01","ESC139356",null,176.59423076923076,0.052676,null,null,null,185.89650846923075]
["LL_SEE1","ESC1",null,null,null,"2008-10-01","ESC139722",null,176.59423076923076,0.08004558,null,null,null,190.72981839580768]
["LL_SEE2","ESC2",null,null,null,"2006-10-01","ESC238991",null,176.59423076923076,0.023,null,null,null,180.65589807692305]
["LL_SEE2","ESC2",null,null,null,"2007-10-01","ESC239356",null,176.59423076923076,0.046529,null,null,null,184.8109837326923]
["LL_SEE2","ESC2",null,null,null,"2008-10-01","ESC239722",null,176.59423076923076,0.070599,null,null,null,189.0616068673077]
["LL_SEE2","ESC2",null,null,null,"2009-10-01","ESC240087",null,176.59423076923076,0.095223,null,null,null,193.41006320576923]
["LL_SEE2","ESC2",null,null,null,"2010-10-01","ESC240452",null,176.59423076923076,0.120413,null,null,null,197.85847187884616]
["LL_SEE2","ESC2",null,null,null,"2011-10-01","ESC240817",null,176.59423076923076,0.120413,null,null,null,197.85847187884616]
["LL_SEE2","ESC2",null,null,null,"2012-10-01","ESC241183",null,176.59423076923076,{"$nulls":4},176.59423076923076]
["LL_SEL","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_SEL","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_SEL","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_SEL","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_SEL","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_SEL","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_SEPM","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_SEPM","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_SEPM","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_SEPM","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_SEPM","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_SEPM","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_TMUC","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_TMUC","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_TMUC","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_TMUC","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_TMUC","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_TMUC","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_TMUE","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_TMUE","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_TMUE","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_TMUE","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_TMUE","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_TMUE","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_TMUI","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_TMUI","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_TMUI","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_TMUI","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_TMUI","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_TMUI","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_TMUO","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_TMUO","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_TMUO","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_TMUO","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_TMUO","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_TMUO","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_TMUP","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_TMUP","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_TMUP","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_TMUP","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_TMUP","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_TMUP","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_TMUW","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_TMUW","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_TMUW","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_TMUW","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_TMUW","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_TMUW","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["PED",{"$nulls":5},"",{"$nulls":6},0]
["R&D",{"$nulls":5},"",{"$nulls":6},0]
["RES",{"$nulls":5},"",{"$nulls":6},0]
["SA_GCFX1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SA_GCFX2",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SA_GCSS","ESC_CF","SL_OH2",null,null,"2004-10-01","ESC_CF38261",null,1,0,0.06,null,null,1.06]
["SA_GCSS","ESC_CF","SL_OH2",null,null,"2005-10-01","ESC_CF38626",null,1,0.03,0.06,null,null,1.0918]
["SA_GCSS","ESC_CF","SL_OH2",null,null,"2006-10-01","ESC_CF38991",null,1,0.08,0.06,null,null,1.1448]
["SA_GCSS","ESC_CF","SL_OH2",null,null,"2007-10-01","ESC_CF39356",null,1,0.19,0.06,null,null,1.2614]
["SA_GCSS","ESC_CF","SL_OH2",null,null,"2008-10-01","ESC_CF39722",null,1,0.3,0.06,null,null,1.3780000000000001]
["SA_GCSS","ESC_CF","SL_OH2",null,null,"2009-10-01","ESC_CF40087",null,1,0.41,0.06,null,null,1.4946]
["SA_GCSS1","ESC_CF","SL_OHN4",null,null,"2004-10-01","ESC_CF38261",null,1,0,0.0552,null,null,1.0552]
["SA_GCSS1","ESC_CF","SL_OHN4",null,null,"2005-10-01","ESC_CF38626",null,1,0.03,0.0552,null,null,1.086856]
["SA_GCSS1","ESC_CF","SL_OHN4",null,null,"2006-10-01","ESC_CF38991",null,1,0.08,0.0552,null,null,1.139616]
["SA_GCSS1","ESC_CF","SL_OHN4",null,null,"2007-10-01","ESC_CF39356",null,1,0.19,0.0552,null,null,1.255688]
["SA_GCSS1","ESC_CF","SL_OHN4",null,null,"2008-10-01","ESC_CF39722",null,1,0.3,0.0552,null,null,1.3717599999999999]
["SA_GCSS1","ESC_CF","SL_OHN4",null,null,"2009-10-01","ESC_CF40087",null,1,0.41,0.0552,null,null,1.4878319999999998]
["SA_GCSS2","ESC_CF","SL_OHN4",null,null,"2004-10-01","ESC_CF38261",null,1,0,0.0552,null,null,1.0552]
["SA_GCSS2","ESC_CF","SL_OHN4",null,null,"2005-10-01","ESC_CF38626",null,1,0.03,0.0552,null,null,1.086856]
["SA_GCSS2","ESC_CF","SL_OHN4",null,null,"2006-10-01","ESC_CF38991",null,1,0.08,0.0552,null,null,1.139616]
["SA_GCSS2","ESC_CF","SL_OHN4",null,null,"2007-10-01","ESC_CF39356",null,1,0.19,0.0552,null,null,1.255688]
["SA_GCSS2","ESC_CF","SL_OHN4",null,null,"2008-10-01","ESC_CF39722",null,1,0.3,0.0552,null,null,1.3717599999999999]
["SA_GCSS2","ESC_CF","SL_OHN4",null,null,"2009-10-01","ESC_CF40087",null,1,0.41,0.0552,null,null,1.4878319999999998]
["SA_GCSX","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,1,0,null,null,null,1]
["SA_GCSX","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,1,0.03,null,null,null,1.03]
["SA_GCSX","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,1,0.08,null,null,null,1.08]
["SA_GCSX","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,1,0.19,null,null,null,1.19]
["SA_GCSX","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,1,0.3,null,null,null,1.3]
["SA_GCSX","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,1,0.41,null,null,null,1.41]
["SA_GCSX1","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,1,0,null,null,null,1]
["SA_GCSX1","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,1,0.03,null,null,null,1.03]
["SA_GCSX1","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,1,0.08,null,null,null,1.08]
["SA_GCSX1","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,1,0.19,null,null,null,1.19]
["SA_GCSX1","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,1,0.3,null,null,null,1.3]
["SA_GCSX1","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,1,0.41,null,null,null,1.41]
["SA_GCSX2","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,1,0,null,null,null,1]
["SA_GCSX2","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,1,0.03,null,null,null,1.03]
["SA_GCSX2","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,1,0.08,null,null,null,1.08]
["SA_GCSX2","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,1,0.19,null,null,null,1.19]
["SA_GCSX2","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,1,0.3,null,null,null,1.3]
["SA_GCSX2","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,1,0.41,null,null,null,1.41]
["SA_MSCS","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.06,null,null,0]
["SA_MSCS","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.06,null,null,0]
["SA_MSCS","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.06,null,null,0]
["SA_MSCS","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.06,null,null,0]
["SA_MSCS","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.06,null,null,0]
["SA_MSCS","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.06,null,null,0]
["SA_MSCS1","ESC1","SL_OHN4",null,null,"2005-10-01","ESC138626",null,null,0,0.0552,null,null,0]
["SA_MSCS1","ESC1","SL_OHN4",null,null,"2006-10-01","ESC138991",null,null,0.026,0.0552,null,null,0]
["SA_MSCS1","ESC1","SL_OHN4",null,null,"2007-10-01","ESC139356",null,null,0.052676,0.0552,null,null,0]
["SA_MSCS1","ESC1","SL_OHN4",null,null,"2008-10-01","ESC139722",null,null,0.08004558,0.0552,null,null,0]
["SA_MSCS2","ESC2","SL_OHN4",null,null,"2006-10-01","ESC238991",null,null,0.023,0.0552,null,null,0]
["SA_MSCS2","ESC2","SL_OHN4",null,null,"2007-10-01","ESC239356",null,null,0.046529,0.0552,null,null,0]
["SA_MSCS2","ESC2","SL_OHN4",null,null,"2008-10-01","ESC239722",null,null,0.070599,0.0552,null,null,0]
["SA_MSCS2","ESC2","SL_OHN4",null,null,"2009-10-01","ESC240087",null,null,0.095223,0.0552,null,null,0]
["SA_MSCS2","ESC2","SL_OHN4",null,null,"2010-10-01","ESC240452",null,null,0.120413,0.0552,null,null,0]
["SA_MSCS2","ESC2","SL_OHN4",null,null,"2011-10-01","ESC240817",null,null,0.120413,0.0552,null,null,0]
["SA_MSCS2","ESC2","SL_OHN4",null,null,"2012-10-01","ESC241183",null,null,null,0.0552,null,null,0]
["SA_MSEG","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SA_MSEG","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SA_MSEG","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SA_MSEG","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SA_MSEG","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SA_MSEG","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SA_MSEG1","ESC1","SL_OHN4",null,null,"2005-10-01","ESC138626",null,1,0,0.0552,null,null,1.0552]
["SA_MSEG1","ESC1","SL_OHN4",null,null,"2006-10-01","ESC138991",null,1,0.026,0.0552,null,null,1.0826352]
["SA_MSEG1","ESC1","SL_OHN4",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.0552,null,null,1.1107837151999997]
["SA_MSEG1","ESC1","SL_OHN4",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.0552,null,null,1.1396640960159998]
["SA_MSEG2","ESC2","SL_OHN4",null,null,"2006-10-01","ESC238991",null,1,0.023,0.0552,null,null,1.0794696]
["SA_MSEG2","ESC2","SL_OHN4",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.0552,null,null,1.1042974008]
["SA_MSEG2","ESC2","SL_OHN4",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.0552,null,null,1.1296960648]
["SA_MSEG2","ESC2","SL_OHN4",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.0552,null,null,1.1556793096]
["SA_MSEG2","ESC2","SL_OHN4",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.0552,null,null,1.1822597976]
["SA_MSEG2","ESC2","SL_OHN4",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.0552,null,null,1.1822597976]
["SA_MSEG2","ESC2","SL_OHN4",null,null,"2012-10-01","ESC241183",null,1,null,0.0552,null,null,1.0552]
["SA_MSEQ","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SA_MSEQ","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SA_MSEQ","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SA_MSEQ","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SA_MSEQ","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SA_MSEQ","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SA_MSEQ1","ESC1","SL_OHN4",null,null,"2005-10-01","ESC138626",null,1,0,0.0552,null,null,1.0552]
["SA_MSEQ1","ESC1","SL_OHN4",null,null,"2006-10-01","ESC138991",null,1,0.026,0.0552,null,null,1.0826352]
["SA_MSEQ1","ESC1","SL_OHN4",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.0552,null,null,1.1107837151999997]
["SA_MSEQ1","ESC1","SL_OHN4",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.0552,null,null,1.1396640960159998]
["SA_MSEQ2","ESC2","SL_OHN4",null,null,"2006-10-01","ESC238991",null,1,0.023,0.0552,null,null,1.0794696]
["SA_MSEQ2","ESC2","SL_OHN4",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.0552,null,null,1.1042974008]
["SA_MSEQ2","ESC2","SL_OHN4",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.0552,null,null,1.1296960648]
["SA_MSEQ2","ESC2","SL_OHN4",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.0552,null,null,1.1556793096]
["SA_MSEQ2","ESC2","SL_OHN4",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.0552,null,null,1.1822597976]
["SA_MSEQ2","ESC2","SL_OHN4",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.0552,null,null,1.1822597976]
["SA_MSEQ2","ESC2","SL_OHN4",null,null,"2012-10-01","ESC241183",null,1,null,0.0552,null,null,1.0552]
["SA_MSPF","SL_OH2",{"$nulls":4},"SL_OH2",null,1,0.06,null,null,null,1.06]
["SA_MSPF1","SL_OHN4",{"$nulls":4},"SL_OHN4",null,1,0.0552,null,null,null,1.0552]
["SA_MSPF2","SL_OHN4",{"$nulls":4},"SL_OHN4",null,1,0.0552,null,null,null,1.0552]
["SA_MSPS","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SA_MSPS","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SA_MSPS","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SA_MSPS","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SA_MSPS","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SA_MSPS","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SA_MSPS1","ESC1","SL_OHN4",null,null,"2005-10-01","ESC138626",null,1,0,0.0552,null,null,1.0552]
["SA_MSPS1","ESC1","SL_OHN4",null,null,"2006-10-01","ESC138991",null,1,0.026,0.0552,null,null,1.0826352]
["SA_MSPS1","ESC1","SL_OHN4",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.0552,null,null,1.1107837151999997]
["SA_MSPS1","ESC1","SL_OHN4",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.0552,null,null,1.1396640960159998]
["SA_MSPS2","ESC2","SL_OHN4",null,null,"2006-10-01","ESC238991",null,1,0.023,0.0552,null,null,1.0794696]
["SA_MSPS2","ESC2","SL_OHN4",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.0552,null,null,1.1042974008]
["SA_MSPS2","ESC2","SL_OHN4",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.0552,null,null,1.1296960648]
["SA_MSPS2","ESC2","SL_OHN4",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.0552,null,null,1.1556793096]
["SA_MSPS2","ESC2","SL_OHN4",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.0552,null,null,1.1822597976]
["SA_MSPS2","ESC2","SL_OHN4",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.0552,null,null,1.1822597976]
["SA_MSPS2","ESC2","SL_OHN4",null,null,"2012-10-01","ESC241183",null,1,null,0.0552,null,null,1.0552]
["SA_MSPX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["SA_MSPX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["SA_MSPX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["SA_MSPX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["SA_MSPX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["SA_MSPX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["SA_MSPX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["SA_MSPX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["SA_MSPX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["SA_MSPX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["SA_MSPX2","ESC2",null,null,null,"2006-10-01","ESC238991",null,1,0.023,null,null,null,1.023]
["SA_MSPX2","ESC2",null,null,null,"2007-10-01","ESC239356",null,1,0.046529,null,null,null,1.046529]
["SA_MSPX2","ESC2",null,null,null,"2008-10-01","ESC239722",null,1,0.070599,null,null,null,1.070599]
["SA_MSPX2","ESC2",null,null,null,"2009-10-01","ESC240087",null,1,0.095223,null,null,null,1.095223]
["SA_MSPX2","ESC2",null,null,null,"2010-10-01","ESC240452",null,1,0.120413,null,null,null,1.120413]
["SA_MSPX2","ESC2",null,null,null,"2011-10-01","ESC240817",null,1,0.120413,null,null,null,1.120413]
["SA_MSPX2","ESC2",null,null,null,"2012-10-01","ESC241183",null,1,{"$nulls":4},1]
["SA_MSPY",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SA_MSPY1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SA_MSPY2",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SA_MSSC","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SA_MSSC","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SA_MSSC","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SA_MSSC","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SA_MSSC","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SA_MSSC","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SA_MSSC1","ESC1","SL_OHN4",null,null,"2005-10-01","ESC138626",null,1,0,0.0552,null,null,1.0552]
["SA_MSSC1","ESC1","SL_OHN4",null,null,"2006-10-01","ESC138991",null,1,0.026,0.0552,null,null,1.0826352]
["SA_MSSC1","ESC1","SL_OHN4",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.0552,null,null,1.1107837151999997]
["SA_MSSC1","ESC1","SL_OHN4",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.0552,null,null,1.1396640960159998]
["SA_MSSC2","ESC2","SL_OHN4",null,null,"2006-10-01","ESC238991",null,1,0.023,0.0552,null,null,1.0794696]
["SA_MSSC2","ESC2","SL_OHN4",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.0552,null,null,1.1042974008]
["SA_MSSC2","ESC2","SL_OHN4",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.0552,null,null,1.1296960648]
["SA_MSSC2","ESC2","SL_OHN4",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.0552,null,null,1.1556793096]
["SA_MSSC2","ESC2","SL_OHN4",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.0552,null,null,1.1822597976]
["SA_MSSC2","ESC2","SL_OHN4",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.0552,null,null,1.1822597976]
["SA_MSSC2","ESC2","SL_OHN4",null,null,"2012-10-01","ESC241183",null,1,null,0.0552,null,null,1.0552]
["SA_MSSF","SL_OH2",{"$nulls":4},"SL_OH2",null,1,0.06,null,null,null,1.06]
["SA_MSSF1","SL_OHN4",{"$nulls":4},"SL_OHN4",null,1,0.0552,null,null,null,1.0552]
["SA_MSSF2","SL_OHN4",{"$nulls":4},"SL_OHN4",null,1,0.0552,null,null,null,1.0552]
["SA_MSSY",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SA_MSSY1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SA_MSSY2",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SA_MSXX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["SA_MSXX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["SA_MSXX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["SA_MSXX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["SA_MSXX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["SA_MSXX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["SA_MSXX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["SA_MSXX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["SA_MSXX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["SA_MSXX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["SA_MSXX2","ESC2",null,null,null,"2006-10-01","ESC238991",null,1,0.023,null,null,null,1.023]
["SA_MSXX2","ESC2",null,null,null,"2007-10-01","ESC239356",null,1,0.046529,null,null,null,1.046529]
["SA_MSXX2","ESC2",null,null,null,"2008-10-01","ESC239722",null,1,0.070599,null,null,null,1.070599]
["SA_MSXX2","ESC2",null,null,null,"2009-10-01","ESC240087",null,1,0.095223,null,null,null,1.095223]
["SA_MSXX2","ESC2",null,null,null,"2010-10-01","ESC240452",null,1,0.120413,null,null,null,1.120413]
["SA_MSXX2","ESC2",null,null,null,"2011-10-01","ESC240817",null,1,0.120413,null,null,null,1.120413]
["SA_MSXX2","ESC2",null,null,null,"2012-10-01","ESC241183",null,1,{"$nulls":4},1]
["SLAC_LABOR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,null,0,0.29,0.215,0.2,0]
["SLAC_LABOR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,null,0.029,0.29,0.215,0.2,0]
["SLAC_LABOR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,null,0.057812,0.29,0.215,0.2,0]
["SLAC_LABOR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,null,0.085315,0.29,0.215,0.2,0]
["SLAC_LABOR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,null,0.113533,0.29,0.215,0.2,0]
["SLAC_LABOR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,null,0.142485,0.29,0.215,0.2,0]
["SLAC_NON-LABOR","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.06,null,null,0]
["SLAC_NON-LABOR","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.06,null,null,0]
["SLAC_NON-LABOR","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.06,null,null,0]
["SLAC_NON-LABOR","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.06,null,null,0]
["SLAC_NON-LABOR","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.06,null,null,0]
["SLAC_NON-LABOR","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.06,null,null,0]
["SLAC_SHOPS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2003-10-01","ESC37895",null,null,0,0,0,0.2,0]
["SLAC_SHOPS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2004-10-01","ESC38261",null,null,0.029,0,0,0.2,0]
["SLAC_SHOPS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2005-10-01","ESC38626",null,null,0.057812,0,0,0.2,0]
["SLAC_SHOPS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2006-10-01","ESC38991",null,null,0.085315,0,0,0.2,0]
["SLAC_SHOPS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2007-10-01","ESC39356",null,null,0.113533,0,0,0.2,0]
["SLAC_SHOPS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2008-10-01","ESC39722",null,null,0.142485,0,0,0.2,0]
["SLAC_TRAVEL","ESC","SL_OH1",null,null,"2003-10-01","ESC37895",null,null,0,0.2,null,null,0]
["SLAC_TRAVEL","ESC","SL_OH1",null,null,"2004-10-01","ESC38261",null,null,0.029,0.2,null,null,0]
["SLAC_TRAVEL","ESC","SL_OH1",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.2,null,null,0]
["SLAC_TRAVEL","ESC","SL_OH1",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.2,null,null,0]
["SLAC_TRAVEL","ESC","SL_OH1",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.2,null,null,0]
["SLAC_TRAVEL","ESC","SL_OH1",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.2,null,null,0]
["SL_ADMN","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,30.1731,0,0.29,0.215,0.2,56.750169942]
["SL_ADMN","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,30.1731,0.029,0.29,0.215,0.2,58.395924870318]
["SL_ADMN","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,30.1731,0.057812,0.29,0.215,0.2,60.031010766686904]
["SL_ADMN","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,30.1731,0.085315,0.29,0.215,0.2,61.59181069060175]
["SL_ADMN","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,30.1731,0.113533,0.29,0.215,0.2,63.193186986025076]
["SL_ADMN","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,30.1731,0.142485,0.29,0.215,0.2,64.83621790618588]
["SL_ADMN1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,30.1731,0,0.305,0.21,0.38,65.74987030589999]
["SL_ADMN1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,30.1731,0.026,0.305,0.21,0.38,67.4593669338534]
["SL_ADMN1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,30.1731,0.052676,0.305,0.21,0.38,69.21331047413358]
["SL_ADMN1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,30.1731,0.08004558,0.305,0.21,0.38,71.01285680946053]
["SL_ADMN2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,30.1731,0.023,0.305,0.21,0.38,67.2621173229357]
["SL_ADMN2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,30.1731,0.046529,0.305,0.21,0.38,68.80914602136322]
["SL_ADMN2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,30.1731,0.070599,0.305,0.21,0.38,70.39174539962623]
["SL_ADMN2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,30.1731,0.095223,0.305,0.21,0.38,72.01077020603871]
["SL_ADMN2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,30.1731,0.120413,0.305,0.21,0.38,73.66700943904432]
["SL_ADMN2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,30.1731,0.120413,0.305,0.21,0.38,73.66700943904432]
["SL_ADMN2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,30.1731,null,0.305,0.21,0.38,65.74987030589999]
["SL_AW1","ESC1","SL_OHN4",null,null,"2005-10-01","ESC138626",null,1,0,0.0552,null,null,1.0552]
["SL_AW1","ESC1","SL_OHN4",null,null,"2006-10-01","ESC138991",null,1,0.026,0.0552,null,null,1.0826352]
["SL_AW1","ESC1","SL_OHN4",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.0552,null,null,1.1107837151999997]
["SL_AW1","ESC1","SL_OHN4",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.0552,null,null,1.1396640960159998]
["SL_AW2","ESC2","SL_OHN4",null,null,"2006-10-01","ESC238991",null,1,0.023,0.0552,null,null,1.0794696]
["SL_AW2","ESC2","SL_OHN4",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.0552,null,null,1.1042974008]
["SL_AW2","ESC2","SL_OHN4",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.0552,null,null,1.1296960648]
["SL_AW2","ESC2","SL_OHN4",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.0552,null,null,1.1556793096]
["SL_AW2","ESC2","SL_OHN4",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.0552,null,null,1.1822597976]
["SL_AW2","ESC2","SL_OHN4",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.0552,null,null,1.1822597976]
["SL_AW2","ESC2","SL_OHN4",null,null,"2012-10-01","ESC241183",null,1,null,0.0552,null,null,1.0552]
["SL_AWARD","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SL_AWARD","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SL_AWARD","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SL_AWARD","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SL_AWARD","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SL_AWARD","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SL_AWFX","SL_OH2",{"$nulls":4},"SL_OH2",null,1,0.06,null,null,null,1.06]
["SL_AWFX1","SL_OHN4",{"$nulls":4},"SL_OHN4",null,1,0.0552,null,null,null,1.0552]
["SL_AWFX2","SL_OHN4",{"$nulls":4},"SL_OHN4",null,1,0.0552,null,null,null,1.0552]
["SL_AWFY",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_AWFY1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_AWFY2",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_AWGC","ESC_CF","SL_OH2",null,null,"2004-10-01","ESC_CF38261",null,1,0,0.06,null,null,1.06]
["SL_AWGC","ESC_CF","SL_OH2",null,null,"2005-10-01","ESC_CF38626",null,1,0.03,0.06,null,null,1.0918]
["SL_AWGC","ESC_CF","SL_OH2",null,null,"2006-10-01","ESC_CF38991",null,1,0.08,0.06,null,null,1.1448]
["SL_AWGC","ESC_CF","SL_OH2",null,null,"2007-10-01","ESC_CF39356",null,1,0.19,0.06,null,null,1.2614]
["SL_AWGC","ESC_CF","SL_OH2",null,null,"2008-10-01","ESC_CF39722",null,1,0.3,0.06,null,null,1.3780000000000001]
["SL_AWGC","ESC_CF","SL_OH2",null,null,"2009-10-01","ESC_CF40087",null,1,0.41,0.06,null,null,1.4946]
["SL_AWGC1","ESC_CF","SL_OHN4",null,null,"2004-10-01","ESC_CF38261",null,1,0,0.0552,null,null,1.0552]
["SL_AWGC1","ESC_CF","SL_OHN4",null,null,"2005-10-01","ESC_CF38626",null,1,0.03,0.0552,null,null,1.086856]
["SL_AWGC1","ESC_CF","SL_OHN4",null,null,"2006-10-01","ESC_CF38991",null,1,0.08,0.0552,null,null,1.139616]
["SL_AWGC1","ESC_CF","SL_OHN4",null,null,"2007-10-01","ESC_CF39356",null,1,0.19,0.0552,null,null,1.255688]
["SL_AWGC1","ESC_CF","SL_OHN4",null,null,"2008-10-01","ESC_CF39722",null,1,0.3,0.0552,null,null,1.3717599999999999]
["SL_AWGC1","ESC_CF","SL_OHN4",null,null,"2009-10-01","ESC_CF40087",null,1,0.41,0.0552,null,null,1.4878319999999998]
["SL_AWGC2","ESC_CF","SL_OHN4",null,null,"2004-10-01","ESC_CF38261",null,1,0,0.0552,null,null,1.0552]
["SL_AWGC2","ESC_CF","SL_OHN4",null,null,"2005-10-01","ESC_CF38626",null,1,0.03,0.0552,null,null,1.086856]
["SL_AWGC2","ESC_CF","SL_OHN4",null,null,"2006-10-01","ESC_CF38991",null,1,0.08,0.0552,null,null,1.139616]
["SL_AWGC2","ESC_CF","SL_OHN4",null,null,"2007-10-01","ESC_CF39356",null,1,0.19,0.0552,null,null,1.255688]
["SL_AWGC2","ESC_CF","SL_OHN4",null,null,"2008-10-01","ESC_CF39722",null,1,0.3,0.0552,null,null,1.3717599999999999]
["SL_AWGC2","ESC_CF","SL_OHN4",null,null,"2009-10-01","ESC_CF40087",null,1,0.41,0.0552,null,null,1.4878319999999998]
["SL_AWGX","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,1,0,null,null,null,1]
["SL_AWGX","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,1,0.03,null,null,null,1.03]
["SL_AWGX","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,1,0.08,null,null,null,1.08]
["SL_AWGX","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,1,0.19,null,null,null,1.19]
["SL_AWGX","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,1,0.3,null,null,null,1.3]
["SL_AWGX","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,1,0.41,null,null,null,1.41]
["SL_AWGX1","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,1,0,null,null,null,1]
["SL_AWGX1","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,1,0.03,null,null,null,1.03]
["SL_AWGX1","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,1,0.08,null,null,null,1.08]
["SL_AWGX1","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,1,0.19,null,null,null,1.19]
["SL_AWGX1","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,1,0.3,null,null,null,1.3]
["SL_AWGX1","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,1,0.41,null,null,null,1.41]
["SL_AWGX2","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,1,0,null,null,null,1]
["SL_AWGX2","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,1,0.03,null,null,null,1.03]
["SL_AWGX2","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,1,0.08,null,null,null,1.08]
["SL_AWGX2","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,1,0.19,null,null,null,1.19]
["SL_AWGX2","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,1,0.3,null,null,null,1.3]
["SL_AWGX2","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,1,0.41,null,null,null,1.41]
["SL_AWXX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["SL_AWXX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["SL_AWXX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["SL_AWXX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["SL_AWXX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["SL_AWXX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["SL_AWXX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["SL_AWXX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["SL_AWXX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["SL_AWXX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["SL_AWXX2","ESC2",null,null,null,"2006-10-01","ESC238991",null,1,0.023,null,null,null,1.023]
["SL_AWXX2","ESC2",null,null,null,"2007-10-01","ESC239356",null,1,0.046529,null,null,null,1.046529]
["SL_AWXX2","ESC2",null,null,null,"2008-10-01","ESC239722",null,1,0.070599,null,null,null,1.070599]
["SL_AWXX2","ESC2",null,null,null,"2009-10-01","ESC240087",null,1,0.095223,null,null,null,1.095223]
["SL_AWXX2","ESC2",null,null,null,"2010-10-01","ESC240452",null,1,0.120413,null,null,null,1.120413]
["SL_AWXX2","ESC2",null,null,null,"2011-10-01","ESC240817",null,1,0.120413,null,null,null,1.120413]
["SL_AWXX2","ESC2",null,null,null,"2012-10-01","ESC241183",null,1,{"$nulls":4},1]
["SL_CCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,33.86,0,0.29,0.215,0.2,63.6845652]
["SL_CCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,33.86,0.029,0.29,0.215,0.2,65.53141759079999]
["SL_CCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,33.86,0.057812,0.29,0.215,0.2,67.3662972833424]
["SL_CCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,33.86,0.085315,0.29,0.215,0.2,69.117813880038]
["SL_CCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,33.86,0.113533,0.29,0.215,0.2,70.9148649408516]
["SL_CCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,33.86,0.142485,0.29,0.215,0.2,72.75866047252201]
["SL_CCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,33.86,0,0.305,0.21,0.38,73.78395354]
["SL_CCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,33.86,0.026,0.305,0.21,0.38,75.70233633203999]
["SL_CCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,33.86,0.052676,0.305,0.21,0.38,77.67059707667303]
["SL_CCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,33.86,0.08004558,0.305,0.21,0.38,79.69003289580235]
["SL_CCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,33.86,0.023,0.305,0.21,0.38,75.48098447141999]
["SL_CCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,33.86,0.046529,0.305,0.21,0.38,77.21704711426266]
["SL_CCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,33.86,0.070599,0.305,0.21,0.38,78.99302687597046]
["SL_CCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,33.86,0.095223,0.305,0.21,0.38,80.8098829479394]
["SL_CCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,33.86,0.120413,0.305,0.21,0.38,82.668500737612]
["SL_CCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,33.86,0.120413,0.305,0.21,0.38,82.668500737612]
["SL_CCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,33.86,null,0.305,0.21,0.38,73.78395354]
["SL_CE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,58.14,0,0.29,0.215,0.2,109.3508748]
["SL_CE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,58.14,0.029,0.29,0.215,0.2,112.52205016919999]
["SL_CE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,58.14,0.057812,0.29,0.215,0.2,115.6726675739376]
["SL_CE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,58.14,0.085315,0.29,0.215,0.2,118.680144683562]
["SL_CE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,58.14,0.113533,0.29,0.215,0.2,121.7658076686684]
["SL_CE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,58.14,0.142485,0.29,0.215,0.2,124.931734195878]
["SL_CE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,58.14,0,0.305,0.21,0.38,126.69223445999998]
["SL_CE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,58.14,0.026,0.305,0.21,0.38,129.98623255596]
["SL_CE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,58.14,0.052676,0.305,0.21,0.38,133.36587460241495]
["SL_CE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,58.14,0.08004558,0.305,0.21,0.38,136.83338784884668]
["SL_CE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,58.14,0.023,0.305,0.21,0.38,129.60615585257997]
["SL_CE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,58.14,0.046529,0.305,0.21,0.38,132.58709743718933]
["SL_CE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,58.14,0.070599,0.305,0.21,0.38,135.63657952064153]
["SL_CE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,58.14,0.095223,0.305,0.21,0.38,138.75624910198457]
["SL_CE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,58.14,0.120413,0.305,0.21,0.38,141.94762648803197]
["SL_CE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,58.14,0.120413,0.305,0.21,0.38,141.94762648803197]
["SL_CE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,58.14,null,0.305,0.21,0.38,126.69223445999998]
["SL_CP","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,47.01,0,0.29,0.215,0.2,88.41734819999999]
["SL_CP","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,47.01,0.029,0.29,0.215,0.2,90.9814512978]
["SL_CP","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,47.01,0.057812,0.29,0.215,0.2,93.5289319341384]
["SL_CP","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,47.01,0.085315,0.29,0.215,0.2,95.96067426168301]
["SL_CP","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,47.01,0.113533,0.29,0.215,0.2,98.4556349931906]
["SL_CP","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,47.01,0.142485,0.29,0.215,0.2,101.015494058277]
["SL_CP1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,42.39,0,0.305,0.21,0.38,92.37158271]
["SL_CP1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,42.39,0.026,0.305,0.21,0.38,94.77324386046]
["SL_CP1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,42.39,0.052676,0.305,0.21,0.38,97.23734820083196]
["SL_CP1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,42.39,0.08004558,0.305,0.21,0.38,99.76551962353989]
["SL_CP2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,42.39,0.023,0.305,0.21,0.38,94.49612911233]
["SL_CP2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,42.39,0.046529,0.305,0.21,0.38,96.66954008191358]
["SL_CP2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,42.39,0.070599,0.305,0.21,0.38,98.89292407774327]
["SL_CP2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,42.39,0.095223,0.305,0.21,0.38,101.16748193039432]
["SL_CP2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,42.39,0.120413,0.305,0.21,0.38,103.49432209885923]
["SL_CP2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,42.39,0.120413,0.305,0.21,0.38,103.49432209885923]
["SL_CP2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,42.39,null,0.305,0.21,0.38,92.37158271]
["SL_CPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,30.93,0,0.29,0.215,0.2,58.1737626]
["SL_CPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,30.93,0.029,0.29,0.215,0.2,59.860801715399994]
["SL_CPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,30.93,0.057812,0.29,0.215,0.2,61.5369041634312]
["SL_CPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,30.93,0.085315,0.29,0.215,0.2,63.136857156219]
["SL_CPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,30.93,0.113533,0.29,0.215,0.2,64.7784043892658]
["SL_CPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,30.93,0.142485,0.29,0.215,0.2,66.46265116406099]
["SL_CPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,30.93,0,0.305,0.21,0.38,67.39922277]
["SL_CPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,30.93,0.026,0.305,0.21,0.38,69.15160256201999]
["SL_CPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,30.93,0.052676,0.305,0.21,0.38,70.9495442286325]
["SL_CPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,30.93,0.08004558,0.305,0.21,0.38,72.79423264817383]
["SL_CPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,30.93,0.023,0.305,0.21,0.38,68.94940489371]
["SL_CPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,30.93,0.046529,0.305,0.21,0.38,70.53524120626533]
["SL_CPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,30.93,0.070599,0.305,0.21,0.38,72.15754049833922]
["SL_CPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,30.93,0.095223,0.305,0.21,0.38,73.8171789598277]
["SL_CPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,30.93,0.120413,0.305,0.21,0.38,75.51496538140401]
["SL_CPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,30.93,0.120413,0.305,0.21,0.38,75.51496538140401]
["SL_CPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,30.93,null,0.305,0.21,0.38,67.39922277]
["SL_CRA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,24.14,0,0.29,0.215,0.2,45.4029948]
["SL_CRA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,24.14,0.029,0.29,0.215,0.2,46.719681649200005]
["SL_CRA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,24.14,0.057812,0.29,0.215,0.2,48.02783273537761]
["SL_CRA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,24.14,0.085315,0.29,0.215,0.2,49.276551301362005]
["SL_CRA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,24.14,0.113533,0.29,0.215,0.2,50.557733008628404]
["SL_CRA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,24.14,0.142485,0.29,0.215,0.2,51.872240514078]
["SL_CRA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,27.19,0,0.305,0.21,0.38,59.249429909999996]
["SL_CRA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,27.19,0.026,0.305,0.21,0.38,60.789915087659985]
["SL_CRA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,27.19,0.052676,0.305,0.21,0.38,62.37045287993915]
["SL_CRA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,27.19,0.08004558,0.305,0.21,0.38,63.99208489181529]
["SL_CRA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,27.19,0.023,0.305,0.21,0.38,60.612166797929994]
["SL_CRA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,27.19,0.046529,0.305,0.21,0.38,62.006246634282384]
["SL_CRA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,27.19,0.070599,0.305,0.21,0.38,63.432380412216084]
["SL_CRA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,27.19,0.095223,0.305,0.21,0.38,64.89133837431993]
["SL_CRA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,27.19,0.120413,0.305,0.21,0.38,66.38383151375282]
["SL_CRA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,27.19,0.120413,0.305,0.21,0.38,66.38383151375282]
["SL_CRA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,27.19,null,0.305,0.21,0.38,59.249429909999996]
["SL_CRM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,30.93,0,0.29,0.215,0.2,58.1737626]
["SL_CRM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,30.93,0.029,0.29,0.215,0.2,59.860801715399994]
["SL_CRM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,30.93,0.057812,0.29,0.215,0.2,61.5369041634312]
["SL_CRM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,30.93,0.085315,0.29,0.215,0.2,63.136857156219]
["SL_CRM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,30.93,0.113533,0.29,0.215,0.2,64.7784043892658]
["SL_CRM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,30.93,0.142485,0.29,0.215,0.2,66.46265116406099]
["SL_CRM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,30.93,0,0.305,0.21,0.38,67.39922277]
["SL_CRM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,30.93,0.026,0.305,0.21,0.38,69.15160256201999]
["SL_CRM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,30.93,0.052676,0.305,0.21,0.38,70.9495442286325]
["SL_CRM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,30.93,0.08004558,0.305,0.21,0.38,72.79423264817383]
["SL_CRM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,59.74,0.023,0.305,0.21,0.38,133.17288872777996]
["SL_CRM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,59.74,0.046529,0.305,0.21,0.38,136.23586516851893]
["SL_CRM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,59.74,0.070599,0.305,0.21,0.38,139.36926832753912]
["SL_CRM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,59.74,0.095223,0.305,0.21,0.38,142.57479052893976]
["SL_CRM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,59.74,0.120413,0.305,0.21,0.38,145.85399391804316]
["SL_CRM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,59.74,0.120413,0.305,0.21,0.38,145.85399391804316]
["SL_CRM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,59.74,null,0.305,0.21,0.38,130.17877686]
["SL_CT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,31.83,0,0.29,0.215,0.2,59.866500599999995]
["SL_CT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,31.83,0.029,0.29,0.215,0.2,61.60262911739999]
["SL_CT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,31.83,0.057812,0.29,0.215,0.2,63.327502732687186]
["SL_CT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,31.83,0.085315,0.29,0.215,0.2,64.974011098689]
["SL_CT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,31.83,0.113533,0.29,0.215,0.2,66.66332401261978]
["SL_CT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,31.83,0.142485,0.29,0.215,0.2,68.396578937991]
["SL_CT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,31.83,0,0.305,0.21,0.38,69.36040286999999]
["SL_CT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,31.83,0.026,0.305,0.21,0.38,71.16377334461997]
["SL_CT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,31.83,0.052676,0.305,0.21,0.38,73.0140314515801]
["SL_CT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,31.83,0.08004558,0.305,0.21,0.38,74.91239654676279]
["SL_CT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,31.83,0.023,0.305,0.21,0.38,70.95569213600999]
["SL_CT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,31.83,0.046529,0.305,0.21,0.38,72.58767305513823]
["SL_CT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,31.83,0.070599,0.305,0.21,0.38,74.25717795221911]
["SL_CT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,31.83,0.095223,0.305,0.21,0.38,75.96510851249]
["SL_CT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,31.83,0.120413,0.305,0.21,0.38,77.7122970607853]
["SL_CT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,31.83,0.120413,0.305,0.21,0.38,77.7122970607853]
["SL_CT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,31.83,null,0.305,0.21,0.38,69.36040286999999]
["SL_EE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,58.14,0,0.29,0.215,0.2,109.3508748]
["SL_EE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,58.14,0.029,0.29,0.215,0.2,112.52205016919999]
["SL_EE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,58.14,0.057812,0.29,0.215,0.2,115.6726675739376]
["SL_EE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,58.14,0.085315,0.29,0.215,0.2,118.680144683562]
["SL_EE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,58.14,0.113533,0.29,0.215,0.2,121.7658076686684]
["SL_EE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,58.14,0.142485,0.29,0.215,0.2,124.931734195878]
["SL_EE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,47.95,0,0.305,0.21,0.38,104.48731754999999]
["SL_EE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,47.95,0.026,0.305,0.21,0.38,107.2039878063]
["SL_EE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,47.95,0.052676,0.305,0.21,0.38,109.99129148926377]
["SL_EE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,47.95,0.08004558,0.305,0.21,0.38,112.85106548593392]
["SL_EE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,47.95,0.023,0.305,0.21,0.38,106.89052585364999]
["SL_EE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,47.95,0.046529,0.305,0.21,0.38,109.34900794828395]
["SL_EE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,47.95,0.070599,0.305,0.21,0.38,111.86401768171244]
["SL_EE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,47.95,0.095223,0.305,0.21,0.38,114.43691338906366]
["SL_EE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,47.95,0.120413,0.305,0.21,0.38,117.06894891814817]
["SL_EE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,47.95,0.120413,0.305,0.21,0.38,117.06894891814817]
["SL_EE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,47.95,null,0.305,0.21,0.38,104.48731754999999]
["SL_ESH2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,65.71,0.023,0.305,0.21,0.38,146.48126076836996]
["SL_ESH2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,65.71,0.046529,0.305,0.21,0.38,149.8503297660425]
["SL_ESH2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,65.71,0.070599,0.305,0.21,0.38,153.29686343827575]
["SL_ESH2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,65.71,0.095223,0.305,0.21,0.38,156.82272322826634]
["SL_ESH2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,65.71,0.120413,0.305,0.21,0.38,160.42962739127245]
["SL_ESH2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,65.71,0.120413,0.305,0.21,0.38,160.42962739127245]
["SL_ESH2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,65.71,null,0.305,0.21,0.38,143.18793818999998]
["SL_FA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,40.7,0,0.29,0.215,0.2,76.54937400000001]
["SL_FA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,40.7,0.029,0.29,0.215,0.2,78.769305846]
["SL_FA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,40.7,0.057812,0.29,0.215,0.2,80.97484640968801]
["SL_FA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,40.7,0.085315,0.29,0.215,0.2,83.08018384281002]
["SL_FA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,40.7,0.113533,0.29,0.215,0.2,85.24025407834199]
["SL_FA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,40.7,0.142485,0.29,0.215,0.2,87.45651155439002]
["SL_FA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,46.24,0,0.305,0.21,0.38,100.76107535999999]
["SL_FA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,46.24,0.026,0.305,0.21,0.38,103.38086331936]
["SL_FA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,46.24,0.052676,0.305,0.21,0.38,106.06876576566334]
["SL_FA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,46.24,0.08004558,0.305,0.21,0.38,108.82655407861489]
["SL_FA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,46.24,0.023,0.305,0.21,0.38,103.07858009327997]
["SL_FA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,46.24,0.046529,0.305,0.21,0.38,105.44938743542542]
["SL_FA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,46.24,0.070599,0.305,0.21,0.38,107.87470651934063]
["SL_FA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,46.24,0.095223,0.305,0.21,0.38,110.35584723900526]
["SL_FA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,46.24,0.120413,0.305,0.21,0.38,112.89401872732368]
["SL_FA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,46.24,0.120413,0.305,0.21,0.38,112.89401872732368]
["SL_FA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,46.24,null,0.305,0.21,0.38,100.76107535999999]
["SL_GCAW","ESC_CF","SL_OH2",null,null,"2004-10-01","ESC_CF38261",null,null,0,0.06,null,null,0]
["SL_GCAW","ESC_CF","SL_OH2",null,null,"2005-10-01","ESC_CF38626",null,null,0.03,0.06,null,null,0]
["SL_GCAW","ESC_CF","SL_OH2",null,null,"2006-10-01","ESC_CF38991",null,null,0.08,0.06,null,null,0]
["SL_GCAW","ESC_CF","SL_OH2",null,null,"2007-10-01","ESC_CF39356",null,null,0.19,0.06,null,null,0]
["SL_GCAW","ESC_CF","SL_OH2",null,null,"2008-10-01","ESC_CF39722",null,null,0.3,0.06,null,null,0]
["SL_GCAW","ESC_CF","SL_OH2",null,null,"2009-10-01","ESC_CF40087",null,null,0.41,0.06,null,null,0]
["SL_GCAW1","ESC_CF","SL_OHN4",null,null,"2004-10-01","ESC_CF38261",null,null,0,0.0552,null,null,0]
["SL_GCAW1","ESC_CF","SL_OHN4",null,null,"2005-10-01","ESC_CF38626",null,null,0.03,0.0552,null,null,0]
["SL_GCAW1","ESC_CF","SL_OHN4",null,null,"2006-10-01","ESC_CF38991",null,null,0.08,0.0552,null,null,0]
["SL_GCAW1","ESC_CF","SL_OHN4",null,null,"2007-10-01","ESC_CF39356",null,null,0.19,0.0552,null,null,0]
["SL_GCAW1","ESC_CF","SL_OHN4",null,null,"2008-10-01","ESC_CF39722",null,null,0.3,0.0552,null,null,0]
["SL_GCAW1","ESC_CF","SL_OHN4",null,null,"2009-10-01","ESC_CF40087",null,null,0.41,0.0552,null,null,0]
["SL_GCAW2","ESC_CF","SL_OHN4",null,null,"2004-10-01","ESC_CF38261",null,null,0,0.0552,null,null,0]
["SL_GCAW2","ESC_CF","SL_OHN4",null,null,"2005-10-01","ESC_CF38626",null,null,0.03,0.0552,null,null,0]
["SL_GCAW2","ESC_CF","SL_OHN4",null,null,"2006-10-01","ESC_CF38991",null,null,0.08,0.0552,null,null,0]
["SL_GCAW2","ESC_CF","SL_OHN4",null,null,"2007-10-01","ESC_CF39356",null,null,0.19,0.0552,null,null,0]
["SL_GCAW2","ESC_CF","SL_OHN4",null,null,"2008-10-01","ESC_CF39722",null,null,0.3,0.0552,null,null,0]
["SL_GCAW2","ESC_CF","SL_OHN4",null,null,"2009-10-01","ESC_CF40087",null,null,0.41,0.0552,null,null,0]
["SL_GCAX","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,null,0,null,null,null,0]
["SL_GCAX","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,null,0.03,null,null,null,0]
["SL_GCAX","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,null,0.08,null,null,null,0]
["SL_GCAX","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,null,0.19,null,null,null,0]
["SL_GCAX","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,null,0.3,null,null,null,0]
["SL_GCAX","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,null,0.41,null,null,null,0]
["SL_GCAX1","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,null,0,null,null,null,0]
["SL_GCAX1","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,null,0.03,null,null,null,0]
["SL_GCAX1","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,null,0.08,null,null,null,0]
["SL_GCAX1","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,null,0.19,null,null,null,0]
["SL_GCAX1","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,null,0.3,null,null,null,0]
["SL_GCAX1","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,null,0.41,null,null,null,0]
["SL_GCAX2","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,null,0,null,null,null,0]
["SL_GCAX2","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,null,0.03,null,null,null,0]
["SL_GCAX2","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,null,0.08,null,null,null,0]
["SL_GCAX2","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,null,0.19,null,null,null,0]
["SL_GCAX2","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,null,0.3,null,null,null,0]
["SL_GCAX2","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,null,0.41,null,null,null,0]
["SL_GCFX1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_GCFX2",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_GCSS","ESC_CF","SL_OH2",null,null,"2004-10-01","ESC_CF38261",null,1,0,0.06,null,null,1.06]
["SL_GCSS","ESC_CF","SL_OH2",null,null,"2005-10-01","ESC_CF38626",null,1,0.03,0.06,null,null,1.0918]
["SL_GCSS","ESC_CF","SL_OH2",null,null,"2006-10-01","ESC_CF38991",null,1,0.08,0.06,null,null,1.1448]
["SL_GCSS","ESC_CF","SL_OH2",null,null,"2007-10-01","ESC_CF39356",null,1,0.19,0.06,null,null,1.2614]
["SL_GCSS","ESC_CF","SL_OH2",null,null,"2008-10-01","ESC_CF39722",null,1,0.3,0.06,null,null,1.3780000000000001]
["SL_GCSS","ESC_CF","SL_OH2",null,null,"2009-10-01","ESC_CF40087",null,1,0.41,0.06,null,null,1.4946]
["SL_GCSS1","ESC_CF","SL_OHN4",null,null,"2004-10-01","ESC_CF38261",null,1,0,0.0552,null,null,1.0552]
["SL_GCSS1","ESC_CF","SL_OHN4",null,null,"2005-10-01","ESC_CF38626",null,1,0.03,0.0552,null,null,1.086856]
["SL_GCSS1","ESC_CF","SL_OHN4",null,null,"2006-10-01","ESC_CF38991",null,1,0.08,0.0552,null,null,1.139616]
["SL_GCSS1","ESC_CF","SL_OHN4",null,null,"2007-10-01","ESC_CF39356",null,1,0.19,0.0552,null,null,1.255688]
["SL_GCSS1","ESC_CF","SL_OHN4",null,null,"2008-10-01","ESC_CF39722",null,1,0.3,0.0552,null,null,1.3717599999999999]
["SL_GCSS1","ESC_CF","SL_OHN4",null,null,"2009-10-01","ESC_CF40087",null,1,0.41,0.0552,null,null,1.4878319999999998]
["SL_GCSS2","ESC_CF","SL_OHN4",null,null,"2004-10-01","ESC_CF38261",null,1,0,0.0552,null,null,1.0552]
["SL_GCSS2","ESC_CF","SL_OHN4",null,null,"2005-10-01","ESC_CF38626",null,1,0.03,0.0552,null,null,1.086856]
["SL_GCSS2","ESC_CF","SL_OHN4",null,null,"2006-10-01","ESC_CF38991",null,1,0.08,0.0552,null,null,1.139616]
["SL_GCSS2","ESC_CF","SL_OHN4",null,null,"2007-10-01","ESC_CF39356",null,1,0.19,0.0552,null,null,1.255688]
["SL_GCSS2","ESC_CF","SL_OHN4",null,null,"2008-10-01","ESC_CF39722",null,1,0.3,0.0552,null,null,1.3717599999999999]
["SL_GCSS2","ESC_CF","SL_OHN4",null,null,"2009-10-01","ESC_CF40087",null,1,0.41,0.0552,null,null,1.4878319999999998]
["SL_GCSX","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,1,0,null,null,null,1]
["SL_GCSX","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,1,0.03,null,null,null,1.03]
["SL_GCSX","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,1,0.08,null,null,null,1.08]
["SL_GCSX","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,1,0.19,null,null,null,1.19]
["SL_GCSX","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,1,0.3,null,null,null,1.3]
["SL_GCSX","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,1,0.41,null,null,null,1.41]
["SL_GCSX1","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,1,0,null,null,null,1]
["SL_GCSX1","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,1,0.03,null,null,null,1.03]
["SL_GCSX1","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,1,0.08,null,null,null,1.08]
["SL_GCSX1","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,1,0.19,null,null,null,1.19]
["SL_GCSX1","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,1,0.3,null,null,null,1.3]
["SL_GCSX1","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,1,0.41,null,null,null,1.41]
["SL_GCSX2","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,1,0,null,null,null,1]
["SL_GCSX2","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,1,0.03,null,null,null,1.03]
["SL_GCSX2","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,1,0.08,null,null,null,1.08]
["SL_GCSX2","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,1,0.19,null,null,null,1.19]
["SL_GCSX2","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,1,0.3,null,null,null,1.3]
["SL_GCSX2","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,1,0.41,null,null,null,1.41]
["SL_IPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_IPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_IPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_IPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_IPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_IPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_IPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,54.62,0,0.305,0.21,0.38,119.02184117999998]
["SL_IPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,54.62,0.026,0.305,0.21,0.38,122.11640905067998]
["SL_IPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,54.62,0.052676,0.305,0.21,0.38,125.29143568599764]
["SL_IPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,54.62,0.08004558,0.305,0.21,0.38,128.54901348992095]
["SL_IPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,54.62,0.023,0.305,0.21,0.38,121.75934352713996]
["SL_IPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,54.62,0.046529,0.305,0.21,0.38,124.5598084282642]
["SL_IPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,54.62,0.070599,0.305,0.21,0.38,127.42466414546679]
["SL_IPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,54.62,0.095223,0.305,0.21,0.38,130.35545796268312]
["SL_IPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,54.62,0.120413,0.305,0.21,0.38,133.35361814200732]
["SL_IPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,54.62,0.120413,0.305,0.21,0.38,133.35361814200732]
["SL_IPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,54.62,null,0.305,0.21,0.38,119.02184117999998]
["SL_KCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,33.86,0,0.29,0.215,0.2,63.6845652]
["SL_KCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,33.86,0.029,0.29,0.215,0.2,65.53141759079999]
["SL_KCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,33.86,0.057812,0.29,0.215,0.2,67.3662972833424]
["SL_KCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,33.86,0.085315,0.29,0.215,0.2,69.117813880038]
["SL_KCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,33.86,0.113533,0.29,0.215,0.2,70.9148649408516]
["SL_KCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,33.86,0.142485,0.29,0.215,0.2,72.75866047252201]
["SL_KCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,33.86,0,0.305,0.21,0.38,73.78395354]
["SL_KCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,33.86,0.026,0.305,0.21,0.38,75.70233633203999]
["SL_KCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,33.86,0.052676,0.305,0.21,0.38,77.67059707667303]
["SL_KCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,33.86,0.08004558,0.305,0.21,0.38,79.69003289580235]
["SL_KCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,33.86,0.023,0.305,0.21,0.38,75.48098447141999]
["SL_KCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,33.86,0.046529,0.305,0.21,0.38,77.21704711426266]
["SL_KCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,33.86,0.070599,0.305,0.21,0.38,78.99302687597046]
["SL_KCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,33.86,0.095223,0.305,0.21,0.38,80.8098829479394]
["SL_KCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,33.86,0.120413,0.305,0.21,0.38,82.668500737612]
["SL_KCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,33.86,0.120413,0.305,0.21,0.38,82.668500737612]
["SL_KCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,33.86,null,0.305,0.21,0.38,73.78395354]
["SL_KE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,58.14,0,0.29,0.215,0.2,109.3508748]
["SL_KE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,58.14,0.029,0.29,0.215,0.2,112.52205016919999]
["SL_KE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,58.14,0.057812,0.29,0.215,0.2,115.6726675739376]
["SL_KE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,58.14,0.085315,0.29,0.215,0.2,118.680144683562]
["SL_KE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,58.14,0.113533,0.29,0.215,0.2,121.7658076686684]
["SL_KE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,58.14,0.142485,0.29,0.215,0.2,124.931734195878]
["SL_KE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,58.14,0,0.305,0.21,0.38,126.69223445999998]
["SL_KE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,58.14,0.026,0.305,0.21,0.38,129.98623255596]
["SL_KE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,58.14,0.052676,0.305,0.21,0.38,133.36587460241495]
["SL_KE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,58.14,0.08004558,0.305,0.21,0.38,136.83338784884668]
["SL_KE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,58.14,0.023,0.305,0.21,0.38,129.60615585257997]
["SL_KE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,58.14,0.046529,0.305,0.21,0.38,132.58709743718933]
["SL_KE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,58.14,0.070599,0.305,0.21,0.38,135.63657952064153]
["SL_KE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,58.14,0.095223,0.305,0.21,0.38,138.75624910198457]
["SL_KE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,58.14,0.120413,0.305,0.21,0.38,141.94762648803197]
["SL_KE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,58.14,0.120413,0.305,0.21,0.38,141.94762648803197]
["SL_KE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,58.14,null,0.305,0.21,0.38,126.69223445999998]
["SL_KT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,31.83,0,0.29,0.215,0.2,59.866500599999995]
["SL_KT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,31.83,0.029,0.29,0.215,0.2,61.60262911739999]
["SL_KT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,31.83,0.057812,0.29,0.215,0.2,63.327502732687186]
["SL_KT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,31.83,0.085315,0.29,0.215,0.2,64.974011098689]
["SL_KT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,31.83,0.113533,0.29,0.215,0.2,66.66332401261978]
["SL_KT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,31.83,0.142485,0.29,0.215,0.2,68.396578937991]
["SL_KT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,31.83,0,0.305,0.21,0.38,69.36040286999999]
["SL_KT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,31.83,0.026,0.305,0.21,0.38,71.16377334461997]
["SL_KT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,31.83,0.052676,0.305,0.21,0.38,73.0140314515801]
["SL_KT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,31.83,0.08004558,0.305,0.21,0.38,74.91239654676279]
["SL_KT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,31.83,0.023,0.305,0.21,0.38,70.95569213600999]
["SL_KT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,31.83,0.046529,0.305,0.21,0.38,72.58767305513823]
["SL_KT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,31.83,0.070599,0.305,0.21,0.38,74.25717795221911]
["SL_KT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,31.83,0.095223,0.305,0.21,0.38,75.96510851249]
["SL_KT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,31.83,0.120413,0.305,0.21,0.38,77.7122970607853]
["SL_KT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,31.83,0.120413,0.305,0.21,0.38,77.7122970607853]
["SL_KT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,31.83,null,0.305,0.21,0.38,69.36040286999999]
["SL_LPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_LPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_LPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_LPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_LPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_LPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_LPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,54.62,0,0.305,0.21,0.38,119.02184117999998]
["SL_LPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,54.62,0.026,0.305,0.21,0.38,122.11640905067998]
["SL_LPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,54.62,0.052676,0.305,0.21,0.38,125.29143568599764]
["SL_LPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,54.62,0.08004558,0.305,0.21,0.38,128.54901348992095]
["SL_LPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,54.62,0.023,0.305,0.21,0.38,121.75934352713996]
["SL_LPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,54.62,0.046529,0.305,0.21,0.38,124.5598084282642]
["SL_LPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,54.62,0.070599,0.305,0.21,0.38,127.42466414546679]
["SL_LPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,54.62,0.095223,0.305,0.21,0.38,130.35545796268312]
["SL_LPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,54.62,0.120413,0.305,0.21,0.38,133.35361814200732]
["SL_LPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,54.62,0.120413,0.305,0.21,0.38,133.35361814200732]
["SL_LPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,54.62,null,0.305,0.21,0.38,119.02184117999998]
["SL_MDD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,32.42,0,0.29,0.215,0.2,60.97618440000001]
["SL_MDD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,32.42,0.029,0.29,0.215,0.2,62.7444937476]
["SL_MDD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,32.42,0.057812,0.29,0.215,0.2,64.5013395725328]
["SL_MDD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,32.42,0.085315,0.29,0.215,0.2,66.17836757208602]
["SL_MDD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,32.42,0.113533,0.29,0.215,0.2,67.8989935434852]
["SL_MDD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,32.42,0.142485,0.29,0.215,0.2,69.66437603423401]
["SL_MDD1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,43.07,0,0.305,0.21,0.38,93.85336322999999]
["SL_MDD1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,43.07,0.026,0.305,0.21,0.38,96.29355067398]
["SL_MDD1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,43.07,0.052676,0.305,0.21,0.38,98.79718299150346]
["SL_MDD1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,43.07,0.08004558,0.305,0.21,0.38,101.36591012469599]
["SL_MDD2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,43.07,0.023,0.305,0.21,0.38,96.01199058428998]
["SL_MDD2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,43.07,0.046529,0.305,0.21,0.38,98.22026636772867]
["SL_MDD2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,43.07,0.070599,0.305,0.21,0.38,100.47931682067475]
["SL_MDD2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,43.07,0.095223,0.305,0.21,0.38,102.79036203685028]
["SL_MDD2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,43.07,0.120413,0.305,0.21,0.38,105.15452825661399]
["SL_MDD2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,43.07,0.120413,0.305,0.21,0.38,105.15452825661399]
["SL_MDD2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,43.07,null,0.305,0.21,0.38,93.85336322999999]
["SL_ME","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_ME","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_ME","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_ME","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_ME","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_ME","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_ME1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,51.37,0,0.305,0.21,0.38,111.93980192999997]
["SL_ME1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,51.37,0.026,0.305,0.21,0.38,114.85023678017998]
["SL_ME1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,51.37,0.052676,0.305,0.21,0.38,117.83634293646463]
["SL_ME1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,51.37,0.08004558,0.305,0.21,0.38,120.90008830057195]
["SL_ME2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,51.37,0.023,0.305,0.21,0.38,114.51441737438996]
["SL_ME2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,51.37,0.046529,0.305,0.21,0.38,117.14824897400095]
["SL_ME2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,51.37,0.070599,0.305,0.21,0.38,119.84264000645607]
["SL_ME2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,51.37,0.095223,0.305,0.21,0.38,122.59904568918037]
["SL_ME2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,51.37,0.120413,0.305,0.21,0.38,125.41880929979706]
["SL_ME2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,51.37,0.120413,0.305,0.21,0.38,125.41880929979706]
["SL_ME2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,51.37,null,0.305,0.21,0.38,111.93980192999997]
["SL_MES","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,46.68,0,0.29,0.215,0.2,87.7966776]
["SL_MES","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,46.68,0.029,0.29,0.215,0.2,90.3427812504]
["SL_MES","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,46.68,0.057812,0.29,0.215,0.2,92.8723791254112]
["SL_MES","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,46.68,0.085315,0.29,0.215,0.2,95.28705114944401]
["SL_MES","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,46.68,0.113533,0.29,0.215,0.2,97.76449779796079]
["SL_MES","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,46.68,0.142485,0.29,0.215,0.2,100.306387207836]
["SL_MES1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,41.3,0,0.305,0.21,0.38,89.99637569999999]
["SL_MES1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,41.3,0.026,0.305,0.21,0.38,92.33628146819999]
["SL_MES1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,41.3,0.052676,0.305,0.21,0.38,94.73702478637318]
["SL_MES1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,41.3,0.08004558,0.305,0.21,0.38,97.20018779080438]
["SL_MES2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,41.3,0.023,0.305,0.21,0.38,92.06629234109998]
["SL_MES2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,41.3,0.046529,0.305,0.21,0.38,94.18381706494529]
["SL_MES2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,41.3,0.070599,0.305,0.21,0.38,96.35002982804428]
["SL_MES2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,41.3,0.095223,0.305,0.21,0.38,98.56610058328107]
["SL_MES2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,41.3,0.120413,0.305,0.21,0.38,100.83310928716409]
["SL_MES2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,41.3,0.120413,0.305,0.21,0.38,100.83310928716409]
["SL_MES2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,41.3,null,0.305,0.21,0.38,89.99637569999999]
["SL_MFAT","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2003-10-01","ESC37895",null,66.3,0,0,0,0.2,79.55999999999999]
["SL_MFAT","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2004-10-01","ESC38261",null,66.3,0.029,0,0,0.2,81.86723999999998]
["SL_MFAT","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2005-10-01","ESC38626",null,66.3,0.057812,0,0,0.2,84.15952272]
["SL_MFAT","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2006-10-01","ESC38991",null,66.3,0.085315,0,0,0.2,86.34766139999999]
["SL_MFAT","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2007-10-01","ESC39356",null,66.3,0.113533,0,0,0.2,88.59268547999999]
["SL_MFAT","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2008-10-01","ESC39722",null,66.3,0.142485,0,0,0.2,90.89610659999998]
["SL_MFAT1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN3","2005-10-01","ESC138626",null,70,0,0,0,0.38,96.6]
["SL_MFAT1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN3","2006-10-01","ESC138991",null,70,0.026,0,0,0.38,99.1116]
["SL_MFAT1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN3","2007-10-01","ESC139356",null,70,0.052676,0,0,0.38,101.6885016]
["SL_MFAT1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN3","2008-10-01","ESC139722",null,70,0.08004558,0,0,0.38,104.33240302799997]
["SL_MFAT2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN3","2006-10-01","ESC238991",null,70,0.023,0,0,0.38,98.8218]
["SL_MFAT2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN3","2007-10-01","ESC239356",null,70,0.046529,0,0,0.38,101.09470139999999]
["SL_MFAT2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN3","2008-10-01","ESC239722",null,70,0.070599,0,0,0.38,103.4198634]
["SL_MFAT2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN3","2009-10-01","ESC240087",null,70,0.095223,0,0,0.38,105.7985418]
["SL_MFAT2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN3","2010-10-01","ESC240452",null,70,0.120413,0,0,0.38,108.23189579999999]
["SL_MFAT2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN3","2011-10-01","ESC240817",null,70,0.120413,0,0,0.38,108.23189579999999]
["SL_MFAT2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN3","2012-10-01","ESC241183",null,70,null,0,0,0.38,96.6]
["SL_MFMS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2003-10-01","ESC37895",null,81.3,0,0,0,0.2,97.55999999999999]
["SL_MFMS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2004-10-01","ESC38261",null,81.3,0.029,0,0,0.2,100.38923999999999]
["SL_MFMS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2005-10-01","ESC38626",null,81.3,0.057812,0,0,0.2,103.20013872]
["SL_MFMS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2006-10-01","ESC38991",null,81.3,0.085315,0,0,0.2,105.88333139999999]
["SL_MFMS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2007-10-01","ESC39356",null,81.3,0.113533,0,0,0.2,108.63627947999998]
["SL_MFMS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2008-10-01","ESC39722",null,81.3,0.142485,0,0,0.2,111.4608366]
["SL_MFMS1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN3","2005-10-01","ESC138626",null,89.59,0,0,0,0.38,123.63419999999999]
["SL_MFMS1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN3","2006-10-01","ESC138991",null,89.59,0.026,0,0,0.38,126.8486892]
["SL_MFMS1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN3","2007-10-01","ESC139356",null,89.59,0.052676,0,0,0.38,130.14675511919998]
["SL_MFMS1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN3","2008-10-01","ESC139722",null,89.59,0.08004558,0,0,0.38,133.530571246836]
["SL_MFMS2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN3","2006-10-01","ESC238991",null,89.59,0.023,0,0,0.38,126.47778659999999]
["SL_MFMS2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN3","2007-10-01","ESC239356",null,89.59,0.046529,0,0,0.38,129.38677569179998]
["SL_MFMS2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN3","2008-10-01","ESC239722",null,89.59,0.070599,0,0,0.38,132.3626508858]
["SL_MFMS2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN3","2009-10-01","ESC240087",null,89.59,0.095223,0,0,0.38,135.4070194266]
["SL_MFMS2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN3","2010-10-01","ESC240452",null,89.59,0.120413,0,0,0.38,138.52136492460002]
["SL_MFMS2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN3","2011-10-01","ESC240817",null,89.59,0.120413,0,0,0.38,138.52136492460002]
["SL_MFMS2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN3","2012-10-01","ESC241183",null,89.59,null,0,0,0.38,123.63419999999999]
["SL_MFPC","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2003-10-01","ESC37895",null,129.8,0,0,0,0.2,155.76000000000002]
["SL_MFPC","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2004-10-01","ESC38261",null,129.8,0.029,0,0,0.2,160.27704]
["SL_MFPC","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2005-10-01","ESC38626",null,129.8,0.057812,0,0,0.2,164.76479712]
["SL_MFPC","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2006-10-01","ESC38991",null,129.8,0.085315,0,0,0.2,169.04866440000004]
["SL_MFPC","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2007-10-01","ESC39356",null,129.8,0.113533,0,0,0.2,173.44390007999996]
["SL_MFPC","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2008-10-01","ESC39722",null,129.8,0.142485,0,0,0.2,177.9534636]
["SL_MFPC1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN3","2005-10-01","ESC138626",null,140.65,0,0,0,0.38,194.09699999999998]
["SL_MFPC1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN3","2006-10-01","ESC138991",null,140.65,0.026,0,0,0.38,199.143522]
["SL_MFPC1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN3","2007-10-01","ESC139356",null,140.65,0.052676,0,0,0.38,204.321253572]
["SL_MFPC1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN3","2008-10-01","ESC139722",null,140.65,0.08004558,0,0,0.38,209.63360694126]
["SL_MFPC2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN3","2006-10-01","ESC238991",null,140.65,0.023,0,0,0.38,198.561231]
["SL_MFPC2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN3","2007-10-01","ESC239356",null,140.65,0.046529,0,0,0.38,203.128139313]
["SL_MFPC2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN3","2008-10-01","ESC239722",null,140.65,0.070599,0,0,0.38,207.800054103]
["SL_MFPC2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN3","2009-10-01","ESC240087",null,140.65,0.095223,0,0,0.38,212.579498631]
["SL_MFPC2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN3","2010-10-01","ESC240452",null,140.65,0.120413,0,0,0.38,217.46880206100002]
["SL_MFPC2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN3","2011-10-01","ESC240817",null,140.65,0.120413,0,0,0.38,217.46880206100002]
["SL_MFPC2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN3","2012-10-01","ESC241183",null,140.65,null,0,0,0.38,194.09699999999998]
["SL_MSCS","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SL_MSCS","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SL_MSCS","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SL_MSCS","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SL_MSCS","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SL_MSCS","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SL_MSCS1","ESC1","SL_OHN4",null,null,"2005-10-01","ESC138626",null,1,0,0.0552,null,null,1.0552]
["SL_MSCS1","ESC1","SL_OHN4",null,null,"2006-10-01","ESC138991",null,1,0.026,0.0552,null,null,1.0826352]
["SL_MSCS1","ESC1","SL_OHN4",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.0552,null,null,1.1107837151999997]
["SL_MSCS1","ESC1","SL_OHN4",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.0552,null,null,1.1396640960159998]
["SL_MSCS2","ESC2","SL_OHN4",null,null,"2006-10-01","ESC238991",null,1,0.023,0.0552,null,null,1.0794696]
["SL_MSCS2","ESC2","SL_OHN4",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.0552,null,null,1.1042974008]
["SL_MSCS2","ESC2","SL_OHN4",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.0552,null,null,1.1296960648]
["SL_MSCS2","ESC2","SL_OHN4",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.0552,null,null,1.1556793096]
["SL_MSCS2","ESC2","SL_OHN4",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.0552,null,null,1.1822597976]
["SL_MSCS2","ESC2","SL_OHN4",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.0552,null,null,1.1822597976]
["SL_MSCS2","ESC2","SL_OHN4",null,null,"2012-10-01","ESC241183",null,1,null,0.0552,null,null,1.0552]
["SL_MSEG","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SL_MSEG","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SL_MSEG","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SL_MSEG","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SL_MSEG","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SL_MSEG","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SL_MSEG1","ESC1","SL_OHN4",null,null,"2005-10-01","ESC138626",null,1,0,0.0552,null,null,1.0552]
["SL_MSEG1","ESC1","SL_OHN4",null,null,"2006-10-01","ESC138991",null,1,0.026,0.0552,null,null,1.0826352]
["SL_MSEG1","ESC1","SL_OHN4",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.0552,null,null,1.1107837151999997]
["SL_MSEG1","ESC1","SL_OHN4",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.0552,null,null,1.1396640960159998]
["SL_MSEG2","ESC2","SL_OHN4",null,null,"2006-10-01","ESC238991",null,1,0.023,0.0552,null,null,1.0794696]
["SL_MSEG2","ESC2","SL_OHN4",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.0552,null,null,1.1042974008]
["SL_MSEG2","ESC2","SL_OHN4",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.0552,null,null,1.1296960648]
["SL_MSEG2","ESC2","SL_OHN4",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.0552,null,null,1.1556793096]
["SL_MSEG2","ESC2","SL_OHN4",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.0552,null,null,1.1822597976]
["SL_MSEG2","ESC2","SL_OHN4",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.0552,null,null,1.1822597976]
["SL_MSEG2","ESC2","SL_OHN4",null,null,"2012-10-01","ESC241183",null,1,null,0.0552,null,null,1.0552]
["SL_MSEQ","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SL_MSEQ","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SL_MSEQ","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SL_MSEQ","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SL_MSEQ","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SL_MSEQ","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SL_MSEQ1","ESC1","SL_OHN4",null,null,"2005-10-01","ESC138626",null,1,0,0.0552,null,null,1.0552]
["SL_MSEQ1","ESC1","SL_OHN4",null,null,"2006-10-01","ESC138991",null,1,0.026,0.0552,null,null,1.0826352]
["SL_MSEQ1","ESC1","SL_OHN4",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.0552,null,null,1.1107837151999997]
["SL_MSEQ1","ESC1","SL_OHN4",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.0552,null,null,1.1396640960159998]
["SL_MSEQ2","ESC2","SL_OHN4",null,null,"2006-10-01","ESC238991",null,1,0.023,0.0552,null,null,1.0794696]
["SL_MSEQ2","ESC2","SL_OHN4",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.0552,null,null,1.1042974008]
["SL_MSEQ2","ESC2","SL_OHN4",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.0552,null,null,1.1296960648]
["SL_MSEQ2","ESC2","SL_OHN4",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.0552,null,null,1.1556793096]
["SL_MSEQ2","ESC2","SL_OHN4",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.0552,null,null,1.1822597976]
["SL_MSEQ2","ESC2","SL_OHN4",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.0552,null,null,1.1822597976]
["SL_MSEQ2","ESC2","SL_OHN4",null,null,"2012-10-01","ESC241183",null,1,null,0.0552,null,null,1.0552]
["SL_MSPF","SL_OH2",{"$nulls":4},"SL_OH2",null,1,0.06,null,null,null,1.06]
["SL_MSPF1","SL_OHN4",{"$nulls":4},"SL_OHN4",null,1,0.0552,null,null,null,1.0552]
["SL_MSPF2","SL_OHN4",{"$nulls":4},"SL_OHN4",null,1,0.0552,null,null,null,1.0552]
["SL_MSPS","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SL_MSPS","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SL_MSPS","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SL_MSPS","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SL_MSPS","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SL_MSPS","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SL_MSPS1","ESC1","SL_OHN4",null,null,"2005-10-01","ESC138626",null,1,0,0.0552,null,null,1.0552]
["SL_MSPS1","ESC1","SL_OHN4",null,null,"2006-10-01","ESC138991",null,1,0.026,0.0552,null,null,1.0826352]
["SL_MSPS1","ESC1","SL_OHN4",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.0552,null,null,1.1107837151999997]
["SL_MSPS1","ESC1","SL_OHN4",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.0552,null,null,1.1396640960159998]
["SL_MSPS2","ESC2","SL_OHN4",null,null,"2006-10-01","ESC238991",null,1,0.023,0.0552,null,null,1.0794696]
["SL_MSPS2","ESC2","SL_OHN4",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.0552,null,null,1.1042974008]
["SL_MSPS2","ESC2","SL_OHN4",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.0552,null,null,1.1296960648]
["SL_MSPS2","ESC2","SL_OHN4",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.0552,null,null,1.1556793096]
["SL_MSPS2","ESC2","SL_OHN4",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.0552,null,null,1.1822597976]
["SL_MSPS2","ESC2","SL_OHN4",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.0552,null,null,1.1822597976]
["SL_MSPS2","ESC2","SL_OHN4",null,null,"2012-10-01","ESC241183",null,1,null,0.0552,null,null,1.0552]
["SL_MSPX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["SL_MSPX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["SL_MSPX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["SL_MSPX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["SL_MSPX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["SL_MSPX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["SL_MSPX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["SL_MSPX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["SL_MSPX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["SL_MSPX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["SL_MSPX2","ESC2",null,null,null,"2006-10-01","ESC238991",null,1,0.023,null,null,null,1.023]
["SL_MSPX2","ESC2",null,null,null,"2007-10-01","ESC239356",null,1,0.046529,null,null,null,1.046529]
["SL_MSPX2","ESC2",null,null,null,"2008-10-01","ESC239722",null,1,0.070599,null,null,null,1.070599]
["SL_MSPX2","ESC2",null,null,null,"2009-10-01","ESC240087",null,1,0.095223,null,null,null,1.095223]
["SL_MSPX2","ESC2",null,null,null,"2010-10-01","ESC240452",null,1,0.120413,null,null,null,1.120413]
["SL_MSPX2","ESC2",null,null,null,"2011-10-01","ESC240817",null,1,0.120413,null,null,null,1.120413]
["SL_MSPX2","ESC2",null,null,null,"2012-10-01","ESC241183",null,1,{"$nulls":4},1]
["SL_MSPY",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_MSPY1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_MSPY2",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_MSSC","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SL_MSSC","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SL_MSSC","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SL_MSSC","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SL_MSSC","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SL_MSSC","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SL_MSSC1","ESC1","SL_OHN4",null,null,"2005-10-01","ESC138626",null,1,0,0.0552,null,null,1.0552]
["SL_MSSC1","ESC1","SL_OHN4",null,null,"2006-10-01","ESC138991",null,1,0.026,0.0552,null,null,1.0826352]
["SL_MSSC1","ESC1","SL_OHN4",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.0552,null,null,1.1107837151999997]
["SL_MSSC1","ESC1","SL_OHN4",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.0552,null,null,1.1396640960159998]
["SL_MSSC2","ESC2","SL_OHN4",null,null,"2006-10-01","ESC238991",null,1,0.023,0.0552,null,null,1.0794696]
["SL_MSSC2","ESC2","SL_OHN4",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.0552,null,null,1.1042974008]
["SL_MSSC2","ESC2","SL_OHN4",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.0552,null,null,1.1296960648]
["SL_MSSC2","ESC2","SL_OHN4",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.0552,null,null,1.1556793096]
["SL_MSSC2","ESC2","SL_OHN4",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.0552,null,null,1.1822597976]
["SL_MSSC2","ESC2","SL_OHN4",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.0552,null,null,1.1822597976]
["SL_MSSC2","ESC2","SL_OHN4",null,null,"2012-10-01","ESC241183",null,1,null,0.0552,null,null,1.0552]
["SL_MSSF","SL_OH2",{"$nulls":4},"SL_OH2",null,1,0.06,null,null,null,1.06]
["SL_MSSF1","SL_OHN4",{"$nulls":4},"SL_OHN4",null,1,0.0552,null,null,null,1.0552]
["SL_MSSF2","SL_OHN4",{"$nulls":4},"SL_OHN4",null,1,0.0552,null,null,null,1.0552]
["SL_MSSY",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_MSSY1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_MSSY2",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_MSTR","ESC","SL_OH1",null,null,"2003-10-01","ESC37895",null,1,0,0.2,null,null,1.2]
["SL_MSTR","ESC","SL_OH1",null,null,"2004-10-01","ESC38261",null,1,0.029,0.2,null,null,1.2348]
["SL_MSTR","ESC","SL_OH1",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.2,null,null,1.2693744]
["SL_MSTR","ESC","SL_OH1",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.2,null,null,1.302378]
["SL_MSTR","ESC","SL_OH1",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.2,null,null,1.3362395999999999]
["SL_MSTR","ESC","SL_OH1",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.2,null,null,1.370982]
["SL_MSTR1","ESC1","SL_OHN3",null,null,"2005-10-01","ESC138626",null,1,0,0.38,null,null,1.38]
["SL_MSTR1","ESC1","SL_OHN3",null,null,"2006-10-01","ESC138991",null,1,0.026,0.38,null,null,1.41588]
["SL_MSTR1","ESC1","SL_OHN3",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.38,null,null,1.4526928799999999]
["SL_MSTR1","ESC1","SL_OHN3",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.38,null,null,1.4904629003999998]
["SL_MSTR2","ESC2","SL_OHN3",null,null,"2006-10-01","ESC238991",null,1,0.023,0.38,null,null,1.4117399999999998]
["SL_MSTR2","ESC2","SL_OHN3",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.38,null,null,1.4442100199999999]
["SL_MSTR2","ESC2","SL_OHN3",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.38,null,null,1.47742662]
["SL_MSTR2","ESC2","SL_OHN3",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.38,null,null,1.5114077399999999]
["SL_MSTR2","ESC2","SL_OHN3",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.38,null,null,1.54616994]
["SL_MSTR2","ESC2","SL_OHN3",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.38,null,null,1.54616994]
["SL_MSTR2","ESC2","SL_OHN3",null,null,"2012-10-01","ESC241183",null,1,null,0.38,null,null,1.38]
["SL_MSXA",{"$nulls":5},"",{"$nulls":6},0]
["SL_MSXX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["SL_MSXX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["SL_MSXX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["SL_MSXX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["SL_MSXX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["SL_MSXX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["SL_MSXX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["SL_MSXX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["SL_MSXX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["SL_MSXX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["SL_MSXX2","ESC2",null,null,null,"2006-10-01","ESC238991",null,1,0.023,null,null,null,1.023]
["SL_MSXX2","ESC2",null,null,null,"2007-10-01","ESC239356",null,1,0.046529,null,null,null,1.046529]
["SL_MSXX2","ESC2",null,null,null,"2008-10-01","ESC239722",null,1,0.070599,null,null,null,1.070599]
["SL_MSXX2","ESC2",null,null,null,"2009-10-01","ESC240087",null,1,0.095223,null,null,null,1.095223]
["SL_MSXX2","ESC2",null,null,null,"2010-10-01","ESC240452",null,1,0.120413,null,null,null,1.120413]
["SL_MSXX2","ESC2",null,null,null,"2011-10-01","ESC240817",null,1,0.120413,null,null,null,1.120413]
["SL_MSXX2","ESC2",null,null,null,"2012-10-01","ESC241183",null,1,{"$nulls":4},1]
["SL_MTRL","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SL_MTRL","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SL_MTRL","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SL_MTRL","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SL_MTRL","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SL_MTRL","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SL_MTRL1","ESC1","SL_OHN4",null,null,"2005-10-01","ESC138626",null,1,0,0.0552,null,null,1.0552]
["SL_MTRL1","ESC1","SL_OHN4",null,null,"2006-10-01","ESC138991",null,1,0.026,0.0552,null,null,1.0826352]
["SL_MTRL1","ESC1","SL_OHN4",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.0552,null,null,1.1107837151999997]
["SL_MTRL1","ESC1","SL_OHN4",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.0552,null,null,1.1396640960159998]
["SL_MTRL2","ESC2","SL_OHN4",null,null,"2006-10-01","ESC238991",null,1,0.023,0.0552,null,null,1.0794696]
["SL_MTRL2","ESC2","SL_OHN4",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.0552,null,null,1.1042974008]
["SL_MTRL2","ESC2","SL_OHN4",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.0552,null,null,1.1296960648]
["SL_MTRL2","ESC2","SL_OHN4",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.0552,null,null,1.1556793096]
["SL_MTRL2","ESC2","SL_OHN4",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.0552,null,null,1.1822597976]
["SL_MTRL2","ESC2","SL_OHN4",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.0552,null,null,1.1822597976]
["SL_MTRL2","ESC2","SL_OHN4",null,null,"2012-10-01","ESC241183",null,1,null,0.0552,null,null,1.0552]
["SL_MVE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_MVE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_MVE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_MVE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_MVE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_MVE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_MVE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,54.62,0,0.305,0.21,0.38,119.02184117999998]
["SL_MVE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,54.62,0.026,0.305,0.21,0.38,122.11640905067998]
["SL_MVE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,54.62,0.052676,0.305,0.21,0.38,125.29143568599764]
["SL_MVE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,54.62,0.08004558,0.305,0.21,0.38,128.54901348992095]
["SL_MVE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,54.62,0.023,0.305,0.21,0.38,121.75934352713996]
["SL_MVE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,54.62,0.046529,0.305,0.21,0.38,124.5598084282642]
["SL_MVE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,54.62,0.070599,0.305,0.21,0.38,127.42466414546679]
["SL_MVE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,54.62,0.095223,0.305,0.21,0.38,130.35545796268312]
["SL_MVE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,54.62,0.120413,0.305,0.21,0.38,133.35361814200732]
["SL_MVE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,54.62,0.120413,0.305,0.21,0.38,133.35361814200732]
["SL_MVE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,54.62,null,0.305,0.21,0.38,119.02184117999998]
["SL_OE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,58.14,0,0.29,0.215,0.2,109.3508748]
["SL_OE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,58.14,0.029,0.29,0.215,0.2,112.52205016919999]
["SL_OE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,58.14,0.057812,0.29,0.215,0.2,115.6726675739376]
["SL_OE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,58.14,0.085315,0.29,0.215,0.2,118.680144683562]
["SL_OE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,58.14,0.113533,0.29,0.215,0.2,121.7658076686684]
["SL_OE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,58.14,0.142485,0.29,0.215,0.2,124.931734195878]
["SL_OE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,58.14,0,0.305,0.21,0.38,126.69223445999998]
["SL_OE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,58.14,0.026,0.305,0.21,0.38,129.98623255596]
["SL_OE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,58.14,0.052676,0.305,0.21,0.38,133.36587460241495]
["SL_OE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,58.14,0.08004558,0.305,0.21,0.38,136.83338784884668]
["SL_OE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,58.14,0.023,0.305,0.21,0.38,129.60615585257997]
["SL_OE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,58.14,0.046529,0.305,0.21,0.38,132.58709743718933]
["SL_OE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,58.14,0.070599,0.305,0.21,0.38,135.63657952064153]
["SL_OE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,58.14,0.095223,0.305,0.21,0.38,138.75624910198457]
["SL_OE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,58.14,0.120413,0.305,0.21,0.38,141.94762648803197]
["SL_OE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,58.14,0.120413,0.305,0.21,0.38,141.94762648803197]
["SL_OE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,58.14,null,0.305,0.21,0.38,126.69223445999998]
["SL_OT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,31.83,0,0.29,0.215,0.2,59.866500599999995]
["SL_OT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,31.83,0.029,0.29,0.215,0.2,61.60262911739999]
["SL_OT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,31.83,0.057812,0.29,0.215,0.2,63.327502732687186]
["SL_OT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,31.83,0.085315,0.29,0.215,0.2,64.974011098689]
["SL_OT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,31.83,0.113533,0.29,0.215,0.2,66.66332401261978]
["SL_OT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,31.83,0.142485,0.29,0.215,0.2,68.396578937991]
["SL_OT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,31.83,0,0.305,0.21,0.38,69.36040286999999]
["SL_OT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,31.83,0.026,0.305,0.21,0.38,71.16377334461997]
["SL_OT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,31.83,0.052676,0.305,0.21,0.38,73.0140314515801]
["SL_OT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,31.83,0.08004558,0.305,0.21,0.38,74.91239654676279]
["SL_OT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,31.83,0.023,0.305,0.21,0.38,70.95569213600999]
["SL_OT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,31.83,0.046529,0.305,0.21,0.38,72.58767305513823]
["SL_OT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,31.83,0.070599,0.305,0.21,0.38,74.25717795221911]
["SL_OT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,31.83,0.095223,0.305,0.21,0.38,75.96510851249]
["SL_OT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,31.83,0.120413,0.305,0.21,0.38,77.7122970607853]
["SL_OT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,31.83,0.120413,0.305,0.21,0.38,77.7122970607853]
["SL_OT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,31.83,null,0.305,0.21,0.38,69.36040286999999]
["SL_PCCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,33.86,0,0.29,0.215,0.2,63.6845652]
["SL_PCCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,33.86,0.029,0.29,0.215,0.2,65.53141759079999]
["SL_PCCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,33.86,0.057812,0.29,0.215,0.2,67.3662972833424]
["SL_PCCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,33.86,0.085315,0.29,0.215,0.2,69.117813880038]
["SL_PCCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,33.86,0.113533,0.29,0.215,0.2,70.9148649408516]
["SL_PCCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,33.86,0.142485,0.29,0.215,0.2,72.75866047252201]
["SL_PCCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,33.86,0,0.305,0.21,0.38,73.78395354]
["SL_PCCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,33.86,0.026,0.305,0.21,0.38,75.70233633203999]
["SL_PCCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,33.86,0.052676,0.305,0.21,0.38,77.67059707667303]
["SL_PCCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,33.86,0.08004558,0.305,0.21,0.38,79.69003289580235]
["SL_PCCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,33.86,0.023,0.305,0.21,0.38,75.48098447141999]
["SL_PCCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,33.86,0.046529,0.305,0.21,0.38,77.21704711426266]
["SL_PCCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,33.86,0.070599,0.305,0.21,0.38,78.99302687597046]
["SL_PCCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,33.86,0.095223,0.305,0.21,0.38,80.8098829479394]
["SL_PCCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,33.86,0.120413,0.305,0.21,0.38,82.668500737612]
["SL_PCCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,33.86,0.120413,0.305,0.21,0.38,82.668500737612]
["SL_PCCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,33.86,null,0.305,0.21,0.38,73.78395354]
["SL_PCE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,58.14,0,0.29,0.215,0.2,109.3508748]
["SL_PCE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,58.14,0.029,0.29,0.215,0.2,112.52205016919999]
["SL_PCE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,58.14,0.057812,0.29,0.215,0.2,115.6726675739376]
["SL_PCE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,58.14,0.085315,0.29,0.215,0.2,118.680144683562]
["SL_PCE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,58.14,0.113533,0.29,0.215,0.2,121.7658076686684]
["SL_PCE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,58.14,0.142485,0.29,0.215,0.2,124.931734195878]
["SL_PCE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,58.14,0,0.305,0.21,0.38,126.69223445999998]
["SL_PCE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,58.14,0.026,0.305,0.21,0.38,129.98623255596]
["SL_PCE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,58.14,0.052676,0.305,0.21,0.38,133.36587460241495]
["SL_PCE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,58.14,0.08004558,0.305,0.21,0.38,136.83338784884668]
["SL_PCE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,58.14,0.023,0.305,0.21,0.38,129.60615585257997]
["SL_PCE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,58.14,0.046529,0.305,0.21,0.38,132.58709743718933]
["SL_PCE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,58.14,0.070599,0.305,0.21,0.38,135.63657952064153]
["SL_PCE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,58.14,0.095223,0.305,0.21,0.38,138.75624910198457]
["SL_PCE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,58.14,0.120413,0.305,0.21,0.38,141.94762648803197]
["SL_PCE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,58.14,0.120413,0.305,0.21,0.38,141.94762648803197]
["SL_PCE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,58.14,null,0.305,0.21,0.38,126.69223445999998]
["SL_PCEF","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,31.83,0,0.29,0.215,0.2,59.866500599999995]
["SL_PCEF","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,31.83,0.029,0.29,0.215,0.2,61.60262911739999]
["SL_PCEF","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,31.83,0.057812,0.29,0.215,0.2,63.327502732687186]
["SL_PCEF","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,31.83,0.085315,0.29,0.215,0.2,64.974011098689]
["SL_PCEF","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,31.83,0.113533,0.29,0.215,0.2,66.66332401261978]
["SL_PCEF","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,31.83,0.142485,0.29,0.215,0.2,68.396578937991]
["SL_PCEF1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,31.83,0,0.305,0.21,0.38,69.36040286999999]
["SL_PCEF1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,31.83,0.026,0.305,0.21,0.38,71.16377334461997]
["SL_PCEF1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,31.83,0.052676,0.305,0.21,0.38,73.0140314515801]
["SL_PCEF1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,31.83,0.08004558,0.305,0.21,0.38,74.91239654676279]
["SL_PCEF2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,31.83,0.023,0.305,0.21,0.38,70.95569213600999]
["SL_PCEF2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,31.83,0.046529,0.305,0.21,0.38,72.58767305513823]
["SL_PCEF2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,31.83,0.070599,0.305,0.21,0.38,74.25717795221911]
["SL_PCEF2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,31.83,0.095223,0.305,0.21,0.38,75.96510851249]
["SL_PCEF2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,31.83,0.120413,0.305,0.21,0.38,77.7122970607853]
["SL_PCEF2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,31.83,0.120413,0.305,0.21,0.38,77.7122970607853]
["SL_PCEF2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,31.83,null,0.305,0.21,0.38,69.36040286999999]
["SL_PCT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,31.83,0,0.29,0.215,0.2,59.866500599999995]
["SL_PCT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,31.83,0.029,0.29,0.215,0.2,61.60262911739999]
["SL_PCT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,31.83,0.057812,0.29,0.215,0.2,63.327502732687186]
["SL_PCT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,31.83,0.085315,0.29,0.215,0.2,64.974011098689]
["SL_PCT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,31.83,0.113533,0.29,0.215,0.2,66.66332401261978]
["SL_PCT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,31.83,0.142485,0.29,0.215,0.2,68.396578937991]
["SL_PCT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,31.83,0,0.305,0.21,0.38,69.36040286999999]
["SL_PCT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,31.83,0.026,0.305,0.21,0.38,71.16377334461997]
["SL_PCT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,31.83,0.052676,0.305,0.21,0.38,73.0140314515801]
["SL_PCT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,31.83,0.08004558,0.305,0.21,0.38,74.91239654676279]
["SL_PCT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,31.83,0.023,0.305,0.21,0.38,70.95569213600999]
["SL_PCT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,31.83,0.046529,0.305,0.21,0.38,72.58767305513823]
["SL_PCT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,31.83,0.070599,0.305,0.21,0.38,74.25717795221911]
["SL_PCT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,31.83,0.095223,0.305,0.21,0.38,75.96510851249]
["SL_PCT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,31.83,0.120413,0.305,0.21,0.38,77.7122970607853]
["SL_PCT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,31.83,0.120413,0.305,0.21,0.38,77.7122970607853]
["SL_PCT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,31.83,null,0.305,0.21,0.38,69.36040286999999]
["SL_PEX","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,40.7,0,0.29,0.215,0.2,76.54937400000001]
["SL_PEX","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,40.7,0.029,0.29,0.215,0.2,78.769305846]
["SL_PEX","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,40.7,0.057812,0.29,0.215,0.2,80.97484640968801]
["SL_PEX","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,40.7,0.085315,0.29,0.215,0.2,83.08018384281002]
["SL_PEX","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,40.7,0.113533,0.29,0.215,0.2,85.24025407834199]
["SL_PEX","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,40.7,0.142485,0.29,0.215,0.2,87.45651155439002]
["SL_PEX1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,40.7,0,0.305,0.21,0.38,88.6889223]
["SL_PEX1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,40.7,0.026,0.305,0.21,0.38,90.9948342798]
["SL_PEX1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,40.7,0.052676,0.305,0.21,0.38,93.3606999710748]
["SL_PEX1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,40.7,0.08004558,0.305,0.21,0.38,95.78807852507842]
["SL_PEX2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,40.7,0.023,0.305,0.21,0.38,90.72876751289999]
["SL_PEX2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,40.7,0.046529,0.305,0.21,0.38,92.81552916569669]
["SL_PEX2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,40.7,0.070599,0.305,0.21,0.38,94.9502715254577]
["SL_PEX2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,40.7,0.095223,0.305,0.21,0.38,97.1341475481729]
["SL_PEX2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,40.7,0.120413,0.305,0.21,0.38,99.3682215009099]
["SL_PEX2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,40.7,0.120413,0.305,0.21,0.38,99.3682215009099]
["SL_PEX2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,40.7,null,0.305,0.21,0.38,88.6889223]
["SL_PHH","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,45.68,0,0.29,0.215,0.2,85.9158576]
["SL_PHH","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,45.68,0.029,0.29,0.215,0.2,88.4074174704]
["SL_PHH","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,45.68,0.057812,0.29,0.215,0.2,90.88282515957121]
["SL_PHH","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,45.68,0.085315,0.29,0.215,0.2,93.245768991144]
["SL_PHH","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,45.68,0.113533,0.29,0.215,0.2,95.67014266090081]
["SL_PHH","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,45.68,0.142485,0.29,0.215,0.2,98.15757857013601]
["SL_PHH1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,49.4,0,0.305,0.21,0.38,107.64699659999998]
["SL_PHH1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,49.4,0.026,0.305,0.21,0.38,110.44581851159998]
["SL_PHH1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,49.4,0.052676,0.305,0.21,0.38,113.31740979290157]
["SL_PHH1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,49.4,0.08004558,0.305,0.21,0.38,116.263662878105]
["SL_PHH2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,49.4,0.023,0.305,0.21,0.38,110.12287752179996]
["SL_PHH2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,49.4,0.046529,0.305,0.21,0.38,112.65570370480137]
["SL_PHH2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,49.4,0.070599,0.305,0.21,0.38,115.2467669129634]
["SL_PHH2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,49.4,0.095223,0.305,0.21,0.38,117.89746655724178]
["SL_PHH2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,49.4,0.120413,0.305,0.21,0.38,120.60909440159577]
["SL_PHH2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,49.4,0.120413,0.305,0.21,0.38,120.60909440159577]
["SL_PHH2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,49.4,null,0.305,0.21,0.38,107.64699659999998]
["SL_PHPD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,36.17,0,0.29,0.215,0.2,68.0292594]
["SL_PHPD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,36.17,0.029,0.29,0.215,0.2,70.0021079226]
["SL_PHPD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,36.17,0.057812,0.29,0.215,0.2,71.96216694443281]
["SL_PHPD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,36.17,0.085315,0.29,0.215,0.2,73.83317566571101]
["SL_PHPD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,36.17,0.113533,0.29,0.215,0.2,75.7528253074602]
["SL_PHPD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,36.17,0.142485,0.29,0.215,0.2,77.722408425609]
["SL_PHPD1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,36.17,0,0.305,0.21,0.38,78.81764912999999]
["SL_PHPD1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,36.17,0.026,0.305,0.21,0.38,80.86690800737999]
["SL_PHPD1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,36.17,0.052676,0.305,0.21,0.38,82.96944761557188]
["SL_PHPD1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,36.17,0.08004558,0.305,0.21,0.38,85.12665356884733]
["SL_PHPD2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,36.17,0.023,0.305,0.21,0.38,80.63045505998997]
["SL_PHPD2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,36.17,0.046529,0.305,0.21,0.38,82.48495552636977]
["SL_PHPD2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,36.17,0.070599,0.305,0.21,0.38,84.38209634092887]
["SL_PHPD2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,36.17,0.095223,0.305,0.21,0.38,86.322902133106]
["SL_PHPD2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,36.17,0.120413,0.305,0.21,0.38,88.3083187146907]
["SL_PHPD2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,36.17,0.120413,0.305,0.21,0.38,88.3083187146907]
["SL_PHPD2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,36.17,null,0.305,0.21,0.38,78.81764912999999]
["SL_PHPU","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,63.33,0,0.305,0.21,0.38,138.00170636999997]
["SL_PHPU","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,63.33,0.026,0.305,0.21,0.38,141.58975073562]
["SL_PHPU","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,63.33,0.052676,0.305,0.21,0.38,145.27108425474609]
["SL_PHPU","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,63.33,0.08004558,0.305,0.21,0.38,149.0481329973763]
["SL_PHPU2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,63.33,0.023,0.305,0.21,0.38,141.17574561650994]
["SL_PHPU2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,63.33,0.046529,0.305,0.21,0.38,144.4227877656897]
["SL_PHPU2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,63.33,0.070599,0.305,0.21,0.38,147.74448883801563]
["SL_PHPU2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,63.33,0.095223,0.305,0.21,0.38,151.1426428556705]
["SL_PHPU2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,63.33,0.120413,0.305,0.21,0.38,154.61890583913078]
["SL_PHPU2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,63.33,0.120413,0.305,0.21,0.38,154.61890583913078]
["SL_PHPU2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,63.33,null,0.305,0.21,0.38,138.00170636999997]
["SL_PHS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,37.62,0,0.29,0.215,0.2,70.7564484]
["SL_PHS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,37.62,0.029,0.29,0.215,0.2,72.80838540359998]
["SL_PHS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,37.62,0.057812,0.29,0.215,0.2,74.84702019490081]
["SL_PHS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,37.62,0.085315,0.29,0.215,0.2,76.79303479524602]
["SL_PHS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,37.62,0.113533,0.29,0.215,0.2,78.78964025619719]
["SL_PHS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,37.62,0.142485,0.29,0.215,0.2,80.83818095027401]
["SL_PHS1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,37.62,0,0.305,0.21,0.38,81.97732817999999]
["SL_PHS1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,37.62,0.026,0.305,0.21,0.38,84.10873871267998]
["SL_PHS1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,37.62,0.052676,0.305,0.21,0.38,86.29556591920965]
["SL_PHS1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,37.62,0.08004558,0.305,0.21,0.38,88.53925096101842]
["SL_PHS2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,37.62,0.023,0.305,0.21,0.38,83.86280672813999]
["SL_PHS2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,37.62,0.046529,0.305,0.21,0.38,85.79165128288722]
["SL_PHS2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,37.62,0.070599,0.305,0.21,0.38,87.76484557217981]
["SL_PHS2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,37.62,0.095223,0.305,0.21,0.38,89.78345530128414]
["SL_PHS2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,37.62,0.120413,0.305,0.21,0.38,91.84846419813833]
["SL_PHS2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,37.62,0.120413,0.305,0.21,0.38,91.84846419813833]
["SL_PHS2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,37.62,null,0.305,0.21,0.38,81.97732817999999]
["SL_PHSS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,47.88,0,0.29,0.215,0.2,90.05366160000001]
["SL_PHSS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,47.88,0.029,0.29,0.215,0.2,92.66521778639999]
["SL_PHSS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,47.88,0.057812,0.29,0.215,0.2,95.25984388441923]
["SL_PHSS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,47.88,0.085315,0.29,0.215,0.2,97.736589739404]
["SL_PHSS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,47.88,0.113533,0.29,0.215,0.2,100.27772396243279]
["SL_PHSS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,47.88,0.142485,0.29,0.215,0.2,102.884957573076]
["SL_PHSS1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,47.88,0,0.305,0.21,0.38,104.33478132]
["SL_PHSS1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,47.88,0.026,0.305,0.21,0.38,107.04748563432]
["SL_PHSS1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,47.88,0.052676,0.305,0.21,0.38,109.8307202608123]
["SL_PHSS1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,47.88,0.08004558,0.305,0.21,0.38,112.68631940493255]
["SL_PHSS2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,47.88,0.023,0.305,0.21,0.38,106.73448129036]
["SL_PHSS2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,47.88,0.046529,0.305,0.21,0.38,109.18937436003827]
["SL_PHSS2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,47.88,0.070599,0.305,0.21,0.38,111.70071254641067]
["SL_PHSS2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,47.88,0.095223,0.305,0.21,0.38,114.26985220163435]
["SL_PHSS2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,47.88,0.120413,0.305,0.21,0.38,116.89804534308516]
["SL_PHSS2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,47.88,0.120413,0.305,0.21,0.38,116.89804534308516]
["SL_PHSS2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,47.88,null,0.305,0.21,0.38,104.33478132]
["SL_PM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,63.8,0,0.29,0.215,0.2,119.99631599999998]
["SL_PM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,63.8,0.029,0.29,0.215,0.2,123.476209164]
["SL_PM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,63.8,0.057812,0.29,0.215,0.2,126.933543020592]
["SL_PM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,63.8,0.085315,0.29,0.215,0.2,130.23380169954004]
["SL_PM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,63.8,0.113533,0.29,0.215,0.2,133.61985774442797]
["SL_PM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,63.8,0.142485,0.29,0.215,0.2,137.09399108526]
["SL_PM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,83.63,0,0.305,0.21,0.38,182.23721306999997]
["SL_PM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,83.63,0.026,0.305,0.21,0.38,186.97538060981995]
["SL_PM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,83.63,0.052676,0.305,0.21,0.38,191.83674050567527]
["SL_PM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,83.63,0.08004558,0.305,0.21,0.38,196.82449648777168]
["SL_PM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,83.63,0.023,0.305,0.21,0.38,186.42866897060992]
["SL_PM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,83.63,0.046529,0.305,0.21,0.38,190.716528356934]
["SL_PM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,83.63,0.070599,0.305,0.21,0.38,195.1029780755289]
["SL_PM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,83.63,0.095223,0.305,0.21,0.38,199.59038721016458]
["SL_PM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,83.63,0.120413,0.305,0.21,0.38,204.18094260739787]
["SL_PM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,83.63,0.120413,0.305,0.21,0.38,204.18094260739787]
["SL_PM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,83.63,null,0.305,0.21,0.38,182.23721306999997]
["SL_POWB",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_POWB1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_POWB2",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_QAO","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_QAO","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_QAO","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_QAO","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_QAO","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_QAO","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_QAO1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,35.53,0,0.305,0.21,0.38,77.42303216999998]
["SL_QAO1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,35.53,0.026,0.305,0.21,0.38,79.43603100642]
["SL_QAO1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,35.53,0.052676,0.305,0.21,0.38,81.5013678125869]
["SL_QAO1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,35.53,0.08004558,0.305,0.21,0.38,83.6204036854063]
["SL_QAO2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,35.53,0.023,0.305,0.21,0.38,79.20376190990997]
["SL_QAO2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,35.53,0.046529,0.305,0.21,0.38,81.02544843383791]
["SL_QAO2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,35.53,0.070599,0.305,0.21,0.38,82.88902081816983]
["SL_QAO2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,35.53,0.095223,0.305,0.21,0.38,84.7954855623239]
["SL_QAO2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,35.53,0.120413,0.305,0.21,0.38,86.74577174268619]
["SL_QAO2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,35.53,0.120413,0.305,0.21,0.38,86.74577174268619]
["SL_QAO2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,35.53,null,0.305,0.21,0.38,77.42303216999998]
["SL_SEE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_SEE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_SEE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_SEE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_SEE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_SEE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_SEE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,54.62,0,0.305,0.21,0.38,119.02184117999998]
["SL_SEE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,54.62,0.026,0.305,0.21,0.38,122.11640905067998]
["SL_SEE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,54.62,0.052676,0.305,0.21,0.38,125.29143568599764]
["SL_SEE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,54.62,0.08004558,0.305,0.21,0.38,128.54901348992095]
["SL_SEE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,54.62,0.023,0.305,0.21,0.38,121.75934352713996]
["SL_SEE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,54.62,0.046529,0.305,0.21,0.38,124.5598084282642]
["SL_SEE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,54.62,0.070599,0.305,0.21,0.38,127.42466414546679]
["SL_SEE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,54.62,0.095223,0.305,0.21,0.38,130.35545796268312]
["SL_SEE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,54.62,0.120413,0.305,0.21,0.38,133.35361814200732]
["SL_SEE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,54.62,0.120413,0.305,0.21,0.38,133.35361814200732]
["SL_SEE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,54.62,null,0.305,0.21,0.38,119.02184117999998]
["SL_SEEM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_SEEM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_SEEM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_SEEM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_SEEM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_SEEM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_SEEM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,54.62,0,0.305,0.21,0.38,119.02184117999998]
["SL_SEEM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,54.62,0.026,0.305,0.21,0.38,122.11640905067998]
["SL_SEEM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,54.62,0.052676,0.305,0.21,0.38,125.29143568599764]
["SL_SEEM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,54.62,0.08004558,0.305,0.21,0.38,128.54901348992095]
["SL_SEEM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,54.62,0.023,0.305,0.21,0.38,121.75934352713996]
["SL_SEEM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,54.62,0.046529,0.305,0.21,0.38,124.5598084282642]
["SL_SEEM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,54.62,0.070599,0.305,0.21,0.38,127.42466414546679]
["SL_SEEM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,54.62,0.095223,0.305,0.21,0.38,130.35545796268312]
["SL_SEEM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,54.62,0.120413,0.305,0.21,0.38,133.35361814200732]
["SL_SEEM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,54.62,0.120413,0.305,0.21,0.38,133.35361814200732]
["SL_SEEM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,54.62,null,0.305,0.21,0.38,119.02184117999998]
["SL_SEL","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2003-10-01","ESC37895",null,38,0,0,0,0.2,45.6]
["SL_SEL","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2004-10-01","ESC38261",null,38,0.029,0,0,0.2,46.922399999999996]
["SL_SEL","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2005-10-01","ESC38626",null,38,0.057812,0,0,0.2,48.236227199999995]
["SL_SEL","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2006-10-01","ESC38991",null,38,0.085315,0,0,0.2,49.490364]
["SL_SEL","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2007-10-01","ESC39356",null,38,0.113533,0,0,0.2,50.7771048]
["SL_SEL","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2008-10-01","ESC39722",null,38,0.142485,0,0,0.2,52.09731599999999]
["SL_SEL1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN3","2005-10-01","ESC138626",null,38,0,0,0,0.38,52.44]
["SL_SEL1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN3","2006-10-01","ESC138991",null,38,0.026,0,0,0.38,53.803439999999995]
["SL_SEL1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN3","2007-10-01","ESC139356",null,38,0.052676,0,0,0.38,55.20232944]
["SL_SEL1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN3","2008-10-01","ESC139722",null,38,0.08004558,0,0,0.38,56.63759021519999]
["SL_SEL2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN3","2006-10-01","ESC238991",null,38,0.023,0,0,0.38,53.64611999999999]
["SL_SEL2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN3","2007-10-01","ESC239356",null,38,0.046529,0,0,0.38,54.879980759999995]
["SL_SEL2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN3","2008-10-01","ESC239722",null,38,0.070599,0,0,0.38,56.14221156]
["SL_SEL2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN3","2009-10-01","ESC240087",null,38,0.095223,0,0,0.38,57.43349411999999]
["SL_SEL2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN3","2010-10-01","ESC240452",null,38,0.120413,0,0,0.38,58.754457720000005]
["SL_SEL2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN3","2011-10-01","ESC240817",null,38,0.120413,0,0,0.38,58.754457720000005]
["SL_SEL2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN3","2012-10-01","ESC241183",null,38,null,0,0,0.38,52.44]
["SL_SEPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,32.28,0,0.29,0.215,0.2,60.71286960000001]
["SL_SEPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,32.28,0.029,0.29,0.215,0.2,62.47354281839999]
["SL_SEPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,32.28,0.057812,0.29,0.215,0.2,64.2228020173152]
["SL_SEPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,32.28,0.085315,0.29,0.215,0.2,65.892588069924]
["SL_SEPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,32.28,0.113533,0.29,0.215,0.2,67.60578382429681]
["SL_SEPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,32.28,0.142485,0.29,0.215,0.2,69.363542824956]
["SL_SEPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,32.28,0,0.305,0.21,0.38,70.34099291999999]
["SL_SEPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,32.28,0.026,0.305,0.21,0.38,72.16985873591999]
["SL_SEPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,32.28,0.052676,0.305,0.21,0.38,74.0462750630539]
["SL_SEPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,32.28,0.08004558,0.305,0.21,0.38,75.97147849605729]
["SL_SEPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,32.28,0.023,0.305,0.21,0.38,71.95883575715997]
["SL_SEPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,32.28,0.046529,0.305,0.21,0.38,73.61388897957468]
["SL_SEPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,32.28,0.070599,0.305,0.21,0.38,75.30699667915907]
["SL_SEPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,32.28,0.095223,0.305,0.21,0.38,77.03907328882116]
["SL_SEPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,32.28,0.120413,0.305,0.21,0.38,78.81096290047596]
["SL_SEPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,32.28,0.120413,0.305,0.21,0.38,78.81096290047596]
["SL_SEPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,32.28,null,0.305,0.21,0.38,70.34099291999999]
["SL_SRA","ESC","SL_OH1",null,null,"2003-10-01","ESC37895",null,20.83,0,0.2,null,null,24.996]
["SL_SRA","ESC","SL_OH1",null,null,"2004-10-01","ESC38261",null,20.83,0.029,0.2,null,null,25.720883999999995]
["SL_SRA","ESC","SL_OH1",null,null,"2005-10-01","ESC38626",null,20.83,0.057812,0.2,null,null,26.441068751999996]
["SL_SRA","ESC","SL_OH1",null,null,"2006-10-01","ESC38991",null,20.83,0.085315,0.2,null,null,27.128533739999998]
["SL_SRA","ESC","SL_OH1",null,null,"2007-10-01","ESC39356",null,20.83,0.113533,0.2,null,null,27.833870867999995]
["SL_SRA","ESC","SL_OH1",null,null,"2008-10-01","ESC39722",null,20.83,0.142485,0.2,null,null,28.557555059999995]
["SL_SRA1","ESC1","SL_OHN3",null,null,"2005-10-01","ESC138626",null,20.83,0,0.38,null,null,28.745399999999997]
["SL_SRA1","ESC1","SL_OHN3",null,null,"2006-10-01","ESC138991",null,20.83,0.026,0.38,null,null,29.492780399999994]
["SL_SRA1","ESC1","SL_OHN3",null,null,"2007-10-01","ESC139356",null,20.83,0.052676,0.38,null,null,30.259592690399995]
["SL_SRA1","ESC1","SL_OHN3",null,null,"2008-10-01","ESC139722",null,20.83,0.08004558,0.38,null,null,31.046342215331993]
["SL_SRA2","ESC2","SL_OHN3",null,null,"2006-10-01","ESC238991",null,20.83,0.023,0.38,null,null,29.406544199999995]
["SL_SRA2","ESC2","SL_OHN3",null,null,"2007-10-01","ESC239356",null,20.83,0.046529,0.38,null,null,30.0828947166]
["SL_SRA2","ESC2","SL_OHN3",null,null,"2008-10-01","ESC239722",null,20.83,0.070599,0.38,null,null,30.774796494599997]
["SL_SRA2","ESC2","SL_OHN3",null,null,"2009-10-01","ESC240087",null,20.83,0.095223,0.38,null,null,31.482623224199997]
["SL_SRA2","ESC2","SL_OHN3",null,null,"2010-10-01","ESC240452",null,20.83,0.120413,0.38,null,null,32.206719850199995]
["SL_SRA2","ESC2","SL_OHN3",null,null,"2011-10-01","ESC240817",null,20.83,0.120413,0.38,null,null,32.206719850199995]
["SL_SRA2","ESC2","SL_OHN3",null,null,"2012-10-01","ESC241183",null,20.83,null,0.38,null,null,28.745399999999997]
["SL_STUP",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_STUP1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_STUP2",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_TMUC","ESC","SL_FRING1","SL_LEAV1","SL_OH1","2003-10-01","ESC37895",null,60.55,0,1,0,0.2,145.32]
["SL_TMUC","ESC","SL_FRING1","SL_LEAV1","SL_OH1","2004-10-01","ESC38261",null,60.55,0.029,1,0,0.2,149.53427999999997]
["SL_TMUC","ESC","SL_FRING1","SL_LEAV1","SL_OH1","2005-10-01","ESC38626",null,60.55,0.057812,1,0,0.2,153.72123983999998]
["SL_TMUC","ESC","SL_FRING1","SL_LEAV1","SL_OH1","2006-10-01","ESC38991",null,60.55,0.085315,1,0,0.2,157.7179758]
["SL_TMUC","ESC","SL_FRING1","SL_LEAV1","SL_OH1","2007-10-01","ESC39356",null,60.55,0.113533,1,0,0.2,161.81861555999998]
["SL_TMUC","ESC","SL_FRING1","SL_LEAV1","SL_OH1","2008-10-01","ESC39722",null,60.55,0.142485,1,0,0.2,166.02592019999997]
["SL_TMUC1","ESC1","SL_FRING1","SL_LEAV1","SL_OHN3","2005-10-01","ESC138626",null,60.55,0,1,0,0.38,167.11799999999997]
["SL_TMUC1","ESC1","SL_FRING1","SL_LEAV1","SL_OHN3","2006-10-01","ESC138991",null,60.55,0.026,1,0,0.38,171.463068]
["SL_TMUC1","ESC1","SL_FRING1","SL_LEAV1","SL_OHN3","2007-10-01","ESC139356",null,60.55,0.052676,1,0,0.38,175.92110776799998]
["SL_TMUC1","ESC1","SL_FRING1","SL_LEAV1","SL_OHN3","2008-10-01","ESC139722",null,60.55,0.08004558,1,0,0.38,180.49505723843995]
["SL_TMUC2","ESC2","SL_FRING1","SL_LEAV1","SL_OHN3","2006-10-01","ESC238991",null,60.55,0.023,1,0,0.38,170.96171399999997]
["SL_TMUC2","ESC2","SL_FRING1","SL_LEAV1","SL_OHN3","2007-10-01","ESC239356",null,60.55,0.046529,1,0,0.38,174.893833422]
["SL_TMUC2","ESC2","SL_FRING1","SL_LEAV1","SL_OHN3","2008-10-01","ESC239722",null,60.55,0.070599,1,0,0.38,178.916363682]
["SL_TMUC2","ESC2","SL_FRING1","SL_LEAV1","SL_OHN3","2009-10-01","ESC240087",null,60.55,0.095223,1,0,0.38,183.031477314]
["SL_TMUC2","ESC2","SL_FRING1","SL_LEAV1","SL_OHN3","2010-10-01","ESC240452",null,60.55,0.120413,1,0,0.38,187.241179734]
["SL_TMUC2","ESC2","SL_FRING1","SL_LEAV1","SL_OHN3","2011-10-01","ESC240817",null,60.55,0.120413,1,0,0.38,187.241179734]
["SL_TMUC2","ESC2","SL_FRING1","SL_LEAV1","SL_OHN3","2012-10-01","ESC241183",null,60.55,null,1,0,0.38,167.11799999999997]
["SL_TMUE","ESC","SL_OH1",null,null,"2003-10-01","ESC37895",null,77.99,0,0.2,null,null,93.588]
["SL_TMUE","ESC","SL_OH1",null,null,"2004-10-01","ESC38261",null,77.99,0.029,0.2,null,null,96.30205199999999]
["SL_TMUE","ESC","SL_OH1",null,null,"2005-10-01","ESC38626",null,77.99,0.057812,0.2,null,null,98.998509456]
["SL_TMUE","ESC","SL_OH1",null,null,"2006-10-01","ESC38991",null,77.99,0.085315,0.2,null,null,101.57246021999998]
["SL_TMUE","ESC","SL_OH1",null,null,"2007-10-01","ESC39356",null,77.99,0.113533,0.2,null,null,104.21332640399999]
["SL_TMUE","ESC","SL_OH1",null,null,"2008-10-01","ESC39722",null,77.99,0.142485,0.2,null,null,106.92288617999999]
["SL_TMUE1","ESC1","SL_OHN3",null,null,"2005-10-01","ESC138626",null,77.99,0,0.38,null,null,107.62619999999998]
["SL_TMUE1","ESC1","SL_OHN3",null,null,"2006-10-01","ESC138991",null,77.99,0.026,0.38,null,null,110.4244812]
["SL_TMUE1","ESC1","SL_OHN3",null,null,"2007-10-01","ESC139356",null,77.99,0.052676,0.38,null,null,113.29551771119998]
["SL_TMUE1","ESC1","SL_OHN3",null,null,"2008-10-01","ESC139722",null,77.99,0.08004558,0.38,null,null,116.24120160219599]
["SL_TMUE2","ESC2","SL_OHN3",null,null,"2006-10-01","ESC238991",null,77.99,0.023,0.38,null,null,110.10160259999998]
["SL_TMUE2","ESC2","SL_OHN3",null,null,"2007-10-01","ESC239356",null,77.99,0.046529,0.38,null,null,112.63393945979999]
["SL_TMUE2","ESC2","SL_OHN3",null,null,"2008-10-01","ESC239722",null,77.99,0.070599,0.38,null,null,115.2245020938]
["SL_TMUE2","ESC2","SL_OHN3",null,null,"2009-10-01","ESC240087",null,77.99,0.095223,0.38,null,null,117.8746896426]
["SL_TMUE2","ESC2","SL_OHN3",null,null,"2010-10-01","ESC240452",null,77.99,0.120413,0.38,null,null,120.58579362059999]
["SL_TMUE2","ESC2","SL_OHN3",null,null,"2011-10-01","ESC240817",null,77.99,0.120413,0.38,null,null,120.58579362059999]
["SL_TMUE2","ESC2","SL_OHN3",null,null,"2012-10-01","ESC241183",null,77.99,null,0.38,null,null,107.62619999999998]
["SL_TMUI","ESC","SL_OH1",null,null,"2003-10-01","ESC37895",null,61.62,0,0.2,null,null,73.94399999999999]
["SL_TMUI","ESC","SL_OH1",null,null,"2004-10-01","ESC38261",null,61.62,0.029,0.2,null,null,76.08837599999998]
["SL_TMUI","ESC","SL_OH1",null,null,"2005-10-01","ESC38626",null,61.62,0.057812,0.2,null,null,78.218850528]
["SL_TMUI","ESC","SL_OH1",null,null,"2006-10-01","ESC38991",null,61.62,0.085315,0.2,null,null,80.25253235999999]
["SL_TMUI","ESC","SL_OH1",null,null,"2007-10-01","ESC39356",null,61.62,0.113533,0.2,null,null,82.33908415199998]
["SL_TMUI","ESC","SL_OH1",null,null,"2008-10-01","ESC39722",null,61.62,0.142485,0.2,null,null,84.47991083999999]
["SL_TMUI1","ESC1","SL_OHN3",null,null,"2005-10-01","ESC138626",null,61.62,0,0.38,null,null,85.03559999999999]
["SL_TMUI1","ESC1","SL_OHN3",null,null,"2006-10-01","ESC138991",null,61.62,0.026,0.38,null,null,87.24652559999998]
["SL_TMUI1","ESC1","SL_OHN3",null,null,"2007-10-01","ESC139356",null,61.62,0.052676,0.38,null,null,89.51493526559997]
["SL_TMUI1","ESC1","SL_OHN3",null,null,"2008-10-01","ESC139722",null,61.62,0.08004558,0.38,null,null,91.84232392264798]
["SL_TMUI2","ESC2","SL_OHN3",null,null,"2006-10-01","ESC238991",null,61.62,0.023,0.38,null,null,86.99141879999998]
["SL_TMUI2","ESC2","SL_OHN3",null,null,"2007-10-01","ESC239356",null,61.62,0.046529,0.38,null,null,88.99222143239999]
["SL_TMUI2","ESC2","SL_OHN3",null,null,"2008-10-01","ESC239722",null,61.62,0.070599,0.38,null,null,91.0390283244]
["SL_TMUI2","ESC2","SL_OHN3",null,null,"2009-10-01","ESC240087",null,61.62,0.095223,0.38,null,null,93.1329449388]
["SL_TMUI2","ESC2","SL_OHN3",null,null,"2010-10-01","ESC240452",null,61.62,0.120413,0.38,null,null,95.27499170280001]
["SL_TMUI2","ESC2","SL_OHN3",null,null,"2011-10-01","ESC240817",null,61.62,0.120413,0.38,null,null,95.27499170280001]
["SL_TMUI2","ESC2","SL_OHN3",null,null,"2012-10-01","ESC241183",null,61.62,null,0.38,null,null,85.03559999999999]
["SL_TMUO","ESC","SL_OH1",null,null,"2003-10-01","ESC37895",null,64.45,0,0.2,null,null,77.34]
["SL_TMUO","ESC","SL_OH1",null,null,"2004-10-01","ESC38261",null,64.45,0.029,0.2,null,null,79.58286]
["SL_TMUO","ESC","SL_OH1",null,null,"2005-10-01","ESC38626",null,64.45,0.057812,0.2,null,null,81.81118008]
["SL_TMUO","ESC","SL_OH1",null,null,"2006-10-01","ESC38991",null,64.45,0.085315,0.2,null,null,83.9382621]
["SL_TMUO","ESC","SL_OH1",null,null,"2007-10-01","ESC39356",null,64.45,0.113533,0.2,null,null,86.12064222]
["SL_TMUO","ESC","SL_OH1",null,null,"2008-10-01","ESC39722",null,64.45,0.142485,0.2,null,null,88.35978990000001]
["SL_TMUO1","ESC1","SL_OHN3",null,null,"2005-10-01","ESC138626",null,64.45,0,0.38,null,null,88.941]
["SL_TMUO1","ESC1","SL_OHN3",null,null,"2006-10-01","ESC138991",null,64.45,0.026,0.38,null,null,91.253466]
["SL_TMUO1","ESC1","SL_OHN3",null,null,"2007-10-01","ESC139356",null,64.45,0.052676,0.38,null,null,93.62605611599999]
["SL_TMUO1","ESC1","SL_OHN3",null,null,"2008-10-01","ESC139722",null,64.45,0.08004558,0.38,null,null,96.06033393078]
["SL_TMUO2","ESC2","SL_OHN3",null,null,"2006-10-01","ESC238991",null,64.45,0.023,0.38,null,null,90.98664299999999]
["SL_TMUO2","ESC2","SL_OHN3",null,null,"2007-10-01","ESC239356",null,64.45,0.046529,0.38,null,null,93.079335789]
["SL_TMUO2","ESC2","SL_OHN3",null,null,"2008-10-01","ESC239722",null,64.45,0.070599,0.38,null,null,95.22014565900001]
["SL_TMUO2","ESC2","SL_OHN3",null,null,"2009-10-01","ESC240087",null,64.45,0.095223,0.38,null,null,97.410228843]
["SL_TMUO2","ESC2","SL_OHN3",null,null,"2010-10-01","ESC240452",null,64.45,0.120413,0.38,null,null,99.65065263299999]
["SL_TMUO2","ESC2","SL_OHN3",null,null,"2011-10-01","ESC240817",null,64.45,0.120413,0.38,null,null,99.65065263299999]
["SL_TMUO2","ESC2","SL_OHN3",null,null,"2012-10-01","ESC241183",null,64.45,null,0.38,null,null,88.941]
["SL_TMUP","ESC","SL_OH1",null,null,"2003-10-01","ESC37895",null,74.69,0,0.2,null,null,89.628]
["SL_TMUP","ESC","SL_OH1",null,null,"2004-10-01","ESC38261",null,74.69,0.029,0.2,null,null,92.227212]
["SL_TMUP","ESC","SL_OH1",null,null,"2005-10-01","ESC38626",null,74.69,0.057812,0.2,null,null,94.80957393599998]
["SL_TMUP","ESC","SL_OH1",null,null,"2006-10-01","ESC38991",null,74.69,0.085315,0.2,null,null,97.27461282]
["SL_TMUP","ESC","SL_OH1",null,null,"2007-10-01","ESC39356",null,74.69,0.113533,0.2,null,null,99.80373572399999]
["SL_TMUP","ESC","SL_OH1",null,null,"2008-10-01","ESC39722",null,74.69,0.142485,0.2,null,null,102.39864558]
["SL_TMUP1","ESC1","SL_OHN3",null,null,"2005-10-01","ESC138626",null,74.69,0,0.38,null,null,103.0722]
["SL_TMUP1","ESC1","SL_OHN3",null,null,"2006-10-01","ESC138991",null,74.69,0.026,0.38,null,null,105.75207719999999]
["SL_TMUP1","ESC1","SL_OHN3",null,null,"2007-10-01","ESC139356",null,74.69,0.052676,0.38,null,null,108.50163120719998]
["SL_TMUP1","ESC1","SL_OHN3",null,null,"2008-10-01","ESC139722",null,74.69,0.08004558,0.38,null,null,111.32267403087599]
["SL_TMUP2","ESC2","SL_OHN3",null,null,"2006-10-01","ESC238991",null,74.69,0.023,0.38,null,null,105.44286059999997]
["SL_TMUP2","ESC2","SL_OHN3",null,null,"2007-10-01","ESC239356",null,74.69,0.046529,0.38,null,null,107.8680463938]
["SL_TMUP2","ESC2","SL_OHN3",null,null,"2008-10-01","ESC239722",null,74.69,0.070599,0.38,null,null,110.3489942478]
["SL_TMUP2","ESC2","SL_OHN3",null,null,"2009-10-01","ESC240087",null,74.69,0.095223,0.38,null,null,112.88704410060001]
["SL_TMUP2","ESC2","SL_OHN3",null,null,"2010-10-01","ESC240452",null,74.69,0.120413,0.38,null,null,115.4834328186]
["SL_TMUP2","ESC2","SL_OHN3",null,null,"2011-10-01","ESC240817",null,74.69,0.120413,0.38,null,null,115.4834328186]
["SL_TMUP2","ESC2","SL_OHN3",null,null,"2012-10-01","ESC241183",null,74.69,null,0.38,null,null,103.0722]
["SL_TMUW","ESC","SL_OH1",null,null,"2003-10-01","ESC37895",null,61.62,0,0.2,null,null,73.94399999999999]
["SL_TMUW","ESC","SL_OH1",null,null,"2004-10-01","ESC38261",null,61.62,0.029,0.2,null,null,76.08837599999998]
["SL_TMUW","ESC","SL_OH1",null,null,"2005-10-01","ESC38626",null,61.62,0.057812,0.2,null,null,78.218850528]
["SL_TMUW","ESC","SL_OH1",null,null,"2006-10-01","ESC38991",null,61.62,0.085315,0.2,null,null,80.25253235999999]
["SL_TMUW","ESC","SL_OH1",null,null,"2007-10-01","ESC39356",null,61.62,0.113533,0.2,null,null,82.33908415199998]
["SL_TMUW","ESC","SL_OH1",null,null,"2008-10-01","ESC39722",null,61.62,0.142485,0.2,null,null,84.47991083999999]
["SL_TMUW1","ESC1","SL_OHN3",null,null,"2005-10-01","ESC138626",null,61.62,0,0.38,null,null,85.03559999999999]
["SL_TMUW1","ESC1","SL_OHN3",null,null,"2006-10-01","ESC138991",null,61.62,0.026,0.38,null,null,87.24652559999998]
["SL_TMUW1","ESC1","SL_OHN3",null,null,"2007-10-01","ESC139356",null,61.62,0.052676,0.38,null,null,89.51493526559997]
["SL_TMUW1","ESC1","SL_OHN3",null,null,"2008-10-01","ESC139722",null,61.62,0.08004558,0.38,null,null,91.84232392264798]
["SL_TMUW2","ESC2","SL_OHN3",null,null,"2006-10-01","ESC238991",null,61.62,0.023,0.38,null,null,86.99141879999998]
["SL_TMUW2","ESC2","SL_OHN3",null,null,"2007-10-01","ESC239356",null,61.62,0.046529,0.38,null,null,88.99222143239999]
["SL_TMUW2","ESC2","SL_OHN3",null,null,"2008-10-01","ESC239722",null,61.62,0.070599,0.38,null,null,91.0390283244]
["SL_TMUW2","ESC2","SL_OHN3",null,null,"2009-10-01","ESC240087",null,61.62,0.095223,0.38,null,null,93.1329449388]
["SL_TMUW2","ESC2","SL_OHN3",null,null,"2010-10-01","ESC240452",null,61.62,0.120413,0.38,null,null,95.27499170280001]
["SL_TMUW2","ESC2","SL_OHN3",null,null,"2011-10-01","ESC240817",null,61.62,0.120413,0.38,null,null,95.27499170280001]
["SL_TMUW2","ESC2","SL_OHN3",null,null,"2012-10-01","ESC241183",null,61.62,null,0.38,null,null,85.03559999999999]
["SL_TSM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_TSM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_TSM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_TSM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_TSM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_TSM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_TSM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,54.62,0,0.305,0.21,0.38,119.02184117999998]
["SL_TSM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,54.62,0.026,0.305,0.21,0.38,122.11640905067998]
["SL_TSM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,54.62,0.052676,0.305,0.21,0.38,125.29143568599764]
["SL_TSM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,54.62,0.08004558,0.305,0.21,0.38,128.54901348992095]
["SL_TSM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,54.62,0.023,0.305,0.21,0.38,121.75934352713996]
["SL_TSM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,54.62,0.046529,0.305,0.21,0.38,124.5598084282642]
["SL_TSM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,54.62,0.070599,0.305,0.21,0.38,127.42466414546679]
["SL_TSM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,54.62,0.095223,0.305,0.21,0.38,130.35545796268312]
["SL_TSM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,54.62,0.120413,0.305,0.21,0.38,133.35361814200732]
["SL_TSM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,54.62,0.120413,0.305,0.21,0.38,133.35361814200732]
["SL_TSM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,54.62,null,0.305,0.21,0.38,119.02184117999998]
["SL_UPGR",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_UPGR1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_UPGR2",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_UTR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_UTR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_UTR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_UTR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_UTR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_UTR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_UTR1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,54.62,0,0.305,0.21,0.38,119.02184117999998]
["SL_UTR1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,54.62,0.026,0.305,0.21,0.38,122.11640905067998]
["SL_UTR1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,54.62,0.052676,0.305,0.21,0.38,125.29143568599764]
["SL_UTR1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,54.62,0.08004558,0.305,0.21,0.38,128.54901348992095]
["SL_UTR2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC238991",null,54.62,0.023,0.305,0.21,0.38,121.75934352713996]
["SL_UTR2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC239356",null,54.62,0.046529,0.305,0.21,0.38,124.5598084282642]
["SL_UTR2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC239722",null,54.62,0.070599,0.305,0.21,0.38,127.42466414546679]
["SL_UTR2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2009-10-01","ESC240087",null,54.62,0.095223,0.305,0.21,0.38,130.35545796268312]
["SL_UTR2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2010-10-01","ESC240452",null,54.62,0.120413,0.305,0.21,0.38,133.35361814200732]
["SL_UTR2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2011-10-01","ESC240817",null,54.62,0.120413,0.305,0.21,0.38,133.35361814200732]
["SL_UTR2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN3","2012-10-01","ESC241183",null,54.62,null,0.305,0.21,0.38,119.02184117999998]
["SPR",{"$nulls":5},"",{"$nulls":6},0]
[null,"END",{"$nulls":4},"END",{"$nulls":6},0]

{"sheet":"tecclc","index":2,"n_rows":2599,"n_cols":15,"rows_kept":2599,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["TEC4CLC ","TEC4CLC ","TEC4CLC ","TEC4CLC ","TEC4CLC ","TEC4CLC ","TEC4CLC ","TEC4CLC ","TEC4CLC ","TEC4CLC ","TEC4CLC ","TEC4CLC ","TEC4CLC ","TEC4CLC "]
["AA_MSEG","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AA_MSEG","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AA_MSEG","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AA_MSEG","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AA_MSEG","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AA_MSEG","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AA_MSEG1","ESC1","AN_OH3",null,null,"2005-10-01","ESC138626",null,1,0,0,null,null,1]
["AA_MSEG1","ESC1","AN_OH3",null,null,"2006-10-01","ESC138991",null,1,0.026,0,null,null,1.026]
["AA_MSEG1","ESC1","AN_OH3",null,null,"2007-10-01","ESC139356",null,1,0.052676,0,null,null,1.052676]
["AA_MSEG1","ESC1","AN_OH3",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0,null,null,1.08004558]
["AA_MSEG2","ESC2","AN_OH3",null,null,"2006-10-01","ESC238991",null,1,0.023,0,null,null,1.023]
["AA_MSEG2","ESC2","AN_OH3",null,null,"2007-10-01","ESC239356",null,1,0.046529,0,null,null,1.046529]
["AA_MSEG2","ESC2","AN_OH3",null,null,"2008-10-01","ESC239722",null,1,0.070599,0,null,null,1.070599]
["AA_MSEG2","ESC2","AN_OH3",null,null,"2009-10-01","ESC240087",null,1,0.095223,0,null,null,1.095223]
["AA_MSEG2","ESC2","AN_OH3",null,null,"2010-10-01","ESC240452",null,1,0.120413,0,null,null,1.120413]
["AA_MSEG2","ESC2","AN_OH3",null,null,"2011-10-01","ESC240817",null,1,0.120413,0,null,null,1.120413]
["AA_MSEG2","ESC2","AN_OH3",null,null,"2012-10-01","ESC241183",null,1,null,0,null,null,1]
["AA_MSEQ","ESC","AN_OH4",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AA_MSEQ","ESC","AN_OH4",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AA_MSEQ","ESC","AN_OH4",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AA_MSEQ","ESC","AN_OH4",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AA_MSEQ","ESC","AN_OH4",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AA_MSEQ","ESC","AN_OH4",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AA_MSEQ1","ESC1","AN_OH4",null,null,"2005-10-01","ESC138626",null,1,0,0,null,null,1]
["AA_MSEQ1","ESC1","AN_OH4",null,null,"2006-10-01","ESC138991",null,1,0.026,0,null,null,1.026]
["AA_MSEQ1","ESC1","AN_OH4",null,null,"2007-10-01","ESC139356",null,1,0.052676,0,null,null,1.052676]
["AA_MSEQ1","ESC1","AN_OH4",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0,null,null,1.08004558]
["AA_MSEQ2","ESC2","AN_OH4",null,null,"2006-10-01","ESC238991",null,1,0.023,0,null,null,1.023]
["AA_MSEQ2","ESC2","AN_OH4",null,null,"2007-10-01","ESC239356",null,1,0.046529,0,null,null,1.046529]
["AA_MSEQ2","ESC2","AN_OH4",null,null,"2008-10-01","ESC239722",null,1,0.070599,0,null,null,1.070599]
["AA_MSEQ2","ESC2","AN_OH4",null,null,"2009-10-01","ESC240087",null,1,0.095223,0,null,null,1.095223]
["AA_MSEQ2","ESC2","AN_OH4",null,null,"2010-10-01","ESC240452",null,1,0.120413,0,null,null,1.120413]
["AA_MSEQ2","ESC2","AN_OH4",null,null,"2011-10-01","ESC240817",null,1,0.120413,0,null,null,1.120413]
["AA_MSEQ2","ESC2","AN_OH4",null,null,"2012-10-01","ESC241183",null,1,null,0,null,null,1]
["AA_MSPS","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,null,0,0,null,null,0]
["AA_MSPS","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,null,0.029,0,null,null,0]
["AA_MSPS","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,null,0.057812,0,null,null,0]
["AA_MSPS","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,null,0.085315,0,null,null,0]
["AA_MSPS","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,null,0.113533,0,null,null,0]
["AA_MSPS","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,null,0.142485,0,null,null,0]
["AA_MSSC","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AA_MSSC","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AA_MSSC","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AA_MSSC","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AA_MSSC","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AA_MSSC","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AA_MSSC1","ESC1","AN_OH3",null,null,"2005-10-01","ESC138626",null,1,0,0,null,null,1]
["AA_MSSC1","ESC1","AN_OH3",null,null,"2006-10-01","ESC138991",null,1,0.026,0,null,null,1.026]
["AA_MSSC1","ESC1","AN_OH3",null,null,"2007-10-01","ESC139356",null,1,0.052676,0,null,null,1.052676]
["AA_MSSC1","ESC1","AN_OH3",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0,null,null,1.08004558]
["AA_MSSC2","ESC2","AN_OH3",null,null,"2006-10-01","ESC238991",null,1,0.023,0,null,null,1.023]
["AA_MSSC2","ESC2","AN_OH3",null,null,"2007-10-01","ESC239356",null,1,0.046529,0,null,null,1.046529]
["AA_MSSC2","ESC2","AN_OH3",null,null,"2008-10-01","ESC239722",null,1,0.070599,0,null,null,1.070599]
["AA_MSSC2","ESC2","AN_OH3",null,null,"2009-10-01","ESC240087",null,1,0.095223,0,null,null,1.095223]
["AA_MSSC2","ESC2","AN_OH3",null,null,"2010-10-01","ESC240452",null,1,0.120413,0,null,null,1.120413]
["AA_MSSC2","ESC2","AN_OH3",null,null,"2011-10-01","ESC240817",null,1,0.120413,0,null,null,1.120413]
["AA_MSSC2","ESC2","AN_OH3",null,null,"2012-10-01","ESC241183",null,1,null,0,null,null,1]
["AA_MSSF","AN_OH3",{"$nulls":4},"AN_OH3",null,1,{"$nulls":4},1]
["AA_MSSF1","AN_OH3",{"$nulls":4},"AN_OH3",null,1,{"$nulls":4},1]
["AA_MSSF2","AN_OH3",{"$nulls":4},"AN_OH3",null,1,{"$nulls":4},1]
["AA_MSXX","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["AA_MSXX","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["AA_MSXX","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["AA_MSXX","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["AA_MSXX","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["AA_MSXX","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["AN_ADMN","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,63.24,0,0.3224,null,null,83.62857600000001]
["AN_ADMN","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,63.24,0.029,0.3224,null,null,86.053804704]
["AN_ADMN","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,63.24,0.057812,0.3224,null,null,88.463311235712]
["AN_ADMN","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,63.24,0.085315,0.3224,null,null,90.76334796144]
["AN_ADMN","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,63.24,0.113533,0.3224,null,null,93.12317911900799]
["AN_ADMN","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,63.24,0.142485,0.3224,null,null,95.54439365136]
["AN_ADMN1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.257,0.026,0,107.70134382000002]
["AN_ADMN1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.257,0.026,0,110.50157875932003]
["AN_ADMN1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.257,0.026,0,113.37461980706233]
["AN_ADMN1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.257,0.026,0,116.32236035285133]
["AN_ADMN2","ESC2","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC238991",null,83.51,0.023,0.257,0.026,0,110.17847472786002]
["AN_ADMN2","ESC2","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC239356",null,83.51,0.046529,0.257,0.026,0,112.7125796466008]
["AN_ADMN2","ESC2","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC239722",null,83.51,0.070599,0.257,0.026,0,115.30495099234821]
["AN_ADMN2","ESC2","AN_CS1","AN_GA1","AN_OH4","2009-10-01","ESC240087",null,83.51,0.095223,0.257,0.026,0,117.95698888257189]
["AN_ADMN2","ESC2","AN_CS1","AN_GA1","AN_OH4","2010-10-01","ESC240452",null,83.51,0.120413,0.257,0.026,0,120.66998573339768]
["AN_ADMN2","ESC2","AN_CS1","AN_GA1","AN_OH4","2011-10-01","ESC240817",null,83.51,0.120413,0.257,0.026,0,120.66998573339768]
["AN_ADMN2","ESC2","AN_CS1","AN_GA1","AN_OH4","2012-10-01","ESC241183",null,83.51,null,0.257,0.026,0,107.70134382000002]
["AN_AW1","ESC1","AN_OH3",null,null,"2005-10-01","ESC138626",null,1,0,0,null,null,1]
["AN_AW1","ESC1","AN_OH3",null,null,"2006-10-01","ESC138991",null,1,0.026,0,null,null,1.026]
["AN_AW1","ESC1","AN_OH3",null,null,"2007-10-01","ESC139356",null,1,0.052676,0,null,null,1.052676]
["AN_AW1","ESC1","AN_OH3",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0,null,null,1.08004558]
["AN_AW2","ESC2","AN_OH3",null,null,"2006-10-01","ESC238991",null,1,0.023,0,null,null,1.023]
["AN_AW2","ESC2","AN_OH3",null,null,"2007-10-01","ESC239356",null,1,0.046529,0,null,null,1.046529]
["AN_AW2","ESC2","AN_OH3",null,null,"2008-10-01","ESC239722",null,1,0.070599,0,null,null,1.070599]
["AN_AW2","ESC2","AN_OH3",null,null,"2009-10-01","ESC240087",null,1,0.095223,0,null,null,1.095223]
["AN_AW2","ESC2","AN_OH3",null,null,"2010-10-01","ESC240452",null,1,0.120413,0,null,null,1.120413]
["AN_AW2","ESC2","AN_OH3",null,null,"2011-10-01","ESC240817",null,1,0.120413,0,null,null,1.120413]
["AN_AW2","ESC2","AN_OH3",null,null,"2012-10-01","ESC241183",null,1,null,0,null,null,1]
["AN_AWARD","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AN_AWARD","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AN_AWARD","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AN_AWARD","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AN_AWARD","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AN_AWARD","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AN_AWFX","AN_OH3",{"$nulls":4},"AN_OH3",{"$nulls":6},0]
["AN_AWXX","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["AN_AWXX","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["AN_AWXX","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["AN_AWXX","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["AN_AWXX","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["AN_AWXX","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["AN_CCA","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,67.43,0,0.3224,null,null,89.16943200000001]
["AN_CCA","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,67.43,0.029,0.3224,null,null,91.75534552799999]
["AN_CCA","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,67.43,0.057812,0.3224,null,null,94.32449520278401]
["AN_CCA","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,67.43,0.085315,0.3224,null,null,96.77692209108002]
["AN_CCA","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,67.43,0.113533,0.3224,null,null,99.293105123256]
["AN_CCA","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,67.43,0.142485,0.3224,null,null,101.87473851852002]
["AN_CCA1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.257,0.026,0,107.70134382000002]
["AN_CCA1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.257,0.026,0,110.50157875932003]
["AN_CCA1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.257,0.026,0,113.37461980706233]
["AN_CCA1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.257,0.026,0,116.32236035285133]
["AN_CCA2","ESC2","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC238991",null,83.51,0.023,0.257,0.026,0,110.17847472786002]
["AN_CCA2","ESC2","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC239356",null,83.51,0.046529,0.257,0.026,0,112.7125796466008]
["AN_CCA2","ESC2","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC239722",null,83.51,0.070599,0.257,0.026,0,115.30495099234821]
["AN_CCA2","ESC2","AN_CS1","AN_GA1","AN_OH4","2009-10-01","ESC240087",null,83.51,0.095223,0.257,0.026,0,117.95698888257189]
["AN_CCA2","ESC2","AN_CS1","AN_GA1","AN_OH4","2010-10-01","ESC240452",null,83.51,0.120413,0.257,0.026,0,120.66998573339768]
["AN_CCA2","ESC2","AN_CS1","AN_GA1","AN_OH4","2011-10-01","ESC240817",null,83.51,0.120413,0.257,0.026,0,120.66998573339768]
["AN_CCA2","ESC2","AN_CS1","AN_GA1","AN_OH4","2012-10-01","ESC241183",null,83.51,null,0.257,0.026,0,107.70134382000002]
["AN_CE","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,67.43,0,0.3224,null,null,89.16943200000001]
["AN_CE","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,67.43,0.029,0.3224,null,null,91.75534552799999]
["AN_CE","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,67.43,0.057812,0.3224,null,null,94.32449520278401]
["AN_CE","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,67.43,0.085315,0.3224,null,null,96.77692209108002]
["AN_CE","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,67.43,0.113533,0.3224,null,null,99.293105123256]
["AN_CE","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,67.43,0.142485,0.3224,null,null,101.87473851852002]
["AN_CE1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.257,0.026,0,107.70134382000002]
["AN_CE1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.257,0.026,0,110.50157875932003]
["AN_CE1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.257,0.026,0,113.37461980706233]
["AN_CE1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.257,0.026,0,116.32236035285133]
["AN_CE2","ESC2","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC238991",null,83.51,0.023,0.257,0.026,0,110.17847472786002]
["AN_CE2","ESC2","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC239356",null,83.51,0.046529,0.257,0.026,0,112.7125796466008]
["AN_CE2","ESC2","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC239722",null,83.51,0.070599,0.257,0.026,0,115.30495099234821]
["AN_CE2","ESC2","AN_CS1","AN_GA1","AN_OH4","2009-10-01","ESC240087",null,83.51,0.095223,0.257,0.026,0,117.95698888257189]
["AN_CE2","ESC2","AN_CS1","AN_GA1","AN_OH4","2010-10-01","ESC240452",null,83.51,0.120413,0.257,0.026,0,120.66998573339768]
["AN_CE2","ESC2","AN_CS1","AN_GA1","AN_OH4","2011-10-01","ESC240817",null,83.51,0.120413,0.257,0.026,0,120.66998573339768]
["AN_CE2","ESC2","AN_CS1","AN_GA1","AN_OH4","2012-10-01","ESC241183",null,83.51,null,0.257,0.026,0,107.70134382000002]
["AN_CP","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,67.43,0,0.3224,null,null,89.16943200000001]
["AN_CP","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,67.43,0.029,0.3224,null,null,91.75534552799999]
["AN_CP","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,67.43,0.057812,0.3224,null,null,94.32449520278401]
["AN_CP","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,67.43,0.085315,0.3224,null,null,96.77692209108002]
["AN_CP","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,67.43,0.113533,0.3224,null,null,99.293105123256]
["AN_CP","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,67.43,0.142485,0.3224,null,null,101.87473851852002]
["AN_CP1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.257,0.026,0,107.70134382000002]
["AN_CP1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.257,0.026,0,110.50157875932003]
["AN_CP1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.257,0.026,0,113.37461980706233]
["AN_CP1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.257,0.026,0,116.32236035285133]
["AN_CP2","ESC2","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC238991",null,83.51,0.023,0.257,0.026,0,110.17847472786002]
["AN_CP2","ESC2","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC239356",null,83.51,0.046529,0.257,0.026,0,112.7125796466008]
["AN_CP2","ESC2","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC239722",null,83.51,0.070599,0.257,0.026,0,115.30495099234821]
["AN_CP2","ESC2","AN_CS1","AN_GA1","AN_OH4","2009-10-01","ESC240087",null,83.51,0.095223,0.257,0.026,0,117.95698888257189]
["AN_CP2","ESC2","AN_CS1","AN_GA1","AN_OH4","2010-10-01","ESC240452",null,83.51,0.120413,0.257,0.026,0,120.66998573339768]
["AN_CP2","ESC2","AN_CS1","AN_GA1","AN_OH4","2011-10-01","ESC240817",null,83.51,0.120413,0.257,0.026,0,120.66998573339768]
["AN_CP2","ESC2","AN_CS1","AN_GA1","AN_OH4","2012-10-01","ESC241183",null,83.51,null,0.257,0.026,0,107.70134382000002]
["AN_CT","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,42.99,0,0.3224,null,null,56.849976000000005]
["AN_CT","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,42.99,0.029,0.3224,null,null,58.498625303999994]
["AN_CT","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,42.99,0.057812,0.3224,null,null,60.136586812512]
["AN_CT","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,42.99,0.085315,0.3224,null,null,61.70013170244001]
["AN_CT","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,42.99,0.113533,0.3224,null,null,63.30432432520799]
["AN_CT","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,42.99,0.142485,0.3224,null,null,64.95024483036]
["AN_CT1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,49.03,0,0.257,0.026,0,63.23310846000001]
["AN_CT1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,49.03,0.026,0.257,0.026,0,64.87716927996]
["AN_CT1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,49.03,0.052676,0.257,0.026,0,66.56397568123896]
["AN_CT1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,49.03,0.08004558,0.257,0.026,0,68.2946393018836]
["AN_CT2","ESC2","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC238991",null,49.03,0.023,0.257,0.026,0,64.68746995458001]
["AN_CT2","ESC2","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC239356",null,49.03,0.046529,0.257,0.026,0,66.17528176353535]
["AN_CT2","ESC2","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC239722",null,49.03,0.070599,0.257,0.026,0,67.69730268416757]
["AN_CT2","ESC2","AN_CS1","AN_GA1","AN_OH4","2009-10-01","ESC240087",null,49.03,0.095223,0.257,0.026,0,69.2543547468866]
["AN_CT2","ESC2","AN_CS1","AN_GA1","AN_OH4","2010-10-01","ESC240452",null,49.03,0.120413,0.257,0.026,0,70.84719674899401]
["AN_CT2","ESC2","AN_CS1","AN_GA1","AN_OH4","2011-10-01","ESC240817",null,49.03,0.120413,0.257,0.026,0,70.84719674899401]
["AN_CT2","ESC2","AN_CS1","AN_GA1","AN_OH4","2012-10-01","ESC241183",null,49.03,null,0.257,0.026,0,63.23310846000001]
["AN_EE","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,67.43,0,0.3224,null,null,89.16943200000001]
["AN_EE","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,67.43,0.029,0.3224,null,null,91.75534552799999]
["AN_EE","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,67.43,0.057812,0.3224,null,null,94.32449520278401]
["AN_EE","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,67.43,0.085315,0.3224,null,null,96.77692209108002]
["AN_EE","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,67.43,0.113533,0.3224,null,null,99.293105123256]
["AN_EE","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,67.43,0.142485,0.3224,null,null,101.87473851852002]
["AN_EE1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.257,0.026,0,107.70134382000002]
["AN_EE1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.257,0.026,0,110.50157875932003]
["AN_EE1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.257,0.026,0,113.37461980706233]
["AN_EE1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.257,0.026,0,116.32236035285133]
["AN_EE2","ESC2","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC238991",null,83.51,0.023,0.257,0.026,0,110.17847472786002]
["AN_EE2","ESC2","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC239356",null,83.51,0.046529,0.257,0.026,0,112.7125796466008]
["AN_EE2","ESC2","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC239722",null,83.51,0.070599,0.257,0.026,0,115.30495099234821]
["AN_EE2","ESC2","AN_CS1","AN_GA1","AN_OH4","2009-10-01","ESC240087",null,83.51,0.095223,0.257,0.026,0,117.95698888257189]
["AN_EE2","ESC2","AN_CS1","AN_GA1","AN_OH4","2010-10-01","ESC240452",null,83.51,0.120413,0.257,0.026,0,120.66998573339768]
["AN_EE2","ESC2","AN_CS1","AN_GA1","AN_OH4","2011-10-01","ESC240817",null,83.51,0.120413,0.257,0.026,0,120.66998573339768]
["AN_EE2","ESC2","AN_CS1","AN_GA1","AN_OH4","2012-10-01","ESC241183",null,83.51,null,0.257,0.026,0,107.70134382000002]
["AN_MDD","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,42.99,0,0.3224,null,null,56.849976000000005]
["AN_MDD","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,42.99,0.029,0.3224,null,null,58.498625303999994]
["AN_MDD","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,42.99,0.057812,0.3224,null,null,60.136586812512]
["AN_MDD","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,42.99,0.085315,0.3224,null,null,61.70013170244001]
["AN_MDD","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,42.99,0.113533,0.3224,null,null,63.30432432520799]
["AN_MDD","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,42.99,0.142485,0.3224,null,null,64.95024483036]
["AN_MDD1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,49.03,0,0.257,0.026,0,63.23310846000001]
["AN_MDD1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,49.03,0.026,0.257,0.026,0,64.87716927996]
["AN_MDD1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,49.03,0.052676,0.257,0.026,0,66.56397568123896]
["AN_MDD1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,49.03,0.08004558,0.257,0.026,0,68.2946393018836]
["AN_MDD2","ESC2","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC238991",null,49.03,0.023,0.257,0.026,0,64.68746995458001]
["AN_MDD2","ESC2","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC239356",null,49.03,0.046529,0.257,0.026,0,66.17528176353535]
["AN_MDD2","ESC2","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC239722",null,49.03,0.070599,0.257,0.026,0,67.69730268416757]
["AN_MDD2","ESC2","AN_CS1","AN_GA1","AN_OH4","2009-10-01","ESC240087",null,49.03,0.095223,0.257,0.026,0,69.2543547468866]
["AN_MDD2","ESC2","AN_CS1","AN_GA1","AN_OH4","2010-10-01","ESC240452",null,49.03,0.120413,0.257,0.026,0,70.84719674899401]
["AN_MDD2","ESC2","AN_CS1","AN_GA1","AN_OH4","2011-10-01","ESC240817",null,49.03,0.120413,0.257,0.026,0,70.84719674899401]
["AN_MDD2","ESC2","AN_CS1","AN_GA1","AN_OH4","2012-10-01","ESC241183",null,49.03,null,0.257,0.026,0,63.23310846000001]
["AN_ME","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,63.24,0,0.3224,null,null,83.62857600000001]
["AN_ME","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,63.24,0.029,0.3224,null,null,86.053804704]
["AN_ME","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,63.24,0.057812,0.3224,null,null,88.463311235712]
["AN_ME","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,63.24,0.085315,0.3224,null,null,90.76334796144]
["AN_ME","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,63.24,0.113533,0.3224,null,null,93.12317911900799]
["AN_ME","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,63.24,0.142485,0.3224,null,null,95.54439365136]
["AN_ME1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.257,0.026,0,107.70134382000002]
["AN_ME1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.257,0.026,0,110.50157875932003]
["AN_ME1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.257,0.026,0,113.37461980706233]
["AN_ME1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.257,0.026,0,116.32236035285133]
["AN_ME2","ESC2","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC238991",null,83.51,0.023,0.257,0.026,0,110.17847472786002]
["AN_ME2","ESC2","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC239356",null,83.51,0.046529,0.257,0.026,0,112.7125796466008]
["AN_ME2","ESC2","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC239722",null,83.51,0.070599,0.257,0.026,0,115.30495099234821]
["AN_ME2","ESC2","AN_CS1","AN_GA1","AN_OH4","2009-10-01","ESC240087",null,83.51,0.095223,0.257,0.026,0,117.95698888257189]
["AN_ME2","ESC2","AN_CS1","AN_GA1","AN_OH4","2010-10-01","ESC240452",null,83.51,0.120413,0.257,0.026,0,120.66998573339768]
["AN_ME2","ESC2","AN_CS1","AN_GA1","AN_OH4","2011-10-01","ESC240817",null,83.51,0.120413,0.257,0.026,0,120.66998573339768]
["AN_ME2","ESC2","AN_CS1","AN_GA1","AN_OH4","2012-10-01","ESC241183",null,83.51,null,0.257,0.026,0,107.70134382000002]
["AN_MES","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,67.43,0,0.3224,null,null,89.16943200000001]
["AN_MES","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,67.43,0.029,0.3224,null,null,91.75534552799999]
["AN_MES","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,67.43,0.057812,0.3224,null,null,94.32449520278401]
["AN_MES","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,67.43,0.085315,0.3224,null,null,96.77692209108002]
["AN_MES","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,67.43,0.113533,0.3224,null,null,99.293105123256]
["AN_MES","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,67.43,0.142485,0.3224,null,null,101.87473851852002]
["AN_MES1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.257,0.026,0,107.70134382000002]
["AN_MES1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.257,0.026,0,110.50157875932003]
["AN_MES1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.257,0.026,0,113.37461980706233]
["AN_MES1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.257,0.026,0,116.32236035285133]
["AN_MES2","ESC2","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC238991",null,83.51,0.023,0.257,0.026,0,110.17847472786002]
["AN_MES2","ESC2","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC239356",null,83.51,0.046529,0.257,0.026,0,112.7125796466008]
["AN_MES2","ESC2","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC239722",null,83.51,0.070599,0.257,0.026,0,115.30495099234821]
["AN_MES2","ESC2","AN_CS1","AN_GA1","AN_OH4","2009-10-01","ESC240087",null,83.51,0.095223,0.257,0.026,0,117.95698888257189]
["AN_MES2","ESC2","AN_CS1","AN_GA1","AN_OH4","2010-10-01","ESC240452",null,83.51,0.120413,0.257,0.026,0,120.66998573339768]
["AN_MES2","ESC2","AN_CS1","AN_GA1","AN_OH4","2011-10-01","ESC240817",null,83.51,0.120413,0.257,0.026,0,120.66998573339768]
["AN_MES2","ESC2","AN_CS1","AN_GA1","AN_OH4","2012-10-01","ESC241183",null,83.51,null,0.257,0.026,0,107.70134382000002]
["AN_MFAT","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,42.51,0,0.2598,null,null,53.554097999999996]
["AN_MFAT","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,42.51,0.029,0.2598,null,null,55.10716684199999]
["AN_MFAT","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,42.51,0.057812,0.2598,null,null,56.650167513575994]
["AN_MFAT","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,42.51,0.085315,0.2598,null,null,58.12306587087]
["AN_MFAT","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,42.51,0.113533,0.2598,null,null,59.634255408234]
["AN_MFAT","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,42.51,0.142485,0.2598,null,null,61.18475365353]
["AN_MFAT1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,49.03,0,0.257,0.026,0,63.23310846000001]
["AN_MFAT1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,49.03,0.026,0.257,0.026,0,64.87716927996]
["AN_MFAT1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,49.03,0.052676,0.257,0.026,0,66.56397568123896]
["AN_MFAT1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,49.03,0.08004558,0.257,0.026,0,68.2946393018836]
["AN_MFAT2","ESC2","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC238991",null,49.03,0.023,0.257,0.026,0,64.68746995458001]
["AN_MFAT2","ESC2","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC239356",null,49.03,0.046529,0.257,0.026,0,66.17528176353535]
["AN_MFAT2","ESC2","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC239722",null,49.03,0.070599,0.257,0.026,0,67.69730268416757]
["AN_MFAT2","ESC2","AN_CS1","AN_GA1","AN_OH4","2009-10-01","ESC240087",null,49.03,0.095223,0.257,0.026,0,69.2543547468866]
["AN_MFAT2","ESC2","AN_CS1","AN_GA1","AN_OH4","2010-10-01","ESC240452",null,49.03,0.120413,0.257,0.026,0,70.84719674899401]
["AN_MFAT2","ESC2","AN_CS1","AN_GA1","AN_OH4","2011-10-01","ESC240817",null,49.03,0.120413,0.257,0.026,0,70.84719674899401]
["AN_MFAT2","ESC2","AN_CS1","AN_GA1","AN_OH4","2012-10-01","ESC241183",null,49.03,null,0.257,0.026,0,63.23310846000001]
["AN_MFMS","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,53.97,0,0.2598,null,null,67.991406]
["AN_MFMS","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,53.97,0.029,0.2598,null,null,69.963156774]
["AN_MFMS","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,53.97,0.057812,0.2598,null,null,71.92212516367199]
["AN_MFMS","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,53.97,0.085315,0.2598,null,null,73.79209280289001]
["AN_MFMS","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,53.97,0.113533,0.2598,null,null,75.71067429739799]
["AN_MFMS","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,53.97,0.142485,0.2598,null,null,77.67916148391001]
["AN_MFMS1","ESC1","AN_CS2","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,81,0,0.196,0.026,0,99.394776]
["AN_MFMS1","ESC1","AN_CS2","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,81,0.026,0.196,0.026,0,101.97904017600001]
["AN_MFMS1","ESC1","AN_CS2","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,81,0.052676,0.196,0.026,0,104.630495220576]
["AN_MFMS1","ESC1","AN_CS2","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,81,0.08004558,0.196,0.026,0,107.35088849389007]
["AN_MFMS2","ESC2","AN_CS2","AN_GA1","AN_OH4","2006-10-01","ESC238991",null,81,0.023,0.196,0.026,0,101.680855848]
["AN_MFMS2","ESC2","AN_CS2","AN_GA1","AN_OH4","2007-10-01","ESC239356",null,81,0.046529,0.196,0.026,0,104.019515532504]
["AN_MFMS2","ESC2","AN_CS2","AN_GA1","AN_OH4","2008-10-01","ESC239722",null,81,0.070599,0.196,0.026,0,106.411947790824]
["AN_MFMS2","ESC2","AN_CS2","AN_GA1","AN_OH4","2009-10-01","ESC240087",null,81,0.095223,0.196,0.026,0,108.859444755048]
["AN_MFMS2","ESC2","AN_CS2","AN_GA1","AN_OH4","2010-10-01","ESC240452",null,81,0.120413,0.196,0.026,0,111.36319916248802]
["AN_MFMS2","ESC2","AN_CS2","AN_GA1","AN_OH4","2011-10-01","ESC240817",null,81,0.120413,0.196,0.026,0,111.36319916248802]
["AN_MFMS2","ESC2","AN_CS2","AN_GA1","AN_OH4","2012-10-01","ESC241183",null,81,null,0.196,0.026,0,99.394776]
["AN_MFPC","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.2598,null,null,0]
["AN_MFPC","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.2598,null,null,0]
["AN_MFPC","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.2598,null,null,0]
["AN_MFPC","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.2598,null,null,0]
["AN_MFPC","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.2598,null,null,0]
["AN_MFPC","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.2598,null,null,0]
["AN_MSCS","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AN_MSCS","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AN_MSCS","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AN_MSCS","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AN_MSCS","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AN_MSCS","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AN_MSCS1","ESC1","AN_OH3",null,null,"2005-10-01","ESC138626",null,1,0,0,null,null,1]
["AN_MSCS1","ESC1","AN_OH3",null,null,"2006-10-01","ESC138991",null,1,0.026,0,null,null,1.026]
["AN_MSCS1","ESC1","AN_OH3",null,null,"2007-10-01","ESC139356",null,1,0.052676,0,null,null,1.052676]
["AN_MSCS1","ESC1","AN_OH3",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0,null,null,1.08004558]
["AN_MSCS2","ESC2","AN_OH3",null,null,"2006-10-01","ESC238991",null,1,0.023,0,null,null,1.023]
["AN_MSCS2","ESC2","AN_OH3",null,null,"2007-10-01","ESC239356",null,1,0.046529,0,null,null,1.046529]
["AN_MSCS2","ESC2","AN_OH3",null,null,"2008-10-01","ESC239722",null,1,0.070599,0,null,null,1.070599]
["AN_MSCS2","ESC2","AN_OH3",null,null,"2009-10-01","ESC240087",null,1,0.095223,0,null,null,1.095223]
["AN_MSCS2","ESC2","AN_OH3",null,null,"2010-10-01","ESC240452",null,1,0.120413,0,null,null,1.120413]
["AN_MSCS2","ESC2","AN_OH3",null,null,"2011-10-01","ESC240817",null,1,0.120413,0,null,null,1.120413]
["AN_MSCS2","ESC2","AN_OH3",null,null,"2012-10-01","ESC241183",null,1,null,0,null,null,1]
["AN_MSEG","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AN_MSEG","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AN_MSEG","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AN_MSEG","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AN_MSEG","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AN_MSEG","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AN_MSEG1","ESC1","AN_OH3",null,null,"2005-10-01","ESC138626",null,1,0,0,null,null,1]
["AN_MSEG1","ESC1","AN_OH3",null,null,"2006-10-01","ESC138991",null,1,0.026,0,null,null,1.026]
["AN_MSEG1","ESC1","AN_OH3",null,null,"2007-10-01","ESC139356",null,1,0.052676,0,null,null,1.052676]
["AN_MSEG1","ESC1","AN_OH3",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0,null,null,1.08004558]
["AN_MSEG2","ESC2","AN_OH3",null,null,"2006-10-01","ESC238991",null,1,0.023,0,null,null,1.023]
["AN_MSEG2","ESC2","AN_OH3",null,null,"2007-10-01","ESC239356",null,1,0.046529,0,null,null,1.046529]
["AN_MSEG2","ESC2","AN_OH3",null,null,"2008-10-01","ESC239722",null,1,0.070599,0,null,null,1.070599]
["AN_MSEG2","ESC2","AN_OH3",null,null,"2009-10-01","ESC240087",null,1,0.095223,0,null,null,1.095223]
["AN_MSEG2","ESC2","AN_OH3",null,null,"2010-10-01","ESC240452",null,1,0.120413,0,null,null,1.120413]
["AN_MSEG2","ESC2","AN_OH3",null,null,"2011-10-01","ESC240817",null,1,0.120413,0,null,null,1.120413]
["AN_MSEG2","ESC2","AN_OH3",null,null,"2012-10-01","ESC241183",null,1,null,0,null,null,1]
["AN_MSEQ","ESC","AN_OH4",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AN_MSEQ","ESC","AN_OH4",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AN_MSEQ","ESC","AN_OH4",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AN_MSEQ","ESC","AN_OH4",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AN_MSEQ","ESC","AN_OH4",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AN_MSEQ","ESC","AN_OH4",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AN_MSEQ1","ESC1","AN_OH4",null,null,"2005-10-01","ESC138626",null,1,0,0,null,null,1]
["AN_MSEQ1","ESC1","AN_OH4",null,null,"2006-10-01","ESC138991",null,1,0.026,0,null,null,1.026]
["AN_MSEQ1","ESC1","AN_OH4",null,null,"2007-10-01","ESC139356",null,1,0.052676,0,null,null,1.052676]
["AN_MSEQ1","ESC1","AN_OH4",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0,null,null,1.08004558]
["AN_MSEQ2","ESC2","AN_OH4",null,null,"2006-10-01","ESC238991",null,1,0.023,0,null,null,1.023]
["AN_MSEQ2","ESC2","AN_OH4",null,null,"2007-10-01","ESC239356",null,1,0.046529,0,null,null,1.046529]
["AN_MSEQ2","ESC2","AN_OH4",null,null,"2008-10-01","ESC239722",null,1,0.070599,0,null,null,1.070599]
["AN_MSEQ2","ESC2","AN_OH4",null,null,"2009-10-01","ESC240087",null,1,0.095223,0,null,null,1.095223]
["AN_MSEQ2","ESC2","AN_OH4",null,null,"2010-10-01","ESC240452",null,1,0.120413,0,null,null,1.120413]
["AN_MSEQ2","ESC2","AN_OH4",null,null,"2011-10-01","ESC240817",null,1,0.120413,0,null,null,1.120413]
["AN_MSEQ2","ESC2","AN_OH4",null,null,"2012-10-01","ESC241183",null,1,null,0,null,null,1]
["AN_MSPS","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AN_MSPS","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AN_MSPS","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AN_MSPS","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AN_MSPS","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AN_MSPS","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AN_MSPS1","ESC1","AN_OH3",null,null,"2005-10-01","ESC138626",null,1,0,0,null,null,1]
["AN_MSPS1","ESC1","AN_OH3",null,null,"2006-10-01","ESC138991",null,1,0.026,0,null,null,1.026]
["AN_MSPS1","ESC1","AN_OH3",null,null,"2007-10-01","ESC139356",null,1,0.052676,0,null,null,1.052676]
["AN_MSPS1","ESC1","AN_OH3",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0,null,null,1.08004558]
["AN_MSPS2","ESC2","AN_OH3",null,null,"2006-10-01","ESC238991",null,1,0.023,0,null,null,1.023]
["AN_MSPS2","ESC2","AN_OH3",null,null,"2007-10-01","ESC239356",null,1,0.046529,0,null,null,1.046529]
["AN_MSPS2","ESC2","AN_OH3",null,null,"2008-10-01","ESC239722",null,1,0.070599,0,null,null,1.070599]
["AN_MSPS2","ESC2","AN_OH3",null,null,"2009-10-01","ESC240087",null,1,0.095223,0,null,null,1.095223]
["AN_MSPS2","ESC2","AN_OH3",null,null,"2010-10-01","ESC240452",null,1,0.120413,0,null,null,1.120413]
["AN_MSPS2","ESC2","AN_OH3",null,null,"2011-10-01","ESC240817",null,1,0.120413,0,null,null,1.120413]
["AN_MSPS2","ESC2","AN_OH3",null,null,"2012-10-01","ESC241183",null,1,null,0,null,null,1]
["AN_MSSC","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AN_MSSC","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AN_MSSC","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AN_MSSC","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AN_MSSC","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AN_MSSC","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AN_MSSC1","ESC1","AN_OH3",null,null,"2005-10-01","ESC138626",null,1,0,0,null,null,1]
["AN_MSSC1","ESC1","AN_OH3",null,null,"2006-10-01","ESC138991",null,1,0.026,0,null,null,1.026]
["AN_MSSC1","ESC1","AN_OH3",null,null,"2007-10-01","ESC139356",null,1,0.052676,0,null,null,1.052676]
["AN_MSSC1","ESC1","AN_OH3",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0,null,null,1.08004558]
["AN_MSSC2","ESC2","AN_OH3",null,null,"2006-10-01","ESC238991",null,1,0.023,0,null,null,1.023]
["AN_MSSC2","ESC2","AN_OH3",null,null,"2007-10-01","ESC239356",null,1,0.046529,0,null,null,1.046529]
["AN_MSSC2","ESC2","AN_OH3",null,null,"2008-10-01","ESC239722",null,1,0.070599,0,null,null,1.070599]
["AN_MSSC2","ESC2","AN_OH3",null,null,"2009-10-01","ESC240087",null,1,0.095223,0,null,null,1.095223]
["AN_MSSC2","ESC2","AN_OH3",null,null,"2010-10-01","ESC240452",null,1,0.120413,0,null,null,1.120413]
["AN_MSSC2","ESC2","AN_OH3",null,null,"2011-10-01","ESC240817",null,1,0.120413,0,null,null,1.120413]
["AN_MSSC2","ESC2","AN_OH3",null,null,"2012-10-01","ESC241183",null,1,null,0,null,null,1]
["AN_MSSF","AN_OH3",{"$nulls":4},"AN_OH3",null,1,{"$nulls":4},1]
["AN_MSSF1","AN_OH3",{"$nulls":4},"AN_OH3",null,1,{"$nulls":4},1]
["AN_MSSF2","AN_OH3",{"$nulls":4},"AN_OH3",null,1,{"$nulls":4},1]
["AN_MSTR","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,1,0,0.3224,null,null,1.3224]
["AN_MSTR","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,1,0.029,0.3224,null,null,1.3607496]
["AN_MSTR","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.3224,null,null,1.3988505888]
["AN_MSTR","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.3224,null,null,1.435220556]
["AN_MSTR","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.3224,null,null,1.4725360392]
["AN_MSTR","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.3224,null,null,1.510822164]
["AN_MSTR1","ESC1","AN_OH1",null,null,"2005-10-01","ESC138626",null,1.29,0,0.3224,null,null,1.705896]
["AN_MSTR1","ESC1","AN_OH1",null,null,"2006-10-01","ESC138991",null,1.29,0.026,0.3224,null,null,1.7502492960000002]
["AN_MSTR1","ESC1","AN_OH1",null,null,"2007-10-01","ESC139356",null,1.29,0.052676,0.3224,null,null,1.795755777696]
["AN_MSTR1","ESC1","AN_OH1",null,null,"2008-10-01","ESC139722",null,1.29,0.08004558,0.3224,null,null,1.84244543473968]
["AN_MSTR2","ESC2","AN_OH1",null,null,"2006-10-01","ESC238991",null,1.29,0.023,0.3224,null,null,1.745131608]
["AN_MSTR2","ESC2","AN_OH1",null,null,"2007-10-01","ESC239356",null,1.29,0.046529,0.3224,null,null,1.785269634984]
["AN_MSTR2","ESC2","AN_OH1",null,null,"2008-10-01","ESC239722",null,1.29,0.070599,0.3224,null,null,1.8263305517040003]
["AN_MSTR2","ESC2","AN_OH1",null,null,"2009-10-01","ESC240087",null,1.29,0.095223,0.3224,null,null,1.868336534808]
["AN_MSTR2","ESC2","AN_OH1",null,null,"2010-10-01","ESC240452",null,1.29,0.120413,0.3224,null,null,1.9113080550480004]
["AN_MSTR2","ESC2","AN_OH1",null,null,"2011-10-01","ESC240817",null,1.29,0.120413,0.3224,null,null,1.9113080550480004]
["AN_MSTR2","ESC2","AN_OH1",null,null,"2012-10-01","ESC241183",null,1.29,null,0.3224,null,null,1.705896]
["AN_MSXX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["AN_MSXX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["AN_MSXX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["AN_MSXX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["AN_MSXX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["AN_MSXX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["AN_MSXX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["AN_MSXX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["AN_MSXX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["AN_MSXX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["AN_MSXX2","ESC2",null,null,null,"2006-10-01","ESC238991",null,1,0.023,null,null,null,1.023]
["AN_MSXX2","ESC2",null,null,null,"2007-10-01","ESC239356",null,1,0.046529,null,null,null,1.046529]
["AN_MSXX2","ESC2",null,null,null,"2008-10-01","ESC239722",null,1,0.070599,null,null,null,1.070599]
["AN_MSXX2","ESC2",null,null,null,"2009-10-01","ESC240087",null,1,0.095223,null,null,null,1.095223]
["AN_MSXX2","ESC2",null,null,null,"2010-10-01","ESC240452",null,1,0.120413,null,null,null,1.120413]
["AN_MSXX2","ESC2",null,null,null,"2011-10-01","ESC240817",null,1,0.120413,null,null,null,1.120413]
["AN_MSXX2","ESC2",null,null,null,"2012-10-01","ESC241183",null,1,{"$nulls":4},1]
["AN_MTRL","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AN_MTRL","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AN_MTRL","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AN_MTRL","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AN_MTRL","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AN_MTRL","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AN_MTRL1","ESC1","AN_OH3",null,null,"2005-10-01","ESC138626",null,1,0,0,null,null,1]
["AN_MTRL1","ESC1","AN_OH3",null,null,"2006-10-01","ESC138991",null,1,0.026,0,null,null,1.026]
["AN_MTRL1","ESC1","AN_OH3",null,null,"2007-10-01","ESC139356",null,1,0.052676,0,null,null,1.052676]
["AN_MTRL1","ESC1","AN_OH3",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0,null,null,1.08004558]
["AN_MTRL2","ESC2","AN_OH3",null,null,"2006-10-01","ESC238991",null,1,0.023,0,null,null,1.023]
["AN_MTRL2","ESC2","AN_OH3",null,null,"2007-10-01","ESC239356",null,1,0.046529,0,null,null,1.046529]
["AN_MTRL2","ESC2","AN_OH3",null,null,"2008-10-01","ESC239722",null,1,0.070599,0,null,null,1.070599]
["AN_MTRL2","ESC2","AN_OH3",null,null,"2009-10-01","ESC240087",null,1,0.095223,0,null,null,1.095223]
["AN_MTRL2","ESC2","AN_OH3",null,null,"2010-10-01","ESC240452",null,1,0.120413,0,null,null,1.120413]
["AN_MTRL2","ESC2","AN_OH3",null,null,"2011-10-01","ESC240817",null,1,0.120413,0,null,null,1.120413]
["AN_MTRL2","ESC2","AN_OH3",null,null,"2012-10-01","ESC241183",null,1,null,0,null,null,1]
["AN_MVE","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,63.24,0,0.3224,null,null,83.62857600000001]
["AN_MVE","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,63.24,0.029,0.3224,null,null,86.053804704]
["AN_MVE","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,63.24,0.057812,0.3224,null,null,88.463311235712]
["AN_MVE","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,63.24,0.085315,0.3224,null,null,90.76334796144]
["AN_MVE","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,63.24,0.113533,0.3224,null,null,93.12317911900799]
["AN_MVE","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,63.24,0.142485,0.3224,null,null,95.54439365136]
["AN_MVE1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.257,0.026,0,107.70134382000002]
["AN_MVE1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.257,0.026,0,110.50157875932003]
["AN_MVE1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.257,0.026,0,113.37461980706233]
["AN_MVE1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.257,0.026,0,116.32236035285133]
["AN_MVE2","ESC2","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC238991",null,83.51,0.023,0.257,0.026,0,110.17847472786002]
["AN_MVE2","ESC2","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC239356",null,83.51,0.046529,0.257,0.026,0,112.7125796466008]
["AN_MVE2","ESC2","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC239722",null,83.51,0.070599,0.257,0.026,0,115.30495099234821]
["AN_MVE2","ESC2","AN_CS1","AN_GA1","AN_OH4","2009-10-01","ESC240087",null,83.51,0.095223,0.257,0.026,0,117.95698888257189]
["AN_MVE2","ESC2","AN_CS1","AN_GA1","AN_OH4","2010-10-01","ESC240452",null,83.51,0.120413,0.257,0.026,0,120.66998573339768]
["AN_MVE2","ESC2","AN_CS1","AN_GA1","AN_OH4","2011-10-01","ESC240817",null,83.51,0.120413,0.257,0.026,0,120.66998573339768]
["AN_MVE2","ESC2","AN_CS1","AN_GA1","AN_OH4","2012-10-01","ESC241183",null,83.51,null,0.257,0.026,0,107.70134382000002]
["AN_PHH","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,45.68,0,0.3224,null,null,60.407232]
["AN_PHH","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,45.68,0.029,0.3224,null,null,62.159041728]
["AN_PHH","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,45.68,0.057812,0.3224,null,null,63.899494896384006]
["AN_PHH","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,45.68,0.085315,0.3224,null,null,65.56087499808]
["AN_PHH","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,45.68,0.113533,0.3224,null,null,67.265446270656]
["AN_PHH","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,45.68,0.142485,0.3224,null,null,69.01435645152]
["AN_PHH1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,45.68,0,0.257,0.026,0,58.912673760000004]
["AN_PHH1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,45.68,0.026,0.257,0.026,0,60.44440327776]
["AN_PHH1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,45.68,0.052676,0.257,0.026,0,62.01595776298176]
["AN_PHH1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,45.68,0.08004558,0.257,0.026,0,63.628372900469984]
["AN_PHH2","ESC2","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC238991",null,45.68,0.023,0.257,0.026,0,60.26766525648]
["AN_PHH2","ESC2","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC239356",null,45.68,0.046529,0.257,0.026,0,61.653821557379054]
["AN_PHH2","ESC2","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC239722",null,45.68,0.070599,0.257,0.026,0,63.07184961478225]
["AN_PHH2","ESC2","AN_CS1","AN_GA1","AN_OH4","2009-10-01","ESC240087",null,45.68,0.095223,0.257,0.026,0,64.52251529344849]
["AN_PHH2","ESC2","AN_CS1","AN_GA1","AN_OH4","2010-10-01","ESC240452",null,45.68,0.120413,0.257,0.026,0,66.00652554546289]
["AN_PHH2","ESC2","AN_CS1","AN_GA1","AN_OH4","2011-10-01","ESC240817",null,45.68,0.120413,0.257,0.026,0,66.00652554546289]
["AN_PHH2","ESC2","AN_CS1","AN_GA1","AN_OH4","2012-10-01","ESC241183",null,45.68,null,0.257,0.026,0,58.912673760000004]
["AN_PHPD","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,33.95,0,0.3224,null,null,44.895480000000006]
["AN_PHPD","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,33.95,0.029,0.3224,null,null,46.19744892]
["AN_PHPD","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,33.95,0.057812,0.3224,null,null,47.490977489760006]
["AN_PHPD","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,33.95,0.085315,0.3224,null,null,48.72573787620001]
["AN_PHPD","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,33.95,0.113533,0.3224,null,null,49.992598530840006]
["AN_PHPD","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,33.95,0.142485,0.3224,null,null,51.2924124678]
["AN_PHPD1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,37.26,0,0.257,0.026,0,48.053551320000004]
["AN_PHPD1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,37.26,0.026,0.257,0.026,0,49.30294365432]
["AN_PHPD1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,37.26,0.052676,0.257,0.026,0,50.584820189332326]
["AN_PHPD1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,37.26,0.08004558,0.257,0.026,0,51.900025706469165]
["AN_PHPD2","ESC2","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC238991",null,37.26,0.023,0.257,0.026,0,49.15878300036]
["AN_PHPD2","ESC2","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC239356",null,37.26,0.046529,0.257,0.026,0,50.289435009368276]
["AN_PHPD2","ESC2","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC239722",null,37.26,0.070599,0.257,0.026,0,51.446083989640684]
["AN_PHPD2","ESC2","AN_CS1","AN_GA1","AN_OH4","2009-10-01","ESC240087",null,37.26,0.095223,0.257,0.026,0,52.62935463734436]
["AN_PHPD2","ESC2","AN_CS1","AN_GA1","AN_OH4","2010-10-01","ESC240452",null,37.26,0.120413,0.257,0.026,0,53.83982359509516]
["AN_PHPD2","ESC2","AN_CS1","AN_GA1","AN_OH4","2011-10-01","ESC240817",null,37.26,0.120413,0.257,0.026,0,53.83982359509516]
["AN_PHPD2","ESC2","AN_CS1","AN_GA1","AN_OH4","2012-10-01","ESC241183",null,37.26,null,0.257,0.026,0,48.053551320000004]
["AN_PHS","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,63.24,0,0.3224,null,null,83.62857600000001]
["AN_PHS","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,63.24,0.029,0.3224,null,null,86.053804704]
["AN_PHS","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,63.24,0.057812,0.3224,null,null,88.463311235712]
["AN_PHS","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,63.24,0.085315,0.3224,null,null,90.76334796144]
["AN_PHS","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,63.24,0.113533,0.3224,null,null,93.12317911900799]
["AN_PHS","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,63.24,0.142485,0.3224,null,null,95.54439365136]
["AN_PHS1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.257,0.026,0,107.70134382000002]
["AN_PHS1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.257,0.026,0,110.50157875932003]
["AN_PHS1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.257,0.026,0,113.37461980706233]
["AN_PHS1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.257,0.026,0,116.32236035285133]
["AN_PHS2","ESC2","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC238991",null,83.51,0.023,0.257,0.026,0,110.17847472786002]
["AN_PHS2","ESC2","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC239356",null,83.51,0.046529,0.257,0.026,0,112.7125796466008]
["AN_PHS2","ESC2","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC239722",null,83.51,0.070599,0.257,0.026,0,115.30495099234821]
["AN_PHS2","ESC2","AN_CS1","AN_GA1","AN_OH4","2009-10-01","ESC240087",null,83.51,0.095223,0.257,0.026,0,117.95698888257189]
["AN_PHS2","ESC2","AN_CS1","AN_GA1","AN_OH4","2010-10-01","ESC240452",null,83.51,0.120413,0.257,0.026,0,120.66998573339768]
["AN_PHS2","ESC2","AN_CS1","AN_GA1","AN_OH4","2011-10-01","ESC240817",null,83.51,0.120413,0.257,0.026,0,120.66998573339768]
["AN_PHS2","ESC2","AN_CS1","AN_GA1","AN_OH4","2012-10-01","ESC241183",null,83.51,null,0.257,0.026,0,107.70134382000002]
["AN_PHSS","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,63.24,0,0.3224,null,null,83.62857600000001]
["AN_PHSS","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,63.24,0.029,0.3224,null,null,86.053804704]
["AN_PHSS","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,63.24,0.057812,0.3224,null,null,88.463311235712]
["AN_PHSS","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,63.24,0.085315,0.3224,null,null,90.76334796144]
["AN_PHSS","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,63.24,0.113533,0.3224,null,null,93.12317911900799]
["AN_PHSS","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,63.24,0.142485,0.3224,null,null,95.54439365136]
["AN_PHSS1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,63.24,0,0.257,0.026,0,81.55948968000001]
["AN_PHSS1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,63.24,0.026,0.257,0.026,0,83.68003641168002]
["AN_PHSS1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,63.24,0.052676,0.257,0.026,0,85.8557173583837]
["AN_PHSS1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,63.24,0.08004558,0.257,0.026,0,88.08796633593961]
["AN_PHSS2","ESC2","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC238991",null,63.24,0.023,0.257,0.026,0,83.43535794264001]
["AN_PHSS2","ESC2","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC239356",null,63.24,0.046529,0.257,0.026,0,85.35437117532074]
["AN_PHSS2","ESC2","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC239722",null,63.24,0.070599,0.257,0.026,0,87.31750809191833]
["AN_PHSS2","ESC2","AN_CS1","AN_GA1","AN_OH4","2009-10-01","ESC240087",null,63.24,0.095223,0.257,0.026,0,89.32582896579865]
["AN_PHSS2","ESC2","AN_CS1","AN_GA1","AN_OH4","2010-10-01","ESC240452",null,63.24,0.120413,0.257,0.026,0,91.38031251083785]
["AN_PHSS2","ESC2","AN_CS1","AN_GA1","AN_OH4","2011-10-01","ESC240817",null,63.24,0.120413,0.257,0.026,0,91.38031251083785]
["AN_PHSS2","ESC2","AN_CS1","AN_GA1","AN_OH4","2012-10-01","ESC241183",null,63.24,null,0.257,0.026,0,81.55948968000001]
["AN_PM","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,63.24,0,0.3224,null,null,83.62857600000001]
["AN_PM","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,63.24,0.029,0.3224,null,null,86.053804704]
["AN_PM","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,63.24,0.057812,0.3224,null,null,88.463311235712]
["AN_PM","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,63.24,0.085315,0.3224,null,null,90.76334796144]
["AN_PM","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,63.24,0.113533,0.3224,null,null,93.12317911900799]
["AN_PM","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,63.24,0.142485,0.3224,null,null,95.54439365136]
["AN_PM1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.257,0.026,0,107.70134382000002]
["AN_PM1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.257,0.026,0,110.50157875932003]
["AN_PM1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.257,0.026,0,113.37461980706233]
["AN_PM1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.257,0.026,0,116.32236035285133]
["AN_PM2","ESC2","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC238991",null,83.51,0.023,0.257,0.026,0,110.17847472786002]
["AN_PM2","ESC2","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC239356",null,83.51,0.046529,0.257,0.026,0,112.7125796466008]
["AN_PM2","ESC2","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC239722",null,83.51,0.070599,0.257,0.026,0,115.30495099234821]
["AN_PM2","ESC2","AN_CS1","AN_GA1","AN_OH4","2009-10-01","ESC240087",null,83.51,0.095223,0.257,0.026,0,117.95698888257189]
["AN_PM2","ESC2","AN_CS1","AN_GA1","AN_OH4","2010-10-01","ESC240452",null,83.51,0.120413,0.257,0.026,0,120.66998573339768]
["AN_PM2","ESC2","AN_CS1","AN_GA1","AN_OH4","2011-10-01","ESC240817",null,83.51,0.120413,0.257,0.026,0,120.66998573339768]
["AN_PM2","ESC2","AN_CS1","AN_GA1","AN_OH4","2012-10-01","ESC241183",null,83.51,null,0.257,0.026,0,107.70134382000002]
["AN_SEE","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,85,0,0.3224,null,null,112.404]
["AN_SEE","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,85,0.029,0.3224,null,null,115.663716]
["AN_SEE","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,85,0.057812,0.3224,null,null,118.90230004799999]
["AN_SEE","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,85,0.085315,0.3224,null,null,121.99374726000002]
["AN_SEE","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,85,0.113533,0.3224,null,null,125.16556333199999]
["AN_SEE","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,85,0.142485,0.3224,null,null,128.41988394]
["AN_SEE1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.257,0.026,0,107.70134382000002]
["AN_SEE1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.257,0.026,0,110.50157875932003]
["AN_SEE1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.257,0.026,0,113.37461980706233]
["AN_SEE1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.257,0.026,0,116.32236035285133]
["AN_SEE2","ESC2","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC238991",null,83.51,0.023,0.257,0.026,0,110.17847472786002]
["AN_SEE2","ESC2","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC239356",null,83.51,0.046529,0.257,0.026,0,112.7125796466008]
["AN_SEE2","ESC2","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC239722",null,83.51,0.070599,0.257,0.026,0,115.30495099234821]
["AN_SEE2","ESC2","AN_CS1","AN_GA1","AN_OH4","2009-10-01","ESC240087",null,83.51,0.095223,0.257,0.026,0,117.95698888257189]
["AN_SEE2","ESC2","AN_CS1","AN_GA1","AN_OH4","2010-10-01","ESC240452",null,83.51,0.120413,0.257,0.026,0,120.66998573339768]
["AN_SEE2","ESC2","AN_CS1","AN_GA1","AN_OH4","2011-10-01","ESC240817",null,83.51,0.120413,0.257,0.026,0,120.66998573339768]
["AN_SEE2","ESC2","AN_CS1","AN_GA1","AN_OH4","2012-10-01","ESC241183",null,83.51,null,0.257,0.026,0,107.70134382000002]
["AN_SEL","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,null,0,0.3224,null,null,0]
["AN_SEL","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,null,0.029,0.3224,null,null,0]
["AN_SEL","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.3224,null,null,0]
["AN_SEL","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.3224,null,null,0]
["AN_SEL","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.3224,null,null,0]
["AN_SEL","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.3224,null,null,0]
["AN_SEPM","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,null,0,0.3224,null,null,0]
["AN_SEPM","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,null,0.029,0.3224,null,null,0]
["AN_SEPM","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.3224,null,null,0]
["AN_SEPM","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.3224,null,null,0]
["AN_SEPM","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.3224,null,null,0]
["AN_SEPM","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.3224,null,null,0]
["AN_TMUC","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.2598,null,null,0]
["AN_TMUC","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.2598,null,null,0]
["AN_TMUC","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.2598,null,null,0]
["AN_TMUC","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.2598,null,null,0]
["AN_TMUC","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.2598,null,null,0]
["AN_TMUC","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.2598,null,null,0]
["AN_TMUE","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.2598,null,null,0]
["AN_TMUE","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.2598,null,null,0]
["AN_TMUE","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.2598,null,null,0]
["AN_TMUE","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.2598,null,null,0]
["AN_TMUE","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.2598,null,null,0]
["AN_TMUE","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.2598,null,null,0]
["AN_TMUI","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.2598,null,null,0]
["AN_TMUI","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.2598,null,null,0]
["AN_TMUI","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.2598,null,null,0]
["AN_TMUI","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.2598,null,null,0]
["AN_TMUI","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.2598,null,null,0]
["AN_TMUI","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.2598,null,null,0]
["AN_TMUO","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.2598,null,null,0]
["AN_TMUO","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.2598,null,null,0]
["AN_TMUO","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.2598,null,null,0]
["AN_TMUO","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.2598,null,null,0]
["AN_TMUO","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.2598,null,null,0]
["AN_TMUO","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.2598,null,null,0]
["AN_TMUP","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.2598,null,null,0]
["AN_TMUP","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.2598,null,null,0]
["AN_TMUP","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.2598,null,null,0]
["AN_TMUP","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.2598,null,null,0]
["AN_TMUP","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.2598,null,null,0]
["AN_TMUP","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.2598,null,null,0]
["AN_TMUW","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.2598,null,null,0]
["AN_TMUW","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.2598,null,null,0]
["AN_TMUW","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.2598,null,null,0]
["AN_TMUW","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.2598,null,null,0]
["AN_TMUW","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.2598,null,null,0]
["AN_TMUW","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.2598,null,null,0]
["BA",{"$nulls":5},"",null,1,{"$nulls":4},1]
["BASE",{"$nulls":5},"",null,1,{"$nulls":4},1]
["CNST",{"$nulls":5},"",{"$nulls":6},0]
["COMM",{"$nulls":5},"",{"$nulls":6},0]
["LA_MSCS","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,null,0,0.19,null,null,0]
["LA_MSCS","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,null,0.029,0.19,null,null,0]
["LA_MSCS","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.19,null,null,0]
["LA_MSCS","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.19,null,null,0]
["LA_MSCS","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.19,null,null,0]
["LA_MSCS","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.19,null,null,0]
["LA_MSCS1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,null,0,0.11,null,null,0]
["LA_MSCS1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,null,0.026,0.11,null,null,0]
["LA_MSCS1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,null,0.052676,0.11,null,null,0]
["LA_MSCS1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,null,0.08004558,0.11,null,null,0]
["LA_MSCS2","ESC2","LL_OH2",null,null,"2006-10-01","ESC238991",null,null,0.023,0.11,null,null,0]
["LA_MSCS2","ESC2","LL_OH2",null,null,"2007-10-01","ESC239356",null,null,0.046529,0.11,null,null,0]
["LA_MSCS2","ESC2","LL_OH2",null,null,"2008-10-01","ESC239722",null,null,0.070599,0.11,null,null,0]
["LA_MSCS2","ESC2","LL_OH2",null,null,"2009-10-01","ESC240087",null,null,0.095223,0.11,null,null,0]
["LA_MSCS2","ESC2","LL_OH2",null,null,"2010-10-01","ESC240452",null,null,0.120413,0.11,null,null,0]
["LA_MSCS2","ESC2","LL_OH2",null,null,"2011-10-01","ESC240817",null,null,0.120413,0.11,null,null,0]
["LA_MSCS2","ESC2","LL_OH2",null,null,"2012-10-01","ESC241183",null,null,null,0.11,null,null,0]
["LA_MSEG","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LA_MSEG","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LA_MSEG","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LA_MSEG","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LA_MSEG","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LA_MSEG","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LA_MSEG1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LA_MSEG1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LA_MSEG1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LA_MSEG1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LA_MSEG2","ESC2","LL_OH2",null,null,"2006-10-01","ESC238991",null,1,0.023,0.11,null,null,1.13553]
["LA_MSEG2","ESC2","LL_OH2",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.11,null,null,1.16164719]
["LA_MSEG2","ESC2","LL_OH2",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.11,null,null,1.1883648900000001]
["LA_MSEG2","ESC2","LL_OH2",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.11,null,null,1.2156975300000001]
["LA_MSEG2","ESC2","LL_OH2",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LA_MSEG2","ESC2","LL_OH2",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LA_MSEG2","ESC2","LL_OH2",null,null,"2012-10-01","ESC241183",null,1,null,0.11,null,null,1.11]
["LA_MSEQ","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LA_MSEQ","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LA_MSEQ","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LA_MSEQ","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LA_MSEQ","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LA_MSEQ","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LA_MSEQ1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LA_MSEQ1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LA_MSEQ1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LA_MSEQ1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LA_MSEQ2","ESC2","LL_OH2",null,null,"2006-10-01","ESC238991",null,1,0.023,0.11,null,null,1.13553]
["LA_MSEQ2","ESC2","LL_OH2",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.11,null,null,1.16164719]
["LA_MSEQ2","ESC2","LL_OH2",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.11,null,null,1.1883648900000001]
["LA_MSEQ2","ESC2","LL_OH2",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.11,null,null,1.2156975300000001]
["LA_MSEQ2","ESC2","LL_OH2",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LA_MSEQ2","ESC2","LL_OH2",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LA_MSEQ2","ESC2","LL_OH2",null,null,"2012-10-01","ESC241183",null,1,null,0.11,null,null,1.11]
["LA_MSPS","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,null,0,0.19,null,null,0]
["LA_MSPS","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,null,0.029,0.19,null,null,0]
["LA_MSPS","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.19,null,null,0]
["LA_MSPS","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.19,null,null,0]
["LA_MSPS","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.19,null,null,0]
["LA_MSPS","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.19,null,null,0]
["LA_MSSC","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LA_MSSC","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LA_MSSC","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LA_MSSC","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LA_MSSC","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LA_MSSC","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LA_MSSC1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LA_MSSC1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LA_MSSC1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LA_MSSC1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LA_MSSC2","ESC2","LL_OH2",null,null,"2006-10-01","ESC238991",null,1,0.023,0.11,null,null,1.13553]
["LA_MSSC2","ESC2","LL_OH2",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.11,null,null,1.16164719]
["LA_MSSC2","ESC2","LL_OH2",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.11,null,null,1.1883648900000001]
["LA_MSSC2","ESC2","LL_OH2",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.11,null,null,1.2156975300000001]
["LA_MSSC2","ESC2","LL_OH2",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LA_MSSC2","ESC2","LL_OH2",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LA_MSSC2","ESC2","LL_OH2",null,null,"2012-10-01","ESC241183",null,1,null,0.11,null,null,1.11]
["LA_MSSF","LL_OH",{"$nulls":4},"LL_OH",{"$nulls":6},0]
["LA_MSSX","LL_OH",{"$nulls":4},"LL_OH",{"$nulls":6},0]
["LA_MSXX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["LA_MSXX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["LA_MSXX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["LA_MSXX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["LA_MSXX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["LA_MSXX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["LA_MSXX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["LA_MSXX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["LA_MSXX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["LA_MSXX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["LA_MSXX2","ESC2",null,null,null,"2006-10-01","ESC238991",null,1,0.023,null,null,null,1.023]
["LA_MSXX2","ESC2",null,null,null,"2007-10-01","ESC239356",null,1,0.046529,null,null,null,1.046529]
["LA_MSXX2","ESC2",null,null,null,"2008-10-01","ESC239722",null,1,0.070599,null,null,null,1.070599]
["LA_MSXX2","ESC2",null,null,null,"2009-10-01","ESC240087",null,1,0.095223,null,null,null,1.095223]
["LA_MSXX2","ESC2",null,null,null,"2010-10-01","ESC240452",null,1,0.120413,null,null,null,1.120413]
["LA_MSXX2","ESC2",null,null,null,"2011-10-01","ESC240817",null,1,0.120413,null,null,null,1.120413]
["LA_MSXX2","ESC2",null,null,null,"2012-10-01","ESC241183",null,1,{"$nulls":4},1]
["LLNL_LABOR","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LLNL_LABOR","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LLNL_LABOR","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LLNL_LABOR","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LLNL_LABOR","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LLNL_LABOR","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LLNL_NON-LABOR","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,null,0,0.19,null,null,0]
["LLNL_NON-LABOR","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,null,0.029,0.19,null,null,0]
["LLNL_NON-LABOR","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.19,null,null,0]
["LLNL_NON-LABOR","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.19,null,null,0]
["LLNL_NON-LABOR","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.19,null,null,0]
["LLNL_NON-LABOR","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.19,null,null,0]
["LLNL_SHOPS","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LLNL_SHOPS","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LLNL_SHOPS","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LLNL_SHOPS","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LLNL_SHOPS","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LLNL_SHOPS","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LLNL_TRAVEL","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,null,0,0.19,null,null,0]
["LLNL_TRAVEL","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,null,0.029,0.19,null,null,0]
["LLNL_TRAVEL","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.19,null,null,0]
["LLNL_TRAVEL","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.19,null,null,0]
["LLNL_TRAVEL","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.19,null,null,0]
["LLNL_TRAVEL","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.19,null,null,0]
["LL_ADMN","ESC",null,null,null,"2003-10-01","ESC37895",null,134.15048076923077,0,null,null,null,134.15048076923077]
["LL_ADMN","ESC",null,null,null,"2004-10-01","ESC38261",null,134.15048076923077,0.029,null,null,null,138.04084471153845]
["LL_ADMN","ESC",null,null,null,"2005-10-01","ESC38626",null,134.15048076923077,0.057812,null,null,null,141.90598836346155]
["LL_ADMN","ESC",null,null,null,"2006-10-01","ESC38991",null,134.15048076923077,0.085315,null,null,null,145.59552903605768]
["LL_ADMN","ESC",null,null,null,"2007-10-01","ESC39356",null,134.15048076923077,0.113533,null,null,null,149.38098730240384]
["LL_ADMN","ESC",null,null,null,"2008-10-01","ESC39722",null,134.15048076923077,0.142485,null,null,null,153.26491202163461]
["LL_ADMN1","ESC1",null,null,null,"2005-10-01","ESC138626",null,134.15048076923077,0,null,null,null,134.15048076923077]
["LL_ADMN1","ESC1",null,null,null,"2006-10-01","ESC138991",null,134.15048076923077,0.026,null,null,null,137.63839326923076]
["LL_ADMN1","ESC1",null,null,null,"2007-10-01","ESC139356",null,134.15048076923077,0.052676,null,null,null,141.21699149423077]
["LL_ADMN1","ESC1",null,null,null,"2008-10-01","ESC139722",null,134.15048076923077,0.08004558,null,null,null,144.8886338096827]
["LL_ADMN2","ESC2",null,null,null,"2006-10-01","ESC238991",null,134.15048076923077,0.023,null,null,null,137.23594182692307]
["LL_ADMN2","ESC2",null,null,null,"2007-10-01","ESC239356",null,134.15048076923077,0.046529,null,null,null,140.3923684889423]
["LL_ADMN2","ESC2",null,null,null,"2008-10-01","ESC239722",null,134.15048076923077,0.070599,null,null,null,143.6213705610577]
["LL_ADMN2","ESC2",null,null,null,"2009-10-01","ESC240087",null,134.15048076923077,0.095223,null,null,null,146.92469199951924]
["LL_ADMN2","ESC2",null,null,null,"2010-10-01","ESC240452",null,134.15048076923077,0.120413,null,null,null,150.30394261009616]
["LL_ADMN2","ESC2",null,null,null,"2011-10-01","ESC240817",null,134.15048076923077,0.120413,null,null,null,150.30394261009616]
["LL_ADMN2","ESC2",null,null,null,"2012-10-01","ESC241183",null,134.15048076923077,{"$nulls":4},134.15048076923077]
["LL_AW1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LL_AW1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LL_AW1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LL_AW1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LL_AW2","ESC2","LL_OH2",null,null,"2006-10-01","ESC238991",null,1,0.023,0.11,null,null,1.13553]
["LL_AW2","ESC2","LL_OH2",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.11,null,null,1.16164719]
["LL_AW2","ESC2","LL_OH2",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.11,null,null,1.1883648900000001]
["LL_AW2","ESC2","LL_OH2",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.11,null,null,1.2156975300000001]
["LL_AW2","ESC2","LL_OH2",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LL_AW2","ESC2","LL_OH2",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LL_AW2","ESC2","LL_OH2",null,null,"2012-10-01","ESC241183",null,1,null,0.11,null,null,1.11]
["LL_AWARD","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LL_AWARD","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LL_AWARD","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LL_AWARD","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LL_AWARD","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LL_AWARD","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LL_AWFX",{"$nulls":5},"",{"$nulls":6},0]
["LL_AWFX1",{"$nulls":5},"",{"$nulls":6},0]
["LL_AWFX2",{"$nulls":5},"",{"$nulls":6},0]
["LL_AWFY",{"$nulls":5},"",{"$nulls":6},0]
["LL_AWFY1",{"$nulls":5},"",{"$nulls":6},0]
["LL_AWFY2",{"$nulls":5},"",{"$nulls":6},0]
["LL_AWXX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["LL_AWXX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["LL_AWXX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["LL_AWXX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["LL_AWXX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["LL_AWXX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["LL_AWXX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["LL_AWXX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["LL_AWXX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["LL_AWXX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["LL_AWXX2","ESC2",null,null,null,"2006-10-01","ESC238991",null,1,0.023,null,null,null,1.023]
["LL_AWXX2","ESC2",null,null,null,"2007-10-01","ESC239356",null,1,0.046529,null,null,null,1.046529]
["LL_AWXX2","ESC2",null,null,null,"2008-10-01","ESC239722",null,1,0.070599,null,null,null,1.070599]
["LL_AWXX2","ESC2",null,null,null,"2009-10-01","ESC240087",null,1,0.095223,null,null,null,1.095223]
["LL_AWXX2","ESC2",null,null,null,"2010-10-01","ESC240452",null,1,0.120413,null,null,null,1.120413]
["LL_AWXX2","ESC2",null,null,null,"2011-10-01","ESC240817",null,1,0.120413,null,null,null,1.120413]
["LL_AWXX2","ESC2",null,null,null,"2012-10-01","ESC241183",null,1,{"$nulls":4},1]
["LL_CCA","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_CCA","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_CCA","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_CCA","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_CCA","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_CCA","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_CE","ESC",null,null,null,"2003-10-01","ESC37895",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_CE","ESC",null,null,null,"2004-10-01","ESC38261",null,176.59423076923076,0.029,null,null,null,181.71546346153843]
["LL_CE","ESC",null,null,null,"2005-10-01","ESC38626",null,176.59423076923076,0.057812,null,null,null,186.80349643846154]
["LL_CE","ESC",null,null,null,"2006-10-01","ESC38991",null,176.59423076923076,0.085315,null,null,null,191.6603675673077]
["LL_CE","ESC",null,null,null,"2007-10-01","ESC39356",null,176.59423076923076,0.113533,null,null,null,196.64350357115381]
["LL_CE","ESC",null,null,null,"2008-10-01","ESC39722",null,176.59423076923076,0.142485,null,null,null,201.7562597403846]
["LL_CE1","ESC1",null,null,null,"2005-10-01","ESC138626",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_CE1","ESC1",null,null,null,"2006-10-01","ESC138991",null,176.59423076923076,0.026,null,null,null,181.18568076923077]
["LL_CE1","ESC1",null,null,null,"2007-10-01","ESC139356",null,176.59423076923076,0.052676,null,null,null,185.89650846923075]
["LL_CE1","ESC1",null,null,null,"2008-10-01","ESC139722",null,176.59423076923076,0.08004558,null,null,null,190.72981839580768]
["LL_CE2","ESC2",null,null,null,"2006-10-01","ESC238991",null,176.59423076923076,0.023,null,null,null,180.65589807692305]
["LL_CE2","ESC2",null,null,null,"2007-10-01","ESC239356",null,176.59423076923076,0.046529,null,null,null,184.8109837326923]
["LL_CE2","ESC2",null,null,null,"2008-10-01","ESC239722",null,176.59423076923076,0.070599,null,null,null,189.0616068673077]
["LL_CE2","ESC2",null,null,null,"2009-10-01","ESC240087",null,176.59423076923076,0.095223,null,null,null,193.41006320576923]
["LL_CE2","ESC2",null,null,null,"2010-10-01","ESC240452",null,176.59423076923076,0.120413,null,null,null,197.85847187884616]
["LL_CE2","ESC2",null,null,null,"2011-10-01","ESC240817",null,176.59423076923076,0.120413,null,null,null,197.85847187884616]
["LL_CE2","ESC2",null,null,null,"2012-10-01","ESC241183",null,176.59423076923076,{"$nulls":4},176.59423076923076]
["LL_CP","ESC",null,null,null,"2003-10-01","ESC37895",null,189.60865384615386,0,null,null,null,189.60865384615386]
["LL_CP","ESC",null,null,null,"2004-10-01","ESC38261",null,189.60865384615386,0.029,null,null,null,195.10730480769232]
["LL_CP","ESC",null,null,null,"2005-10-01","ESC38626",null,189.60865384615386,0.057812,null,null,null,200.5703093423077]
["LL_CP","ESC",null,null,null,"2006-10-01","ESC38991",null,189.60865384615386,0.085315,null,null,null,205.7851161490385]
["LL_CP","ESC",null,null,null,"2007-10-01","ESC39356",null,189.60865384615386,0.113533,null,null,null,211.13549314326923]
["LL_CP","ESC",null,null,null,"2008-10-01","ESC39722",null,189.60865384615386,0.142485,null,null,null,216.62504288942307]
["LL_CP1","ESC1",null,null,null,"2005-10-01","ESC138626",null,189.60865384615386,0,null,null,null,189.60865384615386]
["LL_CP1","ESC1",null,null,null,"2006-10-01","ESC138991",null,189.60865384615386,0.026,null,null,null,194.53847884615385]
["LL_CP1","ESC1",null,null,null,"2007-10-01","ESC139356",null,189.60865384615386,0.052676,null,null,null,199.59647929615386]
["LL_CP1","ESC1",null,null,null,"2008-10-01","ESC139722",null,189.60865384615386,0.08004558,null,null,null,204.78598851628846]
["LL_CP2","ESC2",null,null,null,"2006-10-01","ESC238991",null,189.60865384615386,0.023,null,null,null,193.96965288461539]
["LL_CP2","ESC2",null,null,null,"2007-10-01","ESC239356",null,189.60865384615386,0.046529,null,null,null,198.43095490096155]
["LL_CP2","ESC2",null,null,null,"2008-10-01","ESC239722",null,189.60865384615386,0.070599,null,null,null,202.99483519903848]
["LL_CP2","ESC2",null,null,null,"2009-10-01","ESC240087",null,189.60865384615386,0.095223,null,null,null,207.66375869134617]
["LL_CP2","ESC2",null,null,null,"2010-10-01","ESC240452",null,189.60865384615386,0.120413,null,null,null,212.4400006817308]
["LL_CP2","ESC2",null,null,null,"2011-10-01","ESC240817",null,189.60865384615386,0.120413,null,null,null,212.4400006817308]
["LL_CP2","ESC2",null,null,null,"2012-10-01","ESC241183",null,189.60865384615386,{"$nulls":4},189.60865384615386]
["LL_CT","ESC",null,null,null,"2003-10-01","ESC37895",null,137.21778846153848,0,null,null,null,137.21778846153848]
["LL_CT","ESC",null,null,null,"2004-10-01","ESC38261",null,137.21778846153848,0.029,null,null,null,141.19710432692307]
["LL_CT","ESC",null,null,null,"2005-10-01","ESC38626",null,137.21778846153848,0.057812,null,null,null,145.15062324807693]
["LL_CT","ESC",null,null,null,"2006-10-01","ESC38991",null,137.21778846153848,0.085315,null,null,null,148.92452408413465]
["LL_CT","ESC",null,null,null,"2007-10-01","ESC39356",null,137.21778846153848,0.113533,null,null,null,152.79653563894232]
["LL_CT","ESC",null,null,null,"2008-10-01","ESC39722",null,137.21778846153848,0.142485,null,null,null,156.76926505048078]
["LL_EE","ESC",null,null,null,"2003-10-01","ESC37895",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_EE","ESC",null,null,null,"2004-10-01","ESC38261",null,176.59423076923076,0.029,null,null,null,181.71546346153843]
["LL_EE","ESC",null,null,null,"2005-10-01","ESC38626",null,176.59423076923076,0.057812,null,null,null,186.80349643846154]
["LL_EE","ESC",null,null,null,"2006-10-01","ESC38991",null,176.59423076923076,0.085315,null,null,null,191.6603675673077]
["LL_EE","ESC",null,null,null,"2007-10-01","ESC39356",null,176.59423076923076,0.113533,null,null,null,196.64350357115381]
["LL_EE","ESC",null,null,null,"2008-10-01","ESC39722",null,176.59423076923076,0.142485,null,null,null,201.7562597403846]
["LL_EE1","ESC1",null,null,null,"2005-10-01","ESC138626",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_EE1","ESC1",null,null,null,"2006-10-01","ESC138991",null,176.59423076923076,0.026,null,null,null,181.18568076923077]
["LL_EE1","ESC1",null,null,null,"2007-10-01","ESC139356",null,176.59423076923076,0.052676,null,null,null,185.89650846923075]
["LL_EE1","ESC1",null,null,null,"2008-10-01","ESC139722",null,176.59423076923076,0.08004558,null,null,null,190.72981839580768]
["LL_EE2","ESC2",null,null,null,"2006-10-01","ESC238991",null,176.59423076923076,0.023,null,null,null,180.65589807692305]
["LL_EE2","ESC2",null,null,null,"2007-10-01","ESC239356",null,176.59423076923076,0.046529,null,null,null,184.8109837326923]
["LL_EE2","ESC2",null,null,null,"2008-10-01","ESC239722",null,176.59423076923076,0.070599,null,null,null,189.0616068673077]
["LL_EE2","ESC2",null,null,null,"2009-10-01","ESC240087",null,176.59423076923076,0.095223,null,null,null,193.41006320576923]
["LL_EE2","ESC2",null,null,null,"2010-10-01","ESC240452",null,176.59423076923076,0.120413,null,null,null,197.85847187884616]
["LL_EE2","ESC2",null,null,null,"2011-10-01","ESC240817",null,176.59423076923076,0.120413,null,null,null,197.85847187884616]
["LL_EE2","ESC2",null,null,null,"2012-10-01","ESC241183",null,176.59423076923076,{"$nulls":4},176.59423076923076]
["LL_KCA","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_KCA","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_KCA","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_KCA","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_KCA","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_KCA","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_KE","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_KE","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_KE","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_KE","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_KE","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_KE","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_KT","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_KT","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_KT","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_KT","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_KT","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_KT","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_MDD","ESC",null,null,null,"2003-10-01","ESC37895",null,162.0105769230769,0,null,null,null,162.0105769230769]
["LL_MDD","ESC",null,null,null,"2004-10-01","ESC38261",null,162.0105769230769,0.029,null,null,null,166.70888365384613]
["LL_MDD","ESC",null,null,null,"2005-10-01","ESC38626",null,162.0105769230769,0.057812,null,null,null,171.37673239615384]
["LL_MDD","ESC",null,null,null,"2006-10-01","ESC38991",null,162.0105769230769,0.085315,null,null,null,175.83250929326923]
["LL_MDD","ESC",null,null,null,"2007-10-01","ESC39356",null,162.0105769230769,0.113533,null,null,null,180.40412375288457]
["LL_MDD","ESC",null,null,null,"2008-10-01","ESC39722",null,162.0105769230769,0.142485,null,null,null,185.0946539759615]
["LL_MDD1","ESC1",null,null,null,"2005-10-01","ESC138626",null,162.0105769230769,0,null,null,null,162.0105769230769]
["LL_MDD1","ESC1",null,null,null,"2006-10-01","ESC138991",null,162.0105769230769,0.026,null,null,null,166.22285192307692]
["LL_MDD1","ESC1",null,null,null,"2007-10-01","ESC139356",null,162.0105769230769,0.052676,null,null,null,170.5446460730769]
["LL_MDD1","ESC1",null,null,null,"2008-10-01","ESC139722",null,162.0105769230769,0.08004558,null,null,null,174.9788075190192]
["LL_MDD2","ESC2",null,null,null,"2006-10-01","ESC238991",null,162.0105769230769,0.023,null,null,null,165.73682019230768]
["LL_MDD2","ESC2",null,null,null,"2007-10-01","ESC239356",null,162.0105769230769,0.046529,null,null,null,169.54876705673075]
["LL_MDD2","ESC2",null,null,null,"2008-10-01","ESC239722",null,162.0105769230769,0.070599,null,null,null,173.44836164326924]
["LL_MDD2","ESC2",null,null,null,"2009-10-01","ESC240087",null,162.0105769230769,0.095223,null,null,null,177.43771008942306]
["LL_MDD2","ESC2",null,null,null,"2010-10-01","ESC240452",null,162.0105769230769,0.120413,null,null,null,181.51875652211538]
["LL_MDD2","ESC2",null,null,null,"2011-10-01","ESC240817",null,162.0105769230769,0.120413,null,null,null,181.51875652211538]
["LL_MDD2","ESC2",null,null,null,"2012-10-01","ESC241183",null,162.0105769230769,{"$nulls":4},162.0105769230769]
["LL_ME","ESC",null,null,null,"2003-10-01","ESC37895",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_ME","ESC",null,null,null,"2004-10-01","ESC38261",null,176.59423076923076,0.029,null,null,null,181.71546346153843]
["LL_ME","ESC",null,null,null,"2005-10-01","ESC38626",null,176.59423076923076,0.057812,null,null,null,186.80349643846154]
["LL_ME","ESC",null,null,null,"2006-10-01","ESC38991",null,176.59423076923076,0.085315,null,null,null,191.6603675673077]
["LL_ME","ESC",null,null,null,"2007-10-01","ESC39356",null,176.59423076923076,0.113533,null,null,null,196.64350357115381]
["LL_ME","ESC",null,null,null,"2008-10-01","ESC39722",null,176.59423076923076,0.142485,null,null,null,201.7562597403846]
["LL_ME1","ESC1",null,null,null,"2005-10-01","ESC138626",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_ME1","ESC1",null,null,null,"2006-10-01","ESC138991",null,176.59423076923076,0.026,null,null,null,181.18568076923077]
["LL_ME1","ESC1",null,null,null,"2007-10-01","ESC139356",null,176.59423076923076,0.052676,null,null,null,185.89650846923075]
["LL_ME1","ESC1",null,null,null,"2008-10-01","ESC139722",null,176.59423076923076,0.08004558,null,null,null,190.72981839580768]
["LL_ME2","ESC2",null,null,null,"2006-10-01","ESC238991",null,176.59423076923076,0.023,null,null,null,180.65589807692305]
["LL_ME2","ESC2",null,null,null,"2007-10-01","ESC239356",null,176.59423076923076,0.046529,null,null,null,184.8109837326923]
["LL_ME2","ESC2",null,null,null,"2008-10-01","ESC239722",null,176.59423076923076,0.070599,null,null,null,189.0616068673077]
["LL_ME2","ESC2",null,null,null,"2009-10-01","ESC240087",null,176.59423076923076,0.095223,null,null,null,193.41006320576923]
["LL_ME2","ESC2",null,null,null,"2010-10-01","ESC240452",null,176.59423076923076,0.120413,null,null,null,197.85847187884616]
["LL_ME2","ESC2",null,null,null,"2011-10-01","ESC240817",null,176.59423076923076,0.120413,null,null,null,197.85847187884616]
["LL_ME2","ESC2",null,null,null,"2012-10-01","ESC241183",null,176.59423076923076,{"$nulls":4},176.59423076923076]
["LL_MES","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_MES","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_MES","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_MES","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_MES","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_MES","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_MFAT","ESC",null,null,null,"2003-10-01","ESC37895",null,137.21778846153848,0,null,null,null,137.21778846153848]
["LL_MFAT","ESC",null,null,null,"2004-10-01","ESC38261",null,137.21778846153848,0.029,null,null,null,141.19710432692307]
["LL_MFAT","ESC",null,null,null,"2005-10-01","ESC38626",null,137.21778846153848,0.057812,null,null,null,145.15062324807693]
["LL_MFAT","ESC",null,null,null,"2006-10-01","ESC38991",null,137.21778846153848,0.085315,null,null,null,148.92452408413465]
["LL_MFAT","ESC",null,null,null,"2007-10-01","ESC39356",null,137.21778846153848,0.113533,null,null,null,152.79653563894232]
["LL_MFAT","ESC",null,null,null,"2008-10-01","ESC39722",null,137.21778846153848,0.142485,null,null,null,156.76926505048078]
["LL_MFAT1","ESC1",null,null,null,"2005-10-01","ESC138626",null,137.21778846153848,0,null,null,null,137.21778846153848]
["LL_MFAT1","ESC1",null,null,null,"2006-10-01","ESC138991",null,137.21778846153848,0.026,null,null,null,140.7854509615385]
["LL_MFAT1","ESC1",null,null,null,"2007-10-01","ESC139356",null,137.21778846153848,0.052676,null,null,null,144.44587268653848]
["LL_MFAT1","ESC1",null,null,null,"2008-10-01","ESC139722",null,137.21778846153848,0.08004558,null,null,null,148.2014659252596]
["LL_MFAT2","ESC2",null,null,null,"2006-10-01","ESC238991",null,137.21778846153848,0.023,null,null,null,140.37379759615385]
["LL_MFAT2","ESC2",null,null,null,"2007-10-01","ESC239356",null,137.21778846153848,0.046529,null,null,null,143.6023949408654]
["LL_MFAT2","ESC2",null,null,null,"2008-10-01","ESC239722",null,137.21778846153848,0.070599,null,null,null,146.90522710913464]
["LL_MFAT2","ESC2",null,null,null,"2009-10-01","ESC240087",null,137.21778846153848,0.095223,null,null,null,150.28407793221157]
["LL_MFAT2","ESC2",null,null,null,"2010-10-01","ESC240452",null,137.21778846153848,0.120413,null,null,null,153.74059402355772]
["LL_MFAT2","ESC2",null,null,null,"2011-10-01","ESC240817",null,137.21778846153848,0.120413,null,null,null,153.74059402355772]
["LL_MFAT2","ESC2",null,null,null,"2012-10-01","ESC241183",null,137.21778846153848,{"$nulls":4},137.21778846153848]
["LL_MFMS","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_MFMS","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_MFMS","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_MFMS","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_MFMS","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_MFMS","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_MFPC","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_MFPC","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_MFPC","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_MFPC","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_MFPC","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_MFPC","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_MSCS","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LL_MSCS","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LL_MSCS","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LL_MSCS","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LL_MSCS","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LL_MSCS","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LL_MSCS1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LL_MSCS1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LL_MSCS1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LL_MSCS1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LL_MSCS2","ESC2","LL_OH2",null,null,"2006-10-01","ESC238991",null,1,0.023,0.11,null,null,1.13553]
["LL_MSCS2","ESC2","LL_OH2",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.11,null,null,1.16164719]
["LL_MSCS2","ESC2","LL_OH2",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.11,null,null,1.1883648900000001]
["LL_MSCS2","ESC2","LL_OH2",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.11,null,null,1.2156975300000001]
["LL_MSCS2","ESC2","LL_OH2",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LL_MSCS2","ESC2","LL_OH2",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LL_MSCS2","ESC2","LL_OH2",null,null,"2012-10-01","ESC241183",null,1,null,0.11,null,null,1.11]
["LL_MSEG","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LL_MSEG","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LL_MSEG","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LL_MSEG","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LL_MSEG","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LL_MSEG","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LL_MSEG1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LL_MSEG1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LL_MSEG1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LL_MSEG1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LL_MSEG2","ESC2","LL_OH2",null,null,"2006-10-01","ESC238991",null,1,0.023,0.11,null,null,1.13553]
["LL_MSEG2","ESC2","LL_OH2",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.11,null,null,1.16164719]
["LL_MSEG2","ESC2","LL_OH2",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.11,null,null,1.1883648900000001]
["LL_MSEG2","ESC2","LL_OH2",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.11,null,null,1.2156975300000001]
["LL_MSEG2","ESC2","LL_OH2",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LL_MSEG2","ESC2","LL_OH2",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LL_MSEG2","ESC2","LL_OH2",null,null,"2012-10-01","ESC241183",null,1,null,0.11,null,null,1.11]
["LL_MSEQ","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LL_MSEQ","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LL_MSEQ","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LL_MSEQ","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LL_MSEQ","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LL_MSEQ","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LL_MSEQ1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LL_MSEQ1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LL_MSEQ1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LL_MSEQ1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LL_MSEQ2","ESC2","LL_OH2",null,null,"2006-10-01","ESC238991",null,1,0.023,0.11,null,null,1.13553]
["LL_MSEQ2","ESC2","LL_OH2",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.11,null,null,1.16164719]
["LL_MSEQ2","ESC2","LL_OH2",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.11,null,null,1.1883648900000001]
["LL_MSEQ2","ESC2","LL_OH2",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.11,null,null,1.2156975300000001]
["LL_MSEQ2","ESC2","LL_OH2",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LL_MSEQ2","ESC2","LL_OH2",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LL_MSEQ2","ESC2","LL_OH2",null,null,"2012-10-01","ESC241183",null,1,null,0.11,null,null,1.11]
["LL_MSPS","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LL_MSPS","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LL_MSPS","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LL_MSPS","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LL_MSPS","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LL_MSPS","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LL_MSPS1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LL_MSPS1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LL_MSPS1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LL_MSPS1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LL_MSPS2","ESC2","LL_OH2",null,null,"2006-10-01","ESC238991",null,1,0.023,0.11,null,null,1.13553]
["LL_MSPS2","ESC2","LL_OH2",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.11,null,null,1.16164719]
["LL_MSPS2","ESC2","LL_OH2",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.11,null,null,1.1883648900000001]
["LL_MSPS2","ESC2","LL_OH2",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.11,null,null,1.2156975300000001]
["LL_MSPS2","ESC2","LL_OH2",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LL_MSPS2","ESC2","LL_OH2",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LL_MSPS2","ESC2","LL_OH2",null,null,"2012-10-01","ESC241183",null,1,null,0.11,null,null,1.11]
["LL_MSSC","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LL_MSSC","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LL_MSSC","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LL_MSSC","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LL_MSSC","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LL_MSSC","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LL_MSSC1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LL_MSSC1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LL_MSSC1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LL_MSSC1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LL_MSSC2","ESC2","LL_OH2",null,null,"2006-10-01","ESC238991",null,1,0.023,0.11,null,null,1.13553]
["LL_MSSC2","ESC2","LL_OH2",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.11,null,null,1.16164719]
["LL_MSSC2","ESC2","LL_OH2",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.11,null,null,1.1883648900000001]
["LL_MSSC2","ESC2","LL_OH2",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.11,null,null,1.2156975300000001]
["LL_MSSC2","ESC2","LL_OH2",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LL_MSSC2","ESC2","LL_OH2",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LL_MSSC2","ESC2","LL_OH2",null,null,"2012-10-01","ESC241183",null,1,null,0.11,null,null,1.11]
["LL_MSTR","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LL_MSTR","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LL_MSTR","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LL_MSTR","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LL_MSTR","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LL_MSTR","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LL_MSTR1","ESC1","LL_OH",null,null,"2005-10-01","ESC138626",null,1,0,0.19,null,null,1.19]
["LL_MSTR1","ESC1","LL_OH",null,null,"2006-10-01","ESC138991",null,1,0.026,0.19,null,null,1.22094]
["LL_MSTR1","ESC1","LL_OH",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.19,null,null,1.25268444]
["LL_MSTR1","ESC1","LL_OH",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.19,null,null,1.2852542401999998]
["LL_MSTR2","ESC2","LL_OH",null,null,"2006-10-01","ESC238991",null,1,0.023,0.19,null,null,1.2173699999999998]
["LL_MSTR2","ESC2","LL_OH",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.19,null,null,1.24536951]
["LL_MSTR2","ESC2","LL_OH",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.19,null,null,1.27401281]
["LL_MSTR2","ESC2","LL_OH",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.19,null,null,1.30331537]
["LL_MSTR2","ESC2","LL_OH",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.19,null,null,1.33329147]
["LL_MSTR2","ESC2","LL_OH",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.19,null,null,1.33329147]
["LL_MSTR2","ESC2","LL_OH",null,null,"2012-10-01","ESC241183",null,1,null,0.19,null,null,1.19]
["LL_MSXX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["LL_MSXX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["LL_MSXX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["LL_MSXX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["LL_MSXX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["LL_MSXX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["LL_MSXX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["LL_MSXX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["LL_MSXX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["LL_MSXX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["LL_MSXX2","ESC2",null,null,null,"2006-10-01","ESC238991",null,1,0.023,null,null,null,1.023]
["LL_MSXX2","ESC2",null,null,null,"2007-10-01","ESC239356",null,1,0.046529,null,null,null,1.046529]
["LL_MSXX2","ESC2",null,null,null,"2008-10-01","ESC239722",null,1,0.070599,null,null,null,1.070599]
["LL_MSXX2","ESC2",null,null,null,"2009-10-01","ESC240087",null,1,0.095223,null,null,null,1.095223]
["LL_MSXX2","ESC2",null,null,null,"2010-10-01","ESC240452",null,1,0.120413,null,null,null,1.120413]
["LL_MSXX2","ESC2",null,null,null,"2011-10-01","ESC240817",null,1,0.120413,null,null,null,1.120413]
["LL_MSXX2","ESC2",null,null,null,"2012-10-01","ESC241183",null,1,{"$nulls":4},1]
["LL_MTRL","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LL_MTRL","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LL_MTRL","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LL_MTRL","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LL_MTRL","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LL_MTRL","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LL_MTRL1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LL_MTRL1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LL_MTRL1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LL_MTRL1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LL_MTRL2","ESC2","LL_OH2",null,null,"2006-10-01","ESC238991",null,1,0.023,0.11,null,null,1.13553]
["LL_MTRL2","ESC2","LL_OH2",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.11,null,null,1.16164719]
["LL_MTRL2","ESC2","LL_OH2",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.11,null,null,1.1883648900000001]
["LL_MTRL2","ESC2","LL_OH2",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.11,null,null,1.2156975300000001]
["LL_MTRL2","ESC2","LL_OH2",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LL_MTRL2","ESC2","LL_OH2",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.11,null,null,1.2436584300000002]
["LL_MTRL2","ESC2","LL_OH2",null,null,"2012-10-01","ESC241183",null,1,null,0.11,null,null,1.11]
["LL_MVE","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_MVE","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_MVE","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_MVE","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_MVE","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_MVE","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_PCCA","ESC",null,null,null,"2003-10-01","ESC37895",null,158.32548076923078,0,null,null,null,158.32548076923078]
["LL_PCCA","ESC",null,null,null,"2004-10-01","ESC38261",null,158.32548076923078,0.029,null,null,null,162.91691971153847]
["LL_PCCA","ESC",null,null,null,"2005-10-01","ESC38626",null,158.32548076923078,0.057812,null,null,null,167.47859346346155]
["LL_PCCA","ESC",null,null,null,"2006-10-01","ESC38991",null,158.32548076923078,0.085315,null,null,null,171.8330191610577]
["LL_PCCA","ESC",null,null,null,"2007-10-01","ESC39356",null,158.32548076923078,0.113533,null,null,null,176.30064757740385]
["LL_PCCA","ESC",null,null,null,"2008-10-01","ESC39722",null,158.32548076923078,0.142485,null,null,null,180.88448689663463]
["LL_PCCA1","ESC1",null,null,null,"2005-10-01","ESC138626",null,158.32548076923078,0,null,null,null,158.32548076923078]
["LL_PCCA1","ESC1",null,null,null,"2006-10-01","ESC138991",null,158.32548076923078,0.026,null,null,null,162.4419432692308]
["LL_PCCA1","ESC1",null,null,null,"2007-10-01","ESC139356",null,158.32548076923078,0.052676,null,null,null,166.66543379423078]
["LL_PCCA1","ESC1",null,null,null,"2008-10-01","ESC139722",null,158.32548076923078,0.08004558,null,null,null,170.99873570618269]
["LL_PCCA2","ESC2",null,null,null,"2006-10-01","ESC238991",null,158.32548076923078,0.023,null,null,null,161.96696682692308]
["LL_PCCA2","ESC2",null,null,null,"2007-10-01","ESC239356",null,158.32548076923078,0.046529,null,null,null,165.69220706394233]
["LL_PCCA2","ESC2",null,null,null,"2008-10-01","ESC239722",null,158.32548076923078,0.070599,null,null,null,169.50310138605772]
["LL_PCCA2","ESC2",null,null,null,"2009-10-01","ESC240087",null,158.32548076923078,0.095223,null,null,null,173.40170802451925]
["LL_PCCA2","ESC2",null,null,null,"2010-10-01","ESC240452",null,158.32548076923078,0.120413,null,null,null,177.38992688509617]
["LL_PCCA2","ESC2",null,null,null,"2011-10-01","ESC240817",null,158.32548076923078,0.120413,null,null,null,177.38992688509617]
["LL_PCCA2","ESC2",null,null,null,"2012-10-01","ESC241183",null,158.32548076923078,{"$nulls":4},158.32548076923078]
["LL_PCE","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_PCE","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_PCE","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_PCE","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_PCE","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_PCE","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_PCEF","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_PCEF","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_PCEF","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_PCEF","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_PCEF","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_PCEF","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_PCT","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_PCT","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_PCT","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_PCT","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_PCT","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_PCT","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_PHPD","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_PHPD","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_PHPD","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_PHPD","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_PHPD","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_PHPD","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_PHPD2","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_PHPD2","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_PHPD2","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_PHPD2","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_PHPD2","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_PHPD2","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_PHS","ESC",null,null,null,"2003-10-01","ESC37895",null,188.69326923076923,0,null,null,null,188.69326923076923]
["LL_PHS","ESC",null,null,null,"2004-10-01","ESC38261",null,188.69326923076923,0.029,null,null,null,194.16537403846152]
["LL_PHS","ESC",null,null,null,"2005-10-01","ESC38626",null,188.69326923076923,0.057812,null,null,null,199.60200451153847]
["LL_PHS","ESC",null,null,null,"2006-10-01","ESC38991",null,188.69326923076923,0.085315,null,null,null,204.7916354951923]
["LL_PHS","ESC",null,null,null,"2007-10-01","ESC39356",null,188.69326923076923,0.113533,null,null,null,210.11618216634614]
["LL_PHS","ESC",null,null,null,"2008-10-01","ESC39722",null,188.69326923076923,0.142485,null,null,null,215.57922969711538]
["LL_PHS1","ESC1",null,null,null,"2005-10-01","ESC138626",null,188.69326923076923,0,null,null,null,188.69326923076923]
["LL_PHS1","ESC1",null,null,null,"2006-10-01","ESC138991",null,188.69326923076923,0.026,null,null,null,193.59929423076923]
["LL_PHS1","ESC1",null,null,null,"2007-10-01","ESC139356",null,188.69326923076923,0.052676,null,null,null,198.63287588076923]
["LL_PHS1","ESC1",null,null,null,"2008-10-01","ESC139722",null,188.69326923076923,0.08004558,null,null,null,203.7973314084423]
["LL_PHS2","ESC2",null,null,null,"2006-10-01","ESC238991",null,188.69326923076923,0.023,null,null,null,193.0332144230769]
["LL_PHS2","ESC2",null,null,null,"2007-10-01","ESC239356",null,188.69326923076923,0.046529,null,null,null,197.4729783548077]
["LL_PHS2","ESC2",null,null,null,"2008-10-01","ESC239722",null,188.69326923076923,0.070599,null,null,null,202.01482534519232]
["LL_PHS2","ESC2",null,null,null,"2009-10-01","ESC240087",null,188.69326923076923,0.095223,null,null,null,206.6612084067308]
["LL_PHS2","ESC2",null,null,null,"2010-10-01","ESC240452",null,188.69326923076923,0.120413,null,null,null,211.41439185865386]
["LL_PHS2","ESC2",null,null,null,"2011-10-01","ESC240817",null,188.69326923076923,0.120413,null,null,null,211.41439185865386]
["LL_PHS2","ESC2",null,null,null,"2012-10-01","ESC241183",null,188.69326923076923,{"$nulls":4},188.69326923076923]
["LL_PHSS","ESC",null,null,null,"2003-10-01","ESC37895",null,208.3653846153846,0,null,null,null,208.3653846153846]
["LL_PHSS","ESC",null,null,null,"2004-10-01","ESC38261",null,208.3653846153846,0.029,null,null,null,214.40798076923076]
["LL_PHSS","ESC",null,null,null,"2005-10-01","ESC38626",null,208.3653846153846,0.057812,null,null,null,220.41140423076922]
["LL_PHSS","ESC",null,null,null,"2006-10-01","ESC38991",null,208.3653846153846,0.085315,null,null,null,226.14207740384614]
["LL_PHSS","ESC",null,null,null,"2007-10-01","ESC39356",null,208.3653846153846,0.113533,null,null,null,232.02173182692306]
["LL_PHSS","ESC",null,null,null,"2008-10-01","ESC39722",null,208.3653846153846,0.142485,null,null,null,238.05432644230768]
["LL_PHSS1","ESC1",null,null,null,"2005-10-01","ESC138626",null,208.3653846153846,0,null,null,null,208.3653846153846]
["LL_PHSS1","ESC1",null,null,null,"2006-10-01","ESC138991",null,208.3653846153846,0.026,null,null,null,213.78288461538463]
["LL_PHSS1","ESC1",null,null,null,"2007-10-01","ESC139356",null,208.3653846153846,0.052676,null,null,null,219.3412396153846]
["LL_PHSS1","ESC1",null,null,null,"2008-10-01","ESC139722",null,208.3653846153846,0.08004558,null,null,null,225.04411267884615]
["LL_PHSS2","ESC2",null,null,null,"2006-10-01","ESC238991",null,208.3653846153846,0.023,null,null,null,213.15778846153844]
["LL_PHSS2","ESC2",null,null,null,"2007-10-01","ESC239356",null,208.3653846153846,0.046529,null,null,null,218.06041759615385]
["LL_PHSS2","ESC2",null,null,null,"2008-10-01","ESC239722",null,208.3653846153846,0.070599,null,null,null,223.07577240384617]
["LL_PHSS2","ESC2",null,null,null,"2009-10-01","ESC240087",null,208.3653846153846,0.095223,null,null,null,228.20656163461538]
["LL_PHSS2","ESC2",null,null,null,"2010-10-01","ESC240452",null,208.3653846153846,0.120413,null,null,null,233.45528567307693]
["LL_PHSS2","ESC2",null,null,null,"2011-10-01","ESC240817",null,208.3653846153846,0.120413,null,null,null,233.45528567307693]
["LL_PHSS2","ESC2",null,null,null,"2012-10-01","ESC241183",null,208.3653846153846,{"$nulls":4},208.3653846153846]
["LL_PM","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_PM","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_PM","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_PM","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_PM","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_PM","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_PRC","ESC",null,null,null,"2003-10-01","ESC37895",null,162.0105769230769,0,null,null,null,162.0105769230769]
["LL_PRC","ESC",null,null,null,"2004-10-01","ESC38261",null,162.0105769230769,0.029,null,null,null,166.70888365384613]
["LL_PRC","ESC",null,null,null,"2005-10-01","ESC38626",null,162.0105769230769,0.057812,null,null,null,171.37673239615384]
["LL_PRC","ESC",null,null,null,"2006-10-01","ESC38991",null,162.0105769230769,0.085315,null,null,null,175.83250929326923]
["LL_PRC","ESC",null,null,null,"2007-10-01","ESC39356",null,162.0105769230769,0.113533,null,null,null,180.40412375288457]
["LL_PRC","ESC",null,null,null,"2008-10-01","ESC39722",null,162.0105769230769,0.142485,null,null,null,185.0946539759615]
["LL_PRC1","ESC1",null,null,null,"2005-10-01","ESC138626",null,162.0105769230769,0,null,null,null,162.0105769230769]
["LL_PRC1","ESC1",null,null,null,"2006-10-01","ESC138991",null,162.0105769230769,0.026,null,null,null,166.22285192307692]
["LL_PRC1","ESC1",null,null,null,"2007-10-01","ESC139356",null,162.0105769230769,0.052676,null,null,null,170.5446460730769]
["LL_PRC1","ESC1",null,null,null,"2008-10-01","ESC139722",null,162.0105769230769,0.08004558,null,null,null,174.9788075190192]
["LL_PRC2","ESC2",null,null,null,"2006-10-01","ESC238991",null,162.0105769230769,0.023,null,null,null,165.73682019230768]
["LL_PRC2","ESC2",null,null,null,"2007-10-01","ESC239356",null,162.0105769230769,0.046529,null,null,null,169.54876705673075]
["LL_PRC2","ESC2",null,null,null,"2008-10-01","ESC239722",null,162.0105769230769,0.070599,null,null,null,173.44836164326924]
["LL_PRC2","ESC2",null,null,null,"2009-10-01","ESC240087",null,162.0105769230769,0.095223,null,null,null,177.43771008942306]
["LL_PRC2","ESC2",null,null,null,"2010-10-01","ESC240452",null,162.0105769230769,0.120413,null,null,null,181.51875652211538]
["LL_PRC2","ESC2",null,null,null,"2011-10-01","ESC240817",null,162.0105769230769,0.120413,null,null,null,181.51875652211538]
["LL_PRC2","ESC2",null,null,null,"2012-10-01","ESC241183",null,162.0105769230769,{"$nulls":4},162.0105769230769]
["LL_PRE","ESC",null,null,null,"2003-10-01","ESC37895",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_PRE","ESC",null,null,null,"2004-10-01","ESC38261",null,176.59423076923076,0.029,null,null,null,181.71546346153843]
["LL_PRE","ESC",null,null,null,"2005-10-01","ESC38626",null,176.59423076923076,0.057812,null,null,null,186.80349643846154]
["LL_PRE","ESC",null,null,null,"2006-10-01","ESC38991",null,176.59423076923076,0.085315,null,null,null,191.6603675673077]
["LL_PRE","ESC",null,null,null,"2007-10-01","ESC39356",null,176.59423076923076,0.113533,null,null,null,196.64350357115381]
["LL_PRE","ESC",null,null,null,"2008-10-01","ESC39722",null,176.59423076923076,0.142485,null,null,null,201.7562597403846]
["LL_PRE1","ESC1",null,null,null,"2005-10-01","ESC138626",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_PRE1","ESC1",null,null,null,"2006-10-01","ESC138991",null,176.59423076923076,0.026,null,null,null,181.18568076923077]
["LL_PRE1","ESC1",null,null,null,"2007-10-01","ESC139356",null,176.59423076923076,0.052676,null,null,null,185.89650846923075]
["LL_PRE1","ESC1",null,null,null,"2008-10-01","ESC139722",null,176.59423076923076,0.08004558,null,null,null,190.72981839580768]
["LL_PRE2","ESC2",null,null,null,"2006-10-01","ESC238991",null,176.59423076923076,0.023,null,null,null,180.65589807692305]
["LL_PRE2","ESC2",null,null,null,"2007-10-01","ESC239356",null,176.59423076923076,0.046529,null,null,null,184.8109837326923]
["LL_PRE2","ESC2",null,null,null,"2008-10-01","ESC239722",null,176.59423076923076,0.070599,null,null,null,189.0616068673077]
["LL_PRE2","ESC2",null,null,null,"2009-10-01","ESC240087",null,176.59423076923076,0.095223,null,null,null,193.41006320576923]
["LL_PRE2","ESC2",null,null,null,"2010-10-01","ESC240452",null,176.59423076923076,0.120413,null,null,null,197.85847187884616]
["LL_PRE2","ESC2",null,null,null,"2011-10-01","ESC240817",null,176.59423076923076,0.120413,null,null,null,197.85847187884616]
["LL_PRE2","ESC2",null,null,null,"2012-10-01","ESC241183",null,176.59423076923076,{"$nulls":4},176.59423076923076]
["LL_RP","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_RP","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_RP","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_RP","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_RP","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_RP","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_SEE","ESC",null,null,null,"2003-10-01","ESC37895",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_SEE","ESC",null,null,null,"2004-10-01","ESC38261",null,176.59423076923076,0.029,null,null,null,181.71546346153843]
["LL_SEE","ESC",null,null,null,"2005-10-01","ESC38626",null,176.59423076923076,0.057812,null,null,null,186.80349643846154]
["LL_SEE","ESC",null,null,null,"2006-10-01","ESC38991",null,176.59423076923076,0.085315,null,null,null,191.6603675673077]
["LL_SEE","ESC",null,null,null,"2007-10-01","ESC39356",null,176.59423076923076,0.113533,null,null,null,196.64350357115381]
["LL_SEE","ESC",null,null,null,"2008-10-01","ESC39722",null,176.59423076923076,0.142485,null,null,null,201.7562597403846]
["LL_SEE1","ESC1",null,null,null,"2005-10-01","ESC138626",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_SEE1","ESC1",null,null,null,"2006-10-01","ESC138991",null,176.59423076923076,0.026,null,null,null,181.18568076923077]
["LL_SEE1","ESC1",null,null,null,"2007-10-01","ESC139356",null,176.59423076923076,0.052676,null,null,null,185.89650846923075]
["LL_SEE1","ESC1",null,null,null,"2008-10-01","ESC139722",null,176.59423076923076,0.08004558,null,null,null,190.72981839580768]
["LL_SEE2","ESC2",null,null,null,"2006-10-01","ESC238991",null,176.59423076923076,0.023,null,null,null,180.65589807692305]
["LL_SEE2","ESC2",null,null,null,"2007-10-01","ESC239356",null,176.59423076923076,0.046529,null,null,null,184.8109837326923]
["LL_SEE2","ESC2",null,null,null,"2008-10-01","ESC239722",null,176.59423076923076,0.070599,null,null,null,189.0616068673077]
["LL_SEE2","ESC2",null,null,null,"2009-10-01","ESC240087",null,176.59423076923076,0.095223,null,null,null,193.41006320576923]
["LL_SEE2","ESC2",null,null,null,"2010-10-01","ESC240452",null,176.59423076923076,0.120413,null,null,null,197.85847187884616]
["LL_SEE2","ESC2",null,null,null,"2011-10-01","ESC240817",null,176.59423076923076,0.120413,null,null,null,197.85847187884616]
["LL_SEE2","ESC2",null,null,null,"2012-10-01","ESC241183",null,176.59423076923076,{"$nulls":4},176.59423076923076]
["LL_SEL","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_SEL","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_SEL","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_SEL","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_SEL","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_SEL","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_SEPM","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_SEPM","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_SEPM","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_SEPM","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_SEPM","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_SEPM","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_TMUC","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_TMUC","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_TMUC","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_TMUC","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_TMUC","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_TMUC","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_TMUE","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_TMUE","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_TMUE","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_TMUE","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_TMUE","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_TMUE","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_TMUI","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_TMUI","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_TMUI","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_TMUI","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_TMUI","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_TMUI","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_TMUO","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_TMUO","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_TMUO","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_TMUO","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_TMUO","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_TMUO","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_TMUP","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_TMUP","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_TMUP","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_TMUP","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_TMUP","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_TMUP","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_TMUW","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_TMUW","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_TMUW","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_TMUW","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_TMUW","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_TMUW","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["PED",{"$nulls":5},"",{"$nulls":6},0]
["R&D",{"$nulls":5},"",{"$nulls":6},0]
["RES",{"$nulls":5},"",{"$nulls":6},0]
["SA_GCFX1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SA_GCFX2",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SA_GCSS","ESC_CF","SL_OH2",null,null,"2004-10-01","ESC_CF38261",null,1,0,0.06,null,null,1.06]
["SA_GCSS","ESC_CF","SL_OH2",null,null,"2005-10-01","ESC_CF38626",null,1,0.03,0.06,null,null,1.0918]
["SA_GCSS","ESC_CF","SL_OH2",null,null,"2006-10-01","ESC_CF38991",null,1,0.08,0.06,null,null,1.1448]
["SA_GCSS","ESC_CF","SL_OH2",null,null,"2007-10-01","ESC_CF39356",null,1,0.19,0.06,null,null,1.2614]
["SA_GCSS","ESC_CF","SL_OH2",null,null,"2008-10-01","ESC_CF39722",null,1,0.3,0.06,null,null,1.3780000000000001]
["SA_GCSS","ESC_CF","SL_OH2",null,null,"2009-10-01","ESC_CF40087",null,1,0.41,0.06,null,null,1.4946]
["SA_GCSS1","ESC_CF","SL_OHN2",null,null,"2004-10-01","ESC_CF38261",null,1,0,0.048,null,null,1.048]
["SA_GCSS1","ESC_CF","SL_OHN2",null,null,"2005-10-01","ESC_CF38626",null,1,0.03,0.048,null,null,1.0794400000000002]
["SA_GCSS1","ESC_CF","SL_OHN2",null,null,"2006-10-01","ESC_CF38991",null,1,0.08,0.048,null,null,1.1318400000000002]
["SA_GCSS1","ESC_CF","SL_OHN2",null,null,"2007-10-01","ESC_CF39356",null,1,0.19,0.048,null,null,1.24712]
["SA_GCSS1","ESC_CF","SL_OHN2",null,null,"2008-10-01","ESC_CF39722",null,1,0.3,0.048,null,null,1.3624]
["SA_GCSS1","ESC_CF","SL_OHN2",null,null,"2009-10-01","ESC_CF40087",null,1,0.41,0.048,null,null,1.4776799999999999]
["SA_GCSS2","ESC_CF","SL_OHN2",null,null,"2004-10-01","ESC_CF38261",null,1,0,0.048,null,null,1.048]
["SA_GCSS2","ESC_CF","SL_OHN2",null,null,"2005-10-01","ESC_CF38626",null,1,0.03,0.048,null,null,1.0794400000000002]
["SA_GCSS2","ESC_CF","SL_OHN2",null,null,"2006-10-01","ESC_CF38991",null,1,0.08,0.048,null,null,1.1318400000000002]
["SA_GCSS2","ESC_CF","SL_OHN2",null,null,"2007-10-01","ESC_CF39356",null,1,0.19,0.048,null,null,1.24712]
["SA_GCSS2","ESC_CF","SL_OHN2",null,null,"2008-10-01","ESC_CF39722",null,1,0.3,0.048,null,null,1.3624]
["SA_GCSS2","ESC_CF","SL_OHN2",null,null,"2009-10-01","ESC_CF40087",null,1,0.41,0.048,null,null,1.4776799999999999]
["SA_GCSX","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,1,0,null,null,null,1]
["SA_GCSX","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,1,0.03,null,null,null,1.03]
["SA_GCSX","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,1,0.08,null,null,null,1.08]
["SA_GCSX","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,1,0.19,null,null,null,1.19]
["SA_GCSX","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,1,0.3,null,null,null,1.3]
["SA_GCSX","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,1,0.41,null,null,null,1.41]
["SA_GCSX1","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,1,0,null,null,null,1]
["SA_GCSX1","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,1,0.03,null,null,null,1.03]
["SA_GCSX1","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,1,0.08,null,null,null,1.08]
["SA_GCSX1","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,1,0.19,null,null,null,1.19]
["SA_GCSX1","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,1,0.3,null,null,null,1.3]
["SA_GCSX1","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,1,0.41,null,null,null,1.41]
["SA_GCSX2","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,1,0,null,null,null,1]
["SA_GCSX2","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,1,0.03,null,null,null,1.03]
["SA_GCSX2","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,1,0.08,null,null,null,1.08]
["SA_GCSX2","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,1,0.19,null,null,null,1.19]
["SA_GCSX2","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,1,0.3,null,null,null,1.3]
["SA_GCSX2","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,1,0.41,null,null,null,1.41]
["SA_MSCS","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.06,null,null,0]
["SA_MSCS","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.06,null,null,0]
["SA_MSCS","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.06,null,null,0]
["SA_MSCS","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.06,null,null,0]
["SA_MSCS","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.06,null,null,0]
["SA_MSCS","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.06,null,null,0]
["SA_MSCS1","ESC1","SL_OHN2",null,null,"2005-10-01","ESC138626",null,null,0,0.048,null,null,0]
["SA_MSCS1","ESC1","SL_OHN2",null,null,"2006-10-01","ESC138991",null,null,0.026,0.048,null,null,0]
["SA_MSCS1","ESC1","SL_OHN2",null,null,"2007-10-01","ESC139356",null,null,0.052676,0.048,null,null,0]
["SA_MSCS1","ESC1","SL_OHN2",null,null,"2008-10-01","ESC139722",null,null,0.08004558,0.048,null,null,0]
["SA_MSCS2","ESC2","SL_OHN2",null,null,"2006-10-01","ESC238991",null,null,0.023,0.048,null,null,0]
["SA_MSCS2","ESC2","SL_OHN2",null,null,"2007-10-01","ESC239356",null,null,0.046529,0.048,null,null,0]
["SA_MSCS2","ESC2","SL_OHN2",null,null,"2008-10-01","ESC239722",null,null,0.070599,0.048,null,null,0]
["SA_MSCS2","ESC2","SL_OHN2",null,null,"2009-10-01","ESC240087",null,null,0.095223,0.048,null,null,0]
["SA_MSCS2","ESC2","SL_OHN2",null,null,"2010-10-01","ESC240452",null,null,0.120413,0.048,null,null,0]
["SA_MSCS2","ESC2","SL_OHN2",null,null,"2011-10-01","ESC240817",null,null,0.120413,0.048,null,null,0]
["SA_MSCS2","ESC2","SL_OHN2",null,null,"2012-10-01","ESC241183",null,null,null,0.048,null,null,0]
["SA_MSEG","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SA_MSEG","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SA_MSEG","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SA_MSEG","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SA_MSEG","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SA_MSEG","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SA_MSEG1","ESC1","SL_OHN2",null,null,"2005-10-01","ESC138626",null,1,0,0.048,null,null,1.048]
["SA_MSEG1","ESC1","SL_OHN2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.048,null,null,1.075248]
["SA_MSEG1","ESC1","SL_OHN2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.048,null,null,1.103204448]
["SA_MSEG1","ESC1","SL_OHN2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.048,null,null,1.13188776784]
["SA_MSEG2","ESC2","SL_OHN2",null,null,"2006-10-01","ESC238991",null,1,0.023,0.048,null,null,1.072104]
["SA_MSEG2","ESC2","SL_OHN2",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.048,null,null,1.096762392]
["SA_MSEG2","ESC2","SL_OHN2",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.048,null,null,1.1219877520000001]
["SA_MSEG2","ESC2","SL_OHN2",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.048,null,null,1.1477937040000001]
["SA_MSEG2","ESC2","SL_OHN2",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.048,null,null,1.1741928240000001]
["SA_MSEG2","ESC2","SL_OHN2",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.048,null,null,1.1741928240000001]
["SA_MSEG2","ESC2","SL_OHN2",null,null,"2012-10-01","ESC241183",null,1,null,0.048,null,null,1.048]
["SA_MSEQ","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SA_MSEQ","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SA_MSEQ","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SA_MSEQ","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SA_MSEQ","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SA_MSEQ","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SA_MSEQ1","ESC1","SL_OHN2",null,null,"2005-10-01","ESC138626",null,1,0,0.048,null,null,1.048]
["SA_MSEQ1","ESC1","SL_OHN2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.048,null,null,1.075248]
["SA_MSEQ1","ESC1","SL_OHN2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.048,null,null,1.103204448]
["SA_MSEQ1","ESC1","SL_OHN2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.048,null,null,1.13188776784]
["SA_MSEQ2","ESC2","SL_OHN2",null,null,"2006-10-01","ESC238991",null,1,0.023,0.048,null,null,1.072104]
["SA_MSEQ2","ESC2","SL_OHN2",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.048,null,null,1.096762392]
["SA_MSEQ2","ESC2","SL_OHN2",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.048,null,null,1.1219877520000001]
["SA_MSEQ2","ESC2","SL_OHN2",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.048,null,null,1.1477937040000001]
["SA_MSEQ2","ESC2","SL_OHN2",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.048,null,null,1.1741928240000001]
["SA_MSEQ2","ESC2","SL_OHN2",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.048,null,null,1.1741928240000001]
["SA_MSEQ2","ESC2","SL_OHN2",null,null,"2012-10-01","ESC241183",null,1,null,0.048,null,null,1.048]
["SA_MSPF","SL_OH2",{"$nulls":4},"SL_OH2",null,1,0.06,null,null,null,1.06]
["SA_MSPF1","SL_OHN2",{"$nulls":4},"SL_OHN2",null,1,0.048,null,null,null,1.048]
["SA_MSPF2","SL_OHN2",{"$nulls":4},"SL_OHN2",null,1,0.048,null,null,null,1.048]
["SA_MSPS","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SA_MSPS","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SA_MSPS","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SA_MSPS","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SA_MSPS","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SA_MSPS","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SA_MSPS1","ESC1","SL_OHN2",null,null,"2005-10-01","ESC138626",null,1,0,0.048,null,null,1.048]
["SA_MSPS1","ESC1","SL_OHN2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.048,null,null,1.075248]
["SA_MSPS1","ESC1","SL_OHN2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.048,null,null,1.103204448]
["SA_MSPS1","ESC1","SL_OHN2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.048,null,null,1.13188776784]
["SA_MSPS2","ESC2","SL_OHN2",null,null,"2006-10-01","ESC238991",null,1,0.023,0.048,null,null,1.072104]
["SA_MSPS2","ESC2","SL_OHN2",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.048,null,null,1.096762392]
["SA_MSPS2","ESC2","SL_OHN2",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.048,null,null,1.1219877520000001]
["SA_MSPS2","ESC2","SL_OHN2",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.048,null,null,1.1477937040000001]
["SA_MSPS2","ESC2","SL_OHN2",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.048,null,null,1.1741928240000001]
["SA_MSPS2","ESC2","SL_OHN2",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.048,null,null,1.1741928240000001]
["SA_MSPS2","ESC2","SL_OHN2",null,null,"2012-10-01","ESC241183",null,1,null,0.048,null,null,1.048]
["SA_MSPX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["SA_MSPX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["SA_MSPX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["SA_MSPX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["SA_MSPX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["SA_MSPX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["SA_MSPX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["SA_MSPX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["SA_MSPX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["SA_MSPX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["SA_MSPX2","ESC2",null,null,null,"2006-10-01","ESC238991",null,1,0.023,null,null,null,1.023]
["SA_MSPX2","ESC2",null,null,null,"2007-10-01","ESC239356",null,1,0.046529,null,null,null,1.046529]
["SA_MSPX2","ESC2",null,null,null,"2008-10-01","ESC239722",null,1,0.070599,null,null,null,1.070599]
["SA_MSPX2","ESC2",null,null,null,"2009-10-01","ESC240087",null,1,0.095223,null,null,null,1.095223]
["SA_MSPX2","ESC2",null,null,null,"2010-10-01","ESC240452",null,1,0.120413,null,null,null,1.120413]
["SA_MSPX2","ESC2",null,null,null,"2011-10-01","ESC240817",null,1,0.120413,null,null,null,1.120413]
["SA_MSPX2","ESC2",null,null,null,"2012-10-01","ESC241183",null,1,{"$nulls":4},1]
["SA_MSPY",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SA_MSPY1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SA_MSPY2",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SA_MSSC","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SA_MSSC","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SA_MSSC","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SA_MSSC","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SA_MSSC","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SA_MSSC","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SA_MSSC1","ESC1","SL_OHN2",null,null,"2005-10-01","ESC138626",null,1,0,0.048,null,null,1.048]
["SA_MSSC1","ESC1","SL_OHN2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.048,null,null,1.075248]
["SA_MSSC1","ESC1","SL_OHN2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.048,null,null,1.103204448]
["SA_MSSC1","ESC1","SL_OHN2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.048,null,null,1.13188776784]
["SA_MSSC2","ESC2","SL_OHN2",null,null,"2006-10-01","ESC238991",null,1,0.023,0.048,null,null,1.072104]
["SA_MSSC2","ESC2","SL_OHN2",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.048,null,null,1.096762392]
["SA_MSSC2","ESC2","SL_OHN2",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.048,null,null,1.1219877520000001]
["SA_MSSC2","ESC2","SL_OHN2",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.048,null,null,1.1477937040000001]
["SA_MSSC2","ESC2","SL_OHN2",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.048,null,null,1.1741928240000001]
["SA_MSSC2","ESC2","SL_OHN2",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.048,null,null,1.1741928240000001]
["SA_MSSC2","ESC2","SL_OHN2",null,null,"2012-10-01","ESC241183",null,1,null,0.048,null,null,1.048]
["SA_MSSF","SL_OH2",{"$nulls":4},"SL_OH2",null,1,0.06,null,null,null,1.06]
["SA_MSSF1","SL_OHN2",{"$nulls":4},"SL_OHN2",null,1,0.048,null,null,null,1.048]
["SA_MSSF2","SL_OHN2",{"$nulls":4},"SL_OHN2",null,1,0.048,null,null,null,1.048]
["SA_MSSY",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SA_MSSY1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SA_MSSY2",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SA_MSXX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["SA_MSXX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["SA_MSXX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["SA_MSXX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["SA_MSXX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["SA_MSXX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["SA_MSXX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["SA_MSXX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["SA_MSXX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["SA_MSXX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["SA_MSXX2","ESC2",null,null,null,"2006-10-01","ESC238991",null,1,0.023,null,null,null,1.023]
["SA_MSXX2","ESC2",null,null,null,"2007-10-01","ESC239356",null,1,0.046529,null,null,null,1.046529]
["SA_MSXX2","ESC2",null,null,null,"2008-10-01","ESC239722",null,1,0.070599,null,null,null,1.070599]
["SA_MSXX2","ESC2",null,null,null,"2009-10-01","ESC240087",null,1,0.095223,null,null,null,1.095223]
["SA_MSXX2","ESC2",null,null,null,"2010-10-01","ESC240452",null,1,0.120413,null,null,null,1.120413]
["SA_MSXX2","ESC2",null,null,null,"2011-10-01","ESC240817",null,1,0.120413,null,null,null,1.120413]
["SA_MSXX2","ESC2",null,null,null,"2012-10-01","ESC241183",null,1,{"$nulls":4},1]
["SLAC_LABOR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,null,0,0.29,0.215,0.2,0]
["SLAC_LABOR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,null,0.029,0.29,0.215,0.2,0]
["SLAC_LABOR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,null,0.057812,0.29,0.215,0.2,0]
["SLAC_LABOR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,null,0.085315,0.29,0.215,0.2,0]
["SLAC_LABOR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,null,0.113533,0.29,0.215,0.2,0]
["SLAC_LABOR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,null,0.142485,0.29,0.215,0.2,0]
["SLAC_NON-LABOR","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.06,null,null,0]
["SLAC_NON-LABOR","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.06,null,null,0]
["SLAC_NON-LABOR","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.06,null,null,0]
["SLAC_NON-LABOR","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.06,null,null,0]
["SLAC_NON-LABOR","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.06,null,null,0]
["SLAC_NON-LABOR","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.06,null,null,0]
["SLAC_SHOPS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2003-10-01","ESC37895",null,null,0,0,0,0.2,0]
["SLAC_SHOPS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2004-10-01","ESC38261",null,null,0.029,0,0,0.2,0]
["SLAC_SHOPS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2005-10-01","ESC38626",null,null,0.057812,0,0,0.2,0]
["SLAC_SHOPS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2006-10-01","ESC38991",null,null,0.085315,0,0,0.2,0]
["SLAC_SHOPS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2007-10-01","ESC39356",null,null,0.113533,0,0,0.2,0]
["SLAC_SHOPS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2008-10-01","ESC39722",null,null,0.142485,0,0,0.2,0]
["SLAC_TRAVEL","ESC","SL_OH1",null,null,"2003-10-01","ESC37895",null,null,0,0.2,null,null,0]
["SLAC_TRAVEL","ESC","SL_OH1",null,null,"2004-10-01","ESC38261",null,null,0.029,0.2,null,null,0]
["SLAC_TRAVEL","ESC","SL_OH1",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.2,null,null,0]
["SLAC_TRAVEL","ESC","SL_OH1",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.2,null,null,0]
["SLAC_TRAVEL","ESC","SL_OH1",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.2,null,null,0]
["SLAC_TRAVEL","ESC","SL_OH1",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.2,null,null,0]
["SL_ADMN","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,30.1731,0,0.29,0.215,0.2,56.750169942]
["SL_ADMN","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,30.1731,0.029,0.29,0.215,0.2,58.395924870318]
["SL_ADMN","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,30.1731,0.057812,0.29,0.215,0.2,60.031010766686904]
["SL_ADMN","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,30.1731,0.085315,0.29,0.215,0.2,61.59181069060175]
["SL_ADMN","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,30.1731,0.113533,0.29,0.215,0.2,63.193186986025076]
["SL_ADMN","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,30.1731,0.142485,0.29,0.215,0.2,64.83621790618588]
["SL_ADMN1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,30.1731,0,0.305,0.21,0.2,57.17380026599999]
["SL_ADMN1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,30.1731,0.026,0.305,0.21,0.2,58.660319072916]
["SL_ADMN1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,30.1731,0.052676,0.305,0.21,0.2,60.185487368811806]
["SL_ADMN1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,30.1731,0.08004558,0.305,0.21,0.2,61.75031026909612]
["SL_ADMN2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,30.1731,0.023,0.305,0.21,0.2,58.488797672118]
["SL_ADMN2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,30.1731,0.046529,0.305,0.21,0.2,59.83404001857671]
["SL_ADMN2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,30.1731,0.070599,0.305,0.21,0.2,61.210213390979334]
["SL_ADMN2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,30.1731,0.095223,0.305,0.21,0.2,62.61806104872932]
["SL_ADMN2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,30.1731,0.120413,0.305,0.21,0.2,64.05826907742986]
["SL_ADMN2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,30.1731,0.120413,0.305,0.21,0.2,64.05826907742986]
["SL_ADMN2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,30.1731,null,0.305,0.21,0.2,57.17380026599999]
["SL_AW1","ESC1","SL_OHN2",null,null,"2005-10-01","ESC138626",null,1,0,0.048,null,null,1.048]
["SL_AW1","ESC1","SL_OHN2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.048,null,null,1.075248]
["SL_AW1","ESC1","SL_OHN2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.048,null,null,1.103204448]
["SL_AW1","ESC1","SL_OHN2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.048,null,null,1.13188776784]
["SL_AW2","ESC2","SL_OHN2",null,null,"2006-10-01","ESC238991",null,1,0.023,0.048,null,null,1.072104]
["SL_AW2","ESC2","SL_OHN2",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.048,null,null,1.096762392]
["SL_AW2","ESC2","SL_OHN2",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.048,null,null,1.1219877520000001]
["SL_AW2","ESC2","SL_OHN2",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.048,null,null,1.1477937040000001]
["SL_AW2","ESC2","SL_OHN2",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.048,null,null,1.1741928240000001]
["SL_AW2","ESC2","SL_OHN2",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.048,null,null,1.1741928240000001]
["SL_AW2","ESC2","SL_OHN2",null,null,"2012-10-01","ESC241183",null,1,null,0.048,null,null,1.048]
["SL_AWARD","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SL_AWARD","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SL_AWARD","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SL_AWARD","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SL_AWARD","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SL_AWARD","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SL_AWFX","SL_OH2",{"$nulls":4},"SL_OH2",null,1,0.06,null,null,null,1.06]
["SL_AWFX1","SL_OHN2",{"$nulls":4},"SL_OHN2",null,1,0.048,null,null,null,1.048]
["SL_AWFX2","SL_OHN2",{"$nulls":4},"SL_OHN2",null,1,0.048,null,null,null,1.048]
["SL_AWFY",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_AWFY1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_AWFY2",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_AWGC","ESC_CF","SL_OH2",null,null,"2004-10-01","ESC_CF38261",null,1,0,0.06,null,null,1.06]
["SL_AWGC","ESC_CF","SL_OH2",null,null,"2005-10-01","ESC_CF38626",null,1,0.03,0.06,null,null,1.0918]
["SL_AWGC","ESC_CF","SL_OH2",null,null,"2006-10-01","ESC_CF38991",null,1,0.08,0.06,null,null,1.1448]
["SL_AWGC","ESC_CF","SL_OH2",null,null,"2007-10-01","ESC_CF39356",null,1,0.19,0.06,null,null,1.2614]
["SL_AWGC","ESC_CF","SL_OH2",null,null,"2008-10-01","ESC_CF39722",null,1,0.3,0.06,null,null,1.3780000000000001]
["SL_AWGC","ESC_CF","SL_OH2",null,null,"2009-10-01","ESC_CF40087",null,1,0.41,0.06,null,null,1.4946]
["SL_AWGC1","ESC_CF","SL_OHN2",null,null,"2004-10-01","ESC_CF38261",null,1,0,0.048,null,null,1.048]
["SL_AWGC1","ESC_CF","SL_OHN2",null,null,"2005-10-01","ESC_CF38626",null,1,0.03,0.048,null,null,1.0794400000000002]
["SL_AWGC1","ESC_CF","SL_OHN2",null,null,"2006-10-01","ESC_CF38991",null,1,0.08,0.048,null,null,1.1318400000000002]
["SL_AWGC1","ESC_CF","SL_OHN2",null,null,"2007-10-01","ESC_CF39356",null,1,0.19,0.048,null,null,1.24712]
["SL_AWGC1","ESC_CF","SL_OHN2",null,null,"2008-10-01","ESC_CF39722",null,1,0.3,0.048,null,null,1.3624]
["SL_AWGC1","ESC_CF","SL_OHN2",null,null,"2009-10-01","ESC_CF40087",null,1,0.41,0.048,null,null,1.4776799999999999]
["SL_AWGC2","ESC_CF","SL_OHN2",null,null,"2004-10-01","ESC_CF38261",null,1,0,0.048,null,null,1.048]
["SL_AWGC2","ESC_CF","SL_OHN2",null,null,"2005-10-01","ESC_CF38626",null,1,0.03,0.048,null,null,1.0794400000000002]
["SL_AWGC2","ESC_CF","SL_OHN2",null,null,"2006-10-01","ESC_CF38991",null,1,0.08,0.048,null,null,1.1318400000000002]
["SL_AWGC2","ESC_CF","SL_OHN2",null,null,"2007-10-01","ESC_CF39356",null,1,0.19,0.048,null,null,1.24712]
["SL_AWGC2","ESC_CF","SL_OHN2",null,null,"2008-10-01","ESC_CF39722",null,1,0.3,0.048,null,null,1.3624]
["SL_AWGC2","ESC_CF","SL_OHN2",null,null,"2009-10-01","ESC_CF40087",null,1,0.41,0.048,null,null,1.4776799999999999]
["SL_AWGX","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,1,0,null,null,null,1]
["SL_AWGX","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,1,0.03,null,null,null,1.03]
["SL_AWGX","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,1,0.08,null,null,null,1.08]
["SL_AWGX","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,1,0.19,null,null,null,1.19]
["SL_AWGX","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,1,0.3,null,null,null,1.3]
["SL_AWGX","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,1,0.41,null,null,null,1.41]
["SL_AWGX1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_AWGX2",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_AWXX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["SL_AWXX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["SL_AWXX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["SL_AWXX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["SL_AWXX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["SL_AWXX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["SL_AWXX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["SL_AWXX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["SL_AWXX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["SL_AWXX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["SL_AWXX2","ESC2",null,null,null,"2006-10-01","ESC238991",null,1,0.023,null,null,null,1.023]
["SL_AWXX2","ESC2",null,null,null,"2007-10-01","ESC239356",null,1,0.046529,null,null,null,1.046529]
["SL_AWXX2","ESC2",null,null,null,"2008-10-01","ESC239722",null,1,0.070599,null,null,null,1.070599]
["SL_AWXX2","ESC2",null,null,null,"2009-10-01","ESC240087",null,1,0.095223,null,null,null,1.095223]
["SL_AWXX2","ESC2",null,null,null,"2010-10-01","ESC240452",null,1,0.120413,null,null,null,1.120413]
["SL_AWXX2","ESC2",null,null,null,"2011-10-01","ESC240817",null,1,0.120413,null,null,null,1.120413]
["SL_AWXX2","ESC2",null,null,null,"2012-10-01","ESC241183",null,1,{"$nulls":4},1]
["SL_CCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,33.86,0,0.29,0.215,0.2,63.6845652]
["SL_CCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,33.86,0.029,0.29,0.215,0.2,65.53141759079999]
["SL_CCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,33.86,0.057812,0.29,0.215,0.2,67.3662972833424]
["SL_CCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,33.86,0.085315,0.29,0.215,0.2,69.117813880038]
["SL_CCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,33.86,0.113533,0.29,0.215,0.2,70.9148649408516]
["SL_CCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,33.86,0.142485,0.29,0.215,0.2,72.75866047252201]
["SL_CCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,33.86,0,0.305,0.21,0.2,64.1599596]
["SL_CCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,33.86,0.026,0.305,0.21,0.2,65.82811854959999]
["SL_CCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,33.86,0.052676,0.305,0.21,0.2,67.53964963188959]
["SL_CCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,33.86,0.08004558,0.305,0.21,0.2,69.29568077895857]
["SL_CCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,33.86,0.023,0.305,0.21,0.2,65.63563867079999]
["SL_CCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,33.86,0.046529,0.305,0.21,0.2,67.1452583602284]
["SL_CCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,33.86,0.070599,0.305,0.21,0.2,68.6895885878004]
["SL_CCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,33.86,0.095223,0.305,0.21,0.2,70.26946343299079]
["SL_CCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,33.86,0.120413,0.305,0.21,0.2,71.88565281531478]
["SL_CCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,33.86,0.120413,0.305,0.21,0.2,71.88565281531478]
["SL_CCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,33.86,null,0.305,0.21,0.2,64.1599596]
["SL_CE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,58.14,0,0.29,0.215,0.2,109.3508748]
["SL_CE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,58.14,0.029,0.29,0.215,0.2,112.52205016919999]
["SL_CE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,58.14,0.057812,0.29,0.215,0.2,115.6726675739376]
["SL_CE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,58.14,0.085315,0.29,0.215,0.2,118.680144683562]
["SL_CE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,58.14,0.113533,0.29,0.215,0.2,121.7658076686684]
["SL_CE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,58.14,0.142485,0.29,0.215,0.2,124.931734195878]
["SL_CE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,58.14,0,0.305,0.21,0.2,110.16716039999999]
["SL_CE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,58.14,0.026,0.305,0.21,0.2,113.0315065704]
["SL_CE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,58.14,0.052676,0.305,0.21,0.2,115.97032574123038]
["SL_CE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,58.14,0.08004558,0.305,0.21,0.2,118.98555465117103]
["SL_CE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,58.14,0.023,0.305,0.21,0.2,112.70100508919998]
["SL_CE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,58.14,0.046529,0.305,0.21,0.2,115.29312820625158]
["SL_CE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,58.14,0.070599,0.305,0.21,0.2,117.9448517570796]
["SL_CE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,58.14,0.095223,0.305,0.21,0.2,120.65760791476919]
["SL_CE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,58.14,0.120413,0.305,0.21,0.2,123.43271868524519]
["SL_CE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,58.14,0.120413,0.305,0.21,0.2,123.43271868524519]
["SL_CE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,58.14,null,0.305,0.21,0.2,110.16716039999999]
["SL_CP","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,47.01,0,0.29,0.215,0.2,88.41734819999999]
["SL_CP","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,47.01,0.029,0.29,0.215,0.2,90.9814512978]
["SL_CP","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,47.01,0.057812,0.29,0.215,0.2,93.5289319341384]
["SL_CP","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,47.01,0.085315,0.29,0.215,0.2,95.96067426168301]
["SL_CP","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,47.01,0.113533,0.29,0.215,0.2,98.4556349931906]
["SL_CP","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,47.01,0.142485,0.29,0.215,0.2,101.015494058277]
["SL_CP1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,42.39,0,0.305,0.21,0.2,80.32311539999999]
["SL_CP1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,42.39,0.026,0.305,0.21,0.2,82.4115164004]
["SL_CP1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,42.39,0.052676,0.305,0.21,0.2,84.55421582681039]
["SL_CP1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,42.39,0.08004558,0.305,0.21,0.2,86.75262575959991]
["SL_CP2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,42.39,0.023,0.305,0.21,0.2,82.1705470542]
["SL_CP2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,42.39,0.046529,0.305,0.21,0.2,84.0604696364466]
["SL_CP2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,42.39,0.070599,0.305,0.21,0.2,85.99384702412459]
["SL_CP2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,42.39,0.095223,0.305,0.21,0.2,87.9717234177342]
["SL_CP2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,42.39,0.120413,0.305,0.21,0.2,89.9950626946602]
["SL_CP2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,42.39,0.120413,0.305,0.21,0.2,89.9950626946602]
["SL_CP2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,42.39,null,0.305,0.21,0.2,80.32311539999999]
["SL_CPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,30.93,0,0.29,0.215,0.2,58.1737626]
["SL_CPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,30.93,0.029,0.29,0.215,0.2,59.860801715399994]
["SL_CPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,30.93,0.057812,0.29,0.215,0.2,61.5369041634312]
["SL_CPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,30.93,0.085315,0.29,0.215,0.2,63.136857156219]
["SL_CPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,30.93,0.113533,0.29,0.215,0.2,64.7784043892658]
["SL_CPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,30.93,0.142485,0.29,0.215,0.2,66.46265116406099]
["SL_CPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,30.93,0,0.305,0.21,0.2,58.608019799999994]
["SL_CPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,30.93,0.026,0.305,0.21,0.2,60.13182831479999]
["SL_CPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,30.93,0.052676,0.305,0.21,0.2,61.695255850984786]
["SL_CPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,30.93,0.08004558,0.305,0.21,0.2,63.29933273754247]
["SL_CPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,30.93,0.023,0.305,0.21,0.2,59.956004255399996]
["SL_CPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,30.93,0.046529,0.305,0.21,0.2,61.334992353274195]
["SL_CPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,30.93,0.070599,0.305,0.21,0.2,62.74568738986019]
["SL_CPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,30.93,0.095223,0.305,0.21,0.2,64.1888512694154]
["SL_CPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,30.93,0.120413,0.305,0.21,0.2,65.6651872881774]
["SL_CPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,30.93,0.120413,0.305,0.21,0.2,65.6651872881774]
["SL_CPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,30.93,null,0.305,0.21,0.2,58.608019799999994]
["SL_CRA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,24.14,0,0.29,0.215,0.2,45.4029948]
["SL_CRA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,24.14,0.029,0.29,0.215,0.2,46.719681649200005]
["SL_CRA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,24.14,0.057812,0.29,0.215,0.2,48.02783273537761]
["SL_CRA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,24.14,0.085315,0.29,0.215,0.2,49.276551301362005]
["SL_CRA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,24.14,0.113533,0.29,0.215,0.2,50.557733008628404]
["SL_CRA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,24.14,0.142485,0.29,0.215,0.2,51.872240514078]
["SL_CRA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,27.19,0,0.305,0.21,0.2,51.5212434]
["SL_CRA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,27.19,0.026,0.305,0.21,0.2,52.860795728399985]
["SL_CRA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,27.19,0.052676,0.305,0.21,0.2,54.235176417338394]
["SL_CRA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,27.19,0.08004558,0.305,0.21,0.2,55.645291210274166]
["SL_CRA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,27.19,0.023,0.305,0.21,0.2,52.706231998199996]
["SL_CRA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,27.19,0.046529,0.305,0.21,0.2,53.9184753341586]
["SL_CRA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,27.19,0.070599,0.305,0.21,0.2,55.1585916627966]
["SL_CRA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,27.19,0.095223,0.305,0.21,0.2,56.427250760278206]
["SL_CRA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,27.19,0.120413,0.305,0.21,0.2,57.7250708815242]
["SL_CRA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,27.19,0.120413,0.305,0.21,0.2,57.7250708815242]
["SL_CRA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,27.19,null,0.305,0.21,0.2,51.5212434]
["SL_CRM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,30.93,0,0.29,0.215,0.2,58.1737626]
["SL_CRM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,30.93,0.029,0.29,0.215,0.2,59.860801715399994]
["SL_CRM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,30.93,0.057812,0.29,0.215,0.2,61.5369041634312]
["SL_CRM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,30.93,0.085315,0.29,0.215,0.2,63.136857156219]
["SL_CRM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,30.93,0.113533,0.29,0.215,0.2,64.7784043892658]
["SL_CRM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,30.93,0.142485,0.29,0.215,0.2,66.46265116406099]
["SL_CRM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,30.93,0,0.305,0.21,0.2,58.608019799999994]
["SL_CRM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,30.93,0.026,0.305,0.21,0.2,60.13182831479999]
["SL_CRM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,30.93,0.052676,0.305,0.21,0.2,61.695255850984786]
["SL_CRM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,30.93,0.08004558,0.305,0.21,0.2,63.29933273754247]
["SL_CRM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,59.74,0.023,0.305,0.21,0.2,115.80251193719998]
["SL_CRM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,59.74,0.046529,0.305,0.21,0.2,118.46596971175559]
["SL_CRM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,59.74,0.070599,0.305,0.21,0.2,121.19066811090359]
["SL_CRM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,59.74,0.095223,0.305,0.21,0.2,123.9780787208172]
["SL_CRM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,59.74,0.120413,0.305,0.21,0.2,126.82955992873318]
["SL_CRM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,59.74,0.120413,0.305,0.21,0.2,126.82955992873318]
["SL_CRM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,59.74,null,0.305,0.21,0.2,113.1989364]
["SL_CT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,31.83,0,0.29,0.215,0.2,59.866500599999995]
["SL_CT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,31.83,0.029,0.29,0.215,0.2,61.60262911739999]
["SL_CT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,31.83,0.057812,0.29,0.215,0.2,63.327502732687186]
["SL_CT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,31.83,0.085315,0.29,0.215,0.2,64.974011098689]
["SL_CT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,31.83,0.113533,0.29,0.215,0.2,66.66332401261978]
["SL_CT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,31.83,0.142485,0.29,0.215,0.2,68.396578937991]
["SL_CT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,31.83,0,0.305,0.21,0.2,60.313393799999986]
["SL_CT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,31.83,0.026,0.305,0.21,0.2,61.88154203879998]
["SL_CT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,31.83,0.052676,0.305,0.21,0.2,63.49046213180878]
["SL_CT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,31.83,0.08004558,0.305,0.21,0.2,65.14121438848939]
["SL_CT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,31.83,0.023,0.305,0.21,0.2,61.70060185739999]
["SL_CT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,31.83,0.046529,0.305,0.21,0.2,63.119715700120196]
["SL_CT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,31.83,0.070599,0.305,0.21,0.2,64.57145908888619]
["SL_CT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,31.83,0.095223,0.305,0.21,0.2,66.0566160978174]
["SL_CT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,31.83,0.120413,0.305,0.21,0.2,67.57591048763939]
["SL_CT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,31.83,0.120413,0.305,0.21,0.2,67.57591048763939]
["SL_CT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,31.83,null,0.305,0.21,0.2,60.313393799999986]
["SL_EE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,58.14,0,0.29,0.215,0.2,109.3508748]
["SL_EE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,58.14,0.029,0.29,0.215,0.2,112.52205016919999]
["SL_EE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,58.14,0.057812,0.29,0.215,0.2,115.6726675739376]
["SL_EE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,58.14,0.085315,0.29,0.215,0.2,118.680144683562]
["SL_EE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,58.14,0.113533,0.29,0.215,0.2,121.7658076686684]
["SL_EE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,58.14,0.142485,0.29,0.215,0.2,124.931734195878]
["SL_EE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,47.95,0,0.305,0.21,0.2,90.858537]
["SL_EE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,47.95,0.026,0.305,0.21,0.2,93.22085896200001]
["SL_EE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,47.95,0.052676,0.305,0.21,0.2,95.64460129501198]
["SL_EE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,47.95,0.08004558,0.305,0.21,0.2,98.13136129211645]
["SL_EE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,47.95,0.023,0.305,0.21,0.2,92.948283351]
["SL_EE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,47.95,0.046529,0.305,0.21,0.2,95.08609386807301]
["SL_EE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,47.95,0.070599,0.305,0.21,0.2,97.27305885366299]
["SL_EE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,47.95,0.095223,0.305,0.21,0.2,99.51035946875102]
["SL_EE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,47.95,0.120413,0.305,0.21,0.2,101.79908601578101]
["SL_EE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,47.95,0.120413,0.305,0.21,0.2,101.79908601578101]
["SL_EE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,47.95,null,0.305,0.21,0.2,90.858537]
["SL_ESH2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,65.71,0.023,0.305,0.21,0.2,127.37500936379998]
["SL_ESH2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,65.71,0.046529,0.305,0.21,0.2,130.30463457916738]
["SL_ESH2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,65.71,0.070599,0.305,0.21,0.2,133.30162038110936]
["SL_ESH2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,65.71,0.095223,0.305,0.21,0.2,136.36758541588378]
["SL_ESH2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,65.71,0.120413,0.305,0.21,0.2,139.50402381849779]
["SL_ESH2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,65.71,0.120413,0.305,0.21,0.2,139.50402381849779]
["SL_ESH2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,65.71,null,0.305,0.21,0.2,124.51125059999998]
["SL_FA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,40.7,0,0.29,0.215,0.2,76.54937400000001]
["SL_FA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,40.7,0.029,0.29,0.215,0.2,78.769305846]
["SL_FA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,40.7,0.057812,0.29,0.215,0.2,80.97484640968801]
["SL_FA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,40.7,0.085315,0.29,0.215,0.2,83.08018384281002]
["SL_FA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,40.7,0.113533,0.29,0.215,0.2,85.24025407834199]
["SL_FA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,40.7,0.142485,0.29,0.215,0.2,87.45651155439002]
["SL_FA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,46.24,0,0.305,0.21,0.2,87.61832639999999]
["SL_FA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,46.24,0.026,0.305,0.21,0.2,89.8964028864]
["SL_FA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,46.24,0.052676,0.305,0.21,0.2,92.2337093614464]
["SL_FA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,46.24,0.08004558,0.305,0.21,0.2,94.6317861553173]
["SL_FA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,46.24,0.023,0.305,0.21,0.2,89.63354790719998]
["SL_FA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,46.24,0.046529,0.305,0.21,0.2,91.69511950906559]
["SL_FA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,46.24,0.070599,0.305,0.21,0.2,93.8040926255136]
["SL_FA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,46.24,0.095223,0.305,0.21,0.2,95.96160629478719]
["SL_FA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,46.24,0.120413,0.305,0.21,0.2,98.1687119368032]
["SL_FA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,46.24,0.120413,0.305,0.21,0.2,98.1687119368032]
["SL_FA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,46.24,null,0.305,0.21,0.2,87.61832639999999]
["SL_GCAW","ESC_CF","SL_OH2",null,null,"2004-10-01","ESC_CF38261",null,null,0,0.06,null,null,0]
["SL_GCAW","ESC_CF","SL_OH2",null,null,"2005-10-01","ESC_CF38626",null,null,0.03,0.06,null,null,0]
["SL_GCAW","ESC_CF","SL_OH2",null,null,"2006-10-01","ESC_CF38991",null,null,0.08,0.06,null,null,0]
["SL_GCAW","ESC_CF","SL_OH2",null,null,"2007-10-01","ESC_CF39356",null,null,0.19,0.06,null,null,0]
["SL_GCAW","ESC_CF","SL_OH2",null,null,"2008-10-01","ESC_CF39722",null,null,0.3,0.06,null,null,0]
["SL_GCAW","ESC_CF","SL_OH2",null,null,"2009-10-01","ESC_CF40087",null,null,0.41,0.06,null,null,0]
["SL_GCAW1","ESC_CF","SL_OHN2",null,null,"2004-10-01","ESC_CF38261",null,null,0,0.048,null,null,0]
["SL_GCAW1","ESC_CF","SL_OHN2",null,null,"2005-10-01","ESC_CF38626",null,null,0.03,0.048,null,null,0]
["SL_GCAW1","ESC_CF","SL_OHN2",null,null,"2006-10-01","ESC_CF38991",null,null,0.08,0.048,null,null,0]
["SL_GCAW1","ESC_CF","SL_OHN2",null,null,"2007-10-01","ESC_CF39356",null,null,0.19,0.048,null,null,0]
["SL_GCAW1","ESC_CF","SL_OHN2",null,null,"2008-10-01","ESC_CF39722",null,null,0.3,0.048,null,null,0]
["SL_GCAW1","ESC_CF","SL_OHN2",null,null,"2009-10-01","ESC_CF40087",null,null,0.41,0.048,null,null,0]
["SL_GCAW2","ESC_CF","SL_OHN2",null,null,"2004-10-01","ESC_CF38261",null,null,0,0.048,null,null,0]
["SL_GCAW2","ESC_CF","SL_OHN2",null,null,"2005-10-01","ESC_CF38626",null,null,0.03,0.048,null,null,0]
["SL_GCAW2","ESC_CF","SL_OHN2",null,null,"2006-10-01","ESC_CF38991",null,null,0.08,0.048,null,null,0]
["SL_GCAW2","ESC_CF","SL_OHN2",null,null,"2007-10-01","ESC_CF39356",null,null,0.19,0.048,null,null,0]
["SL_GCAW2","ESC_CF","SL_OHN2",null,null,"2008-10-01","ESC_CF39722",null,null,0.3,0.048,null,null,0]
["SL_GCAW2","ESC_CF","SL_OHN2",null,null,"2009-10-01","ESC_CF40087",null,null,0.41,0.048,null,null,0]
["SL_GCAX","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,null,0,null,null,null,0]
["SL_GCAX","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,null,0.03,null,null,null,0]
["SL_GCAX","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,null,0.08,null,null,null,0]
["SL_GCAX","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,null,0.19,null,null,null,0]
["SL_GCAX","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,null,0.3,null,null,null,0]
["SL_GCAX","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,null,0.41,null,null,null,0]
["SL_GCAX1","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,null,0,null,null,null,0]
["SL_GCAX1","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,null,0.03,null,null,null,0]
["SL_GCAX1","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,null,0.08,null,null,null,0]
["SL_GCAX1","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,null,0.19,null,null,null,0]
["SL_GCAX1","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,null,0.3,null,null,null,0]
["SL_GCAX1","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,null,0.41,null,null,null,0]
["SL_GCAX2","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,null,0,null,null,null,0]
["SL_GCAX2","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,null,0.03,null,null,null,0]
["SL_GCAX2","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,null,0.08,null,null,null,0]
["SL_GCAX2","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,null,0.19,null,null,null,0]
["SL_GCAX2","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,null,0.3,null,null,null,0]
["SL_GCAX2","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,null,0.41,null,null,null,0]
["SL_GCFX1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_GCFX2",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_GCSS","ESC_CF","SL_OH2",null,null,"2004-10-01","ESC_CF38261",null,1,0,0.06,null,null,1.06]
["SL_GCSS","ESC_CF","SL_OH2",null,null,"2005-10-01","ESC_CF38626",null,1,0.03,0.06,null,null,1.0918]
["SL_GCSS","ESC_CF","SL_OH2",null,null,"2006-10-01","ESC_CF38991",null,1,0.08,0.06,null,null,1.1448]
["SL_GCSS","ESC_CF","SL_OH2",null,null,"2007-10-01","ESC_CF39356",null,1,0.19,0.06,null,null,1.2614]
["SL_GCSS","ESC_CF","SL_OH2",null,null,"2008-10-01","ESC_CF39722",null,1,0.3,0.06,null,null,1.3780000000000001]
["SL_GCSS","ESC_CF","SL_OH2",null,null,"2009-10-01","ESC_CF40087",null,1,0.41,0.06,null,null,1.4946]
["SL_GCSS1","ESC_CF","SL_OHN2",null,null,"2004-10-01","ESC_CF38261",null,1,0,0.048,null,null,1.048]
["SL_GCSS1","ESC_CF","SL_OHN2",null,null,"2005-10-01","ESC_CF38626",null,1,0.03,0.048,null,null,1.0794400000000002]
["SL_GCSS1","ESC_CF","SL_OHN2",null,null,"2006-10-01","ESC_CF38991",null,1,0.08,0.048,null,null,1.1318400000000002]
["SL_GCSS1","ESC_CF","SL_OHN2",null,null,"2007-10-01","ESC_CF39356",null,1,0.19,0.048,null,null,1.24712]
["SL_GCSS1","ESC_CF","SL_OHN2",null,null,"2008-10-01","ESC_CF39722",null,1,0.3,0.048,null,null,1.3624]
["SL_GCSS1","ESC_CF","SL_OHN2",null,null,"2009-10-01","ESC_CF40087",null,1,0.41,0.048,null,null,1.4776799999999999]
["SL_GCSS2","ESC_CF","SL_OHN2",null,null,"2004-10-01","ESC_CF38261",null,1,0,0.048,null,null,1.048]
["SL_GCSS2","ESC_CF","SL_OHN2",null,null,"2005-10-01","ESC_CF38626",null,1,0.03,0.048,null,null,1.0794400000000002]
["SL_GCSS2","ESC_CF","SL_OHN2",null,null,"2006-10-01","ESC_CF38991",null,1,0.08,0.048,null,null,1.1318400000000002]
["SL_GCSS2","ESC_CF","SL_OHN2",null,null,"2007-10-01","ESC_CF39356",null,1,0.19,0.048,null,null,1.24712]
["SL_GCSS2","ESC_CF","SL_OHN2",null,null,"2008-10-01","ESC_CF39722",null,1,0.3,0.048,null,null,1.3624]
["SL_GCSS2","ESC_CF","SL_OHN2",null,null,"2009-10-01","ESC_CF40087",null,1,0.41,0.048,null,null,1.4776799999999999]
["SL_GCSX","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,1,0,null,null,null,1]
["SL_GCSX","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,1,0.03,null,null,null,1.03]
["SL_GCSX","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,1,0.08,null,null,null,1.08]
["SL_GCSX","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,1,0.19,null,null,null,1.19]
["SL_GCSX","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,1,0.3,null,null,null,1.3]
["SL_GCSX","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,1,0.41,null,null,null,1.41]
["SL_GCSX1","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,1,0,null,null,null,1]
["SL_GCSX1","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,1,0.03,null,null,null,1.03]
["SL_GCSX1","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,1,0.08,null,null,null,1.08]
["SL_GCSX1","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,1,0.19,null,null,null,1.19]
["SL_GCSX1","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,1,0.3,null,null,null,1.3]
["SL_GCSX1","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,1,0.41,null,null,null,1.41]
["SL_GCSX2","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,1,0,null,null,null,1]
["SL_GCSX2","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,1,0.03,null,null,null,1.03]
["SL_GCSX2","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,1,0.08,null,null,null,1.08]
["SL_GCSX2","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,1,0.19,null,null,null,1.19]
["SL_GCSX2","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,1,0.3,null,null,null,1.3]
["SL_GCSX2","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,1,0.41,null,null,null,1.41]
["SL_IPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_IPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_IPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_IPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_IPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_IPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_IPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,54.62,0,0.305,0.21,0.2,103.49725319999999]
["SL_IPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,54.62,0.026,0.305,0.21,0.2,106.18818178319998]
["SL_IPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,54.62,0.052676,0.305,0.21,0.2,108.94907450956318]
["SL_IPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,54.62,0.08004558,0.305,0.21,0.2,111.78175086080083]
["SL_IPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,54.62,0.023,0.305,0.21,0.2,105.87769002359997]
["SL_IPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,54.62,0.046529,0.305,0.21,0.2,108.31287689414279]
["SL_IPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,54.62,0.070599,0.305,0.21,0.2,110.80405577866678]
["SL_IPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,54.62,0.095223,0.305,0.21,0.2,113.3525721414636]
["SL_IPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,54.62,0.120413,0.305,0.21,0.2,115.95966794957158]
["SL_IPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,54.62,0.120413,0.305,0.21,0.2,115.95966794957158]
["SL_IPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,54.62,null,0.305,0.21,0.2,103.49725319999999]
["SL_KCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,33.86,0,0.29,0.215,0.2,63.6845652]
["SL_KCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,33.86,0.029,0.29,0.215,0.2,65.53141759079999]
["SL_KCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,33.86,0.057812,0.29,0.215,0.2,67.3662972833424]
["SL_KCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,33.86,0.085315,0.29,0.215,0.2,69.117813880038]
["SL_KCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,33.86,0.113533,0.29,0.215,0.2,70.9148649408516]
["SL_KCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,33.86,0.142485,0.29,0.215,0.2,72.75866047252201]
["SL_KCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,33.86,0,0.305,0.21,0.2,64.1599596]
["SL_KCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,33.86,0.026,0.305,0.21,0.2,65.82811854959999]
["SL_KCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,33.86,0.052676,0.305,0.21,0.2,67.53964963188959]
["SL_KCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,33.86,0.08004558,0.305,0.21,0.2,69.29568077895857]
["SL_KCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,33.86,0.023,0.305,0.21,0.2,65.63563867079999]
["SL_KCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,33.86,0.046529,0.305,0.21,0.2,67.1452583602284]
["SL_KCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,33.86,0.070599,0.305,0.21,0.2,68.6895885878004]
["SL_KCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,33.86,0.095223,0.305,0.21,0.2,70.26946343299079]
["SL_KCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,33.86,0.120413,0.305,0.21,0.2,71.88565281531478]
["SL_KCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,33.86,0.120413,0.305,0.21,0.2,71.88565281531478]
["SL_KCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,33.86,null,0.305,0.21,0.2,64.1599596]
["SL_KE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,58.14,0,0.29,0.215,0.2,109.3508748]
["SL_KE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,58.14,0.029,0.29,0.215,0.2,112.52205016919999]
["SL_KE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,58.14,0.057812,0.29,0.215,0.2,115.6726675739376]
["SL_KE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,58.14,0.085315,0.29,0.215,0.2,118.680144683562]
["SL_KE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,58.14,0.113533,0.29,0.215,0.2,121.7658076686684]
["SL_KE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,58.14,0.142485,0.29,0.215,0.2,124.931734195878]
["SL_KE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,58.14,0,0.305,0.21,0.2,110.16716039999999]
["SL_KE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,58.14,0.026,0.305,0.21,0.2,113.0315065704]
["SL_KE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,58.14,0.052676,0.305,0.21,0.2,115.97032574123038]
["SL_KE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,58.14,0.08004558,0.305,0.21,0.2,118.98555465117103]
["SL_KE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,58.14,0.023,0.305,0.21,0.2,112.70100508919998]
["SL_KE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,58.14,0.046529,0.305,0.21,0.2,115.29312820625158]
["SL_KE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,58.14,0.070599,0.305,0.21,0.2,117.9448517570796]
["SL_KE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,58.14,0.095223,0.305,0.21,0.2,120.65760791476919]
["SL_KE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,58.14,0.120413,0.305,0.21,0.2,123.43271868524519]
["SL_KE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,58.14,0.120413,0.305,0.21,0.2,123.43271868524519]
["SL_KE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,58.14,null,0.305,0.21,0.2,110.16716039999999]
["SL_KT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,31.83,0,0.29,0.215,0.2,59.866500599999995]
["SL_KT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,31.83,0.029,0.29,0.215,0.2,61.60262911739999]
["SL_KT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,31.83,0.057812,0.29,0.215,0.2,63.327502732687186]
["SL_KT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,31.83,0.085315,0.29,0.215,0.2,64.974011098689]
["SL_KT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,31.83,0.113533,0.29,0.215,0.2,66.66332401261978]
["SL_KT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,31.83,0.142485,0.29,0.215,0.2,68.396578937991]
["SL_KT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,31.83,0,0.305,0.21,0.2,60.313393799999986]
["SL_KT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,31.83,0.026,0.305,0.21,0.2,61.88154203879998]
["SL_KT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,31.83,0.052676,0.305,0.21,0.2,63.49046213180878]
["SL_KT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,31.83,0.08004558,0.305,0.21,0.2,65.14121438848939]
["SL_KT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,31.83,0.023,0.305,0.21,0.2,61.70060185739999]
["SL_KT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,31.83,0.046529,0.305,0.21,0.2,63.119715700120196]
["SL_KT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,31.83,0.070599,0.305,0.21,0.2,64.57145908888619]
["SL_KT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,31.83,0.095223,0.305,0.21,0.2,66.0566160978174]
["SL_KT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,31.83,0.120413,0.305,0.21,0.2,67.57591048763939]
["SL_KT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,31.83,0.120413,0.305,0.21,0.2,67.57591048763939]
["SL_KT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,31.83,null,0.305,0.21,0.2,60.313393799999986]
["SL_LPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_LPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_LPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_LPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_LPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_LPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_LPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,54.62,0,0.305,0.21,0.2,103.49725319999999]
["SL_LPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,54.62,0.026,0.305,0.21,0.2,106.18818178319998]
["SL_LPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,54.62,0.052676,0.305,0.21,0.2,108.94907450956318]
["SL_LPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,54.62,0.08004558,0.305,0.21,0.2,111.78175086080083]
["SL_LPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,54.62,0.023,0.305,0.21,0.2,105.87769002359997]
["SL_LPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,54.62,0.046529,0.305,0.21,0.2,108.31287689414279]
["SL_LPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,54.62,0.070599,0.305,0.21,0.2,110.80405577866678]
["SL_LPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,54.62,0.095223,0.305,0.21,0.2,113.3525721414636]
["SL_LPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,54.62,0.120413,0.305,0.21,0.2,115.95966794957158]
["SL_LPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,54.62,0.120413,0.305,0.21,0.2,115.95966794957158]
["SL_LPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,54.62,null,0.305,0.21,0.2,103.49725319999999]
["SL_MDD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,32.42,0,0.29,0.215,0.2,60.97618440000001]
["SL_MDD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,32.42,0.029,0.29,0.215,0.2,62.7444937476]
["SL_MDD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,32.42,0.057812,0.29,0.215,0.2,64.5013395725328]
["SL_MDD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,32.42,0.085315,0.29,0.215,0.2,66.17836757208602]
["SL_MDD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,32.42,0.113533,0.29,0.215,0.2,67.8989935434852]
["SL_MDD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,32.42,0.142485,0.29,0.215,0.2,69.66437603423401]
["SL_MDD1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,43.07,0,0.305,0.21,0.2,81.61162019999999]
["SL_MDD1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,43.07,0.026,0.305,0.21,0.2,83.7335223252]
["SL_MDD1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,43.07,0.052676,0.305,0.21,0.2,85.91059390565519]
["SL_MDD1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,43.07,0.08004558,0.305,0.21,0.2,88.1442696736487]
["SL_MDD2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,43.07,0.023,0.305,0.21,0.2,83.48868746459999]
["SL_MDD2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,43.07,0.046529,0.305,0.21,0.2,85.4089272762858]
["SL_MDD2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,43.07,0.070599,0.305,0.21,0.2,87.37331897449978]
["SL_MDD2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,43.07,0.095223,0.305,0.21,0.2,89.3829235103046]
["SL_MDD2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,43.07,0.120413,0.305,0.21,0.2,91.4387202231426]
["SL_MDD2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,43.07,0.120413,0.305,0.21,0.2,91.4387202231426]
["SL_MDD2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,43.07,null,0.305,0.21,0.2,81.61162019999999]
["SL_ME","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_ME","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_ME","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_ME","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_ME","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_ME","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_ME1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,51.37,0,0.305,0.21,0.2,97.33895819999998]
["SL_ME1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,51.37,0.026,0.305,0.21,0.2,99.86977111319999]
["SL_ME1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,51.37,0.052676,0.305,0.21,0.2,102.46638516214317]
["SL_ME1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,51.37,0.08004558,0.305,0.21,0.2,105.13051156571474]
["SL_ME2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,51.37,0.023,0.305,0.21,0.2,99.57775423859998]
["SL_ME2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,51.37,0.046529,0.305,0.21,0.2,101.8680425860878]
["SL_ME2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,51.37,0.070599,0.305,0.21,0.2,104.2109913099618]
["SL_ME2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,51.37,0.095223,0.305,0.21,0.2,106.6078658166786]
["SL_ME2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,51.37,0.120413,0.305,0.21,0.2,109.05983417373658]
["SL_ME2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,51.37,0.120413,0.305,0.21,0.2,109.05983417373658]
["SL_ME2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,51.37,null,0.305,0.21,0.2,97.33895819999998]
["SL_MES","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,46.68,0,0.29,0.215,0.2,87.7966776]
["SL_MES","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,46.68,0.029,0.29,0.215,0.2,90.3427812504]
["SL_MES","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,46.68,0.057812,0.29,0.215,0.2,92.8723791254112]
["SL_MES","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,46.68,0.085315,0.29,0.215,0.2,95.28705114944401]
["SL_MES","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,46.68,0.113533,0.29,0.215,0.2,97.76449779796079]
["SL_MES","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,46.68,0.142485,0.29,0.215,0.2,100.306387207836]
["SL_MES1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,41.3,0,0.305,0.21,0.2,78.257718]
["SL_MES1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,41.3,0.026,0.305,0.21,0.2,80.292418668]
["SL_MES1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,41.3,0.052676,0.305,0.21,0.2,82.380021553368]
["SL_MES1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,41.3,0.08004558,0.305,0.21,0.2,84.52190242678643]
["SL_MES2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,41.3,0.023,0.305,0.21,0.2,80.05764551399999]
["SL_MES2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,41.3,0.046529,0.305,0.21,0.2,81.89897136082199]
["SL_MES2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,41.3,0.070599,0.305,0.21,0.2,83.782634633082]
["SL_MES2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,41.3,0.095223,0.305,0.21,0.2,85.70965268111398]
["SL_MES2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,41.3,0.120413,0.305,0.21,0.2,87.68096459753399]
["SL_MES2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,41.3,0.120413,0.305,0.21,0.2,87.68096459753399]
["SL_MES2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,41.3,null,0.305,0.21,0.2,78.257718]
["SL_MFAT","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2003-10-01","ESC37895",null,66.3,0,0,0,0.2,79.55999999999999]
["SL_MFAT","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2004-10-01","ESC38261",null,66.3,0.029,0,0,0.2,81.86723999999998]
["SL_MFAT","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2005-10-01","ESC38626",null,66.3,0.057812,0,0,0.2,84.15952272]
["SL_MFAT","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2006-10-01","ESC38991",null,66.3,0.085315,0,0,0.2,86.34766139999999]
["SL_MFAT","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2007-10-01","ESC39356",null,66.3,0.113533,0,0,0.2,88.59268547999999]
["SL_MFAT","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2008-10-01","ESC39722",null,66.3,0.142485,0,0,0.2,90.89610659999998]
["SL_MFAT1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN1","2005-10-01","ESC138626",null,70,0,0,0,0.2,84]
["SL_MFAT1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN1","2006-10-01","ESC138991",null,70,0.026,0,0,0.2,86.18400000000001]
["SL_MFAT1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN1","2007-10-01","ESC139356",null,70,0.052676,0,0,0.2,88.424784]
["SL_MFAT1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN1","2008-10-01","ESC139722",null,70,0.08004558,0,0,0.2,90.72382871999999]
["SL_MFAT2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN1","2006-10-01","ESC238991",null,70,0.023,0,0,0.2,85.932]
["SL_MFAT2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN1","2007-10-01","ESC239356",null,70,0.046529,0,0,0.2,87.908436]
["SL_MFAT2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN1","2008-10-01","ESC239722",null,70,0.070599,0,0,0.2,89.93031599999999]
["SL_MFAT2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN1","2009-10-01","ESC240087",null,70,0.095223,0,0,0.2,91.998732]
["SL_MFAT2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN1","2010-10-01","ESC240452",null,70,0.120413,0,0,0.2,94.114692]
["SL_MFAT2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN1","2011-10-01","ESC240817",null,70,0.120413,0,0,0.2,94.114692]
["SL_MFAT2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN1","2012-10-01","ESC241183",null,70,null,0,0,0.2,84]
["SL_MFMS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2003-10-01","ESC37895",null,81.3,0,0,0,0.2,97.55999999999999]
["SL_MFMS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2004-10-01","ESC38261",null,81.3,0.029,0,0,0.2,100.38923999999999]
["SL_MFMS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2005-10-01","ESC38626",null,81.3,0.057812,0,0,0.2,103.20013872]
["SL_MFMS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2006-10-01","ESC38991",null,81.3,0.085315,0,0,0.2,105.88333139999999]
["SL_MFMS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2007-10-01","ESC39356",null,81.3,0.113533,0,0,0.2,108.63627947999998]
["SL_MFMS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2008-10-01","ESC39722",null,81.3,0.142485,0,0,0.2,111.4608366]
["SL_MFMS1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN1","2005-10-01","ESC138626",null,89.59,0,0,0,0.2,107.508]
["SL_MFMS1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN1","2006-10-01","ESC138991",null,89.59,0.026,0,0,0.2,110.303208]
["SL_MFMS1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN1","2007-10-01","ESC139356",null,89.59,0.052676,0,0,0.2,113.171091408]
["SL_MFMS1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN1","2008-10-01","ESC139722",null,89.59,0.08004558,0,0,0.2,116.11354021463998]
["SL_MFMS2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN1","2006-10-01","ESC238991",null,89.59,0.023,0,0,0.2,109.980684]
["SL_MFMS2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN1","2007-10-01","ESC239356",null,89.59,0.046529,0,0,0.2,112.510239732]
["SL_MFMS2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN1","2008-10-01","ESC239722",null,89.59,0.070599,0,0,0.2,115.097957292]
["SL_MFMS2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN1","2009-10-01","ESC240087",null,89.59,0.095223,0,0,0.2,117.745234284]
["SL_MFMS2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN1","2010-10-01","ESC240452",null,89.59,0.120413,0,0,0.2,120.45336080400001]
["SL_MFMS2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN1","2011-10-01","ESC240817",null,89.59,0.120413,0,0,0.2,120.45336080400001]
["SL_MFMS2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN1","2012-10-01","ESC241183",null,89.59,null,0,0,0.2,107.508]
["SL_MFPC","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2003-10-01","ESC37895",null,129.8,0,0,0,0.2,155.76000000000002]
["SL_MFPC","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2004-10-01","ESC38261",null,129.8,0.029,0,0,0.2,160.27704]
["SL_MFPC","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2005-10-01","ESC38626",null,129.8,0.057812,0,0,0.2,164.76479712]
["SL_MFPC","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2006-10-01","ESC38991",null,129.8,0.085315,0,0,0.2,169.04866440000004]
["SL_MFPC","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2007-10-01","ESC39356",null,129.8,0.113533,0,0,0.2,173.44390007999996]
["SL_MFPC","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2008-10-01","ESC39722",null,129.8,0.142485,0,0,0.2,177.9534636]
["SL_MFPC1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN1","2005-10-01","ESC138626",null,140.65,0,0,0,0.2,168.78]
["SL_MFPC1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN1","2006-10-01","ESC138991",null,140.65,0.026,0,0,0.2,173.16828]
["SL_MFPC1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN1","2007-10-01","ESC139356",null,140.65,0.052676,0,0,0.2,177.67065527999998]
["SL_MFPC1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN1","2008-10-01","ESC139722",null,140.65,0.08004558,0,0,0.2,182.29009299240002]
["SL_MFPC2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN1","2006-10-01","ESC238991",null,140.65,0.023,0,0,0.2,172.66194]
["SL_MFPC2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN1","2007-10-01","ESC239356",null,140.65,0.046529,0,0,0.2,176.63316462]
["SL_MFPC2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN1","2008-10-01","ESC239722",null,140.65,0.070599,0,0,0.2,180.69569922000002]
["SL_MFPC2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN1","2009-10-01","ESC240087",null,140.65,0.095223,0,0,0.2,184.85173794000002]
["SL_MFPC2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN1","2010-10-01","ESC240452",null,140.65,0.120413,0,0,0.2,189.10330614000003]
["SL_MFPC2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN1","2011-10-01","ESC240817",null,140.65,0.120413,0,0,0.2,189.10330614000003]
["SL_MFPC2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN1","2012-10-01","ESC241183",null,140.65,null,0,0,0.2,168.78]
["SL_MSCS","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SL_MSCS","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SL_MSCS","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SL_MSCS","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SL_MSCS","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SL_MSCS","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SL_MSCS1","ESC1","SL_OHN2",null,null,"2005-10-01","ESC138626",null,1,0,0.048,null,null,1.048]
["SL_MSCS1","ESC1","SL_OHN2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.048,null,null,1.075248]
["SL_MSCS1","ESC1","SL_OHN2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.048,null,null,1.103204448]
["SL_MSCS1","ESC1","SL_OHN2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.048,null,null,1.13188776784]
["SL_MSCS2","ESC2","SL_OHN2",null,null,"2006-10-01","ESC238991",null,1,0.023,0.048,null,null,1.072104]
["SL_MSCS2","ESC2","SL_OHN2",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.048,null,null,1.096762392]
["SL_MSCS2","ESC2","SL_OHN2",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.048,null,null,1.1219877520000001]
["SL_MSCS2","ESC2","SL_OHN2",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.048,null,null,1.1477937040000001]
["SL_MSCS2","ESC2","SL_OHN2",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.048,null,null,1.1741928240000001]
["SL_MSCS2","ESC2","SL_OHN2",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.048,null,null,1.1741928240000001]
["SL_MSCS2","ESC2","SL_OHN2",null,null,"2012-10-01","ESC241183",null,1,null,0.048,null,null,1.048]
["SL_MSEG","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SL_MSEG","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SL_MSEG","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SL_MSEG","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SL_MSEG","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SL_MSEG","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SL_MSEG1","ESC1","SL_OHN2",null,null,"2005-10-01","ESC138626",null,1,0,0.048,null,null,1.048]
["SL_MSEG1","ESC1","SL_OHN2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.048,null,null,1.075248]
["SL_MSEG1","ESC1","SL_OHN2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.048,null,null,1.103204448]
["SL_MSEG1","ESC1","SL_OHN2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.048,null,null,1.13188776784]
["SL_MSEG2","ESC2","SL_OHN2",null,null,"2006-10-01","ESC238991",null,1,0.023,0.048,null,null,1.072104]
["SL_MSEG2","ESC2","SL_OHN2",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.048,null,null,1.096762392]
["SL_MSEG2","ESC2","SL_OHN2",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.048,null,null,1.1219877520000001]
["SL_MSEG2","ESC2","SL_OHN2",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.048,null,null,1.1477937040000001]
["SL_MSEG2","ESC2","SL_OHN2",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.048,null,null,1.1741928240000001]
["SL_MSEG2","ESC2","SL_OHN2",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.048,null,null,1.1741928240000001]
["SL_MSEG2","ESC2","SL_OHN2",null,null,"2012-10-01","ESC241183",null,1,null,0.048,null,null,1.048]
["SL_MSEQ","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SL_MSEQ","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SL_MSEQ","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SL_MSEQ","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SL_MSEQ","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SL_MSEQ","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SL_MSEQ1","ESC1","SL_OHN2",null,null,"2005-10-01","ESC138626",null,1,0,0.048,null,null,1.048]
["SL_MSEQ1","ESC1","SL_OHN2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.048,null,null,1.075248]
["SL_MSEQ1","ESC1","SL_OHN2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.048,null,null,1.103204448]
["SL_MSEQ1","ESC1","SL_OHN2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.048,null,null,1.13188776784]
["SL_MSEQ2","ESC2","SL_OHN2",null,null,"2006-10-01","ESC238991",null,1,0.023,0.048,null,null,1.072104]
["SL_MSEQ2","ESC2","SL_OHN2",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.048,null,null,1.096762392]
["SL_MSEQ2","ESC2","SL_OHN2",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.048,null,null,1.1219877520000001]
["SL_MSEQ2","ESC2","SL_OHN2",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.048,null,null,1.1477937040000001]
["SL_MSEQ2","ESC2","SL_OHN2",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.048,null,null,1.1741928240000001]
["SL_MSEQ2","ESC2","SL_OHN2",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.048,null,null,1.1741928240000001]
["SL_MSEQ2","ESC2","SL_OHN2",null,null,"2012-10-01","ESC241183",null,1,null,0.048,null,null,1.048]
["SL_MSPF","SL_OH2",{"$nulls":4},"SL_OH2",null,1,0.06,null,null,null,1.06]
["SL_MSPF1","SL_OHN2",{"$nulls":4},"SL_OHN2",null,1,0.048,null,null,null,1.048]
["SL_MSPF2","SL_OHN2",{"$nulls":4},"SL_OHN2",null,1,0.048,null,null,null,1.048]
["SL_MSPS","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SL_MSPS","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SL_MSPS","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SL_MSPS","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SL_MSPS","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SL_MSPS","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SL_MSPS1","ESC1","SL_OHN2",null,null,"2005-10-01","ESC138626",null,1,0,0.048,null,null,1.048]
["SL_MSPS1","ESC1","SL_OHN2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.048,null,null,1.075248]
["SL_MSPS1","ESC1","SL_OHN2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.048,null,null,1.103204448]
["SL_MSPS1","ESC1","SL_OHN2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.048,null,null,1.13188776784]
["SL_MSPS2","ESC2","SL_OHN2",null,null,"2006-10-01","ESC238991",null,1,0.023,0.048,null,null,1.072104]
["SL_MSPS2","ESC2","SL_OHN2",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.048,null,null,1.096762392]
["SL_MSPS2","ESC2","SL_OHN2",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.048,null,null,1.1219877520000001]
["SL_MSPS2","ESC2","SL_OHN2",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.048,null,null,1.1477937040000001]
["SL_MSPS2","ESC2","SL_OHN2",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.048,null,null,1.1741928240000001]
["SL_MSPS2","ESC2","SL_OHN2",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.048,null,null,1.1741928240000001]
["SL_MSPS2","ESC2","SL_OHN2",null,null,"2012-10-01","ESC241183",null,1,null,0.048,null,null,1.048]
["SL_MSPX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["SL_MSPX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["SL_MSPX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["SL_MSPX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["SL_MSPX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["SL_MSPX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["SL_MSPX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["SL_MSPX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["SL_MSPX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["SL_MSPX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["SL_MSPX2","ESC2",null,null,null,"2006-10-01","ESC238991",null,1,0.023,null,null,null,1.023]
["SL_MSPX2","ESC2",null,null,null,"2007-10-01","ESC239356",null,1,0.046529,null,null,null,1.046529]
["SL_MSPX2","ESC2",null,null,null,"2008-10-01","ESC239722",null,1,0.070599,null,null,null,1.070599]
["SL_MSPX2","ESC2",null,null,null,"2009-10-01","ESC240087",null,1,0.095223,null,null,null,1.095223]
["SL_MSPX2","ESC2",null,null,null,"2010-10-01","ESC240452",null,1,0.120413,null,null,null,1.120413]
["SL_MSPX2","ESC2",null,null,null,"2011-10-01","ESC240817",null,1,0.120413,null,null,null,1.120413]
["SL_MSPX2","ESC2",null,null,null,"2012-10-01","ESC241183",null,1,{"$nulls":4},1]
["SL_MSPY",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_MSPY1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_MSPY2",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_MSSC","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SL_MSSC","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SL_MSSC","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SL_MSSC","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SL_MSSC","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SL_MSSC","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SL_MSSC1","ESC1","SL_OHN2",null,null,"2005-10-01","ESC138626",null,1,0,0.048,null,null,1.048]
["SL_MSSC1","ESC1","SL_OHN2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.048,null,null,1.075248]
["SL_MSSC1","ESC1","SL_OHN2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.048,null,null,1.103204448]
["SL_MSSC1","ESC1","SL_OHN2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.048,null,null,1.13188776784]
["SL_MSSC2","ESC2","SL_OHN2",null,null,"2006-10-01","ESC238991",null,1,0.023,0.048,null,null,1.072104]
["SL_MSSC2","ESC2","SL_OHN2",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.048,null,null,1.096762392]
["SL_MSSC2","ESC2","SL_OHN2",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.048,null,null,1.1219877520000001]
["SL_MSSC2","ESC2","SL_OHN2",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.048,null,null,1.1477937040000001]
["SL_MSSC2","ESC2","SL_OHN2",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.048,null,null,1.1741928240000001]
["SL_MSSC2","ESC2","SL_OHN2",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.048,null,null,1.1741928240000001]
["SL_MSSC2","ESC2","SL_OHN2",null,null,"2012-10-01","ESC241183",null,1,null,0.048,null,null,1.048]
["SL_MSSF","SL_OH2",{"$nulls":4},"SL_OH2",null,1,0.06,null,null,null,1.06]
["SL_MSSF1","SL_OHN2",{"$nulls":4},"SL_OHN2",null,1,0.048,null,null,null,1.048]
["SL_MSSF2","SL_OHN2",{"$nulls":4},"SL_OHN2",null,1,0.048,null,null,null,1.048,57640]
["SL_MSSY",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_MSSY1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_MSSY2",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_MSTR","ESC","SL_OH1",null,null,"2003-10-01","ESC37895",null,1,0,0.2,null,null,1.2]
["SL_MSTR","ESC","SL_OH1",null,null,"2004-10-01","ESC38261",null,1,0.029,0.2,null,null,1.2348]
["SL_MSTR","ESC","SL_OH1",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.2,null,null,1.2693744]
["SL_MSTR","ESC","SL_OH1",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.2,null,null,1.302378]
["SL_MSTR","ESC","SL_OH1",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.2,null,null,1.3362395999999999]
["SL_MSTR","ESC","SL_OH1",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.2,null,null,1.370982]
["SL_MSTR1","ESC1","SL_OHN1",null,null,"2005-10-01","ESC138626",null,1,0,0.2,null,null,1.2]
["SL_MSTR1","ESC1","SL_OHN1",null,null,"2006-10-01","ESC138991",null,1,0.026,0.2,null,null,1.2312]
["SL_MSTR1","ESC1","SL_OHN1",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.2,null,null,1.2632112]
["SL_MSTR1","ESC1","SL_OHN1",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.2,null,null,1.296054696]
["SL_MSTR2","ESC2","SL_OHN1",null,null,"2006-10-01","ESC238991",null,1,0.023,0.2,null,null,1.2275999999999998]
["SL_MSTR2","ESC2","SL_OHN1",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.2,null,null,1.2558348]
["SL_MSTR2","ESC2","SL_OHN1",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.2,null,null,1.2847188]
["SL_MSTR2","ESC2","SL_OHN1",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.2,null,null,1.3142676]
["SL_MSTR2","ESC2","SL_OHN1",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.2,null,null,1.3444956000000001]
["SL_MSTR2","ESC2","SL_OHN1",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.2,null,null,1.3444956000000001]
["SL_MSTR2","ESC2","SL_OHN1",null,null,"2012-10-01","ESC241183",null,1,null,0.2,null,null,1.2]
["SL_MSXA",{"$nulls":5},"",{"$nulls":6},0]
["SL_MSXX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["SL_MSXX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["SL_MSXX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["SL_MSXX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["SL_MSXX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["SL_MSXX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["SL_MSXX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["SL_MSXX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["SL_MSXX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["SL_MSXX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["SL_MSXX2","ESC2",null,null,null,"2006-10-01","ESC238991",null,1,0.023,null,null,null,1.023]
["SL_MSXX2","ESC2",null,null,null,"2007-10-01","ESC239356",null,1,0.046529,null,null,null,1.046529]
["SL_MSXX2","ESC2",null,null,null,"2008-10-01","ESC239722",null,1,0.070599,null,null,null,1.070599]
["SL_MSXX2","ESC2",null,null,null,"2009-10-01","ESC240087",null,1,0.095223,null,null,null,1.095223]
["SL_MSXX2","ESC2",null,null,null,"2010-10-01","ESC240452",null,1,0.120413,null,null,null,1.120413]
["SL_MSXX2","ESC2",null,null,null,"2011-10-01","ESC240817",null,1,0.120413,null,null,null,1.120413]
["SL_MSXX2","ESC2",null,null,null,"2012-10-01","ESC241183",null,1,{"$nulls":4},1]
["SL_MTRL","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SL_MTRL","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SL_MTRL","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SL_MTRL","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SL_MTRL","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SL_MTRL","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SL_MTRL1","ESC1","SL_OHN2",null,null,"2005-10-01","ESC138626",null,1,0,0.048,null,null,1.048]
["SL_MTRL1","ESC1","SL_OHN2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.048,null,null,1.075248]
["SL_MTRL1","ESC1","SL_OHN2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.048,null,null,1.103204448]
["SL_MTRL1","ESC1","SL_OHN2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.048,null,null,1.13188776784]
["SL_MTRL2","ESC2","SL_OHN2",null,null,"2006-10-01","ESC238991",null,1,0.023,0.048,null,null,1.072104]
["SL_MTRL2","ESC2","SL_OHN2",null,null,"2007-10-01","ESC239356",null,1,0.046529,0.048,null,null,1.096762392]
["SL_MTRL2","ESC2","SL_OHN2",null,null,"2008-10-01","ESC239722",null,1,0.070599,0.048,null,null,1.1219877520000001]
["SL_MTRL2","ESC2","SL_OHN2",null,null,"2009-10-01","ESC240087",null,1,0.095223,0.048,null,null,1.1477937040000001]
["SL_MTRL2","ESC2","SL_OHN2",null,null,"2010-10-01","ESC240452",null,1,0.120413,0.048,null,null,1.1741928240000001]
["SL_MTRL2","ESC2","SL_OHN2",null,null,"2011-10-01","ESC240817",null,1,0.120413,0.048,null,null,1.1741928240000001]
["SL_MTRL2","ESC2","SL_OHN2",null,null,"2012-10-01","ESC241183",null,1,null,0.048,null,null,1.048]
["SL_MVE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_MVE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_MVE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_MVE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_MVE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_MVE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_MVE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,54.62,0,0.305,0.21,0.2,103.49725319999999]
["SL_MVE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,54.62,0.026,0.305,0.21,0.2,106.18818178319998]
["SL_MVE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,54.62,0.052676,0.305,0.21,0.2,108.94907450956318]
["SL_MVE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,54.62,0.08004558,0.305,0.21,0.2,111.78175086080083]
["SL_MVE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,54.62,0.023,0.305,0.21,0.2,105.87769002359997]
["SL_MVE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,54.62,0.046529,0.305,0.21,0.2,108.31287689414279]
["SL_MVE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,54.62,0.070599,0.305,0.21,0.2,110.80405577866678]
["SL_MVE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,54.62,0.095223,0.305,0.21,0.2,113.3525721414636]
["SL_MVE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,54.62,0.120413,0.305,0.21,0.2,115.95966794957158]
["SL_MVE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,54.62,0.120413,0.305,0.21,0.2,115.95966794957158]
["SL_MVE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,54.62,null,0.305,0.21,0.2,103.49725319999999]
["SL_OE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,58.14,0,0.29,0.215,0.2,109.3508748]
["SL_OE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,58.14,0.029,0.29,0.215,0.2,112.52205016919999]
["SL_OE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,58.14,0.057812,0.29,0.215,0.2,115.6726675739376]
["SL_OE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,58.14,0.085315,0.29,0.215,0.2,118.680144683562]
["SL_OE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,58.14,0.113533,0.29,0.215,0.2,121.7658076686684]
["SL_OE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,58.14,0.142485,0.29,0.215,0.2,124.931734195878]
["SL_OE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,58.14,0,0.305,0.21,0.2,110.16716039999999]
["SL_OE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,58.14,0.026,0.305,0.21,0.2,113.0315065704]
["SL_OE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,58.14,0.052676,0.305,0.21,0.2,115.97032574123038]
["SL_OE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,58.14,0.08004558,0.305,0.21,0.2,118.98555465117103]
["SL_OE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,58.14,0.023,0.305,0.21,0.2,112.70100508919998]
["SL_OE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,58.14,0.046529,0.305,0.21,0.2,115.29312820625158]
["SL_OE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,58.14,0.070599,0.305,0.21,0.2,117.9448517570796]
["SL_OE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,58.14,0.095223,0.305,0.21,0.2,120.65760791476919]
["SL_OE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,58.14,0.120413,0.305,0.21,0.2,123.43271868524519]
["SL_OE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,58.14,0.120413,0.305,0.21,0.2,123.43271868524519]
["SL_OE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,58.14,null,0.305,0.21,0.2,110.16716039999999]
["SL_OT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,31.83,0,0.29,0.215,0.2,59.866500599999995]
["SL_OT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,31.83,0.029,0.29,0.215,0.2,61.60262911739999]
["SL_OT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,31.83,0.057812,0.29,0.215,0.2,63.327502732687186]
["SL_OT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,31.83,0.085315,0.29,0.215,0.2,64.974011098689]
["SL_OT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,31.83,0.113533,0.29,0.215,0.2,66.66332401261978]
["SL_OT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,31.83,0.142485,0.29,0.215,0.2,68.396578937991]
["SL_OT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,31.83,0,0.305,0.21,0.2,60.313393799999986]
["SL_OT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,31.83,0.026,0.305,0.21,0.2,61.88154203879998]
["SL_OT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,31.83,0.052676,0.305,0.21,0.2,63.49046213180878]
["SL_OT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,31.83,0.08004558,0.305,0.21,0.2,65.14121438848939]
["SL_OT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,31.83,0.023,0.305,0.21,0.2,61.70060185739999]
["SL_OT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,31.83,0.046529,0.305,0.21,0.2,63.119715700120196]
["SL_OT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,31.83,0.070599,0.305,0.21,0.2,64.57145908888619]
["SL_OT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,31.83,0.095223,0.305,0.21,0.2,66.0566160978174]
["SL_OT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,31.83,0.120413,0.305,0.21,0.2,67.57591048763939]
["SL_OT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,31.83,0.120413,0.305,0.21,0.2,67.57591048763939]
["SL_OT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,31.83,null,0.305,0.21,0.2,60.313393799999986]
["SL_PCCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,33.86,0,0.29,0.215,0.2,63.6845652]
["SL_PCCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,33.86,0.029,0.29,0.215,0.2,65.53141759079999]
["SL_PCCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,33.86,0.057812,0.29,0.215,0.2,67.3662972833424]
["SL_PCCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,33.86,0.085315,0.29,0.215,0.2,69.117813880038]
["SL_PCCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,33.86,0.113533,0.29,0.215,0.2,70.9148649408516]
["SL_PCCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,33.86,0.142485,0.29,0.215,0.2,72.75866047252201]
["SL_PCCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,33.86,0,0.305,0.21,0.2,64.1599596]
["SL_PCCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,33.86,0.026,0.305,0.21,0.2,65.82811854959999]
["SL_PCCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,33.86,0.052676,0.305,0.21,0.2,67.53964963188959]
["SL_PCCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,33.86,0.08004558,0.305,0.21,0.2,69.29568077895857]
["SL_PCCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,33.86,0.023,0.305,0.21,0.2,65.63563867079999]
["SL_PCCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,33.86,0.046529,0.305,0.21,0.2,67.1452583602284]
["SL_PCCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,33.86,0.070599,0.305,0.21,0.2,68.6895885878004]
["SL_PCCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,33.86,0.095223,0.305,0.21,0.2,70.26946343299079]
["SL_PCCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,33.86,0.120413,0.305,0.21,0.2,71.88565281531478]
["SL_PCCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,33.86,0.120413,0.305,0.21,0.2,71.88565281531478]
["SL_PCCA2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,33.86,null,0.305,0.21,0.2,64.1599596]
["SL_PCE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,58.14,0,0.29,0.215,0.2,109.3508748]
["SL_PCE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,58.14,0.029,0.29,0.215,0.2,112.52205016919999]
["SL_PCE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,58.14,0.057812,0.29,0.215,0.2,115.6726675739376]
["SL_PCE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,58.14,0.085315,0.29,0.215,0.2,118.680144683562]
["SL_PCE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,58.14,0.113533,0.29,0.215,0.2,121.7658076686684]
["SL_PCE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,58.14,0.142485,0.29,0.215,0.2,124.931734195878]
["SL_PCE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,58.14,0,0.305,0.21,0.2,110.16716039999999]
["SL_PCE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,58.14,0.026,0.305,0.21,0.2,113.0315065704]
["SL_PCE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,58.14,0.052676,0.305,0.21,0.2,115.97032574123038]
["SL_PCE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,58.14,0.08004558,0.305,0.21,0.2,118.98555465117103]
["SL_PCE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,58.14,0.023,0.305,0.21,0.2,112.70100508919998]
["SL_PCE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,58.14,0.046529,0.305,0.21,0.2,115.29312820625158]
["SL_PCE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,58.14,0.070599,0.305,0.21,0.2,117.9448517570796]
["SL_PCE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,58.14,0.095223,0.305,0.21,0.2,120.65760791476919]
["SL_PCE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,58.14,0.120413,0.305,0.21,0.2,123.43271868524519]
["SL_PCE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,58.14,0.120413,0.305,0.21,0.2,123.43271868524519]
["SL_PCE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,58.14,null,0.305,0.21,0.2,110.16716039999999]
["SL_PCEF","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,31.83,0,0.29,0.215,0.2,59.866500599999995]
["SL_PCEF","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,31.83,0.029,0.29,0.215,0.2,61.60262911739999]
["SL_PCEF","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,31.83,0.057812,0.29,0.215,0.2,63.327502732687186]
["SL_PCEF","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,31.83,0.085315,0.29,0.215,0.2,64.974011098689]
["SL_PCEF","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,31.83,0.113533,0.29,0.215,0.2,66.66332401261978]
["SL_PCEF","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,31.83,0.142485,0.29,0.215,0.2,68.396578937991]
["SL_PCEF1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,31.83,0,0.305,0.21,0.2,60.313393799999986]
["SL_PCEF1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,31.83,0.026,0.305,0.21,0.2,61.88154203879998]
["SL_PCEF1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,31.83,0.052676,0.305,0.21,0.2,63.49046213180878]
["SL_PCEF1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,31.83,0.08004558,0.305,0.21,0.2,65.14121438848939]
["SL_PCEF2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,31.83,0.023,0.305,0.21,0.2,61.70060185739999]
["SL_PCEF2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,31.83,0.046529,0.305,0.21,0.2,63.119715700120196]
["SL_PCEF2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,31.83,0.070599,0.305,0.21,0.2,64.57145908888619]
["SL_PCEF2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,31.83,0.095223,0.305,0.21,0.2,66.0566160978174]
["SL_PCEF2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,31.83,0.120413,0.305,0.21,0.2,67.57591048763939]
["SL_PCEF2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,31.83,0.120413,0.305,0.21,0.2,67.57591048763939]
["SL_PCEF2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,31.83,null,0.305,0.21,0.2,60.313393799999986]
["SL_PCT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,31.83,0,0.29,0.215,0.2,59.866500599999995]
["SL_PCT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,31.83,0.029,0.29,0.215,0.2,61.60262911739999]
["SL_PCT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,31.83,0.057812,0.29,0.215,0.2,63.327502732687186]
["SL_PCT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,31.83,0.085315,0.29,0.215,0.2,64.974011098689]
["SL_PCT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,31.83,0.113533,0.29,0.215,0.2,66.66332401261978]
["SL_PCT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,31.83,0.142485,0.29,0.215,0.2,68.396578937991]
["SL_PCT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,31.83,0,0.305,0.21,0.2,60.313393799999986]
["SL_PCT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,31.83,0.026,0.305,0.21,0.2,61.88154203879998]
["SL_PCT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,31.83,0.052676,0.305,0.21,0.2,63.49046213180878]
["SL_PCT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,31.83,0.08004558,0.305,0.21,0.2,65.14121438848939]
["SL_PCT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,31.83,0.023,0.305,0.21,0.2,61.70060185739999]
["SL_PCT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,31.83,0.046529,0.305,0.21,0.2,63.119715700120196]
["SL_PCT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,31.83,0.070599,0.305,0.21,0.2,64.57145908888619]
["SL_PCT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,31.83,0.095223,0.305,0.21,0.2,66.0566160978174]
["SL_PCT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,31.83,0.120413,0.305,0.21,0.2,67.57591048763939]
["SL_PCT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,31.83,0.120413,0.305,0.21,0.2,67.57591048763939]
["SL_PCT2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,31.83,null,0.305,0.21,0.2,60.313393799999986]
["SL_PEX","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,40.7,0,0.29,0.215,0.2,76.54937400000001]
["SL_PEX","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,40.7,0.029,0.29,0.215,0.2,78.769305846]
["SL_PEX","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,40.7,0.057812,0.29,0.215,0.2,80.97484640968801]
["SL_PEX","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,40.7,0.085315,0.29,0.215,0.2,83.08018384281002]
["SL_PEX","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,40.7,0.113533,0.29,0.215,0.2,85.24025407834199]
["SL_PEX","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,40.7,0.142485,0.29,0.215,0.2,87.45651155439002]
["SL_PEX1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,40.7,0,0.305,0.21,0.2,77.120802]
["SL_PEX1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,40.7,0.026,0.305,0.21,0.2,79.125942852]
["SL_PEX1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,40.7,0.052676,0.305,0.21,0.2,81.183217366152]
["SL_PEX1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,40.7,0.08004558,0.305,0.21,0.2,83.29398132615515]
["SL_PEX2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,40.7,0.023,0.305,0.21,0.2,78.89458044599999]
["SL_PEX2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,40.7,0.046529,0.305,0.21,0.2,80.70915579625799]
["SL_PEX2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,40.7,0.070599,0.305,0.21,0.2,82.56545350039801]
["SL_PEX2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,40.7,0.095223,0.305,0.21,0.2,84.464476128846]
["SL_PEX2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,40.7,0.120413,0.305,0.21,0.2,86.407149131226]
["SL_PEX2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,40.7,0.120413,0.305,0.21,0.2,86.407149131226]
["SL_PEX2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,40.7,null,0.305,0.21,0.2,77.120802]
["SL_PHH","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,45.68,0,0.29,0.215,0.2,85.9158576]
["SL_PHH","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,45.68,0.029,0.29,0.215,0.2,88.4074174704]
["SL_PHH","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,45.68,0.057812,0.29,0.215,0.2,90.88282515957121]
["SL_PHH","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,45.68,0.085315,0.29,0.215,0.2,93.245768991144]
["SL_PHH","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,45.68,0.113533,0.29,0.215,0.2,95.67014266090081]
["SL_PHH","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,45.68,0.142485,0.29,0.215,0.2,98.15757857013601]
["SL_PHH1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,49.4,0,0.305,0.21,0.2,93.60608399999998]
["SL_PHH1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,49.4,0.026,0.305,0.21,0.2,96.03984218399998]
["SL_PHH1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,49.4,0.052676,0.305,0.21,0.2,98.53687808078398]
["SL_PHH1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,49.4,0.08004558,0.305,0.21,0.2,101.0988372853087]
["SL_PHH2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,49.4,0.023,0.305,0.21,0.2,95.75902393199998]
["SL_PHH2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,49.4,0.046529,0.305,0.21,0.2,97.96148148243599]
["SL_PHH2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,49.4,0.070599,0.305,0.21,0.2,100.214579924316]
["SL_PHH2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,49.4,0.095223,0.305,0.21,0.2,102.51953613673199]
["SL_PHH2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,49.4,0.120413,0.305,0.21,0.2,104.87747339269198]
["SL_PHH2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,49.4,0.120413,0.305,0.21,0.2,104.87747339269198]
["SL_PHH2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,49.4,null,0.305,0.21,0.2,93.60608399999998]
["SL_PHPD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,36.17,0,0.29,0.215,0.2,68.0292594]
["SL_PHPD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,36.17,0.029,0.29,0.215,0.2,70.0021079226]
["SL_PHPD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,36.17,0.057812,0.29,0.215,0.2,71.96216694443281]
["SL_PHPD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,36.17,0.085315,0.29,0.215,0.2,73.83317566571101]
["SL_PHPD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,36.17,0.113533,0.29,0.215,0.2,75.7528253074602]
["SL_PHPD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,36.17,0.142485,0.29,0.215,0.2,77.722408425609]
["SL_PHPD1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,36.17,0,0.305,0.21,0.2,68.53708619999999]
["SL_PHPD1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,36.17,0.026,0.305,0.21,0.2,70.3190504412]
["SL_PHPD1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,36.17,0.052676,0.305,0.21,0.2,72.1473457526712]
["SL_PHPD1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,36.17,0.08004558,0.305,0.21,0.2,74.02317701638898]
["SL_PHPD2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,36.17,0.023,0.305,0.21,0.2,70.11343918259998]
["SL_PHPD2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,36.17,0.046529,0.305,0.21,0.2,71.7260482837998]
["SL_PHPD2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,36.17,0.070599,0.305,0.21,0.2,73.3757359486338]
["SL_PHPD2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,36.17,0.095223,0.305,0.21,0.2,75.0633931592226]
["SL_PHPD2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,36.17,0.120413,0.305,0.21,0.2,76.7898423606006]
["SL_PHPD2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,36.17,0.120413,0.305,0.21,0.2,76.7898423606006]
["SL_PHPD2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,36.17,null,0.305,0.21,0.2,68.53708619999999]
["SL_PHPU","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,63.33,0,0.305,0.21,0.2,120.00148379999999]
["SL_PHPU","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,63.33,0.026,0.305,0.21,0.2,123.12152237879998]
["SL_PHPU","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,63.33,0.052676,0.305,0.21,0.2,126.32268196064877]
["SL_PHPU","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,63.33,0.08004558,0.305,0.21,0.2,129.6070721716316]
["SL_PHPU2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,63.33,0.023,0.305,0.21,0.2,122.76151792739996]
["SL_PHPU2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,63.33,0.046529,0.305,0.21,0.2,125.58503283973018]
["SL_PHPU2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,63.33,0.070599,0.305,0.21,0.2,128.4734685547962]
["SL_PHPU2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,63.33,0.095223,0.305,0.21,0.2,131.42838509188738]
["SL_PHPU2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,63.33,0.120413,0.305,0.21,0.2,134.4512224688094]
["SL_PHPU2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,63.33,0.120413,0.305,0.21,0.2,134.4512224688094]
["SL_PHPU2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,63.33,null,0.305,0.21,0.2,120.00148379999999]
["SL_PHS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,37.62,0,0.29,0.215,0.2,70.7564484]
["SL_PHS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,37.62,0.029,0.29,0.215,0.2,72.80838540359998]
["SL_PHS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,37.62,0.057812,0.29,0.215,0.2,74.84702019490081]
["SL_PHS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,37.62,0.085315,0.29,0.215,0.2,76.79303479524602]
["SL_PHS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,37.62,0.113533,0.29,0.215,0.2,78.78964025619719]
["SL_PHS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,37.62,0.142485,0.29,0.215,0.2,80.83818095027401]
["SL_PHS1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,37.62,0,0.305,0.21,0.2,71.28463319999999]
["SL_PHS1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,37.62,0.026,0.305,0.21,0.2,73.13803366319999]
["SL_PHS1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,37.62,0.052676,0.305,0.21,0.2,75.03962253844318]
["SL_PHS1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,37.62,0.08004558,0.305,0.21,0.2,76.99065300958124]
["SL_PHS2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,37.62,0.023,0.305,0.21,0.2,72.9241797636]
["SL_PHS2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,37.62,0.046529,0.305,0.21,0.2,74.60143589816279]
["SL_PHS2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,37.62,0.070599,0.305,0.21,0.2,76.3172570192868]
["SL_PHS2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,37.62,0.095223,0.305,0.21,0.2,78.0725698272036]
["SL_PHS2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,37.62,0.120413,0.305,0.21,0.2,79.8682297375116]
["SL_PHS2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,37.62,0.120413,0.305,0.21,0.2,79.8682297375116]
["SL_PHS2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,37.62,null,0.305,0.21,0.2,71.28463319999999]
["SL_PHSS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,47.88,0,0.29,0.215,0.2,90.05366160000001]
["SL_PHSS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,47.88,0.029,0.29,0.215,0.2,92.66521778639999]
["SL_PHSS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,47.88,0.057812,0.29,0.215,0.2,95.25984388441923]
["SL_PHSS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,47.88,0.085315,0.29,0.215,0.2,97.736589739404]
["SL_PHSS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,47.88,0.113533,0.29,0.215,0.2,100.27772396243279]
["SL_PHSS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,47.88,0.142485,0.29,0.215,0.2,102.884957573076]
["SL_PHSS1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,47.88,0,0.305,0.21,0.2,90.7258968]
["SL_PHSS1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,47.88,0.026,0.305,0.21,0.2,93.0847701168]
["SL_PHSS1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,47.88,0.052676,0.305,0.21,0.2,95.50497413983679]
["SL_PHSS1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,47.88,0.08004558,0.305,0.21,0.2,97.98810383037613]
["SL_PHSS2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,47.88,0.023,0.305,0.21,0.2,92.8125924264]
["SL_PHSS2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,47.88,0.046529,0.305,0.21,0.2,94.9472820522072]
["SL_PHSS2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,47.88,0.070599,0.305,0.21,0.2,97.1310543881832]
["SL_PHSS2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,47.88,0.095223,0.305,0.21,0.2,99.3650888709864]
["SL_PHSS2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,47.88,0.120413,0.305,0.21,0.2,101.6504742113784]
["SL_PHSS2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,47.88,0.120413,0.305,0.21,0.2,101.6504742113784]
["SL_PHSS2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,47.88,null,0.305,0.21,0.2,90.7258968]
["SL_PM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,63.8,0,0.29,0.215,0.2,119.99631599999998]
["SL_PM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,63.8,0.029,0.29,0.215,0.2,123.476209164]
["SL_PM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,63.8,0.057812,0.29,0.215,0.2,126.933543020592]
["SL_PM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,63.8,0.085315,0.29,0.215,0.2,130.23380169954004]
["SL_PM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,63.8,0.113533,0.29,0.215,0.2,133.61985774442797]
["SL_PM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,63.8,0.142485,0.29,0.215,0.2,137.09399108526]
["SL_PM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,83.63,0,0.305,0.21,0.2,158.46714179999998]
["SL_PM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,83.63,0.026,0.305,0.21,0.2,162.58728748679997]
["SL_PM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,83.63,0.052676,0.305,0.21,0.2,166.81455696145676]
["SL_PM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,83.63,0.08004558,0.305,0.21,0.2,171.1517360763232]
["SL_PM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,83.63,0.023,0.305,0.21,0.2,162.11188606139993]
["SL_PM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,83.63,0.046529,0.305,0.21,0.2,165.84045944081217]
["SL_PM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,83.63,0.070599,0.305,0.21,0.2,169.65476354393817]
["SL_PM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,83.63,0.095223,0.305,0.21,0.2,173.55685844362137]
["SL_PM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,83.63,0.120413,0.305,0.21,0.2,177.5486457455634]
["SL_PM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,83.63,0.120413,0.305,0.21,0.2,177.5486457455634]
["SL_PM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,83.63,null,0.305,0.21,0.2,158.46714179999998]
["SL_POWB",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_POWB1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_POWB2",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_QAO","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_QAO","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_QAO","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_QAO","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_QAO","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_QAO","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_QAO1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,35.53,0,0.305,0.21,0.2,67.3243758]
["SL_QAO1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,35.53,0.026,0.305,0.21,0.2,69.0748095708]
["SL_QAO1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,35.53,0.052676,0.305,0.21,0.2,70.87075461964079]
["SL_QAO1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,35.53,0.08004558,0.305,0.21,0.2,72.71339450904895]
["SL_QAO2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,59.74,0.023,0.305,0.21,0.2,115.80251193719998]
["SL_QAO2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,59.74,0.046529,0.305,0.21,0.2,118.46596971175559]
["SL_QAO2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,59.74,0.070599,0.305,0.21,0.2,121.19066811090359]
["SL_QAO2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,59.74,0.095223,0.305,0.21,0.2,123.9780787208172]
["SL_QAO2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,59.74,0.120413,0.305,0.21,0.2,126.82955992873318]
["SL_QAO2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,59.74,0.120413,0.305,0.21,0.2,126.82955992873318]
["SL_QAO2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,59.74,null,0.305,0.21,0.2,113.1989364]
["SL_SEE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_SEE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_SEE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_SEE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_SEE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_SEE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_SEE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,54.62,0,0.305,0.21,0.2,103.49725319999999]
["SL_SEE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,54.62,0.026,0.305,0.21,0.2,106.18818178319998]
["SL_SEE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,54.62,0.052676,0.305,0.21,0.2,108.94907450956318]
["SL_SEE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,54.62,0.08004558,0.305,0.21,0.2,111.78175086080083]
["SL_SEE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,54.62,0.023,0.305,0.21,0.2,105.87769002359997]
["SL_SEE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,54.62,0.046529,0.305,0.21,0.2,108.31287689414279]
["SL_SEE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,54.62,0.070599,0.305,0.21,0.2,110.80405577866678]
["SL_SEE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,54.62,0.095223,0.305,0.21,0.2,113.3525721414636]
["SL_SEE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,54.62,0.120413,0.305,0.21,0.2,115.95966794957158]
["SL_SEE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,54.62,0.120413,0.305,0.21,0.2,115.95966794957158]
["SL_SEE2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,54.62,null,0.305,0.21,0.2,103.49725319999999]
["SL_SEEM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_SEEM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_SEEM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_SEEM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_SEEM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_SEEM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_SEEM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,54.62,0,0.305,0.21,0.2,103.49725319999999]
["SL_SEEM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,54.62,0.026,0.305,0.21,0.2,106.18818178319998]
["SL_SEEM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,54.62,0.052676,0.305,0.21,0.2,108.94907450956318]
["SL_SEEM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,54.62,0.08004558,0.305,0.21,0.2,111.78175086080083]
["SL_SEEM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,54.62,0.023,0.305,0.21,0.2,105.87769002359997]
["SL_SEEM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,54.62,0.046529,0.305,0.21,0.2,108.31287689414279]
["SL_SEEM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,54.62,0.070599,0.305,0.21,0.2,110.80405577866678]
["SL_SEEM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,54.62,0.095223,0.305,0.21,0.2,113.3525721414636]
["SL_SEEM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,54.62,0.120413,0.305,0.21,0.2,115.95966794957158]
["SL_SEEM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,54.62,0.120413,0.305,0.21,0.2,115.95966794957158]
["SL_SEEM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,54.62,null,0.305,0.21,0.2,103.49725319999999]
["SL_SEL","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2003-10-01","ESC37895",null,38,0,0,0,0.2,45.6]
["SL_SEL","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2004-10-01","ESC38261",null,38,0.029,0,0,0.2,46.922399999999996]
["SL_SEL","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2005-10-01","ESC38626",null,38,0.057812,0,0,0.2,48.236227199999995]
["SL_SEL","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2006-10-01","ESC38991",null,38,0.085315,0,0,0.2,49.490364]
["SL_SEL","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2007-10-01","ESC39356",null,38,0.113533,0,0,0.2,50.7771048]
["SL_SEL","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2008-10-01","ESC39722",null,38,0.142485,0,0,0.2,52.09731599999999]
["SL_SEL1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN1","2005-10-01","ESC138626",null,38,0,0,0,0.2,45.6]
["SL_SEL1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN1","2006-10-01","ESC138991",null,38,0.026,0,0,0.2,46.785599999999995]
["SL_SEL1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN1","2007-10-01","ESC139356",null,38,0.052676,0,0,0.2,48.0020256]
["SL_SEL1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN1","2008-10-01","ESC139722",null,38,0.08004558,0,0,0.2,49.250078448]
["SL_SEL2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN1","2006-10-01","ESC238991",null,38,0.023,0,0,0.2,46.648799999999994]
["SL_SEL2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN1","2007-10-01","ESC239356",null,38,0.046529,0,0,0.2,47.7217224]
["SL_SEL2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN1","2008-10-01","ESC239722",null,38,0.070599,0,0,0.2,48.8193144]
["SL_SEL2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN1","2009-10-01","ESC240087",null,38,0.095223,0,0,0.2,49.9421688]
["SL_SEL2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN1","2010-10-01","ESC240452",null,38,0.120413,0,0,0.2,51.09083280000001]
["SL_SEL2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN1","2011-10-01","ESC240817",null,38,0.120413,0,0,0.2,51.09083280000001]
["SL_SEL2","ESC2","SL_FRNGX","SL_LEAVX","SL_OHN1","2012-10-01","ESC241183",null,38,null,0,0,0.2,45.6]
["SL_SEPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,32.28,0,0.29,0.215,0.2,60.71286960000001]
["SL_SEPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,32.28,0.029,0.29,0.215,0.2,62.47354281839999]
["SL_SEPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,32.28,0.057812,0.29,0.215,0.2,64.2228020173152]
["SL_SEPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,32.28,0.085315,0.29,0.215,0.2,65.892588069924]
["SL_SEPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,32.28,0.113533,0.29,0.215,0.2,67.60578382429681]
["SL_SEPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,32.28,0.142485,0.29,0.215,0.2,69.363542824956]
["SL_SEPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,32.28,0,0.305,0.21,0.2,61.166080799999996]
["SL_SEPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,32.28,0.026,0.305,0.21,0.2,62.756398900799994]
["SL_SEPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,32.28,0.052676,0.305,0.21,0.2,64.38806527222079]
["SL_SEPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,32.28,0.08004558,0.305,0.21,0.2,66.06215521396287]
["SL_SEPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,32.28,0.023,0.305,0.21,0.2,62.57290065839999]
["SL_SEPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,32.28,0.046529,0.305,0.21,0.2,64.0120773735432]
["SL_SEPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,32.28,0.070599,0.305,0.21,0.2,65.4843449383992]
["SL_SEPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,32.28,0.095223,0.305,0.21,0.2,66.99049851201839]
["SL_SEPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,32.28,0.120413,0.305,0.21,0.2,68.5312720873704]
["SL_SEPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,32.28,0.120413,0.305,0.21,0.2,68.5312720873704]
["SL_SEPM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,32.28,null,0.305,0.21,0.2,61.166080799999996]
["SL_SRA","ESC","SL_OH1",null,null,"2003-10-01","ESC37895",null,20.83,0,0.2,null,null,24.996]
["SL_SRA","ESC","SL_OH1",null,null,"2004-10-01","ESC38261",null,20.83,0.029,0.2,null,null,25.720883999999995]
["SL_SRA","ESC","SL_OH1",null,null,"2005-10-01","ESC38626",null,20.83,0.057812,0.2,null,null,26.441068751999996]
["SL_SRA","ESC","SL_OH1",null,null,"2006-10-01","ESC38991",null,20.83,0.085315,0.2,null,null,27.128533739999998]
["SL_SRA","ESC","SL_OH1",null,null,"2007-10-01","ESC39356",null,20.83,0.113533,0.2,null,null,27.833870867999995]
["SL_SRA","ESC","SL_OH1",null,null,"2008-10-01","ESC39722",null,20.83,0.142485,0.2,null,null,28.557555059999995]
["SL_SRA1","ESC1","SL_OHN1",null,null,"2005-10-01","ESC138626",null,20.83,0,0.2,null,null,24.996]
["SL_SRA1","ESC1","SL_OHN1",null,null,"2006-10-01","ESC138991",null,20.83,0.026,0.2,null,null,25.645895999999997]
["SL_SRA1","ESC1","SL_OHN1",null,null,"2007-10-01","ESC139356",null,20.83,0.052676,0.2,null,null,26.312689296]
["SL_SRA1","ESC1","SL_OHN1",null,null,"2008-10-01","ESC139722",null,20.83,0.08004558,0.2,null,null,26.996819317679996]
["SL_SRA2","ESC2","SL_OHN1",null,null,"2006-10-01","ESC238991",null,20.83,0.023,0.2,null,null,25.570907999999996]
["SL_SRA2","ESC2","SL_OHN1",null,null,"2007-10-01","ESC239356",null,20.83,0.046529,0.2,null,null,26.159038884]
["SL_SRA2","ESC2","SL_OHN1",null,null,"2008-10-01","ESC239722",null,20.83,0.070599,0.2,null,null,26.760692604]
["SL_SRA2","ESC2","SL_OHN1",null,null,"2009-10-01","ESC240087",null,20.83,0.095223,0.2,null,null,27.376194108]
["SL_SRA2","ESC2","SL_OHN1",null,null,"2010-10-01","ESC240452",null,20.83,0.120413,0.2,null,null,28.005843348]
["SL_SRA2","ESC2","SL_OHN1",null,null,"2011-10-01","ESC240817",null,20.83,0.120413,0.2,null,null,28.005843348]
["SL_SRA2","ESC2","SL_OHN1",null,null,"2012-10-01","ESC241183",null,20.83,null,0.2,null,null,24.996]
["SL_STUP",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_STUP1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_STUP2",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_TMUC","ESC","SL_FRING1","SL_LEAV1","SL_OH1","2003-10-01","ESC37895",null,60.55,0,1,0,0.2,145.32]
["SL_TMUC","ESC","SL_FRING1","SL_LEAV1","SL_OH1","2004-10-01","ESC38261",null,60.55,0.029,1,0,0.2,149.53427999999997]
["SL_TMUC","ESC","SL_FRING1","SL_LEAV1","SL_OH1","2005-10-01","ESC38626",null,60.55,0.057812,1,0,0.2,153.72123983999998]
["SL_TMUC","ESC","SL_FRING1","SL_LEAV1","SL_OH1","2006-10-01","ESC38991",null,60.55,0.085315,1,0,0.2,157.7179758]
["SL_TMUC","ESC","SL_FRING1","SL_LEAV1","SL_OH1","2007-10-01","ESC39356",null,60.55,0.113533,1,0,0.2,161.81861555999998]
["SL_TMUC","ESC","SL_FRING1","SL_LEAV1","SL_OH1","2008-10-01","ESC39722",null,60.55,0.142485,1,0,0.2,166.02592019999997]
["SL_TMUC1","ESC1","SL_FRING1","SL_LEAV1","SL_OHN1","2005-10-01","ESC138626",null,60.55,0,1,0,0.2,145.32]
["SL_TMUC1","ESC1","SL_FRING1","SL_LEAV1","SL_OHN1","2006-10-01","ESC138991",null,60.55,0.026,1,0,0.2,149.09832]
["SL_TMUC1","ESC1","SL_FRING1","SL_LEAV1","SL_OHN1","2007-10-01","ESC139356",null,60.55,0.052676,1,0,0.2,152.97487632]
["SL_TMUC1","ESC1","SL_FRING1","SL_LEAV1","SL_OHN1","2008-10-01","ESC139722",null,60.55,0.08004558,1,0,0.2,156.9522236856]
["SL_TMUC2","ESC2","SL_FRING1","SL_LEAV1","SL_OHN1","2006-10-01","ESC238991",null,60.55,0.023,1,0,0.2,148.66235999999998]
["SL_TMUC2","ESC2","SL_FRING1","SL_LEAV1","SL_OHN1","2007-10-01","ESC239356",null,60.55,0.046529,1,0,0.2,152.08159428]
["SL_TMUC2","ESC2","SL_FRING1","SL_LEAV1","SL_OHN1","2008-10-01","ESC239722",null,60.55,0.070599,1,0,0.2,155.57944668000002]
["SL_TMUC2","ESC2","SL_FRING1","SL_LEAV1","SL_OHN1","2009-10-01","ESC240087",null,60.55,0.095223,1,0,0.2,159.15780636000002]
["SL_TMUC2","ESC2","SL_FRING1","SL_LEAV1","SL_OHN1","2010-10-01","ESC240452",null,60.55,0.120413,1,0,0.2,162.81841716000002]
["SL_TMUC2","ESC2","SL_FRING1","SL_LEAV1","SL_OHN1","2011-10-01","ESC240817",null,60.55,0.120413,1,0,0.2,162.81841716000002]
["SL_TMUC2","ESC2","SL_FRING1","SL_LEAV1","SL_OHN1","2012-10-01","ESC241183",null,60.55,null,1,0,0.2,145.32]
["SL_TMUE","ESC","SL_OH1",null,null,"2003-10-01","ESC37895",null,77.99,0,0.2,null,null,93.588]
["SL_TMUE","ESC","SL_OH1",null,null,"2004-10-01","ESC38261",null,77.99,0.029,0.2,null,null,96.30205199999999]
["SL_TMUE","ESC","SL_OH1",null,null,"2005-10-01","ESC38626",null,77.99,0.057812,0.2,null,null,98.998509456]
["SL_TMUE","ESC","SL_OH1",null,null,"2006-10-01","ESC38991",null,77.99,0.085315,0.2,null,null,101.57246021999998]
["SL_TMUE","ESC","SL_OH1",null,null,"2007-10-01","ESC39356",null,77.99,0.113533,0.2,null,null,104.21332640399999]
["SL_TMUE","ESC","SL_OH1",null,null,"2008-10-01","ESC39722",null,77.99,0.142485,0.2,null,null,106.92288617999999]
["SL_TMUE1","ESC1","SL_OHN1",null,null,"2005-10-01","ESC138626",null,77.99,0,0.2,null,null,93.588]
["SL_TMUE1","ESC1","SL_OHN1",null,null,"2006-10-01","ESC138991",null,77.99,0.026,0.2,null,null,96.021288]
["SL_TMUE1","ESC1","SL_OHN1",null,null,"2007-10-01","ESC139356",null,77.99,0.052676,0.2,null,null,98.51784148799999]
["SL_TMUE1","ESC1","SL_OHN1",null,null,"2008-10-01","ESC139722",null,77.99,0.08004558,0.2,null,null,101.07930574103999]
["SL_TMUE2","ESC2","SL_OHN1",null,null,"2006-10-01","ESC238991",null,77.99,0.023,0.2,null,null,95.74052399999998]
["SL_TMUE2","ESC2","SL_OHN1",null,null,"2007-10-01","ESC239356",null,77.99,0.046529,0.2,null,null,97.942556052]
["SL_TMUE2","ESC2","SL_OHN1",null,null,"2008-10-01","ESC239722",null,77.99,0.070599,0.2,null,null,100.195219212]
["SL_TMUE2","ESC2","SL_OHN1",null,null,"2009-10-01","ESC240087",null,77.99,0.095223,0.2,null,null,102.49973012400001]
["SL_TMUE2","ESC2","SL_OHN1",null,null,"2010-10-01","ESC240452",null,77.99,0.120413,0.2,null,null,104.85721184399999]
["SL_TMUE2","ESC2","SL_OHN1",null,null,"2011-10-01","ESC240817",null,77.99,0.120413,0.2,null,null,104.85721184399999]
["SL_TMUE2","ESC2","SL_OHN1",null,null,"2012-10-01","ESC241183",null,77.99,null,0.2,null,null,93.588]
["SL_TMUI","ESC","SL_OH1",null,null,"2003-10-01","ESC37895",null,61.62,0,0.2,null,null,73.94399999999999]
["SL_TMUI","ESC","SL_OH1",null,null,"2004-10-01","ESC38261",null,61.62,0.029,0.2,null,null,76.08837599999998]
["SL_TMUI","ESC","SL_OH1",null,null,"2005-10-01","ESC38626",null,61.62,0.057812,0.2,null,null,78.218850528]
["SL_TMUI","ESC","SL_OH1",null,null,"2006-10-01","ESC38991",null,61.62,0.085315,0.2,null,null,80.25253235999999]
["SL_TMUI","ESC","SL_OH1",null,null,"2007-10-01","ESC39356",null,61.62,0.113533,0.2,null,null,82.33908415199998]
["SL_TMUI","ESC","SL_OH1",null,null,"2008-10-01","ESC39722",null,61.62,0.142485,0.2,null,null,84.47991083999999]
["SL_TMUI1","ESC1","SL_OHN1",null,null,"2005-10-01","ESC138626",null,61.62,0,0.2,null,null,73.94399999999999]
["SL_TMUI1","ESC1","SL_OHN1",null,null,"2006-10-01","ESC138991",null,61.62,0.026,0.2,null,null,75.86654399999999]
["SL_TMUI1","ESC1","SL_OHN1",null,null,"2007-10-01","ESC139356",null,61.62,0.052676,0.2,null,null,77.83907414399998]
["SL_TMUI1","ESC1","SL_OHN1",null,null,"2008-10-01","ESC139722",null,61.62,0.08004558,0.2,null,null,79.86289036751998]
["SL_TMUI2","ESC2","SL_OHN1",null,null,"2006-10-01","ESC238991",null,61.62,0.023,0.2,null,null,75.64471199999998]
["SL_TMUI2","ESC2","SL_OHN1",null,null,"2007-10-01","ESC239356",null,61.62,0.046529,0.2,null,null,77.38454037599999]
["SL_TMUI2","ESC2","SL_OHN1",null,null,"2008-10-01","ESC239722",null,61.62,0.070599,0.2,null,null,79.164372456]
["SL_TMUI2","ESC2","SL_OHN1",null,null,"2009-10-01","ESC240087",null,61.62,0.095223,0.2,null,null,80.985169512]
["SL_TMUI2","ESC2","SL_OHN1",null,null,"2010-10-01","ESC240452",null,61.62,0.120413,0.2,null,null,82.847818872]
["SL_TMUI2","ESC2","SL_OHN1",null,null,"2011-10-01","ESC240817",null,61.62,0.120413,0.2,null,null,82.847818872]
["SL_TMUI2","ESC2","SL_OHN1",null,null,"2012-10-01","ESC241183",null,61.62,null,0.2,null,null,73.94399999999999]
["SL_TMUO","ESC","SL_OH1",null,null,"2003-10-01","ESC37895",null,64.45,0,0.2,null,null,77.34]
["SL_TMUO","ESC","SL_OH1",null,null,"2004-10-01","ESC38261",null,64.45,0.029,0.2,null,null,79.58286]
["SL_TMUO","ESC","SL_OH1",null,null,"2005-10-01","ESC38626",null,64.45,0.057812,0.2,null,null,81.81118008]
["SL_TMUO","ESC","SL_OH1",null,null,"2006-10-01","ESC38991",null,64.45,0.085315,0.2,null,null,83.9382621]
["SL_TMUO","ESC","SL_OH1",null,null,"2007-10-01","ESC39356",null,64.45,0.113533,0.2,null,null,86.12064222]
["SL_TMUO","ESC","SL_OH1",null,null,"2008-10-01","ESC39722",null,64.45,0.142485,0.2,null,null,88.35978990000001]
["SL_TMUO1","ESC1","SL_OHN1",null,null,"2005-10-01","ESC138626",null,64.45,0,0.2,null,null,77.34]
["SL_TMUO1","ESC1","SL_OHN1",null,null,"2006-10-01","ESC138991",null,64.45,0.026,0.2,null,null,79.35084]
["SL_TMUO1","ESC1","SL_OHN1",null,null,"2007-10-01","ESC139356",null,64.45,0.052676,0.2,null,null,81.41396184]
["SL_TMUO1","ESC1","SL_OHN1",null,null,"2008-10-01","ESC139722",null,64.45,0.08004558,0.2,null,null,83.5307251572]
["SL_TMUO2","ESC2","SL_OHN1",null,null,"2006-10-01","ESC238991",null,64.45,0.023,0.2,null,null,79.11882]
["SL_TMUO2","ESC2","SL_OHN1",null,null,"2007-10-01","ESC239356",null,64.45,0.046529,0.2,null,null,80.93855286]
["SL_TMUO2","ESC2","SL_OHN1",null,null,"2008-10-01","ESC239722",null,64.45,0.070599,0.2,null,null,82.80012666000002]
["SL_TMUO2","ESC2","SL_OHN1",null,null,"2009-10-01","ESC240087",null,64.45,0.095223,0.2,null,null,84.70454682]
["SL_TMUO2","ESC2","SL_OHN1",null,null,"2010-10-01","ESC240452",null,64.45,0.120413,0.2,null,null,86.65274142]
["SL_TMUO2","ESC2","SL_OHN1",null,null,"2011-10-01","ESC240817",null,64.45,0.120413,0.2,null,null,86.65274142]
["SL_TMUO2","ESC2","SL_OHN1",null,null,"2012-10-01","ESC241183",null,64.45,null,0.2,null,null,77.34]
["SL_TMUP","ESC","SL_OH1",null,null,"2003-10-01","ESC37895",null,74.69,0,0.2,null,null,89.628]
["SL_TMUP","ESC","SL_OH1",null,null,"2004-10-01","ESC38261",null,74.69,0.029,0.2,null,null,92.227212]
["SL_TMUP","ESC","SL_OH1",null,null,"2005-10-01","ESC38626",null,74.69,0.057812,0.2,null,null,94.80957393599998]
["SL_TMUP","ESC","SL_OH1",null,null,"2006-10-01","ESC38991",null,74.69,0.085315,0.2,null,null,97.27461282]
["SL_TMUP","ESC","SL_OH1",null,null,"2007-10-01","ESC39356",null,74.69,0.113533,0.2,null,null,99.80373572399999]
["SL_TMUP","ESC","SL_OH1",null,null,"2008-10-01","ESC39722",null,74.69,0.142485,0.2,null,null,102.39864558]
["SL_TMUP1","ESC1","SL_OHN1",null,null,"2005-10-01","ESC138626",null,74.69,0,0.2,null,null,89.628]
["SL_TMUP1","ESC1","SL_OHN1",null,null,"2006-10-01","ESC138991",null,74.69,0.026,0.2,null,null,91.958328]
["SL_TMUP1","ESC1","SL_OHN1",null,null,"2007-10-01","ESC139356",null,74.69,0.052676,0.2,null,null,94.34924452799999]
["SL_TMUP1","ESC1","SL_OHN1",null,null,"2008-10-01","ESC139722",null,74.69,0.08004558,0.2,null,null,96.80232524424]
["SL_TMUP2","ESC2","SL_OHN1",null,null,"2006-10-01","ESC238991",null,74.69,0.023,0.2,null,null,91.68944399999998]
["SL_TMUP2","ESC2","SL_OHN1",null,null,"2007-10-01","ESC239356",null,74.69,0.046529,0.2,null,null,93.798301212]
["SL_TMUP2","ESC2","SL_OHN1",null,null,"2008-10-01","ESC239722",null,74.69,0.070599,0.2,null,null,95.955647172]
["SL_TMUP2","ESC2","SL_OHN1",null,null,"2009-10-01","ESC240087",null,74.69,0.095223,0.2,null,null,98.16264704400001]
["SL_TMUP2","ESC2","SL_OHN1",null,null,"2010-10-01","ESC240452",null,74.69,0.120413,0.2,null,null,100.42037636399999]
["SL_TMUP2","ESC2","SL_OHN1",null,null,"2011-10-01","ESC240817",null,74.69,0.120413,0.2,null,null,100.42037636399999]
["SL_TMUP2","ESC2","SL_OHN1",null,null,"2012-10-01","ESC241183",null,74.69,null,0.2,null,null,89.628]
["SL_TMUW","ESC","SL_OH1",null,null,"2003-10-01","ESC37895",null,61.62,0,0.2,null,null,73.94399999999999]
["SL_TMUW","ESC","SL_OH1",null,null,"2004-10-01","ESC38261",null,61.62,0.029,0.2,null,null,76.08837599999998]
["SL_TMUW","ESC","SL_OH1",null,null,"2005-10-01","ESC38626",null,61.62,0.057812,0.2,null,null,78.218850528]
["SL_TMUW","ESC","SL_OH1",null,null,"2006-10-01","ESC38991",null,61.62,0.085315,0.2,null,null,80.25253235999999]
["SL_TMUW","ESC","SL_OH1",null,null,"2007-10-01","ESC39356",null,61.62,0.113533,0.2,null,null,82.33908415199998]
["SL_TMUW","ESC","SL_OH1",null,null,"2008-10-01","ESC39722",null,61.62,0.142485,0.2,null,null,84.47991083999999]
["SL_TMUW1","ESC1","SL_OHN1",null,null,"2005-10-01","ESC138626",null,61.62,0,0.2,null,null,73.94399999999999]
["SL_TMUW1","ESC1","SL_OHN1",null,null,"2006-10-01","ESC138991",null,61.62,0.026,0.2,null,null,75.86654399999999]
["SL_TMUW1","ESC1","SL_OHN1",null,null,"2007-10-01","ESC139356",null,61.62,0.052676,0.2,null,null,77.83907414399998]
["SL_TMUW1","ESC1","SL_OHN1",null,null,"2008-10-01","ESC139722",null,61.62,0.08004558,0.2,null,null,79.86289036751998]
["SL_TMUW2","ESC2","SL_OHN1",null,null,"2006-10-01","ESC238991",null,61.62,0.023,0.2,null,null,75.64471199999998]
["SL_TMUW2","ESC2","SL_OHN1",null,null,"2007-10-01","ESC239356",null,61.62,0.046529,0.2,null,null,77.38454037599999]
["SL_TMUW2","ESC2","SL_OHN1",null,null,"2008-10-01","ESC239722",null,61.62,0.070599,0.2,null,null,79.164372456]
["SL_TMUW2","ESC2","SL_OHN1",null,null,"2009-10-01","ESC240087",null,61.62,0.095223,0.2,null,null,80.985169512]
["SL_TMUW2","ESC2","SL_OHN1",null,null,"2010-10-01","ESC240452",null,61.62,0.120413,0.2,null,null,82.847818872]
["SL_TMUW2","ESC2","SL_OHN1",null,null,"2011-10-01","ESC240817",null,61.62,0.120413,0.2,null,null,82.847818872]
["SL_TMUW2","ESC2","SL_OHN1",null,null,"2012-10-01","ESC241183",null,61.62,null,0.2,null,null,73.94399999999999]
["SL_TSM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_TSM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_TSM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_TSM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_TSM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_TSM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_TSM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,54.62,0,0.305,0.21,0.2,103.49725319999999]
["SL_TSM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,54.62,0.026,0.305,0.21,0.2,106.18818178319998]
["SL_TSM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,54.62,0.052676,0.305,0.21,0.2,108.94907450956318]
["SL_TSM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,54.62,0.08004558,0.305,0.21,0.2,111.78175086080083]
["SL_TSM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,54.62,0.023,0.305,0.21,0.2,105.87769002359997]
["SL_TSM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,54.62,0.046529,0.305,0.21,0.2,108.31287689414279]
["SL_TSM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,54.62,0.070599,0.305,0.21,0.2,110.80405577866678]
["SL_TSM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,54.62,0.095223,0.305,0.21,0.2,113.3525721414636]
["SL_TSM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,54.62,0.120413,0.305,0.21,0.2,115.95966794957158]
["SL_TSM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,54.62,0.120413,0.305,0.21,0.2,115.95966794957158]
["SL_TSM2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,54.62,null,0.305,0.21,0.2,103.49725319999999]
["SL_UPGR",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_UPGR1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_UPGR2",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_UTR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_UTR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_UTR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_UTR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_UTR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_UTR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_UTR1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,54.62,0,0.305,0.21,0.2,103.49725319999999]
["SL_UTR1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,54.62,0.026,0.305,0.21,0.2,106.18818178319998]
["SL_UTR1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,54.62,0.052676,0.305,0.21,0.2,108.94907450956318]
["SL_UTR1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,54.62,0.08004558,0.305,0.21,0.2,111.78175086080083]
["SL_UTR2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC238991",null,54.62,0.023,0.305,0.21,0.2,105.87769002359997]
["SL_UTR2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC239356",null,54.62,0.046529,0.305,0.21,0.2,108.31287689414279]
["SL_UTR2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC239722",null,54.62,0.070599,0.305,0.21,0.2,110.80405577866678]
["SL_UTR2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2009-10-01","ESC240087",null,54.62,0.095223,0.305,0.21,0.2,113.3525721414636]
["SL_UTR2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2010-10-01","ESC240452",null,54.62,0.120413,0.305,0.21,0.2,115.95966794957158]
["SL_UTR2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2011-10-01","ESC240817",null,54.62,0.120413,0.305,0.21,0.2,115.95966794957158]
["SL_UTR2","ESC2","SL_FRNG1","SL_LEAV2","SL_OHN1","2012-10-01","ESC241183",null,54.62,null,0.305,0.21,0.2,103.49725319999999]
["SPR",{"$nulls":5},"",{"$nulls":6},0]
[null,"END",{"$nulls":4},"END",{"$nulls":6},0]

{"sheet":"Master","index":3,"n_rows":1487,"n_cols":58,"rows_kept":1487,"cut":false,"hidden":false,"merged":[[0,37,0,38],[0,39,0,40],[0,41,0,42],[0,43,0,44],[0,47,0,48],[1,0,1,5],[0,18,0,20],[0,16,0,17],[0,45,0,46],[0,32,0,33],[0,34,0,36],[0,0,0,5]],"flags":["formulas_cached_only"]}
["WBS Level",{"$nulls":5},"P3","C/A","W/P","April 2007 CR Rebaseline","Early","Early","OBS","Fund","Res","Units","Budgeted Quantity",null,"Fully Burdened and Escalated Cost",null,null,"Work","Contingency","Contingency","Design","Judgement",{"$nulls":6},"Work Rem. Bud. Qtty",null,"Work Rem. Full Burd and Escltd Cost",null,null,"FY07",null,"FY08",null,"FY09",null,"FY10",null,"FY11",null,"FY12",null,"Contingency","Contingency","Design","Judgement","Basis","Program",null,"Tech"]
[{"$nulls":6},"ID","Number","Number","Description","Start","Finish",null,"Type","Code",null,"Hours","$$","Labor","M&S","Total (No Conting)","Remaining","%","$","Maturity","Factor",{"$nulls":6},"Hours","$$","Labor","M&S","Total","BAC","% of Wrk Rem.","BAC","% of Wrk Rem.","BAC","% of Wrk Rem.","BAC","% of Wrk Rem.","BAC","% of Wrk Rem.","BAC","% of Wrk Rem.","%","$","Maturity","Factor","of Estimate","Phase","CAM","Lead","CAM"]
["1","2","3","4","5","6",{"$nulls":20},"Flag","Cam"]
[]
["1","  ","  ","  ","  ","  ",null,null,null,"LCLS PROJECT - PED & CONSTRUCTION                           "]
["1","01","  ","  ","  ","  ",null,null,null,"LCLS PROJECT MGMT, PLANNING & ADMN (TEC)                    "]
["1","01","01","  ","  ","  ",null,null,null,"Environment, Safety & Health                                "]
["1","01","01","01","  ","  ",null,null,null,"Radiation Physics                                           ",{"$nulls":47},"Wendy Sisson"]
["1","01","01","02","  ","  ",null,null,null,"ESH Management & Coordination                               ",{"$nulls":47},"Wendy Sisson"]
["1","01","01","03","  ","  ",null,null,null,"Seismic & Engineering Support                               ",{"$nulls":47},"Wendy Sisson"]
["1","01","02","  ","  ","  ",null,null,null,"Project Management                                          ",{"$nulls":47},"Wendy Sisson"]
["1","01","02","01","  ","  ",null,null,null,"Project Management Office                                   ",{"$nulls":47},"Wendy Sisson"]
["1","01","02","01","01","  ",null,null,null,"Project Office - General                                    ",{"$nulls":47},"Wendy Sisson"]
["1","01","02","01","02","  ",null,null,null,"Project Support                                             ",{"$nulls":47},"Wendy Sisson"]
["1","01","02","01","03","  ",null,null,null,"Project Office M&S                                          ",{"$nulls":47},"Wendy Sisson"]
["1","01","02","01","04","  ",null,null,null,"SSRL Physics Support                                        ",{"$nulls":47},"Wendy Sisson"]
["1","01","03","  ","  ","  ",null,null,null,"Technical Integration                                       "]
["1","01","03","01","  ","  ",null,null,null,"Global Laser Coordination                                   ",{"$nulls":47},"Wendy Sisson"]
["1","01","03","02","  ","  ",null,null,null,"Global Alignment Coordination                               ",{"$nulls":47},"Wendy Sisson"]
["1","01","03","03","  ","  ",null,null,null,"System Integration                                          ",{"$nulls":47},"Wendy Sisson"]
["1","01","03","05","  ","  ",null,null,null,"Global Controls                                             ",{"$nulls":47},"Hamid Shoaee"]
["1","01","03","05","01","  ",null,null,null,"Global Controls Management                                  ",{"$nulls":47},"Hamid Shoaee"]
["1","01","03","05","02","  ",null,null,null,"LLRF Controls                                               ",{"$nulls":47},"Hamid Shoaee"]
["1","01","03","05","03","  ",null,null,null,"E-beam Diagnostics & Controls                               ",{"$nulls":47},"Hamid Shoaee"]
["1","01","03","05","03","01",null,null,null,"Controls - Wire Scanners                                    ",{"$nulls":47},"Hamid Shoaee"]
["1","01","03","05","03","02",null,null,null,"Controls - Toroids                                          ",{"$nulls":47},"Hamid Shoaee"]
["1","01","03","05","03","03",null,null,null,"Controls - Faraday Cups                                     ",{"$nulls":47},"Hamid Shoaee"]
["1","01","03","05","03","04",null,null,null,"Controls - Tune-Up Dump                                     ",{"$nulls":47},"Hamid Shoaee"]
["1","01","03","05","03","05",null,null,null,"Controls - Profile Monitors                                 ",{"$nulls":47},"Hamid Shoaee"]
["1","01","03","05","03","06",null,null,null,"Controls - E/O Diagnostics                                  ",{"$nulls":47},"Hamid Shoaee"]
["1","01","03","05","03","07",null,null,null,"Controls - BPM                                              ",{"$nulls":47},"Hamid Shoaee"]
["1","01","03","05","03","08",null,null,null,"Controls - Stopppers                                        ",{"$nulls":47},"Hamid Shoaee"]
["1","01","03","05","03","09",null,null,null,"Controls - Bunch Length Monitors                            ",{"$nulls":47},"Hamid Shoaee"]
["1","01","03","05","03","10",null,null,null,"Controls - Beam Loss Monitors                               ",{"$nulls":47},"Hamid Shoaee"]
["1","01","03","05","03","11",null,null,null,"Controls - Cherenkov Radiation Detector                     ",{"$nulls":47},"Hamid Shoaee"]
["1","01","03","05","03","12",null,null,null,"Controls - Movable Collimator                               ",{"$nulls":47},"Hamid Shoaee"]
["1","01","03","05","04","  ",null,null,null,"Laser Controls Design                                       ",{"$nulls":47},"Hamid Shoaee"]
["1","01","03","05","05","  ",null,null,null,"Laser Heater Controls                                       ",{"$nulls":47},"Hamid Shoaee"]
["1","01","03","05","06","  ",null,null,null,"Timing Controls                                             ",{"$nulls":47},"Hamid Shoaee"]
["1","01","03","05","07","  ",null,null,null,"Vacuum Controls                                             ",{"$nulls":47},"Hamid Shoaee"]
["1","01","03","05","09","  ",null,null,null,"Power Supply Controls                                       ",{"$nulls":47},"Hamid Shoaee"]
["1","01","03","05","10","  ",null,null,null,"Controls - PPS                                              ",{"$nulls":47},"Hamid Shoaee"]
["1","01","03","05","11","  ",null,null,null,"Controls - MPS                                              ",{"$nulls":47},"Hamid Shoaee"]
["1","01","03","05","12","  ",null,null,null,"Global Controls Management                                  ",{"$nulls":47},"Hamid Shoaee"]
["1","01","03","05","12","01",null,null,null,"Global Controls Management LOE                              ",{"$nulls":47},"Hamid Shoaee"]
["1","01","03","05","12","02",null,null,null,"Global Controls Management                                  ",{"$nulls":47},"Hamid Shoaee"]
["1","01","03","05","13","  ",null,null,null,"SLC Aware IOC                                               ",{"$nulls":47},"Hamid Shoaee"]
["1","01","03","05","14","  ",null,null,null,"Controls - S/W Application                                  ",{"$nulls":47},"Hamid Shoaee"]
["1","01","03","05","15","  ",null,null,null,"Controls - BCS                                              ",{"$nulls":47},"Hamid Shoaee"]
["1","01","03","06","  ","  ",null,null,null,"Technical Requirements/Parameters                           ",{"$nulls":47},"Wendy Sisson"]
["1","01","04","  ","  ","  ",null,null,null,"Education Support                                           ",{"$nulls":47},"Wendy Sisson"]
["1","01","04","01","  ","  ",null,null,null,"Education/Outreach Travel                                   ",{"$nulls":47},"Wendy Sisson"]
["1","01","04","02","  ","  ",null,null,null,"Education/Outreach M&S                                      ",{"$nulls":47},"Wendy Sisson"]
["1","02","  ","  ","  ","  ",null,null,null,"INJECTOR SYSTEM                                             "]
["1","02","01","  ","  ","  ",null,null,null,"Injector System Management & Integration                    ",{"$nulls":47},"Jose Chan"]
["1","02","01","01","  ","  ",null,null,null,"Injector System Integration                                 ",{"$nulls":47},"Jose Chan"]
["1","02","01","01","01","  ",null,null,null,"Injector Region Integration                                 ",{"$nulls":47},"Jose Chan"]
["1","02","01","01","02","  ",null,null,null,"Gun Area Integration                                        ",{"$nulls":47},"Jose Chan"]
["1","02","01","01","03","  ",null,null,null,"Accelerator Area Integration                                ",{"$nulls":47},"Jose Chan"]
["1","02","01","01","04","  ",null,null,null,"Heater Area Integration                                     ",{"$nulls":47},"Jose Chan"]
["1","02","01","01","05","  ",null,null,null,"Wall Area Integration                                       ",{"$nulls":47},"Jose Chan"]
["1","02","01","01","06","  ",null,null,null,"Insertion Area Integration                                  ",{"$nulls":47},"Jose Chan"]
["1","02","01","01","07","  ",null,null,null,"Spectrometer Area Integration                               ",{"$nulls":47},"Jose Chan"]
["1","02","01","01","08","  ",null,null,null,"Drive Laser Integration                                     ",{"$nulls":47},"Jose Chan"]
["1","02","01","04","  ","  ",null,null,null,"Injector System Integration Effort / M&S                    ",{"$nulls":47},"Jose Chan"]
["1","02","02","  ","  ","  ",null,null,null,"Injector Controls Subsystem                                 ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","01","  ","  ",null,null,null,"Personnel Protection Subsystem (PPS)                        ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","02","  ","  ",null,null,null,"Beam Containment Subsystem (BCS)                            ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","03","  ","  ",null,null,null,"Machine Protection Subsystem (MPS)                          ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","04","  ","  ",null,null,null,"Injector Power Conversion                                   ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","04","01","  ",null,null,null,"Beamline Pwr Supplies - (Dipole Type)                       ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","04","01","01",null,null,null,"10kw Power Supply - (Solenoid 1)                            ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","04","01","02",null,null,null,"30kw Power Supply - (Solenoid 2)                            ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","04","01","03",null,null,null,"2kw Power Supply - (B0.5 Spect)                             ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","04","01","04",null,null,null,"15kw Power Supply - (B1-2)                                  ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","04","01","05",null,null,null,"15kw Power Supply - (B3 Spect)                              ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","04","01","06",null,null,null,"10kw Power Supply - (New)                                   ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","04","02","  ",null,null,null,"Power Supply Controls                                       ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","04","03","  ",null,null,null,"Beamline Pwr Supplies - (Trim Type)                         ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","04","03","01",null,null,null,"12Amp Power Supply - (MCOR_1)                               ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","04","03","02",null,null,null,"30Amp Power Supply - (MCOR_2)                               ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","04","03","03",null,null,null,"30Amp Power Supply - (MCOR_3)                               ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","04","03","04",null,null,null,"30Amp Power Supply - (MCOR_4)                               ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","04","04","  ",null,null,null,"Beamline Pwr Supply - Misc Hdwr                             ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","04","05","  ",null,null,null,"Magnet Interlock Protection System                          ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","05","  ","  ",null,null,null,"LLRF Controls                                               ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","05","01","  ",null,null,null,"Readback & Controls - RF Gun LLRF & Temperature             ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","05","02","  ",null,null,null,"Readback & Controls - L0 LLRF                               ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","05","03","  ",null,null,null,"Readback & Controls - Transverse Cavity LLRF                ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","05","04","  ",null,null,null,"S-Band Cavity Controls                                      ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","05","05","  ",null,null,null,"EO Phase Controls                                           ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","06","  ","  ",null,null,null,"E-Beam Diagnostics Controls                                 ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","06","01","  ",null,null,null,"Controls - Wire Scanners                                    ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","06","02","  ",null,null,null,"Controls - BPM                                              ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","06","03","  ",null,null,null,"Controls - Toroids                                          ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","06","05","  ",null,null,null,"Controls - Profile Monitors                                 ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","06","06","  ",null,null,null,"Controls - E/O Diagnostics                                  ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","06","12","  ",null,null,null,"Controls - Movable Collimator                               ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","06","14","  ",null,null,null,"Controls - Faraday Cups                                     ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","06","15","  ",null,null,null,"Controls - Tune-Up Dump                                     ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","06","16","  ",null,null,null,"Controls - Cherenkov Radiation Detector                     ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","08","  ","  ",null,null,null,"Timing Controls                                             ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","09","  ","  ",null,null,null,"Vacuum Controls                                             ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","10","  ","  ",null,null,null,"Software & Controls Infrastructure                          ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","10","01","  ",null,null,null,"Low Level Application Software                              ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","10","02","  ",null,null,null,"High Level Application Software                             ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","10","03","  ",null,null,null,"Data Communications                                         ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","10","04","  ",null,null,null,"Computers & Crates                                          ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","11","  ","  ",null,null,null,"EPICS VXI Control Modules                                   ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","12","  ","  ",null,null,null,"Laser Controls                                              ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","12","01","  ",null,null,null,"Controls - Alignment Laser                                  ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","12","02","  ",null,null,null,"Controls - Gun Laser                                        ",{"$nulls":47},"Hamid Shoaee"]
["1","02","02","13","  ","  ",null,null,null,"Laser Heater Controls                                       ",{"$nulls":47},"Hamid Shoaee"]
["1","02","03","  ","  ","  ",null,null,null,"Injector Lasers                                             ",{"$nulls":47},"Bill White"]
["1","02","03","01","  ","  ",null,null,null,"Drive Laser Support                                         ",{"$nulls":47},"Bill White"]
["1","02","03","01","01","  ",null,null,null,"Drive Laser Support (ANL)                                   ",{"$nulls":47},"Bill White"]
["1","02","03","01","02","  ",null,null,null,"Drive Laser Support (LLNL)                                  ",{"$nulls":47},"Bill White"]
["1","02","03","02","  ","  ",null,null,null,"Drive Laser System                                          ",{"$nulls":47},"Bill White"]
["1","02","03","03","  ","  ",null,null,null,"Drive Laser Diagnostics                                     ",{"$nulls":47},"Bill White"]
["1","02","03","04","  ","  ",null,null,null,"Timing Stability Monitoring                                 ",{"$nulls":47},"Bill White"]
["1","02","03","05","  ","  ",null,null,null,"Steering Stability Feedback & Msmts                         ",{"$nulls":47},"Bill White"]
["1","02","03","06","  ","  ",null,null,null,"Pre Amp Low Power Comp                                      ",{"$nulls":47},"Bill White"]
["1","02","03","07","  ","  ",null,null,null,"Transport to Tunnel & Relay Optics                          ",{"$nulls":47},"Bill White"]
["1","02","03","08","  ","  ",null,null,null,"UV Launch, Conditioning & Diagnostics                       ",{"$nulls":47},"Bill White"]
["1","02","03","09","  ","  ",null,null,null,"Load Lock Transport System                                  ",{"$nulls":47},"Bill White"]
["1","02","03","10","  ","  ",null,null,null,"Visible Optical Transport & Optics                          ",{"$nulls":47},"Bill White"]
["1","02","03","11","  ","  ",null,null,null,"LB Infrastructure & LB System Wide Items                    ",{"$nulls":47},"Bill White"]
["1","02","03","12","  ","  ",null,null,null,"Alignment Laser                                             ",{"$nulls":47},"Bill White"]
["1","02","03","13","  ","  ",null,null,null,"Light path to Streak Camera                                 ",{"$nulls":47},"Bill White"]
["1","02","03","14","  ","  ",null,null,null,"LSR HTR - Beam Conditioning Optics (Laser Bay)              ",{"$nulls":47},"Jose Chan"]
["1","02","03","15","  ","  ",null,null,null,"LSR HTR - Transport Optics (Bay to Tunnel)                  ",{"$nulls":47},"Bill White"]
["1","02","03","16","  ","  ",null,null,null,"LSR HTR - Photon Beam Diagnostics                           ",{"$nulls":47},"Bill White"]
["1","02","03","21","  ","  ",null,null,null,"UV Conv Harmonic Generation Unit (Closed Account)           ",{"$nulls":47},"Bill White"]
["1","02","04","  ","  ","  ",null,null,null,"Injector RF Subsystem                                       ",{"$nulls":47},"Jose Chan"]
["1","02","04","01","  ","  ",null,null,null,"RF Gun & Load Lock                                          ",{"$nulls":47},"Jose Chan"]
["1","02","04","01","01","  ",null,null,null,"RF Gun                                                      ",{"$nulls":47},"Jose Chan"]
["1","02","04","01","02","  ",null,null,null,"RF Gun Supports                                             ",{"$nulls":47},"Jose Chan"]
["1","02","04","01","03","  ",null,null,null,"Gun Load Lock                                               ",{"$nulls":47},"Jose Chan"]
["1","02","04","01","04","  ",null,null,null,"Gun Load Lock Supports                                      ",{"$nulls":47},"Jose Chan"]
["1","02","04","01","05","  ",null,null,null,"Gun Solenoid                                                ",{"$nulls":47},"Jose Chan"]
["1","02","04","01","06","  ",null,null,null,"Gun Solenoid Supports                                       ",{"$nulls":47},"Jose Chan"]
["1","02","04","01","07","  ",null,null,null,"Gun RF Feed                                                 ",{"$nulls":47},"Jose Chan"]
["1","02","04","01","08","  ",null,null,null,"Gun RF Feed Supports                                        ",{"$nulls":47},"Jose Chan"]
["1","02","04","02","  ","  ",null,null,null,"Cathode Processing (CP) Station                             ",{"$nulls":47},"Jose Chan"]
["1","02","04","02","01","  ",null,null,null,"CP Cathode Assembly & Supports                              ",{"$nulls":47},"Jose Chan"]
["1","02","04","02","02","  ",null,null,null,"CP Load Lock                                                ",{"$nulls":47},"Jose Chan"]
["1","02","04","02","03","  ",null,null,null,"CP Load Lock Supports                                       ",{"$nulls":47},"Jose Chan"]
["1","02","04","02","04","  ",null,null,null,"CP Station                                                  ",{"$nulls":47},"Jose Chan"]
["1","02","04","02","05","  ",null,null,null,"Cathode Lab Infrastructure                                  ",{"$nulls":47},"Jose Chan"]
["1","02","04","03","  ","  ",null,null,null,"S-Band Low Level Timing                                     ",{"$nulls":47},"Jose Chan"]
["1","02","04","03","01","  ",null,null,null,"Controls Interface & Timing                                 ",{"$nulls":47},"Jose Chan"]
["1","02","04","03","02","  ",null,null,null,"LLRF Phase Reference System                                 ",{"$nulls":47},"Jose Chan"]
["1","02","04","03","03","  ",null,null,null,"LLRF Monitor & Control System                               ",{"$nulls":47},"Jose Chan"]
["1","02","04","03","04","  ",null,null,null,"Beam Phase Monitor Cavity                                   ",{"$nulls":47},"Jose Chan"]
["1","02","04","03","05","  ",null,null,null,"RF System S/W Development / Docs                            ",{"$nulls":47},"Jose Chan"]
["1","02","04","04","  ","  ",null,null,null,"S-Band High Power System                                    ",{"$nulls":47},"Jose Chan"]
["1","02","04","04","01","  ",null,null,null,"RF Gun High Power                                           ",{"$nulls":47},"Jose Chan"]
["1","02","04","04","02","  ",null,null,null,"L0 High Power                                               ",{"$nulls":47},"Jose Chan"]
["1","02","04","04","03","  ",null,null,null,"Transverse Cavity High Power                                ",{"$nulls":47},"Jose Chan"]
["1","02","04","05","  ","  ",null,null,null,"Injector RF Waveguide Subsystem                             ",{"$nulls":47},"Jose Chan"]
["1","02","04","05","01","  ",null,null,null,"RF Waveguides                                               ",{"$nulls":47},"Jose Chan"]
["1","02","04","05","02","  ",null,null,null,"RF Waveguide Supports                                       ",{"$nulls":47},"Jose Chan"]
["1","02","04","06","  ","  ",null,null,null,"Injector Linac Structures                                   ",{"$nulls":47},"Jose Chan"]
["1","02","04","06","01","  ",null,null,null,"L0A-0B Structure Assembly                                   ",{"$nulls":47},"Jose Chan"]
["1","02","04","06","03","  ",null,null,null,"Major Linac Support                                         ",{"$nulls":47},"Jose Chan"]
["1","02","04","06","04","  ",null,null,null,"GTL RF Phase Cavity                                         ",{"$nulls":47},"Jose Chan"]
["1","02","04","06","05","  ",null,null,null,"LTDL1 RF Kicker                                             ",{"$nulls":47},"Jose Chan"]
["1","02","05","  ","  ","  ",null,null,null,"Injector Magnets & Supports                                 ",{"$nulls":47},"Jose Chan"]
["1","02","05","01","  ","  ",null,null,null,"Injector Dipoles                                            ",{"$nulls":47},"Jose Chan"]
["1","02","05","01","01","  ",null,null,null,"Gun Spectrometer Dipole                                     ",{"$nulls":47},"Jose Chan"]
["1","02","05","01","02","  ",null,null,null,"DL1 B01 & B02 Dipoles                                       ",{"$nulls":47},"Jose Chan"]
["1","02","05","01","03","  ",null,null,null,"SAB Spectrometer Dipole                                     ",{"$nulls":47},"Jose Chan"]
["1","02","05","01","04","  ",null,null,null,"Chicane DIPOLES (4)                                         ",{"$nulls":47},"Jose Chan"]
["1","02","05","02","  ","  ",null,null,null,"Injector Quads                                              ",{"$nulls":47},"Jose Chan"]
["1","02","05","02","01","  ",null,null,null,"Gun Spectrometer Quadrupoles                                ",{"$nulls":47},"Jose Chan"]
["1","02","05","02","02","  ",null,null,null,"Injector Quadrupoles                                        ",{"$nulls":47},"Jose Chan"]
["1","02","05","02","03","  ",null,null,null,"                                                            ",{"$nulls":47},"Jose Chan"]
["1","02","05","03","  ","  ",null,null,null,"Injector Steering Coils                                     ",{"$nulls":47},"Jose Chan"]
["1","02","05","03","01","  ",null,null,null,"Gun Solenoid Correctors                                     ",{"$nulls":47},"Jose Chan"]
["1","02","05","03","02","  ",null,null,null,"Gun Spectrometer Correctors                                 ",{"$nulls":47},"Jose Chan"]
["1","02","05","03","03","  ",null,null,null,"Injector Correctors - A                                     ",{"$nulls":47},"Jose Chan"]
["1","02","05","03","04","  ",null,null,null,"Injector Correctors - D (Gun)                               ",{"$nulls":47},"Jose Chan"]
["1","02","05","03","05","  ",null,null,null,"Gun Solenoid Quadrupole Correctors                          ",{"$nulls":47},"Jose Chan"]
["1","02","05","04","  ","  ",null,null,null,"Linac Solenoid                                              ",{"$nulls":47},"Jose Chan"]
["1","02","05","05","  ","  ",null,null,null,"Injector Laser Heater Subsystem                             ",{"$nulls":47},"Jose Chan"]
["1","02","05","05","01","  ",null,null,null,"System Design & Optimization (LSR HTR)                      ",{"$nulls":47},"Jose Chan"]
["1","02","05","05","02","  ",null,null,null,"Injector Undulator                                          ",{"$nulls":47},"Jose Chan"]
["1","02","06","  ","  ","  ",null,null,null,"Injector Vacuum & Supports                                  ",{"$nulls":47},"Jose Chan"]
["1","02","06","01","  ","  ",null,null,null,"Injector Vacuum Engineering                                 ",{"$nulls":47},"Jose Chan"]
["1","02","06","02","  ","  ",null,null,null,"Injector Vacuum Components                                  ",{"$nulls":47},"Jose Chan"]
["1","02","06","03","  ","  ",null,null,null,"Injector Vacuum Special Chambers                            ",{"$nulls":47},"Jose Chan"]
["1","02","06","04","  ","  ",null,null,null,"Injector Vacuum Supports Engineering                        ",{"$nulls":47},"Jose Chan"]
["1","02","06","05","  ","  ",null,null,null,"Injector Vacuum Support Components                          ",{"$nulls":47},"Jose Chan"]
["1","02","06","08","  ","  ",null,null,null,"DL1 Vacuum Chamber                                          ",{"$nulls":47},"Jose Chan"]
["1","02","06","10","  ","  ",null,null,null,"DL1TL Vacuum Components                                     ",{"$nulls":47},"Jose Chan"]
["1","02","07","  ","  ","  ",null,null,null,"Injector Diagnostics                                        ",{"$nulls":47},"Jose Chan"]
["1","02","07","01","  ","  ",null,null,null,"Beam Position Monitors                                      ",{"$nulls":47},"Jose Chan"]
["1","02","07","01","01","  ",null,null,null,"Large Aperture BPM                                          ",{"$nulls":47},"Jose Chan"]
["1","02","07","01","02","  ",null,null,null,"Small Aperture BPM                                          ",{"$nulls":47},"Jose Chan"]
["1","02","07","01","06","  ",null,null,null,"                                                            ",{"$nulls":47},"Jose Chan"]
["1","02","07","02","  ","  ",null,null,null,"Current Monitors                                            ",{"$nulls":47},"Jose Chan"]
["1","02","07","02","01","  ",null,null,null,"Current Monitors                                            ",{"$nulls":47},"Jose Chan"]
["1","02","07","03","  ","  ",null,null,null,"Bunch Length Monitors                                       ",{"$nulls":47},"Jose Chan"]
["1","02","07","03","01","  ",null,null,null,"Bunch Length Monitors                                       ",{"$nulls":47},"Jose Chan"]
["1","02","07","04","  ","  ",null,null,null,"Profile Monitors                                            ",{"$nulls":47},"Jose Chan"]
["1","02","07","04","01","  ",null,null,null,"Profile Monitors                                            ",{"$nulls":47},"Jose Chan"]
["1","02","07","04","03","  ",null,null,null,"GS Faraday Cup/YAG2                                         ",{"$nulls":47},"Jose Chan"]
["1","02","07","04","06","  ",null,null,null,"DL1 OTR/YAG                                                 ",{"$nulls":47},"Jose Chan"]
["1","02","07","04","07","  ",null,null,null,"DL1TL OTR/YAG                                               ",{"$nulls":47},"Jose Chan"]
["1","02","07","04","08","  ",null,null,null,"LTDL1 OTR/YAG (6)                                           ",{"$nulls":47},"Jose Chan"]
["1","02","07","05","  ","  ",null,null,null," Injector Wire Scanners                                     ",{"$nulls":47},"Jose Chan"]
["1","02","07","06","  ","  ",null,null,null,"LSR HTR - Electron Beam Diagnostics                         ",{"$nulls":47},"Jose Chan"]
["1","02","07","07","  ","  ",null,null,null,"PPS Stopper                                                 ",{"$nulls":47},"Jose Chan"]
["1","02","17","  ","  ","  ",null,null,null,"Injector Installation & Alignment                           ",{"$nulls":47},"Jose Chan"]
["1","02","17","01","  ","  ",null,null,null,"Injector Infrastructure Installation                        ",{"$nulls":47},"Jose Chan"]
["1","02","17","02","  ","  ",null,null,null,"Injector Controls Subsystem Install & Align                 ",{"$nulls":47},"Jose Chan"]
["1","02","17","03","  ","  ",null,null,null,"Injector Lasers Install & Align                             ",{"$nulls":47},"Jose Chan"]
["1","02","17","04","  ","  ",null,null,null,"Gun Area Integration                                        ",{"$nulls":47},"Jose Chan"]
["1","02","17","06","  ","  ",null,null,null,"Accelerator Area Integration                                ",{"$nulls":47},"Jose Chan"]
["1","02","17","07","  ","  ",null,null,null,"Heater Area Integration                                     ",{"$nulls":47},"Jose Chan"]
["1","02","17","08","  ","  ",null,null,null,"Wall Area Integration                                       ",{"$nulls":47},"Jose Chan"]
["1","02","17","09","  ","  ",null,null,null,"Insertion Area Integration                                  ",{"$nulls":47},"Jose Chan"]
["1","02","17","11","  ","  ",null,null,null,"Spectrometer Area Integration                               ",{"$nulls":47},"Jose Chan"]
["1","02","17","12","  ","  ",null,null,null,"Injector RF High Power System Install & Align               ",{"$nulls":47},"Jose Chan"]
["1","02","17","13","  ","  ",null,null,null,"Injector RF Low Level Install & Align                       ",{"$nulls":47},"Jose Chan"]
["1","02","17","14","  ","  ",null,null,null,"Cathode and Load Lock Install & Align                       ",{"$nulls":47},"Jose Chan"]
["1","02","17","15","  ","  ",null,null,null,"Injector Laser Heater Subsystem Install & Align             ",{"$nulls":47},"Jose Chan"]
["1","02","17","17","  ","  ",null,null,null,"Power  Conversion Subsystem Installation                    ",{"$nulls":47},"Jose Chan"]
["1","02","17","18","  ","  ",null,null,null,"Cathode Processing Center Installation                      ",{"$nulls":47},"Jose Chan"]
["1","03","  ","  ","  ","  ",null,null,null,"LINAC SYSTEM                                                "]
["1","03","01","  ","  ","  ",null,null,null,"System Management & Integration                             ",{"$nulls":47},"Jose Chan"]
["1","03","01","01","  ","  ",null,null,null,"Linac Mechanical Integration                                ",{"$nulls":47},"Jose Chan"]
["1","03","01","01","01","  ",null,null,null,"L01 System Integration                                      ",{"$nulls":47},"Jose Chan"]
["1","03","01","01","02","  ",null,null,null,"BC1 System Integration                                      ",{"$nulls":47},"Jose Chan"]
["1","03","01","01","03","  ",null,null,null,"L02 System Integration                                      ",{"$nulls":47},"Jose Chan"]
["1","03","01","01","04","  ",null,null,null,"BC2 System Integration                                      ",{"$nulls":47},"Jose Chan"]
["1","03","01","01","05","  ",null,null,null,"L03 System Integration                                      ",{"$nulls":47},"Jose Chan"]
["1","03","01","01","06","  ",null,null,null,"LTU System Integration                                      ",{"$nulls":47},"Jose Chan"]
["1","03","01","01","07","  ",null,null,null,"E-Dump System Integration                                   ",{"$nulls":47},"Jose Chan"]
["1","03","01","03","  ","  ",null,null,null,"Travel                                                      ",{"$nulls":47},"Jose Chan"]
["1","03","01","04","  ","  ",null,null,null,"Linac Management                                            ",{"$nulls":47},"Jose Chan"]
["1","03","02","  ","  ","  ",null,null,null,"Linac Controls & Power Conversion Subsystem                 ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","01","  ","  ",null,null,null,"Personnel Protection System (PPS)                           ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","02","  ","  ",null,null,null,"Beam Containment System (BCS)                               ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","03","  ","  ",null,null,null,"Machine Protection System (MPS)                             ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","  ","  ",null,null,null,"Linac Power Conversion Subsystem                            ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","01","  ",null,null,null,"Beamline Power Supplies - (Dipole Type)                     ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","01","01",null,null,null,"Power Supply BX11-14                                        ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","01","02",null,null,null,"Power Supply BX21-24                                        ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","01","03",null,null,null,"Kicker Power Supply BXKIK                                   ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","01","04",null,null,null,"Power Supply BX31,32,35,36                                  ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","01","05",null,null,null,"Power Supply -BY1-2                                         ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","01","06",null,null,null,"Kicker Power Supply BYKIK                                   ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","01","07",null,null,null,"Power Supply BYW1-3                                         ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","01","08",null,null,null,"Muon Spoiler Power Supply MUSPLR                            ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","01","09",null,null,null,"Powe Supply BYD1-3                                          ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","  ",null,null,null,"Beamline Power Supplies - (Quad Type)                       ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","06",null,null,null,"Q21201-Q21901 Switch Over                                   ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","07",null,null,null,"Q24201-Q24501 Split                                         ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","08",null,null,null,"Power Supply Q24601                                         ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","09",null,null,null,"Power Supply  Q24701A,Q24701B                               ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","10",null,null,null,"Power Supply QM21                                           ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","11",null,null,null,"Power Supply Q24901A,Q24901B                                ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","12",null,null,null,"Power Supply QM22                                           ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","13",null,null,null,"Power Supply Q5                                             ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","14",null,null,null,"Power Supply Q6                                             ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","15",null,null,null,"Power Supply QA0                                            ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","16",null,null,null,"Power Supply Q50Q1,Q50Q2,Q50Q3                              ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","17",null,null,null,"Power Supply  QVM1                                          ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","18",null,null,null,"Power Supply  QVM2                                          ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","19",null,null,null,"Power Supply  QVM3                                          ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","20",null,null,null,"Power Supply  QVM4                                          ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","21",null,null,null,"Power Supply  QVB1-3                                        ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","22",null,null,null,"Power Supply  QDL31-34                                      ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","23",null,null,null,"Power Supply  QE31-36                                       ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","24",null,null,null,"Power Supply  QEM1                                          ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","25",null,null,null,"Power Supply  QEM2                                          ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","26",null,null,null,"Power Supply  QEM3                                          ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","27",null,null,null,"Power Supply  QEM4                                          ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","28",null,null,null,"Power Supply QT11,13,21,23,31,33,41,43                      ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","29",null,null,null,"Power Supply QT12,22,32,42                                  ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","30",null,null,null,"Power Supply  QUM1                                          ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","31",null,null,null,"Power Supply  QUM2                                          ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","32",null,null,null,"Power Supply  QUM3                                          ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","33",null,null,null,"Power Supply QUM4                                           ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","34",null,null,null,"Power Supply QDMP1-2                                        ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","35",null,null,null,"Power Supply QUE1                                           ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","36",null,null,null,"Power Supply QUE2                                           ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","37",null,null,null,"Rack Accessories - LI21                                     ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","38",null,null,null,"Rack Accessories - LI24                                     ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","39",null,null,null,"Rack Accessories - LI25                                     ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","40",null,null,null,"Rack Accessories - BSY                                      ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","02","41",null,null,null,"Rack Accessories - Dump                                     ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","  ",null,null,null,"Beamline Power Supplies - (Trim Type)                       ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","01",null,null,null,"MCOR_1                                                      ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","02",null,null,null,"MCOR_2                                                      ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","03",null,null,null,"MCOR_3                                                      ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","04",null,null,null,"MCOR_4                                                      ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","05",null,null,null,"MCOR_5                                                      ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","06",null,null,null,"MCOR_6                                                      ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","07",null,null,null,"MCOR_BSY1                                                   ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","08",null,null,null,"MCOR_LTU1                                                   ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","09",null,null,null,"MCOR_LTU2                                                   ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","10",null,null,null,"MCOR_LTU3                                                   ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","11",null,null,null,"MCOR_LTU4                                                   ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","12",null,null,null,"MCOR_LTU5                                                   ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","13",null,null,null,"MCOR_LTU6                                                   ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","14",null,null,null,"MCOR_LTU7                                                   ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","15",null,null,null,"MCOR_LTU8                                                   ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","16",null,null,null,"MCOR_LTU9                                                   ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","17",null,null,null,"MCOR_DUMP1                                                  ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","18",null,null,null,"MCOR Bulk PS - LI21_1                                       ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","19",null,null,null,"MCOR Bulk PS - LI21_2                                       ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","20",null,null,null,"MCOR Bulk PS - LI24                                         ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","21",null,null,null,"MCOR Bulk PS - LI25                                         ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","22",null,null,null,"MCOR Bulk PS - BSY                                          ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","23",null,null,null,"MCOR Bulk PS - LTU_1                                        ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","24",null,null,null,"MCOR Bulk PS - LTU_2                                        ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","25",null,null,null,"MCOR Bulk PS - LTU_3                                        ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","26",null,null,null,"MCOR Bulk PS - LTU_4                                        ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","27",null,null,null,"MCOR PLC - LI21                                             ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","28",null,null,null,"MCOR PLC - LI24                                             ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","29",null,null,null,"MCOR PLC - LI25                                             ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","30",null,null,null,"MCOR PLC - BSY                                              ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","31",null,null,null,"MCOR PLC - LTU_1 (BLD 2.1)                                  ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","32",null,null,null,"MCOR PLC - LTU_2 (BLD 2.2)                                  ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","33",null,null,null,"MCOR PLC - LTU_3 (BLD 2.3)                                  ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","34",null,null,null,"MCOR PLC - Dump                                             ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","35",null,null,null,"MCOR Bulk Dump                                              ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","36",null,null,null,"Rack Accessories - LTU_1 (bld 2.1)                          ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","37",null,null,null,"Rack Accessories - LTU_2 (bld 2.2)                          ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","03","38",null,null,null,"Rack Accessories - LTU_3 (bld 2.3)                          ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","04","04","  ",null,null,null,"Controls & Power Supply                                     ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","05","  ","  ",null,null,null,"Controls - LLRF                                             ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","05","01","  ",null,null,null,"Solid State Sub-booster 5X                                  ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","05","03","  ",null,null,null,"L2/L3 RF Distribution                                       ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","05","04","  ",null,null,null,"Beam Phase Measurement 2x                                   ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","05","05","  ",null,null,null,"Sector 24 Rack Electrical Crate / IOC / EVG                 ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","05","06","  ",null,null,null,"Sector 24 T-Cav                                             ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","05","07","  ",null,null,null,"Sector 29/30 Controls (PACs & PADs)                         ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","05","10","  ",null,null,null,"RF Stability / Feedback                                     ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","05","11","  ",null,null,null,"System Documentation                                        ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","06","  ","  ",null,null,null,"Controls - E-Beam Diagnostic                                ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","06","01","  ",null,null,null,"Controls - Wire Scanners                                    ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","06","02","  ",null,null,null,"Controls - BPMs                                             ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","06","03","  ",null,null,null,"Controls - Toroids                                          ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","06","04","  ",null,null,null,"Controls - Stoppers                                         ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","06","05","  ",null,null,null,"Controls - Profile Monitors                                 ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","06","06","  ",null,null,null,"Controls - E/O Diagnostics                                  ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","06","07","  ",null,null,null,"Controls - Bunch Length Monitors                            ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","06","08","  ",null,null,null,"Controls - Beam Loss Monitors                               ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","06","09","  ",null,null,null,"Controls - Single Beam Dump                                 ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","06","10","  ",null,null,null,"Controls - E Beam Dump                                      ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","06","11","  ",null,null,null,"Controls - Protection Collimator                            ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","06","12","  ",null,null,null,"Controls - Movable Collimator                               ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","06","13","  ",null,null,null,"Controls - X-Band Accel Structure                           ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","08","  ","  ",null,null,null,"Controls - Timing                                           ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","09","  ","  ",null,null,null,"Controls - Vacuum                                           ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","09","01","  ",null,null,null,"Controls - Vacuum Instrumentation & Interlocks              ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","09","02","  ",null,null,null,"Controls - Vacuum Pump Power Supplies                       ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","10","  ","  ",null,null,null,"Software & Controls Infrastructure                          ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","10","04","  ",null,null,null,"Data Communications                                         ",{"$nulls":47},"Hamid Shoaee"]
["1","03","02","10","05","  ",null,null,null,"Computers                                                   ",{"$nulls":47},"Hamid Shoaee"]
["1","03","03","  ","  ","  ",null,null,null,"Linac Magnets & Supports                                    ",{"$nulls":47},"Jose Chan"]
["1","03","03","01","  ","  ",null,null,null,"Bend Magnet (BX1_BC1)                                       ",{"$nulls":47},"Jose Chan"]
["1","03","03","02","  ","  ",null,null,null,"Bend Magnet (BX3_LTU)                                       ",{"$nulls":47},"Jose Chan"]
["1","03","03","03","  ","  ",null,null,null,"Bend Magnet (BX2_BC2)                                       ",{"$nulls":47},"Jose Chan"]
["1","03","03","04","  ","  ",null,null,null,"Bend Magnet (BY_LTU)                                        ",{"$nulls":47},"Jose Chan"]
["1","03","03","05","  ","  ",null,null,null,"Quad Magnet (Quad_LTU)                                      ",{"$nulls":47},"Jose Chan"]
["1","03","03","07","  ","  ",null,null,null,"Quad Magnet (QE_BC1/BC2)                                    ",{"$nulls":47},"Jose Chan"]
["1","03","03","08","  ","  ",null,null,null,"Corrector Magnet (Type 4_LTU/E-Dump)                        ",{"$nulls":47},"Jose Chan"]
["1","03","03","09","  ","  ",null,null,null,"Bend Magnet (BYD_E-Dump)                                    ",{"$nulls":47},"Jose Chan"]
["1","03","03","10","  ","  ",null,null,null,"Quad Magnet (E-Dump)                                        ",{"$nulls":47},"Jose Chan"]
["1","03","03","11","  ","  ",null,null,null,"Bend Magnet (BYPM_LTU)                                      ",{"$nulls":47},"Jose Chan"]
["1","03","03","12","  ","  ",null,null,null,"Bend Magnet (BYKIK_LTU)                                     ",{"$nulls":47},"Jose Chan"]
["1","03","03","13","  ","  ",null,null,null,"Bend Magnet (BYW_LTU)                                       ",{"$nulls":47},"Jose Chan"]
["1","03","03","14","  ","  ",null,null,null,"BXKIK LINAC TCAV Screen Kicker                              ",{"$nulls":47},"Jose Chan"]
["1","03","03","15","  ","  ",null,null,null,"Muon Toroid (E-Dump)                                        ",{"$nulls":47},"Jose Chan"]
["1","03","04","  ","  ","  ",null,null,null,"Linac Vacuum Subsystem                                      ",{"$nulls":47},"Jose Chan"]
["1","03","04","02","  ","  ",null,null,null,"Linac Beamline Vacuum System                                ",{"$nulls":47},"Jose Chan"]
["1","03","04","03","  ","  ",null,null,null,"BC1 Vacuum System                                           ",{"$nulls":47},"Jose Chan"]
["1","03","04","04","  ","  ",null,null,null,"BC2 Vacuum System                                           ",{"$nulls":47},"Jose Chan"]
["1","03","04","05","  ","  ",null,null,null,"Linac to Undulator (LTU) Vacuum System                      ",{"$nulls":47},"Jose Chan"]
["1","03","04","06","  ","  ",null,null,null,"Dumpline Vacuum System                                      ",{"$nulls":47},"Jose Chan"]
["1","03","04","07","  ","  ",null,null,null,"Vacuum System Undulator Interface                           ",{"$nulls":47},"Jose Chan"]
["1","03","04","07","01","  ",null,null,null,"Entrance Section Assembly                                   ",{"$nulls":47},"Jose Chan"]
["1","03","04","07","02","  ",null,null,null,"Exit Section Assembly                                       ",{"$nulls":47},"Jose Chan"]
["1","03","04","08","  ","  ",null,null,null,"LTU/BSY& Cold Trap Vacuum System                            ",{"$nulls":47},"Jose Chan"]
["1","03","05","  ","  ","  ",null,null,null,"Linac Electron Diagnostics Summary                          ",{"$nulls":47},"Jose Chan"]
["1","03","05","01","  ","  ",null,null,null,"Wire Scanners (11) Summary                                  ",{"$nulls":47},"Jose Chan"]
["1","03","05","02","  ","  ",null,null,null,"Beam Position Monitors                                      ",{"$nulls":47},"Jose Chan"]
["1","03","05","02","01","  ",null,null,null,"BPM - Standard  Linac (4) Summary                           ",{"$nulls":47},"Jose Chan"]
["1","03","05","02","02","  ",null,null,null,"BPM - RF (10) Summary                                       ",{"$nulls":47},"Jose Chan"]
["1","03","05","02","03","  ",null,null,null,"BPM - FFTB (12) Summary                                     ",{"$nulls":47},"Jose Chan"]
["1","03","05","02","04","  ",null,null,null,"BPM - Large Aperture (2) Summary                            ",{"$nulls":47},"Jose Chan"]
["1","03","05","03","  ","  ",null,null,null,"Toroid Beam Current Monitor (10) Summary                    ",{"$nulls":47},"Jose Chan"]
["1","03","05","04","  ","  ",null,null,null,"Beam Stoppers (4) Summary                                   ",{"$nulls":47},"Jose Chan"]
["1","03","05","05","  ","  ",null,null,null,"Profile Monitors (7 OTR-3 PHOSPHOR SCREEN-1 YAG)            ",{"$nulls":47},"Jose Chan"]
["1","03","05","06","  ","  ",null,null,null,"E/O Bunch Length Monitors (1) Summary                       ",{"$nulls":47},"Jose Chan"]
["1","03","05","07","  ","  ",null,null,null,"CSR/OTR/CTR Bunch Length Monitors (5) Summary               ",{"$nulls":47},"Jose Chan"]
["1","03","05","08","  ","  ",null,null,null,"Beam Loss Monitors                                          ",{"$nulls":47},"Jose Chan"]
["1","03","05","08","01","  ",null,null,null,"PIC Beam Loss Monitors (10) Summary                         ",{"$nulls":47},"Jose Chan"]
["1","03","05","08","02","  ",null,null,null,"PLIC Beam Loss Monitors (2) Summary                         ",{"$nulls":47},"Jose Chan"]
["1","03","05","09","  ","  ",null,null,null,"Single Beam Dump (1) Summary                                ",{"$nulls":47},"Jose Chan"]
["1","03","05","10","  ","  ",null,null,null,"Electron Beam Dump (1) Summary                              ",{"$nulls":47},"Jose Chan"]
["1","03","05","11","  ","  ",null,null,null,"Protection Collimators (5) Summary                          ",{"$nulls":47},"Jose Chan"]
["1","03","05","12","  ","  ",null,null,null,"Movable Collimators (7x,3y) Summary                         ",{"$nulls":47},"Jose Chan"]
["1","03","05","13","  ","  ",null,null,null,"Safety Electron Dump (1) Summary                            ",{"$nulls":47},"Jose Chan"]
["1","03","05","14","  ","  ",null,null,null,"Charge Monitor (Entrance/Exit Assembly)                     ",{"$nulls":47},"Jose Chan"]
["1","03","06","  ","  ","  ",null,null,null,"Linac RF Subsystem                                          ",{"$nulls":47},"Jose Chan"]
["1","03","06","02","  ","  ",null,null,null,"S-Band High Power System                                    ",{"$nulls":47},"Jose Chan"]
["1","03","06","03","  ","  ",null,null,null,"S-Band Structures                                           ",{"$nulls":47},"Jose Chan"]
["1","03","06","04","  ","  ",null,null,null,"X-Band Low Level System                                     ",{"$nulls":47},"Jose Chan"]
["1","03","06","05","  ","  ",null,null,null,"X-Band High Power System                                    ",{"$nulls":47},"Jose Chan"]
["1","03","06","05","01","  ",null,null,null,"X-Band HP Klystron                                          ",{"$nulls":47},"Jose Chan"]
["1","03","06","05","02","  ",null,null,null,"X-Band HP Modulator                                         ",{"$nulls":47},"Jose Chan"]
["1","03","06","05","03","  ",null,null,null,"X-Band HP Waveguide System                                  ",{"$nulls":47},"Jose Chan"]
["1","03","06","06","  ","  ",null,null,null,"X-Band Structures                                           ",{"$nulls":47},"Jose Chan"]
["1","03","06","07","  ","  ",null,null,null,"RF Distribution System                                      ",{"$nulls":47},"Jose Chan"]
["1","03","06","07","01","  ",null,null,null,"Modulator Refurbishment                                     ",{"$nulls":47},"Jose Chan"]
["1","03","06","07","02","  ",null,null,null,"Solid State Sub Booster                                     ",{"$nulls":47},"Jose Chan"]
["1","03","06","07","03","  ",null,null,null,"IPA Modifications                                           ",{"$nulls":47},"Jose Chan"]
["1","03","06","07","04","  ",null,null,null,"Klystron Controls Interfaces                                ",{"$nulls":47},"Jose Chan"]
["1","03","06","07","05","  ",null,null,null,"Bunch Length Electronics                                    ",{"$nulls":47},"Jose Chan"]
["1","03","06","07","06","  ",null,null,null,"RF Phase Measurements                                       ",{"$nulls":47},"Jose Chan"]
["1","03","06","07","07","  ",null,null,null,"RF Distribution L2 & L3                                     ",{"$nulls":47},"Jose Chan"]
["1","03","06","07","08","  ",null,null,null,"RF Fiber Optics Electronics System                          ",{"$nulls":47},"Jose Chan"]
["1","03","06","07","09","  ",null,null,null,"RF Stability                                                ",{"$nulls":47},"Jose Chan"]
["1","03","07","  ","  ","  ",null,null,null,"Linac Installation & Alignment                              ",{"$nulls":47},"Jose Chan"]
["1","03","07","01","  ","  ",null,null,null,"Linac L01 System Installation & Alignment                   ",{"$nulls":47},"Jose Chan"]
["1","03","07","02","  ","  ",null,null,null,"Linac BC1 System Installation & Alignment                   ",{"$nulls":47},"Jose Chan"]
["1","03","07","03","  ","  ",null,null,null,"Linac L02 System Installation & Alignment                   ",{"$nulls":47},"Jose Chan"]
["1","03","07","04","  ","  ",null,null,null,"Linac BC2 System Installation & Alignment                   ",{"$nulls":47},"Jose Chan"]
["1","03","07","05","  ","  ",null,null,null,"Linac L03 System Installation & Alignment                   ",{"$nulls":47},"Jose Chan"]
["1","03","07","06","  ","  ",null,null,null,"Linac LTU System Installation & Alignment                   ",{"$nulls":47},"Jose Chan"]
["1","03","07","07","  ","  ",null,null,null,"Linac E-Dump System Installation & Alignment                ",{"$nulls":47},"Jose Chan"]
["1","03","07","10","  ","  ",null,null,null,"LINAC  Installation 2006 Shut Down                          ",{"$nulls":47},"Jose Chan"]
["1","03","07","10","01","  ",null,null,null,"Beamline Equip Removal L01 thru BC1 Out                     ",{"$nulls":47},"Jose Chan"]
["1","03","07","10","02","  ",null,null,null,"Gallery Waveguide Installation                              ",{"$nulls":47},"Jose Chan"]
["1","03","07","10","03","  ",null,null,null,"Beamline Equip Installation L01 thru BC1 Out                ",{"$nulls":47},"Jose Chan"]
["1","03","07","10","04","  ",null,null,null,"2006 Linac Controls Install and Checkout Gallery to Linac B ",{"$nulls":47},"Jose Chan"]
["1","03","07","10","05","  ",null,null,null,"2006 Linac Controls Install and Checkout L01 to BC1         ",{"$nulls":47},"Jose Chan"]
["1","03","07","20","  ","  ",null,null,null,"LINAC Installation 2007 Shut Down                           ",{"$nulls":47},"Jose Chan"]
["1","03","07","20","01","  ",null,null,null,"Beamline Equip Removal L02, L03 and BC2                     ",{"$nulls":47},"Jose Chan"]
["1","03","07","20","02","  ",null,null,null,"Beamline Equip Installation L02, L03 and BC2                ",{"$nulls":47},"Jose Chan"]
["1","03","07","20","03","  ",null,null,null,"2007 Linac Controlls Install and Checkout                   ",{"$nulls":47},"Jose Chan"]
["1","03","07","20","04","  ",null,null,null,"Linac Undulator Interface                                   ",{"$nulls":47},"Jose Chan"]
["1","04","  ","  ","  ","  ",null,null,null,"UNDULATOR SYSTEM                                            "]
["1","04","01","  ","  ","  ",null,null,null,"Undulator System Management & Integration                   ",{"$nulls":47},"Geoff Pile"]
["1","04","01","01","  ","  ",null,null,null,"Undulator System Management                                 ",{"$nulls":47},"Geoff Pile"]
["1","04","01","01","01","  ",null,null,null,"Undulator System Management - Technical                     ",{"$nulls":47},"Geoff Pile"]
["1","04","01","01","02","  ",null,null,null,"ANL Project Support                                         ",{"$nulls":47},"Geoff Pile"]
["1","04","01","02","  ","  ",null,null,null,"Undulator System Materials & Supplies                       ",{"$nulls":47},"Geoff Pile"]
["1","04","01","02","01","  ",null,null,null,"Undulator System M&S - General                              ",{"$nulls":47},"Geoff Pile"]
["1","04","01","02","02","  ",null,null,null,"Undulator System Travel                                     ",{"$nulls":47},"Geoff Pile"]
["1","04","01","03","  ","  ",null,null,null,"Undulator System Reviews and Workshops                      ",{"$nulls":47},"Geoff Pile"]
["1","04","02","  ","  ","  ",null,null,null,"Controls                                                    ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","01","  ","  ",null,null,null,"Controls Management and Integration                         ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","01","03","  ",null,null,null,"Software Interface with SLAC                                ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","01","04","  ",null,null,null,"Undulator Cable, Tray, and Rack Layout                      ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","01","05","  ",null,null,null,"Miscellaneous Controls                                      ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","02","  ","  ",null,null,null,"Motion                                                      ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","02","01","  ",null,null,null,"Undulator Cam Movers                                        ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","02","01","01",null,null,null,"Motor Interface                                             ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","02","01","02",null,null,null,"Encoder Interface                                           ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","02","01","03",null,null,null,"Motor Driver                                                ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","02","01","04",null,null,null,"Cabling                                                     ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","02","01","05",null,null,null,"Integrate components                                        ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","02","02","  ",null,null,null,"Motion Test Stand                                           ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","02","06","  ",null,null,null,"Scanning Wire Motion                                        ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","02","06","01",null,null,null,"Motor Interface                                             ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","02","06","02",null,null,null,"Encoder Interface                                           ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","02","06","03",null,null,null,"Motor Driver                                                ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","02","06","04",null,null,null,"Cabling                                                     ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","02","06","05",null,null,null,"Integrate components                                        ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","02","07","  ",null,null,null,"Translation Stage Motion                                    ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","02","07","01",null,null,null,"Motor Interface                                             ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","02","07","03",null,null,null,"Motor Driver                                                ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","02","07","04",null,null,null,"Cabling                                                     ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","02","07","05",null,null,null,"Integrate components                                        ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","03","  ","  ",null,null,null,"Signal Analysis                                             ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","03","01","  ",null,null,null,"RFBPM                                                       ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","03","01","02",null,null,null,"Signal Acquisition                                          ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","03","01","03",null,null,null,"Timing interface                                            ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","03","01","04",null,null,null,"Cabling                                                     ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","03","01","05",null,null,null,"Integrate components                                        ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","03","02","  ",null,null,null,"Charge Monitor                                              ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","03","02","03",null,null,null,"Integrate components                                        ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","03","03","  ",null,null,null,"Beam Finder Wire                                            ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","03","03","01",null,null,null,"BFW Actuator Control                                        ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","03","03","06",null,null,null,"Integrate components                                        ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","04","  ","  ",null,null,null,"Video                                                       ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","04","01","  ",null,null,null,"OTR Monitor                                                 ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","04","01","01",null,null,null,"Camera                                                      ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","04","01","02",null,null,null,"Camera trigger interface                                    ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","04","01","03",null,null,null,"Digitizer                                                   ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","04","01","04",null,null,null,"Timing interface                                            ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","04","01","05",null,null,null,"Cabling                                                     ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","04","01","06",null,null,null,"Integrate components                                        ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","04","03","  ",null,null,null,"Observation station video                                   ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","04","03","01",null,null,null,"Camera                                                      ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","04","03","02",null,null,null,"Camera trigger interface                                    ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","04","03","03",null,null,null,"Multiplexor                                                 ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","04","03","04",null,null,null,"Cabling                                                     ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","04","03","05",null,null,null,"Integrate components                                        ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","04","03","06",null,null,null,"Imaging Test Stand                                          ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","05","  ","  ",null,null,null,"Data Acquisition and Control                                ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","05","01","  ",null,null,null,"Strongback Temperature monitoring                           ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","05","01","01",null,null,null,"Integrate components                                        ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","06","  ","  ",null,null,null,"Vacuum                                                      ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","06","01","  ",null,null,null,"Ion Pump Controller                                         ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","06","01","01",null,null,null,"Integrate components                                        ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","06","02","  ",null,null,null,"RGA                                                         ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","06","02","01",null,null,null," Integrate components                                       ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","07","  ","  ",null,null,null,"Machine Protection                                          ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","07","01","  ",null,null,null,"Undulator Beam Loss Monitor Controls                        ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","07","01","01",null,null,null,"Hardware design                                             ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","07","01","02",null,null,null,"Interface components                                        ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","07","02","  ",null,null,null,"Cerenkov Detector                                           ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","07","02","01",null,null,null,"Signal interface                                            ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","07","03","  ",null,null,null,"Gamma Ray Detector                                          ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","07","03","01",null,null,null,"Signal interface                                            ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","08","  ","  ",null,null,null,"Power Supply Controls                                       ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","08","01","  ",null,null,null,"Software                                                    ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","08","02","  ",null,null,null,"Beam Line Power Supplies (Trim Type)                        ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","08","02","01",null,null,null,"CPUs and Crates                                             ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","08","02","02",null,null,null,"Bulk Power Supplies                                         ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","08","02","03",null,null,null,"PLC Power Supply Protection                                 ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","08","02","04",null,null,null,"MCOR                                                        ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","08","03","  ",null,null,null,"Rack Assembly                                               ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","08","04","  ",null,null,null,"System Checkout                                             ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","10","  ","  ",null,null,null,"Undualtor Controls Module                                   ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","10","01","  ",null,null,null,"UCM Hardware Design                                         ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","10","02","  ",null,null,null,"UCM EPICS Development                                       ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","10","03","  ",null,null,null,"Procure UCMI Prototype                                      ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","10","04","  ",null,null,null,"UCMI Proto H/W Assembly                                     ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","10","05","  ",null,null,null,"UCMI Prototype Testing                                      ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","10","06","  ",null,null,null,"UCMI Blade IOC First Article                                ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","10","07","  ",null,null,null,"Procure UCMI First Article                                  ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","10","08","  ",null,null,null,"UCM First Article Testing and QA                            ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","10","09","  ",null,null,null,"Procure Production UCMI                                     ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","10","10","  ",null,null,null,"Procure Production Blade IOC                                ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","10","11","  ",null,null,null,"Procure Production Motors                                   ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","10","12","  ",null,null,null,"Procure Production Potentiometers                           ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","10","13","  ",null,null,null,"Procure Production RTD                                      ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","12","  ","  ",null,null,null,"Rack and Cables                                             ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","12","01","  ",null,null,null,"Undulator Racks                                             ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","12","02","  ",null,null,null,"Intra-Undulator Cabling                                     ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","12","03","  ",null,null,null,"Electronics Interface Assembly                              ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","12","04","  ",null,null,null,"Undulator Cableplant                                        ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","13","  ","  ",null,null,null,"BPM                                                         ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","13","01","  ",null,null,null,"APS Testing                                                 ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","14","  ","  ",null,null,null,"Long Term Test Prep                                         ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","17","  ","  ",null,null,null,"Undulator Controls Management                               ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","20","  ","  ",null,null,null,"Undulator Controls - MPS                                    ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","20","02","  ",null,null,null,"Undulator MPS - IMUX                                        ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","20","03","  ",null,null,null,"Undulator MPS - TIU                                         ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","20","04","  ",null,null,null,"Undulator MPS - PLIC                                        ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","20","05","  ",null,null,null,"Undulator Controls  MPS -Toroids                            ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","20","06","  ",null,null,null,"Undulator Controls MPS - Fault Devices                      ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","21","  ","  ",null,null,null,"Undulator Controls - Timing                                 ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","22","  ","  ",null,null,null,"Undulator Controls - BPM                                    ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","23","  ","  ",null,null,null,"Undulator Controls - Vacuum                                 ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","24","  ","  ",null,null,null,"Undulator Controls - ADS System                             ",{"$nulls":47},"Hamid Shoaee"]
["1","04","03","  ","  ","  ",null,null,null,"Undulator Magnet & Support                                  ",{"$nulls":47},"Geoff Pile"]
["1","04","03","01","  ","  ",null,null,null,"UND Magnet & Support - Mgmt and Integration                 ",{"$nulls":47},"Geoff Pile"]
["1","04","03","02","  ","  ",null,null,null,"First Prototype Undulator & Mfg Plan                        ",{"$nulls":47},"Geoff Pile"]
["1","04","03","03","  ","  ",null,null,null,"1st Article Undulators & Long Lead Procurements             ",{"$nulls":47},"Geoff Pile"]
["1","04","03","03","01","  ",null,null,null,"Ti Strongback (LLP)                                         ",{"$nulls":47},"Geoff Pile"]
["1","04","03","03","02","  ",null,null,null,"Magnet Blocks (LLP)                                         ",{"$nulls":47},"Geoff Pile"]
["1","04","03","03","03","  ",null,null,null,"Magnet Poles (LLP)                                          ",{"$nulls":47},"Geoff Pile"]
["1","04","03","03","04","  ",null,null,null,"Magnet Assembly & Supports - 1st Articles                   ",{"$nulls":47},"Geoff Pile"]
["1","04","03","03","04","01",null,null,null,"Magnet Assembly 1st Article - Vendor A                      ",{"$nulls":47},"Geoff Pile"]
["1","04","03","03","04","02",null,null,null,"Magnet Assembly 1st Article - Vendor B                      ",{"$nulls":47},"Geoff Pile"]
["1","04","03","03","04","03",null,null,null,"Support/Mover System - Articles 1 & 2                       ",{"$nulls":47},"Geoff Pile"]
["1","04","03","03","05","  ",null,null,null,"Magnetic Measurement (ANL)                                  ",{"$nulls":47},"Geoff Pile"]
["1","04","03","03","05","01",null,null,null,"Magnetic Measurement (ANL) - Vendor A Und #1                ",{"$nulls":47},"Geoff Pile"]
["1","04","03","03","05","02",null,null,null,"Magnetic Measurement (ANL) - Vendor B Und #2                ",{"$nulls":47},"Geoff Pile"]
["1","04","03","03","06","  ",null,null,null,"Integrated Single-Undulator Module Test                     ",{"$nulls":47},"Geoff Pile"]
["1","04","03","03","07","  ",null,null,null," System Test - Two Undulators                               ",{"$nulls":47},"Geoff Pile"]
["1","04","03","04","  ","  ",null,null,null,"Production Undulator Magnet Assembly & Supports             ",{"$nulls":47},"Geoff Pile"]
["1","04","03","04","01","  ",null,null,null,"Production Undulator Assembly - Vendor A                    ",{"$nulls":47},"Geoff Pile"]
["1","04","03","04","02","  ",null,null,null,"Production Undulator Assembly - Vendor B                    ",{"$nulls":47},"Geoff Pile"]
["1","04","03","04","03","  ",null,null,null,"Production Support/Mover Fabrication/Assembly               ",{"$nulls":47},"Geoff Pile"]
["1","04","03","04","04","  ",null,null,null,"Mu Metal Shield                                             ",{"$nulls":47},"Geoff Pile"]
["1","04","03","05","  ","  ",null,null,null,"Quadrupole Focusing Magnets                                 ",{"$nulls":47},"Geoff Pile"]
["1","04","03","05","01","  ",null,null,null,"Quadrupole Magnets                                          ",{"$nulls":47},"Geoff Pile"]
["1","04","03","05","02","  ",null,null,null,"Quadrupole Power Supplies                                   ",{"$nulls":47},"Geoff Pile"]
["1","04","03","05","03","  ",null,null,null,"Quadrupole Stages & Stands                                  ",{"$nulls":47},"Geoff Pile"]
["1","04","03","05","04","  ",null,null,null,"Quadrupole Cables                                           ",{"$nulls":47},"Geoff Pile"]
["1","04","03","06","  ","  ",null,null,null,"Undulator Magnetic Measurement Facility (SLAC)              ",{"$nulls":47},"Rod Pope"]
["1","04","03","06","01","  ",null,null,null,"Undulator MMF Setup                                         ",{"$nulls":47},"Rod Pope"]
["1","04","03","06","01","01",null,null,null,"Undulator Test Stand Prototype                              ",{"$nulls":47},"Rod Pope"]
["1","04","03","06","01","04",null,null,null,"Undulator Test Stand                                        ",{"$nulls":47},"Rod Pope"]
["1","04","03","06","01","05",null,null,null,"Undulator Fiducialization                                   ",{"$nulls":47},"Rod Pope"]
["1","04","03","06","01","06",null,null,null,"Quad Strength and Field Quality                             ",{"$nulls":47},"Rod Pope"]
["1","04","03","06","01","07",null,null,null,"Quad Fiducialization System                                 ",{"$nulls":47},"Rod Pope"]
["1","04","03","06","01","08",null,null,null,"Hall Probe Calibration System                               ",{"$nulls":47},"Rod Pope"]
["1","04","03","06","01","09",null,null,null,"Undulator Handling                                          ",{"$nulls":47},"Rod Pope"]
["1","04","03","06","02","  ",null,null,null,"Fiducialization and Magnetic Measurements (F/MM)            ",{"$nulls":47},"Rod Pope"]
["1","04","03","06","02","01",null,null,null,"F/MM Undulator Magnet Sections                              ",{"$nulls":47},"Rod Pope"]
["1","04","03","06","02","02",null,null,null,"F/MM Quadrupoles                                            ",{"$nulls":47},"Rod Pope"]
["1","04","03","06","02","03",null,null,null,"F/MM BPMs                                                   ",{"$nulls":47},"Rod Pope"]
["1","04","03","06","02","04",null,null,null,"F/MM Correctors                                             ",{"$nulls":47},"Rod Pope"]
["1","04","03","06","02","05",null,null,null,"F/MM Vacuum Chamber                                         ",{"$nulls":47},"Rod Pope"]
["1","04","03","06","02","06",null,null,null,"F/MM Photon Diagnostics Components                          ",{"$nulls":47},"Rod Pope"]
["1","04","03","06","03","  ",null,null,null,"Undulator Monitoring                                        ",{"$nulls":47},"Rod Pope"]
["1","04","03","06","03","01",null,null,null,"Stretched Wire System                                       ",{"$nulls":47},"Rod Pope"]
["1","04","03","06","03","02",null,null,null,"Hydrostatic Level System                                    ",{"$nulls":47},"Rod Pope"]
["1","04","03","06","03","03",null,null,null,"F/MM BPMs                                                   ",{"$nulls":47},"Rod Pope"]
["1","04","03","08","  ","  ",null,null,null,"Fixed Supports                                              ",{"$nulls":47},"Geoff Pile"]
["1","04","03","08","01","  ",null,null,null,"Fixed Sppt Mgmt & Integration                               ",{"$nulls":47},"Geoff Pile"]
["1","04","03","08","02","  ",null,null,null,"Fixed Support Design                                        ",{"$nulls":47},"Geoff Pile"]
["1","04","03","08","03","  ",null,null,null,"Stabilized Girder Assemblies                                ",{"$nulls":47},"Geoff Pile"]
["1","04","03","08","04","  ",null,null,null,"Thermal Intercept System                                    ",{"$nulls":47},"Geoff Pile"]
["1","04","03","08","05","  ",null,null,null,"Thermometry                                                 ",{"$nulls":47},"Geoff Pile"]
["1","04","03","08","06","  ",null,null,null,"Kinematic Girder Support                                    ",{"$nulls":47},"Geoff Pile"]
["1","04","03","08","07","  ",null,null,null,"Earthquake Bracing                                          ",{"$nulls":47},"Geoff Pile"]
["1","04","03","08","08","  ",null,null,null,"Controls and Software                                       ",{"$nulls":47},"Geoff Pile"]
["1","04","04","  ","  ","  ",null,null,null,"Vacuum System                                               ",{"$nulls":47},"Geoff Pile"]
["1","04","04","02","  ","  ",null,null,null,"Undulator Vacuum Chamber Assembly                           ",{"$nulls":47},"Geoff Pile"]
["1","04","04","02","01","  ",null,null,null,"Prototype Chamber Weldment                                  ",{"$nulls":47},"Geoff Pile"]
["1","04","04","02","02","  ",null,null,null,"Production Chamber Weldment                                 ",{"$nulls":47},"Geoff Pile"]
["1","04","04","02","03","  ",null,null,null,"Prototype Aluminum Chamber                                  ",{"$nulls":47},"Geoff Pile"]
["1","04","04","03","  ","  ",null,null,null,"Beam-line Bellows Module Assembly                           ",{"$nulls":47},"Geoff Pile"]
["1","04","04","03","01","  ",null,null,null,"Prototype Bellows Module                                    ",{"$nulls":47},"Geoff Pile"]
["1","04","04","03","02","  ",null,null,null,"Production Bellows Module                                   ",{"$nulls":47},"Geoff Pile"]
["1","04","04","04","  ","  ",null,null,null,"Single Undulator Test (SUT) Vacuum                          ",{"$nulls":47},"Geoff Pile"]
["1","04","04","05","  ","  ",null,null,null,"Short Diagnostic Break (SDB) Assembly                       ",{"$nulls":47},"Geoff Pile"]
["1","04","04","06","  ","  ",null,null,null,"Long Diagnostic Break (LDB) Assembly                        ",{"$nulls":47},"Geoff Pile"]
["1","04","04","07","  ","  ",null,null,null,"Entrance Section Assembly                                   ",{"$nulls":47},"Geoff Pile"]
["1","04","04","08","  ","  ",null,null,null,"Exit Section Assembly                                       ",{"$nulls":47},"Geoff Pile"]
["1","04","04","09","  ","  ",null,null,null,"Baking System                                               ",{"$nulls":47},"Geoff Pile"]
["1","04","05","  ","  ","  ",null,null,null,"Diagnostics                                                 ",{"$nulls":47},"Geoff Pile"]
["1","04","05","02","  ","  ",null,null,null,"Undulator Line Diagnostics (ULD)                            ",{"$nulls":47},"Geoff Pile"]
["1","04","05","02","01","  ",null,null,null,"ULD Test Station                                            ",{"$nulls":47},"Geoff Pile"]
["1","04","05","02","02","  ",null,null,null,"ULD Vacuum Chamber                                          ",{"$nulls":47},"Geoff Pile"]
["1","04","05","02","03","  ",null,null,null,"Positioning Mechanism                                       ",{"$nulls":47},"Geoff Pile"]
["1","04","05","02","04","  ",null,null,null,"Scanning wire assembly (ULD-SWA)                            ",{"$nulls":47},"Geoff Pile"]
["1","04","05","02","05","  ",null,null,null,"Optical transition radiation imaging assembly               ",{"$nulls":47},"Geoff Pile"]
["1","04","05","02","09","  ",null,null,null,"ULD Design & Integration                                    ",{"$nulls":47},"Geoff Pile"]
["1","04","05","04","  ","  ",null,null,null,"End-of-Undulator(EOU) X-ray and Profile diagnost            ",{"$nulls":47},"Geoff Pile"]
["1","04","05","04","01","  ",null,null,null,"Prototype Construction and Testing                          ",{"$nulls":47},"Geoff Pile"]
["1","04","05","04","02","  ",null,null,null,"Bunch Length Monitor-Streak Camera (BLM)                    ",{"$nulls":47},"Geoff Pile"]
["1","04","05","04","03","  ",null,null,null,"Upstream corrector / separator                              ",{"$nulls":47},"Geoff Pile"]
["1","04","05","04","04","  ",null,null,null,"Optical Diffraction radiation imaging assembly (            ",{"$nulls":47},"Geoff Pile"]
["1","04","05","04","05","  ",null,null,null,"X-ray High Resolution monochromator assembly (EO            ",{"$nulls":47},"Geoff Pile"]
["1","04","05","04","06","  ",null,null,null,"X-ray Imaging High Resolution detector assembly             ",{"$nulls":47},"Geoff Pile"]
["1","04","05","04","07","  ",null,null,null,"EOU Design and Integration                                  ",{"$nulls":47},"Geoff Pile"]
["1","04","05","05","  ","  ",null,null,null,"RFBPM                                                       ",{"$nulls":47},"Geoff Pile"]
["1","04","05","05","01","  ",null,null,null,"X-Band Cavity BPM Development                               ",{"$nulls":47},"Geoff Pile"]
["1","04","05","05","02","  ",null,null,null,"X-Band Receiver Development                                 ",{"$nulls":47},"Geoff Pile"]
["1","04","05","05","03","  ",null,null,null,"X-Band BPM Production                                       ",{"$nulls":47},"Geoff Pile"]
["1","04","05","06","  ","  ",null,null,null,"Beam Finder Wire                                            ",{"$nulls":47},"Geoff Pile"]
["1","04","05","07","  ","  ",null,null,null,"Charge Monitor (CM)                                         ",{"$nulls":47},"Geoff Pile"]
["1","04","05","08","  ","  ",null,null,null,"Beam Loss Monitoring                                        ",{"$nulls":47},"Geoff Pile"]
["1","04","05","09","  ","  ",null,null,null,"Radiation Detection Monitor (RDM)                           ",{"$nulls":47},"Geoff Pile"]
["1","04","05","10","  ","  ",null,null,null,"SIngle Undulator Test (SUT) Diagnostics                     ",{"$nulls":47},"Geoff Pile"]
["1","04","05","11","  ","  ",null,null,null,"Supplemental Shielding                                      ",{"$nulls":47},"Geoff Pile"]
["1","04","06","  ","  ","  ",null,null,null,"Undulator System Installation and Alignment                 ",{"$nulls":47},"Rod Pope"]
["1","04","06","01","  ","  ",null,null,null,"Undulator System Installation and Alignment Inte            ",{"$nulls":47},"Rod Pope"]
["1","04","06","01","01","  ",null,null,null,"Undulator System                                            ",{"$nulls":47},"Rod Pope"]
["1","04","06","02","  ","  ",null,null,null,"Control System Installation and Alignment                   ",{"$nulls":47},"Rod Pope"]
["1","04","06","04","  ","  ",null,null,null,"Vacuum System Installation and Alignment                    ",{"$nulls":47},"Rod Pope"]
["1","04","06","05","  ","  ",null,null,null,"Diagnostics System Installation and Alignment               ",{"$nulls":47},"Rod Pope"]
["1","04","06","06","  ","  ",null,null,null,"2008 Undulator System Installation and Alignment            ",{"$nulls":47},"Rod Pope"]
["1","05","  ","  ","  ","  ",null,null,null,"X-RAY TRANSPORT & DIAGNOSTICS SYSTEMS                       "]
["1","05","01","  ","  ","  ",null,null,null,"System Management & Integration                             ",{"$nulls":47},"Donn McMahon"]
["1","05","01","01","  ","  ",null,null,null,"Management                                                  ",{"$nulls":47},"Donn McMahon"]
["1","05","01","01","01","  ",null,null,null,"XTOD Management - Technical                                 ",{"$nulls":47},"Donn McMahon"]
["1","05","01","01","02","  ",null,null,null,"LLNL Project Support                                        ",{"$nulls":47},"Donn McMahon"]
["1","05","01","01","03","  ",null,null,null,"Commissioning Coordinator                                   ",{"$nulls":47},"Donn McMahon"]
["1","05","02","  ","  ","  ",null,null,null,"Controls                                                    ",{"$nulls":47},"Gunter Haller"]
["1","05","02","01","  ","  ",null,null,null,"Controls - EPICS                                            ",{"$nulls":47},"Gunter Haller"]
["1","05","02","02","  ","  ",null,null,null,"Motor Controls                                              ",{"$nulls":47},"Gunter Haller"]
["1","05","02","03","  ","  ",null,null,null,"Controls - Vacuum                                           ",{"$nulls":47},"Gunter Haller"]
["1","05","03","  ","  ","  ",null,null,null,"Mechanical & Vacuum Subsystem                               ",{"$nulls":47},"Donn McMahon"]
["1","05","03","01","  ","  ",null,null,null,"Vacuum Systems Engineering                                  ",{"$nulls":47},"Donn McMahon"]
["1","05","03","02","  ","  ",null,null,null,"Mech/Vac Front End                                          ",{"$nulls":47},"Donn McMahon"]
["1","05","03","03","  ","  ",null,null,null,"Mech/Vac Near Hall                                          ",{"$nulls":47},"Donn McMahon"]
["1","05","03","03","01","  ",null,null,null,"Mech/Vac Near Hall                                          ",{"$nulls":47},"Donn McMahon"]
["1","05","03","03","02","  ",null,null,null,"NEH Hutch 2                                                 ",{"$nulls":47},"Donn McMahon"]
["1","05","03","03","03","  ",null,null,null,"NEH Hutch 3                                                 ",{"$nulls":47},"Donn McMahon"]
["1","05","03","04","  ","  ",null,null,null,"Mech/Vac Tunnel                                             ",{"$nulls":47},"Donn McMahon"]
["1","05","03","05","  ","  ",null,null,null,"Mech/Vac Far Hall                                           ",{"$nulls":47},"Donn McMahon"]
["1","05","03","05","01","  ",null,null,null,"FEH Hutch 1                                                 ",{"$nulls":47},"Donn McMahon"]
["1","05","03","05","02","  ",null,null,null,"FEH Hutch 2                                                 ",{"$nulls":47},"Donn McMahon"]
["1","05","03","05","03","  ",null,null,null,"FEH Hutch 3                                                 ",{"$nulls":47},"Donn McMahon"]
["1","05","04","  ","  ","  ",null,null,null,"Optical  Subsystem                                          ",{"$nulls":47},"Donn McMahon"]
["1","05","04","01","  ","  ",null,null,null,"Optical Systems Engineering                                 ",{"$nulls":47},"Donn McMahon"]
["1","05","04","02","  ","  ",null,null,null,"Facility Optics                                             ",{"$nulls":47},"Donn McMahon"]
["1","05","04","02","01","  ",null,null,null,"Fast Valve                                                  ",{"$nulls":47},"Donn McMahon"]
["1","05","04","02","02","  ",null,null,null,"Fixed Mask                                                  ",{"$nulls":47},"Donn McMahon"]
["1","05","04","02","03","  ",null,null,null,"Slit/Collimators                                            ",{"$nulls":47},"Donn McMahon"]
["1","05","04","02","04","  ",null,null,null,"Flipper Mirror                                              ",{"$nulls":47},"Donn McMahon"]
["1","05","04","02","05","  ",null,null,null,"Gas/Solid Attenuator                                        ",{"$nulls":47},"Donn McMahon"]
["1","05","04","02","06","  ",null,null,null,"TTF Damage Experiment                                       ",{"$nulls":47},"Donn McMahon"]
["1","05","04","02","07","  ",null,null,null,"FEL Offset Mirrors                                          ",{"$nulls":47},"Donn McMahon"]
["1","05","04","02","07","01",null,null,null,"Low Energy Mirrors                                          ",{"$nulls":47},"Donn McMahon"]
["1","05","04","02","07","02",null,null,null,"High Energy Mirrors                                         ",{"$nulls":47},"Donn McMahon"]
["1","05","04","02","08","  ",null,null,null,"Solid Attenuator                                            ",{"$nulls":47},"Donn McMahon"]
["1","05","04","02","09","  ",null,null,null,"Low Energy Mirror System                                    ",{"$nulls":47},"Donn McMahon"]
["1","05","04","03","  ","  ",null,null,null,"End Station Optics                                          ",{"$nulls":47},"Donn McMahon"]
["1","05","04","03","01","  ",null,null,null,"End Station Optics Engineering                              ",{"$nulls":47},"Donn McMahon"]
["1","05","04","03","02","  ",null,null,null,"Optics Tank - Near Hall                                     ",{"$nulls":47},"Donn McMahon"]
["1","05","04","03","03","  ",null,null,null,"Optics Tank - Far Hall                                      ",{"$nulls":47},"Donn McMahon"]
["1","05","04","03","04","  ",null,null,null,"K-B Focusing System                                         ",{"$nulls":47},"Donn McMahon"]
["1","05","04","03","05","  ",null,null,null,"Refractive Focusing System                                  ",{"$nulls":47},"Donn McMahon"]
["1","05","04","04","  ","  ",null,null,null,"Crystals & Gratings                                         ",{"$nulls":47},"Donn McMahon"]
["1","05","04","04","01","  ",null,null,null,"Crystals & Gratings Engineering                             ",{"$nulls":47},"Donn McMahon"]
["1","05","04","04","02","  ",null,null,null,"System Monochrometer                                        ",{"$nulls":47},"Donn McMahon"]
["1","05","04","04","03","  ",null,null,null,"Pulse Split & Delay                                         ",{"$nulls":47},"Donn McMahon"]
["1","05","05","  ","  ","  ",null,null,null,"Diagnostics Subsystem                                       ",{"$nulls":47},"Donn McMahon"]
["1","05","05","01","  ","  ",null,null,null,"Diagnostic Systems Engineering                              ",{"$nulls":47},"Donn McMahon"]
["1","05","05","01","01","  ",null,null,null,"Diagnostic Systems Engineering                              ",{"$nulls":47},"Donn McMahon"]
["1","05","05","02","  ","  ",null,null,null,"Modeling & Simulation                                       ",{"$nulls":47},"Donn McMahon"]
["1","05","05","02","01","  ",null,null,null,"Wave Model                                                  ",{"$nulls":47},"Donn McMahon"]
["1","05","05","02","02","  ",null,null,null,"Monte Carlo Model                                           ",{"$nulls":47},"Donn McMahon"]
["1","05","05","02","03","  ",null,null,null,"Beam Simulation                                             ",{"$nulls":47},"Donn McMahon"]
["1","05","05","03","  ","  ",null,null,null,"Facility Diagnostics                                        ",{"$nulls":47},"Donn McMahon"]
["1","05","05","03","01","  ",null,null,null,"Direct Imager                                               ",{"$nulls":47},"Donn McMahon"]
["1","05","05","03","02","  ",null,null,null,"Indirect Imager                                             ",{"$nulls":47},"Donn McMahon"]
["1","05","05","03","03","  ",null,null,null,"Pulsed Ion Chamber                                          ",{"$nulls":47},"Donn McMahon"]
["1","05","05","03","04","  ",null,null,null,"Gas Mixing System                                           ",{"$nulls":47},"Donn McMahon"]
["1","05","05","03","05","  ",null,null,null,"FEE Diagnostic Tank                                         ",{"$nulls":47},"Donn McMahon"]
["1","05","05","03","06","  ",null,null,null,"Gas Detector                                                ",{"$nulls":47},"Donn McMahon"]
["1","05","05","03","07","  ",null,null,null,"NEH Imager                                                  ",{"$nulls":47},"Donn McMahon"]
["1","05","05","03","08","  ",null,null,null,"FEH Imager                                                  ",{"$nulls":47},"Donn McMahon"]
["1","05","05","04","  ","  ",null,null,null,"Commissioning Diagnostics                                   ",{"$nulls":47},"Donn McMahon"]
["1","05","05","04","01","  ",null,null,null,"Commission Diagnostic Tanks                                 ",{"$nulls":47},"Donn McMahon"]
["1","05","05","04","02","  ",null,null,null,"Total Energy Measurement                                    ",{"$nulls":47},"Donn McMahon"]
["1","05","05","04","03","  ",null,null,null,"Pulse Length Measurement                                    ",{"$nulls":47},"Donn McMahon"]
["1","05","05","04","04","  ",null,null,null,"Low Energy Spectral Measurement System                      ",{"$nulls":47},"Donn McMahon"]
["1","05","05","04","05","  ",null,null,null,"Popup Cameras                                               ",{"$nulls":47},"Donn McMahon"]
["1","05","05","04","06","  ",null,null,null,"K Measurement System                                        ",{"$nulls":47},"Donn McMahon"]
["1","05","05","04","07","  ",null,null,null,"Divergence Measurement                                      ",{"$nulls":47},"Donn McMahon"]
["1","05","06","  ","  ","  ",null,null,null,"X-Ray Transport System Installation & Alignment             ",{"$nulls":47},"Donn McMahon"]
["1","05","06","01","  ","  ",null,null,null,"Front End Enclosure Install                                 ",{"$nulls":47},"Donn McMahon"]
["1","05","06","02","  ","  ",null,null,null,"Near Hall Install                                           ",{"$nulls":47},"Donn McMahon"]
["1","05","06","03","  ","  ",null,null,null,"Tunnel Install                                              ",{"$nulls":47},"Donn McMahon"]
["1","05","06","04","  ","  ",null,null,null,"Far Hall Install                                            ",{"$nulls":47},"Donn McMahon"]
["1","05","06","05","  ","  ",null,null,null,"Electron Dump Enclosure Install                             ",{"$nulls":47},"Donn McMahon"]
["1","06","  ","  ","  ","  ",null,null,null,"X-RAY END STATION SYSTEMS                                   "]
["1","06","01","  ","  ","  ",null,null,null,"System Management & Integration                             ",{"$nulls":47},"Stefan Moeller"]
["1","06","01","01","  ","  ",null,null,null,"Management                                                  ",{"$nulls":47},"Stefan Moeller"]
["1","06","01","02","  ","  ",null,null,null,"SSRL Physics                                                ",{"$nulls":47},"Stefan Moeller"]
["1","06","02","  ","  ","  ",null,null,null,"XES Controls                                                ",{"$nulls":47},"Gunter Haller"]
["1","06","02","01","  ","  ",null,null,null,"Controls Management                                         ",{"$nulls":47},"Gunter Haller"]
["1","06","02","02","  ","  ",null,null,null,"Network - Closed (Moved to new WBS Element)                 ",{"$nulls":47},"Gunter Haller"]
["1","06","02","03","  ","  ",null,null,null,"PC Support - Closed (Moved to New WBS Element)              ",{"$nulls":47},"Gunter Haller"]
["1","06","02","04","  ","  ",null,null,null,"Beamline Controls - AP - Closed  (Moved to new WBS Element) ",{"$nulls":47},"Gunter Haller"]
["1","06","02","05","  ","  ",null,null,null,"X-Ray PPS - Closed (Moved to new WBS Element)               ",{"$nulls":47},"Gunter Haller"]
["1","06","02","05","01","  ",null,null,null,"FEE X-Ray PPS - Closed (Moved to new WBS Element)           ",{"$nulls":47},"Gunter Haller"]
["1","06","02","05","02","  ",null,null,null,"Near Hall X-Ray PPS - Closed to BCWP                        ",{"$nulls":47},"Gunter Haller"]
["1","06","02","05","03","  ",null,null,null,"Tunnel X-Ray PPS - Closed to BCWP                           ",{"$nulls":47},"Gunter Haller"]
["1","06","02","05","04","  ",null,null,null,"Far Hall X-Ray PPS - Closed to BCWP                         ",{"$nulls":47},"Gunter Haller"]
["1","06","02","06","  ","  ",null,null,null,"X-Ray MPS - Closed (Moved to new WBS Element)               ",{"$nulls":47},"Gunter Haller"]
["1","06","02","06","01","  ",null,null,null,"FEE X-Ray MPS - Closed to BCWP                              ",{"$nulls":47},"Gunter Haller"]
["1","06","02","07","  ","  ",null,null,null,"AMOS Experiment Controls X1                                 ",{"$nulls":47},"Gunter Haller"]
["1","06","02","07","01","  ",null,null,null,"AMOS Experiment Controls X1                                 ",{"$nulls":47},"Gunter Haller"]
["1","06","02","07","02","  ",null,null,null,"X-Ray Flourescence Detector                                 ",{"$nulls":47},"Gunter Haller"]
["1","06","02","07","03","  ",null,null,null,"Ion Imaging & Electron TOF                                  ",{"$nulls":47},"Gunter Haller"]
["1","06","02","07","04","  ",null,null,null,"Sample Source                                               ",{"$nulls":47},"Gunter Haller"]
["1","06","02","07","05","  ",null,null,null,"Vacuum Controls & Mechanical Exp 1                          ",{"$nulls":47},"Gunter Haller"]
["1","06","02","07","06","  ",null,null,null,"Refocus Optics                                              ",{"$nulls":47},"Gunter Haller"]
["1","06","02","07","07","  ",null,null,null,"Diagnostics                                                 ",{"$nulls":47},"Gunter Haller"]
["1","06","02","08","  ","  ",null,null,null,"AMOS Experiment Controls X2                                 ",{"$nulls":47},"Gunter Haller"]
["1","06","02","08","01","  ",null,null,null,"AMOS Experiment Controls X2                                 ",{"$nulls":47},"Gunter Haller"]
["1","06","02","08","02","  ",null,null,null,"X2 Praticle Imaging                                         ",{"$nulls":47},"Gunter Haller"]
["1","06","02","09","  ","  ",null,null,null,"Controls Management - Closed (Moved to new WBS Element)     ",{"$nulls":47},"Gunter Haller"]
["1","06","02","10","  ","  ",null,null,null,"Global Controls System                                      ",{"$nulls":47},"Gunter Haller"]
["1","06","02","10","01","  ",null,null,null,"Network                                                     ",{"$nulls":47},"Gunter Haller"]
["1","06","02","10","02","  ",null,null,null,"Machine Protection System                                   ",{"$nulls":47},"Gunter Haller"]
["1","06","02","10","03","  ",null,null,null,"Personnel Protection System                                 ",{"$nulls":47},"Gunter Haller"]
["1","06","02","10","04","  ",null,null,null,"Laser PPS                                                   ",{"$nulls":47},"Gunter Haller"]
["1","06","02","10","05","  ",null,null,null,"User Safeguards                                             ",{"$nulls":47},"Gunter Haller"]
["1","06","02","10","06","  ",null,null,null,"Timing System                                               ",{"$nulls":47},"Gunter Haller"]
["1","06","02","10","07","  ",null,null,null,"Data Management                                             ",{"$nulls":47},"Gunter Haller"]
["1","06","02","10","08","  ",null,null,null,"Global Cabling & Racks                                      ",{"$nulls":47},"Gunter Haller"]
["1","06","02","10","09","  ",null,null,null,"Laser Timing                                                ",{"$nulls":47},"Gunter Haller"]
["1","06","02","10","10","  ",null,null,null,"Experimental High Level Applications                        ",{"$nulls":47},"Gunter Haller"]
["1","06","02","11","  ","  ",null,null,null,"Laser Controls                                              ",{"$nulls":47},"Gunter Haller"]
["1","06","02","12","  ","  ",null,null,null,"K-Measuerment/Vacuum Subsystem                              ",{"$nulls":47},"Gunter Haller"]
["1","06","03","  ","  ","  ",null,null,null,"Mechanical/Vacuum Subsystem                                 ",{"$nulls":47},"Stefan Moeller"]
["1","06","03","01","  ","  ",null,null,null,"Chamber Support Tables - Mech/Vac                           ",{"$nulls":47},"Stefan Moeller"]
["1","06","03","02","  ","  ",null,null,null,"Vacuum Components - Mech/Vac                                ",{"$nulls":47},"Stefan Moeller"]
["1","06","03","02","01","  ",null,null,null,"Valves - Vacuum                                             ",{"$nulls":47},"Stefan Moeller"]
["1","06","03","02","02","  ",null,null,null,"Hardware - Vacuum                                           ",{"$nulls":47},"Stefan Moeller"]
["1","06","03","02","03","  ",null,null,null,"Ion Pump - Vacuum                                           ",{"$nulls":47},"Stefan Moeller"]
["1","06","03","02","04","  ",null,null,null,"Turbo Pump - Vacuum                                         ",{"$nulls":47},"Stefan Moeller"]
["1","06","03","02","05","  ",null,null,null,"Gauges - Vacuum                                             ",{"$nulls":47},"Stefan Moeller"]
["1","06","03","03","  ","  ",null,null,null,"Experimental Chambers                                       ",{"$nulls":47},"Stefan Moeller"]
["1","06","03","03","01","  ",null,null,null,"AP Chamber 1                                                ",{"$nulls":47},"Stefan Moeller"]
["1","06","03","03","02","  ",null,null,null,"AP Chamber 2                                                ",{"$nulls":47},"Stefan Moeller"]
["1","06","04","  ","  ","  ",null,null,null,"Laser Subsystem                                             ",{"$nulls":47},"Bill White"]
["1","06","04","01","  ","  ",null,null,null,"XES Laser                                                   ",{"$nulls":47},"Bill White"]
["1","06","04","02","  ","  ",null,null,null,"Laser Diagnostics                                           ",{"$nulls":47},"Bill White"]
["1","06","04","03","  ","  ",null,null,null,"Laser Optical Transport                                     ",{"$nulls":47},"Bill White"]
["1","06","04","04","  ","  ",null,null,null,"Laser Safety                                                ",{"$nulls":47},"Bill White"]
["1","06","05","  ","  ","  ",null,null,null,"X-Ray Detectors                                             ",{"$nulls":47},"Stefan Moeller"]
["1","06","05","01","  ","  ",null,null,null,"Beam Imaging                                                ",{"$nulls":47},"Stefan Moeller"]
["1","06","05","02","  ","  ",null,null,null,"Not Used                                                    ",{"$nulls":47},"Stefan Moeller"]
["1","06","05","03","  ","  ",null,null,null,"Beam Intensity                                              ",{"$nulls":47},"Stefan Moeller"]
["1","06","05","04","  ","  ",null,null,null,"Detector & Streak Camera                                    ",{"$nulls":47},"Stefan Moeller"]
["1","06","05","04","01","  ",null,null,null,"Detector Management                                         ",{"$nulls":47},"Stefan Moeller"]
["1","06","05","04","02","  ",null,null,null,"Streak Camera - LBL                                         ",{"$nulls":47},"Stefan Moeller"]
["1","06","06","  ","  ","  ",null,null,null,"System Installation & Alignment                             ",{"$nulls":47},"Stefan Moeller"]
["1","06","06","01","  ","  ",null,null,null,"Front End Install                                           ",{"$nulls":47},"Stefan Moeller"]
["1","06","06","02","  ","  ",null,null,null,"Near Hall Install                                           ",{"$nulls":47},"Stefan Moeller"]
["1","06","06","02","01","  ",null,null,null,"Near Hall Install Global Controls                           ",{"$nulls":47},"Stefan Moeller"]
["1","06","06","02","02","  ",null,null,null,"Near Hall Install Mech/Vac                                  ",{"$nulls":47},"Stefan Moeller"]
["1","06","06","02","03","  ",null,null,null,"Near Hall Install Laser                                     ",{"$nulls":47},"Stefan Moeller"]
["1","06","06","02","04","  ",null,null,null,"Near Hall Install Detectors                                 ",{"$nulls":47},"Stefan Moeller"]
["1","06","06","02","05","  ",null,null,null,"Near Hall Install Atomic Physics                            ",{"$nulls":47},"Stefan Moeller"]
["1","06","06","02","06","  ",null,null,null,"Near Hall Install PPS System                                ",{"$nulls":47},"Stefan Moeller"]
["1","06","06","02","07","  ",null,null,null,"Near Hall Install Laser PPS                                 ",{"$nulls":47},"Stefan Moeller"]
["1","06","06","02","08","  ",null,null,null,"2008 Near Hall Install                                      ",{"$nulls":47},"Stefan Moeller"]
["1","06","06","03","  ","  ",null,null,null,"Tunnel Install                                              ",{"$nulls":47},"Stefan Moeller"]
["1","06","06","04","  ","  ",null,null,null,"Far Hall Install                                            ",{"$nulls":47},"Stefan Moeller"]
["1","06","06","04","01","  ",null,null,null,"Far Hall Install Global Controls                            ",{"$nulls":47},"Stefan Moeller"]
["1","06","06","04","02","  ",null,null,null,"Far Hall Install Mech/Vac                                   ",{"$nulls":47},"Stefan Moeller"]
["1","06","06","04","04","  ",null,null,null,"Far Hall Install Detectors                                  ",{"$nulls":47},"Stefan Moeller"]
["1","06","06","04","05","  ",null,null,null,"Far Hall Install PPS System                                 ",{"$nulls":47},"Stefan Moeller"]
["1","06","06","04","06","  ",null,null,null,"2008 Far Hall Install                                       ",{"$nulls":47},"Stefan Moeller"]
["1","06","06","05","  ","  ",null,null,null,"Electron Dump Enclosure Install                             ",{"$nulls":47},"Stefan Moeller"]
["1","06","07","  ","  ","  ",null,null,null,"AMOS Experiment                                             ",{"$nulls":47},"Stefan Moeller"]
["1","06","07","01","  ","  ",null,null,null,"AP Management & Design                                      ",{"$nulls":47},"Stefan Moeller"]
["1","06","07","01","01","  ",null,null,null,"Management                                                  ",{"$nulls":47},"Stefan Moeller"]
["1","06","07","01","02","  ",null,null,null,"Conceptual Design                                           ",{"$nulls":47},"Stefan Moeller"]
["1","06","07","01","03","  ",null,null,null,"Preliminary Design                                          ",{"$nulls":47},"Stefan Moeller"]
["1","06","07","01","04","  ",null,null,null,"Final Design                                                ",{"$nulls":47},"Stefan Moeller"]
["1","06","07","02","  ","  ",null,null,null,"AP X1 High Field Physics Exp.                               ",{"$nulls":47},"Stefan Moeller"]
["1","06","07","02","01","  ",null,null,null,"X-Ray Fluorescence Detectors                                ",{"$nulls":47},"Stefan Moeller"]
["1","06","07","02","02","  ",null,null,null,"Ion Imaging & Electron TOF Detectors                        ",{"$nulls":47},"Stefan Moeller"]
["1","06","07","02","03","  ",null,null,null,"Sample Source                                               ",{"$nulls":47},"Stefan Moeller"]
["1","06","07","02","04","  ",null,null,null,"Vacuum System                                               ",{"$nulls":47},"Stefan Moeller"]
["1","06","07","02","05","  ",null,null,null,"Other X1 Items                                              ",{"$nulls":47},"Stefan Moeller"]
["1","06","07","03","  ","  ",null,null,null,"AP Refocus Optics                                           ",{"$nulls":47},"Stefan Moeller"]
["1","06","07","04","  ","  ",null,null,null,"AP Diagnostics                                              ",{"$nulls":47},"Stefan Moeller"]
["1","06","07","05","  ","  ",null,null,null,"AP Particle Imaging Experiment                              ",{"$nulls":47},"Stefan Moeller"]
["1","06","08","  ","  ","  ",null,null,null,"Crystals and Gratings                                       ",{"$nulls":47},"Stefan Moeller"]
["1","06","08","01","  ","  ",null,null,null,"K Measurement Spectrometer                                  ",{"$nulls":47},"Stefan Moeller"]
["1","06","09","  ","  ","  ",null,null,null,"Mechanical Systems                                          ",{"$nulls":47},"Stefan Moeller"]
["1","06","09","01","  ","  ",null,null,null,"PPS Stoppers                                                ",{"$nulls":47},"Stefan Moeller"]
["1","06","09","02","  ","  ",null,null,null,"PPS Shielding                                               ",{"$nulls":47},"Stefan Moeller"]
["1","06","09","03","  ","  ",null,null,null,"NEH Hutch Doors                                             ",{"$nulls":47},"Stefan Moeller"]
["1","09","  ","  ","  ","  ",null,null,null,"CONVENTIONAL FACILITIES                                     "]
["1","09","01","  ","  ","  ",null,null,null,"System Management & Integration                             ",{"$nulls":47},"David Saenz"]
["1","09","01","01","  ","  ",null,null,null,"Management                                                  ",{"$nulls":47},"David Saenz"]
["1","09","01","02","  ","  ",null,null,null,"CF Engineering                                              ",{"$nulls":47},"David Saenz"]
["1","09","01","03","  ","  ",null,null,null,"Construction Management & AE Support                        ",{"$nulls":47},"David Saenz"]
["1","09","01","04","  ","  ",null,null,null,"Mechanical Design (MD)                                      ",{"$nulls":47},"David Saenz"]
["1","09","01","04","01","  ",null,null,null,"Mechanical Design Title 1 - RSY through CLOC                ",{"$nulls":47},"David Saenz"]
["1","09","01","04","02","  ",null,null,null,"Mechanical Design T1 Linac Facilities                       ",{"$nulls":47},"David Saenz"]
["1","09","01","04","03","  ",null,null,null,"Mechanical Design Title 2 - RSY through CLOC                ",{"$nulls":47},"David Saenz"]
["1","09","01","04","04","  ",null,null,null,"Mechanical Design T2 Linac Facilities                       ",{"$nulls":47},"David Saenz"]
["1","09","01","04","05","  ",null,null,null,"Mechanical Design Title 3 Linac Facility                    ",{"$nulls":47},"David Saenz"]
["1","09","01","04","06","  ",null,null,null,"Mechanical Design Title 3 - RSY through CLOC                ",{"$nulls":47},"David Saenz"]
["1","09","01","05","  ","  ",null,null,null,"Conventional Experiment Facility (CEF)                      ",{"$nulls":47},"David Saenz"]
["1","09","01","05","01","  ",null,null,null,"CEF Engineering Title 1 - RSY through CLOC                  ",{"$nulls":47},"David Saenz"]
["1","09","01","05","02","  ",null,null,null,"CEF Engineering Title 1 Linac Facility                      ",{"$nulls":47},"David Saenz"]
["1","09","01","05","03","  ",null,null,null,"CEF Engineering Title 2 - RSY through CLOC                  ",{"$nulls":47},"David Saenz"]
["1","09","01","05","04","  ",null,null,null,"CEF Design Linac Facility Title 2                           ",{"$nulls":47},"David Saenz"]
["1","09","02","  ","  ","  ",null,null,null,"Title 1 & Title 2 Conventional Facilities                   ",{"$nulls":47},"David Saenz"]
["1","09","02","02","  ","  ",null,null,null,"A & E Services  - RSY throguh CLOC                          ",{"$nulls":47},"David Saenz"]
["1","09","02","02","01","  ",null,null,null,"Title 1 Design                                              ",{"$nulls":47},"David Saenz"]
["1","09","02","02","02","  ",null,null,null,"Title 2 Design                                              ",{"$nulls":47},"David Saenz"]
["1","09","02","03","  ","  ",null,null,null,"A & E Services - (S20, MMF,MCC)                             ",{"$nulls":47},"David Saenz"]
["1","09","02","03","01","  ",null,null,null,"Title 1 Design (Sector 20)                                  ",{"$nulls":47},"David Saenz"]
["1","09","02","03","02","  ",null,null,null,"Title 2 Design (Sector 20)                                  ",{"$nulls":47},"David Saenz"]
["1","09","02","03","03","  ",null,null,null,"Title 1 Design (MMF)                                        ",{"$nulls":47},"David Saenz"]
["1","09","02","03","04","  ",null,null,null,"Title 2 Design (MMF)                                        ",{"$nulls":47},"David Saenz"]
["1","09","02","03","05","  ",null,null,null,"Title 1 Design (MCC)                                        ",{"$nulls":47},"David Saenz"]
["1","09","02","03","06","  ",null,null,null,"Title 2 Design (MCC)                                        ",{"$nulls":47},"David Saenz"]
["1","09","03","  ","  ","  ",null,null,null,"Construction-T3 Conventional Facilities                     ",{"$nulls":47},"David Saenz"]
["1","09","03","01","  ","  ",null,null,null,"Sector 20 Injector Facilities                               ",{"$nulls":47},"David Saenz"]
["1","09","03","01","01","  ",null,null,null,"S20 - Site Preparation/General Requirements                 ",{"$nulls":47},"David Saenz"]
["1","09","03","01","02","  ",null,null,null,"S20 - Site Construction                                     ",{"$nulls":47},"David Saenz"]
["1","09","03","01","03","  ",null,null,null,"S20 - Concrete                                              ",{"$nulls":47},"David Saenz"]
["1","09","03","01","04","  ",null,null,null,"S20 - Masonry                                               ",{"$nulls":47},"David Saenz"]
["1","09","03","01","05","  ",null,null,null,"S20 - Metals                                                ",{"$nulls":47},"David Saenz"]
["1","09","03","01","06","  ",null,null,null,"S20 - Woods & Plastics                                      ",{"$nulls":47},"David Saenz"]
["1","09","03","01","07","  ",null,null,null,"S20 - Thermal & Moisture Protection                         ",{"$nulls":47},"David Saenz"]
["1","09","03","01","08","  ",null,null,null,"S20 - Doors & Windows                                       ",{"$nulls":47},"David Saenz"]
["1","09","03","01","09","  ",null,null,null,"S20 - Finishes                                              ",{"$nulls":47},"David Saenz"]
["1","09","03","01","10","  ",null,null,null,"S20 - Specialties                                           ",{"$nulls":47},"David Saenz"]
["1","09","03","01","14","  ",null,null,null,"S20 - Conveying Systems                                     ",{"$nulls":47},"David Saenz"]
["1","09","03","01","15","  ",null,null,null,"S20 - Mechanical                                            ",{"$nulls":47},"David Saenz"]
["1","09","03","01","16","  ",null,null,null,"S20 - Electrical                                            ",{"$nulls":47},"David Saenz"]
["1","09","03","01","20","  ",null,null,null,"S20 - Project Close Out                                     ",{"$nulls":47},"David Saenz"]
["1","09","03","02","  ","  ",null,null,null,"Magnetic Measurement Facility                               ",{"$nulls":47},"David Saenz"]
["1","09","03","02","01","  ",null,null,null,"MMF - Site Preparation/General Requirements                 ",{"$nulls":47},"David Saenz"]
["1","09","03","02","02","  ",null,null,null,"MMF - Site Construction                                     ",{"$nulls":47},"David Saenz"]
["1","09","03","02","03","  ",null,null,null,"MMF - Concrete                                              ",{"$nulls":47},"David Saenz"]
["1","09","03","02","04","  ",null,null,null,"Utilities                                                   ",{"$nulls":47},"David Saenz"]
["1","09","03","02","05","  ",null,null,null,"MMF - Metals                                                ",{"$nulls":47},"David Saenz"]
["1","09","03","02","06","  ",null,null,null,"MMF - Woods & Plastics                                      ",{"$nulls":47},"David Saenz"]
["1","09","03","02","07","  ",null,null,null,"MMF - Thermal & Moisture Protection                         ",{"$nulls":47},"David Saenz"]
["1","09","03","02","08","  ",null,null,null,"MMF - Doors & Windows                                       ",{"$nulls":47},"David Saenz"]
["1","09","03","02","09","  ",null,null,null,"MMF - Finishes                                              ",{"$nulls":47},"David Saenz"]
["1","09","03","02","10","  ",null,null,null,"MMF - Specialities                                          ",{"$nulls":47},"David Saenz"]
["1","09","03","02","13","  ",null,null,null,"                                                            ",{"$nulls":47},"David Saenz"]
["1","09","03","02","14","  ",null,null,null,"MMF - Conveying Systems                                     ",{"$nulls":47},"David Saenz"]
["1","09","03","02","15","  ",null,null,null,"MMF - Mechanical                                            ",{"$nulls":47},"David Saenz"]
["1","09","03","02","16","  ",null,null,null,"MMF - Electrical                                            ",{"$nulls":47},"David Saenz"]
["1","09","03","02","20","  ",null,null,null,"MMF - Project Close Out                                     ",{"$nulls":47},"David Saenz"]
["1","09","03","03","  ","  ",null,null,null,"BTH West                                                    ",{"$nulls":47},"David Saenz"]
["1","09","03","03","01","  ",null,null,null,"BTH West - Site Preparation                                 ",{"$nulls":47},"David Saenz"]
["1","09","03","03","15","  ",null,null,null,"BTH West - Mechanical                                       ",{"$nulls":47},"David Saenz"]
["1","09","03","03","16","  ",null,null,null,"BTH West - Electrical                                       ",{"$nulls":47},"David Saenz"]
["1","09","03","03","20","  ",null,null,null,"BTH West - Project Close Out                                ",{"$nulls":47},"David Saenz"]
["1","09","03","04","  ","  ",null,null,null,"Linac Facility Upgrade (LN)                                 ",{"$nulls":47},"David Saenz"]
["1","09","03","04","01","  ",null,null,null,"LN - Site Preparation                                       ",{"$nulls":47},"David Saenz"]
["1","09","03","04","02","  ",null,null,null,"LN - Sitework                                               ",{"$nulls":47},"David Saenz"]
["1","09","03","04","03","  ",null,null,null,"Electrical                                                  ",{"$nulls":47},"David Saenz"]
["1","09","03","04","04","  ",null,null,null,"Utilities                                                   ",{"$nulls":47},"David Saenz"]
["1","09","03","04","05","  ",null,null,null,"Linac - Metals                                              ",{"$nulls":47},"David Saenz"]
["1","09","03","04","06","  ",null,null,null,"Special System - Fire Protection                            ",{"$nulls":47},"David Saenz"]
["1","09","03","04","10","  ",null,null,null,"Project Close Out Linac Facility                            ",{"$nulls":47},"David Saenz"]
["1","09","03","04","15","  ",null,null,null,"LN - Mechanical                                             ",{"$nulls":47},"David Saenz"]
["1","09","03","04","16","  ",null,null,null,"LN - Electrical                                             ",{"$nulls":47},"David Saenz"]
["1","09","03","04","20","  ",null,null,null,"LN - Project Close Out                                      ",{"$nulls":47},"David Saenz"]
["1","09","03","05","  ","  ",null,null,null,"Research Yard Modifications                                 ",{"$nulls":47},"David Saenz"]
["1","09","03","05","01","  ",null,null,null,"RY - Site Preparation                                       ",{"$nulls":47},"David Saenz"]
["1","09","03","05","01","01",null,null,null,"General Requirements- CEF                                   ",{"$nulls":47},"David Saenz"]
["1","09","03","05","01","02",null,null,null,"General Requirements - G/C                                  ",{"$nulls":47},"David Saenz"]
["1","09","03","05","02","  ",null,null,null,"RY - FFTB/BSY & Site Construction                           ",{"$nulls":47},"David Saenz"]
["1","09","03","05","02","01",null,null,null,"Site Construction - CEF                                     ",{"$nulls":47},"David Saenz"]
["1","09","03","05","02","02",null,null,null,"Site Construction - G/C                                     ",{"$nulls":47},"David Saenz"]
["1","09","03","05","03","  ",null,null,null,"Electrical                                                  ",{"$nulls":47},"David Saenz"]
["1","09","03","05","03","01",null,null,null,"Electrical CEF                                              ",{"$nulls":47},"David Saenz"]
["1","09","03","05","03","02",null,null,null,"Electrical G/C                                              ",{"$nulls":47},"David Saenz"]
["1","09","03","05","04","  ",null,null,null,"Utilities                                                   ",{"$nulls":47},"David Saenz"]
["1","09","03","05","04","01",null,null,null,"Utilities CEF                                               ",{"$nulls":47},"David Saenz"]
["1","09","03","05","04","02",null,null,null,"Utilities G/C                                               ",{"$nulls":47},"David Saenz"]
["1","09","03","05","05","  ",null,null,null,"RY - Metals                                                 ",{"$nulls":47},"David Saenz"]
["1","09","03","05","05","01",null,null,null,"HVAC CEF                                                    ",{"$nulls":47},"David Saenz"]
["1","09","03","05","05","02",null,null,null,"HVAC G/C                                                    ",{"$nulls":47},"David Saenz"]
["1","09","03","05","06","  ",null,null,null,"Special System - Fire Protection                            ",{"$nulls":47},"David Saenz"]
["1","09","03","05","06","01",null,null,null,"Special System - Fire Protection CEF                        ",{"$nulls":47},"David Saenz"]
["1","09","03","05","06","02",null,null,null,"Special System - Fire Protection                            ",{"$nulls":47},"David Saenz"]
["1","09","03","05","07","  ",null,null,null,"Interior                                                    ",{"$nulls":47},"David Saenz"]
["1","09","03","05","07","01",null,null,null,"Interior CEF                                                ",{"$nulls":47},"David Saenz"]
["1","09","03","05","07","02",null,null,null,"Interior G/C                                                ",{"$nulls":47},"David Saenz"]
["1","09","03","05","10","  ",null,null,null,"Project Close Out Reasearch Yard                            ",{"$nulls":47},"David Saenz"]
["1","09","03","05","20","  ",null,null,null,"RY - Project Close Out                                      ",{"$nulls":47},"David Saenz"]
["1","09","03","06","  ","  ",null,null,null,"Pre-Purchase Equipment                                      ",{"$nulls":47},"David Saenz"]
["1","09","03","06","01","  ",null,null,null,"PPE - General Requirements                                  ",{"$nulls":47},"David Saenz"]
["1","09","03","06","02","  ",null,null,null,"AR - Site Construction                                      ",{"$nulls":47},"David Saenz"]
["1","09","03","06","03","  ",null,null,null,"AR - Concrete                                               ",{"$nulls":47},"David Saenz"]
["1","09","03","06","04","  ",null,null,null,"Utilities                                                   ",{"$nulls":47},"David Saenz"]
["1","09","03","06","05","  ",null,null,null,"HVAC                                                        ",{"$nulls":47},"David Saenz"]
["1","09","03","06","06","  ",null,null,null,"Special System- Fire Protection                             ",{"$nulls":47},"David Saenz"]
["1","09","03","06","07","  ",null,null,null,"Interior                                                    ",{"$nulls":47},"David Saenz"]
["1","09","03","06","10","  ",null,null,null,"Project Close Out  Beam Trans Hall                          ",{"$nulls":47},"David Saenz"]
["1","09","03","06","11","  ",null,null,null,"Pre-Purchase Equipment for Beam Path                        ",{"$nulls":47},"David Saenz"]
["1","09","03","06","20","  ",null,null,null,"AR - Project Close Out                                      ",{"$nulls":47},"David Saenz"]
["1","09","03","07","  ","  ",null,null,null,"SITEWORK                                                    ",{"$nulls":47},"David Saenz"]
["1","09","03","07","01","  ",null,null,null,"SW - Site Preparation/General Requirements                  ",{"$nulls":47},"David Saenz"]
["1","09","03","07","02","  ",null,null,null,"SW - Site Construction                                      ",{"$nulls":47},"David Saenz"]
["1","09","03","07","03","  ",null,null,null,"SW - Concrete                                               ",{"$nulls":47},"David Saenz"]
["1","09","03","07","04","  ",null,null,null,"Utilities                                                   ",{"$nulls":47},"David Saenz"]
["1","09","03","07","05","  ",null,null,null,"HVAC                                                        ",{"$nulls":47},"David Saenz"]
["1","09","03","07","06","  ",null,null,null,"Special System - Fire Protection                            ",{"$nulls":47},"David Saenz"]
["1","09","03","07","07","  ",null,null,null,"Interior                                                    ",{"$nulls":47},"David Saenz"]
["1","09","03","07","09","  ",null,null,null,"Tunneling                                                   ",{"$nulls":47},"David Saenz"]
["1","09","03","07","10","  ",null,null,null,"Project Close Out Undulator Hall                            ",{"$nulls":47},"David Saenz"]
["1","09","03","07","15","  ",null,null,null,"SW - Mechanical                                             ",{"$nulls":47},"David Saenz"]
["1","09","03","07","16","  ",null,null,null,"SW - Electrical                                             ",{"$nulls":47},"David Saenz"]
["1","09","03","07","17","  ",null,null,null,"SW - Others (include Div 4, and 6 through 14)               ",{"$nulls":47},"David Saenz"]
["1","09","03","07","20","  ",null,null,null,"SW - Project Close Out                                      ",{"$nulls":47},"David Saenz"]
["1","09","03","08","  ","  ",null,null,null,"Beam Transport Hall (BTH)                                   ",{"$nulls":47},"David Saenz"]
["1","09","03","08","01","  ",null,null,null,"BTH - Site Preparation/General Requirements                 ",{"$nulls":47},"David Saenz"]
["1","09","03","08","02","  ",null,null,null,"BTH - Site Construction                                     ",{"$nulls":47},"David Saenz"]
["1","09","03","08","03","  ",null,null,null,"BTH - Concrete                                              ",{"$nulls":47},"David Saenz"]
["1","09","03","08","04","  ",null,null,null,"Utilities                                                   ",{"$nulls":47},"David Saenz"]
["1","09","03","08","05","  ",null,null,null,"BTH - Metals                                                ",{"$nulls":47},"David Saenz"]
["1","09","03","08","06","  ",null,null,null,"Special System - Fire Protection                            ",{"$nulls":47},"David Saenz"]
["1","09","03","08","07","  ",null,null,null,"Interior                                                    ",{"$nulls":47},"David Saenz"]
["1","09","03","08","09","  ",null,null,null,"Tunneling                                                   ",{"$nulls":47},"David Saenz"]
["1","09","03","08","10","  ",null,null,null,"Project Close Out Front End Enclosure                       ",{"$nulls":47},"David Saenz"]
["1","09","03","08","15","  ",null,null,null,"BTH - Mechanical                                            ",{"$nulls":47},"David Saenz"]
["1","09","03","08","16","  ",null,null,null,"BTH - Electrical                                            ",{"$nulls":47},"David Saenz"]
["1","09","03","08","17","  ",null,null,null,"BTH - Others (include Div 4, and 6 through 14)              ",{"$nulls":47},"David Saenz"]
["1","09","03","08","20","  ",null,null,null,"BTH - Project Close Out                                     ",{"$nulls":47},"David Saenz"]
["1","09","03","09","  ","  ",null,null,null,"Front End Enclosure (FEE)                                   ",{"$nulls":47},"David Saenz"]
["1","09","03","09","01","  ",null,null,null,"FEE - Site Preparation/General Requirements                 ",{"$nulls":47},"David Saenz"]
["1","09","03","09","02","  ",null,null,null,"FEE - Site Construction                                     ",{"$nulls":47},"David Saenz"]
["1","09","03","09","03","  ",null,null,null,"FEE - Concrete                                              ",{"$nulls":47},"David Saenz"]
["1","09","03","09","04","  ",null,null,null,"Utilities                                                   ",{"$nulls":47},"David Saenz"]
["1","09","03","09","05","  ",null,null,null,"FEE - Metals                                                ",{"$nulls":47},"David Saenz"]
["1","09","03","09","06","  ",null,null,null,"Special System (Fire Protection) Beam Dump                  ",{"$nulls":47},"David Saenz"]
["1","09","03","09","09","  ",null,null,null,"Tunneling                                                   ",{"$nulls":47},"David Saenz"]
["1","09","03","09","10","  ",null,null,null,"Project Close Out Beam Dump                                 ",{"$nulls":47},"David Saenz"]
["1","09","03","09","15","  ",null,null,null,"FEE - Mechanical                                            ",{"$nulls":47},"David Saenz"]
["1","09","03","09","16","  ",null,null,null,"FEE - Electrical                                            ",{"$nulls":47},"David Saenz"]
["1","09","03","09","17","  ",null,null,null,"FEE - Others (include Div 4, and 6 through 14)              ",{"$nulls":47},"David Saenz"]
["1","09","03","09","20","  ",null,null,null,"FEE - Project Close Out                                     ",{"$nulls":47},"David Saenz"]
["1","09","03","10","  ","  ",null,null,null,"Electron Beam Dump (EBD)                                    ",{"$nulls":47},"David Saenz"]
["1","09","03","10","01","  ",null,null,null,"EBD - Site Preparation/General Requirements                 ",{"$nulls":47},"David Saenz"]
["1","09","03","10","02","  ",null,null,null,"EBD - Site Construction                                     ",{"$nulls":47},"David Saenz"]
["1","09","03","10","03","  ",null,null,null,"EBD - Concrete                                              ",{"$nulls":47},"David Saenz"]
["1","09","03","10","04","  ",null,null,null,"Utilities                                                   ",{"$nulls":47},"David Saenz"]
["1","09","03","10","05","  ",null,null,null,"EBD - Metals                                                ",{"$nulls":47},"David Saenz"]
["1","09","03","10","06","  ",null,null,null,"Special System - Fire Protection                            ",{"$nulls":47},"David Saenz"]
["1","09","03","10","07","  ",null,null,null,"Interior                                                    ",{"$nulls":47},"David Saenz"]
["1","09","03","10","10","  ",null,null,null,"Project Close Out Near Experimental Hall                    ",{"$nulls":47},"David Saenz"]
["1","09","03","10","15","  ",null,null,null,"EBD - Mechanical                                            ",{"$nulls":47},"David Saenz"]
["1","09","03","10","16","  ",null,null,null,"EBD - Electrical                                            ",{"$nulls":47},"David Saenz"]
["1","09","03","10","17","  ",null,null,null,"EBD - Others (include Div 4, and 6 through 14)              ",{"$nulls":47},"David Saenz"]
["1","09","03","10","20","  ",null,null,null,"EBD - Project Close Out                                     ",{"$nulls":47},"David Saenz"]
["1","09","03","11","  ","  ",null,null,null,"Near Experimental Hall (NEH)                                ",{"$nulls":47},"David Saenz"]
["1","09","03","11","01","  ",null,null,null,"NEH - Site Preparation/General Requirements                 ",{"$nulls":47},"David Saenz"]
["1","09","03","11","02","  ",null,null,null,"NEH - Site Construction                                     ",{"$nulls":47},"David Saenz"]
["1","09","03","11","03","  ",null,null,null,"NEH - Concrete                                              ",{"$nulls":47},"David Saenz"]
["1","09","03","11","04","  ",null,null,null,"Utilities                                                   ",{"$nulls":47},"David Saenz"]
["1","09","03","11","05","  ",null,null,null,"NEH - Metals                                                ",{"$nulls":47},"David Saenz"]
["1","09","03","11","06","  ",null,null,null,"Special System - Fire Protection                            ",{"$nulls":47},"David Saenz"]
["1","09","03","11","07","  ",null,null,null,"Interiors                                                   ",{"$nulls":47},"David Saenz"]
["1","09","03","11","09","  ",null,null,null,"Tunneling                                                   ",{"$nulls":47},"David Saenz"]
["1","09","03","11","10","  ",null,null,null,"Project Close Out X-Ray Transport & Diagonistic             ",{"$nulls":47},"David Saenz"]
["1","09","03","11","15","  ",null,null,null,"NEH - Mechanical                                            ",{"$nulls":47},"David Saenz"]
["1","09","03","11","16","  ",null,null,null,"NEH - Electrical                                            ",{"$nulls":47},"David Saenz"]
["1","09","03","11","17","  ",null,null,null,"NEH - Others (include Div 4, and 6 through 14)              ",{"$nulls":47},"David Saenz"]
["1","09","03","11","20","  ",null,null,null,"NEH - Project Close Out                                     ",{"$nulls":47},"David Saenz"]
["1","09","03","12","  ","  ",null,null,null,"Undulator Hall (UH)                                         ",{"$nulls":47},"David Saenz"]
["1","09","03","12","01","  ",null,null,null,"UH - Site Preparation/General Requirements                  ",{"$nulls":47},"David Saenz"]
["1","09","03","12","02","  ",null,null,null,"UH - Site Construction                                      ",{"$nulls":47},"David Saenz"]
["1","09","03","12","03","  ",null,null,null,"UH - Concrete                                               ",{"$nulls":47},"David Saenz"]
["1","09","03","12","04","  ",null,null,null,"Utilities                                                   ",{"$nulls":47},"David Saenz"]
["1","09","03","12","05","  ",null,null,null,"UH - Metals                                                 ",{"$nulls":47},"David Saenz"]
["1","09","03","12","06","  ",null,null,null,"Special System - Fire Protection                            ",{"$nulls":47},"David Saenz"]
["1","09","03","12","07","  ",null,null,null,"Interiors                                                   ",{"$nulls":47},"David Saenz"]
["1","09","03","12","09","  ",null,null,null,"Tunneling                                                   ",{"$nulls":47},"David Saenz"]
["1","09","03","12","10","  ",null,null,null,"Project Close Out Far Experimental Hall                     ",{"$nulls":47},"David Saenz"]
["1","09","03","12","15","  ",null,null,null,"UH - Mechanical                                             ",{"$nulls":47},"David Saenz"]
["1","09","03","12","16","  ",null,null,null,"UH - Electrical                                             ",{"$nulls":47},"David Saenz"]
["1","09","03","12","17","  ",null,null,null,"UH - Others (include Div 4, and 6 through 14)               ",{"$nulls":47},"David Saenz"]
["1","09","03","12","19","  ",null,null,null,"UH - Tunnel Construction                                    ",{"$nulls":47},"David Saenz"]
["1","09","03","12","20","  ",null,null,null,"UH - Project Close Out                                      ",{"$nulls":47},"David Saenz"]
["1","09","03","13","  ","  ",null,null,null,"X-Ray - Transport & Diagnostic Hall (XRTD)                  ",{"$nulls":47},"David Saenz"]
["1","09","03","13","01","  ",null,null,null,"XRTD - Site Preparation/General Requirements                ",{"$nulls":47},"David Saenz"]
["1","09","03","13","02","  ",null,null,null,"XRTD - Site Construction                                    ",{"$nulls":47},"David Saenz"]
["1","09","03","13","03","  ",null,null,null,"XRTD - Concrete                                             ",{"$nulls":47},"David Saenz"]
["1","09","03","13","04","  ",null,null,null,"Utilities                                                   ",{"$nulls":47},"David Saenz"]
["1","09","03","13","05","  ",null,null,null,"HVAC                                                        ",{"$nulls":47},"David Saenz"]
["1","09","03","13","06","  ",null,null,null,"Special System - Fire Protection                            ",{"$nulls":47},"David Saenz"]
["1","09","03","13","07","  ",null,null,null,"Interior                                                    ",{"$nulls":47},"David Saenz"]
["1","09","03","13","10","  ",null,null,null,"Project Close Out Central Laboratory Office Complex (CLOC)  ",{"$nulls":47},"David Saenz"]
["1","09","03","13","15","  ",null,null,null,"XRTD - Mechanical                                           ",{"$nulls":47},"David Saenz"]
["1","09","03","13","16","  ",null,null,null,"XRTD - Electrical                                           ",{"$nulls":47},"David Saenz"]
["1","09","03","13","17","  ",null,null,null,"XRTD - Others (include Div 4, and 6 through 14)             ",{"$nulls":47},"David Saenz"]
["1","09","03","13","19","  ",null,null,null,"XRTD - Tunnel Construction                                  ",{"$nulls":47},"David Saenz"]
["1","09","03","13","20","  ",null,null,null,"XRTD - Project Close Out                                    ",{"$nulls":47},"David Saenz"]
["1","09","03","14","  ","  ",null,null,null,"Far Experimental Hall (FEH)                                 ",{"$nulls":47},"David Saenz"]
["1","09","03","14","01","  ",null,null,null,"FEH - Site Preparation/General Requirements                 ",{"$nulls":47},"David Saenz"]
["1","09","03","14","02","  ",null,null,null,"FEH - Site Construction                                     ",{"$nulls":47},"David Saenz"]
["1","09","03","14","03","  ",null,null,null,"FEH - Concrete                                              ",{"$nulls":47},"David Saenz"]
["1","09","03","14","05","  ",null,null,null,"FEH - Metals                                                ",{"$nulls":47},"David Saenz"]
["1","09","03","14","15","  ",null,null,null,"FEH - Mechanical                                            ",{"$nulls":47},"David Saenz"]
["1","09","03","14","16","  ",null,null,null,"FEH - Electrical                                            ",{"$nulls":47},"David Saenz"]
["1","09","03","14","17","  ",null,null,null,"FEH - Others (include Div 4, and 6 through 14)              ",{"$nulls":47},"David Saenz"]
["1","09","03","14","18","  ",null,null,null,"FEH - Access Tunnel                                         ",{"$nulls":47},"David Saenz"]
["1","09","03","14","19","  ",null,null,null,"FEH - Tunnel Construction                                   ",{"$nulls":47},"David Saenz"]
["1","09","03","14","20","  ",null,null,null,"FEH - Project Close Out                                     ",{"$nulls":47},"David Saenz"]
["1","09","03","15","  ","  ",null,null,null,"BTH Service Buildings 2.1, 2.2, and 2.3 (SB BTH)            ",{"$nulls":47},"David Saenz"]
["1","09","03","15","03","  ",null,null,null,"SB BTH - Concrete                                           ",{"$nulls":47},"David Saenz"]
["1","09","03","15","05","  ",null,null,null,"SB BTH - Metals                                             ",{"$nulls":47},"David Saenz"]
["1","09","03","15","15","  ",null,null,null,"SB BTH - Mechanical                                         ",{"$nulls":47},"David Saenz"]
["1","09","03","15","16","  ",null,null,null,"SB BTH - Electrical                                         ",{"$nulls":47},"David Saenz"]
["1","09","03","15","17","  ",null,null,null,"SB BTH - Others (include Div 4, and 6 through 14            ",{"$nulls":47},"David Saenz"]
["1","09","03","15","20","  ",null,null,null,"SB BTH - Project Close Out                                  ",{"$nulls":47},"David Saenz"]
["1","09","03","16","  ","  ",null,null,null,"UH Service Building 3.1 (SB UH)                             ",{"$nulls":47},"David Saenz"]
["1","09","03","16","01","  ",null,null,null,"SB UH - Site Preparation                                    ",{"$nulls":47},"David Saenz"]
["1","09","03","16","03","  ",null,null,null,"SB UH - Concrete                                            ",{"$nulls":47},"David Saenz"]
["1","09","03","16","05","  ",null,null,null,"SB UH - Metals                                              ",{"$nulls":47},"David Saenz"]
["1","09","03","16","15","  ",null,null,null,"SB UH - Mechanical                                          ",{"$nulls":47},"David Saenz"]
["1","09","03","16","16","  ",null,null,null,"SB UH - Electrical                                          ",{"$nulls":47},"David Saenz"]
["1","09","03","16","17","  ",null,null,null,"SB UH - Others (include Div 4, and 6 through 14)            ",{"$nulls":47},"David Saenz"]
["1","09","03","16","20","  ",null,null,null,"SB UH - Project Close Out                                   ",{"$nulls":47},"David Saenz"]
["1","09","03","17","  ","  ",null,null,null,"FEH Service Building 8.1 (FEH SB)                           ",{"$nulls":47},"David Saenz"]
["1","09","03","17","01","  ",null,null,null,"SB FEH - Site Preparation                                   ",{"$nulls":47},"David Saenz"]
["1","09","03","17","03","  ",null,null,null,"SB FEH - Concrete                                           ",{"$nulls":47},"David Saenz"]
["1","09","03","17","05","  ",null,null,null,"SB FEH - Metals                                             ",{"$nulls":47},"David Saenz"]
["1","09","03","17","15","  ",null,null,null,"SB FEH - Mechanical                                         ",{"$nulls":47},"David Saenz"]
["1","09","03","17","16","  ",null,null,null,"SB FEH - Electrical                                         ",{"$nulls":47},"David Saenz"]
["1","09","03","17","17","  ",null,null,null,"SB FEH - Others (include Div 4, and 6 through 14            ",{"$nulls":47},"David Saenz"]
["1","09","03","17","20","  ",null,null,null,"SB FEH - Project Close Out                                  ",{"$nulls":47},"David Saenz"]
["1","09","03","18","  ","  ",null,null,null,"NEH Central Utility Plant (CUP)                             ",{"$nulls":47},"David Saenz"]
["1","09","03","18","01","  ",null,null,null,"CUP - Site Preparation/General Requirements                 ",{"$nulls":47},"David Saenz"]
["1","09","03","18","02","  ",null,null,null,"CUP - Site Construction                                     ",{"$nulls":47},"David Saenz"]
["1","09","03","18","03","  ",null,null,null,"CUP - Concrete                                              ",{"$nulls":47},"David Saenz"]
["1","09","03","18","05","  ",null,null,null,"CUP - Metals                                                ",{"$nulls":47},"David Saenz"]
["1","09","03","18","15","  ",null,null,null,"CUP - Mechanical                                            ",{"$nulls":47},"David Saenz"]
["1","09","03","18","16","  ",null,null,null,"CUP - Electrical                                            ",{"$nulls":47},"David Saenz"]
["1","09","03","18","17","  ",null,null,null,"CUP - Others (include Div 4, and 6 through 14)              ",{"$nulls":47},"David Saenz"]
["1","09","03","18","20","  ",null,null,null,"CUP - Project Close Out                                     ",{"$nulls":47},"David Saenz"]
["1","09","03","19","  ","  ",null,null,null,"SLAC Space Renovation for LCLS Ops                          ",{"$nulls":47},"David Saenz"]
["1","09","03","19","01","  ",null,null,null,"ED&I of SLAC Space Renovation for LCLS Ops                  ",{"$nulls":47},"David Saenz"]
["1","09","03","19","02","  ",null,null,null,"Construction of SLAC Space Renovation for LCLS Ops          ",{"$nulls":47},"David Saenz"]
["1","09","03","20","  ","  ",null,null,null,"Construction Credits and Debits                             ",{"$nulls":47},"David Saenz"]
["1","09","03","20","01","  ",null,null,null,"Reduction for Subcontractor Work in Deleting CLOC           ",{"$nulls":47},"David Saenz"]
["1","09","03","20","02","  ",null,null,null,"Bulletin #2 Changes                                         ",{"$nulls":47},"David Saenz"]
["2","  ","  ","  ","  ","  ",null,null,null,"LCLS PROJECT - R&D, SPARES, COMMISSIONING                   "]
["2","01","  ","  ","  ","  ",null,null,null,"LCLS PROJECT MGMT, PLANNING & ADMN (OPC)                    "]
["2","01","01","  ","  ","  ",null,null,null,"LCLS Commissioning Mgmt & Physics Support                   "]
["2","01","01","01","  ","  ",null,null,null,"LCLS Commissioning Management                               ",{"$nulls":47},"Dave Schultz"]
["2","01","01","02","  ","  ",null,null,null,"Injector Physics                                            ",{"$nulls":47},"Dave Schultz"]
["2","01","01","03","  ","  ",null,null,null,"Linac Physics                                               ",{"$nulls":47},"Dave Schultz"]
["2","01","01","04","  ","  ",null,null,null,"Undulator Physics                                           ",{"$nulls":47},"Dave Schultz"]
["2","01","01","05","  ","  ",null,null,null,"X-Ray Transport Physics                                     "]
["2","01","01","06","  ","  ",null,null,null,"X-Ray Physics Commissioning                                 "]
["2","01","01","07","  ","  ",null,null,null,"Conventional Facilities Physics                             ",{"$nulls":47},"Dave Schultz"]
["2","01","01","08","  ","  ",null,null,null,"Consulting Physics (Collaboration)                          ",{"$nulls":47},"Dave Schultz"]
["2","01","01","09","  ","  ",null,null,null,"Consulting Physics (SLAC)                                   ",{"$nulls":47},"Dave Schultz"]
["2","01","01","10","  ","  ",null,null,null,"Global Controls Physics Liaison                             ",{"$nulls":47},"Dave Schultz"]
["2","01","01","11","  ","  ",null,null,null,"Global Controls OPC                                         "]
["2","01","01","11","01","  ",null,null,null,"EPICS Control Modules                                       ",{"$nulls":47},"Hamid Shoaee"]
["2","01","01","11","02","  ",null,null,null,"LLRF Controls - Closed                                      ",{"$nulls":47},"Hamid Shoaee"]
["2","01","01","11","04","  ",null,null,null,"Laser Controls Design                                       ",{"$nulls":47},"Hamid Shoaee"]
["2","01","01","11","05","  ",null,null,null,"Laser Heater Controls Design                                ",{"$nulls":47},"Hamid Shoaee"]
["2","01","01","11","06","  ",null,null,null,"Timing Controls                                             ",{"$nulls":47},"Hamid Shoaee"]
["2","01","01","11","07","  ",null,null,null,"Vacuum Controls                                             ",{"$nulls":47},"Hamid Shoaee"]
["2","01","01","11","08","  ",null,null,null,"S/W & Controls Infrastructure                               ",{"$nulls":47},"Hamid Shoaee"]
["2","01","01","11","09","  ",null,null,null,"Power Supply Control                                        ",{"$nulls":47},"Hamid Shoaee"]
["2","01","01","11","10","  ",null,null,null,"MPS/PPS/BCS Controls                                        ",{"$nulls":47},"Hamid Shoaee"]
["2","01","01","11","11","  ",null,null,null,"Global Controls Commissioning                               ",{"$nulls":47},"Dave Schultz"]
["2","01","01","11","12","  ",null,null,null,"Global Controls Management - OPC                            ",{"$nulls":47},"Dave Schultz"]
["2","01","01","11","12","01",null,null,null,"                                                            ",{"$nulls":47},"Dave Schultz"]
["2","01","01","11","13","  ",null,null,null,"SLC Aware IOC                                               ",{"$nulls":47},"Hamid Shoaee"]
["2","01","01","11","14","  ",null,null,null,"Controls - Networking and Data Comm. OPC                    ",{"$nulls":47},"Hamid Shoaee"]
["2","01","01","11","15","  ",null,null,null,"Controls S/W Applications LOE                               ",{"$nulls":47},"Hamid Shoaee"]
["2","01","01","12","  ","  ",null,null,null,"E-Beam Systems Commissioning Management                     ",{"$nulls":47},"Dave Schultz"]
["2","01","01","13","  ","  ",null,null,null,"E-Beam Systems Physics Support                              ",{"$nulls":47},"Dave Schultz"]
["2","01","01","14","  ","  ",null,null,null,"Laser Commissioning Management                              ",{"$nulls":47},"Dave Schultz"]
["2","01","02","  ","  ","  ",null,null,null,"R&D Studies & Prototyping                                   ",{"$nulls":47},"Wendy Sisson"]
["2","01","02","01","  ","  ",null,null,null,"R&D Studies & Prototyping                                   ",{"$nulls":47},"Wendy Sisson"]
["2","01","03","  ","  ","  ",null,null,null,"Project Mgmnt, Planning and Admn - M&S (OPC)                ",{"$nulls":47},"Wendy Sisson"]
["2","01","03","01","  ","  ",null,null,null,"SLAC Project Office - General                               ",{"$nulls":47},"Wendy Sisson"]
["2","01","03","02","  ","  ",null,null,null,"SLAC Project Support                                        ",{"$nulls":47},"Wendy Sisson"]
["2","01","03","03","  ","  ",null,null,null,"Project Mgmnt, Planning and Admn - M&S (OPC)                ",{"$nulls":47},"Wendy Sisson"]
["2","01","03","05","  ","  ",null,null,null,"X-Ray Transport Physics                                     ",{"$nulls":47},"Wendy Sisson"]
["2","01","03","06","  ","  ",null,null,null,"X-Ray Endstation Physics                                    ",{"$nulls":47},"Wendy Sisson"]
["2","01","03","07","  ","  ",null,null,null,"Conventional Facilities Physics                             ",{"$nulls":47},"Wendy Sisson"]
["2","01","03","08","  ","  ",null,null,null,"Consulting Physics (Collaboration)                          ",{"$nulls":47},"Wendy Sisson"]
["2","01","03","09","  ","  ",null,null,null,"Consulting Physics (SLAC)                                   ",{"$nulls":47},"Wendy Sisson"]
["2","01","03","10","  ","  ",null,null,null,"Global Controls Physics Liaison                             ",{"$nulls":47},"Wendy Sisson"]
["2","01","03","11","  ","  ",null,null,null," Physics Commissioning Support - General                    ",{"$nulls":47},"Wendy Sisson"]
["2","02","  ","  ","  ","  ",null,null,null,"INJECTOR SYSTEM (OPC)                                       "]
["2","02","01","  ","  ","  ",null,null,null,"Injector System Management & Integration                    ",{"$nulls":47},"Jose Chan"]
["2","02","01","01","  ","  ",null,null,null,"Injector System Integration Effort / M&S                    ",{"$nulls":47},"Jose Chan"]
["2","02","01","02","  ","  ",null,null,null,"High level Application Software                             ",{"$nulls":47},"Jose Chan"]
["2","02","01","03","  ","  ",null,null,null,"Feedback Software                                           ",{"$nulls":47},"Jose Chan"]
["2","02","02","  ","  ","  ",null,null,null,"Injector Controls Subsystem                                 "]
["2","02","02","01","  ","  ",null,null,null,"Personnel Protection System (PPS) R&D                       ",{"$nulls":47},"Dave Schultz"]
["2","02","02","02","  ","  ",null,null,null,"Beam Containment Subsystem (BCS)                            ",{"$nulls":47},"Dave Schultz"]
["2","02","02","03","  ","  ",null,null,null,"Machine Protection Subsystem (MPS)                          ",{"$nulls":47},"Dave Schultz"]
["2","02","02","04","  ","  ",null,null,null,"Power Conv (beamline pwr supp) Spares                       ",{"$nulls":47},"Hamid Shoaee"]
["2","02","02","04","01","  ",null,null,null,"Power Supply Controls                                       ",{"$nulls":47},"Hamid Shoaee"]
["2","02","02","05","  ","  ",null,null,null,"LLRF Controls                                               ",{"$nulls":47},"Hamid Shoaee"]
["2","02","02","05","01","  ",null,null,null,"LLRF Controls                                               ",{"$nulls":47},"Dave Schultz"]
["2","02","02","06","  ","  ",null,null,null,"E-Beam Diagnostics Controls                                 ",{"$nulls":47},"Dave Schultz"]
["2","02","02","06","01","  ",null,null,null,"Controls - Wire Scanners                                    ",{"$nulls":47},"Dave Schultz"]
["2","02","02","06","02","  ",null,null,null,"Controls - BPM Processor Module                             ",{"$nulls":47},"Dave Schultz"]
["2","02","02","06","03","  ",null,null,null,"Controls - Toroids                                          ",{"$nulls":47},"Dave Schultz"]
["2","02","02","06","05","  ",null,null,null,"Controls - Profile Monitors                                 ",{"$nulls":47},"Dave Schultz"]
["2","02","02","06","06","  ",null,null,null,"Control - EO Diagnostic                                     ",{"$nulls":47},"Dave Schultz"]
["2","02","02","06","12","  ",null,null,null,"Controls - Movable Collimator                               ",{"$nulls":47},"Dave Schultz"]
["2","02","02","06","14","  ",null,null,null,"Controls - Faraday Cup                                      ",{"$nulls":47},"Dave Schultz"]
["2","02","02","06","15","  ",null,null,null,"Controls - Tune-Up Dump                                     ",{"$nulls":47},"Dave Schultz"]
["2","02","02","06","16","  ",null,null,null,"Cherenkov Commissioning Support                             ",{"$nulls":47},"Dave Schultz"]
["2","02","02","08","  ","  ",null,null,null,"Timing Controls                                             ",{"$nulls":47},"Dave Schultz"]
["2","02","02","09","  ","  ",null,null,null,"Vacuum Controls                                             ",{"$nulls":47},"Dave Schultz"]
["2","02","02","10","  ","  ",null,null,null,"Software & Controls Infrastructure                          ",{"$nulls":47},"Hamid Shoaee"]
["2","02","02","11","  ","  ",null,null,null,"EPICS VXI Control Modules                                   ",{"$nulls":47},"Hamid Shoaee"]
["2","02","02","12","  ","  ",null,null,null,"Laser Controls                                              ",{"$nulls":47},"Hamid Shoaee"]
["2","02","02","13","  ","  ",null,null,null,"Laser Heater Controls                                       ",{"$nulls":47},"Dave Schultz"]
["2","02","03","  ","  ","  ",null,null,null,"Injector Lasers                                             "]
["2","02","03","01","  ","  ",null,null,null,"Drive Laser Prototyping                                     ",{"$nulls":47},"Jose Chan"]
["2","02","03","02","  ","  ",null,null,null,"Drive Laser System                                          ",{"$nulls":47},"Jose Chan"]
["2","02","03","03","  ","  ",null,null,null,"Drive Laser Diagnostics                                     ",{"$nulls":47},"Dave Schultz"]
["2","02","03","04","  ","  ",null,null,null,"Timing Stability Monitoring                                 ",{"$nulls":47},"Jose Chan"]
["2","02","03","05","  ","  ",null,null,null,"Steering Stability Feedback & Msmts                         ",{"$nulls":47},"Jose Chan"]
["2","02","03","06","  ","  ",null,null,null,"Pre Amp Low Power Comp                                      ",{"$nulls":47},"Jose Chan"]
["2","02","03","07","  ","  ",null,null,null,"Transport to Tunnel & Relay Optics                          ",{"$nulls":47},"Jose Chan"]
["2","02","03","08","  ","  ",null,null,null,"UV Launch, Conditioning & Diagnostics                       ",{"$nulls":47},"Jose Chan"]
["2","02","03","09","  ","  ",null,null,null,"Load Lock Transport System                                  ",{"$nulls":47},"Jose Chan"]
["2","02","03","10","  ","  ",null,null,null,"Visible Optical Transport & Optics                          ",{"$nulls":47},"Jose Chan"]
["2","02","03","11","  ","  ",null,null,null,"LB Infrastructure & LB System Wide Items                    ",{"$nulls":47},"Jose Chan"]
["2","02","03","12","  ","  ",null,null,null,"Alignment Laser                                             ",{"$nulls":47},"Jose Chan"]
["2","02","03","13","  ","  ",null,null,null,"Light path to Streak Camera                                 ",{"$nulls":47},"Jose Chan"]
["2","02","03","14","  ","  ",null,null,null,"LSR HTR - Beam Conditioning Optics (Laser Bay)              ",{"$nulls":47},"Jose Chan"]
["2","02","03","15","  ","  ",null,null,null,"LSR HTR - Transport Optics (Bay to Tunnel)                  ",{"$nulls":47},"Jose Chan"]
["2","02","03","16","  ","  ",null,null,null,"LSR HTR - Photon Beam Diagnostics                           ",{"$nulls":47},"Jose Chan"]
["2","02","04","  ","  ","  ",null,null,null,"Injector RF Subsystem                                       ",{"$nulls":47},"Jose Chan"]
["2","02","04","01","  ","  ",null,null,null,"RF Gun & Load Lock                                          ",{"$nulls":47},"Jose Chan"]
["2","02","04","01","01","  ",null,null,null,"RF Gun                                                      ",{"$nulls":47},"Jose Chan"]
["2","02","04","01","02","  ",null,null,null,"RF Gun Supports                                             ",{"$nulls":47},"Jose Chan"]
["2","02","04","01","03","  ",null,null,null,"Gun Load Lock                                               ",{"$nulls":47},"Jose Chan"]
["2","02","04","01","04","  ",null,null,null,"Gun Load Lock Supports                                      ",{"$nulls":47},"Jose Chan"]
["2","02","04","01","05","  ",null,null,null,"Gun Solenoid                                                ",{"$nulls":47},"Jose Chan"]
["2","02","04","01","06","  ",null,null,null,"Gun Solenoid Supports                                       ",{"$nulls":47},"Jose Chan"]
["2","02","04","01","07","  ",null,null,null,"Gun RF Feed                                                 ",{"$nulls":47},"Jose Chan"]
["2","02","04","01","08","  ",null,null,null,"Gun RF Feed Supports                                        ",{"$nulls":47},"Jose Chan"]
["2","02","04","02","  ","  ",null,null,null,"Cathode Processing (CP) Station                             ",{"$nulls":47},"Jose Chan"]
["2","02","04","02","01","  ",null,null,null,"CP Cathode Assembly & Supports                              ",{"$nulls":47},"Jose Chan"]
["2","02","04","02","02","  ",null,null,null,"CP Load Lock                                                ",{"$nulls":47},"Jose Chan"]
["2","02","04","02","03","  ",null,null,null,"CP Load Lock Supports                                       ",{"$nulls":47},"Jose Chan"]
["2","02","04","02","04","  ",null,null,null,"CP Station                                                  ",{"$nulls":47},"Jose Chan"]
["2","02","04","02","05","  ",null,null,null,"Cathode Lab Infrastructure                                  ",{"$nulls":47},"Jose Chan"]
["2","02","04","03","  ","  ",null,null,null,"S-Band Low Level System                                     ",{"$nulls":47},"Jose Chan"]
["2","02","04","03","01","  ",null,null,null,"S-Band LL Controls Timing System                            ",{"$nulls":47},"Jose Chan"]
["2","02","04","04","  ","  ",null,null,null,"S-Band High Power System                                    ",{"$nulls":47},"Jose Chan"]
["2","02","04","05","  ","  ",null,null,null,"Injector RF Waveguide Subsystem                             ",{"$nulls":47},"Jose Chan"]
["2","02","04","05","01","  ",null,null,null,"RF Waveguides                                               ",{"$nulls":47},"Jose Chan"]
["2","02","04","05","02","  ",null,null,null,"RF Waveguide Supports                                       ",{"$nulls":47},"Jose Chan"]
["2","02","04","06","  ","  ",null,null,null,"Injector Linac Structures                                   ",{"$nulls":47},"Jose Chan"]
["2","02","04","06","01","  ",null,null,null,"L0-1 Structure Assembly                                     ",{"$nulls":47},"Jose Chan"]
["2","02","04","06","02","  ",null,null,null,"L0-2 Structure Assembly                                     ",{"$nulls":47},"Jose Chan"]
["2","02","04","06","03","  ",null,null,null,"Major Linac Support                                         ",{"$nulls":47},"Jose Chan"]
["2","02","04","06","04","  ",null,null,null,"GTL RF Phase Cavity                                         ",{"$nulls":47},"Jose Chan"]
["2","02","04","06","05","  ",null,null,null,"LTDL1 RF Kicker                                             ",{"$nulls":47},"Jose Chan"]
["2","02","05","  ","  ","  ",null,null,null,"Injector Magnets & Supports                                 ",{"$nulls":47},"Jose Chan"]
["2","02","05","01","  ","  ",null,null,null,"Injector Dipoles                                            ",{"$nulls":47},"Jose Chan"]
["2","02","05","01","01","  ",null,null,null,"DL1 B01 & B02 Dipoles                                       ",{"$nulls":47},"Jose Chan"]
["2","02","05","01","02","  ",null,null,null,"SAB Spectrometer Dipole                                     ",{"$nulls":47},"Jose Chan"]
["2","02","05","01","03","  ",null,null,null,"Chicane                                                     ",{"$nulls":47},"Jose Chan"]
["2","02","05","02","  ","  ",null,null,null,"Injector Quadrupoles                                        ",{"$nulls":47},"Jose Chan"]
["2","02","05","02","01","  ",null,null,null,"L0-1TL0-2 Quadrupoles ( )                                   ",{"$nulls":47},"Jose Chan"]
["2","02","05","02","02","  ",null,null,null,"LTDL1 Quadrupoles ( )                                       ",{"$nulls":47},"Jose Chan"]
["2","02","05","02","03","  ",null,null,null,"DL1 QB Quadrupole                                           ",{"$nulls":47},"Jose Chan"]
["2","02","05","02","04","  ",null,null,null,"DL1TL Quadrupoles ( )                                       ",{"$nulls":47},"Jose Chan"]
["2","02","05","02","05","  ",null,null,null,"SAB Quadrupoles ( )                                         ",{"$nulls":47},"Jose Chan"]
["2","02","05","03","  ","  ",null,null,null,"Injector Steering Coils                                     ",{"$nulls":47},"Jose Chan"]
["2","02","05","03","01","  ",null,null,null,"GTL Steering Coils ( )X-Y (SC1)                             ",{"$nulls":47},"Jose Chan"]
["2","02","05","03","02","  ",null,null,null,"L0-1TL0-2 Linac Steering Coils ( )                          ",{"$nulls":47},"Jose Chan"]
["2","02","05","03","03","  ",null,null,null,"LTDL1 Steering Coils ( )X-Y                                 ",{"$nulls":47},"Jose Chan"]
["2","02","05","03","04","  ",null,null,null,"DL1TL Steering Coils ( X-Y Assys)                           ",{"$nulls":47},"Jose Chan"]
["2","02","05","03","05","  ",null,null,null,"SAB Steering Coils ( )                                      ",{"$nulls":47},"Jose Chan"]
["2","02","05","04","  ","  ",null,null,null,"Linac Solenoid & Supports                                   ",{"$nulls":47},"Jose Chan"]
["2","02","05","05","  ","  ",null,null,null,"Injector Laser Heater Subsystem                             ",{"$nulls":47},"Jose Chan"]
["2","02","05","05","01","  ",null,null,null,"System Design & Optimization                                ",{"$nulls":47},"Jose Chan"]
["2","02","05","05","02","  ",null,null,null,"Undulator                                                   ",{"$nulls":47},"Jose Chan"]
["2","02","06","  ","  ","  ",null,null,null,"Injector Vacuum & Supports                                  ",{"$nulls":47},"Jose Chan"]
["2","02","06","01","  ","  ",null,null,null,"GTL Vacuum Components                                       ",{"$nulls":47},"Jose Chan"]
["2","02","06","02","  ","  ",null,null,null,"GTL Supports                                                ",{"$nulls":47},"Jose Chan"]
["2","02","06","03","  ","  ",null,null,null,"GTL Pumping & Optic Chamber                                 ",{"$nulls":47},"Jose Chan"]
["2","02","06","04","  ","  ",null,null,null,"L0-1TL0-2 Vacuum Components                                 ",{"$nulls":47},"Jose Chan"]
["2","02","06","05","  ","  ",null,null,null,"L0-1TL0-2 Major tube support structure                      ",{"$nulls":47},"Jose Chan"]
["2","02","06","06","  ","  ",null,null,null,"LTDL1 Minor Tube Supports                                   ",{"$nulls":47},"Jose Chan"]
["2","02","06","07","  ","  ",null,null,null,"DL1 Supports                                                ",{"$nulls":47},"Jose Chan"]
["2","02","06","08","  ","  ",null,null,null,"DL1 Vacuum Chamber                                          ",{"$nulls":47},"Jose Chan"]
["2","02","06","09","  ","  ",null,null,null,"DL1TL Vacuum Components                                     ",{"$nulls":47},"Jose Chan"]
["2","02","06","10","  ","  ",null,null,null,"SAB Vacuum Chamber and Components                           ",{"$nulls":47},"Jose Chan"]
["2","02","06","11","  ","  ",null,null,null,"SAB Supports                                                ",{"$nulls":47},"Jose Chan"]
["2","02","07","  ","  ","  ",null,null,null,"Injector Diagnostics                                        ",{"$nulls":47},"Jose Chan"]
["2","02","07","01","  ","  ",null,null,null,"Injector Beam Position Monitors                             ",{"$nulls":47},"Jose Chan"]
["2","02","07","01","01","  ",null,null,null,"GTL BPMs ( )                                                ",{"$nulls":47},"Jose Chan"]
["2","02","07","01","02","  ",null,null,null,"Gun Spectrometer (GS) Assembly                              ",{"$nulls":47},"Jose Chan"]
["2","02","07","01","03","  ",null,null,null,"L0-1TL0-2 BPMs ( )                                          ",{"$nulls":47},"Jose Chan"]
["2","02","07","01","04","  ",null,null,null,"LTDL1 BPMs ( )                                              ",{"$nulls":47},"Jose Chan"]
["2","02","07","01","05","  ",null,null,null,"DL1TL BPMs ( )                                              ",{"$nulls":47},"Jose Chan"]
["2","02","07","01","06","  ",null,null,null,"SAB BPM ( )                                                 ",{"$nulls":47},"Jose Chan"]
["2","02","07","02","  ","  ",null,null,null,"Injector Current Monitors                                   ",{"$nulls":47},"Jose Chan"]
["2","02","07","02","01","  ",null,null,null,"GTL Current Monitors ( )                                    ",{"$nulls":47},"Jose Chan"]
["2","02","07","02","02","  ",null,null,null,"L0-1TL0-2 Current Monitor ( )                               ",{"$nulls":47},"Jose Chan"]
["2","02","07","02","03","  ",null,null,null,"LTDL1 Current Monitors ( )                                  ",{"$nulls":47},"Jose Chan"]
["2","02","07","02","04","  ",null,null,null,"DL1TL Current Monitor ( )                                   ",{"$nulls":47},"Jose Chan"]
["2","02","07","02","05","  ",null,null,null,"SAB Current Monitor ( )                                     ",{"$nulls":47},"Jose Chan"]
["2","02","07","03","  ","  ",null,null,null,"Injector Bunch Length Monitors                              ",{"$nulls":47},"Jose Chan"]
["2","02","07","03","01","  ",null,null,null,"GTL E/O (EO1)                                               ",{"$nulls":47},"Jose Chan"]
["2","02","07","03","02","  ",null,null,null,"LTDL1 E/O EO2                                               ",{"$nulls":47},"Jose Chan"]
["2","02","07","03","03","  ",null,null,null,"DL1TL EO3                                                   ",{"$nulls":47},"Jose Chan"]
["2","02","07","04","  ","  ",null,null,null,"Injector Profile Monitors                                   ",{"$nulls":47},"Jose Chan"]
["2","02","07","04","01","  ",null,null,null,"GTL Faraday Cup/YAG1                                        ",{"$nulls":47},"Jose Chan"]
["2","02","07","04","02","  ",null,null,null,"GTL YAG ( )                                                 ",{"$nulls":47},"Jose Chan"]
["2","02","07","04","03","  ",null,null,null,"L0-1TL0-2 OTR/YAG ( )                                       ",{"$nulls":47},"Jose Chan"]
["2","02","07","04","04","  ",null,null,null,"LTDL1 OTR(5)/YAG ( )                                        ",{"$nulls":47},"Jose Chan"]
["2","02","07","04","05","  ",null,null,null,"DL1 OTR                                                     ",{"$nulls":47},"Jose Chan"]
["2","02","07","04","06","  ",null,null,null,"DL1TL OTR                                                   ",{"$nulls":47},"Jose Chan"]
["2","02","07","04","07","  ",null,null,null,"SAB YAG                                                     ",{"$nulls":47},"Jose Chan"]
["2","02","07","04","08","  ",null,null,null,"SAB Beam Dump and Shielding                                 ",{"$nulls":47},"Jose Chan"]
["2","02","07","05","  ","  ",null,null,null,"Injector Wire Scanners                                      ",{"$nulls":47},"Jose Chan"]
["2","02","07","05","01","  ",null,null,null,"LTDL1 Wire Scanners ( )                                     ",{"$nulls":47},"Jose Chan"]
["2","02","07","05","02","  ",null,null,null,"DL1 Wire Scanner                                            ",{"$nulls":47},"Jose Chan"]
["2","02","07","06","  ","  ",null,null,null,"LSR HTR - Electron Beam Diagnostics                         ",{"$nulls":47},"Jose Chan"]
["2","02","07","07","  ","  ",null,null,null,"PPS Stopper                                                 ",{"$nulls":47},"Jose Chan"]
["2","02","08","  ","  ","  ",null,null,null,"Injector System Emittance Enhancement                       ",{"$nulls":47},"Jose Chan"]
["2","02","08","01","  ","  ",null,null,null,"Heater Integration                                          ",{"$nulls":47},"Jose Chan"]
["2","02","08","02","  ","  ",null,null,null,"Heater Laser & Optics                                       ",{"$nulls":47},"Jose Chan"]
["2","02","08","03","  ","  ",null,null,null,"Heater Magnets                                              ",{"$nulls":47},"Jose Chan"]
["2","02","08","03","01","  ",null,null,null,"Heater Dipoles                                              ",{"$nulls":47},"Jose Chan"]
["2","02","08","03","02","  ",null,null,null,"Heater Undulator                                            ",{"$nulls":47},"Jose Chan"]
["2","02","08","04","  ","  ",null,null,null,"Heater Vacuum                                               ",{"$nulls":47},"Jose Chan"]
["2","02","08","05","  ","  ",null,null,null,"Heater Diagnostics                                          ",{"$nulls":47},"Jose Chan"]
["2","02","08","06","  ","  ",null,null,null,"Heater Install & Align                                      ",{"$nulls":47},"Jose Chan"]
["2","02","17","  ","  ","  ",null,null,null,"Injector System Commissioning                               ",{"$nulls":47},"Dave Schultz"]
["2","02","17","01","  ","  ",null,null,null,"Controls Commissioning                                      ",{"$nulls":47},"Dave Schultz"]
["2","02","17","02","  ","  ",null,null,null,"Drive Laser Commissioning                                   ",{"$nulls":47},"Dave Schultz"]
["2","02","17","10","  ","  ",null,null,null,"Injector System Commissioning                               ",{"$nulls":47},"Dave Schultz"]
["2","02","17","11","  ","  ",null,null,null,"Injector Engr, Design, Maintenance Support                  ",{"$nulls":47},"Dave Schultz"]
["2","03","  ","  ","  ","  ",null,null,null,"LINAC SYSTEM (OPC)                                          "]
["2","03","01","  ","  ","  ",null,null,null,"Linac System Mgmt & Integration                             ",{"$nulls":47},"Jose Chan"]
["2","03","01","01","  ","  ",null,null,null,"Linac System Mgmt & Integration                             ",{"$nulls":47},"Dave Schultz"]
["2","03","01","02","  ","  ",null,null,null,"Linac Controls Integration                                  ",{"$nulls":47},"Jose Chan"]
["2","03","01","03","  ","  ",null,null,null,"Travel                                                      ",{"$nulls":47},"Jose Chan"]
["2","03","01","04","  ","  ",null,null,null,"Linac Management                                            ",{"$nulls":47},"Jose Chan"]
["2","03","02","  ","  ","  ",null,null,null,"Linac Controls & Power Conversion Subsystem                 ",{"$nulls":47},"Hamid Shoaee"]
["2","03","02","01","  ","  ",null,null,null,"Personnel Protection System (PPS)                           ",{"$nulls":47},"Dave Schultz"]
["2","03","02","02","  ","  ",null,null,null,"Beam Containment System (BCS)                               ",{"$nulls":47},"Dave Schultz"]
["2","03","02","03","  ","  ",null,null,null,"Machine Protection System (MPS)                             ",{"$nulls":47},"Dave Schultz"]
["2","03","02","04","  ","  ",null,null,null,"Power Conversion                                            ",{"$nulls":47},"Hamid Shoaee"]
["2","03","02","04","01","  ",null,null,null,"Spare Power Supply (Dipole Type)                            ",{"$nulls":47},"Hamid Shoaee"]
["2","03","02","04","02","  ",null,null,null,"Spare Power Supply (Quad Type)                              ",{"$nulls":47},"Hamid Shoaee"]
["2","03","02","04","03","  ",null,null,null,"Spare Power Supply (Trim Type)                              ",{"$nulls":47},"Hamid Shoaee"]
["2","03","02","04","04","  ",null,null,null,"Controls & Power Supply - Spare Misc Hdwr                   ",{"$nulls":47},"Hamid Shoaee"]
["2","03","02","05","  ","  ",null,null,null,"Controls - LLRF                                             ",{"$nulls":47},"Dave Schultz"]
["2","03","02","06","  ","  ",null,null,null,"Controls - E-Beam Diagnostic                                ",{"$nulls":47},"Dave Schultz"]
["2","03","02","06","01","  ",null,null,null,"Controls - Wire Scanners                                    ",{"$nulls":47},"Dave Schultz"]
["2","03","02","06","02","  ",null,null,null,"Controls - BPMs                                             ",{"$nulls":47},"Dave Schultz"]
["2","03","02","06","03","  ",null,null,null,"Controls - Toroids                                          ",{"$nulls":47},"Dave Schultz"]
["2","03","02","06","04","  ",null,null,null,"Controls - Stoppers Commissioning                           ",{"$nulls":47},"Dave Schultz"]
["2","03","02","06","05","  ",null,null,null,"Controls - Profile Monitors                                 ",{"$nulls":47},"Dave Schultz"]
["2","03","02","06","07","  ",null,null,null,"Controls - BLM                                              ",{"$nulls":47},"Dave Schultz"]
["2","03","02","06","09","  ",null,null,null,"Controls - Single Beam Dump                                 ",{"$nulls":47},"Dave Schultz"]
["2","03","02","06","10","  ",null,null,null,"Controls - E-Beam Dump                                      ",{"$nulls":47},"Dave Schultz"]
["2","03","02","06","12","  ",null,null,null,"Controls - Collimators                                      ",{"$nulls":47},"Dave Schultz"]
["2","03","02","07","  ","  ",null,null,null,"Controls - Laser                                            ",{"$nulls":47},"Dave Schultz"]
["2","03","02","08","  ","  ",null,null,null,"Controls - Timing                                           ",{"$nulls":47},"Dave Schultz"]
["2","03","02","09","  ","  ",null,null,null,"Controls - Vacuum                                           ",{"$nulls":47},"Dave Schultz"]
["2","03","02","10","  ","  ",null,null,null,"Software & Controls Infrastructure                          ",{"$nulls":47},"Hamid Shoaee"]
["2","03","03","  ","  ","  ",null,null,null,"Linac Magnets & Supports                                    ",{"$nulls":47},"Jose Chan"]
["2","03","03","01","  ","  ",null,null,null,"Bend Magnet (BX1_BC1)                                       ",{"$nulls":47},"Jose Chan"]
["2","03","03","02","  ","  ",null,null,null,"Bend Magnet (BX3_LTU)                                       ",{"$nulls":47},"Jose Chan"]
["2","03","03","03","  ","  ",null,null,null,"Bend Magnet (BX2_BC2)                                       ",{"$nulls":47},"Jose Chan"]
["2","03","03","04","  ","  ",null,null,null,"Bend Magnet (BY_LTU)                                        ",{"$nulls":47},"Jose Chan"]
["2","03","03","05","  ","  ",null,null,null,"Quad Magnet (Quad_LTU)                                      ",{"$nulls":47},"Jose Chan"]
["2","03","03","07","  ","  ",null,null,null,"Quad Magnet (QE)                                            ",{"$nulls":47},"Jose Chan"]
["2","03","03","08","  ","  ",null,null,null,"Corrector Magnet (Type 4)                                   ",{"$nulls":47},"Jose Chan"]
["2","03","03","09","  ","  ",null,null,null,"Bend Magnet (BYD_LTU)                                       ",{"$nulls":47},"Jose Chan"]
["2","03","03","10","  ","  ",null,null,null,"Quad Magnet (QA)                                            ",{"$nulls":47},"Jose Chan"]
["2","03","03","11","  ","  ",null,null,null,"Bend Magnet (BYPM_LTU)                                      ",{"$nulls":47},"Jose Chan"]
["2","03","03","12","  ","  ",null,null,null,"Bend Magnet (BYKIK_LTU)                                     ",{"$nulls":47},"Jose Chan"]
["2","03","03","13","  ","  ",null,null,null,"Bend Magnet (BYW_LTU)                                       ",{"$nulls":47},"Jose Chan"]
["2","03","04","  ","  ","  ",null,null,null,"Linac Vacuum Subsystem                                      ",{"$nulls":47},"Jose Chan"]
["2","03","04","01","  ","  ",null,null,null,"Linac Vacuum Subsystem Operations Equip                     ",{"$nulls":47},"Jose Chan"]
["2","03","04","02","  ","  ",null,null,null,"Linac Beamline Vacuum System                                ",{"$nulls":47},"Jose Chan"]
["2","03","04","03","  ","  ",null,null,null,"BC1 Vacuum System                                           ",{"$nulls":47},"Jose Chan"]
["2","03","04","04","  ","  ",null,null,null,"BC2 Vacuum System                                           ",{"$nulls":47},"Jose Chan"]
["2","03","04","05","  ","  ",null,null,null,"Linac to Undulator (LTU) Vacuum System                      ",{"$nulls":47},"Jose Chan"]
["2","03","04","06","  ","  ",null,null,null,"Dumpline Vacuum System                                      ",{"$nulls":47},"Jose Chan"]
["2","03","04","07","  ","  ",null,null,null,"Vacuum Undulator Interface                                  ",{"$nulls":47},"Jose Chan"]
["2","03","04","07","01","  ",null,null,null,"Entrance Assembly Section                                   ",{"$nulls":47},"Jose Chan"]
["2","03","04","07","02","  ",null,null,null,"Exit Assembly Section                                       ",{"$nulls":47},"Jose Chan"]
["2","03","05","  ","  ","  ",null,null,null,"Linac Electron Diagnostics                                  ",{"$nulls":47},"Jose Chan"]
["2","03","05","01","  ","  ",null,null,null,"Wire Scanners                                               ",{"$nulls":47},"Jose Chan"]
["2","03","05","02","  ","  ",null,null,null,"Beam Position Monitors                                      ",{"$nulls":47},"Jose Chan"]
["2","03","05","03","  ","  ",null,null,null,"Toroids Beam Charge                                         ",{"$nulls":47},"Jose Chan"]
["2","03","05","04","  ","  ",null,null,null,"Stoppers Tune Up Dump                                       ",{"$nulls":47},"Jose Chan"]
["2","03","05","05","  ","  ",null,null,null,"Profile Monitors                                            ",{"$nulls":47},"Jose Chan"]
["2","03","05","06","  ","  ",null,null,null,"E/O Bunch Length Monitors                                   ",{"$nulls":47},"Jose Chan"]
["2","03","05","07","  ","  ",null,null,null,"Bunch Length Monitors                                       ",{"$nulls":47},"Jose Chan"]
["2","03","05","08","  ","  ",null,null,null,"Beam Loss Monitors                                          ",{"$nulls":47},"Jose Chan"]
["2","03","05","09","  ","  ",null,null,null,"Single Beam Dump                                            ",{"$nulls":47},"Jose Chan"]
["2","03","05","10","  ","  ",null,null,null,"Electron Safety Beam Dump                                   ",{"$nulls":47},"Jose Chan"]
["2","03","05","11","  ","  ",null,null,null,"Protection Collimators                                      ",{"$nulls":47},"Jose Chan"]
["2","03","05","12","  ","  ",null,null,null,"Movable Collimators                                         ",{"$nulls":47},"Jose Chan"]
["2","03","05","13","  ","  ",null,null,null,"Safety Dump                                                 ",{"$nulls":47},"Jose Chan"]
["2","03","05","14","  ","  ",null,null,null,"Charge Monitor (Entrance/Exit Assebmly)                     ",{"$nulls":47},"Jose Chan"]
["2","03","06","  ","  ","  ",null,null,null,"Linac RF Subsystem                                          ",{"$nulls":47},"Jose Chan"]
["2","03","06","02","  ","  ",null,null,null,"S-Band High Power System                                    ",{"$nulls":47},"Jose Chan"]
["2","03","06","03","  ","  ",null,null,null,"S-Band Structures                                           ",{"$nulls":47},"Jose Chan"]
["2","03","06","04","  ","  ",null,null,null,"X-Band Low Level System                                     ",{"$nulls":47},"Jose Chan"]
["2","03","06","05","  ","  ",null,null,null,"X-Band High Power System                                    ",{"$nulls":47},"Jose Chan"]
["2","03","06","06","  ","  ",null,null,null,"X-Band Structures                                           ",{"$nulls":47},"Jose Chan"]
["2","03","06","07","  ","  ",null,null,null,"RF Distribution System                                      ",{"$nulls":47},"Jose Chan"]
["2","03","06","07","01","  ",null,null,null,"Modulator                                                   ",{"$nulls":47},"Jose Chan"]
["2","03","06","07","02","  ",null,null,null,"Solid State Sub Booster                                     ",{"$nulls":47},"Jose Chan"]
["2","03","06","07","05","  ",null,null,null,"Bunch Length Electronics                                    ",{"$nulls":47},"Jose Chan"]
["2","03","06","07","07","  ",null,null,null,"RF Distribution L2 & L3                                     ",{"$nulls":47},"Jose Chan"]
["2","03","06","07","08","  ",null,null,null,"RF Fiber Optics Electronics                                 ",{"$nulls":47},"Jose Chan"]
["2","03","07","  ","  ","  ",null,null,null,"Linac System Commissioning                                  ",{"$nulls":47},"Dave Schultz"]
["2","03","07","10","  ","  ",null,null,null,"L2/BC2/L3 Commissioning                                     ",{"$nulls":47},"Dave Schultz"]
["2","04","  ","  ","  ","  ",null,null,null,"UNDULATOR SYSTEM (OPC)                                      "]
["2","04","01","  ","  ","  ",null,null,null,"Undulator System Management & Integration                   ",{"$nulls":47},"Geoff Pile"]
["2","04","01","01","  ","  ",null,null,null,"Undulator System Mgmt & Integration                         ",{"$nulls":47},"Geoff Pile"]
["2","04","02","  ","  ","  ",null,null,null,"Controls                                                    ",{"$nulls":47},"Hamid Shoaee"]
["2","04","02","01","  ","  ",null,null,null,"Controls Management and Integration                         ",{"$nulls":47},"Hamid Shoaee"]
["2","04","02","04","  ","  ",null,null,null,"Video                                                       ",{"$nulls":47},"Hamid Shoaee"]
["2","04","02","07","  ","  ",null,null,null,"Machine Protection                                          ",{"$nulls":47},"Hamid Shoaee"]
["2","04","03","  ","  ","  ",null,null,null,"Undulator Magnet & Support                                  ",{"$nulls":47},"Geoff Pile"]
["2","04","03","01","  ","  ",null,null,null,"Undulator Magnets & Support-Mgmt & Integration              ",{"$nulls":47},"Geoff Pile"]
["2","04","03","02","  ","  ",null,null,null,"First Prototype Undulator & Mfg Plan                        ",{"$nulls":47},"Geoff Pile"]
["2","04","03","03","  ","  ",null,null,null,"1st Article Undulators & Long Lead Procurements             ",{"$nulls":47},"Geoff Pile"]
["2","04","03","04","  ","  ",null,null,null,"Production Undulator                                        ",{"$nulls":47},"Geoff Pile"]
["2","04","03","05","  ","  ",null,null,null,"Focusing Magnets                                            ",{"$nulls":47},"Geoff Pile"]
["2","04","03","06","  ","  ",null,null,null,"Undulator Magnetic Measurement Facility (SLAC)              ",{"$nulls":47},"Rod Pope"]
["2","04","03","08","  ","  ",null,null,null,"Fixed Supports                                              ",{"$nulls":47},"Geoff Pile"]
["2","04","04","  ","  ","  ",null,null,null,"Vacuum System                                               ",{"$nulls":47},"Geoff Pile"]
["2","04","04","02","  ","  ",null,null,null,"Undulator Vacuum Chamber Assembly                           ",{"$nulls":47},"Geoff Pile"]
["2","04","04","02","01","  ",null,null,null,"Surface Roughness Minimization                              ",{"$nulls":47},"Geoff Pile"]
["2","04","04","02","03","  ",null,null,null,"Materials Study for AC Conductivity                         ",{"$nulls":47},"Geoff Pile"]
["2","04","04","03","  ","  ",null,null,null,"Beam-line Bellows Module Assembly                           ",{"$nulls":47},"Geoff Pile"]
["2","04","04","04","  ","  ",null,null,null,"Single Undulator Test (SUV) Vacuum                          ",{"$nulls":47},"Geoff Pile"]
["2","04","04","05","  ","  ",null,null,null,"Short Diagnostic Break (SDB) Assembly                       ",{"$nulls":47},"Geoff Pile"]
["2","04","04","06","  ","  ",null,null,null,"Long Diagnostic Break (LDB) Assembly                        ",{"$nulls":47},"Geoff Pile"]
["2","04","04","07","  ","  ",null,null,null,"Entrance Section Assembly                                   ",{"$nulls":47},"Geoff Pile"]
["2","04","04","08","  ","  ",null,null,null,"Exit Section Assembly                                       ",{"$nulls":47},"Geoff Pile"]
["2","04","04","09","  ","  ",null,null,null,"Baking System                                               ",{"$nulls":47},"Geoff Pile"]
["2","04","05","  ","  ","  ",null,null,null,"Undulator System Diagnostics [OPC]                          ",{"$nulls":47},"Geoff Pile"]
["2","04","05","02","  ","  ",null,null,null,"Undulator Line Diagnostics                                  ",{"$nulls":47},"Geoff Pile"]
["2","04","05","03","  ","  ",null,null,null,"High-Power X-Ray and Profile Diagnostics (HPD)              ",{"$nulls":47},"Geoff Pile"]
["2","04","05","04","  ","  ",null,null,null,"End-of-Undulator(EOU) X-ray and Profile diagnost            ",{"$nulls":47},"Geoff Pile"]
["2","04","05","05","  ","  ",null,null,null,"RFBPM                                                       ",{"$nulls":47},"Geoff Pile"]
["2","04","05","06","  ","  ",null,null,null,"Beam Finder Wire                                            ",{"$nulls":47},"Geoff Pile"]
["2","04","05","07","  ","  ",null,null,null,"Charge Monitor (CM)                                         ",{"$nulls":47},"Geoff Pile"]
["2","04","05","08","  ","  ",null,null,null,"Beam Loss Monitoring                                        ",{"$nulls":47},"Geoff Pile"]
["2","04","05","09","  ","  ",null,null,null,"Radiation Detection Monitor (RDM)                           ",{"$nulls":47},"Geoff Pile"]
["2","04","05","10","  ","  ",null,null,null,"Single Undulator Test (SUT) Diagnostics                     ",{"$nulls":47},"Geoff Pile"]
["2","04","06","  ","  ","  ",null,null,null,"LTU/Undulator/Dump Commissioning                            ",{"$nulls":47},"Dave Schultz"]
["2","04","06","01","  ","  ",null,null,null,"LTU/Undulator/Dump Commissioning                            ",{"$nulls":47},"Dave Schultz"]
["2","05","  ","  ","  ","  ",null,null,null,"X-RAY TRANSPORT & DIAGNOSTICS SYSTEMS (OPC)                 "]
["2","05","01","  ","  ","  ",null,null,null,"System Management & Integration                             ",{"$nulls":47},"Donn McMahon"]
["2","05","01","01","  ","  ",null,null,null,"Management                                                  ",{"$nulls":47},"Donn McMahon"]
["2","05","02","  ","  ","  ",null,null,null,"Controls                                                    ",{"$nulls":47},"Gunter Haller"]
["2","05","02","01","  ","  ",null,null,null,"Controls - EPICS                                            ",{"$nulls":47},"Gunter Haller"]
["2","05","02","02","  ","  ",null,null,null,"Controls - System                                           ",{"$nulls":47},"Gunter Haller"]
["2","05","03","  ","  ","  ",null,null,null,"Mechanical & Vacuum Subsystem                               ",{"$nulls":47},"Donn McMahon"]
["2","05","03","01","  ","  ",null,null,null,"Vacuum Systems Engineering                                  ",{"$nulls":47},"Donn McMahon"]
["2","05","03","02","  ","  ",null,null,null,"Mech/Vac Front End                                          ",{"$nulls":47},"Donn McMahon"]
["2","05","03","03","  ","  ",null,null,null,"Mech/Vac Near Hall                                          ",{"$nulls":47},"Donn McMahon"]
["2","05","03","04","  ","  ",null,null,null,"Mech/Vac Tunnel                                             ",{"$nulls":47},"Donn McMahon"]
["2","05","03","05","  ","  ",null,null,null,"Mech/Vac Far Hall                                           ",{"$nulls":47},"Donn McMahon"]
["2","05","04","  ","  ","  ",null,null,null,"Optical Subsystem                                           ",{"$nulls":47},"Donn McMahon"]
["2","05","04","01","  ","  ",null,null,null,"Optical Systems Engineering                                 ",{"$nulls":47},"Donn McMahon"]
["2","05","04","02","  ","  ",null,null,null,"Facility Optics                                             ",{"$nulls":47},"Donn McMahon"]
["2","05","04","03","  ","  ",null,null,null,"End Station Optics                                          ",{"$nulls":47},"Donn McMahon"]
["2","05","04","04","  ","  ",null,null,null,"Crystals & Gratings                                         ",{"$nulls":47},"Donn McMahon"]
["2","05","05","  ","  ","  ",null,null,null,"Diagnostics Subsystem                                       ",{"$nulls":47},"Donn McMahon"]
["2","05","05","01","  ","  ",null,null,null,"Diagnostic Systems Engineering                              ",{"$nulls":47},"Donn McMahon"]
["2","05","05","02","  ","  ",null,null,null,"Modeling & Simulation                                       ",{"$nulls":47},"Donn McMahon"]
["2","05","05","03","  ","  ",null,null,null,"Facility Diagnostics                                        ",{"$nulls":47},"Donn McMahon"]
["2","05","05","04","  ","  ",null,null,null,"Commissioning Diagnostics                                   ",{"$nulls":47},"Donn McMahon"]
["2","05","06","  ","  ","  ",null,null,null,"X-Ray Transport & Diag. System Commissioning                "]
["2","05","06","01","  ","  ",null,null,null,"X-Ray Transport & Diag. System Commissioning                "]
["2","06","  ","  ","  ","  ",null,null,null,"X-RAY END STATION SYSTEMS (OPC)                             "]
["2","06","01","  ","  ","  ",null,null,null,"XE System Mgmt & Integration                                ",{"$nulls":47},"Stefan Moeller"]
["2","06","01","01","  ","  ",null,null,null,"Management                                                  ",{"$nulls":47},"Stefan Moeller"]
["2","06","02","  ","  ","  ",null,null,null,"Controls Subsystem                                          ",{"$nulls":47},"Gunter Haller"]
["2","06","02","01","  ","  ",null,null,null,"Cabling                                                     ",{"$nulls":47},"Gunter Haller"]
["2","06","02","02","  ","  ",null,null,null,"Network                                                     ",{"$nulls":47},"Gunter Haller"]
["2","06","02","03","  ","  ",null,null,null,"PC Support                                                  ",{"$nulls":47},"Gunter Haller"]
["2","06","02","04","  ","  ",null,null,null,"Beamline Controls                                           ",{"$nulls":47},"Gunter Haller"]
["2","06","02","05","  ","  ",null,null,null,"X-Ray PPS                                                   ",{"$nulls":47},"Gunter Haller"]
["2","06","02","06","  ","  ",null,null,null,"X-Ray MPS                                                   ",{"$nulls":47},"Gunter Haller"]
["2","06","02","07","  ","  ",null,null,null,"Laser PPS                                                   ",{"$nulls":47},"Gunter Haller"]
["2","06","02","08","  ","  ",null,null,null,"R&D: 2D X-Ray Detector Controls                             ",{"$nulls":47},"Gunter Haller"]
["2","06","03","  ","  ","  ",null,null,null,"Commissioning                                               "]
["2","06","03","01","  ","  ",null,null,null,"Commissioning - Controls                                    "]
["2","06","03","02","  ","  ",null,null,null,"Commissioning - XES Laser                                   "]
["2","06","03","03","  ","  ",null,null,null,"Commissioning - AMO Experiment                              "]
["2","06","03","05","  ","  ",null,null,null,"Commissioning - 2D X-Ray Detector                           "]
["2","06","04","  ","  ","  ",null,null,null,"Spares                                                      ",{"$nulls":47},"Stefan Moeller"]
["2","06","04","01","  ","  ",null,null,null,"Spares - PPS Stoppers                                       ",{"$nulls":47},"Stefan Moeller"]
["2","06","04","02","  ","  ",null,null,null,"Spares -                                                    ",{"$nulls":47},"Stefan Moeller"]
["2","06","04","03","  ","  ",null,null,null,"Spares -                                                    ",{"$nulls":47},"Stefan Moeller"]
["2","06","04","04","  ","  ",null,null,null,"Spares -                                                    ",{"$nulls":47},"Stefan Moeller"]
["2","06","04","05","  ","  ",null,null,null,"Spares -                                                    ",{"$nulls":47},"Stefan Moeller"]
["2","06","05","  ","  ","  ",null,null,null,"X-Ray Detectors                                             ",{"$nulls":47},"Stefan Moeller"]
["2","06","05","01","  ","  ",null,null,null,"Beam Imaging                                                ",{"$nulls":47},"Stefan Moeller"]
["2","06","05","02","  ","  ",null,null,null,"2-D X-Ray Detector                                          ",{"$nulls":47},"Stefan Moeller"]
["2","06","05","02","01","  ",null,null,null,"Proto 2 ASIC                                                ",{"$nulls":47},"Stefan Moeller"]
["2","06","05","02","02","  ",null,null,null,"Proto 3 ASIC                                                ",{"$nulls":47},"Stefan Moeller"]
["2","06","05","02","03","  ",null,null,null,"Full Lot Prototype                                          ",{"$nulls":47},"Stefan Moeller"]
["2","06","05","02","04","  ",null,null,null,"500px Detector                                              ",{"$nulls":47},"Stefan Moeller"]
["2","06","05","02","05","  ",null,null,null,"2D X-Ray Detector Commissioning                             ",{"$nulls":47},"Stefan Moeller"]
["2","06","05","03","  ","  ",null,null,null,"Beam Intensity                                              ",{"$nulls":47},"Stefan Moeller"]
["2","06","05","04","  ","  ",null,null,null,"Streak Camera                                               ",{"$nulls":47},"Stefan Moeller"]
["2","06","07","  ","  ","  ",null,null,null,"Atomic Physics                                              ",{"$nulls":47},"Stefan Moeller"]
["2","06","07","01","  ","  ",null,null,null,"Atomic Physics Samples                                      ",{"$nulls":47},"Stefan Moeller"]
["2","06","07","02","  ","  ",null,null,null,"Atomic Physics Diagnostics                                  ",{"$nulls":47},"Stefan Moeller"]
["2","06","07","03","  ","  ",null,null,null,"Atomic Physics Data Analysis                                ",{"$nulls":47},"Stefan Moeller"]
["2","06","07","04","  ","  ",null,null,null,"Atomic Physics Detectors                                    ",{"$nulls":47},"Stefan Moeller"]
["2","09","  ","  ","  ","  ",null,null,null,"CONVENTIONAL FACILITIES (OPC)                               "]
["2","09","01","  ","  ","  ",null,null,null,"MANAGEMENT INTEGRATION                                      ",{"$nulls":47},"David Saenz"]
["2","09","03","  ","  ","  ",null,null,null,"RSY - CLOC Commissioning                                    ",{"$nulls":47},"David Saenz"]
["2","09","03","05","  ","  ",null,null,null,"RSY-CLOC Commissioning                                      ",{"$nulls":47},"David Saenz"]

{"sheet":"April-2007 DCE","index":4,"n_rows":1464,"n_cols":36,"rows_kept":1464,"cut":false,"hidden":true,"merged":[[0,20,0,21],[0,22,0,23],[0,24,0,25],[0,26,0,27],[0,13,0,14],[0,15,0,17],[0,18,0,19],[1,0,1,5],[0,0,0,5],[0,7,0,8],[0,9,0,11]],"flags":["formulas_cached_only"]}
["WBS Level",{"$nulls":5},"LCLA  DCE April-2007","Budgeted Quantity",null,"Fully Burdened and Escalated Cost",null,null,null,"Work Rem. Bud. Qtty",null,"Work Rem. Full Burd and Escltd Cost",null,null,"FY05",null,"FY06",null,"FY07",null,"FY08",null,"FY09",null,"Contingency","Contingency","Design","Judgement","Basis","Program",null,"Tech"]
[{"$nulls":6},"Description","Hours","$$","Labor","M&S","Total (No Conting)",null,"Hours","$$","Labor","M&S","Total","BAC","% of Wrk Rem.","BAC","% of Wrk Rem.","BAC","% of Wrk Rem.","BAC","% of Wrk Rem.","BAC","% of Wrk Rem.","%","$","Maturity","Factor","of Estimate","Phase","CAM","Lead"]
["1","2","3","4","5","6"]
[{"$nulls":7},672715,164920794,71991028.7882482,164991129.25023675,211756182.65994766,null,506522.2819999999,131481414.99299997,54704512.344742596,130849311.28346746,185553823.6282105,0,null,1388366.720290325,null,105951667.83612011,null,62284607.54116008,null,15929181.530639263,null,null,27579745.69237628]
["1","  ","  ","  ","  ","  ","LCLS PROJECT - PED & CONSTRUCTION                           ",451292,144863153,46009354.660881184,144285188.06353953,166893428.07705373,null,300418.322,112602989.82299998,30534562.411021907,111519117.5151235,142053679.9261451,0,null,899225.916879578,null,94293403.15576768,null,45648408.517321475,null,1212642.336176415,null,null,27578514.880756088]
["1","01","  ","  ","  ","  ","LCLS PROJECT MGMT, PLANNING & ADMN (TEC)                    ",62978,3773747,6182863.061427882,4028883.475486999,9721735.804770928,null,40617.8,2556662.64,4037471.0730110174,2755389.374736062,6792860.447747083,0,null,83937.83090274602,null,4554778.2469098065,null,1744720.6029079559,null,409423.76702657016,null,null,1582711.5846414363]
["1","01","01","  ","  ","  ","Environment, Safety & Health                                ",12447,495350,1209600.6283274726,503403.0404287111,1647648.9448450727,null,8373,335000,815739.9761548765,342333.0404287111,1158073.0165835875,0,null,0,null,692471.3014190282,null,344188.29973123554,null,121413.41543332388,null,null,287906.0984564761]
["1","01","01","01","  ","  ","Radiation Physics                                           ",5636,0,541556.567844198,0,541556.567844198,null,4446,0,430165.32788419805,0,430165.32788419805,0,null,0,null,325382.98531939194,null,83854.88324674717,null,20927.459318058904,null,null,150557.86475946932]
["1","01","01","02","  ","  ","ESH Management & Coordination                               ",6811,405350,668044.0604832744,405350,1073394.0604832745,null,3927,260000,385574.64827067853,260000,645574.6482706785,0,null,0,null,334455.77905759995,null,227611.22961541355,null,83507.639597665,null,null,129114.92965413572]
["1","01","01","03","  ","  ","Seismic & Engineering Support                               ",0,90000,0,98053.0404287111,32698.316517599997,null,0,75000,0,82333.0404287111,82333.0404287111,0,null,0,null,32632.537042036278,null,32722.186869074834,null,16978.316517599997,null,null,8233.30404287111]
["1","01","02","  ","  ","  ","Project Management                                          ",21712,2233137,2223611.4813603275,2397458.626828298,4196414.099955783,null,15866,1637602.64,1649278.694176611,1772172.1260773607,3421450.820253971,0,null,83297.542549866,null,2296484.602551169,null,839040.2650857879,null,202628.4100671483,null,null,554538.7850048244]
["1","01","02","01","  ","  ","Project Management Office                                   ",21712,2233137,2223611.4813603275,2397458.626828298,4196414.099955783,null,15866,1637602.64,1649278.694176611,1772172.1260773607,3421450.820253971,0,null,83297.542549866,null,2296484.602551169,null,839040.2650857879,null,202628.4100671483,null,null,554538.7850048244]
["1","01","02","01","01","  ","Project Office - General                                    ",18279,0,2004720.6341672163,0,2004720.6341672163,null,13330,0,1486060.1033397005,0,1486060.1033397005,0,null,0,null,962731.2309675376,null,421433.59420504124,null,101895.27816712155,null,null,148606.01033397007]
["1","01","02","01","02","  ","Project Support                                             ",3433,1343661,218890.84719311073,1411447.6181110006,1230338.4653041114,null,2536,985021,163218.59083691076,1039432.8981110007,1202651.4889479114,0,null,80661.15702479339,null,906194.0679258325,null,191988.62211480876,null,23807.641882476637,null,null,240530.29778958226]
["1","01","02","01","03","  ","Project Office M&S                                          ",0,889476,0,986011.0087172976,961355.0004844544,null,0,652581.64,0,732739.2279663598,732739.2279663598,0,null,2636.385525072623,null,427559.3036577992,null,225618.0487659379,null,76925.49001755012,null,null,165402.47688127198]
["1","01","02","01","04","  ","SSRL Physics Support                                        "]
["1","01","03","  ","  ","  ","Technical Integration                                       ",28819,1045260,2749650.9517400777,1128021.8082299903,3877672.7599700675,null,16378.8,584060,1572452.4026795267,640884.2082299902,2213336.610909517,0,null,640.2883528799999,null,1565822.3429396069,null,561492.0380909324,null,85381.94152609797,null,null,740266.701180136]
["1","01","03","01","  ","  ","Global Laser Coordination                                   "]
["1","01","03","02","  ","  ","Global Alignment Coordination                               ",595,0,61580.865653999994,0,61580.865653999994,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","01","03","03","  ","  ","System Integration                                          ",5001,0,478187.7170873275,0,478187.7170873275,null,3811,0,368047.9374143275,0,368047.9374143275,0,null,0,null,321727.36675962957,null,37042.68533325148,null,9277.885321446469,null,null,294438.349931462]
["1","01","03","05","  ","  ","Global Controls                                             ",21735,1045260,2103810.834797149,1128021.8082299903,3231832.6430271408,null,12567.8,584060,1204404.4652651995,640884.2082299902,1845288.6734951895,0,null,640.2883528799999,null,1244094.9761799772,null,524449.3527576812,null,76104.0562046515,null,null,445828.3512486741]
["1","01","03","05","01","  ","Global Controls Management                                  "]
["1","01","03","05","02","  ","LLRF Controls                                               "]
["1","01","03","05","03","  ","E-beam Diagnostics & Controls                               ",5888,0,569777.3969110148,0,569777.3969110148,null,7.8,0,640.2883528799999,0,640.2883528799999,0,null,640.2883528799999,null,0,null,0,null,0,null,null,160.07208821999998]
["1","01","03","05","03","01","Controls - Wire Scanners                                    "]
["1","01","03","05","03","02","Controls - Toroids                                          ",4440,0,430584.04595742165,0,430584.04595742165,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","01","03","05","03","03","Controls - Faraday Cups                                     ",60,0,6360.760790999999,0,6360.760790999999,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","01","03","05","03","04","Controls - Tune-Up Dump                                     ",21,0,1964.5340021999998,0,1964.5340021999998,null,2.8,0,238.67277587999996,0,238.67277587999996,0,null,238.67277587999996,null,0,null,0,null,0,null,null,59.66819396999999]
["1","01","03","05","03","05","Controls - Profile Monitors                                 ",16,0,1413.6982002,0,1413.6982002,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","01","03","05","03","06","Controls - E/O Diagnostics                                  "]
["1","01","03","05","03","07","Controls - BPM                                              ",877,0,83915.52865499287,0,83915.52865499287,null,5,0,401.615577,0,401.615577,0,null,401.615577,null,0,null,0,null,0,null,null,100.40389425]
["1","01","03","05","03","08","Controls - Stopppers                                        ",16,0,1413.6982002,0,1413.6982002,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","01","03","05","03","09","Controls - Bunch Length Monitors                            ",228,0,24470.013605399996,0,24470.013605399996,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","01","03","05","03","10","Controls - Beam Loss Monitors                               "]
["1","01","03","05","03","11","Controls - Cherenkov Radiation Detector                     ",16,0,1413.6982002,0,1413.6982002,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","01","03","05","03","12","Controls - Movable Collimator                               ",214,0,18241.419299399997,0,18241.419299399997,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","01","03","05","04","  ","Laser Controls Design                                       "]
["1","01","03","05","05","  ","Laser Heater Controls                                       ",504,0,50426.28293535359,0,50426.28293535359,null,504,0,50426.28293535359,0,50426.28293535359,0,null,0,null,50426.28293535359,null,0,null,0,null,null,17649.19902737376]
["1","01","03","05","06","  ","Timing Controls                                             "]
["1","01","03","05","07","  ","Vacuum Controls                                             ",79,0,6561.8812314,0,6561.8812314,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","01","03","05","09","  ","Power Supply Controls                                       ",7341,0,612883.8122480953,0,612883.8122480953,null,6191,0,519367.3261030754,0,519367.3261030754,0,null,0,null,325530.3506117744,null,179349.28698944772,null,14487.688501853185,null,null,129841.83152576885]
["1","01","03","05","10","  ","Controls - PPS                                              ",3058,0,345137.83372393664,0,345137.83372393664,null,1529,0,172825.1735461416,0,172825.1735461416,0,null,0,null,172825.1735461416,null,0,null,0,null,null,77771.32809576373]
["1","01","03","05","11","  ","Controls - MPS                                              ",0,22000,0,23655.456,23655.456,null,0,22000,0,23655.456,23655.456,0,null,0,null,23655.456,null,0,null,0,null,null,4731.0912]
["1","01","03","05","12","  ","Global Controls Management                                  ",4697,1023260,500515.5448001493,1104366.3522299903,1604881.8970301393,null,4336,562060,461145.39432774927,617228.7522299902,1078374.1465577392,0,null,0,null,671657.713086708,null,345100.0657682334,null,61616.3677027983,null,null,215674.82931154803]
["1","01","03","05","12","01","Global Controls Management LOE                              ",4697,829260,500515.5448001493,886350.5449190304,1386866.0897191796,null,4336,448060,461145.39432774927,486852.9449190304,947998.3392467796,0,null,0,null,592491.5530867081,null,304487.8256882333,null,51018.960471838305,null,null,189599.667849356]
["1","01","03","05","12","02","Global Controls Management                                  ",0,194000,0,218015.80731095996,218015.80731095996,null,0,114000,0,130375.80731096004,130375.80731096004,0,null,0,null,79166.16,null,40612.240079999996,null,10597.40723096,null,null,26075.161462191998]
["1","01","03","05","13","  ","SLC Aware IOC                                               "]
["1","01","03","05","14","  ","Controls - S/W Application                                  "]
["1","01","03","05","15","  ","Controls - BCS                                              ",168,0,18508.082947199997,0,18508.082947199997,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","01","03","06","  ","  ","Technical Requirements/Parameters                           ",1488,0,106071.53420159998,0,106071.53420159998,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","01","04","  ","  ","  ","Education Support                                           "]
["1","01","04","01","  ","  ","Education/Outreach Travel                                   "]
["1","01","04","02","  ","  ","Education/Outreach M&S                                      "]
["1","02","  ","  ","  ","  ","INJECTOR SYSTEM                                             ",34585,3740665,3107282.1713680895,3894722.378949591,6320177.369496101,null,978,195400,94818.64532293781,208068.35627368418,302887.001596622,0,null,91264.72443431028,null,188598.5302785036,null,23023.746883808108,null,0,null,null,72500.40810327281]
["1","02","01","  ","  ","  ","Injector System Management & Integration                    ",5702,51402,539909.900457133,57969.98430204878,539909.900457133,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","01","01","  ","  ","Injector System Integration                                 ",2331,0,206572.14929390422,0,206572.14929390422,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","01","01","01","  ","Injector Region Integration                                 ",960,0,85758.25920541219,0,85758.25920541219,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","01","01","02","  ","Gun Area Integration                                        ",340,0,30895.071898227423,0,30895.071898227423,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","01","01","03","  ","Accelerator Area Integration                                ",317,0,27396.435389399994,0,27396.435389399994,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","01","01","04","  ","Heater Area Integration                                     "]
["1","02","01","01","05","  ","Wall Area Integration                                       "]
["1","02","01","01","06","  ","Insertion Area Integration                                  ",210,0,18432.248081759997,0,18432.248081759997,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","01","01","07","  ","Spectrometer Area Integration                               ",230,0,20386.787491421994,0,20386.787491421994,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","01","01","08","  ","Drive Laser Integration                                     ",274,0,23703.347227682567,0,23703.347227682567,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","01","04","  ","  ","Injector System Integration Effort / M&S                    ",3371,51402,333337.7511632288,57969.98430204878,333337.7511632288,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","  ","  ","  ","Injector Controls Subsystem                                 ",8546,1221970,741578.6248861526,1290350.0796479997,2031928.7045341516,null,278,84100,27618.370163094853,90428.3568,118046.72696309484,0,null,8668.641373575287,null,109378.08558951956,null,0,null,0,null,null,23968.77830077371]
["1","02","02","01","  ","  ","Personnel Protection Subsystem (PPS)                        ",1264,22000,98738.93443043517,23056,121794.93443043517,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","02","  ","  ","Beam Containment Subsystem (BCS)                            ",1800,217100,195832.23609357254,227520.8,423353.0360935726,null,138,0,15374.456760450856,0,15374.456760450856,0,null,8668.641373575287,null,6705.815386875569,null,0,null,0,null,null,3843.614190112714]
["1","02","02","03","  ","  ","Machine Protection Subsystem (MPS)                          ",0,75800,0,79438.4,79438.4,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","04","  ","  ","Injector Power Conversion                                   ",1193,95468,85696.17332988382,100050.464,185746.63732988382,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","04","01","  ","Beamline Pwr Supplies - (Dipole Type)                       ",280,15197,22208.144235552,15926.456,38134.600235552,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","04","01","01","10kw Power Supply - (Solenoid 1)                            ",56,0,4441.6288471104,0,4441.6288471104,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","04","01","02","30kw Power Supply - (Solenoid 2)                            ",56,15197,4441.6288471104,15926.456,20368.0848471104,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","04","01","03","2kw Power Supply - (B0.5 Spect)                             "]
["1","02","02","04","01","04","15kw Power Supply - (B1-2)                                  ",56,0,4441.6288471104,0,4441.6288471104,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","04","01","05","15kw Power Supply - (B3 Spect)                              ",56,0,4441.6288471104,0,4441.6288471104,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","04","01","06","10kw Power Supply - (New)                                   ",56,0,4441.6288471104,0,4441.6288471104,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","04","02","  ","Power Supply Controls                                       "]
["1","02","02","04","03","  ","Beamline Pwr Supplies - (Trim Type)                         ",224,0,17766.5153884416,0,17766.5153884416,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","04","03","01","12Amp Power Supply - (MCOR_1)                               ",56,0,4441.6288471104,0,4441.6288471104,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","04","03","02","30Amp Power Supply - (MCOR_2)                               ",56,0,4441.6288471104,0,4441.6288471104,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","04","03","03","30Amp Power Supply - (MCOR_3)                               ",56,0,4441.6288471104,0,4441.6288471104,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","04","03","04","30Amp Power Supply - (MCOR_4)                               ",56,0,4441.6288471104,0,4441.6288471104,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","04","04","  ","Beamline Pwr Supply - Misc Hdwr                             ",689,80271,45721.51370589022,84124.008,129845.52170589023,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","04","05","  ","Magnet Interlock Protection System                          "]
["1","02","02","05","  ","  ","LLRF Controls                                               ",0,263226,0,283033.230048,283033.230048,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","05","01","  ","Readback & Controls - RF Gun LLRF & Temperature             ",0,263226,0,283033.230048,283033.230048,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","05","02","  ","Readback & Controls - L0 LLRF                               "]
["1","02","02","05","03","  ","Readback & Controls - Transverse Cavity LLRF                "]
["1","02","02","05","04","  ","S-Band Cavity Controls                                      "]
["1","02","02","05","05","  ","EO Phase Controls                                           "]
["1","02","02","06","  ","  ","E-Beam Diagnostics Controls                                 ",3531,215453,303684.26009559823,226056.3248,529740.5848955982,null,80,0,6996.521944368,0,6996.521944368,0,null,0,null,6996.521944368,null,0,null,0,null,null,1749.130486092]
["1","02","02","06","01","  ","Controls - Wire Scanners                                    ",216,26688,17973.224453131195,27969.024,45942.2484531312,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","06","02","  ","Controls - BPM                                              ",1547,84405,133568.6551086877,88456.44,222025.0951086877,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","06","03","  ","Controls - Toroids                                          ",800,27700,69737.7696528857,29029.6,98767.36965288571,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","06","05","  ","Controls - Profile Monitors                                 ",56,31560,4892.877932183999,33336.4608,38229.338732184,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","06","06","  ","Controls - E/O Diagnostics                                  "]
["1","02","02","06","12","  ","Controls - Movable Collimator                               ",360,14500,30044.023976735996,15196,45240.023976735996,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","06","14","  ","Controls - Faraday Cups                                     ",144,500,12513.444731567999,524,13037.444731567999,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","06","15","  ","Controls - Tune-Up Dump                                     ",264,14200,22402.826699616002,14881.6,37284.426699616,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","06","16","  ","Controls - Cherenkov Radiation Detector                     ",144,15900,12551.437540789713,16663.2,29214.637540789714,null,80,0,6996.521944368,0,6996.521944368,0,null,0,null,6996.521944368,null,0,null,0,null,null,1749.130486092]
["1","02","02","08","  ","  ","Timing Controls                                             ",0,117500,0,123140,123140,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","09","  ","  ","Vacuum Controls                                             ",494,99190,39463.96241399039,103951.12,143415.0824139904,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","10","  ","  ","Software & Controls Infrastructure                          ",0,23133,0,24243.384,24243.384,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","10","01","  ","Low Level Application Software                              "]
["1","02","02","10","02","  ","High Level Application Software                             "]
["1","02","02","10","03","  ","Data Communications                                         ",0,16000,0,16768,16768,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","10","04","  ","Computers & Crates                                          ",0,7133,0,7475.384,7475.384,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","11","  ","  ","EPICS VXI Control Modules                                   "]
["1","02","02","12","  ","  ","Laser Controls                                              ",204,9000,12915.66706439554,9432,22347.66706439554,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","12","01","  ","Controls - Alignment Laser                                  "]
["1","02","02","12","02","  ","Controls - Gun Laser                                        ",204,9000,12915.66706439554,9432,22347.66706439554,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","13","  ","  ","Laser Heater Controls                                       ",60,84100,5247.391458276,90428.3568,95675.74825827598,null,60,84100,5247.391458276,90428.3568,95675.74825827598,0,null,0,null,95675.74825827598,null,0,null,0,null,null,18376.033624568998]
["1","02","03","  ","  ","  ","Injector Lasers                                             ",4722,1221573,470989.0681828807,1260942.94474424,1277812.6601828814,null,241,111300,20769.052277496594,117639.9994736842,138409.05175118078,0,null,82596.08306073499,null,55812.96869044581,null,0,null,0,null,null,34602.262937795196]
["1","02","03","01","  ","  ","Drive Laser Support                                         ",412,12800,78484.99107472981,14343.856661157028,78484.99107472981,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","03","01","01","  ","Drive Laser Support (ANL)                                   "]
["1","02","03","01","02","  ","Drive Laser Support (LLNL)                                  ",412,12800,78484.99107472981,14343.856661157028,78484.99107472981,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","03","02","  ","  ","Drive Laser System                                          ",154,544898,15005.055265199999,544898,559903.0552652,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","03","03","  ","  ","Drive Laser Diagnostics                                     ",1068,318000,93701.81990067029,336114.2842105263,93701.81990067029,null,241,111300,20769.052277496594,117639.9994736842,138409.05175118078,0,null,82596.08306073499,null,55812.96869044581,null,0,null,0,null,null,34602.262937795196]
["1","02","03","04","  ","  ","Timing Stability Monitoring                                 ",618,120600,55635.83888051094,126388.8,182024.63888051096,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","03","05","  ","  ","Steering Stability Feedback & Msmts                         ",60,16275,4856.477462152105,17056.2,21912.677462152104,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","03","06","  ","  ","Pre Amp Low Power Comp                                      ",380,32000,35111.82767076,34407.936,69519.76367076,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","03","07","  ","  ","Transport to Tunnel & Relay Optics                          "]
["1","02","03","08","  ","  ","UV Launch, Conditioning & Diagnostics                       ",710,88000,62173.247718476065,92955.85963898918,91517.24771847606,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","03","09","  ","  ","Load Lock Transport System                                  "]
["1","02","03","10","  ","  ","Visible Optical Transport & Optics                          "]
["1","02","03","11","  ","  ","LB Infrastructure & LB System Wide Items                    ",540,42000,47566.67844240515,44241.35223356752,51758.67844240515,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","03","12","  ","  ","Alignment Laser                                             ",180,20000,17623.633412016,21504.96,39128.593412015995,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","03","13","  ","  ","Light path to Streak Camera                                 ",600,27000,60829.49835596034,29031.696,89861.19435596034,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","03","14","  ","  ","LSR HTR - Beam Conditioning Optics (Laser Bay)              "]
["1","02","03","15","  ","  ","LSR HTR - Transport Optics (Bay to Tunnel)                  "]
["1","02","03","16","  ","  ","LSR HTR - Photon Beam Diagnostics                           "]
["1","02","03","21","  ","  ","UV Conv Harmonic Generation Unit (Closed Account)           "]
["1","02","04","  ","  ","  ","Injector RF Subsystem                                       ",4793,54000,399285.83564536896,56592,455877.83564536896,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","04","01","  ","  ","RF Gun & Load Lock                                          ",2883,52000,213816.33894238796,54496,268312.33894238796,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","04","01","01","  ","RF Gun                                                      ",2517,37000,183300.27019318796,38776,222076.27019318796,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","04","01","02","  ","RF Gun Supports                                             ",40,5000,3264.4648079999997,5240,8504.464808,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","04","01","03","  ","Gun Load Lock                                               "]
["1","02","04","01","04","  ","Gun Load Lock Supports                                      "]
["1","02","04","01","05","  ","Gun Solenoid                                                ",160,0,12980.61744,0,12980.61744,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","04","01","06","  ","Gun Solenoid Supports                                       ",166,10000,14270.986501199997,10480,24750.986501199997,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","04","01","07","  ","Gun RF Feed                                                 "]
["1","02","04","01","08","  ","Gun RF Feed Supports                                        "]
["1","02","04","02","  ","  ","Cathode Processing (CP) Station                             "]
["1","02","04","02","01","  ","CP Cathode Assembly & Supports                              "]
["1","02","04","02","02","  ","CP Load Lock                                                "]
["1","02","04","02","03","  ","CP Load Lock Supports                                       "]
["1","02","04","02","04","  ","CP Station                                                  "]
["1","02","04","02","05","  ","Cathode Lab Infrastructure                                  "]
["1","02","04","03","  ","  ","S-Band Low Level Timing                                     "]
["1","02","04","03","01","  ","Controls Interface & Timing                                 "]
["1","02","04","03","02","  ","LLRF Phase Reference System                                 "]
["1","02","04","03","03","  ","LLRF Monitor & Control System                               "]
["1","02","04","03","04","  ","Beam Phase Monitor Cavity                                   "]
["1","02","04","03","05","  ","RF System S/W Development / Docs                            "]
["1","02","04","04","  ","  ","S-Band High Power System                                    "]
["1","02","04","04","01","  ","RF Gun High Power                                           "]
["1","02","04","04","02","  ","L0 High Power                                               "]
["1","02","04","04","03","  ","Transverse Cavity High Power                                "]
["1","02","04","05","  ","  ","Injector RF Waveguide Subsystem                             ",1090,0,101173.27567426678,0,101173.27567426678,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","04","05","01","  ","RF Waveguides                                               ",1090,0,101173.27567426678,0,101173.27567426678,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","04","05","02","  ","RF Waveguide Supports                                       "]
["1","02","04","06","  ","  ","Injector Linac Structures                                   ",820,2000,84296.22102871421,2096,86392.22102871421,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","04","06","01","  ","L0A-0B Structure Assembly                                   ",640,0,64519.31536471422,0,64519.31536471422,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","04","06","03","  ","Major Linac Support                                         "]
["1","02","04","06","04","  ","GTL RF Phase Cavity                                         "]
["1","02","04","06","05","  ","LTDL1 RF Kicker                                             ",180,2000,19776.905663999998,2096,21872.905663999998,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","05","  ","  ","  ","Injector Magnets & Supports                                 ",1288,135500,113766.76065839994,142076.8411881188,224330.76065840002,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","05","01","  ","  ","Injector Dipoles                                            ",780,94500,67672.776168,99108.84118811881,135268.77616799998,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","05","01","01","  ","Gun Spectrometer Dipole                                     ",340,37500,30060.440628,39372.84118811881,37920.440628,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","05","01","02","  ","DL1 B01 & B02 Dipoles                                       ",100,1000,8400,1048,9448,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","05","01","03","  ","SAB Spectrometer Dipole                                     ",340,56000,29212.33554,58688,87900.33554,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","05","01","04","  ","Chicane DIPOLES (4)                                         "]
["1","02","05","02","  ","  ","Injector Quads                                              ",68,12000,5712,12576,18288,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","05","02","01","  ","Gun Spectrometer Quadrupoles                                ",40,12000,3360,12576,15936,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","05","02","02","  ","Injector Quadrupoles                                        ",28,0,2352,0,2352,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","05","02","03","  ","                                                            "]
["1","02","05","03","  ","  ","Injector Steering Coils                                     ",120,14000,10300.6345224,14672,24972.6345224,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","05","03","01","  ","Gun Solenoid Correctors                                     "]
["1","02","05","03","02","  ","Gun Spectrometer Correctors                                 "]
["1","02","05","03","03","  ","Injector Correctors - A                                     ",120,14000,10300.6345224,14672,24972.6345224,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","05","03","04","  ","Injector Correctors - D (Gun)                               "]
["1","02","05","03","05","  ","Gun Solenoid Quadrupole Correctors                          "]
["1","02","05","04","  ","  ","Linac Solenoid                                              ",320,15000,30081.349967999995,15720,45801.349967999995,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","05","05","  ","  ","Injector Laser Heater Subsystem                             "]
["1","02","05","05","01","  ","System Design & Optimization (LSR HTR)                      "]
["1","02","05","05","02","  ","Injector Undulator                                          "]
["1","02","06","  ","  ","  ","Injector Vacuum & Supports                                  ",540,126000,53052.66324736813,133176.54943081966,112400.18972736812,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","06","01","  ","  ","Injector Vacuum Engineering                                 ",240,0,22103.162927999998,0,22103.162927999998,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","06","02","  ","  ","Injector Vacuum Components                                  "]
["1","02","06","03","  ","  ","Injector Vacuum Special Chambers                            ",300,81000,30949.500319368133,85357.02295081966,42477.50031936813,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","06","04","  ","  ","Injector Vacuum Supports Engineering                        "]
["1","02","06","05","  ","  ","Injector Vacuum Support Components                          ",0,45000,0,47819.52648,47819.52648,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","06","08","  ","  ","DL1 Vacuum Chamber                                          "]
["1","02","06","10","  ","  ","DL1TL Vacuum Components                                     "]
["1","02","07","  ","  ","  ","Injector Diagnostics                                        ",1752,536000,149754.35122826265,559393.9796363637,644752.3512282626,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","07","01","  ","  ","Beam Position Monitors                                      ",200,31000,16407.383437299097,32488,48895.3834372991,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","07","01","01","  ","Large Aperture BPM                                          ",200,31000,16407.383437299097,32488,48895.3834372991,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","07","01","02","  ","Small Aperture BPM                                          "]
["1","02","07","01","06","  ","                                                            "]
["1","02","07","02","  ","  ","Current Monitors                                            ",120,80000,9648.310299407998,83840,93488.310299408,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","07","02","01","  ","Current Monitors                                            ",120,80000,9648.310299407998,83840,93488.310299408,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","07","03","  ","  ","Bunch Length Monitors                                       "]
["1","02","07","03","01","  ","Bunch Length Monitors                                       "]
["1","02","07","04","  ","  ","Profile Monitors                                            ",1232,425000,106365.09916355555,443065.9796363636,485035.09916355554,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","07","04","01","  ","Profile Monitors                                            ",1232,425000,106365.09916355555,443065.9796363636,485035.09916355554,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","07","04","03","  ","GS Faraday Cup/YAG2                                         "]
["1","02","07","04","06","  ","DL1 OTR/YAG                                                 "]
["1","02","07","04","07","  ","DL1TL OTR/YAG                                               "]
["1","02","07","04","08","  ","LTDL1 OTR/YAG (6)                                           "]
["1","02","07","05","  ","  "," Injector Wire Scanners                                     ",200,0,17333.558328,0,17333.558328,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","07","06","  ","  ","LSR HTR - Electron Beam Diagnostics                         "]
["1","02","07","07","  ","  ","PPS Stopper                                                 "]
["1","02","17","  ","  ","  ","Injector Installation & Alignment                           ",7242,394220,638944.9670625298,394220,1033164.9670625299,null,459,0,46431.22288234635,0,46431.22288234635,0,null,0,null,23407.475998538244,null,23023.746883808108,null,0,null,null,13929.366864703905]
["1","02","17","01","  ","  ","Injector Infrastructure Installation                        ",2245,31440,211663.14815794275,31440,243103.14815794275,null,459,0,46431.22288234635,0,46431.22288234635,0,null,0,null,23407.475998538244,null,23023.746883808108,null,0,null,null,13929.366864703905]
["1","02","17","02","  ","  ","Injector Controls Subsystem Install & Align                 ",0,179240,0,179240,179240,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","17","03","  ","  ","Injector Lasers Install & Align                             ",1336,141320,118267.68997777917,141320,259587.68997777914,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","17","04","  ","  ","Gun Area Integration                                        ",672,7680,56819.40599475199,7680,64499.40599475199,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","17","06","  ","  ","Accelerator Area Integration                                ",896,13540,75744.43758950406,13540,89284.43758950406,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","17","07","  ","  ","Heater Area Integration                                     ",656,3440,55145.67016354331,3440,58585.67016354331,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","17","08","  ","  ","Wall Area Integration                                       "]
["1","02","17","09","  ","  ","Insertion Area Integration                                  ",725,17560,60829.01778163205,17560,78389.01778163205,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","17","11","  ","  ","Spectrometer Area Integration                               ",712,0,60475.597397376,0,60475.597397376,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","17","12","  ","  ","Injector RF High Power System Install & Align               "]
["1","02","17","13","  ","  ","Injector RF Low Level Install & Align                       "]
["1","02","17","14","  ","  ","Cathode and Load Lock Install & Align                       "]
["1","02","17","15","  ","  ","Injector Laser Heater Subsystem Install & Align             "]
["1","02","17","17","  ","  ","Power  Conversion Subsystem Installation                    "]
["1","02","17","18","  ","  ","Cathode Processing Center Installation                      "]
["1","03","  ","  ","  ","  ","LINAC SYSTEM                                                ",110527,10890180,9988942.221587664,11529258.399698067,20011101.340878233,null,76230.95,8958198.4,6892576.87233404,9487286.197956149,16379863.070290163,0,null,172645.36379524978,null,11684501.710805573,null,4519086.37651687,null,3629.6191724795926,null,null,3621527.536117501]
["1","03","01","  ","  ","  ","System Management & Integration                             ",20422,364478,1968090.3209093555,397728.35998120176,2146049.651812012,null,9431.3,326837.4,916636.7478416432,355163.3907388002,1271800.138580444,0,null,15773.502060656465,null,847892.8676343659,null,404504.1497129413,null,3629.6191724795926,null,null,312288.7179895804]
["1","03","01","01","  ","  ","Linac Mechanical Integration                                ",14467,300000,1380308.6581953957,322706.4777070866,1541595.8581953957,null,8042.9,300000,777543.7927912528,322706.4777070866,1100250.2704983393,0,null,15773.502060656465,null,743289.4614769816,null,337557.68778822175,null,3629.6191724795926,null,null,290997.1703358014]
["1","03","01","01","01","  ","L01 System Integration                                      ",480,0,45618.55979046237,0,45618.55979046237,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","03","01","01","02","  ","BC1 System Integration                                      ",550,0,52643.85397459933,0,52643.85397459933,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","03","01","01","03","  ","L02 System Integration                                      ",1174,0,117837.23048491549,0,117837.23048491549,null,1018.8,0,102852.54251394945,0,102852.54251394945,0,null,274.2612312124947,null,26921.832523839115,null,75656.44875889782,null,0,null,null,15427.88137709241]
["1","03","01","01","04","  ","BC2 System Integration                                      ",4070,0,393652.45665187197,0,393652.45665187197,null,2163.5,0,215294.97440954283,0,215294.97440954283,0,null,6406.921507206062,null,94363.50388186477,null,114524.54902047204,null,0,null,null,53823.74360238571]
["1","03","01","01","05","  ","L03 System Integration                                      ",1081,0,106792.39542967634,0,106792.39542967634,null,864.2,0,85901.87144087239,0,85901.87144087239,0,null,831.8468613338612,null,22789.857286424838,null,62280.16729311367,null,0,null,null,12885.280716130854]
["1","03","01","01","06","  ","LTU System Integration                                      ",3858,150000,362290.5555401099,161353.2388535433,442934.15554010996,null,2208,150000,207186.98403383058,161353.2388535433,368540.2228873739,0,null,4191.393233486812,null,316502.3510988913,null,44216.859382516195,null,3629.6191724795926,null,null,110562.06686621218]
["1","03","01","01","07","  ","E-Dump System Integration                                   ",3254,150000,301473.60632376024,161353.2388535433,382117.2063237603,null,1788.4,150000,166307.4203930577,161353.2388535433,327660.65924660105,0,null,4069.0792274172363,null,282711.9166859616,null,40879.663333222124,null,0,null,null,98298.19777398031]
["1","03","01","03","  ","  ","Travel                                                      ",0,36000,0,44583.93664719101,15158.5344,null,0,20200,0,25254.3744,25254.3744,0,null,0,null,10095.84,null,15158.5344,null,0,null,null,3788.1561599999995]
["1","03","01","04","  ","  ","Linac Management                                            ",5955,28478,587781.6627139596,30437.945626924135,589295.2592166155,null,1388.4,6637.4,139092.95505039024,7202.5386317136445,146295.49368210384,0,null,0,null,94507.56615738427,null,51787.9275247196,null,0,null,null,17503.391493779087]
["1","03","02","  ","  ","  ","Linac Controls & Power Conversion Subsystem                 ",31592,4826453,2655961.4596261308,5179470.59353448,7612874.680970129,null,25826.2,3939351,2177501.069660595,4239146.864368002,6416647.934028604,0,null,119696.82421104645,null,5498396.451944916,null,798554.6578726424,null,0,null,null,1669606.399544891]
["1","03","02","01","  ","  ","Personnel Protection System (PPS)                           ",2514,284280,191671.61710061473,305671.50144,497343.11854061484,null,2462.5,284280,187846.64829460953,305671.50144,493518.14973460964,0,null,0,null,416828.22455569386,null,76689.92517891574,null,0,null,null,123379.53743365241]
["1","03","02","02","  ","  ","Beam Containment System (BCS)                               ",1248,126200,137951.3286660542,135696.2976,273647.6262660542,null,1181.6,126200,132188.21050498448,135696.2976,267884.5081049845,0,null,2538.79481114754,null,255630.57055483435,null,9715.142739002567,null,0,null,null,66971.12702624612]
["1","03","02","03","  ","  ","Machine Protection System (MPS)                             ",0,84000,0,89863.0656,89863.0656,null,0,67200,0,72256.6656,72256.6656,0,null,0,null,72256.6656,null,0,null,0,null,null,32515.499519999998]
["1","03","02","04","  ","  ","Linac Power Conversion Subsystem                            ",11420,2438413,880103.2529045067,2614721.222702476,3272267.103416519,null,9200.1,1892869,707398.1794324736,2035139.5735519975,2742537.7529844805,0,null,69944.2339217375,null,2605710.7200368047,null,66882.7990259382,null,0,null,null,643581.7523079372]
["1","03","02","04","01","  ","Beamline Power Supplies - (Dipole Type)                     ",1860,162950,157763.40204865942,175117.38352000006,332880.78556865966,null,1680,120260,138493.9264427691,129215.04639999995,267708.97284276935,0,null,7057.461249328027,null,252553.97259582262,null,8097.538997618553,null,0,null,null,61188.48324269229]
["1","03","02","04","01","01","Power Supply BX11-14                                        ",32,23260,2694.0996412704,25010.26848,27704.368121270396,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","03","02","04","01","02","Power Supply BX21-24                                        ",32,3460,2625.8281104,3626.08,6251.908110399999,null,32,3460,2625.8281104,3626.08,6251.908110399999,0,null,6251.908110399999,null,0,null,0,null,0,null,null,1486.4730275999998]
["1","03","02","04","01","03","Kicker Power Supply BXKIK                                   ",826,18665,70005.93535880178,20069.50392,90075.43927880179,null,746,8950,61041.704639384545,9623.469599999997,70665.17423938455,0,null,309.82813035693397,null,67327.761808854,null,3027.584300173605,null,0,null,null,17265.763679846135]
["1","03","02","04","01","04","Power Supply BX31,32,35,36                                  ",32,37960,2694.0996412704,40816.414079999995,43510.51372127039,null,32,37960,2694.0996412704,40816.414079999995,43510.51372127039,0,null,0,null,43510.51372127039,null,0,null,0,null,null,8944.332526317601]
["1","03","02","04","01","05","Power Supply -BY1-2                                         ",32,15260,2694.0996412704,16408.28448,19102.384121270396,null,32,15260,2694.0996412704,16408.28448,19102.384121270396,0,null,0,null,19102.384121270396,null,0,null,0,null,null,4054.104622317601]
["1","03","02","04","01","06","Kicker Power Supply BYKIK                                   ",826,18665,70056.75889082404,20069.50392,90126.26281082405,null,758,8950,62445.61364562134,9623.469599999997,72069.08324562135,0,null,495.7250085710944,null,66503.40353960531,null,5069.954697444948,null,0,null,null,17536.097331405337]
["1","03","02","04","01","07","Power Supply BYW1-3                                         ",32,15260,2694.0996412704,16408.28448,19102.384121270396,null,32,15260,2694.0996412704,16408.28448,19102.384121270396,0,null,0,null,19102.384121270396,null,0,null,0,null,null,4070.2333423176005]
["1","03","02","04","01","08","Muon Spoiler Power Supply MUSPLR                            ",32,15260,2694.0996412704,16408.28448,19102.384121270396,null,32,15260,2694.0996412704,16408.28448,19102.384121270396,0,null,0,null,19102.384121270396,null,0,null,0,null,null,4062.7066063176007]
["1","03","02","04","01","09","Powe Supply BYD1-3                                          ",16,15160,1604.3814822816,16300.75968,17905.141162281598,null,16,15160,1604.3814822816,16300.75968,17905.141162281598,0,null,0,null,17905.141162281598,null,0,null,0,null,null,3768.7721065704]
["1","03","02","04","02","  ","Beamline Power Supplies - (Quad Type)                       ",731,486842,60904.08386334356,523307.43967999954,584211.5235433442,null,692,439780,57319.42899402717,472802.81055999955,530122.2395540277,0,null,3406.6407255999998,null,526715.5988284276,null,0,null,0,null,null,110787.36203250688]
["1","03","02","04","02","06","Q21201-Q21901 Switch Over                                   ",36,3622,3399.0102432,3795.856,7194.8662432,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","03","02","04","02","07","Q24201-Q24501 Split                                         ",56,48060,5150.478607876799,51676.418880000005,56826.8974878768,null,56,48060,5150.478607876799,51676.418880000005,56826.8974878768,0,null,0,null,56826.8974878768,null,0,null,0,null,null,11046.7756999692]
["1","03","02","04","02","08","Power Supply Q24601                                         "]
["1","03","02","04","02","09","Power Supply  Q24701A,Q24701B                               "]
["1","03","02","04","02","10","Power Supply QM21                                           ",24,15260,1978.6611407903997,16408.28448,18386.945620790397,null,24,15260,1978.6611407903997,16408.28448,18386.945620790397,0,null,0,null,18386.945620790397,null,0,null,0,null,null,3883.8469811976]
["1","03","02","04","02","11","Power Supply Q24901A,Q24901B                                "]
["1","03","02","04","02","12","Power Supply QM22                                           ",24,15260,1978.6611407903997,16408.28448,18386.945620790397,null,24,15260,1978.6611407903997,16408.28448,18386.945620790397,0,null,0,null,18386.945620790397,null,0,null,0,null,null,3883.8469811976]
["1","03","02","04","02","13","Power Supply Q5                                             ",24,15260,1978.6611407903997,16408.28448,18386.945620790397,null,24,15260,1978.6611407903997,16408.28448,18386.945620790397,0,null,0,null,18386.945620790397,null,0,null,0,null,null,3883.8469811976]
["1","03","02","04","02","14","Power Supply Q6                                             ",24,15260,1978.6611407903997,16408.28448,18386.945620790397,null,24,15260,1978.6611407903997,16408.28448,18386.945620790397,0,null,0,null,18386.945620790397,null,0,null,0,null,null,3883.8469811976]
["1","03","02","04","02","15","Power Supply QA0                                            ",24,15260,1978.6611407903997,16408.28448,18386.945620790397,null,24,15260,1978.6611407903997,16408.28448,18386.945620790397,0,null,0,null,18386.945620790397,null,0,null,0,null,null,3883.8469811976]
["1","03","02","04","02","16","Power Supply Q50Q1,Q50Q2,Q50Q3                              ",24,15260,1978.6611407903997,16408.28448,18386.945620790397,null,24,15260,1978.6611407903997,16408.28448,18386.945620790397,0,null,0,null,18386.945620790397,null,0,null,0,null,null,3883.8469811976]
["1","03","02","04","02","17","Power Supply  QVM1                                          ",24,15260,1978.6611407903997,16408.28448,18386.945620790397,null,24,15260,1978.6611407903997,16408.28448,18386.945620790397,0,null,0,null,18386.945620790397,null,0,null,0,null,null,3883.8469811976]
["1","03","02","04","02","18","Power Supply  QVM2                                          ",24,15260,1978.6611407903997,16408.28448,18386.945620790397,null,24,15260,1978.6611407903997,16408.28448,18386.945620790397,0,null,0,null,18386.945620790397,null,0,null,0,null,null,3883.8469811976]
["1","03","02","04","02","19","Power Supply  QVM3                                          ",24,15260,1978.6611407903997,16408.28448,18386.945620790397,null,24,15260,1978.6611407903997,16408.28448,18386.945620790397,0,null,0,null,18386.945620790397,null,0,null,0,null,null,3883.8469811976]
["1","03","02","04","02","20","Power Supply  QVM4                                          ",24,15260,1978.6611407903997,16408.28448,18386.945620790397,null,24,13260,1978.6611407903997,14257.78848,16236.449620790398,0,null,0,null,16236.449620790398,null,0,null,0,null,null,3346.2229811976]
["1","03","02","04","02","21","Power Supply  QVB1-3                                        ",24,15260,1978.6611407903997,16408.28448,18386.945620790397,null,24,3460,1978.6611407903997,3720.3580800000004,5699.019220790401,0,null,0,null,5699.019220790401,null,0,null,0,null,null,1346.2617011976001]
["1","03","02","04","02","22","Power Supply  QDL31-34                                      ",24,27260,1978.6611407903997,29311.260479999997,31289.921620790396,null,24,27260,1978.6611407903997,29311.260479999997,31289.921620790396,0,null,0,null,31289.921620790396,null,0,null,0,null,null,6464.4421811976]
["1","03","02","04","02","23","Power Supply  QE31-36                                       ",24,15260,1978.6611407903997,16408.28448,18386.945620790397,null,24,15260,1978.6611407903997,16408.28448,18386.945620790397,0,null,0,null,18386.945620790397,null,0,null,0,null,null,3883.8469811976]
["1","03","02","04","02","24","Power Supply  QEM1                                          ",24,15260,1978.6611407903997,16408.28448,18386.945620790397,null,24,15260,1978.6611407903997,16408.28448,18386.945620790397,0,null,0,null,18386.945620790397,null,0,null,0,null,null,3883.8469811976]
["1","03","02","04","02","25","Power Supply  QEM2                                          ",24,15260,1978.6611407903997,16408.28448,18386.945620790397,null,24,15260,1978.6611407903997,16408.28448,18386.945620790397,0,null,0,null,18386.945620790397,null,0,null,0,null,null,3883.8469811976]
["1","03","02","04","02","26","Power Supply  QEM3                                          ",24,15260,1978.6611407903997,16408.28448,18386.945620790397,null,24,15260,1978.6611407903997,16408.28448,18386.945620790397,0,null,0,null,18386.945620790397,null,0,null,0,null,null,3883.8469811976]
["1","03","02","04","02","27","Power Supply  QEM4                                          ",24,15260,1978.6611407903997,16408.28448,18386.945620790397,null,24,15260,1978.6611407903997,16408.28448,18386.945620790397,0,null,0,null,18386.945620790397,null,0,null,0,null,null,3883.8469811976]
["1","03","02","04","02","28","Power Supply QT11,13,21,23,31,33,41,43                      ",24,25260,1978.6611407903997,27160.764479999998,29139.425620790396,null,24,3460,1978.6611407903997,3720.3580800000004,5699.019220790401,0,null,0,null,5699.019220790401,null,0,null,0,null,null,1346.2617011976001]
["1","03","02","04","02","29","Power Supply QT12,22,32,42                                  ",24,25260,1978.6611407903997,27160.764479999998,29139.425620790396,null,24,25260,1978.6611407903997,27160.764479999998,29139.425620790396,0,null,0,null,29139.425620790396,null,0,null,0,null,null,6034.3429811976]
["1","03","02","04","02","30","Power Supply  QUM1                                          ",24,15260,1978.6611407903997,16408.28448,18386.945620790397,null,24,15260,1978.6611407903997,16408.28448,18386.945620790397,0,null,0,null,18386.945620790397,null,0,null,0,null,null,3883.8469811976]
["1","03","02","04","02","31","Power Supply  QUM2                                          ",24,15260,1978.6611407903997,16408.28448,18386.945620790397,null,24,13260,1978.6611407903997,14257.78848,16236.449620790398,0,null,0,null,16236.449620790398,null,0,null,0,null,null,3346.2229811976]
["1","03","02","04","02","32","Power Supply  QUM3                                          ",24,15260,1978.6611407903997,16408.28448,18386.945620790397,null,24,15260,1978.6611407903997,16408.28448,18386.945620790397,0,null,0,null,18386.945620790397,null,0,null,0,null,null,3883.8469811976]
["1","03","02","04","02","33","Power Supply QUM4                                           ",24,15260,1978.6611407903997,16408.28448,18386.945620790397,null,24,15260,1978.6611407903997,16408.28448,18386.945620790397,0,null,0,null,18386.945620790397,null,0,null,0,null,null,3883.8469811976]
["1","03","02","04","02","34","Power Supply QDMP1-2                                        ",24,15260,1978.6611407903997,16408.28448,18386.945620790397,null,24,15260,1978.6611407903997,16408.28448,18386.945620790397,0,null,0,null,18386.945620790397,null,0,null,0,null,null,3883.8469811976]
["1","03","02","04","02","35","Power Supply QUE1                                           ",24,15260,1978.6611407903997,16408.28448,18386.945620790397,null,24,13260,1978.6611407903997,14257.78848,16236.449620790398,0,null,0,null,16236.449620790398,null,0,null,0,null,null,3346.2229811976]
["1","03","02","04","02","36","Power Supply QUE2                                           ",24,15260,1978.6611407903997,16408.28448,18386.945620790397,null,24,15260,1978.6611407903997,16408.28448,18386.945620790397,0,null,0,null,18386.945620790397,null,0,null,0,null,null,3883.8469811976]
["1","03","02","04","02","37","Rack Accessories - LI21                                     ",3,3840,185.64462611639993,4128.95232,4314.5969461164,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","03","02","04","02","38","Rack Accessories - LI24                                     ",3,640,180.94018139999997,670.72,851.6601814,null,3,640,180.94018139999997,670.72,851.6601814,0,null,851.6601814,null,0,null,0,null,0,null,null,179.37904535]
["1","03","02","04","02","39","Rack Accessories - LI25                                     ",3,640,180.94018139999997,670.72,851.6601814,null,3,640,180.94018139999997,670.72,851.6601814,0,null,851.6601814,null,0,null,0,null,0,null,null,179.37904535]
["1","03","02","04","02","40","Rack Accessories - BSY                                      ",3,640,180.94018139999997,670.72,851.6601814,null,3,640,180.94018139999997,670.72,851.6601814,0,null,851.6601814,null,0,null,0,null,0,null,null,179.37904535]
["1","03","02","04","02","41","Rack Accessories - Dump                                     ",3,640,180.94018139999997,670.72,851.6601814,null,3,640,180.94018139999997,670.72,851.6601814,0,null,851.6601814,null,0,null,0,null,0,null,null,179.37904535]
["1","03","02","04","03","  ","Beamline Power Supplies - (Trim Type)                       ",1595,583946,163971.47491064837,624584.2565119998,788555.731422648,null,1366,390104,141594.47157065597,419458.54579199955,561053.0173626557,0,null,294.0443643194749,null,560758.9729983362,null,0,null,0,null,null,125692.52622648251]
["1","03","02","04","03","01","MCOR_1                                                      ",24,26725,2061.6180552,28007.8,30069.4180552,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","03","02","04","03","02","MCOR_2                                                      ",28,26725,2569.06848,28007.8,30576.86848,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","03","02","04","03","03","MCOR_3                                                      ",28,26725,2569.06848,28007.8,30576.86848,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","03","02","04","03","04","MCOR_4                                                      ",20,27845,1871.76,29181.56,31053.32,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","03","02","04","03","05","MCOR_5                                                      ",28,26725,2635.8642604799998,28736.002800000006,31371.867060480003,null,28,26725,2635.8642604799998,28736.002800000006,31371.867060480003,0,null,0,null,31371.867060480003,null,0,null,0,null,null,6406.166625119999]
["1","03","02","04","03","06","MCOR_6                                                      ",28,19025,2635.8642604799998,20456.593200000003,23092.45746048,null,28,19025,2635.8642604799998,20456.593200000003,23092.45746048,0,null,0,null,23092.45746048,null,0,null,0,null,null,4750.28470512]
["1","03","02","04","03","07","MCOR_BSY1                                                   ",28,20950,2635.8642604799998,22526.445600000003,25162.30986048,null,28,20950,2635.8642604799998,22526.445600000003,25162.30986048,0,null,0,null,25162.30986048,null,0,null,0,null,null,5164.255185119999]
["1","03","02","04","03","08","MCOR_LTU1                                                   ",28,22875,2635.8642604799998,24596.298000000006,27232.162260480003,null,28,22875,2635.8642604799998,24596.298000000006,27232.162260480003,0,null,0,null,27232.162260480003,null,0,null,0,null,null,5578.225665119999]
["1","03","02","04","03","09","MCOR_LTU2                                                   ",28,20950,2635.8642604799998,22526.445600000003,25162.30986048,null,28,20950,2635.8642604799998,22526.445600000003,25162.30986048,0,null,0,null,25162.30986048,null,0,null,0,null,null,5164.255185119999]
["1","03","02","04","03","10","MCOR_LTU3                                                   ",28,19025,2635.8642604799998,20456.593200000003,23092.45746048,null,28,19025,2635.8642604799998,20456.593200000003,23092.45746048,0,null,0,null,23092.45746048,null,0,null,0,null,null,4750.28470512]
["1","03","02","04","03","11","MCOR_LTU4                                                   ",28,22875,2635.8642604799998,24596.298000000006,27232.162260480003,null,28,22875,2635.8642604799998,24596.298000000006,27232.162260480003,0,null,0,null,27232.162260480003,null,0,null,0,null,null,5578.225665119999]
["1","03","02","04","03","12","MCOR_LTU5                                                   ",28,22875,2635.8642604799998,24596.298000000006,27232.162260480003,null,28,22875,2635.8642604799998,24596.298000000006,27232.162260480003,0,null,0,null,27232.162260480003,null,0,null,0,null,null,5578.225665119999]
["1","03","02","04","03","13","MCOR_LTU6                                                   ",28,22875,2635.8642604799998,24596.298000000006,27232.162260480003,null,28,22875,2635.8642604799998,24596.298000000006,27232.162260480003,0,null,0,null,27232.162260480003,null,0,null,0,null,null,5578.225665119999]
["1","03","02","04","03","14","MCOR_LTU7                                                   ",28,22875,2635.8642604799998,24596.298000000006,27232.162260480003,null,28,22875,2635.8642604799998,24596.298000000006,27232.162260480003,0,null,0,null,27232.162260480003,null,0,null,0,null,null,5578.225665119999]
["1","03","02","04","03","15","MCOR_LTU8                                                   ",28,22875,2635.8642604799998,24596.298000000006,27232.162260480003,null,28,22875,2635.8642604799998,24596.298000000006,27232.162260480003,0,null,0,null,27232.162260480003,null,0,null,0,null,null,5578.225665119999]
["1","03","02","04","03","16","MCOR_LTU9                                                   ",28,19025,2635.8642604799998,20456.593200000003,23092.45746048,null,28,19025,2635.8642604799998,20456.593200000003,23092.45746048,0,null,0,null,23092.45746048,null,0,null,0,null,null,4750.28470512]
["1","03","02","04","03","17","MCOR_DUMP1                                                  ",28,24800,2635.8642604799998,26666.150400000002,29302.01466048,null,28,24800,2635.8642604799998,26666.150400000002,29302.01466048,0,null,0,null,29302.01466048,null,0,null,0,null,null,5992.196145119999]
["1","03","02","04","03","18","MCOR Bulk PS - LI21_1                                       ",4,8100,247.5261681551999,8709.5088,8957.0349681552,null,0,100,0,107.5248,107.5248,0,null,0,null,107.5248,null,0,null,0,null,null,21.50496]
["1","03","02","04","03","19","MCOR Bulk PS - LI21_2                                       ",4,8100,247.5261681551999,8709.5088,8957.0349681552,null,0,100,0,107.5248,107.5248,0,null,0,null,107.5248,null,0,null,0,null,null,21.50496]
["1","03","02","04","03","20","MCOR Bulk PS - LI24                                         ",4,8100,247.5261681551999,8709.5088,8957.0349681552,null,4,100,247.5261681551999,107.5248,355.05096815519994,0,null,0,null,355.05096815519994,null,0,null,0,null,null,83.38650203879997]
["1","03","02","04","03","21","MCOR Bulk PS - LI25                                         ",4,8100,247.5261681551999,8709.5088,8957.0349681552,null,4,100,247.5261681551999,107.5248,355.05096815519994,0,null,0,null,355.05096815519994,null,0,null,0,null,null,83.38650203879997]
["1","03","02","04","03","22","MCOR Bulk PS - BSY                                          ",4,8100,247.5261681551999,8709.5088,8957.0349681552,null,4,100,247.5261681551999,107.5248,355.05096815519994,0,null,0,null,355.05096815519994,null,0,null,0,null,null,83.38650203879997]
["1","03","02","04","03","23","MCOR Bulk PS - LTU_1                                        ",4,8100,247.5261681551999,8709.5088,8957.0349681552,null,4,100,247.5261681551999,107.5248,355.05096815519994,0,null,0,null,355.05096815519994,null,0,null,0,null,null,83.38650203879997]
["1","03","02","04","03","24","MCOR Bulk PS - LTU_2                                        ",4,8100,247.5261681551999,8709.5088,8957.0349681552,null,4,100,247.5261681551999,107.5248,355.05096815519994,0,null,0,null,355.05096815519994,null,0,null,0,null,null,83.38650203879997]
["1","03","02","04","03","25","MCOR Bulk PS - LTU_3                                        ",4,8000,247.5261681551999,8601.984,8849.5101681552,null,4,0,247.5261681551999,0,247.5261681551999,0,null,0,null,247.5261681551999,null,0,null,0,null,null,61.88154203879998]
["1","03","02","04","03","26","MCOR Bulk PS - LTU_4                                        ",4,8100,247.5261681551999,8709.5088,8957.0349681552,null,4,100,247.5261681551999,107.5248,355.05096815519994,0,null,0,null,355.05096815519994,null,0,null,0,null,null,83.38650203879997]
["1","03","02","04","03","27","MCOR PLC - LI21                                             ",136,13182,14549.576177899982,13814.735999999999,28364.31217789998,null,16,0,1801.0217314567838,0,1801.0217314567838,0,null,294.0443643194749,null,1506.9773671373089,null,0,null,0,null,null,180.1021731456784]
["1","03","02","04","03","28","MCOR PLC - LI24                                             ",136,13182,14774.74886052,14173.919135999999,28948.66799652,null,136,13182,14774.74886052,14173.919135999999,28948.66799652,0,null,0,null,28948.66799652,null,0,null,0,null,null,7481.6642473495185]
["1","03","02","04","03","29","MCOR PLC - LI25                                             ",136,13182,14774.74886052,14173.919135999999,28948.66799652,null,136,13182,14774.74886052,14173.919135999999,28948.66799652,0,null,0,null,28948.66799652,null,0,null,0,null,null,7481.6642473495185]
["1","03","02","04","03","30","MCOR PLC - BSY                                              ",136,13182,14774.74886052,14173.919135999999,28948.66799652,null,136,13182,14774.74886052,14173.919135999999,28948.66799652,0,null,0,null,28948.66799652,null,0,null,0,null,null,7481.6642473495185]
["1","03","02","04","03","31","MCOR PLC - LTU_1 (BLD 2.1)                                  ",136,13182,14774.74886052,14173.919135999999,28948.66799652,null,136,13182,14774.74886052,14173.919135999999,28948.66799652,0,null,0,null,28948.66799652,null,0,null,0,null,null,7481.6642473495185]
["1","03","02","04","03","32","MCOR PLC - LTU_2 (BLD 2.2)                                  ",136,13182,14774.74886052,14173.919135999999,28948.66799652,null,136,13182,14774.74886052,14173.919135999999,28948.66799652,0,null,0,null,28948.66799652,null,0,null,0,null,null,7481.6642473495185]
["1","03","02","04","03","33","MCOR PLC - LTU_3 (BLD 2.3)                                  ",136,13182,14774.74886052,14173.919135999999,28948.66799652,null,136,13182,14774.74886052,14173.919135999999,28948.66799652,0,null,0,null,28948.66799652,null,0,null,0,null,null,7481.6642473495185]
["1","03","02","04","03","34","MCOR PLC - Dump                                             ",136,13182,14774.74886052,14173.919135999999,28948.66799652,null,136,13182,14774.74886052,14173.919135999999,28948.66799652,0,null,0,null,28948.66799652,null,0,null,0,null,null,7481.6642473495185]
["1","03","02","04","03","35","MCOR Bulk Dump                                              ",4,8000,247.5261681551999,8601.984,8849.5101681552,null,4,8000,247.5261681551999,8601.984,8849.5101681552,0,null,0,null,8849.5101681552,null,0,null,0,null,null,1782.2783420388002]
["1","03","02","04","03","36","Rack Accessories - LTU_1 (bld 2.1)                          ",1,640,61.88154203879998,688.15872,750.0402620387999,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","03","02","04","03","37","Rack Accessories - LTU_2 (bld 2.2)                          ",1,640,61.88154203879998,688.15872,750.0402620387999,null,1,640,61.88154203879998,688.15872,750.0402620387999,0,null,0,null,750.0402620387999,null,0,null,0,null,null,153.10212950969998]
["1","03","02","04","03","38","Rack Accessories - LTU_3 (bld 2.3)                          ",1,640,61.88154203879998,688.15872,750.0402620387999,null,1,640,61.88154203879998,688.15872,750.0402620387999,0,null,0,null,750.0402620387999,null,0,null,0,null,null,153.10212950969998]
["1","03","02","04","04","  ","Controls & Power Supply                                     ",7234,1204675,497464.29208185547,1291712.142990476,1566619.0628818558,null,5462.1,942725,369990.35242502147,1013663.1708000001,1383653.523225022,0,null,59186.08758248999,null,1265682.1756142112,null,58785.26002831965,null,0,null,null,345913.3808062555]
["1","03","02","05","  ","  ","Controls - LLRF                                             ",4452,375000,396652.95093892084,406992.1204799999,803645.0714189209,null,4452,375000,396652.95093892084,406992.1204799999,803645.0714189209,0,null,0,null,464941.25753383065,null,338703.81388509006,null,0,null,null,200911.26785473022]
["1","03","02","05","01","  ","Solid State Sub-Booster 5x",216,135000,16488.238309031804,148932.60048,165420.8387890318,null,216,135000,16488.238309031804,148932.60048,165420.8387890318,0,null,0,null,6329.7643679424,null,159091.0744210894,null,0,null,null,41355.20969725795]
["1","03","02","05","03","  ","L2/L3 RF Distribution",1200,120000,105273.3065265094,129029.76,234303.0665265094,null,1200,120000,105273.3065265094,129029.76,234303.0665265094,0,null,0,null,199419.01261138657,null,34884.053915122844,null,0,null,null,58575.76663162735]
["1","03","02","05","04","  ","Beam Phase Measurement 2x",486,25000,42237.07137708333,26881.2,69118.27137708334,null,486,25000,42237.07137708333,26881.2,69118.27137708334,0,null,0,null,56309.63934615659,null,12808.632030926745,null,0,null,null,17279.567844270834]
["1","03","02","05","05","  ","Sector 24 Rack Electrical Crate / IOC / EVG",320,70000,29121.494121287567,75267.36,104388.85412128754,null,320,70000,29121.494121287567,75267.36,104388.85412128754,0,null,0,null,99972.1675513198,null,4416.686569967759,null,0,null,null,26097.213530321886]
["1","03","02","05","06","  ","Sector 24 T-Cav",358,15000,27443.326580287194,16128.72,43572.0465802872,null,358,15000,27443.326580287194,16128.72,43572.0465802872,0,null,0,null,43572.0465802872,null,0,null,0,null,null,10893.0116450718]
["1","03","02","05","07","  ","Sector 29/30 Controls (PACs & PADs)",280,10000,22657.626249983994,10752.48,33410.106249984,null,280,10000,22657.626249983994,10752.48,33410.106249984,0,null,0,null,33410.106249984,null,0,null,0,null,null,8352.526562496]
["1","03","02","05","10","  ","RF Stability / Feedback",1048,0,104975.46264053736,0,104975.46264053736,null,1048,0,104975.46264053736,0,104975.46264053736,0,null,0,null,8862.106943010735,null,96113.35569752661,null,0,null,null,26243.86566013434]
["1","03","02","05","11","  ","System Documentation",544,0,48456.42513420014,0,48456.42513420014,null,544,0,48456.42513420014,0,48456.42513420014,0,null,0,null,17066.413883743444,null,31390.011250456693,null,0,null,null,12114.106283550034]
["1","03","02","06","  ","  ","Controls - E-Beam Diagnostic                                ",8240,847956,726792.4647244549,908292.0066079998,1635084.4713324576,null,5521.8,650704,490615.25514641247,699425.6673919997,1190040.9225384134,0,null,17292.888262399996,null,951146.4283143267,null,221601.60596168565,null,0,null,null,280061.40176761954]
["1","03","02","06","01","  ","Controls - Wire Scanners                                    ",1400,85320,119460.80729842692,91740.15936,211200.96665842689,null,1040,65880,89361.93518943319,70837.33824,160199.27342943315,0,null,0,null,111450.46914843867,null,48748.804280994504,null,0,null,null,32039.854685886632]
["1","03","02","06","02","  ","Controls - BPMs                                             ",3900,391476,349477.27947307,420356.91864000016,769834.19811307,null,2977,370305,269292.25673272,398169.7106400001,667461.9673727201,0,null,0,null,511667.8006613695,null,155794.1667113507,null,0,null,null,166865.49184318003]
["1","03","02","06","03","  ","Controls - Toroids                                          ",432,51400,37970.654172105606,55267.7472,93238.4013721056,null,288,51400,25313.7694480704,55267.7472,80581.5166480704,0,null,0,null,80581.5166480704,null,0,null,0,null,null,20145.3791620176]
["1","03","02","06","04","  ","Controls - Stoppers                                         ",240,19500,21035.5615131552,20708.48,41744.04151315519,null,112,10000,9889.8485583744,10752.48,20642.328558374404,0,null,0,null,20642.328558374404,null,0,null,0,null,null,4676.720539593601]
["1","03","02","06","05","  ","Controls - Profile Monitors                                 ",342,143143,30123.520658345504,151796.67339199997,181920.19405034542,null,216,40859,19114.545310931502,43933.558032,63048.10334293151,0,null,0,null,59817.8091612168,null,3230.294181714705,null,0,null,null,13614.271718132877]
["1","03","02","06","06","  ","Controls - E/O Diagnostics                                  "]
["1","03","02","06","07","  ","Controls - Bunch Length Monitors                            ",528,27600,44982.88617335041,29676.8448,74659.7309733504,null,264,12800,22546.266692083198,13763.1744,36309.4410920832,0,null,0,null,36309.4410920832,null,0,null,0,null,null,8416.0827530208]
["1","03","02","06","08","  ","Controls - Beam Loss Monitors                               "]
["1","03","02","06","09","  ","Controls - Single Beam Dump                                 ",240,19500,21000.1015578816,20708.48,41708.5815578816,null,182.4,10000,16041.0255546816,10752.48,26793.505554681604,0,null,1921.6912175999996,null,24871.814337081603,null,0,null,0,null,null,6214.514788670401]
["1","03","02","06","10","  ","Controls - E Beam Dump                                      ",240,19500,21000.1015578816,20708.48,41708.5815578816,null,230.4,18900,20163.3313818816,20079.68,40243.0113818816,0,null,15371.197044800001,null,24871.814337081603,null,0,null,0,null,null,9136.731245470399]
["1","03","02","06","11","  ","Controls - Protection Collimator                            ",361,19957,33903.79203414342,21458.724336,55362.51637014342,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","03","02","06","12","  ","Controls - Movable Collimator                               ",557,70560,47837.76028609446,75869.49888,123707.25916609445,null,212,70560,18892.276278236466,75869.49888,94761.77515823644,0,null,0,null,80933.43437061076,null,13828.340787625697,null,0,null,null,18952.355031647294]
["1","03","02","06","13","  ","Controls - X-Band Accel Structure                           "]
["1","03","02","08","  ","  ","Controls - Timing                                           ",0,153400,0,164943.0432,164943.0432,null,0,129800,0,139567.19040000002,139567.19040000002,0,null,0,null,139567.19040000002,null,0,null,0,null,null,34891.797600000005]
["1","03","02","09","  ","  ","Controls - Vacuum                                           ",2908,148604,247322.81046113494,158998.523104,406321.333565135,null,2248,119698,192898.43545616136,128705.03510400001,321603.47056016134,0,null,0,null,236642.09947815133,null,84961.37108200998,null,0,null,null,75217.20455684034]
["1","03","02","09","01","  ","Controls - Vacuum Instrumentation & Interlocks              ",2908,148604,247322.81046113494,158998.523104,406321.333565135,null,2248,119698,192898.43545616136,128705.03510400001,321603.47056016134,0,null,0,null,236642.09947815133,null,84961.37108200998,null,0,null,null,75217.20455684034]
["1","03","02","09","02","  ","Controls - Vacuum Pump Power Supplies                       "]
["1","03","02","10","  ","  ","Software & Controls Infrastructure                          ",810,368600,75467.03483043646,394292.81279999996,469759.84763043653,null,760.2,293600,69901.38988702846,315692.81279999996,385594.20268702856,0,null,29920.907215761403,null,355673.29547126713,null,0,null,0,null,null,212076.81147786565]
["1","03","02","10","04","  ","Data Communications                                         "]
["1","03","02","10","05","  ","Computers                                                   ",810,368600,75467.03483043646,394292.81279999996,469759.84763043653,null,760.2,293600,69901.38988702846,315692.81279999996,385594.20268702856,0,null,29920.907215761403,null,355673.29547126713,null,0,null,0,null,null,212076.81147786565]
["1","03","03","  ","  ","  ","Linac Magnets & Supports                                    ",6646,1239404,598309.0652182347,1293233.2511999996,1891542.3164182345,null,4160.3,1141435,376590.94187293213,1190453.4283999996,1567044.3702729314,0,null,31697.991386140955,null,1068225.5342356793,null,467120.84465111146,null,0,null,null,231717.77269568908]
["1","03","03","01","  ","  ","Bend Magnet (BX1_BC1)                                       ",120,44350,10950.70729924208,46478.8,57429.50729924208,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","03","03","02","  ","  ","Bend Magnet (BX3_LTU)                                       ",460,93000,39893.508045648,97891.12,137784.628045648,null,405.8,92750,35206.67820550896,97622.308,132828.98620550893,0,null,28000,null,104828.98620550895,null,0,null,0,null,null,26565.797241101798]
["1","03","03","03","  ","  ","Bend Magnet (BX2_BC2)                                       ",160,97400,13629.881084687999,104729.1552,118359.036284688,null,160,97400,13629.881084687999,104729.1552,118359.036284688,0,null,0,null,118359.036284688,null,0,null,0,null,null,7962.4339769376]
["1","03","03","04","  ","  ","Bend Magnet (BY_LTU)                                        ",512,60000,44903.97272056319,64514.88,109418.85272056321,null,180.8,59000,15688.658942303042,63439.632,79128.29094230305,0,null,0,null,79128.29094230305,null,0,null,0,null,null,11869.243641345456]
["1","03","03","05","  ","  ","Quad Magnet (Quad_LTU)                                      ",420,578000,35968.631375750396,590716.912,626685.5433757504,null,200,577775,16619.0740881912,590474.9812,607094.0552881912,0,null,0,null,194557.0639281912,null,412536.99136,null,0,null,null,73376.2786932287]
["1","03","03","07","  ","  ","Quad Magnet (QE_BC1/BC2)                                    ",320,49644,25961.40059223724,52026.912000000004,77988.31259223726,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","03","03","08","  ","  ","Corrector Magnet (Type 4_LTU/E-Dump)                        ",760,0,70529.87930702399,0,70529.87930702399,null,558,0,51117.177250836,0,51117.177250836,0,null,0,null,51117.177250836,null,0,null,0,null,null,10223.4354501672]
["1","03","03","09","  ","  ","Bend Magnet (BYD_E-Dump)                                    ",420,200000,37204.5838931362,215049.6,252254.18389313619,null,104.4,200000,9101.09537084005,215049.6,224150.69537084008,0,null,197.45400069358976,null,223953.24137014648,null,0,null,0,null,null,41794.69789966354]
["1","03","03","10","  ","  ","Quad Magnet (E-Dump)                                        ",520,16000,46240.019550576,17203.968,63443.987550576,null,130,14250,11526.530775804,15322.284,26848.814775804,0,null,0,null,26848.814775804,null,0,null,0,null,null,4027.3222163705996]
["1","03","03","11","  ","  ","Bend Magnet (BYPM_LTU)                                      ",822,53010,74335.6753545168,53010,127345.6753545168,null,690.9,53010,62437.424626002954,53010,115447.42462600296,0,null,0,null,62437.424626002954,null,53010,null,0,null,null,17317.113693900443]
["1","03","03","12","  ","  ","Bend Magnet (BYKIK_LTU)                                     ",412,5000,38467.907864171706,5376.24,43844.147864171704,null,334.4,4750,31277.857232107523,5107.428,36385.285232107526,0,null,0,null,34811.43194099604,null,1573.853291111485,null,0,null,null,5457.792784816128]
["1","03","03","13","  ","  ","Bend Magnet (BYW_LTU)                                       ",480,2000,42930.303696864,2150.496,45080.799696864,null,480,2000,42930.303696864,2150.496,45080.799696864,0,null,0,null,45080.799696864,null,0,null,0,null,null,6762.1199545296]
["1","03","03","14","  ","  ","BXKIK LINAC TCAV Screen Kicker                              ",920,5000,86345.078733216,5376.24,91721.318733216,null,616,4500,58055.5240631856,4838.616,62894.1400631856,0,null,0,null,62894.1400631856,null,0,null,0,null,null,9434.121009477838]
["1","03","03","15","  ","  ","Muon Toroid (E-Dump)                                        ",320,36000,30947.51570060057,38708.928,69656.44370060058,null,300,36000,29000.73653660057,38708.928,67709.66453660057,0,null,3500.5373854473664,null,64209.1271511532,null,0,null,0,null,null,16927.416134150142]
["1","03","04","  ","  ","  ","Linac Vacuum Subsystem                                      ",9446,1183266,870251.326830892,1256704.8384960003,2063343.0914068923,null,5823.35,1117266,544026.788145937,1187100.870496,1731127.6586419377,0,null,936.8339428799998,null,1585256.1464138308,null,144934.67828522716,null,0,null,null,361530.8997076339]
["1","03","04","02","  ","  ","Linac Beamline Vacuum System                                ",914,115000,83306.870676144,122291.12,205597.990676144,null,322,59000,29541.8653066296,63439.632,92981.49730662961,0,null,0,null,92981.49730662961,null,0,null,0,null,null,18596.299461325918]
["1","03","04","03","  ","  ","BC1 Vacuum System                                           ",80,0,7253.558327999999,0,7253.558327999999,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","03","04","04","  ","  ","BC2 Vacuum System                                           ",1600,275000,143231.2541757244,295693.2,438924.4541757245,null,576,275000,51891.1208006112,295693.2,347584.3208006113,0,null,0,null,347584.3208006113,null,0,null,0,null,null,104275.29624018336]
["1","03","04","05","  ","  ","Linac to Undulator (LTU) Vacuum System                      ",3014,365612,278321.22134018294,378803.57638399996,598970.7977241828,null,2348,365612,218862.35667001884,378803.57638399996,597665.9330540188,0,null,936.8339428799998,null,503345.41601295304,null,93383.68309818575,null,0,null,null,102858.3526654135]
["1","03","04","06","  ","  ","Dumpline Vacuum System                                      ",3394,97654,315547.5619762522,105002.268192,420549.83016825217,null,2199.35,87654,207473.80994695213,94249.78819199999,301723.5981389521,0,null,0,null,280834.0193836402,null,20889.578755311857,null,0,null,null,57566.48947236597]
["1","03","04","07","  ","  ","Vacuum System Undulator Interface                           "]
["1","03","04","07","01","  ","Entrance Section Assembly                                   "]
["1","03","04","07","02","  ","Exit Section Assembly                                       "]
["1","03","04","08","  ","  ","LTU/BSY& Cold Trap Vacuum System                            ",444,330000,42590.860334588615,354914.67392,392046.46033458854,null,378,330000,36257.63542172541,354914.67392,391172.3093417253,0,null,0,null,360510.89290999586,null,30661.41643172955,null,0,null,null,78234.46186834508]
["1","03","05","  ","  ","  ","Linac Electron Diagnostics Summary                          ",7737,1419339,730131.5832574727,1481759.279391811,2188259.0028254744,null,6297.8,1273809,598611.4129136307,1326537.6962576937,1925149.1091713267,0,null,3141.9236844290654,null,1560372.1006443875,null,361635.08484251035,null,0,null,null,404507.3184539188]
["1","03","05","01","  ","  ","Wire Scanners (11) Summary                                  ",154,169279,14822.145314244,182016.906192,196839.051506244,null,154,138279,14822.145314244,148684.218192,163506.363506244,0,null,0,null,163506.363506244,null,0,null,0,null,null,24525.9545259366]
["1","03","05","02","  ","  ","Beam Position Monitors                                      ",637,200000,64975.07124582869,201209.5535962353,255215.07124582873,null,498.5,195000,53274.719279558085,195969.5535962353,249244.2728757934,0,null,0,null,7116.2394573864885,null,242128.0334184069,null,0,null,null,49848.854575158664]
["1","03","05","02","01","  ","BPM - Standard  Linac (4) Summary                           ",8,0,672,0,672,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","03","05","02","02","  ","BPM - RF (10) Summary                                       "]
["1","03","05","02","03","  ","BPM - FFTB (12) Summary                                     ",579,195000,60160.49406582869,195969.5535962353,245160.49406582874,null,498.5,195000,53274.719279558085,195969.5535962353,249244.2728757934,0,null,0,null,7116.2394573864885,null,242128.0334184069,null,0,null,null,49848.854575158664]
["1","03","05","02","04","  ","BPM - Large Aperture (2) Summary                            ",50,5000,4142.57718,5240,9382.57718,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","03","05","03","  ","  ","Toroid Beam Current Monitor (10) Summary                    ",232,116000,20131.829144831998,124728.768,144860.59714483202,null,92,51400,7768.56891155616,55267.7472,63036.31611155616,0,null,0,null,63036.31611155616,null,0,null,0,null,null,18910.894833466846]
["1","03","05","04","  ","  ","Beam Stoppers (4) Summary                                   ",539,12000,51820.825007538,12902.976,64723.80100753799,null,228.75,12000,24708.928228787703,12902.976,37611.904228787695,0,null,0,null,37611.904228787695,null,0,null,0,null,null,7522.380845757541]
["1","03","05","05","  ","  ","Profile Monitors (7 OTR-3 PHOSPHOR SCREEN-1 YAG)            ",840,494000,81060.997804272,509350.592,590411.5898042719,null,840,490680,81060.997804272,505780.76863999997,586841.7664442719,0,null,0,null,586841.7664442719,null,0,null,0,null,null,117368.35328885443]
["1","03","05","06","  ","  ","E/O Bunch Length Monitors (1) Summary                       "]
["1","03","05","07","  ","  ","CSR/OTR/CTR Bunch Length Monitors (5) Summary               ",1658,91050,160364.77978220026,96782.8,257147.5797822003,null,1237.3,50000,118566.0605875728,53762.4,172328.4605875728,0,null,1559.9063999999998,null,170768.5541875728,null,0,null,0,null,null,60314.96120565048]
["1","03","05","08","  ","  ","Beam Loss Monitors                                          ",591,43100,55555.419244062,46343.188799999996,101898.60804406198,null,510,43100,48111.417735412804,46343.188799999996,94454.60653541278,0,null,0,null,94403.43617452389,null,51.17036088888889,null,0,null,null,14168.19098031192]
["1","03","05","08","01","  ","PIC Beam Loss Monitors (10) Summary                         ",262,24050,24102.1441842156,25859.7144,49961.858584215595,null,237,24050,21605.3999063856,25859.7144,47465.11430638559,0,null,0,null,47465.11430638559,null,0,null,0,null,null,7119.76714595784]
["1","03","05","08","02","  ","PLIC Beam Loss Monitors (2) Summary                         ",329,19050,31453.275059846397,20483.4744,51936.7494598464,null,273,19050,26506.017829027194,20483.4744,46989.49222902719,0,null,0,null,46938.3218681383,null,51.17036088888889,null,0,null,null,7048.42383435408]
["1","03","05","09","  ","  ","Single Beam Dump (1) Summary                                ",551,8950,49663.8563825016,9623.4696,59287.3259825016,null,537,8950,48362.4970796448,9623.4696,57985.9666796448,0,null,0,null,57985.9666796448,null,0,null,0,null,null,20295.08833787568]
["1","03","05","10","  ","  ","Electron Beam Dump (1) Summary                              ",763,12950,69463.89907371,13924.4616,83388.36067370999,null,491.35,12950,45658.343001137226,13924.4616,59582.80460113722,0,null,0,null,59582.80460113722,null,0,null,0,null,null,11916.560920227446]
["1","03","05","11","  ","  ","Protection Collimators (5) Summary                          ",968,74200,89452.58380763188,80052.4277824,162819.2151036319,null,968,74200,89452.58380763188,80052.4277824,169505.01159003185,0,null,0,null,50049.13052681733,null,119455.88106321453,null,0,null,null,25425.751738504783]
["1","03","05","12","  ","  ","Movable Collimators (7x,3y) Summary                         ",437,174560,40275.251494430406,179824.6198211765,214123.36157443037,null,411.8,174000,37730.46337043041,179226.96884705883,216957.4322174892,0,null,1582.0172844290657,null,215375.41493306015,null,0,null,0,null,null,43391.486443497844]
["1","03","05","13","  ","  ","Safety Electron Dump (1) Summary                            ",367,23250,32544.924956222403,24999.516,57544.440956222395,null,329.1,23250,29094.687793383124,24999.516,54094.203793383116,0,null,0,null,54094.203793383116,null,0,null,0,null,null,10818.840758676624]
["1","03","05","14","  ","  ","Charge Monitor (Entrance/Exit Assembly)                     "]
["1","03","06","  ","  ","  ","Linac RF Subsystem                                          ",1228,244250,130454.7193825592,274898.7927517022,252678.58388255915,null,0,14500,0,16645.7804956383,16645.7804956383,0,null,1398.2885100967633,null,15247.491985541536,null,0,null,0,null,null,1608.0022822127662]
["1","03","06","02","  ","  ","S-Band High Power System                                    ",850,56250,86678.62989556801,58950,145628.629895568,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","03","06","03","  ","  ","S-Band Structures                                           "]
["1","03","06","04","  ","  ","X-Band Low Level System                                     ",378,188000,43776.08948699116,215948.79275170216,107049.95398699118,null,0,14500,0,16645.7804956383,16645.7804956383,0,null,1398.2885100967633,null,15247.491985541536,null,0,null,0,null,null,1608.0022822127662]
["1","03","06","05","  ","  ","X-Band High Power System                                    "]
["1","03","06","05","01","  ","X-Band HP Klystron                                          "]
["1","03","06","05","02","  ","X-Band HP Modulator                                         "]
["1","03","06","05","03","  ","X-Band HP Waveguide System                                  "]
["1","03","06","06","  ","  ","X-Band Structures                                           "]
["1","03","06","07","  ","  ","RF Distribution System                                      "]
["1","03","06","07","01","  ","Modulator Refurbishment                                     "]
["1","03","06","07","02","  ","Solid State Sub Booster                                     "]
["1","03","06","07","03","  ","IPA Modifications                                           "]
["1","03","06","07","04","  ","Klystron Controls Interfaces                                "]
["1","03","06","07","05","  ","Bunch Length Electronics                                    "]
["1","03","06","07","06","  ","RF Phase Measurements                                       "]
["1","03","06","07","07","  ","RF Distribution L2 & L3                                     "]
["1","03","06","07","08","  ","RF Fiber Optics Electronics System                          "]
["1","03","06","07","09","  ","RF Stability                                                "]
["1","03","07","  ","  ","  ","Linac Installation & Alignment                              ",33456,1612990,3035743.746363037,1645463.284342857,3856354.01356304,null,24692,1145000,2279209.911899299,1172238.1672,3451448.079099299,0,null,0,null,1109111.1179468634,null,2342336.9611524357,null,0,null,null,640268.4254435863]
["1","03","07","01","  ","  ","Linac L01 System Installation & Alignment                   ",30,20000,2653.389582,20960,23613.389582,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","03","07","02","  ","  ","Linac BC1 System Installation & Alignment                   ",90,4400,7960.168745999999,4611.2,12571.368746,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","03","07","03","  ","  ","Linac L02 System Installation & Alignment                   "]
["1","03","07","04","  ","  ","Linac BC2 System Installation & Alignment                   "]
["1","03","07","05","  ","  ","Linac L03 System Installation & Alignment                   "]
["1","03","07","06","  ","  ","Linac LTU System Installation & Alignment                   ",8336,175000,749194.765579252,192361.86719999998,941556.6327792522,null,7688,156250,694815.8678112522,172200.9672,867016.8350112522,0,null,0,null,30914.235159231575,null,836102.5998520206,null,0,null,null,216754.20875281305]
["1","03","07","07","  ","  ","Linac E-Dump System Installation & Alignment                ",5732,200000,502559.68449721887,213940.21714285715,690046.8844972189,null,5732,150000,502559.68449721887,161287.2,663846.8844972189,0,null,0,null,161287.2,null,502559.68449721887,null,0,null,null,165961.72112430472]
["1","03","07","10","  ","  ","LINAC  Installation 2006 Shut Down                          ",7828,374840,677062.4663677391,374840,1019502.466367739,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","03","07","10","01","  ","Beamline Equip Removal L01 thru BC1 Out                     ",2748,0,232103.18559447274,0,232103.18559447274,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","03","07","10","02","  ","Gallery Waveguide Installation                              ",2632,164600,236855.41837093027,164600,401455.41837093025,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","03","07","10","03","  ","Beamline Equip Installation L01 thru BC1 Out                ",2448,48500,208103.86240233592,48500,256603.86240233586,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","03","07","10","04","  ","2006 Linac Controls Install and Checkout Gallery to Linac B ",0,107640,0,107640,86240,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","03","07","10","05","  ","2006 Linac Controls Install and Checkout L01 to BC1         ",0,54100,0,54100,43100,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","03","07","20","  ","  ","LINAC Installation 2007 Shut Down                           ",11440,838750,1096313.2715908284,838750,1169063.271590828,null,11272,838750,1081834.3595908284,838750,1920584.3595908284,0,null,0,null,916909.6827876314,null,1003674.6768031964,null,0,null,null,257552.49556646953]
["1","03","07","20","01","  ","Beamline Equip Removal L02, L03 and BC2                     ",2908,0,274214.4945122198,0,274214.4945122198,null,2908,0,274214.4945122198,0,274214.4945122198,0,null,0,null,71488.04184572969,null,202726.4526664902,null,0,null,null,82264.34835366588]
["1","03","07","20","02","  ","Beamline Equip Installation L02, L03 and BC2                ",3660,72750,320056.6377497852,72750,392806.6377497852,null,3492,72750,305577.72574978526,72750,378327.7257497852,0,null,0,null,128212.88469600963,null,250114.8410537756,null,0,null,null,113498.31772493556]
["1","03","07","20","03","  ","2007 Linac Controlls Install and Checkout                   ",2748,766000,296076.0410359301,766000,296076.0410359301,null,2748,766000,296076.0410359301,766000,1062076.0410359302,0,null,0,null,685109.9366075946,null,376966.1044283355,null,0,null,null,0]
["1","03","07","20","04","  ","Linac Undulator Interface                                   ",2124,0,205966.09829289268,0,205966.09829289268,null,2124,0,205966.09829289268,0,205966.09829289268,0,null,0,null,32098.819638297595,null,173867.27865459508,null,0,null,null,61789.82948786782]
["1","04","  ","  ","  ","  ","UNDULATOR SYSTEM                                            ",80564,11858902,7248919.478542959,8587678.06610936,14900632.32351888,null,55637.982,8648255.15,4890434.976922504,5257698.212697829,10148133.189620303,0,null,136671.65129145916,null,7287200.345530983,null,2724261.1927978713,null,0,null,null,2148753.202891954]
["1","04","01","  ","  ","  ","Undulator System Management & Integration                   ",18663,372744,1738084.4963150905,445530.7751115055,1849309.7763150905,null,7702.844,255120,650582.380652776,288903.47655057657,939485.8572033526,0,null,65577.15643713054,null,653979.9991723918,null,219928.70159383022,null,0,null,null,0]
["1","04","01","01","  ","  ","Undulator System Management                                 ",18663,254365,1738084.4963150905,268617.4518843931,1849309.7763150905,null,7702.844,205500,650582.380652776,219752.4518843931,870334.8325371691,0,null,57997.526492782476,null,608626.4757348993,null,203710.83030948738,null,0,null,null,0]
["1","04","01","01","01","  ","Undulator System Management - Technical                     ",17029,37500,1558676.5132411567,46530.819884393066,1558676.5132411567,null,7447.424,37500,622582.993046531,46530.819884393066,669113.8129309241,0,null,50997.67959122124,null,448090.93503021554,null,170025.19830948737,null,0,null,null,0]
["1","04","01","01","02","  ","ANL Project Support                                         ",1634,216865,179407.98307393357,222086.632,290633.26307393354,null,255.42,168000,27999.387606244956,173221.632,201221.01960624495,0,null,6999.846901561239,null,160535.54070468372,null,33685.632,null,0,null,null,0]
["1","04","01","02","  ","  ","Undulator System Materials & Supplies                       ",0,88379,0,146040.69218886102,0,null,0,24870,0,43681.104059626094,43681.104059626094,0,null,4749.638765841696,null,28419.96966446261,null,10511.495629321787,null,0,null,null,0]
["1","04","01","02","01","  ","Undulator System M&S - General                              ",0,41368,0,64280.995734168995,0,null,0,24870,0,43681.104059626094,43681.104059626094,0,null,4749.638765841696,null,28419.96966446261,null,10511.495629321787,null,0,null,null,0]
["1","04","01","02","02","  ","Undulator System Travel                                     ",0,47011,0,81759.696454692,0,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","04","01","03","  ","  ","Undulator System Reviews and Workshops                      ",0,30000,0,30872.631038251362,0,null,0,24750,0,25469.920606557374,25469.920606557374,0,null,2829.9911785063746,null,16933.553773029947,null,5706.375655021051,null,0,null,null,0]
["1","04","02","  ","  ","  ","Controls                                                    ",1488,290100,139598.3904198384,312572.443104,452170.8335238384,null,1488,290100,139598.3904198384,312572.443104,452170.8335238384,0,null,0,null,349448.6452506279,null,102722.18827321056,null,0,null,null,0]
["1","04","02","01","  ","  ","Controls Management and Integration                         "]
["1","04","02","01","03","  ","Software Interface with SLAC                                "]
["1","04","02","01","04","  ","Undulator Cable, Tray, and Rack Layout                      "]
["1","04","02","01","05","  ","Miscellaneous Controls                                      "]
["1","04","02","02","  ","  ","Motion                                                      "]
["1","04","02","02","01","  ","Undulator Cam Movers                                        "]
["1","04","02","02","01","01","Motor Interface                                             "]
["1","04","02","02","01","02","Encoder Interface                                           "]
["1","04","02","02","01","03","Motor Driver                                                "]
["1","04","02","02","01","04","Cabling                                                     "]
["1","04","02","02","01","05","Integrate components                                        "]
["1","04","02","02","02","  ","Motion Test Stand                                           "]
["1","04","02","02","06","  ","Scanning Wire Motion                                        "]
["1","04","02","02","06","01","Motor Interface                                             "]
["1","04","02","02","06","02","Encoder Interface                                           "]
["1","04","02","02","06","03","Motor Driver                                                "]
["1","04","02","02","06","04","Cabling                                                     "]
["1","04","02","02","06","05","Integrate components                                        "]
["1","04","02","02","07","  ","Translation Stage Motion                                    "]
["1","04","02","02","07","01","Motor Interface                                             "]
["1","04","02","02","07","03","Motor Driver                                                "]
["1","04","02","02","07","04","Cabling                                                     "]
["1","04","02","02","07","05","Integrate components                                        "]
["1","04","02","03","  ","  ","Signal Analysis                                             "]
["1","04","02","03","01","  ","RFBPM                                                       "]
["1","04","02","03","01","02","Signal Acquisition                                          "]
["1","04","02","03","01","03","Timing interface                                            "]
["1","04","02","03","01","04","Cabling                                                     "]
["1","04","02","03","01","05","Integrate components                                        "]
["1","04","02","03","02","  ","Charge Monitor                                              "]
["1","04","02","03","02","03","Integrate components                                        "]
["1","04","02","03","03","  ","Beam Finder Wire                                            "]
["1","04","02","03","03","01","BFW Actuator Control                                        "]
["1","04","02","03","03","06","Integrate components                                        "]
["1","04","02","04","  ","  ","Video                                                       "]
["1","04","02","04","01","  ","OTR Monitor                                                 "]
["1","04","02","04","01","01","Camera                                                      "]
["1","04","02","04","01","02","Camera trigger interface                                    "]
["1","04","02","04","01","03","Digitizer                                                   "]
["1","04","02","04","01","04","Timing interface                                            "]
["1","04","02","04","01","05","Cabling                                                     "]
["1","04","02","04","01","06","Integrate components                                        "]
["1","04","02","04","03","  ","Observation station video                                   "]
["1","04","02","04","03","01","Camera                                                      "]
["1","04","02","04","03","02","Camera trigger interface                                    "]
["1","04","02","04","03","03","Multiplexor                                                 "]
["1","04","02","04","03","04","Cabling                                                     "]
["1","04","02","04","03","05","Integrate components                                        "]
["1","04","02","04","03","06","Imaging Test Stand                                          "]
["1","04","02","05","  ","  ","Data Acquisition and Control                                "]
["1","04","02","05","01","  ","Strongback Temperature monitoring                           "]
["1","04","02","05","01","01","Integrate components                                        "]
["1","04","02","06","  ","  ","Vacuum                                                      "]
["1","04","02","06","01","  ","Ion Pump Controller                                         "]
["1","04","02","06","01","01","Integrate components                                        "]
["1","04","02","06","02","  ","RGA                                                         "]
["1","04","02","06","02","01"," Integrate components                                       "]
["1","04","02","07","  ","  ","Machine Protection                                          "]
["1","04","02","07","01","  ","Undulator Beam Loss Monitor Controls                        "]
["1","04","02","07","01","01","Hardware design                                             "]
["1","04","02","07","01","02","Interface components                                        "]
["1","04","02","07","02","  ","Cerenkov Detector                                           "]
["1","04","02","07","02","01","Signal interface                                            "]
["1","04","02","07","03","  ","Gamma Ray Detector                                          "]
["1","04","02","07","03","01","Signal interface                                            "]
["1","04","02","08","  ","  ","Power Supply Controls                                       "]
["1","04","02","10","  ","  ","Undualtor Controls Module                                   "]
["1","04","02","12","  ","  ","Rack and Cables                                             "]
["1","04","02","13","  ","  ","BPM                                                         "]
["1","04","02","14","  ","  ","Long Term Test Prep                                         ",560,0,43631.12031347521,0,43631.12031347521,null,560,0,43631.12031347521,0,43631.12031347521,0,null,0,null,43631.12031347521,null,0,null,0,null,null,0]
["1","04","02","17","  ","  ","Undulator Controls Management                               "]
["1","04","02","20","  ","  ","Undulator Controls - MPS                                    "]
["1","04","02","21","  ","  ","Undulator Controls - Timing                                 ",128,23000,10934.648631121247,25373.702304000002,36308.350935121256,null,128,23000,10934.648631121247,25373.702304000002,36308.350935121256,0,null,0,null,0,null,36308.350935121256,null,0,null,null,0]
["1","04","02","22","  ","  ","Undulator Controls - BPM                                    ",560,104900,64198.20624577113,112793.5152,176991.7214457711,null,560,104900,64198.20624577113,112793.5152,176991.7214457711,0,null,0,null,130753.00720594943,null,46238.71423982169,null,0,null,null,0]
["1","04","02","23","  ","  ","Undulator Controls - Vacuum                                 ",160,162200,14070.077963325963,174405.22559999998,188475.30356332596,null,160,162200,14070.077963325963,174405.22559999998,188475.30356332596,0,null,0,null,175064.51773120317,null,13410.785832122763,null,0,null,null,0]
["1","04","02","24","  ","  ","Undulator Controls - ADS System                             ",80,0,6764.337266144831,0,6764.337266144831,null,80,0,6764.337266144831,0,6764.337266144831,0,null,0,null,0,null,6764.337266144831,null,0,null,null,0]
["1","04","03","  ","  ","  ","Undulator Magnet & Support                                  ",35091,7927039,3126800.2755328277,4478520.438885767,7095596.673052822,null,27116.338000000003,5109489.15,2407712.2772774305,1582343.0698912535,3990055.3471686975,0,null,34715.93100046541,null,2653477.2425655923,null,1301862.1736026225,null,0,null,null,1077759.4412931663]
["1","04","03","01","  ","  ","UND Magnet & Support - Mgmt and Integration                 ",891,0,97830.56615786736,0,97830.56615786736,null,179.388,0,19652.912202472493,0,19652.912202472493,0,null,4974.388565771046,null,14678.523636701448,null,0,null,0,null,null,0]
["1","04","03","02","  ","  ","First Prototype Undulator & Mfg Plan                        "]
["1","04","03","03","  ","  ","1st Article Undulators & Long Lead Procurements             ",2607,1215170,234769.3800649701,783409.0123312883,804096.1300649698,null,2534.9,659581.25,226807.81670630173,227656.62483128835,454464.44153759,0,null,0,null,251536.29284310678,null,202928.14869448324,null,0,null,null,52770.73214237792]
["1","04","03","03","01","  ","Ti Strongback (LLP)                                         ",0,127159,0,127159,127159,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","04","03","03","02","  ","Magnet Blocks (LLP)                                         ",2,422136,215.40268764000004,422136,344015.40268764,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","04","03","03","03","  ","Magnet Poles (LLP)                                          "]
["1","04","03","03","04","  ","Magnet Assembly & Supports - 1st Articles                   ",715,535875,72621.21148580342,98388.27,165858.96148580342,null,644.9,529581.25,64875.050814775095,91930.8825,156805.93331477503,0,null,0,null,156013.54562246735,null,792.3876923076924,null,0,null,null,23520.889997216265]
["1","04","03","03","04","01","Magnet Assembly 1st Article - Vendor A                      "]
["1","04","03","03","04","02","Magnet Assembly 1st Article - Vendor B                      "]
["1","04","03","03","04","03","Support/Mover System - Articles 1 & 2                       ",629,535000,63118.0757125019,97490.52,155458.0757125019,null,563.2,528750,55847.07183013865,91078.02,146925.09183013858,0,null,0,null,146132.7041378309,null,792.3876923076924,null,0,null,null,22038.763774520798]
["1","04","03","03","05","  ","Magnetic Measurement (ANL)                                  ",80,5000,5190.1735423968,5130,10320.1735423968,null,80,5000,5190.1735423968,5130,10320.1735423968,0,null,0,null,10320.1735423968,null,0,null,0,null,null,516.0086771198401]
["1","04","03","03","05","01","Magnetic Measurement (ANL) - Vendor A Und #1                ",80,5000,5190.1735423968,5130,10320.1735423968,null,80,5000,5190.1735423968,5130,10320.1735423968,0,null,0,null,10320.1735423968,null,0,null,0,null,null,516.0086771198401]
["1","04","03","03","05","02","Magnetic Measurement (ANL) - Vendor B Und #2                "]
["1","04","03","03","06","  ","Integrated Single-Undulator Module Test                     ",1810,125000,156742.59234912985,130595.74233128835,156742.59234912985,null,1810,125000,156742.59234912985,130595.74233128835,287338.33468041813,0,null,0,null,85202.57367824262,null,202135.76100217554,null,0,null,null,28733.83346804182]
["1","04","03","03","07","  "," System Test - Two Undulators                               "]
["1","04","03","04","  ","  ","Production Undulator Magnet Assembly & Supports             ",1804,4152964,191154.77375973618,1573001.970600985,1718564.6377597365,null,860,2626694,87672.55315435331,17128.044,104800.59715435332,0,null,0,null,35478.113264864645,null,69322.48388948868,null,0,null,null,22774.54048858833]
["1","04","03","04","01","  ","Production Undulator Assembly - Vendor A                    ",40,97564,4420.063150372801,98020.664,102440.7271503728,null,0,16694,0,17128.044,17128.044,0,null,0,null,17128.044,null,0,null,0,null,null,856.4022]
["1","04","03","04","02","  ","Production Undulator Assembly - Vendor B                    ",840,1255400,92169.27145053005,1284981.3066009851,1331558.47145053,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","04","03","04","03","  ","Production Support/Mover Fabrication/Assembly               ",860,2610000,87672.55315435331,0,87672.55315435331,null,860,2610000,87672.55315435331,0,87672.55315435331,0,null,0,null,18350.06926486465,null,69322.48388948868,null,0,null,null,21918.13828858833]
["1","04","03","04","04","  ","Mu Metal Shield                                             ",64,190000,6892.88600448,190000,196892.88600448,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","04","03","05","  ","  ","Quadrupole Focusing Magnets                                 ",904,391565,92437.06269963816,393801.2930313832,407502.0626996382,null,806,332381.9,81980.0710774291,334506.37837981404,416486.44945724314,0,null,0,null,274417.4071068072,null,142069.0423504359,null,0,null,null,66491.68869115156]
["1","04","03","05","01","  ","Quadrupole Magnets                                          ",622,332565,64915.06415532695,333240.7668965517,379980.064155327,null,568.5,276331.9,59138.14545421704,276973.87855172413,336112.0240059412,0,null,0,null,195397.6068035609,null,140714.41720238025,null,0,null,null,50416.80360089118]
["1","04","03","05","02","  ","Quadrupole Power Supplies                                   "]
["1","04","03","05","03","  ","Quadrupole Stages & Stands                                  ",282,59000,27521.998544311216,60560.52613483147,27521.998544311216,null,237.5,56050,22841.925623212053,57532.49982808989,80374.42545130194,0,null,0,null,79019.80030324629,null,1354.6251480556507,null,0,null,null,16074.88509026039]
["1","04","03","05","04","  ","Quadrupole Cables                                           "]
["1","04","03","06","  ","  ","Undulator Magnetic Measurement Facility (SLAC)              ",27453,1571340,2365734.2136196834,1687268.1629221106,3881688.9971396825,null,21304.05,894832,1846724.6449059567,962012.0226801509,2808736.667586107,0,null,29741.542434694362,null,1976146.550009682,null,802848.57514173,null,0,null,null,897094.6574726328]
["1","04","03","06","01","  ","Undulator MMF Setup                                         ",3248,108890,271237.9030393067,117049.69471999998,388287.5977593067,null,1120,60912,95179.419960048,65495.506175999995,160674.926136048,0,null,0,null,160674.926136048,null,0,null,0,null,null,35716.1444664048]
["1","04","03","06","01","01","Undulator Test Stand Prototype                              "]
["1","04","03","06","01","04","Undulator Test Stand                                        ",136,0,10403.036181599999,0,10403.036181599999,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","04","03","06","01","05","Undulator Fiducialization                                   "]
["1","04","03","06","01","06","Quad Strength and Field Quality                             ",264,4750,20711.32935611258,5073.368,25784.697356112578,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","04","03","06","01","07","Quad Fiducialization System                                 ",276,0,21364.99120122616,0,21364.99120122616,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","04","03","06","01","08","Hall Probe Calibration System                               ",118,0,9106.433592,0,9106.433592,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","04","03","06","01","09","Undulator Handling                                          ",2454,104140,209652.11270836802,111976.32671999998,321628.439428368,null,1120,60912,95179.419960048,65495.506175999995,160674.926136048,0,null,0,null,160674.926136048,null,0,null,0,null,null,35716.1444664048]
["1","04","03","06","02","  ","Fiducialization and Magnetic Measurements (F/MM)            ",16842,147600,1452897.029524356,157935.1265207547,1452897.029524356,null,15184.4,29520,1310427.8972752527,31587.025304150946,1342014.9225794037,0,null,6059.146363374867,null,703023.8682392989,null,632931.9079767298,null,0,null,null,547462.3167479379]
["1","04","03","06","02","01","F/MM Undulator Magnet Sections                              ",14784,0,1277867.731788536,0,1277867.731788536,null,13235,0,1144758.1819394326,0,1144758.1819394326,0,null,0,null,511826.27396270295,null,632931.9079767298,null,0,null,null,483738.18419591326]
["1","04","03","06","02","02","F/MM Quadrupoles                                            ",1508,0,125459.89484158045,0,125459.89484158045,null,1508,0,125459.89484158045,0,125459.89484158045,0,null,0,null,125459.89484158045,null,0,null,0,null,null,43910.96319455336]
["1","04","03","06","02","03","F/MM BPMs                                                   ",0,147600,0,157935.1265207547,0,null,0,29520,0,31587.025304150946,31587.025304150946,0,null,6059.146363374867,null,25527.87894077608,null,0,null,0,null,null,6317.4050608301895]
["1","04","03","06","02","04","F/MM Correctors                                             "]
["1","04","03","06","02","05","F/MM Vacuum Chamber                                         "]
["1","04","03","06","02","06","F/MM Photon Diagnostics Components                          ",362,0,31198.608000000004,0,31198.608000000004,null,253.4,0,21839.025600000004,0,21839.025600000004,0,null,0,null,21839.025600000004,null,0,null,0,null,null,6551.707680000001]
["1","04","03","06","03","  ","Undulator Monitoring                                        ",7363,1314850,641599.2810560203,1412283.3416813556,2040504.3698560207,null,4999.65,804400,441117.3276706549,864929.4911999999,1306046.818870655,0,null,23682.396071319497,null,1112447.7556343353,null,169916.66716500017,null,0,null,null,313916.19625828904]
["1","04","03","06","03","01","Stretched Wire System                                       ",4366,391100,391734.8196321929,419085.3488,810820.168432193,null,3104,338100,284569.7804308782,363541.3488,648111.1292308782,0,null,9390.83105288064,null,521901.14472565835,null,116819.15345233916,null,0,null,null,198381.91718771958]
["1","04","03","06","03","02","Hydrostatic Level System                                    ",2377,452000,200415.61740524237,485949.7488813559,672987.1134052423,null,1564.65,394300,130053.87054956245,423970.2863999999,554024.1569495623,0,null,11057.030481085454,null,489869.612755816,null,53097.51371266099,null,0,null,null,104456.74676461119]
["1","04","03","06","03","03","F/MM BPMs                                                   ",620,471750,49448.844018585,507248.24400000006,556697.088018585,null,331,72000,26493.676690214248,77417.856,103911.53269021426,0,null,3234.5345373534037,null,100676.99815286085,null,0,null,0,null,null,11077.53230595825]
["1","04","03","08","  ","  ","Fixed Supports                                              ",1432,596000,144874.27923091716,41040,185914.27923091716,null,1432,596000,144874.27923091716,41040,185914.27923091716,0,null,0,null,101220.35570443046,null,84693.9235264867,null,0,null,null,38627.82249841467]
["1","04","03","08","01","  ","Fixed Sppt Mgmt & Integration                               "]
["1","04","03","08","02","  ","Fixed Support Design                                        ",1416,560000,143106.25397076804,4104,147210.25397076804,null,1416,560000,143106.25397076804,4104,147210.25397076804,0,null,0,null,62516.33044428133,null,84693.9235264867,null,0,null,null,30887.01744638485]
["1","04","03","08","03","  ","Stabilized Girder Assemblies                                "]
["1","04","03","08","04","  ","Thermal Intercept System                                    "]
["1","04","03","08","05","  ","Thermometry                                                 ",0,12000,0,12312,12312,null,0,12000,0,12312,12312,0,null,0,null,12312,null,0,null,0,null,null,2462.4]
["1","04","03","08","06","  ","Kinematic Girder Support                                    "]
["1","04","03","08","07","  ","Earthquake Bracing                                          ",16,24000,1768.0252601491204,24624,26392.02526014912,null,16,24000,1768.0252601491204,24624,26392.02526014912,0,null,0,null,26392.02526014912,null,0,null,0,null,null,5278.405052029824]
["1","04","03","08","08","  ","Controls and Software                                       "]
["1","04","04","  ","  ","  ","Vacuum System                                               ",7060,1707396,649073.751309826,1751125.063008085,2314341.129661832,null,3943,1525221,357811.16555977805,1567484.3783520001,1925295.5439117788,0,null,26215.321080043963,null,1780065.3262658063,null,119014.8965659289,null,0,null,null,377877.81274941185]
["1","04","04","02","  ","  ","Undulator Vacuum Chamber Assembly                           ",3773,1393550,341214.56961519725,1429213.3170080849,1684570.2019671977,null,2088.2,1215000,187575.22664404803,1249197.632352,1436772.858996048,0,null,0,null,1317831.949376075,null,118940.90961997294,null,0,null,null,287354.57179920963]
["1","04","04","02","01","  ","Prototype Chamber Weldment                                  "]
["1","04","04","02","02","  ","Production Chamber Weldment                                 ",2628,1215000,233719.15365243834,1249197.632352,1482916.7860044385,null,2088.2,1215000,187575.22664404803,1249197.632352,1436772.858996048,0,null,0,null,1317831.949376075,null,118940.90961997294,null,0,null,null,287354.57179920963]
["1","04","04","02","03","  ","Prototype Aluminum Chamber                                  ",1145,178550,107495.41596275917,180015.68465608466,201653.41596275917,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","04","04","03","  ","  ","Beam-line Bellows Module Assembly                           ",870,173197,73609.56236988548,177605.872,251215.43436988545,null,441.2,169572,37829.7504600294,173980.872,211810.62246002935,0,null,1321.6696386712993,null,210488.95282135805,null,0,null,0,null,null,42362.124492005896]
["1","04","04","03","01","  ","Prototype Bellows Module                                    ",238,3625,20669.50243477205,3625,24294.50243477205,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","04","04","03","02","  ","Production Bellows Module                                   ",632,169572,52940.059935113444,173980.872,226920.9319351134,null,441.2,169572,37829.7504600294,173980.872,211810.62246002935,0,null,1321.6696386712993,null,210488.95282135805,null,0,null,0,null,null,42362.124492005896]
["1","04","04","04","  ","  ","Single Undulator Test (SUT) Vacuum                          ",218,0,23537.91630481099,0,23537.91630481099,null,3.6,0,443.92167573577495,0,443.92167573577495,0,null,0,null,369.93472977981247,null,73.98694595596248,null,0,null,null,44.392167573577495]
["1","04","04","05","  ","  ","Short Diagnostic Break (SDB) Assembly                       ",472,43682,48683.90867920174,44817.732,93501.64067920175,null,278,43682,24274.738750993925,44817.732,69092.47075099395,0,null,5566.850448264001,null,63525.62030272994,null,0,null,0,null,null,10363.870612649089]
["1","04","04","06","  ","  ","Long Diagnostic Break (LDB) Assembly                        ",495,40827,44887.02700201918,41888.502,86775.52900201919,null,352,40827,31757.10455641825,41888.502,73645.60655641826,0,null,0,null,73645.60655641826,null,0,null,0,null,null,11046.840983462738]
["1","04","04","07","  ","  ","Entrance Section Assembly                                   ",40,0,4308.0537528,0,4308.0537528,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","04","04","08","  ","  ","Exit Section Assembly                                       ",48,0,5169.664503360001,0,5169.664503360001,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","04","04","09","  ","  ","Baking System                                               ",1144,56140,107663.04908255296,57599.64,165262.6890825529,null,780,56140,75930.42347255294,57599.64,133530.06347255292,0,null,19326.80099310866,null,114203.26247944425,null,0,null,0,null,null,26706.012694510584]
["1","04","05","  ","  ","  ","Diagnostics                                                 ",6240,1561623,563999.9682811535,1599929.346,2157851.3142811526,null,3633,1468325,320515.9285360839,1506394.8447999998,1826910.7733360827,0,null,10163.242773819282,null,1816747.5305622632,null,0,null,0,null,null,378954.6310031285]
["1","04","05","02","  ","  ","Undulator Line Diagnostics (ULD)                            "]
["1","04","05","02","01","  ","ULD Test Station                                            "]
["1","04","05","02","02","  ","ULD Vacuum Chamber                                          "]
["1","04","05","02","03","  ","Positioning Mechanism                                       "]
["1","04","05","02","04","  ","Scanning wire assembly (ULD-SWA)                            "]
["1","04","05","02","05","  ","Optical transition radiation imaging assembly               "]
["1","04","05","02","09","  ","ULD Design & Integration                                    "]
["1","04","05","04","  ","  ","End-of-Undulator(EOU) X-ray and Profile diagnost            "]
["1","04","05","04","01","  ","Prototype Construction and Testing                          "]
["1","04","05","04","02","  ","Bunch Length Monitor-Streak Camera (BLM)                    "]
["1","04","05","04","03","  ","Upstream corrector / separator                              "]
["1","04","05","04","04","  ","Optical Diffraction radiation imaging assembly (            "]
["1","04","05","04","05","  ","X-ray High Resolution monochromator assembly (EO            "]
["1","04","05","04","06","  ","X-ray Imaging High Resolution detector assembly             "]
["1","04","05","04","07","  ","EOU Design and Integration                                  "]
["1","04","05","05","  ","  ","RFBPM                                                       ",2737,1022362,248412.30690983447,1046647.56,1288981.8669098343,null,1644.2,936810.2,150402.36086788235,961060.66,1111463.0208678823,0,null,9228.52768877128,null,1102234.4931791108,null,0,null,0,null,null,222292.60417357652]
["1","04","05","05","01","  ","X-Band Cavity BPM Development                               ",914,66800,86117.81368424834,66878,146917.81368424837,null,238.4,3300,25018.837253611207,3342.9,28361.7372536112,0,null,2923.9453731112803,null,25437.79188049992,null,0,null,0,null,null,5672.347450722241]
["1","04","05","05","02","  ","X-Band Receiver Development                                 ",159,24502,13389.181897140003,24502,37891.181897140006,null,49,2450.2,3854.3823156600006,2450.2,6304.582315660001,0,null,6304.582315660001,null,0,null,0,null,0,null,null,1260.9164631320002]
["1","04","05","05","03","  ","X-Band BPM Production                                       ",1664,931060,148905.3113284464,955267.56,1104172.8713284463,null,1356.8,931060,121529.14129861121,955267.56,1076796.701298611,0,null,0,null,1076796.701298611,null,0,null,0,null,null,215359.34025972226]
["1","04","05","06","  ","  ","Beam Finder Wire                                            ",1192,337261,102048.95743133906,346029.786,448078.7434313391,null,576.4,329514.8,48399.80793939059,338082.1848,386481.9927393907,0,null,0,null,386481.9927393907,null,0,null,0,null,null,57972.2989109086]
["1","04","05","07","  ","  ","Charge Monitor (CM)                                         ",32,0,2734.9512364800003,0,2734.9512364800003,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","04","05","08","  ","  ","Beam Loss Monitoring                                        ",1854,202000,171841.89197872722,207252,379093.8919787273,null,1012.4,202000,85494.836828446,207252,292746.836828446,0,null,934.7150850480002,null,291812.121743398,null,0,null,0,null,null,87824.0510485338]
["1","04","05","09","  ","  ","Radiation Detection Monitor (RDM)                           "]
["1","04","05","10","  ","  ","SIngle Undulator Test (SUT) Diagnostics                     ",25,0,2742.9378244077607,0,2742.9378244077607,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","04","05","11","  ","  ","Supplemental Shielding                                      ",400,0,36218.92290036481,0,36218.92290036481,null,400,0,36218.92290036481,0,36218.92290036481,0,null,0,null,36218.92290036481,null,0,null,0,null,null,10865.676870109442]
["1","04","06","  ","  ","  ","Undulator System Installation and Alignment                 ",12022,0,1031362.596684236,0,1031362.596684236,null,11754.8,0,1014214.8344765846,0,1014214.8344765846,0,null,0,null,33481.60171429883,null,980733.232762286,null,0,null,null,314161.31784625293]
["1","04","06","01","  ","  ","Undulator System Installation and Alignment Inte            ",8232,0,686600.8695743904,0,686600.8695743904,null,8232,0,686600.8695743904,0,686600.8695743904,0,null,0,null,21261.848938848,null,665339.0206355425,null,0,null,null,223950.85496626404]
["1","04","06","01","01","  ","Undulator System                                            ",8232,0,686600.8695743904,0,686600.8695743904,null,8232,0,686600.8695743904,0,686600.8695743904,0,null,0,null,21261.848938848,null,665339.0206355425,null,0,null,null,223950.85496626404]
["1","04","06","02","  ","  ","Control System Installation and Alignment                   ",2272,0,214412.39208554875,0,214412.39208554875,null,2272,0,214412.39208554875,0,214412.39208554875,0,null,0,null,0,null,214412.39208554875,null,0,null,null,53603.09802138719]
["1","04","06","04","  ","  ","Vacuum System Installation and Alignment                    ",1518,0,130349.33502429358,0,130349.33502429358,null,1250.8,0,113201.57281664222,0,113201.57281664222,0,null,0,null,12219.75277545082,null,100981.82004119139,null,0,null,null,36607.364858603185]
["1","04","06","05","  ","  ","Diagnostics System Installation and Alignment               "]
["1","05","  ","  ","  ","  ","X-RAY TRANSPORT & DIAGNOSTICS SYSTEMS                       ",55785,6187640,9215978.514347762,7040465.577435408,14249555.318274165,null,37328.63,5906270,5997070.272829492,6718482.862570713,12715553.135400197,0,null,47029.39994187083,null,9653558.943711678,null,3013364.5132661974,null,1600.2784804595592,null,null,3577484.7071474614]
["1","05","01","  ","  ","  ","System Management & Integration                             ",8839,230350,1616150.5883454373,268806.19392823096,1723615.2106474373,null,4195.55,145250,783069.3184110455,169854.60552643312,952923.9239374786,0,null,26349.87091069641,null,468678.59458854655,null,456295.1799577761,null,1600.2784804595592,null,null,162296.19548153135]
["1","05","01","01","  ","  ","Management                                                  ",8839,230350,1616150.5883454373,268806.19392823096,1723615.2106474373,null,4195.55,145250,783069.3184110455,169854.60552643312,952923.9239374786,0,null,26349.87091069641,null,468678.59458854655,null,456295.1799577761,null,1600.2784804595592,null,null,162296.19548153135]
["1","05","01","01","01","  ","XTOD Management - Technical                                 ",7182,172000,1397885.4999351155,200982.48937517242,1459253.9665351151,null,3477.55,94400,683976.6425443846,110595.54112634483,794572.1836707294,0,null,10361.160610751178,null,403835.4917054354,null,380375.53135454294,null,0,null,null,135077.271224024]
["1","05","01","01","02","  ","LLNL Project Support                                        ",1436,58350,198185.3517333218,67823.70455305857,244281.50743532178,null,718,50850,99092.6758666609,59259.064400088275,158351.74026674917,0,null,15988.710299945227,null,64843.10288311119,null,75919.64860323319,null,1600.2784804595592,null,null,27218.924257507362]
["1","05","01","01","03","  ","Commissioning Coordinator                                   ",221,0,20079.736677,0,20079.736677,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","05","02","  ","  ","  ","Controls                                                    ",2019,850000,373137.3905663793,928530,1301667.3905663793,null,1447,850000,264017.2513324154,928530,1192547.2513324153,0,null,0,null,1120867.6315458568,null,71679.61978655859,null,0,null,null,238509.45026648307]
["1","05","02","01","  ","  ","Controls - EPICS                                            ",2019,850000,373137.3905663793,928530,1301667.3905663793,null,1447,850000,264017.2513324154,928530,1192547.2513324153,0,null,0,null,1120867.6315458568,null,71679.61978655859,null,0,null,null,238509.45026648307]
["1","05","02","02","  ","  ","Motor Controls                                              "]
["1","05","02","03","  ","  ","Controls - Vacuum                                           "]
["1","05","03","  ","  ","  ","Mechanical & Vacuum Subsystem                               ",7565,1446190,1260068.768701044,1651234.3716315592,1794832.940829443,null,5508.48,1432790,925771.2321102355,1636050.650197931,2561821.882308166,0,null,14739.225629316985,null,2241711.05219704,null,305371.6044818106,null,0,null,null,576141.559042006]
["1","05","03","01","  ","  ","Vacuum Systems Engineering                                  ",1416,43100,212973.33745685435,49653.936112460186,239965.00277285435,null,574.48,29700,85693.24018747464,34470.214678831864,120163.4548663065,0,null,13950.08958593237,null,56110.360334527984,null,50103.00494584616,null,0,null,null,22831.056424598235]
["1","05","03","02","  ","  ","Mech/Vac Front End                                          ",3420,364090,584800.2155162424,416663.70681239996,1001463.9223286421,null,3112.9,364090,530789.3798631656,416663.70681239996,947453.0866755652,0,null,358.69820153846155,null,791533.2850249613,null,155561.1034490654,null,0,null,null,236863.2716688913]
["1","05","03","03","  ","  ","Mech/Vac Near Hall                                          ",847,209000,143161.54966142055,238424.2483082927,143161.54966142055,null,687.1,209000,115401.62739680518,238424.2483082927,353825.87570509786,0,null,215.2189209230769,null,314258.8309187943,null,39351.8258653805,null,0,null,null,91994.72768332546]
["1","05","03","03","01","  ","Mech/Vac Near Hall                                          ",847,209000,143161.54966142055,238424.2483082927,143161.54966142055,null,687.1,209000,115401.62739680518,238424.2483082927,353825.87570509786,0,null,215.2189209230769,null,314258.8309187943,null,39351.8258653805,null,0,null,null,91994.72768332546]
["1","05","03","03","02","  ","NEH Hutch 2                                                 "]
["1","05","03","03","03","  ","NEH Hutch 3                                                 "]
["1","05","03","04","  ","  ","Mech/Vac Tunnel                                             ",1390,750000,236225.3235790999,855383.6803984065,236225.3235790999,null,749.2,750000,129387.6865915174,855383.6803984065,984771.3669899236,0,null,0,null,929746.5400447226,null,55024.826945201115,null,0,null,null,187106.55972808553]
["1","05","03","05","  ","  ","Mech/Vac Far Hall                                           ",492,80000,82908.34248742694,91108.8,174017.14248742696,null,384.8,80000,64499.29807127308,91108.8,155608.0980712731,0,null,215.2189209230769,null,150062.03587403253,null,5330.843276317457,null,0,null,null,37345.94353710554]
["1","05","03","05","01","  ","FEH Hutch 1                                                 "]
["1","05","03","05","02","  ","FEH Hutch 2                                                 "]
["1","05","03","05","03","  ","FEH Hutch 3                                                 "]
["1","05","04","  ","  ","  ","Optical  Subsystem                                          ",11735,2592000,2036988.3565081873,2965795.525535537,4614982.66030819,null,6788.1,2545000,1172484.674480159,2911813.245535537,4084297.920015696,0,null,178.88995576923077,null,3487209.9507441865,null,596909.0793157407,null,0,null,null,1466274.307926712]
["1","05","04","01","  ","  ","Optical Systems Engineering                                 "]
["1","05","04","02","  ","  ","Facility Optics                                             ",11735,2592000,2036988.3565081873,2965795.525535537,4614982.66030819,null,6788.1,2545000,1172484.674480159,2911813.245535537,4084297.920015696,0,null,178.88995576923077,null,3487209.9507441865,null,596909.0793157407,null,0,null,null,1466274.307926712]
["1","05","04","02","01","  ","Fast Valve                                                  ",439,25000,72249.12345426924,28471.5,100720.62345426923,null,383.8,25000,62846.18702965384,28471.5,91317.68702965384,0,null,0,null,85934.67647538461,null,5383.010554269231,null,0,null,null,15524.006795041154]
["1","05","04","02","02","  ","Fixed Mask                                                  ",623,32000,101921.19505317032,36443.52,138364.71505317034,null,191.2,32000,29971.441501961537,36443.52,66414.96150196154,0,null,0,null,61031.950947692305,null,5383.010554269231,null,0,null,null,12618.842685372692]
["1","05","04","02","03","  ","Slit/Collimators                                            ",1505,180000,252116.43213132312,204994.8,457111.23213132314,null,494,180000,79825.79727747693,204994.8,284820.5972774769,0,null,0,null,279314.7718240385,null,5505.825453438461,null,0,null,null,74053.35529214403]
["1","05","04","02","04","  ","Flipper Mirror                                              "]
["1","05","04","02","05","  ","Gas/Solid Attenuator                                        ",3014,1295000,513712.2792250384,1474583.2,1960064.479225038,null,958.8,1270000,162020.95834157694,1446352.2,1608373.1583415766,0,null,178.88995576923077,null,1601201.2708646152,null,6992.997521192307,null,0,null,null,450344.48433564155]
["1","05","04","02","06","  ","TTF Damage Experiment                                       ",630,22000,121378.83236538462,25751.28,147130.11236538462,null,25.5,0,4936.782002884615,0,4936.782002884615,0,null,0,null,4936.782002884615,null,0,null,0,null,null,937.9885805480769]
["1","05","04","02","07","  ","FEL Offset Mirrors                                          ",5524,1038000,975610.4942790021,1195551.225535537,1811591.4980790014,null,4734.8,1038000,832883.5083266053,1195551.225535537,2028434.7338621425,0,null,0,null,1454790.4986295712,null,573644.2352325715,null,0,null,null,912795.6302379643]
["1","05","04","02","07","01","Low Energy Mirrors                                          ",2655,523000,467915.57219903526,596444.58,1064360.152199035,null,1958.8,523000,342337.6681793309,596444.58,938782.248179331,0,null,0,null,925025.7572516985,null,13756.490927632545,null,0,null,null,422452.0116806989]
["1","05","04","02","07","02","High Energy Mirrors                                         ",2869,515000,507694.922079967,599106.6455355373,747231.3458799667,null,2776,515000,490545.8401472747,599106.6455355373,1089652.4856828123,0,null,0,null,529764.7413778728,null,559887.7443049389,null,0,null,null,490343.6185572654]
["1","05","04","02","08","  ","Solid Attenuator                                            "]
["1","05","04","02","09","  ","Low Energy Mirror System                                    "]
["1","05","04","03","  ","  ","End Station Optics                                          "]
["1","05","04","03","01","  ","End Station Optics Engineering                              "]
["1","05","04","03","02","  ","Optics Tank - Near Hall                                     "]
["1","05","04","03","03","  ","Optics Tank - Far Hall                                      "]
["1","05","04","03","04","  ","K-B Focusing System                                         "]
["1","05","04","03","05","  ","Refractive Focusing System                                  "]
["1","05","04","04","  ","  ","Crystals & Gratings                                         "]
["1","05","04","04","01","  ","Crystals & Gratings Engineering                             "]
["1","05","04","04","02","  ","System Monochrometer                                        "]
["1","05","04","04","03","  ","Pulse Split & Delay                                         "]
["1","05","05","  ","  ","  ","Diagnostics Subsystem                                       ",17509,1069100,3045984.873664146,1226099.486340081,3930808.5793601456,null,11271.5,933230,1968079.2599330537,1072234.3613108126,3040313.6212438717,0,null,5761.413446088205,null,2335091.7146360525,null,699460.4931617285,null,0,null,null,913351.0602900848]
["1","05","05","01","  ","  ","Diagnostic Systems Engineering                              "]
["1","05","05","01","01","  ","Diagnostic Systems Engineering                              "]
["1","05","05","02","  ","  ","Modeling & Simulation                                       ",908,0,172164.6576923077,0,172164.6576923077,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","05","05","02","01","  ","Wave Model                                                  ",454,0,86082.32884615385,0,86082.32884615385,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","05","05","02","02","  ","Monte Carlo Model                                           ",454,0,86082.32884615385,0,86082.32884615385,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","05","05","02","03","  ","Beam Simulation                                             "]
["1","05","05","03","  ","  ","Facility Diagnostics                                        ",6997,408600,1225255.5440097244,467771.85252526833,1664749.4697057235,null,4325.3,329350,754398.564209436,377855.070696,1132253.6349054363,0,null,0,null,947375.8897980863,null,184877.74510735035,null,0,null,null,335854.6809009163]
["1","05","05","03","01","  ","Direct Imager                                               ",2078,197000,359927.3011102516,224355.42,584282.7211102517,null,1556.9,147750,267795.29545880936,168266.56500000003,436061.8604588093,0,null,0,null,416515.1010357399,null,19546.759423069543,null,0,null,null,109015.46511470233]
["1","05","05","03","02","  ","Indirect Imager                                             ",344,0,62615.773076923084,0,62615.773076923084,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","05","05","03","03","  ","Pulsed Ion Chamber                                          "]
["1","05","05","03","04","  ","Gas Mixing System                                           "]
["1","05","05","03","05","  ","FEE Diagnostic Tank                                         "]
["1","05","05","03","06","  ","Gas Detector                                                ",2891,118000,509174.36648613075,134047.60682926828,614944.0464861306,null,1084.4,88000,193065.16541420767,100219.68,293284.8454142076,0,null,0,null,287779.01996076916,null,5505.825453438461,null,0,null,null,126112.48352810933]
["1","05","05","03","07","  ","NEH Imager                                                  ",1684,93600,293538.1033364192,109368.82569600001,402906.9290324192,null,1684,93600,293538.1033364192,109368.82569600001,402906.9290324192,0,null,0,null,243081.76880157698,null,159825.16023084236,null,0,null,null,100726.7322581048]
["1","05","05","03","08","  ","FEH Imager                                                  "]
["1","05","05","04","  ","  ","Commissioning Diagnostics                                   ",9604,660500,1648564.6719621113,758327.6338148129,2093894.4519621108,null,6946.2,603880,1213680.6957236188,694379.2906148129,1908059.986338431,0,null,5761.413446088205,null,1387715.8248379654,null,514582.7480543784,null,0,null,null,577496.3793891688]
["1","05","05","04","01","  ","Commission Diagnostic Tanks                                 "]
["1","05","05","04","02","  ","Total Energy Measurement                                    ",3659,241500,603576.4913135418,274500.78,878077.2713135413,null,1265.7,184880,217347.1577872019,210552.43680000002,427899.5945872019,0,null,2721.767905128205,null,308698.3390866987,null,116479.487595375,null,0,null,null,141206.86621377664]
["1","05","05","04","03","  ","Pulse Length Measurement                                    "]
["1","05","05","04","04","  ","Low Energy Spectral Measurement System                      ",2254,150000,391999.377434264,170829,562828.3774342639,null,2233.5,150000,388275.1392798025,170829,559104.1392798026,0,null,3039.6455409600003,null,543149.1556349399,null,12915.33810390265,null,0,null,null,173322.28317673874]
["1","05","05","04","05","  ","Popup Cameras                                               ",1912,49000,327791.1562219576,57096.478499016404,327791.1562219576,null,1862,49000,318906.9926258038,57096.478499016404,376003.47112482024,0,null,0,null,263955.1642246778,null,112048.30690014262,null,0,null,null,94000.86778120506]
["1","05","05","04","06","  ","K Measurement System                                        ",1779,220000,325197.64699234994,255901.37531579647,325197.64699234994,null,1585,220000,289151.40603081154,255901.37531579647,545052.781346608,0,null,0,null,271913.16589164984,null,273139.6154549582,null,0,null,null,168966.3622174485]
["1","05","05","04","07","  ","Divergence Measurement                                      "]
["1","05","06","  ","  ","  ","X-Ray Transport System Installation & Alignment             ",8118,0,883648.5365625748,0,883648.5365625748,null,8118,0,883648.5365625748,0,883648.5365625748,0,null,0,null,0,null,883648.5365625748,null,0,null,null,220912.1341406437]
["1","05","06","01","  ","  ","Front End Enclosure Install                                 ",3710,0,428637.64247026213,0,428637.64247026213,null,3710,0,428637.64247026213,0,428637.64247026213,0,null,0,null,0,null,428637.64247026213,null,0,null,null,107159.41061756553]
["1","05","06","02","  ","  ","Near Hall Install                                           ",1436,0,140141.8508942484,0,140141.8508942484,null,1436,0,140141.8508942484,0,140141.8508942484,0,null,0,null,0,null,140141.8508942484,null,0,null,null,35035.4627235621]
["1","05","06","03","  ","  ","Tunnel Install                                              ",1720,0,183174.9147771554,0,183174.9147771554,null,1720,0,183174.9147771554,0,183174.9147771554,0,null,0,null,0,null,183174.9147771554,null,0,null,null,45793.72869428885]
["1","05","06","04","  ","  ","Far Hall Install                                            ",1124,0,118394.95329149892,0,118394.95329149892,null,1124,0,118394.95329149892,0,118394.95329149892,0,null,0,null,0,null,118394.95329149892,null,0,null,null,29598.73832287473]
["1","05","06","05","  ","  ","Electron Dump Enclosure Install                             ",128,0,13299.17512941059,0,13299.17512941059,null,128,0,13299.17512941059,0,13299.17512941059,0,null,0,null,0,null,13299.17512941059,null,0,null,null,3324.7937823526477]
["1","06","  ","  ","  ","  ","X-RAY END STATION SYSTEMS                                   ",78163,6274946,7357132.566038699,6893858.058108707,12637175.160386782,null,69884.13,6247228,6575923.5041249795,6859972.422108707,13435895.926233672,0,null,117663.78713223858,null,5412264.365623254,null,7263179.719688294,null,642788.0537899103,null,null,3557506.378874678]
["1","06","01","  ","  ","  ","System Management & Integration                             ",4021,63968,377549.5043634985,79593.936,457143.44036349846,null,2425.58,42600,230264.0979551645,53409.456000000006,283673.5539551645,0,null,0,null,82033.66053810397,null,201639.89341706052,null,0,null,null,62075.6563910329]
["1","06","01","01","  ","  ","Management                                                  ",4021,63968,377549.5043634985,79593.936,457143.44036349846,null,2425.58,42600,230264.0979551645,53409.456000000006,283673.5539551645,0,null,0,null,82033.66053810397,null,201639.89341706052,null,0,null,null,62075.6563910329]
["1","06","01","02","  ","  ","SSRL Physics                                                "]
["1","06","02","  ","  ","  ","XES Controls                                                ",29825,2840726,2639322.5788242393,3107961.0098640006,5668897.188688245,null,27709.2,2834376,2465126.440334232,3100259.8538640006,5565386.294198239,0,null,59035.6331155288,null,3256678.9339548047,null,1891844.8092968967,null,357826.9178310063,null,null,1427632.2537736227]
["1","06","02","01","  ","  ","Controls Management                                         ",0,450000,0,516020.868216,437634.468216,null,0,444400,0,509126.14821599994,509126.14821599994,0,null,0,null,71491.68,null,216009.1152,null,221625.35301599998,null,null,127281.53705399999]
["1","06","02","02","  ","  ","Network - Closed (Moved to new WBS Element)                 "]
["1","06","02","03","  ","  ","PC Support - Closed (Moved to New WBS Element)              "]
["1","06","02","04","  ","  ","Beamline Controls - AP - Closed  (Moved to new WBS Element) "]
["1","06","02","05","  ","  ","X-Ray PPS - Closed (Moved to new WBS Element)               "]
["1","06","02","05","01","  ","FEE X-Ray PPS - Closed (Moved to new WBS Element)           "]
["1","06","02","05","02","  ","Near Hall X-Ray PPS - Closed to BCWP                        "]
["1","06","02","05","03","  ","Tunnel X-Ray PPS - Closed to BCWP                           "]
["1","06","02","05","04","  ","Far Hall X-Ray PPS - Closed to BCWP                         "]
["1","06","02","06","  ","  ","X-Ray MPS - Closed (Moved to new WBS Element)               "]
["1","06","02","06","01","  ","FEE X-Ray MPS - Closed to BCWP                              "]
["1","06","02","07","  ","  ","AMOS Experiment Controls X1                                 ",8932,876400,775361.0173825686,943862.5866816001,1719223.6040641686,null,8212.9,875650,716125.5276597518,943056.1506816001,1659181.678341352,0,null,2551.5065829593104,null,1274861.3511571442,null,381768.82060124853,null,0,null,null,414795.419585338]
["1","06","02","07","01","  ","AMOS Experiment Controls X1                                 ",2320,0,204288.97419438863,0,204288.97419438863,null,1656,0,149594.35902523386,0,149594.35902523386,0,null,2551.5065829593104,null,13431.205155478237,null,133611.64728679633,null,0,null,null,37398.589756308465]
["1","06","02","07","02","  ","X-Ray Flourescence Detector                                 ",783,54200,68907.91596566074,59793.6810816,128701.59704726074,null,783,54200,68907.91596566074,59793.6810816,128701.59704726074,0,null,0,null,0,null,128701.59704726074,null,0,null,null,32175.399261815186]
["1","06","02","07","03","  ","Ion Imaging & Electron TOF                                  ",1044,285400,89824.97226147699,306875.7792000001,396700.7514614771,null,1044,285400,89824.97226147699,306875.7792000001,396700.7514614771,0,null,0,null,351684.86247840995,null,45015.88898306715,null,0,null,null,99175.18786536927]
["1","06","02","07","04","  ","Sample Source                                               ",1566,71100,134323.4229350112,76450.13279999999,210773.55573501118,null,1566,71100,134323.4229350112,76450.13279999999,210773.55573501118,0,null,0,null,210773.55573501118,null,0,null,0,null,null,52693.388933752794]
["1","06","02","07","05","  ","Vacuum Controls & Mechanical Exp 1                          ",783,104900,68114.94835287075,112793.5152,180908.46355287076,null,783,104900,68114.94835287075,112793.5152,180908.46355287076,0,null,0,null,143688.61991080863,null,37219.84364206213,null,0,null,null,45227.11588821769]
["1","06","02","07","06","  ","Refocus Optics                                              ",783,133700,68114.94835287075,143760.65759999998,211875.6059528707,null,783,133700,68114.94835287075,143760.65759999998,211875.6059528707,0,null,0,null,174655.76231080864,null,37219.84364206213,null,0,null,null,52968.90148821768]
["1","06","02","07","07","  ","Diagnostics                                                 ",1653,227100,141785.8353202896,244188.82080000002,385974.6561202896,null,1597.9,226350,137244.96076662754,243382.3848,380627.34556662745,0,null,0,null,380627.34556662745,null,0,null,0,null,null,95156.83639165686]
["1","06","02","08","  ","  ","AMOS Experiment Controls X2                                 ",3724,77300,326636.7702482462,85277.70383040002,411914.47407864616,null,3682,77300,323233.01863860176,85277.70383040002,408510.7224690017,0,null,4146.19819730888,null,60336.75173936727,null,344027.7725323255,null,0,null,null,109541.10263594227]
["1","06","02","08","01","  ","AMOS Experiment Controls X2                                 ",2320,0,204288.97419438863,0,204288.97419438863,null,2278,0,200885.22258474413,0,200885.22258474413,0,null,4146.19819730888,null,60336.75173936727,null,136402.27264806797,null,0,null,null,50221.30564618603]
["1","06","02","08","02","  ","X2 Praticle Imaging                                         ",1404,77300,122347.79605385764,85277.70383040002,207625.49988425762,null,1404,77300,122347.79605385764,85277.70383040002,207625.49988425762,0,null,0,null,0,null,207625.49988425762,null,0,null,null,59319.79698975625]
["1","06","02","09","  ","  ","Controls Management - Closed (Moved to new WBS Element)     "]
["1","06","02","10","  ","  ","Global Controls System                                      ",15479,1337426,1394445.7032458063,1455705.150336,2850150.853581806,null,14474.3,1337426,1311715.1434310374,1455705.150336,2767420.293767038,0,null,50288.273011718564,null,1630891.3549769896,null,950039.100963323,null,136201.56481500634,null,null,720727.3316471309]
["1","06","02","10","01","  ","Network                                                     ",1120,150000,99649.696009248,161287.2,260936.896009248,null,1120,150000,99649.696009248,161287.2,260936.896009248,0,null,0,null,260936.896009248,null,0,null,0,null,null,65234.224002312]
["1","06","02","10","02","  ","Machine Protection System                                   ",1120,4000,99649.696009248,4300.992,103950.688009248,null,872,4000,79211.6399419488,4300.992,83512.6319419488,0,null,0,null,83512.6319419488,null,0,null,0,null,null,20878.1579854872]
["1","06","02","10","03","  ","Personnel Protection System                                 ",1720,208200,156445.403490288,223866.63359999994,380312.037090288,null,1328,208200,124140.0890613312,223866.63359999994,348006.72266133124,0,null,0,null,348006.72266133124,null,0,null,0,null,null,87001.68066533281]
["1","06","02","10","04","  ","Laser PPS                                                   ",1360,49226,126777.257586144,52930.158048000005,179707.41563414398,null,1360,49226,126777.257586144,52930.158048000005,179707.41563414398,0,null,0,null,179707.41563414398,null,0,null,0,null,null,44926.853908535995]
["1","06","02","10","05","  ","User Safeguards                                             ",704,50000,68908.37348339747,54461.311200000004,123369.68468339751,null,704,50000,68908.37348339747,54461.311200000004,123369.68468339751,0,null,0,null,67814.44805939212,null,55555.23662400533,null,0,null,null,30842.42117084938]
["1","06","02","10","06","  ","Timing System                                               ",1120,30000,99649.696009248,32257.44,131907.136009248,null,788,30000,72289.0725643152,32257.44,104546.5125643152,0,null,0,null,104546.5125643152,null,0,null,0,null,null,26136.6281410788]
["1","06","02","10","07","  ","Data Management                                             ",3591,240000,319385.64410742396,258059.52,577445.1641074241,null,3591,240000,319385.64410742396,258059.52,577445.1641074241,0,null,26457.419442649283,null,385172.47356507485,null,100918.45057207918,null,64896.8205276207,null,null,173233.5492322272]
["1","06","02","10","08","  ","Global Cabling & Racks                                      ",880,0,99467.72578195199,0,99467.72578195199,null,880,0,99467.72578195199,0,99467.72578195199,0,null,0,null,99467.72578195199,null,0,null,0,null,null,24866.931445487997]
["1","06","02","10","09","  ","Laser Timing                                                ",0,606000,0,668541.8954880001,668541.8954880001,null,0,606000,0,668541.8954880001,668541.8954880001,0,null,0,null,0,null,668541.8954880001,null,0,null,null,167135.47387200003]
["1","06","02","10","10","  ","Experimental High Level Applications                        ",3864,0,324512.21076885704,0,324512.21076885704,null,3831.3,0,321885.64489527704,0,321885.64489527704,0,null,23830.85356906928,null,101726.52875958376,null,125023.51827923837,null,71304.74428738562,null,null,80471.41122381926]
["1","06","02","11","  ","  ","Laser Controls                                              ",1360,87400,115754.06112494401,93976.6752,209730.736324944,null,1020,87400,87734.14554880801,93976.6752,181710.820748808,0,null,0,null,181710.820748808,null,0,null,0,null,null,45427.705187202]
["1","06","02","12","  ","  ","K-Measuerment/Vacuum Subsystem                              ",330,12200,27125.026822674,13118.025599999999,40243.052422674,null,320,12200,26318.6050560345,13118.025599999999,39436.6306560345,0,null,2049.6553235420624,null,37386.97533249243,null,0,null,0,null,null,9859.157664008624]
["1","06","03","  ","  ","  ","Mechanical/Vacuum Subsystem                                 "]
["1","06","03","01","  ","  ","Chamber Support Tables - Mech/Vac                           "]
["1","06","03","02","  ","  ","Vacuum Components - Mech/Vac                                "]
["1","06","03","02","01","  ","Valves - Vacuum                                             "]
["1","06","03","02","02","  ","Hardware - Vacuum                                           "]
["1","06","03","02","03","  ","Ion Pump - Vacuum                                           "]
["1","06","03","02","04","  ","Turbo Pump - Vacuum                                         "]
["1","06","03","02","05","  ","Gauges - Vacuum                                             "]
["1","06","03","03","  ","  ","Experimental Chambers                                       "]
["1","06","03","03","01","  ","AP Chamber 1                                                "]
["1","06","03","03","02","  ","AP Chamber 2                                                "]
["1","06","04","  ","  ","  ","Laser Subsystem                                             ",8926,961700,959644.4735053703,1058323.500686986,1199701.7613901705,null,7883.26,961700,829917.6810855321,1058323.500686986,1888241.1817725184,0,null,37212.35064947485,null,615382.298557252,null,1224482.8273709484,null,11163.705194842454,null,null,472060.2954431296]
["1","06","04","01","  ","  ","XES Laser                                                   ",1328,641100,124123.6650818419,704988.4504937143,124123.6650818419,null,1328,641100,124123.6650818419,704988.4504937143,829112.1155755562,0,null,0,null,193699.83441894857,null,635412.2811566076,null,0,null,null,207278.02889388904]
["1","06","04","02","  ","  ","Laser Diagnostics                                           ",4542,127600,542954.9226402005,140768.8875648,683723.8102050006,null,3499.26,127600,413228.13022036233,140768.8875648,553997.0177851624,0,null,37212.35064947485,null,209398.2135435312,null,296222.74839731405,null,11163.705194842454,null,null,138499.2544462906]
["1","06","04","03","  ","  ","Laser Optical Transport                                     ",2696,184000,259272.38903389484,202637.32259647158,348631.94932189485,null,2696,184000,259272.38903389484,202637.32259647158,461909.71163036645,0,null,0,null,201911.94763890043,null,259997.763991466,null,0,null,null,115477.42790759161]
["1","06","04","04","  ","  ","Laser Safety                                                ",360,9000,33293.49674943283,9928.840032,43222.33678143283,null,360,9000,33293.49674943283,9928.840032,43222.33678143283,0,null,0,null,10372.302955871999,null,32850.03382556083,null,0,null,null,10805.584195358208]
["1","06","05","  ","  ","  ","X-Ray Detectors                                             ",4143,0,305674.8926843022,0,305674.8926843022,null,2610.09,0,192568.54209655532,0,192568.54209655532,0,null,21135.571693524365,null,85716.48520151548,null,85716.48520151548,null,0,null,null,38513.708419311064]
["1","06","05","01","  ","  ","Beam Imaging                                                "]
["1","06","05","02","  ","  ","Not Used                                                    "]
["1","06","05","03","  ","  ","Beam Intensity                                              "]
["1","06","05","04","  ","  ","Detector & Streak Camera                                    ",4143,0,305674.8926843022,0,305674.8926843022,null,2610.09,0,192568.54209655532,0,192568.54209655532,0,null,21135.571693524365,null,85716.48520151548,null,85716.48520151548,null,0,null,null,38513.708419311064]
["1","06","05","04","01","  ","Detector Management                                         ",4143,0,305674.8926843022,0,305674.8926843022,null,2610.09,0,192568.54209655532,0,192568.54209655532,0,null,21135.571693524365,null,85716.48520151548,null,85716.48520151548,null,0,null,null,38513.708419311064]
["1","06","05","04","02","  ","Streak Camera - LBL                                         "]
["1","06","06","  ","  ","  ","System Installation & Alignment                             ",12192,0,1113341.2185857391,0,1113341.2185857391,null,12192,0,1113341.2185857391,0,1113341.2185857391,0,null,0,null,0,null,977489.6175116401,null,135851.6010740995,null,null,304232.5742686427]
["1","06","06","01","  ","  ","Front End Install                                           ",692,0,63236.4690794385,0,63236.4690794385,null,692,0,63236.4690794385,0,63236.4690794385,0,null,0,null,0,null,63236.4690794385,null,0,null,null,16422.385834595705]
["1","06","06","02","  ","  ","Near Hall Install                                           ",8888,0,815357.7654025799,0,815357.7654025799,null,8888,0,815357.7654025799,0,815357.7654025799,0,null,0,null,0,null,688656.3253901096,null,126701.44001247037,null,null,213266.66300726382]
["1","06","06","02","01","  ","Near Hall Install Global Controls                           ",1032,0,91492.02671260147,0,91492.02671260147,null,1032,0,91492.02671260147,0,91492.02671260147,0,null,0,null,0,null,91492.02671260147,null,0,null,null,31404.000461233165]
["1","06","06","02","02","  ","Near Hall Install Mech/Vac                                  ",288,0,26420.9151968832,0,26420.9151968832,null,288,0,26420.9151968832,0,26420.9151968832,0,null,0,null,0,null,18676.729177344,null,7744.1860195392,null,null,6605.2287992208]
["1","06","06","02","03","  ","Near Hall Install Laser                                     ",2080,0,202074.80192521456,0,202074.80192521456,null,2080,0,202074.80192521456,0,202074.80192521456,0,null,0,null,0,null,202074.80192521456,null,0,null,null,50518.70048130364]
["1","06","06","02","04","  ","Near Hall Install Detectors                                 "]
["1","06","06","02","05","  ","Near Hall Install Atomic Physics                            ",3600,0,322414.12154110405,0,322414.12154110405,null,3600,0,322414.12154110405,0,322414.12154110405,0,null,0,null,0,null,203456.86754817292,null,118957.25399293116,null,null,80603.53038527601]
["1","06","06","02","06","  ","Near Hall Install PPS System                                ",928,0,85100.89825162469,0,85100.89825162469,null,928,0,85100.89825162469,0,85100.89825162469,0,null,0,null,0,null,85100.89825162469,null,0,null,null,22171.45243644225]
["1","06","06","02","07","  ","Near Hall Install Laser PPS                                 ",960,0,87855.00177515212,0,87855.00177515212,null,960,0,87855.00177515212,0,87855.00177515212,0,null,0,null,0,null,87855.00177515212,null,0,null,null,21963.75044378803]
["1","06","06","03","  ","  ","Tunnel Install                                              ",428,0,39220.87375671358,0,39220.87375671358,null,428,0,39220.87375671358,0,39220.87375671358,0,null,0,null,0,null,39220.87375671358,null,0,null,null,10347.747176714478]
["1","06","06","04","  ","  ","Far Hall Install                                            ",1960,0,174968.821001584,0,174968.821001584,null,1960,0,174968.821001584,0,174968.821001584,0,null,0,null,0,null,165818.65993995487,null,9150.16106162914,null,null,59056.45591371267]
["1","06","06","04","01","  ","Far Hall Install Global Controls                            ",920,0,81220.51776332023,0,81220.51776332023,null,920,0,81220.51776332023,0,81220.51776332023,0,null,0,null,0,null,81220.51776332023,null,0,null,null,30919.645617458125]
["1","06","06","04","02","  ","Far Hall Install Mech/Vac                                   "]
["1","06","06","04","04","  ","Far Hall Install Detectors                                  ",720,0,64292.5372495294,0,64292.5372495294,null,720,0,64292.5372495294,0,64292.5372495294,0,null,0,null,0,null,64292.5372495294,null,0,null,null,19287.76117485882]
["1","06","06","04","05","  ","Far Hall Install PPS System                                 ",320,0,29455.765988734394,0,29455.765988734394,null,320,0,29455.765988734394,0,29455.765988734394,0,null,0,null,0,null,20305.604927105258,null,9150.16106162914,null,null,8849.049121395728]
["1","06","06","05","  ","  ","Electron Dump Enclosure Install                             ",224,0,20557.289345423727,0,20557.289345423727,null,224,0,20557.289345423727,0,20557.289345423727,0,null,0,null,0,null,20557.289345423727,null,0,null,null,5139.322336355932]
["1","06","07","  ","  ","  ","AMOS Experiment                                             ",14270,2022552,1510409.965762775,2231447.2583228964,3046679.5262340712,null,12514,2022552,1316354.8912890144,2231447.2583228964,3547802.1496119117,0,null,0,null,632818.5629865286,null,2777037.75693542,null,137945.82968996206,null,null,1041771.1440755532]
["1","06","07","01","  ","  ","AP Management & Design                                      ",7478,0,813712.9867774213,0,813712.9867774213,null,5722,0,619657.9123036612,0,619657.9123036612,0,null,0,null,435079.97617815563,null,184577.9361255055,null,0,null,null,154252.22527689254]
["1","06","07","01","01","  ","Management                                                  ",698,0,81055.49156486036,0,81055.49156486036,null,534,0,60995.704705133394,0,60995.704705133394,0,null,0,null,15267.068774971198,null,45728.63593016219,null,0,null,null,12199.140941026679]
["1","06","07","01","02","  ","Conceptual Design                                           ",1220,0,134332.54362323816,0,134332.54362323816,null,168,0,18452.247638140798,0,18452.247638140798,0,null,0,null,18452.247638140798,null,0,null,0,null,null,3690.4495276281596]
["1","06","07","01","03","  ","Preliminary Design                                          ",1980,0,214483.407715368,0,214483.407715368,null,1440,0,156368.41608643197,0,156368.41608643197,0,null,0,null,156368.41608643197,null,0,null,0,null,null,38312.05442567976]
["1","06","07","01","04","  ","Final Design                                                ",3580,0,383841.54387395503,0,383841.54387395503,null,3580,0,383841.54387395503,0,383841.54387395503,0,null,0,null,244992.24367861162,null,138849.30019534333,null,0,null,null,100050.5803825579]
["1","06","07","02","  ","  ","AP X1 High Field Physics Exp.                               ",3540,1248661,365980.84287242603,1377205.7948441282,1081586.5433165538,null,3540,1248661,365980.84287242603,1377205.7948441282,1743186.6377165546,0,null,0,null,84276.61830127753,null,1595132.001577023,null,63778.01783825403,null,null,492070.9683853583]
["1","06","07","02","01","  ","X-Ray Fluorescence Detectors                                ",550,600000,55017.38882582968,661600.0944000001,55017.38882582968,null,550,600000,55017.38882582968,661600.0944000001,716617.4832258298,0,null,0,null,21642.730478141537,null,655496.8974710448,null,39477.855276643386,null,null,191916.89752698274]
["1","06","07","02","02","  ","Ion Imaging & Electron TOF Detectors                        ",1340,260378,135291.14952704147,287250.167761344,422541.3172883854,null,1340,260378,135291.14952704147,287250.167761344,422541.3172883854,0,null,0,null,26972.523763704063,null,395568.7935246814,null,0,null,null,115799.21700812988]
["1","06","07","02","03","  ","Sample Source                                               ",600,129246,63566.48302974329,142584.762086208,206151.24511595131,null,600,129246,63566.48302974329,142584.762086208,206151.24511595131,0,null,0,null,8688.840295727845,null,197462.40482022343,null,0,null,null,52463.34944831357]
["1","06","07","02","04","  ","Vacuum System                                               ",120,195837,13854.06902408436,216048.249482976,229902.31850706038,null,120,195837,13854.06902408436,216048.249482976,229902.31850706038,0,null,0,null,13486.261881852031,null,216416.05662520835,null,0,null,null,79080.4045750627]
["1","06","07","02","05","  ","Other X1 Items                                              ",120,63200,13854.06902408436,69722.5211136,83576.59013768435,null,120,63200,13854.06902408436,69722.5211136,83576.59013768435,0,null,0,null,13486.261881852031,null,70090.32825583233,null,0,null,null,29949.031759325524]
["1","06","07","03","  ","  ","AP Refocus Optics                                           ",820,256881,89168.69816186179,283873.73181828804,339464.8265285498,null,820,256881,89168.69816186179,283873.73181828804,373042.42998014984,0,null,0,null,57571.21162488555,null,265981.07190659014,null,49490.14644867412,null,null,131423.19601049597]
["1","06","07","04","  ","  ","AP Diagnostics                                              ",1131,282605,108627.38224471222,311771.09302704,420398.4752717522,null,1131,282605,108627.38224471222,311771.09302704,420398.4752717522,0,null,0,null,13486.261881852031,null,406912.21338990016,null,0,null,null,130263.3365659943]
["1","06","07","05","  ","  ","AP Particle Imaging Experiment                              ",1301,234405,132920.055706353,258596.63863344002,391516.694339793,null,1301,234405,132920.055706353,258596.63863344002,391516.694339793,0,null,0,null,42404.49500035792,null,324434.5339364012,null,24677.66540303392,null,null,133761.41783681198]
["1","06","08","  ","  ","  ","Crystals and Gratings                                       ",120,20000,14630.445691956505,21985.15310682353,14630.445691956505,null,44,20000,5410.140134992224,21985.15310682353,27395.293241815754,0,null,280.2316737105526,null,8233.694782244993,null,18881.36678586021,null,0,null,null,6848.823310453939]
["1","06","08","01","  ","  ","K Measurement Spectrometer                                  ",120,20000,14630.445691956505,21985.15310682353,14630.445691956505,null,44,20000,5410.140134992224,21985.15310682353,27395.293241815754,0,null,280.2316737105526,null,8233.694782244993,null,18881.36678586021,null,0,null,null,6848.823310453939]
["1","06","09","  ","  ","  ","Mechanical Systems                                          ",4666,366000,436559.4866208183,394547.200128,831106.6867488184,null,4506,366000,422940.4926437464,394547.200128,817487.6927717463,0,null,0,null,731400.7296028001,null,86086.96316894605,null,0,null,null,204371.92319293658]
["1","06","09","01","  ","  ","PPS Stoppers                                                ",2408,300000,226639.99013497398,322574.4,549214.390134974,null,2248,300000,213020.99615790203,322574.4,535595.396157902,0,null,0,null,493277.216642289,null,42318.179515612945,null,0,null,null,133898.8490394755]
["1","06","09","02","  ","  ","PPS Shielding                                               ",1858,30000,172911.81118744705,32257.44,205169.25118744705,null,1858,30000,172911.81118744705,32257.44,205169.25118744705,0,null,0,null,203686.4892701248,null,1482.761917322262,null,0,null,null,51292.31279686176]
["1","06","09","03","  ","  ","NEH Hutch Doors                                             ",400,36000,37007.68529839709,39715.360128,76723.04542639709,null,400,36000,37007.68529839709,39715.360128,76723.04542639709,0,null,0,null,34437.02369038624,null,42286.02173601085,null,0,null,null,19180.761356599272]
["1","09","  ","  ","  ","  ","CONVENTIONAL FACILITIES                                     ",28690,102137073,2908236.6475683628,102310322.10775143,89053050.75972836,null,19740.83,80090975.63299999,2046267.066476818,80232220.08878037,82278487.15525721,0,null,250013.15938170342,null,55512501.01290796,null,26360772.365260564,null,155200.6177069948,null,null,13018031.062979737]
["1","09","01","  ","  ","  ","System Management & Integration                             ",24530,12652722,2582855.267923224,12712585.176441714,14614973.163059222,null,18216.73,7368516.23,1933641.5125660554,7402634.243756399,9336275.756322455,0,null,21421.167207272047,null,6987450.691167501,null,2327403.897947681,null,0,null,null,1375584.5751775375]
["1","09","01","01","  ","  ","Management                                                  ",3535,566750,379694.7711295077,580934.8951359999,960629.6662655078,null,2666.58,185110,287855.56030698924,193420.114016,481275.6743229893,0,null,0,null,275598.75544622226,null,205676.91887676695,null,0,null,null,96255.13486459784]
["1","09","01","02","  ","  ","CF Engineering                                              ",8133,1784026,867604.8460827314,1829302.6740662046,1122604.8460827314,null,5568.15,621614.82,597185.556615995,647422.7197403989,1244608.276356394,0,null,13951.618872978497,null,808519.554482498,null,422137.1030009176,null,0,null,null,309942.9389588384]
["1","09","01","03","  ","  ","Construction Management & AE Support                        ",10874,10281946,1160128.337847591,10282347.60723951,12336311.33784759,null,9072,6561791.41,970122.6985658646,6561791.41,7531914.108565864,0,null,0,null,5832324.232495869,null,1699589.8760699967,null,0,null,null,945843.1922309388]
["1","09","01","04","  ","  ","Mechanical Design (MD)                                      ",1758,20000,151180.86350301033,20000,171180.86350301036,null,910,0,78477.69707720693,0,78477.69707720693,0,null,7469.548334293551,null,71008.14874291338,null,0,null,0,null,null,23543.30912316208]
["1","09","01","04","01","  ","Mechanical Design Title 1 - RSY through CLOC                "]
["1","09","01","04","02","  ","Mechanical Design T1 Linac Facilities                       "]
["1","09","01","04","03","  ","Mechanical Design Title 2 - RSY through CLOC                "]
["1","09","01","04","04","  ","Mechanical Design T2 Linac Facilities                       ",738,20000,61078.136557679994,20000,81078.13655768,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","09","01","04","05","  ","Mechanical Design Title 3 Linac Facility                    ",220,0,23250.059736246818,0,23250.059736246818,null,110,0,11625.029868123409,0,11625.029868123409,0,null,2186.3588284085313,null,9438.671039714878,null,0,null,0,null,null,3487.508960437023]
["1","09","01","04","06","  ","Mechanical Design Title 3 - RSY through CLOC                ",800,0,66852.66720908352,0,66852.66720908352,null,800,0,66852.66720908352,0,66852.66720908352,0,null,5283.18950588502,null,61569.47770319851,null,0,null,0,null,null,20055.800162725056]
["1","09","01","05","  ","  ","Conventional Experiment Facility (CEF)                      ",230,0,24246.44936038285,0,24246.44936038285,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","09","01","05","01","  ","CEF Engineering Title 1 - RSY through CLOC                  "]
["1","09","01","05","02","  ","CEF Engineering Title 1 Linac Facility                      "]
["1","09","01","05","03","  ","CEF Engineering Title 2 - RSY through CLOC                  "]
["1","09","01","05","04","  ","CEF Design Linac Facility Title 2                           ",230,0,24246.44936038285,0,24246.44936038285,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","09","02","  ","  ","  ","Title 1 & Title 2 Conventional Facilities                   ",0,27100,0,27100,0,null,0,4250,0,4250,4250,0,null,607.1428571428571,null,3642.8571428571427,null,0,null,0,null,null,1275]
["1","09","02","02","  ","  ","A & E Services  - RSY throguh CLOC                          ",0,27100,0,27100,0,null,0,4250,0,4250,4250,0,null,607.1428571428571,null,3642.8571428571427,null,0,null,0,null,null,1275]
["1","09","02","02","01","  ","Title 1 Design                                              "]
["1","09","02","02","02","  ","Title 2 Design                                              ",0,27100,0,27100,0,null,0,4250,0,4250,4250,0,null,607.1428571428571,null,3642.8571428571427,null,0,null,0,null,null,1275]
["1","09","02","03","  ","  ","A & E Services - (S20, MMF,MCC)                             "]
["1","09","02","03","01","  ","Title 1 Design (Sector 20)                                  "]
["1","09","02","03","02","  ","Title 2 Design (Sector 20)                                  "]
["1","09","02","03","03","  ","Title 1 Design (MMF)                                        "]
["1","09","02","03","04","  ","Title 2 Design (MMF)                                        "]
["1","09","02","03","05","  ","Title 1 Design (MCC)                                        "]
["1","09","02","03","06","  ","Title 2 Design (MCC)                                        "]
["1","09","03","  ","  ","  ","Construction-T3 Conventional Facilities                     ",4160,89457251,325381.3796451382,89570636.93130971,74438077.59666914,null,1524.1,72718209.403,112625.5539107626,72825335.84502399,72937961.39893475,0,null,227984.84931728852,null,48521407.4645976,null,24033368.46731288,null,155200.6177069948,null,null,11641171.487802196]
["1","09","03","01","  ","  ","Sector 20 Injector Facilities                               ",20,183430,1297.038755211854,183430,96102.03875521186,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","09","03","01","01","  ","S20 - Site Preparation/General Requirements                 "]
["1","09","03","01","02","  ","S20 - Site Construction                                     "]
["1","09","03","01","03","  ","S20 - Concrete                                              "]
["1","09","03","01","04","  ","S20 - Masonry                                               "]
["1","09","03","01","05","  ","S20 - Metals                                                "]
["1","09","03","01","06","  ","S20 - Woods & Plastics                                      "]
["1","09","03","01","07","  ","S20 - Thermal & Moisture Protection                         "]
["1","09","03","01","08","  ","S20 - Doors & Windows                                       "]
["1","09","03","01","09","  ","S20 - Finishes                                              "]
["1","09","03","01","10","  ","S20 - Specialties                                           "]
["1","09","03","01","14","  ","S20 - Conveying Systems                                     "]
["1","09","03","01","15","  ","S20 - Mechanical                                            "]
["1","09","03","01","16","  ","S20 - Electrical                                            "]
["1","09","03","01","20","  ","S20 - Project Close Out                                     ",20,183430,1297.038755211854,183430,96102.03875521186,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","09","03","02","  ","  ","Magnetic Measurement Facility                               ",0,267748,0,267748,232748,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","09","03","02","01","  ","MMF - Site Preparation/General Requirements                 "]
["1","09","03","02","02","  ","MMF - Site Construction                                     "]
["1","09","03","02","03","  ","MMF - Concrete                                              "]
["1","09","03","02","04","  ","Utilities                                                   "]
["1","09","03","02","05","  ","MMF - Metals                                                "]
["1","09","03","02","06","  ","MMF - Woods & Plastics                                      "]
["1","09","03","02","07","  ","MMF - Thermal & Moisture Protection                         "]
["1","09","03","02","08","  ","MMF - Doors & Windows                                       "]
["1","09","03","02","09","  ","MMF - Finishes                                              "]
["1","09","03","02","10","  ","MMF - Specialities                                          "]
["1","09","03","02","13","  ","                                                            "]
["1","09","03","02","14","  ","MMF - Conveying Systems                                     "]
["1","09","03","02","15","  ","MMF - Mechanical                                            "]
["1","09","03","02","16","  ","MMF - Electrical                                            "]
["1","09","03","02","20","  ","MMF - Project Close Out                                     ",0,267748,0,267748,232748,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","09","03","03","  ","  ","BTH West                                                    ",600,310000,37653.83934047999,310000,37653.83934047999,null,600,310000,37653.83934047999,310000,347653.83934048,0,null,0,null,281980.7034875689,null,65673.13585291115,null,0,null,null,123826.91967024]
["1","09","03","03","01","  ","BTH West - Site Preparation                                 ",600,0,37653.83934047999,0,37653.83934047999,null,600,0,37653.83934047999,0,37653.83934047999,0,null,0,null,37653.83934047999,null,0,null,0,null,null,18826.919670239997]
["1","09","03","03","15","  ","BTH West - Mechanical                                       ",0,100000,0,100000,0,null,0,100000,0,100000,100000,0,null,0,null,82584.26966292135,null,17415.730337078654,null,0,null,null,0]
["1","09","03","03","16","  ","BTH West - Electrical                                       ",0,180000,0,180000,0,null,0,180000,0,180000,180000,0,null,0,null,148651.68539325843,null,31348.314606741576,null,0,null,null,90000]
["1","09","03","03","20","  ","BTH West - Project Close Out                                ",0,30000,0,30000,0,null,0,30000,0,30000,30000,0,null,0,null,13090.90909090909,null,16909.090909090908,null,0,null,null,15000]
["1","09","03","04","  ","  ","Linac Facility Upgrade (LN)                                 ",40,2047225,3349.340893008,2160610.9313097144,2057700.5579170082,null,40,1328000,3349.340893008,1435126.2170240001,1438475.5579170082,0,null,0,null,293349.340893008,null,1145126.2170240001,null,0,null,null,430872.79919650086]
["1","09","03","04","01","  ","LN - Site Preparation                                       "]
["1","09","03","04","02","  ","LN - Sitework                                               "]
["1","09","03","04","03","  ","Electrical                                                  "]
["1","09","03","04","04","  ","Utilities                                                   "]
["1","09","03","04","05","  ","Linac - Metals                                              "]
["1","09","03","04","06","  ","Special System - Fire Protection                            "]
["1","09","03","04","10","  ","Project Close Out Linac Facility                            "]
["1","09","03","04","15","  ","LN - Mechanical                                             ",0,699225,0,704232.7714285714,619225,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","09","03","04","16","  ","LN - Electrical                                             ",0,1298000,0,1406378.159881143,1385126.2170240001,null,0,1278000,0,1385126.2170240001,1385126.2170240001,0,null,0,null,240000,null,1145126.2170240001,null,0,null,null,415537.86510720005]
["1","09","03","04","20","  ","LN - Project Close Out                                      ",40,50000,3349.340893008,50000,53349.340893008,null,40,50000,3349.340893008,50000,53349.340893008,0,null,0,null,53349.340893008,null,0,null,0,null,null,15334.9340893008]
["1","09","03","05","  ","  ","Research Yard Modifications                                 ",3500,2053266,283081.1606564384,2053266,1465347.1606564384,null,884.1,640000,71622.37367727459,640000,711622.3736772746,0,null,20045.08571381616,null,442676.18906235957,null,248901.0989010989,null,0,null,null,142324.47473545492]
["1","09","03","05","01","  ","RY - Site Preparation                                       ",3500,315000,283081.1606564384,315000,427081.1606564384,null,884.1,0,71622.37367727459,0,71622.37367727459,0,null,14135.994804725251,null,57486.37887254935,null,0,null,0,null,null,14324.474735454922]
["1","09","03","05","01","01","General Requirements- CEF                                   "]
["1","09","03","05","01","02","General Requirements - G/C                                  "]
["1","09","03","05","02","  ","RY - FFTB/BSY & Site Construction                           ",0,1038266,0,1038266,1038266,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","09","03","05","02","01","Site Construction - CEF                                     "]
["1","09","03","05","02","02","Site Construction - G/C                                     "]
["1","09","03","05","03","  ","Electrical                                                  "]
["1","09","03","05","03","01","Electrical CEF                                              "]
["1","09","03","05","03","02","Electrical G/C                                              "]
["1","09","03","05","04","  ","Utilities                                                   "]
["1","09","03","05","04","01","Utilities CEF                                               "]
["1","09","03","05","04","02","Utilities G/C                                               "]
["1","09","03","05","05","  ","RY - Metals                                                 "]
["1","09","03","05","05","01","HVAC CEF                                                    "]
["1","09","03","05","05","02","HVAC G/C                                                    "]
["1","09","03","05","06","  ","Special System - Fire Protection                            "]
["1","09","03","05","06","01","Special System - Fire Protection CEF                        "]
["1","09","03","05","06","02","Special System - Fire Protection                            "]
["1","09","03","05","07","  ","Interior                                                    "]
["1","09","03","05","07","01","Interior CEF                                                "]
["1","09","03","05","07","02","Interior G/C                                                "]
["1","09","03","05","10","  ","Project Close Out Reasearch Yard                            "]
["1","09","03","05","20","  ","RY - Project Close Out                                      ",0,700000,0,700000,0,null,0,640000,0,640000,640000,0,null,5909.090909090909,null,385189.81018981023,null,248901.0989010989,null,0,null,null,128000]
["1","09","03","06","  ","  ","Pre-Purchase Equipment                                      ",0,2076952,0,2076952,355340,null,0,1932276.1,0,1932276,1932276,0,null,6857.167832167832,null,817974.7338071765,null,1107444.0983606558,null,0,null,null,289841.4]
["1","09","03","06","01","  ","PPE - General Requirements                                  ",0,357225,0,357225,196474,null,0,212549.1,0,212549,212549,0,null,6857.167832167832,null,127101.83216783217,null,78590,null,0,null,null,31882.35]
["1","09","03","06","02","  ","AR - Site Construction                                      "]
["1","09","03","06","03","  ","AR - Concrete                                               "]
["1","09","03","06","04","  ","Utilities                                                   "]
["1","09","03","06","05","  ","HVAC                                                        "]
["1","09","03","06","06","  ","Special System- Fire Protection                             "]
["1","09","03","06","07","  ","Interior                                                    "]
["1","09","03","06","10","  ","Project Close Out  Beam Trans Hall                          "]
["1","09","03","06","11","  ","Pre-Purchase Equipment for Beam Path                        ",0,1719727,0,1719727,158866,null,0,1719727,0,1719727,1719727,0,null,0,null,690872.9016393443,null,1028854.0983606557,null,0,null,null,257959.05]
["1","09","03","06","20","  ","AR - Project Close Out                                      "]
["1","09","03","07","  ","  ","SITEWORK                                                    ",0,11800915,0,11800915,11040653,null,0,5749664,0,5749664,5749664,0,null,58868.31005701882,null,3454215.4756786497,null,2236580.2142643314,null,0,null,null,862449.6]
["1","09","03","07","01","  ","SW - Site Preparation/General Requirements                  ",0,2618954,0,2618954,2187079,null,0,1426292,0,1426292,1426292,0,null,0,null,486372.1785714286,null,939919.8214285714,null,0,null,null,213943.8]
["1","09","03","07","02","  ","SW - Site Construction                                      ",0,8331379,0,8331379,8032992,null,0,4145070.4,0,4145070.4,4145070.4,0,null,58868.31005701882,null,2935091.6971072205,null,1151110.39283576,null,0,null,null,621760.56]
["1","09","03","07","03","  ","SW - Concrete                                               "]
["1","09","03","07","04","  ","Utilities                                                   "]
["1","09","03","07","05","  ","HVAC                                                        "]
["1","09","03","07","06","  ","Special System - Fire Protection                            "]
["1","09","03","07","07","  ","Interior                                                    "]
["1","09","03","07","09","  ","Tunneling                                                   "]
["1","09","03","07","10","  ","Project Close Out Undulator Hall                            "]
["1","09","03","07","15","  ","SW - Mechanical                                             "]
["1","09","03","07","16","  ","SW - Electrical                                             ",0,850582,0,850582,820582,null,0,178301.6,0,178301.6,178301.6,0,null,0,null,32751.6,null,145550,null,0,null,null,26745.24]
["1","09","03","07","17","  ","SW - Others (include Div 4, and 6 through 14)               "]
["1","09","03","07","20","  ","SW - Project Close Out                                      "]
["1","09","03","08","  ","  ","Beam Transport Hall (BTH)                                   ",0,9513019,0,9513019,7555059,null,0,8662160.4,0,8662160.4,8662160.4,0,null,142214.2857142857,null,7987076.5238881195,null,532869.5903975959,null,0,null,null,1317424.06]
["1","09","03","08","01","  ","BTH - Site Preparation/General Requirements                 ",0,676488,0,676488,593488,null,0,20789,0,20789,20789,0,null,0,null,20789,null,0,null,0,null,null,3118.35]
["1","09","03","08","02","  ","BTH - Site Construction                                     "]
["1","09","03","08","03","  ","BTH - Concrete                                              ",0,6159829,0,6159829,6159829,null,0,6143203,0,6143203,6143203,0,null,0,null,6143203,null,0,null,0,null,null,921480.45]
["1","09","03","08","04","  ","Utilities                                                   "]
["1","09","03","08","05","  ","BTH - Metals                                                ",0,368641,0,368641,368641,null,0,368641,0,368641,368641,0,null,0,null,368641,null,0,null,0,null,null,55296.15]
["1","09","03","08","06","  ","Special System - Fire Protection                            "]
["1","09","03","08","07","  ","Interior                                                    "]
["1","09","03","08","09","  ","Tunneling                                                   "]
["1","09","03","08","10","  ","Project Close Out Front End Enclosure                       "]
["1","09","03","08","15","  ","BTH - Mechanical                                            ",0,719488,0,719488,82241,null,0,719488,0,719488,719488,0,null,0,null,595782.4576976422,null,123705.54230235783,null,0,null,null,107923.2]
["1","09","03","08","16","  ","BTH - Electrical                                            ",0,1555404,0,1555404,343956,null,0,1376870.4,0,1376870.4,1376870.4,0,null,142214.2857142857,null,826805.3161904761,null,407850.79809523805,null,0,null,null,224630.56]
["1","09","03","08","17","  ","BTH - Others (include Div 4, and 6 through 14)              ",0,33169,0,33169,6904,null,0,33169,0,33169,33169,0,null,0,null,31855.75,null,1313.25,null,0,null,null,4975.35]
["1","09","03","08","20","  ","BTH - Project Close Out                                     "]
["1","09","03","09","  ","  ","Front End Enclosure (FEE)                                   ",0,2042883,0,2042883,2029284,null,0,2038131.9,0,2038131.9,2038131.9,0,null,0,null,2025921.5666666667,null,12210.333333333334,null,0,null,null,305719.7850000001]
["1","09","03","09","01","  ","FEE - Site Preparation/General Requirements                 "]
["1","09","03","09","02","  ","FEE - Site Construction                                     "]
["1","09","03","09","03","  ","FEE - Concrete                                              ",0,1282593,0,1282593,1282593,null,0,1282593,0,1282593,1282593,0,null,0,null,1282593,null,0,null,0,null,null,192388.95]
["1","09","03","09","04","  ","Utilities                                                   "]
["1","09","03","09","05","  ","FEE - Metals                                                ",0,4537,0,4537,4537,null,0,4537,0,4537,4537,0,null,0,null,4537,null,0,null,0,null,null,680.55]
["1","09","03","09","06","  ","Special System (Fire Protection) Beam Dump                  "]
["1","09","03","09","09","  ","Tunneling                                                   "]
["1","09","03","09","10","  ","Project Close Out Beam Dump                                 "]
["1","09","03","09","15","  ","FEE - Mechanical                                            ",0,270466,0,270466,269116,null,0,270466,0,270466,270466,0,null,0,null,270016,null,450,null,0,null,null,40569.9]
["1","09","03","09","16","  ","FEE - Electrical                                            ",0,297085,0,297085,284836,null,0,292333.9,0,292333.9,292333.9,0,null,0,null,291426.56666666665,null,907.3333333333333,null,0,null,null,43850.085]
["1","09","03","09","17","  ","FEE - Others (include Div 4, and 6 through 14)              ",0,188202,0,188202,188202,null,0,188202,0,188202,188202,0,null,0,null,177349,null,10853,null,0,null,null,28230.3]
["1","09","03","09","20","  ","FEE - Project Close Out                                     "]
["1","09","03","10","  ","  ","Electron Beam Dump (EBD)                                    ",0,2716633,0,2716633,2673283,null,0,2199693.65,0,2199693.65,2199693.65,0,null,0,null,1548486.076923077,null,651207.573076923,null,0,null,null,363353.04750000004]
["1","09","03","10","01","  ","EBD - Site Preparation/General Requirements                 ",0,639650,0,639650,639650,null,0,123930,0,123930,123930,0,null,0,null,123930,null,0,null,0,null,null,51988.5]
["1","09","03","10","02","  ","EBD - Site Construction                                     "]
["1","09","03","10","03","  ","EBD - Concrete                                              ",0,1289554,0,1289554,1246204,null,0,1289554,0,1289554,1289554,0,null,0,null,1185527.076923077,null,104026.92307692308,null,0,null,null,193433.1]
["1","09","03","10","04","  ","Utilities                                                   "]
["1","09","03","10","05","  ","EBD - Metals                                                ",0,225818,0,225818,225818,null,0,225818,0,225818,225818,0,null,0,null,0,null,225818,null,0,null,null,33872.7]
["1","09","03","10","06","  ","Special System - Fire Protection                            "]
["1","09","03","10","07","  ","Interior                                                    "]
["1","09","03","10","10","  ","Project Close Out Near Experimental Hall                    "]
["1","09","03","10","15","  ","EBD - Mechanical                                            ",0,228663,0,228663,228663,null,0,228663,0,228663,228663,0,null,0,null,30000,null,198663,null,0,null,null,34299.45]
["1","09","03","10","16","  ","EBD - Electrical                                            ",0,210476,0,210476,210476,null,0,209256.65,0,209256.65,209256.65,0,null,0,null,91958,null,117298.65,null,0,null,null,31388.497499999998]
["1","09","03","10","17","  ","EBD - Others (include Div 4, and 6 through 14)              ",0,122472,0,122472,122472,null,0,122472,0,122472,122472,0,null,0,null,117071,null,5401,null,0,null,null,18370.8]
["1","09","03","10","20","  ","EBD - Project Close Out                                     "]
["1","09","03","11","  ","  ","Near Experimental Hall (NEH)                                ",0,17834434,0,17834434,15422702,null,0,14244020.240000002,0,14244020.240000002,14244020.240000002,0,null,0,null,10189574.136984784,null,4054446.103015217,null,0,null,null,2175603.036]
["1","09","03","11","01","  ","NEH - Site Preparation/General Requirements                 ",0,3036540,0,3036540,2936540,null,0,753562.39,0,753562.39,753562.39,0,null,0,null,638732.0192134832,null,114830.37078651685,null,0,null,null,113034.35849999999]
["1","09","03","11","02","  ","NEH - Site Construction                                     ",0,200000,0,200000,0,null,0,200000,0,200000,200000,0,null,0,null,182828.28282828283,null,17171.71717171717,null,0,null,null,60000]
["1","09","03","11","03","  ","NEH - Concrete                                              ",0,4550571,0,4550571,4542071,null,0,3890601,0,3890601,3890601,0,null,0,null,3798411,null,92190,null,0,null,null,583590.15]
["1","09","03","11","04","  ","Utilities                                                   "]
["1","09","03","11","05","  ","NEH - Metals                                                ",0,533354,0,533354,533354,null,0,533354,0,533354,533354,0,null,0,null,533354,null,0,null,0,null,null,80003.1]
["1","09","03","11","06","  ","Special System - Fire Protection                            "]
["1","09","03","11","07","  ","Interiors                                                   "]
["1","09","03","11","09","  ","Tunneling                                                   "]
["1","09","03","11","10","  ","Project Close Out X-Ray Transport & Diagonistic             "]
["1","09","03","11","15","  ","NEH - Mechanical                                            ",0,4792889,0,4792889,4056888,null,0,4251475,0,4251475,4251475,0,null,0,null,3191153.2659698026,null,1060321.7340301974,null,0,null,null,637721.25]
["1","09","03","11","16","  ","NEH - Electrical                                            ",0,1976439,0,1976439,1582781,null,0,1870386.85,0,1870386.85,1870386.85,0,null,0,null,1240479.5142857144,null,629907.3357142857,null,0,null,null,280558.02749999997]
["1","09","03","11","17","  ","NEH - Others (include Div 4, and 6 through 14)              ",0,2564641,0,2564641,1591068,null,0,2564641,0,2564641,2564641,0,null,0,null,604616.0546875,null,1960024.9453125,null,0,null,null,384696.15]
["1","09","03","11","20","  ","NEH - Project Close Out                                     ",0,180000,0,180000,180000,null,0,180000,0,180000,180000,0,null,0,null,0,null,180000,null,0,null,null,36000]
["1","09","03","12","  ","  ","Undulator Hall (UH)                                         ",0,8783003,0,8783003,7410374,null,0,6437754.079,0,6437754.404,6437754.404,0,null,0,null,5989108.17578371,null,448646.2282162905,null,0,null,null,965663.1606]
["1","09","03","12","01","  ","UH - Site Preparation/General Requirements                  ",0,2558169,0,2558169,2266504,null,0,681768.525,0,681769,681769,0,null,0,null,565278.4574979952,null,116490.54250200481,null,0,null,null,102265.35]
["1","09","03","12","02","  ","UH - Site Construction                                      "]
["1","09","03","12","03","  ","UH - Concrete                                               "]
["1","09","03","12","04","  ","Utilities                                                   "]
["1","09","03","12","05","  ","UH - Metals                                                 "]
["1","09","03","12","06","  ","Special System - Fire Protection                            "]
["1","09","03","12","07","  ","Interiors                                                   "]
["1","09","03","12","09","  ","Tunneling                                                   "]
["1","09","03","12","10","  ","Project Close Out Far Experimental Hall                     "]
["1","09","03","12","15","  ","UH - Mechanical                                             ",0,542293,0,542293,191892,null,0,542293,0,542293,542293,0,null,0,null,294049.6,null,248243.4,null,0,null,null,81343.95]
["1","09","03","12","16","  ","UH - Electrical                                             ",0,1163798,0,1163798,433235,null,0,973535.15,0,973535,973535,0,null,0,null,889622.7142857143,null,83912.28571428571,null,0,null,null,146030.25]
["1","09","03","12","17","  ","UH - Others (include Div 4, and 6 through 14)               ",0,18610,0,18610,18610,null,0,18610,0,18610,18610,0,null,0,null,18610,null,0,null,0,null,null,2791.5]
["1","09","03","12","19","  ","UH - Tunnel Construction                                    ",0,4500133,0,4500133,4500133,null,0,4221547.404,0,4221547.404,4221547.404,0,null,0,null,4221547.404,null,0,null,0,null,null,633232.1106]
["1","09","03","12","20","  ","UH - Project Close Out                                      "]
["1","09","03","13","  ","  ","X-Ray - Transport & Diagnostic Hall (XRTD)                  ",0,5055749,0,5055749,4017849,null,0,5055749,0,5055749,5055749,0,null,0,null,3498214,null,1557535,null,0,null,null,758362.35]
["1","09","03","13","01","  ","XRTD - Site Preparation/General Requirements                "]
["1","09","03","13","02","  ","XRTD - Site Construction                                    "]
["1","09","03","13","03","  ","XRTD - Concrete                                             "]
["1","09","03","13","04","  ","Utilities                                                   "]
["1","09","03","13","05","  ","HVAC                                                        "]
["1","09","03","13","06","  ","Special System - Fire Protection                            "]
["1","09","03","13","07","  ","Interior                                                    "]
["1","09","03","13","10","  ","Project Close Out Central Laboratory Office Complex (CLOC)  "]
["1","09","03","13","15","  ","XRTD - Mechanical                                           ",0,293687,0,293687,293687,null,0,293687,0,293687,293687,0,null,0,null,0,null,293687,null,0,null,null,44053.05]
["1","09","03","13","16","  ","XRTD - Electrical                                           ",0,628639,0,628639,628639,null,0,628639,0,628639,628639,0,null,0,null,0,null,628639,null,0,null,null,94295.85]
["1","09","03","13","17","  ","XRTD - Others (include Div 4, and 6 through 14)             ",0,5356,0,5356,5356,null,0,5356,0,5356,5356,0,null,0,null,0,null,5356,null,0,null,null,803.4]
["1","09","03","13","19","  ","XRTD - Tunnel Construction                                  ",0,4128067,0,4128067,3090167,null,0,4128067,0,4128067,4128067,0,null,0,null,3498214,null,629853,null,0,null,null,619210.05]
["1","09","03","13","20","  ","XRTD - Project Close Out                                    "]
["1","09","03","14","  ","  ","Far Experimental Hall (FEH)                                 ",0,8323230,0,8323230,8323230,null,0,7731470.96,0,7731470.96,7731470.96,0,null,0,null,3333614.96,null,4397856,null,0,null,null,1159720.6439999999]
["1","09","03","14","01","  ","FEH - Site Preparation/General Requirements                 "]
["1","09","03","14","02","  ","FEH - Site Construction                                     "]
["1","09","03","14","03","  ","FEH - Concrete                                              "]
["1","09","03","14","05","  ","FEH - Metals                                                "]
["1","09","03","14","15","  ","FEH - Mechanical                                            ",0,1194448,0,1194448,1194448,null,0,1194448,0,1194448,1194448,0,null,0,null,0,null,1194448,null,0,null,null,179167.2]
["1","09","03","14","16","  ","FEH - Electrical                                            ",0,583480,0,583480,583480,null,0,583480,0,583480,583480,0,null,0,null,0,null,583480,null,0,null,null,87522]
["1","09","03","14","17","  ","FEH - Others (include Div 4, and 6 through 14)              ",0,533813,0,533813,533813,null,0,533813,0,533813,533813,0,null,0,null,0,null,533813,null,0,null,null,80071.95]
["1","09","03","14","18","  ","FEH - Access Tunnel                                         ",0,2515883,0,2515883,2515883,null,0,1924123.96,0,1924123.96,1924123.96,0,null,0,null,719056.96,null,1205067,null,0,null,null,288618.594]
["1","09","03","14","19","  ","FEH - Tunnel Construction                                   ",0,3495606,0,3495606,3495606,null,0,3495606,0,3495606,3495606,0,null,0,null,2614558,null,881048,null,0,null,null,524340.9]
["1","09","03","14","20","  ","FEH - Project Close Out                                     "]
["1","09","03","15","  ","  ","BTH Service Buildings 2.1, 2.2, and 2.3 (SB BTH)            ",0,3306437,0,3306437,2311805,null,0,3301313.9,0,3301313.9,3301313.9,0,null,0,null,2676390.523076923,null,624923.3769230769,null,0,null,null,495197.085]
["1","09","03","15","03","  ","SB BTH - Concrete                                           "]
["1","09","03","15","05","  ","SB BTH - Metals                                             ",0,114548,0,114548,114548,null,0,114548,0,114548,114548,0,null,0,null,114548,null,0,null,0,null,null,17182.2]
["1","09","03","15","15","  ","SB BTH - Mechanical                                         ",0,971016,0,971016,900516,null,0,971016,0,971016,971016,0,null,0,null,799437.923076923,null,171578.07692307694,null,0,null,null,145652.4]
["1","09","03","15","16","  ","SB BTH - Electrical                                         ",0,1293721,0,1293721,1293721,null,0,1288597.9,0,1288597.9,1288597.9,0,null,0,null,835252.6,null,453345.3,null,0,null,null,193289.68499999997]
["1","09","03","15","17","  ","SB BTH - Others (include Div 4, and 6 through 14            ",0,927152,0,927152,3020,null,0,927152,0,927152,927152,0,null,0,null,927152,null,0,null,0,null,null,139072.8]
["1","09","03","15","20","  ","SB BTH - Project Close Out                                  "]
["1","09","03","16","  ","  ","UH Service Building 3.1 (SB UH)                             ",0,1778931,0,1778931,1778931,null,0,1776611.45,0,1776611.45,1776611.45,0,null,0,null,1772680.45,null,3931,null,0,null,null,266491.71749999997]
["1","09","03","16","01","  ","SB UH - Site Preparation                                    "]
["1","09","03","16","03","  ","SB UH - Concrete                                            ",0,123153,0,123153,123153,null,0,123153,0,123153,123153,0,null,0,null,123153,null,0,null,0,null,null,18472.95]
["1","09","03","16","05","  ","SB UH - Metals                                              ",0,13908,0,13908,13908,null,0,13908,0,13908,13908,0,null,0,null,13908,null,0,null,0,null,null,2086.2]
["1","09","03","16","15","  ","SB UH - Mechanical                                          ",0,740435,0,740435,740435,null,0,740435,0,740435,740435,0,null,0,null,740435,null,0,null,0,null,null,111065.25]
["1","09","03","16","16","  ","SB UH - Electrical                                          ",0,439596,0,439596,439596,null,0,437276.45,0,437276.45,437276.45,0,null,0,null,433345.45,null,3931,null,0,null,null,65591.4675]
["1","09","03","16","17","  ","SB UH - Others (include Div 4, and 6 through 14)            ",0,461839,0,461839,461839,null,0,461839,0,461839,461839,0,null,0,null,461839,null,0,null,0,null,null,69275.85]
["1","09","03","16","20","  ","SB UH - Project Close Out                                   "]
["1","09","03","17","  ","  ","FEH Service Building 8.1 (FEH SB)                           ",0,847382,0,847382,847382,null,0,847382,0,847382,847382,0,null,0,null,0,null,847382,null,0,null,null,127107.3]
["1","09","03","17","01","  ","SB FEH - Site Preparation                                   "]
["1","09","03","17","03","  ","SB FEH - Concrete                                           ",0,597473,0,597473,597473,null,0,597473,0,597473,597473,0,null,0,null,0,null,597473,null,0,null,null,89620.95]
["1","09","03","17","05","  ","SB FEH - Metals                                             "]
["1","09","03","17","15","  ","SB FEH - Mechanical                                         "]
["1","09","03","17","16","  ","SB FEH - Electrical                                         ",0,249909,0,249909,249909,null,0,249909,0,249909,249909,0,null,0,null,0,null,249909,null,0,null,null,37486.35]
["1","09","03","17","17","  ","SB FEH - Others (include Div 4, and 6 through 14            "]
["1","09","03","17","20","  ","SB FEH - Project Close Out                                  "]
["1","09","03","18","  ","  ","NEH Central Utility Plant (CUP)                             ",0,5492014,0,5492014,3756109,null,0,5439981.724,0,5439981.724,5439981.724,0,null,0,null,3870935.5992762456,null,1569046.124723755,null,0,null,null,1025566.6086000002]
["1","09","03","18","01","  ","CUP - Site Preparation/General Requirements                 ",0,4428,0,4428,4428,null,0,871,0,871,871,0,null,0,null,871,null,0,null,0,null,null,0]
["1","09","03","18","02","  ","CUP - Site Construction                                     ",0,108000,0,108000,108000,null,0,108000,0,108000,108000,0,null,0,null,108000,null,0,null,0,null,null,43200]
["1","09","03","18","03","  ","CUP - Concrete                                              ",0,688071,0,688071,688071,null,0,688071,0,688071,688071,0,null,0,null,688071,null,0,null,0,null,null,103210.65]
["1","09","03","18","05","  ","CUP - Metals                                                ",0,44986,0,44986,44986,null,0,44986,0,44986,44986,0,null,0,null,44986,null,0,null,0,null,null,6747.9]
["1","09","03","18","15","  ","CUP - Mechanical                                            ",0,1644896,0,1644896,716852,null,0,1638103.7,0,1638103.7,1638103.7,0,null,0,null,389214.421875,null,1248889.278125,null,0,null,null,245715.555]
["1","09","03","18","16","  ","CUP - Electrical                                            ",0,2550696,0,2550696,2080642,null,0,2509013.024,0,2509013.024,2509013.024,0,null,0,null,2264481.704,null,244531.32,null,0,null,null,559051.9535999999]
["1","09","03","18","17","  ","CUP - Others (include Div 4, and 6 through 14)              ",0,450937,0,450937,113130,null,0,450937,0,450937,450937,0,null,0,null,375311.47340124496,null,75625.52659875495,null,0,null,null,67640.55]
["1","09","03","18","20","  ","CUP - Project Close Out                                     "]
["1","09","03","19","  ","  ","SLAC Space Renovation for LCLS Ops                          ",0,5024000,0,5024000,3026525,null,0,5024000,0,5024000,5024000,0,null,0,null,339209.00906931545,null,4529590.37322369,null,155200.6177069948,null,null,831647.5]
["1","09","03","19","01","  ","ED&I of SLAC Space Renovation for LCLS Ops                  ",0,780475,0,780475,447000,null,0,780475,0,780475,780475,0,null,0,null,339209.00906931545,null,413365.91967177717,null,27900.071258907363,null,null,195118.75]
["1","09","03","19","02","  ","Construction of SLAC Space Renovation for LCLS Ops          ",0,4243525,0,4243525,2579525,null,0,4243525,0,4243525,4243525,0,null,0,null,0,null,4116224.4535519127,null,127300.54644808744,null,null,636528.75]
["1","09","03","20","  ","  ","Construction Credits and Debits                             "]
["1","09","03","20","01","  ","Reduction for Subcontractor Work in Deleting CLOC           "]
["1","09","03","20","02","  ","Bulletin #2 Changes                                         "]
["2","  ","  ","  ","  ","  ","LCLS PROJECT - R&D, SPARES, COMMISSIONING                   ",221423,20057641,25981674.12736722,20705941.186697185,44862754.58289326,null,206103.96,18878425.169999998,24169949.93372063,19330193.76834396,43500143.70206465,0,null,489140.80341074715,null,11658264.680352401,null,16636199.023838587,null,14716539.194462847,null,null,1230.8116201886025]
["2","01","  ","  ","  ","  ","LCLS PROJECT MGMT, PLANNING & ADMN (OPC)                    ",100090,12067844,11882717.756265732,12537007.751322258,23011766.11852282,null,92665.8,11903815.27,11077088.54150033,12252716.202445265,23329804.743945595,0,null,413053.5444342791,null,5345255.738174695,null,6973096.4032741515,null,10598399.058062473,null,null,0]
["2","01","01","  ","  ","  ","Physics Support (OPC)                                       ",53918,1296840,6367533.688742801,1427610.029638631,7465352.055734943,null,48724.8,1247240,5804142.9124683,1319867.2293342068,7124010.141802507,0,null,386961.6421982649,null,2657911.4565831753,null,2811770.713916656,null,1267366.3291044123,null,null,0]
["2","01","01","01","  ","  ","LCLS Commissioning Management                               ",4816,0,692396.0308181101,0,692396.0308181101,null,4382.56,0,630143.6468180598,0,630143.6468180598,0,null,74421.61172488218,null,222654.82196378688,null,223264.83517464658,null,109802.37795474421,null,null,0]
["2","01","01","02","  ","  ","Injector Physics                                            ",6812,0,846048.2019304807,0,846048.2019304807,null,6480.12,0,807581.7445697716,0,807581.7445697716,0,null,39265.72155824367,null,345816.5589901034,null,299274.4694478925,null,123224.99457353205,null,null,0]
["2","01","01","03","  ","  ","Linac Physics                                               ",4519,0,386863.89290587255,0,386863.89290587255,null,4221,0,362434.6491082325,0,362434.6491082325,0,null,0,null,144973.85964329302,null,145770.41931166276,null,71690.37015327676,null,null,0]
["2","01","01","04","  ","  ","Undulator Physics                                           ",4519,0,386863.89290587255,0,386863.89290587255,null,4221,0,362434.6491082325,0,362434.6491082325,0,null,0,null,144973.85964329302,null,145770.41931166276,null,71690.37015327676,null,null,0]
["2","01","01","05","  ","  ","X-Ray Transport Physics                                     ",4816,0,692396.0308181101,0,692396.0308181101,null,4382.56,0,630143.6468180598,0,630143.6468180598,0,null,74421.61172488218,null,222654.82196378688,null,223264.83517464658,null,109802.37795474421,null,null,0]
["2","01","01","06","  ","  ","X-Ray Physics Commissioning                                 ",4221,0,362442.8027528992,0,362442.8027528992,null,4221,0,362442.8027528992,0,362442.8027528992,0,null,0,null,144737.88492772542,null,145934.06579489668,null,71770.85203027706,null,null,0]
["2","01","01","07","  ","  ","Conventional Facilities Physics                             ",2437,0,347345.76624927775,0,347345.76624927775,null,2139,0,306221.2577510178,0,306221.2577510178,0,null,0,null,186633.15647324614,null,107199.98066011704,null,12388.120617654582,null,null,0]
["2","01","01","08","  ","  ","Consulting Physics (Collaboration)                          ",0,300000,0,329791.6626464898,0,null,0,273000,0,245896.3823420654,245896.3823420654,0,null,29041.005465374616,null,86884.97536771913,null,87123.01639612386,null,42847.38511284779,null,null,0]
["2","01","01","09","  ","  ","Consulting Physics (SLAC)                                   ",6498,0,699832.2453152512,0,699832.2453152512,null,3831,0,451648.0744951519,0,451648.0744951519,0,null,0,null,203355.8858243438,null,201882.8722289777,null,46409.316441830335,null,null,0]
["2","01","01","10","  ","  ","Global Controls Physics Liaison                             ",4816,0,692396.0308181101,0,692396.0308181101,null,4382.56,0,630143.6468180598,0,630143.6468180598,0,null,74421.61172488218,null,222654.82196378688,null,223264.83517464658,null,109802.37795474421,null,null,0]
["2","01","01","11","  ","  ","Global Controls OPC                                         ",10464,996840,1260948.7942288157,1097818.3669921411,2358767.161220957,null,10464,974240,1260948.7942288157,1073970.846992141,2334919.641220957,0,null,95390.08,null,732570.8098220904,null,1009020.9652413827,null,497937.7861574841,null,null,0]
["2","01","01","11","01","  ","EPICS Control Modules                                       "]
["2","01","01","11","02","  ","LLRF Controls - Closed                                      "]
["2","01","01","11","04","  ","Laser Controls Design                                       "]
["2","01","01","11","05","  ","Laser Heater Controls Design                                "]
["2","01","01","11","06","  ","Timing Controls                                             "]
["2","01","01","11","07","  ","Vacuum Controls                                             "]
["2","01","01","11","08","  ","S/W & Controls Infrastructure                               "]
["2","01","01","11","09","  ","Power Supply Control                                        "]
["2","01","01","11","10","  ","MPS/PPS/BCS Controls                                        "]
["2","01","01","11","11","  ","Global Controls Commissioning                               "]
["2","01","01","11","12","  ","Global Controls Management - OPC                            ",9193,883840,1139822.177959543,978580.7669921411,2118402.944951684,null,9193,883840,1139822.177959543,978580.7669921411,2118402.944951684,0,null,0,null,637349.886049714,null,983115.2727444862,null,497937.7861574841,null,null,0]
["2","01","01","11","12","01","                                                            ",9193,883840,1139822.177959543,978580.7669921411,2118402.944951684,null,9193,883840,1139822.177959543,978580.7669921411,2118402.944951684,0,null,0,null,637349.886049714,null,983115.2727444862,null,497937.7861574841,null,null,0]
["2","01","01","11","13","  ","SLC Aware IOC                                               "]
["2","01","01","11","14","  ","Controls - Networking and Data Comm. OPC                    ",1271,0,121126.61626927282,0,121126.61626927282,null,1271,0,121126.61626927282,0,121126.61626927282,0,null,0,null,95220.92377237634,null,25905.6924968965,null,0,null,null,0]
["2","01","01","11","15","  ","Controls S/W Applications LOE                               ",0,113000,0,119237.6,119237.6,null,0,90400,0,95390.08,95390.08,0,null,95390.08,null,0,null,0,null,0,null,null,0]
["2","01","02","  ","  ","  ","R&D Studies & Prototyping                                   "]
["2","01","02","01","  ","  ","R&D Studies & Prototyping                                   "]
["2","01","03","  ","  ","  ","Project Mgmnt, Planning and Admn - M&S (OPC)                ",46172,10771004,5515184.067522932,11109397.721683625,15546414.062787883,null,43941,10656575.27,5272945.629032031,10932848.973111058,16205794.602143086,0,null,26091.902236014175,null,2687344.2815915197,null,4161325.689357496,null,9331032.728958061,null,null,0]
["2","01","03","01","  ","  ","SLAC Project Office - General                               ",38320,0,4855187.084090032,0,4855187.084090032,null,36683,0,4657152.860581091,0,4657152.860581091,0,null,0,null,1363318.909773167,null,2119419.0377293346,null,1174414.913078589,null,null,0]
["2","01","03","02","  ","  ","SLAC Project Support                                        ",7852,1248307,659996.9834329012,1369692.6317880976,1769758.3334535907,null,7258,1155427,615792.7684509412,1271685.6557880973,1887478.4242390387,0,null,0,null,686835.8094932198,null,878274.7557339298,null,322367.85901188914,null,null,0]
["2","01","03","03","  ","  ","Project Mgmnt, Planning and Admn - M&S (OPC)                ",0,9522697,0,9739705.089895528,8921468.645244263,null,0,9501148.27,0,9661163.31732296,9661163.31732296,0,null,26091.902236014175,null,637189.5623251327,null,1163631.8958942313,null,7834249.956867583,null,null,0]
["2","01","03","05","  ","  ","X-Ray Transport Physics                                     "]
["2","01","03","06","  ","  ","X-Ray Endstation Physics                                    "]
["2","01","03","07","  ","  ","Conventional Facilities Physics                             "]
["2","01","03","08","  ","  ","Consulting Physics (Collaboration)                          "]
["2","01","03","09","  ","  ","Consulting Physics (SLAC)                                   "]
["2","01","03","10","  ","  ","Global Controls Physics Liaison                             "]
["2","01","03","11","  ","  "," Physics Commissioning Support - General                    "]
["2","02","  ","  ","  ","  ","INJECTOR SYSTEM (OPC)                                       ",29109,1330810,3141761.328202904,1449441.566037212,4479105.929295834,null,24928.4,1078854.2,2707530.871170044,1179260.181568771,3886791.0527388155,0,null,0,null,2657072.24776834,null,1219287.817184905,null,10430.987785569461,null,null,0]
["2","02","01","  ","  ","  ","Injector System Management & Integration                    "]
["2","02","01","01","  ","  ","Injector System Integration Effort / M&S                    "]
["2","02","01","02","  ","  ","High level Application Software                             "]
["2","02","01","03","  ","  ","Feedback Software                                           "]
["2","02","02","  ","  ","  ","Injector Controls Subsystem                                 ",9032,49200,920543.7791236484,52478.98947265306,962297.1989636485,null,8212.2,14200,848418.4952784977,15373.419839999999,863791.9151184977,0,null,0,null,859664.3169974178,null,4127.598121079901,null,0,null,null,0]
["2","02","02","01","  ","  ","Personnel Protection System (PPS) R&D                       ",1132,35000,105595.86678763793,37105.56963265306,131975.86678763793,null,388,0,41954.69983024187,0,41954.69983024187,0,null,0,null,41954.69983024187,null,0,null,0,null,null,0]
["2","02","02","02","  ","  ","Beam Containment Subsystem (BCS)                            ",220,0,27188.451614491198,0,27188.451614491198,null,182.6,0,22566.414840027694,0,22566.414840027694,0,null,0,null,22566.414840027694,null,0,null,0,null,null,0]
["2","02","02","03","  ","  ","Machine Protection Subsystem (MPS)                          ",1280,0,143846.06490650878,0,143846.06490650878,null,1280,0,143846.06490650878,0,143846.06490650878,0,null,0,null,143846.06490650878,null,0,null,0,null,null,0]
["2","02","02","04","  ","  ","Power Conv (beamline pwr supp) Spares                       ",0,14200,0,15373.419839999999,15373.419839999999,null,0,14200,0,15373.419839999999,15373.419839999999,0,null,0,null,15373.419839999999,null,0,null,0,null,null,0]
["2","02","02","04","01","  ","Power Supply Controls                                       "]
["2","02","02","05","  ","  ","LLRF Controls                                               ",1680,0,166645.30132055518,0,166645.30132055518,null,1680,0,166645.30132055518,0,166645.30132055518,0,null,0,null,166645.30132055518,null,0,null,0,null,null,0]
["2","02","02","05","01","  ","LLRF Controls                                               ",1680,0,166645.30132055518,0,166645.30132055518,null,1680,0,166645.30132055518,0,166645.30132055518,0,null,0,null,166645.30132055518,null,0,null,0,null,null,0]
["2","02","02","06","  ","  ","E-Beam Diagnostics Controls                                 ",2280,0,228382.72527228843,0,228382.72527228843,null,2241.6,0,224520.6451589972,0,224520.6451589972,0,null,0,null,224520.6451589972,null,0,null,0,null,null,0]
["2","02","02","06","01","  ","Controls - Wire Scanners                                    ",200,0,20115.000590057993,0,20115.000590057993,null,200,0,20115.000590057993,0,20115.000590057993,0,null,0,null,20115.000590057993,null,0,null,0,null,null,0]
["2","02","02","06","02","  ","Controls - BPM Processor Module                             ",1440,0,143899.72279404476,0,143899.72279404476,null,1440,0,143899.72279404476,0,143899.72279404476,0,null,0,null,143899.72279404476,null,0,null,0,null,null,0]
["2","02","02","06","03","  ","Controls - Toroids                                          ",40,0,4023.000118011599,0,4023.000118011599,null,40,0,4023.000118011599,0,4023.000118011599,0,null,0,null,4023.000118011599,null,0,null,0,null,null,0]
["2","02","02","06","05","  ","Controls - Profile Monitors                                 ",80,0,8046.000236023198,0,8046.000236023198,null,56,0,5632.200165216239,0,5632.200165216239,0,null,0,null,5632.200165216239,null,0,null,0,null,null,0]
["2","02","02","06","06","  ","Control - EO Diagnostic                                     "]
["2","02","02","06","12","  ","Controls - Movable Collimator                               ",400,0,40230.001180115985,0,40230.001180115985,null,400,0,40230.001180115985,0,40230.001180115985,0,null,0,null,40230.001180115985,null,0,null,0,null,null,0]
["2","02","02","06","14","  ","Controls - Faraday Cup                                      ",40,0,4023.000118011599,0,4023.000118011599,null,35.2,0,3540.2401038502076,0,3540.2401038502076,0,null,0,null,3540.2401038502076,null,0,null,0,null,null,0]
["2","02","02","06","15","  ","Controls - Tune-Up Dump                                     ",40,0,4023.000118011599,0,4023.000118011599,null,35.2,0,3540.2401038502076,0,3540.2401038502076,0,null,0,null,3540.2401038502076,null,0,null,0,null,null,0]
["2","02","02","06","16","  ","Cherenkov Commissioning Support                             ",40,0,4023.000118011599,0,4023.000118011599,null,35.2,0,3540.2401038502076,0,3540.2401038502076,0,null,0,null,3540.2401038502076,null,0,null,0,null,null,0]
["2","02","02","08","  ","  ","Timing Controls                                             ",1600,0,166618.4723767872,0,166618.4723767872,null,1600,0,166618.4723767872,0,166618.4723767872,0,null,0,null,166618.4723767872,null,0,null,0,null,null,0]
["2","02","02","09","  ","  ","Vacuum Controls                                             ",800,0,78139.2987243,0,78139.2987243,null,800,0,78139.2987243,0,78139.2987243,0,null,0,null,78139.2987243,null,0,null,0,null,null,0]
["2","02","02","10","  ","  ","Software & Controls Infrastructure                          "]
["2","02","02","11","  ","  ","EPICS VXI Control Modules                                   "]
["2","02","02","12","  ","  ","Laser Controls                                              "]
["2","02","02","13","  ","  ","Laser Heater Controls                                       ",40,0,4127.598121079901,0,4127.598121079901,null,40,0,4127.598121079901,0,4127.598121079901,0,null,0,null,0,null,4127.598121079901,null,0,null,null,0]
["2","02","03","  ","  ","  ","Injector Lasers                                             ",6240,502000,815624.4481184707,543539.1674304,1359163.6155488708,null,4992,472000,652499.5584947766,511060.11143039993,1163559.6699251765,0,null,0,null,1021786.1737993619,null,141773.49612581465,null,0,null,null,0]
["2","02","03","01","  ","  ","Drive Laser Prototyping                                     "]
["2","02","03","02","  ","  ","Drive Laser System                                          ",0,500000,0,541317.6,541317.6,null,0,470000,0,508838.54399999994,508838.54399999994,0,null,0,null,508838.54399999994,null,0,null,0,null,null,0]
["2","02","03","03","  ","  ","Drive Laser Diagnostics                                     ",6240,0,815624.4481184707,0,815624.4481184707,null,4992,0,652499.5584947766,0,652499.5584947766,0,null,0,null,512947.629799362,null,139551.92869541465,null,0,null,null,0]
["2","02","03","04","  ","  ","Timing Stability Monitoring                                 "]
["2","02","03","05","  ","  ","Steering Stability Feedback & Msmts                         "]
["2","02","03","06","  ","  ","Pre Amp Low Power Comp                                      "]
["2","02","03","07","  ","  ","Transport to Tunnel & Relay Optics                          "]
["2","02","03","08","  ","  ","UV Launch, Conditioning & Diagnostics                       "]
["2","02","03","09","  ","  ","Load Lock Transport System                                  "]
["2","02","03","10","  ","  ","Visible Optical Transport & Optics                          "]
["2","02","03","11","  ","  ","LB Infrastructure & LB System Wide Items                    "]
["2","02","03","12","  ","  ","Alignment Laser                                             "]
["2","02","03","13","  ","  ","Light path to Streak Camera                                 "]
["2","02","03","14","  ","  ","LSR HTR - Beam Conditioning Optics (Laser Bay)              ",0,2000,0,2221.5674303999995,2221.5674303999995,null,0,2000,0,2221.5674303999995,2221.5674303999995,0,null,0,null,0,null,2221.5674303999995,null,0,null,null,0]
["2","02","03","15","  ","  ","LSR HTR - Transport Optics (Bay to Tunnel)                  "]
["2","02","03","16","  ","  ","LSR HTR - Photon Beam Diagnostics                           "]
["2","02","04","  ","  ","  ","Injector RF Subsystem                                       ",1334,209660,125554.36621952523,225177.12494362792,249360.0958515252,null,504.8,57128,54199.126699391665,61848.78370559999,116047.91040499165,0,null,0,null,116047.91040499165,null,0,null,0,null,null,0]
["2","02","04","01","  ","  ","RF Gun & Load Lock                                          ",1334,14660,125554.36621952523,15542.209632,141096.5758515252,null,504.8,2128,54199.126699391665,2303.8477055999997,56502.97440499166,0,null,0,null,56502.97440499166,null,0,null,0,null,null,0]
["2","02","04","01","01","  ","RF Gun                                                      ",1334,14660,125554.36621952523,15542.209632,141096.5758515252,null,504.8,2128,54199.126699391665,2303.8477055999997,56502.97440499166,0,null,0,null,56502.97440499166,null,0,null,0,null,null,0]
["2","02","04","01","02","  ","RF Gun Supports                                             "]
["2","02","04","01","03","  ","Gun Load Lock                                               "]
["2","02","04","01","04","  ","Gun Load Lock Supports                                      "]
["2","02","04","01","05","  ","Gun Solenoid                                                "]
["2","02","04","01","06","  ","Gun Solenoid Supports                                       "]
["2","02","04","01","07","  ","Gun RF Feed                                                 "]
["2","02","04","01","08","  ","Gun RF Feed Supports                                        "]
["2","02","04","02","  ","  ","Cathode Processing (CP) Station                             ",0,100000,0,108263.52,108263.52,null,0,55000,0,59544.935999999994,59544.935999999994,0,null,0,null,59544.935999999994,null,0,null,0,null,null,0]
["2","02","04","02","01","  ","CP Cathode Assembly & Supports                              "]
["2","02","04","02","02","  ","CP Load Lock                                                ",0,100000,0,108263.52,108263.52,null,0,55000,0,59544.935999999994,59544.935999999994,0,null,0,null,59544.935999999994,null,0,null,0,null,null,0]
["2","02","04","02","03","  ","CP Load Lock Supports                                       "]
["2","02","04","02","04","  ","CP Station                                                  "]
["2","02","04","02","05","  ","Cathode Lab Infrastructure                                  "]
["2","02","04","03","  ","  ","S-Band Low Level System                                     "]
["2","02","04","03","01","  ","S-Band LL Controls Timing System                            "]
["2","02","04","04","  ","  ","S-Band High Power System                                    "]
["2","02","04","05","  ","  ","Injector RF Waveguide Subsystem                             ",0,95000,0,101371.3953116279,0,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["2","02","04","05","01","  ","RF Waveguides                                               "]
["2","02","04","05","02","  ","RF Waveguide Supports                                       ",0,95000,0,101371.3953116279,0,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["2","02","04","06","  ","  ","Injector Linac Structures                                   "]
["2","02","04","06","01","  ","L0-1 Structure Assembly                                     "]
["2","02","04","06","02","  ","L0-2 Structure Assembly                                     "]
["2","02","04","06","03","  ","Major Linac Support                                         "]
["2","02","04","06","04","  ","GTL RF Phase Cavity                                         "]
["2","02","04","06","05","  ","LTDL1 RF Kicker                                             "]
["2","02","05","  ","  ","  ","Injector Magnets & Supports                                 "]
["2","02","05","01","  ","  ","Injector Dipoles                                            "]
["2","02","05","01","01","  ","DL1 B01 & B02 Dipoles                                       "]
["2","02","05","01","02","  ","SAB Spectrometer Dipole                                     "]
["2","02","05","01","03","  ","Chicane                                                     "]
["2","02","05","02","  ","  ","Injector Quadrupoles                                        "]
["2","02","05","02","01","  ","L0-1TL0-2 Quadrupoles ( )                                   "]
["2","02","05","02","02","  ","LTDL1 Quadrupoles ( )                                       "]
["2","02","05","02","03","  ","DL1 QB Quadrupole                                           "]
["2","02","05","02","04","  ","DL1TL Quadrupoles ( )                                       "]
["2","02","05","02","05","  ","SAB Quadrupoles ( )                                         "]
["2","02","05","03","  ","  ","Injector Steering Coils                                     "]
["2","02","05","03","01","  ","GTL Steering Coils ( )X-Y (SC1)                             "]
["2","02","05","03","02","  ","L0-1TL0-2 Linac Steering Coils ( )                          "]
["2","02","05","03","03","  ","LTDL1 Steering Coils ( )X-Y                                 "]
["2","02","05","03","04","  ","DL1TL Steering Coils ( X-Y Assys)                           "]
["2","02","05","03","05","  ","SAB Steering Coils ( )                                      "]
["2","02","05","04","  ","  ","Linac Solenoid & Supports                                   "]
["2","02","05","05","  ","  ","Injector Laser Heater Subsystem                             "]
["2","02","05","05","01","  ","System Design & Optimization                                "]
["2","02","05","05","02","  ","Undulator                                                   "]
["2","02","06","  ","  ","  ","Injector Vacuum & Supports                                  "]
["2","02","06","01","  ","  ","GTL Vacuum Components                                       "]
["2","02","06","02","  ","  ","GTL Supports                                                "]
["2","02","06","03","  ","  ","GTL Pumping & Optic Chamber                                 "]
["2","02","06","04","  ","  ","L0-1TL0-2 Vacuum Components                                 "]
["2","02","06","05","  ","  ","L0-1TL0-2 Major tube support structure                      "]
["2","02","06","06","  ","  ","LTDL1 Minor Tube Supports                                   "]
["2","02","06","07","  ","  ","DL1 Supports                                                "]
["2","02","06","08","  ","  ","DL1 Vacuum Chamber                                          "]
["2","02","06","09","  ","  ","DL1TL Vacuum Components                                     "]
["2","02","06","10","  ","  ","SAB Vacuum Chamber and Components                           "]
["2","02","06","11","  ","  ","SAB Supports                                                "]
["2","02","07","  ","  ","  ","Injector Diagnostics                                        "]
["2","02","07","01","  ","  ","Injector Beam Position Monitors                             "]
["2","02","07","01","01","  ","GTL BPMs ( )                                                "]
["2","02","07","01","02","  ","Gun Spectrometer (GS) Assembly                              "]
["2","02","07","01","03","  ","L0-1TL0-2 BPMs ( )                                          "]
["2","02","07","01","04","  ","LTDL1 BPMs ( )                                              "]
["2","02","07","01","05","  ","DL1TL BPMs ( )                                              "]
["2","02","07","01","06","  ","SAB BPM ( )                                                 "]
["2","02","07","02","  ","  ","Injector Current Monitors                                   "]
["2","02","07","02","01","  ","GTL Current Monitors ( )                                    "]
["2","02","07","02","02","  ","L0-1TL0-2 Current Monitor ( )                               "]
["2","02","07","02","03","  ","LTDL1 Current Monitors ( )                                  "]
["2","02","07","02","04","  ","DL1TL Current Monitor ( )                                   "]
["2","02","07","02","05","  ","SAB Current Monitor ( )                                     "]
["2","02","07","03","  ","  ","Injector Bunch Length Monitors                              "]
["2","02","07","03","01","  ","GTL E/O (EO1)                                               "]
["2","02","07","03","02","  ","LTDL1 E/O EO2                                               "]
["2","02","07","03","03","  ","DL1TL EO3                                                   "]
["2","02","07","04","  ","  ","Injector Profile Monitors                                   "]
["2","02","07","04","01","  ","GTL Faraday Cup/YAG1                                        "]
["2","02","07","04","02","  ","GTL YAG ( )                                                 "]
["2","02","07","04","03","  ","L0-1TL0-2 OTR/YAG ( )                                       "]
["2","02","07","04","04","  ","LTDL1 OTR(5)/YAG ( )                                        "]
["2","02","07","04","05","  ","DL1 OTR                                                     "]
["2","02","07","04","06","  ","DL1TL OTR                                                   "]
["2","02","07","04","07","  ","SAB YAG                                                     "]
["2","02","07","04","08","  ","SAB Beam Dump and Shielding                                 "]
["2","02","07","05","  ","  ","Injector Wire Scanners                                      "]
["2","02","07","05","01","  ","LTDL1 Wire Scanners ( )                                     "]
["2","02","07","05","02","  ","DL1 Wire Scanner                                            "]
["2","02","07","06","  ","  ","LSR HTR - Electron Beam Diagnostics                         "]
["2","02","07","07","  ","  ","PPS Stopper                                                 "]
["2","02","08","  ","  ","  ","Injector System Emittance Enhancement                       ",3480,328168,376796.1943253641,364523.6702497535,741319.8645751176,null,3480,328168,376796.1943253641,364523.6702497535,741319.8645751176,0,null,0,null,0,null,730888.8767895482,null,10430.987785569461,null,null,0]
["2","02","08","01","  ","  ","Heater Integration                                          ",854,0,91966.27813760558,0,91966.27813760558,null,854,0,91966.27813760558,0,91966.27813760558,0,null,0,null,0,null,89881.88259427613,null,2084.3955433294636,null,null,0]
["2","02","08","02","  ","  ","Heater Laser & Optics                                       ",746,86168,89782.34720628663,95714.01117135357,185496.35837764022,null,746,86168,89782.34720628663,95714.01117135357,185496.35837764022,0,null,0,null,0,null,185496.35837764022,null,0,null,null,0]
["2","02","08","03","  ","  ","Heater Magnets                                              ",1012,177000,103473.73353335587,196608.71759039996,300082.4511237557,null,1012,177000,103473.73353335587,196608.71759039996,300082.4511237557,0,null,0,null,0,null,300082.4511237557,null,0,null,null,0]
["2","02","08","03","01","  ","Heater Dipoles                                              ",100,52000,10301.415387279681,57760.75319039999,68062.16857767967,null,100,52000,10301.415387279681,57760.75319039999,68062.16857767967,0,null,0,null,0,null,68062.16857767967,null,0,null,null,0]
["2","02","08","03","02","  ","Heater Undulator                                            ",912,125000,93172.3181460762,138847.96439999997,232020.28254607614,null,912,125000,93172.3181460762,138847.96439999997,232020.28254607614,0,null,0,null,0,null,232020.28254607614,null,0,null,null,0]
["2","02","08","04","  ","  ","Heater Vacuum                                               ",400,45000,43119.40110320419,49985.26718399999,93104.66828720417,null,400,45000,43119.40110320419,49985.26718399999,93104.66828720417,0,null,0,null,0,null,93104.66828720417,null,0,null,null,0]
["2","02","08","05","  ","  ","Heater Diagnostics                                          ",296,20000,31044.66554749759,22215.674303999996,53260.339851497585,null,296,20000,31044.66554749759,22215.674303999996,53260.339851497585,0,null,0,null,0,null,53260.339851497585,null,0,null,null,0]
["2","02","08","06","  ","  ","Heater Install & Align                                      ",172,0,17409.7687974144,0,17409.7687974144,null,172,0,17409.7687974144,0,17409.7687974144,0,null,0,null,0,null,9063.1765551744,null,8346.592242239998,null,null,0]
["2","02","17","  ","  ","  ","Injector System Commissioning                               ",9023,241782,903242.5404158953,263722.6139407776,1166965.154356673,null,7739.4,207358.2,775617.4963720131,226454.1963430176,1002071.6927150309,0,null,0,null,659573.8465665684,null,342497.84614846244,null,0,null,null,0]
["2","02","17","01","  ","  ","Controls Commissioning                                      "]
["2","02","17","02","  ","  ","Drive Laser Commissioning                                   "]
["2","02","17","03","  ","  ","RF Conditioning                                             "]
["2","02","17","04","  ","  ","RF Gun Operation with Beam                                  "]
["2","02","17","05","  ","  ","L0-1&L0-2 Commissioning                                     "]
["2","02","17","06","  ","  ","L0&SAB Commissioning                                        "]
["2","02","17","07","  ","  ","DL1 Commissioning                                           "]
["2","02","17","08","  ","  ","Injector Optimization                                       "]
["2","02","17","10","  ","  ","Injector System Commissioning                               ",9023,241782,903242.5404158953,263722.6139407776,1166965.154356673,null,7739.4,207358.2,775617.4963720131,226454.1963430176,1002071.6927150309,0,null,0,null,659573.8465665684,null,342497.84614846244,null,0,null,null,0]
["2","03","  ","  ","  ","  ","LINAC SYSTEM (OPC)                                          ",29380,298882,2994923.649146789,329367.47325490846,3267888.403660489,null,28832.8,283626.7,2942228.456759934,312851.54848834843,3255080.005248283,0,null,26499.465511199996,null,738849.0960731588,null,1937777.7462583676,null,551953.6974055569,null,null,0]
["2","03","01","  ","  ","  ","Linac System Mgmt & Integration                             ",8244,50000,854088.26828247,56402.71874120929,854088.26828247,null,8244,50000,854088.26828247,56402.71874120929,910490.9870236792,0,null,0,null,0,null,358537.2896181223,null,551953.6974055569,null,null,0]
["2","03","01","01","  ","  ","Linac System Mgmt & Integration                             ",8244,50000,854088.26828247,56402.71874120929,854088.26828247,null,8244,50000,854088.26828247,56402.71874120929,910490.9870236792,0,null,0,null,0,null,358537.2896181223,null,551953.6974055569,null,null,0]
["2","03","01","02","  ","  ","Linac Controls Integration                                  "]
["2","03","01","03","  ","  ","Travel                                                      "]
["2","03","01","04","  ","  ","Linac Management                                            "]
["2","03","02","  ","  ","  ","Linac Controls & Power Conversion Subsystem                 ",14738,73110,1515991.4330412084,79151.45947199999,1595142.8925132076,null,14738,73110,1515991.4330412084,79151.45947199999,1595142.8925132076,0,null,26499.465511199996,null,577356.489381859,null,991286.9376201493,null,0,null,null,0]
["2","03","02","01","  ","  ","Personnel Protection System (PPS)                           ",720,0,72868.14102115847,0,72868.14102115847,null,720,0,72868.14102115847,0,72868.14102115847,0,null,0,null,0,null,72868.14102115847,null,0,null,null,0]
["2","03","02","02","  ","  ","Beam Containment System (BCS)                               ",268,0,32322.97106969059,0,32322.97106969059,null,268,0,32322.97106969059,0,32322.97106969059,0,null,26499.465511199996,null,0,null,5823.5055584905895,null,0,null,null,0]
["2","03","02","03","  ","  ","Machine Protection System (MPS)                             ",1600,0,184482.57824259752,0,184482.57824259752,null,1600,0,184482.57824259752,0,184482.57824259752,0,null,0,null,0,null,184482.57824259752,null,0,null,null,0]
["2","03","02","04","  ","  ","Power Conversion                                            ",174,73110,14515.929425781354,79151.45947199999,93667.38889778135,null,174,73110,14515.929425781354,79151.45947199999,93667.38889778135,0,null,0,null,93667.38889778135,null,0,null,0,null,null,0]
["2","03","02","04","01","  ","Spare Power Supply (Dipole Type)                            ",80,21480,6508.171300090678,23255.004095999997,29763.17539609067,null,80,21480,6508.171300090678,23255.004095999997,29763.17539609067,0,null,0,null,29763.17539609067,null,0,null,0,null,null,0]
["2","03","02","04","02","  ","Spare Power Supply (Quad Type)                              ",82,21480,6682.6643512906785,23255.004095999997,29937.66844729067,null,82,21480,6682.6643512906785,23255.004095999997,29937.66844729067,0,null,0,null,29937.66844729067,null,0,null,0,null,null,0]
["2","03","02","04","03","  ","Spare Power Supply (Trim Type)                              ",12,30150,1325.0937744,32641.451279999997,33966.5450544,null,12,30150,1325.0937744,32641.451279999997,33966.5450544,0,null,0,null,33966.5450544,null,0,null,0,null,null,0]
["2","03","02","04","04","  ","Controls & Power Supply - Spare Misc Hdwr                   "]
["2","03","02","05","  ","  ","Controls - LLRF                                             ",3280,0,329647.26427214843,0,329647.26427214843,null,3280,0,329647.26427214843,0,329647.26427214843,0,null,0,null,174227.16082939197,null,155420.1034427565,null,0,null,null,0]
["2","03","02","06","  ","  ","Controls - E-Beam Diagnostic                                ",4656,0,472205.58924304973,0,472205.58924304973,null,4656,0,472205.58924304973,0,472205.58924304973,0,null,0,null,227438.88303053012,null,244766.7062125196,null,0,null,null,0]
["2","03","02","06","01","  ","Controls - Wire Scanners                                    ",680,0,69646.17804301681,0,69646.17804301681,null,680,0,69646.17804301681,0,69646.17804301681,0,null,0,null,20115.000590057993,null,49531.17745295881,null,0,null,null,0]
["2","03","02","06","02","  ","Controls - BPMs                                             ",2880,0,291540.83838073467,0,291540.83838073467,null,2880,0,291540.83838073467,0,291540.83838073467,0,null,0,null,143899.72279404476,null,147641.11558668994,null,0,null,null,0]
["2","03","02","06","03","  ","Controls - Toroids                                          ",120,0,12278.196360171401,0,12278.196360171401,null,120,0,12278.196360171401,0,12278.196360171401,0,null,0,null,4023.000118011599,null,8255.196242159802,null,0,null,null,0]
["2","03","02","06","04","  ","Controls - Stoppers Commissioning                           ",48,0,4911.27854406856,0,4911.27854406856,null,48,0,4911.27854406856,0,4911.27854406856,0,null,0,null,1609.2000472046398,null,3302.078496863921,null,0,null,null,0]
["2","03","02","06","05","  ","Controls - Profile Monitors                                 ",200,0,20428.7945992629,0,20428.7945992629,null,200,0,20428.7945992629,0,20428.7945992629,0,null,0,null,8046.000236023198,null,12382.794363239704,null,0,null,null,0]
["2","03","02","06","07","  ","Controls - BLM                                              ",80,0,8150.5982390915,0,8150.5982390915,null,80,0,8150.5982390915,0,8150.5982390915,0,null,0,null,4023.000118011599,null,4127.598121079901,null,0,null,null,0]
["2","03","02","06","09","  ","Controls - Single Beam Dump                                 ",48,0,4911.27854406856,0,4911.27854406856,null,48,0,4911.27854406856,0,4911.27854406856,0,null,0,null,1609.2000472046398,null,3302.078496863921,null,0,null,null,0]
["2","03","02","06","10","  ","Controls - E-Beam Dump                                      ",120,0,11853.229110359536,0,11853.229110359536,null,120,0,11853.229110359536,0,11853.229110359536,0,null,0,null,3883.7578998556796,null,7969.471210503854,null,0,null,null,0]
["2","03","02","06","12","  ","Controls - Collimators                                      ",480,0,48485.197422275785,0,48485.197422275785,null,480,0,48485.197422275785,0,48485.197422275785,0,null,0,null,40230.001180115985,null,8255.196242159802,null,0,null,null,0]
["2","03","02","07","  ","  ","Controls - Laser                                            "]
["2","03","02","08","  ","  ","Controls - Timing                                           ",1000,0,107807.29205340725,0,107807.29205340725,null,1000,0,107807.29205340725,0,107807.29205340725,0,null,0,null,3883.7578998556796,null,103923.53415355156,null,0,null,null,0]
["2","03","02","09","  ","  ","Controls - Vacuum                                           ",3040,0,302141.6677133758,0,302141.6677133758,null,3040,0,302141.6677133758,0,302141.6677133758,0,null,0,null,78139.2987243,null,224002.36898907577,null,0,null,null,0]
["2","03","02","10","  ","  ","Software & Controls Infrastructure                          "]
["2","03","03","  ","  ","  ","Linac Magnets & Supports                                    "]
["2","03","03","01","  ","  ","Bend Magnet (BX1_BC1)                                       "]
["2","03","03","02","  ","  ","Bend Magnet (BX3_LTU)                                       "]
["2","03","03","03","  ","  ","Bend Magnet (BX2_BC2)                                       "]
["2","03","03","04","  ","  ","Bend Magnet (BY_LTU)                                        "]
["2","03","03","05","  ","  ","Quad Magnet (Quad_LTU)                                      "]
["2","03","03","07","  ","  ","Quad Magnet (QE)                                            "]
["2","03","03","08","  ","  ","Corrector Magnet (Type 4)                                   "]
["2","03","03","09","  ","  ","Bend Magnet (BYD_LTU)                                       "]
["2","03","03","10","  ","  ","Quad Magnet (QA)                                            "]
["2","03","03","11","  ","  ","Bend Magnet (BYPM_LTU)                                      "]
["2","03","03","12","  ","  ","Bend Magnet (BYKIK_LTU)                                     "]
["2","03","03","13","  ","  ","Bend Magnet (BYW_LTU)                                       "]
["2","03","04","  ","  ","  ","Linac Vacuum Subsystem                                      "]
["2","03","04","01","  ","  ","Linac Vacuum Subsystem Operations Equip                     "]
["2","03","04","02","  ","  ","Linac Beamline Vacuum System                                "]
["2","03","04","03","  ","  ","BC1 Vacuum System                                           "]
["2","03","04","04","  ","  ","BC2 Vacuum System                                           "]
["2","03","04","05","  ","  ","Linac to Undulator (LTU) Vacuum System                      "]
["2","03","04","06","  ","  ","Dumpline Vacuum System                                      "]
["2","03","04","07","  ","  ","Vacuum Undulator Interface                                  "]
["2","03","04","07","01","  ","Entrance Assembly Section                                   "]
["2","03","04","07","02","  ","Exit Assembly Section                                       "]
["2","03","05","  ","  ","  ","Linac Electron Diagnostics                                  "]
["2","03","05","01","  ","  ","Wire Scanners                                               "]
["2","03","05","02","  ","  ","Beam Position Monitors                                      "]
["2","03","05","03","  ","  ","Toroids Beam Charge                                         "]
["2","03","05","04","  ","  ","Stoppers Tune Up Dump                                       "]
["2","03","05","05","  ","  ","Profile Monitors                                            "]
["2","03","05","06","  ","  ","E/O Bunch Length Monitors                                   "]
["2","03","05","07","  ","  ","Bunch Length Monitors                                       "]
["2","03","05","08","  ","  ","Beam Loss Monitors                                          "]
["2","03","05","09","  ","  ","Single Beam Dump                                            "]
["2","03","05","10","  ","  ","Electron Safety Beam Dump                                   "]
["2","03","05","11","  ","  ","Protection Collimators                                      "]
["2","03","05","12","  ","  ","Movable Collimators                                         "]
["2","03","05","13","  ","  ","Safety Dump                                                 "]
["2","03","05","14","  ","  ","Charge Monitor (Entrance/Exit Assebmly)                     "]
["2","03","06","  ","  ","  ","Linac RF Subsystem                                          "]
["2","03","06","02","  ","  ","S-Band High Power System                                    "]
["2","03","06","03","  ","  ","S-Band Structures                                           "]
["2","03","06","04","  ","  ","X-Band Low Level System                                     "]
["2","03","06","05","  ","  ","X-Band High Power System                                    "]
["2","03","06","06","  ","  ","X-Band Structures                                           "]
["2","03","06","07","  ","  ","RF Distribution System                                      "]
["2","03","06","07","01","  ","Modulator                                                   "]
["2","03","06","07","02","  ","Solid State Sub Booster                                     "]
["2","03","06","07","05","  ","Bunch Length Electronics                                    "]
["2","03","06","07","07","  ","RF Distribution L2 & L3                                     "]
["2","03","06","07","08","  ","RF Fiber Optics Electronics                                 "]
["2","03","07","  ","  ","  ","Linac System Commissioning                                  ",6398,175772,624843.9478231107,193813.29504169917,818657.2428648099,null,5850.8,160516.7,572148.7554362564,177297.37027513917,749446.1257113954,0,null,0,null,161492.6066913002,null,587953.5190200954,null,0,null,null,0]
["2","03","07","01","  ","  ","Linac L01 System Commissioning                              "]
["2","03","07","02","  ","  ","Linac BC1 System Commissioning                              "]
["2","03","07","03","  ","  ","Linac L02 System Commissioning                              "]
["2","03","07","04","  ","  ","Linac BC2 System Commissioning                              "]
["2","03","07","05","  ","  ","Linac L03 System Commissioning                              "]
["2","03","07","06","  ","  ","Linac LTU System Commissioning                              "]
["2","03","07","07","  ","  ","Linac E-Dump System Commissioining                          "]
["2","03","07","08","  ","  ","Linac Undulator Interface                                   "]
["2","03","07","10","  ","  ","Linac System Commissioning                                  ",6398,175772,624843.9478231107,193813.29504169917,818657.2428648099,null,5850.8,160516.7,572148.7554362564,177297.37027513917,749446.1257113954,0,null,0,null,161492.6066913002,null,587953.5190200954,null,0,null,null,0]
["2","04","  ","  ","  ","  ","UNDULATOR SYSTEM (OPC)                                      ",28240,2024655,3005017.4577706303,1626440.4673487148,4471813.170837569,null,27038,1922129,2868124.020781027,1517863.824707484,4385987.845488508,0,null,45962.24259013265,null,1475308.179363997,null,1554887.174029773,null,1309830.2495046088,null,null,1230.8116201886025]
["2","04","01","  ","  ","  ","Undulator System Management & Integration                   ",16202,217281,1702350.8785136628,264050.44132797065,1857071.438513663,null,16202,187281,1702350.8785136628,234050.44132797062,1936401.3198416336,0,null,0,null,962159.4144890921,null,791511.4294259271,null,182730.47592661413,null,null,0]
["2","04","01","01","  ","  ","Undulator System Mgmt & Integration                         ",16202,217281,1702350.8785136628,264050.44132797065,1857071.438513663,null,16202,187281,1702350.8785136628,234050.44132797062,1936401.3198416336,0,null,0,null,962159.4144890921,null,791511.4294259271,null,182730.47592661413,null,null,0]
["2","04","02","  ","  ","  ","Controls                                                    ",0,87444,0,94520.51877337143,89246.2919616,null,0,87444,0,94520.51877337143,94520.51877337143,0,null,5749.852190132653,null,88770.66658323877,null,0,null,0,null,null,0]
["2","04","02","01","  ","  ","Controls Management and Integration                         ",0,87444,0,94520.51877337143,89246.2919616,null,0,87444,0,94520.51877337143,94520.51877337143,0,null,5749.852190132653,null,88770.66658323877,null,0,null,0,null,null,0]
["2","04","02","04","  ","  ","Video                                                       "]
["2","04","02","07","  ","  ","Machine Protection                                          "]
["2","04","03","  ","  ","  ","Undulator Magnet & Support                                  ",4927,1396461,528019.1248682716,902789.764759894,1430808.8896281656,null,4895,1363935,524720.5794981226,869253.768260694,1393974.3477588166,0,null,40212.3904,null,186836.30997918287,null,40158.52742319164,null,1126767.119956441,null,null,1230.8116201886025]
["2","04","03","01","  ","  ","Undulator Magnets & Support-Mgmt & Integration              ",810,0,92088.1653250104,0,92088.1653250104,null,810,0,92088.1653250104,0,92088.1653250104,0,null,0,null,92088.1653250104,null,0,null,0,null,null,0]
["2","04","03","02","  ","  ","First Prototype Undulator & Mfg Plan                        "]
["2","04","03","03","  ","  ","1st Article Undulators & Long Lead Procurements             ",191,0,21897.639960244524,0,21897.639960244524,null,191,0,21897.639960244524,0,21897.639960244524,0,null,0,null,14798.954478626794,null,7098.68548161773,null,0,null,null,0]
["2","04","03","04","  ","  ","Production Undulator                                        ",638,1301661,75959.11872375994,797551.316535894,873510.4352596538,null,638,1270535,75959.11872375994,765584.914535894,841544.0332596538,0,null,0,null,0,null,0,null,841544.0332596538,null,null,1230.8116201886025]
["2","04","03","05","  ","  ","Focusing Magnets                                            ",0,58000,0,65026.057824,65026.057824,null,0,56600,0,63456.4633248,63456.4633248,0,null,0,null,63456.4633248,null,0,null,0,null,null,0]
["2","04","03","06","  ","  ","Undulator Magnetic Measurement Facility (SLAC)              ",3288,0,338074.20085925655,0,338074.20085925655,null,3256,0,334775.6554891074,0,334775.6554891074,0,null,0,null,16492.7268507456,null,33059.84194157391,null,285223.08669678785,null,null,0]
["2","04","03","08","  ","  ","Fixed Supports                                              ",0,36800,0,40212.3904,40212.3904,null,0,36800,0,40212.3904,40212.3904,0,null,40212.3904,null,0,null,0,null,0,null,null,0]
["2","04","04","  ","  ","  ","Vacuum System                                               ",37,167001,4324.497080190125,189146.8888759195,193471.38595610965,null,37,167001,4324.497080190125,189146.8888759195,193471.38595610965,0,null,0,null,113555.67746140802,null,79583.05487314856,null,332.65362155308657,null,null,0]
["2","04","04","02","  ","  ","Undulator Vacuum Chamber Assembly                           ",0,145715,0,165282.32565451151,165282.32565451151,null,0,145715,0,165282.32565451151,165282.32565451151,0,null,0,null,89691.11424000001,null,75591.21141451152,null,0,null,null,0]
["2","04","04","02","01","  ","Surface Roughness Minimization                              "]
["2","04","04","02","03","  ","Materials Study for AC Conductivity                         "]
["2","04","04","03","  ","  ","Beam-line Bellows Module Assembly                           ",0,14304,0,16036.771226112001,16036.771226112001,null,0,14304,0,16036.771226112001,16036.771226112001,0,null,0,null,16036.771226112001,null,0,null,0,null,null,0]
["2","04","04","04","  ","  ","Single Undulator Test (SUV) Vacuum                          ",37,0,4324.497080190125,0,4324.497080190125,null,37,0,4324.497080190125,0,4324.497080190125,0,null,0,null,0,null,3991.843458637039,null,332.65362155308657,null,null,0]
["2","04","04","05","  ","  ","Short Diagnostic Break (SDB) Assembly                       ",0,1215,0,1362.1837975200003,1362.1837975200003,null,0,1215,0,1362.1837975200003,1362.1837975200003,0,null,0,null,1362.1837975200003,null,0,null,0,null,null,0]
["2","04","04","06","  ","  ","Long Diagnostic Break (LDB) Assembly                        ",0,5767,0,6465.608197776001,6465.608197776001,null,0,5767,0,6465.608197776001,6465.608197776001,0,null,0,null,6465.608197776001,null,0,null,0,null,null,0]
["2","04","04","07","  ","  ","Entrance Section Assembly                                   "]
["2","04","04","08","  ","  ","Exit Section Assembly                                       "]
["2","04","04","09","  ","  ","Baking System                                               "]
["2","04","05","  ","  ","  ","Undulator System Diagnostics [OPC]                          ",1255,156468,142210.52512611492,175932.8536115596,273102.7325956439,null,85,116468,8615.63350666096,130892.20746952898,139507.84097618994,0,null,0,null,123986.11085107514,null,15521.730125114798,null,0,null,null,0]
["2","04","05","02","  ","  ","Undulator Line Diagnostics                                  "]
["2","04","05","03","  ","  ","High-Power X-Ray and Profile Diagnostics (HPD)              "]
["2","04","05","04","  ","  ","End-of-Undulator(EOU) X-ray and Profile diagnost            ",1170,40000,133594.89161945393,45040.6461420306,133594.89161945393,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["2","04","05","05","  ","  ","RFBPM                                                       ",32,70620,2511.4793288832,79174.83109536002,81686.31042424322,null,32,70620,2511.4793288832,79174.83109536002,81686.31042424322,0,null,0,null,81686.31042424322,null,0,null,0,null,null,0]
["2","04","05","06","  ","  ","Beam Finder Wire                                            ",16,29974,1842.6728192441587,33920.417031096964,35763.08985034112,null,16,29974,1842.6728192441587,33920.417031096964,35763.08985034112,0,null,0,null,22383.80777086272,null,13379.2820794784,null,0,null,null,0]
["2","04","05","07","  ","  ","Charge Monitor (CM)                                         "]
["2","04","05","08","  ","  ","Beam Loss Monitoring                                        ",0,15874,0,17796.959343072,17796.959343072,null,0,15874,0,17796.959343072,17796.959343072,0,null,0,null,17796.959343072,null,0,null,0,null,null,0]
["2","04","05","09","  ","  ","Radiation Detection Monitor (RDM)                           "]
["2","04","05","10","  ","  ","Single Undulator Test (SUT) Diagnostics                     ",37,0,4261.4813585336005,0,4261.4813585336005,null,37,0,4261.4813585336005,0,4261.4813585336005,0,null,0,null,2119.0333128972024,null,2142.448045636398,null,0,null,null,0]
["2","04","06","  ","  ","  ","Undulator System Commissioning                              ",5819,0,628112.4321823912,0,628112.4321823912,null,5819,0,628112.4321823912,0,628112.4321823912,0,null,0,null,0,null,628112.4321823912,null,0,null,null,0]
["2","04","06","01","  ","  ","Undulator System Commissioning                              ",5819,0,628112.4321823912,0,628112.4321823912,null,5819,0,628112.4321823912,0,628112.4321823912,0,null,0,null,0,null,628112.4321823912,null,0,null,null,0]
["2","05","  ","  ","  ","  ","X-RAY TRANSPORT & DIAGNOSTICS SYSTEMS (OPC)                 ",16379,955000,2973636.5440990916,1081482.762111,4055119.3062100913,null,14413.96,955000,2591360.6516272454,1081482.762111,3672843.413738245,0,null,0,null,333763.47385892307,null,2213564.520992443,null,1125515.4188868795,null,null,0]
["2","05","01","  ","  ","  ","System Management & Integration                             ",11290,0,1975026.5664855645,0,1975026.5664855645,null,11290,0,1975026.5664855645,0,1975026.5664855645,0,null,0,null,0,null,1400820.413909685,null,574206.1525758795,null,null,0]
["2","05","01","01","  ","  ","Management                                                  ",11290,0,1975026.5664855645,0,1975026.5664855645,null,11290,0,1975026.5664855645,0,1975026.5664855645,0,null,0,null,0,null,1400820.413909685,null,574206.1525758795,null,null,0]
["2","05","02","  ","  ","  ","Controls                                                    "]
["2","05","02","01","  ","  ","Controls - EPICS                                            "]
["2","05","02","02","  ","  ","Controls - System                                           "]
["2","05","03","  ","  ","  ","Mechanical & Vacuum Subsystem                               "]
["2","05","03","01","  ","  ","Vacuum Systems Engineering                                  "]
["2","05","03","02","  ","  ","Mech/Vac Front End                                          "]
["2","05","03","03","  ","  ","Mech/Vac Near Hall                                          "]
["2","05","03","04","  ","  ","Mech/Vac Tunnel                                             "]
["2","05","03","05","  ","  ","Mech/Vac Far Hall                                           "]
["2","05","04","  ","  ","  ","Optical Subsystem                                           ",0,905000,0,1024539.762111,1024539.762111,null,0,905000,0,1024539.762111,1024539.762111,0,null,0,null,0,null,473230.49580000003,null,551309.266311,null,null,0]
["2","05","04","01","  ","  ","Optical Systems Engineering                                 "]
["2","05","04","02","  ","  ","Facility Optics                                             ",0,905000,0,1024539.762111,1024539.762111,null,0,905000,0,1024539.762111,1024539.762111,0,null,0,null,0,null,473230.49580000003,null,551309.266311,null,null,0]
["2","05","04","03","  ","  ","End Station Optics                                          "]
["2","05","04","04","  ","  ","Crystals & Gratings                                         "]
["2","05","05","  ","  ","  ","Diagnostics Subsystem                                       ",5089,50000,998609.977613527,56943,1055552.9776135269,null,3123.96,50000,616334.0851416808,56943,673277.0851416808,0,null,0,null,333763.47385892307,null,339513.6112827577,null,0,null,null,0]
["2","05","05","01","  ","  ","Diagnostic Systems Engineering                              "]
["2","05","05","02","  ","  ","Modeling & Simulation                                       ",5089,0,998609.977613527,0,998609.977613527,null,3123.96,0,616334.0851416808,0,616334.0851416808,0,null,0,null,276820.47385892307,null,339513.6112827577,null,0,null,null,0]
["2","05","05","03","  ","  ","Facility Diagnostics                                        ",0,50000,0,56943,56943,null,0,50000,0,56943,56943,0,null,0,null,56943,null,0,null,0,null,null,0]
["2","05","05","04","  ","  ","Commissioning Diagnostics                                   "]
["2","05","06","  ","  ","  ","X-Ray Transport & Diag. System Commissioning                "]
["2","05","06","01","  ","  ","X-Ray Transport & Diag. System Commissioning                "]
["2","06","  ","  ","  ","  ","X-RAY END STATION SYSTEMS (OPC)                             ",16440,2945450,1759972.1791825437,3247201.1666230983,4918416.441666902,null,16440,2300000,1759972.1791825437,2551019.249023098,4310991.428205642,0,null,3625.5508751354696,null,748015.9451133058,null,2438940.1493994403,null,1120409.7828177616,null,null,0]
["2","06","01","  ","  ","  ","XE System Mgmt & Integration                                ",8764,20000,959798.4904586291,29809.258007999997,989607.7484666291,null,8764,20000,959798.4904586291,29809.258007999997,989607.7484666291,0,null,0,null,0,null,489610.2670929487,null,499997.4813736804,null,null,0]
["2","06","01","01","  ","  ","Management                                                  "]
["2","06","02","  ","  ","  ","Controls Subsystem                                          ",400,0,38572.635231215085,0,38572.635231215085,null,400,0,38572.635231215085,0,38572.635231215085,0,null,3625.5508751354696,null,7654.22167054636,null,24724.28227504653,null,2568.580410486727,null,null,0]
["2","06","02","01","  ","  ","Cabling                                                     "]
["2","06","02","02","  ","  ","Network                                                     "]
["2","06","02","03","  ","  ","PC Support                                                  "]
["2","06","02","04","  ","  ","Beamline Controls                                           "]
["2","06","02","05","  ","  ","X-Ray PPS                                                   "]
["2","06","02","06","  ","  ","X-Ray MPS                                                   "]
["2","06","02","07","  ","  ","Laser PPS                                                   "]
["2","06","02","08","  ","  ","R&D: 2D X-Ray Detector Controls                             ",400,0,38572.635231215085,0,38572.635231215085,null,400,0,38572.635231215085,0,38572.635231215085,0,null,3625.5508751354696,null,7654.22167054636,null,24724.28227504653,null,2568.580410486727,null,null,0]
["2","06","03","  ","  ","  ","Commissioning                                               ",6636,0,689383.4372917943,0,689383.4372917943,null,6636,0,689383.4372917943,0,689383.4372917943,0,null,0,null,0,null,382098.1824225596,null,307285.25486923504,null,null,0]
["2","06","03","01","  ","  ","Commissioning - Controls                                    ",3940,0,409080.8211521497,0,409080.8211521497,null,3940,0,409080.8211521497,0,409080.8211521497,0,null,0,null,0,null,333919.42267153086,null,75161.39848061916,null,null,0]
["2","06","03","02","  ","  ","Commissioning - XES Laser                                   ",1976,0,208150.27065901208,0,208150.27065901208,null,1976,0,208150.27065901208,0,208150.27065901208,0,null,0,null,0,null,34386.10854213034,null,173764.16211688175,null,null,0]
["2","06","03","03","  ","  ","Commissioning - AMO Experiment                              ",240,0,27943.911401638205,0,27943.911401638205,null,240,0,27943.911401638205,0,27943.911401638205,0,null,0,null,0,null,13792.651208898491,null,14151.260192739715,null,null,0]
["2","06","03","05","  ","  ","Commissioning - 2D X-Ray Detector                           ",480,0,44208.43407899442,0,44208.43407899442,null,480,0,44208.43407899442,0,44208.43407899442,0,null,0,null,0,null,0,null,44208.43407899442,null,null,0]
["2","06","04","  ","  ","  ","Spares                                                      ",640,120000,72217.61620090634,129916.22399999999,202133.84020090633,null,640,120000,72217.61620090634,129916.22399999999,202133.84020090633,0,null,0,null,129916.22399999999,null,72217.61620090634,null,0,null,null,0]
["2","06","04","01","  ","  ","Spares - PPS Stoppers                                       ",640,120000,72217.61620090634,129916.22399999999,202133.84020090633,null,640,120000,72217.61620090634,129916.22399999999,202133.84020090633,0,null,0,null,129916.22399999999,null,72217.61620090634,null,0,null,null,0]
["2","06","04","02","  ","  ","Spares -                                                    "]
["2","06","04","03","  ","  ","Spares -                                                    "]
["2","06","04","04","  ","  ","Spares -                                                    "]
["2","06","04","05","  ","  ","Spares -                                                    "]
["2","06","05","  ","  ","  ","X-Ray Detectors                                             ",0,2805450,0,3087475.6846150984,2998718.78047636,null,0,2160000,0,2391293.7670150977,2391293.7670150977,0,null,0,null,610445.4994427594,null,1470289.8014079782,null,310558.46616435994,null,null,0]
["2","06","05","01","  ","  ","Beam Imaging                                                "]
["2","06","05","02","  ","  ","2-D X-Ray Detector                                          ",0,2805450,0,3087475.6846150984,2998718.78047636,null,0,2160000,0,2391293.7670150977,2391293.7670150977,0,null,0,null,610445.4994427594,null,1470289.8014079782,null,310558.46616435994,null,null,0]
["2","06","05","02","01","  ","Proto 2 ASIC                                                ",0,4950,0,5223.24,5223.24,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["2","06","05","02","02","  ","Proto 3 ASIC                                                ",0,21000,0,22735.3392,22735.3392,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["2","06","05","02","03","  ","Full Lot Prototype                                          ",0,350000,0,378922.32,378922.32,null,0,196400,0,212629.55328,212629.55328,0,null,0,null,212629.55328,null,0,null,0,null,null,0]
["2","06","05","02","04","  ","500px Detector                                              ",0,392000,0,434139.1856427381,345382.28150399996,null,0,392000,0,434139.1856427381,434139.1856427381,0,null,0,null,49640.46584275951,null,384498.71979997866,null,0,null,null,0]
["2","06","05","02","05","  ","2D X-Ray Detector Commissioning                             "]
["2","06","05","03","  ","  ","Beam Intensity                                              "]
["2","06","05","04","  ","  ","Streak Camera                                               "]
["2","06","07","  ","  ","  ","Atomic Physics                                              "]
["2","06","07","01","  ","  ","Atomic Physics Samples                                      "]
["2","06","07","02","  ","  ","Atomic Physics Diagnostics                                  "]
["2","06","07","03","  ","  ","Atomic Physics Data Analysis                                "]
["2","06","07","04","  ","  ","Atomic Physics Detectors                                    "]
["2","08","  ","  ","  ","  ","LCLS SYSTEM COMMISSIONING (OPC)                             "]
["2","09","  ","  ","  ","  ","CONVENTIONAL FACILITIES (OPC)                               ",1785,435000,223645.2126995058,435000,658645.2126995057,null,1785,435000,223645.2126995058,435000,658645.2126995057,0,null,0,null,360000,null,298645.2126995058,null,0,null,null,0]
["2","09","01","  ","  ","  ","MANAGEMENT INTEGRATION                                      "]
["2","09","03","  ","  ","  ","RSY - CLOC Commissioning                                    ",1785,435000,223645.2126995058,435000,658645.2126995057,null,1785,435000,223645.2126995058,435000,658645.2126995057,0,null,0,null,360000,null,298645.2126995058,null,0,null,null,0]
["2","09","03","05","  ","  ","RSY-CLOC Commissioning                                      ",1785,435000,223645.2126995058,435000,658645.2126995057,null,1785,435000,223645.2126995058,435000,658645.2126995057,0,null,0,null,360000,null,298645.2126995058,null,0,null,null,0]

{"sheet":"Detailed Cost Estimate","index":5,"n_rows":7300,"n_cols":48,"rows_kept":2250,"cut":true,"hidden":false,"merged":[[0,37,0,38],[0,29,0,30],[0,31,0,32],[0,33,0,34],[0,35,0,36],[0,22,0,23],[1,0,1,5],[0,0,0,5],[0,16,0,17],[0,18,0,20],[0,27,0,28],[0,24,0,26]],"bounds":{"rows_first":1000,"rows_last":250,"rows_between":1000,"halvings":1},"flags":["formulas_cached_only"]}
["WBS Level",{"$nulls":5},"P3","C/A","W/P","April 2007 CR Rebaseline","Early","Early","OBS","Fund","Res","Units","Budgeted Quantity",null,"Fully Burdened and Escalated Cost",null,null,null,"Work Rem. Bud. Qtty",null,"Work Rem. Full Burd and Escltd Cost",null,null,"FY07",null,"FY08",null,"FY09",null,"FY10",null,"FY11",null,"FY12",null,"Contingency","Contingency","Design","Judgement","Basis","Program",null,"Tech"]
[{"$nulls":6},"ID","Number","Number","Description","Start","Finish",null,"Type","Code",null,"Hours","$$","Labor","M&S","Total (No Conting)",null,"Hours","$$","Labor","M&S","Total","BAC","% of Wrk Rem.","BAC","% of Wrk Rem.","BAC","% of Wrk Rem.","BAC","% of Wrk Rem.","BAC","% of Wrk Rem.","BAC","% of Wrk Rem.","%","$","Maturity","Factor","of Estimate","Phase","CAM","Lead","CAM"]
["1","2","3","4","5","6"]
[{"$nulls":16},660538,130104271,70767566.34099157,135194996.2528595,186596336.28630915,null,660538,130104271,70767566.34099157,135095233.47623512,205862799.81722614,77079314.19476366,null,85839830.5841994,null,34361718.977906734,null,8581936.060356624,null,0,null,0,null,null,32787148.897485387]
["1","  ","  ","  ","  ","  ",null,null,null,"LCLS PROJECT - PED & CONSTRUCTION                           ",{"$nulls":6},401116,114236624,41260864.34880457,117673266.35073483,141523868.16441876,null,401116,114236624,41260864.34880457,117651281.45084788,158912145.79965156,70464221.87911665,null,69072036.11509696,null,17470672.940161653,null,1905214.8652770154,null,0,null,0,null,null,32278257.45171585]
["1","01","  ","  ","  ","  ",null,null,null,"LCLS PROJECT MGMT, PLANNING & ADMN (TEC)                    ",{"$nulls":6},61820,2734894,6586344.892232721,2951207.508458241,8770289.764379598,null,61820,2734894,6586344.892232721,2929222.6085712956,9515567.500804013,2202522.6415978586,null,3666544.862272166,null,2720661.3491259804,null,925838.6478080133,null,0,null,0,null,null,1734430.5349052593]
["1","01","01","  ","  ","  ",null,null,null,"Environment, Safety & Health                                ",{"$nulls":6},14637,214057,1627387.3817838205,224178.60774596618,1751444.3817838205,null,14637,214057,1627387.3817838205,202193.7078590205,1829581.089642841,297441.9264264742,null,661536.9417795799,null,569648.1591376568,null,300954.0622991299,null,0,null,0,null,null,403932.7866650432]
["1","01","01","01","  ","  ",null,null,null,"Radiation Physics                                           ",{"$nulls":6},9261,0,916604.7904475416,0,916604.7904475416,null,9261,0,916604.7904475416,0,916604.7904475416,142284.151845026,null,340366.0102959446,null,311907.2652955359,null,122047.36301103508,null,0,null,0,null,null,229151.1976118854,{"$nulls":6},"Wendy Sisson"]
["1","01","01","01","","","PM110_0015","1.01.01.01","CRB10101","Radiation Physics- FY07-CD4a","2007-05-01","2009-07-31","S","C","SL_PHH2","Hrs",7770,null,764428.580500728,null,764428.580500728,null,7770,null,764428.580500728,null,764428.580500728,142284.151845026,0.19,340366.0102959446,0.45,281778.4183597574,0.37,{"$nulls":6},0.25,191107.145125182,1,1.25,4,1,"1A"]
["1","01","01","01","","","PM110_0020","1.01.01.01","CRB10101","Radiation Physics- CD4a-CD4b","2009-08-03","2010-05-28","S","C","SL_PHH2","Hrs",1491,null,152176.20994681361,null,152176.20994681361,null,1491,null,152176.20994681361,null,152176.20994681361,{"$nulls":4},30128.846935778532,0.2,122047.36301103508,0.8,{"$nulls":4},0.25,38044.052486703404,1,1.25,4,1,"1A"]
["1","01","01","02","  ","  ",null,null,null,"ESH Management & Coordination                               ",{"$nulls":6},5376,124057,710782.5913362787,124057,834839.5913362787,null,5376,124057,710782.5913362787,124057,834839.5913362787,144512.25694793958,null,295705.1834191637,null,232344.72432427361,null,162277.4266449017,null,0,null,0,null,null,166967.9182672557,{"$nulls":6},"Wendy Sisson"]
["1","01","01","02","","","PM120_0027","1.01.01.02","CRB10102","ESH Management & Coordination - FY07","2007-05-01","2007-09-28","S","C","SL_ESH2","Hrs",742,null,94512.25694793958,null,94512.25694793958,null,742,null,94512.25694793958,null,94512.25694793958,94512.25694793958,1,{"$nulls":10},0.2,18902.451389587917,1,1.2,4,1,"1A"]
["1","01","01","02","","","PM120_0028","1.01.01.02","CRB10102","ESH Management & Coordination - FY08","2007-10-01","2008-09-30","S","C","SL_ESH2","Hrs",1701,null,221648.18341916372,null,221648.18341916372,null,1701,null,221648.18341916372,null,221648.18341916372,null,null,221648.18341916372,1,{"$nulls":8},0.2,44329.636683832745,1,1.2,4,1,"1A"]
["1","01","01","02","","","PM120_0029","1.01.01.02","CRB10102","ESH Management & Coordination - FY09","2008-10-01","2009-09-30","S","C","SL_ESH2","Hrs",1743,null,232344.72432427361,null,232344.72432427361,null,1743,null,232344.72432427361,null,232344.72432427361,{"$nulls":4},232344.72432427361,1,{"$nulls":6},0.2,46468.944864854726,1,1.2,4,1,"1A"]
["1","01","01","02","","","PM210_0030","1.01.01.02","CRB10102","ESH Management & Coordination - FY10","2009-10-01","2010-05-28","S","C","SL_ESH2","Hrs",1190,null,162277.4266449017,null,162277.4266449017,null,1190,null,162277.4266449017,null,162277.4266449017,{"$nulls":6},162277.4266449017,1,{"$nulls":4},0.2,32455.48532898034,1,1.2,4,1,"1A"]
["1","01","01","02","","","PM210_0127","1.01.01.02","CRB10102","ESH Management & Coordination - FY07 (Hislop)","2007-05-01","2007-09-28","S","C","SL_MSPY2","$$",null,50000,null,50000,50000,null,null,50000,null,50000,50000,50000,1,{"$nulls":10},0.2,10000,1,1.2,4,1,"1A"]
["1","01","01","02","","","PM210_0129","1.01.01.02","CRB10102","ESH Management & Coord - FY08-CD4a (Hislop)","2007-10-02","2008-05-30","S","C","SL_MSPY2","$$",null,74057,null,74057,74057,null,null,74057,null,74057,74057,null,null,74057,1,{"$nulls":8},0.2,14811.400000000001,1,1.2,4,1,"1A"]
["1","01","01","03","  ","  ",null,null,null,"Seismic & Engineering Support                               ",{"$nulls":6},0,90000,0,100121.60774596618,0,null,0,90000,0,78136.70785902049,78136.70785902049,10645.51763350858,null,25465.748064471503,null,25396.169517847266,null,16629.27264319314,null,0,null,0,null,null,7813.67078590205,{"$nulls":6},"Wendy Sisson"]
["1","01","01","03","","","PM120_0033","1.01.01.03","CRB10103","Professional Services-Project Office Support","2007-05-01","2010-05-28","S","C","SL_MSPS2","$$",null,90000,null,100121.60774596618,null,null,null,90000,null,78136.70785902049,78136.70785902049,10645.51763350858,0.14,25465.748064471503,0.33,25396.169517847266,0.33,16629.27264319314,0.21,{"$nulls":4},0.1,7813.67078590205,1,1.1,4,1,"1A"]
["1","01","02","  ","  ","  ",null,null,null,"Project Management                                          ",{"$nulls":6},30168,2002575,3339110.5358664617,2151239.381571017,4823208.888872087,null,30168,2002575,3339110.5358664617,2151239.381571017,5490349.917437481,1041666.0602869485,null,2299974.244926204,null,1627085.285896616,null,521624.326327712,null,0,null,0,null,null,589787.9028134712,{"$nulls":6},"Wendy Sisson"]
["1","01","02","01","  ","  ",null,null,null,"Project Management Office                                   ",{"$nulls":6},30168,2002575,3339110.5358664617,2151239.381571017,4823208.888872087,null,30168,2002575,3339110.5358664617,2151239.381571017,5490349.917437481,1041666.0602869485,null,2299974.244926204,null,1627085.285896616,null,521624.326327712,null,0,null,0,null,null,589787.9028134712,{"$nulls":6},"Wendy Sisson"]
["1","01","02","01","01","  ",null,null,null,"Project Office - General                                    ",{"$nulls":6},26629,0,2945933.716567701,0,2945933.716567701,null,26629,0,2945933.716567701,0,2945933.716567701,450065.623298637,null,1055721.0178042226,null,1053377.963581033,null,386769.11188380927,null,0,null,0,null,null,294593.3716567701,{"$nulls":6},"Wendy Sisson"]
["1","01","02","01","01","","PM211_0013","1.01.02.01.01","CRB1020101","Project Director  - FY07","2007-05-01","2007-09-28","S","C","SL_PM2","Hrs",371,null,60143.509728779376,null,60143.509728779376,null,371,null,60143.509728779376,null,60143.509728779376,60143.509728779376,1,{"$nulls":10},0.1,6014.350972877938,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0014","1.01.02.01.01","CRB1020101","Project Director  - FY08","2007-10-01","2008-09-30","S","C","SL_PM2","Hrs",851,null,141130.23098413117,null,141130.23098413117,null,851,null,141130.23098413117,null,141130.23098413117,null,null,141130.23098413117,1,{"$nulls":8},0.1,14113.023098413118,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0015","1.01.02.01.01","CRB1020101","Project Director- FY09","2008-10-01","2009-09-30","S","C","SL_PM2","Hrs",872,null,147938.9538103141,null,147938.9538103141,null,872,null,147938.9538103141,null,147938.9538103141,{"$nulls":4},147938.9538103141,1,{"$nulls":6},0.1,14793.89538103141,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0016","1.01.02.01.01","CRB1020101","Project Director- FY10","2009-10-01","2010-05-28","S","C","SL_PM2","Hrs",298,null,51719.943816199164,null,51719.943816199164,null,298,null,51719.943816199164,null,51719.943816199164,{"$nulls":6},51719.943816199164,1,{"$nulls":4},0.1,5171.994381619917,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0023","1.01.02.01.01","CRB1020101","Senior Project Mgrs - FY07","2007-05-01","2007-09-28","S","C","SL_PM2","Hrs",1113,null,180430.52918633813,null,180430.52918633813,null,1113,null,180430.52918633813,null,180430.52918633813,180430.52918633813,1,{"$nulls":10},0.1,18043.052918633814,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0024","1.01.02.01.01","CRB1020101","Senior Project Mgrs - FY08","2007-10-01","2008-09-30","S","C","SL_PM2","Hrs",2552,null,423224.85249295266,null,423224.85249295266,null,2552,null,423224.85249295266,null,423224.85249295266,null,null,423224.85249295266,1,{"$nulls":8},0.1,42322.48524929527,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0025","1.01.02.01.01","CRB1020101","Senior Project Mgrs - FY09","2008-10-01","2009-09-30","S","C","SL_PM2","Hrs",2615,null,443647.20666739834,null,443647.20666739834,null,2615,null,443647.20666739834,null,443647.20666739834,{"$nulls":4},443647.20666739834,1,{"$nulls":6},0.1,44364.720666739835,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0026","1.01.02.01.01","CRB1020101","Senior Project Mgrs - FY10","2009-10-01","2010-05-28","S","C","SL_PM2","Hrs",893,null,154986.2745901539,null,154986.2745901539,null,893,null,154986.2745901539,null,154986.2745901539,{"$nulls":6},154986.2745901539,1,{"$nulls":4},0.1,15498.62745901539,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0033","1.01.02.01.01","CRB1020101","Budget/Finance Officer  - FY07","2007-05-01","2007-09-28","S","C","SL_FA2","Hrs",371,null,33254.04627357119,null,33254.04627357119,null,371,null,33254.04627357119,null,33254.04627357119,33254.04627357119,1,{"$nulls":10},0.1,3325.4046273571194,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0034","1.01.02.01.01","CRB1020101","Budget/Finance Officer  - FY08","2007-10-01","2008-09-30","S","C","SL_FA2","Hrs",851,null,78032.54670221482,null,78032.54670221482,null,851,null,78032.54670221482,null,78032.54670221482,null,null,78032.54670221482,1,{"$nulls":8},0.1,7803.254670221482,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0035","1.01.02.01.01","CRB1020101","Budget/Finance Officer - FY09","2008-10-01","2009-09-30","S","C","SL_FA2","Hrs",872,null,81797.16876944786,null,81797.16876944786,null,872,null,81797.16876944786,null,81797.16876944786,{"$nulls":4},81797.16876944786,1,{"$nulls":6},0.1,8179.716876944786,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0036","1.01.02.01.01","CRB1020101","Budget/Finance Officer - FY10","2009-10-01","2010-05-28","S","C","SL_FA2","Hrs",298,null,28596.558675846583,null,28596.558675846583,null,298,null,28596.558675846583,null,28596.558675846583,{"$nulls":6},28596.558675846583,1,{"$nulls":4},0.1,2859.6558675846586,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0054","1.01.02.01.01","CRB1020101","Administrative Support  - FY07","2007-05-01","2007-09-28","S","C","SL_ADMN2","Hrs",1484,null,86797.37574542311,null,86797.37574542311,null,1484,null,86797.37574542311,null,86797.37574542311,86797.37574542311,1,{"$nulls":10},0.1,8679.73757454231,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0056","1.01.02.01.01","CRB1020101","Administrative Support  - FY08","2007-10-01","2008-09-30","S","C","SL_ADMN2","Hrs",3402,null,203555.40414319796,null,203555.40414319796,null,3402,null,203555.40414319796,null,203555.40414319796,null,null,203555.40414319796,1,{"$nulls":8},0.1,20355.540414319796,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0057","1.01.02.01.01","CRB1020101","Administrative Support  - FY09","2008-10-01","2009-09-30","S","C","SL_ADMN2","Hrs",2615,null,160064.70801741094,null,160064.70801741094,null,2615,null,160064.70801741094,null,160064.70801741094,{"$nulls":4},160064.70801741094,1,{"$nulls":6},0.1,16006.470801741096,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0058","1.01.02.01.01","CRB1020101","Administrative Support  - FY10","2009-10-01","2010-05-28","S","C","SL_ADMN2","Hrs",1190,null,74515.49264798789,null,74515.49264798789,null,1190,null,74515.49264798789,null,74515.49264798789,{"$nulls":6},74515.49264798789,1,{"$nulls":4},0.1,7451.549264798789,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0151","1.01.02.01.01","CRB1020101","E-Beam Systems Manager - FY07","2007-05-01","2007-09-28","S","C","SL_TSM2","Hrs",371,null,39280.622998755585,null,39280.622998755585,null,371,null,39280.622998755585,null,39280.622998755585,39280.622998755585,1,{"$nulls":10},0.1,3928.062299875559,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0152","1.01.02.01.01","CRB1020101","E-Beam Systems Manager - FY08","2007-10-01","2008-09-30","S","C","SL_TSM2","Hrs",851,null,92174.25823691551,null,92174.25823691551,null,851,null,92174.25823691551,null,92174.25823691551,null,null,92174.25823691551,1,{"$nulls":8},0.1,9217.425823691552,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0153","1.01.02.01.01","CRB1020101","E-Beam Systems Manager - FY09","2008-10-01","2009-09-30","S","C","SL_TSM2","Hrs",872,null,96621.13663899743,null,96621.13663899743,null,872,null,96621.13663899743,null,96621.13663899743,{"$nulls":4},96621.13663899743,1,{"$nulls":6},0.1,9662.113663899743,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0154","1.01.02.01.01","CRB1020101","E-Beam Systems Manager - FY10","2009-10-01","2010-05-28","S","C","SL_TSM2","Hrs",298,null,33779.06649815615,null,33779.06649815615,null,298,null,33779.06649815615,null,33779.06649815615,{"$nulls":6},33779.06649815615,1,{"$nulls":4},0.1,3377.9066498156153,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0W54","1.01.02.01.01","CRB1020101","Finance Administrative Support  - FY07","2007-05-01","2007-09-28","S","C","SL_ADMN2","Hrs",186,null,10878.916367013948,null,10878.916367013948,null,186,null,10878.916367013948,null,10878.916367013948,10878.916367013948,1,{"$nulls":10},0.1,1087.8916367013949,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0W55","1.01.02.01.01","CRB1020101","Finance Administrative Support  - FY08","2007-10-01","2008-09-30","S","C","SL_ADMN2","Hrs",425,null,25429.467007895102,null,25429.467007895102,null,425,null,25429.467007895102,null,25429.467007895102,null,null,25429.467007895102,1,{"$nulls":8},0.1,2542.9467007895105,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0W57","1.01.02.01.01","CRB1020101","Finance Administrative Support  - FY09","2008-10-01","2009-09-30","S","C","SL_ADMN2","Hrs",436,null,26687.65303846699,null,26687.65303846699,null,436,null,26687.65303846699,null,26687.65303846699,{"$nulls":4},26687.65303846699,1,{"$nulls":6},0.1,2668.765303846699,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0W58","1.01.02.01.01","CRB1020101","Finance Administrative Support  - FY10","2009-10-01","2010-05-28","S","C","SL_ADMN2","Hrs",150,null,9392.709157309397,null,9392.709157309397,null,150,null,9392.709157309397,null,9392.709157309397,{"$nulls":6},9392.709157309397,1,{"$nulls":4},0.1,939.2709157309397,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_161","1.01.02.01.01","CRB1020101","Photon System Manager - FY07","2007-05-01","2007-09-28","S","C","SL_TSM2","Hrs",371,null,39280.622998755585,null,39280.622998755585,null,371,null,39280.622998755585,null,39280.622998755585,39280.622998755585,1,{"$nulls":10},0.1,3928.062299875559,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_162","1.01.02.01.01","CRB1020101","Photon System Manager - FY08","2007-10-01","2008-09-30","S","C","SL_TSM2","Hrs",851,null,92174.25823691551,null,92174.25823691551,null,851,null,92174.25823691551,null,92174.25823691551,null,null,92174.25823691551,1,{"$nulls":8},0.1,9217.425823691552,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_163","1.01.02.01.01","CRB1020101","Photon System Manager - FY09","2008-10-01","2009-09-30","S","C","SL_TSM2","Hrs",872,null,96621.13663899743,null,96621.13663899743,null,872,null,96621.13663899743,null,96621.13663899743,{"$nulls":4},96621.13663899743,1,{"$nulls":6},0.1,9662.113663899743,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_164","1.01.02.01.01","CRB1020101","Photon System Manager - FY10","2009-10-01","2010-05-28","S","C","SL_TSM2","Hrs",298,null,33779.06649815615,null,33779.06649815615,null,298,null,33779.06649815615,null,33779.06649815615,{"$nulls":6},33779.06649815615,1,{"$nulls":4},0.1,3377.9066498156153,1,1.1,4,1,"1A"]
["1","01","02","01","02","  ",null,null,null,"Project Support                                             ",{"$nulls":6},3539,1645839,393176.8192987608,1743710.2708737839,1494451.0901725446,null,3539,1645839,393176.8192987608,1743710.2708737839,2136887.0901725446,511493.61747150595,null,1048082.6855665129,null,499082.6322112632,null,78228.15492326269,null,0,null,0,null,null,213688.7090172545,{"$nulls":6},"Wendy Sisson"]
["1","01","02","01","02","","PM212_0044","1.01.02.01.02","CRB1020102","Additional Procmnt Consulting Serv thru Dec 07","2007-05-01","2007-12-14","S","C","SL_MSPY2","$$",null,269874,null,269874,null,null,null,269874,null,269874,269874,181897.4537444934,0.67,87976.5462555066,0.33,{"$nulls":8},0.1,26987.4,1,1.1,4,1,"1A"]
["1","01","02","01","02","","PM212_0045","1.01.02.01.02","CRB1020102","Additional Procmnt Consulting Serv thru Sep 09","2008-01-02","2009-09-30","S","C","SL_MSPY2","$$",null,372562,null,372562,null,null,null,372562,null,372562,372562,null,null,159669.42857142855,0.43,212892.57142857142,0.57,{"$nulls":6},0.1,37256.200000000004,1,1.1,4,1,"1A"]
["1","01","02","01","02","","PM212_0053","1.01.02.01.02","CRB1020102","QA/QC Support - FY07","2007-05-01","2007-09-28","S","C","SL_QAO2","Hrs",371,null,42962.73192870119,null,42962.73192870119,null,371,null,42962.73192870119,null,42962.73192870119,42962.73192870119,1,{"$nulls":10},0.1,4296.27319287012,1,1.1,4,1,"1A"]
["1","01","02","01","02","","PM212_0054","1.01.02.01.02","CRB1020102","QA/QC Support - FY08","2007-10-01","2008-09-30","S","C","SL_QAO2","Hrs",851,null,100814.540224704,null,100814.540224704,null,851,null,100814.540224704,null,100814.540224704,null,null,100814.540224704,1,{"$nulls":8},0.1,10081.454022470401,1,1.1,4,1,"1A"]
["1","01","02","01","02","","PM212_0055","1.01.02.01.02","CRB1020102","QA/QC Support - FY09","2008-10-01","2009-09-30","S","C","SL_QAO2","Hrs",436,null,52839.13129635397,null,52839.13129635397,null,436,null,52839.13129635397,null,52839.13129635397,{"$nulls":4},52839.13129635397,1,{"$nulls":6},0.1,5283.913129635397,1,1.1,4,1,"1A"]
["1","01","02","01","02","","PM212_0056","1.01.02.01.02","CRB1020102","QA/QC Support - FY10","2009-10-01","2010-05-28","S","C","SL_QAO2","Hrs",119,null,14753.391367777245,null,14753.391367777245,null,119,null,14753.391367777245,null,14753.391367777245,{"$nulls":6},14753.391367777245,1,{"$nulls":4},0.1,1475.3391367777247,1,1.1,4,1,"1A"]
["1","01","02","01","02","","PM212_0073","1.01.02.01.02","CRB1020102","Computing Mgr Support - FY07","2007-05-01","2007-09-28","S","C","SL_CRM2","Hrs",279,null,32308.900830478793,null,32308.900830478793,null,279,null,32308.900830478793,null,32308.900830478793,32308.900830478793,1,{"$nulls":10},0.1,3230.8900830478797,1,1.1,4,1,"1A"]
["1","01","02","01","02","","PM212_0074","1.01.02.01.02","CRB1020102","Computing Mgr Support - FY08","2007-10-01","2008-09-30","S","C","SL_CRM2","Hrs",639,null,75699.75464581182,null,75699.75464581182,null,639,null,75699.75464581182,null,75699.75464581182,null,null,75699.75464581182,1,{"$nulls":8},0.1,7569.975464581182,1,1.1,4,1,"1A"]
["1","01","02","01","02","","PM212_0075","1.01.02.01.02","CRB1020102","Computing Mgr Support - FY09","2008-10-01","2009-09-30","S","C","SL_CRM2","Hrs",326,null,39508.15780415457,null,39508.15780415457,null,326,null,39508.15780415457,null,39508.15780415457,{"$nulls":4},39508.15780415457,1,{"$nulls":6},0.1,3950.8157804154575,1,1.1,4,1,"1A"]
["1","01","02","01","02","","PM212_0076","1.01.02.01.02","CRB1020102","Computing Mgr Support - FY10","2009-10-01","2010-05-28","S","C","SL_CRM2","Hrs",90,null,11158.027084873547,null,11158.027084873547,null,90,null,11158.027084873547,null,11158.027084873547,{"$nulls":6},11158.027084873547,1,{"$nulls":4},0.1,1115.8027084873547,1,1.1,4,1,"1A"]
["1","01","02","01","02","","PM212_0091","1.01.02.01.02","CRB1020102","Computing Res Support - FY07","2007-05-01","2007-09-28","S","C","SL_CRA2","Hrs",93,null,4901.6795758326,null,4901.6795758326,null,93,null,4901.6795758326,null,4901.6795758326,4901.6795758326,1,{"$nulls":10},0.1,490.16795758326,1,1.1,4,1,"1A"]
["1","01","02","01","02","","PM212_0092","1.01.02.01.02","CRB1020102","Computing Res Support - FY08","2007-10-01","2008-09-30","S","C","SL_CRA2","Hrs",214,null,11538.553721509941,null,11538.553721509941,null,214,null,11538.553721509941,null,11538.553721509941,null,null,11538.553721509941,1,{"$nulls":8},0.1,1153.855372150994,1,1.1,4,1,"1A"]
["1","01","02","01","02","","PM212_0093","1.01.02.01.02","CRB1020102","Computing Res Support - FY09","2008-10-01","2009-09-30","S","C","SL_CRA2","Hrs",107,null,5901.969307919237,null,5901.969307919237,null,107,null,5901.969307919237,null,5901.969307919237,{"$nulls":4},5901.969307919237,1,{"$nulls":6},0.1,590.1969307919237,1,1.1,4,1,"1A"]
["1","01","02","01","02","","PM212_0094","1.01.02.01.02","CRB1020102","Computing Res Support - FY10","2009-10-01","2010-05-28","S","C","SL_CRA2","Hrs",14,null,789.9815106438949,null,789.9815106438949,null,14,null,789.9815106438949,null,789.9815106438949,{"$nulls":6},789.9815106438949,1,{"$nulls":4},0.1,78.9981510643895,1,1.1,4,1,"1A"]
["1","01","02","01","02","","PM212_0700","1.01.02.01.02","CRB1020102","AWARD: PMCS Support - Maintenance - FY07","2007-05-01","2007-05-01","S","C","SL_AWARD","$$",null,244280,null,281027.993092,281027.993092,null,null,244280,null,281027.993092,281027.993092,281027.993092,1,{"$nulls":10},0.1,28102.799309200003,1,1.1,2,1,"1A"]
["1","01","02","01","02","","PM212_0717","1.01.02.01.02","CRB1020102","PMCS Support - Maintenance - FY07","2007-05-01","2007-09-28","S","C","SA_MSPS2","$$",null,232648,null,249422.85139199998,249422.85139199998,null,null,232648,null,249422.85139199998,249422.85139199998,249422.85139199998,1,{"$nulls":10},0.1,24942.2851392,1,1.1,2,1,"1A"]
["1","01","02","01","02","","PM212_0800","1.01.02.01.02","CRB1020102","AWARD: PMCS Support - Maintenance - FY08","2007-10-01","2007-10-01","S","C","SL_AWARD","$$",null,825685,null,974593.1448112999,974593.1448112999,null,null,825685,null,974593.1448112999,974593.1448112999,null,null,974593.1448112999,1,{"$nulls":8},0.1,97459.31448112999,1,1.1,2,1,"1A"]
["1","01","02","01","02","","PM212_0817","1.01.02.01.02","CRB1020102","PMCS Support - Maintenance - FY08","2007-10-01","2008-09-30","S","C","SA_MSPS2","$$",null,558356,null,612383.862147552,612383.862147552,null,null,558356,null,612383.862147552,612383.862147552,null,null,612383.862147552,1,{"$nulls":8},0.1,61238.3862147552,1,1.1,2,1,"1A"]
["1","01","02","01","02","","PM212_0900","1.01.02.01.02","CRB1020102","AWARD: PMCS Support - Maintenance - FY09","2008-10-01","2008-10-01","S","C","SL_AWARD","$$",null,384258,null,465349.5411978,465349.5411978,null,null,384258,null,465349.5411978,465349.5411978,{"$nulls":4},465349.5411978,1,{"$nulls":6},0.1,46534.954119780006,1,1.1,2,1,"1A"]
["1","01","02","01","02","","PM212_0917","1.01.02.01.02","CRB1020102","PMCS Support - Maintenance - FY09","2008-10-01","2009-09-30","S","C","SA_MSPS2","$$",null,167507,null,187940.80237426402,187940.80237426402,null,null,167507,null,187940.80237426402,187940.80237426402,{"$nulls":4},187940.80237426402,1,{"$nulls":6},0.1,18794.080237426402,1,1.1,2,1,"1A"]
["1","01","02","01","02","","PM212_0918","1.01.02.01.02","CRB1020102","PMCS Support - Maintenance - FY10","2009-10-01","2010-05-28","S","C","SA_MSPS2","$$",null,44892,null,51526.754959968006,51526.754959968006,null,null,44892,null,51526.754959968006,51526.754959968006,{"$nulls":6},51526.754959968006,1,{"$nulls":4},0.1,5152.675495996801,1,1.1,2,1,"1A"]
["1","01","02","01","02","","PM212_0950","1.01.02.01.02","CRB1020102","AWARD: PMCS Support - Maintenance - FY10","2009-10-01","2009-10-01","S","C","SL_AWARD","$$",null,50279,{"$nulls":5},50279,{"$nulls":15},0.1,0,1,1.1,2,1,"1A"]
["1","01","02","01","03","  ",null,null,null,"Project Office M&S                                          ",{"$nulls":6},0,356736,0,407529.110697234,382824.08213184,null,0,356736,0,407529.110697234,407529.110697234,80106.81951680555,null,196170.54155546843,null,74624.69010432,null,56627.05952064,null,0,null,0,null,null,81505.8221394468,{"$nulls":6},"Wendy Sisson"]
["1","01","02","01","03","","PM213_0015","1.01.02.01.03","CRB1020103","SLAC Project Office Consumables- FY07","2007-05-01","2007-09-28","S","C","SL_MSCS2","$$",null,53600,null,57464.774399999995,57464.774399999995,null,null,53600,null,57464.774399999995,57464.774399999995,57464.774399999995,1,{"$nulls":10},0.2,11492.95488,1,1.2,4,1,"1A"]
["1","01","02","01","03","","PM213_0016","1.01.02.01.03","CRB1020103","SLAC Project Office Consumables- FY08","2007-10-01","2008-09-30","S","C","SL_MSCS2","$$",null,128640,null,141087.51410688,141087.51410688,null,null,128640,null,141087.51410688,141087.51410688,null,null,141087.51410688,1,{"$nulls":8},0.2,28217.502821376,1,1.2,4,1,"1A"]
["1","01","02","01","03","","PM213_0017","1.01.02.01.03","CRB1020103","SLAC Project Office Consumables- FY09","2008-10-01","2009-09-30","S","C","SL_MSCS2","$$",null,32160,null,36083.12610432001,36083.12610432001,null,null,32160,null,36083.12610432001,36083.12610432001,{"$nulls":4},36083.12610432001,1,{"$nulls":6},0.2,7216.625220864002,1,1.2,4,1,"1A"]
["1","01","02","01","03","","PM213_0018","1.01.02.01.03","CRB1020103","SLAC Project Office Consumables- FY10","2009-10-01","2010-05-28","S","C","SL_MSCS2","$$",null,32160,null,36913.04552064001,36913.04552064001,null,null,32160,null,36913.04552064001,36913.04552064001,{"$nulls":6},36913.04552064001,1,{"$nulls":4},0.2,7382.6091041280015,1,1.2,4,1,"1A"]
["1","01","02","01","03","","PM213_0052","1.01.02.01.03","CRB1020103","Project Related Travel/ Shipping - FY07","2007-05-01","2007-09-28","S","C","SL_MSTR2","$$",null,12500,null,15345,15345,null,null,12500,null,15345,15345,15345,1,{"$nulls":10},0.2,3069,1,1.2,4,1,"1A"]
["1","01","02","01","03","","PM213_0053","1.01.02.01.03","CRB1020103","Project Related Travel/ Shipping - FY08","2007-10-01","2008-09-30","S","C","SL_MSTR2","$$",null,30000,null,37675.043999999994,37675.043999999994,null,null,30000,null,37675.043999999994,37675.043999999994,null,null,37675.043999999994,1,{"$nulls":8},0.2,7535.0088,1,1.2,4,1,"1A"]
["1","01","02","01","03","","PM213_0054","1.01.02.01.03","CRB1020103","Project Related Travel/ Shipping - FY09","2008-10-01","2009-09-30","S","C","SL_MSTR2","$$",null,30000,null,38541.564,38541.564,null,null,30000,null,38541.564,38541.564,{"$nulls":4},38541.564,1,{"$nulls":6},0.2,7708.3128,1,1.2,4,1,"1A"]
["1","01","02","01","03","","PM213_0055","1.01.02.01.03","CRB1020103","Project Related Travel/ Shipping - FY10","2009-10-01","2010-05-28","S","C","SL_MSTR2","$$",null,15000,null,19714.014,19714.014,null,null,15000,null,19714.014,19714.014,{"$nulls":6},19714.014,1,{"$nulls":4},0.2,3942.8028,1,1.2,4,1,"1A"]
["1","01","02","01","03","","PM213_0061","1.01.02.01.03","CRB1020103","Software Licenses","2007-05-01","2008-09-30","S","C","SL_MSEG2","$$",null,22676,null,24705.02856539398,null,null,null,22676,null,24705.02856539398,24705.02856539398,7297.045116805558,0.3,17407.983448588424,0.7,{"$nulls":8},0.2,4941.005713078796,1,1.2,4,1,"1A"]
["1","01","02","01","04","  ",null,null,null,"SSRL Physics Support                                        ",{"$nulls":37},"Wendy Sisson"]
["1","01","03","  ","  ","  ",null,null,null,"Technical Integration                                       ",{"$nulls":6},17015,518262,1619846.9745824414,575789.519141256,2195636.493723698,null,17015,518262,1619846.9745824414,575789.519141256,2195636.493723698,863414.6548844352,null,705033.6755663824,null,523927.90409170726,null,103260.25918117161,null,0,null,0,null,null,740709.8454267458]
["1","01","03","01","  ","  ",null,null,null,"Global Laser Coordination                                   ",{"$nulls":37},"Wendy Sisson"]
["1","01","03","02","  ","  ",null,null,null,"Global Alignment Coordination                               ",{"$nulls":37},"Wendy Sisson"]
["1","01","03","03","  ","  ",null,null,null,"System Integration                                          ",{"$nulls":6},7739,0,745921.3847713624,0,745921.3847713624,null,7739,0,745921.3847713624,0,745921.3847713624,140509.85209624437,null,329520.78889389907,null,248912.83161155053,null,26977.912169668336,null,0,null,0,null,null,381024.5759961408,{"$nulls":6},"Wendy Sisson"]
["1","01","03","03","","","PM300_0065","1.01.03.03","CRB10303","Installation Coordination - FY07","2007-05-01","2007-09-28","S","C","SL_IPM2","Hrs",742,null,78561.24599751117,null,78561.24599751117,null,742,null,78561.24599751117,null,78561.24599751117,78561.24599751117,1,{"$nulls":10},0.8,62848.99679800894,1,1.8,5,1,"1A"]
["1","01","03","03","","","PM300_0066","1.01.03.03","CRB10303","Installation Coordination - FY08","2007-10-01","2008-09-30","S","C","SL_IPM2","Hrs",1701,null,184240.2035969369,null,184240.2035969369,null,1701,null,184240.2035969369,null,184240.2035969369,null,null,184240.2035969369,1,{"$nulls":8},0.8,147392.1628775495,1,1.8,5,1,"1A"]
["1","01","03","03","","","PM300_0067","1.01.03.03","CRB10303","Installation Coordination - FY09","2008-10-01","2009-09-30","S","C","SL_IPM2","Hrs",872,null,96621.13663899743,null,96621.13663899743,null,872,null,96621.13663899743,null,96621.13663899743,{"$nulls":4},96621.13663899743,1,{"$nulls":6},0.8,77296.90931119795,1,1.8,5,1,"1A"]
["1","01","03","03","","","PM300_0068","1.01.03.03","CRB10303","Installation Coordination - FY10","2009-10-01","2010-05-28","S","C","SL_IPM2","Hrs",238,null,26977.912169668336,null,26977.912169668336,null,238,null,26977.912169668336,null,26977.912169668336,{"$nulls":6},26977.912169668336,1,{"$nulls":4},0.8,21582.32973573467,1,1.8,5,1,"1A"]
["1","01","03","03","","","PM300_0075","1.01.03.03","CRB10303","Design Supervisor  - FY07","2007-05-01","2007-09-28","S","C","SL_MDD2","Hrs",742,null,61948.606098733195,null,61948.606098733195,null,742,null,61948.606098733195,null,61948.606098733195,61948.606098733195,1,{"$nulls":10},0.2,12389.72121974664,1,1.2,5,1,"1A"]
["1","01","03","03","","","PM300_0076","1.01.03.03","CRB10303","Design Supervisor  - FY08","2007-10-01","2008-09-30","S","C","SL_MDD2","Hrs",1701,null,145280.58529696215,null,145280.58529696215,null,1701,null,145280.58529696215,null,145280.58529696215,null,null,145280.58529696215,1,{"$nulls":8},0.2,29056.117059392433,1,1.2,5,1,"1A"]
["1","01","03","03","","","PM300_0077","1.01.03.03","CRB10303","Design Supervisor  - FY09","2008-10-01","2009-09-30","S","C","SL_MDD2","Hrs",1743,null,152291.69497255312,null,152291.69497255312,null,1743,null,152291.69497255312,null,152291.69497255312,{"$nulls":4},152291.69497255312,1,{"$nulls":6},0.2,30458.338994510625,1,1.2,5,1,"1A"]
["1","01","03","05","  ","  ",null,null,null,"Global Controls                                             ",{"$nulls":6},9276,518262,873925.5898110782,575789.519141256,1449715.1089523344,null,9276,518262,873925.5898110782,575789.519141256,1449715.1089523344,722904.8027881911,null,375512.88667248323,null,275015.0724801568,null,76282.34701150327,null,0,null,0,null,null,359685.2694306051,{"$nulls":6},"Hamid Shoaee"]
["1","01","03","05","01","  ",null,null,null,"Global Controls Management                                  ",{"$nulls":37},"Hamid Shoaee"]
["1","01","03","05","02","  ",null,null,null,"LLRF Controls                                               ",{"$nulls":37},"Hamid Shoaee"]
["1","01","03","05","03","  ",null,null,null,"E-beam Diagnostics & Controls                               ",{"$nulls":37},"Hamid Shoaee"]
["1","01","03","05","03","01",null,null,null,"Controls - Wire Scanners                                    ",{"$nulls":37},"Hamid Shoaee"]
["1","01","03","05","03","02",null,null,null,"Controls - Toroids                                          ",{"$nulls":37},"Hamid Shoaee"]
["1","01","03","05","03","03",null,null,null,"Controls - Faraday Cups                                     ",{"$nulls":37},"Hamid Shoaee"]
["1","01","03","05","03","04",null,null,null,"Controls - Tune-Up Dump                                     ",{"$nulls":37},"Hamid Shoaee"]
["1","01","03","05","03","05",null,null,null,"Controls - Profile Monitors                                 ",{"$nulls":37},"Hamid Shoaee"]
["1","01","03","05","03","06",null,null,null,"Controls - E/O Diagnostics                                  ",{"$nulls":37},"Hamid Shoaee"]
["1","01","03","05","03","07",null,null,null,"Controls - BPM                                              ",{"$nulls":37},"Hamid Shoaee"]
["1","01","03","05","03","08",null,null,null,"Controls - Stopppers                                        ",{"$nulls":37},"Hamid Shoaee"]
["1","01","03","05","03","09",null,null,null,"Controls - Bunch Length Monitors                            ",{"$nulls":37},"Hamid Shoaee"]
["1","01","03","05","03","10",null,null,null,"Controls - Beam Loss Monitors                               ",{"$nulls":37},"Hamid Shoaee"]
["1","01","03","05","03","11",null,null,null,"Controls - Cherenkov Radiation Detector                     ",{"$nulls":37},"Hamid Shoaee"]
["1","01","03","05","03","12",null,null,null,"Controls - Movable Collimator                               ",{"$nulls":37},"Hamid Shoaee"]
["1","01","03","05","04","  ",null,null,null,"Laser Controls Design                                       ",{"$nulls":37},"Hamid Shoaee"]
["1","01","03","05","05","  ",null,null,null,"Laser Heater Controls                                       ",{"$nulls":6},504,0,50278.8376636128,0,50278.8376636128,null,504,0,50278.8376636128,0,50278.8376636128,50278.8376636128,null,0,null,0,null,0,null,0,null,0,null,null,17597.593182264478,{"$nulls":6},"Hamid Shoaee"]
["1","01","03","05","05","","PM505_0001","1.01.03.05.05","CBG30505","Laser Heater Controls Conceptual Design","2007-05-01","2007-05-25",null,"C","SL_CP2","Hrs",80,null,6573.6437643360005,null,6573.6437643360005,null,80,null,6573.6437643360005,null,6573.6437643360005,6573.6437643360005,1,{"$nulls":10},0.35,2300.7753175176,1.25,1.1,4,2,"2G","S. Peng"]
["1","01","03","05","05","","PM505_0001","1.01.03.05.05","CBG30505","Laser Heater Controls Conceptual Design","2007-05-01","2007-05-25",null,"C","SL_CE2","Hrs",80,null,9016.080407135998,null,9016.080407135998,null,80,null,9016.080407135998,null,9016.080407135998,9016.080407135998,1,{"$nulls":10},0.35,3155.628142497599,1.25,1.1,4,2,"2G","S. Peng"]
["1","01","03","05","05","","PM505_0005","1.01.03.05.05","CBG30505","Conceptual Design Review","2007-05-29","2007-05-29","S","C","SL_CE2","Hrs",8,null,901.6080407135998,null,901.6080407135998,null,8,null,901.6080407135998,null,901.6080407135998,901.6080407135998,1,{"$nulls":10},0.35,315.5628142497599,1.25,1.1,4,2,"2G","S. Peng"]
["1","01","03","05","05","","PM505_0010","1.01.03.05.05","CBG30505","Laser Heater Controls Preliminary Design","2007-05-30","2007-06-26",null,"C","SL_CE2","Hrs",80,null,9016.080407135998,null,9016.080407135998,null,80,null,9016.080407135998,null,9016.080407135998,9016.080407135998,1,{"$nulls":10},0.35,3155.628142497599,1.25,1.1,4,2,"2G","S. Peng"]
["1","01","03","05","05","","PM505_0015","1.01.03.05.05","CBG30505","Preliminary Design Review (PDR)","2007-06-27","2007-06-27",null,"C","SL_CE2","Hrs",8,null,901.6080407135998,null,901.6080407135998,null,8,null,901.6080407135998,null,901.6080407135998,901.6080407135998,1,{"$nulls":10},0.35,315.5628142497599,1.25,1.1,4,2,"2G","S. Peng"]
["1","01","03","05","05","","PM505_0017","1.01.03.05.05","CBG30505","Laser Heater Contrils Final Design","2007-06-28","2007-07-30",null,"C","SL_CE2","Hrs",80,null,9016.080407135998,null,9016.080407135998,null,80,null,9016.080407135998,null,9016.080407135998,9016.080407135998,1,{"$nulls":10},0.35,3155.628142497599,1.25,1.1,4,2,"2G","S. Peng"]
["1","01","03","05","05","","PM505_0020","1.01.03.05.05","CBG30505","Laser Heater Cntrls Final Design Review (FDR)","2007-07-31","2007-07-31",null,"C","SL_CE2","Hrs",8,null,901.6080407135998,null,901.6080407135998,null,8,null,901.6080407135998,null,901.6080407135998,901.6080407135998,1,{"$nulls":10},0.35,315.5628142497599,1.25,1.1,4,2,"2G","S. Peng"]
["1","01","03","05","05","","PM505_0050","1.01.03.05.05","CBG30505","Laser Heater Controls Prototype Hardware","2007-08-01","2007-08-15",null,"C","SL_CT2","Hrs",80,null,4936.048148591999,null,4936.048148591999,null,80,null,4936.048148591999,null,4936.048148591999,4936.048148591999,1,{"$nulls":10},0.35,1727.6168520071997,1.25,1.1,4,2,"2G","S. Peng"]
["1","01","03","05","05","","PM505_0050","1.01.03.05.05","CBG30505","Laser Heater Controls Prototype Hardware","2007-08-01","2007-08-15",null,"C","SL_CE2","Hrs",80,null,9016.080407135998,null,9016.080407135998,null,80,null,9016.080407135998,null,9016.080407135998,9016.080407135998,1,{"$nulls":10},0.35,3155.628142497599,1.25,1.1,4,2,"2G","S. Peng"]
["1","01","03","05","06","  ",null,null,null,"Timing Controls                                             ",{"$nulls":37},"Hamid Shoaee"]
["1","01","03","05","07","  ",null,null,null,"Vacuum Controls                                             ",{"$nulls":37},"Hamid Shoaee"]
["1","01","03","05","09","  ",null,null,null,"Power Supply Controls                                       ",{"$nulls":6},4897,0,411492.9711958158,0,411492.9711958158,null,4897,0,411492.9711958158,0,411492.9711958158,190743.99999263402,null,195982.74326023384,null,24766.22794294788,null,0,null,0,null,0,null,null,102873.24279895394,{"$nulls":6},"Hamid Shoaee"]
["1","01","03","05","09","","PM509_0205","1.01.03.05.09","CACG30509","Controls Power Supplies Management FY07","2007-05-01","2007-09-28",null,"C","SL_CP2","Hrs",742,null,60970.5459142164,null,60970.5459142164,null,742,null,60970.5459142164,null,60970.5459142164,60970.5459142164,1,{"$nulls":10},0.25,15242.6364785541,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0210","1.01.03.05.09","CACG30509","Controls Power Supplies Technical Lead FY07","2007-05-01","2007-09-28",null,"C","SL_CP2","Hrs",148,null,12161.2409640216,null,12161.2409640216,null,148,null,12161.2409640216,null,12161.2409640216,12161.2409640216,1,{"$nulls":10},0.25,3040.3102410054,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0215","1.01.03.05.09","CACG30509","Power Conversion Project Coordinator  (10% time)","2007-05-01","2007-09-28",null,"C","SL_TSM2","Hrs",74,null,7834.949061746398,null,7834.949061746398,null,74,null,7834.949061746398,null,7834.949061746398,7834.949061746398,1,{"$nulls":10},0.25,1958.7372654365995,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0220","1.01.03.05.09","CACG30509","Misc. Power Supplies Support FY07","2007-05-01","2007-09-28",null,"C","SL_TMUE2","Hrs",74,null,7084.798775999999,null,7084.798775999999,null,74,null,7084.798775999999,null,7084.798775999999,7084.798775999999,1,{"$nulls":10},0.25,1771.1996939999997,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0220","1.01.03.05.09","CACG30509","Misc. Power Supplies Support FY07","2007-05-01","2007-09-28",null,"C","SL_PCT2","Hrs",74,null,4565.8445374476,null,4565.8445374476,null,74,null,4565.8445374476,null,4565.8445374476,4565.8445374476,1,{"$nulls":10},0.25,1141.4611343619,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0220","1.01.03.05.09","CACG30509","Misc. Power Supplies Support FY07","2007-05-01","2007-09-28",null,"C","SL_EE2","Hrs",74,null,6878.172967974,null,6878.172967974,null,74,null,6878.172967974,null,6878.172967974,6878.172967974,1,{"$nulls":10},0.25,1719.5432419935,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0220","1.01.03.05.09","CACG30509","Misc. Power Supplies Support FY07","2007-05-01","2007-09-28",null,"C","SL_CT2","Hrs",74,null,4565.8445374476,null,4565.8445374476,null,74,null,4565.8445374476,null,4565.8445374476,4565.8445374476,1,{"$nulls":10},0.25,1141.4611343619,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0220","1.01.03.05.09","CACG30509","Misc. Power Supplies Support FY07","2007-05-01","2007-09-28",null,"C","SL_CP2","Hrs",74,null,6080.6204820108,null,6080.6204820108,null,74,null,6080.6204820108,null,6080.6204820108,6080.6204820108,1,{"$nulls":10},0.25,1520.1551205027,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0305","1.01.03.05.09","CADG30509","Controls Power Supplies Management FY08","2007-10-01","2008-09-30",null,"C","SL_CP2","Hrs",851,null,71535.45966061605,null,71535.45966061605,null,851,null,71535.45966061605,null,71535.45966061605,null,null,71535.45966061605,1,{"$nulls":8},0.25,17883.864915154012,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0315","1.01.03.05.09","CADG30509","Power Conversion Project Coordinator  (10% time)","2007-10-01","2008-09-30",null,"C","SL_TSM2","Hrs",170,null,18413.189072004276,null,18413.189072004276,null,170,null,18413.189072004276,null,18413.189072004276,null,null,18413.189072004276,1,{"$nulls":8},0.25,4603.297268001069,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0320","1.01.03.05.09","CADG30509","Misc. Power Supplies Support FY08","2007-10-01","2008-09-30",null,"C","SL_TMUE2","Hrs",170,null,16650.23452884,null,16650.23452884,null,170,null,16650.23452884,null,16650.23452884,null,null,16650.23452884,1,{"$nulls":8},0.25,4162.55863221,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0320","1.01.03.05.09","CADG30509","Misc. Power Supplies Support FY08","2007-10-01","2008-09-30",null,"C","SL_PCT2","Hrs",170,null,10730.351669020434,null,10730.351669020434,null,170,null,10730.351669020434,null,10730.351669020434,null,null,10730.351669020434,1,{"$nulls":8},0.25,2682.5879172551086,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0320","1.01.03.05.09","CADG30509","Misc. Power Supplies Support FY08","2007-10-01","2008-09-30",null,"C","SL_EE2","Hrs",170,null,16164.635957572411,null,16164.635957572411,null,170,null,16164.635957572411,null,16164.635957572411,null,null,16164.635957572411,1,{"$nulls":8},0.25,4041.1589893931027,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0320","1.01.03.05.09","CADG30509","Misc. Power Supplies Support FY08","2007-10-01","2008-09-30",null,"C","SL_CT2","Hrs",170,null,10730.351669020434,null,10730.351669020434,null,170,null,10730.351669020434,null,10730.351669020434,null,null,10730.351669020434,1,{"$nulls":8},0.25,2682.5879172551086,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0320","1.01.03.05.09","CADG30509","Misc. Power Supplies Support FY08","2007-10-01","2008-09-30",null,"C","SL_CP2","Hrs",170,null,14290.279838195922,null,14290.279838195922,null,170,null,14290.279838195922,null,14290.279838195922,null,null,14290.279838195922,1,{"$nulls":8},0.25,3572.5699595489805,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0405","1.01.03.05.09","CAEG30509","Controls Power Supplies Management FY09","2008-10-01","2009-07-31",null,"C","SL_CP2","Hrs",288,null,24766.22794294788,null,24766.22794294788,null,288,null,24766.22794294788,null,24766.22794294788,{"$nulls":4},24766.22794294788,1,{"$nulls":6},0.25,6191.55698573697,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0510","1.01.03.05.09","CBBG30509","LINAC Drawings","2007-05-01","2007-07-19",null,"C","SL_MDD2","Hrs",504,null,42078.298482158396,null,42078.298482158396,null,504,null,42078.298482158396,null,42078.298482158396,42078.298482158396,1,{"$nulls":10},0.25,10519.574620539599,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0515","1.01.03.05.09","CBBG30509","Undulator Drawings","2007-07-20","2007-12-11",null,"C","SL_MDD2","Hrs",900,null,75991.92513457558,null,75991.92513457558,null,900,null,75991.92513457558,null,75991.92513457558,38523.68426961123,0.51,37468.24086496435,0.49,{"$nulls":8},0.25,18997.981283643894,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","10","  ",null,null,null,"Controls - PPS                                              ",{"$nulls":6},1468,0,166503.09372322212,0,166503.09372322212,null,1468,0,166503.09372322212,0,166503.09372322212,119482.86544057704,null,47020.22828264509,null,0,null,0,null,0,null,0,null,null,74926.39217544996,{"$nulls":6},"Hamid Shoaee"]
["1","01","03","05","10","","PM3510_105","1.01.03.05.10","CBC1030510","LTU PPS Concepual Design","2007-05-01","2007-07-30",null,"C","SL_CE2","Hrs",334,null,37642.135699792794,null,37642.135699792794,null,334,null,37642.135699792794,null,37642.135699792794,37642.135699792794,1,{"$nulls":10},0.45,16938.961064906758,1.35,1.1,5,2,"2G","P. Bong"]
["1","01","03","05","10","","PM3510_115","1.01.03.05.10","CBC1030510","LTU Preliminary Design","2007-07-31","2007-09-25",null,"C","SL_CE2","Hrs",669,null,75396.97240467479,null,75396.97240467479,null,669,null,75396.97240467479,null,75396.97240467479,75396.97240467479,1,{"$nulls":10},0.45,33928.637582103656,1.35,1.1,5,2,"2G","P. Bong"]
["1","01","03","05","10","","PM3510_125","1.01.03.05.10","CBC1030510","Functional Requirements Review","2007-07-31","2007-10-23",null,"C","SL_CE2","Hrs",77,null,8730.25187472894,null,8730.25187472894,null,77,null,8730.25187472894,null,8730.25187472894,6443.7573361094555,0.74,2286.4945386194845,0.26,{"$nulls":8},0.45,3928.613343628023,1.35,1.1,5,2,"2G","P. Bong"]
["1","01","03","05","10","","PM3510_135","1.01.03.05.10","CBC1030510","LTU Final Design","2007-10-24","2008-01-11",null,"C","SL_CE2","Hrs",334,null,38507.90482088803,null,38507.90482088803,null,334,null,38507.90482088803,null,38507.90482088803,null,null,38507.90482088803,1,{"$nulls":8},0.45,17328.557169399613,1.35,1.1,5,2,"2G","P. Bong"]
["1","01","03","05","10","","PM3510_140","1.01.03.05.10","CBC1030510","External Review","2007-10-24","2008-01-11",null,"C","SL_CE2","Hrs",38,null,4381.13887183756,null,4381.13887183756,null,38,null,4381.13887183756,null,4381.13887183756,null,null,4381.13887183756,1,{"$nulls":8},0.45,1971.512492326902,1.35,1.1,5,2,"2G","P. Bong"]
["1","01","03","05","10","","PM3510_145","1.01.03.05.10","CBC1030510","Final Design Review (FDR)","2008-01-14","2008-01-14",null,"C","SL_CE2","Hrs",16,null,1844.6900513000253,null,1844.6900513000253,null,16,null,1844.6900513000253,null,1844.6900513000253,null,null,1844.6900513000253,1,{"$nulls":8},0.45,830.1105230850114,1.35,1.1,5,2,"2G","P. Bong"]
["1","01","03","05","11","  ",null,null,null,"Controls - MPS                                              ",{"$nulls":6},0,22000,0,23586.288,23586.288,null,0,22000,0,23586.288,23586.288,23586.288,null,0,null,0,null,0,null,0,null,0,null,null,4717.2576,{"$nulls":6},"Hamid Shoaee"]
["1","01","03","05","11","","PM511_0163","1.01.03.05.11","CBBG30511","RCV: MPS Prototype Equipment/Hardware","2007-07-27","2007-07-27",null,"C","SL_MSEG2","$$",null,22000,null,23586.288,23586.288,null,null,22000,null,23586.288,23586.288,23586.288,1,{"$nulls":10},0.2,4717.2576,1.1,1.1,2,2,"2G","A. Tilghman"]
["1","01","03","05","12","  ",null,null,null,"Global Controls Management                                  ",{"$nulls":6},2407,496262,245650.68722842756,552203.2311412559,797853.9183696834,null,2407,496262,245650.68722842756,552203.2311412559,797853.9183696834,338812.81169136707,null,132509.91512960428,null,250248.84453720888,null,76282.34701150327,null,0,null,0,null,null,159570.78367393676,{"$nulls":6},"Hamid Shoaee"]
["1","01","03","05","12","01",null,null,null,"Global Controls Management LOE                              ",{"$nulls":6},2407,382262,245650.68722842756,422388.744933256,668039.4321616834,null,2407,382262,245650.68722842756,422388.744933256,668039.4321616834,259878.13169136716,null,92134.82630960428,null,239744.12714920889,null,76282.34701150327,null,0,null,0,null,null,133607.88643233676,{"$nulls":6},"Hamid Shoaee"]
["1","01","03","05","12","01","PM512_0200","1.01.03.05.12","CACG30512","Controls Cost Account Manager - FY07","2007-05-01","2007-09-28",null,"C","SL_TSM2","Hrs",74,null,7834.949061746398,null,7834.949061746398,null,74,null,7834.949061746398,null,7834.949061746398,7834.949061746398,1,{"$nulls":10},0.2,1566.9898123492796,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0205","1.01.03.05.12","CACG30512","Controls Deputy Cost Account Manger - FY07","2007-05-01","2007-09-28",null,"C","SL_TSM2","Hrs",371,null,39280.622998755585,null,39280.622998755585,null,371,null,39280.622998755585,null,39280.622998755585,39280.622998755585,1,{"$nulls":10},0.2,7856.124599751118,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0207","1.01.03.05.12","CACG30512","Controls Physicist - FY07","2007-05-01","2007-09-28",null,"C","SL_PHH2","Hrs",371,null,35526.597878771994,null,35526.597878771994,null,371,null,35526.597878771994,null,35526.597878771994,35526.597878771994,1,{"$nulls":10},0.2,7105.319575754399,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0210","1.01.03.05.12","CACG30512","Controls Technical Coordinator - FY07","2007-05-01","2007-09-28",null,"C","SL_CE2","Hrs",371,null,41812.07288809319,null,41812.07288809319,null,371,null,41812.07288809319,null,41812.07288809319,41812.07288809319,1,{"$nulls":10},0.2,8362.41457761864,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0215","1.01.03.05.12","CACG30512","Controls E-Beam Diagnostics Tech Lead - FY07","2007-05-01","2007-09-28",null,"C","SL_MSPS2","$$",null,48583,null,52086.028631999994,52086.028631999994,null,null,48583,null,52086.028631999994,52086.028631999994,52086.028631999994,1,{"$nulls":10},0.2,10417.2057264,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0220","1.01.03.05.12","CACG30512","Controls - Wire Scanners Tech Lead - FY07","2007-05-01","2007-09-28",null,"C","SL_MSPS2","$$",null,48583,null,52086.028631999994,52086.028631999994,null,null,48583,null,52086.028631999994,52086.028631999994,52086.028631999994,1,{"$nulls":10},0.2,10417.2057264,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0225","1.01.03.05.12","CACG30512","Controls XT/XE Tech Lead - FY07","2007-05-01","2007-09-28",null,"C","SL_MSPS2","$$",null,29150,null,31251.831599999998,31251.831599999998,null,null,29150,null,31251.831599999998,31251.831599999998,31251.831599999998,1,{"$nulls":10},0.2,6250.36632,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0300","1.01.03.05.12","CADG30512","Controls Cost Account Manager - FY08","2007-10-01","2008-09-30",null,"C","SL_TSM2","Hrs",170,null,18413.189072004276,null,18413.189072004276,null,170,null,18413.189072004276,null,18413.189072004276,null,null,18413.189072004276,1,{"$nulls":8},0.2,3682.6378144008554,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0325","1.01.03.05.12","CADG30512","Controls XT/XE Tech Lead - FY08","2007-10-01","2008-09-30",null,"C","SL_MSPS1","$$",null,66825,null,73721.6372376,73721.6372376,null,null,66825,null,73721.6372376,73721.6372376,null,null,73721.6372376,1,{"$nulls":8},0.2,14744.327447520001,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0400","1.01.03.05.12","CAEG30512","Controls Cost Account Manager - FY09","2008-10-01","2009-09-30",null,"C","SL_TSM2","Hrs",42,null,4653.770342704005,null,4653.770342704005,null,42,null,4653.770342704005,null,4653.770342704005,{"$nulls":4},4653.770342704005,1,{"$nulls":6},0.2,930.7540685408011,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0405","1.01.03.05.12","CAEG30512","Controls Deputy Cost Account Manger - FY09","2008-10-01","2009-09-30",null,"C","SL_TSM1","Hrs",208,null,23250.60417904657,null,23250.60417904657,null,208,null,23250.60417904657,null,23250.60417904657,{"$nulls":4},23250.60417904657,1,{"$nulls":6},0.2,4650.1208358093145,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0407","1.01.03.05.12","CAEG30512","Controls Physicist - FY09","2008-10-01","2009-09-30",null,"C","SL_PHH2","Hrs",208,null,20844.632624257727,null,20844.632624257727,null,208,null,20844.632624257727,null,20844.632624257727,{"$nulls":4},20844.632624257727,1,{"$nulls":6},0.2,4168.926524851546,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0410","1.01.03.05.12","CAEG30512","Controls Technical Coordinator - FY09","2008-10-01","2009-09-30",null,"C","SL_CE2","Hrs",208,null,24532.52916547256,null,24532.52916547256,null,208,null,24532.52916547256,null,24532.52916547256,{"$nulls":4},24532.52916547256,1,{"$nulls":6},0.2,4906.505833094512,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0415","1.01.03.05.12","CAEG30512","Controls E-Beam Diagnostics Tech Lead - FY09","2008-10-01","2009-09-30",null,"C","SL_MSPS2","$$",null,57063,null,64023.98709237601,64023.98709237601,null,null,57063,null,64023.98709237601,64023.98709237601,{"$nulls":4},64023.98709237601,1,{"$nulls":6},0.2,12804.797418475202,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0420","1.01.03.05.12","CAEG30512","Controls - Wire Scanners Tech Lead - FY09","2008-10-01","2009-09-30",null,"C","SL_MSPS2","$$",null,57063,null,64023.98709237601,64023.98709237601,null,null,57063,null,64023.98709237601,64023.98709237601,{"$nulls":4},64023.98709237601,1,{"$nulls":6},0.2,12804.797418475202,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0425","1.01.03.05.12","CAEG30512","Controls XT/XE Tech Lead - FY09","2008-10-01","2009-09-30",null,"C","SL_MSPS2","$$",null,34238,null,38414.616652976,38414.616652976,null,null,34238,null,38414.616652976,38414.616652976,{"$nulls":4},38414.616652976,1,{"$nulls":6},0.2,7682.9233305952,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0505","1.01.03.05.12","CAFG30512","Controls Cost Account Manager - FY10","2009-10-01","2010-05-31",null,"C","SL_TSM2","Hrs",24,null,2720.461731395126,null,2720.461731395126,null,24,null,2720.461731395126,null,2720.461731395126,{"$nulls":6},2720.461731395126,1,{"$nulls":4},0.2,544.0923462790253,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0510","1.01.03.05.12","CAFG30512","Controls Deputy Cost Account Manger - FY10","2009-10-01","2010-05-31",null,"C","SL_TSM1","Hrs",120,{"$nulls":5},120,{"$nulls":16},0.2,0,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0515","1.01.03.05.12","CAFG30512","Controls Physicist - FY10","2009-10-01","2010-05-31",null,"C","SL_PHH2","Hrs",120,null,12302.344336407838,null,12302.344336407838,null,120,null,12302.344336407838,null,12302.344336407838,{"$nulls":6},12302.344336407838,1,{"$nulls":4},0.2,2460.468867281568,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0520","1.01.03.05.12","CAFG30512","Controls Technical Coordinator - FY10","2009-10-01","2010-05-31",null,"C","SL_CE2","Hrs",120,null,14478.912949772302,null,14478.912949772302,null,120,null,14478.912949772302,null,14478.912949772302,{"$nulls":6},14478.912949772302,1,{"$nulls":4},0.2,2895.7825899544605,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0525","1.01.03.05.12","CAFG30512","Controls E-Beam Diagnostics Tech Lead - FY10","2009-10-01","2010-05-31",null,"C","SL_MSPS2","$$",null,15676,null,17992.814103904002,17992.814103904002,null,null,15676,null,17992.814103904002,17992.814103904002,{"$nulls":6},17992.814103904002,1,{"$nulls":4},0.2,3598.5628207808004,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0530","1.01.03.05.12","CAFG30512","Controls - Wire Scanners Tech Lead - FY10","2009-10-01","2010-05-31",null,"C","SL_MSPS2","$$",null,15676,null,17992.814103904002,17992.814103904002,null,null,15676,null,17992.814103904002,17992.814103904002,{"$nulls":6},17992.814103904002,1,{"$nulls":4},0.2,3598.5628207808004,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0535","1.01.03.05.12","CAFG30512","Controls XT/XE Tech Lead - FY10","2009-10-01","2010-05-31",null,"C","SL_MSPS2","$$",null,9405,null,10794.99978612,10794.99978612,null,null,9405,null,10794.99978612,10794.99978612,{"$nulls":6},10794.99978612,1,{"$nulls":4},0.2,2158.9999572240004,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","02",null,null,null,"Global Controls Management                                  ",{"$nulls":6},0,114000,0,129814.486208,129814.486208,null,0,114000,0,129814.486208,129814.486208,78934.68,null,40375.08882,null,10504.717388000001,null,0,null,0,null,0,null,null,25962.897241600007,{"$nulls":6},"Hamid Shoaee"]
["1","01","03","05","12","02","PM512_0240","1.01.03.05.12","CBCG30512","Controls - Travel FY07","2007-05-01","2007-09-28",null,"C","SL_MSTR2","$$",null,25000,null,30690,30690,null,null,25000,null,30690,30690,30690,1,{"$nulls":10},0.2,6138,1.1,1.1,4,3,"2G","H. Shoaee"]
["1","01","03","05","12","02","PM512_0245","1.01.03.05.12","CBCG30512","Controls - Materials & Supplies - FY07","2007-05-01","2007-09-28",null,"C","SL_MSCS2","$$",null,10000,null,10721.04,10721.04,null,null,10000,null,10721.04,10721.04,10721.04,1,{"$nulls":10},0.2,2144.208,1.1,1.1,4,3,"2G","H. Shoaee"]
["1","01","03","05","12","02","PM512_0250","1.01.03.05.12","CBCG30512","Controls - Training - FY07","2007-05-01","2007-09-28",null,"C","SL_MSCS2","$$",null,10000,null,10721.04,10721.04,null,null,10000,null,10721.04,10721.04,10721.04,1,{"$nulls":10},0.2,2144.208,1.1,1.1,4,3,"2G","H. Shoaee"]
["1","01","03","05","12","02","PM512_0255","1.01.03.05.12","CBCG30512","Controls - Misc. Hardware - FY07","2007-05-01","2007-09-28",null,"C","SL_MSEG2","$$",null,25000,null,26802.6,26802.6,null,null,25000,null,26802.6,26802.6,26802.6,1,{"$nulls":10},0.2,5360.52,1.1,1.1,4,3,"2G","H. Shoaee"]
["1","01","03","05","12","02","PM512_0340","1.01.03.05.12","CBDG30512","Controls - Travel FY08","2007-10-01","2008-09-30",null,"C","SL_MSTR2","$$",null,12500,null,15697.935,15697.935,null,null,12500,null,15697.935,15697.935,null,null,15697.935,1,{"$nulls":8},0.2,3139.587,1.1,1.1,4,3,"2G","H. Shoaee"]
["1","01","03","05","12","02","PM512_0345","1.01.03.05.12","CBDG30512","Controls - Materials & Supplies - FY08","2007-10-01","2008-09-30",null,"C","SL_MSCS2","$$",null,5000,null,5483.81196,5483.81196,null,null,5000,null,5483.81196,5483.81196,null,null,5483.81196,1,{"$nulls":8},0.2,1096.762392,1.1,1.1,4,3,"2G","H. Shoaee"]
["1","01","03","05","12","02","PM512_0350","1.01.03.05.12","CBDG30512","Controls - Training - FY08","2007-10-01","2008-09-30",null,"C","SL_MSCS2","$$",null,5000,null,5483.81196,5483.81196,null,null,5000,null,5483.81196,5483.81196,null,null,5483.81196,1,{"$nulls":8},0.2,1096.762392,1.1,1.1,4,3,"2G","H. Shoaee"]
["1","01","03","05","12","02","PM512_0355","1.01.03.05.12","CBDG30512","Controls - Misc. Hardware - FY08","2007-10-01","2008-09-30",null,"C","SL_MSEG2","$$",null,12500,null,13709.5299,13709.5299,null,null,12500,null,13709.5299,13709.5299,null,null,13709.5299,1,{"$nulls":8},0.2,2741.90598,1.1,1.1,4,3,"2G","H. Shoaee"]
["1","01","03","05","12","02","PM512_0440","1.01.03.05.12","CBEG30512","Controls - Travel FY09","2008-10-01","2009-03-31",null,"C","SL_MSTR2","$$",null,2500,null,3211.797,3211.797,null,null,2500,null,3211.797,3211.797,{"$nulls":4},3211.797,1,{"$nulls":6},0.2,642.3594,1.1,1.1,4,3,"2G","H. Shoaee"]
["1","01","03","05","12","02","PM512_0445","1.01.03.05.12","CBEG30512","Controls - Materials & Supplies - FY09","2008-10-01","2009-03-31",null,"C","SL_MSCS2","$$",null,2000,null,2243.9755040000005,2243.9755040000005,null,null,2000,null,2243.9755040000005,2243.9755040000005,{"$nulls":4},2243.9755040000005,1,{"$nulls":6},0.2,448.7951008000001,1.1,1.1,4,3,"2G","H. Shoaee"]
["1","01","03","05","12","02","PM512_0450","1.01.03.05.12","CBEG30512","Controls - Training - FY09","2008-10-01","2009-03-31",null,"C","SL_MSCS2","$$",null,2000,null,2243.9755040000005,2243.9755040000005,null,null,2000,null,2243.9755040000005,2243.9755040000005,{"$nulls":4},2243.9755040000005,1,{"$nulls":6},0.2,448.7951008000001,1.1,1.1,4,3,"2G","H. Shoaee"]
["1","01","03","05","12","02","PM512_0455","1.01.03.05.12","CBEG30512","Controls - Misc. Hardware - FY09","2008-10-01","2009-03-31",null,"C","SL_MSEG2","$$",null,2500,null,2804.9693800000005,2804.9693800000005,null,null,2500,null,2804.9693800000005,2804.9693800000005,{"$nulls":4},2804.9693800000005,1,{"$nulls":6},0.2,560.9938760000001,1.1,1.1,4,3,"2G","H. Shoaee"]
["1","01","03","05","13","  ",null,null,null,"SLC Aware IOC                                               ",{"$nulls":37},"Hamid Shoaee"]
["1","01","03","05","14","  ",null,null,null,"Controls - S/W Application                                  ",{"$nulls":37},"Hamid Shoaee"]
["1","01","03","05","15","  ",null,null,null,"Controls - BCS                                              ",{"$nulls":37},"Hamid Shoaee"]
["1","01","03","06","  ","  ",null,null,null,"Technical Requirements/Parameters                           ",{"$nulls":37},"Wendy Sisson"]
["1","01","04","  ","  ","  ",null,null,null,"Education Support                                           ",{"$nulls":37},"Wendy Sisson"]
["1","01","04","01","  ","  ",null,null,null,"Education/Outreach Travel                                   ",{"$nulls":37},"Wendy Sisson"]
["1","01","04","02","  ","  ",null,null,null,"Education/Outreach M&S                                      ",{"$nulls":37},"Wendy Sisson"]
["1","02","  ","  ","  ","  ",null,null,null,"INJECTOR SYSTEM                                             ",{"$nulls":6},301,195400,26251.963359722475,210483.99524823,116415.90975972248,null,301,195400,26251.963359722475,210483.99524823,236735.95860795246,183557.17920584083,null,53178.77940211161,null,0,null,0,null,0,null,0,null,null,53657.293531988114]
["1","02","01","  ","  ","  ",null,null,null,"Injector System Management & Integration                    ",{"$nulls":37},"Jose Chan"]
["1","02","01","01","  ","  ",null,null,null,"Injector System Integration                                 ",{"$nulls":37},"Jose Chan"]
["1","02","01","01","01","  ",null,null,null,"Injector Region Integration                                 ",{"$nulls":37},"Jose Chan"]
["1","02","01","01","02","  ",null,null,null,"Gun Area Integration                                        ",{"$nulls":37},"Jose Chan"]
["1","02","01","01","03","  ",null,null,null,"Accelerator Area Integration                                ",{"$nulls":37},"Jose Chan"]
["1","02","01","01","04","  ",null,null,null,"Heater Area Integration                                     ",{"$nulls":37},"Jose Chan"]
["1","02","01","01","05","  ",null,null,null,"Wall Area Integration                                       ",{"$nulls":37},"Jose Chan"]
["1","02","01","01","06","  ",null,null,null,"Insertion Area Integration                                  ",{"$nulls":37},"Jose Chan"]
["1","02","01","01","07","  ",null,null,null,"Spectrometer Area Integration                               ",{"$nulls":37},"Jose Chan"]
["1","02","01","01","08","  ",null,null,null,"Drive Laser Integration                                     ",{"$nulls":37},"Jose Chan"]
["1","02","01","04","  ","  ",null,null,null,"Injector System Integration Effort / M&S                    ",{"$nulls":37},"Jose Chan"]
["1","02","02","  ","  ","  ",null,null,null,"Injector Controls Subsystem                                 ",{"$nulls":6},60,84100,5293.7595462406425,90163.9464,95457.70594624065,null,60,84100,5293.7595462406425,90163.9464,95457.70594624065,92727.13404102938,null,2730.5719052112636,null,0,null,0,null,0,null,0,null,null,18337.73036656016,{"$nulls":6},"Hamid Shoaee"]
["1","02","02","01","  ","  ",null,null,null,"Personnel Protection Subsystem (PPS)                        ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","02","  ","  ",null,null,null,"Beam Containment Subsystem (BCS)                            ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","03","  ","  ",null,null,null,"Machine Protection Subsystem (MPS)                          ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","04","  ","  ",null,null,null,"Injector Power Conversion                                   ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","04","01","  ",null,null,null,"Beamline Pwr Supplies - (Dipole Type)                       ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","04","01","01",null,null,null,"10kw Power Supply - (Solenoid 1)                            ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","04","01","02",null,null,null,"30kw Power Supply - (Solenoid 2)                            ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","04","01","03",null,null,null,"2kw Power Supply - (B0.5 Spect)                             ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","04","01","04",null,null,null,"15kw Power Supply - (B1-2)                                  ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","04","01","05",null,null,null,"15kw Power Supply - (B3 Spect)                              ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","04","01","06",null,null,null,"10kw Power Supply - (New)                                   ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","04","02","  ",null,null,null,"Power Supply Controls                                       ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","04","03","  ",null,null,null,"Beamline Pwr Supplies - (Trim Type)                         ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","04","03","01",null,null,null,"12Amp Power Supply - (MCOR_1)                               ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","04","03","02",null,null,null,"30Amp Power Supply - (MCOR_2)                               ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","04","03","03",null,null,null,"30Amp Power Supply - (MCOR_3)                               ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","04","03","04",null,null,null,"30Amp Power Supply - (MCOR_4)                               ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","04","04","  ",null,null,null,"Beamline Pwr Supply - Misc Hdwr                             ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","04","05","  ",null,null,null,"Magnet Interlock Protection System                          ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","05","  ","  ",null,null,null,"LLRF Controls                                               ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","05","01","  ",null,null,null,"Readback & Controls - RF Gun LLRF & Temperature             ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","05","02","  ",null,null,null,"Readback & Controls - L0 LLRF                               ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","05","03","  ",null,null,null,"Readback & Controls - Transverse Cavity LLRF                ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","05","04","  ",null,null,null,"S-Band Cavity Controls                                      ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","05","05","  ",null,null,null,"EO Phase Controls                                           ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","06","  ","  ",null,null,null,"E-Beam Diagnostics Controls                                 ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","06","01","  ",null,null,null,"Controls - Wire Scanners                                    ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","06","02","  ",null,null,null,"Controls - BPM                                              ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","06","03","  ",null,null,null,"Controls - Toroids                                          ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","06","05","  ",null,null,null,"Controls - Profile Monitors                                 ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","06","06","  ",null,null,null,"Controls - E/O Diagnostics                                  ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","06","12","  ",null,null,null,"Controls - Movable Collimator                               ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","06","14","  ",null,null,null,"Controls - Faraday Cups                                     ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","06","15","  ",null,null,null,"Controls - Tune-Up Dump                                     ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","06","16","  ",null,null,null,"Controls - Cherenkov Radiation Detector                     ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","08","  ","  ",null,null,null,"Timing Controls                                             ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","09","  ","  ",null,null,null,"Vacuum Controls                                             ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","10","  ","  ",null,null,null,"Software & Controls Infrastructure                          ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","10","01","  ",null,null,null,"Low Level Application Software                              ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","10","02","  ",null,null,null,"High Level Application Software                             ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","10","03","  ",null,null,null,"Data Communications                                         ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","10","04","  ",null,null,null,"Computers & Crates                                          ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","11","  ","  ",null,null,null,"EPICS VXI Control Modules                                   ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","12","  ","  ",null,null,null,"Laser Controls                                              ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","12","01","  ",null,null,null,"Controls - Alignment Laser                                  ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","12","02","  ",null,null,null,"Controls - Gun Laser                                        ",{"$nulls":37},"Hamid Shoaee"]
["1","02","02","13","  ","  ",null,null,null,"Laser Heater Controls                                       ",{"$nulls":6},60,84100,5293.7595462406425,90163.9464,95457.70594624065,null,60,84100,5293.7595462406425,90163.9464,95457.70594624065,92727.13404102938,null,2730.5719052112636,null,0,null,0,null,0,null,0,null,null,18337.73036656016,{"$nulls":6},"Hamid Shoaee"]
["1","02","02","13","","","IJ213_0115","1.02.02.13","CBBIJ20213","RCV: 4 Camera","2007-08-29","2007-08-29",null,"C","SL_MSEG2","$$",null,12000,null,12865.248,12865.248,null,null,12000,null,12865.248,12865.248,12865.248,1,{"$nulls":10},0.1,1286.5248000000001,1,1.1,2,3,"2G","S. Peng"]
["1","02","02","13","","","IJ213_0125","1.02.02.13","CBBIJ20213","RCV: 4 PMC Interface and Cables","2007-08-29","2007-08-29",null,"C","SL_MSEG2","$$",null,10400,null,11149.881599999999,11149.881599999999,null,null,10400,null,11149.881599999999,11149.881599999999,11149.881599999999,1,{"$nulls":10},0.2,2229.9763199999998,1.1,1.1,2,3,"2G","S. Peng"]
["1","02","02","13","","","IJ213_0135","1.02.02.13","CBBIJ20213","RCV: 4 Interrack Cables","2007-08-29","2007-08-29",null,"C","SL_MSEG2","$$",null,500,null,536.052,536.052,null,null,500,null,536.052,536.052,536.052,1,{"$nulls":10},0.25,134.013,1.15,1.1,3,3,"2G","S. Peng"]
["1","02","02","13","","","IJ213_0145","1.02.02.13","CBBIJ20213","RCV: 1 Motor Drivers","2007-08-29","2007-08-29",null,"C","SL_MSEG2","$$",null,6500,null,6968.6759999999995,6968.6759999999995,null,null,6500,null,6968.6759999999995,6968.6759999999995,6968.6759999999995,1,{"$nulls":10},0.2,1393.7352,1.1,1.1,2,3,"2G","S. Peng"]
["1","02","02","13","","","IJ213_0155","1.02.02.13","CBBIJ20213","RCV: 8 Motor Drivers","2007-08-29","2007-08-29",null,"C","SL_MSEG2","$$",null,10400,null,11149.881599999999,11149.881599999999,null,null,10400,null,11149.881599999999,11149.881599999999,11149.881599999999,1,{"$nulls":10},0.2,2229.9763199999998,1.1,1.1,2,3,"2G","S. Peng"]
["1","02","02","13","","","IJ213_0165","1.02.02.13","CBBIJ20213","RCV: 5 IOCs CPU/EVR/Span","2007-08-29","2007-08-29",null,"C","SL_MSEG2","$$",null,28000,null,30018.912,30018.912,null,null,28000,null,30018.912,30018.912,30018.912,1,{"$nulls":10},0.2,6003.7824,1.1,1.1,2,3,"2G","S. Peng"]
["1","02","02","13","","","IJ213_0175","1.02.02.13","CBBIJ20213","RCV: 1 IOC Crate","2007-08-29","2007-08-29",null,"C","SL_MSEG2","$$",null,10000,null,10721.04,10721.04,null,null,10000,null,10721.04,10721.04,10721.04,1,{"$nulls":10},0.2,2144.208,1.1,1.1,2,3,"2G","S. Peng"]
["1","02","02","13","","","IJ213_0177","1.02.02.13","CBBIJ20213","RCV: 1 UPS","2007-08-29","2007-08-29",null,"C","SL_MSEG2","$$",null,1800,null,1929.7872,1929.7872,null,null,1800,null,1929.7872,1929.7872,1929.7872,1,{"$nulls":10},0.2,385.95744,1.1,1.1,2,3,"2G","S. Peng"]
["1","02","02","13","","","IJ213_0179","1.02.02.13","CBBIJ20213","RCV: 1 Function Generator","2007-08-29","2007-08-29",null,"C","SL_MSEG2","$$",null,4500,null,4824.468,4824.468,null,null,4500,null,4824.468,4824.468,4824.468,1,{"$nulls":10},0.25,1206.117,1.15,1.1,2,3,"2G","S. Peng"]
["1","02","02","13","","","IJ213_0180","1.02.02.13","CBBIJ20213","LTU Laser Heater Controls H/W Fab","2007-08-30","2007-09-27",null,"C","SL_CT2","Hrs",10,null,617.0060185739999,null,617.0060185739999,null,10,null,617.0060185739999,null,617.0060185739999,617.0060185739999,1,{"$nulls":10},0.25,154.25150464349997,1.15,1.1,3,3,"2G","S. Peng"]
["1","02","02","13","","","IJ213_0180","1.02.02.13","CBBIJ20213","LTU Laser Heater Controls H/W Fab","2007-08-30","2007-09-27",null,"C","SL_CE2","Hrs",10,null,1127.0100508919998,null,1127.0100508919998,null,10,null,1127.0100508919998,null,1127.0100508919998,1127.0100508919998,1,{"$nulls":10},0.25,281.75251272299994,1.15,1.1,3,3,"2G","S. Peng"]
["1","02","02","13","","","IJ213_0185","1.02.02.13","CBBIJ20213","LTU Laser Heater Contrls Integration and Test","2007-09-28","2007-10-11",null,"C","SL_CT2","Hrs",20,null,1255.8445578052338,null,1255.8445578052338,null,20,null,1255.8445578052338,null,1255.8445578052338,289.8102825704386,0.23,966.0342752347952,0.77,{"$nulls":8},0.25,313.96113945130844,1.15,1.1,3,3,"2G","S. Peng"]
["1","02","02","13","","","IJ213_0185","1.02.02.13","CBBIJ20213","LTU Laser Heater Contrls Integration and Test","2007-09-28","2007-10-11",null,"C","SL_CE2","Hrs",20,null,2293.898918969409,null,2293.898918969409,null,20,null,2293.898918969409,null,2293.898918969409,529.3612889929406,0.23,1764.5376299764685,0.77,{"$nulls":8},0.25,573.4747297423522,1.15,1.1,3,3,"2G","S. Peng"]
["1","02","03","  ","  ","  ",null,null,null,"Injector Lasers                                             ",{"$nulls":6},241,111300,20958.20381348183,120320.04884822998,20958.20381348183,null,241,111300,20958.20381348183,120320.04884822998,141278.25266171183,90830.04516481145,null,50448.20749690035,null,0,null,0,null,0,null,0,null,null,35319.56316542796,{"$nulls":6},"Bill White"]
["1","02","03","01","  ","  ",null,null,null,"Drive Laser Support                                         ",{"$nulls":37},"Bill White"]
["1","02","03","01","01","  ",null,null,null,"Drive Laser Support (ANL)                                   ",{"$nulls":37},"Bill White"]
["1","02","03","01","02","  ",null,null,null,"Drive Laser Support (LLNL)                                  ",{"$nulls":37},"Bill White"]
["1","02","03","02","  ","  ",null,null,null,"Drive Laser System                                          ",{"$nulls":37},"Bill White"]
["1","02","03","03","  ","  ",null,null,null,"Drive Laser Diagnostics                                     ",{"$nulls":6},241,111300,20958.20381348183,120320.04884822998,20958.20381348183,null,241,111300,20958.20381348183,120320.04884822998,141278.25266171183,90830.04516481145,null,50448.20749690035,null,0,null,0,null,0,null,0,null,null,35319.56316542796,{"$nulls":6},"Bill White"]
["1","02","03","03","","","IJ03030060","1.02.03.03","CBE20303","Assemble & Checkout: Drive Laser Diagnostics","2007-05-01","2007-12-14","SG","C","SL_PHSS2","Hrs",12,null,1122.1017892389004,null,1122.1017892389004,null,12,null,1122.1017892389004,null,1122.1017892389004,756.3064923063955,0.67,365.795296932505,0.33,{"$nulls":8},0.25,280.5254473097251,1.15,1.1,3,4,"2L"]
["1","02","03","03","","","IJ03030060","1.02.03.03","CBE20303","Assemble & Checkout: Drive Laser Diagnostics","2007-05-01","2007-12-14","SG","C","SL_OT2","Hrs",120,null,7459.5864560305345,null,7459.5864560305345,null,120,null,7459.5864560305345,null,7459.5864560305345,5027.826994593268,0.67,2431.7594614372665,0.33,{"$nulls":8},0.25,1864.8966140076336,1.15,1.1,3,4,"2L"]
["1","02","03","03","","","IJ03030060","1.02.03.03","CBE20303","Assemble & Checkout: Drive Laser Diagnostics","2007-05-01","2007-12-14","SG","C","SL_OE2","Hrs",60,null,6812.760863236181,null,6812.760863236181,null,60,null,6812.760863236181,null,6812.760863236181,4591.860846145973,0.67,2220.9000170902086,0.33,{"$nulls":8},0.25,1703.1902158090452,1.15,1.1,3,4,"2L"]
["1","02","03","03","","","IJ03030925","1.02.03.03","CBE20303","Procure Drive Laser Diagnostics","2007-05-01","2007-12-14","SG","C","SL_OE2","Hrs",49,null,5563.754704976213,null,5563.754704976213,null,49,null,5563.754704976213,null,5563.754704976213,3750.01969101921,0.67,1813.7350139570033,0.33,{"$nulls":8},0.25,1390.9386762440533,1.15,1.1,3,3,"2L"]
["1","02","03","03","","","IJ03030930","1.02.03.03","CBE20303","RCV: Drive Laser Diagnostics","2007-05-01","2007-12-27","SG","C","SL_MSEG2","$$",null,111300,null,120320.04884822998,null,null,null,111300,null,120320.04884822998,120320.04884822998,76704.0311407466,0.64,43616.01770748337,0.36,{"$nulls":8},0.25,30080.012212057496,1.15,1.1,3,3,"2L"]
["1","02","03","04","  ","  ",null,null,null,"Timing Stability Monitoring                                 ",{"$nulls":37},"Bill White"]
["1","02","03","05","  ","  ",null,null,null,"Steering Stability Feedback & Msmts                         ",{"$nulls":37},"Bill White"]
["1","02","03","06","  ","  ",null,null,null,"Pre Amp Low Power Comp                                      ",{"$nulls":37},"Bill White"]
["1","02","03","07","  ","  ",null,null,null,"Transport to Tunnel & Relay Optics                          ",{"$nulls":37},"Bill White"]
["1","02","03","08","  ","  ",null,null,null,"UV Launch, Conditioning & Diagnostics                       ",{"$nulls":37},"Bill White"]
["1","02","03","09","  ","  ",null,null,null,"Load Lock Transport System                                  ",{"$nulls":37},"Bill White"]
["1","02","03","10","  ","  ",null,null,null,"Visible Optical Transport & Optics                          ",{"$nulls":37},"Bill White"]
["1","02","03","11","  ","  ",null,null,null,"LB Infrastructure & LB System Wide Items                    ",{"$nulls":37},"Bill White"]
["1","02","03","12","  ","  ",null,null,null,"Alignment Laser                                             ",{"$nulls":37},"Bill White"]
["1","02","03","13","  ","  ",null,null,null,"Light path to Streak Camera                                 ",{"$nulls":37},"Bill White"]
["1","02","03","14","  ","  ",null,null,null,"LSR HTR - Beam Conditioning Optics (Laser Bay)              ",{"$nulls":37},"Jose Chan"]
["1","02","03","15","  ","  ",null,null,null,"LSR HTR - Transport Optics (Bay to Tunnel)                  ",{"$nulls":37},"Bill White"]
["1","02","03","16","  ","  ",null,null,null,"LSR HTR - Photon Beam Diagnostics                           ",{"$nulls":37},"Bill White"]
["1","02","03","21","  ","  ",null,null,null,"UV Conv Harmonic Generation Unit (Closed Account)           ",{"$nulls":37},"Bill White"]
["1","02","04","  ","  ","  ",null,null,null,"Injector RF Subsystem                                       ",{"$nulls":37},"Jose Chan"]
["1","02","04","01","  ","  ",null,null,null,"RF Gun & Load Lock                                          ",{"$nulls":37},"Jose Chan"]
["1","02","04","01","01","  ",null,null,null,"RF Gun                                                      ",{"$nulls":37},"Jose Chan"]
["1","02","04","01","02","  ",null,null,null,"RF Gun Supports                                             ",{"$nulls":37},"Jose Chan"]
["1","02","04","01","03","  ",null,null,null,"Gun Load Lock                                               ",{"$nulls":37},"Jose Chan"]
["1","02","04","01","04","  ",null,null,null,"Gun Load Lock Supports                                      ",{"$nulls":37},"Jose Chan"]
["1","02","04","01","05","  ",null,null,null,"Gun Solenoid                                                ",{"$nulls":37},"Jose Chan"]
["1","02","04","01","06","  ",null,null,null,"Gun Solenoid Supports                                       ",{"$nulls":37},"Jose Chan"]
["1","02","04","01","07","  ",null,null,null,"Gun RF Feed                                                 ",{"$nulls":37},"Jose Chan"]
["1","02","04","01","08","  ",null,null,null,"Gun RF Feed Supports                                        ",{"$nulls":37},"Jose Chan"]
["1","02","04","02","  ","  ",null,null,null,"Cathode Processing (CP) Station                             ",{"$nulls":37},"Jose Chan"]
["1","02","04","02","01","  ",null,null,null,"CP Cathode Assembly & Supports                              ",{"$nulls":37},"Jose Chan"]
["1","02","04","02","02","  ",null,null,null,"CP Load Lock                                                ",{"$nulls":37},"Jose Chan"]
["1","02","04","02","03","  ",null,null,null,"CP Load Lock Supports                                       ",{"$nulls":37},"Jose Chan"]
["1","02","04","02","04","  ",null,null,null,"CP Station                                                  ",{"$nulls":37},"Jose Chan"]
["1","02","04","02","05","  ",null,null,null,"Cathode Lab Infrastructure                                  ",{"$nulls":37},"Jose Chan"]
["1","02","04","03","  ","  ",null,null,null,"S-Band Low Level Timing                                     ",{"$nulls":37},"Jose Chan"]
["1","02","04","03","01","  ",null,null,null,"Controls Interface & Timing                                 ",{"$nulls":37},"Jose Chan"]
["1","02","04","03","02","  ",null,null,null,"LLRF Phase Reference System                                 ",{"$nulls":37},"Jose Chan"]
["1","02","04","03","03","  ",null,null,null,"LLRF Monitor & Control System                               ",{"$nulls":37},"Jose Chan"]
["1","02","04","03","04","  ",null,null,null,"Beam Phase Monitor Cavity                                   ",{"$nulls":37},"Jose Chan"]
["1","02","04","03","05","  ",null,null,null,"RF System S/W Development / Docs                            ",{"$nulls":37},"Jose Chan"]
["1","02","04","04","  ","  ",null,null,null,"S-Band High Power System                                    ",{"$nulls":37},"Jose Chan"]
["1","02","04","04","01","  ",null,null,null,"RF Gun High Power                                           ",{"$nulls":37},"Jose Chan"]
["1","02","04","04","02","  ",null,null,null,"L0 High Power                                               ",{"$nulls":37},"Jose Chan"]
["1","02","04","04","03","  ",null,null,null,"Transverse Cavity High Power                                ",{"$nulls":37},"Jose Chan"]
["1","02","04","05","  ","  ",null,null,null,"Injector RF Waveguide Subsystem                             ",{"$nulls":37},"Jose Chan"]
["1","02","04","05","01","  ",null,null,null,"RF Waveguides                                               ",{"$nulls":37},"Jose Chan"]
["1","02","04","05","02","  ",null,null,null,"RF Waveguide Supports                                       ",{"$nulls":37},"Jose Chan"]
["1","02","04","06","  ","  ",null,null,null,"Injector Linac Structures                                   ",{"$nulls":37},"Jose Chan"]
["1","02","04","06","01","  ",null,null,null,"L0A-0B Structure Assembly                                   ",{"$nulls":37},"Jose Chan"]
["1","02","04","06","03","  ",null,null,null,"Major Linac Support                                         ",{"$nulls":37},"Jose Chan"]
["1","02","04","06","04","  ",null,null,null,"GTL RF Phase Cavity                                         ",{"$nulls":37},"Jose Chan"]
["1","02","04","06","05","  ",null,null,null,"LTDL1 RF Kicker                                             ",{"$nulls":37},"Jose Chan"]
["1","02","05","  ","  ","  ",null,null,null,"Injector Magnets & Supports                                 ",{"$nulls":37},"Jose Chan"]
["1","02","05","01","  ","  ",null,null,null,"Injector Dipoles                                            ",{"$nulls":37},"Jose Chan"]
["1","02","05","01","01","  ",null,null,null,"Gun Spectrometer Dipole                                     ",{"$nulls":37},"Jose Chan"]
["1","02","05","01","02","  ",null,null,null,"DL1 B01 & B02 Dipoles                                       ",{"$nulls":37},"Jose Chan"]
["1","02","05","01","03","  ",null,null,null,"SAB Spectrometer Dipole                                     ",{"$nulls":37},"Jose Chan"]
["1","02","05","01","04","  ",null,null,null,"Chicane DIPOLES (4)                                         ",{"$nulls":37},"Jose Chan"]
["1","02","05","02","  ","  ",null,null,null,"Injector Quads                                              ",{"$nulls":37},"Jose Chan"]
["1","02","05","02","01","  ",null,null,null,"Gun Spectrometer Quadrupoles                                ",{"$nulls":37},"Jose Chan"]
["1","02","05","02","02","  ",null,null,null,"Injector Quadrupoles                                        ",{"$nulls":37},"Jose Chan"]
["1","02","05","02","03","  ",null,null,null,"                                                            ",{"$nulls":37},"Jose Chan"]
["1","02","05","03","  ","  ",null,null,null,"Injector Steering Coils                                     ",{"$nulls":37},"Jose Chan"]
["1","02","05","03","01","  ",null,null,null,"Gun Solenoid Correctors                                     ",{"$nulls":37},"Jose Chan"]
["1","02","05","03","02","  ",null,null,null,"Gun Spectrometer Correctors                                 ",{"$nulls":37},"Jose Chan"]
["1","02","05","03","03","  ",null,null,null,"Injector Correctors - A                                     ",{"$nulls":37},"Jose Chan"]
["1","02","05","03","04","  ",null,null,null,"Injector Correctors - D (Gun)                               ",{"$nulls":37},"Jose Chan"]
["1","02","05","03","05","  ",null,null,null,"Gun Solenoid Quadrupole Correctors                          ",{"$nulls":37},"Jose Chan"]
["1","02","05","04","  ","  ",null,null,null,"Linac Solenoid                                              ",{"$nulls":37},"Jose Chan"]
["1","02","05","05","  ","  ",null,null,null,"Injector Laser Heater Subsystem                             ",{"$nulls":37},"Jose Chan"]
["1","02","05","05","01","  ",null,null,null,"System Design & Optimization (LSR HTR)                      ",{"$nulls":37},"Jose Chan"]
["1","02","05","05","02","  ",null,null,null,"Injector Undulator                                          ",{"$nulls":37},"Jose Chan"]
["1","02","06","  ","  ","  ",null,null,null,"Injector Vacuum & Supports                                  ",{"$nulls":37},"Jose Chan"]
["1","02","06","01","  ","  ",null,null,null,"Injector Vacuum Engineering                                 ",{"$nulls":37},"Jose Chan"]
["1","02","06","02","  ","  ",null,null,null,"Injector Vacuum Components                                  ",{"$nulls":37},"Jose Chan"]
["1","02","06","03","  ","  ",null,null,null,"Injector Vacuum Special Chambers                            ",{"$nulls":37},"Jose Chan"]
["1","02","06","04","  ","  ",null,null,null,"Injector Vacuum Supports Engineering                        ",{"$nulls":37},"Jose Chan"]
["1","02","06","05","  ","  ",null,null,null,"Injector Vacuum Support Components                          ",{"$nulls":37},"Jose Chan"]
["1","02","06","08","  ","  ",null,null,null,"DL1 Vacuum Chamber                                          ",{"$nulls":37},"Jose Chan"]
["1","02","06","10","  ","  ",null,null,null,"DL1TL Vacuum Components                                     ",{"$nulls":37},"Jose Chan"]
["1","02","07","  ","  ","  ",null,null,null,"Injector Diagnostics                                        ",{"$nulls":37},"Jose Chan"]
["1","02","07","01","  ","  ",null,null,null,"Beam Position Monitors                                      ",{"$nulls":37},"Jose Chan"]
["1","02","07","01","01","  ",null,null,null,"Large Aperture BPM                                          ",{"$nulls":37},"Jose Chan"]
["1","02","07","01","02","  ",null,null,null,"Small Aperture BPM                                          ",{"$nulls":37},"Jose Chan"]
["1","02","07","01","06","  ",null,null,null,"                                                            ",{"$nulls":37},"Jose Chan"]
["1","02","07","02","  ","  ",null,null,null,"Current Monitors                                            ",{"$nulls":37},"Jose Chan"]
["1","02","07","02","01","  ",null,null,null,"Current Monitors                                            ",{"$nulls":37},"Jose Chan"]
["1","02","07","03","  ","  ",null,null,null,"Bunch Length Monitors                                       ",{"$nulls":37},"Jose Chan"]
["1","02","07","03","01","  ",null,null,null,"Bunch Length Monitors                                       ",{"$nulls":37},"Jose Chan"]
["1","02","07","04","  ","  ",null,null,null,"Profile Monitors                                            ",{"$nulls":37},"Jose Chan"]
["1","02","07","04","01","  ",null,null,null,"Profile Monitors                                            ",{"$nulls":37},"Jose Chan"]
["1","02","07","04","03","  ",null,null,null,"GS Faraday Cup/YAG2                                         ",{"$nulls":37},"Jose Chan"]
["1","02","07","04","06","  ",null,null,null,"DL1 OTR/YAG                                                 ",{"$nulls":37},"Jose Chan"]
["1","02","07","04","07","  ",null,null,null,"DL1TL OTR/YAG                                               ",{"$nulls":37},"Jose Chan"]
["1","02","07","04","08","  ",null,null,null,"LTDL1 OTR/YAG (6)                                           ",{"$nulls":37},"Jose Chan"]
["1","02","07","05","  ","  ",null,null,null," Injector Wire Scanners                                     ",{"$nulls":37},"Jose Chan"]
["1","02","07","06","  ","  ",null,null,null,"LSR HTR - Electron Beam Diagnostics                         ",{"$nulls":37},"Jose Chan"]
["1","02","07","07","  ","  ",null,null,null,"PPS Stopper                                                 ",{"$nulls":37},"Jose Chan"]
["1","02","17","  ","  ","  ",null,null,null,"Injector Installation & Alignment                           ",{"$nulls":37},"Jose Chan"]
["1","02","17","01","  ","  ",null,null,null,"Injector Infrastructure Installation                        ",{"$nulls":37},"Jose Chan"]
["1","02","17","02","  ","  ",null,null,null,"Injector Controls Subsystem Install & Align                 ",{"$nulls":37},"Jose Chan"]
["1","02","17","03","  ","  ",null,null,null,"Injector Lasers Install & Align                             ",{"$nulls":37},"Jose Chan"]
["1","02","17","04","  ","  ",null,null,null,"Gun Area Integration                                        ",{"$nulls":37},"Jose Chan"]
["1","02","17","06","  ","  ",null,null,null,"Accelerator Area Integration                                ",{"$nulls":37},"Jose Chan"]
["1","02","17","07","  ","  ",null,null,null,"Heater Area Integration                                     ",{"$nulls":37},"Jose Chan"]
["1","02","17","08","  ","  ",null,null,null,"Wall Area Integration                                       ",{"$nulls":37},"Jose Chan"]
["1","02","17","09","  ","  ",null,null,null,"Insertion Area Integration                                  ",{"$nulls":37},"Jose Chan"]
["1","02","17","11","  ","  ",null,null,null,"Spectrometer Area Integration                               ",{"$nulls":37},"Jose Chan"]
["1","02","17","12","  ","  ",null,null,null,"Injector RF High Power System Install & Align               ",{"$nulls":37},"Jose Chan"]
["1","02","17","13","  ","  ",null,null,null,"Injector RF Low Level Install & Align                       ",{"$nulls":37},"Jose Chan"]
["1","02","17","14","  ","  ",null,null,null,"Cathode and Load Lock Install & Align                       ",{"$nulls":37},"Jose Chan"]
["1","02","17","15","  ","  ",null,null,null,"Injector Laser Heater Subsystem Install & Align             ",{"$nulls":37},"Jose Chan"]
["1","02","17","17","  ","  ",null,null,null,"Power  Conversion Subsystem Installation                    ",{"$nulls":37},"Jose Chan"]
["1","02","17","18","  ","  ",null,null,null,"Cathode Processing Center Installation                      ",{"$nulls":37},"Jose Chan"]
["1","03","  ","  ","  ","  ",null,null,null,"LINAC SYSTEM                                                ",{"$nulls":6},100164,9312100,9065254.736751823,9911739.36339631,17781211.65937575,null,100164,9312100,9065254.736751823,9911739.36339631,18976994.10014814,11959543.087161792,null,6549435.769961357,null,364489.7926051428,null,103525.45041983701,null,0,null,0,null,null,6099199.734433253]
["1","03","01","  ","  ","  ",null,null,null,"System Management & Integration                             ",{"$nulls":6},18147,510716,1796728.2905697643,567370.8410626348,2119750.8027121644,null,18147,510716,1796728.2905697643,567370.8410626348,2364099.1316323997,897386.6182179411,null,998697.270389479,null,364489.7926051428,null,103525.45041983701,null,0,null,0,null,null,430241.5489289551,{"$nulls":6},"Jose Chan"]
["1","03","01","01","  ","  ",null,null,null,"Linac Mechanical Integration                                ",{"$nulls":6},8042,371400,774926.3133805814,403153.73392023495,933731.7183805814,null,8042,371400,774926.3133805814,403153.73392023495,1178080.0473008163,607965.3026809809,null,570114.7446198355,null,0,null,0,null,0,null,0,null,null,303428.78513867676,{"$nulls":6},"Jose Chan"]
["1","03","01","01","01","  ",null,null,null,"L01 System Integration                                      ",{"$nulls":37},"Jose Chan"]
["1","03","01","01","02","  ",null,null,null,"BC1 System Integration                                      ",{"$nulls":37},"Jose Chan"]
["1","03","01","01","03","  ",null,null,null,"L02 System Integration                                      ",{"$nulls":6},1019,69000,102337.99828880308,73975.176,176313.17428880307,null,1019,69000,102337.99828880308,73975.176,176313.17428880307,101090.27251046392,null,75222.90177833918,null,0,null,0,null,0,null,0,null,null,26446.976143320462,{"$nulls":6},"Jose Chan"]
["1","03","01","01","03","","LN101-0308","1.03.01.01.03","CBX3010103","Misc. Materials and Supplies","2007-05-30","2007-05-30",null,"C","SL_MSPS2","$$",null,24000,null,25730.496,25730.496,null,null,24000,null,25730.496,25730.496,25730.496,1,{"$nulls":10},0.15,3859.5743999999995,1.1,1.05,null,null,"2A"]
["1","03","01","01","03","","LN101-0308","1.03.01.01.03","CBX3010103","Misc. Materials and Supplies","2007-05-30","2007-05-30",null,"C","SL_MSCS2","$$",null,10000,null,10721.04,10721.04,null,null,10000,null,10721.04,10721.04,10721.04,1,{"$nulls":10},0.15,1608.1560000000002,1.1,1.05,null,null,"2A"]
["1","03","01","01","03","","LN101-3010","1.03.01.01.03","CBX3010103","L2 Procurement Support","2007-05-01","2007-07-31","JC","C","SL_ME2","Hrs",56,null,5576.354237361599,null,5576.354237361599,null,56,null,5576.354237361599,null,5576.354237361599,5576.354237361599,1,{"$nulls":10},0.15,836.4531356042398,1.1,1.05,5,1,"2A"]
["1","03","01","01","03","","LN101-3020","1.03.01.01.03","CBX3010103","L2 Fabrication Oversight","2007-05-01","2007-07-31","JC","C","SL_ME2","Hrs",56,null,5576.354237361599,null,5576.354237361599,null,56,null,5576.354237361599,null,5576.354237361599,5576.354237361599,1,{"$nulls":10},0.15,836.4531356042398,1.1,1.05,5,1,"2A"]
["1","03","01","01","03","","LN101-3030","1.03.01.01.03","CBX3010103","L2 Installation Coordination Planning","2007-05-01","2007-07-02","JC","C","SL_ME2","Hrs",96,null,9559.464406905598,null,9559.464406905598,null,96,null,9559.464406905598,null,9559.464406905598,9559.464406905598,1,{"$nulls":10},0.15,1433.9196610358397,1.1,1.05,5,1,"2A"]
["1","03","01","01","03","","LN101-3040","1.03.01.01.03","CBX3010103","L2 Installation Oversight","2007-09-04","2007-10-31","JC","C","SL_ME2","Hrs",80,null,8062.6535326664325,null,8062.6535326664325,null,80,null,8062.6535326664325,null,8062.6535326664325,3819.1516733683097,0.47,4243.501859298122,0.53,{"$nulls":8},0.15,1209.3980298999647,1.1,1.05,5,1,"2A"]
["1","03","01","01","03","","LN101-3040","1.03.01.01.03","CBX3010103","L2 Installation Oversight","2007-09-04","2007-10-31","JC","C","SL_MDD2","Hrs",40,null,3379.973599882648,null,3379.973599882648,null,40,null,3379.973599882648,null,3379.973599882648,1601.0401262602018,0.47,1778.9334736224464,0.53,{"$nulls":8},0.15,506.9960399823972,1.1,1.05,5,1,"2A"]
["1","03","01","01","03","","LN101-3050","1.03.01.01.03","CBX3010103","L2 Documentation","2007-12-04","2008-07-14","JC","C","SL_ME2","Hrs",120,null,12224.165110330536,null,12224.165110330536,null,120,null,12224.165110330536,null,12224.165110330536,null,null,12224.165110330536,1,{"$nulls":8},0.15,1833.6247665495803,1.1,1.05,5,2,"2A"]
["1","03","01","01","03","","LN101-3050","1.03.01.01.03","CBX3010103","L2 Documentation","2007-12-04","2008-07-14","JC","C","SL_MDD2","Hrs",200,null,17081.78545525716,null,17081.78545525716,null,200,null,17081.78545525716,null,17081.78545525716,null,null,17081.78545525716,1,{"$nulls":8},0.15,2562.267818288574,1.1,1.05,5,2,"2A"]
["1","03","01","01","03","","LN101-3060","1.03.01.01.03","CBX3010103","L2 System Construction Support to Components","2007-11-01","2008-07-11","JC","C","SL_ME2","Hrs",120,null,12224.165110330536,null,12224.165110330536,null,120,null,12224.165110330536,null,12224.165110330536,null,null,12224.165110330536,1,{"$nulls":8},0.15,1833.6247665495803,1.1,1.05,5,1,"2A"]
["1","03","01","01","03","","LN101-3060","1.03.01.01.03","CBX3010103","L2 System Construction Support to Components","2007-11-01","2008-07-11","JC","C","SL_KE2","Hrs",120,null,13835.17538475019,null,13835.17538475019,null,120,null,13835.17538475019,null,13835.17538475019,null,null,13835.17538475019,1,{"$nulls":8},0.15,2075.2763077125283,1.1,1.05,5,1,"2A"]
["1","03","01","01","03","","LN101-3060","1.03.01.01.03","CBX3010103","L2 System Construction Support to Components","2007-11-01","2008-07-11","JC","C","SL_CE2","Hrs",120,null,13835.17538475019,null,13835.17538475019,null,120,null,13835.17538475019,null,13835.17538475019,null,null,13835.17538475019,1,{"$nulls":8},0.15,2075.2763077125283,1.1,1.05,5,1,"2A"]
["1","03","01","01","03","","LN101-3070","1.03.01.01.03","CBX3010103","L2 Top Assembly","2007-05-01","2007-05-15","JC","C","SL_ME2","Hrs",4,null,398.3110169543999,null,398.3110169543999,null,4,null,398.3110169543999,null,398.3110169543999,398.3110169543999,1,{"$nulls":10},0.15,59.74665254315998,1.1,1.05,4,2,"2A"]
["1","03","01","01","03","","LN101-3070","1.03.01.01.03","CBX3010103","L2 Top Assembly","2007-05-01","2007-05-15","JC","C","SL_MDD2","Hrs",7,null,584.4208122522,null,584.4208122522,null,7,null,584.4208122522,null,584.4208122522,584.4208122522,1,{"$nulls":10},0.15,87.66312183782999,1.1,1.05,4,2,"2A"]
["1","03","01","01","03","","LN101-3080","1.03.01.01.03","CBX3010103","RCV: Misc. Parts","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,35000,null,37523.64,37523.64,null,null,35000,null,37523.64,37523.64,37523.64,1,{"$nulls":10},0.15,5628.545999999999,1.1,1.05,null,null,"2A"]
["1","03","01","01","04","  ",null,null,null,"BC2 System Integration                                      ",{"$nulls":6},2163,0,214494.31217471565,0,214494.31217471565,null,2163,0,214494.31217471565,0,214494.31217471565,100624.93866633067,null,113869.37350838498,null,0,null,0,null,0,null,0,null,null,53623.578043678914,{"$nulls":6},"Jose Chan"]
["1","03","01","01","04","","LN101-4010","1.03.01.01.04","CBX3010104","BC2 Bunch Length Monitor Integration","2007-05-01","2007-08-30","JC","C","SL_ME2","Hrs",120,null,11949.330508631998,null,11949.330508631998,null,120,null,11949.330508631998,null,11949.330508631998,11949.330508631998,1,{"$nulls":10},0.25,2987.3326271579995,1.15,1.1,5,1,"2A"]
["1","03","01","01","04","","LN101-4030","1.03.01.01.04","CBX3010104","BC2 Emittance Section Design","2007-05-01","2007-06-29","JC","C","SL_ME2","Hrs",96,null,9559.464406905598,null,9559.464406905598,null,96,null,9559.464406905598,null,9559.464406905598,9559.464406905598,1,{"$nulls":10},0.25,2389.8661017263994,1.15,1.1,5,2,"2A"]
["1","03","01","01","04","","LN101-4030","1.03.01.01.04","CBX3010104","BC2 Emittance Section Design","2007-05-01","2007-06-29","JC","C","SL_MDD2","Hrs",96,null,8014.913996601599,null,8014.913996601599,null,96,null,8014.913996601599,null,8014.913996601599,8014.913996601599,1,{"$nulls":10},0.25,2003.7284991503998,1.15,1.1,5,2,"2A"]
["1","03","01","01","04","","LN101-4040","1.03.01.01.04","CBX3010104","BC2 Procurement Support","2007-05-01","2007-08-16","JC","C","SL_ME2","Hrs",144,null,14339.196610358396,null,14339.196610358396,null,144,null,14339.196610358396,null,14339.196610358396,14339.196610358396,1,{"$nulls":10},0.25,3584.799152589599,1.15,1.1,5,1,"2A"]
["1","03","01","01","04","","LN101-4050","1.03.01.01.04","CBX3010104","BC2 Fabrication Oversight","2007-05-01","2007-08-16","JC","C","SL_ME2","Hrs",60,null,5974.665254315999,null,5974.665254315999,null,60,null,5974.665254315999,null,5974.665254315999,5974.665254315999,1,{"$nulls":10},0.25,1493.6663135789997,1.15,1.1,5,1,"2A"]
["1","03","01","01","04","","LN101-4060","1.03.01.01.04","CBX3010104","BC2 Installation Coordination Planning","2007-05-01","2007-08-13","JC","C","SL_ME2","Hrs",200,null,19915.550847719995,null,19915.550847719995,null,200,null,19915.550847719995,null,19915.550847719995,19915.550847719995,1,{"$nulls":10},0.25,4978.887711929999,1.15,1.1,5,1,"2A"]
["1","03","01","01","04","","LN101-4070","1.03.01.01.04","CBX3010104","BC2 Installation Oversight","2007-09-04","2007-10-31","JC","C","SL_ME2","Hrs",120,null,12093.98029899965,null,12093.98029899965,null,120,null,12093.98029899965,null,12093.98029899965,5728.727510052466,0.47,6365.252788947184,0.53,{"$nulls":8},0.25,3023.4950747499124,1.15,1.1,5,1,"2A"]
["1","03","01","01","04","","LN101-4070","1.03.01.01.04","CBX3010104","BC2 Installation Oversight","2007-09-04","2007-10-31","JC","C","SL_MDD2","Hrs",80,null,6759.947199765296,null,6759.947199765296,null,80,null,6759.947199765296,null,6759.947199765296,3202.0802525204035,0.47,3557.866947244893,0.53,{"$nulls":8},0.25,1689.986799941324,1.15,1.1,5,1,"2A"]
["1","03","01","01","04","","LN101-4080","1.03.01.01.04","CBX3010104","BC2 Documentation","2007-12-04","2008-04-11","JC","C","SL_ME2","Hrs",200,null,20373.60851721756,null,20373.60851721756,null,200,null,20373.60851721756,null,20373.60851721756,null,null,20373.60851721756,1,{"$nulls":8},0.25,5093.40212930439,1.15,1.1,5,2,"2A"]
["1","03","01","01","04","","LN101-4080","1.03.01.01.04","CBX3010104","BC2 Documentation","2007-12-04","2008-04-11","JC","C","SL_MDD2","Hrs",200,null,17081.78545525716,null,17081.78545525716,null,200,null,17081.78545525716,null,17081.78545525716,null,null,17081.78545525716,1,{"$nulls":8},0.25,4270.44636381429,1.15,1.1,5,2,"2A"]
["1","03","01","01","04","","LN101-4090","1.03.01.01.04","CBX3010104","BC2 System Construction Support to Component","2007-12-04","2008-04-11","JC","C","SL_ME2","Hrs",200,null,20373.60851721756,null,20373.60851721756,null,200,null,20373.60851721756,null,20373.60851721756,null,null,20373.60851721756,1,{"$nulls":8},0.25,5093.40212930439,1.15,1.1,5,1,"2A"]
["1","03","01","01","04","","LN101-4090","1.03.01.01.04","CBX3010104","BC2 System Construction Support to Component","2007-12-04","2008-04-11","JC","C","SL_KE2","Hrs",200,null,23058.625641250317,null,23058.625641250317,null,200,null,23058.625641250317,null,23058.625641250317,null,null,23058.625641250317,1,{"$nulls":8},0.25,5764.656410312579,1.15,1.1,5,1,"2A"]
["1","03","01","01","04","","LN101-4090","1.03.01.01.04","CBX3010104","BC2 System Construction Support to Component","2007-12-04","2008-04-11","JC","C","SL_CE2","Hrs",200,null,23058.625641250317,null,23058.625641250317,null,200,null,23058.625641250317,null,23058.625641250317,null,null,23058.625641250317,1,{"$nulls":8},0.25,5764.656410312579,1.15,1.1,5,1,"2A"]
["1","03","01","01","04","","LN101-4100","1.03.01.01.04","CBX3010104","BC2 Top Assembly Drawing","2007-05-01","2007-06-01","JC","C","SL_ME2","Hrs",82,null,8165.3758475651985,null,8165.3758475651985,null,82,null,8165.3758475651985,null,8165.3758475651985,8165.3758475651985,1,{"$nulls":10},0.25,2041.3439618912996,1.15,1.1,5,2,"2A"]
["1","03","01","01","04","","LN101-4100","1.03.01.01.04","CBX3010104","BC2 Top Assembly Drawing","2007-05-01","2007-06-01","JC","C","SL_MDD2","Hrs",165,null,13775.633431658998,null,13775.633431658998,null,165,null,13775.633431658998,null,13775.633431658998,13775.633431658998,1,{"$nulls":10},0.25,3443.9083579147496,1.15,1.1,5,2,"2A"]
["1","03","01","01","05","  ",null,null,null,"L03 System Integration                                      ",{"$nulls":6},864,0,85490.24866341245,0,85490.24866341245,null,864,0,85490.24866341245,0,85490.24866341245,23565.518845016908,null,61924.729818395535,null,0,null,0,null,0,null,0,null,null,12823.537299511867,{"$nulls":6},"Jose Chan"]
["1","03","01","01","05","","LN101-5010","1.03.01.01.05","CBX3010105","L3 Procurement Support","2007-05-01","2007-08-31","JC","C","SL_ME2","Hrs",48,null,4779.732203452799,null,4779.732203452799,null,48,null,4779.732203452799,null,4779.732203452799,4779.732203452799,1,{"$nulls":10},0.15,716.9598305179198,1.1,1.05,5,1,"2A"]
["1","03","01","01","05","","LN101-5020","1.03.01.01.05","CBX3010105","L3 Fabrication Oversight","2007-05-01","2007-08-31","JC","C","SL_ME2","Hrs",56,null,5576.354237361599,null,5576.354237361599,null,56,null,5576.354237361599,null,5576.354237361599,5576.354237361599,1,{"$nulls":10},0.15,836.4531356042398,1.1,1.05,5,1,"2A"]
["1","03","01","01","05","","LN101-5030","1.03.01.01.05","CBX3010105","L3 Installation Coordination Planning","2007-05-01","2007-07-02","JC","C","SL_ME2","Hrs",64,null,6372.976271270399,null,6372.976271270399,null,64,null,6372.976271270399,null,6372.976271270399,6372.976271270399,1,{"$nulls":10},0.15,955.9464406905597,1.1,1.05,5,1,"2A"]
["1","03","01","01","05","","LN101-5040","1.03.01.01.05","CBX3010105","L3 Installation Oversight","2007-09-04","2007-10-31","JC","C","SL_ME2","Hrs",80,null,8062.6535326664325,null,8062.6535326664325,null,80,null,8062.6535326664325,null,8062.6535326664325,3819.1516733683097,0.47,4243.501859298122,0.53,{"$nulls":8},0.15,1209.3980298999647,1.1,1.05,5,1,"2A"]
["1","03","01","01","05","","LN101-5040","1.03.01.01.05","CBX3010105","L3 Installation Oversight","2007-09-04","2007-10-31","JC","C","SL_MDD2","Hrs",40,null,3379.973599882648,null,3379.973599882648,null,40,null,3379.973599882648,null,3379.973599882648,1601.0401262602018,0.47,1778.9334736224464,0.53,{"$nulls":8},0.15,506.9960399823972,1.1,1.05,5,1,"2A"]
["1","03","01","01","05","","LN101-5050","1.03.01.01.05","CBX3010105","L3 Documentation","2007-12-04","2008-09-30","JC","C","SL_ME2","Hrs",120,null,12224.165110330536,null,12224.165110330536,null,120,null,12224.165110330536,null,12224.165110330536,null,null,12224.165110330536,1,{"$nulls":8},0.15,1833.6247665495803,1.1,1.05,5,2,"2A"]
["1","03","01","01","05","","LN101-5050","1.03.01.01.05","CBX3010105","L3 Documentation","2007-12-04","2008-09-30","JC","C","SL_MDD2","Hrs",200,null,17081.78545525716,null,17081.78545525716,null,200,null,17081.78545525716,null,17081.78545525716,null,null,17081.78545525716,1,{"$nulls":8},0.15,2562.267818288574,1.1,1.05,5,2,"2A"]
["1","03","01","01","05","","LN101-5060","1.03.01.01.05","CBX3010105","L3 System Construction Support to Components","2007-12-04","2008-04-11","JC","C","SL_ME2","Hrs",80,null,8149.443406887023,null,8149.443406887023,null,80,null,8149.443406887023,null,8149.443406887023,null,null,8149.443406887023,1,{"$nulls":8},0.15,1222.4165110330534,1.1,1.05,5,1,"2A"]
["1","03","01","01","05","","LN101-5060","1.03.01.01.05","CBX3010105","L3 System Construction Support to Components","2007-12-04","2008-04-11","JC","C","SL_KE2","Hrs",80,null,9223.450256500126,null,9223.450256500126,null,80,null,9223.450256500126,null,9223.450256500126,null,null,9223.450256500126,1,{"$nulls":8},0.15,1383.517538475019,1.1,1.05,5,1,"2A"]
["1","03","01","01","05","","LN101-5060","1.03.01.01.05","CBX3010105","L3 System Construction Support to Components","2007-12-04","2008-04-11","JC","C","SL_CE2","Hrs",80,null,9223.450256500126,null,9223.450256500126,null,80,null,9223.450256500126,null,9223.450256500126,null,null,9223.450256500126,1,{"$nulls":8},0.15,1383.517538475019,1.1,1.05,5,1,"2A"]
["1","03","01","01","05","","LN101-5070","1.03.01.01.05","CBX3010105","L3 Top Assembly","2007-05-01","2007-05-14","JC","C","SL_ME2","Hrs",5,null,497.8887711929999,null,497.8887711929999,null,5,null,497.8887711929999,null,497.8887711929999,497.8887711929999,1,{"$nulls":10},0.15,74.68331567894998,1.1,1.05,4,2,"2A"]
["1","03","01","01","05","","LN101-5070","1.03.01.01.05","CBX3010105","L3 Top Assembly","2007-05-01","2007-05-14","JC","C","SL_MDD2","Hrs",11,null,918.3755621106,null,918.3755621106,null,11,null,918.3755621106,null,918.3755621106,918.3755621106,1,{"$nulls":10},0.15,137.75633431659,1.1,1.05,4,2,"2A"]
["1","03","01","01","06","  ",null,null,null,"LTU System Integration                                      ",{"$nulls":6},2208,152400,206473.17240691753,166076.71724464433,209046.22200691752,null,2208,152400,206473.17240691753,166076.71724464433,372549.88965156197,208432.24859611547,null,164117.6410554464,null,0,null,0,null,0,null,0,null,null,111764.96689546855,{"$nulls":6},"Jose Chan"]
["1","03","01","01","06","","LN101-6020","1.03.01.01.06","CBX3010106","LTU Pedestal and Raft Design","2007-05-01","2007-05-31","TM","C","SL_ME2","Hrs",16,null,1593.2440678175997,null,1593.2440678175997,null,16,null,1593.2440678175997,null,1593.2440678175997,1593.2440678175997,1,{"$nulls":10},0.3,477.97322034527986,1.2,1.1,4,2,"2A"]
["1","03","01","01","06","","LN101-6020","1.03.01.01.06","CBX3010106","LTU Pedestal and Raft Design","2007-05-01","2007-05-31","TM","C","SL_MDD2","Hrs",32,null,2671.6379988671997,null,2671.6379988671997,null,32,null,2671.6379988671997,null,2671.6379988671997,2671.6379988671997,1,{"$nulls":10},0.3,801.4913996601599,1.2,1.1,4,2,"2A"]
["1","03","01","01","06","","LN101-6030","1.03.01.01.06","CBX3010106","LTU Beamline Shielding Fabrication","2007-09-26","2008-01-07","TM","C","SL_MSSC2","$$",null,75000,null,82167.40370097088,null,null,null,75000,null,82167.40370097088,82167.40370097088,3988.7089175228584,0.05,78178.69478344802,0.95,{"$nulls":8},0.3,24650.221110291266,1.2,1.1,4,3,"2A"]
["1","03","01","01","06","","LN101-6040","1.03.01.01.06","CBX3010106","LTU Pedestal and Raft Fabrication","2007-06-01","2008-02-01","TM","C","SL_MSSC2","$$",null,75000,null,81336.26394367346,null,null,null,75000,null,81336.26394367346,81336.26394367346,40502.13959644148,0.5,40834.124347231984,0.5,{"$nulls":8},0.3,24400.87918310204,1.2,1.1,4,3,"2A"]
["1","03","01","01","06","","LN101-6050","1.03.01.01.06","CBX3010106","LTU Procurement Support","2007-05-01","2007-07-23","TM","C","SL_ME2","Hrs",76,null,7567.909322133599,null,7567.909322133599,null,76,null,7567.909322133599,null,7567.909322133599,7567.909322133599,1,{"$nulls":10},0.3,2270.3727966400797,1.2,1.1,5,1,"2A"]
["1","03","01","01","06","","LN101-6060","1.03.01.01.06","CBX3010106","LTU Fabrication Oversight","2007-05-01","2008-01-18","TM","C","SL_ME2","Hrs",76,null,7640.324393395389,null,7640.324393395389,null,76,null,7640.324393395389,null,7640.324393395389,4461.7161533950175,0.58,3178.608240000372,0.42,{"$nulls":8},0.3,2292.0973180186165,1.2,1.1,5,1,"2A"]
["1","03","01","01","06","","LN101-6070","1.03.01.01.06","CBX3010106","LTU Installation Coordination Planning","2007-05-01","2007-10-03","TM","C","SL_ME2","Hrs",280,null,27890.045776966657,null,27890.045776966657,null,280,null,27890.045776966657,null,27890.045776966657,27530.174218554184,0.99,359.871558412473,0.01,{"$nulls":8},0.3,8367.013733089996,1.2,1.1,5,1,"2A"]
["1","03","01","01","06","","LN101-6080","1.03.01.01.06","CBX3010106","LTU Installation Oversight","2008-02-04","2008-03-31","TM","C","SL_ME2","Hrs",160,null,16298.886813774046,null,16298.886813774046,null,160,null,16298.886813774046,null,16298.886813774046,null,null,16298.886813774046,1,{"$nulls":8},0.3,4889.666044132214,1.2,1.1,5,1,"2A"]
["1","03","01","01","06","","LN101-6080","1.03.01.01.06","CBX3010106","LTU Installation Oversight","2008-02-04","2008-03-31","TM","C","SL_MDD2","Hrs",80,null,6832.714182102864,null,6832.714182102864,null,80,null,6832.714182102864,null,6832.714182102864,null,null,6832.714182102864,1,{"$nulls":8},0.3,2049.814254630859,1.2,1.1,5,1,"2A"]
["1","03","01","01","06","","LN101-6090","1.03.01.01.06","CBX3010106","LTU Documentation","2007-05-01","2007-10-18","TM","C","SL_ME2","Hrs",80,null,7984.5426458679,null,7984.5426458679,null,80,null,7984.5426458679,null,7984.5426458679,7186.088381281111,0.9,798.45426458679,0.1,{"$nulls":8},0.3,2395.36279376037,1.2,1.1,5,2,"2A"]
["1","03","01","01","06","","LN101-6090","1.03.01.01.06","CBX3010106","LTU Documentation","2007-05-01","2007-10-18","TM","C","SL_MDD2","Hrs",160,null,13388.91383132297,null,13388.91383132297,null,160,null,13388.91383132297,null,13388.91383132297,12050.022448190673,0.9,1338.891383132297,0.1,{"$nulls":8},0.3,4016.674149396891,1.2,1.1,5,2,"2A"]
["1","03","01","01","06","","LN101-6100","1.03.01.01.06","CBX3010106","LTU Water System Design Support","2007-05-01","2008-01-16","TM","C","SL_ME2","Hrs",160,null,16083.247357056733,null,16083.247357056733,null,160,null,16083.247357056733,null,16083.247357056733,9464.372483191077,0.59,6618.874873865655,0.41,{"$nulls":8},0.3,4824.974207117019,1.2,1.1,5,2,"2A"]
["1","03","01","01","06","","LN101-6110","1.03.01.01.06","CBX3010106","LTU Vibration Engineering","2007-05-01","2007-09-14","TM","C","SL_ME2","Hrs",32,null,3186.4881356351993,null,3186.4881356351993,null,32,null,3186.4881356351993,null,3186.4881356351993,3186.4881356351993,1,{"$nulls":10},0.3,955.9464406905597,1.2,1.1,5,2,"2A"]
["1","03","01","01","06","","LN101-6120","1.03.01.01.06","CBX3010106","LTU CF Interface","2007-09-04","2007-09-17","TM","C","SL_ME2","Hrs",64,null,6372.976271270399,null,6372.976271270399,null,64,null,6372.976271270399,null,6372.976271270399,6372.976271270399,1,{"$nulls":10},0.3,1911.8928813811194,1.2,1.1,5,1,"2A"]
["1","03","01","01","06","","LN101-6130","1.03.01.01.06","CBX3010106","LTU Undulator Interface","2007-09-04","2007-09-17","TM","C","SL_ME2","Hrs",48,null,4779.732203452799,null,4779.732203452799,null,48,null,4779.732203452799,null,4779.732203452799,4779.732203452799,1,{"$nulls":10},0.3,1433.9196610358397,1.2,1.1,5,1,"2A"]
["1","03","01","01","06","","LN101-6140","1.03.01.01.06","CBX3010106","LTU Spot Shielding Design","2007-07-02","2007-09-25","TM","C","SL_ME2","Hrs",320,null,31864.881356351994,null,31864.881356351994,null,320,null,31864.881356351994,null,31864.881356351994,31864.881356351994,1,{"$nulls":10},0.3,9559.464406905598,1.2,1.1,5,2,"2A"]
["1","03","01","01","06","","LN101-6140","1.03.01.01.06","CBX3010106","LTU Spot Shielding Design","2007-07-02","2007-09-25","TM","C","SL_MDD2","Hrs",320,null,26716.379988671997,null,26716.379988671997,null,320,null,26716.379988671997,null,26716.379988671997,26716.379988671997,1,{"$nulls":10},0.3,8014.913996601599,1.2,1.1,5,2,"2A"]
["1","03","01","01","06","","LN101-6150","1.03.01.01.06","CBX3010106","LTU Installation Drawings","2007-05-01","2008-01-02","TM","C","SL_MDD2","Hrs",304,null,25601.24806223019,null,25601.24806223019,null,304,null,25601.24806223019,null,25601.24806223019,15922.727453338288,0.62,9678.5206088919,0.38,{"$nulls":8},0.3,7680.3744186690565,1.2,1.1,5,1,"2A"]
["1","03","01","01","06","","LN101-6160","1.03.01.01.06","CBX3010106","LTU: Finite Element Analysis","2007-05-01","2007-05-01",null,"C","SL_MSPS2","$$",null,2400,null,2573.0496,2573.0496,null,null,2400,null,2573.0496,2573.0496,2573.0496,1,{"$nulls":10},0.3,771.9148799999999,1.2,1.1,null,1,"2A"]
["1","03","01","01","07","  ",null,null,null,"E-Dump System Integration                                   ",{"$nulls":6},1788,150000,166130.58184673273,163101.84067559056,248387.76124673276,null,1788,150000,166130.58184673273,163101.84067559056,329232.4225223232,174252.32406305405,null,154980.09845926924,null,0,null,0,null,0,null,0,null,null,98769.72675669698,{"$nulls":6},"Jose Chan"]
["1","03","01","01","07","","LN101-7020","1.03.01.01.07","CBX3010107","E-Dump Pedestal and Raft Design","2007-05-01","2007-09-28","JL","C","SL_ME2","Hrs",18,null,1792.3995762947995,null,1792.3995762947995,null,18,null,1792.3995762947995,null,1792.3995762947995,1792.3995762947995,1,{"$nulls":10},0.3,537.7198728884398,1.2,1.1,5,2,"2A"]
["1","03","01","01","07","","LN101-7020","1.03.01.01.07","CBX3010107","E-Dump Pedestal and Raft Design","2007-05-01","2007-09-28","JL","C","SL_MDD2","Hrs",48,null,4007.4569983007996,null,4007.4569983007996,null,48,null,4007.4569983007996,null,4007.4569983007996,4007.4569983007996,1,{"$nulls":10},0.3,1202.2370994902399,1.2,1.1,5,2,"2A"]
["1","03","01","01","07","","LN101-7030","1.03.01.01.07","CBX3010107","E-Dump Beamline Shielding Fabrication","2007-06-26","2007-10-31","JL","C","SL_MSSC2","$$",null,75000,null,80844.66127559054,null,null,null,75000,null,80844.66127559054,80844.66127559054,61747.49719474238,0.76,19097.164080848157,0.24,{"$nulls":8},0.3,24253.398382677162,1.2,1.1,5,3,"2A"]
["1","03","01","01","07","","LN101-7040","1.03.01.01.07","CBX3010107","E-Dump Pedestal and Raft Fabrication","2007-10-01","2008-02-25","JL","C","SL_MSSC2","$$",null,75000,null,82257.17940000001,82257.17940000001,null,null,75000,null,82257.17940000001,82257.17940000001,null,null,82257.17940000001,1,{"$nulls":8},0.3,24677.153820000003,1.2,1.1,5,3,"2A"]
["1","03","01","01","07","","LN101-7050","1.03.01.01.07","CBX3010107","E-Dump Procurement Support","2007-05-01","2008-01-02","JL","C","SL_ME2","Hrs",76,null,7633.713216605322,null,7633.713216605322,null,76,null,7633.713216605322,null,7633.713216605322,4747.797244474042,0.62,2885.9159721312803,0.38,{"$nulls":8},0.3,2290.1139649815964,1.2,1.1,5,1,"2A"]
["1","03","01","01","07","","LN101-7060","1.03.01.01.07","CBX3010107","E-Dump Fabrication Oversight","2007-05-01","2008-01-02","JL","C","SL_ME2","Hrs",78,null,7834.600406515988,null,7834.600406515988,null,78,null,7834.600406515988,null,7834.600406515988,4872.739277223358,0.62,2961.8611292926294,0.38,{"$nulls":8},0.3,2350.3801219547963,1.2,1.1,5,1,"2A"]
["1","03","01","01","07","","LN101-7070","1.03.01.01.07","CBX3010107","E-Dump Installation Coordination Planning","2007-05-01","2008-01-02","JL","C","SL_ME2","Hrs",152,null,15267.426433210643,null,15267.426433210643,null,152,null,15267.426433210643,null,15267.426433210643,9495.594488948083,0.62,5771.831944262561,0.38,{"$nulls":8},0.3,4580.227929963193,1.2,1.1,5,1,"2A"]
["1","03","01","01","07","","LN101-7080","1.03.01.01.07","CBX3010107","E-Dump Installation Oversight","2008-04-21","2008-05-02","JL","C","SL_ME2","Hrs",160,null,16298.886813774046,null,16298.886813774046,null,160,null,16298.886813774046,null,16298.886813774046,null,null,16298.886813774046,1,{"$nulls":8},0.3,4889.666044132214,1.2,1.1,5,1,"2A"]
["1","03","01","01","07","","LN101-7080","1.03.01.01.07","CBX3010107","E-Dump Installation Oversight","2008-04-21","2008-05-02","JL","C","SL_MDD2","Hrs",80,null,6832.714182102864,null,6832.714182102864,null,80,null,6832.714182102864,null,6832.714182102864,null,null,6832.714182102864,1,{"$nulls":8},0.3,2049.814254630859,1.2,1.1,5,1,"2A"]
["1","03","01","01","07","","LN101-7090","1.03.01.01.07","CBX3010107","E-Dump Documentation","2007-05-01","2007-11-01","JL","C","SL_ME2","Hrs",80,null,7997.0894429019645,null,7997.0894429019645,null,80,null,7997.0894429019645,null,7997.0894429019645,6649.753721543481,0.83,1347.3357213584832,0.17,{"$nulls":8},0.3,2399.126832870589,1.2,1.1,5,2,"2A"]
["1","03","01","01","07","","LN101-7090","1.03.01.01.07","CBX3010107","E-Dump Documentation","2007-05-01","2007-11-01","JL","C","SL_MDD2","Hrs",80,null,6704.976490282025,null,6704.976490282025,null,80,null,6704.976490282025,null,6704.976490282025,5575.333712027988,0.83,1129.6427782540368,0.17,{"$nulls":8},0.3,2011.4929470846075,1.2,1.1,5,2,"2A"]
["1","03","01","01","07","","LN101-7100","1.03.01.01.07","CBX3010107","E-Dump Water System Design Support","2007-05-01","2008-01-16","JL","C","SL_ME2","Hrs",32,null,3216.649471411347,null,3216.649471411347,null,32,null,3216.649471411347,null,3216.649471411347,1892.8744966382158,0.59,1323.7749747731311,0.41,{"$nulls":8},0.3,964.9948414234041,1.2,1.1,5,1,"2A"]
["1","03","01","01","07","","LN101-7110","1.03.01.01.07","CBX3010107","E-Dump Vibration Engineering","2007-05-01","2007-09-14","JL","C","SL_ME2","Hrs",16,null,1593.2440678175997,null,1593.2440678175997,null,16,null,1593.2440678175997,null,1593.2440678175997,1593.2440678175997,1,{"$nulls":10},0.3,477.97322034527986,1.2,1.1,5,2,"2A"]
["1","03","01","01","07","","LN101-7120","1.03.01.01.07","CBX3010107","E-Dump CF Interface","2007-05-01","2007-09-17","JL","C","SL_ME2","Hrs",32,null,3186.4881356351993,null,3186.4881356351993,null,32,null,3186.4881356351993,null,3186.4881356351993,3186.4881356351993,1,{"$nulls":10},0.3,955.9464406905597,1.2,1.1,5,1,"2A"]
["1","03","01","01","07","","LN101-7130","1.03.01.01.07","CBX3010107","E-Dump Undulator Interface","2007-05-01","2007-09-17","JL","C","SL_ME2","Hrs",40,null,3983.1101695439993,null,3983.1101695439993,null,40,null,3983.1101695439993,null,3983.1101695439993,3983.1101695439993,1,{"$nulls":10},0.3,1194.9330508631997,1.2,1.1,5,1,"2A"]
["1","03","01","01","07","","LN101-7140","1.03.01.01.07","CBX3010107","E-Dump Spot Shielding Design","2007-05-01","2007-06-25","JL","C","SL_ME2","Hrs",288,null,28678.393220716793,null,28678.393220716793,null,288,null,28678.393220716793,null,28678.393220716793,28678.393220716793,1,{"$nulls":10},0.3,8603.517966215037,1.2,1.1,5,2,"2A"]
["1","03","01","01","07","","LN101-7140","1.03.01.01.07","CBX3010107","E-Dump Spot Shielding Design","2007-05-01","2007-06-25","JL","C","SL_MDD2","Hrs",288,null,24044.741989804796,null,24044.741989804796,null,288,null,24044.741989804796,null,24044.741989804796,24044.741989804796,1,{"$nulls":10},0.3,7213.422596941438,1.2,1.1,5,2,"2A"]
["1","03","01","01","07","","LN101-7150","1.03.01.01.07","CBX3010107","E-Dump Installation Drawings","2007-06-26","2008-01-31","JL","C","SL_MDD2","Hrs",320,null,27058.691231814526,null,27058.691231814526,null,320,null,27058.691231814526,null,27058.691231814526,11984.899769342506,0.44,15073.791462472018,0.56,{"$nulls":8},0.3,8117.607369544357,1.2,1.1,5,1,"2A"]
["1","03","01","03","  ","  ",null,null,null,"Travel                                                      ",{"$nulls":6},0,59316,0,75444.15018239999,75444.15018239999,null,0,59316,0,75444.15018239999,75444.15018239999,10670.299199999998,null,25116.696,null,25694.376,null,13962.7789824,null,0,null,0,null,null,11316.62252736,{"$nulls":6},"Jose Chan"]
["1","03","01","03","","","LN103-0010","1.03.01.03","CAX30103","FY07 Travel","2007-05-01","2007-09-28","JC","C","SL_MSTR2","$$",null,8692,null,10670.299199999998,10670.299199999998,null,null,8692,null,10670.299199999998,10670.299199999998,10670.299199999998,1,{"$nulls":10},0.15,1600.5448799999997,1.1,1.05,6,1,"2A"]
["1","03","01","03","","","LN103-0020","1.03.01.03","CAX30103","FY08 Travel","2007-10-01","2008-09-30","JC","C","SL_MSTR2","$$",null,20000,null,25116.696,25116.696,null,null,20000,null,25116.696,25116.696,null,null,25116.696,1,{"$nulls":8},0.15,3767.5044,1.1,1.05,6,1,"2A"]
["1","03","01","03","","","LN103-0030","1.03.01.03","CAX30103","FY09 Travel","2008-10-01","2009-09-30",null,"C","SL_MSTR2","$$",null,20000,null,25694.376,25694.376,null,null,20000,null,25694.376,25694.376,{"$nulls":4},25694.376,1,{"$nulls":6},0.15,3854.1564,1.1,1.05,null,1,"2A"]
["1","03","01","03","","","LN103-0040","1.03.01.03","CAX30103","FY10 Travel","2009-10-01","2010-03-31",null,"C","SL_MSTR2","$$",null,10624,null,13962.7789824,13962.7789824,null,null,10624,null,13962.7789824,13962.7789824,{"$nulls":6},13962.7789824,1,{"$nulls":4},0.15,2094.41684736,1.1,1.05,null,1,"2A"]
["1","03","01","04","  ","  ",null,null,null,"Linac Management                                            ",{"$nulls":6},10105,80000,1021801.9771891834,88772.95696000001,1110574.9341491833,null,10105,80000,1021801.9771891834,88772.95696000001,1110574.9341491833,278751.01633696014,null,403465.8297696435,null,338795.41660514276,null,89562.67143743702,null,0,null,0,null,null,115496.14126291833,{"$nulls":6},"Jose Chan"]
["1","03","01","04","","","LN104-1000","1.03.01.04","CAX30104","Computers - CONST 70%","2007-05-01","2007-09-28","JC","C","SL_MSEG2","$$",null,10000,null,10721.04,10721.04,null,null,10000,null,10721.04,10721.04,10721.04,1,{"$nulls":10},0.15,1608.1560000000002,1.1,1.05,5,1,"2A"]
["1","03","01","04","","","LN104-1010","1.03.01.04","CAX30104","Material & Supplies - CONST 70%","2007-05-01","2007-09-28","JC","C","SL_MSCS2","$$",null,10000,null,10721.04,10721.04,null,null,10000,null,10721.04,10721.04,10721.04,1,{"$nulls":10},0.15,1608.1560000000002,1.1,1.05,5,3,"2A"]
["1","03","01","04","","","LN104-1050","1.03.01.04","CAX30104","Linac System Management Effort - CONST 70%","2007-05-01","2007-09-28","JC","C","SL_TSM2","Hrs",742,null,78561.24599751117,null,78561.24599751117,null,742,null,78561.24599751117,null,78561.24599751117,78561.24599751117,1,{"$nulls":10},0.1,7856.124599751118,1.1,1,4,1,"2A"]
["1","03","01","04","","","LN104-1060","1.03.01.04","CAX30104","Technical Leads - CONST 70%","2007-05-01","2007-09-28","JC","C","SL_ME2","Hrs",1113,null,110830.04046756178,null,110830.04046756178,null,1113,null,110830.04046756178,null,110830.04046756178,110830.04046756178,1,{"$nulls":10},0.1,11083.004046756178,1.1,1,4,1,"2A"]
["1","03","01","04","","","LN104-1070","1.03.01.04","CAX30104","Fabrication Coordination 70%","2007-05-01","2007-09-28","JC","C","SL_ME2","Hrs",371,null,36943.346822520594,null,36943.346822520594,null,371,null,36943.346822520594,null,36943.346822520594,36943.346822520594,1,{"$nulls":10},0.1,3694.33468225206,1.1,1,4,1,"2A"]
["1","03","01","04","","","LN104-1070","1.03.01.04","CAX30104","Fabrication Coordination 70%","2007-05-01","2007-09-28","JC","C","SL_MDD2","Hrs",371,null,30974.303049366597,null,30974.303049366597,null,371,null,30974.303049366597,null,30974.303049366597,30974.303049366597,1,{"$nulls":10},0.1,3097.43030493666,1.1,1,4,1,"2A"]
["1","03","01","04","","","LN104-2000","1.03.01.04","CAY30104","Computers - CONST","2007-10-01","2008-09-30","JC","C","SL_MSEG2","$$",null,10000,null,10967.62392,10967.62392,null,null,10000,null,10967.62392,10967.62392,null,null,10967.62392,1,{"$nulls":8},0.15,1645.143588,1.1,1.05,5,1,"2A"]
["1","03","01","04","","","LN104-2010","1.03.01.04","CAY30104","Material & Supplies - CONST","2007-10-01","2008-09-30","JC","C","SL_MSCS2","$$",null,10000,null,10967.62392,10967.62392,null,null,10000,null,10967.62392,10967.62392,null,null,10967.62392,1,{"$nulls":8},0.15,1645.143588,1.1,1.05,5,3,"2A"]
["1","03","01","04","","","LN104-2050","1.03.01.04","CAY30104","Linac System Management Effort - CONST 50%","2007-10-01","2008-09-30","JC","C","SL_TSM2","Hrs",851,null,92174.25823691551,null,92174.25823691551,null,851,null,92174.25823691551,null,92174.25823691551,null,null,92174.25823691551,1,{"$nulls":8},0.1,9217.425823691552,1.1,1,4,1,"2A"]
["1","03","01","04","","","LN104-2060","1.03.01.04","CAY30104","Technical Leads - CONST 50%","2007-10-01","2008-09-30","JC","C","SL_ME2","Hrs",1276,null,129983.62233984802,null,129983.62233984802,null,1276,null,129983.62233984802,null,129983.62233984802,null,null,129983.62233984802,1,{"$nulls":8},0.1,12998.362233984803,1.1,1,4,1,"2A"]
["1","03","01","04","","","LN104-2070","1.03.01.04","CAY30104","Fabrication Coordination 50%","2007-10-01","2008-09-30","JC","C","SL_ME2","Hrs",851,null,86689.70424076071,null,86689.70424076071,null,851,null,86689.70424076071,null,86689.70424076071,null,null,86689.70424076071,1,{"$nulls":8},0.1,8668.970424076071,1.1,1,4,1,"2A"]
["1","03","01","04","","","LN104-2070","1.03.01.04","CAY30104","Fabrication Coordination 50%","2007-10-01","2008-09-30","JC","C","SL_MDD2","Hrs",851,null,72682.9971121192,null,72682.9971121192,null,851,null,72682.9971121192,null,72682.9971121192,null,null,72682.9971121192,1,{"$nulls":8},0.1,7268.299711211921,1.1,1,4,1,"2A"]
["1","03","01","04","","","LN104-3010","1.03.01.04","CAZ30104","Computers - CONST","2008-10-01","2009-09-30","JC","C","SL_MSEG2","$$",null,10000,null,11219.877520000002,11219.877520000002,null,null,10000,null,11219.877520000002,11219.877520000002,{"$nulls":4},11219.877520000002,1,{"$nulls":6},0.15,1682.9816280000002,1.1,1.05,5,1,"2A"]
["1","03","01","04","","","LN104-3020","1.03.01.04","CAZ30104","Material & Supplies - CONST","2008-10-01","2009-09-30","JC","C","SL_MSCS2","$$",null,10000,null,11219.877520000002,11219.877520000002,null,null,10000,null,11219.877520000002,11219.877520000002,{"$nulls":4},11219.877520000002,1,{"$nulls":6},0.15,1682.9816280000002,1.1,1.05,5,3,"2A"]
["1","03","01","04","","","LN104-3060","1.03.01.04","CAZ30104","Linac System Management Effort - CONST 25%","2008-10-01","2009-09-30","JC","C","SL_TSM2","Hrs",872,null,96621.13663899743,null,96621.13663899743,null,872,null,96621.13663899743,null,96621.13663899743,{"$nulls":4},96621.13663899743,1,{"$nulls":6},0.1,9662.113663899743,1.1,1,4,1,"2A"]
["1","03","01","04","","","LN104-3070","1.03.01.04","CAZ30104","Cost Account Managers - CONST 25%","2008-10-01","2009-09-30","JC","C","SL_ME2","Hrs",1307,null,136203.76564212007,null,136203.76564212007,null,1307,null,136203.76564212007,null,136203.76564212007,{"$nulls":4},136203.76564212007,1,{"$nulls":6},0.1,13620.376564212007,1.1,1,4,1,"2A"]
["1","03","01","04","","","LN104-3080","1.03.01.04","CAZ30104","Fabrication Coordination 25%","2008-10-01","2009-09-30","JC","C","SL_ME2","Hrs",436,null,45435.99221114334,null,45435.99221114334,null,436,null,45435.99221114334,null,45435.99221114334,{"$nulls":4},45435.99221114334,1,{"$nulls":6},0.1,4543.599221114334,1.1,1,4,1,"2A"]
["1","03","01","04","","","LN104-3080","1.03.01.04","CAZ30104","Fabrication Coordination 25%","2008-10-01","2009-09-30","JC","C","SL_MDD2","Hrs",436,null,38094.76707288191,null,38094.76707288191,null,436,null,38094.76707288191,null,38094.76707288191,{"$nulls":4},38094.76707288191,1,{"$nulls":6},0.1,3809.476707288191,1.1,1,4,1,"2A"]
["1","03","01","04","","","LN104-4010","1.03.01.04","CAZZ30104","Computers - CONST","2009-10-01","2010-03-31","JC","C","SL_MSEG2","$$",null,10000,null,11477.93704,11477.93704,null,null,10000,null,11477.93704,11477.93704,{"$nulls":6},11477.93704,1,{"$nulls":4},0.15,1721.690556,1.1,1.05,5,1,"2A"]
["1","03","01","04","","","LN104-4020","1.03.01.04","CAZZ30104","Material & Supplies - CONST","2009-10-01","2010-03-31","JC","C","SL_MSCS2","$$",null,10000,null,11477.93704,11477.93704,null,null,10000,null,11477.93704,11477.93704,{"$nulls":6},11477.93704,1,{"$nulls":4},0.15,1721.690556,1.1,1.05,5,3,"2A"]
["1","03","01","04","","","LN104-4060","1.03.01.04","CAZZ30104","Linac System Management Effort - CONST 10%","2009-10-01","2010-03-31","JC","C","SL_TSM2","Hrs",179,null,20290.110413321985,null,20290.110413321985,null,179,null,20290.110413321985,null,20290.110413321985,{"$nulls":6},20290.110413321985,1,{"$nulls":4},0.1,2029.0110413321986,1.1,1,4,1,"2A"]
["1","03","01","04","","","LN104-4070","1.03.01.04","CAZZ30104","Cost Account Managers - CONST 10%","2009-10-01","2010-03-31","JC","C","SL_ME2","Hrs",269,null,28677.51590468654,null,28677.51590468654,null,269,null,28677.51590468654,null,28677.51590468654,{"$nulls":6},28677.51590468654,1,{"$nulls":4},0.1,2867.7515904686543,1.1,1,4,1,"2A"]
["1","03","01","04","","","LN104-4080","1.03.01.04","CAZZ30104","Fabrication Coordination 10%","2009-10-01","2010-03-31","JC","C","SL_ME2","Hrs",90,null,9594.707923501073,null,9594.707923501073,null,90,null,9594.707923501073,null,9594.707923501073,{"$nulls":6},9594.707923501073,1,{"$nulls":4},0.1,959.4707923501073,1.1,1,4,1,"2A"]
["1","03","01","04","","","LN104-4080","1.03.01.04","CAZZ30104","Fabrication Coordination 10%","2009-10-01","2010-03-31","JC","C","SL_MDD2","Hrs",90,null,8044.463115927413,null,8044.463115927413,null,90,null,8044.463115927413,null,8044.463115927413,{"$nulls":6},8044.463115927413,1,{"$nulls":4},0.1,804.4463115927414,1.1,1,4,1,"2A"]
["1","03","02","  ","  ","  ",null,null,null,"Linac Controls & Power Conversion Subsystem                 ",{"$nulls":6},34820,3980691,2866515.6345673883,4273437.021411999,7139952.6559793865,null,34820,3980691,2866515.6345673883,4273437.021411999,7139952.6559793865,5664513.287931696,null,1475439.3680476868,null,0,null,0,null,0,null,0,null,null,1837566.4611474467,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","01","  ","  ",null,null,null,"Personnel Protection System (PPS)                           ",{"$nulls":6},4554,284280,354213.56513173255,304777.72512,658991.2902517326,null,4554,284280,354213.56513173255,304777.72512,658991.2902517326,506442.483027391,null,152548.80722434158,null,0,null,0,null,0,null,0,null,null,164747.82256293314,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","01","","","LN201_0805","1.03.02.01","CBCLN30201","LTU Rack Layout and Wiring","2007-06-01","2007-08-02",null,"C","SL_CCA2","Hrs",660,null,43319.52152272799,null,43319.52152272799,null,660,null,43319.52152272799,null,43319.52152272799,43319.52152272799,1,{"$nulls":10},0.25,10829.880380681998,1.15,1.1,3,3,"2G","P. Bong"]
["1","03","02","01","","","LN201_0810","1.03.02.01","CBCLN30201","LTU Rack and Wiring Bid Prep","2007-08-03","2007-11-14",null,"C","SL_CCA2","Hrs",292,null,19353.91322750249,null,19353.91322750249,null,292,null,19353.91322750249,null,19353.91322750249,11086.222140025697,0.57,8267.691087476791,0.43,{"$nulls":8},0.25,4838.478306875622,1.15,1.1,3,3,"2G","P. Bong"]
["1","03","02","01","","","LN201_0820","1.03.02.01","CBCLN30201","LTU Controls Software","2007-06-01","2007-10-22",null,"C","SL_CP2","Hrs",400,null,32979.2352530847,null,32979.2352530847,null,400,null,32979.2352530847,null,32979.2352530847,28136.13077535897,0.85,4843.104477725725,0.15,{"$nulls":8},0.25,8244.808813271175,1.15,1.1,4,3,"2G","P. Bong"]
["1","03","02","01","","","LN201_0825","1.03.02.01","CBCLN30201","LTU Mechanical Desgin","2007-06-01","2007-10-22",null,"C","SL_ME2","Hrs",200,null,19982.818057925935,null,19982.818057925935,null,200,null,19982.818057925935,null,19982.818057925935,17048.27834312562,0.85,2934.539714800312,0.15,{"$nulls":8},0.25,4995.704514481484,1.15,1.1,4,3,"2G","P. Bong"]
["1","03","02","01","","","LN201_0830","1.03.02.01","CBCLN30201","LTU Mechanical Fab","2007-06-01","2007-10-22",null,"C","SL_ME2","Hrs",240,null,23979.381669511116,null,23979.381669511116,null,240,null,23979.381669511116,null,23979.381669511116,20457.93401175074,0.85,3521.4476577603737,0.15,{"$nulls":8},0.25,5994.845417377779,1.15,1.1,4,3,"2G","P. Bong"]
["1","03","02","01","","","LN201_0840","1.03.02.01","CBCLN30201","RCV: 1000 4PR16AS cable","2007-08-27","2007-08-27",null,"C","SL_MSEG2","$$",null,1360,null,1458.06144,1458.06144,null,null,1360,null,1458.06144,1458.06144,1458.06144,1,{"$nulls":10},0.25,364.51536,1.15,1.1,2,3,"2G","P. Bong"]
["1","03","02","01","","","LN201_0845","1.03.02.01","CBCLN30201","RCV: 2000 36PR16AS cable","2007-08-27","2007-08-27",null,"C","SL_MSEG2","$$",null,24000,null,25730.496,25730.496,null,null,24000,null,25730.496,25730.496,25730.496,1,{"$nulls":10},0.25,6432.624,1.15,1.1,2,3,"2G","P. Bong"]
["1","03","02","01","","","LN201_0850","1.03.02.01","CBCLN30201","RCV: 8000 Hookup wire","2007-08-27","2007-08-27",null,"C","SL_MSEG2","$$",null,2800,null,3001.8912,3001.8912,null,null,2800,null,3001.8912,3001.8912,3001.8912,1,{"$nulls":10},0.25,750.4728,1.15,1.1,2,3,"2G","P. Bong"]
["1","03","02","01","","","LN201_0855","1.03.02.01","CBCLN30201","RCV: 50 EO buttons","2007-08-27","2007-08-27",null,"C","SL_MSEG2","$$",null,9000,null,9648.936,9648.936,null,null,9000,null,9648.936,9648.936,9648.936,1,{"$nulls":10},0.25,2412.234,1.15,1.1,2,3,"2G","P. Bong"]
["1","03","02","01","","","LN201_0860","1.03.02.01","CBCLN30201","RCV: 6 EE buttons","2007-08-27","2007-08-27",null,"C","SL_MSEG2","$$",null,900,null,964.8936,964.8936,null,null,900,null,964.8936,964.8936,964.8936,1,{"$nulls":10},0.25,241.2234,1.15,1.1,2,3,"2G","P. Bong"]
["1","03","02","01","","","LN201_0865","1.03.02.01","CBCLN30201","RCV: 12 Limit Switches","2007-08-27","2007-08-27",null,"C","SL_MSEG2","$$",null,1800,null,1929.7872,1929.7872,null,null,1800,null,1929.7872,1929.7872,1929.7872,1,{"$nulls":10},0.25,482.4468,1.15,1.1,2,3,"2G","P. Bong"]
["1","03","02","01","","","LN201_0870","1.03.02.01","CBCLN30201","RCV: 2 Camera","2007-08-27","2007-08-27",null,"C","SL_MSEG2","$$",null,400,null,428.84159999999997,428.84159999999997,null,null,400,null,428.84159999999997,428.84159999999997,428.84159999999997,1,{"$nulls":10},0.25,107.21039999999999,1.15,1.1,2,3,"2G","P. Bong"]
["1","03","02","01","","","LN201_0875","1.03.02.01","CBCLN30201","RCV: 2 Annunciator","2007-08-27","2007-08-27",null,"C","SL_MSEG2","$$",null,2400,null,2573.0496,2573.0496,null,null,2400,null,2573.0496,2573.0496,2573.0496,1,{"$nulls":10},0.25,643.2624,1.15,1.1,2,3,"2G","P. Bong"]
["1","03","02","01","","","LN201_0880","1.03.02.01","CBCLN30201","RCV: 2 Y/M Light","2007-08-27","2007-08-27",null,"C","SL_MSEG2","$$",null,400,null,428.84159999999997,428.84159999999997,null,null,400,null,428.84159999999997,428.84159999999997,428.84159999999997,1,{"$nulls":10},0.25,107.21039999999999,1.15,1.1,2,3,"2G","P. Bong"]
["1","03","02","01","","","LN201_0885","1.03.02.01","CBCLN30201","RCV: 6 Search Buttons","2007-08-27","2007-08-27",null,"C","SL_MSEG2","$$",null,1200,null,1286.5248,1286.5248,null,null,1200,null,1286.5248,1286.5248,1286.5248,1,{"$nulls":10},0.25,321.6312,1.15,1.1,2,3,"2G","P. Bong"]
["1","03","02","01","","","LN201_0890","1.03.02.01","CBCLN30201","RCV: 2 Audio Amplifier","2007-08-27","2007-08-27",null,"C","SL_MSEG2","$$",null,1000,null,1072.104,1072.104,null,null,1000,null,1072.104,1072.104,1072.104,1,{"$nulls":10},0.25,268.026,1.15,1.1,2,3,"2G","P. Bong"]
["1","03","02","01","","","LN201_0895","1.03.02.01","CBCLN30201","RCV: 2 Audio Annunciuator","2007-08-27","2007-08-27",null,"C","SL_MSEG2","$$",null,2000,null,2144.208,2144.208,null,null,2000,null,2144.208,2144.208,2144.208,1,{"$nulls":10},0.25,536.052,1.15,1.1,2,3,"2G","P. Bong"]
["1","03","02","01","","","LN201_0900","1.03.02.01","CBCLN30201","RCV: 10 Speakers","2007-08-27","2007-08-27",null,"C","SL_MSEG2","$$",null,1000,null,1072.104,1072.104,null,null,1000,null,1072.104,1072.104,1072.104,1,{"$nulls":10},0.25,268.026,1.15,1.1,2,3,"2G","P. Bong"]
["1","03","02","01","","","LN201_0905","1.03.02.01","CBCLN30201","RCV: 6 Door Hardware","2007-08-27","2007-08-27",null,"C","SL_MSEG2","$$",null,1500,null,1608.156,1608.156,null,null,1500,null,1608.156,1608.156,1608.156,1,{"$nulls":10},0.25,402.039,1.15,1.1,2,3,"2G","P. Bong"]
["1","03","02","01","","","LN201_0910","1.03.02.01","CBCLN30201","RCV: 3 Keybank","2007-08-27","2007-08-27",null,"C","SL_MSEG2","$$",null,4500,null,4824.468,4824.468,null,null,4500,null,4824.468,4824.468,4824.468,1,{"$nulls":10},0.25,1206.117,1.15,1.1,2,3,"2G","P. Bong"]
["1","03","02","01","","","LN201_0915","1.03.02.01","CBCLN30201","RCV: 4 Hoffman Boxes","2007-08-27","2007-08-27",null,"C","SL_MSEG2","$$",null,520,null,557.4940799999999,557.4940799999999,null,null,520,null,557.4940799999999,557.4940799999999,557.4940799999999,1,{"$nulls":10},0.25,139.37351999999998,1.15,1.1,2,3,"2G","P. Bong"]
["1","03","02","01","","","LN201_0920","1.03.02.01","CBCLN30201","RCV: 6 PLC Control Package","2007-08-27","2007-08-27",null,"C","SL_MSEG2","$$",null,120000,null,128652.48,128652.48,null,null,120000,null,128652.48,128652.48,128652.48,1,{"$nulls":10},0.25,32163.12,1.15,1.1,2,3,"2G","P. Bong"]
["1","03","02","01","","","LN201_0925","1.03.02.01","CBCLN30201","RCV: 1 BSOIC","2007-08-27","2007-08-27",null,"C","SL_MSEG2","$$",null,87500,null,93809.1,93809.1,null,null,87500,null,93809.1,93809.1,93809.1,1,{"$nulls":10},0.25,23452.275,1.15,1.1,6,3,"2G","P. Bong"]
["1","03","02","01","","","LN201_0930","1.03.02.01","CBCLN30201","RCV: 3 Battery Recharger","2007-08-27","2007-08-27",null,"C","SL_MSEG2","$$",null,22000,null,23586.288,23586.288,null,null,22000,null,23586.288,23586.288,23586.288,1,{"$nulls":10},0.25,5896.572,1.15,1.1,2,3,"2G","P. Bong"]
["1","03","02","01","","","LN201_0935","1.03.02.01","CBCLN30201","Plant Labor (Crafts)","2007-06-01","2007-12-05",null,"C","SL_MFAT2","Hrs",312,null,27025.12689882353,null,27025.12689882353,null,312,null,27025.12689882353,null,27025.12689882353,17631.366212066692,0.65,9393.760686756843,0.35,{"$nulls":8},0.25,6756.281724705883,1.15,1.1,3,3,"2G","P. Bong"]
["1","03","02","01","","","LN201_0945","1.03.02.01","CBCLN30201","LTU Control Hardware","2007-06-01","2007-10-22",null,"C","SL_CT2","Hrs",700,null,43336.30223366242,null,43336.30223366242,null,700,null,43336.30223366242,null,43336.30223366242,36972.22987767003,0.85,6364.072355992384,0.15,{"$nulls":8},0.25,10834.075558415605,1.15,1.1,4,3,"2G","P. Bong"]
["1","03","02","01","","","LN201_0945","1.03.02.01","CBCLN30201","LTU Control Hardware","2007-06-01","2007-10-22",null,"C","SL_CE2","Hrs",280,null,31662.866627271545,null,31662.866627271545,null,280,null,31662.866627271545,null,31662.866627271545,27013.075024665235,0.85,4649.79160260631,0.15,{"$nulls":8},0.25,7915.716656817886,1.15,1.1,4,3,"2G","P. Bong"]
["1","03","02","01","","","LN201_0950","1.03.02.01","CBCLN30201","LTU Build and Test Equipment Racks","2007-11-15","2008-02-05",null,"C","SL_CT2","Hrs",880,null,55545.34981610577,null,55545.34981610577,null,880,null,55545.34981610577,null,55545.34981610577,null,null,55545.34981610577,1,{"$nulls":8},0.25,13886.337454026443,1.15,1.1,3,3,"2G","P. Bong"]
["1","03","02","01","","","LN201_0950","1.03.02.01","CBCLN30201","LTU Build and Test Equipment Racks","2007-11-15","2008-02-05",null,"C","SL_CP2","Hrs",352,null,29589.285312029202,null,29589.285312029202,null,352,null,29589.285312029202,null,29589.285312029202,null,null,29589.285312029202,1,{"$nulls":8},0.25,7397.3213280073005,1.15,1.1,3,3,"2G","P. Bong"]
["1","03","02","01","","","LN201_0950","1.03.02.01","CBCLN30201","LTU Build and Test Equipment Racks","2007-11-15","2008-02-05",null,"C","SL_CE2","Hrs",238,null,27439.764513087877,null,27439.764513087877,null,238,null,27439.764513087877,null,27439.764513087877,null,null,27439.764513087877,1,{"$nulls":8},0.25,6859.941128271969,1.15,1.1,3,3,"2G","P. Bong"]
["1","03","02","02","  ","  ",null,null,null,"Beam Containment System (BCS)                               ",{"$nulls":6},1766,126200,194564.8910316023,135299.5248,329864.4158316023,null,1766,126200,194564.8910316023,135299.5248,329864.4158316023,297815.2971832557,null,32049.1186483466,null,0,null,0,null,0,null,0,null,null,82466.10395790057,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","02","","","LN202_0010","1.03.02.02","CBBLN30202","Write Certification Procedures","2007-05-01","2007-05-07",null,"C","SL_CE2","Hrs",10,null,1127.0100508919998,null,1127.0100508919998,null,10,null,1127.0100508919998,null,1127.0100508919998,1127.0100508919998,1,{"$nulls":10},0.25,281.75251272299994,1.15,1.1,4,3,"2G","K. Traeger"]
["1","03","02","02","","","LN202_0015","1.03.02.02","CBBLN30202","Write System Documentation","2007-05-01","2007-05-07",null,"C","SL_CE2","Hrs",12,null,1352.4120610704,null,1352.4120610704,null,12,null,1352.4120610704,null,1352.4120610704,1352.4120610704,1,{"$nulls":10},0.25,338.1030152676,1.15,1.1,3,3,"2G","K. Traeger"]
["1","03","02","02","","","LN202_0020","1.03.02.02","CBBLN30202","L02-L03 Controls Software","2007-05-01","2007-05-14",null,"C","SL_CP2","Hrs",110,null,9038.760175962,null,9038.760175962,null,110,null,9038.760175962,null,9038.760175962,9038.760175962,1,{"$nulls":10},0.25,2259.6900439905,1.15,1.1,4,3,"2G","K. Traeger"]
["1","03","02","02","","","LN202_0025","1.03.02.02","CBBLN30202","L02-L03 Control BCS HW Fabrication","2007-05-01","2007-05-07",null,"C","SL_CE2","Hrs",8,null,901.6080407135998,null,901.6080407135998,null,8,null,901.6080407135998,null,901.6080407135998,901.6080407135998,1,{"$nulls":10},0.25,225.40201017839996,1.15,1.1,4,3,"2G","K. Traeger"]
["1","03","02","02","","","LN202_0030","1.03.02.02","CBBLN30202","L02-L03 Controls BCS Integration and Test","2007-05-08","2007-05-14",null,"C","SL_CE2","Hrs",50,null,5635.050254459999,null,5635.050254459999,null,50,null,5635.050254459999,null,5635.050254459999,5635.050254459999,1,{"$nulls":10},0.25,1408.7625636149999,1.15,1.1,3,3,"2G","K. Traeger"]
["1","03","02","02","","","LN202_0110","1.03.02.02","CBCLN30202","Write Certification Procedures","2007-07-02","2007-07-30",null,"C","SL_CE2","Hrs",320,null,36064.32162854399,null,36064.32162854399,null,320,null,36064.32162854399,null,36064.32162854399,36064.32162854399,1,{"$nulls":10},0.25,9016.080407135998,1.15,1.1,4,3,"2G","K. Traeger"]
["1","03","02","02","","","LN202_0115","1.03.02.02","CBCLN30202","Write System Documentation","2007-07-02","2007-07-30",null,"C","SL_CE2","Hrs",96,null,10819.2964885632,null,10819.2964885632,null,96,null,10819.2964885632,null,10819.2964885632,10819.2964885632,1,{"$nulls":10},0.25,2704.8241221408,1.15,1.1,3,3,"2G","K. Traeger"]
["1","03","02","02","","","LN202_0120","1.03.02.02","CBCLN30202","Injector Controls Software","2007-07-02","2007-07-30",null,"C","SL_CP2","Hrs",40,null,3286.8218821680002,null,3286.8218821680002,null,40,null,3286.8218821680002,null,3286.8218821680002,3286.8218821680002,1,{"$nulls":10},0.25,821.7054705420001,1.15,1.1,3,3,"2G","K. Traeger"]
["1","03","02","02","","","LN202_0130","1.03.02.02","CBCLN30202","RCV: 750 Lion Cables","2007-07-31","2007-07-31",null,"C","SL_MSEG2","$$",null,15000,null,16081.56,16081.56,null,null,15000,null,16081.56,16081.56,16081.56,1,{"$nulls":10},0.25,4020.39,1.15,1.1,4,3,"2G","K. Traeger"]
["1","03","02","02","","","LN202_0135","1.03.02.02","CBCLN30202","RCV: 12 PICS","2007-07-31","2007-07-31",null,"C","SL_MSEG2","$$",null,16800,null,18011.3472,18011.3472,null,null,16800,null,18011.3472,18011.3472,18011.3472,1,{"$nulls":10},0.25,4502.8368,1.15,1.1,3,3,"2G","K. Traeger"]
["1","03","02","02","","","LN202_0140","1.03.02.02","CBCLN30202","RCV: 12 Flow Switches","2007-07-31","2007-07-31",null,"C","SL_MSEG2","$$",null,16800,null,18011.3472,18011.3472,null,null,16800,null,18011.3472,18011.3472,18011.3472,1,{"$nulls":10},0.25,4502.8368,1.15,1.1,2,3,"2G","K. Traeger"]
["1","03","02","02","","","LN202_0145","1.03.02.02","CBCLN30202","RCV: 6 Hall Probe and Chassis","2007-07-31","2007-07-31",null,"C","SL_MSEG2","$$",null,36000,null,38595.744,38595.744,null,null,36000,null,38595.744,38595.744,38595.744,1,{"$nulls":10},0.25,9648.936,1.15,1.1,2,3,"2G","K. Traeger"]
["1","03","02","02","","","LN202_0150","1.03.02.02","CBCLN30202","LTU BCS HW Fabrication","2007-08-01","2007-08-28",null,"C","SL_CE2","Hrs",80,null,9016.080407135998,null,9016.080407135998,null,80,null,9016.080407135998,null,9016.080407135998,9016.080407135998,1,{"$nulls":10},0.25,2254.0201017839995,1.15,1.1,4,3,"2G","K. Traeger"]
["1","03","02","02","","","LN202_0155","1.03.02.02","CBCLN30202","LTU BCS Integration and Test","2007-08-29","2007-09-12",null,"C","SL_CE2","Hrs",360,null,40572.361832111994,null,40572.361832111994,null,360,null,40572.361832111994,null,40572.361832111994,40572.361832111994,1,{"$nulls":10},0.25,10143.090458027998,1.15,1.1,3,3,"2G","K. Traeger"]
["1","03","02","02","","","LN202_0210","1.03.02.02","CBDLN30202","Write Certification Procedures","2007-05-01","2007-11-13",null,"C","SL_CE2","Hrs",320,null,36246.29925145537,null,36246.29925145537,null,320,null,36246.29925145537,null,36246.29925145537,28294.305027921793,0.78,7951.994223533576,0.22,{"$nulls":8},0.25,9061.574812863842,1.15,1.1,4,3,"2G","K. Traeger"]
["1","03","02","02","","","LN202_0215","1.03.02.02","CBDLN30202","Write System Documentation","2007-05-01","2007-11-13",null,"C","SL_CE2","Hrs",120,null,13592.362219295765,null,13592.362219295765,null,120,null,13592.362219295765,null,13592.362219295765,10610.364385470673,0.78,2981.997833825091,0.22,{"$nulls":8},0.25,3398.090554823941,1.15,1.1,3,3,"2G","K. Traeger"]
["1","03","02","02","","","LN202_0220","1.03.02.02","CBDLN30202","XTOD Controls Software","2007-05-01","2007-11-13",null,"C","SL_CP2","Hrs",20,null,1651.7034585367146,null,1651.7034585367146,null,20,null,1651.7034585367146,null,1651.7034585367146,1289.3399446740682,0.78,362.3635138626466,0.22,{"$nulls":8},0.25,412.92586463417865,1.15,1.1,6,3,"2G","K. Traeger"]
["1","03","02","02","","","LN202_0230","1.03.02.02","CBDLN30202","RCV: 6 Fault Sensor","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,12600,null,13508.5104,13508.5104,null,null,12600,null,13508.5104,13508.5104,13508.5104,1,{"$nulls":10},0.25,3377.1276,1.15,1.1,3,3,"2G","K. Traeger"]
["1","03","02","02","","","LN202_0235","1.03.02.02","CBDLN30202","RCV: 6 Specialized Electronics","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,21000,null,22514.183999999997,22514.183999999997,null,null,21000,null,22514.183999999997,22514.183999999997,22514.183999999997,1,{"$nulls":10},0.25,5628.545999999999,1.15,1.1,2,3,"2G","K. Traeger"]
["1","03","02","02","","","LN202_0240","1.03.02.02","CBDLN30202","RCV: 1 PLC I/O and Chasis","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,8000,null,8576.832,8576.832,null,null,8000,null,8576.832,8576.832,8576.832,1,{"$nulls":10},0.25,2144.208,1.15,1.1,2,3,"2G","K. Traeger"]
["1","03","02","02","","","LN202_0250","1.03.02.02","CBDLN30202","XTOD H/W Fabrication","2007-05-31","2007-09-21",null,"C","SL_CE2","Hrs",40,null,4508.040203567999,null,4508.040203567999,null,40,null,4508.040203567999,null,4508.040203567999,4508.040203567999,1,{"$nulls":10},0.25,1127.0100508919998,1.15,1.1,4,3,"2G","K. Traeger"]
["1","03","02","02","","","LN202_0255","1.03.02.02","CBDLN30202","Injector Controls BCS Integration and Test","2007-11-14","2008-01-30",null,"C","SL_CE2","Hrs",180,null,20752.763077125284,null,20752.763077125284,null,180,null,20752.763077125284,null,20752.763077125284,null,null,20752.763077125284,1,{"$nulls":8},0.25,5188.190769281321,1.15,1.1,3,3,"2G","K. Traeger"]
["1","03","02","03","  ","  ",null,null,null,"Machine Protection System (MPS)                             ",{"$nulls":6},0,67200,0,72045.3888,72045.3888,null,0,67200,0,72045.3888,72045.3888,72045.3888,null,0,null,0,null,0,null,0,null,0,null,null,32420.42496,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","03","","","LN203_0215","1.03.02.03","CBCLN30203","RCV: 12 Custom Input Electronics","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,50400,null,54034.0416,54034.0416,null,null,50400,null,54034.0416,54034.0416,54034.0416,1,{"$nulls":10},0.45,24315.31872,1.35,1.1,5,3,"2G","A. Tilghman"]
["1","03","02","03","","","LN203_0315","1.03.02.03","CBDLN30203","RCV: 12 Custom Input Electronics","2007-06-29","2007-06-29",null,"C","SL_MSEG2","$$",null,16800,null,18011.3472,18011.3472,null,null,16800,null,18011.3472,18011.3472,18011.3472,1,{"$nulls":10},0.45,8105.10624,1.35,1.1,5,3,"2G","A. Tilghman"]
["1","03","02","04","  ","  ",null,null,null,"Linac Power Conversion Subsystem                            ",{"$nulls":6},15079,1890069,1134024.0931407623,2026387.522763999,3160411.6159047657,null,15079,1890069,1134024.0931407623,2026387.522763999,3160411.6159047657,2684124.7098922455,null,476286.9060125186,null,0,null,0,null,0,null,0,null,null,747621.2308840561,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","01","  ",null,null,null,"Beamline Power Supplies - (Dipole Type)                     ",{"$nulls":6},3004,120260,256523.92440266712,128968.21462800002,385492.1390306671,null,3004,120260,256523.92440266712,128968.21462800002,385492.1390306671,315100.65308128955,null,70391.48594937762,null,0,null,0,null,0,null,0,null,null,90647.22212226674,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","01","01",null,null,null,"Power Supply BX11-14                                        ",{"$nulls":37},"Hamid Shoaee"]
["1","03","02","04","01","02",null,null,null,"Power Supply BX21-24                                        ",{"$nulls":6},62,3460,5194.107670118399,3709.47984,8903.5875101184,null,62,3460,5194.107670118399,3709.47984,8903.5875101184,8903.5875101184,null,0,null,0,null,0,null,0,null,0,null,null,2147.6332855295996,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","01","02","LN40102020","1.03.02.04.01","CBBLN40102","RCV: Transductors","2007-05-15","2007-05-15",null,"C","SL_MSEG2","$$",null,1320,null,1415.1772799999999,1415.1772799999999,null,null,1320,null,1415.1772799999999,1415.1772799999999,1415.1772799999999,1,{"$nulls":10},0.2,283.035456,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","01","02","LN40102030","1.03.02.04.01","CBBLN40102","RCV: PS Controller","2007-05-15","2007-05-15",null,"C","SL_MSEG2","$$",null,2000,null,2144.208,2144.208,null,null,2000,null,2144.208,2144.208,2144.208,1,{"$nulls":10},0.25,536.052,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","02","LN40102040","1.03.02.04.01","CBBLN40102","RCV: Intra-rack Cables and Connectors","2007-05-15","2007-05-15",null,"C","SL_MSEG2","$$",null,40,null,42.884159999999994,42.884159999999994,null,null,40,null,42.884159999999994,42.884159999999994,42.884159999999994,1,{"$nulls":10},0.2,8.576832,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","01","02","LN40102041","1.03.02.04.01","CBBLN40102","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-05-15","2007-05-15",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.2,21.44208,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","02","LN40102045","1.03.02.04.01","CBBLN40102","Bench test and perform safety inspection of PS","2007-05-16","2007-05-17",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","02","LN40102050","1.03.02.04.01","CBBLN40102","Bench test PS Controller","2007-05-16","2007-05-16",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","02","LN40102055","1.03.02.04.01","CBBLN40102","Pre-install Qual Test","2007-05-17","2007-05-21",null,"C","SL_PCE2","Hrs",15,null,1690.5150763379997,null,1690.5150763379997,null,15,null,1690.5150763379997,null,1690.5150763379997,1690.5150763379997,1,{"$nulls":10},0.25,422.62876908449994,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","02","LN40102055","1.03.02.04.01","CBBLN40102","Pre-install Qual Test","2007-05-17","2007-05-21",null,"C","SL_PCCA2","Hrs",15,null,984.5345800619999,null,984.5345800619999,null,15,null,984.5345800619999,null,984.5345800619999,984.5345800619999,1,{"$nulls":10},0.25,246.13364501549998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","02","LN40102060","1.03.02.04.01","CBBLN40102","Integrate cables","2007-05-22","2007-05-22",null,"C","SL_TMUE2","Hrs",16,null,1531.8483839999997,null,1531.8483839999997,null,16,null,1531.8483839999997,null,1531.8483839999997,1531.8483839999997,1,{"$nulls":10},0.25,382.9620959999999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","03",null,null,null,"Kicker Power Supply BXKIK                                   ",{"$nulls":6},1219,8950,107982.4301641655,9595.330799999998,117577.76096416547,null,1219,8950,107982.4301641655,9595.330799999998,117577.76096416547,107927.35118289145,null,9650.409781274015,null,0,null,0,null,0,null,0,null,null,28995.08150104137,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","01","03","LN40103020","1.03.02.04.01","CBBLN4103","Final Design Reviews","2007-05-01","2007-06-15",null,"C","SL_PCE2","Hrs",79,null,8903.379402046798,null,8903.379402046798,null,79,null,8903.379402046798,null,8903.379402046798,8903.379402046798,1,{"$nulls":10},0.25,2225.8448505116994,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","03","LN40103030","1.03.02.04.01","CBBLN4103","Documentation","2007-05-01","2007-07-11",null,"C","SL_PCE2","Hrs",100,null,11270.100508919999,null,11270.100508919999,null,100,null,11270.100508919999,null,11270.100508919999,11270.100508919999,1,{"$nulls":10},0.25,2817.5251272299997,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","03","LN40103065","1.03.02.04.01","CBBLN4103","RCV: PS Controller Hardware","2007-07-12","2007-07-12",null,"C","SL_MSEG2","$$",null,1500,null,1608.156,1608.156,null,null,1500,null,1608.156,1608.156,1608.156,1,{"$nulls":10},0.25,402.039,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","03","LN40103075","1.03.02.04.01","CBBLN4103","RCV:  Analog to Digital Cnvrtr Mods - 16 Ch","2007-07-12","2007-07-12",null,"C","SL_MSEG2","$$",null,3000,null,3216.312,3216.312,null,null,3000,null,3216.312,3216.312,3216.312,1,{"$nulls":10},0.2,643.2624000000001,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","01","03","LN40103080","1.03.02.04.01","CBBLN4103","RCV:  Digital to Analog Cnvrtr Mods - 16 Ch","2007-07-12","2007-07-12",null,"C","SL_MSEG2","$$",null,2200,null,2358.6288,2358.6288,null,null,2200,null,2358.6288,2358.6288,2358.6288,1,{"$nulls":10},0.2,471.72576000000004,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","01","03","LN40103085","1.03.02.04.01","CBBLN4103","RCV:  DIO Module - 8 Chan","2007-07-12","2007-07-12",null,"C","SL_MSEG2","$$",null,500,null,536.052,536.052,null,null,500,null,536.052,536.052,536.052,1,{"$nulls":10},0.2,107.2104,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","01","03","LN40103090","1.03.02.04.01","CBBLN4103","RCV:  IP Carrier Board","2007-07-12","2007-07-12",null,"C","SL_MSEG2","$$",null,800,null,857.6831999999999,857.6831999999999,null,null,800,null,857.6831999999999,857.6831999999999,857.6831999999999,1,{"$nulls":10},0.2,171.53664,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","01","03","LN40103095","1.03.02.04.01","CBBLN4103","RCV:  IO Accessories","2007-07-12","2007-07-12",null,"C","SL_MSEG2","$$",null,350,null,375.2364,375.2364,null,null,350,null,375.2364,375.2364,375.2364,1,{"$nulls":10},0.2,75.04728,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","01","03","LN40103105","1.03.02.04.01","CBBLN4103","RCV:  Intra-rack cables and conectors","2007-09-21","2007-09-21",null,"C","SL_MSEG2","$$",null,500,null,536.052,536.052,null,null,500,null,536.052,536.052,536.052,1,{"$nulls":10},0.2,107.2104,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","01","03","LN40103106","1.03.02.04.01","CBBLN4103","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-09-21","2007-09-21",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.2,21.44208,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","01","03","LN40103110","1.03.02.04.01","CBBLN4103","Fab & Assy- Power Supply","2007-05-01","2007-06-28",null,"C","SL_PCT2","Hrs",168,null,10365.701112043198,null,10365.701112043198,null,168,null,10365.701112043198,null,10365.701112043198,10365.701112043198,1,{"$nulls":10},0.25,2591.4252780107995,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","03","LN40103110","1.03.02.04.01","CBBLN4103","Fab & Assy- Power Supply","2007-05-01","2007-06-28",null,"C","SL_PCE2","Hrs",168,null,18933.768854985596,null,18933.768854985596,null,168,null,18933.768854985596,null,18933.768854985596,18933.768854985596,1,{"$nulls":10},0.25,4733.442213746399,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","03","LN40103110","1.03.02.04.01","CBBLN4103","Fab & Assy- Power Supply","2007-05-01","2007-06-28",null,"C","SL_PCCA2","Hrs",84,null,5513.393648347199,null,5513.393648347199,null,84,null,5513.393648347199,null,5513.393648347199,5513.393648347199,1,{"$nulls":10},0.25,1378.3484120867997,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","03","LN40103115","1.03.02.04.01","CBBLN4103","Fab & Assy- PS Controller","2007-07-13","2007-09-11",null,"C","SL_PCT2","Hrs",168,null,10365.701112043198,null,10365.701112043198,null,168,null,10365.701112043198,null,10365.701112043198,10365.701112043198,1,{"$nulls":10},0.25,2591.4252780107995,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","03","LN40103115","1.03.02.04.01","CBBLN4103","Fab & Assy- PS Controller","2007-07-13","2007-09-11",null,"C","SL_PCE2","Hrs",168,null,18933.768854985596,null,18933.768854985596,null,168,null,18933.768854985596,null,18933.768854985596,18933.768854985596,1,{"$nulls":10},0.25,4733.442213746399,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","03","LN40103115","1.03.02.04.01","CBBLN4103","Fab & Assy- PS Controller","2007-07-13","2007-09-11",null,"C","SL_PCCA2","Hrs",84,null,5513.393648347199,null,5513.393648347199,null,84,null,5513.393648347199,null,5513.393648347199,5513.393648347199,1,{"$nulls":10},0.25,1378.3484120867997,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","03","LN40103120","1.03.02.04.01","CBBLN4103","Pre-install Qual Test","2007-09-12","2007-09-18",null,"C","SL_PCE2","Hrs",30,null,3381.0301526759995,null,3381.0301526759995,null,30,null,3381.0301526759995,null,3381.0301526759995,3381.0301526759995,1,{"$nulls":10},0.25,845.2575381689999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","03","LN40103120","1.03.02.04.01","CBBLN4103","Pre-install Qual Test","2007-09-12","2007-09-18",null,"C","SL_PCCA2","Hrs",30,null,1969.0691601239998,null,1969.0691601239998,null,30,null,1969.0691601239998,null,1969.0691601239998,1969.0691601239998,1,{"$nulls":10},0.25,492.26729003099996,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","03","LN40103125","1.03.02.04.01","CBBLN4103","System Integration Test","2007-09-19","2007-10-30",null,"C","SL_PCE2","Hrs",60,null,6872.067481539067,null,6872.067481539067,null,60,null,6872.067481539067,null,6872.067481539067,2011.3368238650926,0.29,4860.730657673974,0.71,{"$nulls":8},0.25,1718.0168703847667,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","03","LN40103125","1.03.02.04.01","CBBLN4103","System Integration Test","2007-09-19","2007-10-30",null,"C","SL_PCCA2","Hrs",60,null,4002.205107067644,null,4002.205107067644,null,60,null,4002.205107067644,null,4002.205107067644,1171.377104507603,0.29,2830.8280025600407,0.71,{"$nulls":8},0.25,1000.551276766911,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","03","LN40103130","1.03.02.04.01","CBBLN4103","Integrate cables","2007-10-31","2007-11-13",null,"C","SL_TMUE2","Hrs",20,null,1958.85112104,null,1958.85112104,null,20,null,1958.85112104,null,1958.85112104,null,null,1958.85112104,1,{"$nulls":8},0.25,489.71278026,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","04",null,null,null,"Power Supply BX31,32,35,36                                  ",{"$nulls":6},50,37960,4071.5101905983997,40697.067839999996,44768.5780305984,null,50,37960,4071.5101905983997,40697.067839999996,44768.5780305984,44768.5780305984,null,0,null,0,null,0,null,0,null,0,null,null,9264.5015156496,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","01","04","LN40104015","1.03.02.04.01","CBBLN40104","RCV: Power Supply","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,34500,null,36987.587999999996,36987.587999999996,null,null,34500,null,36987.587999999996,36987.587999999996,36987.587999999996,1,{"$nulls":10},0.2,7397.517599999999,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","01","04","LN40104020","1.03.02.04.01","CBBLN40104","RCV: Transductors","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1320,null,1415.1772799999999,1415.1772799999999,null,null,1320,null,1415.1772799999999,1415.1772799999999,1415.1772799999999,1,{"$nulls":10},0.2,283.035456,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","01","04","LN40104030","1.03.02.04.01","CBBLN40104","RCV: PS Controller","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,2000,null,2144.208,2144.208,null,null,2000,null,2144.208,2144.208,2144.208,1,{"$nulls":10},0.25,536.052,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","04","LN40104040","1.03.02.04.01","CBBLN40104","RCV: Intra-rack Cables and Connectors","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,40,null,42.884159999999994,42.884159999999994,null,null,40,null,42.884159999999994,42.884159999999994,42.884159999999994,1,{"$nulls":10},0.2,8.576832,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","01","04","LN40104041","1.03.02.04.01","CBBLN40104","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.2,21.44208,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","04","LN40104045","1.03.02.04.01","CBBLN40104","Bench test and perform safety inspection of PS","2007-05-31","2007-06-01",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","04","LN40104050","1.03.02.04.01","CBBLN40104","Bench test PS Controller","2007-05-31","2007-05-31",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","04","LN40104055","1.03.02.04.01","CBBLN40104","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCE2","Hrs",13,null,1465.1130661595998,null,1465.1130661595998,null,13,null,1465.1130661595998,null,1465.1130661595998,1465.1130661595998,1,{"$nulls":10},0.25,366.27826653989996,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","04","LN40104055","1.03.02.04.01","CBBLN40104","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCCA2","Hrs",13,null,853.2633027203999,null,853.2633027203999,null,13,null,853.2633027203999,null,853.2633027203999,853.2633027203999,1,{"$nulls":10},0.25,213.31582568009998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","04","LN40104060","1.03.02.04.01","CBBLN40104","Integrate cables","2007-09-27","2007-09-27",null,"C","SL_TMUE2","Hrs",8,null,765.9241919999998,null,765.9241919999998,null,8,null,765.9241919999998,null,765.9241919999998,765.9241919999998,1,{"$nulls":10},0.25,191.48104799999996,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","05",null,null,null,"Power Supply -BY1-2                                         ",{"$nulls":6},58,15260,4837.4343825984,16360.30704,21197.741422598403,null,58,15260,4837.4343825984,16360.30704,21197.741422598403,21197.741422598403,null,0,null,0,null,0,null,0,null,0,null,null,4580.053571649601,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","01","05","LN40105015","1.03.02.04.01","CBBLN40105","RCV: Power Supply","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,11800,null,12650.8272,12650.8272,null,null,11800,null,12650.8272,12650.8272,12650.8272,1,{"$nulls":10},0.2,2530.16544,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","01","05","LN40105020","1.03.02.04.01","CBBLN40105","RCV: Transductors","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1320,null,1415.1772799999999,1415.1772799999999,null,null,1320,null,1415.1772799999999,1415.1772799999999,1415.1772799999999,1,{"$nulls":10},0.2,283.035456,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","01","05","LN40105030","1.03.02.04.01","CBBLN40105","RCV: PS Controller","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,2000,null,2144.208,2144.208,null,null,2000,null,2144.208,2144.208,2144.208,1,{"$nulls":10},0.25,536.052,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","05","LN40105040","1.03.02.04.01","CBBLN40105","RCV: Intra-rack Cables and Connectors","2007-08-23","2007-08-23",null,"C","SL_MSEG2","$$",null,40,null,42.884159999999994,42.884159999999994,null,null,40,null,42.884159999999994,42.884159999999994,42.884159999999994,1,{"$nulls":14},1,3,"2G","K. Luchini"]
["1","03","02","04","01","05","LN40105041","1.03.02.04.01","CBBLN40105","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-08-23","2007-08-23",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.2,21.44208,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","05","LN40105045","1.03.02.04.01","CBBLN40105","Bench test and perform safety inspection of PS","2007-05-31","2007-06-01",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","05","LN40105050","1.03.02.04.01","CBBLN40105","Bench test PS Controller","2007-05-31","2007-05-31",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","05","LN40105055","1.03.02.04.01","CBBLN40105","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCE2","Hrs",13,null,1465.1130661595998,null,1465.1130661595998,null,13,null,1465.1130661595998,null,1465.1130661595998,1465.1130661595998,1,{"$nulls":10},0.25,366.27826653989996,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","05","LN40105055","1.03.02.04.01","CBBLN40105","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCCA2","Hrs",13,null,853.2633027203999,null,853.2633027203999,null,13,null,853.2633027203999,null,853.2633027203999,853.2633027203999,1,{"$nulls":10},0.25,213.31582568009998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","05","LN40105060","1.03.02.04.01","CBBLN40105","Integrate cables","2007-08-24","2007-08-24",null,"C","SL_TMUE2","Hrs",16,null,1531.8483839999997,null,1531.8483839999997,null,16,null,1531.8483839999997,null,1531.8483839999997,1531.8483839999997,1,{"$nulls":10},0.25,382.9620959999999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","06",null,null,null,"Kicker Power Supply BYKIK                                   ",{"$nulls":6},1475,8950,122193.9571167056,9632.318387999998,131826.27550470558,null,1475,8950,122193.9571167056,9632.318387999998,131826.27550470558,71085.19933660197,null,60741.07616810359,null,0,null,0,null,0,null,0,null,null,32474.9529567764,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","01","06","LN40106020","1.03.02.04.01","CBBLN40106","Final Design Reviews","2007-05-01","2007-06-15",null,"C","SL_PCE2","Hrs",79,null,8903.379402046798,null,8903.379402046798,null,79,null,8903.379402046798,null,8903.379402046798,8903.379402046798,1,{"$nulls":10},0.25,2225.8448505116994,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","06","LN40106030","1.03.02.04.01","CBBLN40106","Documentation","2007-05-01","2007-09-20",null,"C","SL_PCE2","Hrs",80,null,9016.080407135998,null,9016.080407135998,null,80,null,9016.080407135998,null,9016.080407135998,9016.080407135998,1,{"$nulls":10},0.25,2254.0201017839995,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","06","LN40106065","1.03.02.04.01","CBBLN40106","RCV: PS Controller Hardware","2007-11-07","2007-11-07",null,"C","SL_MSEG2","$$",null,1500,null,1645.1435880000001,1645.1435880000001,null,null,1500,null,1645.1435880000001,1645.1435880000001,null,null,1645.1435880000001,1,{"$nulls":8},0.2,329.02871760000005,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","01","06","LN40106075","1.03.02.04.01","CBBLN40106","RCV:  Analog to Digital Cnvrtr Mods - 16 Ch","2007-07-19","2007-07-19",null,"C","SL_MSEG2","$$",null,3000,null,3216.312,3216.312,null,null,3000,null,3216.312,3216.312,3216.312,1,{"$nulls":10},0.2,643.2624000000001,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","01","06","LN40106080","1.03.02.04.01","CBBLN40106","RCV:  Digital to Analog Cnvrtr Mods - 16 Ch","2007-07-19","2007-07-19",null,"C","SL_MSEG2","$$",null,2200,null,2358.6288,2358.6288,null,null,2200,null,2358.6288,2358.6288,2358.6288,1,{"$nulls":10},0.2,471.72576000000004,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","01","06","LN40106085","1.03.02.04.01","CBBLN40106","RCV:  DIO Module - 8 Chan","2007-07-19","2007-07-19",null,"C","SL_MSEG2","$$",null,500,null,536.052,536.052,null,null,500,null,536.052,536.052,536.052,1,{"$nulls":10},0.2,107.2104,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","01","06","LN40106090","1.03.02.04.01","CBBLN40106","RCV:  IP Carrier Board","2007-07-19","2007-07-19",null,"C","SL_MSEG2","$$",null,800,null,857.6831999999999,857.6831999999999,null,null,800,null,857.6831999999999,857.6831999999999,857.6831999999999,1,{"$nulls":10},0.2,171.53664,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","01","06","LN40106095","1.03.02.04.01","CBBLN40106","RCV:  IO Accessories","2007-07-19","2007-07-19",null,"C","SL_MSEG2","$$",null,350,null,375.2364,375.2364,null,null,350,null,375.2364,375.2364,375.2364,1,{"$nulls":10},0.2,75.04728,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","01","06","LN40106105","1.03.02.04.01","CBBLN40106","RCV:  Intra-rack cables and conectors","2007-09-21","2007-09-21",null,"C","SL_MSEG2","$$",null,500,null,536.052,536.052,null,null,500,null,536.052,536.052,536.052,1,{"$nulls":10},0.2,107.2104,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","01","06","LN40106106","1.03.02.04.01","CBBLN40106","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-09-21","2007-09-21",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.2,21.44208,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","01","06","LN40106110","1.03.02.04.01","CBBLN40106","Fab & Assy- Power Supply","2007-05-01","2007-06-28",null,"C","SL_PCT2","Hrs",336,null,20731.402224086396,null,20731.402224086396,null,336,null,20731.402224086396,null,20731.402224086396,20731.402224086396,1,{"$nulls":10},0.25,5182.850556021599,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","06","LN40106110","1.03.02.04.01","CBBLN40106","Fab & Assy- Power Supply","2007-05-01","2007-06-28",null,"C","SL_PCE2","Hrs",168,null,18933.768854985596,null,18933.768854985596,null,168,null,18933.768854985596,null,18933.768854985596,18933.768854985596,1,{"$nulls":10},0.25,4733.442213746399,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","06","LN40106110","1.03.02.04.01","CBBLN40106","Fab & Assy- Power Supply","2007-05-01","2007-06-28",null,"C","SL_PCCA2","Hrs",84,null,5513.393648347199,null,5513.393648347199,null,84,null,5513.393648347199,null,5513.393648347199,5513.393648347199,1,{"$nulls":10},0.25,1378.3484120867997,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","06","LN40106115","1.03.02.04.01","CBBLN40106","Fab & Assy- PS Controller","2007-11-08","2008-01-25",null,"C","SL_PCT2","Hrs",336,null,21208.224475240386,null,21208.224475240386,null,336,null,21208.224475240386,null,21208.224475240386,null,null,21208.224475240386,1,{"$nulls":8},0.25,5302.056118810096,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","06","LN40106115","1.03.02.04.01","CBBLN40106","Fab & Assy- PS Controller","2007-11-08","2008-01-25",null,"C","SL_PCE2","Hrs",168,null,19369.245538650266,null,19369.245538650266,null,168,null,19369.245538650266,null,19369.245538650266,null,null,19369.245538650266,1,{"$nulls":8},0.25,4842.3113846625665,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","06","LN40106115","1.03.02.04.01","CBBLN40106","Fab & Assy- PS Controller","2007-11-08","2008-01-25",null,"C","SL_PCCA2","Hrs",84,null,5640.201702259185,null,5640.201702259185,null,84,null,5640.201702259185,null,5640.201702259185,null,null,5640.201702259185,1,{"$nulls":8},0.25,1410.0504255647963,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","06","LN40106120","1.03.02.04.01","CBBLN40106","Pre-install Qual Test","2008-01-28","2008-02-01",null,"C","SL_PCE2","Hrs",32,null,3689.3801026000506,null,3689.3801026000506,null,32,null,3689.3801026000506,null,3689.3801026000506,null,null,3689.3801026000506,1,{"$nulls":8},0.25,922.3450256500126,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","06","LN40106120","1.03.02.04.01","CBBLN40106","Pre-install Qual Test","2008-01-28","2008-02-01",null,"C","SL_PCCA2","Hrs",32,null,2148.6482675273087,null,2148.6482675273087,null,32,null,2148.6482675273087,null,2148.6482675273087,null,null,2148.6482675273087,1,{"$nulls":8},0.25,537.1620668818272,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","06","LN40106125","1.03.02.04.01","CBBLN40106","System Integration Test","2008-02-04","2008-03-17",null,"C","SL_PCE2","Hrs",30,null,3458.7938461875474,null,3458.7938461875474,null,30,null,3458.7938461875474,null,3458.7938461875474,null,null,3458.7938461875474,1,{"$nulls":8},0.25,864.6984615468868,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","06","LN40106125","1.03.02.04.01","CBBLN40106","System Integration Test","2008-02-04","2008-03-17",null,"C","SL_PCCA2","Hrs",30,null,2014.357750806852,null,2014.357750806852,null,30,null,2014.357750806852,null,2014.357750806852,null,null,2014.357750806852,1,{"$nulls":8},0.25,503.589437701713,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","06","LN40106130","1.03.02.04.01","CBBLN40106","Integrate cables","2008-03-18","2008-03-31",null,"C","SL_TMUE2","Hrs",16,null,1567.080896832,null,1567.080896832,null,16,null,1567.080896832,null,1567.080896832,null,null,1567.080896832,1,{"$nulls":8},0.25,391.770224208,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","07",null,null,null,"Power Supply BYW1-3                                         ",{"$nulls":6},58,15260,4837.4343825984,16360.30704,21197.741422598403,null,58,15260,4837.4343825984,16360.30704,21197.741422598403,21197.741422598403,null,0,null,0,null,0,null,0,null,0,null,null,4596.1351316496,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","01","07","LN40107015","1.03.02.04.01","CBBLN40107","RCV: Power Supply","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,11800,null,12650.8272,12650.8272,null,null,11800,null,12650.8272,12650.8272,12650.8272,1,{"$nulls":10},0.2,2530.16544,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","01","07","LN40107020","1.03.02.04.01","CBBLN40107","RCV: Transductors","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1320,null,1415.1772799999999,1415.1772799999999,null,null,1320,null,1415.1772799999999,1415.1772799999999,1415.1772799999999,1,{"$nulls":10},0.2,283.035456,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","01","07","LN40107030","1.03.02.04.01","CBBLN40107","RCV: PS Controller","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,2000,null,2144.208,2144.208,null,null,2000,null,2144.208,2144.208,2144.208,1,{"$nulls":10},0.25,536.052,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","07","LN40107040","1.03.02.04.01","CBBLN40107","RCV: Intra-rack Cables and Connectors","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,40,null,42.884159999999994,42.884159999999994,null,null,40,null,42.884159999999994,42.884159999999994,42.884159999999994,1,{"$nulls":10},0.25,10.721039999999999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","07","LN40107041","1.03.02.04.01","CBBLN40107","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.25,26.802599999999998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","07","LN40107045","1.03.02.04.01","CBBLN40107","Bench test and perform safety inspection of PS","2007-05-31","2007-06-01",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","07","LN40107050","1.03.02.04.01","CBBLN40107","Bench test PS Controller","2007-05-31","2007-05-31",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","07","LN40107055","1.03.02.04.01","CBBLN40107","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCE2","Hrs",13,null,1465.1130661595998,null,1465.1130661595998,null,13,null,1465.1130661595998,null,1465.1130661595998,1465.1130661595998,1,{"$nulls":10},0.25,366.27826653989996,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","07","LN40107055","1.03.02.04.01","CBBLN40107","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCCA2","Hrs",13,null,853.2633027203999,null,853.2633027203999,null,13,null,853.2633027203999,null,853.2633027203999,853.2633027203999,1,{"$nulls":10},0.25,213.31582568009998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","07","LN40107060","1.03.02.04.01","CBBLN40107","Integrate cables","2007-09-27","2007-09-27",null,"C","SL_TMUE2","Hrs",16,null,1531.8483839999997,null,1531.8483839999997,null,16,null,1531.8483839999997,null,1531.8483839999997,1531.8483839999997,1,{"$nulls":10},0.25,382.9620959999999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","08",null,null,null,"Muon Spoiler Power Supply MUSPLR                            ",{"$nulls":6},54,15260,4590.6319751688,16360.30704,20950.939015168802,null,54,15260,4590.6319751688,16360.30704,20950.939015168802,20950.939015168802,null,0,null,0,null,0,null,0,null,0,null,null,4526.9298017922,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","01","08","LN40108015","1.03.02.04.01","CBBLN40108","RCV: Power Supply","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,11800,null,12650.8272,12650.8272,null,null,11800,null,12650.8272,12650.8272,12650.8272,1,{"$nulls":10},0.2,2530.16544,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","01","08","LN40108020","1.03.02.04.01","CBBLN40108","1RCV: Transductors","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1320,null,1415.1772799999999,1415.1772799999999,null,null,1320,null,1415.1772799999999,1415.1772799999999,1415.1772799999999,1,{"$nulls":10},0.2,283.035456,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","01","08","LN40108030","1.03.02.04.01","CBBLN40108","RCV: PS Controller","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,2000,null,2144.208,2144.208,null,null,2000,null,2144.208,2144.208,2144.208,1,{"$nulls":10},0.25,536.052,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","08","LN40108040","1.03.02.04.01","CBBLN40108","RCV: Intra-rack Cables and Connectors","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,40,null,42.884159999999994,42.884159999999994,null,null,40,null,42.884159999999994,42.884159999999994,42.884159999999994,1,{"$nulls":10},0.2,8.576832,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","01","08","LN40108041","1.03.02.04.01","CBBLN40108","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.2,21.44208,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","08","LN40108045","1.03.02.04.01","CBBLN40108","Bench test and perform safety inspection of PS","2007-05-31","2007-06-01",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","08","LN40108050","1.03.02.04.01","CBBLN40108","Bench test PS Controller","2007-05-31","2007-05-31",null,"C","SL_PCT2","Hrs",4,null,246.80240742959995,null,246.80240742959995,null,4,null,246.80240742959995,null,246.80240742959995,246.80240742959995,1,{"$nulls":10},0.25,61.70060185739999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","08","LN40108055","1.03.02.04.01","CBBLN40108","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCE2","Hrs",13,null,1465.1130661595998,null,1465.1130661595998,null,13,null,1465.1130661595998,null,1465.1130661595998,1465.1130661595998,1,{"$nulls":10},0.25,366.27826653989996,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","08","LN40108055","1.03.02.04.01","CBBLN40108","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCCA2","Hrs",13,null,853.2633027203999,null,853.2633027203999,null,13,null,853.2633027203999,null,853.2633027203999,853.2633027203999,1,{"$nulls":10},0.25,213.31582568009998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","08","LN40108060","1.03.02.04.01","CBBLN40108","Integrate cables","2007-09-27","2007-09-27",null,"C","SL_TMUE2","Hrs",16,null,1531.8483839999997,null,1531.8483839999997,null,16,null,1531.8483839999997,null,1531.8483839999997,1531.8483839999997,1,{"$nulls":10},0.25,382.9620959999999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","09",null,null,null,"Powe Supply BYD1-3                                          ",{"$nulls":6},28,15160,2816.4185207135997,16253.09664,19069.5151607136,null,28,15160,2816.4185207135997,16253.09664,19069.5151607136,19069.5151607136,null,0,null,0,null,0,null,0,null,0,null,null,4061.9343581784,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","01","09","LN40109015","1.03.02.04.01","CBBLN40109","RCV: Power Supply","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,11800,null,12650.8272,12650.8272,null,null,11800,null,12650.8272,12650.8272,12650.8272,1,{"$nulls":10},0.2,2530.16544,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","01","09","LN40109020","1.03.02.04.01","CBBLN40109","RCV: Transductors","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1320,null,1415.1772799999999,1415.1772799999999,null,null,1320,null,1415.1772799999999,1415.1772799999999,1415.1772799999999,1,{"$nulls":10},0.2,283.035456,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","01","09","LN40109030","1.03.02.04.01","CBBLN40109","RCV: PS Controller","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,2000,null,2144.208,2144.208,null,null,2000,null,2144.208,2144.208,2144.208,1,{"$nulls":10},0.25,536.052,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","09","LN40109040","1.03.02.04.01","CBBLN40109","RCV: Intra-rack Cables and Connectors","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,40,null,42.884159999999994,42.884159999999994,null,null,40,null,42.884159999999994,42.884159999999994,42.884159999999994,1,{"$nulls":10},0.2,8.576832,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","01","09","LN40109045","1.03.02.04.01","CBBLN40109","Bench test and perform safety inspection of PS","2007-05-31","2007-06-01",null,"C","SL_TMUE2","Hrs",4,null,382.9620959999999,null,382.9620959999999,null,4,null,382.9620959999999,null,382.9620959999999,382.9620959999999,1,{"$nulls":10},0.25,95.74052399999998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","09","LN40109050","1.03.02.04.01","CBBLN40109","Bench test PS Controller","2007-05-31","2007-05-31",null,"C","SL_PCE2","Hrs",8,null,901.6080407135998,null,901.6080407135998,null,8,null,901.6080407135998,null,901.6080407135998,901.6080407135998,1,{"$nulls":10},0.25,225.40201017839996,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","09","LN40109060","1.03.02.04.01","CBBLN40109","Integrate cables","2007-09-27","2007-09-27",null,"C","SL_TMUE2","Hrs",16,null,1531.8483839999997,null,1531.8483839999997,null,16,null,1531.8483839999997,null,1531.8483839999997,1531.8483839999997,1,{"$nulls":10},0.25,382.9620959999999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","  ",null,null,null,"Beamline Power Supplies - (Quad Type)                       ",{"$nulls":6},1237,437780,102382.13249583251,469345.68911999994,571727.8216158323,null,1237,437780,102382.13249583251,469345.68911999994,571727.8216158323,571189.7353774473,null,538.08623838486,null,0,null,0,null,0,null,0,null,null,120674.41345995816,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","02","06",null,null,null,"Q21201-Q21901 Switch Over                                   ",{"$nulls":37},"Hamid Shoaee"]
["1","03","02","04","02","07",null,null,null,"Q24201-Q24501 Split                                         ",{"$nulls":6},113,48060,10383.538462901997,51525.31823999999,61908.85670290199,null,113,48060,10383.538462901997,51525.31823999999,61908.85670290199,61908.85670290199,null,0,null,0,null,0,null,0,null,0,null,null,11752.061975725499,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","02","07","LN40207015","1.03.02.04.02","CBBLN40207","RCV:  Power Supply  Q24601","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,11800,null,12650.8272,12650.8272,null,null,11800,null,12650.8272,12650.8272,12650.8272,1,{"$nulls":10},0.2,2530.16544,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","07","LN40207016","1.03.02.04.02","CBBLN40207","RCV:  Power Supply  Q24701B","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,11800,null,12650.8272,12650.8272,null,null,11800,null,12650.8272,12650.8272,12650.8272,1,{"$nulls":10},0.2,2530.16544,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","07","LN40207017","1.03.02.04.02","CBBLN40207","RCV:  Power Supply  Q247901B","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,11800,null,12650.8272,12650.8272,null,null,11800,null,12650.8272,12650.8272,12650.8272,1,{"$nulls":10},0.2,2530.16544,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","07","LN40207020","1.03.02.04.02","CBBLN40207","RCV: Transductors","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,3960,null,4245.53184,4245.53184,null,null,3960,null,4245.53184,4245.53184,4245.53184,1,{"$nulls":10},0.2,849.106368,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","07","LN40207030","1.03.02.04.02","CBBLN40207","RCV: Cables 1C/#350  - Q24201-Q24501","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,1500,null,1608.156,1608.156,null,null,1500,null,1608.156,1608.156,1608.156,1,{"$nulls":10},0.2,321.63120000000004,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","07","LN40207031","1.03.02.04.02","CBBLN40207","RCV: Cables 1C/#350 - Q24601","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,3000,null,3216.312,3216.312,null,null,3000,null,3216.312,3216.312,3216.312,1,{"$nulls":10},0.2,643.2624000000001,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","07","LN40207032","1.03.02.04.02","CBBLN40207","RCV: Cables 4/0Cu - Q24701, Q24901","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,4200,null,4502.8368,4502.8368,null,null,4200,null,4502.8368,4502.8368,4502.8368,1,{"$nulls":10},0.2,900.56736,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","07","LN40207045","1.03.02.04.02","CBBLN40207","Bench test and perform safety inspection of PS","2007-05-31","2007-06-01",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","07","LN40207055","1.03.02.04.02","CBBLN40207","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCE2","Hrs",33,null,3719.1331679435993,null,3719.1331679435993,null,33,null,3719.1331679435993,null,3719.1331679435993,3719.1331679435993,1,{"$nulls":10},0.25,929.7832919858998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","07","LN40207055","1.03.02.04.02","CBBLN40207","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCCA2","Hrs",24,null,1575.2553280991997,null,1575.2553280991997,null,24,null,1575.2553280991997,null,1575.2553280991997,1575.2553280991997,1,{"$nulls":10},0.25,393.8138320247999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","07","LN40207060","1.03.02.04.02","CBBLN40207","Integrate cables","2007-09-27","2007-09-27",null,"C","SL_TMUE2","Hrs",48,null,4595.545151999999,null,4595.545151999999,null,48,null,4595.545151999999,null,4595.545151999999,4595.545151999999,1,{"$nulls":14},3,3,"2G","K. Luchini"]
["1","03","02","04","02","08",null,null,null,"Power Supply Q24601                                         ",{"$nulls":37},"Hamid Shoaee"]
["1","03","02","04","02","09",null,null,null,"Power Supply  Q24701A,Q24701B                               ",{"$nulls":37},"Hamid Shoaee"]
["1","03","02","04","02","10",null,null,null,"Power Supply QM21                                           ",{"$nulls":6},48,15260,3945.751163798399,16360.30704,20306.058203798402,null,48,15260,3945.751163798399,16360.30704,20306.058203798402,20306.058203798402,null,0,null,0,null,0,null,0,null,0,null,null,4365.7095989496,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","02","10","LN40210015","1.03.02.04.02","CBBLN40210","RCV: Power Supply","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,11800,null,12650.8272,12650.8272,null,null,11800,null,12650.8272,12650.8272,12650.8272,1,{"$nulls":10},0.2,2530.16544,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","10","LN40210020","1.03.02.04.02","CBBLN40210","RCV: Transductors","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1320,null,1415.1772799999999,1415.1772799999999,null,null,1320,null,1415.1772799999999,1415.1772799999999,1415.1772799999999,1,{"$nulls":10},0.2,283.035456,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","10","LN40210030","1.03.02.04.02","CBBLN40210","RCV: PS Controller","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,2000,null,2144.208,2144.208,null,null,2000,null,2144.208,2144.208,2144.208,1,{"$nulls":10},0.25,536.052,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","10","LN40210040","1.03.02.04.02","CBBLN40210","RCV: Intra-rack Cables and Connectors","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,40,null,42.884159999999994,42.884159999999994,null,null,40,null,42.884159999999994,42.884159999999994,42.884159999999994,1,{"$nulls":10},0.2,8.576832,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","10","LN40210041","1.03.02.04.02","CBBLN40210","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.2,21.44208,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","10","LN40210045","1.03.02.04.02","CBBLN40210","Bench test and perform safety inspection of PS","2007-05-31","2007-06-01",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","10","LN40210050","1.03.02.04.02","CBBLN40210","Bench test PS Controller","2007-05-31","2007-05-31",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","10","LN40210055","1.03.02.04.02","CBBLN40210","Pre-install Qual Test","2007-05-31","2007-06-04",null,"C","SL_PCE2","Hrs",8,null,901.6080407135998,null,901.6080407135998,null,8,null,901.6080407135998,null,901.6080407135998,901.6080407135998,1,{"$nulls":10},0.25,225.40201017839996,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","10","LN40210055","1.03.02.04.02","CBBLN40210","Pre-install Qual Test","2007-05-31","2007-06-04",null,"C","SL_PCCA2","Hrs",8,null,525.0851093663999,null,525.0851093663999,null,8,null,525.0851093663999,null,525.0851093663999,525.0851093663999,1,{"$nulls":10},0.25,131.27127734159998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","10","LN40210060","1.03.02.04.02","CBBLN40210","Integrate cables","2007-09-27","2007-09-27",null,"C","SL_TMUE2","Hrs",16,null,1531.8483839999997,null,1531.8483839999997,null,16,null,1531.8483839999997,null,1531.8483839999997,1531.8483839999997,1,{"$nulls":10},0.25,382.9620959999999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","11",null,null,null,"Power Supply Q24901A,Q24901B                                ",{"$nulls":37},"Hamid Shoaee"]
["1","03","02","04","02","12",null,null,null,"Power Supply QM22                                           ",{"$nulls":6},48,15260,3945.751163798399,16360.30704,20306.058203798402,null,48,15260,3945.751163798399,16360.30704,20306.058203798402,20306.058203798402,null,0,null,0,null,0,null,0,null,0,null,null,4365.7095989496,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","02","12","LN40212015","1.03.02.04.02","CBBLN40212","RCV: Power Supply","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,11800,null,12650.8272,12650.8272,null,null,11800,null,12650.8272,12650.8272,12650.8272,1,{"$nulls":10},0.2,2530.16544,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","12","LN40212020","1.03.02.04.02","CBBLN40212","RCV: Transductors","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1320,null,1415.1772799999999,1415.1772799999999,null,null,1320,null,1415.1772799999999,1415.1772799999999,1415.1772799999999,1,{"$nulls":10},0.2,283.035456,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","12","LN40212030","1.03.02.04.02","CBBLN40212","RCV: PS Controller","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,2000,null,2144.208,2144.208,null,null,2000,null,2144.208,2144.208,2144.208,1,{"$nulls":10},0.25,536.052,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","12","LN40212040","1.03.02.04.02","CBBLN40212","RCV: Intra-rack Cables and Connectors","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,40,null,42.884159999999994,42.884159999999994,null,null,40,null,42.884159999999994,42.884159999999994,42.884159999999994,1,{"$nulls":10},0.2,8.576832,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","12","LN40212041","1.03.02.04.02","CBBLN40212","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.2,21.44208,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","12","LN40212045","1.03.02.04.02","CBBLN40212","Bench test and perform safety inspection of PS","2007-05-31","2007-06-01",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","12","LN40212050","1.03.02.04.02","CBBLN40212","Bench test PS Controller","2007-05-31","2007-05-31",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","12","LN40212055","1.03.02.04.02","CBBLN40212","Pre-install Qual Test","2007-05-31","2007-06-04",null,"C","SL_PCE2","Hrs",8,null,901.6080407135998,null,901.6080407135998,null,8,null,901.6080407135998,null,901.6080407135998,901.6080407135998,1,{"$nulls":10},0.25,225.40201017839996,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","12","LN40212055","1.03.02.04.02","CBBLN40212","Pre-install Qual Test","2007-05-31","2007-06-04",null,"C","SL_PCCA2","Hrs",8,null,525.0851093663999,null,525.0851093663999,null,8,null,525.0851093663999,null,525.0851093663999,525.0851093663999,1,{"$nulls":10},0.25,131.27127734159998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","12","LN40212060","1.03.02.04.02","CBBLN40212","Integrate cables","2007-09-27","2007-09-27",null,"C","SL_TMUE2","Hrs",16,null,1531.8483839999997,null,1531.8483839999997,null,16,null,1531.8483839999997,null,1531.8483839999997,1531.8483839999997,1,{"$nulls":10},0.25,382.9620959999999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","13",null,null,null,"Power Supply Q5                                             ",{"$nulls":6},48,15260,3945.751163798399,16360.30704,20306.058203798402,null,48,15260,3945.751163798399,16360.30704,20306.058203798402,20306.058203798402,null,0,null,0,null,0,null,0,null,0,null,null,4365.7095989496,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","02","13","LN40213015","1.03.02.04.02","CBBLN40213","RCV: Power Supply","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,11800,null,12650.8272,12650.8272,null,null,11800,null,12650.8272,12650.8272,12650.8272,1,{"$nulls":10},0.2,2530.16544,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","13","LN40213020","1.03.02.04.02","CBBLN40213","RCV: Transductors","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1320,null,1415.1772799999999,1415.1772799999999,null,null,1320,null,1415.1772799999999,1415.1772799999999,1415.1772799999999,1,{"$nulls":10},0.2,283.035456,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","13","LN40213030","1.03.02.04.02","CBBLN40213","RCV: PS Controller","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,2000,null,2144.208,2144.208,null,null,2000,null,2144.208,2144.208,2144.208,1,{"$nulls":10},0.25,536.052,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","13","LN40213040","1.03.02.04.02","CBBLN40213","RCV: Intra-rack Cables and Connectors","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,40,null,42.884159999999994,42.884159999999994,null,null,40,null,42.884159999999994,42.884159999999994,42.884159999999994,1,{"$nulls":10},0.2,8.576832,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","13","LN40213041","1.03.02.04.02","CBBLN40213","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.2,21.44208,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","13","LN40213045","1.03.02.04.02","CBBLN40213","Bench test and perform safety inspection of PS","2007-05-31","2007-06-01",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","13","LN40213050","1.03.02.04.02","CBBLN40213","Bench test PS Controller","2007-05-31","2007-05-31",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","13","LN40213055","1.03.02.04.02","CBBLN40213","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCE2","Hrs",8,null,901.6080407135998,null,901.6080407135998,null,8,null,901.6080407135998,null,901.6080407135998,901.6080407135998,1,{"$nulls":10},0.25,225.40201017839996,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","13","LN40213055","1.03.02.04.02","CBBLN40213","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCCA2","Hrs",8,null,525.0851093663999,null,525.0851093663999,null,8,null,525.0851093663999,null,525.0851093663999,525.0851093663999,1,{"$nulls":10},0.25,131.27127734159998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","13","LN40213060","1.03.02.04.02","CBBLN40213","Integrate cables","2007-09-27","2007-09-27",null,"C","SL_TMUE2","Hrs",16,null,1531.8483839999997,null,1531.8483839999997,null,16,null,1531.8483839999997,null,1531.8483839999997,1531.8483839999997,1,{"$nulls":10},0.25,382.9620959999999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","14",null,null,null,"Power Supply Q6                                             ",{"$nulls":6},48,15260,3945.751163798399,16360.30704,20306.058203798402,null,48,15260,3945.751163798399,16360.30704,20306.058203798402,20306.058203798402,null,0,null,0,null,0,null,0,null,0,null,null,4365.7095989496,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","02","14","LN40214015","1.03.02.04.02","CBBLN40214","RCV: Power Supply","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,11800,null,12650.8272,12650.8272,null,null,11800,null,12650.8272,12650.8272,12650.8272,1,{"$nulls":10},0.2,2530.16544,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","14","LN40214020","1.03.02.04.02","CBBLN40214","RCV: Transductors","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1320,null,1415.1772799999999,1415.1772799999999,null,null,1320,null,1415.1772799999999,1415.1772799999999,1415.1772799999999,1,{"$nulls":10},0.2,283.035456,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","14","LN40214030","1.03.02.04.02","CBBLN40214","RCV: PS Controller","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,2000,null,2144.208,2144.208,null,null,2000,null,2144.208,2144.208,2144.208,1,{"$nulls":10},0.25,536.052,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","14","LN40214040","1.03.02.04.02","CBBLN40214","RCV: Intra-rack Cables and Connectors","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,40,null,42.884159999999994,42.884159999999994,null,null,40,null,42.884159999999994,42.884159999999994,42.884159999999994,1,{"$nulls":10},0.2,8.576832,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","14","LN40214041","1.03.02.04.02","CBBLN40214","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.2,21.44208,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","14","LN40214045","1.03.02.04.02","CBBLN40214","Bench test and perform safety inspection of PS","2007-05-31","2007-06-01",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","14","LN40214050","1.03.02.04.02","CBBLN40214","Bench test PS Controller","2007-05-31","2007-05-31",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","14","LN40214055","1.03.02.04.02","CBBLN40214","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCE2","Hrs",8,null,901.6080407135998,null,901.6080407135998,null,8,null,901.6080407135998,null,901.6080407135998,901.6080407135998,1,{"$nulls":10},0.25,225.40201017839996,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","14","LN40214055","1.03.02.04.02","CBBLN40214","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCCA2","Hrs",8,null,525.0851093663999,null,525.0851093663999,null,8,null,525.0851093663999,null,525.0851093663999,525.0851093663999,1,{"$nulls":10},0.25,131.27127734159998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","14","LN40214060","1.03.02.04.02","CBBLN40214","Integrate cables","2007-09-27","2007-09-27",null,"C","SL_TMUE2","Hrs",16,null,1531.8483839999997,null,1531.8483839999997,null,16,null,1531.8483839999997,null,1531.8483839999997,1531.8483839999997,1,{"$nulls":10},0.25,382.9620959999999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","15",null,null,null,"Power Supply QA0                                            ",{"$nulls":6},48,15260,3945.751163798399,16360.30704,20306.058203798402,null,48,15260,3945.751163798399,16360.30704,20306.058203798402,20306.058203798402,null,0,null,0,null,0,null,0,null,0,null,null,4365.7095989496,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","02","15","LN40215015","1.03.02.04.02","CBBLN40215","RCV: Power Supply","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,11800,null,12650.8272,12650.8272,null,null,11800,null,12650.8272,12650.8272,12650.8272,1,{"$nulls":10},0.2,2530.16544,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","15","LN40215020","1.03.02.04.02","CBBLN40215","RCV: Transductors","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1320,null,1415.1772799999999,1415.1772799999999,null,null,1320,null,1415.1772799999999,1415.1772799999999,1415.1772799999999,1,{"$nulls":10},0.2,283.035456,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","15","LN40215030","1.03.02.04.02","CBBLN40215","RCV: PS Controller","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,2000,null,2144.208,2144.208,null,null,2000,null,2144.208,2144.208,2144.208,1,{"$nulls":10},0.25,536.052,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","15","LN40215040","1.03.02.04.02","CBBLN40215","RCV: Intra-rack Cables and Connectors","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,40,null,42.884159999999994,42.884159999999994,null,null,40,null,42.884159999999994,42.884159999999994,42.884159999999994,1,{"$nulls":10},0.2,8.576832,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","15","LN40215041","1.03.02.04.02","CBBLN40215","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.2,21.44208,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","15","LN40215045","1.03.02.04.02","CBBLN40215","Bench test and perform safety inspection of PS","2007-05-31","2007-06-01",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","15","LN40215050","1.03.02.04.02","CBBLN40215","Bench test PS Controller","2007-05-31","2007-05-31",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","15","LN40215055","1.03.02.04.02","CBBLN40215","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCE2","Hrs",8,null,901.6080407135998,null,901.6080407135998,null,8,null,901.6080407135998,null,901.6080407135998,901.6080407135998,1,{"$nulls":10},0.25,225.40201017839996,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","15","LN40215055","1.03.02.04.02","CBBLN40215","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCCA2","Hrs",8,null,525.0851093663999,null,525.0851093663999,null,8,null,525.0851093663999,null,525.0851093663999,525.0851093663999,1,{"$nulls":10},0.25,131.27127734159998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","15","LN40215060","1.03.02.04.02","CBBLN40215","Integrate cables","2007-09-27","2007-09-27",null,"C","SL_TMUE2","Hrs",16,null,1531.8483839999997,null,1531.8483839999997,null,16,null,1531.8483839999997,null,1531.8483839999997,1531.8483839999997,1,{"$nulls":10},0.25,382.9620959999999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","16",null,null,null,"Power Supply Q50Q1,Q50Q2,Q50Q3                              ",{"$nulls":6},48,15260,3945.751163798399,16360.30704,20306.058203798402,null,48,15260,3945.751163798399,16360.30704,20306.058203798402,20306.058203798402,null,0,null,0,null,0,null,0,null,0,null,null,4365.7095989496,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","02","16","LN40216015","1.03.02.04.02","CBBLN40216","RCV: Power Supply","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,11800,null,12650.8272,12650.8272,null,null,11800,null,12650.8272,12650.8272,12650.8272,1,{"$nulls":10},0.2,2530.16544,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","16","LN40216020","1.03.02.04.02","CBBLN40216","RCV: Transductors","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1320,null,1415.1772799999999,1415.1772799999999,null,null,1320,null,1415.1772799999999,1415.1772799999999,1415.1772799999999,1,{"$nulls":10},0.2,283.035456,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","16","LN40216030","1.03.02.04.02","CBBLN40216","RCV: PS Controller","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,2000,null,2144.208,2144.208,null,null,2000,null,2144.208,2144.208,2144.208,1,{"$nulls":10},0.25,536.052,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","16","LN40216040","1.03.02.04.02","CBBLN40216","RCV: Intra-rack Cables and Connectors","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,40,null,42.884159999999994,42.884159999999994,null,null,40,null,42.884159999999994,42.884159999999994,42.884159999999994,1,{"$nulls":10},0.2,8.576832,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","16","LN40216041","1.03.02.04.02","CBBLN40216","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.2,21.44208,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","16","LN40216045","1.03.02.04.02","CBBLN40216","Bench test and perform safety inspection of PS","2007-05-31","2007-06-01",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","16","LN40216050","1.03.02.04.02","CBBLN40216","Bench test PS Controller","2007-05-31","2007-05-31",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","16","LN40216055","1.03.02.04.02","CBBLN40216","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCE2","Hrs",8,null,901.6080407135998,null,901.6080407135998,null,8,null,901.6080407135998,null,901.6080407135998,901.6080407135998,1,{"$nulls":10},0.25,225.40201017839996,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","16","LN40216055","1.03.02.04.02","CBBLN40216","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCCA2","Hrs",8,null,525.0851093663999,null,525.0851093663999,null,8,null,525.0851093663999,null,525.0851093663999,525.0851093663999,1,{"$nulls":10},0.25,131.27127734159998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","16","LN40216060","1.03.02.04.02","CBBLN40216","Integrate cables","2007-09-27","2007-09-27",null,"C","SL_TMUE2","Hrs",16,null,1531.8483839999997,null,1531.8483839999997,null,16,null,1531.8483839999997,null,1531.8483839999997,1531.8483839999997,1,{"$nulls":10},0.25,382.9620959999999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","17",null,null,null,"Power Supply  QVM1                                          ",{"$nulls":6},56,15260,4439.355978657599,16360.30704,20799.6630186576,null,56,15260,4439.355978657599,16360.30704,20799.6630186576,20799.6630186576,null,0,null,0,null,0,null,0,null,0,null,null,4489.110802664401,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","02","17","LN40217015","1.03.02.04.02","CBBLN40217","RCV: Power Supply","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,11800,null,12650.8272,12650.8272,null,null,11800,null,12650.8272,12650.8272,12650.8272,1,{"$nulls":10},0.2,2530.16544,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","17","LN40217020","1.03.02.04.02","CBBLN40217","RCV: Transductors","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1320,null,1415.1772799999999,1415.1772799999999,null,null,1320,null,1415.1772799999999,1415.1772799999999,1415.1772799999999,1,{"$nulls":10},0.2,283.035456,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","17","LN40217030","1.03.02.04.02","CBBLN40217","RCV: PS Controller","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,2000,null,2144.208,2144.208,null,null,2000,null,2144.208,2144.208,2144.208,1,{"$nulls":10},0.25,536.052,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","17","LN40217040","1.03.02.04.02","CBBLN40217","RCV: Intra-rack Cables and Connectors","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,40,null,42.884159999999994,42.884159999999994,null,null,40,null,42.884159999999994,42.884159999999994,42.884159999999994,1,{"$nulls":10},0.2,8.576832,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","17","LN40217041","1.03.02.04.02","CBBLN40217","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.2,21.44208,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","17","LN40217045","1.03.02.04.02","CBBLN40217","Bench test and perform safety inspection of PS","2007-05-31","2007-06-01",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","17","LN40217050","1.03.02.04.02","CBBLN40217","Bench test PS Controller","2007-05-31","2007-05-31",null,"C","SL_PCT2","Hrs",16,null,987.2096297183998,null,987.2096297183998,null,16,null,987.2096297183998,null,987.2096297183998,987.2096297183998,1,{"$nulls":10},0.25,246.80240742959995,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","17","LN40217055","1.03.02.04.02","CBBLN40217","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCE2","Hrs",8,null,901.6080407135998,null,901.6080407135998,null,8,null,901.6080407135998,null,901.6080407135998,901.6080407135998,1,{"$nulls":10},0.25,225.40201017839996,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","17","LN40217055","1.03.02.04.02","CBBLN40217","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCCA2","Hrs",8,null,525.0851093663999,null,525.0851093663999,null,8,null,525.0851093663999,null,525.0851093663999,525.0851093663999,1,{"$nulls":10},0.25,131.27127734159998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","17","LN40217060","1.03.02.04.02","CBBLN40217","Integrate cables","2007-09-27","2007-09-27",null,"C","SL_TMUE2","Hrs",16,null,1531.8483839999997,null,1531.8483839999997,null,16,null,1531.8483839999997,null,1531.8483839999997,1531.8483839999997,1,{"$nulls":10},0.25,382.9620959999999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","18",null,null,null,"Power Supply  QVM2                                          ",{"$nulls":6},48,13260,3945.751163798399,14216.09904,18161.8502037984,null,48,13260,3945.751163798399,14216.09904,18161.8502037984,18161.8502037984,null,0,null,0,null,0,null,0,null,0,null,null,3829.6575989496,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","02","18","LN40218015","1.03.02.04.02","CBBLN40218","RCV: Power Supply","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,11800,null,12650.8272,12650.8272,null,null,11800,null,12650.8272,12650.8272,12650.8272,1,{"$nulls":10},0.2,2530.16544,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","18","LN40218020","1.03.02.04.02","CBBLN40218","RCV: Transductors","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1320,null,1415.1772799999999,1415.1772799999999,null,null,1320,null,1415.1772799999999,1415.1772799999999,1415.1772799999999,1,{"$nulls":10},0.2,283.035456,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","18","LN40218040","1.03.02.04.02","CBBLN40218","RCV: Intra-rack Cables and Connectors","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,40,null,42.884159999999994,42.884159999999994,null,null,40,null,42.884159999999994,42.884159999999994,42.884159999999994,1,{"$nulls":10},0.2,8.576832,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","18","LN40218041","1.03.02.04.02","CBBLN40218","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.2,21.44208,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","18","LN40218045","1.03.02.04.02","CBBLN40218","Bench test and perform safety inspection of PS","2007-05-31","2007-06-01",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","18","LN40218050","1.03.02.04.02","CBBLN40218","Bench test PS Controller","2007-05-31","2007-05-31",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","18","LN40218055","1.03.02.04.02","CBBLN40218","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCE2","Hrs",8,null,901.6080407135998,null,901.6080407135998,null,8,null,901.6080407135998,null,901.6080407135998,901.6080407135998,1,{"$nulls":10},0.25,225.40201017839996,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","18","LN40218055","1.03.02.04.02","CBBLN40218","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCCA2","Hrs",8,null,525.0851093663999,null,525.0851093663999,null,8,null,525.0851093663999,null,525.0851093663999,525.0851093663999,1,{"$nulls":10},0.25,131.27127734159998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","18","LN40218060","1.03.02.04.02","CBBLN40218","Integrate cables","2007-09-27","2007-09-27",null,"C","SL_TMUE2","Hrs",16,null,1531.8483839999997,null,1531.8483839999997,null,16,null,1531.8483839999997,null,1531.8483839999997,1531.8483839999997,1,{"$nulls":10},0.25,382.9620959999999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","19",null,null,null,"Power Supply  QVM3                                          ",{"$nulls":6},48,15260,3945.751163798399,16360.30704,20306.058203798402,null,48,15260,3945.751163798399,16360.30704,20306.058203798402,20306.058203798402,null,0,null,0,null,0,null,0,null,0,null,null,4365.7095989496,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","02","19","LN40219015","1.03.02.04.02","CBBLN40219","RCV: Power Supply","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,11800,null,12650.8272,12650.8272,null,null,11800,null,12650.8272,12650.8272,12650.8272,1,{"$nulls":10},0.2,2530.16544,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","19","LN40219020","1.03.02.04.02","CBBLN40219","RCV: Transductors","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1320,null,1415.1772799999999,1415.1772799999999,null,null,1320,null,1415.1772799999999,1415.1772799999999,1415.1772799999999,1,{"$nulls":10},0.2,283.035456,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","19","LN40219030","1.03.02.04.02","CBBLN40219","RCV: PS Controller","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,2000,null,2144.208,2144.208,null,null,2000,null,2144.208,2144.208,2144.208,1,{"$nulls":10},0.25,536.052,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","19","LN40219040","1.03.02.04.02","CBBLN40219","RCV: Intra-rack Cables and Connectors","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,40,null,42.884159999999994,42.884159999999994,null,null,40,null,42.884159999999994,42.884159999999994,42.884159999999994,1,{"$nulls":10},0.2,8.576832,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","19","LN40219041","1.03.02.04.02","CBBLN40219","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.2,21.44208,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","19","LN40219045","1.03.02.04.02","CBBLN40219","Bench test and perform safety inspection of PS","2007-05-31","2007-06-01",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","19","LN40219050","1.03.02.04.02","CBBLN40219","Bench test PS Controller","2007-05-31","2007-05-31",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","19","LN40219055","1.03.02.04.02","CBBLN40219","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCE2","Hrs",8,null,901.6080407135998,null,901.6080407135998,null,8,null,901.6080407135998,null,901.6080407135998,901.6080407135998,1,{"$nulls":10},0.25,225.40201017839996,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","19","LN40219055","1.03.02.04.02","CBBLN40219","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCCA2","Hrs",8,null,525.0851093663999,null,525.0851093663999,null,8,null,525.0851093663999,null,525.0851093663999,525.0851093663999,1,{"$nulls":10},0.25,131.27127734159998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","19","LN40219060","1.03.02.04.02","CBBLN40219","Integrate cables","2007-09-27","2007-09-27",null,"C","SL_TMUE2","Hrs",16,null,1531.8483839999997,null,1531.8483839999997,null,16,null,1531.8483839999997,null,1531.8483839999997,1531.8483839999997,1,{"$nulls":10},0.25,382.9620959999999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","20",null,null,null,"Power Supply  QVM4                                          ",{"$nulls":6},48,13260,3945.751163798399,14216.09904,18161.8502037984,null,48,13260,3945.751163798399,14216.09904,18161.8502037984,18161.8502037984,null,0,null,0,null,0,null,0,null,0,null,null,3829.6575989496,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","02","20","LN40220015","1.03.02.04.02","CBBLN40220","RCV: Power Supply","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,11800,null,12650.8272,12650.8272,null,null,11800,null,12650.8272,12650.8272,12650.8272,1,{"$nulls":10},0.2,2530.16544,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","20","LN40220020","1.03.02.04.02","CBBLN40220","RCV: Transductors","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1320,null,1415.1772799999999,1415.1772799999999,null,null,1320,null,1415.1772799999999,1415.1772799999999,1415.1772799999999,1,{"$nulls":10},0.2,283.035456,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","20","LN40220040","1.03.02.04.02","CBBLN40220","RCV: Intra-rack Cables and Connectors","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,40,null,42.884159999999994,42.884159999999994,null,null,40,null,42.884159999999994,42.884159999999994,42.884159999999994,1,{"$nulls":10},0.2,8.576832,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","20","LN40220041","1.03.02.04.02","CBBLN40220","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.2,21.44208,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","20","LN40220045","1.03.02.04.02","CBBLN40220","Bench test and perform safety inspection of PS","2007-05-31","2007-06-01",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","20","LN40220050","1.03.02.04.02","CBBLN40220","Bench test PS Controller","2007-05-01","2007-05-01",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","20","LN40220055","1.03.02.04.02","CBBLN40220","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCE2","Hrs",8,null,901.6080407135998,null,901.6080407135998,null,8,null,901.6080407135998,null,901.6080407135998,901.6080407135998,1,{"$nulls":10},0.25,225.40201017839996,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","20","LN40220055","1.03.02.04.02","CBBLN40220","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCCA2","Hrs",8,null,525.0851093663999,null,525.0851093663999,null,8,null,525.0851093663999,null,525.0851093663999,525.0851093663999,1,{"$nulls":10},0.25,131.27127734159998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","20","LN40220060","1.03.02.04.02","CBBLN40220","Integrate cables","2007-09-27","2007-09-27",null,"C","SL_TMUE2","Hrs",16,null,1531.8483839999997,null,1531.8483839999997,null,16,null,1531.8483839999997,null,1531.8483839999997,1531.8483839999997,1,{"$nulls":10},0.25,382.9620959999999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","21",null,null,null,"Power Supply  QVB1-3                                        ",{"$nulls":6},48,3460,3953.9546494113592,3709.47984,7663.43448941136,null,48,3460,3953.9546494113592,3709.47984,7663.43448941136,7304.710330488119,null,358.72415892324,null,0,null,0,null,0,null,0,null,null,1837.59503035284,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","02","21","LN40221020","1.03.02.04.02","CBBLN40221","RCV: Transductors","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1320,null,1415.1772799999999,1415.1772799999999,null,null,1320,null,1415.1772799999999,1415.1772799999999,1415.1772799999999,1,{"$nulls":10},0.2,283.035456,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","21","LN40221030","1.03.02.04.02","CBBLN40221","RCV: PS Controller","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,2000,null,2144.208,2144.208,null,null,2000,null,2144.208,2144.208,2144.208,1,{"$nulls":10},0.25,536.052,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","21","LN40221040","1.03.02.04.02","CBBLN40221","RCV: Intra-rack Cables and Connectors","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,40,null,42.884159999999994,42.884159999999994,null,null,40,null,42.884159999999994,42.884159999999994,42.884159999999994,1,{"$nulls":10},0.2,8.576832,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","21","LN40221041","1.03.02.04.02","CBBLN40221","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.2,21.44208,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","21","LN40221045","1.03.02.04.02","CBBLN40221","Bench test and perform safety inspection of PS","2007-05-31","2007-06-01",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","21","LN40221050","1.03.02.04.02","CBBLN40221","Bench test PS Controller","2007-09-27","2007-09-27",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","21","LN40221055","1.03.02.04.02","CBBLN40221","Pre-install Qual Test","2007-09-28","2007-10-02",null,"C","SL_PCE2","Hrs",8,null,906.7922869477031,null,906.7922869477031,null,8,null,906.7922869477031,null,906.7922869477031,680.0942152107773,0.75,226.69807173692578,0.25,{"$nulls":8},0.25,226.69807173692578,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","21","LN40221055","1.03.02.04.02","CBBLN40221","Pre-install Qual Test","2007-09-28","2007-10-02",null,"C","SL_PCCA2","Hrs",8,null,528.1043487452567,null,528.1043487452567,null,8,null,528.1043487452567,null,528.1043487452567,396.0782615589426,0.75,132.0260871863142,0.25,{"$nulls":8},0.25,132.0260871863142,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","21","LN40221060","1.03.02.04.02","CBBLN40221","Integrate cables","2007-09-27","2007-09-27",null,"C","SL_TMUE2","Hrs",16,null,1531.8483839999997,null,1531.8483839999997,null,16,null,1531.8483839999997,null,1531.8483839999997,1531.8483839999997,1,{"$nulls":10},0.25,382.9620959999999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","22",null,null,null,"Power Supply  QDL31-34                                      ",{"$nulls":6},48,27260,3945.751163798399,29225.55504,33171.3062037984,null,48,27260,3945.751163798399,29225.55504,33171.3062037984,33171.3062037984,null,0,null,0,null,0,null,0,null,0,null,null,6938.759198949599,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","02","22","LN40222015","1.03.02.04.02","CBBLN40222","RCV: Power Supply","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,23800,null,25516.0752,25516.0752,null,null,23800,null,25516.0752,25516.0752,25516.0752,1,{"$nulls":10},0.2,5103.21504,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","22","LN40222020","1.03.02.04.02","CBBLN40222","RCV: Transductors","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1320,null,1415.1772799999999,1415.1772799999999,null,null,1320,null,1415.1772799999999,1415.1772799999999,1415.1772799999999,1,{"$nulls":10},0.2,283.035456,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","22","LN40222030","1.03.02.04.02","CBBLN40222","RCV: PS Controller","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,2000,null,2144.208,2144.208,null,null,2000,null,2144.208,2144.208,2144.208,1,{"$nulls":10},0.25,536.052,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","22","LN40222040","1.03.02.04.02","CBBLN40222","RCV: Intra-rack Cables and Connectors","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,40,null,42.884159999999994,42.884159999999994,null,null,40,null,42.884159999999994,42.884159999999994,42.884159999999994,1,{"$nulls":10},0.2,8.576832,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","22","LN40222041","1.03.02.04.02","CBBLN40222","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.2,21.44208,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","22","LN40222045","1.03.02.04.02","CBBLN40222","Bench test and perform safety inspection of PS","2007-05-31","2007-06-01",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","22","LN40222050","1.03.02.04.02","CBBLN40222","Bench test PS Controller","2007-05-31","2007-05-31",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","22","LN40222055","1.03.02.04.02","CBBLN40222","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCE2","Hrs",8,null,901.6080407135998,null,901.6080407135998,null,8,null,901.6080407135998,null,901.6080407135998,901.6080407135998,1,{"$nulls":10},0.25,225.40201017839996,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","22","LN40222055","1.03.02.04.02","CBBLN40222","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCCA2","Hrs",8,null,525.0851093663999,null,525.0851093663999,null,8,null,525.0851093663999,null,525.0851093663999,525.0851093663999,1,{"$nulls":10},0.25,131.27127734159998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","22","LN40222060","1.03.02.04.02","CBBLN40222","Integrate cables","2007-09-27","2007-09-27",null,"C","SL_TMUE2","Hrs",16,null,1531.8483839999997,null,1531.8483839999997,null,16,null,1531.8483839999997,null,1531.8483839999997,1531.8483839999997,1,{"$nulls":10},0.25,382.9620959999999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","23",null,null,null,"Power Supply  QE31-36                                       ",{"$nulls":6},48,15260,3945.751163798399,16360.30704,20306.058203798402,null,48,15260,3945.751163798399,16360.30704,20306.058203798402,20306.058203798402,null,0,null,0,null,0,null,0,null,0,null,null,4365.7095989496,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","02","23","LN40223015","1.03.02.04.02","CBBLN40223","RCV: Power Supply","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,11800,null,12650.8272,12650.8272,null,null,11800,null,12650.8272,12650.8272,12650.8272,1,{"$nulls":10},0.2,2530.16544,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","23","LN40223020","1.03.02.04.02","CBBLN40223","RCV: Transductors","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1320,null,1415.1772799999999,1415.1772799999999,null,null,1320,null,1415.1772799999999,1415.1772799999999,1415.1772799999999,1,{"$nulls":10},0.2,283.035456,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","23","LN40223030","1.03.02.04.02","CBBLN40223","RCV: PS Controller","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,2000,null,2144.208,2144.208,null,null,2000,null,2144.208,2144.208,2144.208,1,{"$nulls":10},0.25,536.052,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","23","LN40223040","1.03.02.04.02","CBBLN40223","RCV: Intra-rack Cables and Connectors","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,40,null,42.884159999999994,42.884159999999994,null,null,40,null,42.884159999999994,42.884159999999994,42.884159999999994,1,{"$nulls":10},0.2,8.576832,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","23","LN40223041","1.03.02.04.02","CBBLN40223","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.2,21.44208,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","23","LN40223045","1.03.02.04.02","CBBLN40223","Bench test and perform safety inspection of PS","2007-05-31","2007-06-01",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","23","LN40223050","1.03.02.04.02","CBBLN40223","Bench test PS Controller","2007-05-31","2007-05-31",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","23","LN40223055","1.03.02.04.02","CBBLN40223","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCE2","Hrs",8,null,901.6080407135998,null,901.6080407135998,null,8,null,901.6080407135998,null,901.6080407135998,901.6080407135998,1,{"$nulls":10},0.25,225.40201017839996,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","23","LN40223055","1.03.02.04.02","CBBLN40223","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCCA2","Hrs",8,null,525.0851093663999,null,525.0851093663999,null,8,null,525.0851093663999,null,525.0851093663999,525.0851093663999,1,{"$nulls":10},0.25,131.27127734159998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","23","LN40223060","1.03.02.04.02","CBBLN40223","Integrate cables","2007-09-27","2007-09-27",null,"C","SL_TMUE2","Hrs",16,null,1531.8483839999997,null,1531.8483839999997,null,16,null,1531.8483839999997,null,1531.8483839999997,1531.8483839999997,1,{"$nulls":10},0.25,382.9620959999999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","24",null,null,null,"Power Supply  QEM1                                          ",{"$nulls":6},48,15260,3945.751163798399,16360.30704,20306.058203798402,null,48,15260,3945.751163798399,16360.30704,20306.058203798402,20306.058203798402,null,0,null,0,null,0,null,0,null,0,null,null,4365.7095989496,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","02","24","LN40224015","1.03.02.04.02","CBBLN40224","RCV: Power Supply","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,11800,null,12650.8272,12650.8272,null,null,11800,null,12650.8272,12650.8272,12650.8272,1,{"$nulls":10},0.2,2530.16544,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","24","LN40224020","1.03.02.04.02","CBBLN40224","RCV: Transductors","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1320,null,1415.1772799999999,1415.1772799999999,null,null,1320,null,1415.1772799999999,1415.1772799999999,1415.1772799999999,1,{"$nulls":10},0.2,283.035456,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","24","LN40224030","1.03.02.04.02","CBBLN40224","RCV: PS Controller","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,2000,null,2144.208,2144.208,null,null,2000,null,2144.208,2144.208,2144.208,1,{"$nulls":10},0.25,536.052,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","24","LN40224040","1.03.02.04.02","CBBLN40224","RCV: Intra-rack Cables and Connectors","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,40,null,42.884159999999994,42.884159999999994,null,null,40,null,42.884159999999994,42.884159999999994,42.884159999999994,1,{"$nulls":10},0.2,8.576832,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","24","LN40224041","1.03.02.04.02","CBBLN40224","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.2,21.44208,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","24","LN40224045","1.03.02.04.02","CBBLN40224","Bench test and perform safety inspection of PS","2007-05-31","2007-06-01",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","24","LN40224050","1.03.02.04.02","CBBLN40224","Bench test PS Controller","2007-05-31","2007-05-31",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","24","LN40224055","1.03.02.04.02","CBBLN40224","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCE2","Hrs",8,null,901.6080407135998,null,901.6080407135998,null,8,null,901.6080407135998,null,901.6080407135998,901.6080407135998,1,{"$nulls":10},0.25,225.40201017839996,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","24","LN40224055","1.03.02.04.02","CBBLN40224","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCCA2","Hrs",8,null,525.0851093663999,null,525.0851093663999,null,8,null,525.0851093663999,null,525.0851093663999,525.0851093663999,1,{"$nulls":10},0.25,131.27127734159998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","24","LN40224060","1.03.02.04.02","CBBLN40224","Integrate cables","2007-09-27","2007-09-27",null,"C","SL_TMUE2","Hrs",16,null,1531.8483839999997,null,1531.8483839999997,null,16,null,1531.8483839999997,null,1531.8483839999997,1531.8483839999997,1,{"$nulls":10},0.25,382.9620959999999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","25",null,null,null,"Power Supply  QEM2                                          ",{"$nulls":6},48,15260,3945.751163798399,16360.30704,20306.058203798402,null,48,15260,3945.751163798399,16360.30704,20306.058203798402,20306.058203798402,null,0,null,0,null,0,null,0,null,0,null,null,4365.7095989496,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","02","25","LN40225015","1.03.02.04.02","CBBLN40225","RCV: Power Supply","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,11800,null,12650.8272,12650.8272,null,null,11800,null,12650.8272,12650.8272,12650.8272,1,{"$nulls":10},0.2,2530.16544,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","25","LN40225020","1.03.02.04.02","CBBLN40225","RCV: Transductors","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1320,null,1415.1772799999999,1415.1772799999999,null,null,1320,null,1415.1772799999999,1415.1772799999999,1415.1772799999999,1,{"$nulls":10},0.2,283.035456,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","25","LN40225030","1.03.02.04.02","CBBLN40225","RCV: PS Controller","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,2000,null,2144.208,2144.208,null,null,2000,null,2144.208,2144.208,2144.208,1,{"$nulls":10},0.25,536.052,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","25","LN40225040","1.03.02.04.02","CBBLN40225","RCV: Intra-rack Cables and Connectors","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,40,null,42.884159999999994,42.884159999999994,null,null,40,null,42.884159999999994,42.884159999999994,42.884159999999994,1,{"$nulls":10},0.2,8.576832,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","25","LN40225041","1.03.02.04.02","CBBLN40225","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.2,21.44208,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","25","LN40225045","1.03.02.04.02","CBBLN40225","Bench test and perform safety inspection of PS","2007-05-31","2007-06-01",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","25","LN40225050","1.03.02.04.02","CBBLN40225","Bench test PS Controller","2007-05-31","2007-05-31",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","25","LN40225055","1.03.02.04.02","CBBLN40225","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCE2","Hrs",8,null,901.6080407135998,null,901.6080407135998,null,8,null,901.6080407135998,null,901.6080407135998,901.6080407135998,1,{"$nulls":10},0.25,225.40201017839996,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","25","LN40225055","1.03.02.04.02","CBBLN40225","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCCA2","Hrs",8,null,525.0851093663999,null,525.0851093663999,null,8,null,525.0851093663999,null,525.0851093663999,525.0851093663999,1,{"$nulls":10},0.25,131.27127734159998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","25","LN40225060","1.03.02.04.02","CBBLN40225","Integrate cables","2007-09-27","2007-09-27",null,"C","SL_TMUE2","Hrs",16,null,1531.8483839999997,null,1531.8483839999997,null,16,null,1531.8483839999997,null,1531.8483839999997,1531.8483839999997,1,{"$nulls":10},0.25,382.9620959999999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","26",null,null,null,"Power Supply  QEM3                                          ",{"$nulls":6},48,15260,3945.751163798399,16360.30704,20306.058203798402,null,48,15260,3945.751163798399,16360.30704,20306.058203798402,20306.058203798402,null,0,null,0,null,0,null,0,null,0,null,null,4365.7095989496,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","02","26","LN40226015","1.03.02.04.02","CBBLN40226","RCV: Power Supply","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,11800,null,12650.8272,12650.8272,null,null,11800,null,12650.8272,12650.8272,12650.8272,1,{"$nulls":10},0.2,2530.16544,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","26","LN40226020","1.03.02.04.02","CBBLN40226","RCV: Transductors","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1320,null,1415.1772799999999,1415.1772799999999,null,null,1320,null,1415.1772799999999,1415.1772799999999,1415.1772799999999,1,{"$nulls":10},0.2,283.035456,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","26","LN40226030","1.03.02.04.02","CBBLN40226","RCV: PS Controller","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,2000,null,2144.208,2144.208,null,null,2000,null,2144.208,2144.208,2144.208,1,{"$nulls":10},0.25,536.052,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","26","LN40226040","1.03.02.04.02","CBBLN40226","RCV: Intra-rack Cables and Connectors","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,40,null,42.884159999999994,42.884159999999994,null,null,40,null,42.884159999999994,42.884159999999994,42.884159999999994,1,{"$nulls":10},0.2,8.576832,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","26","LN40226041","1.03.02.04.02","CBBLN40226","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.2,21.44208,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","26","LN40226045","1.03.02.04.02","CBBLN40226","Bench test and perform safety inspection of PS","2007-05-31","2007-06-01",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","26","LN40226050","1.03.02.04.02","CBBLN40226","Bench test PS Controller","2007-05-31","2007-05-31",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","26","LN40226055","1.03.02.04.02","CBBLN40226","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCE2","Hrs",8,null,901.6080407135998,null,901.6080407135998,null,8,null,901.6080407135998,null,901.6080407135998,901.6080407135998,1,{"$nulls":10},0.25,225.40201017839996,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","26","LN40226055","1.03.02.04.02","CBBLN40226","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCCA2","Hrs",8,null,525.0851093663999,null,525.0851093663999,null,8,null,525.0851093663999,null,525.0851093663999,525.0851093663999,1,{"$nulls":10},0.25,131.27127734159998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","26","LN40226060","1.03.02.04.02","CBBLN40226","Integrate cables","2007-09-27","2007-09-27",null,"C","SL_TMUE2","Hrs",16,null,1531.8483839999997,null,1531.8483839999997,null,16,null,1531.8483839999997,null,1531.8483839999997,1531.8483839999997,1,{"$nulls":10},0.25,382.9620959999999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","27",null,null,null,"Power Supply  QEM4                                          ",{"$nulls":6},48,15260,3945.751163798399,16360.30704,20306.058203798402,null,48,15260,3945.751163798399,16360.30704,20306.058203798402,20306.058203798402,null,0,null,0,null,0,null,0,null,0,null,null,4365.7095989496,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","02","27","LN40227015","1.03.02.04.02","CBBLN40227","RCV: Power Supply","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,11800,null,12650.8272,12650.8272,null,null,11800,null,12650.8272,12650.8272,12650.8272,1,{"$nulls":10},0.2,2530.16544,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","27","LN40227020","1.03.02.04.02","CBBLN40227","RCV: Transductors","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1320,null,1415.1772799999999,1415.1772799999999,null,null,1320,null,1415.1772799999999,1415.1772799999999,1415.1772799999999,1,{"$nulls":10},0.2,283.035456,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","27","LN40227030","1.03.02.04.02","CBBLN40227","RCV: PS Controller","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,2000,null,2144.208,2144.208,null,null,2000,null,2144.208,2144.208,2144.208,1,{"$nulls":10},0.25,536.052,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","27","LN40227040","1.03.02.04.02","CBBLN40227","RCV: Intra-rack Cables and Connectors","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,40,null,42.884159999999994,42.884159999999994,null,null,40,null,42.884159999999994,42.884159999999994,42.884159999999994,1,{"$nulls":10},0.2,8.576832,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","27","LN40227041","1.03.02.04.02","CBBLN40227","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.2,21.44208,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","27","LN40227045","1.03.02.04.02","CBBLN40227","Bench test and perform safety inspection of PS","2007-05-31","2007-06-01",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","27","LN40227050","1.03.02.04.02","CBBLN40227","Bench test PS Controller","2007-05-31","2007-05-31",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","27","LN40227055","1.03.02.04.02","CBBLN40227","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCE2","Hrs",8,null,901.6080407135998,null,901.6080407135998,null,8,null,901.6080407135998,null,901.6080407135998,901.6080407135998,1,{"$nulls":10},0.25,225.40201017839996,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","27","LN40227055","1.03.02.04.02","CBBLN40227","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCCA2","Hrs",8,null,525.0851093663999,null,525.0851093663999,null,8,null,525.0851093663999,null,525.0851093663999,525.0851093663999,1,{"$nulls":10},0.25,131.27127734159998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","27","LN40227060","1.03.02.04.02","CBBLN40227","Integrate cables","2007-09-27","2007-09-27",null,"C","SL_TMUE2","Hrs",16,null,1531.8483839999997,null,1531.8483839999997,null,16,null,1531.8483839999997,null,1531.8483839999997,1531.8483839999997,1,{"$nulls":10},0.25,382.9620959999999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","28",null,null,null,"Power Supply QT11,13,21,23,31,33,41,43                      ",{"$nulls":6},48,3460,3945.751163798399,3709.47984,7655.231003798399,null,48,3460,3945.751163798399,3709.47984,7655.231003798399,7655.231003798399,null,0,null,0,null,0,null,0,null,0,null,null,1835.5441589495997,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","02","28","LN40228020","1.03.02.04.02","CBBLN40228","RCV: Transductors","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1320,null,1415.1772799999999,1415.1772799999999,null,null,1320,null,1415.1772799999999,1415.1772799999999,1415.1772799999999,1,{"$nulls":10},0.2,283.035456,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","28","LN40228030","1.03.02.04.02","CBBLN40228","RCV: PS Controller","2007-05-01","2007-05-01",null,"C","SL_MSEG2","$$",null,2000,null,2144.208,2144.208,null,null,2000,null,2144.208,2144.208,2144.208,1,{"$nulls":10},0.25,536.052,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","28","LN40228040","1.03.02.04.02","CBBLN40228","RCV: Intra-rack Cables and Connectors","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,40,null,42.884159999999994,42.884159999999994,null,null,40,null,42.884159999999994,42.884159999999994,42.884159999999994,1,{"$nulls":10},0.2,8.576832,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","28","LN40228041","1.03.02.04.02","CBBLN40228","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.2,21.44208,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","28","LN40228045","1.03.02.04.02","CBBLN40228","Bench test and perform safety inspection of PS","2007-05-31","2007-06-01",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","28","LN40228050","1.03.02.04.02","CBBLN40228","Bench test PS Controller","2007-05-02","2007-05-02",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","28","LN40228055","1.03.02.04.02","CBBLN40228","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCE2","Hrs",8,null,901.6080407135998,null,901.6080407135998,null,8,null,901.6080407135998,null,901.6080407135998,901.6080407135998,1,{"$nulls":10},0.25,225.40201017839996,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","28","LN40228055","1.03.02.04.02","CBBLN40228","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCCA2","Hrs",8,null,525.0851093663999,null,525.0851093663999,null,8,null,525.0851093663999,null,525.0851093663999,525.0851093663999,1,{"$nulls":10},0.25,131.27127734159998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","28","LN40228060","1.03.02.04.02","CBBLN40228","Integrate cables","2007-09-27","2007-09-27",null,"C","SL_TMUE2","Hrs",16,null,1531.8483839999997,null,1531.8483839999997,null,16,null,1531.8483839999997,null,1531.8483839999997,1531.8483839999997,1,{"$nulls":10},0.25,382.9620959999999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","29",null,null,null,"Power Supply QT12,22,32,42                                  ",{"$nulls":6},48,25260,3945.751163798399,27081.34704,31027.098203798403,null,48,25260,3945.751163798399,27081.34704,31027.098203798403,31027.098203798403,null,0,null,0,null,0,null,0,null,0,null,null,6509.917598949599,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","02","29","LN40229015","1.03.02.04.02","CBBLN40229","RCV: Power Supply","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,21800,null,23371.8672,23371.8672,null,null,21800,null,23371.8672,23371.8672,23371.8672,1,{"$nulls":10},0.2,4674.37344,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","29","LN40229020","1.03.02.04.02","CBBLN40229","RCV: Transductors","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1320,null,1415.1772799999999,1415.1772799999999,null,null,1320,null,1415.1772799999999,1415.1772799999999,1415.1772799999999,1,{"$nulls":10},0.2,283.035456,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","29","LN40229030","1.03.02.04.02","CBBLN40229","RCV: PS Controller","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,2000,null,2144.208,2144.208,null,null,2000,null,2144.208,2144.208,2144.208,1,{"$nulls":10},0.25,536.052,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","29","LN40229040","1.03.02.04.02","CBBLN40229","RCV: Intra-rack Cables and Connectors","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,40,null,42.884159999999994,42.884159999999994,null,null,40,null,42.884159999999994,42.884159999999994,42.884159999999994,1,{"$nulls":10},0.2,8.576832,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","29","LN40229041","1.03.02.04.02","CBBLN40229","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.2,21.44208,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","29","LN40229045","1.03.02.04.02","CBBLN40229","Bench test and perform safety inspection of PS","2007-05-31","2007-06-01",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","29","LN40229050","1.03.02.04.02","CBBLN40229","Bench test PS Controller","2007-05-31","2007-05-31",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","29","LN40229055","1.03.02.04.02","CBBLN40229","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCE2","Hrs",8,null,901.6080407135998,null,901.6080407135998,null,8,null,901.6080407135998,null,901.6080407135998,901.6080407135998,1,{"$nulls":10},0.25,225.40201017839996,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","29","LN40229055","1.03.02.04.02","CBBLN40229","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCCA2","Hrs",8,null,525.0851093663999,null,525.0851093663999,null,8,null,525.0851093663999,null,525.0851093663999,525.0851093663999,1,{"$nulls":10},0.25,131.27127734159998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","29","LN40229060","1.03.02.04.02","CBBLN40229","Integrate cables","2007-09-27","2007-09-27",null,"C","SL_TMUE2","Hrs",16,null,1531.8483839999997,null,1531.8483839999997,null,16,null,1531.8483839999997,null,1531.8483839999997,1531.8483839999997,1,{"$nulls":10},0.25,382.9620959999999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","30",null,null,null,"Power Supply  QUM1                                          ",{"$nulls":6},48,15260,3945.751163798399,16360.30704,20306.058203798402,null,48,15260,3945.751163798399,16360.30704,20306.058203798402,20306.058203798402,null,0,null,0,null,0,null,0,null,0,null,null,4365.7095989496,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","02","30","LN40230015","1.03.02.04.02","CBBLN40230","RCV: Power Supply","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,11800,null,12650.8272,12650.8272,null,null,11800,null,12650.8272,12650.8272,12650.8272,1,{"$nulls":10},0.2,2530.16544,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","30","LN40230020","1.03.02.04.02","CBBLN40230","RCV: Transductors","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1320,null,1415.1772799999999,1415.1772799999999,null,null,1320,null,1415.1772799999999,1415.1772799999999,1415.1772799999999,1,{"$nulls":10},0.2,283.035456,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","30","LN40230030","1.03.02.04.02","CBBLN40230","RCV: PS Controller","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,2000,null,2144.208,2144.208,null,null,2000,null,2144.208,2144.208,2144.208,1,{"$nulls":10},0.25,536.052,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","30","LN40230040","1.03.02.04.02","CBBLN40230","RCV: Intra-rack Cables and Connectors","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,40,null,42.884159999999994,42.884159999999994,null,null,40,null,42.884159999999994,42.884159999999994,42.884159999999994,1,{"$nulls":10},0.2,8.576832,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","30","LN40230041","1.03.02.04.02","CBBLN40230","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.2,21.44208,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","30","LN40230045","1.03.02.04.02","CBBLN40230","Bench test and perform safety inspection of PS","2007-05-31","2007-06-01",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","30","LN40230050","1.03.02.04.02","CBBLN40230","Bench test PS Controller","2007-05-31","2007-05-31",null,"C","SL_PCT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","30","LN40230055","1.03.02.04.02","CBBLN40230","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCE2","Hrs",8,null,901.6080407135998,null,901.6080407135998,null,8,null,901.6080407135998,null,901.6080407135998,901.6080407135998,1,{"$nulls":10},0.25,225.40201017839996,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","30","LN40230055","1.03.02.04.02","CBBLN40230","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCCA2","Hrs",8,null,525.0851093663999,null,525.0851093663999,null,8,null,525.0851093663999,null,525.0851093663999,525.0851093663999,1,{"$nulls":10},0.25,131.27127734159998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","30","LN40230060","1.03.02.04.02","CBBLN40230","Integrate cables","2007-09-27","2007-09-27",null,"C","SL_TMUE2","Hrs",16,null,1531.8483839999997,null,1531.8483839999997,null,16,null,1531.8483839999997,null,1531.8483839999997,1531.8483839999997,1,{"$nulls":10},0.25,382.9620959999999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","31",null,null,null,"Power Supply  QUM2                                          ",{"$nulls":6},24,13260,1972.8755818991995,14216.09904,16188.974621899199,null,24,13260,1972.8755818991995,14216.09904,16188.974621899199,16188.974621899199,null,0,null,0,null,0,null,0,null,0,null,null,3336.4387034748,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","02","31","LN40231015","1.03.02.04.02","CBBLN40231","RCV: Power Supply","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,11800,null,12650.8272,12650.8272,null,null,11800,null,12650.8272,12650.8272,12650.8272,1,{"$nulls":10},0.2,2530.16544,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","31","LN40231020","1.03.02.04.02","CBBLN40231","RCV: Transductors","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1320,null,1415.1772799999999,1415.1772799999999,null,null,1320,null,1415.1772799999999,1415.1772799999999,1415.1772799999999,1,{"$nulls":10},0.2,283.035456,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","31","LN40231040","1.03.02.04.02","CBBLN40231","RCV: Intra-rack Cables and Connectors","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,40,null,42.884159999999994,42.884159999999994,null,null,40,null,42.884159999999994,42.884159999999994,42.884159999999994,1,{"$nulls":10},0.2,8.576832,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","31","LN40231041","1.03.02.04.02","CBBLN40231","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.2,21.44208,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","31","LN40231045","1.03.02.04.02","CBBLN40231","Bench test and perform safety inspection of PS","2007-05-31","2007-06-01",null,"C","SL_PCT2","Hrs",4,null,246.80240742959995,null,246.80240742959995,null,4,null,246.80240742959995,null,246.80240742959995,246.80240742959995,1,{"$nulls":10},0.25,61.70060185739999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","31","LN40231050","1.03.02.04.02","CBBLN40231","Bench test PS Controller","2007-05-01","2007-05-01",null,"C","SL_PCT2","Hrs",4,null,246.80240742959995,null,246.80240742959995,null,4,null,246.80240742959995,null,246.80240742959995,246.80240742959995,1,{"$nulls":10},0.25,61.70060185739999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","31","LN40231055","1.03.02.04.02","CBBLN40231","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCE2","Hrs",4,null,450.8040203567999,null,450.8040203567999,null,4,null,450.8040203567999,null,450.8040203567999,450.8040203567999,1,{"$nulls":10},0.25,112.70100508919998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","31","LN40231055","1.03.02.04.02","CBBLN40231","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCCA2","Hrs",4,null,262.54255468319997,null,262.54255468319997,null,4,null,262.54255468319997,null,262.54255468319997,262.54255468319997,1,{"$nulls":10},0.25,65.63563867079999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","31","LN40231060","1.03.02.04.02","CBBLN40231","Integrate cables","2007-09-27","2007-09-27",null,"C","SL_TMUE2","Hrs",8,null,765.9241919999998,null,765.9241919999998,null,8,null,765.9241919999998,null,765.9241919999998,765.9241919999998,1,{"$nulls":10},0.25,191.48104799999996,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","32",null,null,null,"Power Supply  QUM3                                          ",{"$nulls":6},24,15260,1972.8755818991995,16360.30704,18333.182621899203,null,24,15260,1972.8755818991995,16360.30704,18333.182621899203,18333.182621899203,null,0,null,0,null,0,null,0,null,0,null,null,3872.4907034748007,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","02","32","LN40232015","1.03.02.04.02","CBBLN40232","RCV: Power Supply","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,11800,null,12650.8272,12650.8272,null,null,11800,null,12650.8272,12650.8272,12650.8272,1,{"$nulls":10},0.2,2530.16544,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","32","LN40232020","1.03.02.04.02","CBBLN40232","RCV: Transductors","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1320,null,1415.1772799999999,1415.1772799999999,null,null,1320,null,1415.1772799999999,1415.1772799999999,1415.1772799999999,1,{"$nulls":10},0.2,283.035456,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","32","LN40232030","1.03.02.04.02","CBBLN40232","RCV: PS Controller","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,2000,null,2144.208,2144.208,null,null,2000,null,2144.208,2144.208,2144.208,1,{"$nulls":10},0.25,536.052,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","32","LN40232040","1.03.02.04.02","CBBLN40232","RCV: Intra-rack Cables and Connectors","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,40,null,42.884159999999994,42.884159999999994,null,null,40,null,42.884159999999994,42.884159999999994,42.884159999999994,1,{"$nulls":10},0.2,8.576832,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","32","LN40232041","1.03.02.04.02","CBBLN40232","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.2,21.44208,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","32","LN40232045","1.03.02.04.02","CBBLN40232","Bench test and perform safety inspection of PS","2007-05-31","2007-06-01",null,"C","SL_PCT2","Hrs",4,null,246.80240742959995,null,246.80240742959995,null,4,null,246.80240742959995,null,246.80240742959995,246.80240742959995,1,{"$nulls":10},0.25,61.70060185739999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","32","LN40232050","1.03.02.04.02","CBBLN40232","Bench test PS Controller","2007-05-31","2007-05-31",null,"C","SL_PCT2","Hrs",4,null,246.80240742959995,null,246.80240742959995,null,4,null,246.80240742959995,null,246.80240742959995,246.80240742959995,1,{"$nulls":10},0.25,61.70060185739999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","32","LN40232055","1.03.02.04.02","CBBLN40232","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCE2","Hrs",4,null,450.8040203567999,null,450.8040203567999,null,4,null,450.8040203567999,null,450.8040203567999,450.8040203567999,1,{"$nulls":10},0.25,112.70100508919998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","32","LN40232055","1.03.02.04.02","CBBLN40232","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCCA2","Hrs",4,null,262.54255468319997,null,262.54255468319997,null,4,null,262.54255468319997,null,262.54255468319997,262.54255468319997,1,{"$nulls":10},0.25,65.63563867079999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","32","LN40232060","1.03.02.04.02","CBBLN40232","Integrate cables","2007-09-27","2007-09-27",null,"C","SL_TMUE2","Hrs",8,null,765.9241919999998,null,765.9241919999998,null,8,null,765.9241919999998,null,765.9241919999998,765.9241919999998,1,{"$nulls":10},0.25,191.48104799999996,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","33",null,null,null,"Power Supply QUM4                                           ",{"$nulls":6},24,15260,1972.8755818991995,16360.30704,18333.182621899203,null,24,15260,1972.8755818991995,16360.30704,18333.182621899203,18333.182621899203,null,0,null,0,null,0,null,0,null,0,null,null,3872.4907034748007,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","02","33","LN40233015","1.03.02.04.02","CBBLN40233","RCV: Power Supply","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,11800,null,12650.8272,12650.8272,null,null,11800,null,12650.8272,12650.8272,12650.8272,1,{"$nulls":10},0.2,2530.16544,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","33","LN40233020","1.03.02.04.02","CBBLN40233","RCV: Transductors","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1320,null,1415.1772799999999,1415.1772799999999,null,null,1320,null,1415.1772799999999,1415.1772799999999,1415.1772799999999,1,{"$nulls":10},0.2,283.035456,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","33","LN40233030","1.03.02.04.02","CBBLN40233","RCV: PS Controller","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,2000,null,2144.208,2144.208,null,null,2000,null,2144.208,2144.208,2144.208,1,{"$nulls":10},0.25,536.052,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","33","LN40233040","1.03.02.04.02","CBBLN40233","RCV: Intra-rackCables and Connectors","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,40,null,42.884159999999994,42.884159999999994,null,null,40,null,42.884159999999994,42.884159999999994,42.884159999999994,1,{"$nulls":10},0.2,8.576832,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","33","LN40233041","1.03.02.04.02","CBBLN40233","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.2,21.44208,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","33","LN40233045","1.03.02.04.02","CBBLN40233","Bench test and perform safety inspection of PS","2007-05-31","2007-06-01",null,"C","SL_PCT2","Hrs",4,null,246.80240742959995,null,246.80240742959995,null,4,null,246.80240742959995,null,246.80240742959995,246.80240742959995,1,{"$nulls":10},0.25,61.70060185739999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","33","LN40233050","1.03.02.04.02","CBBLN40233","Bench test PS Controller","2007-05-31","2007-05-31",null,"C","SL_PCT2","Hrs",4,null,246.80240742959995,null,246.80240742959995,null,4,null,246.80240742959995,null,246.80240742959995,246.80240742959995,1,{"$nulls":10},0.25,61.70060185739999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","33","LN40233055","1.03.02.04.02","CBBLN40233","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCE2","Hrs",4,null,450.8040203567999,null,450.8040203567999,null,4,null,450.8040203567999,null,450.8040203567999,450.8040203567999,1,{"$nulls":10},0.25,112.70100508919998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","33","LN40233055","1.03.02.04.02","CBBLN40233","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCCA2","Hrs",4,null,262.54255468319997,null,262.54255468319997,null,4,null,262.54255468319997,null,262.54255468319997,262.54255468319997,1,{"$nulls":10},0.25,65.63563867079999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","33","LN40233060","1.03.02.04.02","CBBLN40233","Integrate cables","2007-09-27","2007-09-27",null,"C","SL_TMUE2","Hrs",8,null,765.9241919999998,null,765.9241919999998,null,8,null,765.9241919999998,null,765.9241919999998,765.9241919999998,1,{"$nulls":10},0.25,191.48104799999996,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","34",null,null,null,"Power Supply QDMP1-2                                        ",{"$nulls":6},24,15260,1972.8755818991995,16360.30704,18333.182621899203,null,24,15260,1972.8755818991995,16360.30704,18333.182621899203,18333.182621899203,null,0,null,0,null,0,null,0,null,0,null,null,3872.4907034748007,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","02","34","LN40234015","1.03.02.04.02","CBBLN40234","RCV: Power Supply","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,11800,null,12650.8272,12650.8272,null,null,11800,null,12650.8272,12650.8272,12650.8272,1,{"$nulls":10},0.2,2530.16544,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","34","LN40234020","1.03.02.04.02","CBBLN40234","RCV: Transductors","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1320,null,1415.1772799999999,1415.1772799999999,null,null,1320,null,1415.1772799999999,1415.1772799999999,1415.1772799999999,1,{"$nulls":10},0.2,283.035456,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","34","LN40234030","1.03.02.04.02","CBBLN40234","RCV: PS Controller","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,2000,null,2144.208,2144.208,null,null,2000,null,2144.208,2144.208,2144.208,1,{"$nulls":10},0.25,536.052,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","34","LN40234040","1.03.02.04.02","CBBLN40234","RCV: Intra-rack Cables and Connectors","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,40,null,42.884159999999994,42.884159999999994,null,null,40,null,42.884159999999994,42.884159999999994,42.884159999999994,1,{"$nulls":10},0.2,8.576832,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","34","LN40234041","1.03.02.04.02","CBBLN40234","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.2,21.44208,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","34","LN40234045","1.03.02.04.02","CBBLN40234","Bench test and perform safety inspection of PS","2007-05-31","2007-06-01",null,"C","SL_PCT2","Hrs",4,null,246.80240742959995,null,246.80240742959995,null,4,null,246.80240742959995,null,246.80240742959995,246.80240742959995,1,{"$nulls":10},0.25,61.70060185739999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","34","LN40234050","1.03.02.04.02","CBBLN40234","Bench test PS Controller","2007-05-31","2007-05-31",null,"C","SL_PCT2","Hrs",4,null,246.80240742959995,null,246.80240742959995,null,4,null,246.80240742959995,null,246.80240742959995,246.80240742959995,1,{"$nulls":10},0.25,61.70060185739999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","34","LN40234055","1.03.02.04.02","CBBLN40234","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCE2","Hrs",4,null,450.8040203567999,null,450.8040203567999,null,4,null,450.8040203567999,null,450.8040203567999,450.8040203567999,1,{"$nulls":10},0.25,112.70100508919998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","34","LN40234055","1.03.02.04.02","CBBLN40234","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCCA2","Hrs",4,null,262.54255468319997,null,262.54255468319997,null,4,null,262.54255468319997,null,262.54255468319997,262.54255468319997,1,{"$nulls":10},0.25,65.63563867079999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","34","LN40234060","1.03.02.04.02","CBBLN40234","Integrate cables","2007-09-27","2007-09-27",null,"C","SL_TMUE2","Hrs",8,null,765.9241919999998,null,765.9241919999998,null,8,null,765.9241919999998,null,765.9241919999998,765.9241919999998,1,{"$nulls":10},0.25,191.48104799999996,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","35",null,null,null,"Power Supply QUE1                                           ",{"$nulls":6},24,13260,1972.8755818991995,14216.09904,16188.974621899199,null,24,13260,1972.8755818991995,14216.09904,16188.974621899199,16188.974621899199,null,0,null,0,null,0,null,0,null,0,null,null,3336.4387034748,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","02","35","LN40235015","1.03.02.04.02","CBBLN40235","RCV: Power Supply","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,11800,null,12650.8272,12650.8272,null,null,11800,null,12650.8272,12650.8272,12650.8272,1,{"$nulls":10},0.2,2530.16544,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","35","LN40235020","1.03.02.04.02","CBBLN40235","RCV: Transductors","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1320,null,1415.1772799999999,1415.1772799999999,null,null,1320,null,1415.1772799999999,1415.1772799999999,1415.1772799999999,1,{"$nulls":10},0.2,283.035456,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","35","LN40235040","1.03.02.04.02","CBBLN40235","RCV: Intra-rack Cables and Connectors","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,40,null,42.884159999999994,42.884159999999994,null,null,40,null,42.884159999999994,42.884159999999994,42.884159999999994,1,{"$nulls":10},0.2,8.576832,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","35","LN40235041","1.03.02.04.02","CBBLN40235","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.2,21.44208,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","35","LN40235045","1.03.02.04.02","CBBLN40235","Bench test and perform safety inspection of PS","2007-05-31","2007-06-01",null,"C","SL_PCT2","Hrs",4,null,246.80240742959995,null,246.80240742959995,null,4,null,246.80240742959995,null,246.80240742959995,246.80240742959995,1,{"$nulls":10},0.25,61.70060185739999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","35","LN40235050","1.03.02.04.02","CBBLN40235","Bench test PS Controller","2007-05-01","2007-05-01",null,"C","SL_PCT2","Hrs",4,null,246.80240742959995,null,246.80240742959995,null,4,null,246.80240742959995,null,246.80240742959995,246.80240742959995,1,{"$nulls":10},0.25,61.70060185739999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","35","LN40235055","1.03.02.04.02","CBBLN40235","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCE2","Hrs",4,null,450.8040203567999,null,450.8040203567999,null,4,null,450.8040203567999,null,450.8040203567999,450.8040203567999,1,{"$nulls":10},0.25,112.70100508919998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","35","LN40235055","1.03.02.04.02","CBBLN40235","Pre-install Qual Test","2007-06-04","2007-06-06",null,"C","SL_PCCA2","Hrs",4,null,262.54255468319997,null,262.54255468319997,null,4,null,262.54255468319997,null,262.54255468319997,262.54255468319997,1,{"$nulls":10},0.25,65.63563867079999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","35","LN40235060","1.03.02.04.02","CBBLN40235","Integrate cables","2007-09-27","2007-09-27",null,"C","SL_TMUE2","Hrs",8,null,765.9241919999998,null,765.9241919999998,null,8,null,765.9241919999998,null,765.9241919999998,765.9241919999998,1,{"$nulls":10},0.25,191.48104799999996,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","36",null,null,null,"Power Supply QUE2                                           ",{"$nulls":6},24,15260,1976.9773247056796,16360.30704,18337.28436470568,null,24,15260,1976.9773247056796,16360.30704,18337.28436470568,18157.922285244058,null,179.36207946162,null,0,null,0,null,0,null,0,null,null,3873.516139176421,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","02","36","LN40236015","1.03.02.04.02","CBBLN40236","RCV: Power Supply","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,11800,null,12650.8272,12650.8272,null,null,11800,null,12650.8272,12650.8272,12650.8272,1,{"$nulls":10},0.2,2530.16544,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","36","LN40236020","1.03.02.04.02","CBBLN40236","RCV: Transductors","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1320,null,1415.1772799999999,1415.1772799999999,null,null,1320,null,1415.1772799999999,1415.1772799999999,1415.1772799999999,1,{"$nulls":10},0.2,283.035456,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","36","LN40236030","1.03.02.04.02","CBBLN40236","RCV: PS Controller","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,2000,null,2144.208,2144.208,null,null,2000,null,2144.208,2144.208,2144.208,1,{"$nulls":10},0.25,536.052,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","36","LN40236040","1.03.02.04.02","CBBLN40236","RCV: Intra-rack Cables and Connectors","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,40,null,42.884159999999994,42.884159999999994,null,null,40,null,42.884159999999994,42.884159999999994,42.884159999999994,1,{"$nulls":10},0.2,8.576832,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","36","LN40236041","1.03.02.04.02","CBBLN40236","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-09-26","2007-09-26",null,"C","SL_MSEG2","$$",null,100,null,107.21039999999999,107.21039999999999,null,null,100,null,107.21039999999999,107.21039999999999,107.21039999999999,1,{"$nulls":10},0.2,21.44208,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","36","LN40236045","1.03.02.04.02","CBBLN40236","Bench test and perform safety inspection of PS","2007-05-31","2007-06-01",null,"C","SL_PCT2","Hrs",4,null,246.80240742959995,null,246.80240742959995,null,4,null,246.80240742959995,null,246.80240742959995,246.80240742959995,1,{"$nulls":10},0.25,61.70060185739999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","36","LN40236050","1.03.02.04.02","CBBLN40236","Bench test PS Controller","2007-09-27","2007-09-27",null,"C","SL_PCT2","Hrs",4,null,246.80240742959995,null,246.80240742959995,null,4,null,246.80240742959995,null,246.80240742959995,246.80240742959995,1,{"$nulls":10},0.25,61.70060185739999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","36","LN40236055","1.03.02.04.02","CBBLN40236","Pre-install Qual Test","2007-09-28","2007-10-02",null,"C","SL_PCE2","Hrs",4,null,453.39614347385157,null,453.39614347385157,null,4,null,453.39614347385157,null,453.39614347385157,340.04710760538865,0.75,113.34903586846289,0.25,{"$nulls":8},0.25,113.34903586846289,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","36","LN40236055","1.03.02.04.02","CBBLN40236","Pre-install Qual Test","2007-09-28","2007-10-02",null,"C","SL_PCCA2","Hrs",4,null,264.0521743726284,null,264.0521743726284,null,4,null,264.0521743726284,null,264.0521743726284,198.0391307794713,0.75,66.0130435931571,0.25,{"$nulls":8},0.25,66.0130435931571,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","36","LN40236060","1.03.02.04.02","CBBLN40236","Integrate cables","2007-09-27","2007-09-27",null,"C","SL_TMUE2","Hrs",8,null,765.9241919999998,null,765.9241919999998,null,8,null,765.9241919999998,null,765.9241919999998,765.9241919999998,1,{"$nulls":10},0.25,191.48104799999996,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","37",null,null,null,"Rack Accessories - LI21                                     ",{"$nulls":37},"Hamid Shoaee"]
["1","03","02","04","02","38",null,null,null,"Rack Accessories - LI24                                     ",{"$nulls":6},3,640,185.10180557219996,686.1465599999999,871.2483655721999,null,3,640,185.10180557219996,686.1465599999999,871.2483655721999,871.2483655721999,null,0,null,0,null,0,null,0,null,0,null,null,183.50476339304998,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","02","38","LN40238015","1.03.02.04.02","CBBLN40238","RCV: Circuit Breaker, 100A 480V, 3-pole,25kAIC","2007-06-13","2007-06-13",null,"C","SL_MSEG2","$$",null,640,null,686.1465599999999,686.1465599999999,null,null,640,null,686.1465599999999,686.1465599999999,686.1465599999999,1,{"$nulls":10},0.2,137.229312,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","38","LN40238020","1.03.02.04.02","CBBLN40238","Assemble and test","2007-06-14","2007-06-14",null,"C","SL_PCT2","Hrs",3,null,185.10180557219996,null,185.10180557219996,null,3,null,185.10180557219996,null,185.10180557219996,185.10180557219996,1,{"$nulls":10},0.25,46.27545139304999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","39",null,null,null,"Rack Accessories - LI25                                     ",{"$nulls":6},3,640,185.10180557219996,686.1465599999999,871.2483655721999,null,3,640,185.10180557219996,686.1465599999999,871.2483655721999,871.2483655721999,null,0,null,0,null,0,null,0,null,0,null,null,183.50476339304998,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","02","39","LN40239015","1.03.02.04.02","CBBLN40239","RCV: Circuit Breaker, 100A 480V, 3-pole,25kAIC","2007-06-13","2007-06-13",null,"C","SL_MSEG2","$$",null,640,null,686.1465599999999,686.1465599999999,null,null,640,null,686.1465599999999,686.1465599999999,686.1465599999999,1,{"$nulls":10},0.2,137.229312,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","39","LN40239020","1.03.02.04.02","CBBLN40239","Assemble and test","2007-06-14","2007-06-14",null,"C","SL_PCT2","Hrs",3,null,185.10180557219996,null,185.10180557219996,null,3,null,185.10180557219996,null,185.10180557219996,185.10180557219996,1,{"$nulls":10},0.25,46.27545139304999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","40",null,null,null,"Rack Accessories - BSY                                      ",{"$nulls":6},3,640,185.10180557219996,686.1465599999999,871.2483655721999,null,3,640,185.10180557219996,686.1465599999999,871.2483655721999,871.2483655721999,null,0,null,0,null,0,null,0,null,0,null,null,183.50476339304998,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","02","40","LN40240015","1.03.02.04.02","CBBLN40240","RCV: Circuit Breaker, 100A 480V, 3-pole,25kAIC","2007-06-13","2007-06-13",null,"C","SL_MSEG2","$$",null,640,null,686.1465599999999,686.1465599999999,null,null,640,null,686.1465599999999,686.1465599999999,686.1465599999999,1,{"$nulls":10},0.2,137.229312,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","40","LN40240020","1.03.02.04.02","CBBLN40240","Assemble and test","2007-06-14","2007-06-14",null,"C","SL_PCT2","Hrs",3,null,185.10180557219996,null,185.10180557219996,null,3,null,185.10180557219996,null,185.10180557219996,185.10180557219996,1,{"$nulls":10},0.25,46.27545139304999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","41",null,null,null,"Rack Accessories - Dump                                     ",{"$nulls":6},3,640,185.10180557219996,686.1465599999999,871.2483655721999,null,3,640,185.10180557219996,686.1465599999999,871.2483655721999,871.2483655721999,null,0,null,0,null,0,null,0,null,0,null,null,183.50476339304998,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","02","41","LN40241015","1.03.02.04.02","CBBLN40241","RCV: Circuit Breaker, 100A 480V, 3-pole,25kAIC","2007-06-13","2007-06-13",null,"C","SL_MSEG2","$$",null,640,null,686.1465599999999,686.1465599999999,null,null,640,null,686.1465599999999,686.1465599999999,686.1465599999999,1,{"$nulls":10},0.2,137.229312,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","41","LN40241020","1.03.02.04.02","CBBLN40241","Assemble and test","2007-06-14","2007-06-14",null,"C","SL_PCT2","Hrs",3,null,185.10180557219996,null,185.10180557219996,null,3,null,185.10180557219996,null,185.10180557219996,185.10180557219996,1,{"$nulls":10},0.25,46.27545139304999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","  ",null,null,null,"Beamline Power Supplies - (Trim Type)                       ",{"$nulls":6},1366,389304,142187.08103302948,417374.3756160003,559561.4566490292,null,1366,389304,142187.08103302948,417374.3756160003,559561.4566490292,515249.1193688604,null,44312.337280169406,null,0,null,0,null,0,null,0,null,null,125392.04564952214,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","03","01",null,null,null,"MCOR_1                                                      ",{"$nulls":37},"Hamid Shoaee"]
["1","03","02","04","03","02",null,null,null,"MCOR_2                                                      ",{"$nulls":37},"Hamid Shoaee"]
["1","03","02","04","03","03",null,null,null,"MCOR_3                                                      ",{"$nulls":37},"Hamid Shoaee"]
["1","03","02","04","03","04",null,null,null,"MCOR_4                                                      ",{"$nulls":37},"Hamid Shoaee"]
["1","03","02","04","03","05",null,null,null,"MCOR_5                                                      ",{"$nulls":6},28,26725,2676.8604963619196,28651.979399999993,31328.839896361915,null,28,26725,2676.8604963619196,28651.979399999993,31328.839896361915,29169.120067413325,null,2159.7198289485864,null,0,null,0,null,0,null,0,null,null,6399.611004090482,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","03","05","LN40305015","1.03.02.04.03","CBBLN40305","RCV: MCOR Chassis","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,2850,null,3055.4964,3055.4964,null,null,2850,null,3055.4964,3055.4964,3055.4964,1,{"$nulls":10},0.2,611.09928,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","05","LN40305020","1.03.02.04.03","CBBLN40305","RCV: MCOR Blower","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,500,null,536.052,536.052,null,null,500,null,536.052,536.052,536.052,1,{"$nulls":10},0.2,107.2104,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","05","LN40305025","1.03.02.04.03","CBBLN40305","RCV: MCOR Crate Accessories","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,500,null,536.052,536.052,null,null,500,null,536.052,536.052,536.052,1,{"$nulls":10},0.2,107.2104,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","05","LN40305030","1.03.02.04.03","CBBLN40305","RCV: MCOR Controller Module","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,800,null,857.6831999999999,857.6831999999999,null,null,800,null,857.6831999999999,857.6831999999999,857.6831999999999,1,{"$nulls":10},0.2,171.53664,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","05","LN40305035","1.03.02.04.03","CBBLN40305","RCV: 30Amp Pwr & Prog Modules - BX21 (Trim)","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1925,null,2063.8001999999997,2063.8001999999997,null,null,1925,null,2063.8001999999997,2063.8001999999997,2063.8001999999997,1,{"$nulls":10},0.2,412.76003999999995,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","05","LN40305040","1.03.02.04.03","CBBLN40305","RCV: 30Amp Pwr & Prog Modules - BX23 (Trim)","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1925,null,2063.8001999999997,2063.8001999999997,null,null,1925,null,2063.8001999999997,2063.8001999999997,2063.8001999999997,1,{"$nulls":10},0.2,412.76003999999995,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","05","LN40305045","1.03.02.04.03","CBBLN40305","RCV: 30Amp Pwr & Prog Modules -  BX24 (Trim)","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1925,null,2063.8001999999997,2063.8001999999997,null,null,1925,null,2063.8001999999997,2063.8001999999997,2063.8001999999997,1,{"$nulls":10},0.2,412.76003999999995,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","05","LN40305060","1.03.02.04.03","CBBLN40305","RCV: 12Amp Pwr & Prog Modules - YC24900","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1925,null,2063.8001999999997,2063.8001999999997,null,null,1925,null,2063.8001999999997,2063.8001999999997,2063.8001999999997,1,{"$nulls":10},0.2,412.76003999999995,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","05","LN40305115","1.03.02.04.03","CBBLN40305","Integrate Cables","2007-09-19","2007-10-16",null,"C","SL_TMUE2","Hrs",12,null,1163.5665016799999,null,1163.5665016799999,null,12,null,1163.5665016799999,null,1163.5665016799999,517.1406674133333,0.44,646.4258342666666,0.56,{"$nulls":8},0.25,290.89162541999997,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","05","LN40305122","1.03.02.04.03","CBBLN40305","Pre-install Qual Test","2007-11-14","2007-11-20",null,"C","SL_PCCA2","Hrs",4,null,268.5810334409136,null,268.5810334409136,null,4,null,268.5810334409136,null,268.5810334409136,null,null,268.5810334409136,1,{"$nulls":8},0.25,67.1452583602284,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","06","LN40306040","1.03.02.04.03","CBBLN40306","RCV: 12Amp Pwr & Prog Modules - XC25602","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1925,null,2063.8001999999997,2063.8001999999997,null,null,1925,null,2063.8001999999997,2063.8001999999997,2063.8001999999997,1,{"$nulls":10},0.2,412.76003999999995,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","06","LN40306110","1.03.02.04.03","CBBLN40306","MCOR Bench Test and Assembly","2007-10-17","2007-11-13",null,"C","SL_TMUE2","Hrs",8,null,783.540448416,null,783.540448416,null,8,null,783.540448416,null,783.540448416,null,null,783.540448416,1,{"$nulls":8},0.25,195.885112104,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","07",null,null,null,"MCOR_BSY1                                                   ",{"$nulls":6},28,20950,2676.8604963619196,22460.578799999996,25137.439296361918,null,28,20950,2676.8604963619196,22460.578799999996,25137.439296361918,22977.719467413328,null,2159.7198289485864,null,0,null,0,null,0,null,0,null,null,5161.330884090481,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","03","07","LN40307045","1.03.02.04.03","CBBLN40307","RCV: 12Amp Pwr & Prog Modules - XCA0","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1925,null,2063.8001999999997,2063.8001999999997,null,null,1925,null,2063.8001999999997,2063.8001999999997,2063.8001999999997,1,{"$nulls":10},0.2,412.76003999999995,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","07","LN40307070","1.03.02.04.03","CBBLN40307","RCV:  Digital to Analog Converter Module - 16 Ch","2007-09-18","2007-09-18",null,"C","SL_MSEG2","$$",null,2200,null,2358.6288,2358.6288,null,null,2200,null,2358.6288,2358.6288,2358.6288,1,{"$nulls":10},0.2,471.72576000000004,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","07","LN40307117","1.03.02.04.03","CBBLN40307","Pre-install Qual Test","2007-11-14","2007-11-20",null,"C","SL_PCE2","Hrs",4,null,461.1725128250063,null,461.1725128250063,null,4,null,461.1725128250063,null,461.1725128250063,null,null,461.1725128250063,1,{"$nulls":8},0.25,115.29312820625158,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","08","LN40308045","1.03.02.04.03","CBBLN40308","RCV: 12Amp Pwr & Prog Modules - BY1-BY2","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1925,null,2063.8001999999997,2063.8001999999997,null,null,1925,null,2063.8001999999997,2063.8001999999997,2063.8001999999997,1,{"$nulls":10},0.2,412.76003999999995,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","08","LN40308070","1.03.02.04.03","CBBLN40308","RCV:  Analog to Digital Converter Module - 32 Ch","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,4000,null,4288.416,4288.416,null,null,4000,null,4288.416,4288.416,4288.416,1,{"$nulls":10},0.2,857.6832,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","08","LN40308120","1.03.02.04.03","CBBLN40308","MCOR Bench Test and Assembly","2007-10-17","2007-11-13",null,"C","SL_TMUE2","Hrs",8,null,783.540448416,null,783.540448416,null,8,null,783.540448416,null,783.540448416,null,null,783.540448416,1,{"$nulls":8},0.25,195.885112104,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","09","LN40309040","1.03.02.04.03","CBBLN40309","RCV: 12Amp Pwr & Prog Modules - XCVM3","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1925,null,2063.8001999999997,2063.8001999999997,null,null,1925,null,2063.8001999999997,2063.8001999999997,2063.8001999999997,1,{"$nulls":10},0.2,412.76003999999995,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","09","LN40309065","1.03.02.04.03","CBBLN40309","RCV:  Analog to Digital Converter Module - 32 Ch","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,4000,null,4288.416,4288.416,null,null,4000,null,4288.416,4288.416,4288.416,1,{"$nulls":10},0.2,857.6832,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","09","LN40309115","1.03.02.04.03","CBBLN40309","MCOR Bench Test and Assembly","2007-10-17","2007-11-13",null,"C","SL_TMUE2","Hrs",8,null,783.540448416,null,783.540448416,null,8,null,783.540448416,null,783.540448416,null,null,783.540448416,1,{"$nulls":8},0.25,195.885112104,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","10",null,null,null,"MCOR_LTU3                                                   ",{"$nulls":6},28,19025,2676.8604963619196,20396.778599999998,23073.63909636192,null,28,19025,2676.8604963619196,20396.778599999998,23073.63909636192,20913.91926741333,null,2159.7198289485864,null,0,null,0,null,0,null,0,null,null,4748.570844090479,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","03","10","LN40310045","1.03.02.04.03","CBBLN40310","RCV: 12Amp Pwr & Prog Modules - XCDL1","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1925,null,2063.8001999999997,2063.8001999999997,null,null,1925,null,2063.8001999999997,2063.8001999999997,2063.8001999999997,1,{"$nulls":10},0.2,412.76003999999995,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","10","LN40310117","1.03.02.04.03","CBBLN40310","Pre-install Qual Test","2007-11-14","2007-11-20",null,"C","SL_PCE2","Hrs",4,null,461.1725128250063,null,461.1725128250063,null,4,null,461.1725128250063,null,461.1725128250063,null,null,461.1725128250063,1,{"$nulls":8},0.25,115.29312820625158,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","11","LN40311015","1.03.02.04.03","CBBLN40311","RCV: MCOR Chassis","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,2850,null,3055.4964,3055.4964,null,null,2850,null,3055.4964,3055.4964,3055.4964,1,{"$nulls":10},0.2,611.09928,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","11","LN40311075","1.03.02.04.03","CBBLN40311","RCV:  DI Module - 16 Chan","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1000,null,1072.104,1072.104,null,null,1000,null,1072.104,1072.104,1072.104,1,{"$nulls":10},0.2,214.4208,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","11","LN40311117","1.03.02.04.03","CBBLN40311","Pre-install Qual Test","2007-11-14","2007-11-20",null,"C","SL_PCE2","Hrs",4,null,461.1725128250063,null,461.1725128250063,null,4,null,461.1725128250063,null,461.1725128250063,null,null,461.1725128250063,1,{"$nulls":8},0.25,115.29312820625158,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","11","LN40311117","1.03.02.04.03","CBBLN40311","Pre-install Qual Test","2007-11-14","2007-11-20",null,"C","SL_PCCA2","Hrs",4,null,268.5810334409136,null,268.5810334409136,null,4,null,268.5810334409136,null,268.5810334409136,null,null,268.5810334409136,1,{"$nulls":8},0.25,67.1452583602284,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","12","LN40312050","1.03.02.04.03","CBBLN40312","RCV: 12Amp Pwr  & Prog Modules - YCDL3","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1925,null,2063.8001999999997,2063.8001999999997,null,null,1925,null,2063.8001999999997,2063.8001999999997,2063.8001999999997,1,{"$nulls":10},0.2,412.76003999999995,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","12","LN40312075","1.03.02.04.03","CBBLN40312","RCV:  Digital to Analog Converter Module - 16 Ch","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,2200,null,2358.6288,2358.6288,null,null,2200,null,2358.6288,2358.6288,2358.6288,1,{"$nulls":10},0.2,471.72576000000004,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","12","LN40312122","1.03.02.04.03","CBBLN40312","Pre-install Qual Test","2007-11-14","2007-11-20",null,"C","SL_PCE2","Hrs",4,null,461.1725128250063,null,461.1725128250063,null,4,null,461.1725128250063,null,461.1725128250063,null,null,461.1725128250063,1,{"$nulls":8},0.25,115.29312820625158,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","13","LN40313045","1.03.02.04.03","CBBLN40313","RCV: 12Amp Pwr & Prog Modules - YCQT42","2007-09-18","2007-09-18",null,"C","SL_MSEG2","$$",null,1925,null,2063.8001999999997,2063.8001999999997,null,null,1925,null,2063.8001999999997,2063.8001999999997,2063.8001999999997,1,{"$nulls":10},0.2,412.76003999999995,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","13","LN40313070","1.03.02.04.03","CBBLN40313","RCV:  Analog to Digital Converter Module - 32 Ch","2007-09-18","2007-09-18",null,"C","SL_MSEG2","$$",null,4000,null,4288.416,4288.416,null,null,4000,null,4288.416,4288.416,4288.416,1,{"$nulls":10},0.2,857.6832,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","13","LN40313120","1.03.02.04.03","CBBLN40313","MCOR Bench Test and Assembly","2007-10-17","2007-11-13",null,"C","SL_TMUE2","Hrs",8,null,783.540448416,null,783.540448416,null,8,null,783.540448416,null,783.540448416,null,null,783.540448416,1,{"$nulls":8},0.25,195.885112104,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","14","LN40314040","1.03.02.04.03","CBBLN40314","RCV: 12Amp Pwr & Prog Modules - XCEM4","2007-05-01","2007-05-01",null,"C","SL_MSEG2","$$",null,1925,null,2063.8001999999997,2063.8001999999997,null,null,1925,null,2063.8001999999997,2063.8001999999997,2063.8001999999997,1,{"$nulls":10},0.2,412.76003999999995,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","14","LN40314045","1.03.02.04.03","CBBLN40314","RCV: 12Amp Pwr & Prog Modules -  QEMV3","2007-05-01","2007-05-01",null,"C","SL_MSEG2","$$",null,1925,null,2063.8001999999997,2063.8001999999997,null,null,1925,null,2063.8001999999997,2063.8001999999997,2063.8001999999997,1,{"$nulls":10},0.2,412.76003999999995,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","14","LN40314115","1.03.02.04.03","CBBLN40314","Integrate Cables","2007-09-19","2007-10-16",null,"C","SL_TMUE2","Hrs",12,null,1163.5665016799999,null,1163.5665016799999,null,12,null,1163.5665016799999,null,1163.5665016799999,517.1406674133333,0.44,646.4258342666666,0.56,{"$nulls":8},0.25,290.89162541999997,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","14","LN40314122","1.03.02.04.03","CBBLN40314","Pre-install Qual Test","2007-11-14","2007-11-20",null,"C","SL_PCCA2","Hrs",4,null,268.5810334409136,null,268.5810334409136,null,4,null,268.5810334409136,null,268.5810334409136,null,null,268.5810334409136,1,{"$nulls":8},0.25,67.1452583602284,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","15","LN40315040","1.03.02.04.03","CBBLN40315","RCV: 12Amp Pwr & Prog Modules - YCE34","2007-05-01","2007-05-01",null,"C","SL_MSEG2","$$",null,1925,null,2063.8001999999997,2063.8001999999997,null,null,1925,null,2063.8001999999997,2063.8001999999997,2063.8001999999997,1,{"$nulls":10},0.2,412.76003999999995,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","15","LN40315100","1.03.02.04.03","CBBLN40315","RCV:  ADC,DAC,DI cables and conectors","2007-09-18","2007-09-18",null,"C","SL_MSEG2","$$",null,300,null,321.6312,321.6312,null,null,300,null,321.6312,321.6312,321.6312,1,{"$nulls":10},0.2,64.32624,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","15","LN40315122","1.03.02.04.03","CBBLN40315","Pre-install Qual Test","2007-11-14","2007-11-20",null,"C","SL_PCE2","Hrs",4,null,461.1725128250063,null,461.1725128250063,null,4,null,461.1725128250063,null,461.1725128250063,null,null,461.1725128250063,1,{"$nulls":8},0.25,115.29312820625158,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","16","LN40316035","1.03.02.04.03","CBBLN40316","RCV: 12Amp Pwr & Prog Modules - YCUM2","2007-05-01","2007-05-01",null,"C","SL_MSEG2","$$",null,1925,null,2063.8001999999997,2063.8001999999997,null,null,1925,null,2063.8001999999997,2063.8001999999997,2063.8001999999997,1,{"$nulls":10},0.2,412.76003999999995,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","16","LN40316115","1.03.02.04.03","CBBLN40316","Integrate Cables","2007-09-19","2007-10-16",null,"C","SL_TMUE2","Hrs",12,null,1163.5665016799999,null,1163.5665016799999,null,12,null,1163.5665016799999,null,1163.5665016799999,517.1406674133333,0.44,646.4258342666666,0.56,{"$nulls":8},0.25,290.89162541999997,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","16","LN40316120","1.03.02.04.03","CBBLN40316","MCOR Bench Test and Assembly","2007-10-17","2007-11-13",null,"C","SL_TMUE2","Hrs",8,null,783.540448416,null,783.540448416,null,8,null,783.540448416,null,783.540448416,null,null,783.540448416,1,{"$nulls":8},0.25,195.885112104,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","17","LN40317035","1.03.02.04.03","CBBLN40317","RCV: 12Amp Pwr & Prog Modules - XCUE1","2007-05-01","2007-05-01",null,"C","SL_MSEG2","$$",null,1925,null,2063.8001999999997,2063.8001999999997,null,null,1925,null,2063.8001999999997,2063.8001999999997,2063.8001999999997,1,{"$nulls":10},0.2,412.76003999999995,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","17","LN40317080","1.03.02.04.03","CBBLN40317","RCV:  IP Carrier Board","2007-05-01","2007-05-01",null,"C","SL_MSEG2","$$",null,800,null,857.6831999999999,857.6831999999999,null,null,800,null,857.6831999999999,857.6831999999999,857.6831999999999,1,{"$nulls":10},0.2,171.53664,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","17","LN40317110","1.03.02.04.03","CBBLN40317","Integrate Cables","2007-09-19","2007-10-16",null,"C","SL_TMUE2","Hrs",12,null,1163.5665016799999,null,1163.5665016799999,null,12,null,1163.5665016799999,null,1163.5665016799999,517.1406674133333,0.44,646.4258342666666,0.56,{"$nulls":8},0.25,290.89162541999997,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","21","LN40321015","1.03.02.04.03","CBBLN40321","Bench test and safety inspection","2007-05-01","2007-05-07",null,"C","SL_PCT2","Hrs",4,null,246.80240742959995,null,246.80240742959995,null,4,null,246.80240742959995,null,246.80240742959995,246.80240742959995,1,{"$nulls":10},0.25,61.70060185739999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","25",null,null,null,"MCOR Bulk PS - LTU_3                                        ",{"$nulls":6},4,0,246.80240742959995,0,246.80240742959995,null,4,0,246.80240742959995,0,246.80240742959995,246.80240742959995,null,0,null,0,null,0,null,0,null,0,null,null,61.70060185739999,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","03","26","LN40326015","1.03.02.04.03","CBBLN40326","Bench test and safety inspection","2007-05-01","2007-05-07",null,"C","SL_PCT2","Hrs",4,null,246.80240742959995,null,246.80240742959995,null,4,null,246.80240742959995,null,246.80240742959995,246.80240742959995,1,{"$nulls":10},0.25,61.70060185739999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","28","LN40328045","1.03.02.04.03","CBBLN40328","RCV:  Analog to Digital Converter Modules 12-ch","2007-06-27","2007-06-27",null,"C","SL_MSEG2","$$",null,2673,null,2865.733992,2865.733992,null,null,2673,null,2865.733992,2865.733992,2865.733992,1,{"$nulls":10},0.2,573.1467984,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","28","LN40328050","1.03.02.04.03","CBBLN40328","RCV:  Digital to Analog Converter Modules 6-ch","2007-06-27","2007-06-27",null,"C","SL_MSEG2","$$",null,2146,null,2300.7351839999997,2300.7351839999997,null,null,2146,null,2300.7351839999997,2300.7351839999997,2300.7351839999997,1,{"$nulls":10},0.2,460.14703679999997,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","28","LN40328105","1.03.02.04.03","CBBLN40328","Documentation","2007-06-28","2007-10-19",null,"C","SL_PCE2","Hrs",16,null,1809.822554504287,null,1809.822554504287,null,16,null,1809.822554504287,null,1809.822554504287,1521.5322360876748,0.84,288.2903184166121,0.16,{"$nulls":8},0.2,361.9645109008574,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","28","LN40328112","1.03.02.04.03","CBBLN40328","Pre-install Qual Test","2007-10-08","2007-10-12",null,"C","SL_PCCA2","Hrs",4,null,268.5810334409136,null,268.5810334409136,null,4,null,268.5810334409136,null,268.5810334409136,null,null,268.5810334409136,1,{"$nulls":8},0.25,67.1452583602284,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","29","LN40329045","1.03.02.04.03","CBBLN40329","RCV:  Analog to Digital Converter Modules 12-ch","2007-06-27","2007-06-27",null,"C","SL_MSEG2","$$",null,2673,null,2865.733992,2865.733992,null,null,2673,null,2865.733992,2865.733992,2865.733992,1,{"$nulls":10},0.2,573.1467984,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","29","LN40329100","1.03.02.04.03","CBBLN40329","Integrate Cables","2007-08-24","2007-09-21",null,"C","SL_TMUE2","Hrs",12,null,1148.8862879999997,null,1148.8862879999997,null,12,null,1148.8862879999997,null,1148.8862879999997,1148.8862879999997,1,{"$nulls":10},0.2,229.77725759999996,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","30","LN40330015","1.03.02.04.03","CBBLN40330","RCV:  PLC Power Supply","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,554,null,593.945616,593.945616,null,null,554,null,593.945616,593.945616,593.945616,1,{"$nulls":10},0.2,118.7891232,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","30","LN40330040","1.03.02.04.03","CBBLN40330","RCV:  PLC EtherNet/IP Module","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1209,null,1296.173736,1296.173736,null,null,1209,null,1296.173736,1296.173736,1296.173736,1,{"$nulls":10},0.2,259.2347472,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","30","LN40330095","1.03.02.04.03","CBBLN40330","Debug Ladder logic and displays","2007-06-28","2007-07-05",null,"C","SL_PCE2","Hrs",40,null,4508.040203567999,null,4508.040203567999,null,40,null,4508.040203567999,null,4508.040203567999,4508.040203567999,1,{"$nulls":10},0.35,1577.8140712487996,1.25,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","30","LN40330100","1.03.02.04.03","CBBLN40330","Integrate Cables","2007-07-06","2007-08-30",null,"C","SL_TMUE2","Hrs",12,null,1148.8862879999997,null,1148.8862879999997,null,12,null,1148.8862879999997,null,1148.8862879999997,1148.8862879999997,1,{"$nulls":10},0.2,229.77725759999996,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","31","LN40331035","1.03.02.04.03","CBBLN40331","RCV:  PLC Control Interface Module","2007-08-23","2007-08-23",null,"C","SL_MSEG2","$$",null,3450,null,3698.7587999999996,3698.7587999999996,null,null,3450,null,3698.7587999999996,3698.7587999999996,3698.7587999999996,1,{"$nulls":10},0.2,739.75176,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","31","LN40331080","1.03.02.04.03","CBBLN40331","RCV:  Intra-rack Cables and conectors","2007-08-23","2007-08-23",null,"C","SL_MSEG2","$$",null,300,null,321.6312,321.6312,null,null,300,null,321.6312,321.6312,321.6312,1,{"$nulls":10},0.25,80.4078,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","31","LN40331095","1.03.02.04.03","CBBLN40331","Debug Ladder logic and displays","2007-09-24","2007-09-28",null,"C","SL_PCE2","Hrs",40,null,4508.040203567999,null,4508.040203567999,null,40,null,4508.040203567999,null,4508.040203567999,4508.040203567999,1,{"$nulls":10},0.35,1577.8140712487996,1.25,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","32","LN40332020","1.03.02.04.03","CBBLN40332","RCV:  PLC Chassis Accessories","2007-08-23","2007-08-23",null,"C","SL_MSEG2","$$",null,150,null,160.8156,160.8156,null,null,150,null,160.8156,160.8156,160.8156,1,{"$nulls":10},0.2,32.16312,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","32","LN40332070","1.03.02.04.03","CBBLN40332","RCV:  Touch Panel Display","2007-08-23","2007-08-23",null,"C","SL_MSEG2","$$",null,1685,null,1806.49524,1806.49524,null,null,1685,null,1806.49524,1806.49524,1806.49524,1,{"$nulls":10},0.2,361.299048,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","32","LN40332085","1.03.02.04.03","CBBLN40332","Develop Ladder logic for application","2007-08-24","2007-09-21",null,"C","SL_PCE2","Hrs",40,null,4508.040203567999,null,4508.040203567999,null,40,null,4508.040203567999,null,4508.040203567999,4508.040203567999,1,{"$nulls":10},0.35,1577.8140712487996,1.25,1.1,4,3,"2G","K. Luchini"]
["1","03","02","04","03","33","LN40333015","1.03.02.04.03","CBBLN40333","RCV:  PLC Chassis Accessories","2007-08-23","2007-08-23",null,"C","SL_MSEG2","$$",null,150,null,160.8156,160.8156,null,null,150,null,160.8156,160.8156,160.8156,1,{"$nulls":10},0.2,32.16312,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","33","LN40333030","1.03.02.04.03","CBBLN40333","RCV:  PLC Control Interface Module","2007-08-23","2007-08-23",null,"C","SL_MSEG2","$$",null,3450,null,3698.7587999999996,3698.7587999999996,null,null,3450,null,3698.7587999999996,3698.7587999999996,3698.7587999999996,1,{"$nulls":10},0.2,739.75176,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","33","LN40333085","1.03.02.04.03","CBBLN40333","Develop Touch Panel Displays","2007-08-24","2007-09-21",null,"C","SL_PCE2","Hrs",16,null,1803.2160814271997,null,1803.2160814271997,null,16,null,1803.2160814271997,null,1803.2160814271997,1803.2160814271997,1,{"$nulls":10},0.35,631.1256284995198,1.25,1.1,4,3,"2G","K. Luchini"]
["1","03","02","04","03","34",null,null,null,"MCOR PLC - Dump                                             ",{"$nulls":6},136,13182,14811.740734254448,14132.474927999998,28944.21566225445,null,136,13182,14811.740734254448,14132.474927999998,28944.21566225445,25384.853678873955,null,3559.3619833804905,null,0,null,0,null,0,null,0,null,null,7476.930786188688,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","04","03","34","LN40334020","1.03.02.04.03","CBBLN40334","RCV:  PLC Chassis Accessories","2007-08-23","2007-08-23",null,"C","SL_MSEG2","$$",null,150,null,160.8156,160.8156,null,null,150,null,160.8156,160.8156,160.8156,1,{"$nulls":10},0.2,32.16312,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","34","LN40334080","1.03.02.04.03","CBBLN40334","Develop Ladder logic for application","2007-08-24","2007-09-21",null,"C","SL_PCE2","Hrs",40,null,4508.040203567999,null,4508.040203567999,null,40,null,4508.040203567999,null,4508.040203567999,4508.040203567999,1,{"$nulls":10},0.35,1577.8140712487996,1.25,1.1,4,3,"2G","K. Luchini"]
["1","03","02","04","03","34","LN40334107","1.03.02.04.03","CBBLN40334","Pre-install Qual Test","2007-11-05","2007-11-09",null,"C","SL_PCCA2","Hrs",4,null,268.5810334409136,null,268.5810334409136,null,4,null,268.5810334409136,null,268.5810334409136,null,null,268.5810334409136,1,{"$nulls":8},0.25,67.1452583602284,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","35","LN40335020","1.03.02.04.03","CBBLN40335","Bench test and safety inspection","2007-05-31","2007-06-06",null,"C","SL_PCT2","Hrs",4,null,246.80240742959995,null,246.80240742959995,null,4,null,246.80240742959995,null,246.80240742959995,246.80240742959995,1,{"$nulls":10},0.25,61.70060185739999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","04","","LN20404000","1.03.02.04.04","CBA3020404","Write Software to Integrate","2007-05-01","2007-05-29",null,"C","SL_CP2","Hrs",140,null,11503.876587588,null,11503.876587588,null,140,null,11503.876587588,null,11503.876587588,11503.876587588,1,{"$nulls":10},0.25,2875.969146897,1.15,1.1,4,3,"2G","M. Ortega"]
["1","03","02","04","04","","LN0204_715","1.03.02.04.04","CBD3020404","AWARD: L2-BC2 Cable Plant Contract","2007-06-06","2007-06-06",null,"C","SL_AWARD","$$",null,189000,null,217432.00710000002,217432.00710000002,null,null,189000,null,217432.00710000002,217432.00710000002,217432.00710000002,1,{"$nulls":15},3,"2G","M. Ortega"]
["1","03","02","04","04","","LN20404400","1.03.02.04.04","CBE3020404","L2-BC2 Racks Design","2007-05-01","2007-05-29",null,"C","SL_CE2","Hrs",128,null,14425.728651417598,null,14425.728651417598,null,128,null,14425.728651417598,null,14425.728651417598,14425.728651417598,1,{"$nulls":10},0.25,3606.4321628543994,1.15,1.1,3,3,"2G","M. Ortega"]
["1","03","02","04","04","","LN20404500","1.03.02.04.04","CBF3020404","LTU Cable Plant Design","2007-05-01","2007-06-12",null,"C","SL_CE2","Hrs",36,null,4057.236183211199,null,4057.236183211199,null,36,null,4057.236183211199,null,4057.236183211199,4057.236183211199,1,{"$nulls":10},0.25,1014.3090458027998,1.15,1.1,3,3,"2G","M. Ortega"]
["1","03","02","04","04","","LN20404515","1.03.02.04.04","CBF3020404","Vendor Fab LTU Cable Plant Hardware","2007-06-21","2007-09-14",null,"C","SA_MSEG2","$$",null,450000,null,482446.8,482446.8,null,null,450000,null,482446.8,482446.8,482446.8,1,{"$nulls":10},0.25,120611.7,1.15,1.1,4,3,"2G","M. Ortega"]
["1","03","02","04","04","","LN20404625","1.03.02.04.04","CBG3020404","Intall & Integrate LTU Racks","2007-09-17","2008-01-25",null,"C","SL_CT2","Hrs",18,null,1133.4039849993521,null,1133.4039849993521,null,18,null,1133.4039849993521,null,1133.4039849993521,122.05889069223792,0.11,1011.3450943071143,0.89,{"$nulls":8},0.25,283.35099624983803,1.15,1.1,4,3,"2G","M. Ortega"]
["1","03","02","04","04","","LN20404825","1.03.02.04.04","CBI3020404","Intall & Integrate Undulator Racks","2007-09-17","2008-01-25",null,"C","SL_PCEF2","Hrs",560,null,35261.457311090955,null,35261.457311090955,null,560,null,35261.457311090955,null,35261.457311090955,3797.38771042518,0.11,31464.069600665778,0.89,{"$nulls":8},0.25,8815.364327772739,1.15,1.1,4,3,"2G","M. Ortega"]
["1","03","02","05","  ","  ",null,null,null,"Controls - LLRF                                             ",{"$nulls":6},5473,375000,484014.7316843417,408326.88995999994,892341.6216443422,null,5473,375000,484014.7316843417,408326.88995999994,892341.6216443422,380063.109257993,null,512278.5123863487,null,0,null,0,null,0,null,0,null,null,223085.40541108555,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","05","03","  ",null,null,null,"L2/L3 RF Distribution                                       ",{"$nulls":6},1561,120000,136758.19769055772,131611.48704,268369.6847305577,null,1561,120000,136758.19769055772,131611.48704,268369.6847305577,83234.34451864619,null,185135.34021191153,null,0,null,0,null,0,null,0,null,null,67092.42118263943,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","05","03","","LN20503010","1.03.02.05","CBFLN30205","FDR: L2/L3 RF Distribution","2007-06-27","2007-06-27","S","C","SL_KE2","Hrs",8,null,901.6080407135998,null,901.6080407135998,null,8,null,901.6080407135998,null,901.6080407135998,901.6080407135998,1,{"$nulls":10},0.25,225.40201017839996,1.15,1.1,3,3,"2G","R. Akre"]
["1","03","02","05","04","","LN20504010","1.03.02.05","CBGLN30205","FDR: Beam Phase Measurement 2x","2007-07-16","2007-07-16","S","C","SL_KE2","Hrs",10,null,1127.0100508919998,null,1127.0100508919998,null,10,null,1127.0100508919998,null,1127.0100508919998,1127.0100508919998,1,{"$nulls":10},0.25,281.75251272299994,1.15,1.1,6,3,"2G","R. Akre"]
["1","03","02","05","05","","LN20505005","1.03.02.05","CBHLN30205","Desgin: Sector 24 Rack Electrical Crate IOC EVG","2007-05-01","2007-06-26","S","C","SL_KE2","Hrs",100,null,11270.100508919999,null,11270.100508919999,null,100,null,11270.100508919999,null,11270.100508919999,11270.100508919999,1,{"$nulls":10},0.25,2817.5251272299997,1.15,1.1,3,3,"2G","R. Akre"]
["1","03","02","05","05","","LN20505035","1.03.02.05","CBHLN30205","Integrate & Test: Sector 24 Rack Electrical Crat","2007-10-22","2007-11-02","S","C","SL_KT2","Hrs",40,null,2524.788628004808,null,2524.788628004808,null,40,null,2524.788628004808,null,2524.788628004808,null,null,2524.788628004808,1,{"$nulls":8},0.25,631.197157001202,1.15,1.1,3,3,"2G","R. Akre"]
["1","03","02","05","07","","LN20507005","1.03.02.05","CBJLN30205","Design: Sector 29/30 Control (Packs & Pads)","2007-05-01","2007-06-12","S","C","SL_KE2","Hrs",60,null,6762.060305351999,null,6762.060305351999,null,60,null,6762.060305351999,null,6762.060305351999,6762.060305351999,1,{"$nulls":10},0.25,1690.5150763379997,1.15,1.1,3,3,"2G","R. Akre"]
["1","03","02","05","10","","LN20510010","1.03.02.05","CBMLN30205","FDR: RF Stability / Feedback","2008-07-18","2008-07-18","S","C","SL_KE2","Hrs",8,null,922.3450256500126,null,922.3450256500126,null,8,null,922.3450256500126,null,922.3450256500126,null,null,922.3450256500126,1,{"$nulls":8},0.25,230.58625641250316,1.15,1.1,3,3,"2G","R. Akre"]
["1","03","02","05","11","","LN20511005","1.03.02.05","CBNLN30205","System Documentation","2007-05-01","2008-08-20","S","C","SL_PHS2","Hrs",224,null,16590.212370237237,null,16590.212370237237,null,224,null,16590.212370237237,null,16590.212370237237,5321.388873472321,0.32,11268.823496764915,0.68,{"$nulls":8},0.25,4147.553092559309,1.15,1.1,6,3,"2G","R. Akre"]
["1","03","02","06","01","","LN601_0245","1.03.02.06.01","CBCLN20601","RCV: 2 LVDTs","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,8080,null,8662.60032,8662.60032,null,null,8080,null,8662.60032,8662.60032,8662.60032,1,{"$nulls":10},0.2,1732.520064,1.1,1.1,2,3,"2G","D. Murray"]
["1","03","02","06","01","","LN601_0315","1.03.02.06.01","CBDLN20601","RCV: 5 PMTs","2007-09-25","2007-09-25",null,"C","SL_MSEG2","$$",null,4000,null,4288.416,4288.416,null,null,4000,null,4288.416,4288.416,4288.416,1,{"$nulls":10},0.2,857.6832,1.1,1.1,2,3,"2G","D. Murray"]
["1","03","02","06","02","  ",null,null,null,"Controls - BPMs                                             ",{"$nulls":6},2977,370305,268149.97432978865,397005.47172000003,665155.4460497887,null,2977,370305,268149.97432978865,397005.47172000003,665155.4460497887,505510.74017403304,null,159644.70587575572,null,0,null,0,null,0,null,0,null,null,166288.86151244718,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","06","02","","LN602_0280","1.03.02.06.02","CBCLN20602","L02-L03 Hardware Fab","2007-07-27","2007-09-21",null,"C","SL_CT2","Hrs",321,null,19805.893196225396,null,19805.893196225396,null,321,null,19805.893196225396,null,19805.893196225396,19805.893196225396,1,{"$nulls":10},0.25,4951.473299056349,1.15,1.1,4,3,"2G","S. Smith"]
["1","03","02","06","02","","LN602_0285","1.03.02.06.02","CBCLN20602","L02-L03 ntegration and Test","2007-09-24","2007-11-16",null,"C","SL_CP2","Hrs",107,null,8967.76172253181,null,8967.76172253181,null,107,null,8967.76172253181,null,8967.76172253181,1184.421359579673,0.13,7783.340362952137,0.87,{"$nulls":8},0.25,2241.9404306329525,1.15,1.1,4,3,"2G","S. Smith"]
["1","03","02","06","02","","LN602_0380","1.03.02.06.02","CBDLN20602","LTU Hardware Fab","2007-09-26","2008-01-02",null,"C","SL_CE2","Hrs",468,null,53895.29044854716,null,53895.29044854716,null,468,null,53895.29044854716,null,53895.29044854716,2749.7597167626104,0.05,51145.53073178455,0.95,{"$nulls":8},0.25,13473.82261213679,1.15,1.1,4,3,"2G","S. Smith"]
["1","03","02","06","03","","LN603_0220","1.03.02.06.03","CBCLN20603","RCV: 2 EVRs","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,8000,null,8576.832,8576.832,null,null,8000,null,8576.832,8576.832,8576.832,1,{"$nulls":10},0.25,2144.208,1.15,1.1,2,3,"2G","M. Cecere"]
["1","03","02","06","03","","LN603_0250","1.03.02.06.03","CBCLN20603","RCV: L02-L03 Interrack Cables","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,1000,null,1072.104,1072.104,null,null,1000,null,1072.104,1072.104,1072.104,1,{"$nulls":10},0.25,268.026,1.15,1.1,3,3,"2G","M. Cecere"]
["1","03","02","06","03","","LN603_0320","1.03.02.06.03","CBDLN20603","RCV: 3 EVRs","2007-06-29","2007-06-29",null,"C","SL_MSEG2","$$",null,12000,null,12865.248,12865.248,null,null,12000,null,12865.248,12865.248,12865.248,1,{"$nulls":10},0.25,3216.312,1.15,1.1,2,3,"2G","M. Cecere"]
["1","03","02","06","03","","LN603_0350","1.03.02.06.03","CBDLN20603","RCV: LTU Interrack Cables","2007-06-29","2007-06-29",null,"C","SL_MSEG2","$$",null,1000,null,1072.104,1072.104,null,null,1000,null,1072.104,1072.104,1072.104,1,{"$nulls":10},0.25,268.026,1.15,1.1,4,3,"2G","M. Cecere"]
["1","03","02","06","04","","LN604_230","1.03.02.06.04","CBC20604","RCV: L02-L03 I/Os","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,2000,null,2144.208,2144.208,null,null,2000,null,2144.208,2144.208,2144.208,1,{"$nulls":10},0.2,428.8416,1.1,1.1,2,3,"2G","P. Bong"]
["1","03","02","06","04","","LN604_305","1.03.02.06.04","CBD20604","LTU Rack Layout and Wiring","2007-06-01","2007-06-28",null,"C","SL_CCA2","Hrs",16,null,1050.1702187327999,null,1050.1702187327999,null,16,null,1050.1702187327999,null,1050.1702187327999,1050.1702187327999,1,{"$nulls":10},0.25,262.54255468319997,1.15,1.1,3,3,"2G","P. Bong"]
["1","03","02","06","04","","LN604_345","1.03.02.06.04","CBD20604","LTU Hardware Fab","2007-07-02","2007-07-16",null,"C","SL_CE2","Hrs",16,null,1803.2160814271997,null,1803.2160814271997,null,16,null,1803.2160814271997,null,1803.2160814271997,1803.2160814271997,1,{"$nulls":10},0.25,450.8040203567999,1.15,1.1,3,3,"2G","P. Bong"]
["1","03","02","06","05","","LN605_0230","1.03.02.06.05","CBCLN20605","RCV: 2 PMC Interfaced Cables","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,7098,null,7609.794191999999,7609.794191999999,null,null,7098,null,7609.794191999999,7609.794191999999,7609.794191999999,1,{"$nulls":10},0.2,1521.9588383999999,1.1,1.1,2,3,"2G","S. Peng"]
["1","03","02","06","05","","LN605_0405","1.03.02.06.05","CBDLN20605","LTU Rack Layout and Wiring","2007-06-01","2007-08-31",null,"C","SL_CE2","Hrs",18,null,2028.6180916055996,null,2028.6180916055996,null,18,null,2028.6180916055996,null,2028.6180916055996,2028.6180916055996,1,{"$nulls":10},0.25,507.1545229013999,1.15,1.1,3,3,"2G","S. Peng"]
["1","03","02","06","05","","LN605_0450","1.03.02.06.05","CBDLN20605","RCV: 4 Interrack Cables","2007-06-29","2007-06-29",null,"C","SL_MSEG2","$$",null,455,null,487.80731999999995,487.80731999999995,null,null,455,null,487.80731999999995,487.80731999999995,487.80731999999995,1,{"$nulls":10},0.25,121.95182999999999,1.15,1.1,3,3,"2G","S. Peng"]
["1","03","02","06","07","  ",null,null,null,"Controls - Bunch Length Monitors                            ",{"$nulls":6},264,12800,22480.341935673598,13722.931199999999,36203.2731356736,null,264,12800,22480.341935673598,13722.931199999999,36203.2731356736,36203.2731356736,null,0,null,0,null,0,null,0,null,0,null,null,8391.474323918399,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","06","07","","LN607_210","1.03.02.06.07","CBC20607","L02-L03 BLM Control Software","2007-05-01","2007-05-29",null,"C","SL_CP2","Hrs",40,null,3286.8218821680002,null,3286.8218821680002,null,40,null,3286.8218821680002,null,3286.8218821680002,3286.8218821680002,1,{"$nulls":10},0.25,821.7054705420001,1.15,1.1,4,3,"2G","S. Peng"]
["1","03","02","06","07","","LN607_250","1.03.02.06.07","CBC20607","L02-L03 BLM Integration and Test","2007-06-14","2007-06-20",null,"C","SL_CE2","Hrs",40,null,4508.040203567999,null,4508.040203567999,null,40,null,4508.040203567999,null,4508.040203567999,4508.040203567999,1,{"$nulls":10},0.25,1127.0100508919998,1.15,1.1,4,3,"2G","S. Peng"]
["1","03","02","06","09","","LN609_0240","1.03.02.06.09","CBCLN20609","RCV: L02-L03 Interrack Cables","2007-05-30","2007-05-30",null,"C","SL_MSEG2","$$",null,500,null,536.052,536.052,null,null,500,null,536.052,536.052,536.052,1,{"$nulls":10},0.25,134.013,1.15,1.1,3,3,"2G","TBD"]
["1","03","02","06","09","","LN609_0250","1.03.02.06.09","CBCLN20609","L02-L03 Integration and Test","2007-06-14","2007-06-20",null,"C","SL_CT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","TBD"]
["1","03","02","06","09","","LN609_0330","1.03.02.06.09","CBDLN20609","LTU Integration and Test","2007-07-17","2007-07-23",null,"C","SL_CT2","Hrs",8,null,493.6048148591999,null,493.6048148591999,null,8,null,493.6048148591999,null,493.6048148591999,493.6048148591999,1,{"$nulls":10},0.25,123.40120371479998,1.15,1.1,3,3,"2G","TBD"]
["1","03","02","06","10","","LN610_0245","1.03.02.06.10","CBCLN20610","L02-L03 Hardware Fab","2007-05-31","2007-06-13",null,"C","SL_CE2","Hrs",16,null,1803.2160814271997,null,1803.2160814271997,null,16,null,1803.2160814271997,null,1803.2160814271997,1803.2160814271997,1,{"$nulls":10},0.25,450.8040203567999,1.15,1.1,3,3,"2G","TBD"]
["1","03","02","06","10","","LN610_0305","1.03.02.06.10","CBDLN20610","LTU Rack Layout and Wiring","2007-06-01","2007-06-28",null,"C","SL_CE2","Hrs",16,null,1803.2160814271997,null,1803.2160814271997,null,16,null,1803.2160814271997,null,1803.2160814271997,1803.2160814271997,1,{"$nulls":10},0.25,450.8040203567999,1.15,1.1,3,3,"2G","TBD"]
["1","03","02","06","11","  ",null,null,null,"Controls - Protection Collimator                            ",{"$nulls":37},"Hamid Shoaee"]
["1","03","02","06","12","","LN612_0280","1.03.02.06.12","CBCLN20612","L02-L03 Hardware Fab","2007-07-27","2007-09-21",null,"C","SL_CT2","Hrs",15,null,925.5090278609998,null,925.5090278609998,null,15,null,925.5090278609998,null,925.5090278609998,925.5090278609998,1,{"$nulls":10},0.2,185.10180557219996,1.1,1.1,4,3,"2G","D. Murray"]
["1","03","02","06","12","","LN612_0390","1.03.02.06.12","CBDLN20612","LTU HW/SW Integration and Test","2008-01-03","2008-02-29",null,"C","SL_CT2","Hrs",38,null,2398.5491966045674,null,2398.5491966045674,null,38,null,2398.5491966045674,null,2398.5491966045674,null,null,2398.5491966045674,1,{"$nulls":8},0.2,479.7098393209135,1.1,1.1,4,3,"2G","D. Murray"]
["1","03","02","09","01","  ",null,null,null,"Controls - Vacuum Instrumentation & Interlocks              ",{"$nulls":6},2248,119698,191732.71900104897,128328.704592,320061.42359304894,null,2248,119698,191732.71900104897,128328.704592,320061.42359304894,251055.65754369358,null,69005.7660493554,null,0,null,0,null,0,null,0,null,null,74846.84972466223,{"$nulls":6},"Hamid Shoaee"]
["1","03","02","09","01","","LN209_0205","1.03.02.09.01","CBC3020901","L02-L03 Control Vacuum H/W in House FAB","2007-05-01","2007-09-06",null,"C","SL_CE2","Hrs",155,null,17468.655788825996,null,17468.655788825996,null,155,null,17468.655788825996,null,17468.655788825996,17468.655788825996,1,{"$nulls":10},0.25,4367.163947206499,1.15,1.1,3,3,"2G","S. Schuh"]
["1","03","02","09","01","","LN209_0315","1.03.02.09.01","CBD3020901","RCV: 8 LTU Ion Guage Controllers","2007-06-29","2007-06-29",null,"C","SL_MSEG2","$$",null,19400,null,20798.8176,20798.8176,null,null,19400,null,20798.8176,20798.8176,20798.8176,1,{"$nulls":10},0.2,4159.7635199999995,1.1,1.1,2,3,"2G","S. Schuh"]
["1","03","02","10","04","  ",null,null,null,"Data Communications                                         ",{"$nulls":37},"Hamid Shoaee"]
["1","03","02","10","05","","LN02100530","1.03.02.10.05","CB3021005","Prep Bid Pak - MVME6100-0163 PowerPC Processor","2007-07-12","2007-07-18",null,"C","SL_CCA2","Hrs",16,null,1050.1702187327999,null,1050.1702187327999,null,16,null,1050.1702187327999,null,1050.1702187327999,1050.1702187327999,1,{"$nulls":10},0.55,577.59362030304,1.45,1.1,4,3,"2G","H. Shoaee"]
["1","03","03","  ","  ","  ",null,null,null,"Linac Magnets & Supports                                    ",{"$nulls":6},4415,1218435,394903.5378299874,1271688.5444376173,1648322.2439499872,null,4415,1218435,394903.5378299874,1271688.5444376173,1666592.082267604,1254896.1439942683,null,411695.938273336,null,0,null,0,null,0,null,0,null,null,244888.39726373638,{"$nulls":6},"Jose Chan"]
["1","03","03","02","","","LN302-0500","1.03.03.02","CBZ30302","BX3 Engr Suppt Magnet Refurbish (BCR_90%)","2007-05-01","2007-05-29","RC","C","SL_ME2","Hrs",1,null,99.57775423859998,null,99.57775423859998,null,1,null,99.57775423859998,null,99.57775423859998,99.57775423859998,1,{"$nulls":10},0.2,19.91555084772,1.15,1.05,3,1,"2A"]
["1","03","03","02","","","LN302-0610","1.03.03.02","CBZ30302","BX3 Design Safety Cover","2007-05-01","2007-08-21","RC","C","SL_ME2","Hrs",87,null,8663.264618758198,null,8663.264618758198,null,87,null,8663.264618758198,null,8663.264618758198,8663.264618758198,1,{"$nulls":10},0.2,1732.6529237516397,1.15,1.05,4,2,"2A"]
["1","03","03","04","","","LN304-0520","1.03.03.04","CBZ30304","BYLTU Perform Magnetic Measurement","2007-05-01","2007-05-02","RC","C","SL_MES2","Hrs",4,null,320.23058205599995,null,320.23058205599995,null,4,null,320.23058205599995,null,320.23058205599995,320.23058205599995,1,{"$nulls":10},0.15,48.03458730839999,1.1,1.05,3,3,"2A"]
["1","03","03","04","","","LN304-0530","1.03.03.04","CBZ30304","BYLTU Support Design (BCR_10%)","2007-05-01","2007-05-29","TM","C","SL_MDD2","Hrs",43,null,3590.0135609777994,null,3590.0135609777994,null,43,null,3590.0135609777994,null,3590.0135609777994,3590.0135609777994,1,{"$nulls":10},0.15,538.5020341466699,1.1,1.05,4,2,"2A"]
["1","03","03","04","","","LN304-0590","1.03.03.04","CBZ30304","BYLTU Final Assembly/Kit for Installation","2007-10-09","2007-10-22","RC","C","SL_MFAT2","Hrs",80,null,7032.67488,null,7032.67488,null,80,null,7032.67488,null,7032.67488,null,null,7032.67488,1,{"$nulls":8},0.15,1054.901232,1.1,1.05,4,3,"2A"]
["1","03","03","05","","","LN305-0600","1.03.03.05","CBZ30305","Final Assembly LTU Quads","2007-09-05","2007-10-30","RC","C","SL_MFAT2","Hrs",160,null,13915.859327999999,null,13915.859327999999,null,160,null,13915.859327999999,null,13915.859327999999,6578.4062277818175,0.47,7337.45310021818,0.53,{"$nulls":8},0.15,2087.3788991999995,1.1,1.05,4,3,"2A"]
["1","03","03","08","","","LN308-0010","1.03.03.08","CBX30308","Engineering Support Corrector Fabrication","2007-08-01","2007-08-30","RC","C","SL_ME2","Hrs",88,null,8762.842372996798,null,8762.842372996798,null,88,null,8762.842372996798,null,8762.842372996798,8762.842372996798,1,{"$nulls":10},0.2,1752.5684745993597,1.1,1.1,3,1,"2A"]
["1","03","03","09","","","LN309-0050","1.03.03.09","CBX30309","Evaluate Vendor Proposals - Magnets","2007-08-01","2007-08-14","JL","C","SL_ME2","Hrs",8,null,796.6220339087998,null,796.6220339087998,null,8,null,796.6220339087998,null,796.6220339087998,796.6220339087998,1,{"$nulls":10},0.25,199.15550847719996,1.25,1,3,3,"2A"]
["1","03","03","09","","","LN309-0090","1.03.03.09","CBX30309","BYD Magnetic Measurement","2008-01-15","2008-02-12","JL","C","SL_MES2","Hrs",40,null,3275.9588544328794,null,3275.9588544328794,null,40,null,3275.9588544328794,null,3275.9588544328794,null,null,3275.9588544328794,1,{"$nulls":8},0.15,491.3938281649319,1.1,1.05,3,3,"2A"]
["1","03","03","10","","","LN310-0050","1.03.03.10","CBX30310","Dump Quad Support Design","2008-04-01","2008-04-14","JL","C","SL_ME2","Hrs",44,null,4482.193873787863,null,4482.193873787863,null,44,null,4482.193873787863,null,4482.193873787863,null,null,4482.193873787863,1,{"$nulls":8},0.15,672.3290810681793,1.1,1.05,3,2,"2A"]
["1","03","03","11","","","LN311-0570","1.03.03.11","CBZ30311","BXPM Support Design","2007-05-01","2007-07-30","JL","C","SL_MDD2","Hrs",140,null,11688.416245043998,null,11688.416245043998,null,140,null,11688.416245043998,null,11688.416245043998,11688.416245043998,1,{"$nulls":10},0.15,1753.2624367565998,1.1,1.05,4,2,"2A"]
["1","03","03","12","  ","  ",null,null,null,"Bend Magnet (BYKIK_LTU)                                     ",{"$nulls":6},775,6000,71968.049855757,6432.624,78400.67385575699,null,775,6000,71968.049855757,6432.624,78400.67385575699,78400.67385575699,null,0,null,0,null,0,null,0,null,0,null,null,11760.101078363548,{"$nulls":6},"Jose Chan"]
["1","03","03","13","  ","  ",null,null,null,"Bend Magnet (BYW_LTU)                                       ",{"$nulls":37},"Jose Chan"]
["1","03","03","14","","","LN314-0080","1.03.03.14","CBX30314","BXKIK Measure Kicker","2007-07-26","2007-08-09","RC","C","SL_MES2","Hrs",40,null,3202.3058205599996,null,3202.3058205599996,null,40,null,3202.3058205599996,null,3202.3058205599996,3202.3058205599996,1,{"$nulls":10},0.15,480.3458730839999,1.1,1.05,4,3,"2A"]
["1","03","03","15","  ","  ",null,null,null,"Muon Toroid (E-Dump)                                        ",{"$nulls":37},"Jose Chan"]
["1","03","04","02","","","LN402-0090","1.03.04.02","CBX30402","RCV:  L3 Vacuum Drifts and Supports","2007-05-29","2007-05-29","LE","C","SL_MSEG2","$$",null,30000,null,32163.12,32163.12,null,null,30000,null,32163.12,32163.12,32163.12,1,{"$nulls":10},0.2,6432.624,1.1,1.1,4,3,"2A"]
["1","03","04","03","  ","  ",null,null,null,"BC1 Vacuum System                                           ",{"$nulls":37},"Jose Chan"]
["1","03","04","04","","","LN404-0120","1.03.04.04","CBX30404","Perform Pre-Installation Qual Test","2007-08-24","2007-08-27","JC","C","SL_MFAT2","Hrs",120,null,10311.84,null,10311.84,null,120,null,10311.84,null,10311.84,10311.84,1,{"$nulls":10},0.3,3093.552,1.2,1.1,4,3,"2A"]
["1","03","04","05","","","LN405-0510","1.03.04.05","CBZ30405","Design Drifts (BCR_30%)","2007-05-01","2007-07-25","TM","C","SL_MDD2","Hrs",180,null,15027.963743627999,null,15027.963743627999,null,180,null,15027.963743627999,null,15027.963743627999,15027.963743627999,1,{"$nulls":10},0.15,2254.1945615441996,1.1,1.05,4,2,"2A"]
["1","03","04","05","","","LN405-0530","1.03.04.05","CBZ30405","Design Pump Supports","2007-05-01","2007-05-30","TM","C","SL_ME2","Hrs",42,null,4182.265678021199,null,4182.265678021199,null,42,null,4182.265678021199,null,4182.265678021199,4182.265678021199,1,{"$nulls":10},0.15,627.3398517031799,1.1,1.05,4,2,"2A"]
["1","03","04","05","","","LN405-0590","1.03.04.05","CBZ30405","Purchase Pump Supports","2007-09-12","2007-10-08","TM","C","SL_MSSY2","$$",null,56400,null,56400,null,null,null,56400,null,56400,56400,41215.38461538461,0.73,15184.615384615385,0.27,{"$nulls":8},0.15,8460,1.1,1.05,4,3,"2A"]
["1","03","04","05","","","LN405-0640","1.03.04.05","CBZ30405","Fabricate Dump Kicker Chamber","2007-05-30","2007-09-20","JL","C","SL_MFMS2","Hrs",80,null,8798.45472,null,8798.45472,null,80,null,8798.45472,null,8798.45472,8798.45472,1,{"$nulls":10},0.25,2199.61368,1.15,1.1,4,3,"2A"]
["1","03","04","05","","","LN405-0660","1.03.04.05","CBZ30405","Fabricate Dump Kicker Chamber Supports","2007-08-02","2007-10-01","JL","C","SL_MSSY2","$$",null,58154,null,58154,null,null,null,58154,null,58154,58154,58154,1,0,0,{"$nulls":8},0.25,14538.5,1.15,1.1,4,3,"2A"]
["1","03","04","06","  ","  ",null,null,null,"Dumpline Vacuum System                                      ",{"$nulls":6},2200,87654,206861.40991945175,93974.204016,300835.6139354518,null,2200,87654,206861.40991945175,93974.204016,300835.6139354518,280147.57685963885,null,20688.037075812932,null,0,null,0,null,0,null,0,null,null,57387.22571800425,{"$nulls":6},"Jose Chan"]
["1","03","04","06","","","LN406-0020","1.03.04.06","CBX30406","Design Dump Drifts","2007-05-01","2007-05-01","JL","C","SL_MDD2","Hrs",40,null,3339.5474985839996,null,3339.5474985839996,null,40,null,3339.5474985839996,null,3339.5474985839996,3339.5474985839996,1,{"$nulls":10},0.15,500.93212478759995,1.1,1.05,4,2,"2A"]
["1","03","04","06","","","LN406-0070","1.03.04.06","CBX30406","Purchase Dump Vacuum Drifts","2007-05-02","2007-07-26","JL","C","SL_MSEG2","$$",null,15000,null,16081.56,16081.56,null,null,15000,null,16081.56,16081.56,16081.56,1,{"$nulls":10},0.15,2412.234,1.1,1.05,4,3,"2A"]
["1","03","04","06","","","LN406-0130","1.03.04.06","CBX30406","Design Dump Chamber Supports","2007-05-01","2007-06-26","JL","C","SL_ME2","Hrs",44,null,4381.421186498399,null,4381.421186498399,null,44,null,4381.421186498399,null,4381.421186498399,4381.421186498399,1,{"$nulls":10},0.25,1095.3552966245998,1.15,1.1,4,2,"2A"]
["1","03","04","06","","","LN406-0170","1.03.04.06","CBX30406","Vacuum Process Dump Chamber","2007-09-21","2007-10-18","JL","C","SL_MFAT2","Hrs",40,null,3487.0569066666667,null,3487.0569066666667,null,40,null,3487.0569066666667,null,3487.0569066666667,1291.5025580246913,0.37,2195.5543486419756,0.63,{"$nulls":8},0.25,871.7642266666667,1.15,1.1,4,3,"2A"]
["1","03","04","06","","","LN406-0190","1.03.04.06","CBX30406","Design Safety Dump Chamber Supports","2007-06-06","2007-08-01","JL","C","SL_ME2","Hrs",52,null,5178.0432204071985,null,5178.0432204071985,null,52,null,5178.0432204071985,null,5178.0432204071985,5178.0432204071985,1,{"$nulls":10},0.25,1294.5108051017996,1.15,1.1,4,2,"2A"]
["1","03","04","06","","","LN406-0300","1.03.04.06","CBX30406","Design Undulator OUT Assembly","2007-05-01","2007-05-25","JL","C","SL_MDD2","Hrs",6,null,500.93212478759995,null,500.93212478759995,null,6,null,500.93212478759995,null,500.93212478759995,500.93212478759995,1,{"$nulls":15},2,"2A"]
["1","03","04","06","","","LN406-0310","1.03.04.06","CBX30406","Procure Undulator OUT Assembly","2007-05-29","2007-07-24","JL","C","SL_MSEG2","$$",null,7654,null,8205.884016,8205.884016,null,null,7654,null,8205.884016,8205.884016,8205.884016,1,{"$nulls":15},3,"2A"]
["1","03","04","07","02","","LN407-2010","1.03.04.07.02","CCX3040702","Prelim Prototype Design Exit Sec","2007-05-01","2007-05-14","JL","C","SL_MVE2","Hrs",28,null,2964.575320660799,null,2964.575320660799,null,28,null,2964.575320660799,null,2964.575320660799,2964.575320660799,1,{"$nulls":10},0.25,741.1438301651998,1.2,1.05,4,2,"2A"]
["1","03","04","08","","","LN408-0510","1.03.04.08","CBZ30408","Generate Cold Trap Specifications","2007-05-01","2007-06-01","LE","C","SL_ME2","Hrs",18,null,1792.3995762947995,null,1792.3995762947995,null,18,null,1792.3995762947995,null,1792.3995762947995,1792.3995762947995,1,{"$nulls":10},0.2,358.4799152589599,1.15,1.05,4,2,"2A"]
["1","03","04","08","","","LN408-0560","1.03.04.08","CBZ30408","Field Qualify Cold Trap (thru LTU Install)","2008-05-27","2008-09-03","LE","C","SL_ME2","Hrs",80,null,8149.443406887023,null,8149.443406887023,null,80,null,8149.443406887023,null,8149.443406887023,null,null,8149.443406887023,1,{"$nulls":8},0.2,1629.8886813774047,1.15,1.05,4,3,"2A"]
["1","03","05","01","","","LN501-0580","1.03.05.01","CBZ30501","Pocure Misc. Materials - Wire Scanner Support","2007-05-01","2007-06-04","TM","C","SL_MSEG2","$$",null,1747,null,1872.965688,1872.965688,null,null,1747,null,1872.965688,1872.965688,1872.965688,1,{"$nulls":10},0.15,280.9448532,1.1,1.05,3,3,"2A"]
["1","03","05","02","03","","LN502-3550","1.03.05.02.03","CBZ3050203","Create / Remodel / Revise Dsn Documentation","2007-05-01","2007-05-29","TM","C","SL_MDD2","Hrs",16,null,1335.8189994335999,null,1335.8189994335999,null,16,null,1335.8189994335999,null,1335.8189994335999,1335.8189994335999,1,{"$nulls":10},0.2,267.16379988671997,1.15,1.05,4,2,"2A"]
["1","03","05","02","03","","LN502-3580","1.03.05.02.03","CBZ3050203","Conduct Prelim Design Review (PDR) - FFTB BPMs","2007-05-29","2007-05-29","TM","C","SL_ME2","Hrs",1,null,99.57775423859998,null,99.57775423859998,null,1,null,99.57775423859998,null,99.57775423859998,99.57775423859998,1,{"$nulls":10},0.2,19.91555084772,1.15,1.05,4,2,"2A"]
["1","03","05","02","03","","LN502-3640","1.03.05.02.03","CBZ3050203","Perform Functional Testing - BPMs","2007-08-27","2007-08-28","TM","C","SL_CCA2","Hrs",15,null,984.5345800619999,null,984.5345800619999,null,15,null,984.5345800619999,null,984.5345800619999,984.5345800619999,1,{"$nulls":10},0.2,196.9069160124,1.15,1.05,4,3,"2A"]
["1","03","05","02","03","","LN502-3650","1.03.05.02.03","CBZ3050203","Post Process & Test","2007-08-29","2007-09-05","TM","C","SL_MFAT2","Hrs",40,null,3437.28,null,3437.28,null,40,null,3437.28,null,3437.28,3437.28,1,{"$nulls":10},0.2,687.4560000000001,1.15,1.05,4,3,"2A"]
["1","03","05","03","","","LN503-0140","1.03.05.03","CBX30503","Perform Functional Testing Dump Toroid","2007-11-16","2007-12-03","JL","C","SL_CCA2","Hrs",16,null,1074.3241337636543,null,1074.3241337636543,null,16,null,1074.3241337636543,null,1074.3241337636543,null,null,1074.3241337636543,1,{"$nulls":8},0.3,322.2972401290963,1.2,1.1,4,3,"2A"]
["1","03","05","04","","","LN504-0090","1.03.05.04","CBX30504","Conduct Stoppers FDR","2007-08-01","2007-08-03","TM","C","SL_ME2","Hrs",12,null,1194.9330508631997,null,1194.9330508631997,null,12,null,1194.9330508631997,null,1194.9330508631997,1194.9330508631997,1,{"$nulls":10},0.2,238.98661017263996,1.15,1.05,4,2,"2A"]
["1","03","05","04","","","LN504-0190","1.03.05.04","CBX30504","Vendor Fab 1st Lot - Supports","2007-08-14","2007-09-11","TM","C","SL_MSEG2","$$",null,4000,null,4288.416,4288.416,null,null,4000,null,4288.416,4288.416,4288.416,1,{"$nulls":10},0.2,857.6832,1.15,1.05,4,3,"2A"]
["1","03","05","05","","","LN505-0680","1.03.05.05","CBZ30505","RCV: Profile Monitors 1st Lot","2007-05-29","2007-05-29","TM","C","SA_MSEG2","$$",null,69000,null,73975.17599999999,73975.17599999999,null,null,69000,null,73975.17599999999,73975.17599999999,73975.17599999999,1,{"$nulls":10},0.2,14795.035199999998,1.2,1,3,3,"2A"]
["1","03","05","05","","","LN505-0760","1.03.05.05","CBZ30505","Procure Misc Materials - Diagnostics Supports","2007-06-12","2007-07-10","TM","C","SL_MSEG2","$$",null,2400,null,2573.0496,2573.0496,null,null,2400,null,2573.0496,2573.0496,2573.0496,1,{"$nulls":10},0.2,514.60992,1.2,1,3,3,"2A"]
["1","03","05","05","","","LN505-0790","1.03.05.05","CBZ30505","RCV: Supports from Vendor","2007-07-26","2007-07-26","TM","C","SA_MSEG2","$$",null,17480,null,18740.37792,18740.37792,null,null,17480,null,18740.37792,18740.37792,18740.37792,1,{"$nulls":10},0.2,3748.075584,1.2,1,3,3,"2A"]
["1","03","05","07","","","LN507-0160","1.03.05.07","CBX30507","BL21 Engineering & Design","2007-05-23","2007-05-30","TM","C","SL_MDD2","Hrs",160,null,13358.189994335999,null,13358.189994335999,null,160,null,13358.189994335999,null,13358.189994335999,13358.189994335999,1,{"$nulls":10},0.35,4675.366498017599,1.25,1.1,4,2,"2A"]
["1","03","05","07","","","LN507-0170","1.03.05.07","CBX30507","BL21 Materials & Hardware","2007-05-31","2007-06-13","TM","C","SL_MSEG2","$$",null,50000,null,53605.2,53605.2,null,null,50000,null,53605.2,53605.2,53605.2,1,{"$nulls":10},0.35,18761.819999999996,1.25,1.1,4,3,"2A"]
["1","03","05","07","","","LN507-0190","1.03.05.07","CBX30507","BL21 Fabrcation Optics Assembly","2007-05-31","2007-07-26","TM","C","SL_MFMS2","Hrs",80,null,8798.45472,null,8798.45472,null,80,null,8798.45472,null,8798.45472,8798.45472,1,{"$nulls":10},0.35,3079.459152,1.25,1.1,4,3,"2A"]
["1","03","05","07","","","LN507-0210","1.03.05.07","CBX30507","BL21 QC/Fiducialization","2007-08-10","2007-08-23","TM","C","SL_MES2","Hrs",40,null,3202.3058205599996,null,3202.3058205599996,null,40,null,3202.3058205599996,null,3202.3058205599996,3202.3058205599996,1,{"$nulls":10},0.35,1120.8070371959998,1.25,1.1,4,3,"2A"]
["1","03","05","07","","","LN507-0230","1.03.05.07","CBX30507","BL21 Testing","2007-07-27","2007-08-23","TM","C","SL_PHSS2","Hrs",40,null,3712.503697056,null,3712.503697056,null,40,null,3712.503697056,null,3712.503697056,3712.503697056,1,{"$nulls":10},0.35,1299.3762939695998,1.25,1.1,4,3,"2A"]
["1","03","05","08","01","","LN508-1040","1.03.05.08.01","CBX3050801","Revise  Design Documentation","2007-05-08","2007-05-21","TM","C","SL_MDD2","Hrs",50,null,4174.434373229999,null,4174.434373229999,null,50,null,4174.434373229999,null,4174.434373229999,4174.434373229999,1,{"$nulls":10},0.15,626.1651559844998,1.15,1,4,2,"2A"]
["1","03","05","08","01","","LN508-1110","1.03.05.08.01","CBX3050801","Perform Functional Testing - Beam Loss Monito","2007-08-02","2007-08-15","TM","C","SL_CCA2","Hrs",40,null,2625.425546832,null,2625.425546832,null,40,null,2625.425546832,null,2625.425546832,2625.425546832,1,{"$nulls":10},0.15,393.8138320248,1.15,1,4,3,"2A"]
["1","03","05","08","01","","LN508-1170","1.03.05.08.01","CBX3050801","Vendor Fab Supports","2007-06-15","2007-07-06","TM","C","SL_MSEG2","$$",null,4320,null,4631.48928,4631.48928,null,null,4320,null,4631.48928,4631.48928,4631.48928,1,{"$nulls":10},0.15,694.723392,1.15,1,4,3,"2A"]
["1","03","05","08","02","","LN508-2100","1.03.05.08.02","CBX3050802","Procure Component Material - Beam Loss Monitors","2007-05-31","2007-06-20","TM","C","SL_MSEG2","$$",null,18000,null,19297.872,19297.872,null,null,18000,null,19297.872,19297.872,19297.872,1,{"$nulls":10},0.15,2894.6807999999996,1.15,1,4,3,"2A"]
["1","03","05","08","02","","LN508-2110","1.03.05.08.02","CBX3050802","Component Fab & Assembly - Beam Loss Monitors","2007-06-21","2007-08-23","TM","C","SL_MFPC2","Hrs",180,null,31079.149199999996,null,31079.149199999996,null,180,null,31079.149199999996,null,31079.149199999996,31079.149199999996,1,{"$nulls":10},0.15,4661.872379999999,1.15,1,4,3,"2A"]
["1","03","05","09","  ","  ",null,null,null,"Single Beam Dump (1) Summary                                ",{"$nulls":6},1090,11200,98920.91986128,12007.5648,110928.48466128,null,1090,11200,98920.91986128,12007.5648,110928.48466128,110928.48466128,null,0,null,0,null,0,null,0,null,0,null,null,38824.969631447995,{"$nulls":6},"Jose Chan"]
["1","03","05","09","","","LN509-0090","1.03.05.09","CBX30509","Procure Component Material - Single Beam Dump","2007-07-19","2007-08-15","TM","C","SL_MSEG2","$$",null,7200,null,7719.1488,7719.1488,null,null,7200,null,7719.1488,7719.1488,7719.1488,1,{"$nulls":10},0.35,2701.70208,1.25,1.1,4,3,"2A"]
["1","03","05","09","","","LN509-0110","1.03.05.09","CBX30509","Post Process & Test","2007-08-30","2007-09-13","TM","C","SL_MFAT2","Hrs",120,null,10311.84,null,10311.84,null,120,null,10311.84,null,10311.84,10311.84,1,{"$nulls":10},0.35,3609.144,1.25,1.1,4,3,"2A"]
["1","03","05","10","","","LN510-0070","1.03.05.10","CBX30510","Create / Remodel / Revise Dsn Documentation","2007-05-01","2007-05-14","JL","C","SL_MDD2","Hrs",180,null,15027.963743627999,null,15027.963743627999,null,180,null,15027.963743627999,null,15027.963743627999,15027.963743627999,1,{"$nulls":10},0.2,3005.5927487256,1.15,1.05,4,2,"2A"]
["1","03","05","10","","","LN510-0140","1.03.05.10","CBX30510","Component Fab & Assembly - Electron Beam Dump","2007-08-01","2007-08-28","JL","C","SL_MFMS2","Hrs",80,null,8798.45472,null,8798.45472,null,80,null,8798.45472,null,8798.45472,8798.45472,1,{"$nulls":10},0.2,1759.690944,1.15,1.05,4,3,"2A"]
["1","03","05","10","","","LN510-0160","1.03.05.10","CBX30510","Post Process & Test","2007-09-06","2007-09-19","JL","C","SL_MFAT2","Hrs",80,null,6874.56,null,6874.56,null,80,null,6874.56,null,6874.56,6874.56,1,{"$nulls":10},0.2,1374.9120000000003,1.15,1.05,4,3,"2A"]
["1","03","05","11","","","LN511-0510","1.03.05.11","CBZ30511","Design Check","2007-06-01","2007-07-27","TM","C","SL_MDD2","Hrs",480,null,40074.569983008,null,40074.569983008,null,480,null,40074.569983008,null,40074.569983008,40074.569983008,1,{"$nulls":10},0.15,6011.1854974512,1.15,1,4,2,"2A"]
["1","03","05","11","","","LN511-0560","1.03.05.11","CBZ30511","Prep Bid Pak - Protection Collimator","2007-08-08","2007-08-09","TM","C","SL_ME2","Hrs",10,null,995.7775423859998,null,995.7775423859998,null,10,null,995.7775423859998,null,995.7775423859998,995.7775423859998,1,{"$nulls":10},0.15,149.36663135789996,1.15,1,4,2,"2A"]
["1","03","05","11","","","LN511-0610","1.03.05.11","CBZ30511","Component Fab & Assembly - Protection Collimat","2007-09-18","2007-10-15","TM","C","SL_MFPC2","Hrs",80,null,13977.687480533332,null,13977.687480533332,null,80,null,13977.687480533332,null,13977.687480533332,6729.997675812345,0.48,7247.689804720986,0.52,{"$nulls":8},0.15,2096.65312208,1.15,1,4,3,"2A"]
["1","03","05","11","","","LN511-0650","1.03.05.11","CBZ30511","Vendor Fab 1st Lot - Supports","2007-09-14","2007-10-11","TM","C","SL_MSEG2","$$",null,14400,null,15569.809023999998,null,null,null,14400,null,15569.809023999998,15569.809023999998,9803.213089185185,0.63,5766.5959348148135,0.37,{"$nulls":8},0.15,2335.4713535999995,1.15,1,4,3,"2A"]
["1","03","05","12","  ","  ",null,null,null,"Movable Collimators (7x,3y) Summary                         ",{"$nulls":6},1445,204800,157823.93368819996,210568.32,368392.25368819985,null,1445,204800,157823.93368819996,210568.32,368392.25368819985,356740.6038506092,null,11651.649837590663,null,0,null,0,null,0,null,0,null,null,73678.45073764,{"$nulls":6},"Jose Chan"]
["1","03","05","12","","","LN512-0630","1.03.05.12","CBZ30512","Component Fab & Assembly - Movable Collimator","2007-05-31","2007-09-21","TM","C","SL_MFAT2","Hrs",320,null,27498.24,null,27498.24,null,320,null,27498.24,null,27498.24,27498.24,1,{"$nulls":10},0.2,5499.648000000001,1.15,1.05,4,3,"2A"]
["1","03","05","12","","","LN512-0710","1.03.05.12","CBZ30512","Assemble Supports","2007-06-05","2007-06-18","TM","C","SL_MFAT2","Hrs",180,null,15467.76,null,15467.76,null,180,null,15467.76,null,15467.76,15467.76,1,{"$nulls":10},0.2,3093.552,1.15,1.05,4,3,"2A"]
["1","03","05","12","","","LN512-0760","1.03.05.12","CBZ30512","Component Fab & Assembly - Movable Collimator","2007-05-01","2007-05-30","TM","C","SL_MFAT2","Hrs",1,null,85.932,null,85.932,null,1,null,85.932,null,85.932,85.932,1,{"$nulls":10},0.2,17.186400000000003,1.15,1.05,4,3,"2A"]
["1","03","05","13","","","LN513-0060","1.03.05.13","CBX30513","Write Component Traveler","2007-05-30","2007-06-05","JL","C","SL_ME2","Hrs",8,null,796.6220339087998,null,796.6220339087998,null,8,null,796.6220339087998,null,796.6220339087998,796.6220339087998,1,{"$nulls":10},0.2,159.32440678176,1.2,1,4,2,"2A"]
["1","03","05","13","","","LN513-0090","1.03.05.13","CBX30513","Conduct Single Beam Dump FDR","2007-06-14","2007-06-20","JL","C","SL_ME2","Hrs",3,null,298.7332627157999,null,298.7332627157999,null,3,null,298.7332627157999,null,298.7332627157999,298.7332627157999,1,{"$nulls":10},0.2,59.74665254315999,1.2,1,4,2,"2A"]
["1","03","05","13","","","LN513-0210","1.03.05.13","CBX30513","Vendor Fab Diagnostics Supports","2007-07-26","2007-09-20","JL","C","SL_MSEG2","$$",null,2000,null,2144.208,2144.208,null,null,2000,null,2144.208,2144.208,2144.208,1,{"$nulls":10},0.2,428.8416,1.2,1,4,3,"2A"]
["1","03","06","05","  ","  ",null,null,null,"X-Band High Power System                                    ",{"$nulls":37},"Jose Chan"]
["1","03","06","05","03","  ",null,null,null,"X-Band HP Waveguide System                                  ",{"$nulls":37},"Jose Chan"]
["1","03","06","07","07","  ",null,null,null,"RF Distribution L2 & L3                                     ",{"$nulls":37},"Jose Chan"]
["1","03","07","04","  ","  ",null,null,null,"Linac BC2 System Installation & Alignment                   ",{"$nulls":37},"Jose Chan"]
["1","03","07","06","","","S8X3_BL050","1.03.07.06","CBZ30706","Network & Monumentation- BTH","2008-01-09","2008-01-23",null,"C","SL_MFAT2","Hrs",240,null,21098.02464,null,21098.02464,null,240,null,21098.02464,null,21098.02464,null,null,21098.02464,1,{"$nulls":8},0.5,10549.01232,1.25,1.25,null,null,"2A"]
["1","03","07","06","","","S8X3_BL090","1.03.07.06","CBZ30706","Install Racks & cable plant BTH (SB 2.1,2.2)","2007-12-05","2008-03-10",null,"C","SL_CE2","Hrs",60,null,6917.587692375095,null,6917.587692375095,null,60,null,6917.587692375095,null,6917.587692375095,null,null,6917.587692375095,1,{"$nulls":8},1,6917.587692375095,1.5,1.5,null,null,"2A"]
["1","03","07","06","","","S8X3_BL100","1.03.07.06","CBZ30706","Install LTU to EBD components","2008-03-20","2008-06-12",null,"C","SL_MFAT2","Hrs",1320,null,116039.13552,null,116039.13552,null,1320,null,116039.13552,null,116039.13552,null,null,116039.13552,1,{"$nulls":8},1,116039.13552,1.5,1.5,null,null,"2A"]
["1","03","07","06","","","S8X3_BL120","1.03.07.06","CBZ30706","Checkout LTU","2008-09-04","2008-10-01",null,"C","SL_CCA2","Hrs",32,null,2148.6482675273087,null,2148.6482675273087,null,32,null,2148.6482675273087,null,2148.6482675273087,null,null,2148.6482675273087,1,0,0,{"$nulls":6},0.5,1074.3241337636543,1.25,1.25,null,null,"2A"]
["1","03","07","07","","","S8X5_BD050","1.03.07.07","CBZ30707","Install Dump components - LN","2008-04-21","2008-07-15",null,"C","SL_MFAT2","Hrs",1320,null,116039.13552,null,116039.13552,null,1320,null,116039.13552,null,116039.13552,null,null,116039.13552,1,{"$nulls":8},0.5,58019.56776,1.25,1.25,null,null,"2A"]
["1","03","07","07","","","S8X5_BD050","1.03.07.07","CBZ30707","Install Dump components - LN","2008-04-21","2008-07-15",null,"C","SL_CE2","Hrs",30,null,3458.7938461875474,null,3458.7938461875474,null,30,null,3458.7938461875474,null,3458.7938461875474,null,null,3458.7938461875474,1,{"$nulls":8},0.5,1729.3969230937737,1.25,1.25,null,null,"2A"]
["1","03","07","07","","","S8X5_BD080","1.03.07.07","CBZ30707","Terminate cable plant Dump (SB3.1)","2008-07-16","2008-08-20",null,"C","SL_PCCA2","Hrs",20,null,1342.905167204568,null,1342.905167204568,null,20,null,1342.905167204568,null,1342.905167204568,null,null,1342.905167204568,1,{"$nulls":8},0.5,671.452583602284,1.25,1.25,null,null,"2A"]
["1","03","07","10","03","  ",null,null,null,"Beamline Equip Installation L01 thru BC1 Out                ",{"$nulls":37},"Jose Chan"]
["1","03","07","20","  ","  ",null,null,null,"LINAC Installation 2007 Shut Down                           ",{"$nulls":6},11272,838750,1079182.9742136425,879010,1155424.9742136425,null,11272,838750,1079182.9742136425,879010,1958192.9742136423,704080.261531271,null,1254112.7126823715,null,0,null,0,null,0,null,0,null,null,1529204.7898455355,{"$nulls":6},"Jose Chan"]
["1","03","07","20","01","","LN720-1060","1.03.07.20.01","CBX3072001","Disconnect Water from Structures and Loads","2007-10-05","2007-10-08","KR","C","SL_MFAT2","Hrs",32,null,2813.069952,null,2813.069952,null,32,null,2813.069952,null,2813.069952,null,null,2813.069952,1,{"$nulls":8},0.5,1406.534976,1.25,1.25,4,4,"2A"]
["1","03","07","20","01","","LN720-1090","1.03.07.20.01","CBX3072001","Remove LLRF","2007-10-11","2007-10-11","KR","C","SL_KT2","Hrs",16,null,1009.9154512019231,null,1009.9154512019231,null,16,null,1009.9154512019231,null,1009.9154512019231,null,null,1009.9154512019231,1,{"$nulls":8},0.5,504.95772560096157,1.25,1.25,4,4,"2A"]
["1","03","07","20","01","","LN720-1180","1.03.07.20.01","CBX3072001","Remove Quad LI21 20 QEF 201","2007-10-22","2007-10-22","KR","C","SL_MFAT2","Hrs",16,null,1406.534976,null,1406.534976,null,16,null,1406.534976,null,1406.534976,null,null,1406.534976,1,{"$nulls":8},0.5,703.267488,1.25,1.25,4,4,"2A"]
["1","03","07","20","01","","LN720-1250","1.03.07.20.01","CBX3072001","Remove Waveguide and Loads from Structure","2007-10-12","2007-10-17","KR","C","SL_MFAT2","Hrs",64,null,5626.139904,null,5626.139904,null,64,null,5626.139904,null,5626.139904,null,null,5626.139904,1,{"$nulls":8},0.5,2813.069952,1.25,1.25,4,4,"2A"]
["1","03","07","20","01","","LN720-1280","1.03.07.20.01","CBX3072001","Remove Waveguide and Loads from Structure","2007-10-12","2007-10-17","KR","C","SL_MFAT2","Hrs",64,null,5626.139904,null,5626.139904,null,64,null,5626.139904,null,5626.139904,null,null,5626.139904,1,{"$nulls":8},0.5,2813.069952,1.25,1.25,4,4,"2A"]
["1","03","07","20","01","","LN720-1350","1.03.07.20.01","CBX3072001","Remove Accelerator Section LI21 310 3A","2007-10-25","2007-10-25","KR","C","SL_MFAT2","Hrs",64,null,5626.139904,null,5626.139904,null,64,null,5626.139904,null,5626.139904,null,null,5626.139904,1,{"$nulls":8},0.5,2813.069952,1.25,1.25,4,4,"2A"]
["1","03","07","20","02","","LN720-2070","1.03.07.20.02","CBX3072002","Weld Upstream BPM Eyelet between 1B and 1C","2007-11-01","2007-11-01","KR","C","SL_MFAT2","Hrs",6,null,527.450616,null,527.450616,null,6,null,527.450616,null,527.450616,null,null,527.450616,1,{"$nulls":8},0.5,263.725308,1.25,1.25,4,4,"2A"]
["1","03","07","20","02","","LN720-2100","1.03.07.20.02","CBX3072002","Weld Downstream BPM Eyelet between 1C and 1D","2007-11-01","2007-11-01","KR","C","SL_MFAT2","Hrs",6,null,527.450616,null,527.450616,null,6,null,527.450616,null,527.450616,null,null,527.450616,1,{"$nulls":8},0.5,263.725308,1.25,1.25,4,4,"2A"]
["1","03","07","20","02","","LN720-2170","1.03.07.20.02","CBX3072002","Install XY Correctors on Structures 1B, 1C and 1","2007-11-01","2007-11-01","KR","C","SL_MFAT2","Hrs",24,null,2109.802464,null,2109.802464,null,24,null,2109.802464,null,2109.802464,null,null,2109.802464,1,{"$nulls":8},0.5,1054.901232,1.25,1.25,4,4,"2A"]
["1","03","07","20","02","","LN720-2200","1.03.07.20.02","CBX3072002","Align X Band Structure","2007-09-20","2007-09-20","KR","C","SL_MES2","Hrs",24,null,1921.3834923359996,null,1921.3834923359996,null,24,null,1921.3834923359996,null,1921.3834923359996,1921.3834923359996,1,{"$nulls":10},0.5,960.6917461679998,1.25,1.25,4,4,"2A"]
["1","03","07","20","02","","LN720-2290","1.03.07.20.02","CBX3072002","Install BC1 Input Supports","2007-09-11","2007-09-12","KR","C","SL_MSPF2","$$",null,4170,null,4370.16,4370.16,null,null,4170,null,4370.16,4370.16,4370.16,1,{"$nulls":10},0.5,2185.08,1.25,1.25,4,4,"2A"]
["1","03","07","20","02","","LN720-2360","1.03.07.20.02","CBX3072002","Install BC1 Table Upstream Vacuum Assy","2007-09-26","2007-09-27","KR","C","SL_MFAT2","Hrs",72,null,6187.104,null,6187.104,null,72,null,6187.104,null,6187.104,6187.104,1,{"$nulls":10},0.5,3093.552,1.25,1.25,4,4,"2A"]
["1","03","07","20","02","","LN720-2390","1.03.07.20.02","CBX3072002","Install Quad Magnet QM12","2007-10-04","2007-10-04","KR","C","SL_MFAT2","Hrs",24,null,2109.802464,null,2109.802464,null,24,null,2109.802464,null,2109.802464,null,null,2109.802464,1,{"$nulls":8},0.5,1054.901232,1.25,1.25,4,4,"2A"]
["1","03","07","20","02","","LN720-2460","1.03.07.20.02","CBX3072002","Install Wire Scanner WS11","2007-10-17","2007-10-17","KR","C","SL_MFAT2","Hrs",24,null,2109.802464,null,2109.802464,null,24,null,2109.802464,null,2109.802464,null,null,2109.802464,1,{"$nulls":8},0.5,1054.901232,1.25,1.25,4,4,"2A"]
["1","03","07","20","02","","LN720-2550","1.03.07.20.02","CBX3072002","Install Quad Magnet Q21301","2007-11-08","2007-11-08","KR","C","SL_MFAT2","Hrs",24,null,2109.802464,null,2109.802464,null,24,null,2109.802464,null,2109.802464,null,null,2109.802464,1,{"$nulls":8},0.5,1054.901232,1.25,1.25,4,4,"2A"]
["1","03","07","20","02","","LN720-2580","1.03.07.20.02","CBX3072002","Install Corrector XCM14","2007-11-09","2007-11-09","KR","C","SL_MFAT2","Hrs",24,null,2109.802464,null,2109.802464,null,24,null,2109.802464,null,2109.802464,null,null,2109.802464,1,{"$nulls":8},0.5,1054.901232,1.25,1.25,4,4,"2A"]
["1","03","07","20","02","","LN720-2650","1.03.07.20.02","CBX3072002","Reconfigure SLC quadrupole to LCLS","2007-09-04","2007-09-06","KR","C","SL_CE2","Hrs",72,null,8114.472366422398,null,8114.472366422398,null,72,null,8114.472366422398,null,8114.472366422398,8114.472366422398,1,{"$nulls":10},0.5,4057.236183211199,1.25,1.25,4,4,"2A"]
["1","03","07","20","04","","LN720-4030","1.03.07.20.04","CCX3072004","Entrance Section Assy & Support Arrive at SLAC","2007-06-01","2007-06-14","KR","C","SL_SEE2","Hrs",16,null,1694.0430403775995,null,1694.0430403775995,null,16,null,1694.0430403775995,null,1694.0430403775995,1694.0430403775995,1,{"$nulls":10},0.5,847.0215201887997,1.25,1.25,4,4,"2A"]
["1","03","07","20","04","","LN720-4030","1.03.07.20.04","CCX3072004","Entrance Section Assy & Support Arrive at SLAC","2007-06-01","2007-06-14","KR","C","SL_MFAT2","Hrs",40,null,3437.28,null,3437.28,null,40,null,3437.28,null,3437.28,3437.28,1,{"$nulls":10},0.5,1718.64,1.25,1.25,4,4,"2A"]
["1","03","07","20","04","","LN720-4070","1.03.07.20.04","CCX3072004","EOU Arrive at SLAC","2007-05-01","2007-05-15","KR","C","SL_MFAT2","Hrs",16,null,1374.912,null,1374.912,null,16,null,1374.912,null,1374.912,1374.912,1,{"$nulls":10},0.5,687.456,1.25,1.25,4,4,"2A"]
["1","03","07","20","04","","LN720-4080","1.03.07.20.04","CCX3072004","Pre-Align EOU at SLAC","2007-05-16","2007-06-14","KR","C","SL_MES2","Hrs",120,null,9606.91746168,null,9606.91746168,null,120,null,9606.91746168,null,9606.91746168,9606.91746168,1,{"$nulls":10},0.5,4803.45873084,1.25,1.25,4,4,"2A"]
["1","03","07","20","04","","LN720-4100","1.03.07.20.04","CCX3072004","Align EOU","2008-01-14","2008-01-18","KR","C","SL_SEE2","Hrs",72,null,7798.527136378281,null,7798.527136378281,null,72,null,7798.527136378281,null,7798.527136378281,null,null,7798.527136378281,1,{"$nulls":8},0.5,3899.2635681891406,1.25,1.25,4,4,"2A"]
["1","03","07","20","04","","LN720-4120","1.03.07.20.04","CCX3072004","Integrate EOU","2008-01-31","2008-02-13","KR","C","SL_ME2","Hrs",24,null,2444.8330220661073,null,2444.8330220661073,null,24,null,2444.8330220661073,null,2444.8330220661073,null,null,2444.8330220661073,1,{"$nulls":8},0.5,1222.4165110330537,1.25,1.25,4,4,"2A"]
["1","03","07","20","04","","LN720-4130","1.03.07.20.04","CCX3072004","Test EOU","2008-02-14","2008-02-27","KR","C","SL_SEE2","Hrs",96,null,10398.036181837708,null,10398.036181837708,null,96,null,10398.036181837708,null,10398.036181837708,null,null,10398.036181837708,1,{"$nulls":8},0.5,5199.018090918854,1.25,1.25,4,4,"2A"]
["1","04","01","01","  ","  ",null,null,null,"Undulator System Management                                 ",{"$nulls":6},15853,107742,1553771.8525894189,117738.22734764712,1633428.770589419,null,15853,107742,1553771.8525894189,117738.22734764712,1671510.0799370657,1093565.7570115926,null,540805.3256195087,null,37138.99730596462,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Geoff Pile"]
["1","04","01","01","01","","UN11_0A205","1.04.01.01.01","CRB4010101","Undulator Documentation","2007-05-01","2007-09-28","A","C","AN_PM2","Hrs",742,null,81752.42824807213,null,81752.42824807213,null,742,null,81752.42824807213,null,81752.42824807213,81752.42824807213,1,{"$nulls":10},0,0,1,1,4,1,"4A"]
["1","04","01","01","01","","UN11_0A240","1.04.01.01.01","CRB4010101","Quality Assurance Oversight","2007-05-01","2007-09-28","A","C","AN_PM2","Hrs",1484,null,163504.85649614426,null,163504.85649614426,null,1484,null,163504.85649614426,null,163504.85649614426,163504.85649614426,1,{"$nulls":10},0,0,1,1,4,1,"4A"]
["1","04","01","01","02","","UN11_00570","1.04.01.01.02","CRB4010102","ANL Indirect Cost Allocation - FY08 (CNST)","2007-10-01","2008-01-31","A","C","AN_MSXX2","$$",null,2000,null,2093.058,2093.058,null,null,2000,null,2093.058,2093.058,null,null,2093.058,1,{"$nulls":8},0,0,1,1,4,1,"4A"]
["1","04","01","01","02","","UN11_0A265","1.04.01.01.02","CRB4010102","ANL Division - PMCS Support","2007-05-01","2007-09-28","A","C","AN_ADMN2","Hrs",186,null,20493.196299381965,null,20493.196299381965,null,186,null,20493.196299381965,null,20493.196299381965,20493.196299381965,1,{"$nulls":10},0,0,1,1,4,1,"4A"]
["1","04","01","02","01","","UN12_0A082","1.04.01.02.01","CRB4010201","Shipping and Storage","2007-05-01","2008-02-29","A","C","AN_MSTR2","$$",null,31869,null,56250.970847177385,null,null,null,31869,null,56250.970847177385,56250.970847177385,28310.521511901774,0.5,27940.44933527561,0.5,{"$nulls":8},0,0,1,1,1,1,"4A"]
["1","04","02","01","04","  ",null,null,null,"Undulator Cable, Tray, and Rack Layout                      ",{"$nulls":37},"Hamid Shoaee"]
["1","04","02","02","01","  ",null,null,null,"Undulator Cam Movers                                        ",{"$nulls":37},"Hamid Shoaee"]
["1","04","02","02","06","  ",null,null,null,"Scanning Wire Motion                                        ",{"$nulls":37},"Hamid Shoaee"]
["1","04","02","02","06","03",null,null,null,"Motor Driver                                                ",{"$nulls":37},"Hamid Shoaee"]
["1","04","02","02","07","05",null,null,null,"Integrate components                                        ",{"$nulls":37},"Hamid Shoaee"]
["1","04","02","03","03","  ",null,null,null,"Beam Finder Wire                                            ",{"$nulls":37},"Hamid Shoaee"]
["1","04","02","04","  ","  ",null,null,null,"Video                                                       ",{"$nulls":37},"Hamid Shoaee"]
["1","04","02","04","01","06",null,null,null,"Integrate components                                        ",{"$nulls":37},"Hamid Shoaee"]
["1","04","02","05","01","01",null,null,null,"Integrate components                                        ",{"$nulls":37},"Hamid Shoaee"]
["1","04","02","06","  ","  ",null,null,null,"Vacuum                                                      ",{"$nulls":37},"Hamid Shoaee"]
["1","04","02","07","02","  ",null,null,null,"Cerenkov Detector                                           ",{"$nulls":37},"Hamid Shoaee"]
["1","04","02","07","03","01",null,null,null,"Signal interface                                            ",{"$nulls":37},"Hamid Shoaee"]
["1","04","02","08","02","01","UN8020B010","1.04.02.08","CB80201BB","RCV: CPUs","2007-10-19","2007-10-19",null,"C","SL_MSEG2","$$",null,8000,null,8774.099136,8774.099136,null,null,8000,null,8774.099136,8774.099136,null,null,8774.099136,1,{"$nulls":13},"B","2G","K. Luchini"]
["1","04","02","08","02","03",null,null,null,"PLC Power Supply Protection                                 ",{"$nulls":6},832,27602,90189.9865392768,29592.214608,119782.20114727678,null,832,27602,90189.9865392768,29592.214608,119782.20114727678,119782.20114727678,null,0,null,0,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Hamid Shoaee"]
["1","04","02","08","02","03","UN8203B020","1.04.02.08","CB80203BB","RCV:  PLC Chassis Accessories","2007-07-19","2007-07-19",null,"C","SL_MSEG2","$$",null,200,null,214.42079999999999,214.42079999999999,null,null,200,null,214.42079999999999,214.42079999999999,214.42079999999999,1,{"$nulls":15},"B","2G","K. Luchini"]
["1","04","02","08","02","03","UN8203B055","1.04.02.08","CB80203BB","RCV:  Touch Panel Display","2007-07-19","2007-07-19",null,"C","SL_MSEG2","$$",null,2000,null,2144.208,2144.208,null,null,2000,null,2144.208,2144.208,2144.208,1,{"$nulls":15},"B","2G","K. Luchini"]
["1","04","02","08","02","03","UN8203C020","1.04.02.08","CB80203CC","Documentation","2007-05-01","2007-05-10",null,"C","SL_PCE2","Hrs",64,null,7212.864325708799,null,7212.864325708799,null,64,null,7212.864325708799,null,7212.864325708799,7212.864325708799,1,{"$nulls":15},"C","2G","K. Luchini"]
["1","04","02","08","02","03","UN8203C025","1.04.02.08","CB80203CC","Pre-install Qual Test and Integration","2007-09-27","2007-10-01",null,"C","SL_PCE2","Hrs",24,null,2704.8241221408,null,2704.8241221408,null,24,null,2704.8241221408,null,2704.8241221408,2704.8241221408,1,0,0,{"$nulls":13},"C","2G","K. Luchini"]
["1","04","02","08","02","03","UN8203C085","1.04.02.08","CB80203CC","RCV:  Digital Input Modules +24V - 32-ch","2007-07-19","2007-07-19",null,"C","SL_MSEG2","$$",null,500,null,536.052,536.052,null,null,500,null,536.052,536.052,536.052,1,{"$nulls":15},"C","2G","K. Luchini"]
["1","04","02","08","02","03","UN8203C100","1.04.02.08","CB80203CC","RCV:  Intra-rack cables and Conectors","2007-07-20","2007-07-20",null,"C","SL_MSEG2","$$",null,350,null,375.2364,375.2364,null,null,350,null,375.2364,375.2364,375.2364,1,{"$nulls":15},"C","2G","K. Luchini"]
["1","04","02","08","02","03","UN8203D010","1.04.02.08","CB80203DD","Develop Touch Panel Displays","2007-06-27","2007-07-31",null,"C","SL_PCE2","Hrs",192,null,21638.5929771264,null,21638.5929771264,null,192,null,21638.5929771264,null,21638.5929771264,21638.5929771264,1,{"$nulls":15},"D","2G","K. Luchini"]
["1","04","02","08","02","04","UN8204B030","1.04.02.08","CB80204BB","RCV: 12Amp Pwr & Prog Modules - QD10","2007-08-06","2007-08-06",null,"C","SL_MSEG2","$$",null,2098,null,2249.274192,2249.274192,null,null,2098,null,2249.274192,2249.274192,2249.274192,1,{"$nulls":15},"B","2G","K. Luchini"]
["1","04","02","08","02","04","UN8204B065","1.04.02.08","CB80204BB","RCV: 12Amp Pwr & Prog Modules - QD8","2007-08-06","2007-08-06",null,"C","SL_MSEG2","$$",null,2098,null,2249.274192,2249.274192,null,null,2098,null,2249.274192,2249.274192,2249.274192,1,{"$nulls":15},"B","2G","K. Luchini"]
["1","04","02","08","02","04","UN8204B080","1.04.02.08","CB80204BB","RCV: 12Amp Pwr & Prog Modules - QF13","2007-08-06","2007-08-06",null,"C","SL_MSEG2","$$",null,2098,null,2249.274192,2249.274192,null,null,2098,null,2249.274192,2249.274192,2249.274192,1,{"$nulls":15},"B","2G","K. Luchini"]
["1","04","02","08","02","04","UN8204C020","1.04.02.08","CB80204CC","RCV: IP Carrier Board","2007-05-01","2007-05-01",null,"C","SL_MSEG2","$$",null,800,null,857.6831999999999,857.6831999999999,null,null,800,null,857.6831999999999,857.6831999999999,857.6831999999999,1,{"$nulls":15},"C","2G","K. Luchini"]
["1","04","02","08","02","04","UN8204C025","1.04.02.08","CB80204CC","RCV: Transition Module","2007-05-01","2007-05-01",null,"C","SL_MSEG2","$$",null,300,null,321.6312,321.6312,null,null,300,null,321.6312,321.6312,321.6312,1,{"$nulls":15},"C","2G","K. Luchini"]
["1","04","02","08","02","04","UN8204D045","1.04.02.08","CB80204DD","RCV: 12Amp Pwr & Prog Modules - QF5","2007-08-06","2007-08-06",null,"C","SL_MSEG2","$$",null,2098,null,2249.274192,2249.274192,null,null,2098,null,2249.274192,2249.274192,2249.274192,1,{"$nulls":15},"D","2G","K. Luchini"]
["1","04","02","08","02","04","UN8204D065","1.04.02.08","CB80204DD","RCV: Amp-36 Pin Connectors","2007-08-06","2007-08-06",null,"C","SL_MSEG2","$$",null,150,null,160.8156,160.8156,null,null,150,null,160.8156,160.8156,160.8156,1,{"$nulls":15},"D","2G","K. Luchini"]
["1","04","02","08","02","04","UN8204E030","1.04.02.08","CB80204EE","RCV: Cables and connectors","2007-05-01","2007-05-01",null,"C","SL_MSEG2","$$",null,300,null,321.6312,321.6312,null,null,300,null,321.6312,321.6312,321.6312,1,{"$nulls":15},"E","2G","K. Luchini"]
["1","04","02","08","02","04","UN8204F045","1.04.02.08","CB80204FF","RCV: 12Amp Pwr & Prog Modules - QD24","2007-08-06","2007-08-06",null,"C","SL_MSEG2","$$",null,2098,null,2249.274192,2249.274192,null,null,2098,null,2249.274192,2249.274192,2249.274192,1,{"$nulls":15},"F","2G","K. Luchini"]
["1","04","02","08","02","04","UN8204F080","1.04.02.08","CB80204FF","RCV: 12Amp Pwr & Prog Modules - QF23","2007-08-06","2007-08-06",null,"C","SL_MSEG2","$$",null,2098,null,2249.274192,2249.274192,null,null,2098,null,2249.274192,2249.274192,2249.274192,1,{"$nulls":15},"F","2G","K. Luchini"]
["1","04","02","08","02","04","UN8204F095","1.04.02.08","CB80204FF","RCV: 12Amp Pwr & Prog Modules - QF29","2007-08-06","2007-08-06",null,"C","SL_MSEG2","$$",null,2098,null,2249.274192,2249.274192,null,null,2098,null,2249.274192,2249.274192,2249.274192,1,{"$nulls":15},"F","2G","K. Luchini"]
["1","04","02","08","02","04","UN8204G030","1.04.02.08","CB80204GG","RCV: Cables and connectors","2007-05-01","2007-05-01",null,"C","SL_MSEG2","$$",null,300,null,321.6312,321.6312,null,null,300,null,321.6312,321.6312,321.6312,1,{"$nulls":15},"G","2G","K. Luchini"]
["1","04","02","08","02","04","UN8204G035","1.04.02.08","CB80204GG","Bench Test and Assembly","2007-06-13","2007-06-13",null,"C","SL_CP2","Hrs",4,null,328.6821882168,null,328.6821882168,null,4,null,328.6821882168,null,328.6821882168,328.6821882168,1,{"$nulls":15},"G","2G","K. Luchini"]
["1","04","02","08","02","04","UN8204H050","1.04.02.08","CB80204HH","RCV: Amp-36 Pin Connectors","2007-08-06","2007-08-06",null,"C","SL_MSEG2","$$",null,150,null,160.8156,160.8156,null,null,150,null,160.8156,160.8156,160.8156,1,{"$nulls":15},"H","2G","K. Luchini"]
["1","04","02","08","02","04","UN8204H080","1.04.02.08","CB80204HH","RCV:  Analog to Digital Converter Module - 16 Ch","2007-05-01","2007-05-01",null,"C","SL_MSEG2","$$",null,2500,null,2680.26,2680.26,null,null,2500,null,2680.26,2680.26,2680.26,1,{"$nulls":15},"H","2G","K. Luchini"]
["1","04","02","08","03","","UN2803B010","1.04.02.08","CB20803BB","RCV: Circuit Breaker, 100A 480V, 3-pole,25kAIC -","2007-09-07","2007-09-07",null,"C","SL_MSEG2","$$",null,640,null,686.1465599999999,686.1465599999999,null,null,640,null,686.1465599999999,686.1465599999999,686.1465599999999,1,{"$nulls":15},"B","2G","K. Luchini"]
["1","04","02","08","03","","UN2803B055","1.04.02.08","CB20803BB","Pre-install Qual Test","2008-03-03","2008-03-05",null,"C","SL_CE2","Hrs",24,null,2767.035076950038,null,2767.035076950038,null,24,null,2767.035076950038,null,2767.035076950038,null,null,2767.035076950038,1,{"$nulls":13},"B","2G","K. Luchini"]
["1","04","02","08","03","","UN2803C050","1.04.02.08","CB20803CC","Pre-install Qual Test","2007-05-09","2007-05-15",null,"C","SL_PCCA2","Hrs",5,null,328.178193354,null,328.178193354,null,5,null,328.178193354,null,328.178193354,328.178193354,1,{"$nulls":15},"C","2G","K. Luchini"]
["1","04","02","08","03","","UN2803D015","1.04.02.08","CB20803EE","RCV: Panel","2008-01-02","2008-01-02",null,"C","SL_MSEG2","$$",null,50,null,54.8381196,54.8381196,null,null,50,null,54.8381196,54.8381196,null,null,54.8381196,1,{"$nulls":13},"E","2G","K. Luchini"]
["1","04","02","08","04","","UN2804B010","1.04.02.08","CB20804BB","Integration Testing","2008-04-01","2008-04-14",null,"C","SL_PCT2","Hrs",27,null,1704.2323239032453,null,1704.2323239032453,null,27,null,1704.2323239032453,null,1704.2323239032453,null,null,1704.2323239032453,1,{"$nulls":13},"B","2G","K. Luchini"]
["1","04","02","08","04","","UN2804B010","1.04.02.08","CB20804BB","Integration Testing","2008-04-01","2008-04-14",null,"C","SL_PCE2","Hrs",16,null,1844.6900513000253,null,1844.6900513000253,null,16,null,1844.6900513000253,null,1844.6900513000253,null,null,1844.6900513000253,1,{"$nulls":13},"B","2G","K. Luchini"]
["1","04","02","10","01","","UN21001035","1.04.02.10","CBB1040210","Conduct FDR","2007-06-05","2007-06-05",null,"C","AN_CE2","Hrs",8,null,881.4277978228802,null,881.4277978228802,null,8,null,881.4277978228802,null,881.4277978228802,881.4277978228802,1,{"$nulls":15},10,"2G","ANL"]
["1","04","02","10","02","","UN21002035","1.04.02.10","CBC1040210","Integrate UCM Software with SLAC","2007-07-09","2007-07-13",null,"C","AN_CE2","Hrs",40,null,4407.138989114401,null,4407.138989114401,null,40,null,4407.138989114401,null,4407.138989114401,4407.138989114401,1,{"$nulls":15},10,"2G","ANL"]
["1","04","02","10","03","","UN21003005","1.04.02.10","CBD1040210","Prepare requisition for UCMI Prototype","2007-06-13","2007-06-13",null,"C","AN_CE2","Hrs",8,null,881.4277978228802,null,881.4277978228802,null,8,null,881.4277978228802,null,881.4277978228802,881.4277978228802,1,{"$nulls":15},10,"2G","ANL"]
["1","04","02","10","06","  ",null,null,null,"UCMI Blade IOC First Article                                ",{"$nulls":6},8,10000,881.4277978228802,10230,11111.42779782288,null,8,10000,881.4277978228802,10230,11111.42779782288,11111.42779782288,null,0,null,0,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Hamid Shoaee"]
["1","04","02","10","08","  ",null,null,null,"UCM First Article Testing and QA                            ",{"$nulls":6},96,0,10820.407646073678,0,10820.407646073678,null,96,0,10820.407646073678,0,10820.407646073678,0,null,10820.407646073678,null,0,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Hamid Shoaee"]
["1","04","02","10","09","","UN21009001","1.04.02.10","CBH1040210","Prepare req for production UCMI","2008-01-21","2008-01-21",null,"C","AN_ME2","Hrs",8,null,901.7006371728064,null,901.7006371728064,null,8,null,901.7006371728064,null,901.7006371728064,null,null,901.7006371728064,1,{"$nulls":13},10,"2G","ANL"]
["1","04","02","10","11","  ",null,null,null,"Procure Production Motors                                   ",{"$nulls":6},248,350000,21865.34115971568,358050,379915.34115971567,null,248,350000,21865.34115971568,358050,379915.34115971567,379915.34115971567,null,0,null,0,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Hamid Shoaee"]
["1","04","02","10","11","","UN21011015","1.04.02.10","CBM1040210","RCV production Motors","2007-07-06","2007-07-06",null,"C","AN_MSEG2","$$",null,350000,null,358050,358050,null,null,350000,null,358050,358050,358050,1,{"$nulls":15},10,"2G","ANL"]
["1","04","02","10","13","  ",null,null,null,"Procure Production RTD                                      ",{"$nulls":6},248,25000,21865.34115971568,25575,47440.34115971568,null,248,25000,21865.34115971568,25575,47440.34115971568,47440.34115971568,null,0,null,0,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Hamid Shoaee"]
["1","04","02","12","01","","UN21201001","1.04.02.12","CBB1040212","Undulator rack design","2007-05-01","2007-05-14",null,"C","AN_CT2","Hrs",80,null,5174.997596366401,null,5174.997596366401,null,80,null,5174.997596366401,null,5174.997596366401,5174.997596366401,1,{"$nulls":15},12,"2G","ANL"]
["1","04","02","12","01","","UN21201015","1.04.02.12","CBB1040212","Motor power supply design","2007-05-30","2007-06-05",null,"C","AN_CT2","Hrs",40,null,2587.4987981832005,null,2587.4987981832005,null,40,null,2587.4987981832005,null,2587.4987981832005,2587.4987981832005,1,{"$nulls":15},12,"2G","ANL"]
["1","04","02","12","01","","UN21201045","1.04.02.12","CBB1040212","Install rack in LTT and populate","2007-10-01","2007-10-05",null,"C","AN_CE2","Hrs",40,null,4508.503185864032,null,4508.503185864032,null,40,null,4508.503185864032,null,4508.503185864032,null,null,4508.503185864032,1,{"$nulls":13},12,"2G","ANL"]
["1","04","02","12","01","","UN21201100","1.04.02.12","CBB1040212","Assemble production components","2008-03-12","2008-03-25",null,"C","AN_CT2","Hrs",80,null,5294.022541082828,null,5294.022541082828,null,80,null,5294.022541082828,null,5294.022541082828,null,null,5294.022541082828,1,{"$nulls":13},12,"2G","ANL"]
["1","04","02","12","02","  ",null,null,null,"Intra-Undulator Cabling                                     ",{"$nulls":6},212,105000,14259.635687650323,107415,121674.63568765033,null,212,105000,14259.635687650323,107415,121674.63568765033,121674.63568765033,null,0,null,0,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Hamid Shoaee"]
["1","04","02","12","03","  ",null,null,null,"Electronics Interface Assembly                              ",{"$nulls":6},88,112000,6056.425394189281,114576,120632.42539418928,null,88,112000,6056.425394189281,114576,120632.42539418928,120632.42539418928,null,0,null,0,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Hamid Shoaee"]
["1","04","02","12","03","","UN21203013","1.04.02.12","CBD1040212","RCV: First Article EIA","2007-06-26","2007-06-26",null,"C","AN_MSEG2","$$",null,4000,null,4092,4092,null,null,4000,null,4092,4092,4092,1,{"$nulls":15},12,"2G","ANL"]
["1","04","02","13","01","","UN21301010","1.04.02.13","CBB1040213","EPICS support","2007-05-01","2007-05-04",null,"C","AN_CE2","Hrs",32,null,3525.7111912915207,null,3525.7111912915207,null,32,null,3525.7111912915207,null,3525.7111912915207,3525.7111912915207,1,{"$nulls":15},13,"2G","ANL"]
["1","04","02","17","","","UN21701005","1.04.02.17","CBB1040217","Technical Managment - OPC","2008-04-01","2008-10-29","A","C","AN_CE2","Hrs",521,null,58902.48391621913,null,58902.48391621913,null,521,null,58902.48391621913,null,58902.48391621913,null,null,51086.040552929386,0.87,7816.443363289743,0.13,{"$nulls":11},"G","2G"]
["1","04","02","20","02","","UN2002B005","1.04.02.20","CB22002BB","Software design","2008-01-02","2008-01-23",null,"C","SL_CP2","Hrs",40,null,3362.418785457864,null,3362.418785457864,null,40,null,3362.418785457864,null,3362.418785457864,null,null,3362.418785457864,1,{"$nulls":13},"B","2G","ANL"]
["1","04","02","20","03","","UN2003B050","1.04.02.20","CB22003BB","Integrate & Test MPS TIU Hardware","2008-03-05","2008-03-18",null,"C","SL_CP2","Hrs",120,null,10087.256356373591,null,10087.256356373591,null,120,null,10087.256356373591,null,10087.256356373591,null,null,10087.256356373591,1,{"$nulls":13},"B","2G","ANL"]
["1","04","02","20","04","","UN2004B040","1.04.02.20","CB22004BB","Assemble & Pre-install MPS PLIC Production Units","2008-02-20","2008-03-04",null,"C","SL_TMUE2","Hrs",80,null,7835.40448416,null,7835.40448416,null,80,null,7835.40448416,null,7835.40448416,null,null,7835.40448416,1,{"$nulls":13},"B","2G","ANL"]
["1","04","02","20","05","","UN2005B040","1.04.02.20","CB22005BB","RCV: MPS TOROIDS Hardware","2008-01-15","2008-01-15",null,"C","SL_MSEG2","$$",null,28000,null,30709.346976,30709.346976,null,null,28000,null,30709.346976,30709.346976,null,null,30709.346976,1,{"$nulls":13},"B","2G","ANL"]
["1","04","02","21","","","UN221B0045","1.04.02.21","CB40221BB","RCV: Connector and Cables","2008-02-14","2008-02-14",null,"C","SL_MSEG2","$$",null,1000,null,1096.762392,1096.762392,null,null,1000,null,1096.762392,1096.762392,null,null,1096.762392,1,{"$nulls":13},"B","2G","ANL"]
["1","04","02","21","","","UN221B0070","1.04.02.21","CB40221BB","Integration & Test","2008-03-28","2008-04-10",null,"C","SL_CP2","Hrs",16,null,1344.9675141831456,null,1344.9675141831456,null,16,null,1344.9675141831456,null,1344.9675141831456,null,null,1344.9675141831456,1,{"$nulls":13},"B","2G","ANL"]
["1","04","02","22","","","UN222B0053","1.04.02.22","CB40222BB","RCV: 33 Dgitizers Chassis","2007-09-25","2007-09-25",null,"C","SL_MSEG2","$$",null,33000,null,35379.432,35379.432,null,null,33000,null,35379.432,35379.432,35379.432,1,{"$nulls":15},"B","2G","ANL"]
["1","04","02","22","","","UN222B0057","1.04.02.22","CB40222BB","RCV: Jumper Cables for tunner - 100","2007-09-25","2007-09-25",null,"C","SL_MSEG2","$$",null,5000,null,5360.52,5360.52,null,null,5000,null,5360.52,5360.52,5360.52,1,{"$nulls":15},"B","2G","ANL"]
["1","04","02","23","","","UN223B0010","1.04.02.23","CB40223BB","DBs and Displays","2008-01-02","2008-01-15",null,"C","SL_CP2","Hrs",80,null,6724.837570915728,null,6724.837570915728,null,80,null,6724.837570915728,null,6724.837570915728,null,null,6724.837570915728,1,{"$nulls":13},"B","2G","ANL"]
["1","04","02","23","","","UN223B0070","1.04.02.23","CB40223BB","Assemble & Pre-install Production Units","2008-01-02","2008-01-15",null,"C","SL_CP2","Hrs",16,null,1344.9675141831456,null,1344.9675141831456,null,16,null,1344.9675141831456,null,1344.9675141831456,null,null,1344.9675141831456,1,{"$nulls":13},"B","2G","ANL"]
["1","04","03","03","  ","  ",null,null,null,"1st Article Undulators & Long Lead Procurements             ",{"$nulls":6},2534,659581,226255.03025506515,667200.3188562836,758134.388255065,null,2534,659581,226255.03025506515,667200.3188562836,893455.3491113486,471467.0257631819,null,406504.4674155839,null,15483.85593258301,null,0,null,0,null,0,null,null,118619.3789147608,{"$nulls":6},"Geoff Pile"]
["1","04","03","03","03","  ",null,null,null,"Magnet Poles (LLP)                                          ",{"$nulls":37},"Geoff Pile"]
["1","04","03","03","04","03","UN33_40310","1.04.03.03.04","CRB4030304","Vendor Prep & Documentation-Support/Mover System","2007-05-09","2007-05-22","A","C","AN_CE2","Hrs",16,null,1762.8555956457603,null,1762.8555956457603,null,16,null,1762.8555956457603,null,1762.8555956457603,1762.8555956457603,1,{"$nulls":10},0.15,264.42833934686405,1.1,1.05,7,3,"4A"]
["1","04","03","03","04","03","UN33_40320","1.04.03.03.04","CRB4030304","Factory Accept Testing 1st Art - Supt/Mover Sys","2007-07-20","2007-07-24","A","C","AN_PHS2","Hrs",24,null,2644.2833934686405,null,2644.2833934686405,null,24,null,2644.2833934686405,null,2644.2833934686405,2644.2833934686405,1,{"$nulls":10},0.15,396.6425090202961,1.1,1.05,7,3,"4A"]
["1","04","03","03","04","03","UN33_40335","1.04.03.03.04","CRB4030304","Ship 1st Articles to SLAC","2007-08-31","2007-09-05",null,"C","AN_MSEG2","$$",null,5000,null,5115,5115,null,null,5000,null,5115,5115,5115,1,{"$nulls":10},0.15,767.25,1.1,1.05,7,3,"4A"]
["1","04","03","03","04","03","UN33_40A58","1.04.03.03.04","CRB4030304","Survey  & Align/Prep for Accept Msmts","2007-05-01","2007-09-28",null,"C","AN_MES2","Hrs",82,null,9034.634927684521,null,9034.634927684521,null,82,null,9034.634927684521,null,9034.634927684521,9034.634927684521,1,{"$nulls":10},0.15,1355.1952391526781,1.1,1.05,7,3,"4A"]
["1","04","03","03","04","03","UN33_4A300","1.04.03.03.04","CRB4030304","Evaluate Bids -  Support/Mover System","2007-05-01","2007-05-07","A","C","AN_CE2","Hrs",2,null,220.35694945572004,null,220.35694945572004,null,2,null,220.35694945572004,null,220.35694945572004,220.35694945572004,1,{"$nulls":10},0.15,33.053542418358006,1.1,1.05,7,3,"4A"]
["1","04","03","03","06","  ",null,null,null,"Integrated Single-Undulator Module Test                     ",{"$nulls":6},1810,125000,156253.04898384906,130187.8616255144,156253.04898384906,null,1810,125000,156253.04898384906,130187.8616255144,286440.91060936346,66011.07404989447,null,215714.7598416194,null,4715.076717849604,null,0,null,0,null,0,null,null,28644.09106093635,{"$nulls":6},"Geoff Pile"]
["1","04","03","04","  ","  ",null,null,null,"Production Undulator Magnet Assembly & Supports             ",{"$nulls":6},860,2626694,87213.01835031384,2627077.9620000003,2714290.9803503137,null,860,2626694,87213.01835031384,2627077.9620000003,2714290.9803503137,575331.8495616936,null,2138959.13078862,null,0,null,0,null,0,null,0,null,null,675157.1526875785,{"$nulls":6},"Geoff Pile"]
["1","04","03","04","01","","UN34_00A64","1.04.03.04.01","CRB4030401","Misc. Assembly and Tuning Items","2007-05-01","2007-09-28",null,"C","AN_MSEG2","$$",null,14250,null,14577.75,14577.75,null,null,14250,null,14577.75,14577.75,14577.75,1,{"$nulls":10},0.05,728.8875,1,1.05,7,3,"4A"]
["1","04","03","04","03","","UN34_00016","1.04.03.04.03","CRB4030403","Vendor Fab Support/Mover Production Units","2007-09-04","2008-01-11","A","C","AN_CE2","Hrs",100,null,11218.21855938411,null,11218.21855938411,null,100,null,11218.21855938411,null,11218.21855938411,2347.999233359465,0.21,8870.219326024644,0.79,{"$nulls":8},0.25,2804.5546398460274,1.15,1.1,4,3,"4A"]
["1","04","03","04","03","","UN34_00050","1.04.03.04.03","CRB4030403","RCV: 2 Support/Movers","2007-09-25","2007-09-25","A","C","AA_MSSF2","$$",null,180000,null,180000,180000,null,null,180000,null,180000,180000,180000,1,{"$nulls":10},0.25,45000,1.15,1.1,4,3,"4A"]
["1","04","03","04","03","","UN34_00195","1.04.03.04.03","CRB4030403","RCV: 2 Support/Movers","2007-11-29","2007-11-29","A","C","AA_MSSF2","$$",null,180000,null,180000,180000,null,null,180000,null,180000,180000,null,null,180000,1,{"$nulls":8},0.25,45000,1.15,1.1,4,3,"4A"]
["1","04","03","05","01","","UN35_Q0110","1.04.03.05.01","CRB4030501","Vendor Fab/Assy - Quad Magnet 1st Article (Q1)","2007-05-01","2007-05-23","A","C","AN_MSSF2","$$",null,19000,null,19000,19000,null,null,19000,null,19000,19000,19000,1,{"$nulls":10},0.15,2850,1.1,1.05,7,3,"4A"]
["1","04","03","05","01","","UN35_Q0410","1.04.03.05.01","CRB4030501","Vendor Fab/Assy - Quad Mag (Q4,Q5)","2007-09-05","2007-09-14","A","C","AN_MSSF2","$$",null,15000,null,15000,15000,null,null,15000,null,15000,15000,15000,1,{"$nulls":10},0.15,2250,1.1,1.05,7,3,"4A"]
["1","04","03","05","01","","UN35_Q2410","1.04.03.05.01","CRB4030501","Vendor Fab/Assy - Quad Mag (Q24,Q25,Q26,Q27)","2007-12-11","2008-01-02","A","C","AN_MSSF2","$$",null,15000,null,15000,15000,null,null,15000,null,15000,15000,null,null,15000,1,{"$nulls":8},0.15,2250,1.1,1.05,7,3,"4A"]
["1","04","03","05","01","","UN35_QA005","1.04.03.05.01","CRB4030501","ANL Vendor Management & 1st/2nd Art Testing","2007-05-01","2008-05-12","A","C","AN_MSEQ2","$$",null,16625,null,17239.794087533155,null,null,null,16625,null,17239.794087533155,17239.794087533155,6996.521207937859,0.41,10243.272879595295,0.59,{"$nulls":8},0.15,2585.9691131299733,1.1,1.05,7,3,"4A"]
["1","04","03","05","03","","UN35_A1134","1.04.03.05.03","CRB4030503","ANL Vendor Mgmt & 1st Art Test - Stages & Stands","2007-05-01","2007-10-04","A","C","AN_ME2","Hrs",162,null,17856.80761739094,null,17856.80761739094,null,162,null,17856.80761739094,null,17856.80761739094,17513.40747090265,0.98,343.4001464882873,0.02,{"$nulls":8},0.2,3571.3615234781882,1.1,1.1,3,3,"4A"]
["1","04","03","06","01","01",null,null,null,"Undulator Test Stand Prototype                              ",{"$nulls":37},"Rod Pope"]
["1","04","03","06","01","06",null,null,null,"Quad Strength and Field Quality                             ",{"$nulls":37},"Rod Pope"]
["1","04","03","06","01","09","UN36_RA265","1.04.03.06.01","CRB4030601","Girder Assy & Install Prep","2007-07-17","2007-11-15","S","C","SL_MES2","Hrs",696,null,56196.735538260225,null,56196.735538260225,null,696,null,56196.735538260225,null,56196.735538260225,35297.12314799816,0.63,20899.612390262067,0.37,{"$nulls":8},0.4,22478.69421530409,1.3,1.1,4,3,"4B"]
["1","04","03","06","02","01","UN362_0015","1.04.03.06.02","CRB4030602","Undulator Shimming Prototype","2007-05-30","2007-06-08","S","C","SL_MES2","Hrs",40,null,3202.3058205599996,null,3202.3058205599996,null,40,null,3202.3058205599996,null,3202.3058205599996,3202.3058205599996,1,{"$nulls":15},4,"4B"]
["1","04","03","06","02","01","UN362_0016","1.04.03.06.02","CRB4030602","Assemble Girder - 01","2008-03-05","2008-04-01","S","C","SL_MFAT2","Hrs",102,null,8966.660472,null,8966.660472,null,102,null,8966.660472,null,8966.660472,null,null,8966.660472,1,{"$nulls":8},0.45,4034.9972124,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","01","UN362_0025","1.04.03.06.02","CRB4030602","Shim Undulator - 03","2007-06-11","2007-06-13","S","C","SL_MES2","Hrs",8,null,640.4611641119999,null,640.4611641119999,null,8,null,640.4611641119999,null,640.4611641119999,640.4611641119999,1,{"$nulls":15},4,"4B"]
["1","04","03","06","02","01","UN362_0036","1.04.03.06.02","CRB4030602","Assemble Girder - 03","2008-04-02","2008-04-29","S","C","SL_MFAT2","Hrs",102,null,8966.660472,null,8966.660472,null,102,null,8966.660472,null,8966.660472,null,null,8966.660472,1,{"$nulls":8},0.45,4034.9972124,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","01","UN362_0046","1.04.03.06.02","CRB4030602","Assemble Girder - 04","2008-04-07","2008-05-02","S","C","SL_MFAT2","Hrs",102,null,8966.660472,null,8966.660472,null,102,null,8966.660472,null,8966.660472,null,null,8966.660472,1,{"$nulls":8},0.45,4034.9972124,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","01","UN362_0056","1.04.03.06.02","CRB4030602","Assemble Girder - 05","2008-04-10","2008-05-07","S","C","SL_MES2","Hrs",70,null,5732.927995257539,null,5732.927995257539,null,70,null,5732.927995257539,null,5732.927995257539,null,null,5732.927995257539,1,{"$nulls":8},0.45,2579.8175978658924,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","01","UN362_0062","1.04.03.06.02","CRB4030602","Fiducialize Undulator - 06","2007-05-07","2007-05-14","S","C","SL_MFAT2","Hrs",40,null,3437.28,null,3437.28,null,40,null,3437.28,null,3437.28,3437.28,1,{"$nulls":10},0.4,1374.9120000000003,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0072","1.04.03.06.02","CRB4030602","Fiducialize Undulator - 07","2007-05-22","2007-05-30","S","C","SL_MFAT2","Hrs",40,null,3437.28,null,3437.28,null,40,null,3437.28,null,3437.28,3437.28,1,{"$nulls":10},0.4,1374.9120000000003,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0086","1.04.03.06.02","CRB4030602","Assemble Girder - 08","2008-04-23","2008-05-20","S","C","SL_SEE2","Hrs",8,null,866.5030151531423,null,866.5030151531423,null,8,null,866.5030151531423,null,866.5030151531423,null,null,866.5030151531423,1,{"$nulls":8},0.45,389.92635681891403,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","01","UN362_0091","1.04.03.06.02","CRB4030602","Tune Undulator - 09","2007-05-22","2007-05-30","S","C","SL_MFAT2","Hrs",180,null,15467.76,null,15467.76,null,180,null,15467.76,null,15467.76,15467.76,1,{"$nulls":10},0.4,6187.104,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0101","1.04.03.06.02","CRB4030602","Tune Undulator - 10","2007-05-30","2007-06-05","S","C","SL_MFAT2","Hrs",180,null,15467.76,null,15467.76,null,180,null,15467.76,null,15467.76,15467.76,1,{"$nulls":10},0.4,6187.104,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0112","1.04.03.06.02","CRB4030602","Fiducialize Undulator - 11","2007-06-14","2007-06-21","S","C","SL_MFAT2","Hrs",40,null,3437.28,null,3437.28,null,40,null,3437.28,null,3437.28,3437.28,1,{"$nulls":10},0.4,1374.9120000000003,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0116","1.04.03.06.02","CRB4030602","Assemble Girder - 11","2008-05-06","2008-06-03","S","C","SL_MFAT2","Hrs",102,null,8966.660472,null,8966.660472,null,102,null,8966.660472,null,8966.660472,null,null,8966.660472,1,{"$nulls":8},0.45,4034.9972124,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","01","UN362_0126","1.04.03.06.02","CRB4030602","Assemble Girder - 12","2008-05-09","2008-06-06","S","C","SL_MFAT2","Hrs",102,null,8966.660472,null,8966.660472,null,102,null,8966.660472,null,8966.660472,null,null,8966.660472,1,{"$nulls":8},0.45,4034.9972124,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","01","UN362_0132","1.04.03.06.02","CRB4030602","Fiducialize Undulator - 13","2007-06-28","2007-07-02","S","C","SL_PHSS2","Hrs",16,null,1485.0014788224,null,1485.0014788224,null,16,null,1485.0014788224,null,1485.0014788224,1485.0014788224,1,{"$nulls":10},0.4,594.0005915289601,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0142","1.04.03.06.02","CRB4030602","Fiducialize Undulator - 14","2007-07-12","2007-07-16","S","C","SL_PHSS2","Hrs",16,null,1485.0014788224,null,1485.0014788224,null,16,null,1485.0014788224,null,1485.0014788224,1485.0014788224,1,{"$nulls":10},0.4,594.0005915289601,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0152","1.04.03.06.02","CRB4030602","Fiducialize Undulator - 15","2007-07-19","2007-07-23","S","C","SL_PHSS2","Hrs",16,null,1485.0014788224,null,1485.0014788224,null,16,null,1485.0014788224,null,1485.0014788224,1485.0014788224,1,{"$nulls":10},0.4,594.0005915289601,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0161","1.04.03.06.02","CRB4030602","Tune Undulator - 16","2007-07-12","2007-07-25","S","C","SL_MFAT2","Hrs",180,null,15467.76,null,15467.76,null,180,null,15467.76,null,15467.76,15467.76,1,{"$nulls":10},0.4,6187.104,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0171","1.04.03.06.02","CRB4030602","Tune Undulator - 17","2007-07-19","2007-08-01","S","C","SL_MFAT2","Hrs",180,null,15467.76,null,15467.76,null,180,null,15467.76,null,15467.76,15467.76,1,{"$nulls":10},0.4,6187.104,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0182","1.04.03.06.02","CRB4030602","Fiducialize Undulator - 18","2007-08-16","2007-08-20","S","C","SL_MFAT2","Hrs",40,null,3437.28,null,3437.28,null,40,null,3437.28,null,3437.28,3437.28,1,{"$nulls":10},0.4,1374.9120000000003,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0182","1.04.03.06.02","CRB4030602","Fiducialize Undulator - 18","2007-08-16","2007-08-20","S","C","SL_MES2","Hrs",48,null,3842.766984671999,null,3842.766984671999,null,48,null,3842.766984671999,null,3842.766984671999,3842.766984671999,1,{"$nulls":10},0.4,1537.1067938687997,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0196","1.04.03.06.02","CRB4030602","Assemble Girder - 19","2008-06-10","2008-07-08","S","C","SL_MFAT2","Hrs",102,null,8966.660472,null,8966.660472,null,102,null,8966.660472,null,8966.660472,null,null,8966.660472,1,{"$nulls":8},0.45,4034.9972124,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","01","UN362_0202","1.04.03.06.02","CRB4030602","Fiducialize Undulator - 20","2007-08-30","2007-09-04","S","C","SL_PHSS2","Hrs",16,null,1485.0014788224,null,1485.0014788224,null,16,null,1485.0014788224,null,1485.0014788224,1485.0014788224,1,{"$nulls":10},0.4,594.0005915289601,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0212","1.04.03.06.02","CRB4030602","Fiducialize Undulator - 21","2007-09-07","2007-09-11","S","C","SL_PHSS2","Hrs",16,null,1485.0014788224,null,1485.0014788224,null,16,null,1485.0014788224,null,1485.0014788224,1485.0014788224,1,{"$nulls":10},0.4,594.0005915289601,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0222","1.04.03.06.02","CRB4030602","Fiducialize Undulator - 22","2007-09-14","2007-09-18","S","C","SL_MES2","Hrs",48,null,3842.766984671999,null,3842.766984671999,null,48,null,3842.766984671999,null,3842.766984671999,3842.766984671999,1,{"$nulls":10},0.4,1537.1067938687997,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0226","1.04.03.06.02","CRB4030602","Assemble Girder - 22","2008-06-23","2008-07-21","S","C","SL_MES2","Hrs",70,null,5732.927995257539,null,5732.927995257539,null,70,null,5732.927995257539,null,5732.927995257539,null,null,5732.927995257539,1,{"$nulls":8},0.45,2579.8175978658924,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","01","UN362_0236","1.04.03.06.02","CRB4030602","Assemble Girder - 23","2008-06-26","2008-07-24","S","C","SL_MES2","Hrs",70,null,5732.927995257539,null,5732.927995257539,null,70,null,5732.927995257539,null,5732.927995257539,null,null,5732.927995257539,1,{"$nulls":8},0.45,2579.8175978658924,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","01","UN362_0252","1.04.03.06.02","CRB4030602","Fiducialize Undulator - 25","2007-10-05","2007-10-09","S","C","SL_PHSS2","Hrs",16,null,1519.1565128353152,null,1519.1565128353152,null,16,null,1519.1565128353152,null,1519.1565128353152,null,null,1519.1565128353152,1,{"$nulls":8},0.4,607.6626051341261,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0252","1.04.03.06.02","CRB4030602","Fiducialize Undulator - 25","2007-10-05","2007-10-09","S","C","SL_MFAT2","Hrs",40,null,3516.33744,null,3516.33744,null,40,null,3516.33744,null,3516.33744,null,null,3516.33744,1,{"$nulls":8},0.4,1406.534976,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0266","1.04.03.06.02","CRB4030602","Assemble Girder - 26","2008-07-10","2008-08-06","S","C","SL_SEE2","Hrs",8,null,866.5030151531423,null,866.5030151531423,null,8,null,866.5030151531423,null,866.5030151531423,null,null,866.5030151531423,1,{"$nulls":8},0.45,389.92635681891403,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","01","UN362_0271","1.04.03.06.02","CRB4030602","Tune Undulator - 27","2007-10-05","2007-10-18","S","C","SL_MFAT2","Hrs",180,null,15823.518479999999,null,15823.518479999999,null,180,null,15823.518479999999,null,15823.518479999999,null,null,15823.518479999999,1,{"$nulls":8},0.4,6329.407392,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0281","1.04.03.06.02","CRB4030602","Tune Undulator - 28","2007-10-12","2007-10-25","S","C","SL_MFAT2","Hrs",180,null,15823.518479999999,null,15823.518479999999,null,180,null,15823.518479999999,null,15823.518479999999,null,null,15823.518479999999,1,{"$nulls":8},0.4,6329.407392,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0292","1.04.03.06.02","CRB4030602","Fiducialize Undulator - 29","2007-11-02","2007-11-06","S","C","SL_MFAT2","Hrs",40,null,3516.33744,null,3516.33744,null,40,null,3516.33744,null,3516.33744,null,null,3516.33744,1,{"$nulls":8},0.4,1406.534976,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0296","1.04.03.06.02","CRB4030602","Assemble Girder - 29","2008-07-23","2008-08-19","S","C","SL_MFAT2","Hrs",102,null,8966.660472,null,8966.660472,null,102,null,8966.660472,null,8966.660472,null,null,8966.660472,1,{"$nulls":8},0.45,4034.9972124,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","01","UN362_0306","1.04.03.06.02","CRB4030602","Assemble Girder - 30","2008-07-28","2008-08-22","S","C","SL_MFAT2","Hrs",102,null,8966.660472,null,8966.660472,null,102,null,8966.660472,null,8966.660472,null,null,8966.660472,1,{"$nulls":8},0.45,4034.9972124,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","01","UN362_0321","1.04.03.06.02","CRB4030602","Tune Undulator - 32","2007-11-09","2007-11-26","S","C","SL_MFAT2","Hrs",180,null,15823.518479999999,null,15823.518479999999,null,180,null,15823.518479999999,null,15823.518479999999,null,null,15823.518479999999,1,{"$nulls":8},0.4,6329.407392,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0326","1.04.03.06.02","CRB4030602","Assemble Girder - 32","2008-08-05","2008-09-02","S","C","SL_MES2","Hrs",70,null,5732.927995257539,null,5732.927995257539,null,70,null,5732.927995257539,null,5732.927995257539,null,null,5732.927995257539,1,{"$nulls":8},0.45,2579.8175978658924,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","01","UN362_0336","1.04.03.06.02","CRB4030602","Assemble Girder - 33","2008-08-08","2008-09-05","S","C","SL_SEE2","Hrs",8,null,866.5030151531423,null,866.5030151531423,null,8,null,866.5030151531423,null,866.5030151531423,null,null,866.5030151531423,1,{"$nulls":8},0.45,389.92635681891403,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","02",null,null,null,"F/MM Quadrupoles                                            ",{"$nulls":6},1508,0,127970.19326380557,0,127970.19326380557,null,1508,0,127970.19326380557,0,127970.19326380557,0,null,127970.19326380557,null,0,null,0,null,0,null,0,null,null,44789.56764233212,{"$nulls":6},"Rod Pope"]
["1","04","03","06","02","02","UN36_02030","1.04.03.06.02","CRB4030602","Measure and Fiducialize Quadrupole - 02","2007-11-08","2007-11-12","S","C","SL_PHSS2","Hrs",4,null,379.7891282088288,null,379.7891282088288,null,4,null,379.7891282088288,null,379.7891282088288,null,null,379.7891282088288,1,{"$nulls":8},0.35,132.92619487309008,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02070","1.04.03.06.02","CRB4030602","Measure and Fiducialize Quadrupole - 04","2007-11-16","2007-11-20","S","C","SL_PHS2","Hrs",20,null,1492.0287179632558,null,1492.0287179632558,null,20,null,1492.0287179632558,null,1492.0287179632558,null,null,1492.0287179632558,1,{"$nulls":8},0.35,522.2100512871394,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02100","1.04.03.06.02","CRB4030602","Measure and Fiducialize Quadrupole - 06","2007-11-28","2007-11-30","S","C","SL_PHSS2","Hrs",4,null,379.7891282088288,null,379.7891282088288,null,4,null,379.7891282088288,null,379.7891282088288,null,null,379.7891282088288,1,{"$nulls":8},0.35,132.92619487309008,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02100","1.04.03.06.02","CRB4030602","Measure and Fiducialize Quadrupole - 06","2007-11-28","2007-11-30","S","C","SL_MES2","Hrs",4,null,327.59588544328795,null,327.59588544328795,null,4,null,327.59588544328795,null,327.59588544328795,null,null,327.59588544328795,1,{"$nulls":8},0.35,114.65855990515078,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02160","1.04.03.06.02","CRB4030602","Measure and Fiducialize Quadrupole - 09","2007-12-11","2007-12-13","S","C","SL_PHSS2","Hrs",4,null,379.7891282088288,null,379.7891282088288,null,4,null,379.7891282088288,null,379.7891282088288,null,null,379.7891282088288,1,{"$nulls":8},0.35,132.92619487309008,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02160","1.04.03.06.02","CRB4030602","Measure and Fiducialize Quadrupole - 09","2007-12-11","2007-12-13","S","C","SL_PHS2","Hrs",20,null,1492.0287179632558,null,1492.0287179632558,null,20,null,1492.0287179632558,null,1492.0287179632558,null,null,1492.0287179632558,1,{"$nulls":8},0.35,522.2100512871394,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02200","1.04.03.06.02","CRB4030602","Measure and Fiducialize Quadrupole - 11","2008-01-03","2008-01-04","S","C","SL_MFAT2","Hrs",8,null,703.267488,null,703.267488,null,8,null,703.267488,null,703.267488,null,null,703.267488,1,{"$nulls":8},0.35,246.14362079999998,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02220","1.04.03.06.02","CRB4030602","Measure and Fiducialize Quadrupole - 12","2008-01-07","2008-01-08","S","C","SL_PHS2","Hrs",20,null,1492.0287179632558,null,1492.0287179632558,null,20,null,1492.0287179632558,null,1492.0287179632558,null,null,1492.0287179632558,1,{"$nulls":8},0.35,522.2100512871394,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02260","1.04.03.06.02","CRB4030602","Measure and Fiducialize Quadrupole - 14","2008-01-11","2008-01-14","S","C","SL_PHSS2","Hrs",4,null,379.7891282088288,null,379.7891282088288,null,4,null,379.7891282088288,null,379.7891282088288,null,null,379.7891282088288,1,{"$nulls":8},0.35,132.92619487309008,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02300","1.04.03.06.02","CRB4030602","Measure and Fiducialize Quadrupole - 16","2008-01-17","2008-01-18","S","C","SL_PHS2","Hrs",20,null,1492.0287179632558,null,1492.0287179632558,null,20,null,1492.0287179632558,null,1492.0287179632558,null,null,1492.0287179632558,1,{"$nulls":8},0.35,522.2100512871394,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02340","1.04.03.06.02","CRB4030602","Measure and Fiducialize Quadrupole - 18","2008-01-24","2008-01-25","S","C","SL_PHSS2","Hrs",4,null,379.7891282088288,null,379.7891282088288,null,4,null,379.7891282088288,null,379.7891282088288,null,null,379.7891282088288,1,{"$nulls":8},0.35,132.92619487309008,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02340","1.04.03.06.02","CRB4030602","Measure and Fiducialize Quadrupole - 18","2008-01-24","2008-01-25","S","C","SL_MES2","Hrs",4,null,327.59588544328795,null,327.59588544328795,null,4,null,327.59588544328795,null,327.59588544328795,null,null,327.59588544328795,1,{"$nulls":8},0.35,114.65855990515078,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02390","1.04.03.06.02","CRB4030602","Measure and Fiducialize Quadrupole - 21","2008-01-30","2008-01-30","S","C","SL_PHSS2","Hrs",4,null,379.7891282088288,null,379.7891282088288,null,4,null,379.7891282088288,null,379.7891282088288,null,null,379.7891282088288,1,{"$nulls":8},0.35,132.92619487309008,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02390","1.04.03.06.02","CRB4030602","Measure and Fiducialize Quadrupole - 21","2008-01-30","2008-01-30","S","C","SL_PHS2","Hrs",20,null,1492.0287179632558,null,1492.0287179632558,null,20,null,1492.0287179632558,null,1492.0287179632558,null,null,1492.0287179632558,1,{"$nulls":8},0.35,522.2100512871394,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02430","1.04.03.06.02","CRB4030602","Measure and Fiducialize Quadrupole - 23","2008-02-01","2008-02-01","S","C","SL_MFAT2","Hrs",8,null,703.267488,null,703.267488,null,8,null,703.267488,null,703.267488,null,null,703.267488,1,{"$nulls":8},0.35,246.14362079999998,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02470","1.04.03.06.02","CRB4030602","Measure and Fiducialize Quadrupole - 25","2008-02-05","2008-02-05","S","C","SL_PHS2","Hrs",20,null,1492.0287179632558,null,1492.0287179632558,null,20,null,1492.0287179632558,null,1492.0287179632558,null,null,1492.0287179632558,1,{"$nulls":8},0.35,522.2100512871394,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02490","1.04.03.06.02","CRB4030602","Measure and Fiducialize Quadrupole - 26","2008-02-06","2008-02-06","S","C","SL_PHSS2","Hrs",4,null,379.7891282088288,null,379.7891282088288,null,4,null,379.7891282088288,null,379.7891282088288,null,null,379.7891282088288,1,{"$nulls":8},0.35,132.92619487309008,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02530","1.04.03.06.02","CRB4030602","Measure and Fiducialize Quadrupole - 28","2008-02-08","2008-02-08","S","C","SL_PHS2","Hrs",20,null,1492.0287179632558,null,1492.0287179632558,null,20,null,1492.0287179632558,null,1492.0287179632558,null,null,1492.0287179632558,1,{"$nulls":8},0.35,522.2100512871394,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02570","1.04.03.06.02","CRB4030602","Measure and Fiducialize Quadrupole - 30","2008-02-12","2008-02-12","S","C","SL_PHS2","Hrs",20,null,1492.0287179632558,null,1492.0287179632558,null,20,null,1492.0287179632558,null,1492.0287179632558,null,null,1492.0287179632558,1,{"$nulls":8},0.35,522.2100512871394,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02590","1.04.03.06.02","CRB4030602","Measure and Fiducialize Quadrupole - 31","2008-02-13","2008-02-13","S","C","SL_PHSS2","Hrs",4,null,379.7891282088288,null,379.7891282088288,null,4,null,379.7891282088288,null,379.7891282088288,null,null,379.7891282088288,1,{"$nulls":8},0.35,132.92619487309008,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02630","1.04.03.06.02","CRB4030602","Measure and Fiducialize Quadrupole - 33","2008-02-15","2008-02-15","S","C","SL_PHS2","Hrs",20,null,1492.0287179632558,null,1492.0287179632558,null,20,null,1492.0287179632558,null,1492.0287179632558,null,null,1492.0287179632558,1,{"$nulls":8},0.35,522.2100512871394,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02630","1.04.03.06.02","CRB4030602","Measure and Fiducialize Quadrupole - 33","2008-02-15","2008-02-15","S","C","SL_MFAT2","Hrs",8,null,703.267488,null,703.267488,null,8,null,703.267488,null,703.267488,null,null,703.267488,1,{"$nulls":8},0.35,246.14362079999998,1.25,1.1,3,4,"4B"]
["1","04","03","06","03","01",null,null,null,"Stretched Wire System                                       ",{"$nulls":6},4232,338100,377527.7077396081,364820.90963999997,742348.617379608,null,4232,338100,377527.7077396081,364820.90963999997,742348.617379608,373090.1872538508,null,357662.98213556246,null,11595.447990194847,null,0,null,0,null,0,null,null,222069.245308902,{"$nulls":6},"Rod Pope"]
["1","04","03","06","03","01","UN601_1492","1.04.03.06.03","CRB4030603","Wire Monitor Calibration","2007-10-10","2008-04-07","S","C","SL_EE2","Hrs",200,null,19017.2187736146,null,19017.2187736146,null,200,null,19017.2187736146,null,19017.2187736146,null,null,19017.2187736146,1,{"$nulls":8},0.25,4754.30469340365,1.15,1.1,3,3,"4B"]
["1","04","03","06","03","01","UN601_R675","1.04.03.06.03","CRB4030603","RCV: Wire Monitor Supports","2007-07-09","2007-07-09","S","C","SL_MSEG2","$$",null,1800,null,1929.7872,1929.7872,null,null,1800,null,1929.7872,1929.7872,1929.7872,1,{"$nulls":10},0.35,675.42552,1.25,1.1,4,3,"4B"]
["1","04","03","06","03","01","UN601_R720","1.04.03.06.03","CRB4030603","RCV: Data Acquisition System","2007-08-02","2007-08-02","S","C","SL_MSEG2","$$",null,40000,null,42884.16,42884.16,null,null,40000,null,42884.16,42884.16,42884.16,1,{"$nulls":10},0.35,15009.456,1.25,1.1,4,3,"4B"]
["1","04","03","06","03","02","UN601_P335","1.04.03.06.03","CRB4030603","PP: Capacitive/Acoustic Sensors","2007-09-21","2007-09-21","S","C","SL_MSEG2","$$",null,51000,null,54677.304,54677.304,null,null,51000,null,54677.304,54677.304,54677.304,1,{"$nulls":10},0.1,5467.7304,1,1.1,2,3,"4B"]
["1","04","03","06","03","02","UN601_P434","1.04.03.06.03","CRB4030603","PP: Capacitive/Acoustic Sensors","2007-08-22","2007-08-22","S","C","SL_MSEG2","$$",null,56000,null,60037.824,60037.824,null,null,56000,null,60037.824,60037.824,60037.824,1,{"$nulls":10},0.1,6003.7824,1,1.1,2,3,"4B"]
["1","04","03","06","03","03","UN601_A320","1.04.03.06.03","CRB4030603","RCV: Laser Trackers (2)","2007-05-01","2007-05-15","S","C","SL_MSEG2","$$",null,72000,null,77191.488,77191.488,null,null,72000,null,77191.488,77191.488,77191.488,1,{"$nulls":10},0,0,1,1,3,3,"4B"]
["1","04","03","06","03","03","UN601_A365","1.04.03.06.03","CRB4030603","AEG Support and Data Evaluation","2007-05-01","2007-06-15","S","C","SL_MES2","Hrs",75,null,6004.323413549999,null,6004.323413549999,null,75,null,6004.323413549999,null,6004.323413549999,6004.323413549999,1,{"$nulls":10},1,6004.323413549999,1.5,1.5,5,3,"4B"]
["1","04","03","08","02","","UN38_00030","1.04.03.08.02","CRB4030802","Factory Accept Testing 1st Art - Fixed Support","2007-07-20","2007-07-24","A","C","AN_PHS2","Hrs",24,null,2644.2833934686405,null,2644.2833934686405,null,24,null,2644.2833934686405,null,2644.2833934686405,2644.2833934686405,1,{"$nulls":10},0.15,396.6425090202961,1.1,1.05,7,3,"4A"]
["1","04","03","08","02","","UN38_00045","1.04.03.08.02","CRB4030802","Evaluate 1st Article Fixed Support","2007-08-02","2007-08-30","A","C","AN_ME2","Hrs",60,null,6610.708483671601,null,6610.708483671601,null,60,null,6610.708483671601,null,6610.708483671601,6610.708483671601,1,{"$nulls":10},0.15,991.6062725507402,1.1,1.05,7,3,"4A"]
["1","04","03","08","02","","UN38_00045","1.04.03.08.02","CRB4030802","Evaluate 1st Article Fixed Support","2007-08-02","2007-08-30","A","C","AA_MSSF2","$$",null,60000,null,60000,60000,null,null,60000,null,60000,60000,60000,1,{"$nulls":10},0.15,9000,1.1,1.05,7,3,"4A"]
["1","04","03","08","02","","UN38_00105","1.04.03.08.02","CRB4030802","Vendor Fab Fixed Support Production Units","2007-09-26","2008-02-04","A","C","AN_MDD2","Hrs",200,null,13223.699010653978,null,13223.699010653978,null,200,null,13223.699010653978,null,13223.699010653978,504.72133628450297,0.04,12718.977674369475,0.96,{"$nulls":8},0.25,3305.9247526634945,1.15,1.1,4,3,"4A"]
["1","04","03","08","02","","UN38_00135","1.04.03.08.02","CRB4030802","RCV: 2 Fixed Supports","2007-11-07","2007-11-07","A","C","AA_MSSF2","$$",null,32000,null,32000,32000,null,null,32000,null,32000,32000,null,null,32000,1,{"$nulls":8},0.25,8000,1.15,1.1,4,3,"4A"]
["1","04","03","08","02","","UN38_00150","1.04.03.08.02","CRB4030802","RCV: 2 Fixed Supports","2007-11-30","2007-11-30","A","C","AA_MSSF2","$$",null,32000,null,32000,32000,null,null,32000,null,32000,32000,null,null,32000,1,{"$nulls":8},0.25,8000,1.15,1.1,4,3,"4A"]
["1","04","03","08","03","  ",null,null,null,"Stabilized Girder Assemblies                                ",{"$nulls":37},"Geoff Pile"]
["1","04","03","08","05","","UN38_00270","1.04.03.08.05","CRB4030805","Mechanical Hardware for Temp Monitoring System","2007-05-01","2007-06-27","S","C","AN_MSEG2","$$",null,12000,null,12276,12276,null,null,12000,null,12276,12276,12276,1,{"$nulls":10},0.2,2455.2000000000003,1.1,1.1,3,3,"4A"]
["1","04","04","02","02","","UN42_00248","1.04.04.02.02","CRB4040202","Oversee Construction of Vacuum Chamber","2007-09-26","2008-05-23",null,"C","AN_MVE2","Hrs",254,null,28615.585591708266,null,28615.585591708266,null,254,null,28615.585591708266,null,28615.585591708266,596.1580331605888,0.02,28019.427558547675,0.98,{"$nulls":8},0.2,5723.117118341654,1.1,1.1,3,3,"4A"]
["1","04","04","02","02","","UN42_00270","1.04.04.02.02","CRB4040202","Oversee Construction of Chamber Supports","2007-05-01","2007-12-21",null,"C","AN_MDD2","Hrs",141,null,9193.549924579025,null,9193.549924579025,null,141,null,9193.549924579025,null,9193.549924579025,6011.167258378593,0.65,3182.3826662004317,0.35,{"$nulls":8},0.2,1838.709984915805,1.1,1.1,3,3,"4A"]
["1","04","04","02","02","","UN42_0A220","1.04.04.02.02","CRB4040202","AWARD:  Chamber Wall Parts (33)","2007-05-01","2007-05-01",null,"C","AN_AWARD","$$",null,106564,null,115655.50766,115655.50766,null,null,106564,null,115655.50766,115655.50766,115655.50766,1,{"$nulls":10},0.2,23131.101532,1.1,1.1,3,3,"4A"]
["1","04","04","02","02","","UN42_0A270","1.04.04.02.02","CRB4040202","AWARD:  Final Machine (33)","2007-09-25","2007-09-25",null,"C","AN_AWARD","$$",null,67320,null,73063.40580000001,73063.40580000001,null,null,67320,null,73063.40580000001,73063.40580000001,73063.40580000001,1,{"$nulls":10},0.2,14612.681160000002,1.1,1.1,3,3,"4A"]
["1","04","04","02","02","","UN42_0B215","1.04.04.02.02","CRB4040202","RCV: Strongback Material (7)","2007-05-11","2007-05-11",null,"C","AA_MSEG2","$$",null,29869,null,30555.986999999997,30555.986999999997,null,null,29869,null,30555.986999999997,30555.986999999997,30555.986999999997,1,{"$nulls":10},0.2,6111.1974,1.1,1.1,3,3,"4A"]
["1","04","04","02","02","","UN42_0B252","1.04.04.02.02","CRB4040202","Inspect, Clean, & Pkg Parts (7)","2007-08-31","2007-09-14",null,"C","AN_MVE2","Hrs",40,null,4407.138989114401,null,4407.138989114401,null,40,null,4407.138989114401,null,4407.138989114401,4407.138989114401,1,{"$nulls":10},0.2,881.4277978228802,1.1,1.1,3,3,"4A"]
["1","04","04","02","02","","UN42_0B290","1.04.04.02.02","CRB4040202","Ship Vacuum Chambers to SLAC (7)","2008-01-07","2008-01-11",null,"C","AN_MVE2","Hrs",32,null,3606.8025486912256,null,3606.8025486912256,null,32,null,3606.8025486912256,null,3606.8025486912256,null,null,3606.8025486912256,1,{"$nulls":8},0.2,721.3605097382451,1.1,1.1,3,3,"4A"]
["1","04","04","02","02","","UN42_0C235","1.04.04.02.02","CRB4040202","RCV:  Chamber Wall Parts (7)","2007-08-28","2007-08-28",null,"C","AA_MSEG2","$$",null,22500,null,23017.5,23017.5,null,null,22500,null,23017.5,23017.5,23017.5,1,{"$nulls":10},0.2,4603.5,1.1,1.1,3,3,"4A"]
["1","04","04","02","02","","UN42_0C290","1.04.04.02.02","CRB4040202","Ship Vacuum Chambers to SLAC (7)","2008-01-31","2008-02-06",null,"C","AN_MVE2","Hrs",44,null,4959.353504450435,null,4959.353504450435,null,44,null,4959.353504450435,null,4959.353504450435,null,null,4959.353504450435,1,{"$nulls":8},0.2,991.870700890087,1.1,1.1,3,3,"4A"]
["1","04","04","02","02","","UN42_0D252","1.04.04.02.02","CRB4040202","Inspect, Clean, & Pkg Parts (7)","2007-10-31","2007-11-13",null,"C","AN_ME2","Hrs",40,null,4508.503185864032,null,4508.503185864032,null,40,null,4508.503185864032,null,4508.503185864032,null,null,4508.503185864032,1,{"$nulls":8},0.2,901.7006371728065,1.1,1.1,3,3,"4A"]
["1","04","04","02","02","","UN42_0D285","1.04.04.02.02","CRB4040202","Inspect, Leak Test, Clean, Coat & Bake (7)","2008-01-31","2008-02-28",null,"C","AN_MVE2","Hrs",128,null,14427.210194764903,null,14427.210194764903,null,128,null,14427.210194764903,null,14427.210194764903,null,null,14427.210194764903,1,{"$nulls":8},0.2,2885.4420389529805,1.1,1.1,3,3,"4A"]
["1","04","04","02","02","","UN42_0E252","1.04.04.02.02","CRB4040202","Inspect, Clean, & Pkg Parts (8)","2007-12-03","2007-12-14",null,"C","AN_ME2","Hrs",40,null,4508.503185864032,null,4508.503185864032,null,40,null,4508.503185864032,null,4508.503185864032,null,null,4508.503185864032,1,{"$nulls":8},0.2,901.7006371728065,1.1,1.1,3,3,"4A"]
["1","04","04","02","02","","UN42_0F100","1.04.04.02.02","CRB4040202","Award Effort Chamber Supports","2007-05-01","2007-06-26",null,"C","AN_MVE2","Hrs",152,null,16747.128158634725,null,16747.128158634725,null,152,null,16747.128158634725,null,16747.128158634725,16747.128158634725,1,{"$nulls":10},0.2,3349.425631726945,1.1,1.1,3,3,"4A"]
["1","04","04","02","02","","UN42_0F115","1.04.04.02.02","CRB4040202","RCV:  Chamber Supports (4)","2007-06-28","2007-06-28",null,"C","AA_MSSC2","$$",null,64000,null,65472,65472,null,null,64000,null,65472,65472,65472,1,{"$nulls":10},0.2,13094.400000000001,1.1,1.1,3,3,"4A"]
["1","04","04","02","02","","UN42_0G115","1.04.04.02.02","CRB4040202","RCV:  Chamber Supports (7)","2007-08-17","2007-08-17",null,"C","AA_MSSC2","$$",null,112000,null,114576,114576,null,null,112000,null,114576,114576,114576,1,{"$nulls":10},0.2,22915.2,1.1,1.1,3,3,"4A"]
["1","04","04","02","02","","UN42_0G125","1.04.04.02.02","CRB4040202","Package Chamber Supports for Shipment (7)","2007-09-06","2007-09-12",null,"C","AN_MVE2","Hrs",16,null,1762.8555956457603,null,1762.8555956457603,null,16,null,1762.8555956457603,null,1762.8555956457603,1762.8555956457603,1,{"$nulls":10},0.2,352.57111912915207,1.1,1.1,3,3,"4A"]
["1","04","04","02","02","","UN42_0H130","1.04.04.02.02","CRB4040202","Ship Chamber Supports to SLAC (7)","2007-11-01","2007-11-07",null,"C","AN_MSEG2","$$",null,2545,null,2663.416305,2663.416305,null,null,2545,null,2663.416305,2663.416305,null,null,2663.416305,1,{"$nulls":8},0.2,532.683261,1.1,1.1,3,3,"4A"]
["1","04","04","02","02","","UN42_0I130","1.04.04.02.02","CRB4040202","Ship Chamber Supports to SLAC (7)","2008-01-02","2008-01-08",null,"C","AN_MSEG2","$$",null,2545,null,2663.416305,2663.416305,null,null,2545,null,2663.416305,2663.416305,null,null,2663.416305,1,{"$nulls":8},0.2,532.683261,1.1,1.1,3,3,"4A"]
["1","04","04","02","02","","UN42_0J120","1.04.04.02.02","CRB4040202","Inspect Chamber Supports (8)","2008-02-04","2008-02-19",null,"C","AN_MVE2","Hrs",64,null,7213.605097382451,null,7213.605097382451,null,64,null,7213.605097382451,null,7213.605097382451,null,null,7213.605097382451,1,{"$nulls":8},0.2,1442.7210194764903,1.1,1.1,3,3,"4A"]
["1","04","04","03","02","  ",null,null,null,"Production Bellows Module                                   ",{"$nulls":6},1063,169572,99753.86834601333,175599.1776,198277.4188340134,null,1063,169572,99753.86834601333,175599.1776,275353.04594601336,120635.52792693136,null,154717.51801908202,null,0,null,0,null,0,null,0,null,null,55070.60918920265,{"$nulls":6},"Geoff Pile"]
["1","04","04","03","02","","UN43_00410","1.04.04.03.02","CRB4040302","REC:  First Lot Standard Bellows Module (4)","2007-06-04","2007-07-30","A","C","AN_MVE2","Hrs",4,null,440.7138989114401,null,440.7138989114401,null,4,null,440.7138989114401,null,440.7138989114401,440.7138989114401,1,{"$nulls":10},0.2,88.14277978228802,1.1,1.1,3,3,"4A"]
["1","04","04","03","02","","UN43_00411","1.04.04.03.02","CRB4040302","Oversee Construction of Bellows Module","2007-06-04","2008-05-01","A","C","AN_MVE2","Hrs",313,null,34994.73680918021,null,34994.73680918021,null,313,null,34994.73680918021,null,34994.73680918021,12543.29421774833,0.36,22451.44259143188,0.64,{"$nulls":8},0.2,6998.947361836043,1.1,1.1,3,3,"4A"]
["1","04","04","03","02","","UN43_00423","1.04.04.03.02","CRB4040302","Clean 1st Lot Std Bel Mod","2007-08-14","2007-08-14","A","C","AN_MVE2","Hrs",16,null,1762.8555956457603,null,1762.8555956457603,null,16,null,1762.8555956457603,null,1762.8555956457603,1762.8555956457603,1,{"$nulls":10},0.2,352.57111912915207,1.1,1.1,3,3,"4A"]
["1","04","04","03","02","","UN43_00424","1.04.04.03.02","CRB4040302","Bake 1st Lot Std Bel Mod","2007-08-15","2007-08-21","A","C","AN_MFAT2","Hrs",32,null,2069.9990385465603,null,2069.9990385465603,null,32,null,2069.9990385465603,null,2069.9990385465603,2069.9990385465603,1,{"$nulls":10},0.2,413.9998077093121,1.1,1.1,3,3,"4A"]
["1","04","04","03","02","","UN43_00450","1.04.04.03.02","CRB4040302","REC: 2nd Prod Lot Std Bellows Module (21)","2007-08-14","2007-10-09","A","C","AA_MSSC2","$$",null,75096,null,77075.62711199999,null,null,null,75096,null,77075.62711199999,77075.62711199999,66064.82323885713,0.86,11010.803873142855,0.14,{"$nulls":8},0.2,15415.125422399999,1.1,1.1,3,3,"4A"]
["1","04","04","03","02","","UN43_00520","1.04.04.03.02","CRB4040302","Bake 2nd Lot Std Bel Mod","2007-11-01","2007-11-07","A","C","AN_MVE2","Hrs",16,null,1803.4012743456128,null,1803.4012743456128,null,16,null,1803.4012743456128,null,1803.4012743456128,null,null,1803.4012743456128,1,{"$nulls":8},0.2,360.68025486912256,1.1,1.1,3,3,"4A"]
["1","04","04","03","02","","UN43_00530","1.04.04.03.02","CRB4040302","Prepare 2nd Lot Std Bellows for Shipment","2007-11-08","2007-11-09","A","C","AN_MFAT2","Hrs",8,null,529.4022541082828,null,529.4022541082828,null,8,null,529.4022541082828,null,529.4022541082828,null,null,529.4022541082828,1,{"$nulls":8},0.2,105.88045082165657,1.1,1.1,3,3,"4A"]
["1","04","04","03","02","","UN43_00552","1.04.04.03.02","CRB4040302","QA Production Rem Lot Std Bel Mod","2007-12-07","2007-12-18","A","C","AN_MVE2","Hrs",16,null,1803.4012743456128,null,1803.4012743456128,null,16,null,1803.4012743456128,null,1803.4012743456128,null,null,1803.4012743456128,1,{"$nulls":8},0.2,360.68025486912256,1.1,1.1,3,3,"4A"]
["1","04","04","03","02","","UN43_00556","1.04.04.03.02","CRB4040302","Prepare Rem Std Bellows for Shipment","2008-01-17","2008-01-18","A","C","AN_MFAT2","Hrs",8,null,529.4022541082828,null,529.4022541082828,null,8,null,529.4022541082828,null,529.4022541082828,null,null,529.4022541082828,1,{"$nulls":8},0.2,105.88045082165657,1.1,1.1,3,3,"4A"]
["1","04","04","03","02","","UN43_00558","1.04.04.03.02","CRB4040302","Ship Rem 22 Std Bel Mod to SLAC","2008-01-23","2008-01-29","A","C","AN_MSEG2","$$",null,500,null,523.2645,523.2645,null,null,500,null,523.2645,523.2645,null,null,523.2645,1,{"$nulls":8},0.2,104.6529,1.1,1.1,3,3,"4A"]
["1","04","04","05","","","UN45_00052","1.04.04.05","CRB40405","Final SDB Vac Cham & Integration Design Review","2007-05-01","2007-06-20","A","C","AN_PHS2","Hrs",3,null,330.53542418358006,null,330.53542418358006,null,3,null,330.53542418358006,null,330.53542418358006,330.53542418358006,1,{"$nulls":10},0.15,49.58031362753701,1.1,1.05,3,2,"4A"]
["1","04","04","05","","","UN45_00150","1.04.04.05","CRB40405","Pump Support Bid Package","2007-06-21","2007-06-27","A","C","AN_MVE2","Hrs",16,null,1762.8555956457603,null,1762.8555956457603,null,16,null,1762.8555956457603,null,1762.8555956457603,1762.8555956457603,1,{"$nulls":10},0.15,264.42833934686405,1.1,1.05,3,3,"4A"]
["1","04","04","05","","","UN45_00336","1.04.04.05","CRB40405","REC: SDB Ion Pump Support (23)","2007-07-10","2007-09-04","A","C","AA_MSSC2","$$",null,26614,null,27226.122,27226.122,null,null,26614,null,27226.122,27226.122,27226.122,1,{"$nulls":10},0.15,4083.9183,1.1,1.05,3,3,"4A"]
["1","04","04","05","","","UN45_00390","1.04.04.05","CRB40405","Prepare Short Diagnostic Break for Shipment","2007-10-08","2007-10-12","A","C","AN_MFAT2","Hrs",24,null,1588.2067623248486,null,1588.2067623248486,null,24,null,1588.2067623248486,null,1588.2067623248486,null,null,1588.2067623248486,1,{"$nulls":8},0.15,238.23101434872729,1.1,1.05,3,3,"4A"]
["1","04","04","05","","","UN45_00410","1.04.04.05","CRB40405","Ship to SLAC SDB","2007-10-22","2007-10-26","A","C","AN_MSEG2","$$",null,1000,null,1046.529,1046.529,null,null,1000,null,1046.529,1046.529,null,null,1046.529,1,{"$nulls":8},0.15,156.97934999999998,1.1,1.05,3,3,"4A"]
["1","04","04","06","","","UN46_00052","1.04.04.06","CRB40406","Final LDB Vac Cham & Integration Design Review","2007-05-01","2007-06-20","A","C","AN_PHS2","Hrs",4,null,440.7138989114401,null,440.7138989114401,null,4,null,440.7138989114401,null,440.7138989114401,440.7138989114401,1,{"$nulls":10},0.15,66.10708483671601,1.1,1.05,3,2,"4A"]
["1","04","04","06","","","UN46_00255","1.04.04.06","CRB40406","LDB Ion Pump Sppt Award Effort","2007-05-31","2007-06-01","A","C","AN_MVE2","Hrs",8,null,881.4277978228802,null,881.4277978228802,null,8,null,881.4277978228802,null,881.4277978228802,881.4277978228802,1,{"$nulls":10},0.15,132.21416967343202,1.1,1.05,3,3,"4A"]
["1","04","04","06","","","UN46_00320","1.04.04.06","CRB40406","AWARD: LDB Ion Pump Support","2007-05-31","2007-06-01","A","C","AN_AWARD","$$",null,3250,null,3527.2737500000003,3527.2737500000003,null,null,3250,null,3527.2737500000003,3527.2737500000003,3527.2737500000003,1,{"$nulls":10},0.15,529.0910625,1.1,1.05,3,3,"4A"]
["1","04","04","06","","","UN46_00408","1.04.04.06","CRB40406","REC: LDB Ion Pump Support (11)","2007-06-04","2007-07-30","A","C","AA_MSSC2","$$",null,3250,null,3324.75,3324.75,null,null,3250,null,3324.75,3324.75,3324.75,1,{"$nulls":10},0.15,498.7125,1.1,1.05,3,3,"4A"]
["1","04","04","06","","","UN46_00430","1.04.04.06","CRB40406","Clean LDB","2007-08-17","2007-08-28","A","C","AN_MFAT2","Hrs",32,null,2069.9990385465603,null,2069.9990385465603,null,32,null,2069.9990385465603,null,2069.9990385465603,2069.9990385465603,1,{"$nulls":10},0.15,310.499855781984,1.1,1.05,3,3,"4A"]
["1","04","04","06","","","UN46_00480","1.04.04.06","CRB40406","Pack Long Diagnostic Break for Shipping","2007-09-13","2007-09-19","A","C","AN_MFAT2","Hrs",24,null,1552.4992789099201,null,1552.4992789099201,null,24,null,1552.4992789099201,null,1552.4992789099201,1552.4992789099201,1,{"$nulls":10},0.15,232.87489183648802,1.1,1.05,3,3,"4A"]
["1","04","04","09","","","UN49_00120","1.04.04.09","CRB40409","Bid Pkg: Vacuum Gauge Baking Station","2007-05-01","2007-05-03","A","C","AN_MVE2","Hrs",8,null,881.4277978228802,null,881.4277978228802,null,8,null,881.4277978228802,null,881.4277978228802,881.4277978228802,1,{"$nulls":10},0.2,176.28555956457603,1.1,1.1,3,3,"4A"]
["1","04","04","09","","","UN49_00151","1.04.04.09","CRB40409","Evaluate Bids: Baking Station","2007-06-22","2007-06-26","A","C","AN_MVE2","Hrs",24,null,2644.2833934686405,null,2644.2833934686405,null,24,null,2644.2833934686405,null,2644.2833934686405,2644.2833934686405,1,{"$nulls":10},0.2,528.8566786937281,1.1,1.1,3,3,"4A"]
["1","04","04","09","","","UN49_00215","1.04.04.09","CRB40409","Valves Award Effort","2007-06-27","2007-06-29","A","C","AN_MVE2","Hrs",8,null,881.4277978228802,null,881.4277978228802,null,8,null,881.4277978228802,null,881.4277978228802,881.4277978228802,1,{"$nulls":10},0.2,176.28555956457603,1.1,1.1,3,3,"4A"]
["1","04","04","09","","","UN49_00280","1.04.04.09","CRB40409","QA of Baking Components","2007-07-24","2007-07-30","A","C","AN_MFMS2","Hrs",40,null,4067.2342339199995,null,4067.2342339199995,null,40,null,4067.2342339199995,null,4067.2342339199995,4067.2342339199995,1,{"$nulls":10},0.2,813.446846784,1.1,1.1,3,3,"4A"]
["1","04","05","02","01","  ",null,null,null,"ULD Test Station                                            ",{"$nulls":37},"Geoff Pile"]
["1","04","05","04","01","  ",null,null,null,"Prototype Construction and Testing                          ",{"$nulls":37},"Geoff Pile"]
["1","04","05","04","04","  ",null,null,null,"Optical Diffraction radiation imaging assembly (            ",{"$nulls":37},"Geoff Pile"]
["1","04","05","05","01","","UN505_1100","1.04.05.05.01","CBB4050501","Braze Three Bodies","2007-05-01","2007-05-25","A","C","AN_MFMS2","Hrs",18,null,1830.2554052639998,null,1830.2554052639998,null,18,null,1830.2554052639998,null,1830.2554052639998,1830.2554052639998,1,{"$nulls":10},0.2,366.0510810528,1.1,1.1,7,3,"4A"]
["1","04","05","05","02","  ",null,null,null,"X-Band Receiver Development                                 ",{"$nulls":6},49,2450,3943.033108920181,2506.35,6449.383108920181,null,49,2450,3943.033108920181,2506.35,6449.383108920181,6449.383108920181,null,0,null,0,null,0,null,0,null,0,null,null,1289.8766217840362,{"$nulls":6},"Geoff Pile"]
["1","04","05","05","02","","UN505_2050","1.04.05.05.02","CBB4050502","Bench Test & Tune (3) DC and LO","2007-05-01","2007-05-30","A","C","AN_EE2","Hrs",16,null,1762.8555956457603,null,1762.8555956457603,null,16,null,1762.8555956457603,null,1762.8555956457603,1762.8555956457603,1,{"$nulls":10},0.2,352.57111912915207,1.1,1.1,1,3,"4A"]
["1","04","05","05","03","","UN505_3010","1.04.05.05.03","CBB4050503","RFBPM Prod Design Review","2007-06-12","2007-06-18","A","C","AN_ME2","Hrs",16,null,1762.8555956457603,null,1762.8555956457603,null,16,null,1762.8555956457603,null,1762.8555956457603,1762.8555956457603,1,{"$nulls":10},0.2,352.57111912915207,1.1,1.1,3,2,"4A"]
["1","04","05","05","03","","UN505_3018","1.04.05.05.03","CBB4050503","Waveguide Final Design","2007-07-03","2007-07-17","A","C","AN_MDD2","Hrs",40,null,2587.4987981832005,null,2587.4987981832005,null,40,null,2587.4987981832005,null,2587.4987981832005,2587.4987981832005,1,{"$nulls":10},0.2,517.4997596366401,1.1,1.1,3,2,"4A"]
["1","04","05","05","03","","UN505_3018","1.04.05.05.03","CBB4050503","Waveguide Final Design","2007-07-03","2007-07-17","A","C","AN_EE2","Hrs",24,null,2644.2833934686405,null,2644.2833934686405,null,24,null,2644.2833934686405,null,2644.2833934686405,2644.2833934686405,1,{"$nulls":10},0.2,528.8566786937281,1.1,1.1,3,2,"4A"]
["1","04","05","05","03","","UN505_3040","1.04.05.05.03","CBB4050503","Bid Process - RFBPM","2007-08-01","2007-08-02","A","C","AN_ME2","Hrs",8,null,881.4277978228802,null,881.4277978228802,null,8,null,881.4277978228802,null,881.4277978228802,881.4277978228802,1,{"$nulls":10},0.2,176.28555956457603,1.1,1.1,3,3,"4A"]
["1","04","05","05","03","","UN505_3050","1.04.05.05.03","CBB4050503","AWARD: Copper Body Brazement (35)","2007-08-08","2007-08-10","A","C","AN_AWARD","$$",null,285600,null,309965.96400000004,309965.96400000004,null,null,285600,null,309965.96400000004,309965.96400000004,309965.96400000004,1,{"$nulls":10},0.2,61993.19280000001,1.1,1.1,3,3,"4A"]
["1","04","05","05","03","","UN505_3059","1.04.05.05.03","CBB4050503","REC: LTU BPM Supports (2)","2007-08-13","2007-09-17","A","C","AN_ME2","Hrs",4,null,440.7138989114401,null,440.7138989114401,null,4,null,440.7138989114401,null,440.7138989114401,440.7138989114401,1,{"$nulls":10},0.2,88.14277978228802,1.1,1.1,3,3,"4A"]
["1","04","05","05","03","","UN505_3068","1.04.05.05.03","CBB4050503","REC: Undulator Local Oscillator (37)","2007-08-13","2007-08-15","A","C","AN_EE2","Hrs",8,null,881.4277978228802,null,881.4277978228802,null,8,null,881.4277978228802,null,881.4277978228802,881.4277978228802,1,{"$nulls":10},0.2,176.28555956457603,1.1,1.1,3,3,"4A"]
["1","04","05","05","03","","UN505_3075","1.04.05.05.03","CBB4050503","RF Cabling (37) Award Effort","2007-08-08","2007-08-10","A","C","AN_EE2","Hrs",8,null,881.4277978228802,null,881.4277978228802,null,8,null,881.4277978228802,null,881.4277978228802,881.4277978228802,1,{"$nulls":10},0.2,176.28555956457603,1.1,1.1,3,3,"4A"]
["1","04","05","05","03","","UN505_3106","1.04.05.05.03","CBB4050503","Cold Test 1st Article","2007-12-04","2007-12-06","A","C","AN_MFAT2","Hrs",16,null,1058.8045082165656,null,1058.8045082165656,null,16,null,1058.8045082165656,null,1058.8045082165656,null,null,1058.8045082165656,1,{"$nulls":8},0.2,211.76090164331313,1.1,1.1,3,3,"4A"]
["1","04","05","05","03","","UN505_3120","1.04.05.05.03","CBB4050503","QA Production Lot","2008-01-18","2008-03-24","A","C","AN_ME2","Hrs",16,null,1803.4012743456128,null,1803.4012743456128,null,16,null,1803.4012743456128,null,1803.4012743456128,null,null,1803.4012743456128,1,{"$nulls":8},0.2,360.68025486912256,1.1,1.1,3,3,"4A"]
["1","04","05","05","03","","UN505_3120","1.04.05.05.03","CBB4050503","QA Production Lot","2008-01-18","2008-03-24","A","C","AN_EE2","Hrs",16,null,1803.4012743456128,null,1803.4012743456128,null,16,null,1803.4012743456128,null,1803.4012743456128,null,null,1803.4012743456128,1,{"$nulls":8},0.2,360.68025486912256,1.1,1.1,3,3,"4A"]
["1","04","05","05","03","","UN505_3127","1.04.05.05.03","CBB4050503","Assemble/Test Undulator BPM","2008-02-06","2008-04-03","A","C","AN_MFAT2","Hrs",280,null,18529.078893789898,null,18529.078893789898,null,280,null,18529.078893789898,null,18529.078893789898,null,null,18529.078893789898,1,{"$nulls":8},0.2,3705.81577875798,1.1,1.1,3,3,"4A"]
["1","04","05","05","03","","UN505_3130","1.04.05.05.03","CBB4050503","Pack/Ship 1st Lot (11)Undulator RFBPM to SLAC","2008-02-27","2008-03-04","A","C","AN_MFAT2","Hrs",24,null,1588.2067623248486,null,1588.2067623248486,null,24,null,1588.2067623248486,null,1588.2067623248486,null,null,1588.2067623248486,1,{"$nulls":8},0.2,317.6413524649697,1.1,1.1,3,3,"4A"]
["1","04","05","05","03","","UN505_3133","1.04.05.05.03","CBB4050503","Pack/Ship 3rd Lot(12)Undulator RFBPM to SLAC","2008-04-09","2008-04-15","A","C","AN_MSEG2","$$",null,2000,null,2093.058,2093.058,null,null,2000,null,2093.058,2093.058,null,null,2093.058,1,{"$nulls":8},0.2,418.6116,1.1,1.1,3,3,"4A"]
["1","04","05","05","03","","UN505_3A66","1.04.05.05.03","CBB4050503","AWARD: Undulator Waveguide (35)","2007-08-08","2007-08-10","A","C","AN_AWARD","$$",null,121229,null,131571.652135,131571.652135,null,null,121229,null,131571.652135,131571.652135,131571.652135,1,{"$nulls":10},0.2,26314.330427000004,1.1,1.1,3,3,"4A"]
["1","04","05","06","  ","  ",null,null,null,"Beam Finder Wire                                            ",{"$nulls":6},2468,329515,243118.10668567842,340201.38165357144,484756.6093956786,null,2468,329515,243118.10668567842,340201.38165357144,583319.4883392503,347418.85238710506,null,235900.6359521448,null,0,null,0,null,0,null,0,null,null,87497.92325088747,{"$nulls":6},"Geoff Pile"]
["1","04","05","06","","","UN506_0121","1.04.05.06","CRB40506","Weld Components (3)","2007-07-16","2007-07-31",null,"C","AN_ME2","Hrs",24,null,2644.2833934686405,null,2644.2833934686405,null,24,null,2644.2833934686405,null,2644.2833934686405,2644.2833934686405,1,{"$nulls":10},0.15,396.6425090202961,1.05,1.1,null,3,"4A"]
["1","04","05","06","","","UN506_0125","1.04.05.06","CRB40506","Beam Finder Wire Production Effort","2007-05-01","2007-11-28",null,"C","AN_ME2","Hrs",32,null,3548.0017065957054,null,3548.0017065957054,null,32,null,3548.0017065957054,null,3548.0017065957054,2572.7216166310095,0.73,975.2800899646963,0.27,{"$nulls":8},0.15,532.2002559893558,1.05,1.1,3,3,"4A"]
["1","04","05","06","","","UN506_0125","1.04.05.06","CRB40506","Beam Finder Wire Production Effort","2007-05-01","2007-11-28",null,"C","AN_MDD2","Hrs",8,null,520.7715353681817,null,520.7715353681817,null,8,null,520.7715353681817,null,520.7715353681817,377.62106593048253,0.73,143.15046943769926,0.27,{"$nulls":8},0.15,78.11573030522726,1.05,1.1,3,3,"4A"]
["1","04","05","06","","","UN506_0136","1.04.05.06","CRB40506","Inspect Components (10)","2007-08-24","2007-09-07",null,"C","AN_MFAT2","Hrs",16,null,1034.9995192732802,null,1034.9995192732802,null,16,null,1034.9995192732802,null,1034.9995192732802,1034.9995192732802,1,{"$nulls":10},0.15,155.249927890992,1.05,1.1,null,3,"4A"]
["1","04","05","06","","","UN506_0137","1.04.05.06","CRB40506","Weld Components (10)","2007-09-10","2007-09-28",null,"C","AN_ME2","Hrs",20,null,2203.5694945572004,null,2203.5694945572004,null,20,null,2203.5694945572004,null,2203.5694945572004,2203.5694945572004,1,{"$nulls":10},0.15,330.53542418358006,1.05,1.1,null,3,"4A"]
["1","04","05","06","","","UN506_0142","1.04.05.06","CRB40506","Assemble (10)","2007-10-31","2007-11-20",null,"C","AN_MFAT2","Hrs",24,null,1588.2067623248486,null,1588.2067623248486,null,24,null,1588.2067623248486,null,1588.2067623248486,null,null,1588.2067623248486,1,{"$nulls":8},0.15,238.23101434872729,1.05,1.1,null,3,"4A"]
["1","04","05","06","","","UN506_0147","1.04.05.06","CRB40506","REC:  Machine Components (10)","2007-08-31","2007-10-12",null,"C","AN_MSEG2","$$",null,95770,null,98562.87894357143,null,null,null,95770,null,98562.87894357143,98562.87894357143,72748.79160120749,0.74,25814.087342363946,0.26,{"$nulls":8},0.15,14784.431841535714,1.05,1.1,3,3,"4A"]
["1","04","05","06","","","UN506_0152","1.04.05.06","CRB40506","Bake Parts (10)","2007-11-14","2007-11-20",null,"C","AN_MFAT2","Hrs",8,null,529.4022541082828,null,529.4022541082828,null,8,null,529.4022541082828,null,529.4022541082828,null,null,529.4022541082828,1,{"$nulls":8},0.15,79.41033811624241,1.05,1.1,null,3,"4A"]
["1","04","05","06","","","UN506_0153","1.04.05.06","CRB40506","Leak Check (10)","2007-11-21","2007-12-03",null,"C","AN_ME2","Hrs",8,null,901.7006371728064,null,901.7006371728064,null,8,null,901.7006371728064,null,901.7006371728064,null,null,901.7006371728064,1,{"$nulls":8},0.15,135.25509557592096,1.05,1.1,null,3,"4A"]
["1","04","05","06","","","UN506_0158","1.04.05.06","CRB40506","Ship Third Lot of Chamber to SLAC (10)","2008-01-11","2008-01-18",null,"C","AN_MSEG2","$$",null,3400,null,3558.1986,3558.1986,null,null,3400,null,3558.1986,3558.1986,null,null,3558.1986,1,{"$nulls":8},0.15,533.72979,1.05,1.1,3,3,"4A"]
["1","04","05","06","","","UN506_0158","1.04.05.06","CRB40506","Ship Third Lot of Chamber to SLAC (10)","2008-01-11","2008-01-18",null,"C","AN_MFAT2","Hrs",4,null,264.7011270541414,null,264.7011270541414,null,4,null,264.7011270541414,null,264.7011270541414,null,null,264.7011270541414,1,{"$nulls":8},0.15,39.70516905812121,1.05,1.1,3,3,"4A"]
["1","04","05","06","","","UN506_0164","1.04.05.06","CRB40506","Bake Parts (10)","2008-01-14","2008-01-18",null,"C","AN_MFAT2","Hrs",12,null,794.1033811624243,null,794.1033811624243,null,12,null,794.1033811624243,null,794.1033811624243,null,null,794.1033811624243,1,{"$nulls":8},0.15,119.11550717436364,1.05,1.1,null,3,"4A"]
["1","04","05","06","","","UN506_0167","1.04.05.06","CRB40506","Test RGA (10)","2008-02-12","2008-02-25",null,"C","AN_ME2","Hrs",24,null,2705.101911518419,null,2705.101911518419,null,24,null,2705.101911518419,null,2705.101911518419,null,null,2705.101911518419,1,{"$nulls":8},0.15,405.7652867277628,1.05,1.1,null,3,"4A"]
["1","04","05","06","","","UN506_0169","1.04.05.06","CRB40506","Ship Fourth Lot of Chamber to SLAC (10)","2008-02-28","2008-03-06",null,"C","AN_MFAT2","Hrs",4,null,264.7011270541414,null,264.7011270541414,null,4,null,264.7011270541414,null,264.7011270541414,null,null,264.7011270541414,1,{"$nulls":8},0.15,39.70516905812121,1.05,1.1,3,3,"4A"]
["1","04","05","08","","","UN508_0021","1.04.05.08","CRB40508","Preliminary Design - Beam Loss Mon","2007-05-01","2007-05-29","A","C","AN_ME2","Hrs",3,null,330.53542418358006,null,330.53542418358006,null,3,null,330.53542418358006,null,330.53542418358006,330.53542418358006,1,{"$nulls":10},0.3,99.16062725507402,1.15,1.15,4,2,"4A"]
["1","04","05","08","","","UN508_0189","1.04.05.08","CRB40508","Put Procurement Packages Together","2007-07-31","2007-08-20",null,"C","AN_EE2","Hrs",113,null,12450.167644248182,null,12450.167644248182,null,113,null,12450.167644248182,null,12450.167644248182,12450.167644248182,1,{"$nulls":10},0.3,3735.0502932744544,1.15,1.15,4,3,"4A"]
["1","04","05","08","","","UN508_0193","1.04.05.08","CRB40508","AWARD: Integrating Fiber (34)","2007-09-04","2007-09-04",null,"C","AN_AWARD","$$",null,51000,null,55351.065,55351.065,null,null,51000,null,55351.065,55351.065,55351.065,1,{"$nulls":10},0.3,16605.3195,1.15,1.15,4,3,"4A"]
["1","04","05","08","","","UN508_0200","1.04.05.08","CRB40508","Assemble Cerenkov Fiber Components","2008-12-03","2009-01-08",null,"C","AN_MFAT2","Hrs",107,null,7243.6113872059295,null,7243.6113872059295,null,107,null,7243.6113872059295,null,7243.6113872059295,{"$nulls":4},7243.6113872059295,1,{"$nulls":6},0.3,2173.0834161617786,1.15,1.15,4,3,"4A"]
["1","04","05","08","","","UN508_0200","1.04.05.08","CRB40508","Assemble Cerenkov Fiber Components","2008-12-03","2009-01-08",null,"C","AN_EE2","Hrs",27,null,3113.2336767934016,null,3113.2336767934016,null,27,null,3113.2336767934016,null,3113.2336767934016,{"$nulls":4},3113.2336767934016,1,{"$nulls":6},0.3,933.9701030380204,1.15,1.15,4,3,"4A"]
["1","04","05","09","  ","  ",null,null,null,"Radiation Detection Monitor (RDM)                           ",{"$nulls":37},"Geoff Pile"]
["1","04","06","04","  ","  ",null,null,null,"Vacuum System Installation and Alignment                    ",{"$nulls":37},"Rod Pope"]
["1","04","06","06","","","S8X4_UN030","1.04.06.06","CBX40606","Network & Monumentation- Undulator Hall & BD","2007-12-05","2007-12-18",null,"C","SL_TMUO2","Hrs",80,null,6475.0842288,null,6475.0842288,null,80,null,6475.0842288,null,6475.0842288,null,null,6475.0842288,1,{"$nulls":13},4,"4B"]
["1","04","06","06","","","S8X4_UN140","1.04.06.06","CBX40606","Install Racks & cable plant Und (2.3 & 3.1)","2008-01-28","2008-05-19",null,"C","SL_MFAT2","Hrs",272,null,23911.094591999998,null,23911.094591999998,null,272,null,23911.094591999998,null,23911.094591999998,null,null,23911.094591999998,1,{"$nulls":13},4,"4B"]
["1","04","06","06","","","S8X4_UN150","1.04.06.06","CBX40606","Install Undulator Girders 1-10","2008-05-30","2008-06-12",null,"C","SL_MES2","Hrs",296,null,24242.09552280331,null,24242.09552280331,null,296,null,24242.09552280331,null,24242.09552280331,null,null,24242.09552280331,1,{"$nulls":13},4,"4B"]
["1","04","06","06","","","S8X4_UN150","1.04.06.06","CBX40606","Install Undulator Girders 1-10","2008-05-30","2008-06-12",null,"C","AN_MVE2","Hrs",6,null,676.2754778796048,null,676.2754778796048,null,6,null,676.2754778796048,null,676.2754778796048,null,null,676.2754778796048,1,{"$nulls":13},4,"4B"]
["1","04","06","06","","","S8X4_UN160","1.04.06.06","CBX40606","Install Undulator Girders 11-20","2008-07-14","2008-07-23",null,"C","AN_MVE2","Hrs",6,null,676.2754778796048,null,676.2754778796048,null,6,null,676.2754778796048,null,676.2754778796048,null,null,676.2754778796048,1,{"$nulls":13},4,"4B"]
["1","04","06","06","","","S8X4_UN170","1.04.06.06","CBX40606","Install Undulator Girders 21-30","2008-08-25","2008-09-04",null,"C","SL_TMUW2","Hrs",80,null,6190.76323008,null,6190.76323008,null,80,null,6190.76323008,null,6190.76323008,null,null,6190.76323008,1,{"$nulls":13},4,"4B"]
["1","04","06","06","","","S8X4_UN180","1.04.06.06","CBX40606","Install Undulator Girders 30-33","2008-09-08","2008-09-17",null,"C","SL_TMUW2","Hrs",25,null,1934.6135093999997,null,1934.6135093999997,null,25,null,1934.6135093999997,null,1934.6135093999997,null,null,1934.6135093999997,1,{"$nulls":13},4,"4B"]
["1","04","06","06","","","S8X4_UN180","1.04.06.06","CBX40606","Install Undulator Girders 30-33","2008-09-08","2008-09-17",null,"C","AN_SEE2","Hrs",2,null,225.4251592932016,null,225.4251592932016,null,2,null,225.4251592932016,null,225.4251592932016,null,null,225.4251592932016,1,{"$nulls":13},4,"4B"]
["1","04","06","06","","","S8X4_UN190","1.04.06.06","CBX40606","Install Undulators","2008-09-18","2008-10-15",null,"C","SL_CE2","Hrs",264,null,30800.377336963764,null,30800.377336963764,null,264,null,30800.377336963764,null,30800.377336963764,null,null,14829.81131038996,0.48,15970.566026573802,0.52,{"$nulls":11},4,"4B"]
["1","04","06","06","","","S8X4_UN210","1.04.06.06","CBX40606","Checkout Undulator System","2008-10-31","2008-12-01",null,"C","AN_MDD2","Hrs",32,null,2166.313685893362,null,2166.313685893362,null,32,null,2166.313685893362,null,2166.313685893362,{"$nulls":4},2166.313685893362,1,{"$nulls":11},4,"4B"]
["1","05","01","01","01","","XT1111020","1.05.01.01.01","CAD50101","Management & Oversight - FY07","2007-05-01","2007-09-28",null,"C","LL_PHSS2","Hrs",714,null,152194.66096153844,null,152194.66096153844,null,714,null,152194.66096153844,null,152194.66096153844,152194.66096153844,1,{"$nulls":10},0.17,25873.092363461536,1.15,1.02,4,1,"5A"]
["1","05","01","01","01","","XT1111020","1.05.01.01.01","CAD50101","Management & Oversight - FY07","2007-05-01","2007-09-28",null,"C","LL_MSTR2","$$",null,12300,null,14973.650999999998,14973.650999999998,null,null,12300,null,14973.650999999998,14973.650999999998,14973.650999999998,1,{"$nulls":10},0.17,2545.52067,1.15,1.02,4,1,"5A"]
["1","05","01","01","02","","XT1112100","1.05.01.01.02","CAD50102","LLNL Support for EIR","2007-05-01","2007-06-29",null,"C","LL_PHS2","Hrs",215,null,41502.14110096153,null,41502.14110096153,null,215,null,41502.14110096153,null,41502.14110096153,41502.14110096153,1,{"$nulls":10},0.17,7055.363987163461,1.15,1.02,4,1,"5A"]
["1","05","01","01","02","","XT1112100","1.05.01.01.02","CAD50102","LLNL Support for EIR","2007-05-01","2007-06-29",null,"C","LL_PHPD2","Hrs",10,null,0,null,0,null,10,null,0,null,0,{"$nulls":12},0.17,0,1.15,1.02,4,1,"5A"]
["1","05","01","01","02","","XT1113030","1.05.01.01.02","CAD50102","Project Support M&S FY09/FY10","2008-10-01","2010-05-31",null,"C","LL_MSCS2","$$",null,30795,null,36931.2709111243,null,null,null,30795,null,36931.2709111243,36931.2709111243,{"$nulls":4},22207.436379835868,0.6,14723.834531288438,0.4,{"$nulls":8},4,1,"5A"]
["1","05","02","01","  ","  ",null,null,null,"Controls - EPICS                                            ",{"$nulls":6},3354,850000,571308.5639263666,966965.7696,1538274.3335263666,null,3354,850000,571308.5639263666,966965.7696,1538274.3335263666,151318.05540167936,null,1055407.2713004416,null,265695.5353608726,null,65853.47146337308,null,0,null,0,null,null,307654.8667052733,{"$nulls":6},"Gunter Haller"]
["1","05","02","01","","","XT_CRLOE","1.05.02.01","CAD50201","Add'l Manpower due to CR","2007-05-01","2010-05-31","L","C","LL_CE2","Hrs",823,null,154289.7646281415,null,154289.7646281415,null,823,null,154289.7646281415,null,154289.7646281415,20964.772635973048,0.14,50151.024737033564,0.33,50014.00007928211,0.32,33159.96717585279,0.21,{"$nulls":4},0.2,30857.952925628302,1.15,1.05,4,2,"2H","S. Lewis"]
["1","05","02","03","  ","  ",null,null,null,"Controls - Vacuum                                           ",{"$nulls":37},"Gunter Haller"]
["1","05","03","01","","","XT1310040","1.05.03.01","CBD50301","Assemble/Test Valve Pressure Manifolds (11)","2007-11-28","2007-12-26",null,"C","LL_MFAT2","Hrs",160,null,22976.383190538465,null,22976.383190538465,null,160,null,22976.383190538465,null,22976.383190538465,null,null,22976.383190538465,1,{"$nulls":8},0.19,4365.512806202309,1.15,1.04,4,3,"5A"]
["1","05","03","02","","","XT1320020","1.05.03.02","CBD50302","PRD Review - FEE Mech/Vac","2007-05-01","2007-06-07",null,"C","LL_PHS2","Hrs",5,null,965.1660721153846,null,965.1660721153846,null,5,null,965.1660721153846,null,965.1660721153846,965.1660721153846,1,{"$nulls":10},0.25,241.29151802884616,1.2,1.05,4,2,"5A"]
["1","05","03","02","","","XT1320065","1.05.03.02","CBD50302","Prepare ESD - FEE Mech/Vac","2007-06-08","2007-07-06",null,"C","LL_ME2","Hrs",16,null,2890.494369230769,null,2890.494369230769,null,16,null,2890.494369230769,null,2890.494369230769,2890.494369230769,1,{"$nulls":10},0.25,722.6235923076922,1.2,1.05,4,2,"5A"]
["1","05","03","02","","","XT1320070","1.05.03.02","CBD50302","Preliminary Engineering/Design - FEE Mech/Vac","2007-06-08","2007-07-31",null,"C","LL_EE2","Hrs",17,null,3071.150267307692,null,3071.150267307692,null,17,null,3071.150267307692,null,3071.150267307692,3071.150267307692,1,{"$nulls":10},0.25,767.787566826923,1.2,1.05,4,2,"5A"]
["1","05","03","02","","","XT1320150","1.05.03.02","CBD50302","Final Design Review - FEE Mech/Vac","2007-08-29","2007-09-12",null,"C","LL_ME2","Hrs",20,null,3613.117961538461,null,3613.117961538461,null,20,null,3613.117961538461,null,3613.117961538461,3613.117961538461,1,{"$nulls":10},0.25,903.2794903846152,1.2,1.05,4,2,"5A"]
["1","05","03","02","","","XT1320190","1.05.03.02","CBD50302","Fab/Deliver - FEE Mech/Vac","2007-10-29","2008-03-03",null,"C","LL_ME2","Hrs",30,null,5544.329511980769,null,5544.329511980769,null,30,null,5544.329511980769,null,5544.329511980769,null,null,5544.329511980769,1,{"$nulls":8},0.25,1386.0823779951922,1.2,1.05,5,2,"5A"]
["1","05","03","02","","","XT1320190","1.05.03.02","CBD50302","Fab/Deliver - FEE Mech/Vac","2007-10-29","2008-03-03",null,"C","LA_MSEQ2","$$",null,296000,null,343847.56824,343847.56824,null,null,296000,null,343847.56824,343847.56824,null,null,343847.56824,1,{"$nulls":8},0.25,85961.89206,1.2,1.05,5,2,"5A"]
["1","05","03","02","","","XT1325090","1.05.03.02","CBE50302","Prepare Safety Note - Wall 1 & 2","2007-05-01","2007-05-30",null,"C","LL_ME2","Hrs",114,null,20594.772380769227,null,20594.772380769227,null,114,null,20594.772380769227,null,20594.772380769227,20594.772380769227,1,{"$nulls":10},0.25,5148.693095192307,1.2,1.05,4,2,"5A"]
["1","05","03","02","","","XT1325140","1.05.03.02","CBE50302","Bid Prep/RFP/Award - Wall 1 & 2","2007-07-20","2007-08-30",null,"C","LL_ME2","Hrs",40,null,7226.235923076922,null,7226.235923076922,null,40,null,7226.235923076922,null,7226.235923076922,7226.235923076922,1,{"$nulls":10},0.25,1806.5589807692304,1.2,1.05,4,2,"5A"]
["1","05","03","02","","","XT1325160","1.05.03.02","CBE50302","AWARD: Wall 1 & 2","2007-10-01","2007-10-01",null,"C","LL_AWARD","$$",null,56886,null,75379.88150322,75379.88150322,null,null,56886,null,75379.88150322,75379.88150322,null,null,75379.88150322,1,{"$nulls":8},0.25,18844.970375805,1.2,1.05,4,2,"5A"]
["1","05","03","02","","","XT1325190","1.05.03.02","CBE50302","Readiness Review - Wall 1 & 2","2008-02-12","2008-02-19",null,"C","LL_ME2","Hrs",40,null,7392.439349307692,null,7392.439349307692,null,40,null,7392.439349307692,null,7392.439349307692,null,null,7392.439349307692,1,{"$nulls":8},0.25,1848.109837326923,1.2,1.05,5,2,"5A"]
["1","05","03","02","","","XT1325210","1.05.03.02","CBE50302","Ship to SLAC - Wall 1 & 2","2008-02-20","2008-02-26",null,"C","LL_ADMN2","Hrs",8,null,1123.1389479115385,null,1123.1389479115385,null,8,null,1123.1389479115385,null,1123.1389479115385,null,null,1123.1389479115385,1,{"$nulls":8},0.25,280.7847369778846,1.2,1.05,4,2,"5A"]
["1","05","03","02","","","XT1327040","1.05.03.02","CBF50302","Final Design Review - Shadow Wall","2007-06-20","2007-06-26",null,"C","LL_ME2","Hrs",40,null,7226.235923076922,null,7226.235923076922,null,40,null,7226.235923076922,null,7226.235923076922,7226.235923076922,1,{"$nulls":10},0.25,1806.5589807692304,1.2,1.05,4,2,"5A"]
["1","05","03","02","","","XT1327070","1.05.03.02","CBF50302","Bid Prep/RFP/Award - Shadow Wall","2007-07-12","2007-08-22",null,"C","LL_ADMN2","Hrs",40,null,5489.437673076923,null,5489.437673076923,null,40,null,5489.437673076923,null,5489.437673076923,5489.437673076923,1,{"$nulls":10},0.25,1372.3594182692307,1.2,1.05,4,2,"5A"]
["1","05","03","02","","","XT1327100","1.05.03.02","CBF50302","Assemble @ LLNL - Shadow Wall","2008-01-14","2008-01-18",null,"C","LL_MFAT2","Hrs",32,null,4595.276638107693,null,4595.276638107693,null,32,null,4595.276638107693,null,4595.276638107693,null,null,4595.276638107693,1,{"$nulls":8},0.25,1148.8191595269232,1.2,1.05,5,2,"5A"]
["1","05","03","03","  ","  ",null,null,null,"Mech/Vac Near Hall                                          ",{"$nulls":6},688,209000,115375.0336791528,242784.26271,358159.2963891528,null,688,209000,115375.0336791528,242784.26271,358159.2963891528,79566.73377225985,null,278592.562616893,null,0,null,0,null,0,null,0,null,null,93121.41706117975,{"$nulls":6},"Donn McMahon"]
["1","05","03","03","01","","XT1331070","1.05.03.03.01","CBD50303","Preliminary Engineering/Design - NEH Mech/Vac","2007-05-01","2007-06-29",null,"C","LL_ME2","Hrs",31,null,5600.332840384614,null,5600.332840384614,null,31,null,5600.332840384614,null,5600.332840384614,5600.332840384614,1,{"$nulls":10},0.26,1456.0865384999997,1.2,1.06,4,2,"5A"]
["1","05","03","03","01","","XT1331080","1.05.03.03.01","CBD50303","Preliminary Design Review - NEH Mech/Vac","2007-07-02","2007-07-16",null,"C","LL_MDD2","Hrs",20,null,3314.7364038461537,null,3314.7364038461537,null,20,null,3314.7364038461537,null,3314.7364038461537,3314.7364038461537,1,{"$nulls":10},0.26,861.831465,1.2,1.06,4,2,"5A"]
["1","05","03","03","01","","XT1331140","1.05.03.03.01","CBD50303","Bid Prep/RFP/Award - NEH Mech/Vac","2007-08-14","2007-10-10",null,"C","LL_ME2","Hrs",16,null,2900.991427729554,null,2900.991427729554,null,16,null,2900.991427729554,null,2900.991427729554,2442.9401496669925,0.84,458.0512780625611,0.16,{"$nulls":8},0.26,754.257771209684,1.2,1.06,4,2,"5A"]
["1","05","03","03","01","","XT1331150","1.05.03.03.01","CBD50303","AWARD: NEH Mech/Vac","2007-10-11","2007-10-11",null,"C","LL_AWARD","$$",null,238260,null,315719.34337019996,315719.34337019996,null,null,238260,null,315719.34337019996,315719.34337019996,null,null,315719.34337019996,1,{"$nulls":8},0.26,82087.029276252,1.2,1.06,4,2,"5A"]
["1","05","03","03","01","","XT1331200","1.05.03.03.01","CBD50303","Ship to SLAC - NEH Mech/Vac","2008-04-01","2008-04-14",null,"C","LL_ME2","Hrs",4,null,739.2439349307692,null,739.2439349307692,null,4,null,739.2439349307692,null,739.2439349307692,null,null,739.2439349307692,1,{"$nulls":8},0.26,192.203423082,1.2,1.06,4,2,"5A"]
["1","05","03","04","","","XT1340040","1.05.03.04","CBD50304","Prepare oper/maint proced - Tunnel Mech/Vac","2008-10-01","2008-12-11",null,"C","LL_ME2","Hrs",100,null,18906.160686730767,null,18906.160686730767,null,100,null,18906.160686730767,null,18906.160686730767,{"$nulls":4},18906.160686730767,1,{"$nulls":6},0.19,3592.1705304788456,1.15,1.04,5,2,"5A"]
["1","05","03","04","","","XT1340140","1.05.03.04","CBD50304","Bid Prep/RFP/Award - Tunnel Mech/Vac","2007-05-01","2008-10-01",null,"C","LL_MDD2","Hrs",13,null,2189.5251811530343,null,2189.5251811530343,null,13,null,2189.5251811530343,null,2189.5251811530343,645.4669609179466,0.29,1544.0582202350877,0.71,0,0,{"$nulls":6},0.19,416.00978441907654,1.15,1.04,4,2,"5A"]
["1","05","03","04","","","XT1340180","1.05.03.04","CBD50304","Readiness Review - Tunnel Mech/Vac","2009-03-26","2009-04-08",null,"C","LL_MFAT2","Hrs",10,null,1469.0522710913465,null,1469.0522710913465,null,10,null,1469.0522710913465,null,1469.0522710913465,{"$nulls":4},1469.0522710913465,1,{"$nulls":6},0.19,279.11993150735583,1.15,1.04,5,2,"5A"]
["1","05","03","05","","","XT1351020","1.05.03.05","CBD50305","PRD Review - FEH Mech/Vac","2007-06-01","2007-06-07",null,"C","LL_ME2","Hrs",10,null,1806.5589807692304,null,1806.5589807692304,null,10,null,1806.5589807692304,null,1806.5589807692304,1806.5589807692304,1,{"$nulls":10},0.24,433.57415538461527,1.2,1.04,4,2,"5A"]
["1","05","03","05","","","XT1351050","1.05.03.05","CBD50305","Conceptual Design Review - FEH Mech/Vac","2007-06-01","2007-06-14",null,"C","LL_ME2","Hrs",10,null,1806.5589807692304,null,1806.5589807692304,null,10,null,1806.5589807692304,null,1806.5589807692304,1806.5589807692304,1,{"$nulls":10},0.24,433.57415538461527,1.2,1.04,4,2,"5A"]
["1","05","03","05","","","XT1351100","1.05.03.05","CBD50305","Prepare documentation - FEH Mech/Vac","2007-05-15","2007-07-13",null,"C","LL_ME2","Hrs",20,null,3613.117961538461,null,3613.117961538461,null,20,null,3613.117961538461,null,3613.117961538461,3613.117961538461,1,{"$nulls":10},0.24,867.1483107692305,1.2,1.04,5,2,"5A"]
["1","05","03","05","","","XT1351110","1.05.03.05","CBD50305","Final Engineering/Design - FEH Mech/Vac","2007-07-02","2007-08-13",null,"C","LL_MDD2","Hrs",60,null,9944.20921153846,null,9944.20921153846,null,60,null,9944.20921153846,null,9944.20921153846,9944.20921153846,1,{"$nulls":10},0.24,2386.6102107692304,1.2,1.04,4,2,"5A"]
["1","05","03","05","","","XT1351160","1.05.03.05","CBD50305","Fab/Deliver - FEH Mech/Vac","2008-10-02","2009-02-13",null,"C","LA_MSEQ2","$$",null,80000,null,95069.19120000002,95069.19120000002,null,null,80000,null,95069.19120000002,95069.19120000002,{"$nulls":4},95069.19120000002,1,{"$nulls":6},0.24,22816.605888000002,1.2,1.04,5,2,"5A"]
["1","05","03","05","","","XT1351200","1.05.03.05","CBD50305","Ship to SLAC - FEH Mech/Vac","2009-03-16","2009-03-27",null,"C","LL_ADMN2","Hrs",8,null,1148.9709644884615,null,1148.9709644884615,null,8,null,1148.9709644884615,null,1148.9709644884615,{"$nulls":4},1148.9709644884615,1,{"$nulls":6},0.24,275.75303147723076,1.2,1.04,4,2,"5A"]
["1","05","03","05","03","  ",null,null,null,"FEH Hutch 3                                                 ",{"$nulls":37},"Donn McMahon"]
["1","05","04","02","01","","XT1421030","1.05.04.02.01","CBD5040201","Preliminary Design Review - Fast Valve","2007-07-02","2007-07-16",null,"C","LL_ME2","Hrs",15,null,2709.8384711538456,null,2709.8384711538456,null,15,null,2709.8384711538456,null,2709.8384711538456,2709.8384711538456,1,{"$nulls":10},0.17,460.6725400961538,1.15,1.02,4,2,"5A"]
["1","05","04","02","01","","XT1421120","1.05.04.02.01","CBD5040201","Bid Prep/RFP/Award - Fast Valve","2007-08-28","2007-09-25",null,"C","LL_ME2","Hrs",8,null,1445.2471846153844,null,1445.2471846153844,null,8,null,1445.2471846153844,null,1445.2471846153844,1445.2471846153844,1,{"$nulls":10},0.17,245.69202138461537,1.15,1.02,4,2,"5A"]
["1","05","04","02","01","","XT1421130","1.05.04.02.01","CBD5040201","AWARD: Fast Valve","2007-09-26","2007-09-26",null,"C","LL_AWARD","$$",null,28463,null,36760.67180555,36760.67180555,null,null,28463,null,36760.67180555,36760.67180555,36760.67180555,1,{"$nulls":10},0.17,6249.314206943501,1.15,1.02,4,2,"5A"]
["1","05","04","02","01","","XT1421170","1.05.04.02.01","CBD5040201","Ship to SLAC - Fast Valve","2008-01-24","2008-02-06",null,"C","LL_MFAT2","Hrs",20,null,2872.047898817308,null,2872.047898817308,null,20,null,2872.047898817308,null,2872.047898817308,null,null,2872.047898817308,1,{"$nulls":8},0.17,488.2481427989424,1.15,1.02,4,2,"5A"]
["1","05","04","02","02","  ",null,null,null,"Fixed Mask                                                  ",{"$nulls":6},192,32000,30435.220617821222,36351.752036814156,30435.220617821222,null,192,32000,30435.220617821222,36351.752036814156,66786.97265463536,41092.92781162166,null,25694.044843013715,null,0,null,0,null,0,null,0,null,null,12689.524804380722,{"$nulls":6},"Donn McMahon"]
["1","05","04","02","02","","XT1422150","1.05.04.02.02","CBD5040202","Fab/Deliver - Fixed Mask","2007-06-12","2007-10-03",null,"C","LA_MSEQ2","$$",null,32000,null,36351.752036814156,null,null,null,32000,null,36351.752036814156,36351.752036814156,35708.35819545461,0.98,643.3938413595425,0.02,{"$nulls":8},0.19,6906.83288699469,1.15,1.04,5,2,"5A"]
["1","05","04","02","03","","XT1423110","1.05.04.02.03","CBD5040203","Final Design Review - Slit","2007-05-01","2007-05-31",null,"C","LL_ME2","Hrs",2,null,361.3117961538461,null,361.3117961538461,null,2,null,361.3117961538461,null,361.3117961538461,361.3117961538461,1,{"$nulls":10},0.26,93.94106699999999,1.2,1.06,4,2,"5A"]
["1","05","04","02","03","","XT1423130","1.05.04.02.03","CBD5040203","Bid Prep/RFP/Award - Slit","2007-05-30","2007-06-28",null,"C","LL_MDD2","Hrs",6,null,994.420921153846,null,994.420921153846,null,6,null,994.420921153846,null,994.420921153846,994.420921153846,1,{"$nulls":10},0.26,258.5494395,1.2,1.06,4,2,"5A"]
["1","05","04","02","03","","XT1423160","1.05.04.02.03","CBD5040203","Testing @ LLNL - Slit","2007-09-28","2007-12-14",null,"C","LL_ME2","Hrs",160,null,29543.855564571426,null,29543.855564571426,null,160,null,29543.855564571426,null,29543.855564571426,1151.059307710575,0.04,28392.79625686085,0.96,{"$nulls":8},0.26,7681.402446788571,1.2,1.06,5,2,"5A"]
["1","05","04","02","05","","XT1425120","1.05.04.02.05","CBD5040205","Prepare acceptance test plan/proced -Gas/Solid A","2007-05-01","2007-05-18",null,"C","LL_PHS2","Hrs",2,null,386.0664288461538,null,386.0664288461538,null,2,null,386.0664288461538,null,386.0664288461538,386.0664288461538,1,{"$nulls":10},0.28,108.09860007692308,1.2,1.08,5,2,"5A"]
["1","05","04","02","05","","XT1425130","1.05.04.02.05","CBD5040205","Prepare oper/maint proced - Gas/Solid Attenuator","2007-05-01","2007-05-18",null,"C","LL_PHS2","Hrs",2,null,386.0664288461538,null,386.0664288461538,null,2,null,386.0664288461538,null,386.0664288461538,386.0664288461538,1,{"$nulls":10},0.28,108.09860007692308,1.2,1.08,5,2,"5A"]
["1","05","04","02","05","","XT1425150","1.05.04.02.05","CBD5040205","Final Design Review - Gas/Solid Attenuator","2007-05-29","2007-06-11",null,"C","LL_EE2","Hrs",20,null,3613.117961538461,null,3613.117961538461,null,20,null,3613.117961538461,null,3613.117961538461,3613.117961538461,1,{"$nulls":10},0.28,1011.6730292307691,1.2,1.08,4,2,"5A"]
["1","05","04","02","05","","XT1425170","1.05.04.02.05","CBD5040205","Bid Prep/RFP/Award - Gas/Solid Attenuator","2007-05-01","2007-06-29",null,"C","LL_ADMN2","Hrs",72,null,9880.98781153846,null,9880.98781153846,null,72,null,9880.98781153846,null,9880.98781153846,9880.98781153846,1,{"$nulls":10},0.28,2766.676587230769,1.2,1.08,4,2,"5A"]
["1","05","04","02","05","","XT1425200","1.05.04.02.05","CBD5040205","Assembly/Test @ LLNL - Gas/Solid Attenuator","2007-10-01","2008-01-02",null,"C","LL_ME2","Hrs",216,null,39919.17248626154,null,39919.17248626154,null,216,null,39919.17248626154,null,39919.17248626154,null,null,39919.17248626154,1,{"$nulls":8},0.28,11177.368296153232,1.2,1.08,4,2,"5A"]
["1","05","04","02","06","","XT1426060","1.05.04.02.06","CBD5040206","Analysis - TTF Damage Exp.","2007-05-01","2007-05-31",null,"C","LL_PHS2","Hrs",25,null,4825.830360576922,null,4825.830360576922,null,25,null,4825.830360576922,null,4825.830360576922,4825.830360576922,1,{"$nulls":10},0.19,916.9077685096153,1.15,1.04,4,2,"5A"]
["1","05","04","02","07","01","XT14271065","1.05.04.02.07","CBD5040271","Prepare ESD - LE Mirror","2007-05-01","2007-05-30",null,"C","LL_PHS2","Hrs",14,null,2702.4650019230767,null,2702.4650019230767,null,14,null,2702.4650019230767,null,2702.4650019230767,2702.4650019230767,1,{"$nulls":10},0.45,1216.1092508653846,1.35,1.1,4,2,"5A"]
["1","05","04","02","07","01","XT14271080","1.05.04.02.07","CBD5040271","Preliminary Design Review - LE Mirror","2007-07-02","2007-07-16",null,"C","LL_ME2","Hrs",30,null,5419.676942307691,null,5419.676942307691,null,30,null,5419.676942307691,null,5419.676942307691,5419.676942307691,1,{"$nulls":10},0.45,2438.854624038461,1.35,1.1,4,2,"5A"]
["1","05","04","02","07","01","XT14271100","1.05.04.02.07","CBD5040271","Final Engineering/Design - LE Mirror","2007-07-02","2007-09-14",null,"C","LL_PHS2","Hrs",106,null,20461.520728846153,null,20461.520728846153,null,106,null,20461.520728846153,null,20461.520728846153,20461.520728846153,1,{"$nulls":10},0.45,9207.684327980769,1.35,1.1,4,2,"5A"]
["1","05","04","02","07","01","XT14271100","1.05.04.02.07","CBD5040271","Final Engineering/Design - LE Mirror","2007-07-02","2007-09-14",null,"C","LL_EE2","Hrs",25,null,4516.397451923076,null,4516.397451923076,null,25,null,4516.397451923076,null,4516.397451923076,4516.397451923076,1,{"$nulls":10},0.45,2032.3788533653842,1.35,1.1,4,2,"5A"]
["1","05","04","02","07","01","XT14271140","1.05.04.02.07","CBD5040271","AWARD: LE Mirror Substrate","2007-05-31","2007-05-31",null,"C","LL_AWARD","$$",null,233100,null,301054.44253500004,301054.44253500004,null,null,233100,null,301054.44253500004,301054.44253500004,301054.44253500004,1,{"$nulls":10},0.45,135474.49914075003,1.35,1.1,4,2,"5A"]
["1","05","04","02","07","01","XT14271150","1.05.04.02.07","CBD5040271","Fab/Deliver - LE Mirror Substrate","2007-06-01","2007-10-22",null,"C","LL_ADMN2","Hrs",16,null,2203.191568240828,null,2203.191568240828,null,16,null,2203.191568240828,null,2203.191568240828,1879.6459533243428,0.85,323.54561491648525,0.15,{"$nulls":8},0.45,991.4362057083727,1.35,1.1,5,2,"5A"]
["1","05","04","02","07","01","XT14271170","1.05.04.02.07","CBD5040271","Bid Prep/RFP/Award - LE Mirror Mount/Tank System","2007-10-01","2007-10-26",null,"C","LL_EE2","Hrs",8,null,1478.4878698615385,null,1478.4878698615385,null,8,null,1478.4878698615385,null,1478.4878698615385,null,null,1478.4878698615385,1,{"$nulls":8},0.45,665.3195414376924,1.35,1.1,4,2,"5A"]
["1","05","04","02","07","01","XT14271210","1.05.04.02.07","CBD5040271","Readiness Review - LE Mirror","2008-03-12","2008-03-25",null,"C","LL_PHS2","Hrs",20,null,3949.4595670961544,null,3949.4595670961544,null,20,null,3949.4595670961544,null,3949.4595670961544,null,null,3949.4595670961544,1,{"$nulls":8},0.45,1777.2568051932694,1.35,1.1,5,2,"5A"]
["1","05","04","02","07","01","XT14271210","1.05.04.02.07","CBD5040271","Readiness Review - LE Mirror","2008-03-12","2008-03-25",null,"C","LL_EE2","Hrs",4,null,739.2439349307692,null,739.2439349307692,null,4,null,739.2439349307692,null,739.2439349307692,null,null,739.2439349307692,1,{"$nulls":8},0.45,332.6597707188462,1.35,1.1,5,2,"5A"]
["1","05","04","02","07","02","XT14272040","1.05.04.02.07","CBD5040272","Conceptual Engr/Design - HE Mirror","2007-05-01","2007-06-15",null,"C","LL_ME2","Hrs",48,null,8671.483107692307,null,8671.483107692307,null,48,null,8671.483107692307,null,8671.483107692307,8671.483107692307,1,{"$nulls":10},0.45,3902.1673984615386,1.35,1.1,4,2,"5A"]
["1","05","04","02","07","02","XT14272070","1.05.04.02.07","CBD5040272","Preliminary Engineering/Design - HE Mirror","2007-06-18","2007-08-31",null,"C","LL_MDD2","Hrs",216,null,35799.15316153846,null,35799.15316153846,null,216,null,35799.15316153846,null,35799.15316153846,35799.15316153846,1,{"$nulls":10},0.45,16109.618922692307,1.35,1.1,4,2,"5A"]
["1","05","04","02","07","02","XT14272070","1.05.04.02.07","CBD5040272","Preliminary Engineering/Design - HE Mirror","2007-06-18","2007-08-31",null,"C","LL_EE2","Hrs",54,null,9755.418496153845,null,9755.418496153845,null,54,null,9755.418496153845,null,9755.418496153845,9755.418496153845,1,{"$nulls":10},0.45,4389.938323269231,1.35,1.1,4,2,"5A"]
["1","05","04","02","07","02","XT14272100","1.05.04.02.07","CBD5040272","Final Engineering/Design - HE Mirror","2007-09-04","2007-11-05",null,"C","LL_PHS2","Hrs",106,null,20727.19047379327,null,20727.19047379327,null,106,null,20727.19047379327,null,20727.19047379327,9026.357141813198,0.44,11700.833331980073,0.56,{"$nulls":8},0.45,9327.235713206972,1.35,1.1,4,2,"5A"]
["1","05","04","02","07","02","XT14272100","1.05.04.02.07","CBD5040272","Final Engineering/Design - HE Mirror","2007-09-04","2007-11-05",null,"C","LL_EE2","Hrs",25,null,4575.037773677885,null,4575.037773677885,null,25,null,4575.037773677885,null,4575.037773677885,1992.3551595048853,0.44,2582.682614173,0.56,{"$nulls":8},0.45,2058.766998155048,1.35,1.1,4,2,"5A"]
["1","05","04","02","07","02","XT14272130","1.05.04.02.07","CBD5040272","Bid Prep/RFP/Award - HE Mirror Substrate","2007-09-18","2007-10-15",null,"C","LL_ADMN2","Hrs",16,null,2221.96172005641,null,2221.96172005641,null,16,null,2221.96172005641,null,2221.96172005641,1069.8334207679009,0.48,1152.1282992885087,0.52,{"$nulls":8},0.45,999.8827740253845,1.35,1.1,4,2,"5A"]
["1","05","04","02","07","02","XT14272170","1.05.04.02.07","CBD5040272","Bid Prep/RFP/Award - HE Mirror Mount/Tank System","2007-11-20","2008-01-18",null,"C","LL_ADMN2","Hrs",24,null,3369.416843734615,null,3369.416843734615,null,24,null,3369.416843734615,null,3369.416843734615,null,null,3369.416843734615,1,{"$nulls":8},0.45,1516.2375796805768,1.35,1.1,4,2,"5A"]
["1","05","04","02","07","02","XT14272190","1.05.04.02.07","CBD5040272","Fab/Deliver Mount & Tank System - HE Mirror","2008-01-23","2008-04-16",null,"C","LA_MSEQ2","$$",null,205000,null,238137.67395,238137.67395,null,null,205000,null,238137.67395,238137.67395,null,null,238137.67395,1,{"$nulls":8},0.45,107161.9532775,1.35,1.1,5,2,"5A"]
["1","05","04","02","07","02","XT14272210","1.05.04.02.07","CBD5040272","Readiness Review - HE Mirror","2008-06-20","2008-07-03",null,"C","LL_ME2","Hrs",20,null,3696.219674653846,null,3696.219674653846,null,20,null,3696.219674653846,null,3696.219674653846,null,null,3696.219674653846,1,{"$nulls":8},0.45,1663.2988535942309,1.35,1.1,5,2,"5A"]
["1","05","04","03","03","  ",null,null,null,"Optics Tank - Far Hall                                      ",{"$nulls":37},"Donn McMahon"]
["1","05","04","03","04","  ",null,null,null,"K-B Focusing System                                         ",{"$nulls":37},"Donn McMahon"]
["1","05","05","02","  ","  ",null,null,null,"Modeling & Simulation                                       ",{"$nulls":37},"Donn McMahon"]
["1","05","05","02","03","  ",null,null,null,"Beam Simulation                                             ",{"$nulls":37},"Donn McMahon"]
["1","05","05","03","01","","XT1531070","1.05.05.03.01","CBD5050301","Preliminary Engineering/Design - Direct Imager","2007-05-01","2007-06-01",null,"C","LL_EE2","Hrs",66,null,11923.289273076922,null,11923.289273076922,null,66,null,11923.289273076922,null,11923.289273076922,11923.289273076922,1,{"$nulls":10},0.25,2980.8223182692304,1.2,1.05,4,2,"5A"]
["1","05","05","03","01","","XT1531140","1.05.05.03.01","CBD5050301","Final Engineering/Design - Direct Imager","2007-06-04","2007-07-31",null,"C","LL_ME2","Hrs",123,null,22220.675463461535,null,22220.675463461535,null,123,null,22220.675463461535,null,22220.675463461535,22220.675463461535,1,{"$nulls":10},0.25,5555.168865865384,1.2,1.05,4,2,"5A"]
["1","05","05","03","01","","XT1531170","1.05.05.03.01","CBD5050301","Bid Prep/RFP/Award - Direct Imager","2007-05-17","2007-09-19",null,"C","LL_EE2","Hrs",18,null,3251.806165384615,null,3251.806165384615,null,18,null,3251.806165384615,null,3251.806165384615,3251.806165384615,1,{"$nulls":10},0.25,812.9515413461537,1.2,1.05,4,2,"5A"]
["1","05","05","03","01","","XT1531190","1.05.05.03.01","CBD5050301","Fab/Deliver - Direct Imager","2007-06-01","2007-11-14",null,"C","LL_ME2","Hrs",19,null,3453.3876755592673,null,3453.3876755592673,null,19,null,3453.3876755592673,null,3453.3876755592673,2538.0319061339196,0.73,915.3557694253481,0.27,{"$nulls":8},0.25,863.3469188898168,1.2,1.05,5,2,"5A"]
["1","05","05","03","01","","XT1531210","1.05.05.03.01","CBD5050301","Readiness Review - Direct Imager","2008-01-31","2008-02-13",null,"C","LL_ME2","Hrs",10,null,1848.109837326923,null,1848.109837326923,null,10,null,1848.109837326923,null,1848.109837326923,null,null,1848.109837326923,1,{"$nulls":8},0.25,462.02745933173077,1.2,1.05,5,2,"5A"]
["1","05","05","03","01","","XT1531230","1.05.05.03.01","CBD5050301","Ship to SLAC - Direct Imager","2008-02-14","2008-02-28",null,"C","LL_MFAT2","Hrs",20,null,2872.047898817308,null,2872.047898817308,null,20,null,2872.047898817308,null,2872.047898817308,null,null,2872.047898817308,1,{"$nulls":8},0.25,718.011974704327,1.2,1.05,4,2,"5A"]
["1","05","05","03","06","","XT1536093","1.05.05.03.06","CBD5050306","Assemble - Detector Calibration @ SSRL","2007-05-01","2007-05-29",null,"C","LL_MFAT2","Hrs",30,null,4211.213927884615,null,4211.213927884615,null,30,null,4211.213927884615,null,4211.213927884615,4211.213927884615,1,{"$nulls":10},0.43,1810.8219889903846,1.35,1.08,5,2,"5A"]
["1","05","05","03","06","","XT1536094","1.05.05.03.06","CBD5050306","Testing - Detector Calibration @ SSRL","2007-05-30","2007-06-12",null,"C","LL_PHS2","Hrs",20,null,3860.6642884615385,null,3860.6642884615385,null,20,null,3860.6642884615385,null,3860.6642884615385,3860.6642884615385,1,{"$nulls":10},0.43,1660.0856440384616,1.35,1.08,5,2,"5A"]
["1","05","05","03","06","","XT1536120","1.05.05.03.06","CBD5050306","Prepare acceptance test plan/proced - Gas Detect","2007-05-01","2007-06-29",null,"C","LL_ME2","Hrs",15,null,2709.8384711538456,null,2709.8384711538456,null,15,null,2709.8384711538456,null,2709.8384711538456,2709.8384711538456,1,{"$nulls":10},0.43,1165.2305425961536,1.35,1.08,5,2,"5A"]
["1","05","05","03","06","","XT1536150","1.05.05.03.06","CBD5050306","Final Design Review - Gas Detector","2007-07-02","2007-07-16",null,"C","LL_PHS2","Hrs",30,null,5790.996432692307,null,5790.996432692307,null,30,null,5790.996432692307,null,5790.996432692307,5790.996432692307,1,{"$nulls":10},0.43,2490.128466057692,1.35,1.08,4,2,"5A"]
["1","05","05","03","06","","XT1536170","1.05.05.03.06","CBD5050306","Bid Prep/RFP/Award - Gas Detector","2007-07-17","2007-08-27",null,"C","LL_EE2","Hrs",24,null,4335.741553846154,null,4335.741553846154,null,24,null,4335.741553846154,null,4335.741553846154,4335.741553846154,1,{"$nulls":10},0.43,1864.368868153846,1.35,1.08,4,2,"5A"]
["1","05","05","03","06","","XT1536190","1.05.05.03.06","CBD5050306","Fab/Deliver - Gas Detector","2007-08-29","2007-12-07",null,"C","LL_ME2","Hrs",20,null,3668.796109325769,null,3668.796109325769,null,20,null,3668.796109325769,null,3668.796109325769,1210.7027160775037,0.33,2458.0933932482653,0.67,{"$nulls":8},0.43,1577.5823270100807,1.35,1.08,5,2,"5A"]
["1","05","05","03","06","","XT1536210","1.05.05.03.06","CBD5050306","Readiness Review - Gas Detector","2008-03-21","2008-04-03",null,"C","LL_PHS2","Hrs",8,null,1579.7838268384617,null,1579.7838268384617,null,8,null,1579.7838268384617,null,1579.7838268384617,null,null,1579.7838268384617,1,{"$nulls":8},0.43,679.3070455405385,1.35,1.08,5,2,"5A"]
["1","05","05","03","06","","XT1536210","1.05.05.03.06","CBD5050306","Readiness Review - Gas Detector","2008-03-21","2008-04-03",null,"C","LL_MFAT2","Hrs",8,null,1148.8191595269232,null,1148.8191595269232,null,8,null,1148.8191595269232,null,1148.8191595269232,null,null,1148.8191595269232,1,{"$nulls":8},0.43,493.99223859657695,1.35,1.08,5,2,"5A"]
["1","05","05","03","07","","XT1537020","1.05.05.03.07","CBD5050307","PRD Review - NEH Imager","2008-10-29","2008-11-04",null,"C","LL_PHS2","Hrs",10,null,2020.1482534519232,null,2020.1482534519232,null,10,null,2020.1482534519232,null,2020.1482534519232,{"$nulls":4},2020.1482534519232,1,{"$nulls":6},0.25,505.0370633629808,1.2,1.05,4,2,"5A"]
["1","05","05","03","07","","XT1537040","1.05.05.03.07","CBD5050307","Conceptual Engr/Design - NEH Imager","2008-10-29","2008-12-11",null,"C","LL_MDD2","Hrs",90,null,15610.352547894232,null,15610.352547894232,null,90,null,15610.352547894232,null,15610.352547894232,{"$nulls":4},15610.352547894232,1,{"$nulls":6},0.25,3902.588136973558,1.2,1.05,4,2,"5A"]
["1","05","05","03","07","","XT1537070","1.05.05.03.07","CBD5050307","Preliminary Engineering/Design - NEH Imager","2008-12-12","2009-02-09",null,"C","LL_ME2","Hrs",80,null,15124.928549384615,null,15124.928549384615,null,80,null,15124.928549384615,null,15124.928549384615,{"$nulls":4},15124.928549384615,1,{"$nulls":6},0.25,3781.2321373461536,1.2,1.05,4,2,"5A"]
["1","05","05","03","07","","XT1537130","1.05.05.03.07","CBD5050307","Prepare oper/maint proced - NEH Imager","2009-02-10","2009-03-23",null,"C","LL_ME2","Hrs",24,null,4537.478564815385,null,4537.478564815385,null,24,null,4537.478564815385,null,4537.478564815385,{"$nulls":4},4537.478564815385,1,{"$nulls":6},0.25,1134.3696412038462,1.2,1.05,5,2,"5A"]
["1","05","05","03","07","","XT1537150","1.05.05.03.07","CBD5050307","Final Design Review - NEH Imager","2009-04-29","2009-05-12",null,"C","LL_EE2","Hrs",30,null,5671.848206019231,null,5671.848206019231,null,30,null,5671.848206019231,null,5671.848206019231,{"$nulls":4},5671.848206019231,1,{"$nulls":6},0.25,1417.9620515048077,1.2,1.05,4,2,"5A"]
["1","05","05","03","07","","XT1537170","1.05.05.03.07","CBD5050307","Bid Prep/RFP/Award - NEH Imager","2009-05-13","2009-07-30",null,"C","LL_ADMN2","Hrs",40,null,5744.8548224423075,null,5744.8548224423075,null,40,null,5744.8548224423075,null,5744.8548224423075,{"$nulls":4},5744.8548224423075,1,{"$nulls":6},0.25,1436.2137056105769,1.2,1.05,4,2,"5A"]
["1","05","05","03","07","","XT1537200","1.05.05.03.07","CBD5050307","Test @ LLNL - NEH Imager","2009-10-13","2009-11-09",null,"C","LL_EE2","Hrs",60,null,11604.603792346154,null,11604.603792346154,null,60,null,11604.603792346154,null,11604.603792346154,{"$nulls":6},11604.603792346154,1,{"$nulls":4},0.25,2901.1509480865384,1.2,1.05,5,2,"5A"]
["1","05","05","03","07","","XT1537210","1.05.05.03.07","CBD5050307","Readiness Review - NEH Imager","2009-11-10","2009-11-23",null,"C","LL_MFAT2","Hrs",10,null,1502.8407793221158,null,1502.8407793221158,null,10,null,1502.8407793221158,null,1502.8407793221158,{"$nulls":6},1502.8407793221158,1,{"$nulls":4},0.25,375.71019483052896,1.2,1.05,5,2,"5A"]
["1","05","05","04","01","  ",null,null,null,"Commission Diagnostic Tanks                                 ",{"$nulls":37},"Donn McMahon"]
["1","05","05","04","02","","XT1542065","1.05.05.04.02","CBD5050402","Prepare ESD - Total Energy Measurement","2007-05-01","2007-05-30",null,"C","LL_PHS2","Hrs",6,null,1158.1992865384614,null,1158.1992865384614,null,6,null,1158.1992865384614,null,1158.1992865384614,1158.1992865384614,1,{"$nulls":10},0.33,382.20576455769225,1.25,1.08,4,2,"5A"]
["1","05","05","04","02","","XT1542120","1.05.05.04.02","CBD5050402","Prepare acceptance test plan/proced - Total Ener","2007-05-01","2007-05-29",null,"C","LL_PHS2","Hrs",40,null,7721.328576923077,null,7721.328576923077,null,40,null,7721.328576923077,null,7721.328576923077,7721.328576923077,1,{"$nulls":10},0.33,2548.0384303846154,1.25,1.08,5,2,"5A"]
["1","05","05","04","02","","XT1542150","1.05.05.04.02","CBD5050402","Final Design Review - Total Energy Measurement","2007-07-02","2007-07-16",null,"C","LL_PHS2","Hrs",30,null,5790.996432692307,null,5790.996432692307,null,30,null,5790.996432692307,null,5790.996432692307,5790.996432692307,1,{"$nulls":10},0.33,1911.0288227884614,1.25,1.08,4,2,"5A"]
["1","05","05","04","02","","XT1542190","1.05.05.04.02","CBD5050402","Fab/Deliver - Total Energy Measurement","2007-07-18","2007-09-26",null,"C","LA_MSEQ2","$$",null,135000,null,153296.55,153296.55,null,null,135000,null,153296.55,153296.55,153296.55,1,{"$nulls":10},0.33,50587.8615,1.25,1.08,4,3,"5A"]
["1","05","05","04","02","","XT1542192","1.05.05.04.02","CBD5050402","Fab/Deliver - Final Production Sensors (Towson U","2007-05-01","2007-12-14",null,"C","LA_MSEQ2","$$",null,49880,null,57064.91341477004,null,null,null,49880,null,57064.91341477004,57064.91341477004,38462.25441612254,0.67,18602.6589986475,0.33,{"$nulls":8},0.33,18831.421426874113,1.25,1.08,4,3,"5A"]
["1","05","05","04","02","","XT1542210","1.05.05.04.02","CBD5050402","Readiness Review - Total Energy Measurement","2008-03-21","2008-04-03",null,"C","LL_EE2","Hrs",8,null,1478.4878698615385,null,1478.4878698615385,null,8,null,1478.4878698615385,null,1478.4878698615385,null,null,1478.4878698615385,1,{"$nulls":8},0.33,487.9009970543077,1.25,1.08,5,2,"5A"]
["1","05","05","04","02","","XT1542230","1.05.05.04.02","CBD5050402","Ship to SLAC - Total Energy Measurement","2008-04-04","2008-04-17",null,"C","LL_PHS2","Hrs",10,null,1974.7297835480772,null,1974.7297835480772,null,10,null,1974.7297835480772,null,1974.7297835480772,null,null,1974.7297835480772,1,{"$nulls":8},0.33,651.6608285708655,1.25,1.08,4,2,"5A"]
["1","05","05","04","04","","XT1544040","1.05.05.04.04","CBD5050404","Conceptual Engr/Design - Low Energy Spectrometer","2007-06-06","2007-07-09",null,"C","LL_ME2","Hrs",32,null,5780.988738461538,null,5780.988738461538,null,32,null,5780.988738461538,null,5780.988738461538,5780.988738461538,1,{"$nulls":10},0.31,1792.1065089230767,1.25,1.06,4,2,"5A"]
["1","05","05","04","04","","XT1544065","1.05.05.04.04","CBD5050404","Prepare ESD - Low Energy Spectrometer","2007-07-17","2007-08-13",null,"C","LL_ME2","Hrs",16,null,2890.494369230769,null,2890.494369230769,null,16,null,2890.494369230769,null,2890.494369230769,2890.494369230769,1,{"$nulls":10},0.31,896.0532544615384,1.25,1.06,4,2,"5A"]
["1","05","05","04","04","","XT1544070","1.05.05.04.04","CBD5050404","Preliminary Engineering/Design - Low Energy Spec","2007-07-10","2007-08-14",null,"C","LL_EE2","Hrs",104,null,18788.213399999997,null,18788.213399999997,null,104,null,18788.213399999997,null,18788.213399999997,18788.213399999997,1,{"$nulls":10},0.31,5824.346153999999,1.25,1.06,4,2,"5A"]
["1","05","05","04","04","","XT1544140","1.05.05.04.04","CBD5050404","Final Engineering/Design - Low Energy Spectromet","2007-08-15","2007-10-10",null,"C","LL_ME2","Hrs",160,null,29011.788752027467,null,29011.788752027467,null,160,null,29011.788752027467,null,29011.788752027467,24349.179845451625,0.84,4662.608906575843,0.16,{"$nulls":8},0.31,8993.654513128515,1.25,1.06,4,2,"5A"]
["1","05","05","04","04","","XT1544170","1.05.05.04.04","CBD5050404","Bid Prep/RFP/Award - Low Energy Spectrometer","2007-10-11","2007-12-26",null,"C","LL_EE2","Hrs",42,null,7762.061316773077,null,7762.061316773077,null,42,null,7762.061316773077,null,7762.061316773077,null,null,7762.061316773077,1,{"$nulls":8},0.31,2406.239008199654,1.25,1.06,4,2,"5A"]
["1","05","05","04","04","","XT1544190","1.05.05.04.04","CBD5050404","Fab/Deliver - Low Energy Spectrometer","2008-01-03","2008-04-04",null,"C","LL_ME2","Hrs",26,null,4805.08557705,null,4805.08557705,null,26,null,4805.08557705,null,4805.08557705,null,null,4805.08557705,1,{"$nulls":8},0.31,1489.5765288855,1.25,1.06,5,2,"5A"]
["1","05","05","04","04","","XT1544210","1.05.05.04.04","CBD5050404","Readiness Review - Low Energy Spectrometer","2008-05-19","2008-06-02",null,"C","LL_ME2","Hrs",10,null,1848.109837326923,null,1848.109837326923,null,10,null,1848.109837326923,null,1848.109837326923,null,null,1848.109837326923,1,{"$nulls":8},0.31,572.9140495713461,1.25,1.06,5,2,"5A"]
["1","05","05","04","04","","XT1544210","1.05.05.04.04","CBD5050404","Readiness Review - Low Energy Spectrometer","2008-05-19","2008-06-02",null,"C","LL_EE2","Hrs",10,null,1848.109837326923,null,1848.109837326923,null,10,null,1848.109837326923,null,1848.109837326923,null,null,1848.109837326923,1,{"$nulls":8},0.31,572.9140495713461,1.25,1.06,5,2,"5A"]
["1","05","05","04","05","","XT1545020","1.05.05.04.05","CBD5050405","PRD Review - Popup Cameras","2007-07-02","2007-07-09",null,"C","LL_EE2","Hrs",10,null,1806.5589807692304,null,1806.5589807692304,null,10,null,1806.5589807692304,null,1806.5589807692304,1806.5589807692304,1,{"$nulls":10},0.25,451.6397451923076,1.2,1.05,5,2,"5A"]
["1","05","05","04","05","","XT1545065","1.05.05.04.05","CBD5050405","Prepare ESD - Popup Cameras","2007-07-24","2007-08-20",null,"C","LL_PHS2","Hrs",16,null,3088.5314307692306,null,3088.5314307692306,null,16,null,3088.5314307692306,null,3088.5314307692306,3088.5314307692306,1,{"$nulls":10},0.25,772.1328576923077,1.2,1.05,4,2,"5A"]
["1","05","05","04","05","","XT1545070","1.05.05.04.05","CBD5050405","Preliminary Engineering/Design - Popup Cameras","2007-07-24","2007-09-04",null,"C","LL_MDD2","Hrs",180,null,29832.627634615383,null,29832.627634615383,null,180,null,29832.627634615383,null,29832.627634615383,29832.627634615383,1,{"$nulls":10},0.25,7458.156908653846,1.2,1.05,4,2,"5A"]
["1","05","05","04","05","","XT1545130","1.05.05.04.05","CBD5050405","Prepare oper/maint proced - Popup Cameras","2007-09-05","2007-10-16",null,"C","LL_EE2","Hrs",24,null,4372.225232774859,null,4372.225232774859,null,24,null,4372.225232774859,null,4372.225232774859,2772.6306354182034,0.63,1599.5945973566559,0.37,{"$nulls":8},0.25,1093.0563081937148,1.2,1.05,5,2,"5A"]
["1","05","05","04","05","","XT1545170","1.05.05.04.05","CBD5050405","Bid Prep/RFP/Award - Popup Cameras","2007-11-07","2008-01-07",null,"C","LL_ME2","Hrs",24,null,4435.463609584615,null,4435.463609584615,null,24,null,4435.463609584615,null,4435.463609584615,null,null,4435.463609584615,1,{"$nulls":8},0.25,1108.8659023961538,1.2,1.05,4,2,"5A"]
["1","05","05","04","05","","XT1545180","1.05.05.04.05","CBD5050405","AWARD: Popup Cameras","2008-01-08","2008-01-08",null,"C","LL_AWARD","$$",null,55860,null,74020.32452219998,74020.32452219998,null,null,55860,null,74020.32452219998,74020.32452219998,null,null,74020.32452219998,1,{"$nulls":8},0.25,18505.081130549996,1.2,1.05,4,2,"5A"]
["1","05","05","04","05","","XT1545200","1.05.05.04.05","CBD5050405","Test @ LLNL - Popup Cameras","2008-02-14","2008-04-10",null,"C","LL_EE2","Hrs",56,null,10349.415089030768,null,10349.415089030768,null,56,null,10349.415089030768,null,10349.415089030768,null,null,10349.415089030768,1,{"$nulls":8},0.25,2587.353772257692,1.2,1.05,5,2,"5A"]
["1","05","05","04","05","","XT1545220","1.05.05.04.05","CBD5050405","Ship to SLAC - Popup Cameras","2008-04-25","2008-05-08",null,"C","LL_EE2","Hrs",4,null,739.2439349307692,null,739.2439349307692,null,4,null,739.2439349307692,null,739.2439349307692,null,null,739.2439349307692,1,{"$nulls":8},0.25,184.8109837326923,1.2,1.05,4,2,"5A"]
["1","05","05","04","06","","XT1546040","1.05.05.04.06","CBD5050406","Conceptual Design Review - K Meas.","2007-06-01","2007-06-28","S","C","LL_PHS2","Hrs",40,null,7721.328576923077,null,7721.328576923077,null,40,null,7721.328576923077,null,7721.328576923077,7721.328576923077,1,{"$nulls":10},0.31,2393.611858846154,1.25,1.06,4,2,"5A"]
["1","05","05","04","06","","XT1546050","1.05.05.04.06","CBD5050406","Preliminary Design - K Meas.","2007-06-29","2007-08-24","S","C","LL_MDD2","Hrs",80,null,13258.945615384615,null,13258.945615384615,null,80,null,13258.945615384615,null,13258.945615384615,13258.945615384615,1,{"$nulls":10},0.31,4110.273140769231,1.25,1.06,4,2,"5A"]
["1","05","05","04","06","","XT1546060","1.05.05.04.06","CBD5050406","Preliminary Design Review - K Meas.","2007-08-27","2007-09-24","S","C","LL_MDD2","Hrs",40,null,6629.4728076923075,null,6629.4728076923075,null,40,null,6629.4728076923075,null,6629.4728076923075,6629.4728076923075,1,{"$nulls":10},0.31,2055.1365703846154,1.25,1.06,4,2,"5A"]
["1","05","05","04","06","","XT1546110","1.05.05.04.06","CBD5050406","AWARD: Goniometer (3)","2008-02-22","2008-02-22","S","C","LL_AWARD","$$",null,51300,null,67977.84905099998,67977.84905099998,null,null,51300,null,67977.84905099998,67977.84905099998,null,null,67977.84905099998,1,{"$nulls":8},0.31,21073.133205809994,1.25,1.06,4,3,"5A"]
["1","05","05","04","06","","XT1546180","1.05.05.04.06","CBD5050406","Bid and Award - Detector & Electronics","2008-01-09","2008-02-21","S","C","LL_PHS2","Hrs",30,null,5924.189350644231,null,5924.189350644231,null,30,null,5924.189350644231,null,5924.189350644231,null,null,5924.189350644231,1,{"$nulls":8},0.31,1836.4986986997117,1.25,1.06,5,3,"5A"]
["1","05","05","04","06","","XT1546210","1.05.05.04.06","CBD5050406","Prepare Bid Docs - Stand & misc.","2007-12-20","2008-01-08","S","C","LL_PHS2","Hrs",10,null,1974.7297835480772,null,1974.7297835480772,null,10,null,1974.7297835480772,null,1974.7297835480772,null,null,1974.7297835480772,1,{"$nulls":8},0.31,612.1662328999039,1.25,1.06,4,2,"5A"]
["1","05","05","04","06","","XT1546280","1.05.05.04.06","CBD5050406","Fab and Deliver - Pumps & Valves","2008-02-25","2008-05-16","S","C","LA_MSEQ2","$$",null,25000,null,29041.179750000003,29041.179750000003,null,null,25000,null,29041.179750000003,29041.179750000003,null,null,29041.179750000003,1,{"$nulls":8},0.31,9002.7657225,1.25,1.06,4,3,"5A"]
["1","05","05","04","06","","XT1546340","1.05.05.04.06","CBD5050406","Bid and Award - Multilayers","2007-10-09","2007-11-19","S","C","LL_PHS2","Hrs",30,null,5924.189350644231,null,5924.189350644231,null,30,null,5924.189350644231,null,5924.189350644231,null,null,5924.189350644231,1,{"$nulls":8},0.31,1836.4986986997117,1.25,1.06,5,3,"5A"]
["1","05","06","01","  ","  ",null,null,null,"Front End Enclosure Install                                 ",{"$nulls":6},3230,0,380931.2184750803,0,380931.2184750803,null,3230,0,380931.2184750803,0,380931.2184750803,0,null,334103.5526424244,null,46827.6658326559,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Donn McMahon"]
["1","05","06","01","","","S8X6_FE070","1.05.06.01","CBZ50601","Install FEE components - XT","2008-07-21","2008-10-13",null,"C","SL_MVE2","Hrs",4,null,434.6750383677277,null,434.6750383677277,null,4,null,434.6750383677277,null,434.6750383677277,null,null,372.57860431519515,0.86,62.09643405253253,0.14,{"$nulls":11},4,"5A"]
["1","05","06","01","","","S8X6_FE070","1.05.06.01","CBZ50601","Install FEE components - XT","2008-07-21","2008-10-13",null,"C","LL_PHS2","Hrs",226,null,44775.52988244753,null,44775.52988244753,null,226,null,44775.52988244753,null,44775.52988244753,null,null,38379.02561352646,0.86,6396.504268921076,0.14,{"$nulls":11},4,"5A"]
["1","05","06","02","","","S8X7_NH040","1.05.06.02","CBZ50602","Core drill holes: NEH","2008-01-14","2008-01-18",null,"C","SL_TMUP2","Hrs",64,null,6003.091277568,null,6003.091277568,null,64,null,6003.091277568,null,6003.091277568,null,null,6003.091277568,1,{"$nulls":14},"5A"]
["1","05","06","02","","","S8X7_NH140","1.05.06.02","CBZ50602","Checkout NEH System - XT","2008-11-11","2008-12-10",null,"C","SL_MFAT2","Hrs",432,null,38849.896512,null,38849.896512,null,432,null,38849.896512,null,38849.896512,{"$nulls":4},38849.896512,1,{"$nulls":12},"5A"]
["1","05","06","03","","","S8X8_XT030","1.05.06.03","CBZ50603","Hole template layout -  X-ray tunnel","2008-10-15","2008-10-21",null,"C","SL_MES2","Hrs",144,null,12064.699387163808,null,12064.699387163808,null,144,null,12064.699387163808,null,12064.699387163808,{"$nulls":4},12064.699387163808,1,{"$nulls":12},"5A"]
["1","05","06","03","","","S8X8_XT070","1.05.06.03","CBZ50603","Install X-ray tunnel components - XT","2009-06-12","2009-07-10",null,"C","LL_ME2","Hrs",56,null,10587.44998456923,null,10587.44998456923,null,56,null,10587.44998456923,null,10587.44998456923,{"$nulls":4},10587.44998456923,1,{"$nulls":12},"5A"]
["1","05","06","03","","","S8X8_XT100","1.05.06.03","CBZ50603","Checkout X-Ray tunnel systems - XT","2009-08-10","2009-09-04",null,"C","LL_EE2","Hrs",56,null,10587.44998456923,null,10587.44998456923,null,56,null,10587.44998456923,null,10587.44998456923,{"$nulls":4},10587.44998456923,1,{"$nulls":12},"5A"]
["1","05","06","04","","","S8X9_FH070","1.05.06.04","CBZ50604","Install FEH components - XT","2009-07-02","2009-10-16",null,"C","SL_MES2","Hrs",48,null,4034.6556415821155,null,4034.6556415821155,null,48,null,4034.6556415821155,null,4034.6556415821155,{"$nulls":4},3463.713805509175,0.86,570.9418360729409,0.14,{"$nulls":10},"5A"]
["1","05","06","05","","","S8X5_BD060","1.05.06.05","CBZ50605","Install Dump components - XT","2008-04-21","2008-07-15",null,"C","SL_TMUP2","Hrs",32,null,3001.545638784,null,3001.545638784,null,32,null,3001.545638784,null,3001.545638784,null,null,3001.545638784,1,{"$nulls":14},"5A"]
["1","05","06","05","","","S8X5_BD060","1.05.06.05","CBZ50605","Install Dump components - XT","2008-04-21","2008-07-15",null,"C","SL_MES2","Hrs",16,null,1310.3835417731518,null,1310.3835417731518,null,16,null,1310.3835417731518,null,1310.3835417731518,null,null,1310.3835417731518,1,{"$nulls":14},"5A"]
["1","06","01","02","  ","  ",null,null,null,"SSRL Physics                                                ",{"$nulls":37},"Stefan Moeller"]
["1","06","02","01","","","XE201_0320","1.06.02.01","CBB60201","Travel - FY10","2009-10-01","2010-05-31","S","C","SL_MSTR2","$$",null,26580,null,34933.232808,34933.232808,null,null,26580,null,34933.232808,34933.232808,{"$nulls":6},34933.232808,1,{"$nulls":4},0.25,8733.308202,1.15,1.1,2,3,"2H","B. Dalesio"]
["1","06","02","01","","","XECR_0100","1.06.02.01","CBB60201","Add'l Manpower due to CR","2007-05-01","2010-05-31","S","C","SL_CE2","Hrs",4214,null,492841.7110897585,null,492841.7110897585,null,4214,null,492841.7110897585,null,492841.7110897585,66966.94653351071,0.14,160195.44072722166,0.33,159757.74826621835,0.32,105921.57556280777,0.21,{"$nulls":4},0.25,123210.42777243962,1.15,1.1,5,3,"2H","B. Dalesio"]
["1","06","02","05","  ","  ",null,null,null,"X-Ray PPS - Closed (Moved to new WBS Element)               ",{"$nulls":37},"Gunter Haller"]
["1","06","02","05","03","  ",null,null,null,"Tunnel X-Ray PPS - Closed to BCWP                           ",{"$nulls":37},"Gunter Haller"]
["1","06","02","07","01","","XE62710140","1.06.02.07.01","CBB6020701","Controls AMOS Final Design","2007-08-09","2008-01-02","S","C","SL_CP2","Hrs",960,null,80039.425775751,null,80039.425775751,null,960,null,80039.425775751,null,80039.425775751,29055.407987087696,0.36,50984.01778866331,0.64,{"$nulls":8},0.25,20009.85644393775,1.15,1.1,5,2,"2H","B. Dalesio"]
["1","06","02","07","02","","XE62720130","1.06.02.07.02","CBB6020702","RCV: Gammadata XES350","2009-03-30","2009-03-30","S","C","SL_MSEG2","$$",null,35000,null,39269.57132,39269.57132,null,null,35000,null,39269.57132,39269.57132,{"$nulls":4},39269.57132,1,{"$nulls":6},0.25,9817.39283,1.15,1.1,2,3,"2H","B. Dalesio"]
["1","06","02","07","02","","XE62720145","1.06.02.07.02","CBB6020702","Xray Fluorescence Detector H/W Build","2009-03-31","2009-07-07","S","C","SL_CT2","Hrs",261,null,16853.150822199295,null,16853.150822199295,null,261,null,16853.150822199295,null,16853.150822199295,{"$nulls":4},16853.150822199295,1,{"$nulls":6},0.25,4213.287705549824,1.15,1.1,5,3,"2H","B. Dalesio"]
["1","06","02","07","03","","XE62730135","1.06.02.07.03","CBB6020703","RCV: Electronics for Detector","2008-04-15","2008-04-15","S","C","SL_MSEG2","$$",null,9600,null,10528.9189632,10528.9189632,null,null,9600,null,10528.9189632,10528.9189632,null,null,10528.9189632,1,{"$nulls":8},0.25,2632.2297408,1.15,1.1,2,3,"2H","B. Dalesio"]
["1","06","02","07","03","","XE62730180","1.06.02.07.03","CBB6020703","RCV: Digitizer","2008-04-15","2008-04-15","S","C","SL_MSEG2","$$",null,75000,null,82257.17940000001,82257.17940000001,null,null,75000,null,82257.17940000001,82257.17940000001,null,null,82257.17940000001,1,{"$nulls":8},0.25,20564.294850000002,1.15,1.1,2,3,"2H","B. Dalesio"]
["1","06","02","07","03","","XE62730195","1.06.02.07.03","CBB6020703","RCV: Stepper Motor Drives","2008-04-15","2008-04-15","S","C","SL_MSEG2","$$",null,4000,null,4387.049568,4387.049568,null,null,4000,null,4387.049568,4387.049568,null,null,4387.049568,1,{"$nulls":8},0.25,1096.762392,1.15,1.1,2,3,"2H","B. Dalesio"]
["1","06","02","07","04","","XE62740125","1.06.02.07.04","CBB6020704","RCV: I/O","2008-04-15","2008-04-15","S","C","SL_MSEG2","$$",null,2000,null,2193.524784,2193.524784,null,null,2000,null,2193.524784,2193.524784,null,null,2193.524784,1,{"$nulls":8},0.25,548.381196,1.15,1.1,2,3,"2H","B. Dalesio"]
["1","06","02","07","04","","XE62740140","1.06.02.07.04","CBB6020704","RCV: Manipulator","2008-04-15","2008-04-15","S","C","SL_MSEG2","$$",null,6000,null,6580.5743520000005,6580.5743520000005,null,null,6000,null,6580.5743520000005,6580.5743520000005,null,null,6580.5743520000005,1,{"$nulls":8},0.25,1645.1435880000001,1.15,1.1,2,3,"2H","B. Dalesio"]
["1","06","02","07","04","","XE62740175","1.06.02.07.04","CBB6020704","Sample Source H/W Build","2008-04-16","2008-07-18","S","C","SL_CT2","Hrs",522,null,32948.49159546274,null,32948.49159546274,null,522,null,32948.49159546274,null,32948.49159546274,null,null,32948.49159546274,1,{"$nulls":8},0.25,8237.122898865686,1.15,1.1,5,3,"2H","B. Dalesio"]
["1","06","02","07","05","","XE62750145","1.06.02.07.05","CBB6020705","RCV: Stepper Motor Drives","2008-04-15","2008-04-15","S","C","SL_MSEG2","$$",null,72000,null,78966.892224,78966.892224,null,null,72000,null,78966.892224,78966.892224,null,null,78966.892224,1,{"$nulls":8},0.25,19741.723056,1.15,1.1,2,3,"2H","B. Dalesio"]
["1","06","02","07","06","  ",null,null,null,"Refocus Optics                                              ",{"$nulls":6},783,133700,69576.53970590964,146637.1318104,216213.67151630967,null,783,133700,69576.53970590964,146637.1318104,216213.67151630967,0,null,168576.9143855126,null,47636.75713079707,null,0,null,0,null,0,null,null,54053.41787907742,{"$nulls":6},"Gunter Haller"]
["1","06","02","07","06","","XE62760145","1.06.02.07.06","CBB6020706","RCV: Valves","2008-09-30","2008-09-30","S","C","SL_MSEG2","$$",null,16000,null,17548.198272,17548.198272,null,null,16000,null,17548.198272,17548.198272,null,null,17548.198272,1,{"$nulls":8},0.25,4387.049568,1.15,1.1,2,3,"2H","B. Dalesio"]
["1","06","02","07","07","  ",null,null,null,"Diagnostics                                                 ",{"$nulls":6},1598,226350,139999.46993208837,248252.16742919997,388251.63736128836,null,1598,226350,139999.46993208837,248252.16742919997,388251.63736128836,0,null,388251.63736128836,null,0,null,0,null,0,null,0,null,null,97062.90934032209,{"$nulls":6},"Gunter Haller"]
["1","06","02","07","07","","XE62770125","1.06.02.07.07","CBB6020707","RCV:I/O","2008-04-14","2008-04-14","S","C","SL_MSEG2","$$",null,6000,null,6580.5743520000005,6580.5743520000005,null,null,6000,null,6580.5743520000005,6580.5743520000005,null,null,6580.5743520000005,1,{"$nulls":8},0.25,1645.1435880000001,1.15,1.1,2,3,"2H","B. Dalesio"]
["1","06","02","07","07","","XE62770160","1.06.02.07.07","CBB6020707","RCV:gas handling system","2008-04-14","2008-04-14","S","C","SL_MSEG2","$$",null,1500,null,1645.1435880000001,1645.1435880000001,null,null,1500,null,1645.1435880000001,1645.1435880000001,null,null,1645.1435880000001,1,{"$nulls":8},0.25,411.28589700000003,1.15,1.1,2,3,"2H","B. Dalesio"]
["1","06","02","07","07","","XE62770200","1.06.02.07.07","CBB6020707","RCV:beam stop electronics","2008-04-14","2008-04-14","S","C","SL_MSEG2","$$",null,12000,null,13161.148704000001,13161.148704000001,null,null,12000,null,13161.148704000001,13161.148704000001,null,null,13161.148704000001,1,{"$nulls":8},0.25,3290.2871760000003,1.15,1.1,2,3,"2H","B. Dalesio"]
["1","06","02","07","07","","XE62770215","1.06.02.07.07","CBB6020707","Diagnostics H/W Build","2008-04-15","2008-07-30","S","C","SL_CT2","Hrs",551,null,34778.96335076623,null,34778.96335076623,null,551,null,34778.96335076623,null,34778.96335076623,null,null,34778.96335076623,1,{"$nulls":8},0.25,8694.740837691557,1.15,1.1,5,3,"2H","B. Dalesio"]
["1","06","02","08","02","  ",null,null,null,"X2 Praticle Imaging                                         ",{"$nulls":6},702,0,60367.680610935466,0,60367.680610935466,null,702,0,60367.680610935466,0,60367.680610935466,0,null,0,null,60367.680610935466,null,0,null,0,null,0,null,null,15091.920152733866,{"$nulls":6},"Gunter Haller"]
["1","06","02","10","  ","  ",null,null,null,"Global Controls System                                      ",{"$nulls":6},14475,1664860,1324356.3073122439,1827287.7269673601,3151644.0342796035,null,14475,1664860,1324356.3073122439,1827287.7269673601,3151644.0342796035,675197.9745068614,null,1791068.603879886,null,685377.4558928561,null,0,null,0,null,0,null,null,724962.3986262825,{"$nulls":6},"Gunter Haller"]
["1","06","02","10","01","","XE221_0140","1.06.02.10.01","CBB6021001","Controls Network Final Design","2007-06-15","2007-07-13","S","C","SL_CP2","Hrs",120,null,9860.465646504,null,9860.465646504,null,120,null,9860.465646504,null,9860.465646504,9860.465646504,1,{"$nulls":10},0.25,2465.116411626,1.15,1.1,5,2,"2H","B. Dalesio"]
["1","06","02","10","02","","XE222_0140","1.06.02.10.02","CBB6021002","Controls MPS Final Design","2007-10-30","2007-11-28","S","C","SL_CP2","Hrs",120,null,10087.256356373591,null,10087.256356373591,null,120,null,10087.256356373591,null,10087.256356373591,null,null,10087.256356373591,1,{"$nulls":8},0.25,2521.814089093398,1.15,1.1,5,2,"2H","B. Dalesio"]
["1","06","02","10","02","","XE222_0145","1.06.02.10.02","CBB6021002","Final Design Review (FDR)","2007-11-29","2007-11-29","S","C","SL_CP2","Hrs",40,null,3362.418785457864,null,3362.418785457864,null,40,null,3362.418785457864,null,3362.418785457864,null,null,3362.418785457864,1,{"$nulls":8},0.25,840.604696364466,1.15,1.1,5,2,"2H","B. Dalesio"]
["1","06","02","10","03","","XE223_0145","1.06.02.10.03","CBB6021003","Final Design Review (FDR)","2007-11-29","2007-11-29","S","C","SL_CP2","Hrs",160,null,13449.675141831456,null,13449.675141831456,null,160,null,13449.675141831456,null,13449.675141831456,null,null,13449.675141831456,1,{"$nulls":8},0.25,3362.418785457864,1.15,1.1,5,2,"2H","B. Dalesio"]
["1","06","02","10","03","","XE223_0175","1.06.02.10.03","CBB6021003","RCV: 12 Near Hall 36PR16AS cable","2008-01-14","2008-01-14","S","C","SL_MSEG2","$$",null,24000,null,26322.297408000002,26322.297408000002,null,null,24000,null,26322.297408000002,26322.297408000002,null,null,26322.297408000002,1,{"$nulls":8},0.25,6580.5743520000005,1.15,1.1,2,3,"2H","B. Dalesio"]
["1","06","02","10","03","","XE223_0250","1.06.02.10.03","CBB6021003","RCV: Far Hall PLC Control Package","2008-10-28","2008-10-28","S","C","SL_MSEG2","$$",null,20000,null,22439.755040000004,22439.755040000004,null,null,20000,null,22439.755040000004,22439.755040000004,{"$nulls":4},22439.755040000004,1,{"$nulls":6},0.25,5609.938760000001,1.15,1.1,2,3,"2H","B. Dalesio"]
["1","06","02","10","04","","XE224_0130","1.06.02.10.04","CBB6021004","Preliminary Design Review (PDR)","2007-11-29","2007-11-29","S","C","SL_CP2","Hrs",40,null,3362.418785457864,null,3362.418785457864,null,40,null,3362.418785457864,null,3362.418785457864,null,null,3362.418785457864,1,{"$nulls":8},0.25,840.604696364466,1.15,1.1,5,2,"2H","B. Dalesio"]
["1","06","02","10","04","","XE224_0155","1.06.02.10.04","CBB6021004","Controls Laser PPS Software Development","2008-01-16","2008-02-13","S","C","SL_CP2","Hrs",200,null,16812.09392728932,null,16812.09392728932,null,200,null,16812.09392728932,null,16812.09392728932,null,null,16812.09392728932,1,{"$nulls":8},0.25,4203.02348182233,1.15,1.1,5,2,"2H","B. Dalesio"]
["1","06","02","10","04","","XE224_0225","1.06.02.10.04","CBB6021004","RCV: PLC Control Package","2008-02-13","2008-02-13","S","C","SL_MSEG2","$$",null,15000,null,16451.43588,16451.43588,null,null,15000,null,16451.43588,16451.43588,null,null,16451.43588,1,{"$nulls":8},0.25,4112.85897,1.15,1.1,2,3,"2H","B. Dalesio"]
["1","06","02","10","05","","XE225_0115","1.06.02.10.05","CBB6021005","Safety Review Near Hall - User Safeguards","2008-01-11","2008-03-10","S","C","SL_CE2","Hrs",40,null,4611.725128250063,null,4611.725128250063,null,40,null,4611.725128250063,null,4611.725128250063,null,null,4611.725128250063,1,{"$nulls":8},0.25,1152.9312820625157,1.15,1.1,5,3,"2H","B. Dalesio"]
["1","06","02","10","05","","XE225_0120","1.06.02.10.05","CBB6021005","Prep Bid Pkg Near Hall Alarms/Signs - User Safeg","2008-03-11","2008-03-24","S","C","SL_CE2","Hrs",40,null,4611.725128250063,null,4611.725128250063,null,40,null,4611.725128250063,null,4611.725128250063,null,null,4611.725128250063,1,{"$nulls":8},0.25,1152.9312820625157,1.15,1.1,5,3,"2H","B. Dalesio"]
["1","06","02","10","05","","XE225_0305","1.06.02.10.05","CBC6021005","Specification Far Hall - User Safeguards","2007-10-01","2007-10-26","S","C","SL_CE2","Hrs",40,null,4611.725128250063,null,4611.725128250063,null,40,null,4611.725128250063,null,4611.725128250063,null,null,4611.725128250063,1,{"$nulls":8},0.25,1152.9312820625157,1.15,1.1,5,2,"2H","B. Dalesio"]
["1","06","02","10","05","","XE225_0310","1.06.02.10.05","CBC6021005","Design Far Hall - User Safeguards","2007-10-29","2008-01-10","S","C","SL_MDD2","Hrs",40,null,3416.357091051432,null,3416.357091051432,null,40,null,3416.357091051432,null,3416.357091051432,null,null,3416.357091051432,1,{"$nulls":8},0.25,854.089272762858,1.15,1.1,5,2,"2H","B. Dalesio"]
["1","06","02","10","05","","XE225_0355","1.06.02.10.05","CBC6021005","AWARD: Contract Far Hall Alarms/Signs -User Saf","2008-10-01","2008-10-01","S","C","SL_AWARD","$$",null,5500,null,6660.68755,6660.68755,null,null,5500,null,6660.68755,6660.68755,{"$nulls":4},6660.68755,1,{"$nulls":11},3,"2H","B. Dalesio"]
["1","06","02","10","06","","XE226_0130","1.06.02.10.06","CBB6021006","Preliminary Design Review (PDR)","2007-10-29","2007-10-29","S","C","SL_CP2","Hrs",40,null,3362.418785457864,null,3362.418785457864,null,40,null,3362.418785457864,null,3362.418785457864,null,null,3362.418785457864,1,{"$nulls":8},0.25,840.604696364466,1.15,1.1,5,2,"2H","B. Dalesio"]
["1","06","02","10","06","","XE226_0155","1.06.02.10.06","CBB6021006","Controls Timing System Software Development","2007-11-30","2008-01-14","S","C","SL_CP2","Hrs",240,null,20174.512712747182,null,20174.512712747182,null,240,null,20174.512712747182,null,20174.512712747182,null,null,20174.512712747182,1,{"$nulls":8},0.25,5043.628178186796,1.15,1.1,5,2,"2H","B. Dalesio"]
["1","06","02","10","07","","XE227_0110","1.06.02.10.07","CBB6021007","Controls Data Management Conceptual Design","2007-05-01","2007-05-29","S","C","SL_CP2","Hrs",109,null,8956.5896289078,null,8956.5896289078,null,109,null,8956.5896289078,null,8956.5896289078,8956.5896289078,1,{"$nulls":10},0.3,2686.9768886723396,1.15,1.15,5,2,"2H","B. Dalesio"]
["1","06","02","10","07","","XE227_0185","1.06.02.10.07","CBB6021007","Installation: Controls Data Management Releas 1","2007-11-27","2008-01-14","S","C","SL_CE2","Hrs",109,null,12566.950974481422,null,12566.950974481422,null,109,null,12566.950974481422,null,12566.950974481422,null,null,12566.950974481422,1,{"$nulls":8},0.3,3770.0852923444263,1.15,1.15,5,3,"2H","B. Dalesio"]
["1","06","02","10","07","","XE227_0190","1.06.02.10.07","CBB6021007","Test Release 1","2008-01-15","2008-02-13","S","C","SL_CP2","Hrs",109,null,9162.59119037268,null,9162.59119037268,null,109,null,9162.59119037268,null,9162.59119037268,null,null,9162.59119037268,1,{"$nulls":8},0.3,2748.7773571118037,1.15,1.15,5,3,"2H","B. Dalesio"]
["1","06","02","10","07","","XE227_0235","1.06.02.10.07","CBB6021007","Installation: Controls Data Management Releas 3","2009-02-05","2009-03-04","S","C","SL_CE2","Hrs",54,null,6369.021994882299,null,6369.021994882299,null,54,null,6369.021994882299,null,6369.021994882299,{"$nulls":4},6369.021994882299,1,{"$nulls":6},0.3,1910.7065984646895,1.15,1.15,5,3,"2H","B. Dalesio"]
["1","06","02","10","08","","XE228_0105","1.06.02.10.08","CBB6021008","Develop Cabling & Racks ICDs","2007-10-01","2007-10-12","S","C","SL_CE2","Hrs",120,null,13835.17538475019,null,13835.17538475019,null,120,null,13835.17538475019,null,13835.17538475019,null,null,13835.17538475019,1,{"$nulls":8},0.25,3458.7938461875474,1.15,1.1,5,2,"2H","B. Dalesio"]
["1","06","02","10","08","","XE228_0170","1.06.02.10.08","CBB6021008","Cabling & Racks Hardware Development","2007-12-03","2007-12-14","S","C","SL_CE2","Hrs",240,null,27670.35076950038,null,27670.35076950038,null,240,null,27670.35076950038,null,27670.35076950038,null,null,27670.35076950038,1,{"$nulls":8},0.25,6917.587692375095,1.15,1.1,5,3,"2H","B. Dalesio"]
["1","06","02","10","10","","XE2210_005","1.06.02.10.10","CBB6021010","Develop High Level Apps ICDs","2007-05-01","2007-05-29","S","C","SL_CP2","Hrs",104,null,8545.7368936368,null,8545.7368936368,null,104,null,8545.7368936368,null,8545.7368936368,8545.7368936368,1,{"$nulls":10},0.25,2136.4342234092,1.15,1.1,5,2,"2H","B. Dalesio"]
["1","06","02","10","10","","XE2210_055","1.06.02.10.10","CBB6021010","High Level Apps SW Release 1","2007-08-27","2007-10-22","S","C","SL_CP2","Hrs",326,null,27018.64137534885,null,27018.64137534885,null,326,null,27018.64137534885,null,27018.64137534885,16886.65085959303,0.63,10131.990515755819,0.38,{"$nulls":8},0.25,6754.660343837212,1.15,1.1,5,3,"2H","B. Dalesio"]
["1","06","02","10","10","","XE2210_100","1.06.02.10.10","CBB6021010","High Level Apps SW Release 2","2008-01-07","2008-05-28","S","C","SL_CP2","Hrs",1034,null,86918.52560408578,null,86918.52560408578,null,1034,null,86918.52560408578,null,86918.52560408578,null,null,86918.52560408578,1,{"$nulls":8},0.25,21729.631401021445,1.15,1.1,5,3,"2H","B. Dalesio"]
["1","06","02","11","","","XE624_0130","1.06.02.11","CBB60211","Preliminary Design Review (PDR)","2007-10-29","2007-10-29","S","C","SL_CP2","Hrs",40,null,3362.418785457864,null,3362.418785457864,null,40,null,3362.418785457864,null,3362.418785457864,null,null,3362.418785457864,1,{"$nulls":8},0.25,840.604696364466,1.15,1.1,5,2,"2H","B. Dalesio"]
["1","06","02","11","","","XE624_0140","1.06.02.11","CBB60211","Laser Controls System Final Design","2007-10-30","2007-11-28","S","C","SL_CP2","Hrs",120,null,10087.256356373591,null,10087.256356373591,null,120,null,10087.256356373591,null,10087.256356373591,null,null,10087.256356373591,1,{"$nulls":8},0.25,2521.814089093398,1.15,1.1,5,2,"2H","B. Dalesio"]
["1","06","02","12","  ","  ",null,null,null,"K-Measuerment/Vacuum Subsystem                              ",{"$nulls":6},320,12200,26341.823121900165,13380.5011824,39722.324304300164,null,320,12200,26341.823121900165,13380.5011824,39722.324304300164,24258.02940519756,null,15464.294899102602,null,0,null,0,null,0,null,0,null,null,9930.581076075041,{"$nulls":6},"Gunter Haller"]
["1","06","02","12","","","XE629_0115","1.06.02.12","CBB60212","Conceptual Design  Review (CDR)","2007-06-27","2007-06-27","S","C","SL_CP2","Hrs",10,null,821.7054705420001,null,821.7054705420001,null,10,null,821.7054705420001,null,821.7054705420001,821.7054705420001,1,{"$nulls":10},0.25,205.42636763550001,1.15,1.1,5,2,"2H","B. Dalesio"]
["1","06","02","12","","","XE629_0170","1.06.02.12","CBB60212","RCV: 1 Timing","2007-11-21","2007-11-21","S","C","SL_MSEG2","$$",null,2900,null,3180.6109368,3180.6109368,null,null,2900,null,3180.6109368,3180.6109368,null,null,3180.6109368,1,{"$nulls":8},0.25,795.1527342,1.15,1.1,2,3,"2H","B. Dalesio"]
["1","06","03","02","05","  ",null,null,null,"Gauges - Vacuum                                             ",{"$nulls":37},"Stefan Moeller"]
["1","06","04","01","","","XE1410020","1.06.04.01","CBA60401","Specification - XES Laser","2007-06-01","2007-07-27","S","C","SL_OE2","Hrs",120,null,13524.120610703998,null,13524.120610703998,null,120,null,13524.120610703998,null,13524.120610703998,13524.120610703998,1,{"$nulls":10},0.25,3381.0301526759995,1.15,1.1,4,2,"2L"]
["1","06","04","01","","","XE1410040","1.06.04.01","CBA60401","Design Review - XES Laser","2007-11-20","2007-12-05","S","C","SL_PHS2","Hrs",32,null,2387.2459487412093,null,2387.2459487412093,null,32,null,2387.2459487412093,null,2387.2459487412093,null,null,2387.2459487412093,1,{"$nulls":8},0.25,596.8114871853023,1.15,1.1,4,2,"2L"]
["1","06","04","01","","","XE1410120","1.06.04.01","CBA60401","Vendor Fab/Ship - XES Laser","2008-02-21","2008-07-11","S","C","SA_MSEQ2","$$",null,385857,null,423193.446289944,423193.446289944,null,null,385857,null,423193.446289944,423193.446289944,null,null,423193.446289944,1,{"$nulls":8},0.25,105798.361572486,1.15,1.1,4,3,"2L"]
["1","06","04","02","  ","  ",null,null,null,"Laser Diagnostics                                           ",{"$nulls":6},3473,47600,417187.1215800644,52205.889859200004,469393.0114392644,null,3473,47600,417187.1215800644,52205.889859200004,469393.0114392644,27808.073482354877,null,331310.56131378305,null,110274.37664312641,null,0,null,0,null,0,null,null,117348.2528598161,{"$nulls":6},"Bill White"]
["1","06","04","02","","","XE1420080","1.06.04.02","CBA60402","AWARD: Energy Sensors - Laser Diagnostics","2008-05-20","2008-05-20","S","C","SL_AWARD","$$",null,9202,null,10861.534505959999,10861.534505959999,null,null,9202,null,10861.534505959999,10861.534505959999,null,null,10861.534505959999,1,{"$nulls":8},0.25,2715.3836264899996,1.15,1.1,4,3,"2L"]
["1","06","04","02","","","XE1420130","1.06.04.02","CBA60402","AWARD: Contract - IR FROG - Laser Diagnostics","2008-05-20","2008-05-20","S","C","SL_AWARD","$$",null,26750,null,31574.228214999996,31574.228214999996,null,null,26750,null,31574.228214999996,31574.228214999996,null,null,31574.228214999996,1,{"$nulls":8},0.25,7893.557053749999,1.15,1.1,4,3,"2L"]
["1","06","04","03","  ","  ",null,null,null,"Laser Optical Transport                                     ",{"$nulls":6},2696,184000,260447.0127922257,201804.280128,462251.29292022577,null,2696,184000,260447.0127922257,201804.280128,462251.29292022577,94422.76804535068,null,367828.52487487503,null,0,null,0,null,0,null,0,null,null,115562.82323005644,{"$nulls":6},"Bill White"]
["1","06","04","03","","","XE1430032","1.06.04.03","CKA60403","Preliminary Design - Laser Optic Transport","2007-09-04","2007-10-08","S","C","SL_ME2","Hrs",240,null,24011.828206198687,null,24011.828206198687,null,240,null,24011.828206198687,null,24011.828206198687,19068.216516687193,0.79,4943.611689511494,0.21,{"$nulls":8},0.25,6002.957051549672,1.15,1.1,4,2,"2L"]
["1","06","04","03","","","XE1430038","1.06.04.03","CKA60403","Design Enclosures for Optical Tables","2007-11-20","2008-01-18","S","C","SL_PHS2","Hrs",120,null,8952.172307779534,null,8952.172307779534,null,120,null,8952.172307779534,null,8952.172307779534,null,null,8952.172307779534,1,{"$nulls":8},0.25,2238.0430769448835,1.15,1.1,4,2,"2L"]
["1","06","04","03","","","XE1430050","1.06.04.03","CKA60403","Prep Bid Pkg Lenses & Mirrors - Laser Optic Tran","2008-01-22","2008-02-04","S","C","SL_PHS2","Hrs",40,null,2984.0574359265115,null,2984.0574359265115,null,40,null,2984.0574359265115,null,2984.0574359265115,null,null,2984.0574359265115,1,{"$nulls":8},0.25,746.0143589816279,1.15,1.1,4,2,"2L"]
["1","06","04","03","","","XE1430170","1.06.04.03","CKA60403","AWARD: Contract Optic Tables (4) - Laser Optic T","2008-03-05","2008-03-05","S","C","SL_AWARD","$$",null,107000,null,126296.91285999998,126296.91285999998,null,null,107000,null,126296.91285999998,126296.91285999998,null,null,126296.91285999998,1,{"$nulls":8},0.25,31574.228214999996,1.15,1.1,4,3,"2L"]
["1","06","04","03","","","XE1430180","1.06.04.03","CKA60403","Vendor Fab/Ship Optic Tables (4) -Laser Optic Tr","2008-03-06","2008-05-29","S","C","SA_MSEQ2","$$",null,100000,null,109676.2392,109676.2392,null,null,100000,null,109676.2392,109676.2392,null,null,109676.2392,1,{"$nulls":8},0.25,27419.0598,1.15,1.1,4,3,"2L"]
["1","06","04","04","","","XE1450045","1.06.04.04","CKA60404","Prepare for Laser Safety Oversight Comm. Review","2007-12-06","2008-04-15","S","C","SL_PHS2","Hrs",40,null,2984.0574359265115,null,2984.0574359265115,null,40,null,2984.0574359265115,null,2984.0574359265115,null,null,2984.0574359265115,1,{"$nulls":8},0.25,746.0143589816279,1.15,1.1,4,2,"2L"]
["1","06","05","  ","  ","  ",null,null,null,"X-Ray Detectors                                             ",{"$nulls":6},3546,0,264805.9359253519,0,264805.9359253519,null,3546,0,264805.9359253519,0,264805.9359253519,57570.324097275625,null,137717.2458797574,null,69518.36594831888,null,0,null,0,null,0,null,null,52961.18718507038,{"$nulls":6},"Stefan Moeller"]
["1","06","05","03","  ","  ",null,null,null,"Beam Intensity                                              ",{"$nulls":37},"Stefan Moeller"]
["1","06","06","01","","","S8X6_FE080","1.06.06.01","CBZ60601","Install FEE components - XE","2008-06-05","2008-08-28",null,"C","SL_MFAT2","Hrs",344,null,30240.501984,null,30240.501984,null,344,null,30240.501984,null,30240.501984,null,null,30240.501984,1,{"$nulls":14},"6A"]
["1","06","06","02","  ","  ",null,null,null,"Near Hall Install                                           ",{"$nulls":6},9704,0,882055.3923597133,0,882055.3923597133,null,9704,0,882055.3923597133,0,882055.3923597133,0,null,820735.4623066558,null,61319.93005305736,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Stefan Moeller"]
["1","06","06","02","03","  ",null,null,null,"Near Hall Install Laser                                     ",{"$nulls":37},"Stefan Moeller"]
["1","06","06","02","08","","S8X7_NH080","1.06.06.02.08","CBZ6060208","Install NEH Beamline components - XE","2008-07-18","2008-08-28",null,"C","SL_MES2","Hrs",8,null,655.1917708865759,null,655.1917708865759,null,8,null,655.1917708865759,null,655.1917708865759,null,null,655.1917708865759,1,{"$nulls":14},"6A"]
["1","06","06","02","08","","S8X7_NH080","1.06.06.02.08","CBZ6060208","Install NEH Beamline components - XE","2008-07-18","2008-08-28",null,"C","SL_ME2","Hrs",960,null,97793.32088264429,null,97793.32088264429,null,960,null,97793.32088264429,null,97793.32088264429,null,null,97793.32088264429,1,{"$nulls":14},"6A"]
["1","06","06","02","08","","S8X7_NH150","1.06.06.02.08","CBZ6060208","Checkout NEH System - XE","2008-11-11","2008-12-10",null,"C","SL_MFAT2","Hrs",40,null,3597.2126399999997,null,3597.2126399999997,null,40,null,3597.2126399999997,null,3597.2126399999997,{"$nulls":4},3597.2126399999997,1,{"$nulls":12},"6A"]
["1","06","06","02","08","","S8Z1_PB070","1.06.06.02.08","CBZ6060208","Install PPS/BCS racks in NEH","2008-06-25","2008-07-09",null,"C","SL_CE2","Hrs",15,null,1729.3969230937737,null,1729.3969230937737,null,15,null,1729.3969230937737,null,1729.3969230937737,null,null,1729.3969230937737,1,{"$nulls":14},"6A"]
["1","06","06","02","08","","S8Z1_PB090","1.06.06.02.08","CBZ6060208","Checkout/verify PPS/BCS through NEH","2008-07-31","2008-08-27",null,"C","SL_CT2","Hrs",164,null,10351.633374819712,null,10351.633374819712,null,164,null,10351.633374819712,null,10351.633374819712,null,null,10351.633374819712,1,{"$nulls":14},"6A"]
["1","06","06","03","","","S8X8_XT080","1.06.06.03","CBZ60603","Install X-Ray tunnel components - XE","2009-02-03","2009-03-02",null,"C","SL_CE2","Hrs",4,null,471.7794070283184,null,471.7794070283184,null,4,null,471.7794070283184,null,471.7794070283184,{"$nulls":4},471.7794070283184,1,{"$nulls":12},"6A"]
["1","06","06","04","01","  ",null,null,null,"Far Hall Install Global Controls                            ",{"$nulls":37},"Stefan Moeller"]
["1","06","06","04","06","  ",null,null,null,"2008 Far Hall Install                                       ",{"$nulls":6},1202,0,110454.20044799622,0,110454.20044799622,null,1202,0,110454.20044799622,0,110454.20044799622,0,null,0,null,89968.37654013952,null,20485.823907856706,null,0,null,0,null,null,0,{"$nulls":6},"Stefan Moeller"]
["1","06","06","04","06","","S8Z1_PB130","1.06.06.04.06","CBZ6060406","Install HPS in FEH","2009-07-01","2009-07-22",null,"C","SL_CP2","Hrs",80,null,6879.507761929967,null,6879.507761929967,null,80,null,6879.507761929967,null,6879.507761929967,{"$nulls":4},6879.507761929967,1,{"$nulls":12},"6A"]
["1","06","06","05","","","S8X5_BD070","1.06.06.05","CBZ60605","Install Dump components - XE","2008-03-26","2008-06-18",null,"C","SL_TMUP2","Hrs",32,null,3001.545638784,null,3001.545638784,null,32,null,3001.545638784,null,3001.545638784,null,null,3001.545638784,1,{"$nulls":14},"6A"]
["1","06","07","01","01","","XE1711010","1.06.07.01","CAA60701","Management of AMO Experiment - Nov08 thru Aug09","2008-11-03","2009-08-31","S","C","SL_PHPU2","Hrs",823,null,105733.66462059726,null,105733.66462059726,null,823,null,105733.66462059726,null,105733.66462059726,{"$nulls":4},105733.66462059726,1,{"$nulls":6},0.2,21146.732924119453,1.1,1.1,5,2,"6A"]
["1","06","07","01","02","","XE1712060","1.06.07.01","CBA60701","Post-System concept review (SCR)","2007-05-01","2007-05-11","S","C","SL_ME2","Hrs",16,null,1593.2440678175997,null,1593.2440678175997,null,16,null,1593.2440678175997,null,1593.2440678175997,1593.2440678175997,1,{"$nulls":10},0.2,318.64881356352,1.1,1.1,5,2,"6A"]
["1","06","07","01","03","","XE1713020","1.06.07.01","CBA60701","Preliminary design - Refocus optics","2007-05-01","2007-06-15","S","C","SL_ME2","Hrs",56,null,5576.354237361599,null,5576.354237361599,null,56,null,5576.354237361599,null,5576.354237361599,5576.354237361599,1,{"$nulls":10},0.35,1951.7239830765595,1.25,1.1,4,2,"6A"]
["1","06","07","01","04","","XE1714030","1.06.07.01","CBA60701","Specify components - Refocus optics","2007-07-17","2007-07-30","S","C","SL_ME2","Hrs",80,null,7966.220339087999,null,7966.220339087999,null,80,null,7966.220339087999,null,7966.220339087999,7966.220339087999,1,{"$nulls":10},0.35,2788.177118680799,1.25,1.1,4,2,"6A"]
["1","06","07","02","  ","  ",null,null,null,"AP X1 High Field Physics Exp.                               ",{"$nulls":6},2080,1248661,183211.4159023418,1386910.431774792,1570121.8476771333,null,2080,1248661,183211.4159023418,1386910.431774792,1570121.8476771333,5814.481456882085,null,673057.9014235553,null,891249.4647966963,null,0,null,0,null,0,null,null,447481.3046761589,{"$nulls":6},"Stefan Moeller"]
["1","06","07","02","","","XE1720500","1.06.07.02","CKA60702","Assemble - HF Physics Exp CD4a","2008-09-16","2008-11-10","S","C","SL_ME2","Hrs",100,null,10357.20052943598,null,10357.20052943598,null,100,null,10357.20052943598,null,10357.20052943598,null,null,2824.69105348254,0.27,7532.50947595344,0.73,{"$nulls":6},0.25,2589.300132358995,1.15,1.1,4,3,"6A"]
["1","06","07","02","01","","XE1721060","1.06.07.02","CKA60702","Assemble - X-Ray Fluor. Spectrometer","2009-08-13","2009-08-26","S","C","SL_MFAT2","Hrs",120,null,10791.63792,null,10791.63792,null,120,null,10791.63792,null,10791.63792,{"$nulls":4},10791.63792,1,{"$nulls":6},0.25,2697.90948,1.15,1.1,4,3,"6A"]
["1","06","07","02","01","","XE1721080","1.06.07.02","CKA60702","Testing - X-Ray Fluor. Spectrometer","2009-09-03","2009-09-23","S","C","SL_MFAT2","Hrs",60,null,5395.81896,null,5395.81896,null,60,null,5395.81896,null,5395.81896,{"$nulls":4},5395.81896,1,{"$nulls":6},0.25,1348.95474,1.15,1.1,4,3,"6A"]
["1","06","07","02","02","","XE1722510","1.06.07.02","CKA60702","Readiness/Safety Review - TOF Detectors","2008-09-16","2008-09-22","S","C","SL_ME2","Hrs",40,null,4074.7217034435116,null,4074.7217034435116,null,40,null,4074.7217034435116,null,4074.7217034435116,null,null,4074.7217034435116,1,{"$nulls":8},0.2,814.9443406887024,1.1,1.1,5,3,"6A"]
["1","06","07","02","03","  ",null,null,null,"Sample Source                                               ",{"$nulls":6},320,129246,28336.79558264142,141752.152116432,170088.94769907344,null,320,129246,28336.79558264142,141752.152116432,170088.94769907344,1453.6203642205212,null,163606.30935427677,null,5029.017980576132,null,0,null,0,null,0,null,null,43693.54056887679,{"$nulls":6},"Stefan Moeller"]
["1","06","07","02","03","","XE1723040","1.06.07.02","CKA60702","Fab/Deliver - X1 Sample Source","2008-01-18","2008-05-12","S","C","SA_MSEQ2","$$",null,129246,null,141752.152116432,141752.152116432,null,null,129246,null,141752.152116432,141752.152116432,null,null,141752.152116432,1,{"$nulls":8},0.26,36855.55955027232,1.16,1.1,3,3,"6A"]
["1","06","07","02","05","  ",null,null,null,"Other X1 Items                                              ",{"$nulls":6},40,63200,4041.7736956375466,69315.3831744,73357.15687003755,null,40,63200,4041.7736956375466,69315.3831744,73357.15687003755,1453.6203642205212,null,71903.53650581703,null,0,null,0,null,0,null,0,null,null,26368.158736257144,{"$nulls":6},"Stefan Moeller"]
["1","06","07","03","","","XE1730040","1.06.07.03","CKA60703","Fab/Deliver - Optics Assembly","2008-10-02","2009-08-12","S","C","SA_MSEQ2","$$",null,65000,null,72929.20388,72929.20388,null,null,65000,null,72929.20388,72929.20388,{"$nulls":4},72929.20388,1,{"$nulls":6},0.45,32818.141746,1.35,1.1,4,3,"6A"]
["1","06","07","03","","","XE1730080","1.06.07.03","CKA60703","AWARD: Optics Chamber","2008-01-17","2008-01-17","S","C","SL_AWARD","$$",null,29833,null,35213.231788339996,35213.231788339996,null,null,29833,null,35213.231788339996,35213.231788339996,null,null,35213.231788339996,1,{"$nulls":8},0.2,7042.646357668,1.1,1.1,4,3,"6A"]
["1","06","07","03","","","XE1730190","1.06.07.03","CKA60703","Fab/Deliver - RO Stand","2008-10-02","2009-01-27","S","C","SA_MSEQ2","$$",null,100000,null,112198.77520000002,112198.77520000002,null,null,100000,null,112198.77520000002,112198.77520000002,{"$nulls":4},112198.77520000002,1,{"$nulls":6},0.35,39269.57132,1.25,1.1,4,3,"6A"]
["1","06","07","04","  ","  ",null,null,null,"AP Diagnostics                                              ",{"$nulls":6},1122,282605,94097.69079359765,310455.04299116,404552.7337847576,null,1122,282605,94097.69079359765,310455.04299116,404552.7337847576,1453.6203642205212,null,339496.7689880675,null,63602.34443246953,null,0,null,0,null,0,null,null,126017.94284571143,{"$nulls":6},"Stefan Moeller"]
["1","06","07","04","","","XE1741010","1.06.07.04","CKB60704","Bid/Evaluate/RFP - CD4b Diagnostic Equipment","2008-10-01","2009-01-26","S","C","SL_ME2","Hrs",40,null,4168.439652398472,null,4168.439652398472,null,40,null,4168.439652398472,null,4168.439652398472,{"$nulls":4},4168.439652398472,1,{"$nulls":6},0.35,1458.9538783394653,1.25,1.1,4,3,"6A"]
["1","06","08","  ","  ","  ",null,null,null,"Crystals and Gratings                                       ",{"$nulls":6},44,20000,5514.447385298807,21935.24784,27449.695225298805,null,44,20000,5514.447385298807,21935.24784,27449.695225298805,491.04607170959986,null,26958.649153589206,null,0,null,0,null,0,null,0,null,null,6862.423806324701,{"$nulls":6},"Stefan Moeller"]
["1","06","08","01","","","XE1810010","1.06.08.01","CBA60801","Prepare PRD - K Meas.","2007-05-01","2007-05-11","S","C","SL_PHPU2","Hrs",4,null,491.04607170959986,null,491.04607170959986,null,4,null,491.04607170959986,null,491.04607170959986,491.04607170959986,1,{"$nulls":10},0.25,122.76151792739996,1.15,1.1,4,2,"6A"]
["1","06","09","01","","","XE1920010","1.06.09.01","CBA60901","Prepare PRD - PPS Beam Stop Hardware","2007-05-01","2007-05-31","S","C","SL_PHS2","Hrs",40,null,2916.967190544,null,2916.967190544,null,40,null,2916.967190544,null,2916.967190544,2916.967190544,1,{"$nulls":10},0.25,729.241797636,1.15,1.1,4,2,"6A"]
["1","06","09","01","","","XE1920120","1.06.09.01","CBA60901","AWARD: - PPS Beam Stop Hardware","2007-10-01","2007-10-01","S","C","SL_AWARD","$$",null,321000,null,378890.73857999995,378890.73857999995,null,null,321000,null,378890.73857999995,378890.73857999995,null,null,378890.73857999995,1,{"$nulls":8},0.25,94722.68464499999,1.15,1.1,4,3,"6A"]
["1","06","09","01","","","XE1920180","1.06.09.01","CBA60901","Assemble FEE - PPS Beam Stop Hardware (2)","2008-02-12","2008-06-04","S","C","SL_MFMS2","Hrs",160,null,18001.63835712,null,18001.63835712,null,160,null,18001.63835712,null,18001.63835712,null,null,18001.63835712,1,{"$nulls":8},0.25,4500.40958928,1.15,1.1,4,2,"6A"]
["1","06","09","01","","","XE1920200","1.06.09.01","CBA60901","Assemble Tunnel - PPS Beam Stop Hardware","2008-05-07","2008-06-18","S","C","SL_MFAT2","Hrs",160,null,14065.34976,null,14065.34976,null,160,null,14065.34976,null,14065.34976,null,null,14065.34976,1,{"$nulls":8},0.25,3516.33744,1.15,1.1,4,2,"6A"]
["1","06","09","01","","","XE1920220","1.06.09.01","CBA60901","Assemble EDE - PPS Beam Stop Hardware","2008-02-12","2008-03-25","S","C","SL_MFAT2","Hrs",160,null,14065.34976,null,14065.34976,null,160,null,14065.34976,null,14065.34976,null,null,14065.34976,1,{"$nulls":8},0.25,3516.33744,1.15,1.1,4,4,"6A"]
["1","06","09","02","","","XE1922040","1.06.09.02","CBA60902","Conceptual Design Review - PPS Shielding & Supp","2007-09-20","2007-10-03","S","C","SL_MDD2","Hrs",80,null,6702.728717927209,null,6702.728717927209,null,80,null,6702.728717927209,null,6702.728717927209,5671.539684399946,0.85,1031.189033527263,0.15,{"$nulls":8},0.25,1675.6821794818022,1.15,1.1,4,3,"6A"]
["1","06","09","02","","","XE1922080","1.06.09.02","CBA60902","Prepare for Safety/RP Review - Shielding & Suppt","2007-11-15","2007-12-14","S","C","SL_ME2","Hrs",80,null,8149.443406887023,null,8149.443406887023,null,80,null,8149.443406887023,null,8149.443406887023,null,null,8149.443406887023,1,{"$nulls":8},0.25,2037.3608517217558,1.15,1.1,4,3,"6A"]
["1","06","09","02","","","XE1922100","1.06.09.02","CBA60902","Prep Bid Pkg - PPS Shielding & Supports","2008-01-16","2008-02-13","S","C","SL_ME2","Hrs",80,null,8149.443406887023,null,8149.443406887023,null,80,null,8149.443406887023,null,8149.443406887023,null,null,8149.443406887023,1,{"$nulls":8},0.25,2037.3608517217558,1.15,1.1,4,2,"6A"]
["1","06","09","02","","","XE1922160","1.06.09.02","CBA60902","Fab/Assemble FEE - PPS Shielding & Supports","2008-04-21","2008-04-25","S","C","SL_MFMS2","Hrs",40,null,4500.40958928,null,4500.40958928,null,40,null,4500.40958928,null,4500.40958928,null,null,4500.40958928,1,{"$nulls":8},0.25,1125.10239732,1.15,1.1,4,2,"6A"]
["1","06","09","02","","","XE1922190","1.06.09.02","CBA60902","Fab/Assemble FH - PPS Shielding & Supports","2008-05-12","2008-05-16","S","C","SL_MFMS2","Hrs",40,null,4500.40958928,null,4500.40958928,null,40,null,4500.40958928,null,4500.40958928,null,null,4500.40958928,1,{"$nulls":8},0.25,1125.10239732,1.15,1.1,4,2,"6A"]
["1","06","09","03","  ","  ",null,null,null,"NEH Hutch Doors                                             ",{"$nulls":6},400,36000,36891.95203971895,39483.446112,76375.39815171895,null,400,36000,36891.95203971895,39483.446112,76375.39815171895,34335.18324066873,null,42040.214911050214,null,0,null,0,null,0,null,0,null,null,19093.84953792974,{"$nulls":6},"Stefan Moeller"]
["1","06","09","03","","","XE19300110","1.06.09.03","CBA60903","Final Design Review - NEH Hutch Doors","2007-07-30","2007-08-10","S","C","SL_MDD2","Hrs",40,null,3339.5474985839996,null,3339.5474985839996,null,40,null,3339.5474985839996,null,3339.5474985839996,3339.5474985839996,1,{"$nulls":10},0.25,834.8868746459999,1.15,1.1,4,2,"6A"]
["1","06","09","03","","","XE19300140","1.06.09.03","CBA60903","AWARD: - NEH Hutch Doors (3 x 44\")","2007-10-09","2007-10-09","S","C","SL_AWARD","$$",null,38520,null,45466.8886296,45466.8886296,null,null,38520,null,45466.8886296,45466.8886296,null,null,45466.8886296,1,{"$nulls":8},0.25,11366.7221574,1.15,1.1,4,3,"6A"]
["1","09","01","01","","","CFMGT_4010","1.09.01.01","9242338","Management - FY07","2007-05-01","2007-09-28",null,"C","SL_SEEM2","Hrs",742,null,78561.24599751117,null,78561.24599751117,null,742,null,78561.24599751117,null,78561.24599751117,78561.24599751117,1,{"$nulls":10},0.2,15712.249199502236,1.1,1.1,3,1,"9A"]
["1","09","01","01","","","CFMGT_5040","1.09.01.01","CK90101","CF Management Support - CD4b","2009-08-03","2010-05-31",null,"X","SL_SEEM2","Hrs",1498,null,169053.83754240844,null,169053.83754240844,null,1498,null,169053.83754240844,null,169053.83754240844,{"$nulls":4},33136.7987209372,0.2,135917.03882147124,0.8,{"$nulls":4},0.15,25358.075631361266,1,1.15,null,1,"9A"]
["1","09","01","02","","","CFENG_1200","1.09.01.02","9242376","CF Engineering Support - FY07","2007-05-01","2007-09-28",null,"C","SL_SEEM2","Hrs",2226,null,235683.73799253354,null,235683.73799253354,null,2226,null,235683.73799253354,null,235683.73799253354,235683.73799253354,1,{"$nulls":16},"9A"]
["1","09","01","02","","","CFENG_1245","1.09.01.02","CK90102","Start: FEH Hutches - A&E Design","2008-07-02","2008-12-22",null,"C","SA_MSSC1","$$",null,212000,null,236761.60212107835,null,null,null,212000,null,236761.60212107835,236761.60212107835,null,null,124539.33984403544,0.53,112222.26227704292,0.47,{"$nulls":6},0.6,142056.961272647,1.5,1.1,null,null,"9A"]
["1","09","01","03","","","CFMGT_1320","1.09.01.03","K8819012","Phase 2 Construction Management - FY08","2007-10-02","2008-05-30",null,"C","SL_MSSF2","$$",null,1276183,null,1337439.784,1337439.784,null,null,1276183,null,1337439.784,1337439.784,null,null,1337439.784,1,{"$nulls":8},0.1,133743.9784,1,1.1,7,1,"9A"]
["1","09","01","04","04","  ",null,null,null,"Mechanical Design T2 Linac Facilities                       ",{"$nulls":37},"David Saenz"]
["1","09","01","05","  ","  ",null,null,null,"Conventional Experiment Facility (CEF)                      ",{"$nulls":37},"David Saenz"]
["1","09","01","05","03","  ",null,null,null,"CEF Engineering Title 2 - RSY through CLOC                  ",{"$nulls":37},"David Saenz"]
["1","09","02","03","01","  ",null,null,null,"Title 1 Design (Sector 20)                                  ",{"$nulls":37},"David Saenz"]
["1","09","03","01","02","  ",null,null,null,"S20 - Site Construction                                     ",{"$nulls":37},"David Saenz"]
["1","09","03","01","05","  ",null,null,null,"S20 - Metals                                                ",{"$nulls":37},"David Saenz"]
["1","09","03","01","15","  ",null,null,null,"S20 - Mechanical                                            ",{"$nulls":37},"David Saenz"]
["1","09","03","02","06","  ",null,null,null,"MMF - Woods & Plastics                                      ",{"$nulls":37},"David Saenz"]
["1","09","03","02","09","  ",null,null,null,"MMF - Finishes                                              ",{"$nulls":37},"David Saenz"]
["1","09","03","03","  ","  ",null,null,null,"BTH West                                                    ",{"$nulls":6},600,310000,37543.74039503999,324880,68983.74039503999,null,600,310000,37543.74039503999,324880,362423.74039504,136200.29211917793,null,226223.4482758621,null,0,null,0,null,0,null,0,null,null,128811.87019752,{"$nulls":6},"David Saenz"]
["1","09","03","03","15","  ",null,null,null,"BTH West - Mechanical                                       ",{"$nulls":6},0,100000,0,104800,0,null,0,100000,0,104800,104800,35234.48275862069,null,69565.51724137932,null,0,null,0,null,0,null,0,null,null,0,{"$nulls":6},"David Saenz"]
["1","09","03","03","20","","CF0031050","1.09.03.03.20","9242940","BTH West - Commissioning & Project Close Out","2007-11-21","2007-12-20",null,"C","SL_MSSF2","$$",null,30000,null,31440,31440,null,null,30000,null,31440,31440,null,null,31440,1,{"$nulls":8},0.5,15720,1.3,1.2,3,3,"9A"]
["1","09","03","04","15","  ",null,null,null,"LN - Mechanical                                             ",{"$nulls":37},"David Saenz"]
["1","09","03","04","16","","CFLNF_3180","1.09.03.04.16","9242761","AWARD: Linac Facility Upgrades - Electr Constr","2007-05-01","2007-05-01",null,"C","SL_AWARD","$$",null,252000,null,289909.34280000004,289909.34280000004,null,null,252000,null,289909.34280000004,289909.34280000004,289909.34280000004,1,{"$nulls":10},0.3,86972.80284,1.1,1.2,3,3,"9A"]
["1","09","03","05","  ","  ",null,null,null,"Research Yard Modifications                                 ",{"$nulls":6},900,632075,80962.1409893513,657035,93037.1409893513,null,900,632075,80962.1409893513,657035,737997.1409893513,382725.67772569833,null,355271.463263653,null,0,null,0,null,0,null,0,null,null,145184.42819787026,{"$nulls":6},"David Saenz"]
["1","09","03","05","02","","GCCR_0010","1.09.03.05.02","8819020","Continue Work - U/G Mech CTW Encasement","2007-05-01","2007-05-07",6,"C","SL_GCFX1","$$",null,7075,null,7075,7075,null,null,7075,null,7075,7075,7075,1,{"$nulls":14},"SI","P2","9A"]
["1","09","03","05","02","01",null,null,null,"Site Construction - CEF                                     ",{"$nulls":37},"David Saenz"]
["1","09","03","05","05","01",null,null,null,"HVAC CEF                                                    ",{"$nulls":37},"David Saenz"]
["1","09","03","05","06","01",null,null,null,"Special System - Fire Protection CEF                        ",{"$nulls":37},"David Saenz"]
["1","09","03","05","20","","CF05033125","1.09.03.05.20","9242789","Start: Third Party Testing - Beam Path - 2007","2007-05-01","2008-02-29",null,"C","SL_MSPY2","$$",null,100000,null,100000,null,null,null,100000,null,100000,100000,50328.94736842105,0.5,49671.05263157895,0.5,{"$nulls":8},0.2,20000,1.1,1.1,2,3,"9A"]
["1","09","03","06","01","","GCEQ1060","1.09.03.06.01","9242811","Equipment Shipped Delivered (15%)","2008-02-20","2008-04-01",8,"C","SL_GCFX1","$$",null,53584,null,53584,53584,null,null,53584,null,53584,53584,null,null,53584,1,{"$nulls":8},0.15,8037.599999999999,1,1.15,"EQ","P2","9A"]
["1","09","03","06","07","  ",null,null,null,"Interior                                                    ",{"$nulls":37},"David Saenz"]
["1","09","03","07","  ","  ",null,null,null,"SITEWORK                                                    ",{"$nulls":6},0,6173346,0,6173346,6071549,null,0,6173346,0,6173346,6173346,2615547.18785165,null,3557798.81214835,null,0,null,0,null,0,null,0,null,null,899391.9,{"$nulls":6},"David Saenz"]
["1","09","03","07","01","","GCMO1178","1.09.03.07.01","9242814","General Requirements Work - Nov 07","2007-10-30","2007-11-29",10,"C","SL_GCFX1","$$",null,81875,null,81875,81875,null,null,81875,null,81875,81875,null,null,81875,1,{"$nulls":8},0.15,12281.25,1,1.15,"SI","P2","9A"]
["1","09","03","07","01","","GCMO1184","1.09.03.07.01","9242814","General Requirements Work - Dec 07","2007-11-30","2007-12-31",10,"C","SL_GCFX1","$$",null,81875,null,81875,81875,null,null,81875,null,81875,81875,null,null,81875,1,{"$nulls":8},0.15,12281.25,1,1.15,"SI","P2","9A"]
["1","09","03","07","02","","GCAC1576","1.09.03.07.02","9242815","Access T Water Lines","2008-05-02","2008-05-06",4,"C","SL_GCFX1","$$",null,20000,null,20000,20000,null,null,20000,null,20000,20000,null,null,20000,1,{"$nulls":8},0.15,3000,1,1.15,"AC","P2","9A"]
["1","09","03","07","02","","GCBT90620","1.09.03.07.02","9242815","BTH East Excavation","2007-08-20","2007-08-23",2,"C","SL_GCFX1","$$",null,80000,null,80000,80000,null,null,80000,null,80000,80000,80000,1,{"$nulls":10},0.15,12000,1,1.15,"H6","P2","9A"]
["1","09","03","07","02","","GCCR_0080","1.09.03.07.02","9242815","RSY Domestic Waterlines","2007-05-01","2007-05-07",4,"C","SL_GCFX1","$$",null,3410,null,3410,3410,null,null,3410,null,3410,3410,3410,1,{"$nulls":10},0.15,511.5,1,1.15,"SI","P2","9A"]
["1","09","03","07","02","","GCCR_0210","1.09.03.07.02","9242815","Bldg Pad Certifications","2007-05-01","2008-01-29",1,"C","SL_GCFX1","$$",null,3802,null,3802,null,null,null,3802,null,3802,3802,2130.7912087912086,0.56,1671.2087912087911,0.44,{"$nulls":8},0.15,570.3,1,1.15,"SI","P2","9A"]
["1","09","03","07","02","","GCCR_0240","1.09.03.07.02","9242815","Tunnel Excavation Checks","2007-05-01","2007-11-21",1,"C","SL_GCFX1","$$",null,7920,null,7920,null,null,null,7920,null,7920,7920,5940,0.75,1980,0.25,{"$nulls":8},0.15,1188,1,1.15,"SI","P2","9A"]
["1","09","03","07","02","","GCHM5040","1.09.03.07.02","9242815","P16 - Site Concrete (Hammock)","2008-01-11","2008-01-25",null,"C","SL_GCFX1","$$",null,162955,null,162955,162955,null,null,162955,null,162955,162955,null,null,162955,1,{"$nulls":8},0.15,24443.25,1,1.15,"SI","P2","9A"]
["1","09","03","07","02","","GCST1114","1.09.03.07.02","9242815","Place Monument Survey-Control @ Tunnel Acc Pts","2007-05-01","2007-11-06",1,"C","SL_GCFX1","$$",null,3168,null,3168,null,null,null,3168,null,3168,3168,2564.5714285714284,0.81,603.4285714285714,0.19,{"$nulls":8},0.15,475.2,1,1.15,"SI","P2","9A"]
["1","09","03","07","02","","GCST1148","1.09.03.07.02","9242815","Site Cleanup","2008-02-11","2008-02-25",2,"C","SL_GCFX1","$$",null,50000,null,50000,50000,null,null,50000,null,50000,50000,null,null,50000,1,{"$nulls":8},0.15,7500,1,1.15,"SI","P2","9A"]
["1","09","03","07","02","","GCST1192","1.09.03.07.02","9242815","NEH/CUP Water Lines","2008-01-09","2008-01-22",4,"C","SL_GCFX1","$$",null,149400,null,149400,149400,null,null,149400,null,149400,149400,null,null,149400,1,{"$nulls":8},0.15,22410,1,1.15,"SI","P2","9A"]
["1","09","03","07","02","","GCST1214","1.09.03.07.02","9242815","Heavy-Duty & Light-Duty Trench Drains","2007-12-24","2008-01-18",4,"C","SL_GCFX1","$$",null,115000,null,115000,115000,null,null,115000,null,115000,115000,null,null,115000,1,{"$nulls":8},0.15,17250,1,1.15,"SI","P2","9A"]
["1","09","03","07","06","  ",null,null,null,"Special System - Fire Protection                            ",{"$nulls":37},"David Saenz"]
["1","09","03","07","17","  ",null,null,null,"SW - Others (include Div 4, and 6 through 14)               ",{"$nulls":37},"David Saenz"]
["1","09","03","08","03","","GCBT2320","1.09.03.08.03","9242823","BTH HH Pour Deck Pour #2","2007-05-24","2007-05-24",5,"C","SL_GCFX1","$$",null,90722,null,90722,90722,null,null,90722,null,90722,90722,90722,1,{"$nulls":10},0.15,13608.3,1,1.15,"Y2","P2","9A"]
["1","09","03","08","03","","GCBT2780","1.09.03.08.03","9242823","BTH HH Pour Mat Pour #3","2007-05-08","2007-05-08",5,"C","SL_GCFX1","$$",null,89513,null,89513,89513,null,null,89513,null,89513,89513,89513,1,{"$nulls":10},0.15,13426.949999999999,1,1.15,"Y3","P2","9A"]
["1","09","03","08","03","","GCBT3800","1.09.03.08.03","9242823","BTH Pour Walls Pour #1","2007-06-14","2007-06-14",5,"C","SL_GCFX1","$$",null,81936,null,81936,81936,null,null,81936,null,81936,81936,81936,1,{"$nulls":10},0.15,12290.4,1,1.15,"H1","P2","9A"]
["1","09","03","08","03","","GCBT90040","1.09.03.08.03","9242823","BTH HH Form Walls Pour #2","2007-05-01","2007-05-11",5,"C","SL_GCFX1","$$",null,93609,null,93609,93609,null,null,93609,null,93609,93609,93609,1,{"$nulls":10},0.15,14041.35,1,1.15,"Y2","P2","9A"]
["1","09","03","08","03","","GCBT90360","1.09.03.08.03","9242823","BTH Form Walls Pour #1","2007-05-30","2007-06-13",5,"C","SL_GCFX1","$$",null,93609,null,93609,93609,null,null,93609,null,93609,93609,93609,1,{"$nulls":10},0.15,14041.35,1,1.15,"H1","P2","9A"]
["1","09","03","08","03","","GCBT90580","1.09.03.08.03","9242823","BTH Rebar Deck Pour #1","2007-07-10","2007-07-16",5,"C","SL_GCFX1","$$",null,39887,null,39887,39887,null,null,39887,null,39887,39887,39887,1,{"$nulls":10},0.15,5983.05,1,1.15,"H1","P2","9A"]
["1","09","03","08","03","","GCBT9100","1.09.03.08.03","9242823","BTH Pour Mat Pour #3","2007-05-17","2007-05-17",5,"C","SL_GCFX1","$$",null,89513,null,89513,89513,null,null,89513,null,89513,89513,89513,1,{"$nulls":10},0.15,13426.949999999999,1,1.15,"H3","P2","9A"]
["1","09","03","08","03","","GCBT9180","1.09.03.08.03","9242823","BTH Pour Mat Pour #4","2007-05-29","2007-05-29",5,"C","SL_GCFX1","$$",null,89513,null,89513,89513,null,null,89513,null,89513,89513,89513,1,{"$nulls":10},0.15,13426.949999999999,1,1.15,"H4","P2","9A"]
["1","09","03","08","03","","GCBT9260","1.09.03.08.03","9242823","BTH Form Mat Pour #5","2007-05-29","2007-06-05",5,"C","SL_GCFX1","$$",null,33252,null,33252,33252,null,null,33252,null,33252,33252,33252,1,{"$nulls":10},0.15,4987.8,1,1.15,"H5","P2","9A"]
["1","09","03","08","03","","GCBT9290","1.09.03.08.03","9242823","BTH Form Walls Pour #5","2007-07-25","2007-08-07",5,"C","SL_GCFX1","$$",null,93609,null,93609,93609,null,null,93609,null,93609,93609,93609,1,{"$nulls":10},0.15,14041.35,1,1.15,"H5","P2","9A"]
["1","09","03","08","03","","GCBT9390","1.09.03.08.03","9242823","BTH Form Walls Pour #6","2007-09-13","2007-09-28",5,"C","SL_GCFX1","$$",null,93609,null,93609,93609,null,null,93609,null,93609,93609,93609,1,{"$nulls":10},0.15,14041.35,1,1.15,"H6","P2","9A"]
["1","09","03","08","03","","GCBT9400","1.09.03.08.03","9242823","BTH Rebar Walls Pour #6","2007-09-13","2007-09-25",5,"C","SL_GCFX1","$$",null,42909,null,42909,42909,null,null,42909,null,42909,42909,42909,1,{"$nulls":10},0.15,6436.349999999999,1,1.15,"H6","P2","9A"]
["1","09","03","08","03","","GCCR_0300","1.09.03.08.03","9242823","BTH Form Mat Pour #2","2007-05-01","2007-05-07",5,"C","SL_GCFX1","$$",null,3325,null,3325,3325,null,null,3325,null,3325,3325,3325,1,{"$nulls":10},0.15,498.75,1,1.15,"H2","P2","9A"]
["1","09","03","08","05","","GCNB2994","1.09.03.08.05","9242824","HH End Plug Panel Achored Bars - Kwan Wo","2007-07-19","2007-07-25",12,"C","SL_GCFX1","$$",null,10000,null,10000,10000,null,null,10000,null,10000,10000,10000,1,{"$nulls":10},0.15,1500,1,1.15,"Y1","P2","9A"]
["1","09","03","08","09","  ",null,null,null,"Tunneling                                                   ",{"$nulls":37},"David Saenz"]
["1","09","03","08","15","","GCBT6042","1.09.03.08.15","9242825","BTH HVAC Insulation","2007-12-14","2007-12-28",6,"C","SL_GCFX1","$$",null,22355,null,22355,22355,null,null,22355,null,22355,22355,null,null,22355,1,{"$nulls":8},0.15,3353.25,1,1.15,"H7","P2","9A"]
["1","09","03","08","16","","GCBT6002","1.09.03.08.16","9242826","BTH O/H Electrical R/I","2007-10-01","2007-12-04",7,"C","SL_GCFX1","$$",null,532603,null,532603,532603,null,null,532603,null,532603,532603,null,null,532603,1,{"$nulls":8},0.15,79890.45,1,1.15,"H7","P2","9A"]
["1","09","03","08","16","","GCBT6038","1.09.03.08.16","9242826","BTH Electrical Trim","2007-12-05","2007-12-17",7,"C","SL_GCFX1","$$",null,9151,null,9151,9151,null,null,9151,null,9151,9151,null,null,9151,1,{"$nulls":8},0.15,1372.6499999999999,1,1.15,"H7","P2","9A"]
["1","09","03","09","  ","  ",null,null,null,"Front End Enclosure (FEE)                                   ",{"$nulls":6},0,2038195,0,2038195,1744353,null,0,2038195,0,2038195,2038195,1841937.2211640212,null,196257.77883597882,null,0,null,0,null,0,null,0,null,null,305729.25,{"$nulls":6},"David Saenz"]
["1","09","03","09","01","  ",null,null,null,"FEE - Site Preparation/General Requirements                 ",{"$nulls":37},"David Saenz"]
["1","09","03","09","03","","GCFE7200","1.09.03.09.03","9242831","FEE Rebar Deck Pour #2","2007-08-14","2007-08-20",5,"C","SL_GCFX1","$$",null,26540,null,26540,26540,null,null,26540,null,26540,26540,26540,1,{"$nulls":10},0.15,3981,1,1.15,"F2","P2","9A"]
["1","09","03","09","03","","GCFE7410","1.09.03.09.03","9242831","FEE Rebar SOG Pour #2","2007-06-05","2007-06-12",5,"C","SL_GCFX1","$$",null,68050,null,68050,68050,null,null,68050,null,68050,68050,68050,1,{"$nulls":10},0.15,10207.5,1,1.15,"F2","P2","9A"]
["1","09","03","09","03","","GCFE7510","1.09.03.09.03","9242831","FEE Pour Walls Pour #2","2007-07-02","2007-07-02",5,"C","SL_GCFX1","$$",null,73200,null,73200,73200,null,null,73200,null,73200,73200,73200,1,{"$nulls":10},0.15,10980,1,1.15,"F2","P2","9A"]
["1","09","03","09","09","  ",null,null,null,"Tunneling                                                   ",{"$nulls":37},"David Saenz"]
["1","09","03","09","15","","GCFE7334","1.09.03.09.15","9242833","FEE HVAC Controls","2007-10-25","2007-11-07",6,"C","SL_GCFX1","$$",null,34520,null,34520,34520,null,null,34520,null,34520,34520,null,null,34520,1,{"$nulls":8},0.15,5178,1,1.15,"FN","P2","9A"]
["1","09","03","09","16","  ",null,null,null,"FEE - Electrical                                            ",{"$nulls":6},0,292334,0,292334,160577,null,0,292334,0,292334,292334,213715.85714285716,null,78618.14285714286,null,0,null,0,null,0,null,0,null,null,43850.1,{"$nulls":6},"David Saenz"]
["1","09","03","09","17","  ",null,null,null,"FEE - Others (include Div 4, and 6 through 14)              ",{"$nulls":6},0,188202,0,188202,188202,null,0,188202,0,188202,188202,174806,null,13396,null,0,null,0,null,0,null,0,null,null,28230.3,{"$nulls":6},"David Saenz"]
["1","09","03","09","17","","GCFE7330","1.09.03.09.17","9242835","FEE Devices / Doors / Fixtures","2007-11-16","2007-12-07",17,"C","SL_GCFX1","$$",null,10373,null,10373,10373,null,null,10373,null,10373,10373,null,null,10373,1,{"$nulls":8},0.15,1555.95,1,1.15,"FN","P2","9A"]
["1","09","03","10","02","  ",null,null,null,"EBD - Site Construction                                     ",{"$nulls":37},"David Saenz"]
["1","09","03","10","03","","GCBD1140","1.09.03.10.03","9242839","BD Pour Pit Walls Pour #1","2007-07-19","2007-07-19",5,"C","SL_GCFX1","$$",null,13200,null,13200,13200,null,null,13200,null,13200,13200,13200,1,{"$nulls":10},0.15,1980,1,1.15,"D1","P2","9A"]
["1","09","03","10","03","","GCBD1200","1.09.03.10.03","9242839","BD Rebar SOG Pour #2","2007-08-23","2007-08-30",5,"C","SL_GCFX1","$$",null,64900,null,64900,64900,null,null,64900,null,64900,64900,64900,1,{"$nulls":10},0.15,9735,1,1.15,"D2","P2","9A"]
["1","09","03","10","03","","GCBD1420","1.09.03.10.03","9242839","BD Form SOG Pour #1","2007-07-23","2007-08-01",5,"C","SL_GCFX1","$$",null,58500,null,58500,58500,null,null,58500,null,58500,58500,58500,1,{"$nulls":10},0.15,8775,1,1.15,"D1","P2","9A"]
["1","09","03","10","03","","GCBD1620","1.09.03.10.03","9242839","BD Pour Deck Pour #1","2007-11-07","2007-11-07",5,"C","SL_GCFX1","$$",null,40050,null,40050,40050,null,null,40050,null,40050,40050,null,null,40050,1,{"$nulls":8},0.15,6007.5,1,1.15,"D1","P2","9A"]
["1","09","03","10","05","  ",null,null,null,"EBD - Metals                                                ",{"$nulls":6},0,206591,0,206591,206591,null,0,206591,0,206591,206591,0,null,206591,null,0,null,0,null,0,null,0,null,null,30988.65,{"$nulls":6},"David Saenz"]
["1","09","03","10","15","","GCBD1302","1.09.03.10.15","9242841","BD HVAC Rough-in","2007-11-26","2007-12-21",6,"C","SL_GCFX1","$$",null,109846,null,109846,109846,null,null,109846,null,109846,109846,null,null,109846,1,{"$nulls":8},0.15,16476.899999999998,1,1.15,"BD","P2","9A"]
["1","09","03","10","15","","GCBD1306","1.09.03.10.15","9242841","BD HVAC Trim","2008-01-02","2008-01-15",6,"C","SL_GCFX1","$$",null,8785,null,8785,8785,null,null,8785,null,8785,8785,null,null,8785,1,{"$nulls":8},0.15,1317.75,1,1.15,"BD","P2","9A"]
["1","09","03","10","16","","GCBD1328","1.09.03.10.16","9242842","BD Electrical Grounding","2007-07-09","2007-08-03",7,"C","SL_GCFX1","$$",null,8623,null,8623,8623,null,null,8623,null,8623,8623,8623,1,{"$nulls":10},0.15,1293.45,1,1.15,"D1","P2","9A"]
["1","09","03","10","17","","GCBD1720","1.09.03.10.17","9242843","EBD Epoxy Flooring","2007-12-01","2007-12-09",22,"C","SL_GCFX1","$$",null,1576,null,1576,1576,null,null,1576,null,1576,1576,null,null,1576,1,{"$nulls":8},0.15,236.39999999999998,1,1.15,"BD","P2","9A"]
["1","09","03","10","20","  ",null,null,null,"EBD - Project Close Out                                     ",{"$nulls":37},"David Saenz"]
["1","09","03","11","01","","GCIN1404","1.09.03.11.01","9242845","Allowances #1- The Conco Companies","2007-05-01","2008-04-23",5,"C","SL_GCFX1","$$",null,50000,null,50000,null,null,null,50000,null,50000,50000,21368.715083798885,0.43,28631.284916201115,0.57,{"$nulls":8},0.15,7500,1,1.15,"I5","P2","9A"]
["1","09","03","11","01","","GCNE6728","1.09.03.11.01","9242845","Bond - Daley's Drywall","2007-10-10","2007-10-10",21,"C","SL_GCFX1","$$",null,23856,null,23856,23856,null,null,23856,null,23856,23856,null,null,23856,1,{"$nulls":8},0.15,3578.4,1,1.15,"I9","P2","9A"]
["1","09","03","11","01","","GCNE7016","1.09.03.11.01","9242845","Materials - Mission Bell Mfg","2007-08-16","2007-09-06",21,"C","SL_GCFX1","$$",null,10298,null,10298,10298,null,null,10298,null,10298,10298,10298,1,{"$nulls":10},0.15,1544.7,1,1.15,"J4","P2","9A"]
["1","09","03","11","03","","GCCR_0400","1.09.03.11.03","9242847","Rebar Slab @ Basement","2007-05-01","2007-05-07",5,"C","SL_GCFX1","$$",null,180810,null,180810,180810,null,null,180810,null,180810,180810,180810,1,{"$nulls":10},0.15,27121.5,1,1.15,"L1","P2","9A"]
["1","09","03","11","03","","GCNB3560","1.09.03.11.03","9242847","Form 1st Floor Soffit","2007-06-14","2007-06-29",5,"C","SL_GCFX1","$$",null,524800,null,524800,524800,null,null,524800,null,524800,524800,524800,1,{"$nulls":10},0.15,78720,1,1.15,"M1","P2","9A"]
["1","09","03","11","03","","GCNB4010","1.09.03.11.03","9242847","Pour Loading Dock Footings","2007-09-06","2007-09-07",5,"C","SL_GCFX1","$$",null,8100,null,8100,8100,null,null,8100,null,8100,8100,8100,1,{"$nulls":10},0.15,1215,1,1.15,"LD","P2","9A"]
["1","09","03","11","03","","GCNB4100","1.09.03.11.03","9242847","Pour Dock Leveler Slab","2007-09-21","2007-09-21",5,"C","SL_GCFX1","$$",null,1900,null,1900,1900,null,null,1900,null,1900,1900,1900,1,{"$nulls":10},0.15,285,1,1.15,"LD","P2","9A"]
["1","09","03","11","03","","GCNB4130","1.09.03.11.03","9242847","Pour Dock Leveler Walls","2007-09-28","2007-09-28",5,"C","SL_GCFX1","$$",null,3500,null,3500,3500,null,null,3500,null,3500,3500,3500,1,{"$nulls":10},0.15,525,1,1.15,"LD","P2","9A"]
["1","09","03","11","09","  ",null,null,null,"Tunneling                                                   ",{"$nulls":37},"David Saenz"]
["1","09","03","11","15","","GCNB3642","1.09.03.11.15","9242849","HVAC Inserts Plaza Deck","2007-07-02","2007-07-09",6,"C","SL_GCFX1","$$",null,30000,null,30000,30000,null,null,30000,null,30000,30000,30000,1,{"$nulls":10},0.15,4500,1,1.15,"M1","P2","9A"]
["1","09","03","11","15","","GCNB9028","1.09.03.11.15","9242849","BM Plumbing Insulation","2007-09-21","2007-10-12",6,"C","SL_GCFX1","$$",null,84413,null,84413,null,null,null,84413,null,84413,84413,40196.666666666664,0.48,44216.333333333336,0.52,{"$nulls":8},0.15,12661.949999999999,1,1.15,"BA","P2","9A"]
["1","09","03","11","15","","GCNE2414","1.09.03.11.15","9242849","Sub BM Plumbing Insulation","2007-09-21","2007-10-12",6,"C","SL_GCFX1","$$",null,47070,null,47070,null,null,null,47070,null,47070,47070,22414.285714285714,0.48,24655.714285714286,0.52,{"$nulls":8},0.15,7060.5,1,1.15,"SU","P2","9A"]
["1","09","03","11","15","","GCNE2424","1.09.03.11.15","9242849","Sub BM HVAC Balancing","2007-12-27","2008-01-03",6,"C","SL_GCFX1","$$",null,22550,null,22550,22550,null,null,22550,null,22550,22550,null,null,22550,1,{"$nulls":8},0.15,3382.5,1,1.15,"SU","P2","9A"]
["1","09","03","11","16","","GCNB27305","1.09.03.11.16","9242850","BM Drop In Light Fixtures","2007-11-28","2007-12-11",7,"C","SL_GCFX1","$$",null,34499,null,34499,34499,null,null,34499,null,34499,34499,null,null,34499,1,{"$nulls":8},0.15,5174.849999999999,1,1.15,"BA","P2","9A"]
["1","09","03","11","16","","GCNB90022","1.09.03.11.16","9242850","BM Electrical Trim","2007-11-28","2007-12-11",7,"C","SL_GCFX1","$$",null,31598,null,31598,31598,null,null,31598,null,31598,31598,null,null,31598,1,{"$nulls":8},0.15,4739.7,1,1.15,"BA","P2","9A"]
["1","09","03","11","16","","GCNE2366","1.09.03.11.16","9242850","Sub BM Fire / Life / Safety R/I","2007-10-15","2007-11-09",7,"C","SL_GCFX1","$$",null,26789,null,26789,26789,null,null,26789,null,26789,26789,null,null,26789,1,{"$nulls":8},0.15,4018.35,1,1.15,"SU","P2","9A"]
["1","09","03","11","17","","GCHM5280","1.09.03.11.17","9242851","BP35 - NEH Misc. Specialties (Hammock)","2007-11-21","2007-12-05",null,"C","SL_GCFX1","$$",null,28540,null,28540,28540,null,null,28540,null,28540,28540,null,null,28540,1,{"$nulls":8},0.15,4281,1,1.15,null,"P2","9A"]
["1","09","03","11","17","","GCNB3500","1.09.03.11.17","9242851","BM Devices / Doors / Fixtures","2007-11-13","2007-11-27",17,"C","SL_GCFX1","$$",null,175666,null,175666,175666,null,null,175666,null,175666,175666,null,null,175666,1,{"$nulls":8},0.15,26349.899999999998,1,1.15,"BA","P2","9A"]
["1","09","03","11","20","","CF11180","1.09.03.11.20","9242852","AWARD: NEH Furnishing","2008-01-07","2008-01-07",null,"C","SL_AWARD","$$",null,189000,null,223085.20122,223085.20122,null,null,189000,null,223085.20122,223085.20122,null,null,223085.20122,1,{"$nulls":8},0.2,44617.040244,1.1,1.1,3,3,"9A"]
["1","09","03","12","02","  ",null,null,null,"UH - Site Construction                                      ",{"$nulls":37},"David Saenz"]
["1","09","03","12","05","  ",null,null,null,"UH - Metals                                                 ",{"$nulls":37},"David Saenz"]
["1","09","03","12","15","","GCUH3380","1.09.03.12.15","9242856","UH HVAC Trim","2008-01-14","2008-01-28",6,"C","SL_GCFX1","$$",null,42138,null,42138,42138,null,null,42138,null,42138,42138,null,null,42138,1,{"$nulls":8},0.15,6320.7,1,1.15,"UH","P2","9A"]
["1","09","03","12","16","","GCUH04542","1.09.03.12.16","9242857","UH Invert Grounding","2007-10-05","2007-10-19",7,"C","SL_GCFX1","$$",null,36881,null,36881,36881,null,null,36881,null,36881,36881,null,null,36881,1,{"$nulls":8},0.15,5532.15,1,1.15,"UH","P2","9A"]
["1","09","03","12","16","","GCUH04580","1.09.03.12.16","9242857","UH Fire / Life / Safety","2007-11-14","2007-12-05",7,"C","SL_GCFX1","$$",null,22570,null,22570,22570,null,null,22570,null,22570,22570,null,null,22570,1,{"$nulls":8},0.15,3385.5,1,1.15,"UH","P2","9A"]
["1","09","03","12","17","","GCUH02442","1.09.03.12.17","9242858","UH Tunnel Epoxy Flooring","2007-11-10","2007-11-25",22,"C","SL_GCFX1","$$",null,5412,null,5412,5412,null,null,5412,null,5412,5412,null,null,5412,1,{"$nulls":8},0.15,811.8,1,1.15,"UH","P2","9A"]
["1","09","03","12","19","","GCCN1140","1.09.03.12.19","9242859","Niche Excavation","2007-08-02","2007-08-02",3,"C","SL_GCFX1","$$",null,4500,null,4500,4500,null,null,4500,null,4500,4500,4500,1,{"$nulls":10},0.15,675,1,1.15,"CN","P2","9A"]
["1","09","03","12","19","","GCUH01024","1.09.03.12.19","9242859","UH - Install 16 Electrical / 1 Fire Shaft","2007-06-01","2007-07-06",3,"C","SL_GCFX1","$$",null,146066,null,146066,146066,null,null,146066,null,146066,146066,146066,1,{"$nulls":10},0.15,21909.899999999998,1,1.15,"UH","P2","9A"]
["1","09","03","13","  ","  ",null,null,null,"X-Ray - Transport & Diagnostic Hall (XRTD)                  ",{"$nulls":6},0,5055749,0,5055749,2988549,null,0,5055749,0,5055749,5055749,875314,null,4180435,null,0,null,0,null,0,null,0,null,null,758362.35,{"$nulls":6},"David Saenz"]
["1","09","03","13","03","  ",null,null,null,"XRTD - Concrete                                             ",{"$nulls":37},"David Saenz"]
["1","09","03","13","15","","GCHM6440","1.09.03.13.15","9242864","BP10 -  Fire Protection (XR)","2007-12-31","2008-01-29",null,"C","SL_GCFX1","$$",null,63200,null,63200,63200,null,null,63200,null,63200,63200,null,null,63200,1,{"$nulls":8},0.15,9480,1,1.15,null,"P2","9A"]
["1","09","03","13","16","","GCXR1408","1.09.03.13.16","9242865","X-Ray Tunnel - Fire / Life / Safety","2008-02-06","2008-03-05",7,"C","SL_GCFX1","$$",null,42967,null,42967,42967,null,null,42967,null,42967,42967,null,null,42967,1,{"$nulls":8},0.15,6445.05,1,1.15,null,"P2","9A"]
["1","09","03","13","17","  ",null,null,null,"XRTD - Others (include Div 4, and 6 through 14)             ",{"$nulls":6},0,5356,0,5356,5356,null,0,5356,0,5356,5356,0,null,5356,null,0,null,0,null,0,null,0,null,null,803.4,{"$nulls":6},"David Saenz"]
["1","09","03","13","19","","GCXR1340","1.09.03.13.19","9242867","X-Ray Tunnel - Install Shotcrete Lining 6\" Thick","2007-11-22","2007-12-03",3,"C","SL_GCFX1","$$",null,1037900,null,1037900,1037900,null,null,1037900,null,1037900,1037900,null,null,1037900,1,{"$nulls":8},0.15,155685,1,1.15,null,"P2","9A"]
["1","09","03","14","02","","CF14115","1.09.03.14.02","9242870","AWARD: FEH Hutches - Equipment","2008-10-02","2008-10-02",null,"C","SL_AWARD","$$",null,315337,null,381883.8599917,381883.8599917,null,null,315337,null,381883.8599917,381883.8599917,{"$nulls":4},381883.8599917,1,{"$nulls":6},0.6,229130.31599501998,1.5,1.1,3,3,"9A"]
["1","09","03","14","03","  ",null,null,null,"FEH - Concrete                                              ",{"$nulls":37},"David Saenz"]
["1","09","03","14","15","","GCAC4146","1.09.03.14.15","9242872","Access T HVAC Balancing","2008-05-27","2008-06-02",6,"C","SL_GCFX1","$$",null,6490,null,6490,6490,null,null,6490,null,6490,6490,null,null,6490,1,{"$nulls":8},0.15,973.5,1,1.15,"AC","P2","9A"]
["1","09","03","14","15","","GCFH3120","1.09.03.14.15","9242872","FEH HVAC Rough-in","2008-02-07","2008-03-13",6,"C","SL_GCFX1","$$",null,300331,null,300331,300331,null,null,300331,null,300331,300331,null,null,300331,1,{"$nulls":8},0.15,45049.65,1,1.15,"FE","P2","9A"]
["1","09","03","14","15","","GCFH6320","1.09.03.14.15","9242872","FEH Plumbing Trim","2008-04-17","2008-04-30",6,"C","SL_GCFX1","$$",null,10123,null,10123,10123,null,null,10123,null,10123,10123,null,null,10123,1,{"$nulls":8},0.15,1518.45,1,1.15,"FE","P2","9A"]
["1","09","03","14","16","","GCFH3320","1.09.03.14.16","9242873","FEH O/H Electrical R/I","2008-02-07","2008-03-13",7,"C","SL_GCFX1","$$",null,401387,null,401387,401387,null,null,401387,null,401387,401387,null,null,401387,1,{"$nulls":8},0.15,60208.049999999996,1,1.15,"FE","P2","9A"]
["1","09","03","14","17","","GCFH3300","1.09.03.14.17","9242874","FEH Signage","2008-03-14","2008-03-20",null,"C","SL_GCFX1","$$",null,2400,null,2400,2400,null,null,2400,null,2400,2400,null,null,2400,1,{"$nulls":8},0.15,360,1,1.15,"FE","P2","9A"]
["1","09","03","14","18","","GCAC1480","1.09.03.14.18","9242875","Access Tunnel  - Remove Bench","2008-02-07","2008-02-22",3,"C","SL_GCFX1","$$",null,593192,null,593192,593192,null,null,593192,null,593192,593192,null,null,593192,1,{"$nulls":8},0.15,88978.8,1,1.15,"AC","P2","9A"]
["1","09","03","14","19","","GCFH2060","1.09.03.14.19","9242876","FEH Begin Side Drift Exc. Top Heading","2007-06-14","2007-06-21",3,"C","SL_GCFX1","$$",null,421593,null,421593,421593,null,null,421593,null,421593,421593,421593,1,{"$nulls":10},0.15,63238.95,1,1.15,"FE","P2","9A"]
["1","09","03","14","19","","GCFH2104","1.09.03.14.19","9242876","FEH Excavate Left Hand Drift -  Bench","2007-08-21","2007-09-07",3,"C","SL_GCFX1","$$",null,421593,null,421593,421593,null,null,421593,null,421593,421593,421593,1,{"$nulls":10},0.15,63238.95,1,1.15,"FE","P2","9A"]
["1","09","03","15","  ","  ",null,null,null,"BTH Service Buildings 2.1, 2.2, and 2.3 (SB BTH)            ",{"$nulls":6},0,3186765,0,3186765,2125544,null,0,3186765,0,3186765,3186765,1144727.819821046,null,2042037.180178954,null,0,null,0,null,0,null,0,null,null,478014.75,{"$nulls":6},"David Saenz"]
["1","09","03","15","15","","GCBT3092","1.09.03.15.15","9242880","Service Bldg 2.1 HVAC Rough-in","2007-08-23","2007-09-20",6,"C","SL_GCFX1","$$",null,170000,null,170000,170000,null,null,170000,null,170000,170000,170000,1,{"$nulls":10},0.15,25500,1,1.15,"S1","P2","9A"]
["1","09","03","15","15","","GCBT3126","1.09.03.15.15","9242880","Service Bldg 2.2 HVAC Insulation","2007-11-02","2007-11-08",6,"C","SL_GCFX1","$$",null,22355,null,22355,22355,null,null,22355,null,22355,22355,null,null,22355,1,{"$nulls":8},0.15,3353.25,1,1.15,"S2","P2","9A"]
["1","09","03","15","15","","GCBT5400","1.09.03.15.15","9242880","Service Bldg 2.2 Plumbing Rough-in","2007-10-04","2007-11-01",6,"C","SL_GCFX1","$$",null,110000,null,110000,110000,null,null,110000,null,110000,110000,null,null,110000,1,{"$nulls":8},0.15,16500,1,1.15,"S2","P2","9A"]
["1","09","03","15","16","  ",null,null,null,"SB BTH - Electrical                                         ",{"$nulls":6},0,1288597,0,1288597,1274528,null,0,1288597,0,1288597,1288597,378659.3076923077,null,909937.6923076923,null,0,null,0,null,0,null,0,null,null,193289.55,{"$nulls":6},"David Saenz"]
["1","09","03","15","16","","GCBT3190","1.09.03.15.16","9242881","BTH 2.1 Cable Trays","2007-08-23","2007-09-06",7,"C","SL_GCFX1","$$",null,32446,null,32446,32446,null,null,32446,null,32446,32446,32446,1,{"$nulls":10},0.15,4866.9,1,1.15,"S1","P2","9A"]
["1","09","03","15","17","  ",null,null,null,"SB BTH - Others (include Div 4, and 6 through 14            ",{"$nulls":6},0,927152,0,927152,0,null,0,927152,0,927152,927152,425004.7209199469,null,502147.27908005303,null,0,null,0,null,0,null,0,null,null,139072.8,{"$nulls":6},"David Saenz"]
["1","09","03","15","17","","GCHM6320","1.09.03.15.17","9242882","BP39 - Metal Bldg (BTH) Hammock","2007-08-01","2007-12-12",null,"C","SL_GCFX1","$$",null,924132,null,924132,null,null,null,924132,null,924132,924132,423850.01503759396,0.46,500281.984962406,0.54,{"$nulls":8},0.15,138619.8,1,1.15,"S1","P2","9A"]
["1","09","03","16","03","","GCUH02197","1.09.03.16.03","9242885","UH3.1 Rebar Retaining Walls","2007-07-27","2007-08-06",5,"C","SL_GCFX1","$$",null,2650,null,2650,2650,null,null,2650,null,2650,2650,2650,1,{"$nulls":10},0.15,397.5,1,1.15,"X1","P2","9A"]
["1","09","03","16","03","","GCUH02204","1.09.03.16.03","9242885","UH3.1 Prep & Form SOG","2007-08-23","2007-08-30",5,"C","SL_GCFX1","$$",null,39400,null,39400,39400,null,null,39400,null,39400,39400,39400,1,{"$nulls":10},0.15,5910,1,1.15,"X1","P2","9A"]
["1","09","03","16","15","","GCUH3244","1.09.03.16.15","9242887","BP10 - Fire Protection (SB UH)","2007-09-28","2007-10-10",null,"C","SL_GCFX1","$$",null,11452,null,11452,null,null,null,11452,null,11452,11452,2863,0.25,8589,0.75,{"$nulls":8},0.15,1717.8,1,1.15,"UH","P2","9A"]
["1","09","03","16","16","","GCUH3220","1.09.03.16.16","9242888","UH 3.1 O/H Electrical R/I","2007-09-28","2007-10-26",7,"C","SL_GCFX1","$$",null,326368,null,326368,null,null,null,326368,null,326368,326368,34968,0.11,291400,0.89,{"$nulls":8},0.15,48955.2,1,1.15,"X1","P2","9A"]
["1","09","03","16","16","","GCUH3344","1.09.03.16.16","9242888","UH 3.1 Lighting","2007-10-29","2007-11-09",7,"C","SL_GCFX1","$$",null,15125,null,15125,15125,null,null,15125,null,15125,15125,null,null,15125,1,{"$nulls":8},0.15,2268.75,1,1.15,"X1","P2","9A"]
["1","09","03","17","03","  ",null,null,null,"SB FEH - Concrete                                           ",{"$nulls":6},0,597473,0,597473,597473,null,0,597473,0,597473,597473,0,null,597473,null,0,null,0,null,0,null,0,null,null,89620.95,{"$nulls":6},"David Saenz"]
["1","09","03","17","03","","GC8B11450","1.09.03.17.03","9242892","AT Yard Form SOG","2008-04-28","2008-04-30",5,"C","SL_GCFX1","$$",null,32100,null,32100,32100,null,null,32100,null,32100,32100,null,null,32100,1,{"$nulls":8},0.15,4815,1,1.15,"8B","P2","9A"]
["1","09","03","17","03","","GC8B11470","1.09.03.17.03","9242892","AT Yard Rebar SOG","2008-05-01","2008-05-05",5,"C","SL_GCFX1","$$",null,6400,null,6400,6400,null,null,6400,null,6400,6400,null,null,6400,1,{"$nulls":8},0.15,960,1,1.15,"8B","P2","9A"]
["1","09","03","17","16","","GC8B11506","1.09.03.17.16","9242895","AT Yard Electrical R/I","2008-05-22","2008-05-29",7,"C","SL_GCFX1","$$",null,189355,null,189355,189355,null,null,189355,null,189355,189355,null,null,189355,1,{"$nulls":8},0.15,28403.25,1,1.15,"8B","P2","9A"]
["1","09","03","17","20","  ",null,null,null,"SB FEH - Project Close Out                                  ",{"$nulls":37},"David Saenz"]
["1","09","03","18","03","  ",null,null,null,"CUP - Concrete                                              ",{"$nulls":6},0,688071,0,688071,688071,null,0,688071,0,688071,688071,688071,null,0,null,0,null,0,null,0,null,0,null,null,103210.65,{"$nulls":6},"David Saenz"]
["1","09","03","18","03","","GCCU1464","1.09.03.18.03","9242900","Pour CUP Walls - Pour #1","2007-07-11","2007-07-11",5,"C","SL_GCFX1","$$",null,34650,null,34650,34650,null,null,34650,null,34650,34650,34650,1,{"$nulls":10},0.15,5197.5,1,1.15,"C1","P2","9A"]
["1","09","03","18","03","","GCCU1744","1.09.03.18.03","9242900","Form CUP Ftgs - Pour #1","2007-06-12","2007-06-19",5,"C","SL_GCFX1","$$",null,42350,null,42350,42350,null,null,42350,null,42350,42350,42350,1,{"$nulls":10},0.15,6352.5,1,1.15,"C1","P2","9A"]
["1","09","03","18","05","  ",null,null,null,"CUP - Metals                                                ",{"$nulls":6},0,46600,0,46600,46600,null,0,46600,0,46600,46600,46600,null,0,null,0,null,0,null,0,null,0,null,null,6990,{"$nulls":6},"David Saenz"]
["1","09","03","18","15","","GCCU42308","1.09.03.18.15","9242902","CUP HVAC Trim","2007-10-29","2007-12-18",6,"C","SL_GCFX1","$$",null,200195,null,200195,200195,null,null,200195,null,200195,200195,null,null,200195,1,{"$nulls":8},0.15,30029.25,1,1.15,"CP","P2","9A"]
["1","09","03","18","15","","GCCU42312","1.09.03.18.15","9242902","CUP HVAC Insulation","2007-11-05","2007-11-19",6,"C","SL_GCFX1","$$",null,32545,null,32545,32545,null,null,32545,null,32545,32545,null,null,32545,1,{"$nulls":8},0.15,4881.75,1,1.15,"CP","P2","9A"]
["1","09","03","18","16","","GCCU1424","1.09.03.18.16","9242903","CUP Set & Anchor Substations / Other Equip","2007-08-07","2007-08-13",7,"C","SL_GCFX1","$$",null,46072,null,46072,46072,null,null,46072,null,46072,46072,46072,1,{"$nulls":10},0.15,6910.8,1,1.15,"CP","P2","9A"]
["1","09","03","18","16","","GCCU3940","1.09.03.18.16","9242903","CUP Set & Anchor Switchboards & Panels","2007-10-11","2007-10-31",7,"C","SL_GCFX1","$$",null,98567,null,98567,98567,null,null,98567,null,98567,98567,null,null,98567,1,{"$nulls":8},0.15,14785.05,1,1.15,"CP","P2","9A"]
["1","09","03","18","17","","GCHM5160","1.09.03.18.17","9242904","BP28 - Overhead Coiling Doors (Hammock)","2007-09-05","2007-09-18",18,"C","SL_GCFX1","$$",null,83500,null,83500,83500,null,null,83500,null,83500,83500,83500,1,{"$nulls":10},0.15,12525,1,1.15,null,"P2","9A"]
["1","09","03","19","01","","CF19110","1.09.03.19.01","8819031","Start: Pre-Design for CEH Building","2007-05-01","2007-05-30",null,"C","SL_MSPY2","$$",null,20000,null,20000,20000,null,null,20000,null,20000,20000,20000,1,{"$nulls":10},0.25,5000,1.1,1.15,null,2,"9A"]
["1","09","03","19","02","","CF19175","1.09.03.19.02","9242907","AWARD: Construction for B028 Phase 2 Renovation","2008-10-02","2008-10-02",null,"C","SL_AWARD","$$",null,1664000,null,2015160.7424,2015160.7424,null,null,1664000,null,2015160.7424,2015160.7424,{"$nulls":4},2015160.7424,1,{"$nulls":6},0.25,503790.1856,1.1,1.15,null,3,"9A"]
["1","09","03","19","02","","CF19230","1.09.03.19.02","9242907","Start: CEH Building Remodel Construction","2008-10-03","2009-06-17",null,"C","SA_MSSY2","$$",null,2579525,null,2579525,2579525,null,null,2579525,null,2579525,2579525,{"$nulls":4},2579525,1,{"$nulls":6},0.25,644881.25,1.1,1.15,null,3,"9A"]
["2","01","01","03","  ","  ",null,null,null,"Linac Physics                                               ",{"$nulls":37},"Dave Schultz"]
["2","01","01","04","  ","  ",null,null,null,"Undulator Physics                                           ",{"$nulls":37},"Dave Schultz"]
["2","01","01","11","  ","  ",null,null,null,"Global Controls OPC                                         ",{"$nulls":6},1271,90400,121705.86451724917,97584.05183999999,219289.91635724914,null,1271,90400,121705.86451724917,97584.05183999999,219289.91635724914,148740.63774972287,null,70549.27860752631,null,0,null,0,null,0,null,0,null,null,0]
["2","01","01","11","04","  ",null,null,null,"Laser Controls Design                                       ",{"$nulls":37},"Hamid Shoaee"]
["2","01","01","11","11","  ",null,null,null,"Global Controls Commissioning                               ",{"$nulls":37},"Dave Schultz"]
["2","01","01","12","","","PMCM_0005","2.01.01.12","XRB10112","Injector Commissioning Management","2007-05-01","2007-11-30",null,"X","SL_ME2","Hrs",1043,null,120212.36446469837,null,120212.36446469837,null,1043,null,120212.36446469837,null,120212.36446469837,86349.72658731855,0.72,33862.63787737983,0.28,{"$nulls":12},4,1,"2S"]
["2","01","01","13","","","PMCM_P005","2.01.01.13","XRB10113","Injector Physicist Commissioning Support","2007-05-01","2007-11-30",null,"X","SL_PHSS2","Hrs",7092,null,761865.1952971931,null,761865.1952971931,null,7092,null,761865.1952971931,null,761865.1952971931,547255.2811289697,0.72,214609.91416822342,0.28,{"$nulls":12},4,1,"2S"]
["2","01","01","13","","","PMCM_P105","2.01.01.13","XRB10113","L2/BC2/L3 Physicist Commissioning Support","2007-12-03","2008-10-31",null,"X","SL_PHSS2","Hrs",11395,null,1246791.0017906283,null,1246791.0017906283,null,11395,null,1246791.0017906283,null,1246791.0017906283,null,null,1134467.488115797,0.91,112323.51367483137,0.09,{"$nulls":10},4,1,"2S"]
["2","01","03","  ","  ","  ",null,null,null,"Project Mgmnt, Planning and Admn - M&S (OPC)                ",{"$nulls":6},52902,4836923,6556858.32980707,5319923.595147794,11006996.186669583,null,52902,4836923,6556858.32980707,5242145.718410352,11799004.048217423,1610999.4247099194,null,3552010.8530108887,null,3525494.9657075703,null,3110498.804789044,null,0,null,0,null,null,0,{"$nulls":6},"Wendy Sisson"]
["2","01","03","01","  ","  ",null,null,null,"SLAC Project Office - General                               ",{"$nulls":6},38847,0,4955852.303152172,0,4955852.303152172,null,38847,0,4955852.303152172,0,4955852.303152172,607920.8996905703,null,1425955.4046113335,null,1433485.8477237364,null,1488490.151126532,null,0,null,0,null,null,0,{"$nulls":6},"Wendy Sisson"]
["2","01","03","01","","","PM213_0245","2.01.03.01","XRB10301","Project Director  - FY07","2007-05-01","2007-09-28","S","X","SL_PM2","Hrs",371,null,69165.03618809627,null,69165.03618809627,null,371,null,69165.03618809627,null,69165.03618809627,69165.03618809627,1,{"$nulls":14},4,1,"1A"]
["2","01","03","01","","","PM213_0256","2.01.03.01","XRB10301","Project Director- FY10","2009-10-01","2010-05-28","S","X","SL_PM2","Hrs",893,null,178234.21577867697,null,178234.21577867697,null,893,null,178234.21577867697,null,178234.21577867697,{"$nulls":6},178234.21577867697,1,{"$nulls":8},4,1,"1A"]
["2","01","03","01","","","PM213_0296","2.01.03.01","XRB10301","E-Beam Systems Manager - FY10","2009-10-01","2010-05-28","S","X","SL_TSM2","Hrs",893,null,116407.42396067602,null,116407.42396067602,null,893,null,116407.42396067602,null,116407.42396067602,{"$nulls":6},116407.42396067602,1,{"$nulls":8},4,1,"1A"]
["2","01","03","01","","","PM301_7000","2.01.03.01","XRB10301","Global Laser Coordination - FY07","2007-05-01","2007-09-28","S","X","SL_LPM2","Hrs",742,null,90345.43289713786,null,90345.43289713786,null,742,null,90345.43289713786,null,90345.43289713786,90345.43289713786,1,{"$nulls":14},4,1,"1A"]
["2","01","03","02","","","PM210_1002","2.01.03.02","XRB10302","PMCS Support - Maintenance - FY09","2008-10-01","2009-09-30","S","X","SA_MSPS2","$$",null,502520,null,567694.866483296,567694.866483296,null,null,502520,null,567694.866483296,567694.866483296,{"$nulls":4},567694.866483296,1,{"$nulls":10},2,1,"1A"]
["2","01","03","02","","","PM212_0154","2.01.03.02","XRB10302","QA/QC Support - FY08","2007-10-01","2008-09-30","S","X","SL_QAO2","Hrs",851,null,68952.65661719606,null,68952.65661719606,null,851,null,68952.65661719606,null,68952.65661719606,null,null,68952.65661719606,1,{"$nulls":12},4,1,"1A"]
["2","01","03","02","","","PM212_0193","2.01.03.02","XRB10302","Computing Res Support - FY09","2008-10-01","2009-09-30","S","X","SL_CRA2","Hrs",326,null,20678.956014382442,null,20678.956014382442,null,326,null,20678.956014382442,null,20678.956014382442,{"$nulls":4},20678.956014382442,1,{"$nulls":10},4,1,"1A"]
["2","01","03","02","","","PM212_0194","2.01.03.02","XRB10302","Computing Res Support - FY10","2009-10-01","2010-05-28","S","X","SL_CRA2","Hrs",269,null,17455.77002269206,null,17455.77002269206,null,269,null,17455.77002269206,null,17455.77002269206,{"$nulls":6},17455.77002269206,1,{"$nulls":8},4,1,"1A"]
["2","01","03","03","","","PM210_0495","2.01.03.03","XRB10303","Pre-ops Electrical Power Usage - 2009","2008-09-30","2009-10-01",null,"X","SL_POWB2","$$",null,500000,null,500000,null,null,null,500000,null,500000,500000,null,null,1366.120218579235,0,498633.87978142075,1,0,0,{"$nulls":8},4,1,"1A"]
["2","01","03","03","","","PM400_0044","2.01.03.03","XRB10303","Education/Outreach M&S - FY09","2008-10-01","2009-09-30","S","X","SL_MSCS2","$$",null,10000,null,11296.960648,11296.960648,null,null,10000,null,11296.960648,11296.960648,{"$nulls":4},11296.960648,1,{"$nulls":10},5,1,"1A"]
["2","01","03","06","  ","  ",null,null,null,"X-Ray Endstation Physics                                    ",{"$nulls":37},"Wendy Sisson"]
["2","02","01","02","  ","  ",null,null,null,"High level Application Software                             ",{"$nulls":37},"Jose Chan"]
["2","02","02","04","","","IJ16020400","2.02.02.04","SK20204","Procure 12 AMP MCOR Modules (2)-Spares","2007-05-01","2007-10-18",null,"X","SL_MSEG2","$$",null,3600,null,3895.028568288,null,null,null,3600,null,3895.028568288,3895.028568288,3505.5257114592,0.9,389.5028568288,0.1,{"$nulls":12},2,3,"2G","K. Luchini"]
["2","02","02","04","01","  ",null,null,null,"Power Supply Controls                                       ",{"$nulls":37},"Hamid Shoaee"]
["2","02","02","06","12","  ",null,null,null,"Controls - Movable Collimator                               ",{"$nulls":37},"Dave Schultz"]
["2","02","02","06","14","  ",null,null,null,"Controls - Faraday Cup                                      ",{"$nulls":37},"Dave Schultz"]
["2","02","03","  ","  ","  ",null,null,null,"Injector Lasers                                             ",{"$nulls":6},0,472000,0,509559.3068015999,2208.5948015999998,null,0,472000,0,509559.3068015999,509559.3068015999,507350.71199999994,null,2208.5948015999998,null,0,null,0,null,0,null,0,null,null,0]
["2","02","03","06","  ","  ",null,null,null,"Pre Amp Low Power Comp                                      ",{"$nulls":37},"Jose Chan"]
["2","02","03","09","  ","  ",null,null,null,"Load Lock Transport System                                  ",{"$nulls":37},"Jose Chan"]
["2","02","04","  ","  ","  ",null,null,null,"Injector RF Subsystem                                       ",{"$nulls":6},505,492394,54063.55260421334,496933.9393088,550997.4919130134,null,505,492394,54063.55260421334,496933.9393088,550997.4919130134,115731.49191301333,null,0,null,435266,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Jose Chan"]
["2","02","04","01","02","  ",null,null,null,"RF Gun Supports                                             ",{"$nulls":37},"Jose Chan"]
["2","02","04","02","  ","  ",null,null,null,"Cathode Processing (CP) Station                             ",{"$nulls":6},0,55000,0,59370.827999999994,59370.827999999994,null,0,55000,0,59370.827999999994,59370.827999999994,59370.827999999994,null,0,null,0,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Jose Chan"]
["2","02","04","02","03","  ",null,null,null,"CP Load Lock Supports                                       ",{"$nulls":37},"Jose Chan"]
["2","02","04","03","  ","  ",null,null,null,"S-Band Low Level System                                     ",{"$nulls":37},"Jose Chan"]
["2","02","04","06","03","  ",null,null,null,"Major Linac Support                                         ",{"$nulls":37},"Jose Chan"]
["2","02","05","01","03","  ",null,null,null,"Chicane                                                     ",{"$nulls":37},"Jose Chan"]
["2","02","05","02","02","  ",null,null,null,"LTDL1 Quadrupoles ( )                                       ",{"$nulls":37},"Jose Chan"]
["2","02","05","03","05","  ",null,null,null,"SAB Steering Coils ( )                                      ",{"$nulls":37},"Jose Chan"]
["2","02","06","02","  ","  ",null,null,null,"GTL Supports                                                ",{"$nulls":37},"Jose Chan"]
["2","02","06","05","  ","  ",null,null,null,"L0-1TL0-2 Major tube support structure                      ",{"$nulls":37},"Jose Chan"]
["2","02","07","  ","  ","  ",null,null,null,"Injector Diagnostics                                        ",{"$nulls":37},"Jose Chan"]
["2","02","07","01","02","  ",null,null,null,"Gun Spectrometer (GS) Assembly                              ",{"$nulls":37},"Jose Chan"]
["2","02","07","02","04","  ",null,null,null,"DL1TL Current Monitor ( )                                   ",{"$nulls":37},"Jose Chan"]
["2","02","07","04","01","  ",null,null,null,"GTL Faraday Cup/YAG1                                        ",{"$nulls":37},"Jose Chan"]
["2","02","07","04","04","  ",null,null,null,"LTDL1 OTR(5)/YAG ( )                                        ",{"$nulls":37},"Jose Chan"]
["2","02","07","05","02","  ",null,null,null,"DL1 Wire Scanner                                            ",{"$nulls":37},"Jose Chan"]
["2","02","08","01","","","IJ101_4190","2.02.08.01","XBG20801","Heater & Optics Fabrication Oversight","2008-01-31","2008-04-02","EB","X","SL_ME2","Hrs",80,null,9371.859917920076,null,9371.859917920076,null,80,null,9371.859917920076,null,9371.859917920076,null,null,9371.859917920076,1,{"$nulls":12},4,5,"2A"]
["2","02","08","02","  ","  ",null,null,null,"Heater Laser & Optics                                       ",{"$nulls":6},746,86168,89258.07184684361,95155.09843213439,184413.170278978,null,746,86168,89258.07184684361,95155.09843213439,184413.170278978,0,null,184413.170278978,null,0,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Jose Chan"]
["2","02","08","03","  ","  ",null,null,null,"Heater Magnets                                              ",{"$nulls":6},1012,177000,102869.50864361814,195460.63994159998,298330.1485852181,null,1012,177000,102869.50864361814,195460.63994159998,298330.1485852181,0,null,298330.1485852181,null,0,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Jose Chan"]
["2","02","08","03","01","","IJ501_4225","2.02.08.03.01","XBG2080301","Vendor Fab Chicane Dipole Assembly","2007-10-02","2007-11-12","RC","X","SL_MDD2","Hrs",10,null,982.2026636772866,null,982.2026636772866,null,10,null,982.2026636772866,null,982.2026636772866,null,null,982.2026636772866,1,{"$nulls":12},4,5,"2A"]
["2","02","08","03","02","","IJ505_2040","2.02.08.03.02","XBG2080302","Prep Bid Pak - Undulator","2008-02-06","2008-03-05","RC","X","SL_ME2","Hrs",20,null,2342.964979480019,null,2342.964979480019,null,20,null,2342.964979480019,null,2342.964979480019,null,null,2342.964979480019,1,{"$nulls":12},4,5,"2A"]
["2","02","08","03","02","","IJ505_2080","2.02.08.03.02","XBG2080302","AWARD: Undulator","2008-04-17","2008-04-17","RC","X","SL_AWARD","$$",null,125000,null,147543.1225,147543.1225,null,null,125000,null,147543.1225,147543.1225,null,null,147543.1225,1,{"$nulls":12},4,5,"2A"]
["2","02","08","04","  ","  ",null,null,null,"Heater Vacuum                                               ",{"$nulls":6},400,45000,42867.60951815676,49693.38303599999,92560.99255415676,null,400,45000,42867.60951815676,49693.38303599999,92560.99255415676,0,null,92560.99255415676,null,0,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Jose Chan"]
["2","02","08","05","  ","  ",null,null,null,"Heater Diagnostics                                          ",{"$nulls":6},296,20000,30863.383216447517,22085.948016,52949.33123244751,null,296,20000,30863.383216447517,22085.948016,52949.33123244751,0,null,52949.33123244751,null,0,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Jose Chan"]
["2","02","08","06","","","IJ1715_070","2.02.08.06","XBE20806","Install Magnet Supports","2008-08-27","2008-09-10","KR","X","SL_TMUI2","Hrs",24,null,2135.8133143775995,null,2135.8133143775995,null,24,null,2135.8133143775995,null,2135.8133143775995,null,null,2135.8133143775995,1,{"$nulls":12},4,5,"2A"]
["2","02","08","06","","","IJ1715_110","2.02.08.06","XBE20806","Install Undulator","2008-10-02","2008-10-22","KR","X","SL_MFAT2","Hrs",80,null,8273.589071999999,null,8273.589071999999,null,80,null,8273.589071999999,null,8273.589071999999,{"$nulls":4},8273.589071999999,1,{"$nulls":10},4,5,"2A"]
["2","02","17","11","","","IJCM_E005","2.02.17.11","XRB21711","Injector Engr Commissioning Support","2007-05-01","2007-11-30",null,"X","SL_EE2","Hrs",3442,null,370300.87882480695,null,370300.87882480695,null,3442,null,370300.87882480695,null,370300.87882480695,265990.77211359376,0.72,104310.10671121323,0.28,{"$nulls":12},4,1,"2S"]
["2","02","17","11","","","IJCM_M010","2.02.17.11","XRB21711","CTL - Maintenance II","2007-12-03","2008-04-30",null,"X","SL_CCA2","Hrs",658,null,50808.81700118483,null,50808.81700118483,null,658,null,50808.81700118483,null,50808.81700118483,null,null,50808.81700118483,1,{"$nulls":12},4,1,"2S"]
["2","03","01","01","  ","  ",null,null,null,"Linac System Mgmt & Integration                             ",{"$nulls":37},"Dave Schultz"]
["2","03","02","03","  ","  ",null,null,null,"Machine Protection System (MPS)                             ",{"$nulls":37},"Dave Schultz"]
["2","03","02","04","01","","LN02043621","2.03.02.04.01","SK3020401","Spare Pwr Supply (Dipole Type) Prcurement","2007-05-01","2007-09-20",null,"X","SL_MSEG2","$$",null,21480,null,23187.007007999997,23187.007007999997,null,null,21480,null,23187.007007999997,23187.007007999997,23187.007007999997,1,{"$nulls":14},3,3,"2G","K. Luchini"]
["2","03","02","04","02","","LN02045317","2.03.02.04.02","SK3020402","Spare Pwr Supply (Quad Type) Procurement","2007-05-01","2007-09-20",null,"X","SL_MSEG2","$$",null,21480,null,23187.007007999997,23187.007007999997,null,null,21480,null,23187.007007999997,23187.007007999997,23187.007007999997,1,{"$nulls":14},3,3,"2G","K. Luchini"]
["2","03","02","04","03","","LN02045238","2.03.02.04.03","SK3020403","Integrate Cables","2007-09-21","2007-09-24",null,"X","SL_TMUE2","Hrs",12,null,1321.2192311999997,null,1321.2192311999997,null,12,null,1321.2192311999997,null,1321.2192311999997,1321.2192311999997,1,{"$nulls":14},3,3,"2G","K. Luchini"]
["2","03","02","06","  ","  ",null,null,null,"Controls - E-Beam Diagnostic                                ",{"$nulls":37},"Dave Schultz"]
["2","03","02","06","09","  ",null,null,null,"Controls - Single Beam Dump                                 ",{"$nulls":37},"Dave Schultz"]
["2","03","02","07","  ","  ",null,null,null,"Controls - Laser                                            ",{"$nulls":37},"Dave Schultz"]
["2","03","03","03","  ","  ",null,null,null,"Bend Magnet (BX2_BC2)                                       ",{"$nulls":37},"Jose Chan"]
["2","03","03","13","  ","  ",null,null,null,"Bend Magnet (BYW_LTU)                                       ",{"$nulls":37},"Jose Chan"]
["2","03","04","02","  ","  ",null,null,null,"Linac Beamline Vacuum System                                ",{"$nulls":37},"Jose Chan"]
["2","03","04","07","02","  ",null,null,null,"Exit Assembly Section                                       ",{"$nulls":37},"Jose Chan"]
["2","03","05","08","  ","  ",null,null,null,"Beam Loss Monitors                                          ",{"$nulls":37},"Jose Chan"]
["2","03","05","10","  ","  ",null,null,null,"Electron Safety Beam Dump                                   ",{"$nulls":37},"Jose Chan"]
["2","03","06","05","  ","  ",null,null,null,"X-Band High Power System                                    ",{"$nulls":37},"Jose Chan"]
["2","03","06","07","01","  ",null,null,null,"Modulator                                                   ",{"$nulls":37},"Jose Chan"]
["2","03","07","10","","","LNCM_D305","2.03.07.10","XRB30710","L2/BC2/L3 Designers Support - Maintenance","2007-12-03","2008-09-30",null,"X","SL_MDD2","Hrs",1400,null,137508.37291482012,null,137508.37291482012,null,1400,null,137508.37291482012,null,137508.37291482012,null,null,137508.37291482012,1,{"$nulls":12},4,1,"2S"]
["2","03","07","10","","","LNCM_M310","2.03.07.10","XRB30710","CTL - Maintenance II","2008-06-02","2008-09-30",null,"X","SL_CCA2","Hrs",1785,null,137832.42909895885,null,137832.42909895885,null,1785,null,137832.42909895885,null,137832.42909895885,null,null,137832.42909895885,1,{"$nulls":12},4,1,"2S"]
["2","03","07","10","","","LNCM_M325","2.03.07.10","XRB30710","MFD - Maintenance I","2007-12-03","2008-05-30",null,"X","SL_MFAT2","Hrs",2415,null,244143.70388099996,null,244143.70388099996,null,2415,null,244143.70388099996,null,244143.70388099996,null,null,244143.70388099996,1,{"$nulls":12},4,1,"2S"]
["2","04","  ","  ","  ","  ",null,null,null,"UNDULATOR SYSTEM (OPC)                                      ",{"$nulls":6},56638,3713651,5872951.660535792,4137704.9072699384,9994138.034904378,null,56638,3713651,5872951.660535792,4137704.9072699384,10010656.567805734,202263.96697098514,null,1900484.12318441,null,7907908.477650335,null,0,null,0,null,0,null,null,211091.5792937839]
["2","04","01","01","","","UN11_0B213","2.04.01.01","XRB40101","Engineering Oversight","2007-10-01","2008-07-15","A","X","AN_PM2","Hrs",523,null,60590.050492030634,null,60590.050492030634,null,523,null,60590.050492030634,null,60590.050492030634,null,null,60590.050492030634,1,{"$nulls":8},0,0,1,1,4,1,"4A"]
["2","04","01","01","","","UN11_0B214","2.04.01.01","XRB40101","Design/Drafter/Integration","2007-10-01","2008-07-15","A","X","AN_MDD2","Hrs",343,null,23330.129805251607,null,23330.129805251607,null,343,null,23330.129805251607,null,23330.129805251607,null,null,23330.129805251607,1,{"$nulls":8},0,0,1,1,4,1,"4A"]
["2","04","01","01","","","UN11_0B240","2.04.01.01","XRB40101","Quality Assurance Oversight & Documentation","2007-10-01","2008-07-15","A","X","AN_PM2","Hrs",2058,null,238421.26943135573,null,238421.26943135573,null,2058,null,238421.26943135573,null,238421.26943135573,null,null,238421.26943135573,1,{"$nulls":8},0,0,1,1,4,1,"4A"]
["2","04","01","01","","","UN11_0B251","2.04.01.01","XRB40101","Secretarial/Administrative/IT","2008-07-16","2008-09-30","A","X","AN_ADMN2","Hrs",125,null,14481.369620466212,null,14481.369620466212,null,125,null,14481.369620466212,null,14481.369620466212,null,null,14481.369620466212,1,{"$nulls":8},0,0,1,1,4,1,"4A"]
["2","04","01","01","","","UN11_0B297","2.04.01.01","XRB40101","CPUs and Software","2008-03-03","2008-07-15","A","X","AN_MSEG2","$$",null,5264,null,6013.899092323585,6013.899092323585,null,null,5264,null,6013.899092323585,6013.899092323585,null,null,6013.899092323585,1,{"$nulls":8},0,0,1,1,4,1,"4A"]
["2","04","01","01","","","XDXXXX","2.04.01.01","XRB40101","Project Management","2008-07-16","2009-07-15","A","X","AN_PM2","Hrs",189,null,22292.90058252075,null,22292.90058252075,null,189,null,22292.90058252075,null,22292.90058252075,null,null,4715.805892456312,0.21,17577.094690064438,0.79,{"$nulls":6},0,0,1,1,4,1,"4A"]
["2","04","02","01","  ","  ",null,null,null,"Controls Management and Integration                         ",{"$nulls":6},0,87444,0,98785.14269037121,98785.14269037121,null,0,87444,0,98785.14269037121,98785.14269037121,0,null,0,null,98785.14269037121,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Hamid Shoaee"]
["2","04","02","01","","","UN45_00221","2.04.02.01","SBA40201","AWARD: SDB Ion Pump Cable (1)","2008-10-01","2008-10-02","A","X","SL_AWARD","$$",null,594,null,719.3542554,719.3542554,null,null,594,null,719.3542554,719.3542554,{"$nulls":4},719.3542554,1,{"$nulls":10},3,3,"2G","ANL"]
["2","04","02","04","  ","  ",null,null,null,"Video                                                       ",{"$nulls":37},"Hamid Shoaee"]
["2","04","02","07","  ","  ",null,null,null,"Machine Protection                                          ",{"$nulls":37},"Hamid Shoaee"]
["2","04","03","04","  ","  ",null,null,null,"Production Undulator                                        ",{"$nulls":6},0,2498836,0,2727889.3031040006,2727889.3031040006,null,0,2498836,0,2727889.3031040006,2727889.3031040006,0,null,0,null,2727889.3031040006,null,0,null,0,null,0,null,null,122812.2,{"$nulls":6},"Geoff Pile"]
["2","04","03","04","","","UN33_SPAR3","2.04.03.04","SRB40304","Magnet Assy & Supports Spares- 1st Art","2008-10-02","2009-03-31","A3","S","AN_MSSF2","$$",null,399894,null,436549.88361600006,436549.88361600006,null,null,399894,null,436549.88361600006,436549.88361600006,{"$nulls":4},436549.88361600006,1,{"$nulls":10},1,3,"4A"]
["2","04","03","05","","","UN35_A0150","2.04.03.05","SRB40305","Vendor Fab/Assy - Quad Stages, Stands, etc. (2)","2008-10-02","2008-11-17","A2","S","AN_MSSC2","$$",null,28000,null,32724.562828608006,32724.562828608006,null,null,28000,null,32724.562828608006,32724.562828608006,{"$nulls":4},32724.562828608006,1,{"$nulls":10},2,3,"4A"]
["2","04","03","08","","","UN38_0A195","2.04.03.08","SRB40308","AWARD: 5 Fixed Supports - Spare","2008-10-02","2008-10-02","A","S","AN_AWARD","$$",null,80000,null,91398.8,91398.8,null,null,80000,null,91398.8,91398.8,{"$nulls":4},91398.8,1,{"$nulls":6},0.25,22849.7,1.15,1.1,4,3,"4A"]
["2","04","04","02","","","UN44_00010","2.04.04.02","RRB40402","Fabricate Prototype Extrusion","2007-05-01","2007-09-28","A","R","AN_MSEQ2","$$",null,31400,null,35066.649340799995,35066.649340799995,null,null,31400,null,35066.649340799995,35066.649340799995,35066.649340799995,1,{"$nulls":14},3,3,"4A"]
["2","04","04","02","","","UN44_00010","2.04.04.02","RRB40402","Fabricate Prototype Extrusion","2007-05-01","2007-09-28","A","R","AN_ME2","Hrs",160,null,18119.4067587456,null,18119.4067587456,null,160,null,18119.4067587456,null,18119.4067587456,18119.4067587456,1,{"$nulls":14},3,3,"4A"]
["2","04","04","02","","","UN42_0A150","2.04.04.02","SRB40402","AWARD: Vacuum Chamber Spares","2008-10-02","2008-10-02",null,"S","AN_AWARD","$$",null,230021,null,262795.54218499997,262795.54218499997,null,null,230021,null,262795.54218499997,262795.54218499997,{"$nulls":4},262795.54218499997,1,{"$nulls":6},0.2,52559.108436999995,1.1,1.1,3,3,"4A"]
["2","04","04","02","","","UN42_0S115","2.04.04.02","SRB40402","RCV: Strongback Material (4)","2008-10-14","2008-10-14",null,"S","AA_MSEG2","$$",null,17068,null,19947.95851281005,19947.95851281005,null,null,17068,null,19947.95851281005,19947.95851281005,{"$nulls":4},19947.95851281005,1,{"$nulls":6},0.2,3989.5917025620106,1.1,1.1,3,3,"4A"]
["2","04","04","02","","","UN42_0S135","2.04.04.02","SRB40402","RCV:  Chamber Wall Parts (4)","2008-11-13","2008-11-13",null,"S","AA_MSEG2","$$",null,44132,null,51578.58595543316,51578.58595543316,null,null,44132,null,51578.58595543316,51578.58595543316,{"$nulls":4},51578.58595543316,1,{"$nulls":6},0.2,10315.717191086633,1.1,1.1,3,3,"4A"]
["2","04","04","02","","","UN42_0S150","2.04.04.02","SRB40402","RCV: Strongback Machine (4)","2009-01-12","2009-01-12",null,"S","AA_MSEG2","$$",null,65332,null,76355.75495423637,76355.75495423637,null,null,65332,null,76355.75495423637,76355.75495423637,{"$nulls":4},76355.75495423637,1,{"$nulls":6},0.2,15271.150990847274,1.1,1.1,3,3,"4A"]
["2","04","04","02","","","UN42_0S165","2.04.04.02","SRB40402","RCV:  Laser Weld (4)","2009-02-18","2009-02-18",null,"S","AA_MSEG2","$$",null,13868,null,16208.008475254852,16208.008475254852,null,null,13868,null,16208.008475254852,16208.008475254852,{"$nulls":4},16208.008475254852,1,{"$nulls":6},0.2,3241.6016950509706,1.1,1.1,3,3,"4A"]
["2","04","04","02","","","UN42_0S180","2.04.04.02","SRB40402","RCV:  Final Machine (4)","2009-03-20","2009-03-20",null,"S","AA_MSEG2","$$",null,14668,null,17142.99598464365,17142.99598464365,null,null,14668,null,17142.99598464365,17142.99598464365,{"$nulls":4},17142.99598464365,1,{"$nulls":6},0.2,3428.59919692873,1.1,1.1,3,3,"4A"]
["2","04","04","02","","","UN42_0S185","2.04.04.02","SRB40402","Inspect, Leak Test, Clean, Coat & Bake (4)","2009-03-23","2009-04-10",null,"S","AN_MVE2","Hrs",120,null,14221.861258435694,null,14221.861258435694,null,120,null,14221.861258435694,null,14221.861258435694,{"$nulls":4},14221.861258435694,1,{"$nulls":6},0.2,2844.372251687139,1.1,1.1,3,3,"4A"]
["2","04","04","02","","","UN42_0S185","2.04.04.02","SRB40402","Inspect, Leak Test, Clean, Coat & Bake (4)","2009-03-23","2009-04-10",null,"S","AN_MFAT2","Hrs",102,null,7097.391676157785,null,7097.391676157785,null,102,null,7097.391676157785,null,7097.391676157785,{"$nulls":4},7097.391676157785,1,{"$nulls":6},0.2,1419.4783352315571,1.1,1.1,3,3,"4A"]
["2","04","04","02","","","UN42_0S190","2.04.04.02","SRB40402","Ship Vacuum Chambers to SLAC (4)","2009-04-13","2009-04-17",null,"S","AN_MVE2","Hrs",24,null,2844.372251687139,null,2844.372251687139,null,24,null,2844.372251687139,null,2844.372251687139,{"$nulls":4},2844.372251687139,1,{"$nulls":6},0.2,568.8744503374278,1.1,1.1,3,3,"4A"]
["2","04","04","02","","","UN42_0S190","2.04.04.02","SRB40402","Ship Vacuum Chambers to SLAC (4)","2009-04-13","2009-04-17",null,"S","AN_MFAT2","Hrs",102,null,7097.391676157785,null,7097.391676157785,null,102,null,7097.391676157785,null,7097.391676157785,{"$nulls":4},7097.391676157785,1,{"$nulls":6},0.2,1419.4783352315571,1.1,1.1,3,3,"4A"]
["2","04","04","02","","","UN42_0S215","2.04.04.02","SRB40402","RCV:  Chamber Supports (4)","2008-12-01","2008-12-01",null,"S","AN_MVE2","Hrs",24,null,2844.372251687139,null,2844.372251687139,null,24,null,2844.372251687139,null,2844.372251687139,{"$nulls":4},2844.372251687139,1,{"$nulls":6},0.2,568.8744503374278,1.1,1.1,3,3,"4A"]
["2","04","04","02","","","UN42_0S215","2.04.04.02","SRB40402","RCV:  Chamber Supports (4)","2008-12-01","2008-12-01",null,"S","AA_MSSC2","$$",null,64000,null,74799.00075110402,74799.00075110402,null,null,64000,null,74799.00075110402,74799.00075110402,{"$nulls":4},74799.00075110402,1,{"$nulls":6},0.2,14959.800150220804,1.1,1.1,3,3,"4A"]
["2","04","04","02","","","UN42_0S220","2.04.04.02","SRB40402","Inspect Chamber Supports (4)","2008-12-02","2008-12-17",null,"S","AN_MVE2","Hrs",64,null,7584.9926711657035,null,7584.9926711657035,null,64,null,7584.9926711657035,null,7584.9926711657035,{"$nulls":4},7584.9926711657035,1,{"$nulls":6},0.2,1516.9985342331408,1.1,1.1,3,3,"4A"]
["2","04","04","02","","","UN42_0S220","2.04.04.02","SRB40402","Inspect Chamber Supports (4)","2008-12-02","2008-12-17",null,"S","AN_MFMS2","Hrs",10,null,1064.11947790824,null,1064.11947790824,null,10,null,1064.11947790824,null,1064.11947790824,{"$nulls":4},1064.11947790824,1,{"$nulls":6},0.2,212.823895581648,1.1,1.1,3,3,"4A"]
["2","04","04","02","","","UN42_0S225","2.04.04.02","SRB40402","Package Chamber Supports for Shipment (4)","2008-12-18","2009-01-02",null,"S","AN_MVE2","Hrs",32,null,3792.4963355828518,null,3792.4963355828518,null,32,null,3792.4963355828518,null,3792.4963355828518,{"$nulls":4},3792.4963355828518,1,{"$nulls":6},0.2,758.4992671165704,1.1,1.1,3,3,"4A"]
["2","04","04","02","","","UN42_0S225","2.04.04.02","SRB40402","Package Chamber Supports for Shipment (4)","2008-12-18","2009-01-02",null,"S","AN_MFAT2","Hrs",12,null,834.9872560185629,null,834.9872560185629,null,12,null,834.9872560185629,null,834.9872560185629,{"$nulls":4},834.9872560185629,1,{"$nulls":6},0.2,166.9974512037126,1.1,1.1,3,3,"4A"]
["2","04","04","02","","","UN42_0S230","2.04.04.02","SRB40402","Ship Chamber Supports to SLAC (4)","2009-01-05","2009-01-09",null,"S","AN_MSEG2","$$",null,2545,null,2974.4290142431205,2974.4290142431205,null,null,2545,null,2974.4290142431205,2974.4290142431205,{"$nulls":4},2974.4290142431205,1,{"$nulls":6},0.2,594.8858028486242,1.1,1.1,3,3,"4A"]
["2","04","04","02","01","  ",null,null,null,"Surface Roughness Minimization                              ",{"$nulls":37},"Geoff Pile"]
["2","04","04","02","03","  ",null,null,null,"Materials Study for AC Conductivity                         ",{"$nulls":37},"Geoff Pile"]
["2","04","04","03","  ","  ",null,null,null,"Beam-line Bellows Module Assembly                           ",{"$nulls":6},0,14304,0,16717.57666787175,16717.57666787175,null,0,14304,0,16717.57666787175,16717.57666787175,0,null,0,null,16717.57666787175,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Geoff Pile"]
["2","04","04","03","","","UN43_00360","2.04.04.03","SRB40403","AWARD: Standard Bellows Module (4)","2008-10-02","2008-10-03","A","S","AN_AWARD","$$",null,15019,null,17158.982215,17158.982215,null,null,15019,null,17158.982215,17158.982215,{"$nulls":4},17158.982215,1,{"$nulls":10},3,3,"4A"]
["2","04","04","03","","","UN43_00451","2.04.04.03","SRB40403","REC:  Standard Bellows Module (4)","2008-10-06","2008-12-02","A","S","AA_MSEG2","$$",null,14304,null,16717.57666787175,16717.57666787175,null,null,14304,null,16717.57666787175,16717.57666787175,{"$nulls":4},16717.57666787175,1,{"$nulls":10},3,3,"4A"]
["2","04","04","04","  ","  ",null,null,null,"Single Undulator Test (SUV) Vacuum                          ",{"$nulls":6},37,0,4256.832301597052,0,4256.832301597052,null,37,0,4256.832301597052,0,4256.832301597052,1309.7945543375545,null,2947.0377472594973,null,0,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Geoff Pile"]
["2","04","04","04","","","UN43_00452","2.04.04.04","XRB40404","Support SUT Long Term Test (FY07-08)","2007-06-11","2008-06-09",null,"X","AN_ME2","Hrs",37,null,4256.832301597052,null,4256.832301597052,null,37,null,4256.832301597052,null,4256.832301597052,1309.7945543375545,0.31,2947.0377472594973,0.69,{"$nulls":12},2,3,"4A"]
["2","04","04","05","  ","  ",null,null,null,"Short Diagnostic Break (SDB) Assembly                       ",{"$nulls":6},0,1215,0,1420.0122798842403,1420.0122798842403,null,0,1215,0,1420.0122798842403,1420.0122798842403,0,null,0,null,1420.0122798842403,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Geoff Pile"]
["2","04","04","05","","","UN45_00191","2.04.04.05","SRB40405","AWARD: Pump Manifold (1)","2008-10-02","2008-10-03","A","S","AN_AWARD","$$",null,961,null,1097.928085,1097.928085,null,null,961,null,1097.928085,1097.928085,{"$nulls":4},1097.928085,1,{"$nulls":10},3,3,"4A"]
["2","04","04","05","","","UN45_00251","2.04.04.05","SRB40405","AWARD: Pump Support (1)","2008-10-02","2008-10-06","A","S","AN_AWARD","$$",null,315,null,359.882775,359.882775,null,null,315,null,359.882775,359.882775,{"$nulls":4},359.882775,1,{"$nulls":10},3,3,"4A"]
["2","04","04","05","","","UN45_00323","2.04.04.05","SRB40405","REC: SDB Pump Manifold (1)","2008-10-06","2008-11-14","A","S","AA_MSEG2","$$",null,915,null,1069.3919638634402,1069.3919638634402,null,null,915,null,1069.3919638634402,1069.3919638634402,{"$nulls":4},1069.3919638634402,1,{"$nulls":10},3,3,"4A"]
["2","04","04","05","","","UN45_00333","2.04.04.05","SRB40405","REC: SDB Pump Supports (1)","2008-10-07","2008-11-17","A","S","AA_MSEG2","$$",null,300,null,350.6203160208001,350.6203160208001,null,null,300,null,350.6203160208001,350.6203160208001,{"$nulls":4},350.6203160208001,1,{"$nulls":10},3,3,"4A"]
["2","04","04","06","  ","  ",null,null,null,"Long Diagnostic Break (LDB) Assembly                        ",{"$nulls":6},0,5767,0,6740.091208306514,6740.091208306514,null,0,5767,0,6740.091208306514,6740.091208306514,0,null,0,null,6740.091208306514,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Geoff Pile"]
["2","04","04","06","","","UN46_00206","2.04.04.06","SRB40406","AWARD: LDB Valve (2)","2008-10-02","2008-10-03","A","S","AN_AWARD","$$",null,4391,null,5016.651635,5016.651635,null,null,4391,null,5016.651635,5016.651635,{"$nulls":4},5016.651635,1,{"$nulls":10},3,3,"4A"]
["2","04","04","06","","","UN46_00211","2.04.04.06","SRB40406","AWARD: LDB Chamber Weldment Assembly (1)","2008-10-02","2008-10-03","A","S","AN_AWARD","$$",null,509,null,581.524865,581.524865,null,null,509,null,581.524865,581.524865,{"$nulls":4},581.524865,1,{"$nulls":10},3,3,"4A"]
["2","04","04","06","","","UN46_00311","2.04.04.06","SRB40406","AWARD: LDB Chamber Support (1)","2008-10-02","2008-10-03","A","S","AN_AWARD","$$",null,788,null,900.27818,900.27818,null,null,788,null,900.27818,900.27818,{"$nulls":4},900.27818,1,{"$nulls":10},3,3,"4A"]
["2","04","04","06","","","UN46_00321","2.04.04.06","SRB40406","AWARD: LDB Ion Pump Support (1)","2008-10-02","2008-10-03","A","S","AN_AWARD","$$",null,368,null,420.43448,420.43448,null,null,368,null,420.43448,420.43448,{"$nulls":4},420.43448,1,{"$nulls":10},3,3,"4A"]
["2","04","04","06","","","UN46_00351","2.04.04.06","SRB40406","REC: LDB Valve (2)","2008-10-06","2008-12-02","A","S","AA_MSEG2","$$",null,4182,null,4887.647205329953,4887.647205329953,null,null,4182,null,4887.647205329953,4887.647205329953,{"$nulls":4},4887.647205329953,1,{"$nulls":10},3,3,"4A"]
["2","04","04","06","","","UN46_00401","2.04.04.06","SRB40406","REC: LDB Chamber Weldment Assembly (1)","2008-10-06","2008-12-02","A","S","AA_MSEG2","$$",null,485,null,566.8361775669601,566.8361775669601,null,null,485,null,566.8361775669601,566.8361775669601,{"$nulls":4},566.8361775669601,1,{"$nulls":10},3,3,"4A"]
["2","04","04","06","","","UN46_00407","2.04.04.06","SRB40406","REC: LDB Chamber Support (1)","2008-10-06","2008-12-02","A","S","AA_MSEG2","$$",null,750,null,876.5507900520003,876.5507900520003,null,null,750,null,876.5507900520003,876.5507900520003,{"$nulls":4},876.5507900520003,1,{"$nulls":10},3,3,"4A"]
["2","04","04","06","","","UN46_00409","2.04.04.06","SRB40406","REC: LDB Ion Pump Support (1)","2008-10-06","2008-12-02","A","S","AA_MSEG2","$$",null,350,null,409.0570353576001,409.0570353576001,null,null,350,null,409.0570353576001,409.0570353576001,{"$nulls":4},409.0570353576001,1,{"$nulls":10},3,3,"4A"]
["2","04","04","07","  ","  ",null,null,null,"Entrance Section Assembly                                   ",{"$nulls":37},"Geoff Pile"]
["2","04","04","08","  ","  ",null,null,null,"Exit Section Assembly                                       ",{"$nulls":37},"Geoff Pile"]
["2","04","04","09","  ","  ",null,null,null,"Baking System                                               ",{"$nulls":37},"Geoff Pile"]
["2","04","05","  ","  ","  ",null,null,null,"Undulator System Diagnostics [OPC]                          ",{"$nulls":6},85,116468,8701.461877857093,133014.91623527717,125197.84521177724,null,85,116468,8701.461877857093,133014.91623527717,141716.37811313427,56189.36553078577,null,30046.63025148493,null,55480.38233086357,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Geoff Pile"]
["2","04","05","02","  ","  ",null,null,null,"Undulator Line Diagnostics                                  ",{"$nulls":37},"Geoff Pile"]
["2","04","05","03","  ","  ",null,null,null,"High-Power X-Ray and Profile Diagnostics (HPD)              ",{"$nulls":37},"Geoff Pile"]
["2","04","05","04","  ","  ",null,null,null,"End-of-Undulator(EOU) X-ray and Profile diagnost            ",{"$nulls":37},"Geoff Pile"]
["2","04","05","05","  ","  ",null,null,null,"RFBPM                                                       ",{"$nulls":6},32,70620,2559.236563365927,79430.78207220504,65471.48573421393,null,32,70620,2559.236563365927,79430.78207220504,81990.01863557097,54404.65535648615,null,27585.363279084806,null,0,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Geoff Pile"]
["2","04","05","05","","","UN505_0172","2.04.05.05","SBA40505","AWARD: Copper Body Brazement (2)","2007-08-08","2007-08-10","A","S","AN_AWARD","$$",null,16320,null,17712.3408,17712.3408,null,null,16320,null,17712.3408,17712.3408,17712.3408,1,{"$nulls":14},3,3,"4A"]
["2","04","05","05","","","UN505_0182","2.04.05.05","SBA40505","AWARD: Support & Alignment Mechanism (2)","2007-08-08","2007-08-10","A","S","AN_AWARD","$$",null,5032,null,5461.30508,5461.30508,null,null,5032,null,5461.30508,5461.30508,5461.30508,1,{"$nulls":14},3,3,"4A"]
["2","04","05","05","","","UN505_0192","2.04.05.05","SBA40505","AWARD: RF Cabling (2)","2007-08-08","2007-08-10","A","S","AN_AWARD","$$",null,3019,null,3276.565985,3276.565985,null,null,3019,null,3276.565985,3276.565985,3276.565985,1,{"$nulls":14},3,3,"4A"]
["2","04","05","05","","","UN505_0213","2.04.05.05","SBA40505","REC: Support & Alignment Mechanism (2)","2007-08-13","2007-10-22","A","S","AA_MSEG2","$$",null,5000,null,5622.390003384,null,null,null,5000,null,5622.390003384,5622.390003384,3935.6730023687996,0.7,1686.7170010152,0.3,{"$nulls":12},3,3,"4A"]
["2","04","05","05","","","UN505_0215","2.04.05.05","SBA40505","REC: RF Cabling (4)","2007-08-13","2007-10-22","A","S","AA_MSEG2","$$",null,3000,null,3373.4340020304,null,null,null,3000,null,3373.4340020304,3373.4340020304,2361.4038014212797,0.7,1012.0302006091199,0.3,{"$nulls":12},3,3,"4A"]
["2","04","05","05","","","UN505_0221","2.04.05.05","SBA40505","REC: Copper Body Brazement (2)","2007-12-11","2008-03-17","A","S","AA_MSEG2","$$",null,16000,null,18279.328548096004,18279.328548096004,null,null,16000,null,18279.328548096004,18279.328548096004,null,null,18279.328548096004,1,{"$nulls":12},3,3,"4A"]
["2","04","05","05","","","UN505_0235","2.04.05.05","SBA40505","AWARD: Undulator Waveguide (2)","2007-08-08","2007-08-10","A","S","AN_AWARD","$$",null,6735,null,7309.596525,7309.596525,null,null,6735,null,7309.596525,7309.596525,7309.596525,1,{"$nulls":14},3,3,"4A"]
["2","04","05","05","","","UN505_0236","2.04.05.05","SBA40505","REC: Undulator Waveguide (2)","2007-08-13","2007-10-16","A","S","AA_MSEG2","$$",null,6700,null,7522.7088959426255,null,null,null,6700,null,7522.7088959426255,7522.7088959426255,5759.573998456072,0.77,1763.1348974865527,0.23,{"$nulls":12},3,3,"4A"]
["2","04","05","05","","","UN505_0240","2.04.05.05","SBA40505","AWARD: Down Converter (4)","2007-08-08","2007-08-10","A","S","AN_AWARD","$$",null,31920,null,34643.2548,34643.2548,null,null,31920,null,34643.2548,34643.2548,34643.2548,1,{"$nulls":14},3,3,"4A"]
["2","04","05","05","","","UN505_0241","2.04.05.05","SBA40505","REC: Down Converter (4)","2007-08-13","2007-08-15","A","S","AA_MSEG2","$$",null,31920,null,35647.37092224,35647.37092224,null,null,31920,null,35647.37092224,35647.37092224,35647.37092224,1,{"$nulls":14},3,3,"4A"]
["2","04","05","05","","","UN505_0245","2.04.05.05","SBA40505","AWARD: Local Oscillator (4)","2007-08-08","2007-08-10","A","S","AN_AWARD","$$",null,6000,null,6511.89,6511.89,null,null,6000,null,6511.89,6511.89,6511.89,1,{"$nulls":14},3,3,"4A"]
["2","04","05","05","","","UN505_0246","2.04.05.05","SBA40505","REC: Local Oscillator (4)","2007-08-13","2007-08-15","A","S","AA_MSEG2","$$",null,6000,null,6700.633632,6700.633632,null,null,6000,null,6700.633632,6700.633632,6700.633632,1,{"$nulls":14},3,3,"4A"]
["2","04","05","05","","","UN505_0247","2.04.05.05","SBA40505","Pack/Ship Spares Lot (4) Undulator RFBPM to SLAC","2008-04-30","2008-04-30",null,"S","AN_MSEG2","$$",null,2000,null,2284.9160685120005,2284.9160685120005,null,null,2000,null,2284.9160685120005,2284.9160685120005,null,null,2284.9160685120005,1,{"$nulls":12},3,3,"4A"]
["2","04","05","05","","","UN505_0247","2.04.05.05","SBA40505","Pack/Ship Spares Lot (4) Undulator RFBPM to SLAC","2008-04-30","2008-04-30",null,"S","AN_MFAT2","Hrs",24,null,1632.4289076560892,null,1632.4289076560892,null,24,null,1632.4289076560892,null,1632.4289076560892,null,null,1632.4289076560892,1,{"$nulls":12},3,3,"4A"]
["2","04","05","05","","","UN505_0247","2.04.05.05","SBA40505","Pack/Ship Spares Lot (4) Undulator RFBPM to SLAC","2008-04-30","2008-04-30",null,"S","AN_ME2","Hrs",8,null,926.8076557098376,null,926.8076557098376,null,8,null,926.8076557098376,null,926.8076557098376,null,null,926.8076557098376,1,{"$nulls":12},3,3,"4A"]
["2","04","05","06","  ","  ",null,null,null,"Beam Finder Wire                                            ",{"$nulls":6},16,29974,1896.2481677914259,35031.64450802487,36927.8926758163,null,16,29974,1896.2481677914259,35031.64450802487,36927.8926758163,0,null,0,null,36927.8926758163,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Geoff Pile"]
["2","04","05","06","","","UN506_0205","2.04.05.06","SRB40506","Machine Components (2)","2008-10-03","2008-11-13","A","S","AN_ME2","Hrs",8,null,948.1240838957129,null,948.1240838957129,null,8,null,948.1240838957129,null,948.1240838957129,{"$nulls":4},948.1240838957129,1,{"$nulls":10},3,3,"4A"]
["2","04","05","06","","","UN506_0205","2.04.05.06","SRB40506","Machine Components (2)","2008-10-03","2008-11-13","A","S","AA_MSEQ2","$$",null,19154,null,22385.93844354135,22385.93844354135,null,null,19154,null,22385.93844354135,22385.93844354135,{"$nulls":4},22385.93844354135,1,{"$nulls":10},3,3,"4A"]
["2","04","05","06","","","UN506_0211","2.04.05.06","SRB40506","AWARD:  Machine Components (2)","2008-10-02","2008-10-02",null,"S","AN_AWARD","$$",null,20112,null,22977.65832,22977.65832,null,null,20112,null,22977.65832,22977.65832,{"$nulls":4},22977.65832,1,{"$nulls":10},3,3,"4A"]
["2","04","05","06","","","UN506_0216","2.04.05.06","SRB40506","Weld Components (2)","2009-02-27","2009-03-12",null,"S","AN_MSEQ2","$$",null,9120,null,10658.857607032323,10658.857607032323,null,null,9120,null,10658.857607032323,10658.857607032323,{"$nulls":4},10658.857607032323,1,{"$nulls":10},3,3,"4A"]
["2","04","05","06","","","UN506_0216","2.04.05.06","SRB40506","Weld Components (2)","2009-02-27","2009-03-12",null,"S","AN_ME2","Hrs",8,null,948.1240838957129,null,948.1240838957129,null,8,null,948.1240838957129,null,948.1240838957129,{"$nulls":4},948.1240838957129,1,{"$nulls":10},3,3,"4A"]
["2","04","05","06","","","UN506_0223","2.04.05.06","SRB40506","Ship Fifth Lot of Chamber to SLAC (2)","2009-05-07","2009-05-14",null,"S","AN_MSEG2","$$",null,1700,null,1986.8484574512004,1986.8484574512004,null,null,1700,null,1986.8484574512004,1986.8484574512004,{"$nulls":4},1986.8484574512004,1,{"$nulls":10},3,3,"4A"]
["2","04","05","07","  ","  ",null,null,null,"Charge Monitor (CM)                                         ",{"$nulls":37},"Geoff Pile"]
["2","04","05","08","  ","  ",null,null,null,"Beam Loss Monitoring                                        ",{"$nulls":6},0,15874,0,18552.48965504727,18552.48965504727,null,0,15874,0,18552.48965504727,18552.48965504727,0,null,0,null,18552.48965504727,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Geoff Pile"]
["2","04","05","08","","","UN508_0082","2.04.05.08","SRB40508","AWARD:  PMT (2)","2008-10-02","2008-10-02","A","S","AN_AWARD","$$",null,6785,null,7751.760725,7751.760725,null,null,6785,null,7751.760725,7751.760725,{"$nulls":4},7751.760725,1,{"$nulls":10},4,3,"4A"]
["2","04","05","08","","","UN508_0105","2.04.05.08","SRB40508","AWARD:  Beam Loss Monitor Fiber (2)","2008-10-02","2008-10-02","A","S","AN_AWARD","$$",null,4941,null,5645.018385,5645.018385,null,null,4941,null,5645.018385,5645.018385,{"$nulls":4},5645.018385,1,{"$nulls":10},4,3,"4A"]
["2","04","05","08","","","UN508_0106","2.04.05.08","SRB40508","AWARD:  Integrating Fiber (2)","2008-10-02","2008-10-02",null,"S","AN_AWARD","$$",null,4941,null,5645.018385,5645.018385,null,null,4941,null,5645.018385,5645.018385,{"$nulls":4},5645.018385,1,{"$nulls":10},4,3,"4A"]
["2","04","05","08","","","UN508_0107","2.04.05.08","SRB40508","REC:  PMT (2)","2008-11-14","2008-11-14",null,"S","AA_MSEG2","$$",null,6462,null,7552.361607088033,7552.361607088033,null,null,6462,null,7552.361607088033,7552.361607088033,{"$nulls":4},7552.361607088033,1,{"$nulls":10},4,3,"4A"]
["2","04","05","08","","","UN508_0108","2.04.05.08","SRB40508","REC:  Beam Loss Monitor Fiber (2)","2008-11-14","2008-11-14",null,"S","AA_MSEG2","$$",null,4706,null,5500.064023979618,5500.064023979618,null,null,4706,null,5500.064023979618,5500.064023979618,{"$nulls":4},5500.064023979618,1,{"$nulls":10},4,3,"4A"]
["2","04","05","08","","","UN508_0109","2.04.05.08","SRB40508","REC:  Integrating Fiber (2)","2008-11-14","2008-11-14",null,"S","AA_MSEG2","$$",null,4706,null,5500.064023979618,5500.064023979618,null,null,4706,null,5500.064023979618,5500.064023979618,{"$nulls":4},5500.064023979618,1,{"$nulls":10},4,3,"4A"]
["2","04","05","09","  ","  ",null,null,null,"Radiation Detection Monitor (RDM)                           ",{"$nulls":37},"Geoff Pile"]
["2","04","05","10","  ","  ",null,null,null,"Single Undulator Test (SUT) Diagnostics                     ",{"$nulls":6},37,0,4245.97714669974,0,4245.97714669974,null,37,0,4245.97714669974,0,4245.97714669974,1784.710174299616,null,2461.2669724001244,null,0,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Geoff Pile"]
["2","04","05","10","","","UN509_0176","2.04.05.10","XRB40510","Support SUT Test (FY07-08)","2007-05-01","2008-04-29",null,"X","AN_MVE2","Hrs",37,null,4245.97714669974,null,4245.97714669974,null,37,null,4245.97714669974,null,4245.97714669974,1784.710174299616,0.42,2461.2669724001244,0.58,{"$nulls":12},2,3,"4A"]
["2","04","06","  ","  ","  ",null,null,null,"LTU/Undulator/Dump Commissioning                            ",{"$nulls":6},37425,500000,3720984.831383937,564848.0324,4285832.863783937,null,37425,500000,3720984.831383937,564848.0324,4285832.863783937,0,null,101369.58734326348,null,4184463.2764406735,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Dave Schultz"]
["2","04","06","01","  ","  ",null,null,null,"LTU/Undulator/Dump Commissioning                            ",{"$nulls":6},37425,500000,3720984.831383937,564848.0324,4285832.863783937,null,37425,500000,3720984.831383937,564848.0324,4285832.863783937,0,null,101369.58734326348,null,4184463.2764406735,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Dave Schultz"]
["2","04","06","01","","","UNCM_D405","2.04.06.01","XRB40601","LTU/Und/Dump Designers Support","2008-10-01","2009-06-30",null,"X","SL_MDD2","Hrs",1288,null,129417.36006502909,null,129417.36006502909,null,1288,null,129417.36006502909,null,129417.36006502909,{"$nulls":4},129417.36006502909,1,{"$nulls":10},4,1,"2S"]
["2","04","06","01","","","UNCM_D406","2.04.06.01","XRB40601","LTU/Und/Dump Designers Support II","2009-07-01","2009-07-31",null,"X","SL_MDD2","Hrs",77,null,7736.907395191956,null,7736.907395191956,null,77,null,7736.907395191956,null,7736.907395191956,{"$nulls":4},7736.907395191956,1,{"$nulls":10},4,1,"2S"]
["2","04","06","01","","","UNCM_E405","2.04.06.01","XRB40601","LTU/Und/Dump Engr Commissioning Support","2008-10-01","2009-06-30",null,"X","SL_EE2","Hrs",14168,null,1584889.402514502,null,1584889.402514502,null,14168,null,1584889.402514502,null,1584889.402514502,{"$nulls":4},1584889.402514502,1,{"$nulls":10},4,1,"2S"]
["2","04","06","01","","","UNCM_E406","2.04.06.01","XRB40601","LTU/Und/Dump Engr Commissioning Support II","2009-07-01","2009-07-31",null,"X","SL_EE2","Hrs",847,null,94748.82297641043,null,94748.82297641043,null,847,null,94748.82297641043,null,94748.82297641043,{"$nulls":4},94748.82297641043,1,{"$nulls":10},4,1,"2S"]
["2","04","06","01","","","UNCM_M405","2.04.06.01","XRB40601","Metrology - Maintenance I","2008-10-01","2009-05-29",null,"X","SL_MES2","Hrs",5670,null,546304.6691250111,null,546304.6691250111,null,5670,null,546304.6691250111,null,546304.6691250111,{"$nulls":4},546304.6691250111,1,{"$nulls":10},4,1,"2S"]
["2","04","06","01","","","UNCM_M410","2.04.06.01","XRB40601","Metrology - Maintenance II","2009-06-01","2009-06-30",null,"X","SL_MES2","Hrs",308,null,29675.80918703764,null,29675.80918703764,null,308,null,29675.80918703764,null,29675.80918703764,{"$nulls":4},29675.80918703764,1,{"$nulls":10},4,1,"2S"]
["2","04","06","01","","","UNCM_M411","2.04.06.01","XRB40601","Metrology - Maintenance III","2009-07-01","2009-07-31",null,"X","SL_MES2","Hrs",154,null,14837.90459351882,null,14837.90459351882,null,154,null,14837.90459351882,null,14837.90459351882,{"$nulls":4},14837.90459351882,1,{"$nulls":10},4,1,"2S"]
["2","04","06","01","","","UNCM_M415","2.04.06.01","XRB40601","CTL - Maintenance I","2008-10-01","2009-05-29",null,"X","SL_CCA2","Hrs",5670,null,447890.4623867525,null,447890.4623867525,null,5670,null,447890.4623867525,null,447890.4623867525,{"$nulls":4},447890.4623867525,1,{"$nulls":10},4,1,"2S"]
["2","04","06","01","","","UNCM_M420","2.04.06.01","XRB40601","CTL - Maintenance II","2009-06-01","2009-06-30",null,"X","SL_CCA2","Hrs",462,null,36494.778416698355,null,36494.778416698355,null,462,null,36494.778416698355,null,36494.778416698355,{"$nulls":4},36494.778416698355,1,{"$nulls":10},4,1,"2S"]
["2","04","06","01","","","UNCM_M421","2.04.06.01","XRB40601","CTL - Maintenance III","2009-07-01","2009-07-31",null,"X","SL_CCA2","Hrs",231,null,18247.389208349177,null,18247.389208349177,null,231,null,18247.389208349177,null,18247.389208349177,{"$nulls":4},18247.389208349177,1,{"$nulls":10},4,1,"2S"]
["2","04","06","01","","","UNCM_M425","2.04.06.01","XRB40601","PCD - Maintenance I","2008-10-01","2009-05-29",null,"X","SL_PCT2","Hrs",2268,null,168415.27959563295,null,168415.27959563295,null,2268,null,168415.27959563295,null,168415.27959563295,{"$nulls":4},168415.27959563295,1,{"$nulls":10},4,1,"2S"]
["2","04","06","01","","","UNCM_M430","2.04.06.01","XRB40601","PCD - Maintenance II","2009-06-01","2009-06-30",null,"X","SL_PCT2","Hrs",154,null,11435.605404641743,null,11435.605404641743,null,154,null,11435.605404641743,null,11435.605404641743,{"$nulls":4},11435.605404641743,1,{"$nulls":10},4,1,"2S"]
["2","04","06","01","","","UNCM_M431","2.04.06.01","XRB40601","PCD - Maintenance III","2009-07-01","2009-07-31",null,"X","SL_PCT2","Hrs",77,null,5717.8027023208715,null,5717.8027023208715,null,77,null,5717.8027023208715,null,5717.8027023208715,{"$nulls":4},5717.8027023208715,1,{"$nulls":10},4,1,"2S"]
["2","04","06","01","","","UNCM_M435","2.04.06.01","XRB40601","MFD - Maintenance I","2008-10-01","2009-05-29",null,"X","SL_MFAT2","Hrs",4536,null,469112.5003824,null,469112.5003824,null,4536,null,469112.5003824,null,469112.5003824,{"$nulls":4},469112.5003824,1,{"$nulls":10},4,1,"2S"]
["2","04","06","01","","","UNCM_M440","2.04.06.01","XRB40601","MFD - Maintenance II","2009-06-01","2009-06-30",null,"X","SL_MFAT2","Hrs",154,null,15926.658963599999,null,15926.658963599999,null,154,null,15926.658963599999,null,15926.658963599999,{"$nulls":4},15926.658963599999,1,{"$nulls":10},4,1,"2S"]
["2","04","06","01","","","UNCM_M441","2.04.06.01","XRB40601","MFD - Maintenance III","2009-07-01","2009-07-31",null,"X","SL_MFAT2","Hrs",77,null,7963.3294817999995,null,7963.3294817999995,null,77,null,7963.3294817999995,null,7963.3294817999995,{"$nulls":4},7963.3294817999995,1,{"$nulls":10},4,1,"2S"]
["2","04","06","01","","","UNCM_M445","2.04.06.01","XRB40601","CEF - Maintenance II","2008-10-01","2009-06-30",null,"X","SL_SEPM2","Hrs",386,null,29068.500718155403,null,29068.500718155403,null,386,null,29068.500718155403,null,29068.500718155403,{"$nulls":4},29068.500718155403,1,{"$nulls":10},4,1,"2S"]
["2","04","06","01","","","UNCM_M446","2.04.06.01","XRB40601","CEF - Maintenance III","2009-07-01","2009-07-31",null,"X","SL_SEPM2","Hrs",23,null,1732.0609236206585,null,1732.0609236206585,null,23,null,1732.0609236206585,null,1732.0609236206585,{"$nulls":4},1732.0609236206585,1,{"$nulls":10},4,1,"2S"]
["2","04","06","01","","","UNCM_M450","2.04.06.01","XRB40601","M&S - Maintenance","2008-10-01","2009-07-31",null,"X","SL_MSEQ2","$$",null,500000,null,564848.0324,564848.0324,null,null,500000,null,564848.0324,564848.0324,{"$nulls":4},564848.0324,1,{"$nulls":10},4,1,"2S"]
["2","04","06","01","","","UNUN_00050","2.04.06.01","XRB40601","Support Commissioning - ANL","2007-10-02","2008-10-01",null,"X","AN_CE2","Hrs",875,null,101369.58734326348,null,101369.58734326348,null,875,null,101369.58734326348,null,101369.58734326348,null,null,101369.58734326348,1,0,0,{"$nulls":10},4,5,"4A"]
["2","05","  ","  ","  ","  ",null,null,null,"X-RAY TRANSPORT & DIAGNOSTICS SYSTEMS (OPC)                 ",{"$nulls":6},3124,955000,613549.8703413433,1112198.9565,1725748.8268413434,null,3124,955000,613549.8703413433,1112198.9565,1725748.8268413434,276018.8160548077,null,337531.0542865356,null,0,null,1112198.9565,null,0,null,0,null,null,0]
["2","05","01","  ","  ","  ",null,null,null,"System Management & Integration                             ",{"$nulls":37},"Donn McMahon"]
["2","05","01","01","  ","  ",null,null,null,"Management                                                  ",{"$nulls":37},"Donn McMahon"]
["2","05","02","  ","  ","  ",null,null,null,"Controls                                                    ",{"$nulls":37},"Gunter Haller"]
["2","05","02","01","  ","  ",null,null,null,"Controls - EPICS                                            ",{"$nulls":37},"Gunter Haller"]
["2","05","02","02","  ","  ",null,null,null,"Controls - System                                           ",{"$nulls":37},"Gunter Haller"]
["2","05","03","  ","  ","  ",null,null,null,"Mechanical & Vacuum Subsystem                               ",{"$nulls":37},"Donn McMahon"]
["2","05","03","01","  ","  ",null,null,null,"Vacuum Systems Engineering                                  ",{"$nulls":37},"Donn McMahon"]
["2","05","03","02","  ","  ",null,null,null,"Mech/Vac Front End                                          ",{"$nulls":37},"Donn McMahon"]
["2","05","03","03","  ","  ",null,null,null,"Mech/Vac Near Hall                                          ",{"$nulls":37},"Donn McMahon"]
["2","05","03","04","  ","  ",null,null,null,"Mech/Vac Tunnel                                             ",{"$nulls":37},"Donn McMahon"]
["2","05","03","05","  ","  ",null,null,null,"Mech/Vac Far Hall                                           ",{"$nulls":37},"Donn McMahon"]
["2","05","04","  ","  ","  ",null,null,null,"Optical Subsystem                                           ",{"$nulls":6},0,905000,0,1051414.08,1051414.08,null,0,905000,0,1051414.08,1051414.08,0,null,0,null,0,null,1051414.08,null,0,null,0,null,null,0,{"$nulls":6},"Donn McMahon"]
["2","05","04","01","  ","  ",null,null,null,"Optical Systems Engineering                                 ",{"$nulls":37},"Donn McMahon"]
["2","05","04","02","  ","  ",null,null,null,"Facility Optics                                             ",{"$nulls":6},0,905000,0,1051414.08,1051414.08,null,0,905000,0,1051414.08,1051414.08,0,null,0,null,0,null,1051414.08,null,0,null,0,null,null,0,{"$nulls":6},"Donn McMahon"]
["2","05","04","02","","","XT2420010","2.05.04.02","SKZ50402","Procure Spares - Part 2","2009-10-01","2009-12-23",null,"S","LL_MSXX2","$$",null,405000,null,443565.315,443565.315,null,null,405000,null,443565.315,443565.315,{"$nulls":6},443565.315,1,{"$nulls":8},4,3,"5A"]
["2","05","04","02","","","XT2420010","2.05.04.02","SKZ50402","Procure Spares - Part 2","2009-10-01","2009-12-23",null,"S","LL_MSCS2","$$",null,95000,null,115491.26535000002,115491.26535000002,null,null,95000,null,115491.26535000002,115491.26535000002,{"$nulls":6},115491.26535000002,1,{"$nulls":8},4,3,"5A"]
["2","05","04","02","","","XT_546","2.05.04.02","SKZ50402","Procure Spares - Part 1","2009-10-01","2009-12-23",null,"S","LL_MSCS2","$$",null,405000,null,492357.49965000007,492357.49965000007,null,null,405000,null,492357.49965000007,492357.49965000007,{"$nulls":6},492357.49965000007,1,{"$nulls":8},4,3,"5A"]
["2","05","04","03","  ","  ",null,null,null,"End Station Optics                                          ",{"$nulls":37},"Donn McMahon"]
["2","05","04","04","  ","  ",null,null,null,"Crystals & Gratings                                         ",{"$nulls":37},"Donn McMahon"]
["2","05","05","  ","  ","  ",null,null,null,"Diagnostics Subsystem                                       ",{"$nulls":6},3124,50000,613549.8703413433,60784.876500000006,674334.7468413434,null,3124,50000,613549.8703413433,60784.876500000006,674334.7468413434,276018.8160548077,null,337531.0542865356,null,0,null,60784.876500000006,null,0,null,0,null,null,0,{"$nulls":6},"Donn McMahon"]
["2","05","05","01","  ","  ",null,null,null,"Diagnostic Systems Engineering                              ",{"$nulls":37},"Donn McMahon"]
["2","05","05","02","  ","  ",null,null,null,"Modeling & Simulation                                       ",{"$nulls":6},3124,0,613549.8703413433,0,613549.8703413433,null,3124,0,613549.8703413433,0,613549.8703413433,276018.8160548077,null,337531.0542865356,null,0,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Donn McMahon"]
["2","05","05","02","","","XT_6501","2.05.05.02","XKZ50502","Modeling & Simulation - FY07","2007-05-01","2007-09-28",null,"X","LL_CP2","Hrs",1423,null,276018.8160548077,null,276018.8160548077,null,1423,null,276018.8160548077,null,276018.8160548077,276018.8160548077,1,{"$nulls":14},4,2,"5A"]
["2","05","05","02","","","XT_6502","2.05.05.02","XKZ50502","Modeling & Simulation - FY-08","2007-10-01","2008-09-30",null,"X","LL_CP2","Hrs",1701,null,337531.0542865356,null,337531.0542865356,null,1701,null,337531.0542865356,null,337531.0542865356,null,null,337531.0542865356,1,{"$nulls":12},4,2,"5A"]
["2","05","05","03","  ","  ",null,null,null,"Facility Diagnostics                                        ",{"$nulls":6},0,50000,0,60784.876500000006,60784.876500000006,null,0,50000,0,60784.876500000006,60784.876500000006,0,null,0,null,0,null,60784.876500000006,null,0,null,0,null,null,0,{"$nulls":6},"Donn McMahon"]
["2","05","05","03","","","XT_4436","2.05.05.03","SKZ50503","Procure Spares - Direct Imager","2009-10-01","2009-12-23",null,"S","LL_MSCS2","$$",null,50000,null,60784.876500000006,60784.876500000006,null,null,50000,null,60784.876500000006,60784.876500000006,{"$nulls":6},60784.876500000006,1,{"$nulls":8},4,3,"5A"]
["2","05","05","04","  ","  ",null,null,null,"Commissioning Diagnostics                                   ",{"$nulls":37},"Donn McMahon"]
["2","05","06","  ","  ","  ",null,null,null,"X-Ray Transport & Diag. System Commissioning                "]
["2","05","06","01","  ","  ",null,null,null,"X-Ray Transport & Diag. System Commissioning                "]
["2","06","  ","  ","  ","  ",null,null,null,"X-RAY END STATION SYSTEMS (OPC)                             ",{"$nulls":6},33906,3234053,4410953.045424036,3587060.526306443,7998013.57173048,null,33906,3234053,4410953.045424036,3587060.526306443,7998013.57173048,727827.7672670796,null,2359594.257222517,null,2723735.0552290757,null,2186856.492011807,null,0,null,0,null,null,0]
["2","06","01","  ","  ","  ",null,null,null,"XE System Mgmt & Integration                                ",{"$nulls":6},32866,65585,4297409.534913096,91521.8137232616,4388931.348636357,null,32866,65585,4297409.534913096,91521.8137232616,4388931.348636357,0,null,0,null,2415892.8775710757,null,1973038.4710652821,null,0,null,0,null,null,0,{"$nulls":6},"Stefan Moeller"]
["2","06","01","","","","XE2100100","2.06.01","XAZ601","LLNL Commissioning Team - Nov08 thru Jun09","2008-11-03","2009-06-30","L","X","LL_PHSS2","Hrs",1210,null,269921.6846086539,null,269921.6846086539,null,1210,null,269921.6846086539,null,269921.6846086539,{"$nulls":4},269921.6846086539,1,{"$nulls":11},1,"2T"]
["2","06","01","","","","XE2100100","2.06.01","XAZ601","LLNL Commissioning Team - Nov08 thru Jun09","2008-11-03","2009-06-30","L","X","LL_ME2","Hrs",605,null,114382.27215472115,null,114382.27215472115,null,605,null,114382.27215472115,null,114382.27215472115,{"$nulls":4},114382.27215472115,1,{"$nulls":11},1,"2T"]
["2","06","01","","","","XE2100100","2.06.01","XAZ601","LLNL Commissioning Team - Nov08 thru Jun09","2008-11-03","2009-06-30","L","X","LL_MDD2","Hrs",1210,null,209872.51758835578,null,209872.51758835578,null,1210,null,209872.51758835578,null,209872.51758835578,{"$nulls":4},209872.51758835578,1,{"$nulls":11},1,"2T"]
["2","06","01","","","","XE2100100","2.06.01","XAZ601","LLNL Commissioning Team - Nov08 thru Jun09","2008-11-03","2009-06-30","L","X","LL_EE2","Hrs",605,null,114382.27215472115,null,114382.27215472115,null,605,null,114382.27215472115,null,114382.27215472115,{"$nulls":4},114382.27215472115,1,{"$nulls":11},1,"2T"]
["2","06","01","","","","XE2100100","2.06.01","XAZ601","LLNL Commissioning Team - Nov08 thru Jun09","2008-11-03","2009-06-30","L","X","LL_CE2","Hrs",1210,null,228764.5443094423,null,228764.5443094423,null,1210,null,228764.5443094423,null,228764.5443094423,{"$nulls":4},228764.5443094423,1,{"$nulls":11},1,"2T"]
["2","06","01","","","","XE2100200","2.06.01","XAZ601","SLAC Commissioning Team - Nov08 thru Jun09","2008-11-03","2009-06-30","L","X","SL_OE2","Hrs",1210,null,164120.26121997627,null,164120.26121997627,null,1210,null,164120.26121997627,null,164120.26121997627,{"$nulls":4},164120.26121997627,1,{"$nulls":11},1,"2T"]
["2","06","01","","","","XE2100200","2.06.01","XAZ601","SLAC Commissioning Team - Nov08 thru Jun09","2008-11-03","2009-06-30","L","X","SL_ME2","Hrs",1210,null,145009.59440781185,null,145009.59440781185,null,1210,null,145009.59440781185,null,145009.59440781185,{"$nulls":4},145009.59440781185,1,{"$nulls":11},1,"2T"]
["2","06","01","","","","XE2100200","2.06.01","XAZ601","SLAC Commissioning Team - Nov08 thru Jun09","2008-11-03","2009-06-30","L","X","SL_EE2","Hrs",1210,null,135355.46139487205,null,135355.46139487205,null,1210,null,135355.46139487205,null,135355.46139487205,{"$nulls":4},135355.46139487205,1,{"$nulls":11},1,"2T"]
["2","06","01","","","","XE2100200","2.06.01","XAZ601","SLAC Commissioning Team - Nov08 thru Jun09","2008-11-03","2009-06-30","L","X","SL_CP2","Hrs",1210,null,119660.43813406937,null,119660.43813406937,null,1210,null,119660.43813406937,null,119660.43813406937,{"$nulls":4},119660.43813406937,1,{"$nulls":11},1,"2T"]
["2","06","01","","","","XE2100200","2.06.01","XAZ601","SLAC Commissioning Team - Nov08 thru Jun09","2008-11-03","2009-06-30","L","X","SL_CE2","Hrs",1210,null,164120.26121997627,null,164120.26121997627,null,1210,null,164120.26121997627,null,164120.26121997627,{"$nulls":4},164120.26121997627,1,{"$nulls":11},1,"2T"]
["2","06","01","","","","XE2100210","2.06.01","XAZ601","SLAC Commissioning Team - Jul09 thru Aug09","2009-07-01","2009-08-31","L","X","SL_PHS2","Hrs",310,null,27207.10212737574,null,27207.10212737574,null,310,null,27207.10212737574,null,27207.10212737574,{"$nulls":4},27207.10212737574,1,{"$nulls":11},1,"2T"]
["2","06","01","","","","XE2100210","2.06.01","XAZ601","SLAC Commissioning Team - Jul09 thru Aug09","2009-07-01","2009-08-31","L","X","SL_OE2","Hrs",310,null,42047.33965139888,null,42047.33965139888,null,310,null,42047.33965139888,null,42047.33965139888,{"$nulls":4},42047.33965139888,1,{"$nulls":11},1,"2T"]
["2","06","01","","","","XE2100210","2.06.01","XAZ601","SLAC Commissioning Team - Jul09 thru Aug09","2009-07-01","2009-08-31","L","X","SL_MFAT2","Hrs",310,null,32060.157654,null,32060.157654,null,310,null,32060.157654,null,32060.157654,{"$nulls":4},32060.157654,1,{"$nulls":11},1,"2T"]
["2","06","01","","","","XE2100210","2.06.01","XAZ601","SLAC Commissioning Team - Jul09 thru Aug09","2009-07-01","2009-08-31","L","X","SL_ME2","Hrs",310,null,37151.21840200138,null,37151.21840200138,null,310,null,37151.21840200138,null,37151.21840200138,{"$nulls":4},37151.21840200138,1,{"$nulls":11},1,"2T"]
["2","06","01","","","","XE2100210","2.06.01","XAZ601","SLAC Commissioning Team - Jul09 thru Aug09","2009-07-01","2009-08-31","L","X","SL_EE2","Hrs",310,null,34677.845481330856,null,34677.845481330856,null,310,null,34677.845481330856,null,34677.845481330856,{"$nulls":4},34677.845481330856,1,{"$nulls":11},1,"2T"]
["2","06","01","","","","XE2100210","2.06.01","XAZ601","SLAC Commissioning Team - Jul09 thru Aug09","2009-07-01","2009-08-31","L","X","SL_CP2","Hrs",619,null,61214.72000412309,null,61214.72000412309,null,619,null,61214.72000412309,null,61214.72000412309,{"$nulls":4},61214.72000412309,1,{"$nulls":11},1,"2T"]
["2","06","01","","","","XE2100210","2.06.01","XAZ601","SLAC Commissioning Team - Jul09 thru Aug09","2009-07-01","2009-08-31","L","X","SL_CE2","Hrs",619,null,83959.0427232771,null,83959.0427232771,null,619,null,83959.0427232771,null,83959.0427232771,{"$nulls":4},83959.0427232771,1,{"$nulls":11},1,"2T"]
["2","06","01","","","","XE2100220","2.06.01","XAZ601","SLAC Commissioning Team - Oct09 thru May10","2009-10-01","2010-05-31","L","X","SL_PHS2","Hrs",1231,null,110523.43347588077,null,110523.43347588077,null,1231,null,110523.43347588077,null,110523.43347588077,{"$nulls":6},110523.43347588077,1,{"$nulls":9},1,"2T"]
["2","06","01","","","","XE2100220","2.06.01","XAZ601","SLAC Commissioning Team - Oct09 thru May10","2009-10-01","2010-05-31","L","X","SL_OE2","Hrs",1231,null,170808.94264454299,null,170808.94264454299,null,1231,null,170808.94264454299,null,170808.94264454299,{"$nulls":6},170808.94264454299,1,{"$nulls":9},1,"2T"]
["2","06","01","","","","XE2100220","2.06.01","XAZ601","SLAC Commissioning Team - Oct09 thru May10","2009-10-01","2010-05-31","L","X","SL_MFAT2","Hrs",1231,null,130238.00495579999,null,130238.00495579999,null,1231,null,130238.00495579999,null,130238.00495579999,{"$nulls":6},130238.00495579999,1,{"$nulls":9},1,"2T"]
["2","06","01","","","","XE2100220","2.06.01","XAZ601","SLAC Commissioning Team - Oct09 thru May10","2009-10-01","2010-05-31","L","X","SL_ME2","Hrs",1231,null,150919.42524338103,null,150919.42524338103,null,1231,null,150919.42524338103,null,150919.42524338103,{"$nulls":6},150919.42524338103,1,{"$nulls":9},1,"2T"]
["2","06","01","","","","XE2100220","2.06.01","XAZ601","SLAC Commissioning Team - Oct09 thru May10","2009-10-01","2010-05-31","L","X","SL_EE2","Hrs",1231,null,140871.84038193736,null,140871.84038193736,null,1231,null,140871.84038193736,null,140871.84038193736,{"$nulls":6},140871.84038193736,1,{"$nulls":9},1,"2T"]
["2","06","01","","","","XE2100220","2.06.01","XAZ601","SLAC Commissioning Team - Oct09 thru May10","2009-10-01","2010-05-31","L","X","SL_CP2","Hrs",2462,null,249074.34051263082,null,249074.34051263082,null,2462,null,249074.34051263082,null,249074.34051263082,{"$nulls":6},249074.34051263082,1,{"$nulls":9},1,"2T"]
["2","06","01","","","","XE2100220","2.06.01","XAZ601","SLAC Commissioning Team - Oct09 thru May10","2009-10-01","2010-05-31","L","X","SL_CE2","Hrs",2462,null,341617.88528908597,null,341617.88528908597,null,2462,null,341617.88528908597,null,341617.88528908597,{"$nulls":6},341617.88528908597,1,{"$nulls":9},1,"2T"]
["2","06","01","","","","XE2320000","2.06.01","XAZ601","Laser Management Nov08 thru Aug09","2008-10-29","2009-08-26","S","X","SL_PHPU2","Hrs",760,null,112285.81151689187,null,112285.81151689187,null,760,null,112285.81151689187,null,112285.81151689187,{"$nulls":4},112285.81151689187,1,{"$nulls":11},1,"2T"]
["2","06","01","","","","XE2320010","2.06.01","XAZ601","Laser Management Oct09 thru May10","2009-10-01","2010-05-31","S","X","SL_PHPU2","Hrs",1231,null,186056.59335533038,null,186056.59335533038,null,1231,null,186056.59335533038,null,186056.59335533038,{"$nulls":6},186056.59335533038,1,{"$nulls":9},1,"2T"]
["2","06","01","","","","XE2330000","2.06.01","XAZ601","AMO Exp. Management - Nov08 thru Aug09","2008-11-03","2009-08-31","S","X","SL_PHPU2","Hrs",796,null,117604.61311506043,null,117604.61311506043,null,796,null,117604.61311506043,null,117604.61311506043,{"$nulls":4},117604.61311506043,1,{"$nulls":11},1,"2T"]
["2","06","01","","","","XE2330010","2.06.01","XAZ601","AMO Exp. Management - Oct09 thru May10","2009-10-01","2010-05-31","S","X","SL_PHPU2","Hrs",1332,null,201322.0002837531,null,201322.0002837531,null,1332,null,201322.0002837531,null,201322.0002837531,{"$nulls":6},201322.0002837531,1,{"$nulls":9},1,"2T"]
["2","06","01","","","","XE2350000","2.06.01","XAZ601","Management X-Ray Detector - Nov08 thru Aug09","2008-11-03","2009-08-31","S","X","SL_PHS2","Hrs",789,null,69246.46315644987,null,69246.46315644987,null,789,null,69246.46315644987,null,69246.46315644987,{"$nulls":4},69246.46315644987,1,{"$nulls":11},1,"2T"]
["2","06","01","","","","XE2350010","2.06.01","XAZ601","Management X-Ray Detector - Oct09 thru May10","2009-10-01","2010-05-31","S","X","SL_PHS2","Hrs",1279,null,114833.0393303424,null,114833.0393303424,null,1279,null,114833.0393303424,null,114833.0393303424,{"$nulls":6},114833.0393303424,1,{"$nulls":9},1,"2T"]
["2","06","01","","","","XE_036","2.06.01","XAZ601","Management & Oversight - Nov08 thru Aug09","2008-11-03","2009-08-31",null,"X","SL_EE2","Hrs",718,null,80318.36469546953,null,80318.36469546953,null,718,null,80318.36469546953,null,80318.36469546953,{"$nulls":4},80318.36469546953,1,{"$nulls":10},4,1,"2T"]
["2","06","01","","","","XE_037","2.06.01","XAZ601","Management & Oversight - Oct09 thru May10","2009-10-01","2010-05-31",null,"X","SL_EE2","Hrs",1204,null,137782.04372043264,null,137782.04372043264,null,1204,null,137782.04372043264,null,137782.04372043264,{"$nulls":6},137782.04372043264,1,{"$nulls":8},4,1,"2T"]
["2","06","01","","","","XE_0491","2.06.01","XAZ601","Travel & Misc Expenses - Nov08 thru Sep09","2008-11-03","2009-09-30",null,"X","SL_MSTR2","$$",null,27228,null,40227.37200936,40227.37200936,null,null,27228,null,40227.37200936,40227.37200936,{"$nulls":4},40227.37200936,1,{"$nulls":10},1,1,"2T"]
["2","06","01","","","","XE_0491","2.06.01","XAZ601","Travel & Misc Expenses - Nov08 thru Sep09","2008-11-03","2009-09-30",null,"X","SL_MSCS2","$$",null,10891,null,12303.519841736801,12303.519841736801,null,null,10891,null,12303.519841736801,12303.519841736801,{"$nulls":4},12303.519841736801,1,{"$nulls":10},1,1,"2T"]
["2","06","01","","","","XE_0492","2.06.01","XAZ601","Travel & Misc Expenses FY-10","2009-10-01","2010-05-31",null,"X","SL_MSTR2","$$",null,20378,null,30799.466925719997,30799.466925719997,null,null,20378,null,30799.466925719997,30799.466925719997,{"$nulls":6},30799.466925719997,1,{"$nulls":8},1,1,"2T"]
["2","06","01","","","","XE_0492","2.06.01","XAZ601","Travel & Misc Expenses FY-10","2009-10-01","2010-05-31",null,"X","SL_MSCS2","$$",null,7088,null,8191.4549464448,8191.4549464448,null,null,7088,null,8191.4549464448,8191.4549464448,{"$nulls":6},8191.4549464448,1,{"$nulls":8},1,1,"2T"]
["2","06","01","01","  ","  ",null,null,null,"Management                                                  ",{"$nulls":37},"Stefan Moeller"]
["2","06","02","  ","  ","  ",null,null,null,"Controls Subsystem                                          ",{"$nulls":6},400,888468,38407.0067164154,975776.5285215816,1014183.5352379968,null,400,888468,38407.0067164154,975776.5285215816,1014183.5352379968,244225.38646707957,null,769958.1487709173,null,0,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Gunter Haller"]
["2","06","02","01","  ","  ",null,null,null,"Cabling                                                     ",{"$nulls":37},"Gunter Haller"]
["2","06","02","02","  ","  ",null,null,null,"Network                                                     ",{"$nulls":37},"Gunter Haller"]
["2","06","02","03","  ","  ",null,null,null,"PC Support                                                  ",{"$nulls":37},"Gunter Haller"]
["2","06","02","04","  ","  ",null,null,null,"Beamline Controls                                           ",{"$nulls":6},0,888468,0,975776.5285215816,975776.5285215816,null,0,888468,0,975776.5285215816,975776.5285215816,232885.85097359997,null,742890.6775479816,null,0,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Gunter Haller"]
["2","06","02","04","","","XE2240010","2.06.02.04","RCA60204","Development of LBL Laser Timing System","2007-05-01","2007-09-28",null,"R","SL_MSSC2","$$",null,215741,null,232885.85097359997,232885.85097359997,null,null,215741,null,232885.85097359997,232885.85097359997,232885.85097359997,1,{"$nulls":14},5,2,"2H"]
["2","06","02","04","","","XE2240020","2.06.02.04","RCA60204","LBL Timing Procurement (FY08)","2007-10-01","2008-09-30",null,"R","SL_MSSC2","$$",null,672727,null,742890.6775479816,742890.6775479816,null,null,672727,null,742890.6775479816,742890.6775479816,null,null,742890.6775479816,1,{"$nulls":13},2,"2H"]
["2","06","02","05","  ","  ",null,null,null,"X-Ray PPS                                                   ",{"$nulls":37},"Gunter Haller"]
["2","06","02","06","  ","  ",null,null,null,"X-Ray MPS                                                   ",{"$nulls":37},"Gunter Haller"]
["2","06","02","07","  ","  ",null,null,null,"Laser PPS                                                   ",{"$nulls":37},"Gunter Haller"]
["2","06","02","08","  ","  ",null,null,null,"R&D: 2D X-Ray Detector Controls                             ",{"$nulls":6},400,0,38407.0067164154,0,38407.0067164154,null,400,0,38407.0067164154,0,38407.0067164154,11339.5354934796,null,27067.471222935805,null,0,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Gunter Haller"]
["2","06","02","08","","","XE628_0105","2.06.02.08","RBB60208","Support Design of EPICS Interface","2007-05-01","2007-07-25","S","R","SL_CP2","Hrs",80,null,7559.690328986399,null,7559.690328986399,null,80,null,7559.690328986399,null,7559.690328986399,7559.690328986399,1,{"$nulls":14},5,2,"2H","B. Dalesio"]
["2","06","02","08","","","XE628_0115","2.06.02.08","RBB60208","Support Integration with Data Farm","2007-07-27","2007-08-23","S","R","SL_CP2","Hrs",40,null,3779.8451644931997,null,3779.8451644931997,null,40,null,3779.8451644931997,null,3779.8451644931997,3779.8451644931997,1,{"$nulls":14},5,2,"2H","B. Dalesio"]
["2","06","02","08","","","XE628_0130","2.06.02.08","RBB60208","Support Development of Control System","2007-10-29","2008-02-08","S","R","SL_CP2","Hrs",120,null,11600.34480982963,null,11600.34480982963,null,120,null,11600.34480982963,null,11600.34480982963,null,null,11600.34480982963,1,{"$nulls":12},5,2,"2H","B. Dalesio"]
["2","06","02","08","","","XE628_0135","2.06.02.08","RBB60208","Prototype Development Support","2007-10-29","2008-02-08","S","R","SL_CP2","Hrs",40,null,3866.781603276543,null,3866.781603276543,null,40,null,3866.781603276543,null,3866.781603276543,null,null,3866.781603276543,1,{"$nulls":12},5,3,"2H","B. Dalesio"]
["2","06","02","08","","","XE628_0145","2.06.02.08","RBB60208","Support for delivery of 2D Detector","2008-02-11","2008-06-03","S","R","SL_CP2","Hrs",120,null,11600.34480982963,null,11600.34480982963,null,120,null,11600.34480982963,null,11600.34480982963,null,null,11600.34480982963,1,{"$nulls":12},5,3,"2H","B. Dalesio"]
["2","06","03","  ","  ","  ",null,null,null,"Commissioning                                               "]
["2","06","03","01","  ","  ",null,null,null,"Commissioning - Controls                                    "]
["2","06","03","02","  ","  ",null,null,null,"Commissioning - XES Laser                                   "]
["2","06","03","03","  ","  ",null,null,null,"Commissioning - AMO Experiment                              "]
["2","06","03","05","  ","  ",null,null,null,"Commissioning - 2D X-Ray Detector                           "]
["2","06","04","  ","  ","  ",null,null,null,"Spares                                                      ",{"$nulls":6},640,120000,75136.50379452485,138681.517152,213818.02094652486,null,640,120000,75136.50379452485,138681.517152,213818.02094652486,0,null,0,null,0,null,213818.02094652486,null,0,null,0,null,null,0,{"$nulls":6},"Stefan Moeller"]
["2","06","04","01","  ","  ",null,null,null,"Spares - PPS Stoppers                                       ",{"$nulls":6},640,120000,75136.50379452485,138681.517152,213818.02094652486,null,640,120000,75136.50379452485,138681.517152,213818.02094652486,0,null,0,null,0,null,213818.02094652486,null,0,null,0,null,null,0,{"$nulls":6},"Stefan Moeller"]
["2","06","04","01","","","XE2410050","2.06.04.01","SKA60401","AWARD: - Spare PPS Beam Stop Hardware","2009-10-01","2009-10-01","S","S","SL_AWARD","$$",null,134400,{"$nulls":5},134400,{"$nulls":19},4,3,"6A"]
["2","06","04","01","","","XE2410060","2.06.04.01","SKA60401","Vendor Fab/Ship - Spare PPS Stoppers","2009-10-02","2009-10-29","S","S","SA_MSEQ2","$$",null,120000,null,138681.517152,138681.517152,null,null,120000,null,138681.517152,138681.517152,{"$nulls":6},138681.517152,1,{"$nulls":8},4,3,"6A"]
["2","06","04","01","","","XE2410080","2.06.04.01","SKA60401","Assemble - Spare PPS Beam Stop Hardware (2)","2009-10-30","2010-01-25","S","S","SL_MFMS2","Hrs",160,null,21665.123108255997,null,21665.123108255997,null,160,null,21665.123108255997,null,21665.123108255997,{"$nulls":6},21665.123108255997,1,{"$nulls":8},4,4,"6A"]
["2","06","04","01","","","XE2410080","2.06.04.01","SKA60401","Assemble - Spare PPS Beam Stop Hardware (2)","2009-10-30","2010-01-25","S","S","SL_MFAT2","Hrs",320,null,33855.533376,null,33855.533376,null,320,null,33855.533376,null,33855.533376,{"$nulls":6},33855.533376,1,{"$nulls":8},4,4,"6A"]
["2","06","04","01","","","XE2410080","2.06.04.01","SKA60401","Assemble - Spare PPS Beam Stop Hardware (2)","2009-10-30","2010-01-25","S","S","SL_ME2","Hrs",160,null,19615.84731026886,null,19615.84731026886,null,160,null,19615.84731026886,null,19615.84731026886,{"$nulls":6},19615.84731026886,1,{"$nulls":8},4,4,"6A"]
["2","06","04","02","  ","  ",null,null,null,"Spares -                                                    ",{"$nulls":37},"Stefan Moeller"]
["2","06","04","03","  ","  ",null,null,null,"Spares -                                                    ",{"$nulls":37},"Stefan Moeller"]
["2","06","04","04","  ","  ",null,null,null,"Spares -                                                    ",{"$nulls":37},"Stefan Moeller"]
["2","06","04","05","  ","  ",null,null,null,"Spares -                                                    ",{"$nulls":37},"Stefan Moeller"]
["2","06","05","  ","  ","  ",null,null,null,"X-Ray Detectors                                             ",{"$nulls":6},0,2160000,0,2381080.6669095997,2381080.6669095997,null,0,2160000,0,2381080.6669095997,2381080.6669095997,483602.3807999999,null,1589636.1084516,null,307842.17765800003,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Stefan Moeller"]
["2","06","05","01","  ","  ",null,null,null,"Beam Imaging                                                ",{"$nulls":37},"Stefan Moeller"]
["2","06","05","02","  ","  ",null,null,null,"2-D X-Ray Detector                                          ",{"$nulls":6},0,2160000,0,2381080.6669095997,2381080.6669095997,null,0,2160000,0,2381080.6669095997,2381080.6669095997,483602.3807999999,null,1589636.1084516,null,307842.17765800003,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Stefan Moeller"]
["2","06","05","02","","","XE2520070","2.06.05.02","RAE60502","Cornell Labor/Materials Q1-Q3 CY07","2007-05-01","2007-09-28","S","R","SA_MSSC2","$$",null,321600,null,347157.42335999996,347157.42335999996,null,null,321600,null,347157.42335999996,347157.42335999996,347157.42335999996,1,{"$nulls":14},5,2,"6A"]
["2","06","05","02","","","XE2520080","2.06.05.02","RAE60502","Cornell Labor/Materials Q4 CY07","2007-10-01","2007-12-27","S","R","SA_MSSC2","$$",null,160000,null,176687.584128,176687.584128,null,null,160000,null,176687.584128,176687.584128,null,null,176687.584128,1,{"$nulls":12},5,2,"6A"]
["2","06","05","02","","","XE2520090","2.06.05.02","RAE60502","Cornell Labor/Materials Q1-Q3 CY08","2008-01-02","2008-09-30","S","R","SA_MSSC2","$$",null,817500,null,902763.125154,902763.125154,null,null,817500,null,902763.125154,902763.125154,null,null,902763.125154,1,{"$nulls":12},5,2,"6A"]
["2","06","05","02","","","XE2520100","2.06.05.02","RAE60502","Cornell Labor/Materials Q4 CY08","2008-10-01","2008-12-31","S","R","SA_MSSC2","$$",null,272500,null,307842.17765800003,307842.17765800003,null,null,272500,null,307842.17765800003,307842.17765800003,{"$nulls":4},307842.17765800003,1,{"$nulls":10},5,2,"6A"]
["2","06","05","02","","","XE2520020","2.06.05.02","RBE60502","AWARD: Cornell Contract - CY07","2007-05-01","2007-05-01","S","R","SL_AWARD","$$",null,628720,null,723300.8016080001,723300.8016080001,null,null,628720,null,723300.8016080001,723300.8016080001,723300.8016080001,1,{"$nulls":14},5,2,"6A"]
["2","06","05","02","","","XE2520030","2.06.05.02","RBE60502","AWARD: Cornell Contract - CY08","2007-11-30","2007-11-30","S","R","SL_AWARD","$$",null,1548975,null,1828324.8653954999,1828324.8653954999,null,null,1548975,null,1828324.8653954999,1828324.8653954999,null,null,1828324.8653954999,1,{"$nulls":12},5,2,"6A"]
["2","06","05","02","01","  ",null,null,null,"Proto 2 ASIC                                                ",{"$nulls":37},"Stefan Moeller"]
["2","06","05","02","02","  ",null,null,null,"Proto 3 ASIC                                                ",{"$nulls":37},"Stefan Moeller"]
["2","06","05","02","03","  ",null,null,null,"Full Lot Prototype                                          ",{"$nulls":6},0,196400,0,213745.775496,213745.775496,null,0,196400,0,213745.775496,213745.775496,136444.95744,null,77300.81805599999,null,0,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Stefan Moeller"]
["2","06","05","02","03","","XE2523100","2.06.05.02","RBE60502","Fabricate Detector Diode","2007-05-01","2007-07-23","S","R","SL_MSSC2","$$",null,46400,null,50087.38944,50087.38944,null,null,46400,null,50087.38944,50087.38944,50087.38944,1,{"$nulls":14},2,2,"6A"]
["2","06","05","02","03","","XE2523170","2.06.05.02","RBE60502","Fabricate Full Lot ASIC","2007-05-01","2007-06-07","S","R","SL_MSSC2","$$",null,80000,null,86357.568,86357.568,null,null,80000,null,86357.568,86357.568,86357.568,1,{"$nulls":14},2,3,"6A"]
["2","06","05","02","03","","XE2523190","2.06.05.02","RBE60502","Bump Bond","2007-10-01","2007-12-07","S","R","SA_MSSC2","$$",null,70000,null,77300.81805599999,77300.81805599999,null,null,70000,null,77300.81805599999,77300.81805599999,null,null,77300.81805599999,1,{"$nulls":12},2,2,"6A"]
["2","06","05","02","04","  ",null,null,null,"500px Detector                                              ",{"$nulls":6},0,392000,0,432884.58111359994,432884.58111359994,null,0,392000,0,432884.58111359994,432884.58111359994,0,null,432884.58111359994,null,0,null,0,null,0,null,0,null,null,0,{"$nulls":6},"Stefan Moeller"]
["2","06","05","02","04","","XE2524030","2.06.05.02","RKE60502","Fabricate Proto 4 ASIC","2007-10-01","2007-11-27","S","R","SA_MSSC2","$$",null,42000,null,46380.4908336,46380.4908336,null,null,42000,null,46380.4908336,46380.4908336,null,null,46380.4908336,1,{"$nulls":12},3,2,"6A"]
["2","06","05","02","04","","XE2524070","2.06.05.02","RKE60502","Fabricate final detector ASIC","2008-04-14","2008-06-09","S","R","SA_MSSC2","$$",null,200000,null,220859.48015999998,220859.48015999998,null,null,200000,null,220859.48015999998,220859.48015999998,null,null,220859.48015999998,1,{"$nulls":12},3,3,"6A"]
["2","06","05","02","04","","XE2524120","2.06.05.02","RKE60502","Fabricate final Detector Diode","2008-03-31","2008-08-19","S","R","SA_MSSC2","$$",null,80000,null,88343.792064,88343.792064,null,null,80000,null,88343.792064,88343.792064,null,null,88343.792064,1,{"$nulls":12},3,2,"6A"]
["2","06","05","02","04","","XE2524140","2.06.05.02","RKE60502","Bump Bond ASIC to final Detector","2008-08-20","2008-09-17","S","R","SA_MSSC2","$$",null,70000,null,77300.81805599999,77300.81805599999,null,null,70000,null,77300.81805599999,77300.81805599999,null,null,77300.81805599999,1,{"$nulls":12},4,3,"6A"]
["2","06","05","02","05","  ",null,null,null,"2D X-Ray Detector Commissioning                             ",{"$nulls":37},"Stefan Moeller"]
["2","06","05","03","  ","  ",null,null,null,"Beam Intensity                                              ",{"$nulls":37},"Stefan Moeller"]
["2","06","05","04","  ","  ",null,null,null,"Streak Camera                                               ",{"$nulls":37},"Stefan Moeller"]
["2","06","07","  ","  ","  ",null,null,null,"Atomic Physics                                              ",{"$nulls":37},"Stefan Moeller"]
["2","06","07","01","  ","  ",null,null,null,"Atomic Physics Samples                                      ",{"$nulls":37},"Stefan Moeller"]
["2","06","07","02","  ","  ",null,null,null,"Atomic Physics Diagnostics                                  ",{"$nulls":37},"Stefan Moeller"]
["2","06","07","03","  ","  ",null,null,null,"Atomic Physics Data Analysis                                ",{"$nulls":37},"Stefan Moeller"]
["2","06","07","04","  ","  ",null,null,null,"Atomic Physics Detectors                                    ",{"$nulls":37},"Stefan Moeller"]
["2","09","  ","  ","  ","  ",null,null,null,"CONVENTIONAL FACILITIES (OPC)                               ",{"$nulls":6},6028,435000,750846.5252055767,459012,1209858.5252055766,null,6028,435000,750846.5252055767,459012,1209858.5252055766,379872,null,829986.5252055767,null,0,null,0,null,0,null,0,null,null,297799.8664757556]
["2","09","01","  ","  ","  ",null,null,null,"MANAGEMENT INTEGRATION                                      ",{"$nulls":37},"David Saenz"]
["2","09","03","  ","  ","  ",null,null,null,"RSY - CLOC Commissioning                                    ",{"$nulls":6},6028,435000,750846.5252055767,459012,1209858.5252055766,null,6028,435000,750846.5252055767,459012,1209858.5252055766,379872,null,829986.5252055767,null,0,null,0,null,0,null,0,null,null,297799.8664757556,{"$nulls":6},"David Saenz"]
["2","09","03","05","  ","  ",null,null,null,"RSY-CLOC Commissioning                                      ",{"$nulls":6},6028,435000,750846.5252055767,459012,1209858.5252055766,null,6028,435000,750846.5252055767,459012,1209858.5252055766,379872,null,829986.5252055767,null,0,null,0,null,0,null,0,null,null,297799.8664757556,{"$nulls":6},"David Saenz"]
["2","09","03","05","","","CF05033040","2.09.03.05","9681319","AWARD: Commissioning Beam Path - FY07","2007-06-04","2007-06-04",null,"X","SL_AWARD","$$",null,341250,null,392585.56837500003,392585.56837500003,null,null,341250,null,392585.56837500003,392585.56837500003,392585.56837500003,1,{"$nulls":10},0.25,98146.39209375001,1.1,1.15,2,3,"9A"]
["2","09","03","05","","","CF05033041","2.09.03.05","9681319","AWARD: Commissioning Beam Path - FY08","2007-10-02","2007-10-02",null,"X","SL_AWARD","$$",null,78750,null,92952.167175,92952.167175,null,null,78750,null,92952.167175,92952.167175,null,null,92952.167175,1,{"$nulls":8},0.25,23238.04179375,1.1,1.15,2,3,"9A"]
["2","09","03","05","","","CF05033045","2.09.03.05","9681319","Commissioning - Beam Path (FY07)","2007-06-05","2007-09-28",null,"X","SA_MSSF2","$$",null,325000,null,342940,342940,null,null,325000,null,342940,342940,342940,1,{"$nulls":10},0.25,85735,1.1,1.15,2,3,"9A"]
["2","09","03","05","","","CF05033085","2.09.03.05","9681319","Commissioning - Beam Path (FY08)","2007-10-02","2008-07-01",null,"X","SA_MSSF2","$$",null,75000,null,79140,79140,null,null,75000,null,79140,79140,null,null,79140,1,{"$nulls":8},0.25,19785,1.1,1.15,2,3,"9A"]
["2","09","03","05","","","CFENG_2020","2.09.03.05","9681319","CF Engineering Support - FY08 (Oct07-Feb08)","2007-10-01","2008-02-29",null,"C","SL_SEEM2","Hrs",1071,null,133403.55482667097,null,133403.55482667097,null,1071,null,133403.55482667097,null,133403.55482667097,null,null,133403.55482667097,1,{"$nulls":8},0.3,40021.066448001286,1.2,1.1,3,1,"9A"]
["2","09","03","05","","","CFENG_2024","2.09.03.05","9681319","CF Engineering Support - FY08 (Oct-nov 07 OPC)","2007-10-01","2007-11-30",null,"C","SL_SEEM2","Hrs",301,null,37492.50233690753,null,37492.50233690753,null,301,null,37492.50233690753,null,37492.50233690753,null,null,37492.50233690753,1,{"$nulls":8},0.3,11247.750701072258,1.2,1.1,3,1,"9A"]
["2","09","03","05","","","CFENG_2034","2.09.03.05","9681319","CF Engineering Support - FY08 (Dec07-Feb08 OPC)","2007-12-03","2008-02-29",null,"C","SL_SEEM2","Hrs",826,null,102886.40176174624,null,102886.40176174624,null,826,null,102886.40176174624,null,102886.40176174624,null,null,102886.40176174624,1,{"$nulls":8},0.3,30865.92052852387,1.2,1.1,3,1,"9A"]
["2","09","03","05","","","CFMGT_1001","2.09.03.05","9681319","AWARD: Dispute Resolution Board - FY07","2007-06-04","2007-06-04",null,"X","SL_AWARD","$$",null,36750,null,42278.445825,42278.445825,null,null,36750,null,42278.445825,42278.445825,42278.445825,1,{"$nulls":10},0.25,10569.61145625,1.1,1.15,6,3,"9A"]
["2","09","03","05","","","CFMGT_1119","2.09.03.05","9681319","Dispute Resolution Board (FY07)","2007-06-05","2007-09-28",null,"X","SA_MSSF2","$$",null,35000,null,36932,36932,null,null,35000,null,36932,36932,36932,1,{"$nulls":10},0.25,9233,1.1,1.15,6,3,"9A"]
["2","09","03","05","","","CFMGT_2135","2.09.03.05","9681319","Management - FY08 (part time OPC)","2008-03-03","2008-09-30",null,"C","SL_SEEM2","Hrs",522,null,65020.21999955391,null,65020.21999955391,null,522,null,65020.21999955391,null,65020.21999955391,null,null,65020.21999955391,1,{"$nulls":8},0.2,13004.043999910784,1.1,1.1,3,1,"9A"]
["2","09","03","05","","","CFUTR_2000","2.09.03.05","9681319","CF OPC Support - FY08","2008-03-03","2008-06-30",null,"X","SL_UTR2","Hrs",1785,null,222339.2580444516,null,222339.2580444516,null,1785,null,222339.2580444516,null,222339.2580444516,null,null,222339.2580444516,1,{"$nulls":8},0.15,33350.888706667734,1,1.15,3,1,"9A"]
["2","09","03","05","","","CFUTR_2060","2.09.03.05","9681319","CF Construction Management-FY08 (Oct-Nov07 OPC)","2007-10-01","2007-11-30",null,"C","SL_UTR2","Hrs",903,null,112477.50701072258,null,112477.50701072258,null,903,null,112477.50701072258,null,112477.50701072258,null,null,112477.50701072258,1,{"$nulls":8},0.3,33743.25210321677,1.2,1.1,3,1,"9A"]
["2","09","03","05","","","CFUTR_2070","2.09.03.05","9681319","CF Construction Management-FY08 (Jan-Feb08 OPC)","2008-01-02","2008-02-29",null,"C","SL_UTR2","Hrs",431,null,53685.277432581875,null,53685.277432581875,null,431,null,53685.277432581875,null,53685.277432581875,null,null,53685.277432581875,1,{"$nulls":8},0.3,16105.583229774562,1.2,1.1,3,1,"9A"]
["2","09","03","05","","","CFUTR_2080","2.09.03.05","9681319","CF Construction Management - FY08 (Dec07 OPC)","2007-12-03","2007-12-27",null,"C","SL_UTR2","Hrs",189,null,23541.803792941933,null,23541.803792941933,null,189,null,23541.803792941933,null,23541.803792941933,null,null,23541.803792941933,1,{"$nulls":8},0.2,4708.3607585883865,1.1,1.1,3,1,"9A"]

{"sheet":"No CT Comparison","index":6,"n_rows":1067,"n_cols":19,"rows_kept":1067,"cut":false,"hidden":true,"merged":[[0,9,0,11],[0,13,0,14],[0,15,0,17],[1,0,1,5],[0,0,0,5],[0,7,0,8]],"flags":["formulas_cached_only"]}
["WBS Level",{"$nulls":5},"April 2007 CR Rebaseline","Budgeted Quantity",null,"Fully Burdened and Escalated Cost",null,null,null,"Work Rem. Bud. Qtty",null,"Work Rem. Full Burd and Escltd Cost"]
["Run Time: 05-03-07 (9:11 am)",{"$nulls":5},"Description","Hours","$$","Labor","M&S","Total (No Conting)",null,"Hours","$$","Labor","M&S","Total"]
["1","2","3","4","5","6"]
[{"$nulls":7},5067,-2792208,1025843.7372397613,10686753.59011974,10750395.905185588,null,52093.818,2356746.58,5480068.180791744,13764340.957457641,19244409.13824938]
["1","  ","  ","  ","  ","  ","LCLS PROJECT - PED & CONSTRUCTION                           ",-2347,-4138895,105997.8717358074,8714944.4506648,8120773.400866912,null,37243.617999999995,766104.85,3730688.3119172053,11537435.502228096,15268123.8141453]
["1","01","  ","  ","  ","  ","LCLS PROJECT MGMT, PLANNING & ADMN (TEC)                    ",8910,-215902,891251.5229233213,-133757.22958791218,1125657.2119505543,null,22103,457488,2137237.1418082328,540825.5916489271,2678062.7334571597]
["1","01","01","  ","  ","  ","Environment, Safety & Health                                ",4493,-185350,417667.8593070612,-150814.69214036522,234509.66558946107,null,8567,-25000,811528.5114796569,-6827.588364425377,804700.9231152317]
["1","01","01","01","  ","  ","Radiation Physics                                           ",3786,0,361190.66794106876,0,361190.66794106876,null,4976,0,472581.9079010687,0,472581.9079010687,1]
["1","01","01","02","  ","  ","ESH Management & Coordination                               ",707,-185350,56477.19136599242,-150459.8772,-93982.68583400769,null,3591,-40000,338946.6035785883,-5109.877199999988,333836.72637858836,1]
["1","01","01","03","  ","  ","Seismic & Engineering Support                               ",0,0,0,-354.8149403652351,-32698.316517599997,null,0,15000,0,-1717.7111644253891,-1717.7111644253891,1]
["1","01","02","  ","  ","  ","Project Management                                          ",6737,-30552,658661.4595193565,17057.462552453042,1076225.3422641894,null,12583,482488,1232994.2467030722,547653.1800133524,1780647.4267164245]
["1","01","02","01","  ","  ","Project Management Office                                   ",6737,-30552,658661.4595193565,17057.462552453042,1076225.3422641894,null,12583,482488,1232994.2467030722,547653.1800133524,1780647.4267164245]
["1","01","02","01","01","  ","Project Office - General                                    ",5736,0,596536.7829994098,0,596536.7829994098,null,10685,0,1115197.3138269256,0,1115197.3138269256,1]
["1","01","02","01","02","  ","Project Support                                             ",1001,182357,62124.67651994666,259995.98610744742,722120.6626273941,null,1898,460997,117796.93287614663,539975.9941074476,657772.9269835942,1]
["1","01","02","01","03","  ","Project Office M&S                                          ",0,-212909,0,-242938.52355499438,-242432.10336261452,null,0,21491,0,7677.185905904858,7677.185905904858,1]
["1","01","02","01","04","  ","SSRL Physics Support                                        ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","01","03","  ","  ","  ","Technical Integration                                       ",-2320,0,-185077.79590309632,0,-185077.79590309632,null,953,0,92714.38362550363,0,92714.38362550363]
["1","01","03","01","  ","  ","Global Laser Coordination                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","01","03","02","  ","  ","Global Alignment Coordination                               ",-595,0,-61580.865653999994,0,-61580.865653999994,null,0,0,0,0,0,1]
["1","01","03","03","  ","  ","System Integration                                          ",-237,0,-17425.396047496353,0,-17425.396047496353,null,953,0,92714.38362550363,0,92714.38362550363,1]
["1","01","03","06","  ","  ","Technical Requirements/Parameters                           ",-1488,0,-106071.53420159998,0,-106071.53420159998,null,0,0,0,0,0,1]
["1","01","04","  ","  ","  ","Education Support                                           ",0,0,0,0,0,null,0,0,0,0,0]
["1","01","04","01","  ","  ","Education/Outreach Travel                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","01","04","02","  ","  ","Education/Outreach M&S                                      ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","  ","  ","  ","  ","INJECTOR SYSTEM                                             ",-60,0,24337.01319074484,65127.329459595916,428084.241140745,null,0,0,-419.84403179789297,2482.5493422311556,2062.705310433288]
["1","02","01","  ","  ","  ","Injector System Management & Integration                    ",0,0,10100.924482843355,928.2926259512169,68999.2014108434,null,0,0,0,0,0]
["1","02","01","01","  ","  ","Injector System Integration                                 ",0,0,4763.0762829250125,0,4763.0762829250125,null,0,0,0,0,0]
["1","02","01","01","01","  ","Injector Region Integration                                 ",0,0,1725.8716934997938,0,1725.8716934997938,null,0,0,0,0,0,1]
["1","02","01","01","02","  ","Gun Area Integration                                        ",0,0,801.5754499405739,0,801.5754499405739,null,0,0,0,0,0,1]
["1","02","01","01","03","  ","Accelerator Area Integration                                ",0,0,712.3073201244042,0,712.3073201244042,null,0,0,0,0,0,1]
["1","02","01","01","04","  ","Heater Area Integration                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","01","01","05","  ","Wall Area Integration                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","01","01","06","  ","Insertion Area Integration                                  ",0,0,442.69150957200327,0,442.69150957200327,null,0,0,0,0,0,1]
["1","02","01","01","07","  ","Spectrometer Area Integration                               ",0,0,485.5475221740053,0,485.5475221740053,null,0,0,0,0,0,1]
["1","02","01","01","08","  ","Drive Laser Integration                                     ",0,0,595.0827876142321,0,595.0827876142321,null,0,0,0,0,0,1]
["1","02","01","04","  ","  ","Injector System Integration Effort / M&S                    ",0,0,5337.848199918342,928.2926259512169,64236.12512791838,null,0,0,0,0,0,1]
["1","02","03","  ","  ","  ","Injector Lasers                                             ",0,0,5314.68927115043,178406.3150309468,294633.0747151504,null,0,0,171.15390958966236,2482.5493422311556,2653.7032518208434]
["1","02","03","01","  ","  ","Drive Laser Support                                         ",0,0,1277.9181483471039,233.55133884297538,15855.326148347114,null,0,0,0,0,0]
["1","02","03","01","01","  ","Drive Laser Support (ANL)                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","03","01","02","  ","Drive Laser Support (LLNL)                                  ",0,0,1277.9181483471039,233.55133884297538,15855.326148347114,null,0,0,0,0,0,1]
["1","02","03","02","  ","  ","Drive Laser System                                          ",0,0,390.13143689520075,164765.16744400002,165155.29888089525,null,0,0,0,0,0,1]
["1","02","03","03","  ","  ","Drive Laser Diagnostics                                     ",0,0,1105.253060240735,7092.998120660486,1105.253060240735,null,0,0,171.15390958966236,2482.5493422311556,2653.7032518208434,1]
["1","02","03","04","  ","  ","Timing Stability Monitoring                                 ",0,0,322.76667244025157,3286.108800000002,3608.875472440239,null,0,0,0,0,0,1]
["1","02","03","05","  ","  ","Steering Stability Feedback & Msmts                         ",0,0,84.01420893429531,443.4611999999979,527.4754089342932,null,0,0,0,0,0,1]
["1","02","03","06","  ","  ","Pre Amp Low Power Comp                                      ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","03","07","  ","  ","Transport to Tunnel & Relay Optics                          ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","03","08","  ","  ","UV Launch, Conditioning & Diagnostics                       ",0,0,836.0795470479352,1665.9643610108178,66113.90354704791,null,0,0,0,0,0,1]
["1","02","03","09","  ","  ","Load Lock Transport System                                  ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","03","10","  ","  ","Visible Optical Transport & Optics                          ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","03","11","  ","  ","LB Infrastructure & LB System Wide Items                    ",0,0,1077.3969250052542,919.063766432475,42045.81292500522,null,0,0,0,0,0,1]
["1","02","03","12","  ","  ","Alignment Laser                                             ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","03","13","  ","  ","Light path to Streak Camera                                 ",0,0,221.1292722396538,0,221.12927223964653,null,0,0,0,0,0,1]
["1","02","03","14","  ","  ","LSR HTR - Beam Conditioning Optics (Laser Bay)              ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","03","15","  ","  ","LSR HTR - Transport Optics (Bay to Tunnel)                  ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","03","16","  ","  ","LSR HTR - Photon Beam Diagnostics                           ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","03","21","  ","  ","UV Conv Harmonic Generation Unit (Closed Account)           ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","04","  ","  ","  ","Injector RF Subsystem                                       ",40,0,10522.887082043046,1471.3919999999996,11994.27908204302,null,0,0,0,0,0]
["1","02","04","01","  ","  ","RF Gun & Load Lock                                          ",0,0,3121.460117392817,1416.8959999999995,4538.356117392792,null,0,0,0,0,0]
["1","02","04","01","01","  ","RF Gun                                                      ",0,0,2328.0423299136164,1008.1759999999995,3336.218329913594,null,0,0,0,0,0,1]
["1","02","04","01","02","  ","RF Gun Supports                                             ",0,0,84.87608500800025,136.24,221.11608500799957,null,0,0,0,0,0,1]
["1","02","04","01","03","  ","Gun Load Lock                                               ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","04","01","04","  ","Gun Load Lock Supports                                      ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","04","01","05","  ","Gun Solenoid                                                ",0,0,337.49605343999974,0,337.49605343999974,null,0,0,0,0,0,1]
["1","02","04","01","06","  ","Gun Solenoid Supports                                       ",0,0,371.0456490312008,272.48,643.5256490311986,null,0,0,0,0,0,1]
["1","02","04","01","07","  ","Gun RF Feed                                                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","04","01","08","  ","Gun RF Feed Supports                                        ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","04","02","  ","  ","Cathode Processing (CP) Station                             ",0,0,0,0,0,null,0,0,0,0,0]
["1","02","04","02","01","  ","CP Cathode Assembly & Supports                              ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","04","02","02","  ","CP Load Lock                                                ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","04","02","03","  ","CP Load Lock Supports                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","04","02","04","  ","CP Station                                                  ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","04","02","05","  ","Cathode Lab Infrastructure                                  ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","04","03","  ","  ","S-Band Low Level Timing                                     ",0,0,0,0,0,null,0,0,0,0,0]
["1","02","04","03","01","  ","Controls Interface & Timing                                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","04","03","02","  ","LLRF Phase Reference System                                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","04","03","03","  ","LLRF Monitor & Control System                               ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","04","03","04","  ","Beam Phase Monitor Cavity                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","04","03","05","  ","RF System S/W Development / Docs                            ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","04","04","  ","  ","S-Band High Power System                                    ",0,0,0,0,0,null,0,0,0,0,0]
["1","02","04","04","01","  ","RF Gun High Power                                           ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","04","04","02","  ","L0 High Power                                               ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","04","04","03","  ","Transverse Cavity High Power                                ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","04","05","  ","  ","Injector RF Waveguide Subsystem                             ",0,0,1863.381702548446,0,1863.381702548446,null,0,0,0,0,0]
["1","02","04","05","01","  ","RF Waveguides                                               ",0,0,1863.381702548446,0,1863.381702548446,null,0,0,0,0,0,1]
["1","02","04","05","02","  ","RF Waveguide Supports                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","04","06","  ","  ","Injector Linac Structures                                   ",40,0,5538.045262101783,54.496000000000095,5592.541262101782,null,0,0,0,0,0]
["1","02","04","06","01","  ","L0A-0B Structure Assembly                                   ",0,0,1576.4857148377778,0,1576.4857148377778,null,0,0,0,0,0,1]
["1","02","04","06","03","  ","Major Linac Support                                         ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","04","06","04","  ","GTL RF Phase Cavity                                         ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","04","06","05","  ","LTDL1 RF Kicker                                             ",40,0,3961.5595472640052,54.496000000000095,4016.0555472640044,null,0,0,0,0,0,1]
["1","02","05","  ","  ","  ","Injector Magnets & Supports                                 ",0,0,2420.147617118408,3619.2628118811904,37552.2516171184,null,0,0,0,0,0]
["1","02","05","01","  ","  ","Injector Dipoles                                            ",0,0,1221.7040203679994,2502.0948118811943,35236.640020367995,null,0,0,0,0,0]
["1","02","05","01","01","  ","Gun Spectrometer Dipole                                     ",0,0,512.6773763279998,948.9588118811953,32974.477376327995,null,0,0,0,0,0,1]
["1","02","05","01","02","  ","DL1 B01 & B02 Dipoles                                       ",0,0,218.4,27.248000000000047,245.64799999999923,null,0,0,0,0,0,1]
["1","02","05","01","03","  ","SAB Spectrometer Dipole                                     ",0,0,490.6266440399995,1525.887999999999,2016.5146440399985,null,0,0,0,0,0,1]
["1","02","05","01","04","  ","Chicane DIPOLES (4)                                         ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","05","02","  ","  ","Injector Quads                                              ",0,0,148.51200000000063,326.97599999999875,475.48799999999983,null,0,0,0,0,0]
["1","02","05","02","01","  ","Gun Spectrometer Quadrupoles                                ",0,0,87.36000000000013,326.97599999999875,414.33599999999933,null,0,0,0,0,0,1]
["1","02","05","02","02","  ","Injector Quadrupoles                                        ",0,0,61.1520000000005,0,61.1520000000005,null,0,0,0,0,0,1]
["1","02","05","02","03","  ","                                                            ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","05","03","  ","  ","Injector Steering Coils                                     ",0,0,267.8164975824038,381.47199999999793,649.2884975824054,null,0,0,0,0,0]
["1","02","05","03","01","  ","Gun Solenoid Correctors                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","05","03","02","  ","Gun Spectrometer Correctors                                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","05","03","03","  ","Injector Correctors - A                                     ",0,0,267.8164975824038,381.47199999999793,649.2884975824054,null,0,0,0,0,0,1]
["1","02","05","03","04","  ","Injector Correctors - D (Gun)                               ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","05","03","05","  ","Gun Solenoid Quadrupole Correctors                          ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","05","04","  ","  ","Linac Solenoid                                              ",0,0,782.1150991680042,408.71999999999935,1190.8350991680054,null,0,0,0,0,0,1]
["1","02","05","05","  ","  ","Injector Laser Heater Subsystem                             ",0,0,0,0,0,null,0,0,0,0,0]
["1","02","05","05","01","  ","System Design & Optimization (LSR HTR)                      ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","05","05","02","  ","Injector Undulator                                          ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","06","  ","  ","  ","Injector Vacuum & Supports                                  ",-100,0,-13138.018083240131,-7372.533430819676,53318.471436759864,null,0,0,0,0,0]
["1","02","06","01","  ","  ","Injector Vacuum Engineering                                 ",0,0,574.6822361280028,0,574.6822361280028,null,0,0,0,0,0,1]
["1","02","06","02","  ","  ","Injector Vacuum Components                                  ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","06","03","  ","  ","Injector Vacuum Special Chambers                            ",-100,0,-13712.700319368134,1738.0650491803244,61854.38768063186,null,0,0,0,0,0,1]
["1","02","06","04","  ","  ","Injector Vacuum Supports Engineering                        ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","06","05","  ","  ","Injector Vacuum Support Components                          ",0,0,0,-9110.59848,-9110.59848,null,0,0,0,0,0,1]
["1","02","06","08","  ","  ","DL1 Vacuum Chamber                                          ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","06","10","  ","  ","DL1TL Vacuum Components                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","07","  ","  ","  ","Injector Diagnostics                                        ",0,0,3145.8320290813463,-171229.45163636364,-103687.63997091865,null,0,0,0,0,0]
["1","02","07","01","  ","  ","Beam Position Monitors                                      ",0,0,421.82226230090237,844.6880000000019,1266.510262300908,null,0,0,0,0,0]
["1","02","07","01","01","  ","Large Aperture BPM                                          ",0,0,421.82226230090237,844.6880000000019,1266.510262300908,null,0,0,0,0,0,1]
["1","02","07","01","02","  ","Small Aperture BPM                                          ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","07","01","06","  ","                                                            ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","07","02","  ","  ","Current Monitors                                            ",0,0,0,2179.84,2179.84,null,0,0,0,0,0]
["1","02","07","02","01","  ","Current Monitors                                            ",0,0,0,2179.84,2179.84,null,0,0,0,0,0,1]
["1","02","07","03","  ","  ","Bunch Length Monitors                                       ",0,0,0,0,0,null,0,0,0,0,0]
["1","02","07","03","01","  ","Bunch Length Monitors                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","07","04","  ","  ","Profile Monitors                                            ",0,0,2273.3372502524435,-174253.97963636363,-107584.66274974757,null,0,0,0,0,0]
["1","02","07","04","01","  ","Profile Monitors                                            ",0,0,2273.3372502524435,-174253.97963636363,-107584.66274974757,null,0,0,0,0,0,1]
["1","02","07","04","03","  ","GS Faraday Cup/YAG2                                         ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","07","04","06","  ","DL1 OTR/YAG                                                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","07","04","07","  ","DL1TL OTR/YAG                                               ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","07","04","08","  ","LTDL1 OTR/YAG (6)                                           ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","07","05","  ","  "," Injector Wire Scanners                                     ",0,0,450.6725165280004,0,450.6725165280004,null,0,0,0,0,0,1]
["1","02","07","06","  ","  ","LSR HTR - Electron Beam Diagnostics                         ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","07","07","  ","  ","PPS Stopper                                                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","17","  ","  ","  ","Injector Installation & Alignment                           ",0,0,5970.550791748385,59304.052058000016,65274.60284974852,null,0,0,-590.9979413875553,0,-590.9979413875553]
["1","02","17","01","  ","  ","Injector Infrastructure Installation                        ",0,0,2759.161645253218,4729.641816000003,7488.803461253236,null,0,0,-590.9979413875553,0,-590.9979413875553,1]
["1","02","17","02","  ","  ","Injector Controls Subsystem Install & Align                 ",0,0,0,26963.77223599999,26963.77223599999,null,0,0,0,0,0,1]
["1","02","17","03","  ","  ","Injector Lasers Install & Align                             ",0,0,2933.8966192224325,21259.31874800002,24193.215367222525,null,0,0,0,0,0,1]
["1","02","17","04","  ","  ","Gun Area Integration                                        ",0,0,719.1808000000165,1155.3323520000013,1874.5131520000214,null,0,0,0,0,0,1]
["1","02","17","06","  ","  ","Accelerator Area Integration                                ",0,0,722.3039999999892,2036.875006000002,2759.1790060000058,null,0,0,0,0,0,1]
["1","02","17","07","  ","  ","Heater Area Integration                                     ",0,0,731.1767272727302,517.4926160000005,1248.6693432727334,null,0,0,0,0,0,1]
["1","02","17","08","  ","  ","Wall Area Integration                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","17","09","  ","  ","Insertion Area Integration                                  ",0,0,-2594.0490000000063,2641.619284000004,47.570284000001266,null,0,0,0,0,0,1]
["1","02","17","11","  ","  ","Spectrometer Area Integration                               ",0,0,698.8800000000047,0,698.8800000000047,null,0,0,0,0,0,1]
["1","02","17","12","  ","  ","Injector RF High Power System Install & Align               ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","17","13","  ","  ","Injector RF Low Level Install & Align                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","17","14","  ","  ","Cathode and Load Lock Install & Align                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","17","15","  ","  ","Injector Laser Heater Subsystem Install & Align             ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","17","17","  ","  ","Power  Conversion Subsystem Installation                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","02","17","18","  ","  ","Cathode Processing Center Installation                      ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","03","  ","  ","  ","  ","LINAC SYSTEM                                                ",260,0,64095.808709811565,-484551.8525244349,-559240.0866714048,null,159.2,0,27968.12481191544,-550110.7385244987,-522142.61371258367]
["1","03","01","  ","  ","  ","System Management & Integration                             ",0,0,8808.236747095136,1895.550753463649,-101872.50642090499,null,0,0,1038.7449615385704,1512.3180983611537,2551.0630598996213]
["1","03","01","01","  ","  ","Linac Mechanical Integration                                ",0,0,3773.229526376592,1511.4007615747978,-157513.97047362354,null,0,0,1021.0490326794825,1511.4007615747978,2532.449794254164]
["1","03","01","01","01","  ","L01 System Integration                                      ",0,0,144.61942284962424,0,144.61942284962424,null,0,0,0,0,0,1]
["1","03","01","01","02","  ","BC1 System Integration                                      ",0,0,174.75421178866236,0,174.75421178866236,null,0,0,0,0,0,1]
["1","03","01","01","03","  ","L02 System Integration                                      ",0,0,34.175138812555815,0,34.175138812555815,null,0,0,-16.20140189563972,0,-16.20140189563972,1]
["1","03","01","01","04","  ","BC2 System Integration                                      ",0,0,655.7829414364533,0,655.7829414364533,null,0,0,213.50943502181326,0,213.50943502181326,1]
["1","03","01","01","05","  ","L03 System Integration                                      ",0,0,108.76007013994968,0,108.76007013994968,null,0,0,44.60362924374931,0,44.60362924374931,1]
["1","03","01","01","06","  ","LTU System Integration                                      ",0,0,1261.0507074058405,1016.1093600000022,-79382.5492925942,null,0,0,454.43671030533733,1016.1093600000022,1470.5460703052813,1]
["1","03","01","01","07","  ","E-Dump System Integration                                   ",0,0,1394.087033943506,495.2914015747956,-79249.51296605659,null,0,0,324.7006600042223,495.2914015747956,819.9920615789597,1]
["1","03","01","03","  ","  ","Travel                                                      ",0,0,0,123.39775280898903,29548.8,null,0,0,0,0,0,1]
["1","03","01","04","  ","  ","Linac Management                                            ",0,0,5035.007220718544,260.7522390798622,26092.664052718552,null,0,0,17.69592885908787,0.9173367863559179,18.61326564545743,1]
["1","03","03","  ","  ","  ","Linac Magnets & Supports                                    ",0,0,1915.8320988121814,-426443.30736000004,-429903.71526118775,null,0,0,898.3233445906462,-429004.455872,-428106.13252740935]
["1","03","03","01","  ","  ","Bend Magnet (BX1_BC1)                                       ",0,0,250.57113653391934,1208.4487999999983,1459.0199365339213,null,0,0,0,0,0,1]
["1","03","03","02","  ","  ","Bend Magnet (BX3_LTU)                                       ",0,0,89.6313599999994,-26602.17759999998,-26512.54623999998,null,0,0,89.6313599999994,-26602.177599999995,-26512.54623999998,1]
["1","03","03","03","  ","  ","Bend Magnet (BX2_BC2)                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","03","03","04","  ","  ","Bend Magnet (BY_LTU)                                        ",0,0,89.6313599999994,0,-5286.608640000006,null,0,0,89.6313599999994,0,89.6313599999994,1]
["1","03","03","05","  ","  ","Quad Magnet (Quad_LTU)                                      ",0,0,0,-409000,-409000,null,0,0,0,-409000,-409000,1]
["1","03","03","07","  ","  ","Quad Magnet (QE_BC1/BC2)                                    ",0,0,439.1631413627583,1352.6997119999942,1791.8628533627489,null,0,0,0,0,0,1]
["1","03","03","08","  ","  ","Corrector Magnet (Type 4_LTU/E-Dump)                        ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","03","03","09","  ","  ","Bend Magnet (BYD_E-Dump)                                    ",0,0,347.77150563211035,5591.289599999989,5939.061105632107,null,0,0,68.48772826979075,5591.289599999989,5659.77732826976,1]
["1","03","03","10","  ","  ","Quad Magnet (E-Dump)                                        ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","03","03","11","  ","  ","Bend Magnet (BYPM_LTU)                                      ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","03","03","12","  ","  ","Bend Magnet (BYKIK_LTU)                                     ",0,0,-42.51118602931092,0,-42.51118602931092,null,0,0,-40.3856267278461,0,-40.3856267278461,1]
["1","03","03","13","  ","  ","Bend Magnet (BYW_LTU)                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","03","03","14","  ","  ","BXKIK LINAC TCAV Screen Kicker                              ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","03","03","15","  ","  ","Muon Toroid (E-Dump)                                        ",0,0,741.5747813127055,1006.4321280000004,1748.0069093127095,null,0,0,690.9585230487028,1006.4321280000004,1697.390651048714,1]
["1","03","04","  ","  ","  ","Linac Vacuum Subsystem                                      ",220,0,22617.781515831477,-33695.512003896074,-38978.83128416848,null,159.2,0,15638.149910783919,-35057.91200389608,-19419.762093112357]
["1","03","04","02","  ","  ","Linac Beamline Vacuum System                                ",0,0,72.14467225679255,1362.4000000000087,1434.5446722568013,null,0,0,0,0,0,1]
["1","03","04","03","  ","  ","BC1 Vacuum System                                           ",0,0,188.5925165280005,0,188.5925165280005,null,0,0,0,0,0,1]
["1","03","04","04","  ","  ","BC2 Vacuum System                                           ",0,0,2020.0936738444725,0,2020.0936738444143,null,0,0,775.3307018408595,0,775.3307018408086,1]
["1","03","04","05","  ","  ","Linac to Undulator (LTU) Vacuum System                      ",0,0,557.4501671490725,-35057.91200389608,-62401.56263285084,null,0,0,551.3607465203968,-35057.91200389608,-34506.551257375744,1]
["1","03","04","06","  ","  ","Dumpline Vacuum System                                      ",0,0,-4.318178578861989,0,-4.318178578861989,null,0,0,-4.318178578774678,0,-4.318178578861989,1]
["1","03","04","07","  ","  ","Vacuum System Undulator Interface                           ",220,0,19783.818664632,0,19783.818664632,null,159.2,0,14315.776641001437,0,14315.776641001437]
["1","03","04","07","01","  ","Entrance Section Assembly                                   ",104,0,9342.0715151808,0,9342.0715151808,null,78,0,7006.553636385599,0,7006.553636385599,1]
["1","03","04","07","02","  ","Exit Section Assembly                                       ",116,0,10441.7471494512,0,10441.7471494512,null,81.2,0,7309.223004615839,0,7309.223004615839,1]
["1","03","04","08","  ","  ","LTU/BSY& Cold Trap Vacuum System                            "]
["1","03","05","  ","  ","  ","Linac Electron Diagnostics Summary                          ",40,0,8447.366340206609,-181604.20198013884,-252670.17390500946,null,0,0,4305.8577405444485,-182863.46028602117,-178557.6025454767]
["1","03","05","01","  ","  ","Wire Scanners (11) Summary                                  ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","03","05","02","  ","  ","Beam Position Monitors                                      ",0,0,125.17900667999982,-185057.5365562353,-184738.58099331998,null,0,0,0,-185193.7765562353,-185193.7765562353]
["1","03","05","02","01","  ","BPM - Standard  Linac (4) Summary                           ",0,0,17.472000000000094,0,17.472000000000094,null,0,0,0,0,0,1]
["1","03","05","02","02","  ","BPM - RF (10) Summary                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","03","05","02","03","  ","BPM - FFTB (12) Summary                                     ",0,0,0,-185193.7765562353,-185000,null,0,0,0,-185193.7765562353,-185193.7765562353,1]
["1","03","05","02","04","  ","BPM - Large Aperture (2) Summary                            ",0,0,107.70700667999972,136.24,243.9470066800004,null,0,0,0,0,0,1]
["1","03","05","03","  ","  ","Toroid Beam Current Monitor (10) Summary                    ",0,0,186.44958531663724,1118.2579200000037,1304.707505316619,null,0,0,99.08958531663302,1118.2579200000037,1217.3475053166403,1]
["1","03","05","04","  ","  ","Beam Stoppers (4) Summary                                   ",0,0,630.0982172160002,300.71734131869016,-8595.897357599992,null,0,0,630.0982172159966,300.71734131869016,930.8155585347049,1]
["1","03","05","05","  ","  ","Profile Monitors (7 OTR-3 PHOSPHOR SCREEN-1 YAG)            ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","03","05","06","  ","  ","E/O Bunch Length Monitors (1) Summary                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","03","05","07","  ","  ","CSR/OTR/CTR Bunch Length Monitors (5) Summary               ",40,0,5287.707810292079,1667.6749142857007,-47356.161789707985,null,0,0,1368.861468962743,549.1445142857119,1918.0059832484985,1]
["1","03","05","08","  ","  ","Beam Loss Monitors                                          ",0,0,321.93677942375507,66.56297142856783,-21183.023220576244,null,0,0,321.93677942375143,66.56297142856783,388.49975085231563]
["1","03","05","08","01","  ","PIC Beam Loss Monitors (10) Summary                         ",0,0,295.47996038976635,66.56297142856783,-21209.48003961023,null,0,0,295.4799603897627,66.56297142856783,362.04293181833054,1]
["1","03","05","08","02","  ","PLIC Beam Loss Monitors (2) Summary                         ",0,0,26.456819033988722,0,26.456819033985084,null,0,0,26.456819033988722,0,26.456819033985084,1]
["1","03","05","09","  ","  ","Single Beam Dump (1) Summary                                ",0,0,853.4419209622793,250.2102096000017,1103.6521305622882,null,0,0,853.4419209622793,250.2102096000017,1103.6521305622882,1]
["1","03","05","10","  ","  ","Electron Beam Dump (1) Summary                              ",0,0,648.6812814630539,0,648.6812814630539,null,0,0,648.6812814630466,0,648.6812814630466,1]
["1","03","05","11","  ","  ","Protection Collimators (5) Summary                          ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","03","05","12","  ","  ","Movable Collimators (7x,3y) Summary                         ",0,0,10.123251652803447,44.87905882351333,6031.512051652797,null,0,0,0,40.39115294115618,40.39115294115618,1]
["1","03","05","13","  ","  ","Safety Electron Dump (1) Summary                            ",0,0,383.7484872000023,5.032160639999347,114.93648720000783,null,0,0,383.74848719999864,5.032160639999347,388.7806478400089,1]
["1","03","05","14","  ","  ","Charge Monitor (Entrance/Exit Assembly)                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","03","06","  ","  ","  ","Linac RF Subsystem                                          ",0,0,1728.1569810064611,1865.4804482978827,156268.56568100653,null,0,0,0,35.5110543617011,35.5110543617011]
["1","03","06","02","  ","  ","S-Band High Power System                                    ",0,0,643.1517776112014,1532.7,2175.851777611184,null,0,0,0,0,0,1]
["1","03","06","03","  ","  ","S-Band Structures                                           ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","03","06","04","  ","  ","X-Band Low Level System                                     ",0,0,1085.0052033952597,332.7804482978827,154092.71390339534,null,0,0,0,35.5110543617011,35.5110543617011,1]
["1","03","06","05","  ","  ","X-Band High Power System                                    ",0,0,0,0,0,null,0,0,0,0,0]
["1","03","06","05","01","  ","X-Band HP Klystron                                          ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","03","06","05","02","  ","X-Band HP Modulator                                         ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","03","06","05","03","  ","X-Band HP Waveguide System                                  ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","03","06","06","  ","  ","X-Band Structures                                           ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","03","06","07","  ","  ","RF Distribution System                                      ",0,0,0,0,0,null,0,0,0,0,0]
["1","03","06","07","01","  ","Modulator Refurbishment                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","03","06","07","02","  ","Solid State Sub Booster                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","03","06","07","03","  ","IPA Modifications                                           ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","03","06","07","04","  ","Klystron Controls Interfaces                                ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","03","06","07","05","  ","Bunch Length Electronics                                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","03","06","07","06","  ","RF Phase Measurements                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","03","06","07","07","  ","RF Distribution L2 & L3                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","03","06","07","08","  ","RF Fiber Optics Electronics System                          ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","03","06","07","09","  ","RF Stability                                                ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","03","07","  ","  ","  ","Linac Installation & Alignment                              ",0,0,20578.435026859697,153430.13761783854,107916.57451885962,null,0,0,6087.048854457855,95267.26048469567,101354.30933915352]
["1","03","07","01","  ","  ","Linac L01 System Installation & Alignment                   ",0,0,68.98812913200027,544.9599999999991,613.9481291320008,null,0,0,0,0,0,1]
["1","03","07","02","  ","  ","Linac BC1 System Installation & Alignment                   ",0,0,206.96438739600035,119.89120000000003,326.85558739599946,null,0,0,0,0,0,1]
["1","03","07","03","  ","  ","Linac L02 System Installation & Alignment                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","03","07","04","  ","  ","Linac BC2 System Installation & Alignment                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","03","07","05","  ","  ","Linac L03 System Installation & Alignment                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","03","07","06","  ","  ","Linac LTU System Installation & Alignment                   ",0,0,1413.851341968053,0,1413.8513419679366,null,0,0,0,0,0,1]
["1","03","07","07","  ","  ","Linac E-Dump System Installation & Alignment                ",0,0,0,1109.3828571428603,27562.399999999907,null,0,0,0,0,0,1]
["1","03","07","10","  ","  ","LINAC  Installation 2006 Shut Down                          ",0,0,12801.58231390579,56388.64307600003,101590.22538990586,null,0,0,0,0,0]
["1","03","07","10","01","  ","Beamline Equip Removal L01 thru BC1 Out                     ",0,0,4552.506063274457,0,4552.506063274457,null,0,0,0,0,0,1]
["1","03","07","10","02","  ","Gallery Waveguide Installation                              ",0,0,6041.821258746495,24761.41994000002,30803.241198746604,null,0,0,0,0,0,1]
["1","03","07","10","03","  ","Beamline Equip Installation L01 thru BC1 Out                ",0,0,2207.254991884838,7296.0441500000015,9503.299141884781,null,0,0,0,0,0,1]
["1","03","07","10","04","  ","2006 Linac Controls Install and Checkout Gallery to Linac B ",0,0,0,16192.704996,37592.704996,null,0,0,0,0,0,1]
["1","03","07","10","05","  ","2006 Linac Controls Install and Checkout L01 to BC1         ",0,0,0,8138.473990000006,19138.473990000006,null,0,0,0,0,0,1]
["1","03","07","20","  ","  ","LINAC Installation 2007 Shut Down                           ",0,0,6087.048854457855,95267.26048469567,-23590.705929542077,null,0,0,6087.048854457855,95267.26048469567,101354.30933915352]
["1","03","07","20","01","  ","Beamline Equip Removal L02, L03 and BC2                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","03","07","20","02","  ","Beamline Equip Installation L02, L03 and BC2                ",0,0,0,-29677.754783999997,-29677.75478399993,null,0,0,0,-29677.754783999997,-29677.75478399993,1]
["1","03","07","20","03","  ","2007 Linac Controlls Install and Checkout                   ",0,0,6087.048854457855,124945.01526869566,6087.048854457855,null,0,0,6087.048854457855,124945.01526869566,131032.06412315345,1]
["1","03","07","20","04","  ","Linac Undulator Interface                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","  ","  ","  ","  ","UNDULATOR SYSTEM                                            ",-12728,-2413982,-928028.4329843328,-2474972.8838210264,-3248528.6898192405,null,13787.418000000001,920994.85,1568612.90391827,987767.5708071035,2556380.4747253745]
["1","04","01","  ","  ","  ","Undulator System Management & Integration                   ",1681,-136382,367690.4488794066,-111686.26033146799,336454.18087940663,null,12641.156,-18758,1455192.564541721,44941.038229460886,1500133.6027711816]
["1","04","01","01","  ","  ","Undulator System Management                                 ",1681,-146623,367690.4488794066,-150452.20550079306,336454.18087940663,null,12641.156,-97758,1455192.564541721,-101587.20550079306,1353605.3590409278]
["1","04","01","01","01","  ","Undulator System Management - Technical                     ",548,-6888,237391.86158076045,-8354.585500793059,237391.86158076045,null,10129.576000000001,-6888,1173485.3817753862,-8354.585500793059,1165130.796274593,1]
["1","04","01","01","02","  ","ANL Project Support                                         ",1133,-139735,130298.58729864616,-142097.62,99062.31929864618,null,2511.58,-90870,281707.1827663348,-93232.62,188474.56276633477,1]
["1","04","01","02","  ","  ","Undulator System Materials & Supplies                       ",0,35491,0,64702.13752007642,0,null,0,99000,0,167061.72564931132,167061.72564931132]
["1","04","01","02","01","  ","Undulator System M&S - General                              ",0,2579,0,4770.11608587292,0,null,0,19077,0,25370.00776041582,25370.00776041582,1]
["1","04","01","02","02","  ","Undulator System Travel                                     ",0,32912,0,59932.0214342035,0,null,0,79923,0,141691.7178888955,141691.7178888955,1]
["1","04","01","03","  ","  ","Undulator System Reviews and Workshops                      ",0,-25250,0,-25936.192350751364,0,null,0,-20000,0,-20533.481919057376,-20533.481919057376,1]
["1","04","03","  ","  ","  ","Undulator Magnet & Support                                  ",-8926,-2916880,-798240.9149918521,-3078961.560456195,-3420423.007878761,null,642.0620000000002,24999.85,59445.92486070247,-50023.5902450781,9422.334615624815]
["1","04","03","01","  ","  ","UND Magnet & Support - Mgmt and Integration                 ",-891,0,-97830.56615786736,0,-97830.56615786736,null,-179.388,0,-19652.912202472493,0,-19652.912202472493,1]
["1","04","03","02","  ","  ","First Prototype Undulator & Mfg Plan                        ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","03","03","  ","  ","1st Article Undulators & Long Lead Procurements             ",-140,-561839,-14859.209197966184,-561618.2868675023,-498418.1252979662,null,-2.1000000000000227,-0.25,373.3580430653892,546.6006324976497,919.9586755632572]
["1","04","03","03","01","  ","Ti Strongback (LLP)                                         ",0,-127159,0,-127159,-127159,null,0,0,0,0,0,1]
["1","04","03","03","02","  ","Magnet Blocks (LLP)                                         ",-2,-422136,-215.40268764000004,-422136,-344015.40268764,null,0,0,0,0,0,1]
["1","04","03","03","03","  ","Magnet Poles (LLP)                                          ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","03","03","04","  ","Magnet Assembly & Supports - 1st Articles                   ",-71,-6294,-7845.612091911717,-6457.644,-14303.256091911724,null,-0.8999999999999773,-0.25,-99.45142088339344,-0.2565000000031432,-99.70792088334565,1]
["1","04","03","03","04","01","Magnet Assembly 1st Article - Vendor A                      ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","03","03","04","02","Magnet Assembly 1st Article - Vendor B                      ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","03","03","04","03","Support/Mover System - Articles 1 & 2                       ",-67,-6250,-7403.605776874443,-6412.5,-13816.105776874407,null,-1.2000000000000455,0,-132.60189451119368,0,-132.60189451108454,1]
["1","04","03","03","05","  ","Magnetic Measurement (ANL)                                  ",0,0,273.397601753888,270.22789999999986,543.6255017538879,null,0,0,273.397601753888,270.22789999999986,543.6255017538879]
["1","04","03","03","05","01","Magnetic Measurement (ANL) - Vendor A Und #1                ",0,0,273.397601753888,270.22789999999986,543.6255017538879,null,0,0,273.397601753888,270.22789999999986,543.6255017538879,1]
["1","04","03","03","05","02","Magnetic Measurement (ANL) - Vendor B Und #2                ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","03","03","06","  ","Integrated Single-Undulator Module Test                     ",0,0,332.0137567060883,276.629232497653,332.0137567060883,null,0,0,332.0137567060883,276.629232497653,608.6429892037995,1]
["1","04","03","03","07","  "," System Test - Two Undulators                               ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","03","04","  ","  ","Production Undulator Magnet Assembly & Supports             ",-944,-1526270,-103482.22060538286,-1555873.9266009852,-1613764.0406053828,null,0,0,0,0,0]
["1","04","03","04","01","  ","Production Undulator Assembly - Vendor A                    ",-40,-80870,-4420.063150372801,-80892.62,-85312.68315037279,null,0,0,0,0,0,1]
["1","04","03","04","02","  ","Production Undulator Assembly - Vendor B                    ",-840,-1255400,-92169.27145053005,-1284981.3066009851,-1331558.47145053,null,0,0,0,0,0,1]
["1","04","03","04","03","  ","Production Support/Mover Fabrication/Assembly               ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","03","04","04","  ","Mu Metal Shield                                             ",-64,-190000,-6892.88600448,-190000,-196892.88600448,null,0,0,0,0,0,1]
["1","04","03","05","  ","  ","Quadrupole Focusing Magnets                                 ",-98,-59183,-10274.15306608822,-139962.43440084293,-146357.10318899626,null,0,0.09999999997671694,182.83855612085608,-80667.51974927378,-80484.68119315288]
["1","04","03","05","01","  ","Quadrupole Magnets                                          ",-54,-56233,-5595.49110637595,-136937.96191601147,-141678.44122928398,null,-0.5,0.09999999997671694,181.4275947339629,-80671.0735711839,-80489.64597644989,1]
["1","04","03","05","02","  ","Quadrupole Power Supplies                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","03","05","03","  ","Quadrupole Stages & Stands                                  ",-44,-2950,-4678.66195971227,-3024.4724848314654,-4678.66195971227,null,0.5,0,1.4109613868931774,3.553821910114493,4.964783297007671,1]
["1","04","03","05","04","  ","Quadrupole Cables                                           ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","03","06","  ","  ","Undulator Magnetic Measurement Facility (SLAC)              ",-7045,-794588,-590375.9350060349,-848639.7875868655,-1109767.2166700352,null,631.55,0,59961.47142250134,2964.4538716980314,62925.92529419954]
["1","04","03","06","01","  ","Undulator MMF Setup                                         ",-2128,-47978,-176058.48307925876,-51554.18854399999,-227612.67162325874,null,0,0,0,0,0]
["1","04","03","06","01","01","Undulator Test Stand Prototype                              ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","03","06","01","04","Undulator Test Stand                                        ",-136,0,-10403.036181599999,0,-10403.036181599999,null,0,0,0,0,0,1]
["1","04","03","06","01","05","Undulator Fiducialization                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","03","06","01","06","Quad Strength and Field Quality                             ",-264,-4750,-20711.32935611258,-5073.368,-25784.697356112578,null,0,0,0,0,0,1]
["1","04","03","06","01","07","Quad Fiducialization System                                 ",-276,0,-21364.99120122616,0,-21364.99120122616,null,0,0,0,0,0,1]
["1","04","03","06","01","08","Hall Probe Calibration System                               ",-118,0,-9106.433592,0,-9106.433592,null,0,0,0,0,0,1]
["1","04","03","06","01","09","Undulator Handling                                          ",-1334,-43228,-114472.69274832001,-46480.82054399999,-160953.51329232,null,0,0,0,0,0,1]
["1","04","03","06","02","  ","Fiducialization and Magnetic Measurements (F/MM)            ",-1593,-118080,-133977.38319596974,-126193.80556075471,-102236.06223596982,null,-0.3999999999996362,0,2921.1017859862186,154.29565584905504,3075.3974418351427,1]
["1","04","03","06","02","01","F/MM Undulator Magnet Sections                              ",-1484,0,-125800.86063460633,0,-125800.86063460633,null,0,0,1738.041947349906,0,1738.041947349906,1]
["1","04","03","06","02","02","F/MM Quadrupoles                                            ",0,0,739.8927713849116,0,739.8927713849116,null,0,0,739.8927713849116,0,739.8927713849116,1]
["1","04","03","06","02","03","F/MM BPMs                                                   ",0,-118080,0,-126193.80556075471,31741.32096,null,0,0,0,154.29565584905504,154.29565584905504,1]
["1","04","03","06","02","04","F/MM Correctors                                             ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","03","06","02","05","F/MM Vacuum Chamber                                         ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","03","06","02","06","F/MM Photon Diagnostics Components                          ",-109,0,-9394.056,0,-9394.056,null,-0.4000000000000057,0,-34.47360000000117,0,-34.47360000000117,1]
["1","04","03","06","03","  ","Undulator Monitoring                                        ",-1731,-510450,-145885.04486758506,-544697.9879213561,-677204.7799075851,null,632.35,0,54596.9085177803,2655.8625599999214,57252.77107778052]
["1","04","03","06","03","01","Stretched Wire System                                       ",-630,-53000,-53507.38410455943,-52888.13744000008,-106395.5215445594,null,632,0,53657.65509675525,2655.8625599999214,56313.5176567554,1]
["1","04","03","06","03","02","Hydrostatic Level System                                    ",-812,-57700,-69505.60732354863,-61979.46248135599,-118106.8169235487,null,0.34999999999990905,0,856.139532131303,0,856.1395321313757,1]
["1","04","03","06","03","03","F/MM BPMs                                                   ",-289,-399750,-22872.053439477,-429830.38800000004,-452702.441439477,null,0,0,83.11388889374939,0,83.11388889374211,1]
["1","04","03","08","  ","  ","Fixed Supports                                              ",192,25000,18581.16904148739,27132.875,45714.04404148739,null,192,25000,18581.16904148739,27132.875,45714.04404148739]
["1","04","03","08","01","  ","Fixed Sppt Mgmt & Integration                               ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","03","08","02","  ","Fixed Support Design                                        ",192,25000,18581.16904148739,27132.875,45714.04404148739,null,192,25000,18581.16904148739,27132.875,45714.04404148739,1]
["1","04","03","08","03","  ","Stabilized Girder Assemblies                                ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","03","08","04","  ","Thermal Intercept System                                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","03","08","05","  ","Thermometry                                                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","03","08","06","  ","Kinematic Girder Support                                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","03","08","07","  ","Earthquake Bracing                                          ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","03","08","08","  ","Controls and Software                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","04","  ","  ","  ","Vacuum System                                               ",-2608,732578,-240783.47418430774,790503.418283915,558242.9526276923,null,505,914753,50037.105250704546,974144.1029399997,1024181.2081907048]
["1","04","04","02","  ","  ","Undulator Vacuum Chamber Assembly                           ",-1181,736203,-105885.38601159959,791650.2178839151,771622.5165284004,null,503.8,914753,47753.95695954989,971665.9025399997,1019419.85949955]
["1","04","04","02","01","  ","Prototype Chamber Weldment                                  ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","04","02","02","  ","Production Chamber Weldment                                 ",-36,914753,1610.0299511595804,971665.9025399997,973275.9324911595,null,503.8,914753,47753.95695954989,971665.9025399997,1019419.85949955,1]
["1","04","04","02","03","  ","Prototype Aluminum Chamber                                  ",-1145,-178550,-107495.41596275917,-180015.68465608466,-201653.41596275917,null,0,0,0,0,0,1]
["1","04","04","03","  ","  ","Beam-line Bellows Module Assembly                           ",-429,-3625,-35094.78956882148,-1200.151600000012,-113629.61729682142,null,-0.19999999999998863,0,685.0223410346225,2424.848399999988,3109.8707410347124]
["1","04","04","03","01","  ","Prototype Bellows Module                                    ",-238,-3625,-20669.50243477205,-3625,-24294.50243477205,null,0,0,0,0,0,1]
["1","04","04","03","02","  ","Production Bellows Module                                   ",-191,0,-14425.287134049424,2424.848399999988,-89335.11486204938,null,-0.19999999999998863,0,685.0223410346225,2424.848399999988,3109.8707410347124,1]
["1","04","04","04","  ","  ","Single Undulator Test (SUT) Vacuum                          ",-214,0,-23095.90998977371,0,-23095.90998977371,null,0.4,0,-1.915360698494851,0,-1.915360698494851,1]
["1","04","04","05","  ","  ","Short Diagnostic Break (SDB) Assembly                       ",-193,0,-23918.309273534847,26.675999999999476,-23891.63327353487,null,1,0,490.86065467296794,26.675999999999476,517.5366546729347,1]
["1","04","04","06","  ","  ","Long Diagnostic Break (LDB) Assembly                        ",-139,0,-12434.045402513126,26.675999999999476,-12407.369402513112,null,0,0,253.87072805052594,26.675999999999476,280.5467280505254,1]
["1","04","04","07","  ","  ","Entrance Section Assembly                                   ",-40,0,-4308.0537528,0,-4308.0537528,null,0,0,0,0,0,1]
["1","04","04","08","  ","  ","Exit Section Assembly                                       ",-48,0,-5169.664503360001,0,-5169.664503360001,null,0,0,0,0,0,1]
["1","04","04","09","  ","  ","Baking System                                               ",-364,0,-30877.315681904976,0,-30877.315681904933,null,0,0,855.309928095041,0,855.3099280950555,1]
["1","04","05","  ","  ","  ","Diagnostics                                                 ",-2608,-93298,-239795.79163758951,-74828.48131727887,-705904.1143975896,null,-0.9999999999999147,1.1823431123048067e-11,3688.248107480268,18706.019882721164,22394.267990201475]
["1","04","05","02","  ","  ","Undulator Line Diagnostics (ULD)                            ",0,0,0,0,0,null,0,0,0,0,0]
["1","04","05","02","01","  ","ULD Test Station                                            ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","05","02","02","  ","ULD Vacuum Chamber                                          ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","05","02","03","  ","Positioning Mechanism                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","05","02","04","  ","Scanning wire assembly (ULD-SWA)                            ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","05","02","05","  ","Optical transition radiation imaging assembly               ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","05","02","09","  ","ULD Design & Integration                                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","05","04","  ","  ","End-of-Undulator(EOU) X-ray and Profile diagnost            ",0,0,0,0,0,null,0,0,0,0,0]
["1","04","05","04","01","  ","Prototype Construction and Testing                          ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","05","04","02","  ","Bunch Length Monitor-Streak Camera (BLM)                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","05","04","03","  ","Upstream corrector / separator                              ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","05","04","04","  ","Optical Diffraction radiation imaging assembly (            ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","05","04","05","  ","X-ray High Resolution monochromator assembly (EO            ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","05","04","06","  ","X-ray Imaging High Resolution detector assembly             ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","05","04","07","  ","EOU Design and Integration                                  ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","05","05","  ","  ","RFBPM                                                       ",-1094,-85552,-96236.20601416394,-75739.45450299315,-464326.37801416405,null,-1.1999999999999602,-0.1999999999998181,1773.7400277883835,9847.445497006853,11621.185524795317]
["1","04","05","05","01","  ","X-Band Cavity BPM Development                               ",-676,-63500,-61066.82946153457,-63492.2,-118481.0294615346,null,-0.4000000000000057,0,32.146969102555886,42.90000000000009,75.04696910256462,1]
["1","04","05","05","02","  ","X-Band Receiver Development                                 ",-110,-22052,-9434.585641272843,-21988.3,-31422.885641272846,null,0,-0.1999999999998181,100.2139402071598,63.5,163.7139402071598,1]
["1","04","05","05","03","  ","X-Band BPM Production                                       ",-308,0,-25734.790911356526,9741.045497006853,-314422.4629113566,null,-0.7999999999999545,0,1641.3791184786678,9741.045497006853,11382.424615485594,1]
["1","04","05","06","  ","  ","Beam Finder Wire                                            ",-616,-7746,-53307.06835923242,-4424.226814285736,-156660.41911923245,null,-0.39999999999997726,0.20000000001164153,342.08113271605544,3523.374385714298,3865.4555184302735,1]
["1","04","05","07","  ","  ","Charge Monitor (CM)                                         ",-32,0,-2734.9512364800003,0,-2734.9512364800003,null,0,0,0,0,0,1]
["1","04","05","08","  ","  ","Beam Loss Monitoring                                        ",-841,0,-84966.34016099808,5335.200000000012,-79631.1401609981,null,0.6000000000000227,0,1380.7149892831367,5335.200000000012,6715.914989283192,1]
["1","04","05","09","  ","  ","Radiation Detection Monitor (RDM)                           ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","05","10","  ","  ","SIngle Undulator Test (SUT) Diagnostics                     ",-25,0,-2742.9378244077607,0,-2742.9378244077607,null,0,0,0,0,0,1]
["1","04","05","11","  ","  ","Supplemental Shielding                                      ",0,0,191.71195769269252,0,191.71195769269252,null,0,0,191.71195769269252,0,191.71195769269252,1]
["1","04","06","  ","  ","  ","Undulator System Installation and Alignment                 ",-267,0,-16898.701049989817,0,-16898.701049989817,null,0.20000000000004547,0,249.06115766154835,0,249.06115766154835]
["1","04","06","01","  ","  ","Undulator System Installation and Alignment Inte            ",0,0,0,0,0,null,0,0,0,0,0]
["1","04","06","01","01","  ","Undulator System                                            ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","06","02","  ","  ","Control System Installation and Alignment                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","04","06","04","  ","  ","Vacuum System Installation and Alignment                    ",-267,0,-16898.701049989817,0,-16898.701049989817,null,0.20000000000004547,0,249.06115766154835,0,249.06115766154835,1]
["1","04","06","05","  ","  ","Diagnostics System Installation and Alignment               ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","05","  ","  ","  ","  ","X-RAY TRANSPORT & DIAGNOSTICS SYSTEMS                       ",140,0,96504.1029836729,83291.15510779,950626.6417036735,null,63,0,46328.83049254176,81264.30568871782,127593.13618125905]
["1","05","01","  ","  ","  ","System Management & Integration                             ",0,0,6852.253378354344,970.034027111542,-35350.09717164548,null,0,0,371.9288873762416,569.3989920053282,941.3278793815989]
["1","05","01","01","  ","  ","Management                                                  ",0,0,6852.253378354344,970.034027111542,-35350.09717164548,null,0,0,371.9288873762416,569.3989920053282,941.3278793815989]
["1","05","01","01","01","  ","XTOD Management - Technical                                 ",0,0,5586.322449999861,629.7866566716693,5741.022450000048,null,0,0,0,261.29766116941755,261.2976611694321,1]
["1","05","01","01","02","  ","LLNL Project Support                                        ",0,0,743.8577747524832,340.2473704398726,-41613.19277524753,null,0,0,371.9288873762416,308.10133083591063,680.0302182121668,1]
["1","05","01","01","03","  ","Commissioning Coordinator                                   ",0,0,522.0731536019994,0,522.0731536019994,null,0,0,0,0,0,1]
["1","05","03","  ","  ","  ","Mechanical & Vacuum Subsystem                               ",0,0,5689.987639486877,58419.91764684079,1180580.104789487,null,0,0,3310.375637449484,58342.91508046911,61653.290717918586]
["1","05","03","01","  ","  ","Vacuum Systems Engineering                                  ",0,0,962.8641537610092,114.92920353981754,23740.06415376102,null,0,0,390.3038960253616,37.92663716813695,428.2305331934913,1]
["1","05","03","02","  ","  ","Mech/Vac Front End                                          ",0,0,683.9418982025236,8764.666560000041,9448.608458202449,null,0,0,666.42375051009,8764.666560000041,9431.090310510015,1]
["1","05","03","03","  ","  ","Mech/Vac Near Hall                                          ",0,0,358.5179814256262,5786.056931707339,244568.8232214256,null,0,0,260.0843571948499,5786.056931707339,6046.141288902145]
["1","05","03","03","01","  ","Mech/Vac Near Hall                                          ",0,0,358.5179814256262,5786.056931707339,244568.8232214256,null,0,0,260.0843571948499,5786.056931707339,6046.141288902145,1]
["1","05","03","03","02","  ","NEH Hutch 2                                                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","05","03","03","03","  ","NEH Hutch 3                                                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","05","03","04","  ","  ","Mech/Vac Tunnel                                             ",0,0,3684.663606097718,43754.26495159359,902822.6089560979,null,0,0,1993.5636337191827,43754.26495159359,45747.828585312935,1]
["1","05","03","05","  ","  ","Mech/Vac Far Hall                                           ",0,0,0,0,0,null,0,0,0,0,0]
["1","05","03","05","01","  ","FEH Hutch 1                                                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","05","03","05","02","  ","FEH Hutch 2                                                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","05","03","05","03","  ","FEH Hutch 3                                                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","05","04","  ","  ","  ","Optical  Subsystem                                          ",140,0,49319.968746832164,14709.619900443653,-186526.0699731676,null,2,0,12428.121143899261,14180.51990044365,26608.641044342003]
["1","05","04","01","  ","  ","Optical Systems Engineering                                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","05","04","02","  ","  ","Facility Optics                                             ",140,0,49319.968746832164,14709.619900443653,-186526.0699731676,null,2,0,12428.121143899261,14180.51990044365,26608.641044342003]
["1","05","04","02","01","  ","Fast Valve                                                  ",-4,0,-307.2754653923039,277.5971250000075,-28778.77546539229,null,-2,0,25.170238453851198,277.5971250000075,302.76736345385143,1]
["1","05","04","02","02","  ","Fixed Mask                                                  ",0,0,1242.1153895604366,0,1242.1153895604366,null,0,0,0,0,0,1]
["1","05","04","02","03","  ","Slit/Collimators                                            ",0,0,4712.959245500038,0,4712.959245499922,null,4,0,2213.6836108846182,0,2213.683610884531,1]
["1","05","04","02","04","  ","Flipper Mirror                                              ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","05","04","02","05","  ","Gas/Solid Attenuator                                        ",0,0,6670.546204949904,240.5,35142.046204950195,null,0,0,2759.340479950013,0,2759.3404799501877,1]
["1","05","04","02","06","  ","TTF Damage Experiment                                       ",144,0,28169.094646153855,288.6000000000022,28457.69464615386,null,0,0,0,0,0,1]
["1","05","04","02","07","  ","FEL Offset Mirrors                                          ",0,0,8832.528726060234,13902.922775443643,-227302.10999393975,null,0,0,7429.926814610779,13902.922775443643,21332.849590053433]
["1","05","04","02","07","01","Low Energy Mirrors                                          ",0,0,3936.3315668567084,10067.128789091017,-232198.30715314334,null,0,0,2533.729655407311,10067.128789091017,12600.858444498037,1]
["1","05","04","02","07","02","High Energy Mirrors                                         ",0,0,4896.197159203526,3835.7939863526262,4896.197159203584,null,0,0,4896.197159203468,3835.7939863526262,8731.991145555396,1]
["1","05","04","02","08","  ","Solid Attenuator                                            ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","05","04","02","09","  ","Low Energy Mirror System                                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","05","04","03","  ","  ","End Station Optics                                          ",0,0,0,0,0,null,0,0,0,0,0]
["1","05","04","03","01","  ","End Station Optics Engineering                              ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","05","04","03","02","  ","Optics Tank - Near Hall                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","05","04","03","03","  ","Optics Tank - Far Hall                                      ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","05","04","03","04","  ","K-B Focusing System                                         ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","05","04","03","05","  ","Refractive Focusing System                                  ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","05","04","04","  ","  ","Crystals & Gratings                                         ",0,0,0,0,0,null,0,0,0,0,0]
["1","05","04","04","01","  ","Crystals & Gratings Engineering                             ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","05","04","04","02","  ","System Monochrometer                                        ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","05","04","04","03","  ","Pulse Split & Delay                                         ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","05","05","  ","  ","  ","Diagnostics Subsystem                                       ",0,0,27827.75363930571,9191.583533394005,-14891.43552069395,null,61,0,23404.265244122973,8171.471715799737,31575.73695992306]
["1","05","05","01","  ","  ","Diagnostic Systems Engineering                              ",0,0,0,0,0,null,0,0,0,0,0]
["1","05","05","01","01","  ","Diagnostic Systems Engineering                              ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","05","05","02","  ","  ","Modeling & Simulation                                       ",0,0,4476.281099999993,0,4476.281099999993,null,0,0,0,0,0]
["1","05","05","02","01","  ","Wave Model                                                  ",0,0,2238.1405499999964,0,2238.1405499999964,null,0,0,0,0,0,1]
["1","05","05","02","02","  ","Monte Carlo Model                                           ",0,0,2238.1405499999964,0,2238.1405499999964,null,0,0,0,0,0,1]
["1","05","05","02","03","  ","Beam Simulation                                             ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","05","05","03","  ","  ","Facility Diagnostics                                        ",0,0,11030.342964924144,2399.0103163317835,-284928.95703507605,null,57,0,14877.735849156597,1982.3095656000369,16860.04541475681]
["1","05","05","03","01","  ","Direct Imager                                               ",0,0,1625.8375051469775,315.3103200000187,-222729.58249485318,null,0,0,1516.451997071912,236.48274000000674,1752.934737071977,1]
["1","05","05","03","02","  ","Indirect Imager                                             ",0,0,1628.010099999985,0,1628.010099999985,null,0,0,0,0,0,1]
["1","05","05","03","03","  ","Pulsed Ion Chamber                                          ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","05","05","03","04","  ","Gas Mixing System                                           ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","05","05","03","05","  ","FEE Diagnostic Tank                                         ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","05","05","03","06","  ","Gas Detector                                                ",0,0,5568.061478785356,2083.699996331765,-66035.81852121465,null,57,0,11152.849971092859,1745.8268256000301,12898.676796693006,1]
["1","05","05","03","07","  ","NEH Imager                                                  ",0,0,2208.4338809918263,0,2208.4338809918263,null,0,0,2208.4338809918263,0,2208.4338809918263,1]
["1","05","05","03","08","  ","FEH Imager                                                  ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","05","05","04","  ","  ","Commissioning Diagnostics                                   ",0,0,12321.129574381572,6792.573217062221,265561.2404143821,null,4,0,8526.529394966376,6189.1621501997,14715.69154516625]
["1","05","05","04","01","  ","Commission Diagnostic Tanks                                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","05","05","04","02","  ","Total Energy Measurement                                    ",0,0,4640.709993851255,1030.3461918749963,-60879.260006148485,null,0,0,85.38900151313283,426.9351250124746,512.3241265256656,1]
["1","05","05","04","03","  ","Pulse Length Measurement                                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","05","05","04","04","  ","Low Energy Spectral Measurement System                      ",0,0,1748.4819399891421,4441.554000000033,6190.035939989262,null,0,0,1734.8055759891286,4441.554000000033,6176.3595759891905,1]
["1","05","05","04","05","  ","Popup Cameras                                               ",0,0,2209.231577639526,158.56914098359994,59464.27921763953,null,0,0,2209.231577639468,158.56914098359994,2367.800718623039,1]
["1","05","05","04","06","  ","K Measurement System                                        ",0,0,3722.7060629016487,1162.1038842035923,260786.18526290177,null,4,0,4497.103239824646,1162.1038842035923,5659.207124028355,1]
["1","05","05","04","07","  ","Divergence Measurement                                      ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","05","06","  ","  ","  ","X-Ray Transport System Installation & Alignment             ",0,0,6814.139579693801,0,6814.139579693801,null,0,0,6814.139579693801,0,6814.139579693801]
["1","05","06","01","  ","  ","Front End Enclosure Install                                 ",0,0,3269.8274150427897,0,3269.8274150427897,null,0,0,3269.8274150427897,0,3269.8274150427897,1]
["1","05","06","02","  ","  ","Near Hall Install                                           ",0,0,1003.0877839649038,0,1003.0877839649038,null,0,0,1003.0877839649038,0,1003.0877839649038,1]
["1","05","06","03","  ","  ","Tunnel Install                                              ",0,0,1949.290743710444,0,1949.290743710444,null,0,0,1949.290743710444,0,1949.290743710444,1]
["1","05","06","04","  ","  ","Far Hall Install                                            ",0,0,591.9336369756638,0,591.9336369756638,null,0,0,591.9336369756638,0,591.9336369756638,1]
["1","05","06","05","  ","  ","Electron Dump Enclosure Install                             ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","06","  ","  ","  ","  ","X-RAY END STATION SYSTEMS                                   ",1131,0,-46467.44928529609,-11911.369334566378,413336.3873193988,null,1131,0,-50031.82166580286,-12035.17093456637,-62066.99260036943]
["1","06","01","  ","  ","  ","System Management & Integration                             ",0,0,1441.0163968200213,123.8015999999916,1564.8179968200275,null,0,0,0,0,0]
["1","06","01","01","  ","  ","Management                                                  ",0,0,1441.0163968200213,123.8015999999916,1564.8179968200275,null,0,0,0,0,0,1]
["1","06","01","02","  ","  ","SSRL Physics                                                ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","06","03","  ","  ","  ","Mechanical/Vacuum Subsystem                                 ",0,0,0,0,0,null,0,0,0,0,0]
["1","06","03","01","  ","  ","Chamber Support Tables - Mech/Vac                           ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","06","03","02","  ","  ","Vacuum Components - Mech/Vac                                ",0,0,0,0,0,null,0,0,0,0,0]
["1","06","03","02","01","  ","Valves - Vacuum                                             ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","06","03","02","02","  ","Hardware - Vacuum                                           ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","06","03","02","03","  ","Ion Pump - Vacuum                                           ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","06","03","02","04","  ","Turbo Pump - Vacuum                                         ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","06","03","02","05","  ","Gauges - Vacuum                                             ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","06","03","03","  ","  ","Experimental Chambers                                       ",0,0,0,0,0,null,0,0,0,0,0]
["1","06","03","03","01","  ","AP Chamber 1                                                ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","06","03","03","02","  ","AP Chamber 2                                                ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","06","04","  ","  ","  ","Laser Subsystem                                             ",0,0,5365.897746309667,2628.2169546142104,826260.3275031098,null,0,0,4818.053514913219,2628.2169546142104,7446.270469527401]
["1","06","04","01","  ","  ","XES Laser                                                   ",0,0,810.1859893114597,2275.921119085746,708074.5576021115,null,0,0,810.1859893114597,2275.921119085746,3086.1071083971765,1]
["1","06","04","02","  ","  ","Laser Diagnostics                                           ",0,0,2028.5469047487713,0,2028.5469047487713,null,0,0,1480.7026733523235,0,1480.7026733523235,1]
["1","06","04","03","  ","  ","Laser Optical Transport                                     ",0,0,2498.036733034125,352.2958355284645,116128.0948770342,null,0,0,2498.036733034125,352.2958355284645,2850.3325685625896,1]
["1","06","04","04","  ","  ","Laser Safety                                                ",0,0,29.128119215311017,0,29.128119215311017,null,0,0,29.128119215311017,0,29.128119215311017,1]
["1","06","05","  ","  ","  ","X-Ray Detectors                                             ",0,0,842.7773545285454,0,842.7773545285454,null,0,0,530.931425372808,0,530.931425372808]
["1","06","05","01","  ","  ","Beam Imaging                                                ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","06","05","02","  ","  ","Not Used                                                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","06","05","03","  ","  ","Beam Intensity                                              ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","06","05","04","  ","  ","Detector & Streak Camera                                    ",0,0,842.7773545285454,0,842.7773545285454,null,0,0,530.931425372808,0,530.931425372808]
["1","06","05","04","01","  ","Detector Management                                         ",0,0,842.7773545285454,0,842.7773545285454,null,0,0,530.931425372808,0,530.931425372808,1]
["1","06","05","04","02","  ","Streak Camera - LBL                                         ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","06","06","  ","  ","  ","System Installation & Alignment                             ",0,0,-111218.66535126376,0,-111218.66535126376,null,0,0,-111218.66535126376,0,-111218.66535126376]
["1","06","06","01","  ","  ","Front End Install                                           ",0,0,851.6095364892099,0,851.6095364892099,null,0,0,851.6095364892099,0,851.6095364892099,1]
["1","06","06","02","  ","  ","Near Hall Install                                           ",0,0,-113910.11913948499,0,-113910.11913948499,null,0,0,-113910.11913948499,0,-113910.11913948499]
["1","06","06","02","01","  ","Near Hall Install Global Controls                           ",0,0,208.5455537092057,0,208.5455537092057,null,0,0,208.5455537092057,0,208.5455537092057,1]
["1","06","06","02","02","  ","Near Hall Install Mech/Vac                                  ",0,0,-7744.1860195392,0,-7744.1860195392,null,0,0,-7744.1860195392,0,-7744.1860195392,1]
["1","06","06","02","03","  ","Near Hall Install Laser                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","06","06","02","04","  ","Near Hall Install Detectors                                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","06","06","02","05","  ","Near Hall Install Atomic Physics                            ",0,0,-106613.91986495076,0,-106613.91986495076,null,0,0,-106613.91986495076,0,-106613.91986495076,1]
["1","06","06","02","06","  ","Near Hall Install PPS System                                ",0,0,208.5455537092057,0,208.5455537092057,null,0,0,208.5455537092057,0,208.5455537092057,1]
["1","06","06","02","07","  ","Near Hall Install Laser PPS                                 ",0,0,30.895637586552766,0,30.895637586552766,null,0,0,30.895637586552766,0,30.895637586552766,1]
["1","06","06","03","  ","  ","Tunnel Install                                              ",0,0,525.8167641435793,0,525.8167641435793,null,0,0,525.8167641435793,0,525.8167641435793,1]
["1","06","06","04","  ","  ","Far Hall Install                                            ",0,0,1314.0274875884497,0,1314.0274875884497,null,0,0,1314.0274875884497,0,1314.0274875884497]
["1","06","06","04","01","  ","Far Hall Install Global Controls                            ",0,0,208.5455537092057,0,208.5455537092057,null,0,0,208.5455537092057,0,208.5455537092057,1]
["1","06","06","04","02","  ","Far Hall Install Mech/Vac                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","06","06","04","04","  ","Far Hall Install Detectors                                  ",0,0,956.1705365473608,0,956.1705365473608,null,0,0,956.1705365473608,0,956.1705365473608,1]
["1","06","06","04","05","  ","Far Hall Install PPS System                                 ",0,0,149.3113973318832,0,149.3113973318832,null,0,0,149.3113973318832,0,149.3113973318832,1]
["1","06","06","05","  ","  ","Electron Dump Enclosure Install                             ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","06","07","  ","  ","  ","AMOS Experiment                                             ",1131,0,50245.18419626268,-20951.597982357052,-11297.59295584225,null,1131,0,49118.44851695263,-20951.597982357052,28166.85053459536]
["1","06","07","01","  ","  ","AP Management & Design                                      ",0,0,3293.3969043934194,0,3293.3969043934194,null,0,0,2166.6612250833714,0,2166.6612250833714]
["1","06","07","01","01","  ","Management                                                  ",0,0,322.6363055257243,0,322.6363055257243,null,0,0,190.49349512948538,0,190.49349512948538,1]
["1","06","07","01","02","  ","Conceptual Design                                           ",0,0,994.5928689138091,0,994.5928689138091,null,0,0,0,0,0,1]
["1","06","07","01","03","  ","Preliminary Design                                          ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","06","07","01","04","  ","Final Design                                                ",0,0,1976.167729953886,0,1976.167729953886,null,0,0,1976.167729953886,0,1976.167729953886,1]
["1","06","07","02","  ","  ","AP X1 High Field Physics Exp.                               ",0,0,941.4849288090772,1693.7001286153682,941.4849288090627,null,0,0,941.4849288090772,1693.7001286153682,2635.1850574243726]
["1","06","07","02","01","  ","X-Ray Fluorescence Detectors                                ",0,0,169.4731703576981,1693.7001286153682,169.4731703576981,null,0,0,169.4731703576981,1693.7001286153682,1863.173298973008,1]
["1","06","07","02","02","  ","Ion Imaging & Electron TOF Detectors                        ",0,0,431.84842098734225,0,431.84842098737136,null,0,0,431.84842098734225,0,431.84842098737136,1]
["1","06","07","02","03","  ","Sample Source                                               ",0,0,82.88031015193701,0,82.88031015190063,null,0,0,82.88031015193701,0,82.88031015190063,1]
["1","06","07","02","04","  ","Vacuum System                                               ",0,0,128.64151365604994,0,128.64151365603902,null,0,0,128.64151365604994,0,128.64151365603902,1]
["1","06","07","02","05","  ","Other X1 Items                                              ",0,0,128.64151365604994,0,128.64151365605358,null,0,0,128.64151365604994,0,128.64151365605358,1]
["1","06","07","03","  ","  ","AP Refocus Optics                                           ",0,0,-28704.561771167566,-29942.478094867576,-97544.51890716757,null,0,0,-28704.561771167566,-29942.478094867576,-58647.03986603522,1]
["1","06","07","04","  ","  ","AP Diagnostics                                              ",1131,0,109322.37353059785,573.666396799963,109896.03992739774,null,1131,0,109322.37353059785,573.666396799963,109896.03992739774,1]
["1","06","07","05","  ","  ","AP Particle Imaging Experiment                              ",0,0,-34607.50939637009,6723.513587095193,-27883.9958092749,null,0,0,-34607.50939637009,6723.513587095193,-27883.9958092749,1]
["1","06","08","  ","  ","  ","Crystals and Gratings                                       ",0,0,272.18337677344243,78.93585317647012,22336.272336773443,null,0,0,135.25323294892587,78.93585317647012,214.189086125396]
["1","06","08","01","  ","  ","K Measurement Spectrometer                                  ",0,0,272.18337677344243,78.93585317647012,22336.272336773443,null,0,0,135.25323294892587,78.93585317647012,214.189086125396,1]
["1","06","09","  ","  ","  ","Mechanical Systems                                          ",0,0,6584.1569952732825,6209.2742400000025,-315151.54956472677,null,0,0,6584.1569952732825,6209.2742400000025,12793.431235273369]
["1","06","09","01","  ","  ","PPS Stoppers                                                ",0,0,2913.127004100621,5370.580799999996,-319661.27299589943,null,0,0,2913.127004100621,5370.580799999996,8283.707804100704,1]
["1","06","09","02","  ","  ","PPS Shielding                                               ",0,0,3671.0299911726615,838.6934400000064,4509.723431172664,null,0,0,3671.0299911726615,838.6934400000064,4509.723431172664,1]
["1","06","09","03","  ","  ","NEH Hutch Doors                                             ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","  ","  ","  ","  ","CONVENTIONAL FACILITIES                                     ",0,-1509011,4305.306197886031,11671719.301365357,9010837.695243191,null,0,-612378,992.9765838464905,10487241.39420018,10488234.370784026]
["1","09","01","  ","  ","  ","System Management & Integration                             ",0,0,5515.262089879678,-400098.3793385131,762568.14266098,null,0,0,905.8937206282826,-992747.1973990311,-991841.3036784037]
["1","09","01","01","  ","  ","Management                                                  ",0,0,376.7300016480731,-117130.24677879986,-116753.51677715208,null,0,0,0,-6800,-6800,1]
["1","09","01","02","  ","  ","CF Engineering                                              ",0,0,1937.4685799039435,190010.2675870387,1195333.748679904,null,0,0,0,48842.34074311168,48842.34074311168,1]
["1","09","01","03","  ","  ","Construction Management & AE Support                        ",0,0,1345.4642916000448,-475987.07814675197,-320876.3664584998,null,0,0,0,-1034789.5381421428,-1034789.5381421437,1]
["1","09","01","04","  ","  ","Mechanical Design (MD)                                      ",0,0,1678.7667669744696,3008.6780000000035,4687.444766974462,null,0,0,905.8937206282826,0,905.8937206282826]
["1","09","01","04","01","  ","Mechanical Design Title 1 - RSY through CLOC                ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","01","04","02","  ","Mechanical Design T1 Linac Facilities                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","01","04","03","  ","Mechanical Design Title 2 - RSY through CLOC                ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","01","04","04","  ","Mechanical Design T2 Linac Facilities                       ",0,0,717.2029183175982,3008.6780000000035,3725.880918317591,null,0,0,0,0,0,1]
["1","09","01","04","05","  ","Mechanical Design Title 3 Linac Facility                    ",0,0,111.34025605717761,0,111.34025605717761,null,0,0,55.670128028588806,0,55.670128028588806,1]
["1","09","01","04","06","  ","Mechanical Design Title 3 - RSY through CLOC                ",0,0,850.2235925996938,0,850.2235925996938,null,0,0,850.2235925996938,0,850.2235925996938,1]
["1","09","01","05","  ","  ","Conventional Experiment Facility (CEF)                      ",0,0,176.83244975314665,0,176.83244975314665,null,0,0,0,0,0]
["1","09","01","05","01","  ","CEF Engineering Title 1 - RSY through CLOC                  ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","01","05","02","  ","CEF Engineering Title 1 Linac Facility                      ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","01","05","03","  ","CEF Engineering Title 2 - RSY through CLOC                  ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","01","05","04","  ","CEF Design Linac Facility Title 2                           ",0,0,176.83244975314665,0,176.83244975314665,null,0,0,0,0,0,1]
["1","09","02","  ","  ","  ","Title 1 & Title 2 Conventional Facilities                   ",0,0,0,4076.7586900000024,31176.758690000002,null,0,0,0,639.3440750000009,639.3440750000009]
["1","09","02","02","  ","  ","A & E Services  - RSY throguh CLOC                          ",0,0,0,4076.7586900000024,31176.758690000002,null,0,0,0,639.3440750000009,639.3440750000009]
["1","09","02","02","01","  ","Title 1 Design                                              ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","02","02","02","  ","Title 2 Design                                              ",0,0,0,4076.7586900000024,31176.758690000002,null,0,0,0,639.3440750000009,639.3440750000009,1]
["1","09","02","03","  ","  ","A & E Services - (S20, MMF,MCC)                             ",0,0,0,0,0,null,0,0,0,0,0]
["1","09","02","03","01","  ","Title 1 Design (Sector 20)                                  ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","02","03","02","  ","Title 2 Design (Sector 20)                                  ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","02","03","03","  ","Title 1 Design (MMF)                                        ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","02","03","04","  ","Title 2 Design (MMF)                                        ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","02","03","05","  ","Title 1 Design (MCC)                                        ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","02","03","06","  ","Title 2 Design (MCC)                                        ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","  ","  ","  ","Construction-T3 Conventional Facilities                     ",0,-1509011,-1209.9558919936462,12067740.922013871,8217092.793892208,null,0,-612378,87.08286321820788,11479349.247524213,11479436.330387432]
["1","09","03","01","  ","  ","Sector 20 Injector Facilities                               ",0,0,-1297.038755211854,27594.09027700004,114922.05152178818,null,0,0,0,0,0]
["1","09","03","01","01","  ","S20 - Site Preparation/General Requirements                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","01","02","  ","S20 - Site Construction                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","01","03","  ","S20 - Concrete                                              ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","01","04","  ","S20 - Masonry                                               ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","01","05","  ","S20 - Metals                                                ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","01","06","  ","S20 - Woods & Plastics                                      ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","01","07","  ","S20 - Thermal & Moisture Protection                         ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","01","08","  ","S20 - Doors & Windows                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","01","09","  ","S20 - Finishes                                              ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","01","10","  ","S20 - Specialties                                           ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","01","14","  ","S20 - Conveying Systems                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","01","15","  ","S20 - Mechanical                                            ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","01","16","  ","S20 - Electrical                                            ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","01","20","  ","S20 - Project Close Out                                     ",0,0,-1297.038755211854,27594.09027700004,114922.05152178818,null,0,0,0,0,0,1]
["1","09","03","02","  ","  ","Magnetic Measurement Facility                               ",0,0,0,40278.37585720001,75278.37585720001,null,0,0,0,0,0]
["1","09","03","02","01","  ","MMF - Site Preparation/General Requirements                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","02","02","  ","MMF - Site Construction                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","02","03","  ","MMF - Concrete                                              ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","02","04","  ","Utilities                                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","02","05","  ","MMF - Metals                                                ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","02","06","  ","MMF - Woods & Plastics                                      ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","02","07","  ","MMF - Thermal & Moisture Protection                         ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","02","08","  ","MMF - Doors & Windows                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","02","09","  ","MMF - Finishes                                              ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","02","10","  ","MMF - Specialities                                          ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","02","13","  ","                                                            ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","02","14","  ","MMF - Conveying Systems                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","02","15","  ","MMF - Mechanical                                            ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","02","16","  ","MMF - Electrical                                            ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","02","20","  ","MMF - Project Close Out                                     ",0,0,0,40278.37585720001,75278.37585720001,null,0,0,0,0,0,1]
["1","09","03","03","  ","  ","BTH West                                                    ",0,0,0,-30000,0,null,0,0,0,-30000,-30000]
["1","09","03","03","01","  ","BTH West - Site Preparation                                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","03","15","  ","BTH West - Mechanical                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","03","16","  ","BTH West - Electrical                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","03","20","  ","BTH West - Project Close Out                                ",0,0,0,-30000,0,null,0,0,0,-30000,-30000,1]
["1","09","03","04","  ","  ","Linac Facility Upgrade (LN)                                 ",0,0,87.08286321820788,-454629.24117389607,-611824.0830867818,null,0,0,87.08286321820788,8054.656061818183,8141.738925036392]
["1","09","03","04","01","  ","LN - Site Preparation                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","04","02","  ","LN - Sitework                                               ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","04","03","  ","Electrical                                                  ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","04","04","  ","Utilities                                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","04","05","  ","Linac - Metals                                              ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","04","06","  ","Special System - Fire Protection                            ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","04","10","  ","Project Close Out Linac Facility                            ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","04","15","  ","LN - Mechanical                                             ",0,0,0,-462936.91437857144,-377929.14295,null,0,0,0,0,0,1]
["1","09","03","04","16","  ","LN - Electrical                                             ",0,0,0,253.01714285719208,-218495.04,null,0,0,0,0,0,1]
["1","09","03","04","20","  ","LN - Project Close Out                                      ",0,0,87.08286321820788,8054.656061818183,-15399.900136781784,null,0,0,87.08286321820788,8054.656061818183,8141.738925036392,1]
["1","09","03","05","  ","  ","Research Yard Modifications                                 ",0,0,0,-100000,0,null,0,0,0,-40000,-40000]
["1","09","03","05","01","  ","RY - Site Preparation                                       ",0,0,0,0,0,null,0,0,0,0,0]
["1","09","03","05","01","01","General Requirements- CEF                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","05","01","02","General Requirements - G/C                                  ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","05","02","  ","RY - FFTB/BSY & Site Construction                           ",0,0,0,0,0,null,0,0,0,0,0]
["1","09","03","05","02","01","Site Construction - CEF                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","05","02","02","Site Construction - G/C                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","05","03","  ","Electrical                                                  ",0,0,0,0,0,null,0,0,0,0,0]
["1","09","03","05","03","01","Electrical CEF                                              ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","05","03","02","Electrical G/C                                              ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","05","04","  ","Utilities                                                   ",0,0,0,0,0,null,0,0,0,0,0]
["1","09","03","05","04","01","Utilities CEF                                               ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","05","04","02","Utilities G/C                                               ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","05","05","  ","RY - Metals                                                 ",0,0,0,0,0,null,0,0,0,0,0]
["1","09","03","05","05","01","HVAC CEF                                                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","05","05","02","HVAC G/C                                                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","05","06","  ","Special System - Fire Protection                            ",0,0,0,0,0,null,0,0,0,0,0]
["1","09","03","05","06","01","Special System - Fire Protection CEF                        ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","05","06","02","Special System - Fire Protection                            ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","05","07","  ","Interior                                                    ",0,0,0,0,0,null,0,0,0,0,0]
["1","09","03","05","07","01","Interior CEF                                                ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","05","07","02","Interior G/C                                                ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","05","10","  ","Project Close Out Reasearch Yard                            ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","05","20","  ","RY - Project Close Out                                      ",0,0,0,-100000,0,null,0,0,0,-40000,-40000,1]
["1","09","03","06","  ","  ","Pre-Purchase Equipment                                      ",0,0,0,492451.4594444444,263168.3464,null,0,0,0,471502.48912444443,471502.48912444443]
["1","09","03","06","01","  ","PPE - General Requirements                                  ",0,0,0,60889.773999999976,221640.77399999998,null,0,0,0,39940.80368000001,39940.80368000001,1]
["1","09","03","06","02","  ","AR - Site Construction                                      ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","06","03","  ","AR - Concrete                                               ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","06","04","  ","Utilities                                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","06","05","  ","HVAC                                                        ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","06","06","  ","Special System- Fire Protection                             ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","06","07","  ","Interior                                                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","06","10","  ","Project Close Out  Beam Trans Hall                          ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","06","11","  ","Pre-Purchase Equipment for Beam Path                        ",0,0,0,431561.6854444444,41527.572400000005,null,0,0,0,431561.6854444444,431561.6854444444,1]
["1","09","03","06","20","  ","AR - Project Close Out                                      ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","07","  ","  ","SITEWORK                                                    ",0,-217000,0,1676120.2360534056,1786337.8481999992,null,0,38432,0,1090580.1751162957,1090580.1751162957]
["1","09","03","07","01","  ","SW - Site Preparation/General Requirements                  ",0,-217000,0,202110.4854000006,633985.4854000006,null,0,38432,0,321831.5813999998,321831.5813999998,1]
["1","09","03","07","02","  ","SW - Site Construction                                      ",0,0,0,1333874.347053405,982216.9591999985,null,0,0,0,725959.392036296,725959.392036296,1]
["1","09","03","07","03","  ","SW - Concrete                                               ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","07","04","  ","Utilities                                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","07","05","  ","HVAC                                                        ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","07","06","  ","Special System - Fire Protection                            ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","07","07","  ","Interior                                                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","07","09","  ","Tunneling                                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","07","10","  ","Project Close Out Undulator Hall                            ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","07","15","  ","SW - Mechanical                                             ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","07","16","  ","SW - Electrical                                             ",0,0,0,140135.40360000008,170135.40360000008,null,0,0,0,42789.20168,42789.20168,1]
["1","09","03","07","17","  ","SW - Others (include Div 4, and 6 through 14)               ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","07","20","  ","SW - Project Close Out                                      ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","08","  ","  ","Beam Transport Hall (BTH)                                   ",0,117071,0,1606732.2448323893,2136724.255000001,null,0,117071,0,1483527.9195523905,1483527.9195523905]
["1","09","03","08","01","  ","BTH - Site Preparation/General Requirements                 ",0,0,0,97955.46239999996,180955.46239999996,null,0,0,0,3010.2472000000016,3010.2472000000016,1]
["1","09","03","08","02","  ","BTH - Site Construction                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","08","03","  ","BTH - Concrete                                              ",0,0,0,935212.9162000008,863282.842600001,null,0,0,0,932805.471400002,932805.471400002,1]
["1","09","03","08","04","  ","Utilities                                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","08","05","  ","BTH - Metals                                                ",0,0,0,67285.65640588233,-368641,null,0,0,0,67285.65640588233,67285.65640588233,1]
["1","09","03","08","06","  ","Special System - Fire Protection                            ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","08","07","  ","Interior                                                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","08","09","  ","Tunneling                                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","08","10","  ","Project Close Out Front End Enclosure                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","08","15","  ","BTH - Mechanical                                            ",0,0,0,77397.79740000004,302397.7974,null,0,0,0,77397.79740000004,77397.79740000004,1]
["1","09","03","08","16","  ","BTH - Electrical                                            ",0,0,0,274345.77600000007,1123793.776,null,0,0,0,248494.11072,248494.11072,1]
["1","09","03","08","17","  ","BTH - Others (include Div 4, and 6 through 14)              ",0,117071,0,154534.63642650604,34935.3766,null,0,117071,0,154534.63642650604,154534.63642650604,1]
["1","09","03","08","20","  ","BTH - Project Close Out                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","09","  ","  ","Front End Enclosure (FEE)                                   ",0,0,0,393240.77375714266,222866.61819999985,null,0,0,0,392552.81447714265,392552.81447714265]
["1","09","03","09","01","  ","FEE - Site Preparation/General Requirements                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","09","02","  ","FEE - Site Construction                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","09","03","  ","FEE - Concrete                                              ",0,0,0,216922.90899999975,46650.07399999979,null,0,0,0,216922.90899999975,216922.90899999975,1]
["1","09","03","09","04","  ","Utilities                                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","09","05","  ","FEE - Metals                                                ",0,0,0,1185.9718000000003,1185.9718000000003,null,0,0,0,1185.9718000000003,1185.9718000000003,1]
["1","09","03","09","06","  ","Special System (Fire Protection) Beam Dump                  ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","09","09","  ","Tunneling                                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","09","10","  ","Project Close Out Beam Dump                                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","09","15","  ","FEE - Mechanical                                            ",0,0,0,64267.28120000003,65617.28120000003,null,0,0,0,64267.28120000003,64267.28120000003,1]
["1","09","03","09","16","  ","FEE - Electrical                                            ",0,0,0,61794.08095714287,60342.76040000003,null,0,0,0,61106.12167714286,61106.12167714286,1]
["1","09","03","09","17","  ","FEE - Others (include Div 4, and 6 through 14)              ",0,0,0,49070.53080000001,49070.53080000001,null,0,0,0,49070.53080000001,49070.53080000001,1]
["1","09","03","09","20","  ","FEE - Project Close Out                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","10","  ","  ","Electron Beam Dump (EBD)                                    ",0,-544721,0,-44381.02479999987,-1031.0247999998683,null,0,-202601,0,253213.79628000013,253213.79628000013]
["1","09","03","10","01","  ","EBD - Site Preparation/General Requirements                 ",0,-427650,0,-372966.3982,-372966.3982,null,0,-85530,0,-75195.01524000001,-75195.01524000001,1]
["1","09","03","10","02","  ","EBD - Site Construction                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","10","03","  ","EBD - Concrete                                              ",0,0,0,282728.1636000001,326078.1636000001,null,0,0,0,282728.1636000001,282728.1636000001,1]
["1","09","03","10","04","  ","Utilities                                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","10","05","  ","EBD - Metals                                                ",0,0,0,59028.82520000002,59028.82520000002,null,0,0,0,59028.82520000002,59028.82520000002,1]
["1","09","03","10","06","  ","Special System - Fire Protection                            ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","10","07","  ","Interior                                                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","10","10","  ","Project Close Out Near Experimental Hall                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","10","15","  ","EBD - Mechanical                                            ",0,0,0,54847.47080000001,54847.47080000001,null,0,0,0,54847.47080000001,54847.47080000001,1]
["1","09","03","10","16","  ","EBD - Electrical                                            ",0,0,0,47671.46040000001,47671.46040000001,null,0,0,0,47494.89852000002,47494.89852000002,1]
["1","09","03","10","17","  ","EBD - Others (include Div 4, and 6 through 14)              ",0,-117071,0,-115690.5466,-115690.5466,null,0,-117071,0,-115690.5466,-115690.5466,1]
["1","09","03","10","20","  ","EBD - Project Close Out                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","11","  ","  ","Near Experimental Hall (NEH)                                ",0,-864361,0,2177360.8655710993,-223453.17740000016,null,0,-565280,0,2001927.8251230994,2001927.8251230994]
["1","09","03","11","01","  ","NEH - Site Preparation/General Requirements                 ",0,-299081,0,91735.56874685967,72664.79579999996,null,0,0,0,105619.28281885991,105619.28281885991,1]
["1","09","03","11","02","  ","NEH - Site Construction                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","11","03","  ","NEH - Concrete                                              ",0,-266800,0,370151.0147999991,378651.0147999991,null,0,-266800,0,274587.35879999865,274587.35879999865,1]
["1","09","03","11","04","  ","Utilities                                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","11","05","  ","NEH - Metals                                                ",0,0,0,139418.7356,139418.7356,null,0,0,0,139418.7356,139418.7356,1]
["1","09","03","11","06","  ","Special System - Fire Protection                            ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","11","07","  ","Interiors                                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","11","09","  ","Tunneling                                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","11","10","  ","Project Close Out X-Ray Transport & Diagonistic             ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","11","15","  ","NEH - Mechanical                                            ",0,0,0,1011632.2278857157,-2271415.2655999996,null,0,0,0,933235.4806857156,933235.4806857156,1]
["1","09","03","11","16","  ","NEH - Electrical                                            ",0,0,0,359032.23500000034,752690.2350000003,null,0,0,0,343675.88368000044,343675.88368000044,1]
["1","09","03","11","17","  ","NEH - Others (include Div 4, and 6 through 14)              ",0,-298480,0,205391.0835385248,704537.307,null,0,-298480,0,205391.0835385248,205391.0835385248,1]
["1","09","03","11","20","  ","NEH - Project Close Out                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","12","  ","  ","Undulator Hall (UH)                                         ",0,0,0,1485013.736459135,2470242.9844000004,null,0,0,0,1144328.8443298736,1144328.8443298736]
["1","09","03","12","01","  ","UH - Site Preparation/General Requirements                  ",0,0,0,381041.5740591348,328189.7792000002,null,0,0,0,108245.78691067314,108245.78691067314,1]
["1","09","03","12","02","  ","UH - Site Construction                                      ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","12","03","  ","UH - Concrete                                               ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","12","04","  ","Utilities                                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","12","05","  ","UH - Metals                                                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","12","06","  ","Special System - Fire Protection                            ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","12","07","  ","Interiors                                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","12","09","  ","Tunneling                                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","12","10","  ","Project Close Out Far Experimental Hall                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","12","15","  ","UH - Mechanical                                             ",0,0,0,125416.84459999995,475817.84459999995,null,0,0,0,125416.84459999995,125416.84459999995,1]
["1","09","03","12","16","  ","UH - Electrical                                             ",0,0,0,243317.89979999978,930997.9425999997,null,0,0,0,215767.9891199998,215767.9891199998,1]
["1","09","03","12","17","  ","UH - Others (include Div 4, and 6 through 14)               ",0,0,0,4864.654000000002,4864.654000000002,null,0,0,0,4864.654000000002,4864.654000000002,1]
["1","09","03","12","19","  ","UH - Tunnel Construction                                    ",0,0,0,730372.7640000004,730372.7640000004,null,0,0,0,690033.5696992008,690033.5696992008,1]
["1","09","03","12","20","  ","UH - Project Close Out                                      ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","13","  ","  ","X-Ray - Transport & Diagnostic Hall (XRTD)                  ",0,0,0,1084174.437799999,-315348.9221999994,null,0,0,0,1084174.437799999,1084174.437799999]
["1","09","03","13","01","  ","XRTD - Site Preparation/General Requirements                ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","13","02","  ","XRTD - Site Construction                                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","13","03","  ","XRTD - Concrete                                             ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","13","04","  ","Utilities                                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","13","05","  ","HVAC                                                        ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","13","06","  ","Special System - Fire Protection                            ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","13","07","  ","Interior                                                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","13","10","  ","Project Close Out Central Laboratory Office Complex (CLOC)  ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","13","15","  ","XRTD - Mechanical                                           ",0,0,0,60249.301800000074,60249.301800000074,null,0,0,0,60249.301800000074,60249.301800000074,1]
["1","09","03","13","16","  ","XRTD - Electrical                                           ",0,0,0,160828.23460000008,160828.23460000008,null,0,0,0,160828.23460000008,160828.23460000008,1]
["1","09","03","13","17","  ","XRTD - Others (include Div 4, and 6 through 14)             ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","13","19","  ","XRTD - Tunnel Construction                                  ",0,0,0,863096.9013999989,-536426.4585999995,null,0,0,0,863096.9013999989,863096.9013999989,1]
["1","09","03","13","20","  ","XRTD - Project Close Out                                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","14","  ","  ","Far Experimental Hall (FEH)                                 ",0,0,0,1652957.3936000005,1652957.3936000005,null,0,0,0,1567270.6846080008,1567270.6846080008]
["1","09","03","14","01","  ","FEH - Site Preparation/General Requirements                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","14","02","  ","FEH - Site Construction                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","14","03","  ","FEH - Concrete                                              ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","14","05","  ","FEH - Metals                                                ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","14","15","  ","FEH - Mechanical                                            ",0,0,0,298660.7402000001,298660.7402000001,null,0,0,0,298660.7402000001,298660.7402000001,1]
["1","09","03","14","16","  ","FEH - Electrical                                            ",0,0,0,152521.67200000002,152521.67200000002,null,0,0,0,152521.67200000002,152521.67200000002,1]
["1","09","03","14","17","  ","FEH - Others (include Div 4, and 6 through 14)              ",0,0,0,94909.37340000004,94909.37340000004,null,0,0,0,94909.37340000004,94909.37340000004,1]
["1","09","03","14","18","  ","FEH - Access Tunnel                                         ",0,0,0,497971.6623999998,497971.6623999998,null,0,0,0,412284.95340800006,412284.95340800006,1]
["1","09","03","14","19","  ","FEH - Tunnel Construction                                   ",0,0,0,608893.9456000007,608893.9456000007,null,0,0,0,608893.9456000007,608893.9456000007,1]
["1","09","03","14","20","  ","FEH - Project Close Out                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","15","  ","  ","BTH Service Buildings 2.1, 2.2, and 2.3 (SB BTH)            ",0,0,0,575232.8385196428,-253358.2248000002,null,0,0,0,574491.0136396429,574491.0136396429]
["1","09","03","15","03","  ","SB BTH - Concrete                                           ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","15","05","  ","SB BTH - Metals                                             ",0,0,0,23004.511200000008,-114548,null,0,0,0,23004.511200000008,23004.511200000008,1]
["1","09","03","15","15","  ","SB BTH - Mechanical                                         ",0,0,0,240631.12525714282,-38959.6176,null,0,0,0,240631.12525714282,240631.12525714282,1]
["1","09","03","15","16","  ","SB BTH - Electrical                                         ",0,0,0,310868.29675,-96830.6072000002,null,0,0,0,310126.47187,310126.47187,1]
["1","09","03","15","17","  ","SB BTH - Others (include Div 4, and 6 through 14            ",0,0,0,728.9053124999627,-3020,null,0,0,0,728.9053124999627,728.9053124999627,1]
["1","09","03","15","20","  ","SB BTH - Project Close Out                                  ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","16","  ","  ","UH Service Building 3.1 (SB UH)                             ",0,0,0,277351.1352,-711620.3847999999,null,0,0,0,277015.26436,277015.26436]
["1","09","03","16","01","  ","SB UH - Site Preparation                                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","16","03","  ","SB UH - Concrete                                            ",0,0,0,17832.554400000023,17832.554400000023,null,0,0,0,17832.554400000023,17832.554400000023,1]
["1","09","03","16","05","  ","SB UH - Metals                                              ",0,0,0,2013.8784000000014,2013.8784000000014,null,0,0,0,2013.8784000000014,2013.8784000000014,1]
["1","09","03","16","15","  ","SB UH - Mechanical                                          ",0,0,0,165372.53839999996,-428227.46160000004,null,0,0,0,165372.53839999996,165372.53839999996,1]
["1","09","03","16","16","  ","SB UH - Electrical                                          ",0,0,0,91948.12320000003,-303423.3968,null,0,0,0,91612.25235999998,91612.25235999998,1]
["1","09","03","16","17","  ","SB UH - Others (include Div 4, and 6 through 14)            ",0,0,0,184.04080000001704,184.04080000001704,null,0,0,0,184.04080000001704,184.04080000001704,1]
["1","09","03","16","20","  ","SB UH - Project Close Out                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","17","  ","  ","FEH Service Building 8.1 (FEH SB)                           ",0,0,0,221505.65479999996,221505.65479999996,null,0,0,0,221505.65479999996,221505.65479999996]
["1","09","03","17","01","  ","SB FEH - Site Preparation                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","17","03","  ","SB FEH - Concrete                                           ",0,0,0,156179.44219999993,156179.44219999993,null,0,0,0,156179.44219999993,156179.44219999993,1]
["1","09","03","17","05","  ","SB FEH - Metals                                             ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","17","15","  ","SB FEH - Mechanical                                         ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","17","16","  ","SB FEH - Electrical                                         ",0,0,0,65326.21260000003,65326.21260000003,null,0,0,0,65326.21260000003,65326.21260000003,1]
["1","09","03","17","17","  ","SB FEH - Others (include Div 4, and 6 through 14            ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","17","20","  ","SB FEH - Project Close Out                                  ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","18","  ","  ","NEH Central Utility Plant (CUP)                             ",0,0,0,934373.1588829268,1397707.7270000007,null,0,0,0,926838.8853181265,926838.8853181265]
["1","09","03","18","01","  ","CUP - Site Preparation/General Requirements                 ",0,0,0,641.1743999999999,641.1743999999999,null,0,0,0,126.12080000000003,126.12080000000003,1]
["1","09","03","18","02","  ","CUP - Site Construction                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","18","03","  ","CUP - Concrete                                              ",0,0,0,99632.68080000009,99632.68080000009,null,0,0,0,99632.68080000009,99632.68080000009,1]
["1","09","03","18","05","  ","CUP - Metals                                                ",0,0,0,9584.43188292683,-44986,null,0,0,0,9584.43188292683,9584.43188292683,1]
["1","09","03","18","15","  ","CUP - Mechanical                                            ",0,0,0,410019.82960000006,1338063.8296,null,0,0,0,409036.3045600001,409036.3045600001,1]
["1","09","03","18","16","  ","CUP - Electrical                                            ",0,0,0,304365.3923999998,-443580.6075999995,null,0,0,0,298329.6974751996,298329.6974751996,1]
["1","09","03","18","17","  ","CUP - Others (include Div 4, and 6 through 14)              ",0,0,0,110129.64980000001,447936.6498,null,0,0,0,110129.64980000001,110129.64980000001,1]
["1","09","03","18","20","  ","CUP - Project Close Out                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","19","  ","  ","SLAC Space Renovation for LCLS Ops                          ",0,0,0,52364.78693338006,-7982.643999999971,null,0,0,0,52364.78693338006,52364.78693338006]
["1","09","03","19","01","  ","ED&I of SLAC Space Renovation for LCLS Ops                  ",0,0,0,52364.78693338006,-7982.643999999971,null,0,0,0,52364.78693338006,52364.78693338006,1]
["1","09","03","19","02","  ","Construction of SLAC Space Renovation for LCLS Ops          ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","20","  ","  ","Construction Credits and Debits                             ",0,0,0,0,0,null,0,0,0,0,0]
["1","09","03","20","01","  ","Reduction for Subcontractor Work in Deleting CLOC           ",0,0,0,0,0,null,0,0,0,0,0,1]
["1","09","03","20","02","  ","Bulletin #2 Changes                                         ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","  ","  ","  ","  ","  ","LCLS PROJECT - R&D, SPARES, COMMISSIONING                   ",11200,1346687,1281036.533445022,1971809.1394549431,2990813.17225974,null,19826.2,1590641.73,2221961.7767756074,2226905.455229545,4448867.232005152]
["2","01","  ","  ","  ","  ","LCLS PROJECT MGMT, PLANNING & ADMN (OPC)                    ",20379,1537619,2229856.924315444,1635821.6207823635,4118275.9865470086,null,27803.2,1679047.73,3035486.1390808444,1784335.6289226308,4819821.768003475]
["2","01","01","  ","  ","  ","Physics Support (OPC)                                       ",5627,16136,530166.0186240452,15742.999566618819,530166.0186240452,null,10820.2,43136,1093556.7948985444,39220.26565535687,1132777.0605539014]
["2","01","01","01","  ","  ","LCLS Commissioning Management                               ",0,0,-3975.493101309752,0,-3975.493101309752,null,433.44,0,58276.8908987405,0,58276.8908987405,1]
["2","01","01","02","  ","  ","Injector Physics                                            ",-1338,0,-118815.7030100961,0,-118815.7030100961,null,-1006.12,0,-80349.24564938701,0,-80349.24564938701,1]
["2","01","01","03","  ","  ","Linac Physics                                               ",-298,0,-28444.091146944207,0,-28444.091146944207,null,0,0,-4014.847349304182,0,-4014.847349304182,1]
["2","01","01","04","  ","  ","Undulator Physics                                           ",-298,0,-28444.091146944207,0,-28444.091146944207,null,0,0,-4014.847349304182,0,-4014.847349304182,1]
["2","01","01","05","  ","  ","X-Ray Transport Physics                                     ",0,0,-3975.493101309752,0,-3975.493101309752,null,433.44,0,58276.8908987405,0,58276.8908987405,1]
["2","01","01","06","  ","  ","X-Ray Physics Commissioning                                 ",0,0,-4023.0009939708398,0,-4023.0009939708398,null,0,0,-4023.0009939708398,0,-4023.0009939708398,1]
["2","01","01","07","  ","  ","Conventional Facilities Physics                             ",2638,0,378097.3875947343,0,378097.3875947343,null,2936,0,419221.89609299426,0,419221.89609299426,1]
["2","01","01","08","  ","  ","Consulting Physics (Collaboration)                          ",0,16136,0,15742.999566618819,0,null,0,43136,0,39220.26565535687,39220.26565535687,1]
["2","01","01","09","  ","  ","Consulting Physics (SLAC)                                   ",4923,0,343721.99663119554,0,343721.99663119554,null,7590,0,591906.1674512948,0,591906.1674512948,1]
["2","01","01","10","  ","  ","Global Controls Physics Liaison                             ",0,0,-3975.493101309752,0,-3975.493101309752,null,433.44,0,58276.8908987405,0,58276.8908987405,1]
["2","01","02","  ","  ","  ","R&D Studies & Prototyping                                   ",0,0,0,0,0,null,0,0,0,0,0]
["2","01","02","01","  ","  ","R&D Studies & Prototyping                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","01","03","  ","  ","  ","Project Mgmnt, Planning and Admn - M&S (OPC)                ",14752,1521483,1699690.9056913988,1620078.6212157446,3588109.967922963,null,16983,1635911.73,1941929.3441823,1745115.3632672739,3687044.707449574]
["2","01","03","01","  ","  ","SLAC Project Office - General                               ",9561,0,1126978.3831427349,0,1126978.3831427349,null,11198,0,1325012.606651676,0,1325012.606651676,1]
["2","01","03","02","  ","  ","SLAC Project Support                                        ",5191,882750,572712.522548664,971106.2472570247,1803750.051573097,null,5785,975630,616916.737530624,1069113.223257025,1686029.960787649,1]
["2","01","03","03","  ","  ","Project Mgmnt, Planning and Admn - M&S (OPC)                ",0,638733,0,648972.3739587199,657381.5332071315,null,0,660281.73,0,676002.1400102489,676002.1400102489,1]
["2","01","03","05","  ","  ","X-Ray Transport Physics                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","01","03","06","  ","  ","X-Ray Endstation Physics                                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","01","03","07","  ","  ","Conventional Facilities Physics                             ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","01","03","08","  ","  ","Consulting Physics (Collaboration)                          ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","01","03","09","  ","  ","Consulting Physics (SLAC)                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","01","03","10","  ","  ","Global Controls Physics Liaison                             ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","01","03","11","  ","  "," Physics Commissioning Support - General                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","  ","  ","  ","  ","INJECTOR SYSTEM (OPC)                                       ",0,0,2367.0682610370277,2060.5093325235357,-622113.053327763,null,0,0,649.0163796378765,201.6537750674761,850.6701547050616]
["2","02","01","  ","  ","  ","Injector System Management & Integration                    ",0,0,0,0,0,null,0,0,0,0,0]
["2","02","01","01","  ","  ","Injector System Integration Effort / M&S                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","01","02","  ","  ","High level Application Software                             ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","01","03","  ","  ","Feedback Software                                           ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","03","  ","  ","  ","Injector Lasers                                             ",0,0,0,0,-541317.6,null,0,0,0,0,0]
["2","02","03","01","  ","  ","Drive Laser Prototyping                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","03","02","  ","  ","Drive Laser System                                          ",0,0,0,0,-541317.6,null,0,0,0,0,0,1]
["2","02","03","03","  ","  ","Drive Laser Diagnostics                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","03","04","  ","  ","Timing Stability Monitoring                                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","03","05","  ","  ","Steering Stability Feedback & Msmts                         ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","03","06","  ","  ","Pre Amp Low Power Comp                                      ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","03","07","  ","  ","Transport to Tunnel & Relay Optics                          ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","03","08","  ","  ","UV Launch, Conditioning & Diagnostics                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","03","09","  ","  ","Load Lock Transport System                                  ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","03","10","  ","  ","Visible Optical Transport & Optics                          ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","03","11","  ","  ","LB Infrastructure & LB System Wide Items                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","03","12","  ","  ","Alignment Laser                                             ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","03","13","  ","  ","Light path to Streak Camera                                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","03","14","  ","  ","LSR HTR - Beam Conditioning Optics (Laser Bay)              ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","03","15","  ","  ","LSR HTR - Transport Optics (Bay to Tunnel)                  ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","03","16","  ","  ","LSR HTR - Photon Beam Diagnostics                           ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","04","  ","  ","  ","Injector RF Subsystem                                       ",0,0,1502.940358656604,1808.1710883720953,104682.5067586566,null,0,0,0,0,0]
["2","02","04","01","  ","  ","RF Gun & Load Lock                                          ",0,0,1502.940358656604,329.22239999999874,1832.1627586566028,null,0,0,0,0,0]
["2","02","04","01","01","  ","RF Gun                                                      ",0,0,1502.940358656604,329.22239999999874,1832.1627586566028,null,0,0,0,0,0,1]
["2","02","04","01","02","  ","RF Gun Supports                                             ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","04","01","03","  ","Gun Load Lock                                               ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","04","01","04","  ","Gun Load Lock Supports                                      ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","04","01","05","  ","Gun Solenoid                                                ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","04","01","06","  ","Gun Solenoid Supports                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","04","01","07","  ","Gun RF Feed                                                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","04","01","08","  ","Gun RF Feed Supports                                        ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","04","02","  ","  ","Cathode Processing (CP) Station                             ",0,0,0,0,0,null,0,0,0,0,0]
["2","02","04","02","01","  ","CP Cathode Assembly & Supports                              ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","04","02","02","  ","CP Load Lock                                                ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","04","02","03","  ","CP Load Lock Supports                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","04","02","04","  ","CP Station                                                  ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","04","02","05","  ","Cathode Lab Infrastructure                                  ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","04","03","  ","  ","S-Band Low Level System                                     ",0,0,0,0,0,null,0,0,0,0,0]
["2","02","04","03","01","  ","S-Band LL Controls Timing System                            ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","04","04","  ","  ","S-Band High Power System                                    "]
["2","02","04","05","  ","  ","Injector RF Waveguide Subsystem                             ",0,0,0,1478.9486883720965,102850.344,null,0,0,0,0,0]
["2","02","04","05","01","  ","RF Waveguides                                               ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","04","05","02","  ","RF Waveguide Supports                                       ",0,0,0,1478.9486883720965,102850.344,null,0,0,0,0,0,1]
["2","02","04","06","  ","  ","Injector Linac Structures                                   ",0,0,0,0,0,null,0,0,0,0,0]
["2","02","04","06","01","  ","L0-1 Structure Assembly                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","04","06","02","  ","L0-2 Structure Assembly                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","04","06","03","  ","Major Linac Support                                         ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","04","06","04","  ","GTL RF Phase Cavity                                         ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","04","06","05","  ","LTDL1 RF Kicker                                             ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","05","  ","  ","  ","Injector Magnets & Supports                                 ",0,0,0,0,0,null,0,0,0,0,0]
["2","02","05","01","  ","  ","Injector Dipoles                                            ",0,0,0,0,0,null,0,0,0,0,0]
["2","02","05","01","01","  ","DL1 B01 & B02 Dipoles                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","05","01","02","  ","SAB Spectrometer Dipole                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","05","01","03","  ","Chicane                                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","05","02","  ","  ","Injector Quadrupoles                                        ",0,0,0,0,0,null,0,0,0,0,0]
["2","02","05","02","01","  ","L0-1TL0-2 Quadrupoles ( )                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","05","02","02","  ","LTDL1 Quadrupoles ( )                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","05","02","03","  ","DL1 QB Quadrupole                                           ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","05","02","04","  ","DL1TL Quadrupoles ( )                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","05","02","05","  ","SAB Quadrupoles ( )                                         ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","05","03","  ","  ","Injector Steering Coils                                     ",0,0,0,0,0,null,0,0,0,0,0]
["2","02","05","03","01","  ","GTL Steering Coils ( )X-Y (SC1)                             ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","05","03","02","  ","L0-1TL0-2 Linac Steering Coils ( )                          ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","05","03","03","  ","LTDL1 Steering Coils ( )X-Y                                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","05","03","04","  ","DL1TL Steering Coils ( X-Y Assys)                           ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","05","03","05","  ","SAB Steering Coils ( )                                      ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","05","04","  ","  ","Linac Solenoid & Supports                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","05","05","  ","  ","Injector Laser Heater Subsystem                             ",0,0,0,0,0,null,0,0,0,0,0]
["2","02","05","05","01","  ","System Design & Optimization                                ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","05","05","02","  ","Undulator                                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","06","  ","  ","  ","Injector Vacuum & Supports                                  ",0,0,0,0,0,null,0,0,0,0,0]
["2","02","06","01","  ","  ","GTL Vacuum Components                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","06","02","  ","  ","GTL Supports                                                ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","06","03","  ","  ","GTL Pumping & Optic Chamber                                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","06","04","  ","  ","L0-1TL0-2 Vacuum Components                                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","06","05","  ","  ","L0-1TL0-2 Major tube support structure                      ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","06","06","  ","  ","LTDL1 Minor Tube Supports                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","06","07","  ","  ","DL1 Supports                                                ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","06","08","  ","  ","DL1 Vacuum Chamber                                          ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","06","09","  ","  ","DL1TL Vacuum Components                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","06","10","  ","  ","SAB Vacuum Chamber and Components                           ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","06","11","  ","  ","SAB Supports                                                ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","07","  ","  ","  ","Injector Diagnostics                                        ",0,0,0,0,0,null,0,0,0,0,0]
["2","02","07","01","  ","  ","Injector Beam Position Monitors                             ",0,0,0,0,0,null,0,0,0,0,0]
["2","02","07","01","01","  ","GTL BPMs ( )                                                ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","07","01","02","  ","Gun Spectrometer (GS) Assembly                              ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","07","01","03","  ","L0-1TL0-2 BPMs ( )                                          ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","07","01","04","  ","LTDL1 BPMs ( )                                              ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","07","01","05","  ","DL1TL BPMs ( )                                              ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","07","01","06","  ","SAB BPM ( )                                                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","07","02","  ","  ","Injector Current Monitors                                   ",0,0,0,0,0,null,0,0,0,0,0]
["2","02","07","02","01","  ","GTL Current Monitors ( )                                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","07","02","02","  ","L0-1TL0-2 Current Monitor ( )                               ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","07","02","03","  ","LTDL1 Current Monitors ( )                                  ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","07","02","04","  ","DL1TL Current Monitor ( )                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","07","02","05","  ","SAB Current Monitor ( )                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","07","03","  ","  ","Injector Bunch Length Monitors                              ",0,0,0,0,0,null,0,0,0,0,0]
["2","02","07","03","01","  ","GTL E/O (EO1)                                               ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","07","03","02","  ","LTDL1 E/O EO2                                               ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","07","03","03","  ","DL1TL EO3                                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","07","04","  ","  ","Injector Profile Monitors                                   ",0,0,0,0,0,null,0,0,0,0,0]
["2","02","07","04","01","  ","GTL Faraday Cup/YAG1                                        ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","07","04","02","  ","GTL YAG ( )                                                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","07","04","03","  ","L0-1TL0-2 OTR/YAG ( )                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","07","04","04","  ","LTDL1 OTR(5)/YAG ( )                                        ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","07","04","05","  ","DL1 OTR                                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","07","04","06","  ","DL1TL OTR                                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","07","04","07","  ","SAB YAG                                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","07","04","08","  ","SAB Beam Dump and Shielding                                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","07","05","  ","  ","Injector Wire Scanners                                      ",0,0,0,0,0,null,0,0,0,0,0]
["2","02","07","05","01","  ","LTDL1 Wire Scanners ( )                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","07","05","02","  ","DL1 Wire Scanner                                            ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","07","06","  ","  ","LSR HTR - Electron Beam Diagnostics                         ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","07","07","  ","  ","PPS Stopper                                                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","08","  ","  ","  ","Injector System Emittance Enhancement                       ",0,0,0,0,0,null,0,0,0,0,0]
["2","02","08","01","  ","  ","Heater Integration                                          ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","08","02","  ","  ","Heater Laser & Optics                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","08","03","  ","  ","Heater Magnets                                              ",0,0,0,0,0,null,0,0,0,0,0]
["2","02","08","03","01","  ","Heater Dipoles                                              ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","08","03","02","  ","Heater Undulator                                            ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","08","04","  ","  ","Heater Vacuum                                               ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","08","05","  ","  ","Heater Diagnostics                                          ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","08","06","  ","  ","Heater Install & Align                                      ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","17","  ","  ","  ","Injector System Commissioning                               ",0,0,864.1279023804236,252.33824415144045,-185477.9600864196,null,0,0,649.0163796378765,201.6537750674761,850.6701547050616]
["2","02","17","01","  ","  ","Controls Commissioning                                      ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","17","02","  ","  ","Drive Laser Commissioning                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","17","03","  ","  ","RF Conditioning                                             ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","17","04","  ","  ","RF Gun Operation with Beam                                  ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","17","05","  ","  ","L0-1&L0-2 Commissioning                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","17","06","  ","  ","L0&SAB Commissioning                                        ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","17","07","  ","  ","DL1 Commissioning                                           ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","17","08","  ","  ","Injector Optimization                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","02","17","10","  ","  ","Injector System Commissioning                               ",0,0,864.1279023804236,252.33824415144045,-185477.9600864196,null,0,0,649.0163796378765,201.6537750674761,850.6701547050616,1]
["2","03","  ","  ","  ","  ","LINAC SYSTEM (OPC)                                          ",0,0,3788.153493749094,1224.9902326914598,-109623.28389062837,null,0,0,3908.7969507300295,1225.3150232514308,5134.111973981606]
["2","03","01","  ","  ","  ","Linac System Mgmt & Integration                             ",0,0,-319.8628885918297,0,-319.8628885918297,null,0,0,-319.8628885918297,0,-319.8628885918297]
["2","03","01","01","  ","  ","Linac System Mgmt & Integration                             ",0,0,-319.8628885918297,0,-319.8628885918297,null,0,0,-319.8628885918297,0,-319.8628885918297,1]
["2","03","01","02","  ","  ","Linac Controls Integration                                  ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","01","03","  ","  ","Travel                                                      ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","01","04","  ","  ","Linac Management                                            ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","03","  ","  ","  ","Linac Magnets & Supports                                    ",0,0,0,0,0,null,0,0,0,0,0]
["2","03","03","01","  ","  ","Bend Magnet (BX1_BC1)                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","03","02","  ","  ","Bend Magnet (BX3_LTU)                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","03","03","  ","  ","Bend Magnet (BX2_BC2)                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","03","04","  ","  ","Bend Magnet (BY_LTU)                                        ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","03","05","  ","  ","Quad Magnet (Quad_LTU)                                      ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","03","07","  ","  ","Quad Magnet (QE)                                            ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","03","08","  ","  ","Corrector Magnet (Type 4)                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","03","09","  ","  ","Bend Magnet (BYD_LTU)                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","03","10","  ","  ","Quad Magnet (QA)                                            ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","03","11","  ","  ","Bend Magnet (BYPM_LTU)                                      ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","03","12","  ","  ","Bend Magnet (BYKIK_LTU)                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","03","13","  ","  ","Bend Magnet (BYW_LTU)                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","04","  ","  ","  ","Linac Vacuum Subsystem                                      ",0,0,0,0,0,null,0,0,0,0,0]
["2","03","04","01","  ","  ","Linac Vacuum Subsystem Operations Equip                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","04","02","  ","  ","Linac Beamline Vacuum System                                ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","04","03","  ","  ","BC1 Vacuum System                                           ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","04","04","  ","  ","BC2 Vacuum System                                           ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","04","05","  ","  ","Linac to Undulator (LTU) Vacuum System                      ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","04","06","  ","  ","Dumpline Vacuum System                                      ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","04","07","  ","  ","Vacuum Undulator Interface                                  ",0,0,0,0,0,null,0,0,0,0,0]
["2","03","04","07","01","  ","Entrance Assembly Section                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","04","07","02","  ","Exit Assembly Section                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","05","  ","  ","  ","Linac Electron Diagnostics                                  ",0,0,0,0,0,null,0,0,0,0,0]
["2","03","05","01","  ","  ","Wire Scanners                                               ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","05","02","  ","  ","Beam Position Monitors                                      ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","05","03","  ","  ","Toroids Beam Charge                                         ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","05","04","  ","  ","Stoppers Tune Up Dump                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","05","05","  ","  ","Profile Monitors                                            ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","05","06","  ","  ","E/O Bunch Length Monitors                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","05","07","  ","  ","Bunch Length Monitors                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","05","08","  ","  ","Beam Loss Monitors                                          ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","05","09","  ","  ","Single Beam Dump                                            ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","05","10","  ","  ","Electron Safety Beam Dump                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","05","11","  ","  ","Protection Collimators                                      ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","05","12","  ","  ","Movable Collimators                                         ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","05","13","  ","  ","Safety Dump                                                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","05","14","  ","  ","Charge Monitor (Entrance/Exit Assebmly)                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","06","  ","  ","  ","Linac RF Subsystem                                          ",0,0,0,0,0,null,0,0,0,0,0]
["2","03","06","02","  ","  ","S-Band High Power System                                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","06","03","  ","  ","S-Band Structures                                           ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","06","04","  ","  ","X-Band Low Level System                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","06","05","  ","  ","X-Band High Power System                                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","06","06","  ","  ","X-Band Structures                                           ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","06","07","  ","  ","RF Distribution System                                      ",0,0,0,0,0,null,0,0,0,0,0]
["2","03","06","07","01","  ","Modulator                                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","06","07","02","  ","Solid State Sub Booster                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","06","07","05","  ","Bunch Length Electronics                                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","06","07","07","  ","RF Distribution L2 & L3                                     ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","06","07","08","  ","RF Fiber Optics Electronics                                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","07","  ","  ","  ","Linac System Commissioning                                  ",0,0,4108.016382340924,1224.9902326914598,-109303.42100203654,null,0,0,4228.659839321859,1225.3150232514308,5453.9748625734355]
["2","03","07","01","  ","  ","Linac L01 System Commissioning                              ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","07","02","  ","  ","Linac BC1 System Commissioning                              ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","07","03","  ","  ","Linac L02 System Commissioning                              ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","07","04","  ","  ","Linac BC2 System Commissioning                              ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","07","05","  ","  ","Linac L03 System Commissioning                              ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","07","06","  ","  ","Linac LTU System Commissioning                              ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","07","07","  ","  ","Linac E-Dump System Commissioining                          ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","07","08","  ","  ","Linac Undulator Interface                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","03","07","10","  ","  ","Linac System Commissioning                                  ",0,0,4108.016382340924,1224.9902326914598,-109303.42100203654,null,0,0,4228.659839321859,1225.3150232514308,5453.9748625734355,1]
["2","04","  ","  ","  ","  ","UNDULATOR SYSTEM (OPC)                                      ",-9179,-190932,-910400.3542460151,330979.90379010304,-441630.23814568465,null,-7977,-88406,-773506.917256412,439556.54643133364,-333950.3708250781]
["2","04","01","  ","  ","  ","Undulator System Management & Integration                   ",-7977,-81602,-773437.6857633013,-81344.9435231624,-745452.747958493,null,-7977,-51602,-773437.6857633013,-51344.943523162365,-824782.6292864636]
["2","04","01","01","  ","  ","Undulator System Mgmt & Integration                         ",-7977,-81602,-773437.6857633013,-81344.9435231624,-745452.747958493,null,-7977,-51602,-773437.6857633013,-51344.943523162365,-824782.6292864636,1]
["2","04","03","  ","  ","  ","Undulator Magnet & Support                                  ",-32,-69326,-3310.8172932835296,455444.367357995,452133.5500647115,null,0,-36800,-12.271923134394456,488980.363857195,488968.0919340606]
["2","04","03","01","  ","  ","Undulator Magnets & Support-Mgmt & Integration              ",0,0,83.0121651655063,0,83.0121651655063,null,0,0,83.0121651655063,0,83.0121651655063,1]
["2","04","03","02","  ","  ","First Prototype Undulator & Mfg Plan                        ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","04","03","03","  ","  ","1st Article Undulators & Long Lead Procurements             ",0,0,-21.32194738095859,0,-21.32194738095859,null,0,0,-21.32194738095859,0,-21.32194738095859,1]
["2","04","03","04","  ","  ","Production Undulator                                        ",0,-111126,-73.96214091894217,417288.140439595,417214.17829867604,null,0,-80000,-73.96214091894217,449254.542439595,449180.58029867604,1]
["2","04","03","05","  ","  ","Focusing Magnets                                            ",0,-1400,0,-1631.3826815999928,-1631.3826815999928,null,0,0,0,-61.788182399992365,-61.788182399992365,1]
["2","04","03","06","  ","  ","Undulator Magnetic Measurement Facility (SLAC)              ",-32,0,-3298.545370149135,0,-3298.545370149135,null,0,0,0,0,0,1]
["2","04","03","08","  ","  ","Fixed Supports                                              ",0,43200,0,39787.6096,39787.6096,null,0,43200,0,39787.6096,39787.6096,1]
["2","04","04","  ","  ","  ","Vacuum System                                               ",0,0,-46.45333676234259,393.312897766657,346.8595610043144,null,0,0,-46.45333676234259,393.312897766657,346.8595610043144]
["2","04","04","02","  ","  ","Undulator Vacuum Chamber Assembly                           ",0,0,0,0,0,null,0,0,0,0,0]
["2","04","04","02","01","  ","Surface Roughness Minimization                              ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","04","04","02","03","  ","Materials Study for AC Conductivity                         ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","04","04","03","  ","  ","Beam-line Bellows Module Assembly                           ",0,0,0,400.93489581465656,400.93489581465656,null,0,0,0,400.93489581465656,400.93489581465656,1]
["2","04","04","04","  ","  ","Single Undulator Test (SUV) Vacuum                          ",0,0,-46.45333676234259,0,-46.45333676234259,null,0,0,-46.45333676234259,0,-46.45333676234259,1]
["2","04","04","05","  ","  ","Short Diagnostic Break (SDB) Assembly                       ",0,0,0,-1.3263717599998017,-1.3263717599998017,null,0,0,0,-1.3263717599998017,-1.3263717599998017,1]
["2","04","04","06","  ","  ","Long Diagnostic Break (LDB) Assembly                        ",0,0,0,-6.295626287999767,-6.295626287999767,null,0,0,0,-6.295626287999767,-6.295626287999767,1]
["2","04","04","07","  ","  ","Entrance Section Assembly                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","04","04","08","  ","  ","Exit Section Assembly                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","04","04","09","  ","  ","Baking System                                               ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","04","05","  ","  ","  ","Undulator System Diagnostics [OPC]                          ",-1170,-40004,-133506.01675896248,-43512.83294249624,-148558.51871920226,null,0,-4,88.87486049145286,1527.813199534361,1616.6880600258028]
["2","04","05","02","  ","  ","Undulator Line Diagnostics                                  ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","04","05","03","  ","  ","High-Power X-Ray and Profile Diagnostics (HPD)              ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","04","05","04","  ","  ","End-of-Undulator(EOU) X-ray and Profile diagnost            ",-1170,-40000,-133594.89161945393,-45040.6461420306,-133594.89161945393,null,0,0,0,0,0,1]
["2","04","05","05","  ","  ","RFBPM                                                       ",0,0,62.789428674201645,562.7091868461139,-15954.816544253801,null,0,0,62.789428674201645,562.7091868461139,625.4986155203078,1]
["2","04","05","06","  ","  ","Beam Finder Wire                                            ",0,-4,21.830077057824155,520.1627000371154,541.9927770949362,null,0,-4,21.830077057824155,520.1627000371154,541.9927770949362,1]
["2","04","05","07","  ","  ","Charge Monitor (CM)                                         ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","04","05","08","  ","  ","Beam Loss Monitoring                                        ",0,0,0,444.94131265113174,444.94131265113174,null,0,0,0,444.94131265113174,444.94131265113174,1]
["2","04","05","09","  ","  ","Radiation Detection Monitor (RDM)                           ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","04","05","10","  ","  ","Single Undulator Test (SUT) Diagnostics                     ",0,0,4.255354759427064,0,4.255354759427064,null,0,0,4.255354759427064,0,4.255354759427064,1]
["2","04","06","  ","  ","  ","Undulator System Commissioning                              ",0,0,-99.38109370530583,0,-99.38109370530583,null,0,0,-99.38109370530583,0,-99.38109370530583]
["2","04","06","01","  ","  ","Undulator System Commissioning                              ",0,0,-99.38109370530583,0,-99.38109370530583,null,0,0,-99.38109370530583,0,-99.38109370530583,1]
["2","05","  ","  ","  ","  ","X-RAY TRANSPORT & DIAGNOSTICS SYSTEMS (OPC)                 ",0,0,0,1480.518000000011,1480.518000000011,null,0,0,0,1480.518000000011,1480.518000000011]
["2","05","01","  ","  ","  ","System Management & Integration                             ",0,0,0,0,0,null,0,0,0,0,0]
["2","05","01","01","  ","  ","Management                                                  ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","05","03","  ","  ","  ","Mechanical & Vacuum Subsystem                               ",0,0,0,0,0,null,0,0,0,0,0]
["2","05","03","01","  ","  ","Vacuum Systems Engineering                                  ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","05","03","02","  ","  ","Mech/Vac Front End                                          ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","05","03","03","  ","  ","Mech/Vac Near Hall                                          ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","05","03","04","  ","  ","Mech/Vac Tunnel                                             ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","05","03","05","  ","  ","Mech/Vac Far Hall                                           ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","05","04","  ","  ","  ","Optical Subsystem                                           ",0,0,0,0,0,null,0,0,0,0,0]
["2","05","04","01","  ","  ","Optical Systems Engineering                                 ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","05","04","02","  ","  ","Facility Optics                                             ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","05","04","03","  ","  ","End Station Optics                                          ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","05","04","04","  ","  ","Crystals & Gratings                                         ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","05","05","  ","  ","  ","Diagnostics Subsystem                                       ",0,0,0,1480.518000000011,1480.518000000011,null,0,0,0,1480.518000000011,1480.518000000011]
["2","05","05","01","  ","  ","Diagnostic Systems Engineering                              ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","05","05","02","  ","  ","Modeling & Simulation                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","05","05","03","  ","  ","Facility Diagnostics                                        ",0,0,0,1480.518000000011,1480.518000000011,null,0,0,0,1480.518000000011,1480.518000000011,1]
["2","05","05","04","  ","  ","Commissioning Diagnostics                                   ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","05","06","  ","  ","  ","X-Ray Transport & Diag. System Commissioning                ",0,0,0,0,0,null,0,0,0,0,0]
["2","05","06","01","  ","  ","X-Ray Transport & Diag. System Commissioning                ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","06","  ","  ","  ","  ","X-RAY END STATION SYSTEMS (OPC)                             ",0,0,-44575.25837919306,241.5973172617687,44423.24307680688,null,0,0,-44575.25837919306,105.79307726176921,-44469.46530193129]
["2","06","01","  ","  ","  ","XE System Mgmt & Integration                                ",0,0,0,0,0,null,0,0,0,0,0]
["2","06","01","01","  ","  ","Management                                                  ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","06","03","  ","  ","  ","Commissioning                                               ",0,0,-44575.25837919306,0,-44575.25837919306,null,0,0,-44575.25837919306,0,-44575.25837919306]
["2","06","03","01","  ","  ","Commissioning - Controls                                    ",0,0,3671.3414760677842,0,3671.3414760677842,null,0,0,3671.3414760677842,0,3671.3414760677842,1]
["2","06","03","02","  ","  ","Commissioning - XES Laser                                   ",0,0,-4038.1657762664254,0,-4038.1657762664254,null,0,0,-4038.1657762664254,0,-4038.1657762664254,1]
["2","06","03","03","  ","  ","Commissioning - AMO Experiment                              ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","06","03","05","  ","  ","Commissioning - 2D X-Ray Detector                           ",0,0,-44208.43407899442,0,-44208.43407899442,null,0,0,-44208.43407899442,0,-44208.43407899442,1]
["2","06","04","  ","  ","  ","Spares                                                      ",0,0,0,0,0,null,0,0,0,0,0]
["2","06","04","01","  ","  ","Spares - PPS Stoppers                                       ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","06","04","02","  ","  ","Spares -                                                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","06","04","03","  ","  ","Spares -                                                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","06","04","04","  ","  ","Spares -                                                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","06","04","05","  ","  ","Spares -                                                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","06","05","  ","  ","  ","X-Ray Detectors                                             ",0,0,0,241.5973172617687,88998.50145599994,null,0,0,0,105.79307726176921,105.79307726176921]
["2","06","05","01","  ","  ","Beam Imaging                                                ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","06","05","02","  ","  ","2-D X-Ray Detector                                          ",0,0,0,241.5973172617687,88998.50145599994,null,0,0,0,105.79307726176921,105.79307726176921]
["2","06","05","02","01","  ","Proto 2 ASIC                                                ",0,0,0,135.80423999999948,135.80423999999948,null,0,0,0,0,0,1]
["2","06","05","02","02","  ","Proto 3 ASIC                                                ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","06","05","02","03","  ","Full Lot Prototype                                          ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","06","05","02","04","  ","500px Detector                                              ",0,0,0,105.79307726176921,88862.69721599994,null,0,0,0,105.79307726176921,105.79307726176921,1]
["2","06","05","02","05","  ","2D X-Ray Detector Commissioning                             ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","06","05","03","  ","  ","Beam Intensity                                              ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","06","05","04","  ","  ","Streak Camera                                               ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","06","07","  ","  ","  ","Atomic Physics                                              ",0,0,0,0,0,null,0,0,0,0,0]
["2","06","07","01","  ","  ","Atomic Physics Samples                                      ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","06","07","02","  ","  ","Atomic Physics Diagnostics                                  ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","06","07","03","  ","  ","Atomic Physics Data Analysis                                ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","06","07","04","  ","  ","Atomic Physics Detectors                                    ",0,0,0,0,0,null,0,0,0,0,0,1]
["2","08","  ","  ","  ","  ","LCLS SYSTEM COMMISSIONING (OPC)                             ",{"$nulls":11},0]
["2","09","  ","  ","  ","  ","CONVENTIONAL FACILITIES (OPC)                               ",{"$nulls":11},0]
["2","09","01","  ","  ","  ","MANAGEMENT INTEGRATION                                      "]
["2","09","03","  ","  ","  ","RSY - CLOC Commissioning                                    ",0,0,0,0,0,null,0,0,0,0,0]
["2","09","03","05","  ","  ","RSY-CLOC Commissioning                                      ",0,0,0,0,0,null,0,0,0,0,0,1]

{"sheet":"CT Only Comparison","index":7,"n_rows":394,"n_cols":19,"rows_kept":394,"cut":false,"hidden":true,"merged":[[0,13,0,14],[0,15,0,17],[1,0,1,5],[0,0,0,5],[0,7,0,8],[0,9,0,11]],"flags":["formulas_cached_only"]}
["WBS Level",{"$nulls":5},"April 2007 CR Rebaseline","Budgeted Quantity",null,"Fully Burdened and Escalated Cost",null,null,null,"Work Rem. Bud. Qtty",null,"Work Rem. Full Burd and Escltd Cost",null,null,"WBS"]
["Run Time: 05-03-07 (3:40 pm)",{"$nulls":5},"Description","Hours","$$","Labor","M&S","Total (No Conting)",null,"Hours","$$","Labor","M&S","Total","CAM"]
["1","2","3","4","5","6"]
[]
["1","  ","  ","  ","  ","  ","LCLS PROJECT - PED & CONSTRUCTION                           ",{"$nulls":11},"                              "]
["1","01","03","05","  ","  ","Global Controls                                             ",0,0,-499.22510755993426,14903.588144297712,-106997.00573155982,null,0,0,2232.72509237146,2238.0105442982167,4470.735636669444,"2G                            "]
["1","01","03","05","01","  ","Global Controls Management                                  ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","01","03","05","02","  ","LLRF Controls                                               ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","01","03","05","03","  ","E-beam Diagnostics & Controls                               ",0,0,10511.601902346592,0,10511.601902346592,null,0,0,16.64749717487996,0,16.64749717487996,"2G                            "]
["1","01","03","05","03","01","Controls - Wire Scanners                                    ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","01","03","05","03","02","Controls - Toroids                                          ",0,0,7440.687479717541,0,7440.687479717541,null,0,0,0,0,0,"2G                            "]
["1","01","03","05","03","03","Controls - Faraday Cups                                     ",0,0,165.3797805660006,0,165.3797805660006,null,0,0,0,0,0,"2G                            "]
["1","01","03","05","03","04","Controls - Tune-Up Dump                                     ",0,0,51.07788405719998,0,51.07788405719998,null,0,0,6.2054921728799854,0,6.2054921728799854,"2G                            "]
["1","01","03","05","03","05","Controls - Profile Monitors                                 ",0,0,36.75615320520001,0,36.75615320520001,null,0,0,0,0,0,"2G                            "]
["1","01","03","05","03","06","Controls - E/O Diagnostics                                  ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","01","03","05","03","07","Controls - BPM                                              ",0,0,1633.6910428655247,0,1633.6910428655247,null,0,0,10.44200500200003,0,10.44200500200003,"2G                            "]
["1","01","03","05","03","08","Controls - Stopppers                                        ",0,0,36.75615320520001,0,36.75615320520001,null,0,0,0,0,0,"2G                            "]
["1","01","03","05","03","09","Controls - Bunch Length Monitors                            ",0,0,636.2203537404021,0,636.2203537404021,null,0,0,0,0,0,"2G                            "]
["1","01","03","05","03","10","Controls - Beam Loss Monitors                               ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","01","03","05","03","11","Controls - Cherenkov Radiation Detector                     ",0,0,36.75615320520001,0,36.75615320520001,null,0,0,0,0,0,"2G                            "]
["1","01","03","05","03","12","Controls - Movable Collimator                               ",0,0,474.27690178440025,0,474.27690178440025,null,0,0,0,0,0,"2G                            "]
["1","01","03","05","04","  ","Laser Controls Design                                       ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","01","03","05","05","  ","Laser Heater Controls                                       ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","01","03","05","06","  ","Timing Controls                                             ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","01","03","05","07","  ","Vacuum Controls                                             ",0,0,170.6089120163997,0,170.6089120163997,null,0,0,0,0,0,"2G                            "]
["1","01","03","05","09","  ","Power Supply Controls                                       ",0,0,2829.2726583475014,0,2829.2726583475014,null,0,0,837.28160088195,0,837.28160088195,"2G                            "]
["1","01","03","05","10","  ","Controls - PPS                                              ",0,0,-15515.542649180454,0,-15515.542649180454,null,0,0,1378.795994314598,0,1378.795994314598,"2G                            "]
["1","01","03","05","11","  ","Controls - MPS                                              ",0,0,0,615.0418560000035,615.0418560000035,null,0,0,0,615.0418560000035,615.0418560000035,"2G                            "]
["1","01","03","05","12","  ","Global Controls Management                                  ",0,0,1023.6239122824045,14288.546288297512,-106089.1985677178,null,0,0,0,1622.9686882982496,1622.9686882980168,"2G                            "]
["1","01","03","05","12","01","Global Controls Management LOE                              ",0,0,1023.6239122824045,10386.937600000063,11410.561512282351,null,0,0,0,0,0,"2G                            "]
["1","01","03","05","12","02","Global Controls Management                                  ",0,0,0,3901.608688298089,-117499.76007999995,null,0,0,0,1622.9686882980313,1622.9686882980313,"2G                            "]
["1","01","03","05","13","  ","SLC Aware IOC                                               ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","01","03","05","14","  ","Controls - S/W Application                                  ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","01","03","05","15","  ","Controls - BCS                                              ",0,0,481.2101566272031,0,481.2101566272031,null,0,0,0,0,0,"2G                            "]
["1","02","02","  ","  ","  ","Injector Controls Subsystem                                 ",-544,-10700,-45645.99521334772,12065.565312000457,-33580.429901346564,null,-80,0,-6702.665578659973,0,-6702.665578659973,"2G                            "]
["1","02","02","01","  ","  ","Personnel Protection Subsystem (PPS)                        ",0,0,1979.8366641768225,599.4559999999983,2579.2926641768136,null,0,0,0,0,0,"2G                            "]
["1","02","02","02","  ","  ","Beam Containment Subsystem (BCS)                            ",0,-10700,2725.277305947442,-5589.612800000003,-2864.3354940526187,null,0,0,223.89114626434457,0,223.89114626434457,"2G                            "]
["1","02","02","03","  ","  ","Machine Protection Subsystem (MPS)                          ",0,0,0,2065.3984000000055,2065.3984000000055,null,0,0,0,0,0,"2G                            "]
["1","02","02","04","  ","  ","Injector Power Conversion                                   ",0,0,316.31223829898227,2601.3120639999834,2917.6243022989947,null,0,0,0,0,0,"2G                            "]
["1","02","02","04","01","  ","Beamline Pwr Supplies - (Dipole Type)                       ",0,0,0,414.0878560000001,414.0878559999983,null,0,0,0,0,0,"2G                            "]
["1","02","02","04","01","01","10kw Power Supply - (Solenoid 1)                            ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","02","02","04","01","02","30kw Power Supply - (Solenoid 2)                            ",0,0,0,414.0878560000001,414.0878560000019,null,0,0,0,0,0,"2G                            "]
["1","02","02","04","01","03","2kw Power Supply - (B0.5 Spect)                             ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","02","02","04","01","04","15kw Power Supply - (B1-2)                                  ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","02","02","04","01","05","15kw Power Supply - (B3 Spect)                              ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","02","02","04","01","06","10kw Power Supply - (New)                                   ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","02","02","04","02","  ","Power Supply Controls                                       ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","02","02","04","03","  ","Beamline Pwr Supplies - (Trim Type)                         ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","02","02","04","03","01","12Amp Power Supply - (MCOR_1)                               ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","02","02","04","03","02","30Amp Power Supply - (MCOR_2)                               ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","02","02","04","03","03","30Amp Power Supply - (MCOR_3)                               ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","02","02","04","03","04","30Amp Power Supply - (MCOR_4)                               ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","02","02","04","04","  ","Beamline Pwr Supply - Misc Hdwr                             ",0,0,316.312238298975,2187.2242079999996,2503.536446298953,null,0,0,0,0,0,"2G                            "]
["1","02","02","04","05","  ","Magnet Interlock Protection System                          ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","02","02","05","  ","  ","LLRF Controls                                               ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","02","02","05","01","  ","Readback & Controls - RF Gun LLRF & Temperature             ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","02","02","05","02","  ","Readback & Controls - L0 LLRF                               ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","02","02","05","03","  ","Readback & Controls - Transverse Cavity LLRF                ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","02","02","05","04","  ","S-Band Cavity Controls                                      ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","02","02","05","05","  ","EO Phase Controls                                           ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","02","02","06","  ","  ","E-Beam Diagnostics Controls                                 ",-544,0,-51614.49366570587,5609.082544000004,-46005.41112170566,null,-80,0,-6996.521944368,0,-6996.521944368,"2G                            "]
["1","02","02","06","01","  ","Controls - Wire Scanners                                    ",0,0,303.5852222832036,727.1946239999961,1030.7798462831852,null,0,0,0,0,0,"2G                            "]
["1","02","02","06","02","  ","Controls - BPM                                              ",0,0,783.1715124431066,2299.867440000002,3083.0389524431084,null,0,0,0,0,0,"2G                            "]
["1","02","02","06","03","  ","Controls - Toroids                                          ",0,0,622.1074418742937,754.7695999999996,1376.8770418742934,null,0,0,0,0,0,"2G                            "]
["1","02","02","06","05","  ","Controls - Profile Monitors                                 ",-32,0,-2762.3487367871994,598.3660799999998,-2163.9826567872005,null,0,0,0,0,0,"2G                            "]
["1","02","02","06","06","  ","Controls - E/O Diagnostics                                  ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","02","02","06","12","  ","Controls - Movable Collimator                               ",-240,0,-20572.240350816,395.09599999999955,-20177.144350816,null,0,0,0,0,0,"2G                            "]
["1","02","02","06","14","  ","Controls - Faraday Cups                                     ",0,0,-6853.0819519008,13.624000000000024,-6839.4579519008,null,0,0,0,0,0,"2G                            "]
["1","02","02","06","15","  ","Controls - Tune-Up Dump                                     ",-160,0,-13446.003263932802,386.92159999999967,-13059.0816639328,null,0,0,0,0,0,"2G                            "]
["1","02","02","06","16","  ","Controls - Cherenkov Radiation Detector                     ",-112,0,-9689.683538869715,433.2432000000008,-9256.440338869717,null,-80,0,-6996.521944368,0,-6996.521944368,"2G                            "]
["1","02","02","08","  ","  ","Timing Controls                                             ",0,0,0,3201.64,3201.64,null,0,0,0,0,0,"2G                            "]
["1","02","02","09","  ","  ","Vacuum Controls                                             ",0,0,695.3503316760107,2702.7291200000036,3398.0794516760216,null,0,0,0,0,0,"2G                            "]
["1","02","02","10","  ","  ","Software & Controls Infrastructure                          ",0,0,0,630.3279840000032,630.3279840000032,null,0,0,0,0,0,"2G                            "]
["1","02","02","10","01","  ","Low Level Application Software                              ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","02","02","10","02","  ","High Level Application Software                             ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","02","02","10","03","  ","Data Communications                                         ",0,0,0,435.96800000000076,435.96800000000076,null,0,0,0,0,0,"2G                            "]
["1","02","02","10","04","  ","Computers & Crates                                          ",0,0,0,194.3599839999997,194.3599839999997,null,0,0,0,0,0,"2G                            "]
["1","02","02","11","  ","  ","EPICS VXI Control Modules                                   ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","02","02","12","  ","  ","Laser Controls                                              ",0,0,181.7566928156557,245.23199999999997,426.9886928156593,null,0,0,0,0,0,"2G                            "]
["1","02","02","12","01","  ","Controls - Alignment Laser                                  ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","02","02","12","02","  ","Controls - Gun Laser                                        ",0,0,181.7566928156557,245.23199999999997,426.9886928156593,null,0,0,0,0,0,"2G                            "]
["1","02","02","13","  ","  ","Laser Heater Controls                                       ",0,0,69.96521944367942,0,69.9652194436785,null,0,0,69.96521944367942,0,69.9652194436785,"2G                            "]
["1","03","02","  ","  ","  ","Linac Controls & Power Conversion Subsystem                 ",-4682,-377800,-415604.29123113304,-392423.77030228823,-731319.9227387793,null,-4452,-377800,-380930.07820939994,-405954.6924318122,-786884.7706412217,"2G                            "]
["1","03","02","01","  ","  ","Personnel Protection System (PPS)                           ",0,0,-344.3364478927979,0,-344.3364478928852,null,0,0,-342.3424310979026,0,-342.3424310980481,"2G                            "]
["1","03","02","02","  ","  ","Beam Containment System (BCS)                               ",0,0,1452.533283279161,0,1452.533283279161,null,0,0,1278.102904778294,0,1278.1029047783231,"2G                            "]
["1","03","02","03","  ","  ","Machine Protection System (MPS)                             ",0,0,0,457.76639999999315,457.76639999999315,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","  ","  ","Linac Power Conversion Subsystem                            ",0,-2800,14006.590319473413,7808.366609704681,98523.09572382504,null,0,-2800,11681.361268122797,794.9208481805399,12476.282116302755,"2G                            "]
["1","03","02","04","01","  ","Beamline Power Supplies - (Dipole Type)                     ",0,0,1532.490044964652,169.76048960001208,1702.2505345644895,null,0,0,1371.5147519411694,169.76048960001208,1541.2752415411524,"2G                            "]
["1","03","02","04","01","01","Power Supply BX11-14                                        ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","01","02","Power Supply BX21-24                                        ",0,0,68.27153087040006,94.2780800000005,162.549610870401,null,0,0,68.27153087040006,94.2780800000005,162.549610870401,"2G                            "]
["1","03","02","04","01","03","Kicker Power Supply BXKIK                                   ",0,0,641.1524713187391,16.773868799999036,657.9263401187345,null,0,0,562.8626651039594,16.773868800000855,579.6365339039621,"2G                            "]
["1","03","02","04","01","04","Power Supply BX31,32,35,36                                  ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","01","05","Power Supply -BY1-2                                         ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","01","06","Kicker Power Supply BYKIK                                   ",0,0,823.0660427754774,58.70854080000208,881.7745835754758,null,0,0,740.3805559667962,58.70854080000208,799.0890967667947,"2G                            "]
["1","03","02","04","01","07","Power Supply BYW1-3                                         ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","01","08","Muon Spoiler Power Supply MUSPLR                            ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","01","09","Powe Supply BYD1-3                                          ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","02","  ","Beamline Power Supplies - (Quad Type)                       ",0,-2000,116.49274569504632,-1982.0488639997202,-1865.5561183054233,null,0,-2000,28.118479371842113,-2080.7411199997296,-2052.622640628717,"2G                            "]
["1","03","02","04","02","06","Q21201-Q21901 Switch Over                                   ",0,0,88.37426632320012,98.69225599999982,187.06652232319993,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","02","07","Q24201-Q24501 Split                                         ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","02","08","Power Supply Q24601                                         ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","02","09","Power Supply  Q24701A,Q24701B                               ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","02","10","Power Supply QM21                                           ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","02","11","Power Supply Q24901A,Q24901B                                ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","02","12","Power Supply QM22                                           ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","02","13","Power Supply Q5                                             ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","02","14","Power Supply Q6                                             ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","02","15","Power Supply QA0                                            ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","02","16","Power Supply Q50Q1,Q50Q2,Q50Q3                              ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","02","17","Power Supply  QVM1                                          ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","02","18","Power Supply  QVM2                                          ",0,-2000,0,-2150.495999999999,-2150.495999999999,null,0,-2000,0,-2150.495999999999,-2150.495999999999,"2G                            "]
["1","03","02","04","02","19","Power Supply  QVM3                                          ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","02","20","Power Supply  QVM4                                          ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","02","21","Power Supply  QVB1-3                                        ",0,0,4.650350253119996,0,4.650350253123179,null,0,0,4.650350253119996,0,4.650350253119541,"2G                            "]
["1","03","02","04","02","22","Power Supply  QDL31-34                                      ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","02","23","Power Supply  QE31-36                                       ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","02","24","Power Supply  QEM1                                          ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","02","25","Power Supply  QEM2                                          ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","02","26","Power Supply  QEM3                                          ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","02","27","Power Supply  QEM4                                          ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","02","28","Power Supply QT11,13,21,23,31,33,41,43                      ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","02","29","Power Supply QT12,22,32,42                                  ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","02","30","Power Supply  QUM1                                          ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","02","31","Power Supply  QUM2                                          ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","02","32","Power Supply  QUM3                                          ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","02","33","Power Supply QUM4                                           ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","02","34","Power Supply QDMP1-2                                        ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","02","35","Power Supply QUE1                                           ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","02","36","Power Supply QUE2                                           ",0,0,4.650350253119996,0,4.650350253123179,null,0,0,4.650350253119996,0,4.650350253123179,"2G                            "]
["1","03","02","04","02","37","Rack Accessories - LI21                                     ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","02","38","Rack Accessories - LI24                                     ",0,0,4.704444716399962,17.43871999999999,22.14316471639995,null,0,0,4.704444716399962,17.43871999999999,22.14316471639995,"2G                            "]
["1","03","02","04","02","39","Rack Accessories - LI25                                     ",0,0,4.704444716399962,17.43871999999999,22.14316471639995,null,0,0,4.704444716399962,17.43871999999999,22.14316471639995,"2G                            "]
["1","03","02","04","02","40","Rack Accessories - BSY                                      ",0,0,4.704444716399962,17.43871999999999,22.14316471639995,null,0,0,4.704444716399962,17.43871999999999,22.14316471639995,"2G                            "]
["1","03","02","04","02","41","Rack Accessories - Dump                                     ",0,0,4.704444716399962,17.43871999999999,22.14316471639995,null,0,0,4.704444716399962,17.43871999999999,22.14316471639995,"2G                            "]
["1","03","02","04","03","  ","Beamline Power Supplies - (Trim Type)                       ",0,-800,3819.022334953479,5021.966978751589,8840.98931370466,null,0,-800,3365.4726356079045,1719.454882752325,5084.927518359502,"2G                            "]
["1","03","02","04","03","01","MCOR_1                                                      ",0,0,53.60206943519961,728.2028000000064,781.8048694352037,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","03","02","MCOR_2                                                      ",0,0,66.79578047999985,728.2028000000064,794.9985804800017,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","03","03","MCOR_3                                                      ",0,0,66.79578047999985,728.2028000000064,794.9985804800017,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","03","04","MCOR_4                                                      ",0,0,48.665759999999864,758.7205600000052,807.3863200000051,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","03","05","MCOR_5                                                      ",0,0,55.21751883647994,0,55.2175188364854,null,0,0,55.21751883647994,0,55.2175188364854,"2G                            "]
["1","03","02","04","03","06","MCOR_6                                                      ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","03","07","MCOR_BSY1                                                   ",0,0,55.21751883647994,0,55.2175188364854,null,0,0,55.21751883647994,0,55.2175188364854,"2G                            "]
["1","03","02","04","03","08","MCOR_LTU1                                                   ",0,0,55.21751883647994,0,55.2175188364854,null,0,0,55.21751883647994,0,55.2175188364854,"2G                            "]
["1","03","02","04","03","09","MCOR_LTU2                                                   ",0,0,55.21751883647994,0,55.2175188364854,null,0,0,55.21751883647994,0,55.2175188364854,"2G                            "]
["1","03","02","04","03","10","MCOR_LTU3                                                   ",0,0,55.21751883647994,0,55.2175188364854,null,0,0,55.21751883647994,0,55.2175188364854,"2G                            "]
["1","03","02","04","03","11","MCOR_LTU4                                                   ",0,0,55.21751883647994,0,55.2175188364854,null,0,0,55.21751883647994,0,55.2175188364854,"2G                            "]
["1","03","02","04","03","12","MCOR_LTU5                                                   ",0,0,55.21751883647994,0,55.2175188364854,null,0,0,55.21751883647994,0,55.2175188364854,"2G                            "]
["1","03","02","04","03","13","MCOR_LTU6                                                   ",0,0,55.21751883647994,0,55.2175188364854,null,0,0,55.21751883647994,0,55.2175188364854,"2G                            "]
["1","03","02","04","03","14","MCOR_LTU7                                                   ",0,0,55.21751883647994,0,55.2175188364854,null,0,0,55.21751883647994,0,55.2175188364854,"2G                            "]
["1","03","02","04","03","15","MCOR_LTU8                                                   ",0,0,55.21751883647994,0,55.2175188364854,null,0,0,55.21751883647994,0,55.2175188364854,"2G                            "]
["1","03","02","04","03","16","MCOR_LTU9                                                   ",0,0,55.21751883647994,0,55.2175188364854,null,0,0,55.21751883647994,0,55.2175188364854,"2G                            "]
["1","03","02","04","03","17","MCOR_DUMP1                                                  ",0,0,55.21751883647994,0,55.2175188364854,null,0,0,55.21751883647994,0,55.2175188364854,"2G                            "]
["1","03","02","04","03","18","MCOR Bulk PS - LI21_1                                       ",0,-100,0,-107.52479999999923,-107.52479999999923,null,0,-100,0,-107.5248,-107.5248,"2G                            "]
["1","03","02","04","03","19","MCOR Bulk PS - LI21_2                                       ",0,-100,0,-107.52479999999923,-107.52479999999923,null,0,-100,0,-107.5248,-107.5248,"2G                            "]
["1","03","02","04","03","20","MCOR Bulk PS - LI24                                         ",0,-100,0,-107.52479999999923,-107.52479999999923,null,0,-100,0,-107.5248,-107.52480000000003,"2G                            "]
["1","03","02","04","03","21","MCOR Bulk PS - LI25                                         ",0,-100,0,-107.52479999999923,-107.52479999999923,null,0,-100,0,-107.5248,-107.52480000000003,"2G                            "]
["1","03","02","04","03","22","MCOR Bulk PS - BSY                                          ",0,-100,0,-107.52479999999923,-107.52479999999923,null,0,-100,0,-107.5248,-107.52480000000003,"2G                            "]
["1","03","02","04","03","23","MCOR Bulk PS - LTU_1                                        ",0,-100,0,-107.52479999999923,-107.52479999999923,null,0,-100,0,-107.5248,-107.52480000000003,"2G                            "]
["1","03","02","04","03","24","MCOR Bulk PS - LTU_2                                        ",0,-100,0,-107.52479999999923,-107.52479999999923,null,0,-100,0,-107.5248,-107.52480000000003,"2G                            "]
["1","03","02","04","03","25","MCOR Bulk PS - LTU_3                                        ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","03","26","MCOR Bulk PS - LTU_4                                        ",0,-100,0,-107.52479999999923,-107.52479999999923,null,0,-100,0,-107.5248,-107.52480000000003,"2G                            "]
["1","03","02","04","03","27","MCOR PLC - LI21                                             ",0,0,231.5484259058867,359.18313599999965,590.7315619058863,null,0,0,13.858116955485457,0,13.858116955485457,"2G                            "]
["1","03","02","04","03","28","MCOR PLC - LI24                                             ",0,0,384.1434703735158,368.52189753600396,752.6653679095252,null,0,0,384.1434703735158,368.52189753600396,752.6653679095252,"2G                            "]
["1","03","02","04","03","29","MCOR PLC - LI25                                             ",0,0,384.1434703735158,368.52189753600396,752.6653679095252,null,0,0,384.1434703735158,368.52189753600396,752.6653679095252,"2G                            "]
["1","03","02","04","03","30","MCOR PLC - BSY                                              ",0,0,384.1434703735158,368.52189753600396,752.6653679095252,null,0,0,384.1434703735158,368.52189753600396,752.6653679095252,"2G                            "]
["1","03","02","04","03","31","MCOR PLC - LTU_1 (BLD 2.1)                                  ",0,0,384.1434703735158,368.52189753600396,752.6653679095252,null,0,0,384.1434703735158,368.52189753600396,752.6653679095252,"2G                            "]
["1","03","02","04","03","32","MCOR PLC - LTU_2 (BLD 2.2)                                  ",0,0,384.1434703735158,368.52189753600396,752.6653679095252,null,0,0,384.1434703735158,368.52189753600396,752.6653679095252,"2G                            "]
["1","03","02","04","03","33","MCOR PLC - LTU_3 (BLD 2.3)                                  ",0,0,384.1434703735158,368.52189753600396,752.6653679095252,null,0,0,384.1434703735158,368.52189753600396,752.6653679095252,"2G                            "]
["1","03","02","04","03","34","MCOR PLC - Dump                                             ",0,0,384.1434703735158,368.52189753600396,752.6653679095252,null,0,0,384.1434703735158,368.52189753600396,752.6653679095252,"2G                            "]
["1","03","02","04","03","35","MCOR Bulk Dump                                              ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","03","36","Rack Accessories - LTU_1 (bld 2.1)                          ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","03","37","Rack Accessories - LTU_2 (bld 2.2)                          ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","03","38","Rack Accessories - LTU_3 (bld 2.3)                          ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","04","04","  ","Controls & Power Supply                                     ",0,0,8538.585193860286,4598.688005352393,89845.41199386003,null,0,0,6916.255401202245,986.446595828631,7902.701997030294,"2G                            "]
["1","03","02","05","  ","  ","Controls - LLRF                                             ",-4452,-375000,-396652.95093892084,-406992.1204799999,-803645.0714189209,null,-4452,-375000,-396652.95093892084,-406992.1204799999,-803645.0714189209,"2G                            "]
["1","03","02","06","  ","  ","Controls - E-Beam Diagnostic                                ",-230,0,-36676.71556549927,3470.9864800000796,-33205.72908549756,null,0,0,1288.9962225758354,242.50719999999274,1531.5034225767013,"2G                            "]
["1","03","02","06","01","  ","Controls - Wire Scanners                                    ",0,0,362.477350030269,0,362.477350030269,null,0,0,0,0,0,"2G                            "]
["1","03","02","06","02","  ","Controls - BPMs                                             ",0,0,1333.9850061328616,576.8674079999328,1910.8524141330272,null,0,0,873.3024363436853,0,873.3024363437435,"2G                            "]
["1","03","02","06","03","  ","Controls - Toroids                                          ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","06","04","  ","Controls - Stoppers                                         ",0,0,143.43999246719977,258.85599999999977,402.2959924672032,null,0,0,0,0,0,"2G                            "]
["1","03","02","06","05","  ","Controls - Profile Monitors                                 ",0,0,-6042.744998287097,2117.551072000031,-3925.1939262870583,null,0,0,172.5396594841077,0,172.5396594841004,"2G                            "]
["1","03","02","06","06","  ","Controls - E/O Diagnostics                                  ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","06","07","  ","Controls - Bunch Length Monitors                            ",0,0,-13479.796045584008,0,-13479.796045583986,null,0,0,0,0,0,"2G                            "]
["1","03","02","06","08","  ","Controls - Beam Loss Monitors                               ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","06","09","  ","Controls - Single Beam Dump                                 ",0,0,178.8999477407997,258.85599999999977,437.75594774079946,null,0,0,49.96397165759845,0,49.96397165759845,"2G                            "]
["1","03","02","06","10","  ","Controls - E Beam Dump                                      ",0,0,178.8999477407997,258.85599999999977,437.75594774079946,null,0,0,157.14392316480007,242.50719999999637,399.65112316479645,"2G                            "]
["1","03","02","06","11","  ","Controls - Protection Collimator                            ",0,0,497.48502352937066,0,497.48502352937066,null,0,0,0,0,0,"2G                            "]
["1","03","02","06","12","  ","Controls - Movable Collimator                               ",-230,0,-19849.361789269413,0,-19849.361789269416,null,0,0,36.046231925782195,0,36.04623192579311,"2G                            "]
["1","03","02","06","13","  ","Controls - X-Band Accel Structure                           ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","08","  ","  ","Controls - Timing                                           ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","09","  ","  ","Controls - Vacuum                                           ",0,0,1468.6299625659012,787.6306880000047,2256.2606505658478,null,0,0,738.120693075849,0,738.1206930758781,"2G                            "]
["1","03","02","09","01","  ","Controls - Vacuum Instrumentation & Interlocks              ",0,0,1468.6299625659012,787.6306880000047,2256.2606505658478,null,0,0,738.120693075849,0,738.1206930758781,"2G                            "]
["1","03","02","09","02","  ","Controls - Vacuum Pump Power Supplies                       ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","10","  ","  ","Software & Controls Infrastructure                          ",0,0,1141.9581558644713,2043.5999999999767,3185.558155864419,null,0,0,1078.6340720665467,0,1078.6340720665175,"2G                            "]
["1","03","02","10","04","  ","Data Communications                                         ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","03","02","10","05","  ","Computers                                                   ",0,0,1141.9581558644713,2043.5999999999767,3185.558155864419,null,0,0,1078.6340720665467,0,1078.6340720665175,"2G                            "]
["1","04","02","  ","  ","  ","Controls                                                    ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","01","  ","  ","Controls Management and Integration                         ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","01","03","  ","Software Interface with SLAC                                ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","01","04","  ","Undulator Cable, Tray, and Rack Layout                      ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","01","05","  ","Miscellaneous Controls                                      ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","02","  ","  ","Motion                                                      ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","02","01","  ","Undulator Cam Movers                                        ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","02","01","01","Motor Interface                                             ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","02","01","02","Encoder Interface                                           ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","02","01","03","Motor Driver                                                ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","02","01","04","Cabling                                                     ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","02","01","05","Integrate components                                        ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","02","02","  ","Motion Test Stand                                           ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","02","06","  ","Scanning Wire Motion                                        ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","02","06","01","Motor Interface                                             ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","02","06","02","Encoder Interface                                           ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","02","06","03","Motor Driver                                                ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","02","06","04","Cabling                                                     ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","02","06","05","Integrate components                                        ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","02","07","  ","Translation Stage Motion                                    ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","02","07","01","Motor Interface                                             ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","02","07","03","Motor Driver                                                ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","02","07","04","Cabling                                                     ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","02","07","05","Integrate components                                        ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","03","  ","  ","Signal Analysis                                             ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","03","01","  ","RFBPM                                                       ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","03","01","02","Signal Acquisition                                          ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","03","01","03","Timing interface                                            ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","03","01","04","Cabling                                                     ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","03","01","05","Integrate components                                        ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","03","02","  ","Charge Monitor                                              ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","03","02","03","Integrate components                                        ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","03","03","  ","Beam Finder Wire                                            ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","03","03","01","BFW Actuator Control                                        ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","03","03","06","Integrate components                                        ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","04","  ","  ","Video                                                       ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","04","01","  ","OTR Monitor                                                 ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","04","01","01","Camera                                                      ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","04","01","02","Camera trigger interface                                    ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","04","01","03","Digitizer                                                   ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","04","01","04","Timing interface                                            ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","04","01","05","Cabling                                                     ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","04","01","06","Integrate components                                        ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","04","03","  ","Observation station video                                   ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","04","03","01","Camera                                                      ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","04","03","02","Camera trigger interface                                    ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","04","03","03","Multiplexor                                                 ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","04","03","04","Cabling                                                     ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","04","03","05","Integrate components                                        ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","04","03","06","Imaging Test Stand                                          ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","05","  ","  ","Data Acquisition and Control                                ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","05","01","  ","Strongback Temperature monitoring                           ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","05","01","01","Integrate components                                        ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","06","  ","  ","Vacuum                                                      ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","06","01","  ","Ion Pump Controller                                         ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","06","01","01","Integrate components                                        ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","06","02","  ","RGA                                                         ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","06","02","01"," Integrate components                                       ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","07","  ","  ","Machine Protection                                          ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","07","01","  ","Undulator Beam Loss Monitor Controls                        ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","07","01","01","Hardware design                                             ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","07","01","02","Interface components                                        ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","07","02","  ","Cerenkov Detector                                           ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","07","02","01","Signal interface                                            ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","07","03","  ","Gamma Ray Detector                                          ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","07","03","01","Signal interface                                            ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","08","  ","  ","Power Supply Controls                                       ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","10","  ","  ","Undualtor Controls Module                                   ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","12","  ","  ","Rack and Cables                                             ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","13","  ","  ","BPM                                                         ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","14","  ","  ","Long Term Test Prep                                         ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","17","  ","  ","Undulator Controls Management                               ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","20","  ","  ","Undulator Controls - MPS                                    ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","21","  ","  ","Undulator Controls - Timing                                 ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","22","  ","  ","Undulator Controls - BPM                                    ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","23","  ","  ","Undulator Controls - Vacuum                                 ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","04","02","24","  ","  ","Undulator Controls - ADS System                             ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","05","02","  ","  ","  ","Controls                                                    ",0,0,4190.898151730304,24141.78,28332.678151730448,null,0,0,2115.614601501904,24141.78,26257.39460150199,"2G                            "]
["1","05","02","01","  ","  ","Controls - EPICS                                            ",0,0,4190.898151730304,24141.78,28332.678151730448,null,0,0,2115.614601501904,24141.78,26257.39460150199,"2G                            "]
["1","05","02","02","  ","  ","Motor Controls                                              ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","05","02","03","  ","  ","Controls - Vacuum                                           ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","06","02","  ","  ","  ","XES Controls                                                ",0,0,9710.003293429036,3810.30570535874,63731.28361342475,null,0,0,9534.696855022106,3810.30570535874,13345.00256037619,"2G                            "]
["1","06","02","01","  ","  ","Controls Management                                         ",0,0,0,0,78386.4,null,0,0,0,0,0,"2G                            "]
["1","06","02","02","  ","  ","Network - Closed (Moved to new WBS Element)                 ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","06","02","03","  ","  ","PC Support - Closed (Moved to New WBS Element)              ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","06","02","04","  ","  ","Beamline Controls - AP - Closed  (Moved to new WBS Element) ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","06","02","05","  ","  ","X-Ray PPS - Closed (Moved to new WBS Element)               ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","06","02","05","01","  ","FEE X-Ray PPS - Closed (Moved to new WBS Element)           ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","06","02","05","02","  ","Near Hall X-Ray PPS - Closed to BCWP                        ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","06","02","05","03","  ","Tunnel X-Ray PPS - Closed to BCWP                           ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","06","02","05","04","  ","Far Hall X-Ray PPS - Closed to BCWP                         ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","06","02","06","  ","  ","X-Ray MPS - Closed (Moved to new WBS Element)               ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","06","02","06","01","  ","FEE X-Ray MPS - Closed to BCWP                              ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","06","02","07","  ","  ","AMOS Experiment Controls X1                                 ",0,0,1496.7470125810942,0,1496.747012580512,null,0,0,1464.95676342363,0,1464.9567634232808,"2G                            "]
["1","06","02","07","01","  ","AMOS Experiment Controls X1                                 ",0,0,-490.50877314736135,0,-490.50877314736135,null,0,0,-517.1404938581982,0,-517.1404938581982,"2G                            "]
["1","06","02","07","02","  ","X-Ray Flourescence Detector                                 ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","06","02","07","03","  ","Ion Imaging & Electron TOF                                  ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","06","02","07","04","  ","Sample Source                                               ",0,0,922.2880301201658,0,922.2880301201658,null,0,0,922.2880301201658,0,922.2880301201658,"2G                            "]
["1","06","02","07","05","  ","Vacuum Controls & Mechanical Exp 1                          ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","06","02","07","06","  ","Refocus Optics                                              ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","06","02","07","07","  ","Diagnostics                                                 ",0,0,1064.9677556080278,0,1064.9677556080278,null,0,0,1059.8092271616624,0,1059.8092271616915,"2G                            "]
["1","06","02","08","  ","  ","AMOS Experiment Controls X2                                 ",0,0,1114.6347007512813,0,1114.6347007512813,null,0,0,1057.1026215789607,0,1057.1026215789607,"2G                            "]
["1","06","02","08","01","  ","AMOS Experiment Controls X2                                 ",0,0,1114.6347007512522,0,1114.6347007512522,null,0,0,1057.1026215789607,0,1057.1026215789607,"2G                            "]
["1","06","02","08","02","  ","X2 Praticle Imaging                                         ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","06","02","09","  ","  ","Controls Management - Closed (Moved to new WBS Element)     ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","06","02","10","  ","  ","Global Controls System                                      ",0,0,6974.280504978728,3810.305705358507,-17390.83917502174,null,0,0,6905.989792265231,3810.305705358507,10716.295497624204,"2G                            "]
["1","06","02","10","01","  ","Network                                                     ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","06","02","10","02","  ","Machine Protection System                                   ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","06","02","10","03","  ","Personnel Protection System                                 ",0,0,1410.6332019985712,2516.0803200000373,3926.7135219985503,null,0,0,1410.6332019985857,2516.0803200000373,3926.7135219985503,"2G                            "]
["1","06","02","10","04","  ","Laser PPS                                                   ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","06","02","10","05","  ","User Safeguards                                             ",0,0,137.9821650577942,1294.2253853584916,-26743.217834942217,null,0,0,137.9821650577942,1294.2253853584916,1432.207550416264,"2G                            "]
["1","06","02","10","06","  ","Timing System                                               ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","06","02","10","07","  ","Data Management                                             ",0,0,3120.6571800555103,0,3120.657180055394,null,0,0,3120.6571800555103,0,3120.657180055394,"2G                            "]
["1","06","02","10","08","  ","Global Cabling & Racks                                      ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","06","02","10","09","  ","Laser Timing                                                ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","06","02","10","10","  ","Experimental High Level Applications                        ",0,0,2305.0079578667064,0,2305.0079578667064,null,0,0,2236.717245153617,0,2236.717245153617,"2G                            "]
["1","06","02","11","  ","  ","Laser Controls                                              ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["1","06","02","12","  ","  ","K-Measuerment/Vacuum Subsystem                              ",0,0,124.34107511826005,0,124.34107511825277,null,0,0,106.64767775376095,0,106.64767775376095,"2G                            "]
["2","01","01","11","  ","  ","Global Controls OPC                                         ",0,0,10520.416831053095,11931.014272100292,-772539.2865897468,null,0,0,10520.416831053095,11310.978752100375,21831.395583154168,"2G                            "]
["2","01","01","11","01","  ","EPICS Control Modules                                       ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","01","01","11","02","  ","LLRF Controls - Closed                                      ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","01","01","11","04","  ","Laser Controls Design                                       ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","01","01","11","05","  ","Laser Heater Controls Design                                ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","01","01","11","06","  ","Timing Controls                                             ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","01","01","11","07","  ","Vacuum Controls                                             ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","01","01","11","08","  ","S/W & Controls Infrastructure                               ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","01","01","11","09","  ","Power Supply Control                                        ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","01","01","11","10","  ","MPS/PPS/BCS Controls                                        ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","01","01","11","11","  ","Global Controls Commissioning                               ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","01","01","11","12","  ","Global Controls Management - OPC                            ",0,0,9374.784202842508,8830.836672100355,-776785.0968179572,null,0,0,9374.784202842508,8830.836672100355,18205.62087494321,"2G                            "]
["2","01","01","11","12","01","                                                            ",0,0,9374.784202842508,8830.836672100355,-776785.0968179572,null,0,0,9374.784202842508,8830.836672100355,18205.62087494321,"2G                            "]
["2","01","01","11","13","  ","SLC Aware IOC                                               ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","01","01","11","14","  ","Controls - Networking and Data Comm. OPC                    ",0,0,1145.6326282105438,0,1145.6326282105438,null,0,0,1145.6326282105438,0,1145.6326282105438,"2G                            "]
["2","01","01","11","15","  ","Controls S/W Applications LOE                               ",0,0,0,3100.177599999981,3100.177599999981,null,0,0,0,2480.1420799999905,2480.1420799999905,"2G                            "]
["2","02","02","  ","  ","  ","Injector Controls Subsystem                                 ",0,0,8016.149420406437,826.6332589309386,4154.961580406292,null,0,0,7335.092607487342,39.97089158400013,7375.063499071286,"2G                            "]
["2","02","02","01","  ","  ","Personnel Protection System (PPS) R&D                       ",0,0,1193.0580339191365,786.6623673469439,12705.290033919155,null,0,0,355.59842499289516,0,355.59842499289516,"2G                            "]
["2","02","02","02","  ","  ","Beam Containment Subsystem (BCS)                            ",0,0,34.5595429410896,0,34.5595429410896,null,0,0,-42.35490539583043,0,-42.35490539583043,"2G                            "]
["2","02","02","03","  ","  ","Machine Protection Subsystem (MPS)                          ",0,0,1219.206294626114,0,1219.206294626114,null,0,0,1219.206294626114,0,1219.206294626114,"2G                            "]
["2","02","02","04","  ","  ","Power Conv (beamline pwr supp) Spares                       ",0,0,0,39.97089158400013,-15373.419839999999,null,0,0,0,39.97089158400013,39.97089158400013,"2G                            "]
["2","02","02","04","01","  ","Power Supply Controls                                       ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","02","02","05","  ","  ","LLRF Controls                                               ",0,0,1412.4473997389723,0,1412.4473997389723,null,0,0,1412.4473997389723,0,1412.4473997389723,"2G                            "]
["2","02","02","05","01","  ","LLRF Controls                                               ",0,0,1412.4473997389723,0,1412.4473997389723,null,0,0,1412.4473997389723,0,1412.4473997389723,"2G                            "]
["2","02","02","06","  ","  ","E-Beam Diagnostics Controls                                 ",0,0,1835.1211159667,0,1835.1211159667,null,0,0,2068.438360310858,0,2068.438360310858,"2G                            "]
["2","02","02","06","01","  ","Controls - Wire Scanners                                    ",0,0,170.490137159788,0,170.490137159788,null,0,0,170.490137159788,0,170.490137159788,"2G                            "]
["2","02","02","06","02","  ","Controls - BPM Processor Module                             ",0,0,1219.6610865891853,0,1219.6610865891853,null,0,0,1219.6610865891853,0,1219.6610865891853,"2G                            "]
["2","02","02","06","03","  ","Controls - Toroids                                          ",0,0,23.36199053302198,0,23.36199053302198,null,0,0,23.36199053302198,0,23.36199053302198,"2G                            "]
["2","02","02","06","05","  ","Controls - Profile Monitors                                 ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","02","02","06","06","  ","Control - EO Diagnostic                                     ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","02","02","06","12","  ","Controls - Movable Collimator                               ",0,0,340.980274319576,0,340.980274319576,null,0,0,340.980274319576,0,340.980274319576,"2G                            "]
["2","02","02","06","14","  ","Controls - Faraday Cup                                      ",0,0,26.875875788383382,0,26.875875788383382,null,0,0,104.64829056977669,0,104.64829056977669,"2G                            "]
["2","02","02","06","15","  ","Controls - Tune-Up Dump                                     ",0,0,26.875875788383382,0,26.875875788383382,null,0,0,104.64829056977669,0,104.64829056977669,"2G                            "]
["2","02","02","06","16","  ","Cherenkov Commissioning Support                             ",0,0,26.875875788383382,0,26.875875788383382,null,0,0,104.64829056977669,0,104.64829056977669,"2G                            "]
["2","02","02","08","  ","  ","Timing Controls                                             ",0,0,1659.4662369784492,0,1659.4662369784492,null,0,0,1659.4662369784492,0,1659.4662369784492,"2G                            "]
["2","02","02","09","  ","  ","Vacuum Controls                                             ",0,0,662.2907962359022,0,662.2907962359022,null,0,0,662.2907962359022,0,662.2907962359022,"2G                            "]
["2","02","02","10","  ","  ","Software & Controls Infrastructure                          ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","02","02","11","  ","  ","EPICS VXI Control Modules                                   ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","02","02","12","  ","  ","Laser Controls                                              ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","02","02","13","  ","  ","Laser Heater Controls                                       ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","03","02","  ","  ","  ","Linac Controls & Power Conversion Subsystem                 ",0,0,5466.983832880156,0,5466.983832880156,null,0,0,5466.983832880156,0,5466.983832880156,"2G                            "]
["2","03","02","01","  ","  ","Personnel Protection System (PPS)                           ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","03","02","02","  ","  ","Beam Containment System (BCS)                               ",0,0,688.986103291194,0,688.986103291194,null,0,0,688.986103291194,0,688.986103291194,"2G                            "]
["2","03","02","03","  ","  ","Machine Protection System (MPS)                             ",0,0,72.67496568657225,0,72.67496568657225,null,0,0,72.67496568657225,0,72.67496568657225,"2G                            "]
["2","03","02","04","  ","  ","Power Conversion                                            ",0,0,135.2026790275304,0,135.20267902752676,null,0,0,135.2026790275304,0,135.20267902752676,"2G                            "]
["2","03","02","04","01","  ","Spare Power Supply (Dipole Type)                            ",0,0,65.33292984816399,0,65.3329298481658,null,0,0,65.33292984816399,0,65.3329298481658,"2G                            "]
["2","03","02","04","02","  ","Spare Power Supply (Quad Type)                              ",0,0,69.86974917936368,0,69.86974917936823,null,0,0,69.86974917936368,0,69.86974917936823,"2G                            "]
["2","03","02","04","03","  ","Spare Power Supply (Trim Type)                              ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","03","02","04","04","  ","Controls & Power Supply - Spare Misc Hdwr                   ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","03","02","05","  ","  ","Controls - LLRF                                             ",0,0,1476.7095041222638,0,1476.7095041222638,null,0,0,1476.7095041222638,0,1476.7095041222638,"2G                            "]
["2","03","02","06","  ","  ","Controls - E-Beam Diagnostic                                ",0,0,1964.8011706007528,0,1964.8011706007528,null,0,0,1964.8011706007528,0,1964.8011706007528,"2G                            "]
["2","03","02","06","01","  ","Controls - Wire Scanners                                    ",0,0,170.49013715976616,0,170.49013715976616,null,0,0,170.49013715976616,0,170.49013715976616,"2G                            "]
["2","03","02","06","02","  ","Controls - BPMs                                             ",0,0,1219.6610865892144,0,1219.6610865892144,null,0,0,1219.6610865892144,0,1219.6610865892144,"2G                            "]
["2","03","02","06","03","  ","Controls - Toroids                                          ",0,0,34.098027431955416,0,34.098027431955416,null,0,0,34.098027431955416,0,34.098027431955416,"2G                            "]
["2","03","02","06","04","  ","Controls - Stoppers Commissioning                           ",0,0,13.639210972782166,0,13.639210972782166,null,0,0,13.639210972782166,0,13.639210972782166,"2G                            "]
["2","03","02","06","05","  ","Controls - Profile Monitors                                 ",0,0,79.08629500286406,0,79.08629500286406,null,0,0,79.08629500286406,0,79.08629500286406,"2G                            "]
["2","03","02","06","07","  ","Controls - BLM                                              ",0,0,34.098027431958144,0,34.098027431958144,null,0,0,34.098027431958144,0,34.098027431958144,"2G                            "]
["2","03","02","06","09","  ","Controls - Single Beam Dump                                 ",0,0,13.639210972782166,0,13.639210972782166,null,0,0,13.639210972782166,0,13.639210972782166,"2G                            "]
["2","03","02","06","10","  ","Controls - E-Beam Dump                                      ",0,0,59.108900719755184,0,59.108900719755184,null,0,0,59.108900719755184,0,59.108900719755184,"2G                            "]
["2","03","02","06","12","  ","Controls - Collimators                                      ",0,0,340.980274319576,0,340.980274319576,null,0,0,340.980274319576,0,340.980274319576,"2G                            "]
["2","03","02","07","  ","  ","Controls - Laser                                            ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","03","02","08","  ","  ","Controls - Timing                                           ",0,0,206.9211088168522,0,206.9211088168522,null,0,0,206.9211088168522,0,206.9211088168522,"2G                            "]
["2","03","02","09","  ","  ","Controls - Vacuum                                           ",0,0,921.6883013352635,0,921.6883013352635,null,0,0,921.6883013352635,0,921.6883013352635,"2G                            "]
["2","03","02","10","  ","  ","Software & Controls Infrastructure                          ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","04","02","  ","  ","  ","Controls                                                    ",0,0,0,149.43365542856918,5423.660467199996,null,0,0,0,149.43365542856918,149.43365542856918,"2G                            "]
["2","04","02","01","  ","  ","Controls Management and Integration                         ",0,0,0,149.43365542856918,5423.660467199996,null,0,0,0,149.43365542856918,149.43365542856918,"2G                            "]
["2","04","02","04","  ","  ","Video                                                       ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","04","02","07","  ","  ","Machine Protection                                          ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","05","02","  ","  ","  ","Controls                                                    ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","05","02","01","  ","  ","Controls - EPICS                                            ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","05","02","02","  ","  ","Controls - System                                           ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","06","02","  ","  ","  ","Controls Subsystem                                          ",0,0,26.611528273060685,0,26.611528273060685,null,0,0,26.611528273060685,0,26.611528273060685,"2G                            "]
["2","06","02","01","  ","  ","Cabling                                                     ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","06","02","02","  ","  ","Network                                                     ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","06","02","03","  ","  ","PC Support                                                  ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","06","02","04","  ","  ","Beamline Controls                                           ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","06","02","05","  ","  ","X-Ray PPS                                                   ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","06","02","06","  ","  ","X-Ray MPS                                                   ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","06","02","07","  ","  ","Laser PPS                                                   ",0,0,0,0,0,null,0,0,0,0,0,"2G                            "]
["2","06","02","08","  ","  ","R&D: 2D X-Ray Detector Controls                             ",0,0,26.611528273060685,0,26.611528273060685,null,0,0,26.611528273060685,0,26.611528273060685,"2G                            "]

{"sheet":"WBS-CN-PP","index":8,"n_rows":1296,"n_cols":15,"rows_kept":1296,"cut":false,"hidden":true,"merged":[[0,10,0,14],[0,0,0,5],[1,0,1,5]],"flags":["formulas_cached_only"]}
["WBS",{"$nulls":5},"P3","June - 2004 DCE","OBS","Summary or","CHARGE NUMBERS"]
["Level",{"$nulls":5},"ID","Description",null,"Cntrl Acc","PED","CNSTR","R&D","SPARES","PRE-OPS"]
["1","2","3","4","5","6"]
[{"$nulls":7},"LINAC COHERENT LIGHT SOURCE (TPC)"]
["1",{"$nulls":6},"LCLS PROJECT - PED & CONSTRUCTION",null,"Summary"]
["1","01",{"$nulls":5},"LCLS PROJECT MGMT, PLANNING & ADMN (TEC)",null,"Summary"]
["1","01","01",{"$nulls":4},"Environment, Safety & Health",null,"Summary"]
["1","01","01","01","","",null,"Radiation Physics",null,"1.01.01.01",9240222,"CN10101"]
["1","01","01","02","","",null,"ESH Management & Coordination",null,"1.01.01.02",9240223,"CN10102"]
["1","01","01","03","","",null,"Seismic & Engineering Support",null,"1.01.01.03",9240224,"CN10103"]
["1","01","02",{"$nulls":4},"Project Management",null,"Summary"]
["1","01","02","01",null,null,null,"SLAC Project Management Office",null,"Summary"]
["1","01","02","01","01","",null,"SLAC Project Office - General",null,"1.01.02.01.01",9240227,"CN1020101"]
["1","01","02","01","02","",null,"SLAC Project Support",null,"1.01.02.01.02",9240228,"CN1020102"]
["1","01","02","01","03","",null,"SLAC Project Office M&S",null,"1.01.02.01.03",9240229,"CN1020103"]
["1","01","02","01","04",null,null,"Reserved",null,"Summary"]
["1","01","02","01","05",null,null,"Reserved",null,"Summary"]
["1","01","02","02",null,null,null,"Reserved",null,"Summary"]
["1","01","02","03",null,null,null,"Reserved",null,"Summary"]
["1","01","03",{"$nulls":4},"Technical Integration",null,"Summary"]
["1","01","03","01","","",null,"Global Controls",null,"1.01.03.01",9240235,"CN10301"]
["1","01","03","02","","",null,"Global Alignment Coordination",null,"1.01.03.02",9240236,"CN10302"]
["1","01","03","03","","",null,"Global Installation Coordination",null,"1.01.03.03",9240237,"CN10303"]
["1","01","04",{"$nulls":4},"Education Support",null,"Summary"]
["1","01","04","01","","",null,"Education/Outreach Travel",null,"1.01.04.01",9240239,"CN10401"]
["1","01","04","02","","",null,"Education/Outreach M&S",null,"1.01.04.02",9240240,"CN10402"]
["1","01","05",{"$nulls":4},"Reserved",null,"Summary"]
["1","02",{"$nulls":5},"INJECTOR SYSTEM",null,"Summary"]
["1","02","01",{"$nulls":4},"Injector System Management & Integration",null,"Summary"]
["1","02","01","01","","",null,"Injector System Integration Effort / M&S",null,"1.02.01.01",9240242,"CN20101"]
["1","02","01","02",null,null,null,"Reserved",null,"Summary"]
["1","02","01","03",null,null,null,"Reserved",null,"Summary"]
["1","02","02",{"$nulls":4},"Injector Controls Subsystem",null,"Summary"]
["1","02","02","01",null,null,null,"Reserved",null,"Summary"]
["1","02","02","02",null,null,null,"LLRF Controls",null,"Summary"]
["1","02","02","02","01","",null,"Readback & Controls - RF Gun LLRF & Temperature",null,"1.02.02.02.01","CN2020201","CN2020201"]
["1","02","02","02","02","",null,"Readback & Controls - L0 LLRF",null,"1.02.02.02.02",null,"CN2020202"]
["1","02","02","02","03","",null,"Readback & Controls - LLRF Transverse Cavity",null,"1.02.02.02.03",null,"CN2020203"]
["1","02","02","02","04","",null,"S-Band Cavity Controls",null,"1.02.02.02.04",null,"CN2020204"]
["1","02","02","02","05",null,null,"Reserved",null,"Summary"]
["1","02","02","03",null,null,null,"E-Beam Diagnostics Controls",null,"Summary"]
["1","02","02","03","01",null,null,"Reserved",null,"Summary"]
["1","02","02","03","02","",null,"Controls - Toroids",null,"1.02.02.03.02",null,"CN2020302"]
["1","02","02","03","03","",null,"Controls - Faraday Cups",null,"1.02.02.03.03","CN2020303","CN2020303"]
["1","02","02","03","04","",null,"Controls - Tune-Up Dump",null,"1.02.02.03.04",null,"CN2020304"]
["1","02","02","03","05","",null,"Controls - Profile Monitors",null,"1.02.02.03.05",null,"CN2020305"]
["1","02","02","03","06","",null,"Controls - E/O Diagnostics",null,"1.02.02.03.06",null,"CN2020306"]
["1","02","02","03","07","",null,"Controls - BPM",null,"1.02.02.03.07",null,"CN2020307"]
["1","02","02","03","08",null,null,"Reserved",null,"Summary"]
["1","02","02","04",null,null,null,"Laser Controls",null,"Summary"]
["1","02","02","04","01",null,null,"Reserved",null,"Summary"]
["1","02","02","04","02","",null,"Controls - Gun Laser",null,"1.02.02.04.02","CN2020402","CN2020402"]
["1","02","02","05","","",null,"Laser Heater Controls",null,"1.02.02.05",null,"CN20205"]
["1","02","02","06","","",null,"Timing Controls",null,"1.02.02.06",null,"CN20206"]
["1","02","02","07","","",null,"Vacuum Controls",null,"1.02.02.07","CN20207","CN20207"]
["1","02","02","08",null,null,null,"Software & Controls Infrastructure",null,"Summary"]
["1","02","02","08","01",null,null,"Reserved",null,"Summary"]
["1","02","02","08","02",null,null,"Reserved",null,"Summary"]
["1","02","02","08","03","",null,"Data Communications",null,"1.02.02.08.03",null,"CN2020803"]
["1","02","02","08","04","",null,"Computers & Crates",null,"1.02.02.08.04",null,"CN2020804"]
["1","02","02","09","","",null,"Power Supply Controls",null,"1.02.02.09","CN20209","CN20209"]
["1","02","02","10","","",null,"PPS,BCS,MPS Controls",null,"1.02.02.10","CN20210","CN20210"]
["1","02","03",{"$nulls":4},"Injector Lasers",null,"Summary"]
["1","02","03","01",null,null,null,"Drive Laser Prototyping",null,"Summary"]
["1","02","03","02","","",null,"Drive Laser System",null,"1.02.03.02",9240277,"CN20302"]
["1","02","03","03","","",null,"Drive Laser Diagnostics",null,"1.02.03.03","CN20303","CN20303"]
["1","02","03","04","","",null,"Timing Stability Monitoring",null,"1.02.03.04",null,"CN20304"]
["1","02","03","05","","",null,"Steering Stability Feedback & Msmts",null,"1.02.03.05",null,"CN20305"]
["1","02","03","06","","",null,"Pre Amp Low Power Comp",null,"1.02.03.06","CN20306","CN20306"]
["1","02","03","07","","",null,"Transport to Tunnel & Rela Optics",null,"1.02.03.07",9240282,"CN20307"]
["1","02","03","08","","",null,"UV Launch, Conditioning & Diagnostics",null,"1.02.03.08",9240283,"CN20308"]
["1","02","03","09","","",null,"Load Lock Transport System",null,"1.02.03.09","CN20309","CN20309"]
["1","02","03","10","","",null,"Visible Optical Transport & Optics",null,"1.02.03.10",null,"CN20310"]
["1","02","03","11","","",null,"LB Infrastructure & LB System Wide Items",null,"1.02.03.11",9240286,"CN20311"]
["1","02","03","12","","",null,"Alignment Laser",null,"1.02.03.12",null,"CN20312"]
["1","02","03","13","","",null,"Light Path to Streak Camera",null,"1.02.03.13",null,"CN20313"]
["1","02","03","14","","",null,"Started..Closed Out",null,"1.02.03.14",9240289]
["1","02","03","15",null,null,null,"Moved to 1.02.03.03",null,"Summary"]
["1","02","03","16",null,null,null,"Deleted",null,"Summary"]
["1","02","03","17",null,null,null,"Deleted",null,"Summary"]
["1","02","03","18",null,null,null,"Moved to 1.02.03.07",null,"Summary"]
["1","02","03","19",null,null,null,"Moved to 1.02.03.04",null,"Summary"]
["1","02","03","20",null,null,null,"Moved to 1.02.03.07",null,"Summary"]
["1","02","03","21","","",null,"Started..Closed Out",null,"1.02.03.21",9240296]
["1","02","03","22",null,null,null,"Moved to 1.02.03.03",null,"Summary"]
["1","02","03","23",null,null,null,"Moved to 1.02.03.04 and 1.02.03.05",null,"Summary"]
["1","02","03","24",null,null,null,"Moved to 1.02.03.07 and 1.02.03.08",null,"Summary"]
["1","02","03","25",null,null,null,"Moved to 1.02.03.10",null,"Summary"]
["1","02","03","26",null,null,null,"Moved to 1.02.03.07",null,"Summary"]
["1","02","03","27",null,null,null,"Moved to 1.02.03.08",null,"Summary"]
["1","02","03","28",null,null,null,"Moved to 1.02.03.11",null,"Summary"]
["1","02","03","29",null,null,null,"Moved to 1.02.03.12",null,"Summary"]
["1","02","03","30",null,null,null,"Moved to 1.02.03.13",null,"Summary"]
["1","02","04",{"$nulls":4},"RF Gun, Load Lock & Supports",null,"Summary"]
["1","02","04","01","","",null,"RF Gun (Copper Brazement Only)",null,"1.02.04.01",9240307,"CN20401"]
["1","02","04","02","","",null,"RF Gun Supports",null,"1.02.04.02",9240308,"CN20402"]
["1","02","04","03","","",null,"Gun Load Lock",null,"1.02.04.03",null,"CN20403"]
["1","02","04","04","","",null,"Gun Load Lock Supports",null,"1.02.04.04",null,"CN20404"]
["1","02","04","05","","",null,"Gun Solenoid",null,"1.02.04.05",9240311,"CN20405"]
["1","02","04","06","","",null,"Gun Solenoid Supports",null,"1.02.04.06",9240312,"CN20406"]
["1","02","04","07","","",null,"Gun RF Feed",null,"1.02.04.07",9240313,"CN20407"]
["1","02","04","08","","",null,"Gun RF Feed Supports",null,"1.02.04.08",null,"CN20408"]
["1","02","05",{"$nulls":4},"Gun to Linac Section (GTL)",null,"Summary"]
["1","02","05","01","","",null,"GTL BPMs (3ea)",null,"1.02.05.01",9240316,"CN20501"]
["1","02","05","02","","",null,"GTL Faraday Cup/YAG1",null,"1.02.05.02",9240317,"CN20502"]
["1","02","05","03","","",null,"GTL Current Monitors (CM1)",null,"1.02.05.03",null,"CN20503"]
["1","02","05","04",null,null,null,"Reserved",null,"Summary"]
["1","02","05","05",null,null,null,"Reserved",null,"Summary"]
["1","02","05","06","","",null,"GTL Steering Coils, (2) (SC1)",null,"1.02.05.06",9240321,"CN20506"]
["1","02","05","07","","",null,"GTL Vacuum Components",null,"1.02.05.07",null,"CN20507"]
["1","02","05","08","","",null,"GTL Supports",null,"1.02.05.08",9240323,"CN20508"]
["1","02","05","09",null,null,null,"Gun Spectrometer (GS) Assembly",null,"Summary"]
["1","02","05","09","01","",null,"GS Dipole",null,"1.02.05.09.01",9240325,"CN2050901"]
["1","02","05","09","02","",null,"GS Current Monitor (CM2)",null,"1.02.05.09.02",null,"CN2050902"]
["1","02","05","09","03","",null,"GS BPM (1)",null,"1.02.05.09.03",9240327,"CN2050903"]
["1","02","05","09","04","",null,"GS Faraday Cup/YAG2",null,"1.02.05.09.04",9240328,"CN2050905"]
["1","02","05","09","05",null,null,"Reserved",null,"Summary"]
["1","02","05","09","06","",null,"GS Quadrupoles",null,"1.02.05.09.06",null,"CN2050906"]
["1","02","05","09","07","",null,"GS Supports",null,"1.02.05.09.07",null,"CN2050907"]
["1","02","05","10","","",null,"GTL Pumping & Optic Chamber",null,"1.02.05.10",9240332,"CN20510"]
["1","02","05","11","","",null,"GTL YAG (1ea)",null,"1.02.05.11",9240333,"CN20511"]
["1","02","06",{"$nulls":4},"Injector Linac Structures",null,"Summary"]
["1","02","06","01","","",null,"L0-1 Structure Assembly",null,"1.02.06.01",9240335,"CN20601"]
["1","02","06","02","","",null,"L0-2 Structure Assembly",null,"1.02.06.02",9240336,"CN20602"]
["1","02","06","03","","",null,"Major Linac Support",null,"1.02.06.03",9240337,"CN20603"]
["1","02","06","04","","",null,"Linac Solenoid & Supports",null,"1.02.06.04",9240338,"CN20604"]
["1","02","07",{"$nulls":4},"L0-1 to L0-2 Section (L0-1TL0-2)",null,"Summary"]
["1","02","07","01","","",null,"L0-1TL0-2 Quadrupoles (2)",null,"1.02.07.01",null,"CN20701"]
["1","02","07","02","","",null,"L0-1TL0-2 BPMs (2)",null,"1.02.07.02",9240341,"CN20702"]
["1","02","07","03",null,null,null,"Reserved",null,"Summary"]
["1","02","07","04","","",null,"L0-1TL0-2 OTR/YAG (1)",null,"1.02.07.04",9240343,"CN20704"]
["1","02","07","05","","",null,"L0-1TL0-2 Linac Steering Coils (4)",null,"1.02.07.05",9240344,"CN20705"]
["1","02","07","06","","",null,"L0-1TL0-2 Vacuum Components",null,"1.02.07.06",9240345,"CN20706"]
["1","02","07","07","","",null,"L0-1TL0-2 Major tube support structure",null,"1.02.07.07",9240346,"CN20707"]
["1","02","08",{"$nulls":4},"Linac to DL1 (LTDL1)",null,"Summary"]
["1","02","08","01","","",null,"LTDL1 Current Monitors (CM3)",null,"1.02.08.01",null,"CN20801"]
["1","02","08","02","","",null,"LTDL1 BPMs (6ea)",null,"1.02.08.02",9240349,"CN20802"]
["1","02","08","03","","",null,"LTDL1 OTR(5)/YAG (1)",null,"1.02.08.03",9240350,"CN20803"]
["1","02","08","04","","",null,"LTDL1 Quadrupoles (6ea)",null,"1.02.08.04",null,"CN20804"]
["1","02","08","05",null,null,null,"Reserved",null,"Summary"]
["1","02","08","06","","",null,"LTDL1 RF Kicker",null,"1.02.08.06",9240353,"CN20806"]
["1","02","08","07","","",null,"LTDL1 Steering Coils (2ea)X-Y",null,"1.02.08.07",9240354,"CN20807"]
["1","02","08","08","","",null,"LTDL1 PPS Stopper",null,"1.02.08.08",9240355,"CN20808"]
["1","02","08","09","","",null,"LTDL1 E/O EO2",null,"1.02.08.09",9240356,"CN20809"]
["1","02","08","10","","",null,"LTDL1 Minor Tube Supports",null,"1.02.08.10",9240357,"CN20810"]
["1","02","09",{"$nulls":4},"Dog Leg 1 Bend (DL1)",null,"Summary"]
["1","02","09","01","","",null,"DL1 B01 & B02 Dipoles",null,"1.02.09.01",9240359,"CN20901"]
["1","02","09","02","","",null,"DL1 QB Quadrupole",null,"1.02.09.02",null,"CN20902"]
["1","02","09","03",null,null,null,"DL1 Wire Scanner",null,"Summary"]
["1","02","09","04","","",null,"DL1 OTR",null,"1.02.09.04",9240362,"CN20904"]
["1","02","09","05","","",null,"DL1 Supports",null,"1.02.09.05",null,"CN20905"]
["1","02","09","06","","",null,"DL1 Vacuum Chamber",null,"1.02.09.06",null,"CN20906"]
["1","02","10",{"$nulls":4},"DL1 to Linac (DL1TL)",null,"Summary"]
["1","02","10","01","","",null,"DL1TL BPMs (2)",null,"1.02.10.01",9240366,"CN21001"]
["1","02","10","02","","",null,"DL1TL Steering Coils (3eaX-Y Assys)",null,"1.02.10.02",9240367,"CN21002"]
["1","02","10","03","","",null,"DL1TL Quadrupoles (2)",null,"1.02.10.03",null,"CN21003"]
["1","02","10","04","","",null,"DL1TL Vacuum Components",null,"1.02.10.04",null,"CN21004"]
["1","02","10","05","","",null,"DL1TL Current Monitor (CM4 )",null,"1.02.10.05",null,"CN21005"]
["1","02","10","06","","",null,"DL1TL OTR",null,"1.02.10.06",9240371,"CN21006"]
["1","02","10","07",null,null,null,"Reserved",null,"Summary"]
["1","02","11",{"$nulls":4},"Straight Ahead Beamline (SAB)",null,"Summary"]
["1","02","11","01","","",null,"SAB Spectrometer Dipole",null,"1.02.11.01",9240374,"CN21101"]
["1","02","11","02","","",null,"SAB Quadrupoles (3)",null,"1.02.11.02",null,"CN21102"]
["1","02","11","03","","",null,"SAB Current Monitor (CM5)",null,"1.02.11.03",null,"CN21103"]
["1","02","11","04","","",null,"SAB BPM (4ea)",null,"1.02.11.04",9240377,"CN21104"]
["1","02","11","05","","",null,"SAB YAG",null,"1.02.11.05",9240378,"CN21105"]
["1","02","11","06","","",null,"SAB Vacuum Chamber and Components",null,"1.02.11.06",null,"CN21106"]
["1","02","11","07","","",null,"SAB Beam Dump and Shielding",null,"1.02.11.07",9240380,"CN21107"]
["1","02","11","08","","",null,"SAB Supports",null,"1.02.11.08",null,"CN21108"]
["1","02","11","09","","",null,"SAB Steering Coils (2)",null,"1.02.11.09",9240382,"CN21109"]
["1","02","12",{"$nulls":4},"Injector RF Waveguide Subsystem",null,"Summary"]
["1","02","12","01","","",null,"RF Waveguides",null,"1.02.12.01",9240384,"CN21201"]
["1","02","12","02",null,null,null,"Reseved",null,"Summary"]
["1","02","13",{"$nulls":4},"Injector RF Subsystem",null,"Summary"]
["1","02","13","01",null,null,null,"S-Band Low Level System",null,"Summary"]
["1","02","13","01","01","",null,"Controls Interface & Timing",null,"1.02.13.01.01",9240388,"CN2130101"]
["1","02","13","01","02","",null,"LLRF Phase Reference System",null,"1.02.13.01.02",9240389,"CN2130102"]
["1","02","13","01","03","",null,"LLRF Monitor & Control System",null,"1.02.13.01.03",9240390,"CN2130103"]
["1","02","13","01","04","",null,"Beam Phase Monitor Cavity",null,"1.02.13.01.04",9240391,"CN2130104"]
["1","02","13","01","05","",null,"RF System S/W Development / Docs",null,"1.02.13.01.05",9240392,"CN2130105"]
["1","02","13","02",null,null,null,"Reserved",null,"Summary"]
["1","02","13","02","01",null,null,"Reserved",null,"Summary"]
["1","02","13","02","02",null,null,"Reserved",null,"Summary"]
["1","02","13","02","03",null,null,"Reserved",null,"Summary"]
["1","02","14",{"$nulls":4},"Cathode Processing (CP) Station",null,"Summary"]
["1","02","14","01","","",null,"CP Cathode Assembly & Supports",null,"1.02.14.01",null,"CN21401"]
["1","02","14","02","","",null,"CP Load Lock",null,"1.02.14.02",null,"CN21402"]
["1","02","14","03","","",null,"CP Load Lock Supports",null,"1.02.14.03",null,"CN21403"]
["1","02","14","04","","",null,"CP Station",null,"1.02.14.04",null,"CN21404"]
["1","02","14","05","","",null,"Cathode Lab Infrastructure",null,"1.02.14.05",null,"CN21405"]
["1","02","15",{"$nulls":4},"Injector Laser Heater Subsystem",null,"Summary"]
["1","02","15","01","","",null,"System Design & Optimization",null,"1.02.15.01",null,"CN21501"]
["1","02","15","02","","",null,"Beam Conditioning Optics (Laser Bay)",null,"1.02.15.02",null,"CN21502"]
["1","02","15","03","","",null,"Transport Optics (Bay to Tunnel)",null,"1.02.15.03",null,"CN21503"]
["1","02","15","04","","",null,"Chicane",null,"1.02.15.04",null,"CN21504"]
["1","02","15","05","","",null,"Undulator",null,"1.02.15.05",null,"CN21505"]
["1","02","15","06","","",null,"Photon Beam Diagnostics",null,"1.02.15.06",null,"CN21506"]
["1","02","15","07",null,null,null,"Reserved",null,"Summary"]
["1","02","15","08",null,null,null,"Reserved",null,"Summary"]
["1","02","16",{"$nulls":4},"Injector Protection & Pwr Conv Subsystem",null,"Summary"]
["1","02","16","01","","",null,"Personnel Protection Subsystem (PPS)",null,"1.02.16.01",9240413,"CN21601"]
["1","02","16","02",null,null,null,"Reserved",null,"Summary"]
["1","02","16","03","","",null,"Machine Protection Subsystem (MPS)",null,"1.02.16.03",null,"CN21603"]
["1","02","16","04",null,null,null,"Injector Power Conversion",null,"Summary"]
["1","02","16","04","01","",null,"Beamline Pwr Supplies - (Dipole Type)",null,"1.02.16.04.01",9240417,"CN2160401"]
["1","02","16","04","01","01",null,"10kw Power Supply - (Solenoid 1)",null,"1.02.16.04.01",9240417,"CN2160401"]
["1","02","16","04","01","02",null,"30kw Power Supply - (Solenoid 2)",null,"1.02.16.04.01",9240417,"CN2160401"]
["1","02","16","04","01","03",null,"Reserved",null,"Summary"]
["1","02","16","04","01","04",null,"15kw Power Supply - (B1-2)",null,"1.02.16.04.01",null,"CN2160401"]
["1","02","16","04","01","05",null,"15kw Power Supply - (B3 Spect)",null,"1.02.16.04.01",null,"CN2160401"]
["1","02","16","04","01","06",null,"10kw Power Supply - (New)",null,"1.02.16.04.01",null,"CN2160401"]
["1","02","16","04","02",null,null,"Beamline Pwr Supplies - (Trim Type)",null,"Summary"]
["1","02","16","04","02","01",null,"12Amp Power Supply - (MCOR_1)",null,"1.02.16.04.02",9240418,"CN2160402"]
["1","02","16","04","02","02",null,"30Amp Power Supply - (MCOR_2)",null,"1.02.16.04.02",9240418,"CN2160402"]
["1","02","16","04","02","03",null,"30Amp Power Supply - (MCOR_3)",null,"1.02.16.04.02",9240418,"CN2160402"]
["1","02","16","04","02","04",null,"30Amp Power Supply - (MCOR_4)",null,"1.02.16.04.02",9240418,"CN2160402"]
["1","02","16","04","03","",null,"Controls & Power Supply - Misc Hdwr",null,"1.02.16.04.03",9240419,"CN2160403"]
["1","02","16","04","04",null,null,"Reserved",null,"Summary"]
["1","02","17",{"$nulls":4},"Injector Installation & Alignment",null,"Summary"]
["1","02","17","01","","",null,"Injector Infrastructure Installation",null,"1.02.17.01",null,"CN21701"]
["1","02","17","02",null,null,null,"Reserved",null,"Summary"]
["1","02","17","03","","",null,"Injector Lasers Install & Align",null,"1.02.17.03",null,"CN21703"]
["1","02","17","04","","",null,"RF Gun & Load Lock Install & Align",null,"1.02.17.04",null,"CN21704"]
["1","02","17","05","","",null,"Gun to Linac Section (GTL) Install & Align",null,"1.02.17.05",null,"CN21705"]
["1","02","17","06","","",null,"Injector Linac Structures Install & Align",null,"1.02.17.06",null,"CN21706"]
["1","02","17","07","","",null,"L0-1 to L0-2 Section (L0-1TL0-2) Install & Align",null,"1.02.17.07",null,"CN21707"]
["1","02","17","08","","",null,"Linac to DL1 (LTDL1) Install & Align",null,"1.02.17.08",null,"CN21708"]
["1","02","17","09","","",null,"Dog Leg 1 Bend (DL1) Install & Align",null,"1.02.17.09",null,"CN21709"]
["1","02","17","10","","",null,"DL1 to Linac (DL1TL) Install & Align",null,"1.02.17.10",null,"CN21710"]
["1","02","17","11","","",null,"Straight Ahead Beamline (SAB) Install & Align",null,"1.02.17.11",null,"CN21711"]
["1","02","17","12","","",null,"Injector RF Waveguide System Install & Align",null,"1.02.17.12",null,"CN21712"]
["1","02","17","13",null,null,null,"Reserved",null,"Summary"]
["1","02","17","14","","",null,"Cathode and Load Lock Install & Align",null,"1.02.17.14",null,"CN21714"]
["1","02","17","15","","",null,"Injector Laser Heater Subsystem Install & Align",null,"1.02.17.15",null,"CN21715"]
["1","02","17","16",null,null,null,"Reserved",null,"Summary"]
["1","02","17","17","","",null,"Power  Conversion Subsystem Installation",null,"1.02.17.17",null,"CN21717"]
["1","03",{"$nulls":5},"LINAC SYSTEM",null,"Summary"]
["1","03","01",{"$nulls":4},"System Management & Integration",null,"Summary"]
["1","03","01","01",null,null,null,"Linac Mechanical Integration",null,"Summary"]
["1","03","01","01","01","",null,"L01 System Integration",null,"1.03.01.01.01",9240441,"CN3010101"]
["1","03","01","01","02","",null,"BC1 System Integration",null,"1.03.01.01.02",9240442,"CN3010102"]
["1","03","01","01","03","",null,"L02 System Integration",null,"1.03.01.01.03",9240443,"CN3010103"]
["1","03","01","01","04","",null,"BC2 System Integration",null,"1.03.01.01.04",9240444,"CN3010104"]
["1","03","01","01","05","",null,"L03 System Integration",null,"1.03.01.01.05",9240445,"CN3010105"]
["1","03","01","01","06","",null,"LTU System Integration",null,"1.03.01.01.06",9240446,"CN3010106"]
["1","03","01","01","07","",null,"E-Dump System Integration",null,"1.03.01.01.07",9240447,"CN3010107"]
["1","03","01","02",null,null,null,"Reserved",null,"Summary"]
["1","03","01","02","01",null,null,"Reserved",null,"Summary"]
["1","03","01","02","02",null,null,"Reserved",null,"Summary"]
["1","03","01","02","03",null,null,"Reserved",null,"Summary"]
["1","03","01","03","","",null,"Travel",null,"1.03.01.03",9240452,"CN30103"]
["1","03","01","04","","",null,"Linac Management",null,"1.03.01.04",9240453,"CN30104"]
["1","03","02",{"$nulls":4},"Linac Controls & Power Conversion Subsystem",null,"Summary"]
["1","03","02","01","","",null,"Personnel Protection System (PPS)",null,"1.03.02.01",9240455,"CN30201"]
["1","03","02","02","","",null,"Beam Containment System (BCS)",null,"1.03.02.02",9240456,"CN30202"]
["1","03","02","03","","",null,"Machine Protection System (MPS)",null,"1.03.02.03",9240457,"CN30203"]
["1","03","02","04",null,null,null,"Linac Power Conversion Subsystem",null,"Summary"]
["1","03","02","04","01","",null,"Beamline Power Supplies - (Dipole Type)",null,"1.03.02.04.01",9240459,"CN3020401"]
["1","03","02","04","01","01",null,"30kw Pwr Supply - (B11-14)",null,"1.03.02.04.01",null,"CN3020401"]
["1","03","02","04","01","02",null,"Power Supply - (B21-26)",null,"1.03.02.04.01",null,"CN3020401"]
["1","03","02","04","01","03",null,"78kw Pwr Supply - (B31-34)",null,"1.03.02.04.01",null,"CN3020401"]
["1","03","02","04","01","04",null,"Reserved",null,"Summary"]
["1","03","02","04","01","05",null,"Power Supply - (BY1)",null,"1.03.02.04.01",null,"CN3020401"]
["1","03","02","04","01","06",null,"Kicker (BYBKIK)",null,"1.03.02.04.01",null,"CN3020401"]
["1","03","02","04","01","07",null,"Reserved",null,"Summary"]
["1","03","02","04","01","08",null,"78kw Pwr Supply - (Dump Bend)",null,"1.03.02.04.01",null,"CN3020401"]
["1","03","02","04","01","09",null,"Reserved",null,"Summary"]
["1","03","02","04","02","",null,"Beamline Power Supplies - (Quad Type)",null,"1.03.02.04.02",9240460]
["1","03","02","04","02","01",null,"2kw Power Supply - (SEC-23)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","02",null,"2kw Power Supply - (SEC-24)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","03",null,"2kw Power Supply - (SEC-25)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","04",null,"2kw Power Supply - (SEC-26)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","05",null,"2kw Power Supply - (SEC-27)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","06",null,"2kw Power Supply - (SEC-28)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","07",null,"2kw Power Supply - (SEC-29)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","08",null,"10kw Power Supply - (Q24701)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","09",null,"10kw Power Supply - (QM21)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","10",null,"Reserved",null,"Summary"]
["1","03","02","04","02","11",null,"10kw Power Supply - (Q24901)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","12",null,"10kw Power Supply - (QM22)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","13",null,"Power Supply - (QVM1)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","14",null,"Power Supply - (QVM2)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","15",null,"Power Supply - (QVM3)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","16",null,"Power Supply - (QVM4)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","17",null,"Power Supply - (QVB1)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","18",null,"Power Supply - (QDL1)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","19",null,"Power Supply - (QE31)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","20",null,"Power Supply - (QEM1)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","21",null,"Power Supply - (QEM2)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","22",null,"Power Supply - (QEM3)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","23",null,"Power Supply - (QEM4)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","24",null,"Power Supply - (QTm1)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","25",null,"Power Supply - (QTm2)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","26",null,"Power Supply - (QUM1)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","27",null,"Power Supply - (QUM2)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","28",null,"Power Supply - (QUM3)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","29",null,"Power Supply - (QUM4)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","30",null,"Power Supply - (QDMP)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","31",null,"Power Supply - (QUE1)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","32",null,"Power Supply - (QUE2)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","03","",null,"Beamline Power Supplies - (Trim Type)",null,"1.03.02.04.03",9240461]
["1","03","02","04","03","01",null,"12Amp Power Supply - (MCOR_1)",null,"1.03.02.04.03",null,"CN3020403"]
["1","03","02","04","03","02",null,"30Amp Power Supply - (MCOR_2)",null,"1.03.02.04.03",null,"CN3020403"]
["1","03","02","04","03","03",null,"30Amp Power Supply - (MCOR_3)",null,"1.03.02.04.03",null,"CN3020403"]
["1","03","02","04","03","04",null,"30Amp Power Supply - (MCOR_4)",null,"1.03.02.04.03",null,"CN3020403"]
["1","03","02","04","03","05",null,"Reserved",null,"Summary"]
["1","03","02","04","03","06",null,"Reserved",null,"Summary"]
["1","03","02","04","03","07",null,"Reserved",null,"Summary"]
["1","03","02","04","03","08",null,"Reserved",null,"Summary"]
["1","03","02","04","03","09",null,"Reserved",null,"Summary"]
["1","03","02","04","03","10",null,"Power Supply - (MCOR_LTU1)",null,"1.03.02.04.03",null,"CN3020403"]
["1","03","02","04","03","11",null,"Power Supply - (MCOR_LTU2)",null,"1.03.02.04.03",null,"CN3020403"]
["1","03","02","04","03","12",null,"Power Supply - (MCOR_LTU3)",null,"1.03.02.04.03",null,"CN3020403"]
["1","03","02","04","03","13",null,"Power Supply - (MCOR_LTU4)",null,"1.03.02.04.03",null,"CN3020403"]
["1","03","02","04","03","14",null,"Power Supply - (MCOR_LTU5)",null,"1.03.02.04.03",null,"CN3020403"]
["1","03","02","04","03","15",null,"Power Supply - (MCOR_LTU6)",null,"1.03.02.04.03",null,"CN3020403"]
["1","03","02","04","04","",null,"Controls & Power Supply ",null,"1.03.02.04.04",9240462,"CN3020404"]
["1","03","02","05","","",null,"Controls - LLRF",null,"1.03.02.05",9240463,"CN30205"]
["1","03","02","06",null,null,null,"Controls - E-Beam Diagnostic",null,"Summary"]
["1","03","02","06","01","",null,"Controls - Wire Scanners",null,"1.03.02.06.01",9240465,"CN3020601"]
["1","03","02","06","02","",null,"Controls - BPMs",null,"1.03.02.06.02",9240466,"CN3020602"]
["1","03","02","06","03","",null,"Controls - Toroids",null,"1.03.02.06.03",9240467,"CN3020603"]
["1","03","02","06","04","",null,"Controls - Stoppers",null,"1.03.02.06.04",9240468,"CN3020604"]
["1","03","02","06","05","",null,"Controls - Profile Monitors",null,"1.03.02.06.05",9240469,"CN3020605"]
["1","03","02","06","06","",null,"Controls - E/O Diagnostics",null,"1.03.02.06.06",9240470,"CN3020606"]
["1","03","02","06","07","",null,"Controls - Bunch Length Monitors",null,"1.03.02.06.07",9240471,"CN3020607"]
["1","03","02","06","08","",null,"Controls - Beam Loss Monitors",null,"1.03.02.06.08",9240472,"CN3020608"]
["1","03","02","06","09","",null,"Controls - Single Beam Dump",null,"1.03.02.06.09",9240473,"CN3020609"]
["1","03","02","06","10","",null,"Controls - E Beam Dump",null,"1.03.02.06.10",9240474,"CN3020610"]
["1","03","02","06","11","",null,"Controls - Protection Collimator",null,"1.03.02.06.11",9240475,"CN3020611"]
["1","03","02","06","12","",null,"Controls - Movable Collimator",null,"1.03.02.06.12",9240476,"CN3020612"]
["1","03","02","06","13","",null,"Controls - X-Band Accel Structure",null,"1.03.02.06.13",9240477,"CN3020613"]
["1","03","02","07",null,null,null,"Reserved",null,"Summary"]
["1","03","02","08","","",null,"Controls - Timing",null,"1.03.02.08",9240479,"CN30208"]
["1","03","02","09",null,null,null,"Controls - Vacuum",null,"Summary"]
["1","03","02","09","01","",null,"Controls - Vacuum Instrumentation & Interlocks",null,"1.03.02.09.01",9240481,"CN3020901"]
["1","03","02","09","02","",null,"Controls - Vacuum Pump Power Supplies",null,"1.03.02.09.02",null,"CN3020902"]
["1","03","02","10",null,null,null,"Software & Controls Infrastructure",null,"Summary"]
["1","03","02","10","01",null,null,"Reserved",null,"Summary"]
["1","03","02","10","02",null,null,"Reserved",null,"Summary"]
["1","03","02","10","03",null,null,"Reserved",null,"Summary"]
["1","03","02","10","04","",null,"Data Communications",null,"1.03.02.10.04",null,"CN3021004"]
["1","03","02","10","05","",null,"Computers",null,"1.03.02.10.05",9240488,"CN3021005"]
["1","03","03",{"$nulls":4},"Linac Magnets & Supports",null,"Summary"]
["1","03","03","01","","",null,"Bend Magnet (BX1_BC1)",null,"1.03.03.01",null,"CN30301"]
["1","03","03","02","","",null,"Bend Magnet (BX3_LTU)",null,"1.03.03.02",9240491,"CN30302"]
["1","03","03","03","","",null,"Bend Magnet (BX2_BC2)",null,"1.03.03.03",null,"CN30303"]
["1","03","03","04","","",null,"Bend Magnet (BY_LTU)",null,"1.03.03.04",9240493,"CN30304"]
["1","03","03","05","","",null,"Quad Magnet (Quad_LTU)",null,"1.03.03.05",9240494,"CN30305"]
["1","03","03","06",null,null,null,"Reserved",null,"Summary"]
["1","03","03","07","","",null,"Quad Magnet (QE)",null,"1.03.03.07",9240496,"CN30307"]
["1","03","03","08","","",null,"Corrector Magnet (Type 4)",null,"1.03.03.08",9240497,"CN30308"]
["1","03","03","09","","",null,"Bend Magnet (BYD_LTU)",null,"1.03.03.09",9240498,"CN30309"]
["1","03","03","10","","",null,"Quad Magnet (QA)",null,"1.03.03.10",9240499,"CN30310"]
["1","03","03","11","","",null,"Bend Magnet (BYPM_LTU)",null,"1.03.03.11",9240500,"CN30311"]
["1","03","03","12","","",null,"Bend Magnet (BYKIK_LTU)",null,"1.03.03.12",9240501,"CN30312"]
["1","03","03","13","","",null,"Bend Magnet (BYW_LTU)",null,"1.03.03.13",9240502,"CN30313"]
["1","03","04",{"$nulls":4},"Linac Vacuum Subsystem",null,"Summary"]
["1","03","04","01",null,null,null,"Reserved",null,"Summary"]
["1","03","04","02","","",null,"Linac Beamline Vacuum System",null,"1.03.04.02",9240505,"CN30402"]
["1","03","04","03","","",null,"BC1 Vacuum System",null,"1.03.04.03",9240506,"CN30403"]
["1","03","04","04","","",null,"BC2 Vacuum System",null,"1.03.04.04",9240507,"CN30404"]
["1","03","04","05","","",null,"Linac to Undulator (LTU) Vacuum System",null,null,9240508]
["1","03","04","06","","",null,"Dumpline Vacuum System",null,"1.03.04.06",9240509,"CN30406"]
["1","03","05",{"$nulls":4},"Linac Electron Diagnostics",null,"Summary"]
["1","03","05","01","","",null,"Wire Scanners (15)",null,"1.03.05.01",9240511,"CN30501"]
["1","03","05","02",null,null,null,"Beam Position Monitors",null,"Summary"]
["1","03","05","02","01","",null,"BPMs - Linac Standard (6ea)",null,"1.03.05.02.01",9240513,"CN3050201"]
["1","03","05","02","02","",null,"BPMs - RF (8ea)",null,"1.03.05.02.02",9240514,"CN3050202"]
["1","03","05","02","03","",null,"BPMs - FFTB (9ea)",null,"1.03.05.02.03",9240515,"CN3050203"]
["1","03","05","02","04","",null,"BPMs - High Resolution BC1 (3ea)",null,"1.03.05.02.04",9240516,"CN3050204"]
["1","03","05","03","","",null,"Toroids (9ea) Beam Charge",null,"1.03.05.03",9240517,"CN30503"]
["1","03","05","04","","",null,"Stoppers TU Dump (2ea)",null,"1.03.05.04",9240518,"CN30504"]
["1","03","05","05","","",null,"Profile Monitors (6/4/1 ea)",null,"1.03.05.05",9240519,"CN30505"]
["1","03","05","06","","",null,"E/O Bunch Length Monitors (1ea)",null,"1.03.05.06","CN30506","CN30506"]
["1","03","05","07","","",null,"Bunch Length Monitors (4ea)",null,"1.03.05.07",9240521,"CN30507"]
["1","03","05","08",null,null,null,"Beam Loss Monitors",null,"Summary"]
["1","03","05","08","01","",null,"Beam Loss Monitors (10 PIC)",null,"1.03.05.08.01",9240523,"CN3050801"]
["1","03","05","08","02","",null,"Beam Loss Monitors (2 PLIC)",null,"1.03.05.08.02",9240524,"CN3050802"]
["1","03","05","09","","",null,"Single Beam Dump (1ea)",null,"1.03.05.09",9240525,"CN30509"]
["1","03","05","10","","",null,"Electron Beam Dump (1ea)",null,"1.03.05.10",9240526,"CN30510"]
["1","03","05","11","","",null,"Protection Collimators (4ea)",null,"1.03.05.11",9240527,"CN30511"]
["1","03","05","12","","",null,"Movable Collimators (6ea)",null,"1.03.05.12",9240528,"CN30512"]
["1","03","05","13","","",null,"Safety Dump",null,"1.03.05.13",9240529,"CN30513"]
["1","03","06",{"$nulls":4},"Linac RF Subsystem",null,"Summary"]
["1","03","06","01",null,null,null,"Reserved",null,"Summary"]
["1","03","06","02","","",null,"S-Band High Power System",null,"1.03.06.02",9240532,"CN30602"]
["1","03","06","03","","",null,"S-Band Structures",null,"1.03.06.03",null,"CN30603"]
["1","03","06","04","","",null,"X-Band Low Level System",null,"1.03.06.04",9240534,"CN30604"]
["1","03","06","05",null,null,null,"X-Band High Power System",null,"Summary"]
["1","03","06","05","01","",null,"X-Band HP Klystron",null,"1.03.06.05.01",9240536,"CN3060501"]
["1","03","06","05","02","",null,"X-Band HP Modulator",null,"1.03.06.05.02",9240537,"CN3060502"]
["1","03","06","05","03","",null,"X-Band HP Waveguide System",null,"1.03.06.05.03",null,"CN3060503"]
["1","03","06","06","","",null,"X-Band Structures",null,"1.03.06.06",null,"CN30606"]
["1","03","06","07",null,null,null,"RF Distribution System",null,"Summary"]
["1","03","06","07","01","",null,"Modulator Refurbishment",null,"1.03.06.07.01",null,"CN3060701"]
["1","03","06","07","02","",null,"Solid State Sub Booster",null,"1.03.06.07.02",null,"CN3060702"]
["1","03","06","07","03","",null,"IPA Modifications",null,"1.03.06.07.03",null,"CN3060703"]
["1","03","06","07","04","",null,"Klystron Controls Interfaces",null,"1.03.06.07.04",null,"CN3060704"]
["1","03","06","07","05","",null,"Bunch Length Electronics",null,"1.03.06.07.05",null,"CN3060705"]
["1","03","06","07","06","",null,"RF Phase Measurements",null,"1.03.06.07.06",null,"CN3060706"]
["1","03","06","07","07","",null,"RF Distribution L2 & L3",null,"1.03.06.07.07",null,"CN3060707"]
["1","03","06","07","08","",null,"RF Fiber Optics Electronics System",null,"1.03.06.07.08",null,"CN3060708"]
["1","03","06","07","09","",null,"RF Stability",null,"1.03.06.07.09",null,"CN3060709"]
["1","03","07",{"$nulls":4},"Linac Installation & Alignment",null,"Summary"]
["1","03","07","01","","",null,"Linac L01 System Installation & Alignment",null,"1.03.07.01",null,"CN30701"]
["1","03","07","02","","",null,"Linac BC1 System Installation & Alignment",null,"1.03.07.02",null,"CN30702"]
["1","03","07","03","","",null,"Linac L02 System Installation & Alignment",null,"1.03.07.03",null,"CN30703"]
["1","03","07","04","","",null,"Linac BC2 System Installation & Alignment",null,"1.03.07.04",null,"CN30704"]
["1","03","07","05","","",null,"Linac L03 System Installation & Alignment",null,"1.03.07.05",null,"CN30705"]
["1","03","07","06","","",null,"Linac LTU System Installation & Alignment",null,"1.03.07.06",null,"CN30706"]
["1","03","07","07","","",null,"Linac E-Dump System Installation & Alignment",null,"1.03.07.07",null,"CN30707"]
["1","04",{"$nulls":5},"UNDULATOR SYSTEM",null,"Summary"]
["1","04","01",{"$nulls":4},"Undulator System Management & Integration",null,"Summary"]
["1","04","01","01",null,null,null,"Undulator System Management",null,"Summary"]
["1","04","01","01","01","",null,"Undulator System Management - Technical",null,"1.04.01.01.01","PD4010101","CN4010101"]
["1","04","01","01","02","",null,"ANL Project Support",null,"1.04.01.01.02","PD4010102","CN4010102"]
["1","04","01","02",null,null,null,"Undulator System Materials & Supplies",null,"Summary"]
["1","04","01","02","01","",null,"Undulator System M&S - General",null,"1.04.01.02.01","PD4010201","CN4010201"]
["1","04","01","02","02","",null,"Undulator System Travel",null,"1.04.01.02.02","PD4010202","CN4010202"]
["1","04","01","03","","",null,"Undulator System Reviews and Workshops",null,"1.04.01.03","PD40103","CN40103"]
["1","04","02",{"$nulls":4},"Controls",null,"Summary"]
["1","04","02","01",null,null,null,"Controls Management and Integration",null,"Summary"]
["1","04","02","01","01",null,null,"Reserved",null,"Summary"]
["1","04","02","01","02",null,null,"Reserved",null,"Summary"]
["1","04","02","01","03","",null,"Software Interface with SLAC",null,"1.04.02.01.03","PD4020103","CN4020103"]
["1","04","02","01","04",null,null,"Reserved",null,"Summary"]
["1","04","02","02",null,null,null,"Motion",null,"Summary"]
["1","04","02","02","01",null,null,"Fine Motion",null,"Summary"]
["1","04","02","02","01","01",null,"Motor Interface",null,"1.04.02.02.01","PD4020201","CN4020201"]
["1","04","02","02","01","02",null,"Encoder Interface",null,"1.04.02.02.01","PD4020201","CN4020201"]
["1","04","02","02","01","03",null,"Motor Driver",null,"1.04.02.02.01","PD4020201","CN4020201"]
["1","04","02","02","01","04",null,"Cabling",null,"1.04.02.02.01","PD4020201","CN4020201"]
["1","04","02","02","01","05",null,"Integrate components",null,"1.04.02.02.01","PD4020201","CN4020201"]
["1","04","02","02","02",null,null,"Phase Corrector Motion",null,"Summary"]
["1","04","02","02","02","01",null,"Motor Interface",null,"1.04.02.02.02","PD4020202","CN4020202"]
["1","04","02","02","02","02",null,"Reserved",null,"Summary"]
["1","04","02","02","02","03",null,"Reserved",null,"Summary"]
["1","04","02","02","02","04",null,"Cabling",null,"1.04.02.02.02","PD4020202","CN4020202"]
["1","04","02","02","02","05",null,"Integrate components",null,"1.04.02.02.02","PD4020202","CN4020202"]
["1","04","02","02","03",null,null,"Reserved",null,"Summary"]
["1","04","02","02","04",null,null,"Reserved",null,"Summary"]
["1","04","02","02","05",null,null,"Reserved",null,"Summary"]
["1","04","02","02","06",null,null,"Scanning Wire Motion",null,"Summary"]
["1","04","02","02","06","01",null,"Motor Interface",null,"1.04.02.02.06","PD4020206"]
["1","04","02","02","06","02",null,"Reserved",null,"Summary"]
["1","04","02","02","06","03",null,"Reserved",null,"Summary"]
["1","04","02","02","06","04",null,"Reserved",null,"Summary"]
["1","04","02","02","06","05",null,"Integrate components",null,"1.04.02.02.06","PD4020206","CN4020206"]
["1","04","02","02","07",null,null,"Macroscopic Motion",null,"Summary"]
["1","04","02","02","07","01",null,"Motor Interface",null,"1.04.02.02.07","PD4020207","CN4020207"]
["1","04","02","02","07","02",null,"Reserved",null,"Summary"]
["1","04","02","02","07","03",null,"Motor Driver",null,"1.04.02.02.07","PD4020207","CN4020207"]
["1","04","02","02","07","04",null,"Cabling",null,"1.04.02.02.07","PD4020207","CN4020207"]
["1","04","02","02","07","05",null,"Integrate components",null,"1.04.02.02.07","PD4020207","CN4020207"]
["1","04","02","03",null,null,null,"Signal Analysis",null,"Summary"]
["1","04","02","03","01",null,null,"RFBPM",null,"Summary"]
["1","04","02","03","01","01",null,"Reserved",null,"Summary"]
["1","04","02","03","01","02",null,"Signal Acquisition",null,"1.04.02.03.01","PD4020301","CN4020301"]
["1","04","02","03","01","03",null,"Timing interface",null,"1.04.02.03.01","PD4020301","CN4020301"]
["1","04","02","03","01","04",null,"Cabling",null,"1.04.02.03.01","PD4020301","CN4020301"]
["1","04","02","03","01","05",null,"Integrate components",null,"1.04.02.03.01","PD4020301","CN4020301"]
["1","04","02","03","02",null,null,"Charge Monitor",null,"Summary"]
["1","04","02","03","02","01",null,"Reserved",null,"Summary"]
["1","04","02","03","02","02",null,"Reserved",null,"Summary"]
["1","04","02","03","02","03",null,"Integrate components",null,"1.04.02.03.02","PD4020302","CN4020302"]
["1","04","02","03","03",null,null,"Scanning Wire",null,"Summary"]
["1","04","02","03","03","01",null,"Reserved",null,"Summary"]
["1","04","02","03","03","02",null,"Reserved",null,"Summary"]
["1","04","02","03","03","03",null,"Reserved",null,"Summary"]
["1","04","02","03","03","04",null,"Reserved",null,"Summary"]
["1","04","02","03","03","05",null,"Reserved",null,"Summary"]
["1","04","02","03","03","06",null,"Integrate components",null,"1.04.02.03.03","PD4020303","CN4020303"]
["1","04","02","04",null,null,null,"Video",null,"Summary"]
["1","04","02","04","01",null,null,"OTR Monitor",null,"Summary"]
["1","04","02","04","01","01",null,"Camera",null,"1.04.02.04.01","PD4020401","CN4020401"]
["1","04","02","04","01","02",null,"Camera trigger interface",null,"1.04.02.04.01","PD4020401","CN4020401"]
["1","04","02","04","01","03",null,"Digitizer",null,"1.04.02.04.01","PD4020401","CN4020401"]
["1","04","02","04","01","04",null,"Timing interface",null,"Summary"]
["1","04","02","04","01","05",null,"Cabling",null,"1.04.02.04.01","PD4020401","CN4020401"]
["1","04","02","04","01","06",null,"Integrate components",null,"1.04.02.04.01","PD4020401","CN4020401"]
["1","04","02","04","02",null,null,"Reserved",null,"Summary"]
["1","04","02","04","03",null,null,"Observation station video",null,"Summary"]
["1","04","02","04","03","01",null,"Camera",null,"1.04.02.04.03","PD4020403","CN4020403"]
["1","04","02","04","03","02",null,"Camera trigger interface",null,"1.04.02.04.03",null,"CN4020403"]
["1","04","02","04","03","03",null,"Multiplexor",null,"1.04.02.04.03","PD4020403","CN4020403"]
["1","04","02","04","03","04",null,"Cabling",null,"1.04.02.04.03","PD4020403","CN4020403"]
["1","04","02","04","03","05",null,"Integrate components",null,"1.04.02.04.03","PD4020403","CN4020403"]
["1","04","02","05",null,null,null,"Data Acquisition and Control",null,"Summary"]
["1","04","02","05","01",null,null,"Strongback Temperature monitoring",null,"Summary"]
["1","04","02","05","01","01",null,"Integrate components",null,"1.04.02.05.01","PD4020501","CN4020501"]
["1","04","02","06",null,null,null,"Vacuum",null,"Summary"]
["1","04","02","06","01",null,null,"Ion Pump Controller",null,"Summary"]
["1","04","02","06","01","01",null,"Integrate components",null,"1.04.02.06.01","PD4020601","CN4020601"]
["1","04","02","06","02",null,null,"Reserved",null,"Summary"]
["1","04","02","06","03",null,null,"Reserved",null,"Summary"]
["1","04","02","06","04",null,null,"RGA",null,"Summary"]
["1","04","02","06","04","01",null,"Integrate components",null,"1.04.02.06.04","PD4020604","CN4020604"]
["1","04","02","07",null,null,null,"Machine Protection",null,"Summary"]
["1","04","02","07","01",null,null,"Undulator Global MPS",null,"Summary"]
["1","04","02","07","01","01",null,"Hardware design",null,"1.04.02.07.01","PD4020701","CN4020701"]
["1","04","02","07","01","02",null,"Interface components",null,"1.04.02.07.01","PD4020701","CN4020701"]
["1","04","02","07","02",null,null,"Cerenkov Detector",null,"Summary"]
["1","04","02","07","02","01",null,"Signal interface",null,"1.04.02.07.02","PD4020702","CN4020702"]
["1","04","02","07","03",null,null,"Gamma Ray Detector",null,"Summary"]
["1","04","02","07","03","01",null,"Signal interface",null,"1.04.02.07.03","PD4020703","CN4020703"]
["1","04","02","07","04",null,null,"Chamber Temperature",null,"Summary"]
["1","04","02","07","04","01",null,"Signal interface",null,"1.04.02.07.04","PD4020704","CN4020704"]
["1","04","03",{"$nulls":4},"Undulator Magnet & Support",null,"Summary"]
["1","04","03","01","","",null,"UND Magnet & Support - Mgmt and Integration",null,"1.04.03.01",null,"CN40301"]
["1","04","03","02","","",null,"First Prototype Undulator & Mfg Plan",null,"1.04.03.02","PD40302"]
["1","04","03","03",null,null,null,"1st Article Undulators & Long Lead Procurements",null,"Summary"]
["1","04","03","03","01","",null,"Ti Strongback (LLP)",null,"1.04.03.03.01","PD4030301","CN4030301"]
["1","04","03","03","02","",null,"Magnet Blocks (LLP)",null,"1.04.03.03.02","PD4030302","CN4030302"]
["1","04","03","03","03","",null,"Magnet Poles (LLP)",null,"1.04.03.03.03","PD4030303","CN4030303"]
["1","04","03","03","04","",null,"Magnet Assembly & Supports - 1st Articles",null,"1.04.03.03.04","PD4030304","CN4030304"]
["1","04","03","03","05","",null,"Magnetic Measurement (ANL or SLAC)",null,"1.04.03.03.05",null,"CN4030305"]
["1","04","03","04",null,null,null,"Production Undulator",null,"Summary"]
["1","04","03","04","01","",null,"Magnet Assembly & Supports",null,"1.04.03.04.01",null,"CN4030401"]
["1","04","03","04","02",null,null,"Reserved",null,"Summary"]
["1","04","03","05",null,null,null,"Focusing Magnets",null,"Summary"]
["1","04","03","05","01","",null,"Quadrupoles",null,"1.04.03.05.01","PD4030501","CN4030501"]
["1","04","03","05","02",null,null,"Reserved",null,"Summary"]
["1","04","03","06",null,null,null,"Undulator Magnetic Measurement Facility (SLAC)",null,"Summary"]
["1","04","03","06","01",null,null,"Undulator MMF Setup",null,"Summary"]
["1","04","03","06","01","01",null,"Undulator Test Stand Prototype",null,"1.04.03.06.01",null,"CN4030601"]
["1","04","03","06","01","02",null,"Reserved",null,"Summary"]
["1","04","03","06","01","03",null,"Reserved",null,"Summary"]
["1","04","03","06","01","04",null,"Undulator Test Stand",null,"1.04.03.06.01",null,"CN4030601"]
["1","04","03","06","01","05",null,"Undulator Fiducialization",null,"1.04.03.06.01",null,"CN4030601"]
["1","04","03","06","01","06",null,"Quad Strength and Field Quality",null,"1.04.03.06.01",null,"CN4030601"]
["1","04","03","06","01","07",null,"Quad Fiducialization System",null,"1.04.03.06.01",null,"CN4030601"]
["1","04","03","06","01","08",null,"Hall Probe Calibration System",null,"1.04.03.06.01",null,"CN4030601"]
["1","04","03","06","01","09",null,"Undulator Handling",null,"1.04.03.06.01",null,"CN4030601"]
["1","04","03","06","02",null,null,"Fiducialization and Magnetic Measurements (F/MM)",null,"Summary"]
["1","04","03","06","02","01",null,"F/MM Undulator Magnet Sections",null,"1.04.03.06.02",null,"CN4030602"]
["1","04","03","06","02","02",null,"F/MM Quadrupoles",null,"1.04.03.06.02",null,"CN4030602"]
["1","04","03","06","02","03",null,"F/MM BPMs",null,"1.04.03.06.02",null,"CN4030602"]
["1","04","03","06","02","04",null,"F/MM Correctors",null,"1.04.03.06.02",null,"CN4030602"]
["1","04","03","06","02","05",null,"F/MM Vacuum Chamber",null,"1.04.03.06.02",null,"CN4030602"]
["1","04","03","06","02","06",null,"F/MM Photon Diagnostics Components",null,"1.04.03.06.02",null,"CN4030602"]
["1","04","03","06","03",null,null,"Undulator Monitoring",null,"Summary"]
["1","04","03","06","03","01",null,"Stretched Wire System",null,"1.04.03.06.03",null,"CN4030603"]
["1","04","03","06","03","02",null,"Hydrostatic Level System",null,"1.04.03.06.03",null,"CN4030603"]
["1","04","03","06","03","03",null,"Alignment Hardware & Software",null,"1.04.03.06.03",null,"CN4030603"]
["1","04","03","07",null,null,null,"Reserved",null,"Summary"]
["1","04","03","08",null,null,null,"Fixed Supports",null,"Summary"]
["1","04","03","08","01","",null,"Fixed Sppt Mgmt & Integration",null,"1.04.03.08.01","PD4030801"]
["1","04","03","08","02","",null,"Fixed Support Design",null,"1.04.03.08.02",null,"CN4030802"]
["1","04","03","08","03","",null,"Stabilized Girder Assemblies",null,"1.04.03.08.03",null,"CN4030803"]
["1","04","03","08","04","",null,"Thermal Intercept System",null,"1.04.03.08.04",null,"CN4030804"]
["1","04","03","08","05","",null,"Thermometry",null,"1.04.03.08.05",null,"CN4030805"]
["1","04","03","08","06","",null,"Kinematic Girder Support",null,"1.04.03.08.06",null,"CN4030806"]
["1","04","03","08","07","",null,"Earthquake Bracing",null,"1.04.03.08.07",null,"CN4030807"]
["1","04","03","08","08","",null,"Controls and Software",null,"1.04.03.08.08",null,"CN4030808"]
["1","04","04",{"$nulls":4},"Vacuum System",null,"Summary"]
["1","04","04","01",null,null,null,"Project Oversight",null,"Summary"]
["1","04","04","02",null,null,null,"Undulator Vacuum Chamber Assembly",null,"Summary"]
["1","04","04","02","01","",null,"Prototype Chamber Weldment",null,"1.04.04.02.01","PD4040201","CN4040201"]
["1","04","04","02","02","",null,"Production Chamber Weldment",null,"1.04.04.02.02","PD4040202","CN4040202"]
["1","04","04","03",null,null,null,"Beam-line Bellows Module Assembly",null,"Summary"]
["1","04","04","03","01","",null,"Prototype Bellows Module",null,"1.04.04.03.01","PD4040301","CN4040301"]
["1","04","04","03","02","",null,"Production Bellows Module",null,"1.04.04.03.02","PD4040302","CN4040302"]
["1","04","04","04",null,null,null,"Reserved",null,"Summary"]
["1","04","04","05","","",null,"Short Diagnostic Break (SDB) Assembly",null,"1.04.04.05","PD40405","CN40405"]
["1","04","04","06","","",null,"Long Diagnostic Break (LDB) Assembly",null,"1.04.04.06","PD40406","CN40406"]
["1","04","04","07","","",null,"Entrance Section Assembly",null,"1.04.04.07","PD40407","CN40407"]
["1","04","04","08","","",null,"Exit Section Assembly",null,"1.04.04.08","PD40408","CN40408"]
["1","04","04","09","","",null,"Baking System",null,"1.04.04.09","PD40409","CN40409"]
["1","04","05",{"$nulls":4},"Diagnostics",null,"Summary"]
["1","04","05","01",null,null,null,"Project Oversight",null,"Summary"]
["1","04","05","02",null,null,null,"E-Beam and X-Ray Profile Diagnostics",null,"Summary"]
["1","04","05","02","01","",null,"EBXPD Test Station",null,"1.04.05.02.01","PD4050201","CN4050201"]
["1","04","05","02","02","",null,"EBXPD Vacuum Chamber",null,"1.04.05.02.02","PD4050202","CN4050202"]
["1","04","05","02","03","",null,"Positioning Mechanism",null,"1.04.05.02.03","PD4050203","CN4050203"]
["1","04","05","02","04","",null,"Scanning wire assembly (EBXPD -SWA)",null,"1.04.05.02.04","PD4050204","CN4050204"]
["1","04","05","02","05","",null,"Optical transition radiation imaging assembly",null,"1.04.05.02.05","PD4050205","CN4050205"]
["1","04","05","02","06",null,null,"Reserved",null,"Summary"]
["1","04","05","02","07",null,null,"Reserved",null,"Summary"]
["1","04","05","02","08",null,null,"Reserved",null,"Summary"]
["1","04","05","02","09","",null,"EBXPD  Design & Integration",null,"1.04.05.02.09","PD4050209","CN4050209"]
["1","04","05","03",null,null,null,"Reserved",null,"Summary"]
["1","04","05","04",null,null,null,"End-of-Undulator(EOU) X-ray and Profile diagnost",null,"Summary"]
["1","04","05","04","01","",null,"Prototype Construction and Testing",null,"1.04.05.04.01","PD4050401","CN4050401"]
["1","04","05","04","02","",null,"Bunch Length Monitor-Streak Camera (BLM)",null,"1.04.05.04.02",null,"CN4050402"]
["1","04","05","04","03","",null,"Upstream corrector / separator",null,"1.04.05.04.03","PD4050403","CN4050403"]
["1","04","05","04","04","",null,"Optical Diffraction radiation imaging assembly (",null,"1.04.05.04.04","PD4050404","CN4050404"]
["1","04","05","04","05","",null,"X-ray High Resolution monochromator assembly (EO",null,"1.04.05.04.05","PD4050405","CN4050405"]
["1","04","05","04","06","",null,"X-ray Imaging High Resolution detector assembly",null,"1.04.05.04.06","PD4050406","CN4050406"]
["1","04","05","04","07","",null,"EOU Design and Integration",null,"1.04.05.04.07","PD4050407","CN4050407"]
["1","04","05","05","","",null,"RFBPM",null,"1.04.05.05","PD40505","CN40505"]
["1","04","05","06",null,null,null,"Reserved",null,"Summary"]
["1","04","05","07","","",null,"Charge Monitor (CM)",null,"1.04.05.07","PD40507","CN40507"]
["1","04","05","08","","",null,"Cherenkov Detector",null,"1.04.05.08","PD40508","CN40508"]
["1","04","05","09","","",null,"Radiation Detection Monitor (RDM)",null,"1.04.05.09","PD40509","CN40509"]
["1","04","05","10",null,null,null,"Reserved",null,"Summary"]
["1","04","05","11","","",null,"Supplemental Shielding",null,"1.04.05.11","PD40511","CN40511"]
["1","04","06",{"$nulls":4},"Undulator System Installation and Alignment",null,"Summary"]
["1","04","06","01",null,null,null,"Undulator System Installation and Alignment Inte",null,"Summary"]
["1","04","06","01","01","",null,"Undulator System",null,"1.04.06.01.01",null,"CN4060101"]
["1","04","06","01","02",null,null,"Entrance Section",null,"Summary"]
["1","04","06","01","03",null,null,"Exit Section",null,"Summary"]
["1","04","06","02","","",null,"Control System Installation and Alignment",null,"1.04.06.02",null,"CN40602"]
["1","04","06","03",null,null,null,"Magnets & Supports Installation and Alignment",null,"Summary"]
["1","04","06","03","01",null,null,"Magnets Installation and Alignment",null,"Summary"]
["1","04","06","03","02",null,null,"Fixed Supports Installation and Alignment",null,"Summary"]
["1","04","06","04","","",null,"Vacuum System Installation and Alignment",null,"1.04.06.04",null,"CN40604"]
["1","04","06","05","","",null,"Diagnostics System Installation and Alignment",null,"1.04.06.05",null,"CN40605"]
["1","05",{"$nulls":5},"X-RAY TRANSPORT & DIAGNOSTICS SYSTEMS",null,"Summary"]
["1","05","01",{"$nulls":4},"System Management & Integration",null,"Summary"]
["1","05","01","01",null,null,null,"Management",null,"Summary"]
["1","05","01","01","01","",null,"XTOD Management - Technical",null,"1.05.01.01.01","PD50101","CN50101"]
["1","05","01","01","02","",null,"LLNL Project Support",null,"1.05.01.01.02","PD50101","CN50101"]
["1","05","02",{"$nulls":4},"Controls",null,"Summary"]
["1","05","02","01",null,null,null,"Reserved",null,"Summary"]
["1","05","02","02","","",null,"Slow Controls",null,"1.05.02.02","PD50202","CN50202"]
["1","05","02","03","","",null,"Fast Controls",null,"1.05.02.03","PD50203","CN50203"]
["1","05","02","04","","",null,"Femto Controls",null,"1.05.02.04","PD50204","CN50204"]
["1","05","03",{"$nulls":4},"Mechanical & Vacuum Subsystem",null,"Summary"]
["1","05","03","01",null,null,null,"Reserved",null,"Summary"]
["1","05","03","02","","",null,"Mech/Vac Front End",null,"1.05.03.02","PD50302","CN50302"]
["1","05","03","03",null,null,null,"Mech/Vac Near Hall",null,"Summary"]
["1","05","03","03","01","",null,"NEH Hutch 1",null,"1.05.03.03.01","PD5030301","CN5030301"]
["1","05","03","03","02","",null,"NEH Hutch 2",null,"1.05.03.03.02","PD5030302","CN5030302"]
["1","05","03","03","03","",null,"NEH Hutch 3",null,"1.05.03.03.03","PD5030303","CN5030303"]
["1","05","03","04","","",null,"Mech/Vac Tunnel",null,"1.05.03.04","PD50304","CN50304"]
["1","05","03","05",null,null,null,"Mech/Vac Far Hall",null,"Summary"]
["1","05","03","05","01","",null,"FEH Hutch 1",null,"1.05.03.05.01","PD5030501","CN5030501"]
["1","05","03","05","02","",null,"FEH Hutch 2",null,"1.05.03.05.02","PD5030502","CN5030502"]
["1","05","03","05","03","",null,"FEH Hutch 3",null,"1.05.03.05.03","PD5030503","CN5030503"]
["1","05","04",{"$nulls":4},"Optical  Subsystem",null,"Summary"]
["1","05","04","01",null,null,null,"Reserved",null,"Summary"]
["1","05","04","02",null,null,null,"Facility Optics",null,"Summary"]
["1","05","04","02","01",null,null,"Reserved",null,"Summary"]
["1","05","04","02","02","",null,"Fixed Mask",null,"1.05.04.02.02","PD5040202","CN5040202"]
["1","05","04","02","03","",null,"Slit/Collimators",null,"1.05.04.02.03","PD5040203","CN5040203"]
["1","05","04","02","04","",null,"Flipper Mirror",null,"1.05.04.02.04","PD5040204","CN5040204"]
["1","05","04","02","05","",null,"Gas Attenuator",null,"1.05.04.02.05","CN5040205","CN5040205"]
["1","05","04","02","06",null,null,"Reserved",null,"Summary"]
["1","05","04","02","07",null,null,"Reserved",null,"Summary"]
["1","05","04","02","08","",null,"Solid Attenuator",null,"1.05.04.02.08",null,"CN5040208"]
["1","05","04","02","09",null,null,"Reserved",null,"Summary"]
["1","05","04","03",null,null,null,"End Station Optics",null,"Summary"]
["1","05","04","03","01",null,null,"Reserved",null,"Summary"]
["1","05","04","03","02","",null,"Optics Tank - Near Hall",null,"1.05.04.03.02",null,"CN5040302"]
["1","05","04","03","03",null,null,"Reserved",null,"Summary"]
["1","05","04","03","04",null,null,"Reserved",null,"Summary"]
["1","05","04","03","05",null,null,"Reserved",null,"Summary"]
["1","05","04","04",null,null,null,"Crystals & Gratings",null,"Summary"]
["1","05","04","04","01",null,null,"Reserved",null,"Summary"]
["1","05","04","04","02","",null,"System Monochrometer",null,"1.05.04.04.02","PD5040402","CN5040402"]
["1","05","04","04","03","",null,"Pulse Split & Delay",null,"1.05.04.04.03","PD5040403","CN5040403"]
["1","05","05",{"$nulls":4},"Diagnostics Subsystem",null,"Summary"]
["1","05","05","01",null,null,null,"Reserved",null,"Summary"]
["1","05","05","01","01",null,null,"Reserved",null,"Summary"]
["1","05","05","02",null,null,null,"Modeling & Simulation",null,"Summary"]
["1","05","05","02","01","",null,"Wave Model",null,"1.05.05.02.01","PD5050201","CN5050201"]
["1","05","05","02","02","",null,"Monte Carlo Model",null,"1.05.05.02.02","PD5050202"]
["1","05","05","03",null,null,null,"Facility Diagnostics",null,"Summary"]
["1","05","05","03","01","",null,"Direct Imager",null,"1.05.05.03.01","PD5050301","CN5050301"]
["1","05","05","03","02","",null,"Indirect Imager",null,"1.05.05.03.02","PD5050302","CN5050302"]
["1","05","05","03","03",null,null,"Pulsed Ion Chamber",null,"Summary"]
["1","05","05","03","04",null,null,"Gas Mixing System",null,"Summary"]
["1","05","05","03","05","",null,"FEE Diagnostic Tanks",null,"1.05.05.03.05","PD5050305","CN5050305"]
["1","05","05","03","06","",null,"Ion Pumped Diagnostic Tanks",null,"1.05.05.03.06","PD5050306","CN5050306"]
["1","05","05","04",null,null,null,"Commissioning Diagnostics",null,"Summary"]
["1","05","05","04","01","",null,"Commission Diagnostic Tank",null,"1.05.05.04.01","PD5050401","CN5050401"]
["1","05","05","04","02","",null,"Total Energy Measurement",null,"1.05.05.04.02",null,"CN5050402"]
["1","05","05","04","03",null,null,"Reserved",null,"Summary"]
["1","05","05","04","04","",null,"Spectral Measurement",null,"1.05.05.04.04","PD5050404","CN5050404"]
["1","05","05","04","05","",null,"Spatial Coherence",null,"1.05.05.04.05","PD5050405","CN5050405"]
["1","05","05","04","06","",null,"Spatial Shape & Centroid Measurement",null,"1.05.05.04.06","PD5050406","CN5050406"]
["1","05","05","04","07","",null,"Divergence Measurement",null,"1.05.05.04.07",null,"CN5050407"]
["1","05","06",{"$nulls":4},"X-Ray Transport System Installation & Alignment",null,"Summary"]
["1","05","06","01","","",null,"Front End Enclosure Install",null,"1.05.06.01",null,"CN50601"]
["1","05","06","02","","",null,"Near Hall Install",null,"1.05.06.02",null,"CN50602"]
["1","05","06","03","","",null,"Tunnel Install",null,"1.05.06.03",null,"CN50603"]
["1","05","06","04","","",null,"Far Hall Install",null,"1.05.06.04",null,"CN50604"]
["1","06",{"$nulls":5},"X-RAY END STATION SYSTEMS",null,"Summary"]
["1","06","01",{"$nulls":4},"System Management & Integration",null,"Summary"]
["1","06","01","01","","",null,"Management",null,"1.06.01.01",9240575,"CN60101"]
["1","06","02",{"$nulls":4},"Controls Subsystem",null,"Summary"]
["1","06","02","01",null,null,null,"Cabling",null,"Summary"]
["1","06","02","01","01","",null,"Front End Enclosure Cable",null,"1.06.02.01.01",9240578,"CN6020101"]
["1","06","02","01","02","",null,"Near Hall Cable",null,"1.06.02.01.02",9240579,"CN6020102"]
["1","06","02","01","03","",null,"Tunnel Cable",null,"1.06.02.01.03",9240580,"CN6020103"]
["1","06","02","01","04","",null,"Far Hall Cable",null,"1.06.02.01.04",9240581,"CN6020104"]
["1","06","02","02","","",null,"Network",null,"1.06.02.02",9240582,"CN60202"]
["1","06","02","03","","",null,"PC Support",null,"1.06.02.03",9240583,"CN60203"]
["1","06","02","04","","",null,"Beamline Controls",null,"1.06.02.04",9240584,"CN60204"]
["1","06","02","05",null,null,null,"X-Ray PPS",null,"Summary"]
["1","06","02","05","01","",null,"FEE X-Ray PPS",null,"1.06.02.05.01",9240586,"CN6020501"]
["1","06","02","05","02","",null,"Near Hall X-Ray PPS",null,"1.06.02.05.02",9240587,"CN6020502"]
["1","06","02","05","03","",null,"Tunnel X-Ray PPS",null,"1.06.02.05.03",9240588,"CN6020503"]
["1","06","02","05","04","",null,"Far Hall X-Ray PPS",null,"1.06.02.05.04",9240589,"CN6020504"]
["1","06","02","06",null,null,null,"X-Ray MPS",null,"Summary"]
["1","06","02","06","01","",null,"FEE X-Ray MPS",null,"1.06.02.06.01",9240591,"CN6020601"]
["1","06","02","06","02","",null,"Near Hall X-Ray MPS",null,"1.06.02.06.02",9240592,"CN6020602"]
["1","06","02","06","03","",null,"Tunnel X-Ray MPS",null,"1.06.02.06.03",9240593,"CN6020603"]
["1","06","02","06","04","",null,"Far Hall X-Ray MPS",null,"1.06.02.06.04",9240594,"CN6020604"]
["1","06","02","07",null,null,null,"Laser PPS",null,"Summary"]
["1","06","02","07","01","",null,"Near Hall Laser PPS",null,"1.06.02.07.01",9240596,"CN6020701"]
["1","06","02","07","02","",null,"Far Hall Laser PPS",null,"1.06.02.07.02",9240597,"CN6020702"]
["1","06","02","08",null,null,null,"User Safeguards",null,"Summary"]
["1","06","02","08","01","",null,"Near Hall User Safeguards",null,"1.06.02.08.01",9240599,"CN6020801"]
["1","06","02","08","02","",null,"Far Hall User Safeguards",null,"1.06.02.08.02",9240600,"CN6020802"]
["1","06","03",{"$nulls":4},"Mechanical/Vacuum Subsystem",null,"Summary"]
["1","06","03","01","","",null,"Chamber Support Tables - Mech/Vac",null,"1.06.03.01",9240602,"CN60301"]
["1","06","03","02",null,null,null,"Vacuum Components - Mech/Vac",null,"Summary"]
["1","06","03","02","01","",null,"Valves - Vacuum",null,"1.06.03.02.01",9240604,"CN6030201"]
["1","06","03","02","02","",null,"Hardware - Vacuum",null,"1.06.03.02.02",9240605,"CN6030202"]
["1","06","03","02","03","",null,"Ion Pump - Vacuum",null,"1.06.03.02.03",9240606,"CN6030203"]
["1","06","03","02","04","",null,"Turbo Pump - Vacuum",null,"1.06.03.02.04",9240607,"CN6030204"]
["1","06","03","02","05","",null,"Gauges - Vacuum",null,"1.06.03.02.05",9240608,"CN6030205"]
["1","06","03","03",null,null,null,"Experimental Chambers",null,"Summary"]
["1","06","03","03","01","",null,"Near Hall Experimental Chamber",null,"1.06.03.03.01",9240610,"CN6030301"]
["1","06","03","03","02","",null,"Far Hall Experimental Chamber",null,"1.06.03.03.02",9240611,"CN6030302"]
["1","06","04",{"$nulls":4},"Laser Subsystem",null,"Summary"]
["1","06","04","01",null,null,null,"Oscillator Laser & Pump",null,"Summary"]
["1","06","04","01","01","",null,"Near Hall Oscillator Laser & Pump",null,"1.06.04.01.01",9240614,"CN6040101"]
["1","06","04","01","02","",null,"Far Hall Oscillator Laser & Pump",null,"1.06.04.01.02",9240615,"CN6040102"]
["1","06","04","02","","",null,"Laser Diagnostics",null,"1.06.04.02",9240616,"CN60402"]
["1","06","04","03","","",null,"Laser Supplies & Optical Transport",null,"1.06.04.03",9240617,"CN60403"]
["1","06","04","04","","",null,"Laser Timing",null,"1.06.04.04",9240618,"CN60404"]
["1","06","04","05",null,null,null,"Laser Amplifiers",null,"Summary"]
["1","06","04","05","01","",null,"Near Hall Laser Amplifier",null,"1.06.04.05.01",9240620,"CN6040501"]
["1","06","04","05","02","",null,"Far Hall Laser Amplifier",null,"1.06.04.05.02",9240621,"CN6040502"]
["1","06","05",{"$nulls":4},"X-Ray Detectors",null,"Summary"]
["1","06","05","01","","",null,"Beam Imaging",null,"1.06.05.01",9240623,"CN60501"]
["1","06","05","02","","",null,"2-D X-Ray Detector",null,"1.06.05.02",9240624,"CN60502"]
["1","06","05","03","","",null,"Beam Intensity",null,"1.06.05.03",9240625,"CN60503"]
["1","06","05","04","","",null,"Streak Camera",null,"1.06.05.04",9240626,"CN60504"]
["1","06","06",{"$nulls":4},"System Installation & Alignment",null,"Summary"]
["1","06","06","01","","",null,"Front End Install",null,"1.06.06.01",null,"CN60601"]
["1","06","06","02",null,null,null,"Near Hall Install",null,"Summary"]
["1","06","06","02","01","",null," Near Hall Install Controls",null,"1.06.06.02.01",null,"CN6060201"]
["1","06","06","02","02","",null,"Near Hall Install Mech/Vac",null,"1.06.06.02.02",null,"CN6060202"]
["1","06","06","02","03","",null," Near Hall Install Laser",null,"1.06.06.02.03",null,"CN6060203"]
["1","06","06","02","04","",null,"Near Hall Install Detectors",null,"1.06.06.02.04",null,"CN6060204"]
["1","06","06","02","05",null,null,"Near Hall Install Atomic Physics",null,"Summary"]
["1","06","06","03","","",null,"Tunnel Install",null,"1.06.06.03",null,"CN60603"]
["1","06","06","04",null,null,null,"Far Hall Install",null,"Summary"]
["1","06","06","04","01","",null,"Far Hall Install Controls",null,"1.06.06.04.01",null,"CN6060401"]
["1","06","06","04","02","",null,"Far Hall Install Mech/Vac",null,"1.06.06.04.02",null,"CN6060402"]
["1","06","06","04","03","",null,"Far Hall Install Laser",null,"1.06.06.04.03",null,"CN6060403"]
["1","06","06","04","04","",null,"Far Hall Install Detectors",null,"1.06.06.04.04",null,"CN6060404"]
["1","06","06","04","05",null,null,"Reserved",null,"Summary"]
["1","06","07",{"$nulls":4},"Reserved",null,"Summary"]
["1","06","07","01",null,null,null,"Reserved",null,"Summary"]
["1","06","07","02",null,null,null,"Reserved",null,"Summary"]
["1","06","07","03",null,null,null,"Reserved",null,"Summary"]
["1","06","07","04",null,null,null,"Reserved",null,"Summary"]
["1","07",{"$nulls":5},"Reserved",null,"Summary"]
["1","08",{"$nulls":5},"Reserved",null,"Summary"]
["1","09",{"$nulls":5},"CONVENTIONAL FACILITIES",null,"Summary"]
["1","09","01",{"$nulls":4},"System Management & Integration",null,"Summary"]
["1","09","01","01","","",null,"Management",null,"1.09.01.01",9240651,"CN90101"]
["1","09","01","02","","",null,"Cost Account Managers",null,"1.09.01.02",9240652,"CN90102"]
["1","09","01","03","","",null,"Construction Management",null,"1.09.01.03",null,"CN90103"]
["1","09","01","04",null,null,null,"Mechanical Design (MD)",null,"Summary"]
["1","09","01","04","01",null,null,"Mechanical Design Title 1 (Linac not included)",null,"Summary"]
["1","09","01","04","02","",null,"Mechanical Design T1 Linac Facilities",null,"1.09.01.04",9240655]
["1","09","01","04","03","",null,"Mechanical Design Title 2 (Linac not included)",null,"1.09.01.04",9240655]
["1","09","01","04","04","",null,"Mechanical Design T2 Linac Facilities",null,"1.09.01.04",9240655]
["1","09","01","04","05","",null,"Mechanical Design Title 3 Linac Facility",null,"1.09.01.04",9240655]
["1","09","01","04","06","",null,"Mechanical Design Title 3 (Linac not Included)",null,"1.09.01.04",9240655]
["1","09","01","05",null,null,null,"Site Engineering and Maintenance (SEM)",null,"Summary"]
["1","09","01","05","01","",null,"SEM Engineering Title 1(Linac Not Included)",null,"1.09.01.05",9240656]
["1","09","01","05","02","",null,"SEM Engineering Title 1 Linac Facility",null,"1.09.01.05",9240656]
["1","09","01","05","03",null,null,"SEM Engineering Title 2 (Linac Not Included)",null,"Summary"]
["1","09","01","05","04","",null,"SEM Design Linac Facility Title 2",null,"1.09.01.05",9240656]
["1","09","02",{"$nulls":4},"Title 1 & Title 2 Conventional Facilities",null,"Summary"]
["1","09","02","01",null,null,null,"Reserved",null,"Summary"]
["1","09","02","02",null,null,null,"A & E Services (S20, MMF, MMC not Incl)",null,"Summary"]
["1","09","02","02","01","",null,"Title 1 Design",null,"1.09.02.02",9240658]
["1","09","02","02","02","",null,"Title 2 Design",null,"1.09.02.02",9240658]
["1","09","02","03",null,null,null,"A & E Services - (S20, MMF,MCC)",null,"Summary"]
["1","09","02","03","01","",null,"Title 1 Design (Sector 20)",null,"1.09.02.03",9240659]
["1","09","02","03","02","",null,"Title 2 Design (Sector 20)",null,"1.09.02.03",9240659]
["1","09","02","03","03","",null,"Title 1 Design (MMF)",null,"1.09.02.03",9240659]
["1","09","02","03","04","",null,"Title 2 Design (MMF)",null,"1.09.02.03",9240659]
["1","09","02","03","05","",null,"Title 1 Design (MCC)",null,"1.09.02.03",9240659]
["1","09","02","03","06","",null,"Title 2 Design (MCC)",null,"1.09.02.03",9240659]
["1","09","03",{"$nulls":4},"Construction-T3 Conventional Facilities",null,"Summary"]
["1","09","03","01",null,null,null,"Sector 20 Injector Facilities",null,"Summary"]
["1","09","03","01","01","",null,"Site Preparation",null,"1.09.03.01",null,"CN90301"]
[" ","09","03","01","02",null,null,"Structural",null,"Summary"]
["1","09","03","01","03",null,null,"Electrical",null,"Summary"]
["1","09","03","01","04","",null,"Utilities",null,"1.09.03.01",null,"CN90301"]
["1","09","03","01","05",null,null,"HVAC",null,"Summary"]
["1","09","03","01","06",null,null,"Special System - Fire Protection",null,"Summary"]
["1","09","03","01","07",null,null,"Interior",null,"Summary"]
["1","09","03","01","10","",null,"Project Close Out Sector 20 Injector Facility",null,"1.09.03.01",null,"CN90301"]
["1","09","03","02","","",null,"Magnetic Measurement Facility",null,"1.09.03.02",null,9240662]
["1","09","03","02","01","",null,"Site Preparation",null,"1.09.03.02",null,"CN90302"]
["1","09","03","02","02","",null,"Structural",null,"1.09.03.02",null,"CN90302"]
["1","09","03","02","03","",null,"Electrical",null,"1.09.03.02",null,"CN90302"]
["1","09","03","02","04",null,null,"Utilities",null,"Summary"]
["1","09","03","02","05",null,null,"HVAC",null,"Summary"]
["1","09","03","02","06",null,null,"Special System - Fire Protection",null,"Summary"]
["1","09","03","02","07",null,null,"Interior",null,"Summary"]
["1","09","03","02","10","",null,"Project Close Out Magnetic Measurement Facility",null,"1.09.03.02",null,"CN90302"]
["1","09","03","03",null,null,null,"Main Control Center Facilities Upgrade",null,"Summary"]
["1","09","03","03","01","",null,"Site Preparation",null,"1.09.03.03",null,"CN90303"]
["1","09","03","03","02",null,null,"Structural",null,"Summary"]
["1","09","03","03","03",null,null,"Electrical",null,"Summary"]
["1","09","03","03","04",null,null,"Utilities",null,"Summary"]
["1","09","03","03","05",null,null,"HVAC",null,"Summary"]
["1","09","03","03","06",null,null,"Special System - Fire Protection",null,"Summary"]
["1","09","03","03","07",null,null,"Interior",null,"Summary"]
["1","09","03","03","10","",null,"Project Close Out Main Control Center Facilitiy",null,"1.09.03.03",null,"CN90303"]
["1","09","03","04",null,null,null,"Linac Facility",null,"Summary"]
["1","09","03","04","03","",null,"Electrical",null,"1.09.03.04",null,"CN90304"]
["1","09","03","04","04","",null,"Utilities",null,"1.09.03.04",null,"CN90304"]
["1","09","03","04","06",null,null,"Special System - Fire Protection",null,"Summary"]
["1","09","03","04","10","",null,"Project Close Out Linac Facility",null,"1.09.03.04",null,"CN90304"]
["1","09","03","05","","",null,"Research Yard/B102,B211,B113 & Storage Trailers",null,"1.09.03.05",null,"CN90305"]
["1","09","03","05","01",null,null,"Site Preparation",null,"Summary"]
["1","09","03","05","01","01",null,"Site Preparation SEM",null,"1.09.03.05",null,"CN90305"]
["1","09","03","05","01","02",null,"Site Preparation G/C",null,"Summary"]
["1","09","03","05","02",null,null,"Structural",null,"Summary"]
["1","09","03","05","02","01",null,"Structural SEM",null,"1.09.03.05",null,"CN90305"]
["1","09","03","05","02","02",null,"Structural G/C",null,"Summary"]
["1","09","03","05","03",null,null,"Electrical",null,"Summary"]
["1","09","03","05","03","01",null,"Electrical SEM",null,"1.09.03.05",null,"CN90305"]
["1","09","03","05","03","02",null,"Electrical G/C",null,"Summary"]
["1","09","03","05","04",null,null,"Utilities",null,"Summary"]
["1","09","03","05","04","01",null,"Utilities SEM",null,"1.09.03.05",null,"CN90305"]
["1","09","03","05","04","02",null,"Utilities G/C",null,"Summary"]
["1","09","03","05","05",null,null,"HVAC",null,"Summary"]
["1","09","03","05","05","01",null,"HVAC SEM",null,"1.09.03.05",null,"CN90305"]
["1","09","03","05","05","02",null,"HVAC G/C",null,"Summary"]
["1","09","03","05","06",null,null,"Special System - Fire Protection",null,"Summary"]
["1","09","03","05","06","01",null,"Special System - Fire Protection SEM",null,"1.09.03.05",null,"CN90305"]
["1","09","03","05","06","02",null,"Special System - Fire Protection",null,"Summary"]
["1","09","03","05","07",null,null,"Interior",null,"Summary"]
["1","09","03","05","07","01",null,"Interior SEM",null,"Summary"]
["1","09","03","05","07","02",null,"Interior G/C",null,"Summary"]
["1","09","03","05","10","",null,"Project Close Out Reasearch Yard",null,"1.09.03.05",null,"CN90305"]
["1","09","03","06","","",null,"Access Road & Beam Transport Hall",null,"1.09.03.06",null,"CN90306"]
["1","09","03","06","01","",null,"Site Preparation",null,"1.09.03.06",null,"CN90306"]
["1","09","03","06","02",null,null,"Structural",null,"Summary"]
["1","09","03","06","03",null,null,"Electrical",null,"Summary"]
["1","09","03","06","04",null,null,"Utilities",null,"Summary"]
["1","09","03","06","05",null,null,"HVAC",null,"Summary"]
["1","09","03","06","06",null,null,"Special System- Fire Protection",null,"Summary"]
["1","09","03","06","07",null,null,"Interior",null,"Summary"]
["1","09","03","06","09",null,null,"Reserved",null,"Summary"]
["1","09","03","06","10","",null,"Project Close Out  Beam Trans Hall",null,"1.09.03.06",null,"CN90306"]
["1","09","03","07","","",null,"Undulator Hall",null,"1.09.03.07",null,"CN90307"]
["1","09","03","07","01",null,null,"Site Preparation",null,"Summary"]
["1","09","03","07","02",null,null,"Structural",null,"Summary"]
["1","09","03","07","03",null,null,"Electrical",null,"Summary"]
["1","09","03","07","04",null,null,"Utilities",null,"Summary"]
["1","09","03","07","05",null,null,"HVAC",null,"Summary"]
["1","09","03","07","06",null,null,"Special System - Fire Protection",null,"Summary"]
["1","09","03","07","07",null,null,"Interior",null,"Summary"]
["1","09","03","07","09",null,null,"Tunneling",null,"Summary"]
["1","09","03","07","10","",null,"Project Close Out Undulator Hall",null,"1.09.03.07",null,"CN90307"]
["1","09","03","08","","",null,"Front End Enclosure",null,"1.09.03.08",null,"CN90308"]
["1","09","03","08","01",null,null,"Site Preparation",null,"Summary"]
["1","09","03","08","02",null,null,"Structural",null,"Summary"]
["1","09","03","08","03",null,null,"Electrical",null,"Summary"]
["1","09","03","08","04",null,null,"Utilities",null,"Summary"]
["1","09","03","08","05",null,null,"HVAC",null,"Summary"]
["1","09","03","08","06",null,null,"Special System - Fire Protection",null,"Summary"]
["1","09","03","08","07",null,null,"Interior",null,"Summary"]
["1","09","03","08","09",null,null,"Tunneling",null,"Summary"]
["1","09","03","08","10","",null,"Project Close Out Front End Enclosure",null,"1.09.03.08",null,"CN90308"]
["1","09","03","09","","",null,"Beam Dump",null,"1.09.03.09",null,"CN90309"]
["1","09","03","09","01",null,null,"Site Preparation",null,"Summary"]
["1","09","03","09","02",null,null,"Structural",null,"Summary"]
["1","09","03","09","03","",null,"Electrical",null,"1.09.03.09",null,"CN90309"]
["1","09","03","09","04",null,null,"Utilities",null,"Summary"]
["1","09","03","09","05",null,null,"reserved",null,"Summary"]
["1","09","03","09","06",null,null,"Special System (Fire Protection) Beam Dump",null,"Summary"]
["1","09","03","09","09",null,null,"Tunneling",null,"Summary"]
["1","09","03","09","10","",null,"Project Close Out Beam Dump",null,"1.09.03.09",null,"CN90309"]
["1","09","03","10","","",null,"Near Experimental Hall",null,"1.09.03.10",null,"CN90310"]
["1","09","03","10","01",null,null,"Site Preparation",null,"Summary"]
["1","09","03","10","02",null,null,"Structural",null,"Summary"]
["1","09","03","10","03",null,null,"Electrical",null,"Summary"]
["1","09","03","10","04",null,null,"Utilities",null,"Summary"]
["1","09","03","10","05",null,null,"HVAC",null,"Summary"]
["1","09","03","10","06",null,null,"Special System - Fire Protection",null,"Summary"]
["1","09","03","10","07",null,null,"Interior",null,"Summary"]
["1","09","03","10","09",null,null,"Reserved",null,"Summary"]
["1","09","03","10","10","",null,"Project Close Out Near Experimental Hall",null,"1.09.03.10",null,"CN90310"]
["1","09","03","11","","",null,"X-Ray Transport & Diagnostic Hall",null,"1.09.03.11",null,"CN90311"]
["1","09","03","11","01",null,null,"Site Preparation",null,"Summary"]
["1","09","03","11","02",null,null,"Structural",null,"Summary"]
["1","09","03","11","03",null,null,"Electrical",null,"Summary"]
["1","09","03","11","04",null,null,"Utilities",null,"Summary"]
["1","09","03","11","05",null,null,"HVAC",null,"Summary"]
["1","09","03","11","06",null,null,"Special System - Fire Protection",null,"Summary"]
["1","09","03","11","07",null,null,"Interiors",null,"Summary"]
["1","09","03","11","09","",null,"Tunneling",null,"1.09.03.11",null,"CN90311"]
["1","09","03","11","10","",null,"Project Close Out X-Ray Transport & Diagonistic",null,"1.09.03.11",null,"CN90311"]
["1","09","03","12","","",null,"Far Experimental Hall",null,"1.09.03.12",null,"CN90312"]
["1","09","03","12","01",null,null,"Reserved",null,"Summary"]
["1","09","03","12","02",null,null,"Structural",null,"Summary"]
["1","09","03","12","03",null,null,"Electrical",null,"Summary"]
["1","09","03","12","04",null,null,"Utilities",null,"Summary"]
["1","09","03","12","05",null,null,"HVAC",null,"Summary"]
["1","09","03","12","06",null,null,"Special System - Fire Protection",null,"Summary"]
["1","09","03","12","07",null,null,"Interiors",null,"Summary"]
["1","09","03","12","09",null,null,"Tunneling",null,"Summary"]
["1","09","03","12","10","",null,"Project Close Out Far Experimental Hall",null,"1.09.03.12",null,"CN90312"]
["1","09","03","13","","",null,"Central Lab Office Bldg (CLOB)",null,"1.09.03.13",null,"CN90313"]
["1","09","03","13","01",null,null,"Site Preparation",null,"Summary"]
["1","09","03","13","02",null,null,"Structural",null,"Summary"]
["1","09","03","13","03",null,null,"Electrical",null,"Summary"]
["1","09","03","13","04",null,null,"Utilities",null,"Summary"]
["1","09","03","13","05",null,null,"HVAC",null,"Summary"]
["1","09","03","13","06",null,null,"Special System - Fire Protection",null,"Summary"]
["1","09","03","13","07",null,null,"Interior",null,"Summary"]
["1","09","03","13","10","",null,"Project Close Out CLOB",null,"1.09.03.13",null,"CN90313"]
["2",{"$nulls":6},"LCLS PROJECT - R&D, SPARES, COMMISSIONING",null,"Summary"]
["2","01",{"$nulls":5},"LCLS PROJECT MGMT, PLANNING & ADMN (OPC)",null,"Summary"]
["2","01","01",{"$nulls":4},"Physics Support (OPC)",null,"Summary"]
["2","01","01","01","","",null,"SAC-MAC Physics",null,"2.01.01.01",null,null,9681321,null,"CM10101"]
["2","01","01","02","","",null,"Injector Physics",null,"2.01.01.02",null,null,9681322,null,"CM10102"]
["2","01","01","03","","",null,"Linac Physics",null,"2.01.01.03",null,null,9681323,null,"CM10103"]
["2","01","01","04","","",null,"Undulator Physics",null,"2.01.01.04",null,null,9681324,null,"CM10104"]
["2","01","01","05","","",null,"X-Ray Transport Physics",null,"2.01.01.05",null,null,9681325,null,"CM10105"]
["2","01","01","06","","",null,"X-Ray Endstation Physics",null,"2.01.01.06",null,null,9681326,null,"CM10106"]
["2","01","01","07","","",null,"Conventional Facilities Physics",null,"2.01.01.07",null,null,9681327,null,"CM10107"]
["2","01","01","08","","",null,"Consulting Physics (Collaboration)",null,"2.01.01.08",null,null,9681328,null,"CM10108"]
["2","01","01","09","","",null,"Consulting Physics (SLAC)",null,"2.01.01.09",null,null,9681329,null,"CM10109"]
["2","01","01","10","","",null,"Global Controls Physics Liaison",null,"2.01.01.10",null,null,9681330,null,"CM10110"]
["2","01","01","11","","",null,"Global Controls OPC",null,"2.01.01.11",{"$nulls":4},"CM10111"]
["2","01","02","","","",null,"R&D Studies & Prototyping",null,"2.01.02",null,null,9681010,null,"CM102"]
["2","01","03","","","",null,"Project Mgmnt, Planning and Admn - M&S (OPC)",null,"2.01.03",null,null,9681011,null,"CM103"]
["2","01","03","01",null,null,null,"Reserved",null,"Summary"]
["2","01","03","02",null,null,null,"Reserved",null,"Summary"]
["2","01","03","03",null,null,null,"Reserved",null,"Summary"]
["2","01","03","04",null,null,null,"Reserved",null,"Summary"]
["2","01","03","05",null,null,null,"Reserved",null,"Summary"]
["2","01","03","06",null,null,null,"Reserved",null,"Summary"]
["2","01","03","07",null,null,null,"Reserved",null,"Summary"]
["2","01","03","08",null,null,null,"Reserved",null,"Summary"]
["2","01","03","09",null,null,null,"Reserved",null,"Summary"]
["2","01","03","10",null,null,null,"Reserved",null,"Summary"]
["2","01","03","11",null,null,null,"Reserved",null,"Summary"]
["2","02",{"$nulls":5},"INJECTOR SYSTEM (OPC)",null,"Summary"]
["2","02","01",{"$nulls":4},"Reserved",null,"Summary"]
["2","02","01","01",null,null,null,"Reserved",null,"Summary"]
["2","02","01","02",null,null,null,"Reserved",null,"Summary"]
["2","02","01","03",null,null,null,"Reserved",null,"Summary"]
["2","02","02",{"$nulls":4},"Injector Controls Subsystem",null,"Summary"]
["2","02","02","01","","",null,"EPICS VXI Control Modules",null,"2.02.02.01",null,null,9681017,"SP20201","CM20201"]
["2","02","02","02","","",null,"LLRF Controls",null,"2.02.02.02",null,null,9681018]
["2","02","02","03",null,null,null,"E-Beam Diagnostics Controls",null,"Summary"]
["2","02","02","03","01",null,null,"Reserved",null,"Summary"]
["2","02","02","03","02","",null,"Controls - Toroids",null,"2.02.02.03.02",{"$nulls":4},"CM2020302"]
["2","02","02","03","03","",null,"Controls - Faraday Cup",null,"2.02.02.03.03",null,null,9681022]
["2","02","02","03","04","",null,"Controls - Tune-Up Dump",null,"2.02.02.03.04",{"$nulls":4},"CM2020304"]
["2","02","02","03","05","",null,"Controls - Profile Monitors",null,"2.02.02.03.05",null,null,9681024]
["2","02","02","03","06","",null,"Control - EO Diagnostic",null,"2.02.02.03.06",{"$nulls":4},"CM2020306"]
["2","02","02","03","07","",null,"Controls - BPM Processor Module",null,"2.02.02.03.07",null,null,9681026]
["2","02","02","04",null,null,null,"Reserved",null,"Summary"]
["2","02","02","05",null,null,null,"Reserved",null,"Summary"]
["2","02","02","06",null,null,null,"Reserved",null,"Summary"]
["2","02","02","07",null,null,null,"Reserved",null,"Summary"]
["2","02","02","08",null,null,null,"Reserved",null,"Summary"]
["2","02","02","09",null,null,null,"Reserved",null,"Summary"]
["2","02","03",{"$nulls":4},"Injector Lasers",null,"Summary"]
["2","02","03","01","","",null,"Drive Laser Prototyping",null,"2.02.03.01",null,null,9681034]
["2","02","03","02","","",null,"Drive Laser Oscillator",null,"2.02.03.02",null,null,null,"SP20302"]
["2","02","03","03",null,null,null,"Reserved",null,"Summary"]
["2","02","03","04",null,null,null,"Reserved",null,"Summary"]
["2","02","03","05",null,null,null,"Reserved",null,"Summary"]
["2","02","03","06",null,null,null,"Reserved",null,"Summary"]
["2","02","03","07",null,null,null,"Reserved",null,"Summary"]
["2","02","03","08",null,null,null,"Reserved",null,"Summary"]
["2","02","03","09",null,null,null,"Reserved",null,"Summary"]
["2","02","03","10",null,null,null,"Reserved",null,"Summary"]
["2","02","03","11",null,null,null,"Reserved",null,"Summary"]
["2","02","03","12",null,null,null,"Reserved",null,"Summary"]
["2","02","03","13",null,null,null,"Reserved",null,"Summary"]
["2","02","03","14",null,null,null,"Reserved",null,"Summary"]
["2","02","03","15",null,null,null,"Reserved",null,"Summary"]
["2","02","03","16",null,null,null,"Reserved",null,"Summary"]
["2","02","03","17",null,null,null,"Reserved",null,"Summary"]
["2","02","03","18",null,null,null,"Reserved",null,"Summary"]
["2","02","03","19",null,null,null,"Reserved",null,"Summary"]
["2","02","03","20",null,null,null,"Reserved",null,"Summary"]
["2","02","03","21",null,null,null,"Reserved",null,"Summary"]
["2","02","03","22",null,null,null,"Reserved",null,"Summary"]
["2","02","03","23",null,null,null,"Reserved",null,"Summary"]
["2","02","03","24",null,null,null,"Reserved",null,"Summary"]
["2","02","03","25",null,null,null,"Reserved",null,"Summary"]
["2","02","03","26",null,null,null,"Reserved",null,"Summary"]
["2","02","03","27",null,null,null,"Reserved",null,"Summary"]
["2","02","03","28",null,null,null,"Reserved",null,"Summary"]
["2","02","03","29",null,null,null,"Reserved",null,"Summary"]
["2","02","03","30",null,null,null,"Reserved",null,"Summary"]
["2","02","04",{"$nulls":4},"RF Gun & Load Lock",null,"Summary"]
["2","02","04","01","","",null,"RF Gun",null,"2.02.04.01",null,null,9681065]
["2","02","04","02","","",null,"RF Gun Supports",null,"2.02.04.02",null,null,null,"SP20402"]
["2","02","04","03","","",null,"Gun Load Lock",null,"2.02.04.03",null,null,null,"SP20403"]
["2","02","04","04",null,null,null,"Reserved",null,"Summary"]
["2","02","04","05",null,null,null,"Reserved",null,"Summary"]
["2","02","04","06",null,null,null,"Reserved",null,"Summary"]
["2","02","04","07",null,null,null,"Reserved",null,"Summary"]
["2","02","04","08",null,null,null,"Reserved",null,"Summary"]
["2","02","05",{"$nulls":4},"Gun to Linac Section (GTL)",null,"Summary"]
["2","02","05","01",null,null,null,"Reserved",null,"Summary"]
["2","02","05","02","","",null,"GTL Faraday Cup/YAG1",null,"2.02.05.02",null,null,null,"SP20502"]
["2","02","05","03",null,null,null,"Reserved",null,"Summary"]
["2","02","05","04",null,null,null,"Reserved",null,"Summary"]
["2","02","05","05",null,null,null,"Reserved",null,"Summary"]
["2","02","05","06",null,null,null,"Reserved",null,"Summary"]
["2","02","05","07",null,null,null,"Reserved",null,"Summary"]
["2","02","05","08",null,null,null,"Reserved",null,"Summary"]
["2","02","05","09",null,null,null,"Reserved",null,"Summary"]
["2","02","05","10",null,null,null,"Reserved",null,"Summary"]
["2","02","05","11",null,null,null,"Reserved",null,"Summary"]
["2","02","06",{"$nulls":4},"Injector Linac Structures",null,"Summary"]
["2","02","06","01",null,null,null,"Reserved",null,"Summary"]
["2","02","06","02","","",null,"L0-2 Structure Assembly",null,"2.02.06.02",null,null,null,"SP20602"]
["2","02","06","03",null,null,null,"Reserved",null,"Summary"]
["2","02","06","04",null,null,null,"Reserved",null,"Summary"]
["2","02","07",{"$nulls":4},"L0-1 to L0-2 Section (L0-1TL0-2)",null,"Summary"]
["2","02","07","01",null,null,null,"Reserved",null,"Summary"]
["2","02","07","02","","",null,"L0-1TL0-2 BPMs ( )",null,"2.02.07.02",null,null,null,"SP20702"]
["2","02","07","03",null,null,null,"Reserved",null,"Summary"]
["2","02","07","04",null,null,null,"Reserved",null,"Summary"]
["2","02","07","05",null,null,null,"Reserved",null,"Summary"]
["2","02","07","06",null,null,null,"Reserved",null,"Summary"]
["2","02","07","07",null,null,null,"Reserved",null,"Summary"]
["2","02","08",{"$nulls":4},"Linac to DL1 (LTDL1)",null,"Summary"]
["2","02","08","01",null,null,null,"Reserved",null,"Summary"]
["2","02","08","02","","",null,"LTDL1 BPMs ( )",null,"2.02.08.02",null,null,null,"SP20802"]
["2","02","08","03",null,null,null,"Reserved",null,"Summary"]
["2","02","08","04",null,null,null,"Reserved",null,"Summary"]
["2","02","08","05",null,null,null,"Reserved",null,"Summary"]
["2","02","08","06",null,null,null,"Reserved",null,"Summary"]
["2","02","08","07",null,null,null,"Reserved",null,"Summary"]
["2","02","08","08",null,null,null,"Reserved",null,"Summary"]
["2","02","08","09",null,null,null,"Reserved",null,"Summary"]
["2","02","08","10",null,null,null,"Reserved",null,"Summary"]
["2","02","09",{"$nulls":4},"Dog Leg 1 Bend (DL1)",null,"Summary"]
["2","02","09","01",null,null,null,"Reserved",null,"Summary"]
["2","02","09","02","","",null,"DL1 QB Quadrupole",null,"2.02.09.02",null,null,null,"SP20902"]
["2","02","09","03",null,null,null,"Reserved",null,"Summary"]
["2","02","09","04",null,null,null,"Reserved",null,"Summary"]
["2","02","09","05",null,null,null,"Reserved",null,"Summary"]
["2","02","09","06",null,null,null,"Reserved",null,"Summary"]
["2","02","10",{"$nulls":4},"DL1 to Linac (DL1TL)",null,"Summary"]
["2","02","10","01",null,null,null,"Reserved",null,"Summary"]
["2","02","10","02","","",null,"DL1TL Steering Coils ( X-Y Assys)",null,"2.02.10.02",null,null,null,"SP21002"]
["2","02","10","03",null,null,null,"Reserved",null,"Summary"]
["2","02","10","04",null,null,null,"Reserved",null,"Summary"]
["2","02","10","05",null,null,null,"Reserved",null,"Summary"]
["2","02","10","06",null,null,null,"Reserved",null,"Summary"]
["2","02","10","07",null,null,null,"Reserved",null,"Summary"]
["2","02","11",{"$nulls":4},"Straight Ahead Beamline (SAB)",null,"Summary"]
["2","02","11","01",null,null,null,"Reserved",null,"Summary"]
["2","02","11","02","","",null,"SAB Quadrupoles ( )",null,"2.02.11.02",null,null,null,"SP21102"]
["2","02","11","03",null,null,null,"Reserved",null,"Summary"]
["2","02","11","04",null,null,null,"Reserved",null,"Summary"]
["2","02","11","05",null,null,null,"Reserved",null,"Summary"]
["2","02","11","06",null,null,null,"Reserved",null,"Summary"]
["2","02","11","07",null,null,null,"Reserved",null,"Summary"]
["2","02","11","08",null,null,null,"Reserved",null,"Summary"]
["2","02","11","09",null,null,null,"Reserved",null,"Summary"]
["2","02","12",{"$nulls":4},"Injector RF Waveguide Subsystem",null,"Summary"]
["2","02","12","01",null,null,null,"Reserved",null,"Summary"]
["2","02","12","02","","",null,"RF Waveguide Supports",null,"2.02.12.02",null,null,null,"SP21202"]
["2","02","13",{"$nulls":4},"Injector RF Subsystem",null,"Summary"]
["2","02","13","01",null,null,null,"Reserved",null,"Summary"]
["2","02","13","01","01",null,null,"Reserved",null,"Summary"]
["2","02","13","02",null,null,null,"Reserved",null,"Summary"]
["2","02","14",{"$nulls":4},"Cathode Processing (CP) Station",null,"Summary"]
["2","02","14","01",null,null,null,"Reserved",null,"Summary"]
["2","02","14","02","","",null,"CP Load Lock",null,"2.02.14.02",null,null,null,"SP21302"]
["2","02","14","03",null,null,null,"Reserved",null,"Summary"]
["2","02","14","04",null,null,null,"Reserved",null,"Summary"]
["2","02","14","05",null,null,null,"Reserved",null,"Summary"]
["2","02","15",{"$nulls":4},"Injector Laser Heater Subsystem",null,"Summary"]
["2","02","15","01",null,null,null,"Reserved",null,"Summary"]
["2","02","15","02","","",null,"Beam Conditioning Optics (Laser Bay)",null,"2.02.15.02",null,null,null,"SP21502"]
["2","02","15","03",null,null,null,"Reserved",null,"Summary"]
["2","02","15","04",null,null,null,"Reserved",null,"Summary"]
["2","02","15","05",null,null,null,"Reserved",null,"Summary"]
["2","02","15","06",null,null,null,"Reserved",null,"Summary"]
["2","02","15","07",null,null,null,"Reserved",null,"Summary"]
["2","02","15","08",null,null,null,"Reserved",null,"Summary"]
["2","02","16",{"$nulls":4},"Injector Power Conversion Subsystem",null,"Summary"]
["2","02","16","01","","",null,"Personnel Protection System (PPS) R&D",null,"2.02.16.01",null,null,9681155]
["2","02","16","02",null,null,null,"Reserved",null,"Summary"]
["2","02","16","03",null,null,null,"Reserved",null,"Summary"]
["2","02","16","04","","",null,"Power Conv (beamline pwr supp) Spares",null,"2.02.16.04",null,null,null,"SP21604"]
["2","02","17",{"$nulls":4},"Injector System Commissioning",null,"Summary"]
["2","02","17","01",null,null,null,"Reserved",null,"Summary"]
["2","02","17","02","","",null,"Drive Laser Commissioning",null,"2.02.17.02",{"$nulls":4},"CM21702"]
["2","02","17","03","","",null,"RF Conditioning",null,"2.02.17.03",{"$nulls":4},"CM21703"]
["2","02","17","04","","",null,"RF Gun Operation with Beam",null,"2.02.17.04",{"$nulls":4},"CM21704"]
["2","02","17","05","","",null,"L0-1&L0-2 Commissioning",null,"2.02.17.05",{"$nulls":4},"CM21705"]
["2","02","17","06","","",null,"L0&SAB Commissioning",null,"2.02.17.06",{"$nulls":4},"CM21706"]
["2","02","17","07","","",null,"DL1 Commissioning",null,"2.02.17.07",{"$nulls":4},"CM21707"]
["2","02","17","08","","",null,"Injector Optimization",null,"2.02.17.08",{"$nulls":4},"CM21708"]
["2","03",{"$nulls":5},"LINAC SYSTEM (OPC)",null,"Summary"]
["2","03","01",{"$nulls":4},"Reserved",null,"Summary"]
["2","03","01","01",null,null,null,"Reserved",null,"Summary"]
["2","03","01","02",null,null,null,"Reserved",null,"Summary"]
["2","03","01","03",null,null,null,"Reserved",null,"Summary"]
["2","03","01","04",null,null,null,"Reserved",null,"Summary"]
["2","03","02",{"$nulls":4},"Linac Controls & Power Conversion Subsystem",null,"Summary"]
["2","03","02","01",null,null,null,"Reserved",null,"Summary"]
["2","03","02","02",null,null,null,"Reserved",null,"Summary"]
["2","03","02","03",null,null,null,"Reserved",null,"Summary"]
["2","03","02","04",null,null,null,"Power Conversion",null,"Summary"]
["2","03","02","04","01","",null,"Spare Power Supply (Dipole Type)",null,"2.03.02.04.01",null,null,null,"SP3020401"]
["2","03","02","04","02","",null,"Spare Power Supply (Quad Type)",null,"2.03.02.04.02",null,null,null,"SP3020402"]
["2","03","02","04","03","",null,"Spare Power Supply (Trim Type)",null,"2.03.02.04.03",null,null,null,"SP3020403"]
["2","03","02","04","04",null,null,"Reserved",null,"Summary"]
["2","03","02","05",null,null,null,"Reserved",null,"Summary"]
["2","03","02","06",null,null,null,"Reserved",null,"Summary"]
["2","03","02","07",null,null,null,"Reserved",null,"Summary"]
["2","03","02","08",null,null,null,"Reserved",null,"Summary"]
["2","03","02","09",null,null,null,"Reserved",null,"Summary"]
["2","03","02","10",null,null,null,"Reserved",null,"Summary"]
["2","03","03",{"$nulls":4},"Linac Magnets & Supports",null,"Summary"]
["2","03","03","01","","",null,"Bend Magnet (BX1_BC1)",null,"2.03.03.01",null,null,null,"SP30301"]
["2","03","03","02","","",null,"Bend Magnet (BX3_LTU)",null,"2.03.03.02",null,null,null,"SP30302"]
["2","03","03","03","","",null,"Bend Magnet (BX2_BC2)",null,"2.03.03.03",null,null,null,"SP30303"]
["2","03","03","04","","",null,"Bend Magnet (BY_LTU)",null,"2.03.03.04",null,null,null,"SP30304"]
["2","03","03","05","","",null,"Quad Magnet (Quad_LTU)",null,"2.03.03.05",null,null,null,"SP30305"]
["2","03","03","06",null,null,null,"Resered",null,"Summary"]
["2","03","03","07",null,null,null,"Resered",null,"Summary"]
["2","03","03","08",null,null,null,"Resered",null,"Summary"]
["2","03","03","09","","",null,"Bend Magnet (BYD_LTU)",null,"2.03.03.09",null,null,null,"SP30309"]
["2","03","03","10",null,null,null,"Reserved",null,"Summary"]
["2","03","03","11","","",null,"Bend Magnet (BYPM_LTU)",null,"2.03.03.11",null,null,null,"SP30311"]
["2","03","03","12","","",null,"Bend Magnet (BYKIK_LTU)",null,"2.03.03.12",null,null,null,"SP30312"]
["2","03","03","13","","",null,"Bend Magnet (BYW_LTU)",null,"2.03.03.13",null,null,null,"SP30313"]
["2","03","04",{"$nulls":4},"Linac Vacuum Subsystem",null,"Summary"]
["2","03","04","01","","",null,"Linac Vacuum Subsystem Operations Equip",null,"2.03.04.01",{"$nulls":4},"CM30401"]
["2","03","04","02","","",null,"Linac Beamline Vacuum System",null,"2.03.04.02",null,null,null,"SP30402"]
["2","03","04","03","","",null,"BC1 Vacuum System",null,"2.03.04.03",null,null,null,"SP30403"]
["2","03","04","04","","",null,"BC2 Vacuum System",null,"2.03.04.04",null,null,null,"SP30404"]
["2","03","04","05","","",null,"Linac to Undulator (LTU) Vacuum System",null,"2.03.04.05",null,null,null,"SP30405"]
["2","03","04","06","","",null,"Dumpline Vacuum System",null,"2.03.04.06",null,null,null,"SP30406"]
["2","03","05",{"$nulls":4},"Linac Electron Diagnostics",null,"Summary"]
["2","03","05","01","","",null,"Wire Scanners",null,"2.03.05.01",null,null,null,"SP30501"]
["2","03","05","02","","",null,"Beam Position Monitors",null,"2.03.05.02",null,null,null,"SP30502"]
["2","03","05","03","","",null,"Toroids Beam Charge",null,"2.03.05.03",null,null,null,"SP30503"]
["2","03","05","04","","",null,"Stoppers Tune Up Dump",null,"2.03.05.04",null,null,null,"SP30504"]
["2","03","05","05","","",null,"Profile Monitors",null,"2.03.05.05",null,null,null,"SP30505"]
["2","03","05","06",null,null,null,"Reserved",null,"Summary"]
["2","03","05","07","","",null,"Bunch Length Monitors",null,"2.03.05.07",null,null,null,"SP30507"]
["2","03","05","08","","",null,"Beam Loss Monitors",null,"2.03.05.08",null,null,null,"SP30508"]
["2","03","05","09",null,null,null,"Reserved",null,"Summary"]
["2","03","05","10",null,null,null,"Reserved",null,"Summary"]
["2","03","05","11","","",null,"Protection Collimators",null,"2.03.05.11",null,null,null,"SP30511"]
["2","03","05","12","","",null,"Movable Collimators",null,"2.03.05.12",null,null,null,"SP30512"]
["2","03","05","13","","",null,"Safety Dump",null,"2.03.05.13",null,null,null,"SP30513"]
["2","03","06",{"$nulls":4},"Linac RF Subsystem",null,"Summary"]
["2","03","06","01",null,null,null,"Reserved",null,"Summary"]
["2","03","06","02",null,null,null,"Reserved",null,"Summary"]
["2","03","06","03",null,null,null,"Reserved",null,"Summary"]
["2","03","06","04",null,null,null,"Reserved",null,"Summary"]
["2","03","06","05","","",null,"X-Band High Power System",null,"2.03.06.05",null,null,null,"SP30605"]
["2","03","06","06",null,null,null,"Reserved",null,"Summary"]
["2","03","06","07",null,null,null,"RF Distribution System",null,"Summary"]
["2","03","06","07","01","",null,"Modulator",null,"2.03.06.07.01",null,null,null,"SP3060701"]
["2","03","06","07","02","",null,"Solid State Sub Booster",null,"2.03.06.07.02",null,null,null,"SP3060702"]
["2","03","06","07","05","",null,"Bunch Length Electronics",null,"2.03.06.07.07",null,null,null,"SP3060707"]
["2","03","06","07","07","",null,"RF Distribution L2 & L3",null,"2.03.06.07.07",null,null,null,"SP3060707"]
["2","03","06","07","08","",null,"RF Fiber Optics Electronics",null,"2.03.06.07.08",null,null,null,"SP3060708"]
["2","03","07",{"$nulls":4},"Linac System Commissioning",null,"Summary"]
["2","03","07","01","","",null,"Linac L01 System Commissioning",null,"2.03.07.01",{"$nulls":4},"CM30701"]
["2","03","07","02","","",null,"Linac BC1 System Commissioning",null,"2.03.07.02",{"$nulls":4},"CM30702"]
["2","03","07","03","","",null,"Linac L02 System Commissioning",null,"2.03.07.03",{"$nulls":4},"CM30703"]
["2","03","07","04","","",null,"Linac BC2 System Commissioning",null,"2.03.07.04",{"$nulls":4},"CM30704"]
["2","03","07","05","","",null,"Linac L03 System Commissioning",null,"2.03.07.05",{"$nulls":4},"CM30705"]
["2","03","07","06","","",null,"Linac LTU System Commissioning",null,"2.03.07.06",{"$nulls":4},"CM30706"]
["2","03","07","07","","",null,"Linac E-Dump System Commissioining",null,"2.03.07.07",{"$nulls":4},"CM30707"]
["2","04",{"$nulls":5},"UNDULATOR SYSTEM (OPC)",null,"Summary"]
["2","04","01",{"$nulls":4},"Undulator System Management & Integration",null,"Summary"]
["2","04","02",{"$nulls":4},"Controls",null,"Summary"]
["2","04","02","01",null,null,null,"Controls Management and Integration",null,"Summary"]
["2","04","02","02",null,null,null,"Motion",null,"Summary"]
["2","04","02","03",null,null,null,"Signal Analysis",null,"Summary"]
["2","04","02","04",null,null,null,"Video",null,"Summary"]
["2","04","02","05",null,null,null,"Data Acquisition and Control",null,"Summary"]
["2","04","02","06",null,null,null,"Vacuum",null,"Summary"]
["2","04","02","07","","",null,"Machine Protection",null,"2.04.02.07",null,null,null,"SP40207"]
["2","04","03",{"$nulls":4},"Undulator Magnet & Support",null,"Summary"]
["2","04","03","01",null,null,null,"UND Magnet & Support - Mgmt and Integration",null,"Summary"]
["2","04","03","02",null,null,null,"First Prototype Undulator & Mfg Plan",null,"Summary"]
["2","04","03","03","","",null,"1st Article Undulators & Long Lead Procurements",null,"2.04.03.03",null,null,null,"SP40303"]
["2","04","03","04","","",null,"Production Undulator",null,"2.04.03.04",null,null,null,"SP40304"]
["2","04","03","05","","",null,"Focusing Magnets",null,"2.04.03.05",null,null,null,"SP40305"]
["2","04","03","06","","",null,"Undulator Magnetic Measurement Facility (SLAC)",null,"2.04.03.06",null,null,null,"SP40306"]
["2","04","03","07",null,null,null,"Reserved",null,"Summary"]
["2","04","03","08","","",null,"Fixed Supports",null,"2.04.03.08",null,null,null,"SP40308"]
["2","04","04",{"$nulls":4},"Vacuum System",null,"Summary"]
["2","04","04","01",null,null,null,"Reserved",null,"Summary"]
["2","04","04","02","","",null,"Undulator Vacuum Chamber Assembly",null,"2.04.04.02",null,null,null,"SP40402"]
["2","04","04","03","","",null,"Beam-line Bellows Module Assembly",null,"2.04.04.03",null,null,null,"SP40403"]
["2","04","04","04",null,null,null,"Reserved",null,"Summary"]
["2","04","04","05","","",null,"Short Diagnostic Break (SDB) Assembly",null,"2.04.04.05",null,null,null,"SP40405"]
["2","04","04","06","","",null,"Long Diagnostic Break (LDB) Assembly",null,"2.04.04.06",null,null,null,"SP40406"]
["2","04","04","07","","",null,"Entrance Section Assembly",null,"2.04.04.07",null,null,null,"SP40407"]
["2","04","04","08","","",null,"Exit Section Assembly",null,"2.04.04.08",null,null,null,"SP40408"]
["2","04","04","09",null,null,null,"Reserved",null,"Summary"]
["2","04","05",{"$nulls":4},"Undulator System Diagnostics [OPC]",null,"Summary"]
["2","04","05","01",null,null,null,"Reserved",null,"Summary"]
["2","04","05","02","","",null,"E-Beam and X-Ray Profile Diagnostics",null,"2.04.05.02",null,null,9681254,"SP40502","CM40502"]
["2","04","05","03","","",null,"High-Power X-Ray and Profile Diagnostics (HPD)",null,"2.04.05.03",null,null,9681255,null,"CM40503"]
["2","04","05","04","","",null,"End-of-Undulator(EOU) X-ray and Profile diagnost",null,"2.04.05.04",null,null,9681256]
["2","04","05","05","","",null,"RFBPM",null,"2.04.05.05",null,null,null,"SP40505"]
["2","04","05","06",null,null,null,"Reserved",null,"Summary"]
["2","04","05","07","","",null,"Charge Monitor (CM)",null,"2.04.05.07",null,null,null,"SP40507"]
["2","04","05","08","","",null,"Cherenkov Detector",null,"2.04.05.08",null,null,null,"SP40508"]
["2","04","05","09","","",null,"Radiation Detection Monitor (RDM)",null,"2.04.05.09",null,null,null,"SP40509"]
["2","04","05","10",null,null,null,"Reserved",null,"Summary"]
["2","04","05","11",null,null,null,"Reserved",null,"Summary"]
["2","04","06",{"$nulls":4},"Undulator System Commissioning",null,"Summary"]
["2","04","06","01","","",null,"Undulator System Commissioning",null,"2.04.06.01",{"$nulls":4},"CM40601"]
["2","05",{"$nulls":5},"X-RAY TRANSPORT & DIAGNOSTICS SYSTEMS (OPC)",null,"Summary"]
["2","05","01",{"$nulls":4},"System Management & Integration",null,"Summary"]
["2","05","01","01","","",null,"Management",null,"2.05.01.01",null,null,9681283,null,"CM50101"]
["2","05","02",{"$nulls":4},"Controls",null,"Summary"]
["2","05","02","01",null,null,null,"Reserved",null,"Summary"]
["2","05","02","02",null,null,null,"Slow Controls",null,"Summary"]
["2","05","02","03",null,null,null,"Fast Controls",null,"Summary"]
["2","05","02","04",null,null,null,"Femto Controls",null,"Summary"]
["2","05","03",{"$nulls":4},"Mechanical & Vacuum Subsystem",null,"Summary"]
["2","05","03","01",null,null,null,"Reserved",null,"Summary"]
["2","05","03","02",null,null,null,"Mech/Vac Front End",null,"Summary"]
["2","05","03","03",null,null,null,"Mech/Vac Near Hall",null,"Summary"]
["2","05","03","04",null,null,null,"Mech/Vac Tunnel",null,"Summary"]
["2","05","03","05",null,null,null,"Mech/Vac Far Hall",null,"Summary"]
["2","05","04",{"$nulls":4},"Optical  Subsystem",null,"Summary"]
["2","05","04","01","","",null,"Optical Systems Engineering",null,"2.05.04.01",null,null,9681278]
["2","05","04","02",null,null,null,"Facility Optics",null,"Summary"]
["2","05","04","03",null,null,null,"End Station Optics",null,"Summary"]
["2","05","04","04",null,null,null,"Crystals & Gratings",null,"Summary"]
["2","05","05",{"$nulls":4},"Diagnostics Subsystem",null,"Summary"]
["2","05","05","01",null,null,null,"Reserved",null,"Summary"]
["2","05","05","02","","",null,"Modeling & Simulation",null,"2.05.05.02",null,null,9681284]
["2","05","05","03","","",null,"Facility Diagnostics",null,"2.05.05.03",null,null,null,"SP50503"]
["2","05","05","04","","",null,"Commissioning Diagnostics",null,"2.05.05.04",null,null,"RD50504"]
["2","05","06",{"$nulls":4},"Reserved",null,"Summary"]
["2","05","06","01",null,null,null,"Reserved",null,"Summary"]
["2","06",{"$nulls":5},"X-RAY END STATION SYSTEMS (OPC)",null,"Summary"]
["2","06","01",{"$nulls":4},"Reserved",null,"Summary"]
["2","06","01","01",null,null,null,"Reserved",null,"Summary"]
["2","06","02",{"$nulls":4},"Controls Subsystem",null,"Summary"]
["2","06","02","01","","",null,"Cabling",null,"2.06.02.01",{"$nulls":4},"CM60201"]
["2","06","02","02","","",null,"Network",null,"2.06.02.02",{"$nulls":4},"CM60202"]
["2","06","02","03","","",null,"PC Support",null,"2.06.02.03",{"$nulls":4},"CM60203"]
["2","06","02","04","","",null,"Beamline Controls",null,"2.06.02.04",{"$nulls":4},"CM60204"]
["2","06","02","05","","",null,"X-Ray PPS",null,"2.06.02.05",{"$nulls":4},"CM60205"]
["2","06","02","06","","",null,"X-Ray MPS",null,"2.06.02.06",{"$nulls":4},"CM60206"]
["2","06","02","07","","",null,"Laser PPS",null,"2.06.02.07",{"$nulls":4},"CM60207"]
["2","06","02","08","","",null,"User Safeguards",null,"2.06.02.08",{"$nulls":4},"CM60208"]
["2","06","03",{"$nulls":4},"Mechanical/Vacuum Subsystem",null,"Summary"]
["2","06","03","01",null,null,null,"Reserved",null,"Summary"]
["2","06","03","02","","",null,"Vacuum Components - Mech/Vac",null,"2.06.03.02",{"$nulls":4},"CM60302"]
["2","06","03","03","","",null,"Experimental Chambers",null,"2.06.03.03",{"$nulls":4},"CM60303"]
["2","06","04",{"$nulls":4},"Laser Subsystem",null,"Summary"]
["2","06","04","01","","",null,"Oscillator Laser & Pump",null,"2.06.04.01",{"$nulls":4},"CM60401"]
["2","06","04","02","","",null,"Laser Diagnostics",null,"2.06.04.02",{"$nulls":4},"CM60402"]
["2","06","04","03","","",null,"Laser Supplies & Optical Transport",null,"2.06.04.03",{"$nulls":4},"CM60403"]
["2","06","04","04","","",null,"Laser Timing",null,"2.06.04.04",{"$nulls":4},"CM60404"]
["2","06","04","05","","",null,"Laser Amplifiers",null,"2.06.04.05",{"$nulls":4},"CM60405"]
["2","06","05",{"$nulls":4},"X-Ray Detectors",null,"Summary"]
["2","06","05","01","","",null,"Beam Imaging",null,"2.06.05.01",{"$nulls":4},"CM60501"]
["2","06","05","02","","",null,"2-D X-Ray Detector",null,"2.06.05.02",{"$nulls":4},"CM60502"]
["2","06","05","03","","",null,"Beam Intensity",null,"2.06.05.03",{"$nulls":4},"CM60503"]
["2","06","05","04","","",null,"Streak Camera",null,"2.06.05.04",{"$nulls":4},"CM60504"]
["2","06","06",{"$nulls":4},"X-Ray End Station System Commissioning",null,"Summary"]
["2","06","06","01",null,null,null,"X-Ray End Station System Commissioning",null,"Summary"]
["2","06","07",{"$nulls":4},"Atomic Physics",null,"Summary"]
["2","06","07","01","","",null,"Atomic Physics Samples",null,"2.06.07.01",null,null,"RD60701",null,"CM60701"]
["2","06","07","02","","",null,"Atomic Physics Diagnostics",null,"2.06.07.02",null,null,"RD60702",null,"CM60702"]
["2","06","07","03","","",null,"Atomic Physics Data Analysis",null,"2.06.07.03",null,null,"RD60703",null,"CM60703"]
["2","06","07","04","","",null,"Atomic Physics Detectors",null,"2.06.07.04",null,null,"RD60704",null,"CM60704"]
["2","07",{"$nulls":5},"Reserved",null,"Summary"]
["2","08",{"$nulls":5},"LCLS SYSTEM COMMISSIONING (OPC)",null,"Summary"]
["2","08","01",{"$nulls":4},"Reserved",null,"Summary"]
["2","08","02",{"$nulls":4},"Reserved",null,"Summary"]
["2","08","03",{"$nulls":4},"Reserved",null,"Summary"]
["2","08","04",{"$nulls":4},"Reserved",null,"Summary"]
["2","08","05",{"$nulls":4},"Reserved",null,"Summary"]
["2","08","06",{"$nulls":4},"Reserved",null,"Summary"]
["2","09",{"$nulls":5},"CONVENTIONAL FACILITIES (OPC)",null,"Summary"]
["2","09","01",{"$nulls":4},"Management Integration",null,"Summary"]
["2","09","01","01",null,null,null,"Reserved",null,"Summary"]
["2","09","02",{"$nulls":4},"Reserved",null,"Summary"]
["2","09","03",{"$nulls":4},"Reserved",null,"Summary"]

{"sheet":"ResDes","index":9,"n_rows":149,"n_cols":2,"rows_kept":149,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}
["Resource","Description"]
["AN_ADMN","ANL Administration"]
["AN_AWARD","ANL Award - Commitments"]
["AN_AWRD5","ANL Award - Commitments (no OH)"]
["AN_AWXX","ANL Award - Commitments (no OH)"]
["AN_CCA","ANL Controls: Coordinator Associate"]
["AN_CE","ANL Controls: Engineer"]
["AN_CP","ANL Controls: Programmer"]
["AN_CT","ANL Controls: Technician"]
["AN_EE","ANL Electrical Engineer"]
["AN_KCA","ANL Klystron: Coordinator Associate"]
["AN_KE","ANL Klystron: Engineer"]
["AN_KT","ANL Klystron: Technician"]
["AN_MDD","ANL Mech Drafting / Design"]
["AN_ME","ANL Mechanical Engineer"]
["AN_MES","ANL Metrology: Eng / Surveyors"]
["AN_MFAT","ANL Mech Fab: Assembly Tech"]
["AN_MFMS","ANL Mech Fab: Machine Shop"]
["AN_MFPC","ANL Mech Fab: Plating & Cleaning"]
["AN_MSCS","ANL M&S - Conusmable Supply"]
["AN_MSEG","ANL M&S - Equip Genrl(dsn, s/hdwr, mtrl)"]
["AN_MSEQ","ANL M&S - Equipment (capital, prdn sppt)"]
["AN_MSPS","ANL M&S - Procured Services"]
["AN_MSSC","ANL M&S - Major Subcontracts"]
["AN_MSTR","ANL M&S - Travel"]
["AN_MSXX","ANL M&S - OH Alloc Rate Excluded (no OH)"]
["AN_MTRL","ANL M&S - Raw Material"]
["AN_MTRL5","ANL M&S - Raw Material (no OH)"]
["AN_MTRT","ANL Non-labor: Travel"]
["AN_MVE","ANL AD: Mech / Vacuum Engineer"]
["AN_PCCA","ANL PCD: Coordinator Associate"]
["AN_PCE","ANL PCD: Engineer"]
["AN_PCEF","ANL PCD: Inst-Cabling-Elec Fab"]
["AN_PCT","ANL PCD: Technician"]
["AN_PHPD","ANL Physicist - Post Doc"]
["AN_PHS","ANL Physicist - Scientist"]
["AN_PHSS","ANL Physicist - Senior Scientist"]
["AN_PM","ANL Project Management"]
["AN_SEE","ANL Site Engineering: Engineer"]
["AN_SEL","ANL Site Engineering: Labor"]
["AN_SEPM","ANL Site Engineering: Plant Maint"]
["AN_TMUC","ANL T&M Crafts - Union Carpenter"]
["AN_TMUE","ANL T&M Crafts - Union Electrician"]
["AN_TMUI","ANL T&M Crafts - Union Ironwork"]
["AN_TMUO","ANL T&M Crafts - Union Equip Op"]
["AN_TMUP","ANL T&M Crafts - Union Pipefitter"]
["AN_TMUW","ANL T&M Crafts - Welder"]
["LL_ADMN","LLNL Administration"]
["LL_AWARD","LLNL Award - Commitments"]
["LL_AWRD5","LLNL Award - Commitments (no OH)"]
["LL_AWXX","LLNL Award - Commitments (no OH)"]
["LL_CCA","LLNL Controls: Coordinator Associate"]
["LL_CE","LLNL Controls: Engineer"]
["LL_CP","LLNL Controls: Programmer"]
["LL_CT","LLNL Controls: Technician"]
["LL_EE","LLNL Electrical Engineer"]
["LL_KCA","LLNL Klystron: Coordinator Associate"]
["LL_KE","LLNL Klystron: Engineer"]
["LL_KT","LLNL Klystron: Technician"]
["LL_MDD","LLNL Mech Drafting / Design"]
["LL_ME","LLNL Mechanical Engineer"]
["LL_MES","LLNL Metrology: Eng / Surveyors"]
["LL_MFAT","LLNL Mech Fab: Assembly Tech"]
["LL_MFMS","LLNL Mech Fab: Machine Shop"]
["LL_MFPC","LLNL Mech Fab: Plating & Cleaning"]
["LL_MSCS","LLNL M&S - Consumable Supplies"]
["LL_MSEG","LLNL M&S - Equip Gen (dsn,h/swre,mtrl)"]
["LL_MSEQ","LLNL M&S - Equip (captial, prdn sppt)"]
["LL_MSPS","LLNL M&S - Procured Services"]
["LL_MSSC","LLNL M&S - Major Subcontracts"]
["LL_MSTR","LLNL M&S - Travel"]
["LL_MSXX","LLNL M&S-OH Alloc Rate Excluded (no OH)"]
["LL_MTRL","LLNL M&S - Raw Material"]
["LL_MTRL5","LLNL M&S - Raw Material (no OH)"]
["LL_MVE","LLNL AD: Mech / Vacuum Engineer"]
["LL_PCCA","LLNL PCD: Coordinator Associate"]
["LL_PCE","LLNL PCD: Engineer"]
["LL_PCEF","LLNL PCD: Inst-Cabling-Elec Fab"]
["LL_PCT","LLNL PCD: Technician"]
["LL_PHPD","LLNL Physicist - Post Doc"]
["LL_PHS","LLNL Physicist - Scientist"]
["LL_PHSS","LLNL Physicist - Senior Scientist"]
["LL_PM","LLNL Project Management"]
["LL_PRC","LLNL Precision Crafts (machine tech)"]
["LL_PRE","LLNL Precision Engineer"]
["LL_RP","LLNL Radiation Physicist"]
["LL_SEE","LLNL Site Engineering: Engineer"]
["LL_SEL","LLNL Site Engineering: Labor"]
["LL_SEPM","LLNL Site Engineering: Plant Maint"]
["LL_TMUC","LLNL T&M Crafts - Union Carpenter"]
["LL_TMUE","LLNL T&M Crafts - Union Electrician"]
["LL_TMUI","LLNL T&M Crafts - Union Ironwork"]
["LL_TMUO","LLNL T&M Crafts - Union Equip Op"]
["LL_TMUP","LLNL T&M Crafts - Union Pipefitter"]
["LL_TMUW","LLNL T&M Crafts - Welder"]
["SL_ADMN","SLAC Administration"]
["SL_AWARD","SLAC Award - Commitments"]
["SL_AWRD5","SLAC Award - Commitments (no OH)"]
["SL_AWXX","SLAC Award - Commitments (no OH)"]
["SL_CCA","SLAC Controls: Coordinator Associate"]
["SL_CE","SLAC Controls: Engineer"]
["SL_CP","SLAC Controls: Programmer"]
["SL_CRA","SLAC Computer Resource Associate"]
["SL_CRM","SLAC Computer Resource Manager"]
["SL_CT","SLAC Controls: Technician"]
["SL_EE","SLAC Electrical Engineer"]
["SL_FA","SLAC Financial Analyst"]
["SL_KCA","SLAC Klystron: Coordinator Associate"]
["SL_KE","SLAC Klystron: Engineer"]
["SL_KT","SLAC Klystron: Technician"]
["SL_MDD","SLAC Mech Drafting / Design"]
["SL_ME","SLAC Mechanical Engineer"]
["SL_MES","SLAC Metrology: Eng \\ Surveyors"]
["SL_MFAT","SLAC Mech Fab: Assembly Tech"]
["SL_MFMS","SLAC Mech Fab: Machine Shop"]
["SL_MFPC","SLAC Mech Fab: Plating & Cleaning"]
["SL_MSCS","SLAC M&S - Consumable Supplies"]
["SL_MSEG","SLAC M&S-Equip General (DSN,HW/SW,MTRL)"]
["SL_MSEQ","SLAC M&S - Equip (capital, prdn spprt)"]
["SL_MSPS","SLAC M&S - Procured Services"]
["SL_MSSC","SLAC M&S - Major Subcontract"]
["SL_MSTR","SLAC M&S - Travel"]
["SL_MSXX","SLAC M&S-OH Alloc Rate Excluded (no OH)"]
["SL_MTRL","SLAC M&S - Raw Material"]
["SL_MTRL5","SLAC M&S - Raw Material (no OH)"]
["SL_MVE","SLAC AD: Mech / Vacuum Engineer"]
["SL_OE","SLAC Optics Engineer"]
["SL_OT","SLAC Optics Technician"]
["SL_PCCA","SLAC PCD: Coordinator Associate"]
["SL_PCE","SLAC PCD: Engineer"]
["SL_PCEF","SLAC PCD: Inst-Cabling-Elec Fab"]
["SL_PCT","SLAC PCD: Technician"]
["SL_PHH","SLAC Physicist - Health Scientist"]
["SL_PHPD","SLAC Physicist - Post Doc"]
["SL_PHS","SLAC Physicist - Scientist"]
["SL_PHSS","SLAC Physicist - Senior Scientist"]
["SL_PM","SLAC Project Management"]
["SL_SEE","SLAC Site Engineering: Engineer"]
["SL_SEEM","SSLAC-Site Engrg Mgmt"]
["SL_SEL","SLAC Site Engineering: Labor"]
["SL_SEPM","SLAC Site Engineering: Plant Maint"]
["SL_TMUC","SLAC T&M Crafts - Union Carpenter"]
["SL_TMUE","SLAC T&M Crafts - Union Electrician"]
["SL_TMUI","SLAC T&M Crafts - Union Ironwork"]
["SL_TMUO","SLAC T&M Crafts - Union Equip Op"]
["SL_TMUP","SLAC T&M Crafts - Union Pipefitter"]
["SL_TMUW","SLAC T&M Crafts - Welder"]
["SL_TSM","SLAC Technical System Management"]
["SL_UTR","SLAC UTR"]

{"sheet":"Indirect","index":10,"n_rows":35,"n_cols":4,"rows_kept":35,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}
["SL_ADMN1","SLAC Administration",1.2,1.38]
["SL_CCA11","SLAC Controls: Coord",1.2,1.38]
["SL_CE1","SLAC Controls: Engin",1.2,1.38]
["SL_CP1","SLAC Controls: Progr",1.2,1.38]
["SL_CT1","SLAC Controls: Techn",1.2,1.38]
["SL_EE1","SLAC Electrical Engi",1.2,1.38]
["SL_KCA1","SLAC Klystron: Coord",1.2,1.38]
["SL_KE1","SLAC Klystron: Engin",1.2,1.38]
["SL_KT1","SLAC Klystron: Techn",1.2,1.38]
["SL_MDD1","SLAC Mech Drafting /",1.2,1.38]
["SL_ME1","SLAC Mechanical Engi",1.2,1.38]
["SL_MES1","SLAC Metrology: Eng ",1.2,1.38]
["SL_MFAT1","SLAC Mech Fab: Assem",1.2,1.38]
["SL_MFMS1","SLAC Mech Fab: Machi",1.2,1.38]
["SL_MFPC1","SLAC Mech Fab: Plati",1.2,1.38]
["SL_MSEG1","SLAC M&S-Equip Gener",1.06,1.0552]
["SL_MSEQ1","SLAC M&S - Equip (ca",1.06,1.0552]
["SL_MSPS1","SLAC M&S - Procured ",1.06,1.0552]
["SL_MSSC1","SLAC M&S - Major Sub",1.06,1.0552]
["SL_MSTR1","SLAC M&S - Travel",1.2,1.38]
["SL_MSXX1","SLAC M&S-OH Alloc Ra",1,1]
["SL_MVE1","SLAC AD: Mech / Vacu",1.2,1.38]
["SL_OE1","SLAC Optics Engineer",1.2,1.38]
["SL_OT1","SLAC Optics Technici",1.2,1.38]
["SL_PCCA1","SLAC PCD: Coordinato",1.2,1.38]
["SL_PCE1","SLAC PCD: Engineer",1.2,1.38]
["SL_PCEF1","SLAC PCD: Inst-Cabli",1.2,1.38]
["SL_PCT1","SLAC PCD: Technician",1.2,1.38]
["SL_PHPD1","SLAC Physicist - Pos",1.2,1.38]
["SL_PHS1","SLAC Physicist - Sci",1.2,1.38]
["SL_PHSS1","SLAC Physicist - Sen",1.2,1.38]
["SL_SEE1","SLAC Site Engineerin",1.2,1.38]
["SL_TMUE1","SLAC T&M Crafts - Un",1.2,1.38]
["SL_TMUI1","SLAC T&M Crafts - Un",1.2,1.38]
["SL_PHPU","SLAC NEW",1.2,1.38]