{"text_format":"2","workbook":"xls","n_sheets":9,"sheets":["lclsrate","opcclc","tecclc","Master","CHNUM","Detailed Cost Estimate","WBS-CN-PP","ResDes","Indirect"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":1,"defined_names":14,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"lclsrate","index":0,"n_rows":676,"n_cols":7,"rows_kept":676,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["RATEFILE","DESCRIP","RATE_TABLE","RATE_DESCRIP","COMBO","RATE","RATE_DATE"]
["LCLSRAT3","LCLS RATES","AA_MSEG","RTDESC","AA_MSEG37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AA_MSEG1","RTDESC","AA_MSEG138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AA_MSEQ","RTDESC","AA_MSEQ37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AA_MSEQ1","RTDESC","AA_MSEQ138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AA_MSSC","RTDESC","AA_MSSC37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AA_MSSC1","RTDESC","AA_MSSC138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_ADMN","RTDESC","AN_ADMN37895",63.24,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AN_ADMN1","RTDESC","AN_ADMN138626",83.51,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_AW1","RTDESC","AN_AW138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_AWARD","RTDESC","AN_AWARD37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AN_CCA","RTDESC","AN_CCA37895",67.43,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AN_CCA1","RTDESC","AN_CCA138626",83.51,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_CE","RTDESC","AN_CE37895",67.43,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AN_CE1","RTDESC","AN_CE138626",83.51,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_CP","RTDESC","AN_CP37895",67.43,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AN_CP1","RTDESC","AN_CP138626",83.51,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_CS1","RTDESC","AN_CS138626",0.257,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_CS2","RTDESC","AN_CS238626",0.196,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_CS4","RTDESC","AN_CS438626",0.292,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_CS5","RTDESC","AN_CS538626",0.196,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_CS6","RTDESC","AN_CS638626",0.064,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_CT","RTDESC","AN_CT37895",42.99,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AN_CT1","RTDESC","AN_CT138626",49.03,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_EE","RTDESC","AN_EE37895",67.43,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AN_EE1","RTDESC","AN_EE138626",83.51,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_GA1","RTDESC","AN_GA138626",0.026,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_GA2","RTDESC","AN_GA238626",0.027,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_MDD","RTDESC","AN_MDD37895",42.99,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AN_MDD1","RTDESC","AN_MDD138626",49.03,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_ME","RTDESC","AN_ME37895",63.24,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AN_ME1","RTDESC","AN_ME138626",83.51,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_MES","RTDESC","AN_MES37895",67.43,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AN_MES1","RTDESC","AN_MES138626",83.51,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_MFAT","RTDESC","AN_MFAT37895",42.51,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AN_MFAT1","RTDESC","AN_MFAT138626",49.03,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_MFMS","RTDESC","AN_MFMS37895",53.97,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AN_MFMS1","RTDESC","AN_MFMS138626",81,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_MSCS","RTDESC","AN_MSCS37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AN_MSCS1","RTDESC","AN_MSCS138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_MSEG","RTDESC","AN_MSEG37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AN_MSEG1","RTDESC","AN_MSEG138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_MSEQ","RTDESC","AN_MSEQ37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AN_MSEQ1","RTDESC","AN_MSEQ138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_MSPS","RTDESC","AN_MSPS37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AN_MSPS1","RTDESC","AN_MSPS138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_MSSC","RTDESC","AN_MSSC37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AN_MSSC1","RTDESC","AN_MSSC138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_MSSF","RTDESC","AN_MSSF37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AN_MSSF1","RTDESC","AN_MSSF138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_MSTR","RTDESC","AN_MSTR37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AN_MSTR1","RTDESC","AN_MSTR138626",1.29,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_MSXX","RTDESC","AN_MSXX37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AN_MSXX1","RTDESC","AN_MSXX138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_MTRL","RTDESC","AN_MTRL37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AN_MTRL1","RTDESC","AN_MTRL138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_MVE","RTDESC","AN_MVE37895",63.24,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AN_MVE1","RTDESC","AN_MVE138626",83.51,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_OH1","RTDESC","AN_OH137895",0.3224,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AN_OH2","RTDESC","AN_OH237895",0.2598,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AN_OH3","RTDESC","AN_OH337895",0,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AN_OH4","RTDESC","AN_OH437895",0,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AN_PHH","RTDESC","AN_PHH37895",45.68,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AN_PHH1","RTDESC","AN_PHH138626",45.68,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_PHPD","RTDESC","AN_PHPD37895",33.95,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AN_PHPD1","RTDESC","AN_PHPD138626",37.26,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_PHS","RTDESC","AN_PHS37895",63.24,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AN_PHS1","RTDESC","AN_PHS138626",83.51,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_PHSS","RTDESC","AN_PHSS37895",63.24,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AN_PHSS1","RTDESC","AN_PHSS138626",63.24,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_PM","RTDESC","AN_PM37895",63.24,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AN_PM1","RTDESC","AN_PM138626",83.51,"2005-10-01"]
["LCLSRAT3","LCLS RATES","AN_SEE","RTDESC","AN_SEE37895",85,"2003-10-01"]
["LCLSRAT3","LCLS RATES","AN_SEE1","RTDESC","AN_SEE138626",83.51,"2005-10-01"]
["LCLSRAT3","LCLS RATES","BA","RTDESC","BA37500",1,"2002-09-01"]
["LCLSRAT3","LCLS RATES","BASE","RTDESC","BASE37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","ESC","RTDESC","ESC37895",0,"2003-10-01"]
["LCLSRAT3","LCLS RATES","ESC","RTDESC","ESC38261",0.029,"2004-10-01"]
["LCLSRAT3","LCLS RATES","ESC","RTDESC","ESC38626",0.057812,"2005-10-01"]
["LCLSRAT3","LCLS RATES","ESC","RTDESC","ESC38991",0.085315,"2006-10-01"]
["LCLSRAT3","LCLS RATES","ESC","RTDESC","ESC39356",0.113533,"2007-10-01"]
["LCLSRAT3","LCLS RATES","ESC","RTDESC","ESC39722",0.142485,"2008-10-01"]
["LCLSRAT3","LCLS RATES","ESC1","RTDESC","ESC138626",0,"2005-10-01"]
["LCLSRAT3","LCLS RATES","ESC1","RTDESC","ESC138991",0.026,"2006-10-01"]
["LCLSRAT3","LCLS RATES","ESC1","RTDESC","ESC139356",0.052676,"2007-10-01"]
["LCLSRAT3","LCLS RATES","ESC1","RTDESC","ESC139722",0.08004558,"2008-10-01"]
["LCLSRAT3","LCLS RATES","ESC_CF","RTDESC","ESC_CF38261",0,"2004-10-01"]
["LCLSRAT3","LCLS RATES","ESC_CF","RTDESC","ESC_CF38626",0.03,"2005-10-01"]
["LCLSRAT3","LCLS RATES","ESC_CF","RTDESC","ESC_CF38991",0.08,"2006-10-01"]
["LCLSRAT3","LCLS RATES","ESC_CF","RTDESC","ESC_CF39356",0.19,"2007-10-01"]
["LCLSRAT3","LCLS RATES","ESC_CF","RTDESC","ESC_CF39722",0.3,"2008-10-01"]
["LCLSRAT3","LCLS RATES","ESC_CF","RTDESC","ESC_CF40087",0.41,"2009-10-01"]
["LCLSRAT3","LCLS RATES","ESC_ZERO","RTDESC","ESC_ZERO38626",0,"2005-10-01"]
["LCLSRAT3","LCLS RATES","ESC_ZERO","RTDESC","ESC_ZERO38991",0,"2006-10-01"]
["LCLSRAT3","LCLS RATES","ESC_ZERO","RTDESC","ESC_ZERO39356",0,"2007-10-01"]
["LCLSRAT3","LCLS RATES","ESC_ZERO","RTDESC","ESC_ZERO39722",0,"2008-10-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE37803",0.005434782608695652,"2003-07-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE37895",0.005434782608695652,"2003-10-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE37956",0.005434782608695652,"2003-12-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38047",0.005434782608695652,"2004-03-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38412",0.005434782608695652,"2005-03-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38565",0.005434782608695652,"2005-08-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38777",0.005434782608695652,"2006-03-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38930",0.005434782608695652,"2006-08-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39295",0.005434782608695652,"2007-08-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39356",0.005434782608695652,"2007-10-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39722",0.005434782608695652,"2008-10-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39995",0.005434782608695652,"2009-07-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE40056",0.005434782608695652,"2009-08-31"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE37712",0.005681818181818182,"2003-04-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE37742",0.005681818181818182,"2003-05-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE37865",0.005681818181818182,"2003-09-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38078",0.005681818181818182,"2004-04-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38139",0.005681818181818182,"2004-06-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38200",0.005681818181818182,"2004-08-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38504",0.005681818181818182,"2005-06-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38838",0.005681818181818182,"2006-05-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38869",0.005681818181818182,"2006-06-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38991",0.005681818181818182,"2006-10-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39142",0.005681818181818182,"2007-03-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39203",0.005681818181818182,"2007-05-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39539",0.005681818181818182,"2008-04-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39630",0.005681818181818182,"2008-07-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39783",0.005681818181818182,"2008-12-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39873",0.005681818181818182,"2009-03-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39904",0.005681818181818182,"2009-04-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39965",0.005681818181818182,"2009-06-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE40087",0.005681818181818182,"2009-10-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE40148",0.005681818181818182,"2009-12-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE37681",0.005952380952380952,"2003-03-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE37773",0.005952380952380952,"2003-06-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE37834",0.005952380952380952,"2003-08-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38169",0.005952380952380952,"2004-07-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38231",0.005952380952380952,"2004-09-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38261",0.005952380952380952,"2004-10-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38443",0.005952380952380952,"2005-04-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38473",0.005952380952380952,"2005-05-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38596",0.005952380952380952,"2005-09-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38626",0.005952380952380952,"2005-10-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38687",0.005952380952380952,"2005-12-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39083",0.005952380952380952,"2007-01-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39173",0.005952380952380952,"2007-04-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39234",0.005952380952380952,"2007-06-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39264",0.005952380952380952,"2007-07-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39448",0.005952380952380952,"2008-01-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39508",0.005952380952380952,"2008-03-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39569",0.005952380952380952,"2008-05-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39600",0.005952380952380952,"2008-06-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39661",0.005952380952380952,"2008-08-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39692",0.005952380952380952,"2008-09-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39814",0.005952380952380952,"2009-01-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39934",0.005952380952380952,"2009-05-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE40118",0.005952380952380952,"2009-11-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE37653",0.00625,"2003-02-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE37926",0.00625,"2003-11-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE37987",0.00625,"2004-01-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38108",0.00625,"2004-05-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38292",0.00625,"2004-11-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38322",0.00625,"2004-12-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38353",0.00625,"2005-01-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38534",0.00625,"2005-07-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38657",0.00625,"2005-11-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38718",0.00625,"2006-01-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38808",0.00625,"2006-04-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38899",0.00625,"2006-07-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38961",0.00625,"2006-09-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39022",0.00625,"2006-11-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39052",0.00625,"2006-12-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39387",0.00625,"2007-11-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39417",0.00625,"2007-12-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39479",0.00625,"2008-02-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39845",0.00625,"2009-02-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE40026",0.00625,"2009-08-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38018",0.006578947368421052,"2004-02-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38384",0.006578947368421052,"2005-02-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE38749",0.006578947368421052,"2006-02-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39114",0.006578947368421052,"2007-02-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39326",0.006578947368421052,"2007-09-01"]
["LCLSRAT3","LCLS RATES","FTE","RTDESC","FTE39753",0.006944444444444444,"2008-11-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO37803",0.005434782608695652,"2003-07-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO37895",0.005434782608695652,"2003-10-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38047",0.005434782608695652,"2004-03-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38412",0.005434782608695652,"2005-03-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38565",0.005434782608695652,"2005-08-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38777",0.005434782608695652,"2006-03-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38930",0.005434782608695652,"2006-08-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39295",0.005434782608695652,"2007-08-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39356",0.005434782608695652,"2007-10-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39722",0.005434782608695652,"2008-10-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38078",0.005681818181818182,"2004-04-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38139",0.005681818181818182,"2004-06-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38200",0.005681818181818182,"2004-08-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38504",0.005681818181818182,"2005-06-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38838",0.005681818181818182,"2006-05-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38869",0.005681818181818182,"2006-06-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38991",0.005681818181818182,"2006-10-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39142",0.005681818181818182,"2007-03-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39203",0.005681818181818182,"2007-05-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39539",0.005681818181818182,"2008-04-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39630",0.005681818181818182,"2008-07-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39873",0.005681818181818182,"2009-03-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39904",0.005681818181818182,"2009-04-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39965",0.005681818181818182,"2009-06-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39995",0.005681818181818182,"2009-07-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO40087",0.005681818181818182,"2009-10-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO37560",0.005952380952380952,"2002-10-31"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO37834",0.005952380952380952,"2003-08-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO37865",0.005952380952380952,"2003-09-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO37956",0.005952380952380952,"2003-12-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38169",0.005952380952380952,"2004-07-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38231",0.005952380952380952,"2004-09-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38261",0.005952380952380952,"2004-10-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38443",0.005952380952380952,"2005-04-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38473",0.005952380952380952,"2005-05-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38596",0.005952380952380952,"2005-09-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38626",0.005952380952380952,"2005-10-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39083",0.005952380952380952,"2007-01-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39173",0.005952380952380952,"2007-04-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39234",0.005952380952380952,"2007-06-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39264",0.005952380952380952,"2007-07-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39448",0.005952380952380952,"2008-01-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39508",0.005952380952380952,"2008-03-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39569",0.005952380952380952,"2008-05-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39600",0.005952380952380952,"2008-06-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39661",0.005952380952380952,"2008-08-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39692",0.005952380952380952,"2008-09-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39783",0.005952380952380952,"2008-12-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO40026",0.005952380952380952,"2009-08-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO40056",0.005952380952380952,"2009-08-31"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO40148",0.005952380952380952,"2009-12-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO37500",0.00625,"2002-09-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO37530",0.00625,"2002-10-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO37987",0.00625,"2004-01-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38108",0.00625,"2004-05-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38292",0.00625,"2004-11-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38322",0.00625,"2004-12-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38353",0.00625,"2005-01-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38534",0.00625,"2005-07-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38657",0.00625,"2005-11-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38687",0.00625,"2005-12-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38718",0.00625,"2006-01-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38808",0.00625,"2006-04-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38899",0.00625,"2006-07-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38961",0.00625,"2006-09-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39022",0.00625,"2006-11-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39387",0.00625,"2007-11-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39479",0.00625,"2008-02-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39814",0.00625,"2009-01-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39934",0.00625,"2009-05-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38018",0.006578947368421052,"2004-02-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38384",0.006578947368421052,"2005-02-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO38749",0.006578947368421052,"2006-02-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39052",0.006578947368421052,"2006-12-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39114",0.006578947368421052,"2007-02-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39326",0.006578947368421052,"2007-09-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39417",0.006578947368421052,"2007-12-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39845",0.006578947368421052,"2009-02-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO40118",0.006578947368421052,"2009-11-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO37926",0.006944444444444444,"2003-11-01"]
["LCLSRAT3","LCLS RATES","FTE_MO","RTDESC","FTE_MO39753",0.006944444444444444,"2008-11-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO37803",0.00625,"2003-07-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO37895",0.00625,"2003-10-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38047",0.00625,"2004-03-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38412",0.00625,"2005-03-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38565",0.00625,"2005-08-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38777",0.00625,"2006-03-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38930",0.00625,"2006-08-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39295",0.00625,"2007-08-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39356",0.00625,"2007-10-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39722",0.00625,"2008-10-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38078",0.0065340909090909095,"2004-04-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38139",0.0065340909090909095,"2004-06-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38200",0.0065340909090909095,"2004-08-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38504",0.0065340909090909095,"2005-06-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38838",0.0065340909090909095,"2006-05-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38869",0.0065340909090909095,"2006-06-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38991",0.0065340909090909095,"2006-10-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39142",0.0065340909090909095,"2007-03-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39203",0.0065340909090909095,"2007-05-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39539",0.0065340909090909095,"2008-04-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39630",0.0065340909090909095,"2008-07-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39873",0.0065340909090909095,"2009-03-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39904",0.0065340909090909095,"2009-04-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39965",0.0065340909090909095,"2009-06-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39995",0.0065340909090909095,"2009-07-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO40087",0.0065340909090909095,"2009-10-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO37560",0.006845238095238095,"2002-10-31"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO37834",0.006845238095238095,"2003-08-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO37865",0.006845238095238095,"2003-09-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO37956",0.006845238095238095,"2003-12-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38169",0.006845238095238095,"2004-07-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38231",0.006845238095238095,"2004-09-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38261",0.006845238095238095,"2004-10-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38443",0.006845238095238095,"2005-04-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38473",0.006845238095238095,"2005-05-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38596",0.006845238095238095,"2005-09-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38626",0.006845238095238095,"2005-10-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39083",0.006845238095238095,"2007-01-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39173",0.006845238095238095,"2007-04-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39234",0.006845238095238095,"2007-06-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39264",0.006845238095238095,"2007-07-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39448",0.006845238095238095,"2008-01-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39508",0.006845238095238095,"2008-03-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39569",0.006845238095238095,"2008-05-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39600",0.006845238095238095,"2008-06-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39661",0.006845238095238095,"2008-08-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39692",0.006845238095238095,"2008-09-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39783",0.006845238095238095,"2008-12-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO40026",0.006845238095238095,"2009-08-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO40056",0.006845238095238095,"2009-08-31"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO40148",0.006845238095238095,"2009-12-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO37500",0.0071875,"2002-09-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO37530",0.0071875,"2002-10-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO37987",0.0071875,"2004-01-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38108",0.0071875,"2004-05-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38292",0.0071875,"2004-11-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38322",0.0071875,"2004-12-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38353",0.0071875,"2005-01-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38534",0.0071875,"2005-07-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38657",0.0071875,"2005-11-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38687",0.0071875,"2005-12-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38718",0.0071875,"2006-01-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38808",0.0071875,"2006-04-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38899",0.0071875,"2006-07-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38961",0.0071875,"2006-09-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39022",0.0071875,"2006-11-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39387",0.0071875,"2007-11-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39479",0.0071875,"2008-02-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39814",0.0071875,"2009-01-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39934",0.0071875,"2009-05-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38018",0.00756578947368421,"2004-02-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38384",0.00756578947368421,"2005-02-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO38749",0.00756578947368421,"2006-02-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39052",0.00756578947368421,"2006-12-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39114",0.00756578947368421,"2007-02-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39326",0.00756578947368421,"2007-09-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39417",0.00756578947368421,"2007-12-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39845",0.00756578947368421,"2009-02-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO40118",0.00756578947368421,"2009-11-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO37926",0.00798611111111111,"2003-11-01"]
["LCLSRAT3","LCLS RATES","HEADS_MO","RTDESC","HEADS_MO39753",0.00798611111111111,"2008-11-01"]
["LCLSRAT3","LCLS RATES","LABOR","RTDESC","LABOR38231",0,"2004-09-01"]
["LCLSRAT3","LCLS RATES","LA_MSEG","RTDESC","LA_MSEG37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","LA_MSEG1","RTDESC","LA_MSEG138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","LA_MSEQ","RTDESC","LA_MSEQ37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","LA_MSEQ1","RTDESC","LA_MSEQ138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","LA_MSSC","RTDESC","LA_MSSC37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","LA_MSSC1","RTDESC","LA_MSSC138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","LA_MSXX","RTDESC","LA_MSXX37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","LA_MSXX1","RTDESC","LA_MSXX138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","LL_ADMN","RTDESC","LL_ADMN37895",134.15048076923077,"2003-10-01"]
["LCLSRAT3","LCLS RATES","LL_ADMN1","RTDESC","LL_ADMN138626",134.15048076923077,"2005-10-01"]
["LCLSRAT3","LCLS RATES","LL_AW1","RTDESC","LL_AW138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","LL_AWARD","RTDESC","LL_AWARD37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","LL_AWXX","RTDESC","LL_AWXX37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","LL_AWXX1","RTDESC","LL_AWXX138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","LL_CE","RTDESC","LL_CE37895",176.59423076923076,"2003-10-01"]
["LCLSRAT3","LCLS RATES","LL_CE1","RTDESC","LL_CE138626",176.59423076923076,"2005-10-01"]
["LCLSRAT3","LCLS RATES","LL_CP","RTDESC","LL_CP37895",189.60865384615386,"2003-10-01"]
["LCLSRAT3","LCLS RATES","LL_CP1","RTDESC","LL_CP138626",189.60865384615386,"2005-10-01"]
["LCLSRAT3","LCLS RATES","LL_CT","RTDESC","LL_CT37895",137.21778846153848,"2003-10-01"]
["LCLSRAT3","LCLS RATES","LL_CT1","RTDESC","LL_CT138626",137.21778846153848,"2005-10-01"]
["LCLSRAT3","LCLS RATES","LL_EE","RTDESC","LL_EE37895",176.59423076923076,"2003-10-01"]
["LCLSRAT3","LCLS RATES","LL_EE1","RTDESC","LL_EE138626",176.59423076923076,"2005-10-01"]
["LCLSRAT3","LCLS RATES","LL_LABOR","RTDESC","LL_LABOR37865",0,"2003-09-01"]
["LCLSRAT3","LCLS RATES","LL_MDD","RTDESC","LL_MDD37895",162.0105769230769,"2003-10-01"]
["LCLSRAT3","LCLS RATES","LL_MDD1","RTDESC","LL_MDD138626",162.0105769230769,"2005-10-01"]
["LCLSRAT3","LCLS RATES","LL_ME","RTDESC","LL_ME37895",176.59423076923076,"2003-10-01"]
["LCLSRAT3","LCLS RATES","LL_ME1","RTDESC","LL_ME138626",176.59423076923076,"2005-10-01"]
["LCLSRAT3","LCLS RATES","LL_MFAT","RTDESC","LL_MFAT37895",137.21778846153848,"2003-10-01"]
["LCLSRAT3","LCLS RATES","LL_MFAT1","RTDESC","LL_MFAT138626",137.21778846153848,"2005-10-01"]
["LCLSRAT3","LCLS RATES","LL_MSCS","RTDESC","LL_MSCS37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","LL_MSCS1","RTDESC","LL_MSCS138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","LL_MSEG","RTDESC","LL_MSEG37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","LL_MSEG1","RTDESC","LL_MSEG138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","LL_MSEQ","RTDESC","LL_MSEQ37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","LL_MSEQ1","RTDESC","LL_MSEQ138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","LL_MSPS","RTDESC","LL_MSPS37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","LL_MSPS1","RTDESC","LL_MSPS138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","LL_MSSC","RTDESC","LL_MSSC37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","LL_MSSC1","RTDESC","LL_MSSC138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","LL_MSTR","RTDESC","LL_MSTR37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","LL_MSTR1","RTDESC","LL_MSTR138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","LL_MSXX","RTDESC","LL_MSXX37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","LL_MSXX1","RTDESC","LL_MSXX138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","LL_MTRL","RTDESC","LL_MTRL37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","LL_MTRL1","RTDESC","LL_MTRL138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","LL_OH","RTDESC","LL_OH37895",0.19,"2003-10-01"]
["LCLSRAT3","LCLS RATES","LL_OH2","RTDESC","LL_OH238930",0.11,"2006-08-01"]
["LCLSRAT3","LCLS RATES","LL_PCCA","RTDESC","LL_PCCA37895",158.32548076923078,"2003-10-01"]
["LCLSRAT3","LCLS RATES","LL_PCCA1","RTDESC","LL_PCCA138626",158.32548076923078,"2005-10-01"]
["LCLSRAT3","LCLS RATES","LL_PHS","RTDESC","LL_PHS37895",188.69326923076923,"2003-10-01"]
["LCLSRAT3","LCLS RATES","LL_PHS1","RTDESC","LL_PHS138626",188.69326923076923,"2005-10-01"]
["LCLSRAT3","LCLS RATES","LL_PHSS","RTDESC","LL_PHSS37895",208.3653846153846,"2003-10-01"]
["LCLSRAT3","LCLS RATES","LL_PHSS1","RTDESC","LL_PHSS138626",208.3653846153846,"2005-10-01"]
["LCLSRAT3","LCLS RATES","LL_PRC","RTDESC","LL_PRC37895",162.0105769230769,"2003-10-01"]
["LCLSRAT3","LCLS RATES","LL_PRC1","RTDESC","LL_PRC138626",162.0105769230769,"2005-10-01"]
["LCLSRAT3","LCLS RATES","LL_PRE","RTDESC","LL_PRE37895",176.59423076923076,"2003-10-01"]
["LCLSRAT3","LCLS RATES","LL_PRE1","RTDESC","LL_PRE138626",176.59423076923076,"2005-10-01"]
["LCLSRAT3","LCLS RATES","LL_SEE","RTDESC","LL_SEE37895",176.59423076923076,"2003-10-01"]
["LCLSRAT3","LCLS RATES","LL_SEE1","RTDESC","LL_SEE138626",176.59423076923076,"2005-10-01"]
["LCLSRAT3","LCLS RATES","NON_LABOR","RTDESC","NON_LABOR38231",0,"2004-09-01"]
["LCLSRAT3","LCLS RATES","SA_GCFX1","RTDESC","SA_GCFX138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SA_GCSS","RTDESC","SA_GCSS38625",1,"2005-09-30"]
["LCLSRAT3","LCLS RATES","SA_GCSS1","RTDESC","SA_GCSS138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SA_GCSX","RTDESC","SA_GCSX38625",1,"2005-09-30"]
["LCLSRAT3","LCLS RATES","SA_GCSX1","RTDESC","SA_GCSX138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SA_MSEG","RTDESC","SA_MSEG37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SA_MSEG1","RTDESC","SA_MSEG138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SA_MSEQ","RTDESC","SA_MSEQ37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SA_MSEQ1","RTDESC","SA_MSEQ138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SA_MSPF","RTDESC","SA_MSPF37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SA_MSPF1","RTDESC","SA_MSPF138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SA_MSPS","RTDESC","SA_MSPS37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SA_MSPS1","RTDESC","SA_MSPS138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SA_MSPX","RTDESC","SA_MSPX37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SA_MSPX1","RTDESC","SA_MSPX138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SA_MSPY","RTDESC","SA_MSPY37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SA_MSPY1","RTDESC","SA_MSPY138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SA_MSSC","RTDESC","SA_MSSC37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SA_MSSC1","RTDESC","SA_MSSC138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SA_MSSF","RTDESC","SA_MSSF37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SA_MSSF1","RTDESC","SA_MSSF138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SA_MSSY","RTDESC","SA_MSSY37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SA_MSSY1","RTDESC","SA_MSSY138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SA_MSXX","RTDESC","SA_MSXX37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SA_MSXX1","RTDESC","SA_MSXX138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_ADMN","RTDESC","SL_ADMN37895",30.1731,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_ADMN1","RTDESC","SL_ADMN138626",30.1731,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_AW1","RTDESC","SL_AW138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_AWARD","RTDESC","SL_AWARD37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_AWFX","RTDESC","SL_AWFX37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_AWFX1","RTDESC","SL_AWFX138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_AWFY","RTDESC","SL_AWFY37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_AWFY1","RTDESC","SL_AWFY138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_AWGC","RTDESC","SL_AWGC38625",1,"2005-09-30"]
["LCLSRAT3","LCLS RATES","SL_AWGC1","RTDESC","SL_AWGC138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_AWGX","RTDESC","SL_AWGX38625",1,"2005-09-30"]
["LCLSRAT3","LCLS RATES","SL_AWGX1","RTDESC","SL_AWGX138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_AWXX","RTDESC","SL_AWXX37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_AWXX1","RTDESC","SL_AWXX138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_CCA","RTDESC","SL_CCA37895",33.86,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_CCA1","RTDESC","SL_CCA138626",33.86,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_CE","RTDESC","SL_CE37895",58.14,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_CE1","RTDESC","SL_CE138626",58.14,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_CP","RTDESC","SL_CP37895",47.01,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_CP1","RTDESC","SL_CP138626",42.39,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_CPM","RTDESC","SL_CPM37895",30.93,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_CPM1","RTDESC","SL_CPM138626",30.93,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_CRA","RTDESC","SL_CRA37895",24.14,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_CRA1","RTDESC","SL_CRA138626",27.19,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_CRM","RTDESC","SL_CRM37895",30.93,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_CRM1","RTDESC","SL_CRM138626",30.93,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_CT","RTDESC","SL_CT37895",31.83,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_CT1","RTDESC","SL_CT138626",31.83,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_EE","RTDESC","SL_EE37895",58.14,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_EE1","RTDESC","SL_EE138626",47.95,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_FA","RTDESC","SL_FA37895",40.7,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_FA","RTDESC","SL_FA38687",45.37,"2005-12-01"]
["LCLSRAT3","LCLS RATES","SL_FA1","RTDESC","SL_FA138626",46.24,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_FRING1","RTDESC","SL_FRING137904",1,"2003-10-10"]
["LCLSRAT3","LCLS RATES","SL_FRNG1","RTDESC","SL_FRNG138626",0.305,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_FRNGE","RTDESC","SL_FRNGE37895",0.29,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_FRNGX","RTDESC","SL_FRNGX37895",0,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_GCFX1","RTDESC","SL_GCFX138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_GCSS","RTDESC","SL_GCSS38625",1,"2005-09-30"]
["LCLSRAT3","LCLS RATES","SL_GCSS1","RTDESC","SL_GCSS138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_GCSX","RTDESC","SL_GCSX38625",1,"2005-09-30"]
["LCLSRAT3","LCLS RATES","SL_GCSX1","RTDESC","SL_GCSX138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS37803",0.00624687656171914,"2003-07-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS37895",0.00624687656171914,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS37956",0.00624687656171914,"2003-12-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38047",0.00624687656171914,"2004-03-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38412",0.00624687656171914,"2005-03-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38565",0.00624687656171914,"2005-08-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38777",0.00624687656171914,"2006-03-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38930",0.00624687656171914,"2006-08-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39295",0.00624687656171914,"2007-08-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39356",0.00624687656171914,"2007-10-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39722",0.00624687656171914,"2008-10-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39995",0.00624687656171914,"2009-07-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS40056",0.00624687656171914,"2009-08-31"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS37712",0.006530825496342738,"2003-04-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS37742",0.006530825496342738,"2003-05-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS37865",0.006530825496342738,"2003-09-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38078",0.006530825496342738,"2004-04-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38139",0.006530825496342738,"2004-06-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38200",0.006530825496342738,"2004-08-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38504",0.006530825496342738,"2005-06-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38838",0.006530825496342738,"2006-05-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38869",0.006530825496342738,"2006-06-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38991",0.006530825496342738,"2006-10-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39142",0.006530825496342738,"2007-03-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39203",0.006530825496342738,"2007-05-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39539",0.006530825496342738,"2008-04-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39630",0.006530825496342738,"2008-07-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39783",0.006530825496342738,"2008-12-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39873",0.006530825496342738,"2009-03-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39904",0.006530825496342738,"2009-04-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39965",0.006530825496342738,"2009-06-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS40087",0.006530825496342738,"2009-10-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS40148",0.006530825496342738,"2009-12-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS37681",0.006841817186644773,"2003-03-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS37773",0.006841817186644773,"2003-06-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS37834",0.006841817186644773,"2003-08-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38169",0.006841817186644773,"2004-07-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38231",0.006841817186644773,"2004-09-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38261",0.006841817186644773,"2004-10-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38443",0.006841817186644773,"2005-04-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38473",0.006841817186644773,"2005-05-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38596",0.006841817186644773,"2005-09-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38626",0.006841817186644773,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38687",0.006841817186644773,"2005-12-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39083",0.006841817186644773,"2007-01-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39173",0.006841817186644773,"2007-04-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39234",0.006841817186644773,"2007-06-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39264",0.006841817186644773,"2007-07-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39448",0.006841817186644773,"2008-01-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39508",0.006841817186644773,"2008-03-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39569",0.006841817186644773,"2008-05-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39600",0.006841817186644773,"2008-06-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39661",0.006841817186644773,"2008-08-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39692",0.006841817186644773,"2008-09-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39814",0.006841817186644773,"2009-01-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39934",0.006841817186644773,"2009-05-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS40118",0.006841817186644773,"2009-11-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS37653",0.007183908045977012,"2003-02-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS37926",0.007183908045977012,"2003-11-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS37987",0.007183908045977012,"2004-01-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38108",0.007183908045977012,"2004-05-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38292",0.007183908045977012,"2004-11-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38322",0.007183908045977012,"2004-12-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38353",0.007183908045977012,"2005-01-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38534",0.007183908045977012,"2005-07-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38657",0.007183908045977012,"2005-11-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38718",0.007183908045977012,"2006-01-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38808",0.007183908045977012,"2006-04-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38899",0.007183908045977012,"2006-07-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38961",0.007183908045977012,"2006-09-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39022",0.007183908045977012,"2006-11-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39052",0.007183908045977012,"2006-12-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39387",0.007183908045977012,"2007-11-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39417",0.007183908045977012,"2007-12-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39479",0.007183908045977012,"2008-02-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39845",0.007183908045977012,"2009-02-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS40026",0.007183908045977012,"2009-08-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38018",0.007562008469449486,"2004-02-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38384",0.007562008469449486,"2005-02-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS38749",0.007562008469449486,"2006-02-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39114",0.007562008469449486,"2007-02-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39326",0.007562008469449486,"2007-09-01"]
["LCLSRAT3","LCLS RATES","SL_HEADS","RTDESC","SL_HEADS39753",0.007982120051085569,"2008-11-01"]
["LCLSRAT3","LCLS RATES","SL_IPM","RTDESC","SL_IPM37895",54.62,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_IPM1","RTDESC","SL_IPM138626",54.62,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_KCA","RTDESC","SL_KCA37895",33.86,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_KCA1","RTDESC","SL_KCA138626",33.86,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_KE","RTDESC","SL_KE37895",58.14,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_KE1","RTDESC","SL_KE138626",58.14,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_KT","RTDESC","SL_KT37895",31.83,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_KT1","RTDESC","SL_KT138626",31.83,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_LEAV1","RTDESC","SL_LEAV137895",0,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_LEAV2","RTDESC","SL_LEAV238626",0.21,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_LEAVE","RTDESC","SL_LEAVE37895",0.215,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_LEAVX","RTDESC","SL_LEAVX37895",0,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_LPM","RTDESC","SL_LPM37895",54.62,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_LPM1","RTDESC","SL_LPM138626",54.62,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_MDD","RTDESC","SL_MDD37895",32.42,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_MDD1","RTDESC","SL_MDD138626",43.07,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_ME","RTDESC","SL_ME37895",54.62,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_ME1","RTDESC","SL_ME138626",51.37,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_MES","RTDESC","SL_MES37895",46.68,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_MES1","RTDESC","SL_MES138626",41.3,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_MFAT","RTDESC","SL_MFAT37895",66.3,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_MFAT1","RTDESC","SL_MFAT138626",70,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_MFMS","RTDESC","SL_MFMS37895",81.3,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_MFMS1","RTDESC","SL_MFMS138626",89.59,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_MFPC","RTDESC","SL_MFPC37895",129.8,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_MFPC1","RTDESC","SL_MFPC138626",140.65,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_MSCS","RTDESC","SL_MSCS37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_MSCS1","RTDESC","SL_MSCS138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_MSEG","RTDESC","SL_MSEG37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_MSEG1","RTDESC","SL_MSEG138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_MSEQ","RTDESC","SL_MSEQ37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_MSEQ1","RTDESC","SL_MSEQ138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_MSPF","RTDESC","SL_MSPF37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_MSPF1","RTDESC","SL_MSPF138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_MSPS","RTDESC","SL_MSPS37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_MSPS1","RTDESC","SL_MSPS138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_MSPX","RTDESC","SL_MSPX37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_MSPX1","RTDESC","SL_MSPX138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_MSPY","RTDESC","SL_MSPY37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_MSPY1","RTDESC","SL_MSPY138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_MSSC","RTDESC","SL_MSSC37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_MSSC1","RTDESC","SL_MSSC138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_MSSF","RTDESC","SL_MSSF37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_MSSF1","RTDESC","SL_MSSF138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_MSSY","RTDESC","SL_MSSY37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_MSSY1","RTDESC","SL_MSSY138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_MSTR","RTDESC","SL_MSTR37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_MSTR1","RTDESC","SL_MSTR138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_MSXX","RTDESC","SL_MSXX37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_MSXX1","RTDESC","SL_MSXX138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_MTRL","RTDESC","SL_MTRL37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_MTRL1","RTDESC","SL_MTRL138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_MVE","RTDESC","SL_MVE37895",54.62,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_MVE1","RTDESC","SL_MVE138626",54.62,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_OE","RTDESC","SL_OE37895",58.14,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_OE1","RTDESC","SL_OE138626",58.14,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_OH1","RTDESC","SL_OH137895",0.2,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_OH2","RTDESC","SL_OH237895",0.06,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_OH3","RTDESC","SL_OH337895",0.36,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_OH4","RTDESC","SL_OH437895",0.068,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_OHN","RTDESC","SL_OHN37904",0,"2003-10-10"]
["LCLSRAT3","LCLS RATES","SL_OHN1","RTDESC","SL_OHN137895",0.2,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_OHN2","RTDESC","SL_OHN237895",0.048,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_OHN3","RTDESC","SL_OHN337895",0.38,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_OHN4","RTDESC","SL_OHN437895",0.0552,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_OT","RTDESC","SL_OT37895",31.83,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_OT1","RTDESC","SL_OT138626",31.83,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_PCCA","RTDESC","SL_PCCA37895",33.86,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_PCCA1","RTDESC","SL_PCCA138626",33.86,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_PCE","RTDESC","SL_PCE37895",58.14,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_PCE1","RTDESC","SL_PCE138626",58.14,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_PCEF","RTDESC","SL_PCEF37895",31.83,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_PCEF1","RTDESC","SL_PCEF138626",31.83,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_PCT","RTDESC","SL_PCT37895",31.83,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_PCT1","RTDESC","SL_PCT138626",31.83,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_PEX","RTDESC","SL_PEX37895",40.7,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_PEX1","RTDESC","SL_PEX138626",40.7,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_PHH","RTDESC","SL_PHH37895",45.68,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_PHH1","RTDESC","SL_PHH138626",49.4,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_PHPD","RTDESC","SL_PHPD37895",36.17,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_PHPD1","RTDESC","SL_PHPD138626",36.17,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_PHPU","RTDESC","SL_PHPU38626",63.33,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_PHS","RTDESC","SL_PHS37895",37.62,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_PHS1","RTDESC","SL_PHS138626",37.62,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_PHSS","RTDESC","SL_PHSS37895",47.88,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_PHSS1","RTDESC","SL_PHSS138626",47.88,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_PM","RTDESC","SL_PM37895",63.8,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_PM","RTDESC","SL_PM38687",83.63,"2005-12-01"]
["LCLSRAT3","LCLS RATES","SL_PM1","RTDESC","SL_PM138626",83.63,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_POWB","RTDESC","SL_POWB37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_POWB1","RTDESC","SL_POWB138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_QAO","RTDESC","SL_QAO37895",54.62,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_QAO1","RTDESC","SL_QAO138626",35.53,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_SEE","RTDESC","SL_SEE37895",54.62,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_SEE1","RTDESC","SL_SEE138626",54.62,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_SEEM","RTDESC","SL_SEEM37895",54.62,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_SEEM1","RTDESC","SL_SEEM138626",54.62,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_SEL","RTDESC","SL_SEL37895",38,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_SEL1","RTDESC","SL_SEL138626",38,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_SEPM","RTDESC","SL_SEPM37895",32.28,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_SEPM1","RTDESC","SL_SEPM138626",32.28,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_SRA","RTDESC","SL_SRA37895",20.83,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_SRA1","RTDESC","SL_SRA138626",20.83,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_STUP","RTDESC","SL_STUP37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_STUP1","RTDESC","SL_STUP138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_TMUC","RTDESC","SL_TMUC37895",60.55,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_TMUC1","RTDESC","SL_TMUC138626",60.55,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_TMUE","RTDESC","SL_TMUE37895",77.99,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_TMUE1","RTDESC","SL_TMUE138626",77.99,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_TMUI","RTDESC","SL_TMUI37895",61.62,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_TMUI1","RTDESC","SL_TMUI138626",61.62,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_TMUO","RTDESC","SL_TMUO37895",64.45,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_TMUO1","RTDESC","SL_TMUO138626",64.45,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_TMUP","RTDESC","SL_TMUP37895",74.69,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_TMUP1","RTDESC","SL_TMUP138626",74.69,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_TMUW","RTDESC","SL_TMUW37895",61.62,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_TMUW1","RTDESC","SL_TMUW138626",61.62,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_TSM","RTDESC","SL_TSM37895",54.62,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_TSM1","RTDESC","SL_TSM138626",54.62,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_UPGR","RTDESC","SL_UPGR37895",1,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_UPGR1","RTDESC","SL_UPGR138626",1,"2005-10-01"]
["LCLSRAT3","LCLS RATES","SL_UTR","RTDESC","SL_UTR37895",54.62,"2003-10-01"]
["LCLSRAT3","LCLS RATES","SL_UTR1","RTDESC","SL_UTR138626",54.62,"2005-10-01"]
["LCLSRAT3","LCLS RATES","TRAVEL","RTDESC","TRAVEL38231",0,"2004-09-01"]

{"sheet":"opcclc","index":1,"n_rows":1669,"n_cols":14,"rows_kept":1669,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["OPC3CLC ","OPC3CLC ","OPC3CLC ","OPC3CLC ","OPC3CLC ","OPC3CLC ","OPC3CLC ","OPC3CLC ","OPC3CLC ","OPC3CLC ","OPC3CLC ","OPC3CLC ","OPC3CLC ","OPC3CLC "]
["AA_MSEG","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AA_MSEG","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AA_MSEG","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AA_MSEG","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AA_MSEG","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AA_MSEG","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AA_MSEG1","ESC1","AN_CS6","AN_GA2",null,"2005-10-01","ESC138626",null,1,0,0.064,0.027,null,1.092728]
["AA_MSEG1","ESC1","AN_CS6","AN_GA2",null,"2006-10-01","ESC138991",null,1,0.026,0.064,0.027,null,1.1211389280000001]
["AA_MSEG1","ESC1","AN_CS6","AN_GA2",null,"2007-10-01","ESC139356",null,1,0.052676,0.064,0.027,null,1.150288540128]
["AA_MSEG1","ESC1","AN_CS6","AN_GA2",null,"2008-10-01","ESC139722",null,1,0.08004558,0.064,0.027,null,1.1801960465422399]
["AA_MSEQ","ESC","AN_OH4",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AA_MSEQ","ESC","AN_OH4",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AA_MSEQ","ESC","AN_OH4",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AA_MSEQ","ESC","AN_OH4",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AA_MSEQ","ESC","AN_OH4",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AA_MSEQ","ESC","AN_OH4",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AA_MSEQ1","ESC1","AN_CS6","AN_GA2",null,"2005-10-01","ESC138626",null,1,0,0.064,0.027,null,1.092728]
["AA_MSEQ1","ESC1","AN_CS6","AN_GA2",null,"2006-10-01","ESC138991",null,1,0.026,0.064,0.027,null,1.1211389280000001]
["AA_MSEQ1","ESC1","AN_CS6","AN_GA2",null,"2007-10-01","ESC139356",null,1,0.052676,0.064,0.027,null,1.150288540128]
["AA_MSEQ1","ESC1","AN_CS6","AN_GA2",null,"2008-10-01","ESC139722",null,1,0.08004558,0.064,0.027,null,1.1801960465422399]
["AA_MSPS","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,null,0,0,null,null,0]
["AA_MSPS","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,null,0.029,0,null,null,0]
["AA_MSPS","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,null,0.057812,0,null,null,0]
["AA_MSPS","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,null,0.085315,0,null,null,0]
["AA_MSPS","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,null,0.113533,0,null,null,0]
["AA_MSPS","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,null,0.142485,0,null,null,0]
["AA_MSSC","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AA_MSSC","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AA_MSSC","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AA_MSSC","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AA_MSSC","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AA_MSSC","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AA_MSSC1","ESC1","AN_CS6","AN_GA2",null,"2005-10-01","ESC138626",null,1,0,0.064,0.027,null,1.092728]
["AA_MSSC1","ESC1","AN_CS6","AN_GA2",null,"2006-10-01","ESC138991",null,1,0.026,0.064,0.027,null,1.1211389280000001]
["AA_MSSC1","ESC1","AN_CS6","AN_GA2",null,"2007-10-01","ESC139356",null,1,0.052676,0.064,0.027,null,1.150288540128]
["AA_MSSC1","ESC1","AN_CS6","AN_GA2",null,"2008-10-01","ESC139722",null,1,0.08004558,0.064,0.027,null,1.1801960465422399]
["AA_MSSF","AN_OH3",{"$nulls":4},"AN_OH3",{"$nulls":6},1]
["AA_MSXX","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["AA_MSXX","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["AA_MSXX","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["AA_MSXX","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["AA_MSXX","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["AA_MSXX","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["ANL_LABOR","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,null,0,0.292,0.027,0,0]
["ANL_LABOR","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,null,0.026,0.292,0.027,0,0]
["ANL_LABOR","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,null,0.052676,0.292,0.027,0,0]
["ANL_LABOR","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,null,0.08004558,0.292,0.027,0,0]
["ANL_NON-LABOR","ESC1","AN_CS6","AN_GA2",null,"2005-10-01","ESC138626",null,null,0,0.064,0.027,null,0]
["ANL_NON-LABOR","ESC1","AN_CS6","AN_GA2",null,"2006-10-01","ESC138991",null,null,0.026,0.064,0.027,null,0]
["ANL_NON-LABOR","ESC1","AN_CS6","AN_GA2",null,"2007-10-01","ESC139356",null,null,0.052676,0.064,0.027,null,0]
["ANL_NON-LABOR","ESC1","AN_CS6","AN_GA2",null,"2008-10-01","ESC139722",null,null,0.08004558,0.064,0.027,null,0]
["ANL_SHOPS","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,null,0,0.292,0.027,0,0]
["ANL_SHOPS","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,null,0.026,0.292,0.027,0,0]
["ANL_SHOPS","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,null,0.052676,0.292,0.027,0,0]
["ANL_SHOPS","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,null,0.08004558,0.292,0.027,0,0]
["ANL_TRAVEL","ESC1","AN_OH1",null,null,"2005-10-01","ESC138626",null,null,0,0.3224,null,null,0]
["ANL_TRAVEL","ESC1","AN_OH1",null,null,"2006-10-01","ESC138991",null,null,0.026,0.3224,null,null,0]
["ANL_TRAVEL","ESC1","AN_OH1",null,null,"2007-10-01","ESC139356",null,null,0.052676,0.3224,null,null,0]
["ANL_TRAVEL","ESC1","AN_OH1",null,null,"2008-10-01","ESC139722",null,null,0.08004558,0.3224,null,null,0]
["AN_ADMN","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,63.24,0,0.3224,null,null,83.62857600000001]
["AN_ADMN","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,63.24,0.029,0.3224,null,null,86.053804704]
["AN_ADMN","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,63.24,0.057812,0.3224,null,null,88.463311235712]
["AN_ADMN","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,63.24,0.085315,0.3224,null,null,90.76334796144]
["AN_ADMN","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,63.24,0.113533,0.3224,null,null,93.12317911900799]
["AN_ADMN","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,63.24,0.142485,0.3224,null,null,95.54439365136]
["AN_ADMN1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.292,0.027,0,110.80808284]
["AN_ADMN1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.292,0.027,0,113.68909299384]
["AN_ADMN1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.292,0.027,0,116.64500941167984]
["AN_ADMN1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.292,0.027,0,119.67778009961584]
["AN_AW1","ESC1","AN_CS6","AN_GA2",null,"2005-10-01","ESC138626",null,1,0,0.064,0.027,null,1.092728]
["AN_AW1","ESC1","AN_CS6","AN_GA2",null,"2006-10-01","ESC138991",null,1,0.026,0.064,0.027,null,1.1211389280000001]
["AN_AW1","ESC1","AN_CS6","AN_GA2",null,"2007-10-01","ESC139356",null,1,0.052676,0.064,0.027,null,1.150288540128]
["AN_AW1","ESC1","AN_CS6","AN_GA2",null,"2008-10-01","ESC139722",null,1,0.08004558,0.064,0.027,null,1.1801960465422399]
["AN_AWARD","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AN_AWARD","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AN_AWARD","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AN_AWARD","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AN_AWARD","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AN_AWARD","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AN_AWFX","AN_OH3",{"$nulls":4},"AN_OH3",{"$nulls":6},0]
["AN_AWXX","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["AN_AWXX","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["AN_AWXX","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["AN_AWXX","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["AN_AWXX","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["AN_AWXX","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["AN_CCA","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,67.43,0,0.3224,null,null,89.16943200000001]
["AN_CCA","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,67.43,0.029,0.3224,null,null,91.75534552799999]
["AN_CCA","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,67.43,0.057812,0.3224,null,null,94.32449520278401]
["AN_CCA","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,67.43,0.085315,0.3224,null,null,96.77692209108002]
["AN_CCA","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,67.43,0.113533,0.3224,null,null,99.293105123256]
["AN_CCA","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,67.43,0.142485,0.3224,null,null,101.87473851852002]
["AN_CCA1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.292,0.027,0,110.80808284]
["AN_CCA1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.292,0.027,0,113.68909299384]
["AN_CCA1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.292,0.027,0,116.64500941167984]
["AN_CCA1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.292,0.027,0,119.67778009961584]
["AN_CE","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,67.43,0,0.3224,null,null,89.16943200000001]
["AN_CE","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,67.43,0.029,0.3224,null,null,91.75534552799999]
["AN_CE","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,67.43,0.057812,0.3224,null,null,94.32449520278401]
["AN_CE","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,67.43,0.085315,0.3224,null,null,96.77692209108002]
["AN_CE","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,67.43,0.113533,0.3224,null,null,99.293105123256]
["AN_CE","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,67.43,0.142485,0.3224,null,null,101.87473851852002]
["AN_CE1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.292,0.027,0,110.80808284]
["AN_CE1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.292,0.027,0,113.68909299384]
["AN_CE1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.292,0.027,0,116.64500941167984]
["AN_CE1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.292,0.027,0,119.67778009961584]
["AN_CP","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,67.43,0,0.3224,null,null,89.16943200000001]
["AN_CP","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,67.43,0.029,0.3224,null,null,91.75534552799999]
["AN_CP","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,67.43,0.057812,0.3224,null,null,94.32449520278401]
["AN_CP","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,67.43,0.085315,0.3224,null,null,96.77692209108002]
["AN_CP","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,67.43,0.113533,0.3224,null,null,99.293105123256]
["AN_CP","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,67.43,0.142485,0.3224,null,null,101.87473851852002]
["AN_CP1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.292,0.027,0,110.80808284]
["AN_CP1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.292,0.027,0,113.68909299384]
["AN_CP1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.292,0.027,0,116.64500941167984]
["AN_CP1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.292,0.027,0,119.67778009961584]
["AN_CT","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,42.99,0,0.3224,null,null,56.849976000000005]
["AN_CT","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,42.99,0.029,0.3224,null,null,58.498625303999994]
["AN_CT","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,42.99,0.057812,0.3224,null,null,60.136586812512]
["AN_CT","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,42.99,0.085315,0.3224,null,null,61.70013170244001]
["AN_CT","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,42.99,0.113533,0.3224,null,null,63.30432432520799]
["AN_CT","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,42.99,0.142485,0.3224,null,null,64.95024483036]
["AN_CT1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,49.03,0,0.292,0.027,0,65.05712252]
["AN_CT1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,49.03,0.026,0.292,0.027,0,66.74860770552]
["AN_CT1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,49.03,0.052676,0.292,0.027,0,68.48407150586351]
["AN_CT1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,49.03,0.08004558,0.292,0.027,0,70.26465762524445]
["AN_EE","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,67.43,0,0.3224,null,null,89.16943200000001]
["AN_EE","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,67.43,0.029,0.3224,null,null,91.75534552799999]
["AN_EE","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,67.43,0.057812,0.3224,null,null,94.32449520278401]
["AN_EE","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,67.43,0.085315,0.3224,null,null,96.77692209108002]
["AN_EE","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,67.43,0.113533,0.3224,null,null,99.293105123256]
["AN_EE","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,67.43,0.142485,0.3224,null,null,101.87473851852002]
["AN_EE1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.292,0.027,0,110.80808284]
["AN_EE1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.292,0.027,0,113.68909299384]
["AN_EE1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.292,0.027,0,116.64500941167984]
["AN_EE1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.292,0.027,0,119.67778009961584]
["AN_MDD","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,42.99,0,0.3224,null,null,56.849976000000005]
["AN_MDD","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,42.99,0.029,0.3224,null,null,58.498625303999994]
["AN_MDD","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,42.99,0.057812,0.3224,null,null,60.136586812512]
["AN_MDD","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,42.99,0.085315,0.3224,null,null,61.70013170244001]
["AN_MDD","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,42.99,0.113533,0.3224,null,null,63.30432432520799]
["AN_MDD","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,42.99,0.142485,0.3224,null,null,64.95024483036]
["AN_MDD1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,49.03,0,0.292,0.027,0,65.05712252]
["AN_MDD1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,49.03,0.026,0.292,0.027,0,66.74860770552]
["AN_MDD1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,49.03,0.052676,0.292,0.027,0,68.48407150586351]
["AN_MDD1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,49.03,0.08004558,0.292,0.027,0,70.26465762524445]
["AN_ME","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,63.24,0,0.3224,null,null,83.62857600000001]
["AN_ME","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,63.24,0.029,0.3224,null,null,86.053804704]
["AN_ME","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,63.24,0.057812,0.3224,null,null,88.463311235712]
["AN_ME","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,63.24,0.085315,0.3224,null,null,90.76334796144]
["AN_ME","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,63.24,0.113533,0.3224,null,null,93.12317911900799]
["AN_ME","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,63.24,0.142485,0.3224,null,null,95.54439365136]
["AN_ME1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.292,0.027,0,110.80808284]
["AN_ME1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.292,0.027,0,113.68909299384]
["AN_ME1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.292,0.027,0,116.64500941167984]
["AN_ME1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.292,0.027,0,119.67778009961584]
["AN_MES","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,67.43,0,0.3224,null,null,89.16943200000001]
["AN_MES","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,67.43,0.029,0.3224,null,null,91.75534552799999]
["AN_MES","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,67.43,0.057812,0.3224,null,null,94.32449520278401]
["AN_MES","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,67.43,0.085315,0.3224,null,null,96.77692209108002]
["AN_MES","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,67.43,0.113533,0.3224,null,null,99.293105123256]
["AN_MES","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,67.43,0.142485,0.3224,null,null,101.87473851852002]
["AN_MES1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.292,0.027,0,110.80808284]
["AN_MES1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.292,0.027,0,113.68909299384]
["AN_MES1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.292,0.027,0,116.64500941167984]
["AN_MES1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.292,0.027,0,119.67778009961584]
["AN_MFAT","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,42.51,0,0.2598,null,null,53.554097999999996]
["AN_MFAT","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,42.51,0.029,0.2598,null,null,55.10716684199999]
["AN_MFAT","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,42.51,0.057812,0.2598,null,null,56.650167513575994]
["AN_MFAT","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,42.51,0.085315,0.2598,null,null,58.12306587087]
["AN_MFAT","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,42.51,0.113533,0.2598,null,null,59.634255408234]
["AN_MFAT","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,42.51,0.142485,0.2598,null,null,61.18475365353]
["AN_MFAT1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,49.03,0,0.292,0.027,0,65.05712252]
["AN_MFAT1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,49.03,0.026,0.292,0.027,0,66.74860770552]
["AN_MFAT1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,49.03,0.052676,0.292,0.027,0,68.48407150586351]
["AN_MFAT1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,49.03,0.08004558,0.292,0.027,0,70.26465762524445]
["AN_MFMS","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,53.97,0,0.2598,null,null,67.991406]
["AN_MFMS","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,53.97,0.029,0.2598,null,null,69.963156774]
["AN_MFMS","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,53.97,0.057812,0.2598,null,null,71.92212516367199]
["AN_MFMS","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,53.97,0.085315,0.2598,null,null,73.79209280289001]
["AN_MFMS","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,53.97,0.113533,0.2598,null,null,75.71067429739799]
["AN_MFMS","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,53.97,0.142485,0.2598,null,null,77.67916148391001]
["AN_MFMS1","ESC1","AN_CS5","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,81,0,0.196,0.027,0,99.49165199999999]
["AN_MFMS1","ESC1","AN_CS5","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,81,0.026,0.196,0.027,0,102.078434952]
["AN_MFMS1","ESC1","AN_CS5","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,81,0.052676,0.196,0.027,0,104.73247426075199]
["AN_MFMS1","ESC1","AN_CS5","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,81,0.08004558,0.196,0.027,0,107.45551898949813]
["AN_MFPC","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.2598,null,null,0]
["AN_MFPC","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.2598,null,null,0]
["AN_MFPC","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.2598,null,null,0]
["AN_MFPC","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.2598,null,null,0]
["AN_MFPC","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.2598,null,null,0]
["AN_MFPC","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.2598,null,null,0]
["AN_MSCS","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AN_MSCS","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AN_MSCS","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AN_MSCS","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AN_MSCS","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AN_MSCS","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AN_MSCS1","ESC1","AN_CS6","AN_GA2",null,"2005-10-01","ESC138626",null,1,0,0.064,0.027,null,1.092728]
["AN_MSCS1","ESC1","AN_CS6","AN_GA2",null,"2006-10-01","ESC138991",null,1,0.026,0.064,0.027,null,1.1211389280000001]
["AN_MSCS1","ESC1","AN_CS6","AN_GA2",null,"2007-10-01","ESC139356",null,1,0.052676,0.064,0.027,null,1.150288540128]
["AN_MSCS1","ESC1","AN_CS6","AN_GA2",null,"2008-10-01","ESC139722",null,1,0.08004558,0.064,0.027,null,1.1801960465422399]
["AN_MSEG","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AN_MSEG","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AN_MSEG","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AN_MSEG","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AN_MSEG","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AN_MSEG","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AN_MSEG1","ESC1","AN_CS6","AN_GA2",null,"2005-10-01","ESC138626",null,1,0,0.064,0.027,null,1.092728]
["AN_MSEG1","ESC1","AN_CS6","AN_GA2",null,"2006-10-01","ESC138991",null,1,0.026,0.064,0.027,null,1.1211389280000001]
["AN_MSEG1","ESC1","AN_CS6","AN_GA2",null,"2007-10-01","ESC139356",null,1,0.052676,0.064,0.027,null,1.150288540128]
["AN_MSEG1","ESC1","AN_CS6","AN_GA2",null,"2008-10-01","ESC139722",null,1,0.08004558,0.064,0.027,null,1.1801960465422399]
["AN_MSEQ","ESC","AN_OH4",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AN_MSEQ","ESC","AN_OH4",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AN_MSEQ","ESC","AN_OH4",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AN_MSEQ","ESC","AN_OH4",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AN_MSEQ","ESC","AN_OH4",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AN_MSEQ","ESC","AN_OH4",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AN_MSEQ1","ESC1","AN_CS6","AN_GA2",null,"2005-10-01","ESC138626",null,1,0,0.064,0.027,null,1.092728]
["AN_MSEQ1","ESC1","AN_CS6","AN_GA2",null,"2006-10-01","ESC138991",null,1,0.026,0.064,0.027,null,1.1211389280000001]
["AN_MSEQ1","ESC1","AN_CS6","AN_GA2",null,"2007-10-01","ESC139356",null,1,0.052676,0.064,0.027,null,1.150288540128]
["AN_MSEQ1","ESC1","AN_CS6","AN_GA2",null,"2008-10-01","ESC139722",null,1,0.08004558,0.064,0.027,null,1.1801960465422399]
["AN_MSPS","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AN_MSPS","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AN_MSPS","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AN_MSPS","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AN_MSPS","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AN_MSPS","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AN_MSPS1","ESC1","AN_CS6","AN_GA2",null,"2005-10-01","ESC138626",null,1,0,0.064,0.027,null,1.092728]
["AN_MSPS1","ESC1","AN_CS6","AN_GA2",null,"2006-10-01","ESC138991",null,1,0.026,0.064,0.027,null,1.1211389280000001]
["AN_MSPS1","ESC1","AN_CS6","AN_GA2",null,"2007-10-01","ESC139356",null,1,0.052676,0.064,0.027,null,1.150288540128]
["AN_MSPS1","ESC1","AN_CS6","AN_GA2",null,"2008-10-01","ESC139722",null,1,0.08004558,0.064,0.027,null,1.1801960465422399]
["AN_MSSC","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AN_MSSC","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AN_MSSC","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AN_MSSC","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AN_MSSC","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AN_MSSC","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AN_MSSC1","ESC1","AN_CS6","AN_GA2",null,"2005-10-01","ESC138626",null,1,0,0.064,0.027,null,1.092728]
["AN_MSSC1","ESC1","AN_CS6","AN_GA2",null,"2006-10-01","ESC138991",null,1,0.026,0.064,0.027,null,1.1211389280000001]
["AN_MSSC1","ESC1","AN_CS6","AN_GA2",null,"2007-10-01","ESC139356",null,1,0.052676,0.064,0.027,null,1.150288540128]
["AN_MSSC1","ESC1","AN_CS6","AN_GA2",null,"2008-10-01","ESC139722",null,1,0.08004558,0.064,0.027,null,1.1801960465422399]
["AN_MSSF","AN_OH3",{"$nulls":4},"AN_OH3",null,1,{"$nulls":4},1]
["AN_MSSF1","AN_CS6","AN_GA2",null,null,null,"AN_CS6",null,1,null,0.027,null,null,1.027]
["AN_MSTR","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,1,0,0.3224,null,null,1.3224]
["AN_MSTR","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,1,0.029,0.3224,null,null,1.3607496]
["AN_MSTR","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.3224,null,null,1.3988505888]
["AN_MSTR","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.3224,null,null,1.435220556]
["AN_MSTR","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.3224,null,null,1.4725360392]
["AN_MSTR","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.3224,null,null,1.510822164]
["AN_MSTR1","ESC1","AN_OH1",null,null,"2005-10-01","ESC138626",null,1.29,0,0.3224,null,null,1.705896]
["AN_MSTR1","ESC1","AN_OH1",null,null,"2006-10-01","ESC138991",null,1.29,0.026,0.3224,null,null,1.7502492960000002]
["AN_MSTR1","ESC1","AN_OH1",null,null,"2007-10-01","ESC139356",null,1.29,0.052676,0.3224,null,null,1.795755777696]
["AN_MSTR1","ESC1","AN_OH1",null,null,"2008-10-01","ESC139722",null,1.29,0.08004558,0.3224,null,null,1.84244543473968]
["AN_MSXX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["AN_MSXX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["AN_MSXX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["AN_MSXX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["AN_MSXX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["AN_MSXX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["AN_MSXX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["AN_MSXX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["AN_MSXX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["AN_MSXX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["AN_MTRL","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AN_MTRL","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AN_MTRL","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AN_MTRL","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AN_MTRL","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AN_MTRL","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AN_MTRL1","ESC1","AN_CS6","AN_GA2",null,"2005-10-01","ESC138626",null,1,0,0.064,0.027,null,1.092728]
["AN_MTRL1","ESC1","AN_CS6","AN_GA2",null,"2006-10-01","ESC138991",null,1,0.026,0.064,0.027,null,1.1211389280000001]
["AN_MTRL1","ESC1","AN_CS6","AN_GA2",null,"2007-10-01","ESC139356",null,1,0.052676,0.064,0.027,null,1.150288540128]
["AN_MTRL1","ESC1","AN_CS6","AN_GA2",null,"2008-10-01","ESC139722",null,1,0.08004558,0.064,0.027,null,1.1801960465422399]
["AN_MVE","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,63.24,0,0.3224,null,null,83.62857600000001]
["AN_MVE","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,63.24,0.029,0.3224,null,null,86.053804704]
["AN_MVE","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,63.24,0.057812,0.3224,null,null,88.463311235712]
["AN_MVE","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,63.24,0.085315,0.3224,null,null,90.76334796144]
["AN_MVE","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,63.24,0.113533,0.3224,null,null,93.12317911900799]
["AN_MVE","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,63.24,0.142485,0.3224,null,null,95.54439365136]
["AN_MVE1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.292,0.027,0,110.80808284]
["AN_MVE1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.292,0.027,0,113.68909299384]
["AN_MVE1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.292,0.027,0,116.64500941167984]
["AN_MVE1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.292,0.027,0,119.67778009961584]
["AN_PHH","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,45.68,0,0.3224,null,null,60.407232]
["AN_PHH","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,45.68,0.029,0.3224,null,null,62.159041728]
["AN_PHH","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,45.68,0.057812,0.3224,null,null,63.899494896384006]
["AN_PHH","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,45.68,0.085315,0.3224,null,null,65.56087499808]
["AN_PHH","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,45.68,0.113533,0.3224,null,null,67.265446270656]
["AN_PHH","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,45.68,0.142485,0.3224,null,null,69.01435645152]
["AN_PHH1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,45.68,0,0.292,0.027,0,60.61206111999999]
["AN_PHH1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,45.68,0.026,0.292,0.027,0,62.18797470912]
["AN_PHH1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,45.68,0.052676,0.292,0.027,0,63.80486205155711]
["AN_PHH1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,45.68,0.08004558,0.292,0.027,0,65.46378870734584]
["AN_PHPD","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,33.95,0,0.3224,null,null,44.895480000000006]
["AN_PHPD","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,33.95,0.029,0.3224,null,null,46.19744892]
["AN_PHPD","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,33.95,0.057812,0.3224,null,null,47.490977489760006]
["AN_PHPD","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,33.95,0.085315,0.3224,null,null,48.72573787620001]
["AN_PHPD","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,33.95,0.113533,0.3224,null,null,49.992598530840006]
["AN_PHPD","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,33.95,0.142485,0.3224,null,null,51.2924124678]
["AN_PHPD1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,37.26,0,0.292,0.027,0,49.439697839999994]
["AN_PHPD1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,37.26,0.026,0.292,0.027,0,50.72512998384]
["AN_PHPD1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,37.26,0.052676,0.292,0.027,0,52.04398336341984]
["AN_PHPD1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,37.26,0.08004558,0.292,0.027,0,53.39712712862754]
["AN_PHS","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,63.24,0,0.3224,null,null,83.62857600000001]
["AN_PHS","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,63.24,0.029,0.3224,null,null,86.053804704]
["AN_PHS","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,63.24,0.057812,0.3224,null,null,88.463311235712]
["AN_PHS","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,63.24,0.085315,0.3224,null,null,90.76334796144]
["AN_PHS","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,63.24,0.113533,0.3224,null,null,93.12317911900799]
["AN_PHS","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,63.24,0.142485,0.3224,null,null,95.54439365136]
["AN_PHS1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.292,0.027,0,110.80808284]
["AN_PHS1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.292,0.027,0,113.68909299384]
["AN_PHS1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.292,0.027,0,116.64500941167984]
["AN_PHS1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.292,0.027,0,119.67778009961584]
["AN_PHSS","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,63.24,0,0.3224,null,null,83.62857600000001]
["AN_PHSS","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,63.24,0.029,0.3224,null,null,86.053804704]
["AN_PHSS","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,63.24,0.057812,0.3224,null,null,88.463311235712]
["AN_PHSS","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,63.24,0.085315,0.3224,null,null,90.76334796144]
["AN_PHSS","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,63.24,0.113533,0.3224,null,null,93.12317911900799]
["AN_PHSS","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,63.24,0.142485,0.3224,null,null,95.54439365136]
["AN_PHSS1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,63.24,0,0.292,0.027,0,83.91214416]
["AN_PHSS1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,63.24,0.026,0.292,0.027,0,86.09385990816]
["AN_PHSS1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,63.24,0.052676,0.292,0.027,0,88.33230026577216]
["AN_PHSS1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,63.24,0.08004558,0.292,0.027,0,90.6289404083308]
["AN_PM","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,63.24,0,0.3224,null,null,83.62857600000001]
["AN_PM","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,63.24,0.029,0.3224,null,null,86.053804704]
["AN_PM","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,63.24,0.057812,0.3224,null,null,88.463311235712]
["AN_PM","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,63.24,0.085315,0.3224,null,null,90.76334796144]
["AN_PM","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,63.24,0.113533,0.3224,null,null,93.12317911900799]
["AN_PM","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,63.24,0.142485,0.3224,null,null,95.54439365136]
["AN_PM1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.292,0.027,0,110.80808284]
["AN_PM1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.292,0.027,0,113.68909299384]
["AN_PM1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.292,0.027,0,116.64500941167984]
["AN_PM1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.292,0.027,0,119.67778009961584]
["AN_SEE","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,85,0,0.3224,null,null,112.404]
["AN_SEE","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,85,0.029,0.3224,null,null,115.663716]
["AN_SEE","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,85,0.057812,0.3224,null,null,118.90230004799999]
["AN_SEE","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,85,0.085315,0.3224,null,null,121.99374726000002]
["AN_SEE","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,85,0.113533,0.3224,null,null,125.16556333199999]
["AN_SEE","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,85,0.142485,0.3224,null,null,128.41988394]
["AN_SEE1","ESC1","AN_CS4","AN_GA2","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.292,0.027,0,110.80808284]
["AN_SEE1","ESC1","AN_CS4","AN_GA2","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.292,0.027,0,113.68909299384]
["AN_SEE1","ESC1","AN_CS4","AN_GA2","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.292,0.027,0,116.64500941167984]
["AN_SEE1","ESC1","AN_CS4","AN_GA2","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.292,0.027,0,119.67778009961584]
["AN_SEL","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,null,0,0.3224,null,null,0]
["AN_SEL","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,null,0.029,0.3224,null,null,0]
["AN_SEL","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.3224,null,null,0]
["AN_SEL","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.3224,null,null,0]
["AN_SEL","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.3224,null,null,0]
["AN_SEL","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.3224,null,null,0]
["AN_SEPM","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,null,0,0.3224,null,null,0]
["AN_SEPM","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,null,0.029,0.3224,null,null,0]
["AN_SEPM","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.3224,null,null,0]
["AN_SEPM","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.3224,null,null,0]
["AN_SEPM","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.3224,null,null,0]
["AN_SEPM","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.3224,null,null,0]
["AN_TMUC","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.2598,null,null,0]
["AN_TMUC","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.2598,null,null,0]
["AN_TMUC","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.2598,null,null,0]
["AN_TMUC","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.2598,null,null,0]
["AN_TMUC","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.2598,null,null,0]
["AN_TMUC","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.2598,null,null,0]
["AN_TMUE","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.2598,null,null,0]
["AN_TMUE","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.2598,null,null,0]
["AN_TMUE","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.2598,null,null,0]
["AN_TMUE","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.2598,null,null,0]
["AN_TMUE","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.2598,null,null,0]
["AN_TMUE","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.2598,null,null,0]
["AN_TMUI","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.2598,null,null,0]
["AN_TMUI","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.2598,null,null,0]
["AN_TMUI","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.2598,null,null,0]
["AN_TMUI","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.2598,null,null,0]
["AN_TMUI","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.2598,null,null,0]
["AN_TMUI","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.2598,null,null,0]
["AN_TMUO","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.2598,null,null,0]
["AN_TMUO","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.2598,null,null,0]
["AN_TMUO","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.2598,null,null,0]
["AN_TMUO","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.2598,null,null,0]
["AN_TMUO","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.2598,null,null,0]
["AN_TMUO","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.2598,null,null,0]
["AN_TMUP","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.2598,null,null,0]
["AN_TMUP","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.2598,null,null,0]
["AN_TMUP","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.2598,null,null,0]
["AN_TMUP","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.2598,null,null,0]
["AN_TMUP","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.2598,null,null,0]
["AN_TMUP","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.2598,null,null,0]
["AN_TMUW","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.2598,null,null,0]
["AN_TMUW","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.2598,null,null,0]
["AN_TMUW","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.2598,null,null,0]
["AN_TMUW","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.2598,null,null,0]
["AN_TMUW","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.2598,null,null,0]
["AN_TMUW","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.2598,null,null,0]
["BA",{"$nulls":5},"",null,1,{"$nulls":4},1]
["BASE",{"$nulls":5},"",null,1,{"$nulls":4},1]
["CNST",{"$nulls":5},"",{"$nulls":6},0]
["COMM",{"$nulls":5},"",{"$nulls":6},0]
["LA_MSCS","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,null,0,0.19,null,null,0]
["LA_MSCS","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,null,0.029,0.19,null,null,0]
["LA_MSCS","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.19,null,null,0]
["LA_MSCS","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.19,null,null,0]
["LA_MSCS","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.19,null,null,0]
["LA_MSCS","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.19,null,null,0]
["LA_MSCS1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LA_MSCS1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LA_MSCS1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LA_MSCS1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LA_MSEG","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LA_MSEG","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LA_MSEG","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LA_MSEG","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LA_MSEG","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LA_MSEG","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LA_MSEG1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LA_MSEG1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LA_MSEG1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LA_MSEG1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LA_MSEQ","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LA_MSEQ","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LA_MSEQ","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LA_MSEQ","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LA_MSEQ","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LA_MSEQ","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LA_MSEQ1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LA_MSEQ1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LA_MSEQ1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LA_MSEQ1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LA_MSPS","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,null,0,0.19,null,null,0]
["LA_MSPS","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,null,0.029,0.19,null,null,0]
["LA_MSPS","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.19,null,null,0]
["LA_MSPS","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.19,null,null,0]
["LA_MSPS","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.19,null,null,0]
["LA_MSPS","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.19,null,null,0]
["LA_MSSC","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LA_MSSC","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LA_MSSC","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LA_MSSC","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LA_MSSC","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LA_MSSC","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LA_MSSC1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LA_MSSC1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LA_MSSC1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LA_MSSC1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LA_MSSF","LL_OH",{"$nulls":4},"LL_OH",{"$nulls":6},0]
["LA_MSSX","LL_OH",{"$nulls":4},"LL_OH",{"$nulls":6},0]
["LA_MSXX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["LA_MSXX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["LA_MSXX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["LA_MSXX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["LA_MSXX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["LA_MSXX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["LA_MSXX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["LA_MSXX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["LA_MSXX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["LA_MSXX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["LLNL_LABOR","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LLNL_LABOR","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LLNL_LABOR","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LLNL_LABOR","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LLNL_LABOR","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LLNL_LABOR","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LLNL_NON-LABOR","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,null,0,0.19,null,null,0]
["LLNL_NON-LABOR","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,null,0.029,0.19,null,null,0]
["LLNL_NON-LABOR","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.19,null,null,0]
["LLNL_NON-LABOR","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.19,null,null,0]
["LLNL_NON-LABOR","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.19,null,null,0]
["LLNL_NON-LABOR","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.19,null,null,0]
["LLNL_SHOPS","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LLNL_SHOPS","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LLNL_SHOPS","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LLNL_SHOPS","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LLNL_SHOPS","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LLNL_SHOPS","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LLNL_TRAVEL","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,null,0,0.19,null,null,0]
["LLNL_TRAVEL","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,null,0.029,0.19,null,null,0]
["LLNL_TRAVEL","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.19,null,null,0]
["LLNL_TRAVEL","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.19,null,null,0]
["LLNL_TRAVEL","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.19,null,null,0]
["LLNL_TRAVEL","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.19,null,null,0]
["LL_ADMN","ESC",null,null,null,"2003-10-01","ESC37895",null,134.15048076923077,0,null,null,null,134.15048076923077]
["LL_ADMN","ESC",null,null,null,"2004-10-01","ESC38261",null,134.15048076923077,0.029,null,null,null,138.04084471153845]
["LL_ADMN","ESC",null,null,null,"2005-10-01","ESC38626",null,134.15048076923077,0.057812,null,null,null,141.90598836346155]
["LL_ADMN","ESC",null,null,null,"2006-10-01","ESC38991",null,134.15048076923077,0.085315,null,null,null,145.59552903605768]
["LL_ADMN","ESC",null,null,null,"2007-10-01","ESC39356",null,134.15048076923077,0.113533,null,null,null,149.38098730240384]
["LL_ADMN","ESC",null,null,null,"2008-10-01","ESC39722",null,134.15048076923077,0.142485,null,null,null,153.26491202163461]
["LL_ADMN1","ESC1",null,null,null,"2005-10-01","ESC138626",null,134.15048076923077,0,null,null,null,134.15048076923077]
["LL_ADMN1","ESC1",null,null,null,"2006-10-01","ESC138991",null,134.15048076923077,0.026,null,null,null,137.63839326923076]
["LL_ADMN1","ESC1",null,null,null,"2007-10-01","ESC139356",null,134.15048076923077,0.052676,null,null,null,141.21699149423077]
["LL_ADMN1","ESC1",null,null,null,"2008-10-01","ESC139722",null,134.15048076923077,0.08004558,null,null,null,144.8886338096827]
["LL_AW1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LL_AW1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LL_AW1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LL_AW1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LL_AWARD","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LL_AWARD","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LL_AWARD","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LL_AWARD","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LL_AWARD","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LL_AWARD","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LL_AWFX",{"$nulls":5},"",{"$nulls":6},0]
["LL_AWFX1",{"$nulls":5},"",{"$nulls":6},0]
["LL_AWFY",{"$nulls":5},"",{"$nulls":6},0]
["LL_AWFY1",{"$nulls":5},"",{"$nulls":6},0]
["LL_AWXX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["LL_AWXX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["LL_AWXX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["LL_AWXX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["LL_AWXX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["LL_AWXX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["LL_AWXX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["LL_AWXX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["LL_AWXX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["LL_AWXX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["LL_CCA","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_CCA","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_CCA","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_CCA","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_CCA","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_CCA","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_CE","ESC",null,null,null,"2003-10-01","ESC37895",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_CE","ESC",null,null,null,"2004-10-01","ESC38261",null,176.59423076923076,0.029,null,null,null,181.71546346153843]
["LL_CE","ESC",null,null,null,"2005-10-01","ESC38626",null,176.59423076923076,0.057812,null,null,null,186.80349643846154]
["LL_CE","ESC",null,null,null,"2006-10-01","ESC38991",null,176.59423076923076,0.085315,null,null,null,191.6603675673077]
["LL_CE","ESC",null,null,null,"2007-10-01","ESC39356",null,176.59423076923076,0.113533,null,null,null,196.64350357115381]
["LL_CE","ESC",null,null,null,"2008-10-01","ESC39722",null,176.59423076923076,0.142485,null,null,null,201.7562597403846]
["LL_CE1","ESC1",null,null,null,"2005-10-01","ESC138626",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_CE1","ESC1",null,null,null,"2006-10-01","ESC138991",null,176.59423076923076,0.026,null,null,null,181.18568076923077]
["LL_CE1","ESC1",null,null,null,"2007-10-01","ESC139356",null,176.59423076923076,0.052676,null,null,null,185.89650846923075]
["LL_CE1","ESC1",null,null,null,"2008-10-01","ESC139722",null,176.59423076923076,0.08004558,null,null,null,190.72981839580768]
["LL_CP","ESC",null,null,null,"2003-10-01","ESC37895",null,189.60865384615386,0,null,null,null,189.60865384615386]
["LL_CP","ESC",null,null,null,"2004-10-01","ESC38261",null,189.60865384615386,0.029,null,null,null,195.10730480769232]
["LL_CP","ESC",null,null,null,"2005-10-01","ESC38626",null,189.60865384615386,0.057812,null,null,null,200.5703093423077]
["LL_CP","ESC",null,null,null,"2006-10-01","ESC38991",null,189.60865384615386,0.085315,null,null,null,205.7851161490385]
["LL_CP","ESC",null,null,null,"2007-10-01","ESC39356",null,189.60865384615386,0.113533,null,null,null,211.13549314326923]
["LL_CP","ESC",null,null,null,"2008-10-01","ESC39722",null,189.60865384615386,0.142485,null,null,null,216.62504288942307]
["LL_CP1","ESC1",null,null,null,"2005-10-01","ESC138626",null,189.60865384615386,0,null,null,null,189.60865384615386]
["LL_CP1","ESC1",null,null,null,"2006-10-01","ESC138991",null,189.60865384615386,0.026,null,null,null,194.53847884615385]
["LL_CP1","ESC1",null,null,null,"2007-10-01","ESC139356",null,189.60865384615386,0.052676,null,null,null,199.59647929615386]
["LL_CP1","ESC1",null,null,null,"2008-10-01","ESC139722",null,189.60865384615386,0.08004558,null,null,null,204.78598851628846]
["LL_CT","ESC",null,null,null,"2003-10-01","ESC37895",null,137.21778846153848,0,null,null,null,137.21778846153848]
["LL_CT","ESC",null,null,null,"2004-10-01","ESC38261",null,137.21778846153848,0.029,null,null,null,141.19710432692307]
["LL_CT","ESC",null,null,null,"2005-10-01","ESC38626",null,137.21778846153848,0.057812,null,null,null,145.15062324807693]
["LL_CT","ESC",null,null,null,"2006-10-01","ESC38991",null,137.21778846153848,0.085315,null,null,null,148.92452408413465]
["LL_CT","ESC",null,null,null,"2007-10-01","ESC39356",null,137.21778846153848,0.113533,null,null,null,152.79653563894232]
["LL_CT","ESC",null,null,null,"2008-10-01","ESC39722",null,137.21778846153848,0.142485,null,null,null,156.76926505048078]
["LL_EE","ESC",null,null,null,"2003-10-01","ESC37895",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_EE","ESC",null,null,null,"2004-10-01","ESC38261",null,176.59423076923076,0.029,null,null,null,181.71546346153843]
["LL_EE","ESC",null,null,null,"2005-10-01","ESC38626",null,176.59423076923076,0.057812,null,null,null,186.80349643846154]
["LL_EE","ESC",null,null,null,"2006-10-01","ESC38991",null,176.59423076923076,0.085315,null,null,null,191.6603675673077]
["LL_EE","ESC",null,null,null,"2007-10-01","ESC39356",null,176.59423076923076,0.113533,null,null,null,196.64350357115381]
["LL_EE","ESC",null,null,null,"2008-10-01","ESC39722",null,176.59423076923076,0.142485,null,null,null,201.7562597403846]
["LL_EE1","ESC1",null,null,null,"2005-10-01","ESC138626",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_EE1","ESC1",null,null,null,"2006-10-01","ESC138991",null,176.59423076923076,0.026,null,null,null,181.18568076923077]
["LL_EE1","ESC1",null,null,null,"2007-10-01","ESC139356",null,176.59423076923076,0.052676,null,null,null,185.89650846923075]
["LL_EE1","ESC1",null,null,null,"2008-10-01","ESC139722",null,176.59423076923076,0.08004558,null,null,null,190.72981839580768]
["LL_KCA","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_KCA","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_KCA","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_KCA","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_KCA","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_KCA","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_KE","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_KE","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_KE","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_KE","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_KE","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_KE","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_KT","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_KT","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_KT","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_KT","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_KT","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_KT","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_MDD","ESC",null,null,null,"2003-10-01","ESC37895",null,162.0105769230769,0,null,null,null,162.0105769230769]
["LL_MDD","ESC",null,null,null,"2004-10-01","ESC38261",null,162.0105769230769,0.029,null,null,null,166.70888365384613]
["LL_MDD","ESC",null,null,null,"2005-10-01","ESC38626",null,162.0105769230769,0.057812,null,null,null,171.37673239615384]
["LL_MDD","ESC",null,null,null,"2006-10-01","ESC38991",null,162.0105769230769,0.085315,null,null,null,175.83250929326923]
["LL_MDD","ESC",null,null,null,"2007-10-01","ESC39356",null,162.0105769230769,0.113533,null,null,null,180.40412375288457]
["LL_MDD","ESC",null,null,null,"2008-10-01","ESC39722",null,162.0105769230769,0.142485,null,null,null,185.0946539759615]
["LL_MDD1","ESC1",null,null,null,"2005-10-01","ESC138626",null,162.0105769230769,0,null,null,null,162.0105769230769]
["LL_MDD1","ESC1",null,null,null,"2006-10-01","ESC138991",null,162.0105769230769,0.026,null,null,null,166.22285192307692]
["LL_MDD1","ESC1",null,null,null,"2007-10-01","ESC139356",null,162.0105769230769,0.052676,null,null,null,170.5446460730769]
["LL_MDD1","ESC1",null,null,null,"2008-10-01","ESC139722",null,162.0105769230769,0.08004558,null,null,null,174.9788075190192]
["LL_ME","ESC",null,null,null,"2003-10-01","ESC37895",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_ME","ESC",null,null,null,"2004-10-01","ESC38261",null,176.59423076923076,0.029,null,null,null,181.71546346153843]
["LL_ME","ESC",null,null,null,"2005-10-01","ESC38626",null,176.59423076923076,0.057812,null,null,null,186.80349643846154]
["LL_ME","ESC",null,null,null,"2006-10-01","ESC38991",null,176.59423076923076,0.085315,null,null,null,191.6603675673077]
["LL_ME","ESC",null,null,null,"2007-10-01","ESC39356",null,176.59423076923076,0.113533,null,null,null,196.64350357115381]
["LL_ME","ESC",null,null,null,"2008-10-01","ESC39722",null,176.59423076923076,0.142485,null,null,null,201.7562597403846]
["LL_ME1","ESC1",null,null,null,"2005-10-01","ESC138626",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_ME1","ESC1",null,null,null,"2006-10-01","ESC138991",null,176.59423076923076,0.026,null,null,null,181.18568076923077]
["LL_ME1","ESC1",null,null,null,"2007-10-01","ESC139356",null,176.59423076923076,0.052676,null,null,null,185.89650846923075]
["LL_ME1","ESC1",null,null,null,"2008-10-01","ESC139722",null,176.59423076923076,0.08004558,null,null,null,190.72981839580768]
["LL_MES","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_MES","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_MES","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_MES","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_MES","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_MES","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_MFAT","ESC",null,null,null,"2003-10-01","ESC37895",null,137.21778846153848,0,null,null,null,137.21778846153848]
["LL_MFAT","ESC",null,null,null,"2004-10-01","ESC38261",null,137.21778846153848,0.029,null,null,null,141.19710432692307]
["LL_MFAT","ESC",null,null,null,"2005-10-01","ESC38626",null,137.21778846153848,0.057812,null,null,null,145.15062324807693]
["LL_MFAT","ESC",null,null,null,"2006-10-01","ESC38991",null,137.21778846153848,0.085315,null,null,null,148.92452408413465]
["LL_MFAT","ESC",null,null,null,"2007-10-01","ESC39356",null,137.21778846153848,0.113533,null,null,null,152.79653563894232]
["LL_MFAT","ESC",null,null,null,"2008-10-01","ESC39722",null,137.21778846153848,0.142485,null,null,null,156.76926505048078]
["LL_MFAT1","ESC1",null,null,null,"2005-10-01","ESC138626",null,137.21778846153848,0,null,null,null,137.21778846153848]
["LL_MFAT1","ESC1",null,null,null,"2006-10-01","ESC138991",null,137.21778846153848,0.026,null,null,null,140.7854509615385]
["LL_MFAT1","ESC1",null,null,null,"2007-10-01","ESC139356",null,137.21778846153848,0.052676,null,null,null,144.44587268653848]
["LL_MFAT1","ESC1",null,null,null,"2008-10-01","ESC139722",null,137.21778846153848,0.08004558,null,null,null,148.2014659252596]
["LL_MFMS","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_MFMS","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_MFMS","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_MFMS","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_MFMS","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_MFMS","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_MFPC","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_MFPC","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_MFPC","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_MFPC","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_MFPC","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_MFPC","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_MSCS","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LL_MSCS","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LL_MSCS","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LL_MSCS","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LL_MSCS","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LL_MSCS","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LL_MSCS1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LL_MSCS1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LL_MSCS1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LL_MSCS1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LL_MSEG","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LL_MSEG","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LL_MSEG","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LL_MSEG","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LL_MSEG","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LL_MSEG","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LL_MSEG1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LL_MSEG1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LL_MSEG1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LL_MSEG1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LL_MSEQ","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LL_MSEQ","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LL_MSEQ","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LL_MSEQ","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LL_MSEQ","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LL_MSEQ","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LL_MSEQ1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LL_MSEQ1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LL_MSEQ1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LL_MSEQ1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LL_MSPS","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LL_MSPS","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LL_MSPS","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LL_MSPS","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LL_MSPS","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LL_MSPS","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LL_MSPS1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LL_MSPS1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LL_MSPS1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LL_MSPS1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LL_MSSC","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LL_MSSC","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LL_MSSC","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LL_MSSC","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LL_MSSC","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LL_MSSC","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LL_MSSC1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LL_MSSC1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LL_MSSC1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LL_MSSC1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LL_MSTR","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LL_MSTR","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LL_MSTR","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LL_MSTR","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LL_MSTR","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LL_MSTR","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LL_MSTR1","ESC1","LL_OH",null,null,"2005-10-01","ESC138626",null,1,0,0.19,null,null,1.19]
["LL_MSTR1","ESC1","LL_OH",null,null,"2006-10-01","ESC138991",null,1,0.026,0.19,null,null,1.22094]
["LL_MSTR1","ESC1","LL_OH",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.19,null,null,1.25268444]
["LL_MSTR1","ESC1","LL_OH",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.19,null,null,1.2852542401999998]
["LL_MSXX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["LL_MSXX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["LL_MSXX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["LL_MSXX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["LL_MSXX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["LL_MSXX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["LL_MSXX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["LL_MSXX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["LL_MSXX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["LL_MSXX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["LL_MTRL","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LL_MTRL","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LL_MTRL","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LL_MTRL","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LL_MTRL","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LL_MTRL","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LL_MTRL1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LL_MTRL1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LL_MTRL1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LL_MTRL1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LL_MVE","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_MVE","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_MVE","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_MVE","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_MVE","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_MVE","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_PCCA","ESC",null,null,null,"2003-10-01","ESC37895",null,158.32548076923078,0,null,null,null,158.32548076923078]
["LL_PCCA","ESC",null,null,null,"2004-10-01","ESC38261",null,158.32548076923078,0.029,null,null,null,162.91691971153847]
["LL_PCCA","ESC",null,null,null,"2005-10-01","ESC38626",null,158.32548076923078,0.057812,null,null,null,167.47859346346155]
["LL_PCCA","ESC",null,null,null,"2006-10-01","ESC38991",null,158.32548076923078,0.085315,null,null,null,171.8330191610577]
["LL_PCCA","ESC",null,null,null,"2007-10-01","ESC39356",null,158.32548076923078,0.113533,null,null,null,176.30064757740385]
["LL_PCCA","ESC",null,null,null,"2008-10-01","ESC39722",null,158.32548076923078,0.142485,null,null,null,180.88448689663463]
["LL_PCCA1","ESC1",null,null,null,"2005-10-01","ESC138626",null,158.32548076923078,0,null,null,null,158.32548076923078]
["LL_PCCA1","ESC1",null,null,null,"2006-10-01","ESC138991",null,158.32548076923078,0.026,null,null,null,162.4419432692308]
["LL_PCCA1","ESC1",null,null,null,"2007-10-01","ESC139356",null,158.32548076923078,0.052676,null,null,null,166.66543379423078]
["LL_PCCA1","ESC1",null,null,null,"2008-10-01","ESC139722",null,158.32548076923078,0.08004558,null,null,null,170.99873570618269]
["LL_PCE","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_PCE","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_PCE","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_PCE","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_PCE","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_PCE","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_PCEF","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_PCEF","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_PCEF","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_PCEF","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_PCEF","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_PCEF","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_PCT","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_PCT","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_PCT","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_PCT","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_PCT","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_PCT","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_PHPD","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_PHPD","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_PHPD","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_PHPD","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_PHPD","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_PHPD","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_PHS","ESC",null,null,null,"2003-10-01","ESC37895",null,188.69326923076923,0,null,null,null,188.69326923076923]
["LL_PHS","ESC",null,null,null,"2004-10-01","ESC38261",null,188.69326923076923,0.029,null,null,null,194.16537403846152]
["LL_PHS","ESC",null,null,null,"2005-10-01","ESC38626",null,188.69326923076923,0.057812,null,null,null,199.60200451153847]
["LL_PHS","ESC",null,null,null,"2006-10-01","ESC38991",null,188.69326923076923,0.085315,null,null,null,204.7916354951923]
["LL_PHS","ESC",null,null,null,"2007-10-01","ESC39356",null,188.69326923076923,0.113533,null,null,null,210.11618216634614]
["LL_PHS","ESC",null,null,null,"2008-10-01","ESC39722",null,188.69326923076923,0.142485,null,null,null,215.57922969711538]
["LL_PHS1","ESC1",null,null,null,"2005-10-01","ESC138626",null,188.69326923076923,0,null,null,null,188.69326923076923]
["LL_PHS1","ESC1",null,null,null,"2006-10-01","ESC138991",null,188.69326923076923,0.026,null,null,null,193.59929423076923]
["LL_PHS1","ESC1",null,null,null,"2007-10-01","ESC139356",null,188.69326923076923,0.052676,null,null,null,198.63287588076923]
["LL_PHS1","ESC1",null,null,null,"2008-10-01","ESC139722",null,188.69326923076923,0.08004558,null,null,null,203.7973314084423]
["LL_PHSS","ESC",null,null,null,"2003-10-01","ESC37895",null,208.3653846153846,0,null,null,null,208.3653846153846]
["LL_PHSS","ESC",null,null,null,"2004-10-01","ESC38261",null,208.3653846153846,0.029,null,null,null,214.40798076923076]
["LL_PHSS","ESC",null,null,null,"2005-10-01","ESC38626",null,208.3653846153846,0.057812,null,null,null,220.41140423076922]
["LL_PHSS","ESC",null,null,null,"2006-10-01","ESC38991",null,208.3653846153846,0.085315,null,null,null,226.14207740384614]
["LL_PHSS","ESC",null,null,null,"2007-10-01","ESC39356",null,208.3653846153846,0.113533,null,null,null,232.02173182692306]
["LL_PHSS","ESC",null,null,null,"2008-10-01","ESC39722",null,208.3653846153846,0.142485,null,null,null,238.05432644230768]
["LL_PHSS1","ESC1",null,null,null,"2005-10-01","ESC138626",null,208.3653846153846,0,null,null,null,208.3653846153846]
["LL_PHSS1","ESC1",null,null,null,"2006-10-01","ESC138991",null,208.3653846153846,0.026,null,null,null,213.78288461538463]
["LL_PHSS1","ESC1",null,null,null,"2007-10-01","ESC139356",null,208.3653846153846,0.052676,null,null,null,219.3412396153846]
["LL_PHSS1","ESC1",null,null,null,"2008-10-01","ESC139722",null,208.3653846153846,0.08004558,null,null,null,225.04411267884615]
["LL_PM","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_PM","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_PM","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_PM","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_PM","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_PM","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_PRC","ESC",null,null,null,"2003-10-01","ESC37895",null,162.0105769230769,0,null,null,null,162.0105769230769]
["LL_PRC","ESC",null,null,null,"2004-10-01","ESC38261",null,162.0105769230769,0.029,null,null,null,166.70888365384613]
["LL_PRC","ESC",null,null,null,"2005-10-01","ESC38626",null,162.0105769230769,0.057812,null,null,null,171.37673239615384]
["LL_PRC","ESC",null,null,null,"2006-10-01","ESC38991",null,162.0105769230769,0.085315,null,null,null,175.83250929326923]
["LL_PRC","ESC",null,null,null,"2007-10-01","ESC39356",null,162.0105769230769,0.113533,null,null,null,180.40412375288457]
["LL_PRC","ESC",null,null,null,"2008-10-01","ESC39722",null,162.0105769230769,0.142485,null,null,null,185.0946539759615]
["LL_PRC1","ESC1",null,null,null,"2005-10-01","ESC138626",null,162.0105769230769,0,null,null,null,162.0105769230769]
["LL_PRC1","ESC1",null,null,null,"2006-10-01","ESC138991",null,162.0105769230769,0.026,null,null,null,166.22285192307692]
["LL_PRC1","ESC1",null,null,null,"2007-10-01","ESC139356",null,162.0105769230769,0.052676,null,null,null,170.5446460730769]
["LL_PRC1","ESC1",null,null,null,"2008-10-01","ESC139722",null,162.0105769230769,0.08004558,null,null,null,174.9788075190192]
["LL_PRE","ESC",null,null,null,"2003-10-01","ESC37895",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_PRE","ESC",null,null,null,"2004-10-01","ESC38261",null,176.59423076923076,0.029,null,null,null,181.71546346153843]
["LL_PRE","ESC",null,null,null,"2005-10-01","ESC38626",null,176.59423076923076,0.057812,null,null,null,186.80349643846154]
["LL_PRE","ESC",null,null,null,"2006-10-01","ESC38991",null,176.59423076923076,0.085315,null,null,null,191.6603675673077]
["LL_PRE","ESC",null,null,null,"2007-10-01","ESC39356",null,176.59423076923076,0.113533,null,null,null,196.64350357115381]
["LL_PRE","ESC",null,null,null,"2008-10-01","ESC39722",null,176.59423076923076,0.142485,null,null,null,201.7562597403846]
["LL_PRE1","ESC1",null,null,null,"2005-10-01","ESC138626",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_PRE1","ESC1",null,null,null,"2006-10-01","ESC138991",null,176.59423076923076,0.026,null,null,null,181.18568076923077]
["LL_PRE1","ESC1",null,null,null,"2007-10-01","ESC139356",null,176.59423076923076,0.052676,null,null,null,185.89650846923075]
["LL_PRE1","ESC1",null,null,null,"2008-10-01","ESC139722",null,176.59423076923076,0.08004558,null,null,null,190.72981839580768]
["LL_RP","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_RP","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_RP","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_RP","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_RP","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_RP","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_SEE","ESC",null,null,null,"2003-10-01","ESC37895",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_SEE","ESC",null,null,null,"2004-10-01","ESC38261",null,176.59423076923076,0.029,null,null,null,181.71546346153843]
["LL_SEE","ESC",null,null,null,"2005-10-01","ESC38626",null,176.59423076923076,0.057812,null,null,null,186.80349643846154]
["LL_SEE","ESC",null,null,null,"2006-10-01","ESC38991",null,176.59423076923076,0.085315,null,null,null,191.6603675673077]
["LL_SEE","ESC",null,null,null,"2007-10-01","ESC39356",null,176.59423076923076,0.113533,null,null,null,196.64350357115381]
["LL_SEE","ESC",null,null,null,"2008-10-01","ESC39722",null,176.59423076923076,0.142485,null,null,null,201.7562597403846]
["LL_SEE1","ESC1",null,null,null,"2005-10-01","ESC138626",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_SEE1","ESC1",null,null,null,"2006-10-01","ESC138991",null,176.59423076923076,0.026,null,null,null,181.18568076923077]
["LL_SEE1","ESC1",null,null,null,"2007-10-01","ESC139356",null,176.59423076923076,0.052676,null,null,null,185.89650846923075]
["LL_SEE1","ESC1",null,null,null,"2008-10-01","ESC139722",null,176.59423076923076,0.08004558,null,null,null,190.72981839580768]
["LL_SEL","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_SEL","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_SEL","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_SEL","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_SEL","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_SEL","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_SEPM","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_SEPM","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_SEPM","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_SEPM","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_SEPM","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_SEPM","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_TMUC","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_TMUC","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_TMUC","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_TMUC","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_TMUC","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_TMUC","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_TMUE","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_TMUE","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_TMUE","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_TMUE","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_TMUE","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_TMUE","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_TMUI","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_TMUI","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_TMUI","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_TMUI","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_TMUI","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_TMUI","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_TMUO","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_TMUO","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_TMUO","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_TMUO","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_TMUO","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_TMUO","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_TMUP","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_TMUP","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_TMUP","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_TMUP","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_TMUP","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_TMUP","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_TMUW","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_TMUW","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_TMUW","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_TMUW","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_TMUW","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_TMUW","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["PED",{"$nulls":5},"",{"$nulls":6},0]
["R&D",{"$nulls":5},"",{"$nulls":6},0]
["RES",{"$nulls":5},"",{"$nulls":6},0]
["SA_GCFX1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SA_GCSS","ESC_CF","SL_OH2",null,null,"2004-10-01","ESC_CF38261",null,1,0,0.06,null,null,1.06]
["SA_GCSS","ESC_CF","SL_OH2",null,null,"2005-10-01","ESC_CF38626",null,1,0.03,0.06,null,null,1.0918]
["SA_GCSS","ESC_CF","SL_OH2",null,null,"2006-10-01","ESC_CF38991",null,1,0.08,0.06,null,null,1.1448]
["SA_GCSS","ESC_CF","SL_OH2",null,null,"2007-10-01","ESC_CF39356",null,1,0.19,0.06,null,null,1.2614]
["SA_GCSS","ESC_CF","SL_OH2",null,null,"2008-10-01","ESC_CF39722",null,1,0.3,0.06,null,null,1.3780000000000001]
["SA_GCSS","ESC_CF","SL_OH2",null,null,"2009-10-01","ESC_CF40087",null,1,0.41,0.06,null,null,1.4946]
["SA_GCSS1","ESC_CF","SL_OHN4",null,null,"2004-10-01","ESC_CF38261",null,1,0,0.0552,null,null,1.0552]
["SA_GCSS1","ESC_CF","SL_OHN4",null,null,"2005-10-01","ESC_CF38626",null,1,0.03,0.0552,null,null,1.086856]
["SA_GCSS1","ESC_CF","SL_OHN4",null,null,"2006-10-01","ESC_CF38991",null,1,0.08,0.0552,null,null,1.139616]
["SA_GCSS1","ESC_CF","SL_OHN4",null,null,"2007-10-01","ESC_CF39356",null,1,0.19,0.0552,null,null,1.255688]
["SA_GCSS1","ESC_CF","SL_OHN4",null,null,"2008-10-01","ESC_CF39722",null,1,0.3,0.0552,null,null,1.3717599999999999]
["SA_GCSS1","ESC_CF","SL_OHN4",null,null,"2009-10-01","ESC_CF40087",null,1,0.41,0.0552,null,null,1.4878319999999998]
["SA_GCSX","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,1,0,null,null,null,1]
["SA_GCSX","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,1,0.03,null,null,null,1.03]
["SA_GCSX","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,1,0.08,null,null,null,1.08]
["SA_GCSX","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,1,0.19,null,null,null,1.19]
["SA_GCSX","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,1,0.3,null,null,null,1.3]
["SA_GCSX","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,1,0.41,null,null,null,1.41]
["SA_GCSX1","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,1,0,null,null,null,1]
["SA_GCSX1","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,1,0.03,null,null,null,1.03]
["SA_GCSX1","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,1,0.08,null,null,null,1.08]
["SA_GCSX1","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,1,0.19,null,null,null,1.19]
["SA_GCSX1","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,1,0.3,null,null,null,1.3]
["SA_GCSX1","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,1,0.41,null,null,null,1.41]
["SA_MSCS","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.06,null,null,0]
["SA_MSCS","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.06,null,null,0]
["SA_MSCS","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.06,null,null,0]
["SA_MSCS","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.06,null,null,0]
["SA_MSCS","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.06,null,null,0]
["SA_MSCS","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.06,null,null,0]
["SA_MSCS1","ESC1","SL_OHN4",null,null,"2005-10-01","ESC138626",null,1,0,0.0552,null,null,1.0552]
["SA_MSCS1","ESC1","SL_OHN4",null,null,"2006-10-01","ESC138991",null,1,0.026,0.0552,null,null,1.0826352]
["SA_MSCS1","ESC1","SL_OHN4",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.0552,null,null,1.1107837151999997]
["SA_MSCS1","ESC1","SL_OHN4",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.0552,null,null,1.1396640960159998]
["SA_MSEG","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SA_MSEG","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SA_MSEG","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SA_MSEG","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SA_MSEG","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SA_MSEG","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SA_MSEG1","ESC1","SL_OHN4",null,null,"2005-10-01","ESC138626",null,1,0,0.0552,null,null,1.0552]
["SA_MSEG1","ESC1","SL_OHN4",null,null,"2006-10-01","ESC138991",null,1,0.026,0.0552,null,null,1.0826352]
["SA_MSEG1","ESC1","SL_OHN4",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.0552,null,null,1.1107837151999997]
["SA_MSEG1","ESC1","SL_OHN4",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.0552,null,null,1.1396640960159998]
["SA_MSEQ","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SA_MSEQ","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SA_MSEQ","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SA_MSEQ","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SA_MSEQ","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SA_MSEQ","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SA_MSEQ1","ESC1","SL_OHN4",null,null,"2005-10-01","ESC138626",null,1,0,0.0552,null,null,1.0552]
["SA_MSEQ1","ESC1","SL_OHN4",null,null,"2006-10-01","ESC138991",null,1,0.026,0.0552,null,null,1.0826352]
["SA_MSEQ1","ESC1","SL_OHN4",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.0552,null,null,1.1107837151999997]
["SA_MSEQ1","ESC1","SL_OHN4",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.0552,null,null,1.1396640960159998]
["SA_MSPF","SL_OH2",{"$nulls":4},"SL_OH2",null,1,{"$nulls":4},1]
["SA_MSPF1","SL_OHN4",{"$nulls":4},"SL_OHN4",null,1,{"$nulls":4},1]
["SA_MSPS","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SA_MSPS","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SA_MSPS","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SA_MSPS","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SA_MSPS","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SA_MSPS","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SA_MSPS1","ESC1","SL_OHN4",null,null,"2005-10-01","ESC138626",null,1,0,0.0552,null,null,1.0552]
["SA_MSPS1","ESC1","SL_OHN4",null,null,"2006-10-01","ESC138991",null,1,0.026,0.0552,null,null,1.0826352]
["SA_MSPS1","ESC1","SL_OHN4",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.0552,null,null,1.1107837151999997]
["SA_MSPS1","ESC1","SL_OHN4",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.0552,null,null,1.1396640960159998]
["SA_MSPX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["SA_MSPX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["SA_MSPX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["SA_MSPX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["SA_MSPX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["SA_MSPX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["SA_MSPX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["SA_MSPX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["SA_MSPX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["SA_MSPX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["SA_MSPY",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SA_MSPY1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SA_MSSC","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SA_MSSC","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SA_MSSC","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SA_MSSC","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SA_MSSC","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SA_MSSC","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SA_MSSC1","ESC1","SL_OHN4",null,null,"2005-10-01","ESC138626",null,1,0,0.0552,null,null,1.0552]
["SA_MSSC1","ESC1","SL_OHN4",null,null,"2006-10-01","ESC138991",null,1,0.026,0.0552,null,null,1.0826352]
["SA_MSSC1","ESC1","SL_OHN4",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.0552,null,null,1.1107837151999997]
["SA_MSSC1","ESC1","SL_OHN4",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.0552,null,null,1.1396640960159998]
["SA_MSSF","SL_OH2",{"$nulls":4},"SL_OH2",null,1,{"$nulls":4},1]
["SA_MSSF1","SL_OHN4",{"$nulls":4},"SL_OHN4",null,1,{"$nulls":4},1]
["SA_MSSY",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SA_MSSY1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SA_MSXX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["SA_MSXX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["SA_MSXX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["SA_MSXX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["SA_MSXX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["SA_MSXX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["SA_MSXX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["SA_MSXX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["SA_MSXX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["SA_MSXX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["SLAC_LABOR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,null,0,0.29,0.215,0.2,0]
["SLAC_LABOR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,null,0.029,0.29,0.215,0.2,0]
["SLAC_LABOR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,null,0.057812,0.29,0.215,0.2,0]
["SLAC_LABOR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,null,0.085315,0.29,0.215,0.2,0]
["SLAC_LABOR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,null,0.113533,0.29,0.215,0.2,0]
["SLAC_LABOR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,null,0.142485,0.29,0.215,0.2,0]
["SLAC_NON-LABOR","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.06,null,null,0]
["SLAC_NON-LABOR","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.06,null,null,0]
["SLAC_NON-LABOR","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.06,null,null,0]
["SLAC_NON-LABOR","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.06,null,null,0]
["SLAC_NON-LABOR","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.06,null,null,0]
["SLAC_NON-LABOR","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.06,null,null,0]
["SLAC_SHOPS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2003-10-01","ESC37895",null,null,0,0,0,0.2,0]
["SLAC_SHOPS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2004-10-01","ESC38261",null,null,0.029,0,0,0.2,0]
["SLAC_SHOPS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2005-10-01","ESC38626",null,null,0.057812,0,0,0.2,0]
["SLAC_SHOPS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2006-10-01","ESC38991",null,null,0.085315,0,0,0.2,0]
["SLAC_SHOPS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2007-10-01","ESC39356",null,null,0.113533,0,0,0.2,0]
["SLAC_SHOPS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2008-10-01","ESC39722",null,null,0.142485,0,0,0.2,0]
["SLAC_TRAVEL","ESC","SL_OH1",null,null,"2003-10-01","ESC37895",null,null,0,0.2,null,null,0]
["SLAC_TRAVEL","ESC","SL_OH1",null,null,"2004-10-01","ESC38261",null,null,0.029,0.2,null,null,0]
["SLAC_TRAVEL","ESC","SL_OH1",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.2,null,null,0]
["SLAC_TRAVEL","ESC","SL_OH1",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.2,null,null,0]
["SLAC_TRAVEL","ESC","SL_OH1",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.2,null,null,0]
["SLAC_TRAVEL","ESC","SL_OH1",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.2,null,null,0]
["SL_ADMN","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,30.1731,0,0.29,0.215,0.2,56.750169942]
["SL_ADMN","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,30.1731,0.029,0.29,0.215,0.2,58.395924870318]
["SL_ADMN","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,30.1731,0.057812,0.29,0.215,0.2,60.031010766686904]
["SL_ADMN","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,30.1731,0.085315,0.29,0.215,0.2,61.59181069060175]
["SL_ADMN","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,30.1731,0.113533,0.29,0.215,0.2,63.193186986025076]
["SL_ADMN","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,30.1731,0.142485,0.29,0.215,0.2,64.83621790618588]
["SL_ADMN1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,30.1731,0,0.305,0.21,0.38,65.74987030589999]
["SL_ADMN1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,30.1731,0.026,0.305,0.21,0.38,67.4593669338534]
["SL_ADMN1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,30.1731,0.052676,0.305,0.21,0.38,69.21331047413358]
["SL_ADMN1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,30.1731,0.08004558,0.305,0.21,0.38,71.01285680946053]
["SL_AW1","ESC1","SL_OHN4",null,null,"2005-10-01","ESC138626",null,1,0,0.0552,null,null,1.0552]
["SL_AW1","ESC1","SL_OHN4",null,null,"2006-10-01","ESC138991",null,1,0.026,0.0552,null,null,1.0826352]
["SL_AW1","ESC1","SL_OHN4",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.0552,null,null,1.1107837151999997]
["SL_AW1","ESC1","SL_OHN4",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.0552,null,null,1.1396640960159998]
["SL_AWARD","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SL_AWARD","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SL_AWARD","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SL_AWARD","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SL_AWARD","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SL_AWARD","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SL_AWFX","SL_OH2",{"$nulls":4},"SL_OH2",null,1,{"$nulls":4},1]
["SL_AWFX1","SL_OHN4",{"$nulls":4},"SL_OHN4",null,1,{"$nulls":4},1]
["SL_AWFY",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_AWFY1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_AWGC","ESC_CF","SL_OH2",null,null,"2004-10-01","ESC_CF38261",null,1,0,0.06,null,null,1.06]
["SL_AWGC","ESC_CF","SL_OH2",null,null,"2005-10-01","ESC_CF38626",null,1,0.03,0.06,null,null,1.0918]
["SL_AWGC","ESC_CF","SL_OH2",null,null,"2006-10-01","ESC_CF38991",null,1,0.08,0.06,null,null,1.1448]
["SL_AWGC","ESC_CF","SL_OH2",null,null,"2007-10-01","ESC_CF39356",null,1,0.19,0.06,null,null,1.2614]
["SL_AWGC","ESC_CF","SL_OH2",null,null,"2008-10-01","ESC_CF39722",null,1,0.3,0.06,null,null,1.3780000000000001]
["SL_AWGC","ESC_CF","SL_OH2",null,null,"2009-10-01","ESC_CF40087",null,1,0.41,0.06,null,null,1.4946]
["SL_AWGC1","ESC_CF","SL_OHN4",null,null,"2004-10-01","ESC_CF38261",null,1,0,0.0552,null,null,1.0552]
["SL_AWGC1","ESC_CF","SL_OHN4",null,null,"2005-10-01","ESC_CF38626",null,1,0.03,0.0552,null,null,1.086856]
["SL_AWGC1","ESC_CF","SL_OHN4",null,null,"2006-10-01","ESC_CF38991",null,1,0.08,0.0552,null,null,1.139616]
["SL_AWGC1","ESC_CF","SL_OHN4",null,null,"2007-10-01","ESC_CF39356",null,1,0.19,0.0552,null,null,1.255688]
["SL_AWGC1","ESC_CF","SL_OHN4",null,null,"2008-10-01","ESC_CF39722",null,1,0.3,0.0552,null,null,1.3717599999999999]
["SL_AWGC1","ESC_CF","SL_OHN4",null,null,"2009-10-01","ESC_CF40087",null,1,0.41,0.0552,null,null,1.4878319999999998]
["SL_AWGX","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,1,0,null,null,null,1]
["SL_AWGX","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,1,0.03,null,null,null,1.03]
["SL_AWGX","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,1,0.08,null,null,null,1.08]
["SL_AWGX","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,1,0.19,null,null,null,1.19]
["SL_AWGX","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,1,0.3,null,null,null,1.3]
["SL_AWGX","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,1,0.41,null,null,null,1.41]
["SL_AWGX1","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,1,0,null,null,null,1]
["SL_AWGX1","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,1,0.03,null,null,null,1.03]
["SL_AWGX1","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,1,0.08,null,null,null,1.08]
["SL_AWGX1","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,1,0.19,null,null,null,1.19]
["SL_AWGX1","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,1,0.3,null,null,null,1.3]
["SL_AWGX1","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,1,0.41,null,null,null,1.41]
["SL_AWXX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["SL_AWXX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["SL_AWXX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["SL_AWXX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["SL_AWXX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["SL_AWXX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["SL_AWXX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["SL_AWXX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["SL_AWXX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["SL_AWXX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["SL_CCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,33.86,0,0.29,0.215,0.2,63.6845652]
["SL_CCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,33.86,0.029,0.29,0.215,0.2,65.53141759079999]
["SL_CCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,33.86,0.057812,0.29,0.215,0.2,67.3662972833424]
["SL_CCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,33.86,0.085315,0.29,0.215,0.2,69.117813880038]
["SL_CCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,33.86,0.113533,0.29,0.215,0.2,70.9148649408516]
["SL_CCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,33.86,0.142485,0.29,0.215,0.2,72.75866047252201]
["SL_CCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,33.86,0,0.305,0.21,0.38,73.78395354]
["SL_CCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,33.86,0.026,0.305,0.21,0.38,75.70233633203999]
["SL_CCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,33.86,0.052676,0.305,0.21,0.38,77.67059707667303]
["SL_CCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,33.86,0.08004558,0.305,0.21,0.38,79.69003289580235]
["SL_CE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,58.14,0,0.29,0.215,0.2,109.3508748]
["SL_CE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,58.14,0.029,0.29,0.215,0.2,112.52205016919999]
["SL_CE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,58.14,0.057812,0.29,0.215,0.2,115.6726675739376]
["SL_CE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,58.14,0.085315,0.29,0.215,0.2,118.680144683562]
["SL_CE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,58.14,0.113533,0.29,0.215,0.2,121.7658076686684]
["SL_CE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,58.14,0.142485,0.29,0.215,0.2,124.931734195878]
["SL_CE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,58.14,0,0.305,0.21,0.38,126.69223445999998]
["SL_CE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,58.14,0.026,0.305,0.21,0.38,129.98623255596]
["SL_CE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,58.14,0.052676,0.305,0.21,0.38,133.36587460241495]
["SL_CE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,58.14,0.08004558,0.305,0.21,0.38,136.83338784884668]
["SL_CP","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,47.01,0,0.29,0.215,0.2,88.41734819999999]
["SL_CP","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,47.01,0.029,0.29,0.215,0.2,90.9814512978]
["SL_CP","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,47.01,0.057812,0.29,0.215,0.2,93.5289319341384]
["SL_CP","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,47.01,0.085315,0.29,0.215,0.2,95.96067426168301]
["SL_CP","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,47.01,0.113533,0.29,0.215,0.2,98.4556349931906]
["SL_CP","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,47.01,0.142485,0.29,0.215,0.2,101.015494058277]
["SL_CP1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,42.39,0,0.305,0.21,0.38,92.37158271]
["SL_CP1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,42.39,0.026,0.305,0.21,0.38,94.77324386046]
["SL_CP1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,42.39,0.052676,0.305,0.21,0.38,97.23734820083196]
["SL_CP1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,42.39,0.08004558,0.305,0.21,0.38,99.76551962353989]
["SL_CPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,30.93,0,0.29,0.215,0.2,58.1737626]
["SL_CPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,30.93,0.029,0.29,0.215,0.2,59.860801715399994]
["SL_CPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,30.93,0.057812,0.29,0.215,0.2,61.5369041634312]
["SL_CPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,30.93,0.085315,0.29,0.215,0.2,63.136857156219]
["SL_CPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,30.93,0.113533,0.29,0.215,0.2,64.7784043892658]
["SL_CPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,30.93,0.142485,0.29,0.215,0.2,66.46265116406099]
["SL_CPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,30.93,0,0.305,0.21,0.38,67.39922277]
["SL_CPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,30.93,0.026,0.305,0.21,0.38,69.15160256201999]
["SL_CPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,30.93,0.052676,0.305,0.21,0.38,70.9495442286325]
["SL_CPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,30.93,0.08004558,0.305,0.21,0.38,72.79423264817383]
["SL_CRA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,24.14,0,0.29,0.215,0.2,45.4029948]
["SL_CRA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,24.14,0.029,0.29,0.215,0.2,46.719681649200005]
["SL_CRA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,24.14,0.057812,0.29,0.215,0.2,48.02783273537761]
["SL_CRA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,24.14,0.085315,0.29,0.215,0.2,49.276551301362005]
["SL_CRA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,24.14,0.113533,0.29,0.215,0.2,50.557733008628404]
["SL_CRA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,24.14,0.142485,0.29,0.215,0.2,51.872240514078]
["SL_CRA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,27.19,0,0.305,0.21,0.38,59.249429909999996]
["SL_CRA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,27.19,0.026,0.305,0.21,0.38,60.789915087659985]
["SL_CRA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,27.19,0.052676,0.305,0.21,0.38,62.37045287993915]
["SL_CRA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,27.19,0.08004558,0.305,0.21,0.38,63.99208489181529]
["SL_CRM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,30.93,0,0.29,0.215,0.2,58.1737626]
["SL_CRM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,30.93,0.029,0.29,0.215,0.2,59.860801715399994]
["SL_CRM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,30.93,0.057812,0.29,0.215,0.2,61.5369041634312]
["SL_CRM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,30.93,0.085315,0.29,0.215,0.2,63.136857156219]
["SL_CRM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,30.93,0.113533,0.29,0.215,0.2,64.7784043892658]
["SL_CRM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,30.93,0.142485,0.29,0.215,0.2,66.46265116406099]
["SL_CRM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,30.93,0,0.305,0.21,0.38,67.39922277]
["SL_CRM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,30.93,0.026,0.305,0.21,0.38,69.15160256201999]
["SL_CRM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,30.93,0.052676,0.305,0.21,0.38,70.9495442286325]
["SL_CRM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,30.93,0.08004558,0.305,0.21,0.38,72.79423264817383]
["SL_CT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,31.83,0,0.29,0.215,0.2,59.866500599999995]
["SL_CT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,31.83,0.029,0.29,0.215,0.2,61.60262911739999]
["SL_CT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,31.83,0.057812,0.29,0.215,0.2,63.327502732687186]
["SL_CT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,31.83,0.085315,0.29,0.215,0.2,64.974011098689]
["SL_CT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,31.83,0.113533,0.29,0.215,0.2,66.66332401261978]
["SL_CT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,31.83,0.142485,0.29,0.215,0.2,68.396578937991]
["SL_CT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,31.83,0,0.305,0.21,0.38,69.36040286999999]
["SL_CT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,31.83,0.026,0.305,0.21,0.38,71.16377334461997]
["SL_CT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,31.83,0.052676,0.305,0.21,0.38,73.0140314515801]
["SL_CT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,31.83,0.08004558,0.305,0.21,0.38,74.91239654676279]
["SL_EE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,58.14,0,0.29,0.215,0.2,109.3508748]
["SL_EE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,58.14,0.029,0.29,0.215,0.2,112.52205016919999]
["SL_EE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,58.14,0.057812,0.29,0.215,0.2,115.6726675739376]
["SL_EE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,58.14,0.085315,0.29,0.215,0.2,118.680144683562]
["SL_EE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,58.14,0.113533,0.29,0.215,0.2,121.7658076686684]
["SL_EE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,58.14,0.142485,0.29,0.215,0.2,124.931734195878]
["SL_EE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,47.95,0,0.305,0.21,0.38,104.48731754999999]
["SL_EE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,47.95,0.026,0.305,0.21,0.38,107.2039878063]
["SL_EE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,47.95,0.052676,0.305,0.21,0.38,109.99129148926377]
["SL_EE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,47.95,0.08004558,0.305,0.21,0.38,112.85106548593392]
["SL_FA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,40.7,0,0.29,0.215,0.2,76.54937400000001]
["SL_FA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,40.7,0.029,0.29,0.215,0.2,78.769305846]
["SL_FA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,40.7,0.057812,0.29,0.215,0.2,80.97484640968801]
["SL_FA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,40.7,0.085315,0.29,0.215,0.2,83.08018384281002]
["SL_FA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,40.7,0.113533,0.29,0.215,0.2,85.24025407834199]
["SL_FA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,40.7,0.142485,0.29,0.215,0.2,87.45651155439002]
["SL_FA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,46.24,0,0.305,0.21,0.38,100.76107535999999]
["SL_FA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,46.24,0.026,0.305,0.21,0.38,103.38086331936]
["SL_FA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,46.24,0.052676,0.305,0.21,0.38,106.06876576566334]
["SL_FA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,46.24,0.08004558,0.305,0.21,0.38,108.82655407861489]
["SL_GCAW","ESC_CF","SL_OH2",null,null,"2004-10-01","ESC_CF38261",null,null,0,0.06,null,null,0]
["SL_GCAW","ESC_CF","SL_OH2",null,null,"2005-10-01","ESC_CF38626",null,null,0.03,0.06,null,null,0]
["SL_GCAW","ESC_CF","SL_OH2",null,null,"2006-10-01","ESC_CF38991",null,null,0.08,0.06,null,null,0]
["SL_GCAW","ESC_CF","SL_OH2",null,null,"2007-10-01","ESC_CF39356",null,null,0.19,0.06,null,null,0]
["SL_GCAW","ESC_CF","SL_OH2",null,null,"2008-10-01","ESC_CF39722",null,null,0.3,0.06,null,null,0]
["SL_GCAW","ESC_CF","SL_OH2",null,null,"2009-10-01","ESC_CF40087",null,null,0.41,0.06,null,null,0]
["SL_GCAW1","ESC_CF","SL_OHN4",null,null,"2004-10-01","ESC_CF38261",null,null,0,0.0552,null,null,0]
["SL_GCAW1","ESC_CF","SL_OHN4",null,null,"2005-10-01","ESC_CF38626",null,null,0.03,0.0552,null,null,0]
["SL_GCAW1","ESC_CF","SL_OHN4",null,null,"2006-10-01","ESC_CF38991",null,null,0.08,0.0552,null,null,0]
["SL_GCAW1","ESC_CF","SL_OHN4",null,null,"2007-10-01","ESC_CF39356",null,null,0.19,0.0552,null,null,0]
["SL_GCAW1","ESC_CF","SL_OHN4",null,null,"2008-10-01","ESC_CF39722",null,null,0.3,0.0552,null,null,0]
["SL_GCAW1","ESC_CF","SL_OHN4",null,null,"2009-10-01","ESC_CF40087",null,null,0.41,0.0552,null,null,0]
["SL_GCAX","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,null,0,null,null,null,0]
["SL_GCAX","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,null,0.03,null,null,null,0]
["SL_GCAX","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,null,0.08,null,null,null,0]
["SL_GCAX","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,null,0.19,null,null,null,0]
["SL_GCAX","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,null,0.3,null,null,null,0]
["SL_GCAX","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,null,0.41,null,null,null,0]
["SL_GCAX1","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,null,0,null,null,null,0]
["SL_GCAX1","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,null,0.03,null,null,null,0]
["SL_GCAX1","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,null,0.08,null,null,null,0]
["SL_GCAX1","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,null,0.19,null,null,null,0]
["SL_GCAX1","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,null,0.3,null,null,null,0]
["SL_GCAX1","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,null,0.41,null,null,null,0]
["SL_GCFX1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_GCSS","ESC_CF","SL_OH2",null,null,"2004-10-01","ESC_CF38261",null,1,0,0.06,null,null,1.06]
["SL_GCSS","ESC_CF","SL_OH2",null,null,"2005-10-01","ESC_CF38626",null,1,0.03,0.06,null,null,1.0918]
["SL_GCSS","ESC_CF","SL_OH2",null,null,"2006-10-01","ESC_CF38991",null,1,0.08,0.06,null,null,1.1448]
["SL_GCSS","ESC_CF","SL_OH2",null,null,"2007-10-01","ESC_CF39356",null,1,0.19,0.06,null,null,1.2614]
["SL_GCSS","ESC_CF","SL_OH2",null,null,"2008-10-01","ESC_CF39722",null,1,0.3,0.06,null,null,1.3780000000000001]
["SL_GCSS","ESC_CF","SL_OH2",null,null,"2009-10-01","ESC_CF40087",null,1,0.41,0.06,null,null,1.4946]
["SL_GCSS1","ESC_CF","SL_OHN4",null,null,"2004-10-01","ESC_CF38261",null,1,0,0.0552,null,null,1.0552]
["SL_GCSS1","ESC_CF","SL_OHN4",null,null,"2005-10-01","ESC_CF38626",null,1,0.03,0.0552,null,null,1.086856]
["SL_GCSS1","ESC_CF","SL_OHN4",null,null,"2006-10-01","ESC_CF38991",null,1,0.08,0.0552,null,null,1.139616]
["SL_GCSS1","ESC_CF","SL_OHN4",null,null,"2007-10-01","ESC_CF39356",null,1,0.19,0.0552,null,null,1.255688]
["SL_GCSS1","ESC_CF","SL_OHN4",null,null,"2008-10-01","ESC_CF39722",null,1,0.3,0.0552,null,null,1.3717599999999999]
["SL_GCSS1","ESC_CF","SL_OHN4",null,null,"2009-10-01","ESC_CF40087",null,1,0.41,0.0552,null,null,1.4878319999999998]
["SL_GCSX","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,1,0,null,null,null,1]
["SL_GCSX","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,1,0.03,null,null,null,1.03]
["SL_GCSX","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,1,0.08,null,null,null,1.08]
["SL_GCSX","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,1,0.19,null,null,null,1.19]
["SL_GCSX","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,1,0.3,null,null,null,1.3]
["SL_GCSX","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,1,0.41,null,null,null,1.41]
["SL_GCSX1","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,1,0,null,null,null,1]
["SL_GCSX1","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,1,0.03,null,null,null,1.03]
["SL_GCSX1","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,1,0.08,null,null,null,1.08]
["SL_GCSX1","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,1,0.19,null,null,null,1.19]
["SL_GCSX1","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,1,0.3,null,null,null,1.3]
["SL_GCSX1","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,1,0.41,null,null,null,1.41]
["SL_IPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_IPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_IPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_IPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_IPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_IPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_IPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,54.62,0,0.305,0.21,0.38,119.02184117999998]
["SL_IPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,54.62,0.026,0.305,0.21,0.38,122.11640905067998]
["SL_IPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,54.62,0.052676,0.305,0.21,0.38,125.29143568599764]
["SL_IPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,54.62,0.08004558,0.305,0.21,0.38,128.54901348992095]
["SL_KCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,33.86,0,0.29,0.215,0.2,63.6845652]
["SL_KCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,33.86,0.029,0.29,0.215,0.2,65.53141759079999]
["SL_KCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,33.86,0.057812,0.29,0.215,0.2,67.3662972833424]
["SL_KCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,33.86,0.085315,0.29,0.215,0.2,69.117813880038]
["SL_KCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,33.86,0.113533,0.29,0.215,0.2,70.9148649408516]
["SL_KCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,33.86,0.142485,0.29,0.215,0.2,72.75866047252201]
["SL_KCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,33.86,0,0.305,0.21,0.38,73.78395354]
["SL_KCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,33.86,0.026,0.305,0.21,0.38,75.70233633203999]
["SL_KCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,33.86,0.052676,0.305,0.21,0.38,77.67059707667303]
["SL_KCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,33.86,0.08004558,0.305,0.21,0.38,79.69003289580235]
["SL_KE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,58.14,0,0.29,0.215,0.2,109.3508748]
["SL_KE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,58.14,0.029,0.29,0.215,0.2,112.52205016919999]
["SL_KE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,58.14,0.057812,0.29,0.215,0.2,115.6726675739376]
["SL_KE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,58.14,0.085315,0.29,0.215,0.2,118.680144683562]
["SL_KE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,58.14,0.113533,0.29,0.215,0.2,121.7658076686684]
["SL_KE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,58.14,0.142485,0.29,0.215,0.2,124.931734195878]
["SL_KE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,58.14,0,0.305,0.21,0.38,126.69223445999998]
["SL_KE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,58.14,0.026,0.305,0.21,0.38,129.98623255596]
["SL_KE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,58.14,0.052676,0.305,0.21,0.38,133.36587460241495]
["SL_KE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,58.14,0.08004558,0.305,0.21,0.38,136.83338784884668]
["SL_KT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,31.83,0,0.29,0.215,0.2,59.866500599999995]
["SL_KT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,31.83,0.029,0.29,0.215,0.2,61.60262911739999]
["SL_KT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,31.83,0.057812,0.29,0.215,0.2,63.327502732687186]
["SL_KT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,31.83,0.085315,0.29,0.215,0.2,64.974011098689]
["SL_KT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,31.83,0.113533,0.29,0.215,0.2,66.66332401261978]
["SL_KT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,31.83,0.142485,0.29,0.215,0.2,68.396578937991]
["SL_KT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,31.83,0,0.305,0.21,0.38,69.36040286999999]
["SL_KT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,31.83,0.026,0.305,0.21,0.38,71.16377334461997]
["SL_KT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,31.83,0.052676,0.305,0.21,0.38,73.0140314515801]
["SL_KT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,31.83,0.08004558,0.305,0.21,0.38,74.91239654676279]
["SL_LPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_LPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_LPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_LPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_LPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_LPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_LPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,54.62,0,0.305,0.21,0.38,119.02184117999998]
["SL_LPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,54.62,0.026,0.305,0.21,0.38,122.11640905067998]
["SL_LPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,54.62,0.052676,0.305,0.21,0.38,125.29143568599764]
["SL_LPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,54.62,0.08004558,0.305,0.21,0.38,128.54901348992095]
["SL_MDD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,32.42,0,0.29,0.215,0.2,60.97618440000001]
["SL_MDD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,32.42,0.029,0.29,0.215,0.2,62.7444937476]
["SL_MDD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,32.42,0.057812,0.29,0.215,0.2,64.5013395725328]
["SL_MDD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,32.42,0.085315,0.29,0.215,0.2,66.17836757208602]
["SL_MDD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,32.42,0.113533,0.29,0.215,0.2,67.8989935434852]
["SL_MDD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,32.42,0.142485,0.29,0.215,0.2,69.66437603423401]
["SL_MDD1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,43.07,0,0.305,0.21,0.38,93.85336322999999]
["SL_MDD1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,43.07,0.026,0.305,0.21,0.38,96.29355067398]
["SL_MDD1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,43.07,0.052676,0.305,0.21,0.38,98.79718299150346]
["SL_MDD1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,43.07,0.08004558,0.305,0.21,0.38,101.36591012469599]
["SL_ME","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_ME","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_ME","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_ME","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_ME","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_ME","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_ME1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,51.37,0,0.305,0.21,0.38,111.93980192999997]
["SL_ME1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,51.37,0.026,0.305,0.21,0.38,114.85023678017998]
["SL_ME1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,51.37,0.052676,0.305,0.21,0.38,117.83634293646463]
["SL_ME1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,51.37,0.08004558,0.305,0.21,0.38,120.90008830057195]
["SL_MES","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,46.68,0,0.29,0.215,0.2,87.7966776]
["SL_MES","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,46.68,0.029,0.29,0.215,0.2,90.3427812504]
["SL_MES","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,46.68,0.057812,0.29,0.215,0.2,92.8723791254112]
["SL_MES","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,46.68,0.085315,0.29,0.215,0.2,95.28705114944401]
["SL_MES","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,46.68,0.113533,0.29,0.215,0.2,97.76449779796079]
["SL_MES","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,46.68,0.142485,0.29,0.215,0.2,100.306387207836]
["SL_MES1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,41.3,0,0.305,0.21,0.38,89.99637569999999]
["SL_MES1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,41.3,0.026,0.305,0.21,0.38,92.33628146819999]
["SL_MES1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,41.3,0.052676,0.305,0.21,0.38,94.73702478637318]
["SL_MES1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,41.3,0.08004558,0.305,0.21,0.38,97.20018779080438]
["SL_MFAT","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2003-10-01","ESC37895",null,66.3,0,0,0,0.2,79.55999999999999]
["SL_MFAT","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2004-10-01","ESC38261",null,66.3,0.029,0,0,0.2,81.86723999999998]
["SL_MFAT","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2005-10-01","ESC38626",null,66.3,0.057812,0,0,0.2,84.15952272]
["SL_MFAT","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2006-10-01","ESC38991",null,66.3,0.085315,0,0,0.2,86.34766139999999]
["SL_MFAT","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2007-10-01","ESC39356",null,66.3,0.113533,0,0,0.2,88.59268547999999]
["SL_MFAT","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2008-10-01","ESC39722",null,66.3,0.142485,0,0,0.2,90.89610659999998]
["SL_MFAT1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN3","2005-10-01","ESC138626",null,70,0,0,0,0.38,96.6]
["SL_MFAT1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN3","2006-10-01","ESC138991",null,70,0.026,0,0,0.38,99.1116]
["SL_MFAT1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN3","2007-10-01","ESC139356",null,70,0.052676,0,0,0.38,101.6885016]
["SL_MFAT1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN3","2008-10-01","ESC139722",null,70,0.08004558,0,0,0.38,104.33240302799997]
["SL_MFMS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2003-10-01","ESC37895",null,81.3,0,0,0,0.2,97.55999999999999]
["SL_MFMS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2004-10-01","ESC38261",null,81.3,0.029,0,0,0.2,100.38923999999999]
["SL_MFMS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2005-10-01","ESC38626",null,81.3,0.057812,0,0,0.2,103.20013872]
["SL_MFMS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2006-10-01","ESC38991",null,81.3,0.085315,0,0,0.2,105.88333139999999]
["SL_MFMS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2007-10-01","ESC39356",null,81.3,0.113533,0,0,0.2,108.63627947999998]
["SL_MFMS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2008-10-01","ESC39722",null,81.3,0.142485,0,0,0.2,111.4608366]
["SL_MFMS1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN3","2005-10-01","ESC138626",null,89.59,0,0,0,0.38,123.63419999999999]
["SL_MFMS1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN3","2006-10-01","ESC138991",null,89.59,0.026,0,0,0.38,126.8486892]
["SL_MFMS1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN3","2007-10-01","ESC139356",null,89.59,0.052676,0,0,0.38,130.14675511919998]
["SL_MFMS1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN3","2008-10-01","ESC139722",null,89.59,0.08004558,0,0,0.38,133.530571246836]
["SL_MFPC","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2003-10-01","ESC37895",null,129.8,0,0,0,0.2,155.76000000000002]
["SL_MFPC","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2004-10-01","ESC38261",null,129.8,0.029,0,0,0.2,160.27704]
["SL_MFPC","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2005-10-01","ESC38626",null,129.8,0.057812,0,0,0.2,164.76479712]
["SL_MFPC","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2006-10-01","ESC38991",null,129.8,0.085315,0,0,0.2,169.04866440000004]
["SL_MFPC","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2007-10-01","ESC39356",null,129.8,0.113533,0,0,0.2,173.44390007999996]
["SL_MFPC","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2008-10-01","ESC39722",null,129.8,0.142485,0,0,0.2,177.9534636]
["SL_MFPC1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN3","2005-10-01","ESC138626",null,140.65,0,0,0,0.38,194.09699999999998]
["SL_MFPC1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN3","2006-10-01","ESC138991",null,140.65,0.026,0,0,0.38,199.143522]
["SL_MFPC1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN3","2007-10-01","ESC139356",null,140.65,0.052676,0,0,0.38,204.321253572]
["SL_MFPC1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN3","2008-10-01","ESC139722",null,140.65,0.08004558,0,0,0.38,209.63360694126]
["SL_MSCS","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SL_MSCS","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SL_MSCS","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SL_MSCS","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SL_MSCS","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SL_MSCS","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SL_MSCS1","ESC1","SL_OHN4",null,null,"2005-10-01","ESC138626",null,1,0,0.0552,null,null,1.0552]
["SL_MSCS1","ESC1","SL_OHN4",null,null,"2006-10-01","ESC138991",null,1,0.026,0.0552,null,null,1.0826352]
["SL_MSCS1","ESC1","SL_OHN4",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.0552,null,null,1.1107837151999997]
["SL_MSCS1","ESC1","SL_OHN4",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.0552,null,null,1.1396640960159998]
["SL_MSEG","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SL_MSEG","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SL_MSEG","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SL_MSEG","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SL_MSEG","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SL_MSEG","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SL_MSEG1","ESC1","SL_OHN4",null,null,"2005-10-01","ESC138626",null,1,0,0.0552,null,null,1.0552]
["SL_MSEG1","ESC1","SL_OHN4",null,null,"2006-10-01","ESC138991",null,1,0.026,0.0552,null,null,1.0826352]
["SL_MSEG1","ESC1","SL_OHN4",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.0552,null,null,1.1107837151999997]
["SL_MSEG1","ESC1","SL_OHN4",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.0552,null,null,1.1396640960159998]
["SL_MSEQ","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SL_MSEQ","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SL_MSEQ","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SL_MSEQ","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SL_MSEQ","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SL_MSEQ","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SL_MSEQ1","ESC1","SL_OHN4",null,null,"2005-10-01","ESC138626",null,1,0,0.0552,null,null,1.0552]
["SL_MSEQ1","ESC1","SL_OHN4",null,null,"2006-10-01","ESC138991",null,1,0.026,0.0552,null,null,1.0826352]
["SL_MSEQ1","ESC1","SL_OHN4",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.0552,null,null,1.1107837151999997]
["SL_MSEQ1","ESC1","SL_OHN4",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.0552,null,null,1.1396640960159998]
["SL_MSPF","SL_OH2",{"$nulls":4},"SL_OH2",null,1,{"$nulls":4},1]
["SL_MSPF1","SL_OHN4",{"$nulls":4},"SL_OHN4",null,1,{"$nulls":4},1]
["SL_MSPS","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SL_MSPS","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SL_MSPS","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SL_MSPS","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SL_MSPS","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SL_MSPS","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SL_MSPS1","ESC1","SL_OHN4",null,null,"2005-10-01","ESC138626",null,1,0,0.0552,null,null,1.0552]
["SL_MSPS1","ESC1","SL_OHN4",null,null,"2006-10-01","ESC138991",null,1,0.026,0.0552,null,null,1.0826352]
["SL_MSPS1","ESC1","SL_OHN4",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.0552,null,null,1.1107837151999997]
["SL_MSPS1","ESC1","SL_OHN4",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.0552,null,null,1.1396640960159998]
["SL_MSPX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["SL_MSPX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["SL_MSPX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["SL_MSPX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["SL_MSPX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["SL_MSPX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["SL_MSPX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["SL_MSPX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["SL_MSPX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["SL_MSPX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["SL_MSPY",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_MSPY1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_MSSC","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SL_MSSC","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SL_MSSC","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SL_MSSC","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SL_MSSC","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SL_MSSC","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SL_MSSC1","ESC1","SL_OHN4",null,null,"2005-10-01","ESC138626",null,1,0,0.0552,null,null,1.0552]
["SL_MSSC1","ESC1","SL_OHN4",null,null,"2006-10-01","ESC138991",null,1,0.026,0.0552,null,null,1.0826352]
["SL_MSSC1","ESC1","SL_OHN4",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.0552,null,null,1.1107837151999997]
["SL_MSSC1","ESC1","SL_OHN4",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.0552,null,null,1.1396640960159998]
["SL_MSSF","SL_OH2",{"$nulls":4},"SL_OH2",null,1,{"$nulls":4},1]
["SL_MSSF1","SL_OHN4",{"$nulls":4},"SL_OHN4",null,1,{"$nulls":4},1]
["SL_MSSY",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_MSSY1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_MSTR","ESC","SL_OH1",null,null,"2003-10-01","ESC37895",null,1,0,0.2,null,null,1.2]
["SL_MSTR","ESC","SL_OH1",null,null,"2004-10-01","ESC38261",null,1,0.029,0.2,null,null,1.2348]
["SL_MSTR","ESC","SL_OH1",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.2,null,null,1.2693744]
["SL_MSTR","ESC","SL_OH1",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.2,null,null,1.302378]
["SL_MSTR","ESC","SL_OH1",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.2,null,null,1.3362395999999999]
["SL_MSTR","ESC","SL_OH1",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.2,null,null,1.370982]
["SL_MSTR1","ESC1","SL_OHN3",null,null,"2005-10-01","ESC138626",null,1,0,0.38,null,null,1.38]
["SL_MSTR1","ESC1","SL_OHN3",null,null,"2006-10-01","ESC138991",null,1,0.026,0.38,null,null,1.41588]
["SL_MSTR1","ESC1","SL_OHN3",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.38,null,null,1.4526928799999999]
["SL_MSTR1","ESC1","SL_OHN3",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.38,null,null,1.4904629003999998]
["SL_MSXA",{"$nulls":5},"",{"$nulls":6},0]
["SL_MSXX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["SL_MSXX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["SL_MSXX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["SL_MSXX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["SL_MSXX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["SL_MSXX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["SL_MSXX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["SL_MSXX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["SL_MSXX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["SL_MSXX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["SL_MTRL","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SL_MTRL","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SL_MTRL","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SL_MTRL","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SL_MTRL","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SL_MTRL","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SL_MTRL1","ESC1","SL_OHN4",null,null,"2005-10-01","ESC138626",null,1,0,0.0552,null,null,1.0552]
["SL_MTRL1","ESC1","SL_OHN4",null,null,"2006-10-01","ESC138991",null,1,0.026,0.0552,null,null,1.0826352]
["SL_MTRL1","ESC1","SL_OHN4",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.0552,null,null,1.1107837151999997]
["SL_MTRL1","ESC1","SL_OHN4",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.0552,null,null,1.1396640960159998]
["SL_MVE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_MVE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_MVE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_MVE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_MVE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_MVE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_MVE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,54.62,0,0.305,0.21,0.38,119.02184117999998]
["SL_MVE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,54.62,0.026,0.305,0.21,0.38,122.11640905067998]
["SL_MVE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,54.62,0.052676,0.305,0.21,0.38,125.29143568599764]
["SL_MVE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,54.62,0.08004558,0.305,0.21,0.38,128.54901348992095]
["SL_OE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,58.14,0,0.29,0.215,0.2,109.3508748]
["SL_OE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,58.14,0.029,0.29,0.215,0.2,112.52205016919999]
["SL_OE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,58.14,0.057812,0.29,0.215,0.2,115.6726675739376]
["SL_OE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,58.14,0.085315,0.29,0.215,0.2,118.680144683562]
["SL_OE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,58.14,0.113533,0.29,0.215,0.2,121.7658076686684]
["SL_OE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,58.14,0.142485,0.29,0.215,0.2,124.931734195878]
["SL_OE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,58.14,0,0.305,0.21,0.38,126.69223445999998]
["SL_OE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,58.14,0.026,0.305,0.21,0.38,129.98623255596]
["SL_OE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,58.14,0.052676,0.305,0.21,0.38,133.36587460241495]
["SL_OE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,58.14,0.08004558,0.305,0.21,0.38,136.83338784884668]
["SL_OT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,31.83,0,0.29,0.215,0.2,59.866500599999995]
["SL_OT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,31.83,0.029,0.29,0.215,0.2,61.60262911739999]
["SL_OT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,31.83,0.057812,0.29,0.215,0.2,63.327502732687186]
["SL_OT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,31.83,0.085315,0.29,0.215,0.2,64.974011098689]
["SL_OT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,31.83,0.113533,0.29,0.215,0.2,66.66332401261978]
["SL_OT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,31.83,0.142485,0.29,0.215,0.2,68.396578937991]
["SL_OT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,31.83,0,0.305,0.21,0.38,69.36040286999999]
["SL_OT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,31.83,0.026,0.305,0.21,0.38,71.16377334461997]
["SL_OT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,31.83,0.052676,0.305,0.21,0.38,73.0140314515801]
["SL_OT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,31.83,0.08004558,0.305,0.21,0.38,74.91239654676279]
["SL_PCCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,33.86,0,0.29,0.215,0.2,63.6845652]
["SL_PCCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,33.86,0.029,0.29,0.215,0.2,65.53141759079999]
["SL_PCCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,33.86,0.057812,0.29,0.215,0.2,67.3662972833424]
["SL_PCCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,33.86,0.085315,0.29,0.215,0.2,69.117813880038]
["SL_PCCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,33.86,0.113533,0.29,0.215,0.2,70.9148649408516]
["SL_PCCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,33.86,0.142485,0.29,0.215,0.2,72.75866047252201]
["SL_PCCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,33.86,0,0.305,0.21,0.38,73.78395354]
["SL_PCCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,33.86,0.026,0.305,0.21,0.38,75.70233633203999]
["SL_PCCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,33.86,0.052676,0.305,0.21,0.38,77.67059707667303]
["SL_PCCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,33.86,0.08004558,0.305,0.21,0.38,79.69003289580235]
["SL_PCE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,58.14,0,0.29,0.215,0.2,109.3508748]
["SL_PCE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,58.14,0.029,0.29,0.215,0.2,112.52205016919999]
["SL_PCE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,58.14,0.057812,0.29,0.215,0.2,115.6726675739376]
["SL_PCE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,58.14,0.085315,0.29,0.215,0.2,118.680144683562]
["SL_PCE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,58.14,0.113533,0.29,0.215,0.2,121.7658076686684]
["SL_PCE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,58.14,0.142485,0.29,0.215,0.2,124.931734195878]
["SL_PCE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,58.14,0,0.305,0.21,0.38,126.69223445999998]
["SL_PCE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,58.14,0.026,0.305,0.21,0.38,129.98623255596]
["SL_PCE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,58.14,0.052676,0.305,0.21,0.38,133.36587460241495]
["SL_PCE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,58.14,0.08004558,0.305,0.21,0.38,136.83338784884668]
["SL_PCEF","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,31.83,0,0.29,0.215,0.2,59.866500599999995]
["SL_PCEF","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,31.83,0.029,0.29,0.215,0.2,61.60262911739999]
["SL_PCEF","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,31.83,0.057812,0.29,0.215,0.2,63.327502732687186]
["SL_PCEF","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,31.83,0.085315,0.29,0.215,0.2,64.974011098689]
["SL_PCEF","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,31.83,0.113533,0.29,0.215,0.2,66.66332401261978]
["SL_PCEF","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,31.83,0.142485,0.29,0.215,0.2,68.396578937991]
["SL_PCEF1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,31.83,0,0.305,0.21,0.38,69.36040286999999]
["SL_PCEF1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,31.83,0.026,0.305,0.21,0.38,71.16377334461997]
["SL_PCEF1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,31.83,0.052676,0.305,0.21,0.38,73.0140314515801]
["SL_PCEF1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,31.83,0.08004558,0.305,0.21,0.38,74.91239654676279]
["SL_PCT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,31.83,0,0.29,0.215,0.2,59.866500599999995]
["SL_PCT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,31.83,0.029,0.29,0.215,0.2,61.60262911739999]
["SL_PCT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,31.83,0.057812,0.29,0.215,0.2,63.327502732687186]
["SL_PCT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,31.83,0.085315,0.29,0.215,0.2,64.974011098689]
["SL_PCT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,31.83,0.113533,0.29,0.215,0.2,66.66332401261978]
["SL_PCT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,31.83,0.142485,0.29,0.215,0.2,68.396578937991]
["SL_PCT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,31.83,0,0.305,0.21,0.38,69.36040286999999]
["SL_PCT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,31.83,0.026,0.305,0.21,0.38,71.16377334461997]
["SL_PCT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,31.83,0.052676,0.305,0.21,0.38,73.0140314515801]
["SL_PCT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,31.83,0.08004558,0.305,0.21,0.38,74.91239654676279]
["SL_PEX","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,40.7,0,0.29,0.215,0.2,76.54937400000001]
["SL_PEX","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,40.7,0.029,0.29,0.215,0.2,78.769305846]
["SL_PEX","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,40.7,0.057812,0.29,0.215,0.2,80.97484640968801]
["SL_PEX","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,40.7,0.085315,0.29,0.215,0.2,83.08018384281002]
["SL_PEX","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,40.7,0.113533,0.29,0.215,0.2,85.24025407834199]
["SL_PEX","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,40.7,0.142485,0.29,0.215,0.2,87.45651155439002]
["SL_PEX1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,40.7,0,0.305,0.21,0.38,88.6889223]
["SL_PEX1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,40.7,0.026,0.305,0.21,0.38,90.9948342798]
["SL_PEX1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,40.7,0.052676,0.305,0.21,0.38,93.3606999710748]
["SL_PEX1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,40.7,0.08004558,0.305,0.21,0.38,95.78807852507842]
["SL_PHH","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,45.68,0,0.29,0.215,0.2,85.9158576]
["SL_PHH","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,45.68,0.029,0.29,0.215,0.2,88.4074174704]
["SL_PHH","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,45.68,0.057812,0.29,0.215,0.2,90.88282515957121]
["SL_PHH","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,45.68,0.085315,0.29,0.215,0.2,93.245768991144]
["SL_PHH","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,45.68,0.113533,0.29,0.215,0.2,95.67014266090081]
["SL_PHH","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,45.68,0.142485,0.29,0.215,0.2,98.15757857013601]
["SL_PHH1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,49.4,0,0.305,0.21,0.38,107.64699659999998]
["SL_PHH1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,49.4,0.026,0.305,0.21,0.38,110.44581851159998]
["SL_PHH1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,49.4,0.052676,0.305,0.21,0.38,113.31740979290157]
["SL_PHH1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,49.4,0.08004558,0.305,0.21,0.38,116.263662878105]
["SL_PHPD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,36.17,0,0.29,0.215,0.2,68.0292594]
["SL_PHPD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,36.17,0.029,0.29,0.215,0.2,70.0021079226]
["SL_PHPD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,36.17,0.057812,0.29,0.215,0.2,71.96216694443281]
["SL_PHPD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,36.17,0.085315,0.29,0.215,0.2,73.83317566571101]
["SL_PHPD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,36.17,0.113533,0.29,0.215,0.2,75.7528253074602]
["SL_PHPD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,36.17,0.142485,0.29,0.215,0.2,77.722408425609]
["SL_PHPD1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,36.17,0,0.305,0.21,0.38,78.81764912999999]
["SL_PHPD1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,36.17,0.026,0.305,0.21,0.38,80.86690800737999]
["SL_PHPD1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,36.17,0.052676,0.305,0.21,0.38,82.96944761557188]
["SL_PHPD1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,36.17,0.08004558,0.305,0.21,0.38,85.12665356884733]
["SL_PHPU","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,63.33,0,0.305,0.21,0.38,138.00170636999997]
["SL_PHPU","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,63.33,0.026,0.305,0.21,0.38,141.58975073562]
["SL_PHPU","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,63.33,0.052676,0.305,0.21,0.38,145.27108425474609]
["SL_PHPU","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,63.33,0.08004558,0.305,0.21,0.38,149.0481329973763]
["SL_PHS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,37.62,0,0.29,0.215,0.2,70.7564484]
["SL_PHS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,37.62,0.029,0.29,0.215,0.2,72.80838540359998]
["SL_PHS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,37.62,0.057812,0.29,0.215,0.2,74.84702019490081]
["SL_PHS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,37.62,0.085315,0.29,0.215,0.2,76.79303479524602]
["SL_PHS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,37.62,0.113533,0.29,0.215,0.2,78.78964025619719]
["SL_PHS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,37.62,0.142485,0.29,0.215,0.2,80.83818095027401]
["SL_PHS1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,37.62,0,0.305,0.21,0.38,81.97732817999999]
["SL_PHS1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,37.62,0.026,0.305,0.21,0.38,84.10873871267998]
["SL_PHS1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,37.62,0.052676,0.305,0.21,0.38,86.29556591920965]
["SL_PHS1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,37.62,0.08004558,0.305,0.21,0.38,88.53925096101842]
["SL_PHSS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,47.88,0,0.29,0.215,0.2,90.05366160000001]
["SL_PHSS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,47.88,0.029,0.29,0.215,0.2,92.66521778639999]
["SL_PHSS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,47.88,0.057812,0.29,0.215,0.2,95.25984388441923]
["SL_PHSS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,47.88,0.085315,0.29,0.215,0.2,97.736589739404]
["SL_PHSS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,47.88,0.113533,0.29,0.215,0.2,100.27772396243279]
["SL_PHSS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,47.88,0.142485,0.29,0.215,0.2,102.884957573076]
["SL_PHSS1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,47.88,0,0.305,0.21,0.38,104.33478132]
["SL_PHSS1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,47.88,0.026,0.305,0.21,0.38,107.04748563432]
["SL_PHSS1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,47.88,0.052676,0.305,0.21,0.38,109.8307202608123]
["SL_PHSS1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,47.88,0.08004558,0.305,0.21,0.38,112.68631940493255]
["SL_PM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,63.8,0,0.29,0.215,0.2,119.99631599999998]
["SL_PM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,63.8,0.029,0.29,0.215,0.2,123.476209164]
["SL_PM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,63.8,0.057812,0.29,0.215,0.2,126.933543020592]
["SL_PM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,63.8,0.085315,0.29,0.215,0.2,130.23380169954004]
["SL_PM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,63.8,0.113533,0.29,0.215,0.2,133.61985774442797]
["SL_PM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,63.8,0.142485,0.29,0.215,0.2,137.09399108526]
["SL_PM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,83.63,0,0.305,0.21,0.38,182.23721306999997]
["SL_PM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,83.63,0.026,0.305,0.21,0.38,186.97538060981995]
["SL_PM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,83.63,0.052676,0.305,0.21,0.38,191.83674050567527]
["SL_PM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,83.63,0.08004558,0.305,0.21,0.38,196.82449648777168]
["SL_POWB",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_POWB1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_QAO","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_QAO","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_QAO","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_QAO","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_QAO","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_QAO","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_QAO1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,35.53,0,0.305,0.21,0.38,77.42303216999998]
["SL_QAO1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,35.53,0.026,0.305,0.21,0.38,79.43603100642]
["SL_QAO1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,35.53,0.052676,0.305,0.21,0.38,81.5013678125869]
["SL_QAO1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,35.53,0.08004558,0.305,0.21,0.38,83.6204036854063]
["SL_SEE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_SEE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_SEE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_SEE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_SEE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_SEE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_SEE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,54.62,0,0.305,0.21,0.38,119.02184117999998]
["SL_SEE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,54.62,0.026,0.305,0.21,0.38,122.11640905067998]
["SL_SEE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,54.62,0.052676,0.305,0.21,0.38,125.29143568599764]
["SL_SEE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,54.62,0.08004558,0.305,0.21,0.38,128.54901348992095]
["SL_SEEM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_SEEM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_SEEM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_SEEM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_SEEM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_SEEM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_SEEM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,54.62,0,0.305,0.21,0.38,119.02184117999998]
["SL_SEEM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,54.62,0.026,0.305,0.21,0.38,122.11640905067998]
["SL_SEEM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,54.62,0.052676,0.305,0.21,0.38,125.29143568599764]
["SL_SEEM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,54.62,0.08004558,0.305,0.21,0.38,128.54901348992095]
["SL_SEL","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2003-10-01","ESC37895",null,38,0,0,0,0.2,45.6]
["SL_SEL","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2004-10-01","ESC38261",null,38,0.029,0,0,0.2,46.922399999999996]
["SL_SEL","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2005-10-01","ESC38626",null,38,0.057812,0,0,0.2,48.236227199999995]
["SL_SEL","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2006-10-01","ESC38991",null,38,0.085315,0,0,0.2,49.490364]
["SL_SEL","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2007-10-01","ESC39356",null,38,0.113533,0,0,0.2,50.7771048]
["SL_SEL","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2008-10-01","ESC39722",null,38,0.142485,0,0,0.2,52.09731599999999]
["SL_SEL1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN3","2005-10-01","ESC138626",null,38,0,0,0,0.38,52.44]
["SL_SEL1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN3","2006-10-01","ESC138991",null,38,0.026,0,0,0.38,53.803439999999995]
["SL_SEL1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN3","2007-10-01","ESC139356",null,38,0.052676,0,0,0.38,55.20232944]
["SL_SEL1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN3","2008-10-01","ESC139722",null,38,0.08004558,0,0,0.38,56.63759021519999]
["SL_SEPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,32.28,0,0.29,0.215,0.2,60.71286960000001]
["SL_SEPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,32.28,0.029,0.29,0.215,0.2,62.47354281839999]
["SL_SEPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,32.28,0.057812,0.29,0.215,0.2,64.2228020173152]
["SL_SEPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,32.28,0.085315,0.29,0.215,0.2,65.892588069924]
["SL_SEPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,32.28,0.113533,0.29,0.215,0.2,67.60578382429681]
["SL_SEPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,32.28,0.142485,0.29,0.215,0.2,69.363542824956]
["SL_SEPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,32.28,0,0.305,0.21,0.38,70.34099291999999]
["SL_SEPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,32.28,0.026,0.305,0.21,0.38,72.16985873591999]
["SL_SEPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,32.28,0.052676,0.305,0.21,0.38,74.0462750630539]
["SL_SEPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,32.28,0.08004558,0.305,0.21,0.38,75.97147849605729]
["SL_SRA","ESC","SL_OH1",null,null,"2003-10-01","ESC37895",null,20.83,0,0.2,null,null,24.996]
["SL_SRA","ESC","SL_OH1",null,null,"2004-10-01","ESC38261",null,20.83,0.029,0.2,null,null,25.720883999999995]
["SL_SRA","ESC","SL_OH1",null,null,"2005-10-01","ESC38626",null,20.83,0.057812,0.2,null,null,26.441068751999996]
["SL_SRA","ESC","SL_OH1",null,null,"2006-10-01","ESC38991",null,20.83,0.085315,0.2,null,null,27.128533739999998]
["SL_SRA","ESC","SL_OH1",null,null,"2007-10-01","ESC39356",null,20.83,0.113533,0.2,null,null,27.833870867999995]
["SL_SRA","ESC","SL_OH1",null,null,"2008-10-01","ESC39722",null,20.83,0.142485,0.2,null,null,28.557555059999995]
["SL_SRA1","ESC1","SL_OHN3",null,null,"2005-10-01","ESC138626",null,20.83,0,0.38,null,null,28.745399999999997]
["SL_SRA1","ESC1","SL_OHN3",null,null,"2006-10-01","ESC138991",null,20.83,0.026,0.38,null,null,29.492780399999994]
["SL_SRA1","ESC1","SL_OHN3",null,null,"2007-10-01","ESC139356",null,20.83,0.052676,0.38,null,null,30.259592690399995]
["SL_SRA1","ESC1","SL_OHN3",null,null,"2008-10-01","ESC139722",null,20.83,0.08004558,0.38,null,null,31.046342215331993]
["SL_STUP",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_STUP1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_TMUC","ESC","SL_FRING1","SL_LEAV1","SL_OH1","2003-10-01","ESC37895",null,60.55,0,1,0,0.2,145.32]
["SL_TMUC","ESC","SL_FRING1","SL_LEAV1","SL_OH1","2004-10-01","ESC38261",null,60.55,0.029,1,0,0.2,149.53427999999997]
["SL_TMUC","ESC","SL_FRING1","SL_LEAV1","SL_OH1","2005-10-01","ESC38626",null,60.55,0.057812,1,0,0.2,153.72123983999998]
["SL_TMUC","ESC","SL_FRING1","SL_LEAV1","SL_OH1","2006-10-01","ESC38991",null,60.55,0.085315,1,0,0.2,157.7179758]
["SL_TMUC","ESC","SL_FRING1","SL_LEAV1","SL_OH1","2007-10-01","ESC39356",null,60.55,0.113533,1,0,0.2,161.81861555999998]
["SL_TMUC","ESC","SL_FRING1","SL_LEAV1","SL_OH1","2008-10-01","ESC39722",null,60.55,0.142485,1,0,0.2,166.02592019999997]
["SL_TMUC1","ESC1","SL_FRING1","SL_LEAV1","SL_OHN3","2005-10-01","ESC138626",null,60.55,0,1,0,0.38,167.11799999999997]
["SL_TMUC1","ESC1","SL_FRING1","SL_LEAV1","SL_OHN3","2006-10-01","ESC138991",null,60.55,0.026,1,0,0.38,171.463068]
["SL_TMUC1","ESC1","SL_FRING1","SL_LEAV1","SL_OHN3","2007-10-01","ESC139356",null,60.55,0.052676,1,0,0.38,175.92110776799998]
["SL_TMUC1","ESC1","SL_FRING1","SL_LEAV1","SL_OHN3","2008-10-01","ESC139722",null,60.55,0.08004558,1,0,0.38,180.49505723843995]
["SL_TMUE","ESC","SL_OH1",null,null,"2003-10-01","ESC37895",null,77.99,0,0.2,null,null,93.588]
["SL_TMUE","ESC","SL_OH1",null,null,"2004-10-01","ESC38261",null,77.99,0.029,0.2,null,null,96.30205199999999]
["SL_TMUE","ESC","SL_OH1",null,null,"2005-10-01","ESC38626",null,77.99,0.057812,0.2,null,null,98.998509456]
["SL_TMUE","ESC","SL_OH1",null,null,"2006-10-01","ESC38991",null,77.99,0.085315,0.2,null,null,101.57246021999998]
["SL_TMUE","ESC","SL_OH1",null,null,"2007-10-01","ESC39356",null,77.99,0.113533,0.2,null,null,104.21332640399999]
["SL_TMUE","ESC","SL_OH1",null,null,"2008-10-01","ESC39722",null,77.99,0.142485,0.2,null,null,106.92288617999999]
["SL_TMUE1","ESC1","SL_OHN3",null,null,"2005-10-01","ESC138626",null,77.99,0,0.38,null,null,107.62619999999998]
["SL_TMUE1","ESC1","SL_OHN3",null,null,"2006-10-01","ESC138991",null,77.99,0.026,0.38,null,null,110.4244812]
["SL_TMUE1","ESC1","SL_OHN3",null,null,"2007-10-01","ESC139356",null,77.99,0.052676,0.38,null,null,113.29551771119998]
["SL_TMUE1","ESC1","SL_OHN3",null,null,"2008-10-01","ESC139722",null,77.99,0.08004558,0.38,null,null,116.24120160219599]
["SL_TMUI","ESC","SL_OH1",null,null,"2003-10-01","ESC37895",null,61.62,0,0.2,null,null,73.94399999999999]
["SL_TMUI","ESC","SL_OH1",null,null,"2004-10-01","ESC38261",null,61.62,0.029,0.2,null,null,76.08837599999998]
["SL_TMUI","ESC","SL_OH1",null,null,"2005-10-01","ESC38626",null,61.62,0.057812,0.2,null,null,78.218850528]
["SL_TMUI","ESC","SL_OH1",null,null,"2006-10-01","ESC38991",null,61.62,0.085315,0.2,null,null,80.25253235999999]
["SL_TMUI","ESC","SL_OH1",null,null,"2007-10-01","ESC39356",null,61.62,0.113533,0.2,null,null,82.33908415199998]
["SL_TMUI","ESC","SL_OH1",null,null,"2008-10-01","ESC39722",null,61.62,0.142485,0.2,null,null,84.47991083999999]
["SL_TMUI1","ESC1","SL_OHN3",null,null,"2005-10-01","ESC138626",null,61.62,0,0.38,null,null,85.03559999999999]
["SL_TMUI1","ESC1","SL_OHN3",null,null,"2006-10-01","ESC138991",null,61.62,0.026,0.38,null,null,87.24652559999998]
["SL_TMUI1","ESC1","SL_OHN3",null,null,"2007-10-01","ESC139356",null,61.62,0.052676,0.38,null,null,89.51493526559997]
["SL_TMUI1","ESC1","SL_OHN3",null,null,"2008-10-01","ESC139722",null,61.62,0.08004558,0.38,null,null,91.84232392264798]
["SL_TMUO","ESC","SL_OH1",null,null,"2003-10-01","ESC37895",null,64.45,0,0.2,null,null,77.34]
["SL_TMUO","ESC","SL_OH1",null,null,"2004-10-01","ESC38261",null,64.45,0.029,0.2,null,null,79.58286]
["SL_TMUO","ESC","SL_OH1",null,null,"2005-10-01","ESC38626",null,64.45,0.057812,0.2,null,null,81.81118008]
["SL_TMUO","ESC","SL_OH1",null,null,"2006-10-01","ESC38991",null,64.45,0.085315,0.2,null,null,83.9382621]
["SL_TMUO","ESC","SL_OH1",null,null,"2007-10-01","ESC39356",null,64.45,0.113533,0.2,null,null,86.12064222]
["SL_TMUO","ESC","SL_OH1",null,null,"2008-10-01","ESC39722",null,64.45,0.142485,0.2,null,null,88.35978990000001]
["SL_TMUO1","ESC1","SL_OHN3",null,null,"2005-10-01","ESC138626",null,64.45,0,0.38,null,null,88.941]
["SL_TMUO1","ESC1","SL_OHN3",null,null,"2006-10-01","ESC138991",null,64.45,0.026,0.38,null,null,91.253466]
["SL_TMUO1","ESC1","SL_OHN3",null,null,"2007-10-01","ESC139356",null,64.45,0.052676,0.38,null,null,93.62605611599999]
["SL_TMUO1","ESC1","SL_OHN3",null,null,"2008-10-01","ESC139722",null,64.45,0.08004558,0.38,null,null,96.06033393078]
["SL_TMUP","ESC","SL_OH1",null,null,"2003-10-01","ESC37895",null,74.69,0,0.2,null,null,89.628]
["SL_TMUP","ESC","SL_OH1",null,null,"2004-10-01","ESC38261",null,74.69,0.029,0.2,null,null,92.227212]
["SL_TMUP","ESC","SL_OH1",null,null,"2005-10-01","ESC38626",null,74.69,0.057812,0.2,null,null,94.80957393599998]
["SL_TMUP","ESC","SL_OH1",null,null,"2006-10-01","ESC38991",null,74.69,0.085315,0.2,null,null,97.27461282]
["SL_TMUP","ESC","SL_OH1",null,null,"2007-10-01","ESC39356",null,74.69,0.113533,0.2,null,null,99.80373572399999]
["SL_TMUP","ESC","SL_OH1",null,null,"2008-10-01","ESC39722",null,74.69,0.142485,0.2,null,null,102.39864558]
["SL_TMUP1","ESC1","SL_OHN3",null,null,"2005-10-01","ESC138626",null,74.69,0,0.38,null,null,103.0722]
["SL_TMUP1","ESC1","SL_OHN3",null,null,"2006-10-01","ESC138991",null,74.69,0.026,0.38,null,null,105.75207719999999]
["SL_TMUP1","ESC1","SL_OHN3",null,null,"2007-10-01","ESC139356",null,74.69,0.052676,0.38,null,null,108.50163120719998]
["SL_TMUP1","ESC1","SL_OHN3",null,null,"2008-10-01","ESC139722",null,74.69,0.08004558,0.38,null,null,111.32267403087599]
["SL_TMUW","ESC","SL_OH1",null,null,"2003-10-01","ESC37895",null,61.62,0,0.2,null,null,73.94399999999999]
["SL_TMUW","ESC","SL_OH1",null,null,"2004-10-01","ESC38261",null,61.62,0.029,0.2,null,null,76.08837599999998]
["SL_TMUW","ESC","SL_OH1",null,null,"2005-10-01","ESC38626",null,61.62,0.057812,0.2,null,null,78.218850528]
["SL_TMUW","ESC","SL_OH1",null,null,"2006-10-01","ESC38991",null,61.62,0.085315,0.2,null,null,80.25253235999999]
["SL_TMUW","ESC","SL_OH1",null,null,"2007-10-01","ESC39356",null,61.62,0.113533,0.2,null,null,82.33908415199998]
["SL_TMUW","ESC","SL_OH1",null,null,"2008-10-01","ESC39722",null,61.62,0.142485,0.2,null,null,84.47991083999999]
["SL_TMUW1","ESC1","SL_OHN3",null,null,"2005-10-01","ESC138626",null,61.62,0,0.38,null,null,85.03559999999999]
["SL_TMUW1","ESC1","SL_OHN3",null,null,"2006-10-01","ESC138991",null,61.62,0.026,0.38,null,null,87.24652559999998]
["SL_TMUW1","ESC1","SL_OHN3",null,null,"2007-10-01","ESC139356",null,61.62,0.052676,0.38,null,null,89.51493526559997]
["SL_TMUW1","ESC1","SL_OHN3",null,null,"2008-10-01","ESC139722",null,61.62,0.08004558,0.38,null,null,91.84232392264798]
["SL_TSM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_TSM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_TSM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_TSM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_TSM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_TSM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_TSM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,54.62,0,0.305,0.21,0.38,119.02184117999998]
["SL_TSM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,54.62,0.026,0.305,0.21,0.38,122.11640905067998]
["SL_TSM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,54.62,0.052676,0.305,0.21,0.38,125.29143568599764]
["SL_TSM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,54.62,0.08004558,0.305,0.21,0.38,128.54901348992095]
["SL_UPGR",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_UPGR1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_UTR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_UTR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_UTR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_UTR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_UTR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_UTR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_UTR1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2005-10-01","ESC138626",null,54.62,0,0.305,0.21,0.38,119.02184117999998]
["SL_UTR1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2006-10-01","ESC138991",null,54.62,0.026,0.305,0.21,0.38,122.11640905067998]
["SL_UTR1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2007-10-01","ESC139356",null,54.62,0.052676,0.305,0.21,0.38,125.29143568599764]
["SL_UTR1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN3","2008-10-01","ESC139722",null,54.62,0.08004558,0.305,0.21,0.38,128.54901348992095]
["SPR",{"$nulls":5},"",{"$nulls":6},0]
[null,"END",{"$nulls":4},"END",{"$nulls":6},0]

{"sheet":"tecclc","index":2,"n_rows":1664,"n_cols":14,"rows_kept":1664,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["TEC3CLC ","TEC3CLC ","TEC3CLC ","TEC3CLC ","TEC3CLC ","TEC3CLC ","TEC3CLC ","TEC3CLC ","TEC3CLC ","TEC3CLC ","TEC3CLC ","TEC3CLC ","TEC3CLC ","TEC3CLC "]
["AA_MSEG","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AA_MSEG","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AA_MSEG","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AA_MSEG","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AA_MSEG","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AA_MSEG","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AA_MSEG1","ESC1","AN_OH3",null,null,"2005-10-01","ESC138626",null,1,0,0,null,null,1]
["AA_MSEG1","ESC1","AN_OH3",null,null,"2006-10-01","ESC138991",null,1,0.026,0,null,null,1.026]
["AA_MSEG1","ESC1","AN_OH3",null,null,"2007-10-01","ESC139356",null,1,0.052676,0,null,null,1.052676]
["AA_MSEG1","ESC1","AN_OH3",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0,null,null,1.08004558]
["AA_MSEQ","ESC","AN_OH4",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AA_MSEQ","ESC","AN_OH4",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AA_MSEQ","ESC","AN_OH4",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AA_MSEQ","ESC","AN_OH4",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AA_MSEQ","ESC","AN_OH4",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AA_MSEQ","ESC","AN_OH4",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AA_MSEQ1","ESC1","AN_OH4",null,null,"2005-10-01","ESC138626",null,1,0,0,null,null,1]
["AA_MSEQ1","ESC1","AN_OH4",null,null,"2006-10-01","ESC138991",null,1,0.026,0,null,null,1.026]
["AA_MSEQ1","ESC1","AN_OH4",null,null,"2007-10-01","ESC139356",null,1,0.052676,0,null,null,1.052676]
["AA_MSEQ1","ESC1","AN_OH4",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0,null,null,1.08004558]
["AA_MSPS","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,null,0,0,null,null,0]
["AA_MSPS","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,null,0.029,0,null,null,0]
["AA_MSPS","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,null,0.057812,0,null,null,0]
["AA_MSPS","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,null,0.085315,0,null,null,0]
["AA_MSPS","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,null,0.113533,0,null,null,0]
["AA_MSPS","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,null,0.142485,0,null,null,0]
["AA_MSSC","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AA_MSSC","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AA_MSSC","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AA_MSSC","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AA_MSSC","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AA_MSSC","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AA_MSSC1","ESC1","AN_OH3",null,null,"2005-10-01","ESC138626",null,1,0,0,null,null,1]
["AA_MSSC1","ESC1","AN_OH3",null,null,"2006-10-01","ESC138991",null,1,0.026,0,null,null,1.026]
["AA_MSSC1","ESC1","AN_OH3",null,null,"2007-10-01","ESC139356",null,1,0.052676,0,null,null,1.052676]
["AA_MSSC1","ESC1","AN_OH3",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0,null,null,1.08004558]
["AA_MSSF","AN_OH3",{"$nulls":4},"AN_OH3",{"$nulls":6},1]
["AA_MSXX","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["AA_MSXX","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["AA_MSXX","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["AA_MSXX","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["AA_MSXX","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["AA_MSXX","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["ANL_LABOR","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,null,0,0.257,0.026,0,0]
["ANL_LABOR","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,null,0.026,0.257,0.026,0,0]
["ANL_LABOR","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,null,0.052676,0.257,0.026,0,0]
["ANL_LABOR","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,null,0.08004558,0.257,0.026,0,0]
["ANL_NON-LABOR","ESC1","AN_OH3",null,null,"2005-10-01","ESC138626",null,null,0,0,null,null,0]
["ANL_NON-LABOR","ESC1","AN_OH3",null,null,"2006-10-01","ESC138991",null,null,0.026,0,null,null,0]
["ANL_NON-LABOR","ESC1","AN_OH3",null,null,"2007-10-01","ESC139356",null,null,0.052676,0,null,null,0]
["ANL_NON-LABOR","ESC1","AN_OH3",null,null,"2008-10-01","ESC139722",null,null,0.08004558,0,null,null,0]
["ANL_SHOPS","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,null,0,0.257,0.026,0,0]
["ANL_SHOPS","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,null,0.026,0.257,0.026,0,0]
["ANL_SHOPS","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,null,0.052676,0.257,0.026,0,0]
["ANL_SHOPS","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,null,0.08004558,0.257,0.026,0,0]
["ANL_TRAVEL","ESC1","AN_OH1",null,null,"2005-10-01","ESC138626",null,null,0,0.3224,null,null,0]
["ANL_TRAVEL","ESC1","AN_OH1",null,null,"2006-10-01","ESC138991",null,null,0.026,0.3224,null,null,0]
["ANL_TRAVEL","ESC1","AN_OH1",null,null,"2007-10-01","ESC139356",null,null,0.052676,0.3224,null,null,0]
["ANL_TRAVEL","ESC1","AN_OH1",null,null,"2008-10-01","ESC139722",null,null,0.08004558,0.3224,null,null,0]
["AN_ADMN","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,63.24,0,0.3224,null,null,83.62857600000001]
["AN_ADMN","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,63.24,0.029,0.3224,null,null,86.053804704]
["AN_ADMN","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,63.24,0.057812,0.3224,null,null,88.463311235712]
["AN_ADMN","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,63.24,0.085315,0.3224,null,null,90.76334796144]
["AN_ADMN","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,63.24,0.113533,0.3224,null,null,93.12317911900799]
["AN_ADMN","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,63.24,0.142485,0.3224,null,null,95.54439365136]
["AN_ADMN1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.257,0.026,0,107.70134382000002]
["AN_ADMN1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.257,0.026,0,110.50157875932003]
["AN_ADMN1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.257,0.026,0,113.37461980706233]
["AN_ADMN1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.257,0.026,0,116.32236035285133]
["AN_AW1","ESC1","AN_OH3",null,null,"2005-10-01","ESC138626",null,1,0,0,null,null,1]
["AN_AW1","ESC1","AN_OH3",null,null,"2006-10-01","ESC138991",null,1,0.026,0,null,null,1.026]
["AN_AW1","ESC1","AN_OH3",null,null,"2007-10-01","ESC139356",null,1,0.052676,0,null,null,1.052676]
["AN_AW1","ESC1","AN_OH3",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0,null,null,1.08004558]
["AN_AWARD","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AN_AWARD","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AN_AWARD","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AN_AWARD","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AN_AWARD","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AN_AWARD","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AN_AWFX","AN_OH3",{"$nulls":4},"AN_OH3",{"$nulls":6},0]
["AN_AWXX","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["AN_AWXX","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["AN_AWXX","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["AN_AWXX","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["AN_AWXX","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["AN_AWXX","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["AN_CCA","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,67.43,0,0.3224,null,null,89.16943200000001]
["AN_CCA","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,67.43,0.029,0.3224,null,null,91.75534552799999]
["AN_CCA","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,67.43,0.057812,0.3224,null,null,94.32449520278401]
["AN_CCA","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,67.43,0.085315,0.3224,null,null,96.77692209108002]
["AN_CCA","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,67.43,0.113533,0.3224,null,null,99.293105123256]
["AN_CCA","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,67.43,0.142485,0.3224,null,null,101.87473851852002]
["AN_CCA1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.257,0.026,0,107.70134382000002]
["AN_CCA1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.257,0.026,0,110.50157875932003]
["AN_CCA1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.257,0.026,0,113.37461980706233]
["AN_CCA1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.257,0.026,0,116.32236035285133]
["AN_CE","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,67.43,0,0.3224,null,null,89.16943200000001]
["AN_CE","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,67.43,0.029,0.3224,null,null,91.75534552799999]
["AN_CE","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,67.43,0.057812,0.3224,null,null,94.32449520278401]
["AN_CE","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,67.43,0.085315,0.3224,null,null,96.77692209108002]
["AN_CE","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,67.43,0.113533,0.3224,null,null,99.293105123256]
["AN_CE","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,67.43,0.142485,0.3224,null,null,101.87473851852002]
["AN_CE1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.257,0.026,0,107.70134382000002]
["AN_CE1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.257,0.026,0,110.50157875932003]
["AN_CE1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.257,0.026,0,113.37461980706233]
["AN_CE1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.257,0.026,0,116.32236035285133]
["AN_CP","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,67.43,0,0.3224,null,null,89.16943200000001]
["AN_CP","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,67.43,0.029,0.3224,null,null,91.75534552799999]
["AN_CP","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,67.43,0.057812,0.3224,null,null,94.32449520278401]
["AN_CP","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,67.43,0.085315,0.3224,null,null,96.77692209108002]
["AN_CP","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,67.43,0.113533,0.3224,null,null,99.293105123256]
["AN_CP","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,67.43,0.142485,0.3224,null,null,101.87473851852002]
["AN_CP1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.257,0.026,0,107.70134382000002]
["AN_CP1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.257,0.026,0,110.50157875932003]
["AN_CP1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.257,0.026,0,113.37461980706233]
["AN_CP1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.257,0.026,0,116.32236035285133]
["AN_CT","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,42.99,0,0.3224,null,null,56.849976000000005]
["AN_CT","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,42.99,0.029,0.3224,null,null,58.498625303999994]
["AN_CT","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,42.99,0.057812,0.3224,null,null,60.136586812512]
["AN_CT","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,42.99,0.085315,0.3224,null,null,61.70013170244001]
["AN_CT","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,42.99,0.113533,0.3224,null,null,63.30432432520799]
["AN_CT","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,42.99,0.142485,0.3224,null,null,64.95024483036]
["AN_CT1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,49.03,0,0.257,0.026,0,63.23310846000001]
["AN_CT1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,49.03,0.026,0.257,0.026,0,64.87716927996]
["AN_CT1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,49.03,0.052676,0.257,0.026,0,66.56397568123896]
["AN_CT1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,49.03,0.08004558,0.257,0.026,0,68.2946393018836]
["AN_EE","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,67.43,0,0.3224,null,null,89.16943200000001]
["AN_EE","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,67.43,0.029,0.3224,null,null,91.75534552799999]
["AN_EE","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,67.43,0.057812,0.3224,null,null,94.32449520278401]
["AN_EE","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,67.43,0.085315,0.3224,null,null,96.77692209108002]
["AN_EE","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,67.43,0.113533,0.3224,null,null,99.293105123256]
["AN_EE","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,67.43,0.142485,0.3224,null,null,101.87473851852002]
["AN_EE1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.257,0.026,0,107.70134382000002]
["AN_EE1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.257,0.026,0,110.50157875932003]
["AN_EE1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.257,0.026,0,113.37461980706233]
["AN_EE1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.257,0.026,0,116.32236035285133]
["AN_MDD","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,42.99,0,0.3224,null,null,56.849976000000005]
["AN_MDD","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,42.99,0.029,0.3224,null,null,58.498625303999994]
["AN_MDD","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,42.99,0.057812,0.3224,null,null,60.136586812512]
["AN_MDD","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,42.99,0.085315,0.3224,null,null,61.70013170244001]
["AN_MDD","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,42.99,0.113533,0.3224,null,null,63.30432432520799]
["AN_MDD","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,42.99,0.142485,0.3224,null,null,64.95024483036]
["AN_MDD1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,49.03,0,0.257,0.026,0,63.23310846000001]
["AN_MDD1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,49.03,0.026,0.257,0.026,0,64.87716927996]
["AN_MDD1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,49.03,0.052676,0.257,0.026,0,66.56397568123896]
["AN_MDD1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,49.03,0.08004558,0.257,0.026,0,68.2946393018836]
["AN_ME","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,63.24,0,0.3224,null,null,83.62857600000001]
["AN_ME","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,63.24,0.029,0.3224,null,null,86.053804704]
["AN_ME","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,63.24,0.057812,0.3224,null,null,88.463311235712]
["AN_ME","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,63.24,0.085315,0.3224,null,null,90.76334796144]
["AN_ME","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,63.24,0.113533,0.3224,null,null,93.12317911900799]
["AN_ME","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,63.24,0.142485,0.3224,null,null,95.54439365136]
["AN_ME1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.257,0.026,0,107.70134382000002]
["AN_ME1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.257,0.026,0,110.50157875932003]
["AN_ME1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.257,0.026,0,113.37461980706233]
["AN_ME1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.257,0.026,0,116.32236035285133]
["AN_MES","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,67.43,0,0.3224,null,null,89.16943200000001]
["AN_MES","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,67.43,0.029,0.3224,null,null,91.75534552799999]
["AN_MES","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,67.43,0.057812,0.3224,null,null,94.32449520278401]
["AN_MES","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,67.43,0.085315,0.3224,null,null,96.77692209108002]
["AN_MES","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,67.43,0.113533,0.3224,null,null,99.293105123256]
["AN_MES","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,67.43,0.142485,0.3224,null,null,101.87473851852002]
["AN_MES1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.257,0.026,0,107.70134382000002]
["AN_MES1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.257,0.026,0,110.50157875932003]
["AN_MES1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.257,0.026,0,113.37461980706233]
["AN_MES1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.257,0.026,0,116.32236035285133]
["AN_MFAT","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,42.51,0,0.2598,null,null,53.554097999999996]
["AN_MFAT","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,42.51,0.029,0.2598,null,null,55.10716684199999]
["AN_MFAT","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,42.51,0.057812,0.2598,null,null,56.650167513575994]
["AN_MFAT","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,42.51,0.085315,0.2598,null,null,58.12306587087]
["AN_MFAT","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,42.51,0.113533,0.2598,null,null,59.634255408234]
["AN_MFAT","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,42.51,0.142485,0.2598,null,null,61.18475365353]
["AN_MFAT1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,49.03,0,0.257,0.026,0,63.23310846000001]
["AN_MFAT1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,49.03,0.026,0.257,0.026,0,64.87716927996]
["AN_MFAT1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,49.03,0.052676,0.257,0.026,0,66.56397568123896]
["AN_MFAT1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,49.03,0.08004558,0.257,0.026,0,68.2946393018836]
["AN_MFMS","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,53.97,0,0.2598,null,null,67.991406]
["AN_MFMS","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,53.97,0.029,0.2598,null,null,69.963156774]
["AN_MFMS","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,53.97,0.057812,0.2598,null,null,71.92212516367199]
["AN_MFMS","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,53.97,0.085315,0.2598,null,null,73.79209280289001]
["AN_MFMS","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,53.97,0.113533,0.2598,null,null,75.71067429739799]
["AN_MFMS","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,53.97,0.142485,0.2598,null,null,77.67916148391001]
["AN_MFMS1","ESC1","AN_CS2","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,81,0,0.196,0.026,0,99.394776]
["AN_MFMS1","ESC1","AN_CS2","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,81,0.026,0.196,0.026,0,101.97904017600001]
["AN_MFMS1","ESC1","AN_CS2","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,81,0.052676,0.196,0.026,0,104.630495220576]
["AN_MFMS1","ESC1","AN_CS2","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,81,0.08004558,0.196,0.026,0,107.35088849389007]
["AN_MFPC","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.2598,null,null,0]
["AN_MFPC","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.2598,null,null,0]
["AN_MFPC","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.2598,null,null,0]
["AN_MFPC","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.2598,null,null,0]
["AN_MFPC","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.2598,null,null,0]
["AN_MFPC","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.2598,null,null,0]
["AN_MSCS","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AN_MSCS","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AN_MSCS","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AN_MSCS","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AN_MSCS","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AN_MSCS","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AN_MSCS1","ESC1","AN_OH3",null,null,"2005-10-01","ESC138626",null,1,0,0,null,null,1]
["AN_MSCS1","ESC1","AN_OH3",null,null,"2006-10-01","ESC138991",null,1,0.026,0,null,null,1.026]
["AN_MSCS1","ESC1","AN_OH3",null,null,"2007-10-01","ESC139356",null,1,0.052676,0,null,null,1.052676]
["AN_MSCS1","ESC1","AN_OH3",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0,null,null,1.08004558]
["AN_MSEG","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AN_MSEG","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AN_MSEG","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AN_MSEG","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AN_MSEG","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AN_MSEG","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AN_MSEG1","ESC1","AN_OH3",null,null,"2005-10-01","ESC138626",null,1,0,0,null,null,1]
["AN_MSEG1","ESC1","AN_OH3",null,null,"2006-10-01","ESC138991",null,1,0.026,0,null,null,1.026]
["AN_MSEG1","ESC1","AN_OH3",null,null,"2007-10-01","ESC139356",null,1,0.052676,0,null,null,1.052676]
["AN_MSEG1","ESC1","AN_OH3",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0,null,null,1.08004558]
["AN_MSEQ","ESC","AN_OH4",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AN_MSEQ","ESC","AN_OH4",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AN_MSEQ","ESC","AN_OH4",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AN_MSEQ","ESC","AN_OH4",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AN_MSEQ","ESC","AN_OH4",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AN_MSEQ","ESC","AN_OH4",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AN_MSEQ1","ESC1","AN_OH4",null,null,"2005-10-01","ESC138626",null,1,0,0,null,null,1]
["AN_MSEQ1","ESC1","AN_OH4",null,null,"2006-10-01","ESC138991",null,1,0.026,0,null,null,1.026]
["AN_MSEQ1","ESC1","AN_OH4",null,null,"2007-10-01","ESC139356",null,1,0.052676,0,null,null,1.052676]
["AN_MSEQ1","ESC1","AN_OH4",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0,null,null,1.08004558]
["AN_MSPS","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AN_MSPS","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AN_MSPS","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AN_MSPS","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AN_MSPS","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AN_MSPS","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AN_MSPS1","ESC1","AN_OH3",null,null,"2005-10-01","ESC138626",null,1,0,0,null,null,1]
["AN_MSPS1","ESC1","AN_OH3",null,null,"2006-10-01","ESC138991",null,1,0.026,0,null,null,1.026]
["AN_MSPS1","ESC1","AN_OH3",null,null,"2007-10-01","ESC139356",null,1,0.052676,0,null,null,1.052676]
["AN_MSPS1","ESC1","AN_OH3",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0,null,null,1.08004558]
["AN_MSSC","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AN_MSSC","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AN_MSSC","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AN_MSSC","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AN_MSSC","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AN_MSSC","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AN_MSSC1","ESC1","AN_OH3",null,null,"2005-10-01","ESC138626",null,1,0,0,null,null,1]
["AN_MSSC1","ESC1","AN_OH3",null,null,"2006-10-01","ESC138991",null,1,0.026,0,null,null,1.026]
["AN_MSSC1","ESC1","AN_OH3",null,null,"2007-10-01","ESC139356",null,1,0.052676,0,null,null,1.052676]
["AN_MSSC1","ESC1","AN_OH3",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0,null,null,1.08004558]
["AN_MSSF","AN_OH3",{"$nulls":4},"AN_OH3",null,1,{"$nulls":4},1]
["AN_MSSF1","AN_OH3",{"$nulls":4},"AN_OH3",null,1,{"$nulls":4},1]
["AN_MSTR","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,1,0,0.3224,null,null,1.3224]
["AN_MSTR","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,1,0.029,0.3224,null,null,1.3607496]
["AN_MSTR","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.3224,null,null,1.3988505888]
["AN_MSTR","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.3224,null,null,1.435220556]
["AN_MSTR","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.3224,null,null,1.4725360392]
["AN_MSTR","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.3224,null,null,1.510822164]
["AN_MSTR1","ESC1","AN_OH1",null,null,"2005-10-01","ESC138626",null,1.29,0,0.3224,null,null,1.705896]
["AN_MSTR1","ESC1","AN_OH1",null,null,"2006-10-01","ESC138991",null,1.29,0.026,0.3224,null,null,1.7502492960000002]
["AN_MSTR1","ESC1","AN_OH1",null,null,"2007-10-01","ESC139356",null,1.29,0.052676,0.3224,null,null,1.795755777696]
["AN_MSTR1","ESC1","AN_OH1",null,null,"2008-10-01","ESC139722",null,1.29,0.08004558,0.3224,null,null,1.84244543473968]
["AN_MSXX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["AN_MSXX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["AN_MSXX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["AN_MSXX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["AN_MSXX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["AN_MSXX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["AN_MSXX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["AN_MSXX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["AN_MSXX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["AN_MSXX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["AN_MTRL","ESC","AN_OH3",null,null,"2003-10-01","ESC37895",null,1,0,0,null,null,1]
["AN_MTRL","ESC","AN_OH3",null,null,"2004-10-01","ESC38261",null,1,0.029,0,null,null,1.029]
["AN_MTRL","ESC","AN_OH3",null,null,"2005-10-01","ESC38626",null,1,0.057812,0,null,null,1.057812]
["AN_MTRL","ESC","AN_OH3",null,null,"2006-10-01","ESC38991",null,1,0.085315,0,null,null,1.085315]
["AN_MTRL","ESC","AN_OH3",null,null,"2007-10-01","ESC39356",null,1,0.113533,0,null,null,1.1135329999999999]
["AN_MTRL","ESC","AN_OH3",null,null,"2008-10-01","ESC39722",null,1,0.142485,0,null,null,1.142485]
["AN_MTRL1","ESC1","AN_OH3",null,null,"2005-10-01","ESC138626",null,1,0,0,null,null,1]
["AN_MTRL1","ESC1","AN_OH3",null,null,"2006-10-01","ESC138991",null,1,0.026,0,null,null,1.026]
["AN_MTRL1","ESC1","AN_OH3",null,null,"2007-10-01","ESC139356",null,1,0.052676,0,null,null,1.052676]
["AN_MTRL1","ESC1","AN_OH3",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0,null,null,1.08004558]
["AN_MVE","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,63.24,0,0.3224,null,null,83.62857600000001]
["AN_MVE","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,63.24,0.029,0.3224,null,null,86.053804704]
["AN_MVE","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,63.24,0.057812,0.3224,null,null,88.463311235712]
["AN_MVE","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,63.24,0.085315,0.3224,null,null,90.76334796144]
["AN_MVE","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,63.24,0.113533,0.3224,null,null,93.12317911900799]
["AN_MVE","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,63.24,0.142485,0.3224,null,null,95.54439365136]
["AN_MVE1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.257,0.026,0,107.70134382000002]
["AN_MVE1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.257,0.026,0,110.50157875932003]
["AN_MVE1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.257,0.026,0,113.37461980706233]
["AN_MVE1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.257,0.026,0,116.32236035285133]
["AN_PHH","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,45.68,0,0.3224,null,null,60.407232]
["AN_PHH","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,45.68,0.029,0.3224,null,null,62.159041728]
["AN_PHH","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,45.68,0.057812,0.3224,null,null,63.899494896384006]
["AN_PHH","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,45.68,0.085315,0.3224,null,null,65.56087499808]
["AN_PHH","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,45.68,0.113533,0.3224,null,null,67.265446270656]
["AN_PHH","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,45.68,0.142485,0.3224,null,null,69.01435645152]
["AN_PHH1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,45.68,0,0.257,0.026,0,58.912673760000004]
["AN_PHH1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,45.68,0.026,0.257,0.026,0,60.44440327776]
["AN_PHH1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,45.68,0.052676,0.257,0.026,0,62.01595776298176]
["AN_PHH1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,45.68,0.08004558,0.257,0.026,0,63.628372900469984]
["AN_PHPD","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,33.95,0,0.3224,null,null,44.895480000000006]
["AN_PHPD","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,33.95,0.029,0.3224,null,null,46.19744892]
["AN_PHPD","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,33.95,0.057812,0.3224,null,null,47.490977489760006]
["AN_PHPD","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,33.95,0.085315,0.3224,null,null,48.72573787620001]
["AN_PHPD","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,33.95,0.113533,0.3224,null,null,49.992598530840006]
["AN_PHPD","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,33.95,0.142485,0.3224,null,null,51.2924124678]
["AN_PHPD1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,37.26,0,0.257,0.026,0,48.053551320000004]
["AN_PHPD1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,37.26,0.026,0.257,0.026,0,49.30294365432]
["AN_PHPD1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,37.26,0.052676,0.257,0.026,0,50.584820189332326]
["AN_PHPD1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,37.26,0.08004558,0.257,0.026,0,51.900025706469165]
["AN_PHS","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,63.24,0,0.3224,null,null,83.62857600000001]
["AN_PHS","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,63.24,0.029,0.3224,null,null,86.053804704]
["AN_PHS","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,63.24,0.057812,0.3224,null,null,88.463311235712]
["AN_PHS","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,63.24,0.085315,0.3224,null,null,90.76334796144]
["AN_PHS","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,63.24,0.113533,0.3224,null,null,93.12317911900799]
["AN_PHS","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,63.24,0.142485,0.3224,null,null,95.54439365136]
["AN_PHS1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.257,0.026,0,107.70134382000002]
["AN_PHS1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.257,0.026,0,110.50157875932003]
["AN_PHS1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.257,0.026,0,113.37461980706233]
["AN_PHS1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.257,0.026,0,116.32236035285133]
["AN_PHSS","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,63.24,0,0.3224,null,null,83.62857600000001]
["AN_PHSS","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,63.24,0.029,0.3224,null,null,86.053804704]
["AN_PHSS","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,63.24,0.057812,0.3224,null,null,88.463311235712]
["AN_PHSS","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,63.24,0.085315,0.3224,null,null,90.76334796144]
["AN_PHSS","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,63.24,0.113533,0.3224,null,null,93.12317911900799]
["AN_PHSS","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,63.24,0.142485,0.3224,null,null,95.54439365136]
["AN_PHSS1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,63.24,0,0.257,0.026,0,81.55948968000001]
["AN_PHSS1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,63.24,0.026,0.257,0.026,0,83.68003641168002]
["AN_PHSS1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,63.24,0.052676,0.257,0.026,0,85.8557173583837]
["AN_PHSS1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,63.24,0.08004558,0.257,0.026,0,88.08796633593961]
["AN_PM","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,63.24,0,0.3224,null,null,83.62857600000001]
["AN_PM","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,63.24,0.029,0.3224,null,null,86.053804704]
["AN_PM","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,63.24,0.057812,0.3224,null,null,88.463311235712]
["AN_PM","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,63.24,0.085315,0.3224,null,null,90.76334796144]
["AN_PM","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,63.24,0.113533,0.3224,null,null,93.12317911900799]
["AN_PM","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,63.24,0.142485,0.3224,null,null,95.54439365136]
["AN_PM1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.257,0.026,0,107.70134382000002]
["AN_PM1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.257,0.026,0,110.50157875932003]
["AN_PM1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.257,0.026,0,113.37461980706233]
["AN_PM1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.257,0.026,0,116.32236035285133]
["AN_SEE","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,85,0,0.3224,null,null,112.404]
["AN_SEE","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,85,0.029,0.3224,null,null,115.663716]
["AN_SEE","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,85,0.057812,0.3224,null,null,118.90230004799999]
["AN_SEE","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,85,0.085315,0.3224,null,null,121.99374726000002]
["AN_SEE","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,85,0.113533,0.3224,null,null,125.16556333199999]
["AN_SEE","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,85,0.142485,0.3224,null,null,128.41988394]
["AN_SEE1","ESC1","AN_CS1","AN_GA1","AN_OH4","2005-10-01","ESC138626",null,83.51,0,0.257,0.026,0,107.70134382000002]
["AN_SEE1","ESC1","AN_CS1","AN_GA1","AN_OH4","2006-10-01","ESC138991",null,83.51,0.026,0.257,0.026,0,110.50157875932003]
["AN_SEE1","ESC1","AN_CS1","AN_GA1","AN_OH4","2007-10-01","ESC139356",null,83.51,0.052676,0.257,0.026,0,113.37461980706233]
["AN_SEE1","ESC1","AN_CS1","AN_GA1","AN_OH4","2008-10-01","ESC139722",null,83.51,0.08004558,0.257,0.026,0,116.32236035285133]
["AN_SEL","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,null,0,0.3224,null,null,0]
["AN_SEL","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,null,0.029,0.3224,null,null,0]
["AN_SEL","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.3224,null,null,0]
["AN_SEL","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.3224,null,null,0]
["AN_SEL","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.3224,null,null,0]
["AN_SEL","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.3224,null,null,0]
["AN_SEPM","ESC","AN_OH1",null,null,"2003-10-01","ESC37895",null,null,0,0.3224,null,null,0]
["AN_SEPM","ESC","AN_OH1",null,null,"2004-10-01","ESC38261",null,null,0.029,0.3224,null,null,0]
["AN_SEPM","ESC","AN_OH1",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.3224,null,null,0]
["AN_SEPM","ESC","AN_OH1",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.3224,null,null,0]
["AN_SEPM","ESC","AN_OH1",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.3224,null,null,0]
["AN_SEPM","ESC","AN_OH1",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.3224,null,null,0]
["AN_TMUC","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.2598,null,null,0]
["AN_TMUC","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.2598,null,null,0]
["AN_TMUC","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.2598,null,null,0]
["AN_TMUC","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.2598,null,null,0]
["AN_TMUC","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.2598,null,null,0]
["AN_TMUC","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.2598,null,null,0]
["AN_TMUE","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.2598,null,null,0]
["AN_TMUE","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.2598,null,null,0]
["AN_TMUE","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.2598,null,null,0]
["AN_TMUE","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.2598,null,null,0]
["AN_TMUE","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.2598,null,null,0]
["AN_TMUE","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.2598,null,null,0]
["AN_TMUI","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.2598,null,null,0]
["AN_TMUI","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.2598,null,null,0]
["AN_TMUI","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.2598,null,null,0]
["AN_TMUI","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.2598,null,null,0]
["AN_TMUI","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.2598,null,null,0]
["AN_TMUI","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.2598,null,null,0]
["AN_TMUO","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.2598,null,null,0]
["AN_TMUO","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.2598,null,null,0]
["AN_TMUO","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.2598,null,null,0]
["AN_TMUO","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.2598,null,null,0]
["AN_TMUO","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.2598,null,null,0]
["AN_TMUO","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.2598,null,null,0]
["AN_TMUP","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.2598,null,null,0]
["AN_TMUP","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.2598,null,null,0]
["AN_TMUP","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.2598,null,null,0]
["AN_TMUP","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.2598,null,null,0]
["AN_TMUP","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.2598,null,null,0]
["AN_TMUP","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.2598,null,null,0]
["AN_TMUW","ESC","AN_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.2598,null,null,0]
["AN_TMUW","ESC","AN_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.2598,null,null,0]
["AN_TMUW","ESC","AN_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.2598,null,null,0]
["AN_TMUW","ESC","AN_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.2598,null,null,0]
["AN_TMUW","ESC","AN_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.2598,null,null,0]
["AN_TMUW","ESC","AN_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.2598,null,null,0]
["BA",{"$nulls":5},"",null,1,{"$nulls":4},1]
["BASE",{"$nulls":5},"",null,1,{"$nulls":4},1]
["CNST",{"$nulls":5},"",{"$nulls":6},0]
["COMM",{"$nulls":5},"",{"$nulls":6},0]
["LA_MSCS","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,null,0,0.19,null,null,0]
["LA_MSCS","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,null,0.029,0.19,null,null,0]
["LA_MSCS","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.19,null,null,0]
["LA_MSCS","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.19,null,null,0]
["LA_MSCS","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.19,null,null,0]
["LA_MSCS","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.19,null,null,0]
["LA_MSCS1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LA_MSCS1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LA_MSCS1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LA_MSCS1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LA_MSEG","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LA_MSEG","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LA_MSEG","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LA_MSEG","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LA_MSEG","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LA_MSEG","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LA_MSEG1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LA_MSEG1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LA_MSEG1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LA_MSEG1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LA_MSEQ","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LA_MSEQ","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LA_MSEQ","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LA_MSEQ","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LA_MSEQ","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LA_MSEQ","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LA_MSEQ1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LA_MSEQ1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LA_MSEQ1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LA_MSEQ1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LA_MSPS","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,null,0,0.19,null,null,0]
["LA_MSPS","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,null,0.029,0.19,null,null,0]
["LA_MSPS","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.19,null,null,0]
["LA_MSPS","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.19,null,null,0]
["LA_MSPS","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.19,null,null,0]
["LA_MSPS","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.19,null,null,0]
["LA_MSSC","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LA_MSSC","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LA_MSSC","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LA_MSSC","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LA_MSSC","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LA_MSSC","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LA_MSSC1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LA_MSSC1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LA_MSSC1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LA_MSSC1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LA_MSSF","LL_OH",{"$nulls":4},"LL_OH",{"$nulls":6},0]
["LA_MSSX","LL_OH",{"$nulls":4},"LL_OH",{"$nulls":6},0]
["LA_MSXX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["LA_MSXX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["LA_MSXX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["LA_MSXX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["LA_MSXX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["LA_MSXX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["LA_MSXX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["LA_MSXX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["LA_MSXX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["LA_MSXX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["LLNL_LABOR","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LLNL_LABOR","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LLNL_LABOR","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LLNL_LABOR","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LLNL_LABOR","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LLNL_LABOR","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LLNL_NON-LABOR","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,null,0,0.19,null,null,0]
["LLNL_NON-LABOR","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,null,0.029,0.19,null,null,0]
["LLNL_NON-LABOR","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.19,null,null,0]
["LLNL_NON-LABOR","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.19,null,null,0]
["LLNL_NON-LABOR","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.19,null,null,0]
["LLNL_NON-LABOR","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.19,null,null,0]
["LLNL_SHOPS","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LLNL_SHOPS","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LLNL_SHOPS","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LLNL_SHOPS","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LLNL_SHOPS","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LLNL_SHOPS","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LLNL_TRAVEL","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,null,0,0.19,null,null,0]
["LLNL_TRAVEL","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,null,0.029,0.19,null,null,0]
["LLNL_TRAVEL","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.19,null,null,0]
["LLNL_TRAVEL","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.19,null,null,0]
["LLNL_TRAVEL","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.19,null,null,0]
["LLNL_TRAVEL","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.19,null,null,0]
["LL_ADMN","ESC",null,null,null,"2003-10-01","ESC37895",null,134.15048076923077,0,null,null,null,134.15048076923077]
["LL_ADMN","ESC",null,null,null,"2004-10-01","ESC38261",null,134.15048076923077,0.029,null,null,null,138.04084471153845]
["LL_ADMN","ESC",null,null,null,"2005-10-01","ESC38626",null,134.15048076923077,0.057812,null,null,null,141.90598836346155]
["LL_ADMN","ESC",null,null,null,"2006-10-01","ESC38991",null,134.15048076923077,0.085315,null,null,null,145.59552903605768]
["LL_ADMN","ESC",null,null,null,"2007-10-01","ESC39356",null,134.15048076923077,0.113533,null,null,null,149.38098730240384]
["LL_ADMN","ESC",null,null,null,"2008-10-01","ESC39722",null,134.15048076923077,0.142485,null,null,null,153.26491202163461]
["LL_ADMN1","ESC1",null,null,null,"2005-10-01","ESC138626",null,134.15048076923077,0,null,null,null,134.15048076923077]
["LL_ADMN1","ESC1",null,null,null,"2006-10-01","ESC138991",null,134.15048076923077,0.026,null,null,null,137.63839326923076]
["LL_ADMN1","ESC1",null,null,null,"2007-10-01","ESC139356",null,134.15048076923077,0.052676,null,null,null,141.21699149423077]
["LL_ADMN1","ESC1",null,null,null,"2008-10-01","ESC139722",null,134.15048076923077,0.08004558,null,null,null,144.8886338096827]
["LL_AW1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LL_AW1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LL_AW1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LL_AW1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LL_AWARD","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LL_AWARD","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LL_AWARD","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LL_AWARD","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LL_AWARD","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LL_AWARD","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LL_AWFX",{"$nulls":5},"",{"$nulls":6},0]
["LL_AWFX1",{"$nulls":5},"",{"$nulls":6},0]
["LL_AWFY",{"$nulls":5},"",{"$nulls":6},0]
["LL_AWFY1",{"$nulls":5},"",{"$nulls":6},0]
["LL_AWXX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["LL_AWXX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["LL_AWXX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["LL_AWXX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["LL_AWXX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["LL_AWXX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["LL_AWXX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["LL_AWXX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["LL_AWXX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["LL_AWXX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["LL_CCA","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_CCA","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_CCA","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_CCA","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_CCA","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_CCA","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_CE","ESC",null,null,null,"2003-10-01","ESC37895",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_CE","ESC",null,null,null,"2004-10-01","ESC38261",null,176.59423076923076,0.029,null,null,null,181.71546346153843]
["LL_CE","ESC",null,null,null,"2005-10-01","ESC38626",null,176.59423076923076,0.057812,null,null,null,186.80349643846154]
["LL_CE","ESC",null,null,null,"2006-10-01","ESC38991",null,176.59423076923076,0.085315,null,null,null,191.6603675673077]
["LL_CE","ESC",null,null,null,"2007-10-01","ESC39356",null,176.59423076923076,0.113533,null,null,null,196.64350357115381]
["LL_CE","ESC",null,null,null,"2008-10-01","ESC39722",null,176.59423076923076,0.142485,null,null,null,201.7562597403846]
["LL_CE1","ESC1",null,null,null,"2005-10-01","ESC138626",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_CE1","ESC1",null,null,null,"2006-10-01","ESC138991",null,176.59423076923076,0.026,null,null,null,181.18568076923077]
["LL_CE1","ESC1",null,null,null,"2007-10-01","ESC139356",null,176.59423076923076,0.052676,null,null,null,185.89650846923075]
["LL_CE1","ESC1",null,null,null,"2008-10-01","ESC139722",null,176.59423076923076,0.08004558,null,null,null,190.72981839580768]
["LL_CP","ESC",null,null,null,"2003-10-01","ESC37895",null,189.60865384615386,0,null,null,null,189.60865384615386]
["LL_CP","ESC",null,null,null,"2004-10-01","ESC38261",null,189.60865384615386,0.029,null,null,null,195.10730480769232]
["LL_CP","ESC",null,null,null,"2005-10-01","ESC38626",null,189.60865384615386,0.057812,null,null,null,200.5703093423077]
["LL_CP","ESC",null,null,null,"2006-10-01","ESC38991",null,189.60865384615386,0.085315,null,null,null,205.7851161490385]
["LL_CP","ESC",null,null,null,"2007-10-01","ESC39356",null,189.60865384615386,0.113533,null,null,null,211.13549314326923]
["LL_CP","ESC",null,null,null,"2008-10-01","ESC39722",null,189.60865384615386,0.142485,null,null,null,216.62504288942307]
["LL_CP1","ESC1",null,null,null,"2005-10-01","ESC138626",null,189.60865384615386,0,null,null,null,189.60865384615386]
["LL_CP1","ESC1",null,null,null,"2006-10-01","ESC138991",null,189.60865384615386,0.026,null,null,null,194.53847884615385]
["LL_CP1","ESC1",null,null,null,"2007-10-01","ESC139356",null,189.60865384615386,0.052676,null,null,null,199.59647929615386]
["LL_CP1","ESC1",null,null,null,"2008-10-01","ESC139722",null,189.60865384615386,0.08004558,null,null,null,204.78598851628846]
["LL_CT","ESC",null,null,null,"2003-10-01","ESC37895",null,137.21778846153848,0,null,null,null,137.21778846153848]
["LL_CT","ESC",null,null,null,"2004-10-01","ESC38261",null,137.21778846153848,0.029,null,null,null,141.19710432692307]
["LL_CT","ESC",null,null,null,"2005-10-01","ESC38626",null,137.21778846153848,0.057812,null,null,null,145.15062324807693]
["LL_CT","ESC",null,null,null,"2006-10-01","ESC38991",null,137.21778846153848,0.085315,null,null,null,148.92452408413465]
["LL_CT","ESC",null,null,null,"2007-10-01","ESC39356",null,137.21778846153848,0.113533,null,null,null,152.79653563894232]
["LL_CT","ESC",null,null,null,"2008-10-01","ESC39722",null,137.21778846153848,0.142485,null,null,null,156.76926505048078]
["LL_EE","ESC",null,null,null,"2003-10-01","ESC37895",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_EE","ESC",null,null,null,"2004-10-01","ESC38261",null,176.59423076923076,0.029,null,null,null,181.71546346153843]
["LL_EE","ESC",null,null,null,"2005-10-01","ESC38626",null,176.59423076923076,0.057812,null,null,null,186.80349643846154]
["LL_EE","ESC",null,null,null,"2006-10-01","ESC38991",null,176.59423076923076,0.085315,null,null,null,191.6603675673077]
["LL_EE","ESC",null,null,null,"2007-10-01","ESC39356",null,176.59423076923076,0.113533,null,null,null,196.64350357115381]
["LL_EE","ESC",null,null,null,"2008-10-01","ESC39722",null,176.59423076923076,0.142485,null,null,null,201.7562597403846]
["LL_EE1","ESC1",null,null,null,"2005-10-01","ESC138626",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_EE1","ESC1",null,null,null,"2006-10-01","ESC138991",null,176.59423076923076,0.026,null,null,null,181.18568076923077]
["LL_EE1","ESC1",null,null,null,"2007-10-01","ESC139356",null,176.59423076923076,0.052676,null,null,null,185.89650846923075]
["LL_EE1","ESC1",null,null,null,"2008-10-01","ESC139722",null,176.59423076923076,0.08004558,null,null,null,190.72981839580768]
["LL_KCA","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_KCA","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_KCA","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_KCA","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_KCA","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_KCA","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_KE","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_KE","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_KE","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_KE","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_KE","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_KE","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_KT","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_KT","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_KT","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_KT","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_KT","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_KT","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_MDD","ESC",null,null,null,"2003-10-01","ESC37895",null,162.0105769230769,0,null,null,null,162.0105769230769]
["LL_MDD","ESC",null,null,null,"2004-10-01","ESC38261",null,162.0105769230769,0.029,null,null,null,166.70888365384613]
["LL_MDD","ESC",null,null,null,"2005-10-01","ESC38626",null,162.0105769230769,0.057812,null,null,null,171.37673239615384]
["LL_MDD","ESC",null,null,null,"2006-10-01","ESC38991",null,162.0105769230769,0.085315,null,null,null,175.83250929326923]
["LL_MDD","ESC",null,null,null,"2007-10-01","ESC39356",null,162.0105769230769,0.113533,null,null,null,180.40412375288457]
["LL_MDD","ESC",null,null,null,"2008-10-01","ESC39722",null,162.0105769230769,0.142485,null,null,null,185.0946539759615]
["LL_MDD1","ESC1",null,null,null,"2005-10-01","ESC138626",null,162.0105769230769,0,null,null,null,162.0105769230769]
["LL_MDD1","ESC1",null,null,null,"2006-10-01","ESC138991",null,162.0105769230769,0.026,null,null,null,166.22285192307692]
["LL_MDD1","ESC1",null,null,null,"2007-10-01","ESC139356",null,162.0105769230769,0.052676,null,null,null,170.5446460730769]
["LL_MDD1","ESC1",null,null,null,"2008-10-01","ESC139722",null,162.0105769230769,0.08004558,null,null,null,174.9788075190192]
["LL_ME","ESC",null,null,null,"2003-10-01","ESC37895",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_ME","ESC",null,null,null,"2004-10-01","ESC38261",null,176.59423076923076,0.029,null,null,null,181.71546346153843]
["LL_ME","ESC",null,null,null,"2005-10-01","ESC38626",null,176.59423076923076,0.057812,null,null,null,186.80349643846154]
["LL_ME","ESC",null,null,null,"2006-10-01","ESC38991",null,176.59423076923076,0.085315,null,null,null,191.6603675673077]
["LL_ME","ESC",null,null,null,"2007-10-01","ESC39356",null,176.59423076923076,0.113533,null,null,null,196.64350357115381]
["LL_ME","ESC",null,null,null,"2008-10-01","ESC39722",null,176.59423076923076,0.142485,null,null,null,201.7562597403846]
["LL_ME1","ESC1",null,null,null,"2005-10-01","ESC138626",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_ME1","ESC1",null,null,null,"2006-10-01","ESC138991",null,176.59423076923076,0.026,null,null,null,181.18568076923077]
["LL_ME1","ESC1",null,null,null,"2007-10-01","ESC139356",null,176.59423076923076,0.052676,null,null,null,185.89650846923075]
["LL_ME1","ESC1",null,null,null,"2008-10-01","ESC139722",null,176.59423076923076,0.08004558,null,null,null,190.72981839580768]
["LL_MES","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_MES","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_MES","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_MES","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_MES","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_MES","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_MFAT","ESC",null,null,null,"2003-10-01","ESC37895",null,137.21778846153848,0,null,null,null,137.21778846153848]
["LL_MFAT","ESC",null,null,null,"2004-10-01","ESC38261",null,137.21778846153848,0.029,null,null,null,141.19710432692307]
["LL_MFAT","ESC",null,null,null,"2005-10-01","ESC38626",null,137.21778846153848,0.057812,null,null,null,145.15062324807693]
["LL_MFAT","ESC",null,null,null,"2006-10-01","ESC38991",null,137.21778846153848,0.085315,null,null,null,148.92452408413465]
["LL_MFAT","ESC",null,null,null,"2007-10-01","ESC39356",null,137.21778846153848,0.113533,null,null,null,152.79653563894232]
["LL_MFAT","ESC",null,null,null,"2008-10-01","ESC39722",null,137.21778846153848,0.142485,null,null,null,156.76926505048078]
["LL_MFAT1","ESC1",null,null,null,"2005-10-01","ESC138626",null,137.21778846153848,0,null,null,null,137.21778846153848]
["LL_MFAT1","ESC1",null,null,null,"2006-10-01","ESC138991",null,137.21778846153848,0.026,null,null,null,140.7854509615385]
["LL_MFAT1","ESC1",null,null,null,"2007-10-01","ESC139356",null,137.21778846153848,0.052676,null,null,null,144.44587268653848]
["LL_MFAT1","ESC1",null,null,null,"2008-10-01","ESC139722",null,137.21778846153848,0.08004558,null,null,null,148.2014659252596]
["LL_MFMS","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_MFMS","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_MFMS","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_MFMS","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_MFMS","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_MFMS","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_MFPC","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_MFPC","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_MFPC","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_MFPC","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_MFPC","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_MFPC","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_MSCS","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LL_MSCS","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LL_MSCS","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LL_MSCS","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LL_MSCS","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LL_MSCS","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LL_MSCS1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LL_MSCS1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LL_MSCS1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LL_MSCS1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LL_MSEG","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LL_MSEG","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LL_MSEG","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LL_MSEG","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LL_MSEG","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LL_MSEG","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LL_MSEG1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LL_MSEG1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LL_MSEG1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LL_MSEG1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LL_MSEQ","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LL_MSEQ","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LL_MSEQ","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LL_MSEQ","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LL_MSEQ","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LL_MSEQ","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LL_MSEQ1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LL_MSEQ1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LL_MSEQ1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LL_MSEQ1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LL_MSPS","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LL_MSPS","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LL_MSPS","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LL_MSPS","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LL_MSPS","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LL_MSPS","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LL_MSPS1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LL_MSPS1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LL_MSPS1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LL_MSPS1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LL_MSSC","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LL_MSSC","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LL_MSSC","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LL_MSSC","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LL_MSSC","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LL_MSSC","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LL_MSSC1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LL_MSSC1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LL_MSSC1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LL_MSSC1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LL_MSTR","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LL_MSTR","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LL_MSTR","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LL_MSTR","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LL_MSTR","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LL_MSTR","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LL_MSTR1","ESC1","LL_OH",null,null,"2005-10-01","ESC138626",null,1,0,0.19,null,null,1.19]
["LL_MSTR1","ESC1","LL_OH",null,null,"2006-10-01","ESC138991",null,1,0.026,0.19,null,null,1.22094]
["LL_MSTR1","ESC1","LL_OH",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.19,null,null,1.25268444]
["LL_MSTR1","ESC1","LL_OH",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.19,null,null,1.2852542401999998]
["LL_MSXX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["LL_MSXX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["LL_MSXX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["LL_MSXX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["LL_MSXX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["LL_MSXX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["LL_MSXX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["LL_MSXX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["LL_MSXX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["LL_MSXX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["LL_MTRL","ESC","LL_OH",null,null,"2003-10-01","ESC37895",null,1,0,0.19,null,null,1.19]
["LL_MTRL","ESC","LL_OH",null,null,"2004-10-01","ESC38261",null,1,0.029,0.19,null,null,1.2245099999999998]
["LL_MTRL","ESC","LL_OH",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.19,null,null,1.2587962799999999]
["LL_MTRL","ESC","LL_OH",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.19,null,null,1.29152485]
["LL_MTRL","ESC","LL_OH",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.19,null,null,1.3251042699999998]
["LL_MTRL","ESC","LL_OH",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.19,null,null,1.3595571499999999]
["LL_MTRL1","ESC1","LL_OH2",null,null,"2005-10-01","ESC138626",null,1,0,0.11,null,null,1.11]
["LL_MTRL1","ESC1","LL_OH2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.11,null,null,1.1388600000000002]
["LL_MTRL1","ESC1","LL_OH2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.11,null,null,1.1684703600000002]
["LL_MTRL1","ESC1","LL_OH2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.11,null,null,1.1988505938]
["LL_MVE","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_MVE","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_MVE","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_MVE","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_MVE","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_MVE","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_PCCA","ESC",null,null,null,"2003-10-01","ESC37895",null,158.32548076923078,0,null,null,null,158.32548076923078]
["LL_PCCA","ESC",null,null,null,"2004-10-01","ESC38261",null,158.32548076923078,0.029,null,null,null,162.91691971153847]
["LL_PCCA","ESC",null,null,null,"2005-10-01","ESC38626",null,158.32548076923078,0.057812,null,null,null,167.47859346346155]
["LL_PCCA","ESC",null,null,null,"2006-10-01","ESC38991",null,158.32548076923078,0.085315,null,null,null,171.8330191610577]
["LL_PCCA","ESC",null,null,null,"2007-10-01","ESC39356",null,158.32548076923078,0.113533,null,null,null,176.30064757740385]
["LL_PCCA","ESC",null,null,null,"2008-10-01","ESC39722",null,158.32548076923078,0.142485,null,null,null,180.88448689663463]
["LL_PCCA1","ESC1",null,null,null,"2005-10-01","ESC138626",null,158.32548076923078,0,null,null,null,158.32548076923078]
["LL_PCCA1","ESC1",null,null,null,"2006-10-01","ESC138991",null,158.32548076923078,0.026,null,null,null,162.4419432692308]
["LL_PCCA1","ESC1",null,null,null,"2007-10-01","ESC139356",null,158.32548076923078,0.052676,null,null,null,166.66543379423078]
["LL_PCCA1","ESC1",null,null,null,"2008-10-01","ESC139722",null,158.32548076923078,0.08004558,null,null,null,170.99873570618269]
["LL_PCE","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_PCE","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_PCE","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_PCE","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_PCE","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_PCE","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_PCEF","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_PCEF","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_PCEF","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_PCEF","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_PCEF","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_PCEF","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_PCT","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_PCT","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_PCT","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_PCT","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_PCT","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_PCT","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_PHPD","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_PHPD","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_PHPD","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_PHPD","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_PHPD","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_PHPD","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_PHS","ESC",null,null,null,"2003-10-01","ESC37895",null,188.69326923076923,0,null,null,null,188.69326923076923]
["LL_PHS","ESC",null,null,null,"2004-10-01","ESC38261",null,188.69326923076923,0.029,null,null,null,194.16537403846152]
["LL_PHS","ESC",null,null,null,"2005-10-01","ESC38626",null,188.69326923076923,0.057812,null,null,null,199.60200451153847]
["LL_PHS","ESC",null,null,null,"2006-10-01","ESC38991",null,188.69326923076923,0.085315,null,null,null,204.7916354951923]
["LL_PHS","ESC",null,null,null,"2007-10-01","ESC39356",null,188.69326923076923,0.113533,null,null,null,210.11618216634614]
["LL_PHS","ESC",null,null,null,"2008-10-01","ESC39722",null,188.69326923076923,0.142485,null,null,null,215.57922969711538]
["LL_PHS1","ESC1",null,null,null,"2005-10-01","ESC138626",null,188.69326923076923,0,null,null,null,188.69326923076923]
["LL_PHS1","ESC1",null,null,null,"2006-10-01","ESC138991",null,188.69326923076923,0.026,null,null,null,193.59929423076923]
["LL_PHS1","ESC1",null,null,null,"2007-10-01","ESC139356",null,188.69326923076923,0.052676,null,null,null,198.63287588076923]
["LL_PHS1","ESC1",null,null,null,"2008-10-01","ESC139722",null,188.69326923076923,0.08004558,null,null,null,203.7973314084423]
["LL_PHSS","ESC",null,null,null,"2003-10-01","ESC37895",null,208.3653846153846,0,null,null,null,208.3653846153846]
["LL_PHSS","ESC",null,null,null,"2004-10-01","ESC38261",null,208.3653846153846,0.029,null,null,null,214.40798076923076]
["LL_PHSS","ESC",null,null,null,"2005-10-01","ESC38626",null,208.3653846153846,0.057812,null,null,null,220.41140423076922]
["LL_PHSS","ESC",null,null,null,"2006-10-01","ESC38991",null,208.3653846153846,0.085315,null,null,null,226.14207740384614]
["LL_PHSS","ESC",null,null,null,"2007-10-01","ESC39356",null,208.3653846153846,0.113533,null,null,null,232.02173182692306]
["LL_PHSS","ESC",null,null,null,"2008-10-01","ESC39722",null,208.3653846153846,0.142485,null,null,null,238.05432644230768]
["LL_PHSS1","ESC1",null,null,null,"2005-10-01","ESC138626",null,208.3653846153846,0,null,null,null,208.3653846153846]
["LL_PHSS1","ESC1",null,null,null,"2006-10-01","ESC138991",null,208.3653846153846,0.026,null,null,null,213.78288461538463]
["LL_PHSS1","ESC1",null,null,null,"2007-10-01","ESC139356",null,208.3653846153846,0.052676,null,null,null,219.3412396153846]
["LL_PHSS1","ESC1",null,null,null,"2008-10-01","ESC139722",null,208.3653846153846,0.08004558,null,null,null,225.04411267884615]
["LL_PM","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_PM","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_PM","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_PM","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_PM","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_PM","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_PRC","ESC",null,null,null,"2003-10-01","ESC37895",null,162.0105769230769,0,null,null,null,162.0105769230769]
["LL_PRC","ESC",null,null,null,"2004-10-01","ESC38261",null,162.0105769230769,0.029,null,null,null,166.70888365384613]
["LL_PRC","ESC",null,null,null,"2005-10-01","ESC38626",null,162.0105769230769,0.057812,null,null,null,171.37673239615384]
["LL_PRC","ESC",null,null,null,"2006-10-01","ESC38991",null,162.0105769230769,0.085315,null,null,null,175.83250929326923]
["LL_PRC","ESC",null,null,null,"2007-10-01","ESC39356",null,162.0105769230769,0.113533,null,null,null,180.40412375288457]
["LL_PRC","ESC",null,null,null,"2008-10-01","ESC39722",null,162.0105769230769,0.142485,null,null,null,185.0946539759615]
["LL_PRC1","ESC1",null,null,null,"2005-10-01","ESC138626",null,162.0105769230769,0,null,null,null,162.0105769230769]
["LL_PRC1","ESC1",null,null,null,"2006-10-01","ESC138991",null,162.0105769230769,0.026,null,null,null,166.22285192307692]
["LL_PRC1","ESC1",null,null,null,"2007-10-01","ESC139356",null,162.0105769230769,0.052676,null,null,null,170.5446460730769]
["LL_PRC1","ESC1",null,null,null,"2008-10-01","ESC139722",null,162.0105769230769,0.08004558,null,null,null,174.9788075190192]
["LL_PRE","ESC",null,null,null,"2003-10-01","ESC37895",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_PRE","ESC",null,null,null,"2004-10-01","ESC38261",null,176.59423076923076,0.029,null,null,null,181.71546346153843]
["LL_PRE","ESC",null,null,null,"2005-10-01","ESC38626",null,176.59423076923076,0.057812,null,null,null,186.80349643846154]
["LL_PRE","ESC",null,null,null,"2006-10-01","ESC38991",null,176.59423076923076,0.085315,null,null,null,191.6603675673077]
["LL_PRE","ESC",null,null,null,"2007-10-01","ESC39356",null,176.59423076923076,0.113533,null,null,null,196.64350357115381]
["LL_PRE","ESC",null,null,null,"2008-10-01","ESC39722",null,176.59423076923076,0.142485,null,null,null,201.7562597403846]
["LL_PRE1","ESC1",null,null,null,"2005-10-01","ESC138626",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_PRE1","ESC1",null,null,null,"2006-10-01","ESC138991",null,176.59423076923076,0.026,null,null,null,181.18568076923077]
["LL_PRE1","ESC1",null,null,null,"2007-10-01","ESC139356",null,176.59423076923076,0.052676,null,null,null,185.89650846923075]
["LL_PRE1","ESC1",null,null,null,"2008-10-01","ESC139722",null,176.59423076923076,0.08004558,null,null,null,190.72981839580768]
["LL_RP","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_RP","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_RP","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_RP","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_RP","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_RP","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_SEE","ESC",null,null,null,"2003-10-01","ESC37895",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_SEE","ESC",null,null,null,"2004-10-01","ESC38261",null,176.59423076923076,0.029,null,null,null,181.71546346153843]
["LL_SEE","ESC",null,null,null,"2005-10-01","ESC38626",null,176.59423076923076,0.057812,null,null,null,186.80349643846154]
["LL_SEE","ESC",null,null,null,"2006-10-01","ESC38991",null,176.59423076923076,0.085315,null,null,null,191.6603675673077]
["LL_SEE","ESC",null,null,null,"2007-10-01","ESC39356",null,176.59423076923076,0.113533,null,null,null,196.64350357115381]
["LL_SEE","ESC",null,null,null,"2008-10-01","ESC39722",null,176.59423076923076,0.142485,null,null,null,201.7562597403846]
["LL_SEE1","ESC1",null,null,null,"2005-10-01","ESC138626",null,176.59423076923076,0,null,null,null,176.59423076923076]
["LL_SEE1","ESC1",null,null,null,"2006-10-01","ESC138991",null,176.59423076923076,0.026,null,null,null,181.18568076923077]
["LL_SEE1","ESC1",null,null,null,"2007-10-01","ESC139356",null,176.59423076923076,0.052676,null,null,null,185.89650846923075]
["LL_SEE1","ESC1",null,null,null,"2008-10-01","ESC139722",null,176.59423076923076,0.08004558,null,null,null,190.72981839580768]
["LL_SEL","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_SEL","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_SEL","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_SEL","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_SEL","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_SEL","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_SEPM","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_SEPM","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_SEPM","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_SEPM","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_SEPM","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_SEPM","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_TMUC","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_TMUC","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_TMUC","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_TMUC","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_TMUC","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_TMUC","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_TMUE","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_TMUE","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_TMUE","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_TMUE","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_TMUE","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_TMUE","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_TMUI","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_TMUI","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_TMUI","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_TMUI","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_TMUI","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_TMUI","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_TMUO","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_TMUO","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_TMUO","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_TMUO","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_TMUO","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_TMUO","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_TMUP","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_TMUP","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_TMUP","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_TMUP","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_TMUP","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_TMUP","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["LL_TMUW","ESC",null,null,null,"2003-10-01","ESC37895",null,null,0,null,null,null,0]
["LL_TMUW","ESC",null,null,null,"2004-10-01","ESC38261",null,null,0.029,null,null,null,0]
["LL_TMUW","ESC",null,null,null,"2005-10-01","ESC38626",null,null,0.057812,null,null,null,0]
["LL_TMUW","ESC",null,null,null,"2006-10-01","ESC38991",null,null,0.085315,null,null,null,0]
["LL_TMUW","ESC",null,null,null,"2007-10-01","ESC39356",null,null,0.113533,null,null,null,0]
["LL_TMUW","ESC",null,null,null,"2008-10-01","ESC39722",null,null,0.142485,null,null,null,0]
["PED",{"$nulls":5},"",{"$nulls":6},0]
["R&D",{"$nulls":5},"",{"$nulls":6},0]
["RES",{"$nulls":5},"",{"$nulls":6},0]
["SA_GCFX1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SA_GCSS","ESC_CF","SL_OH2",null,null,"2004-10-01","ESC_CF38261",null,1,0,0.06,null,null,1.06]
["SA_GCSS","ESC_CF","SL_OH2",null,null,"2005-10-01","ESC_CF38626",null,1,0.03,0.06,null,null,1.0918]
["SA_GCSS","ESC_CF","SL_OH2",null,null,"2006-10-01","ESC_CF38991",null,1,0.08,0.06,null,null,1.1448]
["SA_GCSS","ESC_CF","SL_OH2",null,null,"2007-10-01","ESC_CF39356",null,1,0.19,0.06,null,null,1.2614]
["SA_GCSS","ESC_CF","SL_OH2",null,null,"2008-10-01","ESC_CF39722",null,1,0.3,0.06,null,null,1.3780000000000001]
["SA_GCSS","ESC_CF","SL_OH2",null,null,"2009-10-01","ESC_CF40087",null,1,0.41,0.06,null,null,1.4946]
["SA_GCSS1","ESC_CF","SL_OHN2",null,null,"2004-10-01","ESC_CF38261",null,1,0,0.048,null,null,1.048]
["SA_GCSS1","ESC_CF","SL_OHN2",null,null,"2005-10-01","ESC_CF38626",null,1,0.03,0.048,null,null,1.0794400000000002]
["SA_GCSS1","ESC_CF","SL_OHN2",null,null,"2006-10-01","ESC_CF38991",null,1,0.08,0.048,null,null,1.1318400000000002]
["SA_GCSS1","ESC_CF","SL_OHN2",null,null,"2007-10-01","ESC_CF39356",null,1,0.19,0.048,null,null,1.24712]
["SA_GCSS1","ESC_CF","SL_OHN2",null,null,"2008-10-01","ESC_CF39722",null,1,0.3,0.048,null,null,1.3624]
["SA_GCSS1","ESC_CF","SL_OHN2",null,null,"2009-10-01","ESC_CF40087",null,1,0.41,0.048,null,null,1.4776799999999999]
["SA_GCSX","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,1,0,null,null,null,1]
["SA_GCSX","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,1,0.03,null,null,null,1.03]
["SA_GCSX","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,1,0.08,null,null,null,1.08]
["SA_GCSX","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,1,0.19,null,null,null,1.19]
["SA_GCSX","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,1,0.3,null,null,null,1.3]
["SA_GCSX","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,1,0.41,null,null,null,1.41]
["SA_GCSX1","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,1,0,null,null,null,1]
["SA_GCSX1","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,1,0.03,null,null,null,1.03]
["SA_GCSX1","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,1,0.08,null,null,null,1.08]
["SA_GCSX1","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,1,0.19,null,null,null,1.19]
["SA_GCSX1","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,1,0.3,null,null,null,1.3]
["SA_GCSX1","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,1,0.41,null,null,null,1.41]
["SA_MSCS","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.06,null,null,0]
["SA_MSCS","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.06,null,null,0]
["SA_MSCS","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.06,null,null,0]
["SA_MSCS","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.06,null,null,0]
["SA_MSCS","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.06,null,null,0]
["SA_MSCS","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.06,null,null,0]
["SA_MSCS1","ESC1","SL_OHN2",null,null,"2005-10-01","ESC138626",null,1,0,0.048,null,null,1.048]
["SA_MSCS1","ESC1","SL_OHN2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.048,null,null,1.075248]
["SA_MSCS1","ESC1","SL_OHN2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.048,null,null,1.103204448]
["SA_MSCS1","ESC1","SL_OHN2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.048,null,null,1.13188776784]
["SA_MSEG","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SA_MSEG","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SA_MSEG","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SA_MSEG","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SA_MSEG","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SA_MSEG","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SA_MSEG1","ESC1","SL_OHN2",null,null,"2005-10-01","ESC138626",null,1,0,0.048,null,null,1.048]
["SA_MSEG1","ESC1","SL_OHN2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.048,null,null,1.075248]
["SA_MSEG1","ESC1","SL_OHN2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.048,null,null,1.103204448]
["SA_MSEG1","ESC1","SL_OHN2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.048,null,null,1.13188776784]
["SA_MSEQ","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SA_MSEQ","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SA_MSEQ","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SA_MSEQ","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SA_MSEQ","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SA_MSEQ","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SA_MSEQ1","ESC1","SL_OHN2",null,null,"2005-10-01","ESC138626",null,1,0,0.048,null,null,1.048]
["SA_MSEQ1","ESC1","SL_OHN2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.048,null,null,1.075248]
["SA_MSEQ1","ESC1","SL_OHN2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.048,null,null,1.103204448]
["SA_MSEQ1","ESC1","SL_OHN2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.048,null,null,1.13188776784]
["SA_MSPF","SL_OH2",{"$nulls":4},"SL_OH2",null,1,{"$nulls":4},1]
["SA_MSPF1","SL_OHN2",{"$nulls":4},"SL_OHN2",null,1,{"$nulls":4},1]
["SA_MSPS","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SA_MSPS","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SA_MSPS","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SA_MSPS","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SA_MSPS","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SA_MSPS","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SA_MSPS1","ESC1","SL_OHN2",null,null,"2005-10-01","ESC138626",null,1,0,0.048,null,null,1.048]
["SA_MSPS1","ESC1","SL_OHN2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.048,null,null,1.075248]
["SA_MSPS1","ESC1","SL_OHN2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.048,null,null,1.103204448]
["SA_MSPS1","ESC1","SL_OHN2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.048,null,null,1.13188776784]
["SA_MSPX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["SA_MSPX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["SA_MSPX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["SA_MSPX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["SA_MSPX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["SA_MSPX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["SA_MSPX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["SA_MSPX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["SA_MSPX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["SA_MSPX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["SA_MSPY",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SA_MSPY1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SA_MSSC","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SA_MSSC","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SA_MSSC","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SA_MSSC","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SA_MSSC","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SA_MSSC","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SA_MSSC1","ESC1","SL_OHN2",null,null,"2005-10-01","ESC138626",null,1,0,0.048,null,null,1.048]
["SA_MSSC1","ESC1","SL_OHN2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.048,null,null,1.075248]
["SA_MSSC1","ESC1","SL_OHN2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.048,null,null,1.103204448]
["SA_MSSC1","ESC1","SL_OHN2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.048,null,null,1.13188776784]
["SA_MSSF","SL_OH2",{"$nulls":4},"SL_OH2",null,1,{"$nulls":4},1]
["SA_MSSF1","SL_OHN2",{"$nulls":4},"SL_OHN2",null,1,{"$nulls":4},1]
["SA_MSSY",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SA_MSSY1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SA_MSXX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["SA_MSXX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["SA_MSXX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["SA_MSXX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["SA_MSXX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["SA_MSXX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["SA_MSXX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["SA_MSXX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["SA_MSXX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["SA_MSXX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["SLAC_LABOR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,null,0,0.29,0.215,0.2,0]
["SLAC_LABOR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,null,0.029,0.29,0.215,0.2,0]
["SLAC_LABOR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,null,0.057812,0.29,0.215,0.2,0]
["SLAC_LABOR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,null,0.085315,0.29,0.215,0.2,0]
["SLAC_LABOR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,null,0.113533,0.29,0.215,0.2,0]
["SLAC_LABOR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,null,0.142485,0.29,0.215,0.2,0]
["SLAC_NON-LABOR","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,null,0,0.06,null,null,0]
["SLAC_NON-LABOR","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,null,0.029,0.06,null,null,0]
["SLAC_NON-LABOR","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.06,null,null,0]
["SLAC_NON-LABOR","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.06,null,null,0]
["SLAC_NON-LABOR","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.06,null,null,0]
["SLAC_NON-LABOR","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.06,null,null,0]
["SLAC_SHOPS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2003-10-01","ESC37895",null,null,0,0,0,0.2,0]
["SLAC_SHOPS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2004-10-01","ESC38261",null,null,0.029,0,0,0.2,0]
["SLAC_SHOPS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2005-10-01","ESC38626",null,null,0.057812,0,0,0.2,0]
["SLAC_SHOPS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2006-10-01","ESC38991",null,null,0.085315,0,0,0.2,0]
["SLAC_SHOPS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2007-10-01","ESC39356",null,null,0.113533,0,0,0.2,0]
["SLAC_SHOPS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2008-10-01","ESC39722",null,null,0.142485,0,0,0.2,0]
["SLAC_TRAVEL","ESC","SL_OH1",null,null,"2003-10-01","ESC37895",null,null,0,0.2,null,null,0]
["SLAC_TRAVEL","ESC","SL_OH1",null,null,"2004-10-01","ESC38261",null,null,0.029,0.2,null,null,0]
["SLAC_TRAVEL","ESC","SL_OH1",null,null,"2005-10-01","ESC38626",null,null,0.057812,0.2,null,null,0]
["SLAC_TRAVEL","ESC","SL_OH1",null,null,"2006-10-01","ESC38991",null,null,0.085315,0.2,null,null,0]
["SLAC_TRAVEL","ESC","SL_OH1",null,null,"2007-10-01","ESC39356",null,null,0.113533,0.2,null,null,0]
["SLAC_TRAVEL","ESC","SL_OH1",null,null,"2008-10-01","ESC39722",null,null,0.142485,0.2,null,null,0]
["SL_ADMN","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,30.1731,0,0.29,0.215,0.2,56.750169942]
["SL_ADMN","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,30.1731,0.029,0.29,0.215,0.2,58.395924870318]
["SL_ADMN","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,30.1731,0.057812,0.29,0.215,0.2,60.031010766686904]
["SL_ADMN","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,30.1731,0.085315,0.29,0.215,0.2,61.59181069060175]
["SL_ADMN","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,30.1731,0.113533,0.29,0.215,0.2,63.193186986025076]
["SL_ADMN","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,30.1731,0.142485,0.29,0.215,0.2,64.83621790618588]
["SL_ADMN1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,30.1731,0,0.305,0.21,0.2,57.17380026599999]
["SL_ADMN1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,30.1731,0.026,0.305,0.21,0.2,58.660319072916]
["SL_ADMN1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,30.1731,0.052676,0.305,0.21,0.2,60.185487368811806]
["SL_ADMN1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,30.1731,0.08004558,0.305,0.21,0.2,61.75031026909612]
["SL_AW1","ESC1","SL_OHN2",null,null,"2005-10-01","ESC138626",null,1,0,0.048,null,null,1.048]
["SL_AW1","ESC1","SL_OHN2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.048,null,null,1.075248]
["SL_AW1","ESC1","SL_OHN2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.048,null,null,1.103204448]
["SL_AW1","ESC1","SL_OHN2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.048,null,null,1.13188776784]
["SL_AWARD","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SL_AWARD","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SL_AWARD","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SL_AWARD","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SL_AWARD","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SL_AWARD","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SL_AWFX","SL_OH2",{"$nulls":4},"SL_OH2",null,1,{"$nulls":4},1]
["SL_AWFX1","SL_OHN2",{"$nulls":4},"SL_OHN2",null,1,{"$nulls":4},1]
["SL_AWFY",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_AWFY1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_AWGC","ESC_CF","SL_OH2",null,null,"2004-10-01","ESC_CF38261",null,1,0,0.06,null,null,1.06]
["SL_AWGC","ESC_CF","SL_OH2",null,null,"2005-10-01","ESC_CF38626",null,1,0.03,0.06,null,null,1.0918]
["SL_AWGC","ESC_CF","SL_OH2",null,null,"2006-10-01","ESC_CF38991",null,1,0.08,0.06,null,null,1.1448]
["SL_AWGC","ESC_CF","SL_OH2",null,null,"2007-10-01","ESC_CF39356",null,1,0.19,0.06,null,null,1.2614]
["SL_AWGC","ESC_CF","SL_OH2",null,null,"2008-10-01","ESC_CF39722",null,1,0.3,0.06,null,null,1.3780000000000001]
["SL_AWGC","ESC_CF","SL_OH2",null,null,"2009-10-01","ESC_CF40087",null,1,0.41,0.06,null,null,1.4946]
["SL_AWGC1","ESC_CF","SL_OHN2",null,null,"2004-10-01","ESC_CF38261",null,1,0,0.048,null,null,1.048]
["SL_AWGC1","ESC_CF","SL_OHN2",null,null,"2005-10-01","ESC_CF38626",null,1,0.03,0.048,null,null,1.0794400000000002]
["SL_AWGC1","ESC_CF","SL_OHN2",null,null,"2006-10-01","ESC_CF38991",null,1,0.08,0.048,null,null,1.1318400000000002]
["SL_AWGC1","ESC_CF","SL_OHN2",null,null,"2007-10-01","ESC_CF39356",null,1,0.19,0.048,null,null,1.24712]
["SL_AWGC1","ESC_CF","SL_OHN2",null,null,"2008-10-01","ESC_CF39722",null,1,0.3,0.048,null,null,1.3624]
["SL_AWGC1","ESC_CF","SL_OHN2",null,null,"2009-10-01","ESC_CF40087",null,1,0.41,0.048,null,null,1.4776799999999999]
["SL_AWGX","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,1,0,null,null,null,1]
["SL_AWGX","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,1,0.03,null,null,null,1.03]
["SL_AWGX","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,1,0.08,null,null,null,1.08]
["SL_AWGX","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,1,0.19,null,null,null,1.19]
["SL_AWGX","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,1,0.3,null,null,null,1.3]
["SL_AWGX","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,1,0.41,null,null,null,1.41]
["SL_AWGX1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_AWXX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["SL_AWXX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["SL_AWXX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["SL_AWXX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["SL_AWXX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["SL_AWXX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["SL_AWXX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["SL_AWXX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["SL_AWXX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["SL_AWXX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["SL_CCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,33.86,0,0.29,0.215,0.2,63.6845652]
["SL_CCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,33.86,0.029,0.29,0.215,0.2,65.53141759079999]
["SL_CCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,33.86,0.057812,0.29,0.215,0.2,67.3662972833424]
["SL_CCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,33.86,0.085315,0.29,0.215,0.2,69.117813880038]
["SL_CCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,33.86,0.113533,0.29,0.215,0.2,70.9148649408516]
["SL_CCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,33.86,0.142485,0.29,0.215,0.2,72.75866047252201]
["SL_CCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,33.86,0,0.305,0.21,0.2,64.1599596]
["SL_CCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,33.86,0.026,0.305,0.21,0.2,65.82811854959999]
["SL_CCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,33.86,0.052676,0.305,0.21,0.2,67.53964963188959]
["SL_CCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,33.86,0.08004558,0.305,0.21,0.2,69.29568077895857]
["SL_CE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,58.14,0,0.29,0.215,0.2,109.3508748]
["SL_CE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,58.14,0.029,0.29,0.215,0.2,112.52205016919999]
["SL_CE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,58.14,0.057812,0.29,0.215,0.2,115.6726675739376]
["SL_CE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,58.14,0.085315,0.29,0.215,0.2,118.680144683562]
["SL_CE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,58.14,0.113533,0.29,0.215,0.2,121.7658076686684]
["SL_CE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,58.14,0.142485,0.29,0.215,0.2,124.931734195878]
["SL_CE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,58.14,0,0.305,0.21,0.2,110.16716039999999]
["SL_CE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,58.14,0.026,0.305,0.21,0.2,113.0315065704]
["SL_CE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,58.14,0.052676,0.305,0.21,0.2,115.97032574123038]
["SL_CE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,58.14,0.08004558,0.305,0.21,0.2,118.98555465117103]
["SL_CP","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,47.01,0,0.29,0.215,0.2,88.41734819999999]
["SL_CP","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,47.01,0.029,0.29,0.215,0.2,90.9814512978]
["SL_CP","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,47.01,0.057812,0.29,0.215,0.2,93.5289319341384]
["SL_CP","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,47.01,0.085315,0.29,0.215,0.2,95.96067426168301]
["SL_CP","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,47.01,0.113533,0.29,0.215,0.2,98.4556349931906]
["SL_CP","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,47.01,0.142485,0.29,0.215,0.2,101.015494058277]
["SL_CP1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,42.39,0,0.305,0.21,0.2,80.32311539999999]
["SL_CP1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,42.39,0.026,0.305,0.21,0.2,82.4115164004]
["SL_CP1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,42.39,0.052676,0.305,0.21,0.2,84.55421582681039]
["SL_CP1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,42.39,0.08004558,0.305,0.21,0.2,86.75262575959991]
["SL_CPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,30.93,0,0.29,0.215,0.2,58.1737626]
["SL_CPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,30.93,0.029,0.29,0.215,0.2,59.860801715399994]
["SL_CPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,30.93,0.057812,0.29,0.215,0.2,61.5369041634312]
["SL_CPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,30.93,0.085315,0.29,0.215,0.2,63.136857156219]
["SL_CPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,30.93,0.113533,0.29,0.215,0.2,64.7784043892658]
["SL_CPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,30.93,0.142485,0.29,0.215,0.2,66.46265116406099]
["SL_CPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,30.93,0,0.305,0.21,0.2,58.608019799999994]
["SL_CPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,30.93,0.026,0.305,0.21,0.2,60.13182831479999]
["SL_CPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,30.93,0.052676,0.305,0.21,0.2,61.695255850984786]
["SL_CPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,30.93,0.08004558,0.305,0.21,0.2,63.29933273754247]
["SL_CRA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,24.14,0,0.29,0.215,0.2,45.4029948]
["SL_CRA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,24.14,0.029,0.29,0.215,0.2,46.719681649200005]
["SL_CRA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,24.14,0.057812,0.29,0.215,0.2,48.02783273537761]
["SL_CRA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,24.14,0.085315,0.29,0.215,0.2,49.276551301362005]
["SL_CRA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,24.14,0.113533,0.29,0.215,0.2,50.557733008628404]
["SL_CRA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,24.14,0.142485,0.29,0.215,0.2,51.872240514078]
["SL_CRA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,27.19,0,0.305,0.21,0.2,51.5212434]
["SL_CRA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,27.19,0.026,0.305,0.21,0.2,52.860795728399985]
["SL_CRA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,27.19,0.052676,0.305,0.21,0.2,54.235176417338394]
["SL_CRA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,27.19,0.08004558,0.305,0.21,0.2,55.645291210274166]
["SL_CRM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,30.93,0,0.29,0.215,0.2,58.1737626]
["SL_CRM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,30.93,0.029,0.29,0.215,0.2,59.860801715399994]
["SL_CRM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,30.93,0.057812,0.29,0.215,0.2,61.5369041634312]
["SL_CRM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,30.93,0.085315,0.29,0.215,0.2,63.136857156219]
["SL_CRM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,30.93,0.113533,0.29,0.215,0.2,64.7784043892658]
["SL_CRM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,30.93,0.142485,0.29,0.215,0.2,66.46265116406099]
["SL_CRM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,30.93,0,0.305,0.21,0.2,58.608019799999994]
["SL_CRM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,30.93,0.026,0.305,0.21,0.2,60.13182831479999]
["SL_CRM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,30.93,0.052676,0.305,0.21,0.2,61.695255850984786]
["SL_CRM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,30.93,0.08004558,0.305,0.21,0.2,63.29933273754247]
["SL_CT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,31.83,0,0.29,0.215,0.2,59.866500599999995]
["SL_CT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,31.83,0.029,0.29,0.215,0.2,61.60262911739999]
["SL_CT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,31.83,0.057812,0.29,0.215,0.2,63.327502732687186]
["SL_CT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,31.83,0.085315,0.29,0.215,0.2,64.974011098689]
["SL_CT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,31.83,0.113533,0.29,0.215,0.2,66.66332401261978]
["SL_CT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,31.83,0.142485,0.29,0.215,0.2,68.396578937991]
["SL_CT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,31.83,0,0.305,0.21,0.2,60.313393799999986]
["SL_CT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,31.83,0.026,0.305,0.21,0.2,61.88154203879998]
["SL_CT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,31.83,0.052676,0.305,0.21,0.2,63.49046213180878]
["SL_CT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,31.83,0.08004558,0.305,0.21,0.2,65.14121438848939]
["SL_EE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,58.14,0,0.29,0.215,0.2,109.3508748]
["SL_EE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,58.14,0.029,0.29,0.215,0.2,112.52205016919999]
["SL_EE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,58.14,0.057812,0.29,0.215,0.2,115.6726675739376]
["SL_EE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,58.14,0.085315,0.29,0.215,0.2,118.680144683562]
["SL_EE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,58.14,0.113533,0.29,0.215,0.2,121.7658076686684]
["SL_EE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,58.14,0.142485,0.29,0.215,0.2,124.931734195878]
["SL_EE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,47.95,0,0.305,0.21,0.2,90.858537]
["SL_EE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,47.95,0.026,0.305,0.21,0.2,93.22085896200001]
["SL_EE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,47.95,0.052676,0.305,0.21,0.2,95.64460129501198]
["SL_EE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,47.95,0.08004558,0.305,0.21,0.2,98.13136129211645]
["SL_FA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,40.7,0,0.29,0.215,0.2,76.54937400000001]
["SL_FA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,40.7,0.029,0.29,0.215,0.2,78.769305846]
["SL_FA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,40.7,0.057812,0.29,0.215,0.2,80.97484640968801]
["SL_FA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,40.7,0.085315,0.29,0.215,0.2,83.08018384281002]
["SL_FA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,40.7,0.113533,0.29,0.215,0.2,85.24025407834199]
["SL_FA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,40.7,0.142485,0.29,0.215,0.2,87.45651155439002]
["SL_FA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,46.24,0,0.305,0.21,0.2,87.61832639999999]
["SL_FA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,46.24,0.026,0.305,0.21,0.2,89.8964028864]
["SL_FA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,46.24,0.052676,0.305,0.21,0.2,92.2337093614464]
["SL_FA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,46.24,0.08004558,0.305,0.21,0.2,94.6317861553173]
["SL_GCAW","ESC_CF","SL_OH2",null,null,"2004-10-01","ESC_CF38261",null,null,0,0.06,null,null,0]
["SL_GCAW","ESC_CF","SL_OH2",null,null,"2005-10-01","ESC_CF38626",null,null,0.03,0.06,null,null,0]
["SL_GCAW","ESC_CF","SL_OH2",null,null,"2006-10-01","ESC_CF38991",null,null,0.08,0.06,null,null,0]
["SL_GCAW","ESC_CF","SL_OH2",null,null,"2007-10-01","ESC_CF39356",null,null,0.19,0.06,null,null,0]
["SL_GCAW","ESC_CF","SL_OH2",null,null,"2008-10-01","ESC_CF39722",null,null,0.3,0.06,null,null,0]
["SL_GCAW","ESC_CF","SL_OH2",null,null,"2009-10-01","ESC_CF40087",null,null,0.41,0.06,null,null,0]
["SL_GCAW1","ESC_CF","SL_OHN2",null,null,"2004-10-01","ESC_CF38261",null,null,0,0.048,null,null,0]
["SL_GCAW1","ESC_CF","SL_OHN2",null,null,"2005-10-01","ESC_CF38626",null,null,0.03,0.048,null,null,0]
["SL_GCAW1","ESC_CF","SL_OHN2",null,null,"2006-10-01","ESC_CF38991",null,null,0.08,0.048,null,null,0]
["SL_GCAW1","ESC_CF","SL_OHN2",null,null,"2007-10-01","ESC_CF39356",null,null,0.19,0.048,null,null,0]
["SL_GCAW1","ESC_CF","SL_OHN2",null,null,"2008-10-01","ESC_CF39722",null,null,0.3,0.048,null,null,0]
["SL_GCAW1","ESC_CF","SL_OHN2",null,null,"2009-10-01","ESC_CF40087",null,null,0.41,0.048,null,null,0]
["SL_GCAX","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,null,0,null,null,null,0]
["SL_GCAX","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,null,0.03,null,null,null,0]
["SL_GCAX","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,null,0.08,null,null,null,0]
["SL_GCAX","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,null,0.19,null,null,null,0]
["SL_GCAX","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,null,0.3,null,null,null,0]
["SL_GCAX","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,null,0.41,null,null,null,0]
["SL_GCAX1","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,null,0,null,null,null,0]
["SL_GCAX1","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,null,0.03,null,null,null,0]
["SL_GCAX1","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,null,0.08,null,null,null,0]
["SL_GCAX1","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,null,0.19,null,null,null,0]
["SL_GCAX1","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,null,0.3,null,null,null,0]
["SL_GCAX1","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,null,0.41,null,null,null,0]
["SL_GCFX1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_GCSS","ESC_CF","SL_OH2",null,null,"2004-10-01","ESC_CF38261",null,1,0,0.06,null,null,1.06]
["SL_GCSS","ESC_CF","SL_OH2",null,null,"2005-10-01","ESC_CF38626",null,1,0.03,0.06,null,null,1.0918]
["SL_GCSS","ESC_CF","SL_OH2",null,null,"2006-10-01","ESC_CF38991",null,1,0.08,0.06,null,null,1.1448]
["SL_GCSS","ESC_CF","SL_OH2",null,null,"2007-10-01","ESC_CF39356",null,1,0.19,0.06,null,null,1.2614]
["SL_GCSS","ESC_CF","SL_OH2",null,null,"2008-10-01","ESC_CF39722",null,1,0.3,0.06,null,null,1.3780000000000001]
["SL_GCSS","ESC_CF","SL_OH2",null,null,"2009-10-01","ESC_CF40087",null,1,0.41,0.06,null,null,1.4946]
["SL_GCSS1","ESC_CF","SL_OHN2",null,null,"2004-10-01","ESC_CF38261",null,1,0,0.048,null,null,1.048]
["SL_GCSS1","ESC_CF","SL_OHN2",null,null,"2005-10-01","ESC_CF38626",null,1,0.03,0.048,null,null,1.0794400000000002]
["SL_GCSS1","ESC_CF","SL_OHN2",null,null,"2006-10-01","ESC_CF38991",null,1,0.08,0.048,null,null,1.1318400000000002]
["SL_GCSS1","ESC_CF","SL_OHN2",null,null,"2007-10-01","ESC_CF39356",null,1,0.19,0.048,null,null,1.24712]
["SL_GCSS1","ESC_CF","SL_OHN2",null,null,"2008-10-01","ESC_CF39722",null,1,0.3,0.048,null,null,1.3624]
["SL_GCSS1","ESC_CF","SL_OHN2",null,null,"2009-10-01","ESC_CF40087",null,1,0.41,0.048,null,null,1.4776799999999999]
["SL_GCSX","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,1,0,null,null,null,1]
["SL_GCSX","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,1,0.03,null,null,null,1.03]
["SL_GCSX","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,1,0.08,null,null,null,1.08]
["SL_GCSX","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,1,0.19,null,null,null,1.19]
["SL_GCSX","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,1,0.3,null,null,null,1.3]
["SL_GCSX","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,1,0.41,null,null,null,1.41]
["SL_GCSX1","ESC_CF",null,null,null,"2004-10-01","ESC_CF38261",null,1,0,null,null,null,1]
["SL_GCSX1","ESC_CF",null,null,null,"2005-10-01","ESC_CF38626",null,1,0.03,null,null,null,1.03]
["SL_GCSX1","ESC_CF",null,null,null,"2006-10-01","ESC_CF38991",null,1,0.08,null,null,null,1.08]
["SL_GCSX1","ESC_CF",null,null,null,"2007-10-01","ESC_CF39356",null,1,0.19,null,null,null,1.19]
["SL_GCSX1","ESC_CF",null,null,null,"2008-10-01","ESC_CF39722",null,1,0.3,null,null,null,1.3]
["SL_GCSX1","ESC_CF",null,null,null,"2009-10-01","ESC_CF40087",null,1,0.41,null,null,null,1.41]
["SL_IPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_IPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_IPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_IPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_IPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_IPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_IPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,54.62,0,0.305,0.21,0.2,103.49725319999999]
["SL_IPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,54.62,0.026,0.305,0.21,0.2,106.18818178319998]
["SL_IPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,54.62,0.052676,0.305,0.21,0.2,108.94907450956318]
["SL_IPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,54.62,0.08004558,0.305,0.21,0.2,111.78175086080083]
["SL_KCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,33.86,0,0.29,0.215,0.2,63.6845652]
["SL_KCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,33.86,0.029,0.29,0.215,0.2,65.53141759079999]
["SL_KCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,33.86,0.057812,0.29,0.215,0.2,67.3662972833424]
["SL_KCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,33.86,0.085315,0.29,0.215,0.2,69.117813880038]
["SL_KCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,33.86,0.113533,0.29,0.215,0.2,70.9148649408516]
["SL_KCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,33.86,0.142485,0.29,0.215,0.2,72.75866047252201]
["SL_KCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,33.86,0,0.305,0.21,0.2,64.1599596]
["SL_KCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,33.86,0.026,0.305,0.21,0.2,65.82811854959999]
["SL_KCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,33.86,0.052676,0.305,0.21,0.2,67.53964963188959]
["SL_KCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,33.86,0.08004558,0.305,0.21,0.2,69.29568077895857]
["SL_KE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,58.14,0,0.29,0.215,0.2,109.3508748]
["SL_KE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,58.14,0.029,0.29,0.215,0.2,112.52205016919999]
["SL_KE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,58.14,0.057812,0.29,0.215,0.2,115.6726675739376]
["SL_KE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,58.14,0.085315,0.29,0.215,0.2,118.680144683562]
["SL_KE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,58.14,0.113533,0.29,0.215,0.2,121.7658076686684]
["SL_KE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,58.14,0.142485,0.29,0.215,0.2,124.931734195878]
["SL_KE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,58.14,0,0.305,0.21,0.2,110.16716039999999]
["SL_KE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,58.14,0.026,0.305,0.21,0.2,113.0315065704]
["SL_KE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,58.14,0.052676,0.305,0.21,0.2,115.97032574123038]
["SL_KE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,58.14,0.08004558,0.305,0.21,0.2,118.98555465117103]
["SL_KT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,31.83,0,0.29,0.215,0.2,59.866500599999995]
["SL_KT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,31.83,0.029,0.29,0.215,0.2,61.60262911739999]
["SL_KT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,31.83,0.057812,0.29,0.215,0.2,63.327502732687186]
["SL_KT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,31.83,0.085315,0.29,0.215,0.2,64.974011098689]
["SL_KT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,31.83,0.113533,0.29,0.215,0.2,66.66332401261978]
["SL_KT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,31.83,0.142485,0.29,0.215,0.2,68.396578937991]
["SL_KT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,31.83,0,0.305,0.21,0.2,60.313393799999986]
["SL_KT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,31.83,0.026,0.305,0.21,0.2,61.88154203879998]
["SL_KT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,31.83,0.052676,0.305,0.21,0.2,63.49046213180878]
["SL_KT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,31.83,0.08004558,0.305,0.21,0.2,65.14121438848939]
["SL_LPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_LPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_LPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_LPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_LPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_LPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_LPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,54.62,0,0.305,0.21,0.2,103.49725319999999]
["SL_LPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,54.62,0.026,0.305,0.21,0.2,106.18818178319998]
["SL_LPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,54.62,0.052676,0.305,0.21,0.2,108.94907450956318]
["SL_LPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,54.62,0.08004558,0.305,0.21,0.2,111.78175086080083]
["SL_MDD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,32.42,0,0.29,0.215,0.2,60.97618440000001]
["SL_MDD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,32.42,0.029,0.29,0.215,0.2,62.7444937476]
["SL_MDD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,32.42,0.057812,0.29,0.215,0.2,64.5013395725328]
["SL_MDD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,32.42,0.085315,0.29,0.215,0.2,66.17836757208602]
["SL_MDD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,32.42,0.113533,0.29,0.215,0.2,67.8989935434852]
["SL_MDD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,32.42,0.142485,0.29,0.215,0.2,69.66437603423401]
["SL_MDD1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,43.07,0,0.305,0.21,0.2,81.61162019999999]
["SL_MDD1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,43.07,0.026,0.305,0.21,0.2,83.7335223252]
["SL_MDD1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,43.07,0.052676,0.305,0.21,0.2,85.91059390565519]
["SL_MDD1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,43.07,0.08004558,0.305,0.21,0.2,88.1442696736487]
["SL_ME","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_ME","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_ME","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_ME","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_ME","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_ME","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_ME1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,51.37,0,0.305,0.21,0.2,97.33895819999998]
["SL_ME1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,51.37,0.026,0.305,0.21,0.2,99.86977111319999]
["SL_ME1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,51.37,0.052676,0.305,0.21,0.2,102.46638516214317]
["SL_ME1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,51.37,0.08004558,0.305,0.21,0.2,105.13051156571474]
["SL_MES","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,46.68,0,0.29,0.215,0.2,87.7966776]
["SL_MES","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,46.68,0.029,0.29,0.215,0.2,90.3427812504]
["SL_MES","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,46.68,0.057812,0.29,0.215,0.2,92.8723791254112]
["SL_MES","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,46.68,0.085315,0.29,0.215,0.2,95.28705114944401]
["SL_MES","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,46.68,0.113533,0.29,0.215,0.2,97.76449779796079]
["SL_MES","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,46.68,0.142485,0.29,0.215,0.2,100.306387207836]
["SL_MES1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,41.3,0,0.305,0.21,0.2,78.257718]
["SL_MES1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,41.3,0.026,0.305,0.21,0.2,80.292418668]
["SL_MES1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,41.3,0.052676,0.305,0.21,0.2,82.380021553368]
["SL_MES1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,41.3,0.08004558,0.305,0.21,0.2,84.52190242678643]
["SL_MFAT","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2003-10-01","ESC37895",null,66.3,0,0,0,0.2,79.55999999999999]
["SL_MFAT","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2004-10-01","ESC38261",null,66.3,0.029,0,0,0.2,81.86723999999998]
["SL_MFAT","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2005-10-01","ESC38626",null,66.3,0.057812,0,0,0.2,84.15952272]
["SL_MFAT","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2006-10-01","ESC38991",null,66.3,0.085315,0,0,0.2,86.34766139999999]
["SL_MFAT","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2007-10-01","ESC39356",null,66.3,0.113533,0,0,0.2,88.59268547999999]
["SL_MFAT","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2008-10-01","ESC39722",null,66.3,0.142485,0,0,0.2,90.89610659999998]
["SL_MFAT1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN1","2005-10-01","ESC138626",null,70,0,0,0,0.2,84]
["SL_MFAT1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN1","2006-10-01","ESC138991",null,70,0.026,0,0,0.2,86.18400000000001]
["SL_MFAT1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN1","2007-10-01","ESC139356",null,70,0.052676,0,0,0.2,88.424784]
["SL_MFAT1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN1","2008-10-01","ESC139722",null,70,0.08004558,0,0,0.2,90.72382871999999]
["SL_MFMS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2003-10-01","ESC37895",null,81.3,0,0,0,0.2,97.55999999999999]
["SL_MFMS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2004-10-01","ESC38261",null,81.3,0.029,0,0,0.2,100.38923999999999]
["SL_MFMS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2005-10-01","ESC38626",null,81.3,0.057812,0,0,0.2,103.20013872]
["SL_MFMS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2006-10-01","ESC38991",null,81.3,0.085315,0,0,0.2,105.88333139999999]
["SL_MFMS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2007-10-01","ESC39356",null,81.3,0.113533,0,0,0.2,108.63627947999998]
["SL_MFMS","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2008-10-01","ESC39722",null,81.3,0.142485,0,0,0.2,111.4608366]
["SL_MFMS1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN1","2005-10-01","ESC138626",null,89.59,0,0,0,0.2,107.508]
["SL_MFMS1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN1","2006-10-01","ESC138991",null,89.59,0.026,0,0,0.2,110.303208]
["SL_MFMS1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN1","2007-10-01","ESC139356",null,89.59,0.052676,0,0,0.2,113.171091408]
["SL_MFMS1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN1","2008-10-01","ESC139722",null,89.59,0.08004558,0,0,0.2,116.11354021463998]
["SL_MFPC","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2003-10-01","ESC37895",null,129.8,0,0,0,0.2,155.76000000000002]
["SL_MFPC","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2004-10-01","ESC38261",null,129.8,0.029,0,0,0.2,160.27704]
["SL_MFPC","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2005-10-01","ESC38626",null,129.8,0.057812,0,0,0.2,164.76479712]
["SL_MFPC","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2006-10-01","ESC38991",null,129.8,0.085315,0,0,0.2,169.04866440000004]
["SL_MFPC","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2007-10-01","ESC39356",null,129.8,0.113533,0,0,0.2,173.44390007999996]
["SL_MFPC","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2008-10-01","ESC39722",null,129.8,0.142485,0,0,0.2,177.9534636]
["SL_MFPC1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN1","2005-10-01","ESC138626",null,140.65,0,0,0,0.2,168.78]
["SL_MFPC1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN1","2006-10-01","ESC138991",null,140.65,0.026,0,0,0.2,173.16828]
["SL_MFPC1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN1","2007-10-01","ESC139356",null,140.65,0.052676,0,0,0.2,177.67065527999998]
["SL_MFPC1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN1","2008-10-01","ESC139722",null,140.65,0.08004558,0,0,0.2,182.29009299240002]
["SL_MSCS","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SL_MSCS","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SL_MSCS","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SL_MSCS","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SL_MSCS","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SL_MSCS","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SL_MSCS1","ESC1","SL_OHN2",null,null,"2005-10-01","ESC138626",null,1,0,0.048,null,null,1.048]
["SL_MSCS1","ESC1","SL_OHN2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.048,null,null,1.075248]
["SL_MSCS1","ESC1","SL_OHN2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.048,null,null,1.103204448]
["SL_MSCS1","ESC1","SL_OHN2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.048,null,null,1.13188776784]
["SL_MSEG","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SL_MSEG","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SL_MSEG","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SL_MSEG","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SL_MSEG","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SL_MSEG","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SL_MSEG1","ESC1","SL_OHN2",null,null,"2005-10-01","ESC138626",null,1,0,0.048,null,null,1.048]
["SL_MSEG1","ESC1","SL_OHN2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.048,null,null,1.075248]
["SL_MSEG1","ESC1","SL_OHN2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.048,null,null,1.103204448]
["SL_MSEG1","ESC1","SL_OHN2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.048,null,null,1.13188776784]
["SL_MSEQ","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SL_MSEQ","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SL_MSEQ","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SL_MSEQ","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SL_MSEQ","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SL_MSEQ","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SL_MSEQ1","ESC1","SL_OHN2",null,null,"2005-10-01","ESC138626",null,1,0,0.048,null,null,1.048]
["SL_MSEQ1","ESC1","SL_OHN2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.048,null,null,1.075248]
["SL_MSEQ1","ESC1","SL_OHN2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.048,null,null,1.103204448]
["SL_MSEQ1","ESC1","SL_OHN2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.048,null,null,1.13188776784]
["SL_MSPF","SL_OH2",{"$nulls":4},"SL_OH2",null,1,{"$nulls":4},1]
["SL_MSPF1","SL_OHN2",{"$nulls":4},"SL_OHN2",null,1,{"$nulls":4},1]
["SL_MSPS","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SL_MSPS","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SL_MSPS","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SL_MSPS","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SL_MSPS","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SL_MSPS","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SL_MSPS1","ESC1","SL_OHN2",null,null,"2005-10-01","ESC138626",null,1,0,0.048,null,null,1.048]
["SL_MSPS1","ESC1","SL_OHN2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.048,null,null,1.075248]
["SL_MSPS1","ESC1","SL_OHN2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.048,null,null,1.103204448]
["SL_MSPS1","ESC1","SL_OHN2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.048,null,null,1.13188776784]
["SL_MSPX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["SL_MSPX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["SL_MSPX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["SL_MSPX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["SL_MSPX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["SL_MSPX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["SL_MSPX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["SL_MSPX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["SL_MSPX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["SL_MSPX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["SL_MSPY",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_MSPY1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_MSSC","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SL_MSSC","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SL_MSSC","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SL_MSSC","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SL_MSSC","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SL_MSSC","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SL_MSSC1","ESC1","SL_OHN2",null,null,"2005-10-01","ESC138626",null,1,0,0.048,null,null,1.048]
["SL_MSSC1","ESC1","SL_OHN2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.048,null,null,1.075248]
["SL_MSSC1","ESC1","SL_OHN2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.048,null,null,1.103204448]
["SL_MSSC1","ESC1","SL_OHN2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.048,null,null,1.13188776784]
["SL_MSSF","SL_OH2",{"$nulls":4},"SL_OH2",null,1,{"$nulls":4},1]
["SL_MSSF1","SL_OHN2",{"$nulls":4},"SL_OHN2",null,1,{"$nulls":4},1]
["SL_MSSY",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_MSSY1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_MSTR","ESC","SL_OH1",null,null,"2003-10-01","ESC37895",null,1,0,0.2,null,null,1.2]
["SL_MSTR","ESC","SL_OH1",null,null,"2004-10-01","ESC38261",null,1,0.029,0.2,null,null,1.2348]
["SL_MSTR","ESC","SL_OH1",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.2,null,null,1.2693744]
["SL_MSTR","ESC","SL_OH1",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.2,null,null,1.302378]
["SL_MSTR","ESC","SL_OH1",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.2,null,null,1.3362395999999999]
["SL_MSTR","ESC","SL_OH1",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.2,null,null,1.370982]
["SL_MSTR1","ESC1","SL_OHN1",null,null,"2005-10-01","ESC138626",null,1,0,0.2,null,null,1.2]
["SL_MSTR1","ESC1","SL_OHN1",null,null,"2006-10-01","ESC138991",null,1,0.026,0.2,null,null,1.2312]
["SL_MSTR1","ESC1","SL_OHN1",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.2,null,null,1.2632112]
["SL_MSTR1","ESC1","SL_OHN1",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.2,null,null,1.296054696]
["SL_MSXA",{"$nulls":5},"",{"$nulls":6},0]
["SL_MSXX","ESC",null,null,null,"2003-10-01","ESC37895",null,1,0,null,null,null,1]
["SL_MSXX","ESC",null,null,null,"2004-10-01","ESC38261",null,1,0.029,null,null,null,1.029]
["SL_MSXX","ESC",null,null,null,"2005-10-01","ESC38626",null,1,0.057812,null,null,null,1.057812]
["SL_MSXX","ESC",null,null,null,"2006-10-01","ESC38991",null,1,0.085315,null,null,null,1.085315]
["SL_MSXX","ESC",null,null,null,"2007-10-01","ESC39356",null,1,0.113533,null,null,null,1.1135329999999999]
["SL_MSXX","ESC",null,null,null,"2008-10-01","ESC39722",null,1,0.142485,null,null,null,1.142485]
["SL_MSXX1","ESC1",null,null,null,"2005-10-01","ESC138626",null,1,0,null,null,null,1]
["SL_MSXX1","ESC1",null,null,null,"2006-10-01","ESC138991",null,1,0.026,null,null,null,1.026]
["SL_MSXX1","ESC1",null,null,null,"2007-10-01","ESC139356",null,1,0.052676,null,null,null,1.052676]
["SL_MSXX1","ESC1",null,null,null,"2008-10-01","ESC139722",null,1,0.08004558,null,null,null,1.08004558]
["SL_MTRL","ESC","SL_OH2",null,null,"2003-10-01","ESC37895",null,1,0,0.06,null,null,1.06]
["SL_MTRL","ESC","SL_OH2",null,null,"2004-10-01","ESC38261",null,1,0.029,0.06,null,null,1.09074]
["SL_MTRL","ESC","SL_OH2",null,null,"2005-10-01","ESC38626",null,1,0.057812,0.06,null,null,1.1212807200000001]
["SL_MTRL","ESC","SL_OH2",null,null,"2006-10-01","ESC38991",null,1,0.085315,0.06,null,null,1.1504339000000001]
["SL_MTRL","ESC","SL_OH2",null,null,"2007-10-01","ESC39356",null,1,0.113533,0.06,null,null,1.1803449799999999]
["SL_MTRL","ESC","SL_OH2",null,null,"2008-10-01","ESC39722",null,1,0.142485,0.06,null,null,1.2110341]
["SL_MTRL1","ESC1","SL_OHN2",null,null,"2005-10-01","ESC138626",null,1,0,0.048,null,null,1.048]
["SL_MTRL1","ESC1","SL_OHN2",null,null,"2006-10-01","ESC138991",null,1,0.026,0.048,null,null,1.075248]
["SL_MTRL1","ESC1","SL_OHN2",null,null,"2007-10-01","ESC139356",null,1,0.052676,0.048,null,null,1.103204448]
["SL_MTRL1","ESC1","SL_OHN2",null,null,"2008-10-01","ESC139722",null,1,0.08004558,0.048,null,null,1.13188776784]
["SL_MVE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_MVE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_MVE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_MVE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_MVE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_MVE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_MVE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,54.62,0,0.305,0.21,0.2,103.49725319999999]
["SL_MVE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,54.62,0.026,0.305,0.21,0.2,106.18818178319998]
["SL_MVE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,54.62,0.052676,0.305,0.21,0.2,108.94907450956318]
["SL_MVE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,54.62,0.08004558,0.305,0.21,0.2,111.78175086080083]
["SL_OE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,58.14,0,0.29,0.215,0.2,109.3508748]
["SL_OE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,58.14,0.029,0.29,0.215,0.2,112.52205016919999]
["SL_OE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,58.14,0.057812,0.29,0.215,0.2,115.6726675739376]
["SL_OE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,58.14,0.085315,0.29,0.215,0.2,118.680144683562]
["SL_OE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,58.14,0.113533,0.29,0.215,0.2,121.7658076686684]
["SL_OE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,58.14,0.142485,0.29,0.215,0.2,124.931734195878]
["SL_OE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,58.14,0,0.305,0.21,0.2,110.16716039999999]
["SL_OE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,58.14,0.026,0.305,0.21,0.2,113.0315065704]
["SL_OE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,58.14,0.052676,0.305,0.21,0.2,115.97032574123038]
["SL_OE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,58.14,0.08004558,0.305,0.21,0.2,118.98555465117103]
["SL_OT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,31.83,0,0.29,0.215,0.2,59.866500599999995]
["SL_OT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,31.83,0.029,0.29,0.215,0.2,61.60262911739999]
["SL_OT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,31.83,0.057812,0.29,0.215,0.2,63.327502732687186]
["SL_OT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,31.83,0.085315,0.29,0.215,0.2,64.974011098689]
["SL_OT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,31.83,0.113533,0.29,0.215,0.2,66.66332401261978]
["SL_OT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,31.83,0.142485,0.29,0.215,0.2,68.396578937991]
["SL_OT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,31.83,0,0.305,0.21,0.2,60.313393799999986]
["SL_OT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,31.83,0.026,0.305,0.21,0.2,61.88154203879998]
["SL_OT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,31.83,0.052676,0.305,0.21,0.2,63.49046213180878]
["SL_OT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,31.83,0.08004558,0.305,0.21,0.2,65.14121438848939]
["SL_PCCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,33.86,0,0.29,0.215,0.2,63.6845652]
["SL_PCCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,33.86,0.029,0.29,0.215,0.2,65.53141759079999]
["SL_PCCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,33.86,0.057812,0.29,0.215,0.2,67.3662972833424]
["SL_PCCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,33.86,0.085315,0.29,0.215,0.2,69.117813880038]
["SL_PCCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,33.86,0.113533,0.29,0.215,0.2,70.9148649408516]
["SL_PCCA","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,33.86,0.142485,0.29,0.215,0.2,72.75866047252201]
["SL_PCCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,33.86,0,0.305,0.21,0.2,64.1599596]
["SL_PCCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,33.86,0.026,0.305,0.21,0.2,65.82811854959999]
["SL_PCCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,33.86,0.052676,0.305,0.21,0.2,67.53964963188959]
["SL_PCCA1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,33.86,0.08004558,0.305,0.21,0.2,69.29568077895857]
["SL_PCE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,58.14,0,0.29,0.215,0.2,109.3508748]
["SL_PCE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,58.14,0.029,0.29,0.215,0.2,112.52205016919999]
["SL_PCE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,58.14,0.057812,0.29,0.215,0.2,115.6726675739376]
["SL_PCE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,58.14,0.085315,0.29,0.215,0.2,118.680144683562]
["SL_PCE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,58.14,0.113533,0.29,0.215,0.2,121.7658076686684]
["SL_PCE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,58.14,0.142485,0.29,0.215,0.2,124.931734195878]
["SL_PCE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,58.14,0,0.305,0.21,0.2,110.16716039999999]
["SL_PCE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,58.14,0.026,0.305,0.21,0.2,113.0315065704]
["SL_PCE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,58.14,0.052676,0.305,0.21,0.2,115.97032574123038]
["SL_PCE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,58.14,0.08004558,0.305,0.21,0.2,118.98555465117103]
["SL_PCEF","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,31.83,0,0.29,0.215,0.2,59.866500599999995]
["SL_PCEF","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,31.83,0.029,0.29,0.215,0.2,61.60262911739999]
["SL_PCEF","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,31.83,0.057812,0.29,0.215,0.2,63.327502732687186]
["SL_PCEF","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,31.83,0.085315,0.29,0.215,0.2,64.974011098689]
["SL_PCEF","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,31.83,0.113533,0.29,0.215,0.2,66.66332401261978]
["SL_PCEF","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,31.83,0.142485,0.29,0.215,0.2,68.396578937991]
["SL_PCEF1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,31.83,0,0.305,0.21,0.2,60.313393799999986]
["SL_PCEF1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,31.83,0.026,0.305,0.21,0.2,61.88154203879998]
["SL_PCEF1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,31.83,0.052676,0.305,0.21,0.2,63.49046213180878]
["SL_PCEF1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,31.83,0.08004558,0.305,0.21,0.2,65.14121438848939]
["SL_PCT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,31.83,0,0.29,0.215,0.2,59.866500599999995]
["SL_PCT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,31.83,0.029,0.29,0.215,0.2,61.60262911739999]
["SL_PCT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,31.83,0.057812,0.29,0.215,0.2,63.327502732687186]
["SL_PCT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,31.83,0.085315,0.29,0.215,0.2,64.974011098689]
["SL_PCT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,31.83,0.113533,0.29,0.215,0.2,66.66332401261978]
["SL_PCT","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,31.83,0.142485,0.29,0.215,0.2,68.396578937991]
["SL_PCT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,31.83,0,0.305,0.21,0.2,60.313393799999986]
["SL_PCT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,31.83,0.026,0.305,0.21,0.2,61.88154203879998]
["SL_PCT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,31.83,0.052676,0.305,0.21,0.2,63.49046213180878]
["SL_PCT1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,31.83,0.08004558,0.305,0.21,0.2,65.14121438848939]
["SL_PEX","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,40.7,0,0.29,0.215,0.2,76.54937400000001]
["SL_PEX","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,40.7,0.029,0.29,0.215,0.2,78.769305846]
["SL_PEX","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,40.7,0.057812,0.29,0.215,0.2,80.97484640968801]
["SL_PEX","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,40.7,0.085315,0.29,0.215,0.2,83.08018384281002]
["SL_PEX","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,40.7,0.113533,0.29,0.215,0.2,85.24025407834199]
["SL_PEX","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,40.7,0.142485,0.29,0.215,0.2,87.45651155439002]
["SL_PEX1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,40.7,0,0.305,0.21,0.2,77.120802]
["SL_PEX1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,40.7,0.026,0.305,0.21,0.2,79.125942852]
["SL_PEX1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,40.7,0.052676,0.305,0.21,0.2,81.183217366152]
["SL_PEX1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,40.7,0.08004558,0.305,0.21,0.2,83.29398132615515]
["SL_PHH","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,45.68,0,0.29,0.215,0.2,85.9158576]
["SL_PHH","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,45.68,0.029,0.29,0.215,0.2,88.4074174704]
["SL_PHH","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,45.68,0.057812,0.29,0.215,0.2,90.88282515957121]
["SL_PHH","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,45.68,0.085315,0.29,0.215,0.2,93.245768991144]
["SL_PHH","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,45.68,0.113533,0.29,0.215,0.2,95.67014266090081]
["SL_PHH","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,45.68,0.142485,0.29,0.215,0.2,98.15757857013601]
["SL_PHH1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,49.4,0,0.305,0.21,0.2,93.60608399999998]
["SL_PHH1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,49.4,0.026,0.305,0.21,0.2,96.03984218399998]
["SL_PHH1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,49.4,0.052676,0.305,0.21,0.2,98.53687808078398]
["SL_PHH1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,49.4,0.08004558,0.305,0.21,0.2,101.0988372853087]
["SL_PHPD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,36.17,0,0.29,0.215,0.2,68.0292594]
["SL_PHPD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,36.17,0.029,0.29,0.215,0.2,70.0021079226]
["SL_PHPD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,36.17,0.057812,0.29,0.215,0.2,71.96216694443281]
["SL_PHPD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,36.17,0.085315,0.29,0.215,0.2,73.83317566571101]
["SL_PHPD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,36.17,0.113533,0.29,0.215,0.2,75.7528253074602]
["SL_PHPD","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,36.17,0.142485,0.29,0.215,0.2,77.722408425609]
["SL_PHPD1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,36.17,0,0.305,0.21,0.2,68.53708619999999]
["SL_PHPD1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,36.17,0.026,0.305,0.21,0.2,70.3190504412]
["SL_PHPD1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,36.17,0.052676,0.305,0.21,0.2,72.1473457526712]
["SL_PHPD1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,36.17,0.08004558,0.305,0.21,0.2,74.02317701638898]
["SL_PHPU","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,63.33,0,0.305,0.21,0.2,120.00148379999999]
["SL_PHPU","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,63.33,0.026,0.305,0.21,0.2,123.12152237879998]
["SL_PHPU","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,63.33,0.052676,0.305,0.21,0.2,126.32268196064877]
["SL_PHPU","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,63.33,0.08004558,0.305,0.21,0.2,129.6070721716316]
["SL_PHS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,37.62,0,0.29,0.215,0.2,70.7564484]
["SL_PHS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,37.62,0.029,0.29,0.215,0.2,72.80838540359998]
["SL_PHS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,37.62,0.057812,0.29,0.215,0.2,74.84702019490081]
["SL_PHS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,37.62,0.085315,0.29,0.215,0.2,76.79303479524602]
["SL_PHS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,37.62,0.113533,0.29,0.215,0.2,78.78964025619719]
["SL_PHS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,37.62,0.142485,0.29,0.215,0.2,80.83818095027401]
["SL_PHS1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,37.62,0,0.305,0.21,0.2,71.28463319999999]
["SL_PHS1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,37.62,0.026,0.305,0.21,0.2,73.13803366319999]
["SL_PHS1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,37.62,0.052676,0.305,0.21,0.2,75.03962253844318]
["SL_PHS1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,37.62,0.08004558,0.305,0.21,0.2,76.99065300958124]
["SL_PHSS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,47.88,0,0.29,0.215,0.2,90.05366160000001]
["SL_PHSS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,47.88,0.029,0.29,0.215,0.2,92.66521778639999]
["SL_PHSS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,47.88,0.057812,0.29,0.215,0.2,95.25984388441923]
["SL_PHSS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,47.88,0.085315,0.29,0.215,0.2,97.736589739404]
["SL_PHSS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,47.88,0.113533,0.29,0.215,0.2,100.27772396243279]
["SL_PHSS","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,47.88,0.142485,0.29,0.215,0.2,102.884957573076]
["SL_PHSS1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,47.88,0,0.305,0.21,0.2,90.7258968]
["SL_PHSS1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,47.88,0.026,0.305,0.21,0.2,93.0847701168]
["SL_PHSS1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,47.88,0.052676,0.305,0.21,0.2,95.50497413983679]
["SL_PHSS1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,47.88,0.08004558,0.305,0.21,0.2,97.98810383037613]
["SL_PM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,63.8,0,0.29,0.215,0.2,119.99631599999998]
["SL_PM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,63.8,0.029,0.29,0.215,0.2,123.476209164]
["SL_PM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,63.8,0.057812,0.29,0.215,0.2,126.933543020592]
["SL_PM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,63.8,0.085315,0.29,0.215,0.2,130.23380169954004]
["SL_PM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,63.8,0.113533,0.29,0.215,0.2,133.61985774442797]
["SL_PM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,63.8,0.142485,0.29,0.215,0.2,137.09399108526]
["SL_PM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,83.63,0,0.305,0.21,0.2,158.46714179999998]
["SL_PM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,83.63,0.026,0.305,0.21,0.2,162.58728748679997]
["SL_PM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,83.63,0.052676,0.305,0.21,0.2,166.81455696145676]
["SL_PM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,83.63,0.08004558,0.305,0.21,0.2,171.1517360763232]
["SL_POWB",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_POWB1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_QAO","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_QAO","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_QAO","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_QAO","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_QAO","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_QAO","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_QAO1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,35.53,0,0.305,0.21,0.2,67.3243758]
["SL_QAO1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,35.53,0.026,0.305,0.21,0.2,69.0748095708]
["SL_QAO1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,35.53,0.052676,0.305,0.21,0.2,70.87075461964079]
["SL_QAO1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,35.53,0.08004558,0.305,0.21,0.2,72.71339450904895]
["SL_SEE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_SEE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_SEE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_SEE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_SEE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_SEE","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_SEE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,54.62,0,0.305,0.21,0.2,103.49725319999999]
["SL_SEE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,54.62,0.026,0.305,0.21,0.2,106.18818178319998]
["SL_SEE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,54.62,0.052676,0.305,0.21,0.2,108.94907450956318]
["SL_SEE1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,54.62,0.08004558,0.305,0.21,0.2,111.78175086080083]
["SL_SEEM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_SEEM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_SEEM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_SEEM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_SEEM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_SEEM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_SEEM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,54.62,0,0.305,0.21,0.2,103.49725319999999]
["SL_SEEM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,54.62,0.026,0.305,0.21,0.2,106.18818178319998]
["SL_SEEM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,54.62,0.052676,0.305,0.21,0.2,108.94907450956318]
["SL_SEEM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,54.62,0.08004558,0.305,0.21,0.2,111.78175086080083]
["SL_SEL","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2003-10-01","ESC37895",null,38,0,0,0,0.2,45.6]
["SL_SEL","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2004-10-01","ESC38261",null,38,0.029,0,0,0.2,46.922399999999996]
["SL_SEL","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2005-10-01","ESC38626",null,38,0.057812,0,0,0.2,48.236227199999995]
["SL_SEL","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2006-10-01","ESC38991",null,38,0.085315,0,0,0.2,49.490364]
["SL_SEL","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2007-10-01","ESC39356",null,38,0.113533,0,0,0.2,50.7771048]
["SL_SEL","ESC","SL_FRNGX","SL_LEAVX","SL_OH1","2008-10-01","ESC39722",null,38,0.142485,0,0,0.2,52.09731599999999]
["SL_SEL1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN1","2005-10-01","ESC138626",null,38,0,0,0,0.2,45.6]
["SL_SEL1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN1","2006-10-01","ESC138991",null,38,0.026,0,0,0.2,46.785599999999995]
["SL_SEL1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN1","2007-10-01","ESC139356",null,38,0.052676,0,0,0.2,48.0020256]
["SL_SEL1","ESC1","SL_FRNGX","SL_LEAVX","SL_OHN1","2008-10-01","ESC139722",null,38,0.08004558,0,0,0.2,49.250078448]
["SL_SEPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,32.28,0,0.29,0.215,0.2,60.71286960000001]
["SL_SEPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,32.28,0.029,0.29,0.215,0.2,62.47354281839999]
["SL_SEPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,32.28,0.057812,0.29,0.215,0.2,64.2228020173152]
["SL_SEPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,32.28,0.085315,0.29,0.215,0.2,65.892588069924]
["SL_SEPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,32.28,0.113533,0.29,0.215,0.2,67.60578382429681]
["SL_SEPM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,32.28,0.142485,0.29,0.215,0.2,69.363542824956]
["SL_SEPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,32.28,0,0.305,0.21,0.2,61.166080799999996]
["SL_SEPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,32.28,0.026,0.305,0.21,0.2,62.756398900799994]
["SL_SEPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,32.28,0.052676,0.305,0.21,0.2,64.38806527222079]
["SL_SEPM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,32.28,0.08004558,0.305,0.21,0.2,66.06215521396287]
["SL_SRA","ESC","SL_OH1",null,null,"2003-10-01","ESC37895",null,20.83,0,0.2,null,null,24.996]
["SL_SRA","ESC","SL_OH1",null,null,"2004-10-01","ESC38261",null,20.83,0.029,0.2,null,null,25.720883999999995]
["SL_SRA","ESC","SL_OH1",null,null,"2005-10-01","ESC38626",null,20.83,0.057812,0.2,null,null,26.441068751999996]
["SL_SRA","ESC","SL_OH1",null,null,"2006-10-01","ESC38991",null,20.83,0.085315,0.2,null,null,27.128533739999998]
["SL_SRA","ESC","SL_OH1",null,null,"2007-10-01","ESC39356",null,20.83,0.113533,0.2,null,null,27.833870867999995]
["SL_SRA","ESC","SL_OH1",null,null,"2008-10-01","ESC39722",null,20.83,0.142485,0.2,null,null,28.557555059999995]
["SL_SRA1","ESC1","SL_OHN1",null,null,"2005-10-01","ESC138626",null,20.83,0,0.2,null,null,24.996]
["SL_SRA1","ESC1","SL_OHN1",null,null,"2006-10-01","ESC138991",null,20.83,0.026,0.2,null,null,25.645895999999997]
["SL_SRA1","ESC1","SL_OHN1",null,null,"2007-10-01","ESC139356",null,20.83,0.052676,0.2,null,null,26.312689296]
["SL_SRA1","ESC1","SL_OHN1",null,null,"2008-10-01","ESC139722",null,20.83,0.08004558,0.2,null,null,26.996819317679996]
["SL_STUP",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_STUP1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_TMUC","ESC","SL_FRING1","SL_LEAV1","SL_OH1","2003-10-01","ESC37895",null,60.55,0,1,0,0.2,145.32]
["SL_TMUC","ESC","SL_FRING1","SL_LEAV1","SL_OH1","2004-10-01","ESC38261",null,60.55,0.029,1,0,0.2,149.53427999999997]
["SL_TMUC","ESC","SL_FRING1","SL_LEAV1","SL_OH1","2005-10-01","ESC38626",null,60.55,0.057812,1,0,0.2,153.72123983999998]
["SL_TMUC","ESC","SL_FRING1","SL_LEAV1","SL_OH1","2006-10-01","ESC38991",null,60.55,0.085315,1,0,0.2,157.7179758]
["SL_TMUC","ESC","SL_FRING1","SL_LEAV1","SL_OH1","2007-10-01","ESC39356",null,60.55,0.113533,1,0,0.2,161.81861555999998]
["SL_TMUC","ESC","SL_FRING1","SL_LEAV1","SL_OH1","2008-10-01","ESC39722",null,60.55,0.142485,1,0,0.2,166.02592019999997]
["SL_TMUC1","ESC1","SL_FRING1","SL_LEAV1","SL_OHN1","2005-10-01","ESC138626",null,60.55,0,1,0,0.2,145.32]
["SL_TMUC1","ESC1","SL_FRING1","SL_LEAV1","SL_OHN1","2006-10-01","ESC138991",null,60.55,0.026,1,0,0.2,149.09832]
["SL_TMUC1","ESC1","SL_FRING1","SL_LEAV1","SL_OHN1","2007-10-01","ESC139356",null,60.55,0.052676,1,0,0.2,152.97487632]
["SL_TMUC1","ESC1","SL_FRING1","SL_LEAV1","SL_OHN1","2008-10-01","ESC139722",null,60.55,0.08004558,1,0,0.2,156.9522236856]
["SL_TMUE","ESC","SL_OH1",null,null,"2003-10-01","ESC37895",null,77.99,0,0.2,null,null,93.588]
["SL_TMUE","ESC","SL_OH1",null,null,"2004-10-01","ESC38261",null,77.99,0.029,0.2,null,null,96.30205199999999]
["SL_TMUE","ESC","SL_OH1",null,null,"2005-10-01","ESC38626",null,77.99,0.057812,0.2,null,null,98.998509456]
["SL_TMUE","ESC","SL_OH1",null,null,"2006-10-01","ESC38991",null,77.99,0.085315,0.2,null,null,101.57246021999998]
["SL_TMUE","ESC","SL_OH1",null,null,"2007-10-01","ESC39356",null,77.99,0.113533,0.2,null,null,104.21332640399999]
["SL_TMUE","ESC","SL_OH1",null,null,"2008-10-01","ESC39722",null,77.99,0.142485,0.2,null,null,106.92288617999999]
["SL_TMUE1","ESC1","SL_OHN1",null,null,"2005-10-01","ESC138626",null,77.99,0,0.2,null,null,93.588]
["SL_TMUE1","ESC1","SL_OHN1",null,null,"2006-10-01","ESC138991",null,77.99,0.026,0.2,null,null,96.021288]
["SL_TMUE1","ESC1","SL_OHN1",null,null,"2007-10-01","ESC139356",null,77.99,0.052676,0.2,null,null,98.51784148799999]
["SL_TMUE1","ESC1","SL_OHN1",null,null,"2008-10-01","ESC139722",null,77.99,0.08004558,0.2,null,null,101.07930574103999]
["SL_TMUI","ESC","SL_OH1",null,null,"2003-10-01","ESC37895",null,61.62,0,0.2,null,null,73.94399999999999]
["SL_TMUI","ESC","SL_OH1",null,null,"2004-10-01","ESC38261",null,61.62,0.029,0.2,null,null,76.08837599999998]
["SL_TMUI","ESC","SL_OH1",null,null,"2005-10-01","ESC38626",null,61.62,0.057812,0.2,null,null,78.218850528]
["SL_TMUI","ESC","SL_OH1",null,null,"2006-10-01","ESC38991",null,61.62,0.085315,0.2,null,null,80.25253235999999]
["SL_TMUI","ESC","SL_OH1",null,null,"2007-10-01","ESC39356",null,61.62,0.113533,0.2,null,null,82.33908415199998]
["SL_TMUI","ESC","SL_OH1",null,null,"2008-10-01","ESC39722",null,61.62,0.142485,0.2,null,null,84.47991083999999]
["SL_TMUI1","ESC1","SL_OHN1",null,null,"2005-10-01","ESC138626",null,61.62,0,0.2,null,null,73.94399999999999]
["SL_TMUI1","ESC1","SL_OHN1",null,null,"2006-10-01","ESC138991",null,61.62,0.026,0.2,null,null,75.86654399999999]
["SL_TMUI1","ESC1","SL_OHN1",null,null,"2007-10-01","ESC139356",null,61.62,0.052676,0.2,null,null,77.83907414399998]
["SL_TMUI1","ESC1","SL_OHN1",null,null,"2008-10-01","ESC139722",null,61.62,0.08004558,0.2,null,null,79.86289036751998]
["SL_TMUO","ESC","SL_OH1",null,null,"2003-10-01","ESC37895",null,64.45,0,0.2,null,null,77.34]
["SL_TMUO","ESC","SL_OH1",null,null,"2004-10-01","ESC38261",null,64.45,0.029,0.2,null,null,79.58286]
["SL_TMUO","ESC","SL_OH1",null,null,"2005-10-01","ESC38626",null,64.45,0.057812,0.2,null,null,81.81118008]
["SL_TMUO","ESC","SL_OH1",null,null,"2006-10-01","ESC38991",null,64.45,0.085315,0.2,null,null,83.9382621]
["SL_TMUO","ESC","SL_OH1",null,null,"2007-10-01","ESC39356",null,64.45,0.113533,0.2,null,null,86.12064222]
["SL_TMUO","ESC","SL_OH1",null,null,"2008-10-01","ESC39722",null,64.45,0.142485,0.2,null,null,88.35978990000001]
["SL_TMUO1","ESC1","SL_OHN1",null,null,"2005-10-01","ESC138626",null,64.45,0,0.2,null,null,77.34]
["SL_TMUO1","ESC1","SL_OHN1",null,null,"2006-10-01","ESC138991",null,64.45,0.026,0.2,null,null,79.35084]
["SL_TMUO1","ESC1","SL_OHN1",null,null,"2007-10-01","ESC139356",null,64.45,0.052676,0.2,null,null,81.41396184]
["SL_TMUO1","ESC1","SL_OHN1",null,null,"2008-10-01","ESC139722",null,64.45,0.08004558,0.2,null,null,83.5307251572]
["SL_TMUP","ESC","SL_OH1",null,null,"2003-10-01","ESC37895",null,74.69,0,0.2,null,null,89.628]
["SL_TMUP","ESC","SL_OH1",null,null,"2004-10-01","ESC38261",null,74.69,0.029,0.2,null,null,92.227212]
["SL_TMUP","ESC","SL_OH1",null,null,"2005-10-01","ESC38626",null,74.69,0.057812,0.2,null,null,94.80957393599998]
["SL_TMUP","ESC","SL_OH1",null,null,"2006-10-01","ESC38991",null,74.69,0.085315,0.2,null,null,97.27461282]
["SL_TMUP","ESC","SL_OH1",null,null,"2007-10-01","ESC39356",null,74.69,0.113533,0.2,null,null,99.80373572399999]
["SL_TMUP","ESC","SL_OH1",null,null,"2008-10-01","ESC39722",null,74.69,0.142485,0.2,null,null,102.39864558]
["SL_TMUP1","ESC1","SL_OHN1",null,null,"2005-10-01","ESC138626",null,74.69,0,0.2,null,null,89.628]
["SL_TMUP1","ESC1","SL_OHN1",null,null,"2006-10-01","ESC138991",null,74.69,0.026,0.2,null,null,91.958328]
["SL_TMUP1","ESC1","SL_OHN1",null,null,"2007-10-01","ESC139356",null,74.69,0.052676,0.2,null,null,94.34924452799999]
["SL_TMUP1","ESC1","SL_OHN1",null,null,"2008-10-01","ESC139722",null,74.69,0.08004558,0.2,null,null,96.80232524424]
["SL_TMUW","ESC","SL_OH1",null,null,"2003-10-01","ESC37895",null,61.62,0,0.2,null,null,73.94399999999999]
["SL_TMUW","ESC","SL_OH1",null,null,"2004-10-01","ESC38261",null,61.62,0.029,0.2,null,null,76.08837599999998]
["SL_TMUW","ESC","SL_OH1",null,null,"2005-10-01","ESC38626",null,61.62,0.057812,0.2,null,null,78.218850528]
["SL_TMUW","ESC","SL_OH1",null,null,"2006-10-01","ESC38991",null,61.62,0.085315,0.2,null,null,80.25253235999999]
["SL_TMUW","ESC","SL_OH1",null,null,"2007-10-01","ESC39356",null,61.62,0.113533,0.2,null,null,82.33908415199998]
["SL_TMUW","ESC","SL_OH1",null,null,"2008-10-01","ESC39722",null,61.62,0.142485,0.2,null,null,84.47991083999999]
["SL_TMUW1","ESC1","SL_OHN1",null,null,"2005-10-01","ESC138626",null,61.62,0,0.2,null,null,73.94399999999999]
["SL_TMUW1","ESC1","SL_OHN1",null,null,"2006-10-01","ESC138991",null,61.62,0.026,0.2,null,null,75.86654399999999]
["SL_TMUW1","ESC1","SL_OHN1",null,null,"2007-10-01","ESC139356",null,61.62,0.052676,0.2,null,null,77.83907414399998]
["SL_TMUW1","ESC1","SL_OHN1",null,null,"2008-10-01","ESC139722",null,61.62,0.08004558,0.2,null,null,79.86289036751998]
["SL_TSM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_TSM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_TSM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_TSM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_TSM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_TSM","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_TSM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,54.62,0,0.305,0.21,0.2,103.49725319999999]
["SL_TSM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,54.62,0.026,0.305,0.21,0.2,106.18818178319998]
["SL_TSM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,54.62,0.052676,0.305,0.21,0.2,108.94907450956318]
["SL_TSM1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,54.62,0.08004558,0.305,0.21,0.2,111.78175086080083]
["SL_UPGR",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_UPGR1",{"$nulls":5},"",null,1,{"$nulls":4},1]
["SL_UTR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2003-10-01","ESC37895",null,54.62,0,0.29,0.215,0.2,102.73038840000001]
["SL_UTR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2004-10-01","ESC38261",null,54.62,0.029,0.29,0.215,0.2,105.70956966359999]
["SL_UTR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2005-10-01","ESC38626",null,54.62,0.057812,0.29,0.215,0.2,108.66943761418081]
["SL_UTR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2006-10-01","ESC38991",null,54.62,0.085315,0.29,0.215,0.2,111.49483148634599]
["SL_UTR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2007-10-01","ESC39356",null,54.62,0.113533,0.29,0.215,0.2,114.3936775862172]
["SL_UTR","ESC","SL_FRNGE","SL_LEAVE","SL_OH1","2008-10-01","ESC39722",null,54.62,0.142485,0.29,0.215,0.2,117.36792779117398]
["SL_UTR1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2005-10-01","ESC138626",null,54.62,0,0.305,0.21,0.2,103.49725319999999]
["SL_UTR1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2006-10-01","ESC138991",null,54.62,0.026,0.305,0.21,0.2,106.18818178319998]
["SL_UTR1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2007-10-01","ESC139356",null,54.62,0.052676,0.305,0.21,0.2,108.94907450956318]
["SL_UTR1","ESC1","SL_FRNG1","SL_LEAV2","SL_OHN1","2008-10-01","ESC139722",null,54.62,0.08004558,0.305,0.21,0.2,111.78175086080083]
["SPR",{"$nulls":5},"",{"$nulls":6},0]
[null,"END",{"$nulls":4},"END",{"$nulls":6},0]

{"sheet":"Master","index":3,"n_rows":1496,"n_cols":58,"rows_kept":1496,"cut":false,"hidden":false,"merged":[[0,45,0,46],[0,32,0,33],[0,34,0,36],[0,0,0,5],[0,37,0,38],[0,39,0,40],[0,41,0,42],[0,43,0,44],[1,0,1,5],[0,18,0,20],[0,16,0,17]],"flags":["formulas_cached_only"]}
["WBS Level",{"$nulls":5},"P3","C/A","W/P","LCLA  DCE xxx-2007","Early","Early","OBS","Fund","Res","Units","Budgeted Quantity",null,"Fully Burdened and Escalated Cost",null,null,"Work","Contingency","Contingency","Design","Judgement",{"$nulls":6},"Work Rem. Bud. Qtty",null,"Work Rem. Full Burd and Escltd Cost",null,null,"FY05",null,"FY06",null,"FY07",null,"FY08",null,"FY09",null,"Contingency","Contingency","Design","Judgement","Basis","Program",null,"Tech"]
[{"$nulls":6},"ID","Number","Number","Description","Start","Finish",null,"Type","Code",null,"Hours","$$","Labor","M&S","Total (No Conting)","Remaining","%","$","Maturity","Factor",{"$nulls":6},"Hours","$$","Labor","M&S","Total","BAC","% of Wrk Rem.","BAC","% of Wrk Rem.","BAC","% of Wrk Rem.","BAC","% of Wrk Rem.","BAC","% of Wrk Rem.","%","$","Maturity","Factor","of Estimate","Phase","CAM","Lead",null,null,"CAM"]
["1","2","3","4","5","6",{"$nulls":20},"Flag","Cam"]
[]
["1","  ","  ","  ","  ","  ",null,null,null,"LCLS PROJECT - PED & CONSTRUCTION                           "]
["1","01","  ","  ","  ","  ",null,null,null,"LCLS PROJECT MGMT, PLANNING & ADMN (TEC)                    "]
["1","01","01","  ","  ","  ",null,null,null,"Environment, Safety & Health                                "]
["1","01","01","01","  ","  ",null,null,null,"Radiation Physics                                           "]
["1","01","01","02","  ","  ",null,null,null,"ESH Management & Coordination                               "]
["1","01","01","03","  ","  ",null,null,null,"Seismic & Engineering Support                               "]
["1","01","02","  ","  ","  ",null,null,null,"Project Management                                          "]
["1","01","02","01","  ","  ",null,null,null,"Project Management Office                                   "]
["1","01","02","01","01","  ",null,null,null,"Project Office - General                                    "]
["1","01","02","01","02","  ",null,null,null,"Project Support                                             "]
["1","01","02","01","03","  ",null,null,null,"Project Office M&S                                          "]
["1","01","02","01","04","  ",null,null,null,"SSRL Physics Support                                        "]
["1","01","03","  ","  ","  ",null,null,null,"Technical Integration                                       "]
["1","01","03","01","  ","  ",null,null,null,"Global Laser Coordination                                   "]
["1","01","03","02","  ","  ",null,null,null,"Global Alignment Coordination                               "]
["1","01","03","03","  ","  ",null,null,null,"System Integration                                          "]
["1","01","03","05","  ","  ",null,null,null,"Global Controls                                             "]
["1","01","03","05","01","  ",null,null,null,"Global Controls Management                                  "]
["1","01","03","05","02","  ",null,null,null,"LLRF Controls                                               "]
["1","01","03","05","03","  ",null,null,null,"E-beam Diagnostics & Controls                               "]
["1","01","03","05","03","01",null,null,null,"Controls - Wire Scanners                                    "]
["1","01","03","05","03","02",null,null,null,"Controls - Toroids                                          "]
["1","01","03","05","03","03",null,null,null,"Controls - Faraday Cups                                     "]
["1","01","03","05","03","04",null,null,null,"Controls - Tune-Up Dump                                     "]
["1","01","03","05","03","05",null,null,null,"Controls - Profile Monitors                                 "]
["1","01","03","05","03","06",null,null,null,"Controls - E/O Diagnostics                                  "]
["1","01","03","05","03","07",null,null,null,"Controls - BPM                                              "]
["1","01","03","05","03","08",null,null,null,"Controls - Stopppers                                        "]
["1","01","03","05","03","09",null,null,null,"Controls - Bunch Length Monitors                            "]
["1","01","03","05","03","10",null,null,null,"Controls - Beam Loss Monitors                               "]
["1","01","03","05","03","11",null,null,null,"Controls - Cherenkov Radiation Detector                     "]
["1","01","03","05","03","12",null,null,null,"Controls - Movable Collimator                               "]
["1","01","03","05","04","  ",null,null,null,"Laser Controls Design                                       "]
["1","01","03","05","05","  ",null,null,null,"Laser Heater Controls                                       "]
["1","01","03","05","06","  ",null,null,null,"Timing Controls                                             "]
["1","01","03","05","07","  ",null,null,null,"Vacuum Controls                                             "]
["1","01","03","05","09","  ",null,null,null,"Power Supply Controls                                       "]
["1","01","03","05","10","  ",null,null,null,"Controls - PPS                                              "]
["1","01","03","05","11","  ",null,null,null,"Controls - MPS                                              "]
["1","01","03","05","12","  ",null,null,null,"Global Controls Management                                  "]
["1","01","03","05","12","01",null,null,null,"Global Controls Management LOE                              "]
["1","01","03","05","12","02",null,null,null,"Global Controls Management                                  "]
["1","01","03","05","13","  ",null,null,null,"SLC Aware IOC                                               "]
["1","01","03","05","14","  ",null,null,null,"Controls - S/W Application                                  "]
["1","01","03","05","15","  ",null,null,null,"Controls - BCS                                              "]
["1","01","03","06","  ","  ",null,null,null,"Technical Requirements/Parameters                           "]
["1","01","04","  ","  ","  ",null,null,null,"Education Support                                           "]
["1","01","04","01","  ","  ",null,null,null,"Education/Outreach Travel                                   "]
["1","01","04","02","  ","  ",null,null,null,"Education/Outreach M&S                                      "]
["1","02","  ","  ","  ","  ",null,null,null,"INJECTOR SYSTEM                                             "]
["1","02","01","  ","  ","  ",null,null,null,"Injector System Management & Integration                    "]
["1","02","01","01","  ","  ",null,null,null,"Injector System Integration                                 "]
["1","02","01","01","01","  ",null,null,null,"Injector Region Integration                                 "]
["1","02","01","01","02","  ",null,null,null,"Gun Area Integration                                        "]
["1","02","01","01","03","  ",null,null,null,"Accelerator Area Integration                                "]
["1","02","01","01","04","  ",null,null,null,"Heater Area Integration                                     "]
["1","02","01","01","05","  ",null,null,null,"Wall Area Integration                                       "]
["1","02","01","01","06","  ",null,null,null,"Insertion Area Integration                                  "]
["1","02","01","01","07","  ",null,null,null,"Spectrometer Area Integration                               "]
["1","02","01","01","08","  ",null,null,null,"Drive Laser Integration                                     "]
["1","02","01","04","  ","  ",null,null,null,"Injector System Integration Effort / M&S                    "]
["1","02","02","  ","  ","  ",null,null,null,"Injector Controls Subsystem                                 "]
["1","02","02","01","  ","  ",null,null,null,"Personnel Protection Subsystem (PPS)                        "]
["1","02","02","02","  ","  ",null,null,null,"Beam Containment Subsystem (BCS)                            "]
["1","02","02","03","  ","  ",null,null,null,"Machine Protection Subsystem (MPS)                          "]
["1","02","02","04","  ","  ",null,null,null,"Injector Power Conversion                                   "]
["1","02","02","04","01","  ",null,null,null,"Beamline Pwr Supplies - (Dipole Type)                       "]
["1","02","02","04","01","01",null,null,null,"10kw Power Supply - (Solenoid 1)                            "]
["1","02","02","04","01","02",null,null,null,"30kw Power Supply - (Solenoid 2)                            "]
["1","02","02","04","01","03",null,null,null,"2kw Power Supply - (B0.5 Spect)                             "]
["1","02","02","04","01","04",null,null,null,"15kw Power Supply - (B1-2)                                  "]
["1","02","02","04","01","05",null,null,null,"15kw Power Supply - (B3 Spect)                              "]
["1","02","02","04","01","06",null,null,null,"10kw Power Supply - (New)                                   "]
["1","02","02","04","02","  ",null,null,null,"Power Supply Controls                                       "]
["1","02","02","04","03","  ",null,null,null,"Beamline Pwr Supplies - (Trim Type)                         "]
["1","02","02","04","03","01",null,null,null,"12Amp Power Supply - (MCOR_1)                               "]
["1","02","02","04","03","02",null,null,null,"30Amp Power Supply - (MCOR_2)                               "]
["1","02","02","04","03","03",null,null,null,"30Amp Power Supply - (MCOR_3)                               "]
["1","02","02","04","03","04",null,null,null,"30Amp Power Supply - (MCOR_4)                               "]
["1","02","02","04","04","  ",null,null,null,"Beamline Pwr Supply - Misc Hdwr                             "]
["1","02","02","04","05","  ",null,null,null,"Magnet Interlock Protection System                          "]
["1","02","02","05","  ","  ",null,null,null,"LLRF Controls                                               "]
["1","02","02","05","01","  ",null,null,null,"Readback & Controls - RF Gun LLRF & Temperature             "]
["1","02","02","05","02","  ",null,null,null,"Readback & Controls - L0 LLRF                               "]
["1","02","02","05","03","  ",null,null,null,"Readback & Controls - Transverse Cavity LLRF                "]
["1","02","02","05","04","  ",null,null,null,"S-Band Cavity Controls                                      "]
["1","02","02","05","05","  ",null,null,null,"EO Phase Controls                                           "]
["1","02","02","06","  ","  ",null,null,null,"E-Beam Diagnostics Controls                                 "]
["1","02","02","06","01","  ",null,null,null,"Controls - Wire Scanners                                    "]
["1","02","02","06","02","  ",null,null,null,"Controls - BPM                                              "]
["1","02","02","06","03","  ",null,null,null,"Controls - Toroids                                          "]
["1","02","02","06","05","  ",null,null,null,"Controls - Profile Monitors                                 "]
["1","02","02","06","06","  ",null,null,null,"Controls - E/O Diagnostics                                  "]
["1","02","02","06","12","  ",null,null,null,"Controls - Movable Collimator                               "]
["1","02","02","06","14","  ",null,null,null,"Controls - Faraday Cups                                     "]
["1","02","02","06","15","  ",null,null,null,"Controls - Tune-Up Dump                                     "]
["1","02","02","06","16","  ",null,null,null,"Controls - Cherenkov Radiation Detector                     "]
["1","02","02","08","  ","  ",null,null,null,"Timing Controls                                             "]
["1","02","02","09","  ","  ",null,null,null,"Vacuum Controls                                             "]
["1","02","02","10","  ","  ",null,null,null,"Software & Controls Infrastructure                          "]
["1","02","02","10","01","  ",null,null,null,"Low Level Application Software                              "]
["1","02","02","10","02","  ",null,null,null,"High Level Application Software                             "]
["1","02","02","10","03","  ",null,null,null,"Data Communications                                         "]
["1","02","02","10","04","  ",null,null,null,"Computers & Crates                                          "]
["1","02","02","11","  ","  ",null,null,null,"EPICS VXI Control Modules                                   "]
["1","02","02","12","  ","  ",null,null,null,"Laser Controls                                              "]
["1","02","02","12","01","  ",null,null,null,"Controls - Alignment Laser                                  "]
["1","02","02","12","02","  ",null,null,null,"Controls - Gun Laser                                        "]
["1","02","02","13","  ","  ",null,null,null,"Laser Heater Controls                                       "]
["1","02","03","  ","  ","  ",null,null,null,"Injector Lasers                                             "]
["1","02","03","01","  ","  ",null,null,null,"Drive Laser Support                                         "]
["1","02","03","01","01","  ",null,null,null,"Drive Laser Support (ANL)                                   "]
["1","02","03","01","02","  ",null,null,null,"Drive Laser Support (LLNL)                                  "]
["1","02","03","02","  ","  ",null,null,null,"Drive Laser System                                          "]
["1","02","03","03","  ","  ",null,null,null,"Drive Laser Diagnostics                                     "]
["1","02","03","04","  ","  ",null,null,null,"Timing Stability Monitoring                                 "]
["1","02","03","05","  ","  ",null,null,null,"Steering Stability Feedback & Msmts                         "]
["1","02","03","06","  ","  ",null,null,null,"Pre Amp Low Power Comp                                      "]
["1","02","03","07","  ","  ",null,null,null,"Transport to Tunnel & Relay Optics                          "]
["1","02","03","08","  ","  ",null,null,null,"UV Launch, Conditioning & Diagnostics                       "]
["1","02","03","09","  ","  ",null,null,null,"Load Lock Transport System                                  "]
["1","02","03","10","  ","  ",null,null,null,"Visible Optical Transport & Optics                          "]
["1","02","03","11","  ","  ",null,null,null,"LB Infrastructure & LB System Wide Items                    "]
["1","02","03","12","  ","  ",null,null,null,"Alignment Laser                                             "]
["1","02","03","13","  ","  ",null,null,null,"Light path to Streak Camera                                 "]
["1","02","03","14","  ","  ",null,null,null,"LSR HTR - Beam Conditioning Optics (Laser Bay)              "]
["1","02","03","15","  ","  ",null,null,null,"LSR HTR - Transport Optics (Bay to Tunnel)                  "]
["1","02","03","16","  ","  ",null,null,null,"LSR HTR - Photon Beam Diagnostics                           "]
["1","02","03","21","  ","  ",null,null,null,"UV Conv Harmonic Generation Unit (Closed Account)           "]
["1","02","04","  ","  ","  ",null,null,null,"Injector RF Subsystem                                       "]
["1","02","04","01","  ","  ",null,null,null,"RF Gun & Load Lock                                          "]
["1","02","04","01","01","  ",null,null,null,"RF Gun                                                      "]
["1","02","04","01","02","  ",null,null,null,"RF Gun Supports                                             "]
["1","02","04","01","03","  ",null,null,null,"Gun Load Lock                                               "]
["1","02","04","01","04","  ",null,null,null,"Gun Load Lock Supports                                      "]
["1","02","04","01","05","  ",null,null,null,"Gun Solenoid                                                "]
["1","02","04","01","06","  ",null,null,null,"Gun Solenoid Supports                                       "]
["1","02","04","01","07","  ",null,null,null,"Gun RF Feed                                                 "]
["1","02","04","01","08","  ",null,null,null,"Gun RF Feed Supports                                        "]
["1","02","04","02","  ","  ",null,null,null,"Cathode Processing (CP) Station                             "]
["1","02","04","02","01","  ",null,null,null,"CP Cathode Assembly & Supports                              "]
["1","02","04","02","02","  ",null,null,null,"CP Load Lock                                                "]
["1","02","04","02","03","  ",null,null,null,"CP Load Lock Supports                                       "]
["1","02","04","02","04","  ",null,null,null,"CP Station                                                  "]
["1","02","04","02","05","  ",null,null,null,"Cathode Lab Infrastructure                                  "]
["1","02","04","03","  ","  ",null,null,null,"S-Band Low Level Timing                                     "]
["1","02","04","03","01","  ",null,null,null,"Controls Interface & Timing                                 "]
["1","02","04","03","02","  ",null,null,null,"LLRF Phase Reference System                                 "]
["1","02","04","03","03","  ",null,null,null,"LLRF Monitor & Control System                               "]
["1","02","04","03","04","  ",null,null,null,"Beam Phase Monitor Cavity                                   "]
["1","02","04","03","05","  ",null,null,null,"RF System S/W Development / Docs                            "]
["1","02","04","04","  ","  ",null,null,null,"S-Band High Power System                                    "]
["1","02","04","04","01","  ",null,null,null,"RF Gun High Power                                           "]
["1","02","04","04","02","  ",null,null,null,"L0 High Power                                               "]
["1","02","04","04","03","  ",null,null,null,"Transverse Cavity High Power                                "]
["1","02","04","05","  ","  ",null,null,null,"Injector RF Waveguide Subsystem                             "]
["1","02","04","05","01","  ",null,null,null,"RF Waveguides                                               "]
["1","02","04","05","02","  ",null,null,null,"RF Waveguide Supports                                       "]
["1","02","04","06","  ","  ",null,null,null,"Injector Linac Structures                                   "]
["1","02","04","06","01","  ",null,null,null,"L0A-0B Structure Assembly                                   "]
["1","02","04","06","03","  ",null,null,null,"Major Linac Support                                         "]
["1","02","04","06","04","  ",null,null,null,"GTL RF Phase Cavity                                         "]
["1","02","04","06","05","  ",null,null,null,"LTDL1 RF Kicker                                             "]
["1","02","05","  ","  ","  ",null,null,null,"Injector Magnets & Supports                                 "]
["1","02","05","01","  ","  ",null,null,null,"Injector Dipoles                                            "]
["1","02","05","01","01","  ",null,null,null,"Gun Spectrometer Dipole                                     "]
["1","02","05","01","02","  ",null,null,null,"DL1 B01 & B02 Dipoles                                       "]
["1","02","05","01","03","  ",null,null,null,"SAB Spectrometer Dipole                                     "]
["1","02","05","01","04","  ",null,null,null,"Chicane DIPOLES (4)                                         "]
["1","02","05","02","  ","  ",null,null,null,"Injector Quads                                              "]
["1","02","05","02","01","  ",null,null,null,"Gun Spectrometer Quadrupoles                                "]
["1","02","05","02","02","  ",null,null,null,"Injector Quadrupoles                                        "]
["1","02","05","02","03","  ",null,null,null,"                                                            "]
["1","02","05","03","  ","  ",null,null,null,"Injector Steering Coils                                     "]
["1","02","05","03","01","  ",null,null,null,"Gun Solenoid Correctors                                     "]
["1","02","05","03","02","  ",null,null,null,"Gun Spectrometer Correctors                                 "]
["1","02","05","03","03","  ",null,null,null,"Injector Correctors - A                                     "]
["1","02","05","03","04","  ",null,null,null,"Injector Correctors - D (Gun)                               "]
["1","02","05","03","05","  ",null,null,null,"Gun Solenoid Quadrupole Correctors                          "]
["1","02","05","04","  ","  ",null,null,null,"Linac Solenoid                                              "]
["1","02","05","05","  ","  ",null,null,null,"Injector Laser Heater Subsystem                             "]
["1","02","05","05","01","  ",null,null,null,"System Design & Optimization (LSR HTR)                      "]
["1","02","05","05","02","  ",null,null,null,"Injector Undulator                                          "]
["1","02","06","  ","  ","  ",null,null,null,"Injector Vacuum & Supports                                  "]
["1","02","06","01","  ","  ",null,null,null,"Injector Vacuum Engineering                                 "]
["1","02","06","02","  ","  ",null,null,null,"Injector Vacuum Components                                  "]
["1","02","06","03","  ","  ",null,null,null,"Injector Vacuum Special Chambers                            "]
["1","02","06","04","  ","  ",null,null,null,"Injector Vacuum Supports Engineering                        "]
["1","02","06","05","  ","  ",null,null,null,"Injector Vacuum Support Components                          "]
["1","02","06","08","  ","  ",null,null,null,"DL1 Vacuum Chamber                                          "]
["1","02","06","10","  ","  ",null,null,null,"DL1TL Vacuum Components                                     "]
["1","02","07","  ","  ","  ",null,null,null,"Injector Diagnostics                                        "]
["1","02","07","01","  ","  ",null,null,null,"Beam Position Monitors                                      "]
["1","02","07","01","01","  ",null,null,null,"Large Aperture BPM                                          "]
["1","02","07","01","02","  ",null,null,null,"Small Aperture BPM                                          "]
["1","02","07","01","06","  ",null,null,null,"                                                            "]
["1","02","07","02","  ","  ",null,null,null,"Current Monitors                                            "]
["1","02","07","02","01","  ",null,null,null,"Current Monitors                                            "]
["1","02","07","03","  ","  ",null,null,null,"Bunch Length Monitors                                       "]
["1","02","07","03","01","  ",null,null,null,"Bunch Length Monitors                                       "]
["1","02","07","04","  ","  ",null,null,null,"Profile Monitors                                            "]
["1","02","07","04","01","  ",null,null,null,"Profile Monitors                                            "]
["1","02","07","04","03","  ",null,null,null,"GS Faraday Cup/YAG2                                         "]
["1","02","07","04","06","  ",null,null,null,"DL1 OTR/YAG                                                 "]
["1","02","07","04","07","  ",null,null,null,"DL1TL OTR/YAG                                               "]
["1","02","07","04","08","  ",null,null,null,"LTDL1 OTR/YAG (6)                                           "]
["1","02","07","05","  ","  ",null,null,null," Injector Wire Scanners                                     "]
["1","02","07","06","  ","  ",null,null,null,"LSR HTR - Electron Beam Diagnostics                         "]
["1","02","07","07","  ","  ",null,null,null,"PPS Stopper                                                 "]
["1","02","17","  ","  ","  ",null,null,null,"Injector Installation & Alignment                           "]
["1","02","17","01","  ","  ",null,null,null,"Injector Infrastructure Installation                        "]
["1","02","17","02","  ","  ",null,null,null,"Injector Controls Subsystem Install & Align                 "]
["1","02","17","03","  ","  ",null,null,null,"Injector Lasers Install & Align                             "]
["1","02","17","04","  ","  ",null,null,null,"Gun Area Integration                                        "]
["1","02","17","06","  ","  ",null,null,null,"Accelerator Area Integration                                "]
["1","02","17","07","  ","  ",null,null,null,"Heater Area Integration                                     "]
["1","02","17","08","  ","  ",null,null,null,"Wall Area Integration                                       "]
["1","02","17","09","  ","  ",null,null,null,"Insertion Area Integration                                  "]
["1","02","17","11","  ","  ",null,null,null,"Spectrometer Area Integration                               "]
["1","02","17","12","  ","  ",null,null,null,"Injector RF High Power System Install & Align               "]
["1","02","17","13","  ","  ",null,null,null,"Injector RF Low Level Install & Align                       "]
["1","02","17","14","  ","  ",null,null,null,"Cathode and Load Lock Install & Align                       "]
["1","02","17","15","  ","  ",null,null,null,"Injector Laser Heater Subsystem Install & Align             "]
["1","02","17","17","  ","  ",null,null,null,"Power  Conversion Subsystem Installation                    "]
["1","02","17","18","  ","  ",null,null,null,"Cathode Processing Center Installation                      "]
["1","03","  ","  ","  ","  ",null,null,null,"LINAC SYSTEM                                                "]
["1","03","01","  ","  ","  ",null,null,null,"System Management & Integration                             "]
["1","03","01","01","  ","  ",null,null,null,"Linac Mechanical Integration                                "]
["1","03","01","01","01","  ",null,null,null,"L01 System Integration                                      "]
["1","03","01","01","02","  ",null,null,null,"BC1 System Integration                                      "]
["1","03","01","01","03","  ",null,null,null,"L02 System Integration                                      "]
["1","03","01","01","04","  ",null,null,null,"BC2 System Integration                                      "]
["1","03","01","01","05","  ",null,null,null,"L03 System Integration                                      "]
["1","03","01","01","06","  ",null,null,null,"LTU System Integration                                      "]
["1","03","01","01","07","  ",null,null,null,"E-Dump System Integration                                   "]
["1","03","01","03","  ","  ",null,null,null,"Travel                                                      "]
["1","03","01","04","  ","  ",null,null,null,"Linac Management                                            "]
["1","03","02","  ","  ","  ",null,null,null,"Linac Controls & Power Conversion Subsystem                 "]
["1","03","02","01","  ","  ",null,null,null,"Personnel Protection System (PPS)                           "]
["1","03","02","02","  ","  ",null,null,null,"Beam Containment System (BCS)                               "]
["1","03","02","03","  ","  ",null,null,null,"Machine Protection System (MPS)                             "]
["1","03","02","04","  ","  ",null,null,null,"Linac Power Conversion Subsystem                            "]
["1","03","02","04","01","  ",null,null,null,"Beamline Power Supplies - (Dipole Type)                     "]
["1","03","02","04","01","01",null,null,null,"Power Supply BX11-14                                        "]
["1","03","02","04","01","02",null,null,null,"Power Supply BX21-24                                        "]
["1","03","02","04","01","03",null,null,null,"Kicker Power Supply BXKIK                                   "]
["1","03","02","04","01","04",null,null,null,"Power Supply BX31,32,35,36                                  "]
["1","03","02","04","01","05",null,null,null,"Power Supply -BY1-2                                         "]
["1","03","02","04","01","06",null,null,null,"Kicker Power Supply BYKIK                                   "]
["1","03","02","04","01","07",null,null,null,"Power Supply BYW1-3                                         "]
["1","03","02","04","01","08",null,null,null,"Muon Spoiler Power Supply MUSPLR                            "]
["1","03","02","04","01","09",null,null,null,"Powe Supply BYD1-3                                          "]
["1","03","02","04","02","  ",null,null,null,"Beamline Power Supplies - (Quad Type)                       "]
["1","03","02","04","02","06",null,null,null,"Q21201-Q21901 Switch Over                                   "]
["1","03","02","04","02","07",null,null,null,"Q24201-Q24501 Split                                         "]
["1","03","02","04","02","08",null,null,null,"Power Supply Q24601                                         "]
["1","03","02","04","02","09",null,null,null,"Power Supply  Q24701A,Q24701B                               "]
["1","03","02","04","02","10",null,null,null,"Power Supply QM21                                           "]
["1","03","02","04","02","11",null,null,null,"Power Supply Q24901A,Q24901B                                "]
["1","03","02","04","02","12",null,null,null,"Power Supply QM22                                           "]
["1","03","02","04","02","13",null,null,null,"Power Supply Q5                                             "]
["1","03","02","04","02","14",null,null,null,"Power Supply Q6                                             "]
["1","03","02","04","02","15",null,null,null,"Power Supply QA0                                            "]
["1","03","02","04","02","16",null,null,null,"Power Supply Q50Q1,Q50Q2,Q50Q3                              "]
["1","03","02","04","02","17",null,null,null,"Power Supply  QVM1                                          "]
["1","03","02","04","02","18",null,null,null,"Power Supply  QVM2                                          "]
["1","03","02","04","02","19",null,null,null,"Power Supply  QVM3                                          "]
["1","03","02","04","02","20",null,null,null,"Power Supply  QVM4                                          "]
["1","03","02","04","02","21",null,null,null,"Power Supply  QVB1-3                                        "]
["1","03","02","04","02","22",null,null,null,"Power Supply  QDL31-34                                      "]
["1","03","02","04","02","23",null,null,null,"Power Supply  QE31-36                                       "]
["1","03","02","04","02","24",null,null,null,"Power Supply  QEM1                                          "]
["1","03","02","04","02","25",null,null,null,"Power Supply  QEM2                                          "]
["1","03","02","04","02","26",null,null,null,"Power Supply  QEM3                                          "]
["1","03","02","04","02","27",null,null,null,"Power Supply  QEM4                                          "]
["1","03","02","04","02","28",null,null,null,"Power Supply QT11,13,21,23,31,33,41,43                      "]
["1","03","02","04","02","29",null,null,null,"Power Supply QT12,22,32,42                                  "]
["1","03","02","04","02","30",null,null,null,"Power Supply  QUM1                                          "]
["1","03","02","04","02","31",null,null,null,"Power Supply  QUM2                                          "]
["1","03","02","04","02","32",null,null,null,"Power Supply  QUM3                                          "]
["1","03","02","04","02","33",null,null,null,"Power Supply QUM4                                           "]
["1","03","02","04","02","34",null,null,null,"Power Supply QDMP1-2                                        "]
["1","03","02","04","02","35",null,null,null,"Power Supply QUE1                                           "]
["1","03","02","04","02","36",null,null,null,"Power Supply QUE2                                           "]
["1","03","02","04","02","37",null,null,null,"Rack Accessories - LI21                                     "]
["1","03","02","04","02","38",null,null,null,"Rack Accessories - LI24                                     "]
["1","03","02","04","02","39",null,null,null,"Rack Accessories - LI25                                     "]
["1","03","02","04","02","40",null,null,null,"Rack Accessories - BSY                                      "]
["1","03","02","04","02","41",null,null,null,"Rack Accessories - Dump                                     "]
["1","03","02","04","03","  ",null,null,null,"Beamline Power Supplies - (Trim Type)                       "]
["1","03","02","04","03","01",null,null,null,"MCOR_1                                                      "]
["1","03","02","04","03","02",null,null,null,"MCOR_2                                                      "]
["1","03","02","04","03","03",null,null,null,"MCOR_3                                                      "]
["1","03","02","04","03","04",null,null,null,"MCOR_4                                                      "]
["1","03","02","04","03","05",null,null,null,"MCOR_5                                                      "]
["1","03","02","04","03","06",null,null,null,"MCOR_6                                                      "]
["1","03","02","04","03","07",null,null,null,"MCOR_BSY1                                                   "]
["1","03","02","04","03","08",null,null,null,"MCOR_LTU1                                                   "]
["1","03","02","04","03","09",null,null,null,"MCOR_LTU2                                                   "]
["1","03","02","04","03","10",null,null,null,"MCOR_LTU3                                                   "]
["1","03","02","04","03","11",null,null,null,"MCOR_LTU4                                                   "]
["1","03","02","04","03","12",null,null,null,"MCOR_LTU5                                                   "]
["1","03","02","04","03","13",null,null,null,"MCOR_LTU6                                                   "]
["1","03","02","04","03","14",null,null,null,"MCOR_LTU7                                                   "]
["1","03","02","04","03","15",null,null,null,"MCOR_LTU8                                                   "]
["1","03","02","04","03","16",null,null,null,"MCOR_LTU9                                                   "]
["1","03","02","04","03","17",null,null,null,"MCOR_DUMP1                                                  "]
["1","03","02","04","03","18",null,null,null,"MCOR Bulk PS - LI21_1                                       "]
["1","03","02","04","03","19",null,null,null,"MCOR Bulk PS - LI21_2                                       "]
["1","03","02","04","03","20",null,null,null,"MCOR Bulk PS - LI24                                         "]
["1","03","02","04","03","21",null,null,null,"MCOR Bulk PS - LI25                                         "]
["1","03","02","04","03","22",null,null,null,"MCOR Bulk PS - BSY                                          "]
["1","03","02","04","03","23",null,null,null,"MCOR Bulk PS - LTU_1                                        "]
["1","03","02","04","03","24",null,null,null,"MCOR Bulk PS - LTU_2                                        "]
["1","03","02","04","03","25",null,null,null,"MCOR Bulk PS - LTU_3                                        "]
["1","03","02","04","03","26",null,null,null,"MCOR Bulk PS - LTU_4                                        "]
["1","03","02","04","03","27",null,null,null,"MCOR PLC - LI21                                             "]
["1","03","02","04","03","28",null,null,null,"MCOR PLC - LI24                                             "]
["1","03","02","04","03","29",null,null,null,"MCOR PLC - LI25                                             "]
["1","03","02","04","03","30",null,null,null,"MCOR PLC - BSY                                              "]
["1","03","02","04","03","31",null,null,null,"MCOR PLC - LTU_1 (BLD 2.1)                                  "]
["1","03","02","04","03","32",null,null,null,"MCOR PLC - LTU_2 (BLD 2.2)                                  "]
["1","03","02","04","03","33",null,null,null,"MCOR PLC - LTU_3 (BLD 2.3)                                  "]
["1","03","02","04","03","34",null,null,null,"MCOR PLC - Dump                                             "]
["1","03","02","04","03","35",null,null,null,"MCOR Bulk Dump                                              "]
["1","03","02","04","03","36",null,null,null,"Rack Accessories - LTU_1 (bld 2.1)                          "]
["1","03","02","04","03","37",null,null,null,"Rack Accessories - LTU_2 (bld 2.2)                          "]
["1","03","02","04","03","38",null,null,null,"Rack Accessories - LTU_3 (bld 2.3)                          "]
["1","03","02","04","04","  ",null,null,null,"Controls & Power Supply                                     "]
["1","03","02","05","  ","  ",null,null,null,"Controls - LLRF                                             "]
["1","03","02","05","01","  ",null,null,null,"Solid State Sub-booster 5X                                  "]
["1","03","02","05","03","  ",null,null,null,"L2/L3 RF Distribution                                       "]
["1","03","02","05","04","  ",null,null,null,"Beam Phase Measurement 2x                                   "]
["1","03","02","05","05","  ",null,null,null,"Sector 24 Rack Electrical Crate / IOC / EVG                 "]
["1","03","02","05","06","  ",null,null,null,"Sector 24 T-Cav                                             "]
["1","03","02","05","07","  ",null,null,null,"Sector 29/30 Controls (PACs & PADs)                         "]
["1","03","02","05","10","  ",null,null,null,"RF Stability / Feedback                                     "]
["1","03","02","05","11","  ",null,null,null,"System Documentation                                        "]
["1","03","02","06","  ","  ",null,null,null,"Controls - E-Beam Diagnostic                                "]
["1","03","02","06","01","  ",null,null,null,"Controls - Wire Scanners                                    "]
["1","03","02","06","02","  ",null,null,null,"Controls - BPMs                                             "]
["1","03","02","06","03","  ",null,null,null,"Controls - Toroids                                          "]
["1","03","02","06","04","  ",null,null,null,"Controls - Stoppers                                         "]
["1","03","02","06","05","  ",null,null,null,"Controls - Profile Monitors                                 "]
["1","03","02","06","06","  ",null,null,null,"Controls - E/O Diagnostics                                  "]
["1","03","02","06","07","  ",null,null,null,"Controls - Bunch Length Monitors                            "]
["1","03","02","06","08","  ",null,null,null,"Controls - Beam Loss Monitors                               "]
["1","03","02","06","09","  ",null,null,null,"Controls - Single Beam Dump                                 "]
["1","03","02","06","10","  ",null,null,null,"Controls - E Beam Dump                                      "]
["1","03","02","06","11","  ",null,null,null,"Controls - Protection Collimator                            "]
["1","03","02","06","12","  ",null,null,null,"Controls - Movable Collimator                               "]
["1","03","02","06","13","  ",null,null,null,"Controls - X-Band Accel Structure                           "]
["1","03","02","08","  ","  ",null,null,null,"Controls - Timing                                           "]
["1","03","02","09","  ","  ",null,null,null,"Controls - Vacuum                                           "]
["1","03","02","09","01","  ",null,null,null,"Controls - Vacuum Instrumentation & Interlocks              "]
["1","03","02","09","02","  ",null,null,null,"Controls - Vacuum Pump Power Supplies                       "]
["1","03","02","10","  ","  ",null,null,null,"Software & Controls Infrastructure                          "]
["1","03","02","10","04","  ",null,null,null,"Data Communications                                         "]
["1","03","02","10","05","  ",null,null,null,"Computers                                                   "]
["1","03","03","  ","  ","  ",null,null,null,"Linac Magnets & Supports                                    "]
["1","03","03","01","  ","  ",null,null,null,"Bend Magnet (BX1_BC1)                                       "]
["1","03","03","02","  ","  ",null,null,null,"Bend Magnet (BX3_LTU)                                       "]
["1","03","03","03","  ","  ",null,null,null,"Bend Magnet (BX2_BC2)                                       "]
["1","03","03","04","  ","  ",null,null,null,"Bend Magnet (BY_LTU)                                        "]
["1","03","03","05","  ","  ",null,null,null,"Quad Magnet (Quad_LTU)                                      "]
["1","03","03","07","  ","  ",null,null,null,"Quad Magnet (QE_BC1/BC2)                                    "]
["1","03","03","08","  ","  ",null,null,null,"Corrector Magnet (Type 4_LTU/E-Dump)                        "]
["1","03","03","09","  ","  ",null,null,null,"Bend Magnet (BYD_E-Dump)                                    "]
["1","03","03","10","  ","  ",null,null,null,"Quad Magnet (E-Dump)                                        "]
["1","03","03","11","  ","  ",null,null,null,"Bend Magnet (BYPM_LTU)                                      "]
["1","03","03","12","  ","  ",null,null,null,"Bend Magnet (BYKIK_LTU)                                     "]
["1","03","03","13","  ","  ",null,null,null,"Bend Magnet (BYW_LTU)                                       "]
["1","03","03","14","  ","  ",null,null,null,"BXKIK LINAC TCAV Screen Kicker                              "]
["1","03","03","15","  ","  ",null,null,null,"Muon Toroid (E-Dump)                                        "]
["1","03","04","  ","  ","  ",null,null,null,"Linac Vacuum Subsystem                                      "]
["1","03","04","02","  ","  ",null,null,null,"Linac Beamline Vacuum System                                "]
["1","03","04","03","  ","  ",null,null,null,"BC1 Vacuum System                                           "]
["1","03","04","04","  ","  ",null,null,null,"BC2 Vacuum System                                           "]
["1","03","04","05","  ","  ",null,null,null,"Linac to Undulator (LTU) Vacuum System                      "]
["1","03","04","06","  ","  ",null,null,null,"Dumpline Vacuum System                                      "]
["1","03","04","07","  ","  ",null,null,null,"Vacuum System Undulator Interface                           "]
["1","03","04","07","01","  ",null,null,null,"Entrance Section Assembly                                   "]
["1","03","04","07","02","  ",null,null,null,"Exit Section Assembly                                       "]
["1","03","04","08","  ","  ",null,null,null,"LTU/BSY& Cold Trap Vacuum System                            "]
["1","03","05","  ","  ","  ",null,null,null,"Linac Electron Diagnostics Summary                          "]
["1","03","05","01","  ","  ",null,null,null,"Wire Scanners (11) Summary                                  "]
["1","03","05","02","  ","  ",null,null,null,"Beam Position Monitors                                      "]
["1","03","05","02","01","  ",null,null,null,"BPM - Standard  Linac (4) Summary                           "]
["1","03","05","02","02","  ",null,null,null,"BPM - RF (10) Summary                                       "]
["1","03","05","02","03","  ",null,null,null,"BPM - FFTB (12) Summary                                     "]
["1","03","05","02","04","  ",null,null,null,"BPM - Large Aperture (2) Summary                            "]
["1","03","05","03","  ","  ",null,null,null,"Toroid Beam Current Monitor (10) Summary                    "]
["1","03","05","04","  ","  ",null,null,null,"Beam Stoppers (4) Summary                                   "]
["1","03","05","05","  ","  ",null,null,null,"Profile Monitors (7 OTR-3 PHOSPHOR SCREEN-1 YAG)            "]
["1","03","05","06","  ","  ",null,null,null,"E/O Bunch Length Monitors (1) Summary                       "]
["1","03","05","07","  ","  ",null,null,null,"CSR/OTR/CTR Bunch Length Monitors (5) Summary               "]
["1","03","05","08","  ","  ",null,null,null,"Beam Loss Monitors                                          "]
["1","03","05","08","01","  ",null,null,null,"PIC Beam Loss Monitors (10) Summary                         "]
["1","03","05","08","02","  ",null,null,null,"PLIC Beam Loss Monitors (2) Summary                         "]
["1","03","05","09","  ","  ",null,null,null,"Single Beam Dump (1) Summary                                "]
["1","03","05","10","  ","  ",null,null,null,"Electron Beam Dump (1) Summary                              "]
["1","03","05","11","  ","  ",null,null,null,"Protection Collimators (5) Summary                          "]
["1","03","05","12","  ","  ",null,null,null,"Movable Collimators (7x,3y) Summary                         "]
["1","03","05","13","  ","  ",null,null,null,"Safety Electron Dump (1) Summary                            "]
["1","03","05","14","  ","  ",null,null,null,"Charge Monitor (Entrance/Exit Assembly)                     "]
["1","03","06","  ","  ","  ",null,null,null,"Linac RF Subsystem                                          "]
["1","03","06","02","  ","  ",null,null,null,"S-Band High Power System                                    "]
["1","03","06","03","  ","  ",null,null,null,"S-Band Structures                                           "]
["1","03","06","04","  ","  ",null,null,null,"X-Band Low Level System                                     "]
["1","03","06","05","  ","  ",null,null,null,"X-Band High Power System                                    "]
["1","03","06","05","01","  ",null,null,null,"X-Band HP Klystron                                          "]
["1","03","06","05","02","  ",null,null,null,"X-Band HP Modulator                                         "]
["1","03","06","05","03","  ",null,null,null,"X-Band HP Waveguide System                                  "]
["1","03","06","06","  ","  ",null,null,null,"X-Band Structures                                           "]
["1","03","06","07","  ","  ",null,null,null,"RF Distribution System                                      "]
["1","03","06","07","01","  ",null,null,null,"Modulator Refurbishment                                     "]
["1","03","06","07","02","  ",null,null,null,"Solid State Sub Booster                                     "]
["1","03","06","07","03","  ",null,null,null,"IPA Modifications                                           "]
["1","03","06","07","04","  ",null,null,null,"Klystron Controls Interfaces                                "]
["1","03","06","07","05","  ",null,null,null,"Bunch Length Electronics                                    "]
["1","03","06","07","06","  ",null,null,null,"RF Phase Measurements                                       "]
["1","03","06","07","07","  ",null,null,null,"RF Distribution L2 & L3                                     "]
["1","03","06","07","08","  ",null,null,null,"RF Fiber Optics Electronics System                          "]
["1","03","06","07","09","  ",null,null,null,"RF Stability                                                "]
["1","03","07","  ","  ","  ",null,null,null,"Linac Installation & Alignment                              "]
["1","03","07","01","  ","  ",null,null,null,"Linac L01 System Installation & Alignment                   "]
["1","03","07","02","  ","  ",null,null,null,"Linac BC1 System Installation & Alignment                   "]
["1","03","07","03","  ","  ",null,null,null,"Linac L02 System Installation & Alignment                   "]
["1","03","07","04","  ","  ",null,null,null,"Linac BC2 System Installation & Alignment                   "]
["1","03","07","05","  ","  ",null,null,null,"Linac L03 System Installation & Alignment                   "]
["1","03","07","06","  ","  ",null,null,null,"Linac LTU System Installation & Alignment                   "]
["1","03","07","07","  ","  ",null,null,null,"Linac E-Dump System Installation & Alignment                "]
["1","03","07","10","  ","  ",null,null,null,"LINAC  Installation 2006 Shut Down                          "]
["1","03","07","10","01","  ",null,null,null,"Beamline Equip Removal L01 thru BC1 Out                     "]
["1","03","07","10","02","  ",null,null,null,"Gallery Waveguide Installation                              "]
["1","03","07","10","03","  ",null,null,null,"Beamline Equip Installation L01 thru BC1 Out                "]
["1","03","07","10","04","  ",null,null,null,"2006 Linac Controls Install and Checkout Gallery to Linac B "]
["1","03","07","10","05","  ",null,null,null,"2006 Linac Controls Install and Checkout L01 to BC1         "]
["1","03","07","20","  ","  ",null,null,null,"LINAC Installation 2007 Shut Down                           "]
["1","03","07","20","01","  ",null,null,null,"Beamline Equip Removal L02, L03 and BC2                     "]
["1","03","07","20","02","  ",null,null,null,"Beamline Equip Installation L02, L03 and BC2                "]
["1","03","07","20","03","  ",null,null,null,"2007 Linac Controlls Install and Checkout                   "]
["1","03","07","20","04","  ",null,null,null,"Linac Undulator Interface                                   "]
["1","04","  ","  ","  ","  ",null,null,null,"UNDULATOR SYSTEM                                            "]
["1","04","01","  ","  ","  ",null,null,null,"Undulator System Management & Integration                   "]
["1","04","01","01","  ","  ",null,null,null,"Undulator System Management                                 "]
["1","04","01","01","01","  ",null,null,null,"Undulator System Management - Technical                     "]
["1","04","01","01","02","  ",null,null,null,"ANL Project Support                                         "]
["1","04","01","02","  ","  ",null,null,null,"Undulator System Materials & Supplies                       "]
["1","04","01","02","01","  ",null,null,null,"Undulator System M&S - General                              "]
["1","04","01","02","02","  ",null,null,null,"Undulator System Travel                                     "]
["1","04","01","03","  ","  ",null,null,null,"Undulator System Reviews and Workshops                      "]
["1","04","02","  ","  ","  ",null,null,null,"Controls                                                    "]
["1","04","02","01","  ","  ",null,null,null,"Controls Management and Integration                         "]
["1","04","02","01","03","  ",null,null,null,"Software Interface with SLAC                                "]
["1","04","02","01","04","  ",null,null,null,"Undulator Cable, Tray, and Rack Layout                      "]
["1","04","02","01","05","  ",null,null,null,"Miscellaneous Controls                                      "]
["1","04","02","02","  ","  ",null,null,null,"Motion                                                      "]
["1","04","02","02","01","  ",null,null,null,"Undulator Cam Movers                                        "]
["1","04","02","02","01","01",null,null,null,"Motor Interface                                             "]
["1","04","02","02","01","02",null,null,null,"Encoder Interface                                           "]
["1","04","02","02","01","03",null,null,null,"Motor Driver                                                "]
["1","04","02","02","01","04",null,null,null,"Cabling                                                     "]
["1","04","02","02","01","05",null,null,null,"Integrate components                                        "]
["1","04","02","02","02","  ",null,null,null,"Motion Test Stand                                           "]
["1","04","02","02","06","  ",null,null,null,"Scanning Wire Motion                                        "]
["1","04","02","02","06","01",null,null,null,"Motor Interface                                             "]
["1","04","02","02","06","02",null,null,null,"Encoder Interface                                           "]
["1","04","02","02","06","03",null,null,null,"Motor Driver                                                "]
["1","04","02","02","06","04",null,null,null,"Cabling                                                     "]
["1","04","02","02","06","05",null,null,null,"Integrate components                                        "]
["1","04","02","02","07","  ",null,null,null,"Translation Stage Motion                                    "]
["1","04","02","02","07","01",null,null,null,"Motor Interface                                             "]
["1","04","02","02","07","03",null,null,null,"Motor Driver                                                "]
["1","04","02","02","07","04",null,null,null,"Cabling                                                     "]
["1","04","02","02","07","05",null,null,null,"Integrate components                                        "]
["1","04","02","03","  ","  ",null,null,null,"Signal Analysis                                             "]
["1","04","02","03","01","  ",null,null,null,"RFBPM                                                       "]
["1","04","02","03","01","02",null,null,null,"Signal Acquisition                                          "]
["1","04","02","03","01","03",null,null,null,"Timing interface                                            "]
["1","04","02","03","01","04",null,null,null,"Cabling                                                     "]
["1","04","02","03","01","05",null,null,null,"Integrate components                                        "]
["1","04","02","03","02","  ",null,null,null,"Charge Monitor                                              "]
["1","04","02","03","02","03",null,null,null,"Integrate components                                        "]
["1","04","02","03","03","  ",null,null,null,"Beam Finder Wire                                            "]
["1","04","02","03","03","01",null,null,null,"BFW Actuator Control                                        "]
["1","04","02","03","03","06",null,null,null,"Integrate components                                        "]
["1","04","02","04","  ","  ",null,null,null,"Video                                                       "]
["1","04","02","04","01","  ",null,null,null,"OTR Monitor                                                 "]
["1","04","02","04","01","01",null,null,null,"Camera                                                      "]
["1","04","02","04","01","02",null,null,null,"Camera trigger interface                                    "]
["1","04","02","04","01","03",null,null,null,"Digitizer                                                   "]
["1","04","02","04","01","04",null,null,null,"Timing interface                                            "]
["1","04","02","04","01","05",null,null,null,"Cabling                                                     "]
["1","04","02","04","01","06",null,null,null,"Integrate components                                        "]
["1","04","02","04","03","  ",null,null,null,"Observation station video                                   "]
["1","04","02","04","03","01",null,null,null,"Camera                                                      "]
["1","04","02","04","03","02",null,null,null,"Camera trigger interface                                    "]
["1","04","02","04","03","03",null,null,null,"Multiplexor                                                 "]
["1","04","02","04","03","04",null,null,null,"Cabling                                                     "]
["1","04","02","04","03","05",null,null,null,"Integrate components                                        "]
["1","04","02","04","03","06",null,null,null,"Imaging Test Stand                                          "]
["1","04","02","05","  ","  ",null,null,null,"Data Acquisition and Control                                "]
["1","04","02","05","01","  ",null,null,null,"Strongback Temperature monitoring                           "]
["1","04","02","05","01","01",null,null,null,"Integrate components                                        "]
["1","04","02","06","  ","  ",null,null,null,"Vacuum                                                      "]
["1","04","02","06","01","  ",null,null,null,"Ion Pump Controller                                         "]
["1","04","02","06","01","01",null,null,null,"Integrate components                                        "]
["1","04","02","06","02","  ",null,null,null,"RGA                                                         "]
["1","04","02","06","02","01",null,null,null," Integrate components                                       "]
["1","04","02","07","  ","  ",null,null,null,"Machine Protection                                          "]
["1","04","02","07","01","  ",null,null,null,"Undulator Beam Loss Monitor Controls                        "]
["1","04","02","07","01","01",null,null,null,"Hardware design                                             "]
["1","04","02","07","01","02",null,null,null,"Interface components                                        "]
["1","04","02","07","02","  ",null,null,null,"Cerenkov Detector                                           "]
["1","04","02","07","02","01",null,null,null,"Signal interface                                            "]
["1","04","02","07","03","  ",null,null,null,"Gamma Ray Detector                                          "]
["1","04","02","07","03","01",null,null,null,"Signal interface                                            "]
["1","04","02","08","  ","  ",null,null,null,"Power Supply Controls                                       "]
["1","04","02","08","01","  ",null,null,null,"Software                                                    ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","08","02","  ",null,null,null,"Beam Line Power Supplies (Trim Type)                        "]
["1","04","02","08","02","01",null,null,null,"CPUs and Crates                                             ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","08","02","02",null,null,null,"Bulk Power Supplies                                         "]
["1","04","02","08","02","03",null,null,null,"PLC Power Supply Protection                                 "]
["1","04","02","08","02","04",null,null,null,"MCOR                                                        "]
["1","04","02","08","03","  ",null,null,null,"Rack Assembly                                               "]
["1","04","02","08","04","  ",null,null,null,"System Checkout                                             "]
["1","04","02","10","  ","  ",null,null,null,"Undualtor Controls Module                                   "]
["1","04","02","10","01","  ",null,null,null,"UCM Hardware Design                                         ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","10","02","  ",null,null,null,"UCM EPICS Development                                       "]
["1","04","02","10","03","  ",null,null,null,"Procure UCMI Prototype                                      "]
["1","04","02","10","04","  ",null,null,null,"UCMI Proto H/W Assembly                                     "]
["1","04","02","10","05","  ",null,null,null,"UCMI Prototype Testing                                      "]
["1","04","02","10","06","  ",null,null,null,"UCMI Blade IOC First Article                                "]
["1","04","02","10","07","  ",null,null,null,"Procure UCMI First Article                                  "]
["1","04","02","10","08","  ",null,null,null,"UCM First Article Testing and QA                            "]
["1","04","02","10","09","  ",null,null,null,"Procure Production UCMI                                     "]
["1","04","02","10","10","  ",null,null,null,"Procure Production Blade IOC                                "]
["1","04","02","10","11","  ",null,null,null,"Procure Production Motors                                   "]
["1","04","02","10","12","  ",null,null,null,"Procure Production Potentiometers                           "]
["1","04","02","10","13","  ",null,null,null,"Procure Production RTD                                      "]
["1","04","02","12","  ","  ",null,null,null,"Rack and Cables                                             "]
["1","04","02","12","01","  ",null,null,null,"Undulator Racks                                             "]
["1","04","02","12","02","  ",null,null,null,"Intra-Undulator Cabling                                     "]
["1","04","02","12","03","  ",null,null,null,"Electronics Interface Assembly                              "]
["1","04","02","12","04","  ",null,null,null,"Undulator Cableplant                                        "]
["1","04","02","13","  ","  ",null,null,null,"BPM                                                         "]
["1","04","02","13","01","  ",null,null,null,"APS Testing                                                 ",{"$nulls":47},"Hamid Shoaee"]
["1","04","02","14","  ","  ",null,null,null,"Long Term Test Prep                                         "]
["1","04","02","17","  ","  ",null,null,null,"Undulator Controls Management                               "]
["1","04","02","20","  ","  ",null,null,null,"Undulator Controls - MPS                                    "]
["1","04","02","20","02","  ",null,null,null,"Undulator MPS - IMUX                                        "]
["1","04","02","20","03","  ",null,null,null,"Undulator MPS - TIU                                         "]
["1","04","02","20","04","  ",null,null,null,"Undulator MPS - PLIC                                        "]
["1","04","02","20","05","  ",null,null,null,"Undulator Controls  MPS -Toroids                            "]
["1","04","02","20","06","  ",null,null,null,"Undulator Controls MPS - Fault Devices                      "]
["1","04","02","21","  ","  ",null,null,null,"Undulator Controls - Timing                                 "]
["1","04","02","22","  ","  ",null,null,null,"Undulator Controls - BPM                                    "]
["1","04","02","23","  ","  ",null,null,null,"Undulator Controls - Vacuum                                 "]
["1","04","02","24","  ","  ",null,null,null,"Undulator Controls - ADS System                             "]
["1","04","03","  ","  ","  ",null,null,null,"Undulator Magnet & Support                                  "]
["1","04","03","01","  ","  ",null,null,null,"UND Magnet & Support - Mgmt and Integration                 "]
["1","04","03","02","  ","  ",null,null,null,"First Prototype Undulator & Mfg Plan                        "]
["1","04","03","03","  ","  ",null,null,null,"1st Article Undulators & Long Lead Procurements             "]
["1","04","03","03","01","  ",null,null,null,"Ti Strongback (LLP)                                         "]
["1","04","03","03","02","  ",null,null,null,"Magnet Blocks (LLP)                                         "]
["1","04","03","03","03","  ",null,null,null,"Magnet Poles (LLP)                                          "]
["1","04","03","03","04","  ",null,null,null,"Magnet Assembly & Supports - 1st Articles                   "]
["1","04","03","03","04","01",null,null,null,"Magnet Assembly 1st Article - Vendor A                      "]
["1","04","03","03","04","02",null,null,null,"Magnet Assembly 1st Article - Vendor B                      "]
["1","04","03","03","04","03",null,null,null,"Support/Mover System - Articles 1 & 2                       "]
["1","04","03","03","05","  ",null,null,null,"Magnetic Measurement (ANL)                                  "]
["1","04","03","03","05","01",null,null,null,"Magnetic Measurement (ANL) - Vendor A Und #1                "]
["1","04","03","03","05","02",null,null,null,"Magnetic Measurement (ANL) - Vendor B Und #2                "]
["1","04","03","03","06","  ",null,null,null,"Integrated Single-Undulator Module Test                     "]
["1","04","03","03","07","  ",null,null,null," System Test - Two Undulators                               "]
["1","04","03","04","  ","  ",null,null,null,"Production Undulator Magnet Assembly & Supports             "]
["1","04","03","04","01","  ",null,null,null,"Production Undulator Assembly - Vendor A                    "]
["1","04","03","04","02","  ",null,null,null,"Production Undulator Assembly - Vendor B                    "]
["1","04","03","04","03","  ",null,null,null,"Production Support/Mover Fabrication/Assembly               "]
["1","04","03","04","04","  ",null,null,null,"Mu Metal Shield                                             "]
["1","04","03","05","  ","  ",null,null,null,"Quadrupole Focusing Magnets                                 "]
["1","04","03","05","01","  ",null,null,null,"Quadrupole Magnets                                          "]
["1","04","03","05","02","  ",null,null,null,"Quadrupole Power Supplies                                   "]
["1","04","03","05","03","  ",null,null,null,"Quadrupole Stages & Stands                                  "]
["1","04","03","05","04","  ",null,null,null,"Quadrupole Cables                                           "]
["1","04","03","06","  ","  ",null,null,null,"Undulator Magnetic Measurement Facility (SLAC)              "]
["1","04","03","06","01","  ",null,null,null,"Undulator MMF Setup                                         "]
["1","04","03","06","01","01",null,null,null,"Undulator Test Stand Prototype                              "]
["1","04","03","06","01","04",null,null,null,"Undulator Test Stand                                        "]
["1","04","03","06","01","05",null,null,null,"Undulator Fiducialization                                   "]
["1","04","03","06","01","06",null,null,null,"Quad Strength and Field Quality                             "]
["1","04","03","06","01","07",null,null,null,"Quad Fiducialization System                                 "]
["1","04","03","06","01","08",null,null,null,"Hall Probe Calibration System                               "]
["1","04","03","06","01","09",null,null,null,"Undulator Handling                                          "]
["1","04","03","06","02","  ",null,null,null,"Fiducialization and Magnetic Measurements (F/MM)            "]
["1","04","03","06","02","01",null,null,null,"F/MM Undulator Magnet Sections                              "]
["1","04","03","06","02","02",null,null,null,"F/MM Quadrupoles                                            "]
["1","04","03","06","02","03",null,null,null,"F/MM BPMs                                                   "]
["1","04","03","06","02","04",null,null,null,"F/MM Correctors                                             "]
["1","04","03","06","02","05",null,null,null,"F/MM Vacuum Chamber                                         "]
["1","04","03","06","02","06",null,null,null,"F/MM Photon Diagnostics Components                          "]
["1","04","03","06","03","  ",null,null,null,"Undulator Monitoring                                        "]
["1","04","03","06","03","01",null,null,null,"Stretched Wire System                                       "]
["1","04","03","06","03","02",null,null,null,"Hydrostatic Level System                                    "]
["1","04","03","06","03","03",null,null,null,"F/MM BPMs                                                   "]
["1","04","03","08","  ","  ",null,null,null,"Fixed Supports                                              "]
["1","04","03","08","01","  ",null,null,null,"Fixed Sppt Mgmt & Integration                               "]
["1","04","03","08","02","  ",null,null,null,"Fixed Support Design                                        "]
["1","04","03","08","03","  ",null,null,null,"Stabilized Girder Assemblies                                "]
["1","04","03","08","04","  ",null,null,null,"Thermal Intercept System                                    "]
["1","04","03","08","05","  ",null,null,null,"Thermometry                                                 "]
["1","04","03","08","06","  ",null,null,null,"Kinematic Girder Support                                    "]
["1","04","03","08","07","  ",null,null,null,"Earthquake Bracing                                          "]
["1","04","03","08","08","  ",null,null,null,"Controls and Software                                       "]
["1","04","04","  ","  ","  ",null,null,null,"Vacuum System                                               "]
["1","04","04","02","  ","  ",null,null,null,"Undulator Vacuum Chamber Assembly                           "]
["1","04","04","02","01","  ",null,null,null,"Prototype Chamber Weldment                                  "]
["1","04","04","02","02","  ",null,null,null,"Production Chamber Weldment                                 "]
["1","04","04","02","03","  ",null,null,null,"Prototype Aluminum Chamber                                  "]
["1","04","04","03","  ","  ",null,null,null,"Beam-line Bellows Module Assembly                           "]
["1","04","04","03","01","  ",null,null,null,"Prototype Bellows Module                                    "]
["1","04","04","03","02","  ",null,null,null,"Production Bellows Module                                   "]
["1","04","04","04","  ","  ",null,null,null,"Single Undulator Test (SUT) Vacuum                          "]
["1","04","04","05","  ","  ",null,null,null,"Short Diagnostic Break (SDB) Assembly                       "]
["1","04","04","06","  ","  ",null,null,null,"Long Diagnostic Break (LDB) Assembly                        "]
["1","04","04","07","  ","  ",null,null,null,"Entrance Section Assembly                                   "]
["1","04","04","08","  ","  ",null,null,null,"Exit Section Assembly                                       "]
["1","04","04","09","  ","  ",null,null,null,"Baking System                                               "]
["1","04","05","  ","  ","  ",null,null,null,"Diagnostics                                                 "]
["1","04","05","02","  ","  ",null,null,null,"Undulator Line Diagnostics (ULD)                            "]
["1","04","05","02","01","  ",null,null,null,"ULD Test Station                                            "]
["1","04","05","02","02","  ",null,null,null,"ULD Vacuum Chamber                                          "]
["1","04","05","02","03","  ",null,null,null,"Positioning Mechanism                                       "]
["1","04","05","02","04","  ",null,null,null,"Scanning wire assembly (ULD-SWA)                            "]
["1","04","05","02","05","  ",null,null,null,"Optical transition radiation imaging assembly               "]
["1","04","05","02","09","  ",null,null,null,"ULD Design & Integration                                    "]
["1","04","05","04","  ","  ",null,null,null,"End-of-Undulator(EOU) X-ray and Profile diagnost            "]
["1","04","05","04","01","  ",null,null,null,"Prototype Construction and Testing                          "]
["1","04","05","04","02","  ",null,null,null,"Bunch Length Monitor-Streak Camera (BLM)                    "]
["1","04","05","04","03","  ",null,null,null,"Upstream corrector / separator                              "]
["1","04","05","04","04","  ",null,null,null,"Optical Diffraction radiation imaging assembly (            "]
["1","04","05","04","05","  ",null,null,null,"X-ray High Resolution monochromator assembly (EO            "]
["1","04","05","04","06","  ",null,null,null,"X-ray Imaging High Resolution detector assembly             "]
["1","04","05","04","07","  ",null,null,null,"EOU Design and Integration                                  "]
["1","04","05","05","  ","  ",null,null,null,"RFBPM                                                       "]
["1","04","05","05","01","  ",null,null,null,"X-Band Cavity BPM Development                               "]
["1","04","05","05","02","  ",null,null,null,"X-Band Receiver Development                                 "]
["1","04","05","05","03","  ",null,null,null,"X-Band BPM Production                                       "]
["1","04","05","06","  ","  ",null,null,null,"Beam Finder Wire                                            "]
["1","04","05","07","  ","  ",null,null,null,"Charge Monitor (CM)                                         "]
["1","04","05","08","  ","  ",null,null,null,"Beam Loss Monitoring                                        "]
["1","04","05","09","  ","  ",null,null,null,"Radiation Detection Monitor (RDM)                           "]
["1","04","05","10","  ","  ",null,null,null,"SIngle Undulator Test (SUT) Diagnostics                     "]
["1","04","05","11","  ","  ",null,null,null,"Supplemental Shielding                                      "]
["1","04","06","  ","  ","  ",null,null,null,"Undulator System Installation and Alignment                 "]
["1","04","06","01","  ","  ",null,null,null,"Undulator System Installation and Alignment Inte            "]
["1","04","06","01","01","  ",null,null,null,"Undulator System                                            "]
["1","04","06","02","  ","  ",null,null,null,"Control System Installation and Alignment                   "]
["1","04","06","04","  ","  ",null,null,null,"Vacuum System Installation and Alignment                    "]
["1","04","06","05","  ","  ",null,null,null,"Diagnostics System Installation and Alignment               "]
["1","05","  ","  ","  ","  ",null,null,null,"X-RAY TRANSPORT & DIAGNOSTICS SYSTEMS                       "]
["1","05","01","  ","  ","  ",null,null,null,"System Management & Integration                             "]
["1","05","01","01","  ","  ",null,null,null,"Management                                                  "]
["1","05","01","01","01","  ",null,null,null,"XTOD Management - Technical                                 "]
["1","05","01","01","02","  ",null,null,null,"LLNL Project Support                                        "]
["1","05","01","01","03","  ",null,null,null,"Commissioning Coordinator                                   "]
["1","05","02","  ","  ","  ",null,null,null,"Controls                                                    "]
["1","05","02","01","  ","  ",null,null,null,"Controls - EPICS                                            "]
["1","05","02","02","  ","  ",null,null,null,"Motor Controls                                              "]
["1","05","02","03","  ","  ",null,null,null,"Controls - Vacuum                                           "]
["1","05","03","  ","  ","  ",null,null,null,"Mechanical & Vacuum Subsystem                               "]
["1","05","03","01","  ","  ",null,null,null,"Vacuum Systems Engineering                                  "]
["1","05","03","02","  ","  ",null,null,null,"Mech/Vac Front End                                          "]
["1","05","03","03","  ","  ",null,null,null,"Mech/Vac Near Hall                                          "]
["1","05","03","03","01","  ",null,null,null,"Mech/Vac Near Hall                                          "]
["1","05","03","03","02","  ",null,null,null,"NEH Hutch 2                                                 "]
["1","05","03","03","03","  ",null,null,null,"NEH Hutch 3                                                 "]
["1","05","03","04","  ","  ",null,null,null,"Mech/Vac Tunnel                                             "]
["1","05","03","05","  ","  ",null,null,null,"Mech/Vac Far Hall                                           "]
["1","05","03","05","01","  ",null,null,null,"FEH Hutch 1                                                 "]
["1","05","03","05","02","  ",null,null,null,"FEH Hutch 2                                                 "]
["1","05","03","05","03","  ",null,null,null,"FEH Hutch 3                                                 "]
["1","05","04","  ","  ","  ",null,null,null,"Optical  Subsystem                                          "]
["1","05","04","01","  ","  ",null,null,null,"Optical Systems Engineering                                 "]
["1","05","04","02","  ","  ",null,null,null,"Facility Optics                                             "]
["1","05","04","02","01","  ",null,null,null,"Fast Valve                                                  "]
["1","05","04","02","02","  ",null,null,null,"Fixed Mask                                                  "]
["1","05","04","02","03","  ",null,null,null,"Slit/Collimators                                            "]
["1","05","04","02","04","  ",null,null,null,"Flipper Mirror                                              "]
["1","05","04","02","05","  ",null,null,null,"Gas/Solid Attenuator                                        "]
["1","05","04","02","06","  ",null,null,null,"TTF Damage Experiment                                       "]
["1","05","04","02","07","  ",null,null,null,"FEL Offset Mirrors                                          "]
["1","05","04","02","07","01",null,null,null,"Low Energy Mirrors                                          "]
["1","05","04","02","07","02",null,null,null,"High Energy Mirrors                                         "]
["1","05","04","02","08","  ",null,null,null,"Solid Attenuator                                            "]
["1","05","04","02","09","  ",null,null,null,"Low Energy Mirror System                                    "]
["1","05","04","03","  ","  ",null,null,null,"End Station Optics                                          "]
["1","05","04","03","01","  ",null,null,null,"End Station Optics Engineering                              "]
["1","05","04","03","02","  ",null,null,null,"Optics Tank - Near Hall                                     "]
["1","05","04","03","03","  ",null,null,null,"Optics Tank - Far Hall                                      "]
["1","05","04","03","04","  ",null,null,null,"K-B Focusing System                                         "]
["1","05","04","03","05","  ",null,null,null,"Refractive Focusing System                                  "]
["1","05","04","04","  ","  ",null,null,null,"Crystals & Gratings                                         "]
["1","05","04","04","01","  ",null,null,null,"Crystals & Gratings Engineering                             "]
["1","05","04","04","02","  ",null,null,null,"System Monochrometer                                        "]
["1","05","04","04","03","  ",null,null,null,"Pulse Split & Delay                                         "]
["1","05","05","  ","  ","  ",null,null,null,"Diagnostics Subsystem                                       "]
["1","05","05","01","  ","  ",null,null,null,"Diagnostic Systems Engineering                              "]
["1","05","05","01","01","  ",null,null,null,"Diagnostic Systems Engineering                              "]
["1","05","05","02","  ","  ",null,null,null,"Modeling & Simulation                                       "]
["1","05","05","02","01","  ",null,null,null,"Wave Model                                                  "]
["1","05","05","02","02","  ",null,null,null,"Monte Carlo Model                                           "]
["1","05","05","02","03","  ",null,null,null,"Beam Simulation                                             "]
["1","05","05","03","  ","  ",null,null,null,"Facility Diagnostics                                        "]
["1","05","05","03","01","  ",null,null,null,"Direct Imager                                               "]
["1","05","05","03","02","  ",null,null,null,"Indirect Imager                                             "]
["1","05","05","03","03","  ",null,null,null,"Pulsed Ion Chamber                                          "]
["1","05","05","03","04","  ",null,null,null,"Gas Mixing System                                           "]
["1","05","05","03","05","  ",null,null,null,"FEE Diagnostic Tank                                         "]
["1","05","05","03","06","  ",null,null,null,"Gas Detector                                                "]
["1","05","05","03","07","  ",null,null,null,"NEH Imager                                                  "]
["1","05","05","03","08","  ",null,null,null,"FEH Imager                                                  "]
["1","05","05","04","  ","  ",null,null,null,"Commissioning Diagnostics                                   "]
["1","05","05","04","01","  ",null,null,null,"Commission Diagnostic Tanks                                 "]
["1","05","05","04","02","  ",null,null,null,"Total Energy Measurement                                    "]
["1","05","05","04","03","  ",null,null,null,"Pulse Length Measurement                                    "]
["1","05","05","04","04","  ",null,null,null,"Low Energy Spectral Measurement System                      "]
["1","05","05","04","05","  ",null,null,null,"Popup Cameras                                               "]
["1","05","05","04","06","  ",null,null,null,"K Measurement System                                        "]
["1","05","05","04","07","  ",null,null,null,"Divergence Measurement                                      "]
["1","05","06","  ","  ","  ",null,null,null,"X-Ray Transport System Installation & Alignment             "]
["1","05","06","01","  ","  ",null,null,null,"Front End Enclosure Install                                 "]
["1","05","06","02","  ","  ",null,null,null,"Near Hall Install                                           "]
["1","05","06","03","  ","  ",null,null,null,"Tunnel Install                                              "]
["1","05","06","04","  ","  ",null,null,null,"Far Hall Install                                            "]
["1","05","06","05","  ","  ",null,null,null,"Electron Dump Enclosure Install                             "]
["1","06","  ","  ","  ","  ",null,null,null,"X-RAY END STATION SYSTEMS                                   "]
["1","06","01","  ","  ","  ",null,null,null,"System Management & Integration                             "]
["1","06","01","01","  ","  ",null,null,null,"Management                                                  "]
["1","06","01","02","  ","  ",null,null,null,"SSRL Physics                                                "]
["1","06","02","  ","  ","  ",null,null,null,"XES Controls                                                "]
["1","06","02","01","  ","  ",null,null,null,"Controls Management                                         "]
["1","06","02","02","  ","  ",null,null,null,"Network - Closed (Moved to new WBS Element)                 "]
["1","06","02","03","  ","  ",null,null,null,"PC Support - Closed (Moved to New WBS Element)              "]
["1","06","02","04","  ","  ",null,null,null,"Beamline Controls - AP - Closed  (Moved to new WBS Element) "]
["1","06","02","05","  ","  ",null,null,null,"X-Ray PPS - Closed (Moved to new WBS Element)               "]
["1","06","02","05","01","  ",null,null,null,"FEE X-Ray PPS - Closed (Moved to new WBS Element)           "]
["1","06","02","05","02","  ",null,null,null,"Near Hall X-Ray PPS - Closed to BCWP                        "]
["1","06","02","05","03","  ",null,null,null,"Tunnel X-Ray PPS - Closed to BCWP                           "]
["1","06","02","05","04","  ",null,null,null,"Far Hall X-Ray PPS - Closed to BCWP                         "]
["1","06","02","06","  ","  ",null,null,null,"X-Ray MPS - Closed (Moved to new WBS Element)               "]
["1","06","02","06","01","  ",null,null,null,"FEE X-Ray MPS - Closed to BCWP                              "]
["1","06","02","07","  ","  ",null,null,null,"AMOS Experiment Controls X1                                 "]
["1","06","02","07","01","  ",null,null,null,"AMOS Experiment Controls X1                                 "]
["1","06","02","07","02","  ",null,null,null,"X-Ray Flourescence Detector                                 "]
["1","06","02","07","03","  ",null,null,null,"Ion Imaging & Electron TOF                                  "]
["1","06","02","07","04","  ",null,null,null,"Sample Source                                               "]
["1","06","02","07","05","  ",null,null,null,"Vacuum Controls & Mechanical Exp 1                          "]
["1","06","02","07","06","  ",null,null,null,"Refocus Optics                                              "]
["1","06","02","07","07","  ",null,null,null,"Diagnostics                                                 "]
["1","06","02","08","  ","  ",null,null,null,"AMOS Experiment Controls X2                                 "]
["1","06","02","08","01","  ",null,null,null,"AMOS Experiment Controls X2                                 "]
["1","06","02","08","02","  ",null,null,null,"X2 Praticle Imaging                                         "]
["1","06","02","09","  ","  ",null,null,null,"Controls Management - Closed (Moved to new WBS Element)     "]
["1","06","02","10","  ","  ",null,null,null,"Global Controls System                                      "]
["1","06","02","10","01","  ",null,null,null,"Network                                                     "]
["1","06","02","10","02","  ",null,null,null,"Machine Protection System                                   "]
["1","06","02","10","03","  ",null,null,null,"Personnel Protection System                                 "]
["1","06","02","10","04","  ",null,null,null,"Laser PPS                                                   "]
["1","06","02","10","05","  ",null,null,null,"User Safeguards                                             "]
["1","06","02","10","06","  ",null,null,null,"Timing System                                               "]
["1","06","02","10","07","  ",null,null,null,"Data Management                                             "]
["1","06","02","10","08","  ",null,null,null,"Global Cabling & Racks                                      "]
["1","06","02","10","09","  ",null,null,null,"Laser Timing                                                "]
["1","06","02","10","10","  ",null,null,null,"Experimental High Level Applications                        "]
["1","06","02","11","  ","  ",null,null,null,"Laser Controls                                              "]
["1","06","02","12","  ","  ",null,null,null,"K-Measuerment/Vacuum Subsystem                              "]
["1","06","03","  ","  ","  ",null,null,null,"Mechanical/Vacuum Subsystem                                 "]
["1","06","03","01","  ","  ",null,null,null,"Chamber Support Tables - Mech/Vac                           "]
["1","06","03","02","  ","  ",null,null,null,"Vacuum Components - Mech/Vac                                "]
["1","06","03","02","01","  ",null,null,null,"Valves - Vacuum                                             "]
["1","06","03","02","02","  ",null,null,null,"Hardware - Vacuum                                           "]
["1","06","03","02","03","  ",null,null,null,"Ion Pump - Vacuum                                           "]
["1","06","03","02","04","  ",null,null,null,"Turbo Pump - Vacuum                                         "]
["1","06","03","02","05","  ",null,null,null,"Gauges - Vacuum                                             "]
["1","06","03","03","  ","  ",null,null,null,"Experimental Chambers                                       "]
["1","06","03","03","01","  ",null,null,null,"AP Chamber 1                                                "]
["1","06","03","03","02","  ",null,null,null,"AP Chamber 2                                                "]
["1","06","04","  ","  ","  ",null,null,null,"Laser Subsystem                                             "]
["1","06","04","01","  ","  ",null,null,null,"XES Laser                                                   "]
["1","06","04","02","  ","  ",null,null,null,"Laser Diagnostics                                           "]
["1","06","04","03","  ","  ",null,null,null,"Laser Optical Transport                                     "]
["1","06","04","04","  ","  ",null,null,null,"Laser Safety                                                "]
["1","06","05","  ","  ","  ",null,null,null,"X-Ray Detectors                                             "]
["1","06","05","01","  ","  ",null,null,null,"Beam Imaging                                                "]
["1","06","05","02","  ","  ",null,null,null,"Not Used                                                    "]
["1","06","05","03","  ","  ",null,null,null,"Beam Intensity                                              "]
["1","06","05","04","  ","  ",null,null,null,"Detector & Streak Camera                                    "]
["1","06","05","04","01","  ",null,null,null,"Detector Management                                         "]
["1","06","05","04","02","  ",null,null,null,"Streak Camera - LBL                                         "]
["1","06","06","  ","  ","  ",null,null,null,"System Installation & Alignment                             "]
["1","06","06","01","  ","  ",null,null,null,"Front End Install                                           "]
["1","06","06","02","  ","  ",null,null,null,"Near Hall Install                                           "]
["1","06","06","02","01","  ",null,null,null,"Near Hall Install Global Controls                           "]
["1","06","06","02","02","  ",null,null,null,"Near Hall Install Mech/Vac                                  "]
["1","06","06","02","03","  ",null,null,null,"Near Hall Install Laser                                     "]
["1","06","06","02","04","  ",null,null,null,"Near Hall Install Detectors                                 "]
["1","06","06","02","05","  ",null,null,null,"Near Hall Install Atomic Physics                            "]
["1","06","06","02","06","  ",null,null,null,"Near Hall Install PPS System                                "]
["1","06","06","02","07","  ",null,null,null,"Near Hall Install Laser PPS                                 "]
["1","06","06","03","  ","  ",null,null,null,"Tunnel Install                                              "]
["1","06","06","04","  ","  ",null,null,null,"Far Hall Install                                            "]
["1","06","06","04","01","  ",null,null,null,"Far Hall Install Global Controls                            "]
["1","06","06","04","02","  ",null,null,null,"Far Hall Install Mech/Vac                                   "]
["1","06","06","04","04","  ",null,null,null,"Far Hall Install Detectors                                  "]
["1","06","06","04","05","  ",null,null,null,"Far Hall Install PPS System                                 "]
["1","06","06","05","  ","  ",null,null,null,"Electron Dump Enclosure Install                             "]
["1","06","07","  ","  ","  ",null,null,null,"AMOS Experiment                                             "]
["1","06","07","01","  ","  ",null,null,null,"AP Management & Design                                      "]
["1","06","07","01","01","  ",null,null,null,"Management                                                  "]
["1","06","07","01","02","  ",null,null,null,"Conceptual Design                                           "]
["1","06","07","01","03","  ",null,null,null,"Preliminary Design                                          "]
["1","06","07","01","04","  ",null,null,null,"Final Design                                                "]
["1","06","07","02","  ","  ",null,null,null,"AP X1 High Field Physics Exp.                               "]
["1","06","07","02","01","  ",null,null,null,"X-Ray Fluorescence Detectors                                "]
["1","06","07","02","02","  ",null,null,null,"Ion Imaging & Electron TOF Detectors                        "]
["1","06","07","02","03","  ",null,null,null,"Sample Source                                               "]
["1","06","07","02","04","  ",null,null,null,"Vacuum System                                               "]
["1","06","07","02","05","  ",null,null,null,"Other X1 Items                                              "]
["1","06","07","03","  ","  ",null,null,null,"AP Refocus Optics                                           "]
["1","06","07","04","  ","  ",null,null,null,"AP Diagnostics                                              "]
["1","06","07","05","  ","  ",null,null,null,"AP Particle Imaging Experiment                              "]
["1","06","08","  ","  ","  ",null,null,null,"Crystals and Gratings                                       "]
["1","06","08","01","  ","  ",null,null,null,"K Measurement Spectrometer                                  "]
["1","06","09","  ","  ","  ",null,null,null,"Mechanical Systems                                          "]
["1","06","09","01","  ","  ",null,null,null,"PPS Stoppers                                                "]
["1","06","09","02","  ","  ",null,null,null,"PPS Shielding                                               "]
["1","06","09","03","  ","  ",null,null,null,"NEH Hutch Doors                                             "]
["1","09","  ","  ","  ","  ",null,null,null,"CONVENTIONAL FACILITIES                                     "]
["1","09","01","  ","  ","  ",null,null,null,"System Management & Integration                             "]
["1","09","01","01","  ","  ",null,null,null,"Management                                                  "]
["1","09","01","02","  ","  ",null,null,null,"CF Engineering                                              "]
["1","09","01","03","  ","  ",null,null,null,"Construction Management & AE Support                        "]
["1","09","01","04","  ","  ",null,null,null,"Mechanical Design (MD)                                      "]
["1","09","01","04","01","  ",null,null,null,"Mechanical Design Title 1 - RSY through CLOC                "]
["1","09","01","04","02","  ",null,null,null,"Mechanical Design T1 Linac Facilities                       "]
["1","09","01","04","03","  ",null,null,null,"Mechanical Design Title 2 - RSY through CLOC                "]
["1","09","01","04","04","  ",null,null,null,"Mechanical Design T2 Linac Facilities                       "]
["1","09","01","04","05","  ",null,null,null,"Mechanical Design Title 3 Linac Facility                    "]
["1","09","01","04","06","  ",null,null,null,"Mechanical Design Title 3 - RSY through CLOC                "]
["1","09","01","05","  ","  ",null,null,null,"Conventional Experiment Facility (CEF)                      "]
["1","09","01","05","01","  ",null,null,null,"CEF Engineering Title 1 - RSY through CLOC                  "]
["1","09","01","05","02","  ",null,null,null,"CEF Engineering Title 1 Linac Facility                      "]
["1","09","01","05","03","  ",null,null,null,"CEF Engineering Title 2 - RSY through CLOC                  "]
["1","09","01","05","04","  ",null,null,null,"CEF Design Linac Facility Title 2                           "]
["1","09","02","  ","  ","  ",null,null,null,"Title 1 & Title 2 Conventional Facilities                   "]
["1","09","02","02","  ","  ",null,null,null,"A & E Services  - RSY throguh CLOC                          "]
["1","09","02","02","01","  ",null,null,null,"Title 1 Design                                              "]
["1","09","02","02","02","  ",null,null,null,"Title 2 Design                                              "]
["1","09","02","03","  ","  ",null,null,null,"A & E Services - (S20, MMF,MCC)                             "]
["1","09","02","03","01","  ",null,null,null,"Title 1 Design (Sector 20)                                  "]
["1","09","02","03","02","  ",null,null,null,"Title 2 Design (Sector 20)                                  "]
["1","09","02","03","03","  ",null,null,null,"Title 1 Design (MMF)                                        "]
["1","09","02","03","04","  ",null,null,null,"Title 2 Design (MMF)                                        "]
["1","09","02","03","05","  ",null,null,null,"Title 1 Design (MCC)                                        "]
["1","09","02","03","06","  ",null,null,null,"Title 2 Design (MCC)                                        "]
["1","09","03","  ","  ","  ",null,null,null,"Construction-T3 Conventional Facilities                     "]
["1","09","03","01","  ","  ",null,null,null,"Sector 20 Injector Facilities                               "]
["1","09","03","01","01","  ",null,null,null,"S20 - Site Preparation/General Requirements                 "]
["1","09","03","01","02","  ",null,null,null,"S20 - Site Construction                                     "]
["1","09","03","01","03","  ",null,null,null,"S20 - Concrete                                              "]
["1","09","03","01","04","  ",null,null,null,"S20 - Masonry                                               "]
["1","09","03","01","05","  ",null,null,null,"S20 - Metals                                                "]
["1","09","03","01","06","  ",null,null,null,"S20 - Woods & Plastics                                      "]
["1","09","03","01","07","  ",null,null,null,"S20 - Thermal & Moisture Protection                         "]
["1","09","03","01","08","  ",null,null,null,"S20 - Doors & Windows                                       "]
["1","09","03","01","09","  ",null,null,null,"S20 - Finishes                                              "]
["1","09","03","01","10","  ",null,null,null,"S20 - Specialties                                           "]
["1","09","03","01","14","  ",null,null,null,"S20 - Conveying Systems                                     "]
["1","09","03","01","15","  ",null,null,null,"S20 - Mechanical                                            "]
["1","09","03","01","16","  ",null,null,null,"S20 - Electrical                                            "]
["1","09","03","01","20","  ",null,null,null,"S20 - Project Close Out                                     "]
["1","09","03","02","  ","  ",null,null,null,"Magnetic Measurement Facility                               "]
["1","09","03","02","01","  ",null,null,null,"MMF - Site Preparation/General Requirements                 "]
["1","09","03","02","02","  ",null,null,null,"MMF - Site Construction                                     "]
["1","09","03","02","03","  ",null,null,null,"MMF - Concrete                                              "]
["1","09","03","02","04","  ",null,null,null,"Utilities                                                   "]
["1","09","03","02","05","  ",null,null,null,"MMF - Metals                                                "]
["1","09","03","02","06","  ",null,null,null,"MMF - Woods & Plastics                                      "]
["1","09","03","02","07","  ",null,null,null,"MMF - Thermal & Moisture Protection                         "]
["1","09","03","02","08","  ",null,null,null,"MMF - Doors & Windows                                       "]
["1","09","03","02","09","  ",null,null,null,"MMF - Finishes                                              "]
["1","09","03","02","10","  ",null,null,null,"MMF - Specialities                                          "]
["1","09","03","02","13","  ",null,null,null,"                                                            "]
["1","09","03","02","14","  ",null,null,null,"MMF - Conveying Systems                                     "]
["1","09","03","02","15","  ",null,null,null,"MMF - Mechanical                                            "]
["1","09","03","02","16","  ",null,null,null,"MMF - Electrical                                            "]
["1","09","03","02","20","  ",null,null,null,"MMF - Project Close Out                                     "]
["1","09","03","03","  ","  ",null,null,null,"BTH West                                                    "]
["1","09","03","03","01","  ",null,null,null,"BTH West - Site Preparation                                 "]
["1","09","03","03","15","  ",null,null,null,"BTH West - Mechanical                                       "]
["1","09","03","03","16","  ",null,null,null,"BTH West - Electrical                                       "]
["1","09","03","03","20","  ",null,null,null,"BTH West - Project Close Out                                "]
["1","09","03","04","  ","  ",null,null,null,"Linac Facility Upgrade (LN)                                 "]
["1","09","03","04","01","  ",null,null,null,"LN - Site Preparation                                       "]
["1","09","03","04","02","  ",null,null,null,"LN - Sitework                                               "]
["1","09","03","04","03","  ",null,null,null,"Electrical                                                  "]
["1","09","03","04","04","  ",null,null,null,"Utilities                                                   "]
["1","09","03","04","05","  ",null,null,null,"Linac - Metals                                              "]
["1","09","03","04","06","  ",null,null,null,"Special System - Fire Protection                            "]
["1","09","03","04","10","  ",null,null,null,"Project Close Out Linac Facility                            "]
["1","09","03","04","15","  ",null,null,null,"LN - Mechanical                                             "]
["1","09","03","04","16","  ",null,null,null,"LN - Electrical                                             "]
["1","09","03","04","20","  ",null,null,null,"LN - Project Close Out                                      "]
["1","09","03","05","  ","  ",null,null,null,"Research Yard Modifications                                 "]
["1","09","03","05","01","  ",null,null,null,"RY - Site Preparation                                       "]
["1","09","03","05","01","01",null,null,null,"General Requirements- CEF                                   "]
["1","09","03","05","01","02",null,null,null,"General Requirements - G/C                                  "]
["1","09","03","05","02","  ",null,null,null,"RY - FFTB/BSY & Site Construction                           "]
["1","09","03","05","02","01",null,null,null,"Site Construction - CEF                                     "]
["1","09","03","05","02","02",null,null,null,"Site Construction - G/C                                     "]
["1","09","03","05","03","  ",null,null,null,"Electrical                                                  "]
["1","09","03","05","03","01",null,null,null,"Electrical CEF                                              "]
["1","09","03","05","03","02",null,null,null,"Electrical G/C                                              "]
["1","09","03","05","04","  ",null,null,null,"Utilities                                                   "]
["1","09","03","05","04","01",null,null,null,"Utilities CEF                                               "]
["1","09","03","05","04","02",null,null,null,"Utilities G/C                                               "]
["1","09","03","05","05","  ",null,null,null,"RY - Metals                                                 "]
["1","09","03","05","05","01",null,null,null,"HVAC CEF                                                    "]
["1","09","03","05","05","02",null,null,null,"HVAC G/C                                                    "]
["1","09","03","05","06","  ",null,null,null,"Special System - Fire Protection                            "]
["1","09","03","05","06","01",null,null,null,"Special System - Fire Protection CEF                        "]
["1","09","03","05","06","02",null,null,null,"Special System - Fire Protection                            "]
["1","09","03","05","07","  ",null,null,null,"Interior                                                    "]
["1","09","03","05","07","01",null,null,null,"Interior CEF                                                "]
["1","09","03","05","07","02",null,null,null,"Interior G/C                                                "]
["1","09","03","05","10","  ",null,null,null,"Project Close Out Reasearch Yard                            "]
["1","09","03","05","20","  ",null,null,null,"RY - Project Close Out                                      "]
["1","09","03","06","  ","  ",null,null,null,"Pre-Purchase Equipment                                      "]
["1","09","03","06","01","  ",null,null,null,"PPE - General Requirements                                  "]
["1","09","03","06","02","  ",null,null,null,"AR - Site Construction                                      "]
["1","09","03","06","03","  ",null,null,null,"AR - Concrete                                               "]
["1","09","03","06","04","  ",null,null,null,"Utilities                                                   "]
["1","09","03","06","05","  ",null,null,null,"HVAC                                                        "]
["1","09","03","06","06","  ",null,null,null,"Special System- Fire Protection                             "]
["1","09","03","06","07","  ",null,null,null,"Interior                                                    "]
["1","09","03","06","10","  ",null,null,null,"Project Close Out  Beam Trans Hall                          "]
["1","09","03","06","11","  ",null,null,null,"Pre-Purchase Equipment for Beam Path                        "]
["1","09","03","06","20","  ",null,null,null,"AR - Project Close Out                                      "]
["1","09","03","07","  ","  ",null,null,null,"SITEWORK                                                    "]
["1","09","03","07","01","  ",null,null,null,"SW - Site Preparation/General Requirements                  "]
["1","09","03","07","02","  ",null,null,null,"SW - Site Construction                                      "]
["1","09","03","07","03","  ",null,null,null,"SW - Concrete                                               "]
["1","09","03","07","04","  ",null,null,null,"Utilities                                                   "]
["1","09","03","07","05","  ",null,null,null,"HVAC                                                        "]
["1","09","03","07","06","  ",null,null,null,"Special System - Fire Protection                            "]
["1","09","03","07","07","  ",null,null,null,"Interior                                                    "]
["1","09","03","07","09","  ",null,null,null,"Tunneling                                                   "]
["1","09","03","07","10","  ",null,null,null,"Project Close Out Undulator Hall                            "]
["1","09","03","07","15","  ",null,null,null,"SW - Mechanical                                             "]
["1","09","03","07","16","  ",null,null,null,"SW - Electrical                                             "]
["1","09","03","07","17","  ",null,null,null,"SW - Others (include Div 4, and 6 through 14)               "]
["1","09","03","07","20","  ",null,null,null,"SW - Project Close Out                                      "]
["1","09","03","08","  ","  ",null,null,null,"Beam Transport Hall (BTH)                                   "]
["1","09","03","08","01","  ",null,null,null,"BTH - Site Preparation/General Requirements                 "]
["1","09","03","08","02","  ",null,null,null,"BTH - Site Construction                                     "]
["1","09","03","08","03","  ",null,null,null,"BTH - Concrete                                              "]
["1","09","03","08","04","  ",null,null,null,"Utilities                                                   "]
["1","09","03","08","05","  ",null,null,null,"BTH - Metals                                                "]
["1","09","03","08","06","  ",null,null,null,"Special System - Fire Protection                            "]
["1","09","03","08","07","  ",null,null,null,"Interior                                                    "]
["1","09","03","08","09","  ",null,null,null,"Tunneling                                                   "]
["1","09","03","08","10","  ",null,null,null,"Project Close Out Front End Enclosure                       "]
["1","09","03","08","15","  ",null,null,null,"BTH - Mechanical                                            "]
["1","09","03","08","16","  ",null,null,null,"BTH - Electrical                                            "]
["1","09","03","08","17","  ",null,null,null,"BTH - Others (include Div 4, and 6 through 14)              "]
["1","09","03","08","20","  ",null,null,null,"BTH - Project Close Out                                     "]
["1","09","03","09","  ","  ",null,null,null,"Front End Enclosure (FEE)                                   "]
["1","09","03","09","01","  ",null,null,null,"FEE - Site Preparation/General Requirements                 "]
["1","09","03","09","02","  ",null,null,null,"FEE - Site Construction                                     "]
["1","09","03","09","03","  ",null,null,null,"FEE - Concrete                                              "]
["1","09","03","09","04","  ",null,null,null,"Utilities                                                   "]
["1","09","03","09","05","  ",null,null,null,"FEE - Metals                                                "]
["1","09","03","09","06","  ",null,null,null,"Special System (Fire Protection) Beam Dump                  "]
["1","09","03","09","09","  ",null,null,null,"Tunneling                                                   "]
["1","09","03","09","10","  ",null,null,null,"Project Close Out Beam Dump                                 "]
["1","09","03","09","15","  ",null,null,null,"FEE - Mechanical                                            "]
["1","09","03","09","16","  ",null,null,null,"FEE - Electrical                                            "]
["1","09","03","09","17","  ",null,null,null,"FEE - Others (include Div 4, and 6 through 14)              "]
["1","09","03","09","20","  ",null,null,null,"FEE - Project Close Out                                     "]
["1","09","03","10","  ","  ",null,null,null,"Electron Beam Dump (EBD)                                    "]
["1","09","03","10","01","  ",null,null,null,"EBD - Site Preparation/General Requirements                 "]
["1","09","03","10","02","  ",null,null,null,"EBD - Site Construction                                     "]
["1","09","03","10","03","  ",null,null,null,"EBD - Concrete                                              "]
["1","09","03","10","04","  ",null,null,null,"Utilities                                                   "]
["1","09","03","10","05","  ",null,null,null,"EBD - Metals                                                "]
["1","09","03","10","06","  ",null,null,null,"Special System - Fire Protection                            "]
["1","09","03","10","07","  ",null,null,null,"Interior                                                    "]
["1","09","03","10","10","  ",null,null,null,"Project Close Out Near Experimental Hall                    "]
["1","09","03","10","15","  ",null,null,null,"EBD - Mechanical                                            "]
["1","09","03","10","16","  ",null,null,null,"EBD - Electrical                                            "]
["1","09","03","10","17","  ",null,null,null,"EBD - Others (include Div 4, and 6 through 14)              "]
["1","09","03","10","20","  ",null,null,null,"EBD - Project Close Out                                     "]
["1","09","03","11","  ","  ",null,null,null,"Near Experimental Hall (NEH)                                "]
["1","09","03","11","01","  ",null,null,null,"NEH - Site Preparation/General Requirements                 "]
["1","09","03","11","02","  ",null,null,null,"NEH - Site Construction                                     "]
["1","09","03","11","03","  ",null,null,null,"NEH - Concrete                                              "]
["1","09","03","11","04","  ",null,null,null,"Utilities                                                   "]
["1","09","03","11","05","  ",null,null,null,"NEH - Metals                                                "]
["1","09","03","11","06","  ",null,null,null,"Special System - Fire Protection                            "]
["1","09","03","11","07","  ",null,null,null,"Interiors                                                   "]
["1","09","03","11","09","  ",null,null,null,"Tunneling                                                   "]
["1","09","03","11","10","  ",null,null,null,"Project Close Out X-Ray Transport & Diagonistic             "]
["1","09","03","11","15","  ",null,null,null,"NEH - Mechanical                                            "]
["1","09","03","11","16","  ",null,null,null,"NEH - Electrical                                            "]
["1","09","03","11","17","  ",null,null,null,"NEH - Others (include Div 4, and 6 through 14)              "]
["1","09","03","11","20","  ",null,null,null,"NEH - Project Close Out                                     "]
["1","09","03","12","  ","  ",null,null,null,"Undulator Hall (UH)                                         "]
["1","09","03","12","01","  ",null,null,null,"UH - Site Preparation/General Requirements                  "]
["1","09","03","12","02","  ",null,null,null,"UH - Site Construction                                      "]
["1","09","03","12","03","  ",null,null,null,"UH - Concrete                                               "]
["1","09","03","12","04","  ",null,null,null,"Utilities                                                   "]
["1","09","03","12","05","  ",null,null,null,"UH - Metals                                                 "]
["1","09","03","12","06","  ",null,null,null,"Special System - Fire Protection                            "]
["1","09","03","12","07","  ",null,null,null,"Interiors                                                   "]
["1","09","03","12","09","  ",null,null,null,"Tunneling                                                   "]
["1","09","03","12","10","  ",null,null,null,"Project Close Out Far Experimental Hall                     "]
["1","09","03","12","15","  ",null,null,null,"UH - Mechanical                                             "]
["1","09","03","12","16","  ",null,null,null,"UH - Electrical                                             "]
["1","09","03","12","17","  ",null,null,null,"UH - Others (include Div 4, and 6 through 14)               "]
["1","09","03","12","19","  ",null,null,null,"UH - Tunnel Construction                                    "]
["1","09","03","12","20","  ",null,null,null,"UH - Project Close Out                                      "]
["1","09","03","13","  ","  ",null,null,null,"X-Ray - Transport & Diagnostic Hall (XRTD)                  "]
["1","09","03","13","01","  ",null,null,null,"XRTD - Site Preparation/General Requirements                "]
["1","09","03","13","02","  ",null,null,null,"XRTD - Site Construction                                    "]
["1","09","03","13","03","  ",null,null,null,"XRTD - Concrete                                             "]
["1","09","03","13","04","  ",null,null,null,"Utilities                                                   "]
["1","09","03","13","05","  ",null,null,null,"HVAC                                                        "]
["1","09","03","13","06","  ",null,null,null,"Special System - Fire Protection                            "]
["1","09","03","13","07","  ",null,null,null,"Interior                                                    "]
["1","09","03","13","10","  ",null,null,null,"Project Close Out Central Laboratory Office Complex (CLOC)  "]
["1","09","03","13","15","  ",null,null,null,"XRTD - Mechanical                                           "]
["1","09","03","13","16","  ",null,null,null,"XRTD - Electrical                                           "]
["1","09","03","13","17","  ",null,null,null,"XRTD - Others (include Div 4, and 6 through 14)             "]
["1","09","03","13","19","  ",null,null,null,"XRTD - Tunnel Construction                                  "]
["1","09","03","13","20","  ",null,null,null,"XRTD - Project Close Out                                    "]
["1","09","03","14","  ","  ",null,null,null,"Far Experimental Hall (FEH)                                 "]
["1","09","03","14","01","  ",null,null,null,"FEH - Site Preparation/General Requirements                 "]
["1","09","03","14","02","  ",null,null,null,"FEH - Site Construction                                     "]
["1","09","03","14","03","  ",null,null,null,"FEH - Concrete                                              "]
["1","09","03","14","05","  ",null,null,null,"FEH - Metals                                                "]
["1","09","03","14","15","  ",null,null,null,"FEH - Mechanical                                            "]
["1","09","03","14","16","  ",null,null,null,"FEH - Electrical                                            "]
["1","09","03","14","17","  ",null,null,null,"FEH - Others (include Div 4, and 6 through 14)              "]
["1","09","03","14","18","  ",null,null,null,"FEH - Access Tunnel                                         "]
["1","09","03","14","19","  ",null,null,null,"FEH - Tunnel Construction                                   "]
["1","09","03","14","20","  ",null,null,null,"FEH - Project Close Out                                     "]
["1","09","03","15","  ","  ",null,null,null,"BTH Service Buildings 2.1, 2.2, and 2.3 (SB BTH)            "]
["1","09","03","15","03","  ",null,null,null,"SB BTH - Concrete                                           "]
["1","09","03","15","05","  ",null,null,null,"SB BTH - Metals                                             "]
["1","09","03","15","15","  ",null,null,null,"SB BTH - Mechanical                                         "]
["1","09","03","15","16","  ",null,null,null,"SB BTH - Electrical                                         "]
["1","09","03","15","17","  ",null,null,null,"SB BTH - Others (include Div 4, and 6 through 14            "]
["1","09","03","15","20","  ",null,null,null,"SB BTH - Project Close Out                                  "]
["1","09","03","16","  ","  ",null,null,null,"UH Service Building 3.1 (SB UH)                             "]
["1","09","03","16","01","  ",null,null,null,"SB UH - Site Preparation                                    "]
["1","09","03","16","03","  ",null,null,null,"SB UH - Concrete                                            "]
["1","09","03","16","05","  ",null,null,null,"SB UH - Metals                                              "]
["1","09","03","16","15","  ",null,null,null,"SB UH - Mechanical                                          "]
["1","09","03","16","16","  ",null,null,null,"SB UH - Electrical                                          "]
["1","09","03","16","17","  ",null,null,null,"SB UH - Others (include Div 4, and 6 through 14)            "]
["1","09","03","16","20","  ",null,null,null,"SB UH - Project Close Out                                   "]
["1","09","03","17","  ","  ",null,null,null,"FEH Service Building 8.1 (FEH SB)                           "]
["1","09","03","17","01","  ",null,null,null,"SB FEH - Site Preparation                                   "]
["1","09","03","17","03","  ",null,null,null,"SB FEH - Concrete                                           "]
["1","09","03","17","05","  ",null,null,null,"SB FEH - Metals                                             "]
["1","09","03","17","15","  ",null,null,null,"SB FEH - Mechanical                                         "]
["1","09","03","17","16","  ",null,null,null,"SB FEH - Electrical                                         "]
["1","09","03","17","17","  ",null,null,null,"SB FEH - Others (include Div 4, and 6 through 14            "]
["1","09","03","17","20","  ",null,null,null,"SB FEH - Project Close Out                                  "]
["1","09","03","18","  ","  ",null,null,null,"NEH Central Utility Plant (CUP)                             "]
["1","09","03","18","01","  ",null,null,null,"CUP - Site Preparation/General Requirements                 "]
["1","09","03","18","02","  ",null,null,null,"CUP - Site Construction                                     "]
["1","09","03","18","03","  ",null,null,null,"CUP - Concrete                                              "]
["1","09","03","18","05","  ",null,null,null,"CUP - Metals                                                "]
["1","09","03","18","15","  ",null,null,null,"CUP - Mechanical                                            "]
["1","09","03","18","16","  ",null,null,null,"CUP - Electrical                                            "]
["1","09","03","18","17","  ",null,null,null,"CUP - Others (include Div 4, and 6 through 14)              "]
["1","09","03","18","20","  ",null,null,null,"CUP - Project Close Out                                     "]
["1","09","03","19","  ","  ",null,null,null,"SLAC Space Renovation for LCLS Ops                          "]
["1","09","03","19","01","  ",null,null,null,"ED&I of SLAC Space Renovation for LCLS Ops                  "]
["1","09","03","19","02","  ",null,null,null,"Construction of SLAC Space Renovation for LCLS Ops          "]
["1","09","03","20","  ","  ",null,null,null,"Construction Credits and Debits                             "]
["1","09","03","20","01","  ",null,null,null,"Reduction for Subcontractor Work in Deleting CLOC           "]
["1","09","03","20","02","  ",null,null,null,"Bulletin #2 Changes                                         "]
["2","  ","  ","  ","  ","  ",null,null,null,"LCLS PROJECT - R&D, SPARES, COMMISSIONING                   "]
["2","01","  ","  ","  ","  ",null,null,null,"LCLS PROJECT MGMT, PLANNING & ADMN (OPC)                    "]
["2","01","01","  ","  ","  ",null,null,null,"Physics Support (OPC)                                       "]
["2","01","01","01","  ","  ",null,null,null,"LCLS Commissioning Management                               "]
["2","01","01","02","  ","  ",null,null,null,"Injector Physics                                            "]
["2","01","01","03","  ","  ",null,null,null,"Linac Physics                                               "]
["2","01","01","04","  ","  ",null,null,null,"Undulator Physics                                           "]
["2","01","01","05","  ","  ",null,null,null,"X-Ray Transport Physics                                     "]
["2","01","01","06","  ","  ",null,null,null,"X-Ray Physics Commissioning                                 "]
["2","01","01","07","  ","  ",null,null,null,"Conventional Facilities Physics                             "]
["2","01","01","08","  ","  ",null,null,null,"Consulting Physics (Collaboration)                          "]
["2","01","01","09","  ","  ",null,null,null,"Consulting Physics (SLAC)                                   "]
["2","01","01","10","  ","  ",null,null,null,"Global Controls Physics Liaison                             "]
["2","01","01","11","  ","  ",null,null,null,"Global Controls OPC                                         "]
["2","01","01","11","01","  ",null,null,null,"EPICS Control Modules                                       "]
["2","01","01","11","02","  ",null,null,null,"LLRF Controls - Closed                                      "]
["2","01","01","11","04","  ",null,null,null,"Laser Controls Design                                       "]
["2","01","01","11","05","  ",null,null,null,"Laser Heater Controls Design                                "]
["2","01","01","11","06","  ",null,null,null,"Timing Controls                                             "]
["2","01","01","11","07","  ",null,null,null,"Vacuum Controls                                             "]
["2","01","01","11","08","  ",null,null,null,"S/W & Controls Infrastructure                               "]
["2","01","01","11","09","  ",null,null,null,"Power Supply Control                                        "]
["2","01","01","11","10","  ",null,null,null,"MPS/PPS/BCS Controls                                        "]
["2","01","01","11","11","  ",null,null,null,"Global Controls Commissioning                               "]
["2","01","01","11","12","  ",null,null,null,"Global Controls Management - OPC                            "]
["2","01","01","11","12","01",null,null,null,"Global Controls Management - LOE"]
["2","01","01","11","12","02",null,null,null,"Global Controls Management - M&S"]
["2","01","01","11","13","  ",null,null,null,"SLC Aware IOC                                               "]
["2","01","01","11","14","  ",null,null,null,"Controls - Networking and Data Comm. OPC                    "]
["2","01","01","11","15","  ",null,null,null,"Controls S/W Applications LOE                               "]
["2","01","02","  ","  ","  ",null,null,null,"R&D Studies & Prototyping                                   "]
["2","01","02","01","  ","  ",null,null,null,"R&D Studies & Prototyping                                   "]
["2","01","03","  ","  ","  ",null,null,null,"Project Mgmnt, Planning and Admn - M&S (OPC)                "]
["2","01","03","01","  ","  ",null,null,null,"SLAC Project Office - General                               "]
["2","01","03","02","  ","  ",null,null,null,"SLAC Project Support                                        "]
["2","01","03","03","  ","  ",null,null,null,"Project Mgmnt, Planning and Admn - M&S (OPC)                "]
["2","01","03","05","  ","  ",null,null,null,"X-Ray Transport Physics                                     "]
["2","01","03","06","  ","  ",null,null,null,"X-Ray Endstation Physics                                    "]
["2","01","03","07","  ","  ",null,null,null,"Conventional Facilities Physics                             "]
["2","01","03","08","  ","  ",null,null,null,"Consulting Physics (Collaboration)                          "]
["2","01","03","09","  ","  ",null,null,null,"Consulting Physics (SLAC)                                   "]
["2","01","03","10","  ","  ",null,null,null,"Global Controls Physics Liaison                             "]
["2","01","03","11","  ","  ",null,null,null," Physics Commissioning Support - General                    "]
["2","02","  ","  ","  ","  ",null,null,null,"INJECTOR SYSTEM (OPC)                                       "]
["2","02","01","  ","  ","  ",null,null,null,"Injector System Management & Integration                    "]
["2","02","01","01","  ","  ",null,null,null,"Injector System Integration Effort / M&S                    "]
["2","02","01","02","  ","  ",null,null,null,"High level Application Software                             "]
["2","02","01","03","  ","  ",null,null,null,"Feedback Software                                           "]
["2","02","02","  ","  ","  ",null,null,null,"Injector Controls Subsystem                                 "]
["2","02","02","01","  ","  ",null,null,null,"Personnel Protection System (PPS) R&D                       "]
["2","02","02","02","  ","  ",null,null,null,"Beam Containment Subsystem (BCS)                            "]
["2","02","02","03","  ","  ",null,null,null,"Machine Protection Subsystem (MPS)                          "]
["2","02","02","04","  ","  ",null,null,null,"Power Conv (beamline pwr supp) Spares                       "]
["2","02","02","04","01","  ",null,null,null,"Power Supply Controls                                       "]
["2","02","02","05","  ","  ",null,null,null,"LLRF Controls                                               "]
["2","02","02","05","01","  ",null,null,null,"LLRF Controls                                               "]
["2","02","02","06","  ","  ",null,null,null,"E-Beam Diagnostics Controls                                 "]
["2","02","02","06","01","  ",null,null,null,"Controls - Wire Scanners                                    "]
["2","02","02","06","02","  ",null,null,null,"Controls - BPM Processor Module                             "]
["2","02","02","06","03","  ",null,null,null,"Controls - Toroids                                          "]
["2","02","02","06","05","  ",null,null,null,"Controls - Profile Monitors                                 "]
["2","02","02","06","06","  ",null,null,null,"Control - EO Diagnostic                                     "]
["2","02","02","06","12","  ",null,null,null,"Controls - Movable Collimator                               "]
["2","02","02","06","14","  ",null,null,null,"Controls - Faraday Cup                                      "]
["2","02","02","06","15","  ",null,null,null,"Controls - Tune-Up Dump                                     "]
["2","02","02","06","16","  ",null,null,null,"Cherenkov Commissioning Support                             "]
["2","02","02","08","  ","  ",null,null,null,"Timing Controls                                             "]
["2","02","02","09","  ","  ",null,null,null,"Vacuum Controls                                             "]
["2","02","02","10","  ","  ",null,null,null,"Software & Controls Infrastructure                          "]
["2","02","02","11","  ","  ",null,null,null,"EPICS VXI Control Modules                                   "]
["2","02","02","12","  ","  ",null,null,null,"Laser Controls                                              "]
["2","02","02","13","  ","  ",null,null,null,"Laser Heater Controls                                       "]
["2","02","03","  ","  ","  ",null,null,null,"Injector Lasers                                             "]
["2","02","03","01","  ","  ",null,null,null,"Drive Laser Prototyping                                     "]
["2","02","03","02","  ","  ",null,null,null,"Drive Laser System                                          "]
["2","02","03","03","  ","  ",null,null,null,"Drive Laser Diagnostics                                     "]
["2","02","03","04","  ","  ",null,null,null,"Timing Stability Monitoring                                 "]
["2","02","03","05","  ","  ",null,null,null,"Steering Stability Feedback & Msmts                         "]
["2","02","03","06","  ","  ",null,null,null,"Pre Amp Low Power Comp                                      "]
["2","02","03","07","  ","  ",null,null,null,"Transport to Tunnel & Relay Optics                          "]
["2","02","03","08","  ","  ",null,null,null,"UV Launch, Conditioning & Diagnostics                       "]
["2","02","03","09","  ","  ",null,null,null,"Load Lock Transport System                                  "]
["2","02","03","10","  ","  ",null,null,null,"Visible Optical Transport & Optics                          "]
["2","02","03","11","  ","  ",null,null,null,"LB Infrastructure & LB System Wide Items                    "]
["2","02","03","12","  ","  ",null,null,null,"Alignment Laser                                             "]
["2","02","03","13","  ","  ",null,null,null,"Light path to Streak Camera                                 "]
["2","02","03","14","  ","  ",null,null,null,"LSR HTR - Beam Conditioning Optics (Laser Bay)              "]
["2","02","03","15","  ","  ",null,null,null,"LSR HTR - Transport Optics (Bay to Tunnel)                  "]
["2","02","03","16","  ","  ",null,null,null,"LSR HTR - Photon Beam Diagnostics                           "]
["2","02","04","  ","  ","  ",null,null,null,"Injector RF Subsystem                                       "]
["2","02","04","01","  ","  ",null,null,null,"RF Gun & Load Lock                                          "]
["2","02","04","01","01","  ",null,null,null,"RF Gun                                                      "]
["2","02","04","01","02","  ",null,null,null,"RF Gun Supports                                             "]
["2","02","04","01","03","  ",null,null,null,"Gun Load Lock                                               "]
["2","02","04","01","04","  ",null,null,null,"Gun Load Lock Supports                                      "]
["2","02","04","01","05","  ",null,null,null,"Gun Solenoid                                                "]
["2","02","04","01","06","  ",null,null,null,"Gun Solenoid Supports                                       "]
["2","02","04","01","07","  ",null,null,null,"Gun RF Feed                                                 "]
["2","02","04","01","08","  ",null,null,null,"Gun RF Feed Supports                                        "]
["2","02","04","02","  ","  ",null,null,null,"Cathode Processing (CP) Station                             "]
["2","02","04","02","01","  ",null,null,null,"CP Cathode Assembly & Supports                              "]
["2","02","04","02","02","  ",null,null,null,"CP Load Lock                                                "]
["2","02","04","02","03","  ",null,null,null,"CP Load Lock Supports                                       "]
["2","02","04","02","04","  ",null,null,null,"CP Station                                                  "]
["2","02","04","02","05","  ",null,null,null,"Cathode Lab Infrastructure                                  "]
["2","02","04","03","  ","  ",null,null,null,"S-Band Low Level System                                     "]
["2","02","04","03","01","  ",null,null,null,"S-Band LL Controls Timing System                            "]
["2","02","04","04","  ","  ",null,null,null,"S-Band High Power System                                    "]
["2","02","04","05","  ","  ",null,null,null,"Injector RF Waveguide Subsystem                             "]
["2","02","04","05","01","  ",null,null,null,"RF Waveguides                                               "]
["2","02","04","05","02","  ",null,null,null,"RF Waveguide Supports                                       "]
["2","02","04","06","  ","  ",null,null,null,"Injector Linac Structures                                   "]
["2","02","04","06","01","  ",null,null,null,"L0-1 Structure Assembly                                     "]
["2","02","04","06","02","  ",null,null,null,"L0-2 Structure Assembly                                     "]
["2","02","04","06","03","  ",null,null,null,"Major Linac Support                                         "]
["2","02","04","06","04","  ",null,null,null,"GTL RF Phase Cavity                                         "]
["2","02","04","06","05","  ",null,null,null,"LTDL1 RF Kicker                                             "]
["2","02","05","  ","  ","  ",null,null,null,"Injector Magnets & Supports                                 "]
["2","02","05","01","  ","  ",null,null,null,"Injector Dipoles                                            "]
["2","02","05","01","01","  ",null,null,null,"DL1 B01 & B02 Dipoles                                       "]
["2","02","05","01","02","  ",null,null,null,"SAB Spectrometer Dipole                                     "]
["2","02","05","01","03","  ",null,null,null,"Chicane                                                     "]
["2","02","05","02","  ","  ",null,null,null,"Injector Quadrupoles                                        "]
["2","02","05","02","01","  ",null,null,null,"L0-1TL0-2 Quadrupoles ( )                                   "]
["2","02","05","02","02","  ",null,null,null,"LTDL1 Quadrupoles ( )                                       "]
["2","02","05","02","03","  ",null,null,null,"DL1 QB Quadrupole                                           "]
["2","02","05","02","04","  ",null,null,null,"DL1TL Quadrupoles ( )                                       "]
["2","02","05","02","05","  ",null,null,null,"SAB Quadrupoles ( )                                         "]
["2","02","05","03","  ","  ",null,null,null,"Injector Steering Coils                                     "]
["2","02","05","03","01","  ",null,null,null,"GTL Steering Coils ( )X-Y (SC1)                             "]
["2","02","05","03","02","  ",null,null,null,"L0-1TL0-2 Linac Steering Coils ( )                          "]
["2","02","05","03","03","  ",null,null,null,"LTDL1 Steering Coils ( )X-Y                                 "]
["2","02","05","03","04","  ",null,null,null,"DL1TL Steering Coils ( X-Y Assys)                           "]
["2","02","05","03","05","  ",null,null,null,"SAB Steering Coils ( )                                      "]
["2","02","05","04","  ","  ",null,null,null,"Linac Solenoid & Supports                                   "]
["2","02","05","05","  ","  ",null,null,null,"Injector Laser Heater Subsystem                             "]
["2","02","05","05","01","  ",null,null,null,"System Design & Optimization                                "]
["2","02","05","05","02","  ",null,null,null,"Undulator                                                   "]
["2","02","06","  ","  ","  ",null,null,null,"Injector Vacuum & Supports                                  "]
["2","02","06","01","  ","  ",null,null,null,"GTL Vacuum Components                                       "]
["2","02","06","02","  ","  ",null,null,null,"GTL Supports                                                "]
["2","02","06","03","  ","  ",null,null,null,"GTL Pumping & Optic Chamber                                 "]
["2","02","06","04","  ","  ",null,null,null,"L0-1TL0-2 Vacuum Components                                 "]
["2","02","06","05","  ","  ",null,null,null,"L0-1TL0-2 Major tube support structure                      "]
["2","02","06","06","  ","  ",null,null,null,"LTDL1 Minor Tube Supports                                   "]
["2","02","06","07","  ","  ",null,null,null,"DL1 Supports                                                "]
["2","02","06","08","  ","  ",null,null,null,"DL1 Vacuum Chamber                                          "]
["2","02","06","09","  ","  ",null,null,null,"DL1TL Vacuum Components                                     "]
["2","02","06","10","  ","  ",null,null,null,"SAB Vacuum Chamber and Components                           "]
["2","02","06","11","  ","  ",null,null,null,"SAB Supports                                                "]
["2","02","07","  ","  ","  ",null,null,null,"Injector Diagnostics                                        "]
["2","02","07","01","  ","  ",null,null,null,"Injector Beam Position Monitors                             "]
["2","02","07","01","01","  ",null,null,null,"GTL BPMs ( )                                                "]
["2","02","07","01","02","  ",null,null,null,"Gun Spectrometer (GS) Assembly                              "]
["2","02","07","01","03","  ",null,null,null,"L0-1TL0-2 BPMs ( )                                          "]
["2","02","07","01","04","  ",null,null,null,"LTDL1 BPMs ( )                                              "]
["2","02","07","01","05","  ",null,null,null,"DL1TL BPMs ( )                                              "]
["2","02","07","01","06","  ",null,null,null,"SAB BPM ( )                                                 "]
["2","02","07","02","  ","  ",null,null,null,"Injector Current Monitors                                   "]
["2","02","07","02","01","  ",null,null,null,"GTL Current Monitors ( )                                    "]
["2","02","07","02","02","  ",null,null,null,"L0-1TL0-2 Current Monitor ( )                               "]
["2","02","07","02","03","  ",null,null,null,"LTDL1 Current Monitors ( )                                  "]
["2","02","07","02","04","  ",null,null,null,"DL1TL Current Monitor ( )                                   "]
["2","02","07","02","05","  ",null,null,null,"SAB Current Monitor ( )                                     "]
["2","02","07","03","  ","  ",null,null,null,"Injector Bunch Length Monitors                              "]
["2","02","07","03","01","  ",null,null,null,"GTL E/O (EO1)                                               "]
["2","02","07","03","02","  ",null,null,null,"LTDL1 E/O EO2                                               "]
["2","02","07","03","03","  ",null,null,null,"DL1TL EO3                                                   "]
["2","02","07","04","  ","  ",null,null,null,"Injector Profile Monitors                                   "]
["2","02","07","04","01","  ",null,null,null,"GTL Faraday Cup/YAG1                                        "]
["2","02","07","04","02","  ",null,null,null,"GTL YAG ( )                                                 "]
["2","02","07","04","03","  ",null,null,null,"L0-1TL0-2 OTR/YAG ( )                                       "]
["2","02","07","04","04","  ",null,null,null,"LTDL1 OTR(5)/YAG ( )                                        "]
["2","02","07","04","05","  ",null,null,null,"DL1 OTR                                                     "]
["2","02","07","04","06","  ",null,null,null,"DL1TL OTR                                                   "]
["2","02","07","04","07","  ",null,null,null,"SAB YAG                                                     "]
["2","02","07","04","08","  ",null,null,null,"SAB Beam Dump and Shielding                                 "]
["2","02","07","05","  ","  ",null,null,null,"Injector Wire Scanners                                      "]
["2","02","07","05","01","  ",null,null,null,"LTDL1 Wire Scanners ( )                                     "]
["2","02","07","05","02","  ",null,null,null,"DL1 Wire Scanner                                            "]
["2","02","07","06","  ","  ",null,null,null,"LSR HTR - Electron Beam Diagnostics                         "]
["2","02","07","07","  ","  ",null,null,null,"PPS Stopper                                                 "]
["2","02","08","  ","  ","  ",null,null,null,"Injector System Emittance Enhancement                       "]
["2","02","08","01","  ","  ",null,null,null,"Heater Integration                                          "]
["2","02","08","02","  ","  ",null,null,null,"Heater Laser & Optics                                       "]
["2","02","08","03","  ","  ",null,null,null,"Heater Magnets                                              "]
["2","02","08","03","01","  ",null,null,null,"Heater Dipoles                                              "]
["2","02","08","03","02","  ",null,null,null,"Heater Undulator                                            "]
["2","02","08","04","  ","  ",null,null,null,"Heater Vacuum                                               "]
["2","02","08","05","  ","  ",null,null,null,"Heater Diagnostics                                          "]
["2","02","08","06","  ","  ",null,null,null,"Heater Install & Align                                      "]
["2","02","17","  ","  ","  ",null,null,null,"Injector System Commissioning                               "]
["2","02","17","01","  ","  ",null,null,null,"Controls Commissioning                                      "]
["2","02","17","02","  ","  ",null,null,null,"Drive Laser Commissioning                                   "]
["2","02","17","03","  ","  ",null,null,null,"RF Conditioning                                             "]
["2","02","17","04","  ","  ",null,null,null,"RF Gun Operation with Beam                                  "]
["2","02","17","05","  ","  ",null,null,null,"L0-1&L0-2 Commissioning                                     "]
["2","02","17","06","  ","  ",null,null,null,"L0&SAB Commissioning                                        "]
["2","02","17","07","  ","  ",null,null,null,"DL1 Commissioning                                           "]
["2","02","17","08","  ","  ",null,null,null,"Injector Optimization                                       "]
["2","02","17","10","  ","  ",null,null,null,"Injector System Commissioning                               "]
["2","03","  ","  ","  ","  ",null,null,null,"LINAC SYSTEM (OPC)                                          "]
["2","03","01","  ","  ","  ",null,null,null,"Linac System Mgmt & Integration                             "]
["2","03","01","01","  ","  ",null,null,null,"Linac System Mgmt & Integration                             "]
["2","03","01","02","  ","  ",null,null,null,"Linac Controls Integration                                  "]
["2","03","01","03","  ","  ",null,null,null,"Travel                                                      "]
["2","03","01","04","  ","  ",null,null,null,"Linac Management                                            "]
["2","03","02","  ","  ","  ",null,null,null,"Linac Controls & Power Conversion Subsystem                 "]
["2","03","02","01","  ","  ",null,null,null,"Personnel Protection System (PPS)                           "]
["2","03","02","02","  ","  ",null,null,null,"Beam Containment System (BCS)                               "]
["2","03","02","03","  ","  ",null,null,null,"Machine Protection System (MPS)                             "]
["2","03","02","04","  ","  ",null,null,null,"Power Conversion                                            "]
["2","03","02","04","01","  ",null,null,null,"Spare Power Supply (Dipole Type)                            "]
["2","03","02","04","02","  ",null,null,null,"Spare Power Supply (Quad Type)                              "]
["2","03","02","04","03","  ",null,null,null,"Spare Power Supply (Trim Type)                              "]
["2","03","02","04","04","  ",null,null,null,"Controls & Power Supply - Spare Misc Hdwr                   "]
["2","03","02","05","  ","  ",null,null,null,"Controls - LLRF                                             "]
["2","03","02","06","  ","  ",null,null,null,"Controls - E-Beam Diagnostic                                "]
["2","03","02","06","01","  ",null,null,null,"Controls - Wire Scanners                                    "]
["2","03","02","06","02","  ",null,null,null,"Controls - BPMs                                             "]
["2","03","02","06","03","  ",null,null,null,"Controls - Toroids                                          "]
["2","03","02","06","04","  ",null,null,null,"Controls - Stoppers Commissioning                           "]
["2","03","02","06","05","  ",null,null,null,"Controls - Profile Monitors                                 "]
["2","03","02","06","07","  ",null,null,null,"Controls - BLM                                              "]
["2","03","02","06","09","  ",null,null,null,"Controls - Single Beam Dump                                 "]
["2","03","02","06","10","  ",null,null,null,"Controls - E-Beam Dump                                      "]
["2","03","02","06","12","  ",null,null,null,"Controls - Collimators                                      "]
["2","03","02","07","  ","  ",null,null,null,"Controls - Laser                                            "]
["2","03","02","08","  ","  ",null,null,null,"Controls - Timing                                           "]
["2","03","02","09","  ","  ",null,null,null,"Controls - Vacuum                                           "]
["2","03","02","10","  ","  ",null,null,null,"Software & Controls Infrastructure                          "]
["2","03","03","  ","  ","  ",null,null,null,"Linac Magnets & Supports                                    "]
["2","03","03","01","  ","  ",null,null,null,"Bend Magnet (BX1_BC1)                                       "]
["2","03","03","02","  ","  ",null,null,null,"Bend Magnet (BX3_LTU)                                       "]
["2","03","03","03","  ","  ",null,null,null,"Bend Magnet (BX2_BC2)                                       "]
["2","03","03","04","  ","  ",null,null,null,"Bend Magnet (BY_LTU)                                        "]
["2","03","03","05","  ","  ",null,null,null,"Quad Magnet (Quad_LTU)                                      "]
["2","03","03","07","  ","  ",null,null,null,"Quad Magnet (QE)                                            "]
["2","03","03","08","  ","  ",null,null,null,"Corrector Magnet (Type 4)                                   "]
["2","03","03","09","  ","  ",null,null,null,"Bend Magnet (BYD_LTU)                                       "]
["2","03","03","10","  ","  ",null,null,null,"Quad Magnet (QA)                                            "]
["2","03","03","11","  ","  ",null,null,null,"Bend Magnet (BYPM_LTU)                                      "]
["2","03","03","12","  ","  ",null,null,null,"Bend Magnet (BYKIK_LTU)                                     "]
["2","03","03","13","  ","  ",null,null,null,"Bend Magnet (BYW_LTU)                                       "]
["2","03","04","  ","  ","  ",null,null,null,"Linac Vacuum Subsystem                                      "]
["2","03","04","01","  ","  ",null,null,null,"Linac Vacuum Subsystem Operations Equip                     "]
["2","03","04","02","  ","  ",null,null,null,"Linac Beamline Vacuum System                                "]
["2","03","04","03","  ","  ",null,null,null,"BC1 Vacuum System                                           "]
["2","03","04","04","  ","  ",null,null,null,"BC2 Vacuum System                                           "]
["2","03","04","05","  ","  ",null,null,null,"Linac to Undulator (LTU) Vacuum System                      "]
["2","03","04","06","  ","  ",null,null,null,"Dumpline Vacuum System                                      "]
["2","03","04","07","  ","  ",null,null,null,"Vacuum Undulator Interface                                  "]
["2","03","04","07","01","  ",null,null,null,"Entrance Assembly Section                                   "]
["2","03","04","07","02","  ",null,null,null,"Exit Assembly Section                                       "]
["2","03","05","  ","  ","  ",null,null,null,"Linac Electron Diagnostics                                  "]
["2","03","05","01","  ","  ",null,null,null,"Wire Scanners                                               "]
["2","03","05","02","  ","  ",null,null,null,"Beam Position Monitors                                      "]
["2","03","05","03","  ","  ",null,null,null,"Toroids Beam Charge                                         "]
["2","03","05","04","  ","  ",null,null,null,"Stoppers Tune Up Dump                                       "]
["2","03","05","05","  ","  ",null,null,null,"Profile Monitors                                            "]
["2","03","05","06","  ","  ",null,null,null,"E/O Bunch Length Monitors                                   "]
["2","03","05","07","  ","  ",null,null,null,"Bunch Length Monitors                                       "]
["2","03","05","08","  ","  ",null,null,null,"Beam Loss Monitors                                          "]
["2","03","05","09","  ","  ",null,null,null,"Single Beam Dump                                            "]
["2","03","05","10","  ","  ",null,null,null,"Electron Safety Beam Dump                                   "]
["2","03","05","11","  ","  ",null,null,null,"Protection Collimators                                      "]
["2","03","05","12","  ","  ",null,null,null,"Movable Collimators                                         "]
["2","03","05","13","  ","  ",null,null,null,"Safety Dump                                                 "]
["2","03","05","14","  ","  ",null,null,null,"Charge Monitor (Entrance/Exit Assebmly)                     "]
["2","03","06","  ","  ","  ",null,null,null,"Linac RF Subsystem                                          "]
["2","03","06","02","  ","  ",null,null,null,"S-Band High Power System                                    "]
["2","03","06","03","  ","  ",null,null,null,"S-Band Structures                                           "]
["2","03","06","04","  ","  ",null,null,null,"X-Band Low Level System                                     "]
["2","03","06","05","  ","  ",null,null,null,"X-Band High Power System                                    "]
["2","03","06","06","  ","  ",null,null,null,"X-Band Structures                                           "]
["2","03","06","07","  ","  ",null,null,null,"RF Distribution System                                      "]
["2","03","06","07","01","  ",null,null,null,"Modulator                                                   "]
["2","03","06","07","02","  ",null,null,null,"Solid State Sub Booster                                     "]
["2","03","06","07","05","  ",null,null,null,"Bunch Length Electronics                                    "]
["2","03","06","07","07","  ",null,null,null,"RF Distribution L2 & L3                                     "]
["2","03","06","07","08","  ",null,null,null,"RF Fiber Optics Electronics                                 "]
["2","03","07","  ","  ","  ",null,null,null,"Linac System Commissioning                                  "]
["2","03","07","01","  ","  ",null,null,null,"Linac L01 System Commissioning                              "]
["2","03","07","02","  ","  ",null,null,null,"Linac BC1 System Commissioning                              "]
["2","03","07","03","  ","  ",null,null,null,"Linac L02 System Commissioning                              "]
["2","03","07","04","  ","  ",null,null,null,"Linac BC2 System Commissioning                              "]
["2","03","07","05","  ","  ",null,null,null,"Linac L03 System Commissioning                              "]
["2","03","07","06","  ","  ",null,null,null,"Linac LTU System Commissioning                              "]
["2","03","07","07","  ","  ",null,null,null,"Linac E-Dump System Commissioining                          "]
["2","03","07","08","  ","  ",null,null,null,"Linac Undulator Interface                                   "]
["2","03","07","10","  ","  ",null,null,null,"Linac System Commissioning                                  "]
["2","04","  ","  ","  ","  ",null,null,null,"UNDULATOR SYSTEM (OPC)                                      "]
["2","04","01","  ","  ","  ",null,null,null,"Undulator System Management & Integration                   "]
["2","04","01","01","  ","  ",null,null,null,"Undulator System Mgmt & Integration                         "]
["2","04","02","  ","  ","  ",null,null,null,"Controls                                                    "]
["2","04","02","01","  ","  ",null,null,null,"Controls Management and Integration                         "]
["2","04","02","04","  ","  ",null,null,null,"Video                                                       "]
["2","04","02","07","  ","  ",null,null,null,"Machine Protection                                          "]
["2","04","03","  ","  ","  ",null,null,null,"Undulator Magnet & Support                                  "]
["2","04","03","01","  ","  ",null,null,null,"Undulator Magnets & Support-Mgmt & Integration              "]
["2","04","03","02","  ","  ",null,null,null,"First Prototype Undulator & Mfg Plan                        "]
["2","04","03","03","  ","  ",null,null,null,"1st Article Undulators & Long Lead Procurements             "]
["2","04","03","04","  ","  ",null,null,null,"Production Undulator                                        "]
["2","04","03","05","  ","  ",null,null,null,"Focusing Magnets                                            "]
["2","04","03","06","  ","  ",null,null,null,"Undulator Magnetic Measurement Facility (SLAC)              "]
["2","04","03","08","  ","  ",null,null,null,"Fixed Supports                                              "]
["2","04","04","  ","  ","  ",null,null,null,"Vacuum System                                               "]
["2","04","04","02","  ","  ",null,null,null,"Undulator Vacuum Chamber Assembly                           "]
["2","04","04","02","01","  ",null,null,null,"Surface Roughness Minimization                              "]
["2","04","04","02","03","  ",null,null,null,"Materials Study for AC Conductivity                         "]
["2","04","04","03","  ","  ",null,null,null,"Beam-line Bellows Module Assembly                           "]
["2","04","04","04","  ","  ",null,null,null,"Single Undulator Test (SUV) Vacuum                          "]
["2","04","04","05","  ","  ",null,null,null,"Short Diagnostic Break (SDB) Assembly                       "]
["2","04","04","06","  ","  ",null,null,null,"Long Diagnostic Break (LDB) Assembly                        "]
["2","04","04","07","  ","  ",null,null,null,"Entrance Section Assembly                                   "]
["2","04","04","08","  ","  ",null,null,null,"Exit Section Assembly                                       "]
["2","04","04","09","  ","  ",null,null,null,"Baking System                                               "]
["2","04","05","  ","  ","  ",null,null,null,"Undulator System Diagnostics [OPC]                          "]
["2","04","05","02","  ","  ",null,null,null,"Undulator Line Diagnostics                                  "]
["2","04","05","03","  ","  ",null,null,null,"High-Power X-Ray and Profile Diagnostics (HPD)              "]
["2","04","05","04","  ","  ",null,null,null,"End-of-Undulator(EOU) X-ray and Profile diagnost            "]
["2","04","05","05","  ","  ",null,null,null,"RFBPM                                                       "]
["2","04","05","06","  ","  ",null,null,null,"Beam Finder Wire                                            "]
["2","04","05","07","  ","  ",null,null,null,"Charge Monitor (CM)                                         "]
["2","04","05","08","  ","  ",null,null,null,"Beam Loss Monitoring                                        "]
["2","04","05","09","  ","  ",null,null,null,"Radiation Detection Monitor (RDM)                           "]
["2","04","05","10","  ","  ",null,null,null,"Single Undulator Test (SUT) Diagnostics                     "]
["2","04","06","  ","  ","  ",null,null,null,"Undulator System Commissioning                              "]
["2","04","06","01","  ","  ",null,null,null,"Undulator System Commissioning                              "]
["2","05","  ","  ","  ","  ",null,null,null,"X-RAY TRANSPORT & DIAGNOSTICS SYSTEMS (OPC)                 "]
["2","05","01","  ","  ","  ",null,null,null,"System Management & Integration                             "]
["2","05","01","01","  ","  ",null,null,null,"Management                                                  "]
["2","05","02","  ","  ","  ",null,null,null,"Controls                                                    "]
["2","05","02","01","  ","  ",null,null,null,"Controls - EPICS                                            "]
["2","05","02","02","  ","  ",null,null,null,"Controls - System                                           "]
["2","05","03","  ","  ","  ",null,null,null,"Mechanical & Vacuum Subsystem                               "]
["2","05","03","01","  ","  ",null,null,null,"Vacuum Systems Engineering                                  "]
["2","05","03","02","  ","  ",null,null,null,"Mech/Vac Front End                                          "]
["2","05","03","03","  ","  ",null,null,null,"Mech/Vac Near Hall                                          "]
["2","05","03","04","  ","  ",null,null,null,"Mech/Vac Tunnel                                             "]
["2","05","03","05","  ","  ",null,null,null,"Mech/Vac Far Hall                                           "]
["2","05","04","  ","  ","  ",null,null,null,"Optical Subsystem                                           "]
["2","05","04","01","  ","  ",null,null,null,"Optical Systems Engineering                                 "]
["2","05","04","02","  ","  ",null,null,null,"Facility Optics                                             "]
["2","05","04","03","  ","  ",null,null,null,"End Station Optics                                          "]
["2","05","04","04","  ","  ",null,null,null,"Crystals & Gratings                                         "]
["2","05","05","  ","  ","  ",null,null,null,"Diagnostics Subsystem                                       "]
["2","05","05","01","  ","  ",null,null,null,"Diagnostic Systems Engineering                              "]
["2","05","05","02","  ","  ",null,null,null,"Modeling & Simulation                                       "]
["2","05","05","03","  ","  ",null,null,null,"Facility Diagnostics                                        "]
["2","05","05","04","  ","  ",null,null,null,"Commissioning Diagnostics                                   "]
["2","05","06","  ","  ","  ",null,null,null,"X-Ray Transport & Diag. System Commissioning                "]
["2","05","06","01","  ","  ",null,null,null,"X-Ray Transport & Diag. System Commissioning                "]
["2","06","  ","  ","  ","  ",null,null,null,"X-RAY END STATION SYSTEMS (OPC)                             "]
["2","06","01","  ","  ","  ",null,null,null,"XE System Mgmt & Integration                                "]
["2","06","01","01","  ","  ",null,null,null,"Management                                                  "]
["2","06","02","  ","  ","  ",null,null,null,"Controls Subsystem                                          "]
["2","06","02","01","  ","  ",null,null,null,"Cabling                                                     "]
["2","06","02","02","  ","  ",null,null,null,"Network                                                     "]
["2","06","02","03","  ","  ",null,null,null,"PC Support                                                  "]
["2","06","02","04","  ","  ",null,null,null,"Beamline Controls                                           "]
["2","06","02","05","  ","  ",null,null,null,"X-Ray PPS                                                   "]
["2","06","02","06","  ","  ",null,null,null,"X-Ray MPS                                                   "]
["2","06","02","07","  ","  ",null,null,null,"Laser PPS                                                   "]
["2","06","02","08","  ","  ",null,null,null,"R&D: 2D X-Ray Detector Controls                             "]
["2","06","03","  ","  ","  ",null,null,null,"Commissioning                                               "]
["2","06","03","01","  ","  ",null,null,null,"Commissioning - Controls                                    "]
["2","06","03","02","  ","  ",null,null,null,"Commissioning - XES Laser                                   "]
["2","06","03","03","  ","  ",null,null,null,"Commissioning - AMO Experiment                              "]
["2","06","03","05","  ","  ",null,null,null,"Commissioning - 2D X-Ray Detector                           "]
["2","06","04","  ","  ","  ",null,null,null,"Spares                                                      "]
["2","06","04","01","  ","  ",null,null,null,"Spares - PPS Stoppers                                       "]
["2","06","04","02","  ","  ",null,null,null,"Spares -                                                    "]
["2","06","04","03","  ","  ",null,null,null,"Spares -                                                    "]
["2","06","04","04","  ","  ",null,null,null,"Spares -                                                    "]
["2","06","04","05","  ","  ",null,null,null,"Spares -                                                    "]
["2","06","05","  ","  ","  ",null,null,null,"X-Ray Detectors                                             "]
["2","06","05","01","  ","  ",null,null,null,"Beam Imaging                                                "]
["2","06","05","02","  ","  ",null,null,null,"2-D X-Ray Detector                                          "]
["2","06","05","02","01","  ",null,null,null,"Proto 2 ASIC                                                "]
["2","06","05","02","02","  ",null,null,null,"Proto 3 ASIC                                                "]
["2","06","05","02","03","  ",null,null,null,"Full Lot Prototype                                          "]
["2","06","05","02","04","  ",null,null,null,"500px Detector                                              "]
["2","06","05","02","05","  ",null,null,null,"2D X-Ray Detector Commissioning                             "]
["2","06","05","03","  ","  ",null,null,null,"Beam Intensity                                              "]
["2","06","05","04","  ","  ",null,null,null,"Streak Camera                                               "]
["2","06","07","  ","  ","  ",null,null,null,"Atomic Physics                                              "]
["2","06","07","01","  ","  ",null,null,null,"Atomic Physics Samples                                      "]
["2","06","07","02","  ","  ",null,null,null,"Atomic Physics Diagnostics                                  "]
["2","06","07","03","  ","  ",null,null,null,"Atomic Physics Data Analysis                                "]
["2","06","07","04","  ","  ",null,null,null,"Atomic Physics Detectors                                    "]
["2","08","  ","  ","  ","  ",null,null,null,"LCLS SYSTEM COMMISSIONING (OPC)                             "]
["2","09","  ","  ","  ","  ",null,null,null,"CONVENTIONAL FACILITIES (OPC)                               "]
["2","09","01","  ","  ","  ",null,null,null,"MANAGEMENT INTEGRATION                                      "]
["2","09","03","  ","  ","  ",null,null,null,"RSY - CLOC Commissioning                                    "]
["2","09","03","05","  ","  ",null,null,null,"RSY-CLOC Commissioning                                      "]

{"sheet":"CHNUM","index":4,"n_rows":368,"n_cols":5,"rows_kept":368,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["FUND","AID","CODE","TITLE","STATUS"]
["c","9242570","1.01.01.01","Radiation Physics","Open"]
["c","9242571","1.01.01.02","ESH Management & Coodination","Open"]
["c","9242572","1.01.01.03","Seismic & Engineering Support","Open"]
["l","9242335","1.01.02.01.01","SLAC Project Office - General","Open"]
["l","9242336","1.01.02.01.02","SLAC Project Support","Open"]
["l","9242337","1.01.02.01.03","SLAC Project Office M&S","Open"]
["c","9242574","1.01.03.03","System Integration","Open"]
["l","9242059","1.01.03.05.02","LLRF Controls","Open"]
["l","9242060","1.01.03.05.03","E-Beam Diagnostics & Controls","Open"]
["c","9242921","1.01.03.05.04","Laser Controls Design","Open"]
["c","9242575","1.01.03.05.05","Laser Heater Controls Design","Open"]
["l","9242104","1.01.03.05.07","Vacuum Controls Interface","Open"]
["l","9242105","1.01.03.05.09","Power Supply Control","Open"]
["l","9242394","1.01.03.05.11","Design MPS","Open"]
["l","9242333","1.01.03.05.12","Global Controls Management","Open"]
["c","9242576","1.01.04.01","Education/Outreach Travel","Open"]
["c","9242577","1.01.04.02","Education/Outreach M&S","Open"]
["l","9242124","1.02.03.03","Drive Laser Diagnostics","Open"]
["c","9242138","1.02.04.01.09","RF Gun Spares Credit","Open"]
["c","9242580","1.03.01.01.04","BC2 System Integration","Open"]
["c","9242581","1.03.01.01.05","L03 System Integration","Open"]
["c","9242582","1.03.01.01.06","LTU System Integration","Open"]
["c","9242583","1.03.01.01.07","E-Dump System Integration","Open"]
["c","9242584","1.03.01.03","Travel","Open"]
["c","9242585","1.03.01.04","Linac Management","Open"]
["c","9242586","1.03.02.01","Personnel Protection System (PPS)","Open"]
["c","9242587","1.03.02.02","Beam Containment System (BCS)","Open"]
["c","9242588","1.03.02.03","Machine Protection System (MPS)","Open"]
["l","9242226","1.03.02.04.01","Beamline Power Supplies - (Dipole Type)","Open"]
["c","9242589","1.03.02.04.02","Beamline Power Supplies-(Quad Type)","Open"]
["c","9242590","1.03.02.04.03","Beamline Power Supplies-(Trim Type)","Open"]
["l","9242227","1.03.02.04.04","Beamline Power Supplies - MIsc Hdwr","Open"]
["l","9242228","1.03.02.05","Controls - LLRF","Open"]
["c","9242591","1.03.02.06.01","Controls-Wire Scanners","Open"]
["c","9242592","1.03.02.06.02","Controls-BPMs","Open"]
["c","9242593","1.03.02.06.03","Controls-Toroids","Open"]
["c","9242594","1.03.02.06.04","Controls-Stoppers","Open"]
["c","9242595","1.03.02.06.05","Controls-Profile Monitors","Open"]
["c","9242597","1.03.02.06.07","Controls-Bunch Length Monitors","Open"]
["c","9242598","1.03.02.06.08","Controls-Beam Loss Monitors","Open"]
["c","9242599","1.03.02.06.09","Controls-Single Beam Dump","Open"]
["c","9242600","1.03.02.06.10","Controls-E Beam Dump","Open"]
["c","9242601","1.03.02.06.11","Controls-Protection Collimator","Open"]
["c","9242602","1.03.02.06.12","Controls-Movable Collimator","Open"]
["c","9242604","1.03.02.08","Controls Timing","Open"]
["c","9242605","1.03.02.09.01","Interlocks","Open"]
["c","9242606","1.03.02.09.02","Vacuum Instrumentation & Controls","Open"]
["l","9242230","1.03.02.10.05","Computers","Open"]
["c","9242607","1.03.03.02","BX3 LTU ( )","Open"]
["l","9242232","1.03.03.03","BX2_BC2_()","Open"]
["c","9242608","1.03.03.04","BY_LTU","Open"]
["c","9242609","1.03.03.05","LTU Quad","Open"]
["c","9242610","1.03.03.07","QE_( )","Open"]
["c","9242611","1.03.03.08","Corr_(Type 4)","Open"]
["c","9242612","1.03.03.09","BYD_(Dump Bend)","Open"]
["c","9242613","1.03.03.10","QA_( )","Open"]
["c","9242614","1.03.03.11","BYPM_(Safety Dump)","Open"]
["c","9242615","1.03.03.12","BYKIK_(Single Beam Kicker)","Open"]
["c","9242616","1.03.03.13","BYW_( )","Open"]
["l","9242935","1.03.03.14","Muon Spoiler Magnets","Open"]
["c","9242396","1.03.03.15","Muon Toroid (E-Dump)","Open"]
["c","9242617","1.03.04.02","Linac Beamline Vacuum System","Open"]
["c","9242618","1.03.04.04","BC2 Vacuum System","Open"]
["c","9242619","1.03.04.05","Linac to Undulator (LTU) Vacuum System","Open"]
["c","9242620","1.03.04.06","Dumpline Vacuum System","Open"]
["c","9242397","1.03.04.08","LTU/BSY & Cold Trap Vacuum System","Open"]
["c","9242622","1.03.05.02.01","BPM's-Linac Standard (4ea)","Open"]
["c","9242624","1.03.05.02.03","BPMs-FFTB (37ea)","Open"]
["c","9242625","1.03.05.02.04","BPMs-BC1 & BC2 (2ea)","Open"]
["l","9242233","1.03.05.03","Toroids (9ea) Beam Charge","Open"]
["l","9242234","1.03.05.04","Stoppers TU Dump (2ea)","Open"]
["c","9242626","1.03.05.05","Profile Monitors (5ea)","Open"]
["c","9242627","1.03.05.07","Bunch Length Monitors (4ea)","Open"]
["c","9242628","1.03.05.08.01","Beam Loss Monitors (10 PIC)","Open"]
["c","9242629","1.03.05.08.02","Beam Loss Monitors (2 PLIC)","Open"]
["c","9242630","1.03.05.09","Single Beam Dump (1ea)","Open"]
["c","9242631","1.03.05.10","Electron Safety Beam Dump (1ea)","Open"]
["c","9242632","1.03.05.11","Protection Collimators (6ea)","Open"]
["c","9242633","1.03.05.12","Movable Collimators (7ea)","Open"]
["c","9242634","1.03.05.13","Safety Dump","Open"]
["l","9242236","1.03.06.04","X-Band Low Level System","Open"]
["l","9242237","1.03.06.05.01","X-Band HP Klystron","Open"]
["l","9242238","1.03.06.05.02","X-Band HP Modulator","Open"]
["c","9242641","1.03.06.07.09","RF Stability","Open"]
["c","9242646","1.03.07.06","Linac LTU System Installation & Alignment","Open"]
["c","9242647","1.03.07.07","Linac E-Dump System Installation & Alignment","Open"]
["c","9242929","1.03.07.10.04","2006 Linac Controls Install and Checkout Gallery to Linac B","Open"]
["c","9242930","1.03.07.10.05","2006 Linac Controls Install and Checkout L01 to BC1","Open"]
["c","9242931","1.03.07.20.01","Beamline Equip Removal L02,L03 and BC2","Open"]
["c","9242932","1.03.07.20.02","Beamline Equip Installation L02,L03 and BC2","Open"]
["c","9242933","1.03.07.20.03","2007 Linac Controls Install and Checkout","Open"]
["c","9242648","1.04.01.01.01","Undulator System Management-Technical","Open"]
["c","9242649","1.04.01.02.01","Undulator System M&S-General","Open"]
["c","9242650","1.04.01.02.02","Undulator System Travel","Open"]
["c","9242651","1.04.01.03","Undulator System Reviews and Workshops","Open"]
["c","9242652","1.04.02.01.03","Software Interface with SLAC","Open"]
["l","9242087","1.04.02.02.01","RFBPM@","Open"]
["l","9242088","1.04.02.02.06","X-Ray Imaging Detector (IMG)","Open"]
["l","9242089","1.04.02.02.07","Ion Chamber / Gas Jet","Open"]
["c","9242653","1.04.02.03.01","RFBPM","Open"]
["l","9242091","1.04.02.03.02","X-Ray Imaging and Beam Stretcher","Open"]
["c","9242654","1.04.02.03.03","Scanning Wire","Open"]
["c","9242655","1.04.02.04.03","Observation Station Video","Open"]
["c","9242656","1.04.02.05.01","Strongback Temperature Monitoring","Open"]
["c","9242657","1.04.02.06.01","Ion Pump Controller","Open"]
["c","9242658","1.04.02.06.02","RGA","Open"]
["c","9242659","1.04.02.07.01","Undulator Global MPS","Open"]
["l","9242095","1.04.02.07.02","MPS Interface with SLAC","Open"]
["c","9242660","1.04.02.07.03","Gamma Ray Detector","Open"]
["l","9242243","1.04.02.08","Power Supply Controls","Open"]
["c","9242661","1.04.03.01","Undulator Magnet & Support-Mgmt & Integration","Open"]
["c","9242664","1.04.03.04.01","Prod Undulator Assy-Vendor A","Open"]
["c","9242665","1.04.03.04.02","Prod Undulator Assy-Vendor B","Open"]
["c","9242666","1.04.03.04.03","Prod Support/Mover Fab/Assy","Open"]
["c","9242667","1.04.03.05.01","Quadrupole Magnets","Open"]
["c","9242668","1.04.03.05.03","Quadrupole Stages & Stands","Open"]
["c","9242669","1.04.03.05.04","Quadrupole Cables","Open"]
["c","9242670","1.04.03.06.02","Undulator Measurements","Open"]
["c","9242671","1.04.03.06.03","Focusing Magnet Measurement","Open"]
["c","9242672","1.04.03.08.02","Design","Open"]
["c","9242673","1.04.03.08.05","Thermometry","Open"]
["c","9242674","1.04.03.08.07","Earthquake Bracing","Open"]
["l","9242249","1.04.04.02.01","Prototype Chamber Weldment","Open"]
["c","9242675","1.04.04.02.02","Production Chamber Weldment","Open"]
["c","9242676","1.04.04.02.03","Prototype Aluminum Chamber","Open"]
["l","9242250","1.04.04.03.01","Prototype Bellows Module","Open"]
["c","9242677","1.04.04.03.02","Production Bellows Module","Open"]
["c","9242508","1.04.04.05","Short Diagnostic Break (SDB) Assembly","Open"]
["c","9242509","1.04.04.06","Long Diagnostic Break (LDB) Assembly","Open"]
["c","9242510","1.04.04.07","Entrance Section Assembly","Open"]
["c","9242511","1.04.04.08","Exit Section Assembly","Open"]
["c","9242512","1.04.04.09","Baking System","Open"]
["l","9242251","1.04.05.02.01","Low-Power Diagnostics Test Station","Open"]
["c","9242678","1.04.05.02.02","ULD Vacuum Chamber","Open"]
["c","9242679","1.04.05.02.03","Positioning Mechanism","Open"]
["l","9242252","1.04.05.02.04","Scanning Wire Assembly (LPD-SWA)","Open"]
["l","9242253","1.04.05.02.05","Optical Transition Radiation Imaging Assembly (LPD-    )","Open"]
["c","9242680","1.04.05.02.09","ULD Design & Integration","Open"]
["c","9242681","1.04.05.04.01","Prototype Construction and Testing","Open"]
["l","9242254","1.04.05.04.02","Bunch Length Monitor-Streak Camera (BLM)","Open"]
["c","9242682","1.04.05.04.03","Upstream corrector/separator","Open"]
["c","9242683","1.04.05.04.04","Optical Diffraction radiation imaging assembly","Open"]
["c","9242684","1.04.05.04.05","X-ray High Resolution monochromator assembly (EO","Open"]
["c","9242685","1.04.05.04.06","X-ray Imaging High Resolution detector assembly","Open"]
["c","9242686","1.04.05.04.07","EOU Design and Integration","Open"]
["l","9242255","1.04.05.05","RFBPM","Open"]
["l","9242256","1.04.05.07","Charge Monitor (CM)","Open"]
["c","9242513","1.04.05.08","Cherenkov Detector","Open"]
["c","9242514","1.04.05.09","Radiation Detection Monitor (RDM)","Open"]
["c","9242515","1.04.05.11","Supplemental Shielding","Open"]
["c","9242687","1.04.06.01.01","Undulator System","Open"]
["c","9242517","1.04.06.02","Control System Installation and Alignment","Open"]
["c","9242518","1.04.06.04","Vacuum System Installation and Alignment","Open"]
["c","9242519","1.04.06.05","Diagnostics System Installation and Alignment","Open"]
["c","9242688","1.05.01.01.01","XTOD Management-Technical","Open"]
["c","9242922","1.05.01.01.03","Management - Commission Coordinator - FY-06","Open"]
["l","9242923","1.05.02.01","Controls-EPICS","Open"]
["c","9242690","1.05.02.02","Slow Controls","Open"]
["c","9242691","1.05.02.03","Fast Controls","Open"]
["c","9242692","1.05.02.04","Femto Controls","Open"]
["c","9242693","1.05.03.02","Mech/Vac Front End","Open"]
["c","9242694","1.05.03.03.01","NEH Hutch 1","Open"]
["c","9242695","1.05.03.03.02","NEH Hutch 2","Open"]
["c","9242696","1.05.03.03.03","NEH Hutch 3","Open"]
["c","9242523","1.05.03.04","Mech/Vac Tunnel","Open"]
["c","9242697","1.05.03.05.01","FEH Hutch 1","Open"]
["c","9242698","1.05.03.05.02","FEH Hutch 2","Open"]
["c","9242699","1.05.03.05.03","FEH Hutch 3","Open"]
["c","9242700","1.05.04.02.02","Fixed Mask","Open"]
["c","9242701","1.05.04.02.03","Slit/Collimator","Open"]
["c","9242702","1.05.04.02.04","Flipper Mirror","Open"]
["c","9242703","1.05.04.02.05","Gas Attenuator","Open"]
["c","9242704","1.05.04.02.07","FEL Offset Mirrors","Open"]
["c","9242705","1.05.04.02.08","Solid Attenuator","Open"]
["c","9242706","1.05.04.04.02","System Monochrometer","Open"]
["c","9242707","1.05.04.04.03","Pulse Split & Delay","Open"]
["c","9242708","1.05.05.02.01","Wave Model","Open"]
["c","9242709","1.05.05.02.02","Monte Carlo Model","Open"]
["c","9242710","1.05.05.03.01","Direct Imager","Open"]
["c","9242711","1.05.05.03.02","Indirect Imager","Open"]
["c","9242712","1.05.05.03.05","Near & Far Hall Dl Tanks","Open"]
["c","9242713","1.05.05.03.06","Ion Pumped Diagnostic Tanks","Open"]
["c","9242714","1.05.05.04.01","Ion Chamber","Open"]
["c","9242715","1.05.05.04.02","Total Energy Measurement","Open"]
["c","9242716","1.05.05.04.04","Spectral Measurement","Open"]
["c","9242717","1.05.05.04.05","Spatial Coherence","Open"]
["c","9242718","1.05.05.04.06","Spatial Shape & Centroid Measurement","Open"]
["c","9242719","1.05.05.04.07","Divergence Measurement","Open"]
["c","9242530","1.05.06.01","Front End Enclosure Install","Open"]
["c","9242531","1.05.06.02","Near Hall Install","Open"]
["c","9242532","1.05.06.03","Tunnel Install","Open"]
["c","9242533","1.05.06.04","Far Hall Install","Open"]
["c","9242720","1.06.01.01","Management","Open"]
["c","9242536","1.06.02.01","Controls Management","Open"]
["c","9242730","1.06.02.06.02","Near Hall X-Ray MPS","Open"]
["c","9242731","1.06.02.06.03","Tunnel X-Ray MPS","Open"]
["c","9242732","1.06.02.06.04","Far Hall X-Ray MPS","Open"]
["c","9242733","1.06.02.07.01","Near Hall Laser PPS","Open"]
["c","9242734","1.06.02.07.02","Far Hall Laser PPS","Open"]
["c","9242735","1.06.02.08.01","Near Hall User Safeguards","Open"]
["c","9242736","1.06.02.08.02","Far Hall User Safeguards","Open"]
["c","9242790","1.06.02.09","XE-22050 Controls Management Dalesio Contract","Open"]
["c","9242401","1.06.02.10.03","Personnel Protection System","Open"]
["c","9242402","1.06.02.10.04","Laser PPS","Open"]
["c","9242545","1.06.03.01","Chamber Support Tables-Mech/Vac","Open"]
["c","9242737","1.06.03.02.01","Valves-Vacuum","Open"]
["c","9242739","1.06.03.02.03","Ion Pump-Vacuum","Open"]
["c","9242740","1.06.03.02.04","Turbo Pump-Vacuum","Open"]
["c","9242741","1.06.03.02.05","Gauges-Vacuum","Open"]
["c","9242742","1.06.03.03.01","AP Chamber 1","Open"]
["c","9242743","1.06.03.03.02","AP Chamber 2","Open"]
["c","9242744","1.06.04.01.01","AP Oscillator Laser & Pump","Open"]
["c","9242745","1.06.04.01.02","Far Hall Oscillator Laser & Pump","Open"]
["c","9242549","1.06.04.02","Laser Diagnostics","Open"]
["c","9242550","1.06.04.03","Laser Supplies & Optical Transport","Open"]
["c","9242551","1.06.04.04","Laser Timing","Open"]
["c","9242746","1.06.04.05.01","AP Laser Amplifier","Open"]
["c","9242747","1.06.04.05.02","Far Hall Laser Amplifier","Open"]
["c","9242553","1.06.05.01","Beam Imaging","Open"]
["c","9242554","1.06.05.02","2-D X-Ray Detector","Open"]
["c","9242555","1.06.05.03","Beam Intensity","Open"]
["c","9242556","1.06.05.04","Streak Camera","Open"]
["c","9242557","1.06.06.01","Front End Install","Open"]
["c","9242748","1.06.06.02.01","Near Hall Install Controls","Open"]
["c","9242749","1.06.06.02.02","Near Hall Install Mech/Vac","Open"]
["c","9242750","1.06.06.02.03","Near Hall Install Detectors","Open"]
["c","9242751","1.06.06.02.04","Near Hall Install Atomic Physics","Open"]
["c","9242559","1.06.06.03","Tunnel Install","Open"]
["c","9242752","1.06.06.04.01","Far Hall Install Controls","Open"]
["c","9242753","1.06.06.04.02","Far Hall Install Mech/Vac","Open"]
["c","9242754","1.06.06.04.03","Far Hall Install Laser","Open"]
["c","9242755","1.06.06.04.04","Far Hall Install Detectors","Open"]
["c","9242920","1.06.07.01","Samples","Open"]
["l","9242404","1.06.09.01","PPS Stoppers","Open"]
["l","9242405","1.06.09.02","PPS Shielding","Open"]
["l","9242338","1.09.01.01","CF Management & Integration","Open"]
["l","9242376","1.09.01.02","Cost Account Manager","Open"]
["l","9242257","1.09.01.03","Construction Management","Open"]
["c","9242756","1.09.01.04.05","Mechanical Design Title 3 Linac Facility","Open"]
["c","9242757","1.09.01.04.06","Mechanical Design Title 3 (Linac not included)","Open"]
["l","9242354","1.09.03.01.20","Project Closeout","Open"]
["c","9242937","1.09.03.03.01","BTH West Site Preparation","Open"]
["c","9242938","1.09.03.03.15","BTH West Mechanical","Open"]
["c","9242939","1.09.03.03.16","BTH West Electrical","Open"]
["c","9242758","1.09.03.04.01","Site Preparation","Open"]
["c","9242759","1.09.03.04.02","Sitework","Open"]
["l","9242390","1.09.03.04.05","Metals","Open"]
["c","9242760","1.09.03.04.15","Mechanical","Open"]
["c","9242761","1.09.03.04.16","Electrical","Open"]
["c","9242762","1.09.03.04.20","Project Close Out","Open"]
["l","9242379","1.09.03.05.01","RY Site Preparation","Open"]
["c","9242763","1.09.03.05.02","RY - Site Construction","Open"]
["c","9242788","1.09.03.05.05","RY - Metals","Open"]
["c","9242789","1.09.03.05.20","RY - Project Close Out","Open"]
["c","9242811","1.09.03.06.01","PPE General Requirements","Open"]
["c","9242812","1.09.03.06.11","Pre-Purchase Equipments","Open"]
["c","9242814","1.09.03.07.01","SW - Site Preparation/General Requirements","Open"]
["c","9242815","1.09.03.07.02","SW - Earthwork, Site Utilities & Survey","Open"]
["c","9242816","1.09.03.07.03","SW - Concrete","Open"]
["c","9242772","1.09.03.07.10","Project Close Out Undulator Hall","Open"]
["c","9242817","1.09.03.07.15","SW - Mechanical","Open"]
["c","9242818","1.09.03.07.16","SW - Electrical","Open"]
["c","9242819","1.09.03.07.17","SW - Others (include Div 4, and 6 through 14)","Open"]
["c","9242820","1.09.03.07.20","SW - Project Close Out","Open"]
["c","9242821","1.09.03.08.01","BTH - Site Preparation/General Requirements","Open"]
["c","9242822","1.09.03.08.02","BTH - Site Construction","Open"]
["c","9242823","1.09.03.08.03","BTH - Concrete","Open"]
["c","9242824","1.09.03.08.05","BTH - Metals","Open"]
["c","9242825","1.09.03.08.15","BTH - Mechanical","Open"]
["c","9242827","1.09.03.08.17","BTH - Others (include Div 4, and 6 through 14)","Open"]
["c","9242830","1.09.03.09.02","FEE - Site Construction","Open"]
["c","9242837","1.09.03.10.01","EBD - Site Preparation/General Requirements","Open"]
["c","9242838","1.09.03.10.02","EBD - Site Construction","Open"]
["c","9242842","1.09.03.10.16","EBD - Electrical","Open"]
["c","9242845","1.09.03.11.01","NEH - Site Preparation/General Requirements","Open"]
["c","9242846","1.09.03.11.02","NEH - Site Construction","Open"]
["c","9242847","1.09.03.11.03","NEH - Concrete","Open"]
["c","9242848","1.09.03.11.05","NEH - Metals","Open"]
["c","9242849","1.09.03.11.15","NEH - Mechanical","Open"]
["c","9242850","1.09.03.11.16","NEH - Electrical","Open"]
["c","9242851","1.09.03.11.17","NEH - Others (include Div 4, and 6 through 14)","Open"]
["c","9242853","1.09.03.12.01","UH - Site Preparation/General Requirements","Open"]
["c","9242854","1.09.03.12.02","UH - Site Construction","Open"]
["c","9242856","1.09.03.12.15","UH - Mechanical","Open"]
["c","9242857","1.09.03.12.16","UH - Electrical","Open"]
["c","9242858","1.09.03.12.17","UH - Others (include Div 4, and 6 through 14)","Open"]
["c","9242859","1.09.03.12.19","UH - Tunnel Construction","Open"]
["c","9242870","1.09.03.14.02","FEH - Site Construction","Open"]
["c","9242871","1.09.03.14.05","FEH - Metals","Open"]
["c","9242872","1.09.03.14.15","FEH - Mechanical","Open"]
["c","9242873","1.09.03.14.16","FEH - Electrical","Open"]
["c","9242874","1.09.03.14.17","FEH - Others (include Div 4, and 6 through 14)","Open"]
["c","9242875","1.09.03.14.18","FEH - Access Tunnel","Open"]
["c","9242876","1.09.03.14.19","FEH - Tunnel Construction","Open"]
["c","9242878","1.09.03.15.03","SB BTH - Concrete","Open"]
["c","9242880","1.09.03.15.15","SB BTH - Mechanical","Open"]
["c","9242881","1.09.03.15.16","SB BTH - Electrical","Open"]
["c","9242882","1.09.03.15.17","SB BTH - Others (includes Div 4, 6 through 14)","Open"]
["c","9242885","1.09.03.16.03","SB UH - Concrete","Open"]
["c","9242886","1.09.03.16.05","SB UH - Metals","Open"]
["c","9242887","1.09.03.16.15","SB UH - Mechanical","Open"]
["c","9242888","1.09.03.16.16","SB UH - Electrical","Open"]
["c","9242889","1.09.03.16.17","SB UH - Others (includes Div 4, 6 through 14)","Open"]
["c","9242892","1.09.03.17.03","SB FEH - Concrete","Open"]
["c","9242893","1.09.03.17.05","SB FEH - Metals","Open"]
["c","9242894","1.09.03.17.15","SB FEH - Mechanical","Open"]
["c","9242895","1.09.03.17.16","SB FEH - Electrical","Open"]
["c","9242896","1.09.03.17.17","SB FEH - Others (includes Div 4, 6 through 14)","Open"]
["c","9242899","1.09.03.18.02","CUP - Site Construction","Open"]
["c","9242903","1.09.03.18.16","CUP - Electrical","Open"]
["c","9242906","1.09.03.19.01","ED&I-SLAC Space Renovation for LCLS Ops","Open"]
["c","9242907","1.09.03.19.02","Construction-SLAC Space Renovation for LCLS Ops","Open"]
["o","9682321","2.01.01.01","LCLS Commissioning Management (Pre-Ops)","Open"]
["o","9682322","2.01.01.02","Injector Physics (Pre-Ops)","Open"]
["o","9682323","2.01.01.03","Linac Physics (Pre-Ops)","Open"]
["o","9682324","2.01.01.04","Undulator Physics (Pre-Ops)","Open"]
["o","9682325","2.01.01.05","X-Ray Transport Physics (Pre-Ops)","Open"]
["o","9682326","2.01.01.06","X-Ray Physics Commissioning","Open"]
["o","9682327","2.01.01.07","Conventional Facilities Physics (Pre-Ops)","Open"]
["o","9682328","2.01.01.08","Consulting Physics-Collaboration (Pre-Ops)","Open"]
["o","9682329","2.01.01.09","Consulting Physics-SLAC (Pre-Ops)","Open"]
["o","9682330","2.01.01.10","Global Controls Physics Liaison (Pre-Ops)","Open"]
["o","9682342","2.01.01.11.11","Global Controls Commissioning (Pre-Ops)","Open"]
["o","9682343","2.01.01.11.12","Global Controls Management (Pre-Ops)","Open"]
["o","9682009","2.01.03.01","SLAC Project Office-General (Pre-Ops)","Open"]
["o","9682014","2.01.03.02","SLAC Project Support (Pre-Ops)","Open"]
["o","9682015","2.01.03.03","Project Mgmt, Planning & Admin-M&S (PREOPS)","Open"]
["o","9682155","2.02.02.01","Personnel Protection System (PPS) (Pre-Ops)","Open"]
["o","9682156","2.02.02.02","Beam Containment Subsystem (BCS) (Pre-Ops)","Open"]
["o","9682157","2.02.02.03","Machine Protection Subsystem (MPS) (Pre-Ops)","Open"]
["o","9682158","2.02.02.04","Power Conv (beamline pwr supp) (Pre-Ops)","Open"]
["o","9682018","2.02.02.05.01","LLRF Controls (Pre-Ops)","Open"]
["o","9682020","2.02.02.06.01","Controls - Wire Scanners (Pre-Ops)","Open"]
["o","9682026","2.02.02.06.02","Controls - BPM Processor Module (Pre-Ops)","Open"]
["o","9682021","2.02.02.06.03","Controls - Toroids (Pre-Ops)","Open"]
["o","9682024","2.02.02.06.05","Controls - Profile Monitors (Pre-Ops)","Open"]
["o","9682025","2.02.02.06.12","Controls - Movable Collimator (Pre-Ops)","Open"]
["o","9682022","2.02.02.06.14","Controls - Faraday Cup (Pre-Ops)","Open"]
["o","9682023","2.02.02.06.15","Controls - Tune-Up Dump (Pre-Ops)","Open"]
["o","9682027","2.02.02.06.16","Cherenkov Commissioning Support (Pre-Ops)","Open"]
["o","9682162","2.02.02.08","Timing Controls (Pre-Ops)","Open"]
["o","9682163","2.02.02.09","Vacuum Controls (Pre-Ops)","Open"]
["r","9681034","2.02.03.01","Drive Laser Prototyping","Open"]
["o","9682035","2.02.03.02","Drive Laser System (Pre-Ops)","Open"]
["r","9683035","2.02.03.02","Drive Laser System (R&D)","Open"]
["o","9682036","2.02.03.03","Drive Laser Diagnostics (Pre-Ops)","Open"]
["o","9682143","2.02.04.02.02","CP Load Lock (Pre-Ops)","Open"]
["r","9683136","2.02.04.05.02","RF Waveguide Supports (R&D)","Open"]
["o","9682373","2.02.08.01","Heater Integration","Open"]
["o","9682377","2.02.08.02","Heater Laser & Optics (Pre-Ops)","Open"]
["o","9682375","2.02.08.03.01","Heater Dipoles (Pre-Ops)","Open"]
["r","9683375","2.02.08.03.01","Heater Dipoles (R&D)","Open"]
["o","9682376","2.02.08.03.02","Heater Undulator (Pre-Ops)","Open"]
["r","9683377","2.02.08.04","Heater Vacuum (R&D)","Open"]
["o","9682378","2.02.08.05","Heater Diagnostics (Pre-Ops)","Open"]
["o","9682357","2.02.17.02","Drive Laser Commissioning (Pre-Ops)","Open"]
["o","9682365","2.02.17.10","Injector System Commissioning","Open"]
["o","9682169","2.03.02.04.01","Spare Power Supply (Dipole Type) (Pre-Ops)","Open"]
["o","9682170","2.03.02.04.02","Spare Power Supply (Quad Type) (Pre-Ops)","Open"]
["o","9682171","2.03.02.04.03","Spare Power Supply ( Trim Type) (Pre-Ops)","Open"]
["o","9682193","2.03.04.01","Linac Vacuum Subsystem Operations Equip (Pre-Ops)","Open"]
["r","9681206","2.03.05.07","Bunch Length Monitors","Open"]
["o","9682389","2.03.07.10","Linac System Commissioning","Open"]
["o","9682240","2.04.03.06","Undulator Magnetic Measurement Facility SLAC (Pre-Ops)","Open"]
["o","9682371","2.04.06.01","Undulator System Commissioning (Pre-Ops)","Open"]
["r","9683309","2.06.05.02","2-D X-Ray Detector (R&D)","Open"]
["o","9682422","2.09.03.05","RSY-CLOC Commissioning (Pre-Ops)","Open"]

{"sheet":"Detailed Cost Estimate","index":5,"n_rows":10183,"n_cols":49,"rows_kept":2250,"cut":true,"hidden":false,"merged":[[0,30,0,31],[0,32,0,33],[0,34,0,35],[0,36,0,37],[1,0,1,5],[0,0,0,5],[0,17,0,18],[0,19,0,21],[0,23,0,24],[0,25,0,27],[0,28,0,29]],"bounds":{"rows_first":1000,"rows_last":250,"rows_between":1000,"halvings":1},"flags":["formulas_cached_only"]}
["WBS Level",{"$nulls":5},"P3","C/A","W/P","Charge","LCLA  DCE April-2007","Early","Early","OBS","Fund","Res","Units","Budgeted Quantity",null,"Fully Burdened and Escalated Cost",null,null,null,"Work Rem. Bud. Qtty",null,"Work Rem. Full Burd and Escltd Cost",null,null,"FY05",null,"FY06",null,"FY07",null,"FY08",null,"FY09",null,"Contingency","Contingency","Design","Judgement","Basis","Program",null,"Tech"]
[{"$nulls":6},"ID","Number","Number","Number","Description","Start","Finish",null,"Type","Code",null,"Hours","$$","Labor","M&S","Total (No Conting)",null,"Hours","$$","Labor","M&S","Total","BAC","% of Wrk Rem.","BAC","% of Wrk Rem.","BAC","% of Wrk Rem.","BAC","% of Wrk Rem.","BAC","% of Wrk Rem.","%","$","Maturity","Factor","of Estimate","Phase","CAM","Lead",null,null,"CAM"]
["1","2","3","4","5","6"]
[{"$nulls":17},672758,169680973,71912432.05273347,174090128.47551188,219207687.88913393,null,456298.41,131685593.69799998,49230759.90709565,135249721.6023533,184480481.50944945,0,null,3149290.61951088,null,87581888.04738301,null,77080590.8965329,null,16668711.94602209,null,null,28069085.003947824]
["1","  ","  ","  ","  ","  ",{"$nulls":4},"LCLS PROJECT - PED & CONSTRUCTION                           ",{"$nulls":6},451335,148815228,45960883.92772608,151933219.1602955,172918816.9532689,null,278288.31,113009519.75799999,28288231.694933385,115547636.94384706,143835868.63878024,0,null,2660240.5324599366,null,79144339.76504537,null,60444124.28022454,null,1587164.0610505617,null,null,27935354.192327634]
["1","01","  ","  ","  ","  ",{"$nulls":4},"LCLS PROJECT MGMT, PLANNING & ADMN (TEC)                    ",{"$nulls":6},62978,3773747,6182863.061427882,4028883.475486999,9721735.804770928,null,27182.32,1554376.92,2711235.0164333917,1694222.0037139512,4405457.020147345,0,null,34339.67032452473,null,2229033.0122736376,null,1733158.8382255791,null,408925.499323601,null,null,1014319.5138636085]
["1","01","01","  ","  ","  ",{"$nulls":4},"Environment, Safety & Health                                ",{"$nulls":6},12447,495350,1209600.6283274726,503403.0404287111,1647648.9448450727,null,5817.72,224200,570331.288218945,230033.7177336,800365.005952545,0,null,0,null,343925.50311132654,null,335026.0874078946,null,121413.41543332388,null,null,190862.25783294978]
["1","01","01","01","  ","  ",{"$nulls":4},"Radiation Physics                                           ",{"$nulls":6},5636,0,541556.567844198,0,541556.567844198,null,2548.72,0,247950.85610533852,0,247950.85610533852,0,null,0,null,143168.51354053244,null,83854.88324674717,null,20927.459318058904,null,null,86782.79963686847]
["1","01","01","01","","","PM110_0012","1.01.01.01","CBA10101","9242570","Radiation Physics- CONST FY06 Remainder","2006-06-01","2006-09-29","S","C","SL_PHH1","Hrs",1190,null,111391.23995999998,null,111391.23995999998,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.15,1.2,4,1,"1A"]
["1","01","01","01","","","PM110_0015","1.01.01.01","CK10101","9242570","Radiation Physics- CONST FY07","2006-10-02","2007-09-28","S","C","SL_PHH1","Hrs",3388,null,325382.98531939194,null,325382.98531939194,null,1490.72,null,143168.51354053244,null,143168.51354053244,{"$nulls":4},143168.51354053244,1,{"$nulls":4},0.35,50108.979739186354,1.15,1.2,4,1,"1A"]
["1","01","01","01","","","PM110_0020","1.01.01.01","CK10101","9242570","Radiation Physics- CONST FY08","2007-10-01","2008-09-30","S","C","SL_PHH1","Hrs",851,null,83854.88324674717,null,83854.88324674717,null,851,null,83854.88324674717,null,83854.88324674717,{"$nulls":6},83854.88324674717,1,null,null,0.35,29349.209136361507,1.15,1.2,4,1,"1A"]
["1","01","01","01","","","PM110_0025","1.01.01.01","CK10101","9242570","Radiation Physics- CONST FY09","2008-10-01","2009-03-30","S","C","SL_PHH1","Hrs",207,null,20927.459318058904,null,20927.459318058904,null,207,null,20927.459318058904,null,20927.459318058904,{"$nulls":8},20927.459318058904,1,0.35,7324.610761320616,1.15,1.2,4,1,"1A"]
["1","01","01","02","  ","  ",{"$nulls":4},"ESH Management & Coordination                               ",{"$nulls":6},6811,405350,668044.0604832744,405350,1073394.0604832745,null,3269,166000,322380.43211360654,166000,488380.4321136065,0,null,0,null,177261.562900528,null,227611.22961541355,null,83507.639597665,null,null,97676.08642272132]
["1","01","01","02","","","PM120_0027","1.01.01.02","","9242571","ESH Management & Coordination - FY07","2006-10-02","2006-11-30","S","C","SL_PHH1","Hrs",1694,null,162691.49265969597,null,162691.49265969597,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,4,1,"1A"]
["1","01","01","02","","","PM120_0027","1.01.01.02","","9242571","ESH Management & Coordination - FY07","2006-10-02","2006-11-30","S","C","SL_MSPY1","$$",null,145350,null,145350,145350,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,4,1,"1A"]
["1","01","01","02","","","PM120_0025","1.01.01.02","CBA10102","9242571","ESH Management & Coordination - FY06 Remainder","2006-06-01","2006-09-29","S","C","SL_PHH1","Hrs",595,null,55695.61997999999,null,55695.61997999999,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,4,1,"1A"]
["1","01","01","02","","","PM120_0025","1.01.01.02","CBA10102","9242571","ESH Management & Coordination - FY06 Remainder","2006-06-01","2006-09-29","S","C","AN_PM1","Hrs",595,null,64082.29957290001,null,64082.29957290001,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,4,1,"1A"]
["1","01","01","02","","","PM120_0028","1.01.01.02","CCA10102","9242571","ESH Management & Coordination - FY08","2007-10-01","2008-09-30","S","C","SL_PHH1","Hrs",1701,null,167611.22961541355,null,167611.22961541355,null,1701,null,167611.22961541355,null,167611.22961541355,{"$nulls":6},167611.22961541355,1,null,null,0.2,33522.245923082715,1.1,1.1,4,1,"1A"]
["1","01","01","02","","","PM120_0029","1.01.01.02","CCA10102","9242571","ESH Management & Coordination - FY09","2008-10-01","2009-03-30","S","C","SL_PHH1","Hrs",826,null,83507.639597665,null,83507.639597665,null,826,null,83507.639597665,null,83507.639597665,{"$nulls":8},83507.639597665,1,0.2,16701.527919533,1.1,1.1,4,1,"1A"]
["1","01","01","02","","","PM210_0127","1.01.01.02","CCA10102","9242571","ESH Management & Coordination - FY07 (Hislop)","2006-12-01","2007-09-28","S","C","SL_MSPY1","$$",null,200000,null,200000,200000,null,null,106000,null,106000,106000,{"$nulls":4},106000,1,{"$nulls":4},0.2,21200,1.1,1.1,4,1,"1A"]
["1","01","01","02","","","PM210_0128","1.01.01.02","CCA10102","9242571","ESH Management & Coordination - FY07","2006-12-01","2007-09-28","S","C","SL_PHH1","Hrs",1400,null,134455.77905759998,null,134455.77905759998,null,742,null,71261.56290052799,null,71261.56290052799,{"$nulls":4},71261.56290052799,1,{"$nulls":4},0.2,14252.3125801056,1.1,1.1,4,1,"1A"]
["1","01","01","02","","","PM210_0129","1.01.01.02","CCA10102","9242571","ESH Management & Coordination - FY08 (Hislop)","2007-10-01","2008-01-31","S","C","SL_MSPY1","$$",null,60000,null,60000,60000,null,null,60000,null,60000,60000,{"$nulls":6},60000,1,null,null,0.2,12000,1.1,1.1,4,1,"1A"]
["1","01","01","03","  ","  ",{"$nulls":4},"Seismic & Engineering Support                               ",{"$nulls":6},0,90000,0,98053.0404287111,32698.316517599997,null,0,58200,0,64033.717733599995,64033.717733599995,0,null,0,null,23495.42667026612,null,23559.97454573388,null,16978.316517599997,null,null,6403.37177336]
["1","01","01","03","","","PM120_0032","1.01.01.03","CBA10103","9242572","Seismic & Engineering - CONST FY06 Remainder","2006-06-01","2006-09-29","S","C","SL_MSPS1","$$",null,15000,null,15720,15720,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,4,1,"1A"]
["1","01","01","03","","","PM120_0033","1.01.01.03","CK10103","9242572","Seismic & Engineering - CONST FY07-08","2006-10-02","2008-09-30","S","C","SL_MSPS1","$$",null,60000,null,65354.72391111111,null,null,null,43200,null,47055.401216,47055.401216,{"$nulls":4},23495.42667026612,0.5,23559.97454573388,0.5,null,null,0.1,4705.5401216,1,1.1,4,1,"1A"]
["1","01","01","03","","","PM120_0034","1.01.01.03","CK10103","9242572","Seismic & Engineering - CONST FY09","2008-10-01","2009-03-30","S","C","SL_MSPS1","$$",null,15000,null,16978.316517599997,16978.316517599997,null,null,15000,null,16978.316517599997,16978.316517599997,{"$nulls":8},16978.316517599997,1,0.1,1697.8316517599997,1,1.1,4,1,"1A"]
["1","01","02","  ","  ","  ",{"$nulls":4},"Project Management                                          ",{"$nulls":6},21712,2233137,2223611.4813603275,2397458.626828298,4196414.099955783,null,10112,906276.92,1049899.5702390794,995515.7974303612,2045415.3676694399,0,null,34100.99754864474,null,972543.5150298647,null,836640.7127267522,null,202130.14236417913,null,null,329107.8114221002]
["1","01","02","01","  ","  ",{"$nulls":4},"Project Management Office                                   ",{"$nulls":6},21712,2233137,2223611.4813603275,2397458.626828298,4196414.099955783,null,10112,906276.92,1049899.5702390794,995515.7974303612,2045415.3676694399,0,null,34100.99754864474,null,972543.5150298647,null,836640.7127267522,null,202130.14236417913,null,null,329107.8114221002]
["1","01","02","01","01","  ",{"$nulls":4},"Project Office - General                                    ",{"$nulls":6},18279,0,2004720.6341672163,0,2004720.6341672163,null,8521.84,0,946930.6139978791,0,946930.6139978791,0,null,0,null,423601.7416257166,null,421433.59420504124,null,101895.27816712155,null,null,94693.06139978793]
["1","01","02","01","01","","PM211_0012","1.01.02.01.01","CBA1020101","9242335","Project Director  - FY06 Remainder","2006-06-01","2006-09-29","S","C","SL_PM1","Hrs",446,null,70676.34524279999,null,70676.34524279999,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0022","1.01.02.01.01","CBA1020101","9242335","Senior Project Mgrs  - FY06 Remainder","2006-06-01","2006-09-29","S","C","SL_PM1","Hrs",1339,null,212187.50287019997,null,212187.50287019997,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0032","1.01.02.01.01","CBA1020101","9242335","Budget/Finance Officer  - FY06 Remainder","2006-06-01","2006-09-29","S","C","SL_FA1","Hrs",446,null,39077.773574399995,null,39077.773574399995,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0053","1.01.02.01.01","CBA1020101","9242335","Administrative Support  - FY06 Remainder","2006-06-01","2006-09-29","S","C","SL_ADMN1","Hrs",1785,null,102055.23347480998,null,102055.23347480998,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0150","1.01.02.01.01","CBA1020101","9242335","E-Beam Systems Manager - FY06 Remainder","2006-06-01","2006-09-29","S","C","SL_TSM1","Hrs",446,null,46159.77492719999,null,46159.77492719999,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0W53","1.01.02.01.01","CBA1020101","9242335","Finance Administrative Support  - FY06 Remainder","2006-06-01","2006-09-29","S","C","SL_ADMN1","Hrs",41,null,2344.1258109059995,null,2344.1258109059995,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_160","1.01.02.01.01","CBA1020101","9242335","Photon System Manager - FY06 Remainder","2006-06-01","2006-09-29","S","C","SL_TSM1","Hrs",446,null,46159.77492719999,null,46159.77492719999,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0013","1.01.02.01.01","CK1020101","9242335","Project Director  - FY07","2006-10-02","2007-09-28","S","C","SL_PM1","Hrs",847,null,137711.43250131956,null,137711.43250131956,null,372.68,null,60593.03030058061,null,60593.03030058061,{"$nulls":4},60593.03030058061,1,{"$nulls":4},0.1,6059.303030058061,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0014","1.01.02.01.01","CK1020101","9242335","Project Director  - FY08","2007-10-01","2008-09-30","S","C","SL_PM1","Hrs",340,null,56716.9493668953,null,56716.9493668953,null,340,null,56716.9493668953,null,56716.9493668953,{"$nulls":6},56716.9493668953,1,null,null,0.1,5671.694936689531,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0015","1.01.02.01.01","CK1020101","9242335","Project Director- FY09","2008-10-01","2009-03-30","S","C","SL_PM1","Hrs",83,null,14205.594094334825,null,14205.594094334825,null,83,null,14205.594094334825,null,14205.594094334825,{"$nulls":8},14205.594094334825,1,0.1,1420.5594094334826,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0023","1.01.02.01.01","CK1020101","9242335","Senior Project Mgrs - FY07","2006-10-02","2007-09-28","S","C","SL_PM1","Hrs",2541,null,413134.2975039587,null,413134.2975039587,null,1118.04,null,181779.09090174182,null,181779.09090174182,{"$nulls":4},181779.09090174182,1,{"$nulls":4},0.1,18177.909090174184,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0024","1.01.02.01.01","CK1020101","9242335","Senior Project Mgrs - FY08","2007-10-01","2008-09-30","S","C","SL_PM1","Hrs",1021,null,170317.66265764736,null,170317.66265764736,null,1021,null,170317.66265764736,null,170317.66265764736,{"$nulls":6},170317.66265764736,1,null,null,0.1,17031.766265764738,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0026","1.01.02.01.01","CK1020101","9242335","Senior Project Mgrs - FY09","2008-10-01","2009-03-30","S","C","SL_PM1","Hrs",248,null,42445.63054692816,null,42445.63054692816,null,248,null,42445.63054692816,null,42445.63054692816,{"$nulls":8},42445.63054692816,1,0.1,4244.563054692816,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0033","1.01.02.01.01","CK1020101","9242335","Budget/Finance Officer  - FY07","2006-10-02","2007-09-28","S","C","SL_FA1","Hrs",847,null,76142.2532447808,null,76142.2532447808,null,372.68,null,33502.59142770355,null,33502.59142770355,{"$nulls":4},33502.59142770355,1,{"$nulls":4},0.1,3350.259142770355,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0034","1.01.02.01.01","CK1020101","9242335","Budget/Finance Officer  - FY08","2007-10-01","2008-09-30","S","C","SL_FA1","Hrs",340,null,31359.461182891777,null,31359.461182891777,null,340,null,31359.461182891777,null,31359.461182891777,{"$nulls":6},31359.461182891777,1,null,null,0.1,3135.946118289178,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0035","1.01.02.01.01","CK1020101","9242335","Budget/Finance Officer - FY09","2008-10-01","2009-03-30","S","C","SL_FA1","Hrs",83,null,7854.438250891336,null,7854.438250891336,null,83,null,7854.438250891336,null,7854.438250891336,{"$nulls":8},7854.438250891336,1,0.1,785.4438250891336,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0054","1.01.02.01.01","CK1020101","9242335","Administrative Support  - FY07","2006-10-02","2007-09-28","S","C","SL_ADMN1","Hrs",2541,null,149055.87076427956,null,149055.87076427956,null,1118.04,null,65584.583136283,null,65584.583136283,{"$nulls":4},65584.583136283,1,{"$nulls":4},0.1,6558.458313628301,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0056","1.01.02.01.01","CK1020101","9242335","Administrative Support  - FY08","2007-10-01","2008-09-30","S","C","SL_ADMN1","Hrs",1361,null,81912.44830895287,null,81912.44830895287,null,1361,null,81912.44830895287,null,81912.44830895287,{"$nulls":6},81912.44830895287,1,null,null,0.1,8191.244830895287,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0057","1.01.02.01.01","CK1020101","9242335","Administrative Support  - FY09","2008-10-01","2009-03-30","S","C","SL_ADMN1","Hrs",248,null,15314.076946735837,null,15314.076946735837,null,248,null,15314.076946735837,null,15314.076946735837,{"$nulls":8},15314.076946735837,1,0.1,1531.4076946735838,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0151","1.01.02.01.01","CK1020101","9242335","E-Beam Systems Manager - FY07","2006-10-02","2007-09-28","S","C","SL_TSM1","Hrs",847,null,89941.38997037038,null,89941.38997037038,null,372.68,null,39574.21158696297,null,39574.21158696297,{"$nulls":4},39574.21158696297,1,{"$nulls":4},0.1,3957.4211586962974,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0152","1.01.02.01.01","CK1020101","9242335","E-Beam Systems Manager - FY08","2007-10-01","2008-09-30","S","C","SL_TSM1","Hrs",340,null,37042.68533325148,null,37042.68533325148,null,340,null,37042.68533325148,null,37042.68533325148,{"$nulls":6},37042.68533325148,1,null,null,0.1,3704.2685333251484,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0153","1.01.02.01.01","CK1020101","9242335","E-Beam Systems Manager - FY09","2008-10-01","2009-03-30","S","C","SL_TSM1","Hrs",83,null,9277.885321446469,null,9277.885321446469,null,83,null,9277.885321446469,null,9277.885321446469,{"$nulls":8},9277.885321446469,1,0.1,927.788532144647,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0W54","1.01.02.01.01","CK1020101","9242335","Finance Administrative Support  - FY07","2006-10-02","2007-09-28","S","C","SL_ADMN1","Hrs",116,null,6804.597012458256,null,6804.597012458256,null,51.04,null,2994.022685481633,null,2994.022685481633,{"$nulls":4},2994.022685481633,1,{"$nulls":4},0.1,299.4022685481633,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0W55","1.01.02.01.01","CK1020101","9242335","Finance Administrative Support  - FY08","2007-10-01","2008-09-30","S","C","SL_ADMN1","Hrs",117,null,7041.702022150981,null,7041.702022150981,null,117,null,7041.702022150981,null,7041.702022150981,{"$nulls":6},7041.702022150981,1,null,null,0.1,704.1702022150981,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_0W57","1.01.02.01.01","CK1020101","9242335","Finance Administrative Support  - FY09","2008-10-01","2009-03-30","S","C","SL_ADMN1","Hrs",57,null,3519.7676853384787,null,3519.7676853384787,null,57,null,3519.7676853384787,null,3519.7676853384787,{"$nulls":8},3519.7676853384787,1,0.1,351.9767685338479,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_161","1.01.02.01.01","CK1020101","9242335","Photon System Manager - FY07","2006-10-02","2007-09-28","S","C","SL_TSM1","Hrs",847,null,89941.38997037038,null,89941.38997037038,null,372.68,null,39574.21158696297,null,39574.21158696297,{"$nulls":4},39574.21158696297,1,{"$nulls":4},0.1,3957.4211586962974,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_162","1.01.02.01.01","CK1020101","9242335","Photon System Manager - FY08","2007-10-01","2008-09-30","S","C","SL_TSM1","Hrs",340,null,37042.68533325148,null,37042.68533325148,null,340,null,37042.68533325148,null,37042.68533325148,{"$nulls":6},37042.68533325148,1,null,null,0.1,3704.2685333251484,1,1.1,4,1,"1A"]
["1","01","02","01","01","","PM211_163","1.01.02.01.01","CK1020101","9242335","Photon System Manager - FY09","2008-10-01","2009-03-30","S","C","SL_TSM1","Hrs",83,null,9277.885321446469,null,9277.885321446469,null,83,null,9277.885321446469,null,9277.885321446469,{"$nulls":8},9277.885321446469,1,0.1,927.788532144647,1,1.1,4,1,"1A"]
["1","01","02","01","02","  ",{"$nulls":4},"Project Support                                             ",{"$nulls":6},3433,1343661,218890.84719311073,1411447.6181110006,1230338.4653041114,null,1590.16,473513.8,102968.95624120018,503883.42032540066,606852.3765666008,0,null,32264.462809917353,null,358791.6497593981,null,191988.62211480876,null,23807.641882476637,null,null,121370.47531332017]
["1","01","02","01","02","","PM212_0044","1.01.02.01.02","CBA1020102","9242336","Additional Procurement Consulting Serv Rem","2006-06-01","2007-09-28","S","C","SL_MSPY1","$$",null,400000,null,400000,null,null,null,128000,null,128000,128000,null,null,32264.462809917353,0.25,95735.53719008264,0.75,{"$nulls":4},0.2,25600,1.1,1.1,4,1,"1A"]
["1","01","02","01","02","","PM212_0052","1.01.02.01.02","CBA1020102","9242336","QA/QC Support - FY06 Remainder","2006-06-01","2006-09-29","S","C","SL_QAO1","Hrs",446,null,30026.6716068,null,30026.6716068,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,4,1,"1A"]
["1","01","02","01","02","","PM212_0072","1.01.02.01.02","CBA1020102","9242336","Computing Mgr Support - FY06 Remainder","2006-06-01","2006-09-29","S","C","SL_CRM1","Hrs",340,null,19926.726732,null,19926.726732,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,4,1,"1A"]
["1","01","02","01","02","","PM212_0090","1.01.02.01.02","CBA1020102","9242336","Computing Res Support - FY06 Remainder","2006-06-01","2006-09-29","S","C","SL_CRA1","Hrs",111,null,5718.8580174,null,5718.8580174,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,4,1,"1A"]
["1","01","02","01","02","","PM212_0E17","1.01.02.01.02","CBA1020102","9242336","PMCS Support - Maintenance - FY06 Rem","2006-06-01","2006-09-29","S","C","SL_MSPS1","$$",null,278640,null,292014.72,292014.72,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,2,1,"1A"]
["1","01","02","01","02","","PM212_0022","1.01.02.01.02","CK1020102","9242336","AWARD:  PMCS Support-FY07","2006-10-03","2006-10-03","S","C","SL_AW1","$$",null,520128,null,559266.591744,559266.591744,null,null,0,null,0,0,{"$nulls":14},6,1,"1A"]
["1","01","02","01","02","","PM212_0023","1.01.02.01.02","CK1020102","9242336","AWARD:  PMCS Support-FY08","2007-10-02","2007-10-02","S","C","SL_AW1","$$",null,133747,null,147550.285306656,147550.285306656,null,null,133747,null,147550.285306656,147550.285306656,{"$nulls":6},147550.285306656,1,{"$nulls":6},4,1,"1A"]
["1","01","02","01","02","","PM212_0024","1.01.02.01.02","CK1020102","9242336","AWARD:  PMCS Support-FY09","2008-10-01","2008-10-01","S","C","SL_AW1","$$",null,11146,null,12616.02106034464,12616.02106034464,null,null,11146,null,12616.02106034464,12616.02106034464,{"$nulls":8},12616.02106034464,1,{"$nulls":4},4,1,"1A"]
["1","01","02","01","02","","PM212_0053","1.01.02.01.02","CK1020102","9242336","QA/QC Support - FY07","2006-10-02","2007-09-28","S","C","SL_QAO1","Hrs",847,null,58506.3637064676,null,58506.3637064676,null,372.68,null,25742.800030845745,null,25742.800030845745,{"$nulls":4},25742.800030845745,1,{"$nulls":4},0.2,5148.560006169149,1.1,1.1,4,1,"1A"]
["1","01","02","01","02","","PM212_0054","1.01.02.01.02","CK1020102","9242336","QA/QC Support - FY08","2007-10-01","2008-09-30","S","C","SL_QAO1","Hrs",340,null,24096.05657067787,null,24096.05657067787,null,340,null,24096.05657067787,null,24096.05657067787,{"$nulls":6},24096.05657067787,1,null,null,0.2,4819.211314135574,1.1,1.1,4,1,"1A"]
["1","01","02","01","02","","PM212_0055","1.01.02.01.02","CK1020102","9242336","QA/QC Support - FY09","2008-10-01","2009-03-30","S","C","SL_QAO1","Hrs",83,null,6035.2117442510635,null,6035.2117442510635,null,83,null,6035.2117442510635,null,6035.2117442510635,{"$nulls":8},6035.2117442510635,1,0.2,1207.0423488502126,1.1,1.1,4,1,"1A"]
["1","01","02","01","02","","PM212_0073","1.01.02.01.02","CK1020102","9242336","Computing Mgr Support - FY07","2006-10-02","2007-09-28","S","C","SL_CRM1","Hrs",629,null,37822.92001000919,null,37822.92001000919,null,276.76,null,16642.084804404043,null,16642.084804404043,{"$nulls":4},16642.084804404043,1,{"$nulls":4},0.2,3328.416960880809,1.1,1.1,4,1,"1A"]
["1","01","02","01","02","","PM212_0074","1.01.02.01.02","CK1020102","9242336","Computing Mgr Support - FY08","2007-10-01","2008-09-30","S","C","SL_CRM1","Hrs",255,null,15732.29024200112,null,15732.29024200112,null,255,null,15732.29024200112,null,15732.29024200112,{"$nulls":6},15732.29024200112,1,null,null,0.2,3146.458048400224,1.1,1.1,4,1,"1A"]
["1","01","02","01","02","","PM212_0075","1.01.02.01.02","CK1020102","9242336","Computing Mgr Support - FY09","2008-10-01","2009-03-30","S","C","SL_CRM1","Hrs",63,null,3987.8579624651757,null,3987.8579624651757,null,63,null,3987.8579624651757,null,3987.8579624651757,{"$nulls":8},3987.8579624651757,1,0.2,797.5715924930352,1.1,1.1,4,1,"1A"]
["1","01","02","01","02","","PM212_0091","1.01.02.01.02","CK1020102","9242336","Computing Res Support - FY07","2006-10-02","2007-09-28","S","C","SL_CRA1","Hrs",213,null,11259.349490149198,null,11259.349490149198,null,93.72,null,4954.113775665646,null,4954.113775665646,{"$nulls":4},4954.113775665646,1,{"$nulls":4},0.2,990.8227551331292,1.1,1.1,4,1,"1A"]
["1","01","02","01","02","","PM212_0092","1.01.02.01.02","CK1020102","9242336","Computing Res Support - FY08","2007-10-01","2008-09-30","S","C","SL_CRA1","Hrs",85,null,4609.989995473764,null,4609.989995473764,null,85,null,4609.989995473764,null,4609.989995473764,{"$nulls":6},4609.989995473764,1,null,null,0.2,921.9979990947528,1.1,1.1,4,1,"1A"]
["1","01","02","01","02","","PM212_0093","1.01.02.01.02","CK1020102","9242336","Computing Res Support - FY09","2008-10-01","2009-03-30","S","C","SL_CRA1","Hrs",21,null,1168.5511154157575,null,1168.5511154157575,null,21,null,1168.5511154157575,null,1168.5511154157575,{"$nulls":8},1168.5511154157575,1,0.2,233.7102230831515,1.1,1.1,4,1,"1A"]
["1","01","02","01","02","","PM212_0717","1.01.02.01.02","CK1020102","9242336","PMCS Support - Maintenance - (Oct06-May07)","2006-10-02","2007-05-31","S","C","SA_MSPS1","$$",null,371520,null,399476.13696,399476.13696,null,null,52012.8,null,55926.6591744,55926.6591744,{"$nulls":4},55926.6591744,1,{"$nulls":4},0.2,11185.331834880002,1.1,1.1,2,1,"1A"]
["1","01","02","01","02","","PM212_0817","1.01.02.01.02","CK1020102","9242336","PMCS Support - Maintenance -(Oct07-Dec07)","2007-10-01","2007-12-14","S","C","SA_MSPS1","$$",null,44582,null,49183.060700736,49183.060700736,null,null,44582,null,49183.060700736,49183.060700736,{"$nulls":6},49183.060700736,1,null,null,0.2,9836.612140147201,1.1,1.1,2,1,"1A"]
["1","01","02","01","02","","PM212_0917","1.01.02.01.02","CK1020102","9242336","PMCS Support - Maintenance - FY09","2008-10-01","2009-03-30","S","C","SA_MSPS1","$$",null,11146,null,12616.02106034464,12616.02106034464,null,null,11146,null,12616.02106034464,12616.02106034464,{"$nulls":8},12616.02106034464,1,0.2,2523.204212068928,1.1,1.1,2,1,"1A"]
["1","01","02","01","02","","PM212_A717","1.01.02.01.02","CK1020102","9242336","PMCS Support - Maintenance - (Jun07-Sep07)","2007-06-01","2007-09-28","S","C","SA_MSPS1","$$",null,148608,null,159790.454784,159790.454784,null,null,148608,null,159790.454784,159790.454784,{"$nulls":4},159790.454784,1,{"$nulls":4},0.2,31958.090956800002,1.1,1.1,2,1,"1A"]
["1","01","02","01","02","","PM212_A817","1.01.02.01.02","CK1020102","9242336","PMCS Support - Maintenance -(Jan08-Jun08)","2008-01-02","2008-06-30","S","C","SA_MSPS1","$$",null,66874,null,73775.694255552,73775.694255552,null,null,66874,null,73775.694255552,73775.694255552,{"$nulls":6},73775.694255552,1,null,null,0.2,14755.138851110401,1.1,1.1,2,1,"1A"]
["1","01","02","01","02","","PM212_B817","1.01.02.01.02","CK1020102","9242336","PMCS Support - Maintenance -(Jul08-Sep08)","2008-07-01","2008-09-30","S","C","SA_MSPS1","$$",null,22291,null,24591.530350368,24591.530350368,null,null,22291,null,24591.530350368,24591.530350368,{"$nulls":6},24591.530350368,1,null,null,0.2,4918.3060700736005,1.1,1.1,2,1,"1A"]
["1","01","02","01","03","  ",{"$nulls":4},"Project Office M&S                                          ",{"$nulls":6},0,889476,0,986011.0087172976,961355.0004844544,null,0,432763.12,0,491632.37710496044,491632.37710496044,0,null,1836.5347387273812,null,190150.12364474995,null,223218.49640690215,null,76427.22231458095,null,null,113044.2747089921]
["1","01","02","01","03","","PM213_0014","1.01.02.01.03","CBA1020103","9242337","SLAC Project Office Consumables- FY06","2006-06-01","2006-09-29","S","C","SL_MSCS1","$$",null,214400,null,224691.2,224691.2,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,4,1,"1A"]
["1","01","02","01","03","","PM213_0052","1.01.02.01.03","CBA1020103","9242337","Project Related Travel/ Shipping - FY06","2006-06-01","2006-09-29","S","C","SL_MSTR1","$$",null,20000,null,24000,24000,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.2,1.1,4,1,"1A"]
["1","01","02","01","03","","PM213_0061","1.01.02.01.03","CBA1020103","9242337","Software Licenses - CONST Remainder","2006-06-01","2008-12-16","S","C","SL_MSEG1","$$",null,22676,null,24656.008232843265,null,null,null,14059.12,null,13984.76042850604,13984.76042850604,null,null,1836.5347387273812,0.13,5494.550652749952,0.39,5509.604216182143,0.39,1144.070820846565,0.08,0.2,2796.9520857012085,1.1,1.1,4,1,"1A"]
["1","01","02","01","03","","PM213_0A14","1.01.02.01.03","CBA1020103","9242337","SLAC Project Office Consumables- FY07","2006-10-02","2007-09-28","S","C","SL_MSCS1","$$",null,321600,null,345799.7568,345799.7568,null,null,141504,null,152151.892992,152151.892992,{"$nulls":4},152151.892992,1,{"$nulls":4},0.2,30430.378598400002,1.1,1.1,4,1,"1A"]
["1","01","02","01","03","","PM213_0A52","1.01.02.01.03","CBA1020103","9242337","Project Related Travel/ Shipping - FY07","2006-10-02","2007-09-28","S","C","SL_MSTR1","$$",null,60000,null,73872,73872,null,null,26400,null,32503.68,32503.68,{"$nulls":4},32503.68,1,{"$nulls":4},0.3,9751.104,1.2,1.1,4,1,"1A"]
["1","01","02","01","03","","PM213_0016","1.01.02.01.03","CK1020103","9242337","SLAC Project Office Consumables- FY08","2007-10-01","2008-09-30","S","C","SL_MSCS1","$$",null,128640,null,141916.22019072002,141916.22019072002,null,null,128640,null,141916.22019072002,141916.22019072002,{"$nulls":6},141916.22019072002,1,null,null,0.2,28383.244038144006,1.1,1.1,4,1,"1A"]
["1","01","02","01","03","","PM213_0017","1.01.02.01.03","CK1020103","9242337","SLAC Project Office Consumables- FY09","2008-10-01","2009-03-30","S","C","SL_MSCS1","$$",null,32160,null,36401.5106137344,36401.5106137344,null,null,32160,null,36401.5106137344,36401.5106137344,{"$nulls":8},36401.5106137344,1,0.2,7280.30212274688,1.1,1.1,4,1,"1A"]
["1","01","02","01","03","","PM213_0053","1.01.02.01.03","CK1020103","9242337","Project Related Travel/ Shipping - FY08","2007-10-01","2008-09-30","S","C","SL_MSTR1","$$",null,60000,null,75792.672,75792.672,null,null,60000,null,75792.672,75792.672,{"$nulls":6},75792.672,1,null,null,0.3,22737.801600000003,1.2,1.1,4,1,"1A"]
["1","01","02","01","03","","PM213_0054","1.01.02.01.03","CK1020103","9242337","Project Related Travel/ Shipping - FY09","2008-10-01","2009-03-30","S","C","SL_MSTR1","$$",null,30000,null,38881.64088,38881.64088,null,null,30000,null,38881.64088,38881.64088,{"$nulls":8},38881.64088,1,0.3,11664.492263999999,1.2,1.1,4,1,"1A"]
["1","01","02","01","04","  ",{"$nulls":4},"SSRL Physics Support                                        "]
["1","01","03","  ","  ","  ",{"$nulls":4},"Technical Integration                                       ",{"$nulls":6},28819,1045260,2749650.9517400777,1128021.8082299903,3877672.7599700675,null,11252.6,423900,1091004.157975367,468672.4885499904,1559676.6465253572,0,null,238.67277587999996,null,912563.994132447,null,561492.0380909324,null,85381.94152609797,null,null,494349.44460855785]
["1","01","03","01","  ","  ",{"$nulls":4},"Global Laser Coordination                                   "]
["1","01","03","02","  ","  ",{"$nulls":4},"Global Alignment Coordination                               ",{"$nulls":6},595,0,61580.865653999994,0,61580.865653999994,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","01","03","02","","","PM100_0006","1.01.03.02","CBA10302",null,"Global Laser Coordination - FY06 Remainder","2006-06-01","2006-09-29","S","C","SL_LPM1","Hrs",595,null,61580.865653999994,null,61580.865653999994,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.1,1.2,4,1,"1A"]
["1","01","03","03","  ","  ",{"$nulls":4},"System Integration                                          ",{"$nulls":6},5001,0,478187.7170873275,0,478187.7170873275,null,1913.72,0,187880.61202893493,0,187880.61202893493,0,null,0,null,141560.04137423701,null,37042.68533325148,null,9277.885321446469,null,null,150304.489623148]
["1","01","03","03","","","PM300_0064","1.01.03.03","CBA10303","9242574","Installation Coordination - FY06 Rem","2006-06-01","2006-09-29","S","C","SL_IPM1","Hrs",595,null,61580.865653999994,null,61580.865653999994,null,0,null,0,null,0,{"$nulls":10},0.8,0,1.4,1.4,5,1,"1A"]
["1","01","03","03","","","PM300_0074","1.01.03.03","CBA10303","9242574","Design Supervisor  - FY06 Remainder","2006-06-01","2006-09-29","S","C","SL_MDD1","Hrs",595,null,48558.914018999996,null,48558.914018999996,null,0,null,0,null,0,{"$nulls":10},0.8,0,1.4,1.4,5,1,"1A"]
["1","01","03","03","","","PM300_0065","1.01.03.03","CK10303","9242574","Installation Coordination - FY07","2006-10-02","2007-09-28","S","C","SL_IPM1","Hrs",1694,null,179882.77994074076,null,179882.77994074076,null,745.36,null,79148.42317392594,null,79148.42317392594,{"$nulls":4},79148.42317392594,1,{"$nulls":4},0.8,63318.73853914076,1.4,1.4,5,1,"1A"]
["1","01","03","03","","","PM300_0066","1.01.03.03","CK10303","9242574","Installation Coordination - FY08","2007-10-01","2008-09-30","S","C","SL_IPM1","Hrs",340,null,37042.68533325148,null,37042.68533325148,null,340,null,37042.68533325148,null,37042.68533325148,{"$nulls":6},37042.68533325148,1,null,null,0.8,29634.148266601187,1.4,1.4,5,1,"1A"]
["1","01","03","03","","","PM300_0067","1.01.03.03","CK10303","9242574","Installation Coordination - FY09","2008-10-01","2009-03-30","S","C","SL_IPM1","Hrs",83,null,9277.885321446469,null,9277.885321446469,null,83,null,9277.885321446469,null,9277.885321446469,{"$nulls":8},9277.885321446469,1,0.8,7422.308257157176,1.4,1.4,5,1,"1A"]
["1","01","03","03","","","PM300_0075","1.01.03.03","CK10303","9242574","Design Supervisor  - FY07","2006-10-02","2007-09-28","S","C","SL_MDD1","Hrs",1694,null,141844.5868188888,null,141844.5868188888,null,745.36,null,62411.61820031107,null,62411.61820031107,{"$nulls":4},62411.61820031107,1,{"$nulls":4},0.8,49929.29456024886,1.4,1.4,5,1,"1A"]
["1","01","03","05","  ","  ",{"$nulls":4},"Global Controls                                             ",{"$nulls":6},21735,1045260,2103810.834797149,1128021.8082299903,3231832.6430271408,null,9338.88,423900,903123.5459464319,468672.4885499904,1371796.0344964224,0,null,238.67277587999996,null,771003.9527582101,null,524449.3527576812,null,76104.0562046515,null,null,344044.9549854101]
["1","01","03","05","01","  ",{"$nulls":4},"Global Controls Management                                  "]
["1","01","03","05","02","  ",{"$nulls":4},"LLRF Controls                                               "]
["1","01","03","05","03","  ",{"$nulls":4},"E-beam Diagnostics & Controls                               ",{"$nulls":6},5888,0,569777.3969110148,0,569777.3969110148,null,2.8,0,238.67277587999996,0,238.67277587999996,0,null,238.67277587999996,null,0,null,0,null,0,null,null,59.66819396999999]
["1","01","03","05","03","01",{"$nulls":4},"Controls - Wire Scanners                                    "]
["1","01","03","05","03","02",{"$nulls":4},"Controls - Toroids                                          ",{"$nulls":6},4440,0,430584.04595742165,0,430584.04595742165,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","01","03","05","03","02","PM302_0100","1.01.03.05.03","CBG50302","9242060","Controls Toroids Rev1 Prototype","2006-08-01","2006-10-31",null,"C","SL_CE1","Hrs",786,null,87333.59997218057,null,87333.59997218057,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,2,"2G","M. Cecere"]
["1","01","03","05","03","02","PM302_0103","1.01.03.05.03","CBG50302","9242060","Controls Toroids Rev2 Design","2006-08-01","2006-10-31",null,"C","SL_CE1","Hrs",1548,null,172000.52513605027,null,172000.52513605027,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,2,"2G","M. Cecere"]
["1","01","03","05","03","02","PM302_0106","1.01.03.05.03","CBG50302","9242060","Controls Toroids Rev2 Prototype Hardware","2006-08-01","2006-10-31",null,"C","SL_CT1","Hrs",1248,null,75916.29645207769,null,75916.29645207769,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,2,"2G","M. Cecere"]
["1","01","03","05","03","02","PM302_0106","1.01.03.05.03","CBG50302","9242060","Controls Toroids Rev2 Prototype Hardware","2006-08-01","2006-10-31",null,"C","SL_CE1","Hrs",858,null,95333.62439711313,null,95333.62439711313,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,2,"2G","M. Cecere"]
["1","01","03","05","03","03",{"$nulls":4},"Controls - Faraday Cups                                     ",{"$nulls":6},60,0,6360.760790999999,0,6360.760790999999,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","01","03","05","03","03","PM303_0100","1.01.03.05.03","CBG50303","9242060","Controls Faraday Cups Final Desgin","2006-08-01","2006-08-15",null,"C","SL_CE1","Hrs",26,null,2864.3461703999997,null,2864.3461703999997,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,2,"2G","S. Peng"]
["1","01","03","05","03","03","PM303_0120","1.01.03.05.03","CBG50303","9242060","Faraday Cups Prototype Hardware","2006-08-01","2006-08-15",null,"C","SL_CT1","Hrs",5,null,301.5669689999999,null,301.5669689999999,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,2,"2G","S. Peng"]
["1","01","03","05","03","03","PM303_0120","1.01.03.05.03","CBG50303","9242060","Faraday Cups Prototype Hardware","2006-08-01","2006-08-15",null,"C","SL_CE1","Hrs",29,null,3194.8476515999996,null,3194.8476515999996,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,2,"2G","S. Peng"]
["1","01","03","05","03","04",{"$nulls":4},"Controls - Tune-Up Dump                                     ",{"$nulls":6},21,0,1964.5340021999998,0,1964.5340021999998,null,2.8,0,238.67277587999996,0,238.67277587999996,0,null,238.67277587999996,null,0,null,0,null,0,null,null,59.66819396999999]
["1","01","03","05","03","04","PM304_0105","1.01.03.05.03","CBG50304","9242060","Controls Tune-up Dump Final Desgin","2006-08-01","2006-08-15",null,"C","SL_CE1","Hrs",7,null,771.1701228,null,771.1701228,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,2,"2G","TBD"]
["1","01","03","05","03","04","PM304_0125","1.01.03.05.03","CBG50304","9242060","Controls Tune-up Dump Prototype Hardware","2006-08-17","2006-08-31",null,"C","SL_CT1","Hrs",7,null,422.1937565999999,null,422.1937565999999,null,1.4,null,84.43875131999998,null,84.43875131999998,null,null,84.43875131999998,1,{"$nulls":6},0.25,21.109687829999995,1.15,1.1,3,2,"2G","TBD"]
["1","01","03","05","03","04","PM304_0125","1.01.03.05.03","CBG50304","9242060","Controls Tune-up Dump Prototype Hardware","2006-08-17","2006-08-31",null,"C","SL_CE1","Hrs",7,null,771.1701228,null,771.1701228,null,1.4,null,154.23402455999997,null,154.23402455999997,null,null,154.23402455999997,1,{"$nulls":6},0.25,38.55850613999999,1.15,1.1,3,2,"2G","TBD"]
["1","01","03","05","03","05",{"$nulls":4},"Controls - Profile Monitors                                 ",{"$nulls":6},16,0,1413.6982002,0,1413.6982002,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","01","03","05","03","05","PM305_0100","1.01.03.05.03","CBG50305","9242060","Controls Profile Monitors Final Desgin","2006-08-01","2006-08-15",null,"C","SL_CE1","Hrs",2,null,220.33432079999997,null,220.33432079999997,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,2,"2G","S. Peng"]
["1","01","03","05","03","05","PM305_0120","1.01.03.05.03","CBG50305","9242060","Controls Profile Monitors Prototype Hardware","2006-08-17","2006-08-31",null,"C","SL_CT1","Hrs",7,null,422.1937565999999,null,422.1937565999999,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,2,"2G","S. Peng"]
["1","01","03","05","03","05","PM305_0120","1.01.03.05.03","CBG50305","9242060","Controls Profile Monitors Prototype Hardware","2006-08-17","2006-08-31",null,"C","SL_CE1","Hrs",7,null,771.1701228,null,771.1701228,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,2,"2G","S. Peng"]
["1","01","03","05","03","06",{"$nulls":4},"Controls - E/O Diagnostics                                  "]
["1","01","03","05","03","07",{"$nulls":4},"Controls - BPM                                              ",{"$nulls":6},877,0,83915.52865499287,0,83915.52865499287,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","01","03","05","03","07","PM307_0100","1.01.03.05.03","CBG50307","9242060","Controls BPMs Final Desgin","2006-08-01","2006-08-28",null,"C","SL_CP1","Hrs",27,null,2168.7241157999997,null,2168.7241157999997,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,2,"2G","S. Smith"]
["1","01","03","05","03","07","PM307_0100","1.01.03.05.03","CBG50307","9242060","Controls BPMs Final Desgin","2006-08-01","2006-08-28",null,"C","SL_CE1","Hrs",13,null,1432.1730851999998,null,1432.1730851999998,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,2,"2G","S. Smith"]
["1","01","03","05","03","07","PM307_0105","1.01.03.05.03","CBG50307","9242060","Controls BPMs Final Design Review (FDR)","2006-08-29","2006-08-29",null,"C","SL_CP1","Hrs",5,null,401.615577,null,401.615577,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,2,"2G","S. Smith"]
["1","01","03","05","03","07","PM307_0115","1.01.03.05.03","CBG50307","9242060","Controls BPMs Prototype Software","2006-08-01","2006-08-30",null,"C","SL_CP1","Hrs",54,null,4337.448231599999,null,4337.448231599999,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,2,"2G","S. Smith"]
["1","01","03","05","03","07","PM307_0120","1.01.03.05.03","CBG50307","9242060","Controls BPMs Prototype Hardware","2006-08-01","2006-10-24",null,"C","SL_CT1","Hrs",214,null,12998.95229262111,null,12998.95229262111,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,2,"2G","S. Smith"]
["1","01","03","05","03","07","PM307_0120","1.01.03.05.03","CBG50307","9242060","Controls BPMs Prototype Hardware","2006-08-01","2006-10-24",null,"C","SL_CE1","Hrs",564,null,62576.61535277176,null,62576.61535277176,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,2,"2G","S. Smith"]
["1","01","03","05","03","08",{"$nulls":4},"Controls - Stopppers                                        ",{"$nulls":6},16,0,1413.6982002,0,1413.6982002,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","01","03","05","03","08","PM308_0100","1.01.03.05.03","CBG50308","9242060","Controls Stoppers Final Desgin","2006-08-01","2006-08-15",null,"C","SL_CE1","Hrs",2,null,220.33432079999997,null,220.33432079999997,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,2,"2G","P. Bong"]
["1","01","03","05","03","08","PM308_0120","1.01.03.05.03","CBG50308","9242060","Controls Stoppers Prototype Hardware","2006-08-17","2006-08-31",null,"C","SL_CT1","Hrs",7,null,422.1937565999999,null,422.1937565999999,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,2,"2G","P. Bong"]
["1","01","03","05","03","08","PM308_0120","1.01.03.05.03","CBG50308","9242060","Controls Stoppers Prototype Hardware","2006-08-17","2006-08-31",null,"C","SL_CE1","Hrs",7,null,771.1701228,null,771.1701228,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,2,"2G","P. Bong"]
["1","01","03","05","03","09",{"$nulls":4},"Controls - Bunch Length Monitors                            ",{"$nulls":6},228,0,24470.013605399996,0,24470.013605399996,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","01","03","05","03","09","PM309_0100","1.01.03.05.03","CBG50309","9242060","Bunch Length Montors Final Desgin","2006-08-01","2006-08-30",null,"C","SL_CE1","Hrs",54,null,5949.026661599999,null,5949.026661599999,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.25,1.1,4,2,"2G","S. Peng"]
["1","01","03","05","03","09","PM309_0104","1.01.03.05.03","CBG50309","9242060","Bunch Length Montors Prototype Hardware","2006-09-01","2006-09-18",null,"C","SL_CT1","Hrs",13,null,784.0741193999999,null,784.0741193999999,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.25,1.1,4,2,"2G","S. Peng"]
["1","01","03","05","03","09","PM309_0104","1.01.03.05.03","CBG50309","9242060","Bunch Length Montors Prototype Hardware","2006-09-01","2006-09-18",null,"C","SL_CE1","Hrs",161,null,17736.9128244,null,17736.9128244,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.25,1.1,4,2,"2G","S. Peng"]
["1","01","03","05","03","10",{"$nulls":4},"Controls - Beam Loss Monitors                               "]
["1","01","03","05","03","11",{"$nulls":4},"Controls - Cherenkov Radiation Detector                     ",{"$nulls":6},16,0,1413.6982002,0,1413.6982002,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","01","03","05","03","11","PM311_0100","1.01.03.05.03","CBG50311","9242060","Controls CRD Final Desgin","2006-08-01","2006-08-15",null,"C","SL_CE1","Hrs",2,null,220.33432079999997,null,220.33432079999997,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.25,1.1,4,2,"2G","S. Peng"]
["1","01","03","05","03","11","PM311_0120","1.01.03.05.03","CBG50311","9242060","Controls CRD Prototype Hardware","2006-08-17","2006-08-31",null,"C","SL_CT1","Hrs",7,null,422.1937565999999,null,422.1937565999999,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.25,1.1,4,2,"2G","S. Peng"]
["1","01","03","05","03","11","PM311_0120","1.01.03.05.03","CBG50311","9242060","Controls CRD Prototype Hardware","2006-08-17","2006-08-31",null,"C","SL_CE1","Hrs",7,null,771.1701228,null,771.1701228,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.25,1.1,4,2,"2G","S. Peng"]
["1","01","03","05","03","12",{"$nulls":4},"Controls - Movable Collimator                               ",{"$nulls":6},214,0,18241.419299399997,0,18241.419299399997,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","01","03","05","03","12","PM312_0115","1.01.03.05.03","CBG50312","9242060","Controls Movable Collimator Prototype Hardware","2006-08-01","2006-08-30",null,"C","SL_CT1","Hrs",107,null,6453.533136599998,null,6453.533136599998,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,2,"2G","D. Murray"]
["1","01","03","05","03","12","PM312_0115","1.01.03.05.03","CBG50312","9242060","Controls Movable Collimator Prototype Hardware","2006-08-01","2006-08-30",null,"C","SL_CE1","Hrs",107,null,11787.886162799998,null,11787.886162799998,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,2,"2G","D. Murray"]
["1","01","03","05","04","  ",{"$nulls":4},"Laser Controls Design                                       "]
["1","01","03","05","05","  ",{"$nulls":4},"Laser Heater Controls                                       ",{"$nulls":6},504,0,50426.28293535359,0,50426.28293535359,null,504,0,50426.28293535359,0,50426.28293535359,0,null,0,null,50426.28293535359,null,0,null,0,null,null,17649.19902737376]
["1","01","03","05","05","","PM505_0001","1.01.03.05.05","CBG30505","9242575","Laser Heater Controls Conceptual Design","2007-02-15","2007-03-14",null,"C","SL_CP1","Hrs",80,null,6592.921312032,null,6592.921312032,null,80,null,6592.921312032,null,6592.921312032,{"$nulls":4},6592.921312032,1,{"$nulls":4},0.35,2307.5224592112,1.25,1.1,4,2,"2G","S. Peng"]
["1","01","03","05","05","","PM505_0001","1.01.03.05.05","CBG30505","9242575","Laser Heater Controls Conceptual Design","2007-02-15","2007-03-14",null,"C","SL_CE1","Hrs",80,null,9042.520525632,null,9042.520525632,null,80,null,9042.520525632,null,9042.520525632,{"$nulls":4},9042.520525632,1,{"$nulls":4},0.35,3164.8821839712,1.25,1.1,4,2,"2G","S. Peng"]
["1","01","03","05","05","","PM505_0005","1.01.03.05.05","CBG30505","9242575","Conceptual Design Review","2007-03-15","2007-03-15","S","C","SL_CE1","Hrs",8,null,904.2520525632,null,904.2520525632,null,8,null,904.2520525632,null,904.2520525632,{"$nulls":4},904.2520525632,1,{"$nulls":4},0.35,316.48821839711997,1.25,1.1,4,2,"2G","S. Peng"]
["1","01","03","05","05","","PM505_0010","1.01.03.05.05","CBG30505","9242575","Laser Heater Controls Preliminary Design","2007-03-16","2007-04-12",null,"C","SL_CE1","Hrs",80,null,9042.520525632,null,9042.520525632,null,80,null,9042.520525632,null,9042.520525632,{"$nulls":4},9042.520525632,1,{"$nulls":4},0.35,3164.8821839712,1.25,1.1,4,2,"2G","S. Peng"]
["1","01","03","05","05","","PM505_0015","1.01.03.05.05","CBG30505","9242575","Preliminary Design Review (PDR)","2007-04-13","2007-04-13",null,"C","SL_CE1","Hrs",8,null,904.2520525632,null,904.2520525632,null,8,null,904.2520525632,null,904.2520525632,{"$nulls":4},904.2520525632,1,{"$nulls":4},0.35,316.48821839711997,1.25,1.1,4,2,"2G","S. Peng"]
["1","01","03","05","05","","PM505_0017","1.01.03.05.05","CBG30505","9242575","Laser Heater Contrils Final Design","2007-04-16","2007-05-15",null,"C","SL_CE1","Hrs",80,null,9042.520525632,null,9042.520525632,null,80,null,9042.520525632,null,9042.520525632,{"$nulls":4},9042.520525632,1,{"$nulls":4},0.35,3164.8821839712,1.25,1.1,4,2,"2G","S. Peng"]
["1","01","03","05","05","","PM505_0020","1.01.03.05.05","CBG30505","9242575","Laser Heater Cntrls Final Design Review (FDR)","2007-05-16","2007-05-16",null,"C","SL_CE1","Hrs",8,null,904.2520525632,null,904.2520525632,null,8,null,904.2520525632,null,904.2520525632,{"$nulls":4},904.2520525632,1,{"$nulls":4},0.35,316.48821839711997,1.25,1.1,4,2,"2G","S. Peng"]
["1","01","03","05","05","","PM505_0050","1.01.03.05.05","CBG30505","9242575","Laser Heater Controls Prototype Hardware","2007-05-17","2007-06-01",null,"C","SL_CT1","Hrs",80,null,4950.523363103998,null,4950.523363103998,null,80,null,4950.523363103998,null,4950.523363103998,{"$nulls":4},4950.523363103998,1,{"$nulls":4},0.35,1732.6831770863994,1.25,1.1,4,2,"2G","S. Peng"]
["1","01","03","05","05","","PM505_0050","1.01.03.05.05","CBG30505","9242575","Laser Heater Controls Prototype Hardware","2007-05-17","2007-06-01",null,"C","SL_CE1","Hrs",80,null,9042.520525632,null,9042.520525632,null,80,null,9042.520525632,null,9042.520525632,{"$nulls":4},9042.520525632,1,{"$nulls":4},0.35,3164.8821839712,1.25,1.1,4,2,"2G","S. Peng"]
["1","01","03","05","06","  ",{"$nulls":4},"Timing Controls                                             "]
["1","01","03","05","07","  ",{"$nulls":4},"Vacuum Controls                                             ",{"$nulls":6},79,0,6561.8812314,0,6561.8812314,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","01","03","05","07","","PM507_0100","1.01.03.05.07","CBB1030507","9242104","Vacuum Controls Prototype Software","2006-08-01","2006-08-16",null,"C","SL_CP1","Hrs",35,null,2811.3090389999998,null,2811.3090389999998,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,2,"2G","S. Schuh"]
["1","01","03","05","07","","PM507_0105","1.01.03.05.07","CBB1030507","9242104","Vacuum Controls Prototype Hardware","2006-08-01","2006-08-16",null,"C","SL_CT1","Hrs",22,null,1326.8946635999996,null,1326.8946635999996,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,2,"2G","S. Schuh"]
["1","01","03","05","07","","PM507_0105","1.01.03.05.07","CBB1030507","9242104","Vacuum Controls Prototype Hardware","2006-08-01","2006-08-16",null,"C","SL_CE1","Hrs",22,null,2423.6775288,null,2423.6775288,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,2,"2G","S. Schuh"]
["1","01","03","05","09","  ",{"$nulls":4},"Power Supply Controls                                       ",{"$nulls":6},7341,0,612883.8122480953,0,612883.8122480953,null,4484.68,0,378071.5724098642,0,378071.5724098642,0,null,0,null,184234.59691856336,null,179349.28698944772,null,14487.688501853185,null,null,94517.89310246606]
["1","01","03","05","09","","PM509_0110","1.01.03.05.09","CABG30509","9242105","Controls Power Supplies Management FY06","2006-08-01","2006-09-29",null,"C","SL_CP1","Hrs",301,null,24177.2577354,null,24177.2577354,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0115","1.01.03.05.09","CABG30509","9242105","Controls Power Supplies Technical Lead FY06","2006-08-01","2006-09-29",null,"C","SL_CP1","Hrs",301,null,24177.2577354,null,24177.2577354,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0120","1.01.03.05.09","CABG30509","9242105","Power Conversion Project Coordinator  (10% time)","2006-08-01","2006-09-29",null,"C","SL_TSM1","Hrs",30,null,3104.917596,null,3104.917596,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0125","1.01.03.05.09","CABG30509","9242105","Misc. Power Supplies Support FY06","2006-08-01","2006-09-29",null,"C","SL_TMUE1","Hrs",30,null,2807.64,null,2807.64,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0125","1.01.03.05.09","CABG30509","9242105","Misc. Power Supplies Support FY06","2006-08-01","2006-09-29",null,"C","SL_PCT1","Hrs",30,null,1809.4018139999996,null,1809.4018139999996,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0125","1.01.03.05.09","CABG30509","9242105","Misc. Power Supplies Support FY06","2006-08-01","2006-09-29",null,"C","SL_EE1","Hrs",30,null,2725.75611,null,2725.75611,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0125","1.01.03.05.09","CABG30509","9242105","Misc. Power Supplies Support FY06","2006-08-01","2006-09-29",null,"C","SL_CT1","Hrs",30,null,1809.4018139999996,null,1809.4018139999996,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0125","1.01.03.05.09","CABG30509","9242105","Misc. Power Supplies Support FY06","2006-08-01","2006-09-29",null,"C","SL_CP1","Hrs",30,null,2409.6934619999997,null,2409.6934619999997,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0205","1.01.03.05.09","CACG30509","9242105","Controls Power Supplies Management FY07","2006-10-02","2007-09-28",null,"C","SL_CP1","Hrs",1694,null,139605.10878227762,null,139605.10878227762,null,745.36,null,61426.247864202145,null,61426.247864202145,{"$nulls":4},61426.247864202145,1,{"$nulls":4},0.25,15356.561966050536,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0210","1.01.03.05.09","CACG30509","9242105","Controls Power Supplies Technical Lead FY07","2006-10-02","2007-09-28",null,"C","SL_CP1","Hrs",339,null,27937.504059735602,null,27937.504059735602,null,149.16,null,12292.501786283665,null,12292.501786283665,{"$nulls":4},12292.501786283665,1,{"$nulls":4},0.25,3073.125446570916,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0215","1.01.03.05.09","CACG30509","9242105","Power Conversion Project Coordinator  (10% time)","2006-10-02","2007-09-28",null,"C","SL_TSM1","Hrs",169,null,17945.802721360797,null,17945.802721360797,null,74.36,null,7896.15319739875,null,7896.15319739875,{"$nulls":4},7896.15319739875,1,{"$nulls":4},0.25,1974.0382993496876,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0220","1.01.03.05.09","CACG30509","9242105","Misc. Power Supplies Support FY07","2006-10-02","2007-09-28",null,"C","SL_TMUE1","Hrs",169,null,16227.597672,null,16227.597672,null,74.36,null,7140.14297568,null,7140.14297568,{"$nulls":4},7140.14297568,1,{"$nulls":4},0.25,1785.03574392,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0220","1.01.03.05.09","CACG30509","9242105","Misc. Power Supplies Support FY07","2006-10-02","2007-09-28",null,"C","SL_PCT1","Hrs",169,null,10457.980604557197,null,10457.980604557197,null,74.36,null,4601.511466005167,null,4601.511466005167,{"$nulls":4},4601.511466005167,1,{"$nulls":4},0.25,1150.3778665012917,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0220","1.01.03.05.09","CACG30509","9242105","Misc. Power Supplies Support FY07","2006-10-02","2007-09-28",null,"C","SL_EE1","Hrs",169,null,15754.325164578002,null,15754.325164578002,null,74.36,null,6931.90307241432,null,6931.90307241432,{"$nulls":4},6931.90307241432,1,{"$nulls":4},0.25,1732.97576810358,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0220","1.01.03.05.09","CACG30509","9242105","Misc. Power Supplies Support FY07","2006-10-02","2007-09-28",null,"C","SL_CT1","Hrs",169,null,10457.980604557197,null,10457.980604557197,null,74.36,null,4601.511466005167,null,4601.511466005167,{"$nulls":4},4601.511466005167,1,{"$nulls":4},0.25,1150.3778665012917,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0220","1.01.03.05.09","CACG30509","9242105","Misc. Power Supplies Support FY07","2006-10-02","2007-09-28",null,"C","SL_CP1","Hrs",169,null,13927.546271667601,null,13927.546271667601,null,74.36,null,6128.120359533744,null,6128.120359533744,{"$nulls":4},6128.120359533744,1,{"$nulls":4},0.25,1532.030089883436,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0305","1.01.03.05.09","CADG30509","9242105","Controls Power Supplies Management FY08","2007-10-01","2008-09-30",null,"C","SL_CP1","Hrs",851,null,71955.63766861564,null,71955.63766861564,null,851,null,71955.63766861564,null,71955.63766861564,{"$nulls":6},71955.63766861564,1,null,null,0.25,17988.90941715391,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0315","1.01.03.05.09","CADG30509","9242105","Power Conversion Project Coordinator  (10% time)","2007-10-01","2008-09-30",null,"C","SL_TSM1","Hrs",170,null,18521.34266662574,null,18521.34266662574,null,170,null,18521.34266662574,null,18521.34266662574,{"$nulls":6},18521.34266662574,1,null,null,0.25,4630.335666656435,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0320","1.01.03.05.09","CADG30509","9242105","Misc. Power Supplies Support FY08","2007-10-01","2008-09-30",null,"C","SL_TMUE1","Hrs",170,null,16748.03305296,null,16748.03305296,null,170,null,16748.03305296,null,16748.03305296,{"$nulls":6},16748.03305296,1,null,null,0.25,4187.00826324,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0320","1.01.03.05.09","CADG30509","9242105","Misc. Power Supplies Support FY08","2007-10-01","2008-09-30",null,"C","SL_PCT1","Hrs",170,null,10793.378562407494,null,10793.378562407494,null,170,null,10793.378562407494,null,10793.378562407494,{"$nulls":6},10793.378562407494,1,null,null,0.25,2698.3446406018734,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0320","1.01.03.05.09","CADG30509","9242105","Misc. Power Supplies Support FY08","2007-10-01","2008-09-30",null,"C","SL_EE1","Hrs",170,null,16259.582220152037,null,16259.582220152037,null,170,null,16259.582220152037,null,16259.582220152037,{"$nulls":6},16259.582220152037,1,null,null,0.25,4064.895555038009,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0320","1.01.03.05.09","CADG30509","9242105","Misc. Power Supplies Support FY08","2007-10-01","2008-09-30",null,"C","SL_CT1","Hrs",170,null,10793.378562407494,null,10793.378562407494,null,170,null,10793.378562407494,null,10793.378562407494,{"$nulls":6},10793.378562407494,1,null,null,0.25,2698.3446406018734,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0320","1.01.03.05.09","CADG30509","9242105","Misc. Power Supplies Support FY08","2007-10-01","2008-09-30",null,"C","SL_CP1","Hrs",170,null,14374.216690557767,null,14374.216690557767,null,170,null,14374.216690557767,null,14374.216690557767,{"$nulls":6},14374.216690557767,1,null,null,0.25,3593.5541726394417,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0405","1.01.03.05.09","CAEG30509","9242105","Controls Power Supplies Management FY09","2008-10-01","2009-03-31",null,"C","SL_CP1","Hrs",167,null,14487.688501853185,null,14487.688501853185,null,167,null,14487.688501853185,null,14487.688501853185,{"$nulls":8},14487.688501853185,1,0.25,3621.922125463296,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0505","1.01.03.05.09","CBBG30509","9242105","Injector/BC1 Drawings","2006-08-01","2006-11-30",null,"C","SL_MDD1","Hrs",298,null,24633.813315456,null,24633.813315456,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0510","1.01.03.05.09","CBBG30509","9242105","LINAC Drawings","2006-12-01","2007-07-19",null,"C","SL_MDD1","Hrs",700,null,58613.46562764,null,58613.46562764,null,630,null,52752.119064876,null,52752.119064876,{"$nulls":4},52752.119064876,1,{"$nulls":4},0.25,13188.029766219,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","09","","PM509_0515","1.01.03.05.09","CBBG30509","9242105","Undulator Drawings","2007-07-20","2007-12-11",null,"C","SL_MDD1","Hrs",476,null,40368.10323188592,null,40368.10323188592,null,476,null,40368.10323188592,null,40368.10323188592,{"$nulls":4},20464.38566616439,0.51,19903.71756572153,0.49,null,null,0.25,10092.02580797148,1.15,1.1,3,2,"2G","K. Luchini"]
["1","01","03","05","10","  ",{"$nulls":4},"Controls - PPS                                              ",{"$nulls":6},3058,0,345137.83372393664,0,345137.83372393664,null,1529,0,172825.1735461416,0,172825.1735461416,0,null,0,null,172825.1735461416,null,0,null,0,null,null,77771.32809576373]
["1","01","03","05","10","","PM3510_001","1.01.03.05.10","CBB1030510",null,"L02/L03 PPS Concepual Design","2006-09-01","2006-10-27",null,"C","SL_CE1","Hrs",334,null,37240.00982616702,null,37240.00982616702,null,0,null,0,null,0,{"$nulls":10},0.45,0,1.35,1.1,5,2,"2G","P. Bong"]
["1","01","03","05","10","","PM3510_011","1.01.03.05.10","CBB1030510",null,"L02/L03 Preliminary Design","2006-10-30","2007-01-10",null,"C","SL_CE1","Hrs",669,null,75618.0778955976,null,75618.0778955976,null,0,null,0,null,0,{"$nulls":10},0.45,0,1.35,1.1,5,2,"2G","P. Bong"]
["1","01","03","05","10","","PM3510_018","1.01.03.05.10","CBB1030510",null,"Functional Requirements Review","2006-10-30","2007-02-08",null,"C","SL_CE1","Hrs",77,null,8703.426005920799,null,8703.426005920799,null,0,null,0,null,0,{"$nulls":10},0.45,0,1.35,1.1,5,2,"2G","P. Bong"]
["1","01","03","05","10","","PM3510_021","1.01.03.05.10","CBB1030510",null,"L02/L03 Final Design","2007-02-09","2007-04-11",null,"C","SL_CE1","Hrs",334,null,37752.5231945136,null,37752.5231945136,null,0,null,0,null,0,{"$nulls":10},0.45,0,1.35,1.1,5,2,"2G","P. Bong"]
["1","01","03","05","10","","PM3510_026","1.01.03.05.10","CBB1030510",null,"External Review","2007-02-09","2007-04-11",null,"C","SL_CE1","Hrs",38,null,4295.1972496752,null,4295.1972496752,null,0,null,0,null,0,{"$nulls":10},0.45,0,1.35,1.1,5,2,"2G","P. Bong"]
["1","01","03","05","10","","PM3510_031","1.01.03.05.10","CBB1030510",null,"Final Design Review (FDR)","2007-04-12","2007-04-12",null,"C","SL_CE1","Hrs",77,null,8703.426005920799,null,8703.426005920799,null,0,null,0,null,0,{"$nulls":10},0.45,0,1.35,1.1,5,2,"2G","P. Bong"]
["1","01","03","05","10","","PM3510_105","1.01.03.05.10","CBC1030510",null,"LTU PPS Concepual Design","2006-11-01","2007-02-15",null,"C","SL_CE1","Hrs",334,null,37752.5231945136,null,37752.5231945136,null,334,null,37752.5231945136,null,37752.5231945136,{"$nulls":4},37752.5231945136,1,{"$nulls":4},0.45,16988.63543753112,1.35,1.1,5,2,"2G","P. Bong"]
["1","01","03","05","10","","PM3510_115","1.01.03.05.10","CBC1030510",null,"LTU Preliminary Design","2007-02-16","2007-04-13",null,"C","SL_CE1","Hrs",669,null,75618.0778955976,null,75618.0778955976,null,669,null,75618.0778955976,null,75618.0778955976,{"$nulls":4},75618.0778955976,1,{"$nulls":4},0.45,34028.13505301892,1.35,1.1,5,2,"2G","P. Bong"]
["1","01","03","05","10","","PM3510_125","1.01.03.05.10","CBC1030510",null,"Functional Requirements Review","2007-02-16","2007-05-11",null,"C","SL_CE1","Hrs",77,null,8703.426005920799,null,8703.426005920799,null,77,null,8703.426005920799,null,8703.426005920799,{"$nulls":4},8703.426005920799,1,{"$nulls":4},0.45,3916.5417026643595,1.35,1.1,5,2,"2G","P. Bong"]
["1","01","03","05","10","","PM3510_135","1.01.03.05.10","CBC1030510",null,"LTU Final Design","2007-05-14","2007-07-16",null,"C","SL_CE1","Hrs",334,null,37752.5231945136,null,37752.5231945136,null,334,null,37752.5231945136,null,37752.5231945136,{"$nulls":4},37752.5231945136,1,{"$nulls":4},0.45,16988.63543753112,1.35,1.1,5,2,"2G","P. Bong"]
["1","01","03","05","10","","PM3510_140","1.01.03.05.10","CBC1030510",null,"External Review","2007-05-14","2007-07-16",null,"C","SL_CE1","Hrs",38,null,4295.1972496752,null,4295.1972496752,null,38,null,4295.1972496752,null,4295.1972496752,{"$nulls":4},4295.1972496752,1,{"$nulls":4},0.45,1932.83876235384,1.35,1.1,5,2,"2G","P. Bong"]
["1","01","03","05","10","","PM3510_145","1.01.03.05.10","CBC1030510",null,"Final Design Review (FDR)","2007-07-17","2007-07-17",null,"C","SL_CE1","Hrs",77,null,8703.426005920799,null,8703.426005920799,null,77,null,8703.426005920799,null,8703.426005920799,{"$nulls":4},8703.426005920799,1,{"$nulls":4},0.45,3916.5417026643595,1.35,1.1,5,2,"2G","P. Bong"]
["1","01","03","05","11","  ",{"$nulls":4},"Controls - MPS                                              ",{"$nulls":6},0,22000,0,23655.456,23655.456,null,0,22000,0,23655.456,23655.456,0,null,0,null,23655.456,null,0,null,0,null,null,4731.0912]
["1","01","03","05","11","","PM511_0163","1.01.03.05.11","CBBG30511","9242394","RCV: MPS Prototype Equipment/Hardware","2007-02-01","2007-02-01",null,"C","SL_MSEG1","$$",null,22000,null,23655.456,23655.456,null,null,22000,null,23655.456,23655.456,{"$nulls":4},23655.456,1,{"$nulls":4},0.2,4731.0912,1.1,1.1,2,2,"2G","A. Tilghman"]
["1","01","03","05","12","  ",{"$nulls":4},"Global Controls Management                                  ",{"$nulls":6},4697,1023260,500515.5448001493,1104366.3522299903,1604881.8970301393,null,2818.4,401900,301561.84427919274,445017.03254999046,746578.8768291827,0,null,0,null,339862.4433581515,null,345100.0657682334,null,61616.3677027983,null,null,149315.77536583666]
["1","01","03","05","12","01",{"$nulls":4},"Global Controls Management LOE                              ",{"$nulls":6},4697,829260,500515.5448001493,886350.5449190304,1386866.0897191796,null,2818.4,287900,301561.84427919274,314641.22523903043,616203.0695182229,0,null,0,null,260696.2833581515,null,304487.8256882333,null,51018.960471838305,null,null,123240.61390364463]
["1","01","03","05","12","01","PM512_0100","1.01.03.05.12","CABG30512","9242333","Controls Cost Account Manager - FY06","2006-08-01","2006-09-29",null,"C","SL_TSM1","Hrs",60,null,6209.835192,null,6209.835192,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0110","1.01.03.05.12","CABG30512","9242333","Controls Technical Coordinator - FY06","2006-08-01","2006-09-29",null,"C","SL_CE1","Hrs",301,null,33160.3152804,null,33160.3152804,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0115","1.01.03.05.12","CABG30512","9242333","Controls E-Beam Diagnostics Tech Lead - FY06","2006-08-01","2006-09-29",null,"C","SL_MSPS1","$$",null,146600,null,153636.8,153636.8,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0120","1.01.03.05.12","CABG30512","9242333","Controls - Wire Scanners Tech Lead - FY06","2006-08-01","2006-09-29",null,"C","SL_MSPS1","$$",null,146600,null,153636.8,153636.8,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0125","1.01.03.05.12","CABG30512","9242333","Controls XTOD Tech Lead - FY06","2006-08-01","2006-09-29",null,"C","SL_MSPS1","$$",null,88000,null,92224,92224,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0200","1.01.03.05.12","CACG30512","9242333","Controls Cost Account Manager - FY07","2006-10-02","2007-09-28",null,"C","SL_TSM1","Hrs",169,null,17945.802721360797,null,17945.802721360797,null,74.36,null,7896.15319739875,null,7896.15319739875,{"$nulls":4},7896.15319739875,1,{"$nulls":4},0.2,1579.2306394797502,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0205","1.01.03.05.12","CACG30512","9242333","Controls Deputy Cost Account Manger - FY07","2006-10-02","2007-09-28",null,"C","SL_TSM1","Hrs",847,null,89941.38997037038,null,89941.38997037038,null,372.68,null,39574.21158696297,null,39574.21158696297,{"$nulls":4},39574.21158696297,1,{"$nulls":4},0.2,7914.842317392595,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0207","1.01.03.05.12","CACG30512","9242333","Controls Physicist - FY07","2006-10-02","2007-09-28",null,"C","SL_PHH1","Hrs",847,null,81345.74632984799,null,81345.74632984799,null,372.68,null,35792.12838513311,null,35792.12838513311,{"$nulls":4},35792.12838513311,1,{"$nulls":4},0.2,7158.425677026622,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0210","1.01.03.05.12","CACG30512","9242333","Controls Technical Coordinator - FY07","2006-10-02","2007-09-28",null,"C","SL_CE1","Hrs",847,null,95737.6860651288,null,95737.6860651288,null,372.68,null,42124.58186865667,null,42124.58186865667,{"$nulls":4},42124.58186865667,1,{"$nulls":4},0.2,8424.916373731334,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0215","1.01.03.05.12","CACG30512","9242333","Controls E-Beam Diagnostics Tech Lead - FY07","2006-10-02","2007-09-28",null,"C","SL_MSPS1","$$",null,110000,null,118277.28,118277.28,null,null,48400,null,52042.0032,52042.0032,{"$nulls":4},52042.0032,1,{"$nulls":4},0.2,10408.40064,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0220","1.01.03.05.12","CACG30512","9242333","Controls - Wire Scanners Tech Lead - FY07","2006-10-02","2007-09-28",null,"C","SL_MSPS1","$$",null,110000,null,118277.28,118277.28,null,null,48400,null,52042.0032,52042.0032,{"$nulls":4},52042.0032,1,{"$nulls":4},0.2,10408.40064,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0225","1.01.03.05.12","CACG30512","9242333","Controls XT/XE Tech Lead - FY07","2006-10-02","2007-09-28",null,"C","SL_MSPS1","$$",null,66000,null,70966.368,70966.368,null,null,29040,null,31225.20192,31225.20192,{"$nulls":4},31225.20192,1,{"$nulls":4},0.2,6245.040384,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0300","1.01.03.05.12","CADG30512","9242333","Controls Cost Account Manager - FY08","2007-10-01","2008-09-30",null,"C","SL_TSM1","Hrs",85,null,9260.67133331287,null,9260.67133331287,null,85,null,9260.67133331287,null,9260.67133331287,{"$nulls":6},9260.67133331287,1,null,null,0.2,1852.1342666625742,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0305","1.01.03.05.12","CADG30512","9242333","Controls Deputy Cost Account Manger - FY08","2007-10-01","2008-09-30",null,"C","SL_TSM1","Hrs",425,null,46303.35666656435,null,46303.35666656435,null,425,null,46303.35666656435,null,46303.35666656435,{"$nulls":6},46303.35666656435,1,null,null,0.2,9260.67133331287,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0307","1.01.03.05.12","CADG30512","9242333","Controls Physicist - FY08","2007-10-01","2008-09-30",null,"C","SL_PHH1","Hrs",425,null,41878.17318433319,null,41878.17318433319,null,425,null,41878.17318433319,null,41878.17318433319,{"$nulls":6},41878.17318433319,1,null,null,0.2,8375.634636866638,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0310","1.01.03.05.12","CADG30512","9242333","Controls Technical Coordinator - FY08","2007-10-01","2008-09-30",null,"C","SL_CE1","Hrs",425,null,49287.388440022914,null,49287.388440022914,null,425,null,49287.388440022914,null,49287.388440022914,{"$nulls":6},49287.388440022914,1,null,null,0.2,9857.477688004583,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0315","1.01.03.05.12","CADG30512","9242333","Controls E-Beam Diagnostics Tech Lead - FY08","2007-10-01","2008-09-30",null,"C","SL_MSPS1","$$",null,55000,null,60676.244640000004,60676.244640000004,null,null,55000,null,60676.244640000004,60676.244640000004,{"$nulls":6},60676.244640000004,1,null,null,0.2,12135.248928,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0320","1.01.03.05.12","CADG30512","9242333","Controls - Wire Scanners Tech Lead - FY08","2007-10-01","2008-09-30",null,"C","SL_MSPS1","$$",null,55000,null,60676.244640000004,60676.244640000004,null,null,55000,null,60676.244640000004,60676.244640000004,{"$nulls":6},60676.244640000004,1,null,null,0.2,12135.248928,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0325","1.01.03.05.12","CADG30512","9242333","Controls XT/XE Tech Lead - FY08","2007-10-01","2008-09-30",null,"C","SL_MSPS1","$$",null,33000,null,36405.746784,36405.746784,null,null,33000,null,36405.746784,36405.746784,{"$nulls":6},36405.746784,1,null,null,0.2,7281.1493568000005,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0400","1.01.03.05.12","CAEG30512","9242333","Controls Cost Account Manager - FY09","2008-10-01","2009-03-31",null,"C","SL_TSM1","Hrs",17,null,1900.2897646336141,null,1900.2897646336141,null,17,null,1900.2897646336141,null,1900.2897646336141,{"$nulls":8},1900.2897646336141,1,0.2,380.05795292672286,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0405","1.01.03.05.12","CAEG30512","9242333","Controls Deputy Cost Account Manger - FY09","2008-10-01","2009-03-31",null,"C","SL_TSM1","Hrs",83,null,9277.885321446469,null,9277.885321446469,null,83,null,9277.885321446469,null,9277.885321446469,{"$nulls":8},9277.885321446469,1,0.2,1855.577064289294,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0407","1.01.03.05.12","CAEG30512","9242333","Controls Physicist - FY09","2008-10-01","2009-03-31",null,"C","SL_PHH1","Hrs",83,null,8391.203494680622,null,8391.203494680622,null,83,null,8391.203494680622,null,8391.203494680622,{"$nulls":8},8391.203494680622,1,0.2,1678.2406989361243,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0410","1.01.03.05.12","CAEG30512","9242333","Controls Technical Coordinator - FY09","2008-10-01","2009-03-31",null,"C","SL_CE1","Hrs",83,null,9875.801036047196,null,9875.801036047196,null,83,null,9875.801036047196,null,9875.801036047196,{"$nulls":8},9875.801036047196,1,0.2,1975.1602072094392,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0415","1.01.03.05.12","CAEG30512","9242333","Controls E-Beam Diagnostics Tech Lead - FY09","2008-10-01","2009-03-31",null,"C","SL_MSPS1","$$",null,7330,null,8296.7373382672,8296.7373382672,null,null,7330,null,8296.7373382672,8296.7373382672,{"$nulls":8},8296.7373382672,1,0.2,1659.34746765344,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0420","1.01.03.05.12","CAEG30512","9242333","Controls - Wire Scanners Tech Lead - FY09","2008-10-01","2009-03-31",null,"C","SL_MSPS1","$$",null,7330,null,8296.7373382672,8296.7373382672,null,null,7330,null,8296.7373382672,8296.7373382672,{"$nulls":8},8296.7373382672,1,0.2,1659.34746765344,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","01","PM512_0425","1.01.03.05.12","CAEG30512","9242333","Controls XT/XE Tech Lead - FY09","2008-10-01","2009-03-31",null,"C","SL_MSPS1","$$",null,4400,null,4980.306178495999,4980.306178495999,null,null,4400,null,4980.306178495999,4980.306178495999,{"$nulls":8},4980.306178495999,1,0.2,996.0612356991999,1.1,1.1,2,2,"2G","H. Shoaee"]
["1","01","03","05","12","02",{"$nulls":4},"Global Controls Management                                  ",{"$nulls":6},0,194000,0,218015.80731095996,218015.80731095996,null,0,114000,0,130375.80731096004,130375.80731096004,0,null,0,null,79166.16,null,40612.240079999996,null,10597.40723096,null,null,26075.161462191998]
["1","01","03","05","12","02","PM512_0140","1.01.03.05.12","CBBG30512","9242333","Controls - Travel - FY06","2006-08-01","2006-09-29",null,"C","SL_MSTR1","$$",null,25000,null,30000,30000,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,4,3,"2G","H. Shoaee"]
["1","01","03","05","12","02","PM512_0145","1.01.03.05.12","CBBG30512","9242333","Controls - Materials & Supplies - FY06","2006-08-01","2006-09-29",null,"C","SL_MSCS1","$$",null,15000,null,15720,15720,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,4,3,"2G","H. Shoaee"]
["1","01","03","05","12","02","PM512_0150","1.01.03.05.12","CBBG30512","9242333","Controls - Training - FY06","2006-08-01","2006-09-29",null,"C","SL_MSCS1","$$",null,15000,null,15720,15720,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,4,3,"2G","H. Shoaee"]
["1","01","03","05","12","02","PM512_0155","1.01.03.05.12","CBBG30512","9242333","Controls - Misc. Hardware - FY06","2006-08-01","2006-09-29",null,"C","SL_MSEG1","$$",null,25000,null,26200,26200,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,4,3,"2G","H. Shoaee"]
["1","01","03","05","12","02","PM512_0240","1.01.03.05.12","CBCG30512","9242333","Controls - Travel FY07","2006-10-02","2007-09-28",null,"C","SL_MSTR1","$$",null,25000,null,30780,30780,null,null,25000,null,30780,30780,{"$nulls":4},30780,1,{"$nulls":4},0.2,6156,1.1,1.1,4,3,"2G","H. Shoaee"]
["1","01","03","05","12","02","PM512_0245","1.01.03.05.12","CBCG30512","9242333","Controls - Materials & Supplies - FY07","2006-10-02","2007-09-28",null,"C","SL_MSCS1","$$",null,10000,null,10752.48,10752.48,null,null,10000,null,10752.48,10752.48,{"$nulls":4},10752.48,1,{"$nulls":4},0.2,2150.496,1.1,1.1,4,3,"2G","H. Shoaee"]
["1","01","03","05","12","02","PM512_0250","1.01.03.05.12","CBCG30512","9242333","Controls - Training - FY07","2006-10-02","2007-09-28",null,"C","SL_MSCS1","$$",null,10000,null,10752.48,10752.48,null,null,10000,null,10752.48,10752.48,{"$nulls":4},10752.48,1,{"$nulls":4},0.2,2150.496,1.1,1.1,4,3,"2G","H. Shoaee"]
["1","01","03","05","12","02","PM512_0255","1.01.03.05.12","CBCG30512","9242333","Controls - Misc. Hardware - FY07","2006-10-02","2007-09-28",null,"C","SL_MSEG1","$$",null,25000,null,26881.2,26881.2,null,null,25000,null,26881.2,26881.2,{"$nulls":4},26881.2,1,{"$nulls":4},0.2,5376.240000000001,1.1,1.1,4,3,"2G","H. Shoaee"]
["1","01","03","05","12","02","PM512_0340","1.01.03.05.12","CBDG30512","9242333","Controls - Travel FY08","2007-10-01","2008-09-30",null,"C","SL_MSTR1","$$",null,12500,null,15790.14,15790.14,null,null,12500,null,15790.14,15790.14,{"$nulls":6},15790.14,1,null,null,0.2,3158.0280000000002,1.1,1.1,4,3,"2G","H. Shoaee"]
["1","01","03","05","12","02","PM512_0345","1.01.03.05.12","CBDG30512","9242333","Controls - Materials & Supplies - FY08","2007-10-01","2008-09-30",null,"C","SL_MSCS1","$$",null,5000,null,5516.02224,5516.02224,null,null,5000,null,5516.02224,5516.02224,{"$nulls":6},5516.02224,1,null,null,0.2,1103.2044480000002,1.1,1.1,4,3,"2G","H. Shoaee"]
["1","01","03","05","12","02","PM512_0350","1.01.03.05.12","CBDG30512","9242333","Controls - Training - FY08","2007-10-01","2008-09-30",null,"C","SL_MSCS1","$$",null,5000,null,5516.02224,5516.02224,null,null,5000,null,5516.02224,5516.02224,{"$nulls":6},5516.02224,1,null,null,0.2,1103.2044480000002,1.1,1.1,4,3,"2G","H. Shoaee"]
["1","01","03","05","12","02","PM512_0355","1.01.03.05.12","CBDG30512","9242333","Controls - Misc. Hardware - FY08","2007-10-01","2008-09-30",null,"C","SL_MSEG1","$$",null,12500,null,13790.055600000002,13790.055600000002,null,null,12500,null,13790.055600000002,13790.055600000002,{"$nulls":6},13790.055600000002,1,null,null,0.2,2758.0111200000006,1.1,1.1,4,3,"2G","H. Shoaee"]
["1","01","03","05","12","02","PM512_0440","1.01.03.05.12","CBEG30512","9242333","Controls - Travel FY09","2008-10-01","2009-03-31",null,"C","SL_MSTR1","$$",null,2500,null,3240.13674,3240.13674,null,null,2500,null,3240.13674,3240.13674,{"$nulls":8},3240.13674,1,0.2,648.0273480000001,1.1,1.1,4,3,"2G","H. Shoaee"]
["1","01","03","05","12","02","PM512_0445","1.01.03.05.12","CBEG30512","9242333","Controls - Materials & Supplies - FY09","2008-10-01","2009-03-31",null,"C","SL_MSCS1","$$",null,2000,null,2263.77553568,2263.77553568,null,null,2000,null,2263.77553568,2263.77553568,{"$nulls":8},2263.77553568,1,0.2,452.755107136,1.1,1.1,4,3,"2G","H. Shoaee"]
["1","01","03","05","12","02","PM512_0450","1.01.03.05.12","CBEG30512","9242333","Controls - Training - FY09","2008-10-01","2009-03-31",null,"C","SL_MSCS1","$$",null,2000,null,2263.77553568,2263.77553568,null,null,2000,null,2263.77553568,2263.77553568,{"$nulls":8},2263.77553568,1,0.2,452.755107136,1.1,1.1,4,3,"2G","H. Shoaee"]
["1","01","03","05","12","02","PM512_0455","1.01.03.05.12","CBEG30512","9242333","Controls - Misc. Hardware - FY09","2008-10-01","2009-03-31",null,"C","SL_MSEG1","$$",null,2500,null,2829.7194195999996,2829.7194195999996,null,null,2500,null,2829.7194195999996,2829.7194195999996,{"$nulls":8},2829.7194195999996,1,0.2,565.94388392,1.1,1.1,4,3,"2G","H. Shoaee"]
["1","01","03","05","13","  ",{"$nulls":4},"SLC Aware IOC                                               "]
["1","01","03","05","14","  ",{"$nulls":4},"Controls - S/W Application                                  "]
["1","01","03","05","15","  ",{"$nulls":4},"Controls - BCS                                              ",{"$nulls":6},168,0,18508.082947199997,0,18508.082947199997,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","01","03","05","15","","PM515_0005","1.01.03.05.15","CBB3050215",null,"Controls BCS Final Desgin","2006-08-01","2006-08-28",null,"C","SL_CE1","Hrs",160,null,17626.745664,null,17626.745664,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,2,"2G","K. Traeger"]
["1","01","03","05","15","","PM515_0010","1.01.03.05.15","CBB3050215",null,"Controls BCS Final Design Review (FDR)","2006-08-29","2006-08-29",null,"C","SL_CE1","Hrs",8,null,881.3372831999999,null,881.3372831999999,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,2,"2G","K. Traeger"]
["1","01","03","06","  ","  ",{"$nulls":4},"Technical Requirements/Parameters                           ",{"$nulls":6},1488,0,106071.53420159998,0,106071.53420159998,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","01","03","06","","","PM210_0293","1.01.03.06","CBA10306",null,"Define Technical Requirements/Parameters(CON)","2006-06-01","2006-09-29",null,"C","SL_PHS1","Hrs",1488,null,106071.53420159998,null,106071.53420159998,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,4,1,"1A"]
["1","01","04","  ","  ","  ",{"$nulls":4},"Education Support                                           "]
["1","01","04","01","  ","  ",{"$nulls":4},"Education/Outreach Travel                                   "]
["1","01","04","02","  ","  ",{"$nulls":4},"Education/Outreach M&S                                      "]
["1","02","  ","  ","  ","  ",{"$nulls":4},"INJECTOR SYSTEM                                             ",{"$nulls":6},34585,3740665,3107282.1713680895,3894722.378949591,6320177.369496101,null,760,195400,72447.66661811895,208068.35627368418,280516.0228918031,0,null,82596.08306073499,null,174896.19294726005,null,23023.746883808108,null,0,null,null,66907.6634270681]
["1","02","01","  ","  ","  ",{"$nulls":4},"Injector System Management & Integration                    ",{"$nulls":6},5702,51402,539909.900457133,57969.98430204878,539909.900457133,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","01","01","  ","  ",{"$nulls":4},"Injector System Integration                                 ",{"$nulls":6},2331,0,206572.14929390422,0,206572.14929390422,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","01","01","01","  ",{"$nulls":4},"Injector Region Integration                                 ",{"$nulls":6},960,0,85758.25920541219,0,85758.25920541219,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","01","01","01","","IJ101_1225","1.02.01.01.01","CBE2010101",null,"Injector Region Infrastructure Support","2006-05-01","2006-12-29",null,"C","SL_ME1","Hrs",80,null,7861.576936751999,null,7861.576936751999,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,1,"2A"]
["1","02","01","01","01","","IJ101_1225","1.02.01.01.01","CBE2010101",null,"Injector Region Infrastructure Support","2006-05-01","2006-12-29",null,"C","SL_MDD1","Hrs",80,null,6591.359133072,null,6591.359133072,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,1,"2A"]
["1","02","01","01","01","","IJ101_1230","1.02.01.01.01","CBE2010101",null,"Injector Region Installation Drawing","2006-05-01","2006-10-02",null,"C","SL_MDD1","Hrs",160,null,13060.06380563657,null,13060.06380563657,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,4,2,"2A"]
["1","02","01","01","01","","IJ101_1240","1.02.01.01.01","CBE2010101",null,"Injector Water System Design","2006-05-01","2006-11-21",null,"C","SL_ME1","Hrs",160,null,15675.465828527997,null,15675.465828527997,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,2,"2A"]
["1","02","01","01","01","","IJ101_1240","1.02.01.01.01","CBE2010101",null,"Injector Water System Design","2006-05-01","2006-11-21",null,"C","SL_MDD1","Hrs",160,null,13142.735317007999,null,13142.735317007999,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,2,"2A"]
["1","02","01","01","01","","IJ101_1250","1.02.01.01.01","CBE2010101",null,"Injector Water System Consultation","2006-07-01","2006-09-26",null,"C","SL_ME1","Hrs",120,null,11680.674983999997,null,11680.674983999997,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,1,"2A"]
["1","02","01","01","01","","IJ101_1260","1.02.01.01.01","CBE2010101",null,"Injector Water Vibration Consultation","2006-07-01","2006-09-26",null,"C","SL_ME1","Hrs",80,null,7787.116655999998,null,7787.116655999998,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,1,"2A"]
["1","02","01","01","01","","IJ101_1270","1.02.01.01.01","CBE2010101",null,"Integrate Water into Injector Top Install","2006-08-01","2007-01-23",null,"C","SL_MDD1","Hrs",120,null,9959.266544415634,null,9959.266544415634,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,4,2,"2A"]
["1","02","01","01","02","  ",{"$nulls":4},"Gun Area Integration                                        ",{"$nulls":6},340,0,30895.071898227423,0,30895.071898227423,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","01","01","02","","IJ101_2040","1.02.01.01.02","CBE2010102",null,"Gun Region Installation Drawing","2006-05-01","2006-10-02",null,"C","SL_MDD1","Hrs",120,null,9795.047854227427,null,9795.047854227427,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,2,"2A"]
["1","02","01","01","02","","IJ101_2150","1.02.01.01.02","CBE2010102",null,"Gun Area Installation Oversight","2006-08-02","2006-09-28",null,"C","SL_ME1","Hrs",40,null,3893.558327999999,null,3893.558327999999,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,1,"2A"]
["1","02","01","01","02","","IJ101_2150","1.02.01.01.02","CBE2010102",null,"Gun Area Installation Oversight","2006-08-02","2006-09-28",null,"C","SL_MDD1","Hrs",20,null,1632.2324039999999,null,1632.2324039999999,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,1,"2A"]
["1","02","01","01","02","","IJ101_2200","1.02.01.01.02","CBE2010102",null,"Gun Region Procurement Support","2006-05-01","2006-07-01",null,"C","SL_ME1","Hrs",80,null,7787.116655999998,null,7787.116655999998,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,1,"2A"]
["1","02","01","01","02","","IJ101_2210","1.02.01.01.02","CBE2010102",null,"Gun Region Fabrication Oversight","2006-05-01","2006-07-01",null,"C","SL_ME1","Hrs",80,null,7787.116655999998,null,7787.116655999998,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,1,"2A"]
["1","02","01","01","03","  ",{"$nulls":4},"Accelerator Area Integration                                ",{"$nulls":6},317,0,27396.435389399994,0,27396.435389399994,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","01","01","03","","IJ101_3040","1.02.01.01.03","CBE2010103",null,"Accelerator Area Installation Drawing","2006-06-01","2006-08-31",null,"C","SL_MDD1","Hrs",120,null,9793.394423999998,null,9793.394423999998,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,4,2,"2A"]
["1","02","01","01","03","","IJ101_3050","1.02.01.01.03","CBE2010103",null,"Accelerator Area Table and Columns","2006-05-01","2006-06-30",null,"C","SL_ME1","Hrs",9,null,876.0506237999998,null,876.0506237999998,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,2,"2A"]
["1","02","01","01","03","","IJ101_3050","1.02.01.01.03","CBE2010103",null,"Accelerator Area Table and Columns","2006-05-01","2006-06-30",null,"C","SL_MDD1","Hrs",27,null,2203.5137453999996,null,2203.5137453999996,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,2,"2A"]
["1","02","01","01","03","","IJ101_3060","1.02.01.01.03","CBE2010103",null,"Accelerator Area Top Assembly","2006-05-01","2006-06-30",null,"C","SL_ME1","Hrs",16,null,1557.4233311999997,null,1557.4233311999997,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,2,"2A"]
["1","02","01","01","03","","IJ101_3060","1.02.01.01.03","CBE2010103",null,"Accelerator Area Top Assembly","2006-05-01","2006-06-30",null,"C","SL_MDD1","Hrs",53,null,4325.4158706,null,4325.4158706,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,2,"2A"]
["1","02","01","01","03","","IJ101_3070","1.02.01.01.03","CBE2010103",null,"Accelerator Area Procurement Support","2006-05-01","2006-07-28",null,"C","SL_ME1","Hrs",16,null,1557.4233311999997,null,1557.4233311999997,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,1,"2A"]
["1","02","01","01","03","","IJ101_3080","1.02.01.01.03","CBE2010103",null,"Accelerator Area Fabrication Oversight","2006-05-01","2006-07-30",null,"C","SL_ME1","Hrs",16,null,1557.4233311999997,null,1557.4233311999997,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,1,"2A"]
["1","02","01","01","03","","IJ101_3150","1.02.01.01.03","CBE2010103",null,"Accelerator Area Installation Oversight","2006-08-01","2006-09-28",null,"C","SL_ME1","Hrs",40,null,3893.558327999999,null,3893.558327999999,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,1,"2A"]
["1","02","01","01","03","","IJ101_3150","1.02.01.01.03","CBE2010103",null,"Accelerator Area Installation Oversight","2006-08-01","2006-09-28",null,"C","SL_MDD1","Hrs",20,null,1632.2324039999999,null,1632.2324039999999,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,1,"2A"]
["1","02","01","01","04","  ",{"$nulls":4},"Heater Area Integration                                     "]
["1","02","01","01","05","  ",{"$nulls":4},"Wall Area Integration                                       "]
["1","02","01","01","06","  ",{"$nulls":4},"Insertion Area Integration                                  ",{"$nulls":6},210,0,18432.248081759997,0,18432.248081759997,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","01","01","06","","IJ101_6040","1.02.01.01.06","CBE2010106",null,"Insertion Area Drawing","2006-05-01","2006-07-30",null,"C","SL_MDD1","Hrs",120,null,9793.394423999998,null,9793.394423999998,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,4,2,"2A"]
["1","02","01","01","06","","IJ101_6050","1.02.01.01.06","CBE2010106",null,"Insertion Area Procurement Support","2006-05-01","2006-07-30",null,"C","SL_ME1","Hrs",20,null,1946.7791639999996,null,1946.7791639999996,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,1,"2A"]
["1","02","01","01","06","","IJ101_6060","1.02.01.01.06","CBE2010106",null,"Insertion Area Fabrication Oversight","2006-05-01","2006-07-30",null,"C","SL_ME1","Hrs",40,null,3893.558327999999,null,3893.558327999999,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,1,"2A"]
["1","02","01","01","06","","IJ101_6150","1.02.01.01.06","CBE2010106",null,"Insertion Area Installation Oversight","2006-08-01","2006-11-30",null,"C","SL_ME1","Hrs",20,null,1971.8781350399997,null,1971.8781350399997,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,1,"2A"]
["1","02","01","01","06","","IJ101_6150","1.02.01.01.06","CBE2010106",null,"Insertion Area Installation Oversight","2006-08-01","2006-11-30",null,"C","SL_MDD1","Hrs",10,null,826.63803072,null,826.63803072,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,1,"2A"]
["1","02","01","01","07","  ",{"$nulls":4},"Spectrometer Area Integration                               ",{"$nulls":6},230,0,20386.787491421994,0,20386.787491421994,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","01","01","07","","IJ101_7170","1.02.01.01.07","CBE2010107",null,"Spectrometer Area Drawing","2006-05-01","2006-07-30",null,"C","SL_MDD1","Hrs",120,null,9793.394423999998,null,9793.394423999998,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,4,2,"2A"]
["1","02","01","01","07","","IJ101_7180","1.02.01.01.07","CBE2010107",null,"Spectrometer Area Procurement Support","2006-05-01","2006-07-30",null,"C","SL_ME1","Hrs",40,null,3893.558327999999,null,3893.558327999999,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,1,"2A"]
["1","02","01","01","07","","IJ101_7190","1.02.01.01.07","CBE2010107",null,"Spectrometer Area Fabrication Oversight","2006-06-01","2006-07-30",null,"C","SL_ME1","Hrs",40,null,3893.558327999999,null,3893.558327999999,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,1,"2A"]
["1","02","01","01","07","","IJ101_7195","1.02.01.01.07","CBE2010107",null,"Spectrometer Area Installation Oversight","2006-08-01","2007-01-02",null,"C","SL_ME1","Hrs",20,null,1977.3461251594283,null,1977.3461251594283,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,1,"2A"]
["1","02","01","01","07","","IJ101_7195","1.02.01.01.07","CBE2010107",null,"Spectrometer Area Installation Oversight","2006-08-01","2007-01-02",null,"C","SL_MDD1","Hrs",10,null,828.9302862625714,null,828.9302862625714,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,1,"2A"]
["1","02","01","01","08","  ",{"$nulls":4},"Drive Laser Integration                                     ",{"$nulls":6},274,0,23703.347227682567,0,23703.347227682567,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","01","01","08","","IJ101_8040","1.02.01.01.08","CBE2010108",null,"Drive Laser Drawing","2006-07-01","2006-09-28",null,"C","SL_MDD1","Hrs",120,null,9793.394423999998,null,9793.394423999998,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,4,2,"2A"]
["1","02","01","01","08","","IJ101_8050","1.02.01.01.08","CBE2010108",null,"Drive Laser Top Assembly","2006-05-01","2006-10-02",null,"C","SL_ME1","Hrs",20,null,1947.1078410017137,null,1947.1078410017137,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,4,2,"2A"]
["1","02","01","01","08","","IJ101_8050","1.02.01.01.08","CBE2010108",null,"Drive Laser Top Assembly","2006-05-01","2006-10-02",null,"C","SL_MDD1","Hrs",60,null,4897.523927113713,null,4897.523927113713,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,4,2,"2A"]
["1","02","01","01","08","","IJ101_8060","1.02.01.01.08","CBE2010108",null,"Drive Laser Procurement Support","2006-05-01","2006-07-30",null,"C","SL_ME1","Hrs",12,null,1168.0674983999997,null,1168.0674983999997,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,1,"2A"]
["1","02","01","01","08","","IJ101_8070","1.02.01.01.08","CBE2010108",null,"Drive Laser Fabrication Oversight","2006-05-01","2006-07-30",null,"C","SL_ME1","Hrs",12,null,1168.0674983999997,null,1168.0674983999997,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,1,"2A"]
["1","02","01","01","08","","IJ101_8150","1.02.01.01.08","CBE2010108",null,"Drive Laser Installation Oversight","2006-05-01","2006-10-30",null,"C","SL_ME1","Hrs",40,null,3909.6887839302854,null,3909.6887839302854,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,1,"2A"]
["1","02","01","01","08","","IJ101_8150","1.02.01.01.08","CBE2010108",null,"Drive Laser Installation Oversight","2006-05-01","2006-10-30",null,"C","SL_MDD1","Hrs",10,null,819.4972548368571,null,819.4972548368571,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,1,"2A"]
["1","02","01","04","  ","  ",{"$nulls":4},"Injector System Integration Effort / M&S                    ",{"$nulls":6},3371,51402,333337.7511632288,57969.98430204878,333337.7511632288,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","01","04","","","IJ104_1500","1.02.01.04","CBE20104",null,"Management - CONST","2006-05-01","2007-01-02",null,"C","SL_TSM1","Hrs",1085,null,113398.2926841455,null,113398.2926841455,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,4,1,"2A"]
["1","02","01","04","","","IJ104_1510","1.02.01.04","CBE20104",null,"Cost Account Managers - CONST","2006-05-01","2007-01-02",null,"C","SL_ME1","Hrs",543,null,53374.58081196457,null,53374.58081196457,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,4,1,"2A"]
["1","02","01","04","","","IJ104_1520","1.02.01.04","CBE20104",null,"Fabrication Coordination","2006-05-01","2007-01-02",null,"C","SL_ME1","Hrs",543,null,53374.58081196457,null,53374.58081196457,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,4,1,"2A"]
["1","02","01","04","","","IJ104_1530","1.02.01.04","CBE20104",null,"Computers - CONST","2006-05-01","2007-01-02",null,"C","SL_MSEG1","$$",null,16882,null,17866.238717268294,null,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,5,3,"2A"]
["1","02","01","04","","","IJ104_1540","1.02.01.04","CBE20104",null,"Travel - CONST","2006-05-01","2007-01-02",null,"C","SL_MSTR1","$$",null,23266,null,28193.625307317074,null,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,5,1,"2A"]
["1","02","01","04","","","IJ104_1550","1.02.01.04","CBE20104",null,"Materials & Supplies - CONST","2006-05-01","2007-01-02",null,"C","SL_MSCS1","$$",null,11254,null,11910.120277463415,null,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,5,3,"2A"]
["1","02","01","04","","","IJ104_1560","1.02.01.04","CBE20104",null,"Injector System Area Management","2006-05-01","2007-01-02",null,"C","SL_ME1","Hrs",600,null,58977.43736128682,null,58977.43736128682,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,4,1,"2A"]
["1","02","01","04","","","IJ104_1570","1.02.01.04","CBE20104",null,"Injector System Tooling Coordination","2006-05-01","2007-01-02",null,"C","SL_MDD1","Hrs",300,null,24724.1408132239,null,24724.1408132239,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,4,1,"2A"]
["1","02","01","04","","","IJ104_1580","1.02.01.04","CBE20104",null,"Injector System Safety Coordination","2006-05-01","2007-01-02",null,"C","SL_ME1","Hrs",300,null,29488.71868064341,null,29488.71868064341,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,4,1,"2A"]
["1","02","02","  ","  ","  ",{"$nulls":4},"Injector Controls Subsystem                                 ",{"$nulls":6},8546,1221970,741578.6248861526,1290350.0796479997,2031928.7045341516,null,60,84100,5247.391458276,90428.3568,95675.74825827598,0,null,0,null,95675.74825827598,null,0,null,0,null,null,18376.033624568998]
["1","02","02","01","  ","  ",{"$nulls":4},"Personnel Protection Subsystem (PPS)                        ",{"$nulls":6},1264,22000,98738.93443043517,23056,121794.93443043517,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","01","","","IJ201_020","1.02.02.01","CBBIJ20201",null,"Injector Controls Software","2006-08-01","2006-08-29",null,"C","SL_CP1","Hrs",174,null,13976.222079599998,null,13976.222079599998,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,3,"2G","P. Bong"]
["1","02","02","01","","","IJ201_030","1.02.02.01","CBBIJ20201",null,"RCV: 1 Battery Recharger","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,22000,null,23056,23056,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,2,3,"2G","P. Bong"]
["1","02","02","01","","","IJ201_105","1.02.02.01","CBBIJ20201",null,"Injector PPS HW","2006-08-30","2006-09-28",null,"C","SL_CT1","Hrs",696,null,41978.12208479999,null,41978.12208479999,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,3,"2G","P. Bong"]
["1","02","02","01","","","IJ201_105","1.02.02.01","CBBIJ20201",null,"Injector PPS HW","2006-08-30","2006-09-28",null,"C","SL_CE1","Hrs",174,null,19169.0859096,null,19169.0859096,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,3,"2G","P. Bong"]
["1","02","02","01","","","IJ201_110","1.02.02.01","CBBIJ20201",null,"Injector Controls PPS Integration and Test","2006-09-29","2006-11-13",null,"C","SL_CP1","Hrs",40,null,3292.7479431264,null,3292.7479431264,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,3,"2G","P. Bong"]
["1","02","02","01","","","IJ201_110","1.02.02.01","CBBIJ20201",null,"Injector Controls PPS Integration and Test","2006-09-29","2006-11-13",null,"C","SL_CE1","Hrs",180,null,20322.756413308798,null,20322.756413308798,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,3,"2G","P. Bong"]
["1","02","02","02","  ","  ",{"$nulls":4},"Beam Containment Subsystem (BCS)                            ",{"$nulls":6},1800,217100,195832.23609357254,227520.8,423353.0360935726,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","02","","","IJ202_0005","1.02.02.02","CBBIJ20202",null,"Injector Rack Layout Wiring","2006-08-01","2006-09-29",null,"C","SL_CE1","Hrs",80,null,8813.372832,null,8813.372832,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","K. Traeger"]
["1","02","02","02","","","IJ202_0010","1.02.02.02","CBBIJ20202",null,"Write Certification Procedures","2006-08-01","2006-09-29",null,"C","SL_CE1","Hrs",320,null,35253.491328,null,35253.491328,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","K. Traeger"]
["1","02","02","02","","","IJ202_0015","1.02.02.02","CBBIJ20202",null,"Write System Documentation","2006-08-01","2007-01-30",null,"C","SL_CE1","Hrs",600,null,67242.88707500571,null,67242.88707500571,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","K. Traeger"]
["1","02","02","02","","","IJ202_0020","1.02.02.02","CBBIJ20202",null,"Injector Controls Software","2006-08-01","2006-08-28",null,"C","SL_CP1","Hrs",120,null,9638.773847999999,null,9638.773847999999,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.25,1.1,4,3,"2G","K. Traeger"]
["1","02","02","02","","","IJ202_0030","1.02.02.02","CBBIJ20202",null,"RCV: 1 Cables","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,60000,null,62880,62880,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,2,3,"2G","K. Traeger"]
["1","02","02","02","","","IJ202_0035","1.02.02.02","CBBIJ20202",null,"RCV: 2 Local Mode Chassis","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,10700,null,11213.6,11213.6,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","K. Traeger"]
["1","02","02","02","","","IJ202_0040","1.02.02.02","CBBIJ20202",null,"RCV: 2 Interlock Chassis","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,10900,null,11423.2,11423.2,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"2G","K. Traeger"]
["1","02","02","02","","","IJ202_0045","1.02.02.02","CBBIJ20202",null,"RCV: 2 Beam Permissive Current Loop Transmitter","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,10700,null,11213.6,11213.6,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","K. Traeger"]
["1","02","02","02","","","IJ202_0050","1.02.02.02","CBBIJ20202",null,"RCV: 2 Beam Permissive Current Loop Receiver","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,10700,null,11213.6,11213.6,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","K. Traeger"]
["1","02","02","02","","","IJ202_0055","1.02.02.02","CBBIJ20202",null,"RCV: 3 PIC Lion Cards","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,16500,null,17292,17292,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","K. Traeger"]
["1","02","02","02","","","IJ202_0060","1.02.02.02","CBBIJ20202",null,"RCV: 24 PIC / Lion Cards","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,43200,null,45273.6,45273.6,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","K. Traeger"]
["1","02","02","02","","","IJ202_0065","1.02.02.02","CBBIJ20202",null,"RCV: 2 Lion Power Supplies","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,10800,null,11318.4,11318.4,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","K. Traeger"]
["1","02","02","02","","","IJ202_0070","1.02.02.02","CBBIJ20202",null,"RCV: 1 Master Beam Control Panel","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,1200,null,1257.6,1257.6,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","K. Traeger"]
["1","02","02","02","","","IJ202_0075","1.02.02.02","CBBIJ20202",null,"RCV: 3 IOCs","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,16500,null,17292,17292,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,2,3,"2G","K. Traeger"]
["1","02","02","02","","","IJ202_0080","1.02.02.02","CBBIJ20202",null,"RCV: 1 I/O","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,12000,null,12576,12576,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,2,3,"2G","K. Traeger"]
["1","02","02","02","","","IJ202_0085","1.02.02.02","CBBIJ20202",null,"RCV: 4 Lions","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,4400,null,4611.2,4611.2,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"2G","K. Traeger"]
["1","02","02","02","","","IJ202_0090","1.02.02.02","CBBIJ20202",null,"RCV: 1 Injector Lion","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,1100,null,1152.8,1152.8,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"2G","K. Traeger"]
["1","02","02","02","","","IJ202_0095","1.02.02.02","CBBIJ20202",null,"RCV: 2 Dump Flow Switches","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,2800,null,2934.4,2934.4,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,2,3,"2G","K. Traeger"]
["1","02","02","02","","","IJ202_0100","1.02.02.02","CBBIJ20202",null,"RCV: 4 Pressure Switches","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,5600,null,5868.8,5868.8,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,2,3,"2G","K. Traeger"]
["1","02","02","02","","","IJ202_0105","1.02.02.02","CBBIJ20202",null,"Injector Control BCS HW Fabrication","2006-08-30","2006-10-25",null,"C","SL_CE1","Hrs",460,null,51241.57917187885,null,51241.57917187885,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,3,"2G","K. Traeger"]
["1","02","02","02","","","IJ202_0110","1.02.02.02","CBBIJ20202",null,"Injector Controls BCS Integration and Test","2006-10-26","2006-11-22",null,"C","SL_CP1","Hrs",40,null,3296.460656016,null,3296.460656016,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","K. Traeger"]
["1","02","02","02","","","IJ202_0110","1.02.02.02","CBBIJ20202",null,"Injector Controls BCS Integration and Test","2006-10-26","2006-11-22",null,"C","SL_CE1","Hrs",180,null,20345.671182672,null,20345.671182672,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","K. Traeger"]
["1","02","02","03","  ","  ",{"$nulls":4},"Machine Protection Subsystem (MPS)                          ",{"$nulls":6},0,75800,0,79438.4,79438.4,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","03","","","IJ203_0120","1.02.02.03","CBBIJ20203",null,"RCV: 1Custom Electronics","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,2500,null,2620,2620,null,null,0,null,0,0,{"$nulls":10},0.45,0,1.35,1.1,5,3,"2G","A. Tilghman"]
["1","02","02","03","","","IJ203_0130","1.02.02.03","CBBIJ20203",null,"RCV: 1 EVR","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,2900,null,3039.2,3039.2,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,2,3,"2G","A. Tilghman"]
["1","02","02","03","","","IJ203_0140","1.02.02.03","CBBIJ20203",null,"RCV: PLICs, LIONS, TIU Electronics","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,31000,null,32488,32488,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","A. Tilghman"]
["1","02","02","03","","","IJ203_0150","1.02.02.03","CBBIJ20203",null,"RCV: 1 Motorola 6100","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,5600,null,5868.8,5868.8,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,2,3,"2G","A. Tilghman"]
["1","02","02","03","","","IJ203_0160","1.02.02.03","CBBIJ20203",null,"RCV:1 IOC Crate 21 Slots","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,8400,null,8803.2,8803.2,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,2,3,"2G","A. Tilghman"]
["1","02","02","03","","","IJ203_0170","1.02.02.03","CBBIJ20203",null,"RCV:1 Custom Input Electronics","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,8400,null,8803.2,8803.2,null,null,0,null,0,0,{"$nulls":10},0.45,0,1.35,1.1,5,3,"2G","A. Tilghman"]
["1","02","02","03","","","IJ203_0180","1.02.02.03","CBBIJ20203",null,"RCV: 1 Custom Controller","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,17000,null,17816,17816,null,null,0,null,0,0,{"$nulls":10},0.45,0,1.35,1.1,5,3,"2G","A. Tilghman"]
["1","02","02","04","  ","  ",{"$nulls":4},"Injector Power Conversion                                   ",{"$nulls":6},1193,95468,85696.17332988382,100050.464,185746.63732988382,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","04","01","  ",{"$nulls":4},"Beamline Pwr Supplies - (Dipole Type)                       ",{"$nulls":6},280,15197,22208.144235552,15926.456,38134.600235552,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","04","01","01",{"$nulls":4},"10kw Power Supply - (Solenoid 1)                            ",{"$nulls":6},56,0,4441.6288471104,0,4441.6288471104,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","04","01","01","IJ16040175","1.02.02.04.01","CB2020401",null,"Perform Solenoid 1 PS 10KW Pre-Install Qual Test","2006-10-10","2006-11-06","S","C","SL_PCE1","Hrs",16,null,1808.5041051264,null,1808.5041051264,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","K. Luchini"]
["1","02","02","04","01","01","IJ16040175","1.02.02.04.01","CB2020401",null,"Perform Solenoid 1 PS 10KW Pre-Install Qual Test","2006-10-10","2006-11-06","S","C","SL_PCCA1","Hrs",40,null,2633.1247419839997,null,2633.1247419839997,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","K. Luchini"]
["1","02","02","04","01","02",{"$nulls":4},"30kw Power Supply - (Solenoid 2)                            ",{"$nulls":6},56,15197,4441.6288471104,15926.456,20368.0848471104,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","04","01","02","IJ16040288","1.02.02.04.01","CB2020401",null,"Perform Solenoid 2 PS 15KW Pre-Install Qual Test","2006-10-10","2006-11-06","S","C","SL_PCE1","Hrs",16,null,1808.5041051264,null,1808.5041051264,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","K. Luchini"]
["1","02","02","04","01","02","IJ16040288","1.02.02.04.01","CB2020401",null,"Perform Solenoid 2 PS 15KW Pre-Install Qual Test","2006-10-10","2006-11-06","S","C","SL_PCCA1","Hrs",40,null,2633.1247419839997,null,2633.1247419839997,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","K. Luchini"]
["1","02","02","04","01","02","IJ16040208","1.02.02.04.01","LB2020401",null,"30kw Power Supply - (Solenoid 2)","2006-08-01","2006-08-28",null,"C","SL_MSEG1","$$",null,15197,null,15926.456,15926.456,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","K. Luchini"]
["1","02","02","04","01","03",{"$nulls":4},"2kw Power Supply - (B0.5 Spect)                             "]
["1","02","02","04","01","04",{"$nulls":4},"15kw Power Supply - (B1-2)                                  ",{"$nulls":6},56,0,4441.6288471104,0,4441.6288471104,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","04","01","04","IJ16040488","1.02.02.04.01","CB2020401",null,"Perform BX011-BX02 PS 15KW Pre-Install Qual Test","2006-10-10","2006-11-06","S","C","SL_PCE1","Hrs",16,null,1808.5041051264,null,1808.5041051264,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","K. Luchini"]
["1","02","02","04","01","04","IJ16040488","1.02.02.04.01","CB2020401",null,"Perform BX011-BX02 PS 15KW Pre-Install Qual Test","2006-10-10","2006-11-06","S","C","SL_PCCA1","Hrs",40,null,2633.1247419839997,null,2633.1247419839997,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","K. Luchini"]
["1","02","02","04","01","05",{"$nulls":4},"15kw Power Supply - (B3 Spect)                              ",{"$nulls":6},56,0,4441.6288471104,0,4441.6288471104,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","04","01","05","IJ16040588","1.02.02.04.01","CB2020401",null,"Perform BXS Spect  PS 15KW Pre-Install Qual Test","2006-10-10","2006-11-06","S","C","SL_PCE1","Hrs",16,null,1808.5041051264,null,1808.5041051264,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","K. Luchini"]
["1","02","02","04","01","05","IJ16040588","1.02.02.04.01","CB2020401",null,"Perform BXS Spect  PS 15KW Pre-Install Qual Test","2006-10-10","2006-11-06","S","C","SL_PCCA1","Hrs",40,null,2633.1247419839997,null,2633.1247419839997,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","K. Luchini"]
["1","02","02","04","01","06",{"$nulls":4},"10kw Power Supply - (New)                                   ",{"$nulls":6},56,0,4441.6288471104,0,4441.6288471104,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","04","01","06","IJ16041262","1.02.02.04.01","CB2020401",null,"Perform Wiggler PS 10KW Pre-Install Qual","2006-10-10","2006-11-06","S","C","SL_PCE1","Hrs",16,null,1808.5041051264,null,1808.5041051264,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","K. Luchini"]
["1","02","02","04","01","06","IJ16041262","1.02.02.04.01","CB2020401",null,"Perform Wiggler PS 10KW Pre-Install Qual","2006-10-10","2006-11-06","S","C","SL_PCCA1","Hrs",40,null,2633.1247419839997,null,2633.1247419839997,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","K. Luchini"]
["1","02","02","04","02","  ",{"$nulls":4},"Power Supply Controls                                       "]
["1","02","02","04","03","  ",{"$nulls":4},"Beamline Pwr Supplies - (Trim Type)                         ",{"$nulls":6},224,0,17766.5153884416,0,17766.5153884416,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","04","03","01",{"$nulls":4},"12Amp Power Supply - (MCOR_1)                               ",{"$nulls":6},56,0,4441.6288471104,0,4441.6288471104,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","04","03","01","IJ16040688","1.02.02.04.03","CB2020403",null,"Perform MCOR_1 Pre-Install Qual Test","2006-10-10","2006-11-06","S","C","SL_PCE1","Hrs",16,null,1808.5041051264,null,1808.5041051264,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","K. Luchini"]
["1","02","02","04","03","01","IJ16040688","1.02.02.04.03","CB2020403",null,"Perform MCOR_1 Pre-Install Qual Test","2006-10-10","2006-11-06","S","C","SL_PCCA1","Hrs",40,null,2633.1247419839997,null,2633.1247419839997,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","K. Luchini"]
["1","02","02","04","03","02",{"$nulls":4},"30Amp Power Supply - (MCOR_2)                               ",{"$nulls":6},56,0,4441.6288471104,0,4441.6288471104,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","04","03","02","IJ16040725","1.02.02.04.03","CB2020403",null,"Perform MCOR_2 Pre-Install Qual Test","2006-10-10","2006-11-06","S","C","SL_PCE1","Hrs",16,null,1808.5041051264,null,1808.5041051264,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","K. Luchini"]
["1","02","02","04","03","02","IJ16040725","1.02.02.04.03","CB2020403",null,"Perform MCOR_2 Pre-Install Qual Test","2006-10-10","2006-11-06","S","C","SL_PCCA1","Hrs",40,null,2633.1247419839997,null,2633.1247419839997,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","K. Luchini"]
["1","02","02","04","03","03",{"$nulls":4},"30Amp Power Supply - (MCOR_3)                               ",{"$nulls":6},56,0,4441.6288471104,0,4441.6288471104,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","04","03","03","IJ16040888","1.02.02.04.03","CB2020403",null,"Perform MCOR_3 Pre-Install Qual Test","2006-10-10","2006-11-06","S","C","SL_PCE1","Hrs",16,null,1808.5041051264,null,1808.5041051264,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","K. Luchini"]
["1","02","02","04","03","03","IJ16040888","1.02.02.04.03","CB2020403",null,"Perform MCOR_3 Pre-Install Qual Test","2006-10-10","2006-11-06","S","C","SL_PCCA1","Hrs",40,null,2633.1247419839997,null,2633.1247419839997,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","K. Luchini"]
["1","02","02","04","03","04",{"$nulls":4},"30Amp Power Supply - (MCOR_4)                               ",{"$nulls":6},56,0,4441.6288471104,0,4441.6288471104,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","04","03","04","IJ16040988","1.02.02.04.03","CB2020403",null,"Perform MCOR_4 Pre-Install Qual Test","2006-10-10","2006-11-06","S","C","SL_PCE1","Hrs",16,null,1808.5041051264,null,1808.5041051264,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","K. Luchini"]
["1","02","02","04","03","04","IJ16040988","1.02.02.04.03","CB2020403",null,"Perform MCOR_4 Pre-Install Qual Test","2006-10-10","2006-11-06","S","C","SL_PCCA1","Hrs",40,null,2633.1247419839997,null,2633.1247419839997,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","K. Luchini"]
["1","02","02","04","04","  ",{"$nulls":4},"Beamline Pwr Supply - Misc Hdwr                             ",{"$nulls":6},689,80271,45721.51370589022,84124.008,129845.52170589023,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","04","04","","IJ16041300","1.02.02.04.04","CB2020404",null,"Integ Rack HW & Internal AC Wiring - S20","2006-11-01","2006-11-14","S","C","SL_PCEF1","Hrs",135,null,8354.008175237997,null,8354.008175237997,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","M. Ortega"]
["1","02","02","04","04","","IJ16041305","1.02.02.04.04","CB2020404",null,"Integ Rack Mount Pwr Supplies&Intra Cables - S20","2006-09-26","2006-10-09","S","C","SL_PCEF1","Hrs",68,null,4166.931750854399,null,4166.931750854399,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","M. Ortega"]
["1","02","02","04","04","","IJ16041315","1.02.02.04.04","CB2020404",null,"Integ Rack/Crate Mount Cntrls&Intra-Cables - S20","2006-09-26","2006-11-06","S","C","SL_PCEF1","Hrs",270,null,16656.382201149652,null,16656.382201149652,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","M. Ortega"]
["1","02","02","04","04","","IJ16041320","1.02.02.04.04","CB2020404",null,"Perform Pre-Install Testing Controls - S20","2006-11-21","2006-12-13","S","C","SL_CCA1","Hrs",120,null,7899.374225951999,null,7899.374225951999,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","M. Ortega"]
["1","02","02","04","04","","IJ16041104","1.02.02.04.04","LB2020404",null,"Captar Documents","2006-08-15","2006-10-10","S","C","SL_PCCA1","Hrs",4,null,257.7122262961714,null,257.7122262961714,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","M. Ortega"]
["1","02","02","04","04","","IJ16041116","1.02.02.04.04","LB2020404",null,"Cableplant and Rack Hardware","2006-08-01","2006-08-28",null,"C","SL_MSEG1","$$",null,32571,null,34134.408,34134.408,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","M. Ortega"]
["1","02","02","04","04","","IJ16041158","1.02.02.04.04","LB2020404",null,"AWARD: Contract - Single Bay Racks (DC/I&C","2006-08-01","2006-08-01","S","C","SL_AW1","$$",null,25200,null,26409.6,26409.6,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.2,1.1,3,3,"2G","M. Ortega"]
["1","02","02","04","04","","IJ16041159","1.02.02.04.04","LB2020404",null,"Vendor Fab/Assy - Single Bay Racks","2006-08-02","2006-08-29","S","C","SA_MSSC1","$$",null,25200,null,26409.6,26409.6,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","M. Ortega"]
["1","02","02","04","04","","IJ16041168","1.02.02.04.04","LB2020404",null,"AWARD: Contract - Double Bay Racks","2006-08-01","2006-08-01","S","C","SL_AW1","$$",null,22500,null,23580,23580,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.2,1.1,3,3,"2G","M. Ortega"]
["1","02","02","04","04","","IJ16041169","1.02.02.04.04","LB2020404",null,"Vendor Fab/Assy - Double Bay Racks","2006-08-02","2006-08-30","S","C","SA_MSSC1","$$",null,22500,null,23580,23580,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","M. Ortega"]
["1","02","02","04","04","","IJ16041100","1.02.02.04.04","PB2020404",null,"Design Cableplant and Racks","2006-08-01","2006-08-28",null,"C","SL_PCE1","Hrs",54,null,5949.026661599999,null,5949.026661599999,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","M. Ortega"]
["1","02","02","04","04","","IJ16041100","1.02.02.04.04","PB2020404",null,"Design Cableplant and Racks","2006-08-01","2006-08-28",null,"C","SL_PCCA1","Hrs",38,null,2438.0784648,null,2438.0784648,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","M. Ortega"]
["1","02","02","04","05","  ",{"$nulls":4},"Magnet Interlock Protection System                          "]
["1","02","02","05","  ","  ",{"$nulls":4},"LLRF Controls                                               ",{"$nulls":6},0,263226,0,283033.230048,283033.230048,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","05","01","  ",{"$nulls":4},"Readback & Controls - RF Gun LLRF & Temperature             ",{"$nulls":6},0,263226,0,283033.230048,283033.230048,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","05","01","","IJ501_0111","1.02.02.05.01","CBBIJ20501",null,"RCV: 1 RF Reference System","2006-10-30","2006-10-30",null,"C","SL_MSEG1","$$",null,49007,null,52694.678736,52694.678736,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","R. Akre"]
["1","02","02","05","01","","IJ501_0113","1.02.02.05.01","CBBIJ20501",null,"RCV: 1Solid Stat Sub-Booster","2006-10-30","2006-10-30",null,"C","SL_MSEG1","$$",null,1885,null,2026.84248,2026.84248,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","R. Akre"]
["1","02","02","05","01","","IJ501_0115","1.02.02.05.01","CBBIJ20501",null,"RCV: 1Bunch Length Monitor Interface","2006-10-30","2006-10-30",null,"C","SL_MSEG1","$$",null,9424,null,10133.137152,10133.137152,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","R. Akre"]
["1","02","02","05","01","","IJ501_0117","1.02.02.05.01","CBBIJ20501",null,"RCV: 1 RF Gun Temperature Feedback","2006-10-30","2006-10-30",null,"C","SL_MSEG1","$$",null,4712,null,5066.568576,5066.568576,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","R. Akre"]
["1","02","02","05","01","","IJ501_0119","1.02.02.05.01","CBBIJ20501",null,"RCV: 1 Beam Phase Monitor x2","2006-10-30","2006-10-30",null,"C","SL_MSEG1","$$",null,4712,null,5066.568576,5066.568576,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","R. Akre"]
["1","02","02","05","01","","IJ501_0121","1.02.02.05.01","CBBIJ20501",null,"RCV: 15 PADs with RF head","2006-10-30","2006-10-30",null,"C","SL_MSEG1","$$",null,70684,null,76002.829632,76002.829632,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","R. Akre"]
["1","02","02","05","01","","IJ501_0123","1.02.02.05.01","CBBIJ20501",null,"RCV: 15 PACs with RF head","2006-10-30","2006-10-30",null,"C","SL_MSEG1","$$",null,70684,null,76002.829632,76002.829632,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","R. Akre"]
["1","02","02","05","01","","IJ501_0125","1.02.02.05.01","CBBIJ20501",null,"RCV: 1 RF Cables","2006-10-30","2006-10-30",null,"C","SL_MSEG1","$$",null,9424,null,10133.137152,10133.137152,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","R. Akre"]
["1","02","02","05","01","","IJ501_0127","1.02.02.05.01","CBBIJ20501",null,"RCV: 1 X-Band LLRF System","2006-10-30","2006-10-30",null,"C","SL_MSEG1","$$",null,188,null,202.146624,202.146624,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","R. Akre"]
["1","02","02","05","01","","IJ501_0129","1.02.02.05.01","CBBIJ20501",null,"RCV: 2 Network","2006-10-30","2006-10-30",null,"C","SL_MSEG1","$$",null,377,null,405.368496,405.368496,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","R. Akre"]
["1","02","02","05","01","","IJ501_0131","1.02.02.05.01","CBBIJ20501",null,"RCV: 2 PPS Vacuum Interlock","2006-10-30","2006-10-30",null,"C","SL_MSEG1","$$",null,17907,null,19254.465936,19254.465936,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","R. Akre"]
["1","02","02","05","01","","IJ501_0133","1.02.02.05.01","CBBIJ20501",null,"RCV: 1 BCS Sub-Booster Interface Trig","2006-10-30","2006-10-30",null,"C","SL_MSEG1","$$",null,7917,null,8512.738416,8512.738416,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","R. Akre"]
["1","02","02","05","01","","IJ501_0145","1.02.02.05.01","CBBIJ20501",null,"RCV: 1 EVR","2006-10-30","2006-10-30",null,"C","SL_MSEG1","$$",null,2733,null,2938.652784,2938.652784,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","R. Akre"]
["1","02","02","05","01","","IJ501_0155","1.02.02.05.01","CBBIJ20501",null,"RCV: 1 Binary I/O","2006-10-30","2006-10-30",null,"C","SL_MSEG1","$$",null,377,null,405.368496,405.368496,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","R. Akre"]
["1","02","02","05","01","","IJ501_0165","1.02.02.05.01","CBBIJ20501",null,"RCV:Motorola 6100","2006-10-30","2006-10-30",null,"C","SL_MSEG1","$$",null,5278,null,5675.158944,5675.158944,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","R. Akre"]
["1","02","02","05","01","","IJ501_0175","1.02.02.05.01","CBBIJ20501",null,"RCV: IOC Crate 21 Slots","2006-10-30","2006-10-30",null,"C","SL_MSEG1","$$",null,7917,null,8512.738416,8512.738416,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","R. Akre"]
["1","02","02","05","02","  ",{"$nulls":4},"Readback & Controls - L0 LLRF                               "]
["1","02","02","05","03","  ",{"$nulls":4},"Readback & Controls - Transverse Cavity LLRF                "]
["1","02","02","05","04","  ",{"$nulls":4},"S-Band Cavity Controls                                      "]
["1","02","02","05","05","  ",{"$nulls":4},"EO Phase Controls                                           "]
["1","02","02","06","  ","  ",{"$nulls":4},"E-Beam Diagnostics Controls                                 ",{"$nulls":6},3531,215453,303684.26009559823,226056.3248,529740.5848955982,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","06","01","  ",{"$nulls":4},"Controls - Wire Scanners                                    ",{"$nulls":6},216,26688,17973.224453131195,27969.024,45942.2484531312,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","06","01","","IJ601_0120","1.02.02.06.01","CBBIJ20601",null,"RCV: 5 PMTs","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,2400,null,2515.2,2515.2,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,2,3,"2G","D. Murray"]
["1","02","02","06","01","","IJ601_0123","1.02.02.06.01","CBBIJ20601",null,"RCV: 5 Charge Integrating ADC","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,3300,null,3458.4,3458.4,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,2,3,"2G","D. Murray"]
["1","02","02","06","01","","IJ601_0130","1.02.02.06.01","CBBIJ20601",null,"RCV: 7 Motor Contrlr/ Drives/Power Supplies","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,8820,null,9243.36,9243.36,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,2,3,"2G","D. Murray"]
["1","02","02","06","01","","IJ601_0133","1.02.02.06.01","CBBIJ20601",null,"RCV: 1 LVDT","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,4848,null,5080.704000000001,5080.704000000001,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,2,3,"2G","D. Murray"]
["1","02","02","06","01","","IJ601_0140","1.02.02.06.01","CBBIJ20601",null,"RCV: 1 EVR","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,1740,null,1823.52,1823.52,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,2,3,"2G","D. Murray"]
["1","02","02","06","01","","IJ601_0150","1.02.02.06.01","CBBIJ20601",null,"RCV:Motorola 6100","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,2100,null,2200.8,2200.8,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,2,3,"2G","D. Murray"]
["1","02","02","06","01","","IJ601_0153","1.02.02.06.01","CBBIJ20601",null,"RCV: IOC Crate 7 Slots","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,3480,null,3647.04,3647.04,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,2,3,"2G","D. Murray"]
["1","02","02","06","01","","IJ601_0155","1.02.02.06.01","CBBIJ20601",null,"Injector Hardware Fab","2006-08-30","2006-09-27",null,"C","SL_CT1","Hrs",48,null,2895.0429023999995,null,2895.0429023999995,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","D. Murray"]
["1","02","02","06","01","","IJ601_0155","1.02.02.06.01","CBBIJ20601",null,"Injector Hardware Fab","2006-08-30","2006-09-27",null,"C","SL_CE1","Hrs",24,null,2644.0118495999996,null,2644.0118495999996,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","D. Murray"]
["1","02","02","06","01","","IJ601_0160","1.02.02.06.01","CBBIJ20601",null,"Injector Integration and Test","2006-09-28","2006-10-04",null,"C","SL_CT1","Hrs",72,null,4399.017690196799,null,4399.017690196799,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"2G","D. Murray"]
["1","02","02","06","01","","IJ601_0160","1.02.02.06.01","CBBIJ20601",null,"Injector Integration and Test","2006-09-28","2006-10-04",null,"C","SL_CE1","Hrs",72,null,8035.152010934399,null,8035.152010934399,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"2G","D. Murray"]
["1","02","02","06","02","  ",{"$nulls":4},"Controls - BPM                                              ",{"$nulls":6},1547,84405,133568.6551086877,88456.44,222025.0951086877,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","06","02","","IJ602_0110","1.02.02.06.02","CBBIJ20602",null,"Injector Control Software","2006-08-01","2006-08-28",null,"C","SL_CP1","Hrs",51,null,4096.4788854,null,4096.4788854,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,5,3,"2G","P. Bong"]
["1","02","02","06","02","","IJ602_0120","1.02.02.06.02","CBBIJ20602",null,"RCV: 16 BPM Front End Electronics","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,27200,null,28505.6,28505.6,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,2,3,"2G","P. Bong"]
["1","02","02","06","02","","IJ602_0130","1.02.02.06.02","CBBIJ20602",null,"RCV: 8 Echotek","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,27200,null,28505.6,28505.6,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,2,3,"2G","P. Bong"]
["1","02","02","06","02","","IJ602_0140","1.02.02.06.02","CBBIJ20602",null,"RCV: 2 EVRs","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,4930,null,5166.64,5166.64,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,2,3,"2G","P. Bong"]
["1","02","02","06","02","","IJ602_0150","1.02.02.06.02","CBBIJ20602",null,"RCV: 2 Interrack Cables","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,425,null,445.4,445.4,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","P. Bong"]
["1","02","02","06","02","","IJ602_0160","1.02.02.06.02","CBBIJ20602",null,"RCV: 2 Binary I/Os","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,850,null,890.8,890.8,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","P. Bong"]
["1","02","02","06","02","","IJ602_0170","1.02.02.06.02","CBBIJ20602",null,"RCV: 2 Motorola 6100","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,9520,null,9976.96,9976.96,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,2,3,"2G","P. Bong"]
["1","02","02","06","02","","IJ602_0173","1.02.02.06.02","CBBIJ20602",null,"RCV: 2 IOC Crate - 21 Slot","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,14280,null,14965.44,14965.44,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,2,3,"2G","P. Bong"]
["1","02","02","06","02","","IJ602_0175","1.02.02.06.02","CBBIJ20602",null,"Injector Hardware Fab","2006-08-30","2006-09-28",null,"C","SL_CT1","Hrs",136,null,8202.621556799999,null,8202.621556799999,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,3,"2G","P. Bong"]
["1","02","02","06","02","","IJ602_0175","1.02.02.06.02","CBBIJ20602",null,"Injector Hardware Fab","2006-08-30","2006-09-28",null,"C","SL_CE1","Hrs",136,null,14982.733814399999,null,14982.733814399999,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,3,"2G","P. Bong"]
["1","02","02","06","02","","IJ602_0180","1.02.02.06.02","CBBIJ20602",null,"Injector Integration and Test","2006-09-29","2006-12-11",null,"C","SL_CT1","Hrs",544,null,33640.18701590425,null,33640.18701590425,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,3,"2G","P. Bong"]
["1","02","02","06","02","","IJ602_0180","1.02.02.06.02","CBBIJ20602",null,"Injector Integration and Test","2006-09-29","2006-12-11",null,"C","SL_CP1","Hrs",136,null,11200.184791110445,null,11200.184791110445,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,3,"2G","P. Bong"]
["1","02","02","06","02","","IJ602_0180","1.02.02.06.02","CBBIJ20602",null,"Injector Integration and Test","2006-09-29","2006-12-11",null,"C","SL_CE1","Hrs",544,null,61446.449045073,null,61446.449045073,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,3,"2G","P. Bong"]
["1","02","02","06","03","  ",{"$nulls":4},"Controls - Toroids                                          ",{"$nulls":6},800,27700,69737.7696528857,29029.6,98767.36965288571,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","06","03","","IJ603_0105","1.02.02.06.03","CBBIJ20603",null,"Injector Rack Layout and Wiring","2006-08-01","2006-08-15",null,"C","SL_CE1","Hrs",100,null,11016.71604,null,11016.71604,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","M. Cecere"]
["1","02","02","06","03","","IJ603_0105","1.02.02.06.03","CBBIJ20603",null,"Injector Rack Layout and Wiring","2006-08-01","2006-08-15",null,"C","SL_CCA1","Hrs",100,null,6415.995959999999,null,6415.995959999999,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","M. Cecere"]
["1","02","02","06","03","","IJ603_0120","1.02.02.06.03","CBBIJ20603",null,"RCV: 3 EVRs","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,12000,null,12576,12576,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,2,3,"2G","M. Cecere"]
["1","02","02","06","03","","IJ603_0130","1.02.02.06.03","CBBIJ20603",null,"RCV: 1 Crate/CPU/PMC Spa n","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,8000,null,8384,8384,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,2,3,"2G","M. Cecere"]
["1","02","02","06","03","","IJ603_0140","1.02.02.06.03","CBBIJ20603",null,"RCV: 1 I/O","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,6700,null,7021.6,7021.6,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,2,3,"2G","M. Cecere"]
["1","02","02","06","03","","IJ603_0150","1.02.02.06.03","CBBIJ20603",null,"RCV: Injector Interrack Cables","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,1000,null,1048,1048,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"2G","M. Cecere"]
["1","02","02","06","03","","IJ603_0170","1.02.02.06.03","CBBIJ20603",null,"Injector Hardware Fab","2006-08-30","2006-11-22",null,"C","SL_CT1","Hrs",100,null,6128.415223354284,null,6128.415223354284,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,3,"2G","M. Cecere"]
["1","02","02","06","03","","IJ603_0170","1.02.02.06.03","CBBIJ20603",null,"Injector Hardware Fab","2006-08-30","2006-11-22",null,"C","SL_CE1","Hrs",100,null,11194.032707691427,null,11194.032707691427,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,3,"2G","M. Cecere"]
["1","02","02","06","03","","IJ603_0180","1.02.02.06.03","CBBIJ20603",null,"Injector Integration and Test","2006-11-27","2006-12-01",null,"C","SL_CT1","Hrs",200,null,12376.308407759996,null,12376.308407759996,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,3,"2G","M. Cecere"]
["1","02","02","06","03","","IJ603_0180","1.02.02.06.03","CBBIJ20603",null,"Injector Integration and Test","2006-11-27","2006-12-01",null,"C","SL_CE1","Hrs",200,null,22606.30131408,null,22606.30131408,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,3,"2G","M. Cecere"]
["1","02","02","06","05","  ",{"$nulls":4},"Controls - Profile Monitors                                 ",{"$nulls":6},56,31560,4892.877932183999,33336.4608,38229.338732184,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","06","05","","IJ605_0105","1.02.02.06.05","CBBIJ20605",null,"Injector Rack Layout and Wiring","2006-08-17","2006-09-18",null,"C","SL_CE1","Hrs",8,null,881.3372831999999,null,881.3372831999999,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","S. Peng"]
["1","02","02","06","05","","IJ605_0105","1.02.02.06.05","CBBIJ20605",null,"Injector Rack Layout and Wiring","2006-08-17","2006-09-18",null,"C","SL_CCA1","Hrs",8,null,513.2796768,null,513.2796768,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","S. Peng"]
["1","02","02","06","05","","IJ605_0120","1.02.02.06.05","CBBIJ20605",null,"RCV: 8 Injector Profile Monitor Cameras","2006-10-17","2006-10-17",null,"C","SL_MSEG1","$$",null,9600,null,10322.380799999999,10322.380799999999,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","S. Peng"]
["1","02","02","06","05","","IJ605_0123","1.02.02.06.05","CBBIJ20605",null,"RCV: 8 PMC Interfaced Cables","2006-09-15","2006-09-15",null,"C","SL_MSEG1","$$",null,8320,null,8719.36,8719.36,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,2,3,"2G","S. Peng"]
["1","02","02","06","05","","IJ605_0130","1.02.02.06.05","CBBIJ20605",null,"RCV: 2 Smart Lenses","2006-09-15","2006-09-15",null,"C","SL_MSEG1","$$",null,480,null,503.04,503.04,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,2,3,"2G","S. Peng"]
["1","02","02","06","05","","IJ605_0133","1.02.02.06.05","CBBIJ20605",null,"RCV: 4 IOCs CPU/EVR/Span","2006-09-15","2006-09-15",null,"C","SL_MSEG1","$$",null,8960,null,9390.08,9390.08,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,2,3,"2G","S. Peng"]
["1","02","02","06","05","","IJ605_0140","1.02.02.06.05","CBBIJ20605",null,"RCV: Injector Interrack Cables","2006-09-15","2006-09-15",null,"C","SL_MSEG1","$$",null,200,null,209.6,209.6,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,2,3,"2G","S. Peng"]
["1","02","02","06","05","","IJ605_0143","1.02.02.06.05","CBBIJ20605",null,"RCV: 1 IOC Crate","2006-09-15","2006-09-15",null,"C","SL_MSEG1","$$",null,4000,null,4192,4192,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,3,3,"2G","S. Peng"]
["1","02","02","06","05","","IJ605_0145","1.02.02.06.05","CBBIJ20605",null,"Injector Hardware Fab","2006-10-18","2006-11-15",null,"C","SL_CT1","Hrs",4,null,247.5261681551999,null,247.5261681551999,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,2,3,"2G","S. Peng"]
["1","02","02","06","05","","IJ605_0145","1.02.02.06.05","CBBIJ20605",null,"Injector Hardware Fab","2006-10-18","2006-11-15",null,"C","SL_CE1","Hrs",4,null,452.1260262816,null,452.1260262816,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,2,3,"2G","S. Peng"]
["1","02","02","06","05","","IJ605_0150","1.02.02.06.05","CBBIJ20605",null,"Injector Integration and Test","2006-11-16","2006-11-22",null,"C","SL_CT1","Hrs",16,null,990.1046726207996,null,990.1046726207996,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","S. Peng"]
["1","02","02","06","05","","IJ605_0150","1.02.02.06.05","CBBIJ20605",null,"Injector Integration and Test","2006-11-16","2006-11-22",null,"C","SL_CE1","Hrs",16,null,1808.5041051264,null,1808.5041051264,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","S. Peng"]
["1","02","02","06","06","  ",{"$nulls":4},"Controls - E/O Diagnostics                                  "]
["1","02","02","06","12","  ",{"$nulls":4},"Controls - Movable Collimator                               ",{"$nulls":6},360,14500,30044.023976735996,15196,45240.023976735996,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","06","12","","IJ612_0115","1.02.02.06.12","CBBIJ20612",null,"RCV: 5 PMTs","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,4000,null,4192,4192,null,null,0,null,0,0,{"$nulls":10},0,0,1,1,2,3,"2G","D. Murray"]
["1","02","02","06","12","","IJ612_0135","1.02.02.06.12","CBBIJ20612",null,"RCV: 5 Motor Contrlr/ Drives/Power Supplies","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,10500,null,11004,11004,null,null,0,null,0,0,{"$nulls":10},0,0,1,1,1,3,"2G","D. Murray"]
["1","02","02","06","12","","IJ612_0180","1.02.02.06.12","CBBIJ20612",null,"Injector Hardware Fab","2006-08-31","2006-09-28",null,"C","SL_CT1","Hrs",80,null,4825.071503999999,null,4825.071503999999,null,0,null,0,null,0,{"$nulls":10},0.1,0,1.1,1,3,3,"2G","D. Murray"]
["1","02","02","06","12","","IJ612_0180","1.02.02.06.12","CBBIJ20612",null,"Injector Hardware Fab","2006-08-31","2006-09-28",null,"C","SL_CE1","Hrs",40,null,4406.686416,null,4406.686416,null,0,null,0,null,0,{"$nulls":10},0.1,0,1.1,1,3,3,"2G","D. Murray"]
["1","02","02","06","12","","IJ612_0185","1.02.02.06.12","CBBIJ20612",null,"Injector Integration and Test","2006-09-29","2006-10-05",null,"C","SL_CT1","Hrs",120,null,7363.059115103997,null,7363.059115103997,null,0,null,0,null,0,{"$nulls":10},0.1,0,1.1,1,3,3,"2G","D. Murray"]
["1","02","02","06","12","","IJ612_0185","1.02.02.06.12","CBBIJ20612",null,"Injector Integration and Test","2006-09-29","2006-10-05",null,"C","SL_CE1","Hrs",120,null,13449.206941632001,null,13449.206941632001,null,0,null,0,null,0,{"$nulls":10},0.1,0,1.1,1,3,3,"2G","D. Murray"]
["1","02","02","06","14","  ",{"$nulls":4},"Controls - Faraday Cups                                     ",{"$nulls":6},144,500,12513.444731567999,524,13037.444731567999,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","06","14","","IJ614_110","1.02.02.06.14","CBB20614",null,"Injector Controls FC Rack Layout and Wiring","2006-08-17","2006-09-14",null,"C","SL_CE1","Hrs",16,null,1762.6745663999998,null,1762.6745663999998,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","S. Peng"]
["1","02","02","06","14","","IJ614_110","1.02.02.06.14","CBB20614",null,"Injector Controls FC Rack Layout and Wiring","2006-08-17","2006-09-14",null,"C","SL_CCA1","Hrs",16,null,1026.5593536,null,1026.5593536,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","S. Peng"]
["1","02","02","06","14","","IJ614_145","1.02.02.06.14","CBB20614",null,"RCV: Injector Interrack Cables","2006-09-15","2006-09-15",null,"C","SL_MSEG1","$$",null,500,null,524,524,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","S. Peng"]
["1","02","02","06","14","","IJ614_150","1.02.02.06.14","CBB20614",null,"Injector Faraday Cups Hardware Fab","2006-09-18","2006-09-29",null,"C","SL_CT1","Hrs",16,null,965.0143007999998,null,965.0143007999998,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","S. Peng"]
["1","02","02","06","14","","IJ614_150","1.02.02.06.14","CBB20614",null,"Injector Faraday Cups Hardware Fab","2006-09-18","2006-09-29",null,"C","SL_CE1","Hrs",16,null,1762.6745663999998,null,1762.6745663999998,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","S. Peng"]
["1","02","02","06","14","","IJ614_155","1.02.02.06.14","CBB20614",null,"Injector Faraday Cups Integration and Test","2006-10-02","2006-10-06",null,"C","SL_CT1","Hrs",40,null,2475.261681551999,null,2475.261681551999,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","S. Peng"]
["1","02","02","06","14","","IJ614_155","1.02.02.06.14","CBB20614",null,"Injector Faraday Cups Integration and Test","2006-10-02","2006-10-06",null,"C","SL_CE1","Hrs",40,null,4521.260262816,null,4521.260262816,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","S. Peng"]
["1","02","02","06","15","  ",{"$nulls":4},"Controls - Tune-Up Dump                                     ",{"$nulls":6},264,14200,22402.826699616002,14881.6,37284.426699616,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","06","15","","IJ615_0105","1.02.02.06.15","CBBIJ20615",null,"Injector Rack Layout and Wiring","2006-09-01","2006-09-29",null,"C","SL_CE1","Hrs",16,null,1762.6745663999998,null,1762.6745663999998,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","TBD"]
["1","02","02","06","15","","IJ615_0105","1.02.02.06.15","CBBIJ20615",null,"Injector Rack Layout and Wiring","2006-09-01","2006-09-29",null,"C","SL_CCA1","Hrs",16,null,1026.5593536,null,1026.5593536,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","TBD"]
["1","02","02","06","15","","IJ615_0110","1.02.02.06.15","CBBIJ20615",null,"Injector Control Software","2006-10-02","2006-10-31",null,"C","SL_CP1","Hrs",40,null,3296.460656016,null,3296.460656016,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","TBD"]
["1","02","02","06","15","","IJ615_0120","1.02.02.06.15","CBBIJ20615",null,"RCV: 1 Crate/CPU/PMC Span","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,7000,null,7336,7336,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,2,3,"2G","TBD"]
["1","02","02","06","15","","IJ615_0130","1.02.02.06.15","CBBIJ20615",null,"RCV: 1 I/O","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,7000,null,7336,7336,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,2,3,"2G","TBD"]
["1","02","02","06","15","","IJ615_0140","1.02.02.06.15","CBBIJ20615",null,"RCV: 1 Injector Interrack Cables","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,200,null,209.6,209.6,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","TBD"]
["1","02","02","06","15","","IJ615_0165","1.02.02.06.15","CBBIJ20615",null,"Injector Hardware Fab","2006-08-30","2006-09-28",null,"C","SL_CT1","Hrs",16,null,965.0143007999998,null,965.0143007999998,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","TBD"]
["1","02","02","06","15","","IJ615_0165","1.02.02.06.15","CBBIJ20615",null,"Injector Hardware Fab","2006-08-30","2006-09-28",null,"C","SL_CE1","Hrs",16,null,1762.6745663999998,null,1762.6745663999998,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","TBD"]
["1","02","02","06","15","","IJ615_0170","1.02.02.06.15","CBBIJ20615",null,"Injector Integration and Test","2006-11-01","2006-11-07",null,"C","SL_CT1","Hrs",40,null,2475.261681551999,null,2475.261681551999,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","TBD"]
["1","02","02","06","15","","IJ615_0170","1.02.02.06.15","CBBIJ20615",null,"Injector Integration and Test","2006-11-01","2006-11-07",null,"C","SL_CP1","Hrs",80,null,6592.921312032,null,6592.921312032,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","TBD"]
["1","02","02","06","15","","IJ615_0170","1.02.02.06.15","CBBIJ20615",null,"Injector Integration and Test","2006-11-01","2006-11-07",null,"C","SL_CE1","Hrs",40,null,4521.260262816,null,4521.260262816,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","TBD"]
["1","02","02","06","16","  ",{"$nulls":4},"Controls - Cherenkov Radiation Detector                     ",{"$nulls":6},144,15900,12551.437540789713,16663.2,29214.637540789714,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","06","16","","IJ616_0105","1.02.02.06.16","CBBIJ20616",null,"Injector Rack Layout and Wiring","2006-08-17","2006-09-14",null,"C","SL_CE1","Hrs",16,null,1762.6745663999998,null,1762.6745663999998,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","S. Peng"]
["1","02","02","06","16","","IJ616_0105","1.02.02.06.16","CBBIJ20616",null,"Injector Rack Layout and Wiring","2006-08-17","2006-09-14",null,"C","SL_CCA1","Hrs",16,null,1026.5593536,null,1026.5593536,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","S. Peng"]
["1","02","02","06","16","","IJ616_0120","1.02.02.06.16","CBBIJ20616",null,"RCV: 1 Crate/CPU/EVR","2006-09-15","2006-09-15",null,"C","SL_MSEG1","$$",null,7000,null,7336,7336,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,2,3,"2G","S. Peng"]
["1","02","02","06","16","","IJ616_0130","1.02.02.06.16","CBBIJ20616",null,"RCV: 1 Pneumatic I/O","2006-09-15","2006-09-15",null,"C","SL_MSEG1","$$",null,2000,null,2096,2096,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,2,3,"2G","S. Peng"]
["1","02","02","06","16","","IJ616_0140","1.02.02.06.16","CBBIJ20616",null,"RCV: 1 Injector Interrack Cables","2006-09-15","2006-09-15",null,"C","SL_MSEG1","$$",null,1000,null,1048,1048,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","S. Peng"]
["1","02","02","06","16","","IJ616_0150","1.02.02.06.16","CBBIJ20616",null,"RCV: 2 Actuators (motion control from AM01)","2006-09-15","2006-09-15",null,"C","SL_MSEG1","$$",null,2500,null,2620,2620,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,2,3,"2G","S. Peng"]
["1","02","02","06","16","","IJ616_0160","1.02.02.06.16","CBBIJ20616",null,"RCV: 2 Long Haul Cables","2006-09-15","2006-09-15",null,"C","SL_MSEG1","$$",null,3400,null,3563.2,3563.2,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","S. Peng"]
["1","02","02","06","16","","IJ616_0170","1.02.02.06.16","CBBIJ20616",null,"Injector Hardware Fab","2006-09-18","2006-10-16",null,"C","SL_CT1","Hrs",16,null,978.4555714182854,null,978.4555714182854,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","S. Peng"]
["1","02","02","06","16","","IJ616_0170","1.02.02.06.16","CBBIJ20616",null,"Injector Hardware Fab","2006-09-18","2006-10-16",null,"C","SL_CE1","Hrs",16,null,1787.2261050034285,null,1787.2261050034285,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","S. Peng"]
["1","02","02","06","16","","IJ616_0180","1.02.02.06.16","CBBIJ20616",null,"Injector Integration and Test","2006-10-17","2006-10-23",null,"C","SL_CT1","Hrs",40,null,2475.261681551999,null,2475.261681551999,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","S. Peng"]
["1","02","02","06","16","","IJ616_0180","1.02.02.06.16","CBBIJ20616",null,"Injector Integration and Test","2006-10-17","2006-10-23",null,"C","SL_CE1","Hrs",40,null,4521.260262816,null,4521.260262816,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","S. Peng"]
["1","02","02","08","  ","  ",{"$nulls":4},"Timing Controls                                             ",{"$nulls":6},0,117500,0,123140,123140,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","08","","","IJ208_0115","1.02.02.08","CBBIJ20208",null,"RCV: 1 EVG","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,3900,null,4087.2,4087.2,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","P. Krejcik"]
["1","02","02","08","","","IJ208_0120","1.02.02.08","CBBIJ20208",null,"RCV: 4 EVR","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,11600,null,12156.8,12156.8,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","P. Krejcik"]
["1","02","02","08","","","IJ208_0125","1.02.02.08","CBBIJ20208",null,"RCV: 8 EVG Distribution","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,76000,null,79648,79648,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","P. Krejcik"]
["1","02","02","08","","","IJ208_0130","1.02.02.08","CBBIJ20208",null,"RCV: 8 EVR Transition Modules","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,12000,null,12576,12576,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","P. Krejcik"]
["1","02","02","08","","","IJ208_0135","1.02.02.08","CBBIJ20208",null,"RCV: 1 Motorola 6100","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,5600,null,5868.8,5868.8,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","P. Krejcik"]
["1","02","02","08","","","IJ208_0140","1.02.02.08","CBBIJ20208",null,"RCV: 1 IOC Crate - 21 Slots","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,8400,null,8803.2,8803.2,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","P. Krejcik"]
["1","02","02","09","  ","  ",{"$nulls":4},"Vacuum Controls                                             ",{"$nulls":6},494,99190,39463.96241399039,103951.12,143415.0824139904,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","09","","","IJ209_0101","1.02.02.09","CBBIJ20209",null,"Injector Control Vacuum Software","2006-08-17","2006-09-14",null,"C","SL_CP1","Hrs",52,null,4176.802000799999,null,4176.802000799999,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","S. Schuh"]
["1","02","02","09","","","IJ209_0106","1.02.02.09","CBBIJ20209",null,"Injector Control Vacuum H/W in House FAB","2006-08-17","2006-09-14",null,"C","SL_CT1","Hrs",104,null,6272.592955199999,null,6272.592955199999,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","S. Schuh"]
["1","02","02","09","","","IJ209_0106","1.02.02.09","CBBIJ20209",null,"Injector Control Vacuum H/W in House FAB","2006-08-17","2006-09-14",null,"C","SL_CE1","Hrs",26,null,2864.3461703999997,null,2864.3461703999997,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","S. Schuh"]
["1","02","02","09","","","IJ209_0116","1.02.02.09","CBBIJ20209",null,"RCV: 8 Injector Ion Guage Controllers","2006-09-15","2006-09-15",null,"C","SL_MSEG1","$$",null,13000,null,13624,13624,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,2,3,"2G","S. Schuh"]
["1","02","02","09","","","IJ209_0126","1.02.02.09","CBBIJ20209",null,"RCV: 18 Injector Ion Pump Power Supplies","2006-09-15","2006-09-15",null,"C","SL_MSEG1","$$",null,43290,null,45367.92,45367.92,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,2,3,"2G","S. Schuh"]
["1","02","02","09","","","IJ209_0136","1.02.02.09","CBBIJ20209",null,"RCV: 4 Injector Vacuum Valve Controllers","2006-09-15","2006-09-15",null,"C","SL_MSEG1","$$",null,10400,null,10899.2,10899.2,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,4,3,"2G","S. Schuh"]
["1","02","02","09","","","IJ209_0146","1.02.02.09","CBBIJ20209",null,"RCV: 1 Injector Vacuum Control IOC","2006-09-15","2006-09-15",null,"C","SL_MSEG1","$$",null,3250,null,3406,3406,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,2,3,"2G","S. Schuh"]
["1","02","02","09","","","IJ209_0156","1.02.02.09","CBBIJ20209",null,"RCV: 1 Injector Vacuum Control I/O (PLC)","2006-09-15","2006-09-15",null,"C","SL_MSEG1","$$",null,29250,null,30654,30654,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,2,3,"2G","S. Schuh"]
["1","02","02","09","","","IJ209_0171","1.02.02.09","CBBIJ20209",null,"Injector Vacuum Integration and Test","2006-09-18","2006-10-13",null,"C","SL_CT1","Hrs",78,null,4763.15618646067,null,4763.15618646067,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","S. Schuh"]
["1","02","02","09","","","IJ209_0171","1.02.02.09","CBBIJ20209",null,"Injector Vacuum Integration and Test","2006-09-18","2006-10-13",null,"C","SL_CP1","Hrs",156,null,12686.78546930995,null,12686.78546930995,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","S. Schuh"]
["1","02","02","09","","","IJ209_0171","1.02.02.09","CBBIJ20209",null,"Injector Vacuum Integration and Test","2006-09-18","2006-10-13",null,"C","SL_CE1","Hrs",78,null,8700.279631819776,null,8700.279631819776,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","S. Schuh"]
["1","02","02","10","  ","  ",{"$nulls":4},"Software & Controls Infrastructure                          ",{"$nulls":6},0,23133,0,24243.384,24243.384,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","10","01","  ",{"$nulls":4},"Low Level Application Software                              "]
["1","02","02","10","02","  ",{"$nulls":4},"High Level Application Software                             "]
["1","02","02","10","03","  ",{"$nulls":4},"Data Communications                                         ",{"$nulls":6},0,16000,0,16768,16768,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","10","03","","IJ21003015","1.02.02.10.03","CBBIJ21003",null,"RCV: Cisco 3550-24 hubs (4)","2006-08-30","2006-08-30",null,"C","SL_MSEG1","$$",null,16000,null,16768,16768,null,null,0,null,0,0,{"$nulls":10},0.35,0,1.25,1.1,5,3,"2G","T. Lahey"]
["1","02","02","10","04","  ",{"$nulls":4},"Computers & Crates                                          ",{"$nulls":6},0,7133,0,7475.384,7475.384,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","10","04","","IJ02080410","1.02.02.10.04","LB2021005",null,"RCV: Infrastructure Comp, Crates H/W & Cable","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,7133,null,7475.384,7475.384,null,null,0,null,0,0,{"$nulls":10},0.35,0,1.25,1.1,5,3,"2G","H. Shoaee"]
["1","02","02","11","  ","  ",{"$nulls":4},"EPICS VXI Control Modules                                   "]
["1","02","02","12","  ","  ",{"$nulls":4},"Laser Controls                                              ",{"$nulls":6},204,9000,12915.66706439554,9432,22347.66706439554,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","12","01","  ",{"$nulls":4},"Controls - Alignment Laser                                  "]
["1","02","02","12","02","  ",{"$nulls":4},"Controls - Gun Laser                                        ",{"$nulls":6},204,9000,12915.66706439554,9432,22347.66706439554,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","02","12","02","","IJ02040210","1.02.02.12.02","CB2021202",null,"RCV: Procured parts - Gun Laser Controls","2006-08-15","2006-08-15","S","C","SL_MSEG1","$$",null,9000,null,9432,9432,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,2,3,"2G","S. Peng"]
["1","02","02","12","02","","IJ02040215","1.02.02.12.02","CB2021202",null,"Integrate and Test Gun Laser Controls","2006-08-16","2006-11-08",null,"C","SL_PCEF1","Hrs",84,null,5125.914712274398,null,5125.914712274398,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"2G","S. Peng"]
["1","02","02","12","02","","IJ02040215","1.02.02.12.02","CB2021202",null,"Integrate and Test Gun Laser Controls","2006-08-16","2006-11-08",null,"C","SL_CCA1","Hrs",120,null,7789.7523521211415,null,7789.7523521211415,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"2G","S. Peng"]
["1","02","02","13","  ","  ",{"$nulls":4},"Laser Heater Controls                                       ",{"$nulls":6},60,84100,5247.391458276,90428.3568,95675.74825827598,null,60,84100,5247.391458276,90428.3568,95675.74825827598,0,null,0,null,95675.74825827598,null,0,null,0,null,null,18376.033624568998]
["1","02","02","13","","","IJ213_0115","1.02.02.13","CBBIJ20213",null,"RCV: 4 Camera","2007-06-15","2007-06-15",null,"C","SL_MSEG1","$$",null,12000,null,12902.976,12902.976,null,null,12000,null,12902.976,12902.976,{"$nulls":4},12902.976,1,{"$nulls":4},0.1,1290.2976,1,1.1,2,3,"2G","S. Peng"]
["1","02","02","13","","","IJ213_0125","1.02.02.13","CBBIJ20213",null,"RCV: 4 PMC Interface and Cables","2007-06-15","2007-06-15",null,"C","SL_MSEG1","$$",null,10400,null,11182.5792,11182.5792,null,null,10400,null,11182.5792,11182.5792,{"$nulls":4},11182.5792,1,{"$nulls":4},0.2,2236.51584,1.1,1.1,2,3,"2G","S. Peng"]
["1","02","02","13","","","IJ213_0135","1.02.02.13","CBBIJ20213",null,"RCV: 4 Interrack Cables","2007-06-15","2007-06-15",null,"C","SL_MSEG1","$$",null,500,null,537.624,537.624,null,null,500,null,537.624,537.624,{"$nulls":4},537.624,1,{"$nulls":4},0.25,134.406,1.15,1.1,3,3,"2G","S. Peng"]
["1","02","02","13","","","IJ213_0145","1.02.02.13","CBBIJ20213",null,"RCV: 1 Motor Drivers","2007-06-15","2007-06-15",null,"C","SL_MSEG1","$$",null,6500,null,6989.112,6989.112,null,null,6500,null,6989.112,6989.112,{"$nulls":4},6989.112,1,{"$nulls":4},0.2,1397.8224,1.1,1.1,2,3,"2G","S. Peng"]
["1","02","02","13","","","IJ213_0155","1.02.02.13","CBBIJ20213",null,"RCV: 8 Motor Drivers","2007-06-15","2007-06-15",null,"C","SL_MSEG1","$$",null,10400,null,11182.5792,11182.5792,null,null,10400,null,11182.5792,11182.5792,{"$nulls":4},11182.5792,1,{"$nulls":4},0.2,2236.51584,1.1,1.1,2,3,"2G","S. Peng"]
["1","02","02","13","","","IJ213_0165","1.02.02.13","CBBIJ20213",null,"RCV: 5 IOCs CPU/EVR/Span","2007-06-15","2007-06-15",null,"C","SL_MSEG1","$$",null,28000,null,30106.944,30106.944,null,null,28000,null,30106.944,30106.944,{"$nulls":4},30106.944,1,{"$nulls":4},0.2,6021.388800000001,1.1,1.1,2,3,"2G","S. Peng"]
["1","02","02","13","","","IJ213_0175","1.02.02.13","CBBIJ20213",null,"RCV: 1 IOC Crate","2007-06-15","2007-06-15",null,"C","SL_MSEG1","$$",null,10000,null,10752.48,10752.48,null,null,10000,null,10752.48,10752.48,{"$nulls":4},10752.48,1,{"$nulls":4},0.2,2150.496,1.1,1.1,2,3,"2G","S. Peng"]
["1","02","02","13","","","IJ213_0177","1.02.02.13","CBBIJ20213",null,"RCV: 1 UPS","2007-06-15","2007-06-15",null,"C","SL_MSEG1","$$",null,1800,null,1935.4464,1935.4464,null,null,1800,null,1935.4464,1935.4464,{"$nulls":4},1935.4464,1,{"$nulls":4},0.2,387.08928000000003,1.1,1.1,2,3,"2G","S. Peng"]
["1","02","02","13","","","IJ213_0179","1.02.02.13","CBBIJ20213",null,"RCV: 1 Function Generator","2007-06-15","2007-06-15",null,"C","SL_MSEG1","$$",null,4500,null,4838.616,4838.616,null,null,4500,null,4838.616,4838.616,{"$nulls":4},4838.616,1,{"$nulls":4},0.25,1209.654,1.15,1.1,2,3,"2G","S. Peng"]
["1","02","02","13","","","IJ213_0180","1.02.02.13","CBBIJ20213",null,"LTU Laser Heater Controls H/W Fab","2007-06-18","2007-07-16",null,"C","SL_CT1","Hrs",10,null,618.8154203879998,null,618.8154203879998,null,10,null,618.8154203879998,null,618.8154203879998,{"$nulls":4},618.8154203879998,1,{"$nulls":4},0.25,154.70385509699994,1.15,1.1,3,3,"2G","S. Peng"]
["1","02","02","13","","","IJ213_0180","1.02.02.13","CBBIJ20213",null,"LTU Laser Heater Controls H/W Fab","2007-06-18","2007-07-16",null,"C","SL_CE1","Hrs",10,null,1130.315065704,null,1130.315065704,null,10,null,1130.315065704,null,1130.315065704,{"$nulls":4},1130.315065704,1,{"$nulls":4},0.25,282.578766426,1.15,1.1,3,3,"2G","S. Peng"]
["1","02","02","13","","","IJ213_0185","1.02.02.13","CBBIJ20213",null,"LTU Laser Heater Contrls Integration and Test","2007-07-17","2007-07-30",null,"C","SL_CT1","Hrs",20,null,1237.6308407759996,null,1237.6308407759996,null,20,null,1237.6308407759996,null,1237.6308407759996,{"$nulls":4},1237.6308407759996,1,{"$nulls":4},0.25,309.4077101939999,1.15,1.1,3,3,"2G","S. Peng"]
["1","02","02","13","","","IJ213_0185","1.02.02.13","CBBIJ20213",null,"LTU Laser Heater Contrls Integration and Test","2007-07-17","2007-07-30",null,"C","SL_CE1","Hrs",20,null,2260.630131408,null,2260.630131408,null,20,null,2260.630131408,null,2260.630131408,{"$nulls":4},2260.630131408,1,{"$nulls":4},0.25,565.157532852,1.15,1.1,3,3,"2G","S. Peng"]
["1","02","03","  ","  ","  ",{"$nulls":4},"Injector Lasers                                             ",{"$nulls":6},4722,1221573,470989.0681828807,1260942.94474424,1277812.6601828814,null,241,111300,20769.052277496594,117639.9994736842,138409.05175118078,0,null,82596.08306073499,null,55812.96869044581,null,0,null,0,null,null,34602.262937795196]
["1","02","03","01","  ","  ",{"$nulls":4},"Drive Laser Support                                         ",{"$nulls":6},412,12800,78484.99107472981,14343.856661157028,78484.99107472981,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","03","01","01","  ",{"$nulls":4},"Drive Laser Support (ANL)                                   "]
["1","02","03","01","02","  ",{"$nulls":4},"Drive Laser Support (LLNL)                                  ",{"$nulls":6},412,12800,78484.99107472981,14343.856661157028,78484.99107472981,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","03","01","02","","IJ30128010","1.02.03.01.02","CBE2030102",null,"Modeling - modeling and validation (to compl)","2006-05-01","2006-12-29","L","C","LL_MSEG1","$$",null,12800,null,14343.856661157028,null,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.2,1.1,7,2,"2L"]
["1","02","03","01","02","","IJ30128020","1.02.03.01.02","CBE2030102",null,"Temporal Pulse Shaping - IR shaping (to compl)","2006-05-01","2006-12-29","L","C","LL_PHS1","Hrs",150,null,28574.632672838525,null,28574.632672838525,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.2,1.1,7,2,"2L"]
["1","02","03","01","02","","IJ30128040","1.02.03.01.02","CBE2030102",null,"UV Diagnostics - activate (to compl)","2006-05-01","2006-12-29","L","C","LL_PHS1","Hrs",12,null,2285.970613827082,null,2285.970613827082,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.2,1.1,7,2,"2L"]
["1","02","03","01","02","","IJ30128050","1.02.03.01.02","CBE2030102",null,"Shaping and Integration","2006-05-01","2006-12-29","L","C","LL_PHS1","Hrs",250,null,47624.38778806421,null,47624.38778806421,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.2,1.1,7,2,"2L"]
["1","02","03","02","  ","  ",{"$nulls":4},"Drive Laser System                                          ",{"$nulls":6},154,544898,15005.055265199999,544898,559903.0552652,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","03","02","","","IJ03020112","1.02.03.02","CBE20302",null,"Drive Laser-Milestone 3","2006-06-27","2006-06-27","S","C","SL_MSSY1","$$",null,435918,null,435918,435918,null,null,0,null,0,0,{"$nulls":10},0,0,1,1,7,3,"2L"]
["1","02","03","02","","","IJ03020122","1.02.03.02","CBE20302",null,"Drive Laser-Milestone 4","2006-10-16","2006-10-16","S","C","SL_MSSY1","$$",null,108980,null,108980,108980,null,null,0,null,0,0,{"$nulls":10},0.1,0,1.1,1,7,4,"2L"]
["1","02","03","02","","","IJ03020910","1.02.03.02","CBE20302",null,"Reviews of Vendor's Progress (to compl)","2006-05-01","2006-06-26","S","C","SL_QAO1","Hrs",14,null,942.5412612,null,942.5412612,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,7,3,"2L"]
["1","02","03","02","","","IJ03020910","1.02.03.02","CBE20302",null,"Reviews of Vendor's Progress (to compl)","2006-05-01","2006-06-26","S","C","SL_PHSS1","Hrs",70,null,6350.812776,null,6350.812776,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,7,3,"2L"]
["1","02","03","02","","","IJ03020910","1.02.03.02","CBE20302",null,"Reviews of Vendor's Progress (to compl)","2006-05-01","2006-06-26","S","C","SL_OE1","Hrs",70,null,7711.701227999999,null,7711.701227999999,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,7,3,"2L"]
["1","02","03","03","  ","  ",{"$nulls":4},"Drive Laser Diagnostics                                     ",{"$nulls":6},1068,318000,93701.81990067029,336114.2842105263,93701.81990067029,null,241,111300,20769.052277496594,117639.9994736842,138409.05175118078,0,null,82596.08306073499,null,55812.96869044581,null,0,null,0,null,null,34602.262937795196]
["1","02","03","03","","","IJ03030060","1.02.03.03","CBE20303","9242124","Assemble & Checkout: Drive Laser Diagnostics","2007-01-02","2007-01-05","S","C","SL_PHSS1","Hrs",40,null,3723.390804672,null,3723.390804672,null,12,null,1117.0172414016001,null,1117.0172414016001,{"$nulls":4},1117.0172414016001,1,{"$nulls":4},0.25,279.25431035040003,1.15,1.1,3,4,"2L"]
["1","02","03","03","","","IJ03030060","1.02.03.03","CBE20303","9242124","Assemble & Checkout: Drive Laser Diagnostics","2007-01-02","2007-01-05","S","C","SL_OT1","Hrs",400,null,24752.616815519992,null,24752.616815519992,null,120,null,7425.785044655997,null,7425.785044655997,{"$nulls":4},7425.785044655997,1,{"$nulls":4},0.25,1856.4462611639992,1.15,1.1,3,4,"2L"]
["1","02","03","03","","","IJ03030060","1.02.03.03","CBE20303","9242124","Assemble & Checkout: Drive Laser Diagnostics","2007-01-02","2007-01-05","S","C","SL_OE1","Hrs",200,null,22606.30131408,null,22606.30131408,null,60,null,6781.8903942239995,null,6781.8903942239995,{"$nulls":4},6781.8903942239995,1,{"$nulls":4},0.25,1695.4725985559999,1.15,1.1,3,4,"2L"]
["1","02","03","03","","","IJ03030905","1.02.03.03","CBE20303","9242124","Eng & Design of Drive Laser Diagnostics (Timing)","2006-05-01","2006-07-31","S","C","SL_PHSS1","Hrs",8,null,725.8071744,null,725.8071744,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,7,2,"2L"]
["1","02","03","03","","","IJ03030905","1.02.03.03","CBE20303","9242124","Eng & Design of Drive Laser Diagnostics (Timing)","2006-05-01","2006-07-31","S","C","SL_OE1","Hrs",14,null,1542.3402456,null,1542.3402456,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,7,2,"2L"]
["1","02","03","03","","","IJ03030905","1.02.03.03","CBE20303","9242124","Eng & Design of Drive Laser Diagnostics (Timing)","2006-05-01","2006-07-31","S","C","SL_MDD1","Hrs",14,null,1142.5626828,null,1142.5626828,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,7,2,"2L"]
["1","02","03","03","","","IJ03030910","1.02.03.03","CBE20303","9242124","Eng & Design of Cross Correlator","2006-05-01","2006-08-31","S","C","SL_PHS1","Hrs",80,null,5702.770655999999,null,5702.770655999999,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,2,"2L"]
["1","02","03","03","","","IJ03030910","1.02.03.03","CBE20303","9242124","Eng & Design of Cross Correlator","2006-05-01","2006-08-31","S","C","SL_OE1","Hrs",80,null,8813.372832,null,8813.372832,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,2,"2L"]
["1","02","03","03","","","IJ03030915","1.02.03.03","CBE20303","9242124","Procure Cross Correlator Components","2006-09-01","2006-12-01","S","C","SL_OE1","Hrs",20,null,2241.7443324822857,null,2241.7443324822857,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2L"]
["1","02","03","03","","","IJ03030920","1.02.03.03","CBE20303","9242124","Eng &Design of Drive Laser Diagnostics (general)","2006-05-01","2007-01-19","S","C","SL_PHSS1","Hrs",16,null,1467.399964912426,null,1467.399964912426,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,2,"2L"]
["1","02","03","03","","","IJ03030920","1.02.03.03","CBE20303","9242124","Eng &Design of Drive Laser Diagnostics (general)","2006-05-01","2007-01-19","S","C","SL_OE1","Hrs",28,null,3118.2249254389044,null,3118.2249254389044,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,2,"2L"]
["1","02","03","03","","","IJ03030920","1.02.03.03","CBE20303","9242124","Eng &Design of Drive Laser Diagnostics (general)","2006-05-01","2007-01-19","S","C","SL_MDD1","Hrs",28,null,2309.975017864699,null,2309.975017864699,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,2,"2L"]
["1","02","03","03","","","IJ03030925","1.02.03.03","CBE20303","9242124","Procure Drive Laser Diagnostics","2006-05-01","2006-12-15","S","C","SL_OE1","Hrs",140,null,15555.3131349,null,15555.3131349,null,49,null,5444.359597214999,null,5444.359597214999,null,null,3653.4518349732225,0.67,1790.907762241776,0.33,{"$nulls":4},0.25,1361.0898993037497,1.15,1.1,3,3,"2L"]
["1","02","03","03","","","IJ03030930","1.02.03.03","CBE20303","9242124","RCV: Drive Laser Diagnostics","2006-05-01","2006-12-15",null,"C","SL_MSEG1","$$",null,318000,null,336114.2842105263,null,null,null,111300,null,117639.9994736842,117639.9994736842,null,null,78942.63122576177,0.67,38697.36824792244,0.33,{"$nulls":4},0.25,29409.99986842105,1.15,1.1,3,3,"2L"]
["1","02","03","04","  ","  ",{"$nulls":4},"Timing Stability Monitoring                                 ",{"$nulls":6},618,120600,55635.83888051094,126388.8,182024.63888051096,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","03","04","","","IJ03040025","1.02.03.04","CBE20304",null,"Assemble & C/O: Timing Stability Mon Apparatus","2006-12-01","2007-03-13","S","C","SL_PHSS1","Hrs",100,null,9308.477011680001,null,9308.477011680001,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,3,4,"2L"]
["1","02","03","04","","","IJ03040025","1.02.03.04","CBE20304",null,"Assemble & C/O: Timing Stability Mon Apparatus","2006-12-01","2007-03-13","S","C","SL_OT1","Hrs",190,null,11757.492987371996,null,11757.492987371996,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,3,4,"2L"]
["1","02","03","04","","","IJ03040025","1.02.03.04","CBE20304",null,"Assemble & C/O: Timing Stability Mon Apparatus","2006-12-01","2007-03-13","S","C","SL_OE1","Hrs",120,null,13563.780788447999,null,13563.780788447999,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,3,4,"2L"]
["1","02","03","04","","","IJ03040025","1.02.03.04","CBE20304",null,"Assemble & C/O: Timing Stability Mon Apparatus","2006-12-01","2007-03-13","S","C","SL_KE1","Hrs",40,null,4521.260262816,null,4521.260262816,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,3,4,"2L"]
["1","02","03","04","","","IJ03040905","1.02.03.04","CBE20304",null,"Eng & Dsn of Timing Stability Monitoring App","2006-05-01","2006-11-30","S","C","SL_PHSS1","Hrs",80,null,7311.229452547605,null,7311.229452547605,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,4,2,"2L"]
["1","02","03","04","","","IJ03040905","1.02.03.04","CBE20304",null,"Eng & Dsn of Timing Stability Monitoring App","2006-05-01","2006-11-30","S","C","SL_OE1","Hrs",20,null,2219.48036952338,null,2219.48036952338,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,4,2,"2L"]
["1","02","03","04","","","IJ03040905","1.02.03.04","CBE20304",null,"Eng & Dsn of Timing Stability Monitoring App","2006-05-01","2006-11-30","S","C","SL_MDD1","Hrs",20,null,1644.1867821701408,null,1644.1867821701408,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,4,2,"2L"]
["1","02","03","04","","","IJ03040910","1.02.03.04","CBE20304",null,"Proc Timing Stability Apparatus","2006-05-01","2006-09-20","S","C","SL_MSEG1","$$",null,120600,null,126388.8,126388.8,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"2L"]
["1","02","03","04","","","IJ03040915","1.02.03.04","CBE20304",null,"Eng&Dsn of the Osc timing stability measurement","2006-05-01","2006-10-30",null,"C","SL_OE1","Hrs",16,null,1769.9770753179428,null,1769.9770753179428,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,4,2,"2L"]
["1","02","03","04","","","IJ03040915","1.02.03.04","CBE20304",null,"Eng&Dsn of the Osc timing stability measurement","2006-05-01","2006-10-30",null,"C","SL_KE1","Hrs",32,null,3539.9541506358855,null,3539.9541506358855,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,4,2,"2L"]
["1","02","03","05","  ","  ",{"$nulls":4},"Steering Stability Feedback & Msmts                         ",{"$nulls":6},60,16275,4856.477462152105,17056.2,21912.677462152104,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","03","05","","","IJ03050905","1.02.03.05","CBE20305",null,"Procure Steering Stability Apparatus","2006-05-01","2006-07-31","S","C","SL_MSEG1","$$",null,16275,null,17056.2,17056.2,null,null,0,null,0,0,{"$nulls":10},0,0,1,1,7,3,"2L"]
["1","02","03","05","","","IJ03050910","1.02.03.05","CBE20305",null,"Assemble & Checkout: Steering Stabilization App","2006-05-01","2006-12-15","S","C","SL_OT1","Hrs",36,null,2189.8523533121047,null,2189.8523533121047,null,0,null,0,null,0,{"$nulls":10},0.1,0,1.1,1,3,4,"2L"]
["1","02","03","05","","","IJ03050910","1.02.03.05","CBE20305",null,"Assemble & Checkout: Steering Stabilization App","2006-05-01","2006-12-15","S","C","SL_OE1","Hrs",24,null,2666.6251088399995,null,2666.6251088399995,null,0,null,0,null,0,{"$nulls":10},0.1,0,1.1,1,3,4,"2L"]
["1","02","03","06","  ","  ",{"$nulls":4},"Pre Amp Low Power Comp                                      ",{"$nulls":6},380,32000,35111.82767076,34407.936,69519.76367076,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","03","06","","","IJ03060000","1.02.03.06","CBE20306",null,"Define PreAmplifier Low Power Comp Specs","2007-01-22","2007-02-02","S","C","SL_PHSS1","Hrs",20,null,1861.695402336,null,1861.695402336,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.15,1.05,4,2,"2L"]
["1","02","03","06","","","IJ03060000","1.02.03.06","CBE20306",null,"Define PreAmplifier Low Power Comp Specs","2007-01-22","2007-02-02","S","C","SL_OE1","Hrs",20,null,2260.630131408,null,2260.630131408,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.15,1.05,4,2,"2L"]
["1","02","03","06","","","IJ03060005","1.02.03.06","CBE20306",null,"Design PreAmplifier Low Power Comp","2007-02-05","2007-04-02","S","C","SL_PHSS1","Hrs",30,null,2792.543103504,null,2792.543103504,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.15,1.05,4,2,"2L"]
["1","02","03","06","","","IJ03060005","1.02.03.06","CBE20306",null,"Design PreAmplifier Low Power Comp","2007-02-05","2007-04-02","S","C","SL_OE1","Hrs",30,null,3390.9451971119997,null,3390.9451971119997,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.15,1.05,4,2,"2L"]
["1","02","03","06","","","IJ03060005","1.02.03.06","CBE20306",null,"Design PreAmplifier Low Power Comp","2007-02-05","2007-04-02","S","C","SL_MDD1","Hrs",160,null,13397.363572032,null,13397.363572032,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.15,1.05,4,2,"2L"]
["1","02","03","06","","","IJ03060065","1.02.03.06","CBE20306",null,"Procure Low Power Compressor System Parts","2007-04-03","2007-06-26","S","C","SL_MSSC1","$$",null,32000,null,34407.936,34407.936,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.15,1.05,4,3,"2L"]
["1","02","03","06","","","IJ03060075","1.02.03.06","CBE20306",null,"Fab (InHouse): Custom Low Power Compressor Parts","2007-04-03","2007-04-30","S","C","SL_MFMS1","Hrs",40,null,4412.12832,null,4412.12832,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.15,1.05,4,3,"2L"]
["1","02","03","06","","","IJ03060085","1.02.03.06","CBE20306",null,"Assemble: Low Power Compressor","2007-06-27","2007-07-25","S","C","SL_OT1","Hrs",40,null,2475.261681551999,null,2475.261681551999,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.15,1.05,4,4,"2L"]
["1","02","03","06","","","IJ03060085","1.02.03.06","CBE20306",null,"Assemble: Low Power Compressor","2007-06-27","2007-07-25","S","C","SL_OE1","Hrs",40,null,4521.260262816,null,4521.260262816,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.15,1.05,4,4,"2L"]
["1","02","03","07","  ","  ",{"$nulls":4},"Transport to Tunnel & Relay Optics                          "]
["1","02","03","08","  ","  ",{"$nulls":4},"UV Launch, Conditioning & Diagnostics                       ",{"$nulls":6},710,88000,62173.247718476065,92955.85963898918,91517.24771847606,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","03","08","","","IJ03080040","1.02.03.08","CBE20308",null,"FAB (inhouse): Custom Parts","2006-05-01","2006-10-03","S","C","SL_MFMS1","Hrs",60,null,6452.644031999999,null,6452.644031999999,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,7,3,"2L"]
["1","02","03","08","","","IJ03080047","1.02.03.08","CBE20308",null,"Procure Spatial Shaper and Custom Made Parts","2006-05-01","2007-02-02","S","C","SL_MSEG1","$$",null,60000,null,63611.85963898917,null,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,4,3,"2L"]
["1","02","03","08","","","IJ03080055","1.02.03.08","CBE20308",null,"Assemble & C/O: UV Launch & Conditioning System","2006-09-18","2007-02-01","S","C","SL_PHSS1","Hrs",20,null,1857.1857915832943,null,1857.1857915832943,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,4,"2L"]
["1","02","03","08","","","IJ03080055","1.02.03.08","CBE20308",null,"Assemble & C/O: UV Launch & Conditioning System","2006-09-18","2007-02-01","S","C","SL_OT1","Hrs",160,null,9877.063282555762,null,9877.063282555762,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,4,"2L"]
["1","02","03","08","","","IJ03080055","1.02.03.08","CBE20308",null,"Assemble & C/O: UV Launch & Conditioning System","2006-09-18","2007-02-01","S","C","SL_OE1","Hrs",120,null,13530.925052964001,null,13530.925052964001,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,4,"2L"]
["1","02","03","08","","","IJ03080055","1.02.03.08","CBE20308",null,"Assemble & C/O: UV Launch & Conditioning System","2006-09-18","2007-02-01","S","C","SL_CE1","Hrs",40,null,4510.308350988,null,4510.308350988,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,4,"2L"]
["1","02","03","08","","","IJ03080905","1.02.03.08","CBE20308",null,"Eng & Dsn of the Laser Port Window","2006-06-01","2006-06-30","S","C","SL_OE1","Hrs",20,null,2203.343208,null,2203.343208,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,7,2,"2L"]
["1","02","03","08","","","IJ03080905","1.02.03.08","CBE20308",null,"Eng & Dsn of the Laser Port Window","2006-06-01","2006-06-30","S","C","SL_MDD1","Hrs",20,null,1632.2324039999999,null,1632.2324039999999,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,7,2,"2L"]
["1","02","03","08","","","IJ03080910","1.02.03.08","CBE20308",null,"Procure UV Launch,Conditioning & Diag HW","2006-05-01","2006-07-31","S","C","SL_MSEG1","$$",null,28000,null,29344,29344,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,7,3,"2L"]
["1","02","03","08","","","IJ03080920","1.02.03.08","CBE20308",null,"Create Assembly Drawings","2006-05-01","2006-10-20",null,"C","SL_MDD1","Hrs",80,null,6547.681309199442,null,6547.681309199442,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,2,"2L"]
["1","02","03","08","","","IJ03080925","1.02.03.08","CBE20308",null,"Release Drawings","2006-06-01","2006-06-30",null,"C","SL_MDD1","Hrs",30,null,2448.3486059999996,null,2448.3486059999996,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,7,2,"2L"]
["1","02","03","08","","","IJ03080930","1.02.03.08","CBE20308",null,"Eng & Dsn of UV Diagnostic","2006-05-01","2006-10-31","S","C","SL_MDD1","Hrs",160,null,13113.515681185574,null,13113.515681185574,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,2,"2L"]
["1","02","03","09","  ","  ",{"$nulls":4},"Load Lock Transport System                                  "]
["1","02","03","10","  ","  ",{"$nulls":4},"Visible Optical Transport & Optics                          "]
["1","02","03","11","  ","  ",{"$nulls":4},"LB Infrastructure & LB System Wide Items                    ",{"$nulls":6},540,42000,47566.67844240515,44241.35223356752,51758.67844240515,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","03","11","","","IJ03280030","1.02.03.11","CBE20311",null,"Assemble & C/O Optical Tables, Legs & Encl","2006-05-01","2006-07-31","S","C","SL_SEL1","Hrs",60,null,2736,null,2736,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.2,1.1,7,4,"2L"]
["1","02","03","11","","","IJ03280030","1.02.03.11","CBE20311",null,"Assemble & C/O Optical Tables, Legs & Encl","2006-05-01","2006-07-31","S","C","SL_OT1","Hrs",30,null,1809.4018139999996,null,1809.4018139999996,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.2,1.1,7,4,"2L"]
["1","02","03","11","","","IJ03280030","1.02.03.11","CBE20311",null,"Assemble & C/O Optical Tables, Legs & Encl","2006-05-01","2006-07-31","S","C","SL_OE1","Hrs",10,null,1101.671604,null,1101.671604,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.2,1.1,7,4,"2L"]
["1","02","03","11","","","IJ03280050","1.02.03.11","CBE20311",null,"Procure Laser Bay Equipment","2006-05-01","2006-10-31","S","C","SL_MSEG1","$$",null,30000,null,31574.006557377048,null,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.2,1.1,7,3,"2L"]
["1","02","03","11","","","IJ03280118","1.02.03.11","CBE20311",null,"Writing Final and Temporal SOP","2006-05-01","2006-10-31",null,"C","SL_OE1","Hrs",40,null,4425.469013838689,null,4425.469013838689,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.2,1.1,4,2,"2L"]
["1","02","03","11","","","IJ03280121","1.02.03.11","CBE20311",null,"Preparation for Final Laser Safety Review","2006-05-01","2006-10-31",null,"C","SL_OE1","Hrs",40,null,4425.469013838689,null,4425.469013838689,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.2,1.1,4,2,"2L"]
["1","02","03","11","","","IJ03280124","1.02.03.11","CBE20311",null,"Design Safety Equipment","2006-05-01","2006-10-31",null,"C","SL_OE1","Hrs",60,null,6638.203520758033,null,6638.203520758033,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.2,1.1,4,2,"2L"]
["1","02","03","11","","","IJ03280124","1.02.03.11","CBE20311",null,"Design Safety Equipment","2006-05-01","2006-10-31",null,"C","SL_MDD1","Hrs",120,null,9835.13676088918,null,9835.13676088918,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.2,1.1,4,2,"2L"]
["1","02","03","11","","","IJ03280127","1.02.03.11","CBE20311",null,"Procure Beam Path Enclosures","2006-08-01","2006-11-14",null,"C","SL_MSEG1","$$",null,8000,null,8475.345676190476,null,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.2,1.1,7,3,"2L"]
["1","02","03","11","","","IJ03280130","1.02.03.11","CBE20311",null,"Create and Release Assembly Drawings","2006-05-01","2006-11-30",null,"C","SL_MDD1","Hrs",80,null,6576.747128680563,null,6576.747128680563,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.2,1.1,4,2,"2L"]
["1","02","03","11","","","IJ03280133","1.02.03.11","CBE20311",null,"Procure Laser PPS","2006-05-01","2006-06-30",null,"C","SL_MSEG1","$$",null,4000,null,4192,4192,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.2,1.1,7,3,"2L"]
["1","02","03","11","","","IJ03280905","1.02.03.11","CBE20311",null,"Define Laser Bay Equipment","2006-05-01","2006-08-30","S","C","SL_OE1","Hrs",32,null,3525.3491327999996,null,3525.3491327999996,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.2,1.1,4,2,"2L"]
["1","02","03","11","","","IJ03280905","1.02.03.11","CBE20311",null,"Define Laser Bay Equipment","2006-05-01","2006-08-30","S","C","SL_MDD1","Hrs",8,null,652.8929615999999,null,652.8929615999999,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.2,1.1,4,2,"2L"]
["1","02","03","11","","","IJ03280910","1.02.03.11","CBE20311",null,"Assemble Beam Path Enclosures","2006-08-01","2006-09-07","S","C","SL_ME1","Hrs",60,null,5840.337491999999,null,5840.337491999999,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.2,1.1,4,4,"2L"]
["1","02","03","12","  ","  ",{"$nulls":4},"Alignment Laser                                             ",{"$nulls":6},180,20000,17623.633412016,21504.96,39128.593412015995,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","03","12","","","IJ03290000","1.02.03.12","CBE20312",null,"Define alignment Laser System requirements","2007-02-02","2007-02-08","S","C","SL_PHSS1","Hrs",10,null,930.847701168,null,930.847701168,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,2,"2L"]
["1","02","03","12","","","IJ03290000","1.02.03.12","CBE20312",null,"Define alignment Laser System requirements","2007-02-02","2007-02-08","S","C","SL_OE1","Hrs",20,null,2260.630131408,null,2260.630131408,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,2,"2L"]
["1","02","03","12","","","IJ03290030","1.02.03.12","CBE20312",null,"Procure alignment Laser System off-shelf parts","2007-03-26","2007-06-18","S","C","SL_MSEG1","$$",null,20000,null,21504.96,21504.96,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,4,3,"2L"]
["1","02","03","12","","","IJ03290040","1.02.03.12","CBE20312",null,"Fab (In House) Alignmt Laser System parts","2007-03-26","2007-05-04","S","C","SL_MFMS1","Hrs",40,null,4412.12832,null,4412.12832,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,3,"2L"]
["1","02","03","12","","","IJ03290055","1.02.03.12","CBE20312",null,"Assemble: alignment Laser system","2007-06-19","2007-07-02","S","C","SL_OT1","Hrs",20,null,1237.6308407759996,null,1237.6308407759996,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,4,"2L"]
["1","02","03","12","","","IJ03290055","1.02.03.12","CBE20312",null,"Assemble: alignment Laser system","2007-06-19","2007-07-02","S","C","SL_OE1","Hrs",20,null,2260.630131408,null,2260.630131408,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,4,"2L"]
["1","02","03","12","","","IJ03290060","1.02.03.12","CBE20312",null,"Test : alignment Laser system","2007-07-03","2007-07-10","S","C","SL_OT1","Hrs",10,null,618.8154203879998,null,618.8154203879998,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,4,"2L"]
["1","02","03","12","","","IJ03290060","1.02.03.12","CBE20312",null,"Test : alignment Laser system","2007-07-03","2007-07-10","S","C","SL_OE1","Hrs",10,null,1130.315065704,null,1130.315065704,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,4,"2L"]
["1","02","03","12","","","IJ03290905","1.02.03.12","CBE20312",null,"Develop alignment Laser System Engrg & Design","2007-02-09","2007-03-23","S","C","SL_OE1","Hrs",20,null,2260.630131408,null,2260.630131408,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,2,"2L"]
["1","02","03","12","","","IJ03290905","1.02.03.12","CBE20312",null,"Develop alignment Laser System Engrg & Design","2007-02-09","2007-03-23","S","C","SL_MDD1","Hrs",30,null,2512.005669756,null,2512.005669756,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,2,"2L"]
["1","02","03","13","  ","  ",{"$nulls":4},"Light path to Streak Camera                                 ",{"$nulls":6},600,27000,60829.49835596034,29031.696,89861.19435596034,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","03","13","","","IJ03300040","1.02.03.13","CBE20313",null,"Procure Light Path off shelf parts","2007-02-02","2007-04-27","S","C","SL_MSEG1","$$",null,19000,null,20429.712,20429.712,null,null,0,null,0,0,{"$nulls":10},0.4,0,1.2,1.2,4,3,"2L"]
["1","02","03","13","","","IJ03300080","1.02.03.13","CBE20313",null,"FAB: Light Path transport tube/enclosure/supts","2007-04-30","2007-06-11","S","C","SL_MFMS1","Hrs",300,null,33090.9624,null,33090.9624,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,4,3,"2L"]
["1","02","03","13","","","IJ03300085","1.02.03.13","CBE20313",null,"Proc Light Path transport tube/enclosure/supts","2007-02-02","2007-04-27","S","C","SL_MSEG1","$$",null,8000,null,8601.984,8601.984,null,null,0,null,0,0,{"$nulls":10},0.4,0,1.2,1.2,4,3,"2L"]
["1","02","03","13","","","IJ03300125","1.02.03.13","CBE20313",null,"Assemble: Light Path System","2007-06-12","2007-07-10","S","C","SL_OT1","Hrs",40,null,2475.261681551999,null,2475.261681551999,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,4,4,"2L"]
["1","02","03","13","","","IJ03300125","1.02.03.13","CBE20313",null,"Assemble: Light Path System","2007-06-12","2007-07-10","S","C","SL_OE1","Hrs",40,null,4521.260262816,null,4521.260262816,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,4,4,"2L"]
["1","02","03","13","","","IJ03300125","1.02.03.13","CBE20313",null,"Assemble: Light Path System","2007-06-12","2007-07-10","S","C","SL_MFAT1","Hrs",20,null,1723.68,null,1723.68,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,4,4,"2L"]
["1","02","03","13","","","IJ03300140","1.02.03.13","CBE20313",null,"Test: Light Path system","2007-07-11","2007-07-24","S","C","SL_OT1","Hrs",20,null,1237.6308407759996,null,1237.6308407759996,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,4,4,"2L"]
["1","02","03","13","","","IJ03300140","1.02.03.13","CBE20313",null,"Test: Light Path system","2007-07-11","2007-07-24","S","C","SL_OE1","Hrs",20,null,2260.630131408,null,2260.630131408,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,4,4,"2L"]
["1","02","03","13","","","IJ03300905","1.02.03.13","CBE20313",null,"Develop Light Path System Engrg & Design","2006-05-01","2007-02-01","S","C","SL_OE1","Hrs",80,null,8915.49299981426,null,8915.49299981426,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,4,2,"2L"]
["1","02","03","13","","","IJ03300905","1.02.03.13","CBE20313",null,"Develop Light Path System Engrg & Design","2006-05-01","2007-02-01","S","C","SL_MDD1","Hrs",80,null,6604.580039594086,null,6604.580039594086,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,4,2,"2L"]
["1","02","03","14","  ","  ",{"$nulls":4},"LSR HTR - Beam Conditioning Optics (Laser Bay)              "]
["1","02","03","15","  ","  ",{"$nulls":4},"LSR HTR - Transport Optics (Bay to Tunnel)                  "]
["1","02","03","16","  ","  ",{"$nulls":4},"LSR HTR - Photon Beam Diagnostics                           "]
["1","02","03","21","  ","  ",{"$nulls":4},"UV Conv Harmonic Generation Unit (Closed Account)           "]
["1","02","04","  ","  ","  ",{"$nulls":4},"Injector RF Subsystem                                       ",{"$nulls":6},4793,54000,399285.83564536896,56592,455877.83564536896,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","04","01","  ","  ",{"$nulls":4},"RF Gun & Load Lock                                          ",{"$nulls":6},2883,52000,213816.33894238796,54496,268312.33894238796,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","04","01","01","  ",{"$nulls":4},"RF Gun                                                      ",{"$nulls":6},2517,37000,183300.27019318796,38776,222076.27019318796,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","04","01","01","","IJ411_0010","1.02.04.01.01","CBE2040101",null,"Procure Extra Valve for RF Gun (cont)","2006-06-01","2006-06-30",null,"C","SL_MSEG1","$$",null,7000,null,7336,7336,null,null,0,null,0,0,{"$nulls":10},0.45,0,1.15,1.3,3,3,"2A"]
["1","02","04","01","01","","IJ411_0020","1.02.04.01.01","CBE2040101",null,"QC Machine Parts (cont)","2006-06-01","2006-06-30",null,"C","SL_MES1","Hrs",137,null,10721.307366,null,10721.307366,null,0,null,0,null,0,{"$nulls":10},0.45,0,1.15,1.3,3,3,"2A"]
["1","02","04","01","01","","IJ411_0030","1.02.04.01.01","CBE2040101",null,"Clean & Plate Machine Parts (cont)","2006-06-01","2006-06-30",null,"C","SL_MFPC1","Hrs",30,null,5063.4,null,5063.4,null,0,null,0,null,0,{"$nulls":10},0.45,0,1.15,1.3,3,3,"2A"]
["1","02","04","01","01","","IJ411_0040","1.02.04.01.01","CBE2040101",null,"Design Gun Hot Test (cont)","2006-06-01","2006-06-30",null,"C","SL_KE1","Hrs",42,null,4627.020736799999,null,4627.020736799999,null,0,null,0,null,0,{"$nulls":10},0.45,0,1.15,1.3,3,2,"2A"]
["1","02","04","01","01","","IJ411_0050","1.02.04.01.01","CBE2040101",null,"Design/Draft RF Hot Test Components","2006-05-01","2006-06-30",null,"C","SL_MDD1","Hrs",96,null,7834.715539199999,null,7834.715539199999,null,0,null,0,null,0,{"$nulls":10},0.45,0,1.15,1.3,3,2,"2A"]
["1","02","04","01","01","","IJ411_0060","1.02.04.01.01","CBE2040101",null,"Procure RF Hot Test Parts","2006-05-01","2006-08-31",null,"C","SL_MSEG1","$$",null,30000,null,31440,31440,null,null,0,null,0,0,{"$nulls":10},0.45,0,1.15,1.3,3,3,"2A"]
["1","02","04","01","01","","IJ411_0060","1.02.04.01.01","CBE2040101",null,"Procure RF Hot Test Parts","2006-05-01","2006-08-31",null,"C","SL_KCA1","Hrs",40,null,2566.3983839999996,null,2566.3983839999996,null,0,null,0,null,0,{"$nulls":10},0.45,0,1.15,1.3,3,3,"2A"]
["1","02","04","01","01","","IJ411_0070","1.02.04.01.01","CBE2040101",null,"Fabricate RF Gun #1","2006-06-01","2006-08-31","S","C","SL_KT1","Hrs",240,null,14475.214511999997,null,14475.214511999997,null,0,null,0,null,0,{"$nulls":10},0.45,0,1.15,1.3,3,3,"2A"]
["1","02","04","01","01","","IJ411_0080","1.02.04.01.01","CBE2040101",null,"Cold Test RF Gun #1","2006-06-01","2006-08-31","S","C","SL_KE1","Hrs",12,null,1322.0059247999998,null,1322.0059247999998,null,0,null,0,null,0,{"$nulls":10},0.45,0,1.15,1.3,3,3,"2A"]
["1","02","04","01","01","","IJ411_0110","1.02.04.01.01","CBE2040101",null,"Bake RF Gun #1","2006-08-02","2006-08-15","S","C","SL_MFAT1","Hrs",4,null,336,null,336,null,0,null,0,null,0,{"$nulls":10},0.45,0,1.15,1.3,3,3,"2A"]
["1","02","04","01","01","","IJ411_0115","1.02.04.01.01","CBE2040101",null,"Post Bake Assembly #1","2006-08-16","2006-08-18","S","C","SL_MFAT1","Hrs",30,null,2520,null,2520,null,0,null,0,null,0,{"$nulls":10},0.45,0,1.15,1.3,3,3,"2A"]
["1","02","04","01","01","","IJ411_0120","1.02.04.01.01","CBE2040101",null,"Hot Test RF Gun #1","2006-10-02","2006-11-28",null,"C","SL_KT1","Hrs",960,null,59406.280357247975,null,59406.280357247975,null,0,null,0,null,0,{"$nulls":10},0.45,0,1.15,1.3,3,3,"2A"]
["1","02","04","01","01","","IJ411_0120","1.02.04.01.01","CBE2040101",null,"Hot Test RF Gun #1","2006-10-02","2006-11-28",null,"C","SL_KE1","Hrs",240,null,27127.561576895998,null,27127.561576895998,null,0,null,0,null,0,{"$nulls":10},0.45,0,1.15,1.3,3,3,"2A"]
["1","02","04","01","01","","IJ411_013","1.02.04.01.01","CBE2040101",null,"Clean and Plate RF Hot Test Parts","2006-06-01","2006-08-31",null,"C","SL_MFPC1","Hrs",40,null,6751.2,null,6751.2,null,0,null,0,null,0,{"$nulls":10},0.45,0,1.15,1.3,3,3,"2A"]
["1","02","04","01","01","","IJ411_0130","1.02.04.01.01","CBE2040101",null,"Fabricate RF Hot Test Parts","2006-06-01","2006-08-31",null,"C","SL_KT1","Hrs",360,null,21712.821767999994,null,21712.821767999994,null,0,null,0,null,0,{"$nulls":10},0.45,0,1.15,1.3,3,3,"2A"]
["1","02","04","01","01","","IJ411_0140","1.02.04.01.01","CBE2040101",null,"Fabricate RF Gun #2","2006-06-01","2006-11-14","S","C","SL_KT1","Hrs",240,null,14574.971412010407,null,14574.971412010407,null,0,null,0,null,0,{"$nulls":10},0.45,0,1.15,1.3,3,3,"2A"]
["1","02","04","01","01","","IJ411_0150","1.02.04.01.01","CBE2040101",null,"Cold Test RF Gun #2","2006-06-01","2006-11-14","S","C","SL_KE1","Hrs",12,null,1331.1166162335612,null,1331.1166162335612,null,0,null,0,null,0,{"$nulls":10},0.45,0,1.15,1.3,3,3,"2A"]
["1","02","04","01","01","","IJ411_0160","1.02.04.01.01","CBE2040101",null,"Bake RF Gun #2","2006-11-15","2006-12-07","S","C","SL_MFAT1","Hrs",4,null,344.73600000000005,null,344.73600000000005,null,0,null,0,null,0,{"$nulls":10},0.45,0,1.15,1.3,3,3,"2A"]
["1","02","04","01","01","","IJ411_0170","1.02.04.01.01","CBE2040101",null,"Post Bake Assembly #2","2006-12-08","2007-01-08","S","C","SL_MFAT1","Hrs",30,null,2585.52,null,2585.52,null,0,null,0,null,0,{"$nulls":10},0.45,0,1.15,1.3,3,3,"2A"]
["1","02","04","01","02","  ",{"$nulls":4},"RF Gun Supports                                             ",{"$nulls":6},40,5000,3264.4648079999997,5240,8504.464808,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","04","01","02","","IJ401_2000","1.02.04.01.02","CBE2040102",null,"Design RF Gun Support (cont)","2006-05-01","2006-05-31","S","C","SL_MDD1","Hrs",40,null,3264.4648079999997,null,3264.4648079999997,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,3,2,"2A"]
["1","02","04","01","02","","IJ401_2020","1.02.04.01.02","CBE2040102",null,"Procure RF Gun Support","2006-06-01","2006-06-30","S","C","SL_MSEG1","$$",null,5000,null,5240,5240,null,null,0,null,0,0,{"$nulls":10},0,0,1,1,3,3,"2A"]
["1","02","04","01","03","  ",{"$nulls":4},"Gun Load Lock                                               "]
["1","02","04","01","04","  ",{"$nulls":4},"Gun Load Lock Supports                                      "]
["1","02","04","01","05","  ",{"$nulls":4},"Gun Solenoid                                                ",{"$nulls":6},160,0,12980.61744,0,12980.61744,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","04","01","05","","IJ401_5000","1.02.04.01.05","CBE2040105",null,"Perform Lab Tests on Sol Magnet Assembly","2006-05-01","2006-08-31","S","C","SL_MFAT1","Hrs",80,null,6720,null,6720,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.1,1.2,3,3,"2A"]
["1","02","04","01","05","","IJ401_5000","1.02.04.01.05","CBE2040105",null,"Perform Lab Tests on Sol Magnet Assembly","2006-05-01","2006-08-31","S","C","SL_MES1","Hrs",80,null,6260.61744,null,6260.61744,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.1,1.2,3,3,"2A"]
["1","02","04","01","06","  ",{"$nulls":4},"Gun Solenoid Supports                                       ",{"$nulls":6},166,10000,14270.986501199997,10480,24750.986501199997,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","04","01","06","","IJ401_6000","1.02.04.01.06","CBE2040106",null,"Design Solenoid Supports (cont)","2006-06-01","2006-06-30","S","C","SL_ME1","Hrs",40,null,3893.558327999999,null,3893.558327999999,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,3,2,"2A"]
["1","02","04","01","06","","IJ401_6000","1.02.04.01.06","CBE2040106",null,"Design Solenoid Supports (cont)","2006-06-01","2006-06-30","S","C","SL_MDD1","Hrs",120,null,9793.394423999998,null,9793.394423999998,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,3,2,"2A"]
["1","02","04","01","06","","IJ401_6020","1.02.04.01.06","CBE2040106",null,"Prep Bid Pak - Solenoid Supports","2006-06-01","2006-06-30","S","C","SL_ME1","Hrs",4,null,389.3558327999999,null,389.3558327999999,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,3,2,"2A"]
["1","02","04","01","06","","IJ401_6060","1.02.04.01.06","CBE2040106",null,"Evaluate Proposals - Solenoid Supports","2006-06-01","2006-06-30","S","C","SL_ME1","Hrs",2,null,194.67791639999996,null,194.67791639999996,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,3,3,"2A"]
["1","02","04","01","06","","IJ401_6080","1.02.04.01.06","CBE2040106",null,"Vendor Fab Solenoid Supports","2006-06-01","2006-06-30","S","C","SL_MSSC1","$$",null,10000,null,10480,10480,null,null,0,null,0,0,{"$nulls":10},0,0,1,1,3,3,"2A"]
["1","02","04","01","07","  ",{"$nulls":4},"Gun RF Feed                                                 "]
["1","02","04","01","08","  ",{"$nulls":4},"Gun RF Feed Supports                                        "]
["1","02","04","02","  ","  ",{"$nulls":4},"Cathode Processing (CP) Station                             "]
["1","02","04","02","01","  ",{"$nulls":4},"CP Cathode Assembly & Supports                              "]
["1","02","04","02","02","  ",{"$nulls":4},"CP Load Lock                                                "]
["1","02","04","02","03","  ",{"$nulls":4},"CP Load Lock Supports                                       "]
["1","02","04","02","04","  ",{"$nulls":4},"CP Station                                                  "]
["1","02","04","02","05","  ",{"$nulls":4},"Cathode Lab Infrastructure                                  "]
["1","02","04","03","  ","  ",{"$nulls":4},"S-Band Low Level Timing                                     "]
["1","02","04","03","01","  ",{"$nulls":4},"Controls Interface & Timing                                 "]
["1","02","04","03","02","  ",{"$nulls":4},"LLRF Phase Reference System                                 "]
["1","02","04","03","03","  ",{"$nulls":4},"LLRF Monitor & Control System                               "]
["1","02","04","03","04","  ",{"$nulls":4},"Beam Phase Monitor Cavity                                   "]
["1","02","04","03","05","  ",{"$nulls":4},"RF System S/W Development / Docs                            "]
["1","02","04","04","  ","  ",{"$nulls":4},"S-Band High Power System                                    "]
["1","02","04","04","01","  ",{"$nulls":4},"RF Gun High Power                                           "]
["1","02","04","04","02","  ",{"$nulls":4},"L0 High Power                                               "]
["1","02","04","04","03","  ",{"$nulls":4},"Transverse Cavity High Power                                "]
["1","02","04","05","  ","  ",{"$nulls":4},"Injector RF Waveguide Subsystem                             ",{"$nulls":6},1090,0,101173.27567426678,0,101173.27567426678,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","04","05","01","  ",{"$nulls":4},"RF Waveguides                                               ",{"$nulls":6},1090,0,101173.27567426678,0,101173.27567426678,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","04","05","01","","IJ405_1000","1.02.04.05.01","CBE2040501",null,"Fab Vault Waveguide (cont)","2006-05-01","2006-11-14",null,"C","SL_MVE1","Hrs",120,null,12491.79273384414,null,12491.79273384414,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"2A"]
["1","02","04","05","01","","IJ405_1000","1.02.04.05.01","CBE2040501",null,"Fab Vault Waveguide (cont)","2006-05-01","2006-11-14",null,"C","SL_MFAT1","Hrs",197,null,16644.096,null,16644.096,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"2A"]
["1","02","04","05","01","","IJ405_1020","1.02.04.05.01","CBE2040501",null,"Fab KG Waveguide (cont)","2006-05-01","2006-11-14",null,"C","SL_MVE1","Hrs",120,null,12491.79273384414,null,12491.79273384414,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"2A"]
["1","02","04","05","01","","IJ405_1020","1.02.04.05.01","CBE2040501",null,"Fab KG Waveguide (cont)","2006-05-01","2006-11-14",null,"C","SL_MFAT1","Hrs",254,null,21459.900426395943,null,21459.900426395943,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"2A"]
["1","02","04","05","01","","IJ405_1030","1.02.04.05.01","CBE2040501",null,"Post Process KG Waveguide (cont)","2006-05-01","2006-11-30",null,"C","SL_MVE1","Hrs",24,null,2502.1262700385346,null,2502.1262700385346,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"2A"]
["1","02","04","05","01","","IJ405_1040","1.02.04.05.01","CBE2040501",null,"Fab KG Supports (cont)","2006-06-01","2006-08-31",null,"C","SL_MFAT1","Hrs",82,null,6888,null,6888,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"2A"]
["1","02","04","05","01","","IJ405_1060","1.02.04.05.01","CBE2040501",null,"High Power Gun WG Conditioning","2006-08-01","2006-11-30",null,"C","SL_ME1","Hrs",9,null,887.3451607679999,null,887.3451607679999,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"2A"]
["1","02","04","05","01","","IJ405_1060","1.02.04.05.01","CBE2040501",null,"High Power Gun WG Conditioning","2006-08-01","2006-11-30",null,"C","SL_KT1","Hrs",24,null,1466.1837112319995,null,1466.1837112319995,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"2A"]
["1","02","04","05","01","","IJ405_1060","1.02.04.05.01","CBE2040501",null,"High Power Gun WG Conditioning","2006-08-01","2006-11-30",null,"C","SL_KE1","Hrs",64,null,7141.599830015999,null,7141.599830015999,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"2A"]
["1","02","04","05","01","","IJ405_1070","1.02.04.05.01","CBE2040501",null,"High Power ACC WG Conditioning","2006-08-01","2006-11-30",null,"C","SL_ME1","Hrs",10,null,985.9390675199999,null,985.9390675199999,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"2A"]
["1","02","04","05","01","","IJ405_1070","1.02.04.05.01","CBE2040501",null,"High Power ACC WG Conditioning","2006-08-01","2006-11-30",null,"C","SL_KT1","Hrs",24,null,1466.1837112319995,null,1466.1837112319995,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"2A"]
["1","02","04","05","01","","IJ405_1070","1.02.04.05.01","CBE2040501",null,"High Power ACC WG Conditioning","2006-08-01","2006-11-30",null,"C","SL_KE1","Hrs",65,null,7253.1873273599995,null,7253.1873273599995,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"2A"]
["1","02","04","05","01","","IJ405_1080","1.02.04.05.01","CBE2040501",null,"High Power T-Cav WG Contidioning","2006-08-01","2006-11-30",null,"C","SL_ME1","Hrs",9,null,887.3451607679999,null,887.3451607679999,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"2A"]
["1","02","04","05","01","","IJ405_1080","1.02.04.05.01","CBE2040501",null,"High Power T-Cav WG Contidioning","2006-08-01","2006-11-30",null,"C","SL_KT1","Hrs",24,null,1466.1837112319995,null,1466.1837112319995,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"2A"]
["1","02","04","05","01","","IJ405_1080","1.02.04.05.01","CBE2040501",null,"High Power T-Cav WG Contidioning","2006-08-01","2006-11-30",null,"C","SL_KE1","Hrs",64,null,7141.599830015999,null,7141.599830015999,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"2A"]
["1","02","04","05","02","  ",{"$nulls":4},"RF Waveguide Supports                                       "]
["1","02","04","06","  ","  ",{"$nulls":4},"Injector Linac Structures                                   ",{"$nulls":6},820,2000,84296.22102871421,2096,86392.22102871421,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","04","06","01","  ",{"$nulls":4},"L0A-0B Structure Assembly                                   ",{"$nulls":6},640,0,64519.31536471422,0,64519.31536471422,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","04","06","01","","IJ406_1000","1.02.04.06.01","CBE2040601",null,"Fabricate and Modify L0A &B (cont)","2006-05-01","2006-07-30","S","C","SL_MFMS1","Hrs",120,null,12900.96,null,12900.96,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.1,1.25,3,3,"2A"]
["1","02","04","06","01","","IJ406_1010","1.02.04.06.01","CBE2040601",null,"Integrate L0A &B onto Support Structure","2006-06-01","2006-08-31","S","C","SL_MFAT1","Hrs",120,null,10080,null,10080,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.1,1.25,3,3,"2A"]
["1","02","04","06","01","","IJ406_1030","1.02.04.06.01","CBE2040601",null,"Cold Test L0A/L0B","2006-07-01","2006-07-30","S","C","SL_KE1","Hrs",160,null,17626.745664,null,17626.745664,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.1,1.25,3,3,"2A"]
["1","02","04","06","01","","IJ406_1040","1.02.04.06.01","CBE2040601",null,"Perform L0A &B Waveguide Integration","2006-07-01","2006-08-31","S","C","SL_MFAT1","Hrs",40,null,3360,null,3360,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.1,1.25,3,3,"2A"]
["1","02","04","06","01","","IJ406_1050","1.02.04.06.01","CBE2040601",null,"Prep for & Perform L0A &B RF tuning","2006-07-01","2006-07-30","S","C","SL_KE1","Hrs",80,null,8813.372832,null,8813.372832,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.1,1.25,3,3,"2A"]
["1","02","04","06","01","","IJ406_1060","1.02.04.06.01","CBE2040601",null,"Perform L0A &B Vacuum Processing","2006-07-01","2006-10-06","S","C","SL_MVE1","Hrs",80,null,8290.876868714226,null,8290.876868714226,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.1,1.25,3,3,"2A"]
["1","02","04","06","01","","IJ406_1070","1.02.04.06.01","CBE2040601",null,"Integrate L0A & Solenoid","2006-10-09","2006-10-20","S","C","SL_MFAT1","Hrs",40,null,3447.36,null,3447.36,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.1,1.25,3,3,"2A"]
["1","02","04","06","03","  ",{"$nulls":4},"Major Linac Support                                         "]
["1","02","04","06","04","  ",{"$nulls":4},"GTL RF Phase Cavity                                         "]
["1","02","04","06","05","  ",{"$nulls":4},"LTDL1 RF Kicker                                             ",{"$nulls":6},180,2000,19776.905663999998,2096,21872.905663999998,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","04","06","05","","IJ406_5000","1.02.04.06.05","CBE2040605",null,"Conduct Test & RF Processing (cont)","2006-06-01","2006-06-30","S","C","SL_KE1","Hrs",80,null,8813.372832,null,8813.372832,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,3,3,"2A"]
["1","02","04","06","05","","IJ406_5010","1.02.04.06.05","CBE2040605",null,"Procure Support Structure Materials (cont)","2006-05-01","2006-05-31","S","C","SL_MSEG1","$$",null,2000,null,2096,2096,null,null,0,null,0,0,{"$nulls":10},0,0,1,1,3,3,"2A"]
["1","02","04","06","05","","IJ406_5020","1.02.04.06.05","CBE2040605",null,"Fab RF Kicker Support Structure (cont)","2006-05-01","2006-05-31","S","C","SL_MFMS1","Hrs",20,null,2150.16,null,2150.16,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,3,3,"2A"]
["1","02","04","06","05","","IJ406_5030","1.02.04.06.05","CBE2040605",null,"Conduct Test & RF Processing (cont)","2006-05-01","2006-05-31","S","C","SL_KE1","Hrs",80,null,8813.372832,null,8813.372832,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,3,3,"2A"]
["1","02","05","  ","  ","  ",{"$nulls":4},"Injector Magnets & Supports                                 ",{"$nulls":6},1288,135500,113766.76065839994,142076.8411881188,224330.76065840002,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","05","01","  ","  ",{"$nulls":4},"Injector Dipoles                                            ",{"$nulls":6},780,94500,67672.776168,99108.84118811881,135268.77616799998,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","05","01","01","  ",{"$nulls":4},"Gun Spectrometer Dipole                                     ",{"$nulls":6},340,37500,30060.440628,39372.84118811881,37920.440628,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","05","01","01","","IJ501_1200","1.02.05.01.01","CBE2050101",null,"Engineering Support Gun Spectrometer Magnet","2006-05-01","2006-06-30","S","C","SL_ME1","Hrs",80,null,7787.116655999998,null,7787.116655999998,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.15,1.2,3,2,"2A"]
["1","02","05","01","01","","IJ501_1210","1.02.05.01.01","CBE2050101",null,"Purchase Materials","2006-05-01","2006-05-31","S","C","SL_MSEQ1","$$",null,5000,null,5240,5240,null,null,0,null,0,0,{"$nulls":10},0.35,0,1.15,1.2,3,3,"2A"]
["1","02","05","01","01","","IJ501_1220","1.02.05.01.01","CBE2050101",null,"Design Support","2006-05-01","2006-05-31","S","C","SL_ME1","Hrs",20,null,1946.7791639999996,null,1946.7791639999996,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.15,1.2,3,2,"2A"]
["1","02","05","01","01","","IJ501_1220","1.02.05.01.01","CBE2050101",null,"Design Support","2006-05-01","2006-05-31","S","C","SL_MDD1","Hrs",40,null,3264.4648079999997,null,3264.4648079999997,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.15,1.2,3,2,"2A"]
["1","02","05","01","01","","IJ501_1230","1.02.05.01.01","CBE2050101",null,"Fabricate Support","2006-05-01","2006-05-31","S","C","SL_MSEQ1","$$",null,2500,null,2620,2620,null,null,0,null,0,0,{"$nulls":10},0.35,0,1.15,1.2,3,3,"2A"]
["1","02","05","01","01","","IJ501_1240","1.02.05.01.01","CBE2050101",null,"SLAC Fab Coils","2006-06-01","2006-06-30","S","C","SL_MFAT1","Hrs",80,null,6720,null,6720,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.15,1.2,3,3,"2A"]
["1","02","05","01","01","","IJ501_1250","1.02.05.01.01","CBE2050101",null,"LBNL Fab Core","2006-07-01","2006-10-10","S","C","SL_MSPS1","$$",null,30000,null,31512.84118811881,null,null,null,0,null,0,0,{"$nulls":10},0.35,0,1.15,1.2,3,3,"2A"]
["1","02","05","01","01","","IJ501_1260","1.02.05.01.01","CBE2050101",null,"SLAC Assemble Magnet","2006-10-11","2006-10-23","S","C","SL_MFAT1","Hrs",40,null,3447.36,null,3447.36,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.15,1.2,3,3,"2A"]
["1","02","05","01","01","","IJ501_1270","1.02.05.01.01","CBE2050101",null,"Perform QC/MM on Dipole Assembly","2006-10-24","2006-11-07","S","C","SL_MFAT1","Hrs",80,null,6894.72,null,6894.72,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.15,1.2,3,3,"2A"]
["1","02","05","01","02","  ",{"$nulls":4},"DL1 B01 & B02 Dipoles                                       ",{"$nulls":6},100,1000,8400,1048,9448,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","05","01","02","","IJ501_2200","1.02.05.01.02","CBE2050102",null,"Fabricate Support","2006-06-01","2006-06-30","S","C","SL_MSEQ1","$$",null,1000,null,1048,1048,null,null,0,null,0,0,{"$nulls":10},0,0,1,1,3,3,"2A"]
["1","02","05","01","02","","IJ501_2210","1.02.05.01.02","CBE2050102",null,"Perform QC/MM on DL1 Dipole Assm","2006-05-01","2006-08-31","S","C","SL_MFAT1","Hrs",100,null,8400,null,8400,null,0,null,0,null,0,{"$nulls":10},0.1,0,1.1,1,3,3,"2A"]
["1","02","05","01","03","  ",{"$nulls":4},"SAB Spectrometer Dipole                                     ",{"$nulls":6},340,56000,29212.33554,58688,87900.33554,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","05","01","03","","IJ501_3200","1.02.05.01.03","CBE2050103",null,"Purchase Materials","2006-05-01","2006-05-31","S","C","SL_MSEQ1","$$",null,8000,null,8384,8384,null,null,0,null,0,0,{"$nulls":10},0.35,0,1.15,1.2,3,3,"2A"]
["1","02","05","01","03","","IJ501_3210","1.02.05.01.03","CBE2050103",null,"SLAC Fab Coils","2006-06-01","2006-07-30","S","C","SL_MFAT1","Hrs",120,null,10080,null,10080,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.15,1.2,3,3,"2A"]
["1","02","05","01","03","","IJ501_3220","1.02.05.01.03","CBE2050103",null,"Design Support","2006-05-01","2006-05-31","S","C","SL_ME1","Hrs",40,null,3893.558327999999,null,3893.558327999999,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.15,1.2,3,2,"2A"]
["1","02","05","01","03","","IJ501_3220","1.02.05.01.03","CBE2050103",null,"Design Support","2006-05-01","2006-05-31","S","C","SL_MDD1","Hrs",60,null,4896.697211999999,null,4896.697211999999,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.15,1.2,3,2,"2A"]
["1","02","05","01","03","","IJ501_3230","1.02.05.01.03","CBE2050103",null,"Fabricate Support","2006-05-01","2006-05-31","S","C","SL_MSEQ1","$$",null,8000,null,8384,8384,null,null,0,null,0,0,{"$nulls":10},0.35,0,1.15,1.2,3,3,"2A"]
["1","02","05","01","03","","IJ501_3240","1.02.05.01.03","CBE2050103",null,"LBNL Fab Core","2006-06-01","2006-09-26","S","C","SL_MSPS1","$$",null,40000,null,41920,41920,null,null,0,null,0,0,{"$nulls":10},0.35,0,1.15,1.2,3,3,"2A"]
["1","02","05","01","03","","IJ501_3250","1.02.05.01.03","CBE2050103",null,"SLAC Assemble Magnet","2006-10-06","2006-10-18","S","C","SL_MFAT1","Hrs",40,null,3447.36,null,3447.36,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.15,1.2,3,3,"2A"]
["1","02","05","01","03","","IJ501_3260","1.02.05.01.03","CBE2050103",null,"Perform QC/MM on SAB Dipole Assm","2006-10-19","2006-10-30","S","C","SL_MFAT1","Hrs",80,null,6894.72,null,6894.72,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.15,1.2,3,3,"2A"]
["1","02","05","01","04","  ",{"$nulls":4},"Chicane DIPOLES (4)                                         "]
["1","02","05","02","  ","  ",{"$nulls":4},"Injector Quads                                              ",{"$nulls":6},68,12000,5712,12576,18288,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","05","02","01","  ",{"$nulls":4},"Gun Spectrometer Quadrupoles                                ",{"$nulls":6},40,12000,3360,12576,15936,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","05","02","01","","IJ502_1200","1.02.05.02.01","CBE2050201",null,"RCV:   GS Quads Assy","2006-05-01","2006-05-31","S","C","SL_MSSC1","$$",null,10000,null,10480,10480,null,null,0,null,0,0,{"$nulls":10},0,0,1,1,3,3,"2A"]
["1","02","05","02","01","","IJ502_1220","1.02.05.02.01","CBE2050201",null,"Fabricate Supports","2006-05-01","2006-07-30","S","C","SL_MSEQ1","$$",null,2000,null,2096,2096,null,null,0,null,0,0,{"$nulls":10},0,0,1,1,3,3,"2A"]
["1","02","05","02","01","","IJ502_1230","1.02.05.02.01","CBE2050201",null,"Perform QC/MM on GS Quads Assy","2006-08-01","2006-08-31","S","C","SL_MFAT1","Hrs",40,null,3360,null,3360,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"2A"]
["1","02","05","02","02","  ",{"$nulls":4},"Injector Quadrupoles                                        ",{"$nulls":6},28,0,2352,0,2352,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","05","02","02","","IJ502_2200","1.02.05.02.02","CBE2050202",null,"Perform QC/MM on  Inj Quads Assy & Sppt","2006-05-01","2006-06-30","S","C","SL_MFAT1","Hrs",28,null,2352,null,2352,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,3,3,"2A"]
["1","02","05","02","03","  ",{"$nulls":4},"                                                            "]
["1","02","05","03","  ","  ",{"$nulls":4},"Injector Steering Coils                                     ",{"$nulls":6},120,14000,10300.6345224,14672,24972.6345224,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","05","03","01","  ",{"$nulls":4},"Gun Solenoid Correctors                                     "]
["1","02","05","03","02","  ",{"$nulls":4},"Gun Spectrometer Correctors                                 "]
["1","02","05","03","03","  ",{"$nulls":4},"Injector Correctors - A                                     ",{"$nulls":6},120,14000,10300.6345224,14672,24972.6345224,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","05","03","03","","IJ503_3200","1.02.05.03.03","CBE2050303",null,"Design Corrector Type 1A","2006-05-01","2006-05-31","S","C","SL_ME1","Hrs",4,null,389.3558327999999,null,389.3558327999999,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,3,2,"2A"]
["1","02","05","03","03","","IJ503_3200","1.02.05.03.03","CBE2050303",null,"Design Corrector Type 1A","2006-05-01","2006-05-31","S","C","SL_MDD1","Hrs",8,null,652.8929615999999,null,652.8929615999999,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,3,2,"2A"]
["1","02","05","03","03","","IJ503_3210","1.02.05.03.03","CBE2050303",null,"Design Corrector Type 1S","2006-05-01","2006-05-31","S","C","SL_ME1","Hrs",4,null,389.3558327999999,null,389.3558327999999,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,3,2,"2A"]
["1","02","05","03","03","","IJ503_3210","1.02.05.03.03","CBE2050303",null,"Design Corrector Type 1S","2006-05-01","2006-05-31","S","C","SL_MDD1","Hrs",8,null,652.8929615999999,null,652.8929615999999,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,3,2,"2A"]
["1","02","05","03","03","","IJ503_3220","1.02.05.03.03","CBE2050303",null,"Design Corrector Type 1S-LOA","2006-05-01","2006-05-31","S","C","SL_ME1","Hrs",4,null,389.3558327999999,null,389.3558327999999,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,3,2,"2A"]
["1","02","05","03","03","","IJ503_3220","1.02.05.03.03","CBE2050303",null,"Design Corrector Type 1S-LOA","2006-05-01","2006-05-31","S","C","SL_MDD1","Hrs",8,null,652.8929615999999,null,652.8929615999999,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,3,2,"2A"]
["1","02","05","03","03","","IJ503_3230","1.02.05.03.03","CBE2050303",null,"Design Corrector Type 1T","2006-05-01","2006-05-31","S","C","SL_ME1","Hrs",4,null,389.3558327999999,null,389.3558327999999,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,3,2,"2A"]
["1","02","05","03","03","","IJ503_3230","1.02.05.03.03","CBE2050303",null,"Design Corrector Type 1T","2006-05-01","2006-05-31","S","C","SL_MDD1","Hrs",8,null,652.8929615999999,null,652.8929615999999,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,3,2,"2A"]
["1","02","05","03","03","","IJ503_3240","1.02.05.03.03","CBE2050303",null,"Design Corrector Type 1T Support","2006-05-01","2006-05-31","S","C","SL_ME1","Hrs",4,null,389.3558327999999,null,389.3558327999999,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,3,2,"2A"]
["1","02","05","03","03","","IJ503_3240","1.02.05.03.03","CBE2050303",null,"Design Corrector Type 1T Support","2006-05-01","2006-05-31","S","C","SL_MDD1","Hrs",16,null,1305.7859231999998,null,1305.7859231999998,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,3,2,"2A"]
["1","02","05","03","03","","IJ503_3250","1.02.05.03.03","CBE2050303",null,"Design Corrector Type 1X","2006-05-01","2006-05-31","S","C","SL_ME1","Hrs",8,null,778.7116655999998,null,778.7116655999998,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,3,2,"2A"]
["1","02","05","03","03","","IJ503_3250","1.02.05.03.03","CBE2050303",null,"Design Corrector Type 1X","2006-05-01","2006-05-31","S","C","SL_MDD1","Hrs",16,null,1305.7859231999998,null,1305.7859231999998,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,3,2,"2A"]
["1","02","05","03","03","","IJ503_3260","1.02.05.03.03","CBE2050303",null,"Fabricate Corrector Type 1A","2006-06-01","2006-08-31","S","C","SL_MSEQ1","$$",null,6000,null,6288,6288,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,4,3,"2A"]
["1","02","05","03","03","","IJ503_3270","1.02.05.03.03","CBE2050303",null,"Fabricate Corrector Type 1S","2006-06-01","2006-08-31","S","C","SL_MSEQ1","$$",null,4000,null,4192,4192,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,4,3,"2A"]
["1","02","05","03","03","","IJ503_3280","1.02.05.03.03","CBE2050303",null,"Fabricate Corrector Type 1S-LOA","2006-06-01","2006-08-31","S","C","SL_MSEQ1","$$",null,1000,null,1048,1048,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,4,3,"2A"]
["1","02","05","03","03","","IJ503_3290","1.02.05.03.03","CBE2050303",null,"Fabricate Corrector Type 1T","2006-06-01","2006-08-31","S","C","SL_MSEQ1","$$",null,1000,null,1048,1048,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,4,3,"2A"]
["1","02","05","03","03","","IJ503_3300","1.02.05.03.03","CBE2050303",null,"Fabricate Corrector Type 1T Support","2006-06-01","2006-08-31","S","C","SL_MSEQ1","$$",null,1000,null,1048,1048,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,4,3,"2A"]
["1","02","05","03","03","","IJ503_3310","1.02.05.03.03","CBE2050303",null,"Fabricate Corrector Type 1X","2006-06-01","2006-08-31","S","C","SL_MSEQ1","$$",null,1000,null,1048,1048,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,4,3,"2A"]
["1","02","05","03","03","","IJ503_3320","1.02.05.03.03","CBE2050303",null,"Test Corrector Type 1A","2006-08-02","2006-08-31","S","C","SL_MFAT1","Hrs",8,null,672,null,672,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,4,3,"2A"]
["1","02","05","03","03","","IJ503_3330","1.02.05.03.03","CBE2050303",null,"Test  Corrector Type 1S","2006-08-02","2006-08-31","S","C","SL_MFAT1","Hrs",8,null,672,null,672,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,4,3,"2A"]
["1","02","05","03","03","","IJ503_3340","1.02.05.03.03","CBE2050303",null,"Test  Corrector Type 1S-LOA","2006-08-02","2006-08-31","S","C","SL_MFAT1","Hrs",4,null,336,null,336,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,4,3,"2A"]
["1","02","05","03","03","","IJ503_3350","1.02.05.03.03","CBE2050303",null,"Test  Corrector Type 1T","2006-08-02","2006-08-31","S","C","SL_MFAT1","Hrs",4,null,336,null,336,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,4,3,"2A"]
["1","02","05","03","03","","IJ503_3360","1.02.05.03.03","CBE2050303",null,"Test  Corrector Type 1X","2006-08-02","2006-08-31","S","C","SL_MFAT1","Hrs",4,null,336,null,336,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,4,3,"2A"]
["1","02","05","03","04","  ",{"$nulls":4},"Injector Correctors - D (Gun)                               "]
["1","02","05","03","05","  ",{"$nulls":4},"Gun Solenoid Quadrupole Correctors                          "]
["1","02","05","04","  ","  ",{"$nulls":4},"Linac Solenoid                                              ",{"$nulls":6},320,15000,30081.349967999995,15720,45801.349967999995,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","05","04","","","IJ504_1000","1.02.05.04","CBE20504",null,"Design Linac Solenoid Support","2006-05-01","2006-05-31","S","C","SL_ME1","Hrs",240,null,23361.349967999995,null,23361.349967999995,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,3,2,"2A"]
["1","02","05","04","","","IJ504_1010","1.02.05.04","CBE20504",null,"Fabricate Linac Solenoid Support","2006-05-15","2006-05-31","S","C","SL_MSEQ1","$$",null,15000,null,15720,15720,null,null,0,null,0,0,{"$nulls":10},0,0,1,1,4,3,"2A"]
["1","02","05","04","","","IJ504_1020","1.02.05.04","CBE20504",null,"Perform QC/MM on Linac Solenoid Assy","2006-05-01","2006-08-31","S","C","SL_MFAT1","Hrs",80,null,6720,null,6720,null,0,null,0,null,0,{"$nulls":10},0.1,0,1.1,1,4,3,"2A"]
["1","02","05","05","  ","  ",{"$nulls":4},"Injector Laser Heater Subsystem                             "]
["1","02","05","05","01","  ",{"$nulls":4},"System Design & Optimization (LSR HTR)                      "]
["1","02","05","05","02","  ",{"$nulls":4},"Injector Undulator                                          "]
["1","02","06","  ","  ","  ",{"$nulls":4},"Injector Vacuum & Supports                                  ",{"$nulls":6},540,126000,53052.66324736813,133176.54943081966,112400.18972736812,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","06","01","  ","  ",{"$nulls":4},"Injector Vacuum Engineering                                 ",{"$nulls":6},240,0,22103.162927999998,0,22103.162927999998,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","06","01","","","IJ601_1200","1.02.06.01","CBE20601",null,"GTL Chamber Engineering","2006-05-01","2006-06-30","S","C","SL_ME1","Hrs",40,null,3893.558327999999,null,3893.558327999999,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,3,2,"2A"]
["1","02","06","01","","","IJ601_1200","1.02.06.01","CBE20601",null,"GTL Chamber Engineering","2006-05-01","2006-06-30","S","C","SL_MDD1","Hrs",40,null,3264.4648079999997,null,3264.4648079999997,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,3,2,"2A"]
["1","02","06","01","","","IJ601_1210","1.02.06.01","CBE20601",null,"Linac L0aL0b Engineering","2006-05-01","2006-06-30","S","C","SL_ME1","Hrs",20,null,1946.7791639999996,null,1946.7791639999996,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,3,2,"2A"]
["1","02","06","01","","","IJ601_1220","1.02.06.01","CBE20601",null,"Linac L0aL0b Design","2006-05-01","2006-06-30","S","C","SL_MDD1","Hrs",20,null,1632.2324039999999,null,1632.2324039999999,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,3,2,"2A"]
["1","02","06","01","","","IJ601_1250","1.02.06.01","CBE20601",null,"INS/SAB Engineering","2006-05-01","2006-06-30","S","C","SL_ME1","Hrs",20,null,1946.7791639999996,null,1946.7791639999996,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,3,2,"2A"]
["1","02","06","01","","","IJ601_1260","1.02.06.01","CBE20601",null,"INS/SAB Design","2006-05-01","2006-06-30","S","C","SL_MDD1","Hrs",20,null,1632.2324039999999,null,1632.2324039999999,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,3,2,"2A"]
["1","02","06","01","","","IJ601_1270","1.02.06.01","CBE20601",null,"Fabrication Support","2006-06-01","2006-08-31","S","C","SL_ME1","Hrs",80,null,7787.116655999998,null,7787.116655999998,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,4,1,"2A"]
["1","02","06","02","  ","  ",{"$nulls":4},"Injector Vacuum Components                                  "]
["1","02","06","03","  ","  ",{"$nulls":4},"Injector Vacuum Special Chambers                            ",{"$nulls":6},300,81000,30949.500319368133,85357.02295081966,42477.50031936813,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","06","03","","","IJ603_1200","1.02.06.03","CBE20603",null,"Fabricate Linac Region Special Chambers","2006-06-01","2006-08-31",null,"C","SL_MSEG1","$$",null,5000,null,5240,5240,null,null,0,null,0,0,{"$nulls":10},0.4,0,1.15,1.25,3,3,"2A"]
["1","02","06","03","","","IJ603_1210","1.02.06.03","CBE20603",null,"Fabricate Heater Region Special Chambers","2006-06-01","2006-08-31",null,"C","SL_MSEG1","$$",null,6000,null,6288,6288,null,null,0,null,0,0,{"$nulls":10},0.4,0,1.15,1.25,3,3,"2A"]
["1","02","06","03","","","IJ603_1220","1.02.06.03","CBE20603",null,"Fabricate INS/SAB Region Special Chambers","2006-07-01","2006-10-31",null,"C","SL_MSEG1","$$",null,50000,null,52735.016393442624,null,null,null,0,null,0,0,{"$nulls":10},0.4,0,1.15,1.25,3,3,"2A"]
["1","02","06","03","","","IJ603_1230","1.02.06.03","CBE20603",null,"Fabricate Gun Region Special Chambers","2006-07-01","2006-10-31",null,"C","SL_MSEG1","$$",null,20000,null,21094.006557377048,null,null,null,0,null,0,0,{"$nulls":10},0.4,0,1.15,1.25,3,3,"2A"]
["1","02","06","03","","","IJ603_1240","1.02.06.03","CBE20603",null,"Vacuum Process Linac Region Special Chambers","2006-08-01","2006-08-31",null,"C","SL_MFAT1","Hrs",40,null,3360,null,3360,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.15,1.25,3,3,"2A"]
["1","02","06","03","","","IJ603_1250","1.02.06.03","CBE20603",null,"Vacuum Process Heater Region Special Chambers","2006-08-01","2006-08-31",null,"C","SL_MFAT1","Hrs",40,null,3360,null,3360,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.15,1.25,3,3,"2A"]
["1","02","06","03","","","IJ603_1280","1.02.06.03","CBE20603",null,"Vacuum Process INS/SAB Region Special Chambers","2006-11-01","2006-11-14",null,"C","SL_MFAT1","Hrs",80,null,6894.72,null,6894.72,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.15,1.25,3,3,"2A"]
["1","02","06","03","","","IJ603_1300","1.02.06.03","CBE20603",null,"Vacuum Process Gun Region Special Chambers","2006-11-01","2006-11-07",null,"C","SL_MFAT1","Hrs",40,null,3447.36,null,3447.36,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.15,1.25,3,3,"2A"]
["1","02","06","03","","","IJ603_1255","1.02.06.03","CBE20603A",null,"Vacuum Process Special Chambers (LLNL)","2006-09-01","2006-10-27",null,"C","LL_MFAT1","Hrs",100,null,13887.420319368133,null,13887.420319368133,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.15,1.25,3,3,"2A"]
["1","02","06","04","  ","  ",{"$nulls":4},"Injector Vacuum Supports Engineering                        "]
["1","02","06","05","  ","  ",{"$nulls":4},"Injector Vacuum Support Components                          ",{"$nulls":6},0,45000,0,47819.52648,47819.52648,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","06","05","","","IJ605_1200","1.02.06.05","CBE20605",null,"Proc - Special Beam Pump/Spool Support Material","2006-05-01","2006-08-31","S","C","SL_MSEG1","$$",null,2000,null,2096,2096,null,null,0,null,0,0,{"$nulls":10},0.45,0,1.2,1.25,4,3,"2A"]
["1","02","06","05","","","IJ605_1210","1.02.06.05","CBE20605",null,"Proc - LTDL1 Support Structure Materials","2006-05-01","2006-08-31","S","C","SL_MSEG1","$$",null,2000,null,2096,2096,null,null,0,null,0,0,{"$nulls":10},0.45,0,1.2,1.25,4,3,"2A"]
["1","02","06","05","","","IJ605_1220","1.02.06.05","CBE20605",null,"Proc - Misc Support Hardware (bolts, nuts, etc.)","2006-05-01","2006-08-31","S","C","SL_MSEG1","$$",null,2000,null,2096,2096,null,null,0,null,0,0,{"$nulls":10},0.45,0,1.2,1.25,4,3,"2A"]
["1","02","06","05","","","IJ605_1230","1.02.06.05","CBE20605",null,"Fabricate Gun Region Vacuum Supports","2006-07-01","2006-08-29","S","C","SL_MSEG1","$$",null,10000,null,10480,10480,null,null,0,null,0,0,{"$nulls":10},0.45,0,1.2,1.25,4,3,"2A"]
["1","02","06","05","","","IJ605_1240","1.02.06.05","CBE20605",null,"Fabricate Linac Region Vacuum Supports","2006-07-01","2006-08-31","S","C","SL_MSEG1","$$",null,5000,null,5240,5240,null,null,0,null,0,0,{"$nulls":10},0.45,0,1.2,1.25,4,3,"2A"]
["1","02","06","05","","","IJ605_1250","1.02.06.05","CBE20605",null,"Fabricate Heater Region Vacuum Supports","2006-06-01","2006-08-31","S","C","SL_MSEG1","$$",null,5000,null,5240,5240,null,null,0,null,0,0,{"$nulls":10},0.45,0,1.2,1.25,4,3,"2A"]
["1","02","06","05","","","IJ605_1290","1.02.06.05","CBE20605",null,"Fabricate INS/SAB Region Vacuum Supports","2006-08-01","2006-08-30","S","C","SL_MSEG1","$$",null,10000,null,10480,10480,null,null,0,null,0,0,{"$nulls":10},0.45,0,1.2,1.25,4,3,"2A"]
["1","02","06","05","","","IJ605_1060","1.02.06.05","LBA20605",null,"Proc - LTDL1 Support Structure Materials","2005-12-01","2005-12-30","S","L","SL_MSEG","$$",null,4000,null,4485.122880000001,4485.122880000001,null,null,0,null,0,0,{"$nulls":10},0.45,0,1.2,1.25,4,3,"2A"]
["1","02","06","05","","","IJ605_1090","1.02.06.05","LBA20605",null,"Proc - Misc Support Hardware (bolts, nuts, etc.)","2005-12-01","2005-12-30","S","L","SL_MSEG","$$",null,5000,null,5606.403600000001,5606.403600000001,null,null,0,null,0,0,{"$nulls":10},0.45,0,1.2,1.25,4,3,"2A"]
["1","02","06","08","  ","  ",{"$nulls":4},"DL1 Vacuum Chamber                                          "]
["1","02","06","10","  ","  ",{"$nulls":4},"DL1TL Vacuum Components                                     "]
["1","02","07","  ","  ","  ",{"$nulls":4},"Injector Diagnostics                                        ",{"$nulls":6},1752,536000,149754.35122826265,559393.9796363637,644752.3512282626,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","07","01","  ","  ",{"$nulls":4},"Beam Position Monitors                                      ",{"$nulls":6},200,31000,16407.383437299097,32488,48895.3834372991,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","07","01","01","  ",{"$nulls":4},"Large Aperture BPM                                          ",{"$nulls":6},200,31000,16407.383437299097,32488,48895.3834372991,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","07","01","01","","IJ701_1110","1.02.07.01.01","CBE2070101",null,"Vendor Fab LA Linac BPM Core Module","2006-05-01","2006-06-30","S","C","SL_MSSC1","$$",null,31000,null,32488,32488,null,null,0,null,0,0,{"$nulls":10},0.45,0,1.2,1.25,3,3,"2A"]
["1","02","07","01","01","","IJ701_1115","1.02.07.01.01","CBE2070101",null,"In House Assemble LA BPM Variations","2006-06-01","2006-08-31","S","C","SL_MFAT1","Hrs",80,null,6720,null,6720,null,0,null,0,null,0,{"$nulls":10},0.45,0,1.2,1.25,3,3,"2A"]
["1","02","07","01","01","","IJ701_1120","1.02.07.01.01","CBE2070101",null,"Vacuum Process LA Linac BPM","2006-08-01","2006-08-31","S","C","SL_MVE1","Hrs",40,null,4139.890127999999,null,4139.890127999999,null,0,null,0,null,0,{"$nulls":10},0.45,0,1.2,1.25,3,3,"2A"]
["1","02","07","01","01","","IJ701_1130","1.02.07.01.01","CBE2070101",null,"Perform Lab Tests on LA Linac BPM Assembly","2006-08-02","2006-10-03","S","C","SL_MES1","Hrs",40,null,3132.9341402167743,null,3132.9341402167743,null,0,null,0,null,0,{"$nulls":10},0.45,0,1.2,1.25,3,3,"2A"]
["1","02","07","01","01","","IJ701_1130","1.02.07.01.01","CBE2070101",null,"Perform Lab Tests on LA Linac BPM Assembly","2006-08-02","2006-10-03","S","C","SL_CT1","Hrs",40,null,2414.559169082322,null,2414.559169082322,null,0,null,0,null,0,{"$nulls":10},0.45,0,1.2,1.25,3,3,"2A"]
["1","02","07","01","02","  ",{"$nulls":4},"Small Aperture BPM                                          "]
["1","02","07","01","06","  ",{"$nulls":4},"                                                            "]
["1","02","07","02","  ","  ",{"$nulls":4},"Current Monitors                                            ",{"$nulls":6},120,80000,9648.310299407998,83840,93488.310299408,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","07","02","01","  ",{"$nulls":4},"Current Monitors                                            ",{"$nulls":6},120,80000,9648.310299407998,83840,93488.310299408,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","07","02","01","","IJ702_1110","1.02.07.02.01","CBE2070201",null,"RCV:  Fab Current Monitor","2006-07-01","2006-08-01","S","C","SL_MSSC1","$$",null,80000,null,83840,83840,null,null,0,null,0,0,{"$nulls":10},0.5,0,1.2,1.3,7,3,"2A"]
["1","02","07","02","01","","IJ702_1120","1.02.07.02.01","CBE2070201",null,"Vacuum Process Current Monitor","2006-10-23","2006-10-27","S","C","SL_MVE1","Hrs",40,null,4247.527271327999,null,4247.527271327999,null,0,null,0,null,0,{"$nulls":10},0.5,0,1.2,1.3,3,3,"2A"]
["1","02","07","02","01","","IJ702_1130","1.02.07.02.01","CBE2070201",null,"Perform Lab Tests on Current Monitor","2006-10-30","2006-11-10","S","C","SL_PHS1","Hrs",40,null,2925.5213465279994,null,2925.5213465279994,null,0,null,0,null,0,{"$nulls":10},0.5,0,1.2,1.3,3,3,"2A"]
["1","02","07","02","01","","IJ702_1130","1.02.07.02.01","CBE2070201",null,"Perform Lab Tests on Current Monitor","2006-10-30","2006-11-10","S","C","SL_CT1","Hrs",40,null,2475.261681551999,null,2475.261681551999,null,0,null,0,null,0,{"$nulls":10},0.5,0,1.2,1.3,3,3,"2A"]
["1","02","07","03","  ","  ",{"$nulls":4},"Bunch Length Monitors                                       "]
["1","02","07","03","01","  ",{"$nulls":4},"Bunch Length Monitors                                       "]
["1","02","07","04","  ","  ",{"$nulls":4},"Profile Monitors                                            ",{"$nulls":6},1232,425000,106365.09916355555,443065.9796363636,485035.09916355554,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","07","04","01","  ",{"$nulls":4},"Profile Monitors                                            ",{"$nulls":6},1232,425000,106365.09916355555,443065.9796363636,485035.09916355554,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","07","04","01","","IJ741_0020","1.02.07.04.01","CBE2070401",null,"Design Check Profile Monitors","2006-05-01","2006-06-30",null,"C","SL_MDD1","Hrs",200,null,16322.324039999998,null,16322.324039999998,null,0,null,0,null,0,{"$nulls":10},0.2,0,1,1.2,5,2,"2A"]
["1","02","07","04","01","","IJ741_0030","1.02.07.04.01","CBE2070401",null,"Design GTL YAG External Optiics","2006-06-01","2006-09-26",null,"C","SL_ME1","Hrs",80,null,7787.116655999998,null,7787.116655999998,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,2,"2A"]
["1","02","07","04","01","","IJ741_0030","1.02.07.04.01","CBE2070401",null,"Design GTL YAG External Optiics","2006-06-01","2006-09-26",null,"C","SL_MDD1","Hrs",80,null,6528.929615999999,null,6528.929615999999,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,2,"2A"]
["1","02","07","04","01","","IJ741_0040","1.02.07.04.01","CBE2070401",null,"Fabricate GTL YAG External Optics","2006-09-27","2006-11-21",null,"C","SL_MSEG1","$$",null,30000,null,32197.98981818182,null,null,null,0,null,0,0,{"$nulls":10},0.4,0,1.2,1.2,5,3,"2A"]
["1","02","07","04","01","","IJ741_0050","1.02.07.04.01","CBE2070401",null,"Assemble GTL YAG External Optics (3)","2006-11-22","2006-12-14",null,"C","SL_MFAT1","Hrs",36,null,3102.6240000000003,null,3102.6240000000003,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,3,"2A"]
["1","02","07","04","01","","IJ741_0060","1.02.07.04.01","CBE2070401",null,"Design GTL Cerenkov External Optics","2006-07-01","2006-09-26",null,"C","SL_ME1","Hrs",120,null,11680.674983999997,null,11680.674983999997,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,2,"2A"]
["1","02","07","04","01","","IJ741_0060","1.02.07.04.01","CBE2070401",null,"Design GTL Cerenkov External Optics","2006-07-01","2006-09-26",null,"C","SL_MDD1","Hrs",160,null,13057.859231999999,null,13057.859231999999,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,2,"2A"]
["1","02","07","04","01","","IJ741_0070","1.02.07.04.01","CBE2070401",null,"Fabricate GTL Cerenkov External Optics","2006-09-27","2006-11-21",null,"C","SL_MSEG1","$$",null,30000,null,32197.98981818182,null,null,null,0,null,0,0,{"$nulls":10},0.4,0,1.2,1.2,5,3,"2A"]
["1","02","07","04","01","","IJ741_0080","1.02.07.04.01","CBE2070401",null,"Assemble GTL Cerenkov External Optics (2)","2006-11-22","2006-12-14",null,"C","SL_MFAT1","Hrs",24,null,2068.416,null,2068.416,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,3,"2A"]
["1","02","07","04","01","","IJ741_0090","1.02.07.04.01","CBE2070401",null,"Assemble GTL YAG/Cerenkov Beamline Assy (3)","2006-05-01","2006-09-28",null,"C","SL_MFAT1","Hrs",40,null,3360,null,3360,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.15,1.2,3,3,"2A"]
["1","02","07","04","01","","IJ741_0100","1.02.07.04.01","CBE2070401",null,"Vac Process GTL YAG/Cerenkov Beamline Assy (3)","2006-09-29","2006-10-26",null,"C","SL_MFAT1","Hrs",40,null,3440.888888888889,null,3440.888888888889,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.15,1.2,3,3,"2A"]
["1","02","07","04","01","","IJ741_0110","1.02.07.04.01","CBE2070401",null,"Design YAG External Optics","2006-05-01","2006-06-30",null,"C","SL_ME1","Hrs",40,null,3893.558327999999,null,3893.558327999999,null,0,null,0,null,0,{"$nulls":10},0.2,0,1,1.2,5,2,"2A"]
["1","02","07","04","01","","IJ741_0110","1.02.07.04.01","CBE2070401",null,"Design YAG External Optics","2006-05-01","2006-06-30",null,"C","SL_MDD1","Hrs",60,null,4896.697211999999,null,4896.697211999999,null,0,null,0,null,0,{"$nulls":10},0.2,0,1,1.2,5,2,"2A"]
["1","02","07","04","01","","IJ741_0120","1.02.07.04.01","CBE2070401",null,"Fabricate YAG 03/04 External Optics","2006-07-01","2006-09-26",null,"C","SL_MSEG1","$$",null,20000,null,20960,20960,null,null,0,null,0,0,{"$nulls":10},0.4,0,1.2,1.2,5,3,"2A"]
["1","02","07","04","01","","IJ741_0130","1.02.07.04.01","CBE2070401",null,"Assemble YAG 03/04 External Optics (2)","2006-09-27","2006-10-24",null,"C","SL_MFAT1","Hrs",24,null,2060.650666666667,null,2060.650666666667,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,3,"2A"]
["1","02","07","04","01","","IJ741_0140","1.02.07.04.01","CBE2070401",null,"Fabricate YAG 03/YAG 04 Beamline Assemblies (2)","2006-06-01","2006-09-26",null,"C","SL_MSEG1","$$",null,30000,null,31440,31440,null,null,0,null,0,0,{"$nulls":10},0.35,0,1.15,1.2,3,3,"2A"]
["1","02","07","04","01","","IJ741_0150","1.02.07.04.01","CBE2070401",null,"Assemble YAG 03/04 Beamline Assy (2)","2006-09-27","2006-10-10",null,"C","SL_MFAT1","Hrs",32,null,2736.384,null,2736.384,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.15,1.2,3,3,"2A"]
["1","02","07","04","01","","IJ741_0155","1.02.07.04.01","CBE2070401",null,"Fab BL Assy (FC01,YAG01/02/GS,CR01/02)","2006-07-01","2006-09-26",null,"C","SL_MSEG1","$$",null,100000,null,104800,104800,null,null,0,null,0,0,{"$nulls":10},0.35,0,1.15,1.2,3,3,"2A"]
["1","02","07","04","01","","IJ741_0160","1.02.07.04.01","CBE2070401",null,"Vac Process YAG 03/04 Beamline Assy (2)","2006-10-11","2006-10-24",null,"C","SL_MFAT1","Hrs",40,null,3447.36,null,3447.36,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.15,1.2,3,3,"2A"]
["1","02","07","04","01","","IJ741_0170","1.02.07.04.01","CBE2070401",null,"Fabricate YAG 03/04 Mirror Assembly","2006-06-01","2006-08-31",null,"C","SL_MSEG1","$$",null,5000,null,5240,5240,null,null,0,null,0,0,{"$nulls":10},0.35,0,1.15,1.2,3,3,"2A"]
["1","02","07","04","01","","IJ741_0190","1.02.07.04.01","CBE2070401",null,"Design OTR External Optics","2006-05-01","2006-06-30",null,"C","SL_ME1","Hrs",40,null,3893.558327999999,null,3893.558327999999,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,2,"2A"]
["1","02","07","04","01","","IJ741_0190","1.02.07.04.01","CBE2070401",null,"Design OTR External Optics","2006-05-01","2006-06-30",null,"C","SL_MDD1","Hrs",60,null,4896.697211999999,null,4896.697211999999,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,2,"2A"]
["1","02","07","04","01","","IJ741_0200","1.02.07.04.01","CBE2070401",null,"Fabricate OTR 01/02/03 External Optics","2006-07-01","2006-09-12",null,"C","SL_MSEG1","$$",null,30000,null,31440,31440,null,null,0,null,0,0,{"$nulls":10},0.4,0,1.2,1.2,5,3,"2A"]
["1","02","07","04","01","","IJ741_0210","1.02.07.04.01","CBE2070401",null,"Assemble OTR 01/02/03 External Optics (3)","2006-09-13","2006-09-26",null,"C","SL_MFAT1","Hrs",36,null,3024,null,3024,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,5,3,"2A"]
["1","02","07","04","01","","IJ741_0220","1.02.07.04.01","CBE2070401",null,"Fabricate OTR 01/02/03 Mirror Assembly","2006-06-01","2006-08-31",null,"C","SL_MSEG1","$$",null,5000,null,5240,5240,null,null,0,null,0,0,{"$nulls":10},0.35,0,1.15,1.2,3,3,"2A"]
["1","02","07","04","01","","IJ741_0230","1.02.07.04.01","CBE2070401",null,"Assemble OTR 01/02/03 Beamline Assemblies (3)","2006-08-02","2006-08-15",null,"C","SL_MFAT1","Hrs",40,null,3360,null,3360,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.15,1.2,3,3,"2A"]
["1","02","07","04","01","","IJ741_0240","1.02.07.04.01","CBE2070401",null,"Vac Process OTR 01/02/03 Beamline Assy (2)","2006-08-16","2006-08-29",null,"C","SL_MFAT1","Hrs",40,null,3360,null,3360,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.15,1.2,3,3,"2A"]
["1","02","07","04","01","","IJ741_0320","1.02.07.04.01","CBE2070401",null,"Test OTRS1","2006-11-16","2006-12-08",null,"C","SL_MFAT1","Hrs",40,null,3447.36,null,3447.36,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.15,1.2,3,3,"2A"]
["1","02","07","04","01","","IJ741_0315","1.02.07.04.01","CBE20704A",null,"RCV:  ANL Deliver OTRS1 (IJ39)","2006-11-15","2006-11-15","A","C","AN_MSEG1","$$",null,175000,null,179550,179550,null,null,0,null,0,0,{"$nulls":10},0.35,0,1.15,1.2,3,3,"2A"]
["1","02","07","04","03","  ",{"$nulls":4},"GS Faraday Cup/YAG2                                         "]
["1","02","07","04","06","  ",{"$nulls":4},"DL1 OTR/YAG                                                 "]
["1","02","07","04","07","  ",{"$nulls":4},"DL1TL OTR/YAG                                               "]
["1","02","07","04","08","  ",{"$nulls":4},"LTDL1 OTR/YAG (6)                                           "]
["1","02","07","05","  ","  ",{"$nulls":4}," Injector Wire Scanners                                     ",{"$nulls":6},200,0,17333.558328,0,17333.558328,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","07","05","","","IJ705_1020","1.02.07.05","CBE20705",null,"Assemble Wire Scanners","2006-05-01","2006-06-30",null,"C","SL_MFAT1","Hrs",120,null,10080,null,10080,null,0,null,0,null,0,{"$nulls":10},0.1,0,1.1,1,3,3,"2A"]
["1","02","07","05","","","IJ705_1030","1.02.07.05","CBE20705",null,"Vacuum Process Wire Scanners","2006-07-01","2006-07-30",null,"C","SL_MFAT1","Hrs",40,null,3360,null,3360,null,0,null,0,null,0,{"$nulls":10},0.1,0,1.1,1,3,3,"2A"]
["1","02","07","05","","","IJ705_1040","1.02.07.05","CBE20705",null,"Calibrate Wire Scanners","2006-07-01","2006-09-29",null,"C","SL_ME1","Hrs",40,null,3893.558327999999,null,3893.558327999999,null,0,null,0,null,0,{"$nulls":10},0.1,0,1.1,1,3,3,"2A"]
["1","02","07","06","  ","  ",{"$nulls":4},"LSR HTR - Electron Beam Diagnostics                         "]
["1","02","07","07","  ","  ",{"$nulls":4},"PPS Stopper                                                 "]
["1","02","17","  ","  ","  ",{"$nulls":4},"Injector Installation & Alignment                           ",{"$nulls":6},7242,394220,638944.9670625298,394220,1033164.9670625299,null,459,0,46431.22288234635,0,46431.22288234635,0,null,0,null,23407.475998538244,null,23023.746883808108,null,0,null,null,13929.366864703905]
["1","02","17","01","  ","  ",{"$nulls":4},"Injector Infrastructure Installation                        ",{"$nulls":6},2245,31440,211663.14815794275,31440,243103.14815794275,null,459,0,46431.22288234635,0,46431.22288234635,0,null,0,null,23407.475998538244,null,23023.746883808108,null,0,null,null,13929.366864703905]
["1","02","17","01","","","IJ171_0010","1.02.17.01","CBE21701",null,"IJ System Integration Oversight 2006 Shut Down","2006-05-01","2006-11-30",null,"C","SL_ME1","Hrs",1020,null,100012.90051089125,null,100012.90051089125,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","01","","","IJ171_0020","1.02.17.01","CBE21701",null,"IJ System Integration Oversight 2007 Shut Down","2007-08-01","2007-11-30",null,"C","SL_ME1","Hrs",510,null,51590.24764705151,null,51590.24764705151,null,459,null,46431.22288234635,null,46431.22288234635,{"$nulls":4},23407.475998538244,0.5,23023.746883808108,0.5,null,null,0.3,13929.366864703905,1.15,1.15,4,4,"2A"]
["1","02","17","01","","","IJ171_0110","1.02.17.01","CBE21701",null,"Install LCW systems","2006-08-02","2006-08-16",null,"C","SL_MSPF1","$$",null,13040,null,13040,13040,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.15,1.15,5,4,"2A"]
["1","02","17","01","","","IJ171_0120","1.02.17.01","CBE21701",null,"Install laser tight wall","2006-09-01","2006-09-13",null,"C","SL_MSPF1","$$",null,18400,null,18400,18400,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.15,1.15,5,4,"2A"]
["1","02","17","01","","","IJ171_0200","1.02.17.01","CBE21701",null,"Transport Waveguide to Installation Site","2006-08-01","2006-08-14",null,"C","SL_MFAT1","Hrs",40,null,3360,null,3360,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,3,4,"2A"]
["1","02","17","01","","","IJ171_0210","1.02.17.01","CBE21701",null,"Install Gallery Waveguide","2006-08-01","2006-09-12",null,"C","SL_MFAT1","Hrs",275,null,23100,null,23100,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,3,4,"2A"]
["1","02","17","01","","","IJ171_0220","1.02.17.01","CBE21701",null,"Install Vault Waveguide","2006-08-15","2006-09-26",null,"C","SL_MFAT1","Hrs",400,null,33600,null,33600,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,3,4,"2A"]
["1","02","17","02","  ","  ",{"$nulls":4},"Injector Controls Subsystem Install & Align                 ",{"$nulls":6},0,179240,0,179240,179240,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","17","02","","","IJ172_0040","1.02.17.02","CBE21702",null,"Vault Tray Installation","2006-04-01","2006-05-31",null,"C","SL_MSPF1","$$",null,18920,null,18920,18920,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","02","","","IJ172_0050","1.02.17.02","CBE21702",null,"PPS Boxes & Small Rack Install","2006-05-01","2006-05-31",null,"C","SL_MSPF1","$$",null,18280,null,18280,18280,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","02","","","IJ172_0060","1.02.17.02","CBE21702",null,"Gallery Tray Supports Installation","2006-05-01","2006-05-04",null,"C","SL_MSPF1","$$",null,19560,null,19560,19560,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","02","","","IJ172_0070","1.02.17.02","CBE21702",null,"Gallery Tray Installation","2006-05-08","2006-05-11",null,"C","SL_MSPF1","$$",null,19560,null,19560,19560,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","02","","","IJ172_0080","1.02.17.02","CBE21702",null,"DC Cable Installation","2006-05-15","2006-07-30",null,"C","SL_MSPF1","$$",null,22760,null,22760,22760,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","02","","","IJ172_0090","1.02.17.02","CBE21702",null,"PPS Cable Installation","2006-05-01","2006-05-03",null,"C","SL_MSPF1","$$",null,18920,null,18920,18920,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","02","","","IJ172_0100","1.02.17.02","CBE21702",null,"I&C Cable Installation","2006-05-01","2006-07-30",null,"C","SL_MSPF1","$$",null,22760,null,22760,22760,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","02","","","IJ172_0110","1.02.17.02","CBE21702",null,"Rack Installation in Gallery","2006-06-01","2006-07-30",null,"C","SL_MSPF1","$$",null,19560,null,19560,19560,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","02","","","IJ172_0120","1.02.17.02","CBE21702",null,"Cable Tagging and Testing","2006-06-01","2006-07-30",null,"C","SL_MSPF1","$$",null,18920,null,18920,18920,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","03","  ","  ",{"$nulls":4},"Injector Lasers Install & Align                             ",{"$nulls":6},1336,141320,118267.68997777917,141320,259587.68997777914,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","17","03","","","IJ17030105","1.02.17.03","CBE21703",null,"Install Laser Bay Optical Tables/Alignment Laser","2006-07-01","2006-07-30","S","C","SL_OT1","Hrs",40,null,2412.5357519999993,null,2412.5357519999993,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","03","","","IJ17030115","1.02.17.03","CBE21703",null,"Install laser heater optical path","2006-08-02","2006-08-22","S","C","SL_MFAT1","Hrs",80,null,6720,null,6720,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,5,4,"2A"]
["1","02","17","03","","","IJ17030120","1.02.17.03","CBE21703",null,"Install EO optical paths","2006-05-01","2006-05-19","S","C","SL_MFAT1","Hrs",80,null,6720,null,6720,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","03","","","IJ17030125","1.02.17.03","CBE21703",null,"Install Synch Light Tube/Light Path for Strk Cam","2006-05-01","2006-05-19","S","C","SL_OT1","Hrs",80,null,4825.071503999999,null,4825.071503999999,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","03","","","IJ17030125","1.02.17.03","CBE21703",null,"Install Synch Light Tube/Light Path for Strk Cam","2006-05-01","2006-05-19","S","C","SL_MFAT1","Hrs",40,null,3360,null,3360,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","03","","","IJ173_0030","1.02.17.03","CBE21703",null,"Install Cables above table","2006-05-01","2006-07-30",null,"C","SL_MSPF1","$$",null,21760,null,21760,21760,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","03","","","IJ173_0040","1.02.17.03","CBE21703",null,"Ceiling closed room cleaned","2006-07-01","2006-07-30",null,"C","SL_MFAT1","Hrs",72,null,6048,null,6048,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","03","","","IJ173_0050","1.02.17.03","CBE21703",null,"Install Table legs room cleaned","2006-07-01","2006-07-30",null,"C","SL_MSPF1","$$",null,9600,null,9600,9600,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","03","","","IJ173_0060","1.02.17.03","CBE21703",null,"Install Tables","2006-07-01","2006-07-30",null,"C","SL_MSPF1","$$",null,5760,null,5760,5760,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","03","","","IJ173_0070","1.02.17.03","CBE21703",null,"Install Table enclosures","2006-07-01","2006-07-30",null,"C","SL_MSPF1","$$",null,9600,null,9600,9600,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","03","","","IJ173_0090","1.02.17.03","CBE21703",null,"Install Laser safety panels to wall","2006-07-01","2006-07-30",null,"C","SL_CE1","Hrs",64,null,7050.698265599999,null,7050.698265599999,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","03","","","IJ173_0100","1.02.17.03","CBE21703",null,"Instal lLaser safety door switches","2006-07-01","2006-07-30",null,"C","SL_CE1","Hrs",128,null,14101.396531199998,null,14101.396531199998,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","03","","","IJ173_0110","1.02.17.03","CBE21703",null,"Install Laser safety wiring","2006-06-01","2006-07-30",null,"C","SL_CE1","Hrs",128,null,14101.396531199998,null,14101.396531199998,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","03","","","IJ173_0120","1.02.17.03","CBE21703",null,"Certify laser safety system","2006-07-01","2006-07-30",null,"C","SL_CE1","Hrs",80,null,8813.372832,null,8813.372832,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","03","","","IJ173_0150","1.02.17.03","CBE21703",null,"Water system available in laser bay","2006-07-01","2006-07-30",null,"C","SL_MSPF1","$$",null,25000,null,25000,25000,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","03","","","IJ173_0170","1.02.17.03","CBE21703",null,"Install loaded racks","2006-07-01","2006-07-30",null,"C","SL_MSPF1","$$",null,18200,null,18200,18200,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","03","","","IJ173_0180","1.02.17.03","CBE21703",null,"Conduit to racks","2006-07-01","2006-07-30",null,"C","SL_MSPF1","$$",null,18200,null,18200,18200,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","03","","","IJ173_0190","1.02.17.03","CBE21703",null,"Power to racks","2006-07-01","2006-07-30",null,"C","SL_MSPF1","$$",null,18200,null,18200,18200,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","03","","","IJ173_0200","1.02.17.03","CBE21703",null,"Utilities Installed","2006-07-01","2006-07-30",null,"C","SL_MSPF1","$$",null,15000,null,15000,15000,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","03","","","IJ173_0220","1.02.17.03","CBE21703",null,"Install","2006-07-01","2006-07-30",null,"C","SL_OT1","Hrs",80,null,4825.071503999999,null,4825.071503999999,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","03","","","IJ173_0230","1.02.17.03","CBE21703",null,"Characterization","2006-07-01","2006-07-30",null,"C","SL_OT1","Hrs",160,null,9650.143007999997,null,9650.143007999997,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","03","","","IJ173_0240","1.02.17.03","CBE21703",null,"Training","2006-07-01","2006-07-30",null,"C","SL_OT1","Hrs",80,null,4825.071503999999,null,4825.071503999999,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","03","","","IJ173_0260","1.02.17.03","CBE21703",null,"Install shutters\\","2006-07-01","2006-07-30",null,"C","SL_CE1","Hrs",16,null,1762.6745663999998,null,1762.6745663999998,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","03","","","IJ173_0270","1.02.17.03","CBE21703",null,"Install wiring to lasers","2006-07-01","2006-07-30",null,"C","SL_CE1","Hrs",80,null,8813.372832,null,8813.372832,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","03","","","IJ173_0280","1.02.17.03","CBE21703",null,"Test","2006-08-02","2006-08-08",null,"C","SL_CE1","Hrs",80,null,8813.372832,null,8813.372832,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,3,4,"2A"]
["1","02","17","03","","","IJ173_0290","1.02.17.03","CBE21703",null,"Certification by LSO","2006-10-31","2006-11-01",null,"C","SL_CE1","Hrs",48,null,5425.5123153792,null,5425.5123153792,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,3,4,"2A"]
["1","02","17","04","  ","  ",{"$nulls":4},"Gun Area Integration                                        ",{"$nulls":6},672,7680,56819.40599475199,7680,64499.40599475199,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","17","04","","","IJ174_0020","1.02.17.04","CBE21704",null,"Planning, preperation and staging prior to downt","2006-08-01","2006-08-31",null,"C","SL_MFAT1","Hrs",320,null,26880,null,26880,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,5,4,"2A"]
["1","02","17","04","","","IJ174_0030","1.02.17.04","CBE21704",null,"Transport Equipment to S20","2006-08-01","2006-11-14",null,"C","SL_MFAT1","Hrs",8,null,679.3216000000001,null,679.3216000000001,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","04","","","IJ174_0040","1.02.17.04","CBE21704",null,"Lower Equipment into Vault","2006-08-01","2006-11-14",null,"C","SL_MFAT1","Hrs",8,null,679.3216000000001,null,679.3216000000001,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","04","","","IJ174_0050","1.02.17.04","CBE21704",null,"Install RF Gun/GTL Support Assy","2006-11-15","2006-11-15",null,"C","SL_MSPF1","$$",null,3840,null,3840,3840,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","04","","","IJ174_0060","1.02.17.04","CBE21704",null,"Align RF Gun/GTL Support Assy","2006-11-16","2006-11-17",null,"C","SL_MES1","Hrs",32,null,2569.357397376,null,2569.357397376,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","04","","","IJ174_0070","1.02.17.04","CBE21704",null,"Install GTL Assy","2006-11-20","2006-11-21",null,"C","SL_MFAT1","Hrs",32,null,2757.8880000000004,null,2757.8880000000004,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","04","","","IJ174_0080","1.02.17.04","CBE21704",null,"Install GTL Spectrometer Assy","2006-11-22","2006-11-29",null,"C","SL_MFAT1","Hrs",96,null,8273.664,null,8273.664,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","04","","","IJ174_0090","1.02.17.04","CBE21704",null,"Make up vacuum interconnections","2006-11-30","2006-12-01",null,"C","SL_MFAT1","Hrs",16,null,1378.9440000000002,null,1378.9440000000002,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","04","","","IJ174_0100","1.02.17.04","CBE21704",null,"Install RF Gun Assembly","2006-12-15","2006-12-18",null,"C","SL_MFAT1","Hrs",64,null,5515.776000000001,null,5515.776000000001,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","04","","","IJ174_0110","1.02.17.04","CBE21704",null,"Pumpdown and leak check","2006-12-19","2006-12-20",null,"C","SL_MFAT1","Hrs",32,null,2757.8880000000004,null,2757.8880000000004,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","04","","","IJ174_0120","1.02.17.04","CBE21704",null,"Install Gun Solenoid","2006-12-21","2006-12-22",null,"C","SL_MFAT1","Hrs",32,null,2757.8880000000004,null,2757.8880000000004,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","04","","","IJ174_0130","1.02.17.04","CBE21704",null,"Install Plumbing","2006-12-26","2006-12-27",null,"C","SL_MSPF1","$$",null,3840,null,3840,3840,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","04","","","IJ174_0140","1.02.17.04","CBE21704",null,"Final Alignment","2006-12-28","2006-12-29",null,"C","SL_MES1","Hrs",32,null,2569.357397376,null,2569.357397376,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","06","  ","  ",{"$nulls":4},"Accelerator Area Integration                                ",{"$nulls":6},896,13540,75744.43758950406,13540,89284.43758950406,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","02","17","06","","","IJ176_0020","1.02.17.06","CBE21706",null,"Planning, preperation and staging prior to downt","2006-08-01","2006-08-31",null,"C","SL_MFAT1","Hrs",320,null,26880,null,26880,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,5,4,"2A"]
["1","02","17","06","","","IJ176_0030","1.02.17.06","CBE21706",null,"Transport Equipment to S20","2006-08-01","2006-10-31",null,"C","SL_MFAT1","Hrs",8,null,677.76,null,677.76,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","06","","","IJ176_0040","1.02.17.06","CBE21706",null,"Lower Equipment to S20 Vault","2006-08-01","2006-10-31",null,"C","SL_MFAT1","Hrs",8,null,677.76,null,677.76,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","06","","","IJ176_0050","1.02.17.06","CBE21706",null,"Install supports","2006-11-01","2006-11-01",null,"C","SL_MSPF1","$$",null,3840,null,3840,3840,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","06","","","IJ176_0060","1.02.17.06","CBE21706",null,"Install L0A structure","2006-11-02","2006-11-03",null,"C","SL_MFAT1","Hrs",32,null,2757.8880000000004,null,2757.8880000000004,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","06","","","IJ176_0070","1.02.17.06","CBE21706",null,"Install L0B structure","2006-11-06","2006-11-07",null,"C","SL_MFAT1","Hrs",32,null,2757.8880000000004,null,2757.8880000000004,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","06","","","IJ176_0080","1.02.17.06","CBE21706",null,"Align L0A and L0B","2006-11-08","2006-11-09",null,"C","SL_MES1","Hrs",32,null,2569.357397376,null,2569.357397376,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","06","","","IJ176_0090","1.02.17.06","CBE21706",null,"Install RF output W/G to L0A","2006-11-10","2006-11-16",null,"C","SL_MFAT1","Hrs",120,null,10342.08,null,10342.08,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","06","","","IJ176_0100","1.02.17.06","CBE21706",null,"Install YAG03","2006-11-17","2006-11-17",null,"C","SL_MFAT1","Hrs",8,null,689.4720000000001,null,689.4720000000001,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","06","","","IJ176_0110","1.02.17.06","CBE21706",null,"Align YAG03","2006-11-20","2006-11-20",null,"C","SL_MES1","Hrs",16,null,1284.678698688,null,1284.678698688,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","06","","","IJ176_0130","1.02.17.06","CBE21706",null,"Install Magnet QA01","2006-11-22","2006-11-22",null,"C","SL_MFAT1","Hrs",16,null,1378.9440000000002,null,1378.9440000000002,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","06","","","IJ176_0240","1.02.17.06","CBE21706",null,"Install RF output W/G to L0B","2006-12-11","2006-12-15",null,"C","SL_MFAT1","Hrs",120,null,10342.08,null,10342.08,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","07","","","IJ177_0080","1.02.17.07","CBE21707",null,"Interconnect Vat Valve and Current Monitor","2006-10-16","2006-10-16",null,"C","SL_MFAT1","Hrs",8,null,689.4720000000001,null,689.4720000000001,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","07","","","IJ177_0150","1.02.17.07","CBE21707",null,"Transport Equipment to S20","2006-08-01","2006-10-06",null,"C","SL_MFAT1","Hrs",8,null,673.3236363636363,null,673.3236363636363,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","07","","","IJ177_0270","1.02.17.07","CBE21707",null,"Allign Beamline Spoolpiece w/Bellows","2006-10-23","2006-10-23",null,"C","SL_MES1","Hrs",8,null,642.339349344,null,642.339349344,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","07","","","IJ177_0300","1.02.17.07","CBE21707",null,"Align T Cavity","2006-10-26","2006-10-26",null,"C","SL_MES1","Hrs",16,null,1284.678698688,null,1284.678698688,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","07","","","IJ177_0370","1.02.17.07","CBE21707",null,"Align QE04 w/BPM09","2006-11-06","2006-11-06",null,"C","SL_MES1","Hrs",16,null,1284.678698688,null,1284.678698688,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","09","","","IJ179_0110","1.02.17.09","CBE21709",null,"Align Current Monitor","2006-10-09","2006-10-09",null,"C","SL_MES1","Hrs",16,null,1284.678698688,null,1284.678698688,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","09","","","IJ179_0180","1.02.17.09","CBE21709",null,"Install 2ea Flex Coupling","2006-10-18","2006-10-18",null,"C","SL_MFAT1","Hrs",16,null,1378.9440000000002,null,1378.9440000000002,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","09","","","IJ179_0300","1.02.17.09","CBE21709",null,"Install Vat Valve VV04","2006-11-22","2006-11-22",null,"C","SL_MFAT1","Hrs",16,null,1378.9440000000002,null,1378.9440000000002,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","09","","","IJ179_0420","1.02.17.09","CBE21709",null,"Tighten flanges","2006-12-13","2006-12-13",null,"C","SL_MFAT1","Hrs",8,null,689.4720000000001,null,689.4720000000001,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","09","","","IJ179_0490","1.02.17.09","CBE21709",null,"Install Wire Scanner WS04","2006-12-22","2006-12-22",null,"C","SL_MFAT1","Hrs",16,null,1378.9440000000002,null,1378.9440000000002,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","11","","","IJ1711_060","1.02.17.11","CBE21711",null,"Install Vat Valve VVS1","2006-11-20","2006-11-20",null,"C","SL_MFAT1","Hrs",8,null,689.4720000000001,null,689.4720000000001,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","11","","","IJ1711_090","1.02.17.11","CBE21711",null,"Install Bend Magnet BXS","2006-11-27","2006-11-27",null,"C","SL_MFAT1","Hrs",48,null,4136.832,null,4136.832,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.15,1.15,4,4,"2A"]
["1","02","17","12","  ","  ",{"$nulls":4},"Injector RF High Power System Install & Align               "]
["1","02","17","17","  ","  ",{"$nulls":4},"Power  Conversion Subsystem Installation                    "]
["1","03","01","01","01","","LN101-1010","1.03.01.01.01","CBX3010101",null,"L01 Installation Oversight","2006-08-01","2007-01-05",null,"C","SL_MDD1","Hrs",80,null,6632.727121232714,null,6632.727121232714,null,0,null,0,null,0,{"$nulls":10},0.15,0,1.1,1.05,5,1,"2A"]
["1","03","01","01","02","","LN101-2070","1.03.01.01.02","CBX3010102",null,"BC1 Installation Oversight","2006-08-01","2007-01-05",null,"C","SL_ME1","Hrs",114,null,11273.056626660258,null,11273.056626660258,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,5,1,"2A"]
["1","03","01","01","03","","LN101-3060","1.03.01.01.03","CBX3010103",null,"L2 System Construction Support to Components","2007-11-01","2008-06-30",null,"C","SL_CE1","Hrs",120,null,13916.439088947645,null,13916.439088947645,null,120,null,13916.439088947645,null,13916.439088947645,{"$nulls":6},13916.439088947645,1,null,null,0.15,2087.465863342147,1.1,1.05,5,1,"2A"]
["1","03","01","01","04","","LN101-4030","1.03.01.01.04","CBX3010104","9242580","BC2 Emittance Section Design","2007-01-03","2007-07-02",null,"C","SL_ME1","Hrs",160,null,15979.163378111998,null,15979.163378111998,null,96,null,9587.498026867199,null,9587.498026867199,{"$nulls":4},9587.498026867199,1,{"$nulls":4},0.25,2396.8745067167997,1.15,1.1,5,2,"2A"]
["1","03","01","01","04","","LN101-4100","1.03.01.01.04","CBX3010104","9242580","BC2 Top Assembly","2006-07-05","2007-05-01",null,"C","SL_ME1","Hrs",330,null,32712.041777358238,null,32712.041777358238,null,82.5,null,8128.446744676894,null,8128.446744676894,null,null,2384.3443784385554,0.29,5744.102366238339,0.71,{"$nulls":4},0.25,2032.1116861692235,1.15,1.1,5,2,"2A"]
["1","03","01","01","05","","LN101-5040","1.03.01.01.05","CBX3010105","9242581","L3 Installation Oversight","2007-09-04","2007-10-31",null,"C","SL_MDD1","Hrs",40,null,3395.1739789123194,null,3395.1739789123194,null,40,null,3395.1739789123194,null,3395.1739789123194,{"$nulls":4},1608.2403058005723,0.47,1786.9336731117469,0.53,null,null,0.15,509.2760968368479,1.1,1.05,5,1,"2A"]
["1","03","01","01","05","","LN101-5060","1.03.01.01.05","CBX3010105","9242581","L3 System Construction Support to Components","2007-12-03","2008-06-30",null,"C","SL_ME1","Hrs",80,null,8197.310812971453,null,8197.310812971453,null,80,null,8197.310812971453,null,8197.310812971453,{"$nulls":6},8197.310812971453,1,null,null,0.15,1229.596621945718,1.1,1.05,5,1,"2A"]
["1","03","01","01","06","","LN101-6050","1.03.01.01.06","CBX3010106","9242582","LTU Procurement Support","2007-01-08","2007-06-27",null,"C","SL_ME1","Hrs",80,null,7989.581689055999,null,7989.581689055999,null,76,null,7590.102604603199,null,7590.102604603199,{"$nulls":4},7590.102604603199,1,{"$nulls":4},0.3,2277.0307813809595,1.2,1.1,5,1,"2A"]
["1","03","01","01","06","","LN101-6100","1.03.01.01.06","CBX3010106","9242582","LTU Water System Design Support","2006-09-27","2007-03-21",null,"C","SL_ME1","Hrs",400,null,39924.76958435931,null,39924.76958435931,null,160,null,15969.907833743724,null,15969.907833743724,null,null,365.02646477128513,0.02,15604.881368972437,0.98,{"$nulls":4},0.3,4790.972350123117,1.2,1.1,5,2,"2A"]
["1","03","01","01","07","","LN101-7020","1.03.01.01.07","CBX3010107","9242583","E-Dump Pedestal and Raft Design","2007-01-08","2007-05-30",null,"C","SL_ME1","Hrs",120,null,11984.372533583999,null,11984.372533583999,null,18,null,1797.6558800375997,null,1797.6558800375997,{"$nulls":4},1797.6558800375997,1,{"$nulls":4},0.3,539.2967640112798,1.2,1.1,5,2,"2A"]
["1","03","01","01","07","","LN101-7110","1.03.01.01.07","CBX3010107","9242583","E-Dump Vibration Engineering","2006-08-01","2007-01-23",null,"C","SL_ME1","Hrs",80,null,7919.008163247908,null,7919.008163247908,null,16,null,1583.8016326495817,null,1583.8016326495817,null,null,552.0679976664256,0.35,1031.7336349831562,0.65,{"$nulls":4},0.3,475.1404897948745,1.2,1.1,5,2,"2A"]
["1","03","01","01","07","","LN101-7160","1.03.01.01.07","CBX3010107","9242583","E-Dump Layout & CF Interface","2006-07-05","2006-07-31",null,"C","SL_MDD1","Hrs",84,null,6855.376096799999,null,6855.376096799999,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.2,1.1,5,1,"2A"]
["1","03","01","04","","","LN104-0060","1.03.01.04","CAX30104","9242585","Cost Account Managers - CONST","2006-07-05","2007-01-02",null,"C","SL_ME1","Hrs",564,null,55632.57683874013,null,55632.57683874013,null,0,null,0,null,0,{"$nulls":10},0.1,0,1.1,1,4,1,"2A"]
["1","03","01","04","","","LN104-1050","1.03.01.04","CAX30104","9242585","Linac System Management Effort - CONST 70%","2007-01-03","2007-11-30",null,"C","SL_TSM1","Hrs",434,null,46302.87224313688,null,46302.87224313688,null,277.76,null,29659.443510580764,null,29659.443510580764,{"$nulls":4},24283.10933947851,0.82,5376.334171102253,0.18,null,null,0.1,2965.944351058077,1.1,1,4,1,"2A"]
["1","03","01","04","","","LN104-1070","1.03.01.04","CAX30104","9242585","Fabrication Coordination 70%","2007-01-03","2007-11-30",null,"C","SL_ME1","Hrs",319,null,32008.605604134278,null,32008.605604134278,null,204.16,null,20469.45311361565,null,20469.45311361565,{"$nulls":4},16758.97822897233,0.82,3710.4748846433204,0.18,null,null,0.1,2046.9453113615652,1.1,1,4,1,"2A"]
["1","03","02","01","","","LN201_0810","1.03.02.01","CBCLN30201","9242586","LTU Rack and Wiring Bid Prep","2007-07-05","2007-10-16",null,"C","SL_CCA1","Hrs",160,null,10572.379303834008,null,10572.379303834008,null,152,null,10043.760338642309,null,10043.760338642309,{"$nulls":4},8581.076794179837,0.85,1462.6835444624721,0.15,null,null,0.25,2510.940084660577,1.15,1.1,3,3,"2G","P. Bong"]
["1","03","02","01","","","LN201_0855","1.03.02.01","CBCLN30201","9242586","RCV: 50 EO buttons","2007-07-27","2007-07-27",null,"C","SL_MSEG1","$$",null,9000,null,9677.232,9677.232,null,null,9000,null,9677.232,9677.232,{"$nulls":4},9677.232,1,{"$nulls":4},0.25,2419.308,1.15,1.1,2,3,"2G","P. Bong"]
["1","03","02","01","","","LN201_0915","1.03.02.01","CBCLN30201","9242586","RCV: 4 Hoffman Boxes","2007-07-27","2007-07-27",null,"C","SL_MSEG1","$$",null,520,null,559.12896,559.12896,null,null,520,null,559.12896,559.12896,{"$nulls":4},559.12896,1,{"$nulls":4},0.25,139.78224,1.15,1.1,2,3,"2G","P. Bong"]
["1","03","02","02","","","LN202_0015","1.03.02.02","CBBLN30202","9242587","Write System Documentation","2006-08-01","2006-09-12",null,"C","SL_CE1","Hrs",8,null,881.3372831999999,null,881.3372831999999,null,5.2,null,572.86923408,null,572.86923408,null,null,572.86923408,1,{"$nulls":6},0.25,143.21730852,1.15,1.1,3,3,"2G","K. Traeger"]
["1","03","02","02","","","LN202_0130","1.03.02.02","CBCLN30202","9242587","RCV: 750 Lion Cables","2007-03-02","2007-03-02",null,"C","SL_MSEG1","$$",null,15000,null,16128.72,16128.72,null,null,15000,null,16128.72,16128.72,{"$nulls":4},16128.72,1,{"$nulls":4},0.25,4032.18,1.15,1.1,4,3,"2G","K. Traeger"]
["1","03","02","02","","","LN202_0250","1.03.02.02","CBDLN30202","9242587","XTOD H/W Fabrication","2007-03-05","2007-06-25",null,"C","SL_CE1","Hrs",40,null,4521.260262816,null,4521.260262816,null,40,null,4521.260262816,null,4521.260262816,{"$nulls":4},4521.260262816,1,{"$nulls":4},0.25,1130.315065704,1.15,1.1,4,3,"2G","K. Traeger"]
["1","03","02","04","01","  ",{"$nulls":4},"Beamline Power Supplies - (Dipole Type)                     ",{"$nulls":6},1860,162950,157763.40204865942,175117.38352000006,332880.78556865966,null,1680,120260,138493.9264427691,129215.04639999995,267708.97284276935,0,null,7057.461249328027,null,252553.97259582262,null,8097.538997618553,null,0,null,null,61188.48324269229]
["1","03","02","04","01","01","LN40101020","1.03.02.04.01","CBBLN40101","9242226","RCV: Transductors","2006-10-30","2006-10-30",null,"C","SL_MSEG1","$$",null,1320,null,1419.32736,1419.32736,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","01","02","LN40102040","1.03.02.04.01","CBBLN40102","9242226","RCV: Intra-rack Cables and Connectors","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,40,null,41.92,41.92,null,null,40,null,41.92,41.92,null,null,41.92,1,{"$nulls":6},0.2,8.384,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","01","03",{"$nulls":4},"Kicker Power Supply BXKIK                                   ",{"$nulls":6},826,18665,70005.93535880178,20069.50392,90075.43927880179,null,746,8950,61041.704639384545,9623.469599999997,70665.17423938455,0,null,309.82813035693397,null,67327.761808854,null,3027.584300173605,null,0,null,null,17265.763679846135]
["1","03","02","04","01","03","LN40103085","1.03.02.04.01","CBBLN4103","9242226","RCV:  DIO Module - 8 Chan","2007-01-18","2007-01-18",null,"C","SL_MSEG1","$$",null,500,null,537.624,537.624,null,null,500,null,537.624,537.624,{"$nulls":4},537.624,1,{"$nulls":4},0.2,107.52480000000001,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","01","03","LN40103110","1.03.02.04.01","CBBLN4103","9242226","Fab & Assy- Power Supply","2007-04-13","2007-06-12",null,"C","SL_PCCA1","Hrs",42,null,2764.7809790832,null,2764.7809790832,null,42,null,2764.7809790832,null,2764.7809790832,{"$nulls":4},2764.7809790832,1,{"$nulls":4},0.25,691.1952447708,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","04","LN40104015","1.03.02.04.01","CBBLN40104","9242226","RCV: Power Supply","2007-03-15","2007-03-15",null,"C","SL_MSEG1","$$",null,34500,null,37096.056,37096.056,null,null,34500,null,37096.056,37096.056,{"$nulls":4},37096.056,1,{"$nulls":4},0.2,7419.2112,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","01","04","LN40104060","1.03.02.04.01","CBBLN40104","9242226","Integrate cables","2007-03-23","2007-03-23",null,"C","SL_TMUE1","Hrs",8,null,768.170304,null,768.170304,null,8,null,768.170304,null,768.170304,{"$nulls":4},768.170304,1,{"$nulls":4},0.25,192.042576,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","05","LN40105055","1.03.02.04.01","CBBLN40105","9242226","Pre-install Qual Test","2007-03-20","2007-03-22",null,"C","SL_PCE1","Hrs",8,null,904.2520525632,null,904.2520525632,null,8,null,904.2520525632,null,904.2520525632,{"$nulls":4},904.2520525632,1,{"$nulls":4},0.25,226.0630131408,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","06",{"$nulls":4},"Kicker Power Supply BYKIK                                   ",{"$nulls":6},826,18665,70056.75889082404,20069.50392,90126.26281082405,null,758,8950,62445.61364562134,9623.469599999997,72069.08324562135,0,null,495.7250085710944,null,66503.40353960531,null,5069.954697444948,null,0,null,null,17536.097331405337]
["1","03","02","04","01","06","LN40106085","1.03.02.04.01","CBBLN40106","9242226","RCV:  DIO Module - 8 Chan","2007-01-18","2007-01-18",null,"C","SL_MSEG1","$$",null,500,null,537.624,537.624,null,null,500,null,537.624,537.624,{"$nulls":4},537.624,1,{"$nulls":4},0.2,107.52480000000001,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","01","06","LN40106110","1.03.02.04.01","CBBLN40106","9242226","Fab & Assy- Power Supply","2007-04-13","2007-06-12",null,"C","SL_PCCA1","Hrs",42,null,2764.7809790832,null,2764.7809790832,null,42,null,2764.7809790832,null,2764.7809790832,{"$nulls":4},2764.7809790832,1,{"$nulls":4},0.25,691.1952447708,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","07","LN40107015","1.03.02.04.01","CBBLN40107","9242226","RCV: Power Supply","2007-03-15","2007-03-15",null,"C","SL_MSEG1","$$",null,11800,null,12687.9264,12687.9264,null,null,11800,null,12687.9264,12687.9264,{"$nulls":4},12687.9264,1,{"$nulls":4},0.2,2537.5852800000002,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","01","07","LN40107055","1.03.02.04.01","CBBLN40107","9242226","Pre-install Qual Test","2007-03-20","2007-03-22",null,"C","SL_PCE1","Hrs",8,null,904.2520525632,null,904.2520525632,null,8,null,904.2520525632,null,904.2520525632,{"$nulls":4},904.2520525632,1,{"$nulls":4},0.25,226.0630131408,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","01","08","LN40108055","1.03.02.04.01","CBBLN40108","9242226","Pre-install Qual Test","2007-03-20","2007-03-22",null,"C","SL_PCCA1","Hrs",8,null,526.6249483967999,null,526.6249483967999,null,8,null,526.6249483967999,null,526.6249483967999,{"$nulls":4},526.6249483967999,1,{"$nulls":4},0.25,131.65623709919998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","06","LN40206015","1.03.02.04.02","CBBLN40206","9242589","RCV: Hardware","2006-08-02","2006-08-02",null,"C","SL_MSEG1","$$",null,3222,null,3376.656,3376.656,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","07","LN40207015","1.03.02.04.02","CBBLN40207","9242589","RCV:  Power Supply  Q24601","2007-03-15","2007-03-15",null,"C","SL_MSEG1","$$",null,11800,null,12687.9264,12687.9264,null,null,11800,null,12687.9264,12687.9264,{"$nulls":4},12687.9264,1,{"$nulls":4},0.2,2537.5852800000002,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","07","LN40207020","1.03.02.04.02","CBBLN40207","9242589","RCV: Transductors","2007-03-15","2007-03-15",null,"C","SL_MSEG1","$$",null,3960,null,4257.98208,4257.98208,null,null,3960,null,4257.98208,4257.98208,{"$nulls":4},4257.98208,1,{"$nulls":4},0.2,851.596416,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","10","LN40210045","1.03.02.04.02","CBBLN40210","9242589","Bench test and perform safety inspection of PS","2007-03-16","2007-03-19",null,"C","SL_PCT1","Hrs",4,null,247.5261681551999,null,247.5261681551999,null,4,null,247.5261681551999,null,247.5261681551999,{"$nulls":4},247.5261681551999,1,{"$nulls":4},0.25,61.88154203879998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","10","LN40210055","1.03.02.04.02","CBBLN40210","9242589","Pre-install Qual Test","2007-03-16","2007-03-20",null,"C","SL_PCCA1","Hrs",4,null,263.31247419839997,null,263.31247419839997,null,4,null,263.31247419839997,null,263.31247419839997,{"$nulls":4},263.31247419839997,1,{"$nulls":4},0.25,65.82811854959999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","12","LN40212055","","CBBLN40212",null,"Pre-install Qual Test","2007-03-16","2007-03-20",null,"C","SL_PCCA1","Hrs",4,null,263.31247419839997,null,263.31247419839997,null,4,null,263.31247419839997,null,263.31247419839997,{"$nulls":4},263.31247419839997,1,{"$nulls":4},0.25,65.82811854959999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","13","LN40213041","1.03.02.04.02","CBBLN40213","9242589","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-03-15","2007-03-15",null,"C","SL_MSEG1","$$",null,100,null,107.5248,107.5248,null,null,100,null,107.5248,107.5248,{"$nulls":4},107.5248,1,{"$nulls":4},0.2,21.50496,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","14","LN40214041","1.03.02.04.02","CBBLN40214","9242589","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-03-15","2007-03-15",null,"C","SL_MSEG1","$$",null,100,null,107.5248,107.5248,null,null,100,null,107.5248,107.5248,{"$nulls":4},107.5248,1,{"$nulls":4},0.2,21.50496,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","15","LN40215045","1.03.02.04.02","CBBLN40215","9242589","Bench test and perform safety inspection of PS","2007-03-16","2007-03-19",null,"C","SL_PCT1","Hrs",4,null,247.5261681551999,null,247.5261681551999,null,4,null,247.5261681551999,null,247.5261681551999,{"$nulls":4},247.5261681551999,1,{"$nulls":4},0.25,61.88154203879998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","16","LN40216020","1.03.02.04.02","CBBLN40216","9242589","RCV: Transductors","2007-03-15","2007-03-15",null,"C","SL_MSEG1","$$",null,1320,null,1419.32736,1419.32736,null,null,1320,null,1419.32736,1419.32736,{"$nulls":4},1419.32736,1,{"$nulls":4},0.2,283.865472,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","16","LN40216041","1.03.02.04.02","CBBLN40216","9242589","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-03-15","2007-03-15",null,"C","SL_MSEG1","$$",null,100,null,107.5248,107.5248,null,null,100,null,107.5248,107.5248,{"$nulls":4},107.5248,1,{"$nulls":4},0.2,21.50496,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","17","LN40217060","1.03.02.04.02","CBBLN40217","9242589","Integrate cables","2007-03-16","2007-03-16",null,"C","SL_TMUE1","Hrs",8,null,768.170304,null,768.170304,null,8,null,768.170304,null,768.170304,{"$nulls":4},768.170304,1,{"$nulls":4},0.25,192.042576,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","18","LN40218020","1.03.02.04.02","CBBLN40218","9242589","RCV: Transductors","2007-03-15","2007-03-15",null,"C","SL_MSEG1","$$",null,1320,null,1419.32736,1419.32736,null,null,1320,null,1419.32736,1419.32736,{"$nulls":4},1419.32736,1,{"$nulls":4},0.2,283.865472,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","19","LN40219030","1.03.02.04.02","CBBLN40219","9242589","RCV: PS Controller","2007-03-15","2007-03-15",null,"C","SL_MSEG1","$$",null,2000,null,2150.496,2150.496,null,null,2000,null,2150.496,2150.496,{"$nulls":4},2150.496,1,{"$nulls":4},0.25,537.624,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","19","LN40219060","1.03.02.04.02","CBBLN40219","9242589","Integrate cables","2007-03-16","2007-03-16",null,"C","SL_TMUE1","Hrs",8,null,768.170304,null,768.170304,null,8,null,768.170304,null,768.170304,{"$nulls":4},768.170304,1,{"$nulls":4},0.25,192.042576,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","21",{"$nulls":4},"Power Supply  QVB1-3                                        ",{"$nulls":6},24,15260,1978.6611407903997,16408.28448,18386.945620790397,null,24,3460,1978.6611407903997,3720.3580800000004,5699.019220790401,0,null,0,null,5699.019220790401,null,0,null,0,null,null,1346.2617011976001]
["1","03","02","04","02","22","LN40222015","1.03.02.04.02","CBBLN40222","9242589","RCV: Power Supply","2007-03-15","2007-03-15",null,"C","SL_MSEG1","$$",null,23800,null,25590.9024,25590.9024,null,null,23800,null,25590.9024,25590.9024,{"$nulls":4},25590.9024,1,{"$nulls":4},0.2,5118.18048,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","22","LN40222055","1.03.02.04.02","CBBLN40222","9242589","Pre-install Qual Test","2007-03-20","2007-03-22",null,"C","SL_PCE1","Hrs",4,null,452.1260262816,null,452.1260262816,null,4,null,452.1260262816,null,452.1260262816,{"$nulls":4},452.1260262816,1,{"$nulls":4},0.25,113.0315065704,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","23",{"$nulls":4},"Power Supply  QE31-36                                       ",{"$nulls":6},24,15260,1978.6611407903997,16408.28448,18386.945620790397,null,24,15260,1978.6611407903997,16408.28448,18386.945620790397,0,null,0,null,18386.945620790397,null,0,null,0,null,null,3883.8469811976]
["1","03","02","04","02","24","LN40224041","1.03.02.04.02","CBBLN40224","9242589","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-03-15","2007-03-15",null,"C","SL_MSEG1","$$",null,100,null,107.5248,107.5248,null,null,100,null,107.5248,107.5248,{"$nulls":4},107.5248,1,{"$nulls":4},0.2,21.50496,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","24","LN40224055","1.03.02.04.02","CBBLN40224","9242589","Pre-install Qual Test","2007-03-20","2007-03-22",null,"C","SL_PCE1","Hrs",4,null,452.1260262816,null,452.1260262816,null,4,null,452.1260262816,null,452.1260262816,{"$nulls":4},452.1260262816,1,{"$nulls":4},0.25,113.0315065704,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","25","LN40225055","1.03.02.04.02","CBBLN40225","9242589","Pre-install Qual Test","2007-03-20","2007-03-22",null,"C","SL_PCCA1","Hrs",4,null,263.31247419839997,null,263.31247419839997,null,4,null,263.31247419839997,null,263.31247419839997,{"$nulls":4},263.31247419839997,1,{"$nulls":4},0.25,65.82811854959999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","26","LN40226045","1.03.02.04.02","CBBLN40226","9242589","Bench test and perform safety inspection of PS","2007-03-16","2007-03-19",null,"C","SL_PCT1","Hrs",4,null,247.5261681551999,null,247.5261681551999,null,4,null,247.5261681551999,null,247.5261681551999,{"$nulls":4},247.5261681551999,1,{"$nulls":4},0.25,61.88154203879998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","27","LN40227041","1.03.02.04.02","CBBLN40227","9242589","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-03-15","2007-03-15",null,"C","SL_MSEG1","$$",null,100,null,107.5248,107.5248,null,null,100,null,107.5248,107.5248,{"$nulls":4},107.5248,1,{"$nulls":4},0.2,21.50496,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","28","LN40228015","1.03.02.04.02","CBBLN40228","9242589","RCV: Power Supply","2007-03-15","2007-03-15",null,"C","SL_MSEG1","$$",null,21800,null,23440.4064,23440.4064,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","02","29","LN40229020","1.03.02.04.02","CBBLN40229","9242589","RCV: Transductors","2007-03-15","2007-03-15",null,"C","SL_MSEG1","$$",null,1320,null,1419.32736,1419.32736,null,null,1320,null,1419.32736,1419.32736,{"$nulls":4},1419.32736,1,{"$nulls":4},0.2,283.865472,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","29","LN40229041","1.03.02.04.02","CBBLN40229","9242589","RCV:  Circt brkr, 3-pole, 30 A, 480V, Series Trp","2007-03-15","2007-03-15",null,"C","SL_MSEG1","$$",null,100,null,107.5248,107.5248,null,null,100,null,107.5248,107.5248,{"$nulls":4},107.5248,1,{"$nulls":4},0.2,21.50496,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","30","LN40230060","1.03.02.04.02","CBBLN40230","9242589","Integrate cables","2007-03-16","2007-03-16",null,"C","SL_TMUE1","Hrs",8,null,768.170304,null,768.170304,null,8,null,768.170304,null,768.170304,{"$nulls":4},768.170304,1,{"$nulls":4},0.25,192.042576,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","31","LN40231020","1.03.02.04.02","CBBLN40231","9242589","RCV: Transductors","2007-03-15","2007-03-15",null,"C","SL_MSEG1","$$",null,1320,null,1419.32736,1419.32736,null,null,1320,null,1419.32736,1419.32736,{"$nulls":4},1419.32736,1,{"$nulls":4},0.2,283.865472,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","32","LN40232030","1.03.02.04.02","CBBLN40232","9242589","RCV: PS Controller","2007-03-15","2007-03-15",null,"C","SL_MSEG1","$$",null,2000,null,2150.496,2150.496,null,null,2000,null,2150.496,2150.496,{"$nulls":4},2150.496,1,{"$nulls":4},0.25,537.624,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","32","LN40232060","1.03.02.04.02","CBBLN40232","9242589","Integrate cables","2007-03-16","2007-03-16",null,"C","SL_TMUE1","Hrs",8,null,768.170304,null,768.170304,null,8,null,768.170304,null,768.170304,{"$nulls":4},768.170304,1,{"$nulls":4},0.25,192.042576,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","34",{"$nulls":4},"Power Supply QDMP1-2                                        ",{"$nulls":6},24,15260,1978.6611407903997,16408.28448,18386.945620790397,null,24,15260,1978.6611407903997,16408.28448,18386.945620790397,0,null,0,null,18386.945620790397,null,0,null,0,null,null,3883.8469811976]
["1","03","02","04","02","34","LN40234050","1.03.02.04.02","CBBLN40234","9242589","Bench test PS Controller","2007-03-16","2007-03-16",null,"C","SL_PCT1","Hrs",4,null,247.5261681551999,null,247.5261681551999,null,4,null,247.5261681551999,null,247.5261681551999,{"$nulls":4},247.5261681551999,1,{"$nulls":4},0.25,61.88154203879998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","35","LN40235055","1.03.02.04.02","CBBLN40235","9242589","Pre-install Qual Test","2007-03-20","2007-03-22",null,"C","SL_PCE1","Hrs",4,null,452.1260262816,null,452.1260262816,null,4,null,452.1260262816,null,452.1260262816,{"$nulls":4},452.1260262816,1,{"$nulls":4},0.25,113.0315065704,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","02","36",{"$nulls":4},"Power Supply QUE2                                           ",{"$nulls":6},24,15260,1978.6611407903997,16408.28448,18386.945620790397,null,24,15260,1978.6611407903997,16408.28448,18386.945620790397,0,null,0,null,18386.945620790397,null,0,null,0,null,null,3883.8469811976]
["1","03","02","04","02","37","LN40237035","1.03.02.04.02","CBBLN40237","9242589","RCV: Circuit Breaker, 100A 480V, 3-pole,25kAIC","2006-10-16","2006-10-16",null,"C","SL_MSEG1","$$",null,640,null,688.15872,688.15872,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","02","38",{"$nulls":4},"Rack Accessories - LI24                                     ",{"$nulls":6},3,640,180.94018139999997,670.72,851.6601814,null,3,640,180.94018139999997,670.72,851.6601814,0,null,851.6601814,null,0,null,0,null,0,null,null,179.37904535]
["1","03","02","04","02","41","LN40241015","1.03.02.04.02","CBBLN40241","9242589","RCV: Circuit Breaker, 100A 480V, 3-pole,25kAIC","2006-09-13","2006-09-13",null,"C","SL_MSEG1","$$",null,640,null,670.72,670.72,null,null,640,null,670.72,670.72,null,null,670.72,1,{"$nulls":6},0.2,134.144,1.1,1.1,1,3,"2G","K. Luchini"]
["1","03","02","04","03","01","LN40301035","1.03.02.04.03","CBBLN40301","9242590","RCV: 12Amp Pwr & Prog Modules - QA11","2006-08-02","2006-08-02",null,"C","SL_MSEG1","$$",null,1925,null,2017.4,2017.4,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","01","LN40301105","1.03.02.04.03","CBBLN40301","9242590","RCV:  ADC,DAC,DI cables and conectors","2006-08-02","2006-08-02",null,"C","SL_MSEG1","$$",null,300,null,314.4,314.4,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","02","LN40302020","1.03.02.04.03","CBBLN40302","9242590","RCV: MCOR Blower","2006-08-02","2006-08-02",null,"C","SL_MSEG1","$$",null,500,null,524,524,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","02","LN40302085","1.03.02.04.03","CBBLN40302","9242590","RCV:  DI Module - 16 Chan","2006-08-02","2006-08-02",null,"C","SL_MSEG1","$$",null,1000,null,1048,1048,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","02","LN40302105","1.03.02.04.03","CBBLN40302","9242590","RCV:  ADC,DAC,DI cables and conectors","2006-08-02","2006-08-02",null,"C","SL_MSEG1","$$",null,300,null,314.4,314.4,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","03","LN40303065","1.03.02.04.03","CBBLN40303","9242590","RCV: 12Amp Pwr & Prog Modules - CQ12","2006-08-02","2006-08-02",null,"C","SL_MSEG1","$$",null,1925,null,2017.4,2017.4,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","03","LN40303085","1.03.02.04.03","CBBLN40303","9242590","RCV:  DI Module - 16 Chan","2006-08-02","2006-08-02",null,"C","SL_MSEG1","$$",null,1000,null,1048,1048,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","04","LN40304050","1.03.02.04.03","CBBLN40304","9242590","RCV: 12Amp Pwr & Prog Modules - XCM11","2006-08-02","2006-08-02",null,"C","SL_MSEG1","$$",null,1925,null,2017.4,2017.4,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","04","LN40304065","1.03.02.04.03","CBBLN40304","9242590","RCV: 12Amp Pwr & Prog Modules - YCM11","2006-08-02","2006-08-02",null,"C","SL_MSEG1","$$",null,1925,null,2017.4,2017.4,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","05","LN40305015","1.03.02.04.03","CBBLN40305","9242590","RCV: MCOR Chassis","2007-03-07","2007-03-07",null,"C","SL_MSEG1","$$",null,2850,null,3064.4568,3064.4568,null,null,2850,null,3064.4568,3064.4568,{"$nulls":4},3064.4568,1,{"$nulls":4},0.2,612.89136,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","05","LN40305047","1.03.02.04.03","CBBLN40305","9242590","RCV: 12Amp Pwr & Prog Modules - CQ21","2007-03-07","2007-03-07",null,"C","SL_MSEG1","$$",null,1925,null,2069.8523999999998,2069.8523999999998,null,null,1925,null,2069.8523999999998,2069.8523999999998,{"$nulls":4},2069.8523999999998,1,{"$nulls":4},0.2,413.97047999999995,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","05","LN40305122","1.03.02.04.03","CBBLN40305","9242590","Pre-install Qual Test","2007-05-03","2007-05-09",null,"C","SL_PCE1","Hrs",4,null,452.1260262816,null,452.1260262816,null,4,null,452.1260262816,null,452.1260262816,{"$nulls":4},452.1260262816,1,{"$nulls":4},0.25,113.0315065704,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","06","LN40306015","1.03.02.04.03","CBBLN40306","9242590","RCV: MCOR Chassis","2007-03-07","2007-03-07",null,"C","SL_MSEG1","$$",null,2850,null,3064.4568,3064.4568,null,null,2850,null,3064.4568,3064.4568,{"$nulls":4},3064.4568,1,{"$nulls":4},0.2,612.89136,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","06","LN40306112","1.03.02.04.03","CBBLN40306","9242590","Pre-install Qual Test","2007-05-03","2007-05-09",null,"C","SL_PCCA1","Hrs",4,null,263.31247419839997,null,263.31247419839997,null,4,null,263.31247419839997,null,263.31247419839997,{"$nulls":4},263.31247419839997,1,{"$nulls":4},0.25,65.82811854959999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","07","LN40307020","1.03.02.04.03","CBBLN40307","9242590","RCV: MCOR Blower","2007-03-07","2007-03-07",null,"C","SL_MSEG1","$$",null,500,null,537.624,537.624,null,null,500,null,537.624,537.624,{"$nulls":4},537.624,1,{"$nulls":4},0.2,107.52480000000001,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","07","LN40307117","1.03.02.04.03","CBBLN40307","9242590","Pre-install Qual Test","2007-05-03","2007-05-09",null,"C","SL_PCE1","Hrs",4,null,452.1260262816,null,452.1260262816,null,4,null,452.1260262816,null,452.1260262816,{"$nulls":4},452.1260262816,1,{"$nulls":4},0.25,113.0315065704,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","08","LN40308015","1.03.02.04.03","CBBLN40308","9242590","RCV: MCOR Chassis","2007-03-07","2007-03-07",null,"C","SL_MSEG1","$$",null,2850,null,3064.4568,3064.4568,null,null,2850,null,3064.4568,3064.4568,{"$nulls":4},3064.4568,1,{"$nulls":4},0.2,612.89136,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","08","LN40308085","1.03.02.04.03","CBBLN40308","9242590","RCV:  IP Carrier Board","2007-03-07","2007-03-07",null,"C","SL_MSEG1","$$",null,800,null,860.1984,860.1984,null,null,800,null,860.1984,860.1984,{"$nulls":4},860.1984,1,{"$nulls":4},0.2,172.03968,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","09",{"$nulls":4},"MCOR_LTU2                                                   ",{"$nulls":6},28,20950,2635.8642604799998,22526.445600000003,25162.30986048,null,28,20950,2635.8642604799998,22526.445600000003,25162.30986048,0,null,0,null,25162.30986048,null,0,null,0,null,null,5164.255185119999]
["1","03","02","04","03","09","LN40309080","1.03.02.04.03","CBBLN40309","9242590","RCV:  IP Carrier Board","2007-03-07","2007-03-07",null,"C","SL_MSEG1","$$",null,800,null,860.1984,860.1984,null,null,800,null,860.1984,860.1984,{"$nulls":4},860.1984,1,{"$nulls":4},0.2,172.03968,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","10",{"$nulls":4},"MCOR_LTU3                                                   ",{"$nulls":6},28,19025,2635.8642604799998,20456.593200000003,23092.45746048,null,28,19025,2635.8642604799998,20456.593200000003,23092.45746048,0,null,0,null,23092.45746048,null,0,null,0,null,null,4750.28470512]
["1","03","02","04","03","10","LN40310085","1.03.02.04.03","CBBLN40310","9242590","RCV:  IO Accessories","2007-03-07","2007-03-07",null,"C","SL_MSEG1","$$",null,300,null,322.57439999999997,322.57439999999997,null,null,300,null,322.57439999999997,322.57439999999997,{"$nulls":4},322.57439999999997,1,{"$nulls":4},0.2,64.51487999999999,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","10","LN40310115","1.03.02.04.03","CBBLN40310","9242590","MCOR Bench Test and Assembly","2007-04-05","2007-05-02",null,"C","SL_TMUE1","Hrs",8,null,768.170304,null,768.170304,null,8,null,768.170304,null,768.170304,{"$nulls":4},768.170304,1,{"$nulls":4},0.25,192.042576,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","11","LN40311080","1.03.02.04.03","CBBLN40311","9242590","RCV:  IP Carrier Board","2007-03-07","2007-03-07",null,"C","SL_MSEG1","$$",null,800,null,860.1984,860.1984,null,null,800,null,860.1984,860.1984,{"$nulls":4},860.1984,1,{"$nulls":4},0.2,172.03968,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","11","LN40311110","1.03.02.04.03","CBBLN40311","9242590","Integrate Cables","2007-03-08","2007-04-04",null,"C","SL_TMUE1","Hrs",12,null,1152.2554559999999,null,1152.2554559999999,null,12,null,1152.2554559999999,null,1152.2554559999999,{"$nulls":4},1152.2554559999999,1,{"$nulls":4},0.25,288.06386399999997,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","12","LN40312050","1.03.02.04.03","CBBLN40312","9242590","RCV: 12Amp Pwr  & Prog Modules - YCDL3","2007-03-07","2007-03-07",null,"C","SL_MSEG1","$$",null,1925,null,2069.8523999999998,2069.8523999999998,null,null,1925,null,2069.8523999999998,2069.8523999999998,{"$nulls":4},2069.8523999999998,1,{"$nulls":4},0.2,413.97047999999995,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","12","LN40312100","1.03.02.04.03","CBBLN40312","9242590","RCV:  ADC,DAC,DI cables and conectors","2007-03-07","2007-03-07",null,"C","SL_MSEG1","$$",null,300,null,322.57439999999997,322.57439999999997,null,null,300,null,322.57439999999997,322.57439999999997,{"$nulls":4},322.57439999999997,1,{"$nulls":4},0.2,64.51487999999999,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","13","LN40313045","1.03.02.04.03","CBBLN40313","9242590","RCV: 12Amp Pwr & Prog Modules - YCQT42","2007-03-07","2007-03-07",null,"C","SL_MSEG1","$$",null,1925,null,2069.8523999999998,2069.8523999999998,null,null,1925,null,2069.8523999999998,2069.8523999999998,{"$nulls":4},2069.8523999999998,1,{"$nulls":4},0.2,413.97047999999995,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","13","LN40313090","1.03.02.04.03","CBBLN40313","9242590","RCV:  IO Accessories","2007-03-07","2007-03-07",null,"C","SL_MSEG1","$$",null,300,null,322.57439999999997,322.57439999999997,null,null,300,null,322.57439999999997,322.57439999999997,{"$nulls":4},322.57439999999997,1,{"$nulls":4},0.2,64.51487999999999,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","13","LN40313122","1.03.02.04.03","CBBLN40313","9242590","Pre-install Qual Test","2007-05-03","2007-05-09",null,"C","SL_PCCA1","Hrs",4,null,263.31247419839997,null,263.31247419839997,null,4,null,263.31247419839997,null,263.31247419839997,{"$nulls":4},263.31247419839997,1,{"$nulls":4},0.25,65.82811854959999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","14","LN40314050","1.03.02.04.03","CBBLN40314","9242590","RCV: 12Amp Pwr & Prog Modules - XCE31","2007-03-07","2007-03-07",null,"C","SL_MSEG1","$$",null,1925,null,2069.8523999999998,2069.8523999999998,null,null,1925,null,2069.8523999999998,2069.8523999999998,{"$nulls":4},2069.8523999999998,1,{"$nulls":4},0.2,413.97047999999995,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","15","LN40315030","1.03.02.04.03","CBBLN40315","9242590","RCV: MCOR Controller Module","2007-03-07","2007-03-07",null,"C","SL_MSEG1","$$",null,800,null,860.1984,860.1984,null,null,800,null,860.1984,860.1984,{"$nulls":4},860.1984,1,{"$nulls":4},0.2,172.03968,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","15","LN40315045","1.03.02.04.03","CBBLN40315","9242590","RCV: 12Amp Pwr & Prog Modules - XCE35","2007-03-07","2007-03-07",null,"C","SL_MSEG1","$$",null,1925,null,2069.8523999999998,2069.8523999999998,null,null,1925,null,2069.8523999999998,2069.8523999999998,{"$nulls":4},2069.8523999999998,1,{"$nulls":4},0.2,413.97047999999995,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","15","LN40315122","1.03.02.04.03","CBBLN40315","9242590","Pre-install Qual Test","2007-05-03","2007-05-09",null,"C","SL_PCCA1","Hrs",4,null,263.31247419839997,null,263.31247419839997,null,4,null,263.31247419839997,null,263.31247419839997,{"$nulls":4},263.31247419839997,1,{"$nulls":4},0.25,65.82811854959999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","16","LN40316040","1.03.02.04.03","CBBLN40316","9242590","RCV: 12Amp Pwr  & Prog Modules - YCUM3","2007-03-07","2007-03-07",null,"C","SL_MSEG1","$$",null,1925,null,2069.8523999999998,2069.8523999999998,null,null,1925,null,2069.8523999999998,2069.8523999999998,{"$nulls":4},2069.8523999999998,1,{"$nulls":4},0.2,413.97047999999995,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","17",{"$nulls":4},"MCOR_DUMP1                                                  ",{"$nulls":6},28,24800,2635.8642604799998,26666.150400000002,29302.01466048,null,28,24800,2635.8642604799998,26666.150400000002,29302.01466048,0,null,0,null,29302.01466048,null,0,null,0,null,null,5992.196145119999]
["1","03","02","04","03","17","LN40317040","1.03.02.04.03","CBBLN40317","9242590","RCV: 12Amp Pwr & Prog Modules -  XCD3","2007-03-07","2007-03-07",null,"C","SL_MSEG1","$$",null,1925,null,2069.8523999999998,2069.8523999999998,null,null,1925,null,2069.8523999999998,2069.8523999999998,{"$nulls":4},2069.8523999999998,1,{"$nulls":4},0.2,413.97047999999995,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","17","LN40317117","1.03.02.04.03","CBBLN40317","9242590","Pre-install Qual Test","2007-05-03","2007-05-09",null,"C","SL_PCE1","Hrs",4,null,452.1260262816,null,452.1260262816,null,4,null,452.1260262816,null,452.1260262816,{"$nulls":4},452.1260262816,1,{"$nulls":4},0.25,113.0315065704,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","18","LN40318010","1.03.02.04.03","CBBLN40318","9242590","RCV: MCOR Bulk PS - 10kw","2006-10-30","2006-10-30",null,"C","SL_MSEG1","$$",null,8000,null,8601.984,8601.984,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","22","LN40322010","1.03.02.04.03","CBBLN40322","9242590","RCV: MCOR Bulk PS - 10kw","2006-10-30","2006-10-30",null,"C","SL_MSEG1","$$",null,8000,null,8601.984,8601.984,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","23",{"$nulls":4},"MCOR Bulk PS - LTU_1                                        ",{"$nulls":6},4,8100,247.5261681551999,8709.5088,8957.0349681552,null,4,100,247.5261681551999,107.5248,355.05096815519994,0,null,0,null,355.05096815519994,null,0,null,0,null,null,83.38650203879997]
["1","03","02","04","03","24","LN40324015","1.03.02.04.03","CBBLN40324","9242590","Bench test and safety inspection","2006-10-31","2006-11-06",null,"C","SL_PCT1","Hrs",4,null,247.5261681551999,null,247.5261681551999,null,4,null,247.5261681551999,null,247.5261681551999,{"$nulls":4},247.5261681551999,1,{"$nulls":4},0.25,61.88154203879998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","27","LN40327035","1.03.02.04.03","CBBLN40327","9242590","RCV:  PLC Control Interface Module","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,3450,null,3615.6,3615.6,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","27","LN40327105","1.03.02.04.03","CBBLN40327","9242590","Documentation","2006-08-30","2007-03-14",null,"C","SL_PCE1","Hrs",16,null,1801.0217314567838,null,1801.0217314567838,null,16,null,1801.0217314567838,null,1801.0217314567838,null,null,294.0443643194749,0.16,1506.9773671373089,0.84,{"$nulls":4},0.1,180.1021731456784,1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","28","LN40328045","1.03.02.04.03","CBBLN40328","9242590","RCV:  Analog to Digital Converter Modules 12-ch","2007-04-02","2007-04-02",null,"C","SL_MSEG1","$$",null,2673,null,2874.137904,2874.137904,null,null,2673,null,2874.137904,2874.137904,{"$nulls":4},2874.137904,1,{"$nulls":4},0.2,574.8275808000001,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","28","LN40328095","1.03.02.04.03","CBBLN40328","9242590","Debug Ladder logic and displays","2007-05-01","2007-05-07",null,"C","SL_PCE1","Hrs",40,null,4521.260262816,null,4521.260262816,null,40,null,4521.260262816,null,4521.260262816,{"$nulls":4},4521.260262816,1,{"$nulls":4},0.35,1582.4410919856,1.25,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","28","LN40328110","1.03.02.04.03","CBBLN40328","9242590","Bench-test and assembly","2007-07-05","2007-07-11",null,"C","SL_PCT1","Hrs",4,null,247.5261681551999,null,247.5261681551999,null,4,null,247.5261681551999,null,247.5261681551999,{"$nulls":4},247.5261681551999,1,{"$nulls":4},0.25,61.88154203879998,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","29","LN40329090","1.03.02.04.03","CBBLN40329","9242590","Develop Touch Panel Displays","2007-04-03","2007-04-30",null,"C","SL_PCE1","Hrs",16,null,1808.5041051264,null,1808.5041051264,null,16,null,1808.5041051264,null,1808.5041051264,{"$nulls":4},1808.5041051264,1,{"$nulls":4},0.35,632.9764367942399,1.25,1.1,4,3,"2G","K. Luchini"]
["1","03","02","04","03","29","LN40329105","1.03.02.04.03","CBBLN40329","9242590","Documentation","2007-04-03","2007-09-27",null,"C","SL_PCE1","Hrs",16,null,1808.5041051264,null,1808.5041051264,null,16,null,1808.5041051264,null,1808.5041051264,{"$nulls":4},1808.5041051264,1,{"$nulls":4},0.2,361.70082102528,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","30","LN40330020","1.03.02.04.03","CBBLN40330","9242590","RCV:  PLC Chassis Accessories","2007-04-02","2007-04-02",null,"C","SL_MSEG1","$$",null,150,null,161.28719999999998,161.28719999999998,null,null,150,null,161.28719999999998,161.28719999999998,{"$nulls":4},161.28719999999998,1,{"$nulls":4},0.2,32.257439999999995,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","30","LN40330100","1.03.02.04.03","CBBLN40330","9242590","Integrate Cables","2007-05-08","2007-07-03",null,"C","SL_TMUE1","Hrs",12,null,1152.2554559999999,null,1152.2554559999999,null,12,null,1152.2554559999999,null,1152.2554559999999,{"$nulls":4},1152.2554559999999,1,{"$nulls":4},0.2,230.45109119999998,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","31","LN40331050","1.03.02.04.03","CBBLN40331","9242590","RCV:  Digital to Analog Converter Modules 6-ch","2007-04-02","2007-04-02",null,"C","SL_MSEG1","$$",null,2146,null,2307.482208,2307.482208,null,null,2146,null,2307.482208,2307.482208,{"$nulls":4},2307.482208,1,{"$nulls":4},0.2,461.4964416,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","31","LN40331095","1.03.02.04.03","CBBLN40331","9242590","Debug Ladder logic and displays","2007-05-01","2007-05-07",null,"C","SL_PCE1","Hrs",40,null,4521.260262816,null,4521.260262816,null,40,null,4521.260262816,null,4521.260262816,{"$nulls":4},4521.260262816,1,{"$nulls":4},0.35,1582.4410919856,1.25,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","32","LN40332045","1.03.02.04.03","CBBLN40332","9242590","RCV:  Analog to Digital Converter Modules 12-ch","2007-04-02","2007-04-02",null,"C","SL_MSEG1","$$",null,2673,null,2874.137904,2874.137904,null,null,2673,null,2874.137904,2874.137904,{"$nulls":4},2874.137904,1,{"$nulls":4},0.2,574.8275808000001,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","32","LN40332090","1.03.02.04.03","CBBLN40332","9242590","Develop Touch Panel Displays","2007-04-03","2007-04-30",null,"C","SL_PCE1","Hrs",16,null,1808.5041051264,null,1808.5041051264,null,16,null,1808.5041051264,null,1808.5041051264,{"$nulls":4},1808.5041051264,1,{"$nulls":4},0.35,632.9764367942399,1.25,1.1,4,3,"2G","K. Luchini"]
["1","03","02","04","03","33","LN40333035","1.03.02.04.03","CBBLN40333","9242590","RCV:  PLC EtherNet/IP Module","2007-04-02","2007-04-02",null,"C","SL_MSEG1","$$",null,1209,null,1299.9748319999999,1299.9748319999999,null,null,1209,null,1299.9748319999999,1299.9748319999999,{"$nulls":4},1299.9748319999999,1,{"$nulls":4},0.2,259.9949664,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","33","LN40333050","1.03.02.04.03","CBBLN40333","9242590","RCV:  Digital Input Modules +24V (32-chan)","2007-04-02","2007-04-02",null,"C","SL_MSEG1","$$",null,292,null,313.972416,313.972416,null,null,292,null,313.972416,313.972416,{"$nulls":4},313.972416,1,{"$nulls":4},0.2,62.7944832,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","33","LN40333095","1.03.02.04.03","CBBLN40333","9242590","Integrate Cables","2007-05-08","2007-07-03",null,"C","SL_TMUE1","Hrs",12,null,1152.2554559999999,null,1152.2554559999999,null,12,null,1152.2554559999999,null,1152.2554559999999,{"$nulls":4},1152.2554559999999,1,{"$nulls":4},0.2,230.45109119999998,1.1,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","34","LN40334045","1.03.02.04.03","CBBLN40334","9242590","RCV:  Digital to Analog Converter Modules 6-ch","2007-04-02","2007-04-02",null,"C","SL_MSEG1","$$",null,2146,null,2307.482208,2307.482208,null,null,2146,null,2307.482208,2307.482208,{"$nulls":4},2307.482208,1,{"$nulls":4},0.2,461.4964416,1.1,1.1,2,3,"2G","K. Luchini"]
["1","03","02","04","03","34","LN40334107","1.03.02.04.03","CBBLN40334","9242590","Pre-install Qual Test","2007-07-12","2007-07-18",null,"C","SL_PCCA1","Hrs",4,null,263.31247419839997,null,263.31247419839997,null,4,null,263.31247419839997,null,263.31247419839997,{"$nulls":4},263.31247419839997,1,{"$nulls":4},0.25,65.82811854959999,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","03","36","LN40336020","1.03.02.04.03","CBBLN40336","9242590","Assemble and test","2007-03-19","2007-03-19",null,"C","SL_PCT1","Hrs",1,null,61.88154203879998,null,61.88154203879998,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","K. Luchini"]
["1","03","02","04","04","","LN20404015","1.03.02.04.04","CBA3020404","9242227","Integrate Hardware and Software","2006-12-13","2007-01-10",null,"C","SL_CE1","Hrs",37,null,4182.1657431048,null,4182.1657431048,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,3,"2G","M. Ortega"]
["1","03","02","04","04","","LN20404125","1.03.02.04.04","CBB3020404","9242227","Intall & Integrate L1-BC1 Cable Plant","2006-08-22","2006-12-14",null,"C","SL_CCA1","Hrs",187,null,12200.403528924251,null,12200.403528924251,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,3,"2G","M. Ortega"]
["1","03","02","04","04","","LN20404310","1.03.02.04.04","CBD3020404","9242227","Prep L2-BC2 Cable Plant Bid Package","2006-11-13","2006-11-17",null,"C","SL_PCE1","Hrs",32,null,3617.0082102528,null,3617.0082102528,null,32,null,3617.0082102528,null,3617.0082102528,{"$nulls":4},3617.0082102528,1,{"$nulls":4},0.25,904.2520525632,1.15,1.1,3,3,"2G","M. Ortega"]
["1","03","02","04","04","","LN20404325","1.03.02.04.04","CBD3020404","9242227","Intall & Integrate L2-BC2 Cable Plant","2007-03-06","2007-06-26",null,"C","SL_CT","Hrs",28,null,1819.2723107632921,null,1819.2723107632921,null,28,null,1819.2723107632921,null,1819.2723107632921,{"$nulls":4},1819.2723107632921,1,{"$nulls":4},0.25,454.81807769082303,1.15,1.1,4,3,"2G","M. Ortega"]
["1","03","02","04","04","","LN20404425","1.03.02.04.04","CBE3020404","9242227","Intall & Integrate L2-BC2 Racks","2007-03-13","2007-07-03",null,"C","SL_CT1","Hrs",28,null,1732.6831770863994,null,1732.6831770863994,null,28,null,1732.6831770863994,null,1732.6831770863994,{"$nulls":4},1732.6831770863994,1,{"$nulls":4},0.25,433.17079427159985,1.15,1.1,4,3,"2G","M. Ortega"]
["1","03","02","04","04","","LN20404612","1.03.02.04.04","CBG3020404","9242227","AWARD: LTU Racks Contract","2007-05-21","2007-05-21",null,"C","SL_AW1","$$",null,89000,null,95697.072,95697.072,null,null,89000,null,95697.072,95697.072,{"$nulls":4},95697.072,1,{"$nulls":9},3,"2G","M. Ortega"]
["1","03","02","04","04","","LN20404825","1.03.02.04.04","CBI3020404","9242227","Intall & Integrate Undulator Racks","2007-08-16","2007-12-10",null,"C","SL_CCA1","Hrs",140,null,9360.531464240878,null,9360.531464240878,null,140,null,9360.531464240878,null,9360.531464240878,{"$nulls":4},3711.9348909920723,0.4,5648.596573248805,0.6,null,null,0.25,2340.1328660602194,1.15,1.1,4,3,"2G","M. Ortega"]
["1","03","02","05","01","","LN20501045","1.03.02.05","CBDLN30205","9242228","Integrate & Test: Solid State Sub-Booster 5x","2007-10-08","2007-11-02","S","C","SL_KT1","Hrs",160,null,10158.473941089405,null,10158.473941089405,null,160,null,10158.473941089405,null,10158.473941089405,{"$nulls":6},10158.473941089405,1,null,null,0.25,2539.6184852723513,1.15,1.1,6,3,"2G","R. Akre"]
["1","03","02","05","04","","LN20504005","1.03.02.05","CBGLN30205","9242228","Design: Beam Phase Measurement 2x","2007-06-01","2007-07-13","S","C","SL_KE1","Hrs",100,null,11303.15065704,null,11303.15065704,null,100,null,11303.15065704,null,11303.15065704,{"$nulls":4},11303.15065704,1,{"$nulls":4},0.25,2825.78766426,1.15,1.1,3,3,"2G","R. Akre"]
["1","03","02","05","05","  ",{"$nulls":4},"Sector 24 Rack Electrical Crate / IOC / EVG                 ",{"$nulls":6},320,70000,29121.494121287567,75267.36,104388.85412128754,null,320,70000,29121.494121287567,75267.36,104388.85412128754,0,null,0,null,99972.1675513198,null,4416.686569967759,null,0,null,null,26097.213530321886]
["1","03","02","05","06","","LN20506035","1.03.02.05","CBILN30205","9242228","Integrate & Test Sector 24 T-Cav Hardware","2007-07-26","2007-08-08","S","C","SL_KT1","Hrs",40,null,2475.261681551999,null,2475.261681551999,null,40,null,2475.261681551999,null,2475.261681551999,{"$nulls":4},2475.261681551999,1,{"$nulls":4},0.25,618.8154203879998,1.15,1.1,3,3,"2G","R. Akre"]
["1","03","02","05","07","","LN20507020","1.03.02.05","CBJLN30205","9242228","RCV: Sector 29/30 Control (Packs & Pads) H/W","2007-07-11","2007-07-11","S","C","SL_MSEG1","$$",null,10000,null,10752.48,10752.48,null,null,10000,null,10752.48,10752.48,{"$nulls":4},10752.48,1,{"$nulls":4},0.25,2688.12,1.15,1.1,2,3,"2G","R. Akre"]
["1","03","02","05","10","","LN20510020","1.03.02.05","CBMLN30205","9242228","Software Development: RF Stability / Feedback","2007-09-04","2008-07-17","S","C","SL_CP1","Hrs",520,null,43873.291599194396,null,43873.291599194396,null,520,null,43873.291599194396,null,43873.291599194396,{"$nulls":4},3736.841871224759,0.09,40136.44972796964,0.91,null,null,0.25,10968.322899798599,1.15,1.1,3,3,"2G","R. Akre"]
["1","03","02","06","01","","LN601_0245","1.03.02.06.01","CBCLN20601","9242591","RCV: 2 LVDTs","2007-03-02","2007-03-02",null,"C","SL_MSEG1","$$",null,8080,null,8688.00384,8688.00384,null,null,8080,null,8688.00384,8688.00384,{"$nulls":4},8688.00384,1,{"$nulls":4},0.2,1737.600768,1.1,1.1,2,3,"2G","D. Murray"]
["1","03","02","06","01","","LN601_0315","1.03.02.06.01","CBDLN20601","9242591","RCV: 5 PMTs","2007-09-25","2007-09-25",null,"C","SL_MSEG1","$$",null,4000,null,4300.992,4300.992,null,null,4000,null,4300.992,4300.992,{"$nulls":4},4300.992,1,{"$nulls":4},0.2,860.1984000000001,1.1,1.1,2,3,"2G","D. Murray"]
["1","03","02","06","02","","LN602_0125","1.03.02.06.02","CBBLN20602","9242592","RCV: 4 Echotek","2006-08-29","2006-08-29",null,"C","SL_MSEG1","$$",null,9365,null,9814.52,9814.52,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","S. Smith"]
["1","03","02","06","02","","LN602_0235","1.03.02.06.02","CBCLN20602","9242592","RCV: 9 EVRs","2007-03-30","2007-03-30",null,"C","SL_MSEG1","$$",null,17458,null,18771.679584,18771.679584,null,null,17458,null,18771.679584,18771.679584,{"$nulls":4},18771.679584,1,{"$nulls":4},0.25,4692.919896,1.15,1.1,3,3,"2G","S. Smith"]
["1","03","02","06","02","","LN602_0285","1.03.02.06.02","CBCLN20602","9242592","L02-L03 ntegration and Test","2007-08-31","2007-11-30",null,"C","SL_CE1","Hrs",274,null,31501.55793400885,null,31501.55793400885,null,274,null,31501.55793400885,null,31501.55793400885,{"$nulls":4},10731.299955541477,0.34,20770.257978467373,0.66,null,null,0.25,7875.389483502213,1.15,1.1,4,3,"2G","S. Smith"]
["1","03","02","06","03","  ",{"$nulls":4},"Controls - Toroids                                          ",{"$nulls":6},432,51400,37970.654172105606,55267.7472,93238.4013721056,null,288,51400,25313.7694480704,55267.7472,80581.5166480704,0,null,0,null,80581.5166480704,null,0,null,0,null,null,20145.3791620176]
["1","03","02","06","03","","LN603_0155","1.03.02.06.03","CBBLN20603","9242593","L01-BC1 Hardware Fab","2006-11-02","2006-12-01",null,"C","SL_CT1","Hrs",16,null,990.1046726207996,null,990.1046726207996,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,3,"2G","M. Cecere"]
["1","03","02","06","03","","LN603_0230","1.03.02.06.03","CBCLN20603","9242593","RCV: 1 Crate/CPU/PMC Spa n","2007-03-02","2007-03-02",null,"C","SL_MSEG1","$$",null,8000,null,8601.984,8601.984,null,null,8000,null,8601.984,8601.984,{"$nulls":4},8601.984,1,{"$nulls":4},0.25,2150.496,1.15,1.1,2,3,"2G","M. Cecere"]
["1","03","02","06","03","","LN603_0350","1.03.02.06.03","CBDLN20603","9242593","RCV: LTU Interrack Cables","2007-06-29","2007-06-29",null,"C","SL_MSEG1","$$",null,1000,null,1075.248,1075.248,null,null,1000,null,1075.248,1075.248,{"$nulls":4},1075.248,1,{"$nulls":4},0.25,268.812,1.15,1.1,4,3,"2G","M. Cecere"]
["1","03","02","06","04","","LN604_110","1.03.02.06.04","CBB20604","9242594","L01-BC1 Rack Layout and Wiring","2006-08-01","2006-08-28",null,"C","SL_CCA1","Hrs",16,null,1026.5593536,null,1026.5593536,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","P. Bong"]
["1","03","02","06","04","","LN604_240","1.03.02.06.04","CBC20604","9242594","RCV: L02-L03 Interrack Cables","2007-03-02","2007-03-02",null,"C","SL_MSEG1","$$",null,500,null,537.624,537.624,null,null,500,null,537.624,537.624,{"$nulls":4},537.624,1,{"$nulls":4},0.25,134.406,1.15,1.1,3,3,"2G","P. Bong"]
["1","03","02","06","05","  ",{"$nulls":4},"Controls - Profile Monitors                                 ",{"$nulls":6},342,143143,30123.520658345504,151796.67339199997,181920.19405034542,null,216,40859,19114.545310931502,43933.558032,63048.10334293151,0,null,0,null,59817.8091612168,null,3230.294181714705,null,0,null,null,13614.271718132877]
["1","03","02","06","05","","LN605_0160","1.03.02.06.05","CBBLN20605","9242595","RCV: 5 Motors","2006-08-18","2006-08-18",null,"C","SL_MSEG1","$$",null,5460,null,5722.08,5722.08,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,2,3,"2G","S. Peng"]
["1","03","02","06","05","","LN605_0240","1.03.02.06.05","CBCLN20605","9242595","RCV: 1 Smart Lens","2007-03-02","2007-03-02",null,"C","SL_MSEG1","$$",null,546,null,587.085408,587.085408,null,null,546,null,587.085408,587.085408,{"$nulls":4},587.085408,1,{"$nulls":4},0.2,117.41708160000002,1.1,1.1,2,3,"2G","S. Peng"]
["1","03","02","06","05","","LN605_0305","1.03.02.06.05","CBCLN20605","9242595","L02-L03 Hardware Fab","2007-04-04","2007-07-31",null,"C","SL_CT1","Hrs",9,null,556.9338783491999,null,556.9338783491999,null,9,null,556.9338783491999,null,556.9338783491999,{"$nulls":4},556.9338783491999,1,{"$nulls":4},0.25,139.23346958729996,1.15,1.1,3,3,"2G","S. Peng"]
["1","03","02","06","05","","LN605_0475","1.03.02.06.05","CBDLN20605","9242595","LTU Hardware Fab","2007-07-02","2007-09-28",null,"C","SL_CE1","Hrs",9,null,1017.2835591336,null,1017.2835591336,null,9,null,1017.2835591336,null,1017.2835591336,{"$nulls":4},1017.2835591336,1,{"$nulls":4},0.25,254.3208897834,1.15,1.1,3,3,"2G","S. Peng"]
["1","03","02","06","07","","LN607_115","1.03.02.06.07","CBB20607","9242597","L01-BC1 BLM Control Software","2006-09-19","2006-10-16",null,"C","SL_CP1","Hrs",40,null,3259.3335271200003,null,3259.3335271200003,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,3,"2G","S. Peng"]
["1","03","02","06","07","","LN607_155","1.03.02.06.07","CBB20607","9242597","L01-BC1 BLM Integration and Test","2006-10-17","2006-10-23",null,"C","SL_CT1","Hrs",40,null,2475.261681551999,null,2475.261681551999,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,3,"2G","S. Peng"]
["1","03","02","06","07","","LN607_250","1.03.02.06.07","CBC20607","9242597","L02-L03 BLM Integration and Test","2007-03-19","2007-03-23",null,"C","SL_CT1","Hrs",40,null,2475.261681551999,null,2475.261681551999,null,40,null,2475.261681551999,null,2475.261681551999,{"$nulls":4},2475.261681551999,1,{"$nulls":4},0.25,618.8154203879998,1.15,1.1,4,3,"2G","S. Peng"]
["1","03","02","06","09","","LN609_0155","1.03.02.06.09","CBBLN20609","9242599","L01-BC1 Integration and Test","2006-09-14","2006-09-20",null,"C","SL_CT1","Hrs",8,null,482.5071503999999,null,482.5071503999999,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","TBD"]
["1","03","02","06","09","","LN609_0245","1.03.02.06.09","CBCLN20609","9242599","L02-L03 Hardware Fab","2007-03-05","2007-03-16",null,"C","SL_CT1","Hrs",16,null,990.1046726207996,null,990.1046726207996,null,16,null,990.1046726207996,null,990.1046726207996,{"$nulls":4},990.1046726207996,1,{"$nulls":4},0.25,247.5261681551999,1.15,1.1,3,3,"2G","TBD"]
["1","03","02","06","10","","LN610_0110","1.03.02.06.10","CBBLN20610","9242600","L01-BC1 Rack Layout and Wiring","2006-08-01","2006-08-28",null,"C","SL_CE1","Hrs",16,null,1762.6745663999998,null,1762.6745663999998,null,11.2,null,1233.8721964799997,null,1233.8721964799997,null,null,1233.8721964799997,1,{"$nulls":6},0.25,308.46804911999993,1.15,1.1,3,3,"2G","TBD"]
["1","03","02","06","10","","LN610_0155","1.03.02.06.10","CBBLN20610","9242600","L01-BC1 Integration and Test","2006-09-14","2006-09-20",null,"C","SL_CT1","Hrs",8,null,482.5071503999999,null,482.5071503999999,null,8,null,482.5071503999999,null,482.5071503999999,null,null,482.5071503999999,1,{"$nulls":6},0.25,120.62678759999997,1.15,1.1,3,3,"2G","TBD"]
["1","03","02","06","10","","LN610_0205","1.03.02.06.10","CBCLN20610","9242600","L02-L03 Rack Layout and Wiring","2007-02-01","2007-03-01",null,"C","SL_CCA1","Hrs",16,null,1053.2498967935999,null,1053.2498967935999,null,16,null,1053.2498967935999,null,1053.2498967935999,{"$nulls":4},1053.2498967935999,1,{"$nulls":4},0.25,263.31247419839997,1.15,1.1,3,3,"2G","TBD"]
["1","03","02","06","10","","LN610_0325","1.03.02.06.10","CBDLN20610","9242600","LTU Hardware Fab","2007-07-02","2007-07-16",null,"C","SL_CE1","Hrs",16,null,1808.5041051264,null,1808.5041051264,null,16,null,1808.5041051264,null,1808.5041051264,{"$nulls":4},1808.5041051264,1,{"$nulls":4},0.25,452.1260262816,1.15,1.1,3,3,"2G","TBD"]
["1","03","02","06","11","","LN02061129","1.03.02.06.11","CB3020611","9242601","Movable Collimator Hardware","2006-10-25","2006-11-21",null,"C","SL_MSEG1","$$",null,19957,null,21458.724336,21458.724336,null,null,0,null,0,0,{"$nulls":10},0.15,0,1.1,1.05,4,3,"2G","D. Murray"]
["1","03","02","06","12","","LN612_0280","1.03.02.06.12","CBCLN20612","9242602","L02-L03 Hardware Fab","2007-05-29","2007-08-30",null,"C","SL_CE1","Hrs",15,null,1695.4725985559999,null,1695.4725985559999,null,15,null,1695.4725985559999,null,1695.4725985559999,{"$nulls":4},1695.4725985559999,1,{"$nulls":4},0.2,339.0945197112,1.1,1.1,4,3,"2G","D. Murray"]
["1","03","02","08","","","LN208_0115","1.03.02.08","CBCLN30208","9242604","RCV: 13 EVRs","2007-03-02","2007-03-02",null,"C","SL_MSEG1","$$",null,37700,null,40536.8496,40536.8496,null,null,37700,null,40536.8496,40536.8496,{"$nulls":4},40536.8496,1,{"$nulls":4},0.25,10134.2124,1.15,1.1,3,3,"2G","P. Krejcik"]
["1","03","02","09","01","","LN209_0105","1.03.02.09.01","CBB3020901","9242605","L01-BC1 Control Vacuum H/W in House FAB","2006-08-17","2006-09-14",null,"C","SL_CT1","Hrs",78,null,4704.4447163999985,null,4704.4447163999985,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,3,3,"2G","S. Schuh"]
["1","03","02","09","01","","LN209_0250","1.03.02.09.01","CBC3020901","9242605","L02-L03 Vacuum Integration and Test","2007-08-02","2007-11-30",null,"C","SL_CP1","Hrs",233,null,19451.507804470013,null,19451.507804470013,null,233,null,19451.507804470013,null,19451.507804470013,{"$nulls":4},9725.753902235007,0.5,9725.753902235007,0.5,null,null,0.25,4862.876951117503,1.15,1.1,3,3,"2G","S. Schuh"]
["1","03","02","09","01","","LN209_0305","1.03.02.09.01","CBD3020901","9242605","LTU Control Vacuum H/W in House FAB","2007-06-01","2008-01-02",null,"C","SL_CE1","Hrs",155,null,17716.921092121396,null,17716.921092121396,null,155,null,17716.921092121396,null,17716.921092121396,{"$nulls":4},10053.322666227024,0.57,7663.598425894371,0.43,null,null,0.25,4429.230273030349,1.15,1.1,3,3,"2G","S. Schuh"]
["1","03","02","09","01","","LN209_0350","1.03.02.09.01","CBD3020901","9242605","LTU Vacuum Integration and Test","2008-01-03","2008-03-03",null,"C","SL_CT1","Hrs",116,null,7364.893607289819,null,7364.893607289819,null,116,null,7364.893607289819,null,7364.893607289819,{"$nulls":6},7364.893607289819,1,null,null,0.25,1841.2234018224547,1.15,1.1,3,3,"2G","S. Schuh"]
["1","03","02","10","05","","LN02100550","1.03.02.10.05","CB3021005","9242230","Prep Bid Pak -VME Crates/Cntrl/Supt Chassis","2006-11-13","2006-11-17",null,"C","SL_CCA1","Hrs",16,null,1053.2498967935999,null,1053.2498967935999,null,16,null,1053.2498967935999,null,1053.2498967935999,{"$nulls":4},1053.2498967935999,1,{"$nulls":4},0.55,579.2874432364799,1.45,1.1,4,3,"2G","H. Shoaee"]
["1","03","03","  ","  ","  ",{"$nulls":4},"Linac Magnets & Supports                                    ",{"$nulls":6},5846,1201404,524431.2458207699,1252373.8271999997,1776805.0730207702,null,3380.3,1103435,304659.9016394674,1149594.0043999997,1454253.906039467,0,null,28197.45400069359,null,958935.6073876623,null,467120.84465111146,null,0,null,null,208028.2366070093]
["1","03","03","02","","","LN302-0600","1.03.03.02","CBZ30302","9242607","RCV: BX3 Supports","2006-08-01","2006-08-01",null,"C","SL_MSSY1","$$",null,28000,null,28000,28000,null,null,28000,null,28000,28000,null,null,28000,1,{"$nulls":6},0.2,5600,1.15,1.05,3,3,"2A"]
["1","03","03","03","","","LN303-0020","1.03.03.03","CBX30303","9242232","RCV: BX2_BC2 Magnets from Vendor","2007-02-16","2007-02-16",null,"C","SL_MSEG1","$$",null,97400,null,104729.1552,104729.1552,null,null,97400,null,104729.1552,104729.1552,{"$nulls":4},104729.1552,1,{"$nulls":4},0.05,5236.45776,1.05,1,7,3,"2A"]
["1","03","03","04","","","LN304-0560","1.03.03.04","CBZ30304","9242608","BYLTU Design Safety Covers","2007-03-30","2007-05-24","RC","C","SL_ME1","Hrs",8,null,798.9581689055999,null,798.9581689055999,null,6.4,null,639.16653512448,null,639.16653512448,{"$nulls":4},639.16653512448,1,{"$nulls":4},0.15,95.87498026867199,1.1,1.05,4,2,"2A"]
["1","03","03","05","","","LN305-0570","1.03.03.05","CBZ30305","9242609","Measure Everson Tesla Quad (req #121416, qty 14)","2007-01-17","2007-02-13","RC","C","SL_MES1","Hrs",80,null,6423.3934934399995,null,6423.3934934399995,null,80,null,6423.3934934399995,null,6423.3934934399995,{"$nulls":4},6423.3934934399995,1,{"$nulls":4},0.15,963.5090240159999,1.1,1.05,3,3,"2A"]
["1","03","03","07","","","LN307-0030","1.03.03.07","CBX30307","9242610","Magnetic Measure QE Magnets (qty 6)","2007-01-25","2007-03-22",null,"C","SL_MES1","Hrs",40,null,3211.6967467199997,null,3211.6967467199997,null,0,null,0,null,0,{"$nulls":10},0.15,0,1.1,1.05,3,3,"2A"]
["1","03","03","08","  ","  ",{"$nulls":4},"Corrector Magnet (Type 4_LTU/E-Dump)                        ",{"$nulls":6},760,0,70529.87930702399,0,70529.87930702399,null,558,0,51117.177250836,0,51117.177250836,0,null,0,null,51117.177250836,null,0,null,0,null,null,10223.4354501672]
["1","03","03","09","","","LN309-0100","1.03.03.09","CBX30309","9242612","BYD Design Magnet Support","2006-12-14","2007-03-13",null,"C","SL_ME1","Hrs",120,null,11984.372533583999,null,11984.372533583999,null,18,null,1797.6558800375997,null,1797.6558800375997,{"$nulls":4},1797.6558800375997,1,{"$nulls":4},0.15,269.6483820056399,1.1,1.05,3,2,"2A"]
["1","03","03","10","","","LN310-0020","1.03.03.10","CBX30310","9242613","Refurbish Quadrupoles 3.25Q20 (qty 4)","2007-01-08","2007-04-03",null,"C","SL_MES1","Hrs",40,null,3211.6967467199997,null,3211.6967467199997,null,0,null,0,null,0,{"$nulls":10},0.15,0,1.1,1.05,3,3,"2A"]
["1","03","03","11","","","LN311-0570","1.03.03.11","CBZ30311","9242614","BXPM Support Design","2007-06-04","2007-07-30","JL","C","SL_ME1","Hrs",160,null,15979.163378111998,null,15979.163378111998,null,112,null,11185.4143646784,null,11185.4143646784,{"$nulls":4},11185.4143646784,1,{"$nulls":4},0.15,1677.81215470176,1.1,1.05,4,2,"2A"]
["1","03","03","12","","","LN312-0550","1.03.03.12","CBZ30312","9242615","BYKIK Fabricate Kicker and Support","2007-06-08","2007-08-31","RC","C","SL_MFMS1","Hrs",60,null,6618.19248,null,6618.19248,null,60,null,6618.19248,null,6618.19248,{"$nulls":4},6618.19248,1,{"$nulls":4},0.15,992.7288719999999,1.1,1.05,4,3,"2A"]
["1","03","03","14","","","LN314-0030","1.03.03.14","CBX30314","9242935","BXKIK Wind Test Coil","2007-03-07","2007-04-03",null,"C","SL_MFAT1","Hrs",120,null,10342.08,null,10342.08,null,0,null,0,null,0,{"$nulls":10},0.15,0,1.1,1.05,4,3,"2A"]
["1","03","04","02","","","LN402-0040","1.03.04.02","CBX30402","9242617","RCV:  L2 Vacuum Drifts and Supports","2007-04-24","2007-04-24",null,"C","SL_MSEG1","$$",null,30000,null,32257.44,32257.44,null,null,24000,null,25805.952,25805.952,{"$nulls":4},25805.952,1,{"$nulls":4},0.2,5161.1904,1.1,1.1,4,3,"2A"]
["1","03","04","02","","","LN402-0110","1.03.04.02","CBX30402","9242617","L2/L3 Misc Girder Hardware","2007-05-22","2007-07-18",null,"C","SL_MSEG1","$$",null,5000,null,5376.24,5376.24,null,null,5000,null,5376.24,5376.24,{"$nulls":4},5376.24,1,{"$nulls":4},0.2,1075.248,1.1,1.1,4,3,"2A"]
["1","03","04","03","  ","  ",{"$nulls":4},"BC1 Vacuum System                                           ",{"$nulls":6},80,0,7253.558327999999,0,7253.558327999999,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","03","04","04","","","LN404-0120","1.03.04.04","CBX30404","9242618","Perform Pre-Installation Qual Test","2007-06-19","2007-07-17","S","C","SL_ME1","Hrs",120,null,11984.372533583999,null,11984.372533583999,null,120,null,11984.372533583999,null,11984.372533583999,{"$nulls":4},11984.372533583999,1,{"$nulls":4},0.3,3595.3117600752,1.2,1.1,4,3,"2A"]
["1","03","04","05","","","LN405-0510","1.03.04.05","CBZ30405","9242619","Design Drifts","2007-04-27","2007-07-23","TM","C","SL_ME1","Hrs",160,null,15979.163378111998,null,15979.163378111998,null,72,null,7190.623520150399,null,7190.623520150399,{"$nulls":4},7190.623520150399,1,{"$nulls":4},0.15,1078.5935280225597,1.1,1.05,4,2,"2A"]
["1","03","04","05","","","LN405-0600","1.03.04.05","CBZ30405","9242619","Vacuum Process Vacuum Hardware","2007-10-01","2007-11-27","TM","C","SL_MFAT1","Hrs",200,null,17684.9568,null,17684.9568,null,200,null,17684.9568,null,17684.9568,{"$nulls":6},17684.9568,1,null,null,0.15,2652.74352,1.1,1.05,4,3,"2A"]
["1","03","04","05","","","LN405-0630","1.03.04.05","CBZ30405","9242619","Design Dump Kicker Chamber Supports","2007-05-25","2007-08-20","JL","C","SL_MDD1","Hrs",120,null,10048.022679024,null,10048.022679024,null,120,null,10048.022679024,null,10048.022679024,{"$nulls":4},10048.022679024,1,{"$nulls":4},0.25,2512.005669756,1.15,1.1,4,2,"2A"]
["1","03","04","06","  ","  ",{"$nulls":4},"Dumpline Vacuum System                                      ",{"$nulls":6},3394,97654,315547.5619762522,105002.268192,420549.83016825217,null,2199.35,87654,207473.80994695213,94249.78819199999,301723.5981389521,0,null,0,null,280834.0193836402,null,20889.578755311857,null,0,null,null,57566.48947236597]
["1","03","04","06","","","LN406-0090","1.03.04.06","CBX30406","9242620","Purchase Dump Pump Supports","2007-06-28","2007-09-21",null,"C","SL_MSEG1","$$",null,10000,null,10752.48,10752.48,null,null,10000,null,10752.48,10752.48,{"$nulls":4},10752.48,1,{"$nulls":4},0.15,1612.8719999999998,1.1,1.05,4,3,"2A"]
["1","03","04","06","","","LN406-0130","1.03.04.06","CBX30406","9242620","Design Dump Chamber Supports","2007-05-02","2007-06-27",null,"C","SL_ME1","Hrs",80,null,7989.581689055999,null,7989.581689055999,null,44,null,4394.2699289808,null,4394.2699289808,{"$nulls":4},4394.2699289808,1,{"$nulls":4},0.25,1098.5674822452,1.15,1.1,4,2,"2A"]
["1","03","04","06","","","LN406-0140","1.03.04.06","CBX30406","9242620","Fabricate Dump Chamber","2007-05-02","2007-07-26",null,"C","SL_MFAT1","Hrs",120,null,10342.08,null,10342.08,null,120,null,10342.08,null,10342.08,{"$nulls":4},10342.08,1,{"$nulls":4},0.25,2585.52,1.15,1.1,4,3,"2A"]
["1","03","04","06","","","LN406-0300","1.03.04.06","CBX30406","9242620","Design Undulator OUT Assembly","2007-02-12","2007-04-09",null,"C","SL_MDD1","Hrs",6,null,502.4011339512,null,502.4011339512,null,5.7,null,477.28107725364003,null,477.28107725364003,{"$nulls":4},477.28107725364003,1,{"$nulls":9},2,"2A"]
["1","03","04","07","  ","  ",{"$nulls":4},"Vacuum System Undulator Interface                           "]
["1","03","04","08","","","LN408-0560","1.03.04.08","CBZ30408","9242397","Field Qualify Cold Trap (thru LTU Install)","2007-11-15","2008-02-15","LE","C","SL_MFAT1","Hrs",80,null,7073.98272,null,7073.98272,null,80,null,7073.98272,null,7073.98272,{"$nulls":6},7073.98272,1,null,null,0.2,1414.796544,1.15,1.05,4,3,"2A"]
["1","03","05","01","","","LN501-0550","1.03.05.01","CBZ30501",null,"Procure Misc Materials - Wire Scanners","2007-03-02","2007-03-28","TM","C","SL_MSEG1","$$",null,7873,null,8465.427504,8465.427504,null,null,7873,null,8465.427504,8465.427504,{"$nulls":4},8465.427504,1,{"$nulls":4},0.15,1269.8141256,1.1,1.05,3,3,"2A"]
["1","03","05","02","03","","LN502-3550","1.03.05.02.03","CBZ3050203","9242624","Create / Remodel / Revise Dsn Documentation","2007-05-01","2007-06-12","TM","C","SL_MDD1","Hrs",80,null,6698.681786016,null,6698.681786016,null,16,null,1339.7363572032,null,1339.7363572032,{"$nulls":4},1339.7363572032,1,{"$nulls":4},0.2,267.94727144064,1.15,1.05,4,2,"2A"]
["1","03","05","02","03","","LN502-3640","1.03.05.02.03","CBZ3050203","9242624","Perform Functional Testing - BPMs","2008-02-28","2008-02-29","TM","C","SL_CCA1","Hrs",15,null,1013.0947444783438,null,1013.0947444783438,null,15,null,1013.0947444783438,null,1013.0947444783438,{"$nulls":6},1013.0947444783438,1,null,null,0.2,202.61894889566878,1.15,1.05,4,3,"2A"]
["1","03","05","03","","","LN503-0050","1.03.05.03","CBX30503","9242233","Coat Toroid Ceramic","2006-09-01","2006-09-08",null,"C","SL_MFAT1","Hrs",40,null,3360,null,3360,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.2,1.1,4,3,"2A"]
["1","03","05","03","","","LN503-0080","1.03.05.03","CBX30503","9242233","Post Process & Test","2006-10-11","2006-10-17",null,"C","SL_MFAT1","Hrs",32,null,2757.8880000000004,null,2757.8880000000004,null,9.6,null,827.3664000000001,null,827.3664000000001,{"$nulls":4},827.3664000000001,1,{"$nulls":4},0.3,248.20992,1.2,1.1,4,3,"2A"]
["1","03","05","04","","","LN504-0120","1.03.05.04","CBX30504","9242234","Component Fab & Assembly - Stoppers","2007-04-18","2007-07-12",null,"C","SL_MFPC1","Hrs",27,null,4675.54356,null,4675.54356,null,27,null,4675.54356,null,4675.54356,{"$nulls":4},4675.54356,1,{"$nulls":4},0.2,935.1087120000001,1.15,1.05,4,3,"2A"]
["1","03","05","04","","","LN504-0130","1.03.05.04","CBX30504","9242234","Perform Functional Testing - Stoppers","2007-07-13","2007-07-26",null,"C","SL_MFAT1","Hrs",10,null,861.84,null,861.84,null,10,null,861.84,null,861.84,{"$nulls":4},861.84,1,{"$nulls":4},0.2,172.36800000000002,1.15,1.05,4,3,"2A"]
["1","03","05","05","","","LN505-0700","1.03.05.05","CBZ30505","9242626","Procure Profile Monitor Components","2007-06-12","2007-07-10","TM","C","SL_MSEG1","$$",null,60000,null,64514.88,64514.88,null,null,57000,null,61289.136,61289.136,{"$nulls":4},61289.136,1,{"$nulls":4},0.2,12257.8272,1.2,1,3,3,"2A"]
["1","03","05","05","","","LN505-0750","1.03.05.05","CBZ30505","9242626","Post Process & Test","2007-09-20","2007-09-26","TM","C","SL_MFAT1","Hrs",80,null,6894.72,null,6894.72,null,80,null,6894.72,null,6894.72,{"$nulls":4},6894.72,1,{"$nulls":4},0.2,1378.9440000000002,1.2,1,3,3,"2A"]
["1","03","05","07","","","LN507-0120","1.03.05.07","CBX30507","9242627","Procure Misc Materials - Diagnostics Supports","2006-08-01","2006-08-30",null,"C","SL_MSEG1","$$",null,450,null,471.6,471.6,null,null,0,null,0,0,{"$nulls":10},0.35,0,1.25,1.1,3,3,"2A"]
["1","03","05","07","","","LN507-0180","1.03.05.07","CBX30507","9242627","BL21 Fabrication Vacuum Assembly","2007-03-29","2007-06-21",null,"C","SL_MFAT1","Hrs",80,null,6894.72,null,6894.72,null,80,null,6894.72,null,6894.72,{"$nulls":4},6894.72,1,{"$nulls":4},0.35,2413.152,1.25,1.1,4,3,"2A"]
["1","03","05","07","","","LN507-0190","1.03.05.07","CBX30507","9242627","BL21 Fabrcation Optics Assembly","2007-03-29","2007-06-21",null,"C","SL_MES1","Hrs",40,null,3211.6967467199997,null,3211.6967467199997,null,40,null,3211.6967467199997,null,3211.6967467199997,{"$nulls":4},3211.6967467199997,1,{"$nulls":4},0.35,1124.0938613519997,1.25,1.1,4,3,"2A"]
["1","03","05","07","","","LN507-0200","1.03.05.07","CBX30507","9242627","BL21 Fabricate Supports","2007-03-29","2007-05-23",null,"C","SL_MFAT1","Hrs",40,null,3447.36,null,3447.36,null,40,null,3447.36,null,3447.36,{"$nulls":4},3447.36,1,{"$nulls":4},0.35,1206.576,1.25,1.1,4,3,"2A"]
["1","03","05","08","01","","LN508-1040","1.03.05.08.01","CBX3050801","9242628","Revise  Design Documentation","2007-02-22","2007-03-07",null,"C","SL_MDD1","Hrs",25,null,2093.33805813,null,2093.33805813,null,25,null,2093.33805813,null,2093.33805813,{"$nulls":4},2093.33805813,1,{"$nulls":4},0.15,314.0007087195,1.15,1,4,2,"2A"]
["1","03","05","08","01","","LN508-1070","1.03.05.08.01","CBX3050801","9242628","Conduct Beam Loss Monitors FDR","2007-03-22","2007-03-28",null,"C","SL_ME1","Hrs",8,null,798.9581689055999,null,798.9581689055999,null,8,null,798.9581689055999,null,798.9581689055999,{"$nulls":4},798.9581689055999,1,{"$nulls":4},0.15,119.84372533583998,1.15,1,4,2,"2A"]
["1","03","05","08","02","","LN508-2050","1.03.05.08.02","CBX3050802","9242629","Write Component Traveler","2007-03-23","2007-03-29",null,"C","SL_ME1","Hrs",8,null,798.9581689055999,null,798.9581689055999,null,8,null,798.9581689055999,null,798.9581689055999,{"$nulls":4},798.9581689055999,1,{"$nulls":4},0.15,119.84372533583998,1.15,1,4,2,"2A"]
["1","03","05","08","02","","LN508-2080","1.03.05.08.02","CBX3050802","9242629","Conduct Beam Loss Monitors FDR","2007-04-09","2007-04-13",null,"C","SL_ME1","Hrs",3,null,299.60931333959996,null,299.60931333959996,null,3,null,299.60931333959996,null,299.60931333959996,{"$nulls":4},299.60931333959996,1,{"$nulls":4},0.15,44.94139700093999,1.15,1,4,2,"2A"]
["1","03","05","09","","","LN509-0010","1.03.05.09","CBX30509","9242630","Write ICD - Single Beam Dump","2006-10-03","2006-10-04",null,"C","SL_ME1","Hrs",8,null,798.9581689055999,null,798.9581689055999,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.25,1.1,4,2,"2A"]
["1","03","05","09","","","LN509-0090","1.03.05.09","CBX30509","9242630","Procure Component Material - Single Beam Dump","2007-03-29","2007-04-25",null,"C","SL_MSEG1","$$",null,6000,null,6451.488,6451.488,null,null,6000,null,6451.488,6451.488,{"$nulls":4},6451.488,1,{"$nulls":4},0.35,2258.0208,1.25,1.1,4,3,"2A"]
["1","03","05","10","","","LN510-0040","1.03.05.10","CBX30510","9242631","Engineering Analysis","2006-10-12","2006-10-18",null,"C","SL_ME1","Hrs",60,null,5992.1862667919995,null,5992.1862667919995,null,24,null,2396.8745067167997,null,2396.8745067167997,{"$nulls":4},2396.8745067167997,1,{"$nulls":4},0.2,479.37490134335997,1.15,1.05,4,2,"2A"]
["1","03","05","10","","","LN510-0070","1.03.05.10","CBX30510","9242631","Create / Remodel / Revise Dsn Documentation","2006-11-02","2006-12-01",null,"C","SL_MDD1","Hrs",200,null,16746.70446504,null,16746.70446504,null,90,null,7536.017009268,null,7536.017009268,{"$nulls":4},7536.017009268,1,{"$nulls":4},0.2,1507.2034018536,1.15,1.05,4,2,"2A"]
["1","03","05","10","","","LN510-0250","1.03.05.10","CBX30510","9242631","Assemble Supports","2007-03-13","2007-03-26",null,"C","SL_MFAT1","Hrs",35,null,3016.44,null,3016.44,null,35,null,3016.44,null,3016.44,{"$nulls":4},3016.44,1,{"$nulls":4},0.2,603.288,1.15,1.05,4,3,"2A"]
["1","03","05","11","","","LN511-0510","1.03.05.11","CBZ30511","9242632","Design Check","2007-07-02","2007-08-27","TM","C","SL_MDD1","Hrs",240,null,20096.045358048,null,20096.045358048,null,240,null,20096.045358048,null,20096.045358048,{"$nulls":4},20096.045358048,1,{"$nulls":4},0.15,3014.4068037071997,1.15,1,4,2,"2A"]
["1","03","05","11","","","LN511-0610","1.03.05.11","CBZ30511","9242632","Component Fab & Assembly - Protection Collimat","2007-11-14","2007-12-13","TM","C","SL_MFPC1","Hrs",40,null,7106.826211199999,null,7106.826211199999,null,40,null,7106.826211199999,null,7106.826211199999,{"$nulls":6},7106.826211199999,1,null,null,0.15,1066.0239316799998,1.15,1,4,3,"2A"]
["1","03","05","11","","","LN511-0650","1.03.05.11","CBZ30511","9242632","Vendor Fab 1st Lot - Supports","2007-10-15","2007-11-09","TM","C","SL_MSEG1","$$",null,12000,null,13238.453376000001,13238.453376000001,null,null,12000,null,13238.453376000001,13238.453376000001,{"$nulls":6},13238.453376000001,1,null,null,0.15,1985.7680064,1.15,1,4,3,"2A"]
["1","03","05","12","","","LN512-0630","1.03.05.12","CBZ30512","9242633","Component Fab & Assembly - Movable Collimator","2006-10-05","2007-02-13","TM","C","SL_MFPC1","Hrs",20,null,3463.3656,null,3463.3656,null,18,null,3117.0290400000004,null,3117.0290400000004,{"$nulls":4},3117.0290400000004,1,{"$nulls":4},0.2,623.4058080000001,1.15,1.05,4,3,"2A"]
["1","03","05","12","","","LN512-0690","1.03.05.12","CBZ30512","9242633","Vendor Fab 1st Lot - Supports","2007-05-02","2007-05-30","TM","C","SL_MSEG1","$$",null,8400,null,9032.0832,9032.0832,null,null,8400,null,9032.0832,9032.0832,{"$nulls":4},9032.0832,1,{"$nulls":4},0.2,1806.41664,1.15,1.05,4,3,"2A"]
["1","03","05","13","","","LN513-0060","1.03.05.13","CBX30513","9242634","Write Component Traveler","2007-03-23","2007-03-29",null,"C","SL_ME1","Hrs",8,null,798.9581689055999,null,798.9581689055999,null,8,null,798.9581689055999,null,798.9581689055999,{"$nulls":4},798.9581689055999,1,{"$nulls":4},0.2,159.79163378112,1.2,1,4,2,"2A"]
["1","03","05","13","","","LN513-0090","1.03.05.13","CBX30513","9242634","Conduct Single Beam Dump FDR","2007-04-09","2007-04-13",null,"C","SL_ME1","Hrs",3,null,299.60931333959996,null,299.60931333959996,null,3,null,299.60931333959996,null,299.60931333959996,{"$nulls":4},299.60931333959996,1,{"$nulls":4},0.2,59.921862667919996,1.2,1,4,2,"2A"]
["1","03","06","02","","","LN602-0080","1.03.06.02","CBX30602",null,"Fab & Cold Test - T-Cav Waveguide","2007-01-08","2007-05-01",null,"C","SL_MFPC1","Hrs",40,null,6926.7312,null,6926.7312,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,3,3,"2A"]
["1","03","06","02","","","LN602-0140","1.03.06.02","CBX30602",null,"Fab & Cold Test - Cold Test Hardware","2006-07-05","2006-07-18","S","C","SL_MFMS1","Hrs",8,null,860.064,null,860.064,null,0,null,0,null,0,{"$nulls":10},0.15,0,1.1,1.05,3,3,"2A"]
["1","03","06","02","","","LN602-0170","1.03.06.02","CBX30602",null,"Post Process Waveguide","2006-08-01","2006-09-12","S","C","SL_MFAT1","Hrs",13,null,1092,null,1092,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.2,1.05,3,3,"2A"]
["1","03","06","04","","","LN06040008","1.03.06.04","CBA30604","9242236","Design X-Band LLRF System","2006-08-01","2006-08-22","S","C","SL_KE","Hrs",128,null,14806.101449464013,null,14806.101449464013,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.35,1.05,3,2,"2G","R. Akre"]
["1","03","06","04","","","LN06040152","1.03.06.04","LBA30604","9242236","Vendor Fab & Assy - X-Band TWT Driver","2006-11-01","2007-04-30","S","L","SA_MSEG","$$",null,30000,null,34513.01700000001,34513.01700000001,null,null,0,null,0,0,{"$nulls":10},0.4,0,1.35,1.05,3,3,"2G","R. Akre"]
["1","03","06","04","","","LN06040004","1.03.06.04","PBA30604","9242236","Write X-Band LLRF ICD","2006-08-01","2006-08-28","S","P","SL_KE","Hrs",10,null,1156.726675739376,null,1156.726675739376,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,3,2,"2G","R. Akre"]
["1","03","06","07","04","  ",{"$nulls":4},"Klystron Controls Interfaces                                "]
["1","03","06","07","07","  ",{"$nulls":4},"RF Distribution L2 & L3                                     "]
["1","03","07","06","  ","  ",{"$nulls":4},"Linac LTU System Installation & Alignment                   ",{"$nulls":6},8336,175000,749194.765579252,192361.86719999998,941556.6327792522,null,7688,156250,694815.8678112522,172200.9672,867016.8350112522,0,null,0,null,30914.235159231575,null,836102.5998520206,null,0,null,null,216754.20875281305]
["1","03","07","06","","","LN706-0130","1.03.07.06","CBX30706","9242646","RCV:  Installation Hardware","2007-10-02","2007-10-02",null,"C","SL_MSEG1","$$",null,75000,null,82740.3336,82740.3336,null,null,75000,null,82740.3336,82740.3336,{"$nulls":6},82740.3336,1,null,null,0.25,20685.0834,1.2,1.05,4,4,"2A"]
["1","03","07","06","","","LN706-0280","1.03.07.06","CBX30706","9242646","Align Beamline Components to Coordinate System","2008-04-01","2008-04-04","S","C","SL_MFAT1","Hrs",240,null,21221.94816,null,21221.94816,null,240,null,21221.94816,null,21221.94816,{"$nulls":6},21221.94816,1,null,null,0.25,5305.48704,1.2,1.05,4,4,"2A"]
["1","03","07","06","","","LN706-0290","1.03.07.06","CBX30706","9242646","Magnet Power Interconnect & Test","2008-04-07","2008-04-09","S","C","SL_CE1","Hrs",10,null,1159.7032574123039,null,1159.7032574123039,null,10,null,1159.7032574123039,null,1159.7032574123039,{"$nulls":6},1159.7032574123039,1,null,null,0.25,289.92581435307596,1.2,1.05,4,4,"2A"]
["1","03","07","06","","","LN706-0320","1.03.07.06","CBX30706","9242646","Perform Magnet Power Test","2008-04-23","2008-04-24","S","C","SL_CCA1","Hrs",16,null,1080.6343941102334,null,1080.6343941102334,null,16,null,1080.6343941102334,null,1080.6343941102334,{"$nulls":6},1080.6343941102334,1,null,null,0.25,270.15859852755835,1.2,1.05,4,4,"2A"]
["1","03","07","07","","","LN707-0010","1.03.07.07","CBX30707","9242647","Establish & Maintain Component Storage Facility","2006-07-05","2006-08-31","S","C","SL_MSEG1","$$",null,25000,null,26200,26200,null,null,0,null,0,0,{"$nulls":10},0.25,0,1.2,1.05,4,4,"2A"]
["1","03","07","07","","","LN707-0160","1.03.07.07","CBX30707","9242647","Install All Racks, Cables, Trays & Test","2007-12-10","2008-01-30","S","C","SL_CE1","Hrs",12,null,1391.6439088947645,null,1391.6439088947645,null,12,null,1391.6439088947645,null,1391.6439088947645,{"$nulls":6},1391.6439088947645,1,null,null,0.25,347.91097722369113,1.2,1.05,4,4,"2A"]
["1","03","07","07","","","LN707-0170","1.03.07.07","CBX30707","9242647","Install Beamline Components","2008-01-09","2008-01-30","S","C","SL_ME1","Hrs",60,null,6147.9831097285905,null,6147.9831097285905,null,60,null,6147.9831097285905,null,6147.9831097285905,{"$nulls":6},6147.9831097285905,1,null,null,0.25,1536.9957774321476,1.2,1.05,4,4,"2A"]
["1","03","07","07","","","LN707-0220","1.03.07.07","CBX30707","9242647","Perform Magnet Power Test","2008-03-26","2008-03-27","S","C","SL_CT1","Hrs",80,null,5079.236970544703,null,5079.236970544703,null,80,null,5079.236970544703,null,5079.236970544703,{"$nulls":6},5079.236970544703,1,null,null,0.25,1269.8092426361757,1.2,1.05,4,4,"2A"]
["1","03","07","07","","","LN707-0230","1.03.07.07","CBX30707","9242647","Perform Diagnostics Controls Test","2008-03-28","2008-04-01","S","C","SL_CE1","Hrs",24,null,2783.287817789529,null,2783.287817789529,null,24,null,2783.287817789529,null,2783.287817789529,{"$nulls":6},2783.287817789529,1,null,null,0.25,695.8219544473823,1.2,1.05,4,4,"2A"]
["1","03","07","10","01","","LN710-1100","1.03.07.10.01","CBX3071001",null,"Remove fast valve between sector 20 and 21","2006-08-01","2006-08-01",null,"C","SL_MFAT1","Hrs",8,null,672,null,672,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.15,1.05,4,4,"2A"]
["1","03","07","10","01","","LN710-1130","1.03.07.10.01","CBX3071001",null,"Remove Waveguide and Loads from Structure","2006-08-01","2006-08-04",null,"C","SL_MFAT1","Hrs",64,null,5376,null,5376,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.15,1.05,4,4,"2A"]
["1","03","07","10","01","","LN710-1250","1.03.07.10.01","CBX3071001",null,"Grind upstream and downstream eyelets","2006-08-01","2006-08-01",null,"C","SL_MFAT1","Hrs",16,null,1344,null,1344,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.15,1.05,4,4,"2A"]
["1","03","07","10","01","","LN710-1320","1.03.07.10.01","CBX3071001",null,"Grind upstream and downstream eyelets","2006-08-01","2006-08-01",null,"C","SL_MFAT1","Hrs",16,null,1344,null,1344,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.15,1.05,4,4,"2A"]
["1","03","07","10","02","","LN710-2070","1.03.07.10.02","CBX3071002",null,"Install penetration 2.93 waveguide","2006-08-01","2006-08-01",null,"C","SL_MFAT1","Hrs",24,null,2016,null,2016,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.15,1.05,4,4,"2A"]
["1","03","07","10","03","","LN710-3010","1.03.07.10.03","CBX3071003",null,"Planning, preperation and staging prior to downt","2006-07-05","2006-07-31",null,"C","SL_MFAT1","Hrs",320,null,26880,null,26880,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.15,1.05,4,4,"2A"]
["1","03","07","10","03","","LN710-3130","1.03.07.10.03","CBX3071003",null,"Weld Wavguide to Manifold Eyelet","2006-09-22","2006-09-22",null,"C","SL_MFAT1","Hrs",4,null,336,null,336,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.15,1.05,4,4,"2A"]
["1","03","07","10","03","","LN710-3160","1.03.07.10.03","CBX3071003",null,"Install Output Loads to 130 1C","2006-09-22","2006-09-22",null,"C","SL_MFAT1","Hrs",16,null,1344,null,1344,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.15,1.05,4,4,"2A"]
["1","03","07","10","03","","LN710-3330","1.03.07.10.03","CBX3071003",null,"Install BX11 and CQ11","2006-09-14","2006-09-14",null,"C","SL_MFAT1","Hrs",24,null,2016,null,2016,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.15,1.05,4,4,"2A"]
["1","03","07","10","03","","LN710-3360","1.03.07.10.03","CBX3071003",null,"Install BC1 Table Upstream Vacuum Assy","2007-05-22","2007-05-23",null,"C","SL_MFAT1","Hrs",48,null,4136.832,null,4136.832,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.15,1.05,4,4,"2A"]
["1","03","07","10","03","","LN710-3480","1.03.07.10.03","CBX3071003",null,"Install Current Monitor OTR12","2007-06-14","2007-06-14",null,"C","SL_MFAT1","Hrs",16,null,1378.9440000000002,null,1378.9440000000002,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.15,1.05,4,4,"2A"]
["1","03","07","10","03","","LN710-3550","1.03.07.10.03","CBX3071003",null,"Install Quad Magnet Q21301","2007-07-05","2007-07-05",null,"C","SL_MFAT1","Hrs",16,null,1378.9440000000002,null,1378.9440000000002,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.15,1.05,4,4,"2A"]
["1","03","07","10","04","","LN710-4020","1.03.07.10.04","CBX3071004","9242929","DC Cable Installation","2006-08-01","2006-08-11",null,"C","SL_MSPF1","$$",null,20760,null,20760,20760,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.15,1.05,4,4,"2A"]
["1","03","07","10","05","","LN710-5030","1.03.07.10.05","CBX3071005","9242930","I&C Cable Installation","2006-08-14","2006-08-24",null,"C","SL_MSPF1","$$",null,10350,null,10350,10350,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.15,1.05,4,4,"2A"]
["1","03","07","20","01","","LN720-1060","1.03.07.20.01","CBX3072001","9242931","Disconnect Water from Structures and Loads","2007-10-05","2007-10-08",null,"C","SL_MFAT1","Hrs",32,null,2829.593088,null,2829.593088,null,32,null,2829.593088,null,2829.593088,{"$nulls":6},2829.593088,1,null,null,0.3,848.8779264,1.2,1.1,4,4,"2A"]
["1","03","07","20","01","","LN720-1090","1.03.07.20.01","CBX3072001","9242931","Remove LLRF","2007-10-11","2007-10-11",null,"C","SL_KT1","Hrs",16,null,1015.8473941089405,null,1015.8473941089405,null,16,null,1015.8473941089405,null,1015.8473941089405,{"$nulls":6},1015.8473941089405,1,null,null,0.3,304.75421823268215,1.2,1.1,4,4,"2A"]
["1","03","07","20","01","","LN720-1250","1.03.07.20.01","CBX3072001","9242931","Remove Waveguide and Loads from Structure","2007-10-12","2007-10-17",null,"C","SL_MFAT1","Hrs",64,null,5659.186176,null,5659.186176,null,64,null,5659.186176,null,5659.186176,{"$nulls":6},5659.186176,1,null,null,0.3,1697.7558528,1.2,1.1,4,4,"2A"]
["1","03","07","20","01","","LN720-1280","1.03.07.20.01","CBX3072001","9242931","Remove Waveguide and Loads from Structure","2007-10-12","2007-10-17",null,"C","SL_MFAT1","Hrs",64,null,5659.186176,null,5659.186176,null,64,null,5659.186176,null,5659.186176,{"$nulls":6},5659.186176,1,null,null,0.3,1697.7558528,1.2,1.1,4,4,"2A"]
["1","03","07","20","01","","LN720-1350","1.03.07.20.01","CBX3072001","9242931","Remove Accelerator Section LI21 310 3A","2007-10-25","2007-10-25",null,"C","SL_MFAT1","Hrs",64,null,5659.186176,null,5659.186176,null,64,null,5659.186176,null,5659.186176,{"$nulls":6},5659.186176,1,null,null,0.3,1697.7558528,1.2,1.1,4,4,"2A"]
["1","03","07","20","02","","LN720-2100","1.03.07.20.02","CBX3072002","9242932","Weld Downstream BPM Eyelet between 1C and 1D","2007-11-01","2007-11-01",null,"C","SL_MFAT1","Hrs",6,null,530.548704,null,530.548704,null,6,null,530.548704,null,530.548704,{"$nulls":6},530.548704,1,null,null,0.3,159.1646112,1.2,1.1,4,4,"2A"]
["1","03","07","20","02","","LN720-2220","1.03.07.20.02","CBX3072002","9242932","Install Downstram Slowvalve","2007-09-24","2007-09-24",null,"C","SL_MFAT1","Hrs",12,null,1034.208,null,1034.208,null,12,null,1034.208,null,1034.208,{"$nulls":4},1034.208,1,{"$nulls":4},0.3,310.2624,1.2,1.1,4,4,"2A"]
["1","03","07","20","02","","LN720-2290","1.03.07.20.02","CBX3072002","9242932","Install BC1 Input Supports","2007-09-11","2007-09-12",null,"C","SL_MSPF1","$$",null,4170,null,4170,4170,null,null,4170,null,4170,4170,{"$nulls":4},4170,1,{"$nulls":4},0.3,1251,1.2,1.1,4,4,"2A"]
["1","03","07","20","02","","LN720-2410","1.03.07.20.02","CBX3072002","9242932","Install B11","2007-10-08","2007-10-09",null,"C","SL_MFAT1","Hrs",96,null,8488.779264,null,8488.779264,null,96,null,8488.779264,null,8488.779264,{"$nulls":6},8488.779264,1,null,null,0.3,2546.6337792,1.2,1.1,4,4,"2A"]
["1","03","07","20","02","","LN720-2440","1.03.07.20.02","CBX3072002","9242932","Install Corrector XCM13","2007-10-12","2007-10-15",null,"C","SL_MFAT1","Hrs",72,null,6366.5844480000005,null,6366.5844480000005,null,72,null,6366.5844480000005,null,6366.5844480000005,{"$nulls":6},6366.5844480000005,1,null,null,0.3,1909.9753344,1.2,1.1,4,4,"2A"]
["1","03","07","20","02","","LN720-2600","1.03.07.20.02","CBX3072002","9242932","Install Quad Magnet QM15","2007-11-13","2007-11-13",null,"C","SL_MFAT1","Hrs",36,null,3183.2922240000003,null,3183.2922240000003,null,36,null,3183.2922240000003,null,3183.2922240000003,{"$nulls":6},3183.2922240000003,1,null,null,0.3,954.9876672,1.2,1.1,4,4,"2A"]
["1","03","07","20","02","","LN720-2630","1.03.07.20.02","CBX3072002","9242932","Pumpdown and Leack Check Sector 20 and 21","2007-11-27","2007-11-29",null,"C","SL_MFAT1","Hrs",300,null,26527.4352,null,26527.4352,null,300,null,26527.4352,null,26527.4352,{"$nulls":6},26527.4352,1,null,null,0.3,7958.23056,1.2,1.1,4,4,"2A"]
["1","03","07","20","03","","LN720-3630","1.03.07.20.03","CBZ3072003","9242933","Phase III Cable Instllation","2007-08-09","2007-11-09","S","C","SL_MSPF1","$$",null,766000,null,766000,null,null,null,766000,null,766000,766000,{"$nulls":4},441282.60869565216,0.58,324717.39130434784,0.42,{"$nulls":6},4,4,"2A"]
["1","03","07","20","04","","LN720-4060","1.03.07.20.04","CCX3072004",null,"Install Exit Section Components","2007-12-18","2008-01-02","S","C","SL_SEE1","Hrs",50,null,5447.453725478159,null,5447.453725478159,null,50,null,5447.453725478159,null,5447.453725478159,{"$nulls":6},5447.453725478159,1,null,null,0.3,1634.2361176434476,1.2,1.1,4,4,"2A"]
["1","03","07","20","04","","LN720-4090","1.03.07.20.04","CCX3072004",null,"Install EOU","2007-12-05","2008-01-11","S","C","SL_PHS1","Hrs",24,null,1800.9509409226364,null,1800.9509409226364,null,24,null,1800.9509409226364,null,1800.9509409226364,{"$nulls":6},1800.9509409226364,1,null,null,0.3,540.2852822767909,1.2,1.1,4,4,"2A"]
["1","03","07","20","04","","LN720-4110","1.03.07.20.04","CCX3072004",null,"Validate EOU","2008-01-21","2008-01-30","S","C","SL_ME1","Hrs",24,null,2459.193243891436,null,2459.193243891436,null,24,null,2459.193243891436,null,2459.193243891436,{"$nulls":6},2459.193243891436,1,null,null,0.3,737.7579731674308,1.2,1.1,4,4,"2A"]
["1","04","  ","  ","  ","  ",{"$nulls":4},"UNDULATOR SYSTEM                                            ",{"$nulls":6},86011,13758540,7735663.7128395485,14187298.600949194,20929172.814059522,null,57601.81,10513573.15,5072474.225207783,10811864.283501277,15884338.508709041,0,null,258028.2310825978,null,9395576.97164969,null,6230733.305976741,null,0,null,null,2967062.905054943]
["1","04","01","01","01","  ",{"$nulls":4},"Undulator System Management - Technical                     ",{"$nulls":6},17029,37500,1558676.5132411567,46530.819884393066,1558676.5132411567,null,4686.08,22500,381426.644951651,27918.491930635842,409345.1368822868,0,null,31951.093592485802,null,267652.73728829925,null,109741.30600150173,null,0,null,null,0]
["1","04","01","01","01","","UN11_00141","1.04.01.01.01","CCA4010101","9242648","SLAC Travel (30 trips@$1250/trip)","2006-10-03","2008-03-05","A","C","SL_MSTR1","$$",null,37500,null,46530.819884393066,null,null,null,22500,null,27918.491930635842,27918.491930635842,{"$nulls":4},19526.806494837787,0.7,8391.685435798057,0.3,null,null,0,0,1,1,4,1,"4A"]
["1","04","01","01","02","","UN11_00272","1.04.01.01.02","CBA4010102",null,"Monitor Budget, Schedule and Contracts ETC(CNST)","2006-08-01","2007-04-02","A","C","AN_ADMN1","Hrs",1040,null,114193.58082546963,null,114193.58082546963,null,0,null,0,null,0,{"$nulls":10},0,0,1,1,4,1,"4A"]
["1","04","01","01","02","","UN11_00561","1.04.01.01.02","CBA4010102",null,"SLAC Indirect Tax - FY07 (CNST)","2006-10-02","2007-09-28","A","C","SL_MSXX1","$$",null,30000,null,30780,30780,null,null,30000,null,30780,30780,{"$nulls":4},30780,1,{"$nulls":4},0,0,1,1,4,1,"4A"]
["1","04","01","02","02","","UN12_00145","1.04.01.02.02","CBA4010202","9242650","EOU Development Travel","2006-08-01","2007-04-02","A","C","AN_MSTR1","$$",null,2325,null,4043.549259900001,null,null,null,0,null,0,0,{"$nulls":10},0.1,0,1.05,1.05,1,1,"4A"]
["1","04","02","02","01","03",{"$nulls":4},"Motor Driver                                                "]
["1","04","02","02","06","03",{"$nulls":4},"Motor Driver                                                "]
["1","04","02","03","01","04",{"$nulls":4},"Cabling                                                     "]
["1","04","02","04","  ","  ",{"$nulls":4},"Video                                                       "]
["1","04","02","04","03","04",{"$nulls":4},"Cabling                                                     "]
["1","04","02","05","  ","  ",{"$nulls":4},"Data Acquisition and Control                                "]
["1","04","02","06","02","01",{"$nulls":4}," Integrate components                                       "]
["1","04","02","08","01","","UN801BB005","1.04.02.08","CB20801BB","9242243","DBs and Displays","2007-11-12","2007-11-27",null,"C","SL_CP1","Hrs",80,null,6764.337266144831,null,6764.337266144831,null,80,null,6764.337266144831,null,6764.337266144831,{"$nulls":6},6764.337266144831,1,{"$nulls":8},"2G","K. Luchini"]
["1","04","02","08","02","02","UN8202B060","1.04.02.08","CB80202CC","9242243","Bench Test","2006-09-29","2006-09-29",null,"C","SL_PCT1","Hrs",2,null,120.62678759999997,null,120.62678759999997,null,2,null,120.62678759999997,null,120.62678759999997,null,null,120.62678759999997,1,{"$nulls":12},"2G","K. Luchini"]
["1","04","02","08","02","03","UN8203B035","1.04.02.08","CB80203BB","9242243","RCV:  Analog to Digital Converter Modules 12-ch","2006-10-18","2006-10-18",null,"C","SL_MSEG1","$$",null,2500,null,2688.12,2688.12,null,null,2500,null,2688.12,2688.12,{"$nulls":4},2688.12,1,{"$nulls":10},"2G","K. Luchini"]
["1","04","02","08","02","03","UN8203C010","1.04.02.08","CB80203CC","9242243","Develop Touch Panel Displays","2006-09-27","2006-10-30",null,"C","SL_PCE1","Hrs",192,null,21635.388114278398,null,21635.388114278398,null,192,null,21635.388114278398,null,21635.388114278398,null,null,2622.4712865792,0.12,19012.9168276992,0.88,{"$nulls":10},"2G","K. Luchini"]
["1","04","02","08","02","03","UN8203C065","1.04.02.08","CB80203CC","9242243","RCV:  PLC Control Interface Module","2006-10-18","2006-10-18",null,"C","SL_MSEG1","$$",null,3500,null,3763.368,3763.368,null,null,3500,null,3763.368,3763.368,{"$nulls":4},3763.368,1,{"$nulls":10},"2G","K. Luchini"]
["1","04","02","08","02","03","UN8203C125","1.04.02.08","CB80203CC","9242243","Pre-intall Qual Test","2006-10-20","2006-10-23",null,"C","SL_PCCA1","Hrs",8,null,526.6249483967999,null,526.6249483967999,null,8,null,526.6249483967999,null,526.6249483967999,{"$nulls":4},526.6249483967999,1,{"$nulls":10},"2G","K. Luchini"]
["1","04","02","08","02","03","UN8203D020","1.04.02.08","CB80203DD","9242243","Documentation","2006-08-01","2006-08-04",null,"C","SL_PCE1","Hrs",32,null,3525.3491327999996,null,3525.3491327999996,null,32,null,3525.3491327999996,null,3525.3491327999996,null,null,3525.3491327999996,1,{"$nulls":12},"2G","K. Luchini"]
["1","04","02","08","02","04","UN8204B025","1.04.02.08","CB80204BB","9242243","RCV: MCOR Controller Module","2006-11-03","2006-11-03",null,"C","SL_MSEG1","$$",null,800,null,860.1984,860.1984,null,null,800,null,860.1984,860.1984,{"$nulls":4},860.1984,1,{"$nulls":10},"2G","K. Luchini"]
["1","04","02","08","02","04","UN8204B085","1.04.02.08","CB80204BB","9242243","RCV: 12Amp Pwr & Prog Modules - QF15","2006-11-03","2006-11-03",null,"C","SL_MSEG1","$$",null,2098,null,2255.870304,2255.870304,null,null,2098,null,2255.870304,2255.870304,{"$nulls":4},2255.870304,1,{"$nulls":10},"2G","K. Luchini"]
["1","04","02","08","02","04","UN8204D015","1.04.02.08","CB80204DD","9242243","RCV: MCOR Chassis","2006-11-03","2006-11-03",null,"C","SL_MSEG1","$$",null,3000,null,3225.744,3225.744,null,null,3000,null,3225.744,3225.744,{"$nulls":4},3225.744,1,{"$nulls":10},"2G","K. Luchini"]
["1","04","02","08","02","04","UN8204D050","1.04.02.08","CB80204DD","9242243","RCV: 12Amp Pwr & Prog Modules - QF7","2006-11-03","2006-11-03",null,"C","SL_MSEG1","$$",null,2098,null,2255.870304,2255.870304,null,null,2098,null,2255.870304,2255.870304,{"$nulls":4},2255.870304,1,{"$nulls":10},"2G","K. Luchini"]
["1","04","02","08","02","04","UN8204F010","1.04.02.08","CB80204FF","9242243","RCV: MCOR Chassis","2006-11-03","2006-11-03",null,"C","SL_MSEG1","$$",null,2850,null,3064.4568,3064.4568,null,null,2850,null,3064.4568,3064.4568,{"$nulls":4},3064.4568,1,{"$nulls":10},"2G","K. Luchini"]
["1","04","02","08","02","04","UN8204F045","1.04.02.08","CB80204FF","9242243","RCV: 12Amp Pwr & Prog Modules - QD24","2006-11-03","2006-11-03",null,"C","SL_MSEG1","$$",null,2098,null,2255.870304,2255.870304,null,null,2098,null,2255.870304,2255.870304,{"$nulls":4},2255.870304,1,{"$nulls":10},"2G","K. Luchini"]
["1","04","02","08","02","04","UN8204F105","1.04.02.08","CB80204FF","9242243","RCV:  Cable Accessories - Lugs, Splices, etc","2006-11-03","2006-11-03",null,"C","SL_MSEG1","$$",null,560,null,602.13888,602.13888,null,null,560,null,602.13888,602.13888,{"$nulls":4},602.13888,1,{"$nulls":10},"2G","K. Luchini"]
["1","04","02","08","02","04","UN8204F120","1.04.02.08","CB80204FF","9242243","MCOR Bench Test and Assembly","2006-11-07","2006-11-07",null,"C","SL_TMUE1","Hrs",8,null,768.170304,null,768.170304,null,8,null,768.170304,null,768.170304,{"$nulls":4},768.170304,1,{"$nulls":10},"2G","K. Luchini"]
["1","04","02","08","02","04","UN8204H020","1.04.02.08","CB80204HH","9242243","RCV: MCOR Crate Accessories","2006-11-03","2006-11-03",null,"C","SL_MSEG1","$$",null,500,null,537.624,537.624,null,null,500,null,537.624,537.624,{"$nulls":4},537.624,1,{"$nulls":10},"2G","K. Luchini"]
["1","04","02","08","02","04","UN8204H085","1.04.02.08","CB80204HH","9242243","RCV:  Digital to Analog Converter Module - 16 Ch","2006-08-01","2006-08-01",null,"C","SL_MSEG1","$$",null,1500,null,1572,1572,null,null,1500,null,1572,1572,null,null,1572,1,{"$nulls":12},"2G","K. Luchini"]
["1","04","02","08","03","","UN2803B015","1.04.02.08","CB20803BB","9242243","RCV: Panel","2006-12-08","2006-12-08",null,"C","SL_MSEG1","$$",null,50,null,53.7624,53.7624,null,null,50,null,53.7624,53.7624,{"$nulls":4},53.7624,1,{"$nulls":10},"2G","K. Luchini"]
["1","04","02","08","03","","UN2803C045","1.04.02.08","CB20803CC","9242243","Integrate Cables","2006-08-04","2006-08-08",null,"C","SL_TMUE1","Hrs",24,null,2246.112,null,2246.112,null,24,null,2246.112,null,2246.112,null,null,2246.112,1,{"$nulls":12},"2G","K. Luchini"]
["1","04","02","08","04","  ",{"$nulls":4},"System Checkout                                             ",{"$nulls":6},56,0,4738.790623473006,0,4738.790623473006,null,56,0,4738.790623473006,0,4738.790623473006,0,null,0,null,0,null,4738.790623473006,null,0,null,null,0]
["1","04","02","10","01","  ",{"$nulls":4},"UCM Hardware Design                                         ",{"$nulls":6},361,0,39891.06993211453,0,39891.06993211453,null,216.2,0,23890.441327764987,0,23890.441327764987,0,null,0,null,23890.441327764987,null,0,null,0,null,null,0,{"$nulls":8},"Hamid Shoaee"]
["1","04","02","10","02","","UN21002020","1.04.02.10","CBC1040210",null,"Conduct FDR","2006-09-07","2006-09-07",null,"C","AN_CE1","Hrs",8,null,861.6107505600002,null,861.6107505600002,null,8,null,861.6107505600002,null,861.6107505600002,null,null,861.6107505600002,1,{"$nulls":12},"2G","ANL"]
["1","04","02","10","03","","UN21003001","1.04.02.10","CBD1040210",null,"Vendor search for UCMI assy vendor","2007-05-09","2007-05-15",null,"C","AN_CE1","Hrs",40,null,4420.063150372801,null,4420.063150372801,null,40,null,4420.063150372801,null,4420.063150372801,{"$nulls":4},4420.063150372801,1,{"$nulls":10},"2G","ANL"]
["1","04","02","10","05","","UN21005005","1.04.02.10","CBF1040210",null,"Installation in LTT","2007-08-02","2007-08-03",null,"C","AN_CT1","Hrs",16,null,1038.03470847936,null,1038.03470847936,null,16,null,1038.03470847936,null,1038.03470847936,{"$nulls":4},1038.03470847936,1,{"$nulls":10},"2G","ANL"]
["1","04","02","10","08","","UN21008001","1.04.02.10","CBH1040210",null,"Validation of UCMI First Article","2007-11-30","2007-12-13",null,"C","AN_CE1","Hrs",32,null,3627.9878338259946,null,3627.9878338259946,null,32,null,3627.9878338259946,null,3627.9878338259946,{"$nulls":6},3627.9878338259946,1,{"$nulls":8},"2G","ANL"]
["1","04","02","10","10","  ",{"$nulls":4},"Procure Production Blade IOC                                ",{"$nulls":6},160,340000,14030.299843142402,348840,362870.2998431424,null,160,340000,14030.299843142402,348840,362870.2998431424,0,null,0,null,362870.2998431424,null,0,null,0,null,null,0]
["1","04","02","10","12","","UN21012015","1.04.02.10","CBN1040210",null,"RCV production Potentiometers","2006-10-05","2006-10-05",null,"C","AN_MSEG1","$$",null,75000,null,76950,76950,null,null,75000,null,76950,76950,{"$nulls":4},76950,1,{"$nulls":10},"2G","ANL"]
["1","04","02","12","01","","UN21201001","1.04.02.12","CBB1040212",null,"Undulator rack design","2006-08-01","2006-08-14",null,"C","AN_CT1","Hrs",80,null,5058.648676800001,null,5058.648676800001,null,32,null,2023.4594707200004,null,2023.4594707200004,null,null,2023.4594707200004,1,{"$nulls":12},"2G","ANL"]
["1","04","02","12","01","","UN21201030","1.04.02.12","CBB1040212",null,"Tray loading and design","2006-10-25","2006-11-21",null,"C","AN_CT1","Hrs",160,null,10380.3470847936,null,10380.3470847936,null,160,null,10380.3470847936,null,10380.3470847936,{"$nulls":4},10380.3470847936,1,{"$nulls":10},"2G","ANL"]
["1","04","02","12","01","","UN21201100","1.04.02.12","CBB1040212",null,"Assemble production components","2008-02-14","2008-02-27",null,"C","AN_CT1","Hrs",80,null,5325.118054499117,null,5325.118054499117,null,80,null,5325.118054499117,null,5325.118054499117,{"$nulls":6},5325.118054499117,1,{"$nulls":8},"2G","ANL"]
["1","04","02","12","01","","UN21201105","1.04.02.12","CBB1040212",null,"Ship loaded racks to SLAC","2008-02-28","2008-02-29",null,"C","AN_ME1","Hrs",16,null,1813.9939169129973,null,1813.9939169129973,null,16,null,1813.9939169129973,null,1813.9939169129973,{"$nulls":6},1813.9939169129973,1,{"$nulls":8},"2G","ANL"]
["1","04","02","12","02","","UN21202035","1.04.02.12","CBC1040212",null,"Prepare bid package for cable fab","2006-10-30","2006-11-28",null,"C","AN_CT1","Hrs",160,null,10380.3470847936,null,10380.3470847936,null,160,null,10380.3470847936,null,10380.3470847936,{"$nulls":4},10380.3470847936,1,{"$nulls":10},"2G","ANL"]
["1","04","02","13","01","  ",{"$nulls":4},"APS Testing                                                 ",{"$nulls":6},192,0,20768.265531498244,0,20768.265531498244,null,140.8,0,15244.99597610842,0,15244.99597610842,0,null,12062.550507840002,null,3182.445468268417,null,0,null,0,null,null,0,{"$nulls":8},"Hamid Shoaee"]
["1","04","02","14","","","UN21401010","1.04.02.14","CBB1040214",null,"Hardware Support - Vendor CAM test","2006-08-01","2006-09-26",null,"C","AN_CT1","Hrs",320,null,20234.594707200005,null,20234.594707200005,null,320,null,20234.594707200005,null,20234.594707200005,null,null,20234.594707200005,1,{"$nulls":12},"2G","ANL"]
["1","04","02","20","03","","UN2003B045","1.04.02.20","CB22003BB",null,"Assemble & Pre-install MPS TIU Production Units","2008-02-20","2008-03-04",null,"C","SL_TMUE1","Hrs",80,null,7881.427319039999,null,7881.427319039999,null,80,null,7881.427319039999,null,7881.427319039999,{"$nulls":6},7881.427319039999,1,{"$nulls":8},"2G","ANL"]
["1","04","02","20","06","  ",{"$nulls":4},"Undulator Controls MPS - Fault Devices                      "]
["1","04","02","21","","","UN221B0065","1.04.02.21","CB40221BB",null,"Assemble & Pre-install Production Units","2008-02-15","2008-02-29",null,"C","SL_TMUE1","Hrs",8,null,788.1427319039999,null,788.1427319039999,null,8,null,788.1427319039999,null,788.1427319039999,{"$nulls":6},788.1427319039999,1,{"$nulls":8},"2G","ANL"]
["1","04","02","22","","","UN222B0055","1.04.02.22","CB40222BB",null,"RCV: 4 VME Crates & CPUs","2007-09-25","2007-09-25",null,"C","SL_MSEG1","$$",null,36000,null,38708.928,38708.928,null,null,36000,null,38708.928,38708.928,{"$nulls":4},38708.928,1,{"$nulls":10},"2G","ANL"]
["1","04","02","22","","","UN222B0080","1.04.02.22","CB40222BB",null,"Integration & Test","2008-02-29","2008-03-27",null,"C","SL_CE1","Hrs",32,null,3711.0504237193722,null,3711.0504237193722,null,32,null,3711.0504237193722,null,3711.0504237193722,{"$nulls":6},3711.0504237193722,1,{"$nulls":8},"2G","ANL"]
["1","04","02","23","","","UN223B0010","1.04.02.23","CB40223BB",null,"DBs and Displays","2008-01-02","2008-01-15",null,"C","SL_CP1","Hrs",80,null,6764.337266144831,null,6764.337266144831,null,80,null,6764.337266144831,null,6764.337266144831,{"$nulls":6},6764.337266144831,1,{"$nulls":8},"2G","ANL"]
["1","04","02","24","","","UN224B0005","1.04.02.24","CB40225BB",null,"Software Integration","2008-03-04","2008-03-31",null,"C","SL_CP1","Hrs",80,null,6764.337266144831,null,6764.337266144831,null,80,null,6764.337266144831,null,6764.337266144831,{"$nulls":6},6764.337266144831,1,{"$nulls":8},"2G","ANL"]
["1","04","03","03","  ","  ",{"$nulls":4},"1st Article Undulators & Long Lead Procurements             ",{"$nulls":6},2607,1215170,234769.3800649701,1223409.0123312883,1244096.1300649699,null,2534.9,659581.25,226807.81670630173,667656.6248312884,894464.44153759,0,null,0,null,501536.2928431067,null,392928.1486944832,null,0,null,null,118770.7321423779]
["1","04","03","03","03","  ",{"$nulls":4},"Magnet Poles (LLP)                                          "]
["1","04","03","03","04","03","UN33_40305","1.04.03.03.04","CBD4030304",null,"AWARD: Support/Mover System 1st Art (2 units)","2007-05-08","2007-05-08","A","C","AN_AW1","$$",null,440000,null,451440,451440,null,null,440000,null,451440,451440,{"$nulls":4},451440,1,{"$nulls":4},0.15,67716,1.1,1.05,3,3,"4A"]
["1","04","03","03","04","03","UN33_40320","1.04.03.03.04","CBD4030304",null,"Factory Accept Testing 1st Art - Supt/Mover Sys","2007-07-20","2007-07-24","A","C","AN_CE1","Hrs",24,null,2652.0378902236807,null,2652.0378902236807,null,24,null,2652.0378902236807,null,2652.0378902236807,{"$nulls":4},2652.0378902236807,1,{"$nulls":4},0.15,397.8056835335521,1.1,1.05,7,3,"4A"]
["1","04","03","03","04","03","UN33_40422","1.04.03.03.04","CBD4030304",null,"REC: 2nd Articles Support/Mover System at ANL","2007-10-04","2007-10-04","A","C","AA_MSSF","$$",null,190000,null,190000,190000,null,null,190000,null,190000,190000,{"$nulls":6},190000,1,null,null,0.15,28500,1.1,1.05,7,3,"4A"]
["1","04","03","03","06","  ",{"$nulls":4},"Integrated Single-Undulator Module Test                     ",{"$nulls":6},1810,125000,156742.59234912985,130595.74233128835,156742.59234912985,null,1810,125000,156742.59234912985,130595.74233128835,287338.33468041813,0,null,0,null,85202.57367824262,null,202135.76100217554,null,0,null,null,28733.83346804182]
["1","04","03","03","06","","UN33_00546","1.04.03.03.06","CCB4030306",null,"Long-Term Stability Single Und Test","2007-05-09","2008-09-09",null,"C","AN_MFAT1","Hrs",560,null,36995.72683183359,null,36995.72683183359,null,560,null,36995.72683183359,null,36995.72683183359,{"$nulls":4},10970.103048294215,0.3,26025.623783539377,0.7,null,null,0.1,3699.5726831833595,1.05,1.05,7,3,"4A"]
["1","04","03","04","01","","UN34_00112","1.04.03.04.01","CCB4030401","9242664","RCV: From Hi-Tech - Magnet Assy Article 33","2007-05-23","2007-05-23","A2","C","AN_MSSF1","$$",null,80000,null,80000,80000,null,null,0,null,0,0,{"$nulls":10},0.05,0,1,1.05,7,3,"4A"]
["1","04","03","04","02","","UN34_10054","1.04.03.04.02","CBA4030402","9242665","Metalex Fab/Assy - Magnet Assy Article 06","2006-09-14","2006-10-12","A3","C","AN_MSSC1","$$",null,240,null,242.4514285714286,null,null,null,0,null,0,0,{"$nulls":10},0.05,0,1,1.05,7,3,"4A"]
["1","04","03","04","02","","UN34_10070","1.04.03.04.02","CBA4030402","9242665","Metalex Fab/Assy - Magnet Assy Article 14","2006-12-11","2007-01-02","A3","C","AN_MSSC1","$$",null,120,null,123.12,123.12,null,null,0,null,0,0,{"$nulls":10},0.05,0,1,1.05,7,3,"4A"]
["1","04","03","04","02","","UN34_10078","1.04.03.04.02","CBA4030402","9242665","Metalex Fab/Assy - Magnet Assy Article 18","2007-01-19","2007-02-01","A3","C","AN_ME1","Hrs",40,null,4420.063150372801,null,4420.063150372801,null,0,null,0,null,0,{"$nulls":10},0.05,0,1,1.05,7,3,"4A"]
["1","04","03","04","02","","UN34_10094","1.04.03.04.02","CBA4030402","9242665","Metalex Fab/Assy - Magnet Assy Article 26","2007-03-22","2007-04-04","A3","C","AN_ME1","Hrs",40,null,4420.063150372801,null,4420.063150372801,null,0,null,0,null,0,{"$nulls":10},0.05,0,1,1.05,7,3,"4A"]
["1","04","03","04","02","","UN34_10107","1.04.03.04.02","CBA4030402","9242665","RCV: From Metalex - Magnet Assy Article 32","2007-05-22","2007-05-22","A2","C","AN_MSSC1","$$",null,80000,null,82080,82080,null,null,0,null,0,0,{"$nulls":10},0.05,0,1,1.05,7,3,"4A"]
["1","04","03","04","03","","UN34_00040","1.04.03.04.03","CCB4030403","9242666","RCV: 2 Support/Movers","2007-09-11","2007-09-11","A","C","AA_MSSF","$$",null,180000,null,180000,180000,null,null,180000,null,180000,180000,{"$nulls":4},180000,1,{"$nulls":4},0.25,45000,1.15,1.1,4,3,"4A"]
["1","04","03","04","03","","UN34_00055","1.04.03.04.03","CCB4030403","9242666","RCV: 2 Support/Movers","2007-10-02","2007-10-02","A","C","AA_MSSF","$$",null,180000,null,180000,180000,null,null,180000,null,180000,180000,{"$nulls":6},180000,1,null,null,0.25,45000,1.15,1.1,4,3,"4A"]
["1","04","03","04","04","  ",{"$nulls":4},"Mu Metal Shield                                             ",{"$nulls":6},64,190000,6892.88600448,190000,196892.88600448,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["1","04","03","04","04","","UN34_00M21","1.04.03.04.04","CBC4030404",null,"REC:  10 mu metal shields shipped","2006-08-01","2006-08-01",null,"C","AA_MSEQ1","$$",null,50000,null,50000,50000,null,null,0,null,0,0,{"$nulls":10},0.15,0,1.05,1.1,3,3,"4A"]
["1","04","03","05","01","","UN35_Q0110","1.04.03.05.01","CCB4030501","9242667","Vendor Fab/Assy - Quad Magnet 1st Article (Q1)","2007-03-01","2007-04-23","A","C","AN_MSSF1","$$",null,20000,null,20000,20000,null,null,19000,null,19000,19000,{"$nulls":4},19000,1,{"$nulls":4},0.15,2850,1.1,1.05,7,3,"4A"]
["1","04","03","05","01","","UN35_Q1210","1.04.03.05.01","CCB4030501","9242667","Vendor Fab/Assy - Quad Mag (Q12,Q13,Q14,Q15)","2007-10-01","2007-10-09","A","C","AN_MSSF1","$$",null,15000,null,15000,15000,null,null,15000,null,15000,15000,{"$nulls":6},15000,1,null,null,0.15,2250,1.1,1.05,7,3,"4A"]
["1","04","03","05","03","","UN35_01134","1.04.03.05.03","CDB4030503","9242668","ANL Vendor Mgmt & 1st Art Test - Stages & Stands","2007-04-09","2007-10-04","A","C","AN_ME1","Hrs",170,null,18793.500135906586,null,18793.500135906586,null,161.5,null,17909.10012951098,null,17909.10012951098,{"$nulls":4},17607.26136328327,0.98,301.83876622771317,0.02,null,null,0.2,3581.8200259021964,1.1,1.1,3,3,"4A"]
["1","04","03","06","01","04","UN36_0E150","1.04.03.06.01","CBB4030601",null,"Install and Test Undulator Test Stand ETC","2006-08-01","2006-08-30","S","C","SL_MES1","Hrs",32,null,2504.246976,null,2504.246976,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.2,1,3,4,"4B"]
["1","04","03","06","01","06","UN36_0E110","1.04.03.06.01","CBB4030601",null,"Install & Test Quad Strength & Field Quality ETC","2006-08-01","2007-01-09","S","C","SL_PHS1","Hrs",12,null,869.2297633431054,null,869.2297633431054,null,0,null,0,null,0,{"$nulls":10},0.3,0,1.2,1.1,3,4,"4B"]
["1","04","03","06","01","06","UN36_RE101","1.04.03.06.01","CBB4030601",null,"RCV: Hardware for Electro Magnets","2006-08-31","2006-08-31","S","C","SL_MSEQ1","$$",null,1250,null,1310,1310,null,null,0,null,0,0,{"$nulls":10},0.15,0,1.05,1.1,2,3,"4B"]
["1","04","03","06","01","09","UN36_00270","1.04.03.06.01","CBB4030601",null,"Install and Test Undulator Handling","2007-01-22","2007-04-30","S","C","SL_MES1","Hrs",280,null,22481.87722704,null,22481.87722704,null,140,null,11240.93861352,null,11240.93861352,{"$nulls":4},11240.93861352,1,{"$nulls":4},0.1,1124.093861352,1,1.1,2,4,"4B"]
["1","04","03","06","01","09","UN36_0E250","1.04.03.06.01","CBB4030601",null,"Design Undulator Handling ETC","2006-08-01","2006-09-28","S","C","SL_ME1","Hrs",14,null,1362.7454147999997,null,1362.7454147999997,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.3,1.1,2,2,"4B"]
["1","04","03","06","02","","UN511_0210","1.04.03.06.02","CBB4030602","9242670","Supplemental Shielding Arrive at SLAC","2007-06-20","2007-07-05","S","C","SL_MFAT1","Hrs",16,null,1378.9440000000002,null,1378.9440000000002,null,16,null,1378.9440000000002,null,1378.9440000000002,{"$nulls":4},1378.9440000000002,1,{"$nulls":4},0.25,344.73600000000005,1.2,1.05,3,4,"4B"]
["1","04","03","06","02","01",{"$nulls":4},"F/MM Undulator Magnet Sections                              ",{"$nulls":6},14784,0,1277867.731788536,0,1277867.731788536,null,13235,0,1144758.1819394326,0,1144758.1819394326,0,null,0,null,511826.27396270295,null,632931.9079767298,null,0,null,null,483738.18419591326]
["1","04","03","06","02","01","UN362_0022","1.04.03.06.02","CBB4030602","9242670","Fiducialize Undulator - 02","2007-03-16","2007-03-29","S","C","SL_PHSS1","Hrs",16,null,1489.3563218688,null,1489.3563218688,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0035","1.04.03.06.02","CBB4030602","9242670","Pre-assemble Girder - 03","2007-10-12","2007-10-18","S","C","SL_SEE1","Hrs",8,null,871.5925960765054,null,871.5925960765054,null,8,null,871.5925960765054,null,871.5925960765054,{"$nulls":6},871.5925960765054,1,null,null,0.45,392.21666823442746,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","01","UN362_0042","1.04.03.06.02","CBB4030602","9242670","Fiducialize Undulator - 04","2007-04-06","2007-04-10","S","C","SL_MFAT1","Hrs",24,null,2068.416,null,2068.416,null,0,null,0,null,0,{"$nulls":10},0.4,0,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0045","1.04.03.06.02","CBB4030602","9242670","Pre-assemble Girder - 04","2007-10-12","2007-10-18","S","C","SL_MFAT1","Hrs",80,null,7073.98272,null,7073.98272,null,80,null,7073.98272,null,7073.98272,{"$nulls":6},7073.98272,1,null,null,0.45,3183.2922240000003,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","01","UN362_0062","1.04.03.06.02","CBB4030602","9242670","Fiducialize Undulator - 06","2007-04-20","2007-04-24","S","C","SL_MES1","Hrs",40,null,3211.6967467199997,null,3211.6967467199997,null,40,null,3211.6967467199997,null,3211.6967467199997,{"$nulls":4},3211.6967467199997,1,{"$nulls":4},0.4,1284.678698688,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0065","1.04.03.06.02","CBB4030602","9242670","Pre-assemble Girder - 06","2007-10-12","2007-10-18","S","C","SL_MES1","Hrs",36,null,2965.680775921248,null,2965.680775921248,null,36,null,2965.680775921248,null,2965.680775921248,{"$nulls":6},2965.680775921248,1,null,null,0.45,1334.5563491645617,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","01","UN362_0081","1.04.03.06.02","CBB4030602","9242670","Tune Undulator - 08","2007-04-20","2007-05-03","S","C","SL_MFAT1","Hrs",180,null,15513.12,null,15513.12,null,180,null,15513.12,null,15513.12,{"$nulls":4},15513.12,1,{"$nulls":4},0.4,6205.2480000000005,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0092","1.04.03.06.02","CBB4030602","9242670","Fiducialize Undulator - 09","2007-05-11","2007-05-15","S","C","SL_PHSS1","Hrs",16,null,1489.3563218688,null,1489.3563218688,null,16,null,1489.3563218688,null,1489.3563218688,{"$nulls":4},1489.3563218688,1,{"$nulls":4},0.4,595.74252874752,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0101","1.04.03.06.02","CBB4030602","9242670","Tune Undulator - 10","2007-05-04","2007-05-17","S","C","SL_MFAT1","Hrs",180,null,15513.12,null,15513.12,null,180,null,15513.12,null,15513.12,{"$nulls":4},15513.12,1,{"$nulls":4},0.4,6205.2480000000005,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0112","1.04.03.06.02","CBB4030602","9242670","Fiducialize Undulator - 11","2007-05-25","2007-05-30","S","C","SL_MES1","Hrs",40,null,3211.6967467199997,null,3211.6967467199997,null,40,null,3211.6967467199997,null,3211.6967467199997,{"$nulls":4},3211.6967467199997,1,{"$nulls":4},0.4,1284.678698688,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0122","1.04.03.06.02","CBB4030602","9242670","Fiducialize Undulator - 12","2007-06-04","2007-06-06","S","C","SL_PHSS1","Hrs",16,null,1489.3563218688,null,1489.3563218688,null,16,null,1489.3563218688,null,1489.3563218688,{"$nulls":4},1489.3563218688,1,{"$nulls":4},0.4,595.74252874752,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0125","1.04.03.06.02","CBB4030602","9242670","Pre-assemble Girder - 12","2007-11-01","2007-11-07","S","C","SL_SEE1","Hrs",8,null,871.5925960765054,null,871.5925960765054,null,8,null,871.5925960765054,null,871.5925960765054,{"$nulls":6},871.5925960765054,1,null,null,0.45,392.21666823442746,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","01","UN362_0142","1.04.03.06.02","CBB4030602","9242670","Fiducialize Undulator - 14","2007-06-18","2007-06-20","S","C","SL_MFAT1","Hrs",24,null,2068.416,null,2068.416,null,24,null,2068.416,null,2068.416,{"$nulls":4},2068.416,1,{"$nulls":4},0.4,827.3664000000001,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0145","1.04.03.06.02","CBB4030602","9242670","Pre-assemble Girder - 14","2007-11-08","2007-11-14","S","C","SL_MFAT1","Hrs",80,null,7073.98272,null,7073.98272,null,80,null,7073.98272,null,7073.98272,{"$nulls":6},7073.98272,1,null,null,0.45,3183.2922240000003,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","01","UN362_0156","1.04.03.06.02","CBB4030602","9242670","Assemble Girder - 15","2007-11-26","2007-11-30","S","C","SL_MES1","Hrs",34,null,2800.9207328145117,null,2800.9207328145117,null,34,null,2800.9207328145117,null,2800.9207328145117,{"$nulls":6},2800.9207328145117,1,null,null,0.45,1260.4143297665303,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","01","UN362_0165","1.04.03.06.02","CBB4030602","9242670","Pre-assemble Girder - 16","2007-11-15","2007-11-21","S","C","SL_MES1","Hrs",36,null,2965.680775921248,null,2965.680775921248,null,36,null,2965.680775921248,null,2965.680775921248,{"$nulls":6},2965.680775921248,1,null,null,0.45,1334.5563491645617,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","01","UN362_0181","1.04.03.06.02","CBB4030602","9242670","Tune Undulator - 18","2007-07-10","2007-07-23","S","C","SL_MFAT1","Hrs",180,null,15513.12,null,15513.12,null,180,null,15513.12,null,15513.12,{"$nulls":4},15513.12,1,{"$nulls":4},0.4,6205.2480000000005,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0186","1.04.03.06.02","CBB4030602","9242670","Assemble Girder - 18","2007-12-03","2007-12-07","S","C","SL_MFAT1","Hrs",22,null,1945.345248,null,1945.345248,null,22,null,1945.345248,null,1945.345248,{"$nulls":6},1945.345248,1,null,null,0.45,875.4053616000001,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","01","UN362_0202","1.04.03.06.02","CBB4030602","9242670","Fiducialize Undulator - 20","2007-08-07","2007-08-09","S","C","SL_PHSS1","Hrs",16,null,1489.3563218688,null,1489.3563218688,null,16,null,1489.3563218688,null,1489.3563218688,{"$nulls":4},1489.3563218688,1,{"$nulls":4},0.4,595.74252874752,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0205","1.04.03.06.02","CBB4030602","9242670","Pre-assemble Girder - 20","2007-12-03","2007-12-07","S","C","SL_SEE1","Hrs",8,null,871.5925960765054,null,871.5925960765054,null,8,null,871.5925960765054,null,871.5925960765054,{"$nulls":6},871.5925960765054,1,null,null,0.45,392.21666823442746,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","01","UN362_0222","1.04.03.06.02","CBB4030602","9242670","Fiducialize Undulator - 22","2007-08-21","2007-08-23","S","C","SL_MFAT1","Hrs",24,null,2068.416,null,2068.416,null,24,null,2068.416,null,2068.416,{"$nulls":4},2068.416,1,{"$nulls":4},0.4,827.3664000000001,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0226","1.04.03.06.02","CBB4030602","9242670","Assemble Girder - 22","2008-01-02","2008-01-08","S","C","SL_MFAT1","Hrs",22,null,1945.345248,null,1945.345248,null,22,null,1945.345248,null,1945.345248,{"$nulls":6},1945.345248,1,null,null,0.45,875.4053616000001,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","01","UN362_0236","1.04.03.06.02","CBB4030602","9242670","Assemble Girder - 23","2008-01-09","2008-01-15","S","C","SL_MFAT1","Hrs",22,null,1945.345248,null,1945.345248,null,22,null,1945.345248,null,1945.345248,{"$nulls":6},1945.345248,1,null,null,0.45,875.4053616000001,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","01","UN362_0245","1.04.03.06.02","CBB4030602","9242670","Pre-assemble Girder - 24","2008-01-02","2008-01-08","S","C","SL_MFAT1","Hrs",80,null,7073.98272,null,7073.98272,null,80,null,7073.98272,null,7073.98272,{"$nulls":6},7073.98272,1,null,null,0.45,3183.2922240000003,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","01","UN362_0256","1.04.03.06.02","CBB4030602","9242670","Assemble Girder - 25","2008-01-09","2008-01-15","S","C","SL_MES1","Hrs",34,null,2800.9207328145117,null,2800.9207328145117,null,34,null,2800.9207328145117,null,2800.9207328145117,{"$nulls":6},2800.9207328145117,1,null,null,0.45,1260.4143297665303,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","01","UN362_0265","1.04.03.06.02","CBB4030602","9242670","Pre-assemble Girder - 26","2008-01-02","2008-01-08","S","C","SL_MES1","Hrs",36,null,2965.680775921248,null,2965.680775921248,null,36,null,2965.680775921248,null,2965.680775921248,{"$nulls":6},2965.680775921248,1,null,null,0.45,1334.5563491645617,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","01","UN362_0281","1.04.03.06.02","CBB4030602","9242670","Tune Undulator - 28","2007-09-19","2007-10-02","S","C","SL_MFAT1","Hrs",180,null,15544.146240000002,null,15544.146240000002,null,180,null,15544.146240000002,null,15544.146240000002,{"$nulls":4},14348.442683076926,0.92,1195.703556923077,0.08,null,null,0.4,6217.658496000001,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0282","1.04.03.06.02","CBB4030602","9242670","Fiducialize Undulator - 28","2007-10-03","2007-10-05","S","C","SL_MES1","Hrs",40,null,3295.20086213472,null,3295.20086213472,null,40,null,3295.20086213472,null,3295.20086213472,{"$nulls":6},3295.20086213472,1,null,null,0.4,1318.0803448538882,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0302","1.04.03.06.02","CBB4030602","9242670","Fiducialize Undulator - 30","2007-10-17","2007-10-19","S","C","SL_PHSS1","Hrs",16,null,1528.0795862373886,null,1528.0795862373886,null,16,null,1528.0795862373886,null,1528.0795862373886,{"$nulls":6},1528.0795862373886,1,null,null,0.4,611.2318344949555,1.2,1.2,3,4,"4B"]
["1","04","03","06","02","01","UN362_0305","1.04.03.06.02","CBB4030602","9242670","Pre-assemble Girder - 30","2008-01-16","2008-01-23","S","C","SL_SEE1","Hrs",8,null,871.5925960765054,null,871.5925960765054,null,8,null,871.5925960765054,null,871.5925960765054,{"$nulls":6},871.5925960765054,1,null,null,0.45,392.21666823442746,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","01","UN362_0316","1.04.03.06.02","CBB4030602","9242670","Assemble Girder - 31","2008-01-08","2008-01-14","S","C","SL_MFAT1","Hrs",22,null,1945.345248,null,1945.345248,null,22,null,1945.345248,null,1945.345248,{"$nulls":6},1945.345248,1,null,null,0.45,875.4053616000001,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","01","UN362_0325","1.04.03.06.02","CBB4030602","9242670","Pre-assemble Girder - 32","2007-12-14","2008-01-07","S","C","SL_MFAT1","Hrs",80,null,7073.98272,null,7073.98272,null,80,null,7073.98272,null,7073.98272,{"$nulls":6},7073.98272,1,null,null,0.45,3183.2922240000003,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","01","UN362_0336","1.04.03.06.02","CBB4030602","9242670","Assemble Girder - 33","2007-11-19","2007-11-27","S","C","SL_MES1","Hrs",34,null,2800.9207328145117,null,2800.9207328145117,null,34,null,2800.9207328145117,null,2800.9207328145117,{"$nulls":6},2800.9207328145117,1,null,null,0.45,1260.4143297665303,1.25,1.2,4,3,"4B"]
["1","04","03","06","02","02","UN36_02010","1.04.03.06.02","CBB4030602","9242670","Measure and Fiducialize Quadrupole - 01","2007-06-18","2007-06-20","S","C","AN_ME1","Hrs",80,null,8840.126300745602,null,8840.126300745602,null,80,null,8840.126300745602,null,8840.126300745602,{"$nulls":4},8840.126300745602,1,{"$nulls":4},0.35,3094.0442052609606,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02070","1.04.03.06.02","CBB4030602","9242670","Measure and Fiducialize Quadrupole - 04","2007-06-29","2007-07-03","S","C","SL_MES1","Hrs",4,null,321.169674672,null,321.169674672,null,4,null,321.169674672,null,321.169674672,{"$nulls":4},321.169674672,1,{"$nulls":4},0.35,112.40938613519998,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02085","1.04.03.06.02","CBB4030602","9242670","Measure and Fiducialize Quadrupole - 05","2007-07-05","2007-07-09","S","C","SL_MFAT1","Hrs",8,null,689.4720000000001,null,689.4720000000001,null,8,null,689.4720000000001,null,689.4720000000001,{"$nulls":4},689.4720000000001,1,{"$nulls":4},0.35,241.3152,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02140","1.04.03.06.02","CBB4030602","9242670","Measure and Fiducialize Quadrupole - 08","2007-07-18","2007-07-20","S","C","SL_PHS1","Hrs",20,null,1462.7606732639997,null,1462.7606732639997,null,20,null,1462.7606732639997,null,1462.7606732639997,{"$nulls":4},1462.7606732639997,1,{"$nulls":4},0.35,511.96623564239985,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02180","1.04.03.06.02","CBB4030602","9242670","Measure and Fiducialize Quadrupole - 10","2007-07-26","2007-07-27","S","C","SL_PHSS1","Hrs",4,null,372.3390804672,null,372.3390804672,null,4,null,372.3390804672,null,372.3390804672,{"$nulls":4},372.3390804672,1,{"$nulls":4},0.35,130.31867816352,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02260","1.04.03.06.02","CBB4030602","9242670","Measure and Fiducialize Quadrupole - 14","2007-08-07","2007-08-08","S","C","SL_PHSS1","Hrs",4,null,372.3390804672,null,372.3390804672,null,4,null,372.3390804672,null,372.3390804672,{"$nulls":4},372.3390804672,1,{"$nulls":4},0.35,130.31867816352,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02260","1.04.03.06.02","CBB4030602","9242670","Measure and Fiducialize Quadrupole - 14","2007-08-07","2007-08-08","S","C","SL_MES1","Hrs",4,null,321.169674672,null,321.169674672,null,4,null,321.169674672,null,321.169674672,{"$nulls":4},321.169674672,1,{"$nulls":4},0.35,112.40938613519998,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02320","1.04.03.06.02","CBB4030602","9242670","Measure and Fiducialize Quadrupole - 17","2007-08-15","2007-08-16","S","C","SL_MES1","Hrs",4,null,321.169674672,null,321.169674672,null,4,null,321.169674672,null,321.169674672,{"$nulls":4},321.169674672,1,{"$nulls":4},0.35,112.40938613519998,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02360","1.04.03.06.02","CBB4030602","9242670","Magnetic Measure and Fiducialize Quadrupole - 19","2007-08-21","2007-08-21","S","C","SL_MFAT1","Hrs",8,null,689.4720000000001,null,689.4720000000001,null,8,null,689.4720000000001,null,689.4720000000001,{"$nulls":4},689.4720000000001,1,{"$nulls":4},0.35,241.3152,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02410","1.04.03.06.02","CBB4030602","9242670","Magnetic Measure and Fiducialize Quadrupole - 22","2007-08-24","2007-08-24","S","C","SL_MFAT1","Hrs",8,null,689.4720000000001,null,689.4720000000001,null,8,null,689.4720000000001,null,689.4720000000001,{"$nulls":4},689.4720000000001,1,{"$nulls":4},0.35,241.3152,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02430","1.04.03.06.02","CBB4030602","9242670","Magnetic Measure and Fiducialize Quadrupole - 23","2007-08-27","2007-08-27","S","C","SL_PHS1","Hrs",20,null,1462.7606732639997,null,1462.7606732639997,null,20,null,1462.7606732639997,null,1462.7606732639997,{"$nulls":4},1462.7606732639997,1,{"$nulls":4},0.35,511.96623564239985,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02510","1.04.03.06.02","CBB4030602","9242670","Magnetic Measure and Fiducialize Quadrupole - 27","2007-08-31","2007-08-31","S","C","SL_PHS1","Hrs",20,null,1462.7606732639997,null,1462.7606732639997,null,20,null,1462.7606732639997,null,1462.7606732639997,{"$nulls":4},1462.7606732639997,1,{"$nulls":4},0.35,511.96623564239985,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02530","1.04.03.06.02","CBB4030602","9242670","Magnetic Measure and Fiducialize Quadrupole - 28","2007-09-04","2007-09-04","S","C","SL_PHSS1","Hrs",4,null,372.3390804672,null,372.3390804672,null,4,null,372.3390804672,null,372.3390804672,{"$nulls":4},372.3390804672,1,{"$nulls":4},0.35,130.31867816352,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02610","1.04.03.06.02","CBB4030602","9242670","Magnetic Measure and Fiducialize Quadrupole - 32","2007-09-10","2007-09-10","S","C","SL_PHSS1","Hrs",4,null,372.3390804672,null,372.3390804672,null,4,null,372.3390804672,null,372.3390804672,{"$nulls":4},372.3390804672,1,{"$nulls":4},0.35,130.31867816352,1.25,1.1,3,4,"4B"]
["1","04","03","06","02","02","UN36_02610","1.04.03.06.02","CBB4030602","9242670","Magnetic Measure and Fiducialize Quadrupole - 32","2007-09-10","2007-09-10","S","C","SL_MES1","Hrs",4,null,321.169674672,null,321.169674672,null,4,null,321.169674672,null,321.169674672,{"$nulls":4},321.169674672,1,{"$nulls":4},0.35,112.40938613519998,1.25,1.1,3,4,"4B"]
["1","04","03","06","03","01",{"$nulls":4},"Stretched Wire System                                       ",{"$nulls":6},4366,391100,391734.8196321929,419085.3488,810820.168432193,null,2828.76,338100,262395.6250161413,363541.3488,625936.9738161413,0,null,7711.883878430098,null,511854.9854031264,null,106370.10453458472,null,0,null,null,192838.37833403534]
["1","04","03","06","03","01","UN601_0733","1.04.03.06.03","CBE4030603","9242671","Commissioning of WPM at U-Hall","2008-04-01","2008-06-30","S","C","SL_MES1","Hrs",120,null,9885.60258640416,null,9885.60258640416,null,120,null,9885.60258640416,null,9885.60258640416,{"$nulls":6},9885.60258640416,1,null,null,0.25,2471.40064660104,1.15,1.1,3,5,"4B"]
["1","04","03","06","03","01","UN601_R701","1.04.03.06.03","CBE4030603","9242671","RCV: RF Signal Processing","2007-07-02","2007-07-02","S","C","SL_MSEG1","$$",null,19000,null,20429.712,20429.712,null,null,19000,null,20429.712,20429.712,{"$nulls":4},20429.712,1,{"$nulls":4},0.35,7150.3992,1.25,1.1,4,3,"4B"]
["1","04","03","06","03","01","UN601_R715","1.04.03.06.03","CBE4030603","9242671","RCV: Crates","2007-07-02","2007-07-02","S","C","SL_MSEG1","$$",null,23000,null,24730.703999999998,24730.703999999998,null,null,23000,null,24730.703999999998,24730.703999999998,{"$nulls":4},24730.703999999998,1,{"$nulls":4},0.35,8655.746399999998,1.25,1.1,4,3,"4B"]
["1","04","03","06","03","02","UN601_E415","1.04.03.06.03","CBE4030603","9242671","Specify Support System ETC","2006-10-30","2007-02-13","S","C","SL_ME1","Hrs",2,null,199.73954222639998,null,199.73954222639998,null,0,null,0,null,0,{"$nulls":10},0.1,0,1.1,1,2,2,"4B"]
["1","04","03","06","03","02","UN601_P430","1.04.03.06.03","CBE4030603","9242671","PP: Capacitive/Acoustic Sensors","2006-11-01","2006-11-01","S","C","SL_MSEG1","$$",null,36000,null,38708.928,38708.928,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,2,3,"4B"]
["1","04","03","06","03","03","UN601_R335","1.04.03.06.03","CBE4030603","9242671","RCV: Wire Reference Fiducials","2006-10-03","2006-10-03","S","C","SL_MSEG1","$$",null,13500,null,14515.848,14515.848,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.2,1.1,3,3,"4B"]
["1","04","03","06","03","03","UN601_R350","1.04.03.06.03","CBE4030603","9242671","RCV: Portable HLS","2006-11-14","2006-11-14","S","C","SL_MSEG1","$$",null,20250,null,21773.772,21773.772,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.2,1.1,3,3,"4B"]
["1","04","03","08","02","","UN38_00030","1.04.03.08.02","CCB4030802","9242672","Factory Accept Testing 1st Art - Fixed Support","2007-07-20","2007-07-24","A","C","AN_ME1","Hrs",24,null,2652.0378902236807,null,2652.0378902236807,null,24,null,2652.0378902236807,null,2652.0378902236807,{"$nulls":4},2652.0378902236807,1,{"$nulls":4},0.15,397.8056835335521,1.1,1.05,7,3,"4A"]
["1","04","03","08","02","","UN38_00045","1.04.03.08.02","CCB4030802","9242672","Evaluate 1st Article Fixed Support","2007-08-02","2007-08-30","A","C","AA_MSSF","$$",null,60000,null,60000,60000,null,null,60000,null,60000,60000,{"$nulls":4},60000,1,{"$nulls":4},0.15,9000,1.1,1.05,7,3,"4A"]
["1","04","03","08","02","","UN38_00115","1.04.03.08.02","CCB4030802","9242672","RCV: 2 Fixed Supports","2007-10-10","2007-10-10","A","C","AA_MSSF","$$",null,32000,null,32000,32000,null,null,32000,null,32000,32000,{"$nulls":6},32000,1,null,null,0.25,8000,1.15,1.1,4,3,"4A"]
["1","04","03","08","02","","UN38_00150","1.04.03.08.02","CCB4030802","9242672","RCV: 2 Fixed Supports","2007-11-30","2007-11-30","A","C","AA_MSSF","$$",null,32000,null,32000,32000,null,null,32000,null,32000,32000,{"$nulls":6},32000,1,null,null,0.25,8000,1.15,1.1,4,3,"4A"]
["1","04","03","08","07","  ",{"$nulls":4},"Earthquake Bracing                                          ",{"$nulls":6},16,24000,1768.0252601491204,24624,26392.02526014912,null,16,24000,1768.0252601491204,24624,26392.02526014912,0,null,0,null,26392.02526014912,null,0,null,0,null,null,5278.405052029824]
["1","04","03","08","08","  ",{"$nulls":4},"Controls and Software                                       "]
["1","04","04","02","02","","UN42_00248","1.04.04.02.02","CBB4040202","9242675","Oversee Construction of Vacuum Chamber","2007-02-06","2007-10-03",null,"C","AN_MFMS1","Hrs",328,null,33456.402811657885,null,33456.402811657885,null,328,null,33456.402811657885,null,33456.402811657885,{"$nulls":4},33176.43291365238,0.99,279.9698980055053,0.01,null,null,0.2,6691.280562331577,1.1,1.1,3,3,"4A"]
["1","04","04","02","02","","UN42_00249","1.04.04.02.02","CBB4040202","9242675","REC:  Production Group 1 (7)","2007-04-06","2007-04-06",null,"C","AA_MSSC1","$$",null,113456,null,116405.856,116405.856,null,null,113456,null,116405.856,116405.856,{"$nulls":4},116405.856,1,{"$nulls":4},0.2,23281.1712,1.1,1.1,3,3,"4A"]
["1","04","04","02","02","","UN42_00257","1.04.04.02.02","CBB4040202","9242675","Ship Second Lot of Chamber to SLAC (7)","2007-06-05","2007-06-12",null,"C","AN_MSEG1","$$",null,3000,null,3078,3078,null,null,3000,null,3078,3078,{"$nulls":4},3078,1,{"$nulls":4},0.2,615.6,1.1,1.1,3,3,"4A"]
["1","04","04","02","02","","UN42_00262","1.04.04.02.02","CBB4040202","9242675","REC:  Production Group 4 (6)","2007-08-17","2007-08-17",null,"C","AA_MSSC1","$$",null,94752,null,97215.552,97215.552,null,null,94752,null,97215.552,97215.552,{"$nulls":4},97215.552,1,{"$nulls":4},0.2,19443.1104,1.1,1.1,3,3,"4A"]
["1","04","04","02","02","","UN42_00266","1.04.04.02.02","CBB4040202","9242675","REC:  Production Group 5 (6)","2007-10-03","2007-10-03",null,"C","AA_MSSC1","$$",null,94752,null,99743.15635199999,99743.15635199999,null,null,94752,null,99743.15635199999,99743.15635199999,{"$nulls":6},99743.15635199999,1,null,null,0.2,19948.6312704,1.1,1.1,3,3,"4A"]
["1","04","04","02","02","","UN42_00273","1.04.04.02.02","CBB4040202","9242675","Package Chamber Supports for Shipment (33+7)","2007-07-16","2007-07-20",null,"C","AN_MVE1","Hrs",24,null,2652.0378902236807,null,2652.0378902236807,null,24,null,2652.0378902236807,null,2652.0378902236807,{"$nulls":4},2652.0378902236807,1,{"$nulls":4},0.2,530.4075780447362,1.1,1.1,3,3,"4A"]
["1","04","04","02","03","","UN42DR0218","1.04.04.02.03","CBB4040203","9242676","Design weld tooling ETC","2006-08-01","2006-08-30",4,"C","AN_MDD1","Hrs",12,null,758.7973015200001,null,758.7973015200001,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,3,2,"4A"]
["1","04","04","02","03","","UN42_D266","1.04.04.02.03","CBB4040203","9242676","Procure Prototype UN chamber tooling","2006-08-31","2006-09-05",41,"C","AN_MVE1","Hrs",6,null,646.2080629200001,null,646.2080629200001,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"4A"]
["1","04","04","02","03","","UN42_DR217","1.04.04.02.03","CBB4040203","9242676","Machine Strongback - Proto A","2006-08-31","2006-09-21",null,"C","AN_MVE1","Hrs",16,null,1723.2215011200003,null,1723.2215011200003,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"4A"]
["1","04","04","02","03","","UN42_DR220","1.04.04.02.03","CBB4040203","9242676","Proto A-Fab Sheet and End Piece","2006-08-31","2006-09-21",null,"C","AN_MSEG1","$$",null,3000,null,3000,3000,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"4A"]
["1","04","04","02","03","","UN42_DR223","1.04.04.02.03","CBB4040203","9242676","Proto A-Weld Flanges to Chamber","2006-10-27","2006-10-31",null,"C","AN_MFMS1","Hrs",16,null,1631.6646428160002,null,1631.6646428160002,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"4A"]
["1","04","04","02","03","","UN42_DR228","1.04.04.02.03","CBB4040203","9242676","Proto B-Laser Seam Weld","2006-10-03","2006-10-24",null,"C","AN_MSEG1","$$",null,5000,null,5130,5130,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"4A"]
["1","04","04","02","03","","UN42_DR234","1.04.04.02.03","CBB4040203","9242676","Machine Strongback-Proto B","2006-08-31","2006-10-05",null,"C","AN_MVE1","Hrs",16,null,1728.3419307233282,null,1728.3419307233282,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"4A"]
["1","04","04","03","01","","UN43_00200","1.04.04.03.01","CBC4040301","9242250","Quality Assurance Prtp Bel Mod","2006-08-01","2006-08-07","A","C","AN_MVE1","Hrs",8,null,861.6107505600002,null,861.6107505600002,null,0,null,0,null,0,{"$nulls":10},0.15,0,1.05,1.1,3,3,"4A"]
["1","04","04","03","01","","UN43_00230","1.04.04.03.01","CBC4040301","9242250","Review and Report Prtp Bel Mod","2006-08-15","2006-08-21","A","C","AN_PHS1","Hrs",8,null,861.6107505600002,null,861.6107505600002,null,0,null,0,null,0,{"$nulls":10},0.15,0,1.05,1.1,3,3,"4A"]
["1","04","04","03","02","  ",{"$nulls":4},"Production Bellows Module                                   ",{"$nulls":6},632,169572,53220.837112979294,174007.54799999998,227228.3851129793,null,441.2,169572,38110.527637895255,174007.54799999998,212118.0756378952,0,null,1321.6696386712993,null,198663.83059574716,null,12132.575403476761,null,0,null,null,42423.61512757907]
["1","04","04","03","02","","UN43_00355","1.04.04.03.02","CBB4040302","9242677","Standard Bellows Module (47) Support","2006-11-07","2006-11-08","A","C","AN_MVE1","Hrs",8,null,884.0126300745602,null,884.0126300745602,null,8,null,884.0126300745602,null,884.0126300745602,{"$nulls":4},884.0126300745602,1,{"$nulls":4},0.2,176.80252601491205,1.1,1.1,3,3,"4A"]
["1","04","04","03","02","","UN43_00410","1.04.04.03.02","CBB4040302","9242677","REC:  First Lot Standard Bellows Module (4)","2006-11-09","2007-01-16","A","C","AA_MSSC1","$$",null,14304,null,14675.904,14675.904,null,null,14304,null,14675.904,14675.904,{"$nulls":4},14675.904,1,{"$nulls":4},0.2,2935.1808,1.1,1.1,3,3,"4A"]
["1","04","04","03","02","","UN43_00424","1.04.04.03.02","CBB4040302","9242677","Bake 1st Lot Std Bel Mod","2007-11-16","2007-11-26","A","C","AN_MVE1","Hrs",8,null,906.9969584564986,null,906.9969584564986,null,8,null,906.9969584564986,null,906.9969584564986,{"$nulls":6},906.9969584564986,1,null,null,0.2,181.39939169129974,1.1,1.1,3,3,"4A"]
["1","04","04","03","02","","UN43_00510","1.04.04.03.02","CBB4040302","9242677","Clean 2nd Lot Std Bel Mod","2007-04-13","2007-04-18","A","C","AN_MFAT1","Hrs",12,null,778.52603135952,null,778.52603135952,null,12,null,778.52603135952,null,778.52603135952,{"$nulls":4},778.52603135952,1,{"$nulls":4},0.2,155.705206271904,1.1,1.1,3,3,"4A"]
["1","04","04","03","02","","UN43_00550","1.04.04.03.02","CBB4040302","9242677","Ship 2nd Lot  (21) Std Bel Mod to SLAC","2007-05-02","2007-05-08","A","C","AN_MSEG1","$$",null,500,null,513,513,null,null,500,null,513,513,{"$nulls":4},513,1,{"$nulls":4},0.2,102.60000000000001,1.1,1.1,3,3,"4A"]
["1","04","04","03","02","","UN43_00553","1.04.04.03.02","CBB4040302","9242677","Assembly Test Rem Std Bel Mod","2007-06-05","2007-06-11","A","C","AN_MFAT1","Hrs",16,null,1038.03470847936,null,1038.03470847936,null,16,null,1038.03470847936,null,1038.03470847936,{"$nulls":4},1038.03470847936,1,{"$nulls":4},0.2,207.60694169587202,1.1,1.1,3,3,"4A"]
["1","04","04","03","02","","UN43_00560","1.04.04.03.02","CBB4040302","9242677","Transmit Std Bel Mod Design & Drawings to SLA","2007-12-06","2007-12-12","A","C","AN_MDD1","Hrs",16,null,1065.0236108998233,null,1065.0236108998233,null,16,null,1065.0236108998233,null,1065.0236108998233,{"$nulls":6},1065.0236108998233,1,null,null,0.2,213.0047221799647,1.1,1.1,3,2,"4A"]
["1","04","04","04","","","UN44_00426","1.04.04.04","CBA40404",null,"Support SUT Long Term Test FY07","2007-05-09","2007-10-30","A","C","AN_MVE1","Hrs",18,null,1997.6475408109875,null,1997.6475408109875,null,3.6,null,443.92167573577495,null,443.92167573577495,{"$nulls":4},369.93472977981247,0.83,73.98694595596248,0.17,null,null,0.1,44.392167573577495,1.05,1.05,1,3,"4A"]
["1","04","04","05","","","UN45_00322","1.04.04.05","CBA40405","9242508","REC: SDB Pump Manifold (23)","2006-11-03","2007-01-10","A","C","AA_MSSC1","$$",null,10068,null,10329.768,10329.768,null,null,10068,null,10329.768,10329.768,{"$nulls":4},10329.768,1,{"$nulls":4},0.15,1549.4651999999999,1.1,1.05,3,3,"4A"]
["1","04","04","05","","","UN45_00339","1.04.04.05","CBA40405","9242508","QA Production Lot SDB","2007-01-11","2007-01-24","A","C","AN_MFMS1","Hrs",24,null,2447.4969642240003,null,2447.4969642240003,null,24,null,2447.4969642240003,null,2447.4969642240003,{"$nulls":4},2447.4969642240003,1,{"$nulls":4},0.15,367.1245446336,1.1,1.05,3,3,"4A"]
["1","04","04","05","","","UN45_00390","1.04.04.05","CBA40405","9242508","Prepare Short Diagnostic Break for Shipment","2007-11-27","2007-12-03","A","C","AN_MFAT1","Hrs",24,null,1597.535416349735,null,1597.535416349735,null,24,null,1597.535416349735,null,1597.535416349735,{"$nulls":6},1597.535416349735,1,null,null,0.15,239.63031245246023,1.1,1.05,3,3,"4A"]
["1","04","04","06","","","UN45_00041","1.04.04.06","CBA40406","9242509","Pump Support Bid Package","2006-12-06","2006-12-12","A","C","AN_MVE1","Hrs",16,null,1768.0252601491204,null,1768.0252601491204,null,12,null,1326.0189451118404,null,1326.0189451118404,{"$nulls":4},1326.0189451118404,1,{"$nulls":4},0.15,198.90284176677605,1.1,1.05,3,3,"4A"]
["1","04","04","06","","","UN46_00200","1.04.04.06","CBA40406","9242509","Bid Process LDB","2006-12-13","2007-01-25","A","C","AN_MVE1","Hrs",16,null,1768.0252601491204,null,1768.0252601491204,null,12,null,1326.0189451118404,null,1326.0189451118404,{"$nulls":4},1326.0189451118404,1,{"$nulls":4},0.15,198.90284176677605,1.1,1.05,3,3,"4A"]
["1","04","04","06","","","UN46_00325","1.04.04.06","CBA40406","9242509","LDB Ion Pump Support Award Effort","2007-01-30","2007-01-31","A","C","AN_MVE1","Hrs",8,null,884.0126300745602,null,884.0126300745602,null,8,null,884.0126300745602,null,884.0126300745602,{"$nulls":4},884.0126300745602,1,{"$nulls":4},0.15,132.601894511184,1.1,1.05,3,3,"4A"]
["1","04","04","06","","","UN46_00440","1.04.04.06","CBA40406","9242509","Bake LDB","2007-11-16","2007-11-26","A","C","AN_MVE1","Hrs",8,null,906.9969584564986,null,906.9969584564986,null,8,null,906.9969584564986,null,906.9969584564986,{"$nulls":6},906.9969584564986,1,null,null,0.15,136.0495437684748,1.1,1.05,3,3,"4A"]
["1","04","04","06","","","UN46_00500","1.04.04.06","CBA40406","9242509","Transmit Design and Drawings to SLAC","2007-12-18","2008-01-02","A","C","AN_ME1","Hrs",8,null,906.9969584564986,null,906.9969584564986,null,8,null,906.9969584564986,null,906.9969584564986,{"$nulls":6},906.9969584564986,1,null,null,0.15,136.0495437684748,1.1,1.05,3,2,"4A"]
["1","04","04","09","","","UN49_00175","1.04.04.09","CBB40409","9242512","Heater Award Effort","2007-08-13","2007-08-15","A","C","AN_MVE1","Hrs",8,null,884.0126300745602,null,884.0126300745602,null,8,null,884.0126300745602,null,884.0126300745602,{"$nulls":4},884.0126300745602,1,{"$nulls":4},0.2,176.80252601491205,1.1,1.1,3,3,"4A"]
["1","04","04","09","","","UN49_00190","1.04.04.09","CBB40409","9242512","AWARD: Turbo Pump","2007-08-13","2007-08-15","A","C","AN_AW1","$$",null,16000,null,16416,16416,null,null,16000,null,16416,16416,{"$nulls":4},16416,1,{"$nulls":4},0.2,3283.2000000000003,1.1,1.1,3,3,"4A"]
["1","04","05","02","01","  ",{"$nulls":4},"ULD Test Station                                            "]
["1","04","05","02","09","  ",{"$nulls":4},"ULD Design & Integration                                    "]
["1","04","05","05","01","","UN505_1090","1.04.05.05.01","CBB4050501",null,"Machine Three Bodies","2006-08-09","2006-09-20","A","C","AN_MSEG1","$$",null,52000,null,52000,52000,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,7,3,"4A"]
["1","04","05","05","01","","UN505_1100","1.04.05.05.01","CBB4050501",null,"Braze Three Bodies","2006-09-28","2006-10-04","A","C","AN_MFMS1","Hrs",32,null,3221.981058816,null,3221.981058816,null,17.6,null,1812.3643455840001,null,1812.3643455840001,null,null,906.1821727920001,0.5,906.1821727920001,0.5,{"$nulls":4},0.2,362.47286911680004,1.1,1.1,7,3,"4A"]
["1","04","05","05","01","","UN505_1201","1.04.05.05.01","CBB4050501",null,"Procure and Fab Linac Equipment ETC","2006-08-01","2006-08-30","A","C","AN_MSEG1","$$",null,8800,null,8800,8800,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"4A"]
["1","04","05","05","01","","UN505_1210","1.04.05.05.01","CBB4050501",null,"Assemble Linac Equipment","2006-10-10","2006-10-30","A","C","AN_CT1","Hrs",40,null,2595.0867711984,null,2595.0867711984,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,3,3,"4A"]
["1","04","05","05","02","","UN505_2041","1.04.05.05.02","CBB4050502",null,"Update Down Converter and LO Spec ETC","2006-08-01","2006-08-30","A","C","AN_EE1","Hrs",4,null,430.8053752800001,null,430.8053752800001,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,3,2,"4A"]
["1","04","05","05","02","","UN505_2050","1.04.05.05.02","CBB4050502",null,"Bench Test & Tune (3) DC and LO","2006-08-18","2006-09-08","A","C","AN_EE1","Hrs",40,null,4308.0537528,null,4308.0537528,null,16,null,1723.2215011200003,null,1723.2215011200003,null,null,1723.2215011200003,1,{"$nulls":6},0.2,344.64430022400006,1.1,1.1,1,3,"4A"]
["1","04","05","05","03","","UN505_3006","1.04.05.05.03","CBB4050503",null,"LTU BPM Preliminary Prod Design","2006-10-19","2006-11-01","A","C","AN_MDD1","Hrs",40,null,2595.0867711984,null,2595.0867711984,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.1,1.1,3,2,"4A"]
["1","04","05","05","03","","UN505_3017","1.04.05.05.03","CBB4050503",null,"LTU BPM Final Design","2006-11-27","2006-12-08","A","C","AN_MDD1","Hrs",40,null,2595.0867711984,null,2595.0867711984,null,40,null,2595.0867711984,null,2595.0867711984,{"$nulls":4},2595.0867711984,1,{"$nulls":4},0.2,519.01735423968,1.1,1.1,3,2,"4A"]
["1","04","05","05","03","","UN505_3028","1.04.05.05.03","CBB4050503",null,"Prepare Bid Waveguide","2006-12-11","2006-12-15","A","C","AN_EE1","Hrs",8,null,884.0126300745602,null,884.0126300745602,null,8,null,884.0126300745602,null,884.0126300745602,{"$nulls":4},884.0126300745602,1,{"$nulls":4},0.2,176.80252601491205,1.1,1.1,3,3,"4A"]
["1","04","05","05","03","","UN505_3056","1.04.05.05.03","CBB4050503",null,"AWARD: LTU BPM Brazements (2)","2007-01-10","2007-01-12","A","C","AN_AW1","$$",null,16000,null,16416,16416,null,null,16000,null,16416,16416,{"$nulls":4},16416,1,{"$nulls":4},0.2,3283.2000000000003,1.1,1.1,3,3,"4A"]
["1","04","05","05","03","","UN505_3068","1.04.05.05.03","CBB4050503",null,"REC: Undulator Local Oscillator (37)","2007-01-15","2007-01-17","A","C","AN_ME1","Hrs",8,null,884.0126300745602,null,884.0126300745602,null,8,null,884.0126300745602,null,884.0126300745602,{"$nulls":4},884.0126300745602,1,{"$nulls":4},0.2,176.80252601491205,1.1,1.1,3,3,"4A"]
["1","04","05","05","03","","UN505_3090","1.04.05.05.03","CBB4050503",null,"REC: Support & Alignment Mechanism (36)","2007-01-15","2007-03-23","A","C","AA_MSEG1","$$",null,90000,null,92340,92340,null,null,90000,null,92340,92340,{"$nulls":4},92340,1,{"$nulls":4},0.2,18468,1.1,1.1,3,3,"4A"]
["1","04","05","05","03","","UN505_3115","1.04.05.05.03","CBB4050503",null,"REC: Copper Body Brazement (34)","2007-05-10","2007-08-08","A","C","AA_MSEG1","$$",null,272000,null,279072,279072,null,null,272000,null,279072,279072,{"$nulls":4},279072,1,{"$nulls":4},0.2,55814.4,1.1,1.1,3,3,"4A"]
["1","04","05","05","03","","UN505_3121","1.04.05.05.03","CBB4050503",null,"REC: LTU BPMs (2) - Effort Support","2007-01-15","2007-03-23","A","C","AN_EE1","Hrs",4,null,442.0063150372801,null,442.0063150372801,null,4,null,442.0063150372801,null,442.0063150372801,{"$nulls":4},442.0063150372801,1,{"$nulls":4},0.2,88.40126300745602,1.1,1.1,3,3,"4A"]
["1","04","05","05","03","","UN505_3125","1.04.05.05.03","CBB4050503",null,"REC:  Undulator Waveguide (35)","2007-01-15","2007-03-19",null,"C","AA_MSEG1","$$",null,120600,null,123735.6,123735.6,null,null,120600,null,123735.6,123735.6,{"$nulls":4},123735.6,1,{"$nulls":4},0.2,24747.120000000003,1.1,1.1,3,3,"4A"]
["1","04","05","05","03","","UN505_3132","1.04.05.05.03","CBB4050503",null,"Pack/Ship 2nd Lot(11)Undulator RFBPM to SLAC","2007-08-10","2007-08-16","A","C","AN_ME1","Hrs",8,null,884.0126300745602,null,884.0126300745602,null,8,null,884.0126300745602,null,884.0126300745602,{"$nulls":4},884.0126300745602,1,{"$nulls":4},0.2,176.80252601491205,1.1,1.1,3,3,"4A"]
["1","04","05","05","03","","UN505_3A58","1.04.05.05.03","CBB4050503",null,"AWARD: LTU BPM Waveguide (2)","2007-01-10","2007-01-12","A","C","AN_AW1","$$",null,6700,null,6874.2,6874.2,null,null,6700,null,6874.2,6874.2,{"$nulls":4},6874.2,1,{"$nulls":4},0.2,1374.8400000000001,1.1,1.1,3,3,"4A"]
["1","04","05","06","","","UN506_0085","1.04.05.06","CBB40506",null,"Prepare Acceptance Criteria List","2006-08-01","2006-08-28","A","C","AN_ME1","Hrs",16,null,1723.2215011200003,null,1723.2215011200003,null,0,null,0,null,0,{"$nulls":10},0.15,0,1.05,1.1,1,2,"4A"]
["1","04","05","06","","","UN506_0117","1.04.05.06","CBB40506",null,"REC: Beam Finder Wire Tooling","2006-10-18","2006-10-18","A","C","AN_ME1","Hrs",8,null,884.0126300745602,null,884.0126300745602,null,6.4,null,707.2101040596482,null,707.2101040596482,{"$nulls":4},707.2101040596482,1,{"$nulls":4},0.15,106.08151560894723,1.05,1.1,3,3,"4A"]
["1","04","05","06","","","UN506_0132","1.04.05.06","CBB40506",null,"REC:  Machine Components (10)","2006-12-20","2007-02-14",null,"C","AA_MSEG1","$$",null,95770,null,98260.02,98260.02,null,null,95770,null,98260.02,98260.02,{"$nulls":4},98260.02,1,{"$nulls":4},0.15,14739.003,1.05,1.1,3,3,"4A"]
["1","04","05","08","","","UN508_0021","1.04.05.08","CBB40508","9242513","Preliminary Design - Beam Loss Mon ETC","2006-08-01","2006-08-30","A","C","AN_PHS1","Hrs",16,null,1723.2215011200003,null,1723.2215011200003,null,1.6,null,172.32215011200003,null,172.32215011200003,null,null,172.32215011200003,1,{"$nulls":6},0.3,51.69664503360001,1.15,1.15,4,2,"4A"]
["1","04","05","08","","","UN508_0021","1.04.05.08","CBB40508","9242513","Preliminary Design - Beam Loss Mon ETC","2006-08-01","2006-08-30","A","C","AN_EE1","Hrs",26,null,2800.2349393200006,null,2800.2349393200006,null,2.6,null,280.02349393200006,null,280.02349393200006,null,null,280.02349393200006,1,{"$nulls":6},0.3,84.00704817960002,1.15,1.15,4,2,"4A"]
["1","04","05","08","","","UN508_0189","1.04.05.08","CBB40508","9242513","Put Procurement Packages Together","2007-01-22","2007-02-09",null,"C","AN_EE1","Hrs",113,null,12486.678399803162,null,12486.678399803162,null,113,null,12486.678399803162,null,12486.678399803162,{"$nulls":4},12486.678399803162,1,{"$nulls":4},0.3,3746.0035199409485,1.15,1.15,4,3,"4A"]
["1","04","05","08","","","UN508_0200","1.04.05.08","CBB40508","9242513","Assemble Cerenkov Fiber Components","2007-04-24","2007-05-21",null,"C","AN_MFAT1","Hrs",107,null,6941.85711295572,null,6941.85711295572,null,107,null,6941.85711295572,null,6941.85711295572,{"$nulls":4},6941.85711295572,1,{"$nulls":4},0.3,2082.557133886716,1.15,1.15,4,3,"4A"]
["1","04","05","08","","","UN508_0204","1.04.05.08","CBB40508","9242513","Ship to SLAC","2007-05-22","2007-06-12",null,"C","AN_MSEG1","$$",null,10000,null,10260,10260,null,null,10000,null,10260,10260,{"$nulls":4},10260,1,{"$nulls":4},0.3,3078,1.15,1.15,4,3,"4A"]
["1","04","06","01","01","","UN601_0780","1.04.06.01.01","CBB4060101","9242687","HLS Pipe Installation & Welding","2008-03-13","2008-03-13","S","C","SL_TMUW1","Hrs",24,null,1868.1377794559994,null,1868.1377794559994,null,24,null,1868.1377794559994,null,1868.1377794559994,{"$nulls":6},1868.1377794559994,1,null,null,0.35,653.8482228095997,1.25,1.1,4,4,"4B"]
["1","04","06","01","01","","UN601_0930","1.04.06.01.01","CBB4060101","9242687","HLS Pipe Installation & Welding","2008-03-17","2008-03-17","S","C","SL_TMUW1","Hrs",24,null,1868.1377794559994,null,1868.1377794559994,null,24,null,1868.1377794559994,null,1868.1377794559994,{"$nulls":6},1868.1377794559994,1,null,null,0.35,653.8482228095997,1.25,1.1,4,4,"4B"]
["1","04","06","01","01","","UN601_1005","1.04.06.01.01","CBB4060101","9242687","Pedestal Mover Set Up: 31-36","2008-01-15","2008-01-15","S","C","SL_MFAT1","Hrs",16,null,1414.796544,null,1414.796544,null,16,null,1414.796544,null,1414.796544,{"$nulls":6},1414.796544,1,null,null,0.35,495.17879039999997,1.25,1.1,4,4,"4B"]
["1","04","06","01","01","","UN601_1105","1.04.06.01.01","CBB4060101","9242687","Pedestal Mover Set Up: 43-48","2008-01-11","2008-01-11","S","C","SL_MFAT1","Hrs",16,null,1414.796544,null,1414.796544,null,16,null,1414.796544,null,1414.796544,{"$nulls":6},1414.796544,1,null,null,0.35,495.17879039999997,1.25,1.1,4,4,"4B"]
["1","04","06","01","01","","UN601_1235","1.04.06.01.01","CBB4060101","9242687","Pedestal Align: 7-12","2008-02-05","2008-02-06","S","C","SL_MES1","Hrs",40,null,3295.20086213472,null,3295.20086213472,null,40,null,3295.20086213472,null,3295.20086213472,{"$nulls":6},3295.20086213472,1,null,null,0.35,1153.320301747152,1.25,1.1,4,4,"4B"]
["1","04","06","01","01","","UN601_1280","1.04.06.01.01","CBB4060101","9242687","HLS Pipe Installation & Welding","2008-03-26","2008-03-26","S","C","SL_TMUW1","Hrs",24,null,1868.1377794559994,null,1868.1377794559994,null,24,null,1868.1377794559994,null,1868.1377794559994,{"$nulls":6},1868.1377794559994,1,null,null,0.35,653.8482228095997,1.25,1.1,4,4,"4B"]
["1","04","06","01","01","","UN601_1360","1.04.06.01.01","CBB4060101","9242687","Network Installation","2007-12-05","2007-12-11","S","C","SL_TMUO1","Hrs",80,null,6513.1169472,null,6513.1169472,null,80,null,6513.1169472,null,6513.1169472,{"$nulls":6},6513.1169472,1,null,null,0.25,1628.2792368,1.2,1.05,3,4,"4B"]
["1","04","06","01","01","","UN601_1395","1.04.06.01.01","CBB4060101","9242687","Set Studs","2008-01-09","2008-01-10","S","C","SL_TMUI1","Hrs",80,null,6227.125931519999,null,6227.125931519999,null,80,null,6227.125931519999,null,6227.125931519999,{"$nulls":6},6227.125931519999,1,null,null,0.35,2179.494076031999,1.25,1.1,4,4,"4B"]
["1","04","06","01","01","","UN601_1520","1.04.06.01.01","CBB4060101","9242687","Pedestal Transport & Install: 13-18","2008-02-05","2008-02-05","S","C","SL_TMUO1","Hrs",32,null,2605.24677888,null,2605.24677888,null,32,null,2605.24677888,null,2605.24677888,{"$nulls":6},2605.24677888,1,null,null,0.35,911.8363726079999,1.25,1.1,4,4,"4B"]
["1","04","06","01","01","","UN601_1590","1.04.06.01.01","CBB4060101","9242687","Quality Control","2008-02-20","2008-02-26","S","C","SL_MES1","Hrs",40,null,3295.20086213472,null,3295.20086213472,null,40,null,3295.20086213472,null,3295.20086213472,{"$nulls":6},3295.20086213472,1,null,null,0.25,823.80021553368,1.2,1.05,3,4,"4B"]
["1","04","06","01","01","","UN601_1655","1.04.06.01.01","CBB4060101","9242687","Install Girder - 03","2008-03-11","2008-03-11","S","C","SL_TMUO1","Hrs",16,null,1302.62338944,null,1302.62338944,null,16,null,1302.62338944,null,1302.62338944,{"$nulls":6},1302.62338944,1,null,null,0.35,455.91818630399996,1.25,1.1,4,4,"4B"]
["1","04","06","01","01","","UN601_1686","1.04.06.01.01","CBB4060101","9242687","Install Girder - 09","2008-03-13","2008-03-13","S","C","SL_TMUO1","Hrs",16,null,1302.62338944,null,1302.62338944,null,16,null,1302.62338944,null,1302.62338944,{"$nulls":6},1302.62338944,1,null,null,0.35,455.91818630399996,1.25,1.1,4,4,"4B"]
["1","04","06","01","01","","UN601_1702","1.04.06.01.01","CBB4060101","9242687","Align Girder - 12","2008-03-17","2008-03-17","S","C","SL_MES1","Hrs",16,null,1318.080344853888,null,1318.080344853888,null,16,null,1318.080344853888,null,1318.080344853888,{"$nulls":6},1318.080344853888,1,null,null,0.35,461.32812069886074,1.25,1.1,4,4,"4B"]
["1","04","06","01","01","","UN601_1711","1.04.06.01.01","CBB4060101","9242687","Install Girder - 14","2008-03-17","2008-03-17","S","C","SL_TMUO1","Hrs",16,null,1302.62338944,null,1302.62338944,null,16,null,1302.62338944,null,1302.62338944,{"$nulls":6},1302.62338944,1,null,null,0.35,455.91818630399996,1.25,1.1,4,4,"4B"]
["1","04","06","01","01","","UN601_1741","1.04.06.01.01","CBB4060101","9242687","Install Girder - 20","2008-03-19","2008-03-19","S","C","SL_TMUO1","Hrs",16,null,1302.62338944,null,1302.62338944,null,16,null,1302.62338944,null,1302.62338944,{"$nulls":6},1302.62338944,1,null,null,0.35,455.91818630399996,1.25,1.1,4,4,"4B"]
["1","04","06","01","01","","UN601_1757","1.04.06.01.01","CBB4060101","9242687","Align Girder - 23","2008-03-21","2008-03-21","S","C","SL_MES1","Hrs",16,null,1318.080344853888,null,1318.080344853888,null,16,null,1318.080344853888,null,1318.080344853888,{"$nulls":6},1318.080344853888,1,null,null,0.35,461.32812069886074,1.25,1.1,4,4,"4B"]
["1","04","06","01","01","","UN601_1787","1.04.06.01.01","CBB4060101","9242687","Align Girder - 29","2008-03-25","2008-03-25","S","C","SL_MES1","Hrs",16,null,1318.080344853888,null,1318.080344853888,null,16,null,1318.080344853888,null,1318.080344853888,{"$nulls":6},1318.080344853888,1,null,null,0.35,461.32812069886074,1.25,1.1,4,4,"4B"]
["1","04","06","01","01","","UN601_1806","1.04.06.01.01","CBB4060101","9242687","Install Girder - 33","2008-03-25","2008-03-25","S","C","SL_TMUO1","Hrs",16,null,1302.62338944,null,1302.62338944,null,16,null,1302.62338944,null,1302.62338944,{"$nulls":6},1302.62338944,1,null,null,0.35,455.91818630399996,1.25,1.1,4,4,"4B"]
["1","04","06","01","01","","UN601_1855","1.04.06.01.01","CBB4060101","9242687","HLS Electrical Tuning","2008-04-14","2008-04-18","S","C","SL_EE1","Hrs",40,null,3825.784051800479,null,3825.784051800479,null,40,null,3825.784051800479,null,3825.784051800479,{"$nulls":6},3825.784051800479,1,null,null,0.35,1339.0244181301675,1.25,1.1,4,4,"4B"]
["1","04","06","01","01","","UN601_2005","1.04.06.01.01","CBB4060101","9242687","Remeasurement(Laser Tracker,Level,Total Station)","2008-06-06","2008-06-12","S","C","SL_MES1","Hrs",160,null,13180.80344853888,null,13180.80344853888,null,160,null,13180.80344853888,null,13180.80344853888,{"$nulls":6},13180.80344853888,1,null,null,0.35,4613.281206988608,1.25,1.1,4,4,"4B"]
["1","04","06","02","","","UN462_0005","1.04.06.02","CBB40602","9242517","Install Racks in Alcoves/End Stations","2007-12-05","2007-12-11","S","C","SL_TMUE1","Hrs",480,null,47288.563914239996,null,47288.563914239996,null,480,null,47288.563914239996,null,47288.563914239996,{"$nulls":6},47288.563914239996,1,null,null,0.25,11822.140978559999,1.2,1.05,3,4,"4B"]
["1","04","06","02","","","UN462_0020","1.04.06.02","CBB40602","9242517","Install Rack Mount Equipment","2007-12-12","2008-01-03","S","C","SL_TMUE1","Hrs",80,null,7881.427319039999,null,7881.427319039999,null,80,null,7881.427319039999,null,7881.427319039999,{"$nulls":6},7881.427319039999,1,null,null,0.25,1970.3568297599998,1.2,1.05,3,4,"4B"]
["1","04","06","02","","","UN462_0125","1.04.06.02","CBB40602","9242517","Test Devices @ Undulator #31","2008-03-28","2008-03-28","S","C","SL_CE1","Hrs",8,null,927.7626059298431,null,927.7626059298431,null,8,null,927.7626059298431,null,927.7626059298431,{"$nulls":6},927.7626059298431,1,null,null,0.25,231.94065148246077,1.2,1.05,3,4,"4B"]
["1","04","06","02","","","UN462_0145","1.04.06.02","CBB40602","9242517","Test Devices @ Undulator #29","2008-03-27","2008-03-27","S","C","SL_CT1","Hrs",8,null,507.92369705447027,null,507.92369705447027,null,8,null,507.92369705447027,null,507.92369705447027,{"$nulls":6},507.92369705447027,1,null,null,0.25,126.98092426361757,1.2,1.05,3,4,"4B"]
["1","04","06","02","","","UN462_0175","1.04.06.02","CBB40602","9242517","Test Devices @ Undulator #26","2008-03-26","2008-03-26","S","C","SL_CT1","Hrs",8,null,507.92369705447027,null,507.92369705447027,null,8,null,507.92369705447027,null,507.92369705447027,{"$nulls":6},507.92369705447027,1,null,null,0.25,126.98092426361757,1.2,1.05,3,4,"4B"]
["1","04","06","02","","","UN462_0190","1.04.06.02","CBB40602","9242517","Connect Devices @ Undulator #24","2008-03-24","2008-03-24","S","C","SL_CE1","Hrs",8,null,927.7626059298431,null,927.7626059298431,null,8,null,927.7626059298431,null,927.7626059298431,{"$nulls":6},927.7626059298431,1,null,null,0.25,231.94065148246077,1.2,1.05,3,4,"4B"]
["1","04","06","02","","","UN462_0220","1.04.06.02","CBB40602","9242517","Connect Devices @ Undulator #21","2008-03-21","2008-03-21","S","C","SL_CE1","Hrs",8,null,927.7626059298431,null,927.7626059298431,null,8,null,927.7626059298431,null,927.7626059298431,{"$nulls":6},927.7626059298431,1,null,null,0.25,231.94065148246077,1.2,1.05,3,4,"4B"]
["1","04","06","02","","","UN462_0250","1.04.06.02","CBB40602","9242517","Connect Devices @ Undulator #18","2008-03-20","2008-03-20","S","C","SL_CE1","Hrs",8,null,927.7626059298431,null,927.7626059298431,null,8,null,927.7626059298431,null,927.7626059298431,{"$nulls":6},927.7626059298431,1,null,null,0.25,231.94065148246077,1.2,1.05,3,4,"4B"]
["1","04","06","02","","","UN462_0270","1.04.06.02","CBB40602","9242517","Connect Devices @ Undulator #16","2008-03-20","2008-03-20","S","C","SL_CT1","Hrs",8,null,507.92369705447027,null,507.92369705447027,null,8,null,507.92369705447027,null,507.92369705447027,{"$nulls":6},507.92369705447027,1,null,null,0.25,126.98092426361757,1.2,1.05,3,4,"4B"]
["1","04","06","02","","","UN462_0275","1.04.06.02","CBB40602","9242517","Test Devices @ Undulator #16","2008-03-21","2008-03-21","S","C","SL_CE1","Hrs",8,null,927.7626059298431,null,927.7626059298431,null,8,null,927.7626059298431,null,927.7626059298431,{"$nulls":6},927.7626059298431,1,null,null,0.25,231.94065148246077,1.2,1.05,3,4,"4B"]
["1","04","06","02","","","UN462_0305","1.04.06.02","CBB40602","9242517","Test Devices @ Undulator #13","2008-03-20","2008-03-20","S","C","SL_CE1","Hrs",8,null,927.7626059298431,null,927.7626059298431,null,8,null,927.7626059298431,null,927.7626059298431,{"$nulls":6},927.7626059298431,1,null,null,0.25,231.94065148246077,1.2,1.05,3,4,"4B"]
["1","04","06","02","","","UN462_0325","1.04.06.02","CBB40602","9242517","Test Devices @ Undulator #11","2008-03-19","2008-03-19","S","C","SL_CT1","Hrs",8,null,507.92369705447027,null,507.92369705447027,null,8,null,507.92369705447027,null,507.92369705447027,{"$nulls":6},507.92369705447027,1,null,null,0.25,126.98092426361757,1.2,1.05,3,4,"4B"]
["1","04","06","02","","","UN462_0355","1.04.06.02","CBB40602","9242517","Test Devices @ Undulator #8","2008-03-18","2008-03-18","S","C","SL_CT1","Hrs",8,null,507.92369705447027,null,507.92369705447027,null,8,null,507.92369705447027,null,507.92369705447027,{"$nulls":6},507.92369705447027,1,null,null,0.25,126.98092426361757,1.2,1.05,3,4,"4B"]
["1","04","06","02","","","UN462_0370","1.04.06.02","CBB40602","9242517","Connect Devices @ Undulator #6","2008-03-14","2008-03-14","S","C","SL_CE1","Hrs",8,null,927.7626059298431,null,927.7626059298431,null,8,null,927.7626059298431,null,927.7626059298431,{"$nulls":6},927.7626059298431,1,null,null,0.25,231.94065148246077,1.2,1.05,3,4,"4B"]
["1","04","06","02","","","UN462_0400","1.04.06.02","CBB40602","9242517","Connect Devices @ Undulator #3","2008-03-13","2008-03-13","S","C","SL_CT1","Hrs",8,null,507.92369705447027,null,507.92369705447027,null,8,null,507.92369705447027,null,507.92369705447027,{"$nulls":6},507.92369705447027,1,null,null,0.25,126.98092426361757,1.2,1.05,3,4,"4B"]
["1","04","06","02","","","UN462_0500","1.04.06.02","CBB40602","9242517","Test Devices Under Vacuum","2008-05-08","2008-05-08","S","C","SL_CT1","Hrs",8,null,507.92369705447027,null,507.92369705447027,null,8,null,507.92369705447027,null,507.92369705447027,{"$nulls":6},507.92369705447027,1,null,null,0.25,126.98092426361757,1.2,1.05,3,4,"4B"]
["1","04","06","04","","","UN43_00571","1.04.06.04","CCB40604","9242518","2nd Lot Std Bellows Arrive at SLAC","2007-05-09","2007-05-22","S","C","AN_SEE1","Hrs",8,null,884.0126300745602,null,884.0126300745602,null,8,null,884.0126300745602,null,884.0126300745602,{"$nulls":4},884.0126300745602,1,{"$nulls":4},0.25,221.00315751864005,1.2,1.05,3,4,"4A"]
["1","04","06","04","","","UN43_00572","1.04.06.04","CCB40604","9242518","Rem Std Bellows Arrive at SLAC","2007-07-09","2007-07-20","S","C","AN_SEE1","Hrs",8,null,884.0126300745602,null,884.0126300745602,null,8,null,884.0126300745602,null,884.0126300745602,{"$nulls":4},884.0126300745602,1,{"$nulls":4},0.25,221.00315751864005,1.2,1.05,3,4,"4A"]
["1","04","06","04","","","UN48_00620","1.04.06.04","CCB40604","9242518","Pump Down","2008-04-17","2008-04-30","S","C","SL_MFAT1","Hrs",24,null,2122.194816,null,2122.194816,null,24,null,2122.194816,null,2122.194816,{"$nulls":6},2122.194816,1,null,null,0.35,742.7681856,1.25,1.1,4,4,"4B"]
["1","04","06","04","","","UN48_00625","1.04.06.04","CCB40604","9242518","Leak Test","2008-05-01","2008-05-07","S","C","SL_MFAT1","Hrs",24,null,2122.194816,null,2122.194816,null,24,null,2122.194816,null,2122.194816,{"$nulls":6},2122.194816,1,null,null,0.35,742.7681856,1.25,1.1,4,4,"4B"]
["1","04","06","04","","","UN48_D202","1.04.06.04","CCB40604","9242518","Update Vacuum Chamber","2006-08-01","2006-08-21",null,"C","AN_MDD1","Hrs",32,null,2023.4594707200004,null,2023.4594707200004,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.25,1.1,4,4,"4A"]
["1","04","06","04","","","UN48_D211","1.04.06.04","CCB40604","9242518","Update Charge Monitor","2006-08-01","2006-08-14",null,"C","AN_MDD1","Hrs",16,null,1011.7297353600002,null,1011.7297353600002,null,0,null,0,null,0,{"$nulls":10},0.35,0,1.25,1.1,4,4,"4A"]
["1","05","01","01","01","","XT1111010","1.05.01.01.01","CAD50101","9242688","Management & Oversight - Jul-Sep06","2006-07-03","2006-09-29",null,"C","LL_ME1","Hrs",454,null,80173.78076923077,null,80173.78076923077,null,0,null,0,null,0,{"$nulls":10},0.17,0,1.15,1.02,4,1,"5A"]
["1","05","01","01","02","","XT1112020","1.05.01.01.02","CAD50102",null,"Teleconference/Comp","2006-07-03","2008-02-29",null,"C","LL_MSPS1","$$",null,5000,null,5709.760101980199,null,null,null,2500,null,2854.8800509900993,2854.8800509900993,null,null,423.9920867807078,0.15,1719.5234630550929,0.6,711.3645011542986,0.25,null,null,0.17,485.3296086683169,1.15,1.02,4,1,"5A"]
["1","05","01","01","03","","XT1113020","1.05.01.01.03","CAD50103","9242922","Management - Commission Coordinator - FY-06","2006-07-03","2006-09-29",null,"C","SL_EE1","Hrs",221,null,20079.736677,null,20079.736677,null,0,null,0,null,0,{"$nulls":10},0.17,0,1.15,1.02,7,1,"5A"]
["1","05","02","01","","","XT_521001","1.05.02.01","CAD50201","9242923","Controls Mgt - FY-06","2006-08-01","2006-10-27",null,"C","LL_CP1","Hrs",504,null,96305.29517984085,null,96305.29517984085,null,0,null,0,null,0,{"$nulls":10},0.2,0,1.15,1.05,4,2,"2H","S. Lewis"]
["1","05","03","01","","","XT1310030","1.05.03.01","CBD50301",null,"Procure Valve Pressure Manifolds (11)","2007-10-01","2007-11-27",null,"C","LL_MSPS1","$$",null,23100,null,26991.665316000002,26991.665316000002,null,null,23100,null,26991.665316000002,26991.665316000002,{"$nulls":6},26991.665316000002,1,null,null,0.19,5128.41641004,1.15,1.04,4,3,"5A"]
["1","05","03","02","","","XT1320010","1.05.03.02","CBD50302","9242693","Prepare Physics Specification - FEE Mech/Vac","2006-09-11","2006-10-31",null,"C","LL_ME1","Hrs",54,null,9684.851441538462,null,9684.851441538462,null,5.4,null,896.7455038461538,null,896.7455038461538,null,null,358.69820153846155,0.4,538.0473023076922,0.6,{"$nulls":4},0.25,224.18637596153846,1.2,1.05,4,2,"5A"]
["1","05","03","02","","","XT1320070","1.05.03.02","CBD50302","9242693","Preliminary Engineering/Design - FEE Mech/Vac","2007-01-25","2007-02-26",null,"C","LL_ME1","Hrs",88,null,15944.339907692309,null,15944.339907692309,null,83.6,null,15147.122912307692,null,15147.122912307692,{"$nulls":4},15147.122912307692,1,{"$nulls":4},0.25,3786.780728076923,1.2,1.05,4,2,"5A"]
["1","05","03","02","","","XT1320140","1.05.03.02","CBD50302","9242693","Final Engineering/Design - FEE Mech/Vac","2007-02-27","2007-04-09",null,"C","LL_MDD1","Hrs",120,null,19946.74223076923,null,19946.74223076923,null,120,null,19946.74223076923,null,19946.74223076923,{"$nulls":4},19946.74223076923,1,{"$nulls":4},0.25,4986.685557692307,1.2,1.05,4,2,"5A"]
["1","05","03","02","","","XT1320190","1.05.03.02","CBD50302","9242693","Fab/Deliver - FEE Mech/Vac","2007-06-08","2007-09-24",null,"C","LA_MSEQ1","$$",null,296000,null,337102.56,337102.56,null,null,296000,null,337102.56,337102.56,{"$nulls":4},337102.56,1,{"$nulls":4},0.25,84275.64,1.2,1.05,5,2,"5A"]
["1","05","03","02","","","XT1325130","1.05.03.02","CBE50302","9242693","Final Design Review - Wall 1 & 2","2007-04-30","2007-05-04",null,"C","LL_ME1","Hrs",40,null,7247.427230769231,null,7247.427230769231,null,40,null,7247.427230769231,null,7247.427230769231,{"$nulls":4},7247.427230769231,1,{"$nulls":4},0.25,1811.8568076923077,1.2,1.05,4,2,"5A"]
["1","05","03","02","","","XT1325160","1.05.03.02","CBE50302","9242693","AWARD: Wall 1 & 2","2007-10-01","2007-10-01",null,"C","LL_AW1","$$",null,49900,null,58306.670964000004,58306.670964000004,null,null,49900,null,58306.670964000004,58306.670964000004,{"$nulls":6},58306.670964000004,1,null,null,0.25,14576.667741000001,1.2,1.05,4,2,"5A"]
["1","05","03","02","","","XT1325170","1.05.03.02","CBE50302","9242693","Fab/Deliver - Wall 1 & 2","2007-10-02","2008-02-04",null,"C","LA_MSEQ1","$$",null,49900,null,58306.670964000004,58306.670964000004,null,null,49900,null,58306.670964000004,58306.670964000004,{"$nulls":6},58306.670964000004,1,null,null,0.25,14576.667741000001,1.2,1.05,5,2,"5A"]
["1","05","03","02","","","XT1327040","1.05.03.02","CBF50302","9242693","Final Design Review - Shadow Wall","2007-05-21","2007-05-25",null,"C","LL_ME1","Hrs",40,null,7247.427230769231,null,7247.427230769231,null,40,null,7247.427230769231,null,7247.427230769231,{"$nulls":4},7247.427230769231,1,{"$nulls":4},0.25,1811.8568076923077,1.2,1.05,4,2,"5A"]
["1","05","03","02","","","XT1327060","1.05.03.02","CBF50302","9242693","Detailed Design - Shadow Wall","2007-05-29","2007-06-11",null,"C","LL_MDD1","Hrs",40,null,6648.914076923076,null,6648.914076923076,null,40,null,6648.914076923076,null,6648.914076923076,{"$nulls":4},6648.914076923076,1,{"$nulls":4},0.25,1662.228519230769,1.2,1.05,4,2,"5A"]
["1","05","03","02","","","XT1327130","1.05.03.02","CBF50302","9242693","Transport Labor to Ship to SLAC - Shadow Wall","2008-01-29","2008-02-04",null,"C","LL_MFAT1","Hrs",40,null,5777.834907461539,null,5777.834907461539,null,40,null,5777.834907461539,null,5777.834907461539,{"$nulls":6},5777.834907461539,1,null,null,0.25,1444.4587268653847,1.2,1.05,4,2,"5A"]
["1","05","03","03","01","","XT1331040","1.05.03.03.01","CBD50303","9242694","Conceptual Engr/Design - NEH Mech/Vac","2006-11-08","2007-01-09",null,"C","LL_ME1","Hrs",64,null,11595.88356923077,null,11595.88356923077,null,16,null,2898.9708923076923,null,2898.9708923076923,{"$nulls":4},2898.9708923076923,1,{"$nulls":4},0.26,753.732432,1.2,1.06,4,2,"5A"]
["1","05","03","03","01","","XT1331110","1.05.03.03.01","CBD50303","9242694","Final Engineering/Design - NEH Mech/Vac","2007-02-27","2007-04-09",null,"C","LL_MDD1","Hrs",60,null,9973.371115384614,null,9973.371115384614,null,60,null,9973.371115384614,null,9973.371115384614,{"$nulls":4},9973.371115384614,1,{"$nulls":4},0.26,2593.07649,1.2,1.06,4,2,"5A"]
["1","05","03","03","01","","XT1331160","1.05.03.03.01","CBD50303","9242694","Fab/Deliver - NEH Mech/Vac","2007-06-08","2007-10-09",null,"C","LL_ME1","Hrs",34,null,6170.73058627092,null,6170.73058627092,null,34,null,6170.73058627092,null,6170.73058627092,{"$nulls":4},5769.382255456551,0.93,401.3483308143688,0.07,null,null,0.26,1604.3899524304393,1.2,1.06,5,2,"5A"]
["1","05","03","04","  ","  ",{"$nulls":4},"Mech/Vac Tunnel                                             ",{"$nulls":6},1390,750000,236225.3235790999,855383.6803984065,236225.3235790999,null,749.2,750000,129387.6865915174,855383.6803984065,984771.3669899236,0,null,0,null,929746.5400447226,null,55024.826945201115,null,0,null,null,187106.55972808553]
["1","05","03","04","","","XT1340040","1.05.03.04","CBD50304","9242523","Prepare oper/maint proced - Tunnel Mech/Vac","2007-06-01","2007-08-10",null,"C","LL_ME1","Hrs",100,null,18118.56807692308,null,18118.56807692308,null,100,null,18118.56807692308,null,18118.56807692308,{"$nulls":4},18118.56807692308,1,{"$nulls":4},0.19,3442.5279346153848,1.15,1.04,5,2,"5A"]
["1","05","03","04","","","XT1340180","1.05.03.04","CBD50304","9242523","Readiness Review - Tunnel Mech/Vac","2007-07-27","2007-08-09",null,"C","LL_MFAT1","Hrs",10,null,1407.8545096153848,null,1407.8545096153848,null,10,null,1407.8545096153848,null,1407.8545096153848,{"$nulls":4},1407.8545096153848,1,{"$nulls":4},0.19,267.4923568269231,1.15,1.04,5,2,"5A"]
["1","05","03","04","","","XT1340180","1.05.03.04","CBD50304","9242523","Readiness Review - Tunnel Mech/Vac","2007-07-27","2007-08-09",null,"C","LL_MDD1","Hrs",10,null,1662.228519230769,null,1662.228519230769,null,10,null,1662.228519230769,null,1662.228519230769,{"$nulls":4},1662.228519230769,1,{"$nulls":4},0.19,315.82341865384615,1.15,1.04,5,2,"5A"]
["1","05","03","05","","","XT1351065","1.05.03.05","CBD50305",null,"Prepare ESD - FEH Mech/Vac","2007-01-25","2007-02-22",null,"C","LL_ME1","Hrs",16,null,2898.9708923076923,null,2898.9708923076923,null,16,null,2898.9708923076923,null,2898.9708923076923,{"$nulls":4},2898.9708923076923,1,{"$nulls":4},0.24,695.7530141538462,1.2,1.04,4,2,"5A"]
["1","05","03","05","","","XT1351110","1.05.03.05","CBD50305",null,"Final Engineering/Design - FEH Mech/Vac","2007-02-27","2007-04-09",null,"C","LL_ME1","Hrs",30,null,5435.570423076923,null,5435.570423076923,null,30,null,5435.570423076923,null,5435.570423076923,{"$nulls":4},5435.570423076923,1,{"$nulls":4},0.24,1304.5369015384615,1.2,1.04,4,2,"5A"]
["1","05","03","05","","","XT1351170","1.05.03.05","CBD50305",null,"Test @ LLNL - FEH Mech/Vac","2007-09-12","2007-09-25",null,"C","LL_ME1","Hrs",5,null,905.9284038461539,null,905.9284038461539,null,5,null,905.9284038461539,null,905.9284038461539,{"$nulls":4},905.9284038461539,1,{"$nulls":4},0.24,217.4228169230769,1.2,1.04,4,2,"5A"]
["1","05","03","05","02","  ",{"$nulls":4},"FEH Hutch 2                                                 "]
["1","05","04","02","01","","XT1421040","1.05.04.02.01","CBD5040201",null,"Final Engineering/Design - Fast Valve","2006-11-13","2007-01-10",null,"C","LL_MDD1","Hrs",80,null,13297.828153846152,null,13297.828153846152,null,80,null,13297.828153846152,null,13297.828153846152,{"$nulls":4},13297.828153846152,1,{"$nulls":4},0.17,2260.630786153846,1.15,1.02,4,2,"5A"]
["1","05","04","02","01","","XT1421080","1.05.04.02.01","CBD5040201",null,"Prepare oper/maint proced - Fast Valve","2006-11-13","2006-11-28",null,"C","LL_ME1","Hrs",10,null,1811.8568076923077,null,1811.8568076923077,null,10,null,1811.8568076923077,null,1811.8568076923077,{"$nulls":4},1811.8568076923077,1,{"$nulls":4},0.17,308.0156573076923,1.15,1.02,5,2,"5A"]
["1","05","04","02","01","","XT1421170","1.05.04.02.01","CBD5040201",null,"Ship to SLAC - Fast Valve","2007-12-05","2008-01-03",null,"C","LL_ADMN1","Hrs",8,null,1129.7359319538461,null,1129.7359319538461,null,8,null,1129.7359319538461,null,1129.7359319538461,{"$nulls":6},1129.7359319538461,1,null,null,0.17,192.05510843215387,1.15,1.02,4,2,"5A"]
["1","05","04","02","02","","XT1422010","1.05.04.02.02","CBD5040202","9242700","Preliminary Engineering/Design - Fixed Mask","2006-07-03","2006-07-31",null,"C","LL_MDD1","Hrs",40,null,6480.423076923076,null,6480.423076923076,null,0,null,0,null,0,{"$nulls":10},0.19,0,1.15,1.04,7,2,"5A"]
["1","05","04","02","02","","XT1422150","1.05.04.02.02","CBD5040202","9242700","Fab/Deliver - Fixed Mask","2007-01-02","2007-02-28",null,"C","LL_ADMN1","Hrs",16,null,2202.214292307692,null,2202.214292307692,null,16,null,2202.214292307692,null,2202.214292307692,{"$nulls":4},2202.214292307692,1,{"$nulls":4},0.19,418.42071553846154,1.15,1.04,5,2,"5A"]
["1","05","04","02","02","","XT1422160","1.05.04.02.02","CBD5040202","9242700","Testing @ LLNL - Fixed Mask","2007-03-01","2007-03-28",null,"C","LL_MDD1","Hrs",40,null,6648.914076923076,null,6648.914076923076,null,40,null,6648.914076923076,null,6648.914076923076,{"$nulls":4},6648.914076923076,1,{"$nulls":4},0.19,1263.2936746153846,1.15,1.04,4,2,"5A"]
["1","05","04","02","03","","XT1423050","1.05.04.02.03","CBD5040203","9242701","Final Engineering/Design - Slit","2006-08-01","2006-10-17",null,"C","LL_ME1","Hrs",220,null,39060.62562637363,null,39060.62562637363,null,0,null,0,null,0,{"$nulls":10},0.26,0,1.2,1.06,4,2,"5A"]
["1","05","04","02","03","","XT1423130","1.05.04.02.03","CBD5040203","9242701","Bid Prep/RFP/Award - Slit","2006-12-01","2007-01-29",null,"C","LL_ME1","Hrs",24,null,4348.4563384615385,null,4348.4563384615385,null,12,null,2174.2281692307693,null,2174.2281692307693,{"$nulls":4},2174.2281692307693,1,{"$nulls":4},0.26,565.2993240000001,1.2,1.06,4,2,"5A"]
["1","05","04","02","03","","XT1423180","1.05.04.02.03","CBD5040203","9242701","Ship to SLAC - Slit","2007-12-05","2008-01-03",null,"C","LL_ME1","Hrs",8,null,1487.172067753846,null,1487.172067753846,null,8,null,1487.172067753846,null,1487.172067753846,{"$nulls":6},1487.172067753846,1,null,null,0.26,386.66473761599997,1.2,1.06,4,2,"5A"]
["1","05","04","02","05","  ",{"$nulls":4},"Gas/Solid Attenuator                                        ",{"$nulls":6},3014,1295000,513712.2792250384,1474583.2,1960064.479225038,null,958.8,1270000,162020.95834157694,1446352.2,1608373.1583415766,0,null,178.88995576923077,null,1601201.2708646152,null,6992.997521192307,null,0,null,null,450344.48433564155]
["1","05","04","02","05","","XT1425100","1.05.04.02.05","CBD5040205","9242703","Prepare seismic note - Gas/Solid Attenuator","2006-09-01","2006-10-31",null,"C","LL_ME1","Hrs",40,null,7155.59823076923,null,7155.59823076923,null,2,null,357.77991153846153,null,357.77991153846153,null,null,178.88995576923077,0.5,178.88995576923077,0.5,{"$nulls":4},0.28,100.17837523076923,1.2,1.08,4,2,"5A"]
["1","05","04","02","05","","XT1425120","1.05.04.02.05","CBD5040205","9242703","Prepare acceptance test plan/proced -Gas/Solid A","2006-11-16","2007-01-16",null,"C","LL_ME1","Hrs",30,null,5435.570423076923,null,5435.570423076923,null,3,null,543.5570423076923,null,543.5570423076923,{"$nulls":4},543.5570423076923,1,{"$nulls":4},0.28,152.19597184615387,1.2,1.08,5,2,"5A"]
["1","05","04","02","05","","XT1425190","1.05.04.02.05","CBD5040205","9242703","Fab/Deliver - Gas/Solid Attenuator","2007-04-04","2007-06-29",null,"C","LL_EE1","Hrs",25,null,4529.64201923077,null,4529.64201923077,null,25,null,4529.64201923077,null,4529.64201923077,{"$nulls":4},4529.64201923077,1,{"$nulls":4},0.28,1268.2997653846155,1.2,1.08,4,2,"5A"]
["1","05","04","02","05","","XT1425200","1.05.04.02.05","CBD5040205","9242703","Assembly/Test @ LLNL - Gas/Solid Attenuator","2007-07-02","2007-09-17",null,"C","LL_MFAT1","Hrs",158,null,22244.101251923083,null,22244.101251923083,null,158,null,22244.101251923083,null,22244.101251923083,{"$nulls":4},22244.101251923083,1,{"$nulls":4},0.28,6228.348350538464,1.2,1.08,4,2,"5A"]
["1","05","04","02","06","","XT1426050","1.05.04.02.06","CBD5040206",null,"Travel Expense - TTF Damage Exp.","2006-10-02","2006-10-02",null,"C","LL_MSTR1","$$",null,12000,null,14651.28,14651.28,null,null,0,null,0,0,{"$nulls":10},0.19,0,1.15,1.04,4,2,"5A"]
["1","05","04","02","07","01","XT14271040","1.05.04.02.07","CBD5040271","9242704","Conceptual Engr/Design - LE Mirror","2006-09-01","2006-11-08",null,"C","LL_MDD1","Hrs",99,null,16272.085035237556,null,16272.085035237556,null,0,null,0,null,0,{"$nulls":10},0.45,0,1.35,1.1,4,2,"5A"]
["1","05","04","02","07","01","XT14271080","1.05.04.02.07","CBD5040271","9242704","Preliminary Design Review - LE Mirror","2007-01-24","2007-02-06",null,"C","LL_MDD1","Hrs",30,null,4986.685557692307,null,4986.685557692307,null,30,null,4986.685557692307,null,4986.685557692307,{"$nulls":4},4986.685557692307,1,{"$nulls":4},0.45,2244.008500961538,1.35,1.1,4,2,"5A"]
["1","05","04","02","07","01","XT14271093","1.05.04.02.07","CBD5040271","9242704","Prepare acceptance test plan/proced -LE Mirror","2006-11-27","2006-12-08",null,"C","LL_ME1","Hrs",8,null,1449.4854461538462,null,1449.4854461538462,null,7.2,null,1304.5369015384615,null,1304.5369015384615,{"$nulls":4},1304.5369015384615,1,{"$nulls":4},0.45,587.0416056923077,1.35,1.1,5,2,"5A"]
["1","05","04","02","07","01","XT14271150","1.05.04.02.07","CBD5040271","9242704","Fab/Deliver - LE Mirror Substrate","2007-03-23","2007-08-13",null,"C","LL_PHS1","Hrs",40,null,7743.9717692307695,null,7743.9717692307695,null,40,null,7743.9717692307695,null,7743.9717692307695,{"$nulls":4},7743.9717692307695,1,{"$nulls":4},0.45,3484.7872961538465,1.35,1.1,5,2,"5A"]
["1","05","04","02","07","01","XT14271150","1.05.04.02.07","CBD5040271","9242704","Fab/Deliver - LE Mirror Substrate","2007-03-23","2007-08-13",null,"C","LA_MSEQ1","$$",null,210000,null,239160.6,239160.6,null,null,210000,null,239160.6,239160.6,{"$nulls":4},239160.6,1,{"$nulls":4},0.45,107622.27,1.35,1.1,5,2,"5A"]
["1","05","04","02","07","01","XT14271210","1.05.04.02.07","CBD5040271","9242704","Readiness Review - LE Mirror","2007-09-26","2007-10-09",null,"C","LL_PHS1","Hrs",20,null,3933.937658769231,null,3933.937658769231,null,20,null,3933.937658769231,null,3933.937658769231,{"$nulls":4},1513.0529456804736,0.38,2420.8847130887575,0.62,null,null,0.45,1770.2719464461538,1.35,1.1,5,2,"5A"]
["1","05","04","02","07","01","XT14271210","1.05.04.02.07","CBD5040271","9242704","Readiness Review - LE Mirror","2007-09-26","2007-10-09",null,"C","LL_EE1","Hrs",4,null,736.3386066461538,null,736.3386066461538,null,4,null,736.3386066461538,null,736.3386066461538,{"$nulls":4},283.2071564023669,0.38,453.131450243787,0.62,null,null,0.45,331.35237299076925,1.35,1.1,5,2,"5A"]
["1","05","04","02","07","02","XT14272065","1.05.04.02.07","CBD5040272","9242704","Prepare ESD - HE Mirror","2007-01-30","2007-02-27",null,"C","LL_PHS1","Hrs",16,null,3097.5887076923077,null,3097.5887076923077,null,16,null,3097.5887076923077,null,3097.5887076923077,{"$nulls":4},3097.5887076923077,1,{"$nulls":4},0.45,1393.9149184615385,1.35,1.1,4,2,"5A"]
["1","05","04","02","07","02","XT14272080","1.05.04.02.07","CBD5040272","9242704","Preliminary Design Review - HE Mirror","2007-04-03","2007-04-16",null,"C","LL_ME1","Hrs",30,null,5435.570423076923,null,5435.570423076923,null,30,null,5435.570423076923,null,5435.570423076923,{"$nulls":4},5435.570423076923,1,{"$nulls":4},0.45,2446.0066903846155,1.35,1.1,4,2,"5A"]
["1","05","04","02","07","02","XT14272110","1.05.04.02.07","CBD5040272","9242704","Final Design Review - HE Mirror","2007-08-10","2007-08-23",null,"C","LL_ME1","Hrs",40,null,7247.427230769231,null,7247.427230769231,null,40,null,7247.427230769231,null,7247.427230769231,{"$nulls":4},7247.427230769231,1,{"$nulls":4},0.45,3261.342253846154,1.35,1.1,4,2,"5A"]
["1","05","04","02","07","02","XT14272150","1.05.04.02.07","CBD5040272","9242704","Fab/Deliver - HE Mirror Substrate","2007-05-16","2008-05-13",null,"C","LA_MSEQ1","$$",null,300000,null,347164.058677686,null,null,null,300000,null,347164.058677686,347164.058677686,{"$nulls":4},131979.7247865583,0.38,215184.3338911277,0.62,null,null,0.45,156223.8264049587,1.35,1.1,5,2,"5A"]
["1","05","04","02","07","02","XT14272200","1.05.04.02.07","CBD5040272","9242704","Test Mount @ LLNL - HE Mirror","2008-03-19","2008-05-13",null,"C","LL_PHS1","Hrs",80,null,15890.630070461539,null,15890.630070461539,null,80,null,15890.630070461539,null,15890.630070461539,{"$nulls":6},15890.630070461539,1,null,null,0.45,7150.783531707692,1.35,1.1,5,2,"5A"]
["1","05","04","02","07","02","XT14272200","1.05.04.02.07","CBD5040272","9242704","Test Mount @ LLNL - HE Mirror","2008-03-19","2008-05-13",null,"C","LL_EE1","Hrs",16,null,2974.344135507692,null,2974.344135507692,null,16,null,2974.344135507692,null,2974.344135507692,{"$nulls":6},2974.344135507692,1,null,null,0.45,1338.4548609784615,1.35,1.1,5,2,"5A"]
["1","05","04","04","01","  ",{"$nulls":4},"Crystals & Gratings Engineering                             "]
["1","05","05","  ","  ","  ",{"$nulls":4},"Diagnostics Subsystem                                       ",{"$nulls":6},17509,1069100,3045984.873664146,1226099.486340081,3930808.5793601456,null,11271.5,933230,1968079.2599330537,1072234.3613108126,3040313.6212438717,0,null,5761.413446088205,null,2335091.7146360525,null,699460.4931617285,null,0,null,null,913351.0602900848]
["1","05","05","03","01","","XT1531010","1.05.05.03.01","CBD5050301","9242710","Prepare Physics Specification - Direct Imager","2006-07-14","2006-09-29",null,"C","LL_EE1","Hrs",46,null,8123.334615384615,null,8123.334615384615,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.2,1.05,4,2,"5A"]
["1","05","05","03","01","","XT1531050","1.05.05.03.01","CBD5050301","9242710","Conceptual Design Review - Direct Imager","2006-10-16","2006-10-27",null,"C","LL_MDD1","Hrs",20,null,3324.457038461538,null,3324.457038461538,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.2,1.05,4,2,"5A"]
["1","05","05","03","01","","XT1531120","1.05.05.03.01","CBD5050301","9242710","Prepare acceptance test plan/proced - Direct Ima","2007-01-02","2007-02-13",null,"C","LL_EE1","Hrs",24,null,4348.4563384615385,null,4348.4563384615385,null,24,null,4348.4563384615385,null,4348.4563384615385,{"$nulls":4},4348.4563384615385,1,{"$nulls":4},0.25,1087.1140846153846,1.2,1.05,5,2,"5A"]
["1","05","05","03","01","","XT1531150","1.05.05.03.01","CBD5050301","9242710","Final Design Review - Direct Imager","2007-03-02","2007-03-15",null,"C","LL_MDD1","Hrs",20,null,3324.457038461538,null,3324.457038461538,null,20,null,3324.457038461538,null,3324.457038461538,{"$nulls":4},3324.457038461538,1,{"$nulls":4},0.25,831.1142596153845,1.2,1.05,4,2,"5A"]
["1","05","05","03","01","","XT1531200","1.05.05.03.01","CBD5050301","9242710","Test @ LLNL - Direct Imager","2007-07-17","2007-10-16",null,"C","LL_ME1","Hrs",65,null,11827.542403928572,null,11827.542403928572,null,65,null,11827.542403928572,null,11827.542403928572,{"$nulls":4},9877.947502182104,0.84,1949.594901746468,0.16,null,null,0.25,2956.885600982143,1.2,1.05,5,2,"5A"]
["1","05","05","03","01","","XT1531210","1.05.05.03.01","CBD5050301","9242710","Readiness Review - Direct Imager","2007-10-17","2007-10-30",null,"C","LL_ME1","Hrs",10,null,1858.9650846923075,null,1858.9650846923075,null,10,null,1858.9650846923075,null,1858.9650846923075,{"$nulls":6},1858.9650846923075,1,null,null,0.25,464.7412711730769,1.2,1.05,5,2,"5A"]
["1","05","05","03","06","","XT1536030","1.05.05.03.06","CBD5050306","9242713","Prototype Surface Testing - Gas Detector","2006-08-01","2006-10-31",null,"C","LL_EE1","Hrs",46,null,8192.963197802197,null,8192.963197802197,null,0,null,0,null,0,{"$nulls":10},0.43,0,1.35,1.08,4,2,"5A"]
["1","05","05","03","06","","XT1536040","1.05.05.03.06","CBD5050306","9242713","Prepare ESD (Instr Sci) - Gas Detector","2006-07-03","2006-10-30",null,"C","LL_EE1","Hrs",20,null,3554.263111182934,null,3554.263111182934,null,0,null,0,null,0,{"$nulls":10},0.43,0,1.35,1.08,4,2,"5A"]
["1","05","05","03","06","","XT1536092","1.05.05.03.06","CBD5050306","9242713","Procure Hrdwr - Detector Calibration @ SSRL","2006-09-20","2006-10-31",null,"C","LL_MSEQ1","$$",null,25000,null,28277.926829268297,null,null,null,0,null,0,0,{"$nulls":10},0.43,0,1.35,1.08,4,2,"5A"]
["1","05","05","03","06","","XT1536095","1.05.05.03.06","CBD5050306","9242713","Analysis - Detector Calibration @ SSRL","2006-11-13","2006-12-12",null,"C","LL_PHS1","Hrs",40,null,7743.9717692307695,null,7743.9717692307695,null,40,null,7743.9717692307695,null,7743.9717692307695,{"$nulls":4},7743.9717692307695,1,{"$nulls":4},0.43,3329.907860769231,1.35,1.08,5,2,"5A"]
["1","05","05","03","06","","XT1536130","1.05.05.03.06","CBD5050306","9242713","Prepare oper/maint proced - Gas Detector","2006-11-01","2006-12-15",null,"C","LL_ME1","Hrs",20,null,3623.7136153846154,null,3623.7136153846154,null,15,null,2717.7852115384617,null,2717.7852115384617,{"$nulls":4},2717.7852115384617,1,{"$nulls":4},0.43,1168.6476409615384,1.35,1.08,5,2,"5A"]
["1","05","05","03","06","","XT1536150","1.05.05.03.06","CBD5050306","9242713","Final Design Review - Gas Detector","2007-01-16","2007-01-29",null,"C","LL_ME1","Hrs",20,null,3623.7136153846154,null,3623.7136153846154,null,20,null,3623.7136153846154,null,3623.7136153846154,{"$nulls":4},3623.7136153846154,1,{"$nulls":4},0.43,1558.1968546153846,1.35,1.08,4,2,"5A"]
["1","05","05","03","06","","XT1536190","1.05.05.03.06","CBD5050306","9242713","Fab/Deliver - Gas Detector","2007-03-15","2007-06-21",null,"C","LL_ADMN1","Hrs",10,null,1376.3839326923076,null,1376.3839326923076,null,10,null,1376.3839326923076,null,1376.3839326923076,{"$nulls":4},1376.3839326923076,1,{"$nulls":4},0.43,591.8450910576922,1.35,1.08,5,2,"5A"]
["1","05","05","03","06","","XT1536200","1.05.05.03.06","CBD5050306","9242713","Test @ LLNL - Gas Detector","2007-06-22","2007-09-17",null,"C","LL_MFAT1","Hrs",48,null,6757.701646153848,null,6757.701646153848,null,48,null,6757.701646153848,null,6757.701646153848,{"$nulls":4},6757.701646153848,1,{"$nulls":4},0.43,2905.8117078461546,1.35,1.08,5,2,"5A"]
["1","05","05","03","07","","XT1537040","1.05.05.03.07","CBD5050307",null,"Conceptual Engr/Design - NEH Imager","2007-01-30","2007-03-13",null,"C","LL_MDD1","Hrs",90,null,14960.056673076922,null,14960.056673076922,null,90,null,14960.056673076922,null,14960.056673076922,{"$nulls":4},14960.056673076922,1,{"$nulls":4},0.25,3740.0141682692306,1.2,1.05,4,2,"5A"]
["1","05","05","03","07","","XT1537050","1.05.05.03.07","CBD5050307",null,"Conceptual Design Review - NEH Imager","2007-03-14","2007-03-27",null,"C","LL_MDD1","Hrs",20,null,3324.457038461538,null,3324.457038461538,null,20,null,3324.457038461538,null,3324.457038461538,{"$nulls":4},3324.457038461538,1,{"$nulls":4},0.25,831.1142596153845,1.2,1.05,4,2,"5A"]
["1","05","05","03","07","","XT1537080","1.05.05.03.07","CBD5050307",null,"Preliminary Design Review - NEH Imager","2007-05-09","2007-05-22",null,"C","LL_ME1","Hrs",20,null,3623.7136153846154,null,3623.7136153846154,null,20,null,3623.7136153846154,null,3623.7136153846154,{"$nulls":4},3623.7136153846154,1,{"$nulls":4},0.25,905.9284038461539,1.2,1.05,4,2,"5A"]
["1","05","05","03","07","","XT1537150","1.05.05.03.07","CBD5050307",null,"Final Design Review - NEH Imager","2007-07-30","2007-08-10",null,"C","LL_MDD1","Hrs",20,null,3324.457038461538,null,3324.457038461538,null,20,null,3324.457038461538,null,3324.457038461538,{"$nulls":4},3324.457038461538,1,{"$nulls":4},0.25,831.1142596153845,1.2,1.05,4,2,"5A"]
["1","05","05","03","07","","XT1537200","1.05.05.03.07","CBD5050307",null,"Test @ LLNL - NEH Imager","2008-02-01","2008-02-29",null,"C","LL_ME1","Hrs",20,null,3717.930169384615,null,3717.930169384615,null,20,null,3717.930169384615,null,3717.930169384615,{"$nulls":6},3717.930169384615,1,null,null,0.25,929.4825423461538,1.2,1.05,5,2,"5A"]
["1","05","05","03","07","","XT1537220","1.05.05.03.07","CBD5050307",null,"Ship to SLAC - NEH Imager","2008-03-17","2008-03-28",null,"C","LL_EE1","Hrs",4,null,743.586033876923,null,743.586033876923,null,4,null,743.586033876923,null,743.586033876923,{"$nulls":6},743.586033876923,1,null,null,0.25,185.89650846923075,1.2,1.05,4,2,"5A"]
["1","05","05","04","02","","XT1542025","1.05.05.04.02","CBD5050402","9242715","Prototype revision - Total Energy Measurement","2006-09-01","2006-11-30",null,"C","LL_PHS1","Hrs",124,null,23803.53011794872,null,23803.53011794872,null,6.2,null,1151.7837153846153,null,1151.7837153846153,null,null,383.9279051282051,0.33,767.8558102564102,0.67,{"$nulls":4},0.33,380.0886260769231,1.25,1.08,5,2,"5A"]
["1","05","05","04","02","","XT1542035","1.05.05.04.02","CBD5050402","9242715","Model refinement - Total Energy Measurement","2006-10-02","2006-12-15",null,"C","LL_PHS1","Hrs",42,null,8131.170357692307,null,8131.170357692307,null,2.1,null,406.5585178846154,null,406.5585178846154,{"$nulls":4},406.5585178846154,1,{"$nulls":4},0.33,134.1643109019231,1.25,1.08,5,2,"5A"]
["1","05","05","04","02","","XT1542133","1.05.05.04.02","CBD5050402","9242715","Fab Sensor Arrays on Si - Total Energy Measureme","2007-01-02","2007-02-28",null,"C","LL_MFAT1","Hrs",160,null,22525.672153846157,null,22525.672153846157,null,0,null,0,null,0,{"$nulls":10},0.33,0,1.25,1.08,4,2,"5A"]
["1","05","05","04","02","","XT1542140","1.05.05.04.02","CBD5050402","9242715","Final Engineering/Design - Total Energy Measurem","2006-11-09","2007-01-23",null,"C","LL_ME1","Hrs",120,null,21742.281692307693,null,21742.281692307693,null,48,null,8696.912676923077,null,8696.912676923077,{"$nulls":4},8696.912676923077,1,{"$nulls":4},0.33,2869.9811833846156,1.25,1.08,4,2,"5A"]
["1","05","05","04","02","","XT1542170","1.05.05.04.02","CBD5050402","9242715","Bid Prep/RFP/Award - Total Energy Measurement","2007-01-02","2007-02-13",null,"C","LL_ADMN1","Hrs",40,null,5505.53573076923,null,5505.53573076923,null,40,null,5505.53573076923,null,5505.53573076923,{"$nulls":4},5505.53573076923,1,{"$nulls":4},0.33,1816.826791153846,1.25,1.08,4,2,"5A"]
["1","05","05","04","02","","XT1542192","1.05.05.04.02","CBD5050402","9242715","Fab/Deliver - Final Production Sensors (Towson U","2007-03-02","2007-09-28",null,"C","LA_MSEQ1","$$",null,58000,null,66053.88,66053.88,null,null,49880,null,56806.33680000001,56806.33680000001,{"$nulls":4},56806.33680000001,1,{"$nulls":4},0.33,18746.091144000005,1.25,1.08,4,3,"5A"]
["1","05","05","04","02","","XT1542230","1.05.05.04.02","CBD5050402","9242715","Ship to SLAC - Total Energy Measurement","2008-02-19","2008-03-03",null,"C","LL_ADMN1","Hrs",4,null,564.8679659769231,null,564.8679659769231,null,4,null,564.8679659769231,null,564.8679659769231,{"$nulls":6},564.8679659769231,1,null,null,0.33,186.40642877238463,1.25,1.08,4,2,"5A"]
["1","05","05","04","04","","XT1544040","1.05.05.04.04","CBD5050404","9242716","Conceptual Engr/Design - Low Energy Spectrometer","2006-10-23","2006-11-14",null,"C","LL_ME1","Hrs",34,null,6160.313146153846,null,6160.313146153846,null,32.3,null,5852.297488846153,null,5852.297488846153,{"$nulls":4},5852.297488846153,1,{"$nulls":4},0.31,1814.2122215423074,1.25,1.06,4,2,"5A"]
["1","05","05","04","04","","XT1544080","1.05.05.04.04","CBD5050404","9242716","Preliminary Design Review - Low Energy Spectrome","2007-01-09","2007-01-23",null,"C","LL_MDD1","Hrs",20,null,3324.457038461538,null,3324.457038461538,null,20,null,3324.457038461538,null,3324.457038461538,{"$nulls":4},3324.457038461538,1,{"$nulls":4},0.31,1030.5816819230768,1.25,1.06,4,2,"5A"]
["1","05","05","04","04","","XT1544140","1.05.05.04.04","CBD5050404","9242716","Final Engineering/Design - Low Energy Spectromet","2007-01-09","2007-03-07",null,"C","LL_ME1","Hrs",160,null,28989.708923076923,null,28989.708923076923,null,160,null,28989.708923076923,null,28989.708923076923,{"$nulls":4},28989.708923076923,1,{"$nulls":4},0.31,8986.809766153847,1.25,1.06,4,2,"5A"]
["1","05","05","04","04","","XT1544190","1.05.05.04.04","CBD5050404","9242716","Fab/Deliver - Low Energy Spectrometer","2007-05-22","2007-08-22",null,"C","LL_EE1","Hrs",26,null,4710.8277,null,4710.8277,null,26,null,4710.8277,null,4710.8277,{"$nulls":4},4710.8277,1,{"$nulls":4},0.31,1460.356587,1.25,1.06,5,2,"5A"]
["1","05","05","04","04","","XT1544200","1.05.05.04.04","CBD5050404","9242716","Test @ LLNL - Low Energy Spectrometer","2007-08-23","2007-10-04",null,"C","LL_MFAT1","Hrs",30,null,4231.40728968544,null,4231.40728968544,null,30,null,4231.40728968544,null,4231.40728968544,{"$nulls":4},3929.1639118507665,0.93,302.2433778346743,0.07,null,null,0.31,1311.7362598024865,1.25,1.06,5,2,"5A"]
["1","05","05","04","04","","XT1544230","1.05.05.04.04","CBD5050404","9242716","Ship to SLAC - Low Energy Spectrometer","2007-12-05","2008-01-03",null,"C","LL_ME1","Hrs",4,null,743.586033876923,null,743.586033876923,null,4,null,743.586033876923,null,743.586033876923,{"$nulls":6},743.586033876923,1,null,null,0.31,230.51167050184614,1.25,1.06,4,2,"5A"]
["1","05","05","04","05","","XT1545050","1.05.05.04.05","CBD5050405","9242717","Conceptual Design Review - Popup Cameras","2007-02-14","2007-02-28",null,"C","LL_MDD1","Hrs",20,null,3324.457038461538,null,3324.457038461538,null,20,null,3324.457038461538,null,3324.457038461538,{"$nulls":4},3324.457038461538,1,{"$nulls":4},0.25,831.1142596153845,1.2,1.05,4,2,"5A"]
["1","05","05","04","05","","XT1545120","1.05.05.04.05","CBD5050405","9242717","Prepare acceptance test plan/proced - Popup Came","2007-05-03","2007-06-14",null,"C","LL_EE1","Hrs",24,null,4348.4563384615385,null,4348.4563384615385,null,24,null,4348.4563384615385,null,4348.4563384615385,{"$nulls":4},4348.4563384615385,1,{"$nulls":4},0.25,1087.1140846153846,1.2,1.05,5,2,"5A"]
["1","05","05","04","05","","XT1545150","1.05.05.04.05","CBD5050405","9242717","Final Design Review - Popup Cameras","2007-07-27","2007-08-09",null,"C","LL_MDD1","Hrs",20,null,3324.457038461538,null,3324.457038461538,null,20,null,3324.457038461538,null,3324.457038461538,{"$nulls":4},3324.457038461538,1,{"$nulls":4},0.25,831.1142596153845,1.2,1.05,4,2,"5A"]
["1","05","05","04","05","","XT1545200","1.05.05.04.05","CBD5050405","9242717","Test @ LLNL - Popup Cameras","2007-12-13","2008-03-19",null,"C","LL_EE1","Hrs",56,null,10410.204474276921,null,10410.204474276921,null,56,null,10410.204474276921,null,10410.204474276921,{"$nulls":6},10410.204474276921,1,null,null,0.25,2602.5511185692303,1.2,1.05,5,2,"5A"]
["1","05","05","04","05","","XT1545220","1.05.05.04.05","CBD5050405","9242717","Ship to SLAC - Popup Cameras","2008-04-03","2008-04-16",null,"C","LL_ADMN1","Hrs",8,null,1129.7359319538461,null,1129.7359319538461,null,8,null,1129.7359319538461,null,1129.7359319538461,{"$nulls":6},1129.7359319538461,1,null,null,0.25,282.43398298846154,1.2,1.05,4,2,"5A"]
["1","05","05","04","06","","XT1546050","1.05.05.04.06","CBD5050406","9242718","Preliminary Design - K Meas.","2007-01-31","2007-03-28","S","C","LL_ME1","Hrs",80,null,14494.854461538462,null,14494.854461538462,null,80,null,14494.854461538462,null,14494.854461538462,{"$nulls":4},14494.854461538462,1,{"$nulls":4},0.31,4493.404883076923,1.25,1.06,4,2,"5A"]
["1","05","05","04","06","","XT1546060","1.05.05.04.06","CBD5050406","9242718","Preliminary Design Review - K Meas.","2007-03-29","2007-04-25","S","C","LL_ME1","Hrs",16,null,2898.9708923076923,null,2898.9708923076923,null,16,null,2898.9708923076923,null,2898.9708923076923,{"$nulls":4},2898.9708923076923,1,{"$nulls":4},0.31,898.6809766153846,1.25,1.06,4,2,"5A"]
["1","05","05","04","06","","XT1546080","1.05.05.04.06","CBD5050406","9242718","Final Design Review - K Meas.","2007-06-22","2007-07-20","S","C","LL_ME1","Hrs",16,null,2898.9708923076923,null,2898.9708923076923,null,16,null,2898.9708923076923,null,2898.9708923076923,{"$nulls":4},2898.9708923076923,1,{"$nulls":4},0.31,898.6809766153846,1.25,1.06,4,2,"5A"]
["1","05","05","04","06","","XT1546190","1.05.05.04.06","CBD5050406","9242718","AWARD: Detector & Electronics","2007-09-18","2007-09-18","S","C","LL_AW1","$$",null,50000,null,56943,56943,null,null,50000,null,56943,56943,{"$nulls":4},56943,1,{"$nulls":4},0.31,17652.329999999998,1.25,1.06,4,3,"5A"]
["1","05","05","04","06","","XT1546340","1.05.05.04.06","CBD5050406","9242718","Bid and Award - Multilayers","2007-05-10","2007-06-21","S","C","LL_PHS1","Hrs",30,null,5807.978826923077,null,5807.978826923077,null,30,null,5807.978826923077,null,5807.978826923077,{"$nulls":4},5807.978826923077,1,{"$nulls":4},0.31,1800.4734363461537,1.25,1.06,5,3,"5A"]
["1","05","05","04","07","  ",{"$nulls":4},"Divergence Measurement                                      "]
["1","05","06","01","","","XT1610110","1.05.06.01","CKD50601","9242530","Install vacuum cable plant","2008-04-07","2008-04-09",null,"C","SL_TMUP1","Hrs",48,null,4528.763737343999,null,4528.763737343999,null,48,null,4528.763737343999,null,4528.763737343999,{"$nulls":6},4528.763737343999,1,null,null,0.25,1132.1909343359998,1.15,1.1,4,4,"5A"]
["1","05","06","01","","","XT1610170","1.05.06.01","CKD50601","9242530","Align slit/fixed mask package","2008-04-15","2008-04-16",null,"C","SL_MES1","Hrs",32,null,2636.160689707776,null,2636.160689707776,null,32,null,2636.160689707776,null,2636.160689707776,{"$nulls":6},2636.160689707776,1,null,null,0.25,659.040172426944,1.15,1.1,4,4,"5A"]
["1","05","06","01","","","XT1610230","1.05.06.01","CKD50601","9242530","Install undulator-K spectrometer","2008-04-28","2008-04-30",null,"C","LL_ME1","Hrs",24,null,4461.516203261538,null,4461.516203261538,null,24,null,4461.516203261538,null,4461.516203261538,{"$nulls":6},4461.516203261538,1,null,null,0.25,1115.3790508153845,1.15,1.1,4,4,"5A"]
["1","05","06","01","","","XT1610250","1.05.06.01","CKD50601","9242530","Test undulator-K spectrometer","2008-05-05","2008-05-09",null,"C","SL_MFAT1","Hrs",40,null,3536.99136,null,3536.99136,null,40,null,3536.99136,null,3536.99136,{"$nulls":6},3536.99136,1,null,null,0.25,884.24784,1.15,1.1,5,4,"5A"]
["1","05","06","01","","","XT1610280","1.05.06.01","CKD50601","9242530","Install HXR offset mirrors","2008-06-12","2008-06-17",null,"C","LL_ME1","Hrs",32,null,5948.688271015384,null,5948.688271015384,null,32,null,5948.688271015384,null,5948.688271015384,{"$nulls":6},5948.688271015384,1,null,null,0.25,1487.172067753846,1.15,1.1,4,4,"5A"]
["1","05","06","01","","","XT1610350","1.05.06.01","CKD50601","9242530","Align isolation valves","2008-07-11","2008-07-11",null,"C","SL_MES1","Hrs",16,null,1318.080344853888,null,1318.080344853888,null,16,null,1318.080344853888,null,1318.080344853888,{"$nulls":6},1318.080344853888,1,null,null,0.25,329.520086213472,1.15,1.1,4,4,"5A"]
["1","05","06","01","","","XT1610420","1.05.06.01","CKD50601","9242530","Test Instrument Controls","2008-06-18","2008-07-30",null,"C","SL_MFAT1","Hrs",240,null,21221.94816,null,21221.94816,null,240,null,21221.94816,null,21221.94816,{"$nulls":6},21221.94816,1,null,null,0.25,5305.48704,1.15,1.1,5,4,"5A"]
["1","05","06","02","  ","  ",{"$nulls":4},"Near Hall Install                                           ",{"$nulls":6},1436,0,140141.8508942484,0,140141.8508942484,null,1436,0,140141.8508942484,0,140141.8508942484,0,null,0,null,0,null,140141.8508942484,null,0,null,null,35035.4627235621]
["1","05","06","02","","","XT1620130","1.05.06.02","CKD50602","9242531","Test Diagnostic controls","2008-05-02","2008-05-08",null,"C","SL_MFAT1","Hrs",40,null,3536.99136,null,3536.99136,null,40,null,3536.99136,null,3536.99136,{"$nulls":6},3536.99136,1,null,null,0.25,884.24784,1.15,1.1,5,4,"5A"]
["1","05","06","02","","","XT1620170","1.05.06.02","CKD50602","9242531","Install house air stubs","2008-04-29","2008-04-29",null,"C","SL_TMUP1","Hrs",16,null,1509.5879124479998,null,1509.5879124479998,null,16,null,1509.5879124479998,null,1509.5879124479998,{"$nulls":6},1509.5879124479998,1,null,null,0.25,377.39697811199994,1.15,1.1,4,4,"5A"]
["1","05","06","02","","","XT1620210","1.05.06.02","CKD50602","9242531","Install NEH cable tray stubs","2008-01-28","2008-01-28",null,"C","SL_TMUP1","Hrs",16,null,1509.5879124479998,null,1509.5879124479998,null,16,null,1509.5879124479998,null,1509.5879124479998,{"$nulls":6},1509.5879124479998,1,null,null,0.25,377.39697811199994,1.15,1.1,4,4,"5A"]
["1","05","06","02","","","XT1620260","1.05.06.02","CKD50602","9242531","Shield collimator C4","2008-07-31","2008-08-04",null,"C","SL_MFAT1","Hrs",48,null,4244.389632,null,4244.389632,null,48,null,4244.389632,null,4244.389632,{"$nulls":6},4244.389632,1,null,null,0.25,1061.097408,1.15,1.1,6,4,"5A"]
["1","05","06","02","","","XT1620300","1.05.06.02","CKD50602","9242531","Align penetration tube (NH-TN)","2008-03-28","2008-03-28",null,"C","LL_ME1","Hrs",4,null,743.586033876923,null,743.586033876923,null,4,null,743.586033876923,null,743.586033876923,{"$nulls":6},743.586033876923,1,null,null,0.25,185.89650846923075,1.15,1.1,4,4,"5A"]
["1","05","06","03","","","XT1630090","1.05.06.03","CKD50603","9242532","Test vacuum controls","2008-03-13","2008-03-26",null,"C","LL_CE1","Hrs",80,null,14871.72067753846,null,14871.72067753846,null,80,null,14871.72067753846,null,14871.72067753846,{"$nulls":6},14871.72067753846,1,null,null,0.25,3717.930169384615,1.15,1.1,4,4,"5A"]
["1","05","06","03","","","XT1630150","1.05.06.03","CKD50603","9242532","Install spools","2008-08-25","2008-08-28",null,"C","SL_TMUP1","Hrs",64,null,6038.351649791999,null,6038.351649791999,null,64,null,6038.351649791999,null,6038.351649791999,{"$nulls":6},6038.351649791999,1,null,null,0.25,1509.5879124479998,1.15,1.1,4,4,"5A"]
["1","05","06","03","","","XT1630250","1.05.06.03","CKD50603","9242532","Tunnel Vacuum Pumpdown","2008-09-02","2008-09-03",null,"C","LL_ME1","Hrs",16,null,2974.344135507692,null,2974.344135507692,null,16,null,2974.344135507692,null,2974.344135507692,{"$nulls":6},2974.344135507692,1,null,null,0.25,743.586033876923,1.15,1.1,4,4,"5A"]
["1","05","06","04","","","XT1640100","1.05.06.04","CKD50604","9242533","Test vacuum controls","2008-07-29","2008-08-11",null,"C","LL_ME1","Hrs",20,null,3717.930169384615,null,3717.930169384615,null,20,null,3717.930169384615,null,3717.930169384615,{"$nulls":6},3717.930169384615,1,null,null,0.25,929.4825423461538,1.15,1.1,4,4,"5A"]
["1","05","06","04","","","XT1640150","1.05.06.04","CKD50604","9242533","Align FEH vacuum tanks","2008-07-24","2008-07-28",null,"C","SL_MES1","Hrs",48,null,3954.2410345616636,null,3954.2410345616636,null,48,null,3954.2410345616636,null,3954.2410345616636,{"$nulls":6},3954.2410345616636,1,null,null,0.25,988.5602586404159,1.15,1.1,4,4,"5A"]
["1","05","06","05","","","XT1650020","1.05.06.05","CKD50605",null,"Install penetration drift tube/ground plate","2008-03-25","2008-03-25",null,"C","SL_MFAT1","Hrs",16,null,1414.796544,null,1414.796544,null,16,null,1414.796544,null,1414.796544,{"$nulls":6},1414.796544,1,null,null,0.25,353.699136,1.15,1.1,5,4,"5A"]
["1","06","01","01","  ","  ",{"$nulls":4},"Management                                                  ",{"$nulls":6},4021,63968,377549.5043634985,79593.936,457143.44036349846,null,2425.58,42600,230264.0979551645,53409.456000000006,283673.5539551645,0,null,0,null,82033.66053810397,null,201639.89341706052,null,0,null,null,62075.6563910329]
["1","06","01","01","","","XE_035","1.06.01.01","CAB60101","9242720","Management & Oversight - FY08","2007-10-01","2008-09-30","S","C","SL_EE1","Hrs",1712,null,163743.5574170605,null,163743.5574170605,null,1712,null,163743.5574170605,null,163743.5574170605,{"$nulls":6},163743.5574170605,1,null,null,0.2,32748.711483412102,1.2,1,4,1,"6A"]
["1","06","02","01","","","XE201_0410","1.06.02.01","CBC60201","9242536","Misc. Test Equipment  - FY08","2007-10-02","2008-09-30",null,"C","SL_MSEG1","$$",null,150000,null,165480.6672,165480.6672,null,null,150000,null,165480.6672,165480.6672,{"$nulls":6},165480.6672,1,null,null,0.25,41370.1668,1.15,1.1,2,3,"2H","B. Dalesio"]
["1","06","02","05","02","  ",{"$nulls":4},"Near Hall X-Ray PPS - Closed to BCWP                        "]
["1","06","02","07","01","","XE62710140","1.06.02.07.01","CBB6020701","9242733","Controls AMOS Final Design","2007-11-20","2008-05-14",null,"C","SL_CP1","Hrs",960,null,81172.04719373798,null,81172.04719373798,null,960,null,81172.04719373798,null,81172.04719373798,{"$nulls":6},81172.04719373798,1,null,null,0.25,20293.011798434494,1.15,1.1,5,2,"2H","B. Dalesio"]
["1","06","02","07","03","  ",{"$nulls":4},"Ion Imaging & Electron TOF                                  ",{"$nulls":6},1044,285400,89824.97226147699,306875.7792000001,396700.7514614771,null,1044,285400,89824.97226147699,306875.7792000001,396700.7514614771,0,null,0,null,351684.86247840995,null,45015.88898306715,null,0,null,null,99175.18786536927]
["1","06","02","07","03","","XE62730120","1.06.02.07.03","CBB6020703",null,"RCV: Crate/CPU/EVR","2007-08-28","2007-08-28",null,"C","SL_MSEG1","$$",null,9000,null,9677.232,9677.232,null,null,9000,null,9677.232,9677.232,{"$nulls":4},9677.232,1,{"$nulls":4},0.25,2419.308,1.15,1.1,2,3,"2H","B. Dalesio"]
["1","06","02","07","03","","XE62730200","1.06.02.07.03","CBB6020703",null,"RCV: Interrack Cables","2007-08-28","2007-08-28",null,"C","SL_MSEG1","$$",null,200,null,215.0496,215.0496,null,null,200,null,215.0496,215.0496,{"$nulls":4},215.0496,1,{"$nulls":4},0.25,53.7624,1.15,1.1,2,3,"2H","B. Dalesio"]
["1","06","02","07","04","","XE62740130","1.06.02.07.04","CBB6020704",null,"RCV: Valves","2007-03-30","2007-03-30",null,"C","SL_MSEG1","$$",null,12000,null,12902.976,12902.976,null,null,12000,null,12902.976,12902.976,{"$nulls":4},12902.976,1,{"$nulls":4},0.25,3225.744,1.15,1.1,2,3,"2H","B. Dalesio"]
["1","06","02","07","04","","XE62740145","1.06.02.07.04","CBB6020704",null,"RCV: Stepper Motor Drives","2007-03-30","2007-03-30",null,"C","SL_MSEG1","$$",null,6000,null,6451.488,6451.488,null,null,6000,null,6451.488,6451.488,{"$nulls":4},6451.488,1,{"$nulls":4},0.25,1612.872,1.15,1.1,2,3,"2H","B. Dalesio"]
["1","06","02","07","05","","XE62750130","1.06.02.07.05","CBB6020705",null,"RCV: Vacuum Pumps","2007-08-28","2007-08-28",null,"C","SL_MSEG1","$$",null,7400,null,7956.8351999999995,7956.8351999999995,null,null,7400,null,7956.8351999999995,7956.8351999999995,{"$nulls":4},7956.8351999999995,1,{"$nulls":4},0.25,1989.2087999999999,1.15,1.1,2,3,"2H","B. Dalesio"]
["1","06","02","07","06","","XE62760105","1.06.02.07.06","CBB6020706",null,"Refocus Optics Software","2007-06-04","2007-11-30",null,"C","SL_CP1","Hrs",261,null,21696.862054345667,null,21696.862054345667,null,261,null,21696.862054345667,null,21696.862054345667,{"$nulls":4},14424.170862944886,0.66,7272.6911914007815,0.34,null,null,0.25,5424.215513586417,1.15,1.1,5,2,"2H","B. Dalesio"]
["1","06","02","07","06","","XE62760175","1.06.02.07.06","CBB6020706",null,"RCV: Motor Controllers","2007-08-28","2007-08-28",null,"C","SL_MSEG1","$$",null,32000,null,34407.936,34407.936,null,null,32000,null,34407.936,34407.936,{"$nulls":4},34407.936,1,{"$nulls":4},0.25,8601.984,1.15,1.1,2,3,"2H","B. Dalesio"]
["1","06","02","07","07","","XE62770155","1.06.02.07.07","CBB6020707",null,"RCV:stepper motor drives","2007-04-30","2007-04-30",null,"C","SL_MSEG1","$$",null,36000,null,38708.928,38708.928,null,null,36000,null,38708.928,38708.928,{"$nulls":4},38708.928,1,{"$nulls":4},0.25,9677.232,1.15,1.1,2,3,"2H","B. Dalesio"]
["1","06","02","07","07","","XE62770190","1.06.02.07.07","CBB6020707",null,"RCV:power supply controllers","2007-04-30","2007-04-30",null,"C","SL_MSEG1","$$",null,4000,null,4300.992,4300.992,null,null,4000,null,4300.992,4300.992,{"$nulls":4},4300.992,1,{"$nulls":4},0.25,1075.248,1.15,1.1,2,3,"2H","B. Dalesio"]
["1","06","02","08","01","","XE62810125","1.06.02.08.01","CBB6020801","9242735","Controls AMOS Preliminary Design","2007-08-13","2007-10-22",null,"C","SL_CP1","Hrs",320,null,26577.384393063396,null,26577.384393063396,null,320,null,26577.384393063396,null,26577.384393063396,{"$nulls":4},18604.169075144375,0.7,7973.215317919018,0.3,null,null,0.25,6644.346098265849,1.15,1.1,5,2,"2H","B. Dalesio"]
["1","06","02","10","01","","XE221_0105","1.06.02.10.01","CBB6021001",null,"Develop Controls Network ICDs","2006-10-02","2006-11-15",null,"C","SL_CP1","Hrs",120,null,9889.381968048001,null,9889.381968048001,null,120,null,9889.381968048001,null,9889.381968048001,{"$nulls":4},9889.381968048001,1,{"$nulls":4},0.25,2472.3454920120002,1.15,1.1,5,2,"2H","B. Dalesio"]
["1","06","02","10","01","","XE221_0125","1.06.02.10.01","CBB6021001",null,"Controls Network Preliminary Design","2006-12-04","2007-01-12",null,"C","SL_CP1","Hrs",120,null,9889.381968048001,null,9889.381968048001,null,120,null,9889.381968048001,null,9889.381968048001,{"$nulls":4},9889.381968048001,1,{"$nulls":4},0.25,2472.3454920120002,1.15,1.1,5,2,"2H","B. Dalesio"]
["1","06","02","10","02","","XE222_0130","1.06.02.10.02","CBB6021002",null,"Preliminary Desgin Review (PDR)","2007-01-16","2007-01-31",null,"C","SL_CP1","Hrs",40,null,3296.460656016,null,3296.460656016,null,40,null,3296.460656016,null,3296.460656016,{"$nulls":4},3296.460656016,1,{"$nulls":4},0.25,824.115164004,1.15,1.1,5,2,"2H","B. Dalesio"]
["1","06","02","10","03","","XE223_0105","1.06.02.10.03","CBB6021003","9242401","Develop Controls PPS ICDs","2006-10-02","2006-11-15",null,"C","SL_CP1","Hrs",160,null,13185.842624064,null,13185.842624064,null,24,null,1977.8763936096002,null,1977.8763936096002,{"$nulls":4},1977.8763936096002,1,{"$nulls":4},0.25,494.46909840240005,1.15,1.1,5,2,"2H","B. Dalesio"]
["1","06","02","10","03","","XE223_0210","1.06.02.10.03","CBB6021003","9242401","RCV: Near Hall BSOIC","2007-07-24","2007-07-24",null,"C","SL_MSEG1","$$",null,67500,null,72579.24,72579.24,null,null,67500,null,72579.24,72579.24,{"$nulls":4},72579.24,1,{"$nulls":4},0.25,18144.81,1.15,1.1,2,3,"2H","B. Dalesio"]
["1","06","02","10","04","","XE224_0130","1.06.02.10.04","CBB6021004","9242402","Preliminary Desgin Review (PDR)","2007-01-16","2007-01-31",null,"C","SL_CP1","Hrs",40,null,3296.460656016,null,3296.460656016,null,40,null,3296.460656016,null,3296.460656016,{"$nulls":4},3296.460656016,1,{"$nulls":4},0.25,824.115164004,1.15,1.1,5,2,"2H","B. Dalesio"]
["1","06","02","10","04","","XE224_0185","1.06.02.10.04","CBB6021004","9242402","RCV: 36PR16AS cable","2007-03-30","2007-03-30",null,"C","SL_MSEG1","$$",null,6000,null,6451.488,6451.488,null,null,6000,null,6451.488,6451.488,{"$nulls":4},6451.488,1,{"$nulls":4},0.25,1612.872,1.15,1.1,2,3,"2H","B. Dalesio"]
["1","06","02","10","05","","XE225_0115","1.06.02.10.05","CBB6021005",null,"Safety Review Near Hall - User Safeguards","2007-03-14","2007-05-08",null,"C","SL_PHS1","Hrs",40,null,2925.5213465279994,null,2925.5213465279994,null,40,null,2925.5213465279994,null,2925.5213465279994,{"$nulls":4},2925.5213465279994,1,{"$nulls":4},0.25,731.3803366319999,1.15,1.1,5,3,"2H","B. Dalesio"]
["1","06","02","10","05","","XE225_0160","1.06.02.10.05","CBB6021005",null,"AWARD: Contract Near Hall Detectors - User Safe","2007-07-20","2007-07-20",null,"C","SL_AW1","$$",null,15000,null,16128.72,16128.72,null,null,15000,null,16128.72,16128.72,{"$nulls":4},16128.72,1,{"$nulls":9},3,"2H","B. Dalesio"]
["1","06","02","10","05","","XE225_0175","1.06.02.10.05","CBB6021005",null,"Vendor Fab/Ship Near Hall Detectors - User Safeg","2007-07-23","2007-09-17",null,"C","SA_MSEQ1","$$",null,15000,null,16128.72,16128.72,null,null,15000,null,16128.72,16128.72,{"$nulls":4},16128.72,1,{"$nulls":4},0.25,4032.18,1.15,1.1,2,3,"2H","B. Dalesio"]
["1","06","02","10","05","","XE225_0360","1.06.02.10.05","CBC6021005",null,"AWARD: Contract Far Hall Interlck - User Safegu","2008-05-07","2008-05-07",null,"C","SL_AW1","$$",null,5000,null,5516.02224,5516.02224,null,null,5000,null,5516.02224,5516.02224,{"$nulls":6},5516.02224,1,{"$nulls":7},3,"2H","B. Dalesio"]
["1","06","02","10","06","","XE226_0110","1.06.02.10.06","CBB6021006",null,"Controls Timing System Conceptual Design","2006-10-02","2006-11-15",null,"C","SL_CP1","Hrs",120,null,9889.381968048001,null,9889.381968048001,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,5,2,"2H","B. Dalesio"]
["1","06","02","10","07","","XE227_0110","1.06.02.10.07","CBB6021007",null,"Controls Data Management Conceptual Design","2006-08-01","2006-09-01",null,"C","SL_CP1","Hrs",109,null,8755.2195786,null,8755.2195786,null,109,null,8755.2195786,null,8755.2195786,null,null,8755.2195786,1,{"$nulls":6},0.3,2626.56587358,1.15,1.15,5,2,"2H","B. Dalesio"]
["1","06","02","10","07","","XE227_0165","1.06.02.10.07","CBB6021007",null,"RCV: Servers","2007-01-16","2007-01-16",null,"C","SL_MSEG1","$$",null,80000,null,86019.84,86019.84,null,null,80000,null,86019.84,86019.84,{"$nulls":4},86019.84,1,{"$nulls":4},0.3,25805.951999999997,1.15,1.15,4,3,"2H","B. Dalesio"]
["1","06","02","10","07","","XE227_0230","1.06.02.10.07","CBB6021007",null,"Controls Data Managment HW Release 3","2008-08-01","2008-12-12",null,"C","SL_CE1","Hrs",136,null,15993.957695439956,null,15993.957695439956,null,136,null,15993.957695439956,null,15993.957695439956,{"$nulls":6},7335.574582119078,0.46,8658.383113320879,0.54,0.3,4798.1873086319865,1.15,1.15,5,3,"2H","B. Dalesio"]
["1","06","02","10","08","","XE228_0170","1.06.02.10.08","CBB6021008",null,"Cabling & Racks Hardware Development","2007-04-02","2007-05-01",null,"C","SL_CE1","Hrs",240,null,27127.561576895998,null,27127.561576895998,null,240,null,27127.561576895998,null,27127.561576895998,{"$nulls":4},27127.561576895998,1,{"$nulls":4},0.25,6781.8903942239995,1.15,1.1,5,3,"2H","B. Dalesio"]
["1","06","02","10","09","","XE229_0165","1.06.02.10.09","CBB6021009",null,"RCV: 4 Laser End Point Synchronization Hardware","2008-03-31","2008-03-31",null,"C","SL_MSEG1","$$",null,120000,null,132384.53376000002,132384.53376000002,null,null,120000,null,132384.53376000002,132384.53376000002,{"$nulls":6},132384.53376000002,1,null,null,0.25,33096.133440000005,1.15,1.1,2,3,"2H","B. Dalesio"]
["1","06","02","10","10","","XE2210_005","1.06.02.10.10","CBB6021010",null,"Develop High Level Apps ICDs","2006-08-01","2006-09-01",null,"C","SL_CP1","Hrs",109,null,8755.2195786,null,8755.2195786,null,103.55,null,8317.458599669999,null,8317.458599669999,null,null,8317.458599669999,1,{"$nulls":6},0.25,2079.3646499174997,1.15,1.1,5,2,"2H","B. Dalesio"]
["1","06","02","10","10","","XE2210_115","1.06.02.10.10","CBB6021010",null,"Test Release 2","2008-06-02","2008-07-31",null,"C","SL_CP1","Hrs",218,null,18432.819050244667,null,18432.819050244667,null,218,null,18432.819050244667,null,18432.819050244667,{"$nulls":6},18432.819050244667,1,null,null,0.25,4608.204762561167,1.15,1.1,5,3,"2H","B. Dalesio"]
["1","06","02","11","","","XE624_0115","1.06.02.11","CBB60211",null,"Conceptual Design  Review (CDR)","2007-01-22","2007-02-02",null,"C","SL_CP1","Hrs",120,null,9889.381968048001,null,9889.381968048001,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,5,2,"2H","B. Dalesio"]
["1","06","02","12","","","XE629_0110","1.06.02.12","CBB60212",null,"K Measurement Spectrometer Conceptual Design","2006-08-01","2006-10-12",null,"C","SL_CP1","Hrs",20,null,1612.8435332789995,null,1612.8435332789995,null,15,null,1209.6326499592499,null,1209.6326499592499,null,null,1024.8276617710312,0.85,184.80498818821874,0.15,{"$nulls":4},0.25,302.40816248981247,1.15,1.1,5,2,"2H","B. Dalesio"]
["1","06","02","12","","","XE629_0140","1.06.02.12","CBB60212",null,"K Measurement Spectrometer Final Design","2007-01-30","2007-04-19",null,"C","SL_CP1","Hrs",40,null,3296.460656016,null,3296.460656016,null,40,null,3296.460656016,null,3296.460656016,{"$nulls":4},3296.460656016,1,{"$nulls":4},0.25,824.115164004,1.15,1.1,5,2,"2H","B. Dalesio"]
["1","06","03","02","04","  ",{"$nulls":4},"Turbo Pump - Vacuum                                         "]
["1","06","04","01","","","XE1410040","1.06.04.01","CBA60401",null,"Design Review - XES Laser","2007-06-26","2007-07-10","S","C","SL_OE1","Hrs",32,null,3617.0082102528,null,3617.0082102528,null,32,null,3617.0082102528,null,3617.0082102528,{"$nulls":4},3617.0082102528,1,{"$nulls":4},0.25,904.2520525632,1.15,1.1,4,2,"2L"]
["1","06","04","01","","","XE1410120","1.06.04.01","CBA60401",null,"Vendor Fab/Ship - XES Laser","2007-09-07","2008-03-14","S","C","SL_OE1","Hrs",120,null,13871.657082534992,null,13871.657082534992,null,120,null,13871.657082534992,null,13871.657082534992,{"$nulls":4},1761.4802644488877,0.13,12110.176818086104,0.87,null,null,0.25,3467.914270633748,1.15,1.1,4,3,"2L"]
["1","06","04","02","","","XE1420020","1.06.04.02","CAA60402","9242549","Engineering - Laser Diagnostics (thru Apr07)","2006-07-03","2007-04-30","S","C","SL_PHPU","Hrs",1262,null,154202.03904344057,null,154202.03904344057,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,2,"2L"]
["1","06","04","02","","","XE1420260","1.06.04.02","CBA60402","9242549","Prep Bid Pkg  Autocorrelators - Laser Diagnostic","2007-09-27","2007-10-10","S","C","SL_PHS1","Hrs",16,null,1191.2722923062013,null,1191.2722923062013,null,16,null,1191.2722923062013,null,1191.2722923062013,{"$nulls":4},366.5453207096004,0.31,824.7269715966008,0.69,null,null,0.25,297.8180730765503,1.15,1.1,4,2,"2L"]
["1","06","04","03","  ","  ",{"$nulls":4},"Laser Optical Transport                                     ",{"$nulls":6},2696,184000,259272.38903389484,202637.32259647158,348631.94932189485,null,2696,184000,259272.38903389484,202637.32259647158,461909.71163036645,0,null,0,null,201911.94763890043,null,259997.763991466,null,0,null,null,115477.42790759161]
["1","06","04","03","","","XE1430034","1.06.04.03","CKA60403","9242550","Final Design - Laser Optic Transport","2007-10-11","2007-11-21","S","C","SL_ME1","Hrs",240,null,24591.932438914362,null,24591.932438914362,null,240,null,24591.932438914362,null,24591.932438914362,{"$nulls":6},24591.932438914362,1,null,null,0.25,6147.9831097285905,1.15,1.1,4,2,"2L"]
["1","06","04","03","","","XE1430050","1.06.04.03","CKA60403","9242550","Prep Bid Pkg Lenses & Mirrors - Laser Optic Tran","2007-11-26","2007-12-07","S","C","SL_PHS1","Hrs",40,null,3001.584901537727,null,3001.584901537727,null,40,null,3001.584901537727,null,3001.584901537727,{"$nulls":6},3001.584901537727,1,null,null,0.25,750.3962253844318,1.15,1.1,4,2,"2L"]
["1","06","04","03","","","XE1430220","1.06.04.03","CKA60403","9242550","AWARD: Contract Cabinets - Laser Optic Transport","2008-01-24","2008-01-24","S","C","SL_AW1","$$",null,6000,null,6619.226688000001,6619.226688000001,null,null,6000,null,6619.226688000001,6619.226688000001,{"$nulls":6},6619.226688000001,1,null,null,0.25,1654.8066720000002,1.15,1.1,4,3,"2L"]
["1","06","04","04","","","XE1450070","1.06.04.04","CKA60404","9242551","Prepare for Laser Safety Committee Review","2008-03-05","2008-05-28","S","C","SL_OE1","Hrs",40,null,4638.813029649215,null,4638.813029649215,null,40,null,4638.813029649215,null,4638.813029649215,{"$nulls":6},4638.813029649215,1,null,null,0.25,1159.7032574123039,1.15,1.1,4,3,"2L"]
["1","06","05","04","01","  ",{"$nulls":4},"Detector Management                                         ",{"$nulls":6},4143,0,305674.8926843022,0,305674.8926843022,null,2610.09,0,192568.54209655532,0,192568.54209655532,0,null,21135.571693524365,null,85716.48520151548,null,85716.48520151548,null,0,null,null,38513.708419311064]
["1","06","06","  ","  ","  ",{"$nulls":4},"System Installation & Alignment                             ",{"$nulls":6},12192,0,1113341.2185857391,0,1113341.2185857391,null,12192,0,1113341.2185857391,0,1113341.2185857391,0,null,0,null,0,null,977489.6175116401,null,135851.6010740995,null,null,304232.5742686427]
["1","06","06","01","","","XE1610535","1.06.06.01","CKB60601","9242557","Install FEE BCS BSOIC's, cables, AC","2008-01-16","2008-01-22","S","C","SL_MFAT1","Hrs",64,null,5659.186176,null,5659.186176,null,64,null,5659.186176,null,5659.186176,{"$nulls":6},5659.186176,1,null,null,0.25,1414.796544,1.15,1.1,4,4,"6A"]
["1","06","06","01","","","XE1610580","1.06.06.01","CKB60601","9242557","Test/Certify FEE HPS","2008-04-07","2008-04-11","S","C","SL_CP1","Hrs",40,null,3382.1686330724156,null,3382.1686330724156,null,40,null,3382.1686330724156,null,3382.1686330724156,{"$nulls":6},3382.1686330724156,1,null,null,0.3,1014.6505899217246,1.2,1.1,4,4,"6A"]
["1","06","06","02","01","","XE1620210","1.06.06.02.01","CKB6060201","9242748","Install NEH racks","2008-01-28","2008-02-01","S","C","SL_TMUP1","Hrs",48,null,4528.763737343999,null,4528.763737343999,null,48,null,4528.763737343999,null,4528.763737343999,{"$nulls":6},4528.763737343999,1,null,null,0.25,1132.1909343359998,1.15,1.1,4,4,"6A"]
["1","06","06","02","01","","XE1620390","1.06.06.02.01","CKB6060201","9242748","Install/test NEH controls timing system","2008-02-19","2008-03-24","S","C","SL_CP1","Hrs",100,null,8455.42158268104,null,8455.42158268104,null,100,null,8455.42158268104,null,8455.42158268104,{"$nulls":6},8455.42158268104,1,null,null,0.4,3382.168633072416,1.3,1.1,4,4,"6A"]
["1","06","06","02","02","","XE1620200","1.06.06.02.02","CKB6060202","9242749","Install NEH N2 purge lines","2008-01-28","2008-02-01","S","C","SL_MFAT1","Hrs",80,null,7073.98272,null,7073.98272,null,80,null,7073.98272,null,7073.98272,{"$nulls":6},7073.98272,1,null,null,0.25,1768.49568,1.15,1.1,4,4,"6A"]
["1","06","06","02","03","","XE1620032","1.06.06.02.03","CKB6060203","9242750","Install Laser","2008-03-17","2008-04-11","S","C","SL_PHS1","Hrs",160,null,12006.339606150908,null,12006.339606150908,null,160,null,12006.339606150908,null,12006.339606150908,{"$nulls":6},12006.339606150908,1,null,null,0.25,3001.584901537727,1.15,1.1,4,4,"6A"]
["1","06","06","02","05","","XE1622010","1.06.06.02.05","CKB6060205",null,"Install High Field Physics Experiment","2008-07-28","2008-08-22","S","C","SL_MFAT1","Hrs",320,null,28295.93088,null,28295.93088,null,320,null,28295.93088,null,28295.93088,{"$nulls":6},28295.93088,1,null,null,0.25,7073.98272,1.15,1.1,4,4,"6A"]
["1","06","06","02","05","","XE1622010","1.06.06.02.05","CKB6060205",null,"Install High Field Physics Experiment","2008-07-28","2008-08-22","S","C","SL_CP1","Hrs",320,null,27057.349064579324,null,27057.349064579324,null,320,null,27057.349064579324,null,27057.349064579324,{"$nulls":6},27057.349064579324,1,null,null,0.25,6764.337266144831,1.15,1.1,4,4,"6A"]
["1","06","06","02","05","","XE1640300","1.06.06.02.05","CKB6060205",null,"Install Particle Imaging Experiment","2008-10-27","2008-11-21","S","C","SL_ME1","Hrs",160,null,16820.881850514357,null,16820.881850514357,null,160,null,16820.881850514357,null,16820.881850514357,{"$nulls":8},16820.881850514357,1,0.25,4205.220462628589,1.15,1.1,4,4,"6A"]
["1","06","06","02","05","","XE1640300","1.06.06.02.05","CKB6060205",null,"Install Particle Imaging Experiment","2008-10-27","2008-11-21","S","C","SL_CE1","Hrs",160,null,19037.688744187366,null,19037.688744187366,null,160,null,19037.688744187366,null,19037.688744187366,{"$nulls":8},19037.688744187366,1,0.25,4759.4221860468415,1.15,1.1,4,4,"6A"]
["1","06","06","02","06","","XE1620350","1.06.06.02.06","CKB6060206",null,"Shield beam pipe","2008-04-29","2008-05-01","S","C","SL_MFAT1","Hrs",48,null,4244.389632,null,4244.389632,null,48,null,4244.389632,null,4244.389632,{"$nulls":6},4244.389632,1,null,null,0.3,1273.3168896,1.2,1.1,4,4,"6A"]
["1","06","06","02","07","","XE1620281","1.06.06.02.07","CKB6060207",null,"Install Laser PPS Finish","2008-06-26","2008-07-24","S","C","SL_CT1","Hrs",80,null,5079.236970544703,null,5079.236970544703,null,80,null,5079.236970544703,null,5079.236970544703,{"$nulls":6},5079.236970544703,1,null,null,0.25,1269.8092426361757,1.15,1.1,4,4,"6A"]
["1","06","06","03","","","XE1630210","1.06.06.03","CKB60603","9242559","Install Tunnel PPS cables, chassis, keybank","2008-02-13","2008-02-25","S","C","SL_CP1","Hrs",32,null,2705.7349064579325,null,2705.7349064579325,null,32,null,2705.7349064579325,null,2705.7349064579325,{"$nulls":6},2705.7349064579325,1,null,null,0.25,676.4337266144831,1.15,1.1,4,4,"6A"]
["1","06","06","03","","","XE1630270","1.06.06.03","CKB60603","9242559","Wire Tunnel doors","2008-02-21","2008-02-22","S","C","SL_CE1","Hrs",4,null,463.88130296492153,null,463.88130296492153,null,4,null,463.88130296492153,null,463.88130296492153,{"$nulls":6},463.88130296492153,1,null,null,0.25,115.97032574123038,1.15,1.1,4,4,"6A"]
["1","06","06","04","01","","XE1640127","1.06.06.04.01","CKB6060401","9242752","Test/Certify MPS","2008-09-09","2008-09-15","S","C","SL_CE1","Hrs",40,null,4638.813029649215,null,4638.813029649215,null,40,null,4638.813029649215,null,4638.813029649215,{"$nulls":6},4638.813029649215,1,null,null,0.4,1855.5252118596864,1.3,1.1,4,4,"6A"]
["1","06","06","04","01","","XE1640185","1.06.06.04.01","CKB6060401","9242752","Install/test FEH controls timing system","2008-06-23","2008-07-14","S","C","SL_CE1","Hrs",50,null,5798.5162870615195,null,5798.5162870615195,null,50,null,5798.5162870615195,null,5798.5162870615195,{"$nulls":6},5798.5162870615195,1,null,null,0.4,2319.4065148246077,1.3,1.1,4,4,"6A"]
["1","06","06","04","05","","XE1640203","1.06.06.04.05","CKB6060405",null,"Install FEH PPS cables, chassis, lights","2008-04-08","2008-04-21","S","C","SL_CT1","Hrs",15,null,952.3569319771318,null,952.3569319771318,null,15,null,952.3569319771318,null,952.3569319771318,{"$nulls":6},952.3569319771318,1,null,null,0.25,238.08923299428295,1.15,1.1,4,4,"6A"]
["1","06","06","04","05","","XE1640225","1.06.06.04.05","CKB6060405",null,"Install FEH BCS BSOIC's, cables, AC","2008-04-07","2008-04-09","S","C","SL_MFAT1","Hrs",48,null,4244.389632,null,4244.389632,null,48,null,4244.389632,null,4244.389632,{"$nulls":6},4244.389632,1,null,null,0.25,1061.097408,1.15,1.1,4,4,"6A"]
["1","06","06","05","","","XE1650090","1.06.06.05","CKB60605",null,"Install stopper tank/collimator/fast valve","2008-03-21","2008-03-24","S","C","SL_TMUP1","Hrs",32,null,3019.1758248959995,null,3019.1758248959995,null,32,null,3019.1758248959995,null,3019.1758248959995,{"$nulls":6},3019.1758248959995,1,null,null,0.25,754.7939562239999,1.15,1.1,4,4,"6A"]
["1","06","07","01","  ","  ",{"$nulls":4},"AP Management & Design                                      ",{"$nulls":6},6778,0,739126.2220825946,0,739126.2220825946,null,5022,0,545071.1476088347,0,545071.1476088347,0,null,0,null,361554.5074950391,null,183516.64011379544,null,0,null,null,128146.85763370318]
["1","06","07","01","01","","XE1711190","1.06.07.01","CBA60701","9242920","Plan assembly/installation of diagnostics","2008-02-20","2008-03-18","S","C","SL_PHPU","Hrs",30,null,3789.6804588194627,null,3789.6804588194627,null,30,null,3789.6804588194627,null,3789.6804588194627,{"$nulls":6},3789.6804588194627,1,null,null,0.2,757.9360917638926,1.1,1.1,4,4,"6A"]
["1","06","07","01","02","","XE1712010","1.06.07.01","CBA60701","9242920","Conceptual Engr. - X1 High Field Physics","2006-07-07","2006-11-03","S","C","SL_ME1","Hrs",160,null,15686.52484293862,null,15686.52484293862,null,0,null,0,null,0,{"$nulls":10},0.25,0,1.15,1.1,4,2,"6A"]
["1","06","07","01","02","","XE1712060","1.06.07.01","CBA60701","9242920","System concept review (SCR)","2006-12-06","2007-01-04","S","C","SL_ME1","Hrs",160,null,15979.163378111998,null,15979.163378111998,null,16,null,1597.9163378111998,null,1597.9163378111998,{"$nulls":4},1597.9163378111998,1,{"$nulls":4},0.2,319.58326756224,1.1,1.1,5,2,"6A"]
["1","06","07","01","03","","XE1713010","1.06.07.01","CBA60701","9242920","Preliminary design - X1 High Field Physics","2007-01-22","2007-04-02","S","C","SL_ME1","Hrs",400,null,39947.908445279994,null,39947.908445279994,null,160,null,15979.163378111998,null,15979.163378111998,{"$nulls":4},15979.163378111998,1,{"$nulls":4},0.25,3994.7908445279995,1.15,1.1,4,2,"6A"]
["1","06","07","01","04","","XE1714010","1.06.07.01","CBA60701","9242920","Specify components - X1 High Field Physics","2007-04-03","2007-05-07","S","C","SL_ME1","Hrs",100,null,9986.977111319999,null,9986.977111319999,null,100,null,9986.977111319999,null,9986.977111319999,{"$nulls":4},9986.977111319999,1,{"$nulls":4},0.25,2496.7442778299996,1.15,1.1,4,2,"6A"]
["1","06","07","01","04","","XE1714030","1.06.07.01","CBA60701","9242920","Specify components - Refocus optics","2007-04-17","2007-04-30","S","C","SL_ME1","Hrs",80,null,7989.581689055999,null,7989.581689055999,null,80,null,7989.581689055999,null,7989.581689055999,{"$nulls":4},7989.581689055999,1,{"$nulls":4},0.35,2796.3535911695994,1.25,1.1,4,2,"6A"]
["1","06","07","02","","","XE1720510","1.06.07.02","CKA60702",null,"Readiness/Safety Review - X1 High Field Physics","2008-09-23","2008-10-06","S","C","SL_PHPU","Hrs",80,null,10206.872717189835,null,10206.872717189835,null,80,null,10206.872717189835,null,10206.872717189835,{"$nulls":6},6281.152441347592,0.62,3925.7202758422445,0.38,0.25,2551.718179297459,1.15,1.1,5,3,"6A"]
["1","06","07","02","","","XE1720520","1.06.07.02","CKA60702",null,"Testing - X1 High Field Physics","2008-10-07","2008-11-03","S","C","SL_MFAT1","Hrs",80,null,7257.906297599999,null,7257.906297599999,null,80,null,7257.906297599999,null,7257.906297599999,{"$nulls":8},7257.906297599999,1,0.35,2540.2672041599994,1.25,1.1,4,3,"6A"]
["1","06","07","02","01","","XE1721080","1.06.07.02","CKA60702",null,"Testing - X-Ray Fluor. Detector","2008-10-21","2008-11-10","S","C","SL_PHPD1","Hrs",120,null,8882.781241966679,null,8882.781241966679,null,120,null,8882.781241966679,null,8882.781241966679,{"$nulls":8},8882.781241966679,1,0.25,2220.6953104916697,1.15,1.1,4,3,"6A"]
["1","06","07","02","02","","XE1722060","1.06.07.02","CKA60702",null,"Bid/Evaluate/RFP - Ion Imaging Detector","2007-06-13","2007-10-04","S","C","SL_PHPU","Hrs",80,null,9856.520713309696,null,9856.520713309696,null,80,null,9856.520713309696,null,9856.520713309696,{"$nulls":4},9594.843172248377,0.97,261.67754106131935,0.03,null,null,0.35,3449.782249658393,1.25,1.1,4,3,"6A"]
["1","06","07","02","02","","XE1722550","1.06.07.02","CKA60702",null,"Assemble - Ion Imaging Detector","2008-05-30","2008-07-25","S","C","SL_MFAT1","Hrs",120,null,10610.97408,null,10610.97408,null,120,null,10610.97408,null,10610.97408,{"$nulls":6},10610.97408,1,null,null,0.25,2652.74352,1.15,1.1,4,3,"6A"]
["1","06","07","02","03","  ",{"$nulls":4},"Sample Source                                               ",{"$nulls":6},600,129246,63566.48302974329,142584.762086208,206151.24511595131,null,600,129246,63566.48302974329,142584.762086208,206151.24511595131,0,null,0,null,8688.840295727845,null,197462.40482022343,null,0,null,null,52463.34944831357]
["1","06","07","02","04","  ",{"$nulls":4},"Vacuum System                                               ",{"$nulls":6},120,195837,13854.06902408436,216048.249482976,229902.31850706038,null,120,195837,13854.06902408436,216048.249482976,229902.31850706038,0,null,0,null,13486.261881852031,null,216416.05662520835,null,0,null,null,79080.4045750627]
["1","06","07","02","04","","XE1724030","1.06.07.02","CKA60702",null,"AWARD: X1 Vacuum System","2007-11-02","2007-11-02","S","C","SL_AW1","$$",null,195837,null,216048.249482976,216048.249482976,null,null,195837,null,216048.249482976,216048.249482976,{"$nulls":6},216048.249482976,1,null,null,0.25,54012.062370744,1.15,1.1,3,3,"6A"]
["1","06","07","03","","","XE1730090","1.06.07.03","CKA60703",null,"Fab/Deliver - Optics Chamber","2007-11-05","2008-04-30","S","C","SA_MSEQ1","$$",null,27881,null,30758.443214688003,30758.443214688003,null,null,27881,null,30758.443214688003,30758.443214688003,{"$nulls":6},30758.443214688003,1,null,null,0.29,8919.948532259521,1.19,1.1,4,3,"6A"]
["1","06","07","03","","","XE1730130","1.06.07.03","CKA60703",null,"AWARD: Focus Verification","2007-11-02","2007-11-02","S","C","SL_AW1","$$",null,34000,null,37508.951232,37508.951232,null,null,34000,null,37508.951232,37508.951232,{"$nulls":6},37508.951232,1,null,null,0.35,13128.1329312,1.25,1.1,4,3,"6A"]
["1","06","07","04","","","XE1740080","1.06.07.04","CKA60704",null,"AWARD: Diagnostic Equipment","2007-11-02","2007-11-02","S","C","SL_AW1","$$",null,282605,null,311771.09302704,311771.09302704,null,null,282605,null,311771.09302704,311771.09302704,{"$nulls":6},311771.09302704,1,null,null,0.35,109119.882559464,1.25,1.1,3,3,"6A"]
["1","06","07","04","","","XE1740520","1.06.07.04","CKA60704",null,"Testing - Diagnostic Equipment","2008-08-29","2008-12-23","S","C","SL_PHPU","Hrs",160,null,20587.635165443906,null,20587.635165443906,null,160,null,20587.635165443906,null,20587.635165443906,{"$nulls":6},5856.827245341801,0.28,14730.807920102106,0.72,0.2,4117.5270330887815,1.1,1.1,4,3,"6A"]
["1","06","09","01","  ","  ",{"$nulls":4},"PPS Stoppers                                                ",{"$nulls":6},2408,300000,226639.99013497398,322574.4,549214.390134974,null,2248,300000,213020.99615790203,322574.4,535595.396157902,0,null,0,null,493277.216642289,null,42318.179515612945,null,0,null,null,133898.8490394755]
["1","06","09","01","","","XE1920090","1.06.09.01","CBA60901","9242404","Prepare for Safety Review - PPS Beam Stop Hardwa","2006-10-30","2006-11-28","S","C","SL_ME1","Hrs",80,null,7989.581689055999,null,7989.581689055999,null,80,null,7989.581689055999,null,7989.581689055999,{"$nulls":4},7989.581689055999,1,{"$nulls":4},0.25,1997.3954222639998,1.15,1.1,4,3,"6A"]
["1","06","09","01","","","XE1920200","1.06.09.01","CBA60901","9242404","Assemble Tunnel - PPS Beam Stop Hardware","2007-10-12","2007-12-10","S","C","SL_MFMS1","Hrs",80,null,9053.687312639999,null,9053.687312639999,null,80,null,9053.687312639999,null,9053.687312639999,{"$nulls":6},9053.687312639999,1,null,null,0.25,2263.4218281599997,1.15,1.1,4,2,"6A"]
["1","06","09","01","","","XE1920220","1.06.09.01","CBA60901","9242404","Assemble EDE - PPS Beam Stop Hardware","2007-06-20","2007-08-15","S","C","SL_MFMS1","Hrs",80,null,8824.25664,null,8824.25664,null,80,null,8824.25664,null,8824.25664,{"$nulls":4},8824.25664,1,{"$nulls":4},0.25,2206.06416,1.15,1.1,4,4,"6A"]
["1","06","09","02","","","XE1922070","1.06.09.02","CBA60902","9242405","Prepare Final Design - PPS Shielding & Supports","2007-04-19","2007-05-16","S","C","SL_MDD1","Hrs",160,null,13397.363572032,null,13397.363572032,null,160,null,13397.363572032,null,13397.363572032,{"$nulls":4},13397.363572032,1,{"$nulls":4},0.25,3349.340893008,1.15,1.1,4,3,"6A"]
["1","06","09","02","","","XE1922090","1.06.09.02","CBA60902","9242405","Final Design Review - PPS Shielding & Supports","2007-05-17","2007-05-31","S","C","SL_MDD1","Hrs",80,null,6698.681786016,null,6698.681786016,null,80,null,6698.681786016,null,6698.681786016,{"$nulls":4},6698.681786016,1,{"$nulls":4},0.25,1674.670446504,1.15,1.1,4,3,"6A"]
["1","06","09","02","","","XE1922170","1.06.09.02","CBA60902","9242405","Fab/Assemble NH - PPS Shielding & Supports","2007-09-12","2007-09-18","S","C","SL_MFAT1","Hrs",40,null,3447.36,null,3447.36,null,40,null,3447.36,null,3447.36,{"$nulls":4},3447.36,1,{"$nulls":4},0.25,861.84,1.15,1.1,4,4,"6A"]
["1","06","09","02","","","XE1922190","1.06.09.02","CBA60902","9242405","Fab/Assemble FH - PPS Shielding & Supports","2007-09-26","2007-10-02","S","C","SL_ME1","Hrs",10,null,1003.025401213572,null,1003.025401213572,null,10,null,1003.025401213572,null,1003.025401213572,{"$nulls":4},835.85450101131,0.83,167.17090020226198,0.17,null,null,0.25,250.756350303393,1.15,1.1,4,2,"6A"]
["1","06","09","03","","","XE19300110","1.06.09.03","CBA60903",null,"Final Design Review - NEH Hutch Doors","2007-07-30","2007-08-10","S","C","SL_MDD1","Hrs",40,null,3349.340893008,null,3349.340893008,null,40,null,3349.340893008,null,3349.340893008,{"$nulls":4},3349.340893008,1,{"$nulls":4},0.25,837.335223252,1.15,1.1,4,2,"6A"]
["1","09","01","01","","","CFMGT_1095","1.09.01.01","9242338","9242338","Construction Management Consulting - FY06 (rem)","2006-09-01","2006-09-29",null,"C","SL_MSPF1","$$",null,83988,null,83988,83988,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,3,1,"9A"]
["1","09","01","01","","","CFMGT_1130","1.09.01.01","CK90101","9242338","Management - FY08","2007-10-01","2008-09-30",null,"C","SL_SEEM1","Hrs",1701,null,185322.37574076696,null,185322.37574076696,null,1701,null,185322.37574076696,null,185322.37574076696,{"$nulls":6},185322.37574076696,1,null,null,0.2,37064.4751481534,1.1,1.1,3,1,"9A"]
["1","09","01","02","  ","  ",{"$nulls":4},"CF Engineering                                              ",{"$nulls":6},8133,2017286,867604.8460827314,2062562.6740662046,1355864.8460827314,null,4355.82,759373,468450.43819476815,782011.3370331023,1250461.7752278703,0,null,12238.254808287651,null,603347.9586623269,null,634875.5617572558,null,0,null,null,341434.26516174065]
["1","09","01","02","","","CFENG_1235","1.09.01.02","CK90102","9242376","AWARD: FEH Hutches - A&E Design","2007-10-01","2007-10-01",null,"C","SL_AWFY1","$$",null,233260,null,233260,233260,null,null,233260,null,233260,233260,{"$nulls":6},233260,1,null,null,0.4,93304,1.3,1.1,3,1,"9A"]
["1","09","01","03","","","CFUTR_1000","1.09.01.03","8819011","9242257","CF Construction Management - FY06 (remain)","2006-09-01","2006-09-29",null,"C","SL_UTR1","Hrs",420,null,43468.846344,null,43468.846344,null,0,null,0,null,0,{"$nulls":10},0.1,0,1,1.1,3,1,"9A"]
["1","09","01","03","","","CFUTR_1060","1.09.01.03","K8819011","9242257","CF Construction Management - FY08 (Oct-Nov07)","2007-10-01","2007-11-30",null,"C","SL_UTR1","Hrs",1505,null,163968.3571368926,null,163968.3571368926,null,1505,null,163968.3571368926,null,163968.3571368926,{"$nulls":6},163968.3571368926,1,null,null,0.3,49190.50714106778,1.2,1.1,3,1,"9A"]
["1","09","01","04","02","  ",{"$nulls":4},"Mechanical Design T1 Linac Facilities                       "]
["1","09","01","05","02","  ",{"$nulls":4},"CEF Engineering Title 1 Linac Facility                      "]
["1","09","02","02","02","  ",{"$nulls":4},"Title 2 Design                                              ",{"$nulls":6},0,27100,0,27100,0,null,0,4250,0,4250,4250,0,null,607.1428571428571,null,3642.8571428571427,null,0,null,0,null,null,1275]
["1","09","03","01","01","  ",{"$nulls":4},"S20 - Site Preparation/General Requirements                 "]
["1","09","03","01","04","  ",{"$nulls":4},"S20 - Masonry                                               "]
["1","09","03","01","20","","CFS20_4660","1.09.03.01.20","9242354","9242354","S20 Project Close Out for LOTO","2006-09-01","2006-09-29",null,"C","SL_MSPY1","$$",null,9954,null,9954,9954,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,7,3,"9A"]
["1","09","03","02","01","  ",{"$nulls":4},"MMF - Site Preparation/General Requirements                 "]
["1","09","03","02","08","  ",{"$nulls":4},"MMF - Doors & Windows                                       "]
["1","09","03","02","20","","CFMMF_4530","1.09.03.02.20","9242371",null,"MMF Furnishing","2006-09-01","2006-09-29",null,"C","SL_MSPF1","$$",null,7812,null,7812,7812,null,null,0,null,0,0,{"$nulls":10},0.1,0,1,1.1,7,3,"9A"]
["1","09","03","03","20","  ",{"$nulls":4},"BTH West - Project Close Out                                ",{"$nulls":6},0,30000,0,30000,0,null,0,30000,0,30000,30000,0,null,0,null,13090.90909090909,null,16909.090909090908,null,0,null,null,15000]
["1","09","03","04","05","  ",{"$nulls":4},"Linac - Metals                                              "]
["1","09","03","04","16","","CFLNF_3170","1.09.03.04.16","9242761","9242761","Linac Electrical Equipment","2006-09-05","2006-10-31",null,"C","SL_MSEG1","$$",null,20000,null,21251.942857142858,null,null,null,0,null,0,0,{"$nulls":10},0.3,0,1.1,1.2,3,3,"9A"]
["1","09","03","04","16","","CFLNF_3200","1.09.03.04.16","9242761","9242761","AWARD: I&C/PS Electrical Branch Circuit Feeders","2008-01-02","2008-01-02",null,"C","SL_AW1","$$",null,1038000,null,1145126.2170240001,1145126.2170240001,null,null,1038000,null,1145126.2170240001,1145126.2170240001,{"$nulls":6},1145126.2170240001,1,null,null,0.3,343537.86510720005,1.1,1.2,3,3,"9A"]
["1","09","03","05","01","","CF05033060","1.09.03.05.01","9242379","9242379","SLAC RSY through CLOC  - Site Preparation - Rem","2006-09-01","2007-01-31",null,"C","SL_TMUC1","Hrs",461,null,68390.54811473684,null,68390.54811473684,null,115.25,null,17060.548878947367,null,17060.548878947367,null,null,3367.2135945290856,0.2,13693.335284418283,0.8,{"$nulls":4},0.2,3412.1097757894736,1.1,1.1,3,3,"9A"]
["1","09","03","05","01","","CF05033105","1.09.03.05.01","9242379","9242379","Tunnel Rescue Team Equipment - Remain","2006-09-01","2007-01-23",null,"C","SL_MSPF1","$$",null,41000,null,41000,null,null,null,0,null,0,0,{"$nulls":10},0.2,0,1.1,1.1,7,3,"9A"]
["1","09","03","05","02","","GCRY11300","1.09.03.05.02","8819020","9242763","U/G Mechanical Utility (Except FFTB) - SUMMARY","2007-01-18","2007-02-09",6,"C","SL_GCFX1","$$",null,141494,null,141494,141494,null,null,7074.7,null,7074.7,7074.7,{"$nulls":4},7074.7,1,{"$nulls":4},0.15,1061.205,1,1.15,"SI","P2","9A"]
["1","09","03","05","04","02",{"$nulls":4},"Utilities G/C                                               "]
["1","09","03","05","20","","CF05033035","1.09.03.05.20","9242789","9242789","Start: Third Party Testing - Beam Path - 2006","2006-09-05","2007-02-28",null,"C","SL_MSSF1","$$",null,100000,null,100000,null,null,null,20000,null,20000,20000,null,null,2954.5454545454545,0.15,17045.454545454544,0.85,{"$nulls":4},0.2,4000,1.1,1.1,7,3,"9A"]
["1","09","03","06","01","","GCEQ1000","1.09.03.06.01","9242811","9242811","Pre-Construction / Bid / Award (45%)","2006-08-01","2006-08-02",8,"C","SL_GCFX1","$$",null,160751,null,160751,160751,null,null,16075.1,null,16075.1,16075.1,null,null,16075.1,1,{"$nulls":6},0.15,2411.265,1,1.15,"EQ","P2","9A"]
["1","09","03","06","11","  ",{"$nulls":4},"Pre-Purchase Equipment for Beam Path                        ",{"$nulls":6},0,1719727,0,1719727,158866,null,0,1719727,0,1719727,1719727,0,null,0,null,311916.9055408404,null,1407810.0944591595,null,0,null,null,257959.05]
["1","09","03","06","11","","GCEQ2020","1.09.03.06.11","9242812","9242812","Vendor Equipment Startup / Commissioning (10%)","2008-01-08","2008-05-20",8,"C","SL_GCFX1","$$",null,158866,null,158866,158866,null,null,158866,null,158866,158866,{"$nulls":6},158866,1,null,null,0.15,23829.899999999998,1,1.15,"EC","P2","9A"]
["1","09","03","07","01","","GCMO1158","1.09.03.07.01","9242814","9242814","General Requirements Work - Feb 07","2007-01-22","2007-02-20",10,"C","SL_GCFX1","$$",null,75980,null,75980,75980,null,null,0,null,0,0,{"$nulls":10},0,0,1,1,"SI","P2","9A"]
["1","09","03","07","01","","GCMO1166","1.09.03.07.01","9242814","9242814","General Requirements Work - May 07","2007-04-23","2007-05-18",10,"C","SL_GCFX1","$$",null,81875,null,81875,81875,null,null,81875,null,81875,81875,{"$nulls":4},81875,1,{"$nulls":4},0.15,12281.25,1,1.15,"SI","P2","9A"]
["1","09","03","07","01","","GCMO1184","1.09.03.07.01","9242814","9242814","General Requirements Work - Dec 07","2007-11-21","2007-12-20",10,"C","SL_GCFX1","$$",null,81875,null,81875,81875,null,null,81875,null,81875,81875,{"$nulls":6},81875,1,null,null,0.15,12281.25,1,1.15,"SI","P2","9A"]
["1","09","03","07","02","","GCAC1138","1.09.03.07.02","9242815","9242815","Survey & Layout FEH Access Tunnel","2006-11-13","2006-11-14",2,"C","SL_GCFX1","$$",null,7000,null,7000,7000,null,null,0,null,0,0,{"$nulls":10},0,0,1,1,"AC","P2","9A"]
["1","09","03","07","02","","GCBT90624","1.09.03.07.02","9242815","9242815","BTH East Mud Slab","2007-08-08","2007-08-09",2,"C","SL_GCFX1","$$",null,10000,null,10000,10000,null,null,10000,null,10000,10000,{"$nulls":4},10000,1,{"$nulls":4},0.15,1500,1,1.15,"H6","P2","9A"]
["1","09","03","07","02","","GCFCO003","1.09.03.07.02","9242815","9242815","FCO #003 - Temporary Snow Fence","2006-09-22","2006-09-29",null,"C","SL_GCFX1","$$",null,4121,null,4121,4121,null,null,0,null,0,0,{"$nulls":10},0,0,1,1,"O1","P2","9A"]
["1","09","03","07","02","","GCFCO028","1.09.03.07.02","9242815","9242815","FCO #028 - Encase 12\" SD Line & Relocate CBs(RY)","2007-01-29","2007-01-31",null,"C","SL_GCFX1","$$",null,16248,null,16248,16248,null,null,0,null,0,0,{"$nulls":10},0,0,1,1,"O2","P2","9A"]
["1","09","03","07","02","","GCMO1122","1.09.03.07.02","9242815","9242815","Install Trailer Water & Sanitary Serv Undergrnd","2006-09-27","2006-10-03",4,"C","SL_GCFX1","$$",null,16725,null,16725,null,null,null,0,null,0,0,{"$nulls":10},0,0,1,1,"SI","P2","9A"]
["1","09","03","07","02","","GCRY1128","1.09.03.07.02","9242815","9242815","RSY Storm Drain East","2006-12-12","2007-01-19",4,"C","SL_GCFX1","$$",null,94200,null,94200,94200,null,null,0,null,0,0,{"$nulls":10},0,0,1,1,"SI","P2","9A"]
["1","09","03","07","02","","GCRY11324","1.09.03.07.02","9242815","9242815","RSY Precast Utility Trench","2006-11-20","2007-02-16",4,"C","SL_GCFX1","$$",null,69000,null,69000,69000,null,null,0,null,0,0,{"$nulls":10},0.15,0,1,1.15,"SI","P2","9A"]
["1","09","03","07","02","","GCST1040","1.09.03.07.02","9242815","9242815","Clear & Grub NEH / CLOC Area","2006-09-25","2006-09-26",2,"C","SL_GCFX1","$$",null,25000,null,25000,25000,null,null,0,null,0,0,{"$nulls":10},0,0,1,1,"SI","P2","9A"]
["1","09","03","07","02","","GCST1106","1.09.03.07.02","9242815","9242815","Complete Mass Exc/Cut & Fill Oper (Outside NEH)","2006-10-23","2007-05-07",2,"C","SL_GCFX1","$$",null,140000,null,140000,140000,null,null,56000,null,56000,56000,{"$nulls":4},56000,1,{"$nulls":4},0.15,8400,1,1.15,"SI","P2","9A"]
["1","09","03","07","02","","GCST1176","1.09.03.07.02","9242815","9242815","NEH Wall Control Lines","2007-01-02","2007-06-06",1,"C","SL_GCFX1","$$",null,7920,null,7920,7920,null,null,3960,null,3960,3960,{"$nulls":4},3960,1,{"$nulls":4},0.15,594,1,1.15,"SI","P2","9A"]
["1","09","03","07","02","","GCST1194","1.09.03.07.02","9242815","9242815","Site Topo Upon Completion of Mass Grading","2007-05-08","2007-07-20",1,"C","SL_GCFX1","$$",null,5466,null,5466,5466,null,null,5466,null,5466,5466,{"$nulls":4},5466,1,{"$nulls":4},0.15,819.9,1,1.15,"SI","P2","9A"]
["1","09","03","07","07","  ",{"$nulls":4},"Interior                                                    "]
["1","09","03","07","16","","GCMO2328","1.09.03.07.16","9242818","9242818","Temporary Power (Trailer City)","2006-10-05","2007-05-30",7,"C","SL_GCFX1","$$",null,655032,null,655032,655032,null,null,32751.6,null,32751.6,32751.6,{"$nulls":4},32751.6,1,{"$nulls":4},0.15,4912.74,1,1.15,"SI","P2","9A"]
["1","09","03","08","01","","GCIN1320","1.09.03.08.01","9242821","9242821","Bond - Cupertino Electric","2006-09-07","2006-09-07",7,"C","SL_GCFX1","$$",null,83579,null,83579,83579,null,null,0,null,0,0,{"$nulls":10},0,0,1,1,"I3","P2","9A"]
["1","09","03","08","03","","GCBT2300","1.09.03.08.03","9242823","9242823","BTH HH Form Mat Pour #1","2007-03-26","2007-04-02",5,"C","SL_GCFX1","$$",null,33284,null,33284,33284,null,null,0,null,0,0,{"$nulls":10},0.15,0,1,1.15,"Y1","P2","9A"]
["1","09","03","08","03","","GCBT2640","1.09.03.08.03","9242823","9242823","BTH HH Rebar Walls Pour #1","2007-04-05","2007-04-13",5,"C","SL_GCFX1","$$",null,42910,null,42910,42910,null,null,0,null,0,0,{"$nulls":10},0.15,0,1,1.15,"Y1","P2","9A"]
["1","09","03","08","03","","GCBT3520","1.09.03.08.03","9242823","9242823","BTH Pour Mat Pour #1","2007-05-18","2007-05-18",5,"C","SL_GCFX1","$$",null,89513,null,89513,89513,null,null,89513,null,89513,89513,{"$nulls":4},89513,1,{"$nulls":4},0.15,13426.949999999999,1,1.15,"H1","P2","9A"]
["1","09","03","08","03","","GCBT6052","1.09.03.08.03","9242823","9242823","BTH Form Walls #2 Pour #1","2007-07-13","2007-07-19",5,"C","SL_GCFX1","$$",null,93609,null,93609,93609,null,null,93609,null,93609,93609,{"$nulls":4},93609,1,{"$nulls":4},0.15,14041.35,1,1.15,"H1","P2","9A"]
["1","09","03","08","03","","GCBT90440","1.09.03.08.03","9242823","9242823","BTH Form Mat Pour #2","2007-04-16","2007-05-01",5,"C","SL_GCFX1","$$",null,33252,null,33252,33252,null,null,3325.2,null,3325.2,3325.2,{"$nulls":4},3325.2,1,{"$nulls":4},0.15,498.78,1,1.15,"H2","P2","9A"]
["1","09","03","08","03","","GCBT9100","1.09.03.08.03","9242823","9242823","BTH Pour Mat Pour #3","2007-05-11","2007-05-11",5,"C","SL_GCFX1","$$",null,89513,null,89513,89513,null,null,89513,null,89513,89513,{"$nulls":4},89513,1,{"$nulls":4},0.15,13426.949999999999,1,1.15,"H3","P2","9A"]
["1","09","03","08","03","","GCBT9160","1.09.03.08.03","9242823","9242823","BTH Form Mat Pour #4","2007-05-11","2007-05-18",5,"C","SL_GCFX1","$$",null,33252,null,33252,33252,null,null,33252,null,33252,33252,{"$nulls":4},33252,1,{"$nulls":4},0.15,4987.8,1,1.15,"H4","P2","9A"]
["1","09","03","08","03","","GCBT9290","1.09.03.08.03","9242823","9242823","BTH Form Walls Pour #5","2007-08-16","2007-08-29",5,"C","SL_GCFX1","$$",null,93609,null,93609,93609,null,null,93609,null,93609,93609,{"$nulls":4},93609,1,{"$nulls":4},0.15,14041.35,1,1.15,"H5","P2","9A"]
["1","09","03","08","03","","GCBT9320","1.09.03.08.03","9242823","9242823","BTH Form Deck Pour #5","2007-08-31","2007-09-11",5,"C","SL_GCFX1","$$",null,60588,null,60588,60588,null,null,60588,null,60588,60588,{"$nulls":4},60588,1,{"$nulls":4},0.15,9088.199999999999,1,1.15,"H5","P2","9A"]
["1","09","03","08","03","","GCBT9400","1.09.03.08.03","9242823","9242823","BTH Rebar Walls Pour #6","2007-08-30","2007-09-12",5,"C","SL_GCFX1","$$",null,42909,null,42909,42909,null,null,42909,null,42909,42909,{"$nulls":4},42909,1,{"$nulls":4},0.15,6436.349999999999,1,1.15,"H6","P2","9A"]
["1","09","03","08","06","  ",{"$nulls":4},"Special System - Fire Protection                            "]
["1","09","03","08","15","","GCBT6008","1.09.03.08.15","9242825","9242825","BTH Plumbing Trim","2007-12-03","2007-12-21",6,"C","SL_GCFX1","$$",null,4779,null,4779,4779,null,null,4779,null,4779,4779,{"$nulls":6},4779,1,null,null,0.15,716.85,1,1.15,"H7","P2","9A"]
["1","09","03","08","16","","GCBT3076","1.09.03.08.16","9242826",null,"BTH Temporary Power","2006-12-29","2007-05-04",7,"C","SL_GCFX1","$$",null,30000,null,30000,30000,null,null,27000,null,27000,27000,{"$nulls":4},27000,1,{"$nulls":4},0.15,4050,1,1.15,"Y1","P2","9A"]
["1","09","03","09","01","  ",{"$nulls":4},"FEE - Site Preparation/General Requirements                 "]
["1","09","03","09","03","","GCFE7170","1.09.03.09.03","9242831",null,"FEE Form Walls Pour #1","2007-06-07","2007-06-20",5,"C","SL_GCFX1","$$",null,192400,null,192400,192400,null,null,192400,null,192400,192400,{"$nulls":4},192400,1,{"$nulls":4},0.15,28860,1,1.15,"F1","P2","9A"]
["1","09","03","09","03","","GCFE7490","1.09.03.09.03","9242831",null,"FEE Rebar Walls Pour #2","2007-06-15","2007-06-26",5,"C","SL_GCFX1","$$",null,78000,null,78000,78000,null,null,78000,null,78000,78000,{"$nulls":4},78000,1,{"$nulls":4},0.15,11700,1,1.15,"F2","P2","9A"]
["1","09","03","09","03","","GCFE7550","1.09.03.09.03","9242831",null,"FEE Pour SOG Pour #2","2007-06-12","2007-06-12",5,"C","SL_GCFX1","$$",null,69900,null,69900,69900,null,null,69900,null,69900,69900,{"$nulls":4},69900,1,{"$nulls":4},0.15,10485,1,1.15,"F2","P2","9A"]
["1","09","03","09","10","  ",{"$nulls":4},"Project Close Out Beam Dump                                 "]
["1","09","03","09","16","","GCFE7308","1.09.03.09.16","9242834",null,"FEE O/H Electrical R/I","2007-09-04","2007-10-16",7,"C","SL_GCFX1","$$",null,117803,null,117803,null,null,null,117803,null,117803,117803,{"$nulls":4},75730.5,0.64,42072.5,0.36,null,null,0.15,17670.45,1,1.15,"FN","P2","9A"]
["1","09","03","09","16","","GCFE7342","1.09.03.09.16","9242834",null,"FEE Electrical Trim","2007-10-17","2007-11-06",7,"C","SL_GCFX1","$$",null,3495,null,3495,3495,null,null,3495,null,3495,3495,{"$nulls":6},3495,1,null,null,0.15,524.25,1,1.15,"FN","P2","9A"]
["1","09","03","10","01","","CF10073105","1.09.03.10.01","9242837","9242837","Install EBD Steel Shielding","2007-07-03","2007-07-31",null,"C","SA_MSSY1","$$",null,577650,null,577650,577650,null,null,288825,null,288825,288825,{"$nulls":4},288825,1,{"$nulls":4},0.45,129971.25,1.35,1.1,null,3,"9A"]
["1","09","03","10","03","","GCBD1220","1.09.03.10.03","9242839",null,"BD Form Walls Pour #2","2007-08-14","2007-08-24",5,"C","SL_GCFX1","$$",null,192400,null,192400,192400,null,null,192400,null,192400,192400,{"$nulls":4},192400,1,{"$nulls":4},0.15,28860,1,1.15,"D2","P2","9A"]
["1","09","03","10","03","","GCBD1400","1.09.03.10.03","9242839",null,"BD Rebar SOG Pour #1","2007-07-02","2007-07-12",5,"C","SL_GCFX1","$$",null,50000,null,50000,50000,null,null,50000,null,50000,50000,{"$nulls":4},50000,1,{"$nulls":4},0.15,7500,1,1.15,"D1","P2","9A"]
["1","09","03","10","05","","GCHM1238","1.09.03.10.05","9242840",null,"BP18 - Misc. Metals (BD)","2007-12-11","2007-12-12",12,"C","SL_GCFX1","$$",null,14800,null,14800,14800,null,null,14800,null,14800,14800,{"$nulls":6},14800,1,null,null,0.15,2220,1,1.15,"BD","P2","9A"]
["1","09","03","10","15","","GCBD1304","1.09.03.10.15","9242841",null,"BD Plumbing Rough-in","2007-11-02","2007-12-03",6,"C","SL_GCFX1","$$",null,34751,null,34751,34751,null,null,34751,null,34751,34751,{"$nulls":6},34751,1,null,null,0.15,5212.65,1,1.15,"BD","P2","9A"]
["1","09","03","10","15","","GCBD1308","1.09.03.10.15","9242841",null,"BD HVAC Insulation","2007-12-04","2007-12-17",6,"C","SL_GCFX1","$$",null,7000,null,7000,7000,null,null,7000,null,7000,7000,{"$nulls":6},7000,1,null,null,0.15,1050,1,1.15,"BD","P2","9A"]
["1","09","03","10","16","","GCBD4582","1.09.03.10.16","9242842","9242842","BD Install Data Cabling Trays","2007-04-09","2007-06-29",7,"C","SL_GCFX1","$$",null,24387,null,24387,24387,null,null,23167.65,null,23167.65,23167.65,{"$nulls":4},23167.65,1,{"$nulls":4},0.15,3475.1475,1,1.15,"BD","P2","9A"]
["1","09","03","11","  ","  ",{"$nulls":4},"Near Experimental Hall (NEH)                                ",{"$nulls":6},0,17783281,0,17781472,16044269,null,0,12478338.74,0,12478338.74,12478338.74,0,null,1254712.0524535424,null,7163178.036497214,null,4060448.6510492438,null,0,null,null,1909635.8610000003]
["1","09","03","11","01","","GCNB2984","1.09.03.11.01","9242845","9242845","Wrap-up Insurance (CCIP)  - Kwan Wo","2006-10-20","2006-10-20",12,"C","SL_GCFX1","$$",null,47456,null,47456,47456,null,null,0,null,0,0,{"$nulls":10},0.15,0,1,1.15,"I8","P2","9A"]
["1","09","03","11","01","","GCNB3234","1.09.03.11.01","9242845","9242845","Bond - HVAC (O.C. McDonald Co.)","2006-11-17","2006-11-17",6,"C","SL_GCFX1","$$",null,47299,null,47299,47299,null,null,0,null,0,0,{"$nulls":10},0,0,1,1,"I7","P2","9A"]
["1","09","03","11","01","","GCNE6010","1.09.03.11.01","9242845","9242845","Bond - Alcal Arcade Contracting","2006-08-01","2006-08-01",null,"C","SL_GCFX1","$$",null,7206,null,7206,7206,null,null,7206,null,7206,7206,null,null,7206,1,{"$nulls":6},0.15,1080.8999999999999,1,1.15,"K1","P2","9A"]
["1","09","03","11","02","","CF11125","1.09.03.11.02","9242846","9242846","Start: Fire Protection (Hazard Analysis)","2007-04-03","2007-10-18",null,"C","SA_MSPF1","$$",null,200000,null,200000,null,null,null,200000,null,200000,200000,{"$nulls":4},182828.28282828283,0.91,17171.71717171717,0.09,null,null,0.3,60000,1.2,1.1,1,3,"9A"]
["1","09","03","11","03","","GCNB2874","1.09.03.11.03","9242847","9242847","Rebar Vert to 1st Level #2","2007-06-01","2007-06-11",5,"C","SL_GCFX1","$$",null,97591,null,97591,97591,null,null,97591,null,97591,97591,{"$nulls":4},97591,1,{"$nulls":4},0.15,14638.65,1,1.15,"M1","P2","9A"]
["1","09","03","11","03","","GCNB3240","1.09.03.11.03","9242847","9242847","Pour Vert to 1st Level #2","2007-06-12","2007-06-13",5,"C","SL_GCFX1","$$",null,108650,null,108650,108650,null,null,108650,null,108650,108650,{"$nulls":4},108650,1,{"$nulls":4},0.15,16297.5,1,1.15,"M1","P2","9A"]
["1","09","03","11","03","","GCNB4100","1.09.03.11.03","9242847","9242847","Pour Dock Leveler Slab","2007-09-21","2007-09-21",5,"C","SL_GCFX1","$$",null,1900,null,1900,1900,null,null,1900,null,1900,1900,{"$nulls":4},1900,1,{"$nulls":4},0.15,285,1,1.15,"LD","P2","9A"]
["1","09","03","11","03","","GCNE1460","1.09.03.11.03","9242847","9242847","Exc/Form/Rebar/Pour Elevator Pit & Sump(SUMMARY)","2007-01-23","2007-02-23",5,"C","SL_GCFX1","$$",null,17700,null,17700,17700,null,null,0,null,0,0,{"$nulls":10},0.15,0,1,1.15,"L1","P2","9A"]
["1","09","03","11","03","","GCNE27660","1.09.03.11.03","9242847","9242847","Rebar Vert #2","2007-03-21","2007-03-29",5,"C","SL_GCFX1","$$",null,146400,null,146400,146400,null,null,0,null,0,0,{"$nulls":10},0.15,0,1,1.15,"L1","P2","9A"]
["1","09","03","11","10","  ",{"$nulls":4},"Project Close Out X-Ray Transport & Diagonistic             "]
["1","09","03","11","15","","GCNB9020","1.09.03.11.15","9242849","9242849","BM HVAC Trim","2007-12-12","2007-12-26",6,"C","SL_GCFX1","$$",null,155895,null,155895,155895,null,null,155895,null,155895,155895,{"$nulls":6},155895,1,null,null,0.15,23384.25,1,1.15,"BA","P2","9A"]
["1","09","03","11","15","","GCNE2422","1.09.03.11.15","9242849","9242849","Sub BM HVAC Controls","2007-10-05","2007-10-26",6,"C","SL_GCFX1","$$",null,22000,null,22000,22000,null,null,22000,null,22000,22000,{"$nulls":6},22000,1,null,null,0.15,3300,1,1.15,"SU","P2","9A"]
["1","09","03","11","16","","GCCO1560","1.09.03.11.16","9242850","9242850","Conf Ctr Fire / Life / Safety R/I","2006-08-01","2006-08-14",7,"C","SL_GCFX1","$$",null,5885,null,5885,5885,null,null,5885,null,5885,5885,null,null,5885,1,{"$nulls":6},0.15,882.75,1,1.15,"CO","P2","9A"]
["1","09","03","11","16","","GCCO2200","1.09.03.11.16","9242850","9242850","Conf Ctr Elevator Fire Detection / Tel Connect","2008-01-11","2008-01-17",7,"C","SL_GCFX1","$$",null,6200,null,6200,6200,null,null,6200,null,6200,6200,{"$nulls":6},6200,1,null,null,0.15,930,1,1.15,"CO","P2","9A"]
["1","09","03","11","16","","GCNE2354","1.09.03.11.16","9242850","9242850","Sub BM O/H Electrical R/I","2006-08-01","2006-09-12",7,"C","SL_GCFX1","$$",null,555865,null,555865,555865,null,null,541968.375,null,541968.375,541968.375,null,null,541968.375,1,{"$nulls":6},0.15,81295.25624999999,1,1.15,"SU","P2","9A"]
["1","09","03","11","17","  ",{"$nulls":4},"NEH - Others (include Div 4, and 6 through 14)              ",{"$nulls":6},0,2532875,0,2532875,2520423,null,0,2532875,0,2532875,2532875,0,null,0,null,400083.13333333336,null,2132791.8666666667,null,0,null,null,379296.45]
["1","09","03","11","17","","GCHM6600","1.09.03.11.17","9242851","9242851","BP32 - Flooring (NEH) Hammock","2007-09-24","2008-01-07",22,"C","SL_GCFX1","$$",null,12452,null,12452,null,null,null,12452,null,12452,12452,{"$nulls":4},830.1333333333333,0.07,11621.866666666667,0.93,null,null,0.15,1867.8,1,1.15,"BA","P2","9A"]
["1","09","03","12","  ","  ",{"$nulls":4},"Undulator Hall (UH)                                         ",{"$nulls":6},0,8782962,0,8782962,8204457,null,0,6589925.794,0,6589925.554,6589925.554,0,null,154000,null,4219926.158010695,null,2215999.395989305,null,0,null,null,988488.8331]
["1","09","03","12","07","  ",{"$nulls":4},"Interiors                                                   "]
["1","09","03","12","16","","GCUH04540","1.09.03.12.16","9242857","9242857","UH Data Cable Trays","2007-10-23","2007-11-28",7,"C","SL_GCFX1","$$",null,225257,null,225257,225257,null,null,213994.15,null,213994.15,213994.15,{"$nulls":6},213994.15,1,null,null,0.15,32099.122499999998,1,1.15,"UH","P2","9A"]
["1","09","03","12","16","","GCUH3460","1.09.03.12.16","9242857","9242857","Install GDMPs - 40 Ea.","2007-01-29","2007-07-27",3,"C","SL_GCFX1","$$",null,44000,null,44000,44000,null,null,7700,null,7700,7700,{"$nulls":4},7700,1,{"$nulls":4},0.15,1155,1,1.15,"IC","P2","9A"]
["1","09","03","12","16","","GCUH3520","1.09.03.12.16","9242857","9242857","Install MPBXs < 70 Ft Deep - 3 Ea.","2007-02-05","2007-02-15",3,"C","SL_GCFX1","$$",null,45000,null,45000,45000,null,null,0,null,0,0,{"$nulls":10},0,0,1,1,"IC","P2","9A"]
["1","09","03","12","19","","GCCN1100","1.09.03.12.19","9242859","9242859","Lattice Girders, Type 2 FEH","2007-05-03","2007-05-03",3,"C","SL_GCFX1","$$",null,6400,null,6400,6400,null,null,6400,null,6400,6400,{"$nulls":4},6400,1,{"$nulls":4},0.15,960,1,1.15,"CN","P2","9A"]
["1","09","03","12","19","","GCUH02010","1.09.03.12.19","9242859","9242859","UH Tunnel- Excavate UH Tunnel (565')","2007-04-09","2007-07-20",3,"C","SL_GCFX1","$$",null,2557711,null,2557711,2557711,null,null,2465633.404,null,2465633.404,2465633.404,{"$nulls":4},2465633.404,1,{"$nulls":4},0.15,369845.0106,1,1.15,"UH","P2","9A"]
["1","09","03","13","06","  ",{"$nulls":4},"Special System - Fire Protection                            "]
["1","09","03","13","15","","GCXR1426","1.09.03.13.15","9242864",null,"X-Ray Tunnel HVAC Trim","2008-02-06","2008-02-20",6,"C","SL_GCFX1","$$",null,613,null,613,613,null,null,613,null,613,613,{"$nulls":6},613,1,null,null,0.15,91.95,1,1.15,null,"P2","9A"]
["1","09","03","13","19","  ",{"$nulls":4},"XRTD - Tunnel Construction                                  ",{"$nulls":6},0,4128067,0,4128067,2060867,null,0,4128067,0,4128067,4128067,0,null,0,null,1749714,null,2378353,null,0,null,null,619210.05]
["1","09","03","14","02","","CF14110","1.09.03.14.02","9242870","9242870","AWARD: FEH Hutches - Construction","2008-02-04","2008-02-04",null,"C","SL_AWFY1","$$",null,2120907,null,2120907,2120907,null,null,2120907,null,2120907,2120907,{"$nulls":6},2120907,1,null,null,0.4,848362.8,1.3,1.1,null,3,"9A"]
["1","09","03","14","15","","GCAC4120","1.09.03.14.15","9242872","9242872","Access Tunnel HVAC Rough-in","2008-03-17","2008-04-11",6,"C","SL_GCFX1","$$",null,213230,null,213230,213230,null,null,213230,null,213230,213230,{"$nulls":6},213230,1,null,null,0.15,31984.5,1,1.15,"AC","P2","9A"]
["1","09","03","14","15","","GCAC4144","1.09.03.14.15","9242872","9242872","Access T HVAC Controls","2008-04-28","2008-05-09",6,"C","SL_GCFX1","$$",null,84505,null,84505,84505,null,null,84505,null,84505,84505,{"$nulls":6},84505,1,null,null,0.15,12675.75,1,1.15,"AC","P2","9A"]
["1","09","03","14","16","","GCFH3114","1.09.03.14.16","9242873","9242873","FEH Grounding","2008-01-07","2008-01-18",7,"C","SL_GCFX1","$$",null,19124,null,19124,19124,null,null,19124,null,19124,19124,{"$nulls":6},19124,1,null,null,0.15,2868.6,1,1.15,"FE","P2","9A"]
["1","09","03","14","16","","GCFH3320","1.09.03.14.16","9242873","9242873","FEH O/H Electrical R/I","2008-01-24","2008-02-28",7,"C","SL_GCFX1","$$",null,401387,null,401387,401387,null,null,401387,null,401387,401387,{"$nulls":6},401387,1,null,null,0.15,60208.049999999996,1,1.15,"FE","P2","9A"]
["1","09","03","14","18","","GCAC1228","1.09.03.14.18","9242875","9242875","Access Tunnel - Portal Shotcrete","2007-02-16","2007-02-21",3,"C","SL_GCFX1","$$",null,45000,null,45000,45000,null,null,0,null,0,0,{"$nulls":10},0.15,0,1,1.15,"AC","P2","9A"]
["1","09","03","14","18","","GCAC4360","1.09.03.14.18","9242875","9242875","Access Tunnel - Install Wire Mesh at Portal","2008-04-15","2008-04-15",3,"C","SL_GCFX1","$$",null,24000,null,24000,24000,null,null,24000,null,24000,24000,{"$nulls":6},24000,1,null,null,0.15,3600,1,1.15,"AC","P2","9A"]
["1","09","03","14","20","  ",{"$nulls":4},"FEH - Project Close Out                                     "]
["1","09","03","15","15","","GCBT3126","1.09.03.15.15","9242880","9242880","Service Bldg 2.2 HVAC Insulation","2007-11-28","2007-12-04",6,"C","SL_GCFX1","$$",null,22355,null,22355,22355,null,null,22355,null,22355,22355,{"$nulls":6},22355,1,null,null,0.15,3353.25,1,1.15,"S2","P2","9A"]
["1","09","03","15","15","","GCBT5300","1.09.03.15.15","9242880","9242880","Service Bldg 2.1 Plumbing Rough-in","2007-09-17","2007-10-15",6,"C","SL_GCFX1","$$",null,118000,null,118000,null,null,null,118000,null,118000,118000,{"$nulls":4},59000,0.5,59000,0.5,null,null,0.15,17700,1,1.15,"S1","P2","9A"]
["1","09","03","15","15","","GCBT5404","1.09.03.15.15","9242880","9242880","Service Bldg 2.2 Plumbing Trim","2007-11-28","2007-12-11",6,"C","SL_GCFX1","$$",null,9000,null,9000,9000,null,null,9000,null,9000,9000,{"$nulls":6},9000,1,null,null,0.15,1350,1,1.15,"S2","P2","9A"]
["1","09","03","15","16","","GCBT5130","1.09.03.15.16","9242881","9242881","BTH 2.3 Electrical Trim","2007-12-21","2008-01-02",7,"C","SL_GCFX1","$$",null,2736,null,2736,2736,null,null,2736,null,2736,2736,{"$nulls":6},2736,1,null,null,0.15,410.4,1,1.15,"S3","P2","9A"]
["1","09","03","15","17","","GCHM6320","1.09.03.15.17","9242882","9242882","BP39 - Metal Bldg (BTH) Hammock","2007-08-23","2007-11-29",null,"C","SL_GCFX1","$$",null,924132,null,924132,null,null,null,924132,null,924132,924132,{"$nulls":4},367766.8163265306,0.4,556365.1836734693,0.6,null,null,0.15,138619.8,1,1.15,"S1","P2","9A"]
["1","09","03","16","03","","GCUH02204","1.09.03.16.03","9242885","9242885","UH3.1 Prep & Form SOG","2007-08-06","2007-08-13",5,"C","SL_GCFX1","$$",null,39400,null,39400,39400,null,null,39400,null,39400,39400,{"$nulls":4},39400,1,{"$nulls":4},0.15,5910,1,1.15,"X1","P2","9A"]
["1","09","03","16","15","","GCUH3244","1.09.03.16.15","9242887","9242887","BP10 - Fire Protection (SB UH)","2007-09-11","2007-09-20",null,"C","SA_GCFX1","$$",null,11452,null,11452,11452,null,null,11452,null,11452,11452,{"$nulls":4},11452,1,{"$nulls":4},0.15,1717.8,1,1.15,"UH","P2","9A"]
["1","09","03","16","16","","GCUH3344","1.09.03.16.16","9242888","9242888","UH 3.1 Lighting","2007-10-10","2007-10-23",7,"C","SL_GCFX1","$$",null,15125,null,15125,15125,null,null,15125,null,15125,15125,{"$nulls":6},15125,1,null,null,0.15,2268.75,1,1.15,"X1","P2","9A"]
["1","09","03","17","03","","GC8B11390","1.09.03.17.03","9242892","9242892","AT Yard Form Walls","2008-03-31","2008-04-08",5,"C","SL_GCFX1","$$",null,193900,null,193900,193900,null,null,193900,null,193900,193900,{"$nulls":6},193900,1,null,null,0.15,29085,1,1.15,"8B","P2","9A"]
["1","09","03","17","03","","GC8B11490","1.09.03.17.03","9242892","9242892","AT Yard Form Mech. Deck","2008-04-23","2008-04-25",5,"C","SL_GCFX1","$$",null,15900,null,15900,15900,null,null,15900,null,15900,15900,{"$nulls":6},15900,1,null,null,0.15,2385,1,1.15,"8B","P2","9A"]
["1","09","03","17","05","  ",{"$nulls":4},"SB FEH - Metals                                             "]
["1","09","03","18","01","","GCCU4480","1.09.03.18.01","9242898",null,"Wrap-up Insurance (CCIP) - B.T. Mancini","2006-11-14","2006-11-14",18,"C","SL_GCFX1","$$",null,3557,null,3557,3557,null,null,0,null,0,0,{"$nulls":14},"K4","P2","9A"]
["1","09","03","18","03","","GCCU1284","1.09.03.18.03","9242900",null,"Rebar Retaining Wall Ftgs","2007-05-29","2007-06-05",5,"C","SL_GCFX1","$$",null,10295,null,10295,10295,null,null,10295,null,10295,10295,{"$nulls":4},10295,1,{"$nulls":4},0.15,1544.25,1,1.15,"CR","P2","9A"]
["1","09","03","18","03","","GCCU1740","1.09.03.18.03","9242900",null,"Rebar CUP Ftgs & Mat - Pour #1","2007-06-22","2007-06-29",5,"C","SL_GCFX1","$$",null,28180,null,28180,28180,null,null,28180,null,28180,28180,{"$nulls":4},28180,1,{"$nulls":4},0.15,4227,1,1.15,"C1","P2","9A"]
["1","09","03","18","05","","GCHM6240","1.09.03.18.05","9242901",null,"BP18 - Misc. Steel (CUP)","2007-07-31","2007-09-10",12,"C","SA_GCFX1","$$",null,46600,null,46600,46600,null,null,46600,null,46600,46600,{"$nulls":4},46600,1,{"$nulls":4},0.15,6990,1,1.15,"CP","P2","9A"]
["1","09","03","18","16","  ",{"$nulls":4},"CUP - Electrical                                            ",{"$nulls":6},0,2550696,0,2550696,2498078,null,0,2517703.724,0,2517703.724,2517703.724,0,null,103163.35,null,2263122.231142857,null,151418.14285714284,null,0,null,null,560355.5585999999]
["1","09","03","18","16","","GCCU3940","1.09.03.18.16","9242903","9242903","CUP Set & Anchor Switchboards & Panels","2007-10-11","2007-10-31",7,"C","SL_GCFX1","$$",null,98567,null,98567,98567,null,null,98567,null,98567,98567,{"$nulls":6},98567,1,null,null,0.15,14785.05,1,1.15,"CP","P2","9A"]
["1","09","03","18","20","  ",{"$nulls":4},"CUP - Project Close Out                                     "]
["1","09","03","19","01","","CF19030","1.09.03.19.01","8819031","9242906","Independent Cost Estimate for B028 Ph 2","2008-01-22","2008-02-11",null,"C","SL_MSPY1","$$",null,14000,null,14000,14000,null,null,14000,null,14000,14000,{"$nulls":6},14000,1,null,null,0.25,3500,1.1,1.15,5,2,"9A"]
["1","09","03","20","  ","  ",{"$nulls":4},"Construction Credits and Debits                             "]
["2","  ","  ","  ","  ","  ",{"$nulls":4},"LCLS PROJECT - R&D, SPARES, COMMISSIONING                   ",{"$nulls":6},221423,20865745,25951548.125007577,22156909.315216362,46288870.935864605,null,178010.1,18676073.939999998,20942528.212162238,19702084.658506215,40644612.870668486,0,null,489050.08705094364,null,8437548.282337513,null,16636466.616308441,null,15081547.884971527,null,null,133730.8116201886]
["2","01","01","03","","","PM210_0383","2.01.01.03","XBA10103","9682323","Linac Physicists FY06 Remainder","2006-06-01","2006-09-29",null,"X","SL_PHS1","Hrs",298,null,24429.243797639996,null,24429.243797639996,null,0,null,0,null,0,{"$nulls":14},4,1,"1A"]
["2","01","01","06","  ","  ",{"$nulls":4},"X-Ray Physics Commissioning                                 ",{"$nulls":6},4221,0,362442.8027528992,0,362442.8027528992,null,3250.17,0,279066.36080239806,0,279066.36080239806,0,null,0,null,111442.34210260781,null,112363.3531943649,null,55260.665505425364,null,null,0]
["2","01","01","09","","","PM210_A272","2.01.01.09","XCA10109","9682329","Consulting SLAC Physicists Apr07-Sep07","2007-04-02","2007-09-28",null,"X","SL_PHS1","Hrs",445,null,37428.38872714259,null,37428.38872714259,null,369.35,null,31065.562643528352,null,31065.562643528352,{"$nulls":4},31065.562643528352,1,{"$nulls":8},4,1,"1A"]
["2","01","01","11","  ","  ",{"$nulls":4},"Global Controls OPC                                         ",{"$nulls":6},10464,1252840,1260948.7942288157,1411593.5996440772,2672542.3938728925,null,8946.4,1070080,1077427.711672976,1214351.226012077,2291778.9376850533,0,null,95390.08,null,459770.4576342506,null,1138474.8490173828,null,598143.55103342,null,null,0]
["2","01","01","11","12","01",{"$nulls":4},"Global Controls Management - LOE",{"$nulls":6},9193,883840,1139822.177959543,978580.7669921411,2118402.944951684,null,7675.4,723680,956301.0954037032,805185.9133601412,1761487.0087638444,0,null,0,null,280433.9498618742,null,983115.2727444862,null,497937.7861574841,null,null,0]
["2","01","01","11","12","01","PM1112_012","2.01.01.11.12","XACG111201","9682343","Controls Physicist - FY07","2006-10-02","2007-09-28",null,"X","SL_PHH1","Hrs",847,null,93547.60827932518,null,93547.60827932518,null,372.68,null,41160.947642903084,null,41160.947642903084,{"$nulls":4},41160.947642903084,1,{"$nulls":8},3,1,"2G","H. Shoaee"]
["2","01","01","11","12","01","PM1112_215","2.01.01.11.12","XAEG111201","9682343","Controls Technical Coordinator - FY09","2008-10-01","2009-03-31",null,"X","SL_CE1","Hrs",750,null,102625.04088663502,null,102625.04088663502,null,750,null,102625.04088663502,null,102625.04088663502,{"$nulls":8},102625.04088663502,1,{"$nulls":4},3,1,"2G","H. Shoaee"]
["2","01","01","11","12","01","PM1112_230","2.01.01.11.12","XAEG111201","9682343","Controls XT/XE Tech Lead - FY09","2008-10-01","2009-03-31",null,"X","SL_MSPS1","$$",null,36900,null,42053.6051429904,42053.6051429904,null,null,36900,null,42053.6051429904,42053.6051429904,{"$nulls":8},42053.6051429904,1,{"$nulls":4},3,1,"2G","H. Shoaee"]
["2","01","01","11","14","","PM1114_026","2.01.01.11.14","XBCG30514",null,"WPM Application","2007-01-02","2007-12-14",null,"X","SL_CP1","Hrs",1271,null,121126.61626927282,null,121126.61626927282,null,1271,null,121126.61626927282,null,121126.61626927282,{"$nulls":4},95220.92377237634,0.79,25905.6924968965,0.21,{"$nulls":6},3,3,"2G","D. Fairley"]
["2","01","02","  ","  ","  ",{"$nulls":4},"R&D Studies & Prototyping                                   "]
["2","01","03","01","","","PM213_0215","2.01.03.01","XK10301","9682009","Administrative Support  - FY09","2008-10-01","2009-03-30","S","X","SL_ADMN1","Hrs",2974,null,211192.23615133562,null,211192.23615133562,null,2974,null,211192.23615133562,null,211192.23615133562,{"$nulls":8},211192.23615133562,1,{"$nulls":4},4,1,"1A"]
["2","01","03","01","","","PM213_0265","2.01.03.01","XK10301","9682009","Senior Project Mgrs - FY07","2006-10-02","2007-09-28","S","X","SL_PM1","Hrs",2541,null,475104.4421295525,null,475104.4421295525,null,1067.22,null,199543.86569441206,null,199543.86569441206,{"$nulls":4},199543.86569441206,1,{"$nulls":8},4,1,"1A"]
["2","01","03","02","  ","  ",{"$nulls":4},"SLAC Project Support                                        ",{"$nulls":6},7852,1248307,659996.9834329012,1369692.6317880976,1769758.3334535907,null,6312.16,835919.8,546505.6886658741,925775.9144146575,1472281.6030805318,0,null,0,null,271638.9883347127,null,878274.7557339298,null,322367.85901188914,null,null,0]
["2","01","03","02","","","PM212_0172","2.01.03.02","XBA10302","9682014","Computing Mgr Support - FY06 Remainder","2006-06-01","2006-09-29","S","X","SL_CRM1","Hrs",111,null,7481.313727469999,null,7481.313727469999,null,0,null,0,null,0,{"$nulls":14},4,1,"1A"]
["2","01","03","02","","","PM212_0192","2.01.03.02","XK10302","9682014","Computing Res Support - FY08","2007-10-01","2008-09-30","S","X","SL_CRA1","Hrs",340,null,21205.95397917931,null,21205.95397917931,null,340,null,21205.95397917931,null,21205.95397917931,{"$nulls":6},21205.95397917931,1,{"$nulls":6},4,1,"1A"]
["2","01","03","02","","","PM212_A023","2.01.03.02","XK10302","9682014","AWARD:  PMCS Support-FY08","2007-10-02","2007-10-02","S","X","SL_AW1","$$",null,534989,null,594257.0690111327,594257.0690111327,null,null,534989,null,594257.0690111327,594257.0690111327,{"$nulls":6},594257.0690111327,1,{"$nulls":6},4,1,"1A"]
["2","01","03","07","  ","  ",{"$nulls":4},"Conventional Facilities Physics                             "]
["2","01","03","10","  ","  ",{"$nulls":4},"Global Controls Physics Liaison                             "]
["2","02","02","01","","","IJ16010245","2.02.02.01","RB20201","9682155","Evaluate Proposals - BSOIC","2006-09-12","2006-09-12",null,"R","SL_CE1","Hrs",16,null,2027.0757513599997,null,2027.0757513599997,null,0,null,0,null,0,{"$nulls":14},3,3,"2G","P. Bong"]
["2","02","02","01","","","IJ16010255","2.02.02.01","XK20201","9682155","Classic- BSOIC Substitution","2006-09-14","2006-09-27",null,"X","SA_MSSC1","$$",null,25000,null,26380,26380,null,null,0,null,0,0,{"$nulls":14},3,3,"2G","P. Bong"]
["2","02","02","04","01","  ",{"$nulls":4},"Power Supply Controls                                       "]
["2","02","02","05","  ","  ",{"$nulls":4},"LLRF Controls                                               ",{"$nulls":6},1680,0,166645.30132055518,0,166645.30132055518,null,705.6,0,69991.02655463318,0,69991.02655463318,0,null,0,null,69991.02655463318,null,0,null,0,null,null,0]
["2","02","02","06","05","  ",{"$nulls":4},"Controls - Profile Monitors                                 ",{"$nulls":6},80,0,8046.000236023198,0,8046.000236023198,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["2","02","02","06","06","  ",{"$nulls":4},"Control - EO Diagnostic                                     "]
["2","02","02","08","","","IJ208_0170","2.02.02.08","XBBIJ20208","9682162","Injector Timing Controls - Commissioning","2006-12-15","2007-08-20",null,"X","SL_CE1","Hrs",640,null,83191.18883581439,null,83191.18883581439,null,294.4,null,38267.946864474616,null,38267.946864474616,{"$nulls":4},38267.946864474616,1,{"$nulls":8},3,5,"2G","P. Krejcik"]
["2","02","02","09","","","PM1107_100","2.02.02.09","XB011107","9682163","Injector Controls Commission Support","2006-12-15","2007-08-15",null,"X","SL_CP1","Hrs",400,null,37909.297544184,null,37909.297544184,null,180,null,17059.1838948828,null,17059.1838948828,{"$nulls":4},17059.1838948828,1,{"$nulls":8},3,5,"2G","S. Schuh"]
["2","02","03","03","  ","  ",{"$nulls":4},"Drive Laser Diagnostics                                     ",{"$nulls":6},6240,0,815624.4481184707,0,815624.4481184707,null,4992,0,652499.5584947766,0,652499.5584947766,0,null,0,null,512947.629799362,null,139551.92869541465,null,0,null,null,0]
["2","02","03","09","  ","  ",{"$nulls":4},"Load Lock Transport System                                  "]
["2","02","04","01","01","","IJ224_1110","2.02.04.01.01","RBE2040101",null,"GTF - Test digital cameras for LCLS Injector","2006-06-01","2006-06-30",null,"R","SL_PHS1","Hrs",48,null,3934.9117526399996,null,3934.9117526399996,null,0,null,0,null,0,{"$nulls":14},5,5,"2A"]
["2","02","04","01","01","","IJ224_1150","2.02.04.01.01","RBE2040101",null,"Cathode - Test cleaned samples and cathodes","2006-05-01","2006-07-30",null,"R","SL_KCA1","Hrs",100,null,7378.395354,null,7378.395354,null,0,null,0,null,0,{"$nulls":14},5,5,"2A"]
["2","02","04","01","08","  ",{"$nulls":4},"Gun RF Feed Supports                                        "]
["2","02","04","02","02","  ",{"$nulls":4},"CP Load Lock                                                ",{"$nulls":6},0,100000,0,108263.52,108263.52,null,0,55000,0,59544.935999999994,59544.935999999994,0,null,0,null,59544.935999999994,null,0,null,0,null,null,0]
["2","02","04","06","04","  ",{"$nulls":4},"GTL RF Phase Cavity                                         "]
["2","02","05","01","  ","  ",{"$nulls":4},"Injector Dipoles                                            "]
["2","02","05","03","02","  ",{"$nulls":4},"L0-1TL0-2 Linac Steering Coils ( )                          "]
["2","02","06","02","  ","  ",{"$nulls":4},"GTL Supports                                                "]
["2","02","06","10","  ","  ",{"$nulls":4},"SAB Vacuum Chamber and Components                           "]
["2","02","07","01","04","  ",{"$nulls":4},"LTDL1 BPMs ( )                                              "]
["2","02","07","03","03","  ",{"$nulls":4},"DL1TL EO3                                                   "]
["2","02","07","04","02","  ",{"$nulls":4},"GTL YAG ( )                                                 "]
["2","02","08","01","","","IJ101_4160","2.02.08.01","XBG20801","9682373","Heater & Optics Integration","2007-10-02","2008-01-30",null,"X","SL_ME1","Hrs",200,null,23567.268587292925,null,23567.268587292925,null,200,null,23567.268587292925,null,23567.268587292925,{"$nulls":6},23567.268587292925,1,{"$nulls":6},4,5,"2A"]
["2","02","08","01","","","IJ101_4195","2.02.08.01","XBG20801","9682373","Heater & Optics Installation Oversight","2008-08-13","2008-10-10",null,"X","SL_ME1","Hrs",80,null,9464.940135988849,null,9464.940135988849,null,80,null,9464.940135988849,null,9464.940135988849,{"$nulls":6},7996.2425286802345,0.84,1468.6976073086146,0.16,{"$nulls":4},4,5,"2A"]
["2","02","08","03","01","","IJ501_4225","2.02.08.03.01","XBG2080301","9682375 \\ 9683375","Vendor Fab Chicane Dipole Assembly","2007-10-02","2007-11-12","S","X","SL_MDD1","Hrs",10,null,987.9718299150346,null,987.9718299150346,null,10,null,987.9718299150346,null,987.9718299150346,{"$nulls":6},987.9718299150346,1,{"$nulls":6},4,5,"2A"]
["2","02","08","03","02","","IJ505_2010","2.02.08.03.02","XBG2080302","9682376","Design Undulator","2007-11-14","2008-02-01","S","X","SL_ME1","Hrs",160,null,18853.814869834343,null,18853.814869834343,null,160,null,18853.814869834343,null,18853.814869834343,{"$nulls":6},18853.814869834343,1,{"$nulls":6},4,5,"2A"]
["2","02","08","03","02","","IJ505_2110","2.02.08.03.02","XBG2080302","9682376","Perform Magnetic Measurements and QA","2008-07-16","2008-08-12","S","X","SL_MES1","Hrs",20,null,1894.7404957274637,null,1894.7404957274637,null,20,null,1894.7404957274637,null,1894.7404957274637,{"$nulls":6},1894.7404957274637,1,{"$nulls":6},4,5,"2A"]
["2","02","08","04","","","IJ605_1310","2.02.08.04","XBG20804","9683377","Fabricate Heater Vacuum Supports","2008-01-04","2008-04-02","S","X","SL_MSEG1","$$",null,10000,null,11107.837151999998,11107.837151999998,null,null,10000,null,11107.837151999998,11107.837151999998,{"$nulls":6},11107.837151999998,1,{"$nulls":6},4,5,"2A"]
["2","02","08","06","","","IJ1715_100","2.02.08.06","XBE20806",null,"Install Beampipe","2008-09-18","2008-10-01","S","X","SL_MFAT1","Hrs",40,null,4067.540064,null,4067.540064,null,40,null,4067.540064,null,4067.540064,{"$nulls":6},4067.540064,1,0,0,{"$nulls":4},4,5,"2A"]
["2","02","17","01","  ","  ",{"$nulls":4},"Controls Commissioning                                      "]
["2","02","17","10","","","IJX217_100","2.02.17.10","XAE21710","9682365","Injector Commissioning 2007","2007-01-02","2007-08-30",null,"X","SL_KT1","Hrs",189,null,13449.953162133173,null,13449.953162133173,null,113.4,null,8069.971897279905,null,8069.971897279905,{"$nulls":4},8069.971897279905,1,{"$nulls":8},5,5,"2S"]
["2","02","17","10","","","IJX217_110","2.02.17.10","XAE21710","9682365","Injector Commissioning 2008","2007-12-03","2008-09-30",null,"X","SL_PHS1","Hrs",633,null,54625.09322685971,null,54625.09322685971,null,633,null,54625.09322685971,null,54625.09322685971,{"$nulls":6},54625.09322685971,1,{"$nulls":6},5,5,"2S"]
["2","03","01","01","","","LNX101-010","2.03.01.01","XAX30101",null,"Linac System Management Effort - OPC","2008-06-02","2009-03-30",null,"X","SL_TSM1","Hrs",800,null,101791.59108622323,null,101791.59108622323,null,800,null,101791.59108622323,null,101791.59108622323,{"$nulls":6},40919.543260574785,0.4,60872.04782564844,0.6,{"$nulls":4},5,5,"2A"]
["2","03","01","02","  ","  ",{"$nulls":4},"Linac Controls Integration                                  "]
["2","03","02","02","","","LN202_0265","2.03.02.02","CBDLN30202",null,"XTOD Commissioning","2007-10-16","2008-06-02",null,"X","SL_CP1","Hrs",8,null,777.8987856066557,null,777.8987856066557,null,8,null,777.8987856066557,null,777.8987856066557,{"$nulls":6},777.8987856066557,1,{"$nulls":6},3,5,"2G","K. Traeger"]
["2","03","02","03","","","LN203_0135","2.03.02.03","XBBLN30203",null,"L01-BC1 MPS Commissioning Suppt","2007-12-03","2008-07-07",null,"X","SL_CP1","Hrs",640,null,62231.90284853245,null,62231.90284853245,null,448,null,43562.331993972715,null,43562.331993972715,{"$nulls":6},43562.331993972715,1,{"$nulls":6},3,5,"2G","A. Tilghman"]
["2","03","02","04","01","","LN02043628","2.03.02.04.01","SK3020401","9682169","Integrate Pwr Supply, Transductor & Control","2007-03-21","2007-03-29","S","X","SL_PCEF1","Hrs",26,null,1850.2581069601192,null,1850.2581069601192,null,26,null,1850.2581069601192,null,1850.2581069601192,{"$nulls":4},1850.2581069601192,1,{"$nulls":8},3,3,"2G","K. Luchini"]
["2","03","02","04","02","","LN02045317","2.03.02.04.02","SK3020402","9682170","Spare Pwr Supply (Quad Type) Procurement","2006-10-03","2007-03-12",null,"X","SL_MSEG1","$$",null,21480,null,23255.004095999997,23255.004095999997,null,null,21480,null,23255.004095999997,23255.004095999997,{"$nulls":4},23255.004095999997,1,{"$nulls":8},3,3,"2G","K. Luchini"]
["2","03","02","05","","","LN205_0265","2.03.02.05","XBCLN30205",null,"L02-L03 LLRF Commissioning Suppt","2007-12-03","2008-01-02",null,null,"SL_KE1","Hrs",80,null,10669.269968193195,null,10669.269968193195,null,80,null,10669.269968193195,null,10669.269968193195,{"$nulls":6},10669.269968193195,1,{"$nulls":6},3,5,"2G","R. Akre"]
["2","03","02","05","","","LN205_0400","2.03.02.05","XBDLN30205",null,"LTU LLRF Commissioning Suppt","2008-03-03","2008-09-30",null,null,"SL_KE1","Hrs",560,null,74684.88977735236,null,74684.88977735236,null,560,null,74684.88977735236,null,74684.88977735236,{"$nulls":6},74684.88977735236,1,{"$nulls":6},3,5,"2G","R. Akre"]
["2","03","02","06","01","","LN601_0295","2.03.02.06.01","XBCLN20601",null,"L02-L03 Wire Scanners Commissioning Suppt","2007-12-03","2008-01-02",null,"X","SL_CE1","Hrs",80,null,10669.269968193195,null,10669.269968193195,null,80,null,10669.269968193195,null,10669.269968193195,{"$nulls":6},10669.269968193195,1,{"$nulls":6},3,5,"2G","D. Murray"]
["2","03","02","06","02","","LN602_0395","2.03.02.06.02","XBDLN20602",null,"LTU BPMs Commissioning Suppt","2008-03-03","2008-09-30",null,"X","SL_CE1","Hrs",560,null,74684.88977735236,null,74684.88977735236,null,560,null,74684.88977735236,null,74684.88977735236,{"$nulls":6},74684.88977735236,1,{"$nulls":6},3,5,"2G","S. Smith"]
["2","03","02","06","04","","LN604_260","2.03.02.06.04","XBC20604",null,"L02-L03 Commissioning Support","2007-12-03","2008-01-31",null,"X","SL_CE1","Hrs",8,null,1066.9269968193196,null,1066.9269968193196,null,8,null,1066.9269968193196,null,1066.9269968193196,{"$nulls":6},1066.9269968193196,1,{"$nulls":6},3,5,"2G","P. Bong"]
["2","03","02","06","05","","LN605_0320","2.03.02.06.05","XBCLN20605",null,"L02-L03 Profile Monitors Commissioning Suppt","2007-12-03","2008-01-15",null,"X","SL_CE1","Hrs",40,null,5334.634984096598,null,5334.634984096598,null,40,null,5334.634984096598,null,5334.634984096598,{"$nulls":6},5334.634984096598,1,{"$nulls":6},3,5,"2G","S. Peng"]
["2","03","02","06","09","","LN609_0260","2.03.02.06.09","XBCLN20609",null,"L02-L03 Commissioning Support","2007-12-03","2008-01-31",null,"X","SL_CE1","Hrs",8,null,1066.9269968193196,null,1066.9269968193196,null,8,null,1066.9269968193196,null,1066.9269968193196,{"$nulls":6},1066.9269968193196,1,{"$nulls":6},3,5,"2G","TBD"]
["2","03","02","06","10","","LN610_0260","2.03.02.06.10","XBCLN20610",null,"L02-L03 Commissioning Support","2007-12-03","2008-01-31",null,"X","SL_CT1","Hrs",8,null,584.1122516126408,null,584.1122516126408,null,8,null,584.1122516126408,null,584.1122516126408,{"$nulls":6},584.1122516126408,1,{"$nulls":6},3,5,"2G","TBD"]
["2","03","02","06","12","","LN612_0400","2.03.02.06.12","XBDLN20612",null,"LTU Wire Scanners LTU Commissioning Suppt","2008-03-03","2008-09-30",null,"X","SL_CE1","Hrs",20,null,2667.317492048299,null,2667.317492048299,null,20,null,2667.317492048299,null,2667.317492048299,{"$nulls":6},2667.317492048299,1,{"$nulls":6},3,5,"2G","D. Murray"]
["2","03","02","08","","","LN208_0060","2.03.02.08","XBBLN30208",null,"L01-BC1 Timing Controls Commissioning Support","2007-01-24","2007-09-07",null,"X","SL_CE1","Hrs",8,null,1039.88986044768,null,1039.88986044768,null,5.6,null,727.9229023133759,null,727.9229023133759,{"$nulls":4},727.9229023133759,1,{"$nulls":8},3,5,"2G","P. Krejcik"]
["2","03","02","08","","","LN208_0240","2.03.02.08","XBDLN30208",null,"L02-L03 Timing Controls Commissioning Support","2008-04-01","2008-09-30",null,"X","SL_CT1","Hrs",120,null,8761.68377418961,null,8761.68377418961,null,120,null,8761.68377418961,null,8761.68377418961,{"$nulls":6},8761.68377418961,1,{"$nulls":6},3,5,"2G","P. Krejcik"]
["2","03","02","09","","","PM1107_115","2.03.02.09","XB011107",null,"LTU Controls Commission Support","2008-03-04","2008-09-30",null,"X","SL_CE1","Hrs",320,null,42677.07987277278,null,42677.07987277278,null,320,null,42677.07987277278,null,42677.07987277278,{"$nulls":6},42677.07987277278,1,{"$nulls":6},3,5,"2G","S. Schuh"]
["2","03","03","11","  ","  ",{"$nulls":4},"Bend Magnet (BYPM_LTU)                                      "]
["2","03","04","04","  ","  ",{"$nulls":4},"BC2 Vacuum System                                           "]
["2","03","05","06","  ","  ",{"$nulls":4},"E/O Bunch Length Monitors                                   "]
["2","03","05","13","  ","  ",{"$nulls":4},"Safety Dump                                                 "]
["2","03","06","07","07","  ",{"$nulls":4},"RF Distribution L2 & L3                                     "]
["2","03","07","01","  ","  ",{"$nulls":4},"Linac L01 System Commissioning                              "]
["2","03","07","08","  ","  ",{"$nulls":4},"Linac Undulator Interface                                   "]
["2","03","07","10","","","LNX710-000","2.03.07.10","XAX30710","9682389","Linac Commissioning (L1,BC1)","2007-07-30","2007-08-30",null,"X","SL_MES1","Hrs",48,null,4432.141510473599,null,4432.141510473599,null,27.36,null,2526.3206609699514,null,2526.3206609699514,{"$nulls":4},2526.3206609699514,1,{"$nulls":8},4,5,"2S"]
["2","03","07","10","","","LNX710-010","2.03.07.10","XAX30710","9682389","Linac Commissioning (L2,BC2,L3)","2008-01-15","2008-02-01",null,"X","SL_PCT1","Hrs",45,null,3285.631415321104,null,3285.631415321104,null,45,null,3285.631415321104,null,3285.631415321104,{"$nulls":6},3285.631415321104,1,{"$nulls":6},4,5,"2S"]
["2","03","07","10","","","LNX710-010","2.03.07.10","XAX30710","9682389","Linac Commissioning (L2,BC2,L3)","2008-01-15","2008-02-01",null,"X","SL_MES1","Hrs",72,null,6821.06578461887,null,6821.06578461887,null,72,null,6821.06578461887,null,6821.06578461887,{"$nulls":6},6821.06578461887,1,{"$nulls":6},4,5,"2S"]
["2","03","07","10","","","LNX710-020","2.03.07.10","XAX30710","9682389","Linac Commissioning (LTU,EDump,UN Interface)","2008-02-28","2008-09-30",null,"X","SL_PHPD1","Hrs",516,null,42812.23496963509,null,42812.23496963509,null,516,null,42812.23496963509,null,42812.23496963509,{"$nulls":6},42812.23496963509,1,{"$nulls":6},4,5,"2S"]
["2","03","07","10","","","LNX710-020","2.03.07.10","XAX30710","9682389","Linac Commissioning (LTU,EDump,UN Interface)","2008-02-28","2008-09-30",null,"X","SL_MFAT1","Hrs",50,null,5084.42508,null,5084.42508,null,50,null,5084.42508,null,5084.42508,{"$nulls":6},5084.42508,1,{"$nulls":6},4,5,"2S"]
["2","04","  ","  ","  ","  ",{"$nulls":4},"UNDULATOR SYSTEM (OPC)                                      ",{"$nulls":6},28240,2024655,3001451.983324363,2156438.0197369424,5003519.475591301,null,25934.36,1899273.71,2750118.5663383426,2020784.8539325995,4770903.4202709375,0,null,113740.86434666,null,1370298.3782703765,null,1447033.9281492964,null,1839830.2495046088,null,null,133730.8116201886]
["2","04","01","01","","","UN11_TX010","2.04.01.01","XBA40101",null,"SLAC Indirect Tax - FY08 (PreOps)","2007-10-01","2008-09-30","A","X","SL_MSXX1","$$",null,30000,null,31580.28,31580.28,null,null,30000,null,31580.28,31580.28,{"$nulls":6},31580.28,1,{"$nulls":6},4,1,"4A"]
["2","04","01","01","","","UN11_00282","2.04.01.01","XBB40101",null,"Oversee Quality Assurance","2007-04-03","2008-02-15",null,"X","AN_ADMN1","Hrs",684,null,78634.38682691529,null,78634.38682691529,null,622.44,null,71506.7084888031,null,71506.7084888031,{"$nulls":4},40700.359234192954,0.57,30806.34925461014,0.43,{"$nulls":6},4,1,"4A"]
["2","04","01","01","","","UN11_00297","2.04.01.01","XBB40101",null,"CPUs and Software","2007-04-03","2008-02-19",null,"X","AN_MSEG1","$$",null,10282,null,11658.792693652253,null,null,null,9356.62,null,10609.932234439228,10609.932234439228,{"$nulls":4},5963.968119358697,0.56,4645.964115080531,0.44,{"$nulls":6},4,1,"4A"]
["2","04","02","01","  ","  ",{"$nulls":4},"Controls Management and Integration                         ",{"$nulls":6},0,87444,0,94518.0711616,94518.0711616,null,0,87444,0,94518.0711616,94518.0711616,0,null,5841.5872,null,88676.4839616,null,0,null,0,null,null,0]
["2","04","02","01","","","UN46_00253","2.04.02.01","SBA40201",null,"AWARD:  LDB Power Supply (1)","2006-08-01","2006-08-02",null,"X","SL_AW1","$$",null,4996,null,5271.7792,5271.7792,null,null,4996,null,5271.7792,5271.7792,null,null,5271.7792,1,{"$nulls":10},3,3,"2G","ANL"]
["2","04","03","03","  ","  ",{"$nulls":4},"1st Article Undulators & Long Lead Procurements             ",{"$nulls":6},191,0,21897.639960244524,0,21897.639960244524,null,191,0,21897.639960244524,0,21897.639960244524,0,null,0,null,14798.954478626794,null,7098.68548161773,null,0,null,null,0]
["2","04","03","04","","","UN33_MXD22","2.04.03.04","SBC40304",null,"RCV: Ti Strongback Article 37","2008-10-28","2008-10-28","A","S","AN_MSSF1","$$",null,32220,null,33089.94,33089.94,null,null,32220,null,33089.94,33089.94,{"$nulls":8},33089.94,1,{"$nulls":5},3,"4A"]
["2","04","03","04","","","UN34_MXD13","2.04.03.04","SBC40304",null,"Fab/Assemble Shipping Crate - Und Mag Article 36","2008-11-17","2008-11-17","A3","S","AN_MSSF1","$$",null,3000,null,3081,3081,null,null,3000,null,3081,3081,{"$nulls":8},3081,1,{"$nulls":4},1,3,"4A"]
["2","04","03","04","","","UN34_MXD32","2.04.03.04","SBC40304",null,"RCV: Undulator Magnet Article 38","2008-10-23","2008-10-23","A3","S","AN_MSSF1","$$",null,90263,null,92700.101,92700.101,null,null,90263,null,92700.101,92700.101,{"$nulls":8},92700.101,1,{"$nulls":4},1,3,"4A"]
["2","04","03","04","","","UN35_00177","2.04.03.04","SBC40304",null,"Evaluate1st Article Stages & Stands","2008-10-01","2008-10-14","A","S","AN_MDD1","Hrs",8,null,562.1172610019556,null,562.1172610019556,null,8,null,562.1172610019556,null,562.1172610019556,{"$nulls":8},562.1172610019556,1,0.3,168.6351783005867,1.15,1.15,null,3,"4A"]
["2","04","03","06","","","UN362_0345","2.04.03.06","SBA40306","9682240","Pre-assemble Girder - 34","2008-10-03","2008-10-09","S","S","SL_SEE1","Hrs",8,null,1028.3921079193676,null,1028.3921079193676,null,8,null,1028.3921079193676,null,1028.3921079193676,{"$nulls":8},1028.3921079193676,1,{"$nulls":4},4,3,"4B"]
["2","04","03","06","","","UN362_0352","2.04.03.06","SBA40306","9682240","Fiducialize Undulator - 35","2008-12-11","2008-12-15","S","S","SL_MFAT1","Hrs",24,null,2503.9776726719992,null,2503.9776726719992,null,24,null,2503.9776726719992,null,2503.9776726719992,{"$nulls":8},2503.9776726719992,1,{"$nulls":4},3,4,"4B"]
["2","04","03","06","","","UN362_0382","2.04.03.06","SBA40306","9682240","Fiducialize Undulator - 38","2009-01-14","2009-01-16","S","S","SL_MFAT1","Hrs",24,null,2503.9776726719992,null,2503.9776726719992,null,24,null,2503.9776726719992,null,2503.9776726719992,{"$nulls":8},2503.9776726719992,1,{"$nulls":4},3,4,"4B"]
["2","04","03","06","","","UN362_M010","2.04.03.06","SBA40306","9682240","Tune Master Undulator (after #8)","2007-05-04","2007-05-07","S","S","SL_PHSS1","Hrs",16,null,1712.75977014912,null,1712.75977014912,null,16,null,1712.75977014912,null,1712.75977014912,{"$nulls":4},1712.75977014912,1,{"$nulls":8},3,4,"4B"]
["2","04","03","06","","","UN362_M020","2.04.03.06","SBA40306","9682240","Tune Master Undulator (after #16)","2007-07-02","2007-07-03","S","S","SL_PHSS1","Hrs",16,null,1712.75977014912,null,1712.75977014912,null,16,null,1712.75977014912,null,1712.75977014912,{"$nulls":4},1712.75977014912,1,{"$nulls":8},3,4,"4B"]
["2","04","03","06","","","UN36_02650","2.04.03.06","SBA40306","9682240","Magnetic Measure and Fiducialize Quadrupole - 34","2008-10-01","2008-10-02","S","S","SL_PHSS1","Hrs",4,null,450.7452776197302,null,450.7452776197302,null,4,null,450.7452776197302,null,450.7452776197302,{"$nulls":8},450.7452776197302,1,{"$nulls":4},3,4,"4B"]
["2","04","03","06","","","UN36_02670","2.04.03.06","SBA40306","9682240","Magnetic Measure and Fiducialize Quadrupole - 35","2008-10-01","2008-10-02","S","S","SL_MES1","Hrs",4,null,388.8007511632175,null,388.8007511632175,null,4,null,388.8007511632175,null,388.8007511632175,{"$nulls":8},388.8007511632175,1,{"$nulls":4},3,4,"4B"]
["2","04","03","06","","","UN36_02690","2.04.03.06","SBA40306","9682240","Magnetic Measure and Fiducialize Quadrupole - 36","2008-10-03","2008-10-06","S","S","SL_MFAT1","Hrs",8,null,834.6592242239998,null,834.6592242239998,null,8,null,834.6592242239998,null,834.6592242239998,{"$nulls":8},834.6592242239998,1,{"$nulls":4},3,4,"4B"]
["2","04","03","08","  ","  ",{"$nulls":4},"Fixed Supports                                              ",{"$nulls":6},0,36800,0,40212.3904,40212.3904,null,0,36800,0,40212.3904,40212.3904,0,null,40212.3904,null,0,null,0,null,0,null,null,0]
["2","04","04","02","","","UN42_00343","2.04.04.02","SBA40402",null,"AWARD:  Polish (4)","2007-02-05","2007-02-05",null,"S","AN_AW1","$$",null,832,null,932.7875880960001,932.7875880960001,null,null,0,null,0,0,{"$nulls":14},3,3,"4A"]
["2","04","04","03","","","UN43_00451","2.04.04.03","SBA40403",null,"REC:  Standard Bellows Module (4)","2007-03-28","2007-05-22","A","S","AA_MSEG1","$$",null,14304,null,16036.771226112001,16036.771226112001,null,null,14304,null,16036.771226112001,16036.771226112001,{"$nulls":4},16036.771226112001,1,{"$nulls":8},3,3,"4A"]
["2","04","04","06","","","UN46_00321","2.04.04.06","SBA40406",null,"AWARD: LDB Ion Pump Support (1)","2007-01-30","2007-01-31","A","S","AN_AW1","$$",null,350,null,392.39862480000005,392.39862480000005,null,null,350,null,392.39862480000005,392.39862480000005,{"$nulls":4},392.39862480000005,1,{"$nulls":8},3,3,"4A"]
["2","04","04","09","  ","  ",{"$nulls":4},"Baking System                                               "]
["2","04","05","05","","","UN505_0213","2.04.05.05","SBA40505",null,"REC: Support & Alignment Mechanism (2)","2007-01-15","2007-03-23","A","S","AA_MSEG1","$$",null,5000,null,5605.694640000001,5605.694640000001,null,null,5000,null,5605.694640000001,5605.694640000001,{"$nulls":4},5605.694640000001,1,{"$nulls":8},3,3,"4A"]
["2","04","05","05","","","UN505_0245","2.04.05.05","SBA40505",null,"AWARD: Local Oscillator (4)","2007-01-10","2007-01-12","A","S","AN_AW1","$$",null,6000,null,6726.833568000001,6726.833568000001,null,null,6000,null,6726.833568000001,6726.833568000001,{"$nulls":4},6726.833568000001,1,{"$nulls":8},3,3,"4A"]
["2","04","05","05","","","UN505_0247","2.04.05.05","SBA40505",null,"Pack/Ship Spares Lot (4) Undulator RFBPM to SLAC","2007-09-24","2007-09-24",null,"S","AN_MFAT1","Hrs",24,null,1601.9665849324801,null,1601.9665849324801,null,24,null,1601.9665849324801,null,1601.9665849324801,{"$nulls":4},1601.9665849324801,1,{"$nulls":8},3,3,"4A"]
["2","04","05","08","  ","  ",{"$nulls":4},"Beam Loss Monitoring                                        ",{"$nulls":6},0,15874,0,17796.959343072,17796.959343072,null,0,15874,0,17796.959343072,17796.959343072,0,null,0,null,17796.959343072,null,0,null,0,null,null,0]
["2","04","05","09","  ","  ",{"$nulls":4},"Radiation Detection Monitor (RDM)                           "]
["2","04","06","01","","","UN601_1921","2.04.06.01","XBA40601","9682371","Commission Hydrostatic Level System","2006-08-01","2006-08-28","S","X","SL_CP1","Hrs",181,null,16719.25647051,null,16719.25647051,null,181,null,16719.25647051,null,16719.25647051,null,null,16719.25647051,1,{"$nulls":10},4,5,"4A"]
["2","05","01","  ","  ","  ",{"$nulls":4},"System Management & Integration                             ",{"$nulls":6},11290,0,1975026.5664855645,0,1975026.5664855645,null,11290,0,1975026.5664855645,0,1975026.5664855645,0,null,0,null,0,null,1400820.413909685,null,574206.1525758795,null,null,0]
["2","05","01","01","  ","  ",{"$nulls":4},"Management                                                  ",{"$nulls":6},11290,0,1975026.5664855645,0,1975026.5664855645,null,11290,0,1975026.5664855645,0,1975026.5664855645,0,null,0,null,0,null,1400820.413909685,null,574206.1525758795,null,null,0]
["2","05","01","01","","","XT_9626","2.05.01.01","XKA50101",null,"Management & Oversight - FY-08","2008-03-03","2008-09-30",null,"X","LL_SEE1","Hrs",536,null,99640.52853950768,null,99640.52853950768,null,536,null,99640.52853950768,null,99640.52853950768,{"$nulls":6},99640.52853950768,1,{"$nulls":6},4,1,"5A"]
["2","05","01","01","","","XT_9626","2.05.01.01","XKA50101",null,"Management & Oversight - FY-08","2008-03-03","2008-09-30",null,"X","LL_PHSS1","Hrs",1073,null,235353.15010730768,null,235353.15010730768,null,1073,null,235353.15010730768,null,235353.15010730768,{"$nulls":6},235353.15010730768,1,{"$nulls":6},4,1,"5A"]
["2","05","01","01","","","XT_9626","2.05.01.01","XKA50101",null,"Management & Oversight - FY-08","2008-03-03","2008-09-30",null,"X","LL_ME1","Hrs",1073,null,199466.9535874846,null,199466.9535874846,null,1073,null,199466.9535874846,null,199466.9535874846,{"$nulls":6},199466.9535874846,1,{"$nulls":6},4,1,"5A"]
["2","05","01","01","","","XT_9629","2.05.01.01","XKB50101",null,"Management & Oversight - FY-09","2008-10-01","2009-03-31",null,"X","LL_SEE1","Hrs",428,null,81632.36227340568,null,81632.36227340568,null,428,null,81632.36227340568,null,81632.36227340568,{"$nulls":8},81632.36227340568,1,{"$nulls":4},4,1,"5A"]
["2","05","01","01","","","XT_9629","2.05.01.01","XKB50101",null,"Management & Oversight - FY-09","2008-10-01","2009-03-31",null,"X","LL_PHSS1","Hrs",857,null,192862.80456577116,null,192862.80456577116,null,857,null,192862.80456577116,null,192862.80456577116,{"$nulls":8},192862.80456577116,1,{"$nulls":4},4,1,"5A"]
["2","05","01","01","","","XT_9629","2.05.01.01","XKB50101",null,"Management & Oversight - FY-09","2008-10-01","2009-03-31",null,"X","LL_ME1","Hrs",857,null,163455.45436520717,null,163455.45436520717,null,857,null,163455.45436520717,null,163455.45436520717,{"$nulls":8},163455.45436520717,1,{"$nulls":4},4,1,"5A"]
["2","05","01","01","","","XT_3454","2.05.01.01","XKC50101",null,"LLNL - Commissioning Team","2008-04-01","2008-09-30",null,"X","LL_PHS1","Hrs",896,null,177975.05678916923,null,177975.05678916923,null,896,null,177975.05678916923,null,177975.05678916923,{"$nulls":6},177975.05678916923,1,{"$nulls":6},5,1,"5A"]
["2","05","01","01","","","XT_3454","2.05.01.01","XKC50101",null,"LLNL - Commissioning Team","2008-04-01","2008-09-30",null,"X","LL_MFAT1","Hrs",448,null,64711.75096356924,null,64711.75096356924,null,448,null,64711.75096356924,null,64711.75096356924,{"$nulls":6},64711.75096356924,1,{"$nulls":6},5,1,"5A"]
["2","05","01","01","","","XT_3454","2.05.01.01","XKC50101",null,"LLNL - Commissioning Team","2008-04-01","2008-09-30",null,"X","LL_ME1","Hrs",896,null,166563.27158843074,null,166563.27158843074,null,896,null,166563.27158843074,null,166563.27158843074,{"$nulls":6},166563.27158843074,1,{"$nulls":6},5,1,"5A"]
["2","05","01","01","","","XT_3454","2.05.01.01","XKC50101",null,"LLNL - Commissioning Team","2008-04-01","2008-09-30",null,"X","LL_EE1","Hrs",768,null,142768.51850436922,null,142768.51850436922,null,768,null,142768.51850436922,null,142768.51850436922,{"$nulls":6},142768.51850436922,1,{"$nulls":6},5,1,"5A"]
["2","05","01","01","","","XT_3454","2.05.01.01","XKC50101",null,"LLNL - Commissioning Team","2008-04-01","2008-09-30",null,"X","LL_CP1","Hrs",896,null,178838.44544935387,null,178838.44544935387,null,896,null,178838.44544935387,null,178838.44544935387,{"$nulls":6},178838.44544935387,1,{"$nulls":6},5,1,"5A"]
["2","05","01","01","","","XTOPS_0000","2.05.01.01","XKZ50101",null,"XTOD Pre-Operations","2008-04-04","2009-03-31",null,"X","SL_PHS1","Hrs",854,null,74657.12069570462,null,74657.12069570462,null,854,null,74657.12069570462,null,74657.12069570462,{"$nulls":6},37225.157133592336,0.5,37431.96356211229,0.5,{"$nulls":4},5,5,"5A"]
["2","05","01","01","","","XTOPS_0000","2.05.01.01","XKZ50101",null,"XTOD Pre-Operations","2008-04-04","2009-03-31",null,"X","SL_ME1","Hrs",854,null,101944.08001431011,null,101944.08001431011,null,854,null,101944.08001431011,null,101944.08001431011,{"$nulls":6},50830.843220431634,0.5,51113.236793878474,0.5,{"$nulls":4},5,5,"5A"]
["2","05","01","01","","","XTOPS_0000","2.05.01.01","XKZ50101",null,"XTOD Pre-Operations","2008-04-04","2009-03-31",null,"X","SL_EE1","Hrs",854,null,95157.06904197334,null,95157.06904197334,null,854,null,95157.06904197334,null,95157.06904197334,{"$nulls":6},47446.7380264687,0.5,47710.33101550464,0.5,{"$nulls":4},5,5,"5A"]
["2","05","02","  ","  ","  ",{"$nulls":4},"Controls                                                    "]
["2","05","02","01","  ","  ",{"$nulls":4},"Controls - EPICS                                            "]
["2","05","02","02","  ","  ",{"$nulls":4},"Controls - System                                           "]
["2","05","03","  ","  ","  ",{"$nulls":4},"Mechanical & Vacuum Subsystem                               "]
["2","05","03","01","  ","  ",{"$nulls":4},"Vacuum Systems Engineering                                  "]
["2","05","03","02","  ","  ",{"$nulls":4},"Mech/Vac Front End                                          "]
["2","05","03","03","  ","  ",{"$nulls":4},"Mech/Vac Near Hall                                          "]
["2","05","03","04","  ","  ",{"$nulls":4},"Mech/Vac Tunnel                                             "]
["2","05","03","05","  ","  ",{"$nulls":4},"Mech/Vac Far Hall                                           "]
["2","05","04","  ","  ","  ",{"$nulls":4},"Optical Subsystem                                           ",{"$nulls":6},0,905000,0,1024539.762111,1024539.762111,null,0,905000,0,1024539.762111,1024539.762111,0,null,0,null,0,null,473230.49580000003,null,551309.266311,null,null,0]
["2","05","04","01","  ","  ",{"$nulls":4},"Optical Systems Engineering                                 "]
["2","05","04","02","  ","  ",{"$nulls":4},"Facility Optics                                             ",{"$nulls":6},0,905000,0,1024539.762111,1024539.762111,null,0,905000,0,1024539.762111,1024539.762111,0,null,0,null,0,null,473230.49580000003,null,551309.266311,null,null,0]
["2","05","04","02","","","XT2420010","2.05.04.02","SKZ50402",null,"Procure Spares - Part 2","2008-10-01","2009-01-07",null,"S","LL_MSXX1","$$",null,405000,null,437418.45989999996,437418.45989999996,null,null,405000,null,437418.45989999996,437418.45989999996,{"$nulls":8},437418.45989999996,1,{"$nulls":4},4,3,"5A"]
["2","05","04","02","","","XT2420010","2.05.04.02","SKZ50402",null,"Procure Spares - Part 2","2008-10-01","2009-01-07",null,"S","LL_MSCS1","$$",null,95000,null,113890.806411,113890.806411,null,null,95000,null,113890.806411,113890.806411,{"$nulls":8},113890.806411,1,{"$nulls":4},4,3,"5A"]
["2","05","04","02","","","XT_546","2.05.04.02","SKZ50402",null,"Procure Spares - Part 1","2008-04-01","2008-06-24",null,"S","LL_MSCS1","$$",null,405000,null,473230.49580000003,473230.49580000003,null,null,405000,null,473230.49580000003,473230.49580000003,{"$nulls":6},473230.49580000003,1,{"$nulls":6},4,3,"5A"]
["2","05","04","03","  ","  ",{"$nulls":4},"End Station Optics                                          "]
["2","05","04","04","  ","  ",{"$nulls":4},"Crystals & Gratings                                         "]
["2","05","05","  ","  ","  ",{"$nulls":4},"Diagnostics Subsystem                                       ",{"$nulls":6},5089,50000,998609.977613527,56943,1055552.9776135269,null,3123.96,50000,616334.0851416808,56943,673277.0851416808,0,null,0,null,333763.47385892307,null,339513.6112827577,null,0,null,null,0]
["2","05","05","01","  ","  ",{"$nulls":4},"Diagnostic Systems Engineering                              "]
["2","05","05","02","  ","  ",{"$nulls":4},"Modeling & Simulation                                       ",{"$nulls":6},5089,0,998609.977613527,0,998609.977613527,null,3123.96,0,616334.0851416808,0,616334.0851416808,0,null,0,null,276820.47385892307,null,339513.6112827577,null,0,null,null,0]
["2","05","05","02","","","XT_6501","2.05.05.02","XKZ50502",null,"Modeling & Simulation - FY-07","2006-10-02","2007-09-28",null,"X","LL_CP1","Hrs",3388,null,659096.3663307693,null,659096.3663307693,null,1422.96,null,276820.47385892307,null,276820.47385892307,{"$nulls":4},276820.47385892307,1,{"$nulls":8},4,2,"5A"]
["2","05","05","02","","","XT_6502","2.05.05.02","XKZ50502",null,"Modeling & Simulation - FY-08","2007-10-01","2008-09-30",null,"X","LL_CP1","Hrs",1701,null,339513.6112827577,null,339513.6112827577,null,1701,null,339513.6112827577,null,339513.6112827577,{"$nulls":6},339513.6112827577,1,{"$nulls":6},4,2,"5A"]
["2","05","05","03","  ","  ",{"$nulls":4},"Facility Diagnostics                                        ",{"$nulls":6},0,50000,0,56943,56943,null,0,50000,0,56943,56943,0,null,0,null,56943,null,0,null,0,null,null,0]
["2","05","05","03","","","XT_4436","2.05.05.03","SKZ50503",null,"Procure Spares - Direct Imager","2006-10-03","2007-01-11",null,"S","LL_MSCS1","$$",null,50000,null,56943,56943,null,null,50000,null,56943,56943,{"$nulls":4},56943,1,{"$nulls":8},4,3,"5A"]
["2","05","05","04","  ","  ",{"$nulls":4},"Commissioning Diagnostics                                   "]
["2","05","06","  ","  ","  ",{"$nulls":4},"X-Ray Transport & Diag. System Commissioning                "]
["2","05","06","01","  ","  ",{"$nulls":4},"X-Ray Transport & Diag. System Commissioning                "]
["2","06","  ","  ","  ","  ",{"$nulls":4},"X-RAY END STATION SYSTEMS (OPC)                             ",{"$nulls":6},16440,3497554,1733411.6512691744,3854396.5101021156,5499051.2572325505,null,16440,2799304,1733411.6512691744,3101051.4539421154,4834463.105211289,0,null,15945.248445535468,null,937061.6169437362,null,2843958.386381993,null,1037497.8534400249,null,null,0]
["2","06","01","  ","  ","  ",{"$nulls":4},"XE System Mgmt & Integration                                ",{"$nulls":6},8764,20000,959798.4904586291,29809.258007999997,989607.7484666291,null,8764,20000,959798.4904586291,29809.258007999997,989607.7484666291,0,null,0,null,0,null,489610.2670929487,null,499997.4813736804,null,null,0]
["2","06","01","","","","XEOPS_0000","2.06.01","XKZ601",null,"X-Ray End Stations Pre-Operations","2008-02-08","2009-03-31",null,"X","SL_PHS1","Hrs",3962,null,345761.53554013884,null,345761.53554013884,null,3962,null,345761.53554013884,null,345761.53554013884,{"$nulls":6},195682.7874999347,0.57,150078.74804020417,0.43,{"$nulls":4},4,5,"6A"]
["2","06","01","","","","XEOPS_0000","2.06.01","XKZ601",null,"X-Ray End Stations Pre-Operations","2008-02-08","2009-03-31",null,"X","SL_PHPU","Hrs",1981,null,291029.7454247341,null,291029.7454247341,null,1981,null,291029.7454247341,null,291029.7454247341,{"$nulls":6},164707.4818231109,0.57,126322.26360162318,0.43,{"$nulls":4},4,5,"6A"]
["2","06","01","","","","XEOPS_0000","2.06.01","XKZ601",null,"X-Ray End Stations Pre-Operations","2008-02-08","2009-03-31",null,"X","SL_ME1","Hrs",991,null,118093.67453038489,null,118093.67453038489,null,991,null,118093.67453038489,null,118093.67453038489,{"$nulls":6},66834.78942247202,0.57,51258.885107912865,0.43,{"$nulls":4},4,5,"6A"]
["2","06","01","","","","XEOPS_0000","2.06.01","XKZ601",null,"X-Ray End Stations Pre-Operations","2008-02-08","2009-03-31",null,"X","SL_EE1","Hrs",991,null,110231.49102067269,null,110231.49102067269,null,991,null,110231.49102067269,null,110231.49102067269,{"$nulls":6},62385.20834743107,0.57,47846.28267324163,0.43,{"$nulls":4},4,5,"6A"]
["2","06","01","","","","XE_036","2.06.01","XKZ601",null,"Management & Oversight - FY09","2008-10-01","2009-03-31",null,"X","SL_EE1","Hrs",839,null,94682.04394269855,null,94682.04394269855,null,839,null,94682.04394269855,null,94682.04394269855,{"$nulls":8},94682.04394269855,1,{"$nulls":4},4,1,"6A"]
["2","06","01","","","","XE_0491","2.06.01","XKZ601",null,"Travel FY-09","2008-10-01","2009-03-31",null,"X","SL_MSTR1","$$",null,20000,null,29809.258007999997,29809.258007999997,null,null,20000,null,29809.258007999997,29809.258007999997,{"$nulls":8},29809.258007999997,1,{"$nulls":4},1,1,"6A"]
["2","06","01","01","  ","  ",{"$nulls":4},"Management                                                  "]
["2","06","02","  ","  ","  ",{"$nulls":4},"Controls Subsystem                                          ",{"$nulls":6},400,552104,38572.635231215085,607195.3434790175,645767.9787102327,null,400,552104,38572.635231215085,607195.3434790175,645767.9787102327,0,null,3625.5508751354696,null,241223.02235374635,null,398350.82507086406,null,2568.580410486727,null,null,0]
["2","06","02","01","  ","  ",{"$nulls":4},"Cabling                                                     "]
["2","06","02","02","  ","  ",{"$nulls":4},"Network                                                     "]
["2","06","02","03","  ","  ",{"$nulls":4},"PC Support                                                  "]
["2","06","02","04","  ","  ",{"$nulls":4},"Beamline Controls                                           ",{"$nulls":6},0,552104,0,607195.3434790175,607195.3434790175,null,0,552104,0,607195.3434790175,607195.3434790175,0,null,0,null,233568.80068319998,null,373626.54279581754,null,0,null,null,0]
["2","06","02","04","","","XE2240010","2.06.02.04","RCA60204",null,"Development of LBL Laser Timing System","2007-05-01","2007-09-28",null,"R","SL_MSSC1","$$",null,215741,null,233568.80068319998,233568.80068319998,null,null,215741,null,233568.80068319998,233568.80068319998,{"$nulls":4},233568.80068319998,1,{"$nulls":8},5,2,"2G"]
["2","06","02","04","","","XE2240020","2.06.02.04","RCA60204",null,"LBL Timing Procurement (FY08)","2007-10-01","2008-09-30",null,"R","SL_MSSC1","$$",null,336363,null,373626.54279581754,373626.54279581754,null,null,336363,null,373626.54279581754,373626.54279581754,{"$nulls":6},373626.54279581754,1,{"$nulls":7},2,"2G"]
["2","06","02","05","  ","  ",{"$nulls":4},"X-Ray PPS                                                   "]
["2","06","02","06","  ","  ",{"$nulls":4},"X-Ray MPS                                                   "]
["2","06","02","07","  ","  ",{"$nulls":4},"Laser PPS                                                   "]
["2","06","02","08","  ","  ",{"$nulls":4},"R&D: 2D X-Ray Detector Controls                             ",{"$nulls":6},400,0,38572.635231215085,0,38572.635231215085,null,400,0,38572.635231215085,0,38572.635231215085,0,null,3625.5508751354696,null,7654.22167054636,null,24724.28227504653,null,2568.580410486727,null,null,0]
["2","06","02","08","","","XE628_0105","2.06.02.08","RBB60208",null,"Support Design of EPICS Interface","2006-08-01","2006-12-05",null,"R","SL_CP1","Hrs",80,null,7488.842791263429,null,7488.842791263429,null,80,null,7488.842791263429,null,7488.842791263429,null,null,3625.5508751354696,0.48,3863.2919161279597,0.52,{"$nulls":8},5,2,"2H","B. Dalesio"]
["2","06","02","08","","","XE628_0115","2.06.02.08","RBB60208",null,"Support Integration with Data Farm","2006-12-07","2007-02-28",null,"R","SL_CP1","Hrs",40,null,3790.9297544184,null,3790.9297544184,null,40,null,3790.9297544184,null,3790.9297544184,{"$nulls":4},3790.9297544184,1,{"$nulls":8},5,2,"2H","B. Dalesio"]
["2","06","02","08","","","XE628_0130","2.06.02.08","RBB60208",null,"Support Development of Control System","2007-10-29","2008-04-01",null,"R","SL_CP1","Hrs",120,null,11668.481784099835,null,11668.481784099835,null,120,null,11668.481784099835,null,11668.481784099835,{"$nulls":6},11668.481784099835,1,{"$nulls":6},5,2,"2H","B. Dalesio"]
["2","06","02","08","","","XE628_0135","2.06.02.08","RBB60208",null,"Prototype Development Support","2007-10-29","2008-04-01",null,"R","SL_CP1","Hrs",40,null,3889.4939280332783,null,3889.4939280332783,null,40,null,3889.4939280332783,null,3889.4939280332783,{"$nulls":6},3889.4939280332783,1,{"$nulls":6},5,3,"2H","B. Dalesio"]
["2","06","02","08","","","XE628_0145","2.06.02.08","RBB60208",null,"Support for delivery of 2D Detector","2008-04-02","2008-11-21",null,"R","SL_CP1","Hrs",120,null,11734.886973400146,null,11734.886973400146,null,120,null,11734.886973400146,null,11734.886973400146,{"$nulls":6},9166.306562913418,0.78,2568.580410486727,0.22,{"$nulls":4},5,3,"2H","B. Dalesio"]
["2","06","03","  ","  ","  ",{"$nulls":4},"Commissioning                                               ",{"$nulls":6},6636,0,662822.9093784249,0,662822.9093784249,null,6636,0,662822.9093784249,0,662822.9093784249,0,null,12319.697570399998,null,12640.009707230398,null,413489.87660929654,null,224373.32549149825,null,null,0]
["2","06","03","01","  ","  ",{"$nulls":4},"Commissioning - Controls                                    ",{"$nulls":6},3940,0,384583.55724251585,0,384583.55724251585,null,3940,0,384583.55724251585,0,384583.55724251585,0,null,12319.697570399998,null,12640.009707230398,null,285642.9318752727,null,73980.91808961304,null,null,0]
["2","06","03","01","","","XE_0341","2.06.03.01","XKC60301",null,"Test Near Hall - Cabling","2008-12-11","2009-01-06",null,"X","SL_PHS1","Hrs",40,null,3541.570038440737,null,3541.570038440737,null,40,null,3541.570038440737,null,3541.570038440737,{"$nulls":8},3541.570038440737,1,{"$nulls":4},4,5,"6A"]
["2","06","03","01","","","XE_0341","2.06.03.01","XKC60301",null,"Test Near Hall - Cabling","2008-12-11","2009-01-06",null,"X","SL_EE1","Hrs",40,null,4514.042619437357,null,4514.042619437357,null,40,null,4514.042619437357,null,4514.042619437357,{"$nulls":8},4514.042619437357,1,{"$nulls":4},4,5,"6A"]
["2","06","03","01","","","XE_2224","2.06.03.01","XKC60301",null,"Test Near Hall - Network","2008-06-10","2008-06-23",null,"X","SL_PHS1","Hrs",40,null,3451.822636768386,null,3451.822636768386,null,40,null,3451.822636768386,null,3451.822636768386,{"$nulls":6},3451.822636768386,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_2224","2.06.03.01","XKC60301",null,"Test Near Hall - Network","2008-06-10","2008-06-23",null,"X","SL_EE1","Hrs",40,null,4399.651659570551,null,4399.651659570551,null,40,null,4399.651659570551,null,4399.651659570551,{"$nulls":6},4399.651659570551,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_2224","2.06.03.01","XKC60301",null,"Test Near Hall - Network","2008-06-10","2008-06-23",null,"X","SL_CT1","Hrs",40,null,2920.5612580632037,null,2920.5612580632037,null,40,null,2920.5612580632037,null,2920.5612580632037,{"$nulls":6},2920.5612580632037,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_2224","2.06.03.01","XKC60301",null,"Test Near Hall - Network","2008-06-10","2008-06-23",null,"X","SL_CE1","Hrs",40,null,5334.634984096598,null,5334.634984096598,null,40,null,5334.634984096598,null,5334.634984096598,{"$nulls":6},5334.634984096598,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_2227","2.06.03.01","XKC60301",null,"Test Tunnel - Network","2008-07-09","2008-07-15",null,"X","SL_PHS1","Hrs",40,null,3451.822636768386,null,3451.822636768386,null,40,null,3451.822636768386,null,3451.822636768386,{"$nulls":6},3451.822636768386,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_2227","2.06.03.01","XKC60301",null,"Test Tunnel - Network","2008-07-09","2008-07-15",null,"X","SL_EE1","Hrs",40,null,4399.651659570551,null,4399.651659570551,null,40,null,4399.651659570551,null,4399.651659570551,{"$nulls":6},4399.651659570551,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_2227","2.06.03.01","XKC60301",null,"Test Tunnel - Network","2008-07-09","2008-07-15",null,"X","SL_CT1","Hrs",40,null,2920.5612580632037,null,2920.5612580632037,null,40,null,2920.5612580632037,null,2920.5612580632037,{"$nulls":6},2920.5612580632037,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_2227","2.06.03.01","XKC60301",null,"Test Tunnel - Network","2008-07-09","2008-07-15",null,"X","SL_CE1","Hrs",40,null,5334.634984096598,null,5334.634984096598,null,40,null,5334.634984096598,null,5334.634984096598,{"$nulls":6},5334.634984096598,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_2280","2.06.03.01","XKC60301",null,"Test Near Hall - PC Support","2008-04-15","2008-04-28",null,"X","SL_PHS1","Hrs",40,null,3451.822636768386,null,3451.822636768386,null,40,null,3451.822636768386,null,3451.822636768386,{"$nulls":6},3451.822636768386,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_2280","2.06.03.01","XKC60301",null,"Test Near Hall - PC Support","2008-04-15","2008-04-28",null,"X","SL_EE1","Hrs",40,null,4399.651659570551,null,4399.651659570551,null,40,null,4399.651659570551,null,4399.651659570551,{"$nulls":6},4399.651659570551,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_2280","2.06.03.01","XKC60301",null,"Test Near Hall - PC Support","2008-04-15","2008-04-28",null,"X","SL_CT1","Hrs",40,null,2920.5612580632037,null,2920.5612580632037,null,40,null,2920.5612580632037,null,2920.5612580632037,{"$nulls":6},2920.5612580632037,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_2280","2.06.03.01","XKC60301",null,"Test Near Hall - PC Support","2008-04-15","2008-04-28",null,"X","SL_CE1","Hrs",40,null,5334.634984096598,null,5334.634984096598,null,40,null,5334.634984096598,null,5334.634984096598,{"$nulls":6},5334.634984096598,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_2624","2.06.03.01","XKC60301",null,"Test Near Hall - Beamline Control","2008-02-01","2008-02-14",null,"X","SL_PHS1","Hrs",40,null,3451.822636768386,null,3451.822636768386,null,40,null,3451.822636768386,null,3451.822636768386,{"$nulls":6},3451.822636768386,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_2624","2.06.03.01","XKC60301",null,"Test Near Hall - Beamline Control","2008-02-01","2008-02-14",null,"X","SL_EE1","Hrs",40,null,4399.651659570551,null,4399.651659570551,null,40,null,4399.651659570551,null,4399.651659570551,{"$nulls":6},4399.651659570551,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_2624","2.06.03.01","XKC60301",null,"Test Near Hall - Beamline Control","2008-02-01","2008-02-14",null,"X","SL_CP1","Hrs",40,null,3889.4939280332783,null,3889.4939280332783,null,40,null,3889.4939280332783,null,3889.4939280332783,{"$nulls":6},3889.4939280332783,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_2624","2.06.03.01","XKC60301",null,"Test Near Hall - Beamline Control","2008-02-01","2008-02-14",null,"X","SL_CE1","Hrs",40,null,5334.634984096598,null,5334.634984096598,null,40,null,5334.634984096598,null,5334.634984096598,{"$nulls":6},5334.634984096598,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_2723","2.06.03.01","XKC60301",null,"Test Near Hall - Laser PPS","2007-10-16","2007-10-22",null,"X","SL_PHS1","Hrs",40,null,3451.822636768386,null,3451.822636768386,null,40,null,3451.822636768386,null,3451.822636768386,{"$nulls":6},3451.822636768386,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_2723","2.06.03.01","XKC60301",null,"Test Near Hall - Laser PPS","2007-10-16","2007-10-22",null,"X","SL_CE1","Hrs",40,null,5334.634984096598,null,5334.634984096598,null,40,null,5334.634984096598,null,5334.634984096598,{"$nulls":6},5334.634984096598,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_7040","2.06.03.01","XKC60301",null,"Integrate with Controls","2008-04-01","2008-04-28",null,"X","SL_PHS1","Hrs",80,null,6903.645273536772,null,6903.645273536772,null,80,null,6903.645273536772,null,6903.645273536772,{"$nulls":6},6903.645273536772,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_7040","2.06.03.01","XKC60301",null,"Integrate with Controls","2008-04-01","2008-04-28",null,"X","SL_EE1","Hrs",80,null,8799.303319141101,null,8799.303319141101,null,80,null,8799.303319141101,null,8799.303319141101,{"$nulls":6},8799.303319141101,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_7040","2.06.03.01","XKC60301",null,"Integrate with Controls","2008-04-01","2008-04-28",null,"X","SL_CT1","Hrs",80,null,5841.122516126407,null,5841.122516126407,null,80,null,5841.122516126407,null,5841.122516126407,{"$nulls":6},5841.122516126407,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_7040","2.06.03.01","XKC60301",null,"Integrate with Controls","2008-04-01","2008-04-28",null,"X","SL_CE1","Hrs",80,null,10669.269968193195,null,10669.269968193195,null,80,null,10669.269968193195,null,10669.269968193195,{"$nulls":6},10669.269968193195,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_923","2.06.03.01","XKC60301",null,"Test Near Hall - User Safeguards","2007-10-16","2007-10-22",null,"X","SL_PHS1","Hrs",40,null,3451.822636768386,null,3451.822636768386,null,40,null,3451.822636768386,null,3451.822636768386,{"$nulls":6},3451.822636768386,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_923","2.06.03.01","XKC60301",null,"Test Near Hall - User Safeguards","2007-10-16","2007-10-22",null,"X","SL_CE1","Hrs",40,null,5334.634984096598,null,5334.634984096598,null,40,null,5334.634984096598,null,5334.634984096598,{"$nulls":6},5334.634984096598,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_0241","2.06.03.01","XKZ60201",null,"Commission Far Hall - Cabling","2009-10-05","2009-10-30",null,"X","SL_TMUE1","Hrs",20,{"$nulls":5},20,{"$nulls":18},4,5,"6A"]
["2","06","03","01","","","XE_0241","2.06.03.01","XKZ60201",null,"Commission Far Hall - Cabling","2009-10-05","2009-10-30",null,"X","SL_CT1","Hrs",40,{"$nulls":5},40,{"$nulls":18},4,5,"6A"]
["2","06","03","01","","","XE_0241","2.06.03.01","XKZ60201",null,"Commission Far Hall - Cabling","2009-10-05","2009-10-30",null,"X","SL_CE1","Hrs",40,{"$nulls":5},40,{"$nulls":18},4,5,"6A"]
["2","06","03","01","","","XE_0291","2.06.03.01","XKZ60201",null,"Commission Tunnel - Cabling","2008-05-13","2008-06-10",null,"X","SL_TMUE1","Hrs",20,null,2265.9103542239995,null,2265.9103542239995,null,20,null,2265.9103542239995,null,2265.9103542239995,{"$nulls":6},2265.9103542239995,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_0291","2.06.03.01","XKZ60201",null,"Commission Tunnel - Cabling","2008-05-13","2008-06-10",null,"X","SL_CT1","Hrs",40,null,2920.5612580632037,null,2920.5612580632037,null,40,null,2920.5612580632037,null,2920.5612580632037,{"$nulls":6},2920.5612580632037,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_0291","2.06.03.01","XKZ60201",null,"Commission Tunnel - Cabling","2008-05-13","2008-06-10",null,"X","SL_CE1","Hrs",40,null,5334.634984096598,null,5334.634984096598,null,40,null,5334.634984096598,null,5334.634984096598,{"$nulls":6},5334.634984096598,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_0451","2.06.03.01","XKZ60201",null,"Commission FEE - Cabling","2009-01-12","2009-02-06",null,"X","SL_TMUE1","Hrs",20,null,2324.82403204392,null,2324.82403204392,null,20,null,2324.82403204392,null,2324.82403204392,{"$nulls":8},2324.82403204392,1,{"$nulls":4},4,5,"6A"]
["2","06","03","01","","","XE_0451","2.06.03.01","XKZ60201",null,"Commission FEE - Cabling","2009-01-12","2009-02-06",null,"X","SL_CT1","Hrs",40,null,2996.495861870512,null,2996.495861870512,null,40,null,2996.495861870512,null,2996.495861870512,{"$nulls":8},2996.495861870512,1,{"$nulls":4},4,5,"6A"]
["2","06","03","01","","","XE_0451","2.06.03.01","XKZ60201",null,"Commission FEE - Cabling","2009-01-12","2009-02-06",null,"X","SL_CE1","Hrs",40,null,5473.335513953867,null,5473.335513953867,null,40,null,5473.335513953867,null,5473.335513953867,{"$nulls":8},5473.335513953867,1,{"$nulls":4},4,5,"6A"]
["2","06","03","01","","","XE_0461","2.06.03.01","XKZ60201",null,"Commission Near Hall - Cabling","2009-01-07","2009-02-03",null,"X","SL_TMUE1","Hrs",20,null,2324.82403204392,null,2324.82403204392,null,20,null,2324.82403204392,null,2324.82403204392,{"$nulls":8},2324.82403204392,1,{"$nulls":4},4,5,"6A"]
["2","06","03","01","","","XE_0461","2.06.03.01","XKZ60201",null,"Commission Near Hall - Cabling","2009-01-07","2009-02-03",null,"X","SL_CT1","Hrs",40,null,2996.495861870512,null,2996.495861870512,null,40,null,2996.495861870512,null,2996.495861870512,{"$nulls":8},2996.495861870512,1,{"$nulls":4},4,5,"6A"]
["2","06","03","01","","","XE_0461","2.06.03.01","XKZ60201",null,"Commission Near Hall - Cabling","2009-01-07","2009-02-03",null,"X","SL_CE1","Hrs",40,null,5473.335513953867,null,5473.335513953867,null,40,null,5473.335513953867,null,5473.335513953867,{"$nulls":8},5473.335513953867,1,{"$nulls":4},4,5,"6A"]
["2","06","03","01","","","XE_2234","2.06.03.01","XKZ60202",null,"Commission - Network","2008-12-08","2009-01-15",null,"X","SL_PHS1","Hrs",40,null,3541.570038440737,null,3541.570038440737,null,40,null,3541.570038440737,null,3541.570038440737,{"$nulls":8},3541.570038440737,1,{"$nulls":4},4,5,"6A"]
["2","06","03","01","","","XE_2234","2.06.03.01","XKZ60202",null,"Commission - Network","2008-12-08","2009-01-15",null,"X","SL_EE1","Hrs",40,null,4514.042619437357,null,4514.042619437357,null,40,null,4514.042619437357,null,4514.042619437357,{"$nulls":8},4514.042619437357,1,{"$nulls":4},4,5,"6A"]
["2","06","03","01","","","XE_2234","2.06.03.01","XKZ60202",null,"Commission - Network","2008-12-08","2009-01-15",null,"X","SL_CT1","Hrs",40,null,2996.495861870512,null,2996.495861870512,null,40,null,2996.495861870512,null,2996.495861870512,{"$nulls":8},2996.495861870512,1,{"$nulls":4},4,5,"6A"]
["2","06","03","01","","","XE_2234","2.06.03.01","XKZ60202",null,"Commission - Network","2008-12-08","2009-01-15",null,"X","SL_CE1","Hrs",40,null,5473.335513953867,null,5473.335513953867,null,40,null,5473.335513953867,null,5473.335513953867,{"$nulls":8},5473.335513953867,1,{"$nulls":4},4,5,"6A"]
["2","06","03","01","","","XE_4404","2.06.03.01","XKZ60202",null,"Commission - Network","2008-12-08","2009-01-15",null,"X","SL_PHS1","Hrs",40,null,3541.570038440737,null,3541.570038440737,null,40,null,3541.570038440737,null,3541.570038440737,{"$nulls":8},3541.570038440737,1,{"$nulls":4},4,5,"6A"]
["2","06","03","01","","","XE_4404","2.06.03.01","XKZ60202",null,"Commission - Network","2008-12-08","2009-01-15",null,"X","SL_EE1","Hrs",140,null,15799.149168030748,null,15799.149168030748,null,140,null,15799.149168030748,null,15799.149168030748,{"$nulls":8},15799.149168030748,1,{"$nulls":4},4,5,"6A"]
["2","06","03","01","","","XE_4404","2.06.03.01","XKZ60202",null,"Commission - Network","2008-12-08","2009-01-15",null,"X","SL_CT1","Hrs",40,null,2996.495861870512,null,2996.495861870512,null,40,null,2996.495861870512,null,2996.495861870512,{"$nulls":8},2996.495861870512,1,{"$nulls":4},4,5,"6A"]
["2","06","03","01","","","XE_4404","2.06.03.01","XKZ60202",null,"Commission - Network","2008-12-08","2009-01-15",null,"X","SL_CE1","Hrs",40,null,5473.335513953867,null,5473.335513953867,null,40,null,5473.335513953867,null,5473.335513953867,{"$nulls":8},5473.335513953867,1,{"$nulls":4},4,5,"6A"]
["2","06","03","01","","","XE_2294","2.06.03.01","XKZ60203",null,"Commission - PC Support","2008-07-24","2008-08-20",null,"X","SL_PHS1","Hrs",40,null,3451.822636768386,null,3451.822636768386,null,40,null,3451.822636768386,null,3451.822636768386,{"$nulls":6},3451.822636768386,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_2294","2.06.03.01","XKZ60203",null,"Commission - PC Support","2008-07-24","2008-08-20",null,"X","SL_EE1","Hrs",40,null,4399.651659570551,null,4399.651659570551,null,40,null,4399.651659570551,null,4399.651659570551,{"$nulls":6},4399.651659570551,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_2294","2.06.03.01","XKZ60203",null,"Commission - PC Support","2008-07-24","2008-08-20",null,"X","SL_CP1","Hrs",40,null,3889.4939280332783,null,3889.4939280332783,null,40,null,3889.4939280332783,null,3889.4939280332783,{"$nulls":6},3889.4939280332783,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_2294","2.06.03.01","XKZ60203",null,"Commission - PC Support","2008-07-24","2008-08-20",null,"X","SL_CE1","Hrs",40,null,5334.634984096598,null,5334.634984096598,null,40,null,5334.634984096598,null,5334.634984096598,{"$nulls":6},5334.634984096598,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_2635","2.06.03.01","XKZ60204",null,"Commission - Beamline Control","2008-04-14","2008-05-09",null,"X","SL_PHS1","Hrs",80,null,6903.645273536772,null,6903.645273536772,null,80,null,6903.645273536772,null,6903.645273536772,{"$nulls":6},6903.645273536772,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_2635","2.06.03.01","XKZ60204",null,"Commission - Beamline Control","2008-04-14","2008-05-09",null,"X","SL_CT1","Hrs",80,null,5841.122516126407,null,5841.122516126407,null,80,null,5841.122516126407,null,5841.122516126407,{"$nulls":6},5841.122516126407,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_2635","2.06.03.01","XKZ60204",null,"Commission - Beamline Control","2008-04-14","2008-05-09",null,"X","SL_CP1","Hrs",80,null,7778.987856066557,null,7778.987856066557,null,80,null,7778.987856066557,null,7778.987856066557,{"$nulls":6},7778.987856066557,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_2635","2.06.03.01","XKZ60204",null,"Commission - Beamline Control","2008-04-14","2008-05-09",null,"X","SL_CE1","Hrs",80,null,10669.269968193195,null,10669.269968193195,null,80,null,10669.269968193195,null,10669.269968193195,{"$nulls":6},10669.269968193195,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_108","2.06.03.01","XKZ60205",null,"Commission FEE - X-Ray PPS","2008-05-06","2008-06-03",null,"X","SL_ME1","Hrs",40,null,4713.453717458586,null,4713.453717458586,null,40,null,4713.453717458586,null,4713.453717458586,{"$nulls":6},4713.453717458586,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_108","2.06.03.01","XKZ60205",null,"Commission FEE - X-Ray PPS","2008-05-06","2008-06-03",null,"X","SL_CT1","Hrs",40,null,2920.5612580632037,null,2920.5612580632037,null,40,null,2920.5612580632037,null,2920.5612580632037,{"$nulls":6},2920.5612580632037,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_108","2.06.03.01","XKZ60205",null,"Commission FEE - X-Ray PPS","2008-05-06","2008-06-03",null,"X","SL_CE1","Hrs",40,null,5334.634984096598,null,5334.634984096598,null,40,null,5334.634984096598,null,5334.634984096598,{"$nulls":6},5334.634984096598,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_3033","2.06.03.01","XKZ60205",null,"Commission Near Hall - X-Ray PPS","2006-08-01","2006-08-28",null,"X","SL_ME1","Hrs",40,null,4477.592077199999,null,4477.592077199999,null,40,null,4477.592077199999,null,4477.592077199999,null,null,4477.592077199999,1,{"$nulls":10},4,5,"6A"]
["2","06","03","01","","","XE_3033","2.06.03.01","XKZ60205",null,"Commission Near Hall - X-Ray PPS","2006-08-01","2006-08-28",null,"X","SL_CT1","Hrs",40,null,2774.4161147999994,null,2774.4161147999994,null,40,null,2774.4161147999994,null,2774.4161147999994,null,null,2774.4161147999994,1,{"$nulls":10},4,5,"6A"]
["2","06","03","01","","","XE_3033","2.06.03.01","XKZ60205",null,"Commission Near Hall - X-Ray PPS","2006-08-01","2006-08-28",null,"X","SL_CE1","Hrs",40,null,5067.689378399999,null,5067.689378399999,null,40,null,5067.689378399999,null,5067.689378399999,null,null,5067.689378399999,1,{"$nulls":10},4,5,"6A"]
["2","06","03","01","","","XE_458","2.06.03.01","XKZ60205",null,"Commission Far Hall X-Ray PPS","2008-01-08","2008-02-05",null,"X","SL_ME1","Hrs",40,null,4713.453717458586,null,4713.453717458586,null,40,null,4713.453717458586,null,4713.453717458586,{"$nulls":6},4713.453717458586,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_458","2.06.03.01","XKZ60205",null,"Commission Far Hall X-Ray PPS","2008-01-08","2008-02-05",null,"X","SL_CT1","Hrs",40,null,2920.5612580632037,null,2920.5612580632037,null,40,null,2920.5612580632037,null,2920.5612580632037,{"$nulls":6},2920.5612580632037,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_458","2.06.03.01","XKZ60205",null,"Commission Far Hall X-Ray PPS","2008-01-08","2008-02-05",null,"X","SL_CE1","Hrs",40,null,5334.634984096598,null,5334.634984096598,null,40,null,5334.634984096598,null,5334.634984096598,{"$nulls":6},5334.634984096598,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_463","2.06.03.01","XKZ60205",null,"Commission Tunnel - X-Ray PPS","2009-09-07","2009-10-02",null,"X","SL_ME1","Hrs",40,{"$nulls":5},40,{"$nulls":18},4,5,"6A"]
["2","06","03","01","","","XE_463","2.06.03.01","XKZ60205",null,"Commission Tunnel - X-Ray PPS","2009-09-07","2009-10-02",null,"X","SL_CT1","Hrs",40,{"$nulls":5},40,{"$nulls":18},4,5,"6A"]
["2","06","03","01","","","XE_463","2.06.03.01","XKZ60205",null,"Commission Tunnel - X-Ray PPS","2009-09-07","2009-10-02",null,"X","SL_CE1","Hrs",40,{"$nulls":5},40,{"$nulls":18},4,5,"6A"]
["2","06","03","01","","","XE_5097","2.06.03.01","XKZ60206",null,"Commission Near Hall - X-Ray MPS","2007-06-27","2007-07-25",null,"X","SL_ME1","Hrs",40,null,4594.0094712072,null,4594.0094712072,null,40,null,4594.0094712072,null,4594.0094712072,{"$nulls":4},4594.0094712072,1,{"$nulls":8},4,5,"6A"]
["2","06","03","01","","","XE_5097","2.06.03.01","XKZ60206",null,"Commission Near Hall - X-Ray MPS","2007-06-27","2007-07-25",null,"X","SL_CT1","Hrs",40,null,2846.550933784799,null,2846.550933784799,null,40,null,2846.550933784799,null,2846.550933784799,{"$nulls":4},2846.550933784799,1,{"$nulls":8},4,5,"6A"]
["2","06","03","01","","","XE_5097","2.06.03.01","XKZ60206",null,"Commission Near Hall - X-Ray MPS","2007-06-27","2007-07-25",null,"X","SL_CE1","Hrs",40,null,5199.4493022383995,null,5199.4493022383995,null,40,null,5199.4493022383995,null,5199.4493022383995,{"$nulls":4},5199.4493022383995,1,{"$nulls":8},4,5,"6A"]
["2","06","03","01","","","XE_5101","2.06.03.01","XKZ60206",null,"Commission Tunnel - X-Ray MPS","2007-11-28","2008-01-10",null,"X","SL_ME1","Hrs",40,null,4713.453717458586,null,4713.453717458586,null,40,null,4713.453717458586,null,4713.453717458586,{"$nulls":6},4713.453717458586,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_5101","2.06.03.01","XKZ60206",null,"Commission Tunnel - X-Ray MPS","2007-11-28","2008-01-10",null,"X","SL_CT1","Hrs",40,null,2920.5612580632037,null,2920.5612580632037,null,40,null,2920.5612580632037,null,2920.5612580632037,{"$nulls":6},2920.5612580632037,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_5101","2.06.03.01","XKZ60206",null,"Commission Tunnel - X-Ray MPS","2007-11-28","2008-01-10",null,"X","SL_CE1","Hrs",40,null,5334.634984096598,null,5334.634984096598,null,40,null,5334.634984096598,null,5334.634984096598,{"$nulls":6},5334.634984096598,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_5125","2.06.03.01","XKZ60206",null,"Commission Far Hall - X-Ray MPS","2008-01-08","2008-02-05",null,"X","SL_ME1","Hrs",40,null,4713.453717458586,null,4713.453717458586,null,40,null,4713.453717458586,null,4713.453717458586,{"$nulls":6},4713.453717458586,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_5125","2.06.03.01","XKZ60206",null,"Commission Far Hall - X-Ray MPS","2008-01-08","2008-02-05",null,"X","SL_CT1","Hrs",40,null,2920.5612580632037,null,2920.5612580632037,null,40,null,2920.5612580632037,null,2920.5612580632037,{"$nulls":6},2920.5612580632037,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_5125","2.06.03.01","XKZ60206",null,"Commission Far Hall - X-Ray MPS","2008-01-08","2008-02-05",null,"X","SL_CE1","Hrs",40,null,5334.634984096598,null,5334.634984096598,null,40,null,5334.634984096598,null,5334.634984096598,{"$nulls":6},5334.634984096598,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_5132","2.06.03.01","XKZ60206",null,"Commission FEE - X-Ray MPS","2008-05-06","2008-06-03",null,"X","SL_ME1","Hrs",40,null,4713.453717458586,null,4713.453717458586,null,40,null,4713.453717458586,null,4713.453717458586,{"$nulls":6},4713.453717458586,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_5132","2.06.03.01","XKZ60206",null,"Commission FEE - X-Ray MPS","2008-05-06","2008-06-03",null,"X","SL_CT1","Hrs",40,null,2920.5612580632037,null,2920.5612580632037,null,40,null,2920.5612580632037,null,2920.5612580632037,{"$nulls":6},2920.5612580632037,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_5132","2.06.03.01","XKZ60206",null,"Commission FEE - X-Ray MPS","2008-05-06","2008-06-03",null,"X","SL_CE1","Hrs",40,null,5334.634984096598,null,5334.634984096598,null,40,null,5334.634984096598,null,5334.634984096598,{"$nulls":6},5334.634984096598,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_2734","2.06.03.01","XKZ60207",null,"Commission Near Hall - Laser PPS","2007-10-23","2007-11-19",null,"X","SL_PHS1","Hrs",40,null,3451.822636768386,null,3451.822636768386,null,40,null,3451.822636768386,null,3451.822636768386,{"$nulls":6},3451.822636768386,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_2734","2.06.03.01","XKZ60207",null,"Commission Near Hall - Laser PPS","2007-10-23","2007-11-19",null,"X","SL_CT1","Hrs",40,null,2920.5612580632037,null,2920.5612580632037,null,40,null,2920.5612580632037,null,2920.5612580632037,{"$nulls":6},2920.5612580632037,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_2734","2.06.03.01","XKZ60207",null,"Commission Near Hall - Laser PPS","2007-10-23","2007-11-19",null,"X","SL_CE1","Hrs",40,null,5334.634984096598,null,5334.634984096598,null,40,null,5334.634984096598,null,5334.634984096598,{"$nulls":6},5334.634984096598,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_5421","2.06.03.01","XKZ60207",null,"Commission Far Hall - Laser PPS","2008-01-08","2008-02-05",null,"X","SL_PHS1","Hrs",40,null,3451.822636768386,null,3451.822636768386,null,40,null,3451.822636768386,null,3451.822636768386,{"$nulls":6},3451.822636768386,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_5421","2.06.03.01","XKZ60207",null,"Commission Far Hall - Laser PPS","2008-01-08","2008-02-05",null,"X","SL_CT1","Hrs",40,null,2920.5612580632037,null,2920.5612580632037,null,40,null,2920.5612580632037,null,2920.5612580632037,{"$nulls":6},2920.5612580632037,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_5421","2.06.03.01","XKZ60207",null,"Commission Far Hall - Laser PPS","2008-01-08","2008-02-05",null,"X","SL_CE1","Hrs",40,null,5334.634984096598,null,5334.634984096598,null,40,null,5334.634984096598,null,5334.634984096598,{"$nulls":6},5334.634984096598,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_884","2.06.03.01","XKZ60208",null,"Commission Far Hall - User Safeguards","2008-01-08","2008-02-05",null,"X","SL_PHS1","Hrs",40,null,3451.822636768386,null,3451.822636768386,null,40,null,3451.822636768386,null,3451.822636768386,{"$nulls":6},3451.822636768386,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_884","2.06.03.01","XKZ60208",null,"Commission Far Hall - User Safeguards","2008-01-08","2008-02-05",null,"X","SL_CT1","Hrs",40,null,2920.5612580632037,null,2920.5612580632037,null,40,null,2920.5612580632037,null,2920.5612580632037,{"$nulls":6},2920.5612580632037,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_884","2.06.03.01","XKZ60208",null,"Commission Far Hall - User Safeguards","2008-01-08","2008-02-05",null,"X","SL_CE1","Hrs",40,null,5334.634984096598,null,5334.634984096598,null,40,null,5334.634984096598,null,5334.634984096598,{"$nulls":6},5334.634984096598,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_934","2.06.03.01","XKZ60208",null,"Commission Near Hall - User Safeguards","2007-10-23","2007-11-19",null,"X","SL_PHS1","Hrs",40,null,3451.822636768386,null,3451.822636768386,null,40,null,3451.822636768386,null,3451.822636768386,{"$nulls":6},3451.822636768386,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_934","2.06.03.01","XKZ60208",null,"Commission Near Hall - User Safeguards","2007-10-23","2007-11-19",null,"X","SL_CT1","Hrs",40,null,2920.5612580632037,null,2920.5612580632037,null,40,null,2920.5612580632037,null,2920.5612580632037,{"$nulls":6},2920.5612580632037,1,{"$nulls":6},4,5,"6A"]
["2","06","03","01","","","XE_934","2.06.03.01","XKZ60208",null,"Commission Near Hall - User Safeguards","2007-10-23","2007-11-19",null,"X","SL_CE1","Hrs",40,null,5334.634984096598,null,5334.634984096598,null,40,null,5334.634984096598,null,5334.634984096598,{"$nulls":6},5334.634984096598,1,{"$nulls":6},4,5,"6A"]
["2","06","03","02","  ","  ",{"$nulls":4},"Commissioning - XES Laser                                   ",{"$nulls":6},1976,0,206087.00665527652,0,206087.00665527652,null,1976,0,206087.00665527652,0,206087.00665527652,0,null,0,null,0,null,114054.29352512542,null,92032.71313015108,null,null,0]
["2","06","03","02","","","XE_700","2.06.03.02","XKC60302",null,"Test Near Hall - Oscillator Laser/Pum","2008-10-16","2008-10-22",null,"X","SL_TMUE1","Hrs",8,null,929.9296128175679,null,929.9296128175679,null,8,null,929.9296128175679,null,929.9296128175679,{"$nulls":8},929.9296128175679,1,{"$nulls":4},4,5,"6A"]
["2","06","03","02","","","XE_700","2.06.03.02","XKC60302",null,"Test Near Hall - Oscillator Laser/Pum","2008-10-16","2008-10-22",null,"X","SL_PHS1","Hrs",40,null,3541.570038440737,null,3541.570038440737,null,40,null,3541.570038440737,null,3541.570038440737,{"$nulls":8},3541.570038440737,1,{"$nulls":4},4,5,"6A"]
["2","06","03","02","","","XE_700","2.06.03.02","XKC60302",null,"Test Near Hall - Oscillator Laser/Pum","2008-10-16","2008-10-22",null,"X","SL_MFAT1","Hrs",8,null,834.6592242239998,null,834.6592242239998,null,8,null,834.6592242239998,null,834.6592242239998,{"$nulls":8},834.6592242239998,1,{"$nulls":4},4,5,"6A"]
["2","06","03","02","","","XE_712","2.06.03.02","XKC60302",null,"Final Check Near Hall - Oscillator Laser/Pump","2008-10-09","2008-10-15",null,"X","SL_PHS1","Hrs",40,null,3541.570038440737,null,3541.570038440737,null,40,null,3541.570038440737,null,3541.570038440737,{"$nulls":8},3541.570038440737,1,{"$nulls":4},4,5,"6A"]
["2","06","03","02","","","XE_712","2.06.03.02","XKC60302",null,"Final Check Near Hall - Oscillator Laser/Pump","2008-10-09","2008-10-15",null,"X","SL_EE1","Hrs",40,null,4514.042619437357,null,4514.042619437357,null,40,null,4514.042619437357,null,4514.042619437357,{"$nulls":8},4514.042619437357,1,{"$nulls":4},4,5,"6A"]
["2","06","03","02","","","XE_2818","2.06.03.02","XKZ60302",null,"Commission Valves - Vacuum","2008-05-29","2008-06-25",null,"X","SL_MVE1","Hrs",20,null,2505.8287137199527,null,2505.8287137199527,null,20,null,2505.8287137199527,null,2505.8287137199527,{"$nulls":6},2505.8287137199527,1,{"$nulls":6},4,5,"6A"]
["2","06","03","02","","","XE_2818","2.06.03.02","XKZ60302",null,"Commission Valves - Vacuum","2008-05-29","2008-06-25",null,"X","SL_MFAT1","Hrs",20,null,2033.770032,null,2033.770032,null,20,null,2033.770032,null,2033.770032,{"$nulls":6},2033.770032,1,{"$nulls":6},4,5,"6A"]
["2","06","03","02","","","XE_2978","2.06.03.02","XKZ60302",null,"Commission Ion Pump - Vacuum","2008-05-28","2008-06-24",null,"X","SL_MVE1","Hrs",20,null,2505.8287137199527,null,2505.8287137199527,null,20,null,2505.8287137199527,null,2505.8287137199527,{"$nulls":6},2505.8287137199527,1,{"$nulls":6},4,5,"6A"]
["2","06","03","02","","","XE_2978","2.06.03.02","XKZ60302",null,"Commission Ion Pump - Vacuum","2008-05-28","2008-06-24",null,"X","SL_MFAT1","Hrs",20,null,2033.770032,null,2033.770032,null,20,null,2033.770032,null,2033.770032,{"$nulls":6},2033.770032,1,{"$nulls":6},4,5,"6A"]
["2","06","03","02","","","XE_2986","2.06.03.02","XKZ60302",null,"Commission Turbo Pump - Vacuum","2008-05-20","2008-06-17",null,"X","SL_MVE1","Hrs",20,null,2505.8287137199527,null,2505.8287137199527,null,20,null,2505.8287137199527,null,2505.8287137199527,{"$nulls":6},2505.8287137199527,1,{"$nulls":6},4,5,"6A"]
["2","06","03","02","","","XE_2986","2.06.03.02","XKZ60302",null,"Commission Turbo Pump - Vacuum","2008-05-20","2008-06-17",null,"X","SL_MFAT1","Hrs",20,null,2033.770032,null,2033.770032,null,20,null,2033.770032,null,2033.770032,{"$nulls":6},2033.770032,1,{"$nulls":6},4,5,"6A"]
["2","06","03","02","","","XE_828","2.06.03.02","XKZ60302",null,"Commission Gauges - Vacuum","2008-07-24","2008-08-20",null,"X","SL_MVE1","Hrs",20,null,2505.8287137199527,null,2505.8287137199527,null,20,null,2505.8287137199527,null,2505.8287137199527,{"$nulls":6},2505.8287137199527,1,{"$nulls":6},4,5,"6A"]
["2","06","03","02","","","XE_828","2.06.03.02","XKZ60302",null,"Commission Gauges - Vacuum","2008-07-24","2008-08-20",null,"X","SL_MFAT1","Hrs",20,null,2033.770032,null,2033.770032,null,20,null,2033.770032,null,2033.770032,{"$nulls":6},2033.770032,1,{"$nulls":6},4,5,"6A"]
["2","06","03","02","","","XE_7144","2.06.03.02","XKZ60401",null,"Commission Near Hall - Oscillator Laser/Pump","2008-10-23","2008-11-19",null,"X","SL_PHS1","Hrs",480,null,42498.84046128884,null,42498.84046128884,null,480,null,42498.84046128884,null,42498.84046128884,{"$nulls":8},42498.84046128884,1,{"$nulls":4},4,5,"6A"]
["2","06","03","02","","","XE_7144","2.06.03.02","XKZ60401",null,"Commission Near Hall - Oscillator Laser/Pump","2008-10-23","2008-11-19",null,"X","SL_CE1","Hrs",120,null,16420.006541861603,null,16420.006541861603,null,120,null,16420.006541861603,null,16420.006541861603,{"$nulls":8},16420.006541861603,1,{"$nulls":4},4,5,"6A"]
["2","06","03","02","","","XE_56","2.06.03.02","XKZ60402",null,"Commission -  Laser Diagnostics","2008-04-14","2008-07-08",null,"X","SL_PHS1","Hrs",60,null,5177.733955152579,null,5177.733955152579,null,60,null,5177.733955152579,null,5177.733955152579,{"$nulls":6},5177.733955152579,1,{"$nulls":6},4,5,"6A"]
["2","06","03","02","","","XE_57","2.06.03.02","XKZ60403",null,"Commission - Optic Transport","2008-07-25","2008-08-21",null,"X","SL_PHS1","Hrs",20,null,1725.911318384193,null,1725.911318384193,null,20,null,1725.911318384193,null,1725.911318384193,{"$nulls":6},1725.911318384193,1,{"$nulls":6},4,5,"6A"]
["2","06","03","02","","","XE_57","2.06.03.02","XKZ60403",null,"Commission - Optic Transport","2008-07-25","2008-08-21",null,"X","SL_MFAT1","Hrs",20,null,2033.770032,null,2033.770032,null,20,null,2033.770032,null,2033.770032,{"$nulls":6},2033.770032,1,{"$nulls":6},4,5,"6A"]
["2","06","03","02","","","XE_57","2.06.03.02","XKZ60403",null,"Commission - Optic Transport","2008-07-25","2008-08-21",null,"X","SL_ME1","Hrs",20,null,2356.726858729293,null,2356.726858729293,null,20,null,2356.726858729293,null,2356.726858729293,{"$nulls":6},2356.726858729293,1,{"$nulls":6},4,5,"6A"]
["2","06","03","02","","","XE_58","2.06.03.02","XKZ60404",null,"Commission Far Hall - Laser Timing","2008-05-08","2008-10-27",null,"X","SL_PHS1","Hrs",240,null,20792.33462677826,null,20792.33462677826,null,240,null,20792.33462677826,null,20792.33462677826,{"$nulls":6},17649.30729947457,0.85,3143.0273273036905,0.15,{"$nulls":4},4,5,"6A"]
["2","06","03","02","","","XE_58","2.06.03.02","XKZ60404",null,"Commission Far Hall - Laser Timing","2008-05-08","2008-10-27",null,"X","SL_CT1","Hrs",120,null,8796.119234055717,null,8796.119234055717,null,120,null,8796.119234055717,null,8796.119234055717,{"$nulls":6},7466.473303326365,0.85,1329.6459307293526,0.15,{"$nulls":4},4,5,"6A"]
["2","06","03","02","","","XE_58","2.06.03.02","XKZ60404",null,"Commission Far Hall - Laser Timing","2008-05-08","2008-10-27",null,"X","SL_CE1","Hrs",480,null,64267.21611913283,null,64267.21611913283,null,480,null,64267.21611913283,null,64267.21611913283,{"$nulls":6},54552.404380194144,0.85,9714.811738938683,0.15,{"$nulls":4},4,5,"6A"]
["2","06","03","02","","","XE_59","2.06.03.02","XKZ60405",null,"Commission Near Hall - Laser Amplifiers","2008-07-07","2009-01-06",null,"X","SL_PHS1","Hrs",120,null,10498.180991652995,null,10498.180991652995,null,120,null,10498.180991652995,null,10498.180991652995,{"$nulls":6},4933.571394984468,0.47,5564.609596668528,0.53,{"$nulls":4},4,5,"6A"]
["2","06","03","03","  ","  ",{"$nulls":4},"Commissioning - AMO Experiment                              ",{"$nulls":6},240,0,27943.911401638205,0,27943.911401638205,null,240,0,27943.911401638205,0,27943.911401638205,0,null,0,null,0,null,13792.651208898491,null,14151.260192739715,null,null,0]
["2","06","03","03","","","XE_2979","2.06.03.03","XKZ60303",null,"Commission Far Hall Experiment Chamber - Vacuum","2008-08-29","2008-09-26",null,"X","SL_MVE1","Hrs",40,null,5011.657427439905,null,5011.657427439905,null,40,null,5011.657427439905,null,5011.657427439905,{"$nulls":6},5011.657427439905,1,{"$nulls":6},4,5,"6A"]
["2","06","03","03","","","XE_2979","2.06.03.03","XKZ60303",null,"Commission Far Hall Experiment Chamber - Vacuum","2008-08-29","2008-09-26",null,"X","SL_MFAT1","Hrs",40,null,4067.540064,null,4067.540064,null,40,null,4067.540064,null,4067.540064,{"$nulls":6},4067.540064,1,{"$nulls":6},4,5,"6A"]
["2","06","03","03","","","XE_2979","2.06.03.03","XKZ60303",null,"Commission Far Hall Experiment Chamber - Vacuum","2008-08-29","2008-09-26",null,"X","SL_ME1","Hrs",40,null,4713.453717458586,null,4713.453717458586,null,40,null,4713.453717458586,null,4713.453717458586,{"$nulls":6},4713.453717458586,1,{"$nulls":6},4,5,"6A"]
["2","06","03","03","","","XE_5313","2.06.03.03","XKZ60303",null,"Commission Near Hall Experiment Chamber - Vacuum","2008-11-11","2008-12-10",null,"X","SL_MVE1","Hrs",40,null,5141.960539596838,null,5141.960539596838,null,40,null,5141.960539596838,null,5141.960539596838,{"$nulls":8},5141.960539596838,1,{"$nulls":4},4,5,"6A"]
["2","06","03","03","","","XE_5313","2.06.03.03","XKZ60303",null,"Commission Near Hall Experiment Chamber - Vacuum","2008-11-11","2008-12-10",null,"X","SL_MFAT1","Hrs",40,null,4173.296121119999,null,4173.296121119999,null,40,null,4173.296121119999,null,4173.296121119999,{"$nulls":8},4173.296121119999,1,{"$nulls":4},4,5,"6A"]
["2","06","03","03","","","XE_5313","2.06.03.03","XKZ60303",null,"Commission Near Hall Experiment Chamber - Vacuum","2008-11-11","2008-12-10",null,"X","SL_ME1","Hrs",40,null,4836.003532022878,null,4836.003532022878,null,40,null,4836.003532022878,null,4836.003532022878,{"$nulls":8},4836.003532022878,1,{"$nulls":4},4,5,"6A"]
["2","06","03","05","  ","  ",{"$nulls":4},"Commissioning - 2D X-Ray Detector                           ",{"$nulls":6},480,0,44208.43407899442,0,44208.43407899442,null,480,0,44208.43407899442,0,44208.43407899442,0,null,0,null,0,null,0,null,44208.43407899442,null,null,0]
["2","06","03","05","","","XE_62","2.06.03.05","XKB60305",null,"Commission - 2-D X-Ray Detector","2008-10-27","2008-11-04",null,"X","SL_PHS1","Hrs",160,null,14166.280153762948,null,14166.280153762948,null,160,null,14166.280153762948,null,14166.280153762948,{"$nulls":8},14166.280153762948,1,{"$nulls":4},4,5,"6A"]
["2","06","03","05","","","XE_62","2.06.03.05","XKB60305",null,"Commission - 2-D X-Ray Detector","2008-10-27","2008-11-04",null,"X","SL_EE1","Hrs",160,null,18056.170477749427,null,18056.170477749427,null,160,null,18056.170477749427,null,18056.170477749427,{"$nulls":8},18056.170477749427,1,{"$nulls":4},4,5,"6A"]
["2","06","03","05","","","XE_62","2.06.03.05","XKB60305",null,"Commission - 2-D X-Ray Detector","2008-10-27","2008-11-04",null,"X","SL_CT1","Hrs",160,null,11985.983447482047,null,11985.983447482047,null,160,null,11985.983447482047,null,11985.983447482047,{"$nulls":8},11985.983447482047,1,{"$nulls":4},4,5,"6A"]
["2","06","04","  ","  ","  ",{"$nulls":4},"Spares                                                      ",{"$nulls":6},640,120000,72217.61620090634,129916.22399999999,202133.84020090633,null,640,120000,72217.61620090634,129916.22399999999,202133.84020090633,0,null,0,null,129916.22399999999,null,72217.61620090634,null,0,null,null,0]
["2","06","04","01","  ","  ",{"$nulls":4},"Spares - PPS Stoppers                                       ",{"$nulls":6},640,120000,72217.61620090634,129916.22399999999,202133.84020090633,null,640,120000,72217.61620090634,129916.22399999999,202133.84020090633,0,null,0,null,129916.22399999999,null,72217.61620090634,null,0,null,null,0]
["2","06","04","01","","","XE2410050","2.06.04.01","SKA60401",null,"AWARD: - Spare PPS Beam Stop Hardware","2007-02-26","2007-02-26","S","S","SL_AW1","$$",null,120000,null,129916.22399999999,129916.22399999999,null,null,120000,null,129916.22399999999,129916.22399999999,{"$nulls":4},129916.22399999999,1,{"$nulls":8},4,3,"6A"]
["2","06","04","01","","","XE2410060","2.06.04.01","SKA60401",null,"Vendor Fab/Ship - Spare PPS Stoppers","2007-02-27","2007-03-26","S","S","SA_MSEQ1","$$",null,120000,null,129916.22399999999,129916.22399999999,null,null,120000,null,129916.22399999999,129916.22399999999,{"$nulls":4},129916.22399999999,1,{"$nulls":8},4,3,"6A"]
["2","06","04","01","","","XE2410080","2.06.04.01","SKA60401",null,"Assemble - Spare PPS Beam Stop Hardware (2)","2007-12-11","2008-04-18","S","S","SL_MFMS1","Hrs",160,null,20823.480819071996,null,20823.480819071996,null,160,null,20823.480819071996,null,20823.480819071996,{"$nulls":6},20823.480819071996,1,{"$nulls":6},4,4,"6A"]
["2","06","04","01","","","XE2410080","2.06.04.01","SKA60401",null,"Assemble - Spare PPS Beam Stop Hardware (2)","2007-12-11","2008-04-18","S","S","SL_MFAT1","Hrs",320,null,32540.320512,null,32540.320512,null,320,null,32540.320512,null,32540.320512,{"$nulls":6},32540.320512,1,{"$nulls":6},4,4,"6A"]
["2","06","04","01","","","XE2410080","2.06.04.01","SKA60401",null,"Assemble - Spare PPS Beam Stop Hardware (2)","2007-12-11","2008-04-18","S","S","SL_ME1","Hrs",160,null,18853.814869834343,null,18853.814869834343,null,160,null,18853.814869834343,null,18853.814869834343,{"$nulls":6},18853.814869834343,1,{"$nulls":6},4,4,"6A"]
["2","06","04","02","  ","  ",{"$nulls":4},"Spares -                                                    "]
["2","06","04","03","  ","  ",{"$nulls":4},"Spares -                                                    "]
["2","06","04","04","  ","  ",{"$nulls":4},"Spares -                                                    "]
["2","06","04","05","  ","  ",{"$nulls":4},"Spares -                                                    "]
["2","06","05","  ","  ","  ",{"$nulls":4},"X-Ray Detectors                                             ",{"$nulls":6},0,2805450,0,3087475.6846150984,2998718.78047636,null,0,2107200,0,2334130.628455098,2334130.628455098,0,null,0,null,553282.3608827594,null,1470289.8014079782,null,310558.46616435994,null,null,0]
["2","06","05","01","  ","  ",{"$nulls":4},"Beam Imaging                                                "]
["2","06","05","02","  ","  ",{"$nulls":4},"2-D X-Ray Detector                                          ",{"$nulls":6},0,2805450,0,3087475.6846150984,2998718.78047636,null,0,2107200,0,2334130.628455098,2334130.628455098,0,null,0,null,553282.3608827594,null,1470289.8014079782,null,310558.46616435994,null,null,0]
["2","06","05","02","","","XE2520051","2.06.05.02","RAE60502","9683309","Cornell Labor/Materials Jul-Sep2006","2006-07-03","2006-09-29","S","R","SL_MSSC1","$$",null,90000,null,94968,94968,null,null,0,null,0,0,{"$nulls":14},5,2,"6A"]
["2","06","05","02","","","XE2520060","2.06.05.02","RAE60502","9683309","Cornell Labor/Materials Q4 CY06","2006-10-02","2006-12-29","S","R","SL_MSSC1","$$",null,217500,null,235473.156,235473.156,null,null,0,null,0,0,{"$nulls":14},5,2,"6A"]
["2","06","05","02","","","XE2520070","2.06.05.02","RAE60502","9683309","Cornell Labor/Materials Q1-Q3 CY07","2007-01-02","2007-09-28","S","R","SA_MSSC1","$$",null,480000,null,519664.89599999995,519664.89599999995,null,null,268800,null,291012.34176,291012.34176,{"$nulls":4},291012.34176,1,{"$nulls":8},5,2,"6A"]
["2","06","05","02","","","XE2520080","2.06.05.02","RAE60502","9683309","Cornell Labor/Materials Q4 CY07","2007-10-01","2007-12-27","S","R","SA_MSSC1","$$",null,160000,null,177725.39443199997,177725.39443199997,null,null,160000,null,177725.39443199997,177725.39443199997,{"$nulls":6},177725.39443199997,1,{"$nulls":6},5,2,"6A"]
["2","06","05","02","","","XE2520090","2.06.05.02","RAE60502","9683309","Cornell Labor/Materials Q1-Q3 CY08","2008-01-02","2008-09-30","S","R","SA_MSSC1","$$",null,817500,null,908065.6871759997,908065.6871759997,null,null,817500,null,908065.6871759997,908065.6871759997,{"$nulls":6},908065.6871759997,1,{"$nulls":6},5,2,"6A"]
["2","06","05","02","","","XE2520100","2.06.05.02","RAE60502","9683309","Cornell Labor/Materials Q4 CY08","2008-10-01","2008-12-31","S","R","SA_MSSC1","$$",null,272500,null,310558.46616435994,310558.46616435994,null,null,272500,null,310558.46616435994,310558.46616435994,{"$nulls":8},310558.46616435994,1,{"$nulls":4},5,2,"6A"]
["2","06","05","02","","","XE2520020","2.06.05.02","RBE60502","9683309","AWARD: Cornell Contract - CY07","2007-03-30","2007-03-30","S","R","SL_AW1","$$",null,1041370,null,1127423.8182239998,1127423.8182239998,null,null,1041370,null,1127423.8182239998,1127423.8182239998,{"$nulls":4},1127423.8182239998,1,{"$nulls":8},5,2,"6A"]
["2","06","05","02","","","XE2520030","2.06.05.02","RBE60502","9683309","AWARD: Cornell Contract - CY08","2007-11-30","2007-11-30","S","R","SL_AW1","$$",null,1097432,null,1219009.5941393662,1219009.5941393662,null,null,1097432,null,1219009.5941393662,1219009.5941393662,{"$nulls":6},1219009.5941393662,1,{"$nulls":6},5,2,"6A"]
["2","06","05","02","01","  ",{"$nulls":4},"Proto 2 ASIC                                                ",{"$nulls":6},0,4950,0,5223.24,5223.24,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["2","06","05","02","01","","XE2521071","2.06.05.02","RBE60502","9683309","Fabrication of Proto 2 ASIC","2006-07-03","2006-07-31","S","R","SL_MSSC1","$$",null,4950,null,5223.24,5223.24,null,null,0,null,0,0,{"$nulls":14},2,3,"6A"]
["2","06","05","02","02","  ",{"$nulls":4},"Proto 3 ASIC                                                ",{"$nulls":6},0,21000,0,22735.3392,22735.3392,null,0,0,0,0,0,0,null,0,null,0,null,0,null,0,null,null,0]
["2","06","05","02","02","","XE2522050","2.06.05.02","RBE60502","9683309","Fabrication of Proto 3 ASIC","2006-10-05","2006-12-05","S","R","SL_MSSC1","$$",null,21000,null,22735.3392,22735.3392,null,null,0,null,0,0,{"$nulls":14},2,3,"6A"]
["2","06","05","02","03","  ",{"$nulls":4},"Full Lot Prototype                                          ",{"$nulls":6},0,350000,0,378922.32,378922.32,null,0,196400,0,212629.55328,212629.55328,0,null,0,null,212629.55328,null,0,null,0,null,null,0]
["2","06","05","02","03","","XE2523100","2.06.05.02","RBE60502","9683309","Fabricate Detector Diode","2006-10-02","2007-02-26","S","R","SL_MSSC1","$$",null,80000,null,86610.81599999999,86610.81599999999,null,null,46400,null,50234.273279999994,50234.273279999994,{"$nulls":4},50234.273279999994,1,{"$nulls":8},2,2,"6A"]
["2","06","05","02","03","","XE2523170","2.06.05.02","RBE60502","9683309","Fabricate Full Lot ASIC","2007-02-27","2007-04-25","S","R","SL_MSSC1","$$",null,200000,null,216527.04,216527.04,null,null,80000,null,86610.81599999999,86610.81599999999,{"$nulls":4},86610.81599999999,1,{"$nulls":8},2,3,"6A"]
["2","06","05","02","03","","XE2523190","2.06.05.02","RBE60502","9683309","Bump Bond & Assemble Prototype Detector","2007-05-10","2007-06-07","S","R","SA_MSSC1","$$",null,70000,null,75784.46399999999,75784.46399999999,null,null,70000,null,75784.46399999999,75784.46399999999,{"$nulls":4},75784.46399999999,1,{"$nulls":8},2,2,"6A"]
["2","06","05","02","04","  ",{"$nulls":4},"500px Detector                                              ",{"$nulls":6},0,392000,0,434139.1856427381,345382.28150399996,null,0,392000,0,434139.1856427381,434139.1856427381,0,null,0,null,49640.46584275951,null,384498.71979997866,null,0,null,null,0]
["2","06","05","02","04","","XE2524030","2.06.05.02","RKE60502","9683309","Fabricate Proto 4 ASIC","2007-04-06","2007-06-01","S","R","SA_MSSC1","$$",null,42000,null,45470.6784,45470.6784,null,null,42000,null,45470.6784,45470.6784,{"$nulls":4},45470.6784,1,{"$nulls":8},3,2,"6A"]
["2","06","05","02","04","","XE2524070","2.06.05.02","RKE60502","9683309","Fabricate final detector ASIC","2007-10-08","2007-12-04","S","R","SA_MSSC1","$$",null,200000,null,222156.74303999994,222156.74303999994,null,null,200000,null,222156.74303999994,222156.74303999994,{"$nulls":6},222156.74303999994,1,{"$nulls":6},3,3,"6A"]
["2","06","05","02","04","","XE2524120","2.06.05.02","RKE60502","9683309","Fabricate final Detector Diode","2007-09-24","2008-02-20","S","R","SA_MSSC1","$$",null,80000,null,88756.90413873825,null,null,null,80000,null,88756.90413873825,88756.90413873825,{"$nulls":4},4169.787442759515,0.05,84587.11669597872,0.95,{"$nulls":6},3,2,"6A"]
["2","06","05","02","04","","XE2524140","2.06.05.02","RKE60502","9683309","Bump Bond ASIC to final Detector","2008-02-21","2008-03-19","S","R","SA_MSSC1","$$",null,70000,null,77754.86006399998,77754.86006399998,null,null,70000,null,77754.86006399998,77754.86006399998,{"$nulls":6},77754.86006399998,1,{"$nulls":6},4,3,"6A"]
["2","06","05","02","05","  ",{"$nulls":4},"2D X-Ray Detector Commissioning                             "]
["2","06","05","03","  ","  ",{"$nulls":4},"Beam Intensity                                              "]
["2","06","05","04","  ","  ",{"$nulls":4},"Streak Camera                                               "]
["2","06","07","  ","  ","  ",{"$nulls":4},"Atomic Physics                                              "]
["2","06","07","01","  ","  ",{"$nulls":4},"Atomic Physics Samples                                      "]
["2","06","07","02","  ","  ",{"$nulls":4},"Atomic Physics Diagnostics                                  "]
["2","06","07","03","  ","  ",{"$nulls":4},"Atomic Physics Data Analysis                                "]
["2","06","07","04","  ","  ",{"$nulls":4},"Atomic Physics Detectors                                    "]
["2","08","  ","  ","  ","  ",{"$nulls":4},"LCLS SYSTEM COMMISSIONING (OPC)                             "]
["2","09","  ","  ","  ","  ",{"$nulls":4},"CONVENTIONAL FACILITIES (OPC)                               ",{"$nulls":6},1785,435000,223645.2126995058,435000,658645.2126995057,null,1785,435000,223645.2126995058,435000,658645.2126995057,0,null,0,null,360000,null,298645.2126995058,null,0,null,null,0]
["2","09","01","  ","  ","  ",{"$nulls":4},"MANAGEMENT INTEGRATION                                      "]
["2","09","03","  ","  ","  ",{"$nulls":4},"RSY - CLOC Commissioning                                    ",{"$nulls":6},1785,435000,223645.2126995058,435000,658645.2126995057,null,1785,435000,223645.2126995058,435000,658645.2126995057,0,null,0,null,360000,null,298645.2126995058,null,0,null,null,0]
["2","09","03","05","  ","  ",{"$nulls":4},"RSY-CLOC Commissioning                                      ",{"$nulls":6},1785,435000,223645.2126995058,435000,658645.2126995057,null,1785,435000,223645.2126995058,435000,658645.2126995057,0,null,0,null,360000,null,298645.2126995058,null,0,null,null,0]
["2","09","03","05","","","CF05033040","2.09.03.05","9681319","9682422","AWARD: Commissioning Beam Path - FY07","2007-06-04","2007-06-04",null,"X","SL_AWFX1","$$",null,325000,null,325000,325000,null,null,325000,null,325000,325000,{"$nulls":4},325000,1,{"$nulls":8},2,3,"9A"]
["2","09","03","05","","","CF05033041","2.09.03.05","9681319","9682422","AWARD: Commissioning Beam Path - FY08","2007-10-01","2007-10-01",null,"X","SL_AWFX1","$$",null,75000,null,75000,75000,null,null,75000,null,75000,75000,{"$nulls":6},75000,1,{"$nulls":6},2,3,"9A"]
["2","09","03","05","","","CF05033045","2.09.03.05","9681319","9682422","Commissioning - Beam Path (FY07)","2007-06-05","2007-09-28",null,"X","SA_MSSF1","$$",null,325000,null,325000,325000,null,null,325000,null,325000,325000,{"$nulls":4},325000,1,{"$nulls":8},2,3,"9A"]
["2","09","03","05","","","CF05033085","2.09.03.05","9681319","9682422","Commissioning - Beam Path (FY08)","2007-10-01","2008-06-30",null,"X","SA_MSSF1","$$",null,75000,null,75000,75000,null,null,75000,null,75000,75000,{"$nulls":6},75000,1,{"$nulls":6},2,3,"9A"]
["2","09","03","05","","","CFMGT_1001","2.09.03.05","9681319","9682422","AWARD: Dispute Resolution Board - FY07","2007-06-04","2007-06-04",null,"X","SL_AWFX1","$$",null,35000,null,35000,35000,null,null,35000,null,35000,35000,{"$nulls":4},35000,1,{"$nulls":8},6,3,"9A"]
["2","09","03","05","","","CFMGT_1119","2.09.03.05","9681319","9682422","Dispute Resolution Board (FY07)","2007-06-05","2007-09-28",null,"X","SA_MSSF1","$$",null,35000,null,35000,35000,null,null,35000,null,35000,35000,{"$nulls":4},35000,1,{"$nulls":8},6,3,"9A"]
["2","09","03","05","","","CFUTR_2000","2.09.03.05","9681319","9682422","CF OPC Support - FY08 (Mar-Jun08)","2008-03-03","2008-06-30",null,"X","SL_UTR1","Hrs",1785,null,223645.2126995058,null,223645.2126995058,null,1785,null,223645.2126995058,null,223645.2126995058,{"$nulls":6},223645.2126995058,1,{"$nulls":6},3,3,"9A"]

{"sheet":"WBS-CN-PP","index":6,"n_rows":1296,"n_cols":15,"rows_kept":1296,"cut":false,"hidden":true,"merged":[[0,10,0,14],[0,0,0,5],[1,0,1,5]],"flags":["formulas_cached_only"]}
["WBS",{"$nulls":5},"P3","June - 2004 DCE","OBS","Summary or","CHARGE NUMBERS"]
["Level",{"$nulls":5},"ID","Description",null,"Cntrl Acc","PED","CNSTR","R&D","SPARES","PRE-OPS"]
["1","2","3","4","5","6"]
[{"$nulls":7},"LINAC COHERENT LIGHT SOURCE (TPC)"]
["1",{"$nulls":6},"LCLS PROJECT - PED & CONSTRUCTION",null,"Summary"]
["1","01",{"$nulls":5},"LCLS PROJECT MGMT, PLANNING & ADMN (TEC)",null,"Summary"]
["1","01","01",{"$nulls":4},"Environment, Safety & Health",null,"Summary"]
["1","01","01","01","","",null,"Radiation Physics",null,"1.01.01.01",9240222,"CN10101"]
["1","01","01","02","","",null,"ESH Management & Coordination",null,"1.01.01.02",9240223,"CN10102"]
["1","01","01","03","","",null,"Seismic & Engineering Support",null,"1.01.01.03",9240224,"CN10103"]
["1","01","02",{"$nulls":4},"Project Management",null,"Summary"]
["1","01","02","01",null,null,null,"SLAC Project Management Office",null,"Summary"]
["1","01","02","01","01","",null,"SLAC Project Office - General",null,"1.01.02.01.01",9240227,"CN1020101"]
["1","01","02","01","02","",null,"SLAC Project Support",null,"1.01.02.01.02",9240228,"CN1020102"]
["1","01","02","01","03","",null,"SLAC Project Office M&S",null,"1.01.02.01.03",9240229,"CN1020103"]
["1","01","02","01","04",null,null,"Reserved",null,"Summary"]
["1","01","02","01","05",null,null,"Reserved",null,"Summary"]
["1","01","02","02",null,null,null,"Reserved",null,"Summary"]
["1","01","02","03",null,null,null,"Reserved",null,"Summary"]
["1","01","03",{"$nulls":4},"Technical Integration",null,"Summary"]
["1","01","03","01","","",null,"Global Controls",null,"1.01.03.01",9240235,"CN10301"]
["1","01","03","02","","",null,"Global Alignment Coordination",null,"1.01.03.02",9240236,"CN10302"]
["1","01","03","03","","",null,"Global Installation Coordination",null,"1.01.03.03",9240237,"CN10303"]
["1","01","04",{"$nulls":4},"Education Support",null,"Summary"]
["1","01","04","01","","",null,"Education/Outreach Travel",null,"1.01.04.01",9240239,"CN10401"]
["1","01","04","02","","",null,"Education/Outreach M&S",null,"1.01.04.02",9240240,"CN10402"]
["1","01","05",{"$nulls":4},"Reserved",null,"Summary"]
["1","02",{"$nulls":5},"INJECTOR SYSTEM",null,"Summary"]
["1","02","01",{"$nulls":4},"Injector System Management & Integration",null,"Summary"]
["1","02","01","01","","",null,"Injector System Integration Effort / M&S",null,"1.02.01.01",9240242,"CN20101"]
["1","02","01","02",null,null,null,"Reserved",null,"Summary"]
["1","02","01","03",null,null,null,"Reserved",null,"Summary"]
["1","02","02",{"$nulls":4},"Injector Controls Subsystem",null,"Summary"]
["1","02","02","01",null,null,null,"Reserved",null,"Summary"]
["1","02","02","02",null,null,null,"LLRF Controls",null,"Summary"]
["1","02","02","02","01","",null,"Readback & Controls - RF Gun LLRF & Temperature",null,"1.02.02.02.01","CN2020201","CN2020201"]
["1","02","02","02","02","",null,"Readback & Controls - L0 LLRF",null,"1.02.02.02.02",null,"CN2020202"]
["1","02","02","02","03","",null,"Readback & Controls - LLRF Transverse Cavity",null,"1.02.02.02.03",null,"CN2020203"]
["1","02","02","02","04","",null,"S-Band Cavity Controls",null,"1.02.02.02.04",null,"CN2020204"]
["1","02","02","02","05",null,null,"Reserved",null,"Summary"]
["1","02","02","03",null,null,null,"E-Beam Diagnostics Controls",null,"Summary"]
["1","02","02","03","01",null,null,"Reserved",null,"Summary"]
["1","02","02","03","02","",null,"Controls - Toroids",null,"1.02.02.03.02",null,"CN2020302"]
["1","02","02","03","03","",null,"Controls - Faraday Cups",null,"1.02.02.03.03","CN2020303","CN2020303"]
["1","02","02","03","04","",null,"Controls - Tune-Up Dump",null,"1.02.02.03.04",null,"CN2020304"]
["1","02","02","03","05","",null,"Controls - Profile Monitors",null,"1.02.02.03.05",null,"CN2020305"]
["1","02","02","03","06","",null,"Controls - E/O Diagnostics",null,"1.02.02.03.06",null,"CN2020306"]
["1","02","02","03","07","",null,"Controls - BPM",null,"1.02.02.03.07",null,"CN2020307"]
["1","02","02","03","08",null,null,"Reserved",null,"Summary"]
["1","02","02","04",null,null,null,"Laser Controls",null,"Summary"]
["1","02","02","04","01",null,null,"Reserved",null,"Summary"]
["1","02","02","04","02","",null,"Controls - Gun Laser",null,"1.02.02.04.02","CN2020402","CN2020402"]
["1","02","02","05","","",null,"Laser Heater Controls",null,"1.02.02.05",null,"CN20205"]
["1","02","02","06","","",null,"Timing Controls",null,"1.02.02.06",null,"CN20206"]
["1","02","02","07","","",null,"Vacuum Controls",null,"1.02.02.07","CN20207","CN20207"]
["1","02","02","08",null,null,null,"Software & Controls Infrastructure",null,"Summary"]
["1","02","02","08","01",null,null,"Reserved",null,"Summary"]
["1","02","02","08","02",null,null,"Reserved",null,"Summary"]
["1","02","02","08","03","",null,"Data Communications",null,"1.02.02.08.03",null,"CN2020803"]
["1","02","02","08","04","",null,"Computers & Crates",null,"1.02.02.08.04",null,"CN2020804"]
["1","02","02","09","","",null,"Power Supply Controls",null,"1.02.02.09","CN20209","CN20209"]
["1","02","02","10","","",null,"PPS,BCS,MPS Controls",null,"1.02.02.10","CN20210","CN20210"]
["1","02","03",{"$nulls":4},"Injector Lasers",null,"Summary"]
["1","02","03","01",null,null,null,"Drive Laser Prototyping",null,"Summary"]
["1","02","03","02","","",null,"Drive Laser System",null,"1.02.03.02",9240277,"CN20302"]
["1","02","03","03","","",null,"Drive Laser Diagnostics",null,"1.02.03.03","CN20303","CN20303"]
["1","02","03","04","","",null,"Timing Stability Monitoring",null,"1.02.03.04",null,"CN20304"]
["1","02","03","05","","",null,"Steering Stability Feedback & Msmts",null,"1.02.03.05",null,"CN20305"]
["1","02","03","06","","",null,"Pre Amp Low Power Comp",null,"1.02.03.06","CN20306","CN20306"]
["1","02","03","07","","",null,"Transport to Tunnel & Rela Optics",null,"1.02.03.07",9240282,"CN20307"]
["1","02","03","08","","",null,"UV Launch, Conditioning & Diagnostics",null,"1.02.03.08",9240283,"CN20308"]
["1","02","03","09","","",null,"Load Lock Transport System",null,"1.02.03.09","CN20309","CN20309"]
["1","02","03","10","","",null,"Visible Optical Transport & Optics",null,"1.02.03.10",null,"CN20310"]
["1","02","03","11","","",null,"LB Infrastructure & LB System Wide Items",null,"1.02.03.11",9240286,"CN20311"]
["1","02","03","12","","",null,"Alignment Laser",null,"1.02.03.12",null,"CN20312"]
["1","02","03","13","","",null,"Light Path to Streak Camera",null,"1.02.03.13",null,"CN20313"]
["1","02","03","14","","",null,"Started..Closed Out",null,"1.02.03.14",9240289]
["1","02","03","15",null,null,null,"Moved to 1.02.03.03",null,"Summary"]
["1","02","03","16",null,null,null,"Deleted",null,"Summary"]
["1","02","03","17",null,null,null,"Deleted",null,"Summary"]
["1","02","03","18",null,null,null,"Moved to 1.02.03.07",null,"Summary"]
["1","02","03","19",null,null,null,"Moved to 1.02.03.04",null,"Summary"]
["1","02","03","20",null,null,null,"Moved to 1.02.03.07",null,"Summary"]
["1","02","03","21","","",null,"Started..Closed Out",null,"1.02.03.21",9240296]
["1","02","03","22",null,null,null,"Moved to 1.02.03.03",null,"Summary"]
["1","02","03","23",null,null,null,"Moved to 1.02.03.04 and 1.02.03.05",null,"Summary"]
["1","02","03","24",null,null,null,"Moved to 1.02.03.07 and 1.02.03.08",null,"Summary"]
["1","02","03","25",null,null,null,"Moved to 1.02.03.10",null,"Summary"]
["1","02","03","26",null,null,null,"Moved to 1.02.03.07",null,"Summary"]
["1","02","03","27",null,null,null,"Moved to 1.02.03.08",null,"Summary"]
["1","02","03","28",null,null,null,"Moved to 1.02.03.11",null,"Summary"]
["1","02","03","29",null,null,null,"Moved to 1.02.03.12",null,"Summary"]
["1","02","03","30",null,null,null,"Moved to 1.02.03.13",null,"Summary"]
["1","02","04",{"$nulls":4},"RF Gun, Load Lock & Supports",null,"Summary"]
["1","02","04","01","","",null,"RF Gun (Copper Brazement Only)",null,"1.02.04.01",9240307,"CN20401"]
["1","02","04","02","","",null,"RF Gun Supports",null,"1.02.04.02",9240308,"CN20402"]
["1","02","04","03","","",null,"Gun Load Lock",null,"1.02.04.03",null,"CN20403"]
["1","02","04","04","","",null,"Gun Load Lock Supports",null,"1.02.04.04",null,"CN20404"]
["1","02","04","05","","",null,"Gun Solenoid",null,"1.02.04.05",9240311,"CN20405"]
["1","02","04","06","","",null,"Gun Solenoid Supports",null,"1.02.04.06",9240312,"CN20406"]
["1","02","04","07","","",null,"Gun RF Feed",null,"1.02.04.07",9240313,"CN20407"]
["1","02","04","08","","",null,"Gun RF Feed Supports",null,"1.02.04.08",null,"CN20408"]
["1","02","05",{"$nulls":4},"Gun to Linac Section (GTL)",null,"Summary"]
["1","02","05","01","","",null,"GTL BPMs (3ea)",null,"1.02.05.01",9240316,"CN20501"]
["1","02","05","02","","",null,"GTL Faraday Cup/YAG1",null,"1.02.05.02",9240317,"CN20502"]
["1","02","05","03","","",null,"GTL Current Monitors (CM1)",null,"1.02.05.03",null,"CN20503"]
["1","02","05","04",null,null,null,"Reserved",null,"Summary"]
["1","02","05","05",null,null,null,"Reserved",null,"Summary"]
["1","02","05","06","","",null,"GTL Steering Coils, (2) (SC1)",null,"1.02.05.06",9240321,"CN20506"]
["1","02","05","07","","",null,"GTL Vacuum Components",null,"1.02.05.07",null,"CN20507"]
["1","02","05","08","","",null,"GTL Supports",null,"1.02.05.08",9240323,"CN20508"]
["1","02","05","09",null,null,null,"Gun Spectrometer (GS) Assembly",null,"Summary"]
["1","02","05","09","01","",null,"GS Dipole",null,"1.02.05.09.01",9240325,"CN2050901"]
["1","02","05","09","02","",null,"GS Current Monitor (CM2)",null,"1.02.05.09.02",null,"CN2050902"]
["1","02","05","09","03","",null,"GS BPM (1)",null,"1.02.05.09.03",9240327,"CN2050903"]
["1","02","05","09","04","",null,"GS Faraday Cup/YAG2",null,"1.02.05.09.04",9240328,"CN2050905"]
["1","02","05","09","05",null,null,"Reserved",null,"Summary"]
["1","02","05","09","06","",null,"GS Quadrupoles",null,"1.02.05.09.06",null,"CN2050906"]
["1","02","05","09","07","",null,"GS Supports",null,"1.02.05.09.07",null,"CN2050907"]
["1","02","05","10","","",null,"GTL Pumping & Optic Chamber",null,"1.02.05.10",9240332,"CN20510"]
["1","02","05","11","","",null,"GTL YAG (1ea)",null,"1.02.05.11",9240333,"CN20511"]
["1","02","06",{"$nulls":4},"Injector Linac Structures",null,"Summary"]
["1","02","06","01","","",null,"L0-1 Structure Assembly",null,"1.02.06.01",9240335,"CN20601"]
["1","02","06","02","","",null,"L0-2 Structure Assembly",null,"1.02.06.02",9240336,"CN20602"]
["1","02","06","03","","",null,"Major Linac Support",null,"1.02.06.03",9240337,"CN20603"]
["1","02","06","04","","",null,"Linac Solenoid & Supports",null,"1.02.06.04",9240338,"CN20604"]
["1","02","07",{"$nulls":4},"L0-1 to L0-2 Section (L0-1TL0-2)",null,"Summary"]
["1","02","07","01","","",null,"L0-1TL0-2 Quadrupoles (2)",null,"1.02.07.01",null,"CN20701"]
["1","02","07","02","","",null,"L0-1TL0-2 BPMs (2)",null,"1.02.07.02",9240341,"CN20702"]
["1","02","07","03",null,null,null,"Reserved",null,"Summary"]
["1","02","07","04","","",null,"L0-1TL0-2 OTR/YAG (1)",null,"1.02.07.04",9240343,"CN20704"]
["1","02","07","05","","",null,"L0-1TL0-2 Linac Steering Coils (4)",null,"1.02.07.05",9240344,"CN20705"]
["1","02","07","06","","",null,"L0-1TL0-2 Vacuum Components",null,"1.02.07.06",9240345,"CN20706"]
["1","02","07","07","","",null,"L0-1TL0-2 Major tube support structure",null,"1.02.07.07",9240346,"CN20707"]
["1","02","08",{"$nulls":4},"Linac to DL1 (LTDL1)",null,"Summary"]
["1","02","08","01","","",null,"LTDL1 Current Monitors (CM3)",null,"1.02.08.01",null,"CN20801"]
["1","02","08","02","","",null,"LTDL1 BPMs (6ea)",null,"1.02.08.02",9240349,"CN20802"]
["1","02","08","03","","",null,"LTDL1 OTR(5)/YAG (1)",null,"1.02.08.03",9240350,"CN20803"]
["1","02","08","04","","",null,"LTDL1 Quadrupoles (6ea)",null,"1.02.08.04",null,"CN20804"]
["1","02","08","05",null,null,null,"Reserved",null,"Summary"]
["1","02","08","06","","",null,"LTDL1 RF Kicker",null,"1.02.08.06",9240353,"CN20806"]
["1","02","08","07","","",null,"LTDL1 Steering Coils (2ea)X-Y",null,"1.02.08.07",9240354,"CN20807"]
["1","02","08","08","","",null,"LTDL1 PPS Stopper",null,"1.02.08.08",9240355,"CN20808"]
["1","02","08","09","","",null,"LTDL1 E/O EO2",null,"1.02.08.09",9240356,"CN20809"]
["1","02","08","10","","",null,"LTDL1 Minor Tube Supports",null,"1.02.08.10",9240357,"CN20810"]
["1","02","09",{"$nulls":4},"Dog Leg 1 Bend (DL1)",null,"Summary"]
["1","02","09","01","","",null,"DL1 B01 & B02 Dipoles",null,"1.02.09.01",9240359,"CN20901"]
["1","02","09","02","","",null,"DL1 QB Quadrupole",null,"1.02.09.02",null,"CN20902"]
["1","02","09","03",null,null,null,"DL1 Wire Scanner",null,"Summary"]
["1","02","09","04","","",null,"DL1 OTR",null,"1.02.09.04",9240362,"CN20904"]
["1","02","09","05","","",null,"DL1 Supports",null,"1.02.09.05",null,"CN20905"]
["1","02","09","06","","",null,"DL1 Vacuum Chamber",null,"1.02.09.06",null,"CN20906"]
["1","02","10",{"$nulls":4},"DL1 to Linac (DL1TL)",null,"Summary"]
["1","02","10","01","","",null,"DL1TL BPMs (2)",null,"1.02.10.01",9240366,"CN21001"]
["1","02","10","02","","",null,"DL1TL Steering Coils (3eaX-Y Assys)",null,"1.02.10.02",9240367,"CN21002"]
["1","02","10","03","","",null,"DL1TL Quadrupoles (2)",null,"1.02.10.03",null,"CN21003"]
["1","02","10","04","","",null,"DL1TL Vacuum Components",null,"1.02.10.04",null,"CN21004"]
["1","02","10","05","","",null,"DL1TL Current Monitor (CM4 )",null,"1.02.10.05",null,"CN21005"]
["1","02","10","06","","",null,"DL1TL OTR",null,"1.02.10.06",9240371,"CN21006"]
["1","02","10","07",null,null,null,"Reserved",null,"Summary"]
["1","02","11",{"$nulls":4},"Straight Ahead Beamline (SAB)",null,"Summary"]
["1","02","11","01","","",null,"SAB Spectrometer Dipole",null,"1.02.11.01",9240374,"CN21101"]
["1","02","11","02","","",null,"SAB Quadrupoles (3)",null,"1.02.11.02",null,"CN21102"]
["1","02","11","03","","",null,"SAB Current Monitor (CM5)",null,"1.02.11.03",null,"CN21103"]
["1","02","11","04","","",null,"SAB BPM (4ea)",null,"1.02.11.04",9240377,"CN21104"]
["1","02","11","05","","",null,"SAB YAG",null,"1.02.11.05",9240378,"CN21105"]
["1","02","11","06","","",null,"SAB Vacuum Chamber and Components",null,"1.02.11.06",null,"CN21106"]
["1","02","11","07","","",null,"SAB Beam Dump and Shielding",null,"1.02.11.07",9240380,"CN21107"]
["1","02","11","08","","",null,"SAB Supports",null,"1.02.11.08",null,"CN21108"]
["1","02","11","09","","",null,"SAB Steering Coils (2)",null,"1.02.11.09",9240382,"CN21109"]
["1","02","12",{"$nulls":4},"Injector RF Waveguide Subsystem",null,"Summary"]
["1","02","12","01","","",null,"RF Waveguides",null,"1.02.12.01",9240384,"CN21201"]
["1","02","12","02",null,null,null,"Reseved",null,"Summary"]
["1","02","13",{"$nulls":4},"Injector RF Subsystem",null,"Summary"]
["1","02","13","01",null,null,null,"S-Band Low Level System",null,"Summary"]
["1","02","13","01","01","",null,"Controls Interface & Timing",null,"1.02.13.01.01",9240388,"CN2130101"]
["1","02","13","01","02","",null,"LLRF Phase Reference System",null,"1.02.13.01.02",9240389,"CN2130102"]
["1","02","13","01","03","",null,"LLRF Monitor & Control System",null,"1.02.13.01.03",9240390,"CN2130103"]
["1","02","13","01","04","",null,"Beam Phase Monitor Cavity",null,"1.02.13.01.04",9240391,"CN2130104"]
["1","02","13","01","05","",null,"RF System S/W Development / Docs",null,"1.02.13.01.05",9240392,"CN2130105"]
["1","02","13","02",null,null,null,"Reserved",null,"Summary"]
["1","02","13","02","01",null,null,"Reserved",null,"Summary"]
["1","02","13","02","02",null,null,"Reserved",null,"Summary"]
["1","02","13","02","03",null,null,"Reserved",null,"Summary"]
["1","02","14",{"$nulls":4},"Cathode Processing (CP) Station",null,"Summary"]
["1","02","14","01","","",null,"CP Cathode Assembly & Supports",null,"1.02.14.01",null,"CN21401"]
["1","02","14","02","","",null,"CP Load Lock",null,"1.02.14.02",null,"CN21402"]
["1","02","14","03","","",null,"CP Load Lock Supports",null,"1.02.14.03",null,"CN21403"]
["1","02","14","04","","",null,"CP Station",null,"1.02.14.04",null,"CN21404"]
["1","02","14","05","","",null,"Cathode Lab Infrastructure",null,"1.02.14.05",null,"CN21405"]
["1","02","15",{"$nulls":4},"Injector Laser Heater Subsystem",null,"Summary"]
["1","02","15","01","","",null,"System Design & Optimization",null,"1.02.15.01",null,"CN21501"]
["1","02","15","02","","",null,"Beam Conditioning Optics (Laser Bay)",null,"1.02.15.02",null,"CN21502"]
["1","02","15","03","","",null,"Transport Optics (Bay to Tunnel)",null,"1.02.15.03",null,"CN21503"]
["1","02","15","04","","",null,"Chicane",null,"1.02.15.04",null,"CN21504"]
["1","02","15","05","","",null,"Undulator",null,"1.02.15.05",null,"CN21505"]
["1","02","15","06","","",null,"Photon Beam Diagnostics",null,"1.02.15.06",null,"CN21506"]
["1","02","15","07",null,null,null,"Reserved",null,"Summary"]
["1","02","15","08",null,null,null,"Reserved",null,"Summary"]
["1","02","16",{"$nulls":4},"Injector Protection & Pwr Conv Subsystem",null,"Summary"]
["1","02","16","01","","",null,"Personnel Protection Subsystem (PPS)",null,"1.02.16.01",9240413,"CN21601"]
["1","02","16","02",null,null,null,"Reserved",null,"Summary"]
["1","02","16","03","","",null,"Machine Protection Subsystem (MPS)",null,"1.02.16.03",null,"CN21603"]
["1","02","16","04",null,null,null,"Injector Power Conversion",null,"Summary"]
["1","02","16","04","01","",null,"Beamline Pwr Supplies - (Dipole Type)",null,"1.02.16.04.01",9240417,"CN2160401"]
["1","02","16","04","01","01",null,"10kw Power Supply - (Solenoid 1)",null,"1.02.16.04.01",9240417,"CN2160401"]
["1","02","16","04","01","02",null,"30kw Power Supply - (Solenoid 2)",null,"1.02.16.04.01",9240417,"CN2160401"]
["1","02","16","04","01","03",null,"Reserved",null,"Summary"]
["1","02","16","04","01","04",null,"15kw Power Supply - (B1-2)",null,"1.02.16.04.01",null,"CN2160401"]
["1","02","16","04","01","05",null,"15kw Power Supply - (B3 Spect)",null,"1.02.16.04.01",null,"CN2160401"]
["1","02","16","04","01","06",null,"10kw Power Supply - (New)",null,"1.02.16.04.01",null,"CN2160401"]
["1","02","16","04","02",null,null,"Beamline Pwr Supplies - (Trim Type)",null,"Summary"]
["1","02","16","04","02","01",null,"12Amp Power Supply - (MCOR_1)",null,"1.02.16.04.02",9240418,"CN2160402"]
["1","02","16","04","02","02",null,"30Amp Power Supply - (MCOR_2)",null,"1.02.16.04.02",9240418,"CN2160402"]
["1","02","16","04","02","03",null,"30Amp Power Supply - (MCOR_3)",null,"1.02.16.04.02",9240418,"CN2160402"]
["1","02","16","04","02","04",null,"30Amp Power Supply - (MCOR_4)",null,"1.02.16.04.02",9240418,"CN2160402"]
["1","02","16","04","03","",null,"Controls & Power Supply - Misc Hdwr",null,"1.02.16.04.03",9240419,"CN2160403"]
["1","02","16","04","04",null,null,"Reserved",null,"Summary"]
["1","02","17",{"$nulls":4},"Injector Installation & Alignment",null,"Summary"]
["1","02","17","01","","",null,"Injector Infrastructure Installation",null,"1.02.17.01",null,"CN21701"]
["1","02","17","02",null,null,null,"Reserved",null,"Summary"]
["1","02","17","03","","",null,"Injector Lasers Install & Align",null,"1.02.17.03",null,"CN21703"]
["1","02","17","04","","",null,"RF Gun & Load Lock Install & Align",null,"1.02.17.04",null,"CN21704"]
["1","02","17","05","","",null,"Gun to Linac Section (GTL) Install & Align",null,"1.02.17.05",null,"CN21705"]
["1","02","17","06","","",null,"Injector Linac Structures Install & Align",null,"1.02.17.06",null,"CN21706"]
["1","02","17","07","","",null,"L0-1 to L0-2 Section (L0-1TL0-2) Install & Align",null,"1.02.17.07",null,"CN21707"]
["1","02","17","08","","",null,"Linac to DL1 (LTDL1) Install & Align",null,"1.02.17.08",null,"CN21708"]
["1","02","17","09","","",null,"Dog Leg 1 Bend (DL1) Install & Align",null,"1.02.17.09",null,"CN21709"]
["1","02","17","10","","",null,"DL1 to Linac (DL1TL) Install & Align",null,"1.02.17.10",null,"CN21710"]
["1","02","17","11","","",null,"Straight Ahead Beamline (SAB) Install & Align",null,"1.02.17.11",null,"CN21711"]
["1","02","17","12","","",null,"Injector RF Waveguide System Install & Align",null,"1.02.17.12",null,"CN21712"]
["1","02","17","13",null,null,null,"Reserved",null,"Summary"]
["1","02","17","14","","",null,"Cathode and Load Lock Install & Align",null,"1.02.17.14",null,"CN21714"]
["1","02","17","15","","",null,"Injector Laser Heater Subsystem Install & Align",null,"1.02.17.15",null,"CN21715"]
["1","02","17","16",null,null,null,"Reserved",null,"Summary"]
["1","02","17","17","","",null,"Power  Conversion Subsystem Installation",null,"1.02.17.17",null,"CN21717"]
["1","03",{"$nulls":5},"LINAC SYSTEM",null,"Summary"]
["1","03","01",{"$nulls":4},"System Management & Integration",null,"Summary"]
["1","03","01","01",null,null,null,"Linac Mechanical Integration",null,"Summary"]
["1","03","01","01","01","",null,"L01 System Integration",null,"1.03.01.01.01",9240441,"CN3010101"]
["1","03","01","01","02","",null,"BC1 System Integration",null,"1.03.01.01.02",9240442,"CN3010102"]
["1","03","01","01","03","",null,"L02 System Integration",null,"1.03.01.01.03",9240443,"CN3010103"]
["1","03","01","01","04","",null,"BC2 System Integration",null,"1.03.01.01.04",9240444,"CN3010104"]
["1","03","01","01","05","",null,"L03 System Integration",null,"1.03.01.01.05",9240445,"CN3010105"]
["1","03","01","01","06","",null,"LTU System Integration",null,"1.03.01.01.06",9240446,"CN3010106"]
["1","03","01","01","07","",null,"E-Dump System Integration",null,"1.03.01.01.07",9240447,"CN3010107"]
["1","03","01","02",null,null,null,"Reserved",null,"Summary"]
["1","03","01","02","01",null,null,"Reserved",null,"Summary"]
["1","03","01","02","02",null,null,"Reserved",null,"Summary"]
["1","03","01","02","03",null,null,"Reserved",null,"Summary"]
["1","03","01","03","","",null,"Travel",null,"1.03.01.03",9240452,"CN30103"]
["1","03","01","04","","",null,"Linac Management",null,"1.03.01.04",9240453,"CN30104"]
["1","03","02",{"$nulls":4},"Linac Controls & Power Conversion Subsystem",null,"Summary"]
["1","03","02","01","","",null,"Personnel Protection System (PPS)",null,"1.03.02.01",9240455,"CN30201"]
["1","03","02","02","","",null,"Beam Containment System (BCS)",null,"1.03.02.02",9240456,"CN30202"]
["1","03","02","03","","",null,"Machine Protection System (MPS)",null,"1.03.02.03",9240457,"CN30203"]
["1","03","02","04",null,null,null,"Linac Power Conversion Subsystem",null,"Summary"]
["1","03","02","04","01","",null,"Beamline Power Supplies - (Dipole Type)",null,"1.03.02.04.01",9240459,"CN3020401"]
["1","03","02","04","01","01",null,"30kw Pwr Supply - (B11-14)",null,"1.03.02.04.01",null,"CN3020401"]
["1","03","02","04","01","02",null,"Power Supply - (B21-26)",null,"1.03.02.04.01",null,"CN3020401"]
["1","03","02","04","01","03",null,"78kw Pwr Supply - (B31-34)",null,"1.03.02.04.01",null,"CN3020401"]
["1","03","02","04","01","04",null,"Reserved",null,"Summary"]
["1","03","02","04","01","05",null,"Power Supply - (BY1)",null,"1.03.02.04.01",null,"CN3020401"]
["1","03","02","04","01","06",null,"Kicker (BYBKIK)",null,"1.03.02.04.01",null,"CN3020401"]
["1","03","02","04","01","07",null,"Reserved",null,"Summary"]
["1","03","02","04","01","08",null,"78kw Pwr Supply - (Dump Bend)",null,"1.03.02.04.01",null,"CN3020401"]
["1","03","02","04","01","09",null,"Reserved",null,"Summary"]
["1","03","02","04","02","",null,"Beamline Power Supplies - (Quad Type)",null,"1.03.02.04.02",9240460]
["1","03","02","04","02","01",null,"2kw Power Supply - (SEC-23)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","02",null,"2kw Power Supply - (SEC-24)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","03",null,"2kw Power Supply - (SEC-25)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","04",null,"2kw Power Supply - (SEC-26)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","05",null,"2kw Power Supply - (SEC-27)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","06",null,"2kw Power Supply - (SEC-28)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","07",null,"2kw Power Supply - (SEC-29)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","08",null,"10kw Power Supply - (Q24701)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","09",null,"10kw Power Supply - (QM21)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","10",null,"Reserved",null,"Summary"]
["1","03","02","04","02","11",null,"10kw Power Supply - (Q24901)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","12",null,"10kw Power Supply - (QM22)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","13",null,"Power Supply - (QVM1)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","14",null,"Power Supply - (QVM2)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","15",null,"Power Supply - (QVM3)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","16",null,"Power Supply - (QVM4)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","17",null,"Power Supply - (QVB1)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","18",null,"Power Supply - (QDL1)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","19",null,"Power Supply - (QE31)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","20",null,"Power Supply - (QEM1)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","21",null,"Power Supply - (QEM2)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","22",null,"Power Supply - (QEM3)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","23",null,"Power Supply - (QEM4)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","24",null,"Power Supply - (QTm1)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","25",null,"Power Supply - (QTm2)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","26",null,"Power Supply - (QUM1)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","27",null,"Power Supply - (QUM2)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","28",null,"Power Supply - (QUM3)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","29",null,"Power Supply - (QUM4)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","30",null,"Power Supply - (QDMP)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","31",null,"Power Supply - (QUE1)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","02","32",null,"Power Supply - (QUE2)",null,"1.03.02.04.02",null,"CN3020402"]
["1","03","02","04","03","",null,"Beamline Power Supplies - (Trim Type)",null,"1.03.02.04.03",9240461]
["1","03","02","04","03","01",null,"12Amp Power Supply - (MCOR_1)",null,"1.03.02.04.03",null,"CN3020403"]
["1","03","02","04","03","02",null,"30Amp Power Supply - (MCOR_2)",null,"1.03.02.04.03",null,"CN3020403"]
["1","03","02","04","03","03",null,"30Amp Power Supply - (MCOR_3)",null,"1.03.02.04.03",null,"CN3020403"]
["1","03","02","04","03","04",null,"30Amp Power Supply - (MCOR_4)",null,"1.03.02.04.03",null,"CN3020403"]
["1","03","02","04","03","05",null,"Reserved",null,"Summary"]
["1","03","02","04","03","06",null,"Reserved",null,"Summary"]
["1","03","02","04","03","07",null,"Reserved",null,"Summary"]
["1","03","02","04","03","08",null,"Reserved",null,"Summary"]
["1","03","02","04","03","09",null,"Reserved",null,"Summary"]
["1","03","02","04","03","10",null,"Power Supply - (MCOR_LTU1)",null,"1.03.02.04.03",null,"CN3020403"]
["1","03","02","04","03","11",null,"Power Supply - (MCOR_LTU2)",null,"1.03.02.04.03",null,"CN3020403"]
["1","03","02","04","03","12",null,"Power Supply - (MCOR_LTU3)",null,"1.03.02.04.03",null,"CN3020403"]
["1","03","02","04","03","13",null,"Power Supply - (MCOR_LTU4)",null,"1.03.02.04.03",null,"CN3020403"]
["1","03","02","04","03","14",null,"Power Supply - (MCOR_LTU5)",null,"1.03.02.04.03",null,"CN3020403"]
["1","03","02","04","03","15",null,"Power Supply - (MCOR_LTU6)",null,"1.03.02.04.03",null,"CN3020403"]
["1","03","02","04","04","",null,"Controls & Power Supply ",null,"1.03.02.04.04",9240462,"CN3020404"]
["1","03","02","05","","",null,"Controls - LLRF",null,"1.03.02.05",9240463,"CN30205"]
["1","03","02","06",null,null,null,"Controls - E-Beam Diagnostic",null,"Summary"]
["1","03","02","06","01","",null,"Controls - Wire Scanners",null,"1.03.02.06.01",9240465,"CN3020601"]
["1","03","02","06","02","",null,"Controls - BPMs",null,"1.03.02.06.02",9240466,"CN3020602"]
["1","03","02","06","03","",null,"Controls - Toroids",null,"1.03.02.06.03",9240467,"CN3020603"]
["1","03","02","06","04","",null,"Controls - Stoppers",null,"1.03.02.06.04",9240468,"CN3020604"]
["1","03","02","06","05","",null,"Controls - Profile Monitors",null,"1.03.02.06.05",9240469,"CN3020605"]
["1","03","02","06","06","",null,"Controls - E/O Diagnostics",null,"1.03.02.06.06",9240470,"CN3020606"]
["1","03","02","06","07","",null,"Controls - Bunch Length Monitors",null,"1.03.02.06.07",9240471,"CN3020607"]
["1","03","02","06","08","",null,"Controls - Beam Loss Monitors",null,"1.03.02.06.08",9240472,"CN3020608"]
["1","03","02","06","09","",null,"Controls - Single Beam Dump",null,"1.03.02.06.09",9240473,"CN3020609"]
["1","03","02","06","10","",null,"Controls - E Beam Dump",null,"1.03.02.06.10",9240474,"CN3020610"]
["1","03","02","06","11","",null,"Controls - Protection Collimator",null,"1.03.02.06.11",9240475,"CN3020611"]
["1","03","02","06","12","",null,"Controls - Movable Collimator",null,"1.03.02.06.12",9240476,"CN3020612"]
["1","03","02","06","13","",null,"Controls - X-Band Accel Structure",null,"1.03.02.06.13",9240477,"CN3020613"]
["1","03","02","07",null,null,null,"Reserved",null,"Summary"]
["1","03","02","08","","",null,"Controls - Timing",null,"1.03.02.08",9240479,"CN30208"]
["1","03","02","09",null,null,null,"Controls - Vacuum",null,"Summary"]
["1","03","02","09","01","",null,"Controls - Vacuum Instrumentation & Interlocks",null,"1.03.02.09.01",9240481,"CN3020901"]
["1","03","02","09","02","",null,"Controls - Vacuum Pump Power Supplies",null,"1.03.02.09.02",null,"CN3020902"]
["1","03","02","10",null,null,null,"Software & Controls Infrastructure",null,"Summary"]
["1","03","02","10","01",null,null,"Reserved",null,"Summary"]
["1","03","02","10","02",null,null,"Reserved",null,"Summary"]
["1","03","02","10","03",null,null,"Reserved",null,"Summary"]
["1","03","02","10","04","",null,"Data Communications",null,"1.03.02.10.04",null,"CN3021004"]
["1","03","02","10","05","",null,"Computers",null,"1.03.02.10.05",9240488,"CN3021005"]
["1","03","03",{"$nulls":4},"Linac Magnets & Supports",null,"Summary"]
["1","03","03","01","","",null,"Bend Magnet (BX1_BC1)",null,"1.03.03.01",null,"CN30301"]
["1","03","03","02","","",null,"Bend Magnet (BX3_LTU)",null,"1.03.03.02",9240491,"CN30302"]
["1","03","03","03","","",null,"Bend Magnet (BX2_BC2)",null,"1.03.03.03",null,"CN30303"]
["1","03","03","04","","",null,"Bend Magnet (BY_LTU)",null,"1.03.03.04",9240493,"CN30304"]
["1","03","03","05","","",null,"Quad Magnet (Quad_LTU)",null,"1.03.03.05",9240494,"CN30305"]
["1","03","03","06",null,null,null,"Reserved",null,"Summary"]
["1","03","03","07","","",null,"Quad Magnet (QE)",null,"1.03.03.07",9240496,"CN30307"]
["1","03","03","08","","",null,"Corrector Magnet (Type 4)",null,"1.03.03.08",9240497,"CN30308"]
["1","03","03","09","","",null,"Bend Magnet (BYD_LTU)",null,"1.03.03.09",9240498,"CN30309"]
["1","03","03","10","","",null,"Quad Magnet (QA)",null,"1.03.03.10",9240499,"CN30310"]
["1","03","03","11","","",null,"Bend Magnet (BYPM_LTU)",null,"1.03.03.11",9240500,"CN30311"]
["1","03","03","12","","",null,"Bend Magnet (BYKIK_LTU)",null,"1.03.03.12",9240501,"CN30312"]
["1","03","03","13","","",null,"Bend Magnet (BYW_LTU)",null,"1.03.03.13",9240502,"CN30313"]
["1","03","04",{"$nulls":4},"Linac Vacuum Subsystem",null,"Summary"]
["1","03","04","01",null,null,null,"Reserved",null,"Summary"]
["1","03","04","02","","",null,"Linac Beamline Vacuum System",null,"1.03.04.02",9240505,"CN30402"]
["1","03","04","03","","",null,"BC1 Vacuum System",null,"1.03.04.03",9240506,"CN30403"]
["1","03","04","04","","",null,"BC2 Vacuum System",null,"1.03.04.04",9240507,"CN30404"]
["1","03","04","05","","",null,"Linac to Undulator (LTU) Vacuum System",null,null,9240508]
["1","03","04","06","","",null,"Dumpline Vacuum System",null,"1.03.04.06",9240509,"CN30406"]
["1","03","05",{"$nulls":4},"Linac Electron Diagnostics",null,"Summary"]
["1","03","05","01","","",null,"Wire Scanners (15)",null,"1.03.05.01",9240511,"CN30501"]
["1","03","05","02",null,null,null,"Beam Position Monitors",null,"Summary"]
["1","03","05","02","01","",null,"BPMs - Linac Standard (6ea)",null,"1.03.05.02.01",9240513,"CN3050201"]
["1","03","05","02","02","",null,"BPMs - RF (8ea)",null,"1.03.05.02.02",9240514,"CN3050202"]
["1","03","05","02","03","",null,"BPMs - FFTB (9ea)",null,"1.03.05.02.03",9240515,"CN3050203"]
["1","03","05","02","04","",null,"BPMs - High Resolution BC1 (3ea)",null,"1.03.05.02.04",9240516,"CN3050204"]
["1","03","05","03","","",null,"Toroids (9ea) Beam Charge",null,"1.03.05.03",9240517,"CN30503"]
["1","03","05","04","","",null,"Stoppers TU Dump (2ea)",null,"1.03.05.04",9240518,"CN30504"]
["1","03","05","05","","",null,"Profile Monitors (6/4/1 ea)",null,"1.03.05.05",9240519,"CN30505"]
["1","03","05","06","","",null,"E/O Bunch Length Monitors (1ea)",null,"1.03.05.06","CN30506","CN30506"]
["1","03","05","07","","",null,"Bunch Length Monitors (4ea)",null,"1.03.05.07",9240521,"CN30507"]
["1","03","05","08",null,null,null,"Beam Loss Monitors",null,"Summary"]
["1","03","05","08","01","",null,"Beam Loss Monitors (10 PIC)",null,"1.03.05.08.01",9240523,"CN3050801"]
["1","03","05","08","02","",null,"Beam Loss Monitors (2 PLIC)",null,"1.03.05.08.02",9240524,"CN3050802"]
["1","03","05","09","","",null,"Single Beam Dump (1ea)",null,"1.03.05.09",9240525,"CN30509"]
["1","03","05","10","","",null,"Electron Beam Dump (1ea)",null,"1.03.05.10",9240526,"CN30510"]
["1","03","05","11","","",null,"Protection Collimators (4ea)",null,"1.03.05.11",9240527,"CN30511"]
["1","03","05","12","","",null,"Movable Collimators (6ea)",null,"1.03.05.12",9240528,"CN30512"]
["1","03","05","13","","",null,"Safety Dump",null,"1.03.05.13",9240529,"CN30513"]
["1","03","06",{"$nulls":4},"Linac RF Subsystem",null,"Summary"]
["1","03","06","01",null,null,null,"Reserved",null,"Summary"]
["1","03","06","02","","",null,"S-Band High Power System",null,"1.03.06.02",9240532,"CN30602"]
["1","03","06","03","","",null,"S-Band Structures",null,"1.03.06.03",null,"CN30603"]
["1","03","06","04","","",null,"X-Band Low Level System",null,"1.03.06.04",9240534,"CN30604"]
["1","03","06","05",null,null,null,"X-Band High Power System",null,"Summary"]
["1","03","06","05","01","",null,"X-Band HP Klystron",null,"1.03.06.05.01",9240536,"CN3060501"]
["1","03","06","05","02","",null,"X-Band HP Modulator",null,"1.03.06.05.02",9240537,"CN3060502"]
["1","03","06","05","03","",null,"X-Band HP Waveguide System",null,"1.03.06.05.03",null,"CN3060503"]
["1","03","06","06","","",null,"X-Band Structures",null,"1.03.06.06",null,"CN30606"]
["1","03","06","07",null,null,null,"RF Distribution System",null,"Summary"]
["1","03","06","07","01","",null,"Modulator Refurbishment",null,"1.03.06.07.01",null,"CN3060701"]
["1","03","06","07","02","",null,"Solid State Sub Booster",null,"1.03.06.07.02",null,"CN3060702"]
["1","03","06","07","03","",null,"IPA Modifications",null,"1.03.06.07.03",null,"CN3060703"]
["1","03","06","07","04","",null,"Klystron Controls Interfaces",null,"1.03.06.07.04",null,"CN3060704"]
["1","03","06","07","05","",null,"Bunch Length Electronics",null,"1.03.06.07.05",null,"CN3060705"]
["1","03","06","07","06","",null,"RF Phase Measurements",null,"1.03.06.07.06",null,"CN3060706"]
["1","03","06","07","07","",null,"RF Distribution L2 & L3",null,"1.03.06.07.07",null,"CN3060707"]
["1","03","06","07","08","",null,"RF Fiber Optics Electronics System",null,"1.03.06.07.08",null,"CN3060708"]
["1","03","06","07","09","",null,"RF Stability",null,"1.03.06.07.09",null,"CN3060709"]
["1","03","07",{"$nulls":4},"Linac Installation & Alignment",null,"Summary"]
["1","03","07","01","","",null,"Linac L01 System Installation & Alignment",null,"1.03.07.01",null,"CN30701"]
["1","03","07","02","","",null,"Linac BC1 System Installation & Alignment",null,"1.03.07.02",null,"CN30702"]
["1","03","07","03","","",null,"Linac L02 System Installation & Alignment",null,"1.03.07.03",null,"CN30703"]
["1","03","07","04","","",null,"Linac BC2 System Installation & Alignment",null,"1.03.07.04",null,"CN30704"]
["1","03","07","05","","",null,"Linac L03 System Installation & Alignment",null,"1.03.07.05",null,"CN30705"]
["1","03","07","06","","",null,"Linac LTU System Installation & Alignment",null,"1.03.07.06",null,"CN30706"]
["1","03","07","07","","",null,"Linac E-Dump System Installation & Alignment",null,"1.03.07.07",null,"CN30707"]
["1","04",{"$nulls":5},"UNDULATOR SYSTEM",null,"Summary"]
["1","04","01",{"$nulls":4},"Undulator System Management & Integration",null,"Summary"]
["1","04","01","01",null,null,null,"Undulator System Management",null,"Summary"]
["1","04","01","01","01","",null,"Undulator System Management - Technical",null,"1.04.01.01.01","PD4010101","CN4010101"]
["1","04","01","01","02","",null,"ANL Project Support",null,"1.04.01.01.02","PD4010102","CN4010102"]
["1","04","01","02",null,null,null,"Undulator System Materials & Supplies",null,"Summary"]
["1","04","01","02","01","",null,"Undulator System M&S - General",null,"1.04.01.02.01","PD4010201","CN4010201"]
["1","04","01","02","02","",null,"Undulator System Travel",null,"1.04.01.02.02","PD4010202","CN4010202"]
["1","04","01","03","","",null,"Undulator System Reviews and Workshops",null,"1.04.01.03","PD40103","CN40103"]
["1","04","02",{"$nulls":4},"Controls",null,"Summary"]
["1","04","02","01",null,null,null,"Controls Management and Integration",null,"Summary"]
["1","04","02","01","01",null,null,"Reserved",null,"Summary"]
["1","04","02","01","02",null,null,"Reserved",null,"Summary"]
["1","04","02","01","03","",null,"Software Interface with SLAC",null,"1.04.02.01.03","PD4020103","CN4020103"]
["1","04","02","01","04",null,null,"Reserved",null,"Summary"]
["1","04","02","02",null,null,null,"Motion",null,"Summary"]
["1","04","02","02","01",null,null,"Fine Motion",null,"Summary"]
["1","04","02","02","01","01",null,"Motor Interface",null,"1.04.02.02.01","PD4020201","CN4020201"]
["1","04","02","02","01","02",null,"Encoder Interface",null,"1.04.02.02.01","PD4020201","CN4020201"]
["1","04","02","02","01","03",null,"Motor Driver",null,"1.04.02.02.01","PD4020201","CN4020201"]
["1","04","02","02","01","04",null,"Cabling",null,"1.04.02.02.01","PD4020201","CN4020201"]
["1","04","02","02","01","05",null,"Integrate components",null,"1.04.02.02.01","PD4020201","CN4020201"]
["1","04","02","02","02",null,null,"Phase Corrector Motion",null,"Summary"]
["1","04","02","02","02","01",null,"Motor Interface",null,"1.04.02.02.02","PD4020202","CN4020202"]
["1","04","02","02","02","02",null,"Reserved",null,"Summary"]
["1","04","02","02","02","03",null,"Reserved",null,"Summary"]
["1","04","02","02","02","04",null,"Cabling",null,"1.04.02.02.02","PD4020202","CN4020202"]
["1","04","02","02","02","05",null,"Integrate components",null,"1.04.02.02.02","PD4020202","CN4020202"]
["1","04","02","02","03",null,null,"Reserved",null,"Summary"]
["1","04","02","02","04",null,null,"Reserved",null,"Summary"]
["1","04","02","02","05",null,null,"Reserved",null,"Summary"]
["1","04","02","02","06",null,null,"Scanning Wire Motion",null,"Summary"]
["1","04","02","02","06","01",null,"Motor Interface",null,"1.04.02.02.06","PD4020206"]
["1","04","02","02","06","02",null,"Reserved",null,"Summary"]
["1","04","02","02","06","03",null,"Reserved",null,"Summary"]
["1","04","02","02","06","04",null,"Reserved",null,"Summary"]
["1","04","02","02","06","05",null,"Integrate components",null,"1.04.02.02.06","PD4020206","CN4020206"]
["1","04","02","02","07",null,null,"Macroscopic Motion",null,"Summary"]
["1","04","02","02","07","01",null,"Motor Interface",null,"1.04.02.02.07","PD4020207","CN4020207"]
["1","04","02","02","07","02",null,"Reserved",null,"Summary"]
["1","04","02","02","07","03",null,"Motor Driver",null,"1.04.02.02.07","PD4020207","CN4020207"]
["1","04","02","02","07","04",null,"Cabling",null,"1.04.02.02.07","PD4020207","CN4020207"]
["1","04","02","02","07","05",null,"Integrate components",null,"1.04.02.02.07","PD4020207","CN4020207"]
["1","04","02","03",null,null,null,"Signal Analysis",null,"Summary"]
["1","04","02","03","01",null,null,"RFBPM",null,"Summary"]
["1","04","02","03","01","01",null,"Reserved",null,"Summary"]
["1","04","02","03","01","02",null,"Signal Acquisition",null,"1.04.02.03.01","PD4020301","CN4020301"]
["1","04","02","03","01","03",null,"Timing interface",null,"1.04.02.03.01","PD4020301","CN4020301"]
["1","04","02","03","01","04",null,"Cabling",null,"1.04.02.03.01","PD4020301","CN4020301"]
["1","04","02","03","01","05",null,"Integrate components",null,"1.04.02.03.01","PD4020301","CN4020301"]
["1","04","02","03","02",null,null,"Charge Monitor",null,"Summary"]
["1","04","02","03","02","01",null,"Reserved",null,"Summary"]
["1","04","02","03","02","02",null,"Reserved",null,"Summary"]
["1","04","02","03","02","03",null,"Integrate components",null,"1.04.02.03.02","PD4020302","CN4020302"]
["1","04","02","03","03",null,null,"Scanning Wire",null,"Summary"]
["1","04","02","03","03","01",null,"Reserved",null,"Summary"]
["1","04","02","03","03","02",null,"Reserved",null,"Summary"]
["1","04","02","03","03","03",null,"Reserved",null,"Summary"]
["1","04","02","03","03","04",null,"Reserved",null,"Summary"]
["1","04","02","03","03","05",null,"Reserved",null,"Summary"]
["1","04","02","03","03","06",null,"Integrate components",null,"1.04.02.03.03","PD4020303","CN4020303"]
["1","04","02","04",null,null,null,"Video",null,"Summary"]
["1","04","02","04","01",null,null,"OTR Monitor",null,"Summary"]
["1","04","02","04","01","01",null,"Camera",null,"1.04.02.04.01","PD4020401","CN4020401"]
["1","04","02","04","01","02",null,"Camera trigger interface",null,"1.04.02.04.01","PD4020401","CN4020401"]
["1","04","02","04","01","03",null,"Digitizer",null,"1.04.02.04.01","PD4020401","CN4020401"]
["1","04","02","04","01","04",null,"Timing interface",null,"Summary"]
["1","04","02","04","01","05",null,"Cabling",null,"1.04.02.04.01","PD4020401","CN4020401"]
["1","04","02","04","01","06",null,"Integrate components",null,"1.04.02.04.01","PD4020401","CN4020401"]
["1","04","02","04","02",null,null,"Reserved",null,"Summary"]
["1","04","02","04","03",null,null,"Observation station video",null,"Summary"]
["1","04","02","04","03","01",null,"Camera",null,"1.04.02.04.03","PD4020403","CN4020403"]
["1","04","02","04","03","02",null,"Camera trigger interface",null,"1.04.02.04.03",null,"CN4020403"]
["1","04","02","04","03","03",null,"Multiplexor",null,"1.04.02.04.03","PD4020403","CN4020403"]
["1","04","02","04","03","04",null,"Cabling",null,"1.04.02.04.03","PD4020403","CN4020403"]
["1","04","02","04","03","05",null,"Integrate components",null,"1.04.02.04.03","PD4020403","CN4020403"]
["1","04","02","05",null,null,null,"Data Acquisition and Control",null,"Summary"]
["1","04","02","05","01",null,null,"Strongback Temperature monitoring",null,"Summary"]
["1","04","02","05","01","01",null,"Integrate components",null,"1.04.02.05.01","PD4020501","CN4020501"]
["1","04","02","06",null,null,null,"Vacuum",null,"Summary"]
["1","04","02","06","01",null,null,"Ion Pump Controller",null,"Summary"]
["1","04","02","06","01","01",null,"Integrate components",null,"1.04.02.06.01","PD4020601","CN4020601"]
["1","04","02","06","02",null,null,"Reserved",null,"Summary"]
["1","04","02","06","03",null,null,"Reserved",null,"Summary"]
["1","04","02","06","04",null,null,"RGA",null,"Summary"]
["1","04","02","06","04","01",null,"Integrate components",null,"1.04.02.06.04","PD4020604","CN4020604"]
["1","04","02","07",null,null,null,"Machine Protection",null,"Summary"]
["1","04","02","07","01",null,null,"Undulator Global MPS",null,"Summary"]
["1","04","02","07","01","01",null,"Hardware design",null,"1.04.02.07.01","PD4020701","CN4020701"]
["1","04","02","07","01","02",null,"Interface components",null,"1.04.02.07.01","PD4020701","CN4020701"]
["1","04","02","07","02",null,null,"Cerenkov Detector",null,"Summary"]
["1","04","02","07","02","01",null,"Signal interface",null,"1.04.02.07.02","PD4020702","CN4020702"]
["1","04","02","07","03",null,null,"Gamma Ray Detector",null,"Summary"]
["1","04","02","07","03","01",null,"Signal interface",null,"1.04.02.07.03","PD4020703","CN4020703"]
["1","04","02","07","04",null,null,"Chamber Temperature",null,"Summary"]
["1","04","02","07","04","01",null,"Signal interface",null,"1.04.02.07.04","PD4020704","CN4020704"]
["1","04","03",{"$nulls":4},"Undulator Magnet & Support",null,"Summary"]
["1","04","03","01","","",null,"UND Magnet & Support - Mgmt and Integration",null,"1.04.03.01",null,"CN40301"]
["1","04","03","02","","",null,"First Prototype Undulator & Mfg Plan",null,"1.04.03.02","PD40302"]
["1","04","03","03",null,null,null,"1st Article Undulators & Long Lead Procurements",null,"Summary"]
["1","04","03","03","01","",null,"Ti Strongback (LLP)",null,"1.04.03.03.01","PD4030301","CN4030301"]
["1","04","03","03","02","",null,"Magnet Blocks (LLP)",null,"1.04.03.03.02","PD4030302","CN4030302"]
["1","04","03","03","03","",null,"Magnet Poles (LLP)",null,"1.04.03.03.03","PD4030303","CN4030303"]
["1","04","03","03","04","",null,"Magnet Assembly & Supports - 1st Articles",null,"1.04.03.03.04","PD4030304","CN4030304"]
["1","04","03","03","05","",null,"Magnetic Measurement (ANL or SLAC)",null,"1.04.03.03.05",null,"CN4030305"]
["1","04","03","04",null,null,null,"Production Undulator",null,"Summary"]
["1","04","03","04","01","",null,"Magnet Assembly & Supports",null,"1.04.03.04.01",null,"CN4030401"]
["1","04","03","04","02",null,null,"Reserved",null,"Summary"]
["1","04","03","05",null,null,null,"Focusing Magnets",null,"Summary"]
["1","04","03","05","01","",null,"Quadrupoles",null,"1.04.03.05.01","PD4030501","CN4030501"]
["1","04","03","05","02",null,null,"Reserved",null,"Summary"]
["1","04","03","06",null,null,null,"Undulator Magnetic Measurement Facility (SLAC)",null,"Summary"]
["1","04","03","06","01",null,null,"Undulator MMF Setup",null,"Summary"]
["1","04","03","06","01","01",null,"Undulator Test Stand Prototype",null,"1.04.03.06.01",null,"CN4030601"]
["1","04","03","06","01","02",null,"Reserved",null,"Summary"]
["1","04","03","06","01","03",null,"Reserved",null,"Summary"]
["1","04","03","06","01","04",null,"Undulator Test Stand",null,"1.04.03.06.01",null,"CN4030601"]
["1","04","03","06","01","05",null,"Undulator Fiducialization",null,"1.04.03.06.01",null,"CN4030601"]
["1","04","03","06","01","06",null,"Quad Strength and Field Quality",null,"1.04.03.06.01",null,"CN4030601"]
["1","04","03","06","01","07",null,"Quad Fiducialization System",null,"1.04.03.06.01",null,"CN4030601"]
["1","04","03","06","01","08",null,"Hall Probe Calibration System",null,"1.04.03.06.01",null,"CN4030601"]
["1","04","03","06","01","09",null,"Undulator Handling",null,"1.04.03.06.01",null,"CN4030601"]
["1","04","03","06","02",null,null,"Fiducialization and Magnetic Measurements (F/MM)",null,"Summary"]
["1","04","03","06","02","01",null,"F/MM Undulator Magnet Sections",null,"1.04.03.06.02",null,"CN4030602"]
["1","04","03","06","02","02",null,"F/MM Quadrupoles",null,"1.04.03.06.02",null,"CN4030602"]
["1","04","03","06","02","03",null,"F/MM BPMs",null,"1.04.03.06.02",null,"CN4030602"]
["1","04","03","06","02","04",null,"F/MM Correctors",null,"1.04.03.06.02",null,"CN4030602"]
["1","04","03","06","02","05",null,"F/MM Vacuum Chamber",null,"1.04.03.06.02",null,"CN4030602"]
["1","04","03","06","02","06",null,"F/MM Photon Diagnostics Components",null,"1.04.03.06.02",null,"CN4030602"]
["1","04","03","06","03",null,null,"Undulator Monitoring",null,"Summary"]
["1","04","03","06","03","01",null,"Stretched Wire System",null,"1.04.03.06.03",null,"CN4030603"]
["1","04","03","06","03","02",null,"Hydrostatic Level System",null,"1.04.03.06.03",null,"CN4030603"]
["1","04","03","06","03","03",null,"Alignment Hardware & Software",null,"1.04.03.06.03",null,"CN4030603"]
["1","04","03","07",null,null,null,"Reserved",null,"Summary"]
["1","04","03","08",null,null,null,"Fixed Supports",null,"Summary"]
["1","04","03","08","01","",null,"Fixed Sppt Mgmt & Integration",null,"1.04.03.08.01","PD4030801"]
["1","04","03","08","02","",null,"Fixed Support Design",null,"1.04.03.08.02",null,"CN4030802"]
["1","04","03","08","03","",null,"Stabilized Girder Assemblies",null,"1.04.03.08.03",null,"CN4030803"]
["1","04","03","08","04","",null,"Thermal Intercept System",null,"1.04.03.08.04",null,"CN4030804"]
["1","04","03","08","05","",null,"Thermometry",null,"1.04.03.08.05",null,"CN4030805"]
["1","04","03","08","06","",null,"Kinematic Girder Support",null,"1.04.03.08.06",null,"CN4030806"]
["1","04","03","08","07","",null,"Earthquake Bracing",null,"1.04.03.08.07",null,"CN4030807"]
["1","04","03","08","08","",null,"Controls and Software",null,"1.04.03.08.08",null,"CN4030808"]
["1","04","04",{"$nulls":4},"Vacuum System",null,"Summary"]
["1","04","04","01",null,null,null,"Project Oversight",null,"Summary"]
["1","04","04","02",null,null,null,"Undulator Vacuum Chamber Assembly",null,"Summary"]
["1","04","04","02","01","",null,"Prototype Chamber Weldment",null,"1.04.04.02.01","PD4040201","CN4040201"]
["1","04","04","02","02","",null,"Production Chamber Weldment",null,"1.04.04.02.02","PD4040202","CN4040202"]
["1","04","04","03",null,null,null,"Beam-line Bellows Module Assembly",null,"Summary"]
["1","04","04","03","01","",null,"Prototype Bellows Module",null,"1.04.04.03.01","PD4040301","CN4040301"]
["1","04","04","03","02","",null,"Production Bellows Module",null,"1.04.04.03.02","PD4040302","CN4040302"]
["1","04","04","04",null,null,null,"Reserved",null,"Summary"]
["1","04","04","05","","",null,"Short Diagnostic Break (SDB) Assembly",null,"1.04.04.05","PD40405","CN40405"]
["1","04","04","06","","",null,"Long Diagnostic Break (LDB) Assembly",null,"1.04.04.06","PD40406","CN40406"]
["1","04","04","07","","",null,"Entrance Section Assembly",null,"1.04.04.07","PD40407","CN40407"]
["1","04","04","08","","",null,"Exit Section Assembly",null,"1.04.04.08","PD40408","CN40408"]
["1","04","04","09","","",null,"Baking System",null,"1.04.04.09","PD40409","CN40409"]
["1","04","05",{"$nulls":4},"Diagnostics",null,"Summary"]
["1","04","05","01",null,null,null,"Project Oversight",null,"Summary"]
["1","04","05","02",null,null,null,"E-Beam and X-Ray Profile Diagnostics",null,"Summary"]
["1","04","05","02","01","",null,"EBXPD Test Station",null,"1.04.05.02.01","PD4050201","CN4050201"]
["1","04","05","02","02","",null,"EBXPD Vacuum Chamber",null,"1.04.05.02.02","PD4050202","CN4050202"]
["1","04","05","02","03","",null,"Positioning Mechanism",null,"1.04.05.02.03","PD4050203","CN4050203"]
["1","04","05","02","04","",null,"Scanning wire assembly (EBXPD -SWA)",null,"1.04.05.02.04","PD4050204","CN4050204"]
["1","04","05","02","05","",null,"Optical transition radiation imaging assembly",null,"1.04.05.02.05","PD4050205","CN4050205"]
["1","04","05","02","06",null,null,"Reserved",null,"Summary"]
["1","04","05","02","07",null,null,"Reserved",null,"Summary"]
["1","04","05","02","08",null,null,"Reserved",null,"Summary"]
["1","04","05","02","09","",null,"EBXPD  Design & Integration",null,"1.04.05.02.09","PD4050209","CN4050209"]
["1","04","05","03",null,null,null,"Reserved",null,"Summary"]
["1","04","05","04",null,null,null,"End-of-Undulator(EOU) X-ray and Profile diagnost",null,"Summary"]
["1","04","05","04","01","",null,"Prototype Construction and Testing",null,"1.04.05.04.01","PD4050401","CN4050401"]
["1","04","05","04","02","",null,"Bunch Length Monitor-Streak Camera (BLM)",null,"1.04.05.04.02",null,"CN4050402"]
["1","04","05","04","03","",null,"Upstream corrector / separator",null,"1.04.05.04.03","PD4050403","CN4050403"]
["1","04","05","04","04","",null,"Optical Diffraction radiation imaging assembly (",null,"1.04.05.04.04","PD4050404","CN4050404"]
["1","04","05","04","05","",null,"X-ray High Resolution monochromator assembly (EO",null,"1.04.05.04.05","PD4050405","CN4050405"]
["1","04","05","04","06","",null,"X-ray Imaging High Resolution detector assembly",null,"1.04.05.04.06","PD4050406","CN4050406"]
["1","04","05","04","07","",null,"EOU Design and Integration",null,"1.04.05.04.07","PD4050407","CN4050407"]
["1","04","05","05","","",null,"RFBPM",null,"1.04.05.05","PD40505","CN40505"]
["1","04","05","06",null,null,null,"Reserved",null,"Summary"]
["1","04","05","07","","",null,"Charge Monitor (CM)",null,"1.04.05.07","PD40507","CN40507"]
["1","04","05","08","","",null,"Cherenkov Detector",null,"1.04.05.08","PD40508","CN40508"]
["1","04","05","09","","",null,"Radiation Detection Monitor (RDM)",null,"1.04.05.09","PD40509","CN40509"]
["1","04","05","10",null,null,null,"Reserved",null,"Summary"]
["1","04","05","11","","",null,"Supplemental Shielding",null,"1.04.05.11","PD40511","CN40511"]
["1","04","06",{"$nulls":4},"Undulator System Installation and Alignment",null,"Summary"]
["1","04","06","01",null,null,null,"Undulator System Installation and Alignment Inte",null,"Summary"]
["1","04","06","01","01","",null,"Undulator System",null,"1.04.06.01.01",null,"CN4060101"]
["1","04","06","01","02",null,null,"Entrance Section",null,"Summary"]
["1","04","06","01","03",null,null,"Exit Section",null,"Summary"]
["1","04","06","02","","",null,"Control System Installation and Alignment",null,"1.04.06.02",null,"CN40602"]
["1","04","06","03",null,null,null,"Magnets & Supports Installation and Alignment",null,"Summary"]
["1","04","06","03","01",null,null,"Magnets Installation and Alignment",null,"Summary"]
["1","04","06","03","02",null,null,"Fixed Supports Installation and Alignment",null,"Summary"]
["1","04","06","04","","",null,"Vacuum System Installation and Alignment",null,"1.04.06.04",null,"CN40604"]
["1","04","06","05","","",null,"Diagnostics System Installation and Alignment",null,"1.04.06.05",null,"CN40605"]
["1","05",{"$nulls":5},"X-RAY TRANSPORT & DIAGNOSTICS SYSTEMS",null,"Summary"]
["1","05","01",{"$nulls":4},"System Management & Integration",null,"Summary"]
["1","05","01","01",null,null,null,"Management",null,"Summary"]
["1","05","01","01","01","",null,"XTOD Management - Technical",null,"1.05.01.01.01","PD50101","CN50101"]
["1","05","01","01","02","",null,"LLNL Project Support",null,"1.05.01.01.02","PD50101","CN50101"]
["1","05","02",{"$nulls":4},"Controls",null,"Summary"]
["1","05","02","01",null,null,null,"Reserved",null,"Summary"]
["1","05","02","02","","",null,"Slow Controls",null,"1.05.02.02","PD50202","CN50202"]
["1","05","02","03","","",null,"Fast Controls",null,"1.05.02.03","PD50203","CN50203"]
["1","05","02","04","","",null,"Femto Controls",null,"1.05.02.04","PD50204","CN50204"]
["1","05","03",{"$nulls":4},"Mechanical & Vacuum Subsystem",null,"Summary"]
["1","05","03","01",null,null,null,"Reserved",null,"Summary"]
["1","05","03","02","","",null,"Mech/Vac Front End",null,"1.05.03.02","PD50302","CN50302"]
["1","05","03","03",null,null,null,"Mech/Vac Near Hall",null,"Summary"]
["1","05","03","03","01","",null,"NEH Hutch 1",null,"1.05.03.03.01","PD5030301","CN5030301"]
["1","05","03","03","02","",null,"NEH Hutch 2",null,"1.05.03.03.02","PD5030302","CN5030302"]
["1","05","03","03","03","",null,"NEH Hutch 3",null,"1.05.03.03.03","PD5030303","CN5030303"]
["1","05","03","04","","",null,"Mech/Vac Tunnel",null,"1.05.03.04","PD50304","CN50304"]
["1","05","03","05",null,null,null,"Mech/Vac Far Hall",null,"Summary"]
["1","05","03","05","01","",null,"FEH Hutch 1",null,"1.05.03.05.01","PD5030501","CN5030501"]
["1","05","03","05","02","",null,"FEH Hutch 2",null,"1.05.03.05.02","PD5030502","CN5030502"]
["1","05","03","05","03","",null,"FEH Hutch 3",null,"1.05.03.05.03","PD5030503","CN5030503"]
["1","05","04",{"$nulls":4},"Optical  Subsystem",null,"Summary"]
["1","05","04","01",null,null,null,"Reserved",null,"Summary"]
["1","05","04","02",null,null,null,"Facility Optics",null,"Summary"]
["1","05","04","02","01",null,null,"Reserved",null,"Summary"]
["1","05","04","02","02","",null,"Fixed Mask",null,"1.05.04.02.02","PD5040202","CN5040202"]
["1","05","04","02","03","",null,"Slit/Collimators",null,"1.05.04.02.03","PD5040203","CN5040203"]
["1","05","04","02","04","",null,"Flipper Mirror",null,"1.05.04.02.04","PD5040204","CN5040204"]
["1","05","04","02","05","",null,"Gas Attenuator",null,"1.05.04.02.05","CN5040205","CN5040205"]
["1","05","04","02","06",null,null,"Reserved",null,"Summary"]
["1","05","04","02","07",null,null,"Reserved",null,"Summary"]
["1","05","04","02","08","",null,"Solid Attenuator",null,"1.05.04.02.08",null,"CN5040208"]
["1","05","04","02","09",null,null,"Reserved",null,"Summary"]
["1","05","04","03",null,null,null,"End Station Optics",null,"Summary"]
["1","05","04","03","01",null,null,"Reserved",null,"Summary"]
["1","05","04","03","02","",null,"Optics Tank - Near Hall",null,"1.05.04.03.02",null,"CN5040302"]
["1","05","04","03","03",null,null,"Reserved",null,"Summary"]
["1","05","04","03","04",null,null,"Reserved",null,"Summary"]
["1","05","04","03","05",null,null,"Reserved",null,"Summary"]
["1","05","04","04",null,null,null,"Crystals & Gratings",null,"Summary"]
["1","05","04","04","01",null,null,"Reserved",null,"Summary"]
["1","05","04","04","02","",null,"System Monochrometer",null,"1.05.04.04.02","PD5040402","CN5040402"]
["1","05","04","04","03","",null,"Pulse Split & Delay",null,"1.05.04.04.03","PD5040403","CN5040403"]
["1","05","05",{"$nulls":4},"Diagnostics Subsystem",null,"Summary"]
["1","05","05","01",null,null,null,"Reserved",null,"Summary"]
["1","05","05","01","01",null,null,"Reserved",null,"Summary"]
["1","05","05","02",null,null,null,"Modeling & Simulation",null,"Summary"]
["1","05","05","02","01","",null,"Wave Model",null,"1.05.05.02.01","PD5050201","CN5050201"]
["1","05","05","02","02","",null,"Monte Carlo Model",null,"1.05.05.02.02","PD5050202"]
["1","05","05","03",null,null,null,"Facility Diagnostics",null,"Summary"]
["1","05","05","03","01","",null,"Direct Imager",null,"1.05.05.03.01","PD5050301","CN5050301"]
["1","05","05","03","02","",null,"Indirect Imager",null,"1.05.05.03.02","PD5050302","CN5050302"]
["1","05","05","03","03",null,null,"Pulsed Ion Chamber",null,"Summary"]
["1","05","05","03","04",null,null,"Gas Mixing System",null,"Summary"]
["1","05","05","03","05","",null,"FEE Diagnostic Tanks",null,"1.05.05.03.05","PD5050305","CN5050305"]
["1","05","05","03","06","",null,"Ion Pumped Diagnostic Tanks",null,"1.05.05.03.06","PD5050306","CN5050306"]
["1","05","05","04",null,null,null,"Commissioning Diagnostics",null,"Summary"]
["1","05","05","04","01","",null,"Commission Diagnostic Tank",null,"1.05.05.04.01","PD5050401","CN5050401"]
["1","05","05","04","02","",null,"Total Energy Measurement",null,"1.05.05.04.02",null,"CN5050402"]
["1","05","05","04","03",null,null,"Reserved",null,"Summary"]
["1","05","05","04","04","",null,"Spectral Measurement",null,"1.05.05.04.04","PD5050404","CN5050404"]
["1","05","05","04","05","",null,"Spatial Coherence",null,"1.05.05.04.05","PD5050405","CN5050405"]
["1","05","05","04","06","",null,"Spatial Shape & Centroid Measurement",null,"1.05.05.04.06","PD5050406","CN5050406"]
["1","05","05","04","07","",null,"Divergence Measurement",null,"1.05.05.04.07",null,"CN5050407"]
["1","05","06",{"$nulls":4},"X-Ray Transport System Installation & Alignment",null,"Summary"]
["1","05","06","01","","",null,"Front End Enclosure Install",null,"1.05.06.01",null,"CN50601"]
["1","05","06","02","","",null,"Near Hall Install",null,"1.05.06.02",null,"CN50602"]
["1","05","06","03","","",null,"Tunnel Install",null,"1.05.06.03",null,"CN50603"]
["1","05","06","04","","",null,"Far Hall Install",null,"1.05.06.04",null,"CN50604"]
["1","06",{"$nulls":5},"X-RAY END STATION SYSTEMS",null,"Summary"]
["1","06","01",{"$nulls":4},"System Management & Integration",null,"Summary"]
["1","06","01","01","","",null,"Management",null,"1.06.01.01",9240575,"CN60101"]
["1","06","02",{"$nulls":4},"Controls Subsystem",null,"Summary"]
["1","06","02","01",null,null,null,"Cabling",null,"Summary"]
["1","06","02","01","01","",null,"Front End Enclosure Cable",null,"1.06.02.01.01",9240578,"CN6020101"]
["1","06","02","01","02","",null,"Near Hall Cable",null,"1.06.02.01.02",9240579,"CN6020102"]
["1","06","02","01","03","",null,"Tunnel Cable",null,"1.06.02.01.03",9240580,"CN6020103"]
["1","06","02","01","04","",null,"Far Hall Cable",null,"1.06.02.01.04",9240581,"CN6020104"]
["1","06","02","02","","",null,"Network",null,"1.06.02.02",9240582,"CN60202"]
["1","06","02","03","","",null,"PC Support",null,"1.06.02.03",9240583,"CN60203"]
["1","06","02","04","","",null,"Beamline Controls",null,"1.06.02.04",9240584,"CN60204"]
["1","06","02","05",null,null,null,"X-Ray PPS",null,"Summary"]
["1","06","02","05","01","",null,"FEE X-Ray PPS",null,"1.06.02.05.01",9240586,"CN6020501"]
["1","06","02","05","02","",null,"Near Hall X-Ray PPS",null,"1.06.02.05.02",9240587,"CN6020502"]
["1","06","02","05","03","",null,"Tunnel X-Ray PPS",null,"1.06.02.05.03",9240588,"CN6020503"]
["1","06","02","05","04","",null,"Far Hall X-Ray PPS",null,"1.06.02.05.04",9240589,"CN6020504"]
["1","06","02","06",null,null,null,"X-Ray MPS",null,"Summary"]
["1","06","02","06","01","",null,"FEE X-Ray MPS",null,"1.06.02.06.01",9240591,"CN6020601"]
["1","06","02","06","02","",null,"Near Hall X-Ray MPS",null,"1.06.02.06.02",9240592,"CN6020602"]
["1","06","02","06","03","",null,"Tunnel X-Ray MPS",null,"1.06.02.06.03",9240593,"CN6020603"]
["1","06","02","06","04","",null,"Far Hall X-Ray MPS",null,"1.06.02.06.04",9240594,"CN6020604"]
["1","06","02","07",null,null,null,"Laser PPS",null,"Summary"]
["1","06","02","07","01","",null,"Near Hall Laser PPS",null,"1.06.02.07.01",9240596,"CN6020701"]
["1","06","02","07","02","",null,"Far Hall Laser PPS",null,"1.06.02.07.02",9240597,"CN6020702"]
["1","06","02","08",null,null,null,"User Safeguards",null,"Summary"]
["1","06","02","08","01","",null,"Near Hall User Safeguards",null,"1.06.02.08.01",9240599,"CN6020801"]
["1","06","02","08","02","",null,"Far Hall User Safeguards",null,"1.06.02.08.02",9240600,"CN6020802"]
["1","06","03",{"$nulls":4},"Mechanical/Vacuum Subsystem",null,"Summary"]
["1","06","03","01","","",null,"Chamber Support Tables - Mech/Vac",null,"1.06.03.01",9240602,"CN60301"]
["1","06","03","02",null,null,null,"Vacuum Components - Mech/Vac",null,"Summary"]
["1","06","03","02","01","",null,"Valves - Vacuum",null,"1.06.03.02.01",9240604,"CN6030201"]
["1","06","03","02","02","",null,"Hardware - Vacuum",null,"1.06.03.02.02",9240605,"CN6030202"]
["1","06","03","02","03","",null,"Ion Pump - Vacuum",null,"1.06.03.02.03",9240606,"CN6030203"]
["1","06","03","02","04","",null,"Turbo Pump - Vacuum",null,"1.06.03.02.04",9240607,"CN6030204"]
["1","06","03","02","05","",null,"Gauges - Vacuum",null,"1.06.03.02.05",9240608,"CN6030205"]
["1","06","03","03",null,null,null,"Experimental Chambers",null,"Summary"]
["1","06","03","03","01","",null,"Near Hall Experimental Chamber",null,"1.06.03.03.01",9240610,"CN6030301"]
["1","06","03","03","02","",null,"Far Hall Experimental Chamber",null,"1.06.03.03.02",9240611,"CN6030302"]
["1","06","04",{"$nulls":4},"Laser Subsystem",null,"Summary"]
["1","06","04","01",null,null,null,"Oscillator Laser & Pump",null,"Summary"]
["1","06","04","01","01","",null,"Near Hall Oscillator Laser & Pump",null,"1.06.04.01.01",9240614,"CN6040101"]
["1","06","04","01","02","",null,"Far Hall Oscillator Laser & Pump",null,"1.06.04.01.02",9240615,"CN6040102"]
["1","06","04","02","","",null,"Laser Diagnostics",null,"1.06.04.02",9240616,"CN60402"]
["1","06","04","03","","",null,"Laser Supplies & Optical Transport",null,"1.06.04.03",9240617,"CN60403"]
["1","06","04","04","","",null,"Laser Timing",null,"1.06.04.04",9240618,"CN60404"]
["1","06","04","05",null,null,null,"Laser Amplifiers",null,"Summary"]
["1","06","04","05","01","",null,"Near Hall Laser Amplifier",null,"1.06.04.05.01",9240620,"CN6040501"]
["1","06","04","05","02","",null,"Far Hall Laser Amplifier",null,"1.06.04.05.02",9240621,"CN6040502"]
["1","06","05",{"$nulls":4},"X-Ray Detectors",null,"Summary"]
["1","06","05","01","","",null,"Beam Imaging",null,"1.06.05.01",9240623,"CN60501"]
["1","06","05","02","","",null,"2-D X-Ray Detector",null,"1.06.05.02",9240624,"CN60502"]
["1","06","05","03","","",null,"Beam Intensity",null,"1.06.05.03",9240625,"CN60503"]
["1","06","05","04","","",null,"Streak Camera",null,"1.06.05.04",9240626,"CN60504"]
["1","06","06",{"$nulls":4},"System Installation & Alignment",null,"Summary"]
["1","06","06","01","","",null,"Front End Install",null,"1.06.06.01",null,"CN60601"]
["1","06","06","02",null,null,null,"Near Hall Install",null,"Summary"]
["1","06","06","02","01","",null," Near Hall Install Controls",null,"1.06.06.02.01",null,"CN6060201"]
["1","06","06","02","02","",null,"Near Hall Install Mech/Vac",null,"1.06.06.02.02",null,"CN6060202"]
["1","06","06","02","03","",null," Near Hall Install Laser",null,"1.06.06.02.03",null,"CN6060203"]
["1","06","06","02","04","",null,"Near Hall Install Detectors",null,"1.06.06.02.04",null,"CN6060204"]
["1","06","06","02","05",null,null,"Near Hall Install Atomic Physics",null,"Summary"]
["1","06","06","03","","",null,"Tunnel Install",null,"1.06.06.03",null,"CN60603"]
["1","06","06","04",null,null,null,"Far Hall Install",null,"Summary"]
["1","06","06","04","01","",null,"Far Hall Install Controls",null,"1.06.06.04.01",null,"CN6060401"]
["1","06","06","04","02","",null,"Far Hall Install Mech/Vac",null,"1.06.06.04.02",null,"CN6060402"]
["1","06","06","04","03","",null,"Far Hall Install Laser",null,"1.06.06.04.03",null,"CN6060403"]
["1","06","06","04","04","",null,"Far Hall Install Detectors",null,"1.06.06.04.04",null,"CN6060404"]
["1","06","06","04","05",null,null,"Reserved",null,"Summary"]
["1","06","07",{"$nulls":4},"Reserved",null,"Summary"]
["1","06","07","01",null,null,null,"Reserved",null,"Summary"]
["1","06","07","02",null,null,null,"Reserved",null,"Summary"]
["1","06","07","03",null,null,null,"Reserved",null,"Summary"]
["1","06","07","04",null,null,null,"Reserved",null,"Summary"]
["1","07",{"$nulls":5},"Reserved",null,"Summary"]
["1","08",{"$nulls":5},"Reserved",null,"Summary"]
["1","09",{"$nulls":5},"CONVENTIONAL FACILITIES",null,"Summary"]
["1","09","01",{"$nulls":4},"System Management & Integration",null,"Summary"]
["1","09","01","01","","",null,"Management",null,"1.09.01.01",9240651,"CN90101"]
["1","09","01","02","","",null,"Cost Account Managers",null,"1.09.01.02",9240652,"CN90102"]
["1","09","01","03","","",null,"Construction Management",null,"1.09.01.03",null,"CN90103"]
["1","09","01","04",null,null,null,"Mechanical Design (MD)",null,"Summary"]
["1","09","01","04","01",null,null,"Mechanical Design Title 1 (Linac not included)",null,"Summary"]
["1","09","01","04","02","",null,"Mechanical Design T1 Linac Facilities",null,"1.09.01.04",9240655]
["1","09","01","04","03","",null,"Mechanical Design Title 2 (Linac not included)",null,"1.09.01.04",9240655]
["1","09","01","04","04","",null,"Mechanical Design T2 Linac Facilities",null,"1.09.01.04",9240655]
["1","09","01","04","05","",null,"Mechanical Design Title 3 Linac Facility",null,"1.09.01.04",9240655]
["1","09","01","04","06","",null,"Mechanical Design Title 3 (Linac not Included)",null,"1.09.01.04",9240655]
["1","09","01","05",null,null,null,"Site Engineering and Maintenance (SEM)",null,"Summary"]
["1","09","01","05","01","",null,"SEM Engineering Title 1(Linac Not Included)",null,"1.09.01.05",9240656]
["1","09","01","05","02","",null,"SEM Engineering Title 1 Linac Facility",null,"1.09.01.05",9240656]
["1","09","01","05","03",null,null,"SEM Engineering Title 2 (Linac Not Included)",null,"Summary"]
["1","09","01","05","04","",null,"SEM Design Linac Facility Title 2",null,"1.09.01.05",9240656]
["1","09","02",{"$nulls":4},"Title 1 & Title 2 Conventional Facilities",null,"Summary"]
["1","09","02","01",null,null,null,"Reserved",null,"Summary"]
["1","09","02","02",null,null,null,"A & E Services (S20, MMF, MMC not Incl)",null,"Summary"]
["1","09","02","02","01","",null,"Title 1 Design",null,"1.09.02.02",9240658]
["1","09","02","02","02","",null,"Title 2 Design",null,"1.09.02.02",9240658]
["1","09","02","03",null,null,null,"A & E Services - (S20, MMF,MCC)",null,"Summary"]
["1","09","02","03","01","",null,"Title 1 Design (Sector 20)",null,"1.09.02.03",9240659]
["1","09","02","03","02","",null,"Title 2 Design (Sector 20)",null,"1.09.02.03",9240659]
["1","09","02","03","03","",null,"Title 1 Design (MMF)",null,"1.09.02.03",9240659]
["1","09","02","03","04","",null,"Title 2 Design (MMF)",null,"1.09.02.03",9240659]
["1","09","02","03","05","",null,"Title 1 Design (MCC)",null,"1.09.02.03",9240659]
["1","09","02","03","06","",null,"Title 2 Design (MCC)",null,"1.09.02.03",9240659]
["1","09","03",{"$nulls":4},"Construction-T3 Conventional Facilities",null,"Summary"]
["1","09","03","01",null,null,null,"Sector 20 Injector Facilities",null,"Summary"]
["1","09","03","01","01","",null,"Site Preparation",null,"1.09.03.01",null,"CN90301"]
[" ","09","03","01","02",null,null,"Structural",null,"Summary"]
["1","09","03","01","03",null,null,"Electrical",null,"Summary"]
["1","09","03","01","04","",null,"Utilities",null,"1.09.03.01",null,"CN90301"]
["1","09","03","01","05",null,null,"HVAC",null,"Summary"]
["1","09","03","01","06",null,null,"Special System - Fire Protection",null,"Summary"]
["1","09","03","01","07",null,null,"Interior",null,"Summary"]
["1","09","03","01","10","",null,"Project Close Out Sector 20 Injector Facility",null,"1.09.03.01",null,"CN90301"]
["1","09","03","02","","",null,"Magnetic Measurement Facility",null,"1.09.03.02",null,9240662]
["1","09","03","02","01","",null,"Site Preparation",null,"1.09.03.02",null,"CN90302"]
["1","09","03","02","02","",null,"Structural",null,"1.09.03.02",null,"CN90302"]
["1","09","03","02","03","",null,"Electrical",null,"1.09.03.02",null,"CN90302"]
["1","09","03","02","04",null,null,"Utilities",null,"Summary"]
["1","09","03","02","05",null,null,"HVAC",null,"Summary"]
["1","09","03","02","06",null,null,"Special System - Fire Protection",null,"Summary"]
["1","09","03","02","07",null,null,"Interior",null,"Summary"]
["1","09","03","02","10","",null,"Project Close Out Magnetic Measurement Facility",null,"1.09.03.02",null,"CN90302"]
["1","09","03","03",null,null,null,"Main Control Center Facilities Upgrade",null,"Summary"]
["1","09","03","03","01","",null,"Site Preparation",null,"1.09.03.03",null,"CN90303"]
["1","09","03","03","02",null,null,"Structural",null,"Summary"]
["1","09","03","03","03",null,null,"Electrical",null,"Summary"]
["1","09","03","03","04",null,null,"Utilities",null,"Summary"]
["1","09","03","03","05",null,null,"HVAC",null,"Summary"]
["1","09","03","03","06",null,null,"Special System - Fire Protection",null,"Summary"]
["1","09","03","03","07",null,null,"Interior",null,"Summary"]
["1","09","03","03","10","",null,"Project Close Out Main Control Center Facilitiy",null,"1.09.03.03",null,"CN90303"]
["1","09","03","04",null,null,null,"Linac Facility",null,"Summary"]
["1","09","03","04","03","",null,"Electrical",null,"1.09.03.04",null,"CN90304"]
["1","09","03","04","04","",null,"Utilities",null,"1.09.03.04",null,"CN90304"]
["1","09","03","04","06",null,null,"Special System - Fire Protection",null,"Summary"]
["1","09","03","04","10","",null,"Project Close Out Linac Facility",null,"1.09.03.04",null,"CN90304"]
["1","09","03","05","","",null,"Research Yard/B102,B211,B113 & Storage Trailers",null,"1.09.03.05",null,"CN90305"]
["1","09","03","05","01",null,null,"Site Preparation",null,"Summary"]
["1","09","03","05","01","01",null,"Site Preparation SEM",null,"1.09.03.05",null,"CN90305"]
["1","09","03","05","01","02",null,"Site Preparation G/C",null,"Summary"]
["1","09","03","05","02",null,null,"Structural",null,"Summary"]
["1","09","03","05","02","01",null,"Structural SEM",null,"1.09.03.05",null,"CN90305"]
["1","09","03","05","02","02",null,"Structural G/C",null,"Summary"]
["1","09","03","05","03",null,null,"Electrical",null,"Summary"]
["1","09","03","05","03","01",null,"Electrical SEM",null,"1.09.03.05",null,"CN90305"]
["1","09","03","05","03","02",null,"Electrical G/C",null,"Summary"]
["1","09","03","05","04",null,null,"Utilities",null,"Summary"]
["1","09","03","05","04","01",null,"Utilities SEM",null,"1.09.03.05",null,"CN90305"]
["1","09","03","05","04","02",null,"Utilities G/C",null,"Summary"]
["1","09","03","05","05",null,null,"HVAC",null,"Summary"]
["1","09","03","05","05","01",null,"HVAC SEM",null,"1.09.03.05",null,"CN90305"]
["1","09","03","05","05","02",null,"HVAC G/C",null,"Summary"]
["1","09","03","05","06",null,null,"Special System - Fire Protection",null,"Summary"]
["1","09","03","05","06","01",null,"Special System - Fire Protection SEM",null,"1.09.03.05",null,"CN90305"]
["1","09","03","05","06","02",null,"Special System - Fire Protection",null,"Summary"]
["1","09","03","05","07",null,null,"Interior",null,"Summary"]
["1","09","03","05","07","01",null,"Interior SEM",null,"Summary"]
["1","09","03","05","07","02",null,"Interior G/C",null,"Summary"]
["1","09","03","05","10","",null,"Project Close Out Reasearch Yard",null,"1.09.03.05",null,"CN90305"]
["1","09","03","06","","",null,"Access Road & Beam Transport Hall",null,"1.09.03.06",null,"CN90306"]
["1","09","03","06","01","",null,"Site Preparation",null,"1.09.03.06",null,"CN90306"]
["1","09","03","06","02",null,null,"Structural",null,"Summary"]
["1","09","03","06","03",null,null,"Electrical",null,"Summary"]
["1","09","03","06","04",null,null,"Utilities",null,"Summary"]
["1","09","03","06","05",null,null,"HVAC",null,"Summary"]
["1","09","03","06","06",null,null,"Special System- Fire Protection",null,"Summary"]
["1","09","03","06","07",null,null,"Interior",null,"Summary"]
["1","09","03","06","09",null,null,"Reserved",null,"Summary"]
["1","09","03","06","10","",null,"Project Close Out  Beam Trans Hall",null,"1.09.03.06",null,"CN90306"]
["1","09","03","07","","",null,"Undulator Hall",null,"1.09.03.07",null,"CN90307"]
["1","09","03","07","01",null,null,"Site Preparation",null,"Summary"]
["1","09","03","07","02",null,null,"Structural",null,"Summary"]
["1","09","03","07","03",null,null,"Electrical",null,"Summary"]
["1","09","03","07","04",null,null,"Utilities",null,"Summary"]
["1","09","03","07","05",null,null,"HVAC",null,"Summary"]
["1","09","03","07","06",null,null,"Special System - Fire Protection",null,"Summary"]
["1","09","03","07","07",null,null,"Interior",null,"Summary"]
["1","09","03","07","09",null,null,"Tunneling",null,"Summary"]
["1","09","03","07","10","",null,"Project Close Out Undulator Hall",null,"1.09.03.07",null,"CN90307"]
["1","09","03","08","","",null,"Front End Enclosure",null,"1.09.03.08",null,"CN90308"]
["1","09","03","08","01",null,null,"Site Preparation",null,"Summary"]
["1","09","03","08","02",null,null,"Structural",null,"Summary"]
["1","09","03","08","03",null,null,"Electrical",null,"Summary"]
["1","09","03","08","04",null,null,"Utilities",null,"Summary"]
["1","09","03","08","05",null,null,"HVAC",null,"Summary"]
["1","09","03","08","06",null,null,"Special System - Fire Protection",null,"Summary"]
["1","09","03","08","07",null,null,"Interior",null,"Summary"]
["1","09","03","08","09",null,null,"Tunneling",null,"Summary"]
["1","09","03","08","10","",null,"Project Close Out Front End Enclosure",null,"1.09.03.08",null,"CN90308"]
["1","09","03","09","","",null,"Beam Dump",null,"1.09.03.09",null,"CN90309"]
["1","09","03","09","01",null,null,"Site Preparation",null,"Summary"]
["1","09","03","09","02",null,null,"Structural",null,"Summary"]
["1","09","03","09","03","",null,"Electrical",null,"1.09.03.09",null,"CN90309"]
["1","09","03","09","04",null,null,"Utilities",null,"Summary"]
["1","09","03","09","05",null,null,"reserved",null,"Summary"]
["1","09","03","09","06",null,null,"Special System (Fire Protection) Beam Dump",null,"Summary"]
["1","09","03","09","09",null,null,"Tunneling",null,"Summary"]
["1","09","03","09","10","",null,"Project Close Out Beam Dump",null,"1.09.03.09",null,"CN90309"]
["1","09","03","10","","",null,"Near Experimental Hall",null,"1.09.03.10",null,"CN90310"]
["1","09","03","10","01",null,null,"Site Preparation",null,"Summary"]
["1","09","03","10","02",null,null,"Structural",null,"Summary"]
["1","09","03","10","03",null,null,"Electrical",null,"Summary"]
["1","09","03","10","04",null,null,"Utilities",null,"Summary"]
["1","09","03","10","05",null,null,"HVAC",null,"Summary"]
["1","09","03","10","06",null,null,"Special System - Fire Protection",null,"Summary"]
["1","09","03","10","07",null,null,"Interior",null,"Summary"]
["1","09","03","10","09",null,null,"Reserved",null,"Summary"]
["1","09","03","10","10","",null,"Project Close Out Near Experimental Hall",null,"1.09.03.10",null,"CN90310"]
["1","09","03","11","","",null,"X-Ray Transport & Diagnostic Hall",null,"1.09.03.11",null,"CN90311"]
["1","09","03","11","01",null,null,"Site Preparation",null,"Summary"]
["1","09","03","11","02",null,null,"Structural",null,"Summary"]
["1","09","03","11","03",null,null,"Electrical",null,"Summary"]
["1","09","03","11","04",null,null,"Utilities",null,"Summary"]
["1","09","03","11","05",null,null,"HVAC",null,"Summary"]
["1","09","03","11","06",null,null,"Special System - Fire Protection",null,"Summary"]
["1","09","03","11","07",null,null,"Interiors",null,"Summary"]
["1","09","03","11","09","",null,"Tunneling",null,"1.09.03.11",null,"CN90311"]
["1","09","03","11","10","",null,"Project Close Out X-Ray Transport & Diagonistic",null,"1.09.03.11",null,"CN90311"]
["1","09","03","12","","",null,"Far Experimental Hall",null,"1.09.03.12",null,"CN90312"]
["1","09","03","12","01",null,null,"Reserved",null,"Summary"]
["1","09","03","12","02",null,null,"Structural",null,"Summary"]
["1","09","03","12","03",null,null,"Electrical",null,"Summary"]
["1","09","03","12","04",null,null,"Utilities",null,"Summary"]
["1","09","03","12","05",null,null,"HVAC",null,"Summary"]
["1","09","03","12","06",null,null,"Special System - Fire Protection",null,"Summary"]
["1","09","03","12","07",null,null,"Interiors",null,"Summary"]
["1","09","03","12","09",null,null,"Tunneling",null,"Summary"]
["1","09","03","12","10","",null,"Project Close Out Far Experimental Hall",null,"1.09.03.12",null,"CN90312"]
["1","09","03","13","","",null,"Central Lab Office Bldg (CLOB)",null,"1.09.03.13",null,"CN90313"]
["1","09","03","13","01",null,null,"Site Preparation",null,"Summary"]
["1","09","03","13","02",null,null,"Structural",null,"Summary"]
["1","09","03","13","03",null,null,"Electrical",null,"Summary"]
["1","09","03","13","04",null,null,"Utilities",null,"Summary"]
["1","09","03","13","05",null,null,"HVAC",null,"Summary"]
["1","09","03","13","06",null,null,"Special System - Fire Protection",null,"Summary"]
["1","09","03","13","07",null,null,"Interior",null,"Summary"]
["1","09","03","13","10","",null,"Project Close Out CLOB",null,"1.09.03.13",null,"CN90313"]
["2",{"$nulls":6},"LCLS PROJECT - R&D, SPARES, COMMISSIONING",null,"Summary"]
["2","01",{"$nulls":5},"LCLS PROJECT MGMT, PLANNING & ADMN (OPC)",null,"Summary"]
["2","01","01",{"$nulls":4},"Physics Support (OPC)",null,"Summary"]
["2","01","01","01","","",null,"SAC-MAC Physics",null,"2.01.01.01",null,null,9681321,null,"CM10101"]
["2","01","01","02","","",null,"Injector Physics",null,"2.01.01.02",null,null,9681322,null,"CM10102"]
["2","01","01","03","","",null,"Linac Physics",null,"2.01.01.03",null,null,9681323,null,"CM10103"]
["2","01","01","04","","",null,"Undulator Physics",null,"2.01.01.04",null,null,9681324,null,"CM10104"]
["2","01","01","05","","",null,"X-Ray Transport Physics",null,"2.01.01.05",null,null,9681325,null,"CM10105"]
["2","01","01","06","","",null,"X-Ray Endstation Physics",null,"2.01.01.06",null,null,9681326,null,"CM10106"]
["2","01","01","07","","",null,"Conventional Facilities Physics",null,"2.01.01.07",null,null,9681327,null,"CM10107"]
["2","01","01","08","","",null,"Consulting Physics (Collaboration)",null,"2.01.01.08",null,null,9681328,null,"CM10108"]
["2","01","01","09","","",null,"Consulting Physics (SLAC)",null,"2.01.01.09",null,null,9681329,null,"CM10109"]
["2","01","01","10","","",null,"Global Controls Physics Liaison",null,"2.01.01.10",null,null,9681330,null,"CM10110"]
["2","01","01","11","","",null,"Global Controls OPC",null,"2.01.01.11",{"$nulls":4},"CM10111"]
["2","01","02","","","",null,"R&D Studies & Prototyping",null,"2.01.02",null,null,9681010,null,"CM102"]
["2","01","03","","","",null,"Project Mgmnt, Planning and Admn - M&S (OPC)",null,"2.01.03",null,null,9681011,null,"CM103"]
["2","01","03","01",null,null,null,"Reserved",null,"Summary"]
["2","01","03","02",null,null,null,"Reserved",null,"Summary"]
["2","01","03","03",null,null,null,"Reserved",null,"Summary"]
["2","01","03","04",null,null,null,"Reserved",null,"Summary"]
["2","01","03","05",null,null,null,"Reserved",null,"Summary"]
["2","01","03","06",null,null,null,"Reserved",null,"Summary"]
["2","01","03","07",null,null,null,"Reserved",null,"Summary"]
["2","01","03","08",null,null,null,"Reserved",null,"Summary"]
["2","01","03","09",null,null,null,"Reserved",null,"Summary"]
["2","01","03","10",null,null,null,"Reserved",null,"Summary"]
["2","01","03","11",null,null,null,"Reserved",null,"Summary"]
["2","02",{"$nulls":5},"INJECTOR SYSTEM (OPC)",null,"Summary"]
["2","02","01",{"$nulls":4},"Reserved",null,"Summary"]
["2","02","01","01",null,null,null,"Reserved",null,"Summary"]
["2","02","01","02",null,null,null,"Reserved",null,"Summary"]
["2","02","01","03",null,null,null,"Reserved",null,"Summary"]
["2","02","02",{"$nulls":4},"Injector Controls Subsystem",null,"Summary"]
["2","02","02","01","","",null,"EPICS VXI Control Modules",null,"2.02.02.01",null,null,9681017,"SP20201","CM20201"]
["2","02","02","02","","",null,"LLRF Controls",null,"2.02.02.02",null,null,9681018]
["2","02","02","03",null,null,null,"E-Beam Diagnostics Controls",null,"Summary"]
["2","02","02","03","01",null,null,"Reserved",null,"Summary"]
["2","02","02","03","02","",null,"Controls - Toroids",null,"2.02.02.03.02",{"$nulls":4},"CM2020302"]
["2","02","02","03","03","",null,"Controls - Faraday Cup",null,"2.02.02.03.03",null,null,9681022]
["2","02","02","03","04","",null,"Controls - Tune-Up Dump",null,"2.02.02.03.04",{"$nulls":4},"CM2020304"]
["2","02","02","03","05","",null,"Controls - Profile Monitors",null,"2.02.02.03.05",null,null,9681024]
["2","02","02","03","06","",null,"Control - EO Diagnostic",null,"2.02.02.03.06",{"$nulls":4},"CM2020306"]
["2","02","02","03","07","",null,"Controls - BPM Processor Module",null,"2.02.02.03.07",null,null,9681026]
["2","02","02","04",null,null,null,"Reserved",null,"Summary"]
["2","02","02","05",null,null,null,"Reserved",null,"Summary"]
["2","02","02","06",null,null,null,"Reserved",null,"Summary"]
["2","02","02","07",null,null,null,"Reserved",null,"Summary"]
["2","02","02","08",null,null,null,"Reserved",null,"Summary"]
["2","02","02","09",null,null,null,"Reserved",null,"Summary"]
["2","02","03",{"$nulls":4},"Injector Lasers",null,"Summary"]
["2","02","03","01","","",null,"Drive Laser Prototyping",null,"2.02.03.01",null,null,9681034]
["2","02","03","02","","",null,"Drive Laser Oscillator",null,"2.02.03.02",null,null,null,"SP20302"]
["2","02","03","03",null,null,null,"Reserved",null,"Summary"]
["2","02","03","04",null,null,null,"Reserved",null,"Summary"]
["2","02","03","05",null,null,null,"Reserved",null,"Summary"]
["2","02","03","06",null,null,null,"Reserved",null,"Summary"]
["2","02","03","07",null,null,null,"Reserved",null,"Summary"]
["2","02","03","08",null,null,null,"Reserved",null,"Summary"]
["2","02","03","09",null,null,null,"Reserved",null,"Summary"]
["2","02","03","10",null,null,null,"Reserved",null,"Summary"]
["2","02","03","11",null,null,null,"Reserved",null,"Summary"]
["2","02","03","12",null,null,null,"Reserved",null,"Summary"]
["2","02","03","13",null,null,null,"Reserved",null,"Summary"]
["2","02","03","14",null,null,null,"Reserved",null,"Summary"]
["2","02","03","15",null,null,null,"Reserved",null,"Summary"]
["2","02","03","16",null,null,null,"Reserved",null,"Summary"]
["2","02","03","17",null,null,null,"Reserved",null,"Summary"]
["2","02","03","18",null,null,null,"Reserved",null,"Summary"]
["2","02","03","19",null,null,null,"Reserved",null,"Summary"]
["2","02","03","20",null,null,null,"Reserved",null,"Summary"]
["2","02","03","21",null,null,null,"Reserved",null,"Summary"]
["2","02","03","22",null,null,null,"Reserved",null,"Summary"]
["2","02","03","23",null,null,null,"Reserved",null,"Summary"]
["2","02","03","24",null,null,null,"Reserved",null,"Summary"]
["2","02","03","25",null,null,null,"Reserved",null,"Summary"]
["2","02","03","26",null,null,null,"Reserved",null,"Summary"]
["2","02","03","27",null,null,null,"Reserved",null,"Summary"]
["2","02","03","28",null,null,null,"Reserved",null,"Summary"]
["2","02","03","29",null,null,null,"Reserved",null,"Summary"]
["2","02","03","30",null,null,null,"Reserved",null,"Summary"]
["2","02","04",{"$nulls":4},"RF Gun & Load Lock",null,"Summary"]
["2","02","04","01","","",null,"RF Gun",null,"2.02.04.01",null,null,9681065]
["2","02","04","02","","",null,"RF Gun Supports",null,"2.02.04.02",null,null,null,"SP20402"]
["2","02","04","03","","",null,"Gun Load Lock",null,"2.02.04.03",null,null,null,"SP20403"]
["2","02","04","04",null,null,null,"Reserved",null,"Summary"]
["2","02","04","05",null,null,null,"Reserved",null,"Summary"]
["2","02","04","06",null,null,null,"Reserved",null,"Summary"]
["2","02","04","07",null,null,null,"Reserved",null,"Summary"]
["2","02","04","08",null,null,null,"Reserved",null,"Summary"]
["2","02","05",{"$nulls":4},"Gun to Linac Section (GTL)",null,"Summary"]
["2","02","05","01",null,null,null,"Reserved",null,"Summary"]
["2","02","05","02","","",null,"GTL Faraday Cup/YAG1",null,"2.02.05.02",null,null,null,"SP20502"]
["2","02","05","03",null,null,null,"Reserved",null,"Summary"]
["2","02","05","04",null,null,null,"Reserved",null,"Summary"]
["2","02","05","05",null,null,null,"Reserved",null,"Summary"]
["2","02","05","06",null,null,null,"Reserved",null,"Summary"]
["2","02","05","07",null,null,null,"Reserved",null,"Summary"]
["2","02","05","08",null,null,null,"Reserved",null,"Summary"]
["2","02","05","09",null,null,null,"Reserved",null,"Summary"]
["2","02","05","10",null,null,null,"Reserved",null,"Summary"]
["2","02","05","11",null,null,null,"Reserved",null,"Summary"]
["2","02","06",{"$nulls":4},"Injector Linac Structures",null,"Summary"]
["2","02","06","01",null,null,null,"Reserved",null,"Summary"]
["2","02","06","02","","",null,"L0-2 Structure Assembly",null,"2.02.06.02",null,null,null,"SP20602"]
["2","02","06","03",null,null,null,"Reserved",null,"Summary"]
["2","02","06","04",null,null,null,"Reserved",null,"Summary"]
["2","02","07",{"$nulls":4},"L0-1 to L0-2 Section (L0-1TL0-2)",null,"Summary"]
["2","02","07","01",null,null,null,"Reserved",null,"Summary"]
["2","02","07","02","","",null,"L0-1TL0-2 BPMs ( )",null,"2.02.07.02",null,null,null,"SP20702"]
["2","02","07","03",null,null,null,"Reserved",null,"Summary"]
["2","02","07","04",null,null,null,"Reserved",null,"Summary"]
["2","02","07","05",null,null,null,"Reserved",null,"Summary"]
["2","02","07","06",null,null,null,"Reserved",null,"Summary"]
["2","02","07","07",null,null,null,"Reserved",null,"Summary"]
["2","02","08",{"$nulls":4},"Linac to DL1 (LTDL1)",null,"Summary"]
["2","02","08","01",null,null,null,"Reserved",null,"Summary"]
["2","02","08","02","","",null,"LTDL1 BPMs ( )",null,"2.02.08.02",null,null,null,"SP20802"]
["2","02","08","03",null,null,null,"Reserved",null,"Summary"]
["2","02","08","04",null,null,null,"Reserved",null,"Summary"]
["2","02","08","05",null,null,null,"Reserved",null,"Summary"]
["2","02","08","06",null,null,null,"Reserved",null,"Summary"]
["2","02","08","07",null,null,null,"Reserved",null,"Summary"]
["2","02","08","08",null,null,null,"Reserved",null,"Summary"]
["2","02","08","09",null,null,null,"Reserved",null,"Summary"]
["2","02","08","10",null,null,null,"Reserved",null,"Summary"]
["2","02","09",{"$nulls":4},"Dog Leg 1 Bend (DL1)",null,"Summary"]
["2","02","09","01",null,null,null,"Reserved",null,"Summary"]
["2","02","09","02","","",null,"DL1 QB Quadrupole",null,"2.02.09.02",null,null,null,"SP20902"]
["2","02","09","03",null,null,null,"Reserved",null,"Summary"]
["2","02","09","04",null,null,null,"Reserved",null,"Summary"]
["2","02","09","05",null,null,null,"Reserved",null,"Summary"]
["2","02","09","06",null,null,null,"Reserved",null,"Summary"]
["2","02","10",{"$nulls":4},"DL1 to Linac (DL1TL)",null,"Summary"]
["2","02","10","01",null,null,null,"Reserved",null,"Summary"]
["2","02","10","02","","",null,"DL1TL Steering Coils ( X-Y Assys)",null,"2.02.10.02",null,null,null,"SP21002"]
["2","02","10","03",null,null,null,"Reserved",null,"Summary"]
["2","02","10","04",null,null,null,"Reserved",null,"Summary"]
["2","02","10","05",null,null,null,"Reserved",null,"Summary"]
["2","02","10","06",null,null,null,"Reserved",null,"Summary"]
["2","02","10","07",null,null,null,"Reserved",null,"Summary"]
["2","02","11",{"$nulls":4},"Straight Ahead Beamline (SAB)",null,"Summary"]
["2","02","11","01",null,null,null,"Reserved",null,"Summary"]
["2","02","11","02","","",null,"SAB Quadrupoles ( )",null,"2.02.11.02",null,null,null,"SP21102"]
["2","02","11","03",null,null,null,"Reserved",null,"Summary"]
["2","02","11","04",null,null,null,"Reserved",null,"Summary"]
["2","02","11","05",null,null,null,"Reserved",null,"Summary"]
["2","02","11","06",null,null,null,"Reserved",null,"Summary"]
["2","02","11","07",null,null,null,"Reserved",null,"Summary"]
["2","02","11","08",null,null,null,"Reserved",null,"Summary"]
["2","02","11","09",null,null,null,"Reserved",null,"Summary"]
["2","02","12",{"$nulls":4},"Injector RF Waveguide Subsystem",null,"Summary"]
["2","02","12","01",null,null,null,"Reserved",null,"Summary"]
["2","02","12","02","","",null,"RF Waveguide Supports",null,"2.02.12.02",null,null,null,"SP21202"]
["2","02","13",{"$nulls":4},"Injector RF Subsystem",null,"Summary"]
["2","02","13","01",null,null,null,"Reserved",null,"Summary"]
["2","02","13","01","01",null,null,"Reserved",null,"Summary"]
["2","02","13","02",null,null,null,"Reserved",null,"Summary"]
["2","02","14",{"$nulls":4},"Cathode Processing (CP) Station",null,"Summary"]
["2","02","14","01",null,null,null,"Reserved",null,"Summary"]
["2","02","14","02","","",null,"CP Load Lock",null,"2.02.14.02",null,null,null,"SP21302"]
["2","02","14","03",null,null,null,"Reserved",null,"Summary"]
["2","02","14","04",null,null,null,"Reserved",null,"Summary"]
["2","02","14","05",null,null,null,"Reserved",null,"Summary"]
["2","02","15",{"$nulls":4},"Injector Laser Heater Subsystem",null,"Summary"]
["2","02","15","01",null,null,null,"Reserved",null,"Summary"]
["2","02","15","02","","",null,"Beam Conditioning Optics (Laser Bay)",null,"2.02.15.02",null,null,null,"SP21502"]
["2","02","15","03",null,null,null,"Reserved",null,"Summary"]
["2","02","15","04",null,null,null,"Reserved",null,"Summary"]
["2","02","15","05",null,null,null,"Reserved",null,"Summary"]
["2","02","15","06",null,null,null,"Reserved",null,"Summary"]
["2","02","15","07",null,null,null,"Reserved",null,"Summary"]
["2","02","15","08",null,null,null,"Reserved",null,"Summary"]
["2","02","16",{"$nulls":4},"Injector Power Conversion Subsystem",null,"Summary"]
["2","02","16","01","","",null,"Personnel Protection System (PPS) R&D",null,"2.02.16.01",null,null,9681155]
["2","02","16","02",null,null,null,"Reserved",null,"Summary"]
["2","02","16","03",null,null,null,"Reserved",null,"Summary"]
["2","02","16","04","","",null,"Power Conv (beamline pwr supp) Spares",null,"2.02.16.04",null,null,null,"SP21604"]
["2","02","17",{"$nulls":4},"Injector System Commissioning",null,"Summary"]
["2","02","17","01",null,null,null,"Reserved",null,"Summary"]
["2","02","17","02","","",null,"Drive Laser Commissioning",null,"2.02.17.02",{"$nulls":4},"CM21702"]
["2","02","17","03","","",null,"RF Conditioning",null,"2.02.17.03",{"$nulls":4},"CM21703"]
["2","02","17","04","","",null,"RF Gun Operation with Beam",null,"2.02.17.04",{"$nulls":4},"CM21704"]
["2","02","17","05","","",null,"L0-1&L0-2 Commissioning",null,"2.02.17.05",{"$nulls":4},"CM21705"]
["2","02","17","06","","",null,"L0&SAB Commissioning",null,"2.02.17.06",{"$nulls":4},"CM21706"]
["2","02","17","07","","",null,"DL1 Commissioning",null,"2.02.17.07",{"$nulls":4},"CM21707"]
["2","02","17","08","","",null,"Injector Optimization",null,"2.02.17.08",{"$nulls":4},"CM21708"]
["2","03",{"$nulls":5},"LINAC SYSTEM (OPC)",null,"Summary"]
["2","03","01",{"$nulls":4},"Reserved",null,"Summary"]
["2","03","01","01",null,null,null,"Reserved",null,"Summary"]
["2","03","01","02",null,null,null,"Reserved",null,"Summary"]
["2","03","01","03",null,null,null,"Reserved",null,"Summary"]
["2","03","01","04",null,null,null,"Reserved",null,"Summary"]
["2","03","02",{"$nulls":4},"Linac Controls & Power Conversion Subsystem",null,"Summary"]
["2","03","02","01",null,null,null,"Reserved",null,"Summary"]
["2","03","02","02",null,null,null,"Reserved",null,"Summary"]
["2","03","02","03",null,null,null,"Reserved",null,"Summary"]
["2","03","02","04",null,null,null,"Power Conversion",null,"Summary"]
["2","03","02","04","01","",null,"Spare Power Supply (Dipole Type)",null,"2.03.02.04.01",null,null,null,"SP3020401"]
["2","03","02","04","02","",null,"Spare Power Supply (Quad Type)",null,"2.03.02.04.02",null,null,null,"SP3020402"]
["2","03","02","04","03","",null,"Spare Power Supply (Trim Type)",null,"2.03.02.04.03",null,null,null,"SP3020403"]
["2","03","02","04","04",null,null,"Reserved",null,"Summary"]
["2","03","02","05",null,null,null,"Reserved",null,"Summary"]
["2","03","02","06",null,null,null,"Reserved",null,"Summary"]
["2","03","02","07",null,null,null,"Reserved",null,"Summary"]
["2","03","02","08",null,null,null,"Reserved",null,"Summary"]
["2","03","02","09",null,null,null,"Reserved",null,"Summary"]
["2","03","02","10",null,null,null,"Reserved",null,"Summary"]
["2","03","03",{"$nulls":4},"Linac Magnets & Supports",null,"Summary"]
["2","03","03","01","","",null,"Bend Magnet (BX1_BC1)",null,"2.03.03.01",null,null,null,"SP30301"]
["2","03","03","02","","",null,"Bend Magnet (BX3_LTU)",null,"2.03.03.02",null,null,null,"SP30302"]
["2","03","03","03","","",null,"Bend Magnet (BX2_BC2)",null,"2.03.03.03",null,null,null,"SP30303"]
["2","03","03","04","","",null,"Bend Magnet (BY_LTU)",null,"2.03.03.04",null,null,null,"SP30304"]
["2","03","03","05","","",null,"Quad Magnet (Quad_LTU)",null,"2.03.03.05",null,null,null,"SP30305"]
["2","03","03","06",null,null,null,"Resered",null,"Summary"]
["2","03","03","07",null,null,null,"Resered",null,"Summary"]
["2","03","03","08",null,null,null,"Resered",null,"Summary"]
["2","03","03","09","","",null,"Bend Magnet (BYD_LTU)",null,"2.03.03.09",null,null,null,"SP30309"]
["2","03","03","10",null,null,null,"Reserved",null,"Summary"]
["2","03","03","11","","",null,"Bend Magnet (BYPM_LTU)",null,"2.03.03.11",null,null,null,"SP30311"]
["2","03","03","12","","",null,"Bend Magnet (BYKIK_LTU)",null,"2.03.03.12",null,null,null,"SP30312"]
["2","03","03","13","","",null,"Bend Magnet (BYW_LTU)",null,"2.03.03.13",null,null,null,"SP30313"]
["2","03","04",{"$nulls":4},"Linac Vacuum Subsystem",null,"Summary"]
["2","03","04","01","","",null,"Linac Vacuum Subsystem Operations Equip",null,"2.03.04.01",{"$nulls":4},"CM30401"]
["2","03","04","02","","",null,"Linac Beamline Vacuum System",null,"2.03.04.02",null,null,null,"SP30402"]
["2","03","04","03","","",null,"BC1 Vacuum System",null,"2.03.04.03",null,null,null,"SP30403"]
["2","03","04","04","","",null,"BC2 Vacuum System",null,"2.03.04.04",null,null,null,"SP30404"]
["2","03","04","05","","",null,"Linac to Undulator (LTU) Vacuum System",null,"2.03.04.05",null,null,null,"SP30405"]
["2","03","04","06","","",null,"Dumpline Vacuum System",null,"2.03.04.06",null,null,null,"SP30406"]
["2","03","05",{"$nulls":4},"Linac Electron Diagnostics",null,"Summary"]
["2","03","05","01","","",null,"Wire Scanners",null,"2.03.05.01",null,null,null,"SP30501"]
["2","03","05","02","","",null,"Beam Position Monitors",null,"2.03.05.02",null,null,null,"SP30502"]
["2","03","05","03","","",null,"Toroids Beam Charge",null,"2.03.05.03",null,null,null,"SP30503"]
["2","03","05","04","","",null,"Stoppers Tune Up Dump",null,"2.03.05.04",null,null,null,"SP30504"]
["2","03","05","05","","",null,"Profile Monitors",null,"2.03.05.05",null,null,null,"SP30505"]
["2","03","05","06",null,null,null,"Reserved",null,"Summary"]
["2","03","05","07","","",null,"Bunch Length Monitors",null,"2.03.05.07",null,null,null,"SP30507"]
["2","03","05","08","","",null,"Beam Loss Monitors",null,"2.03.05.08",null,null,null,"SP30508"]
["2","03","05","09",null,null,null,"Reserved",null,"Summary"]
["2","03","05","10",null,null,null,"Reserved",null,"Summary"]
["2","03","05","11","","",null,"Protection Collimators",null,"2.03.05.11",null,null,null,"SP30511"]
["2","03","05","12","","",null,"Movable Collimators",null,"2.03.05.12",null,null,null,"SP30512"]
["2","03","05","13","","",null,"Safety Dump",null,"2.03.05.13",null,null,null,"SP30513"]
["2","03","06",{"$nulls":4},"Linac RF Subsystem",null,"Summary"]
["2","03","06","01",null,null,null,"Reserved",null,"Summary"]
["2","03","06","02",null,null,null,"Reserved",null,"Summary"]
["2","03","06","03",null,null,null,"Reserved",null,"Summary"]
["2","03","06","04",null,null,null,"Reserved",null,"Summary"]
["2","03","06","05","","",null,"X-Band High Power System",null,"2.03.06.05",null,null,null,"SP30605"]
["2","03","06","06",null,null,null,"Reserved",null,"Summary"]
["2","03","06","07",null,null,null,"RF Distribution System",null,"Summary"]
["2","03","06","07","01","",null,"Modulator",null,"2.03.06.07.01",null,null,null,"SP3060701"]
["2","03","06","07","02","",null,"Solid State Sub Booster",null,"2.03.06.07.02",null,null,null,"SP3060702"]
["2","03","06","07","05","",null,"Bunch Length Electronics",null,"2.03.06.07.07",null,null,null,"SP3060707"]
["2","03","06","07","07","",null,"RF Distribution L2 & L3",null,"2.03.06.07.07",null,null,null,"SP3060707"]
["2","03","06","07","08","",null,"RF Fiber Optics Electronics",null,"2.03.06.07.08",null,null,null,"SP3060708"]
["2","03","07",{"$nulls":4},"Linac System Commissioning",null,"Summary"]
["2","03","07","01","","",null,"Linac L01 System Commissioning",null,"2.03.07.01",{"$nulls":4},"CM30701"]
["2","03","07","02","","",null,"Linac BC1 System Commissioning",null,"2.03.07.02",{"$nulls":4},"CM30702"]
["2","03","07","03","","",null,"Linac L02 System Commissioning",null,"2.03.07.03",{"$nulls":4},"CM30703"]
["2","03","07","04","","",null,"Linac BC2 System Commissioning",null,"2.03.07.04",{"$nulls":4},"CM30704"]
["2","03","07","05","","",null,"Linac L03 System Commissioning",null,"2.03.07.05",{"$nulls":4},"CM30705"]
["2","03","07","06","","",null,"Linac LTU System Commissioning",null,"2.03.07.06",{"$nulls":4},"CM30706"]
["2","03","07","07","","",null,"Linac E-Dump System Commissioining",null,"2.03.07.07",{"$nulls":4},"CM30707"]
["2","04",{"$nulls":5},"UNDULATOR SYSTEM (OPC)",null,"Summary"]
["2","04","01",{"$nulls":4},"Undulator System Management & Integration",null,"Summary"]
["2","04","02",{"$nulls":4},"Controls",null,"Summary"]
["2","04","02","01",null,null,null,"Controls Management and Integration",null,"Summary"]
["2","04","02","02",null,null,null,"Motion",null,"Summary"]
["2","04","02","03",null,null,null,"Signal Analysis",null,"Summary"]
["2","04","02","04",null,null,null,"Video",null,"Summary"]
["2","04","02","05",null,null,null,"Data Acquisition and Control",null,"Summary"]
["2","04","02","06",null,null,null,"Vacuum",null,"Summary"]
["2","04","02","07","","",null,"Machine Protection",null,"2.04.02.07",null,null,null,"SP40207"]
["2","04","03",{"$nulls":4},"Undulator Magnet & Support",null,"Summary"]
["2","04","03","01",null,null,null,"UND Magnet & Support - Mgmt and Integration",null,"Summary"]
["2","04","03","02",null,null,null,"First Prototype Undulator & Mfg Plan",null,"Summary"]
["2","04","03","03","","",null,"1st Article Undulators & Long Lead Procurements",null,"2.04.03.03",null,null,null,"SP40303"]
["2","04","03","04","","",null,"Production Undulator",null,"2.04.03.04",null,null,null,"SP40304"]
["2","04","03","05","","",null,"Focusing Magnets",null,"2.04.03.05",null,null,null,"SP40305"]
["2","04","03","06","","",null,"Undulator Magnetic Measurement Facility (SLAC)",null,"2.04.03.06",null,null,null,"SP40306"]
["2","04","03","07",null,null,null,"Reserved",null,"Summary"]
["2","04","03","08","","",null,"Fixed Supports",null,"2.04.03.08",null,null,null,"SP40308"]
["2","04","04",{"$nulls":4},"Vacuum System",null,"Summary"]
["2","04","04","01",null,null,null,"Reserved",null,"Summary"]
["2","04","04","02","","",null,"Undulator Vacuum Chamber Assembly",null,"2.04.04.02",null,null,null,"SP40402"]
["2","04","04","03","","",null,"Beam-line Bellows Module Assembly",null,"2.04.04.03",null,null,null,"SP40403"]
["2","04","04","04",null,null,null,"Reserved",null,"Summary"]
["2","04","04","05","","",null,"Short Diagnostic Break (SDB) Assembly",null,"2.04.04.05",null,null,null,"SP40405"]
["2","04","04","06","","",null,"Long Diagnostic Break (LDB) Assembly",null,"2.04.04.06",null,null,null,"SP40406"]
["2","04","04","07","","",null,"Entrance Section Assembly",null,"2.04.04.07",null,null,null,"SP40407"]
["2","04","04","08","","",null,"Exit Section Assembly",null,"2.04.04.08",null,null,null,"SP40408"]
["2","04","04","09",null,null,null,"Reserved",null,"Summary"]
["2","04","05",{"$nulls":4},"Undulator System Diagnostics [OPC]",null,"Summary"]
["2","04","05","01",null,null,null,"Reserved",null,"Summary"]
["2","04","05","02","","",null,"E-Beam and X-Ray Profile Diagnostics",null,"2.04.05.02",null,null,9681254,"SP40502","CM40502"]
["2","04","05","03","","",null,"High-Power X-Ray and Profile Diagnostics (HPD)",null,"2.04.05.03",null,null,9681255,null,"CM40503"]
["2","04","05","04","","",null,"End-of-Undulator(EOU) X-ray and Profile diagnost",null,"2.04.05.04",null,null,9681256]
["2","04","05","05","","",null,"RFBPM",null,"2.04.05.05",null,null,null,"SP40505"]
["2","04","05","06",null,null,null,"Reserved",null,"Summary"]
["2","04","05","07","","",null,"Charge Monitor (CM)",null,"2.04.05.07",null,null,null,"SP40507"]
["2","04","05","08","","",null,"Cherenkov Detector",null,"2.04.05.08",null,null,null,"SP40508"]
["2","04","05","09","","",null,"Radiation Detection Monitor (RDM)",null,"2.04.05.09",null,null,null,"SP40509"]
["2","04","05","10",null,null,null,"Reserved",null,"Summary"]
["2","04","05","11",null,null,null,"Reserved",null,"Summary"]
["2","04","06",{"$nulls":4},"Undulator System Commissioning",null,"Summary"]
["2","04","06","01","","",null,"Undulator System Commissioning",null,"2.04.06.01",{"$nulls":4},"CM40601"]
["2","05",{"$nulls":5},"X-RAY TRANSPORT & DIAGNOSTICS SYSTEMS (OPC)",null,"Summary"]
["2","05","01",{"$nulls":4},"System Management & Integration",null,"Summary"]
["2","05","01","01","","",null,"Management",null,"2.05.01.01",null,null,9681283,null,"CM50101"]
["2","05","02",{"$nulls":4},"Controls",null,"Summary"]
["2","05","02","01",null,null,null,"Reserved",null,"Summary"]
["2","05","02","02",null,null,null,"Slow Controls",null,"Summary"]
["2","05","02","03",null,null,null,"Fast Controls",null,"Summary"]
["2","05","02","04",null,null,null,"Femto Controls",null,"Summary"]
["2","05","03",{"$nulls":4},"Mechanical & Vacuum Subsystem",null,"Summary"]
["2","05","03","01",null,null,null,"Reserved",null,"Summary"]
["2","05","03","02",null,null,null,"Mech/Vac Front End",null,"Summary"]
["2","05","03","03",null,null,null,"Mech/Vac Near Hall",null,"Summary"]
["2","05","03","04",null,null,null,"Mech/Vac Tunnel",null,"Summary"]
["2","05","03","05",null,null,null,"Mech/Vac Far Hall",null,"Summary"]
["2","05","04",{"$nulls":4},"Optical  Subsystem",null,"Summary"]
["2","05","04","01","","",null,"Optical Systems Engineering",null,"2.05.04.01",null,null,9681278]
["2","05","04","02",null,null,null,"Facility Optics",null,"Summary"]
["2","05","04","03",null,null,null,"End Station Optics",null,"Summary"]
["2","05","04","04",null,null,null,"Crystals & Gratings",null,"Summary"]
["2","05","05",{"$nulls":4},"Diagnostics Subsystem",null,"Summary"]
["2","05","05","01",null,null,null,"Reserved",null,"Summary"]
["2","05","05","02","","",null,"Modeling & Simulation",null,"2.05.05.02",null,null,9681284]
["2","05","05","03","","",null,"Facility Diagnostics",null,"2.05.05.03",null,null,null,"SP50503"]
["2","05","05","04","","",null,"Commissioning Diagnostics",null,"2.05.05.04",null,null,"RD50504"]
["2","05","06",{"$nulls":4},"Reserved",null,"Summary"]
["2","05","06","01",null,null,null,"Reserved",null,"Summary"]
["2","06",{"$nulls":5},"X-RAY END STATION SYSTEMS (OPC)",null,"Summary"]
["2","06","01",{"$nulls":4},"Reserved",null,"Summary"]
["2","06","01","01",null,null,null,"Reserved",null,"Summary"]
["2","06","02",{"$nulls":4},"Controls Subsystem",null,"Summary"]
["2","06","02","01","","",null,"Cabling",null,"2.06.02.01",{"$nulls":4},"CM60201"]
["2","06","02","02","","",null,"Network",null,"2.06.02.02",{"$nulls":4},"CM60202"]
["2","06","02","03","","",null,"PC Support",null,"2.06.02.03",{"$nulls":4},"CM60203"]
["2","06","02","04","","",null,"Beamline Controls",null,"2.06.02.04",{"$nulls":4},"CM60204"]
["2","06","02","05","","",null,"X-Ray PPS",null,"2.06.02.05",{"$nulls":4},"CM60205"]
["2","06","02","06","","",null,"X-Ray MPS",null,"2.06.02.06",{"$nulls":4},"CM60206"]
["2","06","02","07","","",null,"Laser PPS",null,"2.06.02.07",{"$nulls":4},"CM60207"]
["2","06","02","08","","",null,"User Safeguards",null,"2.06.02.08",{"$nulls":4},"CM60208"]
["2","06","03",{"$nulls":4},"Mechanical/Vacuum Subsystem",null,"Summary"]
["2","06","03","01",null,null,null,"Reserved",null,"Summary"]
["2","06","03","02","","",null,"Vacuum Components - Mech/Vac",null,"2.06.03.02",{"$nulls":4},"CM60302"]
["2","06","03","03","","",null,"Experimental Chambers",null,"2.06.03.03",{"$nulls":4},"CM60303"]
["2","06","04",{"$nulls":4},"Laser Subsystem",null,"Summary"]
["2","06","04","01","","",null,"Oscillator Laser & Pump",null,"2.06.04.01",{"$nulls":4},"CM60401"]
["2","06","04","02","","",null,"Laser Diagnostics",null,"2.06.04.02",{"$nulls":4},"CM60402"]
["2","06","04","03","","",null,"Laser Supplies & Optical Transport",null,"2.06.04.03",{"$nulls":4},"CM60403"]
["2","06","04","04","","",null,"Laser Timing",null,"2.06.04.04",{"$nulls":4},"CM60404"]
["2","06","04","05","","",null,"Laser Amplifiers",null,"2.06.04.05",{"$nulls":4},"CM60405"]
["2","06","05",{"$nulls":4},"X-Ray Detectors",null,"Summary"]
["2","06","05","01","","",null,"Beam Imaging",null,"2.06.05.01",{"$nulls":4},"CM60501"]
["2","06","05","02","","",null,"2-D X-Ray Detector",null,"2.06.05.02",{"$nulls":4},"CM60502"]
["2","06","05","03","","",null,"Beam Intensity",null,"2.06.05.03",{"$nulls":4},"CM60503"]
["2","06","05","04","","",null,"Streak Camera",null,"2.06.05.04",{"$nulls":4},"CM60504"]
["2","06","06",{"$nulls":4},"X-Ray End Station System Commissioning",null,"Summary"]
["2","06","06","01",null,null,null,"X-Ray End Station System Commissioning",null,"Summary"]
["2","06","07",{"$nulls":4},"Atomic Physics",null,"Summary"]
["2","06","07","01","","",null,"Atomic Physics Samples",null,"2.06.07.01",null,null,"RD60701",null,"CM60701"]
["2","06","07","02","","",null,"Atomic Physics Diagnostics",null,"2.06.07.02",null,null,"RD60702",null,"CM60702"]
["2","06","07","03","","",null,"Atomic Physics Data Analysis",null,"2.06.07.03",null,null,"RD60703",null,"CM60703"]
["2","06","07","04","","",null,"Atomic Physics Detectors",null,"2.06.07.04",null,null,"RD60704",null,"CM60704"]
["2","07",{"$nulls":5},"Reserved",null,"Summary"]
["2","08",{"$nulls":5},"LCLS SYSTEM COMMISSIONING (OPC)",null,"Summary"]
["2","08","01",{"$nulls":4},"Reserved",null,"Summary"]
["2","08","02",{"$nulls":4},"Reserved",null,"Summary"]
["2","08","03",{"$nulls":4},"Reserved",null,"Summary"]
["2","08","04",{"$nulls":4},"Reserved",null,"Summary"]
["2","08","05",{"$nulls":4},"Reserved",null,"Summary"]
["2","08","06",{"$nulls":4},"Reserved",null,"Summary"]
["2","09",{"$nulls":5},"CONVENTIONAL FACILITIES (OPC)",null,"Summary"]
["2","09","01",{"$nulls":4},"Management Integration",null,"Summary"]
["2","09","01","01",null,null,null,"Reserved",null,"Summary"]
["2","09","02",{"$nulls":4},"Reserved",null,"Summary"]
["2","09","03",{"$nulls":4},"Reserved",null,"Summary"]

{"sheet":"ResDes","index":7,"n_rows":149,"n_cols":2,"rows_kept":149,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}
["Resource","Description"]
["AN_ADMN","ANL Administration"]
["AN_AWARD","ANL Award - Commitments"]
["AN_AWRD5","ANL Award - Commitments (no OH)"]
["AN_AWXX","ANL Award - Commitments (no OH)"]
["AN_CCA","ANL Controls: Coordinator Associate"]
["AN_CE","ANL Controls: Engineer"]
["AN_CP","ANL Controls: Programmer"]
["AN_CT","ANL Controls: Technician"]
["AN_EE","ANL Electrical Engineer"]
["AN_KCA","ANL Klystron: Coordinator Associate"]
["AN_KE","ANL Klystron: Engineer"]
["AN_KT","ANL Klystron: Technician"]
["AN_MDD","ANL Mech Drafting / Design"]
["AN_ME","ANL Mechanical Engineer"]
["AN_MES","ANL Metrology: Eng / Surveyors"]
["AN_MFAT","ANL Mech Fab: Assembly Tech"]
["AN_MFMS","ANL Mech Fab: Machine Shop"]
["AN_MFPC","ANL Mech Fab: Plating & Cleaning"]
["AN_MSCS","ANL M&S - Conusmable Supply"]
["AN_MSEG","ANL M&S - Equip Genrl(dsn, s/hdwr, mtrl)"]
["AN_MSEQ","ANL M&S - Equipment (capital, prdn sppt)"]
["AN_MSPS","ANL M&S - Procured Services"]
["AN_MSSC","ANL M&S - Major Subcontracts"]
["AN_MSTR","ANL M&S - Travel"]
["AN_MSXX","ANL M&S - OH Alloc Rate Excluded (no OH)"]
["AN_MTRL","ANL M&S - Raw Material"]
["AN_MTRL5","ANL M&S - Raw Material (no OH)"]
["AN_MTRT","ANL Non-labor: Travel"]
["AN_MVE","ANL AD: Mech / Vacuum Engineer"]
["AN_PCCA","ANL PCD: Coordinator Associate"]
["AN_PCE","ANL PCD: Engineer"]
["AN_PCEF","ANL PCD: Inst-Cabling-Elec Fab"]
["AN_PCT","ANL PCD: Technician"]
["AN_PHPD","ANL Physicist - Post Doc"]
["AN_PHS","ANL Physicist - Scientist"]
["AN_PHSS","ANL Physicist - Senior Scientist"]
["AN_PM","ANL Project Management"]
["AN_SEE","ANL Site Engineering: Engineer"]
["AN_SEL","ANL Site Engineering: Labor"]
["AN_SEPM","ANL Site Engineering: Plant Maint"]
["AN_TMUC","ANL T&M Crafts - Union Carpenter"]
["AN_TMUE","ANL T&M Crafts - Union Electrician"]
["AN_TMUI","ANL T&M Crafts - Union Ironwork"]
["AN_TMUO","ANL T&M Crafts - Union Equip Op"]
["AN_TMUP","ANL T&M Crafts - Union Pipefitter"]
["AN_TMUW","ANL T&M Crafts - Welder"]
["LL_ADMN","LLNL Administration"]
["LL_AWARD","LLNL Award - Commitments"]
["LL_AWRD5","LLNL Award - Commitments (no OH)"]
["LL_AWXX","LLNL Award - Commitments (no OH)"]
["LL_CCA","LLNL Controls: Coordinator Associate"]
["LL_CE","LLNL Controls: Engineer"]
["LL_CP","LLNL Controls: Programmer"]
["LL_CT","LLNL Controls: Technician"]
["LL_EE","LLNL Electrical Engineer"]
["LL_KCA","LLNL Klystron: Coordinator Associate"]
["LL_KE","LLNL Klystron: Engineer"]
["LL_KT","LLNL Klystron: Technician"]
["LL_MDD","LLNL Mech Drafting / Design"]
["LL_ME","LLNL Mechanical Engineer"]
["LL_MES","LLNL Metrology: Eng / Surveyors"]
["LL_MFAT","LLNL Mech Fab: Assembly Tech"]
["LL_MFMS","LLNL Mech Fab: Machine Shop"]
["LL_MFPC","LLNL Mech Fab: Plating & Cleaning"]
["LL_MSCS","LLNL M&S - Consumable Supplies"]
["LL_MSEG","LLNL M&S - Equip Gen (dsn,h/swre,mtrl)"]
["LL_MSEQ","LLNL M&S - Equip (captial, prdn sppt)"]
["LL_MSPS","LLNL M&S - Procured Services"]
["LL_MSSC","LLNL M&S - Major Subcontracts"]
["LL_MSTR","LLNL M&S - Travel"]
["LL_MSXX","LLNL M&S-OH Alloc Rate Excluded (no OH)"]
["LL_MTRL","LLNL M&S - Raw Material"]
["LL_MTRL5","LLNL M&S - Raw Material (no OH)"]
["LL_MVE","LLNL AD: Mech / Vacuum Engineer"]
["LL_PCCA","LLNL PCD: Coordinator Associate"]
["LL_PCE","LLNL PCD: Engineer"]
["LL_PCEF","LLNL PCD: Inst-Cabling-Elec Fab"]
["LL_PCT","LLNL PCD: Technician"]
["LL_PHPD","LLNL Physicist - Post Doc"]
["LL_PHS","LLNL Physicist - Scientist"]
["LL_PHSS","LLNL Physicist - Senior Scientist"]
["LL_PM","LLNL Project Management"]
["LL_PRC","LLNL Precision Crafts (machine tech)"]
["LL_PRE","LLNL Precision Engineer"]
["LL_RP","LLNL Radiation Physicist"]
["LL_SEE","LLNL Site Engineering: Engineer"]
["LL_SEL","LLNL Site Engineering: Labor"]
["LL_SEPM","LLNL Site Engineering: Plant Maint"]
["LL_TMUC","LLNL T&M Crafts - Union Carpenter"]
["LL_TMUE","LLNL T&M Crafts - Union Electrician"]
["LL_TMUI","LLNL T&M Crafts - Union Ironwork"]
["LL_TMUO","LLNL T&M Crafts - Union Equip Op"]
["LL_TMUP","LLNL T&M Crafts - Union Pipefitter"]
["LL_TMUW","LLNL T&M Crafts - Welder"]
["SL_ADMN","SLAC Administration"]
["SL_AWARD","SLAC Award - Commitments"]
["SL_AWRD5","SLAC Award - Commitments (no OH)"]
["SL_AWXX","SLAC Award - Commitments (no OH)"]
["SL_CCA","SLAC Controls: Coordinator Associate"]
["SL_CE","SLAC Controls: Engineer"]
["SL_CP","SLAC Controls: Programmer"]
["SL_CRA","SLAC Computer Resource Associate"]
["SL_CRM","SLAC Computer Resource Manager"]
["SL_CT","SLAC Controls: Technician"]
["SL_EE","SLAC Electrical Engineer"]
["SL_FA","SLAC Financial Analyst"]
["SL_KCA","SLAC Klystron: Coordinator Associate"]
["SL_KE","SLAC Klystron: Engineer"]
["SL_KT","SLAC Klystron: Technician"]
["SL_MDD","SLAC Mech Drafting / Design"]
["SL_ME","SLAC Mechanical Engineer"]
["SL_MES","SLAC Metrology: Eng \\ Surveyors"]
["SL_MFAT","SLAC Mech Fab: Assembly Tech"]
["SL_MFMS","SLAC Mech Fab: Machine Shop"]
["SL_MFPC","SLAC Mech Fab: Plating & Cleaning"]
["SL_MSCS","SLAC M&S - Consumable Supplies"]
["SL_MSEG","SLAC M&S-Equip General (DSN,HW/SW,MTRL)"]
["SL_MSEQ","SLAC M&S - Equip (capital, prdn spprt)"]
["SL_MSPS","SLAC M&S - Procured Services"]
["SL_MSSC","SLAC M&S - Major Subcontract"]
["SL_MSTR","SLAC M&S - Travel"]
["SL_MSXX","SLAC M&S-OH Alloc Rate Excluded (no OH)"]
["SL_MTRL","SLAC M&S - Raw Material"]
["SL_MTRL5","SLAC M&S - Raw Material (no OH)"]
["SL_MVE","SLAC AD: Mech / Vacuum Engineer"]
["SL_OE","SLAC Optics Engineer"]
["SL_OT","SLAC Optics Technician"]
["SL_PCCA","SLAC PCD: Coordinator Associate"]
["SL_PCE","SLAC PCD: Engineer"]
["SL_PCEF","SLAC PCD: Inst-Cabling-Elec Fab"]
["SL_PCT","SLAC PCD: Technician"]
["SL_PHH","SLAC Physicist - Health Scientist"]
["SL_PHPD","SLAC Physicist - Post Doc"]
["SL_PHS","SLAC Physicist - Scientist"]
["SL_PHSS","SLAC Physicist - Senior Scientist"]
["SL_PM","SLAC Project Management"]
["SL_SEE","SLAC Site Engineering: Engineer"]
["SL_SEEM","SSLAC-Site Engrg Mgmt"]
["SL_SEL","SLAC Site Engineering: Labor"]
["SL_SEPM","SLAC Site Engineering: Plant Maint"]
["SL_TMUC","SLAC T&M Crafts - Union Carpenter"]
["SL_TMUE","SLAC T&M Crafts - Union Electrician"]
["SL_TMUI","SLAC T&M Crafts - Union Ironwork"]
["SL_TMUO","SLAC T&M Crafts - Union Equip Op"]
["SL_TMUP","SLAC T&M Crafts - Union Pipefitter"]
["SL_TMUW","SLAC T&M Crafts - Welder"]
["SL_TSM","SLAC Technical System Management"]
["SL_UTR","SLAC UTR"]

{"sheet":"Indirect","index":8,"n_rows":35,"n_cols":4,"rows_kept":35,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}
["SL_ADMN1","SLAC Administration",1.2,1.38]
["SL_CCA11","SLAC Controls: Coord",1.2,1.38]
["SL_CE1","SLAC Controls: Engin",1.2,1.38]
["SL_CP1","SLAC Controls: Progr",1.2,1.38]
["SL_CT1","SLAC Controls: Techn",1.2,1.38]
["SL_EE1","SLAC Electrical Engi",1.2,1.38]
["SL_KCA1","SLAC Klystron: Coord",1.2,1.38]
["SL_KE1","SLAC Klystron: Engin",1.2,1.38]
["SL_KT1","SLAC Klystron: Techn",1.2,1.38]
["SL_MDD1","SLAC Mech Drafting /",1.2,1.38]
["SL_ME1","SLAC Mechanical Engi",1.2,1.38]
["SL_MES1","SLAC Metrology: Eng ",1.2,1.38]
["SL_MFAT1","SLAC Mech Fab: Assem",1.2,1.38]
["SL_MFMS1","SLAC Mech Fab: Machi",1.2,1.38]
["SL_MFPC1","SLAC Mech Fab: Plati",1.2,1.38]
["SL_MSEG1","SLAC M&S-Equip Gener",1.06,1.0552]
["SL_MSEQ1","SLAC M&S - Equip (ca",1.06,1.0552]
["SL_MSPS1","SLAC M&S - Procured ",1.06,1.0552]
["SL_MSSC1","SLAC M&S - Major Sub",1.06,1.0552]
["SL_MSTR1","SLAC M&S - Travel",1.2,1.38]
["SL_MSXX1","SLAC M&S-OH Alloc Ra",1,1]
["SL_MVE1","SLAC AD: Mech / Vacu",1.2,1.38]
["SL_OE1","SLAC Optics Engineer",1.2,1.38]
["SL_OT1","SLAC Optics Technici",1.2,1.38]
["SL_PCCA1","SLAC PCD: Coordinato",1.2,1.38]
["SL_PCE1","SLAC PCD: Engineer",1.2,1.38]
["SL_PCEF1","SLAC PCD: Inst-Cabli",1.2,1.38]
["SL_PCT1","SLAC PCD: Technician",1.2,1.38]
["SL_PHPD1","SLAC Physicist - Pos",1.2,1.38]
["SL_PHS1","SLAC Physicist - Sci",1.2,1.38]
["SL_PHSS1","SLAC Physicist - Sen",1.2,1.38]
["SL_SEE1","SLAC Site Engineerin",1.2,1.38]
["SL_TMUE1","SLAC T&M Crafts - Un",1.2,1.38]
["SL_TMUI1","SLAC T&M Crafts - Un",1.2,1.38]
["SL_PHPU","SLAC NEW",1.2,1.38]