{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":212,"n_cols":9,"rows_kept":212,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[null,null,"Baseline","CR Proposed","Variance"]
["P3 ID","Level 1 DOE (SC1) Milestones"]
["MS1_PM000","CD0 - Approve Mission Need","2001-06-17","6/17/2001A","0 days"]
["MS1_PM005","CD1 - Approve Preliminary Baseline Range","2002-10-16","10/16/2002A","0 days"]
["MS1_PM015","CD2a -  Approve Long-Lead Procurement Budget","2004-07-30","7/30/2004A","0 days"]
["MS1_PM025","CD3a - Approve Start of Long Lead Procurement","2004-10-29","10/29/2004A","0 days"]
["MS1_PM020","CD2b - Approve Performance Baseline","2005-03-31","3/31/2005A","0 days"]
["MS1_PM030","CD3b - Approve Start of Construction","2006-02-28T17:00:00","3/21/2006A","15 days"]
["MS1_PM035","CD4a - Start of Near Hall Operations","NA","2009-07-31","0 days"]
["MS1_PM040","CD4b - Start of Far Hall Ops - Project Complete","2009-03-31","2010-05-31","? days"]
[null,"Level 2 DOE (SSO) Milestones"]
["MS2_LN025","Start Linac (Li20-Li30) Commissioning","2008-03-03T17:00:00","2008-02-04","68 days","q"]
["MS2_UN105","Start Installation of Undulator Facility","2008-05-20T17:00:00","2008-02-04T17:00:00","-97 days","q"]
["MS2_LN110","Start Installation of Beam Transport Hall","2008-05-20T17:00:00","2008-02-04T17:00:00","-97 days","q"]
[null,"Linac ARR (Li20-Li30)  Complete","2008-01-31T17:00:00","2008-04-07T17:00:00","47 days","DELETE","x"]
["MS2_XE060","XE Start Installation in NEH","2008-05-20T17:00:00","2008-09-18","-64 days","q"]
["MS2_XT100","XT Start FEE Installation","2008-05-20T17:00:00","2008-09-22","-97 days","q"]
["MS2_LN032","Linac (Li20-Li30) Commissioning Complete","NEW","2008-09-30T17:00:00","0 days","q"]
["MS2_PM005","Final Safety Analysis Document (FSAD) Approved","2008-03-31T17:00:00","2008-10-15","0 days","Per Dave Schultz",null,"q"]
["MS2_PM030","LCLS ARR Complete (BTH thru FEH)","2008-07-11T17:00:00","2009-02-09","46 days","q"]
["MS2_LN015","Start Linac-to-Undulator (LTU) Commissioning","2008-07-31T17:00:00","2009-02-09","99 days","q"]
["MS2_XE065","AMO Ready for Basic Expmnts (CD4a)","NEW","2009-02-26","0 days","q"]
["MS2_XE015","2-D Detector Shipped to SLAC","2007-12-05T17:00:00","2009-03-13","128 days","q","Desc Change"]
["MS2_UN025","Start Undulator Commissioning (1st Light)","2008-08-18T17:00:00","2009-05-05","85 days","q"]
["MS2_XT005","Start FEE Commissioning with Beam","2008-10-08T17:00:00","2009-05-05","302 days","q","Desc Change"]
["MS2_XE050","XE Start Installation in FEH","2008-08-20T17:00:00","2009-09-01","-87 days","q"]
["MS2_XE005","First X-Rays into NEH","2008-10-02T17:00:00","2009-07-13","104 days","q","Desc Change"]
["MS2_XT050","XT Start Tunnel Installation","2008-08-20T17:00:00","2009-08-12","-139 days","q"]
["MS2_XT075","First X-Rays into FEH","NEW","2010-04-08","353 days","q"]
["MS2_IJ0010","Start Injector Commissioning (Drive Laser)","2007-01-29T17:00:00","1/16/2007A","-9 days","x"]
["MS2_IJ0027","Injector Laser Commissioning Review Complete","2007-01-31T17:00:00","12/1/2006A","-34 days","x"]
["MS2_PM055","Prelim Safety Assessment (PSAD) Doc Approved","2006-02-28T17:00:00","2/28/2006A","0 days","x"]
["MS2BO_020","Linac Water/Power Available","2007-07-11T17:00:00","3/29/2007A","-74 days","x"]
["MS2_IJ0030","Injector Accelerator Readiness Review (ARR) Comp","2007-01-31T17:00:00","3/30/2007A","42 days","x"]
["MS2BO_005","Sector 20/Alcove Beneficial Occupancy","2006-07-21T17:00:00","4/14/2006A","-70 days","x"]
["MS2_PM045","Prelim Safety Assessment (PSAD) Doc Complete","2004-04-30T17:00:00","4/30/2004A","0 days","x"]
["MS2_IJ0020","Start Injector Commissioning(UV Beam to Cathode)","2007-04-09T17:00:00","4/5/2007A","0 days","x"]
["MS2_PM035","DOE External Independent Review (EIR) Complete","2004-06-15T17:00:00","6/15/2004A","0 days","x"]
["MS2_UN010","Delivery of Undulator 1st Articles to MMF","2006-07-03T17:00:00","6/15/2006A","-12 days","x"]
["MS2_PM040","Fire Hazard Analysis Approved","2005-06-30T17:00:00","8/15/2005A","32 days","x"]
["MS2_UN005","MMF Qualified & Ready to Measure Prod Undulators","2006-11-27T17:00:00","8/28/2006A","-65 days","x"]
["MS2BO_025","Research Yards Mods Beneficial Occupancy","2006-10-20T17:00:00","8/30/2006A","-37 days","x"]
[null,"Level 3 SLAC (LCLS PO) Milestones"]
[null,"Injector System (WBS 1.02)"]
["MSC_IJ000","CRIT: Release RFP for Drive Laser","2004-10-15","10/15/2004A","0 days","q","Add to M?S Project?"]
["MS3_IJ095","Award of Drive Laser Contract Complete","2005-06-30T17:00:00","6/30/2005A","0 days","q"]
[null,"Wall Region Installation Complete","2005-12-16T17:00:00","2005-12-16T17:00:00","0 days","?","Not in P3 or dictionary: Delete from M/S Project"]
["MS3_IJ032","Laser Tables & Optical Paths Installation Comp","2006-08-21T17:00:00","8/1/2006A","-14 days","q"]
["MS3_IJ005","Drive Laser Available for Integration","2006-11-16T17:00:00","11/30/2006A","-23 days","q"]
[null,"Heater Region Installation Complete","2006-12-07T17:00:00","2006-12-30T17:00:00","9 days","?","Not in P3 or dictionary: Delete from M/S Project"]
["MS3_IJ0010","Start Injector Commissioning (Drive Laser)","2006-12-14T17:00:00","1/16/2007A","14 days","q"]
["MS3_IJ0027","Injector Laser Commissioning Review Complete","2006-12-14T17:00:00","11/30/2006A","-10 days","q"]
["MS3_IJ0030","Injector Accelerator Readiness Review (ARR) Comp","2006-12-15T17:00:00","3/30/2007A","66 days","x"]
["MS3_IJ085","Accelerator Region Installation Complete","2007-01-29T17:00:00","12/30/2006A","-19 days","x"]
["MS3_IJ080","Gun Region Installation Complete","2007-01-29T17:00:00","3/30/2007A","44 days","x"]
["MS3_IJ110","Injector RF Subsystem Installation Complete","2007-01-31T17:00:00","3/30/2007A","42 days","x"]
["MS3_CT070","Injector Controls Installation Complete","2007-01-02T17:00:00","3/16/2007A","52 days","x"]
["MS3_IJ105","Spectrometer Installation Complete","2007-02-02T17:00:00","3/30/2007A","40 days","x"]
["MS3_IJ125","RF Gun Ready for Installation","2007-02-15T17:00:00","12/1/2006A","-45 days","x"]
["MS3_IJ100","Insertion Region Installation Complete","2007-02-08T17:00:00","12/30/2006A","-27 days","x"]
["MS3_IJ0020","Start Injector Commissioning(UV Beam to Cathode)","2007-03-06T17:00:00","4/5/2007A","0 days","x"]
["MS3_IJ120","Laser Heater Installation Complete","2008-01-02T17:00:00","2008-11-21T17:00:00","230 days","q"]
[null,"Linac System (WBS 1.03)"]
["MSC_LN005","CRIT: Release RFP X-Band Klystron","2005-02-25T17:00:00","2/25/2005A","0 days","x"]
["MSBS_090","Shutdown of FFTB Operations","2006-06-01T17:00:00","4/10/2006A","-38 days","x"]
["MS3_LN016","BC1 Bend Magnet Ready for Installation","2006-11-13T17:00:00","9/29/2006A","-31 days","x"]
["MS3_LN010","X-Band Klystron Ready for Installation","2006-11-27T17:00:00","8/31/2006A","-62 days","x"]
["MS3_LN012","BC1 Installation Complete","2007-01-29T17:00:00","1/31/2007A","2 days","x"]
["MS3_CT072","Linac Controls Ready for BC1 Commissioning","2007-01-31T17:00:00","3/16/2007A","32 days","x","Desc Change: is this documented?"]
["MS3_LN013","Start BC1 Commissioning","2007-02-28T17:00:00","3/30/2007A","22 days","x"]
["MS3_LN030","Linac Commissioning Review Complete - S20-30","2007-11-05T17:00:00","2008-01-03","-198 days","x"]
[null,"Linac ARR (Li20-Li30)  Complete","2007-12-03T17:00:00",null,"59 days","DELETE"]
["MS3_CT075","Linac Controls Ready for BC2 Commissioning","2007-12-03T17:00:00",null,"100 days","DELETE","x","Still in CRFN….Do we want to delete?"]
["MS3_LN011","BC2 Installation Complete","2008-01-02T17:00:00","2008-01-02T17:00:00","0 days","q"]
["MS3_LN025","Start Linac (Li20-Li30) Commissioning","2008-02-01T17:00:00","2008-01-07T17:00:00","66 days","q"]
["MS3_CT080","Linac Controls Ready for LTU Installation","2008-03-03T17:00:00",null,"42 days","DELETE","x","Still in CRFN….Do we want to delete?"]
["MS3_LN055","E-Dump Component Installation Complete","2008-03-26T17:00:00","2008-08-15","147 days","q"]
["MS3_LN035","LTU Component Installation Complete","2008-03-26T17:00:00","2008-10-03","175 days","q"]
["MS3_LN032","Linac Commissioning Review Complete - LTU","2008-03-31T17:00:00","2009-01-07","120 days","q"]
["MS3_LN015","Start Linac-to-Undulator (LTU) Commissioning","2008-06-30T17:00:00","2009-01-08","100 days","q"]
[null,"Undulator System (WBS 1.04)"]
["MSC_UN005","CRIT: Release RFP Ti Strongback","2005-01-14T17:00:00","1/14/2005A","0 days","x"]
["MSC_UN015","CRIT: Release RFP Magnet Poles","2005-02-04T17:00:00","2/4/2005A","0 days","x"]
["MSC_UN010","CRIT: Release RFP  Magnet Blocks","2005-03-23T17:00:00","3/23/2005A","0 days","x"]
["MSC_UN020","CRIT: Release RFP Magnet Assemblies - 1st Art","2005-06-28T17:00:00","6/28/2005A","0 days","x"]
["MS3_UN028","Award of 1st Articles Mag Assy to Vendors Comp","2005-10-11T17:00:00","10/4/2005A","-5 days","x"]
["MSC_UN016","CRIT: Release RFP - Quadrupoles","2006-04-12T17:00:00","6/14/2006A","45 days","x"]
["MS3_UN018","Undulator SUT Completed","2006-04-28T17:00:00","7/19/2006A","58 days","x"]
["MSC_UN030","CRIT: Release RFP - Fixed Supports","2006-05-09T17:00:00","5/9/2006A","0 days","x"]
["MS3_UN006","1st Article Vendor A Undulator 1 Rcvd @ SLAC","2006-06-02T17:00:00","3/30/2006A","-46 days","x"]
["MS3_UN010","1st Article Vendor B Undulator 2 Rcvd @ SLAC","2006-06-02T17:00:00","6/15/2006A","9 days","x"]
["MS3_UN005","MMF Qualified & Ready to Measure Prod Undulators","2006-10-27T17:00:00","8/28/2006A","-44 days","x"]
["MS3_UN015","25% production undulators received","2007-01-02T17:00:00","8/28/2006A","-83 days","x"]
["MS3_UN022","50% production undulators received","2007-03-19T17:00:00","12/21/2006A","-54 days","x"]
["MS3_UN027","75% production undulators received","2007-06-07T17:00:00","1/31/2007A","-91 days","x"]
["MS3_UN029","Undulator Production Units (33) Received","2007-07-06T17:00:00","4/30/2007A","-49 days","DONE","x"]
["MS3_UN040","Hydrostatic Level System Complete","2008-05-28T17:00:00","8/8/2008?","-149 days","Per Rodd",null,"NO!"]
["MS3_CT085","Undulator Controls Ready for Commissioning","NEW","2008-04-28","0 days","x"]
["MS3_UN042","Wire Monitoring System Complete","2008-05-28T17:00:00","8/8/2008?","52 days","Change to Level 4",null,"NO!","Date not correct?"]
["MS3_UN050","Electrons Available to Undulator","2008-05-08T17:00:00","2009-03-04","100 days","Delete",null,"DELETE"]
["MS3_UN020","Undulator System Installation Complete","2008-05-28T17:00:00","2008-11-14","122 days","x"]
["MS3_UN025","Start Undulator Commissioning (1st Light)","2008-07-18T17:00:00","2009-04-06","85 days","x",null,"Edit dictionary and/or title"]
["MS3_UN030","1st production vacuum chamber delivered to SLAC","New","2008-01-02","85 days"]
["MS3_UN035","1st production Undulator RFBPM delivered to SLAC","New","2008-04-04","85 days"]
["MS3_UN045","1st production BFW delivered to SLAC","New","2007-11-17","85 days"]
[null,"X-Ray Transport & Diagnostics  (WBS 1.05)"]
["MS3_XT007","Tunnel Mech/Vac Design Review Complete","2006-11-29T17:00:00","11/14/2006A","-11 days","x"]
[null,"Gas Attenuator Design Review Complete","2007-03-30T17:00:00","2007-07-11T17:00:00","73 days","DELETE",null,"Do not Delete"]
[null,"Low Energy Spectral Measurement Design Complete","2007-04-23T17:00:00","2007-11-26T17:00:00","155 days","DELETE",null,"Replace"]
[null,"Far Hall Mech/Vac Design Review Complete","2007-05-23T17:00:00","2007-09-27T17:00:00","91 days","DELETE"]
["MS3_XT040","AWARD: LE Mirror Substrate","NEW","2007-07-31"]
["MS3_XT060","AWARD: HE Mirror Substrate","NEW","2007-11-16"]
["MS3_XT030","Fixed Mask Ready to Ship to SLAC","2007-07-30T17:00:00","2007-12-14T17:00:00","99 days","x"]
["MS3_XT025","Gas/Solid Attenuator Ready to Ship to SLAC","2007-10-29T17:00:00","2008-02-15T17:00:00","70 days","x"]
["MS3_XT100","XT Start FEE Installation","2007-12-04T17:00:00","2008-08-21","14 days","x","Desc Change"]
["MS3_XT050","XT Start Tunnel Installation","NEW","2009-07-13","14 days","x"]
[null,"Solid Attenuator Installation Complete","2007-12-14T17:00:00","2007-12-14T17:00:00","0 days","DELETE"]
[null,"Gas/Solid Attenuator Installation Complete","2008-04-04T17:00:00","2008-11-13T17:00:00","159 days","DELETE"]
[null,"Total Energy Measurement  Installation Complete","2008-04-10T17:00:00","2008-11-13T17:00:00","155 days","DELETE"]
["MS3_XT071","XT Tunnel/ FEH  Install/Check Complete","2008-05-13T17:00:00","2010-01-11","353 days","x","Desc Change"]
[null,"Start Far Experimental Hall Checkout","2008-06-03T17:00:00","2009-11-05T17:00:00","361 days","DELETE"]
["MS3_XT000","FEE Install/Check Complete","2008-08-14T17:00:00","2009-02-09","65 days","x","Desc Change"]
["MS3_XT005","Start FEE Commissioning with Beam","2008-09-08T17:00:00","2009-04-06","79 days","x","Desc Change"]
[null,"Start Near Experimental Hall Checkout","2008-08-26T17:00:00","2009-01-12T17:00:00","88 days","DELETE"]
[null,"Start XTOD Commissioning","2008-09-08T17:00:00","2009-11-05T17:00:00","292 days","DELETE"]
["MS3_XT075","First X-Rays into FEH","NEW","2010-03-08","353 days"]
[null,"Conventional Facilities (WBS 1.09)"]
["MS3_CF000","A&E Serv (S20, MMF, MCC not incl) Title 1 Comp","2004-04-30T17:00:00","4/30/2004A","0 days","x"]
["MS3_CF002","A&E Serv Sector 20 Title 1 Complete","2004-04-30T17:00:00","4/30/2004A","0 days","x"]
["MS3_CF022","A&E Services MMF Title 1 Complete","2004-04-30T17:00:00","4/30/2004A","0 days","x"]
["MS3_CF010","A&E Services Sector 20 Title 2 Complete","2005-03-18T17:00:00","3/18/2005A","0 days","x"]
["MSC_CF005","CRIT: Rel RFP T3 Const. Pkg. RF Hut & S20/Alcove","2005-04-01T17:00:00","4/1/2005A","0 days","x"]
["MSC_CF010","CRIT: Release RFP T3 Construction Contract (MMF)","2005-04-14T17:00:00","4/14/2005A","0 days","x"]
["MS3_CF015","A&E Services MMF Title 2 Complete","2005-05-31T17:00:00","5/31/2005A","0 days","x"]
["MSC_CF020","CRIT:  Release RFP Constructrion Mgmt Pkg (CM)","2005-07-25T17:00:00","7/25/2005A","0 days","x"]
["MS3_CF065","Award of Sector 20 Title 3 Complete","2005-08-05T17:00:00","7/28/2005A","-6 days","x"]
["MS3_CF066","Award of Magnetic Msmt Facility Title 3 Complete","2005-08-05T17:00:00","7/28/2005A","-6 days","x"]
["MS3_CF060","Award of Construction Management Package - Ph.1","2005-09-30T17:00:00","10/17/2005A","11 days","x"]
["MSBO_000","RF Hut Beneficial Occupancy","2005-12-07T17:00:00","3/9/2006A","56 days","x"]
["MS3_CF005","A&E Serv (S20, MMF, MCC not incl) Title 2 Comp","2006-01-20T17:00:00","2/28/2006A","27 days","x"]
["MSC_CF000","CRIT:  Release RFP T3 Construct (RY-CLOC)","2006-01-26T17:00:00","3/8/2006A","29 days","x"]
["MSBO_010","Magnetic Msmt Facility(MMF) Beneficial Occupancy","2006-04-03T17:00:00","3/29/2006A","-3 days","x"]
["MS3BO_005","Sector 20 Alcove Beneficial Occupancy","2006-06-21T17:00:00","4/14/2006A","-48 days","x"]
["MSC_CF006","CRIT:  Release RFP T3 Construction Pkg (Linac)","2006-07-10T17:00:00","7/31/2006A","15 days","x"]
["MS3BO_025","Research Yards Mods Beneficial Occupancy","2006-09-21T17:00:00","8/30/2006A","-16 days","x"]
["MS3BO_020","Linac Power/Water Available","2007-06-11T17:00:00","3/29/2007A","-52 days","x"]
["MS3CO_015","Front End Enclosure Co-Occupancy","2007-12-04T17:00:00","2007-12-04T17:00:00","0 days","x"]
["MS3CO_005","Beam Transport  Hall Co-Occupancy","2007-12-04T17:00:00","2007-12-04T17:00:00","0 days","x"]
["MS3CO_010","Undulator Facility Co-Occupancy","2007-12-04T17:00:00","2007-12-04T17:00:00","0 days","x"]
["MS3CO_035","Beam Dump Co-Occupancy","2007-12-04T17:00:00","2007-12-04T17:00:00","0 days","x"]
["MS3CO_040","Central Utility Plant Co-Occupancy","2007-12-20T17:00:00","2007-12-20T17:00:00","0 days","x"]
["MS3CO_020","Near Experimental Hall Co-Occupancy","2007-12-20T17:00:00","2007-12-20T17:00:00","0 days","x"]
["MS3CO_025","X-Ray Transport Co-Occupancy","2008-01-07T17:00:00","2008-01-07T17:00:00","0 days","x"]
["MS3BO_035","Undulator Facility Beneficial Occupancy","2008-03-20T17:00:00","2008-03-20T17:00:00","0 days","x"]
["MS3BO_050","Near Experimental Hall Beneficial Occupancy","2008-03-20T17:00:00","2008-03-20T17:00:00","0 days","x"]
["MS3BO_040","Front End Enclosure Beneficial Occupancy","2008-03-20T17:00:00","2008-03-20T17:00:00","0 days","x"]
["MSBO_045","Beam Dump Beneficial Occupancy","2008-03-20T17:00:00","2008-03-20T17:00:00","0 days","x"]
["MS3BO_065","Central Utility Plant Beneficial Occupancy","2008-03-20T17:00:00","2008-03-20T17:00:00","0 days","x"]
["MS3BO_030","Beam Transport Hall Beneficial Occupancy","2008-03-20T17:00:00","2008-03-20T17:00:00","0 days","x"]
["MS3CO_030","Far Experimental Hall Co-Occupancy","2008-03-21T17:00:00","2008-03-21T17:00:00","0 days","x"]
["MS3BO_070","CEH Building Beneficial Occupancy","2008-04-26T17:00:00","2009-07-16","0 days","x"]
["MS3BO_060","Far Experimental Hall Beneficial Occupancy","2008-06-20T17:00:00","2008-06-20T17:00:00","0 days","x"]
["MS3BO_055","X-Ray Transport Beneficial Occupancy","2008-06-20T17:00:00","2008-06-20T17:00:00","0 days","x"]
["MS3BO_075","B028 Beneficial Occupancy","2008-11-12T17:00:00","2009-05-05","0 days","x",null,null,"New Date"]
["MS3BO_080","FEH Hutches Beneficial Occupancy","NEW","2009-07-01","0 days","x","2009-06-01",null,"Change date?"]
[null,"X-Ray Endstations (WBS 1.06)"]
["MS3_XE030","Complete 2-D X-Ray Detector Statement of Work","2005-07-01T17:00:00","5/16/2005A","-34 days","x"]
["MS3_XE035","Award Initial Funding for 2-D X-Ray Detector","2005-07-15T17:00:00","7/15/2005A","0 days","x"]
["MS3_XE110","Hire Atomic Physicist","2006-03-17T17:00:00","1/3/2006A","-52 days","x"]
["MS3_XE100","Hire Detector Physicist","2006-04-03T17:00:00","1/17/2006A","-54 days","x"]
["MS3_XE090","Specification for Streak Camera Complete","2006-04-03T17:00:00","5/30/2006A","-54 days","DELETE",null,null,"In P3 not this list"]
["MS3_XE040","LDAC Mid-Project Review (2D Detector)","2007-03-19T17:00:00","2007-11-30T17:00:00","184 days","x"]
["MS3_XE020","COMP: AMO PDR Meeting","NEW","2007-08-31","184 days","x"]
[null,"XE Network Design Review Complete","2007-04-27T17:00:00","2007-08-16T17:00:00","79 days","DELETE",null,null,"Add one more"]
[null,"XES Timing Controls System Complete","2007-05-30T17:00:00","2008-02-14T17:00:00","177 days","DELETE"]
[null,"XES Cables and Racks Complete","2007-05-30T17:00:00","2008-01-14T17:00:00","154 days","DELETE"]
[null,"XES Laser Control System Complete","2007-07-17T17:00:00","2008-02-14T17:00:00","143 days","DELETE"]
[null,"XE Laser System Final Design Review Complete","2007-08-07T17:00:00","2008-01-04T17:00:00","99 days","DELETE"]
["MS3_XE025","Award XES Laser System","2007-10-04T17:00:00","2008-03-20T17:00:00","111 days","x"]
["MS3_XE130","FEE/NEH PPS Certified","2007-10-04T17:00:00","2009-02-23","312 days","x","Desc Chng"]
["MS3_XE150","TUN/FEH PPS Certified","NEW","2010-02-05","312 days","x"]
["MS3_XE015","2-D Detector Shipped to SLAC","2007-11-05T17:00:00","2009-02-13","128 days","x","Desc Chng"]
["MS3_XE050","XE Start Installation in FEH","2008-08-20T17:00:00","2009-08-03","-87 days","x"]
[null,"Final Design Review AMO Experimental Control Complete","2007-12-14T17:00:00","2008-02-29T17:00:00","46 days","DELETE"]
[null,"Network Installation Complete","2008-03-06T17:00:00","2009-08-24T17:00:00","371 days","DELETE"]
["MS3_XE120","Electron Dump Stoppers Certified","2008-03-25T17:00:00","2009-01-08","132 days","x"]
["MS3_XE060","XE Start Installation in NEH","2008-04-16T17:00:00","2008-08-18","52 days","x"]
[null,"AMO Mechanical & Vacuum Installation Complete","2008-05-13T17:00:00","2008-09-15T17:00:00","89 days","DELETE"]
[null,"XES Controls Laser Timing System Complete","2008-05-29T17:00:00","2008-06-27T17:00:00","21 days","DELETE"]
["MS3_XE005","First X-Rays into NEH","2008-09-02T17:00:00","2009-06-15","106 days","x","Desc Chng"]
["MS3_XE080","XES Laser Operating in Near Hall","2008-09-19T17:00:00","2008-11-24","6 days","x"]
[null,"Complete Acceptance Tests for X-Ray Detectors","2008-11-17T17:00:00","2009-04-03T17:00:00","88 days","DELETE"]
["MS3_XE065","AMO Ready for Basic Expmnts (CD4a)","NEW","2009-01-26","0 days","x"]
[null,"Project Management (WBS 1.01)"]
["MS3_PM025","Advanced Procurement Management Plan Complete","2004-02-28T08:00:00","2/28/2004A","0 days","x"]
["MS3_PM031","Resource Loaded Cost & Schedule (Final) Complete","2004-04-30T17:00:00","4/30/2004A","0 days","x"]
["MS3_PM035","1st Monthly Report (with Earned Value) Submitted","2004-04-30T17:00:00","4/30/2004A","0 days","x"]
["MS3_PM042","Risk Management Plan Complete","2004-04-30T17:00:00","4/30/2004A","0 days","x"]
["MS3_PM045","Prelim Safety Assessment Doc (PSAD) Submitted","2004-04-30T17:00:00","4/30/2004A","0 days","x"]
["MS3_PM050","Project Mgmt Control Syst (PMCS) Review Complete","2004-04-30T17:00:00","4/30/2004A","0 days","x"]
["MS3_PM055","Project Mgmt Plan Complete","2004-04-30T17:00:00","4/30/2004A","0 days","x"]
["MS3_PM000","CRIT: Start Procurement Package - PMCS Support","2004-10-01T17:00:00","10/1/2004A","0 days","x"]
["MS3_PM040","Fire Hazard Analysis Review @ SLAC","2005-06-10T17:00:00","7/15/2005A","25 days","x"]
["MSBS_115","FY05 Shutdown: HW Reqd for Installation","2005-10-03T17:00:00","10/3/2005A","0 days","x"]
["MSBS_120","FY05 Shutdown Over","2005-10-31T17:00:00","10/31/2005A","0 days","x"]
["MSBS_125","FY06 Shutdown: HW Reqd for Installation","2006-08-01T17:00:00","8/21/2006A","14 days","x"]
["MSBS_130","FY06 Shutdown Over","2007-01-05T17:00:00","3/29/2007A","0 days","x"]
["MSBS_135","FY07 Shutdown: HW Reqd for Installation","2007-09-04T17:00:00","2007-09-04T17:00:00","0 days","x"]
["MSBS_140","FY07 Shutdown Over","2007-11-30T17:00:00","2007-12-03T17:00:00","0 days","x"]
["MS3_PM030","LCLS ARR Complete (BTH thru FEH)","2008-06-12T17:00:00","2009-01-08","0 days","x"]
["MSBS_145","Start FY08 Shutdown","2008-09-12T17:00:00","2008-10-01","0 days","x"]
["MSBS_150","FY08 Shutdown Over","2009-01-02T17:00:00","2008-11-03","0 days","x"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}