{"text_format":"2","workbook":"xls","n_sheets":2,"sheets":["Rules","Milestones"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":5,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Rules","index":0,"n_rows":35,"n_cols":2,"rows_kept":35,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["Milestone Rules"]
[]
["1.","Level 2 Milestones are DOE Milestones.  They are fed by the Level 3 Milestones which are Project Milestones.  "]
[null,"The Level 2 Milestones have no successors."]
[null,"The Level 2 Milestones are constrained with mandatory constraints that are set 20 working days after the corresponding Level 3 Milestone."]
[null,"The constraints are applied based on the dates calculated by P3 in a completely unconstrained database, except for Shutdown constraints."]
[]
["2. ","Level 3 Milestones are Project Milestones.  They consist of duplicates of the Level 2 Milestones plus additional Milestones as  "]
[null,"deemed necessary by Project Management."]
[null,"The Level 3 Milestones are fed by the lower level system activities (AVAIL:) or Level 4 System Milestones.  "]
[null,"Most all of the Level 3 Milestones are constrained with manadatory constraints that are set 40 working days after the predecessor (system activity) date."]
[null,"The only Level 3 Milestones that are not constrained, are the CRIT: Milestones.  They are preceded by the Release of the RFP and will be mandatorily"]
[null,"constrained to the RFP Release date that appears in the APP when it is written.  Until the APP is written there is no constraint applied."]
[]
["3.","Level 4 Milestones are System Milestones.  They consist of milestones identified by the System Manager in support of the "]
[null,"Level 3 Milestones.  They are constrained at the discretion of the System Manager."]
[]
["4.","Interface Milestones are defined as handoffs from one System to another and are represented in the P3 database by a pair of"]
[null,"milestones (AVAIL: and REQD:).  The AVAIL: milestone from one system will feed a REQD: milestone in the receiving system."]
[]
["5.","Funding Milestones are set in the database to represent the availability of  funding.  Key funding milestones are:"]
[null,"a. The availability of Construction funding (FY06)"]
[null,"b. The availability of Spares funding (FY07)"]
[null,"c. The availability of Long Lead Procurement Funding (FY05)"]
[]
["6.","\"Swing Procurement\" milestones have been added that allows us to constrain the procurements with greater than 2 years of float to later dates"]
[null,"without effecting the critical path."]
[null,"This constraint is used to help manage the yearly funding profile and available contingency."]
[]
["7.","Shutdown Milestones are set to manage the activity that must take place in the Accelerator during the yearly shutdown period.  "]
[null,"These Shutdown Milestones are represented by two milestones and have mandatory constraints:"]
[null,"a. A \"H/W Required for Installation\" milestone represents the start of the Shutdown period and is fed by the delivery of the equipment that"]
[null,"   needs to be installed during that shutdown."]
[null,"b. A \"Shutdown Completed\" milestone is represents the end of the Shutdown period and is fed by the activities that need to be accomplished during the"]
[null,"   shutdown."]

{"sheet":"Milestones","index":1,"n_rows":192,"n_cols":6,"rows_kept":192,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["MS #","MS ID","Milestone Title","Baseline Date","Act","Milestone Completion Criteria"]
["Level 1 Milestones"]
[1,"MS1_PM000","CD0 - Approve Mission Need","2001-06-17","A","Completion of this milestone is defined as an approved Decision document signed by the Acquisition Executive (SC-1) from DOE."]
[2,"MS1_PM005","CD1 - Approve Preliminary Baseline Range","2002-10-16","A","Completion of this milestone is defined as an approved Decision document signed by the Acquisition Executive (SC-1) from DOE."]
[3,"MS1_PM015","CD2a -  Approve Long-Lead Procurement Budget","2004-07-30","A","Completion of this milestone is defined as an approved Decision document signed by the Acquisition Executive (SC-1) from DOE."]
[4,"MS1_PM025","CD3a - Approve Start of Long Lead Procurement","2004-10-29","A","Completion of this milestone is defined as an approved Decision document signed by the Acquisition Executive (SC-1) from DOE."]
[5,"MS1_PM020","CD2b - Approve Performance Baseline","2005-03-31","A","Completion of this milestone is defined as an approved Decision document signed by the Acquisition Executive (SC-1) from DOE."]
[6,"MS1_PM030","CD3b - Approve Start of Construction","2006-03-21","A","Completion of this milestone is defined as an approved Decision document signed by the Acquisition Executive (SC-1) from DOE."]
[7,"MS1_PM035","CD4a - Start of Near Hall Operations","2009-07-31",null,"All capital facilities installed to demonstrate detection of X-rays in the Near Experimental Hall, and demonstrate a single-pulse x-ray spectral flux density of at least 106 photons/(mm2 *0.1%BW) measured in the FEE. "]
[8,"MS1_PM040","CD4b - Start of Far Hall Ops - Project Complete","2010-05-31",null,"All additional capital facilities installed to demonstrate that the X-ray Transport Tunnel, Far Experiment Hall (FEH), and all associated technical systems in the Project scope have been installed . Detection of x-rays in the FEH will confirm that these systems are functional.\n"]
["Level 2 Milestones"]
["Program Management"]
[9,"MS2_PM045","Prelim Safety Assessment (PSAD) Doc Complete","2004-04-30","A","This milestone is complete when the DOE Stanford Site Office has received the PSAD report from LCLS.  "]
[10,"MS2_PM035","DOE External Independent Review (EIR) Complete","2004-06-15","A","This milestone is complete when the LCLS team has conducted an External Independent Review (EIR) of the LCLS."]
[11,"MS2_PM040","Fire Hazard Analysis Approved","2005-08-30","A","This milestone is complete when the DOE Stanford Site Office accepts the FHA report and issues their acceptance letter.  "]
[12,"MS2_PM055","Prelim Safety Assessment (PSAD) Doc Approved","2006-02-28","A","This milestone is complete when the DOE Stanford Site Office accepts the PSAD report and issues their acceptance letter.  "]
[13,"MS2_PM005","Final Safety Analysis Document (FSAD) Approved","2008-10-15",null,"This milestone is complete when the DOE Stanford Site Office accepts the FSAD report and issues their acceptance letter.  "]
[14,"MS2_PM030","LCLS ARR Complete ","2009-02-09",null,"This milestone is complete when the DOE Stanford Site Office accepts the ARR report and issues a letter authorizing operation.  "]
["Injector System"]
[15,"MS2_IJ0027","Injector Laser Commissioning Review Complete","2007-01-31","A","This milestone establishes the plan for commissioning the Injector Laser."]
[16,"MS2_IJ0010","Start Injector Commissioning (Drive Laser)","2007-01-29","A","This milestone is complete when the Injector Drive Laser is installed and commissioning of the drive laser begins."]
[17,"MS2_IJ0030","Injector Accelerator Readiness Review (ARR) Comp","2007-01-31","A","This milestone is complete when the DOE Stanford Site Office accepts the ARR report and issues a letter authorizing operation.  "]
[18,"MS2_IJ0020","Start Injector Commissioning(UV Beam to Cathode)","2007-04-09","A","This milestone is complete when the first UV beam from the drive laser is sent to the gun photocathode."]
["Linac System"]
[19,"MS2_LN025","Start Linac (Li20-Li30) Commissioning","2008-02-04",null,"This milestone starts commissioning of the Linac from Sector 20 through Sector 30 including BC1 and BC2."]
[20,"MS2_LN015","Start Linac-to-Undulator (LTU) Commissioning","2009-02-09",null,"This milestone is complete when electrons are delivered to LTU and LTU systems are first activated."]
[21,"MS2_LN110","Start Installation of Beam Transport Hall","2008-02-04",null,"This milestone is complete when the LCLS CF group can release the facility for use by the system end user."]
[22,"MS2_LN032","Linac (Li20-Li30) Commissioning Complete","2008-09-30",null,"This milestone is complete when the beam has been brought through BC2 to the end of Linac Sector 30, with BC2 and all major diagnostics operational. \n"]
["Undulator System"]
[23,"MS2_UN010","Delivery of Undulator 1st Articles to MMF","2006-07-03","A","This milestone is complete when the undulator 1st articles have been received at SLAC."]
[24,"MS2_UN005","MMF Qualified & Ready to Measure Prod Undulators","2006-11-27","A","This milestone marks the successful commissioning of the MMF, incl. the completion of the calibration of the test stands, and the acceptance sign-off by the APS project physicist."]
[25,"MS2_UN025","Start Undulator Commissioning (1st Light)","2009-05-05",null,"1st beam through the undulator system with the undulators rolled in."]
[26,"MS2_UN105","Start Installation of Undulator Facility","2008-02-04",null,"This milestone is complete when the LCLS CF group can release the facility for use by the system end user."]
["X-Ray Transport, Optics and Diagnostics System"]
[27,"MS2_XT005","Start FEE Commissioning with Beam","2009-05-05",null,"This milestone is complete when x-rays are first delivered into the FEE."]
[28,"MS2_XT100","XT Start FEE Installation","2008-09-22",null,"This milestone is complete when the XTOD group begins installation of equipment in the FEE."]
[29,"MS2_XT050","XT Start Tunnel Installation","2009-08-12",null,"This milestone is complete when the XTOD group begins installation of beam transport equipment in the X-ray transport tunnel."]
[30,"MS2_XT075","First X-Rays into FEH","2010-04-08",null,"This milestone is complete when X-rays are first delivered into the FEH."]
["X-Ray Endstations"]
[31,"MS2_XE015","2-D Detector Shipped to SLAC","2009-03-13",null,"This milestone is complete when the full-sized version of the 2-D detector is shipped from Cornell to SLAC for final integration into the LCLS."]
[32,"MS2_XE005","First X-Rays into NEH","2009-07-13",null,"This milestone is complete when X-rays are first delivered into the NEH."]
[33,"MS2_XE060","XE Start Installation in NEH","2008-09-18",null,"This milestone is complete when the XES group begins installation of components in the NEH."]
[34,"MS2_XE050","XE Start Installation in FEH","2009-09-01",null,"This milestone is complete when the XES group begins installation of components in the FEH."]
[35,"MS2_XE065","AMO Ready for Basic Expmnts (CD4a)","2009-02-26",null,"This milestone is complete when the CD4a suite of AMO instrumentation has been installed and completed basic checkout. "]
["Conventional Facilities"]
[36,"MS2BO_005","Sector 20 Alcove Beneficial Occupancy","2006-07-21","A","This milestone is complete when the LCLS CF group can release the facility for use by the system end user."]
[37,"MS2BO_025","Research Yards Mods Beneficial Occupancy","2006-10-20","A","This milestone is complete when the LCLS CF group can release the facility for use by the system end user."]
[38,"MS2BO_020","Linac Water/Power Avail","2007-07-11","A","This milestone is complete when the LCLS CF group can release the facility for use by the system end user."]
["Level 3 Milestones"]
["Program Management"]
[39,"MS3_PM025","Advanced Procurement Management Plan Complete","2004-02-28","A","This milestone is complete when a draft of the LCLS Advance Procurement Plan is complete.  "]
[40,"MS3_PM031","Resource Loaded Cost & Schedule (Final) Complete","2004-04-30","A","This milestone is complete when the LCLS cost and schedule TEC and TPC baselines have been accepted by the LCLS Project Office."]
[41,"MS3_PM035","1st Monthly Report (with Earned Value) Submitted","2004-04-30","A","This milestone is complete when the LCLS submits its first monthly report on the LCLS TEC and TPC using earned-value assessments."]
[42,"MS3_PM042","Risk Management Plan Complete","2004-04-30","A","This milestone is complete when a draft of the LCLS Preliminary Safety Assessment Document is complete.  "]
[43,"MS3_PM045","Prelim Safety Assessment Doc (PSAD) Submitted","2004-04-30","A","This milestone is complete when a draft of the LCLS Risk Management Plan is complete.  "]
[44,"MS3_PM050","Project Mgmt Control Syst (PMCS) Review Complete","2004-04-30","A","This milestone is complete when the LCLS team has conducted an independent review of the LCLS PMCS System and Controls."]
[45,"MS3_PM055","Project Mgmt Plan Complete","2004-04-30","A","This milestone is complete when a draft of the LCLS Project Management Plan is complete.  "]
[46,"MSC_PM000","CRIT: Start Procurement Package - PMCS Support","2004-10-01","A","This milestone is complete when a draft Advance Procurement Plan for the PMCS Support Award is submitted to SLAC Purchasing."]
[47,"MS3_PM040","Fire Hazard Analysis Review @ SLAC","2005-07-15","A","This milestone is complete when the DOE Stanford Site Office accepts the FHA report and conducts a review using the appropriate peer review at SLAC."]
[48,"MSBS_115","FY05 Shutdown Start: HW Reqd for Installation","2005-10-03","A","This milestone is complete when date is reached; This date is defined by SLAC, all FY05 HW Reqd for installation must be ready "]
[49,"MSBS_120","FY05 Shutdown Over ","2005-10-31","A","This milestone is complete when the date is reached; defines the end of the FY05 installation activities"]
[50,"MSBS_125","FY06 Shutdown Start: HW Reqd for Installation","2006-08-01","A","This milestone is complete when date is reached; This date is defined by SLAC, all FY06 HW Reqd for installation must be ready "]
[51,"MSBS_130","FY06 Shutdown Over","2007-01-05","A","This milestone is complete when the date is reached; defines the end of the FY06 installation activities"]
[52,"MSBS_135","FY07 Shutdown Start: HW Reqd for Installation","2007-09-04",null,"This milestone is complete when date is reached; This date is defined by SLAC, all FY07 HW Reqd for installation must be ready "]
[53,"MSBS_140","FY07 Shutdown Over","2007-12-03",null,"This milestone is complete when the date is reached; defines the end of the FY07 installation activities"]
[54,"MS3_PM030","LCLS ARR Complete","2009-01-08",null,"This milestone is complete when the DOE Stanford Site Office accepts the ARR report and issues a letter authorizing operation.  "]
[55,"MSBS_145","FY08 Shutdown Start","2008-10-01",null,"This milestone is complete when date is reached; This date is defined by SLAC "]
[56,"MSBS_150","FY08 Shutdown Over","2008-11-03",null,"This milestone is complete when date is reached; This date is defined by SLAC "]
["Injector System"]
[57,"MSC_IJ000","CRIT: Release RFP for Drive Laser","2004-10-15","A","This milestone is complete when the RFP for the injector drive laser is released."]
[58,"MS3_IJ095","Award of Drive Laser Contract Complete","2005-06-30","A","This milestone is complete when the drive laser contract is awarded to the selected vendor"]
[59,"MS3_IJ005","Drive Laser Available for Integration","2006-11-16","A","This milestone is complete when the drive laser has been installed and is available for integration into the injector system."]
[60,"MS3_IJ085","Accelerator Region Installation Complete","2007-01-29","A","This milestone is complete when the Injector beamline segment including both accelerator structures is installed in the Injector housing."]
[61,"MS3_IJ125","RF Gun Ready for Installation","2007-02-15","A","This milestone is complete when the RF gun is installed and aligned on the beamline."]
[62,"MS3_IJ0027","Injector Laser Commissioning Review Complete","2006-12-14","A","This milestone establishes the plan for commissioning the Injector Laser."]
[63,"MS3_IJ080","Gun Region Installation Complete","2007-01-29","A","This milestone is complete when the beamline segment between the Injector RF Gun and the first acclelerating structure (L0A) has been installed."]
[64,"MS3_IJ032","Laser Tables & Optical Paths Installation Comp","2006-08-01","A","This milestone is complete when the LCLS Drive Laser tables and Optical Paths have been installed."]
[65,"MS3_IJ0010","Start Injector Commissioning (Drive Laser)","2006-12-14","A","This milestone complete when the drive is installed and tested by the vendor at S20 Alcove."]
[66,"MS3_IJ100","Insertion Region Installation Complete","2007-02-08","A","This milestone is complete when the Injector beamline segment that connects the injector wall beamline to the SLAC Accelerator is installed."]
[67,"MS3_IJ105","Spectrometer Installation Complete","2007-02-02","A","This milestone is complete when the Injector straight-ahead-spectrometer is installed."]
[68,"MS3_IJ110","Injector RF Subsystem Installation Complete","2007-01-31","A","This milestone is complete when the RF subsystem including the wave guide is installed."]
[69,"MS3_IJ0030","Injector Accelerator Readiness Review (ARR) Comp","2006-12-15","A","This milestone is complete when the DOE Stanford Site Office accepts the ARR report and issues a letter authorizing operation from the gun through BC1."]
[70,"MS3_IJ0020","Start Injector Commissioning(UV Beam to Cathode)","2007-03-06","A","This milestone is complete when the first UV beam from the drive laser is sent to the gun photocathode."]
[71,"MS3_CT070","Injector Controls Installation Complete","2007-01-02","A","Milestone is complete when the LINAC control system commissioning is complete."]
[72,"MS3_IJ120","Laser Heater Installation Complete","2008-11-21",null,"This milestone is complete when the laser heater vacuum chamber, undulator and optical system are installed."]
["Linac System"]
[73,"MSC_LN005","CRIT: Release RFP X-Band Klystron","2005-02-25","A","This milestone is complete after FY05 Long Lead Procurement funds are received and The RFP has been released."]
[74,"MSBS_090","Shutdown of FFTB Operations","2006-06-01","A","This milestone is complete when the FFTB ceases operations and is ready to be decommissioned and dismantled in preparation of the LCLS."]
[75,"MS3_LN016","BC1 Bend Magnet Ready for Installation","2006-11-13","A","This milestone is complete when the LCLS Linac BC1 Dipoles have been received from the vendor and qualified at SLAC. "]
[76,"MS3_LN030","Linac Commissioning Review Complete - S20-30","2008-01-03","A","This milestone is complete when the commissioning plan for Linac sector 20 through 30 is formulated and has been formally reviewed and accepted."]
[77,"MS3_LN010","X-Band Klystron Ready for Installation","2006-11-27","A","This milestone is complete when the fabrication and testing of the X-Band Klystron is complete."]
[78,"MS3_LN012","BC1 Installation Complete","2007-01-29","A","This milestone is complete when the LCLS Linac BC1 subsystem has been installed and checked out prior to start of commissioning."]
[79,"MS3_LN013","Start BC1 Commissioning","2007-02-28","A","This milestone is complete when electrons are delivered to BC1 and BC1 systems are first activated."]
[80,"MS3_LN011","BC2 Installation Complete","2008-01-02",null,"This milestone is complete when the LCLS Linac BC2 subsystem has been installed and checked out prior to start of commissioning."]
[81,"MS3_LN025","Start Linac (Li20-Li30) Commissioning","2008-01-07",null,"This milestone starts beam commissioning of the Linac from Sector 20 through Sector 30 including BC1 and BC2."]
[82,"MS3_LN032","Linac Commissioning Review Complete - LTU","2009-01-07",null,"This milestone is complete when the commissioning plan for Linac LTU is formulated and has been formally reviewed and accepted."]
[83,"MS3_CT072","Linac Controls Ready for BC1 Commissioning","2007-01-31","A","This milestone is complete when the control system is ready to operate the LINAC BC1."]
[84,"MS3_LN055","E-Dump Component Installation Complete","2008-08-15",null,"This milestone is complete when the LCLS Linac E-Dump components have been installed and checked out."]
[85,"MS3_LN035","LTU Component Installation Complete","2008-10-03",null,"This milestone is complete when the LCLS Linac LTU components have been installed and checked out."]
[86,"MS3_LN015","Start Linac-to-Undulator (LTU) Commissioning","2009-01-08",null,"This milestone starts after installation of the LTU is complete and the beam authorization sheet for LTU is signed and electrons are injected into the LTU."]
["Undulator System"]
[87,"MSC_UN005","CRIT: Release RFP Ti Strongback","2005-01-14","A","Comments of the internal design review have been incorporated into the bid package for the Ti Strongbacks and the RFP has been released."]
[88,"MSC_UN015","CRIT: Release RFP Magnet Poles","2005-02-04","A","The RFP for the procurement of the magnet poles has been released.."]
[89,"MSC_UN010","CRIT: Release RFP  Magnet Blocks","2005-03-23","A","The RFP for the procurement of the magnet blocks has been released."]
[90,"MSC_UN020","CRIT: Release RFP Magnet Assemblies - 1st Art","2005-06-28","A","The RFP for the procurement of the Mag Assy & Supt has been released."]
[91,"MS3_UN028","Award of 1st Articles Mag Assy to Vendors Comp","2005-10-11","A","The award for the 1st article magnet assembly has been made to a vendor. "]
[92,"MSC_UN030","CRIT: Release RFP - Fixed Supports","2006-05-09","A","This milestone is complete when the RFP for the Undulator supports has been released."]
[93,"MSC_UN016","CRIT: Release RFP - Quadrupoles","2006-04-12","A","Thr RFP for the procurement of the quadrupoles has been released."]
[94,"MS3_UN018","Undulator SUT Completed","2006-04-28","A","A complete mock-up of the undulator has been assembled and tested."]
[95,"MS3_UN006","1st Article Vendor A Undulator 1 Rcvd @ SLAC","2006-06-02","A","1st article undulator from vendor A has arrived at SLAC."]
[96,"MS3_UN010","1st Article Vendor B Undulator 2 Rcvd @ SLAC","2006-06-02","A","1st article undulator from vendor B has arrived at SLAC"]
[97,"MS3_UN005","MMF Qualified & Ready to Measure Prod Undulators","2006-10-27","A","This milestone marks the successful commissioning of the MMF, incl. the completion of the calibration of the test stands, and the acceptance sign-off by the APS project physicist."]
[98,"MS3_UN015","25% production undulators received","2007-01-02","A","The 10th production undulator has been received at SLAC."]
[99,"MS3_UN022","50% production undulators received","2007-03-19","A","The 20th production undulator has been received at SLAC."]
[100,"MS3_UN027","75% production undulators received","2007-06-07","A","The 30th production undulator has been received at SLAC."]
[101,"MS3_UN040","Hydrostatic Level System Complete","2008-08-08",null,"This milestone marks the date when the HLS is ready to take measurements."]
[102,"MS3_UN029","Undulator Production Units (33) Received","2007-07-06","A","This milestone is complete when the 33rd production undulator has been received at SLAC."]
[103,"MS3_UN042","Wire Monitoring System Complete","2008-08-08",null,"This milestone marks the date when the WMS is ready to take measurements."]
[104,"MS3_UN020","Undulator System Installation Complete","2008-11-14",null,"All undulator system installation, alignment, and basic checkout is complete, and the system is ready for beam."]
[105,"MS3_UN025","Start Undulator Commissioning (1st Light)","2009-04-06",null,"1st beam through the undulator system with the undulators rolled in."]
[106,"MS3_CT085","Undulator Controls Ready for Commissioning","2009-02-06",null,"This milestone is complete when the Undulator control system is ready for commissioing. (New)"]
[107,"MS3_UN030","1st Production Vacuum Chamber Delivered to SLAC","2008-01-02",null,"This milestone is complete when the first production undulator vacuum chamber is delivered to SLAC."]
[108,"MS3_UN035","1st Production RFBPM Delivered to SLAC","2008-04-04",null,"This milestone is complete when the first production RFBPM is delivered to SLAC."]
[109,"MS3_UN045","1st Production Beam Finder Wire Delivered to SLAC","2007-11-17",null,"This milestone is complete when the first production Beam Finder WIre is delivered to SLAC."]
["X-Ray Transport, Optics and Diagnostics System"]
[107,"MS3_XT007","Tunnel Mech/Vac Design Review Complete","2006-11-29","A","This milestone is complete when the LCLS X-TOD transport tunnel hardware design is complete."]
[108,"MS3_XT040","AWARD: LE Mirror System","2007-07-31",null,"This milestone is complete when the purchase order for the low-energy mirror substrates has been signed."]
[109,"MS3_XT060","AWARD: HE Mirror System","2007-11-16",null,"This milestone is complete when the purchase order for the high-energy mirror substrates has been signed."]
[110,"MS3_XT025","Gas/Solid Attenuator Ready to Ship to SLAC","2008-02-15",null,"This milestone is complete when the gas/solid attenuator system has been completed and checked and is ready to ship from LLNL to SLAC."]
[111,"MS3_XT050","XT Start Tunnel Installation","2009-07-13",null,"This milestone is complete when the XTOD group begins installation of beam transport equipment in the X-ray transport tunnel. "]
[112,"MS3_XT030","Fixed Mask Ready to Ship to SLAC","2007-12-14",null,"This milestone is complete when the fixed mask system has been completed and checked and is ready to ship from LLNL to SLAC."]
[113,"MS3_XT100","XT Start FEE Installation","2008-08-21",null,"This milestone is complete when the XTOD group begins installation of equipment in the FEE."]
[114,"MS3_XT000","FEE Install/Check Complete","2009-02-09",null,"This milestone is complete when the beamline components of the XTOD group have been installed and checked in the FEE."]
[115,"MS3_XT071","XT Tunnel/FEH Install/Check Complete","2010-01-11",null,"This milestone is complete when the beamline components of the XTOD group have been installed and checked in the x-ray transport tunnel."]
[116,"MS3_XT005","Start FEE Commissioning with Beam","2009-04-06",null,"This milestone is complete when x-rays are first delivered into the FEE."]
[117,"MS3_XT075","First X-Rays into FEH","2010-03-08",null,"This milestone is complete when X-rays are first delivered into the FEH."]
["X-Ray Endstations"]
[118,"MS3_XE030","Complete 2-D X-Ray Detector Statement of Work","2005-07-01","A","This milestone is complete when a Statement of Work has been prepared for the 2-D X-ray Detector development program, and approved by project management."]
[119,"MS3_XE035","Award Initial Funding for 2-D X-Ray Detector","2005-07-15","A","This milestone is complete when an MOU or contract is signed with an outside party, commencing the first phase of development of the 2-D X-ray detector."]
[120,"MS3_XE110","Hire Atomic Physicist","2006-03-17","A","The day the Atomic Physicist begins work for LCLS."]
[121,"MS3_XE100","Hire Detector Physicist","2006-04-03","A","The day the Detector Physicist begins work for LCLS."]
[122,"MS3_XE020","COMP: AMO PDR Meeting","2007-08-31",null,"This milestone is complete when the AMO instrument has completed its first Preliminary Design Review meeting."]
[123,"MS3_XE040","LDAC Mid-Project Review - 2-D X-Ray Detector","2007-11-30",null,"This milestone is complete upon completion (with written report) of a formal project review by the LCLS Detector Advisory Committee (LDAC) at the half way point of the 2-D X-ray detector development project."]
[124,"MS3_XE025","Award XES Laser System","2008-03-20",null,"This milestone is complete when the first purchase order for the XES laser system is signed."]
[125,"MS3_XE060","XE Start Installation in NEH","2008-08-18",null,"This milestone is complete when the XES group begins installation of components in the NEH."]
[126,"MS3_XE015","2-D Detector Shipped to SLAC","2009-02-13",null,"This milestone is complete when the full-sized version of the 2-D detector is shipped from Cornell to SLAC for final integration into the LCLS."]
[127,"MS3_XE005","First X-Rays into NEH","2009-06-15",null,"This milestone is complete when X-rays are first delivered into the NEH."]
[128,"MS3_XE080","XES Laser Operating in Near Hall","2008-11-24",null,"This milestone is complete when the initial componets of the NEH laser system have been installed, and the NEH laser room PPS system has been certified so that laser operation can begin."]
[129,"MS3_XE065","AMO Ready for Basic Expmnts (CD4a)","2009-01-26",null,"This milestone is complete when the CD4a suite of AMO instrumentation has been installed and completed basic checkout. "]
[130,"MS3_XE120","Electron Dump Stoppers Certified","2009-01-08",null,"This milestone is complete upon safety certification of the PPS stoppers located in the Electron dump which control x-ray beam propagation into the FEE."]
[131,"MS3_XE130","FEE/NEH PPS Certified","2009-02-23",null,"This milestone is complete upon safety certification of the X-ray Personnel Protection System and Hutch Protection System for the FEE/NEH region."]
[132,"MS3_XE150","TUN/FEH PPS Certified","2010-02-05",null,"This milestone is complete upon safety certification of the X-ray Personnel Protection System and Hutch Protection System for the tunnel/FEH region."]
[133,"MS3_XE050","XE Start Installation in FEH","2009-08-03",null,"This milestone is complete when the XES group begins installation of components in the FEH."]
["Conventional Facilities"]
[134,"MS3_CF000","A&E Serv (S20, MMF, MCC not incl) Title 1 Comp","2004-04-30","A","This milestone is complete after a Title I review has been completed and all action (or corrective action) items have been resolved."]
[135,"MS3_CF002","A&E Serv Sector 20 Title 1 Complete","2004-04-30","A","This milestone is complete after a Title I review has been completed and all action (or corrective action) items have been resolved."]
[136,"MS3_CF022","A&E Services MMF Title 1 Complete","2004-04-30","A","This milestone is complete after a final Title I review has been completed and all action (or corrective action) items have been resolved."]
[137,"MS3_CF010","A&E Services Sector 20 Title 2 Complete","2005-03-18","A","This milestone is complete after a final Title II review has been completed and all action (or corrective action) items have been resolved."]
[138,"MSC_CF005","CRIT: Rel RFP T3 Const. Pkg. RF Hut & S20/Alcove","2005-04-01","A","This milestone is complete when the RFP for the Title 3 construction of the RF Hut and Alcove has been released."]
[139,"MSC_CF010","CRIT: Release RFP T3 Construction Contract (MMF)","2005-04-14","A","This milestone is complete when the RFP for the Title 3 construction of the MMF has been released."]
[140,"MSC_CF020","CRIT:  Release RFP Construction Mgmt Pkg (CM)","2005-07-25","A","This milestone is complete when the RFP for the Construction Management Contract has been released."]
[141,"MS3_CF015","A&E Services MMF Title 2 Complete","2005-05-31","A","This milestone is complete after a final Title II review has been completed and all action (or corrective action) items have been resolved."]
[142,"MS3_CF065","Award of S20 Title 3 Complete","2005-08-05","A","This milestone is complete after a contract award has been issued to a successful General Contractor"]
[143,"MS3_CF066","Award of MMF Title 3 Complete","2005-08-05","A","This milestone is complete after a contract award has been issued to a successful General Contractor"]
[144,"MS3_CF060","Award of Construction Management Contract Complete","2005-09-30","A","This milestone is complete after a contract award has been issued to a successful Construction Management"]
[145,"MSC_CF000","CRIT:  Release RFP T3 Construct (RY-CLOC)","2006-01-26","A","This milestone is complete when the pre-qualifications and pre-selection phases have commenced and the RFP has been released."]
[146,"MSBO_010","Magnetic Msmt Facility(MMF) Beneficial Occupancy","2006-04-03","A","This milestone is complete when the LCLS CF group can release the facility or a subset of the entire facility thereof for use by the system end user, prior to final acceptance."]
[147,"MSBO_000","RF Hut Beneficial Occupancy","2005-12-07","A","This milestone is complete when the LCLS CF group can release the facility or a subset of the entire facility thereof for use by the system end user, prior to final acceptance."]
[148,"MS3_CF005","A&E Serv (S20, MMF, MCC not incl) Title 2 Comp","2006-01-20","A","This milestone is complete after a final Title II review has been completed and all action (or corrective action) items have been resolved."]
[149,"MSC_CF006","CRIT:  Release RFP T3 Construction Pkg (Linac)","2006-07-10","A","This milestone is complete when the RFP for the Title 3 construction of the Linac has been released."]
[150,"MS3BO_005","Sector 20 Alcove Beneficial Occupancy","2006-06-21","A","This milestone is complete when the LCLS CF group can release the facility for use by the system end user."]
[151,"MS3BO_025","Research Yards Mods Beneficial Occupancy","2006-09-21","A","This milestone is complete when the LCLS CF group can release the facility for use by the system end user."]
[152,"MS3BO_035","Undulator Facility Beneficial Occupancy","2008-03-20",null,"This milestone is complete when the LCLS CF group can release the facility for use by the system end user."]
[153,"MS3BO_050","Near Experimental Hall Beneficial Occupancy","2008-03-20",null,"This milestone is complete when the LCLS CF group can release the facility for use by the system end user."]
[154,"MS3BO_020","Linac Water/Power Avail","2007-06-11","A","This milestone is complete when the LCLS CF group can release the facility for use by the system end user."]
[155,"MS3BO_060","Far Experimental Hall Beneficial Occupancy","2008-06-20",null,"This milestone is complete when the LCLS CF group can release the facility for use by the system end user."]
[156,"MS3BO_040","Front End Enclosure Beneficial Occupancy","2008-03-20",null,"This milestone is complete when the LCLS CF group can release the facility for use by the system end user."]
[157,"MS3BO_055","X-Ray Transport Beneficial Occupancy","2008-06-20",null,"This milestone is complete when the LCLS CF group can release the facility for use by the system end user."]
[158,"MSBO_045","Electron Beam Dump Beneficial Occupancy","2008-03-20",null,"This milestone is complete when the LCLS CF group can release the facility for use by the system end user."]
[159,"MS3BO_030","Beam Transport Hall Beneficial Occupancy","2008-03-20",null,"This milestone is complete when the LCLS CF group can release the facility for use by the system end user."]
[160,"MS3BO_065","Central Utility Plant Beneficial Occupancy","2008-03-20",null,"This milestone is complete when the LCLS CF group can release the facility for use by the system end user."]
[161,"MS3CO_005","Beam Transport Hall Co-Occupancy","2007-12-04",null,"This milestone makes available the facility for early non CF system activities ie: anchor-bolts, cable plant, equipment stands installation, etc.  All CF construction activities take precedence between this milestone and the BO milestone.  CF systems are not yet commissioned for use by non-CF systems for installation of equipment.  This milestone does not include temperature stable environment."]
[162,"MS3CO_010","Undulator Facility Co-Occupancy","2007-12-04",null,"This milestone makes available the facility for early non CF system activities ie: anchor-bolts, cable plant, equipment stands installation, etc.  All CF construction activities take precedence between this milestone and the BO milestone.  CF systems are not yet commissioned for use by non-CF systems for installation of equipment.  This milestone does not include temperature stable environment."]
[163,"MS3CO_015","Front End Enclosure Co-Occupancy","2007-12-04",null,"This milestone makes available the facility for early non CF system activities ie: anchor-bolts, cable plant, equipment stands installation, etc.  All CF construction activities take precedence between this milestone and the BO milestone.  CF systems are not yet commissioned for use by non-CF systems for installation of equipment.  This milestone does not include temperature stable environment."]
[164,"MS3CO_020","Near Experimental Hall Co-occupancy","2007-12-20",null,"This milestone makes available the facility for early non CF system activities ie: anchor-bolts, cable plant, equipment stands installation, etc.  All CF construction activities take precedence between this milestone and the BO milestone.  CF systems are not yet commissioned for use by non-CF systems for installation of equipment.  This milestone does not include temperature stable environment."]
[165,"MS3CO_025","X-Ray Transport Co-Occupancy","2008-01-07",null,"This milestone makes available the facility for early non CF system activities ie: anchor-bolts, cable plant, equipment stands installation, etc.  All CF construction activities take precedence between this milestone and the BO milestone.  CF systems are not yet commissioned for use by non-CF systems for installation of equipment.  This milestone does not include temperature stable environment."]
[166,"MS3CO_030","Far Experimental Hall Co-Occupancy","2008-03-21",null,"This milestone makes available the facility for early non CF system activities ie: anchor-bolts, cable plant, equipment stands installation, etc.  All CF construction activities take precedence between this milestone and the BO milestone.  CF systems are not yet commissioned for use by non-CF systems for installation of equipment.  This milestone does not include temperature stable environment."]
[167,"MS3CO_035","Beam Dump Co-Occupancy","2007-12-04",null,"This milestone makes available the facility for early non CF system activities ie: anchor-bolts, cable plant, equipment stands installation, etc.  All CF construction activities take precedence between this milestone and the BO milestone.  CF systems are not yet commissioned for use by non-CF systems for installation of equipment.  This milestone does not include temperature stable environment."]
[168,"MS3CO_040","Central Utility Plant Co-Occupancy","2007-12-20",null,"This milestone makes available the facility for early non CF system activities ie: anchor-bolts, cable plant, equipment stands installation, etc.  All CF construction activities take precedence between this milestone and the BO milestone.  CF systems are not yet commissioned for use by non-CF systems for installation of equipment.  This milestone does not include temperature stable environment."]
[169,"MS3BO_070","CEH Building Beneficial Occupancy","2009-07-16",null,"This milestone is complete when the LCLS CF group can release the facility for use by the system end user."]
[170,"MS3BO_075","B028 Beneficial Occupancy","2009-05-05",null,"This milestone is complete when the LCLS CF group can release the facility for use by the system end user."]
[171,"MS3BO_080","FEH Hutches Beneficial Occupancy","2009-07-01",null,"This milestone is complete when the LCLS CF group can release the facility for use by the system end user."]