{"text_format":"2","workbook":"xls","n_sheets":9,"sheets":["LCLA","LC01","PriorMonth","Master","RAM","DATA","c_modConnectP3","m_modGetP3Activities","Help"],"not_rendered":{"charts":0,"images":2,"macros":1,"external_links":2,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[{"sheet":"c_modConnectP3","index":6,"reason":"not_a_worksheet"},{"sheet":"m_modGetP3Activities","index":7,"reason":"not_a_worksheet"}],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"LCLA","index":0,"n_rows":13094,"n_cols":7,"rows_kept":13094,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}
[null,"Activities Detail ","10998 activities in project"]
[null,"Project LCLA","DataDate: 5/2/2005",null,null,null,"Latest EF: 3/31/2009"]
[]
["ID","Description","ES","EF","Total Float","AS","AF"]
["CF04012013","30% Title 2 Design Review - RY - CLOC (Apr Accr)","2005-05-02","2005-05-06"]
["CF04012015","30% Title 2 Design Review - RY through CLOC","2005-05-02","2005-08-26"]
["CF04012023","AWARD: Arch Flash Calculation","2006-05-19","2006-05-19"]
["CF04012025","60% Title 2 Design Review - RY through CLOC","2005-08-29","2005-11-23"]
["CF04012033","Arc Flash Calculation","2006-05-22","2006-07-18"]
["CF04012040","90% Title 2 Design Review - RY through CLOC","2005-11-28","2005-12-16"]
["CF04012055","100% Title 2 Design Review","2006-01-12","2006-02-06"]
["CF04012060","LCLS Review 100% Title 2 Design/Bid Documents","2006-01-24","2006-02-06"]
["CF04012065","SLAC Commitee Review 100% Title 2 Design","2006-02-07","2006-02-17"]
["CF04012070","COMP: LCLS Review 100% Design (RY-CLOC)","2006-02-21","2006-02-17"]
["CF04012075","DOE Review 100% Title 2 Design ( RY - CLOC)","2006-02-21","2006-03-20"]
["CF04012085","RCV: DOE Approval 100% Title 2 ( RY - CLOC)","2006-03-21","2006-03-20"]
["CF04012095","Far Hall A&E Title 2 Design Changes","2005-08-08","2006-02-06"]
["CF04012101","REQD:Obtain Seismic Rvw Committee Appr(T2)","2006-03-14","2006-03-13"]
["CF04012105","A&E Title 2 Design Changes - DCNs","2005-09-01","2006-02-06"]
["CF04012115","A&E Title 2 Design Changes - Committed","2005-09-01","2006-02-06"]
["CF04012125","A&E Title 2 Design Changes - DCNs","2005-10-03","2006-02-06"]
["CF04012135","A&E Title 2 Design Changes - DCNs","2005-12-05","2006-02-28"]
["CF0401235","A&E Post 100% Negotiation","2006-02-27","2006-04-28"]
["CF04012910","SLAC Supp - FFTB Removal  (WO 8819008)","2006-04-10","2006-06-19"]
["CF04012920","REQD: Ready for Construction***","2006-07-21","2006-07-20"]
["CF04012930","SLAC Support - FFTB Removal (WO 8819007)","2006-04-10","2006-06-19"]
["CF04012935","FFTB - Site Preparation (WO 8819006)","2006-05-08","2006-06-05"]
["CF04012940","AWARD: FFTB Components & Shielding Removal","2006-04-04","2006-04-04"]
["CF04012950","FFTB - Mobilization","2006-04-24","2006-04-24"]
["CF04012960","Start - FFTB Components & Shielding Removal","2006-05-01","2006-06-30"]
["CF04012970","COMP:  FFTB Removal & Preservation","2006-07-03","2006-06-30"]
["CF04034005","UTR Support for Construction","2006-11-10","2008-02-08"]
["CF0410000","CEF Title 2 Design Support (Non Linac)","2005-06-06","2005-09-30"]
["CF0410010","Additional CEF Title 2 Design - Non LINAC","2005-12-01","2006-06-30"]
["CF05010","AWARD: Research Yard Construction Pkg - FY06","2006-04-17","2006-04-17"]
["CF05012900","Research Yard Site Preparation","2005-11-07","2006-01-19"]
["CF05012920","Construction of FFTB/BSY Vertical Wall","2005-10-03","2005-10-28"]
["CF05012925","Construction FFTB/BSY  - cost increased","2005-10-03","2005-11-11"]
["CF05012930","COMP: FFTB/BSY Vertical Wall","2005-11-14","2005-11-11"]
["CF05015","AWARD: Research Yard Construction Pkg - FY07","2006-10-02","2006-10-02"]
["CF05020","Sitework","2006-05-24","2006-10-02"]
["CF05030","Metals","2006-05-24","2006-10-02"]
["CF05033006","AWARD: EP Soil Disposal Contract","2006-10-23","2006-10-23"]
["CF05033007","EP Soil Disposal","2006-11-21","2007-07-25"]
["CF05033020","SLAC RSY - Site Construction","2006-04-03","2006-12-12"]
["CF05033030","AWARD: Testing RY through CLOC","2006-10-02","2006-10-02"]
["CF05033035","Testing - RY through CLOC","2006-10-24","2007-08-09"]
["CF05033040","AWARD: Commissioning RY through CLOC - FY07","2006-10-02","2006-10-02"]
["CF05033041","AWARD: Commissioning RY through CLOC - FY08","2007-10-01","2007-10-01"]
["CF05033042","AWARD: Commissioning RY through CLOC - FY09","2008-10-01","2008-10-01"]
["CF05033045","Commissioning - RSY-CLOC (FY07)","2006-10-03","2007-09-28"]
["CF05033050","AVAIL: Beneficial Occupancy Research Yard Mods","2006-10-03","2006-10-02"]
["CF05033053","RY Project Close Out","2006-10-03","2006-11-29"]
["CF05033054","AWARD: Construction Power for Tunnelling - FY06","2006-05-22","2006-05-22"]
["CF05033055","SLAC - Construction Power for Tunnelling","2006-06-21","2008-12-19"]
["CF05033063","AWARD: Tunnel Rescue Team","2006-03-06","2006-03-06"]
["CF05033064","AWARD: Construction Power for Tunnelling - FY07","2006-10-02","2006-10-02"]
["CF05033065","Tunnel Rescue Team","2006-03-06","2006-07-25"]
["CF05033073","AWARD: Sales Tax - FY06","2006-05-24","2006-05-24"]
["CF05033074","AWARD: Construction Power for Tunnelling - FY08","2007-10-01","2007-10-01"]
["CF05033075","Sales Tax","2006-05-24","2008-09-29"]
["CF05033083","AWARD: Sales Tax - FY07","2006-10-02","2006-10-02"]
["CF05033084","AWARD: Construction Power for Tunnelling - FY09","2008-10-01","2008-10-01"]
["CF05033085","Commissioning - RSY-CLOC (FY08)","2007-10-01","2008-09-30"]
["CF05033093","AWARD: Sales Tax - FY08","2007-10-01","2007-10-01"]
["CF05033095","Commissioning - RSY-CLOC (FY09)","2008-10-01","2008-12-31"]
["CF05033200","COMP: Research Yard Mods Final Acceptance","2006-12-13","2006-12-12"]
["CF05033500","AWARD: Furnishing - RY through CLOC","2007-10-01","2007-10-01"]
["CF05033510","Furnishing - RY through CLOC","2007-11-29","2008-09-16"]
["CF05034005","UTR Support for Construction","2006-03-27","2007-01-11"]
["CF05040","COMP: Research Yard Mods Construction","2006-10-03","2006-10-02"]
["CF06100","AWARD: Access Road Construction Package","2006-04-17","2006-04-17"]
["CF06110","Sitework","2006-05-09","2006-08-30"]
["CF06120","Concrete","2006-06-07","2006-08-30"]
["CF06130","Access Road - Project Close Out","2006-08-31","2006-09-28"]
["CF06140","COMP: Access Road Construction","2006-09-29","2006-09-28"]
["CF08100","AWARD: BTH Construction Package - FY06","2006-05-22","2006-05-22"]
["CF08105","AWARD: BTH Construction Package - FY07","2006-10-02","2006-10-02"]
["CF08110","Sitework","2006-07-21","2007-05-24"]
["CF08120","Concrete","2006-08-18","2007-05-07"]
["CF08130","Metals","2006-08-18","2007-05-07"]
["CF08140","Mechanical","2006-08-18","2007-05-07"]
["CF08150","Electrical","2006-08-18","2007-05-07"]
["CF08160","Other Construction","2006-08-18","2007-05-07"]
["CF08170","COMP: Beam Transport Hall Construction","2007-05-25","2007-05-24"]
["CF0833050","AVAIL: Beneficial Occupancy Beam Transport Hall","2007-05-25","2007-05-24"]
["CF0833100","BTH - Project Close Out","2007-05-25","2007-07-23"]
["CF0833200","COMP: Beam Transport Hall Final Acceptance","2007-07-24","2007-07-23"]
["CF09100","AWARD: Front End Enclosure Construction Pkg - FY","2006-08-01","2006-08-01"]
["CF09105","AWARD: Front End Enclosure Construction Pkg - FY","2006-10-02","2006-10-02"]
["CF09110","Sitework","2006-08-23","2007-04-17"]
["CF09120","Concrete","2006-10-19","2007-04-12"]
["CF09130","Mechanical","2006-10-19","2007-04-12"]
["CF09140","Electrical","2006-10-19","2007-04-12"]
["CF09150","Other Construction","2006-10-19","2007-04-12"]
["CF09160","COMP: FEE Construction","2007-04-18","2007-04-17"]
["CF0933050","AVAIL: Beneficial Occupancy Front End Enclosure","2007-04-18","2007-04-17"]
["CF0933100","FEE - CF Project Close Out","2007-04-18","2007-06-13"]
["CF0933200","COMP: Front End Enclosure Final Acceptance","2007-06-14","2007-06-13"]
["CF10010210","CEF Title 2 Support","2005-05-02","2005-05-20"]
["CF10010215","AWARD: 12kv Design (MH 48 to CUP Substation)","2006-06-05","2006-06-05"]
["CF10010230","MD Support For Title 2 Design","2005-09-12","2005-11-30"]
["CF10010240","Additional MD Support  Title 2 Design -Non LINAC","2005-12-01","2006-06-30"]
["CF10012010","TCCo Modification - 30% Estimate","2006-02-06","2006-02-10"]
["CF10012015","Monte Carlo Analysis","2006-02-13","2006-02-17"]
["CF10012025","12 kv Design (MH 48 to CUP Substation)","2006-06-06","2006-08-29"]
["CF10073055","AWARD: EBD Steel Shielding - FY06","2006-07-10","2006-07-10"]
["CF10073057","AWARD: EBD Steel Shielding - FY07","2006-10-02","2006-10-02"]
["CF10073060","SLAC Install EBD Steel Shielding","2006-08-01","2007-01-23"]
["CF10100","AWARD: Electron Beam Dump Construction Package","2006-08-16","2006-08-16"]
["CF10110","Sitework","2006-09-08","2007-05-18"]
["CF10120","Concrete","2006-11-03","2007-05-18"]
["CF10130","Mechanical","2006-11-03","2007-05-18"]
["CF10140","Electrical","2006-11-03","2007-05-18"]
["CF10150","Other Construction","2006-11-03","2007-05-18"]
["CF10160","COMP: Electron Beam Dump Construction","2007-05-21","2007-05-18"]
["CF10170","AWARD: Electron Beam Dump Constr. Pkg - FY07","2006-10-02","2006-10-02"]
["CF1033050","AVAIL: Beneficial Occupancy Beam Dump","2007-05-21","2007-05-18"]
["CF1033100","EBD - Project Close Out","2007-05-21","2007-07-17"]
["CF1033200","COMP: Electron Beam Dump Final Acceptance","2007-07-18","2007-07-17"]
["CF1103010","SLAC Site Preparation","2006-07-10","2006-10-30"]
["CF11100","AWARD: Near Experimental Hall Constr Pkg - FY06","2006-06-20","2006-06-20"]
["CF11105","AWARD: Near Experimental Hall Constr Pkg - FY07","2006-10-02","2006-10-02"]
["CF11110","Sitework including Demo Gas Pad","2006-07-13","2007-06-18"]
["CF11120","Concrete","2006-08-10","2007-03-02"]
["CF11130","Metals","2006-08-10","2007-03-02"]
["CF11140","Mechanical","2006-09-08","2007-05-25"]
["CF11150","Electrical","2006-09-08","2007-05-25"]
["CF11160","Other Construction","2006-09-08","2007-05-25"]
["CF11170","COMP: Near Experimental Hall Construction","2007-06-19","2007-06-18"]
["CF1133050","AVAIL: Beneficial Occupancy NEH","2007-06-19","2007-06-18"]
["CF1133100","NEH - CF Project Close Out","2007-06-19","2007-08-14"]
["CF1133200","COMP: Near Experimental Hall Final Acceptance","2007-08-15","2007-08-14"]
["CF12100","AWARD: Undulator Hall Construction Pkg - FY06","2006-08-07","2006-08-07"]
["CF12105","AWARD: Undulator Hall Construction Pkg - FY07","2006-10-02","2006-10-02"]
["CF12110","Sitework","2006-08-29","2007-04-30"]
["CF12120","Metals","2006-10-25","2007-04-18"]
["CF12130","Mechanical","2006-10-25","2007-04-18"]
["CF12140","Electrical","2006-10-25","2007-04-18"]
["CF12150","Other Construction","2006-10-25","2007-04-18"]
["CF12160","UH Tunnel Construction","2006-08-29","2007-04-30"]
["CF12170","COMP: Undulator Hall Construction","2007-05-01","2007-04-30"]
["CF1233050","AVAIL: Beneficial Occupancy Undulator Facility","2007-05-01","2007-04-30"]
["CF1233100","UH - CF Project Close Out","2007-05-01","2007-06-26"]
["CF1233200","COMP: Undulator Facility Final Acceptance","2007-06-27","2007-06-26"]
["CF13013085","MD Title 3 Support  - Non Linac","2006-05-01","2007-04-30"]
["CF13013100","RY - CLOC Seismic Peer Review","2005-09-06","2006-03-13"]
["CF13013110","In-House Conventional Facility Peer Review","2005-06-06","2006-01-13"]
["CF13013210","Independent Cost Estimate (ICE) - 30% Review","2005-08-15","2005-10-10"]
["CF13013220","Independent Cost Estimate (ICE) - 60% Review","2005-11-08","2006-01-20"]
["CF13013230","Independent Cost Estimate (ICE) - 90% Review","2006-02-21","2006-04-03"]
["CF13014005","UTR Support for Construction","2007-02-27","2008-06-04"]
["CF13100","AWARD: XRTD Construction Package","2006-12-14","2006-12-14"]
["CF13110","Sitework","2007-01-04","2007-08-02"]
["CF13120","Concrete","2007-03-05","2007-07-24"]
["CF13130","Metals","2007-03-05","2007-07-24"]
["CF13140","Mechanical","2007-03-05","2007-07-24"]
["CF13150","Electrical","2007-03-05","2007-07-24"]
["CF13160","Other Construction","2007-03-05","2007-07-24"]
["CF13170","XRTD Tunnel Construction","2007-01-04","2007-08-02"]
["CF13180","COMP: X-Ray Transport & Diagnostics Construction","2007-08-03","2007-08-02"]
["CF1333050","AVAIL: Beneficial Occupancy X-Ray Transport","2007-08-03","2007-08-02"]
["CF1333100","XRTD - CF Project Close Out","2007-08-03","2007-09-28"]
["CF1333200","COMP: X-Ray Transpt & Diag Hall Final Acceptance","2007-10-01","2007-09-28"]
["CF14100","AWARD: Far Experimental Hall Construction Pkg","2006-10-31","2006-10-31"]
["CF14110","Sitework","2006-11-22","2007-08-17"]
["CF14120","Metals","2007-01-24","2007-08-10"]
["CF14130","Mechanical","2007-01-24","2007-08-10"]
["CF14140","Electrical","2007-01-24","2007-08-10"]
["CF14150","Other Construction","2007-01-24","2007-08-10"]
["CF14160","FEH Tunnel Construction","2006-11-22","2007-07-27"]
["CF14170","COMP: Far Experimental Hall Construction","2007-08-20","2007-08-17"]
["CF14180","AWARD: Access Tunnel Construction Pkg - FY06","2006-06-30","2006-06-30"]
["CF14185","AWARD: Access Tunnel Construction Pkg - FY07","2006-10-02","2006-10-02"]
["CF14190","Access Tunnel Constructionn","2006-07-25","2007-08-06"]
["CF14200","COMP: Access Tunnel Constructionn","2007-08-07","2007-08-06"]
["CF1433050","AVAIL:Beneficial Occupancy Far Experimental Hall","2007-08-20","2007-08-17"]
["CF1433100","FEH - CF Project Close Out","2007-08-20","2007-10-15"]
["CF1433200","COMP: Far Experimental Hall Final Acceptance","2007-10-16","2007-10-15"]
["CF15100","AWARD: BTH Service Building Construction Pkg","2006-10-16","2006-10-16"]
["CF15110","Concrete","2006-11-07","2007-05-24"]
["CF15120","Metals","2006-11-07","2007-05-24"]
["CF15130","Mechanical","2006-11-07","2007-05-24"]
["CF15140","Electrical","2006-11-07","2007-05-24"]
["CF15150","Other Construction","2006-11-07","2007-05-24"]
["CF15160","COMP: BTH Service Buildings Construction","2007-05-25","2007-05-24"]
["CF16100","AWARD: UH Service Building Construction Pkg","2006-10-20","2006-10-20"]
["CF16110","Concrete","2006-11-13","2007-04-30"]
["CF16120","Metals","2006-11-13","2007-04-30"]
["CF16130","Mechanical","2006-11-13","2007-04-30"]
["CF16140","Electrical","2006-11-13","2007-04-30"]
["CF16150","Other Construction","2006-11-13","2007-04-30"]
["CF16160","COMP: UH Service Building Construction","2007-05-01","2007-04-30"]
["CF17100","AWARD: FEH Service Building Construction Pkg","2007-04-05","2007-04-05"]
["CF17110","Concrete","2007-04-27","2007-08-17"]
["CF17120","Metals","2007-04-27","2007-08-17"]
["CF17130","Mechanical","2007-06-11","2007-08-17"]
["CF17140","Electrical","2007-06-11","2007-08-17"]
["CF17150","Other Construction","2007-06-11","2007-08-17"]
["CF17160","COMP: FEH Service Building Construction","2007-08-20","2007-08-17"]
["CF18090300","COMP: All Areas Except CLOC","2009-01-02","2008-12-19"]
["CF18100","AWARD: Central Utility Plant Construction - FY06","2006-06-22","2006-06-22"]
["CF18102","AWARD: Central Utility Plant Construction - FY07","2006-10-02","2006-10-02"]
["CF18103","AWARD: Natural Gas Line (Guest House to CUP)","2006-12-11","2006-12-11"]
["CF18105","AWARD: 12 kv Construction (MH48 to CUP Substat)","2006-12-11","2006-12-11"]
["CF18110","Sitework","2006-07-17","2007-05-23"]
["CF18115","Natural Gas Line (Guest House to CUP)","2007-01-18","2007-03-15"]
["CF18120","Concrete","2006-08-14","2007-04-17"]
["CF18130","Metals","2006-08-14","2007-04-17"]
["CF18140","Mechanical","2006-08-14","2007-04-17"]
["CF18150","Electrical","2006-08-14","2007-04-17"]
["CF18155","12 kv Construction (MH48 to CUP Substat)","2007-01-18","2007-05-10"]
["CF18160","Other Construction","2006-08-14","2007-04-17"]
["CF18170","Start Up & Commissioning","2007-04-12","2007-05-23"]
["CF18180","COMP: Central Utility Plant Construction","2007-05-24","2007-05-23"]
["CF1833200","COMP: Central Utility Plant Final Acceptance","2007-05-24","2007-05-23"]
["CF19100","AWARD: CLOC Contruction Package - FY06","2006-06-22","2006-06-22"]
["CF19103","AWARD: CLOC Contruction Package - FY07","2006-10-02","2006-10-02"]
["CF19106","AWARD: CLOC Contruction Package - FY08","2007-10-01","2007-10-01"]
["CF19110","AWARD: CLOC SITEWORK, Landscape & Parking - FY06","2006-06-22","2006-06-22"]
["CF19113","AWARD: CLOC SITEWORK, Landscape & Parking - FY07","2006-10-02","2006-10-02"]
["CF19116","AWARD: CLOC SITEWORK, Landscape & Parking - FY08","2007-10-01","2007-10-01"]
["CF19120","SITEWORK, Landscape and Parking","2006-07-17","2008-09-24"]
["CF19130","Concrete","2006-09-12","2008-06-26"]
["CF19140","Masonry","2006-09-12","2008-06-26"]
["CF19150","Metals","2006-09-12","2008-06-26"]
["CF19160","Wood and Plastics","2006-12-07","2008-09-22"]
["CF19170","Thermal & Moisture Protection","2006-12-07","2008-09-22"]
["CF19180","Doors & Windows","2006-12-07","2008-09-22"]
["CF19190","Finishes","2006-12-07","2008-09-22"]
["CF19200","Specialtieis","2006-12-07","2008-09-22"]
["CF19210","Equipment","2006-12-07","2008-09-22"]
["CF19220","Furnishings","2006-12-07","2008-09-22"]
["CF19230","Special Construction","2006-12-07","2008-09-22"]
["CF19240","Conveying Systems","2006-12-07","2008-09-22"]
["CF19250","Mechanical","2006-12-07","2008-09-22"]
["CF19260","Electrical","2006-12-07","2008-09-22"]
["CF19270","Commissioning & Punchlist","2008-06-03","2008-09-24"]
["CF19280","Testing and Certification","2008-09-25","2008-10-08"]
["CF19290","COMP: CLOC Construction","2008-10-09","2008-10-08"]
["CF1933050","AVAIL: Beneficial Occupancy CLOC","2008-10-09","2008-10-08"]
["CF1933100","CLOC - CF Project Close Out","2008-10-09","2008-12-17"]
["CF1933200","COMP: Central Lab Office Ctr Final Acceptance","2009-01-02","2008-12-19"]
["CFACC1100","Start Access Tunnel","2006-07-25","2006-07-24"]
["CFBD1320","Start Electron Beam Dump","2006-09-08","2006-09-07"]
["CFBID1560","Start Bid Package Phase 1","2006-02-28","2006-02-27"]
["CFBID1640","Phase 1 Subcontract Execution","2006-05-24","2006-05-23"]
["CFBID2200","Start Bid Package Phase 2","2006-04-18","2006-04-17"]
["CFBOD2260","Phase 2 Subcontract Execution","2006-07-31","2006-07-28"]
["CFBTH2000","Start FFTB Removal","2006-07-21","2006-07-20"]
["CFCLC5000","Start Commissioning","2008-06-04","2008-06-03"]
["CFCLS2000","Start Central Laboratory Office Complex","2006-07-17","2006-07-14"]
["CFCUP1120","Start Central Utility Plant","2006-07-17","2006-07-14"]
["CFFEE1100","Start Front End Enclosure","2006-08-23","2006-08-22"]
["CFFEH1180","Start FEH Cavern","2006-11-22","2006-11-21"]
["CFLNF_0010","Develop as-built package Linac Facilitiy","2005-08-08","2005-10-31"]
["CFLNF_0020","Utility investigation Linac Facility","2005-11-01","2005-12-09"]
["CFLNF_0070","MD Support Title 1 Linac Facility","2005-06-13","2005-11-14"]
["CFLNF_0075","Additional MD Support Title 1 Linac Facility","2006-01-03","2006-04-03"]
["CFLNF_0230","Additional Utility Investigation Linac Fac","2006-01-09","2006-03-13"]
["CFLNF_1130","COMP: Title 1 Linac Facility","2006-03-14","2006-03-13"]
["CFLNF_1150","Sector 24 - Stairwells Design","2005-06-07","2005-09-09"]
["CFLNF_1170","Fabricate Sector 24 Stairwells","2005-09-02","2005-09-30"]
["CFLNF_1180","Fabricate Sector 24 Stairwells Enclosure","2005-09-12","2005-10-07"]
["CFLNF_1210","Install Sector 24 Stairwells","2005-10-10","2005-10-24"]
["CFLNF_1230","COMP: Sector 24 Stairwells Installation","2005-10-25","2005-10-24"]
["CFLNF_1510","User mtg.-interior layout details Linac Facility","2006-03-14","2006-04-10"]
["CFLNF_1520","User Review and Approval Linac Facility","2006-04-11","2006-05-01"]
["CFLNF_2010","Multi-Discipline Developmt Phase Linac Facility","2006-05-02","2006-06-27"]
["CFLNF_2020","User Review and Approval Linac Facility","2006-06-28","2006-07-26"]
["CFLNF_2030","Consultant Modify drwgs as necessary Linac Facil","2006-07-27","2006-08-23"]
["CFLNF_2040","Consultants provide 100% dwgs Linac Facility","2006-08-24","2006-09-21"]
["CFLNF_2050","COMP: Title 2 Linac Facility","2006-09-22","2006-09-21"]
["CFLNF_2145","Additional MD Support Title 2 Linac Facility","2005-11-07","2005-11-30"]
["CFLNF_2150","MD Support Title 2 Linac Facility","2006-05-02","2006-07-26"]
["CFLNF_3010","Start Construction Linac Facility","2006-10-03","2006-10-02"]
["CFLNF_3020","AWARD: T3 Construction Package (Linac)","2006-10-02","2006-10-02"]
["CFLNF_3030","MD Title 3 Support - Linac","2006-10-03","2007-02-27"]
["CFLNF_3040","Install Utilities Linac Facility","2006-10-03","2007-04-10"]
["CFLNF_3050","Install Interior Utilities Electrical","2006-10-03","2007-04-10"]
["CFLNF_3060","Building Complete Linac Facility","2007-04-11","2007-04-10"]
["CFLNF_3070","Building Commissioning Linac Facility","2007-04-11","2007-06-06"]
["CFLNF_3080","Project Punch List Linac Facility","2007-04-11","2007-06-06"]
["CFLNF_3090","Drawing Implementation to SLAC System","2007-06-07","2007-06-20"]
["CFLNF_3100","AVAIL: Beneficial Occupancy Linac Facility","2007-04-11","2007-04-10"]
["CFLNF_3120","COMP: Linac Facility  Final Acceptance","2007-06-21","2007-06-20"]
["CFMGT_1001","AWARD: Dispute Resolution Board - FY07","2006-10-02","2006-10-02"]
["CFMGT_1005","AWARD: Dispute Resolution Board - FY08","2007-10-01","2007-10-01"]
["CFMGT_1018","Management - PED (remaining)","2005-05-02","2005-09-30"]
["CFMGT_1020","Management - FY06","2005-10-03","2006-09-29"]
["CFMGT_1040","Construction Management Consulting - PED","2005-05-02","2005-09-30"]
["CFMGT_1045","Cost Account Managers-Phase 2 (add)","2005-06-01","2005-09-30"]
["CFMGT_1050","Cost Account Managers - FY06","2005-10-03","2006-09-29"]
["CFMGT_1051","Cost Account Managers-Phase 2 (remaining)","2005-05-02","2005-09-30"]
["CFMGT_1056","HVAC Specialist (remaining)","2005-05-02","2005-05-31"]
["CFMGT_1070","AWARD: Construction Management Consulting - FY06","2005-10-03","2005-10-03"]
["CFMGT_1076","AWARD: Construction Management Pkg - FY06(LLP)","2005-10-17","2005-10-17"]
["CFMGT_1077","Phase 1 Construction Management","2005-10-21","2006-03-31"]
["CFMGT_1078","AWARD: Construction Management Pkg - FY06 (C)","2006-04-03","2006-04-03"]
["CFMGT_1080","Phase 2 Construction Management + Fee - FY06","2006-04-04","2006-10-02"]
["CFMGT_1082","A&E Title 2 Support  RSY-CLOC (Reimb Apr Accr)","2005-05-02","2005-05-06"]
["CFMGT_1084","AWARD: A&E Title 3 Support for RSY-CLOC","2006-02-07","2006-02-07"]
["CFMGT_1086","A&E Title 2 Support  RSY-CLOC (Reimbursables)","2005-05-02","2006-02-06"]
["CFMGT_1087","A&E Support for Title 3 RSY-CLOC","2006-04-03","2007-11-12"]
["CFMGT_1088","A&E Title 3 Support for RSY-CLOC (reimbursables)","2006-04-03","2007-11-12"]
["CFMGT_1089","A&E Title 3 Support for RSY-CLOC (Mod 2)","2006-04-03","2007-11-12"]
["CFMGT_1090","Construction Management Consulting - FY06","2005-10-03","2006-09-29"]
["CFMGT_1099","AWARD: Dispute Resolution Board - FY06","2006-05-08","2006-05-08"]
["CFMGT_1100","Consumable Supplies - FY06","2005-10-03","2006-09-29"]
["CFMGT_1105","Consumable Supplies - PED (remaining)","2005-05-02","2005-09-30"]
["CFMGT_1109","Dispute Resolution Board (FY06)","2006-05-09","2007-05-07"]
["CFMGT_1110","Student Research Analyst - PED","2005-05-02","2005-09-30"]
["CFMGT_1115","Student Research Analyst - LLP","2006-02-06","2008-09-30"]
["CFMGT_1119","Dispute Resolution Board (FY07)","2007-05-08","2007-10-08"]
["CFMGT_1120","Management - FY07","2006-10-02","2007-09-28"]
["CFMGT_1125","Travel - FY06","2005-10-03","2006-09-29"]
["CFMGT_1129","Dispute Resolution Board (FY08)","2007-10-09","2008-10-08"]
["CFMGT_1130","Management - FY08 and Beyond","2007-10-01","2009-03-31"]
["CFMGT_1134","Travel - FY05 (remaining)","2005-05-02","2005-09-30"]
["CFMGT_1145","Travel - FY07","2006-10-02","2007-09-28"]
["CFMGT_1155","Travel - FY08","2007-10-01","2008-09-30"]
["CFMGT_1160","Construction Management Consulting - FY07","2006-10-02","2007-09-28"]
["CFMGT_1170","COMP: Conventional Facilities","2009-04-01","2009-03-31"]
["CFMGT_1175","CF Controls Liaison FY05Q2-Q4 (remaining)","2005-05-02","2005-09-30"]
["CFMGT_1180","Construction Management Consulting - FY08","2007-10-01","2008-09-29"]
["CFMGT_1190","Consumable Supplies - FY07","2006-10-02","2007-09-28"]
["CFMGT_1200","Consumable Supplies - FY08","2007-10-01","2008-09-30"]
["CFMGT_1210","Electrical Engineer - PED","2005-09-01","2005-09-30"]
["CFMGT_1220","Electrical Engineer - FY06","2005-10-03","2006-09-29"]
["CFMGT_1230","Geotechnical Baseline Report","2005-09-12","2006-03-31"]
["CFMGT_1250","Cost Account Managers - FY07","2006-10-02","2007-09-28"]
["CFMGT_1260","Cost Account Managers - FY08 and Beyond","2007-10-01","2009-03-31"]
["CFMGT_1270","Electrical Engineer - FY07","2006-10-02","2007-09-28"]
["CFMGT_1280","Electrical Engineer - FY08 and Beyond","2007-10-01","2009-03-31"]
["CFMGT_1305","AWARD: Phase 2 CM + Fee - FY07","2006-10-02","2006-10-02"]
["CFMGT_1310","Phase 2 Construction Management + Fee - FY07","2006-10-03","2007-10-01"]
["CFMGT_1315","AWARD: Phase 2 CM + Fee - FY08","2007-10-01","2007-10-01"]
["CFMGT_1317","AWARD: Phase 2 CM + Fee - FY09","2008-10-01","2008-10-01"]
["CFMGT_1320","Phase 2 Construction Management + Fee - FY08","2007-10-02","2008-12-18"]
["CFMGT_1330","AWARD: Construction Management Consulting - FY07","2006-10-02","2006-10-02"]
["CFMGT_1340","AWARD: Construction Management Consulting - FY08","2007-10-01","2007-10-01"]
["CFMGT_1500","UTR Support for Construction","2005-08-15","2005-12-16"]
["CFMGT_1510","UTR Support for Construction","2005-08-15","2006-09-01"]
["CFMGT_1520","UTR Support for Construction","2005-08-15","2006-12-01"]
["CFMGT_1530","UTR Support for Construction","2006-01-09","2006-03-24"]
["CFMGT_1540","UTR Support for Construction","2006-01-09","2006-11-09"]
["CFMGT_1550","UTR Support for Construction","2006-01-09","2007-02-26"]
["CFMGT_1600","Fire Protection Engineer","2005-12-05","2006-02-28"]
["CFMGT_2000","Reproduction - 30% Design","2005-08-22","2006-04-28"]
["CFMGT_2001","EP Produce Sampling Plan (remaining)","2005-05-02","2005-05-18"]
["CFMGT_2005","Reproduction - 60% and 100% Design","2006-03-06","2006-10-24"]
["CFMGT_2006","EP Develop Statement of Work (remaining)","2005-05-02","2005-05-18"]
["CFMGT_2010","Additional ICE - 60% Review","2006-01-03","2006-01-31"]
["CFMGT_2020","Additional ICE - 100% Review","2006-03-02","2006-03-29"]
["CFMGT_2022","CF Management & Integration","2006-03-01","2006-04-25"]
["CFMGT_2025","Review Bids for EP Site Analysis","2005-08-02","2005-08-08"]
["CFMGT_2030","AWARD: Contract for EP Site Analysis","2005-11-14","2005-11-14"]
["CFMGT_2035","EP Site Analysis/Site Characterization","2006-01-09","2006-05-02"]
["CFMGT_2040","EP Excavated Material Disposition Plan","2006-02-22","2006-03-21"]
["CFMGT_2070","MTH - Structural & Electrical Design (LLP)","2005-05-17","2006-03-13"]
["CFMGT_2090","Mechanical Design Consultancy","2005-09-26","2006-03-31"]
["CFMGT_2093","AWARD: Structural & Electrical Design for LCLS","2006-02-13","2006-02-13"]
["CFMGT_2095","Structural & Electrical Design for LCLS","2006-02-14","2006-08-03"]
["CFMGT_2230","A&E Interim Support (cost growth)","2005-08-08","2005-08-26"]
["CFMGT_2240","A&E Title 1 Reimbursables (cost growth)","2005-06-06","2005-07-01"]
["CFMGT_LOE","CF LOE Complete","2009-04-01","2009-03-31"]
["CFMMF_2095","Additional A&E Title 2 Design for MMF","2005-08-08","2005-09-30"]
["CFMMF_2096","MTH Engineering Design for MMF LLP (Committed)","2005-05-02","2005-05-27"]
["CFMMF_2116","MTH Electrical Engrg Svc - Feeder B081","2005-06-07","2005-09-30"]
["CFMMF_2700","CF - Drawing Implementation to SLAC System- MMF","2006-03-08","2006-05-10"]
["CFMMF_3005","MMF Relocate Stores - SLAC","2005-05-09","2005-08-15"]
["CFMMF_3040","AWARD: MMF Major Electrical Equip (LLP)","2006-01-17","2006-01-17"]
["CFMMF_3045","Receive  B81 Transformer (LLP)","2005-08-30","2005-08-30"]
["CFMMF_3047","Receive  B81 MCC  (LLP)","2005-11-07","2005-11-07"]
["CFMMF_3050","SLAC - MMF Major Elec Equipment","2006-03-15","2006-03-28"]
["CFMMF_3055","SLAC - Install MMF Major Elec Equip (LLP)","2006-01-25","2006-03-14"]
["CFMMF_3060","CF - MMF Modify Bldg Lighting & Power","2005-09-01","2006-01-11"]
["CFMMF_3075","AE Engineering Support Title 3 - MMF","2005-08-01","2006-02-01"]
["CFMMF_3110","MMF - Kickoff Meeting","2005-08-23","2005-08-23"]
["CFMMF_3165","CF - Site Preparation","2005-09-01","2005-10-27"]
["CFMMF_3173","AWARD: Building Commissioning MMF","2006-01-17","2006-01-17"]
["CFMMF_3175","CF Building Commissioning MMF","2006-02-07","2006-04-11"]
["CFMMF_3195","COMP: Magnetic Measure Facility Title 3","2006-05-11","2006-05-10"]
["CFMMF_3200","AVAIL: Beneficial Occupancy MMF","2006-03-02","2006-03-01"]
["CFMMF_4000","MMF - General Requirements","2005-09-01","2006-01-31"]
["CFMMF_4005","LLP - Structural Steel","2005-09-01","2005-10-25"]
["CFMMF_4010","LLP - Fire Sprinkler","2005-12-09","2006-01-20"]
["CFMMF_4020","LLP - Mechanical AHUs","2005-09-26","2005-12-07"]
["CFMMF_4030","LLP - Crane Equipment","2005-09-12","2005-12-29"]
["CFMMF_4040","LLP - Mechanical EFs","2005-09-12","2005-11-03"]
["CFMMF_4050","LLP - Doors, Frames & Hardware","2005-09-01","2005-09-29"]
["CFMMF_4060","MMF - Site Mobilization","2005-08-30","2005-09-06"]
["CFMMF_4070","MMF - Site Demolition","2005-09-07","2005-10-07"]
["CFMMF_4073","MMF - Site Demolition - Safe-Off Gas","2005-10-10","2005-10-10"]
["CFMMF_4075","MMF - Install protection @ Carousel","2005-09-06","2005-09-12"]
["CFMMF_4078","MMF - Build New Demising Walls","2005-09-13","2005-10-04"]
["CFMMF_4080","Building Shell - Footings","2005-10-10","2005-10-24"]
["CFMMF_4100","Building Shell - MEP - install & layout","2005-10-04","2005-10-31"]
["CFMMF_4110","Building Shell - MEP -Insulate High Bays","2005-10-21","2005-10-25"]
["CFMMF_4120","Building Shell - MEP - install OH Piping","2005-10-06","2005-11-02"]
["CFMMF_4130","Building Shell - MEP - Install Conduit","2005-10-11","2005-12-01"]
["CFMMF_4140","Building Shell - Underground Utilities","2005-10-25","2005-10-27"]
["CFMMF_4145","Change Order Requests","2006-01-09","2006-02-27"]
["CFMMF_4150","Building Shell - Erect Steel","2005-10-26","2005-11-15"]
["CFMMF_4160","Building Shell - Install Crane Support","2006-01-03","2006-01-23"]
["CFMMF_4170","Building Shell - SOG Concrete Patch","2005-11-11","2005-11-15"]
["CFMMF_4175","Fill void under concrete slab","2006-01-09","2006-02-27"]
["CFMMF_4178","Change Order Requests","2006-01-09","2006-02-27"]
["CFMMF_4180","Building Shell - Install GV / Flashing","2005-11-04","2005-11-08"]
["CFMMF_4190","Building Shell - Install Metal Panels","2005-11-04","2005-11-08"]
["CFMMF_4200","Building Shell - Install Exterior Door Frames","2005-11-09","2005-11-11"]
["CFMMF_4210","Building Shell - Install AHU & MAU/Ducting-Mech","2005-12-08","2006-01-03"]
["CFMMF_4215","Building Shell - Install AHU & MAU/Ducting-Elect","2005-12-08","2006-01-03"]
["CFMMF_4220","LAB TI - Frame Walls","2005-11-04","2005-11-09"]
["CFMMF_4230","LAB TI - In Wall MEP Rough-In","2005-11-07","2005-11-11"]
["CFMMF_4240","LAB TI - Install Finishes","2005-11-10","2005-11-28"]
["CFMMF_4250","LAB TI - Wall Construction","2005-11-28","2005-11-28"]
["CFMMF_4255","LAB TI - Install T-Bar Ceiling","2005-11-22","2005-11-30"]
["CFMMF_4260","LAB TI - Install Registers & Trim Fire Sprinkler","2005-12-01","2005-12-08"]
["CFMMF_4270","LAB TI - Install Light Fixtures","2005-12-09","2005-12-13"]
["CFMMF_4280","LAB TI - Install Ceiling Tile","2005-12-14","2005-12-16"]
["CFMMF_4290","LAB TI - Seal Floors / Epoxy Floors","2005-12-19","2005-12-27"]
["CFMMF_4295","Change Order Requests","2006-01-09","2006-02-27"]
["CFMMF_4300","LAB TI - Finish ProcessPiping","2005-12-28","2006-01-05"]
["CFMMF_4305","Change Order Requests","2006-01-09","2006-02-27"]
["CFMMF_4310","LAB TI - Finish MEP Trim","2006-01-06","2006-01-12"]
["CFMMF_4315","Relocate Electrical Conduit","2006-01-09","2006-02-27"]
["CFMMF_4318","Change Order Requests","2006-01-09","2006-02-27"]
["CFMMF_4320","HVAC Startup & Commissioning","2006-01-24","2006-01-31"]
["CFMMF_4500","COMP: MMF Certificate of Occupancy","2006-02-28","2006-02-27"]
["CFMMF_5010","CF - Data & Voice Cabling","2006-01-03","2006-03-01"]
["CFMMF_5020","CF - Testing and Balancing","2006-02-15","2006-03-01"]
["CFMOB1000","Commence Sitework","2006-05-24","2006-05-23"]
["CFMOB1040","Mobilization","2006-05-24","2006-05-23"]
["CFMOB1100","SWPP & Site Construction Fencing","2006-05-24","2006-05-23"]
["CFNEH1100","Start Near Experimental Hall","2006-07-13","2006-07-12"]
["CFPC8020","Start Project As-Builts & O/M Manuals","2008-11-13","2008-11-12"]
["CFRY102020","Start Research Yard Modifications","2006-05-24","2006-05-23"]
["CFRYB_2215","MD Support For Title 2 Design (remaining)","2005-05-02","2005-08-30"]
["CFRYC_2745","Kickoff Meeting - CM/GC","2005-10-19","2005-10-19"]
["CFS20_2196","MTH Engineering Services for S 20 LLP (Commit)","2005-05-02","2005-05-31"]
["CFS20_2198","Additional MTH Engineering Services for S-20 LLP","2005-08-08","2005-11-30"]
["CFS20_2206","Additional A&E Title 2 Design for S20","2005-08-08","2005-09-30"]
["CFS20_2800","Drawing Implementation to SLAC System- S20","2006-02-22","2006-05-10"]
["CFS20_3002","Remove Alcove Pump Room (remaining)","2005-05-02","2005-08-12"]
["CFS20_3003","Temporary Power & Phone","2005-09-01","2005-12-16"]
["CFS20_3013","Relocate RF Hut Piping","2005-10-03","2005-10-31"]
["CFS20_3015","RF Hut Clear Area (remaining)","2005-05-02","2005-08-12"]
["CFS20_3016","Receive S20 MtrCntlCntr - Hardware","2005-08-15","2005-08-15"]
["CFS20_3017","Receive S20 SubStation - Hardware","2005-09-27","2005-09-27"]
["CFS20_3040","Kick off  - Alcove/RF Hut","2005-08-23","2005-08-23"]
["CFS20_3070","AE Engineering Support Title 3 - Alcove/RF Hut","2005-08-01","2006-02-01"]
["CFS20_3195","AVAIL: RF Hut Shell Beneficial Occupancy","2006-01-30","2006-01-27"]
["CFS20_3225","AWARD: Building Commissioning Alcove","2006-01-17","2006-01-17"]
["CFS20_3230","CF Building Commissioning Alcove","2006-01-24","2006-04-11"]
["CFS20_3250","COMP: Alcove Title 3","2006-05-11","2006-05-10"]
["CFS20_3260","AVAIL: Alcove Beneficial Occupancy","2006-03-02","2006-03-01"]
["CFS20_4000","S20 - General Requirement","2005-09-01","2006-02-14"]
["CFS20_4002","K10B - General Requirement","2005-09-13","2005-11-30"]
["CFS20_4005","Site Mobilization","2005-08-30","2005-09-02"]
["CFS20_4010","Site Construction - Demolition","2005-09-06","2005-10-10"]
["CFS20_4020","Demolition - Electrical","2005-10-11","2005-10-12"]
["CFS20_4030","Demolition - Mechanical","2005-10-11","2005-11-02"]
["CFS20_4040","Structural - Footings & Grade Beams","2005-10-11","2005-10-31"]
["CFS20_4050","Structural - SOG","2005-11-08","2005-11-21"]
["CFS20_4060","Structural - Erect Struct Steel (Emerg Access)","2005-11-08","2005-11-21"]
["CFS20_4070","Building Encl - Roof Decking/Insulate Ceiling","2005-11-22","2005-12-09"]
["CFS20_4080","Building Enclosure - Door Frames","2005-11-29","2005-11-29"]
["CFS20_4090","Overhead MEP - Mechanical","2005-12-12","2005-12-27"]
["CFS20_4095","Overhead MEP - Mechanical - LLP","2005-10-03","2005-12-06"]
["CFS20_4100","Overhead MEP - Electrical","2005-11-09","2005-12-12"]
["CFS20_4110","Wall Construction - Frame Walls","2005-12-13","2005-12-19"]
["CFS20_4120","Wall Construction - MEP Rough-In","2005-12-20","2005-12-28"]
["CFS20_4130","Wall Construction - Install Door Frames","2005-12-20","2005-12-21"]
["CFS20_4140","Wall Construction - Insulate Walls","2005-12-12","2005-12-13"]
["CFS20_4150","Wall Construction - Rock Walls & Finish Walls","2005-12-22","2006-01-03"]
["CFS20_4160","T-Bar Ceiling - Install T-Bar Ceiling","2006-01-04","2006-01-10"]
["CFS20_4170","T-Bar Ceiling - Install Fixtures","2006-01-11","2006-01-13"]
["CFS20_4180","T-Bar Ceiling - Install Diffusers & Fire Sprinkl","2006-01-11","2006-01-19"]
["CFS20_4190","T-Bar Ceiling - Trim Vesda","2006-01-13","2006-01-17"]
["CFS20_4200","T-Bar Ceiling - Drop Tile","2006-01-18","2006-01-19"]
["CFS20_4210","Finishes - Paint Walls","2006-01-18","2006-01-24"]
["CFS20_4220","Finishes - Install Trim MEP","2006-01-25","2006-01-26"]
["CFS20_4230","Finishes - Install Floor Treatment","2006-01-27","2006-01-31"]
["CFS20_4240","Finishes - Install Doors & Hardware","2006-01-25","2006-01-26"]
["CFS20_4250","Finishes - Install Overhead Crane","2006-01-25","2006-01-26"]
["CFS20_4260","RF Hut - Install Frame Walls/Ceiling","2005-12-13","2005-12-19"]
["CFS20_4270","RF Hut - Set Door Frame","2005-12-20","2005-12-20"]
["CFS20_4280","RF Hut - MEP Wall Rough-In","2005-12-21","2005-12-29"]
["CFS20_4290","RF Hut - Install Insulation","2006-01-03","2006-01-03"]
["CFS20_4300","RF Hut - Install Finishes","2006-01-04","2006-01-18"]
["CFS20_4310","RF Hut - Install Door Hardware","2006-01-19","2006-01-19"]
["CFS20_4315","Change Order Requests","2006-01-09","2006-02-27"]
["CFS20_4320","RF Hut - Install Light Fixtures & Vesda","2006-01-19","2006-01-23"]
["CFS20_4330","RF Hut - Set Fan Coil & connect Piping","2006-01-24","2006-01-27"]
["CFS20_4340","Klystron Gallery - Chilled Water Piping","2005-11-14","2005-12-19"]
["CFS20_4350","Klystron Gallery - Cable Trays","2005-11-14","2005-12-29"]
["CFS20_4360","Equipment Yard - Demolition","2005-10-11","2005-10-13"]
["CFS20_4370","Structural - Equipment Pads/Footings","2005-10-14","2005-11-03"]
["CFS20_4380","Structural - Structural Support","2005-11-04","2005-11-08"]
["CFS20_4390","Equipment Yard - Install Groundiing","2005-11-04","2005-11-10"]
["CFS20_4400","Equipment Yard - Patch AC","2005-11-11","2005-11-11"]
["CFS20_4410","K10B - Demolition","2005-09-13","2005-09-16"]
["CFS20_4420","K10B - Underground Electrical","2005-09-13","2005-10-17"]
["CFS20_4430","K10B - Concrete Foundations & SOG","2005-09-13","2005-09-23"]
["CFS20_4435","Change Order Requests","2006-01-09","2006-02-27"]
["CFS20_4440","K10B - Install Equipment","2005-10-10","2005-11-18"]
["CFS20_4450","K10B - Fencing & Grating","2005-11-21","2005-11-29"]
["CFS20_4455","COMP: K10B Stubstation","2006-02-28","2006-02-27"]
["CFS20_4460","Install HVAC System - Mechanical","2005-11-21","2006-01-05"]
["CFS20_4470","HVAC System - Install Electrical","2005-12-19","2006-01-05"]
["CFS20_4480","Install Chilled Water System - Mechanical","2005-11-21","2005-12-15"]
["CFS20_4490","Chilled Water System - Install Electrical","2005-12-06","2005-12-12"]
["CFS20_4500","Install Hot Water System - Mechanical","2005-11-23","2005-12-19"]
["CFS20_4510","Hot Water System - Install Electrical","2005-12-20","2005-12-28"]
["CFS20_4520","Install Compressed Air & City Water","2005-11-29","2005-12-06"]
["CFS20_4530","Injector Housing - Layout & Concrete Demo","2005-11-04","2005-11-11"]
["CFS20_4535","Change Order Requests","2006-01-09","2006-02-27"]
["CFS20_4540","K10B - Set Equipment","2005-09-26","2005-10-07"]
["CFS20_4542","K10B -  Install Finishes","2005-11-30","2005-11-30"]
["CFS20_4545","Injector Housing - Modify Stairs","2005-11-14","2005-11-29"]
["CFS20_4548","Change order Requests","2006-01-09","2006-02-27"]
["CFS20_4550","Injector Housing - Install Sump","2005-11-14","2005-11-18"]
["CFS20_4555","Injector Housing - Install LCWS & R Piping","2005-11-30","2005-12-06"]
["CFS20_4560","Injector Housing - Install Electrical","2005-12-01","2005-12-14"]
["CFS20_4565","K10B - Change Order Requests","2006-01-09","2006-02-27"]
["CFS20_4570","Injector Housing - Paint Surfaces","2005-12-15","2005-12-28"]
["CFS20_4575","Change Order Requests","2006-01-09","2006-02-27"]
["CFS20_4577","DCC Controls Installation","2006-01-09","2006-02-27"]
["CFS20_4578","Change Order Requests","2006-01-09","2006-02-27"]
["CFS20_4580","Start-up & Commissioning - Mechanical","2006-02-07","2006-02-13"]
["CFS20_4590","Start-up & Commissioning - Electrical","2006-01-24","2006-02-07"]
["CFS20_4600","Start-up & Commissioning - HVAC Balancing","2006-02-14","2006-03-01"]
["CFS20_4610","COMP: Sector 20 Certificate of Occupancy","2006-03-02","2006-03-01"]
["CFUH01020","Start Undulator Hall","2006-08-25","2006-08-24"]
["CFXRY1220","Start X-Ray Transport & Diagnostic","2007-01-04","2007-01-03"]
["IJ0101A","Management - PED","2005-05-02","2005-09-30"]
["IJ0101B","Management - CONST","2005-10-03","2009-03-30"]
["IJ0101C","Cost Account Managers - PED","2005-05-02","2005-09-30"]
["IJ0101D","Cost Account Managers - CONST","2005-10-03","2009-03-30"]
["IJ0101S","Computers - PED","2005-05-02","2005-09-30"]
["IJ0101S1","Computers - CONST","2005-10-03","2009-03-30"]
["IJ0101S10","SLAC Place Order Computers - PED","2005-05-02","2005-05-04"]
["IJ0101S20","RCV: Computers - PED","2005-05-05","2005-05-04"]
["IJ0101S21","SLAC Place Order Computers - CONST","2005-10-03","2005-11-11"]
["IJ0101S22","RCV: Computers - CONST","2005-11-14","2005-11-11"]
["IJ0101T","Travel - PED","2005-05-02","2005-09-30"]
["IJ0101T1","Travel - CONST","2005-10-03","2009-03-30"]
["IJ0101U","Materials & Supplies - PED","2005-05-02","2005-09-30"]
["IJ0101U1","Materials & Supplies - CONST","2005-10-03","2009-03-30"]
["IJ02","INJECTOR CONTROLS SUBSYSTEM SUMMARY","2005-05-02","2007-08-29"]
["IJ0202","LLRF CONTROLS SUMMARY","2005-05-02","2007-08-06"]
["IJ02020055","Procure controls H/W (incl digitizer) and cables","2006-07-03","2006-09-29"]
["IJ02020075","RCV: controls H/W (incl digitizer) and cables","2006-10-02","2006-10-02"]
["IJ02020129","Write RF Software and Documentation - PED","2006-07-03","2006-10-05"]
["IJ02020130","Build RF Hardware & Write Documentation","2007-04-04","2007-04-24"]
["IJ02020131","Write RF Software and Documentation - CONST","2006-10-06","2006-10-26"]
["IJ02020141","Integrate & Test RF Control","2007-04-25","2007-08-06"]
["IJ02020180","AVAIL: LLRF Gun Controls Ready to Integrate","2007-04-25","2007-04-24"]
["IJ02020240","Procure Controls H/W (incl Digitizer) and Cables","2006-07-03","2006-09-29"]
["IJ02020250","SLAC Place Order Controls H/W (incl Digitizer)","2006-07-03","2006-08-14"]
["IJ02020303","RCV: Procured parts - LLRF L0-1 Controls","2006-08-15","2006-08-14"]
["IJ02020304","Build RF Control H/W and Write Docmntn - PED","2006-08-15","2007-01-25"]
["IJ02020306","Build RF Control H/W and Write Docmntn - CONST","2007-04-04","2007-04-17"]
["IJ02020307","Write RF Control S/W and Docmntn","2006-07-03","2006-08-14"]
["IJ02020308","Integrate and Test LLRF L0-1","2007-04-18","2007-05-21"]
["IJ02020365","AVAIL: LLRF L0-1 Controls Ready to Install","2007-05-22","2007-05-21"]
["IJ02020425","Procure Controls H/W (incl Digitizer) and Cables","2006-07-03","2006-09-29"]
["IJ02020435","SLAC Place Order Controls H/W (incl Digitizer)","2006-07-03","2006-08-14"]
["IJ02020495","RCV: Procured parts","2006-10-02","2006-09-29"]
["IJ02020505","AVAIL: Hardware for Install in RF Hut","2007-01-04","2007-01-03"]
["IJ02020508","Build RF Hardware and Write Documentation","2006-10-02","2007-01-03"]
["IJ02020516","Write RF Software Documentation","2006-07-03","2006-08-14"]
["IJ02020526","Integrate and Test LLRF L0-2","2007-01-04","2007-02-07"]
["IJ02020555","AVAIL: LLRF L0-2 Controls Ready to Install","2007-02-08","2007-02-07"]
["IJ02020615","Procure Controls H/W (incl Digitizer) and Cables","2006-07-03","2006-09-29"]
["IJ02020625","SLAC Place Order Controls H/W (incl Digitizer)","2005-05-02","2005-05-12"]
["IJ02020680","RCV: Procured parts","2006-10-02","2006-09-29"]
["IJ02020684","Build RF Hardware and Write Documentation","2006-10-02","2007-01-03"]
["IJ02020689","Write RF Software and Documentation","2006-07-03","2006-07-03"]
["IJ02020734","Integrate and Test RF Control","2007-01-04","2007-02-08"]
["IJ02020735","AVAIL: LLRF L1 S-Band Contrls Ready to Integrate","2007-02-09","2007-02-08"]
["IJ02020795","Procure Controls H/W (incl Digitizer) and Cables","2006-07-03","2006-09-29"]
["IJ02020805","SLAC Place Order Controls H/W (incl Digitizer)","2006-07-03","2006-08-14"]
["IJ02020860","RCV: Procured parts","2006-10-02","2006-09-29"]
["IJ02020864","Build RF Hardware and Write Documentation","2006-10-02","2007-01-03"]
["IJ02020870","Write RF Software and Documentation","2006-07-03","2007-01-03"]
["IJ02020880","Integrate and Test RF Control","2007-01-04","2007-02-08"]
["IJ02020915","AVAIL: LLRF L1 X-Band Contrls Ready to Integrate","2007-02-09","2007-02-08"]
["IJ02021830","Procure Contros H/W (incl Digitizer) and Cables","2006-07-03","2006-09-29"]
["IJ02021840","SLAC Place Order Contros H/W (incl Digitizer)","2006-07-03","2006-08-14"]
["IJ02021900","RCV: Procured parts","2006-10-02","2006-09-29"]
["IJ02021904","Build RF Hardware and Write Documentation","2006-10-02","2006-10-02"]
["IJ02021910","AVAIL: Hardware for Install in RF Hut","2006-10-03","2006-10-02"]
["IJ02021919","Write RF Sortware and Documentation","2006-07-03","2007-01-03"]
["IJ02021931","Integrate and Test RF Control","2006-10-03","2007-01-03"]
["IJ02021935","AVAIL:LLRF Tranv Cav Controls Ready to Install","2007-01-04","2007-01-03"]
["IJ0203","E-BEAM DIAG DISPLAY & CONTROLS SUMMARY","2006-05-25","2007-06-12"]
["IJ020302","CONTROLS - TOROIDS (5) SUMMARY","2006-07-03","2007-04-13"]
["IJ02030216","Procure 5 Sets Toroid Contrls H/W and Cables","2006-07-03","2006-08-30"]
["IJ02030226",null,"2005-05-02","2005-05-02"]
["IJ02030238","RCV: Procured parts - Toroid Controls","2006-08-31","2006-08-31"]
["IJ02030243","Build Toroid Hardware and Write Documentatin","2006-11-29","2007-02-20"]
["IJ02030244","Write Toroid Software and Documentation","2006-07-03","2006-09-07"]
["IJ02030250","Integrate Software and Hardware","2007-02-21","2007-04-13"]
["IJ02030256","AVAIL: Toroid Controls Ready for Install","2007-04-16","2007-04-13"]
["IJ02030316","Procure 4 Sets Faraday Cup Controls H/W & Cables","2006-10-26","2007-01-10"]
["IJ02030344","RCV: Procured parts - Faraday Cup Controls","2007-01-11","2007-01-11"]
["IJ02030356","Build H/W and Write Docmtn Faraday Cup Cntrl (4)","2007-01-12","2007-01-12"]
["IJ02030357","Write S/W and Docmtn Faraday Cup Control (4)","2006-10-25","2006-10-25"]
["IJ02030358","Integrate and Test Faraday Cup Control (4)","2007-01-16","2007-02-20"]
["IJ02030362","AVAIL: Faraday Cup Controls Ready for Install","2007-02-21","2007-02-20"]
["IJ02030416","Procure 1 set Tune-up Dump Controls H/W","2006-07-03","2006-08-30"]
["IJ02030422","RCV: Procured parts - Tune-Up Dump Controls","2006-08-31","2006-08-30"]
["IJ02030424","Write S/W - Tune-Up Dump Controls","2006-07-03","2006-08-28"]
["IJ02030426","Write Docs - Tune-Up Dump Controls","2006-07-03","2006-08-28"]
["IJ02030430","Assemble Tune-up Dump Controls","2006-08-31","2006-09-07"]
["IJ02030433","Integrate and Test Tune Up Dump","2006-09-08","2006-09-21"]
["IJ02030436","SLAC Place Order - Tune-Up Dump Controls","2006-07-03","2006-07-06"]
["IJ02030440","AVAIL: Tune-Up Dump Controls Ready for Install","2006-09-22","2006-09-21"]
["IJ02030516","Proc 11 sets Profile Mntr Cntrls H/W & Cables","2006-07-03","2006-08-30"]
["IJ02030526","SLAC Place Order - Profile Monitor Controls","2006-07-03","2006-08-14"]
["IJ02030556","RCV: Procured parts - Profile Monitor Controls","2006-08-31","2006-08-31"]
["IJ02030569","Build H/W and Write Docmntn Profile Monitor (11)","2006-09-01","2006-11-28"]
["IJ02030570","Write S/W and Docmntn Profile Monitors (11)","2006-07-03","2006-08-14"]
["IJ02030571","Integrate and Test Profile Monitors","2006-11-29","2007-03-09"]
["IJ02030574","AVAIL:Profile Monitor Controls Ready for Install","2007-03-12","2007-03-09"]
["IJ02030630","Build H/W and Write Docmntn for E/O Diagnostics","2006-05-25","2006-10-16"]
["IJ02030631","Write S/W and Docmtn E/O Diagnostics","2006-10-03","2007-03-12"]
["IJ02030632","Integrate and Test E/O Diagnostics Controls H/W","2006-11-30","2007-06-12"]
["IJ02030636","AVAIL: EO Diagnostic Controls Ready for Install","2007-06-13","2007-06-12"]
["IJ02030718","Proc 21 sets BPM Controls H/W and Cables","2006-07-05","2006-09-27"]
["IJ02030726","RCV: Procured parts - BPM Proc Module Cntrls","2006-09-28","2006-09-28"]
["IJ02030728","SLAC Place Order 21 sets BPM Ctrls H/W &Cables","2006-07-05","2006-08-15"]
["IJ02030738","Build H/W and Write Docmntn BPMs (21)","2006-10-03","2006-10-30"]
["IJ02030740","Integrate and Test BPM Controls","2006-10-31","2006-11-29"]
["IJ02030744","AVAIL:BPM Proc Module Controls Ready for Install","2007-03-27","2007-03-26"]
["IJ02030747","Procure BLM Controls Hdwr/Eq","2006-07-05","2006-08-01"]
["IJ02030767","RCV: BLM Controls Hdwr/Eq","2006-08-02","2006-08-02"]
["IJ0204","LASER CONTROLS SUMMARY","2006-01-12","2006-05-19"]
["IJ02040201","Procure 1 set Gun Laser Controls H/W","2006-01-12","2006-02-09"]
["IJ02040205","SLAC Place Order - Gun Laser Controls","2006-01-12","2006-02-24"]
["IJ02040210","RCV: Procured parts - Gun Laser Controls","2006-02-27","2006-02-24"]
["IJ02040215","Integrate and Test Gun Laser Controls","2006-02-27","2006-05-19"]
["IJ02040220","AVAIL: Laser Cntrls ready for Test","2006-05-22","2006-05-19"]
["IJ0205","LASER HEATER CONTROLS SUMMARY","2007-01-09","2007-08-29"]
["IJ02050201","Procure 1 set Laser Heater Controls H/W","2007-01-09","2007-04-09"]
["IJ02050205","SLAC Place Order - Laser Heater Cntrls","2007-01-09","2007-01-30"]
["IJ02050210","RCV: procured parts - Laser Heater Cntrls","2007-04-10","2007-04-09"]
["IJ02050215","Integrate and Test Laser Heater Controls","2007-04-10","2007-08-29"]
["IJ02050220","AVAIL: Laser Heater Cntrls Ready for Install","2007-08-30","2007-08-29"]
["IJ0206","TIMING CONTROLS SUMMARY","2006-03-01","2006-04-12"]
["IJ02060060","Procure Master & Distributed Timing Controls H/W","2006-03-01","2006-04-11"]
["IJ02060080","RCV: Master & Distributed Timing Controls H/W","2006-04-12","2006-04-12"]
["IJ02060105","Procure 4 sets of Controls Wire Scanners","2006-07-03","2006-09-26"]
["IJ02060110","Build HW and Write SW for Injector Wire Scanners","2006-09-27","2006-10-24"]
["IJ02060120","Integrate and Test Controls Wire Scanners","2006-10-25","2006-11-21"]
["IJ02060130","AVAIL: Controls Wire Scanners Ready for Install","2006-11-22","2006-11-21"]
["IJ0207","VACUUM CONTROLS SUMMARY","2005-10-26","2006-08-24"]
["IJ02070070","Procure Vacuum Controls Hardware and Cables","2005-10-26","2006-02-09"]
["IJ02070080","SLAC Place Order Vacuum Ctrls Hardware & Cables","2005-10-26","2005-12-08"]
["IJ02070195","RCV: Vacuum Controls Hardware and Cables","2006-02-10","2006-02-10"]
["IJ02070202","Build Vacuum H/W and Write Docmntn","2006-02-13","2006-03-03"]
["IJ02070210","Write Vacuum Documentation","2005-10-26","2005-11-08"]
["IJ02070216","Integration and Test Vacuum Controls","2006-06-29","2006-08-24"]
["IJ02070235","AVAIL: Vacuum Control Modules Ready for Install","2006-08-25","2006-08-24"]
["IJ0208","SOFTWARE & CNTRLS INFRASTRUCTURE SUMMARY","2005-06-01","2007-04-26"]
["IJ02080300","Supervision of installation","2006-04-03","2006-05-12"]
["IJ02080301","SEM Installtn (wall barrd & two 20 A circuits)","2006-04-03","2006-04-28"]
["IJ02080310","Procure singlemode fiber","2006-05-01","2006-06-26"]
["IJ02080314","Fiber termination","2006-06-27","2006-07-25"]
["IJ02080326","Procure Cisco 3550-24 hubs (4)","2007-03-29","2007-04-26"]
["IJ02080330","AVAIL: Data Comm Circuits Active & Ready","2007-04-27","2007-04-26"]
["IJ02080336",null,"2005-05-02","2005-05-02"]
["IJ02080340",null,"2005-05-02","2005-05-02"]
["IJ02080346","RCV: Cisco 3550-24 hubs (4)","2007-04-27","2007-04-26"]
["IJ02080350","RCV: singlemode fiber","2006-06-27","2006-06-26"]
["IJ020804","COMPUTER, CRATES, S/W & LICENCES SUMMARY","2005-06-01","2005-11-17"]
["IJ02080401","Procure Infrastructure Comp, Crates H/W & Cable","2005-06-01","2005-11-17"]
["IJ02080405","SLAC Place Order Infrastr Comp, CratesH/W&Cable","2005-06-01","2005-07-13"]
["IJ02080410","RCV: Infrastructure Comp, Crates H/W & Cable","2005-11-18","2005-11-17"]
["IJ02080415","AVAIL: Computers & Crates Ready for Instl","2005-11-18","2005-11-17"]
["IJ0209","POWER SUPPLY CONTROLS SUMMARY","2006-07-18","2006-07-24"]
["IJ02090065","Integrate software & hardware","2006-07-18","2006-07-24"]
["IJ02090085","AVAIL: Power Supply Cntrls Ready for Install","2006-07-25","2006-07-24"]
["IJ0210","PPS, BCS, MPS CONTROLS SUMMARY","2005-06-23","2006-03-21"]
["IJ02100065","Write S/W Docmtn for Power Supply Controls","2005-06-23","2005-07-28"]
["IJ02100070","Integrate and Test Power Supply Controls","2006-02-22","2006-03-21"]
["IJ02100085","AVAIL: PPS, BCS, MPS control software","2006-03-22","2006-03-21"]
["IJ03",null,"2005-05-02","2005-05-02"]
["IJ0301","DRIVE LASER R&D SUMMARY","2005-05-02","2005-12-16"]
["IJ03010025","UV conversion tests","2005-05-02","2005-12-02"]
["IJ03010030","Analysis and final report (UV convers)","2005-12-05","2005-12-16"]
["IJ03010045","Analysis and final report (Pulse Shaping)","2005-05-02","2005-05-02"]
["IJ03010050","COMP: UV conversion R&D","2006-01-03","2005-12-16"]
["IJ0302","DRIVE LASER SYSTEM SUMMARY","2004-10-16","2006-07-26",null,"2004-10-16"]
["IJ03020075","AWARD: Contract for Drive Laser","2005-06-27","2005-06-27"]
["IJ03020080","Drive Laser-Milestone 1","2005-10-21","2005-10-21"]
["IJ03020082","Reviews of Vendor's Progress","2005-08-09","2006-06-21"]
["IJ03020085","RCV: Drive Laser from Vendor","2006-07-27","2006-07-26"]
["IJ03020092","Drive Laser Design Review","2005-10-18","2005-10-20"]
["IJ03020096","REQD: Sector 20 Alcove Available for Eq Instl","2006-07-27","2006-07-26"]
["IJ03020097","REQD: Optical Tables Available","2006-07-27","2006-07-26"]
["IJ03020102","Drive Laser-Milestone 2","2006-01-06","2006-01-06"]
["IJ03020112","Drive Laser-Milestone 3","2006-03-29","2006-03-29"]
["IJ03020115","AVAIL: Drive Laser for Integration","2006-07-27","2006-07-26"]
["IJ03020122","Drive Laser-Milestone 4","2006-06-16","2006-06-16"]
["IJ03020132","Vendor Fab, Assy & Test - Drive Laser-stage 1","2005-06-28","2005-09-14"]
["IJ03020142","Vendor Fab, Assy & Test - Drive Laser-stage 2","2005-10-24","2006-01-05"]
["IJ03020152","Vendor Fab, Assy & Test - Drive Laser-stage 3","2006-01-09","2006-03-28"]
["IJ03020162","Vendor Fab, Assy & Test - Drive Laser-stage 4","2006-03-30","2006-06-15"]
["IJ0303","DRIVE LASER DIAGNOSTICS SUMMARY","2005-05-02","2006-09-08",null,"2005-05-02"]
["IJ03030005","Define Laser System Diagnostics Specs","2005-05-02","2005-08-22",null,"2005-05-02"]
["IJ03030015","Eng & Design of Drive Laser Diagnostics (Timing)","2005-08-23","2005-12-15"]
["IJ03030025","COMP: Drive Laser Diagnostics Eng & Design","2005-12-16","2005-12-15"]
["IJ03030030","Procure Streak Camera","2005-08-03","2006-02-07"]
["IJ03030035","Procure Oscillator Diagnostics","2005-12-16","2006-03-28"]
["IJ03030037","RCV:  Oscillator Diagnostics","2006-03-29","2006-03-29"]
["IJ03030040","Procure Preamplifier Diagnostics","2005-12-16","2006-03-28"]
["IJ03030042","RCV:  Preamplifier Diagnostics","2006-03-29","2006-03-29"]
["IJ03030045","Procure Final Amplifier Diagnostics","2005-12-16","2006-03-28"]
["IJ03030047","RCV:  Final Amplifier Diagnostics","2006-03-29","2006-03-29"]
["IJ03030050","Procure UV Conversion Diagnostics","2005-09-21","2005-12-15"]
["IJ03030055","RCV: Drive Laser Diagnostics & Streak Camera","2006-06-01","2006-05-31"]
["IJ03030060","Assemble & Checkout: Drive Laser Diagnostics","2006-06-01","2006-09-08"]
["IJ03030065","AVAIL: Drive Laser Diagnostics for Integ","2006-09-11","2006-09-08"]
["IJ03030070","SLAC Place Order Diagnostics","2006-03-29","2006-05-31"]
["IJ03030075","RCV: Streak Camera","2006-02-08","2006-02-08"]
["IJ03030080","Award for the Streak Camera","2005-08-02","2005-08-02"]
["IJ03030085","Eng &Design of Drive Laser Diagnostics (general)","2005-08-23","2005-12-15"]
["IJ03030090","Evaluate the proposals for the streak camera","2005-07-15","2005-08-01"]
["IJ0304","TIMING STABILITY MONITORING SUMMARY","2005-08-01","2006-08-22"]
["IJ03040005","Define Timing stability specs","2005-08-01","2005-08-05"]
["IJ03040010","Eng & Dsn of Timing Stability Monitoring App","2006-01-05","2006-03-03"]
["IJ03040015","Proc Timing Stability Apparatus","2006-03-06","2006-05-26"]
["IJ03040020","RCV: Timing stability Monitoring Apparatus","2006-05-30","2006-05-26"]
["IJ03040025","Assemble & C/O: Timing Stability Mon Apparatus","2006-05-30","2006-08-22"]
["IJ03040030","AVAIL: Timing Stability Monitoring Apparatus","2006-08-23","2006-08-22"]
["IJ03040035","SLAC Place Order Timing Stability Apparatus","2006-03-06","2006-04-14"]
["IJ03040040","Eng&Dsn of the Osc timing Stability measurement","2005-10-21","2006-01-19"]
["IJ0305","STEERING STABILITY FEEDBACK & MSMTS SUMMARY","2005-08-15","2006-04-10"]
["IJ03050005","Define Steering stability specs","2005-08-15","2005-08-19"]
["IJ03050030","Eng & Dsn of Steering Stability Measurement","2005-08-22","2005-11-14"]
["IJ03050045","COMP: Steering Stability Meas Engr & Design","2005-11-15","2005-11-14"]
["IJ03050060","Procure Steering Stability Apparatus","2005-11-15","2006-02-27"]
["IJ03050065","RCV: Steering Stability Apparatus","2006-02-28","2006-02-27"]
["IJ03050070","SLAC Place Order Steering Stability Apparatus","2005-11-15","2006-01-12"]
["IJ03050090","Assemble & Checkout: Steering Stabilization App","2006-02-28","2006-04-10"]
["IJ03050125","AVAIL:Steering Stability Apparatus for Install","2006-04-11","2006-04-10"]
["IJ0306","PREAMPLIFIER LOW PWR COMP SUMMARY","2005-12-16","2006-07-06"]
["IJ03060000","Define PreAmplifier Low Power Comp Specs","2005-12-16","2006-01-13"]
["IJ03060005","Design PreAmplifier Low Power Comp","2006-01-17","2006-03-14"]
["IJ03060010","COMP: PreAmplifier Low Power Comp Design","2006-03-15","2006-03-14"]
["IJ03060065","Procure Low Power Compressor System Parts","2006-03-15","2006-06-07"]
["IJ03060070","RCV: Low Power Compressor Parts","2006-06-08","2006-06-07"]
["IJ03060075","Fab (InHouse): Custom Low Power Compressor Parts","2006-03-15","2006-04-11"]
["IJ03060085","Assemble: Low Power Compressor","2006-06-08","2006-07-06"]
["IJ03060090","AVAIL: Low Power Compressor for Integration","2006-07-07","2006-07-06"]
["IJ0307","TRANSPORT TO TUNNEL & RELAY OPTICS SUMMARY","2005-05-02","2006-04-24"]
["IJ03070000","Define Beam path, Beam Properties & Model Xport","2005-05-02","2005-05-16"]
["IJ03070005","Eng & Dsn of  Vertical Transport Tube","2005-05-02","2005-08-12"]
["IJ03070010","COMP: Beam tube enclosure engr & Dsn","2005-10-19","2005-10-18"]
["IJ03070015","Procure Material and Parts","2005-08-15","2005-11-01"]
["IJ03070017","RCV: Material and Parts","2005-11-02","2005-11-02"]
["IJ03070023","AVAIL: Transport Tube for Installation","2005-11-03","2005-11-02"]
["IJ03070025","Define Spatial Filter(Vacuum) & Opt Relay","2005-05-31","2005-08-12"]
["IJ03070030","Eng & Dsn of Spatial Filter & Opt Relay","2005-08-15","2006-01-12"]
["IJ03070035","COMP: Spatial Filter & Opt Relay Eng & Dsn","2006-01-13","2006-01-12"]
["IJ03070040","FAB (inhouse): Custom Spatial Filter Hardware","2006-01-13","2006-02-10"]
["IJ03070045","RCV: Custom Spatial Filter Hardware","2006-02-13","2006-02-10"]
["IJ03070050","Procure Spatial Filter & Opt Relay Parts","2006-01-13","2006-04-10"]
["IJ03070055","RCV: Spatial Filter & Opt Relay Parts","2006-04-11","2006-04-10"]
["IJ03070060","Assemble: Spatial Filter & Opt Relay","2006-04-11","2006-04-24"]
["IJ03070065","AVAIL: Spatial Filter & Opt Relays for Integ","2006-04-25","2006-04-24"]
["IJ03070070","SLAC Place Order Custom Spatial Filter Hardware","2006-01-13","2006-02-03"]
["IJ03070075","SLAC Place Order Material and Parts","2005-08-15","2005-08-22"]
["IJ03070080","Design of Storage and Installation Fixtures","2005-08-15","2005-09-06"]
["IJ03070085","Write Installation Procedure","2005-08-15","2005-08-22"]
["IJ03070090","Dsn routing system for lsr heater transport","2005-08-23","2005-10-18"]
["IJ03070095","Release Drawings - transport tube","2005-11-02","2005-12-30"]
["IJ03070105","Release drawings - spatial filter","2006-01-13","2006-03-13"]
["IJ0308","UV LAUNCH,CONDITIONING & DIAGNOSTICS SUMMARY","2005-05-02","2006-05-22"]
["IJ03080010","Design UV Beam Xport & Launch Optics","2005-05-02","2005-05-05"]
["IJ03080015","Design UV Beam Steering Stabilization App","2005-05-06","2005-06-06"]
["IJ03080020","Design UV Spatial Profile Shaper","2005-05-02","2005-09-01"]
["IJ03080025","Eng & Dsn of Pulse Energy Control","2005-11-15","2005-12-14"]
["IJ03080030","Eng & Dsn of UV Diagnostic","2005-05-02","2005-06-30"]
["IJ03080035","COMP: UV Launch,Conditioning & Diag engr & Dsn","2005-12-15","2005-12-14"]
["IJ03080040","FAB (inhouse): Custom Parts","2005-12-15","2006-01-27"]
["IJ03080045","Procure UV Launch,Conditioning & Diag HW","2005-10-12","2005-10-18"]
["IJ03080050","RCV: UV Launch,Conditioning & Diag HW","2005-10-19","2005-10-18"]
["IJ03080055","Assemble & C/O: UV Launch & Conditioning System","2006-01-30","2006-05-22"]
["IJ03080060","AVAIL: UV Launch & Conditioning System","2006-05-23","2006-05-22"]
["IJ0309","LOAD LOCK TRANSPORT SYSTEM SUMMARY","2006-06-06","2007-02-13"]
["IJ03090000","Define Load Lock Transport System Specs","2006-06-06","2006-07-03"]
["IJ03090005","Eng & Dsn of Load Lock Transport System","2006-07-05","2006-08-29"]
["IJ03090035","COMP: Load Lock Transport System Engrg & Dsn","2006-08-30","2006-08-29"]
["IJ03090040","FAB (inhouse): Custom Load Lock Transport Sys HW","2006-08-30","2006-10-11"]
["IJ03090042","RCV: Custom Load Lock Transport Sys HW","2006-10-12","2006-10-11"]
["IJ03090045","Procure Load Lock Transport Sys Parts","2006-08-30","2006-11-22"]
["IJ03090050","RCV: Load Lock Transport Sys Parts","2006-11-27","2006-11-22"]
["IJ03090052","Install transport tubes and supports","2006-11-27","2006-12-15"]
["IJ03090055","Assemble, Integ & C/O:Load Lock Transport System","2007-01-02","2007-02-13"]
["IJ03090060","AVAIL: Load Lock Transport System","2007-02-14","2007-02-13"]
["IJ0325","VISIBLE OPTICAL TRANSPORT & DIAG SUMMARY","2006-03-06","2006-10-11"]
["IJ03250000","Define Visible Beam properties, Beam path/model","2006-03-06","2006-03-17"]
["IJ03250005","Define Visible Beam transport Diagnostics Rqmts","2006-03-20","2006-04-07"]
["IJ03250015","Design Visible Beam Transport Optics & Encl","2006-04-10","2006-05-05"]
["IJ03250025","Design Visible Beam Transport Diagnostics","2006-05-08","2006-06-05"]
["IJ03250035","COMP: Visible Beam transport Optics & encl engr","2006-05-08","2006-05-05"]
["IJ03250040","COMP: Visible Beam transport Diagnostics engr &","2006-06-06","2006-06-05"]
["IJ03250045","FAB (inhouse): Visible Beam Transport Tube","2006-08-02","2006-08-29"]
["IJ03250050","FAB (inhouse):Custom Visible Beam Xport Opt Supt","2006-08-02","2006-08-29"]
["IJ03250055","Procure Transport Tube Material","2006-05-08","2006-08-01"]
["IJ03250060","RCV: Procured Transport Tube Material","2006-08-02","2006-08-01"]
["IJ03250065","Procure Visible Beam Transport Optics & Diag HW","2006-05-08","2006-08-01"]
["IJ03250070","RCV: Visible Beam Transport Optics & Diag HW","2006-08-02","2006-08-01"]
["IJ03250085","Assemble: Visible Beam Transport Optics & Encl","2006-08-30","2006-09-27"]
["IJ03250100","Assemble: Visible Beam transport diagnostics","2006-09-28","2006-10-11"]
["IJ03250120","AVAIL: Visible Beam Transport & Encl","2006-09-28","2006-09-27"]
["IJ03250125","AVAIL: Visible Beam Transport Diagnostics","2006-10-12","2006-10-11"]
["IJ0328","LB INFRASTRUC & LB SYSTEM-WIDE & MISC. ITEMS SUM","2005-08-01","2006-09-21"]
["IJ03280000","Define Optical Table Specs","2005-10-21","2005-10-20"]
["IJ03280005","Design Optical Tables,","2005-10-21","2005-11-17"]
["IJ03280010","COMP: Optical Tables, Legs & Encl Engr & Dsn","2006-01-17","2006-01-13"]
["IJ03280015","Procure Laser Bay Optical Tables","2005-11-18","2006-04-13"]
["IJ03280020","RCV: Laser Bay Optical Tables, Legs & Encl","2006-04-14","2006-04-14"]
["IJ03280025","REQD: Sector 20 Alcove Beneficial Occupancy","2006-07-27","2006-07-26"]
["IJ03280030","Assemble & C/O Optical Tables, Legs & Encl","2006-07-27","2006-09-21"]
["IJ03280035","Design Enclosures","2005-12-15","2006-01-13"]
["IJ03280040","AVAIL: Lsr Bay Tables/Legs/Encl","2006-09-22","2006-09-21"]
["IJ03280045","Procure enclosures","2006-01-17","2006-04-11"]
["IJ03280050","Procure Laser Bay Equipment","2006-05-02","2006-07-26"]
["IJ03280055","RCV: Laser Bay Equipment","2006-07-27","2006-07-26"]
["IJ03280060","Define OAL Equipment Requirements","2005-08-01","2005-08-05"]
["IJ03280065","Define Laser Bay Equipment","2006-01-03","2006-01-31"]
["IJ03280070","Procure OAL Equipment","2005-08-08","2005-10-31"]
["IJ03280075","RCV: OAL Equipment","2005-11-01","2005-10-31"]
["IJ03280080","REQD: Room for the OAL Available","2005-11-01","2005-10-31"]
["IJ03280085","Install OAL Equipment","2005-11-01","2005-11-30"]
["IJ03280090","AVAIL:  OAL","2005-12-01","2005-11-30"]
["IJ03280100","Laser Safety Review Planning","2005-09-01","2005-09-29"]
["IJ03280115","Drive Laser Bay Earthquake Safety Review plng","2006-01-17","2006-01-30"]
["IJ0329","ALIGNMENT LASER SUMMARY","2006-03-14","2006-10-12"]
["IJ03290000","Define alignment Laser System requirements","2006-03-14","2006-03-20"]
["IJ03290005","Develop alignment Laser System Engrg & Design","2006-03-21","2006-04-17"]
["IJ03290025","COMP: Alignment Laser System Dsn","2006-04-18","2006-04-17"]
["IJ03290030","Procure alignment Laser System off-shelf parts","2006-04-18","2006-07-12"]
["IJ03290035","RCV: procured alignment Laser System off-shelf p","2006-07-13","2006-07-12"]
["IJ03290040","Fab (In House) Alignmt Laser System parts","2006-04-18","2006-05-30"]
["IJ03290050","RCV: fabricated mechanical parts","2006-05-31","2006-05-30"]
["IJ03290055","Assemble: alignment Laser system","2006-09-22","2006-10-05"]
["IJ03290060","Test : alignment Laser system","2006-10-06","2006-10-12"]
["IJ03290065","AVAIL: Alignment Laser System Ready for Install","2006-10-13","2006-10-12"]
["IJ0330","LIGHT PATH to STREAK CAMERA SUMMARY","2005-12-15","2006-11-02"]
["IJ03300000","Define Light Path Sys Reqmts, Beam path & model","2005-12-15","2006-01-12"]
["IJ03300005","Develop Light Path System Engrg & Design","2006-01-13","2006-03-13"]
["IJ03300035","COMP: Light Path to the Streak Camera Dsn","2006-03-14","2006-03-13"]
["IJ03300040","Procure Light Path off shelf parts","2006-03-14","2006-06-06"]
["IJ03300045","RCV: procured off shelf Light Path parts","2006-06-07","2006-06-06"]
["IJ03300050","Vendors Prep Proposals -Light Path to Srk Camera","2006-03-14","2006-04-10"]
["IJ03300055","RCV: Vendor Proposals - Light Path parts","2006-04-11","2006-04-10"]
["IJ03300060","Evaluate Vendor Proposals","2006-04-11","2006-04-17"]
["IJ03300065","AWARD: order Light Path parts","2006-04-18","2006-04-20"]
["IJ03300070","Vendor Fab, Assy & Test","2006-04-21","2006-07-17"]
["IJ03300075","RCV: Light Path parts from Vendor","2006-07-18","2006-07-17"]
["IJ03300080","FAB: Light Path transport tube/enclosure/supts","2006-07-18","2006-08-28"]
["IJ03300085","Proc Light Path transport tube/enclosure/supts","2006-03-14","2006-06-06"]
["IJ03300090","RCV: Light Path  transport tube/enclosure/supts","2006-06-07","2006-06-06"]
["IJ03300125","Assemble: Light Path System","2006-09-22","2006-10-19"]
["IJ03300140","Test: Light Path system","2006-10-20","2006-11-02"]
["IJ03300145","AVAIL: Light Path System Ready for Instl","2006-11-03","2006-11-02"]
["IJ04","RF GUN, LOAD LOCK & SUPPORTS SUMMARY","2005-09-09","2006-08-03",null,"2005-09-09"]
["IJ0401","RF GUN SUMMARY","2005-05-02","2006-08-03"]
["IJ04010055","AWARD: Contract for RF Gun Design & Build","2005-05-03","2005-05-05"]
["IJ0402","RF GUN SUPPORT SUMMARY","2006-01-17","2006-04-28"]
["IJ04020000","Define RF Gun Support Requirements","2006-01-17","2006-02-21"]
["IJ04020010","COMP: RF Gun Requirements Support Definitions","2006-02-22","2006-02-21"]
["IJ04020100","Design RF Gun Support","2006-01-20","2006-03-06"]
["IJ04020105","COMP: RF Gun Supports Design","2006-03-07","2006-03-06"]
["IJ04020107","Procure RF Gun Support","2006-03-07","2006-04-28"]
["IJ04020125","AVAIL: RF Gun Support Assy Ready for Install","2006-05-01","2006-04-28"]
["IJ0404","GUN LOAD LOCK SUPPORT SUMMARY","2005-05-02","2006-05-18"]
["IJ04040100","Define Load Lock Support Requirements","2005-05-02","2005-05-13"]
["IJ04040105","COMP: Load Lock Support Requirements Definition","2005-05-16","2005-05-13"]
["IJ04040110","Design Load Lock Support","2005-05-16","2005-11-02"]
["IJ04040115","COMP: Load Lock Support Design","2005-11-03","2005-11-02"]
["IJ04040120","Prep Bid Pak - Load Lock Support","2005-11-03","2005-12-02"]
["IJ04040122","RELEASE RFP: Load Lock Support","2005-12-05","2005-12-07"]
["IJ04040125","Vendors Prep Proposals - Load Lock Support","2005-12-08","2006-01-05"]
["IJ04040130","RCV: Vendor Proposals -Load Lock Support","2006-01-06","2006-01-05"]
["IJ04040140","Evaluate Proposals - Load Lock Support","2006-01-06","2006-01-20"]
["IJ04040145","AWARD: Contract for Load Lock Support","2006-01-23","2006-01-25"]
["IJ04040150","Vendor  Fab Load Lock Support","2006-01-26","2006-05-18"]
["IJ04040155","RCV:Load Lock Support (tested&passed at vendor)","2006-05-19","2006-05-18"]
["IJ04040160","AVAIL: Load Lock Support Assy Ready for Instl","2006-05-19","2006-05-18"]
["IJ0405","GUN SOLENOID SUMMARY","2005-06-01","2006-06-26"]
["IJ04050110","Post Release Design Correction -Sole Magnet Assy","2005-07-18","2005-08-18"]
["IJ04050115","Prep Bid Pak - Solenoid Magnet Assembly","2005-06-01","2005-06-14"]
["IJ04050120","RELEASE RFP: Solenoid Magnet Assembly","2005-06-15","2005-06-30"]
["IJ04050125","Vendor Prep Proposals - Solenoid Magnet Assembly","2005-07-01","2005-07-29"]
["IJ04050130","RCV: Proposals - Solenoid Magnet Assembly","2005-08-01","2005-07-29"]
["IJ04050135","Evaluate Proposals - Solenoid Magnet Assembly","2005-08-01","2005-08-12"]
["IJ04050140","AWARD: Contract for 2 Solenoid Magnet Assemblies","2005-08-15","2005-08-17"]
["IJ04050145","Vendor Fab 2 Solenoid Magnet Assemblies","2005-08-18","2006-01-25"]
["IJ04050150","RCV: 2 Solenoid Magnet Assemblies","2006-01-26","2006-01-26"]
["IJ04050160","Perform Lab Tests on Sol Magnet Assembly","2006-05-30","2006-06-26"]
["IJ04050165","AVAIL: Gun Solenoid Ready for Assembly","2006-06-27","2006-06-26"]
["IJ0406","GUN SOLENOID SUPPORTS SUMMARY","2006-01-17","2006-05-26"]
["IJ04060020","Design Solenoid Supports","2006-01-17","2006-04-06"]
["IJ04060030","COMP: Gun Solenoid Support Design","2006-04-07","2006-04-06"]
["IJ04060035","Prep Bid Pak - Solenoid Supports","2006-04-07","2006-04-07"]
["IJ04060040","RELEASE RFP: Solenoid Supports","2006-04-07","2006-04-07"]
["IJ04060045","Vendor Prep Proposals - Solenoid Supports","2006-04-10","2006-04-10"]
["IJ04060050","RCV: Proposals - Solenoid Supports","2006-04-11","2006-04-10"]
["IJ04060055","Evaluate Proposals - Solenoid Supports","2006-04-11","2006-04-11"]
["IJ04060060","AWARD: Contract for Solenoid Supports","2006-04-12","2006-04-14"]
["IJ04060065","Vendor Fab Solenoid Supports","2006-04-17","2006-05-26"]
["IJ04060070","RCV: Solenoid Supports","2006-05-30","2006-05-26"]
["IJ04060080","AVAIL: Gun Solenoid Support Ready for Assy","2006-05-30","2006-05-26"]
["IJ04070032","AWARD: Isolator","2005-09-09","2005-09-09",null,"2005-09-09","2005-09-09"]
["IJ0408","GUN RF FEED SUPPORTS SUMMARY","2005-05-02","2005-09-28"]
["IJ04080010","Design Gun RF Feed Supports","2005-05-02","2005-06-20"]
["IJ04080015","COMP: Gun RF Feed Supports Design","2005-06-21","2005-06-20"]
["IJ04080017","Procure Gun RF Feed Supports Materials","2005-06-21","2005-09-28"]
["IJ04080035","AVAIL: Gun RF Feed Supports Ready for Instl","2005-09-29","2005-09-28"]
["IJ05010022","AWARD:  Contract for BPM (3 ea)","2004-11-03","2004-11-03",null,"2004-11-03","2004-11-03"]
["IJ05010145","AWARD:  Contract for BPM (3 ea)","2004-11-19","2004-11-19",null,"2004-11-19","2004-11-19"]
["IJ05020146","AWARD:  Contract for FC/YAG1","2004-11-03","2004-11-03",null,"2004-11-03","2004-11-03"]
["IJ05020285","AWARD:  Contract for FC/YAG1 Supts","2005-02-16","2005-02-17",null,"2005-02-16","2005-02-17"]
["IJ05030090","AWARD:  Contract for Current Monitor (CM1) Supt","2005-02-08","2005-05-02",null,"2005-02-08"]
["IJ0507","GTL VACUUM COMPONENTS","2005-05-02","2006-09-11"]
["IJ0508","GTL SUPPORTS","2005-10-17","2005-12-14"]
["IJ050901","GS DIPOLE SUMMARY","2005-05-16","2006-05-16"]
["IJ05090267","AWARD:  Contract for Current Monitor (CM2) Supt","2005-01-06","2005-01-06",null,"2005-01-06","2005-01-06"]
["IJ05090322","AWARD:  Contract for GS BPM","2005-01-18","2005-01-18",null,"2005-01-18","2005-01-18"]
["IJ05090372","AWARD:  Contract for GS BPM Support","2005-02-03","2005-02-03",null,"2005-02-03","2005-02-03"]
["IJ050906","GS QUADS (3ea) SUMMARY","2005-05-02","2006-04-06"]
["IJ050907","GS SUPPORT SUMMARY","2005-05-02","2005-11-09"]
["IJ0510","COMBINATION PUMPING & OPTIC CHAMBER","2005-04-07","2006-03-07",null,"2005-04-07"]
["IJ05100050","AWARD:Contract for chamber","2005-04-07","2005-04-07",null,"2005-04-07","2005-04-07"]
["IJ05110028","AWARD:  Contract for GTL/YAG1","2005-09-19","2005-09-20",null,"2005-09-19","2005-09-20"]
["IJ05110071","AWARD:  Contract for GTL/YAG1 Supts","2005-10-17","2005-10-17",null,"2005-10-17","2005-10-17"]
["IJ06","INJECTOR STRUCTURES SUMMARY","2005-04-04","2006-06-01",null,"2005-04-04"]
["IJ0601","L0A-0B STRUCTURE ASSEMBLY SUMMARY","2005-05-02","2006-06-01"]
["IJ0603","MAJOR LINAC SUPPORT SUMMARY","2005-08-02","2006-03-03"]
["IJ06030010","Prep Bid Pak - Major Linac Supports","2005-08-02","2005-09-01"]
["IJ06030015","RELEASE: RFP - Major Linac Supports","2005-09-02","2005-09-07"]
["IJ06030020","Vendors Prep Proposals - Major Linac Supports","2005-09-08","2005-09-28"]
["IJ06030025","RCV: Vendor Proposal for Major Linac Supports","2005-09-29","2005-09-28"]
["IJ06030030","Evaluate Vendor Proposals-Major Linac Supports","2005-09-29","2005-10-12"]
["IJ06030035","AWARD: Major Linac Supports Contract","2005-10-13","2005-10-17"]
["IJ06030040","Vendor Fab, Assy & Test-Major Linac Supports","2005-10-18","2005-12-16"]
["IJ06030045","RCV: Major Linac Supports from Vendor","2006-01-03","2005-12-16"]
["IJ06030055","Fab & Mods Linac Supports","2006-01-03","2006-03-03"]
["IJ06030060","AVAIL: Supts Ready for Integ with L0-1 & L0-2","2006-03-06","2006-03-03"]
["IJ0604","LINAC SOLENOID & SUPPORTS SUMMARY","2005-05-02","2006-03-16"]
["IJ07","L0-1TL0-2 SUMMARY","2004-11-03","2006-08-21",null,"2004-11-03"]
["IJ0701","L0-1TL0-2 QUADRUPOLES SUMMARY (2EA)","2005-05-02","2006-02-01"]
["IJ0706","L0-1TL0-2 Vacuum Components","2004-12-15","2006-05-02",null,"2004-12-15"]
["IJ07060033","AWARD: Vacuum Components","2004-12-15","2004-12-15",null,"2004-12-15","2004-12-15"]
["IJ08020032","AWARD:  LTDL1 BPM (6 ea)","2005-02-24","2005-02-24",null,"2005-02-24","2005-02-24"]
["IJ0806","LTDL1 RF KICKER SUMMARY","2005-04-04","2006-05-01",null,"2005-04-04"]
["IJ08060050","AWARD: Contract for RF Kicker","2005-04-04","2005-04-04",null,"2005-04-04","2005-04-04"]
["IJ08060055","Vendor RF Kicker Production (build to print)","2005-05-02","2005-09-23"]
["IJ08060060","RCV: RF Kicker from Vendor","2005-09-26","2005-09-23"]
["IJ08060065","Vacuum Process Kicker","2005-09-26","2005-11-22"]
["IJ08060070","Conduct Test & RF Processing","2005-11-23","2006-02-08"]
["IJ08060075","Develop RF Kicker Support Structure Engr & Dsn","2005-09-01","2006-01-06"]
["IJ08060080","COMP: RF Kicker Support Structure Engr & Dsn","2006-01-09","2006-01-06"]
["IJ08060085","Procure Support Structure Materials","2006-01-09","2006-02-21"]
["IJ08060090","Fab RF Kicker Support Structure","2006-03-01","2006-04-17"]
["IJ08060095","Integrate RF Kicker onto Supports","2006-04-18","2006-05-01"]
["IJ08060100","AVAIL: LTDL1 RF Kicker & Supts Ready for Instl","2006-05-02","2006-05-01"]
["IJ0807","LTDL1 LINAC STEERING COILS SUMMARY(2ea)X-Y","2005-05-02","2006-05-16"]
["IJ0901","DL1 B01 & B02 DIPOLES SUMMARY","2005-05-02","2006-05-31"]
["IJ1002",null,"2005-05-02","2005-05-02"]
["IJ101_1010","Injector Region Layout","2005-05-02","2005-10-03"]
["IJ101_1020","Injector Region Fabrication Oversight","2005-05-16","2006-08-15"]
["IJ101_1030","injector Region Documentation","2006-10-02","2006-12-29"]
["IJ101_1100","Design Injector Vault Base Supports","2005-05-02","2005-05-31"]
["IJ101_1110","COMP:  Injector Vault Base Supports Design","2005-06-01","2005-05-31"]
["IJ101_1120","Prep Bid Pkg for Injector Vault Base Supports","2006-01-03","2006-01-31"]
["IJ101_1130","RELEASE RFP:  Injector Vault Base Supports","2006-02-01","2006-02-01"]
["IJ101_1140","Vendor Prep Proposal for Inj Vault Base Supports","2006-02-02","2006-02-02"]
["IJ101_1150","RCV:  Proposals for Injector Vault Base Supports","2006-02-03","2006-02-03"]
["IJ101_1160","Evaluate Proposals for Inj Vault Base Supports","2006-02-06","2006-02-06"]
["IJ101_1170","AWARD: Contract for Injector Vault Base Supports","2006-02-07","2006-02-07"]
["IJ101_1180","Vendor Fab Injector Vault Base Supports","2006-02-08","2006-04-05"]
["IJ101_1190","AVAIL:  Injector Vault Base Supports RFI","2006-04-06","2006-04-06"]
["IJ101_1200","Injector Region Infrastructure Support","2005-12-01","2007-01-02"]
["IJ101_1210","Injector Region Top Assembly","2005-12-01","2006-04-03"]
["IJ101_1220","Injector Region Documentation","2006-12-01","2007-06-29"]
["IJ101_2010","Gun Area Layout","2005-06-01","2005-09-30"]
["IJ101_2020","Gun Area Installation Oversight","2006-05-01","2006-07-28"]
["IJ101_2030","Gun Area Documentation","2006-04-03","2006-09-29"]
["IJ101_2100","Gun Area Table and Columns","2005-12-01","2006-01-31"]
["IJ101_2110","Gun Area Top Assembly","2005-12-01","2006-05-01"]
["IJ101_2120","Gun Area Procurement Support","2006-02-01","2006-05-31"]
["IJ101_2130","Gun Area Fabrication Oversight","2006-02-01","2006-05-31"]
["IJ101_2140","Gun Area Installation Coordination Planning","2006-01-03","2006-06-30"]
["IJ101_2150","Gun Area Installation Oversight","2006-06-01","2006-07-28"]
["IJ101_2160","Gun Area Documentation","2006-10-02","2007-06-29"]
["IJ101_3010","Accelerator Area Layout","2005-05-02","2005-08-30"]
["IJ101_3020","Accelerator Area Installation Oversight","2006-03-01","2006-04-28"]
["IJ101_3030","Accelerator Area Documentation","2006-01-03","2006-06-30"]
["IJ101_3100","Accelerator Area Table and Columns","2005-12-01","2006-02-28"]
["IJ101_3110","Accelerator Area Top Assembly","2005-12-01","2006-05-01"]
["IJ101_3120","Accelerator Area Procurement Support","2006-03-01","2006-05-01"]
["IJ101_3130","Accelerator Area Fabrication Oversight","2006-01-03","2006-05-30"]
["IJ101_3140","Accelerator Area Installation Coord Planning","2006-01-03","2006-05-30"]
["IJ101_3150","Accelerator Area Installation Oversight","2006-06-01","2006-07-31"]
["IJ101_3160","Accelerator Area Documentation","2006-10-02","2007-07-02"]
["IJ101_4010","Heater Area Layout","2005-05-02","2005-06-30"]
["IJ101_4020","Heater Area Installation Oversight","2006-01-03","2006-02-28"]
["IJ101_4030","Heater Area Documentation","2005-10-03","2006-03-30"]
["IJ101_4100","Heater Area Table and Columns","2005-12-01","2006-02-28"]
["IJ101_4110","Heater Area Top Assembly","2005-12-01","2006-05-01"]
["IJ101_4120","Heater Area Procurement Support","2006-03-01","2006-05-01"]
["IJ101_4130","Heater Area Fabrication Oversight","2006-03-01","2006-05-01"]
["IJ101_4140","Heater Area Installation Coord Planning","2006-01-03","2006-05-30"]
["IJ101_4150","Heater Area Installation Oversight","2006-06-01","2006-07-31"]
["IJ101_4160","Heater Optics Integration","2006-12-01","2007-07-02"]
["IJ101_4170","Heater Optics Installation Oversight","2007-07-02","2007-10-01"]
["IJ101_4180","Heater Area Documentation","2006-01-03","2006-06-30"]
["IJ101_5020","Wall Area Installation Oversight","2005-10-03","2005-10-28"]
["IJ101_5030","Wall Area Documentation","2005-05-02","2005-07-15"]
["IJ101_5100","Wall Area Top Assembly","2005-12-01","2006-01-03"]
["IJ101_6010","Insertion Area Layout","2005-07-01","2005-11-30"]
["IJ101_6020","Insertion Area Installation Oversight","2006-10-02","2007-02-02"]
["IJ101_6030","Insertion Area Documentation","2006-07-03","2006-12-29"]
["IJ101_6100","Insertion Area Table and Columns","2005-12-01","2006-03-31"]
["IJ101_6110","Insertion Area Top Assembly","2005-12-01","2006-03-31"]
["IJ101_6120","Insertion Area Procurement Support","2006-04-03","2006-06-30"]
["IJ101_6130","Insertion Area Fabrication Oversight","2006-04-03","2006-06-30"]
["IJ101_6140","Insertion Area Installation Coord Planning","2006-01-03","2006-07-31"]
["IJ101_6150","Insertion Area Installation Oversight","2006-08-01","2006-11-30"]
["IJ101_6160","Insertion Area Documentation","2006-12-01","2007-02-28"]
["IJ101_7010","Spectrometer Area Layout","2005-10-03","2006-01-30"]
["IJ101_7020","Spectrometer Area Installation Oversight","2006-10-02","2007-02-02"]
["IJ101_7030","Spectrometer Area Documentation","2006-07-03","2006-12-29"]
["IJ101_7100","Spectrometer Area Table and Columns","2005-12-01","2006-03-31"]
["IJ101_7110","Spectrometer Area Top Assembly","2005-12-01","2006-03-31"]
["IJ101_7120","Spectrometer Area Procurement Support","2006-04-03","2006-06-30"]
["IJ101_7130","Spectrometer Area Fabrication Oversight","2006-04-03","2006-06-30"]
["IJ101_7140","Spectrometer Area Installation Coord Planning","2006-01-03","2006-07-31"]
["IJ101_7150","Spectrometer Area Installation Oversight","2006-08-01","2006-11-30"]
["IJ101_7160","Spectrometer Area Documentation","2006-12-01","2007-02-28"]
["IJ101_8010","Drive Laser Layout","2005-10-03","2005-12-30"]
["IJ101_8020","Drive Laser Installation Oversight","2006-05-01","2006-07-28"]
["IJ101_8030","Drive Laser Documentation","2006-07-03","2006-09-29"]
["IJ101_8100","Table and Columns","2005-05-02","2005-05-02"]
["IJ101_8110","Drive Laser Top Assembly","2006-01-03","2006-05-01"]
["IJ101_8120","Drive Laser Procurement Support","2006-01-03","2006-05-31"]
["IJ101_8130","Drive Laser Fabrication Oversight","2006-01-03","2006-05-31"]
["IJ101_8140","Drive Laser Installation Coordination Planning","2006-02-01","2006-05-01"]
["IJ101_8150","Drive Laser Installation Oversight","2006-05-01","2006-07-31"]
["IJ101_8160","Drive Laser Documentation","2006-12-01","2007-07-02"]
["IJ104_1000","Management - CONST","2005-12-01","2007-01-02"]
["IJ104_1010","Cost Account Managers - CONST","2005-12-01","2007-01-02"]
["IJ104_1020","Fabrication Coordination","2005-12-01","2007-01-02"]
["IJ104_1030","Computers - CONST","2005-12-01","2007-01-02"]
["IJ104_1040","Travel - CONST","2005-12-01","2007-01-02"]
["IJ104_1050","Materials & Supplies - CONST","2005-12-01","2007-01-02"]
["IJ1101","SAB SPECTROMETER DIPOLE SUMMARY","2005-08-10","2006-07-19"]
["IJ11010105","AWARD: Contract for SAB Spectral Dipole","2005-08-10","2005-08-12"]
["IJ12","INJECTOR RF WAVEGUIDE SUMMARY","2005-04-06","2006-10-27",null,"2005-04-06"]
["IJ1201","INJECTOR RF WAVEGUIDE SUBSYSTEM SUMMARY","2005-04-06","2006-10-27",null,"2005-04-06"]
["IJ12010010","Develop RF Waveguide System Engineering & Dsn","2005-05-02","2005-05-27"]
["IJ12010020","Refurbish WG Trailer","2005-07-29","2005-08-25"]
["IJ12010030","Purchase WG Material","2005-05-02","2006-01-06"]
["IJ12010040","Purchase WG Flanges","2005-05-02","2005-10-03"]
["IJ12010050","Design Pen Waveguide","2005-05-02","2005-05-31"]
["IJ12010060","Fab Pen Waveguide","2005-06-01","2005-09-01"]
["IJ12010070","Post Process Pen Waveguide","2005-09-02","2005-09-15"]
["IJ12010080","Fab Pen Supports","2005-09-02","2005-09-30"]
["IJ12010090","AVAIL: Pen WG Ready for Install","2005-10-03","2005-09-30"]
["IJ12010100","Design Vault Waveguide","2005-05-02","2006-01-03"]
["IJ12010108","AWARD: Contract for Waveguide Supt Components","2005-04-20","2005-04-20",null,"2005-04-20","2005-04-20"]
["IJ12010110","Fab Vault Waveguide","2006-01-04","2006-03-20"]
["IJ12010120","Post Process Vault Waveguide","2006-03-21","2006-03-30"]
["IJ12010125","AWARD: Contract for Waveguide Components","2005-04-06","2005-04-06",null,"2005-04-06","2005-04-06"]
["IJ12010130","Fab Vault Supports","2006-01-13","2006-03-30"]
["IJ12010140","AVAIL: Vault WG Ready for Install","2006-03-31","2006-03-30"]
["IJ12010150","Design KG Waveguide","2005-08-29","2005-10-24"]
["IJ12010160","Fab KG Waveguide","2005-10-25","2006-01-03"]
["IJ12010170","Post Process KG Waveguide","2006-01-04","2006-01-17"]
["IJ12010175","AWARD: Contract for Vacuum Components","2005-07-01","2005-07-01",null,"2005-07-01","2005-07-01"]
["IJ12010180","Fab KG Supports","2006-01-18","2006-02-14"]
["IJ12010190","AVAIL: KG WG Ready for Install","2006-02-15","2006-02-14"]
["IJ12010200","High Power Gun WG Conditioning","2006-10-02","2006-10-27"]
["IJ12010210","High Power ACC WG Conditioning","2006-05-01","2006-05-26"]
["IJ12010220","High Power T-Cav WG Contidioning","2006-10-02","2006-10-27"]
["IJ13","INJECTOR RF SUMMARY","2005-04-04","2007-05-25",null,"2005-04-04"]
["IJ13010020","Develop Documentation","2005-05-02","2005-10-14"]
["IJ13010025","Create Layouts","2005-05-02","2005-10-14"]
["IJ13010030","Prepare for PDR","2005-05-02","2005-05-03"]
["IJ13010035","Conduct PDR","2005-05-04","2005-05-04"]
["IJ130101","S-BAND LL CONTROLS TIMING SYSTEM SUMMARY","2005-05-02","2006-07-18"]
["IJ13010108","Design & Prototype Master Amplifier","2005-06-02","2005-06-14"]
["IJ13010120","Generate Procurement Plan","2005-06-15","2005-06-15"]
["IJ13010122","Create Test Plan","2005-06-16","2005-06-22"]
["IJ13010124","Establish Subordinate W.O.'s","2005-06-23","2005-06-23"]
["IJ13010126","Prepare for FDR","2005-06-24","2005-06-27"]
["IJ13010128","Conduct FDR","2005-06-28","2005-06-28"]
["IJ13010130","COMP: S-Band LL Design - Release for Fab","2005-06-29","2005-06-28"]
["IJ13010146","Fab Master Amplifier","2005-06-29","2005-09-22"]
["IJ13010152","System Tests","2005-10-17","2006-03-24"]
["IJ13010153","Fab/Test PEPII IQ PAU","2005-05-02","2006-01-03"]
["IJ13010154","AVAIL: RF Cntrls I/F & Timing Ready for Install","2006-03-27","2006-03-24"]
["IJ13010156","Install Modules","2006-03-27","2006-07-18"]
["IJ13010164","AVAIL: RF Cntrls I/F & Timing Ready for Comm","2006-07-19","2006-07-18"]
["IJ130102","LLRF PHASE REFERENCE SYSTEM SUMMARY","2005-06-01","2007-03-01"]
["IJ13010200","System Design","2005-06-01","2005-11-28"]
["IJ13010205","Develop Documentation","2006-01-03","2007-03-01"]
["IJ13010210","Create Layouts","2006-01-03","2007-03-01"]
["IJ13010215","Prepare for PDR","2005-11-29","2005-11-30"]
["IJ13010217","Conduct PDR","2005-12-01","2005-12-01"]
["IJ13010219","Design & Prototype LCLS Oscillator","2005-06-29","2006-03-30"]
["IJ13010220","Design RF Distribution L0, L1","2005-12-02","2006-01-03"]
["IJ13010222","Design Distribution Amplifier Chassis","2005-12-02","2006-02-01"]
["IJ13010223","Design & Prototype Laser Timing Stability","2005-12-02","2007-02-01"]
["IJ13010225","Design & Prototype Multiplier Chassis","2005-12-02","2005-12-15"]
["IJ13010228","Generate Procurement Plan","2005-12-02","2005-12-02"]
["IJ13010230","Create Test Plan","2005-12-05","2005-12-09"]
["IJ13010232","Establish Subordinate W.O.'s","2005-12-12","2005-12-12"]
["IJ13010234","Prepare for FDR","2005-12-13","2005-12-14"]
["IJ13010236","Conduct FDR","2005-12-15","2005-12-15"]
["IJ13010238","COMP: Design - Release for Fab","2005-12-16","2005-12-15"]
["IJ13010240","Vendor Fab LCLS Oscillator (3)","2005-11-15","2006-06-29"]
["IJ13010241","Prep Bid Pak - LCLS Oscillator (3)","2005-10-03","2005-10-14"]
["IJ13010242","Fab LCLS Oscillator","2006-04-06","2006-06-29"]
["IJ13010243","RELEASE: RFP - LCLS Oscillator (3)","2005-10-17","2005-10-19"]
["IJ13010244","Vendors Prep Prop- LCLS Oscillator (3)","2005-10-20","2005-11-02"]
["IJ13010246","RCV: Vendor Prop- LCLS Oscillator (3)","2005-11-03","2005-11-02"]
["IJ13010247","Eval Vendor Prop- LCLS Oscillator (3)","2005-11-03","2005-11-09"]
["IJ13010248","Fab Distribution Amplifier Chassis","2005-10-03","2006-07-03"]
["IJ13010249","AWARD: LCLS Oscillator (3)","2005-11-10","2005-11-14"]
["IJ13010256","Fab Laser Phase Timing Stability","2005-10-03","2006-07-03"]
["IJ13010260","S-20 MDL Modifications","2005-10-03","2006-07-03"]
["IJ13010264","Fab Multiplier Chassis","2005-10-03","2006-07-03"]
["IJ13010272","AVAIL: LLRF Phase Ref System Ready for Install","2006-07-05","2006-07-03"]
["IJ13010274","Install Cable Guides","2006-07-05","2006-11-15"]
["IJ13010275","Install S-Band RF Cables (31)","2006-07-05","2006-11-15"]
["IJ13010276","Install Modules","2006-07-05","2006-11-15"]
["IJ13010284","AVAIL: LLRF Phase Ref System Ready for Comm","2006-11-16","2006-11-15"]
["IJ130103","LLRF MONITOR & CONTROL SYSTEM SUMMARY","2005-05-02","2007-03-07"]
["IJ13010300","Define Control Interface","2005-05-02","2005-08-31"]
["IJ13010302","Develop Documentation","2005-09-01","2006-09-12"]
["IJ13010305","Create Layouts","2005-09-01","2006-09-12"]
["IJ13010307","Prepare for PDR","2005-09-01","2005-09-02"]
["IJ13010308","Conduct PDR","2005-09-06","2005-09-06"]
["IJ13010310","Design & Prototype S-Band Phase Measurment","2005-05-02","2006-02-01"]
["IJ13010311","Design & Prototype DAC & SAM Breakout","2005-05-02","2006-02-01"]
["IJ13010312","Design Modulator Refurbishment","2005-12-01","2006-02-01"]
["IJ13010314","Design Solid State Sub Booster","2005-10-05","2006-02-01"]
["IJ13010318","Design & Prototype Optical Interface","2005-05-02","2006-10-02"]
["IJ13010330","Generate Procurement Plan","2006-02-02","2006-02-02"]
["IJ13010332","Create Test Plan","2006-02-03","2006-02-09"]
["IJ13010334","Establish Subordinate W.O.'s","2006-02-10","2006-02-10"]
["IJ13010336","Prepare for FDR","2006-02-13","2006-02-14"]
["IJ13010338","Conduct FDR","2006-02-15","2006-02-15"]
["IJ13010339","Prep Bid Pak - Modulator Thyratron Parts","2006-02-16","2006-03-02"]
["IJ13010340","COMP: Design - Release for Fab","2006-02-16","2006-02-15"]
["IJ13010341","RELEASE: RFP - Modulator Thyratron Parts","2006-03-03","2006-03-02"]
["IJ13010342","Vendor Fab Modulator Thyratron Parts","2006-03-27","2006-07-03"]
["IJ13010343","Vendors Prep Prop- Modulator Thyratron Parts","2006-03-03","2006-03-16"]
["IJ13010344","Procure SS Subbooster Amplitude Control","2006-02-16","2006-03-16"]
["IJ13010345","RCV: Vendor Prop- Modulator Thyratron Parts","2006-03-17","2006-03-16"]
["IJ13010346","Eval Vendor Prop- Modulator Thyratron Parts","2006-03-17","2006-03-23"]
["IJ13010347","AWARD: Modulator Thyratron Parts","2006-03-24","2006-03-24"]
["IJ13010348","Procure Monitor Scope SCP","2005-10-05","2005-10-11"]
["IJ13010350","Procure Dual Power Meter SCP","2005-10-05","2005-10-05"]
["IJ13010352","Procure Bunch Length Monitor Electronics","2006-02-16","2006-06-01"]
["IJ13010354","RCV: Procured Hardware/Equipment","2006-07-05","2006-07-03"]
["IJ13010356","Fab S-Band Units (12)","2006-07-05","2006-09-27"]
["IJ13010360","Fab Dac Sam Breakout Units (6)","2006-07-05","2006-09-27"]
["IJ13010366","Refurbish Modulator","2006-07-05","2006-09-27"]
["IJ13010368","Klystron Change to Source Tube","2006-07-05","2006-09-27"]
["IJ13010370","Fab SS Subbooster Amplifier","2005-10-05","2006-04-03"]
["IJ13010372","Integration SS Subbooster Amplifier","2006-05-12","2006-08-07"]
["IJ13010374","Modify IPA Chassis","2006-02-16","2006-05-11"]
["IJ13010382","Modulator Control Interface Cables","2006-07-05","2006-09-27"]
["IJ13010384","Monitor Scope SCP Interface","2006-07-05","2006-07-18"]
["IJ13010387","REQD: Beneficial Occupancy of RF Hut","2006-03-10","2006-03-09"]
["IJ13010388","AVAIL: LLRF Mon & Cntrl Ready for Installation","2006-11-27","2006-11-22"]
["IJ13010389","Install Cables","2006-09-28","2006-11-22"]
["IJ13010390","Recable RF","2006-05-12","2006-07-10"]
["IJ13010391","Install Modules","2006-11-27","2007-01-08"]
["IJ13010392","Install Mod Control Interace","2007-01-09","2007-03-07"]
["IJ13010394","AVAIL: LLRF Mon & Cntrl Ready for Commissioning","2007-03-08","2007-03-07"]
["IJ130104","BEAM PHASE MONITOR CAVITY SUMMARY","2005-08-05","2007-01-25"]
["IJ13010400","Define Beamline Component","2005-08-05","2005-08-18"]
["IJ13010402","COMP: Beamline Component Definition","2005-08-19","2005-08-18"]
["IJ13010408","Develop Documentation","2006-11-15","2007-01-25"]
["IJ13010410","Create Layouts","2005-08-19","2007-01-25"]
["IJ13010412","Prepare for PDR","2006-02-27","2006-02-28"]
["IJ13010414","Conduct PDR","2006-03-01","2006-03-01"]
["IJ13010416","Generate Procurement Plan","2006-03-02","2006-03-02"]
["IJ13010418","Create Test Plan","2006-03-03","2006-03-09"]
["IJ13010420","Establish Subordinate W.O.'s","2006-03-10","2006-03-10"]
["IJ13010422","Prepare for FDR","2006-03-13","2006-03-14"]
["IJ13010424","Conduct FDR","2006-03-15","2006-03-15"]
["IJ13010426","COMP: Design - Release for Fab","2006-03-16","2006-03-15"]
["IJ13010430","Fab Beam Line Components","2006-03-16","2006-06-08"]
["IJ13010436","Cold Test Components","2006-06-09","2006-06-15"]
["IJ13010438","Cold Test Complete","2006-06-16","2006-06-15"]
["IJ13010439","Bake Beamline Components","2006-06-16","2006-06-29"]
["IJ13010440","AVAIL: Beam Phase Mon. Cavity Ready for Install","2006-06-30","2006-06-29"]
["IJ13010441","Fabricate Beam Phase Monitor System","2006-03-16","2006-09-01"]
["IJ13010442","Install Modules","2006-09-05","2006-09-19"]
["IJ13010448","Install Cables","2006-09-20","2006-10-03"]
["IJ13010452","AVAIL: Beam Phase Mon. System Ready for Comm.","2006-10-04","2006-10-03"]
["IJ130105","RF SYSTEM S/W DEVELOPMENT/DOCUMENTATION SUMMARY","2006-05-08","2007-05-25"]
["IJ13010502","Develop Specification","2006-11-15","2007-01-25"]
["IJ13010504","Specification Complete","2007-01-26","2007-01-25"]
["IJ13010506","Create Layouts","2006-05-08","2007-01-25"]
["IJ13010510","Prepare for PDR","2007-01-24","2007-01-25"]
["IJ13010512","Conduct PDR","2007-01-25","2007-01-25"]
["IJ13010516","Create Test Plan","2007-01-19","2007-01-25"]
["IJ13010522","Conduct FDR","2007-01-26","2007-02-01"]
["IJ13010524","COMP: Design - Release for Fab","2007-02-02","2007-02-01"]
["IJ13010528","RF Feedback Measurements/Algorithm Development","2007-02-02","2007-05-25"]
["IJ13010538","AVAIL: RF System S/W & Docs Ready for Comm.","2007-05-29","2007-05-25"]
["IJ15","INJECTOR LASER HEATER SUBSYSTEM SUMMARY","2005-10-03","2007-06-27"]
["IJ1501","SYSTEM DESIGN & OPTIMIZATION SUMMARY","2007-06-07","2007-06-27"]
["IJ15010015","Laser Heater System Design Review","2007-06-07","2007-06-13"]
["IJ15010020","Laser Heater System Design Modifications","2007-06-14","2007-06-27"]
["IJ15010025","COMP: System design","2007-06-28","2007-06-27"]
["IJ1502","BEAM CONDITIONING OPTICS (LB) SUMMARY","2006-10-03","2007-04-12"]
["IJ15020000","Procure Laser Heater Optics Spares","2006-10-03","2006-10-31"]
["IJ15020005","Design Beam Conditioning","2006-10-03","2006-12-01"]
["IJ15020015","Define Beam Conditioning Components Specs","2006-12-04","2007-01-24"]
["IJ15020020","Procure Compressor breadboard and components","2007-01-25","2007-03-22"]
["IJ15020025","Procure First telescope optics","2007-01-25","2007-03-22"]
["IJ15020030","Procure Path length adjustor breadboard & Comps","2007-01-25","2007-03-22"]
["IJ15020035","Procure Optics safety equipment","2007-01-25","2007-03-22"]
["IJ15020040","Install and Test Beam Conditioning optics","2007-03-23","2007-04-12"]
["IJ15020050","COMP: Beam conditioning optics","2007-04-13","2007-04-12"]
["IJ1503","TRANSPORT OPTICS SUMMARY","2007-01-25","2008-03-11"]
["IJ15030005","Design Transport optics","2007-01-25","2007-03-21"]
["IJ15030015","Define Transport System Optics Specs","2007-03-22","2007-04-12"]
["IJ15030020","Procure Relay optics transport system","2007-04-13","2007-06-08"]
["IJ15030025","Procure Reducing telescope","2007-04-13","2007-06-08"]
["IJ15030030","Procure Optics launch table in tunnel","2007-04-13","2007-06-08"]
["IJ15030035","Transport optics installation, alignment & test","2007-11-26","2008-03-11"]
["IJ15030040","Design enclosures,laser beam tubes & supports","2007-03-22","2007-05-18"]
["IJ15030045","Procure enclosures,beam tubes & supports","2007-05-21","2007-11-07"]
["IJ15030049","REQD: Enclosures,Tubes & Supports Installed","2007-11-26","2007-11-21"]
["IJ15030050","AVAIL: Enclosures,tubes & supports for Install","2007-11-08","2007-11-07"]
["IJ15030060","COMP: Transport Optics","2008-03-12","2008-03-11"]
["IJ1504","CHICANE SUMMARY","2005-05-02","2006-05-16"]
["IJ1505","UNDULATOR SUMMARY","2005-10-03","2006-12-14"]
["IJ15050005","Define Undulator specifications","2005-10-03","2006-01-11"]
["IJ15050010","Undulator design review","2006-01-12","2006-01-26"]
["IJ15050011","Prep Bid Pak - Undulator","2006-01-27","2006-02-09"]
["IJ15050012","RELEASE: RFP - Undulator","2006-02-10","2006-02-16"]
["IJ15050013","Vendors Prep Proposals - Undulator","2006-02-17","2006-03-24"]
["IJ15050014","RCV: Vendor Proposals - Undulator","2006-03-27","2006-03-24"]
["IJ15050015","Evaluate Vendor Proposals - Undulator","2006-03-27","2006-03-30"]
["IJ15050016","AWARD: Undulator","2006-03-31","2006-04-03"]
["IJ15050020","Fab/Procure Undulator","2006-04-04","2006-10-02"]
["IJ15050025","RCV:  Undulator","2006-10-03","2006-10-03"]
["IJ15050035","Perform Magnetic measurements and QA","2006-10-04","2006-12-14"]
["IJ15050040","AVAIL: Undulator for installation","2006-12-15","2006-12-14"]
["IJ1506","PHOTON BEAM DIAGNOSTICS SUMMARY","2007-04-13","2007-10-24"]
["IJ15060005","Design Diagnostics","2007-04-13","2007-05-30"]
["IJ15060015","Prepare Diagnostics spec and purchase","2007-05-31","2007-06-06"]
["IJ15060020","Procure Spiricon camera","2007-06-07","2007-07-19"]
["IJ15060025","Procure Molectron power meter","2007-06-07","2007-07-19"]
["IJ15060030","Procure optics for photon diagnostics","2007-06-07","2007-07-06"]
["IJ15060032","Procure video cameras for OTRs & waist-size mon","2007-06-07","2007-07-06"]
["IJ15060035","Procure Timing diode + oscilloscope","2007-06-07","2007-07-06"]
["IJ15060040","Design Supports","2007-05-31","2007-07-30"]
["IJ15060045","Fabricate Supports","2007-07-31","2007-09-04"]
["IJ15060047","AVAIL: Supports for Install","2007-09-05","2007-09-04"]
["IJ15060049","REQD: Photon beam diagnostics Installed","2007-09-26","2007-09-25"]
["IJ15060050","Install and test Photon beam diagnostics","2007-09-26","2007-10-24"]
["IJ15060055","COMP: Photon Beam diagnostics","2007-10-25","2007-10-24"]
["IJ1508","TESTING AND COMMISSIONING SUMMARY","2006-09-20","2008-04-22"]
["IJ15080005","Plan for Laser Heater commissioning","2008-01-08","2008-01-22"]
["IJ15080007","REQD:Complete Chicane Installation","2007-09-19","2007-09-18"]
["IJ15080008","REQD:Complete Undulator Installation","2007-09-26","2007-09-25"]
["IJ15080009","REQD:Complete Laser Heater Controls","2007-08-30","2007-08-29"]
["IJ15080010","Commission Laser Heater Bay Optics","2008-01-23","2008-02-05"]
["IJ15080011","REQD:Complete Spectrometer","2006-09-20","2006-09-19"]
["IJ15080015","Commission IR Optical Path to Laser Heater","2008-03-12","2008-03-18"]
["IJ15080020","Match beam power and size for LH","2008-03-19","2008-04-01"]
["IJ15080025","Setup LH electron energy spread measurement","2008-04-02","2008-04-15"]
["IJ15080030","Overlap LH electron and laser beams","2008-04-16","2008-04-22"]
["IJ15080040","COMP: Laser Heater Commissioning","2008-04-23","2008-04-22"]
["IJ1601","PERSONNEL PROTECTION SUBSYSTEM SUMMARY","2006-02-22","2006-06-14"]
["IJ16010047","BSOIC Design","2005-07-01","2005-07-27"]
["IJ16010050","PROCUREMENT START - Injector PPS","2006-02-22","2006-02-21"]
["IJ16010066","Procure PPS Hardware","2006-02-22","2006-05-16"]
["IJ16010220","RCV: PPS Hardware/Material","2006-05-17","2006-05-16"]
["IJ16010225","Prep Bid Pak - BSOIC","2005-07-28","2005-08-10"]
["IJ16010230","RELEASE: RFP - BSOIC","2005-08-11","2005-08-10"]
["IJ16010235","Vendors Prep Proposals - BSOIC","2005-08-11","2005-08-31"]
["IJ16010240","RCV: Proposals - BSOIC","2005-09-01","2005-08-31"]
["IJ16010245","Evaluate Proposals - BSOIC","2005-09-01","2005-09-15"]
["IJ16010250","AWARD: Contract - BSOIC","2006-07-11","2006-07-11"]
["IJ16010255","Vendor Fab/Assy - BSOIC","2006-07-12","2007-02-28"]
["IJ16010260","RCV: from Vendor - PPS BSOIC","2007-03-01","2007-02-28"]
["IJ16010275","Fab and Pre Assemble Components (as required)","2007-03-01","2007-03-28"]
["IJ16010286","COMP: Injector PPS Component Fab & Assembly","2007-03-29","2007-03-28"]
["IJ16010288","Perform Pre-Install Qual Test on Injector PPS","2007-03-29","2007-04-25"]
["IJ16010290","AVAIL: Injector PPS Equip ready for Install","2007-04-26","2007-04-25"]
["IJ1601_022","PROCUREMENT START - Laser PPS","2006-02-22","2006-02-21"]
["IJ1601_023","Procure Entryway Hardware","2006-02-22","2006-06-14"]
["IJ1601_100","RCV: Laser room Hardware/Material","2006-06-15","2006-06-14"]
["IJ1601_112","AVAIL: Laser Room PPS Equip ready for Install","2006-06-15","2006-06-14"]
["IJ16020000","PLC PPS Design Evaluation","2005-05-02","2005-06-21"]
["IJ16020005","COMP: PLC PPS Design Evaluation","2005-06-22","2005-06-21"]
["IJ16020400","Procure 12 AMP MCOR Modules (2)-Spares","2006-10-03","2007-04-09"]
["IJ16020405","Procure 30 AMP MCOR Modules (1)-Spares","2006-10-03","2007-04-09"]
["IJ16020410","Procure 15KW Power Supply-Spares","2006-10-03","2007-04-09"]
["IJ160300","MACHINE PROTECTION SUBSYSTEM SUMMARY","2006-10-03","2007-03-12"]
["IJ16030055","PROCUREMENT START - Injector MPS","2006-10-03","2006-10-02"]
["IJ16030056","Procure MPS Hardware","2006-10-03","2007-03-12"]
["IJ16030200","RCV: MPS Hardware/Material","2007-03-13","2007-03-12"]
["IJ16030240","COMP: Vendor Equip Fab/Assy - Ready for Instl","2007-03-13","2007-03-12"]
["IJ16030285","AVAIL: Injector MPS Equip ready for Install","2007-03-13","2007-03-12"]
["IJ160401","SOLENOID 1 PS 10KW SUMMARY","2005-05-02","2006-11-15"]
["IJ16040106","PROCUREMENT START - Solenoid 1 PS 10KW","2005-09-01","2005-08-31"]
["IJ16040107","10kw Power Supply - (Selenoid 1)","2005-09-01","2006-02-17"]
["IJ16040132","AVAIL: All Solenoid 1 PS 10KW parts","2006-02-21","2006-02-17"]
["IJ16040165","Conduct Design Review","2005-05-02","2005-05-02"]
["IJ16040170","COMP: Solenoid 1 PS 10KW Fab & Assembly","2006-10-19","2006-10-18"]
["IJ16040175","Perform Solenoid 1 PS 10KW Pre-Install Qual Test","2006-10-19","2006-11-15"]
["IJ16040180","AVAIL: Solenoid 1 PS 10KW Ready for Install","2006-11-16","2006-11-15"]
["IJ160402","SOLENOID 2 PS 15KW SUMMARY","2005-06-01","2006-11-15"]
["IJ16040206","PROCUREMENT START - Solenoid 2 PS 15KW","2005-09-01","2005-08-31"]
["IJ16040207","RCV: Power Supply - (Solenoid 2)","2005-12-13","2005-12-12"]
["IJ16040208","30kw Power Supply - (Solenoid 2)","2005-09-01","2005-12-12"]
["IJ16040255","AVAIL: All Solenoid 1 PS 15KW parts","2005-12-13","2005-12-12"]
["IJ16040284","Conduct Design Review","2005-06-01","2005-06-01"]
["IJ16040286","COMP: Solenoid 2 PS 15KW Fab & Assembly","2006-10-19","2006-10-18"]
["IJ16040288","Perform Solenoid 2 PS 15KW Pre-Install Qual Test","2006-10-19","2006-11-15"]
["IJ16040290","AVAIL: Solenoid 2 PS 15KW Ready for Install","2006-11-16","2006-11-15"]
["IJ160404","BX011-BX02 PS 15KW SUMMARY","2005-06-01","2006-11-15"]
["IJ16040406","PROCUREMENT START -BX011-BX02 PS 15KW","2005-09-01","2005-08-31"]
["IJ16040407","15kw Power Supply - (B1-2)","2005-09-01","2005-12-12"]
["IJ16040410","RCV: 15kw Power Supply (B1-2)","2005-12-13","2005-12-12"]
["IJ16040484","Conduct Design Review","2005-06-01","2005-06-01"]
["IJ16040486","COMP: BX011-BX02 PS 15KW Fab & Assembly","2005-12-13","2005-12-12"]
["IJ16040488","Perform BX011-BX02 PS 15KW Pre-Install Qual Test","2006-10-19","2006-11-15"]
["IJ16040490","AVAIL: BX011-BX02 PS 15KW Ready for Install","2006-11-16","2006-11-15"]
["IJ160405","BXS Spect  PS 15KW SUMMARY","2005-06-01","2006-11-15"]
["IJ16040506","PROCUREMENT START - BXS Spect  PS 15KW","2005-09-01","2005-08-31"]
["IJ16040507","15kw Power Supply (B3-Spect)","2005-09-01","2005-12-12"]
["IJ16040510","RCV: Power Supply (B3- Spect)","2005-12-13","2005-12-12"]
["IJ16040543","AVAIL: All BXS Spect  PS 15KW parts","2005-12-13","2005-12-12"]
["IJ16040582","Conduct Design Review","2005-06-01","2005-06-01"]
["IJ16040584","COMP: BXS Spect  PS 15KW Fab & Assembly","2005-12-13","2005-12-12"]
["IJ16040588","Perform BXS Spect  PS 15KW Pre-Install Qual Test","2006-10-19","2006-11-15"]
["IJ16040590","AVAIL: BXS Spect  PS 15KW Ready for Install","2006-11-16","2006-11-15"]
["IJ160406","MCOR_1 SUMMARY","2005-05-02","2006-11-15"]
["IJ16040606","PROCUREMENT START - MCOR_1 (12Amp)","2006-02-24","2006-02-23"]
["IJ16040607","RCV:12 Amp Power Supply (MCOR 1) (16 ps)","2006-07-25","2006-07-24"]
["IJ16040625","12 Amp Power Supply (MCOR 1) (16 ps)","2006-02-24","2006-07-24"]
["IJ16040667","AVAIL: All MCOR_1 parts","2006-07-25","2006-07-25"]
["IJ16040684","Conduct Design Review","2005-05-02","2005-05-02"]
["IJ16040686","COMP: MCOR_1 Fab & Assembly","2006-10-19","2006-10-18"]
["IJ16040688","Perform MCOR_1 Pre-Install Qual Test","2006-10-19","2006-11-15"]
["IJ16040690","AVAIL: MCOR_1 Ready for Install","2006-11-16","2006-11-15"]
["IJ160407","MCOR_2 SUMMARY","2005-09-01","2006-11-16"]
["IJ16040704","Conduct Design Panel","2006-10-03","2006-10-03"]
["IJ16040706","PROCUREMENT START - MCOR_2 (12Amp)","2005-09-01","2005-08-31"]
["IJ16040716","30 Amp Power Supply - (MCOR_2)","2005-09-01","2006-02-15"]
["IJ16040725","Perform MCOR_2 Pre-Install Qual Test","2006-10-19","2006-11-15"]
["IJ16040791","AVAIL: All MCOR_2 parts","2006-11-16","2006-11-16"]
["IJ16040792","RCV: 30 Amp Power Supply - (MCOR_2)","2006-02-16","2006-02-15"]
["IJ160408","MCOR_3 SUMMARY","2005-05-02","2006-11-15"]
["IJ16040806","PROCUREMENT START - MCOR_3 (30Amp)","2005-09-01","2005-08-31"]
["IJ16040807","RCV:30Amp Power Supply - (MCOR_3)","2006-02-16","2006-02-15"]
["IJ16040825","30Amp Power Supply - (MCOR_3)","2005-09-01","2006-02-15"]
["IJ16040863","AVAIL: All MCOR_3 parts","2006-02-16","2006-02-16"]
["IJ16040884","Conduct Design Review","2005-05-02","2005-05-02"]
["IJ16040886","COMP: MCOR_3 Fab & Assembly","2006-10-19","2006-10-18"]
["IJ16040888","Perform MCOR_3 Pre-Install Qual Test","2006-10-19","2006-11-15"]
["IJ16040890","AVAIL: MCOR_3 Ready for Install","2006-11-16","2006-11-15"]
["IJ160409","MCOR_4 SUMMARY","2005-05-02","2006-11-15"]
["IJ16040906","PROCUREMENT START - MCOR_4  (12Amp)","2005-09-01","2005-08-31"]
["IJ16040907","RCV:Smart Analog Monitor (VMIC 3122)","2006-02-16","2006-02-15"]
["IJ16040925","30 Amp Power Supply (MCOR_4)","2005-09-01","2006-02-15"]
["IJ16040972","AVAIL: All MCOR_4 parts","2006-02-16","2006-02-16"]
["IJ16040984","Conduct Design Review","2005-05-02","2005-05-02"]
["IJ16040986","COMP: MCOR_4 Fab & Assembly","2006-10-19","2006-10-18"]
["IJ16040988","Perform MCOR_4 Pre-Install Qual Test","2006-10-19","2006-11-15"]
["IJ16040990","AVAIL: MCOR_4 Ready for Install","2006-11-16","2006-11-15"]
["IJ160411","MISC HARDWARE SUMMARY","2005-09-01","2006-10-18"]
["IJ16041100","Design Cableplant and Racks","2005-09-01","2006-02-08"]
["IJ16041104","Captar Documents","2005-09-16","2005-09-29"]
["IJ16041115","PROCUREMENT START - Misc Hardware","2005-10-21","2005-10-20"]
["IJ16041116","Cableplant and Rack Hardware","2005-10-21","2006-04-27"]
["IJ16041119","RCV: Cableplant and Rack Hardware","2006-04-28","2006-04-27"]
["IJ16041153","Prep Bid Pak - Single Bay Racks (DC/I&C)","2005-09-30","2005-10-20"]
["IJ16041154","RELEASE: RFP - Single Bay Racks (DC/I&C)","2005-10-21","2005-10-20"]
["IJ16041155","Vendors Prep Proposals - Single Bay Racks","2005-10-21","2005-11-17"]
["IJ16041156","RCV: Proposals - Single Bay Racks (DC/I&C)","2005-11-18","2005-11-17"]
["IJ16041157","Evaluate Proposals - Single Bay Racks (DC/","2005-11-18","2005-12-12"]
["IJ16041158","AWARD: Contract - Single Bay Racks (DC/I&C","2005-12-13","2005-12-13"]
["IJ16041159","Vendor Fab/Assy - Single Bay Racks","2005-12-14","2006-06-19"]
["IJ16041160","RCV: from Vendor - Single Bay Racks (DC/I&C)","2006-06-20","2006-06-19"]
["IJ16041163","Prep Bid Pak - Double Bay Racks","2005-09-30","2005-10-20"]
["IJ16041164","RELEASE: RFP - Double Bay Racks","2005-10-21","2005-10-20"]
["IJ16041165","Vendors Prep Proposals - Double Bay Racks","2005-10-21","2005-11-17"]
["IJ16041166","RCV: Proposals - Double Bay Racks","2005-11-18","2005-11-17"]
["IJ16041167","Evaluate Proposals - Double Bay Racks","2005-11-18","2005-12-12"]
["IJ16041168","AWARD: Contract - Double Bay Racks","2005-12-13","2005-12-13"]
["IJ16041169","Vendor Fab/Assy - Double Bay Racks","2005-12-14","2006-06-19"]
["IJ16041170","RCV: from Vendor - Double Bay Racks","2006-06-20","2006-06-19"]
["IJ160412","New  PS 10KW SUMMARY","2005-10-21","2006-11-15"]
["IJ16041203","Prep Bid Pak - Cableplant Install(DC.I&C)-S20","2005-09-30","2005-10-20"]
["IJ16041205","RELEASE: RFP - Cableplant Install(DC.I&C)-S20","2005-10-21","2005-10-20"]
["IJ16041206","PROCUREMENT START - Wiggler PS 10KW","2005-10-21","2005-10-20"]
["IJ16041207","Vendors Prep Prop-Cableplant Install(DC.I&C)-S20","2005-10-21","2005-11-17"]
["IJ16041209","RCV: Proposals - Cableplant Install(DC.I&C)-S20","2005-11-18","2005-11-17"]
["IJ16041210","RCV: Power Supply - (New)","2006-02-16","2006-02-15"]
["IJ16041211","10kw Power Supply - (New)","2005-10-21","2006-02-15"]
["IJ16041243","AVAIL: All Wiggler PS 10KW parts","2006-02-16","2006-02-15"]
["IJ16041260","COMP: Wiggler PS 10KW Fab & Assembly","2006-02-16","2006-02-15"]
["IJ16041262","Perform Wiggler PS 10KW Pre-Install Qual","2006-10-19","2006-11-15"]
["IJ16041264","AVAIL: Wiggler PS 10KW Ready for Install","2006-11-16","2006-11-15"]
["IJ16041267","Evaluate Prop-Cableplant Install(DC.I&C)-S20","2005-11-18","2005-12-05"]
["IJ16041268","AWARD: Contract - Cableplant Install(DC.I&C)-S20","2005-12-06","2005-12-06"]
["IJ16041269","AVAIL: Cableplant Ready to Install(DC.I&C)-S20","2006-06-27","2006-06-26"]
["IJ16041270","Vendor - Cableplant Install (DC. I&C)-S20","2006-04-03","2006-06-26"]
["IJ16041300","Integ Rack Rack HW & Internal AC Wiring - S20","2006-06-20","2006-07-06"]
["IJ16041305","Integ Rack Mount Pwr Supplies&Intra Cables - S20","2006-07-26","2006-10-18"]
["IJ16041315","Integ Rack/Crate Mount Cntrls&Intra-Cables - S20","2006-07-26","2006-09-06"]
["IJ16041320","Perform Pre-Install Testing Controls - S20","2006-09-07","2006-09-27"]
["IJ16041325","AVAIL:Preloaded Dbl Bay Racks Rdy to Insta - S20","2006-09-28","2006-09-27"]
["IJ17","INJECTOR INSTALLATION SUMMARY","2005-05-02","2007-11-26"]
["IJ1701","INJECTOR INFRASTRUCTURE INSTALL SUMMARY","2005-05-02","2007-02-01"]
["IJ17010010","Evaluate Data","2005-05-02","2005-05-27"]
["IJ17010011","Quality Control of Network","2005-05-31","2005-06-13"]
["IJ17010012","ED&I Engineering, Develop Installation Plan","2005-05-02","2005-09-30"]
["IJ17010015","Quality Control of Support Bolts","2006-01-25","2006-01-31"]
["IJ17010017","Fiducialize Components","2006-02-15","2006-05-10"]
["IJ17010020","Procure Alignment Parts","2006-01-03","2006-02-14"]
["IJ17010023","Pre-Align Supports","2006-05-11","2006-05-17"]
["IJ17010024","Align Gun","2006-05-18","2006-05-24"]
["IJ17010025","Mark Floor Support Bolts","2006-01-10","2006-01-24"]
["IJ17010026","Align Dipoles & Quads","2006-05-25","2006-06-22"]
["IJ17010027","Align Diagnostics","2006-06-23","2006-07-21"]
["IJ17010028","QC of Gun, Dipoles, Quads, & Diagnostics","2006-07-24","2006-08-04"]
["IJ17010030","Compute Layout Parameters","2006-01-03","2006-01-09"]
["IJ17010100","REQD: All Inj InfraStruct Equip Ready for Instl","2006-09-28","2006-09-27"]
["IJ17010102","Engineering Support for Cable Plant","2005-12-07","2006-01-19"]
["IJ17010103","UTR Support for Cable Plant","2006-06-27","2006-09-06"]
["IJ17010110","Install Cableplant, Integ Cntrls&Pwr Conv Racks","2006-09-28","2006-11-28"]
["IJ17010115","Install LCW systems","2006-09-28","2006-11-28"]
["IJ17010135","Install Thermocouples (60)/Isoplanes","2006-09-28","2006-10-11"]
["IJ17010140","Align Systems","2006-11-29","2007-01-10"]
["IJ17010145","Pump Down and Leak Check","2007-01-11","2007-02-01"]
["IJ1702","INJECTOR CONTROLS SUBSYS INSTALL SUMMARY","2007-08-07","2007-09-04"]
["IJ17020100","REQD: All Inj Controls Equip Ready for Instl","2007-08-07","2007-08-06"]
["IJ17020105","Install Controls","2007-08-07","2007-09-04"]
["IJ17020110","AVAIL: Controls Installed","2007-09-05","2007-09-04"]
["IJ1703","INJECTOR LASERS INSTALLATION SUMMARY","2005-11-03","2007-02-23"]
["IJ17030103","REQD:Laser Bay Opt Tables/Legs/Encls/Alignmt Lsr","2006-09-22","2006-09-21"]
["IJ17030105","Install Laser Bay Optical Tables/Alignment Laser","2006-10-02","2006-10-13"]
["IJ17030108","REQD: Vertical optical paths","2005-11-03","2005-11-02"]
["IJ17030110","Install vertical optical paths","2006-06-07","2006-06-27"]
["IJ17030112","REQD: Laser Heater optical paths","2005-11-03","2005-11-02"]
["IJ17030115","Install laser heater optical path","2006-06-07","2006-06-27"]
["IJ17030117","REQD: EO optical paths","2007-02-02","2007-02-01"]
["IJ17030120","Install EO optical paths","2007-02-02","2007-02-23"]
["IJ17030122","REQD: Synch Light Tube/Light Path for Strk Cam","2006-06-07","2006-06-06"]
["IJ17030125","Install Synch Light Tube/Light Path for Strk Cam","2006-06-07","2006-06-27"]
["IJ17030130","AVAIL: Laser Tables & Optical Paths Installed","2007-02-26","2007-02-23"]
["IJ1704","RF GUN & LOAD LOCK INSTALLATION SUMMARY","2005-05-02","2006-09-05"]
["IJ17040000","REQD: RF Gun Support Assy Ready for Instl","2006-05-01","2006-04-28"]
["IJ17040005","REQD: RF Gun Assembly Ready for Instl","2006-08-04","2006-08-03"]
["IJ17040010","REQD: Load Lock Support Assy Ready for Instl","2006-05-19","2006-05-18"]
["IJ17040015","REQD: Gun Load Lock Assy Ready for Instl","2005-05-02","2005-04-29"]
["IJ17040025","REQD: Gun Solenoid Ready for Instl","2006-06-27","2006-06-26"]
["IJ17040030","REQD: Corrector Supt Assy Ready for Instl","2005-09-29","2005-09-28"]
["IJ17040105","Install RF Gun Support Assy","2006-08-22","2006-09-05"]
["IJ17040110","Install RF Gun Assembly","2006-08-04","2006-08-10"]
["IJ17040115","Install Load Lock Support Assy","2006-05-19","2006-05-25"]
["IJ17040120","Install Gun Load Lock Assembly","2005-09-29","2005-10-05"]
["IJ17040121","AVAIL: RF Gun Installed & Aligned","2006-09-06","2006-09-05"]
["IJ17040122","AVAIL: Load Lock Installed & Aligned","2006-09-06","2006-09-05"]
["IJ17040125","Install Gun Sol Support Assembly","2006-08-22","2006-08-28"]
["IJ17040130","Install Gun Solenoid","2006-08-22","2006-08-28"]
["IJ17040135","Install Corrector Supt Assembly","2006-08-22","2006-08-28"]
["IJ17040140","Install Corrector Assembly","2006-08-22","2006-08-28"]
["IJ17040145","Install BPMs Supt Assy","2006-08-22","2006-08-28"]
["IJ17040150","Install BPMs Assy","2006-08-22","2006-08-28"]
["IJ17040155","Install Faraday Cups Supt Assy","2006-08-22","2006-08-28"]
["IJ17040160","Install Faraday Cups Assy","2006-08-22","2006-08-28"]
["IJ17040165","Install Gun E-Spect Support Assy","2006-08-22","2006-08-28"]
["IJ17040175","Install Dipoles Supt Assembly Ready for Install","2006-08-22","2006-08-28"]
["IJ17040180","Install Dipoles Assembly","2006-08-22","2006-08-28"]
["IJ1705","GUN to LINAC SECTION (GTL) INSTALLATION SUMMARY","2005-05-02","2006-09-05"]
["IJ17050105","Install GTL BPMs","2006-08-22","2006-09-05"]
["IJ17050110","Install GTL YAG1","2006-08-22","2006-08-28"]
["IJ17050115","Install GTL Current Monitors (CM1)","2006-08-22","2006-08-28"]
["IJ17050120","Install GTL E/O (EO1) BL Monitor/Opt Tables","2006-08-22","2006-08-28"]
["IJ17050125","Install GTL RF Phase Cavity","2006-08-22","2006-09-05"]
["IJ17050130","Install GTL Steering Coils","2006-08-22","2006-08-28"]
["IJ17050135","Install GTL Vacuum Components","2006-08-22","2006-09-05"]
["IJ17050140","Install GS Supports","2006-08-22","2006-08-28"]
["IJ17050145","Install GS Dipole","2006-08-22","2006-08-28"]
["IJ17050150","Install GS Current Monitor (CM2)","2006-08-22","2006-08-28"]
["IJ17050155","Install GS BPM (2)","2006-08-22","2006-08-28"]
["IJ17050160","Install GS Faraday Cup/YAG2","2006-08-22","2006-08-28"]
["IJ17050165","Install GS Quad Supports (3)","2006-08-22","2006-08-28"]
["IJ17050170","Install GS Quad (3)","2006-08-22","2006-08-28"]
["IJ17050175","Install GS Dump Shielding","2006-08-22","2006-08-28"]
["IJ17050180","AVAIL: GTL Installed","2006-09-06","2006-09-05"]
["IJ17050181","AVAIL: GS Installed","2006-08-29","2006-08-28"]
["IJ1706","INJECTOR LINAC STRUCTURES INSTALL SUMMARY","2006-06-02","2006-07-14"]
["IJ17060005","REQD: Linac Supports Ready for Instl","2006-06-02","2006-06-01"]
["IJ17060015","REQD: LO-2 Structure Ready for Instl","2006-06-02","2006-06-01"]
["IJ17060105","Install supports","2006-06-02","2006-06-29"]
["IJ17060110","Install LO-1 structure","2006-06-02","2006-06-08"]
["IJ17060111","AVAIL:  LO-1 structures installed","2006-07-10","2006-07-14"]
["IJ17060115","Install LO-2 structure","2006-06-02","2006-06-08"]
["IJ17060120","Install Loads","2006-06-02","2006-06-08"]
["IJ17060125","Install Linac Solenoid Support","2006-06-02","2006-06-08"]
["IJ17060130","Install Linac Solenoid","2006-06-02","2006-06-15"]
["IJ17060135","Install Plumbing","2006-06-02","2006-07-07"]
["IJ1707","L0-1 to L0-2 Section (L0-1TL0-2) INSTALL SUMMARY","2005-05-02","2006-05-01"]
["IJ17070021","REQD: Steering Coils Ready for Instl","2005-05-02","2005-04-29"]
["IJ17070105","Install RF Phase Cavity","2006-04-07","2006-04-13"]
["IJ17070110","Install Quads","2006-04-07","2006-04-13"]
["IJ17070115","Install BPM (2)","2006-04-07","2006-04-13"]
["IJ17070120","Install Steering Coil (4)","2006-04-07","2006-04-13"]
["IJ17070125","Install YAG (1)","2006-04-07","2006-04-13"]
["IJ17070130","Install Vacuum components","2006-04-07","2006-04-13"]
["IJ17070135","Install Current Monitor (1)","2006-04-07","2006-04-13"]
["IJ17070140","Install tube support structure","2006-04-07","2006-04-13"]
["IJ17070145","Final Alignment","2006-04-14","2006-04-20"]
["IJ17070150","AVAIL: LO-1TLO-2 Installed","2006-04-21","2006-04-20"]
["IJ1708","LINAC TO DL1 INSTALL & ALIGN SUMMARY","2005-05-02","2006-05-15"]
["IJ17080015","REQD:RF Kicker Ready for Instl","2006-05-02","2006-05-01"]
["IJ17080030","REQD: Supports Ready for Instl","2005-05-02","2005-04-29"]
["IJ17080035","REQD: PPS Stopper Ready for Instl","2005-10-03","2005-09-30"]
["IJ17080045","REQD: Quads Ready for Instl","2005-10-03","2005-09-30"]
["IJ17080050","REQD: BPMs Ready for Instl","2005-10-03","2005-09-30"]
["IJ17080055","REQD: Steering Coils Ready for Instl","2005-10-03","2005-09-30"]
["IJ17080060","REQD: OTRs Ready for Instl","2005-10-03","2005-09-30"]
["IJ17080065","REQD: BPMs Ready for Instl","2005-10-03","2005-09-30"]
["IJ17080070","REQD: Current Monitor Rdy for Instl","2005-10-03","2005-09-30"]
["IJ17080105","LTDL1-North Summary","2005-10-18","2005-10-31"]
["IJ17080110","Install supports  to VACV  N","2005-10-18","2005-10-24"]
["IJ17080115","Install Quads (4)","2005-10-18","2005-10-31"]
["IJ17080120","Install RF Kicker","2006-05-02","2006-05-15"]
["IJ17080130","Install Current Monitors","2005-10-18","2005-10-24"]
["IJ17080131","Install BPMs (4)","2005-10-18","2005-10-24"]
["IJ17080132","Install Steering Coil (1)","2005-10-18","2005-10-24"]
["IJ17080133","Install EO2","2005-10-18","2005-10-24"]
["IJ17080135","Final Alignment","2005-11-01","2005-11-02"]
["IJ17082140","LTDL1-South Summary","2005-10-18","2005-10-24"]
["IJ17082145","Install supports","2005-10-18","2005-10-24"]
["IJ17082150","Install PPS Stopper","2005-10-18","2005-10-24"]
["IJ17082160","Install Quads (2)","2005-10-18","2005-10-24"]
["IJ17082165","Install BPM","2005-10-18","2005-10-24"]
["IJ17082170","Install Steering Coil (3)","2005-10-18","2005-10-24"]
["IJ17082175","Install OTR (2)","2005-10-18","2005-10-24"]
["IJ17082180","Install BPM (6)","2005-10-18","2005-10-24"]
["IJ17082185","Install Current Monitor","2005-10-18","2005-10-24"]
["IJ17082190","AVAIL: LTDL1 Installed","2005-10-25","2005-10-24"]
["IJ1709","DOG LEG 1 BEND (DL1) INSTALLATION SUMMARY","2006-08-01","2006-09-19"]
["IJ17090005","REQD: Supports Ready for Instl","2006-08-01","2006-07-31"]
["IJ17090010","REQD:Dipoles (B01-B02) Ready for Instl","2006-08-01","2006-07-31"]
["IJ17090020","REQD: Quads Ready for Instl","2006-08-01","2006-07-31"]
["IJ17090025","REQD: BPMs Ready for Instl","2006-08-01","2006-07-31"]
["IJ17090030","REQD: Steering Coils Ready for Instl","2006-08-01","2006-07-31"]
["IJ17090035","REQD: OTR Ready for Instl","2006-08-01","2006-07-31"]
["IJ17090040","REQD: Toroid Ready for Instl","2006-08-01","2006-07-31"]
["IJ17090055","REQD: DL1 Vacuum Chamber Ready for Instl","2006-08-01","2006-07-31"]
["IJ17090102","Install DL1 Vacuum Chamber","2006-08-01","2006-08-01"]
["IJ17090103","AVAIL: DL1 Vacuum Chamber installed","2006-08-01","2006-08-01"]
["IJ17090105","Install supports","2006-08-02","2006-08-15"]
["IJ17090110","Install Dipoles (2) (B01-B02)","2006-08-01","2006-08-07"]
["IJ17090120","Install Quads (3)","2006-08-01","2006-08-14"]
["IJ17090125","Install BPM (1)","2006-08-01","2006-08-07"]
["IJ17090130","Install Steering Coil (1)","2006-08-01","2006-08-07"]
["IJ17090135","Install OTR (1)","2006-08-01","2006-08-07"]
["IJ17090140","Install Toroid","2006-08-01","2006-08-07"]
["IJ17090155","Final Alignment","2006-08-16","2006-08-29"]
["IJ1710","DL1 to LINAC (DL1TL) INSTALLATION SUMMARY","2006-08-01","2006-09-19"]
["IJ17100000","REQD: Supports Ready for Instl","2006-08-01","2006-07-31"]
["IJ17100005","REQD: Quads Ready for Instl","2006-08-01","2006-07-31"]
["IJ17100010","REQD: BPM Ready for Instl","2006-08-01","2006-07-31"]
["IJ17100015","REQD: Steering Coils Ready for Instl","2006-08-01","2006-07-31"]
["IJ17100020","REQD: OTR Ready for Instl","2006-08-01","2006-07-31"]
["IJ17100025","REQD: Current Monitor Ready for Instl","2006-08-01","2006-07-31"]
["IJ17100105","Install supports","2006-08-01","2006-08-14"]
["IJ17100110","Install Quads (2)","2006-08-01","2006-08-07"]
["IJ17100115","Install BPM (1)","2006-08-08","2006-08-14"]
["IJ17100120","Install Steering Coil (2)","2006-08-08","2006-08-14"]
["IJ17100125","Install OTR (1)","2006-08-08","2006-08-14"]
["IJ17100130","Install Current Monitor (1)","2006-08-08","2006-08-14"]
["IJ17100135","Final Alignment","2006-08-15","2006-08-28"]
["IJ17100140","AVAIL: DL1TL Installed","2006-08-29","2006-08-28"]
["IJ1710_010","REQD:  Insertion Area Components RFI","2006-08-22","2006-08-21"]
["IJ1710_020","AVAIL:  Insertion Area Components Installed","2006-09-20","2006-09-19"]
["IJ1711","STRAIGHT AHEAD BEAMLINE (SAB) INSTALL SUMMARY","2006-08-01","2006-09-19"]
["IJ17110000","REQD: SAB Spectrometer Dipole Ready for Instl","2006-08-01","2006-07-31"]
["IJ17110005","REQD: SAB Quadrupoles (3) Ready for Instl","2006-08-01","2006-07-31"]
["IJ17110010","REQD: SAB Current Monitor (1) Ready for Instl","2006-08-01","2006-07-31"]
["IJ17110015","REQD: SAB BPM Ready for Instl","2006-08-01","2006-07-31"]
["IJ17110020","REQD: SAB OTR/YAG (1) Ready for Instl","2006-08-01","2006-07-31"]
["IJ17110025","REQD: SAB Vacuum Chamber Ready for Instl","2006-08-01","2006-07-31"]
["IJ17110030","REQD: SAB Beam Dump & Shielding Ready for Instl","2006-08-01","2006-07-31"]
["IJ17110035","REQD: SAB Supports Ready for Instl","2006-08-01","2006-07-31"]
["IJ17110036","REQD: SAB Steering Coils (2) Ready for Instl","2006-08-01","2006-07-31"]
["IJ17110105","Install SAB Spectrometer Dipole","2006-08-22","2006-08-28"]
["IJ17110110","Install SAB Quadrupoles (3)","2006-08-22","2006-09-05"]
["IJ17110115","Install SAB Current Monitor (1)","2006-08-22","2006-08-28"]
["IJ17110120","Install SAB BPM (1)","2006-08-22","2006-08-28"]
["IJ17110125","Install SAB OTR/YAG (1)","2006-08-22","2006-08-28"]
["IJ17110130","Install SAB Vacuum Chamber and Components","2006-08-22","2006-08-28"]
["IJ17110135","Install SAB Beam Dump and Shielding","2006-08-22","2006-09-05"]
["IJ17110140","Install SAB Supports","2006-08-22","2006-09-05"]
["IJ17110141","Install Steering Coils (2)","2006-08-22","2006-08-28"]
["IJ17110145","Final Alignment","2006-09-06","2006-09-19"]
["IJ17110150","AVAIL: SAB Installed","2006-09-20","2006-09-19"]
["IJ1711_010","REQD:  Spectrometer Area Components RFI","2006-08-22","2006-08-21"]
["IJ1711_020","AVAIL:  Spectrometer Area Components Installed","2006-09-20","2006-09-19"]
["IJ1712","INJECTOR RF WAVEGUIDE INSTALLATION SUMMARY","2005-05-02","2006-08-09"]
["IJ17120000","REQD:Vertical Drop Waveguide Rdy to Install","2005-10-03","2005-09-30"]
["IJ17120001","REQD:Klystron Housing Waveguide Rdy to Install","2005-05-02","2005-04-29"]
["IJ17120002","REQD:Injector Housing Waveguide Rdy to Install","2005-05-02","2005-04-29"]
["IJ17120003","REQD:Transverse Kicker Waveguide Rdy to Install","2006-08-01","2006-07-31"]
["IJ17120005","Install Vertical Drop Waveguide","2005-10-03","2005-10-11"]
["IJ17120006","Install Klystron Housing Waveguide","2005-10-12","2005-10-20"]
["IJ17120007","Install Injector Housing Waveguide","2005-10-21","2005-10-31"]
["IJ17120008","Install Transverse Kicker Waveguide","2006-08-01","2006-08-09"]
["IJ17120010","AVAIL: Vertical Drop Waveguide Installed","2005-10-12","2005-10-11"]
["IJ17120011","AVAIL: Klystron Housing Waveguide Installed","2005-10-21","2005-10-20"]
["IJ17120012","AVAIL: Injector Housing Waveguide Installed","2005-11-01","2005-10-31"]
["IJ17120013","AVAIL: Transverse Kicker Waveguide Installed","2006-08-10","2006-08-09"]
["IJ17120018","Install RF Waveguides","2006-04-03","2006-04-07"]
["IJ1712_010","REQD:  Inj RF High Power Components RFI","2005-05-02","2005-04-29"]
["IJ1712_020","AVAIL:  Inj RF High Power Components Installed","2006-08-10","2006-08-09"]
["IJ1713","INJECTOR RF SUBSYS INSTALLATION SUMMARY","2006-11-27","2007-05-25"]
["IJ17130000","AVAIL: Injector RF Subsystem Installed","2006-11-27","2006-11-22"]
["IJ17130100","REQD: All Inj RF Subsys Equip Ready for Instl","2006-11-27","2006-11-22"]
["IJ1713_010","REQD:  Inj RF Low Level Components RFI","2007-05-29","2007-05-25"]
["IJ1713_020","AVAIL:  Inj RF Low Level Components Installed","2006-11-27","2006-11-22"]
["IJ1714","CATHODE AND LOAD LOCK INSTALLATION SUMMARY","2005-05-02","2007-03-07"]
["IJ17140000","REQD: Cathode Assy Ready for Instl","2005-05-02","2005-04-29"]
["IJ17140005","REQD: CP Load Lock Supts Ready for Instl","2005-05-02","2005-04-29"]
["IJ17140010","REQD: CP Load Lock Ready for Instl","2005-05-02","2005-04-29"]
["IJ17140015","REQD: CP Station Ready for Instl","2007-02-14","2007-02-13"]
["IJ17140020","REQD: CP Lab Ready for Instl","2005-05-02","2005-04-29"]
["IJ17140105","Install CP Cathode Assembly","2005-05-02","2005-05-20"]
["IJ17140110","Install CP Load Lock Supports Ready for Install","2005-05-02","2005-05-20"]
["IJ17140115","Install CP Load Lock","2005-05-02","2005-05-20"]
["IJ17140120","Install CP Station","2007-02-14","2007-03-07"]
["IJ17140125","Install CP Lab Infrastructure","2005-05-02","2005-05-20"]
["IJ17140130","AVAIL: CP Station Installed","2007-03-08","2007-03-07"]
["IJ1714_010","REQD:  Cathode & Load Lock Components RFI","2005-05-02","2005-04-29"]
["IJ1714_020","AVAIL:  Cathode & Load Lock Components Installed","2007-03-08","2007-03-07"]
["IJ1715","INJECTOR LASER HEATER SUBSYS INSTALL SUMMARY","2007-09-05","2007-11-26"]
["IJ17150000","REQD: Enclosures,Tubes&Supports Ready for Instl","2007-11-08","2007-11-07"]
["IJ17150005","REQD:Magnet Supports Ready for Instl","2007-09-05","2007-09-04"]
["IJ17150020","REQD: Undulator Ready for Instl","2007-09-05","2007-09-04"]
["IJ17150105","Install  Enclosures,Tubes&Supports","2007-11-08","2007-11-21"]
["IJ17150106","AVAIL: Enclosures,Tubes&Supports Installed","2007-11-26","2007-11-21"]
["IJ17150110","Install Magnet Supports","2007-09-05","2007-09-18"]
["IJ17150115","Install Photon Diagnostics Supports","2007-09-19","2007-09-25"]
["IJ17150116","AVAIL: Photon Diagnostics Supports Installed","2007-09-26","2007-09-25"]
["IJ17150120","Install Beampipe","2007-09-05","2007-09-18"]
["IJ17150125","Install Undulator","2007-09-05","2007-09-25"]
["IJ17150130","AVAIL: Laser Heater Installed","2007-09-26","2007-09-25"]
["IJ1715_010","REQD:  Inj Laser Heater Components RFI","2007-09-05","2007-09-04"]
["IJ1715_020","AVAIL:  Inj Laser Heater Components Installed","2007-11-26","2007-11-21"]
["IJ1716","FY04 SECTOR 20 FACILITY PREPS SUMMARY","2005-05-02","2009-03-31"]
["IJ1717","POWER CONVERSION SUBSYSTEM INSTALL SUMMARY","2006-06-15","2007-05-02"]
["IJ17170000","REQD: Injector MCOR 1","2006-11-16","2006-11-15"]
["IJ17170005","Install Injector MCOR 1","2006-11-16","2006-11-22"]
["IJ17170010","REQD: Injector MCOR 2","2006-11-17","2006-11-16"]
["IJ17170015","Install Injector MCOR 2","2006-11-17","2006-11-27"]
["IJ17170020","REQD: Injector MCOR 3","2006-11-16","2006-11-15"]
["IJ17170025","Install Injector MCOR 3","2006-11-16","2006-11-22"]
["IJ17170030","REQD: Injector MCOR 4","2006-11-16","2006-11-15"]
["IJ17170035","Install Injector MCOR 4","2006-11-16","2006-11-22"]
["IJ17170040","REQD: Wiggler PS 15KW","2006-11-16","2006-11-15"]
["IJ17170045","Install Wiggler PS 15KW","2006-11-16","2006-11-22"]
["IJ17170050","REQD: Injector Solenoid 1PS 15KW","2006-11-16","2006-11-15"]
["IJ17170055","Install Injector Solenoid 1PS 15KW","2006-11-16","2006-11-22"]
["IJ17170060","REQD: Injector Solenoid 2PS 30KW","2006-11-16","2006-11-15"]
["IJ17170065","Install Injector Solenoid 2PS 30KW","2006-11-16","2006-11-22"]
["IJ17170070","REQD: Injector B0.5 Spect PS 2KW","2006-11-16","2006-11-15"]
["IJ17170075","Install Injector B0.5 Spect PS 2KW","2006-11-16","2006-11-22"]
["IJ17170080","REQD: Injector B1-2 PS 15KW","2006-11-16","2006-11-15"]
["IJ17170085","Install Injector B1-2 PS 15KW","2006-11-16","2006-11-22"]
["IJ17170090","REQD: Injector B3 Spect PS 15KW","2006-11-16","2006-11-15"]
["IJ17170095","Install Injector B3 Spect PS 15KW","2006-11-16","2006-11-22"]
["IJ17170100","REQD: Injector MPS Equipment","2007-03-13","2007-03-12"]
["IJ17170105","Install Injector MPS Equipment","2007-03-13","2007-03-19"]
["IJ17170110","REQD: Injector PPS Equipment","2007-04-26","2007-04-25"]
["IJ17170115","Install Injector PPS Equipment","2007-04-26","2007-05-02"]
["IJ17170120","REQD: Laser Room PPS","2006-06-15","2006-06-14"]
["IJ17170122","AVAIL: Power Conversion System Installed","2007-05-03","2007-05-02"]
["IJ17170125","Install Laser Room PPS","2006-06-15","2006-06-21"]
["IJ1717_010","REQD:  Injector Power Conv Components RFI","2006-11-16","2006-11-15"]
["IJ1717_020","AVAIL:  Injector Power Conv Components Installed","2007-05-03","2007-05-02"]
["IJ17_30010","REQD:  Injector Laser Components RFI","2006-06-07","2006-06-06"]
["IJ17_30020","AVAIL:  Injector Laser Components Installed","2007-02-26","2007-02-23"]
["IJ17_40010","REQD:  Gun Area Components RFI","2006-08-22","2006-08-21"]
["IJ17_40020","AVAIL: Gun Area Components Installed","2006-09-06","2006-09-05"]
["IJ17_60010","REQD:  Accelerator Area Components RFI","2006-06-02","2006-06-01"]
["IJ17_60020","AVAIL:  Accelerator Area Components Installed","2006-07-17","2006-07-14"]
["IJ17_70010","REQD:  Heater Area Components RFI","2006-04-07","2006-04-06"]
["IJ17_70020","AVAIL:  Heater Area Components Installed","2006-05-02","2006-05-01"]
["IJ17_80010","REQD:  Wall Area Components RFI","2005-10-18","2005-10-17"]
["IJ17_80020","AVAIL:  Wall Area Components Installed","2005-10-25","2005-10-24"]
["IJ21702","DRIVE LASER COMMISSIONING SUMMARY","2006-07-27","2007-08-02"]
["IJ21702115","Integrate: Drive Laser","2006-07-27","2006-09-07"]
["IJ21702117","Integrate: OSC Diagnostics","2006-09-08","2006-09-14"]
["IJ21702120","Checkout & Integrate: Pre-Amp Diagnostics","2006-09-15","2006-10-05"]
["IJ21702130","Checkout & Integrate: Low Power Compressor","2006-09-15","2006-09-28"]
["IJ21702140","Checkout & Integrate: Final Amplifier diagnostic","2006-09-29","2006-10-26"]
["IJ21702180","Checkout & Integrate:Timing stability monitoring","2006-11-17","2007-01-31"]
["IJ21702220","Checkout & Integrate: Beam relay & Encl","2007-02-01","2007-02-14"]
["IJ21702240","Checkout & Integrate: UV conversion diagnostics","2006-10-27","2006-11-16"]
["IJ21702290","Checkout & Integrate: UV transport & launch Opt","2007-02-15","2007-03-29"]
["IJ21702355","AVAIL: UV Beam to the Cathode","2007-03-30","2007-03-29"]
["IJ21702360","UV Conditioning","2007-03-30","2007-08-02"]
["IJ21702365","Integration of the Drive Laser Controls","2006-12-06","2007-04-27"]
["IJ21702367","C/O & Integ: Visible Beam transport & diag","2007-02-26","2007-04-06"]
["IJ21702369","C/O & Integ: IR Beam transport & diag","2007-04-09","2007-04-27"]
["IJ21702370","AVAIL: Drive Laser","2007-08-03","2007-08-02"]
["IJ21703","RF Conditioning","2007-05-03","2007-07-06"]
["IJ21704000","RF Gun Operation with Beam","2007-07-09","2007-10-08"]
["IJ21704005","RF Gun Operation with Beam","2007-10-09","2007-10-26"]
["IJ21705","L0-1 & L0-2 Commissioning","2007-08-22","2007-11-21"]
["IJ21706","L0 & SAB Commissioning","2007-10-08","2007-11-08"]
["IJ21707","DL1 Commissioning","2007-11-09","2008-01-07"]
["IJ21708","Injector Optimization","2008-01-08","2008-06-24"]
["IJ22320000","Drive Laser Spares","2006-10-03","2007-08-30"]
["IJ22410000","RF Gun R&D (GTF)","2005-05-02","2005-10-31"]
["IJ22410001","RF Gun R&D (GRF) Procurement","2005-05-02","2005-10-31"]
["IJ22410020","GTF - Demostrate sustained 120MV/m gun ops","2005-11-21","2005-12-20"]
["IJ22410030","GTF - RF pulse shaping, pwr dissapation for gun","2005-12-12","2005-12-21"]
["IJ22410040","GTF - Test RF H+ plasma cleaning","2006-02-01","2006-03-15"]
["IJ22410050","GTF - Install new cathode/test H+ beam cleaner","2005-11-01","2006-03-30"]
["IJ22410060","GTF - Reconstruct 4D tomographic","2006-04-03","2006-05-15"]
["IJ22410070","GTF - Test digital cameras for LCLS Injector","2006-04-03","2006-05-15"]
["IJ22410080","GTF - Meas resolution of YAG screens","2006-05-15","2006-07-03"]
["IJ22410090","GTF - Procure materials, laser parts, lenses","2005-12-01","2006-06-01"]
["IJ22410100","Cathode - Modify SLAC Physical Elecrics Syst","2005-11-07","2005-12-15"]
["IJ22410110","Cathode - Meas QE v Wavelength of Sample/Cathode","2005-11-07","2006-06-01"]
["IJ22410120","Cathode - Test cleaned samples and cathodes","2005-11-07","2006-06-01"]
["IJ22410130","Cathode - Establish cathode txfer method","2006-06-02","2006-07-03"]
["IJ22410140","Cathode - Procure cathode materials","2005-12-09","2006-07-03"]
["IJ22520000","GTL Spares","2006-10-03","2007-08-30"]
["IJ22620000","Linac Spares","2006-10-03","2007-08-30"]
["IJ22720000","L0-1 to L0-2 Spares","2006-10-03","2007-08-30"]
["IJ22820000","Linac to DL1 Spares","2006-10-03","2007-08-30"]
["IJ22920000","DL1 Spares","2006-10-03","2007-08-30"]
["IJ22A20000","DL1 to Linac Spares","2006-10-03","2007-08-30"]
["IJ22B20000","SAB Spares","2006-10-03","2007-08-30"]
["IJ22C20000","RF Waveguides Spares","2006-10-03","2007-08-30"]
["IJ22E20000","CP Spares","2006-10-03","2007-08-30"]
["IJ301_1010","Conduct UV Spatial Shaping Test (ANL)","2005-05-02","2005-11-15",null,"2005-05-02"]
["IJ301_2500","Modeling - integrated model","2005-08-01","2005-08-19"]
["IJ301_2510","Modeling - modeling and validation","2005-08-22","2006-01-24"]
["IJ301_2520","Modeling - convert then stretch","2005-08-22","2005-11-29"]
["IJ301_2530","Modeling - review","2005-11-30","2005-11-30"]
["IJ301_2540","Temporal Pulse Shaping - IR shaping","2005-08-01","2005-08-12"]
["IJ301_2545","Temporal Pulse Shaping - review","2005-08-15","2005-08-15"]
["IJ301_2550","Temporal Pulse Shaping - blue shaping","2005-10-26","2006-01-24"]
["IJ301_2560","Temporal Pulse Shaping - UV shaping","2005-10-26","2006-01-24"]
["IJ301_2590","UV Conversion - activate initial crystals","2005-08-01","2005-11-07"]
["IJ301_2600","UV Conversion - specify final crystals","2005-11-08","2005-11-09"]
["IJ301_2610","UV Conversion - procure final crystals","2005-11-10","2005-12-21"]
["IJ301_2620","UV Conversion - activate final crystals","2005-12-22","2006-01-30"]
["IJ301_2630","UV Conversion - review","2006-01-31","2006-01-31"]
["IJ301_2640","IR Diagnostics - Design and specify","2005-08-01","2005-08-12"]
["IJ301_2650","IR Diagnostics - review","2005-08-15","2005-08-15"]
["IJ301_2660","IR Diagnostics - final design","2005-08-16","2005-08-22"]
["IJ301_2670","IR Diagnostics - procure","2005-08-23","2005-09-13"]
["IJ301_2680","IR Diagnostics - activate","2005-09-14","2005-10-12"]
["IJ301_2690","Blue Diagnostics - design and specify","2005-08-02","2005-08-15"]
["IJ301_2700","Blue Diagnostics - procure","2005-08-16","2005-09-13"]
["IJ301_2710","Blue Diagnostics - activate","2005-09-14","2005-10-25"]
["IJ301_2720","UV Diagnostics - design and specify","2005-08-02","2005-08-15"]
["IJ301_2730","UV Diagnostics - procure","2005-08-16","2005-09-13"]
["IJ301_2740","UV Diagnostics - activate","2005-09-14","2005-10-25"]
["IJ301_2745","UV Diagnostics - reveiw","2005-10-26","2005-10-26"]
["IJ301_2750","Cathode Launch Optics - test prototype optics","2005-10-27","2006-02-02"]
["IJ301_2760","Steering Stabilization - support design","2005-08-16","2006-01-27"]
["IJ301_2780","Support Drive Laser Intgr - integrate shaping","2005-11-08","2006-04-11"]
["IJ308_0100","Finalize the design (for normal incidence)","2005-08-01","2005-10-11"]
["IJ308_0110","Create Assembly Drawings","2005-10-12","2006-03-08"]
["IJ308_0120","Release Drawings","2006-03-09","2006-04-05"]
["IJ401_1005","Gun Design - Physics (BCR-IJ22)","2005-09-01","2005-09-29"]
["IJ401_1010","Mechanical Design RF Gun","2005-05-02","2005-11-17"]
["IJ401_1020","COMP:  RF Features Incorporated into Design","2005-06-21","2005-06-20"]
["IJ401_1030","COMP:  RF Gun Mechanical Design Review","2005-11-18","2005-11-17"]
["IJ401_1040","Design/Draft RF Gun","2005-06-21","2005-11-17"]
["IJ401_1050","Procure RF Gun Parts","2005-10-20","2006-01-30"]
["IJ401_1060","Fabricate RF Gun","2006-03-15","2006-07-06"]
["IJ401_1070","Cold Test RF Gun","2006-07-07","2006-07-13"]
["IJ401_1080","Bake RF Gun","2006-07-14","2006-07-27"]
["IJ401_1090","Post Bake Assembly","2006-07-28","2006-08-03"]
["IJ401_1100","AVAIL: RF Gun Assembly Ready for Install","2006-08-04","2006-08-03"]
["IJ401_1110","Gun Design for Normal Incidence","2005-08-01","2006-02-15"]
["IJ401_1120","Procure Hardware for Normal Incidence","2006-02-16","2006-06-09"]
["IJ401_1130","Procure Extra Valve for RF Gun","2005-10-20","2006-01-30"]
["IJ401_1140","Machine RF Gun Parts","2005-10-20","2006-01-30"]
["IJ401_1150","QC Machine Parts","2006-01-31","2006-02-21"]
["IJ401_1160","Clean & Plate Machine Parts","2006-02-22","2006-03-14"]
["IJ401_1170","Design Gun Hot Test","2005-11-01","2006-01-06"]
["IJ401_1180","Design/Draft RF Hot Test Componenets","2005-11-01","2006-01-06"]
["IJ401_1190","Procure RF Hot Test Parts","2006-01-09","2006-03-21"]
["IJ401_1200","Fabricate RF Hot Test Parts","2006-03-22","2006-05-31"]
["IJ401_1210","Clean and Plate RF Hot Test Parts","2006-03-22","2006-05-31"]
["IJ461_0020","Develop L0A & B Mech Engrg & Design / Waveguide","2005-05-02","2005-08-01"]
["IJ461_0025","Develop L0A & B Eng & Dsg/ Waveguide (BCR-IJ-20)","2005-05-02","2005-08-01"]
["IJ461_0030","COMP: L0A & B Mech Engr & Design / Waveguide","2005-08-02","2005-08-01"]
["IJ461_0035","QC Structures for L0A &B","2005-05-02","2005-07-25"]
["IJ461_0037","QC Structures for L0A &B (BCR-IJ-20)","2005-08-01","2005-08-19"]
["IJ461_0040","Procure L0A & B Material","2005-08-02","2005-11-21"]
["IJ461_0050","REQD: Existing L0A &B StructSections from SLAC","2005-08-02","2005-08-01"]
["IJ461_0060","Fabricate and Modify L0A &B","2005-05-02","2006-02-15"]
["IJ461_0065","REQD:  L0-A Solenoid","2006-03-17","2006-03-16"]
["IJ461_0070","Integrate L0A &B onto Support Structure","2006-02-16","2006-03-01"]
["IJ461_0080","Perform L0A &B Vacuum Processing","2006-03-02","2006-04-17"]
["IJ461_0090","Perform L0A &B Waveguide Integration","2005-05-02","2006-04-28"]
["IJ461_0100","Prep for & Perform L0A &B RF tuning","2006-03-02","2006-03-15"]
["IJ461_0120","Conduct L0A &B RF Processing","2006-03-16","2006-06-01"]
["IJ461_0130","AVAIL: L0A &B Structure Ready for Install","2006-06-02","2006-06-01"]
["IJ461_0150","Evaluate and Condition 10' S-band Structures","2005-07-01","2005-08-26"]
["IJ501_1010","Prep Bid Pak - GS Dipole Assembly and Suppt","2005-05-16","2005-11-01"]
["IJ501_1020","RELEASE RFP: GS Dipole Assembly and Suppt","2005-11-02","2005-11-15"]
["IJ501_1030","Vendor Prep Proposals - GS Dipole Assm and Suppt","2005-11-16","2005-12-08"]
["IJ501_1040","RCV: Proposals - GS Dipole Assembly and Suppt","2005-12-09","2005-12-08"]
["IJ501_1050","Evaluate Proposals -GS Dipole Assembly and Suppt","2005-12-09","2005-12-13"]
["IJ501_1060","AWARD: Contract for GS Dipole Assembly and Suppt","2005-12-14","2005-12-15"]
["IJ501_1070","Vendor Fab GS Dipole Assembly and Suppt","2005-12-16","2006-04-17"]
["IJ501_1075","Review Vendor GS Dipole Design","2006-03-01","2006-03-07"]
["IJ501_1080","RCV: GS Dipole Assembly and Suppt","2006-04-18","2006-04-18"]
["IJ501_1090","Perform QC/MM on Dipole Assm & Suppt","2006-04-19","2006-05-16"]
["IJ501_1100","AVAIL:  GS Dipole Assm and Suppt Ready for Inst","2006-05-17","2006-05-16"]
["IJ501_2010","Design DL1 B01 & B02 Dipole","2005-06-15","2005-08-10"]
["IJ501_2020","Prep Bid Pak - DL1 Dipole Assembly and Suppt","2005-05-02","2005-09-01"]
["IJ501_2030","RELEASE RFP: DL1 Dipole Assembly and Suppt","2005-09-02","2005-09-06"]
["IJ501_2040","Vendor Prep Proposals - DL1 Dipole Assm and Sppt","2005-09-07","2005-09-20"]
["IJ501_2050","RCV: Proposals - DL1 Dipole Assm and Sppt","2005-09-21","2005-09-20"]
["IJ501_2060","Evaluate Proposals DL1 Dipole Assm and Sppt","2005-09-21","2005-09-27"]
["IJ501_2070","AWARD: Contract for DL1 Dipole Assm and Sppt","2005-09-28","2005-09-29"]
["IJ501_2080","Vendor Fab DL1 Dipole Assm and Sppt","2005-09-30","2006-03-30"]
["IJ501_2090","RCV: DL1 Dipole Assm and Sppt","2006-03-31","2006-03-31"]
["IJ501_2100","Perform QC/MM on DL1 Dipole Assm and Sppt","2006-04-03","2006-05-31"]
["IJ501_2110","AVAIL:  DL1 Dipole Assm and Sppt RFI","2006-06-01","2006-05-31"]
["IJ501_3020","Prep Bid Pak - BXS Dipole Assembly and Suppt","2005-10-03","2006-01-03"]
["IJ501_3030","RELEASE RFP: SAB Dipole Assembly and Suppt","2006-01-04","2006-01-05"]
["IJ501_3040","Vendor Prep Proposals - SAB Assm and Suppt","2006-01-06","2006-02-03"]
["IJ501_3050","RCV: Proposals - SAB Assembly and Suppt","2006-02-06","2006-02-03"]
["IJ501_3060","Evaluate Proposals SAB Assembly and Suppt","2006-02-06","2006-02-10"]
["IJ501_3070","AWARD: Contract for SAB Assembly and Suppt","2006-02-13","2006-02-15"]
["IJ501_3080","Vendor Fab SAB Dipole Assembly and Suppt","2006-02-16","2006-07-06"]
["IJ501_3085","Review Vendor SAB Spectrometer Dipole Design","2006-04-14","2006-04-14"]
["IJ501_3090","RCV: SAB Dipole Assembly and Suppt","2006-07-07","2006-07-07"]
["IJ501_3100","Perform QC/MM on SAB Dipole Assm & Suppt","2006-07-10","2006-07-19"]
["IJ501_3110","AVAIL:  SAB Dipole Assm and Suppt RFI","2006-07-20","2006-07-19"]
["IJ501_4020","Prep Bid Pak - Chicane Dipole Assembly and Suppt","2005-05-02","2005-09-30"]
["IJ501_4030","RELEASE RFP: Chicane Dipole Assembly and Suppt","2005-10-03","2005-10-03"]
["IJ501_4040","Vendor Prep Proposals - Chicane Assm and Suppt","2005-10-04","2005-10-10"]
["IJ501_4050","RCV: Proposals - Chicane Assembly and Suppt","2005-10-11","2005-10-10"]
["IJ501_4060","Evaluate Proposals -Chicane Assembly and Suppt","2005-10-11","2005-10-12"]
["IJ501_4070","AWARD: Contract for Chicane Assembly and Suppt","2005-10-13","2005-10-14"]
["IJ501_4080","Vendor Fab Chicane Dipole Assembly and Suppt","2005-10-17","2006-04-17"]
["IJ501_4085","Review Vendor Chicane Dipole Design","2005-12-14","2005-12-14"]
["IJ501_4090","RCV: Chicane Dipole Assembly and Suppt","2006-04-18","2006-04-18"]
["IJ501_4100","Perform QC/MM on Chicane Dipole Assm & Suppt","2006-04-19","2006-05-16"]
["IJ501_4110","AVAIL:  Chicane  Dipole Assm and Suppt RFI","2006-05-17","2006-05-16"]
["IJ502_1010","Prep Bid Pak - GS Quads Assy & Sppt","2005-05-02","2005-10-17"]
["IJ502_1020","RELEASE RFP:  GS Quads Assy & Sppt","2005-10-18","2005-10-31"]
["IJ502_1030","Vendor Prep Proposals -  GS Quads Assy & Sppt","2005-11-01","2005-12-14"]
["IJ502_1040","RCV: Proposals -  GS Quads Assy & Sppt","2005-12-15","2005-12-14"]
["IJ502_1050","Eval Proposals -  GS Quads Assy & Sppt","2005-12-15","2006-01-12"]
["IJ502_1060","AWARD:Contract for GS Quads Assy & Sppt","2006-01-13","2006-01-20"]
["IJ502_1070","Vendor Fab  GS Quads Assy & Sppt","2006-01-23","2006-03-08"]
["IJ502_1080","RCV:   GS Quads Assy & Sppt","2006-03-09","2006-03-09"]
["IJ502_1090","Perform QC/MM on GS Quads Assy & Sppt","2006-03-10","2006-04-06"]
["IJ502_1100","AVAIL:  GS Quads Assy & Sppt RFI","2006-04-07","2006-04-06"]
["IJ502_2010","Design Injector Quads","2005-08-01","2005-09-12"]
["IJ502_2020","RELEASE RFP:  Inj Quads  Assy & Sppt","2005-05-02","2005-04-29"]
["IJ502_2030","Vendor Prep Proposals -  Inj Quads Assy & Sppt","2005-05-02","2005-04-29"]
["IJ502_2040","RCV: Proposals -  Inj Quads Assy & Sppt","2005-05-02","2005-04-29"]
["IJ502_2050","Eval Proposals -  Inj Quads Assy & Sppt","2005-05-02","2005-05-06"]
["IJ502_2060","AWARD:Contract for  Inj Quads Assy & Sppt","2005-06-28","2005-06-30"]
["IJ502_2070","Vendor Fab  Inj Quads Assy & Sppt","2005-07-01","2005-11-15"]
["IJ502_2075","Review Vendor Inj Quad","2005-08-29","2005-08-29"]
["IJ502_2080","RCV:   Inj Quads Assy & Sppt","2005-11-16","2005-11-16"]
["IJ502_2090","Perform QC/MM on  Inj Quads Assy & Sppt","2005-11-17","2006-02-01"]
["IJ502_2100","AVAIL:   Inj Quads Assy & Sppt RFI","2006-02-02","2006-02-01"]
["IJ503_1070","AWARD:Contract for Gun Solenoid Corr Assy & Sppt","2005-08-10","2005-08-12"]
["IJ503_2070","AWARD:Contract for Gun Spectr Corr Assy & Sppt","2005-10-25","2005-10-27"]
["IJ503_3010","COMP: Inj Corrector-A Design","2005-05-02","2005-04-29"]
["IJ503_3020","Prep Bid Pak - Inj Corrector-A Assy & Sppt","2005-05-02","2005-11-01"]
["IJ503_3030","RELEASE RFP: Inj Corrector-A Assy & Sppt","2005-11-02","2005-11-02"]
["IJ503_3040","Vendor Prep Proposals - Inj Corrector-A Assy & S","2005-11-03","2005-11-23"]
["IJ503_3050","RCV: Proposals -Inj Corrector-A Assy & Sppt","2005-11-28","2005-11-23"]
["IJ503_3060","Eval Proposals - Inj Corrector-A Assy & Sppt","2005-11-28","2005-12-09"]
["IJ503_3070","AWARD:Contract for Inj Corrector-A Assy & Sppt","2005-12-12","2005-12-14"]
["IJ503_3080","Vendor Fab Inj Corrector-A Assy & Sppt","2005-12-15","2006-04-17"]
["IJ503_3085","Review Vendor Inj Corr-A Design","2006-02-28","2006-02-28"]
["IJ503_3090","RCV: Inj Corrector-A Assy & Sppt","2006-04-18","2006-04-18"]
["IJ503_3100","Perform QC/MM on Inj Corrector-A Assy & Sppt","2006-04-19","2006-05-16"]
["IJ503_3110","AVAIL:  Inj Corrector-A Assy & Sppt RFI","2006-05-17","2006-05-16"]
["IJ503_4070","AWARD:Contract for Inj Corrector-D Assy & Sppt","2005-10-25","2005-10-27"]
["IJ503_5070","AWARD:Contract for GS Quad Cor Assy & Sppt","2005-10-25","2005-10-27"]
["IJ505_4500","Prep Bid Pak - Linac Solenoid Assy & Sppt","2005-05-02","2005-09-30"]
["IJ505_4510","RELEASE RFP: Linac Solenoid Assy & Sppt","2005-10-03","2005-10-14"]
["IJ505_4520","Vendor Prep Proposals -Linac Solenoid Assy&Sppt","2005-10-17","2005-11-04"]
["IJ505_4530","RCV: Proposals -  Linac Solenoid  Assy & Sppt","2005-11-07","2005-11-04"]
["IJ505_4540","Eval Proposals - Linac Solenoid Assy & Sppt","2005-11-07","2005-11-18"]
["IJ505_4550","AWARD:Contract for Linac Solenoid Assy & Sppt","2005-11-21","2005-11-23"]
["IJ505_4560","Vendor Fab Linac Solenoid Assy & Sppt","2005-11-28","2006-03-01"]
["IJ505_4570","RCV: Linac Solenoid Assy & Sppt","2006-03-02","2006-03-02"]
["IJ505_4580","Perform QC/MM on Linac Solenoid Assy & Sppt","2006-03-03","2006-03-16"]
["IJ505_4590","AVAIL:  Linac Solenoid Assy & Sppt RFI","2006-03-17","2006-03-16"]
["IJ601_1040","Develop Inj Vac System Prelim Desgn Review (PDR)","2005-05-02","2005-05-06"]
["IJ601_1050","Vacuum Gauge - Test Engineering","2005-05-02","2005-07-15"]
["IJ601_1070","Prepare Bid Packages for Inj Vacuum System","2005-05-31","2005-07-12"]
["IJ601_1080","Evaluate Vendor Proposals","2005-06-28","2005-07-12"]
["IJ601_1090","Develop Injector Vacuum System Final Design","2005-05-09","2005-08-16"]
["IJ601_1100","Conduct Inj Vac System Final Design Review (FDR)","2005-08-17","2005-08-16"]
["IJ601_1110","Develop Vac Post-Processing Plan for Inj Vac Sys","2005-08-17","2005-08-23"]
["IJ601_1120","Vacuum Post-Processing","2005-08-17","2005-11-09"]
["IJ601_1130","AVAIL:  Injector Vacuum RFI","2005-11-10","2005-11-09"]
["IJ602_1010","Proc - Valve,VAT47132-CE44_ADM1, 24VDC, 34.8mm","2005-05-02","2005-05-27"]
["IJ602_1020","Proc - Valve,VAT47132-CE44_ADL1, 24VDC, 22.1mm","2005-05-02","2005-05-27"]
["IJ602_1030","Proc - ManualValve #54032_GE02","2005-05-02","2005-07-26"]
["IJ602_1040","Proc - Pumps, Varion Ion Pumps #9191115","2005-05-02","2005-07-26"]
["IJ602_1050","Proc - Gauges, MKS422 Cold Cathode Gauge","2005-05-02","2005-06-27"]
["IJ602_1060","Proc - Gauges, MKS317 Enhanced Convection Pirani","2005-05-02","2005-06-27"]
["IJ602_1070","Proc - Granville-Phillips Stabil-Ion Gauge","2005-05-02","2005-06-27"]
["IJ602_1080","Proc - Granville-Phillips Convection Gauge","2005-05-02","2005-05-27"]
["IJ602_1090","Proc - Misc UHV hdwe (flanges, gaskets, etc.)","2005-05-02","2006-09-11"]
["IJ602_1100","AVAIL:  Injector Vacuum Components RFI","2006-02-07","2006-02-06"]
["IJ602_1110","Proc - Pumps for RF Waveguids","2005-12-01","2006-02-06"]
["IJ603_1010","Proc - GTL Pumping and Optics Chamber","2005-10-17","2005-12-13"]
["IJ603_1015","AVAIL:  GTL Pumping and Optics Chamber RFI","2005-12-14","2005-12-14"]
["IJ603_1020","Proc - L0-1TL0-2 Vacuum Components","2005-10-17","2005-12-13"]
["IJ603_1025","AVAIL:  L0-1TL0-2 Vacuum Components RFI","2005-12-14","2005-12-14"]
["IJ603_1030","Proc - DL1 Vacuum Chamber","2005-10-17","2005-12-13"]
["IJ603_1035","AVAIL:  DL1 Vacuum Chamber RFI","2005-12-14","2005-12-14"]
["IJ603_1040","Proc - DL1TL Vacuum Components","2005-10-17","2005-12-13"]
["IJ603_1045","AVAIL:  DL1TL Vacuum Components RFI","2005-12-14","2005-12-14"]
["IJ603_1050","Proc - SAB Vacuum Chamber and Components","2005-10-17","2005-12-13"]
["IJ603_1055","AVAIL:  SAB Vacuum Chamber and Components RFI","2005-12-14","2005-12-14"]
["IJ604_1010","Define GS Vacuum Support Requirements","2005-10-26","2005-10-26"]
["IJ604_1020","Design GS Vacuum Support","2005-10-27","2005-11-23"]
["IJ604_1030","Define Special RF Vauum Valve Supprt Requirement","2005-10-18","2005-10-18"]
["IJ604_1040","Design Special RF Vacuum Valve Supports","2005-10-19","2005-10-25"]
["IJ604_1050","Define GTL Vacuum Supports Requirements","2005-10-10","2005-10-10"]
["IJ604_1060","Design GTL Vacuum Supports","2005-10-11","2005-10-17"]
["IJ604_1070","Define L0-1TL0-2 Vacuum Support Requirements","2005-09-23","2005-09-23"]
["IJ604_1080","Design L0-1TL0-2 Vacuum Supports","2005-09-26","2005-10-07"]
["IJ604_1090","Define LTDL1 Vacuum Support Requirements","2005-08-17","2005-08-17"]
["IJ604_1100","Design LTDL1 Vacuum Supports","2005-08-18","2005-09-22"]
["IJ604_1110","Define DL1 Vacuum Supports Requirements","2005-11-28","2005-11-28"]
["IJ604_1120","Design DL1 Vacuum Supports","2005-11-29","2006-01-04"]
["IJ604_1130","Define DL1TL Vacuum Support Requirements","2006-01-05","2006-01-05"]
["IJ604_1140","Design DL1TL Vacuum Supports","2006-01-06","2006-01-27"]
["IJ604_1150","Define SAB Vacuum Support Requirements","2006-01-30","2006-01-30"]
["IJ604_1160","Design SAB Vacuum Supports","2006-01-31","2006-03-07"]
["IJ605_1010","Proc - GS Support Material","2005-11-28","2006-01-25"]
["IJ605_1015","AVAIL:  GS Support Material","2006-01-26","2006-01-25"]
["IJ605_1020","Proc - Special Beam Pump/Spool Support Material","2005-10-26","2005-12-22"]
["IJ605_1025","AVAIL:  Special Beam/Spool Support Material","2005-12-23","2005-12-22"]
["IJ605_1030","Proc - GTL Supports","2005-10-18","2005-12-14"]
["IJ605_1035","AVAIL:  GTL Supports","2005-12-15","2005-12-14"]
["IJ605_1040","Proc L0-1TL0-2 Minor Tube Support Materials","2005-10-10","2005-12-06"]
["IJ605_1045","AVAIL:  L0-1TL0-2  Minor Tube Support Materials","2005-12-07","2005-12-06"]
["IJ605_1050","Proc - DL1 Support Structure Materials","2006-01-05","2006-03-03"]
["IJ605_1055","AVAIL:  DL1 Support Struture Materials","2006-03-06","2006-03-03"]
["IJ605_1060","Proc - LTDL1 Support Structure Materials","2005-09-23","2005-11-17"]
["IJ605_1065","AVAIL:  LTDL1 Support Structure Materials","2005-11-18","2005-11-17"]
["IJ605_1070","Proc - DL1TL Support Structure Materials","2006-01-30","2006-03-27"]
["IJ605_1075","AVAIL:  DL1TL Support Structure Material","2006-03-28","2006-03-27"]
["IJ605_1080","Proc - SAB Supports","2006-03-08","2006-05-02"]
["IJ605_1085","AVAIL:  SAB Supports","2006-05-03","2006-05-02"]
["IJ605_1090","Proc - Misc Support Hardware (bolts, nuts, etc.)","2005-09-23","2005-11-17"]
["IJ605_1095","AVAIL:  Misc Support Hardware","2005-11-18","2005-11-17"]
["IJ701_1000",null,"2005-05-02","2005-05-02"]
["IJ701_1010","Define LA BPM Physics Requirements","2005-05-02","2005-05-11"]
["IJ701_1020","Define LA Linac BPM Engineering Requirements","2005-05-02","2005-05-11"]
["IJ701_1030","Design LA Linac BPM Core Module","2005-08-01","2005-11-01"]
["IJ701_1040","COMP:  LA Linac BPM Core Module Design","2005-11-02","2005-11-01"]
["IJ701_1050","Prep Bid Pack for LA Linac BPM Core Module","2005-11-02","2005-11-15"]
["IJ701_1060","RELEASE RFP:  LA Linac BPM Core Module","2005-11-16","2005-11-16"]
["IJ701_1070","Vendor Proposals for LA Linac BPM Core Module","2005-11-17","2005-11-23"]
["IJ701_1080","RCV:  Proposals for LA Linac BPM Core Module","2005-11-28","2005-11-28"]
["IJ701_1090","Evaluate Proposals for LA Linac BPM Core Module","2005-11-29","2005-12-15"]
["IJ701_1100","AWARD:  Contract for LA Linac BPM Core Module","2005-12-16","2005-12-16"]
["IJ701_1110","Vendor Fab LA Linac BPM Core Module","2005-12-19","2006-03-01"]
["IJ701_1115","In House Assemble LA BPM Variations","2006-03-02","2006-03-15"]
["IJ701_1120","Vacuum Process LA Linac BPM","2006-03-16","2006-03-29"]
["IJ701_1125","Design LA Linac BPM Variations","2005-08-01","2006-03-01"]
["IJ701_1130","Perform Lab Tests on LA Linac BPM Assembly","2006-03-30","2006-04-10"]
["IJ701_1135","LA BPM Design Check","2005-08-01","2006-03-01"]
["IJ701_1140","AVAIL:  LA Linac BPM Assembly RFI","2006-04-11","2006-04-10"]
["IJ701_1145","Fabricate LA BPM Variations Components","2006-01-10","2006-02-15"]
["IJ701_2000",null,"2005-05-02","2005-05-02"]
["IJ701_2010","Define SA BPM Requirements","2005-05-02","2005-05-13"]
["IJ701_2020","Define SA Linac BPM Requirements","2005-05-02","2005-05-13"]
["IJ701_2030","Design SA Linac BPM","2005-05-16","2005-06-20"]
["IJ701_2040","COMP:  SA Linac BPM Design","2005-06-21","2005-06-20"]
["IJ701_2050","Prep Bid Pack for SA Linac BPM","2005-06-21","2005-07-05"]
["IJ701_2060","RELEASE RFP:  SA Linac BPM","2005-07-06","2005-07-06"]
["IJ701_2070","Vendor Prep Proposals for SA Linac BPM","2005-07-07","2005-07-13"]
["IJ701_2080","RCV:  Proposals for SA Linac BPM","2005-07-14","2005-07-14"]
["IJ701_2090","Evaluate Proposals for SA Linac BPM","2005-07-15","2005-07-28"]
["IJ701_2100","AWARD:  Contract for SA Linac BPM","2005-07-29","2005-07-29"]
["IJ701_2110","Vendor Fab SA Linac BPM","2005-08-01","2005-08-26"]
["IJ701_2112","RCV:  Vendor Fab SA Linac BPMs","2005-12-15","2005-12-15"]
["IJ701_2115","In House Assemble SA Linac BPM","2005-08-29","2005-09-26"]
["IJ701_2120","Vacuum Process SA Linac BPM","2005-09-27","2005-10-03"]
["IJ701_2130","Perform Lab Tests on SA Linac BPM Assembly","2005-10-04","2005-10-17"]
["IJ701_2140","AVAIL:  SA Linac BPM Assembly RFI","2005-10-18","2005-10-17"]
["IJ702_1000",null,"2005-05-02","2005-05-02"]
["IJ702_1010","Define Current Monitor Physics Specifications","2005-05-02","2005-07-29"]
["IJ702_1020","Design Current Monitor","2005-08-01","2005-10-24"]
["IJ702_1030","COMP:  Current Monitor Design","2005-10-25","2005-10-24"]
["IJ702_1040","Prep Bid Pack for Current Monitor","2005-10-25","2005-11-07"]
["IJ702_1050","RELEASE RFP:  Current Monitor","2005-11-08","2005-11-08"]
["IJ702_1060","Vendor Prep Proposals for Current Monitor","2005-11-09","2005-11-15"]
["IJ702_1070","RCV:  Proposals for Current Monitor","2005-11-16","2005-11-16"]
["IJ702_1080","Evaluate Proposals for Current Monitor","2005-11-17","2005-12-02"]
["IJ702_1090","AWARD:  Contract for Current Monitor","2005-12-05","2005-12-05"]
["IJ702_1100","Vendor Fab Current Monitor","2005-12-06","2006-03-03"]
["IJ702_1110","RCV:  Fab Current Monitor","2006-03-06","2006-03-06"]
["IJ702_1120","Vacuum Process Current Monitor","2006-03-07","2006-03-20"]
["IJ702_1130","Perform Lab Tests on Current Monitor","2006-03-21","2006-04-10"]
["IJ702_1140","AVAIL:  Current Monitor RFI","2006-04-11","2006-04-10"]
["IJ704_1000",null,"2005-05-02","2005-05-02"]
["IJ704_1010","Define Profile Monitor Physics Requirements","2005-05-02","2005-06-13"]
["IJ704_1020","Define Profile Monitor Engineering Requirements","2005-05-02","2005-06-13"]
["IJ704_1030","Profile Monitors Engineering","2005-09-01","2006-01-30"]
["IJ704_1040","COMP:  Profile Monitors Design","2005-05-02","2005-04-29"]
["IJ704_1050","Prep Bid Pack for Profile Monitor","2005-06-14","2005-06-15"]
["IJ704_1060","RELEASE RFP:  Profile Monitor","2005-06-14","2005-06-14"]
["IJ704_1070","Vendor Prep Proposals for Profile Monitor","2005-06-16","2005-06-22"]
["IJ704_1080","RCV:  Proposals for Profile Monitor","2005-06-22","2005-06-22"]
["IJ704_1090","Evaluate Proposals for Profile Monitor","2005-06-23","2005-06-27"]
["IJ704_1100","AWARD:  Contract for Profile Monitor","2005-06-27","2005-06-27"]
["IJ704_1110","Vendor Fab Profile Monitors","2005-06-27","2006-08-01"]
["IJ704_1112","RCV:  Vendor Fab Profile Monitors","2006-08-02","2006-08-02"]
["IJ704_1115","Profile Monitors In House Assembly","2005-11-15","2006-08-15"]
["IJ704_1120","Perform Lab Test On Profile Monitors","2005-10-28","2006-08-21"]
["IJ704_1130","AVAIL:  Profile Monitor RFI - Remaining Lot","2006-08-22","2006-08-21"]
["IJ704_1140","Design OTR Profile Monitor Core Module","2005-05-02","2005-12-23"]
["IJ704_1145","Design YAG/FaradayCup/LsrAlgnmt Prof Monitor","2005-06-01","2005-12-20"]
["IJ704_1150","Dsn Gun Spectrm YAG/Cerenkov/Faraday Cup ProfMon","2005-06-01","2006-01-20"]
["IJ704_1155","Design YAG Profile Monitors Optics","2005-06-01","2006-03-15"]
["IJ704_1160","Design Gun Laser On-Axis Mirror Assy","2005-06-01","2006-01-20"]
["IJ704_1165","Design Cerenkov Profile Monitor","2005-06-01","2006-08-01"]
["IJ704_1170","Design Laser Heater OTR Profile Monitor","2005-11-15","2006-02-15"]
["IJ704_1175","Design OTR Profile Monitor Optics","2005-10-03","2006-03-15"]
["IJ704_1180","COMP:  Profile Monitors Design","2006-08-02","2006-08-01"]
["IJ704_1185","Profile Monitors Design Check","2005-06-01","2006-08-01"]
["IJ704_1200","COMP:  Profile Monitor Design (OTR 1-3)","2005-06-02","2005-06-01"]
["IJ704_1210","Prep Bid Pack for Profile Monitor  (OTR 1-3)","2005-06-02","2005-06-15"]
["IJ704_1220","RELEASE RFP:  Profile Monitor  (OTR 1-3)","2005-06-16","2005-06-16"]
["IJ704_1230","Vendor Prep Proposals for Profile Monitor  (OTR","2005-06-17","2005-06-23"]
["IJ704_1240","RCV:  Proposals for Profile Monitor  (OTR 1-3)","2005-06-24","2005-06-23"]
["IJ704_1250","Evaluate Proposals for Profile Monitor  (OTR 1-3","2005-06-24","2005-06-27"]
["IJ704_1260","AWARD:  Contract for Profile Monitor  (OTR 1-3)","2005-06-28","2005-06-28"]
["IJ704_1270","Vendor Fab Profile Monitor (OTR 1-3)","2005-06-29","2005-12-15"]
["IJ704_1275","RCV:  Vendor Fab Profile Monitor (OTR 1-3)","2005-12-16","2005-12-16"]
["IJ704_1280","In House Assembly  (OTR 1-3)","2005-12-19","2006-02-01"]
["IJ704_1290","Perform Lab Test On Profile Monitors  (OTR 1-3)","2006-02-02","2006-02-21"]
["IJ704_1300","AVAIL:  Profile Monitors (OTR 1-3) RFI","2006-02-22","2006-02-21"]
["IJ705_1000",null,"2005-05-02","2005-05-02"]
["IJ705_1005","AVAIL:  Injector Wire Scanners RFI","2006-03-16","2006-03-16"]
["IJ705_1010","Procure Injector Wire Scanners","2005-10-03","2006-03-15"]
["IJ707_1000",null,"2005-05-02","2005-05-02"]
["IJ707_1010","Define PPS Stopper Physics Specifications","2005-05-02","2005-06-15"]
["IJ707_1020","Define PPS Stopper Engineering Specs","2005-05-02","2005-06-27"]
["IJ707_1030","Design PPS Stopper","2005-05-02","2005-06-27"]
["IJ707_1040","COMP:  PPS Stopper Design","2005-06-28","2005-06-27"]
["IJ707_1050","Prep Bid Pack for PPS Stopper","2005-06-28","2005-07-12"]
["IJ707_1060","RELEASE RFP:  PPS Stopper","2005-07-13","2005-07-13"]
["IJ707_1070","Vendor Prep Proposals for PPS Stopper","2005-07-14","2005-07-20"]
["IJ707_1080","RCV:  Proposals for PPS Stopper","2005-07-21","2005-07-21"]
["IJ707_1090","Evaluate Proposals for PPS Stopper","2005-07-22","2005-08-04"]
["IJ707_1100","AWARD:  Contract for PPS Stopper","2005-08-05","2005-08-05"]
["IJ707_1110","Vendor Fab PPS Stopper","2005-08-08","2005-09-02"]
["IJ707_1120","In House Fab PPS Stopper","2005-08-08","2005-09-02"]
["IJ707_1130","Assemble PPS Stopper","2005-09-06","2005-09-19"]
["IJ707_1140","Vacuum Process PPS Stopper","2005-09-20","2005-10-10"]
["IJ707_1150","AVAIL:  PPS Stopper RFI","2005-10-11","2005-10-10"]
["IJMS_03","FY 05 Funding Constraint Q2 May","2005-05-02","2005-04-29"]
["IJOPS_0000","Injector System Pre-Operations","2007-07-23","2009-03-31"]
["IJ_LOE","Injector LOE Complete","2009-03-31","2009-03-30"]
["IJ_OPCSPR","Injector OPC Spares Complete","2007-08-31","2007-08-30"]
["LN01010100","L01 SYSTEM SUMMARY","2005-05-02","2009-03-30"]
["LN01010108","Write System ICD - L01","2005-05-02","2005-05-16"]
["LN01010118","Write Installation Plan - L01","2005-05-02","2005-05-16"]
["LN01010124","Prepare for PDR - L01","2005-05-02","2005-06-30"]
["LN01010126","Conduct L01 System PDR","2005-07-01","2005-07-15"]
["LN01010128","Generate Detailed Procurement Plan","2005-07-15","2005-07-15"]
["LN01010130","Create RF Cold Test Plan","2005-07-18","2005-07-20"]
["LN01010132","Establish Subordinate Work Orders","2005-07-21","2005-07-21"]
["LN01010134","Prepare for FDR - L01","2005-07-28","2005-08-01"]
["LN01010136","Conduct L01 System FDR","2005-08-02","2005-08-03"]
["LN01010138","COMP: L01 System Design","2005-08-04","2005-08-03"]
["LN01010139","Document System Assembly Model - L01","2005-11-17","2005-12-16"]
["LN01010140","L01 System PED Support to Components","2005-05-02","2005-09-30"]
["LN01010142","L01 System CONST Support to Components","2005-10-03","2009-03-30"]
["LN01010200","BC1 SYSTEM SUMMARY","2005-05-02","2009-03-30"]
["LN01010208","Write System ICD - BC1","2005-05-17","2005-05-18"]
["LN01010218","Write Installation Plan - BC1","2005-05-02","2005-06-15"]
["LN01010228","Generate Detailed Procurement Plan","2005-05-02","2005-06-15"]
["LN01010232","Establish Subordinate Work Orders","2005-05-02","2005-05-02"]
["LN01010234","Prepare for FDR - BC1","2005-07-28","2005-08-01"]
["LN01010236","Conduct BC1 System FDR","2005-08-02","2005-08-03"]
["LN01010238","COMP: BC1 System Design","2005-08-04","2005-08-03"]
["LN01010239","Document System Assembly Model - BC1","2006-01-03","2006-01-31"]
["LN01010240","BC1 System PED Support to Components","2005-05-02","2005-09-30"]
["LN01010242","BC1 System CONST Support to Components","2005-10-03","2009-03-30"]
["LN01010300","L02 SYSTEM SUMMARY","2005-05-19","2009-03-31"]
["LN01010308","Write System ICD - L02","2005-05-19","2005-05-25"]
["LN01010318","Write Installation Plan - L02","2005-09-01","2005-09-06"]
["LN01010322","Make Linac Vacuum Schematic","2005-09-07","2005-09-13"]
["LN01010324","Prepare for PDR - L02","2005-09-07","2005-09-09"]
["LN01010326","Conduct L02 System PDR","2005-09-12","2005-09-12"]
["LN01010328","Generate Detailed Procurement Plan","2005-09-13","2005-09-13"]
["LN01010330","Create Cold Test Plan","2005-09-14","2005-09-16"]
["LN01010332","Establish Subordinate Work Orders","2005-09-19","2005-09-19"]
["LN01010334","Prepare for FDR - L02","2005-09-20","2005-09-22"]
["LN01010336","Conduct L02 System FDR","2005-09-23","2005-09-23"]
["LN01010338","COMP: L02 System Design","2005-09-26","2005-09-23"]
["LN01010339","Document System Assembly Model - L02","2006-02-01","2006-03-01"]
["LN01010340","L02 System PED Support to Components","2005-09-01","2006-02-06"]
["LN01010342","L02 System CONST Support to Components","2006-02-07","2009-03-31"]
["LN01010400","BC2 SYSTEM SUMMARY","2005-05-26","2009-03-31"]
["LN01010408","Write System ICD - BC2","2005-05-26","2005-06-02"]
["LN01010418","Write Installation Plan - BC2","2005-07-01","2005-07-08"]
["LN01010422","Make Linac Vacuum Schematic","2005-07-11","2005-07-14"]
["LN01010424","Prepare for PDR - BC2","2005-07-11","2005-07-13"]
["LN01010426","Conduct BC2 System PDR","2005-07-14","2005-07-14"]
["LN01010428","Generate Detailed Procurement Plan","2005-07-15","2005-07-15"]
["LN01010430","Create Cold Test Plan","2005-07-18","2005-07-20"]
["LN01010432","Establish Subordinate Work Orders","2005-07-21","2005-07-21"]
["LN01010434","Prepare for FDR - BC2","2005-07-28","2005-08-01"]
["LN01010436","Conduct BC2 System FDR","2005-08-02","2005-08-02"]
["LN01010438","COMP: BC2 System Design","2005-08-03","2005-08-02"]
["LN01010439","Document System Assembly Model - BC2","2006-03-29","2006-04-25"]
["LN01010440","BC2 System PED Support to Components","2005-07-01","2006-01-26"]
["LN01010442","BC2 System CONST Support to Components","2006-01-27","2009-03-31"]
["LN01010500","L03 SYSTEM SUMMARY","2005-06-03","2009-03-31"]
["LN01010508","Write System ICD - L03","2005-06-03","2005-06-09"]
["LN01010517","AVAIL: System Reqmts for L03 Component Designs","2005-06-10","2005-06-09"]
["LN01010518","Write Installation Plan - L03","2005-06-10","2005-06-14"]
["LN01010522","Make Linac Vacuum Schematic","2005-06-15","2005-06-21"]
["LN01010524","Prepare for PDR - L03","2005-06-22","2005-06-24"]
["LN01010526","Conduct L03 System PDR","2005-06-27","2005-06-27"]
["LN01010528","Generate Detailed Procurement Plan","2005-06-28","2005-06-28"]
["LN01010530","Create Cold Test Plan","2005-06-29","2005-06-30"]
["LN01010532","Establish Subordinate Work Orders","2005-08-05","2005-08-05"]
["LN01010534","Prepare for FDR - L03","2005-08-08","2005-08-10"]
["LN01010536","Conduct L03 System FDR","2005-08-11","2005-08-11"]
["LN01010538","COMP: L03 System Design","2005-08-12","2005-08-11"]
["LN01010539","Document System Assembly Model - L03","2006-04-26","2006-05-23"]
["LN01010540","L03 System PED Support to Components","2005-06-10","2006-03-17"]
["LN01010542","L03 System CONST Support to Components","2006-03-20","2009-03-31"]
["LN01010600","LTU SYSTEM SUMMARY","2005-05-02","2009-03-30"]
["LN01010608","Write System ICD - L03","2005-06-10","2005-06-16"]
["LN01010612","Generate Removal Document List - FFTB to LT","2005-05-02","2005-05-31"]
["LN01010617","AVAIL: System Reqmts for LTU Component Designs","2005-07-01","2005-06-30"]
["LN01010618","Write Installation Plan - LTU","2005-07-01","2005-07-06"]
["LN01010624","Prepare for PDR - LTU","2005-05-02","2005-05-04"]
["LN01010626","Conduct LTU System PDR","2005-08-01","2005-08-01"]
["LN01010628","Generate Detailed Procurement Plan","2005-08-02","2005-08-02"]
["LN01010630","Create Test Plan","2005-08-03","2005-08-04"]
["LN01010632","Establish Subordinate Work Orders","2005-08-05","2005-08-05"]
["LN01010634","Prepare for FDR - LTU","2005-08-08","2005-08-10"]
["LN01010636","Conduct LTU System FDR","2005-08-11","2005-08-11"]
["LN01010638","COMP: LTU System Design","2005-08-12","2005-08-11"]
["LN01010640","LTU System PED Support to Components","2005-07-01","2005-09-30"]
["LN01010642","LTU System CONST Support to Components","2005-10-03","2009-03-30"]
["LN01010700","E-DUMP SYSTEM SUMMARY","2005-05-02","2009-03-30"]
["LN01010708","Write System ICD - E-Dump","2005-07-01","2005-07-08"]
["LN01010717","AVAIL: System Reqmts for E Dmp Component Designs","2005-07-11","2005-07-08"]
["LN01010718","Write Installation Plan - E-Dump","2005-07-11","2005-07-13"]
["LN01010724","Prepare for PDR - E-Dump","2005-05-02","2005-05-04"]
["LN01010726","Conduct E-Dump System PDR","2005-07-25","2005-07-25"]
["LN01010728","Generate Detailed Procurement Plan","2005-07-26","2005-07-26"]
["LN01010730","Create Test Plan","2005-07-27","2005-07-28"]
["LN01010732","Establish Subordinate Work Orders","2005-07-29","2005-07-29"]
["LN01010734","Prepare for FDR - E-Dump","2005-08-01","2005-08-03"]
["LN01010736","Conduct E-Dump System FDR","2005-08-04","2005-08-04"]
["LN01010738","COMP: E-Dump System Design","2005-08-05","2005-08-04"]
["LN01010740","E-Dump System PED Support to Components","2005-07-11","2005-09-30"]
["LN01010742","E-Dump System CONST Support to Components","2005-10-03","2009-03-30"]
["LN0101_616","Define/Develop LTU System Assembly Model - FY05","2005-05-02","2005-06-30"]
["LN0101_716","Define/Develop E-Dump System Assy Model - FY05","2005-05-02","2005-05-02"]
["LN0103A01","Travel - PED","2005-05-02","2005-05-31"]
["LN0103A02","Travel - PED","2005-06-01","2005-07-28"]
["LN0103A03","Travel - PED","2005-07-29","2005-09-26"]
["LN0103A04","Travel - PED","2005-05-02","2005-06-28"]
["LN0103A05","Travel - PED","2005-06-29","2005-08-25"]
["LN0103A06","Travel - PED","2005-08-26","2005-10-24"]
["LN0103A07","Travel - CONST","2005-10-25","2006-01-06"]
["LN0103A08","Travel - CONST","2006-01-09","2006-03-08"]
["LN0103A09","Travel - CONST","2006-03-09","2006-05-04"]
["LN0103B01","Travel - CONST","2006-05-05","2006-07-03"]
["LN0103B02","Travel - CONST","2006-07-05","2006-08-30"]
["LN0103B03","Travel - CONST","2006-08-31","2006-10-27"]
["LN0103B04","Travel - CONST","2006-10-30","2007-01-11"]
["LN0103B05","Travel - CONST","2007-01-12","2007-03-13"]
["LN0103B06","Travel - CONST","2007-03-14","2007-05-09"]
["LN0103B07","Travel - CONST","2006-10-03","2006-11-30"]
["LN0103B08","Travel - CONST","2006-12-01","2007-02-13"]
["LN0103B09","Travel - CONST","2007-02-14","2007-04-12"]
["LN0103B10","Travel - CONST","2007-04-13","2007-06-11"]
["LN0103B11","Travel - CONST","2007-06-12","2007-08-08"]
["LN0103B12","Travel - CONST","2007-08-09","2007-10-05"]
["LN0103B13","Travel - CONST","2007-10-08","2007-12-05"]
["LN0103B14","Travel - CONST","2007-12-06","2008-02-20"]
["LN0103B15","Travel - CONST","2008-02-21","2008-04-17"]
["LN0103B16","Travel - CONST","2008-04-18","2008-06-16"]
["LN0103B17","Travel - CONST","2008-06-17","2008-08-13"]
["LN0103B18","Travel - CONST","2008-08-14","2008-10-10"]
["LN010400","Linac System Management Effort - PED","2005-05-02","2005-09-30"]
["LN01040035","LINAC COMPONENT DATA BASE SUMMARY","2005-05-02","2005-09-23"]
["LN01040070","LINAC ADMINISTRATIVE SUMMARY","2005-05-02","2007-05-01"]
["LN01040085","Linac Procurement Management","2005-05-02","2006-09-29"]
["LN01040090","Linac Testing & Post-Process Management","2005-05-02","2006-09-29"]
["LN01040095","Linac Stage & Storage Management","2005-05-02","2006-09-29"]
["LN01040100","Linac Physics Requirements","2005-07-13","2005-10-26"]
["LN01040105","Receive and Review Linac Optics Requirements","2005-07-13","2005-07-13"]
["LN01040110","Verify Diagnostic Requirements","2005-07-14","2005-07-20"]
["LN01040115","Back Check Component Spec vs Optics Requirements","2005-07-21","2005-07-27"]
["LN010402","Linac System Management Effort - CONST","2005-10-03","2009-03-30"]
["LN02","LINAC CNTRLS & PWR CONV SUBSYSTEM SUMMARY","2005-05-02","2008-01-03"]
["LN0201","PERSONNEL PROTECTION SUBSYSTEM SUMARY","2005-10-03","2007-11-21"]
["LN02010040","Construction Funds Available - Begin Procurement","2005-10-03","2005-09-30"]
["LN02010041","Start PPS BSOIC Mounting H/W Procurement","2006-02-22","2006-02-21"]
["LN02010045","Procure PPS BSOIC Mounting Hardware/Material","2006-02-22","2006-03-07"]
["LN02010050","RCV: PPS BSOIC Mounting Hardware/Material","2006-03-08","2006-03-07"]
["LN02010055","Prep Bid Pak - BSOIC Rad Monitor ADM-600 Series","2006-02-22","2006-03-07"]
["LN02010060","RELEASE: RFP - BSOIC Rad Monitor ADM-600 Series","2006-03-08","2006-03-07"]
["LN02010065","Vendors Prep Proposals - BSOIC Rad Monitor ADM-6","2006-03-08","2006-03-28"]
["LN02010070","RCV: Proposals - BSOIC Rad Monitor ADM-600 Serie","2006-03-29","2006-03-28"]
["LN02010075","Evaluate Proposals - BSOIC Rad Monitor ADM-600 S","2006-03-29","2006-04-11"]
["LN02010080","AWARD: Contract - BSOIC Rad Monitor ADM-600 Seri","2006-04-12","2006-04-12"]
["LN02010085","Vendor Fab/Assy - BSOIC Rad Monitor ADM-600 Seri","2006-10-02","2007-07-02"]
["LN02010090","Fab/Assy - BSOIC Mounting Hardware (15)","2006-10-02","2007-09-26"]
["LN02010095","RCV: PPS BSOIC Rad Monitor ADM-600 Series (20) f","2007-07-03","2007-07-02"]
["LN02010100","Fab and Pre Assemble Components (as required)","2007-09-27","2007-10-24"]
["LN02010105","COMP: Linac PPS Component Fab & Assembly","2007-10-25","2007-10-24"]
["LN02010110","Perform PPS BSOIC Pre-Installation Qual Test","2007-10-25","2007-11-21"]
["LN02010115","AVAIL: Linac PPS BSOIC Equipment Ready for Instl","2007-11-26","2007-11-21"]
["LN02010230","Start PPS Maze/Gate H/W Procurement","2006-04-10","2006-04-07"]
["LN02010240","RCV: PPS Hardware/Material","2006-02-22","2006-02-21"]
["LN02010241","Start PLC Access Cntrl Sys Elect Procurement","2006-02-22","2006-02-21"]
["LN02010245","Prep Bid Pak - PLC Access Cntrl Sys Electronics","2006-02-22","2006-02-28"]
["LN02010250","RELEASE: RFP - PLC Access Cntrl Sys Electronics","2006-03-01","2006-02-28"]
["LN02010255","Vendors Prep Proposals - PLC Access Cntrl Sys El","2006-03-01","2006-03-28"]
["LN02010260","RCV: Proposals - PLC Access Cntrl Sys Electronic","2006-03-29","2006-03-28"]
["LN02010265","Evaluate Proposals - PLC Access Cntrl Sys Electr","2006-03-29","2006-04-04"]
["LN02010270","AWARD: Contract - PLC Access Cntrl Sys Electroni","2006-04-05","2006-04-05"]
["LN02010272","Vendor Fab/Assy - PLC Access Cntrl Sys Electroni","2006-04-06","2006-11-20"]
["LN02010274","RCV: from Vendor - PPS PLC Access Cntrl Sys Elec","2006-11-21","2006-11-20"]
["LN02010281","Fab, Pre Assemble and Qual Test PPS Component","2006-11-21","2007-02-02"]
["LN02010282","AVAIL: Linac PPS Equipment Ready for Integ","2007-02-05","2007-02-02"]
["LN02010335","Procure PPS Maze/Gate Hdwr/Matl/Switch/Latch/Sol","2006-04-10","2006-05-05"]
["LN02010340","Fab/PreAssy PPS Maze/Gate Hdwr/Matl/Switch/Latch","2006-05-08","2006-08-01"]
["LN02010345","Procure Cable PPS Maze/Gate Cableplant","2006-10-03","2007-01-11"]
["LN02010350","RCV: PPS Maze/Gate Hdwr/Matl/Switches/Latches/So","2007-01-12","2007-01-11"]
["LN02010355","Prep Bid Pak - Mazes/Gates Access Control Gates","2006-02-22","2006-03-14"]
["LN02010360","RELEASE: RFP - Mazes/Gates Access Control Gates","2006-03-15","2006-03-14"]
["LN02010365","Vendors Prep Proposals - Mazes/Gates Access Cntr","2006-03-15","2006-04-11"]
["LN02010370","RCV: Proposals - Mazes/Gates Access Control Gate","2006-04-12","2006-04-11"]
["LN02010375","Evaluate Proposals - Mazes/Gates Access Control","2006-04-12","2006-04-25"]
["LN02010380","AWARD: Mazes/Gates Access Control Gates (3 sets","2006-04-26","2006-04-26"]
["LN02010382","Vendor Fab/Assy - Mazes/Gates Access Cntrl Gates","2006-04-27","2006-11-13"]
["LN02010384","RCV: PPS Mazes/Gates Access Control Set 3 from V","2006-11-14","2006-11-13"]
["LN02010386","AVAIL: PPS Mazes/Gates Access Control Gates","2007-01-12","2007-01-11"]
["LN02010388","Write Software & Documentation to Integrate PPS","2006-02-22","2006-04-18"]
["LN02010394","Integrate and Test PPS","2007-01-12","2007-01-26"]
["LN02010398","AVAIL: PPS Controls ready to Integrate","2007-01-29","2007-01-26"]
["LN0202","BEAM CONTAINMENT SUBSYSTEM SUMMARY","2005-10-03","2006-11-30"]
["LN02020025","Construction Funds Available - Begin Procurement","2005-10-03","2005-09-30"]
["LN02020029","Start BCS LTU & Halls Procurement","2005-10-03","2005-09-30"]
["LN02020030","Procure BCS PLIC/LION System HV Power Supply Cha","2006-10-03","2006-10-23"]
["LN02020035","Procure Gas System - BCS PLIC/LION Regulators/Fi","2006-10-03","2006-10-23"]
["LN02020040","Procure BCS  PLIC/LION Gas Bottle(s) & Bottle(s","2006-10-03","2006-10-31"]
["LN02020045","Procure BCS  PLIC/LION Cableplant Heliax, Andre","2006-10-03","2006-10-31"]
["LN02020050","RCV: from Vendor - BCS PLIC/LION  HV Supply","2006-11-01","2006-10-31"]
["LN02020055","RCV: from Vendor - BCS PLIC/LION Cableplant","2006-11-01","2006-10-31"]
["LN02020060","Prep Bid Pak - BCS PLIC/LION Cableplant","2006-10-03","2006-10-09"]
["LN02020065","RELEASE: RFP - BCS PLIC/LION Cableplant","2006-10-10","2006-10-09"]
["LN02020070","Vendors Prep Proposals - BCS PLIC/LION Cableplan","2006-10-10","2006-10-16"]
["LN02020075","RCV: Proposals - BCS PLIC/LION Cableplant","2006-10-17","2006-10-16"]
["LN02020080","Evaluate Proposals - BCS PLIC/LION Cableplant","2006-10-17","2006-10-23"]
["LN02020085","AWARD: Contract - BCS PLIC/LION Cableplant","2006-10-24","2006-10-24"]
["LN02020090","AVAIL: HV Power Supply ready to integrate","2006-10-25","2006-10-24"]
["LN02020095","COMP: BCS  LTU & Halls Component Fab & Assembly","2006-11-01","2006-10-31"]
["LN02020100","Perform Pre-Installation Qual Test on BCS LTU","2006-11-01","2006-11-30"]
["LN02020105","AVAIL: Linac BCS Cableplant ready for Instl","2006-12-01","2006-11-30"]
["LN02020110","Write Software Documentation","2006-03-01","2006-04-11"]
["LN02020125","Integrate and Test BCS","2006-04-12","2006-04-25"]
["LN02020135","AVAIL: Linac BCS Controls Ready to Integrate","2006-04-26","2006-04-25"]
["LN0203","MACHINE PROTECTION SUBSYSTEM SUMMARY","2005-10-03","2007-02-27"]
["LN02030040","Construction Funds Available - Begin Procurement","2005-10-03","2005-09-30"]
["LN02030049","Start MPS Procurement & Fabrication","2006-04-27","2006-04-26"]
["LN02030050","Acqquire MPS Hardware","2006-04-27","2006-04-27"]
["LN02030051","Prep Bid Pak - PIC Modules","2006-04-27","2006-05-17"]
["LN02030055","Prep Assy Pak - TC Reference Planes Modules","2006-05-18","2006-06-08"]
["LN02030060","RELEASE: RFP - PIC's","2006-06-09","2006-06-08"]
["LN02030065","Vendors Prep Proposals - PIC's","2006-06-09","2006-07-07"]
["LN02030070","RCV: Proposals - PIC Modules","2006-07-10","2006-07-07"]
["LN02030075","Evaluate Proposals - PIC Modules","2006-07-10","2006-07-21"]
["LN02030080","AWARD: Contract - PIC Modules","2006-07-24","2006-07-24"]
["LN02030085","Vendor Fab/Assy - PIC Modules","2006-07-25","2007-01-29"]
["LN02030090","RCV: from Vendor - MPS PIC Modules","2007-01-30","2007-01-29"]
["LN02030095","Procure TC Reference Plane material (as required","2005-10-03","2005-10-28"]
["LN02030100","Fab and Pre Assemble TC Ref. Planes (as required","2005-10-31","2005-11-29"]
["LN02030105","Procure Cable TC Reference Plane material","2005-10-03","2005-10-28"]
["LN02030110","Fab Cable, Coax, PIC Module to PIC Detector (6)","2005-10-31","2005-11-29"]
["LN02030115","Fab Cable, Coax, HV P.S. to PIC Detector (6)","2005-10-31","2005-11-29"]
["LN02030120","Fab Cable,1553, PIC Module Chain to VME A.P. Cra","2005-10-31","2005-11-29"]
["LN02030125","Fab Cable,8/C, HV P.S. to X-connects (P.S. Statu","2005-10-31","2005-11-29"]
["LN02030130","Fab Cable,4/C, HV P.S. to X-connects (HV Enable)","2005-10-31","2005-11-29"]
["LN02030135","Fab and Pre Assemble PIC Components (as reqd)","2005-11-30","2006-01-11"]
["LN02030140","COMP: Linac MPS Component Fab & Assembly","2006-01-12","2006-01-11"]
["LN02030145","Perform Pre-Installation Qual Test on Linac MPS","2007-01-30","2007-02-27"]
["LN02030150","AVAIL: Linac MPS Equipment ready for Install","2007-02-28","2007-02-27"]
["LN02030225","Prep Bid Pak - BSOIC","2005-10-03","2005-10-21"]
["LN02030230","RELEASE: RFP - BSOIC","2005-10-24","2005-10-21"]
["LN02030235","Vendors Prep Proposals - BSOIC","2005-10-24","2005-11-18"]
["LN02030240","RCV: Proposals - BSOIC","2005-11-21","2005-11-18"]
["LN02030245","Evaluate Proposals - BSOIC","2005-11-21","2005-12-06"]
["LN02030250","AWARD: Contract - BSOIC","2005-12-07","2005-12-07"]
["LN02030255","Vendor Fab/Assy - BSOIC","2005-12-08","2006-05-15"]
["LN02030260","RCV: from Vendor - MPS BSOIC","2006-05-16","2006-05-15"]
["LN02030280","Fab and Pre Assemble Components (as required)","2006-05-16","2006-05-15"]
["LN02030285","COMP: Linac MPS Component Fab & Assembly","2006-05-16","2006-05-15"]
["LN02030290","Perform Pre-Installation Qual Test on Linac MPS","2006-05-16","2006-05-15"]
["LN02030295","AVAIL: Linac MPS Equipment ready for Install","2006-05-16","2006-05-15"]
["LN02030300","Write Software and Doc. to Integrate MPS","2006-05-16","2006-07-12"]
["LN02030315","Integrate and Test MPS Hardware and Software","2006-07-13","2006-08-09"]
["LN02030320","AVAIL: Linac MPS Controls Ready to Integrate","2006-08-10","2006-08-09"]
["LN020401","BX11-14 SUMMARY","2007-07-26","2008-01-03"]
["LN02040104","Procure 20kw Pwr Supply (BX11-14) - Hardware","2007-07-26","2008-01-02"]
["LN02040133","AVAIL: 20kw Pwr Supply (BX11-14) - Ready for Ins","2008-01-03","2008-01-03"]
["LN020402","2kw POWER SUPPLY (SEC-23) SUMMARY","2006-10-03","2007-03-12"]
["LN02040204","Procure 2kw Pwr Supply  - (Sec 23)","2006-10-03","2007-03-12"]
["LN02040233","AVAIL: 2kw Pwr Supply (SEC-23) Ready for Integ","2007-03-13","2007-03-12"]
["LN020403","2kw POWER SUPPLY (SEC-24) SUMMARY","2006-10-03","2007-03-12"]
["LN02040304","Procure 2kw Pwr Supply - (Sec 24)","2006-10-03","2007-03-12"]
["LN02040333","AVAIL: 2kw Pwr Supply (SEC-24) Ready for Integ","2007-03-13","2007-03-12"]
["LN020404","Q21201-Q21901 Split SUMMARY","2006-10-03","2006-11-21"]
["LN02040404","Procure Q21201-Q21901 Hardware","2006-10-03","2006-11-13"]
["LN02040409","RCV: Quad Q21201-Q21901 Hardware","2006-11-14","2006-11-14"]
["LN02040414","Integrate Cables for quad Q21201-Q21901 Hardware","2006-11-15","2006-11-21"]
["LN02040433","AVAIL: Q21201-Q21901 Split Ready for Integ","2006-11-22","2006-11-21"]
["LN020405","Q24201-Q24501 Split SUMMARY","2006-10-03","2007-03-20"]
["LN02040505","Procure Q24201-Q24501Hardware","2006-10-03","2007-03-12"]
["LN02040510","RCV: Quad Q24201-Q24501 Hardware","2007-03-13","2007-03-13"]
["LN02040515","Integrate Cables for quad Q24201-Q24501 Hardware","2007-03-14","2007-03-20"]
["LN02040520","AVAIL: Q24201-Q24501 Split Ready for Integ","2007-03-21","2007-03-20"]
["LN020406","25kw Pwr Supply (BX21-24) POWER SUPPLY SUMMARY","2006-10-03","2007-07-26"]
["LN02040604","Procure 25kw Pwr Supply (BX21-24) - Hardware","2006-10-03","2007-03-12"]
["LN0204061","10kw POWER SUPPLY (Q24601) SUMMARY","2006-10-03","2007-03-20"]
["LN02040615","Procure 10kw Pwr Supply - (Q24601)","2006-10-03","2007-03-12"]
["LN02040616","RCV: Q24601 Hardware","2007-03-13","2007-03-13"]
["LN02040617","Integrate Cables for Q24601","2007-03-14","2007-03-20"]
["LN02040619","AVAIL: 10kw Pwr Supply (Q24601) Ready for Integ","2007-03-21","2007-03-20"]
["LN02040646","AVAIL: 25kw Pwr Supply (BX21-24) Ready for Instl","2007-07-26","2007-07-26"]
["LN020407","10KW PS - (Q24701A,Q24701B) SUMMARY","2006-10-03","2007-03-20"]
["LN02040705","Procure 10KW PS - (Q24701A,Q24701B) Hardware","2006-10-03","2007-03-12"]
["LN02040710","RCV: Q24701A,Q24701B Split Hardware","2007-03-13","2007-03-13"]
["LN02040715","Integrate Cables for Q24701A,Q2470 split H/W","2007-03-14","2007-03-20"]
["LN02040720","AVAIL: Q24201-Q24501 Split Ready for Integ","2007-03-21","2007-03-20"]
["LN020408","10kw POWER SUPPLY (QM21) SUMMARY","2006-10-03","2007-03-27"]
["LN02040804","Procure 10kw Pwr Supply (QM21)","2006-10-03","2007-03-26"]
["LN02040833","AVAIL: QM21 10kw P/S Ready for Integ","2007-03-27","2007-03-27"]
["LN020409","Q24901A,Q24901B SUMMARY","2006-10-03","2007-03-13"]
["LN02040904","Procure Q24901A,Q24901B Hardware","2006-10-03","2007-03-12"]
["LN02040933","AVAIL: Q24901A,Q24901B 10kw P/S Ready for  Integ","2007-03-13","2007-03-13"]
["LN020410","2kw POWER SUPPLY (SEC-25) SUMMARY","2006-10-03","2007-03-12"]
["LN0204100","QM22 10kw Pwr Supply SUMMARY","2006-10-03","2007-03-13"]
["LN02041004","Procure 2kw Pwr Supply - (SEC 25)","2006-10-03","2007-03-12"]
["LN02041005","Procure QM22 10kw Pwr Supply","2006-10-03","2007-03-12"]
["LN02041010","AVAIL: QM22 10kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN02041033","AVAIL: 2kw Pwr Supply (SEC-25) Ready for Integ","2007-03-13","2007-03-12"]
["LN020411","2kw POWER SUPPLY (SEC-26) SUMMARY","2006-10-03","2007-03-12"]
["LN02041100","Q5 10kw P/S SUMMARY","2006-10-03","2007-03-13"]
["LN02041104","Procure2kw Pwr Supply - (Sec 26)","2006-10-03","2007-03-12"]
["LN02041105","Procure Q5 10kw P/S","2006-10-03","2007-03-12"]
["LN02041110","AVAIL: Q5 10kw P/S Ready for Integ","2007-03-13","2007-03-13"]
["LN02041133","AVAIL: 2kw Pwr Supply (SEC-26) Ready for Integ","2007-03-13","2007-03-12"]
["LN020412","2kw POWER SUPPLY (SEC-27) SUMMARY","2006-10-03","2007-03-12"]
["LN02041204","Procure 2kw Pwr Supply - (Sec 27)","2006-10-03","2007-03-12"]
["LN02041233","AVAIL: 2kw Pwr Supply (SEC-27) Ready for Integ","2007-03-13","2007-03-12"]
["LN020415","KICKER (BXBKIK) SUMMARY","2006-09-15","2007-03-19"]
["LN02041510","Prep Bid Package - Pwr Supply - Dipole Type","2006-09-15","2006-09-21"]
["LN02041515","RELEASE: RFP - Pwr Supply - Dipole Type","2006-09-22","2006-09-21"]
["LN02041520","Vendors Prep Proposals - Pwr Spply - Dipole Type","2006-09-22","2006-09-28"]
["LN02041525","RCV: Vendor Proposals - Pwr Supply - Dipole Type","2006-09-29","2006-09-28"]
["LN02041530","Evaluate Vendors Prep Proposals","2006-09-29","2006-10-05"]
["LN02041535","AWARD: Contract - KICKER (BXBKIK)","2006-10-06","2006-10-06"]
["LN02041540","Fab & Assy - KICKER (BXBKIK)","2006-10-09","2007-03-16"]
["LN02041545","AVAIL: BXBKIK Pwr Supply Ready for Instl","2007-03-19","2007-03-19"]
["LN02041610","BY1 POWER SUPPLY SUMMARY","2006-10-03","2007-03-13"]
["LN02041615","Procure 50.8kw P/S (BX31,32,35,36)","2006-10-03","2007-03-12"]
["LN02041620","AVAIL: 50.8kw P/S (BX31,32,35,36) Ready for Inst","2007-03-13","2007-03-13"]
["LN020417","Q6 10kw P/S Ready for Integ SUMMARY","2006-10-03","2007-03-13"]
["LN02041704","Procure Q6 10kw P/S Ready for Integ","2006-10-03","2007-03-12"]
["LN02041733","AVAIL: Q6 10kw P/S Ready for Integ","2007-03-13","2007-03-13"]
["LN020418","QA0 10kw  P/S Ready for Integ SUMMARY","2006-10-03","2007-03-13"]
["LN02041804","Procure QA0 10kw  P/S Ready for Integ","2006-10-03","2007-03-12"]
["LN02041833","AVAIL: QA0 10kw  P/S Ready for Integ","2007-03-13","2007-03-13"]
["LN020419","Q50Q1,Q50Q2,Q50Q3 10kw P/S Rdy for Integ SUMMARY","2006-10-03","2007-03-13"]
["LN02041904","Procure Q50Q1,Q50Q2,Q50Q3 10kw P/S","2006-10-03","2007-03-12"]
["LN02041933","AVAIL: Q50Q1,Q50Q2,Q50Q3 10kw P/S Rdy for Integ","2007-03-13","2007-03-13"]
["LN020420","QVM1 10kw Pwr Supply SUMMARY","2006-10-03","2007-03-13"]
["LN02042004","Procure QVM1 10kw Pwr Supply","2006-10-03","2007-03-12"]
["LN02042033","AVAIL: QVM1 10kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN020421","QVM2 10kw Pwr Supply SUMMARY","2006-10-03","2007-03-13"]
["LN02042104","Procure QVM2 10kw Pwr Supply","2006-10-03","2007-03-12"]
["LN02042133","AVAIL: QVM2 10kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN020422","QEM110 kw Pwr Supply SUMMARY","2006-10-03","2007-03-13"]
["LN02042205","Procure QEM110 kw Pwr Supply","2006-10-03","2007-03-12"]
["LN02042210","AVAIL: QEM110 kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN020423","QEM2 10kw Pwr Supply SUMMARY","2006-10-03","2007-03-13"]
["LN02042305","Procure QEM2 10kw Pwr Supply","2006-10-03","2007-03-12"]
["LN02042310","AVAIL: QEM2 10kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN020424","QVM3 10kw Pwr Supply SUMMARY","2006-10-03","2007-03-13"]
["LN02042404","Procure QVM3 10kw Pwr Supply","2006-10-03","2007-03-12"]
["LN02042433","AVAIL: QVM3 10kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN020425","QVM410kw Pwr Suppl SUMMARY","2006-10-03","2007-03-13"]
["LN02042501","Procure QVM410kw Pwr Suppl","2006-10-03","2007-03-12"]
["LN02042506","AVAIL: QVM410kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN020426","QVB1-3 Pwr Supply SUMMARY","2006-10-03","2007-03-13"]
["LN02042605","Procure QVB1-3 Pwr Supply","2006-10-03","2007-03-12"]
["LN02042610","AVAIL: QVB1-3 Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN020427","QDL31-34 10kw Pwr Supply SUMMARY","2006-10-03","2007-03-13"]
["LN02042705","Procure QDL31-34 10kw Pwr Supply","2006-10-03","2007-03-12"]
["LN02042710","AVAIL: QDL31-34 10kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN020428","QE31-36 10kw Pwr Supply SUMMARY","2006-10-03","2007-03-13"]
["LN02042805","Procure QE31-36 10kw Pwr Supply","2006-10-03","2007-03-12"]
["LN02042810","AVAIL: QE31-36 10kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN020429","QEM3 10kw Pwr SupplySUMMARY","2006-10-03","2007-03-13"]
["LN02042905","Procure QEM3 10kw Pwr Supply","2006-10-03","2007-03-12"]
["LN02042910","AVAIL: QEM3 10kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN02043000","QEM4 10kw Pwr Supply SUMMARY","2006-10-03","2007-03-20"]
["LN02043005","Procure QEM4 10kw Pwr Supply","2006-10-03","2007-03-12"]
["LN02043010","RCV: QEM4 10kw Pwr Supply Ready Hardware","2007-03-13","2007-03-13"]
["LN02043013","Integrate and Test Magnet Interlock","2007-03-14","2007-03-20"]
["LN02043015","AVAIL: QEM4 10kw Pwr Supply Ready for Integ","2007-03-21","2007-03-20"]
["LN020431","QT11,13,21,23,31,33,41,43 26kw P/S SUMMARY","2006-10-03","2007-03-13"]
["LN02043105","Procure QT11,13,21,23,31,33,41,43 26kw P/S","2006-10-03","2007-03-12"]
["LN02043110","AVAIL: QT11,13,21,23,31,33,41,43 26kw Pwr Supply","2007-03-13","2007-03-13"]
["LN020432","QT12,22,32,42  27.2 kw P/S SUMMARY","2006-10-03","2007-03-13"]
["LN02043205","Procure QT12,22,32,42  27.2 kw P/S","2006-10-03","2007-03-12"]
["LN02043210","AVAIL: QT12,22,32,42  27.2 kw P/S Rdy for Integ","2007-03-13","2007-03-13"]
["LN020433","QUM1 10kw Pwr Supply Ready SUMMARY","2006-10-03","2007-03-13"]
["LN02043305","Procure QUM1 10kw Pwr Supply Ready","2006-10-03","2007-03-12"]
["LN02043310","AVAIL: QUM1 10kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN020434","BY1- 2 POWER SUPPLY SUMMARY","2006-10-03","2007-03-13"]
["LN0204341","QUM2 10kw Pwr Supply SUMMARY","2006-10-03","2007-03-13"]
["LN02043410","Procure QUM2 10kw Pwr Supply","2006-10-03","2007-03-12"]
["LN02043415","AVAIL: QUM2 10kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN02043418","Procure 10kw P/S (BY1-2) - Hardware","2006-10-03","2007-03-12"]
["LN02043423","AVAIL: 10kw P/S (BY1-2) Ready for Instl","2007-03-13","2007-03-13"]
["LN020435","KICKER (BYBKIK) SUMMARY","2006-09-15","2007-03-19"]
["LN02043501","Prep Bid Package -  BYBKIK Pwr Supply","2006-09-15","2006-09-21"]
["LN02043503","RELEASE: RFP - Pwr Supply -  BYBKIK Pwr Supply","2006-09-22","2006-09-21"]
["LN02043505","Vendors Prep Proposals -  BYBKIK Pwr Supply","2006-09-22","2006-09-28"]
["LN02043507","RCV: Vendor Proposals -  BYBKIK Pwr Supply","2006-09-29","2006-09-28"]
["LN02043509","Evaluate Vendors Prep Proposals","2006-09-29","2006-10-05"]
["LN02043511","AWARD: Contract -  BYBKIK Pwr Supply","2006-10-06","2006-10-06"]
["LN02043512","Fab & Assy- Power Supply - (Dipole Type)","2006-10-09","2007-03-16"]
["LN02043533","AVAIL: BYBKIK Pwr Supply Ready for Instl","2007-03-19","2007-03-19"]
["LN020436","SPARE PWR SUPPLY SUMMARY- DIPOLE TYPE (1ea)","2006-10-03","2007-04-02"]
["LN0204361","BYW1- 3 POWER SUPPLY SUMMARY","2006-10-03","2007-03-13"]
["LN02043615","Procure 30kw Pwr Supply (BW1-3) - Hardware","2006-10-03","2007-03-12"]
["LN02043619","AVAIL: 30kw Pwr Supply (BW1-3) Ready for Instl","2007-03-13","2007-03-13"]
["LN02043621","Spare Pwr Supply (Dipole Type) Prcurement","2006-10-03","2007-03-12"]
["LN02043622","Assemble Pwr Supply, Transductor & Control","2007-03-13","2007-03-20"]
["LN02043628","Integrate Pwr Supply, Transductor & Control","2007-03-21","2007-03-29"]
["LN02043630","Integrate Cables","2007-03-30","2007-04-02"]
["LN02043633","AVAIL: Spare Power Supply Available - Dipole Typ","2007-04-03","2007-04-02"]
["LN020437","12Amp Pwr Supply + Gnd Flt -(MCOR_1) 7 SUMMARY","2006-01-03","2006-03-06"]
["LN02043704","Procure 12Amp Pwr Supply + Gnd Flt -(MCOR_1) 7","2006-01-03","2006-03-01"]
["LN02043706","RCV: 12Amp Pwr Supply + Gnd Flt -(MCOR_1) 7 Mod","2006-03-02","2006-03-02"]
["LN02043738","Integrate Cables","2006-03-03","2006-03-06"]
["LN02043741","AVAIL: 12Amp P/S + Gnd Flt -(MCOR_1) 7","2006-03-07","2006-03-06"]
["LN020438","MCOR_2 (30Amp) SUMMARY","2006-01-03","2006-03-06"]
["LN02043805","Procure 30Amp P/S + Gnd Flt -(MCOR_2) 7 Mods","2006-01-03","2006-03-01"]
["LN02043810","RCV: 30Amp P/S + Gnd Flt -(MCOR_2) 7 Mods","2006-03-02","2006-03-02"]
["LN02043815","Integrate Cables","2006-03-03","2006-03-06"]
["LN02043820","AVAIL: 30Amp P/S + Gnd Flt -(MCOR_2) 7 Mods","2006-03-07","2006-03-06"]
["LN020439","MCOR_3 (30Amp) SUMMARY","2006-01-03","2006-03-06"]
["LN02043905","Procure 30Amp P/S + Gnd Flt -(MCOR_3) 7 Mods","2006-01-03","2006-03-01"]
["LN02043910","RCV: 30Amp P/S + Gnd Flt -(MCOR_3) 7 Mods","2006-03-02","2006-03-02"]
["LN02043915","Integrate Cables","2006-03-03","2006-03-06"]
["LN02043920","AVAIL: 30Amp P/S + Gnd Flt -(MCOR_3) 7 Mods","2006-03-07","2006-03-06"]
["LN020440","MCOR_4 (30Amp) SUMMARY","2006-01-03","2006-03-06"]
["LN02044005","Procure 30Amp P/S + Gnd Flt -(MCOR_4) 7 Mod","2006-01-03","2006-03-01"]
["LN02044010","RCV: 30Amp P/S + Gnd Flt -(MCOR_4) 7 Mods","2006-03-02","2006-03-02"]
["LN02044015","Integrate Cables","2006-03-03","2006-03-06"]
["LN02044020","AVAIL: 30Amp P/S + Gnd Flt -(MCOR_4) 7 Mods","2006-03-07","2006-03-06"]
["LN020445","MCOR_5 (12/30Amp) SUMMARY","2006-10-03","2007-03-29"]
["LN02044505","Procure 12/30Amp P/S + Gnd Flt -(MCOR_5) 7 Mods","2006-10-03","2007-03-26"]
["LN02044510","RCV: 12/30Amp P/S + Gnd Flt -(MCOR_5) 7 Mods","2007-03-27","2007-03-27"]
["LN02044515","Integrate Cables","2007-03-28","2007-03-29"]
["LN02044520","AVAIL: 12/30Amp P/S + Gnd Flt -(MCOR_5) 7 Mods","2007-03-30","2007-03-29"]
["LN020446","MCOR_LTU3 (12Amp) SUMMARY","2006-10-03","2007-03-15"]
["LN02044605","Procure  12Amp P/S + Gnd Flt-(MCOR_LTU3) Mods","2006-10-03","2007-03-12"]
["LN02044610","RCV:  12Amp P/S + Gnd Flt-(MCOR_LTU3) Mods","2007-03-13","2007-03-13"]
["LN02044615","Integrate Cables","2007-03-14","2007-03-15"]
["LN02044620","AVAIL:  12Amp P/S + Gnd Flt-(MCOR_LTU3) Mods","2007-03-16","2007-03-15"]
["LN02044700","MCOR_LTU3 (12Amp) SUMMARY","2006-10-03","2007-03-23"]
["LN02044705","Procure 12Amp P/S + Gnd Flt-(MCOR_LTU3) 5 Mods","2006-10-03","2007-03-12"]
["LN02044710","RCV: 12Amp P/S + Gnd Flt-(MCOR_LTU3) 5 Mods","2007-03-13","2007-03-13"]
["LN02044715","Integrate Cables","2007-03-14","2007-03-15"]
["LN02044717","Assemble Pwr Supply, Transductor & Control","2007-03-16","2007-03-23"]
["LN02044720","AVAIL: 12Amp P/S + Gnd Flt-(MCOR_LTU3) 5 Mods","2007-03-26","2007-03-23"]
["LN020448","MCOR_LTU5 (12Amp) SUMMARY","2006-10-03","2007-03-15"]
["LN02044805","Procure 12Amp P/S+ Gnd Flt-(MCOR_LTU5) 5 Mods","2006-10-03","2007-03-12"]
["LN02044810","RCV: 12Amp P/S+ Gnd Flt-(MCOR_LTU5) 5 Mods","2007-03-13","2007-03-13"]
["LN02044815","Integrate Cables","2007-03-14","2007-03-15"]
["LN02044820","AVAIL: 12Amp P/S+ Gnd Flt-(MCOR_LTU5) 5 Mods","2007-03-16","2007-03-15"]
["LN020449","MCOR_LTU6 (12Amp) SUMMARY","2006-10-03","2007-03-15"]
["LN02044905","Procure 12Amp P/S + Gnd Flt-(MCOR_LTU6) 5 Mods","2006-10-03","2007-03-12"]
["LN02044910","RCV: 12Amp P/S + Gnd Flt-(MCOR_LTU6) 5 Mods","2007-03-13","2007-03-13"]
["LN02044915","Integrate Cables","2007-03-14","2007-03-15"]
["LN02044920","AVAIL: 12Amp P/S + Gnd Flt-(MCOR_LTU6) 5 Mods","2007-03-16","2007-03-15"]
["LN020450","MCOR_LTU7 (12Amp) SUMMARY","2006-10-03","2007-03-15"]
["LN02045010","RCV: 12Amp P/S + Gnd Flt-(MCOR_LTU7) 5 Mods","2007-03-13","2007-03-13"]
["LN02045015","Integrate Cables","2007-03-14","2007-03-15"]
["LN02045020","AVAIL: 12Amp P/S + Gnd Flt-(MCOR_LTU7) 5 Mods","2007-03-16","2007-03-15"]
["LN020451","MCOR_LTU8 (12Amp) SUMMARY","2006-10-03","2007-03-15"]
["LN02045105","Procure  12Amp P/S + Gnd Flt-(MCOR_LTU8) 5 Mods","2006-10-03","2007-03-12"]
["LN02045110","RCV:  12Amp P/S + Gnd Flt-(MCOR_LTU8) 5 Mods","2007-03-13","2007-03-13"]
["LN02045115","Integrate Cables","2007-03-14","2007-03-15"]
["LN02045120","AVAIL:  12Amp P/S + Gnd Flt-(MCOR_LTU8) 5 Mods","2007-03-16","2007-03-15"]
["LN0204520","MCOR_LTU9 (12Amp) SUMMARY","2006-10-03","2007-03-15"]
["LN02045205","Procure 12Amp P/S + Gnd Flt-(MCOR_LTU9) 5 Mods","2006-10-03","2007-03-12"]
["LN02045210","RCV: 12Amp P/S + Gnd Flt-(MCOR_LTU9) 5 Mods","2007-03-13","2007-03-13"]
["LN02045215","Integrate Cables","2007-03-14","2007-03-15"]
["LN02045220","AVAIL: 12Amp P/S + Gnd Flt-(MCOR_LTU9) 5 Mods","2007-03-16","2007-03-15"]
["LN02045225","Spare Power Supply Procurement","2006-10-03","2007-03-12"]
["LN02045226","RCV: Spare MCOR System Hardware/Equip.","2007-03-13","2007-03-12"]
["LN02045238","Integrate Cables","2007-03-13","2007-03-14"]
["LN02045241","AVAIL: Spare Power Supply Available - Trim Type","2007-03-15","2007-03-14"]
["LN020453","SPARE PWR SUPPLY SUMMARY- QUAD TYPE (1ea)","2006-10-03","2007-04-03"]
["LN02045317","Spare Pwr Supply (Quad Type) Procurement","2006-10-03","2007-03-12"]
["LN02045318","Assemble Pwr Supply, Transductor & Control","2007-03-13","2007-03-20"]
["LN02045320","Integrate Pwr Supply, Transductor & Control","2007-03-21","2007-03-29"]
["LN02045322","Integrate Cables","2007-03-30","2007-04-02"]
["LN02045324","Integrate Magnet Interlock","2007-04-03","2007-04-03"]
["LN02045326","AVAIL: Spare Power Supply Available - Quad Type","2007-04-04","2007-04-03"]
["LN020455","QUM3 10kw Pwr SupplySUMMARY","2006-10-03","2007-03-13"]
["LN02045505","Procure QUM3 10kw Pwr Supply","2006-10-03","2007-03-12"]
["LN02045510","AVAIL: QUM3 10kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN020465","QUM4 10kw Pwr Supply SUMMARY","2006-10-03","2007-03-13"]
["LN02046505","Procure QUM4 10kw Pwr Supply","2006-10-03","2007-03-12"]
["LN02046510","AVAIL: QUM4 10kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN020466","QDMP1-2 10kw Pwr Supply SUMMARY","2006-10-03","2007-03-13"]
["LN02046605","Procure QDMP1-2 10kw Pwr Supply","2006-10-03","2007-03-12"]
["LN02046610","AVAIL: QDMP1-2 10kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN020467","QUE1 10kw Pwr Supply SUMMARY","2006-10-03","2007-03-13"]
["LN02046705","Procure QUE1 10kw Pwr Supply","2006-10-03","2007-03-12"]
["LN02046710","AVAIL: QUE1 10kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN020468","QUE2 10kw Pwr Supply SUMMARY","2006-10-03","2007-03-13"]
["LN02046805","Procure QUE2 10kw Pwr Supply","2006-10-03","2007-03-12"]
["LN02046810","AVAIL: QUE2 10kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN020471","MCOR_6 (12/30Amp) SUMMARY","2006-10-03","2007-03-15"]
["LN02047105","Procure 12/30Amp P/Sy + Gnd Flt -(MCOR_6) 7 Mods","2006-10-03","2007-03-12"]
["LN02047110","RCV: 12/30Amp P/Sy + Gnd Flt -(MCOR_6) 7 Mods","2007-03-13","2007-03-13"]
["LN02047115","Integrate Cables","2007-03-14","2007-03-15"]
["LN02047120","AVAIL: 12/30Amp P/Sy + Gnd Flt -(MCOR_6) 7 Mods","2007-03-16","2007-03-15"]
["LN020472","MCOR_BS1Y (12Amp) SUMMARY","2006-10-03","2007-03-15"]
["LN02047205","Procure 12Amp P/S + Gnd Flt-(MCOR_BSY1) 5 Mods","2006-10-03","2007-03-12"]
["LN02047210","RCV: 12Amp P/S + Gnd Flt-(MCOR_BSY1) 5 Mods","2007-03-13","2007-03-13"]
["LN02047215","Integrate Cables","2007-03-14","2007-03-15"]
["LN02047220","AVAIL: 12Amp P/S + Gnd Flt-(MCOR_BSY1) 5 Mods","2007-03-16","2007-03-15"]
["LN020473","MCOR_LTU1 (12Amp) SUMMARY","2006-10-03","2007-03-15"]
["LN02047305","Procure 12Amp P/S + Gnd Flt-(MCOR_LTU1) 5 Mods","2006-10-03","2007-03-12"]
["LN02047310","RCV: 12Amp P/S + Gnd Flt-(MCOR_LTU1) 5 Mods","2007-03-13","2007-03-13"]
["LN02047315","Integrate Cables","2007-03-14","2007-03-15"]
["LN02047320","AVAIL: 12Amp P/S + Gnd Flt-(MCOR_LTU1) 5 Mods","2007-03-16","2007-03-15"]
["LN020474","MCOR_LTU2 (12Amp) SUMMARY","2006-10-03","2007-03-15"]
["LN02047405","Procure 12Amp P/S + Gnd Flt-(MCOR_LTU2) 5 Mods","2006-10-03","2007-03-12"]
["LN02047410","RCV: 12Amp P/S + Gnd Flt-(MCOR_LTU2) 5 Mods","2007-03-13","2007-03-13"]
["LN02047415","Integrate Cables","2007-03-14","2007-03-15"]
["LN02047420","AVAIL: 12Amp P/S + Gnd Flt-(MCOR_LTU2) 5 Mods","2007-03-16","2007-03-15"]
["LN020479","MCOR_DMP1 (12Amp) SUMMARY","2006-10-03","2007-03-15"]
["LN02047905","Procure 12Amp P/S + Gnd Flt-(MCOR_DMP1) 5 Mods","2006-10-03","2007-03-12"]
["LN02047910","RCV: 12Amp P/S + Gnd Flt-(MCOR_DMP1) 5 Mods","2007-03-13","2007-03-13"]
["LN02047915","Integrate Cables","2007-03-14","2007-03-15"]
["LN02047920","AVAIL: 12Amp P/S + Gnd Flt-(MCOR_DMP1) 5 Mods","2007-03-16","2007-03-15"]
["LN020480","10kw Pwr Supply (MUSPLR) SUMMARY","2006-10-03","2007-03-13"]
["LN02048018","Procure 10kw Pwr Supply (MUSPLR)- Hrdwr","2006-10-03","2007-03-12"]
["LN02048046","AVAIL: 10kw Pwr Supply (MUSPLR)- Ready for Integ","2007-03-13","2007-03-13"]
["LN020490","Procure 10kw Pwr Supply  - (BYD1-3) SUMMARY","2006-10-03","2007-03-13"]
["LN02049015","Procure 10kw Pwr Supply  - (BYD1-3)","2006-10-03","2007-03-12"]
["LN02049020","AVAIL: 10kw Pwr Supply (BYD1-3) Ready for Integ","2007-03-13","2007-03-13"]
["LN0204_000","LINAC POWER SUPPLIES (DIPOLE) SUMMARY","2005-07-11","2008-01-03"]
["LN0204_010","Finalize Power Conv Reqmts Definition (Dipole)","2005-07-11","2005-07-15"]
["LN0204_015","COMP: Pwr Conv Specification Requirements","2005-07-18","2005-07-15"]
["LN0204_020","Dev Engr (43 instaces - 18 types) PED","2005-07-18","2005-12-16"]
["LN0204_021","Dev Engr (43 instaces - 18 types) CONST","2006-01-03","2007-06-05"]
["LN0204_025","Create System Drawings","2006-01-03","2007-07-25"]
["LN0204_027","AWARD: LTU Racks Contract","2007-05-21","2007-05-21"]
["LN0204_050","LINAC POWER SUPPLIES (QUAD) SUMMARY","2005-07-11","2007-03-27"]
["LN0204_060","Finalize Power Conv Reqmts Definition (Quad)","2005-07-11","2005-07-15"]
["LN0204_065","COMP: Pwr Conv Specification Reqmts (Quad)","2005-07-18","2005-07-15"]
["LN0204_075","Conduct ES&H Review - (Quad Type)","2005-07-18","2005-07-19"]
["LN0204_080","COMP: Power Supply Design  - (Quad Type)","2005-07-20","2005-07-19"]
["LN0204_100","LINAC POWER SUPPLIES (TRIM) SUMMARY","2005-07-11","2007-03-29"]
["LN0204_110","Finalize Power Conv Reqmts Definition (Trim)","2005-07-11","2005-07-15"]
["LN0204_115","COMP: Pwr Conv Specification Requirements","2005-07-18","2005-07-15"]
["LN0204_200","CONTROLS & POWER SUPPLY MISC HDWR SUMMARY","2005-10-03","2007-12-10"]
["LN0204_210","Write Software to Integrate","2005-10-03","2006-01-11"]
["LN0204_212","Write Documentation","2006-01-12","2006-01-26"]
["LN0204_214","Perform Point to Point Checkout","2006-01-27","2006-04-21"]
["LN0204_216","Integrate Hardware and Software","2006-04-24","2006-05-05"]
["LN0204_218","AVAIL: Linac Controls Ready to Integrate","2006-05-08","2006-05-05"]
["LN0204_444","L1-BC1 Cable Plant Design","2005-11-01","2005-12-14"]
["LN0204_454","COMP: L1-BC1 Cable Plant Design","2005-12-15","2005-12-14"]
["LN0204_464","Prep L1-BC1 Bid Package","2005-12-15","2006-01-05"]
["LN0204_474","AWARD: L1-BC1 Cable Plant Contract","2006-01-06","2006-01-06"]
["LN0204_484","Vendor Fab L1-BC1 Cable Plant Hardware","2006-01-09","2006-04-04"]
["LN0204_494","RCV: L1-BC1 Cable Plant from Vendor","2006-04-05","2006-04-04"]
["LN0204_504","Intall & Integrate L1-BC1 Cable Plant","2006-04-05","2006-07-27"]
["LN0204_514","AVAIL: Cable Plant Ready for L1-BC1 Installation","2006-07-28","2006-07-27"]
["LN0204_605","L1-BC1 Racks Design","2005-11-01","2005-12-14"]
["LN0204_615","COMP: L1-BC1 Racks Design","2005-12-15","2005-12-14"]
["LN0204_625","Prep L1-BC1 Bid Package","2005-12-15","2006-01-05"]
["LN0204_635","AWARD: L1-BC1 Racks Contract","2006-01-06","2006-01-06"]
["LN0204_645","Vendor Fab LC1-BC1 Racks","2006-01-09","2006-04-04"]
["LN0204_655","RCV: L1-BC1 Racks from Vendor","2006-04-05","2006-04-04"]
["LN0204_665","Intall & Integrate L1-BC1 Racks","2006-04-05","2006-07-27"]
["LN0204_675","AVAIL: Racks for L1-BC1 Installation","2006-07-28","2006-07-27"]
["LN0204_685","L2-BC2 Cable Plant Design","2006-10-02","2006-11-10"]
["LN0204_695","COMP: L2-BC2 Cable Plant Design","2006-11-13","2006-11-10"]
["LN0204_705","Prep L2-BC2 Cable Plant Bid Package","2006-11-13","2006-11-17"]
["LN0204_715","AWARD: L2-BC2 Cable Plant Contract","2006-11-20","2006-11-20"]
["LN0204_725","Vendor Fab L2-BC2 Cable Plant Hardware","2006-11-21","2007-03-05"]
["LN0204_735","RCV: L2-BC2 Cable Plant from Vendor","2007-03-06","2007-03-05"]
["LN0204_745","Intall & Integrate L2-BC2 Cable Plant","2007-03-06","2007-06-26"]
["LN0204_755","AVAIL: Cable Plant Ready for L2-BC2 Installation","2007-06-27","2007-06-26"]
["LN0204_765","L2-BC2 Racks Design","2006-10-02","2006-11-10"]
["LN0204_775","COMP: L2-BC2 Rack Design","2006-11-13","2006-11-10"]
["LN0204_785","Prep LC2-BC2 Bid Package","2006-11-13","2007-02-01"]
["LN0204_795","AWARD: LC2-BC2 Racks Contract","2007-02-02","2007-02-02"]
["LN0204_805","Vendor Fab LC2-BC2 Racks","2007-02-05","2007-04-30"]
["LN0204_815","RCV: L2-BC2 Racks from Vendor","2007-05-01","2007-04-30"]
["LN0204_825","Intall & Integrate L2-BC2 Racks","2007-05-01","2007-08-22"]
["LN0204_835","AVAIL: Racks for L2-BC2 Installation","2007-08-23","2007-08-22"]
["LN0204_926","LTU Cable Plant Design","2007-04-02","2007-05-11"]
["LN0204_936","COMP: LTU Cable Plant Design","2007-05-14","2007-05-11"]
["LN0204_946","Prep LTLU Bid Package","2007-05-14","2007-05-18"]
["LN0204_956","AWARD: LTU Cable Plant Contract","2007-05-21","2007-05-21"]
["LN0204_966","Vendor Fab LTU Cable Plant Hardware","2007-05-22","2007-08-15"]
["LN0204_976","RCV: LTU Cable Plant from Vendor","2007-08-16","2007-08-15"]
["LN0204_986","Intall & Integrate LTU Cable Plant","2007-08-16","2007-12-10"]
["LN0204_996","AVAIL: Cable Plant Ready for LTU Installation","2007-12-11","2007-12-10"]
["LN0204_997","LTU Racks Design","2007-04-02","2007-05-11"]
["LN0204`007","COMP: LTU Racks Design","2007-05-14","2007-05-11"]
["LN0204`017","Prep LTU Bid Package","2007-05-14","2007-05-18"]
["LN0204`037","Vendor Fab LTU Racks","2007-05-22","2007-08-15"]
["LN0204`047","RCV: LTU Racks from Vendor","2007-08-16","2007-08-15"]
["LN0204`057","Intall & Integrate LTU Racks","2007-08-16","2007-12-10"]
["LN0204`067","AVAIL: Racks for LTU Installation","2007-12-11","2007-12-10"]
["LN02050045","Construction Funds Available - Begin Procurement","2005-10-03","2005-09-30"]
["LN02050130","Procure Linac LLRF Hardware","2006-07-03","2006-09-26"]
["LN02050195","RCV: Procured parts - Bm Phz Monitor Cntrls","2006-09-27","2006-09-26"]
["LN02050201","Build LLRF H/W and Write Docmntatn (sec 24/30)","2006-08-28","2006-09-26"]
["LN02050206","Write LLRF S/W Docmntatn (sec 24/30)","2006-07-03","2006-07-10"]
["LN02050207","Integrate and Test (sec 24/30)","2006-09-27","2006-12-01"]
["LN02050260","Procure LLRF BL Mon Cntrls hardware","2006-07-03","2006-09-26"]
["LN02050265","RCV: Procured parts","2006-09-27","2006-09-26"]
["LN02050266","Integrate and Test (BLM sec 24/30)","2006-09-27","2006-12-01"]
["LN02050295","AVAIL: Bnch Length Monitor Cntrls Ready to Integ","2006-12-04","2006-12-01"]
["LN02055005","Procure 12Amp P/S + Gnd Flt-(MCOR_LTU7) 5 Mods","2006-10-03","2007-03-12"]
["LN02060190","Procure 3 sets of Controls Wire Scanners Ph-1","2006-07-03","2006-07-31"]
["LN02060191","RCV: 3 Sets of Controls Wire Scanners Ph-1","2006-08-01","2006-08-01"]
["LN02060200","Build HW & Write SW for LINAC Wire Scanners Ph-1","2006-08-02","2006-08-29"]
["LN02060210","Integrate and Test Controls Wire Scanners Ph-1","2006-08-30","2006-09-27"]
["LN02060220","AVAIL: Ph-1 Ctrl Wire Scanners Ready for Install","2006-08-30","2006-08-29"]
["LN02060230","Procure 8 sets of Controls Wire Scanners Ph-2","2006-08-30","2006-11-22"]
["LN02060232","RCV: 8 Sets of Controls Wire Scanners Ph-2","2006-11-27","2006-11-27"]
["LN02060240","Build HW & Write SW for LINAC Wire Scanners Ph-2","2006-11-28","2007-01-25"]
["LN02060250","Integrate and Test Controls Wire Scanners Ph-2","2007-01-26","2007-03-23"]
["LN02060260","AVAIL: Ph-2 Ctrl Wire Scanners Ready for Install","2005-05-02","2005-04-29"]
["LN02060270","Procure 4 sets of Controls Wire Scanners Ph-3","2006-10-02","2006-12-27"]
["LN02060272","RCV: 4 Sets of Controls Wire Scanners Ph-3","2007-01-02","2007-01-02"]
["LN02060280","Build HW & Write SW for LINAC Wire Scanners Ph-3","2007-01-03","2007-03-01"]
["LN02060290","Integrate and Test Controls Wire Scanners Ph-3","2007-03-02","2007-04-26"]
["LN020603","CONTROLS - TOROIDS (6) SUMMARY","2005-10-03","2006-12-06"]
["LN02060300","AVAIL: Ph-3 Ctrl Wire Scanners Ready for Install","2007-04-27","2007-04-26"]
["LN02060327","Construction Funds Available - Begin Procurement","2005-10-03","2005-09-30"]
["LN02060330","AWARD Torroid Shielding, Preamps, Hardware (6)","2006-07-03","2006-07-03"]
["LN02060331","Procure Torroid Shielding, Preamps, Hardware (6)","2006-07-05","2006-09-06"]
["LN02060340","Build Hardware (Toroids)","2006-09-07","2006-11-02"]
["LN02060358","Write Software - Toroids","2006-11-03","2006-11-09"]
["LN02060360","Write Documentation - Toroids","2006-11-10","2006-11-16"]
["LN02060361","Integrate and Test Toroids","2006-11-17","2006-12-06"]
["LN02060366","AVAIL: Toroids Cntrls Eq Ready for Rack Integ","2006-12-07","2006-12-06"]
["LN020604","CONTROLS - STOPPERS SUMMARY","2005-10-03","2007-06-12"]
["LN02060428","Construction Funds Available - Begin Procurement","2005-10-03","2005-09-30"]
["LN02060430","Procure Stopper Controls Hdwr/Eq","2007-01-02","2007-01-30"]
["LN02060431","RCV: Stopper Controls Hdwr/Eq","2007-01-31","2007-01-31"]
["LN02060432","Build Stopper Controls H/W","2007-02-01","2007-03-30"]
["LN02060438","Write Software - Stoppers","2007-04-02","2007-04-27"]
["LN02060440","Write Documentation - Stoppers","2007-04-30","2007-05-04"]
["LN02060446","Integrate and Test Stopper Controls","2007-05-07","2007-06-12"]
["LN02060448","AVAIL: Stoppers Cntrls Eq Ready for Rack Integ","2007-06-13","2007-06-12"]
["LN02060590","Procure 7 Units - Profile Monitors PH1","2006-07-03","2006-07-31"]
["LN02060592","RCV: 7 Units - Profile Monitors PH1","2006-08-01","2006-08-01"]
["LN020606","CONTROLS - E/O DIAGNOSTICS SUMMARY","2005-10-03","2006-08-08"]
["LN02060600","Build HW & Write SW - Profile Monitors PH1","2006-08-01","2006-08-28"]
["LN02060610","Integrate & Test - Profile Monitors PH1","2006-08-29","2006-09-26"]
["LN02060620","AVAIL: Profile Monitors PH1 Ready for Rack Integ","2006-08-29","2006-08-28"]
["LN02060627","Construction Funds Available - Begin Procurement","2005-10-03","2005-09-30"]
["LN02060628","Procure E/O Electronics","2006-04-27","2006-05-24"]
["LN02060630","Procure 7 Units - Profile Monitors PH2","2006-10-02","2006-12-27"]
["LN02060632","RCV: 7 Units - Profile Monitors PH2","2006-12-28","2006-12-28"]
["LN02060640","Build HW & Write SW - Profile Monitors PH2","2006-12-29","2007-01-29"]
["LN02060643","Build H/W (E/O Diagnostics)","2006-05-25","2006-06-30"]
["LN02060644","Write Software - E/O Diagnostics","2006-05-25","2006-06-22"]
["LN02060646","Write Documentation - E/O Eloctronics","2006-06-23","2006-06-29"]
["LN02060650","Integrate & Test - Profile Monitors PH2","2007-01-30","2007-02-27"]
["LN02060653","Integrate and Test E/O Electronics","2006-07-03","2006-08-08"]
["LN02060654","AVAIL: E/O Diag Cntrls Eq Ready for Rack Integ","2006-08-09","2006-08-08"]
["LN02060660","AVAIL: Profile Monitors PH2 Ready for Rack Integ","2007-02-28","2007-02-27"]
["LN02060670","Build HW & Write SW - Profile Monitors PH3","2007-02-28","2007-05-22"]
["LN02060672","Build HW & Write SW - Profile Monitors PH3","2007-05-23","2007-05-23"]
["LN02060680","Build HW & Write SW - Profile Monitors PH3","2007-05-24","2007-06-21"]
["LN02060690","Integrate & Test - Profile Monitors PH3","2007-06-22","2007-07-20"]
["LN020607","CONTROLS - BUNCH LENGTH MONITORS SUMMARY","2006-07-03","2006-10-12"]
["LN02060700","AVAIL: Profile Monitors PH3 Ready for Rack Integ","2007-07-23","2007-07-20"]
["LN02060727","Construction Funds Available - Begin Procurement","2006-07-03","2006-06-30"]
["LN02060728","Procure BLM Controls Hdwr/Eq","2006-07-03","2006-07-31"]
["LN02060733","Build BLM Hardware","2006-08-01","2006-09-06"]
["LN02060734","Write Software - BLM Diagnostics","2006-07-03","2006-07-31"]
["LN02060736","Write Documentation - BLM Diagnostics","2006-08-01","2006-08-07"]
["LN02060743","Integrate and Test BLM","2006-09-07","2006-10-12"]
["LN02060744","AVAIL: Bnch Lngth Cntrls Eq Ready for Rack Integ","2006-10-13","2006-10-12"]
["LN020608","CONTROLS - BEAM LOSS MONITORS (PLIC) SUMMARY","2006-07-03","2006-11-17"]
["LN02060828","Procure BLM Controls Hdwr/Eq","2006-07-03","2006-07-31"]
["LN02060833","Build Beam Loss Monitor","2006-08-01","2006-09-07"]
["LN02060834","Write Software - Bm Lss Mon Diagnostics","2006-09-08","2006-10-05"]
["LN02060836","Write Documentation - Bm Lss Mon Diagnostics","2006-10-06","2006-10-12"]
["LN02060843","Integrate & Test","2006-10-13","2006-11-17"]
["LN02060844","AVAIL: Bm Lss Mon Cntrls Eq Ready for Rack Integ","2006-11-20","2006-11-17"]
["LN020609","CONTROLS - SINGLE BEAM DUMP SUMMARY","2005-10-03","2007-03-21"]
["LN02060900","Receive System Requirements","2006-10-03","2006-10-09"]
["LN02060925","Design Single Beam Dump","2006-10-10","2006-12-13"]
["LN02060926","COMP: Controls Design - Single Beam Dump","2006-12-14","2006-12-13"]
["LN02060927","Construction Funds Available - Begin Procurement","2005-10-03","2005-09-30"]
["LN02060929","Single Beam Dump Hardware","2006-12-14","2007-01-26"]
["LN02060937","Build Single Beam Dump H/W","2007-01-29","2007-02-27"]
["LN02060938","Write Software - Single Beam Dump","2007-01-29","2007-02-26"]
["LN02060940","Write Documentation - Single Beam Dump","2007-02-27","2007-03-05"]
["LN02060947","Integrate and Test Signle Beam Dump","2007-03-06","2007-03-21"]
["LN02060948","AVAIL: Sngl Bm DmpCntrls Eq Ready for Rack Integ","2007-03-22","2007-03-21"]
["LN020610","CONTROLS - E-BEAM DUMP SUMMARY","2005-10-03","2007-05-03"]
["LN02061000","Receive System Requirements","2006-10-03","2006-10-09"]
["LN02061025","Design E Beam Dump","2006-10-10","2007-01-22"]
["LN02061026","COMP: Controls Design - E Beam Dump","2007-01-23","2007-01-22"]
["LN02061027","Construction Funds Available - Begin Procurement","2005-10-03","2005-09-30"]
["LN02061028","Procure E-Beam Dump Controls Hdwr/Eq","2007-01-23","2007-02-20"]
["LN02061033","Build E Beam Dump H/W","2007-01-23","2007-02-21"]
["LN02061034","Write Software - E Beam Dump","2007-02-22","2007-03-21"]
["LN02061036","Write Documentation - E Beam Dump","2007-03-22","2007-03-28"]
["LN02061043","Integrate and Test","2007-03-29","2007-05-03"]
["LN02061044","AVAIL: E Bm Dmp Cntrls Eq Ready for Rack Integ","2007-05-04","2007-05-03"]
["LN020611","CONTROLS - PROTECTION COLLIMATOR SUMMARY","2005-10-03","2006-10-13"]
["LN02061100","Receive System Requirements","2006-04-10","2006-04-14"]
["LN02061125","Design Moveable Protection Collimator","2006-04-17","2006-07-03"]
["LN02061126","COMP: Controls Design - Protection Collimators","2006-07-05","2006-07-03"]
["LN02061127","Construction Funds Available - Begin Procurement","2005-10-03","2005-09-30"]
["LN02061129","Movable Collimator Hardware","2006-07-05","2006-08-01"]
["LN02061165","Build Collimator H/W","2006-07-05","2006-08-02"]
["LN02061166","Write Software - Prot Collimator","2006-08-03","2006-08-30"]
["LN02061168","Write Documentation - Prot Collimator","2006-08-31","2006-09-07"]
["LN02061175","Integrate and Test","2006-09-08","2006-10-13"]
["LN02061176","AVAIL: Prot Coll Cntrls Eq Ready for Rack Integ","2006-10-16","2006-10-13"]
["LN020612","CONTROLS - MOVABLE COLLIMATORS SUMMARY","2006-12-01","2007-04-25"]
["LN02061200","Receive System Requirements","2006-12-01","2006-12-07"]
["LN02061225","Design Collimator Controls","2006-12-08","2007-01-22"]
["LN02061226","COMP: Controls Design - Movable Collimators","2007-01-23","2007-01-22"]
["LN02061228","Procure Movable Collimator Controls Hdwr/Eq","2007-01-23","2007-01-22"]
["LN02061233","Build Collimator H/W","2007-01-23","2007-02-21"]
["LN02061234","Write Software - Movable Collimator","2007-02-22","2007-03-21"]
["LN02061236","Write Documentation - Movable Collimator","2007-03-22","2007-03-28"]
["LN02061243","Integrate and Test","2007-03-29","2007-04-25"]
["LN02061244","AVAIL: Move Coll Cntrls Eq Ready for Rack Integ","2007-04-26","2007-04-25"]
["LN020613","CONTROLS - X-BAND ACCEL STRUCTURE SUMMARY","2006-06-01","2006-11-14"]
["LN02061300","Receive System Requirements","2006-06-01","2006-06-07"]
["LN02061325","Design X Band Controls","2006-06-08","2006-09-01"]
["LN02061326","COMP: Controls Design - X Band Accel Structures","2006-09-05","2006-09-01"]
["LN02061328","Procure X-Band Accel Struct Controls Hdwr/Eq","2006-09-05","2006-10-02"]
["LN02061333","Build X-Band H/W","2006-09-05","2006-10-02"]
["LN02061334","Write Software - X Band Accel Structure","2006-09-05","2006-10-02"]
["LN02061336","Write Documentation - X Band Accel Structure","2006-10-03","2006-10-09"]
["LN02061343","Integrate and Test","2006-10-10","2006-11-14"]
["LN02061344","AVAIL: X Bnd Stru Cntrls Eq Ready for Rack Integ","2006-11-15","2006-11-14"]
["LN02062550","Procure 7 Units of BPMs PH1","2006-07-05","2006-08-15"]
["LN02062552","RCV: 7 Units of BPMs Ph1","2006-08-16","2006-08-16"]
["LN02062560","Build HW & Write SW - BPMs PH1","2006-08-16","2006-09-13"]
["LN02062570","Integrate & Test - BPMs PH1","2006-09-14","2006-10-11"]
["LN02062580","AVAIL: L01 BPMs Ready for Install","2006-10-12","2006-10-11"]
["LN02062890","Procure 87 Units of BPMs PH2","2006-10-12","2006-11-22"]
["LN02062892","RCV: 87 Units of BPMs PH2","2006-11-27","2006-11-27"]
["LN02062900","Build HW & Write SW - BPMs PH2","2006-11-27","2007-03-22"]
["LN02062910","Integrate & Test - BPMs PH2","2007-03-23","2007-07-16"]
["LN02062920","AVAIL: L02 BPMs Ready for Install","2007-03-23","2007-03-22"]
["LN02062930","Procure 42 Units of BPMs PH3","2007-03-23","2007-05-03"]
["LN02062932","RCV: 42 Units of BPMs PH3","2007-05-04","2007-05-04"]
["LN02062940","Build HW & Write SW - BPMs PH3","2007-05-04","2007-06-29"]
["LN02062945","AVAIL: L03 BPMs Ready for Install","2007-07-02","2007-07-02"]
["LN02062950","Integrate & Test - BPMs PH3","2007-07-03","2007-08-28"]
["LN0208","LINAC TIMING SUMMARY","2005-10-03","2006-05-18"]
["LN02080020","Construction Funds Available - Begin Procurement","2005-10-03","2005-09-30"]
["LN02080025","Prep Bid Pak - Linac Timing Modules","2006-03-01","2006-03-07"]
["LN02080030","RELEASE: RFP - Linac Timing Modules","2006-03-08","2006-03-07"]
["LN02080035","Vendors Prep Proposals - Timing Cntrls Equipment","2006-03-08","2006-03-14"]
["LN02080040","RCV: Vendor Proposals","2006-03-15","2006-03-14"]
["LN02080045","Evaluate Vendor Proposals","2006-03-15","2006-03-21"]
["LN02080050","AWARD: Contract - Linac Timing Modules","2006-03-22","2006-03-22"]
["LN02080060","Vendor Fab & Assy - Timing modules (SLC to VME)","2006-03-23","2006-05-17"]
["LN02080065","RCV: Linac Timing Equip/Material Ready for Integ","2006-05-18","2006-05-18"]
["LN0209","VACUUM CONTROLS SUMMARY","2005-10-03","2007-06-19"]
["LN02090070","Construction Funds Available - Begin Procurement","2005-10-03","2005-09-30"]
["LN02090088","AWARD: Contract - Vacuum Valve Chassis  (4)","2005-10-03","2005-10-03"]
["LN02090090","Vendor Fab & Assy - Vacuum Valve Chassis  (4)","2006-02-01","2006-03-01"]
["LN02090250","Procure Vacuum Instrumentation & Iterlocks H/W","2006-01-03","2006-03-29"]
["LN02090260","Build Hardeare & Write SW for Vacuum Controls","2006-03-30","2006-04-26"]
["LN02090270","Integrate & Test Vacuum Controls","2006-04-27","2006-05-24"]
["LN02090280","AVAIL: Vac Controls Equip Ready for Install","2006-05-25","2006-05-24"]
["LN02090290","Procure Vacuum Instrumentation & Iterlocks H/W","2006-10-02","2006-12-27"]
["LN02090300","Build Hardeare & Write SW for Vacuum Controls","2006-12-28","2007-03-26"]
["LN02090310","Integrate & Test Vacuum Controls","2007-03-27","2007-06-19"]
["LN02090320","AVAIL: Vac Controls Equip Ready for Install","2007-06-20","2007-06-19"]
["LN021004","DATA COMMUNICATIONS SUMMARY","2006-01-03","2006-11-17"]
["LN02100400","Supervise Equipment Installation","2006-01-03","2006-02-14"]
["LN02100405","Upgrade/Establish BDF","2006-02-15","2006-02-15"]
["LN02100410","SEM Install Wall Board","2006-02-16","2006-03-02"]
["LN02100415","SEM Install Two 20 A Circuits","2006-03-03","2006-03-30"]
["LN02100420","Single Mode Fiber Installation","2006-03-31","2006-03-31"]
["LN02100425","Procure Singlemode Fiber","2006-04-03","2006-04-28"]
["LN02100430","Fiber Cabling Installation","2006-05-01","2006-05-26"]
["LN02100435","Fiber Termination","2006-05-30","2006-06-26"]
["LN02100440","Desktop Cabling Installation","2006-06-27","2006-06-27"]
["LN02100445","Cabling Installation in Ground & Sub Ground Loc","2006-06-28","2006-07-26"]
["LN02100450","Cable Termination","2006-07-27","2006-08-23"]
["LN02100455","Desktop Circuit Activation","2006-08-24","2006-08-24"]
["LN02100460","Telcom to Provide Phone & Activate Circuits","2006-08-25","2006-09-22"]
["LN02100465","Procure Cisco 3550-24 Hubs (6ea)","2006-09-25","2006-10-20"]
["LN02100470","Hub Installation & Data Circuit Activiation","2006-10-23","2006-11-17"]
["LN02100475","AVAIL: Data Comm Circuits Active & Ready","2006-11-20","2006-11-17"]
["LN021005","COMPUTERS & CRATES SUMMARY","2006-01-03","2006-06-19"]
["LN02100500","Finalize Specification Requirements - Computer","2006-01-03","2006-01-03"]
["LN02100502","Provide Hardware Engineer & Systems Integ Sup","2006-01-04","2006-05-11"]
["LN02100504","Design  VME Crates, Control & Support Modules","2006-01-04","2006-02-01"]
["LN02100506","COMP: Computers & Crates Design","2006-02-02","2006-02-01"]
["LN02100510","Prep Bid Pak - VME Crates/IOCs/Interface Chassis","2006-02-02","2006-02-08"]
["LN02100512","RELEASE: RFP - VME Crates/IOCs/Interface Chassis","2006-02-09","2006-02-08"]
["LN02100514","Vendors Prep Proposals - Cntrls Computers","2006-02-09","2006-02-15"]
["LN02100516","RCV: Proposl - VME Crates/IOCs/Interface Chassis","2006-02-16","2006-02-15"]
["LN02100518","Evaluate Vendors Proposals","2006-02-16","2006-02-23"]
["LN02100520","AWARD: Contrct VME Crates/IOCs/Interface Chassis","2006-02-24","2006-02-24"]
["LN02100522","Vendor Fab/Assy VME Crates/IOCs/Interface Chssis","2006-02-27","2006-03-24"]
["LN02100524","RCV: VME Crates/IOC's/Interface Chassis (3VME-7","2006-03-27","2006-03-24"]
["LN02100530","Prep Bid Pak - VME Crates for BPMs","2006-02-02","2006-02-08"]
["LN02100532","RELEASE: RFP - VME Crates for BPMs","2006-02-09","2006-02-08"]
["LN02100534","Vendors Prep Proposals - VME Crates for BPMs","2006-02-09","2006-02-15"]
["LN02100536","RCV: Proposals - VME Crates for BPMs","2006-02-16","2006-02-15"]
["LN02100538","Evaluate Vendors Proposals","2006-02-16","2006-02-23"]
["LN02100540","AWARD: Contract - VME Crates for BPMs","2006-02-24","2006-02-24"]
["LN02100542","Vendor Fab & Assy - VME Crates for BPMs","2006-02-27","2006-03-24"]
["LN02100544","RCV: from Vendors VME Crates for BPMs","2006-03-27","2006-03-24"]
["LN02100550","Prep Bid Pak -VME Crates/Cntrl/Supt Chassis","2006-02-02","2006-02-08"]
["LN02100552","RELEASE: RFP -VME Crates/Cntrl/Supt Chassis","2006-02-09","2006-02-08"]
["LN02100554","Vendors Prep Proposals -VME Crates/Cntrl/Supt Ch","2006-02-09","2006-02-15"]
["LN02100556","RCV: Proposals -VME Crates/Cntrl/Supt Chassis","2006-02-16","2006-02-15"]
["LN02100558","Evaluate Vendors Proposals","2006-02-16","2006-02-23"]
["LN02100560","AWARD: Contract -VME Crates/Cntrl/Supt Chassis","2006-02-24","2006-02-24"]
["LN02100562","Vendor Fab & Assy -VME Crates/Cntrl/Supt Chassis","2006-02-27","2006-03-24"]
["LN02100564","RCV: VME Crates, Control & Support Chassis","2006-03-27","2006-03-24"]
["LN02100620","Procure Cableplant","2006-02-02","2006-03-02"]
["LN02100625","RCV: Cableplant","2006-03-03","2006-03-02"]
["LN02100630","Procure VME System I/O Distribution Cableplant","2006-02-02","2006-03-02"]
["LN02100635","RCV: VME System Intra-Rack Dist I/O General Cab","2006-03-03","2006-03-02"]
["LN02100640","Assemble and Integrate Equipment","2006-03-27","2006-05-05"]
["LN02100645","Conduct Pre-Install Testing","2006-05-08","2006-06-19"]
["LN02100650","AVAIL: Computers & Crates Ready","2006-06-20","2006-06-19"]
["LN03","LINAC MAGNETS AND SUPPORTS SUMMARY","2005-05-02","2007-08-06"]
["LN0301","BEND MAGNET (BX1_BC1) SUMMARY","2005-05-02","2006-07-24"]
["LN03010005","Create ICD & Update LCLS Database","2005-05-02","2005-05-09"]
["LN03010010","Review/Accept Reqmts, Update ICD & DB entries","2005-05-10","2005-05-23"]
["LN03010025","Develop Preliminary Dsn - Magnet Field Analysis","2005-05-02","2005-06-30"]
["LN03010030","Conduct Preliminary Design Review (PDR)","2005-07-01","2005-07-01"]
["LN03010040","Develop Final Design - Magnets","2005-07-05","2005-07-18"]
["LN03010050","Conduct Final Design Review (FDR)","2005-07-19","2005-07-20"]
["LN03010060","Develop Magnetic Measurement Plan","2005-07-21","2005-08-03"]
["LN03010065","COMP: Bend Magnet (BX1_BC1) Design","2005-08-04","2005-08-03"]
["LN03010070","Prep Bid Pak - Magnets","2005-08-04","2005-08-05"]
["LN03010080","RELEASE: RFP - BX1_BC1 Bend Magnet","2005-10-03","2005-09-30"]
["LN03010085","Vendors Prep Proposals - Magnets","2005-10-03","2005-10-28"]
["LN03010090","RCV: Proposals from Vendors - Magnet","2005-10-31","2005-10-28"]
["LN03010095","Evaluate Vendor Proposals - Magnets","2005-10-31","2005-11-11"]
["LN03010100","AWARD: Contract for Magnets","2005-11-14","2005-11-15"]
["LN03010105","Vendor Fab BX1 Magnets","2005-11-16","2006-06-15"]
["LN03010110","RCV: BX1 Magnets from Vendor","2006-06-16","2006-06-16"]
["LN03010120","QA BX1 Magnet","2006-06-19","2006-07-17"]
["LN03010235","Perform Magnet Pre-Instlation Qual","2006-07-18","2006-07-24"]
["LN03010240","AVAIL: BX1_BC1 Magnets Ready for Instl","2006-07-25","2006-07-24"]
["LN03010500","Procure Coils (2ea) - Bend Mag (BX1_BC1) SPARES","2006-10-03","2006-11-29"]
["LN03010550","RCV: Bend Magnet Coils (2ea) (BX1_BC1) SPARES","2006-11-30","2006-11-29"]
["LN0302","Bend Magnet (BX3_LTU) SUMMARY","2005-10-03","2007-07-24"]
["LN03020000","Define Magnet Requirements","2006-03-14","2006-03-20"]
["LN03020005","Create ICD & Update LCLS Database","2006-03-21","2006-04-03"]
["LN03020010","Review/Accept Reqmts, Update ICD & DB entries","2006-04-04","2006-04-05"]
["LN03020015","Develop Preliminary Design - Magnet","2006-04-06","2006-04-12"]
["LN03020025","Develop Preliminary Dsn - Magnet Field Analysis","2006-04-13","2006-04-26"]
["LN03020030","Conduct Preliminary Design Review (PDR)","2006-04-27","2006-04-27"]
["LN03020040","Develop Final Design - Magnets","2006-04-28","2006-05-01"]
["LN03020050","Conduct Final Design Review (FDR)","2006-05-02","2006-05-03"]
["LN03020060","Develop Magnetic Measurement Plan","2006-05-04","2006-05-04"]
["LN03020065","COMP: Bend Magnet (BX3_LTU) Design","2006-05-05","2006-05-04"]
["LN03020070","Prep Bid Pak - Magnets","2005-10-03","2006-02-15"]
["LN03020080","RELEASE: ESD - BX3_LTU_( ) Bend Magnet","2006-02-16","2006-02-15"]
["LN03020130","Procure Misc Materials - Magnets","2006-02-16","2006-04-27"]
["LN03020135","Disassemble Magnet","2006-04-28","2006-06-02"]
["LN03020145","Refurbish Magnet Coils","2006-06-05","2006-07-10"]
["LN03020150","Assemble Magnets","2006-07-11","2006-09-07"]
["LN03020160","Prep for and Paint Magnets (as required)","2006-09-08","2006-10-12"]
["LN03020165","Perform Magnet Fiducialization (as required)","2006-10-13","2006-10-12"]
["LN03020170","Perform QC & Inspection - Magnets","2006-10-13","2006-10-12"]
["LN03020175","Perform Magnetic Measurement (as required)","2006-10-13","2006-11-09"]
["LN03020235","Perform Magnet Pre-Instlation Qual","2006-11-10","2006-11-13"]
["LN03020240","AVAIL: BX3_LTU Magnets Ready for Instl","2006-11-14","2006-11-13"]
["LN03020245","Define Magnet Support Requirements","2006-03-21","2006-03-22"]
["LN03020250","Create ICD & Update LCLS Database","2006-03-23","2006-03-23"]
["LN03020255","Review/Accept Reqmts, Update ICD & DB entries","2006-03-24","2006-03-24"]
["LN03020260","Develop Preliminary Design - Magnet Supports","2006-03-27","2006-04-03"]
["LN03020270","Conduct Preliminary Design Review (PDR)","2006-04-04","2006-04-05"]
["LN03020280","Develop Final Design - Magnet Supports","2006-04-06","2006-04-11"]
["LN03020290","Conduct Final Design Review (FDR)","2006-04-12","2006-04-13"]
["LN03020300","COMP: Bend Magnet Supports (BX3_LTU) Design","2006-04-14","2006-04-13"]
["LN03020305","Prep Bid Pak - Magnet Supports","2006-04-14","2006-05-04"]
["LN03020315","RELEASE: RFP - Magnet Supports","2006-05-05","2006-05-04"]
["LN03020320","Vendors Prep Proposals - Magnet Supts","2006-05-05","2006-05-25"]
["LN03020325","RCV: Proposals from Vendors - Supts","2006-05-26","2006-05-25"]
["LN03020330","Evaluate Vendor Proposals - Supports","2006-05-26","2006-05-30"]
["LN03020335","AWARD: Contract for Supts","2006-05-31","2006-05-31"]
["LN03020340","Vendor Fab 1st Lot - Supts","2006-06-01","2007-06-01"]
["LN03020345","RCV: 1st Lot Magnet Supports from Vendor","2007-06-04","2007-06-04"]
["LN03020350","Vendor Fab Remaining Lot - Supts","2007-06-05","2007-06-04"]
["LN03020355","RCV: Remaining Magnet Supts from Vendor","2007-06-05","2007-06-04"]
["LN03020360","Procure Misc Materials - Magnet Supports","2006-04-14","2006-05-11"]
["LN03020365","Fabricate Magnet Supports","2006-05-12","2006-05-19"]
["LN03020370","Prep for, Clean & Plate Magnet Supts","2006-05-22","2006-05-19"]
["LN03020375","Prep for and Paint Magnet Supports (as required)","2006-05-22","2006-05-19"]
["LN03020380","Perform QC & Inspection on Magnets Supts","2006-05-22","2006-05-30"]
["LN03020385","Assemble Magnet Supports","2006-05-31","2006-07-03"]
["LN03020390","Hand-off to Pre-Instl Qual Testing","2007-06-05","2007-06-04"]
["LN03020395","Perform Pre-Installation Qualification - Support","2007-06-05","2007-07-24"]
["LN03020400","AVAIL: BX3_LTU Magnet Supts Ready for Instl","2007-07-25","2007-07-24"]
["LN03020500","Procure Coils (2ea) - Bend Mag (BX3_LTU) SPARES","2007-07-25","2007-09-19"]
["LN03020550","RCV: Bend Magnet Coils (2ea) (BX3_LTU) SPARES","2007-09-20","2007-09-19"]
["LN03020600","Receive & Review Safety Cover Requirements","2006-04-14","2006-04-20"]
["LN03020605","Develop Magnet Safety Cover Design","2006-04-21","2006-06-16"]
["LN03020610","COMP: Magnet Safety Design","2006-06-19","2006-06-16"]
["LN03020615","Procure Magnet Safety Cover Material","2006-10-03","2006-10-02"]
["LN03020620","RCV: Magnet Safety Cover Material","2006-10-03","2006-10-02"]
["LN03020625","Fab and Assemble New Magnet Safety Covers (0ea)","2006-10-03","2006-10-02"]
["LN03020630","REQD: Reusable Safety Covers for Refurbishment","2006-10-03","2006-10-02"]
["LN03020635","Refurbish Reusable Safety Covers (5ea)","2006-10-03","2007-04-09"]
["LN03020640","AVAIL: Magnet Safety Covers Ready for Instl","2007-04-10","2007-04-09"]
["LN0303","BEND MAGNET (BX2_BC2) SUMMARY","2005-05-02","2007-01-10"]
["LN03030005","Create ICD & Update LCLS Database","2005-05-02","2005-05-10"]
["LN03030010","Review/Accept Reqmts, Update ICD & DB entries","2005-05-04","2005-05-10"]
["LN03030025","Develop Preliminary Dsn - Magnet Field Analysis","2005-05-02","2005-09-09"]
["LN03030030","Conduct Preliminary Design Review (PDR)","2005-09-12","2005-09-12"]
["LN03030040","Develop Final Design - Magnets","2005-09-13","2005-09-26"]
["LN03030050","Conduct Final Design Review (FDR)","2005-09-27","2005-09-28"]
["LN03030060","Develop Magnetic Measurement Plan","2005-09-29","2005-10-12"]
["LN03030065","COMP: Bend Magnet (BX2_BC2) Design","2005-10-13","2005-10-12"]
["LN03030070","Prep Bid Pak - Magnets","2005-10-13","2005-10-14"]
["LN03030080","RELEASE: RFP - BX2_BC2 Bend Magnet","2005-10-17","2005-10-14"]
["LN03030085","Vendors Prep Proposals - Magnets","2005-10-17","2005-12-06"]
["LN03030090","RCV: Proposals from Vendors - Magnet","2005-12-07","2005-12-06"]
["LN03030095","Evaluate Vendor Proposals - Magnets","2005-12-07","2005-12-13"]
["LN03030100","AWARD: Contract for Magnets","2005-12-14","2005-12-15"]
["LN03030105","Vendor Fab 1st Lot - Magnets","2005-12-16","2007-01-05"]
["LN03030110","RCV: 1st Lot Magnets from Vendor","2007-01-08","2007-01-08"]
["LN03030115","Vendor Fab Remaining Lot - Magnets","2007-01-09","2007-01-08"]
["LN03030120","RCV: Remaining Magnets from Vendor","2007-01-09","2007-01-08"]
["LN03030235","Perform Magnet Pre-Instlation Qual","2007-01-09","2007-01-10"]
["LN03030240","AVAIL: BX2_BC2 Magnets Ready for Instl","2007-01-11","2007-01-10"]
["LN03030500","Procure Coils (2ea) - Bend Mag (BX2_BC2) SPARES","2007-01-11","2007-03-09"]
["LN03030550","RCV: Bend Magnet Coils (BX2_BC2) Spares Kit","2007-03-12","2007-03-09"]
["LN0304","BEND MAGNET (BY_LTU) SUMMARY","2005-10-03","2007-02-12"]
["LN03040000","Define Magnet Requirements","2005-10-13","2005-11-16"]
["LN03040005","Create ICD & Update LCLS Database","2005-11-17","2005-12-02"]
["LN03040010","Review/Accept Reqmts, Update ICD & DB entries","2005-12-05","2005-12-06"]
["LN03040015","Develop Preliminary Design - Magnet","2005-12-07","2006-01-04"]
["LN03040025","Develop Preliminary Dsn - Magnet Field Analysis","2006-01-05","2006-01-26"]
["LN03040030","Conduct Preliminary Design Review (PDR)","2006-01-27","2006-01-27"]
["LN03040040","Develop Final Design - Magnets","2006-01-30","2006-02-10"]
["LN03040050","Conduct Final Design Review (FDR)","2006-02-13","2006-02-14"]
["LN03040060","Develop Magnetic Measurement Plan","2006-02-15","2006-03-01"]
["LN03040065","COMP: Bend Magnet (BY_LTU) Design","2006-03-02","2006-03-01"]
["LN03040070","Prep Bid Pak - Magnets","2005-10-03","2005-10-14"]
["LN03040080","RELEASE: RFP - BY_LTU Bend Magnet","2005-10-17","2005-10-14"]
["LN03040085","Vendors Prep Proposals - Magnets","2005-10-17","2005-11-11"]
["LN03040090","RCV: Proposals from Vendors - Magnet","2005-11-14","2005-11-11"]
["LN03040095","Evaluate Vendor Proposals - Magnets","2005-11-14","2005-12-13"]
["LN03040100","AWARD: Contract for Magnets","2005-12-14","2005-12-15"]
["LN03040105","Vendor Fab 1st Lot - Magnets","2005-12-16","2007-01-05"]
["LN03040110","RCV: 1st Lot Magnets from Vendor","2007-01-08","2007-01-08"]
["LN03040115","Vendor Fab Remaining Lot - Magnets","2007-01-09","2007-01-08"]
["LN03040120","RCV: Remaining Magnets from Vendor","2007-01-09","2007-01-08"]
["LN03040230","Hand-off to Pre-Instl Qual Testing","2007-01-09","2007-01-08"]
["LN03040235","Perform Magnet Pre-Instlation Qual","2007-01-09","2007-02-06"]
["LN03040240","AVAIL: BY_LTU Magnets Ready for Instl","2007-02-07","2007-02-06"]
["LN03040245","Define Magnet Support Requirements","2005-11-17","2005-11-18"]
["LN03040250","Create ICD & Update LCLS Database","2005-11-21","2005-11-21"]
["LN03040255","Review/Accept Reqmts, Update ICD & DB entries","2005-11-22","2005-11-22"]
["LN03040260","Develop Preliminary Design - Magnet Supports","2005-11-23","2005-12-02"]
["LN03040270","Conduct Preliminary Design Review (PDR)","2005-12-05","2005-12-06"]
["LN03040280","Develop Final Design - Magnet Supports","2005-12-07","2005-12-12"]
["LN03040290","Conduct Final Design Review (FDR)","2005-12-13","2005-12-14"]
["LN03040300","COMP: Bend Magnet Supports (BY_LTU) Design","2005-12-15","2005-12-14"]
["LN03040305","Prep Bid Pak - Magnet Supports","2005-10-03","2005-10-03"]
["LN03040315","RELEASE: RFP - Magnet Supports","2005-10-17","2005-10-14"]
["LN03040320","Vendors Prep Proposals - Magnet Supts","2005-10-17","2005-10-17"]
["LN03040325","RCV: Proposals from Vendors - Supts","2005-10-18","2005-10-17"]
["LN03040330","Evaluate Vendor Proposals - Supports","2005-10-18","2005-10-18"]
["LN03040335","AWARD: Contract for Supts","2005-12-16","2005-12-16"]
["LN03040340","Vendor Fab 1st Lot - Supts","2006-01-03","2006-01-31"]
["LN03040345","RCV: 1st Lot Magnet Supports from Vendor","2007-01-09","2007-01-09"]
["LN03040350","Vendor Fab Remaining Lot - Supts","2007-01-10","2007-01-09"]
["LN03040355","RCV: Remaining Magnet Supts from Vendor","2007-01-10","2007-01-09"]
["LN03040360","Procure Misc Materials - Magnet Supports","2005-12-15","2006-01-27"]
["LN03040365","Fabricate Magnet Supports","2006-01-30","2006-02-06"]
["LN03040370","Prep for, Clean & Plate Magnet Supts","2006-02-07","2006-02-06"]
["LN03040375","Prep for and Paint Magnet Supports (as required)","2006-02-07","2006-02-06"]
["LN03040380","Perform QC & Inspection on Magnets Supts","2007-01-10","2007-01-18"]
["LN03040385","Assemble Magnet Supports","2007-01-19","2007-02-08"]
["LN03040390","Hand-off to Pre-Instl Qual Testing","2007-02-09","2007-02-08"]
["LN03040395","Perform Pre-Installation Qualification - Support","2007-02-09","2007-02-12"]
["LN03040400","AVAIL: BY_LTU Magnet Supts Ready for Instl","2007-02-13","2007-02-12"]
["LN03040500","Procure Coil (1ea) - Bend Mag (BY_LTU) SPARES","2007-02-13","2007-04-10"]
["LN03040550","RCV: Bend Magnet Coil (1ea) (BY_LTU) SPARES","2007-04-11","2007-04-10"]
["LN0305","QUAD MAGNET (Quad_LTU) SUMMARY","2005-10-03","2007-07-05"]
["LN03050000","Define Magnet Requirements","2006-05-05","2006-06-09"]
["LN03050005","Create ICD & Update LCLS Database","2006-06-12","2006-06-23"]
["LN03050010","Review/Accept Reqmts, Update ICD & DB entries","2006-06-26","2006-06-27"]
["LN03050015","Develop Preliminary Design - Magnet","2006-06-28","2006-06-29"]
["LN03050025","Develop Preliminary Dsn - Magnet Field Analysis","2006-06-30","2006-07-03"]
["LN03050030","Conduct Preliminary Design Review (PDR)","2006-07-05","2006-07-05"]
["LN03050040","Develop Final Design - Magnets","2006-07-06","2006-07-19"]
["LN03050050","Conduct Final Design Review (FDR)","2006-07-20","2006-07-21"]
["LN03050060","Develop Magnetic Measurement Plan","2006-07-24","2006-07-25"]
["LN03050065","COMP: Quad Magnet (Quad_LTU) Design","2006-07-26","2006-07-25"]
["LN03050070","Prep Bid Pak - Magnets","2005-10-03","2005-10-14"]
["LN03050080","RELEASE: RFP - Quad_LTU Magnet","2005-10-17","2005-10-14"]
["LN03050085","Vendors Prep Proposals - Magnets","2005-10-17","2005-11-11"]
["LN03050090","RCV: Proposals from Vendors - Magnet","2005-11-14","2005-11-11"]
["LN03050095","Evaluate Vendor Proposals - Magnets","2005-11-14","2005-12-13"]
["LN03050100","AWARD: Contract for Magnets","2005-12-14","2005-12-15"]
["LN03050105","Vendor Fab 1st Lot - Magnets","2005-12-16","2007-06-01"]
["LN03050110","RCV: 1st Lot Magnets from Vendor","2007-06-04","2007-06-04"]
["LN03050115","Vendor Fab Remaining Lot - Magnets","2007-06-05","2007-06-04"]
["LN03050120","RCV: Remaining Magnets from Vendor","2007-06-05","2007-06-04"]
["LN03050125","Hand-off to Pre-Instl Qual Testing","2007-06-05","2007-06-04"]
["LN03050130","Procure Misc Materials - Magnets","2005-12-16","2007-01-03"]
["LN03050135","Disassemble Magnet","2007-01-04","2007-02-01"]
["LN03050145","Refurbish Magnet Coils","2007-02-02","2007-03-02"]
["LN03050150","Assemble Magnets","2007-03-05","2007-03-30"]
["LN03050160","Prep for and Paint Magnets (as required)","2007-04-02","2007-04-27"]
["LN03050165","Perform Magnet Fiducialization (as required)","2007-04-30","2007-05-04"]
["LN03050170","Perform QC & Inspection - Magnets","2007-05-07","2007-05-11"]
["LN03050175","Perform Magnetic Measurement (as required)","2007-05-14","2007-05-25"]
["LN03050235","Perform Magnet Pre-Instlation Qual","2007-06-05","2007-06-06"]
["LN03050240","AVAIL: Quad_LTU Magnets Ready for Instl","2007-06-07","2007-06-06"]
["LN03050245","Define Magnet Support Requirements","2006-06-12","2006-06-13"]
["LN03050250","Create ICD & Update LCLS Database","2006-06-14","2006-06-15"]
["LN03050255","Review/Accept Reqmts, Update ICD & DB entries","2006-06-16","2006-06-19"]
["LN03050260","Develop Preliminary Design - Magnet Supports","2006-06-20","2006-06-27"]
["LN03050270","Conduct Preliminary Design Review (PDR)","2006-06-28","2006-06-29"]
["LN03050280","Develop Final Design - Magnet Supports","2006-06-30","2006-07-06"]
["LN03050290","Conduct Final Design Review (FDR)","2006-07-07","2006-07-10"]
["LN03050300","COMP: Quad Magnet Supports (Quad_LTU) Design","2006-07-11","2006-07-10"]
["LN03050305","Prep Bid Pak - Magnet Supports","2005-10-03","2005-10-14"]
["LN03050315","RELEASE: RFP - Magnet Supports","2005-10-17","2005-10-14"]
["LN03050320","Vendors Prep Proposals - Magnet Supts","2005-10-17","2005-11-11"]
["LN03050325","RCV: Proposals from Vendors - Supts","2005-11-14","2005-11-11"]
["LN03050330","Evaluate Vendor Proposals - Supports","2005-11-14","2005-12-13"]
["LN03050335","AWARD: Contract for Supts","2005-12-14","2005-12-15"]
["LN03050340","Vendor Fab 1st Lot - Supts","2005-12-16","2007-06-01"]
["LN03050345","RCV: 1st Lot Magnet Supports from Vendor","2007-06-04","2007-06-04"]
["LN03050350","Vendor Fab Remaining Lot - Supts","2007-06-05","2007-06-04"]
["LN03050355","RCV: Remaining Magnet Supts from Vendor","2007-06-05","2007-06-04"]
["LN03050360","Procure Misc Materials - Magnet Supports","2006-10-03","2006-10-30"]
["LN03050365","Fabricate Magnet Supports","2006-10-31","2006-12-13"]
["LN03050370","Prep for, Clean & Plate Magnet Supts","2006-12-14","2006-12-13"]
["LN03050375","Prep for and Paint Magnet Supports (as required)","2006-12-14","2006-12-13"]
["LN03050380","Perform QC & Inspection on Magnets Supts","2006-12-14","2007-02-09"]
["LN03050385","Assemble Magnet Supports","2007-02-12","2007-05-09"]
["LN03050390","Hand-off to Pre-Instl Qual Testing","2007-05-10","2007-05-09"]
["LN03050395","Perform Pre-Installation Qualification - Support","2007-06-05","2007-06-12"]
["LN03050400","AVAIL: Quad_LTU Magnet Supts Ready for Instl","2007-06-13","2007-06-12"]
["LN03050500","Procure Coil (4ea) - Quad Mag (Quad_LTU) SPARES","2007-06-13","2007-08-08"]
["LN03050550","RCV: Quad Magnet Coil (4ea) (Quad_LTU) SPARES","2007-08-09","2007-08-08"]
["LN03050600","Receive & Review Safety Cover Requirements","2006-06-12","2006-06-09"]
["LN03050605","Develop Magnet Safety Cover Design","2006-06-12","2006-08-07"]
["LN03050610","COMP: Magnet Safety Design","2006-08-08","2006-08-07"]
["LN03050615","Prep Bid Pak - Magnet Safety Covers","2006-08-08","2006-08-14"]
["LN03050620","RELEASE: RFP - Magnet Safety Covers","2006-08-15","2006-08-14"]
["LN03050625","Vendors Prep Proposals - Magnet Safety Covers","2006-08-15","2006-08-28"]
["LN03050630","RCV: Vendor Proposals - Magnet Safety Covers","2006-08-29","2006-08-28"]
["LN03050635","Evaluate Vendor Proposals","2006-08-29","2006-09-05"]
["LN03050700","AWARD: Contract - Magnet Safety Covers","2006-10-03","2006-10-03"]
["LN03050705","Vendor Fab & Assy - Magnet Safety Cover (15ea)","2006-10-04","2007-03-13"]
["LN03050710","RCV: Magnet Safety Cover Material","2007-03-14","2007-03-13"]
["LN03050715","Fab and Assemble New Magnet Safety Covers (0ea)","2007-03-14","2007-03-13"]
["LN03050720","REQD: Reusable Safety Covers for Refurbishment","2007-03-14","2007-03-13"]
["LN03050725","Refurbish Reusable Safety Covers (25ea)","2007-03-14","2007-07-05"]
["LN03050730","AVAIL: Magnet Safety Covers Ready for Instl","2007-07-06","2007-07-05"]
["LN0307","QUAD MAGNET (QE_ ) SUMMARY","2005-05-02","2007-08-02"]
["LN03070005","Create ICD & Update LCLS Database","2005-05-02","2005-05-13"]
["LN03070010","Review/Accept Reqmts, Update ICD & DB entries","2005-05-16","2005-05-17"]
["LN03070060","Develop Magnetic Measurement Plan","2005-05-02","2005-05-20"]
["LN03070065","COMP: Quad Magnet (QE_ Quad) Design","2005-05-23","2005-05-20"]
["LN03070180","Procure Misc Materials - Magnets","2005-10-03","2005-11-11"]
["LN03070185","Fab Tooling","2005-11-14","2006-01-04"]
["LN03070190","Fab Magnet Core","2005-11-14","2005-12-13"]
["LN03070195","Fab Magnet Coils","2005-11-14","2007-01-05"]
["LN03070205","Prep for and Paint Magnets (as required)","2007-01-08","2007-01-22"]
["LN03070210","Assemble Magnets","2007-01-23","2007-02-20"]
["LN03070215","Perform Magnet Fiducialization (as required)","2007-02-21","2007-03-06"]
["LN03070220","Perform QC & Inspection - Magnets","2007-03-07","2007-03-20"]
["LN03070225","Perform Magnetic Measurement (as required)","2007-03-21","2007-04-03"]
["LN03070230","Hand-off to Pre-Instl Qual Testing","2007-04-04","2007-04-03"]
["LN03070235","Perform Magnet Pre-Instlation Qual","2007-04-04","2007-08-02"]
["LN03070240","AVAIL: QE_ Quad Magnet Ready for BC1 Instl","2005-05-02","2005-04-29"]
["LN03070242","AVAIL: QE_ Quad Magnet Ready for BC2 Instl","2007-08-03","2007-08-02"]
["LN03070245","Define Magnet Support Requirements","2006-09-12","2006-09-13"]
["LN03070250","Create ICD & Update LCLS Database","2006-09-14","2006-09-13"]
["LN03070255","Review/Accept Reqmts, Update ICD & DB entries","2006-09-14","2006-09-14"]
["LN03070260","Develop Preliminary Design - Magnet Supports","2006-09-15","2006-09-15"]
["LN03070270","Conduct Preliminary Design Review (PDR)","2006-09-18","2006-09-18"]
["LN03070280","Develop Final Design - Magnet Supports","2006-09-19","2006-09-19"]
["LN03070290","Conduct Final Design Review (FDR)","2006-09-20","2006-09-20"]
["LN03070300","COMP: Quad Magnet Supports (QE_ Quad) Design","2006-09-21","2006-09-20"]
["LN03070305","Prep Bid Pak - Magnet Supports","2006-09-21","2006-09-21"]
["LN03070315","RELEASE: RFP - Magnet Supports","2006-09-22","2006-09-21"]
["LN03070320","Vendors Prep Proposals - Magnet Supts","2006-09-22","2006-09-22"]
["LN03070325","RCV: Proposals from Vendors - Supts","2006-09-25","2006-09-22"]
["LN03070330","Evaluate Vendor Proposals - Supports","2006-09-25","2006-09-22"]
["LN03070335","AWARD: Contract for Supts","2006-09-25","2006-09-25"]
["LN03070340","Vendor Fab 1st Lot - Supts","2006-09-26","2006-09-25"]
["LN03070345","RCV: 1st Lot Magnet Supports from Vendor","2006-09-26","2006-09-25"]
["LN03070350","Vendor Fab Remaining Lot - Supts","2006-09-26","2006-09-25"]
["LN03070355","RCV: Remaining Magnet Supts from Vendor","2006-09-26","2006-09-25"]
["LN03070360","Procure Misc Materials - Magnet Supports","2006-09-21","2006-09-20"]
["LN03070365","Fabricate Magnet Supports","2006-09-21","2006-09-20"]
["LN03070370","Prep for, Clean & Plate Magnet Supts","2006-09-21","2006-09-20"]
["LN03070375","Prep for and Paint Magnet Supports (as required)","2006-09-21","2006-09-20"]
["LN03070380","Perform QC & Inspection on Magnets Supts","2006-09-21","2006-09-20"]
["LN03070385","Assemble Magnet Supports","2006-09-21","2006-09-20"]
["LN03070390","Hand-off to Pre-Instl Qual Testing","2006-09-21","2006-09-20"]
["LN03070395","Perform Pre-Installation Qualification - Support","2006-09-26","2006-09-25"]
["LN03070400","AVAIL: QE_ Quad Magnet Supts Ready for BC1 Instl","2006-09-26","2006-09-25"]
["LN03070402","AVAIL: QE_ Quad Magnet Supts Ready for BC2 Instl","2006-09-26","2006-09-25"]
["LN0308","CORRECTOR BEND MAGNET (Linac Type 4) SUMMARY","2005-05-02","2006-07-26"]
["LN03080005","Create ICD & Update LCLS Database","2005-05-02","2005-05-13"]
["LN03080010","Review/Accept Reqmts, Update ICD & DB entries","2005-05-16","2005-05-17"]
["LN03080015","Develop Preliminary Design - Magnet","2005-05-18","2005-05-18"]
["LN03080025","Develop Preliminary Dsn - Magnet Field Analysis","2005-05-19","2005-05-19"]
["LN03080030","Conduct Preliminary Design Review (PDR)","2005-05-20","2005-05-20"]
["LN03080040","Develop Final Design - Magnets","2005-05-23","2005-05-23"]
["LN03080050","Conduct Final Design Review (FDR)","2005-05-24","2005-05-25"]
["LN03080060","Develop Magnetic Measurement Plan","2005-05-26","2005-05-27"]
["LN03080065","COMP: Corrector Bend Magnet (Type 4) Design","2005-05-31","2005-05-27"]
["LN03080070","Prep Bid Pak - Magnets","2005-10-03","2005-11-15"]
["LN03080080","RELEASE: RFP - Linac Type 4 Corrector Bend Magne","2005-11-16","2005-11-15"]
["LN03080085","Vendors Prep Proposals - Magnets","2005-11-16","2005-11-28"]
["LN03080090","RCV: Proposals from Vendors - Magnet","2005-11-29","2005-11-28"]
["LN03080095","Evaluate Vendor Proposals - Magnets","2005-11-29","2005-12-12"]
["LN03080100","AWARD: Contract for Magnets","2005-12-13","2005-12-15"]
["LN03080105","Vendor Fab 1st Lot - Magnets","2005-12-16","2006-06-01"]
["LN03080110","RCV: 1st Lot Magnets from Vendor","2006-06-02","2006-06-02"]
["LN03080115","Vendor Fab Remaining Lot - Magnets","2006-06-05","2006-06-02"]
["LN03080120","RCV: Remaining Magnets from Vendor","2006-06-05","2006-06-02"]
["LN03080125","Hand-off to Pre-Instl Qual Testing","2006-06-05","2006-06-02"]
["LN03080130","Procure Misc Materials - Magnets","2005-12-16","2006-01-30"]
["LN03080135","Disassemble Magnet","2006-01-31","2006-01-31"]
["LN03080145","Refurbish Magnet Coils","2006-02-01","2006-02-09"]
["LN03080150","Assemble Magnets","2006-02-10","2006-06-01"]
["LN03080160","Prep for and Paint Magnets (as required)","2006-06-02","2006-06-01"]
["LN03080165","Perform Magnet Fiducialization (as required)","2006-06-02","2006-06-01"]
["LN03080170","Perform QC & Inspection - Magnets","2006-06-02","2006-06-01"]
["LN03080175","Perform Magnetic Measurement (as required)","2006-06-02","2006-06-01"]
["LN03080180","Procure Misc Materials - Magnets","2005-12-16","2005-12-15"]
["LN03080185","Fab Tooling","2005-12-16","2005-12-15"]
["LN03080190","Fab Magnet Core","2005-12-16","2005-12-16"]
["LN03080195","Fab Magnet Coils","2006-01-03","2005-12-16"]
["LN03080205","Prep for and Paint Magnets (as required)","2006-01-03","2005-12-16"]
["LN03080210","Assemble Magnets","2006-01-03","2006-06-01"]
["LN03080215","Perform Magnet Fiducialization (as required)","2006-06-02","2006-06-01"]
["LN03080220","Perform QC & Inspection - Magnets","2006-06-02","2006-06-01"]
["LN03080225","Perform Magnetic Measurement (as required)","2006-06-02","2006-06-01"]
["LN03080230","Hand-off to Pre-Instl Qual Testing","2006-06-02","2006-06-01"]
["LN03080235","Perform Magnet Pre-Instlation Qual","2006-06-05","2006-07-03"]
["LN03080240","AVAIL: Type 4 Corr Bend Mag Ready for L01 Instl","2006-07-05","2006-07-03"]
["LN03080241","AVAIL: Type 4 Corr Bend Mag Ready for BC1 Instl","2006-07-05","2006-07-03"]
["LN03080242","AVAIL: Type 4 Corr Bend Mag Ready for L03 Instl","2006-07-05","2006-07-03"]
["LN03080605","Develop Magnet Safety Cover Design","2006-03-01","2006-03-28"]
["LN03080610","COMP: Magnet Safety Design","2006-03-29","2006-03-28"]
["LN03080615","Procure Magnet Safety Cover (42ea)","2006-03-29","2006-07-26"]
["LN03080620","RCV: Magnet Safety Cover (42ea)","2006-07-27","2006-07-26"]
["LN03080625","Fab and Assemble New Magnet Safety Covers (0ea)","2006-07-27","2006-07-26"]
["LN03080630","REQD: Reusable Safety Covers for Refurbishment","2006-07-27","2006-07-26"]
["LN03080635","Refurbish Reusable Safety Covers (0ea)","2006-07-27","2006-07-26"]
["LN03080640","AVAIL: Magnet Safety Covers Ready for Instl","2006-07-27","2006-07-26"]
["LN0309","BEND MAGNET (BYD_LTU) SUMMARY","2005-10-03","2007-08-01"]
["LN03090000","Define Magnet Requirements","2006-10-03","2006-11-06"]
["LN03090005","Create ICD & Update LCLS Database","2006-11-07","2006-11-20"]
["LN03090010","Review/Accept Reqmts, Update ICD & DB entries","2006-11-21","2006-11-22"]
["LN03090015","Develop Preliminary Design - Magnet","2006-11-27","2006-12-08"]
["LN03090025","Develop Preliminary Dsn - Magnet Field Analysis","2006-12-11","2007-01-16"]
["LN03090030","Conduct Preliminary Design Review (PDR)","2007-01-17","2007-01-17"]
["LN03090040","Develop Final Design - Magnets","2007-01-18","2007-01-31"]
["LN03090050","Conduct Final Design Review (FDR)","2007-02-01","2007-02-02"]
["LN03090060","Develop Magnetic Measurement Plan","2007-02-05","2007-02-16"]
["LN03090065","COMP: Quad Magnet (BYD_LTU) Design","2007-02-20","2007-02-16"]
["LN03090070","Prep Bid Pak - Magnets","2005-10-03","2005-10-14"]
["LN03090080","RELEASE: RFP -BYD_LTU Bend Magnet","2005-10-17","2005-10-14"]
["LN03090085","Vendors Prep Proposals - Magnets","2005-10-17","2005-11-11"]
["LN03090090","RCV: Proposals from Vendors - Magnet","2005-11-14","2005-11-11"]
["LN03090095","Evaluate Vendor Proposals - Magnets","2005-11-14","2005-12-13"]
["LN03090100","AWARD: Contract for Magnets","2005-12-14","2005-12-15"]
["LN03090105","Vendor Fab 1st Lot - Magnets","2005-12-16","2007-01-05"]
["LN03090110","RCV: 1st Lot Magnets from Vendor","2007-01-08","2007-01-08"]
["LN03090115","Vendor Fab Remaining Lot - Magnets","2007-01-09","2007-01-08"]
["LN03090120","RCV: Remaining Magnets from Vendor","2007-01-09","2007-01-08"]
["LN03090125","Hand-off to Pre-Instl Qual Testing","2007-01-09","2007-01-08"]
["LN03090130","Procure Misc Materials - Magnets","2005-12-16","2005-12-15"]
["LN03090135","Disassemble Magnet","2005-12-16","2005-12-16"]
["LN03090145","Refurbish Magnet Coils","2006-01-03","2006-01-03"]
["LN03090150","Assemble Magnets","2006-01-04","2007-01-05"]
["LN03090160","Prep for and Paint Magnets (as required)","2007-01-08","2007-01-05"]
["LN03090165","Perform Magnet Fiducialization (as required)","2007-01-08","2007-01-05"]
["LN03090170","Perform QC & Inspection - Magnets","2007-01-08","2007-01-05"]
["LN03090175","Perform Magnetic Measurement (as required)","2007-01-08","2007-01-05"]
["LN03090180","Procure Misc Materials - Magnets","2006-10-03","2006-10-02"]
["LN03090185","Fab Tooling","2006-10-03","2006-10-02"]
["LN03090190","Fab Magnet Core","2006-10-03","2006-10-02"]
["LN03090195","Fab Magnet Coils","2006-10-03","2006-10-02"]
["LN03090205","Prep for and Paint Magnets (as required)","2006-10-03","2006-10-02"]
["LN03090210","Assemble Magnets","2006-10-03","2006-10-02"]
["LN03090215","Perform Magnet Fiducialization (as required)","2006-10-03","2006-10-02"]
["LN03090220","Perform QC & Inspection - Magnets","2006-10-03","2006-10-02"]
["LN03090225","Perform Magnetic Measurement (as required)","2006-10-03","2006-10-02"]
["LN03090230","Hand-off to Pre-Instl Qual Testing","2007-01-08","2007-01-05"]
["LN03090235","Perform Magnet Pre-Instlation Qual","2007-01-09","2007-01-11"]
["LN03090240","AVAIL: BYD_LTU Bend Magnet Ready for Instl","2007-01-12","2007-01-11"]
["LN03090245","Define Magnet Support Requirements","2005-10-03","2005-10-05"]
["LN03090250","Create ICD & Update LCLS Database","2005-10-06","2005-10-06"]
["LN03090255","Review/Accept Reqmts, Update ICD & DB entries","2005-10-07","2005-10-07"]
["LN03090260","Develop Preliminary Design - Magnet Supports","2005-10-10","2005-10-10"]
["LN03090270","Conduct Preliminary Design Review (PDR)","2005-10-11","2005-10-11"]
["LN03090280","Develop Final Design - Magnet Supports","2005-10-12","2005-10-12"]
["LN03090290","Conduct Final Design Review (FDR)","2005-10-13","2005-10-13"]
["LN03090300","COMP: Bend Magnet Support (BYD_LTU ) Design","2005-10-14","2005-10-13"]
["LN03090305","Prep Bid Pak - Magnet Supports","2005-10-14","2005-10-14"]
["LN03090315","RELEASE: RFP - Magnet Supports","2005-10-17","2005-10-14"]
["LN03090320","Vendors Prep Proposals - Magnet Supts","2005-10-17","2005-11-11"]
["LN03090325","RCV: Proposals from Vendors - Supts","2005-11-14","2005-11-11"]
["LN03090330","Evaluate Vendor Proposals - Supports","2005-11-14","2005-12-13"]
["LN03090335","AWARD: Contract for Supts","2005-12-14","2005-12-15"]
["LN03090340","Vendor Fab 1st Lot - Supts","2005-12-16","2007-01-05"]
["LN03090345","RCV: 1st Lot Magnet Supports from Vendor","2007-01-08","2007-01-08"]
["LN03090350","Vendor Fab Remaining Lot - Supts","2007-01-09","2007-01-08"]
["LN03090355","RCV: Remaining Magnet Supts from Vendor","2007-01-09","2007-01-08"]
["LN03090360","Procure Misc Materials - Magnet Supports","2005-10-14","2005-11-10"]
["LN03090365","Fabricate Magnet Supports","2005-11-11","2005-11-23"]
["LN03090370","Prep for, Clean & Plate Magnet Supts","2005-11-28","2005-11-23"]
["LN03090375","Prep for and Paint Magnet Supports (as required)","2005-11-28","2005-11-23"]
["LN03090380","Perform QC & Inspection on Magnets Supts","2005-11-28","2005-12-08"]
["LN03090385","Assemble Magnet Supports","2005-12-09","2007-01-05"]
["LN03090390","Hand-off to Pre-Instl Qual Testing","2007-01-08","2007-01-05"]
["LN03090395","Perform Pre-Installation Qualification - Support","2007-01-09","2007-08-01"]
["LN03090400","AVAIL: BYD_LTU  Magnet Supts Ready for Instl","2007-08-02","2007-08-01"]
["LN03090500","Procure Coil (2ea) - Bend Mag (BYD_LTU) SPARES","2006-10-03","2006-11-29"]
["LN03090550","RCV: Bend Magnet Coil (2ea) (BYD_LTU) SPARES","2006-11-30","2006-11-29"]
["LN0310","QUAD MAGNET (QA_ ) SUMMARY","2005-06-01","2006-08-30"]
["LN03100000","Define Magnet Requirements","2005-06-01","2005-06-07"]
["LN03100005","Create ICD & Update LCLS Database","2005-06-08","2005-06-21"]
["LN03100010","Review/Accept Reqmts, Update ICD & DB entries","2005-06-22","2005-06-23"]
["LN03100015","Develop Preliminary Design - Magnet","2005-06-24","2005-07-08"]
["LN03100025","Develop Preliminary Dsn - Magnet Field Analysis","2005-07-11","2005-07-11"]
["LN03100030","Conduct Preliminary Design Review (PDR)","2005-07-12","2005-07-11"]
["LN03100040","Develop Final Design - Magnets","2005-07-12","2005-07-25"]
["LN03100050","Conduct Final Design Review (FDR)","2005-07-26","2005-07-27"]
["LN03100060","Develop Magnetic Measurement Plan","2005-07-28","2005-07-29"]
["LN03100065","COMP: Quad Magnet (QA_ Quad) Design","2005-08-01","2005-07-29"]
["LN03100070","Prep Bid Pak - Magnets","2005-08-01","2005-11-01"]
["LN03100080","RELEASE: RFP - QA_ Quad Magnet","2005-11-02","2005-11-01"]
["LN03100085","Vendors Prep Proposals - Magnets","2005-11-02","2005-11-22"]
["LN03100090","RCV: Proposals from Vendors - Magnet","2005-11-23","2005-11-22"]
["LN03100095","Evaluate Vendor Proposals - Magnets","2005-11-23","2005-12-15"]
["LN03100100","AWARD: Contract for Magnets","2005-12-16","2005-12-16"]
["LN03100105","Vendor Fab 1st Lot - Magnets","2006-01-03","2006-06-01"]
["LN03100110","RCV: 1st Lot Magnets from Vendor","2006-06-02","2006-06-01"]
["LN03100115","Vendor Fab Remaining Lot - Magnets","2006-06-02","2006-06-01"]
["LN03100120","RCV: Remaining Magnets from Vendor","2006-06-02","2006-06-01"]
["LN03100125","Hand-off to Pre-Instl Qual Testing","2006-06-02","2006-06-01"]
["LN03100130","Procure Misc Materials - Magnets","2006-01-03","2006-01-31"]
["LN03100135","Disassemble Magnet","2006-02-01","2006-02-01"]
["LN03100145","Refurbish Magnet Coils","2006-02-02","2006-02-02"]
["LN03100150","Assemble Magnets","2006-02-03","2006-05-30"]
["LN03100160","Prep for and Paint Magnets (as required)","2006-05-31","2006-05-30"]
["LN03100165","Perform Magnet Fiducialization (as required)","2006-05-31","2006-05-30"]
["LN03100170","Perform QC & Inspection - Magnets","2006-05-31","2006-05-30"]
["LN03100175","Perform Magnetic Measurement (as required)","2006-05-31","2006-06-27"]
["LN03100230","Hand-off to Pre-Instl Qual Testing","2006-06-28","2006-06-27"]
["LN03100235","Perform Magnet Pre-Instlation Qual","2006-06-28","2006-08-30"]
["LN03100240","AVAIL: QA_ Quad Magnets Ready for BC1 Instl","2006-08-31","2006-08-30"]
["LN03100241","AVAIL: QA_ Quad Magnets Ready for BC2 Instl","2006-08-31","2006-08-30"]
["LN03100245","Define Magnet Support Requirements","2005-10-03","2005-10-04"]
["LN03100250","Create ICD & Update LCLS Database","2005-10-05","2005-10-05"]
["LN03100255","Review/Accept Reqmts, Update ICD & DB entries","2005-10-06","2005-10-06"]
["LN03100260","Develop Preliminary Design - Magnet Supports","2005-10-07","2005-10-10"]
["LN03100270","Conduct Preliminary Design Review (PDR)","2005-10-11","2005-10-11"]
["LN03100280","Develop Final Design - Magnet Supports","2005-10-12","2005-10-13"]
["LN03100290","Conduct Final Design Review (FDR)","2005-10-14","2005-10-18"]
["LN03100300","COMP: Quad Magnet Supports (QA_ Quad) Design","2005-10-19","2005-10-18"]
["LN03100305","Prep Bid Pak - Magnet Supports","2005-10-19","2005-11-01"]
["LN03100315","RELEASE: RFP - Magnet Supports","2005-11-02","2005-11-01"]
["LN03100320","Vendors Prep Proposals - Magnet Supts","2005-11-02","2005-11-22"]
["LN03100325","RCV: Proposals from Vendors - Supts","2005-11-23","2005-11-22"]
["LN03100330","Evaluate Vendor Proposals - Supports","2005-11-23","2005-12-15"]
["LN03100335","AWARD: Contract for Supts","2005-12-16","2005-12-16"]
["LN03100340","Vendor Fab 1st Lot - Supts","2006-01-03","2006-06-01"]
["LN03100345","RCV: 1st Lot Magnet Supports from Vendor","2006-06-02","2006-06-01"]
["LN03100350","Vendor Fab Remaining Lot - Supts","2006-06-02","2006-06-01"]
["LN03100355","RCV: Remaining Magnet Supts from Vendor","2006-06-02","2006-06-01"]
["LN03100360","Procure Misc Materials - Magnet Supports","2005-10-19","2005-11-15"]
["LN03100365","Fabricate Magnet Supports","2005-11-16","2005-11-15"]
["LN03100370","Prep for, Clean & Plate Magnet Supts","2005-11-16","2005-11-15"]
["LN03100375","Prep for and Paint Magnet Supports (as required)","2005-11-16","2005-11-15"]
["LN03100380","Perform QC & Inspection on Magnets Supts","2005-11-16","2005-11-15"]
["LN03100385","Assemble Magnet Supports","2005-11-16","2006-06-01"]
["LN03100390","Hand-off to Pre-Instl Qual Testing","2006-06-02","2006-06-01"]
["LN03100395","Perform Pre-Installation Qualification - Support","2006-06-02","2006-08-04"]
["LN03100400","AVAIL: QA_ Quad Magnet Supts Ready for BC1 Instl","2006-08-07","2006-08-04"]
["LN03100401","AVAIL: QA_ Quad Magnet Supts Ready for BC2 Instl","2006-08-07","2006-08-04"]
["LN0311","BEND MAGNET (BYPM_LTU) SUMMARY","2005-10-03","2007-07-26"]
["LN03110000","Define Magnet Requirements","2005-10-03","2005-11-04"]
["LN03110005","Create ICD & Update LCLS Database","2005-11-07","2005-11-18"]
["LN03110010","Review/Accept Reqmts, Update ICD & DB entries","2005-11-21","2005-11-22"]
["LN03110015","Develop Preliminary Design - Magnet","2005-11-23","2005-12-08"]
["LN03110025","Develop Preliminary Dsn - Magnet Field Analysis","2005-12-09","2006-01-13"]
["LN03110030","Conduct Preliminary Design Review (PDR)","2006-01-17","2006-01-17"]
["LN03110040","Develop Final Design - Magnets","2006-01-18","2006-01-31"]
["LN03110050","Conduct Final Design Review (FDR)","2006-02-01","2006-02-02"]
["LN03110060","Develop Magnetic Measurement Plan","2006-02-03","2006-02-16"]
["LN03110065","COMP: Bend Magnet (BYMP_LTU) Design","2006-02-17","2006-02-16"]
["LN03110070","Prep Bid Pak - Magnets","2006-04-03","2006-04-03"]
["LN03110080","RELEASE: RFP - BYMP_LTU Bend Magnet","2006-04-04","2006-04-03"]
["LN03110085","Vendors Prep Proposals - Magnets","2006-04-04","2006-04-24"]
["LN03110090","RCV: Proposals from Vendors - Magnet","2006-04-25","2006-04-24"]
["LN03110095","Evaluate Vendor Proposals - Magnets","2006-04-25","2006-05-15"]
["LN03110100","AWARD: Contract for Magnets","2006-05-16","2006-05-16"]
["LN03110105","Vendor Fab 1st Lot - Magnets","2006-05-17","2007-06-01"]
["LN03110110","RCV: 1st Lot Magnets from Vendor","2007-06-04","2007-06-01"]
["LN03110115","Vendor Fab Remaining Lot - Magnets","2007-06-04","2007-06-01"]
["LN03110120","RCV: Remaining Magnets from Vendor","2007-06-04","2007-06-01"]
["LN03110125","Hand-off to Pre-Instl Qual Testing","2007-06-04","2007-06-01"]
["LN03110170","Prep Bid Pak - Misc Materials - Magnets","2006-03-28","2006-04-03"]
["LN03110172","RELEASE: RFP  - Misc Materials - Magnets","2006-04-04","2006-04-03"]
["LN03110174","Vendors Prep Proposals - Misc Mtrls - Magnets","2006-04-04","2006-04-24"]
["LN03110176","RCV: Vendor Proposals - Misc Materials - Magnets","2006-04-25","2006-04-24"]
["LN03110178","Evaluate Vendor Proposals - Misc Mtrls - Magnets","2006-04-25","2006-05-15"]
["LN03110180","AWARD: Contract - Misc Materials - Magnets","2006-05-16","2006-05-16"]
["LN03110182","Vendor Fab & Assy - Misc Materials - Magnets","2006-05-17","2007-06-01"]
["LN03110184","RCV: from Vendor  - Misc Materials - Magnets","2007-06-04","2007-06-04"]
["LN03110190","Fab Tooling","2007-06-05","2007-06-11"]
["LN03110192","Fab Magnet Core","2007-06-12","2007-06-18"]
["LN03110194","Fab Magnet Coils","2007-06-19","2007-06-18"]
["LN03110205","Prep for and Paint Magnets (as required)","2007-06-19","2007-06-25"]
["LN03110210","Assemble Magnets","2007-06-26","2007-07-02"]
["LN03110215","Perform Magnet Fiducialization (as required)","2007-07-03","2007-07-10"]
["LN03110220","Perform QC & Inspection - Magnets","2007-07-11","2007-07-17"]
["LN03110225","Perform Magnetic Measurement (as required)","2007-07-18","2007-07-24"]
["LN03110230","Hand-off to Pre-Instl Qual Testing","2007-07-25","2007-07-24"]
["LN03110235","Perform Magnet Pre-Instlation Qual","2007-07-25","2007-07-26"]
["LN03110240","AVAIL: BYMP_LTU Magnets Ready for Instl","2007-07-27","2007-07-26"]
["LN03110245","Define Magnet Support Requirements","2006-10-03","2006-10-04"]
["LN03110250","Create ICD & Update LCLS Database","2006-10-05","2006-10-05"]
["LN03110255","Review/Accept Reqmts, Update ICD & DB entries","2006-10-06","2006-10-06"]
["LN03110260","Develop Preliminary Design - Magnet Supports","2006-10-09","2006-10-16"]
["LN03110270","Conduct Preliminary Design Review (PDR)","2006-10-17","2006-10-18"]
["LN03110280","Develop Final Design - Magnet Supports","2006-10-19","2006-10-24"]
["LN03110290","Conduct Final Design Review (FDR)","2006-10-25","2006-10-26"]
["LN03110300","COMP: Bend Magnet Supports (BYMP_LTU) Design","2006-10-27","2006-10-26"]
["LN03110305","Prep Bid Pak - Magnet Supports","2006-04-03","2006-04-03"]
["LN03110315","RELEASE: RFP - Magnet Supports","2006-04-04","2006-04-03"]
["LN03110320","Vendors Prep Proposals - Magnet Supts","2006-04-04","2006-04-24"]
["LN03110325","RCV: Proposals from Vendors - Supts","2006-04-25","2006-04-24"]
["LN03110330","Evaluate Vendor Proposals - Supports","2006-04-25","2006-05-15"]
["LN03110335","AWARD: Contract for Supts","2006-05-16","2006-05-16"]
["LN03110340","Vendor Fab 1st Lot - Supts","2006-05-17","2007-06-01"]
["LN03110345","RCV: 1st Lot Magnet Supports from Vendor","2007-06-04","2007-06-04"]
["LN03110350","Vendor Fab Remaining Lot - Supts","2007-06-05","2007-06-04"]
["LN03110355","RCV: Remaining Magnet Supts from Vendor","2007-06-05","2007-06-04"]
["LN03110360","Procure Misc Materials - Magnet Supports","2006-05-17","2006-06-14"]
["LN03110365","Fabricate Magnet Supports","2006-06-15","2006-06-22"]
["LN03110370","Prep for, Clean & Plate Magnet Supts","2006-06-23","2006-06-22"]
["LN03110375","Prep for and Paint Magnet Supports (as required)","2006-06-23","2006-06-22"]
["LN03110380","Perform QC & Inspection on Magnets Supts","2006-06-23","2006-06-30"]
["LN03110385","Assemble Magnet Supports","2006-07-03","2006-07-24"]
["LN03110390","Hand-off to Pre-Instl Qual Testing","2006-07-25","2006-07-24"]
["LN03110395","Perform Pre-Installation Qualification - Support","2007-06-05","2007-07-02"]
["LN03110400","AVAIL: BYMP_LTU Magnet Supts Ready for Instl","2007-07-03","2007-07-02"]
["LN03110500","Procure Coil (1ea) - Bend Mag (BYMP_LTU) SPARES","2006-10-03","2006-11-29"]
["LN03110550","RCV: Bend Magnet Coil (1ea) (BYMP_LTU) SPARES","2006-11-30","2006-11-29"]
["LN03110600","Receive & Review Safety Cover Requirements","2006-10-03","2006-10-02"]
["LN03110605","Develop Magnet Safety Cover Design","2006-10-03","2006-11-29"]
["LN03110610","COMP: Magnet Safety Design","2006-11-30","2006-11-29"]
["LN03110615","Procure Magnet Safety Cover Material","2006-11-30","2007-03-12"]
["LN03110620","RCV: Magnet Safety Cover (3ea)","2007-03-13","2007-03-12"]
["LN03110625","Fab and Assemble New Magnet Safety Covers (0ea)","2007-03-13","2007-03-12"]
["LN03110630","REQD: Reusable Safety Covers for Refurbishment","2007-03-13","2007-03-12"]
["LN03110635","Refurbish Reusable Safety Covers (0ea)","2007-03-13","2007-03-12"]
["LN03110640","AVAIL: Magnet Safety Covers Ready for Instl","2007-03-13","2007-03-12"]
["LN0312","BEND MAGNET (BYKIK_LTU) SUMMARY","2005-10-03","2007-08-06"]
["LN03120000","Define Magnet Requirements","2005-10-03","2005-11-04"]
["LN03120005","Create ICD & Update LCLS Database","2005-11-07","2005-11-18"]
["LN03120010","Review/Accept Reqmts, Update ICD & DB entries","2005-11-21","2005-11-22"]
["LN03120015","Develop Preliminary Design - Magnet","2005-11-23","2005-12-08"]
["LN03120025","Develop Preliminary Dsn - Magnet Field Analysis","2005-12-09","2006-01-13"]
["LN03120030","Conduct Preliminary Design Review (PDR)","2006-01-17","2006-01-17"]
["LN03120040","Develop Final Design - Magnets","2006-01-18","2006-01-24"]
["LN03120050","Conduct Final Design Review (FDR)","2006-01-25","2006-01-26"]
["LN03120060","Develop Magnetic Measurement Plan","2006-01-27","2006-02-02"]
["LN03120065","COMP: Bend Magnet (BYKIK_LTU) Design","2006-02-03","2006-02-02"]
["LN03120070","Prep Bid Pak - Magnets","2006-02-03","2006-02-02"]
["LN03120080","RELEASE: RFP - BYKIK_LTU Bend Magnet","2006-02-03","2006-02-02"]
["LN03120085","Vendors Prep Proposals - Magnets","2006-02-03","2006-02-24"]
["LN03120090","RCV: Proposals from Vendors - Magnet","2006-02-27","2006-02-24"]
["LN03120095","Evaluate Vendor Proposals - Magnets","2006-02-27","2006-03-10"]
["LN03120100","AWARD: Contract for Magnets","2006-03-13","2006-03-13"]
["LN03120105","Vendor Fab 1st Lot - Magnets","2006-03-14","2007-06-01"]
["LN03120110","RCV: 1st Lot Magnets from Vendor","2007-06-04","2007-06-01"]
["LN03120115","Vendor Fab Remaining Lot - Magnets","2007-06-04","2007-06-01"]
["LN03120120","RCV: Remaining Magnets from Vendor","2007-06-04","2007-06-01"]
["LN03120125","Hand-off to Pre-Instl Qual Testing","2007-06-04","2007-06-01"]
["LN03120130","Procure Misc Materials - Magnets","2006-10-03","2006-10-02"]
["LN03120135","Disassemble Magnet","2006-10-03","2006-10-03"]
["LN03120145","Refurbish Magnet Coils","2006-10-04","2006-10-04"]
["LN03120150","Assemble Magnets","2006-10-05","2006-10-04"]
["LN03120160","Prep for and Paint Magnets (as required)","2006-10-05","2006-10-04"]
["LN03120165","Perform Magnet Fiducialization (as required)","2006-10-05","2006-10-04"]
["LN03120170","Perform QC & Inspection - Magnets","2006-10-05","2006-10-04"]
["LN03120175","Perform Magnetic Measurement (as required)","2006-10-05","2006-10-04"]
["LN03120180","Procure Misc Materials - Magnets","2006-02-03","2007-04-02"]
["LN03120185","Fab Tooling","2007-04-03","2007-04-09"]
["LN03120190","Fab Magnet Core","2007-04-10","2007-04-16"]
["LN03120195","Fab Magnet Coils","2007-04-17","2007-04-23"]
["LN03120205","Prep for and Paint Magnets (as required)","2007-04-24","2007-04-30"]
["LN03120210","Assemble Magnets","2007-05-01","2007-05-07"]
["LN03120215","Perform Magnet Fiducialization (as required)","2007-05-08","2007-05-14"]
["LN03120220","Perform QC & Inspection - Magnets","2007-05-15","2007-05-21"]
["LN03120225","Perform Magnetic Measurement (as required)","2007-05-22","2007-05-29"]
["LN03120230","Hand-off to Pre-Instl Qual Testing","2007-05-30","2007-05-29"]
["LN03120235","Perform Magnet Pre-Instlation Qual","2007-06-04","2007-07-30"]
["LN03120240","AVAIL: BYKIK_LTU Magnet Ready for Instl","2007-07-31","2007-07-30"]
["LN03120245","Define Magnet Support Requirements","2006-10-03","2006-10-04"]
["LN03120250","Create ICD & Update LCLS Database","2006-10-05","2006-10-05"]
["LN03120255","Review/Accept Reqmts, Update ICD & DB entries","2006-10-06","2006-10-06"]
["LN03120260","Develop Preliminary Design - Magnet Supports","2006-10-09","2006-10-16"]
["LN03120270","Conduct Preliminary Design Review (PDR)","2006-10-17","2006-10-18"]
["LN03120280","Develop Final Design - Magnet Supports","2006-10-19","2006-10-24"]
["LN03120290","Conduct Final Design Review (FDR)","2006-10-25","2006-10-26"]
["LN03120300","COMP: Bend Magnet Supports (BYKIK_LTU) Design","2006-10-27","2006-10-26"]
["LN03120305","Prep Bid Pak - Magnet Supports","2006-10-27","2006-10-27"]
["LN03120315","RELEASE: RFP - Magnet Supports","2006-10-30","2006-10-27"]
["LN03120320","Vendors Prep Proposals - Magnet Supts","2006-10-30","2006-10-30"]
["LN03120325","RCV: Proposals from Vendors - Supts","2006-10-31","2006-10-30"]
["LN03120330","Evaluate Vendor Proposals - Supports","2006-10-31","2006-10-31"]
["LN03120335","AWARD: Contract for Supts","2006-11-01","2006-11-01"]
["LN03120340","Vendor Fab 1st Lot - Supts","2006-11-02","2007-06-01"]
["LN03120345","RCV: 1st Lot Magnet Supports from Vendor","2007-06-04","2007-06-04"]
["LN03120350","Vendor Fab Remaining Lot - Supts","2007-06-05","2007-06-04"]
["LN03120355","RCV: Remaining Magnet Supts from Vendor","2007-06-05","2007-06-04"]
["LN03120360","Procure Misc Materials - Magnet Supports","2006-10-27","2007-05-01"]
["LN03120365","Fabricate Magnet Supports","2007-05-02","2007-05-09"]
["LN03120370","Prep for, Clean & Plate Magnet Supts","2007-05-10","2007-05-09"]
["LN03120375","Prep for and Paint Magnet Supports (as required)","2007-05-10","2007-05-09"]
["LN03120380","Perform QC & Inspection on Magnets Supts","2007-05-10","2007-05-17"]
["LN03120385","Assemble Magnet Supports","2007-05-18","2007-06-08"]
["LN03120390","Hand-off to Pre-Instl Qual Testing","2007-06-11","2007-06-08"]
["LN03120395","Perform Pre-Installation Qualification - Support","2007-06-11","2007-08-06"]
["LN03120400","AVAIL: BYKIK_LTU Magnet Supts Ready for Instl","2007-08-07","2007-08-06"]
["LN03120500","Procure Coil (1ea) - Bend Mag (BYKIK_LTU) SPARES","2006-10-03","2006-11-29"]
["LN03120550","RCV: Bend Magnet Coil (1ea) (BYKIK_LTU) SPARES","2006-11-30","2006-11-29"]
["LN03120600","Receive & Review Safety Cover Requirements","2006-10-03","2006-10-02"]
["LN03120605","Develop Magnet Safety Cover Design","2006-10-03","2006-11-29"]
["LN03120610","COMP: Magnet Safety Design","2006-11-30","2006-11-29"]
["LN03120615","Procure Magnet Safety Cover (1ea)","2006-11-30","2007-01-11"]
["LN03120620","RCV: Magnet Safety Cover Material","2007-01-12","2007-01-11"]
["LN03120625","Fab and Assemble New Magnet Safety Covers (0ea)","2007-01-12","2007-01-11"]
["LN03120630","REQD: Reusable Safety Covers for Refurbishment","2007-01-12","2007-01-11"]
["LN03120635","Refurbish Reusable Safety Covers (0ea)","2007-01-12","2007-01-11"]
["LN03120640","AVAIL: Magnet Safety Covers Ready for Instl","2007-01-12","2007-01-11"]
["LN0313","BEND MAGNET (BYW_LTU) SUMMARY","2005-07-01","2007-07-26"]
["LN03130000","RCV: Magnet Requirements from System Integ","2005-07-01","2005-06-30"]
["LN03130010","REQD: Existing SLAC Magents Available for LCLS","2005-07-01","2005-06-30"]
["LN03130240","AVAIL: BYW_LTU Magnet Ready for Instl","2005-07-01","2005-06-30"]
["LN03130245","Define Magnet Support Requirements","2006-01-03","2006-01-04"]
["LN03130250","Create ICD & Update LCLS Database","2006-01-05","2006-01-05"]
["LN03130255","Review/Accept Reqmts, Update ICD & DB entries","2006-01-06","2006-01-06"]
["LN03130260","Develop Preliminary Design - Magnet Supports","2006-01-09","2006-02-06"]
["LN03130270","Conduct Preliminary Design Review (PDR)","2006-02-07","2006-02-08"]
["LN03130280","Develop Final Design - Magnet Supports","2006-02-09","2006-03-09"]
["LN03130290","Conduct Final Design Review (FDR)","2006-03-10","2006-03-13"]
["LN03130300","COMP: Bend Magnet Supports (BYW_LTU) Design","2006-03-14","2006-03-13"]
["LN03130340","Procure Magnet Supports","2006-03-14","2007-01-05"]
["LN03130345","RCV: Magnet Supports from Vendor","2007-01-08","2007-01-05"]
["LN03130360","Procure Misc Materials - Magnet Supports","2006-03-14","2007-01-05"]
["LN03130365","Fabricate Magnet Supports","2007-01-08","2007-03-06"]
["LN03130380","Perform QC & Inspection on Magnets Supts","2007-03-07","2007-05-01"]
["LN03130385","Assemble Magnet Supports","2007-05-02","2007-06-27"]
["LN03130390","Hand-off to Pre-Instl Qual Testing","2007-06-28","2007-06-27"]
["LN03130395","Perform Pre-Installation Qualification - Support","2007-06-28","2007-07-26"]
["LN03130400","AVAIL: BYW_LTU Magnet Supts Ready for Instl","2007-07-27","2007-07-26"]
["LN03130500","Procure Coil (1ea) - Bend Mag (BYW_LTU) SPARES","2007-07-27","2007-09-21"]
["LN03130550","RCV: Bend Magnet Coil (1ea) (BYW_LTU) SPARES","2007-09-24","2007-09-21"]
["LN03130600","Receive & Review Safety Cover Requirements","2006-10-03","2006-10-02"]
["LN03130605","Develop Magnet Safety Cover Design","2006-10-03","2006-11-29"]
["LN03130610","COMP: Magnet Safety Design","2006-11-30","2006-11-29"]
["LN03130615","Procure Magnet Safety Cover (4ea)","2006-11-30","2007-02-09"]
["LN03130620","RCV: Magnet Safety Cover Material","2007-02-12","2007-02-09"]
["LN03130640","AVAIL: Magnet Safety Covers Ready for Instl","2007-02-12","2007-02-09"]
["LN04","LINAC VACUUM SUBSYSTEM SUMMARY","2005-05-02","2007-10-15"]
["LN0401","LINAC VACUUM SUBSYSTEM TEST EQUIP SUMMARY","2006-10-03","2006-11-29"]
["LN04010000","Begin Varian Pumpdown Cart (3ea) Eq Procurement","2006-10-03","2006-10-02"]
["LN04010005","Procure Basic Unit, V70LP Turbo, MSP5366","2006-10-03","2006-11-29"]
["LN04010010","Procure Dry Scroll Pump, MSP1001","2006-10-03","2006-11-29"]
["LN04010015","Procure Multigauge Controller, MSP0125","2006-10-03","2006-11-29"]
["LN04010020","Procure Thermocouple Board, MSP0126","2006-10-03","2006-11-29"]
["LN04010025","ProcureCold Cathode Board, MSPL9066","2006-10-03","2006-11-29"]
["LN04010030","Procure Setpoint Board, MSP 0130","2006-10-03","2006-11-29"]
["LN04010035","Procure Remote Input/Output Board, MSPL8324","2006-10-03","2006-11-29"]
["LN04010040","Procure Standard RS 485/422 O/I Board, MSPL8490","2006-10-03","2006-11-29"]
["LN04010045","Procure Inverted Magnetron CC Gauge, MSPL9062","2006-10-03","2006-11-29"]
["LN04010050","Procure Gauge Tube, Thrmcpl, 2 3/4 CFF, MSP5316","2006-10-03","2006-11-29"]
["LN04010055","Procure Emergency Vent, MSP0132","2006-10-03","2006-11-29"]
["LN04010060","Procure Forced Aircooling, MSP0136","2006-10-03","2006-11-29"]
["LN04010065","RCV: Equip for Varian Pumpdown Carts (3ea)","2006-11-30","2006-11-29"]
["LN04010100","Begin Leybold Leak Detector (1ea) Eq Procurement","2006-10-03","2006-10-02"]
["LN04010105","Procure Misc Leybold Leak Detector Equip","2006-10-03","2006-11-29"]
["LN04010110","RCV: Equip for Leybold Leak Detector (1ea)","2006-11-30","2006-11-29"]
["LN0402","LINAC BEAMLINE VACUUM CHAMBERS SUMMARY","2005-05-02","2006-08-08"]
["LN04020015","Develop Preliminary Vacuum System Design","2005-05-02","2005-05-25"]
["LN04020020","Develop Prelim Component Layouts, Details & Supp","2005-06-14","2005-08-09"]
["LN04020025","Conduct Prelim Design Review (PDR) - BL Vac Sys","2005-08-10","2005-09-06"]
["LN04020030","Develop Final Design","2005-09-07","2005-11-15"]
["LN04020035","Conduct Final Design Review (FDR) - BL Vac Sys","2005-11-16","2005-11-16"]
["LN04020040","COMP: Beamline Vacuum System Design","2005-11-17","2005-11-16"]
["LN04020045","Develop Vacuum Post-Processing Plan","2005-11-17","2005-11-23"]
["LN04020050","Prep Bid Pak - Linac Beamline Vacuum System","2005-11-28","2005-12-09"]
["LN04020055","RELEASE: RFP - BL Vacuum Chambers","2005-12-12","2005-12-09"]
["LN04020060","Vendors Prep Proposals - BL Vac System Component","2005-12-12","2005-12-09"]
["LN04020065","RCV: Proposal from Vendors","2005-12-12","2005-12-09"]
["LN04020070","Evaluate Vendor Proposals","2005-12-12","2006-01-09"]
["LN04020075","AWARD: Contract for Beamline Vac Chambers","2006-01-10","2006-01-10"]
["LN04020080","Fabricate 1st Lot","2006-01-11","2006-01-10"]
["LN04020085","RCV: 1st Lot Vac Equipment from Vendor","2006-01-11","2006-01-10"]
["LN04020090","Fabricate Remaining Lot (as required)","2006-01-11","2006-01-10"]
["LN04020095","RCV: Remaining Lot from Vendor (as req'd)","2006-01-11","2006-01-10"]
["LN04020100","Procure Vacuum Chamber Materials","2005-11-17","2005-12-16"]
["LN04020105","Fab Vacuum Chamber","2006-01-03","2006-03-01"]
["LN04020110","Vacuum Chamber QA","2006-03-02","2006-03-15"]
["LN04020115","Prep for, Clean & Plate Vacuum Equipment","2006-03-16","2006-04-12"]
["LN04020120","Vacuum Chamber Welding","2006-04-13","2006-06-08"]
["LN04020125","Process Vacuum Chamber","2006-06-09","2006-07-21"]
["LN04020130","Perform QC and Inspection","2006-07-24","2006-07-31"]
["LN04020135","Prep for & Deliver to \"Pre-Install Qual Test\"","2006-08-01","2006-08-01"]
["LN04020140","Perform Pre-Installation Qual Test","2006-08-02","2006-08-08"]
["LN04020145","AVAIL: Beamline Vac Chambers Ready for L01 Instl","2006-08-09","2006-08-08"]
["LN04020150","Prep Bid Pak - BL Vacuum Bellows Module","2005-11-17","2005-12-09"]
["LN04020155","RELEASE: RFP - BL Vacuum Bellows Module","2005-12-12","2005-12-09"]
["LN04020160","Vendors Prep Proposals - BL Vac System Component","2005-12-12","2005-12-09"]
["LN04020165","RCV: Proposal from Vendors","2005-12-12","2005-12-09"]
["LN04020170","Evaluate Vendor Proposals","2005-12-12","2006-01-09"]
["LN04020175","AWARD: Contract for Vacuum Bellows Module","2006-01-12","2006-01-12"]
["LN04020180","Fabricate 1st Lot","2006-01-13","2006-01-12"]
["LN04020185","RCV: 1st Lot Vac Equipment from Vendor","2006-01-13","2006-01-12"]
["LN04020190","Fabricate Remaining Lot (as required)","2006-01-13","2006-01-12"]
["LN04020195","RCV: Remaining Lot from Vendor (as req'd)","2006-01-13","2006-01-12"]
["LN04020200","Procure Bellows Modules","2005-11-17","2005-12-16"]
["LN04020205","Procure Bellows Material","2005-11-17","2005-12-16"]
["LN04020210","Bellows Fabrication","2006-01-13","2006-02-10"]
["LN04020215","Bellows QA","2006-02-13","2006-02-16"]
["LN04020220","Bellows Cleaning/Plating","2006-02-17","2006-03-01"]
["LN04020225","Bellows Welding","2006-03-02","2006-03-13"]
["LN04020230","Bellows Vacuum Processing","2006-03-14","2006-04-03"]
["LN04020235","AVAIL: Vacuum Bellows Module Ready for L01 Instl","2006-04-04","2006-04-03"]
["LN04020240","Prep Bid Pak - Linac Beamline Vacuum System","2005-11-17","2005-11-16"]
["LN04020245","RELEASE: RFP - Linac Vacuum Supports","2005-11-17","2005-11-16"]
["LN04020250","Vendors Prep Proposals - BL Vac System Component","2005-11-17","2005-12-09"]
["LN04020255","RCV: Proposal from Vendors","2005-12-12","2005-12-09"]
["LN04020260","Evaluate Vendor Proposals","2005-12-12","2006-01-09"]
["LN04020265","AWARD: Contract for Linac Vacuum Supports","2006-01-10","2006-01-10"]
["LN04020270","Fabricate 1st Lot","2006-01-11","2006-01-10"]
["LN04020275","RCV: 1st Lot Vac Equipment from Vendor","2006-01-11","2006-01-10"]
["LN04020280","Fabricate Remaining Lot (as required)","2006-01-11","2006-01-10"]
["LN04020285","RCV: Remaining Lot from Vendor (as req'd)","2006-01-11","2006-01-10"]
["LN04020290","Procure Misc Materials - Vacuum Supports","2005-11-17","2005-12-16"]
["LN04020295","Fab Vacuum Support","2006-01-11","2006-06-02"]
["LN04020300","Assemble Beamline Vacuum Supports","2006-02-09","2006-06-30"]
["LN04020305","AVAIL: BL Vac Chamber Supts Ready for L01 Instl","2006-07-03","2006-06-30"]
["LN04020400","Procure Materials for B/L Vac Sys Spares Kit","2006-10-03","2006-10-30"]
["LN04020405","RCV: Materials for B/L Vac Sys Spares Kit","2006-10-31","2006-10-30"]
["LN0403","LINAC BC1 VACUUM CHAMBERS SUMMARY","2005-05-02","2006-05-18"]
["LN04030045","Prep Bid Pak - BC1 Vacuum Chambers","2005-05-02","2005-07-15"]
["LN04030050","RELEASE: RFP - BC1 Vacuum Chambers","2005-07-18","2005-07-15"]
["LN04030055","Vendors Prep Proposals - BC1 Vac System","2005-07-18","2005-07-29"]
["LN04030060","RCV: Proposal from Vendors","2005-08-01","2005-07-29"]
["LN04030065","Evaluate Vendor Proposals","2005-08-01","2005-08-12"]
["LN04030070","AWARD: Contract for BC1 Vacuum Chambers","2005-08-15","2005-08-15"]
["LN04030075","Vendor Fab & Assy - Vacuum Chamber Materials","2005-08-16","2006-01-31"]
["LN04030080","RCV: from Vendor - Vacuum Chamber Materials","2006-02-01","2006-02-01"]
["LN04030100","Fab Vacuum Chamber","2005-09-23","2006-03-02"]
["LN04030105","Vacuum Chamber QA","2006-03-03","2006-03-14"]
["LN04030110","Prep for, Clean & Plate Vacuum Equipment","2006-03-15","2006-03-29"]
["LN04030115","Vacuum Chamber Welding","2006-03-30","2006-04-21"]
["LN04030120","Process Vacuum Chamber","2006-04-24","2006-05-02"]
["LN04030125","Perform QC and Inspection","2006-05-03","2006-05-10"]
["LN04030130","Prep for & Deliver to \"Pre-Install Qual Test\"","2006-05-11","2006-05-11"]
["LN04030135","Perform Pre-Installation Qual Test","2006-05-12","2006-05-18"]
["LN04030140","AVAIL: BC1 Vac Chambers Ready for Install","2006-05-19","2006-05-18"]
["LN04030400","Procure Materials for BC1 Vac Sys Spares Kit","2006-10-03","2006-10-30"]
["LN04030405","RCV: Materials for BC1 Vac Sys Spares Kit","2006-10-31","2006-10-30"]
["LN0404","LINAC BC2 VACUUM CHAMBERS SUMMARY","2005-09-01","2007-03-22"]
["LN04040015","Develop Preliminary Vacuum System Design","2005-09-01","2005-12-15"]
["LN04040020","Conduct Prelim Design Review (PDR) - BC2 Vac Sys","2005-12-16","2006-01-06"]
["LN04040025","Develop Final Design -BC2 Vac","2006-01-09","2006-03-21"]
["LN04040030","Conduct Final Design Review (FDR) - BC2 Vac Sys","2006-03-22","2006-03-28"]
["LN04040035","COMP: BC2 Vacuum Chambers Design","2006-03-29","2006-03-28"]
["LN04040040","Develop Vacuum Post-Processing Plan","2006-03-29","2006-04-04"]
["LN04040045","Prep Bid Pak - BC2 Vac Chamber Mtrl","2006-03-29","2006-04-11"]
["LN04040050","RELEASE: RFP - BC2 Vac Chambers Mtrl","2006-04-12","2006-04-11"]
["LN04040055","Vendors Prep Proposals - BC2 Vac System","2006-04-12","2006-04-25"]
["LN04040060","RCV: Proposal from Vendors","2006-04-26","2006-04-25"]
["LN04040065","Evaluate Vendor Proposals","2006-04-26","2006-05-09"]
["LN04040070","AWARD: Contract for BC2 Vac Chambers Mtrl","2006-05-10","2006-05-10"]
["LN04040075","Procure Vacuum Chamber Materials","2006-05-11","2006-06-08"]
["LN04040076","Procure Bellows Module","2006-05-11","2006-06-08"]
["LN04040077","Procure CF Copper Gasket","2006-05-11","2006-06-08"]
["LN04040078","Procure CF Bolt Set","2006-05-11","2006-06-08"]
["LN04040080","RCV: from Vendor - Vacuum Chamber Materials","2006-06-09","2006-06-08"]
["LN04040100","Fab Vacuum Chamber","2006-06-09","2007-01-02"]
["LN04040105","Vacuum Chamber QA","2007-01-03","2007-01-12"]
["LN04040110","Prep for, Clean & Plate Vacuum Equipment","2007-01-16","2007-01-30"]
["LN04040115","Vacuum Chamber Welding","2007-01-31","2007-02-23"]
["LN04040120","Process Vacuum Chamber","2007-02-26","2007-03-06"]
["LN04040125","Perform QC and Inspection","2007-03-07","2007-03-14"]
["LN04040130","Prep for & Deliver to \"Pre-Install Qual Test\"","2007-03-15","2007-03-15"]
["LN04040135","Perform Pre-Installation Qual Test","2007-03-16","2007-03-22"]
["LN04040140","AVAIL: BC2 Vac Chambers Ready for Install","2007-03-23","2007-03-22"]
["LN04040400","Procure Materials for BC2 Vac Sys Spares Kit","2006-10-03","2006-10-30"]
["LN04040405","RCV: Materials for BC2 Vac Sys Spares Kit","2006-10-31","2006-10-30"]
["LN0405","LINAC to UND (LTU) VAC CHAMBERS SUMMARY","2005-11-17","2007-09-27"]
["LN04050000","Define LTU Vac Sys Requirements","2005-11-17","2005-12-02"]
["LN04050003","Create ICD & Update LCLS Database","2005-12-05","2005-12-06"]
["LN04050005","Review & Accept Requirements, ICD & DB Entries","2005-12-07","2005-12-08"]
["LN04050010","Develop Preliminary Vacuum System Design","2005-12-09","2006-05-16"]
["LN04050015","Develop Preliminary Vac Sys Supports Design","2005-12-09","2006-02-21"]
["LN04050020","Conduct Prelim Design Review (PDR) - LTU Vac Sys","2006-05-17","2006-05-22"]
["LN04050025","Develop Final Design","2006-05-23","2006-08-02"]
["LN04050030","Conduct Final Design Review (FDR) - LTU Vac Sys","2006-08-03","2006-08-08"]
["LN04050035","COMP: LTU Vacuum Chambers Design","2006-08-09","2006-08-08"]
["LN04050040","Develop Vacuum Post-Processing Plan","2006-08-09","2006-09-06"]
["LN04050045","Prep Bid Pak -  Vacuum Equipment","2006-10-03","2006-10-09"]
["LN04050050","RELEASE: RFP  - Vacuum Equipment","2006-10-10","2006-10-09"]
["LN04050055","Vendors Prep Proposals - Vacuum Equipment","2006-10-10","2006-10-23"]
["LN04050060","RCV: Proposals from Vendors - Vacuum Equipment","2006-10-24","2006-10-23"]
["LN04050065","Evaluate Vendor Proposals","2006-10-24","2006-10-25"]
["LN04050070","AWARD: Contract - Vacuum Equipment","2006-10-26","2006-10-26"]
["LN04050080","RCV: from Vendor  - Vacuum Equipment","2007-04-06","2007-04-05"]
["LN04050100","Procure Vacuum Chamber Material","2006-10-27","2006-10-27"]
["LN04050105","Fab Vacuum Chamber","2006-11-28","2007-04-05"]
["LN04050110","Vacuum Chamber QA Fabrication","2007-03-09","2007-03-08"]
["LN04050115","Prep for, Clean & Plate Vacuum Equipment","2007-04-06","2007-06-29"]
["LN04050120","Vacuum Chamber Welding","2007-05-04","2007-08-13"]
["LN04050125","Process Vacuum Chamber","2007-06-04","2007-09-11"]
["LN04050130","Perform QC and Inspection","2007-09-12","2007-09-19"]
["LN04050135","Prep for & Deliver to \"Pre-Install Qual Test\"","2007-09-20","2007-09-20"]
["LN04050140","Perform Pre-Installation Qual Test","2007-09-21","2007-09-27"]
["LN04050145","AVAIL: LTU Vac Chambers Ready for Install","2007-09-28","2007-09-27"]
["LN04050150","Prep Bid Pak - Vacuum Supports","2006-10-03","2006-10-02"]
["LN04050155","RELEASE: RFP - LTU Vacuum Supports","2006-10-03","2006-10-02"]
["LN04050160","Vendors Prep Proposals - LTU Vac System","2006-10-03","2006-10-02"]
["LN04050165","RCV: Proposals from Vendors -","2006-10-03","2006-10-02"]
["LN04050170","Evaluate Vendor Proposals","2006-10-03","2006-10-02"]
["LN04050175","AWARD: Contract for LTU Vacuum Supports","2006-10-03","2006-10-02"]
["LN04050180","Fabricate 1st Lot","2006-10-03","2006-10-02"]
["LN04050185","RCV: 1st Lot Vac Equipment from Vendor","2006-10-03","2006-10-02"]
["LN04050190","Fabricate Remaining Lot (as required)","2006-10-03","2006-10-02"]
["LN04050195","RCV: Remaining Lot from Vendor (as req'd)","2006-10-03","2006-10-02"]
["LN04050205","Procure Misc Materials - Vacuum Supports","2006-10-03","2006-10-30"]
["LN04050206","Procure Materials for Vacuum Supports","2006-10-03","2006-10-30"]
["LN04050207","Procure Bellows","2006-10-27","2007-04-05"]
["LN04050208","Procure CF Flanges","2006-10-27","2007-04-05"]
["LN04050209","Procure CF Crosses","2006-10-27","2007-04-05"]
["LN04050210","Fab Vacuum Support","2006-10-31","2007-03-12"]
["LN04050211","Procure Vat Valve","2006-10-27","2007-04-05"]
["LN04050212","Procure Pump Out Valve","2006-10-27","2007-04-05"]
["LN04050213","Procure Cold Cathode Gauge","2006-10-27","2007-04-05"]
["LN04050214","Procure Pirani Gauge","2006-10-27","2007-04-05"]
["LN04050215","Assemble LTU Vacuum Supports","2007-01-12","2007-05-07"]
["LN04050216","Procure Gauge Pig Tail","2006-10-27","2007-04-05"]
["LN04050217","Procure Ion Pump","2006-10-27","2007-04-05"]
["LN04050218","Procure Ion Pump Pig Tail","2006-10-27","2007-04-05"]
["LN04050219","Procure Copper Gasket","2006-10-27","2007-04-05"]
["LN04050220","AVAIL: LTU Vac Chamber Supports Ready for Instl","2007-05-08","2007-05-07"]
["LN04050221","Procure CF Bolt Set","2006-10-27","2007-04-05"]
["LN04050400","Procure Materials for LTU Vac Sys Spares Kit","2006-10-03","2006-10-30"]
["LN04050405","RCV: Materials for LTU Vac Sys Spares Kit","2006-10-31","2006-10-30"]
["LN0406","LINAC DUMPLINE VACUUM CHAMBERS SUMMARY","2006-03-29","2007-10-15"]
["LN04060000","Define Dumpline Vac Sys Requirements","2006-03-29","2006-04-11"]
["LN04060003","Create ICD & Update LCLS Database","2006-04-12","2006-04-13"]
["LN04060007","Review & Accept Requirements, ICD & DB Entries","2006-04-14","2006-04-14"]
["LN04060010","Develop Preliminary Vacuum System Design","2006-04-17","2006-06-26"]
["LN04060013","Define Requirements LTU Vac Sys Supports","2006-04-17","2006-04-28"]
["LN04060017","Develop Prelim Design LTU Vacuum Sys Supports","2006-05-01","2006-07-11"]
["LN04060020","Conduct Prelim Design Review (PDR) - D/L Vac Sys","2006-06-27","2006-06-28"]
["LN04060025","Develop Final Design","2006-06-29","2006-09-08"]
["LN04060030","Conduct Final Design Review (FDR) - D/L Vac Sys","2006-09-11","2006-09-12"]
["LN04060035","COMP: Dumpline Vacuum System Design","2006-10-03","2006-10-02"]
["LN04060040","Develop Vacuum Post-Processing Plan","2006-10-03","2006-10-16"]
["LN04060045","Prep Bid Pak - Dumpline Vacuum System","2006-10-17","2006-11-06"]
["LN04060050","RELEASE: RFP - Dumpline Vacuum Chambers","2006-11-07","2006-11-06"]
["LN04060055","Vendors Prep Proposals - Dumpline Vac System","2006-11-07","2006-11-29"]
["LN04060060","RCV: Proposals from Vendors -","2006-11-30","2006-11-29"]
["LN04060065","Evaluate Vendor Proposals","2006-11-30","2007-01-04"]
["LN04060070","AWARD: Contract for Linac Dumpline Vac Chamber","2007-01-05","2007-01-05"]
["LN04060075","Fabricate 1st Lot","2007-01-08","2007-03-06"]
["LN04060080","RCV: 1st Lot Vac Equipment from Vendor","2007-03-07","2007-03-06"]
["LN04060085","Fabricate Remaining Lot (as required)","2007-03-07","2007-03-06"]
["LN04060090","RCV: Remaining Lot from Vendor (as req'd)","2007-03-07","2007-03-06"]
["LN04060095","Procure Bellows Modules","2006-10-03","2007-01-11"]
["LN04060096","Procure CF Flanges","2006-10-03","2007-01-11"]
["LN04060097","Procure CF Crosses","2006-10-03","2007-01-11"]
["LN04060098","Procure VAT Valve","2006-10-03","2007-01-11"]
["LN04060099","Procure Pump Out Valve","2006-10-03","2007-01-11"]
["LN04060101","Procure Cold Cathode Gauge","2006-10-03","2007-01-11"]
["LN04060102","Procure Pirani Gauge","2006-10-03","2007-01-11"]
["LN04060103","Procure Gauge Pig Tail","2006-10-03","2007-01-11"]
["LN04060104","Procure Ion Pump","2006-10-03","2007-01-11"]
["LN04060105","Fab Vacuum Chamber","2007-01-12","2007-04-09"]
["LN04060106","Procure Ion Pump Pig Tail","2006-10-03","2007-01-11"]
["LN04060107","Procure CF Copper Gasket","2006-10-03","2007-01-11"]
["LN04060108","Procure CF Bolt Set","2006-10-03","2007-01-11"]
["LN04060109","Procure 304 Tubing","2006-10-03","2007-01-11"]
["LN04060110","Vacuum Chamber QA Fabrication","2007-02-12","2007-05-07"]
["LN04060115","Clean & Plate Vacuum Equipment","2007-03-13","2007-07-03"]
["LN04060120","Vacuum Chamber Welding","2007-06-06","2007-08-29"]
["LN04060125","Process Vacuum Chamber","2007-07-05","2007-09-27"]
["LN04060130","Perform QC and Inspection","2007-09-28","2007-10-05"]
["LN04060135","Prep for & Deliver to \"Pre-Install Qual Test\"","2007-10-08","2007-10-08"]
["LN04060140","Perform Pre-Installation Qual Test","2007-10-09","2007-10-15"]
["LN04060145","AVAIL: DL Vac Chambers Ready for Install","2007-10-16","2007-10-15"]
["LN04060150","Prep Bid Pak - Vacuum Supports","2006-10-03","2006-10-23"]
["LN04060155","RELEASE: RFP - Dumpline Vacuum Supports","2006-10-24","2006-10-23"]
["LN04060160","Vendors Prep Proposals - Dumpline Vac System","2006-10-24","2006-11-20"]
["LN04060165","RCV: Proposals from Vendors -Dumpline Vac System","2006-11-21","2006-11-20"]
["LN04060170","Evaluate Vendor Proposals - UHV Components","2006-11-21","2006-12-13"]
["LN04060175","AWARD: Contract for Dumpline Vac Chamber Supt","2006-12-14","2006-12-14"]
["LN04060180","Fabricate 1st Lot","2006-12-15","2007-02-27"]
["LN04060185","RCV: 1st Lot Vac Equipment from Vendor","2007-02-28","2007-02-27"]
["LN04060190","Fabricate Remaining Lot (as required)","2007-02-28","2007-02-27"]
["LN04060195","RCV: Remaining Lot from Vendor (as req'd)","2007-02-28","2007-02-27"]
["LN04060200","Procure Misc Materials - Vacuum Supports","2007-02-28","2007-03-27"]
["LN04060205","Fab Vacuum Support","2007-03-28","2007-07-19"]
["LN04060210","Assemble DL Vacuum Supports","2007-04-25","2007-08-16"]
["LN04060215","AVAIL: DL Vac Chamber Supports Ready for Instl","2007-08-17","2007-08-16"]
["LN04060400","Procure Materials for D/L Vac Sys Spares Kit","2006-10-03","2006-10-30"]
["LN04060405","RCV: Materials for D/L Vac Sys Spares Kit","2006-10-31","2006-10-30"]
["LN05","LINAC ELECTRON DIAGNOSTICS SUMMARY","2005-09-20","2008-02-20"]
["LN0501",null,"2005-05-02","2005-05-02"]
["LN05010395","Prep Bid Pack - Wire Scanner","2005-11-01","2005-11-07"]
["LN05010400","AWARD: Contract Wire Scanners (2ea) Spares","2006-10-03","2006-10-03"]
["LN05010405","Vendor Fab 1st Lot (2) Spares","2006-10-04","2006-10-31"]
["LN05010410","RCV: 1st Lot from Vendor (2) Spares","2006-11-01","2006-10-31"]
["LN05010415","Vendor Fab Remaining Lot (2) Spares","2006-11-01","2006-11-30"]
["LN05010420","RCV: Remaining from Vendor (2) Spares","2006-12-01","2006-11-30"]
["LN05010425","Procure Misc Materials - Wire Scann - (2) SPARES","2006-10-03","2007-06-26"]
["LN05010430","Component Fab & Assembly - Wire Scanr (2) Spares","2008-10-01","2009-02-04"]
["LN05010435","Release RFP - Wire Scanners","2005-11-08","2005-11-08"]
["LN05010440","Vendors Prep Proposal - Wire Scanners","2005-11-09","2005-12-08"]
["LN05010445","Perform QC / Metrology (2ea) Spares","2009-02-05","2009-02-10"]
["LN05010450","Perform Functional Testing - Wire Scn (2) Spares","2009-02-11","2009-02-12"]
["LN05010455","Collect Component Performance Data (2ea) Spares","2009-02-13","2009-02-19"]
["LN05010460","Load Component Data Base (2ea) Spares","2009-02-20","2009-02-26"]
["LN05010465","Post Process & Test (2ea) Spares","2009-02-27","2009-03-05"]
["LN05010470","AVAIL: Wire Scanners (2ea) Spares","2009-03-06","2009-03-05"]
["LN05010475","RCV: Proposals from Vendors","2005-12-09","2005-12-09"]
["LN05010480","Evaluate Vendor Proposals","2005-12-12","2005-12-16"]
["LN05010485","AWARD: Contract - Wire Scanners L01-BC1","2006-01-03","2006-01-03"]
["LN05010490","Vendor Fab Wire Scanner Components","2006-01-04","2006-03-02"]
["LN05010495","RCV: Wire Scanner Components from Vendor","2006-03-03","2006-03-03"]
["LN05010500","Procure Misc Materials - Wire Scanners","2005-11-08","2005-12-07"]
["LN05010516","Component Fab & Assembley - Wire Scanners","2006-03-06","2006-03-06"]
["LN05010517","AWARD: Contract for Supports L01-BC1","2006-01-03","2006-01-03"]
["LN05010520","Vendor Fab Supports","2006-01-04","2006-03-02"]
["LN05010525","Pocure Misc. Materials - Wire Scanner Support","2006-01-04","2006-02-01"]
["LN05010535","Perform Functional Testing - Wire Scanners","2006-03-07","2006-03-20"]
["LN05010540","Post Process & Test","2006-03-21","2006-04-03"]
["LN05010545","AVAIL: Wire Scanners Ready for L01 Install","2006-04-04","2006-04-04"]
["LN05010550","AVAIL: Wire Scanners Ready for BC1 Install","2006-04-04","2006-04-04"]
["LN05010575","AVAIL: Supports Ready for Install","2006-03-03","2006-03-03"]
["LN05010590","Prep Bid Pack - Wire Scanner","2006-11-01","2006-11-07"]
["LN05010600","Release RFP - Wire Scanners","2006-11-08","2006-11-08"]
["LN05010610","Vendors Prep Proposal - Wire Scanners","2006-11-09","2006-12-08"]
["LN05010620","RCV: Proposals from Vendors","2006-12-11","2006-12-11"]
["LN05010630","Evaluate Vendor Proposals","2006-12-12","2007-01-02"]
["LN05010632","AWARD: Contract - Wire Scanners BC2-L03-LTU","2007-01-03","2007-01-03"]
["LN05010640","Vendor Fab Wire Scanner Components","2007-01-04","2007-03-02"]
["LN05010650","RCV: Wire Scanner Components from Vendor","2007-03-05","2007-03-05"]
["LN05010660","Procure Misc Materials - Wire Scanners","2006-11-08","2006-12-07"]
["LN05010670","Component Fab & Assembley - Wire Scanners","2007-03-06","2007-03-06"]
["LN05010672","AWARD: Contract for Supports BC2-L03-LTU","2006-12-12","2006-12-12"]
["LN05010680","Vendor Fab Supports","2006-12-13","2007-02-23"]
["LN05010690","Pocure Misc. Materials - Wire Scanner Support","2006-12-13","2007-01-25"]
["LN05010700","Perform Functional Testing - Wire Scanners","2007-03-07","2007-03-20"]
["LN05010710","Post Process & Test","2007-03-21","2007-04-03"]
["LN05010740","AVAIL: Wire Scanners Ready for L02 Install","2007-04-04","2007-04-04"]
["LN05010750","AVAIL: Wire Scanners Ready for BC2 Install","2007-04-04","2007-04-04"]
["LN05010760","AVAIL: Wire Scanners Ready for L03 Install","2007-04-04","2007-04-04"]
["LN05010770","AVAIL: Wire Scanners Ready for LTU Install","2007-04-04","2007-04-04"]
["LN05010780","AVAIL: Supports Ready for Install","2007-02-26","2007-02-26"]
["LN05020120","Write ICD - Beam Position Monitor","2005-10-03","2005-10-07"]
["LN05020125","Collect Area Specific Requirements","2005-10-10","2005-10-14"]
["LN05020130","Produce Common Layout","2005-10-17","2005-10-18"]
["LN05020135","Develop General Specifications/Analysis","2005-10-19","2005-11-01"]
["LN05020145","Create/Remodel/Revise DSN Docs","2005-11-02","2005-12-08"]
["LN05020150","Design Check","2005-12-09","2006-06-14"]
["LN05020155","Write Component Traveler","2005-10-03","2005-10-07"]
["LN05020160","BPMs - Preliminary Design Review (PDR)","2005-12-09","2005-12-15"]
["LN05020165","Generate Detailed Procuremnt Plan","2005-12-16","2006-01-06"]
["LN05020170","BPMs - Final Design Review (FDR)","2006-01-09","2006-01-13"]
["LN05020175","Procure Component Material - BPMs","2006-01-17","2006-02-13"]
["LN05020180","Component Fab & Assembly - BPMs","2006-02-14","2006-03-28"]
["LN05020185","Perform QC / Metrology","2006-03-29","2006-04-04"]
["LN05020190","Perform Functional Testing - BPMs","2006-04-05","2006-04-11"]
["LN05020195","Post Process & Test","2006-04-12","2006-04-18"]
["LN05020200","AVAIL: BPMs Ready for BC1 Install","2006-04-19","2006-04-18"]
["LN05020205","AVAIL: BPMs Ready for L01 Install","2006-04-19","2006-04-18"]
["LN05020360","Receive BPM Requirements","2006-10-03","2006-10-03"]
["LN05020365","Write ICD - Beam Path Monitor","2006-10-04","2006-10-09"]
["LN05020370","Collect Area Specific Requirements","2006-10-10","2006-10-16"]
["LN05020375","Produce Common Layout","2006-10-17","2006-11-13"]
["LN05020380","Develop General Specifications / Analysis","2006-11-14","2006-11-20"]
["LN05020385","Create / Remodel / Revise Dsn Documentation","2006-11-21","2007-01-19"]
["LN05020390","Design Check","2007-01-22","2007-03-19"]
["LN05020395","Write Component Traveler","2007-03-20","2007-04-02"]
["LN05020400","Conduct Prelim Design Review (PDR) - FFTB BPMs","2007-04-03","2007-04-03"]
["LN05020405","Generate Detailed Procurement Plan","2007-04-04","2007-04-17"]
["LN05020410","Conduct Final Design Review (FDR) - FFTB BPMs","2007-04-18","2007-04-18"]
["LN05020412","COMP: BPM Design - FFTB","2007-04-19","2007-04-19"]
["LN05020415","Procure Component Material - BPMs","2007-04-20","2007-07-16"]
["LN05020425","Component Fab & Assembly - BPMs","2007-07-17","2007-09-11"]
["LN05020430","Perform QC / Metrology","2007-09-12","2007-09-18"]
["LN05020435","Perform Functional Testing - BPMs","2007-09-19","2007-09-20"]
["LN05020445","Post Process & Test","2007-09-21","2007-09-27"]
["LN05020450","AVAIL: FFTB BPMs Ready for Install","2007-09-28","2007-09-28"]
["LN05020480","Develop General Specifications / Analysis","2006-01-17","2006-03-14"]
["LN05020485","Create / Remodel / Revise Dsn Documentation","2006-01-17","2006-03-14"]
["LN05020490","Write Component Traveler","2006-02-15","2006-03-01"]
["LN05020495","Conduct BPMs PDR","2006-03-02","2006-03-08"]
["LN05020500","Procure Component Material - BPMs - (2) SPARES","2006-10-03","2007-03-12"]
["LN05020505","Component Fab & Assembly - BPMs (2ea) Spares","2007-03-13","2007-08-29"]
["LN05020510","Generate Detailed Procurement Plan","2006-03-09","2006-03-22"]
["LN05020515","Conduct BPMs FDR","2006-03-23","2006-03-29"]
["LN05020520","Perform QC / Metrology (2ea) Spares","2007-08-30","2007-08-31"]
["LN05020525","Perform Functional Testing - BPMs (2ea) Spares","2007-09-04","2007-09-05"]
["LN05020530","Collect Component Performance Data (2ea) Spares","2007-09-06","2007-09-12"]
["LN05020535","Load Component Data Base (2ea) Spares","2007-09-13","2007-09-19"]
["LN05020540","Post Process & Test (2ea) Spares","2007-09-20","2007-09-26"]
["LN05020545","Design Check","2006-03-30","2006-04-26"]
["LN05020547","COMP: BPM Design - BC1","2006-04-27","2006-04-27"]
["LN05020550","Procure Component Material - BPMs","2006-04-28","2006-05-25"]
["LN05020555","Component Fab & Assembly - BPMs","2006-05-26","2006-06-23"]
["LN05020560","Perform QC / Metrology","2006-06-26","2006-07-24"]
["LN05020565","Perform Functional Testing - BPMs","2006-07-25","2006-08-07"]
["LN05020570","Post Process & Test","2006-08-08","2006-08-21"]
["LN05020575","AVAIL: High Resolution BC1 BPM Read for Install","2006-08-22","2006-08-22"]
["LN05020600","Procure Component Material - RF BPM - (2) SPARES","2006-10-03","2007-01-11"]
["LN05020605","Component Fab & Assembly - RFBPMs (2ea) Spares","2007-01-12","2007-05-07"]
["LN05020610","Component Fab & Assembly - RF BPMs","2007-05-08","2007-08-29"]
["LN05020615","Perform QC / Metrology (2ea) Spares","2007-08-30","2007-09-05"]
["LN05020620","Perform Functional Testing - RFBPMs (2ea) Spares","2007-09-06","2007-09-07"]
["LN05020625","Collect Component Performance Data (2ea) Spares","2007-09-10","2007-09-14"]
["LN05020630","Load Component Data Base (2ea) Spares","2007-09-17","2007-09-21"]
["LN05020635","Post Process & Test (2ea) Spares","2007-09-24","2007-09-28"]
["LN05020700","Procure Component Material - BPMs - (2) SPARES","2007-07-17","2007-09-11"]
["LN05020705","Component Fab & Assembly - BPMs (2ea) Spares","2007-09-12","2007-11-06"]
["LN05020720","Perform QC / Metrology (2ea) Spares","2007-11-07","2007-11-13"]
["LN05020725","Perform Functional Testing - BPMs (2ea) Spares","2007-11-14","2007-11-19"]
["LN05020730","Collect Component Performance Data (2ea) Spares","2007-11-20","2007-11-21"]
["LN05020735","Load Component Data Base (2ea) Spares","2007-11-26","2007-11-27"]
["LN05020740","Post Process & Test (2ea) Spares","2007-11-28","2007-12-11"]
["LN05020800","Procure Component Material - BPMs - (1) SPARE","2006-10-03","2006-11-29"]
["LN05020805","Component Fab & Assembly - BPMs (1ea) Spare","2006-11-30","2007-06-05"]
["LN05020820","Perform QC / Metrology (1ea) Spare","2007-06-06","2007-06-11"]
["LN05020825","Perform Functional Testing - BPMs (1ea) Spare","2007-06-12","2007-06-15"]
["LN05020830","Collect Component Performance Data (1ea) Spare","2007-06-18","2007-06-19"]
["LN05020835","Load Component Data Base (1ea) Spare","2007-06-20","2007-06-21"]
["LN05020840","Post Process & Test (1ea) Spare","2007-06-22","2007-06-27"]
["LN05020845","AVAIL: BPMs (2/2/2/1) Spare","2007-12-12","2007-12-11"]
["LN05030300","Procure Component Material - Toroid - (2) SPARES","2006-10-03","2007-01-11"]
["LN05030305","Review & Accept Requirements","2005-10-03","2005-10-14"]
["LN05030310","Component Fab & Assembly - Toroids (2ea) Spares","2007-01-12","2007-05-07"]
["LN05030315","Write ICD - Toroid","2005-10-17","2005-11-04"]
["LN05030320","Collect Area Specific Requirements","2005-11-07","2005-11-29"]
["LN05030325","Perform QC / Metrology (2ea) Spares","2007-05-08","2007-05-09"]
["LN05030330","Perform Functional Testing - Toroid (2ea) Spares","2007-05-10","2007-05-11"]
["LN05030335","Collect Component Performance Data (2ea) Spares","2007-05-14","2007-05-18"]
["LN05030340","Load Component Data Base (2ea) Spares","2007-05-21","2007-05-25"]
["LN05030345","Post Process & Test (2ea) Spares","2007-05-29","2007-06-04"]
["LN05030350","AVAIL: Toroids (2ea) Spares","2007-06-05","2007-06-04"]
["LN05030360","Develop General Specifications / Analysis","2005-11-30","2005-12-13"]
["LN05030370","Conduct Toroids PDR","2005-12-14","2006-01-04"]
["LN05030372","COMP: Toroid Design","2006-01-05","2006-01-04"]
["LN05030375","Generate Detailed Procurement Plan","2006-01-05","2006-02-02"]
["LN05030380","Conduct Toroids FDR","2006-01-05","2006-01-11"]
["LN05030385","Procure Component Material - Toroids","2006-02-03","2006-04-28"]
["LN05030390","Component Fab & Assembly - Toroids","2006-05-01","2006-07-25"]
["LN05030395","Perform Functional Testing - Toroids","2006-07-26","2006-08-22"]
["LN05030400","Post Process & Test","2006-08-23","2006-09-06"]
["LN05030405","AVAIL: Toroids Ready for BC1 Install","2006-09-07","2006-09-06"]
["LN05030410","AVAIL: Toroids Ready for BC2 Install","2006-09-07","2006-09-06"]
["LN05030415","AVAIL: Toroids Ready for LTU Install","2006-09-07","2006-09-06"]
["LN05040300","Procure Hardware Kit - Stoppers - SPARES","2006-10-03","2007-03-12"]
["LN05040305","AVAIL: Spares Hardware Kit - Stoppers","2007-03-13","2007-03-12"]
["LN05040310","Produce Common Layout","2005-11-15","2005-12-07"]
["LN05040315","Develop General Specifications / Analysis","2005-11-15","2005-11-30"]
["LN05040317","Create / Remodel / Revise Dsn Documentation","2005-11-15","2006-01-27"]
["LN05040320","Design Check","2005-11-15","2005-12-14"]
["LN05040325","Write Component Traveler","2005-12-15","2006-01-27"]
["LN05040330","Generate Detailed Procurement Plan","2006-01-30","2006-02-27"]
["LN05040335","Conduct Stoppers FDR","2006-02-28","2006-03-06"]
["LN05040337","COMP: Stopper Design","2006-03-07","2006-03-06"]
["LN05040340","Procure Component Material - Stoppers","2006-03-07","2006-05-01"]
["LN05040345","Component Fab & Assembly - Stoppers","2006-05-02","2006-07-26"]
["LN05040355","Perform Functional Testing - Stoppers","2006-07-27","2006-08-09"]
["LN05040360","Post Process & Test","2006-08-10","2006-08-23"]
["LN05040361","AVAIL: Stoppers Ready for BC1 Install","2006-08-24","2006-08-23"]
["LN05040365","Prep Bid Pak - Diagnostics Supports","2006-03-07","2006-03-20"]
["LN05040367","AWARD: Contract for Supports BC1","2006-03-21","2006-03-21"]
["LN05040370","Vendor Fab 1st Lot - Supports","2006-03-22","2006-05-16"]
["LN05040371","RCV: Supports from Vendor","2006-05-17","2006-05-16"]
["LN05040375","Procure Misc Materials - Diagnostics Supports","2006-03-07","2006-04-03"]
["LN05040380","Assemble Supports","2006-05-17","2006-06-14"]
["LN05040385","AVAIL: Supports Ready for Instl","2006-06-15","2006-06-14"]
["LN05040396","Produce Common Layout","2006-11-01","2006-11-21"]
["LN05040405","Develop General Specifications / Analysis","2006-11-01","2006-11-14"]
["LN05040415","Create / Remodel / Revise Dsn Documentation","2006-11-01","2007-01-12"]
["LN05040425","Design Check","2006-11-01","2006-11-30"]
["LN05040435","Write Component Traveler","2006-12-01","2007-01-12"]
["LN05040445","Generate Detailed Procurement Plan","2007-01-16","2007-02-12"]
["LN05040455","Conduct Stoppers FDR","2007-02-13","2007-02-20"]
["LN05040465","COMP: Stopper Design","2007-02-21","2007-02-20"]
["LN05040475","Procure Component Material - Stoppers","2007-02-21","2007-04-17"]
["LN05040485","Component Fab & Assembly - Stoppers","2007-04-18","2007-07-12"]
["LN05040495","Perform Functional Testing - Stoppers","2007-07-13","2007-07-26"]
["LN05040505","Post Process & Test","2007-07-27","2007-08-09"]
["LN05040525","AVAIL: Stoppers Ready for BC2 Install","2007-08-10","2007-08-09"]
["LN05040535","AVAIL: Stoppers Ready for LTU Install","2007-08-10","2007-08-09"]
["LN05040545","Prep Bid Pak - Diagnostics Supports","2007-02-21","2007-03-06"]
["LN05040555","AWARD: Contract for Supports BC2-LTU","2007-03-07","2007-03-07"]
["LN05040565","Vendor Fab 1st Lot - Supports","2007-03-08","2007-05-02"]
["LN05040575","RCV: Supports from Vendor","2007-05-03","2007-05-02"]
["LN05040585","Procure Misc Materials - Diagnostics Supports","2007-02-21","2007-03-20"]
["LN05040595","Assemble Supports","2007-05-03","2007-05-31"]
["LN05040605","AVAIL: Supports Ready for Instl","2007-06-01","2007-05-31"]
["LN05050400","AWARD: Contract - Profile Monitor (1ea) Spare","2006-10-03","2006-10-03"]
["LN05050405","Vendor Fab 1st Lot (1) Spare","2006-10-04","2006-11-14"]
["LN05050410","RCV: 1st Lot from Vendor (1) Spare","2006-11-15","2006-11-14"]
["LN05050415","Vendor Fab Remaining Lot (1) Spare","2006-11-15","2007-01-12"]
["LN05050420","RCV: Remaining from Vendor (1) Spare","2007-01-16","2007-01-12"]
["LN05050425","Procure Component Material - Profile - (1) SPARE","2006-10-03","2006-11-29"]
["LN05050430","Component Fab & Assembly - Profile Mon (1) Spare","2007-01-16","2007-03-13"]
["LN05050435","Develop General Specifications / Analysis","2005-11-01","2005-11-14"]
["LN05050440","Create / Remodel / Revise Dsn Documentation","2005-11-01","2005-11-14"]
["LN05050445","Perform QC / Metrology (1ea) Spare","2007-03-14","2007-03-27"]
["LN05050450","Perform Functional Testing - Profile Mo(1) Spare","2007-03-28","2007-04-24"]
["LN05050455","Collect Component Performance Data (1ea) Spare","2007-04-25","2007-04-26"]
["LN05050460","Load Component Data Base (1ea) Spare","2007-04-27","2007-05-02"]
["LN05050465","Post Process & Test (1ea) Spare","2007-05-03","2007-05-16"]
["LN05050470","AVAIL: Profile Monitor (1ea) Spare","2007-05-17","2007-05-31"]
["LN05050475","Design YAG Screen Option","2005-11-15","2006-01-27"]
["LN05050480","Design Phosphor Screen Option","2005-11-15","2006-01-27"]
["LN05050485","Design OTR Screen Options","2005-11-15","2006-01-27"]
["LN05050490","Design Check","2006-01-30","2006-03-27"]
["LN05050495","Write Component Traveler","2006-01-30","2006-01-30"]
["LN05050500","Conduct Profile Monitors PDR","2006-03-28","2006-04-03"]
["LN05050505","Generate Detailed Procurement Plan","2006-04-04","2006-04-04"]
["LN05050510","Conduct Profile Monitors FDR","2006-04-04","2006-04-10"]
["LN05050515","COMP: Profile Monitors Design","2006-04-11","2006-04-10"]
["LN05050516","Prep Bid Pak - Profile Monitors","2006-04-05","2006-04-11"]
["LN05050517","AWARD: Contract - Profile Monitor BC1,BC2","2006-04-12","2006-04-12"]
["LN05050520","Vendor Fab 1st Lot","2006-04-13","2006-06-08"]
["LN05050521","RCV: Profile Monitors 1st Lot","2006-06-09","2006-06-08"]
["LN05050525","Vendor Fab Remaining Lot","2006-04-13","2006-06-08"]
["LN05050530","Procure Profile Monitor Components","2006-04-11","2006-05-08"]
["LN05050531","RCV: Profile Monitors Final Lot","2006-06-09","2006-06-08"]
["LN05050535","Procure Component Material - Profile Monitors","2006-04-11","2006-05-08"]
["LN05050540","Component Fab & Assembly - Profile Monitors","2006-06-09","2006-08-04"]
["LN05050545","Perform QC / Metrology","2006-08-07","2006-08-11"]
["LN05050550","Perform Functional Testing - Profile Monitors","2006-08-14","2006-08-18"]
["LN05050555","Post Process & Test","2006-08-21","2006-08-25"]
["LN05050560","AVAIL: Provile Monitors Ready for BC1 Install","2006-08-28","2006-08-25"]
["LN05050565","AVAIL: Profile Monitors Ready for BC2 Install","2006-08-28","2006-08-25"]
["LN05050580","Procure Misc Materials - Diagnostics Supports","2006-04-11","2006-05-08"]
["LN05050581","Prep Bid Bak - Supports","2006-04-11","2006-04-17"]
["LN05050582","AWARD: Contract for Supports BC1,BC2","2006-04-18","2006-04-18"]
["LN05050583","Vendor Fab BC1-BC2 Suports","2006-04-19","2006-06-14"]
["LN05050584","RCV: Supports from Vendor","2006-06-15","2006-06-14"]
["LN05050585","Assemble Supports","2006-06-15","2006-07-13"]
["LN05050590","AVAIL: Supts Ready for BC1, BC2 Instl","2006-07-14","2006-07-14"]
["LN05050601","Develop General Specifications / Analysis","2006-10-02","2006-10-13"]
["LN05050606","Create / Remodel / Revise Dsn Documentation","2006-10-02","2006-10-13"]
["LN05050611","Design YAG Screen Option","2006-10-16","2006-12-12"]
["LN05050616","Design Phosphor Screen Option","2006-10-16","2006-12-12"]
["LN05050621","Design OTR Screen Options","2006-10-16","2006-12-12"]
["LN05050626","Design Check","2006-12-13","2007-02-23"]
["LN05050631","Write Component Traveler","2006-12-13","2006-12-13"]
["LN05050636","Conduct Profile Monitors PDR","2007-02-26","2007-03-02"]
["LN05050641","Generate Detailed Procurement Plan","2007-03-05","2007-03-05"]
["LN05050646","Conduct Profile Monitors FDR","2007-03-05","2007-03-09"]
["LN05050651","COMP: Profile Monitors Design","2007-03-12","2007-03-09"]
["LN05050656","Prep Bid Pak - Profile Monitors","2007-03-06","2007-03-12"]
["LN05050661","AWARD: Contract - Profile Monitor L03-LTU","2007-03-13","2007-03-13"]
["LN05050666","Vendor Fab L03-LTU","2007-03-14","2007-05-08"]
["LN05050671","RCV: Profile Monitors 1st Lot","2007-05-09","2007-05-08"]
["LN05050676","Vendor Fab Remaining Lot","2007-03-14","2007-05-08"]
["LN05050681","Procure Profile Monitor Components","2007-03-12","2007-04-06"]
["LN05050686","RCV: Profile Monitors Final Lot","2007-05-09","2007-05-08"]
["LN05050691","Procure Component Material - Profile Monitors","2007-03-12","2007-04-06"]
["LN05050696","Component Fab & Assembly - Profile Monitors","2007-05-09","2007-07-05"]
["LN05050701","Perform QC / Metrology","2007-07-06","2007-07-12"]
["LN05050706","Perform Functional Testing - Profile Monitors","2007-07-13","2007-07-19"]
["LN05050711","Post Process & Test","2007-07-20","2007-07-26"]
["LN05050726","AVAIL: Profile Monitors Ready for L03 Install","2007-07-27","2007-07-26"]
["LN05050731","AVAIL: Profile Monitors Ready for LTU Install","2007-07-27","2007-07-26"]
["LN05050736","Procure Misc Materials - Diagnostics Supports","2007-03-12","2007-04-06"]
["LN05050741","Prep Bid Bak - Supports","2007-03-12","2007-03-16"]
["LN05050746","AWARD: Contract for Supports L03-LTU","2007-03-19","2007-03-19"]
["LN05050751","Vendor Fab L03-LTU Suports","2007-03-20","2007-05-14"]
["LN05050756","RCV: Supports from Vendor","2007-05-15","2007-05-14"]
["LN05050761","Assemble Supports","2007-05-15","2007-06-12"]
["LN05050766","AVAIL: Supts Ready for L03, LTU Instl","2007-06-13","2007-06-13"]
["LN05070300","Procure Component Mtrl - Bunch Len - (1) SPARE","2006-10-03","2006-10-30"]
["LN05070305","Component Fab & Assy - Bunch Length (1ea) Spare","2006-10-31","2006-11-29"]
["LN05070320","Perform QC / Metrology (1ea) Spare","2006-11-30","2007-01-11"]
["LN05070325","Perform Func Testing - Bunch Length (1ea) Spare","2007-01-12","2007-01-16"]
["LN05070330","Collect Component Performance Data (1ea) Spare","2007-01-17","2007-01-18"]
["LN05070335","Load Component Data Base (1ea) Spare","2007-01-19","2007-01-22"]
["LN05070340","Post Process & Test (1ea) Spare","2007-01-23","2007-02-05"]
["LN05070345","AVAIL: Bunch Length Monitors (1ea) Spare","2007-02-06","2007-02-05"]
["LN05070350","Develop General Specifications / Analysis","2006-05-01","2006-05-05"]
["LN05070360","Create / Remodel / Revise Dsn Documentation","2006-05-01","2006-05-26"]
["LN05070380","Write Component Traveler","2006-05-30","2006-05-30"]
["LN05070390","Conduct B/L Monitors PDR","2006-05-31","2006-05-31"]
["LN05070400","Generate Detailed Procurement Plan","2006-06-01","2006-06-01"]
["LN05070410","Conduct B/L Monitors FDR","2006-06-02","2006-06-02"]
["LN05070420","COMP: B/L Monitors Design","2006-06-05","2006-06-02"]
["LN05070425","Procure Component Material - Bunch Length Mon","2006-06-05","2006-06-30"]
["LN05070430","Component Fab & Assembly - Bunch Length Monit","2006-07-03","2006-07-31"]
["LN05070440","Perform QC / Metrology","2006-08-01","2006-08-02"]
["LN05070450","Perform Functional Testing - Bunch Length Mon","2006-08-03","2006-08-09"]
["LN05070460","Collect Component Performance Data","2006-08-03","2006-08-09"]
["LN05070470","Post Process & Test","2006-08-10","2006-08-16"]
["LN05070480","AVAIL: Bnch Length Monitors Ready for BC1 Instl","2006-08-17","2006-08-16"]
["LN05070490","AVAIL: Bnch Length Monitors Ready for BC2 Instl","2006-08-17","2006-08-16"]
["LN05070500","AVAIL: Bnch Length Monitors Ready for LTU Instl","2006-08-17","2006-08-16"]
["LN05070510","Prep Bid Pak - Diagnostics Supports","2006-06-05","2006-06-05"]
["LN05070520","AWARD: Contract for Diagnostics Supports","2006-06-06","2006-06-06"]
["LN05070530","Vendor Fab 1st Lot - Supports","2006-06-07","2006-08-02"]
["LN05070540","RCV: 1st Lot of Supports","2006-08-03","2006-08-02"]
["LN05070550","Procure Misc Materials - Diagnostics Supports","2006-08-03","2006-08-30"]
["LN05070560","Assemble Supports","2006-08-31","2006-09-07"]
["LN05070570","AVAIL: Supports Ready for BC1, BC2, LTU Instl","2006-09-08","2006-09-07"]
["LN05080209","Write ICD - Beam Loss Monitor","2007-01-02","2007-01-08"]
["LN05080219","Produce Common Layout","2007-01-09","2007-02-06"]
["LN05080229","Develop General Specifications / Analysis","2007-02-07","2007-02-21"]
["LN05080239","Revise  Design Documentation","2007-02-22","2007-03-07"]
["LN05080259","Write Component Traveler","2007-03-08","2007-03-14"]
["LN05080269","Generate Detailed Procurement Plan","2007-03-15","2007-03-21"]
["LN05080279","Conduct Beam Loss Monitors FDR","2007-03-22","2007-03-28"]
["LN05080289","COMP: Beam Loss Monitors Design","2007-03-29","2007-03-28"]
["LN05080300","Procure Component Material - BLM - (2) SPARES","2006-10-03","2007-03-12"]
["LN05080302","Component Fab & Assy - Bm Lss Mon (2) Spares","2008-10-01","2009-02-04"]
["LN05080308","Perform QC / Metrology (2ea) Spares","2009-02-05","2009-02-18"]
["LN05080309","Procure Component Material - Beam Loss Monitors","2007-03-29","2007-06-21"]
["LN05080310","Perform Functional Testing - Bm Lss Mo(2) Spares","2009-02-19","2009-03-04"]
["LN05080312","Collect Component Performance Data (2ea) Spares","2009-03-05","2009-03-11"]
["LN05080314","Load Component Data Base (2ea) Spares","2009-03-12","2009-03-18"]
["LN05080316","Post Process & Test (2ea) Spares","2009-03-19","2009-03-25"]
["LN05080318","AVAIL: Beam Loss Monitor - (2ea) Spares","2009-03-26","2009-03-25"]
["LN05080319","Component Fab & Assembly - Beam Loss Monitors","2007-06-22","2007-07-20"]
["LN05080329","Perform Functional Testing - Beam Loss Monito","2007-07-23","2007-08-03"]
["LN05080339","Post Process & Test","2007-08-06","2007-08-17"]
["LN05080349","AVAIL: Bm Loss Monitor (PIC) Ready for L03 Instl","2007-08-20","2007-08-17"]
["LN05080359","AVAIL: Bm Loss Monitor (PIC) Ready for LTU Instl","2007-08-20","2007-08-17"]
["LN05080369","Prep Bid Pak - Diagnostics Supports","2007-03-29","2007-03-29"]
["LN05080379","AWARD: Contrct for Diagnostics Supports","2007-03-30","2007-03-30"]
["LN05080389","Vendor Fab Supports","2007-04-02","2007-04-27"]
["LN05080399","RCV: Diagnostics Supports from Vendor","2007-04-30","2007-04-27"]
["LN05080409","Procure Misc Materials - Diagnostics Supports","2007-04-30","2007-05-25"]
["LN05080419","Assemble Supports","2007-05-29","2007-06-25"]
["LN05080429","AVAIL: Supports Ready for L03, LTU Instl","2007-06-26","2007-06-25"]
["LN05080439","Write ICD - Beam Loss Monitor","2007-06-01","2007-06-07"]
["LN05080449","Produce Common Layout","2007-06-08","2007-07-06"]
["LN05080459","Develop General Specifications / Analysis","2007-07-09","2007-07-13"]
["LN05080469","Revise  Design Documentation","2007-07-16","2007-07-20"]
["LN05080489","Write Component Traveler","2007-07-23","2007-07-27"]
["LN05080499","Conduct Beam Loss Monitors PDR","2007-07-30","2007-08-03"]
["LN05080509","Generate Detailed Procurement Plan","2007-08-06","2007-08-06"]
["LN05080519","Conduct Beam Loss Monitors FDR","2007-08-07","2007-08-13"]
["LN05080529","COMP: Beam Loss Monitor Design","2007-08-14","2007-08-13"]
["LN05080539","Procure Component Material - Beam Loss Monitors","2007-08-14","2007-09-11"]
["LN05080549","Component Fab & Assembly - Beam Loss Monitors","2007-09-12","2007-12-06"]
["LN05080559","Perform Functional Testing - Beam Loss Monito","2007-12-07","2008-01-22"]
["LN05080569","Post Process & Test","2008-01-23","2008-02-20"]
["LN05080579","AVAIL: Bm Loss Monitor(PLIC) Ready for LTU Instl","2008-02-21","2008-02-20"]
["LN05080589","Prep Bid Pak - Diagnostics Supports","2007-08-14","2007-08-14"]
["LN05080599","AWARD: Contract for Diagnostics Supports","2007-08-15","2007-08-15"]
["LN05080609","Vendor Fab Supports","2007-08-16","2007-10-11"]
["LN05080619","RCV: Diagnostics Support from Vendor","2007-10-12","2007-10-11"]
["LN05080629","Procure Misc Materials - Diagnostics Supports","2007-10-12","2007-11-08"]
["LN05080639","Assemble Supports","2007-11-09","2007-11-26"]
["LN05080649","AVAIL: Supports Ready for LTU Instl","2007-11-27","2007-11-27"]
["LN05090300","Write ICD - Single Beam Dump","2006-10-03","2006-10-04"]
["LN05090310","Produce Common Layout","2006-10-05","2006-11-01"]
["LN05090320","Develop General Specifications / Analysis","2006-11-02","2006-11-15"]
["LN05090330","Create / Remodel / Revise Dsn Documentation","2006-11-16","2006-12-15"]
["LN05090340","Design Check","2007-01-02","2007-03-28"]
["LN05090350","Write Component Traveler","2007-01-02","2007-01-08"]
["LN05090370","Generate Detailed Procurement Plan","2007-01-09","2007-01-09"]
["LN05090390","COMP: Single Beam Dump Design","2007-03-29","2007-03-28"]
["LN05090391","Procure Component Material - Single Beam Dump","2007-03-29","2007-04-25"]
["LN05090400","Component Fab & Assembly - Single Beam Dump","2007-04-26","2007-05-23"]
["LN05090402","Post Process & Test","2007-05-24","2007-06-07"]
["LN05090403","AVAIL: Single Beam Dump Ready for LTU Install","2007-06-08","2007-06-07"]
["LN05090410","Prep Bid Pak - Diagnostics Supports","2007-05-24","2007-05-24"]
["LN05090420","AWARD: Contract for Daignostics Supports","2007-05-25","2007-05-25"]
["LN05090430","Vendor Fab Supports","2007-05-29","2007-08-21"]
["LN05090440","RCV: Diagnostics Supports from Vendor","2007-08-22","2007-08-21"]
["LN05090450","Procure Misc Materials - Diagnostics Supports","2007-08-22","2007-10-17"]
["LN05090460","Perform QC & Inspection - Diagnostic Supports","2007-10-18","2007-10-24"]
["LN05090470","Assemble Supports","2007-10-25","2007-11-07"]
["LN05090480","AVAIL: Supports Ready for LTU Installation","2007-11-08","2007-11-07"]
["LN05100301","Receive Electron Beam Dump Requirements","2006-10-03","2006-10-03"]
["LN05100310","Write ICD - Electron Beam Dump","2006-10-04","2006-10-04"]
["LN05100320","Collect Area Specific Requirements","2006-10-05","2006-10-11"]
["LN05100325","Engineering Analysis","2006-10-12","2006-10-18"]
["LN05100340","Produce Common Layout","2006-10-19","2006-10-25"]
["LN05100350","Develop General Specifications / Analysis","2006-10-26","2006-11-01"]
["LN05100360","Create / Remodel / Revise Dsn Documentation","2006-11-02","2006-12-01"]
["LN05100370","Write Component Traveler","2006-12-04","2006-12-04"]
["LN05100380","Conduct Electron Beam Dump PDR","2006-12-05","2006-12-05"]
["LN05100390","Generate Detailed Procurement Plan","2006-12-06","2006-12-06"]
["LN05100400","Conduct Electron Beam Dump FDR","2006-12-07","2006-12-07"]
["LN05100402","COMP: Electron Beam Dump Design","2006-12-08","2006-12-07"]
["LN05100410","Procure Component Material - Electron Beam Dump","2006-12-08","2007-03-20"]
["LN05100415","Component Fab & Assembly - Electron Beam Dump","2007-03-21","2007-06-13"]
["LN05100420","Perform QC / Metrology","2007-06-14","2007-06-20"]
["LN05100430","Post Process & Test","2007-06-21","2007-07-05"]
["LN05100433","AVAIL: Electron Beam Dump Ready for LTU Instl","2007-07-06","2007-07-05"]
["LN05100440","Prep Bid Pak - Diagnostics Supports","2006-12-08","2006-12-08"]
["LN05100450","Evaluate Vendor Proposals - Supports","2006-12-11","2006-12-11"]
["LN05100460","AWARD: Contract for Diagnostics Supports","2006-12-12","2006-12-12"]
["LN05100470","Vendor Fab Diagnostics Supports","2006-12-13","2007-01-25"]
["LN05100480","RCV: Daignostics Support from Vendor","2007-01-26","2007-01-25"]
["LN05100490","Procure Misc Materials - Diagnostics Supports","2007-01-26","2007-03-09"]
["LN05100500","Perform QC & Inspection - Diagnostic Supports","2007-03-12","2007-03-12"]
["LN05100510","Assemble Supports","2007-03-13","2007-03-26"]
["LN05100521","AVAIL: Supports Ready for Installation","2007-03-27","2007-03-26"]
["LN05110400","Procure Hardware - Protection Collimatr - SPARES","2006-10-03","2006-10-30"]
["LN05110406","Write ICD - Protection Collimator","2006-03-01","2006-03-02"]
["LN05110426",null,"2005-05-02","2005-05-02"]
["LN05110446","Produce Common Layout","2006-03-03","2006-03-09"]
["LN05110456","Develop General Specifications / Analysis","2006-03-10","2006-03-13"]
["LN05110466","Create / Remodel / Revise Dsn Documentation","2006-03-14","2006-05-08"]
["LN05110467","Design Check","2006-03-14","2006-05-08"]
["LN05110476","Write Component Traveler","2006-05-09","2006-05-12"]
["LN05110486","Conduct Protection Collimator PDR","2006-05-15","2006-05-15"]
["LN05110496","Generate Detailed Procurement Plan","2006-05-16","2006-05-16"]
["LN05110506","Conduct Protection Collimator FDR","2006-05-17","2006-05-17"]
["LN05110516","COMP: Protection Collimator Design","2006-05-18","2006-05-17"]
["LN05110526","Prep Bid Pak - Protection Collimator","2006-05-18","2006-05-19"]
["LN05110536","RELEASE: RFP - Protection Collimators","2006-05-22","2006-05-19"]
["LN05110546","Vendors Prep Proposals - Protection Collimator","2006-05-22","2006-06-19"]
["LN05110556","RCV: Proposals from Vendors","2006-06-20","2006-06-19"]
["LN05110566","Evaluate Vendor Proposals","2006-06-20","2006-06-23"]
["LN05110576","AWARD: Contract - Protection Collimator","2006-06-26","2006-06-26"]
["LN05110586","Vendor Fab 1st Lot","2006-06-27","2006-07-25"]
["LN05110596","RCV: 1st Lot Diagnostics Equip from Vendor","2006-07-26","2006-07-25"]
["LN05110606","Procure Component Material - Protection Collimat","2006-05-18","2006-06-15"]
["LN05110616","Component Fab & Assembly - Protection Collimat","2006-07-26","2006-08-22"]
["LN05110646","Post Process & Test","2006-08-23","2006-09-06"]
["LN05110656","AVAIL: Protection Collimator Ready for BC1 Instl","2006-09-07","2006-09-06"]
["LN05110657","AVAIL: Protection Collimator Ready for BC2 Instl","2006-09-07","2006-09-06"]
["LN05110658","AVAIL: Protection Collimator Ready for LTU Instl","2006-09-07","2006-09-06"]
["LN05110668","Prep Bid Pak - Diagnostics Supports","2006-05-18","2006-05-18"]
["LN05110678","RELEASE: RFP - Diagnostics Supports","2006-05-19","2006-05-18"]
["LN05110688","Vendors Prep Proposals - Supports","2006-05-19","2006-06-16"]
["LN05110708","Evaluate Vendor Proposals - Supports","2006-06-19","2006-06-22"]
["LN05110710","AWARD: Contract for Supports","2006-06-23","2006-06-23"]
["LN05110718","Vendor Fab 1st Lot - Supports","2006-06-26","2006-07-24"]
["LN05110728","RCV: 1st Lot Diagnostics Supports from Vendor","2006-07-25","2006-07-24"]
["LN05110738","Procure Misc Materials - Diagnostics Supports","2006-05-18","2006-06-15"]
["LN05110788","Assemble Supports","2006-07-25","2006-08-01"]
["LN05110808","AVAIL: Supports Ready for BC1, BC2, LTU Instl","2006-08-02","2006-08-01"]
["LN05120371","Produce Common Layout","2005-11-01","2005-11-30"]
["LN05120381","Develop General Specifications / Analysis","2005-12-01","2005-12-14"]
["LN05120391","Create / Remodel / Revise Dsn Documentation","2005-09-20","2005-12-14"]
["LN05120400","Procure Hardware - Movable Collimator - SPARES","2006-10-03","2007-01-11"]
["LN05120401","Write Component Traveler","2005-12-15","2006-01-06"]
["LN05120421","Generate Detailed Procurement Plan","2006-01-09","2006-01-09"]
["LN05120441","COMP: Movable Collimator Design","2006-01-10","2006-01-09"]
["LN05120451","RELEASE: RFP - Movable Collimators","2006-01-10","2006-01-09"]
["LN05120461","Vendors Prep Proposals - Movable Collimator","2006-01-10","2006-02-07"]
["LN05120471","RCV: Proposals from Vendors","2006-02-08","2006-02-07"]
["LN05120481","Evaluate Vendor Proposals","2006-02-08","2006-02-13"]
["LN05120485","AWARD: Contract - BC1 Movable Collimator","2006-02-14","2006-02-14"]
["LN05120491","Vendor Fab 1st Lot","2006-02-15","2006-03-15"]
["LN05120501","RCV: 1st Lot Diagnostics Equip from Vendor","2006-03-16","2006-03-15"]
["LN05120511","Procure Component Material - Movable Collimator","2006-04-10","2006-07-03"]
["LN05120521","Component Fab & Assembly - Movable Collimator","2006-05-08","2006-08-01"]
["LN05120531","Perform QC / Metrology","2006-08-02","2006-08-15"]
["LN05120541","Perform Functional Testing - Movable Collimat","2006-08-16","2006-08-29"]
["LN05120551","Post Process & Test","2006-08-30","2006-09-13"]
["LN05120561","AVAIL: Movable Collimators Ready for BC1 Instl","2006-09-14","2006-09-13"]
["LN05120571","Prep Bid Pak - Diagnostics Supports","2006-01-10","2006-01-11"]
["LN05120581","RELEASE: RFP - Diagnostics Supports","2006-01-12","2006-01-11"]
["LN05120591","Vendors Prep Proposals - Supports","2006-01-12","2006-02-09"]
["LN05120601","RCV: Proposals from Vendors - Supports","2006-02-10","2006-02-09"]
["LN05120611","Evaluate Vendor Proposals - Supports","2006-02-10","2006-02-15"]
["LN05120615","AWARD: BC1 Contract for Supports","2006-02-16","2006-02-16"]
["LN05120621","Vendor Fab 1st Lot - Supports","2006-02-17","2006-03-17"]
["LN05120631","RCV: 1st Lot Diagnostics Supports from Vendor","2006-03-20","2006-03-17"]
["LN05120641","Procure Misc Materials - Diagnostics Supports","2006-04-10","2006-05-05"]
["LN05120651","Assemble Supports","2006-05-08","2006-05-19"]
["LN05120671","AVAIL: Supports Ready for BC1 Instl","2006-05-22","2006-05-19"]
["LN05120680","Produce Common Layout","2007-05-01","2007-05-29"]
["LN05120685","Develop General Specifications / Analysis","2007-05-30","2007-06-12"]
["LN05120690","Create / Remodel / Revise Dsn Documentation","2007-03-20","2007-06-12"]
["LN05120695","Write Component Traveler","2007-06-13","2007-06-20"]
["LN05120700","Generate Detailed Procurement Plan","2007-06-21","2007-06-21"]
["LN05120705","COMP: Movable Collimator Design","2007-06-22","2007-06-21"]
["LN05120710","RELEASE: RFP - Movable Collimators","2007-06-22","2007-06-21"]
["LN05120715","Vendors Prep Proposals - Movable Collimator","2007-06-22","2007-07-20"]
["LN05120720","RCV: Proposals from Vendors","2007-07-23","2007-07-20"]
["LN05120725","Evaluate Vendor Proposals","2007-07-23","2007-07-26"]
["LN05120730","AWARD: Contract - LTU Movable Collimator","2007-07-27","2007-07-27"]
["LN05120735","Vendor Fab 1st Lot","2007-07-30","2007-08-24"]
["LN05120740","RCV: 1st Lot Diagnostics Equip from Vendor","2007-08-27","2007-08-24"]
["LN05120745","Procure Component Material - Movable Collimator","2007-06-22","2007-09-17"]
["LN05120750","Component Fab & Assembly - Movable Collimator","2007-08-27","2007-11-19"]
["LN05120755","Perform QC / Metrology","2007-11-20","2007-12-05"]
["LN05120760","Perform Functional Testing - Movable Collimat","2007-12-06","2008-01-04"]
["LN05120765","Post Process & Test","2008-01-07","2008-01-18"]
["LN05120770","AVAIL: Movable Collimators Ready for LTU Instl","2008-01-22","2008-01-18"]
["LN05120775","Prep Bid Pak - Diagnostics Supports","2007-06-22","2007-06-25"]
["LN05120780","RELEASE: RFP - Diagnostics Supports","2007-06-26","2007-06-25"]
["LN05120785","Vendors Prep Proposals - Supports","2007-06-26","2007-07-24"]
["LN05120790","RCV: Proposals from Vendors - Supports","2007-07-25","2007-07-24"]
["LN05120795","Evaluate Vendor Proposals - Supports","2007-07-25","2007-07-30"]
["LN05120800","AWARD: LTU Contract for Supports","2007-07-31","2007-07-31"]
["LN05120805","Vendor Fab 1st Lot - Supports","2007-08-01","2007-08-28"]
["LN05120810","RCV: 1st Lot Diagnostics Supports from Vendor","2007-08-29","2007-08-28"]
["LN05120815","Procure Misc Materials - Diagnostics Supports","2007-08-01","2007-08-28"]
["LN05120820","Assemble Supports","2007-08-29","2007-09-12"]
["LN05120825","AVAIL: Supports Ready for LTU Instl","2007-09-13","2007-09-12"]
["LN05130400","Procure Hardware - Single Beam Dump - SPARES","2006-10-03","2006-11-29"]
["LN05130410","Write ICD - Single Beam Dump","2007-05-15","2007-05-21"]
["LN05130420","Produce Common Layout","2007-05-22","2007-05-29"]
["LN05130430","Develop General Specifications / Analysis","2007-05-30","2007-06-05"]
["LN05130440","Create / Remodel / Revise Dsn Documentation","2007-06-06","2007-07-03"]
["LN05130450","Design Check","2007-07-05","2007-08-29"]
["LN05130460","Write Component Traveler","2007-07-05","2007-07-11"]
["LN05130470","Conduct Single Beam Dump PDR","2007-07-12","2007-07-18"]
["LN05130480","Generate Detailed Procurement Plan","2007-07-19","2007-07-19"]
["LN05130490","Conduct Single Beam Dump FDR","2007-07-20","2007-07-26"]
["LN05130500","COMP: Single Beam Dump Design","2007-08-30","2007-08-29"]
["LN05130501","Prep Bid Pak - Safety Dump","2007-08-30","2007-08-30"]
["LN05130502","AWARD: Contract for Safety Dump","2007-08-31","2007-08-31"]
["LN05130503","Vendor Fab - Safety Dump","2007-09-04","2007-10-29"]
["LN05130504","RCV: Saftey Dump from Vendor","2007-10-30","2007-10-30"]
["LN05130510","Procure Component Material - Single Beam Dump","2007-08-30","2007-09-27"]
["LN05130520","Component Fab & Assembly - Single Beam Dump","2007-10-31","2007-11-29"]
["LN05130530","Post Process & Test","2007-11-30","2007-12-13"]
["LN05130540","AVAIL: Single Beam Dump Ready for LTU Install","2007-12-14","2007-12-13"]
["LN05130560","Assemble Supports","2007-11-29","2007-12-12"]
["LN05130570","AVAIL: Supports Ready for LTU Instl","2007-12-13","2007-12-12"]
["LN05130580","AWARD: Contract for Diagnostics Supports","2007-08-30","2007-08-30"]
["LN05130590","Vendor Fab Diagnostics Supports","2007-08-31","2007-10-26"]
["LN05130600","RCV: Diagnostics Supports from Vendor","2007-10-29","2007-10-29"]
["LN05130610","Procure Misc Materials - Diagnostics Supports","2007-10-30","2007-11-28"]
["LN06","LINAC RF SUBSYSTEM SUMMARY","2005-05-02","2008-01-02"]
["LN0601","S-BAND LOW LEVEL RF SYSTEM SUMMARY","2005-05-02","2006-09-08"]
["LN06010005","Prepare for Final Desgin Review (FDR)","2005-05-02","2005-05-20"]
["LN06010010","Conduct S-Band Low Level FDR","2005-05-23","2005-05-23"]
["LN06010015","COMP: S-Band Low Level Design","2005-05-24","2005-05-23"]
["LN06010020","Generate Detailed Procurement Plan","2005-05-24","2005-06-07"]
["LN06010025","Procure Coupler Connectors","2005-06-08","2005-08-31"]
["LN06010030","Cold Test & Fab - S-Band Low Level Equipment","2005-09-01","2005-09-15"]
["LN06010035","AVAIL: S-Band Low Level Equipment Ready for Inst","2005-09-16","2005-09-15"]
["LN06010045","Purchase Coupler Materials (5)","2005-05-24","2005-06-07"]
["LN06010055","Fabricate Coupler Spools (5)","2005-06-08","2005-06-21"]
["LN06010060","Design Input WG Modifications","2005-05-02","2005-06-27"]
["LN06010065","Assemble Coupler Spools (5)","2005-06-22","2005-07-06"]
["LN06010075","Purchase Input Materials (2)","2005-05-24","2005-07-20"]
["LN06010085","Fabricate Input WG (2)","2005-07-21","2005-08-03"]
["LN06010095","Assemble Input WG (2)","2005-08-04","2005-08-17"]
["LN0602","S-BAND HP WAVEGUIDE SYSTEM SUMMARY","2005-05-02","2006-09-08"]
["LN06020005","Design S-Band Waveguide","2005-05-02","2005-06-15"]
["LN06020010","Design WG Supports","2005-06-16","2005-06-29"]
["LN06020025","Prepare for Prelim Design Review (PDR)","2005-06-30","2005-07-05"]
["LN06020030","Conduct Prelim Design Rev - S-Band HP WG System","2005-07-06","2005-07-06"]
["LN06020035","Generate Detailed Procurement Plan","2005-07-07","2005-07-07"]
["LN06020040","Create Cold Test Plan","2005-07-08","2005-07-14"]
["LN06020045","Establish Subordinate Work Orders","2005-07-15","2005-07-15"]
["LN06020050","Prepare for Final Desgin Review (FDR)","2005-07-18","2005-07-20"]
["LN06020055","Conduct Final Design Rev - S-Band HP WG System","2005-07-21","2005-07-21"]
["LN06020060","COMP: S-Band HP WG System Design","2005-07-22","2005-07-21"]
["LN06020062","RELEASE: RFP - Skarpass Flanges","2005-08-05","2005-08-04"]
["LN06020064","Vendors Prep Proposals - S-Band HP Sys Component","2005-08-05","2005-08-18"]
["LN06020065","Prep Bid Pak - Skarpass Flanges","2005-07-22","2005-08-04"]
["LN06020066","RCV: Proposals from Vendors","2005-08-19","2005-08-18"]
["LN06020068","Evaluate Vendor Proposals","2005-08-19","2005-09-01"]
["LN06020070","AWARD: Contract for Skarpass Flanges","2005-10-03","2005-10-03"]
["LN06020072","Vendor Fab - Skarpass Flanges","2005-10-04","2006-01-12"]
["LN06020090","RELEASE: RFP - S-Band Waveguide","2005-08-05","2005-08-24"]
["LN06020092","Vendors Prep Proposals - S-Band Waveguide","2005-08-25","2005-09-08"]
["LN06020094","RCV: Proposals from Vendors","2005-09-09","2005-09-08"]
["LN06020096","Evaluate Vendor Proposals","2005-09-09","2005-09-22"]
["LN06020098","AWARD: Contract - S-Band Waveguide","2005-09-23","2005-10-12"]
["LN06020100","Vendor Fab & Assy - S-Band Waveguide","2005-10-13","2006-02-07"]
["LN06020105","RCV: from Vendor S-Band Waveguide","2006-02-08","2006-02-07"]
["LN06020115","Procure Waveguide Cooling","2005-07-22","2005-09-30"]
["LN06020120","RCV: Waveguide Cooling","2005-10-03","2005-09-30"]
["LN06020125","Procure Assembly Hardware","2005-10-03","2005-10-28"]
["LN06020130","RCV: Assembly Hardware","2005-10-31","2005-10-28"]
["LN06020135","Fab & Cold Test - Cold Test Hardware","2006-01-13","2006-03-20"]
["LN06020140","Fab & Cold Test - Waveguide Straights","2006-02-21","2006-05-01"]
["LN06020145","Fab & Cold Test - Waveguide Components","2006-04-04","2006-06-13"]
["LN06020150","Fab & Test - Waveguide Supports","2006-06-14","2006-07-19"]
["LN06020155","Collect Component Performance Data","2006-07-20","2006-07-26"]
["LN06020160","Load Component Data Base","2006-07-20","2006-07-26"]
["LN06020165","Receive System / Sub Assemblies","2006-07-27","2006-07-27"]
["LN06020170","Post Process Waveguide","2006-07-28","2006-09-08"]
["LN06020174","RCV: Skarpass Flanges from Vendor","2006-01-13","2006-01-12"]
["LN06020185","AVAIL: S-Band High Pwr Equip L01 Ready for Instl","2006-09-11","2006-09-08"]
["LN06020188","Prep Bid Pak - S-Band Waveguide","2005-07-22","2005-08-04"]
["LN06020190","AVAIL: S-Band High Pwr Equip BC1 Ready for Instl","2006-09-11","2006-09-08"]
["LN06020195","AVAIL: S-Band High Pwr Equip L02 Ready for Instl","2006-09-11","2006-09-08"]
["LN06020200","AVAIL: S-Band High Pwr Equip BC2 Ready for Instl","2006-09-11","2006-09-08"]
["LN06020205","AVAIL: S-Band High Pwr Equip L03 Ready for Instl","2006-09-11","2006-09-08"]
["LN0603","S-BAND STRUCTURES SUMMARY","2005-05-02","2005-08-31"]
["LN06030000","RCV: 9.5ft Structures & Strongbacks","2005-05-02","2005-04-29"]
["LN06030005","RF Evaluation of 9.5ft Structures & Strongbacks","2005-05-02","2005-05-13"]
["LN06030010","Design Strongback Girder Supports","2005-05-16","2005-05-27"]
["LN06030020","Design TV Section Supports","2005-05-31","2005-06-06"]
["LN06030025","Prepare for Prelim Design Review (PDR)","2005-06-07","2005-06-09"]
["LN06030030","Conduct Prelim Design Review (PDR) - S Bnd Struc","2005-06-10","2005-06-10"]
["LN06030035","Generate Detailed Procurement Plan","2005-06-13","2005-06-13"]
["LN06030040","Create Cold Test Plan","2005-06-14","2005-06-20"]
["LN06030045","Establish Subordinate Work Orders","2005-06-21","2005-06-21"]
["LN06030050","Prepare for Final Desgin Review (FDR)","2005-06-22","2005-06-24"]
["LN06030055","Conduct Final Design Review (FDR) - S Bnd Struc","2005-06-27","2005-06-27"]
["LN06030060","COMP: S-Band Structures Design","2005-06-28","2005-06-27"]
["LN06030075","Bead Pull Structures","2005-06-28","2005-07-19"]
["LN06030090","Fabricate 9.5ft Supports","2005-07-20","2005-07-26"]
["LN06030100","Collect Component Performance Data","2005-07-27","2005-08-02"]
["LN06030105","Load Component Data Base","2005-08-03","2005-08-09"]
["LN06030110","Receive System / Sub Assemblies","2005-08-10","2005-08-10"]
["LN06030115","Post Process 9.5 ft Structures","2005-08-11","2005-08-31"]
["LN06030130","AVAIL: S-Band Structures Ready for L01 Instl","2005-09-01","2005-08-31"]
["LN06030135","AVAIL: S-Band Structures Ready for BC1 Instl","2005-09-01","2005-08-31"]
["LN0604","X-BAND LOW LEVEL RF SUMMARY","2005-05-02","2006-09-06"]
["LN06040004","Write X-Band LLRF ICD","2005-05-02","2005-07-15"]
["LN06040008","Design X-Band LLRF System","2005-10-03","2005-10-24"]
["LN06040010","Conduct Prelim Dsign Review (PDR) - X Bnd LL Sys","2005-10-25","2005-10-25"]
["LN06040012","Design X-Band LLRF System","2005-10-26","2005-11-16"]
["LN06040014","Conduct Final Design Review (FDR) - X Bnd LL Sys","2005-11-17","2005-11-17"]
["LN06040016","COMP: X-Band Low Level RF Design","2005-11-18","2005-11-17"]
["LN06040018","Prep Bid Pak - X-Band Analyzer","2005-07-01","2005-07-15"]
["LN06040020","RELEASE: RFP - X-Band Analyzer","2005-07-18","2005-07-15"]
["LN06040022","Vendors Prep Proposals - X-Band Analyzer","2005-07-18","2005-07-29"]
["LN06040024","RCV: Proposals from Vendors","2005-08-01","2005-07-29"]
["LN06040026","Evaluate Vendor Proposals","2005-08-01","2005-08-12"]
["LN06040028","AWARD: Contract X-Band Analyzer","2005-08-15","2005-08-15"]
["LN06040030","Vendor Fab & Assy - X-Band Analyzer","2005-08-16","2006-02-21"]
["LN06040032","RCV: X-Band Analyzer","2006-02-22","2006-02-21"]
["LN06040055","Procure X-Band TWT Driver - SPARE","2006-10-03","2007-08-29"]
["LN06040060","RCV: X-Band TWT Driver - SPARE","2007-08-30","2007-08-29"]
["LN06040075","Procure X-Band 4 X Multiplier - SPARE","2006-10-03","2007-08-29"]
["LN06040080","RCV: X-Band 4 X Multiplier - SPARE","2007-08-30","2007-08-29"]
["LN06040095","Procure X-Band Phase & Amp Dectector - SPARE","2006-10-03","2007-08-29"]
["LN06040100","RCV: X-Band Phase & Amp Dectector - SPARE","2007-08-30","2007-08-29"]
["LN06040125","Procure X-Band Strpline Couplers - SPARE","2006-10-03","2007-08-29"]
["LN06040130","RCV: X-Band Strpline Couplers - SPARE","2007-08-30","2007-08-29"]
["LN06040140","Prep Bid Pak - X-Band TWT Driver","2005-11-18","2005-12-05"]
["LN06040142","RELEASE: RFP - X-Band TWT Driver","2005-12-06","2005-12-05"]
["LN06040144","Vendors Prep Proposals - X-Band TWT Driver","2005-12-06","2006-01-03"]
["LN06040146","RCV: Proposals from Vendors","2006-01-04","2006-01-03"]
["LN06040148","Evaluate Vendor Proposals","2006-01-04","2006-01-18"]
["LN06040150","AWARD: Contract X-Band TWT Driver","2006-01-19","2006-01-19"]
["LN06040152","Vendor Fab & Assy - X-Band TWT Driver","2006-01-20","2006-07-11"]
["LN06040154","RCV: X-Band TWT Driver","2006-07-12","2006-07-11"]
["LN06040164","Prep Bid Pak - X-Band Phase & Amp Dectector","2005-11-18","2005-12-05"]
["LN06040166","RELEASE: RFP - X-Band Phase & Amp Dectector","2005-12-06","2005-12-05"]
["LN06040168","Vendors Prep Proposals - X-Band Phase & Amp D","2005-12-06","2006-01-03"]
["LN06040170","RCV: Proposals from Vendors","2006-01-04","2006-01-03"]
["LN06040172","Evaluate Vendor Proposals","2006-01-04","2006-01-18"]
["LN06040174","AWARD: Contract X-Band Phase & Amp Dectector","2006-01-19","2006-01-19"]
["LN06040176","Vendor Fab & Assy - X-Band Phase & Amp Dectector","2006-01-20","2006-07-11"]
["LN06040178","RCV: X-Band Phase & Amp Dectector","2006-07-12","2006-07-11"]
["LN06040180","Procure X-Band 4 X Multiplier","2005-11-18","2006-05-25"]
["LN06040182","RCV: X-Band 4 X Multiplier","2006-05-26","2006-05-25"]
["LN06040184","Procure X-Band RF Cables","2005-11-18","2006-05-25"]
["LN06040186","RCV: X-Band RF Cables","2006-05-26","2006-05-25"]
["LN06040188","Procure X-Band Strpline Couplers","2005-11-18","2006-05-25"]
["LN06040190","RCV: X-Band Strpline Couplers","2006-05-26","2006-05-25"]
["LN06040192","Procure X-Band Chassis","2005-11-18","2006-05-25"]
["LN06040194","RCV: X-Band Chassis","2006-05-26","2006-05-25"]
["LN06040196","Procure X-Band Drive Monitoring","2005-11-18","2006-05-25"]
["LN06040198","RCV: X-Band Drive Monitoring","2006-05-26","2006-05-25"]
["LN06040200","Assemble X-Band LLRF Equipment","2006-07-12","2006-08-01"]
["LN06040205","Test X-Band LLRF Equipment","2006-08-02","2006-08-22"]
["LN06040210","Collect Component Performance Data","2006-08-23","2006-08-29"]
["LN06040215","Load Component Data Base","2006-08-30","2006-09-06"]
["LN06040220","AVAIL: X-Band LLRF Equip Ready for BC1 Install","2006-09-07","2006-09-06"]
["LN0605","X-BAND HIGH POWER RF SUMMARY","2005-05-02","2006-08-21"]
["LN06051","X-BAND HP KLYSTRON SUMMARY","2005-05-02","2006-08-21"]
["LN06051025","Design Kylstron Mount","2005-07-06","2005-07-06"]
["LN06051030","Design Klystron Gallery Tank","2005-05-02","2005-06-01"]
["LN06051035","Conduct Prelim Design Review (PDR) - X Bnd HP Ky","2005-07-07","2005-07-13"]
["LN06051040","Release Long Lead Procurements","2005-07-14","2005-07-13"]
["LN06051045","Create Cold Test Plan","2005-07-14","2005-07-20"]
["LN06051050","Establish Subordinate Work Orders","2005-07-21","2005-07-21"]
["LN06051052","Conduct Final Design Review (FDR) - X Bnd HP Ky","2005-07-22","2005-07-22"]
["LN06051054","COMP: X-Band Klystron Design","2005-07-25","2005-07-22"]
["LN06051072","AWARD: X-Band Klystrons","2005-07-06","2005-07-06"]
["LN06051074","Vendor Fab & Assy - X-Band Klystrons","2005-07-25","2006-05-22"]
["LN06051076","RCV: X-Band Klystrons","2006-05-23","2006-05-22"]
["LN06051078","Procure Mounting Support","2005-07-25","2006-05-22"]
["LN06051080","RCV: Mounting Support","2006-05-23","2006-05-22"]
["LN06051082","Prep Bid Pak - X-Band Klystron","2006-11-10","2006-11-16"]
["LN06051084","RELEASE: RFP - X-Band Klystron","2006-11-17","2006-11-16"]
["LN06051086","Vendors Prep Proposals - Klystron System","2006-11-17","2006-12-04"]
["LN06051088","RCV: Vendor Proposals - X-Band Klystron","2006-12-05","2006-12-04"]
["LN06051090","Evaluate Vendor Proposals - Klystron System","2006-12-05","2006-12-11"]
["LN06051092","AWARD: X-Band Klystrons (Spares)","2006-12-12","2006-12-12"]
["LN06051100","Vendor Fab & Assy -X-Band Klystrons - SPARE","2006-12-13","2007-11-07"]
["LN06051105","RCV: X-Band Klystrons - SPARE","2007-11-08","2007-11-07"]
["LN06051110","Procure Mounting Support - SPARE","2006-10-03","2007-08-29"]
["LN06051115","RCV: Mounting Support - SPARE","2007-08-30","2007-08-29"]
["LN06051120","Fab & Assemble X-Band Klystron","2006-05-23","2006-07-31"]
["LN06051125","Fab & Asemble Mounting Support","2006-05-23","2006-05-30"]
["LN06051130","Fab & Assemble System Window","2006-05-23","2006-06-13"]
["LN06051135","Test System Window","2006-06-14","2006-06-27"]
["LN06051140","Fab & Assemble X-Band Klystron - SPARE","2006-10-03","2007-03-12"]
["LN06051145","Fab & Asemble Mounting Support - SPARE","2007-08-30","2007-09-06"]
["LN06051150","Collect Component Performance Data","2006-06-28","2006-06-29"]
["LN06051155","Load Component Data Base","2006-06-30","2006-07-03"]
["LN06051165","Dress Klystron","2006-08-01","2006-08-07"]
["LN06051170","Test Klystron System","2006-08-08","2006-08-21"]
["LN06051175","AVAIL: X-Band HP Klystrons Ready for BC1 Install","2006-08-22","2006-08-21"]
["LN06052","X-BAND HP MODULATOR SUMMARY","2005-08-25","2006-07-17"]
["LN06052020","Design Modulator","2005-12-01","2006-01-04"]
["LN06052025","Modulator Documentation","2006-01-05","2006-02-01"]
["LN06052030","Conduct Prelim Dsign Review (PDR) - X Bnd HP Mod","2006-02-02","2006-02-06"]
["LN06052035","Release Long Lead Procurements","2006-02-07","2006-02-06"]
["LN06052040","Create Cold Test Plan","2006-02-07","2006-02-21"]
["LN06052045","Establish Subordinate Work Orders","2006-02-22","2006-02-22"]
["LN06052050","Conduct Final Design Review (FDR) - X Bnd HP Mod","2006-02-23","2006-03-22"]
["LN06052055","COMP: X-Band Modulator Design","2006-03-23","2006-03-22"]
["LN06052060","Procure Tank","2006-03-23","2006-04-21"]
["LN06052065","RCV: Tank","2006-04-24","2006-04-24"]
["LN06052070","Procure Pulsed Transformer","2006-03-23","2006-04-21"]
["LN06052075","RCV: Pulsed Transformer","2006-04-24","2006-04-24"]
["LN06052080","Procure Cap Divider","2006-03-23","2006-04-21"]
["LN06052085","RCV: Cap Divider","2006-04-24","2006-04-24"]
["LN06052090","Procure Heater Isolation","2006-03-23","2006-04-21"]
["LN06052095","RCV: Heater Isolation","2006-04-24","2006-04-24"]
["LN06052100","Procure Toroid & Misc","2006-03-23","2006-04-21"]
["LN06052105","RCV: Toroid & Misc","2006-04-24","2006-04-24"]
["LN06052110","Procure Interlocks","2006-03-23","2006-04-21"]
["LN06052115","RCV: Interlocks","2006-04-24","2006-04-24"]
["LN06052120","Procure HV Connectors","2006-03-23","2006-04-21"]
["LN06052125","RCV: HV Connectors","2006-04-24","2006-04-24"]
["LN06052130","Procure Magnet Power Supply","2005-08-25","2006-04-21"]
["LN06052135","RCV: Magnet Power Supply","2006-04-24","2006-04-24"]
["LN06052140","Procure Power Supply Cabling","2006-03-23","2006-04-21"]
["LN06052145","RCV: Power Supply Cabling","2006-04-24","2006-04-24"]
["LN06052160","Procure Tank - SPARE","2006-10-03","2007-08-29"]
["LN06052165","RCV: Tank - SPARE","2007-08-30","2007-08-29"]
["LN06052170","Procure Pulsed Transformer - SPARE","2006-10-03","2007-08-29"]
["LN06052175","RCV: Pulsed Transformer - SPARE","2007-08-30","2007-08-29"]
["LN06052180","Procure Cap Divider - SPARE","2006-10-03","2007-08-29"]
["LN06052185","RCV: Cap Divider - SPARE","2007-08-30","2007-08-29"]
["LN06052190","Procure Heater Isolation - SPARE","2006-10-03","2007-08-29"]
["LN06052195","RCV: Heater Isolation - SPARE","2007-08-30","2007-08-29"]
["LN06052200","Procure Toroid & Misc - SPARE","2006-10-03","2007-08-29"]
["LN06052205","RCV: Toroid & Misc - SPARE","2007-08-30","2007-08-29"]
["LN06052210","Procure Interlocks - SPARE","2006-10-03","2007-08-29"]
["LN06052215","RCV: Interlocks - SPARE","2007-08-30","2007-08-29"]
["LN06052220","Procure HV Connectors - SPARE","2006-10-03","2007-08-29"]
["LN06052225","RCV: HV Connectors - SPARE","2007-08-30","2007-08-29"]
["LN06052230","Procure Magnet Power Supply - SPARE","2006-10-03","2007-08-29"]
["LN06052235","RCV: Magnet Power Supply - SPARE","2007-08-30","2007-08-29"]
["LN06052240","Procure Power Supply Cabling - SPARE","2006-10-03","2007-08-29"]
["LN06052245","RCV: Power Supply Cabling - SPARE","2007-08-30","2007-08-29"]
["LN06052250","Procure Cathode Ion Pump - SPARE","2006-10-03","2007-08-29"]
["LN06052255","RCV: Cathode Ion Pump - SPARE","2007-08-30","2007-08-29"]
["LN06052260","Assemble Tank","2006-04-17","2006-04-24"]
["LN06052265","Assemble Modulator Assembly","2006-04-25","2006-05-26"]
["LN06052270","Test Modulator Assembly","2006-05-30","2006-07-05"]
["LN06052275","Assemble Tank - SPARE","2007-08-30","2007-09-06"]
["LN06052280","Dress Klystron - SPARE","2007-03-13","2007-04-02"]
["LN06052285","Test Klystron / Tank Assembly - SPARE","2007-09-07","2007-09-27"]
["LN06052286","AVAIL: Klystron / Tank Assembly - SPARE","2007-09-28","2007-09-27"]
["LN06052290","Collect Component Performance Data","2006-07-06","2006-07-17"]
["LN06052295","Load Component Data Base","2006-07-14","2006-07-17"]
["LN06052315","AVAIL: X-Band HP Modulator Ready for BC1 Install","2006-07-18","2006-07-17"]
["LN06053","X-BAND HP WAVEGUIDE SUMMARY","2005-05-02","2006-04-18"]
["LN06053020","Design WG  System","2005-05-02","2005-05-13"]
["LN06053025","Design WG  System Supports","2006-01-03","2006-02-14"]
["LN06053030","Conduct Prelim Design Review (PDR) - S Band WG","2006-02-15","2006-02-22"]
["LN06053035","Release Long Lead Procurements","2006-02-23","2006-02-22"]
["LN06053040","Create Cold Test Plan","2006-02-23","2006-03-01"]
["LN06053045","Establish Subordinate Work Orders","2006-03-02","2006-03-02"]
["LN06053050","Conduct Final Design Review (FDR) - S Band WG","2006-03-03","2006-03-03"]
["LN06053055","COMP: X-Band Waveguide Design","2006-03-06","2006-03-03"]
["LN06053060","Procure ION Pumps (8 EA)","2006-03-06","2006-03-17"]
["LN06053065","RCV: ION Pumps (8 EA)","2006-03-20","2006-03-17"]
["LN06053080","Procure ION Pump Power Supply","2006-03-06","2006-03-17"]
["LN06053085","RCV: ION Pump Power Supply","2006-03-20","2006-03-17"]
["LN06053090","Procure Waveguide Supports","2006-03-06","2006-03-17"]
["LN06053095","RCV: Waveguide Supports","2006-03-20","2006-03-17"]
["LN06053100","Fab & Test Cold Test Hardware","2006-03-20","2006-03-22"]
["LN06053110","Fab, Cold Test & Tune Mode Convertor","2006-01-03","2006-01-17"]
["LN06053115","Fab, Cold Test & Tune Circular Waveguide (WR 293","2006-01-18","2006-02-02"]
["LN06053120","Fab, Cold Test & Tune WR90 Waveguide","2006-02-03","2006-03-15"]
["LN06053125","Waveguide Supports","2006-03-16","2006-03-29"]
["LN06053130","Assemble System","2006-03-30","2006-04-12"]
["LN06053135","Collect Component Performance Data","2006-04-13","2006-04-14"]
["LN06053140","Load Component Data Base","2006-04-17","2006-04-18"]
["LN06053165","AVAIL: X-Band HP Waveguide for Installation","2006-04-19","2006-04-18"]
["LN0606","X-BAND STRUCTURES SUMMARY","2005-05-02","2006-08-23"]
["LN06060005","Write Structure ICD","2005-05-02","2005-05-02"]
["LN06060010","COMP: X-Band Structures Requirements","2005-05-03","2005-05-02"]
["LN06060015","Design Structure Supports","2005-05-03","2005-07-14"]
["LN06060020","Design Collimators","2005-07-15","2005-07-21"]
["LN06060025","Design Removal Mechanism","2005-07-22","2005-11-18"]
["LN06060030","Conduct Fnl Dsn Rev - X-Band Bunch Comp Sys","2005-11-21","2005-11-21"]
["LN06060035","COMP: X-Band Bunch Compressor System Design","2005-11-22","2005-11-21"]
["LN06060040","Procure Valves and Misc Hdwr","2005-11-22","2006-01-23"]
["LN06060060","Fab, Cold Test & Tune WR 90 Tee","2005-11-22","2006-01-23"]
["LN06060065","Fab, Cold Test & Tune WR90 Low Power Loads","2005-11-22","2006-01-23"]
["LN06060070","Fab Collimators","2005-11-22","2006-01-06"]
["LN06060080","Fab Structure Supports","2005-11-22","2006-01-23"]
["LN06060085","Fab Structure Removal Mechanism","2005-11-22","2006-01-23"]
["LN06060090","Assemble X-Band Structures","2006-01-24","2006-02-17"]
["LN06060092","Cold Test & Tune Structure (Shop)","2006-02-21","2006-03-21"]
["LN06060095","Test X-Band Structure System","2006-03-22","2006-08-10"]
["LN06060105","Collect Component Performance Data","2006-08-11","2006-08-14"]
["LN06060110","Load Component Data Base","2006-08-15","2006-08-16"]
["LN06060115","Post Process & Test","2006-08-17","2006-08-23"]
["LN06060120","AVAIL: X-Band Structures Ready for BC1 Install","2006-08-24","2006-08-23"]
["LN0607","RF DISTRIBUTION SUMMARY","2005-10-03","2008-01-02"]
["LN060701","MODULATOR REFURBISHMENT (7) SUMMARY","2006-02-02","2006-09-20"]
["LN06070102","Create Design Documentation","2006-02-02","2006-03-02"]
["LN06070110","Generate Detailed Procurement Plan","2006-03-03","2006-03-03"]
["LN06070112","Create Test Plan","2006-03-06","2006-03-10"]
["LN06070114","Establish Subordinate Work Orders","2006-03-13","2006-03-13"]
["LN06070116","Prepare for Final Desgin Review (FDR)","2006-03-14","2006-03-15"]
["LN06070118","Conduct Final Design Review (FDR) - Mod Refurb","2006-03-16","2006-03-16"]
["LN06070120","COMP: Modulator Refurbishment Design","2006-03-17","2006-03-16"]
["LN06070124","Prep Bid Pak - Thyratron & Parts","2006-03-17","2006-03-23"]
["LN06070126","RELEASE: RFP - Thyratron & Parts","2006-03-24","2006-03-23"]
["LN06070128","Vendors Prep Proposals - Thyratron & Parts","2006-03-24","2006-04-06"]
["LN06070130","RCV: Vendor Proposals - Thyratron & Parts","2006-04-07","2006-04-06"]
["LN06070132","Evaluate Vendor Proposals - Thyratron & Parts","2006-04-07","2006-04-13"]
["LN06070134","AWARD: Contract - Thyratron & Parts","2006-04-14","2006-04-14"]
["LN06070136","Vendor Fab & Assy - Thyratron & Parts","2006-04-17","2006-07-25"]
["LN06070138","RCV: from Vendor - Thyratron & Parts","2006-07-26","2006-07-25"]
["LN06070140","Refurbish Existing Modulators (7ea)","2006-07-26","2006-09-20"]
["LN06070142","AVAIL: Modulators Refurbished - BC1","2006-09-21","2006-09-20"]
["LN06070144","AVAIL: Modulators Refurbished - L02","2006-09-21","2006-09-20"]
["LN06070146","AVAIL: Modulators Refurbished - BC2","2006-09-21","2006-09-20"]
["LN06070148","AVAIL: Modulators Refurbished - L03","2006-09-21","2006-09-20"]
["LN06070150","Procure Thyratron & Parts - SPARE","2006-10-03","2007-01-26"]
["LN060702","SOLID STATE SUB BOOSTER (6) SUMMARY","2006-02-02","2006-10-17"]
["LN06070200","Generate Detailed Procurement Plan","2006-02-02","2006-02-02"]
["LN06070205","Create Test Plan","2006-02-03","2006-02-09"]
["LN06070210","Establish Subordinate Work Orders","2006-02-10","2006-02-10"]
["LN06070215","Prepare for Final Design Review (FDR)","2006-02-13","2006-02-14"]
["LN06070220","Conduct Final Design Review (FDR) - SS SubBoost","2006-02-15","2006-02-15"]
["LN06070225","COMP: Solid State Sub Booster Design","2006-02-16","2006-02-15"]
["LN06070230","Procure Phase Control Electronics","2006-02-16","2006-04-13"]
["LN06070235","Procure Amplitude Control Electronics","2006-02-16","2006-04-13"]
["LN06070240","Fab & Test Amplifier","2006-04-14","2006-08-21"]
["LN06070245","Assemble & Test Sub Booster Systems","2006-08-22","2006-10-17"]
["LN06070250","AVAIL: Solid State Sub Booster Ready for Install","2006-10-18","2006-10-17"]
["LN06070260","Procure Phase Control Electronics - SPARE","2006-10-03","2006-11-29"]
["LN06070265","Procure Amplitude Control Electronics - SPARE","2006-10-03","2006-11-29"]
["LN06070270","Fab & Test Amplifier - SPARE","2006-11-30","2007-04-23"]
["LN06070275","AVAIL: Amplifier - SPARE","2007-04-24","2007-04-23"]
["LN060703","IPA MODIFICATIONS (6) SUMMARY","2006-02-02","2006-03-09"]
["LN06070310","Generate Detailed Procurement Plan","2006-02-02","2006-02-02"]
["LN06070312","Create Test Plan","2006-02-03","2006-02-09"]
["LN06070314","Establish Subordinate Work Orders","2006-02-10","2006-02-10"]
["LN06070316","Prepare for Final Desgin Review (FDR)","2006-02-13","2006-02-14"]
["LN06070318","Conduct Final Design Review (FDR) - IPA Mods","2006-02-15","2006-02-15"]
["LN06070320","COMP: IPA Modifications Design","2006-02-16","2006-02-15"]
["LN06070326","Modify & Test IPA Chasis","2006-02-16","2006-03-09"]
["LN06070327","AVAIL: IPA Chasis Modified","2006-03-10","2006-03-09"]
["LN060704","KLYSTRON CONTROL INTERFACES (6) SUMMARY","2006-01-03","2006-05-15"]
["LN06070400","Develop Design & Prototype","2006-01-03","2006-02-07"]
["LN06070402","Create Design Documentation","2006-02-08","2006-03-08"]
["LN06070404","Create Draft Layouts","2006-03-09","2006-03-22"]
["LN06070406","Prepare for Prelim Design Review (PDR)","2006-03-23","2006-03-24"]
["LN06070408","Conduct Prelim Design Review (PDR) - Cntrols I/F","2006-03-27","2006-03-27"]
["LN06070410","Generate Detailed Procurement Plan","2006-03-28","2006-03-28"]
["LN06070412","Create Test Plan","2006-03-29","2006-04-04"]
["LN06070414","Establish Subordinate Work Orders","2006-04-05","2006-04-05"]
["LN06070416","Prepare for Final Desgin Review (FDR)","2006-04-06","2006-04-07"]
["LN06070418","Conduct Final Design Review (FDR) - Cntrols I/F","2006-04-10","2006-04-10"]
["LN06070420","COMP: Klystron Controls Design","2006-04-11","2006-04-10"]
["LN06070426","Fab Cables","2006-04-11","2006-04-24"]
["LN06070428","Klystron Controls Interface Installation","2006-04-25","2006-05-15"]
["LN060705","BUNCH LENGTH ELECTRONICS SUMMARY","2005-10-03","2006-02-22"]
["LN06070500","Develop Design & Prototype","2005-10-03","2005-11-04"]
["LN06070502","Create Design Documentation","2005-11-07","2005-12-06"]
["LN06070504","Create Draft Layouts","2005-12-07","2006-01-04"]
["LN06070506","Prepare for Prelim Design Review (PDR)","2006-01-05","2006-01-06"]
["LN06070508","Conduct Prelim Design Review (PDR) - Bm Phs Elec","2006-01-09","2006-01-09"]
["LN06070510","Generate Detailed Procurement Plan","2006-01-10","2006-01-10"]
["LN06070512","Create Test Plan","2006-01-11","2006-01-18"]
["LN06070514","Establish Subordinate Work Orders","2006-01-19","2006-01-19"]
["LN06070516","Prepare for Final Desgin Review (FDR)","2006-01-20","2006-01-23"]
["LN06070518","Conduct Final Design Review (FDR) - Bnc Lth Elec","2006-01-24","2006-01-24"]
["LN06070520","COMP: Bunch Length Electronics Design","2006-01-25","2006-01-24"]
["LN06070525","Fab & Test Bunch Length Electronics","2006-01-25","2006-02-22"]
["LN06070530","AVAIL: Bunch Length Electronics","2006-02-23","2006-02-22"]
["LN06070560","Proc, Fab & Test Bunch Length Electronics- SPARE","2006-10-03","2006-10-30"]
["LN06070565","AVAIL: Bunch Length Electronics - SPARE","2006-10-31","2006-10-30"]
["LN060706","X BAND RF PHASE MEASUREMENTS SUMMARY","2006-01-03","2007-09-27"]
["LN06070601","Design X-Band Phase Chasis","2006-01-03","2007-09-27"]
["LN06070602","Create Design Documentation","2006-02-01","2006-03-01"]
["LN06070604","Create Draft Layouts","2006-03-02","2006-03-15"]
["LN06070606","Prepare for Prelim Design Review (PDR)","2006-03-16","2006-03-17"]
["LN06070608","Conduct Prelim Design Review (PDR) - RF Phas Mea","2006-03-20","2006-03-20"]
["LN06070609","Procure, Fab & Test X-Band Chasis Prototype","2006-03-21","2006-06-13"]
["LN06070610","Procure, Fab & Test X-Band PAD Prototype","2006-03-21","2006-07-12"]
["LN06070611","Generate Detailed Procurement Plan","2006-07-13","2006-07-13"]
["LN06070612","Create Test Plan","2006-07-14","2006-07-20"]
["LN06070614","Establish Subordinate Work Orders","2006-07-21","2006-07-21"]
["LN06070616","Prepare for Final Desgin Review (FDR)","2006-07-24","2006-07-25"]
["LN06070618","Conduct Final Design Review (FDR) - RF Phas Mea","2006-07-26","2006-07-26"]
["LN06070620","COMP: RF Phase Measurement Design","2006-07-27","2006-07-26"]
["LN06070622","Procure Material / Equipment","2006-07-27","2006-11-02"]
["LN06070638","Procure, Fab & Test X-Band Chasis","2006-11-03","2006-11-20"]
["LN06070639","AVAIL: X-Band RF Phase Measurement System","2006-11-21","2006-11-20"]
["LN060707","RF DISTRIBUTION L2 & L3 SUMMARY","2006-04-10","2007-03-09"]
["LN06070700","Review & Accept Requirements","2006-04-10","2006-04-11"]
["LN06070701","Design RF Distribution System","2006-04-12","2006-05-16"]
["LN06070702","Create Design Documentation","2006-05-17","2006-06-14"]
["LN06070704","Create Draft Layouts","2006-06-15","2006-06-28"]
["LN06070706","Prepare for Prelim Design Review (PDR)","2006-06-29","2006-06-30"]
["LN06070708","Conduct Prelim Design Review (PDR) - RF Dist","2006-07-03","2006-07-03"]
["LN06070709","Controls Configuration Assessment","2006-07-05","2006-07-18"]
["LN06070710","Design RF Dist PRL Coaxial Water System","2006-07-05","2006-07-18"]
["LN06070711","Proc, Fab & Test 2W Distribution Amp - Prototype","2006-07-19","2006-10-11"]
["LN06070712","Generate Detailed Procurement Plan","2006-10-12","2006-10-12"]
["LN06070713","Create Test Plan","2006-10-13","2006-10-19"]
["LN06070714","Establish Subordinate Work Orders","2006-10-20","2006-10-20"]
["LN06070716","Prepare for Final Desgin Review (FDR)","2006-10-23","2006-10-24"]
["LN06070718","Conduct Final Design Review (FDR) - RF Dist","2006-10-25","2006-10-25"]
["LN06070720","COMP: RF Distribution (L2&L3) Design","2006-10-26","2006-10-25"]
["LN06070730","Procure, Fab & Test 2W Distribution Amp (10)","2006-10-26","2007-02-06"]
["LN06070731","AVAIL: Hdwr Testing Complete Ready for Install","2007-02-07","2007-02-06"]
["LN06070732","Procure & Install 1km 1/2 Superflex","2006-10-26","2007-02-06"]
["LN06070736","Procure & Install 1km Cable Guides","2006-10-26","2007-02-06"]
["LN06070740","Procure & Install Coaxial Water Lines","2006-10-26","2006-11-15"]
["LN06070744","Procure & Install Control Cables","2006-10-26","2006-12-01"]
["LN06070748","Install Cooling System","2007-02-07","2007-02-15"]
["LN06070756","2W Distribution Amp Install (10)","2007-02-16","2007-03-09"]
["LN06070757","AVAIL: RF Distribution System Ready","2007-03-12","2007-03-09"]
["LN06070760","Fab & Test 2W Distribution Amp - SPARE","2007-02-07","2007-05-02"]
["LN06070765","AVAIL: Hdwr Testing Complete Ready - SPARE","2007-05-03","2007-05-02"]
["LN060708","RF FIBER OPTICS ELECTRONICS SUMMARY","2006-10-03","2008-01-02"]
["LN06070800","Review & Accept Requirements","2006-10-03","2006-10-04"]
["LN06070801","Design Fiber Optic Electronics","2006-10-05","2006-11-08"]
["LN06070802","Create Design Documentation","2006-11-09","2006-12-15"]
["LN06070804","Create Draft Layouts","2006-11-09","2006-12-15"]
["LN06070806","Prepare for Prelim Design Review (PDR)","2007-01-02","2007-01-03"]
["LN06070808","Conduct Prelim Design Review (PDR) - RF Elec","2007-01-04","2007-01-04"]
["LN06070810","Generate Detailed Procurement Plan","2007-01-05","2007-01-05"]
["LN06070812","Create Test Plan","2007-01-08","2007-01-12"]
["LN06070814","Establish Subordinate Work Orders","2007-01-16","2007-01-16"]
["LN06070815","Fab & Test RF FO Electronics Prototype","2007-01-17","2007-05-09"]
["LN06070816","Prepare for Final Desgin Review (FDR)","2007-05-10","2007-05-11"]
["LN06070818","Conduct Final Design Review (FDR) - RF Elec","2007-05-14","2007-05-14"]
["LN06070820","COMP: RF Fiber Optics Electronics System Design","2007-05-15","2007-05-14"]
["LN06070828","Fab & Test RF FO Electronics","2007-05-15","2007-08-08"]
["LN06070829","AVAIL: FO System Ready for Install","2007-08-09","2007-08-08"]
["LN06070832","Fiber Optics System Installation","2007-08-09","2007-09-20"]
["LN06070836","Perform RF Electronics Testing","2007-09-21","2008-01-02"]
["LN06070837","AVAIL: FO System Ready for Commissioning","2008-01-03","2008-01-02"]
["LN06070850","Procure, Fab & Test RF FO Electronics","2007-08-09","2007-11-01"]
["LN06070860","AVAIL: Fiber Optic System Ready - SPARE","2007-11-02","2007-11-01"]
["LN060709","RF STABILITY TESTING SUMMARY","2006-10-03","2007-07-02"]
["LN06070900","Review & Accept Requirements","2006-10-03","2006-10-04"]
["LN06070901","Design Stability Algorithms","2006-10-05","2006-11-08"]
["LN06070902","Create Design Documentation","2006-11-09","2006-12-08"]
["LN06070904","Create Draft Layouts","2006-12-11","2007-01-08"]
["LN06070906","Prepare for Prelim Design Review (PDR)","2007-01-09","2007-01-10"]
["LN06070908","Conduct Prelim Design Review (PDR) - RF Stbility","2007-01-11","2007-01-11"]
["LN06070910","Generate Detailed Procurement Plan","2007-01-12","2007-01-12"]
["LN06070912","Create Test Plan","2007-01-16","2007-01-22"]
["LN06070914","Establish Subordinate Work Orders","2007-01-23","2007-01-23"]
["LN06070915","Prepare for Final Desgin Review (FDR)","2007-01-24","2007-01-25"]
["LN06070916","Conduct Final Design Review (FDR) - RF Stability","2007-01-26","2007-01-26"]
["LN06070917","RF Feedback Measurements","2007-01-29","2007-07-02"]
["LN06070918","RF Feedback Setup","2007-01-29","2007-07-02"]
["LN06070919","RF Feedback Algorithim Adjustment","2007-01-29","2007-07-02"]
["LN06070922","AVAIL: RF System Ready for Commissioning","2007-07-03","2007-07-02"]
["LN0701","LINAC L01 SYSTEM INSTALLATION SUMMARY","2005-05-17","2007-04-17"]
["LN07010000","Establish & Maintain Component Storage Facility","2005-05-17","2006-05-25"]
["LN07010005","REQD: L01 Available for Pre-Install Preps","2006-08-01","2006-07-31"]
["LN07010010","Create/Review Dwgs & Identify Installation Hdwr","2005-05-17","2005-06-14"]
["LN07010015","Procure Installation Hardware","2005-10-03","2006-04-07"]
["LN07010020","Review Drawings & Identify Installation Tooling","2005-05-17","2005-06-14"]
["LN07010025","Procure Installation & Alignment Tooling","2005-10-03","2006-06-05"]
["LN07010030","Kit New Components for Installation","2006-05-26","2006-06-23"]
["LN07010035","Develop De-Installation Plan for Existing Equip","2005-06-01","2005-08-31"]
["LN07010040","De-install Existing Components","2006-08-01","2006-08-21"]
["LN07010045","Determine Disposition of De-installed Components","2006-08-22","2006-09-12"]
["LN07010050","Prep for & Move De-installed Equip to Storage","2006-09-13","2006-09-19"]
["LN07010055","Establish Alignment Coordinates for B/L Equip","2006-08-22","2006-08-24"]
["LN07010060","REQD: All Linac L01 Sys Equip Ready for Install","2007-02-28","2007-02-27"]
["LN07010100","Install All Racks, Cables, Trays & Test","2007-02-28","2007-04-03"]
["LN07010200","Install S-Band RF Components","2007-02-28","2007-03-06"]
["LN07010205","Install Beamline Components","2007-03-07","2007-03-22"]
["LN07010210","Align Beamline Components to Coordinate System","2007-03-23","2007-03-28"]
["LN07010215","Magnet Power Interconnect & Test","2007-03-29","2007-04-02"]
["LN07010220","Controls Interconnect & Test","2007-04-04","2007-04-06"]
["LN07010225","Interconnect Vacuum System & Test","2007-03-23","2007-03-27"]
["LN07010230","Perform Magnet Power Test","2007-03-28","2007-03-29"]
["LN07010235","Perform Diagnostics Controls Test","2007-03-30","2007-04-03"]
["LN07010240","Test & Tune S Band RF Equipment","2007-04-04","2007-04-06"]
["LN07010245","Coordinate & Check Installation","2007-04-09","2007-04-17"]
["LN07010250","AVAIL: L01 Equipment Installation Complete","2007-04-18","2007-04-17"]
["LN070105","LINAC L01 COMMISSIONING SUMMARY","2006-10-03","2008-07-31"]
["LN07010500","REQD: L01 Equipment Ready for Commissioning","2007-06-12","2007-06-11"]
["LN07010505","Develop Commissioning Plans","2006-10-03","2006-11-13"]
["LN07010510","COMP: Commissioning Plans Complete","2006-11-14","2006-11-13"]
["LN07010515","Write Bm Authorization Sheet (BAS) Requirements","2006-11-14","2007-01-11"]
["LN07010520","Obtain Beam Authorization Sheet (BAS)","2007-01-12","2007-01-19"]
["LN07010525","PPS Checkout Linac","2007-06-12","2007-06-12"]
["LN07010535","Search and Lock Linac","2007-06-13","2007-06-13"]
["LN07010540","Commission L01, Physics","2008-01-03","2008-01-16"]
["LN07010545","Commission L01, Operations","2008-01-03","2008-01-16"]
["LN07010570","Support L01 Commissioning RF","2008-01-03","2008-01-16"]
["LN07010605","Support L01 Commissioning Mechanical","2008-01-03","2008-01-16"]
["LN07010615","Support L01 Commissioning Survey","2008-01-03","2008-01-16"]
["LN07010620","Support L01 Commissioning Power Conv","2008-01-03","2008-01-16"]
["LN07010635","COMP: L01 Commissioning Complete","2008-01-17","2008-01-16"]
["LN07010700","L01 System Available for Undulator Commissioning","2008-05-07","2008-07-31"]
["LN0702","LINAC BC1 SYSTEM INSTALLATION SUMMARY","2005-06-16","2007-02-14"]
["LN07020000","Establish & Maintain Component Storage Facility","2005-06-16","2006-06-26"]
["LN07020005","REQD: BC1 Available for Pre-Install Preps","2006-08-01","2006-07-31"]
["LN07020010","Create/Review Dwgs & Identify Installation Hdwr","2005-06-16","2005-07-14"]
["LN07020015","Procure Installation Hardware","2005-10-03","2006-04-07"]
["LN07020020","Review Drawings & Identify Installation Tooling","2005-06-16","2005-07-14"]
["LN07020025","Procure Installation Tooling","2005-10-03","2006-06-05"]
["LN07020030","Kit New Components for Installation","2006-06-27","2006-07-25"]
["LN07020035","Develop De-Installation Plan for Existing Equip","2005-06-16","2005-08-31"]
["LN07020040","De-install Existing Components","2006-08-01","2006-08-21"]
["LN07020045","Determine Disposition of De-installed Components","2006-08-22","2006-09-12"]
["LN07020050","Prep for & Move De-installed Equip to Storage","2006-09-13","2006-09-19"]
["LN07020055","Establish Alignment Coordinates for B/L Equip","2006-08-22","2006-08-24"]
["LN07020060","REQD: All Linac BC1 Sys Equip Ready for Install","2006-11-22","2006-11-21"]
["LN07020100","Install All Racks, Cables, Trays & Test","2006-11-22","2007-01-12"]
["LN07020200","Install S-Band RF Components","2006-11-22","2006-11-30"]
["LN07020205","Install Beamline Components","2006-12-01","2007-01-05"]
["LN07020207","Install Subbooster","2006-10-18","2006-10-31"]
["LN07020210","Align Beamline Components to Coordinate System","2007-01-08","2007-01-11"]
["LN07020215","Magnet Power Interconnect & Test","2007-01-12","2007-01-17"]
["LN07020220","Controls Interconnect & Test","2007-01-23","2007-01-25"]
["LN07020225","Interconnect Vacuum System & Test","2007-01-26","2007-01-30"]
["LN07020230","Perform Magnet Power Test","2007-01-31","2007-02-01"]
["LN07020235","Perform Diagnostics Controls Test","2007-02-02","2007-02-06"]
["LN07020240","Test & Tune S Band RF Equipment","2007-02-07","2007-02-09"]
["LN07020241","AVAIL: In-tunnel Installation Completed","2007-02-12","2007-02-14"]
["LN07020245","Install X-Band RF Components-Gallery","2006-04-19","2006-07-27"]
["LN07020246","Install X-Band RF Components-Tunnel","2006-08-22","2006-09-05"]
["LN07020250","Test & Tune X Band RF Equipment","2006-09-06","2006-10-03"]
["LN07020255","Coordinate & Check Installation","2006-10-04","2006-10-13"]
["LN07020256","Install X-Band RF Components-Gallery","2006-08-22","2006-09-05"]
["LN07020260","AVAIL: BC1 Equipment Installation Complete","2006-11-21","2006-11-20"]
["LN070205","LINAC BC1 COMMISSIONING SUMMARY","2006-10-03","2008-07-31"]
["LN07020500","REQD: BC1 Equipment Ready for Commissioning","2006-11-21","2006-11-20"]
["LN07020505","Develop Comissioning Plans","2006-10-03","2006-11-13"]
["LN07020510","COMP: Comissioning Plans Complete","2006-11-14","2006-11-13"]
["LN07020515","Write Bm Authorization Sheet (BAS) Requirements","2007-04-10","2007-05-21"]
["LN07020520","REQD: L01 Commissioning Complete","2008-01-17","2008-01-16"]
["LN07020535","Commission BC1, Physics","2008-01-17","2008-01-31"]
["LN07020540","Commission BC1, Operations","2008-01-17","2008-01-31"]
["LN07020575","Support BC1 Comissioning RF","2008-01-17","2008-01-31"]
["LN07020600","Support BC1 Comissioning Hardware","2008-01-17","2008-01-31"]
["LN07020610","Support BC1 Comissioning Mechanical","2008-01-17","2008-01-31"]
["LN07020620","Support BC1 Comissioning Survey","2008-01-17","2008-01-31"]
["LN07020625","Support BC1 Comissioning Power Conv","2008-01-17","2008-01-31"]
["LN07020640","COMP: BC1 Comissioning Complete","2008-02-01","2008-01-31"]
["LN07020700","BC1 System Available for Undulator Commissioning","2008-05-07","2008-07-31"]
["LN0703","LINAC L02 SYSTEM INSTALLATION SUMMARY","2005-10-03","2007-11-15"]
["LN07030000","Establish & Maintain Component Storage Facility","2006-04-10","2007-02-06"]
["LN07030005","REQD: L02 Available for Pre-Install Preps","2007-09-04","2007-08-31"]
["LN07030010","Create/Review Dwgs & Identify Installation Hdwr","2006-04-10","2006-05-05"]
["LN07030015","Procure Installation Hardware","2006-05-08","2007-03-07"]
["LN07030020","Review Drawings & Identify Installation Tooling","2006-04-10","2006-05-05"]
["LN07030025","Procure Installation Tooling","2006-05-08","2007-03-07"]
["LN07030030","Kit New Components for Installation","2007-03-08","2007-04-04"]
["LN07030035","Develop De-Installation Plan for Existing Equip","2006-04-10","2006-04-28"]
["LN07030038","De-install Existing Components (Oct05 Shut Down)","2005-10-03","2005-10-21"]
["LN07030040","De-install Existing Components","2007-09-04","2007-09-24"]
["LN07030045","Determine Disposition of De-installed Components","2007-09-25","2007-10-15"]
["LN07030050","Prep for & Move De-installed Equip to Storage","2007-10-16","2007-10-22"]
["LN07030055","Establish Alignment Coordinates for B/L Equip","2007-09-25","2007-09-27"]
["LN07030060","REQD: All Linac L02 Sys Equip Ready for Install","2007-06-13","2007-06-12"]
["LN07030100","Install All Racks, Cables, Trays & Test","2007-09-28","2007-11-01"]
["LN07030200","Install S-Band RF Components","2007-09-28","2007-10-04"]
["LN07030205","Install Beamline Components","2007-10-05","2007-10-19"]
["LN07030210","Align Beamline Components to Coordinate System","2007-10-22","2007-10-25"]
["LN07030215","Magnet Power Interconnect & Test","2007-10-26","2007-10-30"]
["LN07030220","Controls Interconnect & Test","2007-11-02","2007-11-06"]
["LN07030225","Interconnect Vacuum System & Test","2007-10-22","2007-10-24"]
["LN07030230","Perform Magnet Power Test","2007-10-25","2007-10-26"]
["LN07030235","Perform Diagnostics Controls Test","2007-10-29","2007-10-31"]
["LN07030240","Test & Tune S Band RF Equipment","2007-11-01","2007-11-05"]
["LN07030245","Coordinate & Check Installation","2007-11-06","2007-11-15"]
["LN07030250","AVAIL: L02 Equipment Installation Complete","2007-11-16","2007-11-15"]
["LN070305","LINAC L02 COMMISSIONING SUMMARY","2006-10-03","2008-07-31"]
["LN07030500","REQD: L02 Equipment Ready for Commissioning","2007-11-16","2007-11-15"]
["LN07030505","Develop Comissioning Plans","2006-10-03","2006-11-13"]
["LN07030510","COMP: Comissioning Plans Complete","2006-11-14","2006-11-13"]
["LN07030515","Write Bm Authorization Sheet (BAS) Requirements","2007-04-10","2007-05-21"]
["LN07030520","REQD: L01 & BC1 Comissioning Complete","2008-02-01","2008-01-31"]
["LN07030525","Obtain Beam Authorization Sheet (BAS)","2008-02-01","2008-02-07"]
["LN07030530","PPS Checkout Linac","2008-02-08","2008-02-08"]
["LN07030540","Search and Lock Linac","2008-02-11","2008-02-11"]
["LN07030545","Commission L02, Physics","2008-02-12","2008-02-26"]
["LN07030550","Commission L02, Operations","2008-02-12","2008-02-26"]
["LN07030575","Support L02 Comissioning RF","2008-02-12","2008-02-26"]
["LN07030600","Support L02 Comissioning Hardware","2008-02-12","2008-02-26"]
["LN07030610","Support L02 Comissioning Mechanical","2008-02-12","2008-02-26"]
["LN07030620","Support L02 Comissioning Survey","2008-02-12","2008-02-26"]
["LN07030625","Support L02 Comissioning Power Conv","2008-02-12","2008-02-26"]
["LN07030640","COMP: L02 Comissioning Complete","2008-02-27","2008-02-26"]
["LN07030700","L02 System Available for Undulator Commissioning","2008-05-07","2008-07-31"]
["LN0704","LINAC BC2 SYSTEM INSTALLATION SUMMARY","2006-04-10","2007-11-16"]
["LN07040000","Establish & Maintain Component Storage Facility","2006-04-10","2007-02-06"]
["LN07040005","REQD: BC2 Available for Pre-Install Preps","2007-09-04","2007-08-31"]
["LN07040010","Create/Review Dwgs & Identify Installation Hdwr","2006-04-10","2006-05-05"]
["LN07040015","Procure Installation Hardware","2006-05-08","2007-03-07"]
["LN07040020","Review Drawings & Identify Installation Tooling","2006-04-10","2006-05-05"]
["LN07040025","Procure Installation Tooling","2006-05-08","2007-03-07"]
["LN07040030","Kit New Components for Installation","2007-03-08","2007-04-04"]
["LN07040035","Develop De-Installation Plan for Existing Equip","2006-04-10","2006-04-28"]
["LN07040040","De-install Existing Components","2007-09-04","2007-09-24"]
["LN07040045","Determine Disposition of De-installed Components","2007-09-25","2007-10-15"]
["LN07040050","Prep for & Move De-installed Equip to Storage","2007-10-16","2007-10-22"]
["LN07040055","Establish Alignment Coordinates for B/L Equip","2007-09-25","2007-09-27"]
["LN07040060","REQD: All Linac BC2 Sys Equip Ready for Install","2007-08-23","2007-08-22"]
["LN07040100","Install All Racks, Cables, Trays & Test","2007-09-28","2007-11-01"]
["LN07040200","Install S-Band RF Components","2007-09-28","2007-10-04"]
["LN07040205","Install Beamline Components","2007-10-05","2007-10-22"]
["LN07040210","Align Beamline Components to Coordinate System","2007-10-23","2007-10-26"]
["LN07040215","Magnet Power Interconnect & Test","2007-10-29","2007-10-31"]
["LN07040220","Controls Interconnect & Test","2007-11-02","2007-11-06"]
["LN07040225","Interconnect Vacuum System & Test","2007-10-23","2007-10-25"]
["LN07040230","Perform Magnet Power Test","2007-10-26","2007-10-29"]
["LN07040235","Perform Diagnostics Controls Test","2007-10-30","2007-11-01"]
["LN07040240","Test & Tune S Band RF Equipment","2007-11-02","2007-11-06"]
["LN07040245","Coordinate & Check Installation","2007-11-07","2007-11-16"]
["LN07040250","AVAIL: BC2 Equipment Installation Complete","2007-11-19","2007-11-16"]
["LN070405","LINAC BC2 COMMISSIONING SUMMARY","2006-10-03","2008-07-31"]
["LN07040500","REQD: BC2 Equipment Ready for Commissioning","2007-11-19","2007-11-16"]
["LN07040505","Develop Comissioning Plans","2006-10-03","2006-11-13"]
["LN07040510","COMP: Comissioning Plans Complete","2006-11-14","2006-11-13"]
["LN07040515","Write Bm Authorization Sheet (BAS) Requirements","2007-04-10","2007-05-21"]
["LN07040520","REQD: BC1 & L02 Comissioning Complete","2008-02-27","2008-02-26"]
["LN07040545","Commission BC2, Physics","2008-02-27","2008-03-11"]
["LN07040550","Commission BC2, Operations","2008-02-27","2008-03-11"]
["LN07040610","Support BC2 Comissioning Mechanical","2008-02-27","2008-03-11"]
["LN07040620","Support BC2 Comissioning Survey","2008-02-27","2008-03-11"]
["LN07040625","Support BC2 Comissioning Power Conv","2008-02-27","2008-03-11"]
["LN07040640","COMP: BC2 Comissioning Complete","2008-03-12","2008-03-11"]
["LN07040700","BC2 System Available for Undulator Commissioning","2008-05-07","2008-07-31"]
["LN0705","LINAC L03 INSTALLATION SUMMARY - 25,27,28,29","2006-04-10","2007-11-30"]
["LN07050000","Establish & Maintain Component Storage Facility","2006-04-10","2007-02-06"]
["LN07050005","REQD: L03 Available for Pre-Install Preps","2007-09-04","2007-08-31"]
["LN07050010","Create/Review Dwgs & Identify Installation Hdwr","2006-04-10","2006-05-05"]
["LN07050015","Procure Installation Hardware","2006-05-08","2007-03-07"]
["LN07050020","Review Drawings & Identify Installation Tooling","2006-04-10","2006-05-05"]
["LN07050025","Procure Installation Tooling","2006-05-08","2007-03-07"]
["LN07050030","Kit New Components for Installation","2007-03-08","2007-04-04"]
["LN07050035","Develop De-Installation Plan for Existing Equip","2006-04-10","2006-04-28"]
["LN07050040","De-install Existing Components","2007-09-04","2007-09-24"]
["LN07050045","Determine Disposition of De-installed Components","2007-09-11","2007-09-13"]
["LN07050050","Prep for & Move De-installed Equip to Storage","2007-09-14","2007-09-20"]
["LN07050055","Establish Alignment Coordinates for B/L Equip","2007-09-04","2007-09-11"]
["LN07050060","REQD: All Linac L03 Sys Equip Ready for Install","2007-08-20","2007-08-17"]
["LN07050100","Install All Racks, Cables, Trays & Test","2007-09-12","2007-10-16"]
["LN07050200","Install S-Band RF Components","2007-09-25","2007-10-08"]
["LN07050205","Install Beamline Components","2007-09-25","2007-10-15"]
["LN07050210","Align Beamline Components to Coordinate System","2007-10-16","2007-10-25"]
["LN07050215","Magnet Power Interconnect & Test","2007-10-26","2007-10-30"]
["LN07050220","Controls Interconnect & Test","2007-10-31","2007-11-07"]
["LN07050225","Interconnect Vacuum System & Test","2007-10-31","2007-11-07"]
["LN07050230","Perform Magnet Power Test","2007-11-08","2007-11-09"]
["LN07050235","Perform Diagnostics Controls Test","2007-11-12","2007-11-19"]
["LN07050240","Test & Tune S Band RF Equipment","2007-11-20","2007-11-21"]
["LN07050245","Coordinate & Check Installation","2007-11-26","2007-11-30"]
["LN07050250","AVAIL: L03 Equipment Installation Complete","2007-12-03","2007-11-30"]
["LN070505","LINAC L03 COMMISSIONING SUMMARY","2006-10-03","2008-07-31"]
["LN07050500","REQD: L03 Equipment Ready for Commissioning","2007-12-03","2007-11-30"]
["LN07050505","Develop Comissioning Plans","2006-10-03","2006-11-13"]
["LN07050510","COMP: Comissioning Plans Complete","2006-11-14","2006-11-13"]
["LN07050515","Write Bm Authorization Sheet (BAS) Requirements","2007-04-10","2007-05-21"]
["LN07050520","REQD: L02 & BC2 Comissioning Complete","2008-03-12","2008-03-11"]
["LN07050525","Commission L03, Physics","2008-03-12","2008-03-25"]
["LN07050530","Commission L03, Operations","2008-03-12","2008-03-25"]
["LN07050555","Support L03 Comissioning RF","2008-03-12","2008-03-25"]
["LN07050590","Support L03 Comissioning Mechanical","2008-03-12","2008-03-25"]
["LN07050600","Support L03 Comissioning Survey","2008-03-12","2008-03-25"]
["LN07050605","Support L03 Comissioning Power Conv","2008-03-12","2008-03-25"]
["LN07050620","COMP: L03 Comissioning Complete","2008-03-26","2008-03-25"]
["LN07050700","L03 System Available for Undulator Commissioning","2008-05-07","2008-07-31"]
["LN0706","LINAC LTU SYSTEM INSTALLATION SUMMARY","2006-04-10","2008-04-22"]
["LN07060000","Establish & Maintain Component Storage Facility","2006-04-10","2007-04-18"]
["LN07060005","REQD: LTU Available for Pre-Install Preps","2007-12-04","2007-12-03"]
["LN07060010","Create/Review Dwgs & Identify Installation Hdwr","2006-04-10","2006-05-05"]
["LN07060015","Procure Installation Hardware","2006-10-03","2007-10-11"]
["LN07060020","Review Drawings & Identify Installation Tooling","2006-04-10","2006-05-05"]
["LN07060025","Procure Installation Tooling","2006-10-03","2007-10-11"]
["LN07060030","Kit New Components for Installation","2007-10-12","2007-11-08"]
["LN07060035","Develop De-Installation Plan for Existing Equip","2006-04-10","2006-04-28"]
["LN07060040","REQD: FFTB Ready for Equip removal","2006-04-10","2006-04-07"]
["LN07060060","COMP: FFTB Equip Removal Comp Ready for CF","2006-07-03","2006-06-30"]
["LN07060065","Establish Alignment Coordinates for B/L Equip","2007-12-04","2007-12-06"]
["LN07060070","REQD: All Linac LTU Sys Equip Ready for Install","2008-02-21","2008-02-20"]
["LN07060100","Install All Racks, Cables, Trays & Test","2008-02-21","2008-03-26"]
["LN07060200","Install Beamline Components","2008-02-21","2008-03-12"]
["LN07060210","Align Beamline Components to Coordinate System","2008-03-13","2008-03-18"]
["LN07060215","Magnet Power Interconnect & Test","2008-03-19","2008-03-21"]
["LN07060220","Controls Interconnect & Test","2008-03-27","2008-03-31"]
["LN07060225","Interconnect Vacuum System & Test","2008-04-01","2008-04-03"]
["LN07060230","Perform Magnet Power Test","2008-04-04","2008-04-07"]
["LN07060235","Perform Diagnostics Controls Test","2008-04-08","2008-04-10"]
["LN07060245","Coordinate & Check Installation","2008-04-11","2008-04-22"]
["LN07060250","AVAIL: LTU Equipment Installation Complete","2008-04-23","2008-04-22"]
["LN070605","LINAC LTU COMMISSIONING SUMMARY","2006-10-03","2008-07-31"]
["LN07060500","REQD: LTU Equipment Ready for Commissioning","2008-04-23","2008-04-22"]
["LN07060505","Develop Comissioning Plans","2006-10-03","2006-11-13"]
["LN07060510","COMP: Comissioning Plans Complete","2006-11-14","2006-11-13"]
["LN07060515","Write Bm Authorization Sheet (BAS) Requirements","2007-04-10","2007-05-21"]
["LN07060520","REQD: L01,02,03 & BC1,2 Comissioning Complete","2008-03-26","2008-03-25"]
["LN07060525","Obtain Beam Authorization Sheet (BAS)","2008-03-26","2008-04-01"]
["LN07060530","PPS Checkout Linac","2008-04-02","2008-04-02"]
["LN07060535","Search and Lock Linac","2008-04-03","2008-04-03"]
["LN07060540","Commission LTU, Physics","2008-04-23","2008-05-06"]
["LN07060545","Commission LTU, Operations","2008-04-23","2008-05-06"]
["LN07060580","Support LTU Comissioning Hardware","2008-04-23","2008-05-06"]
["LN07060585","Support LTU Comissioning Mechanical","2008-04-23","2008-05-06"]
["LN07060590","Support LTU Comissioning Survey","2008-04-23","2008-05-06"]
["LN07060595","Support LTU Comissioning Power Conv","2008-04-23","2008-05-06"]
["LN07060600","COMP: LTU Commissioning Complete","2008-05-07","2008-05-06"]
["LN07060700","LTU System Available for Undulator Commissioning","2008-05-07","2008-07-31"]
["LN0707","LINAC E-DUMP SYSTEM INSTALLATION SUMMARY","2005-10-03","2008-02-26"]
["LN07070000","Establish & Maintain Component Storage Facility","2005-10-03","2006-10-11"]
["LN07070005","REQD: E-Dump Available for Pre-Install Preps","2007-12-03","2007-11-30"]
["LN07070010","Create/Review Dwgs & Identify Installation Hdwr","2005-10-03","2005-10-28"]
["LN07070015","Procure Installation Hardware","2006-10-03","2007-10-11"]
["LN07070020","Review Drawings & Identify Installation Tooling","2005-10-03","2005-10-28"]
["LN07070025","Procure Installation Tooling","2006-10-03","2007-10-11"]
["LN07070030","Kit New Components for Installation","2007-10-12","2007-11-08"]
["LN07070035","REQD: All E-Dump System Equip Avail for Install","2007-11-26","2007-11-21"]
["LN07070040","Establish Alignment Coordinates for B/L Equip","2007-12-03","2007-12-05"]
["LN07070100","Install All Racks, Cables, Trays & Test","2007-12-06","2008-01-28"]
["LN07070200","Install Beamline Components","2008-01-07","2008-01-28"]
["LN07070210","Align Beamline Components to Coordinate System","2008-01-29","2008-02-01"]
["LN07070215","Magnet Power Interconnect & Test","2008-02-04","2008-02-06"]
["LN07070220","Controls Interconnect & Test","2008-02-04","2008-02-06"]
["LN07070225","Interconnect Vacuum System & Test","2008-02-04","2008-02-06"]
["LN07070230","Perform Magnet Power Test","2008-02-07","2008-02-08"]
["LN07070235","Perform Diagnostics Controls Test","2008-02-11","2008-02-13"]
["LN07070245","Coordinate & Check Installation","2008-02-14","2008-02-26"]
["LN07070250","AVAIL: E-Dump Equipment Installation Complete","2008-02-27","2008-02-26"]
["LN070705","LINAC E-DUMP COMMISSIONING SUMMARY","2006-10-03","2008-06-04"]
["LN07070500","REQD: E-Dump Equipment Ready for Commissioning","2008-02-27","2008-02-26"]
["LN07070505","Develop Comissioning Plans","2006-10-03","2006-11-13"]
["LN07070510","COMP: Comissioning Plans Complete","2006-11-14","2006-11-13"]
["LN07070515","Write Bm Authorization Sheet (BAS) Requirements","2007-04-10","2007-05-21"]
["LN07070520","REQD: L01,2,3, BC1,2 & LTU Comissioning Complete","2008-05-21","2008-05-20"]
["LN07070535","Commission E-Dump, Physics","2008-05-21","2008-06-04"]
["LN07070540","Commission E-Dump, Operations","2008-05-21","2008-06-04"]
["LN07070565","Support E-Dump Comissioning Hardware","2008-05-21","2008-06-04"]
["LN07070570","Support E-Dump Comissioning Mechanical","2008-05-21","2008-06-04"]
["LN07070575","Support E-Dump Comissioning Survey","2008-05-21","2008-06-04"]
["LN07070580","Support E-Dump Comissioning Power Conv","2008-05-21","2008-06-04"]
["LN07070585","COMP: E-Dump Comissioning Complete Ready for Ops","2008-06-05","2008-06-04"]
["LN101_1000","L01 Top Assembly","2006-01-03","2006-05-01"]
["LN101_1010","L01 Procurement Support","2006-01-03","2006-06-30"]
["LN101_1020","L01 Fabrication Oversight","2006-01-03","2006-07-31"]
["LN101_1030","L01 Installation Coordination Planning","2006-02-01","2006-05-01"]
["LN101_1040","L01 Installation Oversight","2006-08-01","2006-11-30"]
["LN101_1050","L01 Documentation","2006-12-01","2007-07-31"]
["LN101_1060","L01 System Construction Support to Component","2006-12-01","2007-07-31"]
["LN101_2010","BC1 Emittance Section Layout","2005-12-01","2006-01-03"]
["LN101_2020","BC1 Emittance Section Design","2006-01-03","2006-07-31"]
["LN101_2100","BC1 Top Assembly","2006-01-03","2006-07-31"]
["LN101_2105","BC1 Bunch Length Monitor Integration","2005-12-01","2006-07-31"]
["LN101_2110","BC1 Procurement Support","2006-02-01","2006-07-31"]
["LN101_2120","BC1 Fabrication Oversight","2006-02-01","2006-07-31"]
["LN101_2130","BC1 Installation Coordination Planning","2006-03-01","2006-07-31"]
["LN101_2140","BC1 Installation Oversight","2006-08-01","2006-11-30"]
["LN101_2150","BC1 Documentation","2006-12-01","2007-07-31"]
["LN101_2160","BC1 System Construction Support to Component","2006-12-01","2007-07-31"]
["LN101_3100","L2 Top Assembly","2005-12-01","2006-10-02"]
["LN101_3110","L2 Procurement Support","2006-10-02","2007-07-02"]
["LN101_3120","L2 Fabrication Oversight","2006-10-02","2007-07-02"]
["LN101_3130","L2 Installation Coordination Planning","2006-12-01","2007-07-02"]
["LN101_3140","L2 Installation Oversight","2007-07-02","2007-10-31"]
["LN101_3150","L2 Documentation","2007-11-01","2008-06-30"]
["LN101_3160","L2 System Construction Support to Components","2007-11-01","2008-06-30"]
["LN101_4100","BC2 Top Assembly","2005-12-01","2006-10-31"]
["LN101_4102","BC2 Bunch Length Monitor Integration","2006-07-03","2007-07-02"]
["LN101_4104","BC2 Emittance Section Layout","2006-07-03","2007-01-02"]
["LN101_4106","BC2 Emittance Section Design","2006-10-02","2007-07-02"]
["LN101_4110","BC2 Procurement Support","2006-10-02","2007-07-02"]
["LN101_4120","BC2 Fabrication Oversight","2006-10-02","2007-07-02"]
["LN101_4130","BC2 Installation Coordination Planning","2006-11-01","2007-07-02"]
["LN101_4140","BC2 Installation Oversight","2007-07-02","2007-10-31"]
["LN101_4150","BC2 Documentation","2007-11-01","2008-06-30"]
["LN101_4160","BC2 System Construction Support to Component","2007-11-01","2008-06-30"]
["LN101_5100","L3 Top Assembly","2005-12-01","2006-10-02"]
["LN101_5110","L3 Procurement Support","2006-10-02","2007-07-02"]
["LN101_5120","L3 Fabrication Oversight","2006-10-02","2007-07-02"]
["LN101_5130","L3 Installation Coordination Planning","2007-01-02","2007-07-02"]
["LN101_5140","L3 Installation Oversight","2007-07-02","2007-10-31"]
["LN101_5150","L3 Documentation","2007-11-01","2008-06-30"]
["LN101_5160","L3 System Construction Support to Components","2007-11-01","2008-06-30"]
["LN101_6010","LTU Layout & CF Interface","2005-12-01","2006-05-30"]
["LN101_6100","LTU Top Assembly","2006-06-01","2007-01-02"]
["LN101_6102","LTU Pedestal and Raft Design","2006-10-02","2007-01-30"]
["LN101_6104","LTU Beamline Shielding Fabrication","2007-02-01","2007-04-30"]
["LN101_6106","LTU Pedestal and Raft Fabrication","2007-02-01","2007-04-30"]
["LN101_6110","LTU Procurement Support","2006-10-02","2007-04-30"]
["LN101_6120","LTU Fabrication Oversight","2006-10-02","2007-04-30"]
["LN101_6130","LTU Installation Coordination Planning","2006-11-01","2008-01-02"]
["LN101_6140","LTU Installation Oversight","2008-01-02","2008-04-30"]
["LN101_6150","LTU Documentation","2008-04-01","2008-09-30"]
["LN101_6160","LTU System Construction Support to Component","2008-05-01","2008-09-30"]
["LN101_7010","E-Dump Layout & CF Interface","2005-12-01","2006-05-01"]
["LN101_7100","E-Dump Top Assembly","2006-06-01","2007-01-02"]
["LN101_7102","E-Dump Pedestal and Raft Design","2006-10-02","2007-01-02"]
["LN101_7104","E-Dump Beamline Shielding Fabrication","2007-02-01","2007-04-30"]
["LN101_7106","E-Dump Pedestal and Raft Fabrication","2007-02-01","2007-04-30"]
["LN101_7110","E-Dump Procurement Support","2006-10-02","2007-04-30"]
["LN101_7120","E-Dump Fabrication Oversight","2006-10-02","2007-04-30"]
["LN101_7130","E-Dump Installation Coordination Planning","2006-11-01","2008-01-02"]
["LN101_7140","E-Dump Installation Oversight","2008-01-02","2008-04-30"]
["LN101_7150","E-Dump Documentation","2008-03-03","2008-09-30"]
["LN101_7160","E-Dump System CONST Support to Components","2008-03-03","2008-09-30"]
["LN104_1000","Linac System Management Effort - CONST","2005-12-01","2008-09-30"]
["LN104_1010","Cost Account Managers - CONST","2005-12-01","2008-09-30"]
["LN104_1020","Fabrication Coordination","2005-12-01","2008-09-30"]
["LN502_1000",null,"2005-05-02","2005-05-02"]
["LN502_4000",null,"2005-05-02","2005-05-02"]
["LN503_1000",null,"2005-05-02","2005-05-02"]
["LN504_1000",null,"2005-05-02","2005-05-02"]
["LN505_1000",null,"2005-05-02","2005-05-02"]
["LN507_1000",null,"2005-05-02","2005-05-02"]
["LN508_1000",null,"2005-05-02","2005-05-02"]
["LN508_2000",null,"2005-05-02","2005-05-02"]
["LN509_1000",null,"2005-05-02","2005-05-02"]
["LN510_1000",null,"2005-05-02","2005-05-02"]
["LN511_1000","PROTECTION COLLIMATORS (5) SUMMARY","2006-03-01","2006-09-06"]
["LN512_1000",null,"2005-05-02","2005-05-02"]
["LN513_1000",null,"2005-05-02","2005-05-02"]
["LNMS_0100","System Design Reviews Complete - L01","2005-08-04","2005-08-03"]
["LNMS_0120","System Component Subcontracts Awarded - L01","2005-08-04","2005-08-03"]
["LNMS_0140","Ready to Begin Component Installation - L01","2006-08-01","2006-07-31"]
["LNMS_0200","System Design Reviews Complete - BC1","2005-08-04","2005-08-03"]
["LNMS_0220","System Component Subcontracts Awarded - BC1","2005-08-04","2005-08-03"]
["LNMS_0240","Ready to Begin Component Installation - BC1","2006-08-01","2006-07-31"]
["LNMS_0260","Component Installation Completed - BC1","2006-11-21","2006-11-20"]
["LNMS_0300","System Design Reviews Complete - L02","2005-09-26","2005-09-23"]
["LNMS_0320","System Component Subcontracts Awarded - L02","2005-09-26","2005-09-23"]
["LNMS_0340","Ready to Begin Component Installation - L02","2007-09-04","2007-08-31"]
["LNMS_0360","Component Installation Completed - L02","2007-11-16","2007-11-15"]
["LNMS_0400","System Design Reviews Complete - BC2","2005-08-03","2005-08-02"]
["LNMS_0420","System Component Subcontracts Awarded - BC2","2005-08-03","2005-08-02"]
["LNMS_0440","Ready to Begin Component Installation - BC2","2007-09-04","2007-08-31"]
["LNMS_0500","System Design Reviews Complete - L03","2005-08-12","2005-08-11"]
["LNMS_0520","System Component Subcontracts Awarded - L03","2005-08-12","2005-08-11"]
["LNMS_0540","Ready to Begin Component Installation - L03","2007-09-04","2007-08-31"]
["LNMS_0560","Component Installation Completed - L03","2007-12-03","2007-11-30"]
["LNMS_0600","System Design Reviews Complete - LTU","2005-08-12","2005-08-11"]
["LNMS_0620","System Component Subcontracts Awarded - LTU","2005-08-12","2005-08-11"]
["LNMS_0640","Ready to Begin Component Installation - LTU","2007-12-04","2007-12-03"]
["LNMS_0700","System Design Reviews Complete - E-Dump","2005-08-05","2005-08-04"]
["LNMS_0720","System Component Subcontracts Awarded - E-Dump","2005-08-05","2005-08-04"]
["LNMS_0740","Ready to Begin Component Installation - E-Dump","2007-10-10","2007-10-09"]
["LNOPS_0000","Linac System Pre-Operations","2008-06-09","2009-03-30"]
["LN_LOE","Linac LOE Complete","2009-04-01","2009-03-31"]
["MS1_PM000","CD0 - Approve Mission Need","2001-06-18","2001-06-17",null,"2001-06-18","2001-06-17"]
["MS1_PM005","CD1 - Approve Preliminary Baseline Range","2002-10-17","2002-10-16",null,"2002-10-17","2002-10-16"]
["MS1_PM015","CD2a -  Approve Long-Lead Procurement Budget","2004-07-31","2004-07-30",null,"2004-07-31","2004-07-30"]
["MS1_PM020","CD2b - Approve Performance Baseline","2005-04-01","2005-03-31",null,"2005-04-01","2005-03-31"]
["MS1_PM025","CD3a - Approve Start of Long Lead Procurement","2004-10-30","2004-10-29",null,"2004-10-30","2004-10-29"]
["MS1_PM030","CD3b - Approve Start of Construction","2006-03-01","2006-02-28"]
["MS1_PM035","CD4 - Approve Start of Operations","2009-04-01","2009-03-31"]
["MS2BO_005","Sector 20 Alcove Beneficial Occupancy","2006-07-24","2006-07-21"]
["MS2BO_020","Linac Facility Beneficial Occupancy","2007-07-12","2007-07-11"]
["MS2BO_025","Research Yards Mods Beneficial Occupancy","2006-10-23","2006-10-20"]
["MS2BO_030","Beam Transport Hall Beneficial Occupancy","2008-01-04","2008-01-03"]
["MS2BO_035","Undulator Facility Beneficial Occupancy","2007-06-05","2007-06-04"]
["MS2BO_040","Front End Enclosure Beneficial Occupancy","2007-10-08","2007-10-05"]
["MS2BO_050","Near Experimental Hall Beneficial Occupancy","2007-06-19","2007-06-18"]
["MS2BO_055","X-Ray Transport Beneficial Occupancy","2007-10-15","2007-10-12"]
["MS2BO_060","Far Experimental Hall Beneficial Occupancy","2007-09-05","2007-09-04"]
["MS2BO_065","Central Lab Office Ctr Beneficial Occupancy","2008-11-11","2008-11-10"]
["MS2_IJ0010","Start Injector Commissioning (Drive Laser)","2006-11-20","2006-11-17"]
["MS2_IJ0020","Start Injector Commissioning(UV Beam to Cathode)","2007-07-23","2007-07-20"]
["MS2_IJ0027","Injector Laser Commissioning Review Complete","2007-01-17","2007-01-16"]
["MS2_IJ0030","Injector Accelerator Readiness Review (ARR) Comp","2007-09-21","2007-09-20"]
["MS2_LN015","Start Linac-to-Undulator (LTU) Commissioning","2008-06-12","2008-06-11"]
["MS2_LN020","Linac ARR (Li20-Li30)  Complete","2008-03-10","2008-03-07"]
["MS2_LN025","Start Linac (Li20-Li30) Commissioning","2008-05-08","2008-05-07"]
["MS2_PM005","Final Safety Analysis Document (FSAD) Approved","2008-04-01","2008-03-31"]
["MS2_PM030","LCLS ARR Complete (BTH thru FEH)","2008-06-10","2008-06-09"]
["MS2_PM035","DOE External Independent Review (EIR) Complete","2004-06-15","2004-06-14",null,"2004-06-15","2004-06-14"]
["MS2_PM040","Fire Hazard Analysis Approved","2005-08-16","2005-08-15"]
["MS2_PM045","Prelim Safety Assessment (PSAD) Doc Comp","2004-05-01","2004-04-30",null,"2004-05-01","2004-04-30"]
["MS2_PM055","Prelim Safety Assessment (PSAD) Doc Approved","2006-03-01","2006-02-28"]
["MS2_UN005","MMF Qualified & Ready to Measure Prod Undulators","2006-11-21","2006-11-20"]
["MS2_UN010","Delivery of Undulator 1st Articles to MMF","2006-07-05","2006-07-03"]
["MS2_UN025","Start Undulator Commissioning (1st Light)","2008-08-18","2008-08-15"]
["MS2_XE005","Start XES Commissioning","2008-08-18","2008-08-15"]
["MS2_XE015","2-D Pixel Detector Production Start","2008-01-03","2008-01-02"]
["MS2_XT005","Start XTOD Commissioning","2008-08-18","2008-08-15"]
["MS3BO_005","Sector 20 Alcove Beneficial Occupancy","2006-04-03","2006-03-31"]
["MS3BO_020","Linac Facility Beneficial Occupancy","2007-06-12","2007-06-11"]
["MS3BO_025","Research Yards Mods Beneficial Occupancy","2006-09-22","2006-09-21"]
["MS3BO_030","Beam Transport Hall Beneficial Occupancy","2007-12-04","2007-12-03"]
["MS3BO_035","Undulator Facility Beneficial Occupancy","2007-05-04","2007-05-03"]
["MS3BO_040","Front End Enclosure Beneficial Occupancy","2007-09-06","2007-09-05"]
["MS3BO_050","Near Experimental Hall Beneficial Occupancy","2007-05-21","2007-05-18"]
["MS3BO_055","X-Ray Transport Beneficial Occupancy","2007-09-14","2007-09-13"]
["MS3BO_060","Far Experimental Hall Beneficial Occupancy","2007-08-06","2007-08-03"]
["MS3BO_065","Central Lab Office Ctr Beneficial Occupancy","2008-10-13","2008-10-10"]
["MS3_CF000","A&E Serv (S20, MMF, MCC not incl) Title 1 Comp","2004-05-01","2004-04-30",null,"2004-05-01","2004-04-30"]
["MS3_CF002","A&E Serv Sector 20 Title 1 Complete","2004-05-01","2004-04-30",null,"2004-05-01","2004-04-30"]
["MS3_CF005","A&E Serv (S20, MMF, MCC not incl) Title 2 Comp","2006-02-21","2006-02-17"]
["MS3_CF010","A&E Services Sector 20 Title 2 Complete","2005-03-19","2005-03-18",null,"2005-03-19","2005-03-18"]
["MS3_CF015","A&E Services MMF Title 2 Complete","2005-06-01","2005-05-31",null,"2005-06-01","2005-05-31"]
["MS3_CF022","A&E Services MMF Title 1 Complete","2004-05-01","2004-04-30",null,"2004-05-01","2004-04-30"]
["MS3_CF060","Award of Construction Management Package - Ph.1","2005-10-18","2005-10-17",null,"2005-10-18","2005-10-17"]
["MS3_CF065","Award of Sector 20 Title 3 Complete","2005-07-29","2005-07-28",null,"2005-07-29","2005-07-28"]
["MS3_CF066","Award of Magnetic Msmt Facility Title 3 Complete","2005-07-29","2005-07-28",null,"2005-07-29","2005-07-28"]
["MS3_CT070","Injector Controls Installation Complete","2008-01-02","2007-12-14"]
["MS3_CT075","Linac Controls Ready for Installation","2008-03-04","2008-03-03"]
["MS3_CT080","LTU Controls Ready for Installation","2008-02-07","2008-02-06"]
["MS3_CT090","PNET Integration Complete","2007-05-31","2007-05-30"]
["MS3_CT150","Personnel Protection Design Complete","2006-04-24","2006-04-21"]
["MS3_CT155","Machine Protection System First Article Complete","2006-04-24","2006-04-21"]
["MS3_IJ0010","Start Injector Commissioning (Drive Laser)","2006-10-18","2006-10-17"]
["MS3_IJ0020","Start Injector Commissioning(UV Beam to Cathode)","2007-06-21","2007-06-20"]
["MS3_IJ0027","Injector Laser Commissioning Review Complete","2007-01-02","2006-12-15"]
["MS3_IJ0030","Injector Accelerator Readiness Review (ARR) Comp","2007-08-21","2007-08-20"]
["MS3_IJ005","Drive Laser Available for Integration","2006-07-11","2006-07-10"]
["MS3_IJ010","Wall Region Installation Complete","2006-01-03","2005-12-16"]
["MS3_IJ020","Heater Region Installation Complete","2006-06-01","2006-05-31"]
["MS3_IJ032","Laser Tables & Optical Paths Installation Comp","2006-08-22","2006-08-21"]
["MS3_IJ080","Gun Region Installation Complete","2006-10-10","2006-10-09"]
["MS3_IJ085","Accelerator Region Installation Complete","2006-08-03","2006-08-02"]
["MS3_IJ095","Award of Drive Laser Contract Complete","2005-07-01","2005-06-30"]
["MS3_IJ100","Insertion Region Installation Complete","2006-10-30","2006-10-27"]
["MS3_IJ105","Spectrometer Installation Complete","2006-10-30","2006-10-27"]
["MS3_IJ110","Injector RF Subsystem Installation Complete","2007-03-29","2007-03-28"]
["MS3_IJ115","Cathode Processing Station Installation Complete","2007-11-07","2007-11-06"]
["MS3_IJ120","Laser Heater Installation Complete","2007-11-27","2007-11-26"]
["MS3_IJ125","RF Gun Ready for Installation","2006-10-03","2006-10-02"]
["MS3_LN010","X-Band Klystron Ready for Installation","2006-11-28","2006-11-27"]
["MS3_LN011","BC2 Installation Complete","2008-02-11","2008-02-08"]
["MS3_LN012","BC1 Installation Complete","2006-11-30","2006-11-29"]
["MS3_LN013","Start BC1 Commissioning","2006-11-30","2006-11-29"]
["MS3_LN015","Start Linac-to-Undulator (LTU) Commissioning","2008-05-12","2008-05-09"]
["MS3_LN016","BC1 Magnets Ready for Installation","2006-10-25","2006-10-24"]
["MS3_LN020","Linac ARR (Li20-Li30)  Complete","2008-02-11","2008-02-08"]
["MS3_LN025","Start Linac (Li20-Li30) Commissioning","2008-04-08","2008-04-07"]
["MS3_LN030","Linac Commissioning Review Complete - S20-30","2007-01-30","2007-01-29"]
["MS3_LN032","Linac Commissioning Review Complete - LTU","2008-05-13","2008-05-12"]
["MS3_LN035","LTU Component Installation Complete","2008-05-12","2008-05-09"]
["MS3_LN055","E-Dump Component Installation Complete","2008-04-28","2008-04-25"]
["MS3_PM025","Advanced Procurement Management Plan Complete","2004-02-29","2004-02-28",null,"2004-02-29","2004-02-28"]
["MS3_PM030","LCLS ARR Complete (BTH thru FEH)","2008-05-12","2008-05-09"]
["MS3_PM031","Resource Loaded Cost & Schedule (Final) Complete","2004-05-01","2004-04-30",null,"2004-05-01","2004-04-30"]
["MS3_PM035","1st Monthly Report (with Earned Value) Submitted","2004-05-01","2004-04-30",null,"2004-05-01","2004-04-30"]
["MS3_PM040","Fire Hazard Analysis Review @ SLAC","2005-07-18","2005-07-15"]
["MS3_PM042","Risk Management Plan Complete","2004-05-01","2004-04-30",null,"2004-05-01","2004-04-30"]
["MS3_PM045","Prelim Safety Assessment Doc (PSAD) Submitted","2004-05-01","2004-04-30",null,"2004-05-01","2004-04-30"]
["MS3_PM050","Project Mgmt Control Syst (PMCS) Review Complete","2004-05-01","2004-04-30",null,"2004-05-01","2004-04-30"]
["MS3_PM055","Project Mgmt Plan Complete","2004-05-01","2004-04-30",null,"2004-05-01","2004-04-30"]
["MS3_UN005","MMF Qualified & Ready to Measure Prod Undulators","2006-07-31","2006-07-28"]
["MS3_UN006","1st Article Vendor A Undulator 1 Rcvd @ SLAC","2006-06-05","2006-06-02"]
["MS3_UN010","1st Article Vendor B Undulator 2 Rcvd @ SLAC","2006-06-05","2006-06-02"]
["MS3_UN015","25% production undulators received","2006-09-27","2006-09-26"]
["MS3_UN018","Undulator Mock-up Completed","2006-05-01","2006-04-28"]
["MS3_UN020","Undulator System Installation Complete","2008-07-21","2008-07-18"]
["MS3_UN022","50% production undulators received","2006-12-13","2006-12-12"]
["MS3_UN025","Start Undulator Commissioning (1st Light)","2008-07-21","2008-07-18"]
["MS3_UN027","75% production undulators received","2007-03-26","2007-03-23"]
["MS3_UN028","Award of 1st Articles Mag Assy to Vendors Comp","2005-10-27","2005-10-26"]
["MS3_UN029","Undulator Production Units (33) Received","2007-05-15","2007-05-14"]
["MS3_UN040","Hydrostatic Level System Complete","2008-07-21","2008-07-18"]
["MS3_UN042","Wire Monitoring System Complete","2008-07-21","2008-07-18"]
["MS3_XE005","Start XES Checkout","2008-03-04","2008-03-03"]
["MS3_XE012","XE Network Design Review Complete","2007-05-14","2007-05-11"]
["MS3_XE015","2-D Pixel Detector Production Start","2007-12-03","2007-11-30"]
["MS3_XE017","Final Design Review Beamline Control Complete","2007-09-05","2007-09-04"]
["MS3_XE020","XE Laser System Final Design Review Complete","2008-02-05","2008-02-04"]
["MS3_XE025","Award of Near Hall Oscillator Laser/Pump","2008-04-08","2008-04-07"]
["MS3_XE030","Complete 2-D X-Ray Detector Statement of Work","2005-07-05","2005-07-01"]
["MS3_XE035","Award of Initial Funding for 2-D X-Ray Detector","2005-07-18","2005-07-15"]
["MS3_XE040","FY-06 Design Review - 2-D X-Ray Detector","2006-11-21","2006-11-20"]
["MS3_XE060","Start XE Installation in Far Hall","2007-10-08","2007-10-05"]
["MS3_XE065","XE Beamline Control Complete","2008-07-09","2008-07-08"]
["MS3_XE070","Network & Cable Installation Complete","2008-10-13","2008-10-10"]
["MS3_XE075","XE Mechanical & Vacuum Installation Complete","2008-09-24","2008-09-23"]
["MS3_XE080","XE Laser Operating in Near Hall","2008-12-02","2008-12-01"]
["MS3_XE085","Complete Acceptance Tests for X-Ray Detectors","2009-01-21","2009-01-20"]
["MS3_XE090","COMP:  Specification for Streak Camera","2006-05-31","2006-05-30"]
["MS3_XE100","COMP: Hire Detector Physicist","2006-04-04","2006-04-03"]
["MS3_XE110","COMP: Hire Atomic Physicist","2006-03-20","2006-03-17"]
["MS3_XT000","FEE Mechanical/Vacuum Installation Complete","2008-02-13","2008-02-12"]
["MS3_XT007","Tunnel Mech/Vac Design Review Complete","2007-10-29","2007-10-26"]
["MS3_XT009","Far Hall Mech/Vac Design Review Complete","2007-04-27","2007-04-26"]
["MS3_XT020","Gas Attenuator Design Review Complete","2006-11-14","2006-11-13"]
["MS3_XT025","Solid Attenuator Ready to Ship to SLAC","2007-06-13","2007-06-12"]
["MS3_XT030","Indirect Imager Ready to Ship to SLAC","2007-09-11","2007-09-10"]
["MS3_XT035","Design Package - Spectral Measurement Complete","2007-01-03","2007-01-02"]
["MS3_XT040","Solid Attenuator Installation Complete","2008-01-02","2007-12-14"]
["MS3_XT043","Start XTOD Installation in Near Hall","2007-07-23","2007-07-20"]
["MS3_XT045","Gas Attenuator Installation Complete","2008-01-02","2007-12-14"]
["MS3_XT050","Tunnel Mech/Vac  Installation Complete","2008-01-03","2008-01-02"]
["MS3_XT055","XT Controls System Tests Complete","2008-01-31","2008-01-30"]
["MS3_XT060","Total Energy Measurement  Installation Complete","2007-11-20","2007-11-19"]
["MS3_XT066","Start Near Experimental Hall Checkout","2008-06-12","2008-06-11"]
["MS3_XT071","Start Far Experimental Hall Checkout","2008-06-12","2008-06-11"]
["MS3_XT080","Start Front End Enclosure Checkout","2008-03-04","2008-03-03"]
["MSBO_000","RF Hut Beneficial Occupancy","2006-03-10","2006-03-09"]
["MSBO_010","Magnetic Msmt Facility(MMF) Beneficial Occupancy","2006-04-04","2006-04-03"]
["MSBO_045","Beam Dump Beneficial Occupancy","2007-10-10","2007-10-09"]
["MSBS_090","Shutdown of FFTB Operations","2006-04-10","2006-04-07"]
["MSBS_115","FY05 Shutdown: HW Reqd for Installation","2005-10-03","2005-09-30"]
["MSBS_120","FY05 Shutdown Over","2005-11-01","2005-10-31"]
["MSBS_125","FY06 Shutdown: HW Reqd for Installation","2006-08-01","2006-07-31"]
["MSBS_130","FY06 Shutdown Over","2006-12-01","2006-11-30"]
["MSBS_135","FY07 Shutdown: HW Reqd for Installation","2007-09-04","2007-08-31"]
["MSBS_140","FY07 Shutdown Over","2007-12-03","2007-11-30"]
["MSBS_145","Start FY08 Shutdown","2008-10-01","2008-09-30"]
["MSBS_150","FY08 Shutdown Over","2009-01-05","2009-01-02"]
["MSC_CF000","CRIT:  Release RFP T3 Construct (RY-CLOC)","2005-05-02","2005-04-29"]
["MSC_CF005","CRIT: Rel RFP T3 Const. Pkg. RF Hut & S20/Alcove","2005-04-02","2005-04-01",null,"2005-04-02","2005-04-01"]
["MSC_CF006","CRIT:  Release RFP T3 Construction Pkg (Linac)","2006-06-28","2006-06-27"]
["MSC_CF010","CRIT: Release RFP T3 Construction Contract (MMF)","2005-04-15","2005-04-14",null,"2005-04-15","2005-04-14"]
["MSC_CF020","CRIT:  Release RFP Construction Mgmt Pkg (CM)","2005-07-26","2005-07-25",null,"2005-07-26","2005-07-25"]
["MSC_IJ000","CRIT: Release RFP for Drive Laser","2004-10-16","2004-10-15",null,"2004-10-16","2004-10-15"]
["MSC_LN005","CRIT: Release RFP X-Band Klystron","2005-02-26","2005-02-25",null,"2005-02-26","2005-02-25"]
["MSC_PM000","CRIT: Start Procurement Package - PMCS Support","2004-10-02","2004-10-01",null,"2004-10-02","2004-10-01"]
["MSC_UN005","CRIT: Release RFP Ti Strongback","2005-01-15","2005-01-14",null,"2005-01-15","2005-01-14"]
["MSC_UN010","CRIT: Release RFP  Magnet Blocks","2005-03-24","2005-03-23",null,"2005-03-24","2005-03-23"]
["MSC_UN015","CRIT: Release RFP Magnet Poles","2005-02-05","2005-02-04",null,"2005-02-05","2005-02-04"]
["MSC_UN016","CRIT: Release RFP - Quadrupoles","2006-02-03","2006-02-02"]
["MSC_UN020","CRIT: Release RFP Magnet Assemblies - 1st Art","2005-06-29","2005-06-28",null,"2005-06-29","2005-06-28"]
["MSC_UN030","CRIT: Release RFP - Fixed Supports","2006-05-10","2006-05-09"]
["MSC_XT001","CRIT: Release RFP Ion Gauges","2007-01-29","2007-01-26"]
["MSC_XT002","CRIT: Release RFP Ion Pumps","2007-01-29","2007-01-26"]
["MS_205","CR Funding","2004-12-28","2004-12-27",null,"2004-12-28","2004-12-27"]
["MS_210","FY05 Funding","2004-10-02","2004-10-01",null,"2004-10-02","2004-10-01"]
["MS_220","FY06 Funding","2005-10-03","2005-09-30"]
["MS_235","Swing Procurements Funding","2006-10-02","2006-09-29"]
["MS_250","FY07 - Spares Funds Available","2006-10-03","2006-10-02"]
["PM02020044","Design LLRF - Combined","2005-06-10","2006-06-30"]
["PM02020050","COMP: LLRF Design Combined","2006-07-03","2006-06-30"]
["PM02030311","Design Faraday Cup Controls","2005-07-01","2006-06-30"]
["PM02030314","COMP: Faraday Cup Controls Design","2006-07-03","2006-06-30"]
["PM02030411","Design Tune-up Dump Controls","2005-05-02","2006-06-30"]
["PM02030414","COMP: Tune-Up Dump Controls","2006-07-03","2006-06-30"]
["PM02030511","Design Profile Monitors","2005-07-01","2006-06-30"]
["PM02030514","COMP: Profile MonitorDesign","2006-07-03","2006-06-30"]
["PM100_0000","Global Laser Coordination - PED","2005-05-02","2005-09-30"]
["PM100_0005","Global Laser Coordination - FY06","2005-10-03","2006-09-29"]
["PM110_0010","Radiation Physics - PED","2005-05-02","2005-09-30"]
["PM110_0011","Radiation Physics- CONST FY06","2005-10-03","2006-09-29"]
["PM110_0012","Radiation Physics- CONST FY07-FY09","2006-10-02","2009-03-30"]
["PM11C_002","Global Controls Management - OPC FY06 forward","2005-10-03","2009-03-30"]
["PM120_0020","ESH Management & Coordination - PED","2005-05-02","2005-09-30"]
["PM120_0021","ESH Management & Coordination - (Hislop)","2005-05-02","2005-09-30"]
["PM120_0022","ESH Management & Coordination - (Hislop) -CONST","2005-10-03","2006-09-29"]
["PM120_0024","Hazard Analysis Consulting - PED","2005-05-02","2005-09-30"]
["PM120_002X",null,"2005-05-02","2005-05-02"]
["PM120_0030","Seismic & Engineering - PED","2005-05-02","2005-09-30"]
["PM120_0031","Seismic & Engineering - CONST","2005-10-03","2009-03-30"]
["PM120_0A23","ESH Management & Coordination - CONST A","2005-10-03","2006-09-29"]
["PM120_0A25","Hazard Analysis Consulting - CONST A","2005-10-03","2006-09-29"]
["PM120_0B23","ESH Management & Coordination - CONST B","2006-10-02","2009-03-30"]
["PM120_0B25","Hazard Analysis Consulting - CONST B","2006-10-02","2009-03-30"]
["PM20101A05","RF Conditioning Controls Commissioning","2006-10-02","2006-12-05"]
["PM20101A10","RF Gun Ops with Beam-Controls Comissioning-A","2007-07-09","2007-10-08"]
["PM20101A15","RF Gun Ops with Beam-Controls Comissioning-B","2007-07-09","2007-07-26"]
["PM20101A20","L0-1&L0-2 Controls Commissioning","2007-10-29","2008-02-15"]
["PM20101A25","L0&SAB Controls Commissioning","2007-11-26","2008-01-14"]
["PM20101A30","DL1 Controls Commissioning","2007-11-09","2008-01-07"]
["PM20101A35","Injector Controls Optimization Commissioning","2006-12-15","2008-01-07"]
["PM20101B05","L1-BC1 Controls Commissioning","2007-04-18","2007-05-25"]
["PM20101B10","L2-BC2-L3 Controls Commissioning","2007-11-16","2008-01-24"]
["PM20101B15","LTU + Dump Controls Commissioning","2008-01-25","2008-03-19"]
["PM20101B20","Linac Controls Optimization Commissioning","2006-10-03","2007-10-08"]
["PM210_0130","Consulting SLAC Physicists (R&D)","2005-05-02","2005-09-30"]
["PM210_0240","Consulting Collaboration Physicists (R&D)","2005-05-02","2005-09-30"]
["PM210_0250","Global Controls Physicists Liaison (R&D)","2005-05-02","2005-09-30"]
["PM210_0260","R&D Studies & Prototyping","2005-05-02","2005-09-30"]
["PM210_0265","Low Level Applications R&D","2005-05-02","2005-09-30"]
["PM210_0270","Consulting SLAC Physicists (PreOps)","2005-10-03","2009-03-30"]
["PM210_0271","Planning Experiment Startup (Preops)","2005-11-01","2006-03-31"]
["PM210_0275","Low Level Applications Commissioning","2005-10-03","2009-03-30"]
["PM210_0280","Global Controls Physicists Liaison (PreOps)","2005-10-03","2006-09-29"]
["PM210_0281","Global Controls Physicists Liaison (PreOps)","2006-10-02","2009-03-30"]
["PM210_0290","Physics Group Leader (R&D)","2005-05-02","2005-09-30"]
["PM210_0291","Define Technical Requirements/Parameters(PED)","2005-05-02","2005-09-30"]
["PM210_0292","Define Technical Requirements/Parameters(LLP)","2005-10-03","2006-09-29"]
["PM210_0300","Injector Physicists (R&D)","2005-05-02","2005-09-30"]
["PM210_0310","Linac Physicists (R&D)","2005-05-02","2005-09-30"]
["PM210_0320","Undulator Physicists (R&D)","2005-05-02","2005-09-30"]
["PM210_0330","X-Ray Transport Physicists (R&D)","2005-05-02","2005-09-30"]
["PM210_0340","X-Ray Endstation Physicists (R&D)","2005-05-02","2005-09-30"]
["PM210_0350","Conventional Facility Physicists (R&D)","2005-05-02","2005-09-30"]
["PM210_0360","Physics Group Leader (PreOps)","2005-10-03","2009-03-30"]
["PM210_0370","Injector Physicists (PreOps)","2005-10-03","2006-09-29"]
["PM210_0371","Injector Physicists (PreOps)","2006-10-02","2009-03-30"]
["PM210_0375","Laser & RF Gun Physics Development (R&D)","2005-05-02","2005-09-30"]
["PM210_0380","Linac Physicists (PreOps)","2005-10-03","2006-09-29"]
["PM210_0381","Linac Physicists (PreOps)","2006-10-02","2009-03-30"]
["PM210_0385","Laser & RF Gun Physics Development (PreOps)","2005-10-03","2009-03-30"]
["PM210_0390","Undulator Physicists (PreOps)","2005-10-03","2006-09-29"]
["PM210_0391","Undulator Physicists (PreOps)","2006-10-02","2009-03-30"]
["PM210_0400","X-Ray Transport Physicists (PreOps)","2005-10-03","2009-03-30"]
["PM210_0410","X-Ray Endstation Physicists (PreOps)","2005-10-03","2009-03-30"]
["PM210_0420","Conventional Facility Physicists (PreOps)","2005-10-03","2006-09-29"]
["PM210_0421","Conventional Facility Physicists (PreOps)","2006-10-02","2009-03-30"]
["PM210_0430","Consulting Collaboration Physicists (PreOps)","2005-10-03","2009-03-30"]
["PM210_0440","Physics Programmatic Travel (R&D)","2005-05-02","2005-09-30"]
["PM210_0450","Physics Progammatic Travel (PreOps)","2005-10-03","2009-03-30"]
["PM210_0460","SAC/FAC Travel - PED","2005-05-02","2005-09-30"]
["PM210_0470","SAC/FAC Travel (PreOps)","2005-10-03","2009-03-30"]
["PM210_0480","Pre-ops Electrical Power Usage (1.5k hrs) - 2007","2006-10-03","2007-09-28"]
["PM210_0490","Pre-ops Electrical Power Usage (3.0k hrs) - 2008","2007-10-02","2008-09-30"]
["PM210_0494","Additional Startup Costs-FY08","2007-10-02","2008-09-30"]
["PM210_0495","Pre-ops Electrical Power Usage (3.0k hrs) - 2009","2008-10-01","2009-03-30"]
["PM210_0497","Additional Startup Costs-FY09","2008-10-02","2009-03-31"]
["PM210_0510","SLAC Linac Legacy Upgrades","2006-10-02","2007-09-28"]
["PM210_0515","Control Room Support","2008-06-02","2009-03-30"]
["PM210_1000","PMCS Support - Maintenance - FY07","2006-10-02","2007-09-28"]
["PM210_1010","PMCS Support - Maintenance - FY08","2007-10-01","2008-09-30"]
["PM210_1020","PMCS Support - Maintenance - FY09","2008-10-01","2009-03-30"]
["PM211_0010","Project Director - PED","2005-05-02","2005-09-30"]
["PM211_0011","Project Director - CONST FY06","2005-10-03","2006-09-29"]
["PM211_0012","Project Director - CONST FY07-FY09","2006-10-02","2009-03-30"]
["PM211_0020","Chief Engineer - PED","2005-05-02","2005-09-30"]
["PM211_0021","Chief Engineer - CONST FY06","2005-10-03","2006-09-29"]
["PM211_0022","Chief Engineer - CONST FY07-FY09","2006-10-02","2009-03-30"]
["PM211_0025","E-Beam Systems Manager - PED","2005-05-02","2005-09-30"]
["PM211_0027","E-Beam Systems Manager - FY06","2005-10-03","2006-09-29"]
["PM211_0030","Budget/Finance Officer - PED","2005-05-02","2005-09-30"]
["PM211_0031","Budget/Finance Officer - FY06","2005-10-03","2006-09-29"]
["PM211_0040","Administrative Support - SLAC 1 - PED","2005-05-02","2005-09-30"]
["PM211_0041","Administrative Support - SLAC 1 - FY06","2005-10-03","2006-09-29"]
["PM211_0050","Administrative Support - SLAC 2 - PED","2005-05-02","2005-09-30"]
["PM211_0051","Administrative Support - SLAC 2 - FY06","2005-10-03","2006-09-29"]
["PM211_0052","Administrative Support - CF & Proc - FY06","2005-08-02","2006-09-29"]
["PM211_0055","Administrative Support - CF & Proc - PED","2005-05-02","2005-08-01"]
["PM211_0060","Photon System Manager - PED","2005-05-02","2005-09-30"]
["PM211_0061","Photon System Manager - FY06","2005-10-03","2006-09-29"]
["PM211_1010","E-Beam Systems Manager - FY07-09","2006-10-02","2009-03-30"]
["PM211_1020","Budget/Finance Officer - FY07-09","2006-10-02","2009-03-30"]
["PM211_1030","Photon System Manager - FY07-09","2006-10-02","2009-03-30"]
["PM211_1040","Administrative Support -SLAC 1 - FY07-09","2006-10-02","2009-03-30"]
["PM211_1050","Administrative Support - SLAC 2 - FY07-09","2006-10-02","2009-03-30"]
["PM211_1060","Administrative Support - CF & Proc - FY07-09","2006-10-02","2009-03-30"]
["PM212_0015","AWARD:  PMCS Support-FY05","2004-11-29","2004-11-29",null,"2004-11-29","2004-11-29"]
["PM212_0016","PMCS Support - Maintenance - PED","2005-05-02","2005-09-30"]
["PM212_0017","PMCS Support - Maintenance - FY06","2005-10-03","2006-09-29"]
["PM212_0018","AWARD:  PMCS Support-FY06","2005-10-03","2005-10-12"]
["PM212_0020","Website Support - PED","2005-05-02","2005-09-30"]
["PM212_0021","Website Support - CONST","2005-10-03","2009-03-30"]
["PM212_0022","AWARD:  PMCS Support-FY07","2006-10-03","2006-10-12"]
["PM212_0023","AWARD:  PMCS Support-FY08","2007-10-01","2007-10-10"]
["PM212_0024","AWARD:  PMCS Support-FY09","2008-10-01","2008-10-10"]
["PM212_0030","Relational Database Support - PED","2005-05-02","2005-09-30"]
["PM212_0031","Relational Database Support - CONST","2005-10-03","2009-03-30"]
["PM212_0040","Procurement Support - PED","2005-05-02","2005-09-30"]
["PM212_0041","Procurement Support - CONST","2005-10-03","2009-03-30"]
["PM212_0050","QA/QC Support - PED","2005-05-02","2005-09-30"]
["PM212_0051","QA/QC Support - CONST","2005-10-03","2009-03-30"]
["PM212_0060","Software Licenses - PED","2005-05-02","2005-09-30"]
["PM212_0061","Software Licenses - CONST","2005-10-03","2009-03-30"]
["PM212_0070","Computing Support - PED","2005-05-02","2005-09-30"]
["PM212_0071","Computing Support - CONST","2005-10-03","2009-03-30"]
["PM212_0080","Recruiting/Relocation Support - PED","2005-05-02","2005-09-30"]
["PM212_0081","Recruiting/Relocation Support - CONST","2005-10-03","2009-03-30"]
["PM212_0717","PMCS Support - Maintenance - FY07","2006-10-02","2007-09-28"]
["PM212_0817","PMCS Support - Maintenance - FY08","2007-10-01","2008-09-30"]
["PM212_0917","PMCS Support - Maintenance - FY09","2008-10-01","2009-03-30"]
["PM213_0000","Project Director - R&D","2005-05-02","2005-09-30"]
["PM213_0001","Project Director -PREOPS FY07-FY09","2006-10-02","2009-03-30"]
["PM213_0005","Chief Engineer - R&D","2005-05-02","2005-09-30"]
["PM213_0006","Chief Engineer - PREOPS FY07-FY09","2006-10-02","2009-03-30"]
["PM213_0007","E-Beam Systems Oversight Manager - R&D","2005-05-02","2005-09-30"]
["PM213_0010","SLAC Project Office M&S - PED","2005-05-02","2005-09-30"]
["PM213_0011","SLAC Project Office M&S - CONST","2005-10-03","2005-11-30"]
["PM213_0012","SLAC Project Office M&S - CONST FY06","2005-12-01","2006-09-29"]
["PM213_0013","SLAC Project Office M&S - CONST FY07-FY09","2006-10-02","2009-03-30"]
["PM213_0015","Budget/Finance Officer - R&D","2005-05-02","2005-09-30"]
["PM213_0020","Tele/Video Conferencing  - PED","2005-05-02","2005-09-30"]
["PM213_0021","Tele/Video Conferencing - CONST","2005-10-03","2009-03-30"]
["PM213_0025","Administrative Support - SLAC 1 - R&D","2005-05-02","2005-09-30"]
["PM213_0030","Computer M&S - PED","2005-05-02","2005-09-30"]
["PM213_0031","Computer M&S - CONST","2005-10-03","2009-03-30"]
["PM213_0040","Misc. Shipping/Storage Costs - PED","2005-05-02","2005-09-30"]
["PM213_0041","Misc. Shipping/Storage Costs CONST","2005-10-03","2009-03-30"]
["PM213_0050","Project Related Travel - PED","2005-05-02","2005-09-30"]
["PM213_0051","Project Related Travel - CONST","2005-10-03","2009-03-30"]
["PM213_0055","Building Refurb/Remodeling @ SLAC - PED","2005-05-02","2005-09-30"]
["PM213_0060","Building Refurb/Remodeling @ SLAC - CONST","2005-10-03","2009-03-30"]
["PM213_0070","Review Committee Support - PED","2005-05-02","2005-09-30"]
["PM213_0071","Review Committee Support - CONST","2005-10-03","2009-03-30"]
["PM213_0100","SSRL Physics Support","2005-05-02","2005-06-14"]
["PM213_0105","SSRL Physics Support","2005-10-03","2005-12-16"]
["PM22210000","Define Injector Timing module Reqmts CP","2005-05-02","2005-07-18"]
["PM22210003","Controls Commissioning","2006-12-06","2007-10-17"]
["PM22210005","COMP: Injector Timing Module Rqmts Def","2005-07-19","2005-07-18"]
["PM22210010","Prep Bid Pak-Injector Timing modules","2005-07-19","2005-08-15"]
["PM22210015","RELEASE: RFP-Injector Timing modules","2005-08-16","2005-08-15"]
["PM22210020","Vendors Prep Prop-Injector Timing Modules","2005-08-16","2005-09-14"]
["PM22210025","RCV: Prop-Injector Timing modules","2005-09-15","2005-09-14"]
["PM22210030","Evaluate Vendor Proposals","2005-09-15","2005-09-28"]
["PM22210045","Manage/Work with Vendor","2005-09-29","2006-01-24"]
["PM22210050","RCV: Injector Timing Modules from Vendor","2006-01-25","2006-01-24"]
["PM22210055","Procure SLCnet cable to MPG micro 360 Hz signal","2006-06-27","2006-07-11"]
["PM22210060","Procure VME crate (1) w/IOC(1), VxWorks license","2006-01-25","2006-03-24"]
["PM22210065","Procure cables","2006-01-25","2006-02-23"]
["PM22210070","Write Test Docs - Injector Timing modules","2006-01-25","2006-01-31"]
["PM22210075","Install access to PEP-II timing signal, control","2006-07-12","2006-07-12"]
["PM22210080","RCV: Procured parts","2006-03-27","2006-03-24"]
["PM22210083","Assemble procured parts","2006-03-27","2006-04-19"]
["PM22210085","AVAIL: Test Stand Installed in Test Lab","2006-04-20","2006-04-19"]
["PM22210090","Procure Master & Distributed Timing Hardware","2006-03-01","2006-05-26"]
["PM22210095","Procure Splitter to Main Drive Line (MDL) 476 MH","2006-03-01","2006-05-26"]
["PM22210100","Procure Fiducial Output Module","2006-03-01","2006-05-26"]
["PM22210105","Procure Fiducial RF Amplifier","2006-03-01","2006-05-26"]
["PM22210110","Procure SLCnet cable to MPG micro 360 Hz signal","2006-03-01","2006-05-26"]
["PM22210115","Procure Timing System Heliax Cableplant","2006-03-01","2006-05-26"]
["PM22210116","Implement Fast-feedback in the IOC","2005-11-21","2006-05-26"]
["PM22210117","Port Fast-feedbac software from Kissnet to Ether","2006-05-30","2006-06-26"]
["PM22210160","Write Test S/W - Injector Timing modules","2006-01-25","2006-02-07"]
["PM22210165","Integrate software & hardware","2006-04-20","2006-05-03"]
["PM22210170","Integrate with SLC TIming Sys","2006-07-13","2006-08-09"]
["PM22210175","Perform lab tests on Injector Timing modules","2006-07-13","2006-08-09"]
["PM22210180","AVAIL: Injector Timing Ready for Install","2006-08-10","2006-08-09"]
["PM300_0050","Global Alignment Coordination - PED","2005-05-02","2005-09-30"]
["PM300_0051","Global Alignment Coordination - CONST","2005-10-03","2009-03-30"]
["PM300_0060","Installation Coordination - PED","2005-05-02","2005-09-30"]
["PM300_0061","Installation Coordination - CONST","2005-10-03","2009-03-30"]
["PM300_0062","Design Supervisor - PED","2005-05-02","2005-09-30"]
["PM300_0063","Design Supervisor - CONST","2005-10-03","2009-03-30"]
["PM300_0150","Surface Network Oversight and Integration","2005-10-03","2007-09-28"]
["PM300_0160","Procure Surface Network Components","2005-10-03","2006-04-07"]
["PM300_0170","Install and Measure Surface Network","2005-10-03","2007-09-28"]
["PM301_7000","Global Laser Coordination - FY07","2006-10-02","2007-09-28"]
["PM301_7010","E-Beam Systems Manager - FY07","2006-10-02","2007-09-28"]
["PM301_7020","Budget/Finance Officer - FY07","2006-10-02","2007-09-28"]
["PM301_7030","Photon System Manager - FY07","2006-10-02","2007-09-28"]
["PM301_7040","Administrative Support -SLAC 1 - FY07","2006-10-02","2007-09-28"]
["PM301_7050","Administrative Support - SLAC 2 - FY07","2006-10-02","2007-09-28"]
["PM301_7060","Administrative Support - CF & Proc - FY07","2006-10-02","2007-09-28"]
["PM301_8000","Global Laser Coordination - FY08","2007-10-01","2008-09-30"]
["PM301_8010","E-Beam Systems Manager - FY08","2007-10-01","2008-09-30"]
["PM301_8020","Budget/Finance Officer - FY08","2007-10-01","2008-09-30"]
["PM301_8030","Photon System Manager - FY08","2007-10-01","2008-09-30"]
["PM301_8040","Administrative Support -SLAC 1 - FY08","2007-10-01","2008-09-30"]
["PM301_8050","Administrative Support - SLAC 2 - FY08","2007-10-01","2008-09-30"]
["PM301_8060","Administrative Support - CF & Proc - FY08","2007-10-01","2008-09-30"]
["PM301_9000","Global Laser Coordination - FY09","2008-10-01","2009-03-30"]
["PM301_9010","E-Beam Systems Manager - FY09","2008-10-01","2009-03-30"]
["PM301_9020","Budget/Finance Officer - FY09","2008-10-01","2009-03-30"]
["PM301_9030","Photon System Manager - FY09","2008-10-01","2009-03-30"]
["PM301_9040","Administrative Support -SLAC 1 - FY09","2008-10-01","2009-03-30"]
["PM301_9050","Administrative Support - SLAC 2 - FY09","2008-10-01","2009-03-30"]
["PM301_9060","Administrative Support - CF & Proc - FY09","2008-10-01","2009-03-30"]
["PM3051101","Design MPS","2005-12-15","2006-04-25"]
["PM3051111","COMP: MPS Design","2006-04-26","2006-04-26"]
["PM3051121","Write First Article for MPS","2006-04-27","2006-11-29"]
["PM3051131","Procure 1 Set MPS Cntrls Misc. Hardware","2006-04-27","2006-05-24"]
["PM3051141","RCV: Parts - Controls MPS","2006-05-25","2006-05-24"]
["PM400_0030","Education Support - PED","2005-05-02","2005-09-30"]
["PM400_0031","Education Support - CONST","2005-10-03","2009-03-30"]
["PM400_0040","Education/Outreach M&S - PED","2005-05-02","2005-09-30"]
["PM400_0041","Education/Outreach M&S - CONST","2005-10-03","2009-03-30"]
["PM502_0001","Build RF Boards - Rev .B.C.D","2006-07-03","2007-04-03"]
["PM502_0005","Write First Article RF S/W Documentation","2006-07-03","2007-04-03"]
["PM502_0010","Build First Article Hardware","2007-04-04","2007-05-15"]
["PM50301001","Design Linac Wire Scanners","2005-07-01","2006-06-30"]
["PM50301005","COMP: Linac Wire Scanner Dsgn - Release for Fab","2006-07-03","2006-06-30"]
["PM50301010","Write First Article SW","2006-07-03","2006-09-29"]
["PM50302006","Design Toroid Controls","2005-05-02","2006-06-30"]
["PM50302007","COMP: Toroid Controls Design","2006-07-03","2006-06-30"]
["PM50302010","Write First Article SW - Toroid","2006-07-03","2006-09-07"]
["PM50303001","Write First Article SW - Faraday Cups","2006-07-03","2006-10-24"]
["PM50305010","Write First Article S/W for Profile Monitors","2006-07-03","2007-01-22"]
["PM50306011","Design EO Disgnostics","2005-07-01","2005-11-21"]
["PM50307006","Design BPMs","2005-05-02","2006-06-30"]
["PM50307007","COMP: BPM Design","2006-07-03","2006-07-03"]
["PM50307010","Write First Article S/W for BPMs","2006-07-05","2007-03-26"]
["PM50307015","Procure Prototype Board & Parts","2006-07-05","2006-10-02"]
["PM50307025","RCV: design board & parts","2006-10-03","2006-10-02"]
["PM50308001","Design Linac Stoppers","2005-10-03","2006-12-15"]
["PM50308005","COMP: Controls Design - Stoppers","2007-01-02","2006-12-15"]
["PM50309001","Design Bunch Length Monitors","2005-10-03","2006-06-30"]
["PM50309005","COMP: Controls Design - Bunch Length Monitors","2006-07-03","2006-06-30"]
["PM50310001","Design Beam Loss Monitors","2006-01-03","2006-06-30"]
["PM50310005","COMP: Controls Design - Beam Loss Monitors","2006-07-03","2006-06-30"]
["PM504_0001","Design Gun Laser","2005-10-03","2006-01-11"]
["PM504_0005","COMP: Gun Laser Controls Design","2006-01-12","2006-01-11"]
["PM504_0015","Laser Controls Design Support","2006-01-12","2006-07-03"]
["PM505_0001","Design Laser Heater Controls","2006-07-05","2007-01-08"]
["PM505_0005","COMP: Laser Heater Controls Design","2007-01-09","2007-01-08"]
["PM506_0001","Timing Subsystem Design","2005-07-11","2005-09-19"]
["PM506_0003","Timing Controls 1st Article","2005-07-11","2006-02-28"]
["PM506_0005","COMP: Controls Design - Linac Timing","2006-03-01","2006-02-28"]
["PM507_0001","Design Vacuum Controls","2005-05-02","2005-10-25"]
["PM507_0005","COMP: Vacuum Controls Design","2005-10-26","2005-10-25"]
["PM507_0010","First Article Vacuum Software","2005-10-26","2006-06-28"]
["PM509_0006","Design Power Supply - NEW","2005-05-02","2006-02-23"]
["PM509_0010","COMP: Power Supply Design","2006-02-24","2006-02-23"]
["PM509_0012","Write First Article S/W for Power Supplies","2006-02-24","2006-07-17"]
["PM509_0015","Define Power Conv Spec Requirements","2005-05-02","2005-05-31"]
["PM509_0020","COMP: Injector Power Conv Spec Requirements","2005-06-01","2005-05-31"]
["PM509_0035","Prep Bid Pak -  Power Supplies - (Dipole Type)","2005-06-01","2005-06-07"]
["PM509_0040","Prep Bid Pak -  Power Supplies - (Trim Type)","2005-06-01","2005-06-07"]
["PM510_0061","PPS L1 DESIGN","2005-07-01","2006-02-17"]
["PM510_0062","COMP: PPS/MPS Design","2006-02-21","2006-02-21"]
["PM510_0072","PPS L2 Design","2006-02-22","2006-09-22"]
["PM510_0075","COMP: PPS L2 DESIGN","2006-09-25","2006-09-25"]
["PM510_0082","PPS L3 Design","2006-09-26","2007-05-14"]
["PM510_0085","COMP: PPS L3 DESIGN","2007-05-15","2007-05-15"]
["PM512_0001","Global Controls Management - PED","2005-05-02","2005-09-30"]
["PM512_0002","Global Contorls Mgmt - PED Supplemental","2005-08-01","2005-09-30"]
["PM512_0005","Global Controls Management - CONST","2005-10-03","2009-03-30"]
["PM512_0015","Global Controls System Administrator - CONST","2005-10-03","2009-03-30"]
["PM512_0020","Write low level application SW Rqrmnts - PED","2005-05-02","2006-05-01"]
["PM512_0025","Write low level application SW Rqrmnts - CONST","2006-05-02","2007-04-16"]
["PM512_0026","Write Low Level application SW Rqrmnts - Const","2007-04-17","2008-03-12"]
["PM512_0030","High Level Application Programming - 1st Phase","2005-05-02","2005-10-27"]
["PM512_0035","High Level Application Programming - CON","2005-10-28","2006-02-14"]
["PM512_0040","High Level Application Programming - CONST","2006-02-15","2007-02-13"]
["PM512_0041","High Level Application Programming - CONST","2007-02-14","2008-02-27"]
["PM512_0045","LCLS Beam Instrumentatn Cntls & Test Equip FY05","2005-05-02","2006-02-14"]
["PM512_0046","LCLS Beam Instrumentatn Cntls & Test Equip FY06","2006-02-15","2007-02-13"]
["PM512_0047","LCLS Beam Instrumentatn Cntls & Test Equip FY07","2007-02-14","2008-02-14"]
["PM512_0050","SLAC Place Order Beam Instrument Cntls &Test Equ","2005-05-02","2005-07-05"]
["PM512_0055","RCV: Beam Instrument Cntls & Test Equip","2005-07-06","2005-07-05"]
["PM512_0060","SLAC MCC Controls Upgrade","2006-10-03","2007-10-05"]
["PM512_0065","SLAC Place Order Controls Upgrade","2006-10-03","2006-11-13"]
["PM512_0070","RCV: Controls Upgrade","2006-11-14","2006-11-13"]
["PM513_0001","SLC Aware IOC - PED","2005-05-02","2005-10-25"]
["PM513_0005","SLC Aware IOC - CON","2005-10-03","2005-12-28"]
["PMLCLS_LOE","LCLS LOE Complete","2009-04-01","2009-03-31"]
["PM_LOE","PM LOE Complete","2009-03-31","2009-03-30"]
["SSCF_0105","Start Procurement for Title 3 Construction","2005-03-22","2005-03-21",null,"2005-03-22","2005-03-21"]
["SSCF_0110","S20 Injector Facility Construction","2005-05-02","2006-03-01"]
["SSCF_0115","S20 Injector Facility Alcove B.O.","2006-07-24","2006-07-21"]
["SSCF_0415","Magnetic Measurment Facility Construction","2005-05-02","2006-03-01"]
["SSCF_0420","Magnetic Measurment Facility B.O.","2006-04-04","2006-04-03"]
["SSCF_0510","Undulator Facility Construction","2006-08-25","2007-04-30"]
["SSCF_0515","Undulator Facility B.O.","2007-06-05","2007-06-04"]
["SSCF_0615","Beam Dump B.O.","2007-10-10","2007-10-09"]
["SSCF_0815","Near Experimental Hall B.O.","2007-06-19","2007-06-18"]
["SSCF_0915","Far Experimental Hall B.O.","2007-09-05","2007-09-04"]
["SSCF_1015","Front End Enclosure B.O.","2007-10-08","2007-10-05"]
["SSCF_1115","Beam Transport Hall  B.O.","2008-01-04","2008-01-03"]
["SSCF_1215","Central Lab Office Center B.O.","2008-11-11","2008-11-10"]
["SSCF_1315","X-Ray Transport & Diagnostics Tunnel B.O.","2007-10-15","2007-10-12"]
["SSIJ_0110","Drive Laser Design/Procurement","2005-06-27","2006-06-16"]
["SSIJ_0115","Drive Laser Integration & Checkout","2006-03-30","2007-03-29"]
["SSIJ_0120","UV Beam to Cathode","2007-07-23","2007-07-20"]
["SSIJ_0125","Start Injector Commissioning","2007-08-03","2007-08-02"]
["SSIJ_0130","Injector Accelerator ARR","2007-09-21","2007-09-20"]
["SSIJ_0200","RF Gun Design/Procurement","2005-05-02","2006-08-03"]
["SSIJ_0205","RF Gun Installation & Checkout","2006-08-04","2006-09-05"]
["SSIJ_0215","RF Gun Commissioning","2006-09-28","2007-10-26"]
["SSLN_0011","BC2 Installation Complete","2008-02-11","2008-02-08"]
["SSLN_0012","BC1 Installation Complete","2006-11-30","2006-11-29"]
["SSLN_0025","Start Linac (Li20-Li30) Commissioning","2008-04-08","2008-04-07"]
["SSLN_0090","Linac ARR","2008-03-10","2008-03-07"]
["SSLN_0100","L1,BC1,L2,BC2,L3,&LTU, E-Dump Design & Procure","2005-07-01","2008-01-18"]
["SSLN_0105","L1,BC1 Installation & C/O","2006-08-01","2006-11-20"]
["SSLN_0110","L2,BC2,L3 Installation & C/O","2007-09-04","2007-11-30"]
["SSLN_0112","LTU Installation & C/O","2008-02-21","2008-04-22"]
["SSLN_0115","E-Dump Installation & C/O","2007-12-03","2008-02-26"]
["SSLN_0120","L1,BC1,L2,BC2,L3,&LTU, E-Dump Commissioning","2006-10-03","2008-06-04"]
["SSLN_0205","FFTB Shutdown","2006-04-10","2006-04-07"]
["SSMS_0100","CD2b - Approve Performance Baseline","2005-04-01","2005-03-31",null,"2005-04-01","2005-03-31"]
["SSMS_0105","CD3a - Approve Start of Long Lead Procurement","2004-10-30","2004-10-29",null,"2004-10-30","2004-10-29"]
["SSMS_0110","CD3b - Approve Start of Construction","2006-03-01","2006-02-28"]
["SSMS_0115","CD4 - Approve Start of Operations","2009-04-01","2009-03-31"]
["SSSS_0305","FY05 Shutdown","2005-10-03","2005-10-31"]
["SSSS_0310","FY06 Shutdown","2006-08-01","2006-11-30"]
["SSSS_0315","FY07 Shutdown","2007-09-04","2007-11-30"]
["SSUN_0105","CRIT: Magnet Poles","2005-02-05","2005-02-04",null,"2005-02-05","2005-02-04"]
["SSUN_0110","CRIT: Ti Strongback","2005-01-14","2005-01-13",null,"2005-01-14","2005-01-13"]
["SSUN_0115","CRIT: Magnet Blocks","2005-03-23","2005-03-22",null,"2005-03-23","2005-03-22"]
["SSUN_0120","RCV: Undulator 1st Articles","2006-04-10","2006-04-07"]
["SSUN_0125","RCV: Undulator 1st Articles MMF","2006-06-05","2006-06-02"]
["SSUN_0130","Last Undulator Production Unit Received","2007-05-15","2007-05-14"]
["SSUN_0135","LCLS ARR","2008-06-10","2008-06-09"]
["SSUN_0140","Undulator Design/Procure","2005-05-02","2007-05-02"]
["SSUN_0145","Undulator Testing at MMF","2006-05-19","2008-01-23"]
["SSUN_0170","Undulator Installation","2007-09-21","2008-06-30"]
["SSUN_0173","1st Light","2008-08-18","2008-08-15"]
["SSXE_0005","Start XES Checkout","2008-03-04","2008-03-03"]
["SSXE_0060","Start XE Installation in Far Hall","2007-10-08","2007-10-05"]
["SSXE_0100","XE Design, Procure,Assy","2006-04-03","2008-05-13"]
["SSXE_0105","XE Installation","2007-05-22","2008-12-05"]
["SSXE_0110","2-D X-Ray Detector Design Procure","2005-05-02","2008-07-24"]
["SSXE_0115","2-D X-Ray Detector Installation","2008-08-29","2008-10-24"]
["SSXE_0120","2-D X-Ray Detector Commission","2005-05-02","2008-10-24"]
["SSXT_0043","Start XTOD Installation in Near Hall","2007-07-23","2007-07-20"]
["SSXT_0066","Start Near Experimental Hall Checkout","2008-06-12","2008-06-11"]
["SSXT_0071","Start Far Experimental Hall Checkout","2008-06-12","2008-06-11"]
["SSXT_0080","Start Front End Enclosure Checkout","2008-03-04","2008-03-03"]
["SSXT_0100","XT Design & Procure","2005-05-02","2007-04-02"]
["SSXT_0105","XT Installation","2007-05-15","2007-09-07"]
["SSXT_0110","XT Commissioning","2008-05-09","2009-03-31"]
["UN11_00011","Project Management - FY05 (PED)","2005-05-02","2005-09-30",null,"2005-05-02"]
["UN11_00026","Oversee Engineering and Integration - FY05 (PED)","2005-05-02","2005-09-30",null,"2005-05-02"]
["UN11_00027","Undulator Mgmt/Engr @ SLAC - FY05 (PED)","2005-05-02","2005-09-30",null,"2005-05-02"]
["UN11_00028","Undulator Designer @ SLAC - FY05 (PED)","2005-05-02","2005-09-30",null,"2005-05-02"]
["UN11_00029","Visiting Physicist","2005-05-02","2005-09-30",null,"2005-05-02"]
["UN11_00036","Controls System Engineering Oversight (PED)","2005-05-02","2005-09-30",null,"2005-05-02"]
["UN11_00037","Undulator Mgmt/Engr @ SLAC - FY06-08 (CNST)","2005-10-03","2009-03-31"]
["UN11_00038","Undulator Designer @ SLAC - FY06-07 (CNST)","2005-10-03","2007-10-02"]
["UN11_00056","Undulator Magnet & Support Engr Oversight (PED)","2005-05-02","2005-09-30",null,"2005-05-02"]
["UN11_00076","Vacuum Engineering Oversight (PED)","2005-05-02","2005-09-30",null,"2005-05-02"]
["UN11_00096","Diagnostics Engineering Oversight (PED)","2005-05-02","2005-09-30",null,"2005-05-02"]
["UN11_00175","Oversee Quality Assurance - FY05 (PED)","2005-05-02","2005-09-30",null,"2005-05-02"]
["UN11_00200","Project Management (CNST)","2005-10-03","2008-02-12"]
["UN11_00220","Oversee Engineering and Integration (CNST)","2005-10-03","2008-02-12"]
["UN11_00230","Controls System Engineering Oversight (CNST)","2005-10-03","2008-02-12"]
["UN11_00240","Undulator Magnet & Support Engr Oversight (CNST)","2005-10-03","2008-02-12"]
["UN11_00250","Vacuum Engineering Oversight (CNST)","2005-10-03","2008-02-12"]
["UN11_00260","Diagnostics Engineering Oversight (CNST)","2005-10-03","2008-02-12"]
["UN11_00269","Monitor Budget, Schedule and Contracts (PED)","2005-05-02","2005-09-30"]
["UN11_00270","Monitor Budget, Schedule and Contracts (CNST)","2005-10-03","2008-02-12"]
["UN11_00290","Oversee Quality Assurance (CNST)","2005-10-03","2007-10-02"]
["UN11_00441","ANL Division - Website Support (CNST) -FY06","2005-10-03","2006-10-02"]
["UN11_00443","ANL Division - Website Support-FY05 (PED)","2005-05-02","2005-09-30",null,"2005-05-02"]
["UN11_00499","ANL Division - PMCS Support (PED)","2005-05-02","2005-09-30"]
["UN11_00500","ANL Division - PMCS Support (CNST)","2005-10-03","2008-02-12"]
["UN11_00520","ANL Division - Website Support (CNST)","2006-10-03","2008-10-02"]
["UN11_00549","ANL Indirect Cost Allocation - FY05 (PED)","2005-05-02","2005-09-30"]
["UN11_00550","ANL Indirect Cost Allocation - FY06 (CNST)","2005-10-03","2006-10-02"]
["UN11_00560","ANL Indirect Cost Allocation - FY07 (CNST)","2006-10-03","2007-10-02"]
["UN11_00570","ANL Indirect Cost Allocation - FY08 (CNST)","2007-10-03","2008-10-03"]
["UN12_00015","Office Supplies and Misc Materials - FY05 (PED)","2005-05-02","2005-09-30",null,"2005-05-02"]
["UN12_00025","Tele/Video Conferencing - FY05 (PED)","2005-05-02","2005-09-30",null,"2005-05-02"]
["UN12_00036","CPUs and Software - FY05 (PED) -2nd Half","2005-05-02","2005-09-30",null,"2005-05-02"]
["UN12_00038","Undulator Controls Lab Construction","2005-05-02","2005-06-20",null,"2005-05-02"]
["UN12_00040","Shipping and Storage (PED)","2005-05-02","2005-09-30",null,"2005-05-02"]
["UN12_00050","Office Supplies and Misc Materials (CNST)","2005-10-03","2008-02-12"]
["UN12_00060","Tele/Video Conferencing (CNST)","2005-10-03","2008-02-12"]
["UN12_00070","CPUs and Software (CNST)","2005-10-03","2008-02-12"]
["UN12_00080","Shipping and Storage (CNST)","2005-10-03","2008-02-12"]
["UN12_00110","Domestic Travel - FY05 (PED)","2005-05-02","2005-09-30",null,"2005-05-02"]
["UN12_00111","Domestic Travel - FY05 (PED) (Rollup)","2005-05-02","2005-09-30",null,"2005-05-02"]
["UN12_00125","Foreign Travel - FY05 (PED)","2005-05-02","2005-09-30",null,"2005-05-02"]
["UN12_00130","Domestic Travel (CNST)","2005-10-03","2008-02-04"]
["UN12_00140","Foreign Travel (CNST)","2005-10-03","2008-02-04"]
["UN21_00141","Advise on overall controls system integration","2005-05-02","2005-09-30",null,"2005-05-02"]
["UN21_00142","Advise on overall controls system integration","2005-10-03","2009-03-31"]
["UN21_J27","Generate UN Hall cable, tray, rack document","2006-01-11","2006-02-14"]
["UN21_J28","Submit UN Hall cable, tray, rack document","2006-02-15","2006-02-14"]
["UN21_J29","Complete estimate of WPM and HLS cable runs","2006-01-11","2006-01-18"]
["UN21_J30","Complete estimate of MPS cable runs","2006-01-11","2006-01-11"]
["UN22_00015","Specify prototype motor interface","2006-01-17","2006-01-30"]
["UN22_00020","Procure prototype motor interfaces","2006-01-31","2006-01-31"]
["UN22_00030","Receive prototype motor interfaces","2006-02-01","2006-02-28"]
["UN22_00040","RCVD: Prototyping motor interface","2006-03-01","2006-02-28"]
["UN22_00050","Write QA procedure for Motor interface","2006-03-01","2006-03-06"]
["UN22_00060","Prepare Bid Package for Motor interface","2006-03-07","2006-03-10"]
["UN22_00070","Release RFP for Motor interface","2006-03-13","2006-03-13"]
["UN22_00080","Vendor Prepare Proposal for Motor interface","2006-03-14","2006-03-27"]
["UN22_00090","RCV: Proposal  for Motor interface","2006-03-28","2006-03-27"]
["UN22_00100","Evaluate Proposal for Motor interface","2006-03-28","2006-04-03"]
["UN22_00120","AWARD: production motor interface","2006-04-04","2006-04-04"]
["UN22_00130","Receive production motor interface","2006-04-05","2006-05-31"]
["UN22_00140","QA Test motor interface","2006-06-01","2006-06-14"]
["UN22_00155","Specify prototype encoder interface","2006-01-17","2006-01-30"]
["UN22_00160","Procure prototype encoder interface","2006-01-31","2006-01-31"]
["UN22_00170","Receive prototype encoder interface","2006-02-01","2006-02-28"]
["UN22_00180","RCVD:Prototyping encoder interface","2006-03-01","2006-02-28"]
["UN22_00190","Write QA procedure for Encoder interface","2006-03-01","2006-03-06"]
["UN22_00200","Prepare Bid Package for Encoder interface","2006-03-07","2006-03-10"]
["UN22_00210","Release RFP  for Encoder interface","2006-03-13","2006-03-13"]
["UN22_00220","Vendor Prepare Proposal for Encoder interface","2006-03-14","2006-03-27"]
["UN22_00230","RCVD: Proposal  for Encoder interface","2006-03-28","2006-03-27"]
["UN22_00240","Evaluate Proposal for Encoder interface","2006-03-28","2006-04-03"]
["UN22_00260","AWARD: production encoder interface","2006-04-04","2006-04-04"]
["UN22_00270","Receive production encoder interface","2006-04-05","2006-05-31"]
["UN22_00280","QA Test encoder interface","2006-06-01","2006-06-14"]
["UN22_00295","Specify prototype motor driver","2006-01-17","2006-01-23"]
["UN22_00300","Procure prototype motor driver","2006-01-24","2006-01-24"]
["UN22_00310","Receive prototype motor driver","2006-01-25","2006-02-21"]
["UN22_00320","RCVD:Prototyping motor driver","2006-02-22","2006-02-21"]
["UN22_00330","Write QA procedure for motor driver","2006-02-22","2006-02-23"]
["UN22_00340","Prepare Bid Package for motor driver","2006-02-24","2006-03-01"]
["UN22_00350","Release RFP  for motor driver","2006-03-02","2006-03-02"]
["UN22_00360","Vendor Prepare Proposal for motor driver","2006-03-03","2006-03-16"]
["UN22_00370","RCVD: Proposal  for motor driver","2006-03-17","2006-03-16"]
["UN22_00380","Evaluate Proposal for motor driver","2006-03-17","2006-03-23"]
["UN22_00400","AWARD: production motor driver","2006-10-02","2006-10-02"]
["UN22_00410","Receive production motor driver","2006-10-03","2006-10-30"]
["UN22_00420","QA Motor Driver","2006-10-31","2006-11-13"]
["UN22_00430","Design motor drive cables","2006-03-07","2006-03-13"]
["UN22_00440","Design encoder signal cables","2006-03-07","2006-03-13"]
["UN22_00450","Specify cables","2006-03-14","2006-03-17"]
["UN22_00460","Specify connectors","2006-03-14","2006-03-15"]
["UN22_00470","Procure prototype parts","2006-03-20","2006-03-20"]
["UN22_00480","Receive prototype parts","2006-03-21","2006-04-24"]
["UN22_00490","Assemble prototype cables","2006-04-25","2006-05-01"]
["UN22_00500","Test prototype cables","2006-05-02","2006-05-08"]
["UN22_00510","CMPLT: Prototype cables","2006-05-09","2006-05-08"]
["UN22_00520","Specify production cables","2006-05-09","2006-05-22"]
["UN22_00530","Write QA procedure for production cables","2006-05-23","2006-05-24"]
["UN22_00540","Prepare Bid Package for production cables","2006-05-25","2006-06-01"]
["UN22_00550","Release RFP  for production cables","2006-06-02","2006-06-02"]
["UN22_00560","Vendor Prepare Proposal for production cables","2006-06-05","2006-06-16"]
["UN22_00570","RCVD: Proposal  for production cables","2006-06-19","2006-06-16"]
["UN22_00580","Evaluate Proposal for production cables","2006-06-19","2006-06-23"]
["UN22_00600","AWARD: production cables","2006-06-26","2006-06-26"]
["UN22_00610","Receive production cables","2006-06-27","2006-08-08"]
["UN22_00620","QA Test production cables","2006-08-09","2006-08-22"]
["UN22_00630","Write control Software Requirements Spec.","2006-01-31","2006-02-27"]
["UN22_00640","Design control software","2006-02-28","2006-03-27"]
["UN22_00650","Write testing Software Requirements Spec.","2006-03-28","2006-04-24"]
["UN22_00680","Procure commercial software","2006-04-25","2006-04-25"]
["UN22_00700","Write control software","2006-04-26","2006-05-23"]
["UN22_00710","Test control software","2006-05-24","2006-06-07"]
["UN22_00720","CMPLT: Control Software","2006-06-08","2006-06-07"]
["UN22_00760","Design prototype test setup","2006-06-08","2006-06-21"]
["UN22_00770","Prepare for design review","2006-06-22","2006-06-28"]
["UN22_00780","Conduct design review","2006-06-29","2006-07-13"]
["UN22_00790","CMPLT: Design review","2006-07-14","2006-07-13"]
["UN22_00800","Procure integration components for prototype","2006-07-14","2006-07-17"]
["UN22_00810","Receive integration components for prototype","2006-07-18","2006-08-28"]
["UN22_00820","Assemble prototype","2006-08-29","2006-09-12"]
["UN22_00830","CMPLT: Integrated prototype","2006-09-13","2006-09-12"]
["UN22_00840","Write integrated test procedure","2006-09-13","2006-09-19"]
["UN22_00850","Assemble test setup","2006-09-20","2006-09-26"]
["UN22_00860","Perform prototype testing","2006-09-27","2006-10-03"]
["UN22_00870","CMPLT: Integrated prototype testing","2006-10-04","2006-10-03"]
["UN22_00880","Write validation procedure","2006-10-04","2006-10-10"]
["UN22_00890","Design installation layout and plan","2006-10-11","2006-11-07"]
["UN22_00900","Procure production integration components","2006-11-08","2006-11-09"]
["UN22_00910","Receive production integration components","2006-11-10","2007-01-03"]
["UN22_00920","QA Test production integration components","2007-01-04","2007-01-17"]
["UN22_00922","RFI: Production integration components","2007-01-18","2007-01-17"]
["UN22_02865","Procure prototype motor interfaces","2006-02-06","2006-02-06"]
["UN22_02870","Receive prototype motor interfaces","2006-02-07","2006-03-06"]
["UN22_02875","RCVD: Prototyping motor interface","2006-03-07","2006-03-06"]
["UN22_02930","Procure prototype encoder interface","2006-02-06","2006-02-06"]
["UN22_02935","Receive prototype encoder interface","2006-02-07","2006-03-06"]
["UN22_02940","RCVD:Prototyping encoder interface","2006-03-07","2006-03-06"]
["UN22_02995","Procure prototype motor driver","2006-02-06","2006-02-06"]
["UN22_03000","Receive prototype motor driver","2006-02-07","2006-03-06"]
["UN22_03005","RCVD:Prototyping motor driver","2006-03-07","2006-03-06"]
["UN22_03055","Design motor drive cables","2006-03-07","2006-03-13"]
["UN22_03060","Design encoder signal cables","2006-03-07","2006-03-13"]
["UN22_03065","Specify connectors","2006-03-14","2006-03-15"]
["UN22_03070","Specify cables","2006-03-14","2006-03-17"]
["UN22_03075","Procure prototype parts","2006-03-20","2006-03-20"]
["UN22_03080","Receive prototype parts","2006-03-21","2006-04-24"]
["UN22_03085","Assemble prototype cables","2006-04-25","2006-05-01"]
["UN22_03090","Test prototype cables","2006-05-02","2006-05-08"]
["UN22_03095","CMPLT: Prototype cables","2006-05-09","2006-05-08"]
["UN22_03435","Write control software","2005-10-03","2005-11-29"]
["UN22_03590","Perform prototype testing","2005-11-30","2005-12-13"]
["UN22_03600","CMPLT: Integrated prototype testing","2005-12-14","2005-12-13"]
["UN22_03690","Specify prototype motor interface","2005-10-10","2005-10-24"]
["UN22_03700","Procure prototype motor interfaces","2005-10-25","2005-11-22"]
["UN22_03710","Receive prototype motor interfaces","2005-11-23","2005-11-29"]
["UN22_03720","RCV:Prototyping motor interface","2005-11-30","2005-11-29"]
["UN22_03730","Write QA procedure for Motor interface","2006-03-06","2006-03-09"]
["UN22_03740","Prepare Bid Package for motor interface","2006-03-10","2006-03-15"]
["UN22_03750","Release RFP  for motor interface","2006-03-16","2006-03-16"]
["UN22_03760","Vendor Prepare Proposal for motor interface","2006-03-17","2006-03-30"]
["UN22_03770","RCV: Proposal  for motor interface","2006-03-31","2006-03-30"]
["UN22_03780","Evaluate Proposal for motor interface","2006-03-31","2006-04-06"]
["UN22_03800","AWARD: production motor interface","2006-04-07","2006-04-07"]
["UN22_03810","Receive production motor interface","2006-04-10","2006-05-05"]
["UN22_03820","QA Test motor interface","2006-05-08","2006-05-19"]
["UN22_03970","Specify prototype motor driver","2005-10-10","2005-10-17"]
["UN22_03980","Procure prototype motor driver","2005-10-18","2005-11-15"]
["UN22_03990","Receive prototype motor driver","2005-11-16","2005-11-18"]
["UN22_04000","RCV:Prototyping driver","2005-11-21","2005-11-18"]
["UN22_04010","Write QA Procedure for Motor Driver","2005-11-21","2005-11-28"]
["UN22_04020","Prepare Bid Pkg for Driver Interface","2005-11-29","2005-12-02"]
["UN22_04080","Release RFP for production motor driver","2005-12-05","2005-12-16"]
["UN22_04081","Vendor Prepare Proposal for Driver interface","2005-12-19","2006-01-10"]
["UN22_04082","RCV: Proposal  for Driver interface","2006-01-11","2006-01-10"]
["UN22_04083","Evaluate Proposal for Driver Interface","2006-01-11","2006-01-17"]
["UN22_04084","AWARD: production driver interface","2006-01-18","2006-01-18"]
["UN22_04090","Receive production motor driver","2006-01-19","2006-02-15"]
["UN22_04100","QA Motor Driver","2006-02-16","2006-03-01"]
["UN22_04110","Design motor drive cables","2006-01-03","2006-01-09"]
["UN22_04130","Specify cables","2006-01-10","2006-01-13"]
["UN22_04140","Specify connectors","2006-01-10","2006-01-12"]
["UN22_04150","Procure prototype parts","2006-01-16","2006-02-20"]
["UN22_04160","Receive prototype parts","2006-02-21","2006-02-23"]
["UN22_04170","Assemble prototype cables","2006-02-24","2006-03-03"]
["UN22_04180","Test prototype cables","2006-03-06","2006-03-13"]
["UN22_04190","CMPLT: Prototype cables","2006-03-14","2006-03-13"]
["UN22_04200","Specify production cables","2006-03-14","2006-03-27"]
["UN22_04210","Write QA procedure for production cables","2006-03-28","2006-03-30"]
["UN22_04220","Prepare Bid Package for production cables","2006-03-31","2006-04-06"]
["UN22_04230","Release RFP  for production cables","2006-04-07","2006-04-07"]
["UN22_04240","Vendor Prepare Proposal for production cables","2006-04-10","2006-04-21"]
["UN22_04250","RCV: Proposal  for production cables","2006-04-24","2006-04-21"]
["UN22_04260","Evaluate Proposal for production cables","2006-04-24","2006-04-28"]
["UN22_04280","AWARD: production cables","2006-05-01","2006-05-01"]
["UN22_04290","Receive production cables","2006-05-02","2006-06-13"]
["UN22_04300","QA Test production cables","2006-06-14","2006-06-27"]
["UN22_04310","Write control Software Requirements Spec.","2005-10-25","2005-11-08"]
["UN22_04320","Design control software","2005-11-09","2005-12-09"]
["UN22_04380","Write control software","2005-12-12","2006-01-18"]
["UN22_04400","CMPLT: Control Software","2006-01-19","2006-01-18"]
["UN22_04440","Design prototype test setup","2006-01-19","2006-02-01"]
["UN22_04450","Prepare for design review - hardware","2006-02-02","2006-02-08"]
["UN22_04460","Prepare for design review - software","2006-02-09","2006-02-23"]
["UN22_04470","Conduct design review","2006-02-24","2006-02-23"]
["UN22_04480","Procure integration components for prototype","2006-02-24","2006-03-31"]
["UN22_04490","Receive integration components for prototype","2006-04-03","2006-04-06"]
["UN22_04500","Assemble prototype","2006-04-07","2006-04-20"]
["UN22_04510","CMPLT: Integrated prototype","2006-04-21","2006-04-20"]
["UN22_04520","Write integrated test procedure","2006-04-21","2006-04-27"]
["UN22_04530","Assemble test setup","2006-04-28","2006-05-04"]
["UN22_04540","Perform prototype testing","2006-05-05","2006-05-11"]
["UN22_04550","CMPLT: Integrated prototype testing","2006-05-12","2006-05-11"]
["UN22_04560","Write validation procedure","2006-05-12","2006-05-18"]
["UN22_04570","Design installation layout and plan","2006-05-19","2006-06-16"]
["UN22_04580","Procure production integration components","2006-06-19","2006-06-20"]
["UN22_04590","Receive production integration components","2006-06-21","2006-08-02"]
["UN22_04600","QA Test production integration components","2006-08-03","2006-08-16"]
["UN22_J00","Conduct Servo Motor Tests","2005-10-10","2006-01-13"]
["UN22_J35","Procure host for motion test stand","2005-05-02","2005-05-31"]
["UN22_J36","Assemble components","2005-05-02","2005-05-20"]
["UN22_J37","Test stand checkout","2005-10-03","2005-10-07"]
["UN22_J38","Motion test stand complete","2005-10-10","2005-10-07"]
["UN22_J46","Assemble components","2005-05-02","2005-05-06"]
["UN22_J47","Imaging stand checkout","2005-05-02","2005-05-06"]
["UN22_J48","Imaging test stand complete","2005-05-09","2005-05-06"]
["UN23_00115","REQD:  LINAC RFBPM Design","2005-05-02","2005-04-29"]
["UN23_00120","Specify prototype A/D interface","2005-12-22","2006-01-13"]
["UN23_00130","Procure prototype A/D interfaces","2006-01-16","2006-01-16"]
["UN23_00140","Receive prototype A/D interfaces","2006-01-17","2006-02-13"]
["UN23_00150","Assemble prototype","2006-02-14","2006-02-27"]
["UN23_00160","Prototype testing","2006-02-28","2006-03-13"]
["UN23_00170","CMPLT: Prototyping A/D interface","2006-03-14","2006-03-13"]
["UN23_00180","Write QA procedure for A/D interface","2006-03-14","2006-03-17"]
["UN23_00190","Prepare Bid Package for A/D interface","2006-06-09","2006-06-14"]
["UN23_00200","Release RFP  for A/D interface","2006-06-15","2006-06-15"]
["UN23_00210","Vendor Prepare Proposal for A/D interface","2006-06-16","2006-06-29"]
["UN23_00220","RCV: Proposal  for A/D interface","2006-06-30","2006-06-29"]
["UN23_00230","Evaluate Proposal for A/D interface","2006-06-30","2006-07-07"]
["UN23_00250","AWARD: production A/D interface","2006-10-02","2006-10-27"]
["UN23_00260","Receive production A/D interface","2006-10-30","2006-10-31"]
["UN23_00270","QA Test A/D interface","2006-11-01","2006-11-14"]
["UN23_00475","REQD:  LINAC RFBPM Design","2005-05-02","2005-04-29"]
["UN23_00480","Specify cables","2005-12-22","2006-01-06"]
["UN23_00500","Procure prototype parts","2006-01-09","2006-01-09"]
["UN23_00510","Receive prototype parts","2006-01-10","2006-02-06"]
["UN23_00520","Assemble prototype cables","2006-02-07","2006-02-20"]
["UN23_00530","Test prototype cables","2006-02-21","2006-03-06"]
["UN23_00540","CMPLT: Prototype cables","2006-03-07","2006-03-06"]
["UN23_00550","Specify production cables","2006-03-07","2006-03-20"]
["UN23_00560","Write QA procedure for production cables","2006-03-21","2006-03-27"]
["UN23_00570","Prepare Bid Package for production cables","2006-03-28","2006-03-31"]
["UN23_00580","Release RFP  for production cables","2006-04-03","2006-04-03"]
["UN23_00590","Vendor Prepare Proposal for production cables","2006-04-04","2006-04-17"]
["UN23_00600","RCV: Proposal  for production cables","2006-04-18","2006-04-17"]
["UN23_00610","Evaluate Proposal for production cables","2006-04-18","2006-04-24"]
["UN23_00650","Preliminary Cable Design","2005-05-02","2005-05-13"]
["UN23_00655","REQD:  LINAC RFBPM Design","2005-05-02","2005-04-29"]
["UN23_00660","Write control Software Requirements Spec.","2005-11-04","2005-12-05"]
["UN23_00670","Design control software","2005-12-06","2006-01-11"]
["UN23_00680","Write testing Software Requirements Spec.","2006-01-12","2006-02-08"]
["UN23_00690","Design testing software","2006-02-09","2006-02-22"]
["UN23_00700","Specify commercial software required","2006-02-23","2006-03-01"]
["UN23_00710","Procure commercial software","2006-03-02","2006-03-02"]
["UN23_00720","Receive commercial software","2006-03-03","2006-03-30"]
["UN23_00730","Write control software","2006-03-31","2006-05-11"]
["UN23_00740","Test control software","2006-05-12","2006-05-25"]
["UN23_00750","CMPLT: Control Software","2006-05-26","2006-05-25"]
["UN23_00790","Design prototype test setup","2006-05-26","2006-06-02"]
["UN23_00800","Prepare for design review","2006-06-05","2006-06-09"]
["UN23_00820","Conduct design review","2006-06-12","2006-06-13"]
["UN23_00830","Procure integration components for prototype (","2006-06-14","2006-06-14"]
["UN23_00840","Receive integration components for prototype","2006-06-15","2006-07-13"]
["UN23_00850","Assemble prototype","2006-07-14","2006-08-10"]
["UN23_00860","CMPLT: Integrated prototype","2006-08-11","2006-08-10"]
["UN23_00870","Write integrated test procedure","2006-08-11","2006-08-14"]
["UN23_00880","Assemble test setup","2006-08-15","2006-08-16"]
["UN23_00890","Perform prototype testing","2006-08-17","2006-08-18"]
["UN23_00900","CMPLT: Integrated prototype testing","2006-08-21","2006-08-18"]
["UN23_00910","Write validation procedure","2006-08-21","2006-08-25"]
["UN23_00920","Design installation layout and plan","2006-08-28","2006-09-25"]
["UN23_00921","Prepare Bid Pkg for production integration com","2006-09-26","2006-09-29"]
["UN23_00922","Release RFP  for production integration comp","2006-10-02","2006-10-02"]
["UN23_00923","Vendor Prepare Prop for production integrat co","2006-10-03","2006-10-16"]
["UN23_00924","RCV: Proposal  for production integration comp","2006-10-17","2006-10-16"]
["UN23_00925","Evaluate Prop for production integration comp","2006-10-17","2006-10-23"]
["UN23_00930","AWARD: production integration components","2006-10-24","2006-10-24"]
["UN23_00940","Receive production integration components","2006-10-25","2006-11-21"]
["UN23_00950","QA Test production integration components","2006-11-22","2006-12-07"]
["UN23_01285","REQD:  LINAC Toroid Design","2005-05-02","2005-04-29"]
["UN23_01290","Write control Software Requirements Spec.","2005-11-23","2005-12-22"]
["UN23_01300","Design control software","2006-01-03","2006-01-30"]
["UN23_01360","Write control software","2006-11-06","2006-12-19"]
["UN23_01370","Test control software","2006-12-20","2007-01-11"]
["UN23_01380","CMPLT: Control Software","2007-01-12","2007-01-11"]
["UN23_01420","Design prototype test setup","2007-01-12","2007-01-18"]
["UN23_01430","Prepare for design review","2007-01-19","2007-02-01"]
["UN23_01450","Conduct design review","2007-02-02","2007-02-05"]
["UN23_01460","Procure integration components for prototype","2007-02-06","2007-02-06"]
["UN23_01470","Receive integration components for prototype","2007-02-07","2007-03-06"]
["UN23_01480","Assemble prototype","2007-03-07","2007-04-03"]
["UN23_01490","CMPLT: Integrated prototype","2007-04-04","2007-04-03"]
["UN23_01500","Write integrated test procedure","2007-04-04","2007-04-05"]
["UN23_01510","Assemble test setup","2007-04-06","2007-04-09"]
["UN23_01520","Perform prototype testing","2007-04-10","2007-04-11"]
["UN23_01530","CMPLT: Integrated prototype testing","2007-04-12","2007-04-11"]
["UN23_01540","Write validation procedure","2007-04-12","2007-04-18"]
["UN23_01550","Design installation layout and plan","2007-04-19","2007-05-16"]
["UN23_01551","Prepare Bid Package for product integration co","2007-05-17","2007-05-22"]
["UN23_01552","Release RFP  for production integration comp","2007-05-23","2007-05-23"]
["UN23_01553","Vendor Prepare Prop for product integration co","2007-05-24","2007-06-07"]
["UN23_01554","RCV: Proposal  for production integration comp","2007-06-08","2007-06-07"]
["UN23_01555","Evaluate Proposal for product integration comp","2007-06-08","2007-06-14"]
["UN23_01560","AWARD: production integration components","2007-06-15","2007-06-15"]
["UN23_01570","Receive production integration components","2007-06-18","2007-07-16"]
["UN23_01580","QA Test production integration components","2007-07-17","2007-07-30"]
["UN23_02375","REQD:  ULD-SWA Design","2005-05-02","2005-04-29"]
["UN23_02380","Design control software","2005-05-02","2005-05-27"]
["UN23_02440","Write control software","2005-05-31","2005-07-12"]
["UN23_02450","Test control software","2005-07-13","2005-07-26"]
["UN23_02460","CMPLT: Control Software","2005-07-27","2005-07-26"]
["UN23_02500","Design prototype test setup","2005-07-27","2005-08-03"]
["UN23_02510","Prepare for design review","2005-08-04","2005-08-10"]
["UN23_02530","Conduct design review","2005-08-11","2005-08-12"]
["UN23_02540","Procure integration components for prototype (","2005-08-15","2005-08-15"]
["UN23_02550","Receive integration components for prototype","2005-08-16","2005-09-13"]
["UN23_02560","Assemble prototype","2005-09-14","2005-10-11"]
["UN23_02570","CMPLT: Integrated prototype","2005-10-12","2005-10-11"]
["UN23_02580","Write integrated test procedure","2005-10-12","2005-10-14"]
["UN23_02590","Assemble test setup","2005-10-17","2005-10-19"]
["UN23_02600","Perform prototype testing","2005-10-20","2005-10-24"]
["UN23_02610","CMPLT: Integrated prototype testing","2005-10-25","2005-10-24"]
["UN23_23300","Design actuator control","2006-04-11","2006-04-24"]
["UN23_23305","Procure prototype actuator hardware","2006-04-25","2006-05-22"]
["UN23_23310","Build actuator control chassis","2006-05-23","2006-06-06"]
["UN23_23315","Test and debug actuator control","2006-06-07","2006-06-20"]
["UN23_23320","BFW Actuator Complete","2006-06-21","2006-06-20"]
["UN24_00050","Prototype testing","2005-05-09","2005-05-20"]
["UN24_00060","CMPLT: Prototyping Camera","2005-05-23","2005-05-20"]
["UN24_00070","Write QA procedure for Camera","2005-05-23","2005-05-27"]
["UN24_00210","Prototype testing Camera Interface","2005-10-03","2005-10-14"]
["UN24_00220","CMPLT: Prototyping Camera interface","2005-10-17","2005-10-14"]
["UN24_00230","Write QA procedure for Camera interface","2006-08-28","2006-09-01"]
["UN24_00370","Prototype testing","2005-05-09","2005-05-20"]
["UN24_00380","CMPLT: Prototyping Digitizer","2005-05-23","2005-05-20"]
["UN24_00390","Write QA procedure for Digitizer","2005-05-23","2005-05-27"]
["UN24_00660","Design video feed cables","2005-11-01","2005-11-07"]
["UN24_00670","Design timing signal cables","2005-11-01","2005-11-07"]
["UN24_00680","Specify cables","2005-11-08","2005-11-14"]
["UN24_00700","Procure prototype parts","2005-11-15","2005-11-15"]
["UN24_00710","Receive prototype parts","2005-11-16","2005-12-15"]
["UN24_00720","Assemble prototype cables","2005-12-16","2005-12-22"]
["UN24_00730","Test prototype cables","2006-01-03","2006-01-16"]
["UN24_00740","CMPLT: Prototype cables","2006-01-17","2006-01-16"]
["UN24_00860","Write control Software Requirements Spec.","2005-10-03","2006-01-13"]
["UN24_00870","Design control software","2006-01-16","2006-02-10"]
["UN24_00930","Write control software","2006-02-13","2006-03-24"]
["UN24_00940","Test control software","2006-03-27","2006-04-07"]
["UN24_00950","CMPLT: Control Software","2006-04-10","2006-04-07"]
["UN24_00960","RCV: OTR imaging requirements","2006-04-10","2006-04-07"]
["UN24_00970","Design analysis software","2006-04-10","2006-05-05"]
["UN24_00980","Test Analysis software","2006-05-08","2006-05-19"]
["UN24_00985","CMPLT : OTR Analysis software","2006-05-22","2006-05-19"]
["UN24_00990","Design prototype test setup","2006-05-22","2006-05-26"]
["UN24_01000","Prepare for design review","2006-05-30","2006-06-05"]
["UN24_01020","Conduct design review","2006-06-06","2006-06-12"]
["UN24_01030","Procure integration components for prototype (","2006-06-13","2006-06-13"]
["UN24_01040","Receive integration components for prototype","2006-06-14","2006-07-12"]
["UN24_01050","Assemble prototype","2006-07-13","2006-07-26"]
["UN24_01060","CMPLT: Integrated prototype","2006-07-27","2006-07-26"]
["UN24_01070","Write integrated test procedure","2006-07-27","2006-08-01"]
["UN24_01080","Assemble test setup","2006-08-02","2006-08-08"]
["UN24_01090","Perform prototype testing","2006-08-09","2006-08-15"]
["UN24_01100","CMPLT: Integrated prototype testing","2006-08-16","2006-08-15"]
["UN25_00010","Write control Software Requirements Spec","2005-10-03","2005-10-14"]
["UN25_00020","Design control software","2005-10-17","2005-10-28"]
["UN25_00080","Write control software","2005-10-31","2006-01-13"]
["UN25_00090","Test control software","2006-01-16","2006-01-20"]
["UN25_00100","CMPLT: Control Software","2006-01-23","2006-01-20"]
["UN25_00140","Design prototype test setup","2006-01-23","2006-01-27"]
["UN25_00150","Prepare for design review","2006-01-30","2006-02-03"]
["UN25_00160","Conduct design review","2006-02-06","2006-02-07"]
["UN25_00161","CMPLT: Design Review","2006-02-08","2006-02-07"]
["UN25_00170","Procure integration components for prototype (","2006-02-08","2006-02-08"]
["UN25_00180","Receive integration components for prototype","2006-02-09","2006-03-08"]
["UN25_00190","Assemble prototype","2006-03-09","2006-03-22"]
["UN25_00200","CMPLT: Integrated prototype","2006-03-23","2006-03-22"]
["UN25_00210","Write integrated test procedure","2006-03-23","2006-03-24"]
["UN25_00220","Assemble test setup","2006-03-27","2006-03-28"]
["UN25_00230","Perform prototype testing","2006-03-29","2006-03-30"]
["UN25_00240","CMPLT: Integrated prototype testing","2006-03-31","2006-03-30"]
["UN25_00250","Write validation procedure","2006-03-31","2006-04-06"]
["UN25_00260","Design installation layout and plan","2006-04-07","2006-05-04"]
["UN25_00261","Prepare Bid Package for product integrated com","2006-05-05","2006-05-11"]
["UN25_00262","Release RFP  for production integrated comp","2006-05-12","2006-05-12"]
["UN25_00263","Vendor Prepare Prop for product integrated com","2006-05-15","2006-05-19"]
["UN25_00264","RCV: Proposal  for product integrated comp","2006-05-22","2006-05-19"]
["UN25_00265","Evaluate Proposal for product integrated comp","2006-05-22","2006-05-26"]
["UN25_00270","AWARD production integration components","2006-05-30","2006-05-30"]
["UN25_00280","Receive production integration components","2006-05-31","2006-06-27"]
["UN25_00290","QA Test production integration components","2007-05-04","2007-05-17"]
["UN26_00010","Write control Software Requirements Spec.","2006-06-19","2006-06-30"]
["UN26_00020","Design control software","2006-07-03","2006-07-17"]
["UN26_00080","Write control software","2006-07-18","2006-07-31"]
["UN26_00090","Test control software","2006-08-01","2006-08-07"]
["UN26_00100","CMPLT:  Control Software","2006-08-08","2006-08-07"]
["UN26_00140","Design prototype test setup","2006-08-08","2006-08-14"]
["UN26_00160","Prepare for design review","2006-08-15","2006-08-21"]
["UN26_00170","Conduct design review","2006-08-22","2006-08-23"]
["UN26_00171","CMPLT: Design Review","2006-08-24","2006-08-23"]
["UN26_00180","Procure integration components for prototype (","2006-08-24","2006-08-24"]
["UN26_00190","Receive integration components for prototype","2006-08-25","2006-10-06"]
["UN26_00200","Assemble prototype","2006-10-09","2006-10-20"]
["UN26_00210","CMPLT: Integrated prototype","2006-10-23","2006-10-20"]
["UN26_00220","Write integrated test procedure","2006-10-23","2006-10-24"]
["UN26_00230","Assemble test setup","2006-10-25","2006-10-26"]
["UN26_00240","Perform prototype testing","2006-10-27","2006-10-30"]
["UN26_00250","CMPLT: Integrated prototype testing","2006-10-31","2006-10-30"]
["UN26_00260","Write validation procedure","2006-10-31","2006-11-06"]
["UN26_00270","Design installation layout and plan","2006-11-07","2006-12-06"]
["UN26_00271","Prepare Bid Package for product integration co","2006-12-07","2006-12-13"]
["UN26_00272","Release RFP  for production integration comp","2006-12-14","2006-12-14"]
["UN26_00273","Vendor Prepare Prop for product integration co","2006-12-15","2006-12-21"]
["UN26_00274","RCV: Proposal  for product integration comp","2007-01-02","2006-12-21"]
["UN26_00275","Evaluate Proposal for product integration comp","2007-01-02","2007-01-08"]
["UN26_00280","AWARD:  production integration components","2007-01-09","2007-01-09"]
["UN26_00290","Receive production integration components","2007-01-10","2007-02-06"]
["UN26_00300","QA Test production integration components","2007-02-07","2007-02-20"]
["UN26_01000","Write control Software Requirements Spec.","2006-06-27","2006-07-11"]
["UN26_01010","Design control software","2006-07-12","2006-07-25"]
["UN26_01070","Write control software","2006-07-26","2006-08-08"]
["UN26_01080","Test control software","2006-08-09","2006-08-15"]
["UN26_01090","CMPLT: Control Software","2006-08-16","2006-08-15"]
["UN26_01150","Prepare for design review","2006-08-16","2006-08-22"]
["UN26_01160","Conduct design review","2006-08-23","2006-08-24"]
["UN26_01280","Receive production integration components","2006-08-25","2006-09-15"]
["UN26_01290","QA Test production integration components","2006-09-18","2006-09-29"]
["UN27_00010","Undulator global MPS module design","2006-10-02","2006-10-27"]
["UN27_00011","Prepare for design review","2006-10-30","2006-11-03"]
["UN27_00020","conduct design review","2006-11-06","2006-11-07"]
["UN27_00030","Procure prototype MPS hardware components","2006-11-08","2006-11-08"]
["UN27_00031","Receive Prototype MPS Hardware Components","2006-11-09","2006-12-15"]
["UN27_00040","Assemble prototype MPS hardware","2006-12-18","2007-01-09"]
["UN27_00050","Test prototype MPS hardware","2007-01-10","2007-01-15"]
["UN27_00060","CMPLT: MPS hardware","2007-01-16","2007-01-15"]
["UN27_00070","Specify production MPS hardware","2007-01-16","2007-01-22"]
["UN27_00080","Write QA procedure for production MPS hardware","2007-01-23","2007-01-29"]
["UN27_00090","Procure production MPS hardware","2007-01-30","2007-01-30"]
["UN27_00092","Procure Spare MPS Hardware","2007-01-30","2007-01-30"]
["UN27_00100","Receive production and spare MPS hardware","2007-01-31","2007-02-15"]
["UN27_00110","QA Test production MPS hardware","2007-02-16","2007-03-01"]
["UN27_00120","Design interface electronics","2006-10-30","2006-11-10"]
["UN27_00121","Prepare for design review","2006-11-13","2006-11-17"]
["UN27_00130","conduct design review","2006-11-20","2006-11-21"]
["UN27_00140","Procure prototype Interface electronics compon","2006-11-22","2006-11-22"]
["UN27_00141","Receive Prototype Interface Electronics","2006-11-27","2007-01-09"]
["UN27_00150","Assemble prototype Interface electronics","2007-01-10","2007-01-23"]
["UN27_00160","Test prototype Interface electronics","2007-01-24","2007-01-29"]
["UN27_00170","CMPTL: Interface electronics","2007-01-30","2007-01-29"]
["UN27_00180","Specify production Interface electronics","2007-01-30","2007-02-05"]
["UN27_00190","Write QA procedure for production Interface el","2007-02-06","2007-02-06"]
["UN27_00200","Procure production Interface electronics","2007-02-07","2007-02-07"]
["UN27_00210","Receive production Interface electronics","2007-02-08","2007-02-21"]
["UN27_00220","QA Test production Interface electronics","2007-02-22","2007-03-07"]
["UN27_00230","Design signal interface","2006-10-02","2006-10-13"]
["UN27_00231","Prepare for design review","2006-10-16","2006-10-20"]
["UN27_00240","conduct design review","2006-10-23","2006-10-24"]
["UN27_00250","Procure prototype signal electronics component","2006-10-25","2006-10-25"]
["UN27_00251","Receive Prototype Signal Electronics","2006-10-26","2006-12-01"]
["UN27_00260","Assemble prototype signal electronics","2006-12-04","2006-12-05"]
["UN27_00270","Test prototype signal electronics","2006-12-06","2006-12-11"]
["UN27_00280","CMPTL: signal electronics","2006-12-12","2006-12-11"]
["UN27_00290","Specify production signal electronics","2006-12-12","2006-12-13"]
["UN27_00300","Write QA procedure for production signal elect","2006-12-14","2006-12-15"]
["UN27_00310","AWARD: production signal electronics","2006-12-18","2006-12-18"]
["UN27_00312","AWARD:  spare signal electronics","2007-01-02","2007-01-02"]
["UN27_00320","Receive production and spare signal electronic","2006-12-19","2007-01-10"]
["UN27_00321","REC: production signal electronics","2007-01-11","2007-01-11"]
["UN27_00324","REC: spare signal electronics","2007-01-11","2007-01-11"]
["UN27_00330","QA Test production and spare signal electronic","2007-01-12","2007-01-25"]
["UN27_00340","Design signal interface","2006-10-02","2006-10-13"]
["UN27_00341","Prepare for design review","2006-10-16","2006-10-20"]
["UN27_00350","conduct design review","2006-10-23","2006-10-24"]
["UN27_00360","Procure prototype signal electronics component","2006-10-25","2006-10-25"]
["UN27_00361","Receive Prototype Signal Electronics Component","2006-10-26","2006-12-01"]
["UN27_00370","Assemble prototype signal electronics","2006-12-04","2006-12-05"]
["UN27_00380","Test prototype signal electronics","2006-12-06","2006-12-11"]
["UN27_00390","CMPLT: signal electronics","2006-12-12","2006-12-11"]
["UN27_00400","Specify production signal electronics","2006-12-12","2006-12-13"]
["UN27_00410","Write QA procedure for production signal elect","2006-12-14","2006-12-15"]
["UN27_00420","Procure production signal electronics","2006-12-18","2006-12-18"]
["UN27_00430","Receive production signal electronics","2006-12-19","2007-01-10"]
["UN27_00440","QA Test production signal electronics","2007-01-11","2007-01-24"]
["UN27_00450","Design Power Supply Control","2006-04-28","2006-08-17"]
["UN27_00460","COMP: Power Supply Controls Design","2006-08-18","2006-08-17"]
["UN27_00470","Build H/W and Write Docmtn Power Supply Control","2006-08-18","2006-09-25"]
["UN27_00480","Write S/W Docmtn Power Supply Control","2006-08-18","2006-09-25"]
["UN27_00490","Integrate software & hardware","2006-09-26","2006-10-02"]
["UN27_00500","AVAIL: Power Supply Cntrls Ready for Install","2006-10-03","2006-10-02"]
["UN27_00532","Procure spare signal electronics","2007-01-03","2007-01-03"]
["UN30_28440","All Undulator Magnets Ready for Installation","2008-01-24","2008-01-23"]
["UN31_00010","Undulator Systems Integration","2005-10-03","2007-02-21",null,"2005-10-03"]
["UN31_00040","Dev/Coord Instl/Checkout/Verif/Interface,etc","2006-05-22","2007-05-08"]
["UN33_00310","Prototype Supt/Mover System w/Final Rqmts","2005-12-08","2006-02-14"]
["UN33_00324","Single Undulator Module Tested-Short Term","2006-04-10","2006-04-07"]
["UN33_00530","Mag Measure & Tune-Hi-Tech Article 01 (1st Art)","2006-03-30","2006-04-27"]
["UN33_00540","COMP:  Magnetic Meas. & Tune Hi-Tech Article 01","2006-04-28","2006-04-27"]
["UN33_00545","Carry Out Longer Term Stability Single Und Test","2006-04-10","2006-06-07"]
["UN33_00548","Disassemble and Pack","2006-06-08","2006-06-14"]
["UN33_00549","Design/fab undulator magnetic shield","2005-10-03","2005-10-21"]
["UN33_00550","ACCEPT Hi-Tech Und Article 01 (1st Art) at ANL","2006-04-28","2006-05-04"]
["UN33_00551","Test/measure undulator magnetic shield","2005-10-24","2005-10-28"]
["UN33_00552","Ship Hi-Tech Und Article 01 (1st Art) to SLAC","2006-05-12","2006-05-18"]
["UN33_00553","Disassemble/pack Undulator Hi-Tech Article 01","2006-05-05","2006-05-11"]
["UN33_00554","ACCEPT: Hi-Tech Und Article 01 (1st Art) at SLAC","2006-05-19","2006-05-18"]
["UN33_00556","Hi-Tech Undulator Article 01 Ready for MMF","2006-05-19","2006-05-18"]
["UN33_00560","Mag Measure & Tune-Metalex Article 02 (1st Art)","2006-04-28","2006-05-26"]
["UN33_00565","Develop Plan & Base Design for Single Und Test","2005-09-01","2005-10-14"]
["UN33_00566","AVAIL: Vacuum SUT Components","2006-03-03","2006-03-02"]
["UN33_00567","AVAIL:  Diagnostics SUT Components","2006-03-13","2006-03-10"]
["UN33_00568","Construct model UN for support/mover sys testing","2005-10-03","2005-11-30"]
["UN33_00570","COMP:  Magnetic Meas. & Tune Metalex Article 02","2006-05-30","2006-05-26"]
["UN33_00575","Assemble Test/Meas/Verification Stand","2005-11-04","2006-02-13"]
["UN33_00580","ACCEPT: Metalex Und Article 02 (1st Art) at ANL","2006-05-30","2006-06-05"]
["UN33_00585","Prepare Area for Single Undulator Test","2005-09-16","2005-10-28"]
["UN33_00595","Prepare Ctrls HW/SW for Single Und Test","2005-09-16","2005-11-14"]
["UN33_00605","Carry out Short-Term Single Undulator Test","2006-03-27","2006-04-07"]
["UN33_00610","Ship Metalex Und Article 02 (1st Art) to SLAC","2006-06-13","2006-06-19"]
["UN33_00612","Disassemble/pack Undulator Metalex Article 02","2006-06-06","2006-06-12"]
["UN33_00615","Assemble Module Components on Stand/Connect","2006-03-13","2006-03-24"]
["UN33_00620","ACCEPT: Metalex Und Article 02 (1st Art) at SL","2006-06-20","2006-06-19"]
["UN33_00625","Single Undulator Module Tested - Long Term","2006-06-08","2006-06-07"]
["UN33_00630","Metalex Und Article 02 Ready for MMF","2006-06-20","2006-06-19"]
["UN33_00635","Write Report: Short Term Test Results","2006-04-10","2006-04-21"]
["UN33_00665","Mount Proto Und on PR S/M","2006-02-15","2006-02-17"]
["UN33_10060","AWARD: Contract Ti -Strongback","2005-04-08","2005-04-08",null,"2005-04-08","2005-04-08"]
["UN33_10065","Vendor  Procure All Ti Forgings","2006-07-03","2006-06-30"]
["UN33_10119","Acceptance Measmt & Verification of Strongbacks","2005-06-01","2005-06-30",null,"2005-06-01","2005-06-30"]
["UN33_10165","25% Ti Strongbacks received","2006-04-13","2006-04-12"]
["UN33_10265","50% Ti Strongbacks received","2006-09-12","2006-09-11"]
["UN33_10365","75% Ti Strongbacks received","2007-02-19","2007-02-16"]
["UN33_10500","Ti Strongback Delivery 100% Complete","2007-04-18","2007-04-17"]
["UN33_1A120","Acceptance Measmt & Verification of Strongbacks","2005-07-01","2005-09-21",null,"2005-07-01"]
["UN33_20055","Evaluate Proposal - Magnet Blocks","2005-05-09","2005-05-13",null,"2005-05-09","2005-05-13"]
["UN33_20060","AWARD: Contract - Magnet Blocks","2005-05-16","2005-05-16",null,"2005-05-16","2005-05-16"]
["UN33_20070","Vendor Fab/Assy - 1st 5% Magnet Blocks","2005-05-17","2005-06-16",null,"2005-05-17","2005-06-16"]
["UN33_20071","Vendor Fab/Assy - 1st 5% Magnet Blocks","2005-06-17","2005-11-01",null,"2005-06-17"]
["UN33_20080","RCV: From Vendor - 1st 5% Magnet Blocks","2006-01-03","2006-01-03"]
["UN33_20090","Vendor Fab/Assy - Remainder of Magnet Blocks","2006-01-04","2006-08-24"]
["UN33_20101","RCV: From Vendor 2nd 5% Magnet Blocks","2006-02-01","2006-02-01"]
["UN33_20102","RCV: From Vendor 12.5% Magnet Blocks","2006-03-01","2006-03-01"]
["UN33_20103","RCV: From Vendor 12.92% Magnet Blocks","2006-04-03","2006-04-03"]
["UN33_20104","RCV: From Vendor 12.91% Magnet Blocks","2006-05-01","2006-05-01"]
["UN33_20106","RCV: From Vendor 12.92% Magnet Blocks","2006-06-01","2006-06-01"]
["UN33_20107","RCV: From Vendor 12.92% Magnet Blocks","2006-07-03","2006-07-03"]
["UN33_20108","RCV: From Vendor 10.34% Magnet Blocks","2006-08-01","2006-08-01"]
["UN33_20109","RCV: From Vendor 18.09% Magnet Blocks","2006-09-01","2006-09-01"]
["UN33_20120","100% magnet blocks received","2006-09-05","2006-09-01"]
["UN33_30060","AWARD: Contract - Magnet Poles","2005-03-15","2005-03-15",null,"2005-03-15","2005-03-15"]
["UN33_30070","Vendor Fab/Assy - Magnet Poles (1-2)","2005-05-02","2005-11-01",null,"2005-05-02"]
["UN33_30075","PP: Raw Material","2005-06-01","2005-06-01",null,"2005-06-01","2005-06-01"]
["UN33_30076","PP: Progress payment - 15 weeks","2005-12-01","2005-12-01"]
["UN33_30077","PP: Progress Payment - 21 Weeks","2005-12-01","2005-12-01"]
["UN33_30078","PP: Progress Payment - 31 Weeks","2006-01-31","2006-01-31"]
["UN33_30079","PP: Progress Payment - 41 Weeks","2006-02-14","2006-02-14"]
["UN33_30080","RCV: From Vendor - Magnet Poles (1-2)","2005-11-02","2005-11-01"]
["UN33_30081","PP: Progress Payment - 51 Weeks","2006-04-03","2006-04-03"]
["UN33_30082","Vendor Fab/Assy - 2nd Lot Magnet Poles (3-12)","2006-01-09","2006-02-17"]
["UN33_30086","RCV: From Vendor - 2nd Lot Magnet Poles (3-12)","2006-02-20","2006-02-17"]
["UN33_30087","Vendor Fab/Assy - 3rd Lot Magnet Poles (13-24)","2006-02-20","2006-04-27"]
["UN33_30088","RCV: From Vendor - 3rd Lot Magnet Poles (13-24)","2006-04-28","2006-04-27"]
["UN33_30090","Vendor Fab/Assy - 4th Lot Magnet Poles (25-36)","2006-04-28","2006-06-20"]
["UN33_30095","Vendor Fab/Assy - 5th Lot Magnet Poles (37-40)","2006-06-21","2006-09-06"]
["UN33_30096","50% magnet poles received","2006-02-20","2006-02-17"]
["UN33_30100","RCV: From Vendor - 4th Lot Magnet Poles (25-36)","2006-09-07","2006-09-06"]
["UN33_30120","100% magnet poles received","2006-09-07","2006-09-06"]
["UN33_40010","Prep Bid Package - Magnet Assembly","2005-05-09","2005-05-20"]
["UN33_40020","Release RFP - Magnet Assembly","2005-06-28","2005-06-28",null,"2005-06-28","2005-06-28"]
["UN33_40030","Vendor Prep Proposal - Magnet Assembly","2005-06-29","2005-08-01",null,"2005-06-29"]
["UN33_40040","RCV: Proposals - Magnet Assembly","2005-08-02","2005-08-01"]
["UN33_40050","Evaluate Proposals - Magnet Assembly","2005-08-02","2005-09-30",null,"2005-08-02","2005-09-30"]
["UN33_40055","Contract Prep ANL Procurement - Magnet Assembly","2005-09-01","2005-05-13",null,"2005-09-01"]
["UN33_40056","Survey  & Align","2005-10-03","2007-10-31"]
["UN33_40060","AWARD: 1st Art Mag Assy - Hi-Tech","2005-10-25","2005-10-25"]
["UN33_40070","Hi-Tech Prep Fab/Assy, QA, VE Plans","2005-10-26","2005-11-04"]
["UN33_40080","RCV: Hi-Tech Fab/Assy Plan","2005-11-07","2005-11-04"]
["UN33_40090","Evaluate Hi-Tech Fab/Assy Plan","2005-11-07","2005-11-08"]
["UN33_40092","Feedback and Comments to Hi-Tech","2005-11-09","2005-11-09"]
["UN33_40094","Approve Hi-Tech VE and QA Plans","2005-11-10","2005-11-09"]
["UN33_40096","Permission to start First Article - Hi-Tech","2005-11-10","2005-11-09"]
["UN33_40100","Hi-Tech Procure - 1st Art Mag Assy Parts","2005-11-10","2006-01-19"]
["UN33_40110","RCV: Ti S/B Article 01, Blocks, Poles, Parts","2006-01-04","2006-01-03"]
["UN33_40120","Hi-Tech Fab/Assy-Magnet Article 01 Assembly","2006-01-20","2006-03-20"]
["UN33_40122","Review Hi-Tech travelers/data","2006-03-21","2006-03-22"]
["UN33_40124","Factory Acceptance Article 01 - Hi-Tech","2006-03-23","2006-03-24"]
["UN33_40126","Permission to Ship to ANL Article 01 - Hi-Tech","2006-03-27","2006-03-27"]
["UN33_40128","Hi-Tech Undulator Article 01 Ship to ANL","2006-03-28","2006-03-28"]
["UN33_40140","RCV: From Hi-Tech-1st Article Magnet Assy","2006-03-29","2006-03-29"]
["UN33_40150","AWARD: 1st Art Mag Assy - Metalex","2005-10-26","2005-10-26"]
["UN33_40160","Metalex Prep Fab/Assy, QA, VE Plans","2005-10-27","2005-11-09"]
["UN33_40170","RCV: Metalex Fab/Assy Plan","2005-11-10","2005-11-09"]
["UN33_40180","Evaluate Metalex Fab/Assy Plan","2005-11-10","2005-11-11"]
["UN33_40182","Feedback and Comments to Metalex","2005-11-14","2005-11-14"]
["UN33_40184","Approve Metalex VE and QA Plans","2005-11-15","2005-11-14"]
["UN33_40186","Permission to start First Article - Metalex","2005-11-15","2005-11-14"]
["UN33_40190","Metalex Procure - 1st Art Mag Assy Parts","2005-11-15","2006-01-24"]
["UN33_40200","RCV: Ti S/B Article 02, Blocks, Poles, Parts","2006-01-04","2006-01-03"]
["UN33_40210","Metalex Fab/Assy-Magnet Article 02 Assembly","2006-01-25","2006-03-23"]
["UN33_40211","Review Metalex travelers/data","2006-03-24","2006-03-27"]
["UN33_40212","Factory Acceptance Article 02 - Metalex","2006-03-28","2006-03-29"]
["UN33_40213","Permission to Ship to ANL Article 02 - Metalex","2006-03-30","2006-03-30"]
["UN33_40214","Metalex Undulator Article 02 Ship to ANL","2006-03-31","2006-04-06"]
["UN33_40220","RCV: From Metalex - Magnet Assembly","2006-04-07","2006-04-07"]
["UN33_40230","1st Art. Hi-Tech Undulator Article 01 received","2006-03-30","2006-03-29"]
["UN33_40240","1st Article Metalex Undulator Article 02 recd","2006-04-10","2006-04-07"]
["UN33_40245","All Break Section Interf to UM & Girder Defined","2005-07-01","2005-06-30"]
["UN33_40250","Interface to Fixed Supt Documented & Signed Off","2005-07-01","2005-06-30"]
["UN33_40256","Design Support/Mover System","2005-07-01","2005-10-24",null,"2005-07-01"]
["UN33_40265","Prototype Support/Mover System w/Final Reqmts","2006-02-15","2006-02-14"]
["UN33_40274","Prep for FDR - Supt/Mover System, Incl Ctrls Pkg","2006-02-15","2006-02-21"]
["UN33_40275","FDR - Supt/Mover System, Incl Controls Package","2006-04-24","2006-04-24"]
["UN33_40280","COMP: Prequalify Vendors Support/Mover System","2006-01-03","2005-12-22"]
["UN33_40285","Release RFP -  Support/Mover System","2006-04-25","2006-04-24"]
["UN33_40290","Vendor Prep Bids -  Support/Mover System","2006-04-25","2006-05-23"]
["UN33_40291","Produce SOW -  Support/Mover System","2005-12-07","2006-01-13"]
["UN33_40292","Select Components and Vendors for SM System","2005-09-01","2005-12-22"]
["UN33_40293","Prep Bid Package -  Support/Mover System","2006-01-16","2006-01-27"]
["UN33_40295","Bids Received -  Support/Mover System","2006-05-24","2006-05-23"]
["UN33_40300","Evaluate Bids -  Support/Mover System","2006-05-24","2006-05-31"]
["UN33_40305","AWARD: Support/Mover System 1st Articles","2006-06-01","2006-06-01"]
["UN33_40310","Vendor Prep & Documentation-Support/Mover System","2006-06-02","2006-06-16"]
["UN33_40315","Construction 1st Two Articles - Suppt/Mover Sys","2006-06-19","2006-10-16"]
["UN33_40320","Factory Accept Testing -  Support/Mover System","2006-10-17","2006-10-23"]
["UN33_40321","Ship 1st 2 Articles Support/Mover System to ANL","2006-10-24","2006-10-30"]
["UN33_40322","1st 2 Articles Support/Mover System recd. at ANL","2006-10-31","2006-10-30"]
["UN33_4P019","Pre-Qualify Vendors - Magnet Assembly","2005-05-02","2005-05-31"]
["UN33_4P020","Prepare for Acceptance Measurements","2005-06-01","2006-02-22",null,"2005-06-01"]
["UN33_D0405","Get Quote on Ion Pump","2005-09-01","2005-09-08",null,"2005-09-01","2005-09-08"]
["UN33_DL011","PP: 6 Raws - Dial","2005-07-20","2005-07-20",null,"2005-07-20","2005-07-20"]
["UN33_DL017","Dial-Fab/Assy - Ti Strongback Article 01","2005-10-11","2005-11-21"]
["UN33_DL020","RCV: Ti S/B Article 01 - Dial","2005-11-22","2005-11-22"]
["UN33_DL021","ACCEPT: Factory Acceptance - Ti S/B Article 01","2005-11-23","2005-11-23"]
["UN33_DL022","Vendor Ship  - Ti S/B Article 01","2005-11-28","2005-12-02"]
["UN33_DL023","AVAIL: Ti Strongback Article 01","2005-12-05","2005-12-02"]
["UN33_DL024","ACCEPT: Site acceptance @ Dial - Ti S/B 01","2005-12-05","2005-12-05"]
["UN33_DL025","Permission to proceed with Ti Production-Dial","2005-11-28","2005-11-23"]
["UN33_DL026","Dial - Fab/Assy - Ti Strongback Article 03","2005-11-28","2006-01-04"]
["UN33_DL027","RCV: Ti S/B Article 03 - Dial","2006-01-05","2006-01-05"]
["UN33_DL028","ACCEPT: Factory Acceptance - Ti S/B Article 03","2006-01-06","2006-01-06"]
["UN33_DL029","Vendor Ship - Ti S/B Article 03","2006-01-09","2006-01-13"]
["UN33_DL030","AVAIL: Ti Strongback Article 03","2006-01-16","2006-01-13"]
["UN33_DL031","Dial-Fab/Assy - Ti Strongback Article 05","2006-01-05","2006-02-02"]
["UN33_DL032","RCV: Ti S/B Article 05 - Dial","2006-02-03","2006-02-03"]
["UN33_DL033","ACCEPT: Factory Acceptance - Ti S/B Article 05","2006-02-06","2006-02-06"]
["UN33_DL034","Vendor Ship - Ti S/B Article 05","2006-02-07","2006-02-13"]
["UN33_DL035","AVAIL: Ti Strongback Article 05","2006-02-14","2006-02-13"]
["UN33_DL036","Dial-Fab/Assy - Ti Strongback Article 07","2006-02-03","2006-03-03"]
["UN33_DL037","RCV: Ti S/B Article 07 - Dial","2006-03-06","2006-03-06"]
["UN33_DL038","ACCEPT: Factory Acceptance - Ti S/B Article 07","2006-03-07","2006-03-07"]
["UN33_DL039","Vendor Ship - Ti S/B Article 07","2006-03-08","2006-03-14"]
["UN33_DL040","AVAIL: Ti Strongback Article 07","2006-03-15","2006-03-14"]
["UN33_DL041","Dial - Fab/Assy - Ti Strongback Article 09","2006-03-06","2006-04-03"]
["UN33_DL042","RCV: Ti S/B Article 09 - Dial","2006-04-04","2006-04-04"]
["UN33_DL043","ACCEPT: Factory Acceptance - Ti S/B Article 09","2006-04-05","2006-04-05"]
["UN33_DL044","Vendor Ship - Ti S/B Article 09","2006-04-06","2006-04-12"]
["UN33_DL045","AVAIL: Ti Strongback Article 09","2006-04-13","2006-04-12"]
["UN33_DL046","Dial- Fab/Assy - Ti Strongback Article 11","2006-04-04","2006-05-02"]
["UN33_DL047","RCV: Ti S/B Article 11 - Dial","2006-05-03","2006-05-03"]
["UN33_DL048","ACCEPT: Factory Acceptance - Ti S/B Article 11","2006-05-04","2006-05-04"]
["UN33_DL049","Vendor Ship - Ti S/B Article 11","2006-05-05","2006-05-11"]
["UN33_DL050","AVAIL: Ti Strongback Article 11","2006-05-12","2006-05-11"]
["UN33_DL051","Dial - Fab/Assy - Ti Strongback Article 13","2006-05-03","2006-06-01"]
["UN33_DL052","RCV: Ti S/B Article 13 - Dial","2006-06-02","2006-06-02"]
["UN33_DL053","ACCEPT: Factory Acceptance - Ti S/B Article 13","2006-06-05","2006-06-05"]
["UN33_DL054","Vendor Ship - Ti S/B Article 13","2006-06-06","2006-06-12"]
["UN33_DL055","AVAIL: Ti Strongback Article 13","2006-06-13","2006-06-12"]
["UN33_DL056","Dial - Fab/Assy - Ti Strongback Article 15","2006-06-02","2006-06-30"]
["UN33_DL057","RCV: Ti S/B Article 15 - Dial","2006-07-03","2006-07-03"]
["UN33_DL058","ACCEPT: Factory Acceptance - Ti S/B Article 15","2006-07-05","2006-07-05"]
["UN33_DL059","Vendor Ship - Ti S/B Article 15","2006-07-06","2006-07-12"]
["UN33_DL060","AVAIL: Ti Strongback Article 15","2006-07-13","2006-07-12"]
["UN33_DL061","Dial - Fab/Assy - Ti Strongback Article 17","2006-07-03","2006-08-01"]
["UN33_DL062","RCV: Ti S/B Article 17 - Dial","2006-08-02","2006-08-02"]
["UN33_DL063","ACCEPT: Factory Acceptance - Ti S/B Article 17","2006-08-03","2006-08-03"]
["UN33_DL065","AVAIL: Ti Strongback Article 17","2006-08-11","2006-08-10"]
["UN33_DL066","Dial - Fab/Assy - Ti Strongback Article 19","2006-08-02","2006-08-30"]
["UN33_DL067","RCV: Ti S/B Article 19 - Dial","2006-08-31","2006-08-31"]
["UN33_DL068","ACCEPT: Factory Acceptance - Ti S/B Article 19","2006-09-01","2006-09-01"]
["UN33_DL069","Vendor Ship - Ti S/B Article 19","2006-09-05","2006-09-11"]
["UN33_DL070","AVAIL: Ti Strongback Article 19","2006-09-12","2006-09-11"]
["UN33_DL071","Dial - Fab/Assy - Ti Strongback Article 21","2006-08-31","2006-09-29"]
["UN33_DL072","RCV: Ti S/B Article 21 - Dial","2006-10-02","2006-10-02"]
["UN33_DL073","ACCEPT: Factory Acceptance - Ti S/B Article 21","2006-10-03","2006-10-03"]
["UN33_DL074","Vendor Ship - Ti S/B Article 21","2006-10-04","2006-10-10"]
["UN33_DL075","AVAIL: Ti Strongback Article 21","2006-10-11","2006-10-10"]
["UN33_DL076","Dial-Fab/Assy - Ti Strongback Article 23","2006-10-02","2006-10-30"]
["UN33_DL077","RCV: Ti S/B Article 23 - Dial","2006-10-31","2006-10-31"]
["UN33_DL078","ACCEPT: Factory Acceptance - Ti S/B Article 23","2006-11-01","2006-11-01"]
["UN33_DL079","Vendor Ship - Ti S/B Article 23","2006-11-02","2006-11-08"]
["UN33_DL080","AVAIL: Ti Strongback Article 23","2006-11-09","2006-11-08"]
["UN33_DL081","Dial-Fab/Assy - Ti Strongback Article 25","2006-10-31","2006-11-30"]
["UN33_DL082","RCV: Ti S/B Article 25 - Dial","2006-12-01","2006-12-01"]
["UN33_DL083","ACCEPT: Factory Acceptance - Ti S/B Article 25","2006-12-04","2006-12-04"]
["UN33_DL084","Vendor Ship - Ti S/B Article 25","2006-12-05","2006-12-11"]
["UN33_DL085","AVAIL: Ti Strongback Article 25","2006-12-12","2006-12-11"]
["UN33_DL086","Dial-Fab/Assy - Ti Strongback Article 27","2006-12-01","2007-01-09"]
["UN33_DL087","RCV: Ti S/B Article 27 - Dial","2007-01-10","2007-01-10"]
["UN33_DL088","ACCEPT: Factory Acceptance - Ti S/B Article 27","2007-01-11","2007-01-11"]
["UN33_DL089","Vendor Ship - Ti S/B Article 27","2007-01-12","2007-01-18"]
["UN33_DL090","AVAIL: Ti Strongback Article 27","2007-01-19","2007-01-18"]
["UN33_DL091","Dial-Fab/Assy - Ti Strongback Article 29","2007-01-10","2007-02-07"]
["UN33_DL092","RCV: Ti S/B Article 29 - Dial","2007-02-08","2007-02-08"]
["UN33_DL093","ACCEPT: Factory Acceptance - Ti S/B Article 29","2007-02-09","2007-02-09"]
["UN33_DL094","Vendor Ship - Ti S/B Article 29","2007-02-12","2007-02-16"]
["UN33_DL095","AVAIL: Ti Strongback Article 29","2007-02-19","2007-02-16"]
["UN33_DL096","Dial-Fab/Assy - Ti Strongback Article 31","2007-02-08","2007-03-08"]
["UN33_DL097","RCV: Ti S/B Article 31 - Dial","2007-03-09","2007-03-09"]
["UN33_DL098","ACCEPT: Factory Acceptance - Ti S/B Article 31","2007-03-12","2007-03-12"]
["UN33_DL099","Vendor Ship - Ti S/B Article 31","2007-03-13","2007-03-19"]
["UN33_DL100","AVAIL: Ti Strongback Article 31","2007-03-20","2007-03-19"]
["UN33_DL101","Dial-Fab/Assy - Ti Strongback Article 33","2007-03-09","2007-04-06"]
["UN33_DL102","RCV: Ti S/B Article 33 - Dial","2007-04-09","2007-04-09"]
["UN33_DL103","ACCEPT: Factory Acceptance - Ti S/B Article 33","2007-04-10","2007-04-10"]
["UN33_DL104","Vendor Ship - Ti S/B Article 33","2007-04-11","2007-04-17"]
["UN33_DL105","AVAIL: Ti Strongback Article 33","2007-04-18","2007-04-17"]
["UN33_DL106","Dial-Fab/Assy - Ti Strongback Article 35","2007-04-09","2007-05-07"]
["UN33_DL107","RCV: Ti S/B Article 35 - Dial","2007-05-08","2007-05-08"]
["UN33_DL108","ACCEPT: Factory Acceptance - Ti S/B Article 36","2007-04-02","2007-04-02"]
["UN33_DL109","Vendor Ship - Ti S/B Article 36","2007-04-03","2007-04-09"]
["UN33_DL110","AVAIL: Ti Strongback Article 36","2007-04-10","2007-04-09"]
["UN33_DL111","Dial-Fab/Assy - Ti Strongback Article 37","2007-05-08","2007-06-06"]
["UN33_DL112","RCV: Ti S/B Article 37 - Dial","2007-06-07","2007-06-07"]
["UN33_DL113","ACCEPT: Factory Acceptance - Ti S/B Article 38","2007-05-01","2007-05-01"]
["UN33_DL114","Vendor Ship - Ti S/B Article 38","2007-06-08","2007-06-14"]
["UN33_DL115","AVAIL: Ti Strongback Article 38","2007-07-10","2007-07-09"]
["UN33_DL116","Dial-Fab/Assy - Ti Strongback Article 39","2007-06-07","2007-07-06"]
["UN33_DL117","RCV: Ti S/B Article 39 - Dial","2007-07-09","2007-07-09"]
["UN33_DL118","ACCEPT: Factory Acceptance - Ti S/B Article 40","2007-05-31","2007-05-31"]
["UN33_DL119","Vendor Ship - Ti S/B Article 40","2007-06-01","2007-06-07"]
["UN33_DL120","AVAIL: Ti Strongback Article 40","2007-06-08","2007-06-07"]
["UN33_DL64","Vendor Ship - Ti S/B Article 17","2006-08-04","2006-08-10"]
["UN33_M101","Prepare S/M Engineering Specification","2005-08-01","2005-08-29",null,"2005-08-01"]
["UN33_M103","Undulator support mover sys PED 80% complete","2005-10-01","2005-09-30",null,"2005-10-01","2005-09-30"]
["UN33_M104","Prepare for internal design review s/m system","2005-11-21","2005-12-06"]
["UN33_M105","Internal design review of S/M system","2005-12-07","2005-12-07"]
["UN33_M67","Modify APP for quadrupoles","2005-09-01","2005-05-31",null,"2005-09-01"]
["UN33_M73","Quadrupole APP approved","2005-06-01","2005-05-31"]
["UN33_M96","Undulator assembly procedures complete","2005-05-03","2005-05-02"]
["UN33_MP102","Controls/vacuum sys integration w/supp mover sys","2005-05-02","2005-09-30",null,"2005-05-02"]
["UN33_MP122","General M&S","2005-05-02","2005-09-30",null,"2005-05-02"]
["UN33_MP123","General Effort","2005-05-02","2005-09-30",null,"2005-05-02"]
["UN33_MP95","Produce SOW for undulator assembly","2005-05-02","2005-05-06"]
["UN33_MX010","PP: 1st Raw Piece - Metalex","2005-10-10","2005-10-10"]
["UN33_MX012","Metalex-Fab/Assy - Ti Strongback Article 02","2005-08-29","2005-10-14",null,"2005-08-29","2005-10-14"]
["UN33_MX014","Permission to proceed with Ti Production-Metalex","2005-10-18","2005-10-17"]
["UN33_MX015","RCV: Ti S/B Article 02 + Tooling - Metalex","2005-12-01","2005-12-01"]
["UN33_MX016","ACCEPT: Factory Acceptance - Ti S/B Article 02","2005-05-02","2005-05-02"]
["UN33_MX017","Vendor Ship - Ti S/B Article 02","2005-05-03","2005-05-09"]
["UN33_MX018","AVAIL: - Ti Strongback Article 02","2005-05-10","2005-05-09"]
["UN33_MX019","Metalex-Fab/Assy - Ti Strongback Article 04","2005-10-18","2005-11-15"]
["UN33_MX020","RCV: Ti S/B Article 04 - Metalex","2005-11-16","2005-11-16"]
["UN33_MX021","ACCEPT: Factory Acceptance - Ti S/B Article 04","2005-11-16","2005-11-16"]
["UN33_MX022","Vendor Ship - Ti S/B Article 04","2005-11-17","2005-11-23"]
["UN33_MX023","AVAIL: Ti Strongback Article 04","2005-11-28","2005-11-23"]
["UN33_MX024","Metalex-Fab/Assy - Ti Strongback Article 06","2005-11-16","2005-12-16"]
["UN33_MX025","RCV: Ti S/B Article 06 - Metalex","2005-12-19","2005-12-19"]
["UN33_MX026","ACCEPT: Factory Acceptance - Ti S/B Article 06","2005-12-20","2005-12-20"]
["UN33_MX027","Vendor Ship - Ti S/B Article 06","2005-12-21","2006-01-05"]
["UN33_MX028","AVAIL: Ti Strongback Article 06","2006-01-06","2006-01-05"]
["UN33_MX029","Metalex- Fab/Assy - Ti Strongback Article 08","2005-12-19","2006-01-25"]
["UN33_MX030","RCV: Ti S/B Article 08 - Metalex","2006-01-26","2006-01-26"]
["UN33_MX031","ACCEPT: Factory Acceptance - Ti S/B Article 08","2006-01-26","2006-01-26"]
["UN33_MX032","Vendor Ship - Ti S/B Article 08","2006-01-27","2006-02-02"]
["UN33_MX033","AVAIL: Ti Strongback Article 08","2006-02-03","2006-02-02"]
["UN33_MX034","Metalex-Fab/Assy - Ti Strongback Article 10","2006-01-26","2006-02-23"]
["UN33_MX035","RCV: Ti S/B Article 10 - Metalex","2006-02-24","2006-02-24"]
["UN33_MX036","ACCEPT: Factory Acceptance - Ti S/B Article 10","2006-02-24","2006-02-24"]
["UN33_MX037","MXVendor Ship - Ti S/B Article 10","2006-02-27","2006-03-03"]
["UN33_MX038","AVAIL: Ti Strongback Article 10","2006-03-06","2006-03-03"]
["UN33_MX039","Metalex-Fab/Assy - Ti Strongback Article 12","2006-02-24","2006-03-24"]
["UN33_MX040","RCV: Ti S/B Article 12 - Metalex","2006-03-27","2006-03-27"]
["UN33_MX041","ACCEPT: Factory Acceptance - Ti S/B Article 12","2006-03-27","2006-03-27"]
["UN33_MX042","Vendor Ship - Ti S/B Article 12","2006-03-28","2006-04-03"]
["UN33_MX043","AVAIL: Ti Strongback Article 12","2006-04-04","2006-04-03"]
["UN33_MX044","Metalex-Fab/Assy - Ti Strongback Article 14","2006-03-27","2006-04-24"]
["UN33_MX045","RCV: Ti S/B Article 14 - Metalex","2006-04-25","2006-04-25"]
["UN33_MX046","ACCEPT: Factory Acceptance - Ti S/B Article 14","2006-04-25","2006-04-25"]
["UN33_MX047","Vendor Ship - Ti S/B Article 14","2006-04-26","2006-05-02"]
["UN33_MX048","AVAIL: Ti Strongback Article 14","2006-05-03","2006-05-02"]
["UN33_MX049","Metalex-Fab/Assy - Ti Strongback Article 16","2006-04-25","2006-05-23"]
["UN33_MX050","RCV: Ti S/B Article 16 - Metalex","2006-05-24","2006-05-24"]
["UN33_MX051","ACCEPT: Factory Acceptance - Ti S/B Article 16","2006-05-24","2006-05-24"]
["UN33_MX052","Vendor Ship - Ti S/B Article 16","2006-05-25","2006-06-01"]
["UN33_MX053","AVAIL: Ti Strongback Article 16","2006-06-02","2006-06-01"]
["UN33_MX054","Metalexl-Fab/Assy - Ti Strongback Article 18","2006-05-24","2006-06-22"]
["UN33_MX055","RCV: Ti S/B Article 18 - Metalex","2006-06-23","2006-06-23"]
["UN33_MX056","ACCEPT: Factory Acceptance - Ti S/B Article 18","2006-06-23","2006-06-23"]
["UN33_MX057","Vendor Ship - Ti S/B Article 18","2006-06-26","2006-06-30"]
["UN33_MX058","AVAIL: Ti Strongback Article 18","2006-07-03","2006-06-30"]
["UN33_MX059","Metalex-Fab/Assy - Ti Strongback Article 20","2006-06-23","2006-07-24"]
["UN33_MX060","RCV: Ti S/B Article 20 - Metalex","2006-07-25","2006-07-25"]
["UN33_MX061","ACCEPT: Factory Acceptance - Ti S/B Article 20","2006-07-25","2006-07-25"]
["UN33_MX062","Vendor Ship - Ti S/B Article 20","2006-07-26","2006-08-01"]
["UN33_MX063","AVAIL: Ti Strongback Article 20","2006-08-02","2006-08-01"]
["UN33_MX064","Metalex-Fab/Assy - Ti Strongback Article 22","2006-07-25","2006-08-22"]
["UN33_MX065","RCV: Ti S/B Article 22 - Metalex","2006-08-23","2006-08-23"]
["UN33_MX066","ACCEPT: Factory Acceptance - Ti S/B Article 22","2006-08-24","2006-08-24"]
["UN33_MX067","Vendor Ship - Ti S/B Article 22","2006-08-25","2006-08-31"]
["UN33_MX068","AVAIL: Ti Strongback Article 22","2006-09-01","2006-08-31"]
["UN33_MX069","Metalex-Fab/Assy - Ti Strongback Article 24","2006-08-23","2006-09-21"]
["UN33_MX070","RCV: Ti S/B Article 24 - Metalex","2006-09-22","2006-09-22"]
["UN33_MX071","ACCEPT: Factory Acceptance - Ti S/B Article 24","2006-09-22","2006-09-22"]
["UN33_MX072","Vendor Ship - Ti S/B Article 24","2006-09-25","2006-09-29"]
["UN33_MX073","AVAIL: Ti Strongback Article 24","2006-10-02","2006-09-29"]
["UN33_MX074","Metalex-Fab/Assy - Ti Strongback Article 26","2006-09-22","2006-10-20"]
["UN33_MX080","RCV: Ti S/B Article 26 - Metalex","2006-10-23","2006-10-23"]
["UN33_MX081","ACCEPT: Factory Acceptance - Ti S/B Article 26","2006-10-24","2006-10-24"]
["UN33_MX082","Vendor Ship - Ti S/B Article 26","2006-10-25","2006-10-31"]
["UN33_MX083","AVAIL: Ti Strongback Article 26","2006-11-01","2006-10-31"]
["UN33_MX084","Metalex-Fab/Assy - Ti Strongback Article 28","2006-10-23","2006-11-20"]
["UN33_MX085","RCV: Ti S/B Article 28 - Metalex","2006-11-21","2006-11-21"]
["UN33_MX086","ACCEPT: Factory Acceptance - Ti S/B Article 28","2006-11-22","2006-11-22"]
["UN33_MX087","Vendor Ship - Ti S/B Article 28","2006-11-27","2006-12-01"]
["UN33_MX088","AVAIL: Ti Strongback Article 28","2006-12-04","2006-12-01"]
["UN33_MX089","Metalex-Fab/Assy - Ti Strongback Article 30","2006-11-21","2006-12-21"]
["UN33_MX090","RCV: Ti S/B Article 30 - Metalex","2007-01-02","2007-01-02"]
["UN33_MX091","ACCEPT: Factory Acceptance - Ti S/B Article 30","2007-01-03","2007-01-03"]
["UN33_MX092","Vendor Ship - Ti S/B Article 30","2007-01-04","2007-01-10"]
["UN33_MX093","AVAIL: Ti Strongback Article 30","2007-01-11","2007-01-10"]
["UN33_MX094","Metalex-Fab/Assy - Ti Strongback Article 32","2007-01-02","2007-01-30"]
["UN33_MX096","RCV: Ti S/B Article 32 - Metalex","2007-01-31","2007-01-31"]
["UN33_MX097","ACCEPT: Factory Acceptance - Ti S/B Article 32","2007-02-01","2007-02-01"]
["UN33_MX098","Vendor Ship - Ti S/B Article 32","2007-02-02","2007-02-08"]
["UN33_MX099","AVAIL: Ti Strongback Article 32","2007-02-09","2007-02-08"]
["UN33_MX101","Metalex-Fab/Assy - Ti Strongback Article 34","2007-01-31","2007-02-28"]
["UN33_MX102","RCV: Ti S/B Article 34 - Metalex","2007-03-01","2007-03-01"]
["UN33_MX106","Metalex-Fab/Assy - Ti Strongback Article 36","2007-03-01","2007-03-29"]
["UN33_MX107","RCV: Ti S/B Article 36 - Metalex","2007-03-30","2007-03-30"]
["UN33_MX111","Metalex-Fab/Assy - Ti Strongback Article 38","2007-03-30","2007-04-27"]
["UN33_MX112","RCV: Ti S/B Article 38 - Metalex","2007-04-30","2007-04-30"]
["UN33_MX116","Metalex-Fab/Assy - Ti Strongback Article 40","2007-04-30","2007-05-29"]
["UN33_MX117","RCV: Ti S/B Article 40 - Metalex","2007-05-30","2007-05-30"]
["UN33_MXA15","PP: 3 More Raws - Metalex - Articles 4,6,8","2005-11-30","2005-11-30"]
["UN33_MXB15","PP: 3 More Raws - Metalex - Articles 10,12,14","2005-12-22","2005-12-22"]
["UN33_MXC15","PP: 3 More Raws - Metalex - Articles 16,18,20","2006-01-31","2006-01-31"]
["UN33_MXD15","PP: 3 More Raws - Metalex - Articles 22,24,26","2006-02-28","2006-02-28"]
["UN33_MXE15","PP: 3 More Raws - Metalex - Articles 28,30,32","2006-04-28","2006-04-28"]
["UN33_MXF15","PP: 4 More Raws - Metalex - Articles 34,36,38,40","2006-06-30","2006-06-30"]
["UN33_MXP24","Metalex-Fab/Assy - Ti Strongback Article 06","2005-05-02","2005-05-31"]
["UN33_MXP25","RCV: Ti S/B Article 06 - Metalex","2005-05-02","2005-05-02"]
["UN33_P0550","Design Proto Undulator Shipping Crate","2005-09-01","2005-09-09"]
["UN33_P0553","Construct/Procure Proto Undulator Shipping Crate","2005-10-03","2005-10-13"]
["UN33_P0554","Crate Instrumentation","2005-10-14","2005-10-14"]
["UN33_P0555","Pack & Ship Proto Undulator to SLAC (Loan)","2005-12-01","2005-12-09"]
["UN33_P0560","Proto Undulator at SLAC","2005-12-12","2006-01-18"]
["UN33_P0565","Pack & Ship Proto Undulator back to ANL","2006-01-19","2006-01-27"]
["UN33_VEN05","Ti Strongback Vendor Oversight","2005-07-01","2006-08-22",null,"2005-07-01"]
["UN33_VEN10","Ti Strongback Vendor Oversight","2006-08-23","2006-11-16"]
["UN33_VEN15","Magnet Poles Vendor Oversight","2005-07-18","2006-04-04"]
["UN34_00006","Renegotiate Contract for 38 Suppt/Mover System","2006-12-18","2006-12-18"]
["UN34_00007","Permission to Proc w/Rem 38 Supt/Mover Systems","2006-12-19","2006-12-18"]
["UN34_00010","Revise Contract Option Hi-Tech - Prdn Units","2006-05-05","2006-05-18"]
["UN34_00012","Evaluate 1st 2 Articles Support/Mover","2006-10-31","2006-11-30"]
["UN34_00013","Renegotiate Contract - 1st Article Support/Mover","2006-12-01","2006-12-14"]
["UN34_00014","Vendor Fab Support/Mover Production Units","2006-12-19","2008-03-07"]
["UN34_00015","AWARD:  Support/Mover Production Units","2006-12-15","2006-12-15"]
["UN34_00017","ACCEPT: 1st 2 Articles Support/Mover","2006-12-01","2006-11-30"]
["UN34_00020","AWARD: Exercise Option @ Hi-Tech - Prdn Units","2006-05-19","2006-05-19"]
["UN34_00045","RCV: Ti Strongback - @ Hi-Tech Article 03","2006-01-16","2006-01-13"]
["UN34_00047","RCV: Support/Mover Lot 1 (9 units)","2007-04-25","2007-04-25"]
["UN34_00048","RCV: Support/Mover Lot  2 (10 units)","2007-08-13","2007-08-13"]
["UN34_00049","RCV: Support/Mover Lot 3a (4 units)","2007-10-09","2007-10-09"]
["UN34_00050","Hi-Tech Fab/Assy - Mag Assy Und Article 03","2006-05-22","2006-07-03"]
["UN34_00051","RCV: Support/Mover Lot 4 (3 units)","2008-01-14","2008-01-14"]
["UN34_00052","RCV: From Hi-Tech - Mag Assy Und Article 03","2006-07-05","2006-07-05"]
["UN34_00053","RCV: Ti Strongback - @ Hi-Tech Article 05","2006-02-14","2006-02-13"]
["UN34_00054","Hi-Tech Fab/Assy - Mag Assy Und Article 05","2006-07-06","2006-08-03"]
["UN34_00056","RCV: From Hi-Tech - Magnet Assy Article 05","2006-08-04","2006-08-04"]
["UN34_00057","RCV: Ti Strongback -  @ Hi-Tech Article 07","2006-03-15","2006-03-14"]
["UN34_00058","Hi-Tech Fab/Assy - Magnet Assy Article 07","2006-08-07","2006-08-25"]
["UN34_00059","Acceptance Measmt and Verif of Undulator Assy","2005-05-02","2006-04-21"]
["UN34_00060","RCV: From Hi-Tech - Magnet Assy Article 07","2006-08-28","2006-08-28"]
["UN34_00061","RCV: Ti Strongback - @ Hi-Tech Article 09","2006-04-13","2006-04-12"]
["UN34_00062","Hi-Tech Fab/Assy - Magnet Assy Article 09","2006-08-29","2006-09-12"]
["UN34_00064","RCV: From Hi-Tech - Magnet Assy Article 09","2006-09-13","2006-09-13"]
["UN34_00065","RCV: Ti Strongback - @ Hi-Tech Article 11","2006-05-12","2006-05-11"]
["UN34_00066","RCV: 2nd Lot Magnet Blocks, Poles - @Hi-Tech #11","2006-02-20","2006-02-17"]
["UN34_00067","Hi-Tech Fab/Assy - Magnet Assy Article 11","2006-09-14","2006-09-27"]
["UN34_00068","RCV: From Hi-Tech - Magnet Assy Article 11","2006-09-28","2006-09-28"]
["UN34_00069","RCV: Ti Strongback - @ Hi-Tech Article 13","2006-06-13","2006-06-12"]
["UN34_00070","Hi-Tech Fab/Assy - Magnet Assy Article 13","2006-09-29","2006-10-12"]
["UN34_00072","RCV: From Hi-Tech - Magnet Assy Article 13","2006-10-13","2006-10-13"]
["UN34_00073","RCV: Ti Strongback - @ Hi-Tech Article 15","2006-07-13","2006-07-12"]
["UN34_00074","Hi-Tech Fab/Assy - Magnet Assy Article 15","2006-10-16","2006-10-27"]
["UN34_00075","RCV: Ti Strongback - Hi-Tech Article 17","2006-08-11","2006-08-10"]
["UN34_00076","RCV: From Hi-Tech - Magnet Assy Article 15","2006-10-30","2006-10-30"]
["UN34_00078","Hi-Tech Fab/Assy - Magnet Assy Article 17","2006-10-31","2006-11-13"]
["UN34_00080","RCV: From Hi-Tech - Magnet Assy Article 17","2006-11-14","2006-11-14"]
["UN34_00081","RCV: Ti Strongback - @ Hi-Tech Article 19","2006-09-12","2006-09-11"]
["UN34_00082","Hi-Tech Fab/Assy - Magnet Assy Article 19","2006-11-15","2006-11-30"]
["UN34_00083","RCV: From Hi-Tech - Magnet Assy Article 19","2006-12-08","2006-12-08"]
["UN34_00084","RCV: 3rd Lot Magnet Blocks, Poles - @Hi-Tech #21","2006-04-28","2006-04-27"]
["UN34_00085","RCV: Ti Strongback - @ Hi-Tech Article 21","2006-10-11","2006-10-10"]
["UN34_00086","Hi-Tech Fab/Assy - Magnet Assy Article 21","2006-12-11","2007-01-02"]
["UN34_00088","RCV: From Hi-Tech - Magnet Assy Article 21","2007-01-03","2007-01-03"]
["UN34_00089","RCV: Ti Strongback - @ Hi-Tech Article 23","2006-11-09","2006-11-08"]
["UN34_00090","Hi-Tech Fab/Assy - Magnet Assy Article 23","2007-01-04","2007-01-17"]
["UN34_00092","RCV: From Hi-Tech - Magnet Assy Article 23","2007-01-18","2007-01-18"]
["UN34_00093","RCV: Ti Strongback - @ Hi-Tech Article 25","2006-12-12","2006-12-11"]
["UN34_00094","Hi-Tech Fab/Assy - Magnet Assy Article 25","2007-01-19","2007-02-01"]
["UN34_00096","RCV: From Hi-Tech - Magnet Assy Article 25","2007-02-02","2007-02-02"]
["UN34_00097","RCV: Ti Strongback - @ Hi-Tech Article 27","2007-01-19","2007-01-18"]
["UN34_00098","Hi-Tech Fab/Assy - Magnet Assy Article 27","2007-02-05","2007-02-16"]
["UN34_00100","RCV: From Hi-Tech - Magnet Assy Article 27","2007-02-19","2007-02-19"]
["UN34_00101","RCV: Ti Strongback - @ Hi-Tech Article 29","2007-02-19","2007-02-16"]
["UN34_00102","Hi-Tech Fab/Assy - Magnet Assy Article 29","2007-02-20","2007-03-05"]
["UN34_00103","RCV: From Hi-Tech - Magnet Assy Article 29","2007-03-06","2007-03-06"]
["UN34_00104","RCV: 4th Lot Magnet Blocks, Poles - @Hi-Tech #31","2006-09-07","2006-09-06"]
["UN34_00105","RCV: Ti Strongback - @ Hi-Tech Article 31","2007-03-20","2007-03-19"]
["UN34_00106","Hi-Tech Fab/Assy - Magnet Assy Article 31","2007-03-20","2007-04-02"]
["UN34_00108","RCV: From Hi-Tech - Magnet Assy Article 31","2007-04-03","2007-04-03"]
["UN34_00109","RCV: Ti Strongback - @ Hi-Tech Article 33","2007-04-18","2007-04-17"]
["UN34_00110","Hi-Tech Fab/Assy - Magnet Assy Article 33","2007-04-18","2007-05-01"]
["UN34_00112","RCV: From Hi-Tech - Magnet Assy Article 33","2007-05-02","2007-05-02"]
["UN34_00114","Hi-Tech Fab/Assy - Magnet Assy Article 35","2007-05-03","2007-05-16"]
["UN34_00116","RCV: From Hi-Tech - Magnet Assy Article 35","2007-05-17","2007-05-17"]
["UN34_00118","Hi-Tech Fab/Assy - Magnet Assy Article 37","2007-05-18","2007-06-01"]
["UN34_00120","RCV: From Hi-Tech - Magnet Assy Article 37","2007-06-04","2007-06-04"]
["UN34_00122","Hi-Tech Fab/Assy - Magnet Assy Article 39","2007-06-05","2007-06-18"]
["UN34_00124","RCV: From Hi-Tech - Magnet Assy Article 39","2007-06-19","2007-06-19"]
["UN34_00149","RCV: Support/Mover Lot 3b (3 units)","2007-11-06","2007-11-06"]
["UN34_00249","RCV: Support/Mover Lot 3c (2 units)","2007-12-06","2007-12-06"]
["UN34_10010","Revise Contract Option Metalex - Prdn Units","2006-06-06","2006-06-19"]
["UN34_10020","AWARD: Exercise Option Metalex Prdn Units","2006-06-20","2006-06-20"]
["UN34_10025",null,"2005-05-02","2005-05-02"]
["UN34_10045","RCV: Ti Strongback - @ Metalex Article 04","2005-11-28","2005-11-23"]
["UN34_10050","Metalex Fab/Assy - Magnet Assy Article 04","2006-06-21","2006-08-02"]
["UN34_10052","RCV: From Metalex - Magnet Assy Article 04","2006-08-03","2006-08-03"]
["UN34_10053","RCV: Ti Strongback - @ Metalex Article 06","2006-01-06","2006-01-05"]
["UN34_10054","Metalex Fab/Assy - Magnet Assy Article 06","2006-08-04","2006-09-01"]
["UN34_10056","RCV: From Metalex - Magnet Assy Article 06","2006-09-05","2006-09-05"]
["UN34_10057","RCV: Ti Strongback - @ Metalex Article 08","2006-02-03","2006-02-02"]
["UN34_10058","Metalex Fab/Assy - Magnet Assy Article 08","2006-09-06","2006-09-26"]
["UN34_10060","RCV: From Metalex - Magnet Assy Article 08","2006-09-27","2006-09-27"]
["UN34_10061","RCV: Ti Strongback - @ Metalex Article 10","2006-04-13","2006-04-12"]
["UN34_10062","Metalex Fab/Assy - Magnet Assy Article 10","2006-09-28","2006-10-11"]
["UN34_10064","RCV: From Metalex - Magnet Assy Article 10","2006-10-12","2006-10-12"]
["UN34_10065","RCV: 2nd Lot Magnet Blocks, Poles - @Metalex #12","2006-02-20","2006-02-17"]
["UN34_10066","RCV: Ti Strongback - @ Metalex Article 12","2006-04-04","2006-04-03"]
["UN34_10067","Metalex Fab/Assy - Magnet Assy Article 12","2006-10-13","2006-10-26"]
["UN34_10068","RCV: From Metalex - Magnet Assy Article 12","2006-10-27","2006-10-27"]
["UN34_10069","RCV: Ti Strongback - @ Metalex Article 14","2006-05-03","2006-05-02"]
["UN34_10070","Metalex Fab/Assy - Magnet Assy Article 14","2006-10-30","2006-11-10"]
["UN34_10072","RCV: From Metalex - Magnet Assy Article 14","2006-11-13","2006-11-13"]
["UN34_10073","RCV: Ti Strongback - @ Metalex Article 16","2006-06-02","2006-06-01"]
["UN34_10074","Metalex Fab/Assy - Magnet Assy Article 16","2006-11-14","2006-11-29"]
["UN34_10076","RCV: From Metalex - Magnet Assy Article 16","2006-11-30","2006-11-30"]
["UN34_10077","RCV: Ti Strongback - @ Metalex Article18","2006-07-03","2006-06-30"]
["UN34_10078","Metalex Fab/Assy - Magnet Assy Article 18","2006-12-01","2006-12-14"]
["UN34_10080","RCV: From Metalex - Magnet Assy Article 18","2006-12-15","2006-12-15"]
["UN34_10081","RCV: Ti Strongback - @ Metalex Article 20","2006-09-12","2006-09-11"]
["UN34_10082","Metalex Fab/Assy - Magnet Assy Article 20","2006-12-18","2007-01-09"]
["UN34_10083","RCV: From Metalex - Magnet Assy Article 20","2007-01-10","2007-01-10"]
["UN34_10084","RCV: 3rd Lot Magnet Blocks, Poles - @Metalex #22","2006-04-28","2006-04-27"]
["UN34_10085","RCV: Ti Strongback - @ Metalex Article 22","2006-09-01","2006-08-31"]
["UN34_10086","Metalex Fab/Assy - Magnet Assy Article 22","2007-01-11","2007-01-24"]
["UN34_10088","RCV: From Metalex - Magnet Assy Article 22","2007-01-25","2007-01-25"]
["UN34_10089","RCV: Ti Strongback - @ Metalex Article 24","2006-10-02","2006-09-29"]
["UN34_10090","Metalex Fab/Assy - Magnet Assy Article 24","2007-01-26","2007-02-08"]
["UN34_10092","RCV: From Metalex - Magnet Assy Article 24","2007-02-09","2007-02-09"]
["UN34_10093","RCV: Ti Strongback - @ Metalex Article 26","2006-11-01","2006-10-31"]
["UN34_10094","Metalex Fab/Assy - Magnet Assy Article 26","2007-02-12","2007-02-23"]
["UN34_10096","RCV: From Metalex - Magnet Assy Article 26","2007-02-26","2007-02-26"]
["UN34_10097","RCV: Ti Strongback - @ Metalex Article 28","2006-12-04","2006-12-01"]
["UN34_10098","Metalex Fab/Assy - Magnet Assy Article 28","2007-02-27","2007-03-12"]
["UN34_10100","RCV: From Metalex - Magnet Assy Article 28","2007-03-13","2007-03-13"]
["UN34_10101","RCV: Ti Strongback - @ Metalex Article 30","2007-01-11","2007-01-10"]
["UN34_10102","Metalex Fab/Assy - Magnet Assy Article 30","2007-03-14","2007-03-27"]
["UN34_10103","50% production undulators delivered","2007-01-11","2007-01-10"]
["UN34_10104","RCV: From Metalex - Magnet Assy Article 30","2007-03-28","2007-03-28"]
["UN34_10105","RCV: Ti Strongback - @ Metalex Article 32","2007-02-09","2007-02-08"]
["UN34_10106","Metalex Fab/Assy - Magnet Assy Article 32","2007-03-29","2007-04-11"]
["UN34_10107","RCV: From Metalex - Magnet Assy Article 32","2007-04-12","2007-04-12"]
["UN34_10108","RCV: 4th Lot Magnet Blocks, Poles - @Metalex #32","2006-09-07","2006-09-06"]
["UN34_10110","Metalex Fab/Assy - Magnet Assy Article 34","2007-04-13","2007-04-26"]
["UN34_10112","RCV: From Metalex - Magnet Assy Article 34","2007-04-27","2007-04-27"]
["UN34_10113","RCV: Ti Strongback - Vend B #36","2007-04-10","2007-04-09"]
["UN34_10114","Metalex Fab/Assy - Magnet Assy Article 36","2007-04-30","2007-05-11"]
["UN34_10116","RCV: From Metalex - Magnet Assy Article 36","2007-05-14","2007-05-14"]
["UN34_10117","RCV: Ti Strongback - Vend B #38","2007-07-10","2007-07-09"]
["UN34_10118","Metalex Fab/Assy - Magnet Assy Article 38","2007-07-10","2007-07-23"]
["UN34_10120","RCV: From Metalex - Magnet Assy Article 38","2007-07-24","2007-07-24"]
["UN34_10121","RCV: Ti Strongback - Vend B #40","2007-06-08","2007-06-07"]
["UN34_10122","Metalex Fab/Assy - Magnet Assy Article 40","2007-07-25","2007-08-07"]
["UN34_10123","RCV: From Metalex - Magnet Assy Article 40","2007-08-08","2007-08-08"]
["UN34_10134","25% production undulators delivered","2006-10-13","2006-10-12"]
["UN34_10144","75% production undulators delivered","2007-03-29","2007-03-28"]
["UN34_10154","100% production/spare undulators received","2007-08-09","2007-08-08"]
["UN34_10250","RCV:  Support/Mover Lot 4 (5 units)","2008-01-15","2008-01-15"]
["UN34_P0010","Components for Support/Mover Prototype","2005-10-03","2006-10-02"]
["UN34_P0052","RCV:  Support/Mover Lot 4 (2 units)","2008-01-15","2008-01-15"]
["UN35_00020","Define Engineering Requirements - Quadrupole","2005-06-27","2005-06-29",null,"2005-06-27"]
["UN35_00028","Prototype Quadrupole Section","2005-11-23","2006-01-03"]
["UN35_00030","COMP: Rev Specs - Quadrupoles + Controls + PS","2005-06-30","2005-06-29"]
["UN35_00067","Prepare Bid Package - Quad Cables","2006-07-24","2006-08-04"]
["UN35_00069","Prepare Bid Package - Stages, Stands, etc.","2006-05-24","2006-06-07"]
["UN35_00070","Release RFP - Quadrupole Magnets","2006-02-02","2006-02-02"]
["UN35_00072","Release RFP - Quad Cables","2006-08-07","2006-08-04"]
["UN35_00074","Release RFP - Stages, Stands, etc.","2006-06-08","2006-06-07"]
["UN35_00075","Release RFP - Quadrupole Power Supplies","2006-03-30","2006-03-30"]
["UN35_00080","Vendor Prep Proposal - Quadrupole Magnets","2006-02-03","2006-03-03"]
["UN35_00082","Vendor Prep Proposal - Quad Cables","2006-08-07","2006-09-05"]
["UN35_00084","Vendor Prep Proposal - Stages, Stands, etc.","2006-06-08","2006-07-07"]
["UN35_00085","Vendor Prep Proposal - Quadrupole Power Supplies","2006-03-31","2006-04-28"]
["UN35_00090","RCV: Proposal - Quadrupole Magnets","2006-03-06","2006-03-03"]
["UN35_00092","RCV Proposal - Quad Cables","2006-09-06","2006-09-05"]
["UN35_00094","RCV Proposal - Stages, Stands, etc.","2006-07-10","2006-07-07"]
["UN35_00095","RCV:  Proposal - Qudrupole Power Supplies","2006-05-01","2006-04-28"]
["UN35_00100","Evaluate Proposal - Quadrupole Magnets","2006-03-06","2006-03-17"]
["UN35_00101","Evaluate Proposal - Quad Cables","2006-09-06","2006-09-12"]
["UN35_00102","Evaluate Proposal - Quadrupole Power Supplies","2006-05-01","2006-05-19"]
["UN35_00103","Evaluate Proposal - Stages, Stands, etc.","2006-07-10","2006-07-14"]
["UN35_00105","COMP: Accept Vendor Mag Design & Fab & Assy Plan","2006-03-20","2006-03-17"]
["UN35_00110","AWARD: Contract - Quadrupole Magnets","2006-03-20","2006-03-20"]
["UN35_00111","AWARD:  Contract-Quad PS+2 Corr+CTRL Hdwr+Interf","2006-05-22","2006-05-22"]
["UN35_00112","Vendor Fab/Assy - Quad Magnet 1st Article","2006-03-21","2006-08-16"]
["UN35_00113","Vendor Fab/Assy - Quad PS 1st Articles","2006-05-23","2006-11-17"]
["UN35_00114","Ship to ANL - Quad Magnet 1st Article","2006-08-18","2006-08-24"]
["UN35_00116","Measure Magnet - Quad Magnet 1st Article","2006-08-25","2006-08-31"]
["UN35_00117","Accept Quad Magnet 1st Article","2006-09-01","2006-09-01"]
["UN35_00118","AWARD: Contract Option - Quadrupole Magnets","2006-09-01","2006-09-01"]
["UN35_00119","Dimensional Measurement Quad PS 1st Article","2007-01-09","2007-01-11"]
["UN35_00120","Vendor Fab/Assy - Quad Mag 1st lot (18)","2006-10-02","2007-02-15"]
["UN35_00121","Review Travelers - Quadrupole Magnet 1st lot","2007-02-16","2007-02-22"]
["UN35_00122","Vendor Fab/Assy - Quad Mag 2nd lot (15)","2007-02-16","2007-06-22"]
["UN35_00123","Accept Quad PS 1st Article","2007-01-12","2007-01-12"]
["UN35_00124","Permission to Proceed w/Quad PS Fabrication","2007-01-15","2007-01-15"]
["UN35_00125","Ship to ANL - Quad PS 1st Article","2006-11-21","2006-11-29"]
["UN35_00126","Accept Quad PS 1st Lot","2007-05-30","2007-05-30"]
["UN35_00127","Ship Quad 1st Article to SLAC MMF","2006-09-05","2006-09-11"]
["UN35_00128","Electromagnetic Test Quad PS 1st Article","2006-11-30","2007-01-08"]
["UN35_00129","Permission to Proceed w/Quad PS Fabrication","2007-05-31","2007-05-31"]
["UN35_00130","Vendor Fab/Assy -Quad/Corr PS+Ctl HW 1st lot(18)","2007-01-16","2007-05-21"]
["UN35_00132","Vendor Fab/Assy - Quads Spares (4-mag)","2007-02-20","2007-03-05"]
["UN35_00133","Vendor Fab/Assy - Quad PS+ addl items (4)","2007-10-01","2007-10-08"]
["UN35_00134","Review Travelers - Quadrupole Magnet 1st article","2006-08-11","2006-08-17"]
["UN35_00135","Review Travelers - Quadrupole PS 1st article","2006-11-20","2006-11-20"]
["UN35_00136","Review Travelers - Quadrupole Mag 2nd lot","2007-06-25","2007-06-29"]
["UN35_00137","Review Travelers - Quadrupole PS 1st lot","2007-05-22","2007-05-29"]
["UN35_00138","Ship to SLAC MMF - Quadrupole PS 1st lot","2007-05-31","2007-06-06"]
["UN35_00139","Ship to SLAC MMF - Quadrupole PS 1st Article","2007-01-15","2007-01-19"]
["UN35_00140","Vendor Fab/Assy -Quad/Corr PS+Ctl HW 2nd lot(15)","2007-05-22","2007-09-27"]
["UN35_00141","Review Travelers - Quadrupole PS 2nd lot","2007-09-28","2007-10-04"]
["UN35_00142","100% Quads received","2007-03-06","2007-03-05"]
["UN35_00143","Ship to SLAC MMF - Quadrupole PS 2nd lot","2007-10-08","2007-10-12"]
["UN35_00144","Ship to SLAC MMF - Quadrupole Magnet 1st lot","2007-02-23","2007-03-01"]
["UN35_00145","100% Quad Power Supplies received","2007-10-09","2007-10-09"]
["UN35_00147","Accept Quad PS 2nd Lot","2007-10-05","2007-10-05"]
["UN35_00150","Vendor Fab/Assy - Quad Stages, Stands, etc. (4)","2006-11-03","2006-11-16"]
["UN35_00151","Vendor Fab/Assy - Quad Cables (4)","2006-11-03","2006-11-16"]
["UN35_00154","Ship to SLAC MMF - Quadrupole Mag 2nd lot","2007-07-02","2007-07-09"]
["UN35_00155","100% Quadrupole Magnets Recvd at SLAC","2007-07-10","2007-07-09"]
["UN35_00170","AWARD: - Contract - Stages and Stands, etc.","2006-07-17","2006-07-17"]
["UN35_00172","AWARD: - Contract - Quad Cables","2006-10-02","2006-10-02"]
["UN35_00174","REC:  100% of Stages and Stands, etc.","2007-01-31","2007-01-30"]
["UN35_00175","REC:  100% of Quadrupole Cables","2007-02-16","2007-02-15"]
["UN35_00184","Vendor Ship - Stages, Stands, etc. to SLAC","2007-01-24","2007-01-30"]
["UN35_00210","AWARD: Contract - Quads Spares (4-mag)","2007-02-16","2007-02-16"]
["UN35_00211","AWARD:  Contract-Quad PS+addl items (4)","2007-09-28","2007-09-28"]
["UN35_00270","AWARD - Contract - Stages and Stands (4)","2006-11-02","2006-11-02"]
["UN35_00272","AWARD - Contract - Quad Cables","2006-11-02","2006-11-02"]
["UN35_01132","Vendor Fab/Assy - Quad Cables","2006-10-03","2007-02-08"]
["UN35_01133","Vendor Fab/Assy - Stages, Stands, etc.","2006-07-18","2007-01-23"]
["UN35_01142","Vendor Ship Quad Cables to Slac","2007-02-09","2007-02-15"]
["UN35_M112","Design quadrupole magnet system","2005-07-01","2005-06-29",null,"2005-07-01"]
["UN35_M113","Specify quad and corrector power supplies","2005-09-01","2005-11-18"]
["UN35_M114","Write SOW for quad/corrector magnets","2005-09-01","2005-11-22"]
["UN35_M115","Write SOW for quad and corrector power supplies","2005-11-21","2006-01-30"]
["UN35_M116","SOWs complete","2006-07-24","2006-07-21"]
["UN35_M117","IDR - quadrupole magnet system","2005-11-22","2005-11-22"]
["UN35_M118","Prepare RFPs for quadrupole magnets","2005-11-23","2006-01-03"]
["UN35_M119","Prepare RFP for quad & corrector power supplies","2006-01-31","2006-03-29"]
["UN35_M121","Write SOW for Stages, Stands, etc.","2006-04-25","2006-05-23"]
["UN35_M122","Write SOW for Quad Cables","2006-06-22","2006-07-21"]
["UN35_M124","Verify Quad Section Performance","2006-01-04","2006-01-18"]
["UN35_M125","FDR Quad System","2006-02-01","2006-02-01"]
["UN35_M127","RFI for Quad Magnets with draft SOW","2005-11-23","2006-01-09"]
["UN35_M129","Prepare for Quadrupole System IDR","2005-09-26","2005-06-27",null,"2005-09-26"]
["UN35_M130","Prepare for Quadrupole System FDR","2006-01-18","2006-01-31"]
["UN35_MP110","Preliminary engineering of quadrupole system","2005-05-02","2005-06-24"]
["UN362_0010","REQD:  Undulator Mag Assy - 01","2006-05-19","2006-05-18"]
["UN362_0020","Adjust to Temperature - 01","2006-05-19","2006-06-02"]
["UN362_0030","Undulator Setup and Alignment @ Test Bench - 01","2006-07-31","2006-08-01"]
["UN362_0040","Undulator Measurement and Set Gap - 01","2006-08-02","2006-08-08"]
["UN362_0060","Undulator Measurement/Pre-fiducialization - 01","2006-08-09","2006-08-22"]
["UN362_0070","Undulator Setup and Alignment @ CMM - 01","2006-08-23","2006-08-23"]
["UN362_0080","Undulator Fiducialization - 01","2006-08-24","2006-08-30"]
["UN362_0085","Undulator Ready for Assembly - 01","2006-08-31","2006-09-07"]
["UN362_0087","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 01","2007-07-23","2007-07-20"]
["UN362_0088","Assemble Cradle/Vacuum Chamber - 01","2007-07-23","2007-07-24"]
["UN362_0089","Assemble Quad/Vac Chmbr/BPM/Cher Det - 01","2007-07-25","2007-07-30"]
["UN362_0090","Undulator/QD/VacCh/BPM/Prealign - 01","2007-07-25","2007-07-30"]
["UN362_0100","Undulator Cradle RFI - 01","2007-07-31","2007-07-30"]
["UN362_0110","REQD:  Undulator Mag Assy - 02","2006-06-20","2006-06-19"]
["UN362_0120","Adjust to Temperature - 02","2006-06-20","2006-07-03"]
["UN362_0130","Undulator Setup and Alignment @ Test Bench - 02","2006-08-23","2006-08-24"]
["UN362_0140","Undulator Measurement and Set Gap - 02","2006-08-25","2006-08-31"]
["UN362_0160","Undulator Measurement/Pre-fiducialization - 02","2006-09-01","2006-09-15"]
["UN362_0170","Undulator Setup and Alignment @ CMM - 02","2006-09-18","2006-09-18"]
["UN362_0180","Undulator Fiducialization - 02","2006-09-19","2006-09-25"]
["UN362_0185","Undulator Ready for Assembly - 02","2006-09-26","2006-10-02"]
["UN362_0187","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 02","2007-07-20","2007-07-19"]
["UN362_0188","Assemble Cradle/Vacuum Chamber - 02","2007-07-20","2007-07-23"]
["UN362_0189","Assemble Quad/Vac Chmbr/BPM/Cher Det - 02","2007-07-24","2007-07-27"]
["UN362_0190","Undulator/QD/VacCh/BPM/Prealign - 02","2007-07-24","2007-07-27"]
["UN362_0200","Undulator Cradle RFI - 02","2007-07-30","2007-07-27"]
["UN362_0210","REQD:  Undulator Mag Assy - 03","2006-07-06","2006-07-05"]
["UN362_0220","Adjust to Temperature - 03","2006-07-06","2006-07-19"]
["UN362_0230","Undulator Setup and Alignment @ Test Bench - 03","2006-09-18","2006-09-18"]
["UN362_0240","Undulator Measurement and Set Gap - 03","2006-09-19","2006-09-22"]
["UN362_0260","Undulator Measurement/Pre-fiducialization - 03","2006-09-25","2006-10-04"]
["UN362_0270","Undulator Setup and Alignment @ CMM - 03","2006-10-05","2006-10-05"]
["UN362_0280","Undulator Fiducialization - 03","2006-10-06","2006-10-11"]
["UN362_0285","Undulator Ready for Assembly - 03","2006-10-12","2006-10-18"]
["UN362_0287","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 03","2007-07-20","2007-07-19"]
["UN362_0288","Assemble Cradle/Quad Supt/Movers - 03","2007-07-20","2007-07-20"]
["UN362_0289","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 03","2007-07-23","2007-07-24"]
["UN362_0290","Install Undulators on Cradle- 03","2007-07-25","2007-07-25"]
["UN362_0291","Prealign Vacuum Chamber - 03","2007-07-26","2007-07-26"]
["UN362_0300","Undulator Cradle RFI - 03","2007-07-27","2007-07-26"]
["UN362_0310","REQD:  Undulator Mag Assy - 04","2006-08-04","2006-08-03"]
["UN362_0320","Adjust to Temperature - 04","2006-08-04","2006-08-17"]
["UN362_0330","Undulator Setup and Alignment @ Test Bench - 04","2006-10-05","2006-10-05"]
["UN362_0340","Undulator Measurement and Set Gap - 04","2006-10-06","2006-10-11"]
["UN362_0360","Undulator Measurement/Pre-fiducialization - 04","2006-10-12","2006-10-23"]
["UN362_0370","Undulator Setup and Alignment @ CMM - 04","2006-10-24","2006-10-24"]
["UN362_0380","Undulator Fiducialization - 04","2006-10-25","2006-10-30"]
["UN362_0385","Undulator Ready for Assembly - 04","2006-10-31","2006-11-06"]
["UN362_0387","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 04","2007-07-20","2007-07-19"]
["UN362_0388","Assemble Cradle/Quad Supt/Movers - 04","2007-07-20","2007-07-20"]
["UN362_0389","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 04","2007-07-23","2007-07-24"]
["UN362_0390","Install Undulators on Cradle- 04","2007-07-25","2007-07-25"]
["UN362_0391","Prealign Vacuum Chamber - 04","2007-07-26","2007-07-26"]
["UN362_0400","Undulator Cradle RFI - 04","2007-07-27","2007-07-26"]
["UN362_0410","REQD:  Undulator Mag Assy - 05","2006-08-07","2006-08-04"]
["UN362_0420","Adjust to Temperature - 05","2006-08-07","2006-08-18"]
["UN362_0430","Undulator Setup and Alignment @ Test Bench - 05","2006-10-24","2006-10-24"]
["UN362_0440","Undulator Measurement and Set Gap - 05","2006-10-25","2006-10-26"]
["UN362_0460","Undulator Measurement/Pre-fiducialization - 05","2006-10-27","2006-11-01"]
["UN362_0470","Undulator Setup and Alignment @ CMM - 05","2006-11-02","2006-11-02"]
["UN362_0480","Undulator Fiducialization - 05","2006-11-03","2006-11-06"]
["UN362_0485","Undulator Ready for Assembly - 05","2006-11-07","2006-11-13"]
["UN362_0487","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 05","2007-07-20","2007-07-19"]
["UN362_0488","Assemble Cradle/Quad Supt/Movers - 05","2007-07-20","2007-07-20"]
["UN362_0489","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 05","2007-07-23","2007-07-24"]
["UN362_0490","Install Undulators on Cradle- 05","2007-07-25","2007-07-25"]
["UN362_0491","Prealign Vacuum Chamber - 05","2007-07-26","2007-07-26"]
["UN362_0500","Undulator Cradle RFI - 05","2007-07-27","2007-07-26"]
["UN362_0510","REQD:  Undulator Mag Assy - 06","2006-09-06","2006-09-05"]
["UN362_0520","Adjust to Temperature - 06","2006-09-06","2006-09-19"]
["UN362_0530","Undulator Setup and Alignment @ Test Bench - 06","2006-11-02","2006-11-02"]
["UN362_0540","Undulator Measurement and Set Gap - 06","2006-11-03","2006-11-07"]
["UN362_0560","Undulator Measurement/Pre-fiducialization - 06","2006-11-08","2006-11-10"]
["UN362_0570","Undulator Setup and Alignment @ CMM - 06","2006-11-13","2006-11-13"]
["UN362_0580","Undulator Fiducialization - 06","2006-11-14","2006-11-15"]
["UN362_0585","Undulator Ready for Assembly - 06","2006-11-16","2006-11-22"]
["UN362_0587","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 06","2007-07-20","2007-07-19"]
["UN362_0588","Assemble Cradle/Quad Supt/Movers - 06","2007-07-20","2007-07-20"]
["UN362_0589","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 06","2007-07-23","2007-07-24"]
["UN362_0590","Install Undulators on Cradle- 06","2007-07-25","2007-07-25"]
["UN362_0591","Prealign Vacuum Chamber - 06","2007-07-26","2007-07-26"]
["UN362_0600","Undulator Cradle RFI - 06","2007-07-27","2007-07-26"]
["UN362_0610","REQD:  Undulator Mag Assy - 07","2006-08-29","2006-08-28"]
["UN362_0620","Adjust to Temperature - 07","2006-08-29","2006-09-12"]
["UN362_0630","Undulator Setup and Alignment @ Test Bench - 07","2006-11-13","2006-11-13"]
["UN362_0640","Undulator Measurement and Set Gap - 07","2006-11-14","2006-11-15"]
["UN362_0660","Undulator Measurement/Pre-fiducialization - 07","2006-11-16","2006-11-21"]
["UN362_0670","Undulator Setup and Alignment @ CMM - 07","2006-11-22","2006-11-22"]
["UN362_0680","Undulator Fiducialization - 07","2006-11-27","2006-11-28"]
["UN362_0685","Undulator Ready for Assembly - 07","2006-11-29","2006-12-05"]
["UN362_0687","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 07","2007-07-20","2007-07-19"]
["UN362_0688","Assemble Cradle/Quad Supt/Movers - 07","2007-07-20","2007-07-20"]
["UN362_0689","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 07","2007-07-23","2007-07-24"]
["UN362_0690","Install Undulators on Cradle- 07","2007-07-25","2007-07-25"]
["UN362_0691","Prealign Vacuum Chamber - 07","2007-07-26","2007-07-26"]
["UN362_0700","Undulator Cradle RFI - 07","2007-07-27","2007-07-26"]
["UN362_0710","REQD:  Undulator Mag Assy - 08","2006-09-28","2006-09-27"]
["UN362_0720","Adjust to Temperature - 08","2006-09-28","2006-10-11"]
["UN362_0730","Undulator Setup and Alignment @ Test Bench - 08","2006-11-22","2006-11-22"]
["UN362_0740","Undulator Measurement and Set Gap - 08","2006-11-27","2006-11-28"]
["UN362_0760","Undulator Measurement/Pre-fiducialization - 08","2006-11-29","2006-12-04"]
["UN362_0770","Undulator Setup and Alignment @ CMM - 08","2006-12-05","2006-12-05"]
["UN362_0780","Undulator Fiducialization - 08","2006-12-06","2006-12-07"]
["UN362_0785","Undulator Ready for Assembly - 08","2006-12-08","2006-12-14"]
["UN362_0787","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 08","2007-07-20","2007-07-19"]
["UN362_0788","Assemble Cradle/Quad Supt/Movers - 08","2007-07-20","2007-07-20"]
["UN362_0789","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 08","2007-07-23","2007-07-24"]
["UN362_0790","Install Undulators on Cradle- 08","2007-07-25","2007-07-25"]
["UN362_0791","Prealign Vacuum Chamber - 08","2007-07-26","2007-07-26"]
["UN362_0800","Undulator Cradle RFI - 08","2007-07-27","2007-07-26"]
["UN362_0810","REQD:  Undulator Mag Assy - 09","2006-09-14","2006-09-13"]
["UN362_0820","Adjust to Temperature - 09","2006-09-14","2006-09-27"]
["UN362_0830","Undulator Setup and Alignment @ Test Bench - 09","2006-12-05","2006-12-05"]
["UN362_0840","Undulator Measurement and Set Gap - 09","2006-12-06","2006-12-07"]
["UN362_0860","Undulator Measurement/Pre-fiducialization - 09","2006-12-08","2006-12-13"]
["UN362_0870","Undulator Setup and Alignment @ CMM - 09","2006-12-14","2006-12-14"]
["UN362_0880","Undulator Fiducialization - 09","2006-12-15","2007-01-02"]
["UN362_0885","Undulator Ready for Assembly - 09","2007-01-03","2007-01-09"]
["UN362_0887","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 09","2007-07-20","2007-07-19"]
["UN362_0888","Assemble Cradle/Quad Supt/Movers - 09","2007-07-20","2007-07-20"]
["UN362_0889","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 09","2007-07-23","2007-07-24"]
["UN362_0890","Install Undulators on Cradle- 09","2007-07-25","2007-07-25"]
["UN362_0891","Prealign Vacuum Chamber - 09","2007-07-26","2007-07-26"]
["UN362_0900","Undulator Cradle RFI - 09","2007-07-27","2007-07-26"]
["UN362_0910","REQD:  Undulator Mag Assy - 10","2006-10-13","2006-10-12"]
["UN362_0920","Adjust to Temperature - 10","2006-10-13","2006-10-26"]
["UN362_0930","Undulator Setup and Alignment @ Test Bench - 10","2006-12-14","2006-12-14"]
["UN362_0940","Undulator Measurement and Set Gap - 10","2006-12-15","2007-01-02"]
["UN362_0960","Undulator Measurement/Pre-fiducialization - 10","2007-01-03","2007-01-08"]
["UN362_0970","Undulator Setup and Alignment @ CMM - 10","2007-01-09","2007-01-09"]
["UN362_0980","Undulator Fiducialization - 10","2007-01-10","2007-01-11"]
["UN362_0985","Undulator Ready for Assembly - 10","2007-01-12","2007-01-19"]
["UN362_0987","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 10","2007-08-14","2007-08-13"]
["UN362_0988","Assemble Cradle/Quad Supt/Movers - 10","2007-08-14","2007-08-14"]
["UN362_0989","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 10","2007-08-15","2007-08-16"]
["UN362_0990","Install Undulators on Cradle- 10","2007-08-17","2007-08-17"]
["UN362_0991","Prealign Vacuum Chamber - 10","2007-08-20","2007-08-20"]
["UN362_1000","Undulator Cradle RFI - 10","2007-08-21","2007-08-20"]
["UN362_1010","REQD:  Undulator Mag Assy - 11","2006-09-29","2006-09-28"]
["UN362_1020","Adjust to Temperature - 11","2006-09-29","2006-10-12"]
["UN362_1030","Undulator Setup and Alignment @ Test Bench - 11","2007-01-09","2007-01-09"]
["UN362_1040","Undulator Measurement and Set Gap - 11","2007-01-10","2007-01-11"]
["UN362_1060","Undulator Measurement/Pre-fiducialization - 11","2007-01-12","2007-01-18"]
["UN362_1070","Undulator Setup and Alignment @ CMM - 11","2007-01-19","2007-01-19"]
["UN362_1080","Undulator Fiducialization - 11","2007-01-22","2007-01-23"]
["UN362_1085","Undulator Ready for Assembly - 11","2007-01-24","2007-01-30"]
["UN362_1087","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 11","2007-08-14","2007-08-13"]
["UN362_1088","Assemble Cradle/Quad Supt/Movers - 11","2007-08-14","2007-08-14"]
["UN362_1089","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 11","2007-08-15","2007-08-16"]
["UN362_1090","Install Undulators on Cradle- 11","2007-08-17","2007-08-17"]
["UN362_1091","Prealign Vacuum Chamber - 11","2007-08-20","2007-08-20"]
["UN362_1100","Undulator Cradle RFI - 11","2007-08-21","2007-08-20"]
["UN362_1110","REQD:  Undulator Mag Assy - 12","2006-10-30","2006-10-27"]
["UN362_1120","Adjust to Temperature - 12","2006-10-30","2006-11-10"]
["UN362_1130","Undulator Setup and Alignment @ Test Bench - 12","2007-01-19","2007-01-19"]
["UN362_1140","Undulator Measurement and Set Gap - 12","2007-01-22","2007-01-23"]
["UN362_1160","Undulator Measurement/Pre-fiducialization - 12","2007-01-24","2007-01-29"]
["UN362_1170","Undulator Setup and Alignment @ CMM - 12","2007-01-30","2007-01-30"]
["UN362_1180","Undulator Fiducialization - 12","2007-01-31","2007-02-01"]
["UN362_1185","Undulator Ready for Assembly - 12","2007-02-02","2007-02-08"]
["UN362_1187","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 12","2007-08-14","2007-08-13"]
["UN362_1188","Assemble Cradle/Quad Supt/Movers - 12","2007-08-14","2007-08-14"]
["UN362_1189","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 12","2007-08-15","2007-08-16"]
["UN362_1190","Install Undulators on Cradle- 12","2007-08-17","2007-08-17"]
["UN362_1191","Prealign Vacuum Chamber - 12","2007-08-20","2007-08-20"]
["UN362_1200","Undulator Cradle RFI - 12","2007-08-21","2007-08-20"]
["UN362_1210","REQD:  Undulator Mag Assy - 13","2006-10-16","2006-10-13"]
["UN362_1220","Adjust to Temperature - 13","2006-10-16","2006-10-27"]
["UN362_1230","Undulator Setup and Alignment @ Test Bench - 13","2007-01-30","2007-01-30"]
["UN362_1240","Undulator Measurement and Set Gap - 13","2007-01-31","2007-02-01"]
["UN362_1260","Undulator Measurement/Pre-fiducialization - 13","2007-02-02","2007-02-07"]
["UN362_1270","Undulator Setup and Alignment @ CMM - 13","2007-02-08","2007-02-08"]
["UN362_1280","Undulator Fiducialization - 13","2007-02-09","2007-02-12"]
["UN362_1285","Undulator Ready for Assembly - 13","2007-02-13","2007-02-20"]
["UN362_1287","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 13","2007-08-14","2007-08-13"]
["UN362_1288","Assemble Cradle/Quad Supt/Movers - 13","2007-08-14","2007-08-14"]
["UN362_1289","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 13","2007-08-15","2007-08-16"]
["UN362_1290","Install Undulators on Cradle- 13","2007-08-17","2007-08-17"]
["UN362_1291","Prealign Vacuum Chamber - 13","2007-08-20","2007-08-20"]
["UN362_1300","Undulator Cradle RFI - 13","2007-08-21","2007-08-20"]
["UN362_1310","REQD:  Undulator Mag Assy - 14","2006-11-14","2006-11-13"]
["UN362_1320","Adjust to Temperature - 14","2006-11-14","2006-11-29"]
["UN362_1330","Undulator Setup and Alignment @ Test Bench - 14","2007-02-08","2007-02-08"]
["UN362_1340","Undulator Measurement and Set Gap - 14","2007-02-09","2007-02-12"]
["UN362_1360","Undulator Measurement/Pre-fiducialization - 14","2007-02-13","2007-02-16"]
["UN362_1370","Undulator Setup and Alignment @ CMM - 14","2007-02-20","2007-02-20"]
["UN362_1380","Undulator Fiducialization - 14","2007-02-21","2007-02-22"]
["UN362_1385","Undulator Ready for Assembly - 14","2007-02-23","2007-03-01"]
["UN362_1387","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 14","2007-08-14","2007-08-13"]
["UN362_1388","Assemble Cradle/Quad Supt/Movers - 14","2007-08-14","2007-08-14"]
["UN362_1389","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 14","2007-08-15","2007-08-16"]
["UN362_1390","Install Undulators on Cradle- 14","2007-08-17","2007-08-17"]
["UN362_1391","Prealign Vacuum Chamber - 14","2007-08-20","2007-08-20"]
["UN362_1400","Undulator Cradle RFI - 14","2007-08-21","2007-08-20"]
["UN362_1410","REQD:  Undulator Mag Assy - 15","2006-10-31","2006-10-30"]
["UN362_1420","Adjust to Temperature - 15","2006-10-31","2006-11-13"]
["UN362_1430","Undulator Setup and Alignment @ Test Bench - 15","2007-02-20","2007-02-20"]
["UN362_1440","Undulator Measurement and Set Gap - 15","2007-02-21","2007-02-22"]
["UN362_1460","Undulator Measurement/Pre-fiducialization - 15","2007-02-23","2007-02-28"]
["UN362_1470","Undulator Setup and Alignment @ CMM - 15","2007-03-01","2007-03-01"]
["UN362_1480","Undulator Fiducialization - 15","2007-03-02","2007-03-05"]
["UN362_1485","Undulator Ready for Assembly - 15","2007-03-06","2007-03-12"]
["UN362_1487","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 15","2007-08-14","2007-08-13"]
["UN362_1488","Assemble Cradle/Quad Supt/Movers - 15","2007-08-14","2007-08-14"]
["UN362_1489","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 15","2007-08-15","2007-08-16"]
["UN362_1490","Install Undulators on Cradle- 15","2007-08-17","2007-08-17"]
["UN362_1491","Prealign Vacuum Chamber - 15","2007-08-20","2007-08-20"]
["UN362_1500","Undulator Cradle RFI - 15","2007-08-21","2007-08-20"]
["UN362_1510","REQD:  Undulator Mag Assy - 16","2006-12-01","2006-11-30"]
["UN362_1520","Adjust to Temperature - 16","2006-12-01","2006-12-14"]
["UN362_1530","Undulator Setup and Alignment @ Test Bench - 16","2007-03-01","2007-03-01"]
["UN362_1540","Undulator Measurement and Set Gap - 16","2007-03-02","2007-03-05"]
["UN362_1560","Undulator Measurement/Pre-fiducialization - 16","2007-03-06","2007-03-09"]
["UN362_1570","Undulator Setup and Alignment @ CMM - 16","2007-03-12","2007-03-12"]
["UN362_1580","Undulator Fiducialization - 16","2007-03-13","2007-03-14"]
["UN362_1585","Undulator Ready for Assembly - 16","2007-03-15","2007-03-21"]
["UN362_1587","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 16","2007-08-14","2007-08-13"]
["UN362_1588","Assemble Cradle/Quad Supt/Movers - 16","2007-08-14","2007-08-14"]
["UN362_1589","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 16","2007-08-15","2007-08-16"]
["UN362_1590","Install Undulators on Cradle- 16","2007-08-17","2007-08-17"]
["UN362_1591","Prealign Vacuum Chamber - 16","2007-08-20","2007-08-20"]
["UN362_1600","Undulator Cradle RFI - 16","2007-08-21","2007-08-20"]
["UN362_1610","REQD:  Undulator Mag Assy - 17","2006-11-15","2006-11-14"]
["UN362_1620","Adjust to Temperature - 17","2006-11-15","2006-11-30"]
["UN362_1630","Undulator Setup and Alignment @ Test Bench - 17","2007-03-12","2007-03-12"]
["UN362_1640","Undulator Measurement and Set Gap - 17","2007-03-13","2007-03-14"]
["UN362_1660","Undulator Measurement/Pre-fiducialization - 17","2007-03-15","2007-03-20"]
["UN362_1670","Undulator Setup and Alignment @ CMM - 17","2007-03-21","2007-03-21"]
["UN362_1680","Undulator Fiducialization - 17","2007-03-22","2007-03-23"]
["UN362_1685","Undulator Ready for Assembly - 17","2007-03-26","2007-03-30"]
["UN362_1687","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 17","2007-08-14","2007-08-13"]
["UN362_1688","Assemble Cradle/Quad Supt/Movers - 17","2007-08-14","2007-08-14"]
["UN362_1689","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 17","2007-08-15","2007-08-16"]
["UN362_1690","Install Undulators on Cradle- 17","2007-08-17","2007-08-17"]
["UN362_1691","Prealign Vacuum Chamber - 17","2007-08-20","2007-08-20"]
["UN362_1700","Undulator Cradle RFI - 17","2007-08-21","2007-08-20"]
["UN362_1710","REQD:  Undulator Mag Assy - 18","2007-01-02","2006-12-15"]
["UN362_1720","Adjust to Temperature - 18","2007-01-02","2007-01-16"]
["UN362_1730","Undulator Setup and Alignment @ Test Bench - 18","2007-03-21","2007-03-21"]
["UN362_1740","Undulator Measurement and Set Gap - 18","2007-03-22","2007-03-23"]
["UN362_1760","Undulator Measurement/Pre-fiducialization - 18","2007-03-26","2007-03-29"]
["UN362_1770","Undulator Setup and Alignment @ CMM - 18","2007-03-30","2007-03-30"]
["UN362_1780","Undulator Fiducialization - 18","2007-04-02","2007-04-03"]
["UN362_1785","Undulator Ready for Assembly - 18","2007-04-04","2007-04-10"]
["UN362_1787","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 18","2007-08-14","2007-08-13"]
["UN362_1788","Assemble Cradle/Quad Supt/Movers - 18","2007-08-14","2007-08-14"]
["UN362_1789","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 18","2007-08-15","2007-08-16"]
["UN362_1790","Install Undulators on Cradle- 18","2007-08-17","2007-08-17"]
["UN362_1791","Prealign Vacuum Chamber - 18","2007-08-20","2007-08-20"]
["UN362_1800","Undulator Cradle RFI - 18","2007-08-21","2007-08-20"]
["UN362_1910","REQD:  Undulator Mag Assy - 19","2006-12-11","2006-12-08"]
["UN362_1920","Adjust to Temperature - 19","2006-12-11","2007-01-08"]
["UN362_1930","Undulator Setup and Alignment @ Test Bench - 19","2007-03-30","2007-03-30"]
["UN362_1940","Undulator Measurement and Set Gap - 19","2007-04-02","2007-04-03"]
["UN362_1960","Undulator Measurement/Pre-fiducialization - 19","2007-04-04","2007-04-09"]
["UN362_1970","Undulator Setup and Alignment @ CMM - 19","2007-04-10","2007-04-10"]
["UN362_1980","Undulator Fiducialization - 19","2007-04-11","2007-04-12"]
["UN362_1985","Undulator Ready for Assembly - 19","2007-04-13","2007-04-19"]
["UN362_1987","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 19","2007-08-14","2007-08-13"]
["UN362_1988","Assemble Cradle/Quad Supt/Movers - 19","2007-08-14","2007-08-14"]
["UN362_1989","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 19","2007-08-15","2007-08-16"]
["UN362_1990","Install Undulators on Cradle- 19","2007-08-17","2007-08-17"]
["UN362_1991","Prealign Vacuum Chamber - 19","2007-08-20","2007-08-20"]
["UN362_2000","Undulator Cradle RFI - 19","2007-08-21","2007-08-20"]
["UN362_2010","REQD:  Undulator Mag Assy - 20","2007-01-11","2007-01-10"]
["UN362_2020","Adjust to Temperature - 20","2007-01-11","2007-01-25"]
["UN362_2030","Undulator Setup and Alignment @ Test Bench - 20","2007-04-10","2007-04-10"]
["UN362_2040","Undulator Measurement and Set Gap - 20","2007-04-11","2007-04-12"]
["UN362_2060","Undulator Measurement/Pre-fiducialization - 20","2007-04-13","2007-04-18"]
["UN362_2070","Undulator Setup and Alignment @ CMM - 20","2007-04-19","2007-04-19"]
["UN362_2080","Undulator Fiducialization - 20","2007-04-20","2007-04-23"]
["UN362_2085","Undulator Ready for Assembly - 20","2007-04-24","2007-04-30"]
["UN362_2087","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 20","2007-10-10","2007-10-09"]
["UN362_2088","Assemble Cradle/Quad Supt/Movers - 20","2007-10-10","2007-10-10"]
["UN362_2089","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 20","2007-10-11","2007-10-12"]
["UN362_2090","Install Undulators on Cradle- 20","2007-10-15","2007-10-15"]
["UN362_2091","Prealign Vacuum Chamber - 20","2007-10-16","2007-10-16"]
["UN362_2100","Undulator Cradle RFI - 20","2007-10-17","2007-10-16"]
["UN362_2110","REQD:  Undulator Mag Assy - 21","2007-01-04","2007-01-03"]
["UN362_2120","Adjust to Temperature - 21","2007-01-04","2007-01-18"]
["UN362_2130","Undulator Setup and Alignment @ Test Bench - 21","2007-04-19","2007-04-19"]
["UN362_2140","Undulator Measurement and Set Gap - 21","2007-04-20","2007-04-23"]
["UN362_2160","Undulator Measurement/Pre-fiducialization - 21","2007-04-24","2007-04-27"]
["UN362_2170","Undulator Setup and Alignment @ CMM - 21","2007-04-30","2007-04-30"]
["UN362_2180","Undulator Fiducialization - 21","2007-05-01","2007-05-02"]
["UN362_2185","Undulator Ready for Assembly - 21","2007-05-03","2007-05-09"]
["UN362_2187","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 21","2007-10-10","2007-10-09"]
["UN362_2188","Assemble Cradle/Quad Supt/Movers - 21","2007-10-10","2007-10-10"]
["UN362_2189","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 21","2007-10-11","2007-10-12"]
["UN362_2190","Install Undulators on Cradle- 21","2007-10-15","2007-10-15"]
["UN362_2191","Prealign Vacuum Chamber - 21","2007-10-16","2007-10-16"]
["UN362_2200","Undulator Cradle RFI - 21","2007-10-17","2007-10-16"]
["UN362_2210","REQD:  Undulator Mag Assy - 22","2007-01-26","2007-01-25"]
["UN362_2220","Adjust to Temperature - 22","2007-01-26","2007-02-08"]
["UN362_2230","Undulator Setup and Alignment @ Test Bench - 22","2007-04-30","2007-04-30"]
["UN362_2240","Undulator Measurement and Set Gap - 22","2007-05-01","2007-05-02"]
["UN362_2260","Undulator Measurement/Pre-fiducialization - 22","2007-05-03","2007-05-08"]
["UN362_2270","Undulator Setup and Alignment @ CMM - 22","2007-05-09","2007-05-09"]
["UN362_2280","Undulator Fiducialization - 22","2007-05-10","2007-05-11"]
["UN362_2285","Undulator Ready for Assembly - 22","2007-05-14","2007-05-18"]
["UN362_2287","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 22","2007-10-10","2007-10-09"]
["UN362_2288","Assemble Cradle/Quad Supt/Movers - 22","2007-10-10","2007-10-10"]
["UN362_2289","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 22","2007-10-11","2007-10-12"]
["UN362_2290","Install Undulators on Cradle- 22","2007-10-15","2007-10-15"]
["UN362_2291","Prealign Vacuum Chamber - 22","2007-10-16","2007-10-16"]
["UN362_2300","Undulator Cradle RFI - 22","2007-10-17","2007-10-16"]
["UN362_2310","REQD:  Undulator Mag Assy - 23","2007-01-19","2007-01-18"]
["UN362_2320","Adjust to Temperature - 23","2007-01-19","2007-02-01"]
["UN362_2330","Undulator Setup and Alignment @ Test Bench - 23","2007-05-09","2007-05-09"]
["UN362_2340","Undulator Measurement and Set Gap - 23","2007-05-10","2007-05-11"]
["UN362_2360","Undulator Measurement/Pre-fiducialization - 23","2007-05-14","2007-05-17"]
["UN362_2370","Undulator Setup and Alignment @ CMM - 23","2007-05-18","2007-05-18"]
["UN362_2380","Undulator Fiducialization - 23","2007-05-21","2007-05-22"]
["UN362_2385","Undulator Ready for Assembly - 23","2007-05-23","2007-05-30"]
["UN362_2387","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 23","2007-10-10","2007-10-09"]
["UN362_2388","Assemble Cradle/Quad Supt/Movers - 23","2007-10-10","2007-10-10"]
["UN362_2389","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 23","2007-10-11","2007-10-12"]
["UN362_2390","Install Undulators on Cradle- 23","2007-10-15","2007-10-15"]
["UN362_2391","Prealign Vacuum Chamber - 23","2007-10-16","2007-10-16"]
["UN362_2400","Undulator Cradle RFI - 23","2007-10-17","2007-10-16"]
["UN362_2410","REQD:  Undulator Mag Assy - 24","2007-02-12","2007-02-09"]
["UN362_2420","Adjust to Temperature - 24","2007-02-12","2007-02-26"]
["UN362_2430","Undulator Setup and Alignment @ Test Bench - 24","2007-05-18","2007-05-18"]
["UN362_2440","Undulator Measurement and Set Gap - 24","2007-05-21","2007-05-22"]
["UN362_2460","Undulator Measurement/Pre-fiducialization - 24","2007-05-23","2007-05-29"]
["UN362_2470","Undulator Setup and Alignment @ CMM - 24","2007-05-30","2007-05-30"]
["UN362_2480","Undulator Fiducialization - 24","2007-05-31","2007-06-01"]
["UN362_2485","Undulator Ready for Assembly - 24","2007-06-04","2007-06-08"]
["UN362_2487","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 24","2007-11-07","2007-11-06"]
["UN362_2488","Assemble Cradle/Quad Supt/Movers - 24","2007-11-07","2007-11-07"]
["UN362_2489","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 24","2007-11-08","2007-11-09"]
["UN362_2490","Install Undulators on Cradle- 24","2007-11-12","2007-11-12"]
["UN362_2491","Prealign Vacuum Chamber - 24","2007-11-13","2007-11-13"]
["UN362_2500","Undulator Cradle RFI - 24","2007-11-14","2007-11-13"]
["UN362_2510","REQD:  Undulator Mag Assy - 25","2007-02-05","2007-02-02"]
["UN362_2520","Adjust to Temperature - 25","2007-02-05","2007-02-16"]
["UN362_2530","Undulator Setup and Alignment @ Test Bench - 25","2007-05-30","2007-05-30"]
["UN362_2540","Undulator Measurement and Set Gap - 25","2007-05-31","2007-06-01"]
["UN362_2560","Undulator Measurement/Pre-fiducialization - 25","2007-06-04","2007-06-07"]
["UN362_2570","Undulator Setup and Alignment @ CMM - 25","2007-06-08","2007-06-08"]
["UN362_2580","Undulator Fiducialization - 25","2007-06-11","2007-06-12"]
["UN362_2585","Undulator Ready for Assembly - 25","2007-06-13","2007-06-19"]
["UN362_2587","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 25","2007-11-07","2007-11-06"]
["UN362_2588","Assemble Cradle/Quad Supt/Movers - 25","2007-11-07","2007-11-07"]
["UN362_2589","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 25","2007-11-08","2007-11-09"]
["UN362_2590","Install Undulators on Cradle- 25","2007-11-12","2007-11-12"]
["UN362_2591","Prealign Vacuum Chamber - 25","2007-11-13","2007-11-13"]
["UN362_2600","Undulator Cradle RFI - 25","2007-11-14","2007-11-13"]
["UN362_2610","REQD:  Undulator Mag Assy - 26","2007-02-27","2007-02-26"]
["UN362_2620","Adjust to Temperature - 26","2007-02-27","2007-03-12"]
["UN362_2630","Undulator Setup and Alignment @ Test Bench - 26","2007-06-08","2007-06-08"]
["UN362_2640","Undulator Measurement and Set Gap - 26","2007-06-11","2007-06-12"]
["UN362_2660","Undulator Measurement/Pre-fiducialization - 26","2007-06-13","2007-06-18"]
["UN362_2670","Undulator Setup and Alignment @ CMM - 26","2007-06-19","2007-06-19"]
["UN362_2680","Undulator Fiducialization - 26","2007-06-20","2007-06-21"]
["UN362_2685","Undulator Ready for Assembly - 26","2007-06-22","2007-06-28"]
["UN362_2687","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 26","2007-11-07","2007-11-06"]
["UN362_2688","Assemble Cradle/Quad Supt/Movers - 26","2007-11-07","2007-11-07"]
["UN362_2689","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 26","2007-11-08","2007-11-09"]
["UN362_2690","Install Undulators on Cradle- 26","2007-11-12","2007-11-12"]
["UN362_2691","Prealign Vacuum Chamber - 26","2007-11-13","2007-11-13"]
["UN362_2700","Undulator Cradle RFI - 26","2007-11-14","2007-11-13"]
["UN362_2710","REQD:  Undulator Mag Assy - 27","2007-02-20","2007-02-16"]
["UN362_2720","Adjust to Temperature - 27","2007-02-20","2007-03-05"]
["UN362_2730","Undulator Setup and Alignment @ Test Bench - 27","2007-06-19","2007-06-19"]
["UN362_2740","Undulator Measurement and Set Gap - 27","2007-06-20","2007-06-21"]
["UN362_2760","Undulator Measurement/Pre-fiducialization - 27","2007-06-22","2007-06-27"]
["UN362_2770","Undulator Setup and Alignment @ CMM - 27","2007-06-28","2007-06-28"]
["UN362_2780","Undulator Fiducialization - 27","2007-06-29","2007-07-02"]
["UN362_2785","Undulator Ready for Assembly - 27","2007-07-03","2007-07-10"]
["UN362_2787","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 27","2007-12-07","2007-12-06"]
["UN362_2788","Assemble Cradle/Quad Supt/Movers - 27","2007-12-07","2007-12-07"]
["UN362_2789","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 27","2007-12-10","2007-12-11"]
["UN362_2790","Install Undulators on Cradle- 27","2007-12-12","2007-12-12"]
["UN362_2791","Prealign Vacuum Chamber - 27","2007-12-13","2007-12-13"]
["UN362_2800","Undulator Cradle RFI - 27","2007-12-14","2007-12-13"]
["UN362_2810","REQD:  Undulator Mag Assy - 28","2007-03-14","2007-03-13"]
["UN362_2820","Adjust to Temperature - 28","2007-03-14","2007-03-27"]
["UN362_2830","Undulator Setup and Alignment @ Test Bench - 28","2007-06-28","2007-06-28"]
["UN362_2840","Undulator Measurement and Set Gap - 28","2007-06-29","2007-07-02"]
["UN362_2860","Undulator Measurement/Pre-fiducialization - 28","2007-07-03","2007-07-09"]
["UN362_2870","Undulator Setup and Alignment @ CMM - 28","2007-07-10","2007-07-10"]
["UN362_2880","Undulator Fiducialization - 28","2007-07-11","2007-07-12"]
["UN362_2885","Undulator Ready for Assembly - 28","2007-07-13","2007-07-19"]
["UN362_2887","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 28","2007-12-07","2007-12-06"]
["UN362_2888","Assemble Cradle/Quad Supt/Movers - 28","2007-12-07","2007-12-07"]
["UN362_2889","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 28","2007-12-10","2007-12-11"]
["UN362_2890","Install Undulators on Cradle- 28","2007-12-12","2007-12-12"]
["UN362_2891","Prealign Vacuum Chamber - 28","2007-12-13","2007-12-13"]
["UN362_2900","Undulator Cradle RFI - 28","2007-12-14","2007-12-13"]
["UN362_2910","REQD:  Undulator Mag Assy - 29","2007-03-07","2007-03-06"]
["UN362_2920","Adjust to Temperature - 29","2007-03-07","2007-03-20"]
["UN362_2930","Undulator Setup and Alignment @ Test Bench - 29","2007-07-10","2007-07-10"]
["UN362_2940","Undulator Measurement and Set Gap - 29","2007-07-11","2007-07-12"]
["UN362_2960","Undulator Measurement/Pre-fiducialization - 29","2007-07-13","2007-07-18"]
["UN362_2970","Undulator Setup and Alignment @ CMM - 29","2007-07-19","2007-07-19"]
["UN362_2980","Undulator Fiducialization - 29","2007-07-20","2007-07-23"]
["UN362_2985","Undulator Ready for Assembly - 29","2007-07-24","2007-07-30"]
["UN362_2987","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 29","2008-01-15","2008-01-14"]
["UN362_2988","Assemble Cradle/Quad Supt/Movers - 29","2008-01-15","2008-01-15"]
["UN362_2989","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 29","2008-01-16","2008-01-17"]
["UN362_2990","Install Undulators on Cradle- 29","2008-01-18","2008-01-18"]
["UN362_2991","Prealign Vacuum Chamber - 29","2008-01-22","2008-01-22"]
["UN362_3000","Undulator Cradle RFI - 29","2008-01-23","2008-01-22"]
["UN362_3010","REQD:  Undulator Mag Assy - 30","2007-03-29","2007-03-28"]
["UN362_3020","Adjust to Temperature - 30","2007-03-29","2007-04-11"]
["UN362_3030","Undulator Setup and Alignment @ Test Bench - 30","2007-07-19","2007-07-19"]
["UN362_3040","Undulator Measurement and Set Gap - 30","2007-07-20","2007-07-23"]
["UN362_3060","Undulator Measurement/Pre-fiducialization - 30","2007-07-24","2007-07-27"]
["UN362_3070","Undulator Setup and Alignment @ CMM - 30","2007-07-30","2007-07-30"]
["UN362_3080","Undulator Fiducialization - 30","2007-07-31","2007-08-01"]
["UN362_3085","Undulator Ready for Assembly - 30","2007-08-02","2007-08-08"]
["UN362_3087","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 30","2008-01-15","2008-01-14"]
["UN362_3088","Assemble Cradle/Quad Supt/Movers - 30","2008-01-15","2008-01-15"]
["UN362_3089","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 30","2008-01-16","2008-01-17"]
["UN362_3090","Install Undulators on Cradle- 30","2008-01-18","2008-01-18"]
["UN362_3091","Prealign Vacuum Chamber - 30","2008-01-22","2008-01-22"]
["UN362_3100","Undulator Cradle RFI - 30","2008-01-23","2008-01-22"]
["UN362_3110","REQD:  Undulator Mag Assy - 31","2007-04-04","2007-04-03"]
["UN362_3120","Adjust to Temperature - 31","2007-04-04","2007-04-17"]
["UN362_3130","Undulator Setup and Alignment @ Test Bench - 31","2007-07-30","2007-07-30"]
["UN362_3140","Undulator Measurement and Set Gap - 31","2007-07-31","2007-08-01"]
["UN362_3160","Undulator Measurement/Pre-fiducialization - 31","2007-08-02","2007-08-07"]
["UN362_3170","Undulator Setup and Alignment @ CMM - 31","2007-08-08","2007-08-08"]
["UN362_3180","Undulator Fiducialization - 31","2007-08-09","2007-08-10"]
["UN362_3185","Undulator Ready for Assembly - 31","2007-08-13","2007-08-17"]
["UN362_3187","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 31","2008-01-15","2008-01-14"]
["UN362_3188","Assemble Cradle/Quad Supt/Movers - 31","2008-01-15","2008-01-15"]
["UN362_3189","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 31","2008-01-16","2008-01-17"]
["UN362_3190","Install Undulators on Cradle- 31","2008-01-18","2008-01-18"]
["UN362_3191","Prealign Vacuum Chamber - 31","2008-01-22","2008-01-22"]
["UN362_3200","Undulator Cradle RFI - 31","2008-01-23","2008-01-22"]
["UN362_3210","REQD:  Undulator Mag Assy - 32","2007-04-13","2007-04-12"]
["UN362_3220","Adjust to Temperature - 32","2007-04-13","2007-04-26"]
["UN362_3230","Undulator Setup and Alignment @ Test Bench - 32","2007-08-08","2007-08-08"]
["UN362_3240","Undulator Measurement and Set Gap - 32","2007-08-09","2007-08-10"]
["UN362_3260","Undulator Measurement/Pre-fiducialization - 32","2007-08-13","2007-08-16"]
["UN362_3270","Undulator Setup and Alignment @ CMM - 32","2007-08-17","2007-08-17"]
["UN362_3280","Undulator Fiducialization - 32","2007-08-20","2007-08-21"]
["UN362_3285","Undulator Ready for Assembly - 32","2007-08-22","2007-08-28"]
["UN362_3287","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 32","2008-01-16","2008-01-15"]
["UN362_3288","Assemble Cradle/Quad Supt/Movers - 32","2008-01-16","2008-01-16"]
["UN362_3289","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 32","2008-01-17","2008-01-18"]
["UN362_3290","Install Undulators on Cradle- 32","2008-01-22","2008-01-22"]
["UN362_3291","Prealign Vacuum Chamber - 32","2008-01-23","2008-01-23"]
["UN362_3300","Undulator Cradle RFI - 32","2008-01-24","2008-01-23"]
["UN362_3306","HLS Systems Design-Part II","2005-07-01","2005-09-29"]
["UN362_3310","REQD:  Undulator Mag Assy - 33","2007-05-03","2007-05-02"]
["UN362_3320","Adjust to Temperature - 33","2007-05-03","2007-05-16"]
["UN362_3330","Undulator Setup and Alignment @ Test Bench - 33","2007-08-17","2007-08-17"]
["UN362_3340","Undulator Measurement and Set Gap - 33","2007-08-20","2007-08-21"]
["UN362_3360","Undulator Measurement/Pre-fiducialization - 33","2007-08-22","2007-08-27"]
["UN362_3370","Undulator Setup and Alignment @ CMM - 33","2007-08-28","2007-08-28"]
["UN362_3380","Undulator Fiducialization - 33","2007-08-29","2007-08-30"]
["UN362_3385","Undulator Ready for Assembly - 33","2007-08-31","2007-09-07"]
["UN362_3387","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 33","2008-01-16","2008-01-15"]
["UN362_3388","Assemble Cradle/Quad Supt/Movers - 33","2008-01-16","2008-01-16"]
["UN362_3389","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 33","2008-01-17","2008-01-18"]
["UN362_3390","Install Undulators on Cradle- 33","2008-01-22","2008-01-22"]
["UN362_3391","Prealign Vacuum Chamber - 33","2008-01-23","2008-01-23"]
["UN362_3400","Undulator Cradle RFI - 33","2008-01-24","2008-01-23"]
["UN362_3410","REQD:  Undulator Mag Assy - 34","2007-04-30","2007-04-27"]
["UN362_3420","Adjust to Temperature - 34","2007-04-30","2007-05-11"]
["UN362_3430","Undulator Setup and Alignment @ Test Bench - 34","2007-08-28","2007-08-28"]
["UN362_3440","Undulator Measurement and Set Gap - 34","2007-08-29","2007-08-30"]
["UN362_3460","Undulator Measurement/Pre-fiducialization - 34","2007-08-31","2007-09-06"]
["UN362_3470","Undulator Setup and Alignment @ CMM - 34","2007-09-07","2007-09-07"]
["UN362_3480","Undulator Fiducialization - 34","2007-09-10","2007-09-11"]
["UN362_3485","Undulator Ready for Assembly - 34","2007-09-12","2007-09-18"]
["UN362_3487","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 34","2008-10-07","2008-10-06"]
["UN362_3488","Assemble Cradle/Quad Supt/Movers - 34","2008-10-07","2008-10-07"]
["UN362_3489","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 34","2008-10-08","2008-10-09"]
["UN362_3490","Install Undulators on Cradle- 34","2008-10-10","2008-10-10"]
["UN362_3491","Prealign Vacuum Chamber - 34","2008-10-13","2008-10-13"]
["UN362_3500","Undulator Cradle RFI - 34","2008-10-14","2008-10-13"]
["UN362_3510","REQD:  Undulator Mag Assy - 35","2007-05-18","2007-05-17"]
["UN362_3520","Adjust to Temperature - 35","2007-05-18","2007-06-01"]
["UN362_3530","Undulator Setup and Alignment @ Test Bench - 35","2007-09-07","2007-09-07"]
["UN362_3540","Undulator Measurement and Set Gap - 35","2007-09-10","2007-09-11"]
["UN362_3560","Undulator Measurement/Pre-fiducialization - 35","2007-09-12","2007-09-17"]
["UN362_3570","Undulator Setup and Alignment @ CMM - 35","2007-09-18","2007-09-18"]
["UN362_3580","Undulator Fiducialization - 35","2007-09-19","2007-09-20"]
["UN362_3585","Undulator Ready for Assembly - 35","2007-09-21","2007-09-27"]
["UN362_3587","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 35","2008-10-09","2008-10-08"]
["UN362_3588","Assemble Cradle/Quad Supt/Movers - 35","2008-10-09","2008-10-09"]
["UN362_3589","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 35","2008-10-10","2008-10-13"]
["UN362_3590","Install Undulators on Cradle- 35","2008-10-14","2008-10-14"]
["UN362_3591","Prealign Vacuum Chamber - 35","2008-10-15","2008-10-15"]
["UN362_3600","Undulator Cradle RFI - 35","2008-10-16","2008-10-15"]
["UN362_3610","REQD:  Undulator Mag Assy - 36","2007-05-15","2007-05-14"]
["UN362_3620","Adjust to Temperature - 36","2007-05-15","2007-05-29"]
["UN362_3630","Undulator Setup and Alignment @ Test Bench - 36","2007-09-18","2007-09-18"]
["UN362_3640","Undulator Measurement and Set Gap - 36","2007-09-19","2007-09-20"]
["UN362_3660","Undulator Measurement/Pre-fiducialization - 36","2007-09-21","2007-09-26"]
["UN362_3670","Undulator Setup and Alignment @ CMM - 36","2007-09-27","2007-09-27"]
["UN362_3680","Undulator Fiducialization - 36","2007-09-28","2007-10-01"]
["UN362_3685","Undulator Ready for Assembly - 36","2007-10-02","2007-10-08"]
["UN362_3687","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 36","2008-10-13","2008-10-10"]
["UN362_3688","Assemble Cradle/Quad Supt/Movers - 36","2008-10-13","2008-10-13"]
["UN362_3689","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 36","2008-10-14","2008-10-15"]
["UN362_3690","Install Undulators on Cradle- 36","2008-10-16","2008-10-16"]
["UN362_3691","Prealign Vacuum Chamber - 36","2008-10-17","2008-10-17"]
["UN362_3700","Undulator Cradle RFI - 36","2008-10-20","2008-10-17"]
["UN362_3710","REQD:  Undulator Mag Assy - 37","2007-06-05","2007-06-04"]
["UN362_3720","Adjust to Temperature - 37","2007-06-05","2007-06-18"]
["UN362_3730","Undulator Setup and Alignment @ Test Bench - 37","2007-09-27","2007-09-27"]
["UN362_3740","Undulator Measurement and Set Gap - 37","2007-09-28","2007-10-01"]
["UN362_3760","Undulator Measurement/Pre-fiducialization - 37","2007-10-02","2007-10-05"]
["UN362_3770","Undulator Setup and Alignment @ CMM - 37","2007-10-08","2007-10-08"]
["UN362_3780","Undulator Fiducialization - 37","2007-10-09","2007-10-10"]
["UN362_3785","Undulator Ready for Assembly - 37","2007-10-11","2007-10-17"]
["UN362_3787","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 37","2008-10-15","2008-10-14"]
["UN362_3788","Assemble Cradle/Quad Supt/Movers - 37","2008-10-15","2008-10-15"]
["UN362_3789","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 37","2008-10-16","2008-10-17"]
["UN362_3790","Install Undulators on Cradle- 37","2008-10-20","2008-10-20"]
["UN362_3791","Prealign Vacuum Chamber - 37","2008-10-21","2008-10-21"]
["UN362_3800","Undulator Cradle RFI - 37","2008-10-22","2008-10-21"]
["UN362_3810","REQD:  Undulator Mag Assy - 38","2007-07-25","2007-07-24"]
["UN362_3820","Adjust to Temperature - 38","2007-07-25","2007-08-07"]
["UN362_3830","Undulator Setup and Alignment @ Test Bench - 38","2007-10-08","2007-10-08"]
["UN362_3840","Undulator Measurement and Set Gap - 38","2007-10-09","2007-10-10"]
["UN362_3860","Undulator Measurement/Pre-fiducialization - 38","2007-10-11","2007-10-16"]
["UN362_3870","Undulator Setup and Alignment @ CMM - 38","2007-10-17","2007-10-17"]
["UN362_3880","Undulator Fiducialization - 38","2007-10-18","2007-10-19"]
["UN362_3885","Undulator Ready for Assembly - 38","2007-10-22","2007-10-26"]
["UN362_3887","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 38","2008-10-17","2008-10-16"]
["UN362_3888","Assemble Cradle/Quad Supt/Movers - 38","2008-10-17","2008-10-17"]
["UN362_3889","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 38","2008-10-20","2008-10-21"]
["UN362_3890","Install Undulators on Cradle- 38","2008-10-22","2008-10-22"]
["UN362_3891","Prealign Vacuum Chamber - 38","2008-10-23","2008-10-23"]
["UN362_3900","Undulator Cradle RFI - 38","2008-10-24","2008-10-23"]
["UN362_3910","REQD:  Undulator Mag Assy - 39","2007-06-20","2007-06-19"]
["UN362_3920","Adjust to Temperature - 39","2007-06-20","2007-07-03"]
["UN362_3930","Undulator Setup and Alignment @ Test Bench - 39","2007-10-17","2007-10-17"]
["UN362_3940","Undulator Measurement and Set Gap - 39","2007-10-18","2007-10-19"]
["UN362_3960","Undulator Measurement/Pre-fiducialization - 39","2007-10-22","2007-10-25"]
["UN362_3970","Undulator Setup and Alignment @ CMM - 39","2007-10-26","2007-10-26"]
["UN362_3980","Undulator Fiducialization - 39","2007-10-29","2007-10-30"]
["UN362_3985","Undulator Ready for Assembly - 39","2007-10-31","2007-11-06"]
["UN362_3987","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 39","2008-10-21","2008-10-20"]
["UN362_3988","Assemble Cradle/Quad Supt/Movers - 39","2008-10-21","2008-10-21"]
["UN362_3989","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 39","2008-10-22","2008-10-23"]
["UN362_3990","Install Undulators on Cradle- 39","2008-10-24","2008-10-24"]
["UN362_3991","Prealign Vacuum Chamber - 39","2008-10-27","2008-10-27"]
["UN362_4000","Undulator Cradle RFI - 39","2008-10-28","2008-10-27"]
["UN362_4010","REQD:  Undulator Mag Assy - 40","2007-08-09","2007-08-08"]
["UN362_4020","Adjust to Temperature - 40","2007-08-09","2007-08-22"]
["UN362_4030","Undulator Setup and Alignment @ Test Bench - 40","2007-10-26","2007-10-26"]
["UN362_4040","Undulator Measurement and Set Gap - 40","2007-10-29","2007-10-30"]
["UN362_4060","Undulator Measurement/Pre-fiducialization - 40","2007-10-31","2007-11-05"]
["UN362_4070","Undulator Setup and Alignment @ CMM - 40","2007-11-06","2007-11-06"]
["UN362_4080","Undulator Fiducialization - 40","2007-11-07","2007-11-08"]
["UN362_4085","Undulator Ready for Assembly - 40","2007-11-09","2007-11-15"]
["UN362_4087","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 40","2008-10-23","2008-10-22"]
["UN362_4088","Assemble Cradle/Quad Supt/Movers - 40","2008-10-23","2008-10-23"]
["UN362_4089","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 40","2008-10-24","2008-10-27"]
["UN362_4090","Install Undulators on Cradle- 40","2008-10-28","2008-10-28"]
["UN362_4091","Prealign Vacuum Chamber - 40","2008-10-29","2008-10-29"]
["UN362_4100","Undulator Cradle RFI - 40","2008-10-30","2008-10-29"]
["UN36_00010","Design Quad Fidcuialization System","2005-05-02","2005-06-30"]
["UN36_00011","Revise Design for Electro Magnets","2005-06-01","2005-09-30"]
["UN36_00020","Procure Quad Fiducialization System","2005-05-02","2005-05-31"]
["UN36_00021","Procure Hardware for Electro Magnets","2005-07-01","2005-09-30"]
["UN36_00022","Develop System Software","2005-06-01","2006-06-01"]
["UN36_00023","Fabricate Hardware","2005-06-01","2006-06-01"]
["UN36_00030","Install and Test Quad Fiducialization System","2006-04-04","2006-05-01"]
["UN36_00032","Commission Quad Fiducialization System","2006-01-03","2006-02-28"]
["UN36_00040","Quad Fiducialization System Complete","2006-05-02","2006-05-01"]
["UN36_00050","Design Undulator Fiducialization System","2005-05-02","2005-08-30"]
["UN36_00051","Develop Fiducialization Fixture","2005-05-02","2005-08-31"]
["UN36_00052","Release RFP - Undulator Fiducialization System","2005-05-02","2005-05-02"]
["UN36_00053","Prototype Fiducialization Fixture","2005-05-02","2005-08-31"]
["UN36_00054","Vendor Prep Prop - Undulator Fiducialization Sys","2005-05-03","2005-06-17"]
["UN36_00055","Develop System Software","2005-06-01","2006-06-01"]
["UN36_00056","AWARD: Undulator Fiducialization System","2005-06-20","2005-06-20"]
["UN36_00060","Procure Undulator Fiducialization System","2005-06-21","2006-01-06"]
["UN36_00062","RCV: Undulator Fiducialization System","2006-01-09","2006-01-06"]
["UN36_00070","Install and Test Undulator Fiducialization Sys","2006-04-04","2006-05-01"]
["UN36_00080","Undulator Fiducialization System Complete","2006-05-02","2006-05-01"]
["UN36_00090","Design Quad Strength and Field Quality","2005-05-02","2005-05-31"]
["UN36_00091","Revise Design for Electro Magnets","2005-06-01","2005-08-30"]
["UN36_00092","Develop System Software","2005-06-01","2006-06-01"]
["UN36_00100","Procure Quad Strength and Field Quality","2005-06-01","2005-08-30"]
["UN36_00101","Procure Hardware for Electro Magnets","2005-07-01","2005-08-30"]
["UN36_00102","Fabricate Hardware","2005-06-01","2006-06-01"]
["UN36_00110","Install and Test Quad Strength and Field Quality","2006-04-04","2006-05-01"]
["UN36_00112","Commission Quad Strength and Field System","2006-01-03","2006-02-28"]
["UN36_00120","Quad Strength and Field Quality Complete","2006-05-02","2006-05-01"]
["UN36_00136","AWARD: Undulator Test Stand","2005-05-31","2005-05-31"]
["UN36_00140","Procure Undulator Test Stand","2005-06-01","2006-04-28"]
["UN36_00141","Design Undulator Supports and Movers","2005-05-02","2005-09-30"]
["UN36_00142","RCV: Undulator Test Stand","2006-05-01","2006-04-28"]
["UN36_00143","Procure Undulator Supports and Movers","2005-06-01","2005-08-30"]
["UN36_00145","Develop System Software","2005-06-01","2006-06-01"]
["UN36_00146","Develop Temperature System","2005-06-01","2006-06-01"]
["UN36_00150","Install and Test Undulator Test Stand","2006-05-26","2006-06-23"]
["UN36_00160","Undulator Test Stand Complete","2006-06-26","2006-06-23"]
["UN36_00170","Design Hall Probe Calibration System","2005-05-02","2005-08-30"]
["UN36_00180","Procure Hall Probe Calibration System","2005-05-06","2005-08-01"]
["UN36_00190","Install and Test Hall Probe Calibration System","2006-04-04","2006-05-01"]
["UN36_00191","Commission Hall Probe Calibration System","2006-05-02","2006-05-26"]
["UN36_00192","Develop System Software","2005-06-01","2006-06-01"]
["UN36_00193","Fabricate Hardware","2005-06-01","2006-06-01"]
["UN36_00200","Hall Probe Calibration System Complete","2006-05-30","2006-05-26"]
["UN36_00210","Design Undulator Test Stand Proto","2005-05-02","2005-05-31"]
["UN36_00220","Procure Undulator Test Stand Proto","2005-06-01","2005-08-30"]
["UN36_00221","Procure Undulator Supports and Movers","2005-05-02","2005-11-15"]
["UN36_00230","Install and Test Undulator Test Stand Proto","2006-07-03","2006-07-28"]
["UN36_00240","Undulator Test Stand Proto Complete","2006-07-31","2006-07-28"]
["UN36_00250","Design Undulator Handling","2005-06-01","2005-09-30"]
["UN36_00251","Adapt Design for Cradle Concept","2005-09-01","2005-09-30"]
["UN36_00260","Procure Undulator Handling","2005-10-03","2005-12-16"]
["UN36_00265","Procure Forklift","2005-07-05","2005-09-27"]
["UN36_00270","Install and Test Undulator Handling","2006-04-04","2006-05-30"]
["UN36_00280","Undulator Handling Complete","2006-05-31","2006-05-30"]
["UN36_00290","MMF Ready to Magnetic Measure/Fiducialize","2006-07-31","2006-07-28"]
["UN36_00370","Procure Fiducialization and Mag Meas Hardware","2006-05-01","2006-07-25"]
["UN36_00390","Fiducialization Measurements - BPM","2006-07-31","2007-02-02"]
["UN36_00400","Data Evaluation - BPM","2006-07-31","2007-02-02"]
["UN36_00510","Data Evaluation - Correctors","2006-07-31","2007-02-02"]
["UN36_00550","Magnetic Measurements - Correctors","2006-07-31","2007-02-02"]
["UN36_00560","Fiducialization Measurements - Vacuum Chamber","2006-07-31","2007-02-02"]
["UN36_00570","Data Evaluation - Vacuum Chamber","2006-07-31","2007-02-02"]
["UN36_00600","Fiducialization Measurements - Photon Diagnostic","2006-07-31","2007-02-02"]
["UN36_00610","Data Evaluation - Photon Diagnostic","2006-07-31","2007-02-02"]
["UN36_00620","F/MM for Vacuum and Diag Complete","2007-02-05","2007-02-02"]
["UN36_02000","Quad Mag Measure/Fiducialization Facility Read","2006-05-02","2006-05-01"]
["UN36_02010","Magnetic Field Measurement #01 Article at SLAC","2007-01-22","2007-01-23"]
["UN36_02020","Quadrupole #01 Fiducialization","2007-01-24","2007-01-25"]
["UN36_02030","Magnetic Field Measurement #02 Article at SLAC","2007-03-02","2007-03-05"]
["UN36_02040","Quadrupole #02 Fiducialization","2007-03-06","2007-03-07"]
["UN36_02050","Magnetic Field Measurement #03 Article at SLAC","2007-03-08","2007-03-09"]
["UN36_02060","Quadrupole #03 Fiducialization","2007-03-12","2007-03-13"]
["UN36_02070","Magnetic Field Measurement #04 Article at SLAC","2007-03-14","2007-03-15"]
["UN36_02080","Quadrupole #04 Fiducialization","2007-03-16","2007-03-19"]
["UN36_02085","Magnetic Field Measurement #05 Article at SLAC","2007-03-20","2007-03-21"]
["UN36_02090","Quadrupole #05 Fiducialization","2007-03-22","2007-03-23"]
["UN36_02100","Magnetic Field Measurement #06 Article at SLAC","2007-03-26","2007-03-27"]
["UN36_02110","Quadrupole #06 Fiducialization","2007-03-28","2007-03-29"]
["UN36_02120","Magnetic Field Measurement #07 Article at SLAC","2007-03-30","2007-04-02"]
["UN36_02130","Quadrupole #07 Fiducialization","2007-04-03","2007-04-04"]
["UN36_02140","Magnetic Field Measurement #08 Article at SLAC","2007-04-05","2007-04-06"]
["UN36_02150","Quadrupole #08 Fiducialization","2007-04-09","2007-04-10"]
["UN36_02160","Magnetic Field Measurement #09 Article at SLAC","2007-04-11","2007-04-12"]
["UN36_02170","Quadrupole #09 Fiducialization","2007-04-13","2007-04-16"]
["UN36_02180","Magnetic Field Measurement #10 Article at SLAC","2007-04-17","2007-04-18"]
["UN36_02190","Quadrupole #10 Fiducialization","2007-04-19","2007-04-20"]
["UN36_02200","Magnetic Field Measurement #11 Article at SLAC","2007-04-23","2007-04-24"]
["UN36_02210","Quadrupole #11 Fiducialization","2007-04-25","2007-04-26"]
["UN36_02220","Magnetic Field Measurement #12 Article at SLAC","2007-04-27","2007-04-30"]
["UN36_02230","Quadrupole #12 Fiducialization","2007-05-01","2007-05-02"]
["UN36_02240","Magnetic Field Measurement #13 Article at SLAC","2007-05-03","2007-05-04"]
["UN36_02250","Quadrupole #13 Fiducialization","2007-05-07","2007-05-08"]
["UN36_02260","Magnetic Field Measurement #14 Article at SLAC","2007-05-09","2007-05-10"]
["UN36_02270","Quadrupole #14 Fiducialization","2007-05-11","2007-05-14"]
["UN36_02280","Magnetic Field Measurement #15 Article at SLAC","2007-05-15","2007-05-16"]
["UN36_02290","Quadrupole #15 Fiducialization","2007-05-17","2007-05-18"]
["UN36_02300","Magnetic Field Measurement #16 Article at SLAC","2007-05-21","2007-05-22"]
["UN36_02310","Quadrupole #16 Fiducialization","2007-05-23","2007-05-24"]
["UN36_02320","Magnetic Field Measurement #17 Article at SLAC","2007-05-25","2007-05-29"]
["UN36_02330","Quadrupole #17 Fiducialization","2007-05-30","2007-05-31"]
["UN36_02340","Magnetic Field Measurement #18 Article at SLAC","2007-06-01","2007-06-04"]
["UN36_02350","Quadrupole #18 Fiducialization","2007-06-05","2007-06-06"]
["UN36_02360","Magnetic Field Measurement #19 Article at SLAC","2007-06-07","2007-06-08"]
["UN36_02370","Quadrupole #19 Fiducialization","2007-06-11","2007-06-12"]
["UN36_02375","Magnetic Field Measurement #20 Article at SLAC","2007-07-10","2007-07-11"]
["UN36_02380","Quadrupole #20 Fiducialization","2007-07-12","2007-07-13"]
["UN36_02390","Magnetic Field Measurement #21 Article at SLAC","2007-07-16","2007-07-17"]
["UN36_02400","Quadrupole #21 Fiducialization","2007-07-18","2007-07-19"]
["UN36_02410","Magnetic Field Measurement #22 Article at SLAC","2007-07-20","2007-07-23"]
["UN36_02420","Quadrupole #22 Fiducialization","2007-07-24","2007-07-25"]
["UN36_02430","Magnetic Field Measurement #23 Article at SLAC","2007-07-26","2007-07-27"]
["UN36_02440","Quadrupole #23 Fiducialization","2007-07-30","2007-07-31"]
["UN36_02450","Magnetic Field Measurement #24 Article at SLAC","2007-08-01","2007-08-02"]
["UN36_02460","Quadrupole #24 Fiducialization","2007-08-03","2007-08-06"]
["UN36_02470","Magnetic Field Measurement #25 Article at SLAC","2007-08-07","2007-08-08"]
["UN36_02480","Quadrupole #25 Fiducialization","2007-08-09","2007-08-10"]
["UN36_02490","Magnetic Field Measurement #26 Article at SLAC","2007-08-13","2007-08-14"]
["UN36_02500","Quadrupole #26 Fiducialization","2007-08-15","2007-08-16"]
["UN36_02510","Magnetic Field Measurement #27 Article at SLAC","2007-08-17","2007-08-20"]
["UN36_02520","Quadrupole #27 Fiducialization","2007-08-21","2007-08-22"]
["UN36_02530","Magnetic Field Measurement #28 Article at SLAC","2007-08-23","2007-08-24"]
["UN36_02540","Quadrupole #28 Fiducialization","2007-08-27","2007-08-28"]
["UN36_02550","Magnetic Field Measurement #29 Article at SLAC","2007-08-29","2007-08-30"]
["UN36_02560","Quadrupole #29 Fiducialization","2007-08-31","2007-09-04"]
["UN36_02570","Magnetic Field Measurement #30 Article at SLAC","2007-09-05","2007-09-06"]
["UN36_02580","Quadrupole #30 Fiducialization","2007-09-07","2007-09-10"]
["UN36_02590","Magnetic Field Measurement #31 Article at SLAC","2007-09-11","2007-09-12"]
["UN36_02600","Quadrupole #31 Fiducialization","2007-09-13","2007-09-14"]
["UN36_02610","Magnetic Field Measurement #32 Article at SLAC","2007-09-17","2007-09-18"]
["UN36_02620","Quadrupole #32 Fiducialization","2007-09-19","2007-09-20"]
["UN36_02630","Magnetic Field Measurement #33 Article at SLAC","2007-09-21","2007-09-24"]
["UN36_02640","Quadrupole #33 Fiducialization","2007-09-25","2007-09-26"]
["UN36_02650","Magnetic Field Measurement #34 Article at SLAC","2008-10-01","2008-10-02"]
["UN36_02660","Quadrupole #34 Fiducialization","2008-10-03","2008-10-06"]
["UN36_02670","Magnetic Field Measurement #35 Article at SLAC","2008-10-01","2008-10-02"]
["UN36_02680","Quadrupole #35 Fiducialization","2008-10-07","2008-10-08"]
["UN36_02690","Magnetic Field Measurement #36 Article at SLAC","2008-10-03","2008-10-06"]
["UN36_02700","Quadrupole #36 Fiducialization","2008-10-09","2008-10-10"]
["UN36_02710","Magnetic Field Measurement #37 Article at SLAC","2008-10-07","2008-10-08"]
["UN36_02715","Quadrupole #37 Fiducialization","2008-10-13","2008-10-14"]
["UN36_02718","Magnetic Field Measurement #38 Article at SLAC","2008-10-09","2008-10-10"]
["UN36_02720","Quadrupole #38 Fiducialization","2008-10-15","2008-10-16"]
["UN36_02730","Magnetic Field Measurement #39 Article at SLAC","2008-10-13","2008-10-14"]
["UN36_02740","Quadrupole #39 Fiducialization","2008-10-17","2008-10-20"]
["UN36_02750","Magnetic Field Measurement #40 Article at SLAC","2008-10-15","2008-10-16"]
["UN36_02760","Quadrupole #40 Fiducialization","2008-10-21","2008-10-22"]
["UN38_00010","Produce Final Fixed Support Design","2005-07-01","2005-08-31",null,"2005-07-01"]
["UN38_00013","Fixed Support Development","2005-06-01","2005-08-10"]
["UN38_00014","Design/Analyze Prototype & Test","2005-07-01","2006-02-09",null,"2005-07-01"]
["UN38_00015","Define Supt/Mover Interfaces","2005-07-01","2005-06-30",null,"2005-07-01"]
["UN38_00016","Procurement/Acceptance/Vendor Mgmt","2006-02-10","2006-06-19"]
["UN38_00017","Define Interfaces w/Conventional Facilities","2005-08-01","2005-06-30",null,"2005-08-01"]
["UN38_00018","Define Interfaces w/Survey Alignment","2005-07-01","2005-06-30",null,"2005-07-01"]
["UN38_00019","Define Interfaces w/Controls/Monitor","2005-07-01","2005-06-30",null,"2005-07-01"]
["UN38_00020","Perform Thermal Analysis","2005-07-01","2005-07-01"]
["UN38_00025","Procure Prototype Components","2005-07-01","2005-07-15",null,"2005-07-01"]
["UN38_00030","Fab/Assemble Prototype Components","2005-09-16","2005-05-16",null,"2005-09-16"]
["UN38_00035","Thermal and Vibration Testing","2005-08-01","2005-08-01",null,"2005-08-01"]
["UN38_00040","Perform Vibration Analysis","2005-09-16","2005-06-17",null,"2005-09-16"]
["UN38_00045","Design/Integration of Earthquake Brace","2005-09-01","2005-06-01",null,"2005-09-01"]
["UN38_00047","Integrated PRO-E Model of FS/SM/UM","2005-09-01","2005-06-15",null,"2005-09-01"]
["UN38_00048","Analyze Prototype Test Results","2005-09-01","2005-06-01",null,"2005-09-01"]
["UN38_00049","Write Report","2005-06-02","2005-06-28"]
["UN38_00051","Prepare for IDR","2005-11-28","2005-12-05"]
["UN38_00052","Independent Design Review","2005-12-06","2005-12-06"]
["UN38_00053","Modify Design for Integrated System Test","2005-12-07","2005-12-13"]
["UN38_00054","Procure Fixed Supports for Integrated System Tst","2005-12-14","2006-02-06"]
["UN38_00055","Assy of Fixed Supports at Integrated System Tst","2006-02-07","2006-02-13"]
["UN38_00056","Write SOW for Pillar,Top/Bottom Plates & Insultn","2006-02-07","2006-02-27"]
["UN38_00057","Prepare for FDR","2006-02-28","2006-03-06"]
["UN38_00058","Final Design Review (Integrated with Supt/Mover)","2006-04-24","2006-04-24"]
["UN38_00059","Incorporate Comments from FDR","2006-04-25","2006-05-08"]
["UN38_00060","Release RFP for Pillar/Plates/Insulation","2006-05-09","2006-05-09"]
["UN38_00061","Vendor Prep Prop. for Pillar/Plates/Insulation","2006-05-10","2006-05-31"]
["UN38_00062","Evaluate Prop. for Pillar/Plates/Insulation","2006-06-01","2006-06-14"]
["UN38_00063","AWARD: Fixed Supports","2006-06-15","2006-06-15"]
["UN38_00064","Vendor Fab/Assemble Fixed Supports","2006-06-16","2006-09-14"]
["UN38_00065","RCV: Fixed Supports","2006-09-15","2006-09-14"]
["UN38_00067","Integrate Temperature DAQ with FS/SM/UM","2005-07-01","2005-08-31",null,"2005-07-01"]
["UN38_00068","Specify Temperature DAQ System","2005-09-01","2005-09-06"]
["UN38_00100","Design CAM Transfer Template","2005-07-01","2005-08-31",null,"2005-07-01"]
["UN38_00270","Procure Thermistors","2005-10-03","2005-10-28"]
["UN38_00280","Procure Cabling","2005-10-03","2005-10-28"]
["UN38_00290","Procure Readout Electronics","2005-10-03","2005-11-29"]
["UN38_00300","Thermometry Ready for Assembly","2005-11-30","2005-11-29"]
["UN38_00380","Procure Earthquake Bracing","2005-10-03","2005-11-29"]
["UN38_00390","Write Alignment Software","2006-04-25","2006-06-06"]
["UN38_00400","Fixed Support Controls Ready for Stabilization","2006-06-07","2006-06-06"]
["UN38_00410","REQD: Alignment Monitoring specifications","2006-04-25","2006-04-24"]
["UN42_00230","Receive  Prd Un Cham Specs from Undulator Group","2006-06-01","2006-06-07"]
["UN42_00240","Prelim Design Prd Un Chamber","2006-06-22","2006-07-13"]
["UN42_00250","Prelim Design Review Prd Un Chamber","2006-07-14","2006-07-18"]
["UN42_00260","Final Design Prd Un Chamber","2006-07-19","2006-08-03"]
["UN42_00270","Design Complete Prd Un Chamber","2006-08-04","2006-08-03"]
["UN42_00280","Bid Package- Prd Un Chamber","2006-08-04","2006-08-08"]
["UN42_00330","Bid Process Prd Un Chamber","2006-08-09","2006-09-13"]
["UN42_00331","Evalute Bid Prd Un Chamber","2006-09-14","2006-09-18"]
["UN42_00340","AWARD: Production Undulator Chamber (34)","2006-09-19","2006-09-20"]
["UN42_00341","AWARD: Production Undulator Chamber (7)","2006-10-03","2006-10-04"]
["UN42_00345","AWARD: Production Undulator Chamber (34) Support","2006-09-19","2006-09-20"]
["UN42_00365","AWARD: Chamber Supports (31) Support","2006-09-19","2006-09-20"]
["UN42_00390","AWARD: Complete Prd Un Chamber","2006-09-21","2006-09-20"]
["UN42_00400","Rec: First Lot Production Undulator Chamber (10)","2006-09-21","2006-11-15"]
["UN42_00410","QA First Lot Prd Un Chamber","2006-11-16","2006-11-22"]
["UN42_00420","Fabrication of First Lot Prd Un Chamber","2006-11-27","2007-01-16"]
["UN42_00421","Assembly Test Prd Un Cham (10)","2006-12-18","2007-01-23"]
["UN42_00422","Clean  Prd Un Cham (10)","2007-01-24","2007-02-02"]
["UN42_00423","Bake Prd Un Cham (10)","2007-02-05","2007-02-23"]
["UN42_00424","Prep Chamber Assy & Support for Shipment (10)","2007-02-26","2007-03-02"]
["UN42_00425","Pack Chamber Assembly & Supt for Shipping (10)","2007-03-05","2007-03-09"]
["UN42_00426","Ship  Prd Un Chamber to SLAC (10)","2007-03-12","2007-03-09"]
["UN42_00427","Transmit  Prd Un Cham Design & Drawings to SLAC","2007-03-12","2007-03-16"]
["UN42_00428","RFI: Undulator Vacuum Chamber Assembly (10)","2007-03-19","2007-03-16"]
["UN42_00430","Approve Continuation of Production Prd Un Cham","2006-11-27","2006-11-28"]
["UN42_00440","RCV: Remain Lot Production Undulator Chamb (24)","2006-11-29","2007-02-15"]
["UN42_00441","Rec: Production Undulator Chamb (7)","2006-11-29","2007-02-23"]
["UN42_00450","QA Production Lot Prd Un Chamber","2007-02-26","2007-03-09"]
["UN42_00460","Fabrication of Rem Production Lot Prd Un Chamber","2007-03-12","2007-04-20"]
["UN42_00470","Approve Production Lot Prd Un Chamber","2007-04-02","2007-04-03"]
["UN42_00480","Prelim Design Chamber Sup","2006-07-11","2006-08-07"]
["UN42_00490","Mechanical Analysis","2006-07-07","2006-07-18"]
["UN42_00500","Final Design Chamber Sup","2006-07-19","2006-08-01"]
["UN42_00510","Design Complete Chamber Sup","2006-08-02","2006-08-01"]
["UN42_00520","Bid Package-Chamber Supports","2006-08-02","2006-08-08"]
["UN42_00550","Bid Process Chamber Supports","2006-08-09","2006-09-13"]
["UN42_00551","Evaluate Bid - Chamber Supports","2006-09-14","2006-09-18"]
["UN42_00560","AWARD: Chamber Supports (31)","2006-09-19","2006-09-20"]
["UN42_00561","Award: Chamber Supports","2006-10-03","2006-10-04"]
["UN42_00590","AWARD: Complete Chamber Supports","2006-09-21","2006-09-20"]
["UN42_00600","RCV  Chamber Supports (31)","2006-09-21","2006-11-15"]
["UN42_00601","RCV: Chamber Supports","2006-10-05","2006-12-01"]
["UN42_00610","Quality Assurance Chamber Sup","2006-12-04","2006-12-19"]
["UN42_00640","Assembly Test Prd Un Cham (24)","2007-04-04","2007-05-01"]
["UN42_00650","Clean  Prd Un Cham (24)","2007-05-02","2007-05-11"]
["UN42_00660","Bake Prd Un Cham (24)","2007-05-14","2007-06-04"]
["UN42_00670","Prep Chamber Assembly & Supt for Shipment (24)","2007-06-05","2007-06-11"]
["UN42_00680","Pack Chamber Assembly & Supt for Shipping(24)","2007-06-12","2007-06-18"]
["UN42_00690","Ship  Prd Un Chamber to SLAC (24)","2007-06-19","2007-06-18"]
["UN42_00702","RFI: Undulator Vacuum Chamber Assembly (24)","2007-07-03","2007-07-02"]
["UN42_00710","Develop Installation Plan Prd Un Chamber","2006-08-04","2006-08-17"]
["UN42_00720","Review Installation Plan Prd Un Chamber","2006-08-18","2006-08-24"]
["UN42_00730","Prd Un Cham Assembly Arrive at SLAC (10)","2007-03-19","2007-03-30"]
["UN42_00732","Prd Un Cham Assembly Arrive at SLAC (24)","2007-06-19","2007-07-02"]
["UN42_00810","Commission Un Cham","2006-10-03","2006-10-09"]
["UN42_D220","Perform welding tests","2005-06-13","2005-09-22"]
["UN42_D222","Final determination of metal surface finish meas","2005-11-30","2006-03-07"]
["UN42_D223","Final determination of welding process","2005-09-23","2006-01-11"]
["UN42_D227","Mechanical analysis of chamber","2005-05-02","2005-07-28"]
["UN42_D235","Test samples for AC conductivity","2005-05-02","2005-06-30"]
["UN42_D236","Collect results AC conductivity","2005-05-02","2005-09-23"]
["UN42_D237","Write study report AC conductivity","2005-09-26","2005-12-06"]
["UN42_D238","Submit study report AC conductivity","2005-12-07","2005-12-06"]
["UN42_D240","Create extrusion conceptual design","2005-05-02","2005-07-29"]
["UN42_D241","Create box conceptual design","2005-05-02","2005-05-20"]
["UN42_D257","Preliminary prototype design UN chamber","2005-05-02","2005-08-02"]
["UN42_D258","Prototype UN chamber tooling design","2005-08-03","2005-09-07"]
["UN42_D259","Prototype design review UN chamber","2005-09-08","2005-09-12"]
["UN42_D260","Prototype final design UN chamber","2005-09-13","2005-10-03"]
["UN42_D261","Prototype design complete","2005-11-14","2005-11-11"]
["UN42_D262","Bid process prototype UN chamber","2005-11-14","2005-12-20"]
["UN42_D263","Bid process prototype UN chamber tooling","2005-11-14","2005-12-20"]
["UN42_D264","Evaluate bid prototype UN chamber","2005-12-21","2006-01-05"]
["UN42_D265","Procure Prototype undulator chamber (2)","2006-01-06","2006-01-10"]
["UN42_D266","Procure Prototype UN chamber tooling","2006-01-06","2006-01-10"]
["UN42_D267","RCV Parts prototype UN chamber","2006-01-11","2006-04-04"]
["UN42_D268","Quality assurance prototype UN chamber","2006-04-05","2006-04-18"]
["UN42_D269","Procure Polish parts","2006-04-19","2006-05-16"]
["UN42_D270","Fabrication of prototype chamber weldment","2006-05-17","2006-06-07"]
["UN42_D271","Measurement and test prototype UN chamber","2006-06-08","2006-07-13"]
["UN42_D272","Prototype UN chamber testing complete","2006-07-14","2006-07-13"]
["UN42_DP219","Fabricate Welding Samples and Tooling","2005-05-02","2005-08-31"]
["UN42_DR210","Literature Search - Surface Mesurement","2005-06-14","2005-07-15"]
["UN42_DR212","Procure surface measurement equipment","2005-07-18","2005-08-26"]
["UN42_DR213","Fabricate surface measuring equipment","2005-08-08","2005-09-19"]
["UN42_DR214","Assemble surface measuring equipment","2005-10-03","2005-10-14"]
["UN42_DR215","Initial surface test","2005-10-17","2005-10-28"]
["UN42_DR216","Test confirmation of surface measurement","2005-10-31","2005-11-29"]
["UN42_DR218","Design weld tooling","2005-10-03","2005-11-11"]
["UN42_DR219","Stainless Steel Permeability Testing","2005-05-23","2005-07-05"]
["UN42_DR221","Final determination of metal polishing","2005-11-30","2006-03-07"]
["UN42_DR233","Fabricate AC conductivity samples","2005-05-02","2005-06-06"]
["UN43_00070","Bid Package-Ag Plated RF Finger Prtp Bel Mod","2005-10-28","2005-11-01"]
["UN43_00080","Bid Package-Rh Plated Stub Prtp Bel Mod","2005-10-28","2005-11-01"]
["UN43_00090","Bid Package-Tubes Prtp Bel Mod","2005-10-28","2005-11-01"]
["UN43_00100","Bid Package- Prtp Bellows Module","2005-10-28","2005-11-01"]
["UN43_00120","Bid Process Prtp Bel Mod","2005-11-02","2005-12-08"]
["UN43_00130","Procure Ag Plated RF Finger Prtp Bel Mod","2005-12-09","2005-12-12"]
["UN43_00140","Procure Rh Plated Stub Prtp Bel Mod","2005-12-09","2005-12-12"]
["UN43_00150","Procure Tubes Prtp Bel Mod","2005-12-09","2005-12-12"]
["UN43_00160","Procure Bellows Prtp Bel Mod","2005-12-09","2005-12-12"]
["UN43_00180","Prototype Bel Mod Award Complete","2005-12-13","2005-12-12"]
["UN43_00190","RCV: Bellows  Prtp Bel Mod","2005-12-13","2006-02-01"]
["UN43_00200","Quality Assurance Prtp Bel Mod","2006-02-02","2006-02-08"]
["UN43_00201","Test Equipment Fab & Assy","2005-10-19","2005-12-01"]
["UN43_00220","Measurement and Test Prtp Bel Mod","2006-02-09","2006-02-22"]
["UN43_00230","Review and Report Prtp Bel Mod","2006-02-23","2006-03-01"]
["UN43_00240","Prototype Bel Mod Testing Complete","2006-03-02","2006-03-01"]
["UN43_00241","Proto Prelimin Design","2005-07-22","2005-08-18"]
["UN43_00242","Study of Lubrication Coating","2005-05-02","2005-06-08"]
["UN43_00243","Proto Mech. Anal.","2005-06-23","2005-07-29"]
["UN43_00244","Evaluation of Lubrication Coating","2005-07-29","2005-09-09"]
["UN43_00245","Test Tooling Design","2005-08-12","2005-09-09"]
["UN43_00246","Proto Review","2005-09-12","2005-09-27"]
["UN43_00247","Proto Final Design","2005-09-28","2005-10-18"]
["UN43_00248","Write Bellow Fab Spec","2005-10-12","2005-10-27"]
["UN43_00250","Prelim Standard Bellows Design","2006-03-02","2006-03-22"]
["UN43_00260","Bellows Physics Review","2006-03-23","2006-03-24"]
["UN43_00270","Final Standard Bellows Design","2006-03-27","2006-03-31"]
["UN43_00280","Design Complete FDR Std Bel Mod","2006-04-03","2006-03-31"]
["UN43_00283","Final Design Review Std Bel Mod","2006-04-03","2006-04-04"]
["UN43_00290","Bid Package-Standard Bellows Module","2006-04-05","2006-04-07"]
["UN43_00340","Bid Process Std Bel Mod","2006-04-10","2006-05-12"]
["UN43_00342","Evaluate Bid Std Bel Mod","2006-05-15","2006-05-16"]
["UN43_00350","AWARD: Standard Bellows Module (47)","2006-05-17","2006-05-18"]
["UN43_00355","Standard Bellows Module (47) Support","2006-05-17","2006-05-18"]
["UN43_00360","AWARD: Standard Bellows Module (4)","2006-10-03","2006-10-04"]
["UN43_00400","AWARD: Complete Std Bel Module","2006-05-19","2006-05-18"]
["UN43_00410","Receive First Lot Standard Bellows Module (4)","2006-05-19","2006-06-30"]
["UN43_00420","QA First Lot Std Bel Mod","2006-07-03","2006-07-13"]
["UN43_00440","Approve Continuation of Production Std Bel Mod","2006-07-14","2006-07-17"]
["UN43_00450","Receive Remain Prod Lot Std Bellows Module (43","2006-07-18","2006-09-12"]
["UN43_00451","Receive Standard Bellows Module (4)","2006-10-05","2006-12-01"]
["UN43_00460","QA Production Lot Std Bel Mod","2006-09-13","2006-10-03"]
["UN43_00500","Assembly Test Std Bel Mod","2006-10-04","2006-10-17"]
["UN43_00510","Clean Std Bel Mod","2006-10-18","2006-10-27"]
["UN43_00520","Bake Std Bel Mod","2007-01-19","2007-01-25"]
["UN43_00530","Prepare Standard Bellows for Shipment","2007-01-26","2007-02-01"]
["UN43_00540","Pack Standard Bellows for Shipping","2007-02-02","2007-02-08"]
["UN43_00550","Ship  Std Bel Mod to Slac","2007-02-09","2007-02-08"]
["UN43_00560","Transmit  Std Bel Mod Design & Drawings to SLA","2007-02-09","2007-02-15"]
["UN43_00562","RFI: Beam-Line Bellows Module Assembly","2007-02-16","2007-02-15"]
["UN43_00570","Standard Bellows Arrive at SLAC","2007-07-03","2007-07-17"]
["UN43_00620","Commission Std Bel Mod","2006-12-04","2006-12-08"]
["UN43_CM000","Commission Fixed Supports","2006-10-03","2007-02-09"]
["UN43_SPR00","RCV: Fixed Support Spares","2006-10-03","2006-12-13"]
["UN44_00100","Modify Design Stand-in Chamber","2005-09-01","2005-11-15"]
["UN44_00110","Shops to Quote Chamber","2005-11-16","2005-12-01"]
["UN44_00120","Shops to Fab Chamber","2005-12-02","2006-03-09"]
["UN44_00200","Design BFW-Cher-Vac Chamber","2005-11-16","2005-12-19"]
["UN44_00210","Get Quote on BFW-Ch-Vac Cham","2005-12-20","2006-01-11"]
["UN44_00220","Purchase BFW-Ch-Vac Cham","2006-01-12","2006-03-10"]
["UN44_00300","Select Ion Pump","2005-11-16","2005-11-22"]
["UN44_00310","Get Quote on Ion Pump (contd.)","2005-11-23","2005-12-08"]
["UN44_00320","Purchase Pump","2005-12-09","2006-02-15"]
["UN44_00400","Design Ion Pump Support","2005-11-23","2005-12-15"]
["UN44_00410","Shops to Quote on Ion Pump Support","2005-12-16","2006-01-09"]
["UN44_00420","Shops to Fab Pump Support","2006-01-10","2006-02-21"]
["UN44_00500","Design BFW-Cher-Vac Cham Support","2005-12-06","2006-01-04"]
["UN44_00510","Shops to quote BFW-Ch-Vac Cham Support","2006-01-05","2006-01-18"]
["UN44_00520","Shops to Fab BFW-Ch-Vac Cham Support","2006-01-19","2006-03-02"]
["UN44_00580","Commission Std Col","2006-10-03","2006-10-09"]
["UN45_00020","SDB Design","2005-08-03","2006-05-26"]
["UN45_00030","Mechanical Analysis SDB","2006-05-30","2006-06-07"]
["UN45_00050","Final SDB Design","2006-06-08","2006-06-21"]
["UN45_00052","Final SDB Design Review","2006-06-22","2006-06-28"]
["UN45_00060","SDB Design Complete","2006-06-29","2006-06-28"]
["UN45_00100","Ion Pump Bid Pkg","2006-06-29","2006-07-03"]
["UN45_00110","Ion Pump Power Supply Bid Pkg","2006-06-29","2006-07-03"]
["UN45_00120","Ion Pump Cable Bid Package","2006-06-29","2006-07-03"]
["UN45_00140","Chamber Support Bid Package","2006-06-29","2006-07-06"]
["UN45_00150","Pump Support Bid Package","2006-06-29","2006-07-06"]
["UN45_00160","Bid Process SDB","2006-09-11","2006-10-13"]
["UN45_00161","Evaluate Bids:  SDB","2006-10-16","2006-10-18"]
["UN45_00170","AWARD: Chamber Weldment Assembly (23)","2006-10-16","2006-10-17"]
["UN45_00171","AWARD: Chamber Weldment Assembly (2)","2006-10-16","2006-10-17"]
["UN45_00175","AWARD: Chamber Weldment Assembly (23) Support","2006-10-16","2006-10-17"]
["UN45_00190","AWARD: Pump Manifold (23)","2006-10-19","2006-10-20"]
["UN45_00191","AWARD: Pump Manifold","2006-10-19","2006-10-20"]
["UN45_00195","AWARD: Pump Manifold (23) Support","2006-10-19","2006-10-20"]
["UN45_00200","AWARD: Ion Pump (23)","2006-10-16","2006-10-17"]
["UN45_00201","AWARD: Ion Pump (1)","2006-10-16","2006-10-17"]
["UN45_00205","AWARD: Ion Pump (23) Support","2006-10-16","2006-10-17"]
["UN45_00210","AWARD: Ion Pump Power Supply (12)","2006-10-16","2006-10-17"]
["UN45_00211","AWARD: Ion Pump Power Supply","2006-10-16","2006-10-17"]
["UN45_00215","AWARD: Ion Pump Power Supply (12) Support","2006-10-16","2006-10-17"]
["UN45_00220","AWARD:  Ion Pump Cable (23)","2006-10-16","2006-10-17"]
["UN45_00221","AWARD: Ion Pump Cable (1)","2006-10-16","2006-10-17"]
["UN45_00225","AWARD:  Ion Pump Cable (23) Support","2006-10-16","2006-10-17"]
["UN45_00240","AWARD: Chamber Support (23)","2006-10-16","2006-10-18"]
["UN45_00241","AWARD: Chamber Support (1)","2006-10-16","2006-10-18"]
["UN45_00245","AWARD: Chamber Support (23) Sppt","2006-10-16","2006-10-18"]
["UN45_00250","AWARD: Pump Support (23)","2006-10-16","2006-10-18"]
["UN45_00251","AWARD: Pump Support (1)","2006-10-16","2006-10-18"]
["UN45_00255","AWARD: Pump Support (23) Sppt","2006-10-16","2006-10-18"]
["UN45_00260","AWARD: Short Diagnostic Break Assembly","2006-10-23","2006-10-24"]
["UN45_00320","Rec: SDB Chamber Weldment Assembly","2006-10-25","2006-12-07"]
["UN45_00321","Rec: SDB Chamber Weldment Assembly","2006-10-25","2006-12-07"]
["UN45_00322","Rec: SDB Pump Manifold","2006-10-25","2006-12-07"]
["UN45_00323","Rec: SDB Pump Manifold","2006-10-25","2006-12-07"]
["UN45_00324","Rec: SDB Ion Pump","2006-10-25","2006-12-07"]
["UN45_00325","Rec: SDB Ion Pump","2006-10-25","2006-12-07"]
["UN45_00326","Rec: SDB Ion Pump Power Supply","2006-10-25","2006-12-07"]
["UN45_00327","Rec: SDB Ion Pump Power Supply","2006-10-25","2006-12-07"]
["UN45_00328","Rec: SDB Ion Pump Cable","2006-10-25","2006-12-07"]
["UN45_00329","Rec: SDB Ion Pump Cable","2006-10-25","2006-12-07"]
["UN45_00330","Rec: SDB Chamber Supports","2006-10-25","2006-12-07"]
["UN45_00331","Rec: SDB Chamber Supports","2006-10-25","2006-12-07"]
["UN45_00332","Rec: SDB Pump Supports","2006-10-25","2006-12-07"]
["UN45_00333","Rec: SDB Pump Supports","2006-10-25","2006-12-07"]
["UN45_00335","Rec: SDB Pump Weld","2006-10-25","2006-12-07"]
["UN45_00336","Rec: SDB Ion Pump Support","2006-10-25","2006-12-07"]
["UN45_00339","QA Production Lot SDB","2006-12-08","2006-12-21"]
["UN45_00340","Approve Production Lot SDB","2007-01-02","2007-01-04"]
["UN45_00350","Clean SDB","2007-01-05","2007-01-11"]
["UN45_00360","Bake SDB","2007-01-19","2007-01-25"]
["UN45_00390","Prepare Short Diagnostic Break for Shipment","2007-01-26","2007-02-01"]
["UN45_00400","Pack Short Diagnostic Break for Shipping","2007-02-02","2007-02-08"]
["UN45_00410","Ship to Slac SDB","2007-02-09","2007-02-08"]
["UN45_00420","Transmit  SDB Design & Drawings to SLAC","2007-02-09","2007-02-15"]
["UN45_00422","RFI: Short Diagnostic Break Assembly","2007-02-16","2007-02-15"]
["UN45_00430","Develop Installation Plan SDB","2007-02-09","2007-02-22"]
["UN45_00440","Review installation Plan  SDB","2007-02-23","2007-03-01"]
["UN45_00450","Short Diagnostic Break Assembly Arrive at SLAC","2007-07-03","2007-07-17"]
["UN45_00460","Install Short Break Section Components","2007-08-23","2007-08-29"]
["UN45_00530","Commission - Short Diag Break Assy","2007-08-30","2007-09-06"]
["UN45_D180","Perform literature search Cavity BPM","2005-05-02","2005-06-30"]
["UN45_D181","Develop conceptual design of BPM","2005-07-01","2005-08-31"]
["UN45_D182","BPM conceptual design complete","2005-09-01","2005-08-31"]
["UN462_0000","Equipment Available at SLAC & Und B.O.","2007-07-31","2007-07-30"]
["UN462_0005","Install Racks in Alcoves/End Stations","2007-07-31","2007-08-06"]
["UN462_0010","Install Cables from Racks to Tunnel Locations","2007-08-07","2007-08-13"]
["UN462_0015","Terminate Cables","2007-08-14","2007-08-27"]
["UN462_0020","Install Rack Mount Equipment","2007-08-07","2007-08-13"]
["UN462_0100","Connect Devices @ Undulator #33","2008-04-04","2008-04-04"]
["UN462_0105","Test Devices @ Undulator #33","2008-04-07","2008-04-07"]
["UN462_0110","Connect Devices @ Undulator #32","2008-03-31","2008-03-31"]
["UN462_0115","Test Devices @ Undulator #32","2008-04-01","2008-04-01"]
["UN462_0120","Connect Devices @ Undulator #31","2008-03-25","2008-03-25"]
["UN462_0125","Test Devices @ Undulator #31","2008-03-26","2008-03-26"]
["UN462_0130","Connect Devices @ Undulator #30","2008-03-19","2008-03-19"]
["UN462_0135","Test Devices @ Undulator #30","2008-03-20","2008-03-20"]
["UN462_0140","Connect Devices @ Undulator #29","2008-03-13","2008-03-13"]
["UN462_0145","Test Devices @ Undulator #29","2008-03-14","2008-03-14"]
["UN462_0150","Connect Devices @ Undulator #28","2008-03-07","2008-03-07"]
["UN462_0155","Test Devices @ Undulator #28","2008-03-10","2008-03-10"]
["UN462_0160","Connect Devices @ Undulator #27","2008-03-03","2008-03-03"]
["UN462_0165","Test Devices @ Undulator #27","2008-03-04","2008-03-04"]
["UN462_0170","Connect Devices @ Undulator #26","2008-02-26","2008-02-26"]
["UN462_0175","Test Devices @ Undulator #26","2008-02-27","2008-02-27"]
["UN462_0180","Connect Devices @ Undulator #25","2008-02-20","2008-02-20"]
["UN462_0185","Test Devices @ Undulator #25","2008-02-21","2008-02-21"]
["UN462_0190","Connect Devices @ Undulator #24","2008-02-13","2008-02-13"]
["UN462_0195","Test Devices @ Undulator #24","2008-02-14","2008-02-14"]
["UN462_0200","Connect Devices @ Undulator #23","2008-02-07","2008-02-07"]
["UN462_0205","Test Devices @ Undulator #23","2008-02-08","2008-02-08"]
["UN462_0210","Connect Devices @ Undulator #22","2008-02-01","2008-02-01"]
["UN462_0215","Test Devices @ Undulator #22","2008-02-04","2008-02-04"]
["UN462_0220","Connect Devices @ Undulator #21","2008-01-28","2008-01-28"]
["UN462_0225","Test Devices @ Undulator #21","2008-01-29","2008-01-29"]
["UN462_0230","Connect Devices @ Undulator #20","2008-01-21","2008-01-21"]
["UN462_0235","Test Devices @ Undulator #20","2008-01-22","2008-01-22"]
["UN462_0240","Connect Devices @ Undulator #19","2008-01-15","2008-01-15"]
["UN462_0245","Test Devices @ Undulator #19","2008-01-16","2008-01-16"]
["UN462_0250","Connect Devices @ Undulator #18","2008-01-09","2008-01-09"]
["UN462_0255","Test Devices @ Undulator #18","2008-01-10","2008-01-10"]
["UN462_0260","Connect Devices @ Undulator #17","2008-01-03","2008-01-03"]
["UN462_0265","Test Devices @ Undulator #17","2008-01-04","2008-01-04"]
["UN462_0270","Connect Devices @ Undulator #16","2007-12-12","2007-12-12"]
["UN462_0275","Test Devices @ Undulator #16","2007-12-13","2007-12-13"]
["UN462_0280","Connect Devices @ Undulator #15","2007-12-06","2007-12-06"]
["UN462_0285","Test Devices @ Undulator #15","2007-12-07","2007-12-07"]
["UN462_0290","Connect Devices @ Undulator #14","2007-11-30","2007-11-30"]
["UN462_0295","Test Devices @ Undulator #14","2007-12-03","2007-12-03"]
["UN462_0300","Connect Devices @ Undulator #13","2007-11-26","2007-11-26"]
["UN462_0305","Test Devices @ Undulator #13","2007-11-27","2007-11-27"]
["UN462_0310","Connect Devices @ Undulator #12","2007-11-16","2007-11-16"]
["UN462_0315","Test Devices @ Undulator #12","2007-11-19","2007-11-19"]
["UN462_0320","Connect Devices @ Undulator #11","2007-11-12","2007-11-12"]
["UN462_0325","Test Devices @ Undulator #11","2007-11-13","2007-11-13"]
["UN462_0330","Connect Devices @ Undulator #10","2007-11-06","2007-11-06"]
["UN462_0335","Test Devices @ Undulator #10","2007-11-07","2007-11-07"]
["UN462_0340","Connect Devices @ Undulator #9","2007-10-31","2007-10-31"]
["UN462_0345","Test Devices @ Undulator #9","2007-11-01","2007-11-01"]
["UN462_0350","Connect Devices @ Undulator #8","2007-10-25","2007-10-25"]
["UN462_0355","Test Devices @ Undulator #8","2007-10-26","2007-10-26"]
["UN462_0360","Connect Devices @ Undulator #7","2007-10-19","2007-10-19"]
["UN462_0365","Test Devices @ Undulator #7","2007-10-22","2007-10-22"]
["UN462_0370","Connect Devices @ Undulator #6","2007-10-15","2007-10-15"]
["UN462_0375","Test Devices @ Undulator #6","2007-10-16","2007-10-16"]
["UN462_0380","Connect Devices @ Undulator #5","2007-10-09","2007-10-09"]
["UN462_0385","Test Devices @ Undulator #5","2007-10-10","2007-10-10"]
["UN462_0390","Connect Devices @ Undulator #4","2007-10-03","2007-10-03"]
["UN462_0395","Test Devices @ Undulator #4","2007-10-04","2007-10-04"]
["UN462_0400","Connect Devices @ Undulator #3","2007-09-27","2007-09-27"]
["UN462_0405","Test Devices @ Undulator #3","2007-09-28","2007-09-28"]
["UN462_0410","Connect Devices @ Undulator #2","2007-09-24","2007-09-24"]
["UN462_0415","Test Devices @ Undulator #2","2007-09-25","2007-09-25"]
["UN462_0420","Connect Devices @ Undulator #1","2007-09-24","2007-09-24"]
["UN462_0425","Test Devices @ Undulator #1","2007-09-25","2007-09-25"]
["UN462_0430","Connect Devices @ Short Break Section","2007-08-30","2007-08-30"]
["UN462_0435","Test Devices @ Short Break Section","2007-08-31","2007-08-31"]
["UN462_0440","Connect Devices @ Long Break Section","2007-09-07","2007-09-07"]
["UN462_0445","Test Devices @ Long Break Section","2007-09-10","2007-09-10"]
["UN462_0450","Connect Devices @ Entrance Section","2007-09-07","2007-09-07"]
["UN462_0455","Test Devices @ Entrance Section","2007-09-10","2007-09-10"]
["UN462_0460","Connect Devices @ Exit Section","2007-08-30","2007-08-30"]
["UN462_0465","Test Devices @ Exit Section","2007-08-31","2007-08-31"]
["UN462_0500","Test Devices Under Vacuum","2008-04-29","2008-04-29"]
["UN46_00012","LDB Design","2005-08-03","2006-05-18"]
["UN46_00030","Mechanical Analysis LDB","2006-05-19","2006-06-02"]
["UN46_00050","LDB Final Design","2006-06-05","2006-06-16"]
["UN46_00052","Final LDB Design Review","2006-06-19","2006-06-23"]
["UN46_00060","LDB Design Complete","2006-06-26","2006-06-23"]
["UN46_00200","Bid Process LDB","2006-09-11","2006-10-13"]
["UN46_00202","Evaluate Bid LDB","2006-10-16","2006-10-17"]
["UN46_00205","AWARD: LDB Valve (11)","2006-10-18","2006-10-19"]
["UN46_00206","AWARD: LDB Valve (2)","2006-10-18","2006-10-19"]
["UN46_00210","AWARD: LDB Chamber Weldment Assembly","2006-10-18","2006-10-19"]
["UN46_00211","AWARD: LDB Chamber Weldment Assembly (1)","2006-10-18","2006-10-19"]
["UN46_00215","AWARD: LDB Valve (11) Sppt","2006-10-18","2006-10-19"]
["UN46_00217","AWARD: LDB Chamber Weldment Assembly Sppt","2006-10-18","2006-10-19"]
["UN46_00240","AWARD: LDB Pump Manifold","2006-10-18","2006-10-19"]
["UN46_00241","AWARD: LDB Pump Manifold (1)","2006-10-18","2006-10-19"]
["UN46_00245","AWARD: LDB Pump Manifold Sppt","2006-10-18","2006-10-19"]
["UN46_00250","AWARD: LDB Ion Pump","2006-10-18","2006-10-19"]
["UN46_00251","AWARD: LDB Ion Pump (1)","2006-10-18","2006-10-19"]
["UN46_00255","AWARD: LDB Ion Pump Sppt","2006-10-18","2006-10-19"]
["UN46_00310","AWARD: LDB Chamber Support","2006-10-18","2006-10-19"]
["UN46_00311","AWARD: LDB Chamber Support (1)","2006-10-20","2006-10-23"]
["UN46_00315","AWARD: LDB Chamber Support Sppt","2006-10-18","2006-10-19"]
["UN46_00320","AWARD: LDB Ion Pump Support","2006-10-18","2006-10-19"]
["UN46_00321","AWARD: LDB Ion Pump Support (1)","2006-10-18","2006-10-19"]
["UN46_00325","AWARD: LDB Ion Pump Support Sppt","2006-10-18","2006-10-19"]
["UN46_00340","AWARD: Long Diagnostic Break Assembly","2006-10-20","2006-10-19"]
["UN46_00350","Rec: LDB Valve (2)","2006-10-20","2006-12-18"]
["UN46_00351","Rec: LDB Valve (2)","2006-10-20","2007-01-02"]
["UN46_00400","Rec: LDB Chamber Weldment Assembly","2006-10-20","2006-12-18"]
["UN46_00401","Rec: LDB Chamber Weldment Assembly (1)","2006-10-20","2007-01-02"]
["UN46_00402","Rec: LDB Pump Manifold (11)","2006-10-20","2006-12-18"]
["UN46_00403","Rec: LDB Pump Manifold (1)","2006-10-20","2007-01-02"]
["UN46_00404","Rec: LDB Ion Pump (11)","2006-10-20","2006-12-18"]
["UN46_00405","Rec: LDB Ion Pump (1)","2006-10-20","2007-01-02"]
["UN46_00406","Rec: LDB Chamber Support (11)","2006-10-20","2006-12-18"]
["UN46_00407","Rec: LDB Chamber Support (1)","2006-10-24","2007-01-04"]
["UN46_00408","Rec: LDB Ion Pump Support (11)","2006-10-20","2006-12-18"]
["UN46_00409","Rec: LDB Ion Pump Support (1)","2006-10-20","2007-01-02"]
["UN46_00410","QA Production Lot LDB","2006-12-19","2007-01-10"]
["UN46_00420","Approve Production Lot LDB","2007-01-11","2007-01-15"]
["UN46_00430","Clean LDB","2007-01-16","2007-01-25"]
["UN46_00440","Bake LDB","2007-01-26","2007-02-01"]
["UN46_00470","Prepare Long Diagnostic Break for Shipment","2007-02-02","2007-02-08"]
["UN46_00480","Pack Long Diagnostic Break for Shipping","2007-02-09","2007-02-15"]
["UN46_00490","Ship to Slac LDB","2007-02-16","2007-02-15"]
["UN46_00500","Transmit Design and Drawings to SLAC","2007-02-16","2007-02-22"]
["UN46_00502","RFI: Long Diagnostic Break Assembly","2007-02-23","2007-02-22"]
["UN46_00510","Develop Installation Plan LDB","2007-02-16","2007-02-26"]
["UN46_00520","Review installation Plan LDB","2007-02-27","2007-03-05"]
["UN46_00530","Long Diagnostic Break Assembly Arrive at SLAC","2007-07-03","2007-07-17"]
["UN46_00540","Install Long Break Section Components","2007-08-23","2007-09-06"]
["UN46_00610","Commission - Long Diag Break Assy","2007-09-07","2007-09-13"]
["UN47_00010","Specification Ent Sec","2006-04-03","2006-04-14"]
["UN47_00020","Prelim Design  Ent Sec","2006-04-17","2006-05-19"]
["UN47_00030","Mechanical Analysis  Ent Sec","2006-05-22","2006-06-05"]
["UN47_00040","Prelim Design Review  Ent Sec","2006-06-06","2006-06-12"]
["UN47_00050","Final Design  Ent Sec","2006-06-13","2006-06-26"]
["UN47_00060","Design Complete  Ent Sec","2006-06-27","2006-06-26"]
["UN47_00250","Bid Process Bid Pkg","2006-09-11","2006-10-13"]
["UN47_00251","Evaluate Bids - Entrance Section","2006-10-16","2006-10-18"]
["UN47_00260","AWARD: Standard Entrance Chamber","2006-10-19","2006-10-23"]
["UN47_00261","AWARD: Standard Entrance Chamber (1)","2006-10-19","2006-10-23"]
["UN47_00265","AWARD: Standard Entrance Chamber Sppt","2006-10-19","2006-10-23"]
["UN47_00270","AWARD: Entrance Bellows","2006-10-19","2006-10-23"]
["UN47_00271","AWARD: Entrance Bellows (2)","2006-10-19","2006-10-23"]
["UN47_00275","AWARD: Entrance Bellows Sppt","2006-10-19","2006-10-23"]
["UN47_00280","AWARD: Entrance Upstream Chamber","2006-10-19","2006-10-23"]
["UN47_00281","AWARD: Entrance Upstream Chamber (1)","2006-10-19","2006-10-23"]
["UN47_00285","AWARD: Entrance Upstream Chamber Sppt","2006-10-19","2006-10-23"]
["UN47_00300","AWARD: Pump Manifold","2006-10-19","2006-10-23"]
["UN47_00301","AWARD: Pump Manifold (1)","2006-10-19","2006-10-23"]
["UN47_00305","AWARD: Pump Manifold Sppt","2006-10-19","2006-10-23"]
["UN47_00310","AWARD: Ion Pump (1)","2006-10-19","2006-10-23"]
["UN47_00311","AWARD: Ion Pump (2)","2006-10-19","2006-10-23"]
["UN47_00315","AWARD: Ion Pump (1) Sppt","2006-10-19","2006-10-23"]
["UN47_00320","AWARD: Ion Pump Controller (1)","2006-10-19","2006-10-23"]
["UN47_00321","AWARD: Ion Pump Controller (1)","2006-10-19","2006-10-23"]
["UN47_00325","AWARD: Ion Pump Controller (1) Sppt","2006-10-19","2006-10-23"]
["UN47_00330","AWARD: Ion Pump Cable (1)","2006-10-19","2006-10-23"]
["UN47_00331","AWARD: Ion Pump Cable (2)","2006-10-19","2006-10-23"]
["UN47_00335","AWARD: Ion Pump Cable (1) Sppt","2006-10-19","2006-10-23"]
["UN47_00340","AWARD: Gate Valve (1)","2006-10-19","2006-10-23"]
["UN47_00341","AWARD: Gate Valve (1)","2006-10-19","2006-10-23"]
["UN47_00342","AWARD:  Turbo Pump","2006-10-19","2006-10-23"]
["UN47_00343","AWARD:  Turbo Pump SPPT","2006-10-19","2006-10-23"]
["UN47_00344","AWARD:  Roughing Pump","2006-10-19","2006-10-23"]
["UN47_00345","AWARD: Gate Valve (1) Sppt","2006-10-19","2006-10-23"]
["UN47_00346","AWARD:  Roughing Pump SPPT","2006-10-19","2006-10-23"]
["UN47_00347","AWARD:  Pneumatic Gate Valve","2006-10-19","2006-10-23"]
["UN47_00348","AWARD:  Pneumatic Gate Valve SPPT","2006-10-19","2006-10-23"]
["UN47_00349","AWARD:  Pneumatic Gate Valve","2006-10-24","2006-10-26"]
["UN47_00350","AWARD: Valves (1)","2006-10-19","2006-10-23"]
["UN47_00351","AWARD: Valves (1)","2006-10-19","2006-10-23"]
["UN47_00355","AWARD: Valves (1) Sppt","2006-10-19","2006-10-23"]
["UN47_00360","AWARD: Vacuum Gauge (1)","2006-10-19","2006-10-23"]
["UN47_00361","AWARD: Vacuum Gauge (1)","2006-10-19","2006-10-23"]
["UN47_00365","AWARD: Vacuum Gauge (1) Sppt","2006-10-19","2006-10-23"]
["UN47_00380","AWARD: RGA (1)","2006-10-19","2006-10-23"]
["UN47_00381","AWARD: RGA (1)","2006-10-19","2006-10-23"]
["UN47_00385","AWARD: RGA (1) Sppt","2006-10-19","2006-10-23"]
["UN47_00390","AWARD: Standard Entrance Chamber Support","2006-10-19","2006-10-23"]
["UN47_00391","AWARD: Standard Entrance Chamber Support (1)","2006-10-19","2006-10-23"]
["UN47_00395","AWARD: Standard Entrance Chamber Support Sppt","2006-10-19","2006-10-23"]
["UN47_00400","AWARD: Entrance Chamber Mount","2006-10-19","2006-10-23"]
["UN47_00401","AWARD: Entrance Chamber Mount (1)","2006-10-19","2006-10-23"]
["UN47_00405","AWARD: Entrance Chamber Mount Sppt","2006-10-19","2006-10-23"]
["UN47_00410","AWARD: Ion Pump Support (1)","2006-10-19","2006-10-23"]
["UN47_00411","AWARD: Ion Pump Support (1)","2006-10-19","2006-10-23"]
["UN47_00415","AWARD: Ion Pump Support (1) Sppt","2006-10-19","2006-10-23"]
["UN47_00420","AWARD: Gate Valve Support","2006-10-19","2006-10-23"]
["UN47_00421","AWARD: Gate Valve Support (1)","2006-10-19","2006-10-23"]
["UN47_00425","AWARD: Gate Valve Support Sppt","2006-10-19","2006-10-23"]
["UN47_00430","AWARD: RGA Support","2006-10-19","2006-10-23"]
["UN47_00431","AWARD: RGA Support (1)","2006-10-19","2006-10-23"]
["UN47_00435","AWARD: RGA Support Sppt","2006-10-19","2006-10-23"]
["UN47_00440","AWARD: Entrance Section Assembly and Support","2006-10-24","2006-10-23"]
["UN47_00460","Rec:  Standard Entrance Chamber","2006-10-24","2006-12-20"]
["UN47_00461","Rec: Standard Entrance Chamber","2006-10-24","2007-01-04"]
["UN47_00462","Rec: Entrance Bellows","2006-10-24","2006-12-20"]
["UN47_00463","Rec: Entrance Bellows","2006-10-24","2007-01-04"]
["UN47_00464","Rec: Entrance Upstream Chamber","2006-10-24","2006-12-20"]
["UN47_00465","Rec: Entrance Upstream Chamber","2006-10-24","2007-01-04"]
["UN47_00466","Rec: Pump Manifold","2006-10-24","2006-12-20"]
["UN47_00467","Rec: Pump Manifold","2006-10-24","2007-01-04"]
["UN47_00468","Rec: Ion Pump","2006-10-24","2006-12-20"]
["UN47_00469","Rec: Ion Pump","2006-10-24","2007-01-04"]
["UN47_00470","Rec: Ion Pump Controller","2006-10-24","2006-12-20"]
["UN47_00471","Rec: Ion Pump Controller","2006-10-24","2007-01-04"]
["UN47_00472","Rec: Ion Pump Cable","2006-10-24","2006-12-20"]
["UN47_00473","Rec: Ion Pump Cable","2006-10-24","2007-01-04"]
["UN47_00474","Rec: Gate Valve","2006-10-24","2006-12-20"]
["UN47_00475","Rec: Gate Valve","2006-10-24","2007-01-04"]
["UN47_00476","Rec: Valve","2006-10-24","2006-12-20"]
["UN47_00477","Rec: Valve","2006-10-24","2007-01-04"]
["UN47_00478","Rec: Vacuum Gauge","2006-10-24","2006-12-20"]
["UN47_00479","Rec: Vacuum Gauge","2007-01-02","2007-02-28"]
["UN47_00480","Rec: RGA","2006-10-24","2006-12-20"]
["UN47_00481","Rec: RGA","2006-10-24","2007-01-04"]
["UN47_00482","Rec: Entrance Chamber Support","2006-10-24","2006-12-20"]
["UN47_00483","Rec: Entrance Chamber Support","2006-10-24","2007-01-04"]
["UN47_00484","Rec: Chamber Mount","2006-10-24","2006-12-20"]
["UN47_00485","Rec: Chamber Mount","2006-10-24","2007-01-04"]
["UN47_00486","Rec: Ion Pump Support","2006-10-24","2006-12-20"]
["UN47_00487","Rec: Ion Pump Support","2006-10-24","2007-01-04"]
["UN47_00488","Rec: Gate Valve Support","2006-10-24","2006-12-20"]
["UN47_00489","Rec: Gate Valve Support","2006-10-24","2007-01-04"]
["UN47_00490","Rec: RGA Support","2006-10-24","2006-12-20"]
["UN47_00491","Rec: RGA Support","2007-01-02","2007-02-28"]
["UN47_00492","Rec:  Turbo Pump","2006-10-24","2006-12-20"]
["UN47_00493","Rec:  Roughing Pump","2006-10-24","2006-12-20"]
["UN47_00494","Rec:  Pneumatic Gate Valve","2006-10-24","2006-12-20"]
["UN47_00495","Rec:  Pneumatic Gate Valve","2006-10-27","2006-12-26"]
["UN47_00498","QA of Entrance Section Components","2006-12-21","2007-01-09"]
["UN47_00499","Clean Ent Sec","2007-01-10","2007-01-23"]
["UN47_00500","Bake Ent Sec","2007-01-24","2007-02-06"]
["UN47_00510","Assemble Entrance Section Components","2007-02-07","2007-03-06"]
["UN47_00520","Assembly Test Ent Sec","2007-03-07","2007-03-08"]
["UN47_00530","Prepare Ent Sec Assembly & Support  for Shipme","2007-03-09","2007-03-15"]
["UN47_00540","Pack Ent Sec Assembly & Support for Shipment","2007-03-16","2007-03-22"]
["UN47_00550","Ship  Ent Sec to Slac","2007-03-23","2007-03-22"]
["UN47_00560","Transmit  Ent Sec Design a& Drawings to SLAC","2007-03-23","2007-03-29"]
["UN47_00562","RFI: Entrance Section Assembly and Support","2007-03-30","2007-03-29"]
["UN47_00570","Develop Installation Plan Ent Sec","2007-03-23","2007-03-30"]
["UN47_00580","Review installation Plan Ent Sec","2007-04-02","2007-04-06"]
["UN47_00590","Entrance Section Assy & Support Arrive at SLAC","2007-03-30","2007-04-12"]
["UN47_00595","Install Entrance Section Components","2007-08-30","2007-09-06"]
["UN47_00670","Commission - Entrance Section Assy","2007-09-07","2007-09-13"]
["UN48_00010","Specification Exit Sec","2006-04-03","2006-04-14"]
["UN48_00020","Prelim Prototype Design Exit Sec","2006-04-17","2006-05-12"]
["UN48_00030","Mechanical Analysis Exit Sec","2006-05-15","2006-05-26"]
["UN48_00040","Prelim Prototype Design Review Exit Sec","2006-05-30","2006-06-05"]
["UN48_00050","Final Exit Sec Design","2006-06-06","2006-06-19"]
["UN48_00060","Design Complete Exit Sec","2006-06-20","2006-06-19"]
["UN48_00250","Bid Process Exit Sec","2006-09-11","2006-10-13"]
["UN48_00260","AWARD: Standard Exit Chamber","2006-10-16","2006-10-18"]
["UN48_00261","AWARD: Standard Exit Chamber (1)","2006-10-16","2006-10-18"]
["UN48_00265","AWARD: Standard Exit Chamber Sppt","2006-10-16","2006-10-18"]
["UN48_00270","AWARD: Exit Bellows","2006-10-16","2006-10-18"]
["UN48_00275","AWARD: Exit Bellows Sppt","2006-10-16","2006-10-18"]
["UN48_00290","AWARD: Exit Downstream Chamber","2006-10-16","2006-10-18"]
["UN48_00291","AWARD: Exit Downstream Chamber (1)","2006-10-16","2006-10-18"]
["UN48_00295","AWARD: Exit Downstream Chamber Sppt","2006-10-16","2006-10-18"]
["UN48_00300","AWARD: Exit Pump Manifold","2006-10-16","2006-10-18"]
["UN48_00305","AWARD: Exit Pump Manifold Sppt","2006-10-16","2006-10-18"]
["UN48_00310","AWARD: Ion Pump","2006-10-16","2006-10-18"]
["UN48_00315","AWARD: Ion Pump Sppt","2006-10-16","2006-10-18"]
["UN48_00320","AWARD: Turbo Pump","2006-10-16","2006-10-18"]
["UN48_00321","Award: Turbo Pump","2006-10-16","2006-10-18"]
["UN48_00325","AWARD: Turbo Pump Sppt","2006-10-16","2006-10-18"]
["UN48_00326","AWARD:  Pneumatic Gate Valve","2006-10-16","2006-10-18"]
["UN48_00327","AWARD:  Pneumatic Gate Valve SPPT","2006-10-16","2006-10-18"]
["UN48_00330","AWARD: Roughing Pump","2006-10-16","2006-10-18"]
["UN48_00331","AWARD: Roughing Pump","2006-10-19","2006-10-23"]
["UN48_00335","AWARD: Roughing Pump Sppt","2006-10-16","2006-10-18"]
["UN48_00340","AWARD: Gate Valve","2006-10-16","2006-10-18"]
["UN48_00345","AWARD: Gate Valve Sppt","2006-10-16","2006-10-18"]
["UN48_00350","AWARD: Valves","2006-10-16","2006-10-18"]
["UN48_00355","AWARD: Valves Sppt","2006-10-16","2006-10-18"]
["UN48_00360","AWARD: Vacuum Gauge","2006-10-16","2006-10-18"]
["UN48_00365","AWARD: Vacuum Gauge Sppt","2006-10-16","2006-10-18"]
["UN48_00380","AWARD: RGA","2006-10-16","2006-10-18"]
["UN48_00385","AWARD: RGA Sppt","2006-10-16","2006-10-18"]
["UN48_00390","AWARD: Standard Exit Chamber Support (2)","2006-10-16","2006-10-18"]
["UN48_00391","AWARD: Standard Exit Chamber Support (1)","2006-10-16","2006-10-18"]
["UN48_00395","AWARD: Standard Exit Chamber Support (2) Sppt","2006-10-16","2006-10-18"]
["UN48_00400","AWARD: Exit Downstream Chamber Support (2)","2006-10-16","2006-10-18"]
["UN48_00401","AWARD: Exit Downstream Chamber Support (1)","2006-10-16","2006-10-18"]
["UN48_00405","AWARD: Exit Downstream Chamber Support (2) Sppt","2006-10-16","2006-10-18"]
["UN48_00410","AWARD: Ion Pump Support (2)","2006-10-16","2006-10-18"]
["UN48_00415","AWARD: Ion Pump Support (2) Sppt","2006-10-16","2006-10-18"]
["UN48_00420","AWARD: Gate Valve Support (1)","2006-10-16","2006-10-18"]
["UN48_00425","AWARD: Gate Valve Support (1) Sppt","2006-10-16","2006-10-18"]
["UN48_00430","AWARD: RGA Support (1)","2006-10-16","2006-10-18"]
["UN48_00435","AWARD: RGA Support (1) Sppt","2006-10-16","2006-10-18"]
["UN48_00440","AWARD: Complete Exit Sec","2006-10-19","2006-10-18"]
["UN48_00460","Rec: Standard Exit Chamber","2006-10-19","2006-12-15"]
["UN48_00461","Rec.: Standard Exit Chamber","2006-10-19","2006-12-15"]
["UN48_00462","Rec: Exit Bellows","2006-10-19","2006-12-15"]
["UN48_00463","Rec: Exit Downstream Chamber","2006-10-19","2006-12-15"]
["UN48_00464","Rec: Exit Downstream Chamber","2006-10-19","2006-12-15"]
["UN48_00465","Rec: Exit Pump Manifold","2006-10-19","2006-12-15"]
["UN48_00466","Rec: Ion Pump","2006-10-19","2006-12-15"]
["UN48_00467","Rec: Turbo Pump","2006-10-19","2006-12-15"]
["UN48_00468","Rec: Turbo Pump","2006-10-19","2006-12-15"]
["UN48_00469","Rec: Roughing Pump","2006-10-19","2006-12-15"]
["UN48_00470","Rec: Roughing Pump","2006-10-24","2007-01-04"]
["UN48_00471","Rec:  Pneumatic Gate Valve","2006-10-19","2006-12-15"]
["UN48_00472","Rec: Gate Valve","2006-10-19","2006-12-15"]
["UN48_00473","Rec: Valve","2006-10-19","2006-12-15"]
["UN48_00474","Rec: Vacuum Gauge","2006-10-19","2006-12-15"]
["UN48_00475","Rec: RGA","2006-10-19","2006-12-15"]
["UN48_00476","Rec: Standard Exit Chamber Support","2006-10-19","2006-12-15"]
["UN48_00477","Rec: Standard Exit Chamber Support","2006-10-19","2006-12-15"]
["UN48_00478","Rec: Exit Downstream Chamber Support","2006-10-19","2006-12-15"]
["UN48_00479","Rec: Exit Downstream Chamber Support","2006-10-19","2006-12-15"]
["UN48_00480","Rec: Ion Pump Support","2006-10-19","2006-12-15"]
["UN48_00481","Rec: Gate Valve Support","2006-10-19","2006-12-15"]
["UN48_00482","Rec: RGA Support","2006-10-19","2006-12-15"]
["UN48_00488","QA of Exit Section Components","2006-12-18","2007-01-04"]
["UN48_00489","Approve Production Exit Sec","2007-01-05","2007-01-09"]
["UN48_00490","Clean Exit Sec","2007-01-10","2007-01-19"]
["UN48_00500","Bake Exit Sec","2007-01-22","2007-02-02"]
["UN48_00510","Assemble Exit Section Components","2007-02-05","2007-03-05"]
["UN48_00520","Assembly Test Exit Sec","2007-03-06","2007-03-23"]
["UN48_00530","Prepare Exit Sec Assembly & Support  for Ship","2007-03-26","2007-04-02"]
["UN48_00540","Pack Exit Sec Assembly and Support for Shipmen","2007-04-03","2007-04-10"]
["UN48_00550","Ship  Exit Sec to Slac","2007-04-11","2007-04-10"]
["UN48_00560","Transmit Exit Sec Design & Drawings to SLAC","2007-04-11","2007-04-18"]
["UN48_00562","RFI: Exit Section Assembly and Support","2007-04-19","2007-04-18"]
["UN48_00570","Develop Exit Sec Installation Plan","2007-04-11","2007-04-23"]
["UN48_00580","Review Exit Sec Installation Plan","2007-04-24","2007-05-01"]
["UN48_00590","Exit Section Assembly & Support  Arrive at SLAC","2007-04-11","2007-04-23"]
["UN48_00595","Install Exit Section Components","2007-08-23","2007-08-29"]
["UN48_00600","Install Pumps","2007-08-30","2007-09-06"]
["UN48_00605","Make Up Vacuum","2008-01-09","2008-01-22"]
["UN48_00610","Make Up Vacuum","2007-08-30","2007-09-13"]
["UN48_00620","Pump Down","2008-04-08","2008-04-21"]
["UN48_00625","Leak Test","2008-04-22","2008-04-28"]
["UN48_00630","Controls System Checkout","2008-04-29","2008-05-12"]
["UN48_00635","System Checkout","2008-05-13","2008-05-27"]
["UN48_00670","Commission - Exit Section Assy","2007-08-30","2007-09-07"]
["UN48_D200","Cell Conceptual Layout","2005-05-02","2005-06-30"]
["UN48_D201","System Conceptual Layout","2005-07-01","2005-08-31"]
["UN48_D202","Update Vacuum Chamber","2006-08-04","2006-08-24"]
["UN48_D203","Update Bellows","2006-04-03","2006-04-21"]
["UN48_D204","Update SDB","2006-06-22","2006-07-13"]
["UN48_D205","Update LDB","2006-06-19","2006-07-10"]
["UN48_D206","Update Entrance Section","2006-06-27","2006-07-11"]
["UN48_D207","Update Exit Section","2006-06-20","2006-07-03"]
["UN48_D208","Update ULD Station","2005-09-01","2005-09-22"]
["UN48_D209","Update EOU","2006-07-13","2006-08-02"]
["UN48_D210","Update RFBPM","2006-07-06","2006-07-26"]
["UN48_D211","Update Charge Monitor","2006-12-06","2006-12-19"]
["UN48_D212","Update Cherenkov Detector","2005-12-08","2006-01-06"]
["UN48_D213","Update RDM","2006-11-09","2006-11-22"]
["UN48_D214","System Layout Clean-up","2007-01-18","2007-02-28"]
["UN48_D215","Update Undulator Magnet","2005-09-01","2005-09-22"]
["UN48_D216","Update Movers","2006-12-19","2007-01-17"]
["UN48_D217","Update Fixed Support","2005-09-01","2005-09-22"]
["UN48_D218","Update Quads","2005-09-01","2005-09-22"]
["UN49_00010","Specification of Baking Station (System)","2006-06-22","2006-07-06"]
["UN49_00020","Prelim Design of Baking Station","2006-07-07","2006-07-27"]
["UN49_00030","Prelim Baking Station Design Review","2006-07-28","2006-07-31"]
["UN49_00040","Final Design of Baking Station","2006-08-01","2006-08-07"]
["UN49_00050","Design Complete Baking Station","2006-08-08","2006-08-07"]
["UN49_00060","Bid Package-Baking Station","2006-08-08","2006-08-10"]
["UN49_00070","Bid Package-Heater","2006-08-08","2006-08-10"]
["UN49_00080","Bid Package-Thermal Insulation","2006-08-08","2006-08-10"]
["UN49_00090","Bid Pkg: Turbo Pump Baking Station","2006-08-08","2006-08-14"]
["UN49_00100","Bid Pkg: Roughing Pump Baking Station","2006-08-08","2006-08-10"]
["UN49_00110","Bid Package-Valves Baking Station","2006-08-08","2006-08-10"]
["UN49_00120","Bid Pkg: Vacuum Gauge Baking Station","2006-08-08","2006-08-10"]
["UN49_00140","Bid Pkg: RGA Baking Station","2006-08-08","2006-08-14"]
["UN49_00150","Bid Process Baking Station","2006-08-15","2006-09-28"]
["UN49_00151","Evaluate Bids: Baking Station","2006-09-29","2006-10-03"]
["UN49_00160","AWARD: Baking Station","2006-10-04","2006-10-06"]
["UN49_00165","AWARD: Baking Station Sppt","2006-10-04","2006-10-06"]
["UN49_00170","AWARD: Heater","2006-10-04","2006-10-06"]
["UN49_00175","AWARD: Heater Sppt","2006-10-04","2006-10-06"]
["UN49_00180","AWARD: Thermal Insulation","2006-10-04","2006-10-06"]
["UN49_00185","AWARD: Thermal Insulation Sppt","2006-10-04","2006-10-06"]
["UN49_00190","AWARD: Turbo Pump","2006-10-04","2006-10-06"]
["UN49_00195","AWARD: Turbo Pump Sppt","2006-10-04","2006-10-06"]
["UN49_00200","AWARD: Roughing Pump","2006-10-04","2006-10-06"]
["UN49_00205","AWARD: Roughing Pump Sppt","2006-10-04","2006-10-06"]
["UN49_00210","AWARD: Valves","2006-10-04","2006-10-06"]
["UN49_00215","AWARD: Valves Sppt","2006-10-04","2006-10-06"]
["UN49_00220","AWARD: Vacuum Gauge","2006-10-04","2006-10-06"]
["UN49_00225","AWARD: Vacuum Gauge Sppt","2006-10-04","2006-10-06"]
["UN49_00240","AWARD: RGA","2006-10-04","2006-10-06"]
["UN49_00245","AWARD: RGA Sppt","2006-10-04","2006-10-06"]
["UN49_00250","AWARD: Complete Baking Sys","2006-10-09","2006-10-06"]
["UN49_00260","Fabrication of Baking Components","2006-10-09","2006-11-03"]
["UN49_00270","Receive Baking Components","2006-11-06","2006-11-28"]
["UN49_00280","QA of Baking Components","2006-11-29","2006-12-05"]
["UN49_00290","Integration to Baking System","2006-12-06","2007-01-04"]
["UN49_00300","Preform Bake System Testing","2007-01-05","2007-01-11"]
["UN49_00310","Transmit  Baking Sys Design & Drawings to SLAC","2007-01-12","2007-01-18"]
["UN49_00320","Complete Baking Sys","2007-01-19","2007-01-18"]
["UN501_0042","Travel End-Of-Undulator - FY05 (PED)","2005-05-02","2005-06-29",null,"2005-05-02"]
["UN501_0115","Travel SLAC Project Engineer, etc.","2005-05-02","2005-09-30",null,"2005-05-02"]
["UN502_0241","Award: ULD Vacuum Chamber (1)","2006-10-03","2006-10-09"]
["UN502_0251","AWARD: ULD Support Stand (1)","2006-10-03","2006-10-09"]
["UN502_0260","AWARD: Complete - ULD-VC","2005-05-02","2005-04-29"]
["UN502_0271","Rec: EBXPD Vacuum Chamber (1)","2006-10-10","2006-12-06"]
["UN502_0275","Rec: EBXPD Support Stand (1)","2006-10-10","2006-12-06"]
["UN502_0290","AVAIL: ULD Vacuum Chamber","2005-05-02","2005-04-29"]
["UN502_0402","AWARD: Beam Tube and Spring Contact (1)","2006-10-03","2006-10-04"]
["UN502_0414","AWARD: Main translation stage (1)","2006-10-03","2006-10-04"]
["UN502_0420","AWARD: Complete","2005-05-02","2005-04-29"]
["UN502_0432","Rec: Beam Tube and Spring Contact (1)","2006-10-05","2006-11-15"]
["UN502_0444","Rec: Main translation stage (1)","2006-10-05","2006-11-15"]
["UN502_0450","AVAIL:  ULD Positioning Mechanism","2005-05-02","2005-04-29"]
["UN502_0572","AWARD: Motorized scanner (1)","2006-10-03","2006-10-04"]
["UN502_0582","AWARD: Wire Mounting Rack (1)","2006-10-03","2006-10-04"]
["UN502_0592","AWARD: Photo electron detector (1)","2006-10-03","2006-10-04"]
["UN502_0612","Rec: Motorized Scanner (1)","2006-10-05","2006-12-01"]
["UN502_0616","Rec: Wire Rack (1)","2006-10-05","2006-12-01"]
["UN502_0619","Rec: Photo electron detector (1)","2006-10-05","2006-12-01"]
["UN502_0752","AWARD: Mirrors (1)","2006-10-03","2006-10-04"]
["UN502_0762","AWARD: Motorized shutter (upstream) (1)","2006-10-03","2006-10-04"]
["UN502_0772","AWARD: Light transport/imaging optics (vac) (1","2006-10-03","2006-10-04"]
["UN502_0782","AWARD: Motorized filter/aperture changer (1)","2006-10-03","2006-10-04"]
["UN502_0792","AWARD: Camera assembly and shielding (1)","2006-10-03","2006-10-04"]
["UN502_0800","ULD-OTR AWARDs Complete","2005-05-02","2005-04-29"]
["UN502_0811","Rec: Mirrors (1)","2006-10-05","2006-12-01"]
["UN502_0813","Rec: Motorized Shutter (upstream) (1)","2006-10-05","2006-12-01"]
["UN502_0815","Rec: Light transport/imaging optics (vac) (1)","2006-10-05","2006-12-01"]
["UN502_0819","Rec: Camera assembly and shielding (1)","2006-10-05","2006-12-01"]
["UN502_0826","Rec: Motorized filter/aperture changer (1)","2006-10-05","2006-12-01"]
["UN502_0840","Design Prototype ULD-XRID","2005-06-09","2005-08-04"]
["UN502_0850","Mechanical Analysis - ULD-XRID","2005-08-05","2005-08-23"]
["UN502_0860","Fabricate Prototype EBXPD-XRID","2005-08-24","2005-10-06"]
["UN502_0870","Test Prototype EBXPD-XRID","2005-10-07","2005-10-19"]
["UN502_0960","Design Prototype ULD-XRM","2005-05-02","2005-06-27"]
["UN502_0970","Mechanical Analysis - ULD-XRM","2005-06-28","2005-07-12"]
["UN502_0980","Fabricate Prototype ULD-XRM","2005-07-13","2005-08-17"]
["UN502_0990","Test Prototype EBXPD-XRM","2005-08-18","2005-09-01"]
["UN502_1160","Design Prototype ULD-IMG","2005-05-02","2005-05-31"]
["UN502_1170","Mechanical Analysis - ULD-IMG","2005-06-01","2005-06-08"]
["UN502_1180","Fabricate Prototype ULD-IMG","2005-06-09","2005-07-15"]
["UN502_1190","Test Prototype ULD-IMG","2005-07-18","2005-07-25"]
["UN502_1500","AWARD: Complete ULD","2005-05-02","2005-04-29"]
["UN502_1630","Ship ULD to SLAC","2005-05-02","2005-04-29"]
["UN502_1661","RFI: ULD","2005-05-02","2005-04-29"]
["UN502_1750","Commission EBXPD","2007-09-07","2007-09-20"]
["UN502_D145","Testing complete (Beam)","2005-05-02","2005-04-29"]
["UN502_D146","Testing complete (Bench)","2005-05-02","2005-04-29"]
["UN502_D154","OTR prototype parts arrive","2005-05-02","2005-04-29"]
["UN502_D166","Define design concept for screen survival tests","2006-07-03","2006-07-31"]
["UN502_D167","Design test assembly for screen survival tests","2006-08-01","2006-08-14"]
["UN502_D168","Purchase test assbly parts screen survival tests","2006-08-15","2006-08-21"]
["UN502_D169","Fabricate test assbly parts for scr surv tst","2006-08-22","2006-08-30"]
["UN502_D170","Assemble test assembly screen survival tests","2006-08-31","2006-09-11"]
["UN502_D171","Ship to SLAC screen survival tests","2006-09-12","2006-09-20"]
["UN502_D172","Test assembly scr surv tst arrives at SLAC","2006-09-21","2006-09-20"]
["UN502_D178","Vacuum test document complete","2006-09-07","2006-09-06"]
["UN502_DA76","Perform vacuum tests Part II","2006-07-03","2006-07-11"]
["UN502_DA77","Assemble & report test results vacuum test PII","2006-07-12","2006-09-06"]
["UN503_0040","Preliminary Design - PRPT HPPD","2005-07-25","2005-08-19"]
["UN503_0050","Design Analysis - PRPT HPPD","2005-08-22","2005-08-26"]
["UN503_0060","Design Review - PRPT HPPD","2005-08-29","2005-09-07"]
["UN503_0070","Final Design - PRPT HPPD","2005-09-08","2005-09-28"]
["UN503_0090","Prepare Bid Package - ODR Module","2006-04-13","2006-05-17"]
["UN503_0100","Prepare Bid Package - Laser Wire Module","2006-04-13","2006-05-17"]
["UN503_0110","Bid Process - PRPT HPPD","2006-05-18","2006-06-15"]
["UN503_0120","Evaluate Bids - PRPT HPPD","2006-06-16","2006-06-27"]
["UN503_0130","AWARD: ODR Module","2006-10-02","2006-10-04"]
["UN503_0135","AWARD: ODR Module Sppt","2006-10-02","2006-10-04"]
["UN503_0140","AWARD:  Laser Wire Module","2006-10-05","2006-10-11"]
["UN503_0141","RCV:  PRPT HPPD Components","2006-10-12","2006-10-12"]
["UN503_0142","Determine Suitable Test Facility - HPPD","2006-04-13","2006-04-14"]
["UN503_0145","AWARD:  Laser Wire Module Sppt","2006-10-05","2006-10-11"]
["UN503_0150","Intregrate Controls - HPPD","2006-10-13","2006-11-02"]
["UN503_0152","Assemble Test Station - HPPD","2006-04-17","2006-05-02"]
["UN503_0160","Perform Module Testing - HPPD","2006-11-03","2006-12-04"]
["UN503_0170","Test Measurements Review meeting - HPPD","2006-12-05","2006-12-11"]
["UN503_0180","HPPD Testing Complete","2006-12-12","2006-12-11"]
["UN503_0770","Specification of HPPD","2005-05-02","2005-05-11"]
["UN503_0780","Analysis and Simulations - HPPD","2005-05-12","2005-06-09"]
["UN503_0790","Literature Research - HPPD","2005-06-10","2005-07-08"]
["UN503_0800","Study Review and Recommendations - HPPD","2005-07-11","2005-07-22"]
["UN503_0810","HPPD Study Period Complete","2005-07-25","2005-07-22"]
["UN504_0010","Specification EOU","2006-01-18","2006-03-20"]
["UN504_0015","Design test Fixtures","2006-10-02","2006-10-20"]
["UN504_0017","Design Test Device","2006-10-02","2006-10-20"]
["UN504_0020","Procure and Fabrication test Fixtures","2006-10-23","2006-11-28"]
["UN504_0030","EOU Test Device Fabrication","2006-10-23","2006-11-17"]
["UN504_0040","Define EOU Device Testing Facility","2006-11-20","2006-12-01"]
["UN504_0050","Assemble Test Equipment and Station","2006-12-04","2006-12-15"]
["UN504_0060","Integrate Controls into Test station","2006-12-18","2007-01-09"]
["UN504_0070","Prototype Testing Complete","2007-02-08","2007-02-07"]
["UN504_0300","Upstream corrector / separator Specification","2006-03-21","2006-04-10"]
["UN504_0310","Upstream corrector / separator Design","2006-06-07","2006-07-12"]
["UN504_0320","Upstream corrector / separator Prototype Fabri","2006-07-13","2006-08-16"]
["UN504_0330","Upstream corrector / separator Prototype Testi","2006-08-17","2006-08-30"]
["UN504_0340","Review of Testing","2006-08-31","2006-09-07"]
["UN504_0380","Procurement Bid Package -3 mrad kicker","2006-09-08","2006-09-19"]
["UN504_0390","Procurement Bid Package -Kicker power supply","2006-09-08","2006-09-21"]
["UN504_0400","Bid Process","2006-09-22","2006-10-26"]
["UN504_0410","AWARD: 3 mrad kicker","2006-10-27","2006-10-31"]
["UN504_0420","AWARD: Kicker power supply","2006-10-27","2006-10-31"]
["UN504_0430","AWARD: Upstream Corrector/Separator","2006-11-01","2006-10-31"]
["UN504_0440","Receive Packages","2006-11-01","2007-01-08"]
["UN504_0450","QA Upstream Corrector/Separator","2007-01-09","2007-01-15"]
["UN504_0460","AVAIL: Upstream Corrector/Separator","2007-01-16","2007-01-15"]
["UN504_0470","EOU-OTR Prototype Specification","2006-04-11","2006-04-24"]
["UN504_0480","EOU-OTR Prototype Design","2006-04-25","2006-06-06"]
["UN504_0485","EOU-OTR Prototype Design Review","2006-06-07","2006-06-13"]
["UN504_0490","EOU-OTR Prototype Fabrication","2006-06-14","2006-07-19"]
["UN504_0500","EOU-OTR Prototype Testing","2007-01-10","2007-01-23"]
["UN504_0510","Review of Testing","2007-01-24","2007-02-02"]
["UN504_0550","Procurement Bid Package -Translation Assembly","2007-05-01","2007-05-07"]
["UN504_0560","Procurement Bid Package -Optical parts","2007-05-01","2007-05-07"]
["UN504_0570","Procurement Bid Package -Vacuum Vessel","2007-05-01","2007-05-07"]
["UN504_0580","Procurement Bid Package -Support Table","2007-05-01","2007-05-07"]
["UN504_0590","Procurement Bid Package -Hardware","2007-05-01","2007-05-14"]
["UN504_0600","Bid Process","2007-05-15","2007-06-26"]
["UN504_0610","AWARD: Translation Assembly w/mirrors","2007-06-27","2007-07-03"]
["UN504_0615","AWARD: Translation Assembly w/mirrors Sppt","2007-06-27","2007-07-02"]
["UN504_0620","AWARD: Optical parts","2007-06-27","2007-07-02"]
["UN504_0625","AWARD: Optical parts Sppt","2007-06-27","2007-07-02"]
["UN504_0630","AWARD: Vacuum Vessel","2007-06-27","2007-07-02"]
["UN504_0635","AWARD: Vacuum Vessel Sppt","2007-06-27","2007-07-02"]
["UN504_0640","AWARD: Support Table","2007-06-27","2007-07-02"]
["UN504_0645","AWARD: Support Table Sppt","2007-06-27","2007-07-02"]
["UN504_0650","AWARD: Hardware","2007-06-27","2007-07-02"]
["UN504_0655","AWARD: Hardware Sppt","2007-06-27","2007-07-02"]
["UN504_0660","AWARD: EOU ODR Assembly","2007-07-05","2007-07-03"]
["UN504_0670","Receive Packages","2007-07-05","2007-09-13"]
["UN504_0680","QA EOU ODR Assembly","2007-09-14","2007-09-20"]
["UN504_0690","AVAIL: EOU ODR Assembly","2007-09-21","2007-09-20"]
["UN504_0700","EOU-XRM Prototype Specification","2006-04-25","2006-05-08"]
["UN504_0710","EOU-XRM Prototype Design","2006-07-13","2006-08-30"]
["UN504_0720","EOU-XRM Prototype Fabrication","2006-08-31","2006-10-12"]
["UN504_0730","EOU-XRM Prototype Testing","2007-01-10","2007-01-25"]
["UN504_0740","Review of Testing","2007-01-26","2007-02-06"]
["UN504_0780","Procurement Bid Package -Translation Assembly","2007-02-07","2007-02-15"]
["UN504_0790","Procurement Bid Package -Rotary Assembly","2007-02-07","2007-02-15"]
["UN504_0800","Procurement Bid Package -X-Ray Optics","2007-02-07","2007-02-15"]
["UN504_0810","Procurement Bid Package -Detector & Visible Op","2007-02-07","2007-02-15"]
["UN504_0820","Procurement Bid Package -Vacuum Vessel","2007-02-07","2007-02-15"]
["UN504_0830","Procurement Bid Package -Support Table & H/W","2007-02-07","2007-02-15"]
["UN504_0840","Bid Process","2007-02-16","2007-03-22"]
["UN504_0850","AWARD: Translation Assembly","2007-03-23","2007-03-27"]
["UN504_0855","AWARD: Translation Assembly Sppt","2007-03-23","2007-03-27"]
["UN504_0860","AWARD: Rotary Assembly","2007-03-23","2007-03-27"]
["UN504_0865","AWARD: Rotary Assembly Sppt","2007-03-23","2007-03-27"]
["UN504_0870","AWARD: X-Ray Optics","2007-03-23","2007-03-27"]
["UN504_0875","AWARD: X-Ray Optics Sppt","2007-03-23","2007-03-27"]
["UN504_0880","AWARD: Detector & Visible Optics Parts","2007-03-23","2007-03-27"]
["UN504_0885","AWARD: Detector & Visible Optics Parts Sppt","2007-03-23","2007-03-27"]
["UN504_0890","AWARD: Vacuum Vessel","2007-03-23","2007-03-27"]
["UN504_0895","AWARD: Vacuum Vessel Sppt","2007-03-23","2007-03-27"]
["UN504_0900","AWARD: Support Table and Hardware","2007-03-23","2007-03-28"]
["UN504_0905","AWARD: Support Table and Hardware Sppt","2007-03-23","2007-03-27"]
["UN504_0910","AWARD: EOU XRM Assembly","2007-03-29","2007-03-28"]
["UN504_0920","Receive Packages","2007-03-29","2007-05-23"]
["UN504_0930","QA EOU XRM Assembly","2007-05-24","2007-05-31"]
["UN504_0940","AVAIL: EOU XRM Assembly","2007-06-01","2007-05-31"]
["UN504_0950","EOU-XRID Prototype Specification","2006-05-09","2006-05-30"]
["UN504_0960","EOU-XRID Prototype Design","2006-08-31","2006-10-05"]
["UN504_0970","EOU-XRID Prototype Fabrication","2006-10-06","2006-11-16"]
["UN504_0980","EOU-XRID Prototype Testing","2007-01-10","2007-01-26"]
["UN504_0990","Review of Testing","2007-01-29","2007-02-07"]
["UN504_1030","Procurement Bid Package of Ion / electron gun","2007-02-08","2007-02-14"]
["UN504_1040","Procurement Bid Pkg of Ion/electron accel/optics","2007-02-08","2007-02-19"]
["UN504_1050","Procurement Bid Package of Ion/electron detect","2007-02-08","2007-02-14"]
["UN504_1060","Procurement Bid Package of Vacuum vessel","2007-02-08","2007-02-21"]
["UN504_1070","Procurement Bid Package of Translation stage","2007-02-22","2007-02-28"]
["UN504_1080","Procurement Bid Package of Support Table & H/W","2007-03-01","2007-03-07"]
["UN504_1090","Bid Process","2007-03-08","2007-04-11"]
["UN504_1100","AWARD: Ion / electron gun","2007-04-12","2007-04-16"]
["UN504_1105","AWARD: Ion / electron gun Sppt","2007-04-12","2007-04-16"]
["UN504_1110","AWARD: Ion / electron accelerator / optics","2007-04-12","2007-04-16"]
["UN504_1115","AWARD: Ion / electron accelerator / optics Sppt","2007-04-12","2007-04-16"]
["UN504_1120","AWARD: Ion / electron detector assembly","2007-04-12","2007-04-16"]
["UN504_1125","AWARD: Ion / electron detector assembly Sppt","2007-04-12","2007-04-16"]
["UN504_1130","AWARD: Vacuum vessel","2007-04-12","2007-04-16"]
["UN504_1135","AWARD: Vacuum vessel Sppt","2007-04-12","2007-04-16"]
["UN504_1140","AWARD: Translation stage","2007-04-12","2007-04-16"]
["UN504_1145","AWARD: Translation stage Sppt","2007-04-12","2007-04-16"]
["UN504_1150","AWARD: Support Table & Hardware","2007-04-12","2007-04-16"]
["UN504_1155","AWARD: Support Table & Hardware Sppt","2007-04-12","2007-04-16"]
["UN504_1160","AWARD: EOU XRID Assembly","2007-04-17","2007-04-16"]
["UN504_1170","Receive Packages","2007-04-17","2007-06-26"]
["UN504_1180","QA EOU XRID Assembly","2007-06-27","2007-07-03"]
["UN504_1190","AVAIL: EOU XRID Assembly","2007-07-05","2007-07-03"]
["UN504_1226","X-Ray Studies and Simulations","2005-06-01","2005-11-29"]
["UN504_1235","Organize literature Materials","2005-11-30","2006-01-05"]
["UN504_1240","Conduct Principles of Design Workshop","2006-01-06","2006-01-17"]
["UN504_1250","Justification Complete","2006-01-18","2006-01-17"]
["UN504_1260","PD: EOU Major Assembly Design","2006-05-31","2006-07-12"]
["UN504_1270","PD: EOU Shipping Containers","2006-07-13","2006-07-19"]
["UN504_1280","PD: EOU Supports","2006-07-13","2006-07-28"]
["UN504_1290","EOU Design Review","2006-07-31","2006-08-08"]
["UN504_1330","EOU Design Complete","2006-08-09","2006-08-08"]
["UN504_1340","Prepare EOU Bid Package","2006-08-09","2006-08-15"]
["UN504_1350","EOU Bid Process","2006-08-16","2006-09-20"]
["UN504_1360","AWARD: EOU Package","2006-09-21","2006-09-25"]
["UN504_1370","AWARD: EOU","2006-09-26","2006-09-25"]
["UN504_1410","Receive EOU Package","2006-09-26","2006-10-04"]
["UN504_1420","QA EOU Package","2006-10-05","2006-10-25"]
["UN504_1430","Approve EOU Package","2006-10-26","2006-10-30"]
["UN504_1440","Organize Parts for Assembly","2006-10-31","2006-11-06"]
["UN504_1450","Assemble EOU Package","2007-09-21","2007-10-18"]
["UN504_1460","Integrate Controls onto Assembly","2007-10-19","2007-11-13"]
["UN504_1470","Validation Testing of EOU","2007-11-14","2007-11-29"]
["UN504_1480","Pack EOU for Shipping","2007-11-30","2007-12-11"]
["UN504_1490","Write Shipping Paper Work - EOU","2007-12-12","2007-12-14"]
["UN504_1500","Ship to SLAC","2007-12-17","2007-12-14"]
["UN504_1510","Transmit Engineering Data to SLAC","2007-12-12","2007-12-18"]
["UN504_1520","Develop Installation Plan","2006-08-09","2006-08-25"]
["UN504_1530","Review installation Plan","2006-08-28","2006-09-01"]
["UN504_1540","EOU Arrive at SLAC","2007-12-17","2008-01-09"]
["UN504_1550","Pre-Align EOU at SLAC","2008-01-10","2008-02-07"]
["UN504_1560","Install EOU","2008-02-08","2008-03-07"]
["UN504_1570","Align EOU","2008-03-10","2008-03-31"]
["UN504_1580","Validate EOU","2008-04-01","2008-04-10"]
["UN504_1590","EOU Available","2008-04-11","2008-04-10"]
["UN504_1600","Integrate EOU","2008-04-11","2008-05-09"]
["UN504_1610","Test EOU","2008-05-12","2008-06-03"]
["UN504_1620","Commission EOU","2008-06-04","2008-06-23"]
["UN504_1630","Complete EOU Testing","2008-06-24","2008-06-23"]
["UN505_0172","AWARD: Copper Body Brazement (4)","2006-10-03","2006-10-05"]
["UN505_0182","AWARD: Support & Alignment Mechanism (4)","2006-10-03","2006-10-05"]
["UN505_0192","AWARD: RF Cabling (4)","2006-10-03","2006-10-05"]
["UN505_0211","Rec: Copper Body Brazement (4)","2006-10-06","2007-01-17"]
["UN505_0213","Rec: Support & Alignment Mechanism (4)","2006-10-06","2007-01-17"]
["UN505_0215","Rec: RF Cabling (4)","2006-10-06","2007-01-17"]
["UN505_0220","AWARD: Copper Body Brazement (1)","2006-10-03","2006-10-05"]
["UN505_0221","Rec: Copper Body Brazement (1)","2006-10-06","2007-01-17"]
["UN505_0225","AWARD: Support & Alignment Mechanism (1)","2006-10-03","2006-10-05"]
["UN505_0226","Rec: Support & Alignment Mechanism (1)","2006-10-06","2007-01-17"]
["UN505_0230","AWARD: Waveguide LTU (1)","2006-10-03","2006-10-05"]
["UN505_0231","Rec: Waveguide LTU (1)","2006-10-06","2007-01-17"]
["UN505_0235","AWARD: Undulator Waveguide (2)","2006-10-03","2006-10-05"]
["UN505_0236","Rec: Undulator Waveguide (2)","2006-10-06","2007-01-17"]
["UN505_0240","AWARD: Down Converter (3)","2006-10-03","2006-10-05"]
["UN505_0241","Rec: Down Converter (3)","2006-10-06","2007-01-17"]
["UN505_0245","AWARD: Local Oscillator (3)","2006-10-03","2006-10-05"]
["UN505_0246","Rec: Local Oscillator (3)","2006-10-06","2007-01-17"]
["UN505_0290","RFBPM Arrive at SLAC","2007-06-25","2007-07-09"]
["UN505_0370","Commission RFBPM","2007-07-10","2007-07-23"]
["UN505_1000","Specification and Requirements-Cavity","2005-08-16","2005-09-02"]
["UN505_1005","Specification and Requirements-LTU RFBPM","2005-09-06","2005-09-26"]
["UN505_1010","Conceptual Design of LTU Cavity","2005-09-27","2005-10-17"]
["UN505_1015","Identify Differences Between LTU & Undulator Cav","2005-10-21","2005-11-03"]
["UN505_1020","Design Review to Resolve Differences","2005-11-04","2005-11-17"]
["UN505_1025","Design Vacuum Window","2005-08-30","2005-09-02"]
["UN505_1030","Procure Window for Braze Study","2005-09-06","2005-11-28"]
["UN505_1035","Braze Study Windows","2005-10-04","2005-10-10"]
["UN505_1040","Test Window for Leak Tightness & Elect Perform.","2005-10-11","2005-10-20"]
["UN505_1045","Update Window Design","2005-10-21","2005-10-25"]
["UN505_1050","Procure Prototype RF Windows","2005-10-26","2005-12-20"]
["UN505_1055","Design Cavity","2005-08-26","2005-10-20"]
["UN505_1057","Fab Brass Body","2005-09-12","2005-09-30"]
["UN505_1058","Bench Test Brass Body","2005-10-03","2005-10-07"]
["UN505_1060","Model and Simulate","2005-08-26","2005-10-20"]
["UN505_1065","Machine First Body","2005-10-14","2005-11-29"]
["UN505_1070","Cold Test First Body","2005-11-30","2005-12-06"]
["UN505_1075","Braze First Body","2005-12-07","2005-12-13"]
["UN505_1080","Cold Test First Unit","2005-12-14","2005-12-20"]
["UN505_1085","Update Design","2006-02-21","2006-02-27"]
["UN505_1090","Machine Three Bodies","2006-02-28","2006-04-10"]
["UN505_1095","Cold Test Three Cavity Bodies","2006-04-11","2006-04-17"]
["UN505_1100","Braze Three Bodies","2006-04-18","2006-04-24"]
["UN505_1105","Cold Test Three Brazed Bodies","2006-04-25","2006-05-01"]
["UN505_1110","Select Waveguide Components","2005-09-26","2005-11-04"]
["UN505_1115","Procure Cables & Components (4)","2005-11-07","2005-12-16"]
["UN505_1120","Procure Waveguide Components","2005-11-07","2005-12-16"]
["UN505_1125","Procure Measurement Equipment","2005-11-07","2005-12-16"]
["UN505_1130","Measure RF Performance of Components","2005-12-19","2006-01-06"]
["UN505_1135","Procure Waveguide Components (3)","2006-01-09","2006-02-17"]
["UN505_1140","Test Plan, Cold Test","2005-08-30","2005-09-02"]
["UN505_1145","Design Cold Test Measurement Equipment","2005-10-03","2005-10-28"]
["UN505_1150","Procure and Fab Equipment","2005-09-19","2005-10-14"]
["UN505_1155","Assemble Cold Test Equipment","2005-10-10","2005-10-27"]
["UN505_1160","Test Plan, ITS Test","2005-09-06","2005-09-19"]
["UN505_1165","Design Spools & Supports","2005-09-20","2005-10-24"]
["UN505_1170","Procure and Fab ITS Equipment","2005-10-11","2005-12-21"]
["UN505_1175","Assemble ITS Equipment","2005-12-22","2006-01-23"]
["UN505_1180","Controls Integration in the ITS","2006-01-24","2006-02-06"]
["UN505_1185","ITS Test First Unit","2006-02-07","2006-05-01"]
["UN505_1190","Test Plan, Linac Test","2005-09-20","2005-10-03"]
["UN505_1195","Design Spools & Support Frame","2005-10-04","2005-10-31"]
["UN505_1200","Procure and Fab Linac Equipment","2005-11-01","2006-01-20"]
["UN505_1205","APS Linac Available for Installation","2006-04-25","2006-04-24"]
["UN505_1210","Assemble Linac Equipment","2006-04-28","2006-05-18"]
["UN505_1215","Controls Integration in the Linac","2006-05-05","2006-05-18"]
["UN505_1220","Linac Test Three Units","2006-05-19","2006-07-20"]
["UN505_2000","Specification and Requirements-X Band Rcvr","2005-08-16","2005-09-02"]
["UN505_2005","Model and Simulate","2005-09-12","2005-10-07"]
["UN505_2010","Specify Requirement for Purchased Units","2005-10-03","2005-10-14"]
["UN505_2015","Procure Down Converter and LO","2005-10-17","2005-12-09"]
["UN505_2020","Assemble Down Converter","2005-12-12","2005-12-21"]
["UN505_2025","Tune and Test Units","2005-12-22","2006-01-03"]
["UN505_2030","Controls Development","2006-01-04","2006-01-23"]
["UN505_2035","Review ITS Results","2006-01-24","2006-01-30"]
["UN505_2040","Update Down Converter and LO Specification","2006-01-31","2006-02-06"]
["UN505_2045","Procure Prototype Down Converter and LO(3)","2006-02-07","2006-04-03"]
["UN505_2050","Bench Test & Tune (3) DC and LO","2006-04-04","2006-04-24"]
["UN505_3000","Start RFBPM Preliminary Design","2006-05-23","2006-05-22"]
["UN505_3005","RFBPM Preliminary Design","2006-05-23","2006-06-13"]
["UN505_3006","LTU BPM Preliminary Design","2006-05-31","2006-06-13"]
["UN505_3007","Waveguide Preliminary Design","2006-05-31","2006-06-13"]
["UN505_3010","RFBPM Design Review","2006-06-14","2006-06-20"]
["UN505_3015","RFBPM Final Design","2006-06-21","2006-07-05"]
["UN505_3017","LTU BPM Final Design","2006-07-06","2006-07-19"]
["UN505_3018","Waveguide Final Design","2006-07-06","2006-07-19"]
["UN505_3020","RFBPM Design Complete","2006-07-20","2006-07-19"]
["UN505_3025","Prepare Bid of RF Cabling","2006-07-20","2006-07-21"]
["UN505_3028","Prepare Bid Waveguide","2006-07-20","2006-07-26"]
["UN505_3029","Prepare Bid Down Converter & LO","2006-07-20","2006-07-26"]
["UN505_3030","Prepare Bid of Copper Body Brazement","2006-07-20","2006-07-26"]
["UN505_3035","Prepare Bid of Support & Alignment Mechanism","2006-07-20","2006-08-02"]
["UN505_3040","Bid Process - RFBPM","2006-08-03","2006-08-04"]
["UN505_3045","Evaluate Bids - RFBPM","2006-08-07","2006-08-09"]
["UN505_3050","AWARD: Copper Body Brazement (35)","2006-08-10","2006-08-14"]
["UN505_3055","Copper Body Brazement (35) Support","2006-08-10","2006-08-14"]
["UN505_3056","AWARD: LTU BPM Brazements (8)","2006-08-10","2006-08-14"]
["UN505_3057","Rec: LTU BPM Brazements (8)","2006-08-15","2006-08-17"]
["UN505_3058","Rec: LTU BPM Waveguide (8)","2006-08-15","2006-08-17"]
["UN505_3059","Rec: LTU BPM Supports (8)","2006-08-15","2006-08-17"]
["UN505_3060","AWARD: Support & Alignment Mechanism (35)","2006-08-10","2006-08-14"]
["UN505_3065","Support & Alignment Mechanism (35) Support","2006-08-10","2006-08-14"]
["UN505_3066","Rec: Undulator Waveguide (35)","2006-08-15","2006-08-17"]
["UN505_3067","Rec: Undulator Down Converter (41)","2006-08-15","2006-08-17"]
["UN505_3068","Rec: Undulator Local Oscillator (41)","2006-08-15","2006-08-17"]
["UN505_3070","AWARD: RF Cabling (41)","2006-08-10","2006-08-14"]
["UN505_3075","RF Cabling (35) Support","2006-08-10","2006-08-14"]
["UN505_3080","AWARD: RFBPM Complete","2006-08-18","2006-08-17"]
["UN505_3085","Rec: 1st Art.Support & Alignment Mechanism","2006-08-18","2006-09-22"]
["UN505_3090","Rec: Support & Alignment Mechanism (34)","2006-08-18","2006-11-10"]
["UN505_3095","Rec: RF Cabling (35)","2006-08-18","2006-11-10"]
["UN505_3100","Rec: 1st Article Copper Body Brazement","2006-08-15","2006-11-10"]
["UN505_3105","QA: 1st Articles Copper Body Brazement/Supt","2006-11-13","2006-11-14"]
["UN505_3106","Cold Test 1st Article","2006-11-15","2006-11-17"]
["UN505_3110","Approve: 1st Articles Copper Body Brazement/Supt","2006-11-20","2006-11-21"]
["UN505_3115","Rec: Copper Body Brazement (34)","2006-11-22","2006-12-21"]
["UN505_3120","QA Production Lot","2007-01-02","2007-01-22"]
["UN505_3121","REC: LTU BPMs (6)","2006-08-18","2006-11-10"]
["UN505_3122","REC: Waveguide","2006-08-18","2006-10-17"]
["UN505_3123","Cold Test LTU BPM","2007-01-23","2007-02-01"]
["UN505_3124","Cold Test Undulator BPM","2007-01-23","2007-03-21"]
["UN505_3125","Approve Production Lot","2007-03-22","2007-03-23"]
["UN505_3126","Assemble/Test LTU BPM","2007-03-26","2007-04-04"]
["UN505_3127","Assemble/Test Undulator BPM","2007-03-26","2007-05-22"]
["UN505_3130","Pack RFBPM for Shipping","2007-05-23","2007-05-30"]
["UN505_3135","Write Shipping Paper Work-RFBPM","2007-05-31","2007-06-01"]
["UN505_3140","Transmit Engineering Data to SLAC-RFBPM","2007-05-31","2007-06-06"]
["UN505_3145","Develop Installation Plan-RFBPM","2007-06-07","2007-06-20"]
["UN505_3150","Review installation Plan-RFBPM","2007-06-21","2007-06-22"]
["UN505_3155","RFI: RFBPM","2007-06-25","2007-06-22"]
["UN505_3A58","AWARD: LTU BPM Waveguide (8)","2006-08-10","2006-08-14"]
["UN505_3A59","AWARD: LTU BPM Supports (8)","2006-08-10","2006-08-14"]
["UN505_3A66","AWARD: Undulator Waveguide (35)","2006-08-10","2006-08-14"]
["UN505_3A67","AWARD: Undulator Down Converter (41)","2006-08-10","2006-08-14"]
["UN505_3A68","AWARD: Undulator Local Oscillator (41)","2006-08-10","2006-08-14"]
["UN506_0010","Conceptual Design-BFW","2005-08-01","2005-10-24"]
["UN506_0015","Establish Engineering Requirements","2005-08-01","2005-08-26"]
["UN506_0020","Investigate Possible Radiation Damage to Compnts","2005-08-15","2005-10-10"]
["UN506_0025","Investigate Perf of Commercial Position Devices","2005-08-15","2005-08-26"]
["UN506_0030","Design Prototype Setup","2005-08-29","2005-09-26"]
["UN506_0035","Prepare Test Plan","2005-09-27","2005-10-10"]
["UN506_0040","Procure, Fab, Assemble Test Setup","2005-10-11","2006-01-20"]
["UN506_0045","Perform Tests","2006-01-23","2006-02-27"]
["UN506_0050","Write Report","2006-02-28","2006-03-13"]
["UN506_0055","Prepare ESD","2006-03-14","2006-04-10"]
["UN506_0060","Prepare Preliminary Design","2006-04-11","2006-06-06"]
["UN506_0063","Fixture and Tooling Design","2006-04-11","2006-06-06"]
["UN506_0065","Preliminary Design Review - Beam Finder Wire","2006-06-07","2006-07-05"]
["UN506_0070","Prepare Final Design Drawings & Specs","2006-07-06","2006-08-23"]
["UN506_0075","Prepare Engineering Calculations","2006-07-06","2006-08-23"]
["UN506_0080","Prepare Assembly Procedure","2006-07-06","2006-08-02"]
["UN506_0085","Prepare Acceptance Criteria List","2006-07-06","2006-08-02"]
["UN506_0090","Final Design Review - Beam Finder Wire","2006-08-24","2006-09-14"]
["UN506_0095","Incorporate Design Review Comments","2006-09-15","2006-09-28"]
["UN506_0100","Prepare Bid Pkg - Beam Finder Wire Components","2006-10-02","2006-10-06"]
["UN506_0105","Evaluate Bids - Beam Finder Wire Components","2006-11-06","2006-11-10"]
["UN506_0110","AWARD: Beam Finder Wire Components (33)","2006-11-13","2006-11-17"]
["UN506_0115","Receive Components (33) - Beam Finder Wire","2007-03-06","2007-03-19"]
["UN506_0117","Receive Beam Finder Wire Tooling","2007-03-06","2007-03-26"]
["UN506_0120","Inspect Beam Finder Wire Components","2007-03-27","2007-04-09"]
["UN506_0125","Fabricate & Final Weld","2007-04-10","2007-04-30"]
["UN506_0130","Clean","2007-05-01","2007-05-09"]
["UN506_0135","Bake Parts","2007-05-10","2007-05-16"]
["UN506_0140","Leak Check","2007-05-17","2007-05-31"]
["UN506_0145","Assemble Beam Finder Wire","2007-06-01","2007-06-21"]
["UN506_0150","Test Beam Finder Wire","2007-06-22","2007-07-13"]
["UN506_0155","Send Beam Finder Wire Documents to SLAC","2007-07-16","2007-07-20"]
["UN506_0160","RFI: Beam Finder Wire","2007-07-23","2007-07-20"]
["UN506_0200","AWARD: BFW Card Assembly (4)","2006-10-03","2006-10-09"]
["UN506_0205","Receive Components - BFW Card Assembly (4)","2007-01-23","2007-02-05"]
["UN506_0210","AWARD: Beam Finder Wire Assembly (3)","2006-10-03","2006-10-09"]
["UN506_0215","Rec: Beam Finder Wire Assembly (3)","2007-01-23","2007-02-05"]
["UN507_0010","Specification and Requirements - CM","2006-10-02","2006-10-13"]
["UN507_0020","Specification and Requirements - Cable","2006-10-16","2006-11-06"]
["UN507_0030","Purchase Cable","2006-11-07","2006-12-20"]
["UN507_0040","Preliminary Design - CM","2006-10-16","2006-11-03"]
["UN507_0050","Design Review - CM","2006-11-06","2006-11-10"]
["UN507_0060","Final Design - CM","2006-11-13","2006-12-05"]
["UN507_0070","Design Complete - CM","2006-12-06","2006-12-05"]
["UN507_0080","Prepare Bid of Charge Monitor Package","2006-12-06","2006-12-12"]
["UN507_0090","Bid Process - CM","2006-12-13","2007-01-25"]
["UN507_0100","AWARD: Charge Monitor Package (2)","2007-01-26","2007-02-01"]
["UN507_0102","AWARD: Charge Monitor Package (2) Sppt","2007-01-26","2007-02-01"]
["UN507_0105","AWARD: Charge Monitor Package (1)","2007-01-26","2007-02-01"]
["UN507_0110","AWARD: Charge Monitor","2007-02-02","2007-02-01"]
["UN507_0120","Rec: Charge Monitor Package (2)","2007-02-02","2007-03-15"]
["UN507_0125","Rec: Charge Monitor Package (1)","2007-02-02","2007-03-16"]
["UN507_0130","QA Production Lot","2007-03-16","2007-03-29"]
["UN507_0140","Approve Production Lot","2007-03-30","2007-04-03"]
["UN507_0141","Assemble Charge Monitor","2007-04-04","2007-04-06"]
["UN507_0142","Clean Charge Monitor","2007-04-09","2007-04-10"]
["UN507_0143","Leak Check Charge Monitor","2007-04-11","2007-04-12"]
["UN507_0144","Test Charge Monitor","2007-04-13","2007-04-16"]
["UN507_0150","Pack  Charge Monitor for Shipping","2007-04-17","2007-04-25"]
["UN507_0160","Write Shipping Paper Work","2007-04-26","2007-05-02"]
["UN507_0170","Transmit Engineering Data to Slac","2007-04-26","2007-05-02"]
["UN507_0180","Develop Installation Plan","2006-12-06","2007-01-02"]
["UN507_0190","Review installation Plan","2007-01-03","2007-01-11"]
["UN507_0200","Charge Monitor Arrive at SLAC","2007-05-04","2007-05-18"]
["UN507_0260","Commission  Charge Monitor","2007-08-30","2007-09-07"]
["UN507_0280","RFI - Charge Monitor","2007-05-03","2007-05-03"]
["UN508_0010","Specification and Requirements - Ch-D","2005-08-08","2005-08-19"]
["UN508_0020","Preliminary Design - Ch-D","2005-08-22","2005-10-17"]
["UN508_0030","Design Review - Ch-D","2005-10-18","2005-10-24"]
["UN508_0040","Final Design - Ch-D","2005-10-25","2005-12-07"]
["UN508_0050","Design Complete - Ch-D","2005-12-08","2005-12-07"]
["UN508_0060","Prepare Bid of Cherenkov Detector Package","2006-09-11","2006-09-20"]
["UN508_0070","Bid Process - Ch-D","2006-09-21","2006-10-25"]
["UN508_0072","Evaluate Bids - Ch-D","2006-10-26","2006-10-30"]
["UN508_0080","AWARD: Cherenkov Detector Package (35)","2006-10-31","2006-11-06"]
["UN508_0082","AWARD: Cherenkov Detector Package (4)","2006-10-31","2006-11-06"]
["UN508_0085","AWARD: Cherenkov Detector Package (35) Sppt","2006-10-31","2006-11-06"]
["UN508_0090","AWARD: Complete - Ch-D","2006-11-07","2006-11-06"]
["UN508_0095","Rec: 1st Article Cherenkov Detector","2006-11-07","2007-01-26"]
["UN508_0096","QA: 1st Article Cherenkov Detector","2007-01-29","2007-02-02"]
["UN508_0097","Approve: 1st Article Cherenkov Detector","2007-02-05","2007-02-06"]
["UN508_0100","Rec: Cherenkov Detector (34)","2007-02-07","2007-05-22"]
["UN508_0105","Rec: Cherenkov Detector (4)","2007-02-07","2007-03-21"]
["UN508_0110","QA Production Lot - Ch-D","2007-05-23","2007-06-06"]
["UN508_0120","Approve Production Lot-Ch-D","2007-06-07","2007-06-08"]
["UN508_0130","Pack  Cherenkov Detector for Shipping","2007-06-11","2007-06-15"]
["UN508_0140","Write Shipping Paper Work-Ch-D","2007-06-18","2007-06-22"]
["UN508_0150","Ship to SLAC-Ch-D","2007-06-25","2007-07-05"]
["UN508_0160","Transmit Engineering Data to Slac-Ch-D","2007-06-18","2007-06-22"]
["UN508_0170","Develop Installation Plan - Ch-D","2006-10-26","2006-11-08"]
["UN508_0180","Review installation Plan - Ch-D","2006-11-09","2006-11-20"]
["UN508_0182","RFI: Cherenkov Detector","2007-07-06","2007-07-05"]
["UN508_0190","Cherenkov Detector Arrive at SLAC","2007-07-06","2007-07-19"]
["UN508_0250","Commission  Cherenkov Detector","2007-03-22","2007-04-04"]
["UN509_0010","Specification and Requirements - RDM","2006-08-16","2006-08-29"]
["UN509_0090","Preliminary Design - RDM","2006-08-30","2006-10-04"]
["UN509_0100","Design Review - RDM","2006-10-05","2006-10-11"]
["UN509_0110","Final Design - RDM","2006-10-12","2006-11-08"]
["UN509_0120","Design Complete - RDM","2006-11-09","2006-11-08"]
["UN509_0130","Prepare Bid of RDM Package","2006-11-09","2006-11-22"]
["UN509_0140","Bid Process - RDM","2006-11-27","2007-01-16"]
["UN509_0141","Evaluate Bid - RDM","2007-01-17","2007-01-19"]
["UN509_0150","AWARD: RDM Package (1)","2007-01-22","2007-01-26"]
["UN509_0152","AWARD: RDM Package (1)","2007-01-22","2007-01-26"]
["UN509_0155","AWARD: RDM Package (1) Sppt","2007-01-22","2007-01-26"]
["UN509_0160","AWARD: of RDM Complete","2007-01-29","2007-01-26"]
["UN509_0170","Receive - RDM (1)","2007-01-29","2007-03-09"]
["UN509_0175","Rec: RDM (1)","2007-01-29","2007-03-12"]
["UN509_0180","QA - RDM","2007-03-12","2007-03-23"]
["UN509_0190","Approve - RDM","2007-03-26","2007-03-28"]
["UN509_0200","Pack RDM for Shipping","2007-03-29","2007-04-11"]
["UN509_0210","Write Shipping Paper Work - RDM","2007-04-12","2007-04-18"]
["UN509_0220","Ship RDM to SLAC","2007-04-19","2007-04-30"]
["UN509_0230","Transmit Engineering Data to Slac - RDM","2007-04-12","2007-04-18"]
["UN509_0232","RFI: Radiation Detection Monitor","2007-04-19","2007-04-18"]
["UN509_0240","Develop Installation Plan - RDM","2006-11-09","2006-12-01"]
["UN509_0250","Review installation Plan - RDM","2006-12-04","2006-12-08"]
["UN509_0260","RDM Arrive at SLAC","2007-05-01","2007-05-14"]
["UN509_0320","Commission RDM","2007-03-13","2007-03-21"]
["UN510_0100","Design RFBPM","2005-11-16","2005-12-08"]
["UN510_0110","Get Quote on RFBPM","2005-12-09","2005-12-22"]
["UN510_0120","Purchase RFBPM","2005-12-23","2006-02-24"]
["UN510_0200","Design RFBPM Support","2005-12-02","2005-12-22"]
["UN510_0210","Get Quote on RFBPM Support","2005-12-23","2006-01-09"]
["UN510_0220","Purchase RFBPM Support","2006-01-10","2006-03-10"]
["UN510_0300","Design Cherenkov Detector","2005-11-23","2005-12-15"]
["UN510_0310","Get Quote on Cherenkov Detector","2005-12-16","2005-12-30"]
["UN510_0320","Purchase Cherenkov Detector","2006-01-03","2006-03-03"]
["UN511_0010","Specification and Requirements - Sup S","2006-11-09","2006-11-22"]
["UN511_0020","Preliminary Design - Sup S","2006-11-27","2007-01-30"]
["UN511_0030","Design Review - Sup S","2007-07-30","2007-08-03"]
["UN511_0040","Final Design - Sup S","2007-08-06","2007-08-29"]
["UN511_0050","Design Complete - Sup S","2007-08-30","2007-08-29"]
["UN511_0060","Prepare Bid of Misc Shielding","2007-10-26","2007-11-08"]
["UN511_0070","Prepare Bid of Shielding Supports","2007-11-09","2007-11-20"]
["UN511_0080","Bid Process - Sup S","2007-11-21","2008-01-07"]
["UN511_0090","AWARD: Procurement of Misc Shielding","2008-01-08","2008-01-14"]
["UN511_0095","AWARD: Procurement of Misc Shielding Sppt","2008-01-08","2008-01-14"]
["UN511_0100","AWARD: Procurement of Shielding Supports","2008-01-08","2008-01-14"]
["UN511_0105","AWARD: Procurement of Shielding Supports Sppt","2008-01-08","2008-01-14"]
["UN511_0110","AWARD: Supplemental Shielding Complete","2008-01-15","2008-01-14"]
["UN511_0120","Receive Production Lot - Sup S","2008-01-15","2008-02-25"]
["UN511_0130","QA Production Lot - Sup S","2008-02-26","2008-03-10"]
["UN511_0140","Approve Production Lot - Sup S","2008-03-11","2008-03-12"]
["UN511_0150","Pack  Supplemental Shielding for Shipping-Sup","2008-03-13","2008-03-26"]
["UN511_0160","Write Shipping Paper Work - Sup S","2008-03-27","2008-04-09"]
["UN511_0170","Ship to SLAC - Sup S","2008-04-10","2008-04-21"]
["UN511_0180","Transmit Engineering Data to Slac - Sup S","2008-03-27","2008-04-03"]
["UN511_0182","RFI: Supplemental Shielding","2008-04-22","2008-04-21"]
["UN511_0190","Develop Installation Plan - Sup S","2007-08-30","2007-09-27"]
["UN511_0200","Review installation Plan - Sup S","2007-09-28","2007-10-05"]
["UN511_0205","RFI Supplemental Shielding","2007-10-08","2007-10-05"]
["UN511_0210","Supplemental Shielding Arrive at SLAC","2008-04-22","2008-05-06"]
["UN511_0220","Install Supplemental Shielding","2008-05-07","2008-06-05"]
["UN511_0230","Inspect Supplemental Shielding Placement and S","2008-06-06","2008-06-13"]
["UN511_0240","Supplemental Shielding Available","2008-06-16","2008-06-13"]
["UN511_0250","Commission  Supplemental Shielding","2008-06-16","2008-07-08"]
["UN511_0260","Complete - Sup S Testing","2008-07-09","2008-07-08"]
["UN601_0000","REQD: Undulator #1 RFI","2007-07-31","2007-07-30"]
["UN601_0005","REQD: Undulator #2 RFI","2007-07-30","2007-07-27"]
["UN601_0010","REQD: Undulator #3 RFI","2007-07-27","2007-07-26"]
["UN601_0015","REQD: Undulator #4 RFI","2007-07-27","2007-07-26"]
["UN601_0020","REQD: Undulator #5 RFI","2007-07-27","2007-07-26"]
["UN601_0025","REQD: Undulator #7 RFI","2007-07-27","2007-07-26"]
["UN601_0030","REQD: Undulator #6 RFI","2007-07-27","2007-07-26"]
["UN601_0035","REQD: Undulator #9 RFI","2007-07-27","2007-07-26"]
["UN601_0040","REQD: Undulator #8 RFI","2007-07-27","2007-07-26"]
["UN601_0045","REQD: Undulator #11 RFI","2007-08-21","2007-08-20"]
["UN601_0050","REQD: Undulator #10 RFI","2007-08-21","2007-08-20"]
["UN601_0055","REQD: Undulator #13 RFI","2007-08-21","2007-08-20"]
["UN601_0060","REQD: Undulator #12 RFI","2007-08-21","2007-08-20"]
["UN601_0065","REQD: Undulator #15 RFI","2007-08-21","2007-08-20"]
["UN601_0070","REQD: Undulator #14 RFI","2007-08-21","2007-08-20"]
["UN601_0075","REQD: Undulator #17 RFI","2007-08-21","2007-08-20"]
["UN601_0080","REQD: Undulator #16 RFI","2007-08-21","2007-08-20"]
["UN601_0085","REQD: Undulator #19 RFI","2007-08-21","2007-08-20"]
["UN601_0090","REQD: Undulator #18 RFI","2007-08-21","2007-08-20"]
["UN601_0095","REQD: Undulator #21 RFI","2007-10-17","2007-10-16"]
["UN601_0100","REQD: Undulator #20 RFI","2007-10-17","2007-10-16"]
["UN601_0105","REQD: Undulator #23 RFI","2007-10-17","2007-10-16"]
["UN601_0110","REQD: Undulator #22 RFI","2007-10-17","2007-10-16"]
["UN601_0115","REQD: Undulator #25 RFI","2007-11-14","2007-11-13"]
["UN601_0120","REQD: Undulator #24 RFI","2007-11-14","2007-11-13"]
["UN601_0125","REQD: Undulator #27 RFI","2007-12-14","2007-12-13"]
["UN601_0130","REQD: Undulator #26 RFI","2007-11-14","2007-11-13"]
["UN601_0135","REQD: Undulator #29 RFI","2008-01-23","2008-01-22"]
["UN601_0140","REQD: Undulator #28 RFI","2007-12-14","2007-12-13"]
["UN601_0145","REQD: Undulator #31 RFI","2008-01-23","2008-01-22"]
["UN601_0150","REQD: Undulator #30 RFI","2008-01-23","2008-01-22"]
["UN601_0155","REQD: Undulator #33 RFI","2008-01-24","2008-01-23"]
["UN601_0160","REQD: Undulator #32 RFI","2008-01-24","2008-01-23"]
["UN601_0307","ALIGNMENT HW AND SW SUMMARY","2005-05-02","2009-03-31"]
["UN601_0310","Specify Alignment Hardware","2005-10-03","2005-10-28"]
["UN601_0315","Alignment Hardware/Software Acceptance Testing","2007-03-12","2007-05-04"]
["UN601_0320","Procure Laser Trackers (2)","2006-09-01","2007-03-09"]
["UN601_0325","Procure Retro Reflectors","2006-09-01","2006-11-02"]
["UN601_0330","Procure Reference Points","2006-09-01","2006-11-02"]
["UN601_0335","Procure Wire Reference Fiducials","2006-06-01","2006-08-02"]
["UN601_0340","Procure Digital Level","2006-06-01","2006-08-02"]
["UN601_0345","Procure Absolute Wire Finder","2006-06-01","2006-08-02"]
["UN601_0350","Procure Portable HLS","2005-11-23","2006-10-16"]
["UN601_0355","Procure Misc Tools","2006-06-01","2006-08-24"]
["UN601_0360","Procure Fixturing","2006-06-01","2006-08-24"]
["UN601_0365","Procure Data Analysis Software Extension","2006-04-12","2006-08-03"]
["UN601_0367","HYDROSTATIC LEVEL SYSTEM SUMMARY","2005-05-02","2009-03-31"]
["UN601_0368","HLS Systems Engineering (PED)","2005-06-01","2006-02-15"]
["UN601_0369","HLS Systems Engineering (CNST)","2006-02-16","2008-08-29"]
["UN601_0370","Conceptual Design","2005-10-03","2005-10-07"]
["UN601_0375","Engineer Layout","2005-11-30","2005-12-13"]
["UN601_0380","Design Layout","2005-12-07","2006-02-28"]
["UN601_0385","Engineer Support System","2006-01-05","2006-02-28"]
["UN601_0390","Design Support System","2006-03-01","2006-04-06"]
["UN601_0395","Design Data Acquisition System","2005-10-03","2005-11-29"]
["UN601_0400","DAS Drafting & Doc","2005-11-14","2005-11-29"]
["UN601_0405","Specify Components","2006-03-01","2006-04-06"]
["UN601_0410","Specify Piping","2006-04-07","2006-04-17"]
["UN601_0415","Specify Support System","2006-04-18","2006-04-18"]
["UN601_0420","Specify Data Acquisition System","2006-04-19","2006-04-19"]
["UN601_0425","Specify Cables","2006-04-20","2006-04-21"]
["UN601_0430","Procure Capacitive Sensors","2006-04-07","2006-10-05"]
["UN601_0432","Procure Acoustic Sensors","2006-04-07","2006-10-05"]
["UN601_0435","Procure Support System","2006-04-19","2006-10-17"]
["UN601_0440","Procure Re-Fill Station","2006-04-07","2006-10-05"]
["UN601_0445","Procure Piping","2006-04-18","2006-10-16"]
["UN601_0450","Procure Data Acquisition System","2006-04-20","2006-10-18"]
["UN601_0455","Procure Cables","2006-04-24","2006-10-20"]
["UN601_0457","HLS Components available for Install","2005-05-02","2005-04-29"]
["UN601_0460","Develop Data Acquisition S/W","2005-11-30","2006-03-10"]
["UN601_0465","Develop Control System Connection","2007-01-02","2007-06-29"]
["UN601_0467","WIRE MONITORING SYSTEM SUMMARY","2005-05-02","2009-03-31"]
["UN601_0468","Stretched Wire Systems Engineering (PED)","2005-05-02","2005-09-30",null,"2005-05-02"]
["UN601_0469","Stretched Wire Systems Engineering (CNST)","2005-10-03","2006-01-31"]
["UN601_0470","Engineer Global Layout","2005-10-03","2005-10-20"]
["UN601_0475","Design Global Layout","2005-10-21","2006-01-03"]
["UN601_0670","Procure Wire Monitors","2006-06-01","2006-09-29"]
["UN601_0675","Procure Wire Monitor Supports","2006-06-01","2006-09-29"]
["UN601_0680","Procure Wire Tubes","2006-06-01","2006-09-29"]
["UN601_0685","Procure Wire Tube Supports","2006-06-01","2006-09-29"]
["UN601_0690","Procure Demodulation Modules","2006-06-01","2006-11-30"]
["UN601_0695","Procure Quad ADC","2006-01-03","2006-08-31"]
["UN601_0700","Procure RF Signal Processing","2006-01-03","2006-08-31"]
["UN601_0705","Procure RF Signal Distribution","2006-08-01","2006-11-30"]
["UN601_0710","Procure RF Power Amplifier","2006-08-01","2006-09-29"]
["UN601_0712","Procure Cables","2006-05-01","2006-08-31"]
["UN601_0715","Procure Crates","2006-08-01","2006-11-30"]
["UN601_0720","Procure Data Acquisition System","2006-05-01","2006-11-30"]
["UN601_0723","Stretched Wire Comp available for installation","2005-05-02","2005-04-29"]
["UN601_0725","Develop Data Acquisition Software","2006-07-03","2007-01-11"]
["UN601_0730","Develop Local Control Program","2006-07-03","2007-01-12"]
["UN601_0731","Specs of WPM Installation at U-Hall","2007-07-02","2008-02-29"]
["UN601_0732","Control of WPM Installation at U-Hall","2008-01-31","2008-02-27"]
["UN601_0733","Commissioning of WPM at U-Hall","2008-04-01","2008-06-30"]
["UN601_0740","ASSY & PREALIGN GRANITE GIRDERS SUMMARY","2006-06-07","2006-08-25"]
["UN601_0750","GIRDER #1 SUMMARY","2006-06-07","2006-06-15"]
["UN601_0755","Set Up Girder","2006-06-07","2006-06-07"]
["UN601_0756","Install Cable Tray","2007-05-04","2007-05-10"]
["UN601_0757","Pull Cables","2007-05-11","2007-05-17"]
["UN601_0758","Install Quad Power Supplies","2007-05-18","2007-05-24"]
["UN601_0759","100% Quad Power Supplies Installed","2007-10-15","2007-10-19"]
["UN601_0760","Mount Adjustable Feet","2006-06-07","2006-06-07"]
["UN601_0765","Mount Mechanical Adjustment System","2006-06-08","2006-06-08"]
["UN601_0770","Mount CAM Movers","2006-06-09","2006-06-09"]
["UN601_0775","Mount Temp Acq Sys Components","2006-06-09","2006-06-09"]
["UN601_0780","HLS Pipe Installation & Welding","2006-06-12","2006-06-12"]
["UN601_0785","Align Support Girder wrt Feet","2006-06-13","2006-06-14"]
["UN601_0790","Attach Insulation","2006-06-15","2006-06-15"]
["UN601_0795","Girder #1 RFI","2006-06-16","2006-06-15"]
["UN601_0800","GIRDER #2 SUMMARY","2006-06-14","2006-06-22"]
["UN601_0805","Set Up Girder","2006-06-14","2006-06-14"]
["UN601_0810","Mount Adjustable Feet","2006-06-14","2006-06-14"]
["UN601_0815","Mount Mechanical Adjustment System","2006-06-15","2006-06-15"]
["UN601_0820","Mount CAM Movers","2006-06-16","2006-06-16"]
["UN601_0825","Mount Temp Acq Sys Components","2006-06-16","2006-06-16"]
["UN601_0830","HLS Pipe Installation & Welding","2006-06-19","2006-06-19"]
["UN601_0835","Align Support Girder wrt Feet","2006-06-20","2006-06-21"]
["UN601_0840","Attach Insulation","2006-06-22","2006-06-22"]
["UN601_0845","Girder #2 RFI","2006-06-23","2006-06-22"]
["UN601_0850","GIRDER #3 SUMMARY","2006-06-21","2006-06-29"]
["UN601_0855","Set Up Girder","2006-06-21","2006-06-21"]
["UN601_0860","Mount Adjustable Feet","2006-06-21","2006-06-21"]
["UN601_0865","Mount Mechanical Adjustment System","2006-06-22","2006-06-22"]
["UN601_0870","Mount CAM Movers","2006-06-23","2006-06-23"]
["UN601_0875","Mount Temp Acq Sys Components","2006-06-23","2006-06-23"]
["UN601_0880","HLS Pipe Installation & Welding","2006-06-26","2006-06-26"]
["UN601_0885","Align Support Girder wrt Feet","2006-06-27","2006-06-28"]
["UN601_0890","Attach Insulation","2006-06-29","2006-06-29"]
["UN601_0895","Girder #3 RFI","2006-06-30","2006-06-29"]
["UN601_0900","GIRDER #4 SUMMARY","2006-06-28","2006-07-07"]
["UN601_0905","Set Up Girder","2006-06-28","2006-06-28"]
["UN601_0910","Mount Adjustable Feet","2006-06-28","2006-06-28"]
["UN601_0915","Mount Mechanical Adjustment System","2006-06-29","2006-06-29"]
["UN601_0920","Mount CAM Movers","2006-06-30","2006-06-30"]
["UN601_0925","Mount Temp Acq Sys Components","2006-06-30","2006-06-30"]
["UN601_0930","HLS Pipe Installation & Welding","2006-07-03","2006-07-03"]
["UN601_0935","Align Support Girder wrt Feet","2006-07-05","2006-07-06"]
["UN601_0940","Attach Insulation","2006-07-07","2006-07-07"]
["UN601_0945","Girder #4 RFI","2006-07-10","2006-07-07"]
["UN601_0950","GIRDER #5 SUMMARY","2006-07-06","2006-07-14"]
["UN601_0955","Set Up Girder","2006-07-06","2006-07-06"]
["UN601_0960","Mount Adjustable Feet","2006-07-06","2006-07-06"]
["UN601_0965","Mount Mechanical Adjustment System","2006-07-07","2006-07-07"]
["UN601_0970","Mount CAM Movers","2006-07-10","2006-07-10"]
["UN601_0975","Mount Temp Acq Sys Components","2006-07-10","2006-07-10"]
["UN601_0980","HLS Pipe Installation & Welding","2006-07-11","2006-07-11"]
["UN601_0985","Align Support Girder wrt Feet","2006-07-12","2006-07-13"]
["UN601_0990","Attach Insulation","2006-07-14","2006-07-14"]
["UN601_0995","Girder #5 RFI","2006-07-17","2006-07-14"]
["UN601_1000","GIRDER #6 SUMMARY","2006-07-13","2006-07-21"]
["UN601_1005","Set Up Girder","2006-07-13","2006-07-13"]
["UN601_1010","Mount Adjustable Feet","2006-07-13","2006-07-13"]
["UN601_1015","Mount Mechanical Adjustment System","2006-07-14","2006-07-14"]
["UN601_1020","Mount CAM Movers","2006-07-17","2006-07-17"]
["UN601_1025","Mount Temp Acq Sys Components","2006-07-17","2006-07-17"]
["UN601_1030","HLS Pipe Installation & Welding","2006-07-18","2006-07-18"]
["UN601_1035","Align Support Girder wrt Feet","2006-07-19","2006-07-20"]
["UN601_1040","Attach Insulation","2006-07-21","2006-07-21"]
["UN601_1045","Girder #6 RFI","2006-07-24","2006-07-21"]
["UN601_1050","GIRDER #7 SUMMARY","2006-07-20","2006-07-28"]
["UN601_1055","Set Up Girder","2006-07-20","2006-07-20"]
["UN601_1060","Mount Adjustable Feet","2006-07-20","2006-07-20"]
["UN601_1065","Mount Mechanical Adjustment System","2006-07-21","2006-07-21"]
["UN601_1070","Mount CAM Movers","2006-07-24","2006-07-24"]
["UN601_1075","Mount Temp Acq Sys Components","2006-07-24","2006-07-24"]
["UN601_1080","HLS Pipe Installation & Welding","2006-07-25","2006-07-25"]
["UN601_1085","Align Support Girder wrt Feet","2006-07-26","2006-07-27"]
["UN601_1090","Attach Insulation","2006-07-28","2006-07-28"]
["UN601_1095","Girder #7 RFI","2006-07-31","2006-07-28"]
["UN601_1100","GIRDER #8 SUMMARY","2006-07-27","2006-08-04"]
["UN601_1105","Set Up Girder","2006-07-27","2006-07-27"]
["UN601_1110","Mount Adjustable Feet","2006-07-27","2006-07-27"]
["UN601_1115","Mount Mechanical Adjustment System","2006-07-28","2006-07-28"]
["UN601_1120","Mount CAM Movers","2006-07-31","2006-07-31"]
["UN601_1125","Mount Temp Acq Sys Components","2006-07-31","2006-07-31"]
["UN601_1130","HLS Pipe Installation & Welding","2006-08-01","2006-08-01"]
["UN601_1135","Align Support Girder wrt Feet","2006-08-02","2006-08-03"]
["UN601_1140","Attach Insulation","2006-08-04","2006-08-04"]
["UN601_1145","Girder #8 RFI","2006-08-07","2006-08-04"]
["UN601_1150","GIRDER #9 SUMMARY","2006-08-03","2006-08-11"]
["UN601_1155","Set Up Girder","2006-08-03","2006-08-03"]
["UN601_1160","Mount Adjustable Feet","2006-08-03","2006-08-03"]
["UN601_1165","Mount Mechanical Adjustment System","2006-08-04","2006-08-04"]
["UN601_1170","Mount CAM Movers","2006-08-07","2006-08-07"]
["UN601_1175","Mount Temp Acq Sys Components","2006-08-07","2006-08-07"]
["UN601_1180","HLS Pipe Installation & Welding","2006-08-08","2006-08-08"]
["UN601_1185","Align Support Girder wrt Feet","2006-08-09","2006-08-10"]
["UN601_1190","Attach Insulation","2006-08-11","2006-08-11"]
["UN601_1195","Girder #9 RFI","2006-08-14","2006-08-11"]
["UN601_1200","GIRDER #10 SUMMARY","2006-08-10","2006-08-18"]
["UN601_1205","Set Up Girder","2006-08-10","2006-08-10"]
["UN601_1210","Mount Adjustable Feet","2006-08-10","2006-08-10"]
["UN601_1215","Mount Mechanical Adjustment System","2006-08-11","2006-08-11"]
["UN601_1220","Mount CAM Movers","2006-08-14","2006-08-14"]
["UN601_1225","Mount Temp Acq Sys Components","2006-08-14","2006-08-14"]
["UN601_1230","HLS Pipe Installation & Welding","2006-08-15","2006-08-15"]
["UN601_1235","Align Support Girder wrt Feet","2006-08-16","2006-08-17"]
["UN601_1240","Attach Insulation","2006-08-18","2006-08-18"]
["UN601_1245","Girder #10 RFI","2006-08-21","2006-08-18"]
["UN601_1250","GIRDER #11 SUMMARY","2006-08-17","2006-08-25"]
["UN601_1255","Set Up Girder","2006-08-17","2006-08-17"]
["UN601_1260","Mount Adjustable Feet","2006-08-17","2006-08-17"]
["UN601_1265","Mount Mechanical Adjustment System","2006-08-18","2006-08-18"]
["UN601_1270","Mount CAM Movers","2006-08-21","2006-08-21"]
["UN601_1275","Mount Temp Acq Sys Components","2006-08-21","2006-08-21"]
["UN601_1280","HLS Pipe Installation & Welding","2006-08-22","2006-08-22"]
["UN601_1285","Align Support Girder wrt Feet","2006-08-23","2006-08-24"]
["UN601_1290","Attach Insulation","2006-08-25","2006-08-25"]
["UN601_1295","Girder #11 RFI","2006-08-28","2006-08-25"]
["UN601_1300","ALIGNMT LAYOUT COMPUTATIONS & MONITORING SUMMARY","2006-08-04","2007-05-24"]
["UN601_1305","Vertical Monitoring of Tunnel Floor","2006-08-04","2006-08-09"]
["UN601_1310","Vertical Monitoring of Tunnel Floor","2006-08-10","2006-08-15"]
["UN601_1315","Vertical Monitoring of Tunnel Floor","2006-08-16","2006-08-21"]
["UN601_1320","Vertical Monitoring of Tunnel Floor","2006-08-16","2006-08-21"]
["UN601_1325","Vertical Monitoring of Tunnel Floor","2006-08-22","2006-08-25"]
["UN601_1330","Design Network","2007-05-04","2007-05-15"]
["UN601_1335","Computation of Layout Parameters","2007-05-16","2007-05-22"]
["UN601_1340","Quality Control","2007-05-23","2007-05-24"]
["UN601_1345","INSTALLATION & ALIGNMENT SUMMARY","2007-05-16","2008-06-30"]
["UN601_1350","NETWORK INSTALLATION SUMMARY","2007-05-16","2007-05-22"]
["UN601_1355","Layout Network Points","2007-05-16","2007-05-17"]
["UN601_1360","Network Installation","2007-05-16","2007-05-22"]
["UN601_1365","ALIGNMENT REFERENCE NETWORK MSMTS SUMMARY","2007-05-23","2007-06-07"]
["UN601_1370","Measurements(Laser Tracker,Level,Total Station)","2007-05-23","2007-06-04"]
["UN601_1375","Data Evaluation","2007-05-30","2007-06-05"]
["UN601_1380","Quality Control","2007-06-06","2007-06-07"]
["UN601_1381","Mark Support Bolts on Floor","2007-06-08","2007-06-11"]
["UN601_1382","Quality Control","2007-06-11","2007-06-12"]
["UN601_1385","FOOT PLATE INSTALLATION SUMMARY","2007-06-13","2007-07-03"]
["UN601_1390","Drill Holes","2007-06-13","2007-06-14"]
["UN601_1395","Set Studs","2007-06-13","2007-06-14"]
["UN601_1400","Install Plates, Pre-Set Height","2007-06-13","2007-06-14"]
["UN601_1405","Prealign Plates to 0.5mm","2007-06-14","2007-06-22"]
["UN601_1410","Quality Control: Map Plate Positions","2007-06-15","2007-06-18"]
["UN601_1415","Quality Control: Data Evaluation","2007-06-19","2007-06-19"]
["UN601_1420","Grout Plates","2007-06-20","2007-06-22"]
["UN601_1425","Quality Control: Map Plate Positions","2007-06-25","2007-06-26"]
["UN601_1430","Quality Control: Data Evaluation","2007-06-27","2007-06-27"]
["UN601_1435","Grout Plates","2007-06-28","2007-07-02"]
["UN601_1440","Clean Tunnel","2007-07-02","2007-07-03"]
["UN601_1470","Stretched Wire Systems Engineering (CNST)","2006-02-01","2008-08-29"]
["UN601_1475","Drawings and Documentation","2006-01-03","2008-07-30"]
["UN601_1480","Revise Mechanics","2006-07-03","2006-08-28"]
["UN601_1485","Design & Specs Mechanics","2006-02-06","2006-06-07"]
["UN601_1486","Revise Electronics","2006-06-08","2006-09-08"]
["UN601_1487","Design & Specs Electronics","2006-07-11","2006-12-15"]
["UN601_1488","Design & Specs Wire Test Facility","2006-07-11","2006-12-15"]
["UN601_1489","System Assembly at Test Facility","2007-01-02","2007-05-01"]
["UN601_1490","GRANITE GIRDER & EXIT/ENTR SECTION SUPTS INSTALL","2007-08-14","2007-08-29"]
["UN601_1491","System Measurements at Test Facility","2007-07-02","2007-12-14"]
["UN601_1492","Wire Monitor Calibration","2007-09-04","2008-02-29"]
["UN601_1500","Exit Section Supts Transport & Install","2007-08-14","2007-08-15"]
["UN601_1510","Granite Girder #11 Transport & Install","2007-08-16","2007-08-17"]
["UN601_1515","Granite Girder #10 Transport & Install","2007-08-20","2007-08-20"]
["UN601_1520","Granite Girder #9 Transport & Install","2007-08-21","2007-08-21"]
["UN601_1525","Granite Girder #8 Transport & Install","2007-08-21","2007-08-21"]
["UN601_1530","Granite Girder #7 Transport & Install","2007-08-22","2007-08-22"]
["UN601_1535","Granite Girder #6 Transport & Install","2007-08-23","2007-08-23"]
["UN601_1540","Granite Girder #5 Transport & Install","2007-08-24","2007-08-24"]
["UN601_1545","Granite Girder #4 Transport & Install","2007-08-27","2007-08-27"]
["UN601_1550","Granite Girder #3 Transport & Install","2007-08-27","2007-08-27"]
["UN601_1555","Granite Girder #2 Transport & Install","2007-08-28","2007-08-28"]
["UN601_1560","Granite Girder #1 Transport & Install","2007-08-28","2007-08-28"]
["UN601_1565","Exit Section Supports Transport & Install","2007-08-29","2007-08-29"]
["UN601_1570","RE-MEASURE ALIGNMENT REFERENCE NETWORK","2007-08-27","2007-09-07"]
["UN601_1575","Measurements(Laser Tracker,Level,Total Station)","2007-08-27","2007-08-30"]
["UN601_1580","Stretched Wire Measurements","2007-08-27","2007-08-30"]
["UN601_1585","Data Evaluation","2007-08-27","2007-08-30"]
["UN601_1590","Quality Control","2007-08-31","2007-09-07"]
["UN601_1595","PRE-ALIGNMENT","2007-09-10","2007-09-11"]
["UN601_1600","TABLES #6 - 11","2007-09-10","2007-09-25"]
["UN601_1605","Level Granite Girders","2007-09-10","2007-09-13"]
["UN601_1610","Set Cam Movers to Zero","2007-09-10","2007-09-11"]
["UN601_1615","Align Mech Undulator Supports to 250 Micron","2007-09-13","2007-09-25"]
["UN601_1620","GIRDERS #1 - 5","2007-09-10","2007-09-11"]
["UN601_1625","Level Granite Girders","2007-09-10","2007-09-13"]
["UN601_1630","Set Cam Movers to Zero","2007-09-10","2007-09-11"]
["UN601_1635","Align Mech Undulator Supports to 250 Micron","2007-08-28","2007-09-11"]
["UN601_1645","Cradle #1 Transport and Install","2007-09-21","2007-09-21"]
["UN601_1650","Cradle #2 Transport and Install","2007-09-21","2007-09-21"]
["UN601_1655","Set up Cradle on CMM - 03","2007-09-21","2007-09-21"]
["UN601_1656","Align Cradle System - 03","2007-09-24","2007-09-25"]
["UN601_1657","Component Handling - 03","2007-09-26","2007-09-26"]
["UN601_1661","Set up Cradle on CMM - 04","2007-09-27","2007-09-27"]
["UN601_1662","Align Cradle System - 04","2007-09-28","2007-10-01"]
["UN601_1663","Component Handling - 04","2007-10-02","2007-10-02"]
["UN601_1665","Set up Cradle on CMM - 05","2007-10-03","2007-10-03"]
["UN601_1666","Align Cradle System - 05","2007-10-04","2007-10-05"]
["UN601_1667","Component Handling - 05","2007-10-08","2007-10-08"]
["UN601_1670","Set up Cradle on CMM - 06","2007-10-09","2007-10-09"]
["UN601_1671","Align Cradle System - 06","2007-10-10","2007-10-11"]
["UN601_1672","Component Handling - 06","2007-10-12","2007-10-12"]
["UN601_1675","Set up Cradle on CMM - 07","2007-10-15","2007-10-15"]
["UN601_1676","Align Cradle System - 07","2007-10-16","2007-10-17"]
["UN601_1677","Component Handling - 07","2007-10-18","2007-10-18"]
["UN601_1680","Set up Cradle on CMM - 08","2007-10-19","2007-10-19"]
["UN601_1681","Align Cradle System - 08","2007-10-22","2007-10-23"]
["UN601_1682","Component Handling - 08","2007-10-24","2007-10-24"]
["UN601_1685","Set up Cradle on CMM - 09","2007-10-25","2007-10-25"]
["UN601_1686","Align Cradle System - 09","2007-10-26","2007-10-29"]
["UN601_1687","Component Handling - 09","2007-10-30","2007-10-30"]
["UN601_1690","Set up Cradle on CMM - 10","2007-10-31","2007-10-31"]
["UN601_1691","Align Cradle System - 10","2007-11-01","2007-11-02"]
["UN601_1692","Component Handling - 10","2007-11-05","2007-11-05"]
["UN601_1695","Set up Cradle on CMM - 11","2007-11-06","2007-11-06"]
["UN601_1696","Align Cradle System - 11","2007-11-07","2007-11-08"]
["UN601_1697","Component Handling - 11","2007-11-09","2007-11-09"]
["UN601_1700","Set up Cradle on CMM - 12","2007-11-12","2007-11-12"]
["UN601_1701","Align Cradle System - 12","2007-11-13","2007-11-14"]
["UN601_1702","Component Handling - 12","2007-11-15","2007-11-15"]
["UN601_1705","Set up Cradle on CMM - 13","2007-11-16","2007-11-16"]
["UN601_1706","Align Cradle System - 13","2007-11-19","2007-11-20"]
["UN601_1707","Component Handling - 13","2007-11-21","2007-11-21"]
["UN601_1710","Set up Cradle on CMM - 14","2007-11-26","2007-11-26"]
["UN601_1711","Align Cradle System - 14","2007-11-27","2007-11-28"]
["UN601_1712","Component Handling - 14","2007-11-29","2007-11-29"]
["UN601_1715","Set up Cradle on CMM - 15","2007-11-30","2007-11-30"]
["UN601_1716","Align Cradle System - 15","2007-12-03","2007-12-04"]
["UN601_1717","Component Handling - 15","2007-12-05","2007-12-05"]
["UN601_1720","Set up Cradle on CMM - 16","2007-12-06","2007-12-06"]
["UN601_1721","Align Cradle System - 16","2007-12-07","2007-12-10"]
["UN601_1722","Component Handling - 16","2007-12-11","2007-12-11"]
["UN601_1725","Set up Cradle on CMM - 17","2007-12-12","2007-12-12"]
["UN601_1726","Align Cradle System - 17","2007-12-13","2007-12-14"]
["UN601_1727","Component Handling - 17","2008-01-02","2008-01-02"]
["UN601_1730","Set up Cradle on CMM - 18","2008-01-03","2008-01-03"]
["UN601_1731","Align Cradle System - 18","2008-01-04","2008-01-07"]
["UN601_1732","Component Handling - 18","2008-01-08","2008-01-08"]
["UN601_1735","Set up Cradle on CMM - 19","2008-01-09","2008-01-09"]
["UN601_1736","Align Cradle System - 19","2008-01-10","2008-01-11"]
["UN601_1737","Component Handling - 19","2008-01-14","2008-01-14"]
["UN601_1740","Set up Cradle on CMM - 20","2008-01-15","2008-01-15"]
["UN601_1741","Align Cradle System - 20","2008-01-16","2008-01-17"]
["UN601_1742","Component Handling - 20","2008-01-18","2008-01-18"]
["UN601_1745","Set up Cradle on CMM - 21","2008-01-22","2008-01-22"]
["UN601_1746","Align Cradle System - 21","2008-01-23","2008-01-24"]
["UN601_1747","Component Handling - 21","2008-01-25","2008-01-25"]
["UN601_1750","Set up Cradle on CMM - 22","2008-01-28","2008-01-28"]
["UN601_1751","Align Cradle System - 22","2008-01-29","2008-01-30"]
["UN601_1752","Component Handling - 22","2008-01-31","2008-01-31"]
["UN601_1755","Set up Cradle on CMM - 23","2008-02-01","2008-02-01"]
["UN601_1756","Align Cradle System - 23","2008-02-04","2008-02-05"]
["UN601_1757","Component Handling - 23","2008-02-06","2008-02-06"]
["UN601_1760","Set up Cradle on CMM - 24","2008-02-07","2008-02-07"]
["UN601_1761","Align Cradle System - 24","2008-02-08","2008-02-11"]
["UN601_1762","Component Handling - 24","2008-02-12","2008-02-12"]
["UN601_1765","Set up Cradle on CMM - 25","2008-02-13","2008-02-13"]
["UN601_1766","Align Cradle System - 25","2008-02-14","2008-02-15"]
["UN601_1767","Component Handling - 25","2008-02-19","2008-02-19"]
["UN601_1770","Set up Cradle on CMM - 26","2008-02-20","2008-02-20"]
["UN601_1771","Align Cradle System - 26","2008-02-21","2008-02-22"]
["UN601_1772","Component Handling - 26","2008-02-25","2008-02-25"]
["UN601_1775","Set up Cradle on CMM - 27","2008-02-26","2008-02-26"]
["UN601_1776","Align Cradle System - 27","2008-02-27","2008-02-28"]
["UN601_1777","Component Handling - 27","2008-02-29","2008-02-29"]
["UN601_1780","Set up Cradle on CMM - 28","2008-03-03","2008-03-03"]
["UN601_1781","Align Cradle System - 28","2008-03-04","2008-03-05"]
["UN601_1782","Component Handling - 28","2008-03-06","2008-03-06"]
["UN601_1785","Set up Cradle on CMM - 29","2008-03-07","2008-03-07"]
["UN601_1786","Align Cradle System - 29","2008-03-10","2008-03-11"]
["UN601_1787","Component Handling - 29","2008-03-12","2008-03-12"]
["UN601_1790","Set up Cradle on CMM - 30","2008-03-13","2008-03-13"]
["UN601_1791","Align Cradle System - 30","2008-03-14","2008-03-17"]
["UN601_1792","Component Handling - 30","2008-03-18","2008-03-18"]
["UN601_1795","Set up Cradle on CMM - 31","2008-03-19","2008-03-19"]
["UN601_1796","Align Cradle System - 31","2008-03-20","2008-03-21"]
["UN601_1797","Component Handling - 31","2008-03-24","2008-03-24"]
["UN601_1800","Set up Cradle on CMM - 32","2008-03-25","2008-03-25"]
["UN601_1801","Align Cradle System - 32","2008-03-26","2008-03-27"]
["UN601_1802","Component Handling - 32","2008-03-28","2008-03-28"]
["UN601_1805","Set up Cradle on CMM - 33","2008-03-31","2008-03-31"]
["UN601_1806","Align Cradle System - 33","2008-04-01","2008-04-02"]
["UN601_1807","Component Handling - 33","2008-04-03","2008-04-03"]
["UN601_1810","HYDROSTATIC LEVEL SYSTEM","2005-05-02","2007-08-08"]
["UN601_1812","HLS INSTALLATION","2005-05-02","2005-05-03"]
["UN601_1815","HLS Sensor Installation","2005-05-02","2005-05-03"]
["UN601_1820","Pipe Interconnections w/Flexible Tubing","2005-05-02","2005-05-06"]
["UN601_1825","Install Refill Station","2007-07-02","2007-07-09"]
["UN601_1830","Fill and Leak Testing","2007-07-10","2007-07-11"]
["UN601_1835","Cable Connections","2005-05-02","2005-05-03"]
["UN601_1840","HLS TESTING","2007-07-12","2007-08-08"]
["UN601_1845","HLS System Testing","2007-07-12","2007-07-25"]
["UN601_1850","Mechanical Tuning","2007-07-19","2007-07-25"]
["UN601_1855","Electrical Tuning","2007-07-19","2007-07-25"]
["UN601_1860","Software Changes","2007-07-12","2007-08-08"]
["UN601_1862","Commission Stretched Wire System Complete","2007-08-09","2007-09-06"]
["UN601_1863","HLS ready for measurements","2007-09-07","2007-09-06"]
["UN601_1865","WIRE MONITORING SYSTEM","2006-10-02","2007-11-08"]
["UN601_1870","WMS INSTALLATION","2006-10-02","2007-09-13"]
["UN601_1875","WMS Sensor Installation","2006-10-02","2006-10-03"]
["UN601_1877","WMS Wire Tube Installation","2006-10-02","2006-10-04"]
["UN601_1880","WMS Electronics Installation","2007-08-30","2007-09-05"]
["UN601_1895","Cable Termination","2007-08-30","2007-09-13"]
["UN601_1900","WMS TESTING","2007-09-14","2007-11-08"]
["UN601_1905","WMS System Testing","2007-09-14","2007-09-27"]
["UN601_1910","Mechanical Tuning","2007-09-21","2007-09-27"]
["UN601_1915","Electrical Tuning","2007-09-21","2007-10-04"]
["UN601_1920","Software Changes","2007-09-14","2007-11-08"]
["UN601_1921","Commission Hydrostatic Level System","2007-11-09","2007-12-10"]
["UN601_1922","WMS ready for measurements","2007-12-11","2007-12-10"]
["UN601_2000","RE-MEASURE NETWORK","2008-05-28","2008-06-10"]
["UN601_2005","Remeasurement(Laser Tracker,Level,Total Station)","2008-05-28","2008-06-03"]
["UN601_2010","Stretched Wire Measurements-along granite Girdrs","2007-12-11","2008-01-02"]
["UN601_2015","HLS Measurements","2007-09-07","2007-09-13"]
["UN601_2020","Data Evaluation","2008-05-28","2008-06-03"]
["UN601_2025","Quality Control","2008-06-04","2008-06-10"]
["UN601_2030","ALIGN CRADLES","2008-06-11","2008-06-30"]
["UN601_2035","Set Cradle X,Y Mechanical Adjustments","2008-06-11","2008-06-16"]
["UN601_2040","Quality Control","2008-06-13","2008-06-19"]
["UN601_2045","Set Cradle X,Y Cam Mover Adjustments","2008-06-20","2008-06-25"]
["UN601_2050","Quality Control","2008-06-24","2008-06-30"]
["UNMS4_0115","FY06 Money Arrives at ANL","2005-11-02","2005-11-01",null,"2005-11-02","2005-11-01"]
["UNMS4_0120","FY07 Money Arrives at ANL","2006-11-02","2006-11-01"]
["UNMS4_0200","EM Supply Spec. Accepted","2005-06-30","2005-06-29"]
["UNMS4_0205","Fine Motion Test Fixture Ready for Use","2005-10-10","2005-10-07"]
["UNMS4_0210","Coarse Motion Test Fixture Ready for Use","2005-10-10","2005-10-07"]
["UNMS4_0215","Image Capture Test Fixture Complete","2005-05-09","2005-05-06"]
["UNMS4_0220","Fine Motion Control Hardware Selection Finalized","2006-01-16","2006-01-13"]
["UNMS4_0225","EM Magnet Supply Test Fixture Ready for Use","2006-09-26","2006-09-25"]
["UNMS4_0230","Coarse Motion Control HW Selection Finalized","2006-04-21","2006-04-20"]
["UNMS4_0235","Undulator Fine Motion Controls Software Complete","2006-06-08","2006-06-07"]
["UNMS4_0240","EM Magnet Supply Choice Finalized","2006-08-18","2006-08-17"]
["UNMS4_0245","Undulator Cradle Motion Software Complete","2006-01-19","2006-01-18"]
["UNMS4_0250","Image Capture Hardware Selection Finalized","2005-05-23","2005-05-20"]
["UNMS4_0255","EM Magnet Supply Controls Software Complete","2006-09-26","2006-09-25"]
["UNMS4_0260","Image Analysis Controls Software Complete","2006-04-10","2006-04-07"]
["UNMS4_0330","Award First Article Assbly Undulator 1 - Hi-Tech","2005-10-26","2005-10-25"]
["UNMS4_0335","Award First Article Assbly Undulator - Metalex","2005-10-27","2005-10-26"]
["UNMS4_0340","1st Lot Magnet Poles Arrive","2005-11-02","2005-11-01"]
["UNMS4_0345","1st 5% Magnet Blocks Arrive","2006-01-04","2006-01-03"]
["UNMS4_0350","1st Ti Strongback Arrives & Accepted","2005-12-06","2005-12-05"]
["UNMS4_0355","2nd Ti Strongback Arrives & Accepted","2005-05-03","2005-05-02"]
["UNMS4_0360","Undulator 01 LLPs Available for Fabrication","2006-01-04","2006-01-03"]
["UNMS4_0365","Undulator 02 LLPs Available for Fabrication","2006-01-04","2006-01-03"]
["UNMS4_0380","Hi-Tech Permission to Proceed with 1st Article","2005-11-10","2005-11-09"]
["UNMS4_0381","Renegotiate Hi-Tech Contract for Production","2006-05-22","2006-05-19"]
["UNMS4_0382","Undulator 01 Assembly Com & Rcvd at ANL","2006-03-30","2006-03-29"]
["UNMS4_0385","Undulator 02 Assembly Com & Rcvd at ANL","2006-04-10","2006-04-07"]
["UNMS4_0387","Undulator 01 Measured and Tuned @ ANL","2006-04-28","2006-04-27"]
["UNMS4_0389","Undulator 02 Measured and Tuned @ ANL","2006-05-30","2006-05-26"]
["UNMS4_0390","Undulator 01 Tested w/Supt & Mover System @ ANL","2006-04-10","2006-04-07"]
["UNMS4_0392","Metalex Permission to Proceed with 1st Article","2005-11-15","2005-11-14"]
["UNMS4_0393","Hi-Tech Undulators 03 -> 19 Complete","2006-12-11","2006-12-08"]
["UNMS4_0394","Metalex Undulators 04 -> 20 Complete","2007-01-11","2007-01-10"]
["UNMS4_0395","Hi-Tech Undulators 21 -> 39 Complete","2007-06-20","2007-06-19"]
["UNMS4_0396","Metalex Undulators 22 -> 40 Complete","2007-08-09","2007-08-08"]
["UNMS4_0397","Renegotiate Metalex Contract for Production","2006-06-20","2006-06-19"]
["UNMS4_0410","Prototype Bellows Fabrication Complete","2006-02-02","2006-02-01"]
["UNMS4_0415","Vacuum Chamber Prototype Fabrication Complete","2006-10-03","2006-10-02"]
["UNMS4_0420","Vacuum Chamber Prototype Testing Complete","2006-12-04","2006-12-01"]
["UNMS4_0425","Prototype Bellows Testing Complete","2006-04-05","2006-04-04"]
["UNMS4_0430","Production Chamber Design Complete","2007-02-09","2007-02-08"]
["UNMS4_0435","Bellows Final Design Complete","2006-06-05","2006-06-02"]
["UNMS4_0440","Production Chamber Award Complete","2007-04-10","2007-04-09"]
["UNMS4_0445","Bellows Award Complete","2006-11-01","2006-10-31"]
["UNMS4_0450","Vacuum Chamber Ready for Installation","2007-09-13","2007-09-12"]
["UNMS4_0455","Bellows Ready for Installation","2007-04-10","2007-04-09"]
["UNMS4_0500","Complete Fabrication of Wire Scanner Prototype","2005-05-02","2005-04-29"]
["UNMS4_0505","Complete Fabrication of OTR Prototype","2005-05-02","2005-04-29"]
["UNMS4_0515","Prototype RFBPM Design Complete","2005-05-02","2005-04-29"]
["UNMS4_0525","Prototype RFBPM Fabrication Complete","2005-05-02","2005-04-29"]
["UNMS4_0550","Prototype RFBPM Testing Complete","2006-05-23","2006-05-22"]
["UNMS4_0565","Wire Scanner Award Complete","2005-05-02","2005-04-29"]
["UNMS4_0570","RFBPM Award Complete","2006-09-26","2006-09-25"]
["UNMS4_0575","RFBPMs Ready For Installation","2007-10-23","2007-10-22"]
["UNMS_00040","Undulator System Commissioning Complete","2007-07-24","2007-07-23"]
["UNOPS_0000","Undulator System Pre-Operations","2008-08-18","2009-03-31"]
["UNSL_0005","REQD:  2 Charge Monitors From SLAC","2005-11-23","2005-11-23"]
["UNUN_00010","Support Commissioning - Controls","2006-10-03","2007-06-05"]
["UNUN_00020","Support Commissioning - Mechanical","2006-10-03","2007-06-05"]
["UNUN_00030","Support Commissioning - Physics","2006-10-03","2007-06-05"]
["UNUN_00290","Review Undulator System 5","2005-10-03","2005-10-04"]
["UNUN_00300","Review Undulator System 6","2005-10-05","2005-10-06"]
["UNUN_00310","Review Undulator System 7","2006-10-02","2006-10-03"]
["UNUN_00320","Review Undulator System 8","2006-10-04","2006-10-05"]
["UNUN_00330","Review Undulator System 9","2007-10-01","2007-10-02"]
["UNUN_00470","FY06 Workshops and Meetings","2005-10-03","2005-10-03"]
["UNUN_00480","FY07 Workshops and Meetings","2006-10-02","2006-10-02"]
["UNUN_00490","FY08 Workshops and Meetings","2007-10-01","2007-10-01"]
["UN_LOE","Undulator System LOE Complete","2009-04-01","2009-03-31"]
["XEOPS_0000","X-Ray End Stations Pre-Operations","2008-02-04","2009-03-25"]
["XE_0121","MANAGEMENT","2005-05-02","2009-03-31"]
["XE_0201","Specification FEE - Cabling","2007-06-07","2007-07-05"]
["XE_0202","Design FEE - Cabling","2007-07-06","2007-08-02"]
["XE_0211","FEE CABLING","2007-06-07","2008-03-03"]
["XE_0212","Specification Tunnel - Cabling","2007-06-07","2007-07-05"]
["XE_0232","Prep form, Offer, Hire/Train - Controls Engineer","2005-11-01","2006-02-01"]
["XE_0241","Commission Far Hall - Cabling","2008-07-16","2008-08-12"]
["XE_0261","COMP: Tunnel - Cabling","2008-05-07","2008-05-06"]
["XE_0272","Specification Near Hall - Cabling","2007-06-07","2007-07-05"]
["XE_0282","Design Tunnel - Cabling","2007-07-06","2007-08-02"]
["XE_0291","Commission Tunnel - Cabling","2008-05-07","2008-06-04"]
["XE_0292","Design Near Hall - Cabling","2007-07-06","2007-08-02"]
["XE_0311","Install FEE Racks & Panels - Cabling","2008-03-11","2008-05-05"]
["XE_0312","Install Near Hall  Racks & Panels - Cabling","2007-10-23","2008-01-04"]
["XE_0314","Install Far Hall  Racks & Panels - Cabling","2008-01-17","2008-03-14"]
["XE_0321","Test FEE - Cabling","2008-05-13","2008-05-27"]
["XE_0322","COMP:  Near Hall Laser Installed - Cabling","2008-01-14","2008-01-11"]
["XE_0324","Install Cable Tray FH - Cabling","2007-11-02","2008-01-16"]
["XE_0325","Specification Far Hall - Cabling","2007-06-07","2007-07-05"]
["XE_033","Management & Oversight - FY06-08","2005-10-03","2008-09-30"]
["XE_0331","System Integrate & Test Far Hall - Cabling","2008-06-17","2008-07-15"]
["XE_0332","NEAR HALL CABLING","2007-06-07","2007-10-15"]
["XE_0334","Install Cable Far Hall - Cabling","2008-03-17","2008-05-09"]
["XE_0335","FAR HALL CABLING","2007-06-07","2007-11-01"]
["XE_0341","Test Near Hall - Cabling","2008-01-22","2008-02-04"]
["XE_0342","TUNNEL CABLING","2007-06-07","2007-10-15"]
["XE_0345","Design Far Hall - Cabling","2007-07-06","2007-08-02"]
["XE_0351","Test Tunnel - Cabling","2008-04-23","2008-05-06"]
["XE_0361","Test Far Hall - Cabling","2008-05-19","2008-06-16"]
["XE_0362","REQD: FEE BO","2008-03-03","2008-03-03"]
["XE_0371","Install Cable to Near Hall Laser - Cabling","2008-01-14","2008-01-18"]
["XE_0372","REQD: Near Hall BO","2007-05-21","2007-05-21"]
["XE_0381","Install Cable to Far Hall Laser - Cabling","2008-05-12","2008-05-16"]
["XE_0382","REQD: Far Hall BO","2007-08-06","2007-08-06"]
["XE_0391","COMP:  Far Hall Laser Installed Ready - Cabling","2008-05-12","2008-05-09"]
["XE_0392","REQD: Tunnel BO","2007-09-14","2007-09-14"]
["XE_0401","COMP: System Integrate & Test FH - Cabling","2008-07-16","2008-07-15"]
["XE_0402","Prep form, Offer, Hire/Train - Mech/Vac Engineer","2005-10-03","2006-02-24"]
["XE_0411","COMP: Near Hall - Cabling","2008-02-05","2008-02-04"]
["XE_0412","Prep form, Offer, Hire/Train - Laser Scientist","2005-10-03","2006-02-24"]
["XE_0421","COMP: FEE - Cabling","2008-05-28","2008-05-27"]
["XE_0422","Prep form, Offer, Hire/Train- Detector Engineer","2005-11-01","2006-02-01"]
["XE_0431","COMP: Far Hall - Cabling","2008-06-17","2008-06-16"]
["XE_0432","Prep form, Offer, Hire - Atomic Physic Engineer","2005-11-01","2006-01-17"]
["XE_0441","Install FEE Cables - Cabling","2008-03-18","2008-05-12"]
["XE_0451","Commission FEE - Cabling","2008-05-28","2008-06-24"]
["XE_0452","Travel FY-05","2005-05-02","2005-09-30"]
["XE_0461","Commission Near Hall - Cabling","2008-02-05","2008-03-04"]
["XE_0462","Travel FY-06","2005-10-03","2006-09-29"]
["XE_0472","Travel FY-07","2006-10-02","2007-09-28"]
["XE_0482","Travel FY-08","2007-10-01","2008-09-30"]
["XE_0492","Prep form, Offer, Hire/Train - PPS Engineer","2005-10-03","2006-02-24"]
["XE_055","SSRL Physics Support","2005-05-02","2005-06-29"]
["XE_100","Prepare Bid Pkg FEE Alarms/Signs - PPS","2006-10-02","2006-10-13"]
["XE_101","Bid Process FEE Alarms/Signs - PPS","2006-10-16","2006-12-12"]
["XE_102","AWARD: Contract FEE Alarms/Signs - PPS","2006-12-13","2006-12-13"]
["XE_103","Vendor Fab/Ship FEE Alarms/Signs - PPS","2006-12-14","2007-02-26"]
["XE_104","RECV: FEE Alarms/Signs - PPS","2007-02-27","2007-02-26"]
["XE_106","REQD: FEE Ben Occ PPS","2008-03-04","2008-03-03"]
["XE_107","Install FEE Alarms/Signs - PPS","2008-03-04","2008-04-28"]
["XE_108","Commission FEE - X-Ray PPS","2008-05-06","2008-06-03"]
["XE_111","Design High Perf Data Storage - Beamline Control","2006-12-01","2007-01-12"]
["XE_112","Prep Bid Pkg FEE Beam Stop Hardware - X-Ray PPS","2006-10-02","2006-10-13"]
["XE_116","AVAIL:  FEE X-Ray PPS","2007-02-27","2007-02-26"]
["XE_12","Prep Bid Pkg NH Beam Stop Hardware - X-Ray PPS","2006-10-02","2006-10-13"]
["XE_120","Prepare Bid Pkg FEE Containment/Interlock - PPS","2006-10-02","2006-10-13"]
["XE_121","Bid Process FEE Cable & Cable Tray - Cabling","2007-08-17","2007-09-14"]
["XE_122","AWARD: Contract FEE Containment/Interlock - PPS","2006-12-13","2006-12-13"]
["XE_1250","Bid Process FEE Containment/Interlock - PPS","2006-10-16","2006-12-12"]
["XE_13","Bid Process NH Beam Stop Hardware - X-Ray PPS","2006-10-16","2006-12-12"]
["XE_131","AWARD: Contract FEE Cable & Cable Tray - Cabling","2007-09-17","2007-09-17"]
["XE_132","Assemble FEE Beam Stop Hardware - X-Ray PPS","2007-02-27","2007-04-23"]
["XE_14","AWARD: NH Beam Stop Hardware - X-Ray PPS","2006-12-13","2006-12-13"]
["XE_141","Vendor Fab/Ship FEE Cable & Cable Tray - Cabling","2007-09-18","2007-10-15"]
["XE_142","Install FEE Beam Stop Hardware","2007-04-24","2007-05-21"]
["XE_1422",null,"2005-05-02","2005-05-02"]
["XE_15","Vendor Fab/Ship NH Beam Stop Hardware-X-Ray PPS","2006-12-14","2007-02-26"]
["XE_151","RECV: FEE Cable & Cable Tray - Cabling","2007-10-16","2007-10-15"]
["XE_152","Install Cable Tray FEE  - Cabling","2008-03-04","2008-04-28"]
["XE_153","COMP: Cabling Design","2007-08-03","2007-08-02"]
["XE_154","Bid Process FEE Racks & Panels - Cabling","2007-08-17","2007-09-14"]
["XE_155","AWARD: Contract FEE Racks & Panels - Cabling","2007-09-17","2007-09-17"]
["XE_156","Vendor Fab/Ship FEE Racks & Panels - Cabling","2007-09-18","2007-10-15"]
["XE_157","RECV: FEE Racks & Panels - Cabling","2007-10-16","2007-10-15"]
["XE_158","Prepare Bid Pkg FEE Racks & Panels - Cabling","2007-08-03","2007-08-16"]
["XE_16","RECV: NH Beam Stop Hardware - X-Ray PPS","2007-02-27","2007-02-26"]
["XE_161","FEE PPS","2006-02-27","2008-03-03"]
["XE_162","Install Cable Tray Near Hall  - Cabling","2007-10-16","2007-12-12"]
["XE_163","Install Cable Near Hall  - Cabling","2007-10-30","2008-01-11"]
["XE_167","REQD: FEE Beneficial Occupancy","2008-03-04","2008-03-03"]
["XE_168","Prepare Bid Pkg FEE Cable & Cable Tray - Cabling","2007-08-03","2007-08-16"]
["XE_17","Assemble NH Beam Stop Hardware - X-Ray PPS","2007-02-27","2007-04-23"]
["XE_170","AWARD: Contract - AP Detectors","2008-02-01","2008-02-01"]
["XE_171","Vendor Fab/Ship - AP Detectors","2008-02-04","2008-02-04"]
["XE_172","Install Tunnel Cable Tray - Cabling","2007-10-16","2007-12-12"]
["XE_175","AWARD: Contract - AP Focusing","2007-06-13","2007-06-13"]
["XE_176","Vendor Fab/Ship - AP Focusing","2007-06-14","2007-08-02"]
["XE_177","AVAIL: FEE Cabling","2007-10-16","2007-10-15"]
["XE_18","Install NH Beam Stop Hardware","2007-04-24","2007-05-21"]
["XE_182","Vendor Fab/Ship FEE Containment/Interlock - PPS","2006-12-14","2007-02-26"]
["XE_184","RECV: FEE Containment/Interlock - PPS","2007-02-27","2007-02-26"]
["XE_185","Install FEE Containment/Interlock - PPS","2008-03-04","2008-04-28"]
["XE_186","Test FEE - PPS","2008-04-29","2008-05-05"]
["XE_192","Install Tunnel Racks - Cabling","2007-12-13","2008-02-26"]
["XE_202","Install Tunnel Cable - Cabling","2008-02-27","2008-04-22"]
["XE_212","RECV: FEE Beam Stop Hardware - X-Ray PPS","2007-02-27","2007-02-26"]
["XE_22","AWARD: 2006 Contract - 2-D X-Ray Detector","2006-01-03","2006-01-03"]
["XE_2200","Specification - Network","2006-06-12","2006-08-07"]
["XE_2201","Design FEE - Network","2006-08-08","2007-02-12"]
["XE_2202","Design Near Hall - Network","2006-08-08","2007-02-12"]
["XE_2203","Prepare Bid Pkg Electronics - Network","2007-02-13","2007-04-10"]
["XE_2205","Design Tunnel - Network","2006-08-08","2007-02-12"]
["XE_2206","Bid Process Electronics - Network","2007-04-11","2007-08-30"]
["XE_2208","Design Far Hall - Network","2006-08-08","2007-02-12"]
["XE_2209","AWARD: Contract Electronics - Network","2007-08-31","2007-09-20"]
["XE_2211","Vendor Fab/Ship Electronics - Network","2007-09-21","2008-02-29"]
["XE_2213","COMP: Network Design","2007-02-13","2007-02-12"]
["XE_2214","RECV: Electronics - Network","2008-03-03","2008-02-29"]
["XE_2216","REQD: FEE Beneficial Occupancy","2008-03-03","2008-02-29"]
["XE_2218","Install Electronics FEE - Network","2008-03-03","2008-04-25"]
["XE_2219","Test FEE - Network","2008-04-28","2008-05-09"]
["XE_222","Bid Process FEE Beam Stop Hardware - X-Ray PPS","2006-10-16","2006-12-12"]
["XE_2221","Install Near Hall  Electronics - Network","2008-05-12","2008-06-09"]
["XE_2223","COMP: CONTROLS DESIGN","2007-06-07","2007-06-06"]
["XE_2224","Test Near Hall - Network","2008-06-10","2008-06-23"]
["XE_2226","Install Tunnel Electronics - Network","2008-06-24","2008-07-08"]
["XE_2227","Test Tunnel - Network","2008-07-09","2008-07-15"]
["XE_2229","Install Far Hall Electronics - Network","2008-07-16","2008-08-12"]
["XE_223","2006 Vendor Contract - 2-D X-Ray Det","2006-01-10","2006-12-15"]
["XE_2230","Programming Near Hall - Network","2007-02-13","2007-06-06"]
["XE_2232","Test Far Hall - Network","2008-08-13","2008-10-08"]
["XE_2233","Integrate & Test System Far Hall - Network","2008-10-09","2008-12-05"]
["XE_2234","Commission - Network","2008-12-08","2009-01-15"]
["XE_22345","AWARD: 2007 Contract - 2-D X-Ray Detector","2007-01-02","2007-01-02"]
["XE_22346","2007 Vendor Contract Funds-2-D X-Ray Det","2007-01-02","2007-12-14"]
["XE_2235","Programming Tunnel - Network","2007-02-13","2007-06-06"]
["XE_2236","AVAIL: FEE Network","2008-03-03","2008-02-29"]
["XE_2237","COMP: Tunnel - Network","2008-07-16","2008-07-15"]
["XE_2238","Programming Far Hall - Network","2007-02-13","2007-06-06"]
["XE_2239","COMP: FEE Network","2008-05-12","2008-05-09"]
["XE_2240","REQD: Near Hall Beneficial Occupancy","2008-05-12","2008-05-09"]
["XE_2242","COMP: Far Hall - Network","2008-10-09","2008-10-08"]
["XE_2243","COMP: System Integrate & Test  Far Hall-Network","2008-12-08","2008-12-05"]
["XE_2244","COMP: Near Hall - Network","2008-06-24","2008-06-23"]
["XE_2245","REQD: Tunnel Beneficial Occupancy","2008-06-24","2008-06-23"]
["XE_2247","Programming FEE - Network","2007-02-13","2007-06-06"]
["XE_2248","REQD: Far Hall Beneficial Occupancy","2008-03-03","2008-02-29"]
["XE_225","Commission Coordinator - FY06","2005-11-01","2006-09-29"]
["XE_2250","NETWORK","2006-06-12","2008-06-23"]
["XE_2254","COMP: Commission - Network","2009-01-16","2009-01-15"]
["XE_2255","Specification - PC Support","2007-03-13","2007-05-14"]
["XE_2257","Design Near Hall - PC Support","2007-05-15","2007-07-11"]
["XE_2258","Prepare Bid Pkg Domain Server - PC Support","2007-09-07","2007-10-04"]
["XE_2259","Prepare Bid Pkg File Server - PC Support","2007-09-07","2007-10-04"]
["XE_2260","AVAIL: Near Hall Network","2008-05-12","2008-05-09"]
["XE_2261","Bid Process Domain Server - PC Support","2007-10-05","2007-11-01"]
["XE_2262","Bid Process File Server - PC Support","2007-10-05","2007-11-01"]
["XE_2263","Design Far Hall - PC Support","2007-07-12","2007-09-06"]
["XE_2264","AWARD: Contract Domain Server - PC Support","2007-11-02","2007-11-02"]
["XE_2265","AWARD: Contract File Server - PC Support","2007-11-02","2007-11-02"]
["XE_2266","Vendor Fab/Ship Domain Server - PC Support","2007-11-05","2008-02-15"]
["XE_2267","Vendor Fab/Ship File Server - PC Support","2007-11-05","2008-02-15"]
["XE_2268","COMP:  Design PC Support","2007-09-07","2007-09-06"]
["XE_2269","RECV: Domain Server - PC Support","2008-02-19","2008-02-15"]
["XE_2270","RECV: File Server - PC Support","2008-02-19","2008-02-15"]
["XE_2275","PC SUPPORT","2007-03-13","2008-04-28"]
["XE_2277","Programming Near Hall - PC Support","2007-05-22","2007-09-13"]
["XE_2278","Install Near Hall Domain Server - PC Support","2008-02-19","2008-03-17"]
["XE_2279","Install Near Hall File Server - PC Support","2008-03-18","2008-04-14"]
["XE_2280","Test Near Hall - PC Support","2008-04-15","2008-04-28"]
["XE_2281","COMP: Near Hall - PC Support","2008-04-29","2008-04-28"]
["XE_2285","AVAIL: Tunnel Network","2008-06-24","2008-06-23"]
["XE_2287","Programming Far Hall - PC Support","2007-07-19","2007-11-08"]
["XE_2288","Install Far Hall PCs/Software/Printer - PC Spt","2008-04-29","2008-05-12"]
["XE_2289","Install Far Hall Domain Server - PC Support","2008-04-29","2008-05-12"]
["XE_2290","Test Far Hall - PC Support","2008-05-13","2008-07-09"]
["XE_2291","COMP: Far Hall - PC Support","2008-07-10","2008-07-09"]
["XE_2292","Integrate & Test System - PC Support","2008-07-10","2008-08-06"]
["XE_2293","COMP: System Integrate & Test  - PC Support","2008-08-07","2008-08-06"]
["XE_2294","Commission - PC Support","2008-08-07","2008-09-04"]
["XE_2295","COMP: Commission - PC Support","2008-09-05","2008-09-04"]
["XE_2297","Vendor Fab/Ship PCs/Software/Printer - PC Spt","2007-11-05","2008-02-15"]
["XE_2298","AVAIL: Far Hall Network","2008-03-03","2008-02-29"]
["XE_2299","Prepare Bid Pkg PCs/Software/Printer - PC Spt","2007-09-07","2007-10-04"]
["XE_2300","RECV: PCs/Software/Printer - PC Support","2008-02-19","2008-02-15"]
["XE_2302","Bid Process PCs/Software/Printer - PC Support","2007-10-05","2007-11-01"]
["XE_2305","AWARD: Contract PCs/Software/Printer - PC Suppo","2007-11-02","2007-11-02"]
["XE_2307","REQD: Far Hall Ben Occ PC Support","2008-04-29","2008-04-28"]
["XE_2309","Install Near Hall PCs/Software/Printer - PC Supp","2008-02-19","2008-03-17"]
["XE_2317","REQD: Near Hall Ben Occ PC Support","2008-02-19","2008-02-15"]
["XE_2319","Install Far Hall File Server - PC Support","2008-04-29","2008-05-12"]
["XE_232","AWARD: FEE Beam Stop Hardware - X-Ray PPS","2006-12-13","2006-12-13"]
["XE_2327","AVAIL: Far Hall PC Support","2008-02-19","2008-02-15"]
["XE_233","Procure Beam Stop Hardware","2007-02-27","2007-07-05"]
["XE_2333","Vendor Fab Beam Stop Hardware","2006-10-02","2007-02-26"]
["XE_23336","Assemble Beam Stop Hardware","2007-07-06","2007-08-30"]
["XE_233367","Install Beam Stop Hardware","2007-08-31","2007-09-28"]
["XE_2337","AVAIL: Near Hall PC Support","2008-02-19","2008-02-15"]
["XE_2400","Prepare Bid Pkg Racks & Panels FH - Cabling","2007-08-03","2007-08-16"]
["XE_2401","Prepare Bid Pkg Cable & Cable Tray FH - Cabling","2007-08-03","2007-08-16"]
["XE_2402","Bid Process Cable & Cable Tray FH - Cabling","2007-08-17","2007-09-14"]
["XE_2403","Bid Process Racks & Panels FH - Cabling","2007-08-17","2007-09-14"]
["XE_2404","AWARD: Contract Cable & Cable Tray FH - Cabling","2007-09-17","2007-10-04"]
["XE_2405","AWARD: Contract Racks & Panels FH - Cabling","2007-09-17","2007-10-04"]
["XE_2406","Vendor Fab/Ship Cable & Cable Tray FH - Cabling","2007-10-05","2007-11-01"]
["XE_2407","Vendor Fab/Ship Racks & Panels FH - Cabling","2007-10-05","2007-11-01"]
["XE_2408","RECV: Cable & Cable Tray FH - Cabling","2007-11-02","2007-11-01"]
["XE_2409","RECV: Racks & Panels FH - Cabling","2007-11-02","2007-11-01"]
["XE_2419","REQD:  Far Hall Beneficial Occupancy","2007-11-02","2007-11-01"]
["XE_242","Vendor Fab/Ship FEE Beam Stop Hardware-X-Ray PPS","2006-12-14","2007-02-26"]
["XE_2429","AVAIL: Far Hall Cabling","2007-11-02","2007-11-01"]
["XE_250","AP Engineering","2006-01-18","2008-10-15"]
["XE_2501","Prepare Bid Pkg Tunnel Cable/Cable Tray - Cablng","2007-08-03","2007-08-16"]
["XE_2502","Bid Process Tunnel Cable & Cable Tray - Cabling","2007-08-17","2007-09-14"]
["XE_2504","AWARD: Contract Tunnel Cable/Cable Tray - Cabln","2007-09-17","2007-09-17"]
["XE_2506","Vendor Fab/Ship Tunnel Cable/Cable Tray - Cablng","2007-09-18","2007-10-15"]
["XE_2508","RECV: Tunnel Cable & Cable Tray - Cabling","2007-10-16","2007-10-15"]
["XE_2518","REQD: Tunnel Beneficial Occupancy","2007-10-16","2007-10-15"]
["XE_2519","Prepare Bid Pkg NH Racks & Panels - Cabling","2007-08-03","2007-08-16"]
["XE_2520","Prepare Bid Pkg NH Cable & Cable Tray - Cabling","2007-08-03","2007-08-16"]
["XE_2521","Bid Process NH Cable & Cable Tray - Cabling","2007-08-17","2007-09-14"]
["XE_2522","Bid Process NH Racks & Panels - Cabling","2007-08-17","2007-09-14"]
["XE_2523","AWARD: Contract NH Cable & Cable Tray - Cabling","2007-09-17","2007-09-17"]
["XE_2524","AWARD: Contract NH Racks & Panels - Cabling","2007-09-17","2007-09-17"]
["XE_2525","Vendor Fab/Ship NH Cable & Cable Tray - Cabling","2007-09-18","2007-10-15"]
["XE_2526","Vendor Fab/Ship NH Racks & Panels - Cabling","2007-09-18","2007-10-15"]
["XE_2527","RECV: NH Cable & Cable Tray - Cabling","2007-10-16","2007-10-15"]
["XE_2528","RECV: NH Racks & Panels - Cabling","2007-10-16","2007-10-15"]
["XE_2538","REQD: Near Hall Beneficial Occupancy","2007-10-16","2007-10-15"]
["XE_2548","AVAIL: Near Hall Cabling","2007-10-16","2007-10-15"]
["XE_2558","AVAIL: Tunnel Cabling","2007-10-16","2007-10-15"]
["XE_2599","Install Near Hall Data Storage - Beamline Contrl","2007-11-16","2008-01-02"]
["XE_2600","Specification - Beamline Controls","2006-06-12","2006-11-30"]
["XE_2601","Design Near Hall - Beamline Control","2006-12-01","2007-06-06"]
["XE_2602","Design Far Hall - Beamline Control","2006-12-01","2007-06-06"]
["XE_2603","COMP:  Design Beamline Control","2007-06-07","2007-06-06"]
["XE_2604","Prep Bid Pkg Rotate/Transl Stage- Beamline Cntrl","2007-06-07","2007-07-05"]
["XE_2605","Prepare Bid Pkg MC Software - Beamline Control","2007-06-07","2007-07-05"]
["XE_2606","Prep Bid Pkg MC Electronics - Beamline Control","2007-06-07","2007-07-05"]
["XE_2607","Bid Process Rotate/Transl Stage - Beamline Cntrl","2007-07-06","2007-08-02"]
["XE_2608","Bid Process MC Software - Beamline Control","2007-07-06","2007-08-02"]
["XE_2609","Bid Process MC Electronics - Beamline Control","2007-07-06","2007-08-02"]
["XE_2610","AWARD: Contract Rotate/Transl Stage - Beam Cntr","2007-08-03","2007-08-22"]
["XE_2611","AWARD: Contract MC Software - Beamline Control","2007-08-03","2007-08-22"]
["XE_2612","AWARD: Contract MC Electronics-Beamline Control","2007-08-03","2007-08-22"]
["XE_2613","Vendor Fab/Ship Rotate/Transl Stage - Beam Cntl","2007-08-23","2007-11-15"]
["XE_2614","Vendor Fab/Ship MC Software - Beamline Control","2007-08-23","2007-11-15"]
["XE_2615","Vendor Fab/Ship MC Electronics - Beamline Cntrl","2007-08-23","2007-11-15"]
["XE_2616","RECV: Rotate/Translate Stages - Beamline Control","2007-11-16","2007-11-15"]
["XE_2617","RECV: MC Software - Beamline Control","2007-11-16","2007-11-15"]
["XE_2618","RECV: MC Electronics - Beamline Control","2007-11-16","2007-11-15"]
["XE_2619","REQD: Near Hall Beneficial Occupancy","2007-11-16","2007-11-15"]
["XE_262","AWARD: Contract - Streak Camera","2006-04-03","2006-04-03"]
["XE_2620","Programming Near Hall - Beamline Control","2006-12-08","2007-04-17"]
["XE_2621","Install Near Hall R/Trans Stage - Beamline Contr","2007-11-16","2008-01-02"]
["XE_2622","Install Near Hall MC Software - Beamline Control","2007-11-16","2008-01-02"]
["XE_2623","Install Near Hall MC Electronics - Beam Control","2008-01-03","2008-01-31"]
["XE_2624","Test Near Hall - Beamline Control","2008-02-01","2008-02-14"]
["XE_2625","COMP: Near Hall - Beamline Control","2008-02-15","2008-02-14"]
["XE_2626","REQD: Far Hall Beneficial Occupancy","2007-11-16","2007-11-15"]
["XE_2627","Programming Far Hall - Beamline Control","2007-11-16","2008-03-28"]
["XE_2628","Install Far Hall Rotate/Trans Stage - Beam Cntrl","2008-02-15","2008-03-14"]
["XE_2629","Install Far Hall MC Software - Beamline Cntrl","2007-11-16","2008-01-02"]
["XE_2630","Install Far Hall MC Electronics - Beam Control","2007-11-16","2008-01-02"]
["XE_2631","Test Far Hall - Beamline Control","2008-02-15","2008-03-14"]
["XE_2632","COMP: Far Hall - Beamline Control","2008-03-17","2008-03-14"]
["XE_2633","Integrate & Test System - Beamline Control","2008-03-17","2008-04-11"]
["XE_2634","COMP: System Integrate & Test  - Beamline Contro","2008-04-14","2008-04-11"]
["XE_2635","Commission - Beamline Control","2008-04-14","2008-05-09"]
["XE_2636","COMP: Commission - Beamline Control","2008-05-12","2008-05-09"]
["XE_2639","AVAIL: Near Hall Beamline Control","2007-11-16","2007-11-15"]
["XE_2640","BEAMLINE CONTROLS","2006-06-12","2007-11-15"]
["XE_2646","AVAIL: Far Hall Beamline Control","2007-11-16","2007-11-15"]
["XE_2700","Specification - Near Hall - Laser PPS","2006-07-19","2006-08-15"]
["XE_2701","Design Near Hall - Laser PPS","2006-08-16","2006-10-11"]
["XE_2702","COMP: Near Hall Design - Laser PPS","2006-12-11","2006-12-08"]
["XE_2703","Safety Review Near Hall - Laser PPS","2006-10-12","2006-12-08"]
["XE_2704","Prep Bid Pkg Near Hall Alarms/Signs - Laser PPS","2006-12-11","2007-01-08"]
["XE_2705","Prep Bid Pkg NHall Contain/Interlck - Laser PPS","2006-12-11","2007-01-08"]
["XE_2707","Bid Process Near Hall Alarms/Signs - Laser PPS","2007-01-09","2007-03-07"]
["XE_2708","Bid Process NHall Contain/Interlck - Laser PPS","2007-01-09","2007-03-07"]
["XE_2710","AWARD: Contract Near Hall Alarms/Signs -Laser P","2007-03-08","2007-03-08"]
["XE_2711","AWARD: Contract NHall Contain/Interlck - Laser","2007-03-08","2007-03-08"]
["XE_2713","Vendor Fab/Ship Near Hall Alarm/Sign - Laser PPS","2007-03-09","2007-05-03"]
["XE_2714","Vendor Ship Near Hall Contain/Intrlck-Laser PPS","2007-03-09","2007-05-03"]
["XE_2716","RECV: Near Hall Alarms/Signs - Laser PPS","2007-05-04","2007-05-03"]
["XE_2717","RECV: Near Hall Containment/Interlock -Laser PPS","2007-05-04","2007-05-03"]
["XE_2719","REQD: Near Hall Beneficial Occup - Laser PPS","2007-05-22","2007-05-21"]
["XE_2720","Install Near Hall Alarms/Signs - Laser PPS","2007-05-22","2007-06-19"]
["XE_2721","Install Near Hall Contain/Interlck - Laser PPS","2007-05-22","2007-06-19"]
["XE_2723","Test Near Hall - Laser PPS","2007-06-20","2007-06-26"]
["XE_2724","COMP: Near Hall Laser PPS","2007-06-27","2007-06-26"]
["XE_2729","AVAIL: Near Hall Laser PPS","2007-05-04","2007-05-03"]
["XE_2730","NEAR HALL LASER PPS","2006-07-19","2007-05-21"]
["XE_2734","Commission Near Hall - Laser PPS","2007-06-27","2007-07-25"]
["XE_2760","Specification Valve - Vacuum","2007-08-23","2007-10-18"]
["XE_2761","Design Valve - Vacuum","2007-10-19","2008-01-02"]
["XE_2762","Design Review Valves - Vacuum","2008-01-03","2008-01-09"]
["XE_2763","COMP: Design Beryllium Valve - Vacuum","2008-01-10","2008-01-09"]
["XE_2764","Prep Bid Pkg Isolation Valve - Vacuum","2008-01-10","2008-01-16"]
["XE_2765","Bid Process Isolation Valve - Vacuum","2008-01-17","2008-02-14"]
["XE_2766","AWARD: Contract Isolation Valve - Vacuum","2008-02-15","2008-02-15"]
["XE_2767","Vendor Fab/Ship Isolation Valve - Vacuum","2008-02-19","2008-04-14"]
["XE_2772","COMP: Near Hall Valve -  Vacuum","2008-05-21","2008-05-20"]
["XE_2777","COMP: Vacuum Valves","2008-05-29","2008-05-28"]
["XE_2779","REQD: Near Hall Ben Occ Valves Vacuum","2008-05-14","2008-05-13"]
["XE_2780","Install Near Hall Valves - Vacuum","2008-05-14","2008-05-20"]
["XE_2781","Assemble Near Hall  Valve - Vacuum","2008-04-16","2008-05-13"]
["XE_2789","AVAIL: Near Hall Valves - Vacuum","2008-05-14","2008-05-13"]
["XE_2790","VACUUM VALVES","2006-06-05","2008-09-30"]
["XE_2800","Prep Bid Pkg Beryllium Valve - Vacuum","2008-01-10","2008-01-16"]
["XE_2801","Bid Process Beryllium Valve - Vacuum","2008-01-17","2008-02-14"]
["XE_2802","AWARD: Contract Beryllium Valve - Vacuum","2008-02-15","2008-02-15"]
["XE_2803","Vendor Fab/Ship Beryllium Valve - Vacuum","2008-02-19","2008-04-14"]
["XE_2804","RECV: Beryllium Valves","2008-04-15","2008-04-14"]
["XE_2805","Assemble Far Hall Valve - Vacuum","2008-04-16","2008-05-13"]
["XE_2806","REQD: Far Hall Beneficial Occupancy","2008-05-14","2008-05-13"]
["XE_2807","Install Far Hall Valve - Vacuum","2008-05-21","2008-05-28"]
["XE_2808","COMP: Far Hall Valve - Vacuum","2008-05-29","2008-05-28"]
["XE_2814","RECV: Isolation Valves","2008-04-15","2008-04-15"]
["XE_2816","AVAIL: Far Hall Valves - Vacuum","2008-05-14","2008-05-13"]
["XE_2818","Commission Valves - Vacuum","2008-05-29","2008-06-25"]
["XE_2900","Specification - Vacuum Hardware","2007-08-23","2007-10-18"]
["XE_2901","Design - Vacuum Hardware","2007-10-19","2008-01-02"]
["XE_2902","Design Review - Vacuum Hardware","2008-01-03","2008-01-09"]
["XE_2903","COMP: Design Vacuum Hardware","2008-01-10","2008-01-09"]
["XE_2905","Prep Bid Pkg - Vacuum Hardware","2008-01-10","2008-01-16"]
["XE_2907","Bid Process - Vacuum Hardware","2008-01-17","2008-02-14"]
["XE_2909","AWARD: Contract - Vacuum Hardware","2008-02-15","2008-02-15"]
["XE_2910","VACUUM HARDWARE","2007-08-23","2008-05-12"]
["XE_2911","Vendor Fab/Ship - Vacuum Hardware","2008-02-19","2008-04-14"]
["XE_2912","RECV:  Vacuum Hardware","2008-04-15","2008-04-14"]
["XE_2918","Assemble Near Hall - Vacuum Hardware","2008-04-15","2008-05-12"]
["XE_2919","REQD: Near Hall Beneficial Occupancy","2008-05-13","2008-05-12"]
["XE_2920","Install Near Hall - Vacuum Hardware","2008-05-13","2008-05-19"]
["XE_2921","COMP: Near Hall Vacuum Hardware","2008-05-20","2008-05-19"]
["XE_2926","Assemble Far Hall - Vacuum Hardware","2008-04-15","2008-05-12"]
["XE_2927","REQD: Far Hall Beneficial Occupancy","2008-05-13","2008-05-12"]
["XE_2928","Install Far Hall - Vacuum Hardware","2008-05-20","2008-05-27"]
["XE_2929","COMP: Far Hall Vacuum Hardware","2008-05-28","2008-05-27"]
["XE_2930","COMP: Vacuum Hardware","2008-05-28","2008-05-27"]
["XE_2933","Specification Ion Pump - Vacuum","2007-08-23","2007-10-18"]
["XE_2934","Design Ion Pump - Vacuum","2007-10-19","2008-01-02"]
["XE_2935","Design Review Ion Pump - Vacuum","2008-01-03","2008-01-09"]
["XE_2936","COMP: Design Ion Pump - Vacuum","2008-01-10","2008-01-09"]
["XE_2937","Prep Bid Pkg Ion Pump - Vacuum","2008-01-10","2008-01-16"]
["XE_2938","Bid Process Ion Pump - Vacuum","2008-01-17","2008-02-14"]
["XE_2939","AWARD: Contract Ion Pump - Vacuum","2008-02-15","2008-02-15"]
["XE_2940","Vendor Fab/Ship Ion Pump - Vacuum","2008-02-19","2008-04-14"]
["XE_2941","RECV: Ion Pump - Vacuum","2008-04-15","2008-04-14"]
["XE_2943","VACUUM ION PUMP","2007-08-23","2008-05-12"]
["XE_2947","REQD: Near Hall Beneficial Occupancy","2008-05-13","2008-05-12"]
["XE_2948","Install Near Hall Ion Pump - Vacuum","2008-05-13","2008-05-27"]
["XE_2949","COMP: Near Hall Ion Pump -Vacuum","2008-05-28","2008-05-27"]
["XE_2954","Assemble Far Hall Ion Pump - Vacuum","2008-04-15","2008-05-12"]
["XE_2955","REQD: Far Hall Beneficial Occupancy","2008-05-13","2008-05-12"]
["XE_2956","Install Far Hall Ion Pump - Vacuum","2008-05-13","2008-05-27"]
["XE_2957","COMP: Far Hall Ion Pump - Vacuum","2008-05-28","2008-05-27"]
["XE_2958","COMP: Ion Pump - Vacuum","2008-05-28","2008-05-27"]
["XE_2959","AVAIL: Near Hall Vacuum Hardware","2008-05-13","2008-05-12"]
["XE_2960","Specification Turbo Pump - Vacuum","2007-08-23","2007-10-18"]
["XE_2961","Design Turbo Pump - Vacuum","2007-10-19","2008-01-02"]
["XE_2962","Design Review Turbo Pump - Vacuum","2008-01-03","2008-01-09"]
["XE_2963","COMP: Design Turbo Pump Vacuum","2008-01-10","2008-01-09"]
["XE_2964","Prep Bid Pkg Turbo Pump - Vacuum","2008-01-10","2008-01-16"]
["XE_2965","Bid Process Turbo Pump - Vacuum","2008-01-17","2008-02-14"]
["XE_2966","AWARD: Contract Turbo Pump - Vacuum","2008-02-15","2008-02-15"]
["XE_2967","Vendor Fab/Ship Turbo Pump - Vacuum","2008-02-19","2008-04-14"]
["XE_2968","RECV:  Turbo Pump - Vacuum","2008-04-15","2008-04-14"]
["XE_2969","Assemble NH Turbo Pump - Vacuum","2008-04-15","2008-05-12"]
["XE_2970","REQD: Near Hall Beneficial Occupancy","2008-05-13","2008-05-12"]
["XE_2971","Install NH Turbo Pump - Vacuum","2008-05-13","2008-05-19"]
["XE_2972","AVAIL: NH Turbo Pump - Vacuum","2008-05-13","2008-05-12"]
["XE_29722","Install Far Hall Turbo Pump - Vacuum","2008-05-13","2008-05-19"]
["XE_29723","COMP:  Far Hall Turbo Pump - Vacuum","2008-05-20","2008-05-19"]
["XE_2973","REQD: Far Hall Beneficial Occupancy","2008-05-13","2008-05-12"]
["XE_2975","AVAIL: Far Hall Ion Pump - Vacuum","2008-05-13","2008-05-12"]
["XE_2977","AVAIL: Far Hall Vacuum Hardware","2008-05-13","2008-05-12"]
["XE_2978","Commission Ion Pump - Vacuum","2008-05-28","2008-06-24"]
["XE_2979","Commission Far Hall Experiment Chamber - Vacuum","2008-04-15","2008-05-12"]
["XE_2980","VACUUM TURBO PUMP","2007-08-23","2008-05-12"]
["XE_2985","COMP: NH Turbo Pump - Vacuum","2008-05-20","2008-05-19"]
["XE_2986","Commission Turbo Pump - Vacuum","2008-05-20","2008-06-17"]
["XE_2987","AVAIL: Near Hall Ion Pump - Vacuum","2008-05-13","2008-05-12"]
["XE_2988","Assemble Near Hall Ion Pump - Vacuum","2008-04-15","2008-05-12"]
["XE_29998","Assemble FH Turbo Pump - Vacuum","2008-04-15","2008-05-12"]
["XE_30","COMP: End Stations Project","2009-04-01","2009-03-31"]
["XE_300","Specification High Perf Data Storage - Beam Cntl","2006-06-12","2006-11-30"]
["XE_3000","Specification Near Hall - X-Ray PPS","2006-02-27","2006-03-24"]
["XE_30008","AVAIL: Far Hall Turbo Pump - Vacuum","2008-05-13","2008-05-12"]
["XE_3001","Design Near Hall - X-Ray PPS","2006-03-27","2006-05-19"]
["XE_3002","COMP: Near Hall Design - X-Ray PPS","2006-07-19","2006-07-18"]
["XE_3003","Prepare Bid Pkg Near Hall Alarms/Signs-X-RayPPS","2006-10-02","2006-10-13"]
["XE_3004","Prep Bid Pkg NHall Contain/Interlock - X-Ray PPS","2006-10-02","2006-10-13"]
["XE_3005","Prepare Near Hall Bid Pkg Detectors - X-Ray PPS","2006-10-02","2006-10-13"]
["XE_3006","Bid Process Near Hall Alarms/Signs - X-Ray PPS","2006-10-16","2006-12-12"]
["XE_3007","Bid Process NHall Containmnt/Interlock-X-Ray PPS","2006-10-16","2006-12-12"]
["XE_3008","Bid Process Near Hall Detectors - X-Ray PPS","2006-10-16","2006-12-12"]
["XE_3009","AWARD: Contract Near Hall Alarms/Signs-X-Ray PPS","2006-12-13","2006-12-13"]
["XE_301","Prepare Bid Pkg Data Storage - Beamline Control","2007-06-07","2007-07-05"]
["XE_3010","AWARD: Contract NHall Contain/Interlock-X-Ray PP","2006-12-13","2006-12-13"]
["XE_3011","AWARD: Contract Near Hall Detectors -X-Ray PPS","2006-12-13","2006-12-13"]
["XE_3012","Vendor Fab/Ship Near Hall Alarms/Signs-X-Ray PPS","2006-12-14","2007-02-26"]
["XE_3013","Vendor Fab/Ship NHall Contain/Interlock-X-RayPPS","2006-12-14","2007-02-26"]
["XE_3014","Vendor Fab/Ship Near Hall Detectors -X-Ray PPS","2006-12-14","2007-02-26"]
["XE_3015","RECV: Near Hall Alarms/Signs - X-Ray PPS","2007-02-27","2007-02-26"]
["XE_3016","RECV: Near Hall Containment/Interlock-X-Ray PPS","2007-02-27","2007-02-26"]
["XE_3017","RECV: Near Hall Detectors - X-Ray PPS","2007-02-27","2007-02-26"]
["XE_3018","REQD: Near Hall Beneficial Occupancy","2007-05-22","2007-05-21"]
["XE_3019","Install Near Hall Alarms/Signs - X-Ray PPS","2007-05-22","2007-06-19"]
["XE_302","Bid Process Data Storage - Beamline Control","2007-07-06","2007-08-02"]
["XE_3020","Install Near Hall Containment/Interlock-X-RayPPS","2007-05-22","2007-06-19"]
["XE_3021","Install Near Hall Detectors - X-Ray PPS","2007-05-22","2007-06-19"]
["XE_3022","Test Near Hall - X-Ray PPS","2007-06-20","2007-06-26"]
["XE_3023","COMP: Near Hall X-Ray PPS","2007-06-27","2007-06-26"]
["XE_3028","AVAIL: Near Hall X-Ray PPS","2007-02-27","2007-02-26"]
["XE_303","AWARD: Contract Data Storage - Beamline Ctrl","2007-08-03","2007-08-22"]
["XE_3030","NEAR HALL X-RAY PPS","2006-02-27","2007-05-21"]
["XE_3031","Safety Review Near Hall - X-Ray PPS","2006-05-22","2006-07-18"]
["XE_3033","Commission Near Hall - X-Ray PPS","2007-06-27","2007-07-25"]
["XE_304","Vendor Fab/Ship Data Storage - Beamline Ctrl","2007-08-23","2007-10-18"]
["XE_305","RECV: High Perf Data Storage - Beamline Control","2007-10-19","2007-10-18"]
["XE_306","Install Data Storag Near Hall - Beamline Cntrl","2007-10-19","2007-11-15"]
["XE_307","Test High Perf Data Storage - Beamline Control","2008-01-03","2008-01-09"]
["XE_314","Vendor Ship Computers","2007-08-23","2007-10-18"]
["XE_316","Install Data Storage Far Hall - Beamline Cntrl","2007-11-16","2008-01-02"]
["XE_333","AWARD:  Computer - Beamline Control","2007-08-03","2007-08-22"]
["XE_3333","COMP:  XRAY MPS, PPS DESIGN","2006-07-19","2006-07-18"]
["XE_3424","Crystals & Gratings","2006-10-31","2008-06-30"]
["XE_4","AWARD 2006 Contract-Prototype-2-D X-Ray Det","2006-01-03","2006-01-03"]
["XE_400","Specification Tunnel - X-Ray PPS","2006-02-27","2006-03-24"]
["XE_4000","Specification - Laser Diagnostics","2007-01-04","2007-03-30"]
["XE_4001","Design - Laser Diagnostics","2007-08-01","2007-09-26"]
["XE_4002","COMP:  Design - Laser Diagnostics","2007-10-11","2007-10-10"]
["XE_4003","Safety Review - Laser Diagnostics","2007-09-27","2007-10-10"]
["XE_4004","Prep Bid Pkg  Energy Sensors - Laser Diagnostics","2007-10-11","2007-10-24"]
["XE_4005","Prep Bid Pkg  IR FROG - Laser Diagnostics","2007-10-11","2007-10-24"]
["XE_4006","Prepare  Bid Pkg Fast Diodes - Laser Diagnostics","2007-10-11","2007-10-24"]
["XE_4007","Bid Process  Energy Sensors - Laser Diagnostics","2007-10-25","2008-01-08"]
["XE_4008","Bid Process  IR FROG - Laser Diagnostics","2007-10-25","2008-01-08"]
["XE_4009","Bid Process  Fast Diodes - Laser Diagnostics","2007-10-25","2008-01-08"]
["XE_401","Design Tunnel - X-Ray PPS","2006-03-27","2006-05-19"]
["XE_4010","AWARD: Contract Energy Sensors - Laser Diagnost","2008-01-09","2008-01-09"]
["XE_4011","AWARD: Contract - IR FROG - Laser Diagnostics","2008-01-09","2008-01-09"]
["XE_4012","AWARD: Contract - Fast Diodes - Laser Diagnosti","2008-01-09","2008-01-09"]
["XE_4013","Vendor Fab/Ship Energy Sensor - Laser Diagnostic","2008-01-10","2008-03-07"]
["XE_4014","Vendor Ship  IR FROG- Laser Diagnostics","2008-01-10","2008-03-07"]
["XE_4015","Vendor Fab/Ship  Fast Diodes - Laser Diagnostics","2008-01-10","2008-03-07"]
["XE_4016","RECV:  Energy Sensors - Laser Diagnostics","2008-03-10","2008-03-07"]
["XE_4017","RECV:  IR FROG - Laser Diagnostics","2008-03-10","2008-03-07"]
["XE_4018","RECV:  Fast Diodes - Laser Diagnostics","2008-03-10","2008-03-07"]
["XE_4019","REQD:  Near Hall Beneficial Occup - Laser Diag","2008-03-10","2008-03-07"]
["XE_402","COMP: Tunnel Design - X-Ray PPS","2006-07-19","2006-07-18"]
["XE_4020","Install  Energy Sensors - Laser Diagnostics","2008-03-10","2008-04-04"]
["XE_4021","Install  IR FROG - Laser Diagnostics","2008-03-10","2008-04-04"]
["XE_4023","Test - Laser Diagnostics","2008-04-07","2008-04-11"]
["XE_4024","COMP:  Laser Diagnostics","2008-04-14","2008-04-11"]
["XE_4025","Prep Bid Pkg Oscillo Scope - Laser Diagnostics","2007-10-11","2007-10-24"]
["XE_4026","Prep Bid Pkg  Autocorrelators - Laser Diagnostic","2007-10-11","2007-10-24"]
["XE_4028","Bid Process Oscillo Scope - Laser Diagnostics","2007-10-25","2008-01-08"]
["XE_4029","Bid Process  Autocorrelators - Laser Diagnostics","2007-10-25","2008-01-08"]
["XE_403","Prepare Bid Pkg Tunnel Alarms/Signs - X-Ray PPS","2006-10-02","2006-10-13"]
["XE_4030","Install  Fast Diodes - Laser Diagnostics","2008-03-10","2008-04-04"]
["XE_4031","AWARD: Contract Oscilloscope- Laser Diagnostics","2008-01-09","2008-01-09"]
["XE_4032","AWARD: Contract  Autocorrelator - Laser Diagnos","2008-01-09","2008-01-09"]
["XE_4034","Vendor Fab/Ship  Oscillo Scope - Laser Diagnost","2008-01-10","2008-03-07"]
["XE_4035","Vendor Ship Autocorrelators - Laser Diagnostics","2008-01-10","2008-03-07"]
["XE_4037","RECV:  Oscillo Scope - Laser Diagnostics","2008-03-10","2008-03-07"]
["XE_4038","RECV:  Autocorrelators - Laser Diagnostics","2008-03-10","2008-03-07"]
["XE_404","Prep Bid Pkg Tunnel Containmt/Interlock-X-RayPPS","2006-10-02","2006-10-13"]
["XE_4040","LASER DIAGNOSTICS","2006-06-05","2008-09-30"]
["XE_4041","Install  Oscilloscope - Laser Diagnostics","2008-03-10","2008-04-04"]
["XE_4042","Install  Autocorrelators - Laser Diagnostics","2008-03-10","2008-04-04"]
["XE_4048","AVAIL: Laser Diagnostics","2008-03-10","2008-03-07"]
["XE_405","Prepare Bid Pkg Tunnel Detectors - X-Ray PPS","2006-10-02","2006-10-13"]
["XE_406","Bid Process Tunnel Alarms/Signs - X-Ray PPS","2006-10-16","2006-12-12"]
["XE_407","Bid Process Tunnel Containmt/Interlock-X-Ray PPS","2006-10-16","2006-12-12"]
["XE_408","Bid Process Tunnel Detectors - X-Ray PPS","2006-10-16","2006-12-12"]
["XE_409","AWARD: Contract Tunnel Alarms/Signs - X-Ray PPS","2006-12-13","2006-12-13"]
["XE_410","AWARD: Contract Tunnel Interlock-X-Ray PPS","2006-12-13","2006-12-13"]
["XE_411","AWARD: Contract Tunnel Detectors - X-Ray PPS","2006-12-13","2006-12-13"]
["XE_412","Vendor Fab/Ship Tunnel Alarms/Signs - X-Ray PPS","2006-12-14","2007-02-26"]
["XE_413","Vendor Ship Tunnel Contain/Interlock-X-RayPPS","2006-12-14","2007-02-26"]
["XE_414","Vendor Fab/Ship Tunnel Detectors - X-Ray PPS","2006-12-14","2007-02-26"]
["XE_415","RECV: Tunnel Alarms/Signs - X-Ray PPS","2007-02-27","2007-02-26"]
["XE_416","RECV: Tunnel Containment/Interlock - X-Ray PPS","2007-02-27","2007-02-26"]
["XE_417","RECV: Tunnel Detectors - X-Ray PPS","2007-02-27","2007-02-26"]
["XE_418","REQD: Tunnel Beneficial Occupancy - X-Ray PPS","2007-09-17","2007-09-14"]
["XE_419","Install Tunnel Alarms/Signs - X-Ray PPS","2007-09-17","2007-11-09"]
["XE_420","Install Tunnel Containment/Interlock - X-Ray PPS","2007-09-17","2007-10-12"]
["XE_421","Install Tunnel Detectors - X-Ray PPS","2007-09-17","2007-10-12"]
["XE_422","Test Tunnel - X-Ray PPS","2007-11-12","2007-11-16"]
["XE_423","COMP: Tunnel X-Ray PPS","2007-11-19","2007-11-16"]
["XE_425","Specification Far Hall - PPS","2006-02-27","2006-03-24"]
["XE_426","Design Far Hall - PPS","2006-03-27","2006-05-19"]
["XE_427","COMP: Far Hall Design - PPS","2006-07-19","2006-07-18"]
["XE_428","Prepare Bid Pkg Far Hall Alarms/Signs - PPS","2006-10-02","2006-10-13"]
["XE_429","Prep Bid Pkg Far Hall Contain/Interlock - PPS","2006-10-02","2006-10-13"]
["XE_430","Prepare Far Hall Bid Pkg Detectors - PPS","2006-10-02","2006-10-13"]
["XE_431","Bid Process Far Hall Alarms/Signs - PPS","2006-10-16","2006-12-12"]
["XE_432","Bid Process Far Hall Containmnt/Interlock - PPS","2006-10-16","2006-12-12"]
["XE_433","Bid Process Far Hall Detectors - PPS","2006-10-16","2006-12-12"]
["XE_434","AWARD: Contract Far Hall Alarms/Signs - PPS","2006-12-13","2006-12-13"]
["XE_435","AWARD: Contract Far Hall Contain/Interlock - PP","2006-12-13","2006-12-13"]
["XE_436","AWARD: Contract Far Hall Detectors - PPS","2006-12-13","2006-12-13"]
["XE_437","Vendor Fab/Ship Far Hall Alarms/Signs - PPS","2006-12-14","2007-02-26"]
["XE_438","Vendor Fab/Ship Far Hall Contain/Interlock- PPS","2006-12-14","2007-02-26"]
["XE_439","Vendor Fab/Ship Far Hall Detectors - PPS","2006-12-14","2007-02-26"]
["XE_44","Management - FY-05 - Mar thru Sep","2005-05-02","2005-09-30"]
["XE_440","RECV: Far Hall Alarms/Signs - PPS","2007-02-27","2007-02-26"]
["XE_4400","Engineering - Laser Timing","2006-10-02","2008-09-30"]
["XE_44002","2005 Oct, Nov, Dec - 2-D X-Ray Det","2005-10-03","2005-12-16"]
["XE_4404","Commission - Network","2008-12-08","2009-01-15"]
["XE_4405","Vendor Fab/Ship - AP","2007-11-08","2008-01-15"]
["XE_4406","Vendor Fab/Ship - AP","2006-11-08","2007-01-12"]
["XE_4408","AWARD: Contract - AP","2007-11-08","2007-11-08"]
["XE_4409","AWARD: Contract - AP","2006-11-08","2006-11-08"]
["XE_441","RECV: Far Hall Containment/Interlock - PPS","2007-02-27","2007-02-26"]
["XE_442","RECV: Far Hall Detectors - PPS","2007-02-27","2007-02-26"]
["XE_443","REQD: Far Hall Beneficial Occupancy","2007-08-07","2007-08-06"]
["XE_444","Install Far Hall Alarms/Signs - PPS","2007-08-07","2007-09-04"]
["XE_4447","Procure Beam Stop Hardware","2006-10-02","2007-02-26"]
["XE_44478","Procure Beam Stop Hardware","2007-02-27","2007-07-05"]
["XE_44479","Assemble Beam Stop Hardware","2007-07-06","2007-08-02"]
["XE_444791","Install Beam Stop Hardware","2007-08-07","2007-09-04"]
["XE_445","Install Far Hall Containment/Interlock - PPS","2007-08-07","2007-09-04"]
["XE_44556","Prep Bid Pkg - AP Data Analysis","2007-07-19","2007-07-25"]
["XE_44557","Bid Process - AP Data Analysis","2007-07-26","2007-08-22"]
["XE_44558","AWARD: Contract - AP Data Analysis","2007-08-23","2007-08-23"]
["XE_44559","Vendor Fab/Ship - AP Data Analysis","2007-08-24","2007-10-19"]
["XE_44560","RECV:  AP Data Analysis","2007-10-22","2007-10-19"]
["XE_44561","Prep Bid Pkg - AP Optics","2007-05-08","2007-05-14"]
["XE_44562","Bid Process - AP Optics","2007-05-15","2007-06-12"]
["XE_44563","AWARD: Contract - AP Optics","2007-06-13","2007-06-13"]
["XE_44564","Vendor Fab/Ship - AP Optics","2007-06-14","2007-08-02"]
["XE_44565","RECV:  AP Optics","2007-08-03","2007-08-02"]
["XE_4457","End Stations Commissioning Complete","2009-04-01","2009-03-31"]
["XE_446","Install Far Hall Detectors - PPS","2007-08-07","2007-09-04"]
["XE_447","Test Far Hall - PPS","2007-09-05","2007-09-11"]
["XE_448","COMP: Far Hall X-Ray PPS","2007-09-12","2007-09-11"]
["XE_450","TUNNEL X-Ray PPS","2006-02-27","2007-09-14"]
["XE_451","Safety Review Tunnel - X-Ray PPS","2006-05-22","2006-07-18"]
["XE_453","AVAIL: Far Hall X-Ray PPS","2007-02-27","2007-02-26"]
["XE_455","FAR HALL PPS","2006-02-27","2007-08-06"]
["XE_456","Safety Review Far Hall - PPS","2006-05-22","2006-07-18"]
["XE_458","Commission Far Hall X-Ray PPS","2007-09-12","2007-10-09"]
["XE_463","Commission Tunnel - X-Ray PPS","2007-11-19","2008-01-03"]
["XE_468","AVAIL: Tunnel X-Ray PPS","2007-02-27","2007-02-26"]
["XE_5000","Prepare Bid Pkg FEE Sensors - MPS","2006-07-19","2006-08-01"]
["XE_5001","Bid Process FEE Sensors - MPS","2006-08-02","2006-09-27"]
["XE_5002","AWARD: Contract FEE Sensors - MPS","2006-10-02","2006-10-02"]
["XE_5003","Vendor Fab/Ship FEE Sensors - MPS","2006-10-03","2006-11-29"]
["XE_5004","RECV: FEE Sensors - MPS","2006-11-30","2006-11-29"]
["XE_5005","REQD: FEE Beneficial Occupancy","2008-03-04","2008-03-03"]
["XE_5006","Install FEE Sensors - MPS","2008-03-04","2008-04-28"]
["XE_5007","Prepare Bid Pkg FEE Interlocks - MPS","2006-07-19","2006-08-01"]
["XE_5008","AWARD: Contract FEE Interlocks - MPS","2006-10-02","2006-10-02"]
["XE_5009","Bid Process FEE Interlocks - MPS","2006-08-02","2006-09-27"]
["XE_5010","Vendor Fab/Ship FEE Interlocks - MPS","2006-10-03","2006-11-29"]
["XE_5011","RECV: FEE Interlocks - MPS","2006-11-30","2006-11-29"]
["XE_5012","Install FEE Interlocks - MPS","2008-03-04","2008-04-28"]
["XE_5013","Test FEE - MPS","2008-04-29","2008-05-05"]
["XE_5014","Design FEE - MPS","2006-03-27","2006-05-19"]
["XE_5015","Specification FEE - MPS","2006-02-27","2006-03-24"]
["XE_5016","COMP: FEE Design - MPS","2006-07-19","2006-07-18"]
["XE_5017","Prepare Bid Pkg FEE Valves - MPS","2006-07-19","2006-08-01"]
["XE_5018","Bid Process FEE Valves - MPS","2006-08-02","2006-09-27"]
["XE_5019","AWARD: Contract FEE Valves - MPS","2006-10-02","2006-10-02"]
["XE_5020","Vendor Fab/Ship FEE Valves - MPS","2006-10-03","2006-11-29"]
["XE_5021","RECV: FEE Valves - MPS","2006-11-30","2006-11-29"]
["XE_5022","COMP: FEE MPS","2008-05-06","2008-05-05"]
["XE_5023","Install FEE Valves - MPS","2008-03-04","2008-04-28"]
["XE_5024","Specification Near Hall - MPS","2006-02-27","2006-03-24"]
["XE_5025","Design Near Hall - MPS","2006-03-27","2006-05-19"]
["XE_5026","COMP: Near Hall Design - MPS","2006-07-19","2006-07-18"]
["XE_5027","Prepare Bid Pkg Near Hall Sensors - MPS","2006-10-02","2006-10-13"]
["XE_5028","Prep Bid Pkg Near Hall Interlocks - MPS","2006-10-02","2006-10-13"]
["XE_5029","Prepare Near Hall Bid Pkg Valves - MPS","2006-10-02","2006-10-13"]
["XE_503","Specification - Chamber Spt Table","2007-02-27","2007-04-23"]
["XE_5030","Bid Process Near Hall Sensors - MPS","2006-10-16","2006-12-12"]
["XE_5031","Bid Process Near Hall Interlock - MPS","2006-10-16","2006-12-12"]
["XE_5032","Bid Process Near Hall Valves - MPS","2006-10-16","2006-12-12"]
["XE_5033","AWARD: Contract Near Hall Sensors - MPS","2006-12-13","2006-12-13"]
["XE_5034","AWARD: Contract Near Hall Interlocks - MPS","2006-12-13","2006-12-13"]
["XE_5035","AWARD: Contract Near Hall Valves - MPS","2006-12-13","2006-12-13"]
["XE_5036","Vendor Fab/Ship Near Hall Sensors - MPS","2006-12-14","2007-02-26"]
["XE_5037","Vendor Fab/Ship Near Hall Interlocks- MPS","2006-12-14","2007-02-26"]
["XE_5038","Vendor Fab/Ship Near Hall Valves - MPS","2006-12-14","2007-02-26"]
["XE_5039","RECV: Near Hall Sensors - MPS","2007-02-27","2007-02-26"]
["XE_504","Design - Chamber Spt Table","2007-04-24","2007-06-19"]
["XE_5040","RECV: Near Hall Interlocks - MPS","2007-02-27","2007-02-26"]
["XE_5041","RECV: Near Hall Valves - MPS","2007-02-27","2007-02-26"]
["XE_5042","REQD: Near Hall Beneficial Occupancy","2007-05-22","2007-05-21"]
["XE_5043","Install Near Hall Sensors - MPS","2007-05-22","2007-06-19"]
["XE_5044","Install Near Hall Interlocks - MPS","2007-05-22","2007-06-19"]
["XE_5045","Install Near Hall Valves - MPS","2007-05-22","2007-06-19"]
["XE_5046","Test Near Hall - MPS","2007-06-20","2007-06-26"]
["XE_5047","COMP: Near Hall MPS","2007-06-27","2007-06-26"]
["XE_5048","Specification Tunnel - MPS","2006-02-27","2006-03-24"]
["XE_5049","Design Tunnel - MPS","2006-03-27","2006-05-19"]
["XE_505","Design Review - Chamber Spt Table","2007-06-20","2007-06-26"]
["XE_5050","COMP: Tunnel Design - MPS","2006-07-19","2006-07-18"]
["XE_5051","Prepare Bid Pkg Tunnel Sensors - MPS","2006-10-02","2006-10-13"]
["XE_5052","Prep Bid Pkg Tunnel Interlocks - MPS","2006-10-02","2006-10-13"]
["XE_5053","Prepare Bid Pkg Tunnel Valves - MPS","2006-10-02","2006-10-13"]
["XE_5054","Bid Process Tunnel Sensors - MPS","2006-10-16","2006-12-12"]
["XE_5055","Bid Process Tunnel Interlocks - MPS","2006-10-16","2006-12-12"]
["XE_5056","Bid Process Tunnel Valves - MPS","2006-10-16","2006-12-12"]
["XE_5057","AWARD: Contract Tunnel Sensors - MPS","2006-12-13","2006-12-13"]
["XE_5058","AWARD: Contract Tunnel Interlocks - MPS","2006-12-13","2006-12-13"]
["XE_5059","AWARD: Contract Tunnel Valves - MPS","2006-12-13","2006-12-13"]
["XE_506","COMP: Design Chamber Support Table","2007-06-27","2007-06-26"]
["XE_5060","Vendor Fab/Ship Tunnel Sensors - MPS","2006-12-14","2007-02-26"]
["XE_5061","Vendor Fab/Ship Tunnel Interlocks - MPS","2006-12-14","2007-02-26"]
["XE_5062","Vendor Fab/Ship Tunnel Valves - MPS","2006-12-14","2007-02-26"]
["XE_5063","RECV: Tunnel Sensors - MPS","2007-02-27","2007-02-26"]
["XE_5064","RECV: Tunnel Interlocks - MPS","2007-02-27","2007-02-26"]
["XE_5065","RECV: Tunnel Valves - MPS","2007-02-27","2007-02-26"]
["XE_5066","REQD: Tunnel Beneficial Occupancy","2007-09-17","2007-09-14"]
["XE_5067","Install Tunnel Sensors - MPS","2007-09-17","2007-10-12"]
["XE_5068","Install Tunnel Interlocks - MPS","2007-09-17","2007-10-12"]
["XE_5069","Install Tunnel Valves - MPS","2007-09-17","2007-10-12"]
["XE_507","Prep Bid Pkg Metal Products - Chamber Spt Table","2007-06-27","2007-07-03"]
["XE_5070","Test Tunnel - MPS","2007-10-15","2007-10-19"]
["XE_5071","COMP: Tunnel MPS","2007-10-22","2007-10-19"]
["XE_5072","Specification Far Hall - MPS","2006-02-27","2006-03-24"]
["XE_5073","Design Far Hall - MPS","2006-03-27","2006-05-19"]
["XE_5074","COMP: Far Hall Design - MPS","2006-07-19","2006-07-18"]
["XE_5075","Prepare Bid Pkg Far Hall Sensors - MPS","2006-10-02","2006-10-13"]
["XE_5076","Prep Bid Pkg Far Hall Interlocks - MPS","2006-10-02","2006-10-13"]
["XE_5077","Prepare Far Hall Bid Pkg Valves - MPS","2006-10-02","2006-10-13"]
["XE_5078","Bid Process Far Hall Sensors - MPS","2006-10-16","2006-12-12"]
["XE_5079","Bid Process Far Hall Interlock - MPS","2006-10-16","2006-12-12"]
["XE_508","Bid Process Metal Products - Chamber Spt Table","2007-07-05","2007-08-01"]
["XE_5080","Bid Process Far Hall Valves - MPS","2006-10-16","2006-12-12"]
["XE_5081","AWARD: Contract Far Hall Sensors - MPS","2006-12-13","2006-12-13"]
["XE_5082","AWARD: Contract Far Hall Interlocks - MPS","2006-12-13","2006-12-13"]
["XE_5083","AWARD: Contract Far Hall Valves - MPS","2006-12-13","2006-12-13"]
["XE_5084","Vendor Fab/Ship Far Hall Sensors - MPS","2006-12-14","2007-02-26"]
["XE_5085","Vendor Fab/Ship Far Hall Interlocks- MPS","2006-12-14","2007-02-26"]
["XE_5086","Vendor Fab/Ship Far Hall Valves - MPS","2006-12-14","2007-02-26"]
["XE_5087","RECV: Far Hall Sensors - MPS","2007-02-27","2007-02-26"]
["XE_5088","RECV: Far Hall Interlocks - MPS","2007-02-27","2007-02-26"]
["XE_5089","RECV: Far Hall Valves - MPS","2007-02-27","2007-02-26"]
["XE_509","AWARD: Contract Metal Product-Chamber Spt Table","2007-08-02","2007-08-02"]
["XE_5090","REQD: Far Hall Beneficial Occupancy","2007-08-07","2007-08-06"]
["XE_5091","Install Far Hall Sensors - MPS","2007-08-07","2007-09-04"]
["XE_5092","Install Far Hall Interlocks - MPS","2007-08-07","2007-09-04"]
["XE_5093","Install Far Hall Valves - MPS","2007-08-07","2007-09-04"]
["XE_5094","Test Far Hall - MPS","2007-09-05","2007-09-11"]
["XE_5095","COMP: Far Hall MPS","2007-09-12","2007-09-11"]
["XE_5096","AVAIL: Tunnel X-Ray MPS","2007-02-27","2007-02-26"]
["XE_5097","Commission Near Hall - X-Ray MPS","2007-06-27","2007-07-25"]
["XE_5098","Safety Review - MPS","2006-05-22","2006-07-18"]
["XE_510","Vendor Fab/Ship Metal Products-Chamber Spt Table","2007-08-03","2007-09-28"]
["XE_5100","AVAIL:  Far Hall X-Ray MPS","2007-02-27","2007-02-26"]
["XE_5101","Commission Tunnel - X-Ray MPS","2007-10-22","2007-11-16"]
["XE_5102","Safety Review - MPS","2006-05-22","2006-07-18"]
["XE_5104","Safety Review - MPS","2006-05-22","2006-07-18"]
["XE_5105","FEE MPS","2006-02-27","2008-03-03"]
["XE_5108","TUNNEL MPS","2006-02-27","2007-09-14"]
["XE_511","RECV: Metal Products - Chamber Spt Table","2007-10-01","2007-09-28"]
["XE_5112","FAR HALL MPS","2006-02-27","2007-08-06"]
["XE_5114","Safety Review - MPS","2006-05-22","2006-07-18"]
["XE_5115","AVAIL: FEE X-Ray MPS","2006-11-30","2006-11-29"]
["XE_512","Assemble Far Hall - Chamber Spt Table","2008-03-11","2008-07-01"]
["XE_5122","AVAIL: Near Hall X-Ray PPS","2007-02-27","2007-02-26"]
["XE_5124","NEAR HALL MPS","2006-02-27","2007-05-21"]
["XE_5125","Commission Far Hall - X-Ray MPS","2007-09-12","2007-10-09"]
["XE_513","Install Far Hall - Chamber Spt Table","2008-07-02","2008-07-09"]
["XE_5132","Commission FEE - X-Ray MPS","2008-05-06","2008-06-03"]
["XE_514","COMP: Far Hall Chamber Spt Table","2008-07-10","2008-07-09"]
["XE_515","Assemble Near Hall - Chamber Spt Table","2007-10-01","2008-02-08"]
["XE_516","Install Near Hall - Chamber Spt Table","2008-02-11","2008-03-10"]
["XE_517","COMP: Near Hall Chamber Spt Table","2008-03-11","2008-03-10"]
["XE_522","REQD: Far Hall Beneficial Occupancy","2008-07-02","2008-07-01"]
["XE_523","CHAMBER SUPPORT TABLES","2007-02-27","2008-07-01"]
["XE_525","REQD: Near Hall Beneficial Occupancy","2008-02-11","2008-02-08"]
["XE_527","COMP: Chamber Support Tables","2008-07-10","2008-07-09"]
["XE_5300","Specification Near Hall - Experimental Chamber","2007-02-27","2007-04-23"]
["XE_5301","Design Near Hall - Experimental Chamber","2007-04-24","2007-08-15"]
["XE_5302","Design Review Near Hall - Experimental Chamber","2007-08-16","2007-08-22"]
["XE_5303","COMP: Design Near Hall - Experimental Chamber","2007-08-23","2007-08-22"]
["XE_5304","Prep Bid Pkg Near Hall - Experimental Chamber","2007-08-23","2007-08-29"]
["XE_5305","Bid Process Near Hall - Experimental Chamber","2007-08-30","2007-09-27"]
["XE_5306","AWARD: Contract Near Hall - Experimental Chambe","2007-09-28","2007-09-28"]
["XE_5307","Vendor Fab/Ship Near Hall - Experimental Chamber","2007-10-01","2007-11-27"]
["XE_5308","RECV:  Near Hall Experimental Chamber","2007-11-28","2007-11-27"]
["XE_5309","Assemble Near Hall - Experimental Chamber","2007-11-28","2008-04-07"]
["XE_5310","REQD: Near Hall Beneficial Occupancy","2008-04-08","2008-04-07"]
["XE_5311","Install Near Hall - Experimental Chamber","2008-04-08","2008-05-05"]
["XE_5312","COMP: Near Hall Experimental Chamber","2008-05-13","2008-05-12"]
["XE_5313","Commission Near Hall Experiment Chamber - Vacuum","2008-05-13","2008-06-10"]
["XE_532","AVAIL: Far Hall - Chamber Support Table","2008-07-02","2008-07-01"]
["XE_5320","NEAR HALL EXPERIMENTAL CHAMBER","2007-02-27","2008-04-07"]
["XE_5321","Leak Check/Test Near Hall - Experimental Chamber","2008-05-06","2008-05-12"]
["XE_5330","AVAIL: Near Hall Experimental Chamber","2008-04-08","2008-04-07"]
["XE_535","AVAIL: Near Hall - Chamber Support Table","2008-02-11","2008-02-08"]
["XE_5400","Specification Far Hall - Experimental Chamber","2007-02-27","2007-04-23"]
["XE_5401","Design Far Hall - Experimental Chamber","2007-04-24","2007-08-15"]
["XE_5402","Design Review Far Hall - Experimental Chamber","2007-08-16","2007-08-22"]
["XE_5403","COMP: Design Far Hall Experimental Chamber","2007-08-23","2007-08-22"]
["XE_5404","Prep Bid Pkg Far Hall - Experimental Chamber","2007-08-23","2007-08-29"]
["XE_5405","Bid Process Far Hall - Experimental Chamber","2007-08-30","2007-09-27"]
["XE_5406","AWARD: Contract Far Hall - Experimental Chamber","2007-09-28","2007-09-28"]
["XE_5407","Vendor Fab/Ship Far Hall - Experimental Chamber","2007-10-01","2007-11-27"]
["XE_5408","RECV:  Far Hall Experimental Chamber","2007-11-28","2007-11-27"]
["XE_5410","FAR HALL EXPERIMENTAL CHAMBER","2007-02-27","2008-04-07"]
["XE_5411","COMP: Far Hall Laser PPS","2007-09-12","2007-09-11"]
["XE_5413","Assemble Far Hall - Experimental Chamber","2007-11-28","2008-04-07"]
["XE_5414","REQD: Far Hall Beneficial Occupancy","2008-04-08","2008-04-07"]
["XE_5415","Install Far Hall - Experimental Chamber","2008-04-08","2008-04-14"]
["XE_5416","COMP: Far Hall Experimental Chamber","2008-05-13","2008-05-12"]
["XE_5421","Commission Far Hall - Laser PPS","2007-09-12","2007-10-09"]
["XE_5424","AVAIL: Far Hall Experimental Chamber","2008-04-08","2008-04-07"]
["XE_5488","Leak Check/Test - Experimental Chamber","2008-04-08","2008-04-14"]
["XE_56","Commission -  Laser Diagnostics","2008-04-14","2008-07-08"]
["XE_567","2005 Design Review - 2-D X-Ray Detector","2006-03-30","2006-04-05"]
["XE_5675","COMP: 2005 Design Review - 2-D X-Ray Detector","2006-04-06","2006-04-05"]
["XE_57","Commission - Optic Transport","2008-07-25","2008-08-21"]
["XE_58","Commission Far Hall - Laser Timing","2008-05-08","2008-10-27"]
["XE_59","Commission Near Hall - Laser Amplifiers","2008-07-07","2009-01-06"]
["XE_6000","Specification - Laser Supp/Optic Transport","2007-01-04","2007-03-02"]
["XE_6001","Design - Laser Supp/Optic Transport","2007-08-01","2007-11-21"]
["XE_6003","COMP: Design Laser Supp/Optic Transport","2007-11-26","2007-11-21"]
["XE_6004","Prep Bid Pkg Lenses & Mirrors - Laser Supplies","2007-11-26","2007-12-07"]
["XE_6005","Bid Process Lenses & Mirrors - Laser Supplies","2007-12-10","2008-01-23"]
["XE_6006","AWARD: Contract Lenses & Mirrors-Laser Supplies","2008-01-24","2008-01-24"]
["XE_6007","Vendor Fab/Ship Lenses & Mirrors -Laser Supplies","2008-01-25","2008-04-18"]
["XE_6008","RECV:  Lenses & Mirrors - Laser Supplies","2008-04-21","2008-04-18"]
["XE_6009","REQD: Near Hall Beneficial Occupancy - LSupp","2008-05-05","2008-05-02"]
["XE_6010","LASER SUPPLIES / OPTICS TRANSPORT","2007-01-04","2008-05-02"]
["XE_6011","Install Pipe, Laser Table to X-Ray Hutch-LSupp","2008-05-05","2008-06-02"]
["XE_6015","Test - Optic Transport","2008-06-03","2008-06-09"]
["XE_6016","COMP: Laser Supplies/Optic Transport","2008-06-10","2008-06-09"]
["XE_6020","Specification - Laser Timing","2007-01-02","2007-06-21"]
["XE_6021","Design - Laser Timing","2007-08-01","2007-11-21"]
["XE_6022","Design Review - Laser Timing","2007-11-26","2007-12-07"]
["XE_6023","COMP: Design Laser Timing","2007-12-10","2007-12-07"]
["XE_6024","Prep Bid Pkg Frequency Analyzer - Laser Timing","2007-12-10","2007-12-11"]
["XE_6025","Bid Process Frequency Analyzer - Laser Timing","2007-12-12","2008-01-25"]
["XE_6026","AWARD: Contract Frequency Analyzer-Laser Timing","2008-01-28","2008-01-28"]
["XE_6027","Vendor Fab/Ship Frequency Analyzer - Laser Timin","2008-01-29","2008-04-22"]
["XE_6028","RECV: Frequency Analyzer - Laser Timing","2008-04-23","2008-04-22"]
["XE_6029","REQD: Near Hall Beneficial Occup - Laser Timing","2008-04-30","2008-04-29"]
["XE_6030","REQD: Diagnostics for NHall Laser Demo - Timing","2008-04-30","2008-04-29"]
["XE_6031","Optic Table Ready NHall - Laser Timing","2008-04-23","2008-04-29"]
["XE_6032","Install Diagnostics Near Hall - Laser Timing","2008-04-30","2008-05-28"]
["XE_6036","COMP: Near Hall Laser Timing","2008-07-25","2008-07-24"]
["XE_6038","Specification - Laser Amplifiers","2007-01-04","2007-03-02"]
["XE_6039","Design - Laser Amplifiers","2007-06-01","2007-09-24"]
["XE_6040","Design Review  - Laser Amplifiers","2007-09-25","2007-10-08"]
["XE_6041","COMP: Design - Laser Amplifiers","2007-10-09","2007-10-08"]
["XE_6042","Prep Bid Pkg - Laser Amplifiers","2007-10-09","2007-10-22"]
["XE_6043","Bid Process - Laser Amplifiers","2007-10-23","2007-11-19"]
["XE_6044","AWARD: Contract - Laser Amplifiers","2007-11-20","2007-11-20"]
["XE_6045","Vendor Fab/Ship  - Laser Amplifiers","2007-11-21","2008-04-30"]
["XE_6046","RECV:  Laser Amplifiers","2008-05-01","2008-04-30"]
["XE_6047",null,"2005-05-02","2005-05-02"]
["XE_6048","REQD: Diagnostics for Laser Demo","2008-05-08","2008-05-07"]
["XE_6049","Optic Table Ready - Laser Amplifiers","2008-05-01","2008-05-07"]
["XE_6050","First Install Near Hall - Laser Amplifiers","2008-05-08","2008-05-21"]
["XE_6051","Vendor Setup/Demo NHall - Laser Amplifiers","2008-05-22","2008-06-19"]
["XE_6052","Final Check Near Hall - Laser Amplifiers","2008-06-20","2008-06-26"]
["XE_6053","Test Near Hall - Laser Amplifiers","2008-06-27","2008-07-03"]
["XE_6054","COMP: Near Hall Laser Amplifiers","2008-07-07","2008-07-03"]
["XE_6055","Prep Bid Pkg Shielding/Contain - Laser Supplies","2007-11-26","2008-01-08"]
["XE_6056","Bid Process Shielding/Contain - Laser Supplies","2008-01-09","2008-02-06"]
["XE_6057","AWARD: Contract Shielding/Contai - Laser Suppli","2008-02-07","2008-02-07"]
["XE_6058","Vendor Fab/Ship Shielding/Conta -Laser Supplies","2008-02-08","2008-05-02"]
["XE_6059","RECV:  Shielding/Contain - Laser Supplies","2008-05-05","2008-05-02"]
["XE_6060","Prep Bid Pkg Optic Tables (4) - Laser Supplies","2007-11-26","2007-12-07"]
["XE_6061","Bid Process Optic Tables (4) - Laser Supplies","2007-12-10","2008-01-23"]
["XE_6062","AWARD: Contract Optic Tables (4) - Laser Suppli","2008-01-24","2008-01-24"]
["XE_6063","Vendor Fab/Ship Optic Tables (4) -Laser Supplies","2008-01-25","2008-04-18"]
["XE_6064","RECV:  Optic Tables (4) - Laser Supplies","2008-04-21","2008-04-18"]
["XE_6065","Prep Bid Pkg Cabinets - Laser Supplies","2007-11-26","2007-12-07"]
["XE_6066","Bid Process Cabinets - Laser Supplies","2007-12-10","2008-01-23"]
["XE_6067","AWARD: Contract Cabinets - Laser Supplies","2008-01-24","2008-01-24"]
["XE_6068","Vendor Fab/Ship Cabinets -Laser Supplies","2008-01-25","2008-03-21"]
["XE_6069","RECV:  Cabinets - Laser Supplies","2008-03-24","2008-03-21"]
["XE_6070","LASER TIMING","2006-10-02","2008-09-30"]
["XE_6072","Test Timing System Near Hall - Laser Timing","2008-05-29","2008-07-24"]
["XE_6077","AVAIL: Near Hall Laser Amplifiers","2008-05-08","2008-05-07"]
["XE_6078","AP LASER AMPLIFIERS","2006-04-03","2008-05-13"]
["XE_6079","AVAIL: Laser Supplies","2008-05-05","2008-05-02"]
["XE_6080","AVAIL: Near Hall Laser Timing","2008-04-30","2008-04-29"]
["XE_61","Commission - Beam Imaging","2007-07-19","2008-01-24"]
["XE_62","Commission - 2-D X-Ray Detector","2008-10-27","2008-11-04"]
["XE_63","Commission - Beam Intensity","2008-04-29","2008-10-16"]
["XE_64","Commission - Streak Camera","2008-01-03","2008-06-23"]
["XE_700","Test Near Hall - Oscillator Laser/Pum","2008-10-16","2008-10-22"]
["XE_701","Specification - Oscillator Laser/Pump","2007-01-04","2007-03-02"]
["XE_702","Design - Oscillator Laser/Pump","2007-08-01","2007-11-21"]
["XE_703","Design Review - Oscillator Laser/Pump","2007-11-26","2007-12-07"]
["XE_704","COMP: Design - Oscillator Laser/Pump","2007-12-10","2007-12-07"]
["XE_7040","Integrate with Controls","2008-04-01","2008-04-28"]
["XE_7041","COMP: Beam Intensity","2008-04-29","2008-04-28"]
["XE_7045","COMP: Design - Streak Camera","2007-04-09","2007-04-06"]
["XE_7046","Prep Bid Pkg - Streak Camera","2007-04-09","2007-04-13"]
["XE_7047","Bid Process - Streak Camera","2007-04-16","2007-05-11"]
["XE_7048","AWARD: Contract - Streak Camera","2007-05-14","2007-05-14"]
["XE_7049","Inspect/Vendor Setup - Streak Camera","2007-10-12","2007-10-18"]
["XE_705","Prep Bid Pkg  - Oscillator Laser/Pump","2007-12-10","2008-01-08"]
["XE_7050","RECV:  Streak Camera","2007-10-05","2007-10-04"]
["XE_7051","Assemble at SLAC - Streak Camera","2007-10-05","2007-10-11"]
["XE_7052","REQD: Near  Hall Beneficial Occupancy","2007-10-19","2007-10-18"]
["XE_7053","Install Near Hall - Streak Camera","2007-10-19","2007-11-15"]
["XE_7054","COMP: Streak Camera","2008-01-03","2008-01-02"]
["XE_7056","BEAM IMAGING","2005-05-02","2009-03-31"]
["XE_706","Bid Process - Oscillator Laser/Pump","2008-01-09","2008-02-06"]
["XE_7060","Send Funding - 2-D X-Ray Detector","2005-05-02","2005-05-13"]
["XE_7061","AWARD: 2005 Contract - 2-D X-Ray Detector","2005-06-01","2005-06-01"]
["XE_70611","AWARD: FY-05 Contract - 2-D X-Ray Detector","2005-06-01","2005-06-01"]
["XE_7063","RECV:  2-D X-Ray Detector","2008-08-01","2008-07-31"]
["XE_7064","Install at SLAC - 2-D X-Ray Detector","2008-08-29","2008-09-26"]
["XE_7067","COMP:  2-D X-Ray Detector","2008-10-27","2008-10-24"]
["XE_7069","BEAM INTENSITY","2005-05-02","2009-03-31"]
["XE_707","AWARD: Contract - Oscillator Laser/Pu","2008-02-07","2008-02-07"]
["XE_7073","Integrate with Controls - Streak Camera","2007-11-16","2008-01-02"]
["XE_7076","Integrate with Controls - 2-D X-Ray Detector","2008-09-29","2008-10-24"]
["XE_70775","2006 Vendor Contract - Prototype-2-D X-Ray Det","2006-01-10","2006-12-15"]
["XE_708","Vendor Fab/Ship Near Hall - Oscillator Laser/Pum","2008-02-08","2008-07-29"]
["XE_7081","2006 Design Review - 2-D X-Ray Detector","2006-10-26","2006-10-30"]
["XE_7083","AVAIL: 2-D X-Ray Detector","2008-08-01","2008-07-31"]
["XE_70832","2007 Design Review - 2-D X-Ray Detector","2007-09-18","2007-09-24"]
["XE_7085","2-D X-RAY DETECTOR","2005-05-02","2008-11-04"]
["XE_709","RECV:  Oscillator Laser/Pump","2008-07-30","2008-07-29"]
["XE_710","Install Laser Table Near Hall - Oscillator Laser","2008-07-30","2008-08-26"]
["XE_7102","Contract - Demo at SLAC - 2-D X-Ray Detector","2008-08-01","2008-08-28"]
["XE_7106","Vendor Contract 100% Complete - Streak Camera","2007-05-15","2007-09-06"]
["XE_7107","Produce Report,Contract Complete - Streak Camera","2007-09-07","2007-10-04"]
["XE_7108","Vendor Fab/Ship - AP Samples","2008-02-04","2008-02-08"]
["XE_7109","Design Study LBL - Streak Camera - FY-06","2006-04-03","2006-09-29"]
["XE_7110","Final Design Review - Streak Camera","2007-04-02","2007-04-06"]
["XE_7112","2008 Vendor Contract - 2-D X-Ray Detector","2007-09-25","2008-07-24"]
["XE_71122","2008 Final Report - 2-D X-Ray Detector","2008-07-25","2008-07-31"]
["XE_7113","AWARD 2008 Contract - 2-D X-Ray Detector","2007-09-25","2007-09-25"]
["XE_712","Final Check Near Hall - Oscillator Laser/Pump","2008-10-09","2008-10-15"]
["XE_713","COMP: Near Hall Oscillator Laser/Pump","2008-10-23","2008-10-22"]
["XE_7132","STREAK CAMERA","2006-02-02","2008-11-13"]
["XE_714","Procure  Laser Tables","2007-08-01","2008-02-06"]
["XE_7142","AVAIL: Streak Camera","2007-10-19","2007-10-18"]
["XE_7144","Commission Near Hall - Oscillator Laser/Pump","2008-10-23","2008-11-19"]
["XE_7153","Design Study LBL - Streak Camera - FY-07","2006-10-02","2007-03-30"]
["XE_720","REQD: Diagnostics for Laser Demo","2008-07-30","2008-07-29"]
["XE_7200","Prep Bid Pkg - AP Samples","2007-12-11","2008-01-02"]
["XE_721","AP OSCILLATOR LASER/PUMP","2005-05-02","2008-12-05"]
["XE_72222","2006 Contract Report - 2-D X-Ray Detector","2006-10-24","2006-10-25"]
["XE_730","Vendor Setup/Demo NHall - Oscillator Laser/Pump","2008-09-11","2008-10-08"]
["XE_7300","Bid Process - AP Samples","2008-01-03","2008-01-31"]
["XE_7301","Specification Far Hall - Laser PPS","2006-07-19","2006-08-15"]
["XE_7302","Prep Bid Pkg - AP Diagnostics","2007-12-11","2008-01-02"]
["XE_7303","Bid Process - AP Diagnostics","2008-01-03","2008-01-31"]
["XE_7304","AWARD: Contract - AP Diagnostics","2008-02-01","2008-02-01"]
["XE_7305","Vendor Fab/Ship - AP Diagnostics","2008-02-04","2008-02-04"]
["XE_7306","RECV:  AP Diagnostics","2008-02-05","2008-02-04"]
["XE_731","AVAIL: Near Hall Oscillator Laser/Pump","2008-07-30","2008-07-29"]
["XE_7311","Design Far Hall - Laser PPS","2006-08-16","2006-10-11"]
["XE_7321","COMP: Far Hall Design - Laser PPS","2006-12-11","2006-12-08"]
["XE_7331","Safety Review Far Hall - Laser PPS","2006-10-12","2006-12-08"]
["XE_7341","Prep Bid Pkg Far Hall Alarms/Signs - Laser PPS","2006-12-11","2007-01-08"]
["XE_7350","Define AP Samples","2006-01-18","2006-06-08"]
["XE_7351","Prep Bid Pkg FHall Contain/Interlck - Laser PPS","2006-12-11","2007-01-08"]
["XE_73511","Design AP preparation and handling - Samples","2006-06-09","2006-11-29"]
["XE_73512","Procurements - AP Samples","2007-12-11","2008-01-09"]
["XE_73513","Assembly - AP Samples","2008-02-11","2008-02-11"]
["XE_73514","Test AP Sample","2008-07-25","2008-07-25"]
["XE_73515","Define AP Data Analysis","2006-01-18","2007-01-26"]
["XE_73516","Design AP Data Analysis","2007-01-29","2007-07-18"]
["XE_73517","Procurements - AP Data Analysis","2007-07-19","2008-01-24"]
["XE_73518","Assembly - AP Data Analysis","2007-10-22","2007-11-16"]
["XE_73519","Test - AP Data Analysis","2008-07-25","2008-08-21"]
["XE_73520","Define AP Optics","2006-06-09","2006-10-30"]
["XE_73521","Design AP Optics","2006-10-31","2007-05-07"]
["XE_73522","Procurements - AP  Optics","2007-05-08","2007-10-25"]
["XE_73523","Assembly - AP Optics","2007-10-26","2007-11-26"]
["XE_73524","Test - AP Optics","2008-07-25","2008-08-21"]
["XE_73528","AP DATA ANALYSIS","2006-01-18","2008-08-21"]
["XE_73531","AP SAMPLES","2006-01-18","2008-10-15"]
["XE_73533","AP OPTICS","2006-06-09","2008-08-21"]
["XE_7361","Prepare Bid Pkg Far Hall Detectors - Laser PPS","2006-12-11","2007-01-08"]
["XE_7371","Bid Process Far Hall Alarms/Signs - Laser PPS","2007-01-09","2007-03-07"]
["XE_7381","Bid Process Far Hall Contain/Interlck - Laser PP","2007-01-09","2007-03-07"]
["XE_7391","Bid Process Far Hall Detectors - Laser PPS","2007-01-09","2007-03-07"]
["XE_740","First Install Near Hall - Oscillator Laser/Pump","2008-08-27","2008-09-10"]
["XE_7400","AWARD: Contract - AP Samples","2008-02-01","2008-02-01"]
["XE_7401","AWARD: Contract Far Hall Alarms/Signs -Laser PP","2007-03-08","2007-03-08"]
["XE_74100","Define AP Diagnostics","2006-06-09","2007-06-19"]
["XE_74101","Design AP Diagnostics","2007-06-20","2007-12-10"]
["XE_74102","Procurements - AP Diagnostics","2007-12-11","2008-01-02"]
["XE_74103","Assembly - AP Diagnostics","2008-02-05","2008-02-05"]
["XE_74104","Test AP Diagnostics","2008-07-25","2008-07-25"]
["XE_7411","AWARD: Contract FHall Contain/Interlck - Laser","2007-03-08","2007-03-08"]
["XE_74113","AP DETECTORS & DIAGNOSTICS","2006-06-09","2008-07-25"]
["XE_7421","AWARD: Contract Far Hall Detectors - Laser PPS","2007-03-08","2007-03-08"]
["XE_7431","Vendor Fab/Ship Far Hall Alarm/Sign - Laser PPS","2007-03-09","2007-05-03"]
["XE_7441","Vendor Ship Far Hall Contain/Intrlck-Laser PPS","2007-03-09","2007-05-03"]
["XE_7451","Vendor Fab/Ship Far Hall Detectors - Laser PPS","2007-03-09","2007-05-03"]
["XE_7461","RECV: Far Hall Alarms/Signs - Laser PPS","2007-05-04","2007-05-03"]
["XE_7471","RECV: Far Hall Containment/Interlock -Laser PPS","2007-05-04","2007-05-03"]
["XE_7481","RECV: Far Hall Detectors - Laser PPS","2007-05-04","2007-05-03"]
["XE_7491","REQD: Far Hall Beneficial Occup - Laser PPS","2007-08-07","2007-08-06"]
["XE_750","Give Specs for Near Hall Laser Room to CF","2007-03-05","2007-03-02"]
["XE_7500","RECV:  AP Samples","2008-02-11","2008-02-08"]
["XE_7501","Install Far Hall Alarms/Signs - Laser PPS","2007-08-07","2007-09-04"]
["XE_7511","Install Far Hall Contain/Interlck - Laser PPS","2007-08-07","2007-09-04"]
["XE_7521","Install Far Hall Detectors - Laser PPS","2007-08-07","2007-09-04"]
["XE_7531","Test Far Hall - Laser PPS","2007-09-05","2007-09-11"]
["XE_7555","Specification - Streak Camera","2006-02-02","2006-03-30"]
["XE_7556","Detector Engineering","2006-02-02","2008-11-13"]
["XE_7591","AVAIL: Far Hall Laser PPS","2007-05-04","2007-05-03"]
["XE_760","FAR HALL LASER PPS","2006-07-19","2007-08-06"]
["XE_80","Design FEE - PPS","2006-03-27","2006-05-19"]
["XE_800","Specification Gauges - Vacuum","2007-08-23","2007-10-18"]
["XE_801","Design Gauges - Vacuum","2007-10-19","2008-01-02"]
["XE_802","Design Review Gauges - Vacuum","2008-01-03","2008-01-09"]
["XE_803","COMP: Design Gauges - Vacuum","2008-01-10","2008-01-09"]
["XE_804","Prep Bid Pkg Gauges - Vacuum","2008-01-10","2008-01-16"]
["XE_805","Bid Process Gauges - Vacuum","2008-01-17","2008-02-14"]
["XE_806","Test Gauges - Vacuum System","2008-04-29","2008-07-23"]
["XE_807","AWARD: Contract Gauges - Vacuum","2008-02-15","2008-02-15"]
["XE_808","Vendor Fab/Ship Gauges - Vacuum","2008-02-19","2008-04-14"]
["XE_809","RECV:  Gauges - Vacuum","2008-04-15","2008-04-14"]
["XE_81","Specification FEE - X-Ray PPS","2006-02-27","2006-03-24"]
["XE_810","VACUUM GAUGES","2007-08-23","2008-04-21"]
["XE_816","REQD: Near Hall Beneficial Occupancy","2008-04-22","2008-04-21"]
["XE_817","Install Near Hall Gauges - Vacuum","2008-04-22","2008-04-28"]
["XE_818","COMP: Near Hall Gauges - Vacuum","2008-04-29","2008-04-28"]
["XE_819","Assemble Far Hall  Gauges - Vacuum","2008-04-15","2008-04-21"]
["XE_824","REQD: Far Hall Beneficial Occupancy","2008-04-22","2008-04-21"]
["XE_825","Install Far Hall Gauges - Vacuum","2008-04-22","2008-04-28"]
["XE_826","COMP: Far Hall Gauges - Vacuum","2008-07-24","2008-07-23"]
["XE_827","COMP: Gauges - Vacuum System","2008-07-24","2008-07-23"]
["XE_828","Commission Gauges - Vacuum","2008-07-24","2008-08-20"]
["XE_829","Assemble Near Hall Gauges - Vacuum","2008-04-15","2008-04-21"]
["XE_834","AVAIL: Far Hall Gauges - Vacuum","2008-04-22","2008-04-21"]
["XE_836","AVAIL: Near Hall Gauges - Vacuum","2008-04-22","2008-04-21"]
["XE_850","Specification Far Hall - User Safeguards","2006-07-19","2006-08-15"]
["XE_851","Design Far Hall - User Safeguards","2006-08-16","2006-10-11"]
["XE_852","COMP: Far Hall Design - User Safeguards","2006-12-11","2006-12-08"]
["XE_853","Safety Review Far Hall - User Safeguards","2006-10-12","2006-12-08"]
["XE_854","Prep Bid Pkg Far Hall Alarms/Signs - User Safegu","2006-12-11","2007-01-08"]
["XE_855","Prep Bid Pkg Far Hall Interlock - User Safeguard","2006-12-11","2007-01-08"]
["XE_856","Prepare Far Hall Bid Pkg Detectors - User Safegu","2006-12-11","2007-01-08"]
["XE_857","Bid Process Far Hall Alarms/Signs - User Safegua","2007-01-09","2007-03-07"]
["XE_858","Bid Process Far Hall Interlock - User Safeguards","2007-01-09","2007-03-07"]
["XE_859","Bid Process Far Hall Detectors - User Safeguards","2007-01-09","2007-03-07"]
["XE_860","AWARD: Contract Far Hall Alarms/Signs -User Saf","2007-03-08","2007-03-08"]
["XE_861","AWARD: Contract Far Hall Interlck - User Safegu","2007-03-08","2007-03-08"]
["XE_862","AWARD: Contract Far Hall Detectors - User Safeg","2007-03-08","2007-03-08"]
["XE_863","Vendor Fab/Ship Far Hall Alarm/Sign - User Safeg","2007-03-09","2007-05-03"]
["XE_864","Vendor Ship Far Hall Contain/Intrlck-User Safegu","2007-03-09","2007-05-03"]
["XE_865","Vendor Fab/Ship Far Hall Detectors - User Safegu","2007-03-09","2007-05-03"]
["XE_866","RECV: Far Hall Alarms/Signs - User Safeguards","2007-05-04","2007-05-03"]
["XE_867","RECV: Far Hall Containment/Interlock -User Safeg","2007-05-04","2007-05-03"]
["XE_868","RECV: Far Hall Detectors - User Safeguards","2007-05-04","2007-05-03"]
["XE_869","REQD: Far Hall Beneficial Occup - User Safeguard","2007-08-07","2007-08-06"]
["XE_870","Install Far Hall Alarms/Signs - User Safeguards","2007-08-07","2007-09-04"]
["XE_871","Install Far Hall Contain/Interlck - User Safegua","2007-08-07","2007-09-04"]
["XE_872","Install Far Hall Detectors - User Safeguards","2007-08-07","2007-09-04"]
["XE_873","Test Far Hall - User Safeguards","2007-09-05","2007-09-11"]
["XE_874","COMP: Far Hall User Safeguards","2007-09-12","2007-09-11"]
["XE_879","AVAIL: Far Hall User Safeguards","2007-05-04","2007-05-03"]
["XE_880","FAR HALL USER SAFEGUARDS","2006-07-19","2007-08-06"]
["XE_884","Commission Far Hall - User Safeguards","2007-09-12","2007-10-09"]
["XE_8902","Mechanical Support - Vacuum","2007-10-01","2008-09-30"]
["XE_90","Safety Review FEE - PPS","2006-05-22","2006-07-18"]
["XE_900","Specification Near Hall - User Safeguards","2006-07-19","2006-08-15"]
["XE_901","Design Near Hall - User Safeguards","2006-08-16","2006-10-11"]
["XE_902","COMP: Near Hall Design - User Safeguards","2006-12-11","2006-12-08"]
["XE_903","Safety Review Near Hall - User Safeguards","2006-10-12","2006-12-08"]
["XE_904","Prep Bid Pkg Near Hall Alarms/Signs - User Safeg","2006-12-11","2007-01-08"]
["XE_905","Prep Bid Pkg NHall Interlock - User Safeguards","2006-12-11","2007-01-08"]
["XE_906","Prepare Near Hall Bid Pkg Detectors - User Safeg","2006-12-11","2007-01-08"]
["XE_907","Bid Process Near Hall Alarms/Signs - User Safegu","2007-01-09","2007-03-07"]
["XE_908","Bid Process NHall Interlock - User Safeguards","2007-01-09","2007-03-07"]
["XE_909","Bid Process Near Hall Detectors - User Safeguard","2007-01-09","2007-03-07"]
["XE_91","COMP: FEE Design - X-Ray PPS","2006-07-19","2006-07-18"]
["XE_910","AWARD: Contract Near Hall Alarms/Signs -User Sa","2007-03-08","2007-03-08"]
["XE_911","AWARD: Contract NHall Interlock - User Safeguar","2007-03-08","2007-03-08"]
["XE_912","AWARD: Contract Near Hall Detectors - User Safe","2007-03-08","2007-03-08"]
["XE_913","Vendor Fab/Ship Near Hall Alarm/Sign - User Safe","2007-03-09","2007-05-03"]
["XE_914","Vendor Ship Near Hall Intrlock-User Safeguards","2007-03-09","2007-05-03"]
["XE_915","Vendor Fab/Ship Near Hall Detectors - User Safeg","2007-03-09","2007-05-03"]
["XE_916","RECV: Near Hall Alarms/Signs - User Safeguards","2007-05-04","2007-05-03"]
["XE_917","RECV: Near Hall Interlock -User Safeguards","2007-05-04","2007-05-03"]
["XE_918","RECV: Near Hall Detectors - User Safeguards","2007-05-04","2007-05-03"]
["XE_919","REQD: Near Hall Beneficial Occup - User Safeguar","2007-05-22","2007-05-21"]
["XE_92","Prepare Bid Pkg FEE Detectors - PPS","2006-10-02","2006-10-13"]
["XE_920","Install Near Hall Alarms/Signs - User Safeguards","2007-05-22","2007-06-19"]
["XE_921","Install Near Hall Contain/Interlck - User Safegu","2007-05-22","2007-06-19"]
["XE_922","Install Near Hall Detectors - User Safeguards","2007-05-22","2007-06-19"]
["XE_923","Test Near Hall - User Safeguards","2007-06-20","2007-06-26"]
["XE_924","COMP: Near Hall User Safeguards","2007-06-27","2007-06-26"]
["XE_929","AVAIL: Near Hall User Safeguard","2007-05-04","2007-05-03"]
["XE_93","Bid Process FEE Detectors - PPS","2006-10-16","2006-12-12"]
["XE_930","NEAR HALL USER SAFEGUARDS","2006-07-19","2007-05-21"]
["XE_934","Commission Near Hall - User Safeguards","2007-06-27","2007-07-25"]
["XE_94","AWARD: Contract FEE Detectors - PPS","2006-12-13","2006-12-13"]
["XE_95","Vendor Fab/Ship FEE Detectors - PPS","2006-12-14","2007-02-26"]
["XE_96","RECV: FEE Detectors - PPS","2007-02-27","2007-02-26"]
["XE_98","COMP: FEE X-RAY PPS","2008-05-06","2008-05-05"]
["XE_99","Install FEE Detectors - PPS","2008-03-04","2008-04-28"]
["XE_990","Engineering - Laser Diagnostics","2006-06-05","2008-09-30"]
["XE_9901","Mechanical Engineering - Vacuum","2006-06-05","2007-09-28"]
["XE_LOE","XE LOE Complete","2008-10-01","2008-09-30"]
["XE_M07","Complete 2-D X-Ray Detector Statement of Work","2005-05-02","2005-04-29"]
["XE_M08","Award of Initial Funding for 2-D X-Ray Detector","2005-05-16","2005-05-13"]
["XE_M09","Hire Detector Physicist","2006-02-02","2006-02-01"]
["XE_M12","Hire Atomic Physicist","2006-01-18","2006-01-17"]
["XE_M13","Hire Controls Engineer","2006-02-02","2006-02-01"]
["XE_M14","COMP: 2006 Design Review - 2-D X-Ray Detector","2006-10-31","2006-10-30"]
["XE_M15","Hire Laser Scientist","2006-02-27","2006-02-24"]
["XE_M16","Hire Mechanical/Vacuum Engineer","2006-02-27","2006-02-24"]
["XE_M17","Start Programming Beamline Controls","2007-06-07","2007-06-06"]
["XE_M18","COMP: Network Design Review","2007-02-13","2007-02-12"]
["XE_M19","Laser System Final Design Review","2007-12-10","2007-12-07"]
["XE_M20","Atomic Physics Final Design Review","2007-12-11","2007-12-10"]
["XE_M21","Final Design Review Experimental Chamber","2007-08-23","2007-08-22"]
["XE_M22","Award Experimental Chambers-Near Hall & Far Hall","2007-10-01","2007-09-28"]
["XE_M222","2007 Design Review - 2-D X-Ray Detector","2007-09-25","2007-09-24"]
["XE_M23","Award of AP Oscillator Laser/Pump","2008-02-08","2008-02-07"]
["XE_M24","Complete Laser PPS Design Review","2006-12-11","2006-12-08"]
["XE_M25","X-Ray PPS Final Design Review","2006-07-19","2006-07-18"]
["XE_M27","Start Installation in Near Hall","2007-05-22","2007-05-21"]
["XE_M28","Start Installation in Far Hall","2007-08-07","2007-08-06"]
["XE_M29","Complete Near Hall Installation","2008-10-23","2008-10-22"]
["XE_M30","COMP:  Final Design Review Beamline Control","2007-06-07","2007-06-06"]
["XE_M31","Laser Operating in Near Hall","2008-10-23","2008-10-22"]
["XE_M33","Complete Beamline Control","2008-04-14","2008-04-11"]
["XE_M34","Certify Near Hall X-Ray PPS and MPS","2007-06-27","2007-06-26"]
["XE_M35","Certify X-Ray PPS and MPS in Far Hall","2007-09-12","2007-09-11"]
["XE_M36","Complete Network & Cable - Ready to Commission","2008-07-16","2008-07-15"]
["XE_M37","Complete Mechanical & Vacuum - Ready to Commiss","2008-07-24","2008-07-23"]
["XE_M38","Synchronize NH Laser with LINAC Master Oscillato","2008-07-25","2008-07-24"]
["XE_M40","Complete Accept Tests for 2-D X-Ray Detector","2008-08-29","2008-08-28"]
["XE_M41","First Atomic Physics Experiment","2008-07-25","2008-07-24"]
["XE_M55","COMP:  Specification - Streak Camera","2006-03-31","2006-03-30"]
["XE_MS2005","FY-05 Resource Available","2005-11-01","2005-10-31"]
["XTMS3_066","Near Experimental Hall Commissioning","2007-10-04","2007-10-31"]
["XTMS3_080","Front End Enclosure Commissioning","2007-12-13","2008-02-26"]
["XTOPS_0000","XTOD Pre-Operations","2008-04-04","2009-03-31"]
["XT_0112","COMP: Controls System Tests Complete","2008-01-30","2008-01-29"]
["XT_0115","Assemble FEE - EPICS","2006-11-14","2007-01-26"]
["XT_0116","Programming FEE - EPICS","2007-01-29","2007-03-26"]
["XT_0117","Test FEE - Controls","2007-08-09","2007-09-06"]
["XT_0119","AWARD: EPICS Tools","2006-10-16","2006-10-16"]
["XT_0121","Install FEE - Controls","2007-05-15","2007-06-12"]
["XT_0122","Integrate FEE -  Controls","2007-06-13","2007-08-08"]
["XT_0124","REQD: FEE Beneficial Occup - EPICS","2007-05-15","2007-05-14"]
["XT_0125","REQD: Near Hall Beneficial Occup - EPICS","2007-06-20","2007-06-19"]
["XT_0126","Assemble Near Hall - EPICS","2006-11-14","2007-01-26"]
["XT_0127","Programming Near Hall - EPICS","2007-01-29","2007-03-26"]
["XT_0128","Install Near Hall - Controls","2007-06-20","2007-08-15"]
["XT_0129","Integrate Near Hall - Controls","2007-08-16","2007-10-11"]
["XT_0130","Test Near Hall - Controls","2007-10-12","2007-11-08"]
["XT_0131","REQD: Far Hall Beneficial Occup - EPICS","2007-08-21","2007-08-20"]
["XT_0132","Assemble Far Hall - EPICS","2006-11-14","2007-01-26"]
["XT_0133","Programming Far Hall - EPICS","2007-01-29","2007-03-26"]
["XT_0134","Install Far Hall - Controls","2007-08-21","2007-10-16"]
["XT_0135","Integrate Far Hall - Controls","2007-10-17","2007-12-13"]
["XT_0136","Test Far Hall - Controls","2007-12-14","2008-01-29"]
["XT_03","AWARD: Contract Optics - Direct Imager","2007-03-08","2007-03-08"]
["XT_04","AWARD: Contract Mechanism - Direct Imager","2007-03-08","2007-03-08"]
["XT_0461","Install Ion Gauges - NH Mech/Vac - H1","2007-08-23","2007-08-29"]
["XT_0462","Install Spools - NH Mech/Vac - H1","2007-08-23","2007-08-29"]
["XT_05","AWARD: CCD Sensors - Direct Imager","2007-03-08","2007-03-08"]
["XT_050","FEE Mgt - FEE Mech/Vac","2005-10-03","2005-11-29"]
["XT_0500","Beam Tube Spt Primary Design - FEE Mech/Vac","2006-05-12","2006-05-30"]
["XT_0501","Beam Tube Spt  Detail Design - FEE Mech/Vac","2006-05-31","2006-06-08"]
["XT_0502","Beam Tube Spt  Design Check - FEE Mech/Vac","2006-06-09","2006-06-13"]
["XT_0503","Beam Tube Spt  Design Back Check - FEE Mech/Vac","2006-06-14","2006-06-16"]
["XT_0550","Prepare Install Plan - FEE Mech/Vac","2006-10-02","2007-02-08"]
["XT_05505","Material & Supplies - Near Hall","2007-08-16","2007-09-13"]
["XT_0552","Pkg and Ship to SLAC - FEE Mech/Vac","2007-08-03","2007-08-16"]
["XT_0553","ICD - XTOD-Linac","2005-10-04","2005-10-03"]
["XT_0554","ICD - XTOD-XES","2005-10-04","2005-10-03"]
["XT_0555","ICD - XTOD-CF","2005-11-01","2005-10-31"]
["XT_0556","Prelim Analysis of Flex Support-Tunnel Mech/Vac","2005-12-12","2005-12-16"]
["XT_0557","Detail Analysis of Flex Support- Tunnel Mech/Vac","2006-01-04","2006-01-25"]
["XT_056","Mgt - Ion Chamber","2006-01-03","2006-12-15"]
["XT_0560","Write IWS - Tunnel Mech/Vac","2006-01-04","2006-03-02"]
["XT_06","Order & Receive Scintillator - Direct Imager","2007-03-09","2007-05-03"]
["XT_060","Townsend Phase I - Total Energy","2006-01-23","2006-05-15"]
["XT_061","Townsend Phase II - Total Energy","2006-05-16","2006-08-09"]
["XT_07","AWARD: Scintillator  - Direct Imager","2007-03-08","2007-03-08"]
["XT_070","Configuration Drawing Mgt","2005-12-02","2007-09-28"]
["XT_08","Order & Receive Optics - Direct Imager","2007-03-09","2007-05-03"]
["XT_082","COMP: X-Ray Transport","2009-04-01","2009-03-31"]
["XT_09","REQD:  FEE Beneficial Occup - Direct Imager","2007-05-15","2007-05-14"]
["XT_0900","Physics Specification I - FEL Mirrors","2005-10-03","2006-01-11"]
["XT_0901","Conceptual Design Prep - FEL Mirrors","2006-05-30","2006-06-12"]
["XT_0902","Write ESD - FEL Mirrors","2006-05-30","2006-06-12"]
["XT_0903","Conceptual Design - FEL Mirrors","2006-03-27","2006-05-26"]
["XT_0904","Conceptual Design  Review - FEL Mirrors","2006-06-13","2006-06-12"]
["XT_0905","Revise IWS- FEL Mirrors","2006-06-13","2006-06-26"]
["XT_0910","Controls Defined - FEL Mirrors","2006-06-13","2006-06-16"]
["XT_0912","Engineering Analysis - FEL Mirrors","2006-06-13","2006-08-08"]
["XT_0913","Vacuum Analysis - FEL Mirrors","2006-05-30","2006-06-26"]
["XT_092","REQD: FEE BO","2007-05-14","2007-05-14"]
["XT_0923","Preliminary Design Prep - FEL Mirrors","2006-08-09","2006-08-22"]
["XT_0924","Controls Redefined - FEL Mirrors","2006-08-09","2006-08-24"]
["XT_0925","Preliminary Design Review - FEL Mirrors","2006-08-23","2006-08-22"]
["XT_0926","Write Safety/Ref Note - FEL Mirrors","2006-08-25","2006-09-22"]
["XT_0927","Safety/Ref Note 1st Review - FEL Mirrors","2006-09-25","2006-10-13"]
["XT_0928","Safety/Ref Note 2nd Review - FEL Mirrors","2006-10-16","2006-10-24"]
["XT_0929","Safety/Ref Note Division Review - FEL Mirrors","2006-10-25","2006-11-02"]
["XT_0930","Final Design Prep - FEL Mirrors","2006-11-03","2006-11-16"]
["XT_0931","Prep Procure Docs Optics - FEL Mirrors","2006-11-17","2007-01-02"]
["XT_0932","Prep Procure Docs Vacuum Comp - FEL Mirrors","2006-11-17","2007-01-02"]
["XT_0933","Prep Procure Docs Electronics - FEL Mirrors","2006-11-17","2007-01-02"]
["XT_0934","Prep Procure Docs Mechanisms - FEL Mirrors","2006-11-17","2007-01-02"]
["XT_0935","Final Design Review - FEL Mirrors","2006-11-17","2006-11-16"]
["XT_0936","Select Vendor Optics - FEL Mirrors","2007-01-03","2007-01-31"]
["XT_0937","Select Vendor Vacuum Components - FEL Mirrors","2007-01-03","2007-01-31"]
["XT_0938","Select Vendor Electronics - FEL Mirrors","2007-01-03","2007-01-31"]
["XT_0939","Select Vendor Mechanisms - FEL Mirrors","2007-01-03","2007-01-31"]
["XT_0940","Procure Review Mechanisms - FEL Mirrors","2007-02-01","2007-02-07"]
["XT_0941","Procure Review Optics - FEL Mirrors","2007-02-01","2007-02-07"]
["XT_0942","Procure Review Vacuum Components - FEL Mirrors","2007-02-01","2007-02-07"]
["XT_0943","Procure Review Electronics - FEL Mirrors","2007-02-01","2007-02-07"]
["XT_0944","AWARD: Contract Vacuum Components - FEL Mirrors","2007-02-08","2007-02-08"]
["XT_0945","AWARD: Contract Electronics - FEL Mirrors","2007-02-08","2007-02-08"]
["XT_0946","AWARD: Mechanisms - FEL Mirrors","2007-02-08","2007-02-08"]
["XT_0947","AWARD: Optics- FEL Mirrors","2007-02-08","2007-02-08"]
["XT_0948","Order & Receive Optics - FEL Mirrors","2007-02-09","2007-04-06"]
["XT_0949","Order & Receive Vacuum Components - FEL Mirrors","2007-02-09","2007-04-06"]
["XT_0950","Order & Receive Mechanisms - FEL Mirrors","2007-02-09","2007-04-06"]
["XT_0951","Order & Receive Electronics - FEL Mirrors","2007-02-09","2007-04-06"]
["XT_0952","Component Accept Test Optics-FEL Mirrors","2007-04-09","2007-04-13"]
["XT_0953","Component Accept Test Vacuum Compon-FEL Mirrors","2007-04-09","2007-04-13"]
["XT_0954","Component Accept Test Mechanisms-FEL Mirrors","2007-04-09","2007-04-13"]
["XT_0955","Component Accept Test Electronics -FEL Mirrors","2007-04-09","2007-04-13"]
["XT_0956","Assemble Subsystem at LLNL- FEL Mirrors","2007-04-16","2007-05-11"]
["XT_0957","Test Subsystem at LLNL - FEL Mirrors","2007-05-14","2007-06-11"]
["XT_0958","Pkg and Ship System to SLAC - FEL Mirrors","2007-06-12","2007-06-25"]
["XT_0959","AVAIL: FEL Mirrors","2007-06-26","2007-06-25"]
["XT_0960","REQD:  FEE Beneficial Occup - Mech/Vac","2007-06-26","2007-06-25"]
["XT_1004","Install - Ion Pumped Tank","2007-08-21","2007-11-13"]
["XT_1005","Test - Ion Pumped Tank","2007-11-14","2007-12-13"]
["XT_1006","COMP:  Ion Pumped Tank","2008-01-15","2008-01-14"]
["XT_1007","Commission - FEE Diagnostic Tank","2007-11-21","2007-12-06"]
["XT_1012","COMP: Design - FEE Diagnostic Tank","2007-01-12","2007-01-11"]
["XT_1015","Commission - Ion Pumped Tank","2007-12-14","2008-01-14"]
["XT_1032","Prep Bid Pkg Tank - FEE Diagnostic Tank","2007-01-12","2007-01-26"]
["XT_1042","Bid Process Tank - FEE Diagnostic Tank","2007-01-29","2007-02-26"]
["XT_1052","AWARD: Contract Tank - FEE Diagnostic Tank","2007-02-27","2007-02-27"]
["XT_1062","Vendor Fab/Ship Tank - FEE Diagnostic Tank","2007-02-28","2007-05-22"]
["XT_1072","RECV:  Tank - FEE Diagnostic Tank","2007-05-23","2007-05-22"]
["XT_1108","COMP:  Fixed Mask  Installed & Commissioned","2007-10-17","2007-10-16"]
["XT_111","R&D - Conceptual Design","2005-05-02","2005-09-28"]
["XT_1110","Test - Fixed Mask","2007-06-13","2007-09-06"]
["XT_1111","Install - Fixed Mask","2007-05-15","2007-06-12"]
["XT_1156","Commission - Fixed Mask 1","2007-09-19","2007-10-16"]
["XT_122","REQD: NEH BO","2007-06-19","2007-06-19"]
["XT_132","REQD: FEH BO","2007-08-20","2007-08-20"]
["XT_14","Procure Review CCD Sensors - Direct Imager","2007-03-01","2007-03-07"]
["XT_1414","Physics Specification -FEE Mech/Vac-Peter Stefan","2005-12-01","2006-02-10"]
["XT_1415","Conceptual Design Prep - Direct Imager","2006-06-08","2006-06-21"]
["XT_1416","Write ESD - Direct Imager","2006-06-08","2006-07-06"]
["XT_1417","Conceptual Design - Direct Imager","2006-02-14","2006-06-07"]
["XT_1418","Conceptual Design  Review - Direct Imager","2006-07-07","2006-07-06"]
["XT_142","REQD: Tunnel BO","2007-08-03","2007-08-03"]
["XT_1421","Prelim Engineering Analysis - Direct Imager","2006-06-29","2006-07-20"]
["XT_1424","Controls Defined - Direct Imager","2006-07-21","2006-07-26"]
["XT_1427","Engineering - Direct Imager","2006-10-30","2006-12-12"]
["XT_1428","Drafting Design - Direct Imager","2006-06-08","2006-10-27"]
["XT_1433","Detail Engineering Analysis - Direct Imager","2006-07-21","2006-08-31"]
["XT_1437","Preliminary Design Prep - Direct Imager","2006-09-01","2006-09-15"]
["XT_1438","Controls Redefined - Direct Imager","2006-09-18","2006-10-03"]
["XT_1439","Preliminary Design Review - Direct Imager","2006-09-18","2006-09-15"]
["XT_1440","Write Safety/Ref Note - Direct Imager","2006-10-04","2006-10-31"]
["XT_1441","Safety/Ref Note 1st Review - Direct Imager","2006-11-01","2006-11-21"]
["XT_1442","Safety/Ref Note 2nd Review - Direct Imager","2006-11-22","2006-12-04"]
["XT_1443","Safety/Ref Note Division Review - Direct Imager","2006-12-05","2006-12-13"]
["XT_1444","Final Design Prep - Direct Imager","2006-12-14","2006-12-28"]
["XT_1445","Prep Procure Docs Scintillator - Direct Imager","2007-01-02","2007-01-30"]
["XT_1446","Prep Procure Docs Optics - Direct Imager","2007-01-02","2007-01-30"]
["XT_1447","Prep Procure Docs Mechanism - Direct Imager","2007-01-02","2007-01-30"]
["XT_1448","Prep Procure Docs CCD Sensors - Direct Imager","2007-01-02","2007-01-30"]
["XT_1449","Final Design Review - Direct Imager","2006-12-29","2006-12-28"]
["XT_1450","Prepare Bid Pkg Vacuum System Cart - Mech/Vac","2007-07-06","2007-07-12"]
["XT_14500","Select Vendor Scintillator - Direct Imager","2007-01-31","2007-02-28"]
["XT_1451","Bid Process Vacuum System Cart - Mech/Vac","2007-07-13","2007-08-09"]
["XT_14510","Select Vendor Optics - Direct Imager","2007-01-31","2007-02-28"]
["XT_1452","AWARD: Contract Vacuum System Cart - Mech/Vac","2007-08-10","2007-08-10"]
["XT_14520","Select Vendor Mechanism - Direct Imager","2007-01-31","2007-02-28"]
["XT_1453","Vendor Fab/Ship Vacuum System Cart - Mech/Vac","2007-08-13","2007-09-10"]
["XT_14530","Select Vendor CCD Sensors - Direct Imager","2007-01-31","2007-02-28"]
["XT_1454","RECV:  Vacuum System Cart - Mech/Vac","2007-09-11","2007-09-10"]
["XT_14540","Procure Review Scintillator - Direct Imager","2007-03-01","2007-03-07"]
["XT_1455","Prepare Bid Pkg Welding Cart - Mech/Vac","2007-07-13","2007-07-19"]
["XT_14550","Procure Review Optics - Direct Imager","2007-03-01","2007-03-07"]
["XT_1456","Bid Process Welding Cart - Mech/Vac","2007-07-20","2007-08-16"]
["XT_14560","Procure Review Mechanism - Direct Imager","2007-03-01","2007-03-07"]
["XT_1457","AWARD: Contract Welding Cart - Mech/Vac","2007-08-17","2007-08-17"]
["XT_1458","Vendor Fab/Ship Welding Cart - Mech/Vac","2007-08-20","2007-09-17"]
["XT_1459","RECV:  Welding Cart - Mech/Vac","2007-09-18","2007-09-17"]
["XT_1460","Prepare Procure Docs Stands - FEE Mech/Vac","2006-10-02","2006-11-28"]
["XT_1461","Select Vendor Stands - FEE Mech/Vac","2006-07-06","2006-09-28"]
["XT_1464","Order & Receive CCD Sensors - Direct Imager","2007-03-09","2007-05-03"]
["XT_1465","Order & Receive Mechanism - Direct Imager","2007-03-09","2007-05-03"]
["XT_1467","Accept Test - Direct Imager","2007-05-04","2007-05-10"]
["XT_1470","Assemble Subsystem at LLNL- Direct Imager","2007-05-11","2007-06-08"]
["XT_1471","Procurement Review Stands - FEE Mech/Vac","2006-11-29","2006-12-05"]
["XT_1472","Test Subsystem at LLNL - Direct Imager","2007-06-11","2007-07-09"]
["XT_1473","Pkg and Ship System to SLAC - Direct Imager","2007-07-10","2007-07-23"]
["XT_1474","Select Scintillator - Direct Imager","2006-02-13","2006-06-06"]
["XT_1476","Write IWS - Direct Imager","2006-06-22","2006-07-06"]
["XT_1484","Select Optics - Direct Imager","2006-02-13","2006-06-06"]
["XT_1494","Select CCD Sensors - Direct Imager","2006-02-13","2006-06-06"]
["XT_1500","Select Vendor Sensors - Total Energy","2006-12-05","2007-01-17"]
["XT_1501","Select Vendor Cryo Components - Total Ene","2006-12-05","2007-01-17"]
["XT_1502","Select Vendor Electronics - Total Energy","2006-12-05","2007-01-17"]
["XT_1503","Select Vendor Mechanisms - Total Energy","2006-12-05","2007-01-17"]
["XT_152","BCR Start","2005-12-01","2005-12-01"]
["XT_153","Physics PRD - FEL Mirrors","2006-01-12","2006-01-11"]
["XT_155","Prototype - Testing- Phase II","2006-06-22","2006-07-06"]
["XT_1551","Test at LLNL - FEE Mech/Vac","2007-07-06","2007-08-02"]
["XT_156","Conceptual Design - Gas & Solid Attenuators","2006-01-03","2006-01-31"]
["XT_157","Conceptual Design Prep - Gas & Solid Attenuators","2006-02-01","2006-02-14"]
["XT_158","Concept Design Review - Gas & Solid Attenuators","2006-02-15","2006-02-14"]
["XT_159","Tunnel Transition Section Eng - Tunnel Mech/Vac","2005-12-05","2006-01-03"]
["XT_1600","Prep Procure Docs Sensors - Total Energy","2006-11-03","2006-12-04"]
["XT_1602","Procure Review Sensors - Total Energy","2007-01-18","2007-01-24"]
["XT_1603","AWARD: Sensors - Total Energy","2007-01-25","2007-01-25"]
["XT_1604","Order & Receive Sensors - Total Energy","2007-01-26","2007-02-23"]
["XT_1606","Prep Procure Docs Cryo Components - Total Energy","2006-11-03","2006-12-04"]
["XT_1608","Procure Review Cryo Components - Total Energy","2007-01-18","2007-01-24"]
["XT_1609","AWARD: Contract Cryo Components - Total Energy","2007-01-25","2007-01-25"]
["XT_1610","Order & Receive Cryo Components - Total Energy","2007-01-26","2007-02-23"]
["XT_1800","Engineering Specification - Indirect Imager","2006-03-30","2006-04-12"]
["XT_1801","Conceptual Design Prep - Indirect Imager","2006-06-16","2006-06-29"]
["XT_1802","Write ESD - Indirect Imager","2006-04-13","2006-04-26"]
["XT_1803","Conceptual Design - Indirect Imager","2006-04-13","2006-06-15"]
["XT_1804","Conceptual Design  Review - Indirect Imager","2006-06-30","2006-06-29"]
["XT_1805","Write IWS- Indirect Imager","2006-04-27","2006-05-10"]
["XT_1810","Controls Defined - Indirect Imager","2006-06-30","2006-07-06"]
["XT_1811","Prelim Engineering Analysis -Indirect Imager","2006-05-04","2006-06-01"]
["XT_1812","Detail Engineering Analysis - Indirect Imager","2006-06-02","2006-08-04"]
["XT_1813","Vacuum Analysis - Indirect Imager","2006-06-16","2006-07-14"]
["XT_1815","Shared Vacuum Engineering - Indirect Imager","2006-10-03","2006-10-09"]
["XT_1817","Shared Enclosure/Stand Engineer- Indirect Imager","2006-10-03","2006-10-16"]
["XT_1818","Drafting Design-Enclosure- Ind Imager Only","2006-06-16","2006-07-07"]
["XT_1821","Drafting Mechanism Design - Indirect Imager","2006-06-16","2006-10-09"]
["XT_1823","Preliminary Design Prep - Indirect Imager","2006-10-10","2006-10-23"]
["XT_1824","Controls Redefined - Indirect Imager","2006-10-24","2006-11-08"]
["XT_1825","Preliminary Design Review - Indirect Imager","2006-10-24","2006-10-23"]
["XT_1826","Write Safety/Ref Note - Indirect Imager","2006-08-07","2006-09-01"]
["XT_1827","Safety/Ref Note 1st Review - Indirect Imager","2006-09-05","2006-09-25"]
["XT_1828","Safety/Ref Note 2nd Review - Indirect Imager","2006-09-26","2006-10-04"]
["XT_1829","Safety/Ref Note Division Review - Indirect Image","2006-10-05","2006-10-13"]
["XT_1830","Final Design Prep - Indirect Imager","2006-12-07","2006-12-20"]
["XT_1831","Prep Procure Docs CCD Sensors - Indirect Imager","2007-01-02","2007-01-30"]
["XT_1832","Prep Procure Docs Multilayer - Indirect Imager","2007-01-02","2007-01-30"]
["XT_1834","Prep Procure Docs Mechanisms - Indirect Imager","2007-01-02","2007-01-30"]
["XT_1835","Final Design Review - Indirect Imager","2006-12-21","2006-12-20"]
["XT_1836","Select Vendor CCD Sensors - Indirect Imager","2007-01-31","2007-02-28"]
["XT_1837","Select Vendor Multilayer - Indirect Imager","2007-01-31","2007-02-28"]
["XT_1839","Select Vendor Mechanisms - Indirect Imager","2007-01-31","2007-02-28"]
["XT_1840","Procure Review Mechanisms - Indirect Imager","2007-03-01","2007-03-07"]
["XT_1841","Procure Review CCD Sensors - Indirect Imager","2007-03-01","2007-03-07"]
["XT_1842","Procure Review Multilayer - Indirect Imager","2007-03-01","2007-03-07"]
["XT_1844","AWARD: Contract Multilayer - Indirect Image","2007-03-08","2007-03-08"]
["XT_1846","AWARD: Vac Hardware - Indirect Imager","2007-03-08","2007-03-08"]
["XT_1847","AWARD: CCD Sensors - Indirect Imager","2007-03-08","2007-03-08"]
["XT_1848","Order & Receive CCD Sensors - Indirect Image","2007-03-09","2007-05-03"]
["XT_1849","Order & Receive Multilayer - Indirect Image","2007-03-09","2007-05-03"]
["XT_1850","Order & Receive Mechanisms - Indirect Imager","2007-03-09","2007-05-03"]
["XT_1852","Accept Test - Indirect Imager","2007-05-04","2007-05-10"]
["XT_1856","Assemble Subsystem at LLNL- Indirect Imager","2007-05-11","2007-06-08"]
["XT_1857","REQD:  FEE Beneficial Occup - Mech/Vac","2007-07-24","2007-07-23"]
["XT_1859","Test Subsystem at LLNL - Indirect Imager","2007-06-11","2007-07-09"]
["XT_1860","Pkg and Ship System to SLAC - Indirect Imager","2007-07-10","2007-07-23"]
["XT_1890","Multilayer Specification - Indirect Imager","2006-02-01","2006-03-29"]
["XT_1900","Component Fab Multilayer - Indirect Imager","2006-03-30","2006-05-24"]
["XT_1910","Component Test Multilayer - Indirect Imager","2006-04-20","2006-06-15"]
["XT_1920","Physics Specification - Indirect Imager","2005-12-02","2006-01-31"]
["XT_200","Engineering Specification - FEE Mech/Vac","2005-12-01","2006-03-13"]
["XT_201","Vacuum Controls Defined - FEE Mech/Vac","2006-05-16","2006-05-22"]
["XT_2011","Acceptance Test - Gas Attenuator","2007-08-21","2007-09-18"]
["XT_2012","Assemble - Beamline Test - Gas Attenuator","2007-08-21","2007-09-18"]
["XT_2013","Commission - Gas Attenuator","2007-09-19","2007-10-17"]
["XT_2014","COMP:  Gas Attenuator Installed & Commissioned","2007-10-18","2007-10-17"]
["XT_2021","Theory - Gas Attenuator","2005-10-18","2005-11-14"]
["XT_2023","Bid Process Hardware - Attenuator","2007-02-22","2007-03-07"]
["XT_2032","AWARD: Contract Hardware - Gas Attenuator","2007-03-08","2007-03-08"]
["XT_2033","Vendor Fab Hardware - Attenuator","2007-03-09","2007-06-01"]
["XT_2053","RECV: Hardware - Attenuator","2007-06-04","2007-06-01"]
["XT_20611","TTF Damage Experiment - FY-06","2005-10-03","2006-04-21"]
["XT_2063","Assemble Hardware - Attenuator","2007-06-04","2007-07-09"]
["XT_210","Vacuum Analyses - FEE Mech/Vac","2006-04-25","2006-05-08"]
["XT_2111","Install - FEE Mech/Vac","2007-08-17","2007-08-23"]
["XT_2125","REQD: FEE Beneficial Occupancy Attenuators","2007-08-21","2007-08-20"]
["XT_217","Prep Procure Docs Vac Hardware - FEE Mech/Vac","2006-10-02","2006-11-28"]
["XT_218","AWARD: Vac Hardware - FEE Mech/Vac","2006-12-06","2006-12-06"]
["XT_219","Component Accept Test Vac Hardware-FEE Mech/Vac","2007-05-02","2007-05-08"]
["XT_220","Vacuum Components Defined - FEE Mech/Vac","2006-05-09","2006-05-15"]
["XT_224","REQD:  FEE Beneficial Occup - Mech/Vac","2007-05-15","2007-05-14"]
["XT_227","Select Vac Hardware Vendor - FEE Mech/Vac","2006-07-06","2006-09-28"]
["XT_233","Administrative/Database Support - LLNL-CON","2005-05-02","2008-10-15"]
["XT_234","Teleconference/Comp - LLNL-CON","2005-05-02","2008-10-15"]
["XT_2340","Physics Specification - Total Energy","2005-12-02","2006-03-29"]
["XT_235","Project Support M&S - LLNL-CON","2005-05-02","2008-10-15"]
["XT_237","Procurement Review Vac Hardware - FEE Mech/Vac","2006-11-29","2006-12-05"]
["XT_24","AVAIL: FEE Mechanical/Vacuum","2007-08-17","2007-08-16"]
["XT_240","Write ESD - FEE Mech/Vac","2006-04-11","2006-05-08"]
["XT_242","Engineering Specification - NEH Mech/Vac","2006-03-28","2006-04-24"]
["XT_243","Conceptual Design Review Prep - FEE Mech/Vac","2006-04-11","2006-04-24"]
["XT_244","Preliminary Design Review Prep - FEE Mech/Vac","2006-05-09","2006-05-22"]
["XT_247","Order & Receive Vac Hardware - FEE Mech/Vac","2006-12-07","2007-05-01"]
["XT_250","Conceptual Design - FEE Mech/Vac","2006-03-14","2006-04-10"]
["XT_255","Engineering Specification - FEL Mirrors","2006-02-27","2006-03-24"]
["XT_256","Mirror Specification - FEL Mirrors","2006-01-12","2006-02-24"]
["XT_2560","Engineering - Indirect Imager","2006-10-24","2006-12-06"]
["XT_26","Install Vacuum Piping - Far Hall Mech/Vac","2008-01-30","2008-02-05"]
["XT_260","Specification - Fixed Mask","2005-12-14","2006-01-11"]
["XT_267","Physics Requirements Doc Comp - Gas Attenuator","2006-02-06","2006-02-03"]
["XT_269","Material Mgt","2005-12-02","2007-09-28"]
["XT_270","Conceptual Design Prep - NEH Mech/Vac","2006-05-09","2006-05-22"]
["XT_271","AWARD Prototype Procurement - Gas Attenuator","2006-02-06","2006-02-06"]
["XT_2710","Conceptual Design Review - NEH Mech/Vac","2006-05-23","2006-05-22"]
["XT_273","Final Design Prep - Attenuator","2007-01-12","2007-01-26"]
["XT_2755","Prelim Design Review - Attenuator","2006-12-14","2006-12-13"]
["XT_277","Wave Modeling - FY-06","2006-01-03","2006-09-29"]
["XT_280","Fast Valve Design - FEE Mech/Vac","2006-04-11","2006-05-01"]
["XT_284","Monte Carlo Modeling - FY-06","2006-01-03","2006-09-29"]
["XT_286","Final Design Review Prep - FEH Mech/Vac","2007-02-12","2007-02-26"]
["XT_295","REQD: Diagnostics Ready Undulator Light - FEE","2008-01-07","2008-01-07"]
["XT_296","Final Design Review Prep- Tunnel Mech/Vac","2006-03-17","2006-04-13"]
["XT_30200","Prep Procure Docs Stand - FEL Mirrors","2006-11-17","2007-01-02"]
["XT_30201","Select Vendor Stand- FEL Mirrors","2007-01-03","2007-01-31"]
["XT_30202","Procure Review Stand - FEL Mirrors","2007-02-01","2007-02-07"]
["XT_30203","AWARD: Stand - FEL Mirrors","2007-02-08","2007-02-08"]
["XT_30204","Order & Receive Stand - FEL Mirrors","2007-02-09","2007-04-06"]
["XT_30205","Component Accept Test Stand-FEL Mirrors","2007-04-09","2007-04-13"]
["XT_30206","Prep Procure Docs Enclosure - FEL Mirrors","2006-11-17","2007-01-02"]
["XT_30207","Select Vendor Enclosure- FEL Mirrors","2007-01-03","2007-01-31"]
["XT_30208","Procure Review Enclosure - FEL Mirrors","2007-02-01","2007-02-07"]
["XT_30209","AWARD: Enclosure - FEL Mirrors","2007-02-08","2007-02-08"]
["XT_30210","Order & Receive Enclosure - FEL Mirrors","2007-02-09","2007-04-06"]
["XT_30211","Component Accept Test Enclosure-FEL Mirrors","2007-04-09","2007-04-13"]
["XT_303","Physics Requirements Document - Indirect Imager","2006-02-01","2006-01-31"]
["XT_30311","Write IWS - Spectrometer","2006-07-12","2006-07-25"]
["XT_30316","Physics Specification - Spectrometer","2005-10-03","2006-01-11"]
["XT_30317","Conceptual Design Prep - Spectrometer","2006-04-10","2006-04-21"]
["XT_30318","Write ESD - Spectrometer","2006-07-12","2006-07-25"]
["XT_30319","Conceptual Design - Spectrometer","2006-01-12","2006-04-07"]
["XT_30320","Conceptual Design  Review - Spectrometer","2006-04-24","2006-04-21"]
["XT_30323","Engineering Analysis - Spectrometer","2006-05-01","2006-06-26"]
["XT_30325","Controls Defined - Spectrometer","2006-07-12","2006-07-17"]
["XT_30334","Design - Spectrometer","2006-04-24","2006-06-19"]
["XT_30337","Preliminary Design Prep - Spectrometer","2006-06-27","2006-07-11"]
["XT_30338","Controls Redefined - Spectrometer","2006-07-18","2006-08-02"]
["XT_30339","Preliminary Design Review - Spectrometer","2006-07-12","2006-07-11"]
["XT_30340","Write Safety/Ref Note - Spectrometer","2006-08-03","2006-08-30"]
["XT_30341","Safety/Ref Note 1st Review - Spectrometer","2006-08-31","2006-09-21"]
["XT_30342","Safety/Ref Note 2nd Review - Spectrometer","2006-09-22","2006-10-02"]
["XT_30343","Safety/Ref Note Division Review - Spectrometer","2006-10-03","2006-10-11"]
["XT_30344","Final Design Prep - Spectrometer","2006-10-12","2006-10-25"]
["XT_30345","Prep Procure Docs Readout Electronics - Spectrom","2006-10-26","2006-11-22"]
["XT_30346","Prep Procure Docs Optics - Spectrometer","2006-10-26","2006-11-22"]
["XT_30347","Prep Procure Docs Mechanism - Spectrometer","2006-10-26","2006-11-22"]
["XT_30349","Final Design Review - Spectrometer","2006-10-26","2006-10-25"]
["XT_30350","Select Vendor Readout Electronics - Spectrometer","2006-11-27","2007-01-08"]
["XT_30351","Select Vendor Optics - Spectrometer","2006-11-27","2007-01-08"]
["XT_30352","Select Vendor Mechanism - Spectrometer","2006-11-27","2007-01-08"]
["XT_30355","Procure Review Readout Electronics - Spectromete","2007-01-09","2007-01-16"]
["XT_30356","Procure Review Optics - Spectrometer","2007-01-09","2007-01-16"]
["XT_30357","Procure Review Mechanism - Spectrometer","2006-11-27","2006-12-01"]
["XT_30358","AWARD: Contract Optics - Spectrometer","2007-01-17","2007-01-17"]
["XT_30359","AWARD: Contract Mechanism - Spectrometer","2006-12-04","2006-12-04"]
["XT_30361","AWARD: Readout Electronics  - Spectrometer","2007-01-17","2007-01-17"]
["XT_30362","Order & Receive Readout Electronics - Spectromet","2007-01-18","2007-03-15"]
["XT_30363","Order & Receive Optics - Spectrometer","2007-01-18","2007-03-15"]
["XT_30365","Order & Receive Mechanism - Spectrometer","2006-12-05","2007-02-14"]
["XT_30366","AVAIL: Spectrometer","2007-05-15","2007-05-14"]
["XT_30367","REQD:  FEE Beneficial Occup - Mech/Vac","2007-08-21","2007-08-20"]
["XT_30368","Component Accept Test Readout Electronics-Spectr","2007-03-16","2007-03-22"]
["XT_30369","Component Accept Test Optics - Spectrometer","2007-03-16","2007-03-22"]
["XT_30371","Component Accept Test Mechanism -Spectrometer","2007-02-15","2007-02-22"]
["XT_30372","Assemble Subsystem at LLNL- Spectrometer","2007-03-23","2007-04-19"]
["XT_30373","Test Subsystem at LLNL - Spectrometer","2007-04-20","2007-05-17"]
["XT_30374","Pkg and Ship System to SLAC - Spectrometer","2007-05-18","2007-06-01"]
["XT_330","Install Isolation Valves - NH Mech/Vac - H1","2007-08-23","2007-08-29"]
["XT_3300","R&D - Total Measurement","2005-05-02","2005-09-30"]
["XT_340","Install Berilium Valves - NH Mech/Vac - H1","2007-08-23","2007-08-29"]
["XT_3444","R&D - Component Physics Design","2005-05-02","2005-07-12"]
["XT_3445","R&D - Beamline Mechanical Layout","2005-05-02","2005-07-12"]
["XT_345","Physics Requirement Document - Direct Imager","2006-02-14","2006-02-13"]
["XT_3454","LLNL - Commissioning Team","2008-10-01","2009-03-31"]
["XT_346","Physic Specification - Direct Imager","2005-12-02","2006-02-13"]
["XT_3464","R&D - FEE Physics Preliminary Layout","2005-07-13","2005-07-12"]
["XT_3474","R&D - Near Hall Physics Preliminary Layout","2005-07-13","2005-07-12"]
["XT_3484","R&D - Far Hall Physics Preliminary Layout","2005-09-29","2005-09-28"]
["XT_3485","R&D - Beamline Electronics & Controls","2005-05-02","2005-07-12"]
["XT_350","Install Vacuum Piping - NH Mech/Vac - H1","2007-08-23","2007-08-29"]
["XT_3506","Engineering - Indirect Imager","2006-08-07","2006-10-02"]
["XT_3507","Shared Vacuum Engineering -Direct Imager","2006-09-01","2006-09-08"]
["XT_3508","Shared Enclosure/Stand Engineer- Direct Imager","2006-09-01","2006-09-15"]
["XT_360","Install Ion Pumps - NH Mech/Vac - H1","2007-08-23","2007-08-29"]
["XT_370","Final Design Review Prep - FEE Mech/Vac","2006-09-14","2006-09-27"]
["XT_380","Collimators 1,2 Primary Design - FEE Mech/Vac","2006-04-11","2006-04-19"]
["XT_390","Collimators 3,4 Primary Design - FEE Mech/Vac","2006-05-09","2006-06-13"]
["XT_4","Assemble subsystem - FEE Mech/Vac","2007-05-09","2007-07-05"]
["XT_400","Write ESD - Fixed Mask","2006-01-12","2006-01-26"]
["XT_4003","Assemble Vacuum System - Fixed Mask","2006-10-11","2006-12-12"]
["XT_4009","Prepare Bid Pk Vacuum System - Fixed Mask","2006-06-05","2006-06-09"]
["XT_401","Design - Primary - Fixed Mask","2006-01-12","2006-03-24"]
["XT_4013","COMP: Design Package - Fixed Mask","2006-06-05","2006-06-02"]
["XT_4017","Bid Process Vacuum System - Fixed Mask","2006-06-12","2006-07-10"]
["XT_402","Write ISW - Fixed Mask","2006-07-11","2006-07-24"]
["XT_4023","AWARD: Contract Vacuum System-Fixed Mask","2006-07-11","2006-07-17"]
["XT_4028","RECV: Vacuum System - Fixed Mask","2006-10-11","2006-10-10"]
["XT_403","Design - Detail - Fixed Mask","2006-03-27","2006-04-27"]
["XT_4034","Vendor Fab Vacuum System - Fixed Mask","2006-07-18","2006-10-10"]
["XT_404","Design - Check - Fixed Mask","2006-04-28","2006-05-23"]
["XT_405","Design - Back Check - Fixed Mask","2006-05-24","2006-06-02"]
["XT_406","Vacuum Analysis Engineering - Fixed Mask","2006-03-27","2006-04-07"]
["XT_407","Select Vacuum Components - Fixed Mask","2006-04-10","2006-04-11"]
["XT_408","Preliminary Design Review Fixed Mask","2006-04-19","2006-04-18"]
["XT_409","Final Design Review - Fixed Mask","2006-06-05","2006-06-02"]
["XT_41","Install Spools - Far Hall Mech/Vac","2008-01-30","2008-02-05"]
["XT_410","Conceptual Design Review - Fixed Mask","2006-02-17","2006-02-16"]
["XT_412","Specification & Design I - Comm Diagnostic Tank","2006-05-25","2006-09-29"]
["XT_413","Preliminary Analysis Mechanic-Fixed Mask","2006-02-03","2006-02-22"]
["XT_414","Detail Analysis Mechanical-Fixed Mask","2006-02-23","2006-03-29"]
["XT_415","Safety Note - Fixed Mask","2006-04-28","2006-05-25"]
["XT_416","Test Vacuum System - Fixed Mask","2006-12-13","2007-01-25"]
["XT_417","COMP:  Comm Diagnostic Tank Installed & Commissi","2007-09-10","2007-09-07"]
["XT_420","Package and Ship - Fixed Mask","2007-01-26","2007-02-08"]
["XT_4202","Conceptual Design Review Prep- Fixed Mask","2006-02-10","2006-02-16"]
["XT_4203","PDR Prep Fixed Mask","2006-04-12","2006-04-18"]
["XT_4204","Final Design Review Prep - Fixed Mask","2006-05-26","2006-06-02"]
["XT_423","Test - Total Energy Measurement","2007-08-22","2007-09-19"]
["XT_4235","AVAIL:  Fixed Mask Arrives at SLAC","2007-02-09","2007-02-08"]
["XT_424","COMP:  Total Energy Measurement  Installed & Com","2007-10-04","2007-10-03"]
["XT_430","Pump Cross Detail Design - FEE Mech/Vac","2006-04-25","2006-05-01"]
["XT_4300","Specification - Slit/Collimator","2005-11-07","2005-12-06"]
["XT_4301","Write ESD - Slit/Collimator","2006-02-27","2006-03-10"]
["XT_4302","Write ISW - Slit/Collimator","2006-10-19","2006-11-01"]
["XT_4303","Design - Primary - Slit/Collimator","2006-02-27","2006-05-19"]
["XT_4305","Conceptual Design Review Prep- Slit/Collimator","2006-02-17","2006-02-24"]
["XT_4306","Conceptual Design Review - Slit/Collimator","2006-02-27","2006-02-24"]
["XT_4307","Detail Analysis Mechanical-Slit/Collimator","2005-12-07","2006-03-10"]
["XT_4309","Engineering - Slit/Collimator","2006-02-27","2006-05-19"]
["XT_4311","PDR Prep - Slit/Collimator","2006-03-13","2006-03-17"]
["XT_4312","Preliminary Design Review - Slit/Collimator","2006-05-22","2006-05-19"]
["XT_4314","Safety Note - Slit/Collimator","2006-05-22","2006-06-19"]
["XT_4316","Final Design Review Prep - Slit/Collimator","2006-07-19","2006-07-25"]
["XT_4317","COMP: Design Package - Slit/Collimator","2006-07-26","2006-07-25"]
["XT_4318","Final Design Review - Slit/Collimator","2006-07-26","2006-07-25"]
["XT_4319","Prep Bid Pk Vac System-Slit/Collimator","2006-07-26","2006-08-22"]
["XT_4320","Bid Process Vacuum System - Slit/Collimator","2006-08-23","2006-10-18"]
["XT_4321","Vendor Fab Vacuum System - Slit/Collimator","2006-10-19","2007-01-30"]
["XT_43211","AWARD:  Slit/Collimator","2006-10-19","2006-10-19"]
["XT_4322","RECV: Vacuum System - Slit/Collimator Mechanism","2007-01-31","2007-01-30"]
["XT_4323","Assemble Vacuum System - Slit/Collimator","2007-01-31","2007-03-28"]
["XT_4324","Test Vacuum System - Slit/Collimator","2007-03-29","2007-04-25"]
["XT_4325","Package and Ship - Slit/Collimator","2007-04-26","2007-05-09"]
["XT_4326","AVAIL:  Slit Arrives at SLAC","2007-05-10","2007-05-09"]
["XT_433","Commission - Total Energy Measurement","2007-09-20","2007-10-03"]
["XT_4378","Engineering Analysis - Ion Chamber","2006-10-02","2006-11-28"]
["XT_43788","Design - Ion Chamber","2006-10-02","2006-11-28"]
["XT_4436","Procure Spares - Direct Imager","2006-10-03","2007-01-11"]
["XT_451","Shared Enclosure/Stand Engineer-Total Energy","2006-06-14","2006-06-27"]
["XT_452","Install - Total Energy Measurement","2007-06-26","2007-08-21"]
["XT_453","Engineering - Slit/Collimator","2006-05-22","2006-07-18"]
["XT_45301","Write IWS - Ion Chamber","2006-10-02","2006-10-13"]
["XT_45303","Evaluation of Readout Methods - Ion Chamber","2006-03-15","2006-09-29"]
["XT_45306","Physics Specification - Ion Chamber","2005-12-02","2006-03-14"]
["XT_45307","Conceptual Design Prep - Ion Chamber","2006-06-08","2006-06-21"]
["XT_45308","Write ESD - Ion Chamber","2006-08-18","2006-08-31"]
["XT_45309","Conceptual Design - Ion Chamber","2006-03-15","2006-06-07"]
["XT_45310","Conceptual Design  Review - Ion Chamber","2006-06-22","2006-06-21"]
["XT_45315","Controls Defined - Ion Chamber","2006-08-18","2006-08-23"]
["XT_45317","Engineering Analysis - Ion Chamber","2006-06-22","2006-08-17"]
["XT_45318","Vacuum Analysis System Design - Ion Chamber","2006-06-08","2006-07-06"]
["XT_45321","Design - Ion Chamber","2006-06-22","2006-08-17"]
["XT_45327","Preliminary Design Prep - Ion Chamber","2006-08-18","2006-08-31"]
["XT_45329","Preliminary Design Review - Ion Chamber","2006-09-01","2006-08-31"]
["XT_45330","Write Safety/Ref Note - Ion Chamber","2006-08-24","2006-09-21"]
["XT_45331","Safety/Ref Note 1st Review - Ion Chamber","2006-10-02","2006-10-20"]
["XT_45332","Safety/Ref Note 2nd Review - Ion Chamber","2006-10-23","2006-10-31"]
["XT_45333","Safety/Ref Note Division Review - Ion Chamber","2006-11-01","2006-11-09"]
["XT_45334","Final Design Prep - Ion Chamber","2006-11-10","2006-11-27"]
["XT_45335","Prep Procure Docs Electrical - Ion Chamber","2006-11-29","2007-01-10"]
["XT_45336","Prep Procure Docs Apertures - Ion Chamber","2006-11-29","2007-01-10"]
["XT_45337","Prep Procure Docs Stand - Ion Chamber","2006-11-29","2007-01-10"]
["XT_45338","Prep Procure Docs Vacuum Components - Ion Chambe","2006-11-29","2007-01-10"]
["XT_45339","Final Design Review - Ion Chamber","2006-11-29","2006-11-28"]
["XT_45340","Select Vendor Electrical - Ion Chamber","2007-01-11","2007-02-08"]
["XT_45341","Select Vendor Apertures - Ion Chamber","2007-01-11","2007-02-08"]
["XT_45342","Select Vendor Stand - Ion Chamber","2007-01-11","2007-02-08"]
["XT_45343","Select Vendor Vacuum Components - Ion Chamber","2007-01-11","2007-02-08"]
["XT_45344","Procure Review Vacuum Components - Ion Chamber","2007-02-09","2007-02-15"]
["XT_45345","Procure Review Electrical - Ion Chamber","2007-02-09","2007-02-15"]
["XT_45346","Procure Review Apertures - Ion Chamber","2007-02-09","2007-02-15"]
["XT_45347","Procure Review Stand - Ion Chamber","2007-02-09","2007-02-15"]
["XT_45348","AWARD: Contract Apertures - Ion Chamber","2007-02-16","2007-02-16"]
["XT_45349","AWARD: Contract Stand - Ion Chamber","2007-02-16","2007-02-16"]
["XT_45350","AWARD: Vacuum Components - Ion Chamber","2007-02-16","2007-02-16"]
["XT_45351","AWARD: Electrical  - Ion Chamber","2007-02-16","2007-02-16"]
["XT_45352","Order & Receive Electrical - Ion Chamber","2007-02-20","2007-04-16"]
["XT_45353","Order & Receive Apertures - Ion Chamber","2007-02-20","2007-04-16"]
["XT_45354","Order & Receive Vacuum Components - Ion Chamber","2007-02-20","2007-04-16"]
["XT_45355","Order & Receive Stand - Ion Chamber","2007-02-20","2007-04-16"]
["XT_45356","AVAIL: Ion Chamber","2007-07-05","2007-07-03"]
["XT_45357","REQD:  FEE Beneficial Occup - Mech/Vac","2007-08-21","2007-08-20"]
["XT_45358","Component Accept Test Electrical-Ion Chamber","2007-04-17","2007-04-23"]
["XT_45359","Component Accept Test Apertures - Ion Chamber","2007-04-17","2007-04-23"]
["XT_45360","Component Accept Test Vacuum Components - Ion Ch","2007-04-17","2007-04-23"]
["XT_45361","Component Accept Test Stand -Ion Chamber","2007-04-17","2007-04-23"]
["XT_45362","Assemble Subsystem at LLNL- Ion Chamber","2007-04-24","2007-05-21"]
["XT_45363","Test Subsystem at LLNL - Ion Chamber","2007-05-22","2007-06-19"]
["XT_45364","Pkg and Ship System to SLAC - Ion Chamber","2007-06-20","2007-07-03"]
["XT_456","Mech/Vac Supplies","2007-10-01","2007-11-27"]
["XT_45600","Prep Procure Docs Enclosure - Ion Chamber","2006-11-29","2007-01-10"]
["XT_45601","Select Vendor  Enclosure - Ion Chamber","2007-01-11","2007-02-08"]
["XT_45602","Procure Review  Enclosure - Ion Chamber","2007-02-09","2007-02-15"]
["XT_45603","AWARD:  Enclosure  - Ion Chamber","2007-02-16","2007-02-16"]
["XT_45604","Order & Receive  Enclosure - Ion Chamber","2007-02-20","2007-04-16"]
["XT_45605","Component Accept Test  Enclosure-Ion Chamber","2007-04-17","2007-04-23"]
["XT_4567","Design II - Motors","2006-08-04","2006-09-29"]
["XT_457","Specification & Design II - Comm Diagnostic Tank","2006-10-02","2007-02-08"]
["XT_460","Prelim Analysis of Stand - FEE Mech/Vac","2006-04-04","2006-04-10"]
["XT_4632","Engineering Analysis - Spectrometer","2006-07-12","2006-08-08"]
["XT_46323","Design - Spectrometer","2006-07-12","2006-08-08"]
["XT_470","Detail Analysis of Stand - FEE Mech/Vac","2006-06-14","2006-07-05"]
["XT_4700","Write ESD - Gas Attenuator","2006-05-02","2006-06-05"]
["XT_4701","Design Studies Conceptual - Gas Attenuator","2005-10-03","2005-10-28"]
["XT_4703","Design Studies-Internal Review 1-Gas Attenuator","2005-10-31","2005-10-28"]
["XT_4704","Design Studies-PreliminaryDesign-Gas Attenuator","2005-10-31","2005-11-18"]
["XT_4706","XRay Source-Facil Contact-Gas Attenuator","2005-10-03","2005-10-17"]
["XT_4707","XRay Source- IWS - Gas Attenuator","2005-10-03","2005-10-10"]
["XT_4708","XRay Source-Interface - Gas Attenuator","2005-10-11","2005-10-24"]
["XT_4709","Engineering - PDR Prep - Attenuator","2006-11-30","2006-12-13"]
["XT_4710","Engineering Design Revision - Attenuator","2006-12-14","2007-02-09"]
["XT_4711","Engineering - Design 1 - Attenuator","2006-08-07","2006-10-02"]
["XT_4712","Safety Note - Gas Attenuator","2005-12-02","2006-01-13"]
["XT_4713","Engineering - Design 2 -  Attenuator","2006-10-03","2006-11-29"]
["XT_4714","Engineering Final Design Review- Attenuator","2007-02-12","2007-02-09"]
["XT_4715","COMP: Design Package - Attenuator","2007-02-12","2007-02-09"]
["XT_480","Write Safety/Ref Note - FEE Mech/Vac","2006-07-06","2006-08-02"]
["XT_483","Test - Spectral Measurement","2007-06-20","2007-07-18"]
["XT_484","COMP:  Spectral Measurement","2007-10-03","2007-10-02"]
["XT_490","Safety/Ref Note 1st Review - FEE Mech/Vac","2006-08-03","2006-08-23"]
["XT_491","Preliminary Specification - Gas Attenuator","2006-02-06","2006-02-27"]
["XT_4928","AVAIL: Spectrometer","2007-06-20","2007-06-19"]
["XT_496","Prototype Procurement - Gas Attenuator","2006-02-06","2006-05-01"]
["XT_497","Prepare Bid Pkg Hardware - Attenuator","2007-02-12","2007-02-21"]
["XT_5","Mechanical Design/Draft - Tunnel Mech/V","2006-01-04","2006-01-25"]
["XT_500","Safety/Ref Note 2nd Review - FEE Mech/Vac","2006-08-24","2006-09-01"]
["XT_5003","COMP:  Solid Attenuator Installed & Commissioned","2007-10-18","2007-10-17"]
["XT_510","Safety/Ref Note SLAC Review - FEE Mech/Vac","2006-09-05","2006-09-13"]
["XT_520","Collimators 3,4 Design Check - FEE Mech/Vac","2006-07-06","2006-07-12"]
["XT_530","Collimators 3,4 Design Back Check - FEE Mech/Vac","2006-07-13","2006-07-17"]
["XT_540","Pump Cross Primary Design - FEE Mech/Vac","2006-04-11","2006-04-24"]
["XT_542","Engineering Analysis - FEL Mirrors","2006-08-23","2006-10-18"]
["XT_5432","Design - FEL Mirrors","2006-08-23","2006-10-18"]
["XT_546","Procure Spares","2008-10-01","2009-01-30"]
["XT_55","Travel - FY06-09","2005-10-03","2009-03-30"]
["XT_550","Write IWS - Gas Attenuator","2005-10-17","2005-10-28"]
["XT_5500","Prototype - Report - Attenuator","2006-07-27","2006-08-04"]
["XT_556","Install Isolation Valve - Tunnel Mech/Vac","2007-09-10","2008-01-17"]
["XT_558","Commission - Tunnel Mech/Vac","2007-09-19","2007-10-16"]
["XT_559","COMP:  Tunnel Mech/Vac  Installed & Commiss","2007-10-17","2007-10-16"]
["XT_560","Collimators 3,4 Detail Design - FEE Mech/Vac","2006-06-14","2006-07-05"]
["XT_567","Prototype - Design","2005-10-03","2005-10-14"]
["XT_568","Prototype - First Review","2005-10-25","2005-10-24"]
["XT_569","Prototype - Fabrication - Gas Attenuator","2006-02-06","2006-05-01"]
["XT_570","Prototype - Assembly-Gas Attenuator","2006-05-02","2006-05-23"]
["XT_572","Prototype - Data Analysis - Attenuator","2006-07-07","2006-07-26"]
["XT_574","Commissioning - Spectral Measurement","2007-09-19","2007-10-02"]
["XT_580","Collimators 1,2 Detail Design - FEE Mech/Vac","2006-05-02","2006-05-08"]
["XT_589","Prototype Material - Total Energy","2006-01-06","2006-04-03"]
["XT_590","Collimators 1,2 Design Check - FEE Mech/Vac","2006-05-09","2006-05-11"]
["XT_596","Test - Direct Imager","2007-08-07","2007-09-04"]
["XT_597","COMP: Direct Imager","2007-09-19","2007-09-18"]
["XT_6","Test - FEE Mech/Vac","2007-09-18","2007-12-12"]
["XT_600","Collimators 1,2 Design Back Check - FEE Mech/Vac","2006-05-12","2006-05-15"]
["XT_610","Pump Cross Design Check - FEE Mech/Vac","2006-05-02","2006-05-03"]
["XT_620","Pump Cross Design Back Check - FEE Mech/Vac","2006-05-04","2006-05-08"]
["XT_6231","Physics Specification II - FEL Mirrors","2006-01-12","2006-05-05"]
["XT_625","AVAIL: Tunnel Mechanical/Vacuum","2007-09-10","2007-09-07"]
["XT_626","Install Vacuum Piping - Tunnel Mech/Vac","2007-09-10","2008-01-17"]
["XT_630","Vacuum Valve Primary Design - FEE Mech/Vac","2006-05-02","2006-05-08"]
["XT_6345","Design - FEL Mirrors","2006-06-13","2006-08-08"]
["XT_635","Visible Calibration - Direct Imager","2007-07-24","2007-07-30"]
["XT_636","Install Ion Pumps - Tunnel Mech/Vac","2007-09-10","2008-01-17"]
["XT_640","Vacuum Valve Detail Design - FEE Mech/Vac","2006-05-09","2006-05-11"]
["XT_645","X-Ray Calibration - Direct Imager","2007-07-31","2007-08-06"]
["XT_646","Install Ion Gauges - Tunnel Mech/Vac","2007-09-10","2008-01-17"]
["XT_647","Install Stands - Tunnel Mech/Vac","2007-09-10","2008-01-17"]
["XT_65","Engineering - Total Energy","2006-06-14","2006-08-09"]
["XT_650","Vacuum Valve Design Check - FEE Mech/Vac","2006-05-12","2006-05-15"]
["XT_6501","Modeling & Simulation - FY-07","2006-10-02","2007-09-28"]
["XT_6502","Modeling & Simulation - FY-08","2007-10-01","2008-09-30"]
["XT_653","Conceptual Design - Slit/Collimator","2005-12-07","2006-02-16"]
["XT_6532","EPICs Controls Design II - FY-06","2006-04-12","2006-09-29"]
["XT_654","AVAIL: Direct Imager","2007-07-24","2007-07-23"]
["XT_656","Install Spools - Tunnel Mech/Vac","2007-09-10","2008-01-17"]
["XT_660","Vacuum Valve Design Back Check - FEE Mech/Vac","2006-05-16","2006-05-17"]
["XT_66001","Test System - Attenuator","2007-07-10","2007-08-06"]
["XT_66002","Package and Ship - Attenuator","2007-08-07","2007-08-20"]
["XT_6630","Conceptual Design - Total Energy","2006-04-04","2006-05-30"]
["XT_6631","Conceptual Design Review Prep - Total Energy","2006-05-31","2006-06-13"]
["XT_66311","Conceptual Design Review - Total Energy","2006-06-14","2006-06-13"]
["XT_66312","Preliminary Design Review - Total Energy","2006-08-10","2006-08-09"]
["XT_66313","Preliminary Design Prep - Total Energy","2006-06-21","2006-07-05"]
["XT_6632","Prelim Engineering Analysis - Total Energy","2006-06-21","2006-06-27"]
["XT_6633","Write ESD - Total Energy","2006-05-31","2006-06-13"]
["XT_6634","Engineering - Total Energy","2006-08-10","2006-09-07"]
["XT_6640","Vacuum Analysis - Total Energy","2006-03-30","2006-04-26"]
["XT_6641","Shared Vacuum Engineering - Total Energy","2006-04-27","2006-05-03"]
["XT_6642","Detail Engineering Analysis-Total Energy","2006-05-31","2006-06-20"]
["XT_6646","Drafting Design - Total Energy","2006-05-31","2006-10-19"]
["XT_665","AVAIL: Far Hall Mech/Vac","2007-12-14","2008-01-29"]
["XT_6652","Controls Defined - Total Energy","2006-05-31","2006-06-05"]
["XT_6653","Controls Redefined - Total Energy","2006-06-06","2006-06-21"]
["XT_6659","Write Safety/Ref Note - Total Energy","2006-06-22","2006-07-20"]
["XT_6662","Safety/Ref Note 1st Review - Total Energy","2006-07-21","2006-08-10"]
["XT_6663","Safety/Ref Note 2nd Review - Total Energy","2006-08-11","2006-08-21"]
["XT_6664","Safety/Ref Note Division Review - Total Energy","2006-08-22","2006-08-30"]
["XT_6666","Prep Procure Docs Electronics - Total Energy","2006-11-03","2006-12-04"]
["XT_6667","Prep Procure Docs Mechanisms - Total Energy","2006-11-03","2006-12-04"]
["XT_6668","Procure Review Electronics - Total Energy","2007-01-18","2007-01-24"]
["XT_6669","Procure Review Mechanisms - Total Energy","2007-01-18","2007-01-24"]
["XT_667","Test - Far Hall Mech/Vac - H1","2008-02-06","2008-02-20"]
["XT_66701","AWARD: Contract Electronics - Total Energy","2007-01-25","2007-01-25"]
["XT_66720","Order & Receive Mechanisms - Total Energy","2007-01-26","2007-02-23"]
["XT_66730","Order & Receive Electronics - Total Energy","2007-01-26","2007-02-23"]
["XT_66740","REQD:  FEE Beneficial Occup - Mech/Vac","2007-05-15","2007-05-14"]
["XT_66770","Assemble Subsystem at LLNL- Total Energy","2007-03-05","2007-03-30"]
["XT_66780","AWARD: Vac Hardware - Total Energy","2007-01-25","2007-01-25"]
["XT_667801","Test Subsystem at LLNL - Total Energy","2007-04-02","2007-04-27"]
["XT_667901","Pkg and Ship System to SLAC - Total Energy","2007-04-30","2007-05-11"]
["XT_668","Commission - Far Hall Mech/Vac - H1","2008-02-21","2008-03-05"]
["XT_66801","AVAIL: Total Energy","2007-05-14","2007-05-11"]
["XT_66833","Revise IWS- Total Energy","2006-06-14","2006-06-27"]
["XT_669","COMP:  Far Hall Mech/Vac - H1 Installed & Commis","2008-03-06","2008-03-05"]
["XT_67","Prototype - Testing- Phase I","2006-05-24","2006-06-21"]
["XT_6710","Prototype-Sensor Develop Planning- Total Energy","2005-10-03","2006-01-05"]
["XT_6720","Prototype - Requirements Finalized","2006-01-06","2006-01-05"]
["XT_6730","Sensor Dev-TU Write Scope of Work-Total Energy","2006-01-06","2006-01-20"]
["XT_6740","Sensor Develop-TU SOW Signed - Total Energy","2006-01-23","2006-01-20"]
["XT_6750","Sensor Dev Phase I - TU - Total Energy","2006-01-23","2006-05-15"]
["XT_6760","Sensor Dev Phase II - TU - Total Energy","2006-05-16","2006-08-09"]
["XT_6770","Procure Prototype Pulsed Laser - Total Energy","2006-01-06","2006-02-03"]
["XT_678","Pkg and Ship - FEE Diagnostic Tank","2007-07-24","2007-07-30"]
["XT_6780","Procure Prototype Pulse-tube Cryostat - Total En","2006-01-06","2006-02-03"]
["XT_6789","Design Studies Preliminary Review-Gas Attenuator","2005-11-21","2005-11-23"]
["XT_680","Commission - Near Hall Mech/Vac - H1","2007-08-30","2007-09-27"]
["XT_6800","Prototype Write IWS - Total Energy","2006-01-06","2006-02-03"]
["XT_6810","Prototype Test-Pulse Tube Cryostat -Total Energy","2006-05-16","2006-10-05"]
["XT_6820","Prototype Testing - LN Cryostat - Total Energy","2006-05-16","2006-10-05"]
["XT_68410","Final Design Prep - Total Energy","2006-10-20","2006-11-02"]
["XT_68411","Final Design Review - Total Energy","2006-11-03","2006-11-02"]
["XT_696","Test - Indirect Imager","2007-07-24","2007-08-20"]
["XT_697","COMP:  Indirect Imager Installed & Commissioned","2007-09-05","2007-09-04"]
["XT_70011","REQD: FEE Beneficial Occupancy","2007-05-15","2007-05-14"]
["XT_7022","REQD: FEE Beneficial Occupancy - Fixed Mask","2007-05-15","2007-05-14"]
["XT_704","AVAIL: Indirect Imager","2007-07-24","2007-07-23"]
["XT_710","AVAIL: Near Hall Mech/Vac","2007-08-23","2007-08-22"]
["XT_730","COMP:  Near Hall Mech/Vac - H1","2007-09-28","2007-09-28"]
["XT_7300","Engineering Specification - FEH Mech/Vac","2006-08-31","2006-09-28"]
["XT_7301","Conceptual Design - FEH Mech/Vac","2006-09-29","2006-10-12"]
["XT_7302","Write ESD - FEH Mech/Vac","2006-10-13","2006-11-09"]
["XT_7304","Vacuum Analyses - FEH Mech/Vac","2006-10-13","2006-11-09"]
["XT_7305","Pump Cross  Design - FEH Mech/Vac","2006-10-13","2006-11-13"]
["XT_7306","Prelim Analysis of Stand - FEH Mech/Vac","2006-10-20","2006-10-26"]
["XT_7308","Vacuum Components Defined - FEH Mech/Vac","2006-11-10","2006-11-16"]
["XT_7309","Detail Analysis of Stand - FEH Mech/Vac","2006-11-14","2006-11-29"]
["XT_7313","Vacuum Controls Defined - FEH Mech/Vac","2006-11-17","2006-11-27"]
["XT_7315","Preliminary Design Review - FEH Mech/Vac","2006-11-30","2006-11-29"]
["XT_7316","Write Safety/Ref Note - FEH Mech/Vac","2006-11-30","2006-12-28"]
["XT_7317","Select Vac Hardware Vendor - FEH Mech/Vac","2006-11-30","2006-12-06"]
["XT_7319","Vacuum Valve Design - FEH Mech/Vac","2006-10-13","2006-11-07"]
["XT_732","AWARD: Prototype Material - Total Energy","2006-01-06","2006-04-03"]
["XT_7320","Select Vendor Stands - FEH Mech/Vac","2006-11-30","2006-12-06"]
["XT_7322","Safety/Ref Note 1st Review - FEH Mech/Vac","2006-12-29","2007-01-22"]
["XT_7326","Safety/Ref Note 2nd Review - FEH Mech/Vac","2007-01-23","2007-01-31"]
["XT_7327","Beam Tube Design - FEH Mech/Vac","2006-10-13","2006-10-30"]
["XT_7330","Safety/Ref Note Division Review - FEH Mech/Vac","2007-02-01","2007-02-09"]
["XT_7333","Final Design Review - FEH Mech/Vac","2007-02-27","2007-02-26"]
["XT_7336","Prepare Procure Docs Stands - FEH Mech/Vac","2007-02-27","2007-03-26"]
["XT_7337","Prep Procure Docs Vac Hardware - FEH Mech/Vac","2007-02-27","2007-03-26"]
["XT_7338","Procurement Review Stands - FEH Mech/Vac","2007-03-27","2007-04-02"]
["XT_7339","Procure Review Vac Hardware - FEH Mech/Vac","2007-03-27","2007-04-02"]
["XT_7340","AWARD: Contract Stands - FEH Mech/Vac","2007-04-03","2007-04-03"]
["XT_7341","AWARD: Vac Hardware - FEH Mech/Vac","2007-04-03","2007-04-03"]
["XT_7342","Order & Receive Vac Hardware - FEH Mech/Vac","2007-04-04","2007-08-23"]
["XT_7343","Order & Receive Stands - FEH Mech/Vac","2007-04-04","2007-08-23"]
["XT_7344","Component Accept Test Vac Hardware-FEH Mech/Vac","2007-08-24","2007-08-30"]
["XT_7345","REQD:  FEH Beneficial Occup - Mech/Vac","2007-08-21","2007-08-20"]
["XT_7346","Prepare Install Plan - FEH Mech/Vac","2007-08-21","2007-12-13"]
["XT_7356","Assemble Subsystem at LLNL- FEH Mech/Vac","2007-08-31","2007-10-26"]
["XT_736","Commission - Direct Imager","2007-09-05","2007-09-18"]
["XT_7366","Test Subsystem at LLNL - FEH Mech/Vac","2007-10-29","2007-11-27"]
["XT_7376","Pkg and Ship System to SLAC - FEH Mech/Vac","2007-11-28","2007-11-28"]
["XT_7400","Physics Specification - NEH Mech/Vac","2005-12-01","2006-03-27"]
["XT_7401","Conceptual Design - NEH Mech/Vac","2006-04-25","2006-05-08"]
["XT_7402","Write ESD - NEH Mech/Vac","2006-05-09","2006-06-06"]
["XT_7404","Vacuum Analyses - NEH Mech/Vac","2006-05-09","2006-05-22"]
["XT_7406","Prelim Analysis of Stand - NEH Mech/Vac","2006-05-16","2006-06-13"]
["XT_7408","Vacuum Components Defined - NEH Mech/Vac","2006-05-23","2006-05-30"]
["XT_7409","Detail Analysis of Stand - NEH Mech/Vac","2006-06-14","2006-07-12"]
["XT_7411","Collimator 6 Design - NEH Mech/Vac","2006-06-21","2006-08-16"]
["XT_7412","Collimator 5 Design  - NEH Mech/Vac","2006-06-19","2006-06-20"]
["XT_7413","Vacuum Controls Defined - NEH Mech/Vac","2006-05-31","2006-06-06"]
["XT_7414","Pump Cross Design - NEH Mech/Vac","2006-05-23","2006-06-06"]
["XT_7415","Preliminary Design Review - NEH Mech/Vac","2006-07-13","2006-07-12"]
["XT_7416","Write Safety/Ref Note - NEH Mech/Vac","2006-07-13","2006-08-09"]
["XT_7417","Select Vac Hardware Vendor - NEH Mech/Vac","2006-07-13","2006-10-05"]
["XT_7420","Select Vendor Stands - NEH Mech/Vac","2006-07-13","2006-10-05"]
["XT_7422","Safety/Ref Note 1st Review - NEH Mech/Vac","2006-08-10","2006-08-30"]
["XT_7426","Safety/Ref Note 2nd Review - NEH Mech/Vac","2006-08-31","2006-09-11"]
["XT_7428","Vacuum Valve Design - NEH Mech/Vac","2006-06-07","2006-06-13"]
["XT_7430","Safety/Ref Note Division Review - NEH Mech/Vac","2006-09-12","2006-09-20"]
["XT_7433","Final Design Review - NEH Mech/Vac","2006-09-21","2006-09-20"]
["XT_7435","Beam Tube Spt  Design - NEH Mech/Vac","2006-06-14","2006-06-16"]
["XT_7436","Prepare Procure Docs Stands - NEH Mech/Vac","2006-10-02","2006-11-28"]
["XT_7437","Prep Procure Docs Vac Hardware - NEH Mech/Vac","2006-10-02","2006-11-28"]
["XT_7438","Procurement Review Stands - NEH Mech/Vac","2006-11-29","2006-12-05"]
["XT_7439","Procure Review Vac Hardware - NEH Mech/Vac","2006-11-29","2006-12-05"]
["XT_7440","AWARD: Contract Stands - NEH Mech/Vac","2006-12-06","2006-12-06"]
["XT_7441","AWARD: Vac Hardware - NEH Mech/Vac","2006-12-06","2006-12-06"]
["XT_7442","Order & Receive Vac Hardware - NEH Mech/Vac","2006-12-07","2007-05-01"]
["XT_7443","Order & Receive Stands - NEH Mech/Vac","2006-12-07","2007-05-14"]
["XT_7444","Component Accept Test Vac Hardware-NEH Mech/Vac","2007-05-02","2007-05-08"]
["XT_7445","REQD:  NEH Beneficial Occup - Mech/Vac","2007-06-20","2007-06-19"]
["XT_7446","Assemble subsystem - NEH Mech/Vac","2007-05-15","2007-07-11"]
["XT_7454","Prepare Install Plan - NEH Mech/Vac","2006-10-02","2007-01-26"]
["XT_7456","Test Subsystem at LLNL - NEH Mech/Vac","2007-07-12","2007-08-08"]
["XT_746","Commission - Indirect Imager","2007-08-21","2007-09-04"]
["XT_7462","Write ESD - Tunnel Mech/Vac","2006-01-19","2006-02-01"]
["XT_7464","Vacuum Analyses - Tunnel Mech/Vac","2005-12-05","2005-12-16"]
["XT_7466","Prelim Analysis of Stand - Tunnel Mech/Vac","2005-12-05","2005-12-09"]
["XT_7468","Vacuum Components Defined - Tunnel Mech/Vac","2005-12-19","2005-12-23"]
["XT_7469","Detail Analysis of Stand - Tunnel Mech/Vac","2005-12-12","2006-01-03"]
["XT_7473","Vacuum Controls Defined - Tunnel Mech/Vac","2006-01-03","2006-01-09"]
["XT_7475","Preliminary Design Review - Tunnel Mech/Vac","2005-11-17","2005-11-16"]
["XT_7476","Write Safety/Ref Note - Tunnel Mech/Vac","2006-01-04","2006-02-01"]
["XT_7477","Select Vac Hardware Vendor - Tunnel Mech/Vac","2006-04-14","2006-07-10"]
["XT_7480","Select Vendor Stands - Tunnel Mech/Vac","2006-04-14","2006-07-10"]
["XT_7481","Pump Cross Design  - Tunnel Mech/Vac","2005-12-05","2006-01-03"]
["XT_7482","Safety/Ref Note 1st Review - Tunnel Mech/Vac","2006-02-02","2006-02-15"]
["XT_7486","Safety/Ref Note 2nd Review - Tunnel Mech/Vac","2006-02-16","2006-03-02"]
["XT_7488","Vacuum Valve Design - Tunnel Mech/Vac","2006-01-04","2006-02-01"]
["XT_7490","Safety/Ref Note SLAC Review - Tunnel Mech/Va","2006-03-03","2006-03-16"]
["XT_7493","Final Design Review - Tunnel Mech/Vac","2006-04-14","2006-04-13"]
["XT_7495","Beam Tube Design  - Tunnel Mech/V","2006-02-02","2006-03-16"]
["XT_7496","Prepare Procure Docs Stands - Tunnel Mech/Vac","2006-04-14","2006-09-29"]
["XT_7497","Prep Procure Docs Vac Hardware - Tunnel Mech/Vac","2006-04-14","2006-09-29"]
["XT_7498","Procurement Review Stands - Tunnel Mech/Vac","2006-10-02","2007-01-26"]
["XT_7499","Procure Review Vac Hardware - Tunnel Mech/Vac","2006-10-02","2007-01-26"]
["XT_7500","AWARD: Contract Stands - Tunnel Mech/Vac","2007-01-30","2007-01-30"]
["XT_7501","AWARD: Vac Hardware - Tunnel Mech/Vac","2007-01-29","2007-01-29"]
["XT_7502","Order & Receive Vac Hardware - Tunnel Mech/Vac","2007-01-30","2007-05-22"]
["XT_7503","Order & Receive Stands - Tunnel Mech/Vac","2007-01-30","2007-05-22"]
["XT_7504","Component Accept Test Vac Hardware-Tunnel Mech/V","2007-05-23","2007-05-30"]
["XT_7505","REQD:  Tunnel Beneficial Occup - Mech/Vac","2007-09-10","2007-09-07"]
["XT_7506","Prepare Install Plan - Tunnel Mech/Vac","2006-03-17","2006-06-09"]
["XT_7514","Pkg and Ship to SLAC - NEH Mech/Vac","2007-08-09","2007-08-22"]
["XT_7516","Assemble Subsystem - Tunnel Mech/Vac","2007-05-31","2007-07-26"]
["XT_7526","Test Subsystem at LLNL - Tunnel Mech/Vac","2007-07-27","2007-08-23"]
["XT_753","Controls Mgt - FY-06","2005-12-02","2006-09-29"]
["XT_7536","Pkg and Ship System to SLAC - Tunnel Mech/Vac","2007-08-24","2007-09-07"]
["XT_7741","COMP: Design - Comm Diagnostic Tank","2007-02-09","2007-02-08"]
["XT_7742","Prep Bid Pkg Tank - Comm Diagnostic Tank","2007-02-09","2007-02-15"]
["XT_7751","Bid Process Tank - Comm Diagnostic Tank","2007-02-16","2007-03-16"]
["XT_7759","AWARD: Contract Tank - Comm Diagnostic Tank","2007-03-19","2007-03-19"]
["XT_7767","Vendor Fab/Ship Tank - Comm Diagnostic Tank","2007-03-20","2007-06-12"]
["XT_7775","Assemble - Comm Diagnostic Tank","2007-06-13","2007-09-06"]
["XT_7776","RECV:  Tank - Comm Diagnostic Tank","2007-06-13","2007-06-12"]
["XT_7780","Design Studies-Internal Review 2-Gas Attenuator","2005-11-21","2005-11-18"]
["XT_7793","REQD: Near Hall Beneficial Occup -Comm Diag Tank","2007-09-07","2007-09-07"]
["XT_78202","EPICs Controls Design I - FY-06","2005-12-02","2006-04-11"]
["XT_78203","Global - EPICS - FY-07","2006-10-02","2007-09-28"]
["XT_7821","Leak Check Test","2008-03-14","2008-05-08"]
["XT_7822","Test Beam Line","2008-05-09","2008-07-07"]
["XT_7825","COMP:  Beam Line Test","2008-07-08","2008-07-07"]
["XT_7880","Accept Test - Total Energy","2007-02-26","2007-03-02"]
["XT_789","Sensor Test & Prototype Optimization-Total Energ","2006-01-06","2006-06-27"]
["XT_7890","Management - Commission Coordinator - FY-06","2005-11-01","2006-09-29"]
["XT_8","COMP:  FEE Mechanical/Vacuum Installed & Commiss","2007-12-13","2007-12-12"]
["XT_800","Test Beam Line - Slit/Collimator","2007-07-12","2007-08-22"]
["XT_8002","Commission - Slit/Collimator A","2007-08-23","2007-10-18"]
["XT_801","COMP:  Slit/Collimator","2007-10-19","2007-10-18"]
["XT_810","Install - Slit/Collimator","2007-05-15","2007-07-11"]
["XT_8765","AWARD: Electronics & Cables - Motors","2006-10-30","2007-02-08"]
["XT_9620","Management & Oversight - FY-06","2005-10-03","2006-09-29"]
["XT_9621","Management - Safety - FY-06","2005-10-03","2006-09-29"]
["XT_9622","Management - Mech/Vac - FY-06","2005-10-03","2006-09-29"]
["XT_9623","Management & Oversight - FY-07","2006-10-02","2007-09-28"]
["XT_9624","Management - Safety - FY-07","2006-10-02","2007-09-28"]
["XT_9625","Management - Mech/Vac - FY-07","2006-10-02","2007-09-28"]
["XT_9626","Management & Oversight - FY-08","2007-10-01","2008-09-30"]
["XT_9627","Management - Safety - FY-08","2007-10-01","2008-09-30"]
["XT_9628","Management - Mech/Vac - FY-08","2007-10-01","2008-09-30"]
["XT_9629","Management & Oversight - FY-09","2008-10-01","2009-03-31"]
["XT_9630","Management - Safety - FY-09","2008-10-01","2009-03-31"]
["XT_9631","Management - Mech/Vac - FY-09","2008-10-01","2009-03-31"]
["XT_9640","Prepare Bid Pkg Electronics - Motors","2006-10-02","2006-10-13"]
["XT_9641","Bid Process Electronics - Motors","2006-10-16","2006-10-27"]
["XT_9642","Vendor Fab/Ship Electronics - Motors","2006-10-30","2007-02-08"]
["XT_9643","RECV: Electronics - Motors","2007-02-09","2007-02-08"]
["XT_97","Commission - Electron Dump Mech/Vac","2008-02-27","2008-03-25"]
["XT_9806","RECV: Vacuum System - Slit/Collimator Stand","2007-01-31","2007-01-30"]
["XT_9813","RECV: Vacuum System - Slit/Collimator Enclosure","2007-01-31","2007-01-30"]
["XT_9832","Design - Slit/Collimator","2006-05-22","2006-07-18"]
["XT_9850","Prepare Bid Pkg - EPICS Tools","2006-10-02","2006-10-06"]
["XT_9851","Bid Process - EPICS Tools","2006-10-09","2006-10-13"]
["XT_9852","Vendor Fab/Ship - EPICS Tools","2006-10-17","2006-11-13"]
["XT_9853","RECV: EPICS Tools","2006-11-14","2006-11-13"]
["XT_9860","Specification - Motors","2006-04-12","2006-06-07"]
["XT_9861","Design I - Motors","2006-06-08","2006-08-03"]
["XT_9862","COMP:  Design - Motors","2006-10-02","2006-09-29"]
["XT_9863","Prepare Bid Pkg Cables - Motors","2006-10-02","2006-10-13"]
["XT_9864","Bid Process Cables - Motors","2006-10-16","2006-10-27"]
["XT_9865","Vendor Fab/Ship Cables - Motors","2006-10-30","2007-02-08"]
["XT_9866","RECV: Cables - Motors","2007-02-09","2007-02-08"]
["XT_9867","Assemble FEE - Motors","2007-02-09","2007-03-09"]
["XT_9868","Assemble Near Hall -  Motors","2007-02-09","2007-03-09"]
["XT_9869","Assemble Far Hall - Motors","2007-02-09","2007-03-09"]
["XT_987","Physics Requirements Document - Total Energy","2006-03-30","2006-03-29"]
["XT_9870","Programming FEE - Motors","2007-03-12","2007-04-06"]
["XT_9871","Programming Near Hall - Motors","2007-03-12","2007-04-06"]
["XT_9872","Programming Far Hall - Motors","2007-03-12","2007-04-06"]
["XT_9873","REQD: Near Hall Beneficial Occup - Motors","2007-06-20","2007-06-19"]
["XT_9874","REQD: FEE Beneficial Occup - Motors","2007-05-15","2007-05-14"]
["XT_9875","REQD: Far Hall Beneficial Occup - Motors","2007-08-21","2007-08-20"]
["XT_991","Specification - FEE Diagnostic Tank","2006-10-17","2006-10-30"]
["XT_992","Design - FEE Diagnostic Tank","2006-10-31","2007-01-11"]
["XT_994","Assemble - FEE Diagnostic Tank","2007-05-23","2007-06-06"]
["XT_995","Install - FEE Diagnostic Tank","2007-07-31","2007-10-23"]
["XT_996","Test - FEE Diagnostic Tank","2007-10-24","2007-11-20"]
["XT_997","COMP:  FEE Diagnostic Tank","2007-12-07","2007-12-06"]
["XT_LOE","X-ray LOE Complete","2009-04-01","2009-03-31"]
["XT_M241","Conceptual Design Review - FEE Mech/Vac","2006-04-25","2006-04-24"]
["XT_M245","Final Design Review - FEE Mech/Vac","2006-09-28","2006-09-27"]
["XT_M280","Preliminary Design Review - FEE Mech/Vac","2006-07-06","2006-07-05"]
[]
[null,"Total of 10998 activities selected.",null,null,"Type key: ",null,"0=Task, 1=Independent, 2=Meeting, 3=SM, 4=FM, 5=Hammock, 6=WBS, 7=Topic "]
{"$rows_empty":94}
["XT_7433","Final Design Review - NEH Mech/Vac","2006-09-21","2006-09-20"]
["XT_7435","Beam Tube Spt  Design - NEH Mech/Vac","2006-06-14","2006-06-16"]
["XT_7436","Prepare Procure Docs Stands - NEH Mech/Vac","2006-10-02","2006-11-28"]
["XT_7437","Prep Procure Docs Vac Hardware - NEH Mech/Vac","2006-10-02","2006-11-28"]
["XT_7438","Procurement Review Stands - NEH Mech/Vac","2006-11-29","2006-12-05"]
["XT_7439","Procure Review Vac Hardware - NEH Mech/Vac","2006-11-29","2006-12-05"]
["XT_7440","AWARD: Contract Stands - NEH Mech/Vac","2006-12-06","2006-12-06"]
["XT_7441","AWARD: Vac Hardware - NEH Mech/Vac","2006-12-06","2006-12-06"]
["XT_7442","Order & Receive Vac Hardware - NEH Mech/Vac","2006-12-07","2007-05-01"]
["XT_7443","Order & Receive Stands - NEH Mech/Vac","2006-12-07","2007-05-14"]
["XT_7444","Component Accept Test Vac Hardware-NEH Mech/Vac","2007-05-02","2007-05-08"]
["XT_7445","REQD:  NEH Beneficial Occup - Mech/Vac","2007-06-20","2007-06-19"]
["XT_7446","Assemble subsystem - NEH Mech/Vac","2007-05-15","2007-07-11"]
["XT_7454","Prepare Install Plan - NEH Mech/Vac","2006-10-02","2007-01-26"]
["XT_7456","Test Subsystem at LLNL - NEH Mech/Vac","2007-07-12","2007-08-08"]
["XT_746","Commission - Indirect Imager","2007-08-21","2007-09-04"]
["XT_7462","Write ESD - Tunnel Mech/Vac","2006-01-19","2006-01-25"]
["XT_7464","Vacuum Analyses - Tunnel Mech/Vac","2005-12-05","2005-12-16"]
["XT_7466","Prelim Analysis of Stand - Tunnel Mech/Vac","2005-12-05","2005-12-09"]
["XT_7468","Vacuum Components Defined - Tunnel Mech/Vac","2005-12-19","2005-12-23"]
["XT_7469","Detail Analysis of Stand - Tunnel Mech/Vac","2005-12-12","2006-01-03"]
["XT_7473","Vacuum Controls Defined - Tunnel Mech/Vac","2006-01-03","2006-01-09"]
["XT_7475","Preliminary Design Review - Tunnel Mech/Vac","2005-11-17","2005-11-16"]
["XT_7476","Write Safety/Ref Note - Tunnel Mech/Vac","2006-01-04","2006-02-01"]
["XT_7477","Select Vac Hardware Vendor - Tunnel Mech/Vac","2006-03-10","2006-06-02"]
["XT_7480","Select Vendor Stands - Tunnel Mech/Vac","2006-03-10","2006-06-02"]
["XT_7481","Pump Cross Design  - Tunnel Mech/Vac","2005-12-05","2006-01-03"]
["XT_7482","Safety/Ref Note 1st Review - Tunnel Mech/Vac","2006-02-02","2006-02-08"]
["XT_7486","Safety/Ref Note 2nd Review - Tunnel Mech/Vac","2006-02-09","2006-02-15"]
["XT_7488","Vacuum Valve Design - Tunnel Mech/Vac","2006-01-04","2006-02-01"]
["XT_7490","Safety/Ref Note SLAC Review - Tunnel Mech/Va","2006-02-16","2006-02-23"]
["XT_7493","Final Design Review - Tunnel Mech/Vac","2006-03-10","2006-03-09"]
["XT_7495","Beam Tube Design  - Tunnel Mech/V","2006-02-02","2006-03-02"]
["XT_7496","Prepare Procure Docs Stands - Tunnel Mech/Vac","2006-03-10","2006-06-30"]
["XT_7497","Prep Procure Docs Vac Hardware - Tunnel Mech/Vac","2006-03-10","2006-06-30"]
["XT_7498","Procurement Review Stands - Tunnel Mech/Vac","2006-07-03","2006-10-24"]
["XT_7499","Procure Review Vac Hardware - Tunnel Mech/Vac","2006-07-03","2006-10-24"]
["XT_7500","AWARD: Contract Stands - Tunnel Mech/Vac","2006-10-26","2006-10-26"]
["XT_7501","AWARD: Vac Hardware - Tunnel Mech/Vac","2006-10-25","2006-10-25"]
["XT_7502","Order & Receive Vac Hardware - Tunnel Mech/Vac","2006-10-26","2007-02-22"]
["XT_7503","Order & Receive Stands - Tunnel Mech/Vac","2006-10-26","2007-03-07"]
["XT_7504","Component Accept Test Vac Hardware-Tunnel Mech/V","2007-02-23","2007-03-01"]
["XT_7505","REQD:  Tunnel Beneficial Occup - Mech/Vac","2007-08-06","2007-08-03"]
["XT_7506","Prepare Install Plan - Tunnel Mech/Vac","2006-02-24","2006-05-18"]
["XT_7512","Vendor Fab Vacuum System - Flipper Mirror","2007-06-26","2007-10-17"]
["XT_7514","Pkg and Ship to SLAC - NEH Mech/Vac","2007-08-09","2007-08-22"]
["XT_7516","Assemble Subsystem - Tunnel Mech/Vac","2007-03-08","2007-05-02"]
["XT_7526","Test Subsystem at LLNL - Tunnel Mech/Vac","2007-05-03","2007-05-31"]
["XT_753","Controls Mgt - FY-06","2005-12-02","2006-09-29"]
["XT_7536","Pkg and Ship System to SLAC - Tunnel Mech/Vac","2007-06-01","2007-06-14"]
["XT_754","Design II - Align Cameras Controls","2005-09-22","2005-12-16"]
["XT_77011","Specification - Controls-Direct Imager","2005-05-02","2005-05-27"]
["XT_77012","Specification - Controls-Align Cameras","2005-05-02","2005-05-27"]
["XT_77013","Design I - Controls-Align Cameras","2005-05-31","2005-08-23"]
["XT_77014","COMP:  Design - Controls-Align Cameras","2005-11-17","2005-11-16"]
["XT_77015","Prepare Bid Pkg - Controls-Align Cameras","2005-11-17","2005-12-16"]
["XT_77016","Bid Process - Controls-Align Cameras","2006-01-03","2006-03-01"]
["XT_77017","Vendor Fab/Ship - Controls-Align Cameras","2006-03-02","2006-05-24"]
["XT_77018","RECV:  Controls-Align Cameras","2006-05-25","2006-05-24"]
["XT_77019","Assemble FEE - Controls-Align Cameras","2006-05-25","2006-06-22"]
["XT_77020","Programming FEE - Controls-Align Cameras","2006-06-23","2006-08-18"]
["XT_77021","REQD: FEE Ben Occup - Controls-Align Cameras","2007-05-15","2007-05-14"]
["XT_7741","COMP: Design - Comm Diagnostic Tank","2007-02-09","2007-02-08"]
["XT_7742","Prep Bid Pkg Tank - Comm Diagnostic Tank","2007-02-09","2007-02-15"]
["XT_7751","Bid Process Tank - Comm Diagnostic Tank","2007-02-16","2007-03-16"]
["XT_7759","AWARD: Contract Tank - Comm Diagnostic Tank","2007-03-19","2007-03-19"]
["XT_7767","Vendor Fab/Ship Tank - Comm Diagnostic Tank","2007-03-20","2007-06-12"]
["XT_7775","Assemble - Comm Diagnostic Tank","2007-06-13","2007-09-06"]
["XT_7776","RECV:  Tank - Comm Diagnostic Tank","2007-06-13","2007-06-12"]
["XT_7780","Design Studies-Internal Review 2-Gas Attenuator","2005-11-21","2005-11-18"]
["XT_77801","AWARD: Contract Vacuum System - Flipper Mirror","2006-10-02","2006-10-06"]
["XT_77885","AWARD: Contract Precision Hardware - Flipper Mir","2007-06-26","2007-07-02"]
["XT_7789","RECV: Material -Spatial Shape & Centroid Measure","2007-02-15","2007-02-14"]
["XT_778956","Vendor Fab Jaws - Flipper Mirror","2007-06-26","2007-10-17"]
["XT_7793","REQD: Near Hall Beneficial Occup -Comm Diag Tank","2007-09-07","2007-09-07"]
["XT_780","Prepare Bid Pkg -Spatial Shape & Centroid Measur","2006-09-28","2006-10-04"]
["XT_781","Bid Process - Spatial Shape & Centroid Measure","2006-10-05","2006-11-01"]
["XT_7813","Vendor Fab Precision Hardware - Flipper Mirror","2007-06-26","2007-10-17"]
["XT_782","AWARD: Contract - Spatial Shape & Centroid Measu","2006-11-02","2006-11-02"]
["XT_78202","EPICs Controls Design I - FY-06","2005-12-02","2006-04-11"]
["XT_78203","Global - EPICS - FY-07","2006-10-02","2007-09-28"]
["XT_7821","Leak Check - Flipper Mirror","2008-03-14","2008-05-08"]
["XT_7822","Test Beam Line - Flipper Mirror","2008-05-09","2008-07-07"]
["XT_7824","Commission - Flipper Mirror","2008-07-08","2008-10-28"]
["XT_7825","COMP:  Flipper Mirror","2008-10-29","2008-10-28"]
["XT_783","Vendor Fab/Ship - Spatial Shape & Centroid Measu","2006-11-03","2007-02-14"]
["XT_786","Ship to SLAC-Spatial Shape & Centroid Measure","2007-06-11","2007-06-15"]
["XT_787","Unpack and Assemble at SLAC-Spatial Shape & Cent","2007-06-18","2007-06-29"]
["XT_788","AVAIL: Spatial Shape & Centroid Measure","2007-07-02","2007-06-29"]
["XT_7880","Accept Test - Total Energy","2007-02-26","2007-03-02"]
["XT_789","Sensor Test & Prototype Optimization-Total Energ","2006-01-06","2006-06-27"]
["XT_7890","Management - Commission Coordinator - FY-06","2005-11-01","2006-09-29"]
["XT_7955","Procure - Flipper Mirror","2006-04-18","2007-03-30"]
["XT_7956","AWARD: Contract Jaws - Flipper Mirror","2006-10-02","2006-10-06"]
["XT_7957","AWARD: Contract Tank - Flipper Mirror","2006-10-02","2006-10-06"]
["XT_798","REQD: Near Hall Benefic Occup-Spatial & Centroid","2007-07-02","2007-06-29"]
["XT_8","COMP:  FEE Mechanical/Vacuum Installed & Commiss","2008-02-27","2008-02-26"]
["XT_80","Vendor Fab Tank - Flipper Mirror","2007-06-26","2007-10-17"]
["XT_800","Test Beam Line - Slit/Collimator","2007-07-12","2007-08-22"]
["XT_8002","Commission - Slit/Collimator A","2007-08-23","2007-10-18"]
["XT_801","COMP:  Slit/Collimator","2007-10-19","2007-10-18"]
["XT_810","Install - Slit/Collimator","2007-05-15","2007-07-11"]
["XT_854","Design II - Ion Chamber Controls","2005-09-22","2005-12-16"]
["XT_8765","AWARD: Electronics & Cables - Motors","2006-10-30","2007-02-08"]
["XT_88","RECV: Flipper Mirror","2007-10-18","2007-10-17"]
["XT_899","Assemble -Spatial Shape & Centroid Measure","2007-02-15","2007-06-08"]
["XT_92","Assemble - Flipper Mirror","2007-10-18","2008-03-13"]
["XT_9601","Specification - Spectrometer Controls","2005-05-02","2005-06-27"]
["XT_9602","Design I - Spectrometer Controls","2005-06-28","2005-09-21"]
["XT_9603","COMP:  Design - Spectrometer Controls","2006-01-03","2005-12-16"]
["XT_9604","Prepare Bid Pkg - Spectrometer Controls","2006-01-03","2006-01-31"]
["XT_9605","Bid Process - Spectrometer Controls","2006-02-01","2006-03-29"]
["XT_9606","Vendor Fab/Ship - Spectrometer Controls","2006-03-30","2006-08-18"]
["XT_9607","RECV: Spectrometer Controls","2006-08-21","2006-08-18"]
["XT_9608","Assemble FEE - Spectrometer Controls","2006-08-21","2006-09-18"]
["XT_9611","Programming FEE - Spectrometer Controls","2006-09-19","2006-11-13"]
["XT_9620","Management & Oversight - FY-06","2005-10-03","2006-09-29"]
["XT_9621","Management - Safety - FY-06","2005-10-03","2006-09-29"]
["XT_9622","Management - Mech/Vac - FY-06","2005-10-03","2006-09-29"]
["XT_9623","Management & Oversight - FY-07","2006-10-02","2007-09-28"]
["XT_9624","Management - Safety - FY-07","2006-10-02","2007-09-28"]
["XT_9625","Management - Mech/Vac - FY-07","2006-10-02","2007-09-28"]
["XT_9626","Management & Oversight - FY-08","2007-10-01","2008-09-30"]
["XT_9627","Management - Safety - FY-08","2007-10-01","2008-09-30"]
["XT_9628","Management - Mech/Vac - FY-08","2007-10-01","2008-09-30"]
["XT_9629","Management & Oversight - FY-09","2008-10-01","2009-03-31"]
["XT_9630","Management - Safety - FY-09","2008-10-01","2009-03-31"]
["XT_9631","Management - Mech/Vac - FY-09","2008-10-01","2009-03-31"]
["XT_9640","Prepare Bid Pkg Electronics - Motors","2006-10-02","2006-10-13"]
["XT_9641","Bid Process Electronics - Motors","2006-10-16","2006-10-27"]
["XT_9642","Vendor Fab/Ship Electronics - Motors","2006-10-30","2007-02-08"]
["XT_9643","RECV: Electronics - Motors","2007-02-09","2007-02-08"]
["XT_9644","Prepare Bid Pkg Electronics - Vacuum Controls","2006-01-03","2006-01-09"]
["XT_9645","Bid Process Electronics - Vacuum Controls","2006-01-10","2006-02-07"]
["XT_9646","Vendor Fab/Ship Electronics - Vacuum Controls","2006-02-09","2006-03-09"]
["XT_9647","RECV: Electronics - Vacuum Controls","2006-03-10","2006-03-09"]
["XT_97","Commission - Electron Dump Mech/Vac","2008-02-27","2008-03-25"]
["XT_9806","RECV: Vacuum System - Slit/Collimator Stand","2007-01-31","2007-01-30"]
["XT_9813","RECV: Vacuum System - Slit/Collimator Enclosure","2007-01-31","2007-01-30"]
["XT_9832","Design - Slit/Collimator","2006-05-22","2006-07-18"]
["XT_9850","Prepare Bid Pkg - EPICS Tools","2006-10-02","2006-10-06"]
["XT_9851","Bid Process - EPICS Tools","2006-10-09","2006-10-13"]
["XT_9852","Vendor Fab/Ship - EPICS Tools","2006-10-17","2006-11-13"]
["XT_9853","RECV: EPICS Tools","2006-11-14","2006-11-13"]
["XT_9860","Specification - Motors","2006-04-12","2006-06-07"]
["XT_9861","Design I - Motors","2006-06-08","2006-08-03"]
["XT_9862","COMP:  Design - Motors","2006-10-02","2006-09-29"]
["XT_9863","Prepare Bid Pkg Cables - Motors","2006-10-02","2006-10-13"]
["XT_9864","Bid Process Cables - Motors","2006-10-16","2006-10-27"]
["XT_9865","Vendor Fab/Ship Cables - Motors","2006-10-30","2007-02-08"]
["XT_9866","RECV: Cables - Motors","2007-02-09","2007-02-08"]
["XT_9867","Assemble FEE - Motors","2007-02-09","2007-03-09"]
["XT_9868","Assemble Near Hall -  Motors","2007-02-09","2007-03-09"]
["XT_9869","Assemble Far Hall - Motors","2007-02-09","2007-03-09"]
["XT_987","Physics Requirements Document - Total Energy","2006-03-30","2006-03-29"]
["XT_9870","Programming FEE - Motors","2007-03-12","2007-04-06"]
["XT_9871","Programming Near Hall - Motors","2007-03-12","2007-04-06"]
["XT_9872","Programming Far Hall - Motors","2007-03-12","2007-04-06"]
["XT_9873","REQD: Near Hall Beneficial Occup - Motors","2007-06-20","2007-06-19"]
["XT_9874","REQD: FEE Beneficial Occup - Motors","2007-05-15","2007-05-14"]
["XT_9875","REQD: Far Hall Beneficial Occup - Motors","2007-08-21","2007-08-20"]
["XT_9876","Specification - Vacuum Controls Gauges","2005-05-02","2005-06-27"]
["XT_9877","Design I - Vacuum Controls","2005-06-28","2005-09-21"]
["XT_9878","COMP:  Design - Vacuum Controls","2006-01-03","2005-12-16"]
["XT_9879","Prepare Bid Pkg Cables - Vacuum Controls","2006-01-03","2006-01-09"]
["XT_9880","Bid Process Cables - Vacuum Controls","2006-01-10","2006-02-07"]
["XT_9881","Vendor Fab/Ship Cables - Vacuum Controls","2006-02-08","2006-03-08"]
["XT_9882","RECV: Cables - Vacuum Controls","2006-03-09","2006-03-08"]
["XT_9883","Assemble FEE - Vacuum Controls","2006-03-10","2006-04-06"]
["XT_9884","Assemble Near Hall - Vacuum Controls","2006-03-10","2006-04-06"]
["XT_9885","Assemble Far Hall - Vacuum Controls","2006-03-10","2006-04-06"]
["XT_9886","Programming FEE - Vacuum Controls","2006-04-07","2006-05-04"]
["XT_9887","Programming Near Hall - Vacuum Controls","2006-04-07","2006-05-04"]
["XT_9888","Programming Far Hall - Vacuum Controls","2006-04-07","2006-05-04"]
["XT_9889","REQD: Near Hall Beneficial Occup - Vacuum Contro","2007-06-20","2007-06-19"]
["XT_9890","REQD: FEE Beneficial Occup - Vacuum Controls","2007-05-15","2007-05-14"]
["XT_9891","REQD: Far Hall Beneficial Occup - Vacuum Control","2007-08-21","2007-08-20"]
["XT_991","Specification - FEE Diagnostic Tank","2006-10-17","2006-10-30"]
["XT_992","Design - FEE Diagnostic Tank","2006-10-31","2007-01-11"]
["XT_994","Assemble - FEE Diagnostic Tank","2007-05-23","2007-06-06"]
["XT_995","Install - FEE Diagnostic Tank","2007-07-31","2007-10-23"]
["XT_996","Test - FEE Diagnostic Tank","2007-10-24","2007-11-20"]
["XT_997","COMP:  FEE Diagnostic Tank","2007-12-07","2007-12-06"]
["XT_LOE","X-ray LOE Complete","2009-04-01","2009-03-31"]
["XT_M241","Conceptual Design Review - FEE Mech/Vac","2006-04-25","2006-04-24"]
["XT_M245","Final Design Review - FEE Mech/Vac","2006-09-28","2006-09-27"]
["XT_M280","Preliminary Design Review - FEE Mech/Vac","2006-07-06","2006-07-05"]
[]
[null,"Total of 11281 activities selected.",null,null,"Type key: ",null,"0=Task, 1=Independent, 2=Meeting, 3=SM, 4=FM, 5=Hammock, 6=WBS, 7=Topic "]
{"$rows_empty":192}
["XT_7366","Test Subsystem at LLNL - FEH Mech/Vac","2007-10-25","2007-11-21"]
["XT_7376","Pkg and Ship System to SLAC - FEH Mech/Vac","2007-11-26","2007-11-26"]
["XT_7400","Engineering Specification - NEH Mech/Vac","2005-11-30","2006-01-11"]
["XT_7401","Conceptual Design - NEH Mech/Vac","2006-01-12","2006-01-26"]
["XT_7402","Write ESD - NEH Mech/Vac","2006-01-27","2006-02-24"]
["XT_7403","Collimator 5 Primary Design - NEH Mech/Vac","2006-03-13","2006-03-21"]
["XT_7404","Vacuum Analyses - NEH Mech/Vac","2006-01-27","2006-02-09"]
["XT_7405","Pump Cross Primary Design - NEH Mech/Vac","2006-03-13","2006-04-11"]
["XT_7406","Prelim Analysis of Stand - NEH Mech/Vac","2006-02-03","2006-02-09"]
["XT_7407","Collimator 5 Detail Design - NEH Mech/Vac","2006-03-22","2006-03-28"]
["XT_7408","Vacuum Components Defined - NEH Mech/Vac","2006-02-10","2006-02-16"]
["XT_7409","Detail Analysis of Stand - NEH Mech/Vac","2006-04-12","2006-05-02"]
["XT_7410","Collimator 5 Design Check - NEH Mech/Vac","2006-03-29","2006-03-31"]
["XT_7411","Collimator 6 Primary Design - NEH Mech/Vac","2006-03-29","2006-05-23"]
["XT_7412","Collimator 5 Design Back Check - NEH Mech/Vac","2006-04-03","2006-04-04"]
["XT_7413","Vacuum Controls Defined - NEH Mech/Vac","2006-02-17","2006-02-24"]
["XT_7414","Pump Cross Detail Design - NEH Mech/Vac","2006-04-12","2006-04-25"]
["XT_7415","Preliminary Design Review - NEH Mech/Vac","2006-05-03","2006-05-02"]
["XT_7416","Write Safety/Ref Note - NEH Mech/Vac","2006-05-03","2006-05-31"]
["XT_7417","Select Vac Hardware Vendor - NEH Mech/Vac","2006-05-03","2006-07-27"]
["XT_7418","Pump Cross Design Check - NEH Mech/Vac","2006-04-26","2006-05-01"]
["XT_7419","Vacuum Valve Primary Design - NEH Mech/Vac","2006-04-26","2006-05-19"]
["XT_7420","Select Vendor Stands - NEH Mech/Vac","2006-05-03","2006-07-27"]
["XT_7421","Pump Cross Design Back Check - NEH Mech/Vac","2006-05-02","2006-05-04"]
["XT_7422","Safety/Ref Note 1st Review - NEH Mech/Vac","2006-06-01","2006-06-21"]
["XT_7423","Vacuum Valve Detail Design - NEH Mech/Vac","2006-05-22","2006-06-05"]
["XT_7424","Collimator 6 Detail Design - NEH Mech/Vac","2006-05-24","2006-06-14"]
["XT_7425","Vacuum Valve Design Check - NEH Mech/Vac","2006-06-06","2006-06-09"]
["XT_7426","Safety/Ref Note 2nd Review - NEH Mech/Vac","2006-06-22","2006-06-30"]
["XT_7427","Beam Tube Spt Primary Design - NEH Mech/Vac","2006-06-06","2006-06-21"]
["XT_7428","Vacuum Valve Design Back Check - NEH Mech/Vac","2006-06-12","2006-06-16"]
["XT_7429","Collimator 6 Design Check - NEH Mech/Vac","2006-06-15","2006-06-21"]
["XT_7430","Safety/Ref Note Division Review - NEH Mech/Vac","2006-07-03","2006-07-12"]
["XT_7431","Collimator 6 Design Back Check - NEH Mech/Vac","2006-06-22","2006-06-26"]
["XT_7432","Beam Tube Spt  Detail Design - NEH Mech/Vac","2006-06-22","2006-06-30"]
["XT_7433","Final Design Review - NEH Mech/Vac","2006-07-13","2006-07-12"]
["XT_7434","Beam Tube Spt  Design Check - NEH Mech/Vac","2006-07-03","2006-07-06"]
["XT_7435","Beam Tube Spt  Design Back Check - NEH Mech/Vac","2006-07-07","2006-07-11"]
["XT_7436","Prepare Procure Docs Stands - NEH Mech/Vac","2006-10-02","2006-11-28"]
["XT_7437","Prep Procure Docs Vac Hardware - NEH Mech/Vac","2006-10-02","2006-11-28"]
["XT_7438","Procurement Review Stands - NEH Mech/Vac","2006-11-29","2006-12-05"]
["XT_7439","Procure Review Vac Hardware - NEH Mech/Vac","2006-11-29","2006-12-05"]
["XT_7440","AWARD: Contract Stands - NEH Mech/Vac","2006-12-06","2006-12-06"]
["XT_7441","AWARD: Vac Hardware - NEH Mech/Vac","2006-12-06","2006-12-06"]
["XT_7442","Order & Receive Vac Hardware - NEH Mech/Vac","2006-12-07","2007-05-01"]
["XT_7443","Order & Receive Stands - NEH Mech/Vac","2006-12-07","2007-05-14"]
["XT_7444","Component Accept Test Vac Hardware-NEH Mech/Vac","2007-05-02","2007-05-08"]
["XT_7445","REQD:  NEH Beneficial Occup - Mech/Vac","2007-04-03","2007-04-02"]
["XT_7446","Assemble subsystem - NEH Mech/Vac","2007-05-15","2007-07-11"]
["XT_7454","Prepare Install Plan - NEH Mech/Vac","2006-10-02","2007-01-26"]
["XT_7456","Test Subsystem at LLNL - NEH Mech/Vac","2007-07-12","2007-08-08"]
["XT_746","Commission - Indirect Imager","2007-08-07","2007-08-20"]
["XT_7461","Conceptual Design - Tunnel Mech/Vac","2005-10-03","2005-10-14"]
["XT_7462","Write ESD - Tunnel Mech/Vac","2005-10-17","2005-11-11"]
["XT_7464","Vacuum Analyses - Tunnel Mech/Vac","2005-10-17","2005-10-28"]
["XT_7465","Pump Cross Primary Design - Tunnel Mech/Vac","2005-10-17","2005-11-15"]
["XT_7466","Prelim Analysis of Stand - Tunnel Mech/Vac","2005-10-24","2005-10-28"]
["XT_7468","Vacuum Components Defined - Tunnel Mech/Vac","2005-10-31","2005-11-04"]
["XT_7469","Detail Analysis of Stand - Tunnel Mech/Vac","2005-10-24","2005-11-11"]
["XT_7473","Vacuum Controls Defined - Tunnel Mech/Vac","2005-11-07","2005-11-11"]
["XT_7474","Pump Cross Detail Design - Tunnel Mech/Vac","2005-11-16","2005-12-01"]
["XT_7475","Preliminary Design Review - Tunnel Mech/Vac","2005-11-14","2005-11-11"]
["XT_7476","Write Safety/Ref Note - Tunnel Mech/Vac","2005-12-07","2006-01-05"]
["XT_7477","Select Vac Hardware Vendor - Tunnel Mech/Vac","2005-11-14","2006-02-10"]
["XT_7478","Pump Cross Design Check - Tunnel Mech/Vac","2005-12-02","2005-12-07"]
["XT_7479","Vacuum Valve Primary Design - Tunnel Mech/Vac","2005-12-02","2005-12-28"]
["XT_7480","Select Vendor Stands - Tunnel Mech/Vac","2005-11-14","2006-02-24"]
["XT_7481","Pump Cross Design Back Check - Tunnel Mech/Vac","2005-12-08","2005-12-12"]
["XT_7482","Safety/Ref Note 1st Review - Tunnel Mech/Vac","2006-01-06","2006-01-27"]
["XT_7483","Vacuum Valve Detail Design - Tunnel Mech/Vac","2005-12-29","2006-01-12"]
["XT_7485","Vacuum Valve Design Check - Tunnel Mech/Vac","2006-01-13","2006-01-19"]
["XT_7486","Safety/Ref Note 2nd Review - Tunnel Mech/Vac","2006-01-30","2006-02-07"]
["XT_7487","Beam Tube Spt Primary Design - Tunnel Mech/Vac","2006-01-13","2006-01-31"]
["XT_7488","Vacuum Valve Design Back Check - Tunnel Mech/Vac","2006-01-20","2006-01-24"]
["XT_7490","Safety/Ref Note Division Review - Tunnel Mech/Va","2006-02-08","2006-02-16"]
["XT_7492","Beam Tube Spt  Detail Design - Tunnel Mech/Vac","2006-02-01","2006-02-09"]
["XT_7493","Final Design Review - Tunnel Mech/Vac","2006-02-17","2006-02-16"]
["XT_7494","Beam Tube Spt  Design Check - Tunnel Mech/Vac","2006-02-10","2006-02-14"]
["XT_7495","Beam Tube Spt  Design Back Check - Tunnel Mech/V","2006-02-15","2006-02-17"]
["XT_7496","Prepare Procure Docs Stands - Tunnel Mech/Vac","2006-10-02","2006-11-28"]
["XT_7497","Prep Procure Docs Vac Hardware - Tunnel Mech/Vac","2006-10-02","2006-11-28"]
["XT_7498","Procurement Review Stands - Tunnel Mech/Vac","2006-11-29","2006-12-05"]
["XT_7499","Procure Review Vac Hardware - Tunnel Mech/Vac","2006-11-29","2006-12-05"]
["XT_7500","AWARD: Contract Stands - Tunnel Mech/Vac","2006-12-06","2006-12-06"]
["XT_7501","AWARD: Vac Hardware - Tunnel Mech/Vac","2006-12-06","2006-12-06"]
["XT_7502","Order & Receive Vac Hardware - Tunnel Mech/Vac","2006-12-07","2007-05-01"]
["XT_7503","Order & Receive Stands - Tunnel Mech/Vac","2006-12-07","2007-05-14"]
["XT_7504","Component Accept Test Vac Hardware-Tunnel Mech/V","2007-05-02","2007-05-08"]
["XT_7505","REQD:  Tunnel Beneficial Occup - Mech/Vac","2007-08-23","2007-08-22"]
["XT_7506","Prepare Install Plan - Tunnel Mech/Vac","2006-10-02","2007-02-08"]
["XT_7512","Vendor Fab Vacuum System - Flipper Mirror","2008-05-22","2008-06-19"]
["XT_7514","Pkg and Ship to SLAC - NEH Mech/Vac","2007-08-09","2007-08-22"]
["XT_7516","Assemble Subsystem - Tunnel Mech/Vac","2007-05-15","2007-07-11"]
["XT_7526","Test Subsystem at LLNL - Tunnel Mech/Vac","2007-07-12","2007-08-08"]
["XT_7536","Pkg and Ship System to SLAC - Tunnel Mech/Vac","2007-08-09","2007-08-22"]
["XT_76","Commission - Far Hall Mech/Vac - H2","2005-05-02","2005-05-13"]
["XT_76501","Prepare Bid Pkg - IOCs - 2nd set","2007-06-06","2007-07-03"]
["XT_76502","Prepare Bid Pkg - PLCs - 2nd set","2007-06-06","2007-07-03"]
["XT_76503","Bid Process - IOCs - 2nd set","2007-07-05","2007-08-29"]
["XT_76504","Bid Process - PLCs - 2nd set","2007-07-05","2007-08-29"]
["XT_76505","Vendor Fab/Ship - IOCs - 2nd set","2007-08-30","2008-02-07"]
["XT_76506","Vendor Fab/Ship - PLCs - 2nd set","2007-08-30","2008-02-07"]
["XT_76507","RECV: IOCs - 2nd set","2008-02-08","2008-02-07"]
["XT_76508","RECV:  PLCs - 2nd set","2008-02-08","2008-02-07"]
["XT_76509","AWARD: PLCs and IOCs - 2nd set","2007-08-30","2007-08-30"]
["XT_77011","Specification - NFV Camera Controls","2006-07-03","2006-07-31"]
["XT_77012","Specification - WFV Camera Controls","2006-07-03","2006-07-31"]
["XT_77013","Design - WFV Camera Controls","2006-08-01","2006-10-24"]
["XT_77014","COMP:  Design - WFV Camera Controls","2006-10-25","2006-10-24"]
["XT_77015","Prepare Bid Pkg - WFV Camera Controls","2006-10-25","2006-11-21"]
["XT_77016","Bid Process - WFV Camera Controls","2006-11-22","2007-02-05"]
["XT_77017","Vendor Fab/Ship - WFV Camera Controls","2007-02-06","2007-05-01"]
["XT_77018","RECV: WFV Camera Controls","2007-05-02","2007-05-01"]
["XT_77019","Assemble FEE - WFV Camera Controls","2007-05-02","2007-05-30"]
["XT_77020","Programming FEE - WFV Camera Controls","2007-05-31","2007-07-26"]
["XT_77021","REQD: FEE Ben Occup - WFV Camera Controls","2007-07-27","2007-07-26"]
["XT_7741","COMP: Design - Comm Diagnostic Tank","2006-11-02","2006-11-01"]
["XT_7742","Prep Bid Pkg Tank - Comm Diagnostic Tank","2006-11-02","2006-11-08"]
["XT_7743","Prep Bid Pkg Scroll Dry Pump-Comm Diagnostic Tnk","2006-11-02","2006-11-08"]
["XT_7744","Prep Bid Pkg Turbo System - Comm Diagnostic Tank","2006-11-02","2006-11-08"]
["XT_7745","Prep Bid Pkg Imager Stages - Comm Diagnostic Tan","2006-11-02","2006-11-08"]
["XT_7746","Prep Bid Pkg Stand - Comm Diagnostic Tank","2006-11-02","2006-11-08"]
["XT_7747","Prep Bid Pkg Motor Driver - Comm Diagnostic Tank","2006-11-02","2006-11-08"]
["XT_7748","Prep Bid Pkg EPICS IF - Comm Diagnostic Tank","2006-11-02","2006-11-08"]
["XT_7749","Prep Bid Pk 2 Axis Rail Adjus-Comm Diagnostic Ta","2006-11-02","2006-11-08"]
["XT_7751","Bid Process Tank - Comm Diagnostic Tank","2006-11-09","2006-12-08"]
["XT_7752","Bid Process Scroll Dry Pump-Comm Diagnostic Tank","2006-11-09","2006-12-08"]
["XT_7753","Bid Process Turbo System - Comm Diagnostic Tank","2006-11-09","2006-12-08"]
["XT_7754","Bid Process  Imager Stages - Comm Diagnostic Tan","2006-11-09","2006-12-08"]
["XT_7755","Bid Process Stand - Comm Diagnostic Tank","2006-11-09","2006-12-08"]
["XT_7756","Bid Process Motor Driver - Comm Diagnostic Tank","2006-11-09","2006-12-08"]
["XT_7757","Bid Process EPICS IF - Comm Diagnostic Tank","2006-11-09","2006-12-08"]
["XT_7758","Bid Process 2 Axis Rail Adjus-Comm Diagnostic Ta","2006-11-09","2006-12-08"]
["XT_7759","AWARD: Contract Tank - Comm Diagnostic Tank","2006-12-11","2006-12-11"]
["XT_7767","Vendor Fab/Ship Tank - Comm Diagnostic Tank","2006-12-12","2007-03-22"]
["XT_7775","Assemble - Comm Diagnostic Tank","2007-03-23","2007-07-16"]
["XT_7776","RECV:  Tank - Comm Diagnostic Tank","2007-03-23","2007-03-22"]
["XT_7780","Design Studies-Internal Review 2-Gas Attenuator","2006-01-05","2006-01-04"]
["XT_77801","AWARD: Contract Vacuum System - Flipper Mirror","2008-05-15","2008-05-21"]
["XT_77885","AWARD: Contract Precision Hardware - Flipper Mir","2008-05-15","2008-05-21"]
["XT_7789","RECV: Material -Spatial Shape & Centroid Measure","2007-02-15","2007-02-14"]
["XT_778956","Vendor Fab Jaws - Flipper Mirror","2008-05-22","2008-06-19"]
["XT_7793","REQD: Near Hall Beneficial Occup -Comm Diag Tank","2007-07-17","2007-07-17"]
["XT_780","Prepare Bid Pkg -Spatial Shape & Centroid Measur","2006-09-28","2006-10-04"]
["XT_781","Bid Process - Spatial Shape & Centroid Measure","2006-10-05","2006-11-01"]
["XT_7813","Vendor Fab Precision Hardware - Flipper Mirror","2008-05-15","2008-06-12"]
["XT_7814","RECV Jaws - Flipper Mirror","2008-06-20","2008-06-19"]
["XT_7816","RECV Tank - Flipper Mirror","2008-06-20","2008-06-19"]
["XT_7817","Assemble Tank - Flipper Mirror","2008-06-20","2009-04-14"]
["XT_7818","Assemble Electronics - Flipper Mirror","2008-05-15","2009-03-10"]
["XT_7819","Assemble Jaws - Flipper Mirror","2008-06-20","2009-04-14"]
["XT_782","AWARD: Contract - Spatial Shape & Centroid Measu","2006-11-02","2006-11-02"]
["XT_7820","Install - Flipper Mirror","2009-04-15","2009-06-09"]
["XT_78202","Global - EPICS","2005-10-03","2006-09-29"]
["XT_7821","Leak Check - Flipper Mirror","2009-06-10","2009-07-08"]
["XT_7822","Test Beam Line - Flipper Mirror","2009-07-09","2009-08-05"]
["XT_7824","Commission - Flipper Mirror","2009-08-06","2009-11-25"]
["XT_7825","COMP:  Flipper Mirror","2009-11-26","2009-11-25"]
["XT_783","Vendor Fab/Ship - Spatial Shape & Centroid Measu","2006-11-03","2007-02-14"]
["XT_786","Ship to SLAC-Spatial Shape & Centroid Measure","2007-06-11","2007-06-15"]
["XT_787","Unpack and Assemble at SLAC-Spatial Shape & Cent","2007-06-18","2007-06-29"]
["XT_788","AVAIL: Spatial Shape & Centroid Measure","2007-07-02","2007-06-29"]
["XT_7880","Component Accept Test -Total Energy","2007-11-20","2007-11-28"]
["XT_789","Bid Process Tank - Flipper Mirror","2008-04-17","2008-05-14"]
["XT_7890","Management - Commission Coordinator - FY-06","2005-11-01","2006-09-29"]
["XT_7924","Bid Process Electronics - Flipper Mirror","2008-04-17","2008-05-14"]
["XT_7955","Bid Process Precision Hardware - Flipper Mirror","2008-04-17","2008-05-14"]
["XT_7956","AWARD: Contract Jaws - Flipper Mirror","2008-05-15","2008-05-21"]
["XT_7957","AWARD: Contract Tank - Flipper Mirror","2008-05-15","2008-05-21"]
["XT_798","REQD: Near Hall Benefic Occup-Spatial & Centroid","2007-07-02","2007-06-29"]
["XT_8","COMP:  FEE Mechanical/Vacuum Installed & Commiss","2008-02-08","2008-02-07"]
["XT_80","Vendor Fab Tank - Flipper Mirror","2008-05-22","2008-06-19"]
["XT_800","Test Beam Line - Slit/Collimator","2007-08-21","2007-10-02"]
["XT_8002","Commission - Slit/Collimator A","2007-10-03","2007-11-29"]
["XT_801","COMP:  Slit/Collimator","2007-11-30","2007-11-29"]
["XT_810","Install - Slit/Collimator","2007-06-25","2007-08-20"]
["XT_84","Commission - Far Hall Mech/Vac - H3","2005-05-02","2005-05-13"]
["XT_86","RECV Electronics - Flipper Mirror","2008-05-15","2008-05-14"]
["XT_87","RECV Vacuum System - Flipper Mirror","2008-06-20","2008-06-19"]
["XT_8765","AWARD: Electronics & Cables - Motors","2006-08-02","2006-10-25"]
["XT_88","RECV Precision Motion Hardware - Flipper Mirror","2008-06-13","2008-06-12"]
["XT_899","Assemble -Spatial Shape & Centroid Measure","2007-02-15","2007-06-08"]
["XT_90","Assemble Vacuum System - Flipper Mirror","2008-06-20","2009-04-14"]
["XT_92","Assemble Precision Hardware - Flipper Mirror","2008-06-13","2009-04-07"]
["XT_9601","Specification - Spectrometer Controls","2005-10-03","2005-11-29"]
["XT_9602","Design - Spectrometer Controls","2005-11-30","2006-05-05"]
["XT_9603","COMP:  Design - Spectrometer Controls","2006-05-08","2006-05-05"]
["XT_9604","Prepare Bid Pkg - Spectrometer Controls","2006-05-08","2006-06-05"]
["XT_9605","Bid Process - Spectrometer Controls","2006-06-06","2006-08-01"]
["XT_9606","Vendor Fab/Ship - Spectrometer Controls","2006-08-02","2007-01-08"]
["XT_9607","RECV: Spectrometer Controls","2007-01-09","2007-01-08"]
["XT_9608","Assemble FEE - Spectrometer Controls","2007-01-09","2007-02-06"]
["XT_9611","Programming FEE - Spectrometer Controls","2007-02-07","2007-04-04"]
["XT_9615","REQD: FEE Ben Occup - Spectrometer Controls","2007-07-10","2007-07-09"]
["XT_9620","Management & Oversight - FY-06","2005-10-03","2006-09-29"]
["XT_9621","Management - Safety - FY-06","2005-10-03","2006-09-29"]
["XT_9622","Management - Mech/Vac - FY-06","2005-10-03","2006-09-29"]
["XT_9623","Management & Oversight - FY-07","2006-10-02","2007-09-28"]
["XT_9624","Management - Safety - FY-07","2006-10-02","2007-09-28"]
["XT_9625","Management - Mech/Vac - FY-07","2006-10-02","2007-09-28"]
["XT_9626","Management & Oversight - FY-08","2007-10-01","2008-09-30"]
["XT_9627","Management - Safety - FY-08","2007-10-01","2008-09-30"]
["XT_9628","Management - Mech/Vac - FY-08","2007-10-01","2008-09-30"]
["XT_9629","Management & Oversight - FY-09","2008-10-01","2009-03-31"]
["XT_9630","Management - Safety - FY-09","2008-10-01","2009-03-31"]
["XT_9631","Management - Mech/Vac - FY-09","2008-10-01","2009-03-31"]
["XT_9640","Prepare Bid Pkg Electronics - Motors","2006-05-08","2006-06-05"]
["XT_9641","Bid Process Electronics - Motors","2006-06-06","2006-08-01"]
["XT_9642","Vendor Fab/Ship Electronics - Motors","2006-08-02","2006-10-25"]
["XT_9643","RECV: Electronics - Motors","2006-10-26","2006-10-25"]
["XT_9644","Prepare Bid Pkg Electronics - Vacuum Controls","2006-03-13","2006-04-07"]
["XT_9645","Bid Process Electronics - Vacuum Controls","2006-04-10","2006-06-05"]
["XT_9646","Vendor Fab/Ship Electronics - Vacuum Controls","2006-06-07","2006-09-28"]
["XT_9647","RECV: Electronics - Vacuum Controls","2006-09-29","2006-09-28"]
["XT_97","Commission - Electron Dump Mech/Vac","2008-02-08","2008-03-07"]
["XT_9800","Design - Back Check - Slit/Collimator Stand","2006-09-29","2006-10-09"]
["XT_9801","Design - Check - Slit/Collimator Stand","2006-09-05","2006-09-28"]
["XT_9802","Design - Detail - Slit/Collimator Stand","2006-06-27","2006-09-01"]
["XT_9803","Design - Primary - Slit/Collimator Stand","2005-11-21","2006-06-26"]
["XT_9804","Detail Analysis Mechanical-Slit Stand","2006-01-18","2006-04-05"]
["XT_9805","Prep Bid Pk Vac System-Slit/Collimator Stand","2006-10-27","2006-11-02"]
["XT_9806","RECV: Vacuum System - Slit/Collimator Stand","2007-03-16","2007-03-15"]
["XT_9807","Design - Back Check - Slit/Collimator Enclosure","2006-09-29","2006-10-09"]
["XT_9808","Design - Check - Slit/Collimator Enclosure","2006-09-05","2006-09-28"]
["XT_9809","Design - Detail - Slit/Collimator Enclosure","2006-06-27","2006-09-01"]
["XT_9810","Design - Primary - Slit/Collimator Enclosure","2005-11-21","2006-06-26"]
["XT_9811","Detail Analysis Mechanical-Slit Enclosure","2006-01-18","2006-04-05"]
["XT_9812","Prep Bid Pk Vac System-Slit/Collimator Enclosure","2006-10-27","2006-11-02"]
["XT_9813","RECV: Vacuum System - Slit/Collimator Enclosure","2007-03-16","2007-03-15"]
["XT_9815","Prelim Analysis Mechanic-Slit Enclosure","2005-12-14","2006-01-17"]
["XT_9817","Prelim Analysis Mechanic-Slit Stand","2005-12-14","2006-01-17"]
["XT_9830","Prepare Bid Pkg - IOCs - 1st set","2006-10-03","2006-10-30"]
["XT_9831","Bid Process - IOCs - 1st set","2006-10-31","2007-01-11"]
["XT_9832","Vendor Fab/Ship - IOCs - 1st set","2007-01-12","2007-06-05"]
["XT_9833","Prepare Bid Pkg - PLCs - 1st set","2006-10-03","2006-10-30"]
["XT_9834","Bid Process - PLCs - 1st set","2006-10-31","2007-01-11"]
["XT_9835","Vendor Fab/Ship - PLCs - 1st set","2007-01-12","2007-06-05"]
["XT_9850","Prepare Bid Pkg - EPICS Tools","2006-03-13","2006-04-07"]
["XT_9851","Bid Process - EPICS Tools","2006-04-10","2006-05-05"]
["XT_9852","Vendor Fab/Ship - EPICS Tools","2006-10-02","2007-01-10"]
["XT_9853","RECV: EPICS Tools","2007-01-11","2007-01-10"]
["XT_9856","RECV:  PLCs - 1st set","2007-06-06","2007-06-05"]
["XT_9860","Specification - Motors","2005-10-03","2005-11-29"]
["XT_9861","Design - Motors","2005-11-30","2006-05-05"]
["XT_9862","COMP:  Design - Motors","2006-05-08","2006-05-05"]
["XT_9863","Prepare Bid Pkg Cables - Motors","2006-05-08","2006-06-05"]
["XT_9864","Bid Process Cables - Motors","2006-06-06","2006-08-01"]
["XT_9865","Vendor Fab/Ship Cables - Motors","2006-08-02","2006-10-25"]
["XT_9866","RECV: Cables - Motors","2006-10-26","2006-10-25"]
["XT_9867","Assemble FEE - Motors","2006-10-26","2006-11-22"]
["XT_9868","Assemble Near Hall -  Motors","2006-10-26","2006-11-22"]
["XT_9869","Assemble Far Hall - Motors","2006-10-26","2006-11-22"]
["XT_9870","Programming FEE - Motors","2006-11-27","2007-05-02"]
["XT_9871","Programming Near Hall - Motors","2006-11-27","2007-05-02"]
["XT_9872","Programming Far Hall - Motors","2006-11-27","2007-05-02"]
["XT_9873","REQD: Near Hall Beneficial Occup - Motors","2007-05-03","2007-05-02"]
["XT_9874","REQD: FEE Beneficial Occup - Motors","2007-07-10","2007-07-09"]
["XT_9875","REQD: Far Hall Beneficial Occup - Motors","2007-07-26","2007-07-25"]
["XT_9876","Specification - Vacuum Controls Gauges","2005-10-03","2005-11-29"]
["XT_9877","Design - Vacuum Controls","2005-11-30","2006-03-10"]
["XT_9878","COMP:  Design - Vacuum Controls","2006-03-13","2006-03-10"]
["XT_9879","Prepare Bid Pkg Cables - Vacuum Controls","2006-03-13","2006-04-07"]
["XT_9880","Bid Process Cables - Vacuum Controls","2006-04-10","2006-06-05"]
["XT_9881","Vendor Fab/Ship Cables - Vacuum Controls","2006-06-06","2006-09-27"]
["XT_9882","RECV: Cables - Vacuum Controls","2006-09-28","2006-09-27"]
["XT_9883","Assemble FEE - Vacuum Controls","2006-09-29","2006-10-26"]
["XT_9884","Assemble Near Hall - Vacuum Controls","2006-09-29","2006-10-26"]
["XT_9885","Assemble Far Hall - Vacuum Controls","2006-09-29","2006-10-26"]
["XT_9886","Programming FEE - Vacuum Controls","2006-10-27","2007-04-05"]
["XT_9887","Programming Near Hall - Vacuum Controls","2006-10-27","2007-04-05"]
["XT_9888","Programming Far Hall - Vacuum Controls","2006-10-27","2007-04-05"]
["XT_9889","REQD: Near Hall Beneficial Occup - Vacuum Contro","2007-04-06","2007-04-05"]
["XT_9890","REQD: FEE Beneficial Occup - Vacuum Controls","2007-07-10","2007-07-09"]
["XT_9891","REQD: Far Hall Beneficial Occup - Vacuum Control","2007-07-26","2007-07-25"]
["XT_991","Specification - FEE Diagnostic Tank","2006-03-13","2006-05-05"]
["XT_992","Design - FEE Diagnostic Tank","2006-05-08","2006-11-01"]
["XT_994","Assemble - FEE Diagnostic Tank","2007-07-10","2007-11-29"]
["XT_995","Install - FEE Diagnostic Tank","2007-11-30","2008-03-12"]
["XT_996","Test - FEE Diagnostic Tank","2008-03-13","2008-04-09"]
["XT_997","COMP:  FEE Diagnostic Tank","2008-04-24","2008-04-23"]
["XT_LOE","X-ray LOE Complete","2009-04-01","2009-03-31"]
[]
[null,"Total of 11756 activities selected.",null,null,"Type key: ",null,"0=Task, 1=Independent, 2=Meeting, 3=SM, 4=FM, 5=Hammock, 6=WBS, 7=Topic "]
{"$rows_empty":94}
["XT_801","COMP:  Slit/Collimator A","2008-01-07","2008-01-04"]
["XT_805","Install Ion Gauges - NH Mech/Vac - H3","2007-04-18","2007-04-24"]
["XT_81","Assemble - Far Hall Mech/Vac - H3","2008-02-01","2008-02-07"]
["XT_810","Install - Slit/Collimator A","2007-07-16","2007-09-10"]
["XT_82","Install Ion Pumps - Far Hall Mech/Vac - H3","2008-02-08","2008-02-14"]
["XT_84","Commission - Far Hall Mech/Vac - H3","2008-04-21","2008-05-02"]
["XT_85","COMP:  Far Hall Mech/Vac - H3  Installed & Commi","2008-05-05","2008-05-02"]
["XT_86","RECV Electronics - Flipper Mirror","2006-08-09","2006-08-08"]
["XT_87","RECV Vacuum System - Flipper Mirror","2006-11-06","2006-11-03"]
["XT_88","RECV Precision Motion Hardware - Flipper Mirror","2006-11-06","2006-11-03"]
["XT_8842","Prep Bid Pkg Grating - Spectral Measurement","2006-10-02","2006-10-06"]
["XT_8845","Prep Bid Pkg Low Energy - Spectral Measurement","2006-10-02","2006-10-06"]
["XT_8846","Prep Bid Rails & Stages - Spectral Measurement","2006-10-02","2006-10-06"]
["XT_8852","Bid Process Grating - Spectral Measurement","2006-10-09","2006-11-03"]
["XT_8855","Prep Bid Pkg High Energy - Spectral Measurement","2006-10-02","2006-10-06"]
["XT_8856","Bid Process Rails & Stages -Spectral Measurement","2006-10-09","2006-11-03"]
["XT_8862","AWARD: Grating - Spectral Measurement","2006-11-06","2006-11-06"]
["XT_8865","Bid Process Low Energy - Spectral Measurement","2006-10-09","2006-11-03"]
["XT_8866","AWARD: Rails & Stages - Spectral Measurement","2006-11-06","2006-11-06"]
["XT_8872","Vendor Fab Grating - Spectral Measurement","2006-11-07","2007-01-19"]
["XT_8875","AWARD: Low Energy - Spectral Measurement","2006-11-06","2006-11-06"]
["XT_8876","Vendor Fab Rails & Stages - Spectral Measurement","2006-11-07","2007-01-19"]
["XT_8882","RECV: Grating - Spectral Measurement","2007-01-22","2007-01-19"]
["XT_8885","RECV:  Low Energy - Spectral Measurement","2007-01-22","2007-01-19"]
["XT_8886","RECV: Rails & Stages - Spectral Measurement","2007-01-22","2007-01-19"]
["XT_8895","Bid Process - Spectral Measurement","2006-10-09","2006-11-03"]
["XT_89","Procure Vacuum Hardware - Far Hall Mech/Vac","2007-10-11","2007-12-07"]
["XT_8905","AWARD: Contract - Spectral Measurement","2006-11-06","2006-11-06"]
["XT_8915","Vendor Fab High Energy - Spectral Measurement","2006-11-07","2007-02-16"]
["XT_8925","RECV: High Energy - Spectral Measurement","2007-02-20","2007-02-16"]
["XT_8935","Vendor Fab Low Energy - Spectral Measurement","2006-11-07","2007-01-19"]
["XT_899","Assemble -Spatial Shape & Centroid Measure","2007-09-10","2008-01-17"]
["XT_9","Specification - Electron Dump Mech/Vac","2007-10-01","2007-10-12"]
["XT_90","Assemble Vacuum System - Flipper Mirror","2006-11-06","2007-09-05"]
["XT_91","AVAIL: Far Hall Mech/Vac Ready to Install SLAC","2008-02-08","2008-02-07"]
["XT_92","Assemble Precision Hardware - Flipper Mirror","2006-11-06","2007-09-05"]
["XT_94","Assemble Pipe - Electron Dump Mech/Vac","2008-03-24","2008-03-28"]
["XT_95","Install Vacuum Pipe - Electron Dump Mech/Vac","2008-03-31","2008-04-04"]
["XT_96","Test Pipe - Electron Dump Mech/Vac","2008-04-07","2008-04-18"]
["XT_97","Commission - Electron Dump Mech/Vac","2008-04-21","2008-05-16"]
["XT_98","COMP:  Electron Dump Mech/Vac Install & Commissi","2008-05-19","2008-05-16"]
["XT_99","Beam Simulation - FY-05","2005-05-02","2005-11-02"]
["XT_991","Specification - FEE Diagnostic Tank","2007-05-07","2007-07-02"]
["XT_992","Design - FEE Diagnostic Tank","2007-07-03","2008-01-15"]
["XT_993","Procure Computer - FEE Diagnostic Tank","2008-01-16","2008-04-10"]
["XT_994","Assemble - FEE Diagnostic Tank","2008-05-19","2008-10-08"]
["XT_995","Install - FEE Diagnostic Tank","2008-10-09","2009-01-15"]
["XT_996","Test - FEE Diagnostic Tank","2009-01-16","2009-02-12"]
["XT_997","COMP:  FEE Diagnostic Tank","2009-02-27","2009-02-26"]
["XT_LOE","X-ray LOE Complete","2009-03-31","2009-03-30"]
["XT_M1","COMP: Design Package - Electron Dump Mech/Vac","2007-11-12","2007-11-09"]
["XT_M2","COMP: Design Package - FEE Mech/Vac","2006-01-03","2005-12-16"]
[]
[null,"Total of 11904 activities selected.",null,null,"Type key: ",null,"0=Task, 1=Independent, 2=Meeting, 3=SM, 4=FM, 5=Hammock, 6=WBS, 7=Topic "]
{"$rows_empty":128}
["XT_778","COMP:  Near Hall Mech/Vac - H3","2007-06-07","2007-06-07"]
["XT_77801","AWARD: Contract Vacuum System - Flipper Mirror","2006-10-02","2006-10-06"]
["XT_77885","AWARD: Contract Precision Hardware - Flipper Mir","2006-10-02","2006-10-06"]
["XT_7789","RECV: Material -Spatial Shape & Centroid Measure","2007-09-10","2007-09-07"]
["XT_778956","Vendor Fab Jaws - Flipper Mirror","2006-10-09","2006-11-03"]
["XT_7793","REQD: Near Hall Beneficial Occup -Comm Diag Tank","2007-03-21","2007-03-21"]
["XT_78","Specification - Far Hall Mech/Vac - H3","2007-06-19","2007-07-17"]
["XT_780","Prepare Bid Pkg -Spatial Shape & Centroid Measur","2007-05-08","2007-05-14"]
["XT_7801","Procure Production Unit-Total Energy Measurement","2006-10-03","2007-01-11"]
["XT_781","Bid Process - Spatial Shape & Centroid Measure","2007-05-15","2007-06-12"]
["XT_7813","Vendor Fab Precision Hardware - Flipper Mirror","2006-10-09","2006-11-03"]
["XT_7814","RECV Jaws - Flipper Mirror","2006-11-06","2006-11-03"]
["XT_7816","RECV Tank - Flipper Mirror","2006-11-06","2006-11-03"]
["XT_7817","Assemble Tank - Flipper Mirror","2006-11-06","2007-09-05"]
["XT_7818","Assemble Electronics - Flipper Mirror","2006-06-13","2007-04-11"]
["XT_7819","Assemble Jaws - Flipper Mirror","2006-11-06","2007-09-05"]
["XT_782","AWARD: Contract - Spatial Shape & Centroid Measu","2007-06-13","2007-06-13"]
["XT_7820","Install - Flipper Mirror","2007-09-06","2007-10-31"]
["XT_7821","Leak Check - Flipper Mirror","2007-11-01","2007-11-30"]
["XT_7822","Test Beam Line - Flipper Mirror","2007-12-03","2008-01-15"]
["XT_7823","Fab/Assemble/Test - Const $ - Flipper Mirror","2007-09-06","2008-02-13"]
["XT_7824","Commission - Flipper Mirror","2008-01-16","2008-05-08"]
["XT_7825","COMP:  Flipper Mirror","2008-05-09","2008-05-08"]
["XT_783","Vendor Fab/Ship - Spatial Shape & Centroid Measu","2007-06-14","2007-09-07"]
["XT_784","AVAIL: Near Hall Mech/Vac H3","2008-01-22","2008-01-18"]
["XT_785","Install Ion Pumps - NH Mech/Vac - H3","2007-04-18","2007-04-24"]
["XT_786","Ship to SLAC-Spatial Shape & Centroid Measure","2008-01-18","2008-01-25"]
["XT_787","Unpack and Assemble at SLAC-Spatial Shape & Cent","2008-01-28","2008-02-08"]
["XT_788","AVAIL: Spatial Shape & Centroid Measure","2008-02-11","2008-02-08"]
["XT_789","Bid Process Tank - Flipper Mirror","2006-05-15","2006-06-12"]
["XT_79","Design - Far Hall Mech/Vac - H3","2007-07-18","2007-10-10"]
["XT_7924","Bid Process Electronics - Flipper Mirror","2006-05-15","2006-06-12"]
["XT_7955","Bid Process Precision Hardware - Flipper Mirror","2006-05-15","2006-06-12"]
["XT_7956","AWARD: Contract Jaws - Flipper Mirror","2006-10-02","2006-10-06"]
["XT_7957","AWARD: Contract Tank - Flipper Mirror","2006-10-02","2006-10-06"]
["XT_798","REQD: Near Hall Benefic Occup-Spatial & Centroid","2008-02-11","2008-02-08"]
["XT_8","COMP:  FEE Mechanical/Vacuum Installed & Commiss","2008-03-04","2008-03-03"]
["XT_80","Vendor Fab Tank - Flipper Mirror","2006-10-09","2006-11-03"]
["XT_800","Test Beam Line - Slit/Collimator A","2007-07-30","2007-09-10"]
["XT_8000","Prep Bid Package Vacuum - Near Hall Optics Tank","2007-02-09","2007-02-23"]
["XT_8001","Bid Process Tank - Near Hall Optics Tank","2007-02-26","2007-03-23"]
["XT_8002","Commission - Slit/Collimator A","2007-09-11","2007-11-05"]
["XT_8003","Vendor Fab/Ship Tank - Near Hall Optics Tank","2007-03-27","2007-05-21"]
["XT_8004","AWARD: Contract Tank - Near Hall Optics Tank","2007-03-26","2007-03-26"]
["XT_8007","RECV: Tank - Near Hall Optics Tank","2007-05-22","2007-05-21"]
["XT_801","COMP:  Slit/Collimator A","2008-01-03","2008-01-02"]
["XT_805","Install Ion Gauges - NH Mech/Vac - H3","2007-04-18","2007-04-24"]
["XT_81","Assemble - Far Hall Mech/Vac - H3","2008-02-01","2008-02-07"]
["XT_810","Install - Slit/Collimator A","2007-04-19","2007-06-14"]
["XT_815","Install Stands - NH Mech/Vac - H3","2007-04-18","2007-04-24"]
["XT_82","Install Ion Pumps - Far Hall Mech/Vac - H3","2008-02-08","2008-02-14"]
["XT_820","Fab/Assemble/Test - Const $ - Slit/Col","2007-07-26","2008-01-02"]
["XT_83","Test - Far Hall Mech/Vac - H3","2008-04-21","2008-05-02"]
["XT_84","Commission - Far Hall Mech/Vac - H3","2008-05-05","2008-05-16"]
["XT_85","COMP:  Far Hall Mech/Vac - H3  Installed & Commi","2008-05-19","2008-05-16"]
["XT_86","RECV Electronics - Flipper Mirror","2006-06-13","2006-06-12"]
["XT_87","RECV Vacuum System - Flipper Mirror","2006-11-06","2006-11-03"]
["XT_88","RECV Precision Motion Hardware - Flipper Mirror","2006-11-06","2006-11-03"]
["XT_8842","Prep Bid Pkg Grating - Spectral Measurement","2006-10-02","2006-10-06"]
["XT_8845","Prep Bid Pkg Low Energy - Spectral Measurement","2006-10-02","2006-10-06"]
["XT_8846","Prep Bid Rails & Stages - Spectral Measurement","2006-10-02","2006-10-06"]
["XT_8852","Bid Process Grating - Spectral Measurement","2006-10-09","2006-11-03"]
["XT_8855","Prep Bid Pkg High Energy - Spectral Measurement","2006-10-02","2006-10-06"]
["XT_8856","Bid Process Rails & Stages -Spectral Measurement","2006-10-09","2006-11-03"]
["XT_8862","AWARD: Grating - Spectral Measurement","2006-11-06","2006-11-06"]
["XT_8865","Bid Process Low Energy - Spectral Measurement","2006-10-09","2006-11-03"]
["XT_8866","AWARD: Rails & Stages - Spectral Measurement","2006-11-06","2006-11-06"]
["XT_8872","Vendor Fab Grating - Spectral Measurement","2006-11-07","2007-01-19"]
["XT_8875","AWARD: Low Energy - Spectral Measurement","2006-11-06","2006-11-06"]
["XT_8876","Vendor Fab Rails & Stages - Spectral Measurement","2006-11-07","2007-01-19"]
["XT_8882","RECV: Grating - Spectral Measurement","2007-01-22","2007-01-19"]
["XT_8885","RECV:  Low Energy - Spectral Measurement","2007-01-22","2007-01-19"]
["XT_8886","RECV: Rails & Stages - Spectral Measurement","2007-01-22","2007-01-19"]
["XT_8895","Bid Process - Spectral Measurement","2006-10-09","2006-11-03"]
["XT_89","Procure Vacuum Hardware - Far Hall Mech/Vac","2007-10-11","2007-12-07"]
["XT_8905","AWARD: Contract - Spectral Measurement","2006-11-06","2006-11-06"]
["XT_8915","Vendor Fab High Energy - Spectral Measurement","2006-11-07","2007-02-16"]
["XT_8925","RECV: High Energy - Spectral Measurement","2007-02-20","2007-02-16"]
["XT_8935","Vendor Fab Low Energy - Spectral Measurement","2006-11-07","2007-01-19"]
["XT_899","Assemble -Spatial Shape & Centroid Measure","2007-09-10","2008-01-17"]
["XT_9","Specification - Electron Dump Mech/Vac","2007-10-01","2007-10-12"]
["XT_90","Assemble Vacuum System - Flipper Mirror","2006-11-06","2007-09-05"]
["XT_91","AVAIL: Far Hall Mech/Vac Ready to Install SLAC","2008-02-08","2008-02-07"]
["XT_92","Assemble Precision Hardware - Flipper Mirror","2006-11-06","2007-09-05"]
["XT_94","Assemble Pipe - Electron Dump Mech/Vac","2008-03-24","2008-03-28"]
["XT_95","Install Vacuum Pipe - Electron Dump Mech/Vac","2008-03-31","2008-04-04"]
["XT_96","Test Pipe - Electron Dump Mech/Vac","2008-04-07","2008-04-18"]
["XT_97","Commission - Electron Dump Mech/Vac","2008-08-13","2008-09-10"]
["XT_98","COMP:  Electron Dump Mech/Vac Install & Commissi","2008-09-11","2008-09-10"]
["XT_99","Beam Simulation - FY-05","2005-05-02","2005-11-02"]
["XT_991","Specification - FEE Diagnostic Tank","2007-05-07","2007-07-02"]
["XT_992","Design - FEE Diagnostic Tank","2007-07-03","2008-01-15"]
["XT_993","Procure Computer - FEE Diagnostic Tank","2008-01-16","2008-04-10"]
["XT_994","Assemble - FEE Diagnostic Tank","2008-05-19","2008-10-08"]
["XT_995","Install - FEE Diagnostic Tank","2008-10-09","2009-01-15"]
["XT_996","Test - FEE Diagnostic Tank","2009-01-16","2009-02-12"]
["XT_997","COMP:  FEE Diagnostic Tank","2009-02-27","2009-02-26"]
["XT_LOE","X-ray LOE Complete","2009-03-31","2009-03-30"]
["XT_M1","COMP: Design Package - Electron Dump Mech/Vac","2007-11-12","2007-11-09"]
["XT_M2","COMP: Design Package - FEE Mech/Vac","2006-01-03","2005-12-16"]
[]
[null,"Total of 12134 activities selected.",null,null,"Type key: ",null,"0=Task, 1=Independent, 2=Meeting, 3=SM, 4=FM, 5=Hammock, 6=WBS, 7=Topic "]
{"$rows_empty":94}
["XT_6602","AWARD: Contract Prototype - Indirect Imager","2006-06-07","2006-06-07"]
["XT_6603","Vendor Fab/Ship Prototype Hrdware-Indirect Image","2006-06-08","2006-08-31"]
["XT_6604","RECV: Prototype Hardware - Indirect Imager","2006-09-01","2006-08-31"]
["XT_6605","Prep Bid Pkg Production Units - Indirect Imager","2006-03-28","2006-04-10"]
["XT_6606","Bid Process Production Units - Indirect Imager","2006-04-11","2006-06-06"]
["XT_6607","AWARD: Contract Production Units - Indirect Imag","2006-06-07","2006-06-07"]
["XT_6608","Vendor Fab/Ship Production Units - Indirect Imag","2006-06-08","2006-08-31"]
["XT_6609","RECV: Production Units -  Indirect Imager","2006-09-01","2006-08-31"]
["XT_661","Specification - Far Hall Mech/Vac - H1","2007-06-19","2007-07-17"]
["XT_662","Design - Far Hall Mech/Vac - H1","2007-07-18","2007-10-10"]
["XT_663","RECV: Data Acquisition- Direct Imager","2007-02-27","2007-02-26"]
["XT_665","Assemble - Far Hall Mech/Vac","2008-02-01","2008-02-29"]
["XT_666","Install Isolation Valve - Far Hall Mech/Vac","2008-03-03","2008-03-07"]
["XT_667","Test - Far Hall Mech/Vac - H1","2008-03-10","2008-03-21"]
["XT_6670","Prep Bid Pkg Turbo System - FEE Diagnostic Tank","2008-01-16","2008-01-23"]
["XT_6671","Bid Process Turbo System - FEE Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_6672","AWARD: Contract Turbo System - FEE Diagnostic Tn","2008-02-22","2008-02-22"]
["XT_6673","Vendor Fab/Ship Turbo System - FEE Diagnostic Ta","2008-02-25","2008-05-16"]
["XT_6674","RECV:  Turbo System - FEE Diagnostic Tank","2008-05-19","2008-05-16"]
["XT_6675","Prep Bid Pkg Scroll Dry Pump-FEE Diagnostic Tnk","2008-01-16","2008-01-23"]
["XT_6676","Bid Process Scroll Dry Pump-FEE Diagnostic Tnk","2008-01-24","2008-02-21"]
["XT_6677","AWARD: Contract Scroll Dry Pump-FEE DiagnosticTn","2008-02-22","2008-02-22"]
["XT_6678","Vendor Ship Scroll Dry Pump-FEE Diagnostic Tank","2008-02-25","2008-05-16"]
["XT_6679","RECV: Scroll Dry Pump-FEE Diagnostic Tnk","2008-05-19","2008-05-16"]
["XT_668","Commission - Far Hall Mech/Vac - H1","2008-03-24","2008-04-04"]
["XT_6680","Prep Bid Pkg Imager Stages - FEE Diagnostic Tank","2008-01-16","2008-01-23"]
["XT_6681","Bid Process  Imager Stages - FEE Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_6682","AWARD: Contract  Imager Stages - FEE Diagnostic","2008-02-22","2008-02-22"]
["XT_6683","Vendor Fab/Ship Imager Stages - FEE Diagnostic T","2008-02-25","2008-05-16"]
["XT_6684","RECV:   Imager Stages - FEE Diagnostic Tank","2008-05-19","2008-05-16"]
["XT_6685","Prep Bid Pkg Stand - FEE Diagnostic Tank","2008-01-16","2008-01-23"]
["XT_6686","Bid Process Stand - FEE Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_6687","AWARD: Contract Stand - FEE Diagnostic Tank","2008-02-22","2008-02-22"]
["XT_6688","Vendor Fab/Ship Stand - FEE Diagnostic Tank","2008-02-25","2008-05-16"]
["XT_6689","RECV:  Stand - FEE Diagnostic Tank","2008-05-19","2008-05-16"]
["XT_669","COMP:  Far Hall Mech/Vac - H1 Installed & Commis","2008-04-07","2008-04-04"]
["XT_6690","Prep Bid Pkg Motor Driver - FEE Diagnostic Tank","2008-01-16","2008-01-23"]
["XT_6691","Bid Process Motor Driver - FEE Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_6692","AWARD: Contract Motor Driver - FEE Diagnostic Ta","2008-02-22","2008-02-22"]
["XT_6693","Vendor Fab/Ship Motor Driver -FEE Diagnostic Tnk","2008-02-25","2008-05-16"]
["XT_6694","RECV: Motor Driver - FEE Diagnostic Tank","2008-05-19","2008-05-16"]
["XT_6695","Prep Bid Pkg EPICS IF - FEE Diagnostic Tank","2008-01-16","2008-01-23"]
["XT_6696","Bid Process EPICS IF - FEE Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_6697","AWARD: Contract EPICS IF - FEE Diagnostic Tank","2008-02-22","2008-02-22"]
["XT_6698","Vendor Fab/Ship EPICS IF - FEE Diagnostic Tank","2008-02-25","2008-05-16"]
["XT_6699","RECV: EPICS IF - FEE Diagnostic Tank","2008-05-19","2008-05-16"]
["XT_6700","Prep Bid Pk Misc Racks/Chases-FEE Diagnostic Tnk","2008-01-16","2008-01-23"]
["XT_6701","Bid Process Misc Racks/Chases-FEE Diagnostic Tnk","2008-01-24","2008-02-21"]
["XT_6702","AWARD: Contract Misc Racks/Chases-FEE Diagnostic","2008-02-22","2008-02-22"]
["XT_6703","Vendor Fab/Ship Misc Racks/Chases-FEE Diagnostic","2008-02-25","2008-05-16"]
["XT_6704","RECV:  Misc Racks/Chases-FEE Diagnostic Tnk","2008-05-19","2008-05-16"]
["XT_671","Specification - Near Hall Mech/Vac - H2","2006-01-27","2006-04-21"]
["XT_672","Design - Near Hall Mech/Vac - H2","2006-04-24","2006-08-15"]
["XT_674","Assemble - NH Mech/Vac - H2","2007-03-21","2007-04-17"]
["XT_676","Test - Near Hall Mech/Vac - H2","2008-01-29","2008-02-11"]
["XT_677","Commission - Near Hall Mech/Vac - H2","2008-02-12","2008-03-11"]
["XT_678","COMP:  Near Hall Mech/Vac - H2","2008-03-12","2008-03-12"]
["XT_680","Commission - Near Hall Mech/Vac - H1","2008-02-12","2008-03-11"]
["XT_682","Procure Hand Isolation Valve-Far Hall Mec/Vac-H1","2007-10-11","2007-12-07"]
["XT_683","Procure Gate Isolation Valve-Far Hall Mec/Vac-H1","2007-10-11","2007-12-07"]
["XT_684","AVAIL: Near Hall Mech/Vac - H2","2007-04-18","2007-04-17"]
["XT_685","Procure Bellows & Spools - Far Hall Mech/Vac","2007-10-11","2007-12-07"]
["XT_686","COMP: Design - Spatial Coherence","2008-01-09","2008-01-08"]
["XT_687","AWARD: Low Energy Slit - Spatial Coherence","2008-02-22","2008-02-22"]
["XT_688","Procure Bellows & Spools - Far Hall Mech/Vac","2007-10-11","2007-12-07"]
["XT_69","Bid Process Jaws - Flipper Mirror","2006-05-15","2006-06-12"]
["XT_691","Specification - Indirect Imager","2005-02-02","2005-05-25"]
["XT_692","Design - Indirect Imager","2005-05-26","2006-03-27"]
["XT_694","Assemble - Indirect Imager","2006-09-01","2007-02-08"]
["XT_695","Install - Indirect Imager","2007-07-11","2007-10-03"]
["XT_696","Test - Indirect Imager","2007-10-25","2007-11-21"]
["XT_697","COMP:  Indirect Imager Installed & Commissioned","2007-12-10","2007-12-07"]
["XT_699","Procure Hand Isolation Valve - Far Hall Mech/Vac","2007-10-11","2007-12-07"]
["XT_7","Commission - FEE Mech/Vac","2008-01-04","2008-03-03"]
["XT_70","Specification - Far Hall Mech/Vac - H2","2007-06-19","2007-07-17"]
["XT_700","Assemble - NH Mech/Vac - H1","2008-01-07","2008-01-18"]
["XT_7000","Specification - Slit/Collimator B","2006-10-02","2006-10-27"]
["XT_7001","Design - Slit/Collimator B","2006-10-30","2007-04-06"]
["XT_70011","REQD: FEE Beneficial Occupancy","2008-04-18","2008-04-17"]
["XT_7002","Design Review - Slit/Collimator B","2007-04-09","2007-05-04"]
["XT_7003","COMP: Design Package - Slit/Collimator B","2007-05-07","2007-05-04"]
["XT_7004","Prepare Bid Pkg Jaws - Slit/Collimator B","2007-05-07","2007-05-11"]
["XT_7005","Prepare Bid Pkg Tank - Slit/Collimator B","2007-05-07","2007-05-11"]
["XT_7006","Prepare Bid Pkg Electronics - Slit/Collimator B","2007-05-07","2007-05-11"]
["XT_7007","Prepare Bid Pk Vacuum System - Slit/Collimator B","2007-05-07","2007-05-11"]
["XT_7008","Prepare Bid Pkg Precision Hardware - Slit/Col B","2007-05-07","2007-05-11"]
["XT_7009","Bid Process Jaws - Slit/Collimator B","2007-05-14","2007-06-11"]
["XT_7010","Bid Process Tank - Slit/Collimator B","2007-05-14","2007-06-11"]
["XT_7011","Bid Process Electronics - Slit/Collimator B","2007-05-14","2007-06-11"]
["XT_7012","Bid Process Vacuum System - Slit/Collimator B","2007-05-14","2007-06-11"]
["XT_7013","Bid Process Precision Hardware - Slit/Col B","2007-05-14","2007-06-11"]
["XT_7014","AWARD: Contract Jaws - Slit/Collimator B","2007-06-12","2007-06-18"]
["XT_7015","AWARD: Contract Tank - Slit/Collimator B","2007-06-12","2007-06-18"]
["XT_7017","AWARD: Contract Vacuum System-Slit/Collimator B","2007-06-12","2007-06-18"]
["XT_7018","AWARD: Contract Precision Hardware - Slit/Col B","2007-06-12","2007-06-18"]
["XT_7019","Vendor Fab Jaws - Slit/Collimator B","2007-06-19","2007-07-17"]
["XT_702","Procure Vacuum Hardware - Far Hall Mech/Vac - H1","2007-10-11","2007-12-07"]
["XT_7020","Vendor Fab Tank - Slit/Collimator B","2007-06-19","2007-07-17"]
["XT_7022","Vendor Fab Vacuum System - Slit/Collimator B","2007-06-19","2007-07-17"]
["XT_7023","Vendor Fab Precision Hardware - Slit/Col B","2007-06-19","2007-07-17"]
["XT_7024","RECV Jaws - Slit/Collimator B","2007-07-18","2007-07-17"]
["XT_7025","RECV Tank - Slit/Collimator B","2007-07-18","2007-07-17"]
["XT_7026","RECV Electronics - Slit/Collimator B","2004-10-01","2004-09-30"]
["XT_7027","RECV Vacuum System - Slit/Collimator B","2007-07-18","2007-07-17"]
["XT_7028","RECV Precision Motion Hardware - Slit/Col B","2007-07-18","2007-07-17"]
["XT_7029","Assemble Tank - Slit/Collimator B","2007-07-18","2008-04-17"]
["XT_7030","Assemble Vacuum System - Slit/Collimator B","2007-07-18","2008-04-17"]
["XT_7031","Assemble Electronics - Slit/Collimator B","2004-10-01","2005-06-30"]
["XT_7032","Assemble Precision Hardware - Slit/Collimator B","2007-07-18","2008-04-17"]
["XT_7033","Assemble Jaws - Slit/Collimator B","2007-07-18","2008-04-17"]
["XT_7034","Install - Slit/Collimator B","2008-04-18","2008-06-13"]
["XT_7035","Leak Check - Slit/Collimator B","2008-06-16","2008-09-09"]
["XT_7036","Test Beam Line - Slit/Collimator B","2008-09-10","2008-11-04"]
["XT_7037","Commission - Slit/Collimator B","2008-11-05","2009-03-11"]
["XT_7038","COMP:  Slit/Collimator B  Installed & Commiss","2009-03-12","2009-03-11"]
["XT_704","AVAIL: Indirect Imager Ready to Ship to SLAC","2007-07-11","2007-07-10"]
["XT_7040","Engineering - Slit/Collimator B","2006-10-30","2007-06-18"]
["XT_7046","Fab/Assemble/Test - Const $ - Slit/Col","2008-09-10","2009-02-11"]
["XT_707","Vendor Fab Low Energy Slit - Spatial Coherence","2008-02-25","2008-05-16"]
["XT_71","Design - Far Hall Mech/Vac - H2","2007-07-18","2007-10-10"]
["XT_710","AVAIL: Near Hall Mech/Vac - H1","2008-01-22","2008-01-18"]
["XT_711","Prepare Bid Pkg Tank - Flipper Mirror","2006-05-08","2006-05-12"]
["XT_712","COMP: Design Package - Indirect Imager","2006-03-28","2006-03-27"]
["XT_7122","Prepare Bid Pkg Precision Hardware - Flipper Mir","2006-05-08","2006-05-12"]
["XT_717","RECV: Low Energy Slit - Spatial Coherence","2008-05-19","2008-05-16"]
["XT_72","Bid Process Vacuum System - Flipper Mirror","2006-05-15","2006-06-12"]
["XT_73","Assemble - Far Hall Mech/Vac - H2","2008-02-01","2008-02-29"]
["XT_730","COMP:  Near Hall Mech/Vac - H1","2008-03-12","2008-03-12"]
["XT_736","Commission - Direct Imager","2008-02-08","2008-02-22"]
["XT_74","Install Ion Pumps - Far Hall Mech/Vac - H2","2008-03-03","2008-03-07"]
["XT_746","Commission - Indirect Imager","2007-11-26","2007-12-07"]
["XT_75","Test - Far Hall Mech/Vac - H2","2008-03-10","2008-03-21"]
["XT_7512","Vendor Fab Vacuum System - Flipper Mirror","2006-10-09","2006-11-03"]
["XT_76","Commission - Far Hall Mech/Vac - H2","2008-03-24","2008-04-04"]
["XT_77","COMP:  Far Hall Mech/Vac - H2","2008-04-07","2008-04-04"]
["XT_7700","COMP: Design Package - Ion Pumped Tank","2008-01-16","2008-01-15"]
["XT_7701","Prep Bid Pkg Tank - Ion Pumped Tank","2008-01-16","2008-01-23"]
["XT_7702","Bid Process Tank - Ion Pumped Tank","2008-01-24","2008-02-21"]
["XT_7703","AWARD: Contract Tank - Ion Pumped Tank","2008-02-22","2008-02-22"]
["XT_7704","Vendor Fab/Ship Tank - Ion Pumped Tank","2008-02-25","2008-05-16"]
["XT_7705","RECV:  Tank - Ion Pumped Tank","2008-05-19","2008-05-16"]
["XT_7706","Prep Bid Pkg Ion Pump - Ion Pumped Tank","2008-01-16","2008-01-23"]
["XT_7707","Bid Process Ion Pump - Ion Pumped Tank","2008-01-24","2008-02-21"]
["XT_7708","AWARD: Contract Ion Pump - Ion Pumped Tank","2008-02-22","2008-02-22"]
["XT_7709","Vendor Fab/Ship Ion Pump - Ion Pumped Tank","2008-02-25","2008-05-16"]
["XT_771","Specification - Near Hall Mech/Vac - H3","2006-01-27","2006-04-21"]
["XT_7710","RECV:  Ion Pump - Ion Pumped Tank","2008-05-19","2008-05-16"]
["XT_7711","Prep Bid Pkg  Misc - Ion Pumped Tank","2008-01-16","2008-01-23"]
["XT_7712","Bid Process Misc - Ion Pumped Tank","2008-01-24","2008-02-21"]
["XT_7713","AWARD: Contract Misc - Ion Pump Tnk","2008-02-22","2008-02-22"]
["XT_7714","Vendor Ship Misc - Ion Pumped Tank","2008-02-25","2008-05-16"]
["XT_7715","RECV:  Misc - Ion Pumped Tank","2008-05-19","2008-05-16"]
["XT_7716","Prep Bid Pkg Imager Stages - Ion Pumped Tank","2008-01-16","2008-01-23"]
["XT_7717","Bid Process  Imager Stages - Ion Pumped Tank","2008-01-24","2008-02-21"]
["XT_7718","AWARD: Contract  Imager Stages - Ion Pumped Tank","2008-02-22","2008-02-22"]
["XT_7719","Vendor Fab/Ship Imager Stages - Ion Pumped Tank","2008-02-25","2008-05-16"]
["XT_772","Design - Near Hall Mech/Vac - H3","2006-04-24","2006-08-15"]
["XT_7720","RECV:   Imager Stages - Ion Pumped Tank","2008-05-19","2008-05-16"]
["XT_7721","Prep Bid Pkg Stand - Ion Pumped Tank","2008-01-16","2008-01-23"]
["XT_7722","Bid Process Stand - Ion Pumped Tank","2008-01-24","2008-02-21"]
["XT_7723","AWARD: Contract Stand - Ion Pumped Tank","2008-02-22","2008-02-22"]
["XT_7724","Vendor Fab/Ship Stand - Ion Pumped Tank","2008-02-25","2008-05-16"]
["XT_7725","RECV:  Stand - Ion Pumped Tank","2008-05-19","2008-05-16"]
["XT_7726","Prep Bid Pkg Motor Driver - Ion Pumped Tank","2008-01-16","2008-01-23"]
["XT_7727","Bid Process Motor Driver - Ion Pumped Tank","2008-01-24","2008-02-21"]
["XT_7728","AWARD: Contract Motor Driver - Ion Pumped Tank","2008-02-22","2008-02-22"]
["XT_7729","Vendor Fab/Ship Motor Driver -Ion Pumped Tank","2008-02-25","2008-05-16"]
["XT_773","REQD: Near Hall Beneficial Occup - Mech/Vac","2007-03-21","2007-03-20"]
["XT_7730","RECV: Motor Driver - Ion Pumped Tank","2008-05-19","2008-05-16"]
["XT_7731","Prep Bid Pkg EPICS IF - Ion Pumped Tank","2008-01-16","2008-01-23"]
["XT_7732","Bid Process EPICS IF - Ion Pumped Tank","2008-01-24","2008-02-21"]
["XT_7733","AWARD: Contract EPICS IF - Ion Pumped Tank","2008-02-22","2008-02-22"]
["XT_7734","Vendor Fab/Ship EPICS IF - Ion Pumped Tank","2008-02-25","2008-05-16"]
["XT_7735","RECV: EPICS IF - Ion Pumped Tank","2008-05-19","2008-05-16"]
["XT_7736","Prep Bid Pk Misc Racks/Chases-Ion Pumped Tank","2008-01-16","2008-01-23"]
["XT_7737","Bid Process Misc Racks/Chases-Ion Pumped Tank","2008-01-24","2008-02-21"]
["XT_7738","AWARD: Contract Misc Racks/Chases-Ion Pumped Tan","2008-02-22","2008-02-22"]
["XT_7739","Vendor Fab/Ship Misc Racks/Chases-Ion Pumped Tan","2008-02-25","2008-05-16"]
["XT_774","Assemble - NH Mech/Vac - H3","2007-03-21","2007-04-17"]
["XT_7740","RECV:  Misc Racks/Chases-Ion Pumped Tank","2008-05-19","2008-05-16"]
["XT_7741","COMP: Design - Comm Diagnostic Tank","2008-01-16","2008-01-15"]
["XT_7742","Prep Bid Pkg Tank - Comm Diagnostic Tank","2008-01-16","2008-01-23"]
["XT_7743","Prep Bid Pkg Scroll Dry Pump-Comm Diagnostic Tnk","2008-01-16","2008-01-23"]
["XT_7744","Prep Bid Pkg Turbo System - Comm Diagnostic Tank","2008-01-16","2008-01-23"]
["XT_7745","Prep Bid Pkg Imager Stages - Comm Diagnostic Tan","2008-01-16","2008-01-23"]
["XT_7746","Prep Bid Pkg Stand - Comm Diagnostic Tank","2008-01-16","2008-01-23"]
["XT_7747","Prep Bid Pkg Motor Driver - Comm Diagnostic Tank","2008-01-16","2008-01-23"]
["XT_7748","Prep Bid Pkg EPICS IF - Comm Diagnostic Tank","2008-01-16","2008-01-23"]
["XT_7749","Prep Bid Pk 2 Axis Rail Adjus-Comm Diagnostic Ta","2008-01-16","2008-01-23"]
["XT_775","Install Vacuum Piping - NH Mech/Vac - H3","2007-04-18","2007-04-24"]
["XT_7751","Bid Process Tank - Comm Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_7752","Bid Process Scroll Dry Pump-Comm Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_7753","Bid Process Turbo System - Comm Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_7754","Bid Process  Imager Stages - Comm Diagnostic Tan","2008-01-24","2008-02-21"]
["XT_7755","Bid Process Stand - Comm Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_7756","Bid Process Motor Driver - Comm Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_7757","Bid Process EPICS IF - Comm Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_7758","Bid Process 2 Axis Rail Adjus-Comm Diagnostic Ta","2008-01-24","2008-02-21"]
["XT_7759","AWARD: Contract Tank - Comm Diagnostic Tank","2008-02-22","2008-02-22"]
["XT_776","Test - Near Hall Mech/Vac - H3","2007-04-25","2007-05-08"]
["XT_7767","Vendor Fab/Ship Tank - Comm Diagnostic Tank","2008-02-25","2008-05-16"]
["XT_777","Commission - Near Hall Mech/Vac - H3","2007-05-09","2007-06-06"]
["XT_7775","Assemble - Comm Diagnostic Tank","2008-01-24","2008-05-15"]
["XT_7776","RECV:  Tank - Comm Diagnostic Tank","2008-05-19","2008-05-16"]
["XT_778","COMP:  Near Hall Mech/Vac - H3","2007-06-07","2007-06-07"]
["XT_77801","AWARD: Contract Vacuum System - Flipper Mirror","2006-10-02","2006-10-06"]
["XT_77885","AWARD: Contract Precision Hardware - Flipper Mir","2006-10-02","2006-10-06"]
["XT_7789","RECV: Material -Spatial Shape & Centroid Measure","2008-03-27","2008-03-26"]
["XT_778956","Vendor Fab Jaws - Flipper Mirror","2006-10-09","2006-11-03"]
["XT_7793","REQD: Near Hall Beneficial Occup -Comm Diag Tank","2007-03-21","2007-03-21"]
["XT_78","Specification - Far Hall Mech/Vac - H3","2007-06-19","2007-07-17"]
["XT_780","Prepare Bid Pkg -Spatial Shape & Centroid Measur","2007-11-06","2007-11-12"]
["XT_7801","Procure Production Unit-Total Energy Measurement","2006-10-03","2007-01-11"]
["XT_781","Bid Process - Spatial Shape & Centroid Measure","2007-11-13","2007-12-12"]
["XT_7813","Vendor Fab Precision Hardware - Flipper Mirror","2006-10-09","2006-11-03"]
["XT_7814","RECV Jaws - Flipper Mirror","2006-11-06","2006-11-03"]
["XT_7816","RECV Tank - Flipper Mirror","2006-11-06","2006-11-03"]
["XT_7817","Assemble Tank - Flipper Mirror","2006-11-06","2007-09-05"]
["XT_7818","Assemble Electronics - Flipper Mirror","2006-06-13","2007-04-11"]
["XT_7819","Assemble Jaws - Flipper Mirror","2006-11-06","2007-09-05"]
["XT_782","AWARD: Contract - Spatial Shape & Centroid Measu","2007-12-13","2007-12-13"]
["XT_7820","Install - Flipper Mirror","2007-09-06","2007-10-31"]
["XT_7821","Leak Check - Flipper Mirror","2007-11-01","2007-11-30"]
["XT_7822","Test Beam Line - Flipper Mirror","2007-12-03","2008-01-15"]
["XT_7823","Fab/Assemble/Test - Const $ - Flipper Mirror","2007-09-06","2008-02-13"]
["XT_7824","Commission - Flipper Mirror","2008-01-16","2008-05-08"]
["XT_7825","COMP:  Flipper Mirror","2008-05-09","2008-05-08"]
["XT_783","Vendor Fab/Ship - Spatial Shape & Centroid Measu","2007-12-14","2008-03-26"]
["XT_784","AVAIL: Near Hall Mech/Vac H3","2008-01-22","2008-01-18"]
["XT_785","Install Ion Pumps - NH Mech/Vac - H3","2007-04-18","2007-04-24"]
["XT_786","Ship to SLAC-Spatial Shape & Centroid Measure","2008-07-21","2008-07-25"]
["XT_787","Unpack and Assemble at SLAC-Spatial Shape & Cent","2008-07-28","2008-08-08"]
["XT_788","AVAIL: Spatial Shape & Centroid Measure","2008-08-11","2008-08-08"]
["XT_789","Bid Process Tank - Flipper Mirror","2006-05-15","2006-06-12"]
["XT_79","Design - Far Hall Mech/Vac - H3","2007-07-18","2007-10-10"]
["XT_7924","Bid Process Electronics - Flipper Mirror","2006-05-15","2006-06-12"]
["XT_7955","Bid Process Precision Hardware - Flipper Mirror","2006-05-15","2006-06-12"]
["XT_7956","AWARD: Contract Jaws - Flipper Mirror","2006-10-02","2006-10-06"]
["XT_7957","AWARD: Contract Tank - Flipper Mirror","2006-10-02","2006-10-06"]
["XT_798","REQD: Near Hall Benefic Occup-Spatial & Centroid","2008-08-11","2008-08-08"]
["XT_8","COMP:  FEE Mechanical/Vacuum Installed & Commiss","2008-03-04","2008-03-03"]
["XT_80","Vendor Fab Tank - Flipper Mirror","2006-10-09","2006-11-03"]
["XT_800","Test Beam Line - Slit/Collimator A","2007-07-30","2007-09-10"]
["XT_8000","Prep Bid Package Vacuum - Near Hall Optics Tank","2007-02-09","2007-02-23"]
["XT_8001","Bid Process Tank - Near Hall Optics Tank","2007-02-26","2007-03-23"]
["XT_8002","Commission - Slit/Collimator A","2007-09-11","2007-11-05"]
["XT_8003","Vendor Fab/Ship Tank - Near Hall Optics Tank","2007-03-27","2007-05-21"]
["XT_8004","AWARD: Contract Tank - Near Hall Optics Tank","2007-03-26","2007-03-26"]
["XT_8007","RECV: Tank - Near Hall Optics Tank","2007-05-22","2007-05-21"]
["XT_801","COMP:  Slit/Collimator A","2007-12-03","2007-11-30"]
["XT_805","Install Ion Gauges - NH Mech/Vac - H3","2007-04-18","2007-04-24"]
["XT_81","Assemble - Far Hall Mech/Vac - H3","2008-02-01","2008-02-07"]
["XT_810","Install - Slit/Collimator A","2007-04-19","2007-06-14"]
["XT_815","Install Stands - NH Mech/Vac - H3","2007-04-18","2007-04-24"]
["XT_82","Install Ion Pumps - Far Hall Mech/Vac - H3","2008-02-08","2008-02-14"]
["XT_820","Fab/Assemble/Test - Const $ - Slit/Col","2007-07-11","2007-11-30"]
["XT_83","Test - Far Hall Mech/Vac - H3","2008-04-21","2008-05-02"]
["XT_84","Commission - Far Hall Mech/Vac - H3","2008-05-05","2008-05-16"]
["XT_85","COMP:  Far Hall Mech/Vac - H3  Installed & Commi","2008-05-19","2008-05-16"]
["XT_86","RECV Electronics - Flipper Mirror","2006-06-13","2006-06-12"]
["XT_87","RECV Vacuum System - Flipper Mirror","2006-11-06","2006-11-03"]
["XT_88","RECV Precision Motion Hardware - Flipper Mirror","2006-11-06","2006-11-03"]
["XT_8842","Prep Bid Pkg Grating - Spectral Measurement","2006-10-02","2006-10-06"]
["XT_8845","Prep Bid Pkg Low Energy - Spectral Measurement","2006-10-02","2006-10-06"]
["XT_8846","Prep Bid Rails & Stages - Spectral Measurement","2006-10-02","2006-10-06"]
["XT_8852","Bid Process Grating - Spectral Measurement","2006-10-09","2006-11-03"]
["XT_8855","Prep Bid Pkg High Energy - Spectral Measurement","2006-10-02","2006-10-06"]
["XT_8856","Bid Process Rails & Stages -Spectral Measurement","2006-10-09","2006-11-03"]
["XT_8862","AWARD: Grating - Spectral Measurement","2006-11-06","2006-11-06"]
["XT_8865","Bid Process Low Energy - Spectral Measurement","2006-10-09","2006-11-03"]
["XT_8866","AWARD: Rails & Stages - Spectral Measurement","2006-11-06","2006-11-06"]
["XT_8872","Vendor Fab Grating - Spectral Measurement","2006-11-07","2007-01-19"]
["XT_8875","AWARD: Low Energy - Spectral Measurement","2006-11-06","2006-11-06"]
["XT_8876","Vendor Fab Rails & Stages - Spectral Measurement","2006-11-07","2007-01-19"]
["XT_8882","RECV: Grating - Spectral Measurement","2007-01-22","2007-01-19"]
["XT_8885","RECV:  Low Energy - Spectral Measurement","2007-01-22","2007-01-19"]
["XT_8886","RECV: Rails & Stages - Spectral Measurement","2007-01-22","2007-01-19"]
["XT_8895","Bid Process - Spectral Measurement","2006-10-09","2006-11-03"]
["XT_89","Procure Vacuum Hardware - Far Hall Mech/Vac","2007-10-11","2007-12-07"]
["XT_8905","AWARD: Contract - Spectral Measurement","2006-11-06","2006-11-06"]
["XT_8915","Vendor Fab High Energy - Spectral Measurement","2006-11-07","2007-02-16"]
["XT_8925","RECV: High Energy - Spectral Measurement","2007-02-20","2007-02-16"]
["XT_8935","Vendor Fab Low Energy - Spectral Measurement","2006-11-07","2007-01-19"]
["XT_899","Assemble -Spatial Shape & Centroid Measure","2008-03-27","2008-07-18"]
["XT_9","Specification - Electron Dump Mech/Vac","2007-10-01","2007-10-12"]
["XT_90","Assemble Vacuum System - Flipper Mirror","2006-11-06","2007-09-05"]
["XT_91","AVAIL: Far Hall Mech/Vac Ready to Install SLAC","2008-02-08","2008-02-07"]
["XT_92","Assemble Precision Hardware - Flipper Mirror","2006-11-06","2007-09-05"]
["XT_94","Assemble Pipe - Electron Dump Mech/Vac","2008-03-24","2008-03-28"]
["XT_95","Install Vacuum Pipe - Electron Dump Mech/Vac","2008-03-31","2008-04-04"]
["XT_96","Test Pipe - Electron Dump Mech/Vac","2008-04-07","2008-04-18"]
["XT_97","Commission - Electron Dump Mech/Vac","2008-08-13","2008-09-10"]
["XT_98","COMP:  Electron Dump Mech/Vac Install & Commissi","2008-09-11","2008-09-10"]
["XT_99","Beam Simulation - FY-05","2005-03-02","2005-10-28"]
["XT_991","Specification - FEE Diagnostic Tank","2007-05-07","2007-07-02"]
["XT_992","Design - FEE Diagnostic Tank","2007-07-03","2008-01-15"]
["XT_993","Procure Computer - FEE Diagnostic Tank","2008-01-16","2008-04-10"]
["XT_994","Assemble - FEE Diagnostic Tank","2008-05-19","2008-10-08"]
["XT_995","Install - FEE Diagnostic Tank","2008-10-09","2009-01-15"]
["XT_996","Test - FEE Diagnostic Tank","2009-01-16","2009-02-12"]
["XT_997","COMP:  FEE Diagnostic Tank","2009-02-27","2009-02-26"]
["XT_LOE","X-ray LOE Complete","2009-03-31","2009-03-30"]
["XT_M1","COMP: Design Package - Electron Dump Mech/Vac","2007-11-12","2007-11-09"]
["XT_M2","COMP: Design Package - FEE Mech/Vac","2006-01-27","2006-01-26"]
[]
[null,"Total of 12534 activities selected.",null,null,"Type key: ",null,"0=Task, 1=Independent, 2=Meeting, 3=SM, 4=FM, 5=Hammock, 6=WBS, 7=Topic "]
{"$rows_empty":151}
["XT_5551","Prep Bid Pkg Prototype - Direct Imager","2006-09-27","2006-10-10"]
["XT_5552","Bid Process Prototype - Direct Imager","2006-10-11","2006-12-07"]
["XT_5553","AWARD: Contract Prototype - Direct Imager","2006-12-08","2006-12-08"]
["XT_5554","Vendor Fab/Ship Prototype Hrdware- Direct Imager","2006-12-11","2007-05-02"]
["XT_5555","RECV: Prototype Hardware - Direct Imager","2007-05-03","2007-05-02"]
["XT_5556","Prep Bid Pkg Production Units - Direct Imager","2006-09-27","2006-10-10"]
["XT_5557","Assemble - Divergence Measurement","2008-09-04","2008-10-29"]
["XT_5558","AWARD: Contract Production Units - Direct Imager","2006-12-08","2006-12-08"]
["XT_5559","Vendor Fab/Ship Production Units - Direct Imager","2006-12-11","2007-05-02"]
["XT_556","Install Isolation Valve - Tunnel Mech/Vac","2008-02-19","2008-06-10"]
["XT_5560","RECV: Production Units - Direct Imager","2007-05-03","2007-05-02"]
["XT_5567","Ship to SLAC-Divergence Measurement","2008-10-30","2008-11-05"]
["XT_557","Test - Tunnel Mech/Vac","2008-06-11","2008-08-06"]
["XT_5577","Unpack and Assemble at SLAC-Divergence Measureme","2008-11-06","2008-11-19"]
["XT_558","Commission - Tunnel Mech/Vac","2008-08-13","2008-09-10"]
["XT_5587","AVAIL: Divergence Measurement","2008-11-20","2008-11-19"]
["XT_559","COMP:  Tunnel Mech/Vac  Installed & Commiss","2008-09-11","2008-09-10"]
["XT_56","Specification - Flipper Mirror","2005-10-03","2005-10-28"]
["XT_5607","REQD: Near Hall Beneficial Occup-Divergence Meas","2008-11-20","2008-11-19"]
["XT_561","Bid Process Data Acquisition- Spectral Measure","2008-01-16","2008-02-13"]
["XT_565","Bid Process Stand - Near Hall Optic Tank","2007-02-27","2007-03-26"]
["XT_566","Assemble Tank - Near Hall Optics Tank","2007-05-23","2007-07-19"]
["XT_567","Prepare Bid Pkg Blower - Gas Attenuator","2006-07-11","2006-07-24"]
["XT_568","Commission - Near Hall Optics Tank","2007-10-29","2007-11-09"]
["XT_57","Design - Flipper Mirror","2005-10-31","2006-04-07"]
["XT_571","AWARD: Data Acquisition- Spectral Measurement","2008-02-14","2008-02-14"]
["XT_574","Commissioning - Spectral Measurement","2008-11-13","2008-11-26"]
["XT_575","AWARD: Contract Stand - Near Hall Optic Tank","2007-03-27","2007-03-27"]
["XT_576","Prepare Bid Package Tank - Near Hall Optics Tank","2007-02-12","2007-02-26"]
["XT_577","Prepare Bid Pkg Transfer Manifold - Gas Atten","2006-07-11","2006-07-24"]
["XT_578","Bid Process Vacuum - Near Hall Optics Tank","2007-02-27","2007-03-26"]
["XT_579","Vendor Fab/Ship  Vacuum - Near Hall Optics Tank","2007-03-28","2007-05-22"]
["XT_58","Engineering - Flipper Mirror","2005-10-31","2006-06-19"]
["XT_580","RECV:  Stand - Near Hall Optic Tank","2007-05-23","2007-05-22"]
["XT_581","Vendor Fab Data Acquisition-Spectral Measurement","2008-02-15","2008-04-11"]
["XT_585","RECV:   Vacuum - Near Hall Optics Tank","2007-05-23","2007-05-22"]
["XT_586","Assemble Vacuum - Near Hall Optics Tank","2007-05-23","2007-07-19"]
["XT_587","Prepare Bid Pkg Gas Purifier - Gas Attenuator","2006-07-11","2006-07-24"]
["XT_5888","AWARD: Contract Vacuum - Near Hall Optics Tank","2007-03-27","2007-03-27"]
["XT_59","Design - Flipper Mirror","2005-10-31","2006-04-07"]
["XT_591","Specification - Direct Imager","2005-04-19","2005-07-13"]
["XT_592","Design (5) - Direct Imager","2005-07-14","2006-09-26"]
["XT_593","Prep Bid Pkg Data Acquisition - Direct Imager","2006-09-27","2006-10-10"]
["XT_594","Assemble - Direct  Imager","2007-05-03","2007-09-24"]
["XT_595","Install - Direct Imager","2007-09-25","2008-03-04"]
["XT_596","Test - Direct Imager","2008-03-19","2008-04-15"]
["XT_597","COMP: Direct Imager","2008-04-30","2008-04-29"]
["XT_6","Test - FEE Mech/Vac","2007-09-21","2008-01-02"]
["XT_60","Engineering - Flipper Mirror","2005-10-31","2006-06-19"]
["XT_606","Assemble Stand - Near Hall Optics Tank","2007-05-23","2007-07-19"]
["XT_607","Bid Process Greenfield Comp - Gas Attenuator","2006-07-25","2006-08-21"]
["XT_61","Design Review - Flipper Mirror","2006-04-10","2006-05-05"]
["XT_611","RECV: Data Acquisition- Spectral Measurement","2008-04-14","2008-04-11"]
["XT_616","REQD: Near Hall Beneficial Occupancy","2007-07-20","2007-07-19"]
["XT_617","Bid Process Transfer Manifold - Gas Attenuator","2006-07-25","2006-08-21"]
["XT_62","COMP: Design Package - Flipper Mirror","2006-05-08","2006-05-05"]
["XT_621","REQD: FEE Beneficial Occupany - Solid Attenuator","2007-07-11","2007-07-10"]
["XT_622","COMP: Design","2006-09-27","2006-09-26"]
["XT_625","AVAIL: Tunnel Mechanical/Vacuum","2008-02-19","2008-02-15"]
["XT_626","Install Vacuum Piping - Tunnel Mech/Vac","2008-02-19","2008-06-10"]
["XT_627","Bid Process Gas Purifier - Gas Attenuator","2006-07-25","2006-08-21"]
["XT_63","Prepare Bid Pkg Jaws - Flipper Mirror","2006-05-08","2006-05-12"]
["XT_631","AVAIL:  Solid Attenuator Ready to Ship to SLAC","2007-04-12","2007-04-11"]
["XT_633","Bid Process Data Acquisition - Direct Imager","2006-10-11","2006-12-07"]
["XT_635","Visible Calibration - Direct Imager","2008-03-05","2008-03-11"]
["XT_636","Install Ion Pumps - Tunnel Mech/Vac","2008-02-19","2008-06-10"]
["XT_637","Bid Process Blower - Gas Attenuator","2006-07-25","2006-08-21"]
["XT_64","Bid Process - Fast Controls","2006-12-01","2007-02-12"]
["XT_643","AWARD: Contract Data Acquisition - Direct Imager","2006-12-08","2006-12-08"]
["XT_645","X-Ray Calibration - Direct Imager","2008-03-12","2008-03-18"]
["XT_646","Install Ion Gauges - Tunnel Mech/Vac","2008-02-19","2008-06-10"]
["XT_647","Install Stands - Tunnel Mech/Vac","2008-02-19","2008-06-10"]
["XT_65","Prepare Bid Pkg Electronics - Flipper Mirror","2006-05-08","2006-05-12"]
["XT_653","Vendor Fab/Ship Data Acquisiton - Direct Imager","2006-12-11","2007-05-02"]
["XT_654","AVAIL: Direct Imager","2007-09-25","2007-09-24"]
["XT_655","REQD: FEE Beneficial Occupancy","2007-07-11","2007-07-10"]
["XT_656","Install Spools - Tunnel Mech/Vac","2008-02-19","2008-06-10"]
["XT_657","Bid Process Low Energy Slit - Spatial Coherence","2008-01-24","2008-02-21"]
["XT_66","Prepare Bid Pk Vacuum System - Flipper Mirror","2006-05-08","2006-05-12"]
["XT_660","Test - Near Hall Mech/Vac - H1","2008-01-29","2008-02-11"]
["XT_6600","Prep Bid Pkg Prototype - Indirect Imager","2006-04-14","2006-04-27"]
["XT_6601","Bid Process Prototype - Indirect Imager","2006-04-28","2006-06-23"]
["XT_6602","AWARD: Contract Prototype - Indirect Imager","2006-06-26","2006-06-26"]
["XT_6603","Vendor Fab/Ship Prototype Hrdware-Indirect Image","2006-06-27","2006-09-20"]
["XT_6604","RECV: Prototype Hardware - Indirect Imager","2006-09-21","2006-09-20"]
["XT_6605","Prep Bid Pkg Production Units - Indirect Imager","2006-04-14","2006-04-27"]
["XT_6606","Bid Process Production Units - Indirect Imager","2006-04-28","2006-06-23"]
["XT_6607","AWARD: Contract Production Units - Indirect Imag","2006-06-26","2006-06-26"]
["XT_6608","Vendor Fab/Ship Production Units - Indirect Imag","2006-06-27","2006-09-20"]
["XT_6609","RECV: Production Units -  Indirect Imager","2006-09-21","2006-09-20"]
["XT_661","Specification - Far Hall Mech/Vac - H1","2007-06-19","2007-07-17"]
["XT_662","Design - Far Hall Mech/Vac - H1","2007-07-18","2007-10-10"]
["XT_663","RECV: Data Acquisition- Direct Imager","2007-05-03","2007-05-02"]
["XT_665","Assemble - Far Hall Mech/Vac","2008-02-01","2008-02-29"]
["XT_666","Install Isolation Valve - Far Hall Mech/Vac","2008-03-03","2008-03-07"]
["XT_667","Test - Far Hall Mech/Vac - H1","2008-03-10","2008-03-21"]
["XT_6670","Prep Bid Pkg Turbo System - FEE Diagnostic Tank","2008-01-16","2008-01-23"]
["XT_6671","Bid Process Turbo System - FEE Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_6672","AWARD: Contract Turbo System - FEE Diagnostic Tn","2008-02-22","2008-02-22"]
["XT_6673","Vendor Fab/Ship Turbo System - FEE Diagnostic Ta","2008-02-25","2008-05-16"]
["XT_6674","RECV:  Turbo System - FEE Diagnostic Tank","2008-05-19","2008-05-16"]
["XT_6675","Prep Bid Pkg Scroll Dry Pump-FEE Diagnostic Tnk","2008-01-16","2008-01-23"]
["XT_6676","Bid Process Scroll Dry Pump-FEE Diagnostic Tnk","2008-01-24","2008-02-21"]
["XT_6677","AWARD: Contract Scroll Dry Pump-FEE DiagnosticTn","2008-02-22","2008-02-22"]
["XT_6678","Vendor Ship Scroll Dry Pump-FEE Diagnostic Tank","2008-02-25","2008-05-16"]
["XT_6679","RECV: Scroll Dry Pump-FEE Diagnostic Tnk","2008-05-19","2008-05-16"]
["XT_668","Commission - Far Hall Mech/Vac - H1","2008-03-24","2008-04-04"]
["XT_6680","Prep Bid Pkg Imager Stages - FEE Diagnostic Tank","2008-01-16","2008-01-23"]
["XT_6681","Bid Process  Imager Stages - FEE Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_6682","AWARD: Contract  Imager Stages - FEE Diagnostic","2008-02-22","2008-02-22"]
["XT_6683","Vendor Fab/Ship Imager Stages - FEE Diagnostic T","2008-02-25","2008-05-16"]
["XT_6684","RECV:   Imager Stages - FEE Diagnostic Tank","2008-05-19","2008-05-16"]
["XT_6685","Prep Bid Pkg Stand - FEE Diagnostic Tank","2008-01-16","2008-01-23"]
["XT_6686","Bid Process Stand - FEE Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_6687","AWARD: Contract Stand - FEE Diagnostic Tank","2008-02-22","2008-02-22"]
["XT_6688","Vendor Fab/Ship Stand - FEE Diagnostic Tank","2008-02-25","2008-05-16"]
["XT_6689","RECV:  Stand - FEE Diagnostic Tank","2008-05-19","2008-05-16"]
["XT_669","COMP:  Far Hall Mech/Vac - H1 Installed & Commis","2008-04-07","2008-04-04"]
["XT_6690","Prep Bid Pkg Motor Driver - FEE Diagnostic Tank","2008-01-16","2008-01-23"]
["XT_6691","Bid Process Motor Driver - FEE Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_6692","AWARD: Contract Motor Driver - FEE Diagnostic Ta","2008-02-22","2008-02-22"]
["XT_6693","Vendor Fab/Ship Motor Driver -FEE Diagnostic Tnk","2008-02-25","2008-05-16"]
["XT_6694","RECV: Motor Driver - FEE Diagnostic Tank","2008-05-19","2008-05-16"]
["XT_6695","Prep Bid Pkg EPICS IF - FEE Diagnostic Tank","2008-01-16","2008-01-23"]
["XT_6696","Bid Process EPICS IF - FEE Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_6697","AWARD: Contract EPICS IF - FEE Diagnostic Tank","2008-02-22","2008-02-22"]
["XT_6698","Vendor Fab/Ship EPICS IF - FEE Diagnostic Tank","2008-02-25","2008-05-16"]
["XT_6699","RECV: EPICS IF - FEE Diagnostic Tank","2008-05-19","2008-05-16"]
["XT_6700","Prep Bid Pk Misc Racks/Chases-FEE Diagnostic Tnk","2008-01-16","2008-01-23"]
["XT_6701","Bid Process Misc Racks/Chases-FEE Diagnostic Tnk","2008-01-24","2008-02-21"]
["XT_6702","AWARD: Contract Misc Racks/Chases-FEE Diagnostic","2008-02-22","2008-02-22"]
["XT_6703","Vendor Fab/Ship Misc Racks/Chases-FEE Diagnostic","2008-02-25","2008-05-16"]
["XT_6704","RECV:  Misc Racks/Chases-FEE Diagnostic Tnk","2008-05-19","2008-05-16"]
["XT_671","Specification - Near Hall Mech/Vac - H2","2006-02-16","2006-03-16"]
["XT_672","Design - Near Hall Mech/Vac - H2","2006-03-17","2006-07-10"]
["XT_674","Assemble - NH Mech/Vac - H2","2007-03-21","2007-04-17"]
["XT_676","Test - Near Hall Mech/Vac - H2","2008-01-29","2008-02-11"]
["XT_677","Commission - Near Hall Mech/Vac - H2","2008-02-12","2008-03-11"]
["XT_678","COMP:  Near Hall Mech/Vac - H2","2008-03-12","2008-03-12"]
["XT_680","Commission - Near Hall Mech/Vac - H1","2008-02-12","2008-03-11"]
["XT_682","Procure Hand Isolation Valve-Far Hall Mec/Vac-H1","2007-10-11","2007-12-07"]
["XT_683","Procure Gate Isolation Valve-Far Hall Mec/Vac-H1","2007-10-11","2007-12-07"]
["XT_684","AVAIL: Near Hall Mech/Vac - H2","2007-04-18","2007-04-17"]
["XT_685","Procure Bellows & Spools - Far Hall Mech/Vac","2007-10-11","2007-12-07"]
["XT_686","COMP: Design - Spatial Coherence","2008-01-09","2008-01-08"]
["XT_687","AWARD: Low Energy Slit - Spatial Coherence","2008-02-22","2008-02-22"]
["XT_688","Procure Bellows & Spools - Far Hall Mech/Vac","2007-10-11","2007-12-07"]
["XT_69","Bid Process Jaws - Flipper Mirror","2006-05-15","2006-06-12"]
["XT_691","Specification - Indirect Imager","2005-04-19","2005-06-14"]
["XT_692","Design - Indirect Imager","2005-06-15","2006-04-13"]
["XT_694","Assemble - Indirect Imager","2006-09-21","2007-02-28"]
["XT_695","Install - Indirect Imager","2007-07-11","2007-10-03"]
["XT_696","Test - Indirect Imager","2007-10-25","2007-11-21"]
["XT_697","COMP:  Indirect Imager Installed & Commissioned","2007-12-10","2007-12-07"]
["XT_699","Procure Hand Isolation Valve - Far Hall Mech/Vac","2007-10-11","2007-12-07"]
["XT_7","Commission - FEE Mech/Vac","2008-01-03","2008-02-29"]
["XT_70","Specification - Far Hall Mech/Vac - H2","2007-06-19","2007-07-17"]
["XT_700","Assemble - NH Mech/Vac - H1","2008-01-07","2008-01-18"]
["XT_7000","Specification - Slit/Collimator B","2006-10-03","2006-10-30"]
["XT_7001","Design - Slit/Collimator B","2006-10-31","2007-04-09"]
["XT_70011","REQD: FEE Beneficial Occupancy","2008-04-21","2008-04-18"]
["XT_7002","Design Review - Slit/Collimator B","2007-04-10","2007-05-07"]
["XT_7003","COMP: Design Package - Slit/Collimator B","2007-05-08","2007-05-07"]
["XT_7004","Prepare Bid Pkg Jaws - Slit/Collimator B","2007-05-08","2007-05-14"]
["XT_7005","Prepare Bid Pkg Tank - Slit/Collimator B","2007-05-08","2007-05-14"]
["XT_7006","Prepare Bid Pkg Electronics - Slit/Collimator B","2007-05-08","2007-05-14"]
["XT_7007","Prepare Bid Pk Vacuum System - Slit/Collimator B","2007-05-08","2007-05-14"]
["XT_7008","Prepare Bid Pkg Precision Hardware - Slit/Col B","2007-05-08","2007-05-14"]
["XT_7009","Bid Process Jaws - Slit/Collimator B","2007-05-15","2007-06-12"]
["XT_7010","Bid Process Tank - Slit/Collimator B","2007-05-15","2007-06-12"]
["XT_7011","Bid Process Electronics - Slit/Collimator B","2007-05-15","2007-06-12"]
["XT_7012","Bid Process Vacuum System - Slit/Collimator B","2007-05-15","2007-06-12"]
["XT_7013","Bid Process Precision Hardware - Slit/Col B","2007-05-15","2007-06-12"]
["XT_7014","AWARD: Contract Jaws - Slit/Collimator B","2007-06-13","2007-06-19"]
["XT_7015","AWARD: Contract Tank - Slit/Collimator B","2007-06-13","2007-06-19"]
["XT_7016","AWARD: Contract Electronics - Slit/Collimator B","2007-06-13","2007-06-19"]
["XT_7017","AWARD: Contract Vacuum System - Slit/Collimator","2007-06-13","2007-06-19"]
["XT_7018","AWARD: Contract Precision Hardware - Slit/Col B","2007-06-13","2007-06-19"]
["XT_7019","Vendor Fab Jaws - Slit/Collimator B","2007-06-20","2007-07-18"]
["XT_702","Procure Vacuum Hardware - Far Hall Mech/Vac - H1","2007-10-11","2007-12-07"]
["XT_7020","Vendor Fab Tank - Slit/Collimator B","2007-06-20","2007-07-18"]
["XT_7022","Vendor Fab Vacuum System - Slit/Collimator B","2007-06-20","2007-07-18"]
["XT_7023","Vendor Fab Precision Hardware - Slit/Col B","2007-06-20","2007-07-18"]
["XT_7024","RECV Jaws - Slit/Collimator B","2007-07-19","2007-07-18"]
["XT_7025","RECV Tank - Slit/Collimator B","2007-07-19","2007-07-18"]
["XT_7026","RECV Electronics - Slit/Collimator B","2007-06-20","2007-06-19"]
["XT_7027","RECV Vacuum System - Slit/Collimator B","2007-07-19","2007-07-18"]
["XT_7028","RECV Precision Motion Hardware - Slit/Col B","2007-07-19","2007-07-18"]
["XT_7029","Assemble Tank - Slit/Collimator B","2007-07-19","2008-04-18"]
["XT_7030","Assemble Vacuum System - Slit/Collimator B","2007-07-19","2008-04-18"]
["XT_7031","Assemble Electronics - Slit/Collimator B","2007-06-20","2008-03-21"]
["XT_7032","Assemble Precision Hardware - Slit/Collimator B","2007-07-19","2008-04-18"]
["XT_7033","Assemble Jaws - Slit/Collimator B","2007-07-19","2008-04-18"]
["XT_7034","Install - Slit/Collimator B","2008-04-21","2008-06-16"]
["XT_7035","Leak Check - Slit/Collimator B","2008-06-17","2008-09-10"]
["XT_7036","Test Beam Line - Slit/Collimator B","2008-09-11","2008-11-05"]
["XT_7037","Commission - Slit/Collimator B","2008-11-06","2009-03-12"]
["XT_7038","COMP:  Slit/Collimator B  Installed & Commiss","2009-03-13","2009-03-12"]
["XT_704","AVAIL: Indirect Imager Ready to Ship to SLAC","2007-07-11","2007-07-10"]
["XT_7040","Engineering - Slit/Collimator B","2006-10-31","2007-06-19"]
["XT_7046","Fab/Assemble/Test - Const $ - Slit/Col","2008-09-11","2009-02-12"]
["XT_707","Vendor Fab Low Energy Slit - Spatial Coherence","2008-02-25","2008-05-16"]
["XT_71","Design - Far Hall Mech/Vac - H2","2007-07-18","2007-10-10"]
["XT_710","AVAIL: Near Hall Mech/Vac - H1","2008-01-22","2008-01-18"]
["XT_711","Prepare Bid Pkg Tank - Flipper Mirror","2006-05-08","2006-05-12"]
["XT_712","COMP: Design Package - Indirect Imager","2006-04-14","2006-04-13"]
["XT_7122","Prepare Bid Pkg Precision Hardware - Flipper Mir","2006-05-08","2006-05-12"]
["XT_717","RECV: Low Energy Slit - Spatial Coherence","2008-05-19","2008-05-16"]
["XT_72","Bid Process Vacuum System - Flipper Mirror","2006-05-15","2006-06-12"]
["XT_73","Assemble - Far Hall Mech/Vac - H2","2008-02-01","2008-02-29"]
["XT_730","COMP:  Near Hall Mech/Vac - H1","2008-03-12","2008-03-12"]
["XT_736","Commission - Direct Imager","2008-04-16","2008-04-29"]
["XT_74","Install Ion Pumps - Far Hall Mech/Vac - H2","2008-03-03","2008-03-07"]
["XT_746","Commission - Indirect Imager","2007-11-26","2007-12-07"]
["XT_75","Test - Far Hall Mech/Vac - H2","2008-03-10","2008-03-21"]
["XT_7512","Vendor Fab Vacuum System - Flipper Mirror","2006-06-20","2006-07-18"]
["XT_76","Commission - Far Hall Mech/Vac - H2","2008-03-24","2008-04-04"]
["XT_77","COMP:  Far Hall Mech/Vac - H2","2008-04-07","2008-04-04"]
["XT_7700","COMP: Design Package - Ion Pumped Tank","2008-01-16","2008-01-15"]
["XT_7701","Prep Bid Pkg Tank - Ion Pumped Tank","2008-01-16","2008-01-23"]
["XT_7702","Bid Process Tank - Ion Pumped Tank","2008-01-24","2008-02-21"]
["XT_7703","AWARD: Contract Tank - Ion Pumped Tank","2008-02-22","2008-02-22"]
["XT_7704","Vendor Fab/Ship Tank - Ion Pumped Tank","2008-02-25","2008-05-16"]
["XT_7705","RECV:  Tank - Ion Pumped Tank","2008-05-19","2008-05-16"]
["XT_7706","Prep Bid Pkg Ion Pump - Ion Pumped Tank","2008-01-16","2008-01-23"]
["XT_7707","Bid Process Ion Pump - Ion Pumped Tank","2008-01-24","2008-02-21"]
["XT_7708","AWARD: Contract Ion Pump - Ion Pumped Tank","2008-02-22","2008-02-22"]
["XT_7709","Vendor Fab/Ship Ion Pump - Ion Pumped Tank","2008-02-25","2008-05-16"]
["XT_771","Specification - Near Hall Mech/Vac - H3","2006-02-16","2006-03-16"]
["XT_7710","RECV:  Ion Pump - Ion Pumped Tank","2008-05-19","2008-05-16"]
["XT_7711","Prep Bid Pkg  Misc - Ion Pumped Tank","2008-01-16","2008-01-23"]
["XT_7712","Bid Process Misc - Ion Pumped Tank","2008-01-24","2008-02-21"]
["XT_7713","AWARD: Contract Misc - Ion Pump Tnk","2008-02-22","2008-02-22"]
["XT_7714","Vendor Ship Misc - Ion Pumped Tank","2008-02-25","2008-05-16"]
["XT_7715","RECV:  Misc - Ion Pumped Tank","2008-05-19","2008-05-16"]
["XT_7716","Prep Bid Pkg Imager Stages - Ion Pumped Tank","2008-01-16","2008-01-23"]
["XT_7717","Bid Process  Imager Stages - Ion Pumped Tank","2008-01-24","2008-02-21"]
["XT_7718","AWARD: Contract  Imager Stages - Ion Pumped Tank","2008-02-22","2008-02-22"]
["XT_7719","Vendor Fab/Ship Imager Stages - Ion Pumped Tank","2008-02-25","2008-05-16"]
["XT_772","Design - Near Hall Mech/Vac - H3","2006-03-17","2006-07-10"]
["XT_7720","RECV:   Imager Stages - Ion Pumped Tank","2008-05-19","2008-05-16"]
["XT_7721","Prep Bid Pkg Stand - Ion Pumped Tank","2008-01-16","2008-01-23"]
["XT_7722","Bid Process Stand - Ion Pumped Tank","2008-01-24","2008-02-21"]
["XT_7723","AWARD: Contract Stand - Ion Pumped Tank","2008-02-22","2008-02-22"]
["XT_7724","Vendor Fab/Ship Stand - Ion Pumped Tank","2008-02-25","2008-05-16"]
["XT_7725","RECV:  Stand - Ion Pumped Tank","2008-05-19","2008-05-16"]
["XT_7726","Prep Bid Pkg Motor Driver - Ion Pumped Tank","2008-01-16","2008-01-23"]
["XT_7727","Bid Process Motor Driver - Ion Pumped Tank","2008-01-24","2008-02-21"]
["XT_7728","AWARD: Contract Motor Driver - Ion Pumped Tank","2008-02-22","2008-02-22"]
["XT_7729","Vendor Fab/Ship Motor Driver -Ion Pumped Tank","2008-02-25","2008-05-16"]
["XT_773","REQD: Near Hall Beneficial Occup - Mech/Vac","2007-03-21","2007-03-20"]
["XT_7730","RECV: Motor Driver - Ion Pumped Tank","2008-05-19","2008-05-16"]
["XT_7731","Prep Bid Pkg EPICS IF - Ion Pumped Tank","2008-01-16","2008-01-23"]
["XT_7732","Bid Process EPICS IF - Ion Pumped Tank","2008-01-24","2008-02-21"]
["XT_7733","AWARD: Contract EPICS IF - Ion Pumped Tank","2008-02-22","2008-02-22"]
["XT_7734","Vendor Fab/Ship EPICS IF - Ion Pumped Tank","2008-02-25","2008-05-16"]
["XT_7735","RECV: EPICS IF - Ion Pumped Tank","2008-05-19","2008-05-16"]
["XT_7736","Prep Bid Pk Misc Racks/Chases-Ion Pumped Tank","2008-01-16","2008-01-23"]
["XT_7737","Bid Process Misc Racks/Chases-Ion Pumped Tank","2008-01-24","2008-02-21"]
["XT_7738","AWARD: Contract Misc Racks/Chases-Ion Pumped Tan","2008-02-22","2008-02-22"]
["XT_7739","Vendor Fab/Ship Misc Racks/Chases-Ion Pumped Tan","2008-02-25","2008-05-16"]
["XT_774","Assemble - NH Mech/Vac - H3","2007-03-21","2007-04-17"]
["XT_7740","RECV:  Misc Racks/Chases-Ion Pumped Tank","2008-05-19","2008-05-16"]
["XT_7741","COMP: Design - Comm Diagnostic Tank","2008-01-16","2008-01-15"]
["XT_7742","Prep Bid Pkg Tank - Comm Diagnostic Tank","2008-01-16","2008-01-23"]
["XT_7743","Prep Bid Pkg Scroll Dry Pump-Comm Diagnostic Tnk","2008-01-16","2008-01-23"]
["XT_7744","Prep Bid Pkg Turbo System - Comm Diagnostic Tank","2008-01-16","2008-01-23"]
["XT_7745","Prep Bid Pkg Imager Stages - Comm Diagnostic Tan","2008-01-16","2008-01-23"]
["XT_7746","Prep Bid Pkg Stand - Comm Diagnostic Tank","2008-01-16","2008-01-23"]
["XT_7747","Prep Bid Pkg Motor Driver - Comm Diagnostic Tank","2008-01-16","2008-01-23"]
["XT_7748","Prep Bid Pkg EPICS IF - Comm Diagnostic Tank","2008-01-16","2008-01-23"]
["XT_7749","Prep Bid Pk 2 Axis Rail Adjus-Comm Diagnostic Ta","2008-01-16","2008-01-23"]
["XT_775","Install Vacuum Piping - NH Mech/Vac - H3","2007-04-18","2007-04-24"]
["XT_7751","Bid Process Tank - Comm Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_7752","Bid Process Scroll Dry Pump-Comm Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_7753","Bid Process Turbo System - Comm Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_7754","Bid Process  Imager Stages - Comm Diagnostic Tan","2008-01-24","2008-02-21"]
["XT_7755","Bid Process Stand - Comm Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_7756","Bid Process Motor Driver - Comm Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_7757","Bid Process EPICS IF - Comm Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_7758","Bid Process 2 Axis Rail Adjus-Comm Diagnostic Ta","2008-01-24","2008-02-21"]
["XT_7759","AWARD: Contract Tank - Comm Diagnostic Tank","2008-02-22","2008-02-22"]
["XT_776","Test - Near Hall Mech/Vac - H3","2007-04-25","2007-05-08"]
["XT_7760","AWARD: Contract Scroll Dry Pump Comm Diagnostic","2008-02-22","2008-02-22"]
["XT_7761","AWARD: Contract Turbo System - Comm Diagnostic T","2008-02-22","2008-02-22"]
["XT_7762","AWARD: Contract  Imager Stages - Comm Diagnostic","2008-02-22","2008-02-22"]
["XT_7763","AWARD: Contract Stand - Comm Diagnostic Tank","2008-02-22","2008-02-22"]
["XT_7764","AWARD: Contract Motor Driver - Comm Diagnostic T","2008-02-22","2008-02-22"]
["XT_7765","AWARD: Contract EPICS IF - Comm Diagnostic Tank","2008-02-22","2008-02-22"]
["XT_7766","AWARD: Contract 2 Axis Rail Adjustment-Comm Diag","2008-02-22","2008-02-22"]
["XT_7767","Vendor Fab/Ship Tank - Comm Diagnostic Tank","2008-02-25","2008-05-16"]
["XT_777","Commission - Near Hall Mech/Vac - H3","2007-05-09","2007-06-06"]
["XT_7775","Assemble - Comm Diagnostic Tank","2008-01-24","2008-05-15"]
["XT_7776","RECV:  Tank - Comm Diagnostic Tank","2008-05-19","2008-05-16"]
["XT_7777","RECV: Scroll Dry Pump - Comm Diagnostic Tank","2008-02-25","2008-02-22"]
["XT_7778","RECV:  Turbo System - Comm Diagnostic Tank","2008-02-25","2008-02-22"]
["XT_7779","RECV:   Imager Stages - Comm Diagnostic Tank","2008-02-25","2008-02-22"]
["XT_778","COMP:  Near Hall Mech/Vac - H3","2007-06-07","2007-06-07"]
["XT_7780","RECV:  Stand - Comm Diagnostic Tank","2008-02-25","2008-02-22"]
["XT_77801","AWARD: Contract Vacuum System - Flipper Mirror","2006-06-13","2006-06-19"]
["XT_7781","RECV: Motor Driver - Comm Diagnostic Tank","2008-02-25","2008-02-22"]
["XT_7782","RECV: EPICS IF - Comm Diagnostic Tank","2008-02-25","2008-02-22"]
["XT_7783","RECV:  2 Axis Rail Adjust-Comm Diagnostic Tank","2008-02-25","2008-02-22"]
["XT_77885","AWARD: Contract Precision Hardware - Flipper Mir","2006-06-13","2006-06-19"]
["XT_7789","RECV: Material -Spatial Shape & Centroid Measure","2007-09-25","2007-09-24"]
["XT_778956","Vendor Fab Jaws - Flipper Mirror","2006-06-20","2006-07-18"]
["XT_7793","REQD: Near Hall Beneficial Occup -Comm Diag Tank","2008-02-25","2008-02-25"]
["XT_78","Specification - Far Hall Mech/Vac - H3","2007-06-19","2007-07-17"]
["XT_780","Prepare Bid Pkg -Spatial Shape & Centroid Measur","2007-05-23","2007-05-30"]
["XT_7801","Procure Production Unit-Total Energy Measurement","2006-06-26","2006-09-19"]
["XT_781","Bid Process - Spatial Shape & Centroid Measure","2007-05-31","2007-06-27"]
["XT_7813","Vendor Fab Precision Hardware - Flipper Mirror","2006-06-20","2006-07-18"]
["XT_7814","RECV Jaws - Flipper Mirror","2006-07-19","2006-07-18"]
["XT_7816","RECV Tank - Flipper Mirror","2006-07-19","2006-07-18"]
["XT_7817","Assemble Tank - Flipper Mirror","2006-07-19","2007-05-16"]
["XT_7818","Assemble Electronics - Flipper Mirror","2006-06-20","2007-04-18"]
["XT_7819","Assemble Jaws - Flipper Mirror","2006-07-19","2007-05-16"]
["XT_782","AWARD: Contract - Spatial Shape & Centroid Measu","2007-06-28","2007-06-28"]
["XT_7820","Install - Flipper Mirror","2007-06-07","2007-08-02"]
["XT_7821","Leak Check - Flipper Mirror","2007-08-03","2007-08-30"]
["XT_7822","Test Beam Line - Flipper Mirror","2007-08-31","2007-09-28"]
["XT_7823","Fab/Assemble/Test - Const $ - Flipper Mirror","2007-07-11","2007-11-30"]
["XT_7824","Commission - Flipper Mirror","2007-10-01","2008-02-08"]
["XT_7825","COMP:  Flipper Mirror","2008-02-11","2008-02-08"]
["XT_783","Vendor Fab/Ship - Spatial Shape & Centroid Measu","2007-06-29","2007-09-24"]
["XT_784","AVAIL: Near Hall Mech/Vac H3","2008-01-22","2008-01-18"]
["XT_785","Install Ion Pumps - NH Mech/Vac - H3","2007-04-18","2007-04-24"]
["XT_786","Ship to SLAC-Spatial Shape & Centroid Measure","2008-02-05","2008-02-11"]
["XT_787","Unpack and Assemble at SLAC-Spatial Shape & Cent","2008-02-12","2008-02-26"]
["XT_788","AVAIL: Spatial Shape & Centroid Measure","2008-02-27","2008-02-26"]
["XT_789","Bid Process Tank - Flipper Mirror","2006-05-15","2006-06-12"]
["XT_79","Design - Far Hall Mech/Vac - H3","2007-07-18","2007-10-10"]
["XT_7924","Bid Process Electronics - Flipper Mirror","2006-05-15","2006-06-12"]
["XT_7955","Bid Process Precision Hardware - Flipper Mirror","2006-05-15","2006-06-12"]
["XT_7956","AWARD: Contract Jaws - Flipper Mirror","2006-06-13","2006-06-19"]
["XT_7957","AWARD: Contract Tank - Flipper Mirror","2006-06-13","2006-06-19"]
["XT_7958","AWARD: Contract Electronics - Flipper Mirror","2006-06-13","2006-06-19"]
["XT_798","REQD: Near Hall Benefic Occup-Spatial & Centroid","2008-02-27","2008-02-26"]
["XT_8","COMP:  FEE Mechanical/Vacuum Installed & Commiss","2008-03-03","2008-02-29"]
["XT_80","Vendor Fab Tank - Flipper Mirror","2006-06-20","2006-07-18"]
["XT_800","Test Beam Line - Slit/Collimator A","2007-02-13","2007-03-27"]
["XT_8000","Prep Bid Package Vacuum - Near Hall Optics Tank","2007-02-12","2007-02-26"]
["XT_8001","Bid Process Tank - Near Hall Optics Tank","2007-02-27","2007-03-26"]
["XT_8002","Commission - Slit/Collimator A","2007-03-28","2007-05-22"]
["XT_8003","Vendor Fab/Ship Tank - Near Hall Optics Tank","2007-03-28","2007-05-22"]
["XT_8004","AWARD: Contract Tank - Near Hall Optics Tank","2007-03-27","2007-03-27"]
["XT_8007","RECV: Tank - Near Hall Optics Tank","2007-05-23","2007-05-22"]
["XT_801","COMP:  Slit/Collimator A","2007-12-03","2007-11-30"]
["XT_805","Install Ion Gauges - NH Mech/Vac - H3","2007-04-18","2007-04-24"]
["XT_81","Assemble - Far Hall Mech/Vac - H3","2008-02-01","2008-02-07"]
["XT_810","Install - Slit/Collimator A","2006-10-18","2006-12-14"]
["XT_815","Install Stands - NH Mech/Vac - H3","2007-04-18","2007-04-24"]
["XT_82","Install Ion Pumps - Far Hall Mech/Vac - H3","2008-02-08","2008-02-14"]
["XT_820","Fab/Assemble/Test - Const $ - Slit/Col","2007-07-11","2007-11-30"]
["XT_83","Test - Far Hall Mech/Vac - H3","2008-04-21","2008-05-02"]
["XT_84","Commission - Far Hall Mech/Vac - H3","2008-05-05","2008-05-16"]
["XT_85","COMP:  Far Hall Mech/Vac - H3  Installed & Commi","2008-05-19","2008-05-16"]
["XT_86","RECV Electronics - Flipper Mirror","2006-06-20","2006-06-19"]
["XT_87","RECV Vacuum System - Flipper Mirror","2006-07-19","2006-07-18"]
["XT_88","RECV Precision Motion Hardware - Flipper Mirror","2006-07-19","2006-07-18"]
["XT_8842","Prep Bid Pkg Grating - Spectral Measurement","2008-01-09","2008-01-15"]
["XT_8845","Prep Bid Pkg Low Energy - Spectral Measurement","2008-01-09","2008-01-15"]
["XT_8846","Prep Bid Rails & Stages - Spectral Measurement","2008-01-09","2008-01-15"]
["XT_8852","Bid Process Grating - Spectral Measurement","2008-01-16","2008-02-13"]
["XT_8855","Prep Bid Pkg High Energy - Spectral Measurement","2008-01-09","2008-01-15"]
["XT_8856","Bid Process Rails & Stages -Spectral Measurement","2008-01-16","2008-02-13"]
["XT_8862","AWARD: Grating - Spectral Measurement","2008-02-14","2008-02-14"]
["XT_8865","Bid Process Low Energy - Spectral Measurement","2008-01-16","2008-02-13"]
["XT_8866","AWARD: Rails & Stages - Spectral Measurement","2008-02-14","2008-02-14"]
["XT_8872","Vendor Fab Grating - Spectral Measurement","2008-02-15","2008-04-11"]
["XT_8875","AWARD: Low Energy - Spectral Measurement","2008-02-14","2008-02-14"]
["XT_8876","Vendor Fab Rails & Stages - Spectral Measurement","2008-02-15","2008-04-11"]
["XT_8882","RECV: Grating - Spectral Measurement","2008-04-14","2008-04-11"]
["XT_8885","RECV:  Low Energy - Spectral Measurement","2008-04-14","2008-04-11"]
["XT_8886","RECV: Rails & Stages - Spectral Measurement","2008-04-14","2008-04-11"]
["XT_8895","Bid Process - Spectral Measurement","2008-01-16","2008-02-13"]
["XT_89","Procure Vacuum Hardware - Far Hall Mech/Vac","2007-10-11","2007-12-07"]
["XT_8905","AWARD: Contract - Spectral Measurement","2008-02-14","2008-02-14"]
["XT_8915","Vendor Fab High Energy - Spectral Measurement","2008-02-15","2008-05-09"]
["XT_8925","RECV: High Energy - Spectral Measurement","2008-05-12","2008-05-09"]
["XT_8935","Vendor Fab Low Energy - Spectral Measurement","2008-02-15","2008-04-11"]
["XT_899","Assemble -Spatial Shape & Centroid Measure","2007-09-25","2008-02-04"]
["XT_9","Specification - Electron Dump Mech/Vac","2007-10-01","2007-10-12"]
["XT_90","Assemble Vacuum System - Flipper Mirror","2006-07-19","2007-05-16"]
["XT_91","AVAIL: Far Hall Mech/Vac Ready to Install SLAC","2008-02-08","2008-02-07"]
["XT_92","Assemble Precision Hardware - Flipper Mirror","2006-07-19","2007-05-16"]
["XT_94","Assemble Pipe - Electron Dump Mech/Vac","2008-03-24","2008-03-28"]
["XT_95","Install Vacuum Pipe - Electron Dump Mech/Vac","2008-03-31","2008-04-04"]
["XT_96","Test Pipe - Electron Dump Mech/Vac","2008-04-07","2008-04-18"]
["XT_97","Commission - Electron Dump Mech/Vac","2008-08-13","2008-09-10"]
["XT_98","COMP:  Electron Dump Mech/Vac Install & Commissi","2008-09-11","2008-09-10"]
["XT_991","Specification - FEE Diagnostic Tank","2007-05-07","2007-07-02"]
["XT_992","Design - FEE Diagnostic Tank","2007-07-03","2008-01-15"]
["XT_993","Procure Computer - FEE Diagnostic Tank","2008-01-16","2008-04-10"]
["XT_994","Assemble - FEE Diagnostic Tank","2008-05-19","2008-10-08"]
["XT_995","Install - FEE Diagnostic Tank","2008-10-09","2009-01-15"]
["XT_996","Test - FEE Diagnostic Tank","2009-01-16","2009-02-12"]
["XT_997","COMP:  FEE Diagnostic Tank","2009-02-27","2009-02-26"]
["XT_LOE","X-ray LOE Complete","2009-03-31","2009-03-30"]
["XT_M1","COMP: Design Package - Electron Dump Mech/Vac","2007-11-12","2007-11-09"]
["XT_M2","COMP: Design Package - FEE Mech/Vac","2006-02-16","2006-02-15"]
[]
[null,"Total of 13088 activities selected.",null,null,"Type key: ",null,"0=Task, 1=Independent, 2=Meeting, 3=SM, 4=FM, 5=Hammock, 6=WBS, 7=Topic "]

{"sheet":"LC01","index":1,"n_rows":13212,"n_cols":7,"rows_kept":13212,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}
[null,"Activities Detail ","10971 activities in project"]
[null,"Project LC01","DataDate: 2/1/2006",null,null,null,"Latest EF: 4/5/2010"]
[]
["ID","Description","ES","EF","Total Float","AS","AF"]
["CF04012013","30% Title 2 Design Review - RY - CLOC (Apr Accr)","2005-05-02","2005-05-06",null,"2005-05-02","2005-05-06"]
["CF04012015","30% Title 2 Design Review - RY through CLOC","2005-05-02","2005-08-26",null,"2005-05-02","2005-08-26"]
["CF04012023","AWARD: Arch Flash Calculation","2006-05-19","2006-05-19"]
["CF04012025","60% Title 2 Design Review - RY through CLOC","2005-08-29","2005-11-30",null,"2005-08-29","2005-11-30"]
["CF04012033","Arc Flash Calculation","2006-05-22","2006-07-18"]
["CF04012040","90% Title 2 Design Review - RY through CLOC","2005-12-01","2006-01-06",null,"2005-12-01","2006-01-06"]
["CF04012055","100% Title 2 Design Review","2006-01-25","2006-02-17",null,"2006-01-25"]
["CF04012060","LCLS Review 100% Title 2 Design/Bid Documents","2006-01-24","2006-02-17",null,"2006-01-24"]
["CF04012065","SLAC Commitee Review 100% Title 2 Design","2006-02-21","2006-02-27"]
["CF04012070","COMP: LCLS Review 100% Design (RY-CLOC)","2006-02-28","2006-02-27"]
["CF04012075","DOE Review 100% Title 2 Design ( RY - CLOC)","2006-02-28","2006-03-27"]
["CF04012085","RCV: DOE Approval 100% Title 2 ( RY - CLOC)","2006-03-28","2006-03-27"]
["CF04012095","Far Hall A&E Title 2 Design Changes","2005-08-08","2006-01-31",null,"2005-08-08","2006-01-31"]
["CF04012101","REQD:Obtain Seismic Rvw Committee Appr(T2)","2006-05-01","2006-04-28"]
["CF04012105","A&E Title 2 Design Changes - DCNs","2005-09-01","2006-02-17",null,"2005-09-01"]
["CF04012115","A&E Title 2 Design Changes - Committed","2005-09-01","2006-02-17",null,"2005-09-01"]
["CF04012125","A&E Title 2 Design Changes - DCNs","2005-10-03","2006-02-17",null,"2005-10-03"]
["CF04012135","A&E Title 2 Design Changes - DCNs","2006-01-03","2006-02-17",null,"2006-01-03"]
["CF0401235","A&E Post 100% Negotiation","2006-02-27","2006-04-28"]
["CF04012910","SLAC Supp - FFTB Removal  (WO 8819008)","2006-04-10","2006-06-19"]
["CF04012920","REQD: Ready for Construction***","2006-07-21","2006-07-20"]
["CF04012930","SLAC Support - FFTB Removal (WO 8819007)","2006-04-10","2006-06-19"]
["CF04012935","FFTB - Site Preparation (WO 8819006)","2006-06-02","2006-07-14"]
["CF04012940","AWARD: FFTB Components & Shielding Removal","2006-04-04","2006-04-04"]
["CF04012950","FFTB - Mobilization","2006-06-01","2006-06-01"]
["CF04012960","Start - FFTB Components & Shielding Removal","2006-06-08","2006-07-20"]
["CF04012970","COMP:  FFTB Removal & Preservation","2006-07-21","2006-07-20"]
["CF04034005","UTR Support for Construction","2006-12-06","2008-03-04"]
["CF0410000","CEF Title 2 Design Support (Non Linac)","2005-06-06","2005-09-30",null,"2005-06-06","2005-09-30"]
["CF0410010","Additional CEF Title 2 Design - Non LINAC","2005-12-01","2006-06-30",null,"2005-12-01"]
["CF05010","AWARD: Research Yard Construction Pkg - FY06","2006-04-17","2006-04-17"]
["CF05012900","Research Yard Site Preparation","2005-11-07","2006-03-31",null,"2005-11-07"]
["CF05012920","Construction of FFTB/BSY Vertical Wall","2005-10-03","2005-10-28",null,"2005-10-03","2005-10-28"]
["CF05012925","Construction FFTB/BSY  - cost increased","2005-10-03","2005-11-11",null,"2005-10-03","2005-11-11"]
["CF05012930","COMP: FFTB/BSY Vertical Wall","2005-11-12","2005-11-11",null,"2005-11-12","2005-11-11"]
["CF05015","AWARD: Research Yard Construction Pkg - FY07","2006-10-02","2006-10-02"]
["CF05020","Sitework","2006-05-24","2006-10-02"]
["CF05030","Metals","2006-05-24","2006-10-02"]
["CF05033006","AWARD: EP Soil Disposal Contract","2006-10-23","2006-10-23"]
["CF05033007","EP Soil Disposal","2006-11-21","2007-07-25"]
["CF05033020","SLAC RSY - Site Construction","2006-04-03","2006-12-12"]
["CF05033030","AWARD: Testing RY through CLOC","2006-10-02","2006-10-02"]
["CF05033035","Testing - RY through CLOC","2006-10-24","2007-08-09"]
["CF05033040","AWARD: Commissioning RY through CLOC - FY07","2006-10-02","2006-10-02"]
["CF05033041","AWARD: Commissioning RY through CLOC - FY08","2007-10-01","2007-10-01"]
["CF05033042","AWARD: Commissioning RY through CLOC - FY09","2008-10-01","2008-10-01"]
["CF05033045","Commissioning - RSY-CLOC (FY07)","2006-10-03","2007-09-28"]
["CF05033050","AVAIL: Beneficial Occupancy Research Yard Mods","2006-10-03","2006-10-02"]
["CF05033053","RY Project Close Out","2006-10-03","2006-11-29"]
["CF05033054","AWARD: Construction Power for Tunnelling - FY06","2006-05-22","2006-05-22"]
["CF05033055","SLAC - Construction Power for Tunnelling","2006-06-21","2008-12-19"]
["CF05033063","AWARD: Tunnel Rescue Team","2006-03-06","2006-03-06"]
["CF05033064","AWARD: Construction Power for Tunnelling - FY07","2006-10-02","2006-10-02"]
["CF05033065","Tunnel Rescue Team","2006-03-06","2006-07-25"]
["CF05033073","AWARD: Sales Tax - FY06","2006-05-24","2006-05-24"]
["CF05033074","AWARD: Construction Power for Tunnelling - FY08","2007-10-01","2007-10-01"]
["CF05033075","Sales Tax","2006-05-24","2008-09-29"]
["CF05033083","AWARD: Sales Tax - FY07","2006-10-02","2006-10-02"]
["CF05033084","AWARD: Construction Power for Tunnelling - FY09","2008-10-01","2008-10-01"]
["CF05033085","Commissioning - RSY-CLOC (FY08)","2007-10-01","2008-09-30"]
["CF05033093","AWARD: Sales Tax - FY08","2007-10-01","2007-10-01"]
["CF05033095","Commissioning - RSY-CLOC (FY09)","2008-10-01","2008-12-31"]
["CF05033200","COMP: Research Yard Mods Final Acceptance","2006-12-13","2006-12-12"]
["CF05033500","AWARD: Furnishing - RY through CLOC","2007-10-01","2007-10-01"]
["CF05033510","Furnishing - RY through CLOC","2007-11-29","2008-09-16"]
["CF05034005","UTR Support for Construction","2006-04-18","2007-02-05"]
["CF05040","COMP: Research Yard Mods Construction","2006-10-03","2006-10-02"]
["CF06100","AWARD: Access Road Construction Package","2006-04-17","2006-04-17"]
["CF06110","Sitework","2006-05-09","2006-08-30"]
["CF06120","Concrete","2006-06-07","2006-08-30"]
["CF06130","Access Road - Project Close Out","2006-08-31","2006-09-28"]
["CF06140","COMP: Access Road Construction","2006-09-29","2006-09-28"]
["CF08100","AWARD: BTH Construction Package - FY06","2006-05-22","2006-05-22"]
["CF08105","AWARD: BTH Construction Package - FY07","2006-10-02","2006-10-02"]
["CF08110","Sitework","2006-07-21","2007-05-24"]
["CF08120","Concrete","2006-08-18","2007-05-07"]
["CF08130","Metals","2006-08-18","2007-05-07"]
["CF08140","Mechanical","2006-08-18","2007-05-07"]
["CF08150","Electrical","2006-08-18","2007-05-07"]
["CF08160","Other Construction","2006-08-18","2007-05-07"]
["CF08170","COMP: Beam Transport Hall Construction","2007-05-25","2007-05-24"]
["CF0833050","AVAIL: Beneficial Occupancy Beam Transport Hall","2007-05-25","2007-05-24"]
["CF0833100","BTH - Project Close Out","2007-05-25","2007-07-23"]
["CF0833200","COMP: Beam Transport Hall Final Acceptance","2007-07-24","2007-07-23"]
["CF09100","AWARD: Front End Enclosure Construction Pkg - FY","2006-08-01","2006-08-01"]
["CF09105","AWARD: Front End Enclosure Construction Pkg - FY","2006-10-02","2006-10-02"]
["CF09110","Sitework","2006-08-23","2007-04-17"]
["CF09120","Concrete","2006-10-19","2007-04-12"]
["CF09130","Mechanical","2006-10-19","2007-04-12"]
["CF09140","Electrical","2006-10-19","2007-04-12"]
["CF09150","Other Construction","2006-10-19","2007-04-12"]
["CF09160","COMP: FEE Construction","2007-04-18","2007-04-17"]
["CF0933050","AVAIL: Beneficial Occupancy Front End Enclosure","2007-04-18","2007-04-17"]
["CF0933100","FEE - CF Project Close Out","2007-04-18","2007-06-13"]
["CF0933200","COMP: Front End Enclosure Final Acceptance","2007-06-14","2007-06-13"]
["CF10010210","CEF Title 2 Support","2005-11-22","2005-11-30",null,"2005-11-22","2005-11-30"]
["CF10010215","AWARD: 12kv Design (MH 48 to CUP Substation)","2006-03-06","2006-03-06"]
["CF10010230","MD Support For Title 2 Design","2005-10-03","2005-11-30",null,"2005-10-03","2005-11-30"]
["CF10010240","Additional MD Support  Title 2 Design -Non LINAC","2005-12-01","2006-06-30",null,"2005-12-01"]
["CF10012010","TCCo Modification - 30% Estimate","2006-01-03","2006-01-31",null,"2006-01-03","2006-01-31"]
["CF10012015","Monte Carlo Analysis","2006-01-09","2006-01-27",null,"2006-01-09","2006-01-27"]
["CF10012025","12 kv Design (MH 48 to CUP Substation)","2006-03-07","2006-05-30"]
["CF10073055","AWARD: EBD Steel Shielding - FY06","2006-07-10","2006-07-10"]
["CF10073057","AWARD: EBD Steel Shielding - FY07","2006-10-02","2006-10-02"]
["CF10073060","SLAC Install EBD Steel Shielding","2006-08-01","2007-01-23"]
["CF10100","AWARD: Electron Beam Dump Construction Package","2006-08-16","2006-08-16"]
["CF10110","Sitework","2006-09-08","2007-05-18"]
["CF10120","Concrete","2006-11-03","2007-05-18"]
["CF10130","Mechanical","2006-11-03","2007-05-18"]
["CF10140","Electrical","2006-11-03","2007-05-18"]
["CF10150","Other Construction","2006-11-03","2007-05-18"]
["CF10160","COMP: Electron Beam Dump Construction","2007-05-21","2007-05-18"]
["CF10170","AWARD: Electron Beam Dump Constr. Pkg - FY07","2006-10-02","2006-10-02"]
["CF1033050","AVAIL: Beneficial Occupancy Beam Dump","2007-05-21","2007-05-18"]
["CF1033100","EBD - Project Close Out","2007-05-21","2007-07-17"]
["CF1033200","COMP: Electron Beam Dump Final Acceptance","2007-07-18","2007-07-17"]
["CF1103010","SLAC Site Preparation","2006-07-10","2006-10-30"]
["CF11100","AWARD: Near Experimental Hall Constr Pkg - FY06","2006-06-20","2006-06-20"]
["CF11105","AWARD: Near Experimental Hall Constr Pkg - FY07","2006-10-02","2006-10-02"]
["CF11110","Sitework including Demo Gas Pad","2006-07-13","2007-06-18"]
["CF11120","Concrete","2006-08-10","2007-03-02"]
["CF11130","Metals","2006-08-10","2007-03-02"]
["CF11140","Mechanical","2006-09-08","2007-05-25"]
["CF11150","Electrical","2006-09-08","2007-05-25"]
["CF11160","Other Construction","2006-09-08","2007-05-25"]
["CF11170","COMP: Near Experimental Hall Construction","2007-06-19","2007-06-18"]
["CF1133050","AVAIL: Beneficial Occupancy NEH","2007-06-19","2007-06-18"]
["CF1133100","NEH - CF Project Close Out","2007-06-19","2007-08-14"]
["CF1133200","COMP: Near Experimental Hall Final Acceptance","2007-08-15","2007-08-14"]
["CF12100","AWARD: Undulator Hall Construction Pkg - FY06","2006-08-07","2006-08-07"]
["CF12105","AWARD: Undulator Hall Construction Pkg - FY07","2006-10-02","2006-10-02"]
["CF12110","Sitework","2006-08-29","2007-04-30"]
["CF12120","Metals","2006-10-25","2007-04-18"]
["CF12130","Mechanical","2006-10-25","2007-04-18"]
["CF12140","Electrical","2006-10-25","2007-04-18"]
["CF12150","Other Construction","2006-10-25","2007-04-18"]
["CF12160","UH Tunnel Construction","2006-08-29","2007-04-30"]
["CF12170","COMP: Undulator Hall Construction","2007-05-01","2007-04-30"]
["CF1233050","AVAIL: Beneficial Occupancy Undulator Facility","2007-05-01","2007-04-30"]
["CF1233100","UH - CF Project Close Out","2007-05-01","2007-06-26"]
["CF1233200","COMP: Undulator Facility Final Acceptance","2007-06-27","2007-06-26"]
["CF13013085","MD Title 3 Support  - Non Linac","2006-05-01","2007-04-30"]
["CF13013100","RY - CLOC Seismic Peer Review","2005-09-06","2006-04-28",null,"2005-09-06"]
["CF13013110","In-House Conventional Facility Peer Review","2005-06-06","2006-04-28",null,"2005-06-06"]
["CF13013210","Independent Cost Estimate (ICE) - 30% Review","2005-08-15","2005-10-31",null,"2005-08-15","2005-10-31"]
["CF13013220","Independent Cost Estimate (ICE) - 60% Review","2005-11-08","2006-01-20",null,"2005-11-08","2006-01-20"]
["CF13014005","UTR Support for Construction","2007-03-21","2008-06-26"]
["CF13100","AWARD: XRTD Construction Package","2006-12-14","2006-12-14"]
["CF13110","Sitework","2007-01-04","2007-08-02"]
["CF13120","Concrete","2007-03-05","2007-07-24"]
["CF13130","Metals","2007-03-05","2007-07-24"]
["CF13140","Mechanical","2007-03-05","2007-07-24"]
["CF13150","Electrical","2007-03-05","2007-07-24"]
["CF13160","Other Construction","2007-03-05","2007-07-24"]
["CF13170","XRTD Tunnel Construction","2007-01-04","2007-08-02"]
["CF13180","COMP: X-Ray Transport & Diagnostics Construction","2007-08-03","2007-08-02"]
["CF1333050","AVAIL: Beneficial Occupancy X-Ray Transport","2007-08-03","2007-08-02"]
["CF1333100","XRTD - CF Project Close Out","2007-08-03","2007-09-28"]
["CF1333200","COMP: X-Ray Transpt & Diag Hall Final Acceptance","2007-10-01","2007-09-28"]
["CF14100","AWARD: Far Experimental Hall Construction Pkg","2006-10-31","2006-10-31"]
["CF14110","Sitework","2006-11-22","2007-08-17"]
["CF14120","Metals","2007-01-24","2007-08-10"]
["CF14130","Mechanical","2007-01-24","2007-08-10"]
["CF14140","Electrical","2007-01-24","2007-08-10"]
["CF14150","Other Construction","2007-01-24","2007-08-10"]
["CF14160","FEH Tunnel Construction","2006-11-22","2007-07-27"]
["CF14170","COMP: Far Experimental Hall Construction","2007-08-20","2007-08-17"]
["CF14180","AWARD: Access Tunnel Construction Pkg - FY06","2006-06-30","2006-06-30"]
["CF14185","AWARD: Access Tunnel Construction Pkg - FY07","2006-10-02","2006-10-02"]
["CF14190","Access Tunnel Constructionn","2006-07-25","2007-08-06"]
["CF14200","COMP: Access Tunnel Constructionn","2007-08-07","2007-08-06"]
["CF1433050","AVAIL:Beneficial Occupancy Far Experimental Hall","2007-08-20","2007-08-17"]
["CF1433100","FEH - CF Project Close Out","2007-08-20","2007-10-15"]
["CF1433200","COMP: Far Experimental Hall Final Acceptance","2007-10-16","2007-10-15"]
["CF15100","AWARD: BTH Service Building Construction Pkg","2006-10-16","2006-10-16"]
["CF15110","Concrete","2006-11-07","2007-05-24"]
["CF15120","Metals","2006-11-07","2007-05-24"]
["CF15130","Mechanical","2006-11-07","2007-05-24"]
["CF15140","Electrical","2006-11-07","2007-05-24"]
["CF15150","Other Construction","2006-11-07","2007-05-24"]
["CF15160","COMP: BTH Service Buildings Construction","2007-05-25","2007-05-24"]
["CF16100","AWARD: UH Service Building Construction Pkg","2006-10-20","2006-10-20"]
["CF16110","Concrete","2006-11-13","2007-04-30"]
["CF16120","Metals","2006-11-13","2007-04-30"]
["CF16130","Mechanical","2006-11-13","2007-04-30"]
["CF16140","Electrical","2006-11-13","2007-04-30"]
["CF16150","Other Construction","2006-11-13","2007-04-30"]
["CF16160","COMP: UH Service Building Construction","2007-05-01","2007-04-30"]
["CF17100","AWARD: FEH Service Building Construction Pkg","2007-04-05","2007-04-05"]
["CF17110","Concrete","2007-04-27","2007-08-17"]
["CF17120","Metals","2007-04-27","2007-08-17"]
["CF17130","Mechanical","2007-06-11","2007-08-17"]
["CF17140","Electrical","2007-06-11","2007-08-17"]
["CF17150","Other Construction","2007-06-11","2007-08-17"]
["CF17160","COMP: FEH Service Building Construction","2007-08-20","2007-08-17"]
["CF18090300","COMP: All Areas Except CLOC","2009-01-02","2008-12-19"]
["CF18100","AWARD: Central Utility Plant Construction - FY06","2006-06-22","2006-06-22"]
["CF18102","AWARD: Central Utility Plant Construction - FY07","2006-10-02","2006-10-02"]
["CF18103","AWARD: Natural Gas Line (Guest House to CUP)","2006-12-11","2006-12-11"]
["CF18105","AWARD: 12 kv Construction (MH48 to CUP Substat)","2006-12-11","2006-12-11"]
["CF18110","Sitework","2006-07-17","2007-05-23"]
["CF18115","Natural Gas Line (Guest House to CUP)","2007-01-18","2007-03-15"]
["CF18120","Concrete","2006-08-14","2007-04-17"]
["CF18130","Metals","2006-08-14","2007-04-17"]
["CF18140","Mechanical","2006-08-14","2007-04-17"]
["CF18150","Electrical","2006-08-14","2007-04-17"]
["CF18155","12 kv Construction (MH48 to CUP Substat)","2007-01-18","2007-05-10"]
["CF18160","Other Construction","2006-08-14","2007-04-17"]
["CF18170","Start Up & Commissioning","2007-04-12","2007-05-23"]
["CF18180","COMP: Central Utility Plant Construction","2007-05-24","2007-05-23"]
["CF1833200","COMP: Central Utility Plant Final Acceptance","2007-05-24","2007-05-23"]
["CF19100","AWARD: CLOC Contruction Package - FY06","2006-06-22","2006-06-22"]
["CF19103","AWARD: CLOC Contruction Package - FY07","2006-10-02","2006-10-02"]
["CF19106","AWARD: CLOC Contruction Package - FY08","2007-10-01","2007-10-01"]
["CF19110","AWARD: CLOC SITEWORK, Landscape & Parking - FY06","2006-06-22","2006-06-22"]
["CF19113","AWARD: CLOC SITEWORK, Landscape & Parking - FY07","2006-10-02","2006-10-02"]
["CF19116","AWARD: CLOC SITEWORK, Landscape & Parking - FY08","2007-10-01","2007-10-01"]
["CF19120","SITEWORK, Landscape and Parking","2006-07-17","2008-09-24"]
["CF19130","Concrete","2006-09-12","2008-06-26"]
["CF19140","Masonry","2006-09-12","2008-06-26"]
["CF19150","Metals","2006-09-12","2008-06-26"]
["CF19160","Wood and Plastics","2006-12-07","2008-09-22"]
["CF19170","Thermal & Moisture Protection","2006-12-07","2008-09-22"]
["CF19180","Doors & Windows","2006-12-07","2008-09-22"]
["CF19190","Finishes","2006-12-07","2008-09-22"]
["CF19200","Specialtieis","2006-12-07","2008-09-22"]
["CF19210","Equipment","2006-12-07","2008-09-22"]
["CF19220","Furnishings","2006-12-07","2008-09-22"]
["CF19230","Special Construction","2006-12-07","2008-09-22"]
["CF19240","Conveying Systems","2006-12-07","2008-09-22"]
["CF19250","Mechanical","2006-12-07","2008-09-22"]
["CF19260","Electrical","2006-12-07","2008-09-22"]
["CF19270","Commissioning & Punchlist","2008-06-03","2008-09-24"]
["CF19280","Testing and Certification","2008-09-25","2008-10-08"]
["CF19290","COMP: CLOC Construction","2008-10-09","2008-10-08"]
["CF1933050","AVAIL: Beneficial Occupancy CLOC","2008-10-09","2008-10-08"]
["CF1933100","CLOC - CF Project Close Out","2008-10-09","2008-12-17"]
["CF1933200","COMP: Central Lab Office Ctr Final Acceptance","2009-01-02","2008-12-19"]
["CFACC1100","Start Access Tunnel","2006-07-25","2006-07-24"]
["CFBD1320","Start Electron Beam Dump","2006-09-08","2006-09-07"]
["CFBID1560","Start Bid Package Phase 1","2006-02-28","2006-02-27"]
["CFBID1640","Phase 1 Subcontract Execution","2006-05-24","2006-05-23"]
["CFBID2200","Start Bid Package Phase 2","2006-04-18","2006-04-17"]
["CFBOD2260","Phase 2 Subcontract Execution","2006-07-31","2006-07-28"]
["CFBTH2000","Start FFTB Removal","2006-07-21","2006-07-20"]
["CFCLC5000","Start Commissioning","2008-06-04","2008-06-03"]
["CFCLS2000","Start Central Laboratory Office Complex","2006-07-17","2006-07-14"]
["CFCUP1120","Start Central Utility Plant","2006-07-17","2006-07-14"]
["CFFEE1100","Start Front End Enclosure","2006-08-23","2006-08-22"]
["CFFEH1180","Start FEH Cavern","2006-11-22","2006-11-21"]
["CFLNF_0010","Develop as-built package Linac Facilitiy","2005-06-06","2005-11-01",null,"2005-06-06","2005-11-01"]
["CFLNF_0020","Utility investigation Linac Facility","2005-11-01","2005-12-16",null,"2005-11-01","2005-12-16"]
["CFLNF_0070","MD Support Title 1 Linac Facility","2005-06-01","2005-11-30",null,"2005-06-01","2005-11-30"]
["CFLNF_0075","Additional MD Support Title 1 Linac Facility","2006-02-01","2006-05-24"]
["CFLNF_0230","Additional Utility Investigation Linac Fac","2006-03-06","2006-05-04"]
["CFLNF_1130","COMP: Title 1 Linac Facility","2006-05-05","2006-05-04"]
["CFLNF_1150","Sector 24 - Stairwells Design","2005-06-07","2005-08-31",null,"2005-06-07","2005-08-31"]
["CFLNF_1170","Fabricate Sector 24 Stairwells","2005-09-02","2005-09-30",null,"2005-09-02","2005-09-30"]
["CFLNF_1180","Fabricate Sector 24 Stairwells Enclosure","2005-09-12","2005-10-31",null,"2005-09-12","2005-10-31"]
["CFLNF_1210","Install Sector 24 Stairwells","2005-10-10","2005-11-11",null,"2005-10-10","2005-11-11"]
["CFLNF_1230","COMP: Sector 24 Stairwells Installation","2005-11-12","2005-11-11",null,"2005-11-12","2005-11-11"]
["CFLNF_1510","User mtg.-interior layout details Linac Facility","2006-05-05","2006-06-02"]
["CFLNF_1520","User Review and Approval Linac Facility","2006-06-05","2006-06-23"]
["CFLNF_2010","Multi-Discipline Developmt Phase Linac Facility","2006-06-26","2006-08-21"]
["CFLNF_2020","User Review and Approval Linac Facility","2006-08-22","2006-09-19"]
["CFLNF_2030","Consultant Modify drwgs as necessary Linac Facil","2006-09-20","2006-09-19"]
["CFLNF_2040","Consultants provide 100% dwgs Linac Facility","2006-09-20","2006-10-17"]
["CFLNF_2050","COMP: Title 2 Linac Facility","2006-10-18","2006-10-17"]
["CFLNF_2145","Additional MD Support Title 2 Linac Facility","2005-11-01","2005-11-30",null,"2005-11-01","2005-11-30"]
["CFLNF_2150","MD Support Title 2 Linac Facility","2006-06-26","2006-09-19"]
["CFLNF_3010","Start Construction Linac Facility","2006-10-19","2006-10-18"]
["CFLNF_3020","AWARD: T3 Construction Package (Linac)","2006-10-18","2006-10-18"]
["CFLNF_3030","MD Title 3 Support - Linac","2006-10-19","2007-03-15"]
["CFLNF_3040","Install Utilities Linac Facility","2006-10-19","2007-04-26"]
["CFLNF_3050","Install Interior Utilities Electrical","2006-10-19","2007-04-26"]
["CFLNF_3060","Building Complete Linac Facility","2007-04-27","2007-04-26"]
["CFLNF_3070","Building Commissioning Linac Facility","2007-04-27","2007-06-22"]
["CFLNF_3080","Project Punch List Linac Facility","2007-04-27","2007-06-22"]
["CFLNF_3090","Drawing Implementation to SLAC System","2007-06-25","2007-07-09"]
["CFLNF_3100","AVAIL: Beneficial Occupancy Linac Facility","2007-04-27","2007-04-26"]
["CFLNF_3120","COMP: Linac Facility  Final Acceptance","2007-07-10","2007-07-09"]
["CFMGT_1001","AWARD: Dispute Resolution Board - FY07","2006-10-02","2006-10-02"]
["CFMGT_1005","AWARD: Dispute Resolution Board - FY08","2007-10-01","2007-10-01"]
["CFMGT_1018","Management - PED (remaining)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["CFMGT_1020","Management - FY06","2005-10-03","2006-09-29",null,"2005-10-03"]
["CFMGT_1040","Construction Management Consulting - PED","2005-06-06","2005-10-31",null,"2005-06-06","2005-10-31"]
["CFMGT_1045","Cost Account Managers-Phase 2 (add)","2005-06-01","2005-09-30",null,"2005-06-01","2005-09-30"]
["CFMGT_1050","Cost Account Managers - FY06","2005-10-03","2006-09-29",null,"2005-10-03"]
["CFMGT_1051","Cost Account Managers-Phase 2 (remaining)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["CFMGT_1056","HVAC Specialist (remaining)","2005-05-02","2005-05-31",null,"2005-05-02","2005-05-31"]
["CFMGT_1070","AWARD: Construction Management Consulting - FY06","2005-10-03","2005-10-03",null,"2005-10-03","2005-10-03"]
["CFMGT_1076","AWARD: Construction Management Pkg - FY06(LLP)","2005-10-17","2005-10-17",null,"2005-10-17","2005-10-17"]
["CFMGT_1077","Phase 1 Construction Management","2005-10-19","2006-03-31",null,"2005-10-19"]
["CFMGT_1078","AWARD: Construction Management Pkg - FY06 (C)","2006-04-03","2006-04-03"]
["CFMGT_1080","Phase 2 Construction Management + Fee - FY06","2006-04-04","2006-10-02"]
["CFMGT_1082","A&E Title 2 Support  RSY-CLOC (Reimb Apr Accr)","2005-05-02","2005-05-06",null,"2005-05-02","2005-05-06"]
["CFMGT_1084","AWARD: A&E Title 3 Support for RSY-CLOC","2006-05-01","2006-05-01"]
["CFMGT_1086","A&E Title 2 Support  RSY-CLOC (Reimbursables)","2005-05-02","2006-02-17",null,"2005-05-02"]
["CFMGT_1087","A&E Support for Title 3 RSY-CLOC","2006-04-03","2007-11-12"]
["CFMGT_1088","A&E Title 3 Support for RSY-CLOC (reimbursables)","2006-04-03","2007-11-12"]
["CFMGT_1089","A&E Title 3 Support for RSY-CLOC (Mod 2)","2006-04-03","2007-11-12"]
["CFMGT_1090","Construction Management Consulting - FY06","2005-11-01","2006-09-29",null,"2005-11-01"]
["CFMGT_1099","AWARD: Dispute Resolution Board - FY06","2006-05-08","2006-05-08"]
["CFMGT_1100","Consumable Supplies - FY06","2005-10-03","2006-09-29",null,"2005-10-03"]
["CFMGT_1105","Consumable Supplies - PED (remaining)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["CFMGT_1109","Dispute Resolution Board (FY06)","2006-05-09","2007-05-07"]
["CFMGT_1110","Student Research Analyst - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["CFMGT_1115","Student Research Analyst - LLP","2006-02-06","2008-09-30"]
["CFMGT_1119","Dispute Resolution Board (FY07)","2007-05-08","2007-10-08"]
["CFMGT_1120","Management - FY07","2006-10-02","2007-09-28"]
["CFMGT_1125","Travel - FY06","2005-10-03","2006-09-29",null,"2005-10-03"]
["CFMGT_1129","Dispute Resolution Board (FY08)","2007-10-09","2008-10-08"]
["CFMGT_1130","Management - FY08 and Beyond","2007-10-01","2009-03-31"]
["CFMGT_1134","Travel - FY05 (remaining)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["CFMGT_1145","Travel - FY07","2006-10-02","2007-09-28"]
["CFMGT_1155","Travel - FY08","2007-10-01","2008-09-30"]
["CFMGT_1160","Construction Management Consulting - FY07","2006-10-02","2007-09-28"]
["CFMGT_1170","COMP: Conventional Facilities","2009-04-01","2009-03-31"]
["CFMGT_1175","CF Controls Liaison FY05Q2-Q4 (remaining)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["CFMGT_1180","Construction Management Consulting - FY08","2007-10-01","2008-09-29"]
["CFMGT_1190","Consumable Supplies - FY07","2006-10-02","2007-09-28"]
["CFMGT_1200","Consumable Supplies - FY08","2007-10-01","2008-09-30"]
["CFMGT_1210","Electrical Engineer - PED","2005-09-01","2005-09-30",null,"2005-09-01","2005-09-30"]
["CFMGT_1220","Electrical Engineer - FY06","2005-10-03","2006-09-29",null,"2005-10-03"]
["CFMGT_1230","Geotechnical Baseline Report","2005-09-12","2006-04-28",null,"2005-09-12"]
["CFMGT_1250","Cost Account Managers - FY07","2006-10-02","2007-09-28"]
["CFMGT_1260","Cost Account Managers - FY08 and Beyond","2007-10-01","2009-03-31"]
["CFMGT_1270","Electrical Engineer - FY07","2006-10-02","2007-09-28"]
["CFMGT_1280","Electrical Engineer - FY08 and Beyond","2007-10-01","2009-03-31"]
["CFMGT_1305","AWARD: Phase 2 CM + Fee - FY07","2006-10-02","2006-10-02"]
["CFMGT_1310","Phase 2 Construction Management + Fee - FY07","2006-10-03","2007-10-01"]
["CFMGT_1315","AWARD: Phase 2 CM + Fee - FY08","2007-10-01","2007-10-01"]
["CFMGT_1317","AWARD: Phase 2 CM + Fee - FY09","2008-10-01","2008-10-01"]
["CFMGT_1320","Phase 2 Construction Management + Fee - FY08","2007-10-02","2008-12-18"]
["CFMGT_1330","AWARD: Construction Management Consulting - FY07","2006-10-02","2006-10-02"]
["CFMGT_1340","AWARD: Construction Management Consulting - FY08","2007-10-01","2007-10-01"]
["CFMGT_1500","UTR Support for Construction","2005-08-15","2005-12-16",null,"2005-08-15","2005-12-16"]
["CFMGT_1510","UTR Support for Construction","2005-08-15","2006-09-01",null,"2005-08-15"]
["CFMGT_1520","UTR Support for Construction","2005-08-15","2006-12-01",null,"2005-08-15"]
["CFMGT_1530","UTR Support for Construction","2006-02-01","2006-04-17"]
["CFMGT_1540","UTR Support for Construction","2006-02-01","2006-12-05"]
["CFMGT_1550","UTR Support for Construction","2006-02-01","2007-03-20"]
["CFMGT_1600","Fire Protection Engineer","2005-12-05","2006-04-28",null,"2005-12-05"]
["CFMGT_2000","Reproduction - 30% Design","2005-08-22","2006-01-31",null,"2005-08-22","2006-01-31"]
["CFMGT_2001","EP Produce Sampling Plan (remaining)","2005-05-02","2005-06-30",null,"2005-05-02","2005-06-30"]
["CFMGT_2005","Reproduction - 60% and 100% Design","2006-01-23","2006-06-30",null,"2006-01-23"]
["CFMGT_2006","EP Develop Statement of Work (remaining)","2005-05-02","2005-06-30",null,"2005-05-02","2005-06-30"]
["CFMGT_2010","Additional ICE - 60% Review","2006-01-03","2006-01-31",null,"2006-01-03","2006-01-31"]
["CFMGT_2022","CF Management & Integration","2006-03-01","2006-04-25"]
["CFMGT_2025","Review Bids for EP Site Analysis","2005-08-01","2005-08-05",null,"2005-08-01","2005-08-05"]
["CFMGT_2030","AWARD: Contract for EP Site Analysis","2005-11-14","2005-11-14",null,"2005-11-14","2005-11-14"]
["CFMGT_2035","EP Site Analysis/Site Characterization","2005-11-15","2006-05-02",null,"2005-11-15"]
["CFMGT_2040","EP Excavated Material Disposition Plan","2006-02-01","2006-03-01"]
["CFMGT_2070","MTH - Structural & Electrical Design (LLP)","2005-05-17","2006-03-31",null,"2005-05-17"]
["CFMGT_2090","Mechanical Design Consultancy","2005-09-26","2006-04-28",null,"2005-09-26"]
["CFMGT_2093","AWARD: Structural & Electrical Design for LCLS","2006-02-13","2006-02-13"]
["CFMGT_2095","Structural & Electrical Design for LCLS","2006-02-14","2006-08-03"]
["CFMGT_2230","A&E Interim Support (cost growth)","2005-08-08","2005-08-26",null,"2005-08-08","2005-08-26"]
["CFMGT_2240","A&E Title 1 Reimbursables (cost growth)","2005-06-06","2005-06-30",null,"2005-06-06","2005-06-30"]
["CFMGT_LOE","CF LOE Complete","2009-04-01","2009-03-31"]
["CFMMF_2095","Additional A&E Title 2 Design for MMF","2005-08-08","2005-08-26",null,"2005-08-08","2005-08-26"]
["CFMMF_2096","MTH Engineering Design for MMF LLP (Committed)","2005-05-02","2005-05-27",null,"2005-05-02","2005-05-27"]
["CFMMF_2116","MTH Electrical Engrg Svc - Feeder B081","2005-06-07","2005-09-30",null,"2005-06-07","2005-09-30"]
["CFMMF_2700","CF - Drawing Implementation to SLAC System- MMF","2006-03-21","2006-05-23"]
["CFMMF_3005","MMF Relocate Stores - SLAC","2005-05-09","2005-08-31",null,"2005-05-09","2005-08-31"]
["CFMMF_3040","AWARD: MMF Major Electrical Equip (LLP)","2006-01-17","2006-01-17",null,"2006-01-17","2006-01-17"]
["CFMMF_3045","Receive  B81 Transformer (LLP)","2005-08-29","2005-08-29",null,"2005-08-29","2005-08-29"]
["CFMMF_3047","Receive  B81 MCC  (LLP)","2005-11-07","2005-11-07",null,"2005-11-07","2005-11-07"]
["CFMMF_3050","SLAC - MMF Major Elec Equipment","2006-03-15","2006-03-28"]
["CFMMF_3055","SLAC - Install MMF Major Elec Equip (LLP)","2006-01-25","2006-03-14",null,"2006-01-25"]
["CFMMF_3060","CF - MMF Modify Bldg Lighting & Power","2005-09-01","2006-01-31",null,"2005-09-01","2006-01-31"]
["CFMMF_3075","AE Engineering Support Title 3 - MMF","2005-08-01","2006-02-28",null,"2005-08-01"]
["CFMMF_3110","MMF - Kickoff Meeting","2005-08-22","2005-08-22",null,"2005-08-22","2005-08-22"]
["CFMMF_3165","CF - Site Preparation","2005-09-01","2005-10-28",null,"2005-09-01","2005-10-28"]
["CFMMF_3173","AWARD: Building Commissioning MMF","2006-02-01","2006-02-01"]
["CFMMF_3175","CF Building Commissioning MMF","2006-02-21","2006-04-24"]
["CFMMF_3195","COMP: Magnetic Measure Facility Title 3","2006-05-24","2006-05-23"]
["CFMMF_3200","AVAIL: Beneficial Occupancy MMF","2006-04-12","2006-04-11"]
["CFMMF_4000","MMF - General Requirements","2005-09-01","2006-03-10",null,"2005-09-01"]
["CFMMF_4005","LLP - Structural Steel","2005-09-01","2005-11-18",null,"2005-09-01","2005-11-18"]
["CFMMF_4010","LLP - Fire Sprinkler","2006-01-12","2006-02-17",null,"2006-01-12"]
["CFMMF_4020","LLP - Mechanical AHUs","2005-09-26","2006-01-20",null,"2005-09-26","2006-01-20"]
["CFMMF_4030","LLP - Crane Equipment","2005-09-12","2006-01-23",null,"2005-09-12","2006-01-23"]
["CFMMF_4040","LLP - Mechanical EFs","2005-09-12","2006-01-31",null,"2005-09-12","2006-01-31"]
["CFMMF_4050","LLP - Doors, Frames & Hardware","2005-09-01","2005-12-21",null,"2005-09-01","2005-12-21"]
["CFMMF_4060","MMF - Site Mobilization","2005-08-30","2005-09-08",null,"2005-08-30","2005-09-08"]
["CFMMF_4070","MMF - Site Demolition","2005-09-07","2005-10-07",null,"2005-09-07","2005-10-07"]
["CFMMF_4073","MMF - Site Demolition - Safe-Off Gas","2005-09-20","2005-09-20",null,"2005-09-20","2005-09-20"]
["CFMMF_4075","MMF - Install protection @ Carousel","2005-09-06","2005-09-12",null,"2005-09-06","2005-09-12"]
["CFMMF_4078","MMF - Build New Demising Walls","2005-09-13","2005-09-30",null,"2005-09-13","2005-09-30"]
["CFMMF_4080","Building Shell - Footings","2005-10-10","2005-10-24",null,"2005-10-10","2005-10-24"]
["CFMMF_4100","Building Shell - MEP - install & layout","2005-10-04","2005-11-30",null,"2005-10-04","2005-11-30"]
["CFMMF_4110","Building Shell - MEP -Insulate High Bays","2005-10-21","2005-11-03",null,"2005-10-21","2005-11-03"]
["CFMMF_4120","Building Shell - MEP - install OH Piping","2005-10-06","2005-11-30",null,"2005-10-06","2005-11-30"]
["CFMMF_4130","Building Shell - MEP - Install Conduit","2005-10-10","2005-12-21",null,"2005-10-10","2005-12-21"]
["CFMMF_4140","Building Shell - Underground Utilities","2005-10-03","2005-12-21",null,"2005-10-03","2005-12-21"]
["CFMMF_4145","Change Order Requests","2005-12-05","2005-12-21",null,"2005-12-05","2005-12-21"]
["CFMMF_4150","Building Shell - Erect Steel","2005-10-03","2005-12-21",null,"2005-10-03","2005-12-21"]
["CFMMF_4160","Building Shell - Install Crane Support","2006-01-26","2006-02-17",null,"2006-01-26"]
["CFMMF_4170","Building Shell - SOG Concrete Patch","2005-10-10","2005-12-21",null,"2005-10-10","2005-12-21"]
["CFMMF_4175","Fill Void Under Concrete Slab","2005-12-05","2005-12-21",null,"2005-12-05","2005-12-21"]
["CFMMF_4178","Change Order Requests","2005-12-05","2005-12-21",null,"2005-12-05","2005-12-21"]
["CFMMF_4180","Building Shell - Install GV / Flashing","2006-01-23","2006-02-17",null,"2006-01-23"]
["CFMMF_4190","Building Shell - Install Metal Panels","2005-12-19","2006-01-20",null,"2005-12-19","2006-01-20"]
["CFMMF_4200","Building Shell - Install Exterior Door Frames","2006-01-26","2006-02-17",null,"2006-01-26"]
["CFMMF_4210","Building Shell - Install AHU & MAU/Ducting-Mech","2006-01-26","2006-02-17",null,"2006-01-26"]
["CFMMF_4215","Building Shell - Install AHU & MAU/Ducting-Elect","2006-01-26","2006-02-17",null,"2006-01-26"]
["CFMMF_4220","LAB TI - Frame Walls","2005-11-01","2005-11-11",null,"2005-11-01","2005-11-11"]
["CFMMF_4230","LAB TI - In Wall MEP Rough-In","2005-12-19","2006-01-31",null,"2005-12-19","2006-01-31"]
["CFMMF_4240","LAB TI - Install Finishes","2005-11-07","2006-02-17",null,"2005-11-07"]
["CFMMF_4250","LAB TI - Wall Construction","2006-01-03","2006-01-03",null,"2006-01-03","2006-01-03"]
["CFMMF_4255","LAB TI - Install T-Bar Ceiling","2005-11-07","2005-12-21",null,"2005-11-07","2005-12-21"]
["CFMMF_4260","LAB TI - Install Registers & Trim Fire Sprinkler","2006-01-04","2006-01-11",null,"2006-01-04","2006-01-11"]
["CFMMF_4270","LAB TI - Install Light Fixtures","2006-01-12","2006-01-17",null,"2006-01-12","2006-01-17"]
["CFMMF_4280","LAB TI - Install Ceiling Tile","2006-01-18","2006-01-20",null,"2006-01-18","2006-01-20"]
["CFMMF_4290","LAB TI - Seal Floors / Epoxy Floors","2006-01-23","2006-01-27",null,"2006-01-23","2006-01-27"]
["CFMMF_4295","Change Order Requests","2005-12-05","2006-01-27",null,"2005-12-05","2006-01-27"]
["CFMMF_4300","LAB TI - Finish ProcessPiping","2006-01-30","2006-02-17",null,"2006-01-30"]
["CFMMF_4305","Change Order Requests","2005-12-09","2006-01-27",null,"2005-12-09","2006-01-27"]
["CFMMF_4310","LAB TI - Finish MEP Trim","2006-02-21","2006-02-27"]
["CFMMF_4315","Relocate Electrical Conduit","2006-02-01","2006-01-31",null,null,"2006-01-31"]
["CFMMF_4318","Change Order Requests","2005-12-01","2006-01-27",null,"2005-12-01","2006-01-27"]
["CFMMF_4320","HVAC Startup & Commissioning","2006-01-26","2006-04-07",null,"2006-01-26"]
["CFMMF_4500","COMP: MMF Certificate of Occupancy","2006-04-10","2006-04-07"]
["CFMMF_5010","CF - Data & Voice Cabling","2006-01-03","2006-03-01",null,"2006-01-03"]
["CFMMF_5020","CF - Testing and Balancing","2006-03-29","2006-04-11"]
["CFMOB1000","Commence Sitework","2006-05-24","2006-05-23"]
["CFMOB1040","Mobilization","2006-05-24","2006-05-23"]
["CFMOB1100","SWPP & Site Construction Fencing","2006-05-24","2006-05-23"]
["CFNEH1100","Start Near Experimental Hall","2006-07-13","2006-07-12"]
["CFPC8020","Start Project As-Builts & O/M Manuals","2008-11-13","2008-11-12"]
["CFRY102020","Start Research Yard Modifications","2006-05-24","2006-05-23"]
["CFRYB_2215","MD Support For Title 2 Design (remaining)","2005-05-02","2005-11-30",null,"2005-05-02","2005-11-30"]
["CFRYC_2745","Kickoff Meeting - CM/GC","2005-10-19","2005-10-19",null,"2005-10-19","2005-10-19"]
["CFS20_2196","MTH Engineering Services for S 20 LLP (Commit)","2005-05-02","2005-05-31",null,"2005-05-02","2005-05-31"]
["CFS20_2198","Additional MTH Engineering Services for S-20 LLP","2005-08-08","2005-11-30",null,"2005-08-08","2005-11-30"]
["CFS20_2206","Additional A&E Title 2 Design for S20","2005-08-08","2005-08-26",null,"2005-08-08","2005-08-26"]
["CFS20_2800","Drawing Implementation to SLAC System- S20","2006-03-17","2006-06-05"]
["CFS20_3002","Remove Alcove Pump Room (remaining)","2005-05-02","2005-07-29",null,"2005-05-02","2005-07-29"]
["CFS20_3003","Temporary Power & Phone","2005-09-01","2005-11-30",null,"2005-09-01","2005-11-30"]
["CFS20_3013","Relocate RF Hut Piping","2005-10-03","2005-10-31",null,"2005-10-03","2005-10-31"]
["CFS20_3015","RF Hut Clear Area (remaining)","2005-05-02","2005-07-29",null,"2005-05-02","2005-07-29"]
["CFS20_3016","Receive S20 MtrCntlCntr - Hardware","2005-08-15","2005-08-15",null,"2005-08-15","2005-08-15"]
["CFS20_3017","Receive S20 SubStation - Hardware","2005-09-27","2005-09-27",null,"2005-09-27","2005-09-27"]
["CFS20_3040","Kick off  - Alcove/RF Hut","2005-08-22","2005-08-22",null,"2005-08-22","2005-08-22"]
["CFS20_3070","AE Engineering Support Title 3 - Alcove/RF Hut","2005-08-01","2006-02-28",null,"2005-08-01"]
["CFS20_3195","AVAIL: RF Hut Shell Beneficial Occupancy","2006-02-13","2006-02-10"]
["CFS20_3225","AWARD: Building Commissioning Alcove","2006-02-01","2006-02-01"]
["CFS20_3230","CF Building Commissioning Alcove","2006-02-16","2006-05-04"]
["CFS20_3250","COMP: Alcove Title 3","2006-06-06","2006-06-05"]
["CFS20_3260","AVAIL: Alcove Beneficial Occupancy","2006-03-28","2006-03-27"]
["CFS20_4000","S20 - General Requirement","2005-09-01","2006-03-10",null,"2005-09-01"]
["CFS20_4002","K10B - General Requirement","2005-09-13","2005-11-30",null,"2005-09-13","2005-11-30"]
["CFS20_4005","Site Mobilization","2005-08-30","2005-09-02",null,"2005-08-30","2005-09-02"]
["CFS20_4010","Site Construction - Demolition","2005-09-06","2005-11-09",null,"2005-09-06","2005-11-09"]
["CFS20_4020","Demolition - Electrical","2005-11-10","2005-11-11",null,"2005-11-10","2005-11-11"]
["CFS20_4030","Demolition - Mechanical","2005-12-05","2005-12-16",null,"2005-12-05","2005-12-16"]
["CFS20_4040","Structural - Footings & Grade Beams","2005-10-19","2005-11-09",null,"2005-10-19","2005-11-09"]
["CFS20_4050","Structural - SOG","2005-11-10","2005-12-21",null,"2005-11-10","2005-12-21"]
["CFS20_4060","Structural - Erect Struct Steel (Emerg Access)","2005-10-17","2005-12-12",null,"2005-10-17","2005-12-12"]
["CFS20_4070","Building Encl - Roof Decking/Insulate Ceiling","2005-12-05","2006-01-31",null,"2005-12-05","2006-01-31"]
["CFS20_4080","Building Enclosure - Door Frames","2005-12-19","2006-01-23",null,"2005-12-19","2006-01-23"]
["CFS20_4090","Overhead MEP - Mechanical","2006-01-17","2006-02-17",null,"2006-01-17"]
["CFS20_4095","Overhead MEP - Mechanical - LLP","2005-10-03","2005-10-31",null,"2005-10-03","2005-10-31"]
["CFS20_4100","Overhead MEP - Electrical","2005-11-14","2006-01-31",null,"2005-11-14","2006-01-31"]
["CFS20_4110","Wall Construction - Frame Walls","2005-11-21","2005-11-30",null,"2005-11-21","2005-11-30"]
["CFS20_4120","Wall Construction - MEP Rough-In","2005-12-19","2006-01-23",null,"2005-12-19","2006-01-23"]
["CFS20_4130","Wall Construction - Install Door Frames","2006-01-03","2006-01-04",null,"2006-01-03","2006-01-04"]
["CFS20_4140","Wall Construction - Insulate Walls","2006-01-23","2006-01-27",null,"2006-01-23","2006-01-27"]
["CFS20_4150","Wall Construction - Rock Walls & Finish Walls","2006-01-17","2006-01-31",null,"2006-01-17","2006-01-31"]
["CFS20_4160","T-Bar Ceiling - Install T-Bar Ceiling","2006-01-17","2006-01-27",null,"2006-01-17","2006-01-27"]
["CFS20_4170","T-Bar Ceiling - Install Fixtures","2006-02-13","2006-02-15"]
["CFS20_4180","T-Bar Ceiling - Install Diffusers & Fire Sprinkl","2006-02-13","2006-02-21"]
["CFS20_4190","T-Bar Ceiling - Trim Vesda","2006-02-15","2006-02-16"]
["CFS20_4200","T-Bar Ceiling - Drop Tile","2006-02-17","2006-02-21"]
["CFS20_4210","Finishes - Paint Walls","2006-02-17","2006-02-24"]
["CFS20_4220","Finishes - Install Trim MEP","2006-02-27","2006-02-28"]
["CFS20_4230","Finishes - Install Floor Treatment","2006-03-01","2006-03-03"]
["CFS20_4240","Finishes - Install Doors & Hardware","2006-02-27","2006-02-28"]
["CFS20_4250","Finishes - Install Overhead Crane","2006-02-27","2006-02-28"]
["CFS20_4260","RF Hut - Install Frame Walls/Ceiling","2005-11-08","2005-11-14",null,"2005-11-08","2005-11-14"]
["CFS20_4270","RF Hut - Set Door Frame","2005-12-21","2005-12-21",null,"2005-12-21","2005-12-21"]
["CFS20_4280","RF Hut - MEP Wall Rough-In","2006-01-03","2006-01-09",null,"2006-01-03","2006-01-09"]
["CFS20_4290","RF Hut - Install Insulation","2006-01-23","2006-01-27",null,"2006-01-23","2006-01-27"]
["CFS20_4300","RF Hut - Install Finishes","2006-01-17","2006-01-31",null,"2006-01-17","2006-01-31"]
["CFS20_4310","RF Hut - Install Door Hardware","2006-01-03","2006-01-03",null,"2006-01-03","2006-01-03"]
["CFS20_4315","Change Order Requests","2005-12-01","2006-02-10",null,"2005-12-01"]
["CFS20_4320","RF Hut - Install Light Fixtures & Vesda","2006-01-03","2006-01-31",null,"2006-01-03","2006-01-31"]
["CFS20_4330","RF Hut - Set Fan Coil & connect Piping","2006-01-26","2006-02-10",null,"2006-01-26"]
["CFS20_4340","Klystron Gallery - Chilled Water Piping","2006-01-03","2006-01-31",null,"2006-01-03","2006-01-31"]
["CFS20_4350","Klystron Gallery - Cable Trays","2006-01-03","2006-01-31",null,"2006-01-03","2006-01-31"]
["CFS20_4360","Equipment Yard - Demolition","2005-10-12","2005-10-18",null,"2005-10-12","2005-10-18"]
["CFS20_4370","Structural - Equipment Pads/Footings","2005-10-19","2005-11-09",null,"2005-10-19","2005-11-09"]
["CFS20_4380","Structural - Structural Support","2005-12-13","2005-12-21",null,"2005-12-13","2005-12-21"]
["CFS20_4390","Equipment Yard - Install Groundiing","2005-11-10","2005-11-16",null,"2005-11-10","2005-11-16"]
["CFS20_4400","Equipment Yard - Patch AC","2005-11-30","2006-01-06",null,"2005-11-30","2006-01-06"]
["CFS20_4410","K10B - Demolition","2005-09-13","2005-09-16",null,"2005-09-13","2005-09-16"]
["CFS20_4420","K10B - Underground Electrical","2005-09-13","2005-10-31",null,"2005-09-13","2005-10-31"]
["CFS20_4430","K10B - Concrete Foundations & SOG","2005-09-13","2005-09-23",null,"2005-09-13","2005-09-23"]
["CFS20_4435","Change Order Requests","2005-12-01","2005-12-21",null,"2005-12-01","2005-12-21"]
["CFS20_4440","K10B - Install Equipment","2005-10-10","2005-11-23",null,"2005-10-10","2005-11-23"]
["CFS20_4450","K10B - Fencing & Grating","2005-10-03","2005-10-21",null,"2005-10-03","2005-10-21"]
["CFS20_4455","COMP: K10B Stubstation","2006-02-27","2006-02-24"]
["CFS20_4460","Install HVAC System - Mechanical","2005-12-19","2006-01-31",null,"2005-12-19","2006-01-31"]
["CFS20_4470","HVAC System - Install Electrical","2006-01-19","2006-02-10",null,"2006-01-19"]
["CFS20_4480","Install Chilled Water System - Mechanical","2005-12-19","2006-01-26",null,"2005-12-19","2006-01-26"]
["CFS20_4490","Chilled Water System - Install Electrical","2006-01-05","2006-02-10",null,"2006-01-05"]
["CFS20_4500","Install Hot Water System - Mechanical","2006-01-03","2006-01-26",null,"2006-01-03","2006-01-26"]
["CFS20_4510","Hot Water System - Install Electrical","2006-01-27","2006-02-10",null,"2006-01-27"]
["CFS20_4520","Install Compressed Air & City Water","2006-02-01","2006-01-10",null,null,"2006-01-10"]
["CFS20_4530","Injector Housing - Layout & Concrete Demo","2005-11-28","2006-01-06",null,"2005-11-28","2006-01-06"]
["CFS20_4535","Change Order Requests","2005-12-01","2006-02-28",null,"2005-12-01"]
["CFS20_4540","K10B - Set Equipment","2005-09-26","2005-10-07",null,"2005-09-26","2005-10-07"]
["CFS20_4542","K10B -  Install Finishes","2005-11-01","2005-11-01",null,"2005-11-01","2005-11-01"]
["CFS20_4545","Injector Housing - Modify Stairs","2005-12-07","2005-12-21",null,"2005-12-07","2005-12-21"]
["CFS20_4548","Change order Requests","2005-12-01","2006-02-28",null,"2005-12-01"]
["CFS20_4550","Injector Housing - Install Sump","2006-01-09","2006-01-13",null,"2006-01-09","2006-01-13"]
["CFS20_4555","Injector Housing - Install LCWS & R Piping","2006-01-24","2006-01-30",null,"2006-01-24","2006-01-30"]
["CFS20_4560","Injector Housing - Install Electrical","2006-01-03","2006-02-10",null,"2006-01-03"]
["CFS20_4565","K10B - Change Order Requests","2005-12-05","2005-12-21",null,"2005-12-05","2005-12-21"]
["CFS20_4570","Injector Housing - Paint Surfaces","2005-12-05","2005-12-21",null,"2005-12-05","2005-12-21"]
["CFS20_4575","Change Order Requests","2006-01-09","2006-01-31",null,"2006-01-09","2006-01-31"]
["CFS20_4577","DCC Controls Installation","2005-12-01","2006-02-27",null,"2005-12-01"]
["CFS20_4578","Change Order Requests","2005-12-01","2006-03-27",null,"2005-12-01"]
["CFS20_4580","Start-up & Commissioning - Mechanical","2006-03-07","2006-03-13"]
["CFS20_4590","Start-up & Commissioning - Electrical","2006-02-16","2006-03-15"]
["CFS20_4600","Start-up & Commissioning - HVAC Balancing","2006-03-07","2006-03-24"]
["CFS20_4610","COMP: Sector 20 Certificate of Occupancy","2006-03-28","2006-03-27"]
["CFUH01020","Start Undulator Hall","2006-08-25","2006-08-24"]
["CFXRY1220","Start X-Ray Transport & Diagnostic","2007-01-04","2007-01-03"]
["IJ0101A","Management - PED","2005-06-01","2005-09-30",null,"2005-06-01","2005-09-30"]
["IJ0101B","Management - CONST","2005-10-03","2005-12-30",null,"2005-10-03","2005-12-30"]
["IJ0101C","Cost Account Managers - PED","2005-06-01","2005-09-30",null,"2005-06-01","2005-09-30"]
["IJ0101D","Cost Account Managers - CONST","2005-10-03","2005-12-30",null,"2005-10-03","2005-12-30"]
["IJ0101S","Computers - PED","2005-06-01","2005-09-30",null,"2005-06-01","2005-09-30"]
["IJ0101S1","Computers - CONST","2005-10-03","2005-12-30",null,"2005-10-03","2005-12-30"]
["IJ0101S10","SLAC Place Order Computers - PED","2005-10-03","2005-11-30",null,"2005-10-03","2005-11-30"]
["IJ0101S20","RCV: Computers - PED","2005-12-01","2005-11-30",null,"2005-12-01","2005-11-30"]
["IJ0101S21","SLAC Place Order Computers - CONST","2005-11-01","2005-12-30",null,"2005-11-01","2005-12-30"]
["IJ0101S22","RCV: Computers - CONST","2005-12-01","2005-11-30",null,"2005-12-01","2005-11-30"]
["IJ0101T","Travel - PED","2005-06-01","2005-09-30",null,"2005-06-01","2005-09-30"]
["IJ0101T1","Travel - CONST","2005-10-03","2005-12-30",null,"2005-10-03","2005-12-30"]
["IJ0101U","Materials & Supplies - PED","2005-06-01","2005-09-30",null,"2005-06-01","2005-09-30"]
["IJ0101U1","Materials & Supplies - CONST","2005-10-03","2005-12-30",null,"2005-10-03","2005-12-30"]
["IJ02","INJECTOR CONTROLS SUBSYSTEM SUMMARY","2005-06-01","2007-12-13",null,"2005-06-01"]
["IJ0202","LLRF CONTROLS SUMMARY","2006-02-01","2007-05-21"]
["IJ02020055","Procure controls H/W (incl digitizer) and cables","2006-07-03","2006-09-29"]
["IJ02020075","RCV: controls H/W (incl digitizer) and cables","2006-10-02","2006-10-02"]
["IJ02020129","Write RF Software and Documentation - PED","2006-07-03","2006-10-05"]
["IJ02020130","Build RF Hardware & Write Documentation","2006-10-17","2006-11-06"]
["IJ02020131","Write RF Software and Documentation - CONST","2006-10-06","2006-10-26"]
["IJ02020141","Integrate & Test RF Control","2006-11-07","2007-03-07"]
["IJ02020180","AVAIL: LLRF Gun Controls Ready to Integrate","2006-11-07","2006-11-06"]
["IJ02020240","Procure Controls H/W (incl Digitizer) and Cables","2006-07-03","2006-09-29"]
["IJ02020250","SLAC Place Order Controls H/W (incl Digitizer)","2006-07-03","2006-08-14"]
["IJ02020303","RCV: Procured parts - LLRF L0-1 Controls","2006-08-15","2006-08-14"]
["IJ02020304","Build RF Control H/W and Write Docmntn - PED","2006-08-15","2007-01-25"]
["IJ02020306","Build RF Control H/W and Write Docmntn - CONST","2007-04-04","2007-04-17"]
["IJ02020307","Write RF Control S/W and Docmntn","2006-07-03","2006-08-14"]
["IJ02020308","Integrate and Test LLRF L0-1","2007-04-18","2007-05-21"]
["IJ02020365","AVAIL: LLRF L0-1 Controls Ready to Install","2007-05-22","2007-05-21"]
["IJ02020425","Procure Controls H/W (incl Digitizer) and Cables","2006-07-03","2006-09-29"]
["IJ02020435","SLAC Place Order Controls H/W (incl Digitizer)","2006-07-03","2006-08-14"]
["IJ02020495","RCV: Procured parts","2006-10-02","2006-09-29"]
["IJ02020505","AVAIL: Hardware for Install in RF Hut","2007-01-04","2007-01-03"]
["IJ02020508","Build RF Hardware and Write Documentation","2006-10-02","2007-01-03"]
["IJ02020516","Write RF Software Documentation","2006-07-03","2006-08-14"]
["IJ02020526","Integrate and Test LLRF L0-2","2007-01-04","2007-02-07"]
["IJ02020555","AVAIL: LLRF L0-2 Controls Ready to Install","2007-02-08","2007-02-07"]
["IJ02020615","Procure Controls H/W (incl Digitizer) and Cables","2006-07-03","2006-09-29"]
["IJ02020625","SLAC Place Order Controls H/W (incl Digitizer)","2006-02-01","2006-02-13"]
["IJ02020680","RCV: Procured parts","2006-10-02","2006-09-29"]
["IJ02020684","Build RF Hardware and Write Documentation","2006-10-02","2007-01-03"]
["IJ02020689","Write RF Software and Documentation","2006-07-03","2006-07-03"]
["IJ02020734","Integrate and Test RF Control","2007-01-04","2007-02-08"]
["IJ02020735","AVAIL: LLRF L1 S-Band Contrls Ready to Integrate","2007-02-09","2007-02-08"]
["IJ02020795","Procure Controls H/W (incl Digitizer) and Cables","2006-07-03","2006-09-29"]
["IJ02020805","SLAC Place Order Controls H/W (incl Digitizer)","2006-07-03","2006-08-14"]
["IJ02020860","RCV: Procured parts","2006-10-02","2006-09-29"]
["IJ02020864","Build RF Hardware and Write Documentation","2006-10-02","2007-01-03"]
["IJ02020870","Write RF Software and Documentation","2006-07-03","2007-01-03"]
["IJ02020880","Integrate and Test RF Control","2007-01-04","2007-02-08"]
["IJ02020915","AVAIL: LLRF L1 X-Band Contrls Ready to Integrate","2007-02-09","2007-02-08"]
["IJ02021830","Procure Contros H/W (incl Digitizer) and Cables","2006-07-03","2006-09-29"]
["IJ02021840","SLAC Place Order Contros H/W (incl Digitizer)","2006-07-03","2006-08-14"]
["IJ02021900","RCV: Procured parts","2006-10-02","2006-09-29"]
["IJ02021904","Build RF Hardware and Write Documentation","2006-10-02","2006-10-02"]
["IJ02021910","AVAIL: Hardware for Install in RF Hut","2006-10-03","2006-10-02"]
["IJ02021919","Write RF Sortware and Documentation","2006-07-03","2007-01-03"]
["IJ02021931","Integrate and Test RF Control","2006-10-03","2007-01-03"]
["IJ02021935","AVAIL:LLRF Tranv Cav Controls Ready to Install","2007-01-04","2007-01-03"]
["IJ0203","E-BEAM DIAG DISPLAY & CONTROLS SUMMARY","2006-06-05","2007-07-13"]
["IJ020302","CONTROLS - TOROIDS (5) SUMMARY","2006-07-03","2007-04-13"]
["IJ02030216","Procure 5 Sets Toroid Contrls H/W and Cables","2006-07-03","2006-08-30"]
["IJ02030238","RCV: Procured parts - Toroid Controls","2006-08-31","2006-08-31"]
["IJ02030243","Build Toroid Hardware and Write Documentatin","2006-11-29","2007-02-20"]
["IJ02030244","Write Toroid Software and Documentation","2006-07-03","2006-09-07"]
["IJ02030250","Integrate Software and Hardware","2007-02-21","2007-04-13"]
["IJ02030256","AVAIL: Toroid Controls Ready for Install","2007-04-16","2007-04-13"]
["IJ02030316","Procure 4 Sets Faraday Cup Controls H/W & Cables","2006-10-26","2007-01-10"]
["IJ02030344","RCV: Procured parts - Faraday Cup Controls","2007-01-11","2007-01-11"]
["IJ02030356","Build H/W and Write Docmtn Faraday Cup Cntrl (4)","2007-01-12","2007-01-12"]
["IJ02030357","Write S/W and Docmtn Faraday Cup Control (4)","2006-10-25","2006-10-25"]
["IJ02030358","Integrate and Test Faraday Cup Control (4)","2007-01-16","2007-02-20"]
["IJ02030362","AVAIL: Faraday Cup Controls Ready for Install","2007-02-21","2007-02-20"]
["IJ02030416","Procure 1 set Tune-up Dump Controls H/W","2006-06-05","2006-08-02"]
["IJ02030422","RCV: Procured parts - Tune-Up Dump Controls","2006-08-03","2006-08-02"]
["IJ02030424","Write S/W - Tune-Up Dump Controls","2006-06-05","2006-07-31"]
["IJ02030426","Write Docs - Tune-Up Dump Controls","2006-06-05","2006-07-31"]
["IJ02030430","Assemble Tune-up Dump Controls","2006-08-03","2006-08-09"]
["IJ02030433","Integrate and Test Tune Up Dump","2006-08-10","2006-08-23"]
["IJ02030436","SLAC Place Order - Tune-Up Dump Controls","2006-06-05","2006-06-07"]
["IJ02030440","AVAIL: Tune-Up Dump Controls Ready for Install","2006-08-24","2006-08-23"]
["IJ02030516","Proc 11 sets Profile Mntr Cntrls H/W & Cables","2006-07-03","2006-08-30"]
["IJ02030526","SLAC Place Order - Profile Monitor Controls","2006-07-03","2006-08-14"]
["IJ02030556","RCV: Procured parts - Profile Monitor Controls","2006-08-31","2006-08-31"]
["IJ02030569","Build H/W and Write Docmntn Profile Monitor (11)","2006-09-01","2006-11-28"]
["IJ02030570","Write S/W and Docmntn Profile Monitors (11)","2006-07-03","2006-08-14"]
["IJ02030571","Integrate and Test Profile Monitors","2006-11-29","2007-03-09"]
["IJ02030574","AVAIL:Profile Monitor Controls Ready for Install","2007-03-12","2007-03-09"]
["IJ02030630","Build H/W and Write Docmntn for E/O Diagnostics","2006-06-27","2006-11-15"]
["IJ02030631","Write S/W and Docmtn E/O Diagnostics","2006-10-03","2007-03-12"]
["IJ02030632","Integrate and Test E/O Diagnostics Controls H/W","2007-01-17","2007-07-13"]
["IJ02030636","AVAIL: EO Diagnostic Controls Ready for Install","2007-07-16","2007-07-13"]
["IJ02030718","Proc 21 sets BPM Controls H/W and Cables","2006-07-05","2006-09-27"]
["IJ02030726","RCV: Procured parts - BPM Proc Module Cntrls","2006-09-28","2006-09-28"]
["IJ02030728","SLAC Place Order 21 sets BPM Ctrls H/W &Cables","2006-07-05","2006-08-15"]
["IJ02030738","Build H/W and Write Docmntn BPMs (21)","2006-09-29","2006-10-26"]
["IJ02030740","Integrate and Test BPM Controls","2006-10-27","2006-11-27"]
["IJ02030744","AVAIL:BPM Proc Module Controls Ready for Install","2006-11-28","2006-11-27"]
["IJ02030747","Procure BLM Controls Hdwr/Eq","2006-07-05","2006-08-01"]
["IJ02030767","RCV: BLM Controls Hdwr/Eq","2006-08-02","2006-08-02"]
["IJ0204","LASER CONTROLS SUMMARY","2005-09-01","2006-07-21",null,"2005-09-01"]
["IJ02040201","Procure 1 set Gun Laser Controls H/W","2005-09-01","2006-03-01",null,"2005-09-01"]
["IJ02040205","SLAC Place Order - Gun Laser Controls","2006-02-01","2006-03-15"]
["IJ02040210","RCV: Procured parts - Gun Laser Controls","2006-03-16","2006-03-15"]
["IJ02040215","Integrate and Test Gun Laser Controls","2006-04-27","2006-07-21"]
["IJ02040220","AVAIL: Laser Cntrls ready for Test","2006-07-24","2006-07-21"]
["IJ0205","LASER HEATER CONTROLS SUMMARY","2007-04-24","2007-12-13"]
["IJ02050201","Procure 1 set Laser Heater Controls H/W","2007-04-24","2007-07-23"]
["IJ02050205","SLAC Place Order - Laser Heater Cntrls","2007-04-24","2007-05-14"]
["IJ02050210","RCV: procured parts - Laser Heater Cntrls","2007-07-24","2007-07-23"]
["IJ02050215","Integrate and Test Laser Heater Controls","2007-07-24","2007-12-13"]
["IJ02050220","AVAIL: Laser Heater Cntrls Ready for Install","2007-12-14","2007-12-13"]
["IJ0206","TIMING CONTROLS SUMMARY","2006-09-19","2006-10-31"]
["IJ02060060","Procure Master & Distributed Timing Controls H/W","2006-09-19","2006-10-30"]
["IJ02060080","RCV: Master & Distributed Timing Controls H/W","2006-10-31","2006-10-31"]
["IJ02060105","Procure 4 sets of Controls Wire Scanners","2006-07-03","2006-09-26"]
["IJ02060110","Build HW and Write SW for Injector Wire Scanners","2006-09-27","2006-10-24"]
["IJ02060120","Integrate and Test Controls Wire Scanners","2006-10-25","2006-11-21"]
["IJ02060130","AVAIL: Controls Wire Scanners Ready for Install","2006-11-22","2006-11-21"]
["IJ0207","VACUUM CONTROLS SUMMARY","2006-05-30","2006-11-13"]
["IJ02070070","Procure Vacuum Controls Hardware and Cables","2006-05-30","2006-08-25"]
["IJ02070080","SLAC Place Order Vacuum Ctrls Hardware & Cables","2006-05-30","2006-07-11"]
["IJ02070195","RCV: Vacuum Controls Hardware and Cables","2006-08-28","2006-08-28"]
["IJ02070202","Build Vacuum H/W and Write Docmntn","2006-08-29","2006-09-18"]
["IJ02070210","Write Vacuum Documentation","2006-05-30","2006-06-12"]
["IJ02070216","Integration and Test Vacuum Controls","2006-09-19","2006-11-13"]
["IJ02070235","AVAIL: Vacuum Control Modules Ready for Install","2006-11-14","2006-11-13"]
["IJ0208","SOFTWARE & CNTRLS INFRASTRUCTURE SUMMARY","2005-09-01","2007-04-26",null,"2005-09-01"]
["IJ02080300","Supervision of installation","2006-04-03","2006-05-12"]
["IJ02080301","SEM Installtn (wall barrd & two 20 A circuits)","2006-04-03","2006-04-28"]
["IJ02080310","Procure singlemode fiber","2006-05-01","2006-06-26"]
["IJ02080314","Fiber termination","2006-06-27","2006-07-25"]
["IJ02080326","Procure Cisco 3550-24 hubs (4)","2007-03-29","2007-04-26"]
["IJ02080330","AVAIL: Data Comm Circuits Active & Ready","2007-04-27","2007-04-26"]
["IJ02080346","RCV: Cisco 3550-24 hubs (4)","2007-04-27","2007-04-26"]
["IJ02080350","RCV: singlemode fiber","2006-06-27","2006-06-26"]
["IJ020804","COMPUTER, CRATES, S/W & LICENCES SUMMARY","2005-09-01","2006-07-21",null,"2005-09-01"]
["IJ02080401","Procure Infrastructure Comp, Crates H/W & Cable","2005-09-01","2006-07-21",null,"2005-09-01"]
["IJ02080405","SLAC Place Order Infrastr Comp, CratesH/W&Cable","2005-11-01","2006-03-15",null,"2005-11-01"]
["IJ02080410","RCV: Infrastructure Comp, Crates H/W & Cable","2006-07-24","2006-07-21"]
["IJ02080415","AVAIL: Computers & Crates Ready for Instl","2006-07-24","2006-07-21"]
["IJ0209","POWER SUPPLY CONTROLS SUMMARY","2006-07-18","2006-07-24"]
["IJ02090065","Integrate software & hardware","2006-07-18","2006-07-24"]
["IJ02090085","AVAIL: Power Supply Cntrls Ready for Install","2006-07-25","2006-07-24"]
["IJ0210","PPS, BCS, MPS CONTROLS SUMMARY","2005-06-23","2006-10-03",null,"2005-06-23"]
["IJ02100065","Write S/W Docmtn for Power Supply Controls","2005-06-23","2006-03-08",null,"2005-06-23"]
["IJ02100070","Integrate and Test Power Supply Controls","2006-09-06","2006-10-03"]
["IJ02100085","AVAIL: PPS, BCS, MPS control software","2006-10-04","2006-10-03"]
["IJ03","INJECTOR LASERS SUMMARY","2004-10-16","2008-03-11",null,"2004-10-16"]
["IJ0301","DRIVE LASER R&D SUMMARY","2005-05-02","2006-01-30",null,"2005-05-02","2006-01-30"]
["IJ03010025","UV conversion tests","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ03010030","Analysis and final report (UV convers)","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["IJ03010045","Analysis and final report (Pulse Shaping)","2005-05-02","2005-05-05",null,"2005-05-02","2005-05-05"]
["IJ03010050","COMP: UV conversion R&D","2006-01-31","2006-01-30",null,"2006-01-31","2006-01-30"]
["IJ0302","DRIVE LASER SYSTEM SUMMARY","2004-10-16","2006-06-05",null,"2004-10-16"]
["IJ03020075","AWARD: Contract for Drive Laser","2005-06-27","2005-06-27",null,"2005-06-27","2005-06-27"]
["IJ03020080","Drive Laser-Milestone 1","2005-10-30","2005-10-31",null,"2005-10-30","2005-10-31"]
["IJ03020082","Reviews of Vendor's Progress","2005-10-03","2006-05-15",null,"2005-10-03"]
["IJ03020085","RCV: Drive Laser from Vendor","2006-05-16","2006-05-15"]
["IJ03020092","Drive Laser Design Review","2005-10-18","2005-10-20",null,"2005-10-18","2005-10-20"]
["IJ03020096","REQD: Sector 20 Alcove Available for Eq Instl","2006-04-03","2006-03-31"]
["IJ03020097","REQD: Optical Tables Available","2006-04-03","2006-03-31"]
["IJ03020102","Drive Laser-Milestone 2","2006-03-16","2006-03-15"]
["IJ03020112","Drive Laser-Milestone 3","2006-05-11","2006-05-11"]
["IJ03020115","AVAIL: Drive Laser for Integration","2006-06-06","2006-06-05"]
["IJ03020122","Drive Laser-Milestone 4","2006-06-05","2006-06-05"]
["IJ03020132","Vendor Fab, Assy & Test - Drive Laser-stage 1","2005-10-01","2005-10-30",null,"2005-10-01","2005-10-30"]
["IJ03020142","Vendor Fab, Assy & Test - Drive Laser-stage 2","2005-11-01","2006-03-15",null,"2005-11-01"]
["IJ03020152","Vendor Fab, Assy & Test - Drive Laser-stage 3","2006-03-16","2006-05-10"]
["IJ03020162","Vendor Fab, Assy & Test - Drive Laser-stage 4","2006-05-12","2006-06-02"]
["IJ0303","DRIVE LASER DIAGNOSTICS SUMMARY","2005-05-02","2006-11-20",null,"2005-05-02"]
["IJ03030005","Define Laser System Diagnostics Specs","2005-05-02","2005-08-30",null,"2005-05-02","2005-08-30"]
["IJ03030015","Eng & Design of Drive Laser Diagnostics (Timing)","2005-09-01","2006-03-15",null,"2005-09-01"]
["IJ03030025","COMP: Drive Laser Diagnostics Eng & Design","2006-03-16","2006-03-15"]
["IJ03030030","Procure Streak Camera","2005-12-30","2006-04-14",null,"2005-12-30"]
["IJ03030035","Procure Oscillator Diagnostics","2006-03-02","2006-05-24"]
["IJ03030037","RCV:  Oscillator Diagnostics","2006-05-25","2006-05-25"]
["IJ03030040","Procure Preamplifier Diagnostics","2006-03-02","2006-05-24"]
["IJ03030042","RCV:  Preamplifier Diagnostics","2006-06-09","2006-06-09"]
["IJ03030045","Procure Final Amplifier Diagnostics","2006-03-16","2006-06-08"]
["IJ03030047","RCV:  Final Amplifier Diagnostics","2006-06-09","2006-06-09"]
["IJ03030050","Procure UV Conversion Diagnostics","2005-09-25","2006-02-15",null,"2005-09-25"]
["IJ03030055","RCV: Drive Laser Diagnostics & Streak Camera","2006-08-14","2006-08-11"]
["IJ03030060","Assemble & Checkout: Drive Laser Diagnostics","2006-08-14","2006-11-20"]
["IJ03030065","AVAIL: Drive Laser Diagnostics for Integ","2006-11-21","2006-11-20"]
["IJ03030070","SLAC Place Order Diagnostics","2006-06-09","2006-08-11"]
["IJ03030075","RCV: Streak Camera","2006-04-17","2006-04-17"]
["IJ03030080","Award for the Streak Camera","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ03030085","Eng &Design of Drive Laser Diagnostics (general)","2005-08-15","2006-03-01",null,"2005-08-15"]
["IJ03030090","Evaluate the proposals for the streak camera","2005-09-01","2005-09-20",null,"2005-09-01","2005-09-20"]
["IJ0304","TIMING STABILITY MONITORING SUMMARY","2005-09-01","2006-06-22",null,"2005-09-01"]
["IJ03040005","Define Timing stability specs","2005-09-01","2005-11-30",null,"2005-09-01","2005-11-30"]
["IJ03040010","Eng & Dsn of Timing Stability Monitoring App","2006-03-21","2006-05-15"]
["IJ03040015","Proc Timing Stability Apparatus","2005-12-01","2006-03-29",null,"2005-12-01"]
["IJ03040020","RCV: Timing stability Monitoring Apparatus","2006-03-30","2006-03-29"]
["IJ03040025","Assemble & C/O: Timing Stability Mon Apparatus","2006-03-30","2006-06-22"]
["IJ03040030","AVAIL: Timing Stability Monitoring Apparatus","2006-06-23","2006-06-22"]
["IJ03040035","SLAC Place Order Timing Stability Apparatus","2006-02-01","2006-03-15"]
["IJ03040040","Eng&Dsn of the Osc timing Stability measurement","2005-12-01","2006-02-28",null,"2005-12-01"]
["IJ0305","STEERING STABILITY FEEDBACK & MSMTS SUMMARY","2005-08-01","2006-03-24",null,"2005-08-01"]
["IJ03050005","Define Steering stability specs","2005-08-01","2005-09-30",null,"2005-08-01","2005-09-30"]
["IJ03050030","Eng & Dsn of Steering Stability Measurement","2005-08-15","2006-03-20",null,"2005-08-15"]
["IJ03050045","COMP: Steering Stability Meas Engr & Design","2006-03-21","2006-03-20"]
["IJ03050060","Procure Steering Stability Apparatus","2005-10-01","2006-03-24",null,"2005-10-01"]
["IJ03050065","RCV: Steering Stability Apparatus","2006-03-27","2006-03-24"]
["IJ03050070","SLAC Place Order Steering Stability Apparatus","2005-10-01","2006-03-15",null,"2005-10-01"]
["IJ03050090","Assemble & Checkout: Steering Stabilization App","2006-01-01","2006-03-15",null,"2006-01-01"]
["IJ03050125","AVAIL:Steering Stability Apparatus for Install","2006-03-16","2006-03-15"]
["IJ0306","PREAMPLIFIER LOW PWR COMP SUMMARY","2006-03-16","2006-09-18"]
["IJ03060000","Define PreAmplifier Low Power Comp Specs","2006-03-16","2006-03-29"]
["IJ03060005","Design PreAmplifier Low Power Comp","2006-03-30","2006-05-24"]
["IJ03060010","COMP: PreAmplifier Low Power Comp Design","2006-05-25","2006-05-24"]
["IJ03060065","Procure Low Power Compressor System Parts","2006-05-25","2006-08-18"]
["IJ03060070","RCV: Low Power Compressor Parts","2006-08-21","2006-08-18"]
["IJ03060075","Fab (InHouse): Custom Low Power Compressor Parts","2006-05-25","2006-06-22"]
["IJ03060085","Assemble: Low Power Compressor","2006-08-21","2006-09-18"]
["IJ03060090","AVAIL: Low Power Compressor for Integration","2006-09-19","2006-09-18"]
["IJ0307","TRANSPORT TO TUNNEL & RELAY OPTICS SUMMARY","2005-08-01","2006-01-30",null,"2005-08-01","2006-01-30"]
["IJ03070000","Define Beam path, Beam Properties & Model Xport","2005-08-01","2005-08-30",null,"2005-08-01","2005-08-30"]
["IJ03070005","Eng & Dsn of  Vertical Transport Tube","2005-08-01","2005-08-30",null,"2005-08-01","2005-08-30"]
["IJ03070010","COMP: Beam tube enclosure engr & Dsn","2005-08-31","2005-08-30",null,"2005-08-31","2005-08-30"]
["IJ03070015","Procure Material and Parts","2005-09-01","2005-12-30",null,"2005-09-01","2005-12-30"]
["IJ03070017","RCV: Material and Parts","2005-10-01","2005-12-30",null,"2005-10-01","2005-12-30"]
["IJ03070023","AVAIL: Transport Tube for Installation","2005-10-01","2005-09-30",null,"2005-10-01","2005-09-30"]
["IJ03070025","Define Spatial Filter(Vacuum) & Opt Relay","2005-08-15","2005-09-30",null,"2005-08-15","2005-09-30"]
["IJ03070030","Eng & Dsn of Spatial Filter & Opt Relay","2005-09-16","2005-10-30",null,"2005-09-16","2005-10-30"]
["IJ03070035","COMP: Spatial Filter & Opt Relay Eng & Dsn","2005-10-31","2005-10-30",null,"2005-10-31","2005-10-30"]
["IJ03070040","FAB (inhouse): Custom Spatial Filter Hardware","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ03070045","RCV: Custom Spatial Filter Hardware","2006-01-31","2006-01-30",null,"2006-01-31","2006-01-30"]
["IJ03070050","Procure Spatial Filter & Opt Relay Parts","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ03070055","RCV: Spatial Filter & Opt Relay Parts","2006-01-31","2006-01-30",null,"2006-01-31","2006-01-30"]
["IJ03070060","Assemble: Spatial Filter & Opt Relay","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ03070065","AVAIL: Spatial Filter & Opt Relays for Integ","2006-01-31","2006-01-30",null,"2006-01-31","2006-01-30"]
["IJ03070070","SLAC Place Order Custom Spatial Filter Hardware","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["IJ03070075","SLAC Place Order Material and Parts","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["IJ03070080","Design of Storage and Installation Fixtures","2005-08-01","2005-09-30",null,"2005-08-01","2005-09-30"]
["IJ03070085","Write Installation Procedure","2005-08-15","2005-10-20",null,"2005-08-15","2005-10-20"]
["IJ03070090","Dsn routing system for lsr heater transport","2005-10-21","2005-12-30",null,"2005-10-21","2005-12-30"]
["IJ03070095","Release Drawings - transport tube","2005-08-15","2005-09-30",null,"2005-08-15","2005-09-30"]
["IJ03070105","Release drawings - spatial filter","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ0308","UV LAUNCH,CONDITIONING & DIAGNOSTICS SUMMARY","2005-08-01","2006-09-19",null,"2005-08-01"]
["IJ03080010","Design UV Beam Xport & Launch Optics","2005-08-01","2005-08-30",null,"2005-08-01","2005-08-30"]
["IJ03080015","Design UV Beam Steering Stabilization App","2005-08-15","2006-03-30",null,"2005-08-15"]
["IJ03080020","Design UV Spatial Profile Shaper","2005-08-15","2006-01-30",null,"2005-08-15","2006-01-30"]
["IJ03080025","Eng & Dsn of Pulse Energy Control","2005-12-01","2006-03-20",null,"2005-12-01"]
["IJ03080030","Eng & Dsn of UV Diagnostic","2005-08-01","2006-03-01",null,"2005-08-01"]
["IJ03080035","COMP: UV Launch,Conditioning & Diag engr & Dsn","2006-03-31","2006-03-30"]
["IJ03080040","FAB (inhouse): Custom Parts","2006-03-31","2006-04-27"]
["IJ03080045","Procure UV Launch,Conditioning & Diag HW","2005-12-01","2006-03-15",null,"2005-12-01"]
["IJ03080050","RCV: UV Launch,Conditioning & Diag HW","2006-01-01","2006-02-01",null,"2006-01-01"]
["IJ03080055","Assemble & C/O: UV Launch & Conditioning System","2006-04-28","2006-08-21"]
["IJ03080060","AVAIL: UV Launch & Conditioning System","2006-09-20","2006-09-19"]
["IJ0309","LOAD LOCK TRANSPORT SYSTEM SUMMARY","2006-08-17","2007-04-26"]
["IJ03090000","Define Load Lock Transport System Specs","2006-08-17","2006-09-14"]
["IJ03090005","Eng & Dsn of Load Lock Transport System","2006-09-15","2006-11-09"]
["IJ03090035","COMP: Load Lock Transport System Engrg & Dsn","2006-11-10","2006-11-09"]
["IJ03090040","FAB (inhouse): Custom Load Lock Transport Sys HW","2006-11-10","2007-01-09"]
["IJ03090042","RCV: Custom Load Lock Transport Sys HW","2007-01-10","2007-01-09"]
["IJ03090045","Procure Load Lock Transport Sys Parts","2006-11-10","2007-02-22"]
["IJ03090050","RCV: Load Lock Transport Sys Parts","2007-02-23","2007-02-22"]
["IJ03090052","Install transport tubes and supports","2007-02-23","2007-03-15"]
["IJ03090055","Assemble, Integ & C/O:Load Lock Transport System","2007-03-16","2007-04-26"]
["IJ03090060","AVAIL: Load Lock Transport System","2007-04-27","2007-04-26"]
["IJ0325","VISIBLE OPTICAL TRANSPORT & DIAG SUMMARY","2006-05-16","2007-01-09"]
["IJ03250000","Define Visible Beam properties, Beam path/model","2006-05-16","2006-05-30"]
["IJ03250005","Define Visible Beam transport Diagnostics Rqmts","2006-05-31","2006-06-20"]
["IJ03250015","Design Visible Beam Transport Optics & Encl","2006-06-21","2006-07-19"]
["IJ03250025","Design Visible Beam Transport Diagnostics","2006-07-20","2006-08-16"]
["IJ03250035","COMP: Visible Beam transport Optics & encl engr","2006-07-20","2006-07-19"]
["IJ03250040","COMP: Visible Beam transport Diagnostics engr &","2006-08-17","2006-08-16"]
["IJ03250045","FAB (inhouse): Visible Beam Transport Tube","2006-10-13","2006-11-09"]
["IJ03250050","FAB (inhouse):Custom Visible Beam Xport Opt Supt","2006-10-13","2006-11-09"]
["IJ03250055","Procure Transport Tube Material","2006-07-20","2006-10-12"]
["IJ03250060","RCV: Procured Transport Tube Material","2006-10-13","2006-10-12"]
["IJ03250065","Procure Visible Beam Transport Optics & Diag HW","2006-07-20","2006-10-12"]
["IJ03250070","RCV: Visible Beam Transport Optics & Diag HW","2006-10-13","2006-10-12"]
["IJ03250085","Assemble: Visible Beam Transport Optics & Encl","2006-11-10","2006-12-11"]
["IJ03250100","Assemble: Visible Beam transport diagnostics","2006-12-12","2007-01-09"]
["IJ03250120","AVAIL: Visible Beam Transport & Encl","2006-12-12","2006-12-11"]
["IJ03250125","AVAIL: Visible Beam Transport Diagnostics","2007-01-10","2007-01-09"]
["IJ0328","LB INFRASTRUC & LB SYSTEM-WIDE & MISC. ITEMS SUM","2005-08-01","2006-05-24",null,"2005-08-01"]
["IJ03280000","Define Optical Table Specs","2005-08-15","2005-10-15",null,"2005-08-15","2005-10-15"]
["IJ03280005","Design Optical Tables,","2005-10-16","2005-11-30",null,"2005-10-16","2005-11-30"]
["IJ03280010","COMP: Optical Tables, Legs & Encl Engr & Dsn","2006-02-16","2006-02-15"]
["IJ03280015","Procure Laser Bay Optical Tables","2005-11-01","2006-03-01",null,"2005-11-01"]
["IJ03280020","RCV: Laser Bay Optical Tables, Legs & Encl","2006-03-02","2006-03-02"]
["IJ03280025","REQD: Sector 20 Alcove Beneficial Occupancy","2006-04-03","2006-03-31"]
["IJ03280030","Assemble & C/O Optical Tables, Legs & Encl","2006-03-16","2006-05-10"]
["IJ03280035","Design Enclosures","2005-11-01","2006-02-15",null,"2005-11-01"]
["IJ03280040","AVAIL: Lsr Bay Tables/Legs/Encl","2006-05-11","2006-05-10"]
["IJ03280045","Procure enclosures","2006-02-16","2006-05-11"]
["IJ03280050","Procure Laser Bay Equipment","2006-03-02","2006-05-24"]
["IJ03280055","RCV: Laser Bay Equipment","2006-05-25","2006-05-24"]
["IJ03280060","Define OAL Equipment Requirements","2005-09-01","2005-09-30",null,"2005-09-01","2005-09-30"]
["IJ03280065","Define Laser Bay Equipment","2006-02-01","2006-03-01"]
["IJ03280070","Procure OAL Equipment","2005-08-01","2005-08-30",null,"2005-08-01","2005-08-30"]
["IJ03280075","RCV: OAL Equipment","2006-02-01","2006-01-31"]
["IJ03280080","REQD: Room for the OAL Available","2006-02-01","2006-01-31"]
["IJ03280085","Install OAL Equipment","2005-11-01","2006-02-21",null,"2005-11-01"]
["IJ03280090","AVAIL:  OAL","2006-02-22","2006-02-21"]
["IJ03280100","Laser Safety Review Planning","2005-11-01","2006-03-15",null,"2005-11-01"]
["IJ03280115","Drive Laser Bay Earthquake Safety Review plng","2005-11-01","2006-03-15",null,"2005-11-01"]
["IJ0329","ALIGNMENT LASER SUMMARY","2006-03-02","2006-07-21"]
["IJ03290000","Define alignment Laser System requirements","2006-03-02","2006-03-08"]
["IJ03290005","Develop alignment Laser System Engrg & Design","2006-03-09","2006-04-05"]
["IJ03290025","COMP: Alignment Laser System Dsn","2006-04-06","2006-04-05"]
["IJ03290030","Procure alignment Laser System off-shelf parts","2006-04-06","2006-06-29"]
["IJ03290035","RCV: procured alignment Laser System off-shelf p","2006-06-30","2006-06-29"]
["IJ03290040","Fab (In House) Alignmt Laser System parts","2006-04-06","2006-05-17"]
["IJ03290050","RCV: fabricated mechanical parts","2006-05-18","2006-05-17"]
["IJ03290055","Assemble: alignment Laser system","2006-06-30","2006-07-14"]
["IJ03290060","Test : alignment Laser system","2006-07-17","2006-07-21"]
["IJ03290065","AVAIL: Alignment Laser System Ready for Install","2006-07-24","2006-07-21"]
["IJ0330","LIGHT PATH to STREAK CAMERA SUMMARY","2005-12-01","2006-09-28",null,"2005-12-01"]
["IJ03300000","Define Light Path Sys Reqmts, Beam path & model","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ03300005","Develop Light Path System Engrg & Design","2006-01-01","2006-03-01",null,"2006-01-01"]
["IJ03300035","COMP: Light Path to the Streak Camera Dsn","2006-03-02","2006-03-01"]
["IJ03300040","Procure Light Path off shelf parts","2006-03-02","2006-05-24"]
["IJ03300045","RCV: procured off shelf Light Path parts","2006-05-25","2006-05-24"]
["IJ03300050","Vendors Prep Proposals -Light Path to Srk Camera","2006-03-02","2006-03-29"]
["IJ03300055","RCV: Vendor Proposals - Light Path parts","2006-03-30","2006-03-29"]
["IJ03300060","Evaluate Vendor Proposals","2006-03-30","2006-04-05"]
["IJ03300065","AWARD: order Light Path parts","2006-04-06","2006-04-10"]
["IJ03300070","Vendor Fab, Assy & Test","2006-04-11","2006-07-05"]
["IJ03300075","RCV: Light Path parts from Vendor","2006-07-06","2006-07-05"]
["IJ03300080","FAB: Light Path transport tube/enclosure/supts","2006-07-06","2006-08-16"]
["IJ03300085","Proc Light Path transport tube/enclosure/supts","2006-03-02","2006-05-24"]
["IJ03300090","RCV: Light Path  transport tube/enclosure/supts","2006-05-25","2006-05-24"]
["IJ03300125","Assemble: Light Path System","2006-08-17","2006-09-14"]
["IJ03300140","Test: Light Path system","2006-09-15","2006-09-28"]
["IJ03300145","AVAIL: Light Path System Ready for Instl","2006-09-29","2006-09-28"]
["IJ04","RF GUN, LOAD LOCK & SUPPORTS SUMMARY","2005-05-02","2006-10-12",null,"2005-05-02"]
["IJ0401","RF GUN SUMMARY","2005-05-02","2006-10-12",null,"2005-05-02"]
["IJ0402","RF GUN SUPPORT SUMMARY","2005-05-02","2006-04-28",null,"2005-05-02"]
["IJ04020000","Define RF Gun Support Requirements","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ04020010","COMP: RF Gun Requirements Support Definitions","2005-12-31","2005-12-30",null,"2005-12-31","2005-12-30"]
["IJ04020100","Design RF Gun Support","2005-05-02","2006-03-06",null,"2005-05-02"]
["IJ04020105","COMP: RF Gun Supports Design","2006-03-07","2006-03-06"]
["IJ04020107","Procure RF Gun Support","2006-03-07","2006-04-28"]
["IJ04020125","AVAIL: RF Gun Support Assy Ready for Install","2006-05-01","2006-04-28"]
["IJ0404","GUN LOAD LOCK SUPPORT SUMMARY","2005-12-01","2006-05-30",null,"2005-12-01"]
["IJ04040100","Define Load Lock Support Requirements","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ04040105","COMP: Load Lock Support Requirements Definition","2005-12-31","2005-12-30",null,"2005-12-31","2005-12-30"]
["IJ04040110","Design Load Lock Support","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ04040115","COMP: Load Lock Support Design","2006-01-31","2006-01-30",null,"2006-01-31","2006-01-30"]
["IJ04040120","Prep Bid Pak - Load Lock Support","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["IJ04040122","RELEASE RFP: Load Lock Support","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["IJ04040125","Vendors Prep Proposals - Load Lock Support","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["IJ04040130","RCV: Vendor Proposals -Load Lock Support","2006-01-31","2006-01-30",null,"2006-01-31","2006-01-30"]
["IJ04040140","Evaluate Proposals - Load Lock Support","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["IJ04040145","AWARD: Contract for Load Lock Support","2006-02-01","2006-02-03"]
["IJ04040150","Vendor  Fab Load Lock Support","2006-02-06","2006-05-30"]
["IJ04040155","RCV:Load Lock Support (tested&passed at vendor)","2006-05-31","2006-05-30"]
["IJ04040160","AVAIL: Load Lock Support Assy Ready for Instl","2006-05-31","2006-05-30"]
["IJ0405","GUN SOLENOID SUMMARY","2005-06-01","2006-06-26",null,"2005-06-01"]
["IJ04050110","Post Release Design Correction -Sole Magnet As","2005-07-18","2005-07-30",null,"2005-07-18","2005-07-30"]
["IJ04050115","Prep Bid Pak - Solenoid Magnet Assembly","2005-06-01","2005-06-14",null,"2005-06-01","2005-06-14"]
["IJ04050120","RELEASE RFP: Solenoid Magnet Assembly","2005-06-15","2005-06-30",null,"2005-06-15","2005-06-30"]
["IJ04050125","Vendor Prep Proposals - Solenoid Magnet Assemb","2005-07-01","2005-08-15",null,"2005-07-01","2005-08-15"]
["IJ04050130","RCV: Proposals - Solenoid Magnet Assembly","2005-08-16","2005-08-15",null,"2005-08-16","2005-08-15"]
["IJ04050135","Evaluate Proposals - Solenoid Magnet Assembly","2005-08-16","2005-08-25",null,"2005-08-16","2005-08-25"]
["IJ04050140","AWARD: Contract for 2 Solenoid Magnet Assembli","2005-08-26","2005-08-30",null,"2005-08-26","2005-08-30"]
["IJ04050145","Vendor Fab 2 Solenoid Magnet Assemblies","2005-08-30","2006-03-15",null,"2005-08-30"]
["IJ04050150","RCV: 2 Solenoid Magnet Assemblies","2006-03-16","2006-03-16"]
["IJ04050160","Perform Lab Tests on Sol Magnet Assembly","2006-05-30","2006-06-26"]
["IJ04050165","AVAIL: Gun Solenoid Ready for Assembly","2006-06-27","2006-06-26"]
["IJ0406","GUN SOLENOID SUPPORTS SUMMARY","2005-06-01","2006-05-26",null,"2005-06-01"]
["IJ04060020","Design Solenoid Supports","2005-06-01","2006-03-06",null,"2005-06-01"]
["IJ04060030","COMP: Gun Solenoid Support Design","2006-03-07","2006-03-06"]
["IJ04060035","Prep Bid Pak - Solenoid Supports","2006-03-07","2006-03-07"]
["IJ04060040","RELEASE RFP: Solenoid Supports","2006-03-07","2006-03-07"]
["IJ04060045","Vendor Prep Proposals - Solenoid Supports","2006-03-08","2006-03-08"]
["IJ04060050","RCV: Proposals - Solenoid Supports","2006-03-09","2006-03-08"]
["IJ04060055","Evaluate Proposals - Solenoid Supports","2006-03-09","2006-03-09"]
["IJ04060060","AWARD: Contract for Solenoid Supports","2006-03-10","2006-03-14"]
["IJ04060065","Vendor Fab Solenoid Supports","2006-03-15","2006-05-26"]
["IJ04060070","RCV: Solenoid Supports","2006-05-30","2006-05-26"]
["IJ04060080","AVAIL: Gun Solenoid Support Ready for Assy","2006-05-30","2006-05-26"]
["IJ0408","GUN RF FEED SUPPORTS SUMMARY","2005-12-01","2006-05-10",null,"2005-12-01"]
["IJ04080010","Design Gun RF Feed Supports","2005-12-01","2006-01-31",null,"2005-12-01"]
["IJ04080015","COMP: Gun RF Feed Supports Design","2006-02-01","2006-01-31"]
["IJ04080017","Procure Gun RF Feed Supports Materials","2006-02-01","2006-05-10"]
["IJ04080035","AVAIL: Gun RF Feed Supports Ready for Instl","2006-05-11","2006-05-10"]
["IJ0507","GTL VACUUM COMPONENTS","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["IJ0508","INJECTOR VACUUM SPECIAL CHAMBERS SUMMARY","2005-09-17","2006-04-03",null,"2005-09-17"]
["IJ050901","GUN SPECTROMETER DIPOLE SUMMARY","2005-07-01","2006-05-16",null,"2005-07-01"]
["IJ050906","GS QUADS (3ea) SUMMARY","2005-09-15","2006-03-15",null,"2005-09-15"]
["IJ050907","GS SUPPORT SUMMARY","2005-05-02","2006-01-31",null,"2005-05-02"]
["IJ06","INJECTOR STRUCTURES SUMMARY","2005-05-02","2006-05-03",null,"2005-05-02"]
["IJ0601","L0A-0B STRUCTURE ASSEMBLY SUMMARY","2005-07-01","2006-04-28",null,"2005-07-01"]
["IJ0603","MAJOR LINAC SUPPORT SUMMARY","2005-05-02","2006-05-03",null,"2005-05-02"]
["IJ06030010","Prep Bid Pak - Major Linac Supports","2005-05-02","2006-01-30",null,"2005-05-02","2006-01-30"]
["IJ06030015","RELEASE: RFP - Major Linac Supports","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ06030020","Vendors Prep Proposals - Major Linac Supports","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ06030025","RCV: Vendor Proposal for Major Linac Supports","2005-12-31","2005-12-30",null,"2005-12-31","2005-12-30"]
["IJ06030030","Evaluate Vendor Proposals-Major Linac Supports","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ06030035","AWARD: Major Linac Supports Contract","2006-04-03","2006-04-05"]
["IJ06030040","Vendor Fab, Assy & Test-Major Linac Supports","2006-04-06","2006-04-19"]
["IJ06030045","RCV: Major Linac Supports from Vendor","2006-04-20","2006-04-19"]
["IJ06030055","Fab & Mods Linac Supports","2006-04-20","2006-05-03"]
["IJ06030060","AVAIL: Supts Ready for Integ with L0-1 & L0-2","2006-05-04","2006-05-03"]
["IJ0604","LINAC SOLENOID & SUPPORTS SUMMARY","2005-07-01","2006-02-15",null,"2005-07-01"]
["IJ07","L0-1TL0-2 SUMMARY","2005-05-02","2006-08-21",null,"2005-05-02"]
["IJ0701","L0-1TL0-2 QUADRUPOLES SUMMARY (2EA)","2005-08-01","2006-04-13",null,"2005-08-01"]
["IJ0706","L0-1TL0-2 Vacuum Components","2005-12-01","2006-06-12",null,"2005-12-01"]
["IJ0806","LTDL1 RF KICKER SUMMARY","2005-05-02","2006-05-01",null,"2005-05-02"]
["IJ08060055","Vendor RF Kicker Production (build to print)","2005-05-02","2005-06-30",null,"2005-05-02","2005-06-30"]
["IJ08060060","RCV: RF Kicker from Vendor","2005-07-01","2005-06-30",null,"2005-07-01","2005-06-30"]
["IJ08060065","Vacuum Process Kicker","2005-07-01","2005-07-30",null,"2005-07-01","2005-07-30"]
["IJ08060070","Conduct Test & RF Processing","2005-09-01","2006-03-27",null,"2005-09-01"]
["IJ08060075","Develop RF Kicker Support Structure Engr & Dsn","2005-09-15","2006-03-15",null,"2005-09-15"]
["IJ08060080","COMP: RF Kicker Support Structure Engr & Dsn","2006-03-16","2006-03-15"]
["IJ08060085","Procure Support Structure Materials","2006-03-16","2006-03-15"]
["IJ08060090","Fab RF Kicker Support Structure","2006-03-01","2006-04-17"]
["IJ08060095","Integrate RF Kicker onto Supports","2006-04-18","2006-05-01"]
["IJ08060100","AVAIL: LTDL1 RF Kicker & Supts Ready for Instl","2006-05-02","2006-05-01"]
["IJ0807","LTDL1 LINAC STEERING COILS SUMMARY(2ea)X-Y","2005-09-15","2006-03-02",null,"2005-09-15"]
["IJ0901","DL1 B01 & B02 DIPOLES SUMMARY","2005-06-01","2006-05-31",null,"2005-06-01"]
["IJ1002","DL1TL STEERING COILS SUMMARY(3eaX-Y Assys)","2006-02-01","2010-04-05"]
["IJ101_1010","Injector Region Layout","2005-05-02","2005-10-31",null,"2005-05-02","2005-10-31"]
["IJ101_1020","Injector Region Fabrication Oversight","2005-05-16","2005-09-30",null,"2005-05-16","2005-09-30"]
["IJ101_1030","injector Region Documentation","2006-10-02","2006-12-29"]
["IJ101_1100","Design Injector Vault Base Supports","2005-06-01","2006-02-28",null,"2005-06-01"]
["IJ101_1110","COMP:  Injector Vault Base Supports Design","2005-12-31","2005-12-30",null,"2005-12-31","2005-12-30"]
["IJ101_1120","Prep Bid Pkg for Injector Vault Base Supports","2006-01-01","2006-02-28",null,"2006-01-01"]
["IJ101_1130","RELEASE RFP:  Injector Vault Base Supports","2006-03-01","2006-03-01"]
["IJ101_1140","Vendor Prep Proposal for Inj Vault Base Supports","2006-03-02","2006-03-02"]
["IJ101_1150","RCV:  Proposals for Injector Vault Base Supports","2006-03-03","2006-03-03"]
["IJ101_1160","Evaluate Proposals for Inj Vault Base Supports","2006-03-06","2006-03-06"]
["IJ101_1170","AWARD: Contract for Injector Vault Base Supports","2006-03-07","2006-03-07"]
["IJ101_1180","Vendor Fab Injector Vault Base Supports","2006-03-08","2006-05-02"]
["IJ101_1190","AVAIL:  Injector Vault Base Supports RFI","2006-05-03","2006-05-03"]
["IJ101_1200","Injector Region Infrastructure Support","2005-12-01","2007-01-02",null,"2005-12-01"]
["IJ101_1210","Injector Region Top Assembly","2005-12-01","2006-04-03",null,"2005-12-01"]
["IJ101_1220","Injector Region Documentation","2006-12-01","2007-06-29"]
["IJ101_2010","Gun Area Layout","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["IJ101_2020","Gun Area Installation Oversight","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ101_2030","Gun Area Documentation","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ101_2100","Gun Area Table and Columns","2005-12-01","2006-03-30",null,"2005-12-01"]
["IJ101_2110","Gun Area Top Assembly","2005-12-01","2006-05-01",null,"2005-12-01"]
["IJ101_2120","Gun Area Procurement Support","2006-02-01","2006-05-31"]
["IJ101_2130","Gun Area Fabrication Oversight","2006-02-01","2006-05-31"]
["IJ101_2140","Gun Area Installation Coordination Planning","2005-12-01","2006-06-30",null,"2005-12-01"]
["IJ101_2150","Gun Area Installation Oversight","2006-06-01","2006-07-28"]
["IJ101_2160","Gun Area Documentation","2006-10-02","2007-06-29"]
["IJ101_3010","Accelerator Area Layout","2005-05-02","2005-10-31",null,"2005-05-02","2005-10-31"]
["IJ101_3020","Accelerator Area Installation Oversight","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ101_3030","Accelerator Area Documentation","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ101_3100","Accelerator Area Table and Columns","2006-01-01","2006-04-26",null,"2006-01-01"]
["IJ101_3110","Accelerator Area Top Assembly","2005-12-01","2006-05-01",null,"2005-12-01"]
["IJ101_3120","Accelerator Area Procurement Support","2006-03-01","2006-05-01"]
["IJ101_3130","Accelerator Area Fabrication Oversight","2006-01-01","2006-05-30",null,"2006-01-01"]
["IJ101_3140","Accelerator Area Installation Coord Planning","2006-01-01","2006-05-30",null,"2006-01-01"]
["IJ101_3150","Accelerator Area Installation Oversight","2006-06-01","2006-07-31"]
["IJ101_3160","Accelerator Area Documentation","2006-10-02","2007-07-02"]
["IJ101_4010","Heater Area Layout","2005-05-02","2005-12-30",null,"2005-05-02","2005-12-30"]
["IJ101_4020","Heater Area Installation Oversight","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ101_4030","Heater Area Documentation","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ101_4100","Heater Area Table and Columns","2005-12-01","2006-04-26",null,"2005-12-01"]
["IJ101_4110","Heater Area Top Assembly","2005-12-01","2006-05-01",null,"2005-12-01"]
["IJ101_4120","Heater Area Procurement Support","2006-03-01","2006-05-01"]
["IJ101_4130","Heater Area Fabrication Oversight","2006-03-01","2006-05-01"]
["IJ101_4140","Heater Area Installation Coord Planning","2006-01-01","2006-05-30",null,"2006-01-01"]
["IJ101_4150","Heater Area Installation Oversight","2006-06-01","2006-07-31"]
["IJ101_4160","Heater Optics Integration","2006-12-01","2007-07-02"]
["IJ101_4170","Heater Optics Installation Oversight","2007-07-02","2007-10-01"]
["IJ101_4180","Heater Area Documentation","2006-02-01","2006-06-30"]
["IJ101_5020","Wall Area Installation Oversight","2005-10-03","2005-11-30",null,"2005-10-03","2005-11-30"]
["IJ101_5030","Wall Area Documentation","2005-05-02","2005-11-30",null,"2005-05-02","2005-11-30"]
["IJ101_5100","Wall Area Top Assembly","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ101_6010","Insertion Area Layout","2005-09-15","2005-12-30",null,"2005-09-15","2005-12-30"]
["IJ101_6020","Insertion Area Installation Oversight","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ101_6030","Insertion Area Documentation","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ101_6100","Insertion Area Table and Columns","2005-12-01","2006-03-31",null,"2005-12-01"]
["IJ101_6110","Insertion Area Top Assembly","2005-12-01","2006-03-31",null,"2005-12-01"]
["IJ101_6120","Insertion Area Procurement Support","2006-04-03","2006-06-30"]
["IJ101_6130","Insertion Area Fabrication Oversight","2006-04-03","2006-06-30"]
["IJ101_6140","Insertion Area Installation Coord Planning","2006-01-01","2006-07-31",null,"2006-01-01"]
["IJ101_6150","Insertion Area Installation Oversight","2006-08-01","2006-11-30"]
["IJ101_6160","Insertion Area Documentation","2006-12-01","2007-02-28"]
["IJ101_7010","Spectrometer Area Layout","2005-10-03","2005-12-30",null,"2005-10-03","2005-12-30"]
["IJ101_7020","Spectrometer Area Installation Oversight","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ101_7030","Spectrometer Area Documentation","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ101_7100","Spectrometer Area Table and Columns","2005-12-01","2006-03-31",null,"2005-12-01"]
["IJ101_7110","Spectrometer Area Top Assembly","2005-12-01","2006-03-31",null,"2005-12-01"]
["IJ101_7120","Spectrometer Area Procurement Support","2006-04-03","2006-06-30"]
["IJ101_7130","Spectrometer Area Fabrication Oversight","2006-04-03","2006-06-30"]
["IJ101_7140","Spectrometer Area Installation Coord Planning","2006-01-01","2006-07-31",null,"2006-01-01"]
["IJ101_7150","Spectrometer Area Installation Oversight","2006-08-01","2006-11-30"]
["IJ101_7160","Spectrometer Area Documentation","2006-12-01","2007-02-28"]
["IJ101_8010","Drive Laser Layout","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ101_8020","Drive Laser Installation Oversight","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ101_8030","Drive Laser Documentation","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ101_8110","Drive Laser Top Assembly","2006-01-01","2006-05-01",null,"2006-01-01"]
["IJ101_8120","Drive Laser Procurement Support","2006-02-01","2006-05-31"]
["IJ101_8130","Drive Laser Fabrication Oversight","2006-02-01","2006-05-31"]
["IJ101_8140","Drive Laser Installation Coordination Planning","2006-02-01","2006-05-01"]
["IJ101_8150","Drive Laser Installation Oversight","2006-05-01","2006-07-31"]
["IJ101_8160","Drive Laser Documentation","2006-12-01","2007-07-02"]
["IJ104_1000","Management - CONST","2005-12-01","2007-01-02",null,"2005-12-01"]
["IJ104_1010","Cost Account Managers - CONST","2005-12-01","2007-01-02",null,"2005-12-01"]
["IJ104_1020","Fabrication Coordination","2005-12-01","2007-01-02",null,"2005-12-01"]
["IJ104_1030","Computers - CONST","2005-12-01","2007-01-02",null,"2005-12-01"]
["IJ104_1040","Travel - CONST","2005-12-01","2007-01-02",null,"2005-12-01"]
["IJ104_1050","Materials & Supplies - CONST","2005-12-01","2007-01-02",null,"2005-12-01"]
["IJ1101","SAB SPECTROMETER DIPOLE SUMMARY","2005-12-01","2006-07-19",null,"2005-12-01"]
["IJ12","INJECTOR RF WAVEGUIDE SUMMARY","2005-05-02","2006-10-27",null,"2005-05-02"]
["IJ1201","INJECTOR RF WAVEGUIDE SUBSYSTEM SUMMARY","2005-05-02","2006-10-27",null,"2005-05-02"]
["IJ12010010","Develop RF Waveguide System Engineering & Dsn","2005-05-02","2005-05-27",null,"2005-05-02","2005-05-27"]
["IJ12010020","Refurbish WG Trailer","2005-08-01","2005-09-15",null,"2005-08-01","2005-09-15"]
["IJ12010030","Purchase WG Material","2005-06-01","2005-08-30",null,"2005-06-01","2005-08-30"]
["IJ12010040","Purchase WG Flanges","2005-05-02","2005-07-30",null,"2005-05-02","2005-07-30"]
["IJ12010050","Design Pen Waveguide","2005-05-02","2005-05-27",null,"2005-05-02","2005-05-27"]
["IJ12010060","Fab Pen Waveguide","2005-07-01","2005-09-20",null,"2005-07-01","2005-09-20"]
["IJ12010070","Post Process Pen Waveguide","2005-09-20","2005-10-07",null,"2005-09-20","2005-10-07"]
["IJ12010080","Fab Pen Supports","2005-09-01","2005-09-30",null,"2005-09-01","2005-09-30"]
["IJ12010090","AVAIL: Pen WG Ready for Install","2005-10-08","2005-10-07",null,"2005-10-08","2005-10-07"]
["IJ12010100","Design Vault Waveguide","2005-06-01","2006-02-28",null,"2005-06-01"]
["IJ12010110","Fab Vault Waveguide","2005-12-01","2006-03-20",null,"2005-12-01"]
["IJ12010120","Post Process Vault Waveguide","2006-03-21","2006-03-30"]
["IJ12010130","Fab Vault Supports","2006-02-01","2006-03-20"]
["IJ12010140","AVAIL: Vault WG Ready for Install","2006-03-21","2006-03-20"]
["IJ12010150","Design KG Waveguide","2005-09-01","2006-02-15",null,"2005-09-01"]
["IJ12010160","Fab KG Waveguide","2005-10-31","2006-04-03",null,"2005-10-31"]
["IJ12010170","Post Process KG Waveguide","2006-04-04","2006-04-03"]
["IJ12010180","Fab KG Supports","2006-04-04","2006-05-01"]
["IJ12010190","AVAIL: KG WG Ready for Install","2006-05-02","2006-05-01"]
["IJ12010200","High Power Gun WG Conditioning","2006-10-02","2006-10-27"]
["IJ12010210","High Power ACC WG Conditioning","2006-05-02","2006-05-30"]
["IJ12010220","High Power T-Cav WG Contidioning","2006-10-02","2006-10-27"]
["IJ13","INJECTOR RF SUMMARY","2005-05-02","2007-05-25",null,"2005-05-02"]
["IJ13010020","Develop Documentation","2005-05-02","2006-02-28",null,"2005-05-02"]
["IJ13010025","Create Layouts","2005-05-02","2006-02-28",null,"2005-05-02"]
["IJ13010030","Prepare for PDR","2005-05-02","2005-05-10",null,"2005-05-02","2005-05-10"]
["IJ13010035","Conduct PDR","2005-05-10","2005-05-15",null,"2005-05-10","2005-05-15"]
["IJ130101","S-BAND LL CONTROLS TIMING SYSTEM SUMMARY","2005-05-02","2006-11-15",null,"2005-05-02"]
["IJ13010108","Design & Prototype Master Amplifier","2005-05-15","2005-09-30",null,"2005-05-15","2005-09-30"]
["IJ13010120","Generate Procurement Plan","2005-09-01","2005-09-30",null,"2005-09-01","2005-09-30"]
["IJ13010122","Create Test Plan","2005-09-01","2005-09-30",null,"2005-09-01","2005-09-30"]
["IJ13010124","Establish Subordinate W.O.'s","2005-09-01","2005-09-30",null,"2005-09-01","2005-09-30"]
["IJ13010126","Prepare for FDR","2005-09-01","2005-09-30",null,"2005-09-01","2005-09-30"]
["IJ13010128","Conduct FDR","2005-09-01","2005-09-30",null,"2005-09-01","2005-09-30"]
["IJ13010130","COMP: S-Band LL Design - Release for Fab","2005-10-01","2005-09-30",null,"2005-10-01","2005-09-30"]
["IJ13010146","Fab Master Amplifier","2005-09-01","2005-11-30",null,"2005-09-01","2005-11-30"]
["IJ13010152","System Tests","2006-03-01","2006-07-20"]
["IJ13010153","Fab/Test PEPII IQ PAU","2005-11-01","2006-03-03",null,"2005-11-01"]
["IJ13010154","AVAIL: RF Cntrls I/F & Timing Ready for Install","2006-07-21","2006-07-20"]
["IJ13010156","Install Modules","2006-07-21","2006-11-15"]
["IJ13010164","AVAIL: RF Cntrls I/F & Timing Ready for Comm","2006-11-16","2006-11-15"]
["IJ130102","LLRF PHASE REFERENCE SYSTEM SUMMARY","2005-06-01","2007-03-01",null,"2005-06-01"]
["IJ13010200","System Design","2005-06-01","2005-08-30",null,"2005-06-01","2005-08-30"]
["IJ13010205","Develop Documentation","2005-12-01","2007-03-01",null,"2005-12-01"]
["IJ13010210","Create Layouts","2005-12-01","2007-03-01",null,"2005-12-01"]
["IJ13010215","Prepare for PDR","2005-10-03","2005-10-04",null,"2005-10-03","2005-10-04"]
["IJ13010217","Conduct PDR","2005-10-05","2005-10-05",null,"2005-10-05","2005-10-05"]
["IJ13010219","Design & Prototype LCLS Oscillator","2005-06-29","2006-09-18",null,"2005-06-29"]
["IJ13010220","Design RF Distribution L0, L1","2005-09-01","2006-01-30",null,"2005-09-01","2006-01-30"]
["IJ13010222","Design Distribution Amplifier Chassis","2005-09-01","2005-10-24",null,"2005-09-01","2005-10-24"]
["IJ13010223","Design & Prototype Laser Timing Stability","2005-12-01","2007-02-01",null,"2005-12-01"]
["IJ13010225","Design & Prototype Multiplier Chassis","2005-09-01","2005-09-30",null,"2005-09-01","2005-09-30"]
["IJ13010228","Generate Procurement Plan","2005-12-01","2006-01-30",null,"2005-12-01","2006-01-30"]
["IJ13010230","Create Test Plan","2005-12-01","2006-01-30",null,"2005-12-01","2006-01-30"]
["IJ13010232","Establish Subordinate W.O.'s","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ13010234","Prepare for FDR","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["IJ13010236","Conduct FDR","2006-03-06","2006-03-06"]
["IJ13010238","COMP: Design - Release for Fab","2006-03-07","2006-03-06"]
["IJ13010240","Vendor Fab LCLS Oscillator (3)","2006-02-13","2006-06-29"]
["IJ13010241","Prep Bid Pak - LCLS Oscillator (3)","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["IJ13010242","Fab LCLS Oscillator","2006-04-06","2006-06-29"]
["IJ13010243","RELEASE: RFP - LCLS Oscillator (3)","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["IJ13010244","Vendors Prep Prop- LCLS Oscillator (3)","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["IJ13010246","RCV: Vendor Prop- LCLS Oscillator (3)","2006-02-01","2006-01-31"]
["IJ13010247","Eval Vendor Prop- LCLS Oscillator (3)","2006-02-01","2006-02-07"]
["IJ13010248","Fab Distribution Amplifier Chassis","2006-02-01","2006-07-03"]
["IJ13010249","AWARD: LCLS Oscillator (3)","2006-02-08","2006-02-10"]
["IJ13010256","Fab Laser Phase Timing Stability","2006-02-01","2006-07-03"]
["IJ13010260","S-20 MDL Modifications","2006-02-01","2006-07-03"]
["IJ13010264","Fab Multiplier Chassis","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ13010272","AVAIL: LLRF Phase Ref System Ready for Install","2006-07-05","2006-07-03"]
["IJ13010274","Install Cable Guides","2006-07-05","2006-11-15"]
["IJ13010275","Install S-Band RF Cables (31)","2006-07-05","2006-11-15"]
["IJ13010276","Install Modules","2006-07-05","2006-11-15"]
["IJ13010284","AVAIL: LLRF Phase Ref System Ready for Comm","2006-11-16","2006-11-15"]
["IJ130103","LLRF MONITOR & CONTROL SYSTEM SUMMARY","2005-05-02","2007-04-20",null,"2005-05-02"]
["IJ13010300","Define Control Interface","2005-06-01","2006-02-01",null,"2005-06-01"]
["IJ13010302","Develop Documentation","2006-02-02","2006-09-29"]
["IJ13010305","Create Layouts","2006-02-02","2006-09-29"]
["IJ13010307","Prepare for PDR","2005-10-17","2005-10-18",null,"2005-10-17","2005-10-18"]
["IJ13010308","Conduct PDR","2005-10-19","2005-10-19",null,"2005-10-19","2005-10-19"]
["IJ13010310","Design & Prototype S-Band Phase Measurment","2005-06-20","2006-03-02",null,"2005-06-20"]
["IJ13010311","Design & Prototype DAC & SAM Breakout","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["IJ13010312","Design Modulator Refurbishment","2005-12-01","2006-03-20",null,"2005-12-01"]
["IJ13010314","Design Solid State Sub Booster","2005-09-01","2006-02-28",null,"2005-09-01"]
["IJ13010318","Design & Prototype Optical Interface","2006-02-03","2006-10-02"]
["IJ13010330","Generate Procurement Plan","2006-03-21","2006-03-21"]
["IJ13010332","Create Test Plan","2006-03-22","2006-03-28"]
["IJ13010334","Establish Subordinate W.O.'s","2006-03-29","2006-03-29"]
["IJ13010336","Prepare for FDR","2006-03-30","2006-03-31"]
["IJ13010338","Conduct FDR","2006-04-03","2006-04-03"]
["IJ13010339","Prep Bid Pak - Modulator Thyratron Parts","2006-04-04","2006-04-17"]
["IJ13010340","COMP: Design - Release for Fab","2006-04-04","2006-04-03"]
["IJ13010341","RELEASE: RFP - Modulator Thyratron Parts","2006-04-18","2006-04-17"]
["IJ13010342","Vendor Fab Modulator Thyratron Parts","2006-05-10","2006-08-17"]
["IJ13010343","Vendors Prep Prop- Modulator Thyratron Parts","2006-04-18","2006-05-01"]
["IJ13010344","Procure SS Subbooster Amplitude Control","2006-04-04","2006-05-01"]
["IJ13010345","RCV: Vendor Prop- Modulator Thyratron Parts","2006-05-02","2006-05-01"]
["IJ13010346","Eval Vendor Prop- Modulator Thyratron Parts","2006-05-02","2006-05-08"]
["IJ13010347","AWARD: Modulator Thyratron Parts","2006-05-09","2006-05-09"]
["IJ13010348","Procure Monitor Scope SCP","2005-05-02","2006-01-30",null,"2005-05-02","2006-01-30"]
["IJ13010350","Procure Dual Power Meter SCP","2005-10-03","2006-01-30",null,"2005-10-03","2006-01-30"]
["IJ13010352","Procure Bunch Length Monitor Electronics","2006-04-04","2006-06-01"]
["IJ13010354","RCV: Procured Hardware/Equipment","2006-08-18","2006-08-17"]
["IJ13010356","Fab S-Band Units (12)","2006-08-18","2006-11-10"]
["IJ13010360","Fab Dac Sam Breakout Units (6)","2006-08-18","2006-11-10"]
["IJ13010366","Refurbish Modulator","2006-08-18","2006-11-10"]
["IJ13010368","Klystron Change to Source Tube","2006-08-18","2006-11-10"]
["IJ13010370","Fab SS Subbooster Amplifier","2005-10-03","2006-04-03",null,"2005-10-03"]
["IJ13010372","Integration SS Subbooster Amplifier","2006-06-28","2006-09-21"]
["IJ13010374","Modify IPA Chassis","2006-04-04","2006-06-27"]
["IJ13010382","Modulator Control Interface Cables","2006-08-18","2006-11-10"]
["IJ13010384","Monitor Scope SCP Interface","2006-08-18","2006-08-31"]
["IJ13010387","REQD: Beneficial Occupancy of RF Hut","2006-03-10","2006-03-09"]
["IJ13010388","AVAIL: LLRF Mon & Cntrl Ready for Installation","2007-01-26","2007-01-25"]
["IJ13010389","Install Cables","2006-11-13","2007-01-25"]
["IJ13010390","Recable RF","2006-06-28","2006-08-23"]
["IJ13010391","Install Modules","2007-01-26","2007-02-23"]
["IJ13010392","Install Mod Control Interace","2007-02-26","2007-04-20"]
["IJ13010394","AVAIL: LLRF Mon & Cntrl Ready for Commissioning","2007-04-23","2007-04-20"]
["IJ130104","BEAM PHASE MONITOR CAVITY SUMMARY","2005-07-15","2007-02-28",null,"2005-07-15"]
["IJ13010400","Define Beamline Component","2005-07-15","2005-12-30",null,"2005-07-15","2005-12-30"]
["IJ13010402","COMP: Beamline Component Definition","2005-12-31","2005-12-30",null,"2005-12-31","2005-12-30"]
["IJ13010408","Develop Documentation","2005-09-01","2005-09-30",null,"2005-09-01","2005-09-30"]
["IJ13010410","Create Layouts","2006-01-01","2007-02-28",null,"2006-01-01"]
["IJ13010412","Prepare for PDR","2005-11-01","2005-11-04",null,"2005-11-01","2005-11-04"]
["IJ13010414","Conduct PDR","2005-11-07","2005-11-07",null,"2005-11-07","2005-11-07"]
["IJ13010416","Generate Procurement Plan","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["IJ13010418","Create Test Plan","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["IJ13010420","Establish Subordinate W.O.'s","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["IJ13010422","Prepare for FDR","2006-02-15","2006-02-16"]
["IJ13010424","Conduct FDR","2006-03-15","2006-03-15"]
["IJ13010426","COMP: Design - Release for Fab","2006-03-16","2006-03-15"]
["IJ13010430","Fab Beam Line Components","2006-03-16","2006-06-08"]
["IJ13010436","Cold Test Components","2006-06-09","2006-06-15"]
["IJ13010438","Cold Test Complete","2006-06-16","2006-06-15"]
["IJ13010439","Bake Beamline Components","2006-06-16","2006-06-29"]
["IJ13010440","AVAIL: Beam Phase Mon. Cavity Ready for Install","2006-06-30","2006-06-29"]
["IJ13010441","Fabricate Beam Phase Monitor System","2005-12-01","2006-06-22",null,"2005-12-01"]
["IJ13010442","Install Modules","2006-06-23","2006-07-10"]
["IJ13010448","Install Cables","2006-07-11","2006-07-24"]
["IJ13010452","AVAIL: Beam Phase Mon. System Ready for Comm.","2006-07-25","2006-07-24"]
["IJ130105","RF SYSTEM S/W DEVELOPMENT/DOCUMENTATION SUMMARY","2006-05-08","2007-05-25"]
["IJ13010502","Develop Specification","2006-11-15","2007-01-25"]
["IJ13010504","Specification Complete","2007-01-26","2007-01-25"]
["IJ13010506","Create Layouts","2006-05-08","2007-01-25"]
["IJ13010510","Prepare for PDR","2007-01-24","2007-01-25"]
["IJ13010512","Conduct PDR","2007-01-25","2007-01-25"]
["IJ13010516","Create Test Plan","2007-01-19","2007-01-25"]
["IJ13010522","Conduct FDR","2007-01-26","2007-02-01"]
["IJ13010524","COMP: Design - Release for Fab","2007-02-02","2007-02-01"]
["IJ13010528","RF Feedback Measurements/Algorithm Development","2007-02-02","2007-05-25"]
["IJ13010538","AVAIL: RF System S/W & Docs Ready for Comm.","2007-05-29","2007-05-25"]
["IJ15","INJECTOR LASER HEATER SUBSYSTEM SUMMARY","2005-03-01","2007-06-27",null,"2005-03-01"]
["IJ1501","SYSTEM DESIGN & OPTIMIZATION SUMMARY","2007-06-07","2007-06-27"]
["IJ15010015","Laser Heater System Design Review","2007-06-07","2007-06-13"]
["IJ15010020","Laser Heater System Design Modifications","2007-06-14","2007-06-27"]
["IJ15010025","COMP: System design","2007-06-28","2007-06-27"]
["IJ1502","BEAM CONDITIONING OPTICS (LB) SUMMARY","2006-10-03","2007-04-12"]
["IJ15020000","Procure Laser Heater Optics Spares","2006-10-03","2006-10-31"]
["IJ15020005","Design Beam Conditioning","2006-10-03","2006-12-01"]
["IJ15020015","Define Beam Conditioning Components Specs","2006-12-04","2007-01-24"]
["IJ15020020","Procure Compressor breadboard and components","2007-01-25","2007-03-22"]
["IJ15020025","Procure First telescope optics","2007-01-25","2007-03-22"]
["IJ15020030","Procure Path length adjustor breadboard & Comps","2007-01-25","2007-03-22"]
["IJ15020035","Procure Optics safety equipment","2007-01-25","2007-03-22"]
["IJ15020040","Install and Test Beam Conditioning optics","2007-03-23","2007-04-12"]
["IJ15020050","COMP: Beam conditioning optics","2007-04-13","2007-04-12"]
["IJ1503","TRANSPORT OPTICS SUMMARY","2007-01-25","2008-03-11"]
["IJ15030005","Design Transport optics","2007-01-25","2007-03-21"]
["IJ15030015","Define Transport System Optics Specs","2007-03-22","2007-04-12"]
["IJ15030020","Procure Relay optics transport system","2007-04-13","2007-06-08"]
["IJ15030025","Procure Reducing telescope","2007-04-13","2007-06-08"]
["IJ15030030","Procure Optics launch table in tunnel","2007-04-13","2007-06-08"]
["IJ15030035","Transport optics installation, alignment & test","2007-11-26","2008-03-11"]
["IJ15030040","Design enclosures,laser beam tubes & supports","2007-03-22","2007-05-18"]
["IJ15030045","Procure enclosures,beam tubes & supports","2007-05-21","2007-11-07"]
["IJ15030049","REQD: Enclosures,Tubes & Supports Installed","2007-11-26","2007-11-21"]
["IJ15030050","AVAIL: Enclosures,tubes & supports for Install","2007-11-08","2007-11-07"]
["IJ15030060","COMP: Transport Optics","2008-03-12","2008-03-11"]
["IJ1504","CHICANE SUMMARY","2005-07-01","2006-05-16",null,"2005-07-01"]
["IJ1505","UNDULATOR SUMMARY","2005-03-01","2006-12-14",null,"2005-03-01"]
["IJ15050005","Define Undulator specifications","2005-03-01","2005-03-01",null,"2005-03-01","2005-03-01"]
["IJ15050010","Undulator design review","2006-06-01","2006-06-14"]
["IJ15050011","Prep Bid Pak - Undulator","2006-06-15","2006-06-28"]
["IJ15050012","RELEASE: RFP - Undulator","2006-06-29","2006-07-06"]
["IJ15050013","Vendors Prep Proposals - Undulator","2006-07-07","2006-08-10"]
["IJ15050014","RCV: Vendor Proposals - Undulator","2006-08-11","2006-08-10"]
["IJ15050015","Evaluate Vendor Proposals - Undulator","2006-08-11","2006-08-16"]
["IJ15050016","AWARD: Undulator","2006-08-17","2006-08-18"]
["IJ15050020","Fab/Procure Undulator","2006-08-21","2006-10-02"]
["IJ15050025","RCV:  Undulator","2006-10-03","2006-10-03"]
["IJ15050035","Perform Magnetic measurements and QA","2006-10-04","2006-12-14"]
["IJ15050040","AVAIL: Undulator for installation","2006-12-15","2006-12-14"]
["IJ1506","PHOTON BEAM DIAGNOSTICS SUMMARY","2007-04-13","2007-10-24"]
["IJ15060005","Design Diagnostics","2007-04-13","2007-05-30"]
["IJ15060015","Prepare Diagnostics spec and purchase","2007-05-31","2007-06-06"]
["IJ15060020","Procure Spiricon camera","2007-06-07","2007-07-19"]
["IJ15060025","Procure Molectron power meter","2007-06-07","2007-07-19"]
["IJ15060030","Procure optics for photon diagnostics","2007-06-07","2007-07-06"]
["IJ15060032","Procure video cameras for OTRs & waist-size mon","2007-06-07","2007-07-06"]
["IJ15060035","Procure Timing diode + oscilloscope","2007-06-07","2007-07-06"]
["IJ15060040","Design Supports","2007-05-31","2007-07-30"]
["IJ15060045","Fabricate Supports","2007-07-31","2007-09-04"]
["IJ15060047","AVAIL: Supports for Install","2007-09-05","2007-09-04"]
["IJ15060049","REQD: Photon beam diagnostics Installed","2007-09-26","2007-09-25"]
["IJ15060050","Install and test Photon beam diagnostics","2007-09-26","2007-10-24"]
["IJ15060055","COMP: Photon Beam diagnostics","2007-10-25","2007-10-24"]
["IJ1508","TESTING AND COMMISSIONING SUMMARY","2006-09-20","2008-05-14"]
["IJ15080005","Plan for Laser Heater commissioning","2008-03-06","2008-03-19"]
["IJ15080007","REQD:Complete Chicane Installation","2007-09-19","2007-09-18"]
["IJ15080008","REQD:Complete Undulator Installation","2007-09-26","2007-09-25"]
["IJ15080009","REQD:Complete Laser Heater Controls","2007-12-14","2007-12-13"]
["IJ15080010","Commission Laser Heater Bay Optics","2008-03-20","2008-04-02"]
["IJ15080011","REQD:Complete Spectrometer","2006-09-20","2006-09-19"]
["IJ15080015","Commission IR Optical Path to Laser Heater","2008-04-03","2008-04-09"]
["IJ15080020","Match beam power and size for LH","2008-04-10","2008-04-23"]
["IJ15080025","Setup LH electron energy spread measurement","2008-04-24","2008-05-07"]
["IJ15080030","Overlap LH electron and laser beams","2008-05-08","2008-05-14"]
["IJ15080040","COMP: Laser Heater Commissioning","2008-05-15","2008-05-14"]
["IJ1601","PERSONNEL PROTECTION SUBSYSTEM SUMMARY","2005-09-01","2007-01-12",null,"2005-09-01"]
["IJ16010047","BSOIC Design","2006-03-24","2006-04-18"]
["IJ16010050","PROCUREMENT START - Injector PPS","2006-09-06","2006-09-05"]
["IJ16010066","Procure PPS Hardware","2005-09-01","2006-04-26",null,"2005-09-01"]
["IJ16010220","RCV: PPS Hardware/Material","2006-04-27","2006-04-26"]
["IJ16010225","Prep Bid Pak - BSOIC","2006-04-19","2006-05-02"]
["IJ16010230","RELEASE: RFP - BSOIC","2006-05-03","2006-05-02"]
["IJ16010235","Vendors Prep Proposals - BSOIC","2006-05-03","2006-05-23"]
["IJ16010240","RCV: Proposals - BSOIC","2006-05-24","2006-05-23"]
["IJ16010245","Evaluate Proposals - BSOIC","2006-05-24","2006-06-07"]
["IJ16010250","AWARD: Contract - BSOIC","2006-09-06","2006-09-06"]
["IJ16010255","Vendor Fab/Assy - BSOIC","2006-09-07","2007-04-25"]
["IJ16010260","RCV: from Vendor - PPS BSOIC","2007-04-26","2007-04-25"]
["IJ16010275","Fab and Pre Assemble Components (as required)","2007-04-26","2007-05-23"]
["IJ16010286","COMP: Injector PPS Component Fab & Assembly","2007-05-24","2007-05-23"]
["IJ16010288","Perform Pre-Install Qual Test on Injector PPS","2007-05-24","2007-06-21"]
["IJ16010290","AVAIL: Injector PPS Equip ready for Install","2007-06-22","2007-06-21"]
["IJ1601_022","PROCUREMENT START - Laser PPS","2006-09-06","2006-09-05"]
["IJ1601_023","Procure Entryway Hardware","2006-09-06","2007-01-12"]
["IJ1601_100","RCV: Laser room Hardware/Material","2007-01-16","2007-01-12"]
["IJ1601_112","AVAIL: Laser Room PPS Equip ready for Install","2007-01-16","2007-01-12"]
["IJ16020000","PLC PPS Design Evaluation","2005-11-01","2006-03-23",null,"2005-11-01"]
["IJ16020005","COMP: PLC PPS Design Evaluation","2006-03-24","2006-03-23"]
["IJ16020400","Procure 12 AMP MCOR Modules (2)-Spares","2006-10-03","2007-04-09"]
["IJ16020405","Procure 30 AMP MCOR Modules (1)-Spares","2006-10-03","2007-04-09"]
["IJ16020410","Procure 15KW Power Supply-Spares","2006-10-03","2007-04-09"]
["IJ160300","MACHINE PROTECTION SUBSYSTEM SUMMARY","2006-10-02","2007-03-09"]
["IJ16030055","PROCUREMENT START - Injector MPS","2006-10-02","2006-09-29"]
["IJ16030056","Procure MPS Hardware","2006-10-02","2007-03-09"]
["IJ16030200","RCV: MPS Hardware/Material","2007-03-12","2007-03-09"]
["IJ16030240","COMP: Vendor Equip Fab/Assy - Ready for Instl","2007-03-12","2007-03-09"]
["IJ16030285","AVAIL: Injector MPS Equip ready for Install","2007-03-12","2007-03-09"]
["IJ160401","SOLENOID 1 PS 10KW SUMMARY","2005-12-01","2006-11-15",null,"2005-12-01"]
["IJ16040106","PROCUREMENT START - Solenoid 1 PS 10KW","2006-02-01","2006-01-31"]
["IJ16040107","10kw Power Supply - (Selenoid 1)","2005-12-01","2006-07-03",null,"2005-12-01"]
["IJ16040132","AVAIL: All Solenoid 1 PS 10KW parts","2006-07-05","2006-07-03"]
["IJ16040165","Conduct Design Review","2006-02-01","2006-02-01"]
["IJ16040170","COMP: Solenoid 1 PS 10KW Fab & Assembly","2006-10-19","2006-10-18"]
["IJ16040175","Perform Solenoid 1 PS 10KW Pre-Install Qual Test","2006-10-19","2006-11-15"]
["IJ16040180","AVAIL: Solenoid 1 PS 10KW Ready for Install","2006-11-16","2006-11-15"]
["IJ160402","SOLENOID 2 PS 15KW SUMMARY","2005-12-01","2006-11-15",null,"2005-12-01"]
["IJ16040206","PROCUREMENT START - Solenoid 2 PS 15KW","2006-02-01","2006-01-31"]
["IJ16040207","RCV: Power Supply - (Solenoid 2)","2006-05-11","2006-05-10"]
["IJ16040208","30kw Power Supply - (Solenoid 2)","2005-12-01","2006-05-10",null,"2005-12-01"]
["IJ16040255","AVAIL: All Solenoid 1 PS 15KW parts","2006-05-11","2006-05-10"]
["IJ16040284","Conduct Design Review","2006-02-01","2006-02-01"]
["IJ16040286","COMP: Solenoid 2 PS 15KW Fab & Assembly","2006-10-19","2006-10-18"]
["IJ16040288","Perform Solenoid 2 PS 15KW Pre-Install Qual Test","2006-10-19","2006-11-15"]
["IJ16040290","AVAIL: Solenoid 2 PS 15KW Ready for Install","2006-11-16","2006-11-15"]
["IJ160404","BX011-BX02 PS 15KW SUMMARY","2005-12-01","2006-11-15",null,"2005-12-01"]
["IJ16040406","PROCUREMENT START -BX011-BX02 PS 15KW","2006-02-01","2006-01-31"]
["IJ16040407","15kw Power Supply - (B1-2)","2005-12-01","2006-05-10",null,"2005-12-01"]
["IJ16040410","RCV: 15kw Power Supply (B1-2)","2006-05-11","2006-05-10"]
["IJ16040484","Conduct Design Review","2006-02-01","2006-02-01"]
["IJ16040486","COMP: BX011-BX02 PS 15KW Fab & Assembly","2006-05-11","2006-05-10"]
["IJ16040488","Perform BX011-BX02 PS 15KW Pre-Install Qual Test","2006-10-19","2006-11-15"]
["IJ16040490","AVAIL: BX011-BX02 PS 15KW Ready for Install","2006-11-16","2006-11-15"]
["IJ160405","BXS Spect  PS 15KW SUMMARY","2005-12-01","2006-11-15",null,"2005-12-01"]
["IJ16040506","PROCUREMENT START - BXS Spect  PS 15KW","2006-02-01","2006-01-31"]
["IJ16040507","15kw Power Supply (B3-Spect)","2005-12-01","2006-05-10",null,"2005-12-01"]
["IJ16040510","RCV: Power Supply (B3- Spect)","2006-05-11","2006-05-10"]
["IJ16040543","AVAIL: All BXS Spect  PS 15KW parts","2006-05-11","2006-05-10"]
["IJ16040582","Conduct Design Review","2006-02-01","2006-02-01"]
["IJ16040584","COMP: BXS Spect  PS 15KW Fab & Assembly","2006-05-11","2006-05-10"]
["IJ16040588","Perform BXS Spect  PS 15KW Pre-Install Qual Test","2006-10-19","2006-11-15"]
["IJ16040590","AVAIL: BXS Spect  PS 15KW Ready for Install","2006-11-16","2006-11-15"]
["IJ160406","MCOR_1 SUMMARY","2006-01-03","2006-11-15",null,"2006-01-03"]
["IJ16040606","PROCUREMENT START - MCOR_1 (12Amp)","2006-02-24","2006-02-23"]
["IJ16040607","RCV:12 Amp Power Supply (MCOR 1) (16 ps)","2006-07-25","2006-07-24"]
["IJ16040625","12 Amp Power Supply (MCOR 1) (16 ps)","2006-02-24","2006-07-24"]
["IJ16040667","AVAIL: All MCOR_1 parts","2006-07-25","2006-07-25"]
["IJ16040684","Conduct Design Review","2006-01-03","2006-02-01",null,"2006-01-03"]
["IJ16040686","COMP: MCOR_1 Fab & Assembly","2006-10-19","2006-10-18"]
["IJ16040688","Perform MCOR_1 Pre-Install Qual Test","2006-10-19","2006-11-15"]
["IJ16040690","AVAIL: MCOR_1 Ready for Install","2006-11-16","2006-11-15"]
["IJ160407","MCOR_2 SUMMARY","2006-02-01","2006-11-16"]
["IJ16040704","Conduct Design Panel","2006-10-03","2006-10-03"]
["IJ16040706","PROCUREMENT START - MCOR_2 (12Amp)","2006-02-01","2006-01-31"]
["IJ16040716","30 Amp Power Supply - (MCOR_2)","2006-02-01","2006-06-29"]
["IJ16040725","Perform MCOR_2 Pre-Install Qual Test","2006-10-19","2006-11-15"]
["IJ16040791","AVAIL: All MCOR_2 parts","2006-11-16","2006-11-16"]
["IJ16040792","RCV: 30 Amp Power Supply - (MCOR_2)","2006-06-30","2006-06-29"]
["IJ160408","MCOR_3 SUMMARY","2006-01-03","2006-11-15",null,"2006-01-03"]
["IJ16040806","PROCUREMENT START - MCOR_3 (30Amp)","2006-02-01","2006-01-31"]
["IJ16040807","RCV:30Amp Power Supply - (MCOR_3)","2006-06-30","2006-06-29"]
["IJ16040825","30Amp Power Supply - (MCOR_3)","2006-02-01","2006-06-29"]
["IJ16040863","AVAIL: All MCOR_3 parts","2006-06-30","2006-06-30"]
["IJ16040884","Conduct Design Review","2006-01-03","2006-02-01",null,"2006-01-03"]
["IJ16040886","COMP: MCOR_3 Fab & Assembly","2006-10-19","2006-10-18"]
["IJ16040888","Perform MCOR_3 Pre-Install Qual Test","2006-10-19","2006-11-15"]
["IJ16040890","AVAIL: MCOR_3 Ready for Install","2006-11-16","2006-11-15"]
["IJ160409","MCOR_4 SUMMARY","2006-01-03","2006-11-15",null,"2006-01-03"]
["IJ16040906","PROCUREMENT START - MCOR_4  (12Amp)","2006-02-01","2006-01-31"]
["IJ16040907","RCV:Smart Analog Monitor (VMIC 3122)","2006-06-30","2006-06-29"]
["IJ16040925","30 Amp Power Supply (MCOR_4)","2006-02-01","2006-06-29"]
["IJ16040972","AVAIL: All MCOR_4 parts","2006-06-30","2006-06-30"]
["IJ16040984","Conduct Design Review","2006-01-03","2006-02-01",null,"2006-01-03"]
["IJ16040986","COMP: MCOR_4 Fab & Assembly","2006-10-19","2006-10-18"]
["IJ16040988","Perform MCOR_4 Pre-Install Qual Test","2006-10-19","2006-11-15"]
["IJ16040990","AVAIL: MCOR_4 Ready for Install","2006-11-16","2006-11-15"]
["IJ160411","MISC HARDWARE SUMMARY","2005-09-01","2006-10-19",null,"2005-09-01"]
["IJ16041100","Design Cableplant and Racks","2005-09-01","2006-06-22",null,"2005-09-01"]
["IJ16041104","Captar Documents","2005-09-16","2006-02-14",null,"2005-09-16"]
["IJ16041115","PROCUREMENT START - Misc Hardware","2006-02-15","2006-02-14"]
["IJ16041116","Cableplant and Rack Hardware","2005-10-21","2006-07-21",null,"2005-10-21"]
["IJ16041119","RCV: Cableplant and Rack Hardware","2006-07-24","2006-07-21"]
["IJ16041153","Prep Bid Pak - Single Bay Racks (DC/I&C)","2005-09-30","2005-10-20",null,"2005-09-30","2005-10-20"]
["IJ16041154","RELEASE: RFP - Single Bay Racks (DC/I&C)","2006-02-01","2006-01-31"]
["IJ16041155","Vendors Prep Proposals - Single Bay Racks","2006-02-01","2006-03-01"]
["IJ16041156","RCV: Proposals - Single Bay Racks (DC/I&C)","2006-03-02","2006-03-01"]
["IJ16041157","Evaluate Proposals - Single Bay Racks (DC/","2006-03-02","2006-03-22"]
["IJ16041158","AWARD: Contract - Single Bay Racks (DC/I&C","2006-03-23","2006-03-23"]
["IJ16041159","Vendor Fab/Assy - Single Bay Racks","2006-03-24","2006-09-12"]
["IJ16041160","RCV: from Vendor - Single Bay Racks (DC/I&C)","2006-09-13","2006-09-12"]
["IJ16041163","Prep Bid Pak - Double Bay Racks","2005-09-30","2005-10-20",null,"2005-09-30","2005-10-20"]
["IJ16041164","RELEASE: RFP - Double Bay Racks","2006-02-01","2006-01-31"]
["IJ16041165","Vendors Prep Proposals - Double Bay Racks","2006-02-01","2006-03-01"]
["IJ16041166","RCV: Proposals - Double Bay Racks","2006-03-02","2006-03-01"]
["IJ16041167","Evaluate Proposals - Double Bay Racks","2006-03-02","2006-03-22"]
["IJ16041168","AWARD: Contract - Double Bay Racks","2006-03-23","2006-03-23"]
["IJ16041169","Vendor Fab/Assy - Double Bay Racks","2006-03-24","2006-09-12"]
["IJ16041170","RCV: from Vendor - Double Bay Racks","2006-09-13","2006-09-12"]
["IJ160412","New  PS 10KW SUMMARY","2005-12-01","2006-11-15",null,"2005-12-01"]
["IJ16041203","Prep Bid Pak - Cableplant Install(DC.I&C)-S20","2005-09-30","2005-10-20",null,"2005-09-30","2005-10-20"]
["IJ16041205","RELEASE: RFP - Cableplant Install(DC.I&C)-S20","2006-02-01","2006-01-31"]
["IJ16041206","PROCUREMENT START - Wiggler PS 10KW","2006-02-01","2006-01-31"]
["IJ16041207","Vendors Prep Prop-Cableplant Install(DC.I&C)-S20","2006-02-01","2006-03-01"]
["IJ16041209","RCV: Proposals - Cableplant Install(DC.I&C)-S20","2006-03-02","2006-03-01"]
["IJ16041210","RCV: Power Supply - (New)","2006-05-11","2006-05-10"]
["IJ16041211","10kw Power Supply - (New)","2005-12-01","2006-05-10",null,"2005-12-01"]
["IJ16041243","AVAIL: All Wiggler PS 10KW parts","2006-05-11","2006-05-10"]
["IJ16041260","COMP: Wiggler PS 10KW Fab & Assembly","2006-05-11","2006-05-10"]
["IJ16041262","Perform Wiggler PS 10KW Pre-Install Qual","2006-10-19","2006-11-15"]
["IJ16041264","AVAIL: Wiggler PS 10KW Ready for Install","2006-11-16","2006-11-15"]
["IJ16041267","Evaluate Prop-Cableplant Install(DC.I&C)-S20","2006-03-02","2006-03-15"]
["IJ16041268","AWARD: Contract - Cableplant Install(DC.I&C)-S20","2006-03-16","2006-03-16"]
["IJ16041269","AVAIL: Cableplant Ready to Install(DC.I&C)-S20","2006-06-27","2006-06-26"]
["IJ16041270","Vendor - Cableplant Install (DC. I&C)-S20","2006-04-03","2006-06-26"]
["IJ16041300","Integ Rack Rack HW & Internal AC Wiring - S20","2006-09-13","2006-09-28"]
["IJ16041305","Integ Rack Mount Pwr Supplies&Intra Cables - S20","2006-07-26","2006-10-18"]
["IJ16041315","Integ Rack/Crate Mount Cntrls&Intra-Cables - S20","2006-07-26","2006-09-06"]
["IJ16041320","Perform Pre-Install Testing Controls - S20","2006-09-29","2006-10-19"]
["IJ16041325","AVAIL:Preloaded Dbl Bay Racks Rdy to Insta - S20","2006-10-20","2006-10-19"]
["IJ17","INJECTOR INSTALLATION SUMMARY","2005-05-02","2007-11-26",null,"2005-05-02"]
["IJ1701","INJECTOR INFRASTRUCTURE INSTALL SUMMARY","2005-05-02","2007-03-07",null,"2005-05-02"]
["IJ17010010","Evaluate Data","2005-05-02","2005-05-31",null,"2005-05-02","2005-05-31"]
["IJ17010011","Quality Control of Network","2005-05-16","2005-05-27",null,"2005-05-16","2005-05-27"]
["IJ17010012","ED&I Engineering, Develop Installation Plan","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["IJ17010015","Quality Control of Support Bolts","2005-06-22","2005-09-30",null,"2005-06-22","2005-09-30"]
["IJ17010017","Fiducialize Components","2006-01-01","2006-11-01",null,"2006-01-01"]
["IJ17010020","Procure Alignment Parts","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ17010023","Pre-Align Supports","2006-11-02","2006-11-08"]
["IJ17010024","Align Gun","2006-11-09","2006-11-15"]
["IJ17010025","Mark Floor Support Bolts","2006-03-15","2006-03-28"]
["IJ17010026","Align Dipoles & Quads","2006-11-16","2006-12-15"]
["IJ17010027","Align Diagnostics","2007-01-02","2007-01-30"]
["IJ17010028","QC of Gun, Dipoles, Quads, & Diagnostics","2007-01-31","2007-02-13"]
["IJ17010030","Compute Layout Parameters","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["IJ17010100","REQD: All Inj InfraStruct Equip Ready for Instl","2006-10-20","2006-10-19"]
["IJ17010102","Engineering Support for Cable Plant","2005-06-15","2006-02-28",null,"2005-06-15"]
["IJ17010103","UTR Support for Cable Plant","2006-06-27","2006-06-26"]
["IJ17010110","Install Cableplant, Integ Cntrls&Pwr Conv Racks","2006-10-20","2007-01-04"]
["IJ17010115","Install LCW systems","2006-10-20","2007-01-04"]
["IJ17010135","Install Thermocouples (60)/Isoplanes","2006-10-20","2006-11-02"]
["IJ17010140","Align Systems","2007-01-05","2007-02-02"]
["IJ17010145","Pump Down and Leak Check","2007-02-14","2007-03-07"]
["IJ1702","INJECTOR CONTROLS SUBSYS INSTALL SUMMARY","2007-05-22","2007-06-19"]
["IJ17020100","REQD: All Inj Controls Equip Ready for Instl","2007-05-22","2007-05-21"]
["IJ17020105","Install Controls","2007-05-22","2007-06-19"]
["IJ17020110","AVAIL: Controls Installed","2007-06-20","2007-06-19"]
["IJ1703","INJECTOR LASERS INSTALLATION SUMMARY","2005-10-01","2007-03-28",null,"2005-10-01"]
["IJ17030103","REQD:Laser Bay Opt Tables/Legs/Encls/Alignmt Lsr","2006-05-11","2006-05-10"]
["IJ17030105","Install Laser Bay Optical Tables/Alignment Laser","2006-10-02","2006-10-13"]
["IJ17030108","REQD: Vertical optical paths","2005-10-01","2005-09-30",null,"2005-10-01","2005-09-30"]
["IJ17030110","Install vertical optical paths","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["IJ17030112","REQD: Laser Heater optical paths","2006-07-03","2006-06-30"]
["IJ17030115","Install laser heater optical path","2006-07-03","2006-07-24"]
["IJ17030117","REQD: EO optical paths","2007-03-08","2007-03-07"]
["IJ17030120","Install EO optical paths","2007-03-08","2007-03-28"]
["IJ17030122","REQD: Synch Light Tube/Light Path for Strk Cam","2006-05-25","2006-05-24"]
["IJ17030125","Install Synch Light Tube/Light Path for Strk Cam","2006-05-25","2006-06-15"]
["IJ17030130","AVAIL: Laser Tables & Optical Paths Installed","2007-03-29","2007-03-28"]
["IJ1704","RF GUN & LOAD LOCK INSTALLATION SUMMARY","2006-02-01","2006-10-19"]
["IJ17040000","REQD: RF Gun Support Assy Ready for Instl","2006-05-01","2006-04-28"]
["IJ17040005","REQD: RF Gun Assembly Ready for Instl","2006-10-13","2006-10-12"]
["IJ17040010","REQD: Load Lock Support Assy Ready for Instl","2006-05-31","2006-05-30"]
["IJ17040015","REQD: Gun Load Lock Assy Ready for Instl","2006-02-01","2006-01-31"]
["IJ17040025","REQD: Gun Solenoid Ready for Instl","2006-06-27","2006-06-26"]
["IJ17040030","REQD: Corrector Supt Assy Ready for Instl","2006-05-11","2006-05-10"]
["IJ17040105","Install RF Gun Support Assy","2006-08-22","2006-09-05"]
["IJ17040110","Install RF Gun Assembly","2006-10-13","2006-10-19"]
["IJ17040115","Install Load Lock Support Assy","2006-05-31","2006-06-06"]
["IJ17040120","Install Gun Load Lock Assembly","2006-05-11","2006-05-17"]
["IJ17040121","AVAIL: RF Gun Installed & Aligned","2006-10-20","2006-10-19"]
["IJ17040122","AVAIL: Load Lock Installed & Aligned","2006-10-20","2006-10-19"]
["IJ17040125","Install Gun Sol Support Assembly","2006-08-22","2006-08-28"]
["IJ17040130","Install Gun Solenoid","2006-08-22","2006-08-28"]
["IJ17040135","Install Corrector Supt Assembly","2006-08-22","2006-08-28"]
["IJ17040140","Install Corrector Assembly","2006-08-22","2006-08-28"]
["IJ17040145","Install BPMs Supt Assy","2006-08-22","2006-08-28"]
["IJ17040150","Install BPMs Assy","2006-08-22","2006-08-28"]
["IJ17040155","Install Faraday Cups Supt Assy","2006-08-22","2006-08-28"]
["IJ17040160","Install Faraday Cups Assy","2006-08-22","2006-08-28"]
["IJ17040165","Install Gun E-Spect Support Assy","2006-08-22","2006-08-28"]
["IJ17040175","Install Dipoles Supt Assembly Ready for Install","2006-08-22","2006-08-28"]
["IJ17040180","Install Dipoles Assembly","2006-08-22","2006-08-28"]
["IJ1705","GUN to LINAC SECTION (GTL) INSTALLATION SUMMARY","2006-02-01","2006-10-19"]
["IJ17050105","Install GTL BPMs","2006-08-22","2006-09-05"]
["IJ17050110","Install GTL YAG1","2006-08-22","2006-08-28"]
["IJ17050115","Install GTL Current Monitors (CM1)","2006-08-22","2006-08-28"]
["IJ17050120","Install GTL E/O (EO1) BL Monitor/Opt Tables","2006-08-22","2006-08-28"]
["IJ17050125","Install GTL RF Phase Cavity","2006-08-22","2006-09-05"]
["IJ17050130","Install GTL Steering Coils","2006-08-22","2006-08-28"]
["IJ17050135","Install GTL Vacuum Components","2006-08-22","2006-09-05"]
["IJ17050140","Install GS Supports","2006-08-22","2006-08-28"]
["IJ17050145","Install GS Dipole","2006-08-22","2006-08-28"]
["IJ17050150","Install GS Current Monitor (CM2)","2006-08-22","2006-08-28"]
["IJ17050155","Install GS BPM (2)","2006-08-22","2006-08-28"]
["IJ17050160","Install GS Faraday Cup/YAG2","2006-08-22","2006-08-28"]
["IJ17050165","Install GS Quad Supports (3)","2006-08-22","2006-08-28"]
["IJ17050170","Install GS Quad (3)","2006-08-22","2006-08-28"]
["IJ17050175","Install GS Dump Shielding","2006-08-22","2006-08-28"]
["IJ17050180","AVAIL: GTL Installed","2006-09-06","2006-09-05"]
["IJ17050181","AVAIL: GS Installed","2006-08-29","2006-08-28"]
["IJ1706","INJECTOR LINAC STRUCTURES INSTALL SUMMARY","2006-05-01","2006-07-25"]
["IJ17060005","REQD: Linac Supports Ready for Instl","2006-06-13","2006-06-12"]
["IJ17060015","REQD: LO-2 Structure Ready for Instl","2006-05-01","2006-04-28"]
["IJ17060105","Install supports","2006-06-13","2006-07-11"]
["IJ17060110","Install LO-1 structure","2006-06-13","2006-06-19"]
["IJ17060111","AVAIL:  LO-1 structures installed","2006-07-19","2006-07-25"]
["IJ17060115","Install LO-2 structure","2006-06-13","2006-06-19"]
["IJ17060120","Install Loads","2006-06-13","2006-06-19"]
["IJ17060125","Install Linac Solenoid Support","2006-06-13","2006-06-19"]
["IJ17060130","Install Linac Solenoid","2006-06-13","2006-06-26"]
["IJ17060135","Install Plumbing","2006-06-13","2006-07-18"]
["IJ1707","L0-1 to L0-2 Section (L0-1TL0-2) INSTALL SUMMARY","2006-05-16","2006-07-17"]
["IJ17070021","REQD: Steering Coils Ready for Instl","2006-05-16","2006-05-15"]
["IJ17070105","Install RF Phase Cavity","2006-07-03","2006-07-10"]
["IJ17070110","Install Quads","2006-07-03","2006-07-10"]
["IJ17070115","Install BPM (2)","2006-07-03","2006-07-10"]
["IJ17070120","Install Steering Coil (4)","2006-07-03","2006-07-10"]
["IJ17070125","Install YAG (1)","2006-07-03","2006-07-10"]
["IJ17070130","Install Vacuum components","2006-07-03","2006-07-10"]
["IJ17070135","Install Current Monitor (1)","2006-07-03","2006-07-10"]
["IJ17070140","Install tube support structure","2006-07-03","2006-07-10"]
["IJ17070145","Final Alignment","2006-07-11","2006-07-17"]
["IJ17070150","AVAIL: LO-1TLO-2 Installed","2006-07-18","2006-07-17"]
["IJ1708","LINAC TO DL1 INSTALL & ALIGN SUMMARY","2005-10-03","2006-05-31",null,"2005-10-03"]
["IJ17080015","REQD:RF Kicker Ready for Instl","2006-05-02","2006-05-01"]
["IJ17080030","REQD: Supports Ready for Instl","2005-10-04","2005-10-03",null,"2005-10-04","2005-10-03"]
["IJ17080035","REQD: PPS Stopper Ready for Instl","2005-10-08","2005-10-07",null,"2005-10-08","2005-10-07"]
["IJ17080045","REQD: Quads Ready for Instl","2006-02-01","2006-01-31"]
["IJ17080050","REQD: BPMs Ready for Instl","2006-02-01","2006-01-31"]
["IJ17080055","REQD: Steering Coils Ready for Instl","2006-02-01","2006-01-31"]
["IJ17080060","REQD: OTRs Ready for Instl","2006-02-01","2006-01-31"]
["IJ17080065","REQD: BPMs Ready for Instl","2006-02-01","2006-01-31"]
["IJ17080070","REQD: Current Monitor Rdy for Instl","2006-02-01","2006-01-31"]
["IJ17080105","LTDL1-North Summary","2006-05-15","2006-05-26"]
["IJ17080110","Install supports  to VACV  N","2006-05-15","2006-05-19"]
["IJ17080115","Install Quads (4)","2006-05-15","2006-05-26"]
["IJ17080120","Install RF Kicker","2006-05-15","2006-05-26"]
["IJ17080130","Install Current Monitors","2006-05-15","2006-05-19"]
["IJ17080131","Install BPMs (4)","2006-05-15","2006-05-19"]
["IJ17080132","Install Steering Coil (1)","2006-05-15","2006-05-19"]
["IJ17080133","Install EO2","2006-05-15","2006-05-19"]
["IJ17080135","Final Alignment","2006-05-30","2006-05-31"]
["IJ17082140","LTDL1-South Summary","2006-02-01","2006-02-07"]
["IJ17082145","Install supports","2005-10-03","2005-10-31",null,"2005-10-03","2005-10-31"]
["IJ17082150","Install PPS Stopper","2005-10-17","2005-10-31",null,"2005-10-17","2005-10-31"]
["IJ17082160","Install Quads (2)","2006-02-01","2006-02-07"]
["IJ17082165","Install BPM","2006-02-01","2006-02-07"]
["IJ17082170","Install Steering Coil (3)","2006-02-01","2006-02-07"]
["IJ17082175","Install OTR (2)","2006-02-01","2006-02-07"]
["IJ17082180","Install BPM (6)","2006-02-01","2006-02-07"]
["IJ17082185","Install Current Monitor","2006-02-01","2006-02-07"]
["IJ17082190","AVAIL: LTDL1 Installed","2006-02-08","2006-02-07"]
["IJ1709","DOG LEG 1 BEND (DL1) INSTALLATION SUMMARY","2006-08-01","2006-09-19"]
["IJ17090005","REQD: Supports Ready for Instl","2006-08-01","2006-07-31"]
["IJ17090010","REQD:Dipoles (B01-B02) Ready for Instl","2006-08-01","2006-07-31"]
["IJ17090020","REQD: Quads Ready for Instl","2006-08-01","2006-07-31"]
["IJ17090025","REQD: BPMs Ready for Instl","2006-08-01","2006-07-31"]
["IJ17090030","REQD: Steering Coils Ready for Instl","2006-08-01","2006-07-31"]
["IJ17090035","REQD: OTR Ready for Instl","2006-08-01","2006-07-31"]
["IJ17090040","REQD: Toroid Ready for Instl","2006-08-01","2006-07-31"]
["IJ17090055","REQD: DL1 Vacuum Chamber Ready for Instl","2006-08-01","2006-07-31"]
["IJ17090102","Install DL1 Vacuum Chamber","2006-08-01","2006-08-01"]
["IJ17090103","AVAIL: DL1 Vacuum Chamber installed","2006-08-01","2006-08-01"]
["IJ17090105","Install supports","2006-08-02","2006-08-15"]
["IJ17090110","Install Dipoles (2) (B01-B02)","2006-08-01","2006-08-07"]
["IJ17090120","Install Quads (3)","2006-08-01","2006-08-14"]
["IJ17090125","Install BPM (1)","2006-08-01","2006-08-07"]
["IJ17090130","Install Steering Coil (1)","2006-08-01","2006-08-07"]
["IJ17090135","Install OTR (1)","2006-08-01","2006-08-07"]
["IJ17090140","Install Toroid","2006-08-01","2006-08-07"]
["IJ17090155","Final Alignment","2006-08-16","2006-08-29"]
["IJ1710","DL1 to LINAC (DL1TL) INSTALLATION SUMMARY","2006-08-01","2006-09-19"]
["IJ17100000","REQD: Supports Ready for Instl","2006-08-01","2006-07-31"]
["IJ17100005","REQD: Quads Ready for Instl","2006-08-01","2006-07-31"]
["IJ17100010","REQD: BPM Ready for Instl","2006-08-01","2006-07-31"]
["IJ17100015","REQD: Steering Coils Ready for Instl","2006-08-01","2006-07-31"]
["IJ17100020","REQD: OTR Ready for Instl","2006-08-01","2006-07-31"]
["IJ17100025","REQD: Current Monitor Ready for Instl","2006-08-01","2006-07-31"]
["IJ17100105","Install supports","2006-08-01","2006-08-14"]
["IJ17100110","Install Quads (2)","2006-08-01","2006-08-07"]
["IJ17100115","Install BPM (1)","2006-08-08","2006-08-14"]
["IJ17100120","Install Steering Coil (2)","2006-08-08","2006-08-14"]
["IJ17100125","Install OTR (1)","2006-08-08","2006-08-14"]
["IJ17100130","Install Current Monitor (1)","2006-08-08","2006-08-14"]
["IJ17100135","Final Alignment","2006-08-15","2006-08-28"]
["IJ17100140","AVAIL: DL1TL Installed","2006-08-29","2006-08-28"]
["IJ1710_010","REQD:  Insertion Area Components RFI","2006-08-22","2006-08-21"]
["IJ1710_020","AVAIL:  Insertion Area Components Installed","2006-09-20","2006-09-19"]
["IJ1711","STRAIGHT AHEAD BEAMLINE (SAB) INSTALL SUMMARY","2006-08-01","2006-09-19"]
["IJ17110000","REQD: SAB Spectrometer Dipole Ready for Instl","2006-08-01","2006-07-31"]
["IJ17110005","REQD: SAB Quadrupoles (3) Ready for Instl","2006-08-01","2006-07-31"]
["IJ17110010","REQD: SAB Current Monitor (1) Ready for Instl","2006-08-01","2006-07-31"]
["IJ17110015","REQD: SAB BPM Ready for Instl","2006-08-01","2006-07-31"]
["IJ17110020","REQD: SAB OTR/YAG (1) Ready for Instl","2006-08-01","2006-07-31"]
["IJ17110025","REQD: SAB Vacuum Chamber Ready for Instl","2006-08-01","2006-07-31"]
["IJ17110030","REQD: SAB Beam Dump & Shielding Ready for Instl","2006-08-01","2006-07-31"]
["IJ17110035","REQD: SAB Supports Ready for Instl","2006-08-01","2006-07-31"]
["IJ17110036","REQD: SAB Steering Coils (2) Ready for Instl","2006-08-01","2006-07-31"]
["IJ17110105","Install SAB Spectrometer Dipole","2006-08-22","2006-08-28"]
["IJ17110110","Install SAB Quadrupoles (3)","2006-08-22","2006-09-05"]
["IJ17110115","Install SAB Current Monitor (1)","2006-08-22","2006-08-28"]
["IJ17110120","Install SAB BPM (1)","2006-08-22","2006-08-28"]
["IJ17110125","Install SAB OTR/YAG (1)","2006-08-22","2006-08-28"]
["IJ17110130","Install SAB Vacuum Chamber and Components","2006-08-22","2006-08-28"]
["IJ17110135","Install SAB Beam Dump and Shielding","2006-08-22","2006-09-05"]
["IJ17110140","Install SAB Supports","2006-08-22","2006-09-05"]
["IJ17110141","Install Steering Coils (2)","2006-08-22","2006-08-28"]
["IJ17110145","Final Alignment","2006-09-06","2006-09-19"]
["IJ17110150","AVAIL: SAB Installed","2006-09-20","2006-09-19"]
["IJ1711_010","REQD:  Spectrometer Area Components RFI","2006-08-22","2006-08-21"]
["IJ1711_020","AVAIL:  Spectrometer Area Components Installed","2006-09-20","2006-09-19"]
["IJ1712","INJECTOR RF WAVEGUIDE INSTALLATION SUMMARY","2005-10-17","2006-08-09",null,"2005-10-17"]
["IJ17120000","REQD:Vertical Drop Waveguide Rdy to Install","2005-10-18","2005-10-17",null,"2005-10-18","2005-10-17"]
["IJ17120003","REQD:Transverse Kicker Waveguide Rdy to Install","2006-08-01","2006-07-31"]
["IJ17120005","Install Vertical Drop Waveguide","2005-10-17","2005-10-31",null,"2005-10-17","2005-10-31"]
["IJ17120006","Install Klystron Housing Waveguide","2006-02-01","2006-02-09"]
["IJ17120007","Install Injector Housing Waveguide","2006-02-10","2006-02-21"]
["IJ17120008","Install Transverse Kicker Waveguide","2006-08-01","2006-08-09"]
["IJ17120010","AVAIL: Vertical Drop Waveguide Installed","2005-11-01","2005-10-31",null,"2005-11-01","2005-10-31"]
["IJ17120011","AVAIL: Klystron Housing Waveguide Installed","2006-02-10","2006-02-09"]
["IJ17120012","AVAIL: Injector Housing Waveguide Installed","2006-02-22","2006-02-21"]
["IJ17120013","AVAIL: Transverse Kicker Waveguide Installed","2006-08-10","2006-08-09"]
["IJ17120018","Install RF Waveguides","2006-04-03","2006-04-07"]
["IJ1712_010","REQD:  Inj RF High Power Components RFI","2006-02-01","2006-01-31"]
["IJ1712_020","AVAIL:  Inj RF High Power Components Installed","2006-08-10","2006-08-09"]
["IJ1713","INJECTOR RF SUBSYS INSTALLATION SUMMARY","2007-01-26","2007-05-25"]
["IJ17130000","AVAIL: Injector RF Subsystem Installed","2007-01-26","2007-01-25"]
["IJ17130100","REQD: All Inj RF Subsys Equip Ready for Instl","2007-01-26","2007-01-25"]
["IJ1713_010","REQD:  Inj RF Low Level Components RFI","2007-05-29","2007-05-25"]
["IJ1713_020","AVAIL:  Inj RF Low Level Components Installed","2007-01-26","2007-01-25"]
["IJ1714","CATHODE AND LOAD LOCK INSTALLATION SUMMARY","2006-02-01","2007-05-17"]
["IJ17140000","REQD: Cathode Assy Ready for Instl","2006-02-01","2006-01-31"]
["IJ17140005","REQD: CP Load Lock Supts Ready for Instl","2006-02-01","2006-01-31"]
["IJ17140010","REQD: CP Load Lock Ready for Instl","2006-02-01","2006-01-31"]
["IJ17140015","REQD: CP Station Ready for Instl","2007-04-27","2007-04-26"]
["IJ17140020","REQD: CP Lab Ready for Instl","2006-02-01","2006-01-31"]
["IJ17140105","Install CP Cathode Assembly","2006-02-01","2006-02-22"]
["IJ17140110","Install CP Load Lock Supports Ready for Install","2006-02-01","2006-02-22"]
["IJ17140115","Install CP Load Lock","2006-02-01","2006-02-22"]
["IJ17140120","Install CP Station","2007-04-27","2007-05-17"]
["IJ17140125","Install CP Lab Infrastructure","2006-02-01","2006-02-22"]
["IJ17140130","AVAIL: CP Station Installed","2007-05-18","2007-05-17"]
["IJ1714_010","REQD:  Cathode & Load Lock Components RFI","2006-02-01","2006-01-31"]
["IJ1714_020","AVAIL:  Cathode & Load Lock Components Installed","2007-05-18","2007-05-17"]
["IJ1715","INJECTOR LASER HEATER SUBSYS INSTALL SUMMARY","2007-09-05","2007-11-26"]
["IJ17150000","REQD: Enclosures,Tubes&Supports Ready for Instl","2007-11-08","2007-11-07"]
["IJ17150005","REQD:Magnet Supports Ready for Instl","2007-09-05","2007-09-04"]
["IJ17150020","REQD: Undulator Ready for Instl","2007-09-05","2007-09-04"]
["IJ17150105","Install  Enclosures,Tubes&Supports","2007-11-08","2007-11-21"]
["IJ17150106","AVAIL: Enclosures,Tubes&Supports Installed","2007-11-26","2007-11-21"]
["IJ17150110","Install Magnet Supports","2007-09-05","2007-09-18"]
["IJ17150115","Install Photon Diagnostics Supports","2007-09-19","2007-09-25"]
["IJ17150116","AVAIL: Photon Diagnostics Supports Installed","2007-09-26","2007-09-25"]
["IJ17150120","Install Beampipe","2007-09-05","2007-09-18"]
["IJ17150125","Install Undulator","2007-09-05","2007-09-25"]
["IJ17150130","AVAIL: Laser Heater Installed","2007-09-26","2007-09-25"]
["IJ1715_010","REQD:  Inj Laser Heater Components RFI","2007-09-05","2007-09-04"]
["IJ1715_020","AVAIL:  Inj Laser Heater Components Installed","2007-11-26","2007-11-21"]
["IJ1717","POWER CONVERSION SUBSYSTEM INSTALL SUMMARY","2006-11-16","2007-06-28"]
["IJ17170000","REQD: Injector MCOR 1","2006-11-16","2006-11-15"]
["IJ17170005","Install Injector MCOR 1","2006-11-16","2006-11-22"]
["IJ17170010","REQD: Injector MCOR 2","2006-11-17","2006-11-16"]
["IJ17170015","Install Injector MCOR 2","2006-11-17","2006-11-27"]
["IJ17170020","REQD: Injector MCOR 3","2006-11-16","2006-11-15"]
["IJ17170025","Install Injector MCOR 3","2006-11-16","2006-11-22"]
["IJ17170030","REQD: Injector MCOR 4","2006-11-16","2006-11-15"]
["IJ17170035","Install Injector MCOR 4","2006-11-16","2006-11-22"]
["IJ17170040","REQD: Wiggler PS 15KW","2006-11-16","2006-11-15"]
["IJ17170045","Install Wiggler PS 15KW","2006-11-16","2006-11-22"]
["IJ17170050","REQD: Injector Solenoid 1PS 15KW","2006-11-16","2006-11-15"]
["IJ17170055","Install Injector Solenoid 1PS 15KW","2006-11-16","2006-11-22"]
["IJ17170060","REQD: Injector Solenoid 2PS 30KW","2006-11-16","2006-11-15"]
["IJ17170065","Install Injector Solenoid 2PS 30KW","2006-11-16","2006-11-22"]
["IJ17170070","REQD: Injector B0.5 Spect PS 2KW","2006-11-16","2006-11-15"]
["IJ17170075","Install Injector B0.5 Spect PS 2KW","2006-11-16","2006-11-22"]
["IJ17170080","REQD: Injector B1-2 PS 15KW","2006-11-16","2006-11-15"]
["IJ17170085","Install Injector B1-2 PS 15KW","2006-11-16","2006-11-22"]
["IJ17170090","REQD: Injector B3 Spect PS 15KW","2006-11-16","2006-11-15"]
["IJ17170095","Install Injector B3 Spect PS 15KW","2006-11-16","2006-11-22"]
["IJ17170100","REQD: Injector MPS Equipment","2007-03-12","2007-03-09"]
["IJ17170105","Install Injector MPS Equipment","2007-03-12","2007-03-16"]
["IJ17170110","REQD: Injector PPS Equipment","2007-06-22","2007-06-21"]
["IJ17170115","Install Injector PPS Equipment","2007-06-22","2007-06-28"]
["IJ17170120","REQD: Laser Room PPS","2007-01-16","2007-01-12"]
["IJ17170122","AVAIL: Power Conversion System Installed","2007-06-29","2007-06-28"]
["IJ17170125","Install Laser Room PPS","2007-01-16","2007-01-22"]
["IJ1717_010","REQD:  Injector Power Conv Components RFI","2007-01-16","2007-01-12"]
["IJ1717_020","AVAIL:  Injector Power Conv Components Installed","2007-06-29","2007-06-28"]
["IJ17_30010","REQD:  Injector Laser Components RFI","2006-05-25","2006-05-24"]
["IJ17_30020","AVAIL:  Injector Laser Components Installed","2007-03-29","2007-03-28"]
["IJ17_40010","REQD:  Gun Area Components RFI","2006-08-22","2006-08-21"]
["IJ17_40020","AVAIL: Gun Area Components Installed","2006-10-20","2006-10-19"]
["IJ17_60010","REQD:  Accelerator Area Components RFI","2006-06-13","2006-06-12"]
["IJ17_60020","AVAIL:  Accelerator Area Components Installed","2006-07-26","2006-07-25"]
["IJ17_70010","REQD:  Heater Area Components RFI","2006-07-03","2006-06-30"]
["IJ17_70020","AVAIL:  Heater Area Components Installed","2006-07-18","2006-07-17"]
["IJ17_80010","REQD:  Wall Area Components RFI","2005-10-08","2005-10-07",null,"2005-10-08","2005-10-07"]
["IJ17_80020","AVAIL:  Wall Area Components Installed","2006-02-08","2006-02-07"]
["IJ21702","DRIVE LASER COMMISSIONING SUMMARY","2006-05-25","2007-10-09"]
["IJ21702115","Integrate: Drive Laser","2006-05-25","2006-07-07"]
["IJ21702117","Integrate: OSC Diagnostics","2006-07-10","2006-07-14"]
["IJ21702120","Checkout & Integrate: Pre-Amp Diagnostics","2006-07-17","2006-08-04"]
["IJ21702130","Checkout & Integrate: Low Power Compressor","2006-11-21","2006-12-06"]
["IJ21702140","Checkout & Integrate: Final Amplifier diagnostic","2006-12-07","2007-01-19"]
["IJ21702180","Checkout & Integrate:Timing stability monitoring","2007-02-12","2007-04-09"]
["IJ21702220","Checkout & Integrate: Beam relay & Encl","2007-04-10","2007-04-23"]
["IJ21702240","Checkout & Integrate: UV conversion diagnostics","2007-01-22","2007-02-09"]
["IJ21702290","Checkout & Integrate: UV transport & launch Opt","2007-04-24","2007-06-05"]
["IJ21702355","AVAIL: UV Beam to the Cathode","2007-06-06","2007-06-05"]
["IJ21702360","UV Conditioning","2007-06-06","2007-10-09"]
["IJ21702365","Integration of the Drive Laser Controls","2007-01-29","2007-06-05"]
["IJ21702367","C/O & Integ: Visible Beam transport & diag","2007-03-29","2007-05-09"]
["IJ21702369","C/O & Integ: IR Beam transport & diag","2007-05-10","2007-05-31"]
["IJ21702370","AVAIL: Drive Laser","2007-10-10","2007-10-09"]
["IJ21703","RF Conditioning","2007-06-29","2007-08-31"]
["IJ21704000","RF Gun Operation with Beam","2007-09-04","2007-12-05"]
["IJ21704005","RF Gun Operation with Beam","2007-12-06","2008-01-10"]
["IJ21705","L0-1 & L0-2 Commissioning","2007-10-18","2008-02-06"]
["IJ21706","L0 & SAB Commissioning","2007-12-05","2008-01-24"]
["IJ21707","DL1 Commissioning","2008-01-25","2008-03-05"]
["IJ21708","Injector Optimization","2008-03-06","2008-08-20"]
["IJ22320000","Drive Laser Spares","2006-10-03","2007-08-30"]
["IJ22410000","RF Gun R&D (GTF)","2005-05-02","2005-11-30",null,"2005-05-02","2005-11-30"]
["IJ22410001","RF Gun R&D (GRF) Procurement","2005-05-02","2005-11-30",null,"2005-05-02","2005-11-30"]
["IJ22410020","GTF - Demostrate sustained 120MV/m gun ops","2005-11-28","2006-01-30",null,"2005-11-28","2006-01-30"]
["IJ22410030","GTF - RF pulse shaping, pwr dissapation for gun","2005-12-01","2006-01-30",null,"2005-12-01","2006-01-30"]
["IJ22410040","GTF - Test RF H+ plasma cleaning","2006-02-01","2006-03-15"]
["IJ22410050","GTF - Install new cathode/test H+ beam cleaner","2005-11-01","2006-03-30",null,"2005-11-01"]
["IJ22410060","GTF - Reconstruct 4D tomographic","2006-04-03","2006-05-15"]
["IJ22410070","GTF - Test digital cameras for LCLS Injector","2005-12-01","2006-05-15",null,"2005-12-01"]
["IJ22410080","GTF - Meas resolution of YAG screens","2006-05-15","2006-07-03"]
["IJ22410090","GTF - Procure materials, laser parts, lenses","2005-12-01","2006-06-01",null,"2005-12-01"]
["IJ22410100","Cathode - Modify SLAC Physical Elecrics Syst","2005-11-07","2005-12-30",null,"2005-11-07","2005-12-30"]
["IJ22410110","Cathode - Meas QE v Wavelength of Sample/Cathode","2005-11-07","2006-06-01",null,"2005-11-07"]
["IJ22410120","Cathode - Test cleaned samples and cathodes","2005-11-07","2006-06-01",null,"2005-11-07"]
["IJ22410130","Cathode - Establish cathode txfer method","2006-06-02","2006-07-03"]
["IJ22410140","Cathode - Procure cathode materials","2005-11-07","2006-06-01",null,"2005-11-07"]
["IJ22520000","GTL Spares","2006-10-03","2007-08-30"]
["IJ22620000","Linac Spares","2006-10-03","2007-08-30"]
["IJ22720000","L0-1 to L0-2 Spares","2006-10-03","2007-08-30"]
["IJ22820000","Linac to DL1 Spares","2006-10-03","2007-08-30"]
["IJ22920000","DL1 Spares","2006-10-03","2007-08-30"]
["IJ22A20000","DL1 to Linac Spares","2006-10-03","2007-08-30"]
["IJ22B20000","SAB Spares","2006-10-03","2007-08-30"]
["IJ22C20000","RF Waveguides Spares","2006-10-03","2007-08-30"]
["IJ22E20000","CP Spares","2006-10-03","2007-08-30"]
["IJ301_1010","Conduct UV Spatial Shaping Test (ANL)","2005-05-02","2006-02-28",null,"2005-05-02"]
["IJ301_2500","Modeling - integrated model","2005-08-01","2005-08-15",null,"2005-08-01","2005-08-15"]
["IJ301_2510","Modeling - modeling and validation","2005-08-15","2006-05-31",null,"2005-08-15"]
["IJ301_2520","Modeling - convert then stretch","2005-08-15","2005-12-30",null,"2005-08-15","2005-12-30"]
["IJ301_2530","Modeling - review","2006-03-01","2006-03-01"]
["IJ301_2540","Temporal Pulse Shaping - IR shaping","2005-08-01","2006-05-01",null,"2005-08-01"]
["IJ301_2545","Temporal Pulse Shaping - review","2006-05-01","2006-05-01"]
["IJ301_2550","Temporal Pulse Shaping - blue shaping","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["IJ301_2560","Temporal Pulse Shaping - UV shaping","2006-02-01","2006-01-31"]
["IJ301_2590","UV Conversion - activate initial crystals","2005-08-01","2005-11-07",null,"2005-08-01","2005-11-07"]
["IJ301_2600","UV Conversion - specify final crystals","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ301_2610","UV Conversion - procure final crystals","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ301_2620","UV Conversion - activate final crystals","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["IJ301_2630","UV Conversion - review","2006-02-01","2006-02-01"]
["IJ301_2640","IR Diagnostics - Design and specify","2005-08-01","2005-08-30",null,"2005-08-01","2005-08-30"]
["IJ301_2650","IR Diagnostics - review","2005-08-01","2005-08-30",null,"2005-08-01","2005-08-30"]
["IJ301_2660","IR Diagnostics - final design","2005-08-01","2005-08-30",null,"2005-08-01","2005-08-30"]
["IJ301_2670","IR Diagnostics - procure","2005-08-01","2005-08-30",null,"2005-08-01","2005-08-30"]
["IJ301_2680","IR Diagnostics - activate","2005-08-01","2005-08-30",null,"2005-08-01","2005-08-30"]
["IJ301_2690","Blue Diagnostics - design and specify","2005-08-01","2005-08-30",null,"2005-08-01","2005-08-30"]
["IJ301_2700","Blue Diagnostics - procure","2005-08-01","2005-08-30",null,"2005-08-01","2005-08-30"]
["IJ301_2710","Blue Diagnostics - activate","2005-10-03","2005-12-30",null,"2005-10-03","2005-12-30"]
["IJ301_2720","UV Diagnostics - design and specify","2005-08-01","2005-08-30",null,"2005-08-01","2005-08-30"]
["IJ301_2730","UV Diagnostics - procure","2005-08-01","2005-08-30",null,"2005-08-01","2005-08-30"]
["IJ301_2740","UV Diagnostics - activate","2005-10-03","2006-03-31",null,"2005-10-03"]
["IJ301_2745","UV Diagnostics - reveiw","2006-04-03","2006-04-03"]
["IJ301_2750","Cathode Launch Optics - test prototype optics","2006-04-04","2006-07-06"]
["IJ301_2760","Steering Stabilization - support design","2005-08-01","2005-12-30",null,"2005-08-01","2005-12-30"]
["IJ301_2780","Support Drive Laser Intgr - integrate shaping","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["IJ308_0100","Finalize the design (for normal incidence)","2005-08-15","2006-03-30",null,"2005-08-15"]
["IJ308_0110","Create Assembly Drawings","2006-03-31","2006-08-21"]
["IJ308_0120","Release Drawings","2006-08-22","2006-09-19"]
["IJ401_1005","Gun Design - Physics (BCR-IJ22)","2005-09-01","2005-09-30",null,"2005-09-01","2005-09-30"]
["IJ401_1010","Mechanical Design RF Gun","2005-05-02","2005-11-30",null,"2005-05-02","2005-11-30"]
["IJ401_1020","COMP:  RF Features Incorporated into Design","2005-12-01","2005-11-30",null,"2005-12-01","2005-11-30"]
["IJ401_1030","COMP:  RF Gun Mechanical Design Review","2005-08-11","2005-08-10",null,"2005-08-11","2005-08-10"]
["IJ401_1040","Design/Draft RF Gun","2005-05-15","2005-12-30",null,"2005-05-15","2005-12-30"]
["IJ401_1050","Procure RF Gun Parts","2005-10-20","2006-04-03",null,"2005-10-20"]
["IJ401_1060","Fabricate RF Gun","2006-05-23","2006-09-14"]
["IJ401_1070","Cold Test RF Gun","2006-09-15","2006-09-21"]
["IJ401_1080","Bake RF Gun","2006-09-22","2006-10-05"]
["IJ401_1090","Post Bake Assembly","2006-10-06","2006-10-12"]
["IJ401_1100","AVAIL: RF Gun Assembly Ready for Install","2006-10-13","2006-10-12"]
["IJ401_1110","Gun Design for Normal Incidence","2005-09-01","2005-09-30",null,"2005-09-01","2005-09-30"]
["IJ401_1120","Procure Hardware for Normal Incidence","2005-11-01","2005-12-30",null,"2005-11-01","2005-12-30"]
["IJ401_1130","Procure Extra Valve for RF Gun","2005-11-01","2006-03-01",null,"2005-11-01"]
["IJ401_1140","Machine RF Gun Parts","2005-12-01","2006-05-01",null,"2005-12-01"]
["IJ401_1150","QC Machine Parts","2006-01-01","2006-05-01",null,"2006-01-01"]
["IJ401_1160","Clean & Plate Machine Parts","2006-05-02","2006-05-22"]
["IJ401_1170","Design Gun Hot Test","2005-12-01","2006-02-06",null,"2005-12-01"]
["IJ401_1180","Design/Draft RF Hot Test Componenets","2005-12-01","2006-02-06",null,"2005-12-01"]
["IJ401_1190","Procure RF Hot Test Parts","2006-02-07","2006-04-18"]
["IJ401_1200","Fabricate RF Hot Test Parts","2006-04-19","2006-06-28"]
["IJ401_1210","Clean and Plate RF Hot Test Parts","2006-04-19","2006-06-28"]
["IJ461_0020","Develop L0A & B Mech Engrg & Design / Waveguid","2005-07-01","2005-07-30",null,"2005-07-01","2005-07-30"]
["IJ461_0025","Develop L0A & B Eng & Dsg/ Waveguide (BCR-IJ-2","2005-08-01","2005-08-15",null,"2005-08-01","2005-08-15"]
["IJ461_0030","COMP: L0A & B Mech Engr & Design / Waveguide","2005-07-31","2005-07-30",null,"2005-07-31","2005-07-30"]
["IJ461_0035","QC Structures for L0A &B","2005-07-01","2005-07-30",null,"2005-07-01","2005-07-30"]
["IJ461_0037","QC Structures for L0A &B (BCR-IJ-20)","2005-08-15","2005-08-20",null,"2005-08-15","2005-08-20"]
["IJ461_0040","Procure L0A & B Material","2005-08-01","2006-01-30",null,"2005-08-01","2006-01-30"]
["IJ461_0050","REQD: Existing L0A &B StructSections from SLAC","2005-10-16","2005-10-15",null,"2005-10-16","2005-10-15"]
["IJ461_0060","Fabricate and Modify L0A &B","2005-08-25","2006-04-03",null,"2005-08-25"]
["IJ461_0065","REQD:  L0-A Solenoid","2006-02-16","2006-02-15"]
["IJ461_0070","Integrate L0A &B onto Support Structure","2006-04-04","2006-04-03"]
["IJ461_0080","Perform L0A &B Vacuum Processing","2006-04-04","2006-04-17"]
["IJ461_0090","Perform L0A &B Waveguide Integration","2005-11-01","2006-04-28",null,"2005-11-01"]
["IJ461_0100","Prep for & Perform L0A &B RF tuning","2006-04-04","2006-04-03"]
["IJ461_0120","Conduct L0A &B RF Processing","2006-04-04","2006-04-05"]
["IJ461_0130","AVAIL: L0A &B Structure Ready for Install","2006-05-01","2006-04-28"]
["IJ461_0150","Evaluate and Condition 10' S-band Structures","2005-07-01","2005-08-31",null,"2005-07-01","2005-08-31"]
["IJ501_1010","Prep Bid Pak - GS Dipole Assembly and Suppt","2005-07-01","2005-08-15",null,"2005-07-01","2005-08-15"]
["IJ501_1020","RELEASE RFP: GS Dipole Assembly and Suppt","2006-02-01","2005-08-15",null,null,"2005-08-15"]
["IJ501_1030","Vendor Prep Proposals - GS Dipole Assm and Suppt","2005-08-16","2005-08-25",null,"2005-08-16","2005-08-25"]
["IJ501_1040","RCV: Proposals - GS Dipole Assembly and Suppt","2005-08-25","2005-08-25",null,"2005-08-25","2005-08-25"]
["IJ501_1050","Evaluate Proposals -GS Dipole Assembly and Suppt","2005-08-26","2005-08-27",null,"2005-08-26","2005-08-27"]
["IJ501_1060","AWARD: Contract for GS Dipole Assembly and Suppt","2005-08-27","2005-08-30",null,"2005-08-27","2005-08-30"]
["IJ501_1070","Vendor Fab Gun Spectrom Dipole Assy and Sppt","2005-08-30","2006-04-17",null,"2005-08-30"]
["IJ501_1075","Review Vendor Gun Spectrometer Dipole Design","2006-02-01","2006-02-22"]
["IJ501_1080","RCV: Gun Spectrometer Dipole Assembly and Suppt","2006-04-18","2006-04-18"]
["IJ501_1090","Perform QC/MM on Dipole Assm & Suppt","2006-04-19","2006-05-16"]
["IJ501_1100","AVAIL:  GS Dipole Assm and Suppt Ready for Inst","2006-05-17","2006-05-16"]
["IJ501_2010","Design DL1 B01 & B02 Dipole","2005-06-15","2005-07-30",null,"2005-06-15","2005-07-30"]
["IJ501_2020","Prep Bid Pak - DL1 Dipole Assembly and Suppt","2005-06-01","2005-07-30",null,"2005-06-01","2005-07-30"]
["IJ501_2030","RELEASE RFP: DL1 Dipole Assembly and Suppt","2005-08-15","2005-08-30",null,"2005-08-15","2005-08-30"]
["IJ501_2040","Vendor Prep Proposals - DL1 Dipole Assm and Sppt","2005-09-15","2005-09-30",null,"2005-09-15","2005-09-30"]
["IJ501_2050","RCV: Proposals - DL1 Dipole Assm and Sppt","2005-09-15","2005-09-30",null,"2005-09-15","2005-09-30"]
["IJ501_2060","Evaluate Proposals DL1 Dipole Assm and Sppt","2005-09-15","2005-09-30",null,"2005-09-15","2005-09-30"]
["IJ501_2070","AWARD: Contract for DL1 Dipole Assm and Sppt","2005-09-15","2005-09-30",null,"2005-09-15","2005-09-30"]
["IJ501_2080","Vendor Fab DL1 Dipole Assm and Sppt","2005-09-30","2006-03-30",null,"2005-09-30"]
["IJ501_2090","RCV: DL1 Dipole Assm and Sppt","2006-03-31","2006-03-31"]
["IJ501_2100","Perform QC/MM on DL1 Dipole Assm and Sppt","2006-04-03","2006-05-31"]
["IJ501_2110","AVAIL:  DL1 Dipole Assm and Sppt RFI","2006-06-01","2006-05-31"]
["IJ501_3020","Prep Bid Pak - BXS Dipole Assembly and Suppt","2005-12-01","2006-03-02",null,"2005-12-01"]
["IJ501_3030","RELEASE RFP: SAB Dipole Assembly and Suppt","2006-03-03","2006-03-06"]
["IJ501_3040","Vendor Prep Proposals - SAB Assm and Suppt","2006-03-07","2006-04-03"]
["IJ501_3050","RCV: Proposals - SAB Assembly and Suppt","2006-04-04","2006-04-03"]
["IJ501_3060","Evaluate Proposals SAB Assembly and Suppt","2006-04-04","2006-04-10"]
["IJ501_3070","AWARD: Contract for SAB Assembly and Suppt","2006-04-11","2006-04-13"]
["IJ501_3080","Vendor Fab SAB Dipole Assembly and Suppt","2006-04-14","2006-07-06"]
["IJ501_3085","Review Vendor SAB Spectrometer Dipole Design","2006-06-12","2006-06-12"]
["IJ501_3090","RCV: SAB Dipole Assembly and Suppt","2006-07-07","2006-07-07"]
["IJ501_3100","Perform QC/MM on SAB Dipole Assm & Suppt","2006-07-10","2006-07-19"]
["IJ501_3110","AVAIL:  SAB Dipole Assm and Suppt RFI","2006-07-20","2006-07-19"]
["IJ501_4020","Prep Bid Pak - Chicane Dipole Assembly and Suppt","2005-07-01","2005-10-15",null,"2005-07-01","2005-10-15"]
["IJ501_4030","RELEASE RFP: Chicane Dipole Assembly and Suppt","2006-02-01","2005-10-15",null,null,"2005-10-15"]
["IJ501_4040","Vendor Prep Proposals - Chicane Assm and Suppt","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["IJ501_4050","RCV: Proposals - Chicane Assembly and Suppt","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["IJ501_4060","Evaluate Proposals -Chicane Assembly and Suppt","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["IJ501_4070","AWARD: Contract for Chicane Assembly and Suppt","2006-02-17","2006-02-21"]
["IJ501_4080","Vendor Fab Chicane Dipole Assembly and Suppt","2006-02-22","2006-04-17"]
["IJ501_4085","Review Vendor Chicane Dipole Design","2006-04-19","2006-04-19"]
["IJ501_4090","RCV: Chicane Dipole Assembly and Suppt","2006-04-18","2006-04-18"]
["IJ501_4100","Perform QC/MM on Chicane Dipole Assm & Suppt","2006-04-19","2006-05-16"]
["IJ501_4110","AVAIL:  Chicane  Dipole Assm and Suppt RFI","2006-05-17","2006-05-16"]
["IJ502_1010","Prep Bid Pak - GS Quads Assy & Sppt","2005-09-15","2005-12-30",null,"2005-09-15","2005-12-30"]
["IJ502_1020","RELEASE RFP:  GS Quads Assy & Sppt","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ502_1030","Vendor Prep Proposals -  GS Quads Assy & Sppt","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ502_1040","RCV: Proposals -  GS Quads Assy & Sppt","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ502_1050","Eval Proposals -  GS Quads Assy & Sppt","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ502_1060","AWARD:Contract for GS Quads Assy & Sppt","2006-02-01","2006-02-07"]
["IJ502_1070","Vendor Fab  GS Quads Assy & Sppt","2006-02-08","2006-03-15"]
["IJ502_1080","RCV:   GS Quads Assy & Sppt","2005-12-01","2006-02-01",null,"2005-12-01"]
["IJ502_1090","Perform QC/MM on GS Quads Assy & Sppt","2006-02-02","2006-03-02"]
["IJ502_1100","AVAIL:  GS Quads Assy & Sppt RFI","2006-03-03","2006-03-02"]
["IJ502_2010","Design Injector Quads","2005-08-01","2005-09-30",null,"2005-08-01","2005-09-30"]
["IJ502_2020","RELEASE RFP:  Inj Quads  Assy & Sppt","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["IJ502_2030","Vendor Prep Proposals -  Inj Quads Assy & Sppt","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["IJ502_2040","RCV: Proposals -  Inj Quads Assy & Sppt","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["IJ502_2050","Eval Proposals -  Inj Quads Assy & Sppt","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["IJ502_2060","AWARD:Contract for  Inj Quads Assy & Sppt","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["IJ502_2070","Vendor Fab  Inj Quads Assy & Sppt","2005-08-01","2006-03-15",null,"2005-08-01"]
["IJ502_2075","Review Vendor Inj Quad","2005-09-15","2005-10-03",null,"2005-09-15","2005-10-03"]
["IJ502_2080","RCV:   Inj Quads Assy & Sppt","2005-12-01","2006-02-01",null,"2005-12-01"]
["IJ502_2090","Perform QC/MM on  Inj Quads Assy & Sppt","2006-02-02","2006-04-13"]
["IJ502_2100","AVAIL:   Inj Quads Assy & Sppt RFI","2006-04-14","2006-04-13"]
["IJ503_3010","COMP: Inj Corrector-A Design","2006-01-31","2006-01-30",null,"2006-01-31","2006-01-30"]
["IJ503_3020","Prep Bid Pak - Inj Corrector-A Assy & Sppt","2005-09-15","2005-12-30",null,"2005-09-15","2005-12-30"]
["IJ503_3030","RELEASE RFP: Inj Corrector-A Assy & Sppt","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ503_3040","Vendor Prep Proposals - Inj Corrector-A Assy & S","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ503_3050","RCV: Proposals -Inj Corrector-A Assy & Sppt","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ503_3060","Eval Proposals - Inj Corrector-A Assy & Sppt","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ503_3070","AWARD:Contract for Inj Corrector-A Assy & Sppt","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ503_3080","Vendor Fab Inj Corrector-A Assy & Sppt","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ503_3085","Review Vendor Inj Corr-A Design","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ503_3090","RCV: Inj Corrector-A Assy & Sppt","2005-12-01","2006-02-01",null,"2005-12-01"]
["IJ503_3100","Perform QC/MM on Inj Corrector-A Assy & Sppt","2006-02-02","2006-03-02"]
["IJ503_3110","AVAIL:  Inj Corrector-A Assy & Sppt RFI","2006-03-03","2006-03-02"]
["IJ505_4500","Prep Bid Pak - Linac Solenoid Assy & Sppt","2005-07-01","2005-10-01",null,"2005-07-01","2005-10-01"]
["IJ505_4510","RELEASE RFP: Linac Solenoid Assy & Sppt","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ505_4520","Vendor Prep Proposals -Linac Solenoid Assy&Sppt","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ505_4530","RCV: Proposals -  Linac Solenoid  Assy & Sppt","2006-02-01","2005-12-30",null,null,"2005-12-30"]
["IJ505_4540","Eval Proposals - Linac Solenoid Assy & Sppt","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ505_4550","AWARD:Contract for Linac Solenoid Assy & Sppt","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ505_4560","Vendor Fab Linac Solenoid Assy & Sppt","2005-12-01","2006-02-15",null,"2005-12-01"]
["IJ505_4570","RCV: Linac Solenoid Assy & Sppt","2005-12-01","2006-02-01",null,"2005-12-01"]
["IJ505_4580","Perform QC/MM on Linac Solenoid Assy & Sppt","2006-02-02","2006-02-15"]
["IJ505_4590","AVAIL:  Linac Solenoid Assy & Sppt RFI","2006-02-16","2006-02-15"]
["IJ601_1040","Develop Inj Vac System Prelim Desgn Review (PDR)","2005-05-02","2005-05-05",null,"2005-05-02","2005-05-05"]
["IJ601_1050","Vacuum Gauge - Test Engineering","2005-05-02","2006-01-30",null,"2005-05-02","2006-01-30"]
["IJ601_1070","Prepare Bid Packages for Inj Vacuum System","2005-05-05","2005-08-09",null,"2005-05-05","2005-08-09"]
["IJ601_1080","Evaluate Vendor Proposals","2005-07-01","2005-07-15",null,"2005-07-01","2005-07-15"]
["IJ601_1090","Develop Injector Vacuum System Final Design","2005-07-01","2006-01-30",null,"2005-07-01","2006-01-30"]
["IJ601_1100","Conduct Inj Vac System Final Design Review (FDR)","2006-02-01","2006-01-31"]
["IJ601_1110","Develop Vac Post-Processing Plan for Inj Vac Sys","2005-07-01","2005-07-15",null,"2005-07-01","2005-07-15"]
["IJ601_1120","Vacuum Post-Processing","2005-07-01","2006-01-30",null,"2005-07-01","2006-01-30"]
["IJ601_1130","AVAIL:  Injector Vacuum RFI","2006-02-01","2006-01-31"]
["IJ602_1010","Proc - Valve,VAT47132-CE44_ADM1, 24VDC, 34.8mm","2005-05-02","2005-07-19",null,"2005-05-02","2005-07-19"]
["IJ602_1020","Proc - Valve,VAT47132-CE44_ADL1, 24VDC, 22.1mm","2005-05-02","2005-07-19",null,"2005-05-02","2005-07-19"]
["IJ602_1030","Proc - ManualValve #54032_GE02","2005-05-02","2005-05-15",null,"2005-05-02","2005-05-15"]
["IJ602_1040","Proc - Pumps, Varion Ion Pumps #9191115","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["IJ602_1050","Proc - Gauges, MKS422 Cold Cathode Gauge","2005-05-02","2005-08-30",null,"2005-05-02","2005-08-30"]
["IJ602_1060","Proc - Gauges, MKS317 Enhanced Convection Pirani","2005-05-02","2005-08-30",null,"2005-05-02","2005-08-30"]
["IJ602_1070","Proc - Granville-Phillips Stabil-Ion Gauge","2005-05-02","2005-05-15",null,"2005-05-02","2005-05-15"]
["IJ602_1080","Proc - Granville-Phillips Convection Gauge","2005-05-02","2005-08-30",null,"2005-05-02","2005-08-30"]
["IJ602_1090","Proc - Misc UHV hdwe (flanges, gaskets, etc.)","2005-06-01","2005-09-30",null,"2005-06-01","2005-09-30"]
["IJ602_1100","AVAIL:  Injector Vacuum Components RFI","2005-10-01","2005-09-30",null,"2005-10-01","2005-09-30"]
["IJ602_1110","Proc - Pumps for RF Waveguids","2005-08-01","2005-08-30",null,"2005-08-01","2005-08-30"]
["IJ603_1010","Proc - GTL Pumping and Optics Chamber","2005-09-17","2006-03-31",null,"2005-09-17"]
["IJ603_1015","AVAIL:  GTL Pumping and Optics Chamber RFI","2006-01-01","2006-02-01",null,"2006-01-01"]
["IJ603_1020","Proc - L0-1TL0-2 Vacuum Components","2005-09-17","2006-03-31",null,"2005-09-17"]
["IJ603_1025","AVAIL:  L0-1TL0-2 Vacuum Components RFI","2006-01-01","2006-02-01",null,"2006-01-01"]
["IJ603_1030","Proc - DL1 Vacuum Chamber","2005-09-17","2006-03-31",null,"2005-09-17"]
["IJ603_1035","AVAIL:  DL1 Vacuum Chamber RFI","2006-04-03","2006-04-03"]
["IJ603_1040","Proc - DL1TL Vacuum Components","2005-09-17","2006-03-31",null,"2005-09-17"]
["IJ603_1045","AVAIL:  DL1TL Vacuum Components RFI","2006-01-01","2006-02-01",null,"2006-01-01"]
["IJ603_1050","Proc - SAB Vacuum Chamber and Components","2005-09-17","2006-03-31",null,"2005-09-17"]
["IJ603_1055","AVAIL:  SAB Vacuum Chamber and Components RFI","2006-04-03","2006-04-03"]
["IJ604_1010","Define GS Vacuum Support Requirements","2005-08-08","2005-09-15",null,"2005-08-08","2005-09-15"]
["IJ604_1020","Design GS Vacuum Support","2005-09-01","2006-02-28",null,"2005-09-01"]
["IJ604_1030","Define Special RF Vauum Valve Supprt Requirement","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ604_1040","Design Special RF Vacuum Valve Supports","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ604_1050","Define GTL Vacuum Supports Requirements","2005-09-01","2005-09-15",null,"2005-09-01","2005-09-15"]
["IJ604_1060","Design GTL Vacuum Supports","2005-09-15","2005-12-30",null,"2005-09-15","2005-12-30"]
["IJ604_1070","Define L0-1TL0-2 Vacuum Support Requirements","2005-09-01","2005-09-15",null,"2005-09-01","2005-09-15"]
["IJ604_1080","Design L0-1TL0-2 Vacuum Supports","2005-09-15","2005-12-30",null,"2005-09-15","2005-12-30"]
["IJ604_1090","Define LTDL1 Vacuum Support Requirements","2005-09-01","2005-09-15",null,"2005-09-01","2005-09-15"]
["IJ604_1100","Design LTDL1 Vacuum Supports","2005-09-15","2006-03-15",null,"2005-09-15"]
["IJ604_1110","Define DL1 Vacuum Supports Requirements","2005-09-01","2005-09-15",null,"2005-09-01","2005-09-15"]
["IJ604_1120","Design DL1 Vacuum Supports","2005-09-15","2005-12-30",null,"2005-09-15","2005-12-30"]
["IJ604_1130","Define DL1TL Vacuum Support Requirements","2005-09-01","2005-09-15",null,"2005-09-01","2005-09-15"]
["IJ604_1140","Design DL1TL Vacuum Supports","2005-09-15","2006-03-15",null,"2005-09-15"]
["IJ604_1150","Define SAB Vacuum Support Requirements","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ604_1160","Design SAB Vacuum Supports","2005-12-01","2006-03-15",null,"2005-12-01"]
["IJ605_1010","Proc - GS Support Material","2006-03-01","2006-04-17"]
["IJ605_1015","AVAIL:  GS Support Material","2006-04-18","2006-04-17"]
["IJ605_1020","Proc - Special Beam Pump/Spool Support Material","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ605_1025","AVAIL:  Special Beam/Spool Support Material","2005-12-31","2005-12-30",null,"2005-12-31","2005-12-30"]
["IJ605_1030","Proc - GTL Supports","2006-04-17","2006-06-12"]
["IJ605_1035","AVAIL:  GTL Supports","2006-06-13","2006-06-12"]
["IJ605_1040","Proc L0-1TL0-2 Minor Tube Support Materials","2006-04-17","2006-06-12"]
["IJ605_1045","AVAIL:  L0-1TL0-2  Minor Tube Support Materials","2006-06-13","2006-06-12"]
["IJ605_1050","Proc - DL1 Support Structure Materials","2006-03-15","2006-05-09"]
["IJ605_1055","AVAIL:  DL1 Support Struture Materials","2006-05-10","2006-05-09"]
["IJ605_1060","Proc - LTDL1 Support Structure Materials","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ605_1065","AVAIL:  LTDL1 Support Structure Materials","2005-12-31","2005-12-30",null,"2005-12-31","2005-12-30"]
["IJ605_1070","Proc - DL1TL Support Structure Materials","2006-03-16","2006-05-10"]
["IJ605_1075","AVAIL:  DL1TL Support Structure Material","2006-05-11","2006-05-10"]
["IJ605_1080","Proc - SAB Supports","2006-03-16","2006-05-10"]
["IJ605_1085","AVAIL:  SAB Supports","2006-05-11","2006-05-10"]
["IJ605_1090","Proc - Misc Support Hardware (bolts, nuts, etc.)","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ605_1095","AVAIL:  Misc Support Hardware","2005-12-31","2005-12-30",null,"2005-12-31","2005-12-30"]
["IJ701_1000","LARGE APERTURE BPM SUMMARY","2005-05-02","2006-05-19",null,"2005-05-02"]
["IJ701_1010","Define LA BPM Physics Requirements","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["IJ701_1020","Define LA Linac BPM Engineering Requirements","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["IJ701_1030","Design LA Linac BPM Core Module","2005-08-01","2005-11-30",null,"2005-08-01","2005-11-30"]
["IJ701_1040","COMP:  LA Linac BPM Core Module Design","2006-01-31","2006-01-30",null,"2006-01-31","2006-01-30"]
["IJ701_1050","Prep Bid Pack for LA Linac BPM Core Module","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["IJ701_1060","RELEASE RFP:  LA Linac BPM Core Module","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["IJ701_1070","Vendor Proposals for LA Linac BPM Core Module","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["IJ701_1080","RCV:  Proposals for LA Linac BPM Core Module","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["IJ701_1090","Evaluate Proposals for LA Linac BPM Core Module","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["IJ701_1100","AWARD:  Contract for LA Linac BPM Core Module","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["IJ701_1110","Vendor Fab LA Linac BPM Core Module","2006-02-01","2006-04-11"]
["IJ701_1115","In House Assemble LA BPM Variations","2006-04-12","2006-04-25"]
["IJ701_1120","Vacuum Process LA Linac BPM","2006-04-26","2006-05-09"]
["IJ701_1125","Design LA Linac BPM Variations","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ701_1130","Perform Lab Tests on LA Linac BPM Assembly","2006-05-10","2006-05-19"]
["IJ701_1135","LA BPM Design Check","2005-12-01","2006-01-30",null,"2005-12-01","2006-01-30"]
["IJ701_1140","AVAIL:  LA Linac BPM Assembly RFI","2006-05-22","2006-05-19"]
["IJ701_1145","Fabricate LA BPM Variations Components","2006-02-01","2006-02-15"]
["IJ701_2000","SMALL APERTURE BPM SUMMARY","2005-05-02","2006-06-01",null,"2005-05-02"]
["IJ701_2010","Define SA BPM Requirements","2005-05-02","2005-05-05",null,"2005-05-02","2005-05-05"]
["IJ701_2020","Define SA Linac BPM Requirements","2005-05-02","2005-05-05",null,"2005-05-02","2005-05-05"]
["IJ701_2030","Design SA Linac BPM","2005-05-05","2005-05-30",null,"2005-05-05","2005-05-30"]
["IJ701_2040","COMP:  SA Linac BPM Design","2005-07-01","2005-06-30",null,"2005-07-01","2005-06-30"]
["IJ701_2050","Prep Bid Pack for SA Linac BPM","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["IJ701_2060","RELEASE RFP:  SA Linac BPM","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["IJ701_2070","Vendor Prep Proposals for SA Linac BPM","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["IJ701_2080","RCV:  Proposals for SA Linac BPM","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["IJ701_2090","Evaluate Proposals for SA Linac BPM","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["IJ701_2100","AWARD:  Contract for SA Linac BPM","2005-07-01","2005-07-15",null,"2005-07-01","2005-07-15"]
["IJ701_2110","Vendor Fab SA Linac BPM","2005-09-01","2005-12-30",null,"2005-09-01","2005-12-30"]
["IJ701_2112","RCV:  Vendor Fab SA Linac BPMs","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ701_2115","In House Assemble SA Linac BPM","2005-07-15","2005-12-30",null,"2005-07-15","2005-12-30"]
["IJ701_2120","Vacuum Process SA Linac BPM","2005-12-01","2006-06-01",null,"2005-12-01"]
["IJ701_2130","Perform Lab Tests on SA Linac BPM Assembly","2005-12-01","2006-03-30",null,"2005-12-01"]
["IJ701_2140","AVAIL:  SA Linac BPM Assembly RFI","2006-03-31","2006-03-30"]
["IJ702_1000","CURRENT MONITOR SUMMARY","2005-05-02","2006-06-21",null,"2005-05-02"]
["IJ702_1010","Define Current Monitor Physics Specifications","2005-06-01","2005-11-30",null,"2005-06-01","2005-11-30"]
["IJ702_1020","Design Current Monitor","2005-05-02","2005-11-30",null,"2005-05-02","2005-11-30"]
["IJ702_1030","COMP:  Current Monitor Design","2005-12-01","2005-11-30",null,"2005-12-01","2005-11-30"]
["IJ702_1040","Prep Bid Pack for Current Monitor","2005-11-21","2005-11-30",null,"2005-11-21","2005-11-30"]
["IJ702_1050","RELEASE RFP:  Current Monitor","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["IJ702_1060","Vendor Prep Proposals for Current Monitor","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["IJ702_1070","RCV:  Proposals for Current Monitor","2006-01-01","2006-02-01",null,"2006-01-01"]
["IJ702_1080","Evaluate Proposals for Current Monitor","2006-01-01","2006-02-14",null,"2006-01-01"]
["IJ702_1090","AWARD:  Contract for Current Monitor","2006-02-15","2006-02-15"]
["IJ702_1100","Vendor Fab Current Monitor","2006-02-16","2006-05-15"]
["IJ702_1110","RCV:  Fab Current Monitor","2006-05-16","2006-05-16"]
["IJ702_1120","Vacuum Process Current Monitor","2006-05-17","2006-05-31"]
["IJ702_1130","Perform Lab Tests on Current Monitor","2006-06-01","2006-06-21"]
["IJ702_1140","AVAIL:  Current Monitor RFI","2006-06-22","2006-06-21"]
["IJ704_1000","PROFILE MONITORS SUMMARY","2005-05-02","2006-08-21",null,"2005-05-02"]
["IJ704_1010","Define Profile Monitor Physics Requirements","2005-11-01","2005-12-30",null,"2005-11-01","2005-12-30"]
["IJ704_1020","Define Profile Monitor Engineering Requirements","2005-05-02","2006-01-30",null,"2005-05-02","2006-01-30"]
["IJ704_1030","Design Profile Monitors","2005-10-03","2006-05-01",null,"2005-10-03"]
["IJ704_1040","COMP:  Profile Monitors Design","2006-02-01","2006-01-31"]
["IJ704_1050","Prep Bid Pack for Profile Monitor","2006-01-01","2006-01-31",null,"2006-01-01"]
["IJ704_1060","RELEASE RFP:  Profile Monitor","2006-02-01","2006-02-01"]
["IJ704_1070","Vendor Prep Proposals for Profile Monitor","2006-02-01","2006-01-31"]
["IJ704_1080","RCV:  Proposals for Profile Monitor","2006-02-01","2006-02-01"]
["IJ704_1090","Evaluate Proposals for Profile Monitor","2006-02-01","2006-01-31"]
["IJ704_1100","AWARD:  Contract for Profile Monitor","2006-02-01","2006-02-01"]
["IJ704_1110","Vendor Fab Profile Monitors","2006-02-01","2006-08-01"]
["IJ704_1112","RCV:  Vendor Fab Profile Monitors","2006-08-02","2006-08-02"]
["IJ704_1115","Profile Monitors In House Assembly","2006-02-01","2006-08-15"]
["IJ704_1120","Perform Lab Test On Profile Monitors","2006-02-01","2006-08-21"]
["IJ704_1130","AVAIL:  Profile Monitor RFI - Remaining Lot","2006-08-22","2006-08-21"]
["IJ704_1140","Design OTR Profile Monitor Core Module","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["IJ704_1145","Design YAG/FaradayCup/LsrAlgnmt Prof Monitor","2006-01-01","2006-03-01",null,"2006-01-01"]
["IJ704_1150","Dsn Gun Spectrm YAG/Cerenkov/Faraday Cup ProfMon","2006-01-01","2006-03-01",null,"2006-01-01"]
["IJ704_1155","Design YAG Profile Monitors Optics","2006-01-01","2006-05-15",null,"2006-01-01"]
["IJ704_1160","Design Gun Laser On-Axis Mirror Assy","2005-12-01","2006-03-29",null,"2005-12-01"]
["IJ704_1165","Design Cerenkov Profile Monitor","2005-12-01","2006-03-15",null,"2005-12-01"]
["IJ704_1170","Design Laser Heater OTR Profile Monitor","2006-02-01","2006-04-28"]
["IJ704_1175","Design OTR Profile Monitor Optics","2005-12-01","2006-03-15",null,"2005-12-01"]
["IJ704_1180","COMP:  Profile Monitors Design","2006-06-02","2006-06-01"]
["IJ704_1185","Profile Monitors Design Check","2005-12-01","2006-06-01",null,"2005-12-01"]
["IJ704_1200","COMP:  Profile Monitor Design (OTR 1-3)","2006-02-01","2006-01-31"]
["IJ704_1210","Prep Bid Pack for Profile Monitor  (OTR 1-3)","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["IJ704_1220","RELEASE RFP:  Profile Monitor  (OTR 1-3)","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["IJ704_1230","Vendor Prep Proposals for Profile Monitor  (OTR","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["IJ704_1240","RCV:  Proposals for Profile Monitor  (OTR 1-3)","2005-07-01","2005-06-30",null,"2005-07-01","2005-06-30"]
["IJ704_1250","Evaluate Proposals for Profile Monitor  (OTR 1-3","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["IJ704_1260","AWARD:  Contract for Profile Monitor  (OTR 1-3)","2005-07-01","2005-08-01",null,"2005-07-01","2005-08-01"]
["IJ704_1270","Vendor Fab Profile Monitor (OTR 1-3)","2005-08-01","2006-05-01",null,"2005-08-01"]
["IJ704_1275","RCV:  Vendor Fab Profile Monitor (OTR 1-3)","2006-01-01","2006-05-01",null,"2006-01-01"]
["IJ704_1280","In House Assembly  (OTR 1-3)","2006-05-02","2006-06-13"]
["IJ704_1290","Perform Lab Test On Profile Monitors  (OTR 1-3)","2006-01-01","2006-06-30",null,"2006-01-01"]
["IJ704_1300","AVAIL:  Profile Monitors (OTR 1-3) RFI","2006-07-03","2006-06-30"]
["IJ705_1000","INJECTOR WIRE SCANNERS SUMMARY","2005-11-01","2006-04-14",null,"2005-11-01"]
["IJ705_1005","AVAIL:  Injector Wire Scanners RFI","2005-11-01","2006-04-14",null,"2005-11-01"]
["IJ705_1010","Procure Injector Wire Scanners","2006-01-01","2006-04-14",null,"2006-01-01"]
["IJ707_1000","PPS STOPPER SUMMARY","2005-05-02","2005-10-07",null,"2005-05-02","2005-10-07"]
["IJ707_1010","Define PPS Stopper Physics Specifications","2005-05-02","2005-06-30",null,"2005-05-02","2005-06-30"]
["IJ707_1020","Define PPS Stopper Engineering Specs","2005-05-02","2005-07-15",null,"2005-05-02","2005-07-15"]
["IJ707_1030","Design PPS Stopper","2005-05-02","2005-06-30",null,"2005-05-02","2005-06-30"]
["IJ707_1040","COMP:  PPS Stopper Design","2005-07-01","2005-06-30",null,"2005-07-01","2005-06-30"]
["IJ707_1050","Prep Bid Pack for PPS Stopper","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["IJ707_1060","RELEASE RFP:  PPS Stopper","2006-02-01","2005-07-01",null,null,"2005-07-01"]
["IJ707_1070","Vendor Prep Proposals for PPS Stopper","2005-07-05","2005-07-11",null,"2005-07-05","2005-07-11"]
["IJ707_1080","RCV:  Proposals for PPS Stopper","2005-07-15","2005-07-16",null,"2005-07-15","2005-07-16"]
["IJ707_1090","Evaluate Proposals for PPS Stopper","2005-07-13","2005-07-26",null,"2005-07-13","2005-07-26"]
["IJ707_1100","AWARD:  Contract for PPS Stopper","2005-07-27","2005-07-27",null,"2005-07-27","2005-07-27"]
["IJ707_1110","Vendor Fab PPS Stopper","2005-07-28","2005-09-30",null,"2005-07-28","2005-09-30"]
["IJ707_1120","In House Fab PPS Stopper","2005-07-28","2005-09-30",null,"2005-07-28","2005-09-30"]
["IJ707_1130","Assemble PPS Stopper","2005-08-15","2005-09-30",null,"2005-08-15","2005-09-30"]
["IJ707_1140","Vacuum Process PPS Stopper","2005-09-20","2005-10-07",null,"2005-09-20","2005-10-07"]
["IJ707_1150","AVAIL:  PPS Stopper RFI","2005-10-08","2005-10-07",null,"2005-10-08","2005-10-07"]
["IJMS_03","FY 05 Funding Constraint Q2 May","2005-11-01","2005-10-31",null,"2005-11-01","2005-10-31"]
["IJOPS_0000","Injector System Pre-Operations","2007-07-23","2009-03-31"]
["IJ_LOE","Injector LOE Complete","2006-02-01","2006-01-31"]
["IJ_OPCSPR","Injector OPC Spares Complete","2007-08-31","2007-08-30"]
["LN01010100","L01 SYSTEM SUMMARY","2005-05-02","2007-07-31",null,"2005-05-02"]
["LN01010108","Write System ICD - L01","2005-05-02","2005-05-12",null,"2005-05-02","2005-05-12"]
["LN01010118","Write Installation Plan - L01","2005-05-02","2005-05-31",null,"2005-05-02","2005-05-31"]
["LN01010124","Prepare for PDR - L01","2005-05-02","2005-05-13",null,"2005-05-02","2005-05-13"]
["LN01010126","Conduct L01 System PDR","2005-05-16","2005-05-16",null,"2005-05-16","2005-05-16"]
["LN01010128","Generate Detailed Procurement Plan","2005-05-02","2005-05-31",null,"2005-05-02","2005-05-31"]
["LN01010130","Create RF Cold Test Plan","2005-05-02","2005-05-31",null,"2005-05-02","2005-05-31"]
["LN01010132","Establish Subordinate Work Orders","2005-05-02","2005-05-31",null,"2005-05-02","2005-05-31"]
["LN01010134","Prepare for FDR - L01","2005-09-15","2005-09-21",null,"2005-09-15","2005-09-21"]
["LN01010136","Conduct L01 System FDR","2005-09-15","2005-09-21",null,"2005-09-15","2005-09-21"]
["LN01010138","COMP: L01 System Design","2005-09-22","2005-09-21",null,"2005-09-22","2005-09-21"]
["LN01010139","Document System Assembly Model - L01","2005-09-15","2005-10-31",null,"2005-09-15","2005-10-31"]
["LN01010140","L01 System PED Support to Components","2005-05-02","2005-07-30",null,"2005-05-02","2005-07-30"]
["LN01010142","L01 System CONST Support to Components","2005-10-03","2005-12-30",null,"2005-10-03","2005-12-30"]
["LN01010200","BC1 SYSTEM SUMMARY","2005-05-02","2009-03-31",null,"2005-05-02"]
["LN01010208","Write System ICD - BC1","2005-05-02","2005-05-31",null,"2005-05-02","2005-05-31"]
["LN01010218","Write Installation Plan - BC1","2005-06-01","2005-12-30",null,"2005-06-01","2005-12-30"]
["LN01010228","Generate Detailed Procurement Plan","2005-05-02","2005-05-31",null,"2005-05-02","2005-05-31"]
["LN01010232","Establish Subordinate Work Orders","2005-05-02","2005-05-31",null,"2005-05-02","2005-05-31"]
["LN01010234","Prepare for FDR - BC1","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["LN01010236","Conduct BC1 System FDR","2005-07-01","2005-07-05",null,"2005-07-01","2005-07-05"]
["LN01010238","COMP: BC1 System Design","2005-07-06","2005-07-05",null,"2005-07-06","2005-07-05"]
["LN01010239","Document System Assembly Model - BC1","2005-11-01","2005-12-30",null,"2005-11-01","2005-12-30"]
["LN01010240","BC1 System PED Support to Components","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["LN01010242","BC1 System CONST Support to Components","2005-10-03","2009-03-31",null,"2005-10-03"]
["LN01010300","L02 SYSTEM SUMMARY","2005-05-02","2008-06-30",null,"2005-05-02"]
["LN01010308","Write System ICD - L02","2005-05-02","2005-05-31",null,"2005-05-02","2005-05-31"]
["LN01010318","Write Installation Plan - L02","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010322","Make Linac Vacuum Schematic","2005-05-02","2005-05-31",null,"2005-05-02","2005-05-31"]
["LN01010324","Prepare for PDR - L02","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010326","Conduct L02 System PDR","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010328","Generate Detailed Procurement Plan","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010330","Create Cold Test Plan","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010332","Establish Subordinate Work Orders","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010334","Prepare for FDR - L02","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010336","Conduct L02 System FDR","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010338","COMP: L02 System Design","2005-12-31","2005-12-30",null,"2005-12-31","2005-12-30"]
["LN01010339","Document System Assembly Model - L02","2005-11-01","2005-12-30",null,"2005-11-01","2005-12-30"]
["LN01010340","L02 System PED Support to Components","2005-09-01","2005-12-30",null,"2005-09-01","2005-12-30"]
["LN01010342","L02 System CONST Support to Components","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010400","BC2 SYSTEM SUMMARY","2005-05-02","2008-06-30",null,"2005-05-02"]
["LN01010408","Write System ICD - BC2","2005-05-02","2005-05-31",null,"2005-05-02","2005-05-31"]
["LN01010418","Write Installation Plan - BC2","2005-10-03","2005-12-30",null,"2005-10-03","2005-12-30"]
["LN01010422","Make Linac Vacuum Schematic","2005-05-02","2005-05-31",null,"2005-05-02","2005-05-31"]
["LN01010424","Prepare for PDR - BC2","2005-11-01","2005-12-30",null,"2005-11-01","2005-12-30"]
["LN01010426","Conduct BC2 System PDR","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010428","Generate Detailed Procurement Plan","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010430","Create Cold Test Plan","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010432","Establish Subordinate Work Orders","2005-11-01","2005-11-30",null,"2005-11-01","2005-11-30"]
["LN01010434","Prepare for FDR - BC2","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010436","Conduct BC2 System FDR","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010438","COMP: BC2 System Design","2005-12-31","2005-12-30",null,"2005-12-31","2005-12-30"]
["LN01010439","Document System Assembly Model - BC2","2005-10-03","2005-12-30",null,"2005-10-03","2005-12-30"]
["LN01010440","BC2 System PED Support to Components","2005-09-20","2005-11-30",null,"2005-09-20","2005-11-30"]
["LN01010442","BC2 System CONST Support to Components","2006-02-01","2005-12-30",null,null,"2005-12-30"]
["LN01010500","L03 SYSTEM SUMMARY","2005-07-01","2008-06-30",null,"2005-07-01"]
["LN01010508","Write System ICD - L03","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["LN01010517","AVAIL: System Reqmts for L03 Component Designs","2005-07-01","2005-06-30",null,"2005-07-01","2005-06-30"]
["LN01010518","Write Installation Plan - L03","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010522","Make Linac Vacuum Schematic","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010524","Prepare for PDR - L03","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010526","Conduct L03 System PDR","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010528","Generate Detailed Procurement Plan","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010530","Create Cold Test Plan","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010532","Establish Subordinate Work Orders","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010534","Prepare for FDR - L03","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010536","Conduct L03 System FDR","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010538","COMP: L03 System Design","2005-12-31","2005-12-30",null,"2005-12-31","2005-12-30"]
["LN01010539","Document System Assembly Model - L03","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010540","L03 System PED Support to Components","2005-09-15","2005-11-30",null,"2005-09-15","2005-11-30"]
["LN01010542","L03 System CONST Support to Components","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010600","LTU SYSTEM SUMMARY","2005-05-02","2008-09-30",null,"2005-05-02"]
["LN01010608","Write System ICD - L03","2005-05-02","2005-05-31",null,"2005-05-02","2005-05-31"]
["LN01010612","Generate Removal Document List - FFTB to LTU","2005-05-02","2005-06-30",null,"2005-05-02","2005-06-30"]
["LN01010617","AVAIL: System Reqmts for LTU Component Designs","2005-07-01","2005-06-30",null,"2005-07-01","2005-06-30"]
["LN01010618","Write Installation Plan - LTU","2005-10-03","2005-12-30",null,"2005-10-03","2005-12-30"]
["LN01010624","Prepare for PDR - LTU","2005-10-03","2005-12-30",null,"2005-10-03","2005-12-30"]
["LN01010626","Conduct LTU System PDR","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010628","Generate Detailed Procurement Plan","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010630","Create Test Plan","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010632","Establish Subordinate Work Orders","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010634","Prepare for FDR - LTU","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010636","Conduct LTU System FDR","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010638","COMP: LTU System Design","2005-12-31","2005-12-30",null,"2005-12-31","2005-12-30"]
["LN01010640","LTU System PED Support to Components","2005-07-01","2005-09-30",null,"2005-07-01","2005-09-30"]
["LN01010642","LTU System CONST Support to Components","2005-10-03","2005-12-30",null,"2005-10-03","2005-12-30"]
["LN01010700","E-DUMP SYSTEM SUMMARY","2005-07-01","2008-09-30",null,"2005-07-01"]
["LN01010708","Write System ICD - E-Dump","2005-07-01","2005-07-08",null,"2005-07-01","2005-07-08"]
["LN01010717","AVAIL: System Reqmts for E Dmp Component Designs","2005-07-09","2005-07-08",null,"2005-07-09","2005-07-08"]
["LN01010718","Write Installation Plan - E-Dump","2005-10-03","2005-12-30",null,"2005-10-03","2005-12-30"]
["LN01010724","Prepare for PDR - E-Dump","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010726","Conduct E-Dump System PDR","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010728","Generate Detailed Procurement Plan","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010730","Create Test Plan","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010732","Establish Subordinate Work Orders","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010734","Prepare for FDR - E-Dump","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010736","Conduct E-Dump System FDR","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01010738","COMP: E-Dump System Design","2005-12-31","2005-12-30",null,"2005-12-31","2005-12-30"]
["LN01010740","E-Dump System PED Support to Components","2005-07-01","2005-09-30",null,"2005-07-01","2005-09-30"]
["LN01010742","E-Dump System CONST Support to Components","2005-10-03","2005-12-30",null,"2005-10-03","2005-12-30"]
["LN0101_616","Define/Develop LTU System Assembly Model - FY05","2005-05-02","2005-06-30",null,"2005-05-02","2005-06-30"]
["LN0101_716","Define/Develop E-Dump System Assy Model - FY05","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["LN0103A01","Travel - PED","2005-06-01","2005-06-30",null,"2005-06-01","2005-06-30"]
["LN0103A02","Travel - PED","2005-07-01","2006-03-30",null,"2005-07-01"]
["LN0103A03","Travel - PED","2006-03-31","2006-05-26"]
["LN0103A04","Travel - PED","2005-07-01","2006-03-30",null,"2005-07-01"]
["LN0103A05","Travel - PED","2006-03-31","2006-05-26"]
["LN0103A06","Travel - PED","2006-05-30","2006-07-26"]
["LN0103A07","Travel - CONST","2006-07-27","2006-09-22"]
["LN0103A08","Travel - CONST","2006-09-25","2006-11-20"]
["LN0103A09","Travel - CONST","2006-11-21","2007-02-05"]
["LN0103B01","Travel - CONST","2007-02-06","2007-04-04"]
["LN0103B02","Travel - CONST","2007-04-05","2007-06-01"]
["LN0103B03","Travel - CONST","2007-06-04","2007-07-31"]
["LN0103B04","Travel - CONST","2007-08-01","2007-09-27"]
["LN0103B05","Travel - CONST","2007-09-28","2007-11-27"]
["LN0103B06","Travel - CONST","2007-11-28","2008-02-11"]
["LN0103B07","Travel - CONST","2006-10-03","2006-11-30"]
["LN0103B08","Travel - CONST","2006-12-01","2007-02-13"]
["LN0103B09","Travel - CONST","2007-02-14","2007-04-12"]
["LN0103B10","Travel - CONST","2007-04-13","2007-06-11"]
["LN0103B11","Travel - CONST","2007-06-12","2007-08-08"]
["LN0103B12","Travel - CONST","2007-11-28","2008-02-11"]
["LN0103B13","Travel - CONST","2008-02-12","2008-04-09"]
["LN0103B14","Travel - CONST","2008-04-10","2008-06-06"]
["LN0103B15","Travel - CONST","2008-06-09","2008-08-05"]
["LN0103B16","Travel - CONST","2008-08-06","2008-10-02"]
["LN0103B17","Travel - CONST","2008-10-03","2008-12-02"]
["LN0103B18","Travel - CONST","2008-12-03","2009-02-10"]
["LN010400","Linac System Management Effort - PED","2005-06-01","2005-12-30",null,"2005-06-01","2005-12-30"]
["LN01040035","LINAC COMPONENT DATA BASE SUMMARY","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01040070","LINAC ADMINISTRATIVE SUMMARY","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN01040085","Linac Procurement Management","2005-06-01","2005-12-30",null,"2005-06-01","2005-12-30"]
["LN01040090","Linac Testing & Post-Process Management","2005-06-01","2005-12-30",null,"2005-06-01","2005-12-30"]
["LN01040095","Linac Stage & Storage Management","2005-06-01","2005-12-30",null,"2005-06-01","2005-12-30"]
["LN01040100","Linac Physics Requirements","2005-10-03","2005-10-31",null,"2005-10-03","2005-10-31"]
["LN01040105","Receive and Review Linac Optics Requirements","2005-10-03","2005-10-31",null,"2005-10-03","2005-10-31"]
["LN01040110","Verify Diagnostic Requirements","2005-10-03","2005-10-31",null,"2005-10-03","2005-10-31"]
["LN01040115","Back Check Component Spec vs Optics Requirements","2005-10-03","2005-10-31",null,"2005-10-03","2005-10-31"]
["LN010402","Linac System Management Effort - CONST","2005-10-03","2005-12-30",null,"2005-10-03","2005-12-30"]
["LN02","LINAC CNTRLS & PWR CONV SUBSYSTEM SUMMARY","2005-06-15","2008-07-03",null,"2005-06-15"]
["LN0201","PERSONNEL PROTECTION SUBSYSTEM SUMARY","2006-02-01","2007-11-21"]
["LN02010040","Construction Funds Available - Begin Procurement","2006-02-01","2006-01-31"]
["LN02010041","Start PPS BSOIC Mounting H/W Procurement","2006-09-06","2006-09-05"]
["LN02010045","Procure PPS BSOIC Mounting Hardware/Material","2006-09-06","2006-09-19"]
["LN02010050","RCV: PPS BSOIC Mounting Hardware/Material","2006-09-20","2006-09-19"]
["LN02010055","Prep Bid Pak - BSOIC Rad Monitor ADM-600 Series","2006-09-06","2006-09-19"]
["LN02010060","RELEASE: RFP - BSOIC Rad Monitor ADM-600 Series","2006-09-20","2006-09-19"]
["LN02010065","Vendors Prep Proposals - BSOIC Rad Monitor ADM-6","2006-09-20","2006-10-10"]
["LN02010070","RCV: Proposals - BSOIC Rad Monitor ADM-600 Serie","2006-10-11","2006-10-10"]
["LN02010075","Evaluate Proposals - BSOIC Rad Monitor ADM-600 S","2006-10-11","2006-10-24"]
["LN02010080","AWARD: Contract - BSOIC Rad Monitor ADM-600 Seri","2006-10-25","2006-10-25"]
["LN02010085","Vendor Fab/Assy - BSOIC Rad Monitor ADM-600 Seri","2006-10-26","2007-07-27"]
["LN02010090","Fab/Assy - BSOIC Mounting Hardware (15)","2006-10-02","2007-09-26"]
["LN02010095","RCV: PPS BSOIC Rad Monitor ADM-600 Series (20) f","2007-07-30","2007-07-27"]
["LN02010100","Fab and Pre Assemble Components (as required)","2007-09-27","2007-10-24"]
["LN02010105","COMP: Linac PPS Component Fab & Assembly","2007-10-25","2007-10-24"]
["LN02010110","Perform PPS BSOIC Pre-Installation Qual Test","2007-10-25","2007-11-21"]
["LN02010115","AVAIL: Linac PPS BSOIC Equipment Ready for Instl","2007-11-26","2007-11-21"]
["LN02010230","Start PPS Maze/Gate H/W Procurement","2006-07-24","2006-07-21"]
["LN02010240","RCV: PPS Hardware/Material","2006-09-06","2006-09-05"]
["LN02010241","Start PLC Access Cntrl Sys Elect Procurement","2006-09-06","2006-09-05"]
["LN02010245","Prep Bid Pak - PLC Access Cntrl Sys Electronics","2006-09-06","2006-09-12"]
["LN02010250","RELEASE: RFP - PLC Access Cntrl Sys Electronics","2006-09-13","2006-09-12"]
["LN02010255","Vendors Prep Proposals - PLC Access Cntrl Sys El","2006-09-13","2006-10-10"]
["LN02010260","RCV: Proposals - PLC Access Cntrl Sys Electronic","2006-10-11","2006-10-10"]
["LN02010265","Evaluate Proposals - PLC Access Cntrl Sys Electr","2006-10-11","2006-10-17"]
["LN02010270","AWARD: Contract - PLC Access Cntrl Sys Electroni","2006-10-18","2006-10-18"]
["LN02010272","Vendor Fab/Assy - PLC Access Cntrl Sys Electroni","2006-10-19","2007-06-21"]
["LN02010274","RCV: from Vendor - PPS PLC Access Cntrl Sys Elec","2007-06-22","2007-06-21"]
["LN02010281","Fab, Pre Assemble and Qual Test PPS Component","2007-06-22","2007-08-17"]
["LN02010282","AVAIL: Linac PPS Equipment Ready for Integ","2007-08-20","2007-08-17"]
["LN02010335","Procure PPS Maze/Gate Hdwr/Matl/Switch/Latch/Sol","2006-07-24","2006-08-18"]
["LN02010340","Fab/PreAssy PPS Maze/Gate Hdwr/Matl/Switch/Latch","2006-08-21","2006-11-13"]
["LN02010345","Procure Cable PPS Maze/Gate Cableplant","2006-10-03","2007-01-11"]
["LN02010350","RCV: PPS Maze/Gate Hdwr/Matl/Switches/Latches/So","2007-01-12","2007-01-11"]
["LN02010355","Prep Bid Pak - Mazes/Gates Access Control Gates","2006-09-06","2006-09-26"]
["LN02010360","RELEASE: RFP - Mazes/Gates Access Control Gates","2006-09-27","2006-09-26"]
["LN02010365","Vendors Prep Proposals - Mazes/Gates Access Cntr","2006-09-27","2006-10-24"]
["LN02010370","RCV: Proposals - Mazes/Gates Access Control Gate","2006-10-25","2006-10-24"]
["LN02010375","Evaluate Proposals - Mazes/Gates Access Control","2006-10-25","2006-11-07"]
["LN02010380","AWARD: Mazes/Gates Access Control Gates (3 sets","2006-11-08","2006-11-08"]
["LN02010382","Vendor Fab/Assy - Mazes/Gates Access Cntrl Gates","2006-11-09","2007-06-14"]
["LN02010384","RCV: PPS Mazes/Gates Access Control Set 3 from V","2007-06-15","2007-06-14"]
["LN02010386","AVAIL: PPS Mazes/Gates Access Control Gates","2007-06-15","2007-06-14"]
["LN02010388","Write Software & Documentation to Integrate PPS","2006-09-06","2006-10-31"]
["LN02010394","Integrate and Test PPS","2007-06-15","2007-06-28"]
["LN02010398","AVAIL: PPS Controls ready to Integrate","2007-06-29","2007-06-28"]
["LN0202","BEAM CONTAINMENT SUBSYSTEM SUMMARY","2006-02-01","2006-11-30"]
["LN02020025","Construction Funds Available - Begin Procurement","2006-02-01","2006-01-31"]
["LN02020029","Start BCS LTU & Halls Procurement","2006-02-01","2006-01-31"]
["LN02020030","Procure BCS PLIC/LION System HV Power Supply Cha","2006-10-03","2006-10-23"]
["LN02020035","Procure Gas System - BCS PLIC/LION Regulators/Fi","2006-10-03","2006-10-23"]
["LN02020040","Procure BCS  PLIC/LION Gas Bottle(s) & Bottle(s","2006-10-03","2006-10-31"]
["LN02020045","Procure BCS  PLIC/LION Cableplant Heliax, Andre","2006-10-03","2006-10-31"]
["LN02020050","RCV: from Vendor - BCS PLIC/LION  HV Supply","2006-11-01","2006-10-31"]
["LN02020055","RCV: from Vendor - BCS PLIC/LION Cableplant","2006-11-01","2006-10-31"]
["LN02020060","Prep Bid Pak - BCS PLIC/LION Cableplant","2006-10-03","2006-10-09"]
["LN02020065","RELEASE: RFP - BCS PLIC/LION Cableplant","2006-10-10","2006-10-09"]
["LN02020070","Vendors Prep Proposals - BCS PLIC/LION Cableplan","2006-10-10","2006-10-16"]
["LN02020075","RCV: Proposals - BCS PLIC/LION Cableplant","2006-10-17","2006-10-16"]
["LN02020080","Evaluate Proposals - BCS PLIC/LION Cableplant","2006-10-17","2006-10-23"]
["LN02020085","AWARD: Contract - BCS PLIC/LION Cableplant","2006-10-24","2006-10-24"]
["LN02020090","AVAIL: HV Power Supply ready to integrate","2006-10-25","2006-10-24"]
["LN02020095","COMP: BCS  LTU & Halls Component Fab & Assembly","2006-11-01","2006-10-31"]
["LN02020100","Perform Pre-Installation Qual Test on BCS LTU","2006-11-01","2006-11-30"]
["LN02020105","AVAIL: Linac BCS Cableplant ready for Instl","2006-12-01","2006-11-30"]
["LN02020110","Write Software Documentation","2006-03-01","2006-04-11"]
["LN02020125","Integrate and Test BCS","2006-04-12","2006-04-25"]
["LN02020135","AVAIL: Linac BCS Controls Ready to Integrate","2006-04-26","2006-04-25"]
["LN0203","MACHINE PROTECTION SUBSYSTEM SUMMARY","2006-02-01","2006-11-29"]
["LN02030040","Construction Funds Available - Begin Procurement","2006-02-01","2006-01-31"]
["LN02030049","Start MPS Procurement & Fabrication","2006-02-01","2006-01-31"]
["LN02030050","Acqquire MPS Hardware","2006-02-01","2006-02-01"]
["LN02030051","Prep Bid Pak - PIC Modules","2006-02-01","2006-02-22"]
["LN02030055","Prep Assy Pak - TC Reference Planes Modules","2006-02-23","2006-03-15"]
["LN02030060","RELEASE: RFP - PIC's","2006-03-16","2006-03-15"]
["LN02030065","Vendors Prep Proposals - PIC's","2006-03-16","2006-04-12"]
["LN02030070","RCV: Proposals - PIC Modules","2006-04-13","2006-04-12"]
["LN02030075","Evaluate Proposals - PIC Modules","2006-04-13","2006-04-26"]
["LN02030080","AWARD: Contract - PIC Modules","2006-04-27","2006-04-27"]
["LN02030085","Vendor Fab/Assy - PIC Modules","2006-04-28","2006-08-21"]
["LN02030090","RCV: from Vendor - MPS PIC Modules","2006-08-22","2006-08-21"]
["LN02030095","Procure TC Reference Plane material (as required","2006-02-01","2006-03-01"]
["LN02030100","Fab and Pre Assemble TC Ref. Planes (as required","2006-03-02","2006-03-29"]
["LN02030105","Procure Cable TC Reference Plane material","2006-02-01","2006-03-01"]
["LN02030110","Fab Cable, Coax, PIC Module to PIC Detector (6)","2006-03-02","2006-03-29"]
["LN02030115","Fab Cable, Coax, HV P.S. to PIC Detector (6)","2006-03-02","2006-03-29"]
["LN02030120","Fab Cable,1553, PIC Module Chain to VME A.P. Cra","2006-03-02","2006-03-29"]
["LN02030125","Fab Cable,8/C, HV P.S. to X-connects (P.S. Statu","2006-03-02","2006-03-29"]
["LN02030130","Fab Cable,4/C, HV P.S. to X-connects (HV Enable)","2006-03-02","2006-03-29"]
["LN02030135","Fab and Pre Assemble PIC Components (as reqd)","2006-03-30","2006-04-26"]
["LN02030140","COMP: Linac MPS Component Fab & Assembly","2006-04-27","2006-04-26"]
["LN02030145","Perform Pre-Installation Qual Test on Linac MPS","2006-08-22","2006-09-19"]
["LN02030150","AVAIL: Linac MPS Equipment ready for Install","2006-09-20","2006-09-19"]
["LN02030225","Prep Bid Pak - BSOIC","2006-02-01","2006-02-22"]
["LN02030230","RELEASE: RFP - BSOIC","2006-02-23","2006-02-22"]
["LN02030235","Vendors Prep Proposals - BSOIC","2006-02-23","2006-03-22"]
["LN02030240","RCV: Proposals - BSOIC","2006-03-23","2006-03-22"]
["LN02030245","Evaluate Proposals - BSOIC","2006-03-23","2006-04-05"]
["LN02030250","AWARD: Contract - BSOIC","2006-04-06","2006-04-06"]
["LN02030255","Vendor Fab/Assy - BSOIC","2006-04-07","2006-08-28"]
["LN02030260","RCV: from Vendor - MPS BSOIC","2006-08-29","2006-08-28"]
["LN02030280","Fab and Pre Assemble Components (as required)","2006-08-29","2006-08-28"]
["LN02030285","COMP: Linac MPS Component Fab & Assembly","2006-08-29","2006-08-28"]
["LN02030290","Perform Pre-Installation Qual Test on Linac MPS","2006-08-29","2006-08-28"]
["LN02030295","AVAIL: Linac MPS Equipment ready for Install","2006-08-29","2006-08-28"]
["LN02030300","Write Software and Doc. to Integrate MPS","2006-09-05","2006-10-30"]
["LN02030315","Integrate and Test MPS Hardware and Software","2006-10-31","2006-11-29"]
["LN02030320","AVAIL: Linac MPS Controls Ready to Integrate","2006-11-30","2006-11-29"]
["LN020401","BX11-14 SUMMARY","2008-02-12","2008-07-03"]
["LN02040104","Procure 20kw Pwr Supply (BX11-14) - Hardware","2008-02-12","2008-07-02"]
["LN02040133","AVAIL: 20kw Pwr Supply (BX11-14) - Ready for Ins","2008-07-03","2008-07-03"]
["LN020402","2kw POWER SUPPLY (SEC-23) SUMMARY","2006-10-03","2007-03-12"]
["LN02040204","Procure 2kw Pwr Supply  - (Sec 23)","2006-10-03","2007-03-12"]
["LN02040233","AVAIL: 2kw Pwr Supply (SEC-23) Ready for Integ","2007-03-13","2007-03-12"]
["LN020403","2kw POWER SUPPLY (SEC-24) SUMMARY","2006-10-03","2007-03-12"]
["LN02040304","Procure 2kw Pwr Supply - (Sec 24)","2006-10-03","2007-03-12"]
["LN02040333","AVAIL: 2kw Pwr Supply (SEC-24) Ready for Integ","2007-03-13","2007-03-12"]
["LN020404","Q21201-Q21901 Split SUMMARY","2006-10-03","2006-11-21"]
["LN02040404","Procure Q21201-Q21901 Hardware","2006-10-03","2006-11-13"]
["LN02040409","RCV: Quad Q21201-Q21901 Hardware","2006-11-14","2006-11-14"]
["LN02040414","Integrate Cables for quad Q21201-Q21901 Hardware","2006-11-15","2006-11-21"]
["LN02040433","AVAIL: Q21201-Q21901 Split Ready for Integ","2006-11-22","2006-11-21"]
["LN020405","Q24201-Q24501 Split SUMMARY","2006-10-03","2007-03-20"]
["LN02040505","Procure Q24201-Q24501Hardware","2006-10-03","2007-03-12"]
["LN02040510","RCV: Quad Q24201-Q24501 Hardware","2007-03-13","2007-03-13"]
["LN02040515","Integrate Cables for quad Q24201-Q24501 Hardware","2007-03-14","2007-03-20"]
["LN02040520","AVAIL: Q24201-Q24501 Split Ready for Integ","2007-03-21","2007-03-20"]
["LN020406","25kw Pwr Supply (BX21-24) POWER SUPPLY SUMMARY","2006-10-03","2008-02-12"]
["LN02040604","Procure 25kw Pwr Supply (BX21-24) - Hardware","2006-10-03","2007-03-12"]
["LN0204061","10kw POWER SUPPLY (Q24601) SUMMARY","2006-10-03","2007-03-20"]
["LN02040615","Procure 10kw Pwr Supply - (Q24601)","2006-10-03","2007-03-12"]
["LN02040616","RCV: Q24601 Hardware","2007-03-13","2007-03-13"]
["LN02040617","Integrate Cables for Q24601","2007-03-14","2007-03-20"]
["LN02040619","AVAIL: 10kw Pwr Supply (Q24601) Ready for Integ","2007-03-21","2007-03-20"]
["LN02040646","AVAIL: 25kw Pwr Supply (BX21-24) Ready for Instl","2008-02-12","2008-02-12"]
["LN020407","10KW PS - (Q24701A,Q24701B) SUMMARY","2006-10-03","2007-03-20"]
["LN02040705","Procure 10KW PS - (Q24701A,Q24701B) Hardware","2006-10-03","2007-03-12"]
["LN02040710","RCV: Q24701A,Q24701B Split Hardware","2007-03-13","2007-03-13"]
["LN02040715","Integrate Cables for Q24701A,Q2470 split H/W","2007-03-14","2007-03-20"]
["LN02040720","AVAIL: Q24201-Q24501 Split Ready for Integ","2007-03-21","2007-03-20"]
["LN020408","10kw POWER SUPPLY (QM21) SUMMARY","2006-10-03","2007-03-27"]
["LN02040804","Procure 10kw Pwr Supply (QM21)","2006-10-03","2007-03-26"]
["LN02040833","AVAIL: QM21 10kw P/S Ready for Integ","2007-03-27","2007-03-27"]
["LN020409","Q24901A,Q24901B SUMMARY","2006-10-03","2007-03-13"]
["LN02040904","Procure Q24901A,Q24901B Hardware","2006-10-03","2007-03-12"]
["LN02040933","AVAIL: Q24901A,Q24901B 10kw P/S Ready for  Integ","2007-03-13","2007-03-13"]
["LN020410","2kw POWER SUPPLY (SEC-25) SUMMARY","2006-10-03","2007-03-12"]
["LN0204100","QM22 10kw Pwr Supply SUMMARY","2006-10-03","2007-03-13"]
["LN02041004","Procure 2kw Pwr Supply - (SEC 25)","2006-10-03","2007-03-12"]
["LN02041005","Procure QM22 10kw Pwr Supply","2006-10-03","2007-03-12"]
["LN02041010","AVAIL: QM22 10kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN02041033","AVAIL: 2kw Pwr Supply (SEC-25) Ready for Integ","2007-03-13","2007-03-12"]
["LN020411","2kw POWER SUPPLY (SEC-26) SUMMARY","2006-10-03","2007-03-12"]
["LN02041100","Q5 10kw P/S SUMMARY","2006-10-03","2007-03-13"]
["LN02041104","Procure2kw Pwr Supply - (Sec 26)","2006-10-03","2007-03-12"]
["LN02041105","Procure Q5 10kw P/S","2006-10-03","2007-03-12"]
["LN02041110","AVAIL: Q5 10kw P/S Ready for Integ","2007-03-13","2007-03-13"]
["LN02041133","AVAIL: 2kw Pwr Supply (SEC-26) Ready for Integ","2007-03-13","2007-03-12"]
["LN020412","2kw POWER SUPPLY (SEC-27) SUMMARY","2006-10-03","2007-03-12"]
["LN02041204","Procure 2kw Pwr Supply - (Sec 27)","2006-10-03","2007-03-12"]
["LN02041233","AVAIL: 2kw Pwr Supply (SEC-27) Ready for Integ","2007-03-13","2007-03-12"]
["LN020415","KICKER (BXBKIK) SUMMARY","2006-09-15","2007-03-19"]
["LN02041510","Prep Bid Package - Pwr Supply - Dipole Type","2006-09-15","2006-09-21"]
["LN02041515","RELEASE: RFP - Pwr Supply - Dipole Type","2006-09-22","2006-09-21"]
["LN02041520","Vendors Prep Proposals - Pwr Spply - Dipole Type","2006-09-22","2006-09-28"]
["LN02041525","RCV: Vendor Proposals - Pwr Supply - Dipole Type","2006-09-29","2006-09-28"]
["LN02041530","Evaluate Vendors Prep Proposals","2006-09-29","2006-10-05"]
["LN02041535","AWARD: Contract - KICKER (BXBKIK)","2006-10-06","2006-10-06"]
["LN02041540","Fab & Assy - KICKER (BXBKIK)","2006-10-09","2007-03-16"]
["LN02041545","AVAIL: BXBKIK Pwr Supply Ready for Instl","2007-03-19","2007-03-19"]
["LN02041610","BY1 POWER SUPPLY SUMMARY","2006-10-03","2007-03-13"]
["LN02041615","Procure 50.8kw P/S (BX31,32,35,36)","2006-10-03","2007-03-12"]
["LN02041620","AVAIL: 50.8kw P/S (BX31,32,35,36) Ready for Inst","2007-03-13","2007-03-13"]
["LN020417","Q6 10kw P/S Ready for Integ SUMMARY","2006-10-03","2007-03-13"]
["LN02041704","Procure Q6 10kw P/S Ready for Integ","2006-10-03","2007-03-12"]
["LN02041733","AVAIL: Q6 10kw P/S Ready for Integ","2007-03-13","2007-03-13"]
["LN020418","QA0 10kw  P/S Ready for Integ SUMMARY","2006-10-03","2007-03-13"]
["LN02041804","Procure QA0 10kw  P/S Ready for Integ","2006-10-03","2007-03-12"]
["LN02041833","AVAIL: QA0 10kw  P/S Ready for Integ","2007-03-13","2007-03-13"]
["LN020419","Q50Q1,Q50Q2,Q50Q3 10kw P/S Rdy for Integ SUMMARY","2006-10-03","2007-03-13"]
["LN02041904","Procure Q50Q1,Q50Q2,Q50Q3 10kw P/S","2006-10-03","2007-03-12"]
["LN02041933","AVAIL: Q50Q1,Q50Q2,Q50Q3 10kw P/S Rdy for Integ","2007-03-13","2007-03-13"]
["LN020420","QVM1 10kw Pwr Supply SUMMARY","2006-10-03","2007-03-13"]
["LN02042004","Procure QVM1 10kw Pwr Supply","2006-10-03","2007-03-12"]
["LN02042033","AVAIL: QVM1 10kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN020421","QVM2 10kw Pwr Supply SUMMARY","2006-10-03","2007-03-13"]
["LN02042104","Procure QVM2 10kw Pwr Supply","2006-10-03","2007-03-12"]
["LN02042133","AVAIL: QVM2 10kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN020422","QEM110 kw Pwr Supply SUMMARY","2006-10-03","2007-03-13"]
["LN02042205","Procure QEM110 kw Pwr Supply","2006-10-03","2007-03-12"]
["LN02042210","AVAIL: QEM110 kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN020423","QEM2 10kw Pwr Supply SUMMARY","2006-10-03","2007-03-13"]
["LN02042305","Procure QEM2 10kw Pwr Supply","2006-10-03","2007-03-12"]
["LN02042310","AVAIL: QEM2 10kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN020424","QVM3 10kw Pwr Supply SUMMARY","2006-10-03","2007-03-13"]
["LN02042404","Procure QVM3 10kw Pwr Supply","2006-10-03","2007-03-12"]
["LN02042433","AVAIL: QVM3 10kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN020425","QVM410kw Pwr Suppl SUMMARY","2006-10-03","2007-03-13"]
["LN02042501","Procure QVM410kw Pwr Suppl","2006-10-03","2007-03-12"]
["LN02042506","AVAIL: QVM410kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN020426","QVB1-3 Pwr Supply SUMMARY","2006-10-03","2007-03-13"]
["LN02042605","Procure QVB1-3 Pwr Supply","2006-10-03","2007-03-12"]
["LN02042610","AVAIL: QVB1-3 Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN020427","QDL31-34 10kw Pwr Supply SUMMARY","2006-10-03","2007-03-13"]
["LN02042705","Procure QDL31-34 10kw Pwr Supply","2006-10-03","2007-03-12"]
["LN02042710","AVAIL: QDL31-34 10kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN020428","QE31-36 10kw Pwr Supply SUMMARY","2006-10-03","2007-03-13"]
["LN02042805","Procure QE31-36 10kw Pwr Supply","2006-10-03","2007-03-12"]
["LN02042810","AVAIL: QE31-36 10kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN020429","QEM3 10kw Pwr SupplySUMMARY","2006-10-03","2007-03-13"]
["LN02042905","Procure QEM3 10kw Pwr Supply","2006-10-03","2007-03-12"]
["LN02042910","AVAIL: QEM3 10kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN02043000","QEM4 10kw Pwr Supply SUMMARY","2006-10-03","2007-03-20"]
["LN02043005","Procure QEM4 10kw Pwr Supply","2006-10-03","2007-03-12"]
["LN02043010","RCV: QEM4 10kw Pwr Supply Ready Hardware","2007-03-13","2007-03-13"]
["LN02043013","Integrate and Test Magnet Interlock","2007-03-14","2007-03-20"]
["LN02043015","AVAIL: QEM4 10kw Pwr Supply Ready for Integ","2007-03-21","2007-03-20"]
["LN020431","QT11,13,21,23,31,33,41,43 26kw P/S SUMMARY","2006-10-03","2007-03-13"]
["LN02043105","Procure QT11,13,21,23,31,33,41,43 26kw P/S","2006-10-03","2007-03-12"]
["LN02043110","AVAIL: QT11,13,21,23,31,33,41,43 26kw Pwr Supply","2007-03-13","2007-03-13"]
["LN020432","QT12,22,32,42  27.2 kw P/S SUMMARY","2006-10-03","2007-03-13"]
["LN02043205","Procure QT12,22,32,42  27.2 kw P/S","2006-10-03","2007-03-12"]
["LN02043210","AVAIL: QT12,22,32,42  27.2 kw P/S Rdy for Integ","2007-03-13","2007-03-13"]
["LN020433","QUM1 10kw Pwr Supply Ready SUMMARY","2006-10-03","2007-03-13"]
["LN02043305","Procure QUM1 10kw Pwr Supply Ready","2006-10-03","2007-03-12"]
["LN02043310","AVAIL: QUM1 10kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN020434","BY1- 2 POWER SUPPLY SUMMARY","2006-10-03","2007-03-13"]
["LN0204341","QUM2 10kw Pwr Supply SUMMARY","2006-10-03","2007-03-13"]
["LN02043410","Procure QUM2 10kw Pwr Supply","2006-10-03","2007-03-12"]
["LN02043415","AVAIL: QUM2 10kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN02043418","Procure 10kw P/S (BY1-2) - Hardware","2006-10-03","2007-03-12"]
["LN02043423","AVAIL: 10kw P/S (BY1-2) Ready for Instl","2007-03-13","2007-03-13"]
["LN020435","KICKER (BYBKIK) SUMMARY","2006-09-15","2007-03-19"]
["LN02043501","Prep Bid Package -  BYBKIK Pwr Supply","2006-09-15","2006-09-21"]
["LN02043503","RELEASE: RFP - Pwr Supply -  BYBKIK Pwr Supply","2006-09-22","2006-09-21"]
["LN02043505","Vendors Prep Proposals -  BYBKIK Pwr Supply","2006-09-22","2006-09-28"]
["LN02043507","RCV: Vendor Proposals -  BYBKIK Pwr Supply","2006-09-29","2006-09-28"]
["LN02043509","Evaluate Vendors Prep Proposals","2006-09-29","2006-10-05"]
["LN02043511","AWARD: Contract -  BYBKIK Pwr Supply","2006-10-06","2006-10-06"]
["LN02043512","Fab & Assy- Power Supply - (Dipole Type)","2006-10-09","2007-03-16"]
["LN02043533","AVAIL: BYBKIK Pwr Supply Ready for Instl","2007-03-19","2007-03-19"]
["LN020436","SPARE PWR SUPPLY SUMMARY- DIPOLE TYPE (1ea)","2006-10-03","2007-04-02"]
["LN0204361","BYW1- 3 POWER SUPPLY SUMMARY","2006-10-03","2007-03-13"]
["LN02043615","Procure 30kw Pwr Supply (BW1-3) - Hardware","2006-10-03","2007-03-12"]
["LN02043619","AVAIL: 30kw Pwr Supply (BW1-3) Ready for Instl","2007-03-13","2007-03-13"]
["LN02043621","Spare Pwr Supply (Dipole Type) Prcurement","2006-10-03","2007-03-12"]
["LN02043622","Assemble Pwr Supply, Transductor & Control","2007-03-13","2007-03-20"]
["LN02043628","Integrate Pwr Supply, Transductor & Control","2007-03-21","2007-03-29"]
["LN02043630","Integrate Cables","2007-03-30","2007-04-02"]
["LN02043633","AVAIL: Spare Power Supply Available - Dipole Typ","2007-04-03","2007-04-02"]
["LN020437","12Amp Pwr Supply + Gnd Flt -(MCOR_1) 7 SUMMARY","2006-02-08","2006-04-10"]
["LN02043704","Procure 12Amp Pwr Supply + Gnd Flt -(MCOR_1) 7","2006-02-08","2006-04-05"]
["LN02043706","RCV: 12Amp Pwr Supply + Gnd Flt -(MCOR_1) 7 Mod","2006-04-06","2006-04-06"]
["LN02043738","Integrate Cables","2006-04-07","2006-04-10"]
["LN02043741","AVAIL: 12Amp P/S + Gnd Flt -(MCOR_1) 7","2006-04-11","2006-04-10"]
["LN020438","MCOR_2 (30Amp) SUMMARY","2006-02-08","2006-04-10"]
["LN02043805","Procure 30Amp P/S + Gnd Flt -(MCOR_2) 7 Mods","2006-02-08","2006-04-05"]
["LN02043810","RCV: 30Amp P/S + Gnd Flt -(MCOR_2) 7 Mods","2006-04-06","2006-04-06"]
["LN02043815","Integrate Cables","2006-04-07","2006-04-10"]
["LN02043820","AVAIL: 30Amp P/S + Gnd Flt -(MCOR_2) 7 Mods","2006-04-11","2006-04-10"]
["LN020439","MCOR_3 (30Amp) SUMMARY","2006-02-08","2006-04-10"]
["LN02043905","Procure 30Amp P/S + Gnd Flt -(MCOR_3) 7 Mods","2006-02-08","2006-04-05"]
["LN02043910","RCV: 30Amp P/S + Gnd Flt -(MCOR_3) 7 Mods","2006-04-06","2006-04-06"]
["LN02043915","Integrate Cables","2006-04-07","2006-04-10"]
["LN02043920","AVAIL: 30Amp P/S + Gnd Flt -(MCOR_3) 7 Mods","2006-04-11","2006-04-10"]
["LN020440","MCOR_4 (30Amp) SUMMARY","2006-02-08","2006-04-10"]
["LN02044005","Procure 30Amp P/S + Gnd Flt -(MCOR_4) 7 Mod","2006-02-08","2006-04-05"]
["LN02044010","RCV: 30Amp P/S + Gnd Flt -(MCOR_4) 7 Mods","2006-04-06","2006-04-06"]
["LN02044015","Integrate Cables","2006-04-07","2006-04-10"]
["LN02044020","AVAIL: 30Amp P/S + Gnd Flt -(MCOR_4) 7 Mods","2006-04-11","2006-04-10"]
["LN020445","MCOR_5 (12/30Amp) SUMMARY","2006-10-03","2007-03-29"]
["LN02044505","Procure 12/30Amp P/S + Gnd Flt -(MCOR_5) 7 Mods","2006-10-03","2007-03-26"]
["LN02044510","RCV: 12/30Amp P/S + Gnd Flt -(MCOR_5) 7 Mods","2007-03-27","2007-03-27"]
["LN02044515","Integrate Cables","2007-03-28","2007-03-29"]
["LN02044520","AVAIL: 12/30Amp P/S + Gnd Flt -(MCOR_5) 7 Mods","2007-03-30","2007-03-29"]
["LN020446","MCOR_LTU3 (12Amp) SUMMARY","2006-10-03","2007-03-15"]
["LN02044605","Procure  12Amp P/S + Gnd Flt-(MCOR_LTU3) Mods","2006-10-03","2007-03-12"]
["LN02044610","RCV:  12Amp P/S + Gnd Flt-(MCOR_LTU3) Mods","2007-03-13","2007-03-13"]
["LN02044615","Integrate Cables","2007-03-14","2007-03-15"]
["LN02044620","AVAIL:  12Amp P/S + Gnd Flt-(MCOR_LTU3) Mods","2007-03-16","2007-03-15"]
["LN02044700","MCOR_LTU3 (12Amp) SUMMARY","2006-10-03","2007-03-23"]
["LN02044705","Procure 12Amp P/S + Gnd Flt-(MCOR_LTU3) 5 Mods","2006-10-03","2007-03-12"]
["LN02044710","RCV: 12Amp P/S + Gnd Flt-(MCOR_LTU3) 5 Mods","2007-03-13","2007-03-13"]
["LN02044715","Integrate Cables","2007-03-14","2007-03-15"]
["LN02044717","Assemble Pwr Supply, Transductor & Control","2007-03-16","2007-03-23"]
["LN02044720","AVAIL: 12Amp P/S + Gnd Flt-(MCOR_LTU3) 5 Mods","2007-03-26","2007-03-23"]
["LN020448","MCOR_LTU5 (12Amp) SUMMARY","2006-10-03","2007-03-15"]
["LN02044805","Procure 12Amp P/S+ Gnd Flt-(MCOR_LTU5) 5 Mods","2006-10-03","2007-03-12"]
["LN02044810","RCV: 12Amp P/S+ Gnd Flt-(MCOR_LTU5) 5 Mods","2007-03-13","2007-03-13"]
["LN02044815","Integrate Cables","2007-03-14","2007-03-15"]
["LN02044820","AVAIL: 12Amp P/S+ Gnd Flt-(MCOR_LTU5) 5 Mods","2007-03-16","2007-03-15"]
["LN020449","MCOR_LTU6 (12Amp) SUMMARY","2006-10-03","2007-03-15"]
["LN02044905","Procure 12Amp P/S + Gnd Flt-(MCOR_LTU6) 5 Mods","2006-10-03","2007-03-12"]
["LN02044910","RCV: 12Amp P/S + Gnd Flt-(MCOR_LTU6) 5 Mods","2007-03-13","2007-03-13"]
["LN02044915","Integrate Cables","2007-03-14","2007-03-15"]
["LN02044920","AVAIL: 12Amp P/S + Gnd Flt-(MCOR_LTU6) 5 Mods","2007-03-16","2007-03-15"]
["LN020450","MCOR_LTU7 (12Amp) SUMMARY","2006-10-03","2007-03-15"]
["LN02045010","RCV: 12Amp P/S + Gnd Flt-(MCOR_LTU7) 5 Mods","2007-03-13","2007-03-13"]
["LN02045015","Integrate Cables","2007-03-14","2007-03-15"]
["LN02045020","AVAIL: 12Amp P/S + Gnd Flt-(MCOR_LTU7) 5 Mods","2007-03-16","2007-03-15"]
["LN020451","MCOR_LTU8 (12Amp) SUMMARY","2006-10-03","2007-03-15"]
["LN02045105","Procure  12Amp P/S + Gnd Flt-(MCOR_LTU8) 5 Mods","2006-10-03","2007-03-12"]
["LN02045110","RCV:  12Amp P/S + Gnd Flt-(MCOR_LTU8) 5 Mods","2007-03-13","2007-03-13"]
["LN02045115","Integrate Cables","2007-03-14","2007-03-15"]
["LN02045120","AVAIL:  12Amp P/S + Gnd Flt-(MCOR_LTU8) 5 Mods","2007-03-16","2007-03-15"]
["LN020452","SPARE PWR SUPPLY SUMMARY- TRIM TYPE (1ea)","2006-10-03","2007-03-15"]
["LN0204520","MCOR_LTU9 (12Amp) SUMMARY","2006-10-03","2007-03-15"]
["LN02045205","Procure 12Amp P/S + Gnd Flt-(MCOR_LTU9) 5 Mods","2006-10-03","2007-03-12"]
["LN02045210","RCV: 12Amp P/S + Gnd Flt-(MCOR_LTU9) 5 Mods","2007-03-13","2007-03-13"]
["LN02045215","Integrate Cables","2007-03-14","2007-03-15"]
["LN02045220","AVAIL: 12Amp P/S + Gnd Flt-(MCOR_LTU9) 5 Mods","2007-03-16","2007-03-15"]
["LN02045225","Spare Power Supply Procurement","2006-10-03","2007-03-12"]
["LN02045226","RCV: Spare MCOR System Hardware/Equip.","2007-03-13","2007-03-12"]
["LN02045238","Integrate Cables","2007-03-13","2007-03-14"]
["LN02045241","AVAIL: Spare Power Supply Available - Trim Type","2007-03-15","2007-03-14"]
["LN020453","SPARE PWR SUPPLY SUMMARY- QUAD TYPE (1ea)","2006-10-03","2007-04-03"]
["LN02045317","Spare Pwr Supply (Quad Type) Procurement","2006-10-03","2007-03-12"]
["LN02045318","Assemble Pwr Supply, Transductor & Control","2007-03-13","2007-03-20"]
["LN02045320","Integrate Pwr Supply, Transductor & Control","2007-03-21","2007-03-29"]
["LN02045322","Integrate Cables","2007-03-30","2007-04-02"]
["LN02045324","Integrate Magnet Interlock","2007-04-03","2007-04-03"]
["LN02045326","AVAIL: Spare Power Supply Available - Quad Type","2007-04-04","2007-04-03"]
["LN020455","QUM3 10kw Pwr SupplySUMMARY","2006-10-03","2007-03-13"]
["LN02045505","Procure QUM3 10kw Pwr Supply","2006-10-03","2007-03-12"]
["LN02045510","AVAIL: QUM3 10kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN020465","QUM4 10kw Pwr Supply SUMMARY","2006-10-03","2007-03-13"]
["LN02046505","Procure QUM4 10kw Pwr Supply","2006-10-03","2007-03-12"]
["LN02046510","AVAIL: QUM4 10kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN020466","QDMP1-2 10kw Pwr Supply SUMMARY","2006-10-03","2007-03-13"]
["LN02046605","Procure QDMP1-2 10kw Pwr Supply","2006-10-03","2007-03-12"]
["LN02046610","AVAIL: QDMP1-2 10kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN020467","QUE1 10kw Pwr Supply SUMMARY","2006-10-03","2007-03-13"]
["LN02046705","Procure QUE1 10kw Pwr Supply","2006-10-03","2007-03-12"]
["LN02046710","AVAIL: QUE1 10kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN020468","QUE2 10kw Pwr Supply SUMMARY","2006-10-03","2007-03-13"]
["LN02046805","Procure QUE2 10kw Pwr Supply","2006-10-03","2007-03-12"]
["LN02046810","AVAIL: QUE2 10kw Pwr Supply Ready for Integ","2007-03-13","2007-03-13"]
["LN020471","MCOR_6 (12/30Amp) SUMMARY","2006-10-03","2007-03-15"]
["LN02047105","Procure 12/30Amp P/Sy + Gnd Flt -(MCOR_6) 7 Mods","2006-10-03","2007-03-12"]
["LN02047110","RCV: 12/30Amp P/Sy + Gnd Flt -(MCOR_6) 7 Mods","2007-03-13","2007-03-13"]
["LN02047115","Integrate Cables","2007-03-14","2007-03-15"]
["LN02047120","AVAIL: 12/30Amp P/Sy + Gnd Flt -(MCOR_6) 7 Mods","2007-03-16","2007-03-15"]
["LN020472","MCOR_BS1Y (12Amp) SUMMARY","2006-10-03","2007-03-15"]
["LN02047205","Procure 12Amp P/S + Gnd Flt-(MCOR_BSY1) 5 Mods","2006-10-03","2007-03-12"]
["LN02047210","RCV: 12Amp P/S + Gnd Flt-(MCOR_BSY1) 5 Mods","2007-03-13","2007-03-13"]
["LN02047215","Integrate Cables","2007-03-14","2007-03-15"]
["LN02047220","AVAIL: 12Amp P/S + Gnd Flt-(MCOR_BSY1) 5 Mods","2007-03-16","2007-03-15"]
["LN020473","MCOR_LTU1 (12Amp) SUMMARY","2006-10-03","2007-03-15"]
["LN02047305","Procure 12Amp P/S + Gnd Flt-(MCOR_LTU1) 5 Mods","2006-10-03","2007-03-12"]
["LN02047310","RCV: 12Amp P/S + Gnd Flt-(MCOR_LTU1) 5 Mods","2007-03-13","2007-03-13"]
["LN02047315","Integrate Cables","2007-03-14","2007-03-15"]
["LN02047320","AVAIL: 12Amp P/S + Gnd Flt-(MCOR_LTU1) 5 Mods","2007-03-16","2007-03-15"]
["LN020474","MCOR_LTU2 (12Amp) SUMMARY","2006-10-03","2007-03-15"]
["LN02047405","Procure 12Amp P/S + Gnd Flt-(MCOR_LTU2) 5 Mods","2006-10-03","2007-03-12"]
["LN02047410","RCV: 12Amp P/S + Gnd Flt-(MCOR_LTU2) 5 Mods","2007-03-13","2007-03-13"]
["LN02047415","Integrate Cables","2007-03-14","2007-03-15"]
["LN02047420","AVAIL: 12Amp P/S + Gnd Flt-(MCOR_LTU2) 5 Mods","2007-03-16","2007-03-15"]
["LN020479","MCOR_DMP1 (12Amp) SUMMARY","2006-10-03","2007-03-15"]
["LN02047905","Procure 12Amp P/S + Gnd Flt-(MCOR_DMP1) 5 Mods","2006-10-03","2007-03-12"]
["LN02047910","RCV: 12Amp P/S + Gnd Flt-(MCOR_DMP1) 5 Mods","2007-03-13","2007-03-13"]
["LN02047915","Integrate Cables","2007-03-14","2007-03-15"]
["LN02047920","AVAIL: 12Amp P/S + Gnd Flt-(MCOR_DMP1) 5 Mods","2007-03-16","2007-03-15"]
["LN020480","10kw Pwr Supply (MUSPLR) SUMMARY","2006-10-03","2007-03-13"]
["LN02048018","Procure 10kw Pwr Supply (MUSPLR)- Hrdwr","2006-10-03","2007-03-12"]
["LN02048046","AVAIL: 10kw Pwr Supply (MUSPLR)- Ready for Integ","2007-03-13","2007-03-13"]
["LN020490","Procure 10kw Pwr Supply  - (BYD1-3) SUMMARY","2006-10-03","2007-03-13"]
["LN02049015","Procure 10kw Pwr Supply  - (BYD1-3)","2006-10-03","2007-03-12"]
["LN02049020","AVAIL: 10kw Pwr Supply (BYD1-3) Ready for Integ","2007-03-13","2007-03-13"]
["LN0204_000","LINAC POWER SUPPLIES (DIPOLE) SUMMARY","2005-06-15","2008-07-03",null,"2005-06-15"]
["LN0204_010","Finalize Power Conv Reqmts Definition (Dipole)","2006-02-01","2006-02-07"]
["LN0204_015","COMP: Pwr Conv Specification Requirements","2006-02-08","2006-02-07"]
["LN0204_020","Dev Engr (43 instaces - 18 types) PED","2005-06-15","2006-01-31",null,"2005-06-15","2006-01-31"]
["LN0204_021","Dev Engr (43 instaces - 18 types) CONST","2006-07-05","2007-12-05"]
["LN0204_025","Create System Drawings","2006-07-05","2008-02-11"]
["LN0204_050","LINAC POWER SUPPLIES (QUAD) SUMMARY","2006-02-01","2007-03-27"]
["LN0204_060","Finalize Power Conv Reqmts Definition (Quad)","2006-02-01","2006-02-07"]
["LN0204_065","COMP: Pwr Conv Specification Reqmts (Quad)","2006-02-08","2006-02-07"]
["LN0204_075","Conduct ES&H Review - (Quad Type)","2006-02-08","2006-02-09"]
["LN0204_080","COMP: Power Supply Design  - (Quad Type)","2006-02-10","2006-02-09"]
["LN0204_100","LINAC POWER SUPPLIES (TRIM) SUMMARY","2006-02-01","2007-03-29"]
["LN0204_110","Finalize Power Conv Reqmts Definition (Trim)","2006-02-01","2006-02-07"]
["LN0204_115","COMP: Pwr Conv Specification Requirements","2006-02-08","2006-02-07"]
["LN0204_200","CONTROLS & POWER SUPPLY MISC HDWR SUMMARY","2005-11-01","2007-12-10",null,"2005-11-01"]
["LN0204_210","Write Software to Integrate","2006-02-01","2006-04-26"]
["LN0204_212","Write Documentation","2006-04-27","2006-05-10"]
["LN0204_214","Perform Point to Point Checkout","2006-05-11","2006-08-04"]
["LN0204_216","Integrate Hardware and Software","2006-08-07","2006-08-18"]
["LN0204_218","AVAIL: Linac Controls Ready to Integrate","2006-08-21","2006-08-18"]
["LN0204_444","L1-BC1 Cable Plant Design","2005-11-01","2006-03-15",null,"2005-11-01"]
["LN0204_454","COMP: L1-BC1 Cable Plant Design","2006-03-16","2006-03-15"]
["LN0204_464","Prep L1-BC1 Bid Package","2006-03-16","2006-03-22"]
["LN0204_474","AWARD: L1-BC1 Cable Plant Contract","2006-03-23","2006-03-23"]
["LN0204_484","Vendor Fab L1-BC1 Cable Plant Hardware","2006-03-24","2006-06-16"]
["LN0204_494","RCV: L1-BC1 Cable Plant from Vendor","2006-06-19","2006-06-16"]
["LN0204_504","Intall & Integrate L1-BC1 Cable Plant","2006-06-19","2006-10-10"]
["LN0204_514","AVAIL: Cable Plant Ready for L1-BC1 Installation","2006-10-11","2006-10-10"]
["LN0204_605","L1-BC1 Racks Design","2005-11-01","2006-03-15",null,"2005-11-01"]
["LN0204_615","COMP: L1-BC1 Racks Design","2006-03-16","2006-03-15"]
["LN0204_625","Prep L1-BC1 Bid Package","2006-03-16","2006-03-22"]
["LN0204_635","AWARD: L1-BC1 Racks Contract","2006-03-23","2006-03-23"]
["LN0204_645","Vendor Fab LC1-BC1 Racks","2006-03-24","2006-06-16"]
["LN0204_655","RCV: L1-BC1 Racks from Vendor","2006-06-19","2006-06-16"]
["LN0204_665","Intall & Integrate L1-BC1 Racks","2006-06-19","2006-10-10"]
["LN0204_675","AVAIL: Racks for L1-BC1 Installation","2006-10-11","2006-10-10"]
["LN0204_685","L2-BC2 Cable Plant Design","2006-10-02","2006-11-10"]
["LN0204_695","COMP: L2-BC2 Cable Plant Design","2006-11-13","2006-11-10"]
["LN0204_705","Prep L2-BC2 Cable Plant Bid Package","2006-11-13","2006-11-17"]
["LN0204_715","AWARD: L2-BC2 Cable Plant Contract","2006-11-20","2006-11-20"]
["LN0204_725","Vendor Fab L2-BC2 Cable Plant Hardware","2006-11-21","2007-03-05"]
["LN0204_735","RCV: L2-BC2 Cable Plant from Vendor","2007-03-06","2007-03-05"]
["LN0204_745","Intall & Integrate L2-BC2 Cable Plant","2007-03-06","2007-06-26"]
["LN0204_755","AVAIL: Cable Plant Ready for L2-BC2 Installation","2007-06-27","2007-06-26"]
["LN0204_765","L2-BC2 Racks Design","2006-10-02","2006-11-10"]
["LN0204_775","COMP: L2-BC2 Rack Design","2006-11-13","2006-11-10"]
["LN0204_785","Prep LC2-BC2 Bid Package","2006-11-13","2007-02-01"]
["LN0204_795","AWARD: LC2-BC2 Racks Contract","2007-02-02","2007-02-02"]
["LN0204_805","Vendor Fab LC2-BC2 Racks","2007-02-05","2007-04-30"]
["LN0204_815","RCV: L2-BC2 Racks from Vendor","2007-05-01","2007-04-30"]
["LN0204_825","Intall & Integrate L2-BC2 Racks","2007-05-01","2007-08-22"]
["LN0204_835","AVAIL: Racks for L2-BC2 Installation","2007-08-23","2007-08-22"]
["LN0204_926","LTU Cable Plant Design","2007-04-02","2007-05-11"]
["LN0204_936","COMP: LTU Cable Plant Design","2007-05-14","2007-05-11"]
["LN0204_946","Prep LTLU Bid Package","2007-05-14","2007-05-18"]
["LN0204_956","AWARD: LTU Cable Plant Contract","2007-05-21","2007-05-21"]
["LN0204_966","Vendor Fab LTU Cable Plant Hardware","2007-05-22","2007-08-15"]
["LN0204_976","RCV: LTU Cable Plant from Vendor","2007-08-16","2007-08-15"]
["LN0204_986","Intall & Integrate LTU Cable Plant","2007-08-16","2007-12-10"]
["LN0204_996","AVAIL: Cable Plant Ready for LTU Installation","2007-12-11","2007-12-10"]
["LN0204_997","LTU Racks Design","2007-04-02","2007-05-11"]
["LN0204`007","COMP: LTU Racks Design","2007-05-14","2007-05-11"]
["LN0204`017","Prep LTU Bid Package","2007-05-14","2007-05-18"]
["LN0204`027","AWARD: LTU Racks Contract","2007-05-21","2007-05-21"]
["LN0204`037","Vendor Fab LTU Racks","2007-05-22","2007-08-15"]
["LN0204`047","RCV: LTU Racks from Vendor","2007-08-16","2007-08-15"]
["LN0204`057","Intall & Integrate LTU Racks","2007-08-16","2007-12-10"]
["LN0204`067","AVAIL: Racks for LTU Installation","2007-12-11","2007-12-10"]
["LN02050045","Construction Funds Available - Begin Procurement","2006-02-01","2006-01-31"]
["LN02050130","Procure Linac LLRF Hardware","2006-07-03","2006-09-26"]
["LN02050195","RCV: Procured parts - Bm Phz Monitor Cntrls","2006-09-27","2006-09-26"]
["LN02050201","Build LLRF H/W and Write Docmntatn (sec 24/30)","2006-08-28","2006-09-26"]
["LN02050206","Write LLRF S/W Docmntatn (sec 24/30)","2006-07-03","2006-07-10"]
["LN02050207","Integrate and Test (sec 24/30)","2006-09-27","2006-12-01"]
["LN02050260","Procure LLRF BL Mon Cntrls hardware","2006-07-03","2006-09-12"]
["LN02050265","RCV: Procured parts","2006-09-13","2006-09-12"]
["LN02050266","Integrate and Test (BLM sec 24/30)","2006-09-13","2006-10-10"]
["LN02050295","AVAIL: Bnch Length Monitor Cntrls Ready to Integ","2006-12-04","2006-12-01"]
["LN02055005","Procure 12Amp P/S + Gnd Flt-(MCOR_LTU7) 5 Mods","2006-10-03","2007-03-12"]
["LN02060190","Procure 3 sets of Controls Wire Scanners Ph-1","2006-07-03","2006-07-31"]
["LN02060191","RCV: 3 Sets of Controls Wire Scanners Ph-1","2006-08-01","2006-08-01"]
["LN02060200","Build HW & Write SW for LINAC Wire Scanners Ph-1","2006-08-02","2006-08-29"]
["LN02060210","Integrate and Test Controls Wire Scanners Ph-1","2006-08-30","2006-09-27"]
["LN02060220","AVAIL: Ph-1 Ctrl Wire Scanners Ready for Install","2006-08-30","2006-08-29"]
["LN02060230","Procure 8 sets of Controls Wire Scanners Ph-2","2006-08-30","2006-11-22"]
["LN02060232","RCV: 8 Sets of Controls Wire Scanners Ph-2","2006-11-27","2006-11-27"]
["LN02060240","Build HW & Write SW for LINAC Wire Scanners Ph-2","2006-11-28","2007-01-25"]
["LN02060250","Integrate and Test Controls Wire Scanners Ph-2","2007-01-26","2007-03-23"]
["LN02060260","AVAIL: Ph-2 Ctrl Wire Scanners Ready for Install","2007-03-26","2007-03-23"]
["LN02060270","Procure 4 sets of Controls Wire Scanners Ph-3","2007-03-26","2007-06-18"]
["LN02060272","RCV: 4 Sets of Controls Wire Scanners Ph-3","2007-06-19","2007-06-19"]
["LN02060280","Build HW & Write SW for LINAC Wire Scanners Ph-3","2007-06-20","2007-08-15"]
["LN02060290","Integrate and Test Controls Wire Scanners Ph-3","2007-08-16","2007-10-11"]
["LN020603","CONTROLS - TOROIDS (6) SUMMARY","2006-02-01","2006-12-06"]
["LN02060300","AVAIL: Ph-3 Ctrl Wire Scanners Ready for Install","2007-10-12","2007-10-11"]
["LN02060327","Construction Funds Available - Begin Procurement","2006-02-01","2006-01-31"]
["LN02060330","AWARD Torroid Shielding, Preamps, Hardware (6)","2006-07-03","2006-07-03"]
["LN02060331","Procure Torroid Shielding, Preamps, Hardware (6)","2006-07-05","2006-09-06"]
["LN02060340","Build Hardware (Toroids)","2006-09-07","2006-11-02"]
["LN02060358","Write Software - Toroids","2006-11-03","2006-11-09"]
["LN02060360","Write Documentation - Toroids","2006-11-10","2006-11-16"]
["LN02060361","Integrate and Test Toroids","2006-11-17","2006-12-06"]
["LN02060366","AVAIL: Toroids Cntrls Eq Ready for Rack Integ","2006-12-07","2006-12-06"]
["LN020604","CONTROLS - STOPPERS SUMMARY","2006-02-01","2007-09-25"]
["LN02060428","Construction Funds Available - Begin Procurement","2006-02-01","2006-01-31"]
["LN02060430","Procure Stopper Controls Hdwr/Eq","2007-04-17","2007-05-14"]
["LN02060431","RCV: Stopper Controls Hdwr/Eq","2007-05-15","2007-05-15"]
["LN02060432","Build Stopper Controls H/W","2007-05-16","2007-07-13"]
["LN02060438","Write Software - Stoppers","2007-07-16","2007-08-10"]
["LN02060440","Write Documentation - Stoppers","2007-08-13","2007-08-17"]
["LN02060446","Integrate and Test Stopper Controls","2007-08-20","2007-09-25"]
["LN02060448","AVAIL: Stoppers Cntrls Eq Ready for Rack Integ","2007-09-26","2007-09-25"]
["LN02060590","Procure 7 Units - Profile Monitors PH1","2006-07-03","2006-07-31"]
["LN02060592","RCV: 7 Units - Profile Monitors PH1","2006-08-01","2006-08-01"]
["LN020606","CONTROLS - E/O DIAGNOSTICS SUMMARY","2006-02-01","2006-09-08"]
["LN02060600","Build HW & Write SW - Profile Monitors PH1","2006-08-01","2006-08-28"]
["LN02060610","Integrate & Test - Profile Monitors PH1","2006-08-29","2006-09-26"]
["LN02060620","AVAIL: Profile Monitors PH1 Ready for Rack Integ","2006-08-29","2006-08-28"]
["LN02060627","Construction Funds Available - Begin Procurement","2006-02-01","2006-01-31"]
["LN02060628","Procure E/O Electronics","2006-05-30","2006-06-26"]
["LN02060630","Procure 7 Units - Profile Monitors PH2","2006-10-02","2006-12-27"]
["LN02060632","RCV: 7 Units - Profile Monitors PH2","2006-12-28","2006-12-28"]
["LN02060640","Build HW & Write SW - Profile Monitors PH2","2006-12-29","2007-01-29"]
["LN02060643","Build H/W (E/O Diagnostics)","2006-06-27","2006-08-02"]
["LN02060644","Write Software - E/O Diagnostics","2006-06-27","2006-07-25"]
["LN02060646","Write Documentation - E/O Eloctronics","2006-07-26","2006-08-01"]
["LN02060650","Integrate & Test - Profile Monitors PH2","2007-01-30","2007-02-27"]
["LN02060653","Integrate and Test E/O Electronics","2006-08-03","2006-09-08"]
["LN02060654","AVAIL: E/O Diag Cntrls Eq Ready for Rack Integ","2006-09-11","2006-09-08"]
["LN02060660","AVAIL: Profile Monitors PH2 Ready for Rack Integ","2007-02-28","2007-02-27"]
["LN02060670","Build HW & Write SW - Profile Monitors PH3","2007-02-28","2007-05-22"]
["LN02060672","Build HW & Write SW - Profile Monitors PH3","2007-05-23","2007-05-23"]
["LN02060680","Build HW & Write SW - Profile Monitors PH3","2007-05-24","2007-06-21"]
["LN02060690","Integrate & Test - Profile Monitors PH3","2007-06-22","2007-07-20"]
["LN020607","CONTROLS - BUNCH LENGTH MONITORS SUMMARY","2006-07-03","2006-10-12"]
["LN02060700","AVAIL: Profile Monitors PH3 Ready for Rack Integ","2007-07-23","2007-07-20"]
["LN02060727","Construction Funds Available - Begin Procurement","2006-07-03","2006-06-30"]
["LN02060728","Procure BLM Controls Hdwr/Eq","2006-07-03","2006-07-31"]
["LN02060733","Build BLM Hardware","2006-08-01","2006-09-06"]
["LN02060734","Write Software - BLM Diagnostics","2006-07-03","2006-07-31"]
["LN02060736","Write Documentation - BLM Diagnostics","2006-08-01","2006-08-07"]
["LN02060743","Integrate and Test BLM","2006-09-07","2006-10-12"]
["LN02060744","AVAIL: Bnch Lngth Cntrls Eq Ready for Rack Integ","2006-10-13","2006-10-12"]
["LN020608","CONTROLS - BEAM LOSS MONITORS (PLIC) SUMMARY","2006-08-01","2007-01-03"]
["LN02060828","Procure BLM Controls Hdwr/Eq","2006-08-01","2006-08-28"]
["LN02060833","Build Beam Loss Monitor","2006-08-29","2006-10-05"]
["LN02060834","Write Software - Bm Lss Mon Diagnostics","2006-10-06","2006-11-02"]
["LN02060836","Write Documentation - Bm Lss Mon Diagnostics","2006-11-03","2006-11-09"]
["LN02060843","Integrate & Test","2006-11-10","2007-01-03"]
["LN02060844","AVAIL: Bm Lss Mon Cntrls Eq Ready for Rack Integ","2007-01-04","2007-01-03"]
["LN020609","CONTROLS - SINGLE BEAM DUMP SUMMARY","2006-02-01","2007-03-21"]
["LN02060900","Receive System Requirements","2006-10-03","2006-10-09"]
["LN02060925","Design Single Beam Dump","2006-10-10","2006-12-13"]
["LN02060926","COMP: Controls Design - Single Beam Dump","2006-12-14","2006-12-13"]
["LN02060927","Construction Funds Available - Begin Procurement","2006-02-01","2006-01-31"]
["LN02060929","Single Beam Dump Hardware","2006-12-14","2007-01-26"]
["LN02060937","Build Single Beam Dump H/W","2007-01-29","2007-02-27"]
["LN02060938","Write Software - Single Beam Dump","2007-01-29","2007-02-26"]
["LN02060940","Write Documentation - Single Beam Dump","2007-02-27","2007-03-05"]
["LN02060947","Integrate and Test Signle Beam Dump","2007-03-06","2007-03-21"]
["LN02060948","AVAIL: Sngl Bm DmpCntrls Eq Ready for Rack Integ","2007-03-22","2007-03-21"]
["LN020610","CONTROLS - E-BEAM DUMP SUMMARY","2006-02-01","2007-05-03"]
["LN02061000","Receive System Requirements","2006-10-03","2006-10-09"]
["LN02061025","Design E Beam Dump","2006-10-10","2007-01-22"]
["LN02061026","COMP: Controls Design - E Beam Dump","2007-01-23","2007-01-22"]
["LN02061027","Construction Funds Available - Begin Procurement","2006-02-01","2006-01-31"]
["LN02061028","Procure E-Beam Dump Controls Hdwr/Eq","2007-01-23","2007-02-20"]
["LN02061033","Build E Beam Dump H/W","2007-01-23","2007-02-21"]
["LN02061034","Write Software - E Beam Dump","2007-02-22","2007-03-21"]
["LN02061036","Write Documentation - E Beam Dump","2007-03-22","2007-03-28"]
["LN02061043","Integrate and Test","2007-03-29","2007-05-03"]
["LN02061044","AVAIL: E Bm Dmp Cntrls Eq Ready for Rack Integ","2007-05-04","2007-05-03"]
["LN020611","CONTROLS - PROTECTION COLLIMATOR SUMMARY","2006-02-01","2007-02-13"]
["LN02061100","Receive System Requirements","2006-07-24","2006-07-28"]
["LN02061125","Design Moveable Protection Collimator","2006-07-31","2006-10-16"]
["LN02061126","COMP: Controls Design - Protection Collimators","2006-10-17","2006-10-16"]
["LN02061127","Construction Funds Available - Begin Procurement","2006-02-01","2006-01-31"]
["LN02061129","Movable Collimator Hardware","2006-10-17","2006-11-13"]
["LN02061165","Build Collimator H/W","2006-10-17","2006-11-14"]
["LN02061166","Write Software - Prot Collimator","2006-11-15","2006-12-14"]
["LN02061168","Write Documentation - Prot Collimator","2006-12-15","2007-01-05"]
["LN02061175","Integrate and Test","2007-01-08","2007-02-13"]
["LN02061176","AVAIL: Prot Coll Cntrls Eq Ready for Rack Integ","2007-02-14","2007-02-13"]
["LN020612","CONTROLS - MOVABLE COLLIMATORS SUMMARY","2006-02-01","2006-06-09"]
["LN02061200","Receive System Requirements","2006-02-01","2006-02-07"]
["LN02061225","Design Collimator Controls","2006-02-08","2006-03-08"]
["LN02061226","COMP: Controls Design - Movable Collimators","2006-03-09","2006-03-08"]
["LN02061228","Procure Movable Collimator Controls Hdwr/Eq","2006-03-09","2006-03-08"]
["LN02061233","Build Collimator H/W","2006-03-09","2006-04-06"]
["LN02061234","Write Software - Movable Collimator","2006-04-07","2006-05-04"]
["LN02061236","Write Documentation - Movable Collimator","2006-05-05","2006-05-11"]
["LN02061243","Integrate and Test","2006-05-12","2006-06-09"]
["LN02061244","AVAIL: Move Coll Cntrls Eq Ready for Rack Integ","2006-06-12","2006-06-09"]
["LN020613","CONTROLS - X-BAND ACCEL STRUCTURE SUMMARY","2005-11-01","2006-07-18",null,"2005-11-01"]
["LN02061300","Receive System Requirements","2005-11-01","2006-02-07",null,"2005-11-01"]
["LN02061325","Design X Band Controls","2006-02-08","2006-05-04"]
["LN02061326","COMP: Controls Design - X Band Accel Structures","2006-05-05","2006-05-04"]
["LN02061328","Procure X-Band Accel Struct Controls Hdwr/Eq","2006-05-05","2006-06-02"]
["LN02061333","Build X-Band H/W","2006-05-05","2006-06-02"]
["LN02061334","Write Software - X Band Accel Structure","2006-05-05","2006-06-02"]
["LN02061336","Write Documentation - X Band Accel Structure","2006-06-05","2006-06-09"]
["LN02061343","Integrate and Test","2006-06-12","2006-07-18"]
["LN02061344","AVAIL: X Bnd Stru Cntrls Eq Ready for Rack Integ","2006-07-19","2006-07-18"]
["LN02062550","Procure 7 Units of BPMs PH1","2006-07-05","2006-08-15"]
["LN02062552","RCV: 7 Units of BPMs Ph1","2006-08-16","2006-08-16"]
["LN02062560","Build HW & Write SW - BPMs PH1","2006-08-16","2006-09-13"]
["LN02062570","Integrate & Test - BPMs PH1","2006-09-14","2006-10-11"]
["LN02062580","AVAIL: L01 BPMs Ready for Install","2006-10-12","2006-10-11"]
["LN02062890","Procure 87 Units of BPMs PH2","2006-10-12","2006-11-22"]
["LN02062892","RCV: 87 Units of BPMs PH2","2006-11-27","2006-11-27"]
["LN02062900","Build HW & Write SW - BPMs PH2","2006-11-27","2007-03-22"]
["LN02062910","Integrate & Test - BPMs PH2","2007-03-23","2007-07-16"]
["LN02062920","AVAIL: L02 BPMs Ready for Install","2007-03-23","2007-03-22"]
["LN02062930","Procure 42 Units of BPMs PH3","2007-03-23","2007-05-03"]
["LN02062932","RCV: 42 Units of BPMs PH3","2007-05-04","2007-05-04"]
["LN02062940","Build HW & Write SW - BPMs PH3","2007-05-04","2007-06-29"]
["LN02062945","AVAIL: L03 BPMs Ready for Install","2007-07-02","2007-07-02"]
["LN02062950","Integrate & Test - BPMs PH3","2007-07-03","2007-08-28"]
["LN0208","LINAC TIMING SUMMARY","2006-02-01","2006-12-08"]
["LN02080020","Construction Funds Available - Begin Procurement","2006-02-01","2006-01-31"]
["LN02080025","Prep Bid Pak - Linac Timing Modules","2006-09-19","2006-09-25"]
["LN02080030","RELEASE: RFP - Linac Timing Modules","2006-09-26","2006-09-25"]
["LN02080035","Vendors Prep Proposals - Timing Cntrls Equipment","2006-09-26","2006-10-02"]
["LN02080040","RCV: Vendor Proposals","2006-10-03","2006-10-02"]
["LN02080045","Evaluate Vendor Proposals","2006-10-03","2006-10-09"]
["LN02080050","AWARD: Contract - Linac Timing Modules","2006-10-10","2006-10-10"]
["LN02080060","Vendor Fab & Assy - Timing modules (SLC to VME)","2006-10-11","2006-12-07"]
["LN02080065","RCV: Linac Timing Equip/Material Ready for Integ","2006-12-08","2006-12-08"]
["LN0209","VACUUM CONTROLS SUMMARY","2006-02-01","2007-06-19"]
["LN02090070","Construction Funds Available - Begin Procurement","2006-02-01","2006-01-31"]
["LN02090088","AWARD: Contract - Vacuum Valve Chassis  (4)","2006-02-01","2006-02-01"]
["LN02090090","Vendor Fab & Assy - Vacuum Valve Chassis  (4)","2006-02-02","2006-03-02"]
["LN02090250","Procure Vacuum Instrumentation & Iterlocks H/W","2006-05-30","2006-08-22"]
["LN02090260","Build Hardeare & Write SW for Vacuum Controls","2006-08-23","2006-09-20"]
["LN02090270","Integrate & Test Vacuum Controls","2006-09-21","2006-10-18"]
["LN02090280","AVAIL: Vac Controls Equip Ready for Install","2006-10-19","2006-10-18"]
["LN02090290","Procure Vacuum Instrumentation & Iterlocks H/W","2006-10-02","2006-12-27"]
["LN02090300","Build Hardeare & Write SW for Vacuum Controls","2006-12-28","2007-03-26"]
["LN02090310","Integrate & Test Vacuum Controls","2007-03-27","2007-06-19"]
["LN02090320","AVAIL: Vac Controls Equip Ready for Install","2007-06-20","2007-06-19"]
["LN021004","DATA COMMUNICATIONS SUMMARY","2006-02-01","2007-01-03"]
["LN02100400","Supervise Equipment Installation","2006-02-01","2006-03-15"]
["LN02100405","Upgrade/Establish BDF","2006-03-16","2006-03-16"]
["LN02100410","SEM Install Wall Board","2006-03-17","2006-03-30"]
["LN02100415","SEM Install Two 20 A Circuits","2006-03-31","2006-04-27"]
["LN02100420","Single Mode Fiber Installation","2006-04-28","2006-04-28"]
["LN02100425","Procure Singlemode Fiber","2006-05-01","2006-05-26"]
["LN02100430","Fiber Cabling Installation","2006-05-30","2006-06-26"]
["LN02100435","Fiber Termination","2006-06-27","2006-07-25"]
["LN02100440","Desktop Cabling Installation","2006-07-26","2006-07-26"]
["LN02100445","Cabling Installation in Ground & Sub Ground Loc","2006-07-27","2006-08-23"]
["LN02100450","Cable Termination","2006-08-24","2006-09-21"]
["LN02100455","Desktop Circuit Activation","2006-09-22","2006-09-22"]
["LN02100460","Telcom to Provide Phone & Activate Circuits","2006-09-25","2006-10-20"]
["LN02100465","Procure Cisco 3550-24 Hubs (6ea)","2006-10-23","2006-11-17"]
["LN02100470","Hub Installation & Data Circuit Activiation","2006-11-20","2007-01-03"]
["LN02100475","AVAIL: Data Comm Circuits Active & Ready","2007-01-04","2007-01-03"]
["LN021005","COMPUTERS & CRATES SUMMARY","2006-02-01","2006-07-18"]
["LN02100500","Finalize Specification Requirements - Computer","2006-02-01","2006-02-01"]
["LN02100502","Provide Hardware Engineer & Systems Integ Sup","2006-02-02","2006-06-09"]
["LN02100504","Design  VME Crates, Control & Support Modules","2006-02-02","2006-03-02"]
["LN02100506","COMP: Computers & Crates Design","2006-03-03","2006-03-02"]
["LN02100510","Prep Bid Pak - VME Crates/IOCs/Interface Chassis","2006-03-03","2006-03-09"]
["LN02100512","RELEASE: RFP - VME Crates/IOCs/Interface Chassis","2006-03-10","2006-03-09"]
["LN02100514","Vendors Prep Proposals - Cntrls Computers","2006-03-10","2006-03-16"]
["LN02100516","RCV: Proposl - VME Crates/IOCs/Interface Chassis","2006-03-17","2006-03-16"]
["LN02100518","Evaluate Vendors Proposals","2006-03-17","2006-03-23"]
["LN02100520","AWARD: Contrct VME Crates/IOCs/Interface Chassis","2006-03-24","2006-03-24"]
["LN02100522","Vendor Fab/Assy VME Crates/IOCs/Interface Chssis","2006-03-27","2006-04-21"]
["LN02100524","RCV: VME Crates/IOC's/Interface Chassis (3VME-7","2006-04-24","2006-04-21"]
["LN02100530","Prep Bid Pak - VME Crates for BPMs","2006-03-03","2006-03-09"]
["LN02100532","RELEASE: RFP - VME Crates for BPMs","2006-03-10","2006-03-09"]
["LN02100534","Vendors Prep Proposals - VME Crates for BPMs","2006-03-10","2006-03-16"]
["LN02100536","RCV: Proposals - VME Crates for BPMs","2006-03-17","2006-03-16"]
["LN02100538","Evaluate Vendors Proposals","2006-03-17","2006-03-23"]
["LN02100540","AWARD: Contract - VME Crates for BPMs","2006-03-24","2006-03-24"]
["LN02100542","Vendor Fab & Assy - VME Crates for BPMs","2006-03-27","2006-04-21"]
["LN02100544","RCV: from Vendors VME Crates for BPMs","2006-04-24","2006-04-21"]
["LN02100550","Prep Bid Pak -VME Crates/Cntrl/Supt Chassis","2006-03-03","2006-03-09"]
["LN02100552","RELEASE: RFP -VME Crates/Cntrl/Supt Chassis","2006-03-10","2006-03-09"]
["LN02100554","Vendors Prep Proposals -VME Crates/Cntrl/Supt Ch","2006-03-10","2006-03-16"]
["LN02100556","RCV: Proposals -VME Crates/Cntrl/Supt Chassis","2006-03-17","2006-03-16"]
["LN02100558","Evaluate Vendors Proposals","2006-03-17","2006-03-23"]
["LN02100560","AWARD: Contract -VME Crates/Cntrl/Supt Chassis","2006-03-24","2006-03-24"]
["LN02100562","Vendor Fab & Assy -VME Crates/Cntrl/Supt Chassis","2006-03-27","2006-04-21"]
["LN02100564","RCV: VME Crates, Control & Support Chassis","2006-04-24","2006-04-21"]
["LN02100620","Procure Cableplant","2006-03-03","2006-03-30"]
["LN02100625","RCV: Cableplant","2006-03-31","2006-03-30"]
["LN02100630","Procure VME System I/O Distribution Cableplant","2006-03-03","2006-03-30"]
["LN02100635","RCV: VME System Intra-Rack Dist I/O General Cab","2006-03-31","2006-03-30"]
["LN02100640","Assemble and Integrate Equipment","2006-04-24","2006-06-05"]
["LN02100645","Conduct Pre-Install Testing","2006-06-06","2006-07-18"]
["LN02100650","AVAIL: Computers & Crates Ready","2006-07-19","2006-07-18"]
["LN03","LINAC MAGNETS AND SUPPORTS SUMMARY","2005-03-01","2007-08-06",null,"2005-03-01"]
["LN0301","BEND MAGNET (BX1_BC1) SUMMARY","2005-09-15","2006-07-24",null,"2005-09-15"]
["LN03010005","Create ICD & Update LCLS Database","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["LN03010010","Review/Accept Reqmts, Update ICD & DB entries","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["LN03010025","Develop Preliminary Dsn - Magnet Field Analysis","2005-09-15","2005-09-30",null,"2005-09-15","2005-09-30"]
["LN03010030","Conduct Preliminary Design Review (PDR)","2005-09-15","2005-09-30",null,"2005-09-15","2005-09-30"]
["LN03010040","Develop Final Design - Magnets","2005-09-15","2005-09-30",null,"2005-09-15","2005-09-30"]
["LN03010050","Conduct Final Design Review (FDR)","2005-09-15","2005-09-30",null,"2005-09-15","2005-09-30"]
["LN03010060","Develop Magnetic Measurement Plan","2005-09-15","2005-09-30",null,"2005-09-15","2005-09-30"]
["LN03010065","COMP: Bend Magnet (BX1_BC1) Design","2005-10-01","2005-09-30",null,"2005-10-01","2005-09-30"]
["LN03010070","Prep Bid Pak - Magnets","2005-09-15","2005-09-30",null,"2005-09-15","2005-09-30"]
["LN03010080","RELEASE: RFP - BX1_BC1 Bend Magnet","2005-10-01","2005-09-30",null,"2005-10-01","2005-09-30"]
["LN03010085","Vendors Prep Proposals - Magnets","2006-02-01","2006-02-15"]
["LN03010090","RCV: Proposals from Vendors - Magnet","2006-02-01","2006-01-31"]
["LN03010095","Evaluate Vendor Proposals - Magnets","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03010100","AWARD: Contract for Magnets","2006-02-01","2006-02-01"]
["LN03010105","Vendor Fab BX1 Magnets","2006-02-02","2006-06-15"]
["LN03010110","RCV: BX1 Magnets from Vendor","2006-06-16","2006-06-16"]
["LN03010120","QA BX1 Magnet","2006-06-19","2006-07-17"]
["LN03010235","Perform Magnet Pre-Instlation Qual","2006-07-18","2006-07-24"]
["LN03010240","AVAIL: BX1_BC1 Magnets Ready for Instl","2006-07-25","2006-07-24"]
["LN03010500","Procure Coils (2ea) - Bend Mag (BX1_BC1) SPARES","2006-10-03","2006-11-29"]
["LN03010550","RCV: Bend Magnet Coils (2ea) (BX1_BC1) SPARES","2006-11-30","2006-11-29"]
["LN0302","Bend Magnet (BX3_LTU) SUMMARY","2006-01-01","2007-07-24",null,"2006-01-01"]
["LN03020000","Define Magnet Requirements","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN03020005","Create ICD & Update LCLS Database","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN03020010","Review/Accept Reqmts, Update ICD & DB entries","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN03020015","Develop Preliminary Design - Magnet","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN03020025","Develop Preliminary Dsn - Magnet Field Analysis","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN03020030","Conduct Preliminary Design Review (PDR)","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN03020040","Develop Final Design - Magnets","2006-02-01","2006-02-02"]
["LN03020050","Conduct Final Design Review (FDR)","2006-02-03","2006-02-06"]
["LN03020060","Develop Magnetic Measurement Plan","2006-02-07","2006-02-07"]
["LN03020065","COMP: Bend Magnet (BX3_LTU) Design","2006-02-08","2006-02-07"]
["LN03020070","Prep Bid Pak - Magnets","2006-02-01","2006-05-01"]
["LN03020080","RELEASE: ESD - BX3_LTU_( ) Bend Magnet","2006-05-02","2006-05-01"]
["LN03020130","Procure Misc Materials - Magnets","2006-05-02","2006-07-12"]
["LN03020135","Disassemble Magnet","2006-07-13","2006-08-16"]
["LN03020145","Refurbish Magnet Coils","2006-08-17","2006-09-21"]
["LN03020150","Assemble Magnets","2006-09-22","2006-11-20"]
["LN03020160","Prep for and Paint Magnets (as required)","2006-11-21","2007-01-11"]
["LN03020165","Perform Magnet Fiducialization (as required)","2007-01-12","2007-01-11"]
["LN03020170","Perform QC & Inspection - Magnets","2007-01-12","2007-01-11"]
["LN03020175","Perform Magnetic Measurement (as required)","2007-01-12","2007-02-09"]
["LN03020235","Perform Magnet Pre-Instlation Qual","2007-02-12","2007-02-13"]
["LN03020240","AVAIL: BX3_LTU Magnets Ready for Instl","2007-02-14","2007-02-13"]
["LN03020245","Define Magnet Support Requirements","2006-02-01","2006-02-02"]
["LN03020250","Create ICD & Update LCLS Database","2006-02-03","2006-02-03"]
["LN03020255","Review/Accept Reqmts, Update ICD & DB entries","2006-02-06","2006-02-06"]
["LN03020260","Develop Preliminary Design - Magnet Supports","2006-02-07","2006-02-14"]
["LN03020270","Conduct Preliminary Design Review (PDR)","2006-02-15","2006-02-16"]
["LN03020280","Develop Final Design - Magnet Supports","2006-02-17","2006-02-23"]
["LN03020290","Conduct Final Design Review (FDR)","2006-02-24","2006-02-27"]
["LN03020300","COMP: Bend Magnet Supports (BX3_LTU) Design","2006-02-28","2006-02-27"]
["LN03020305","Prep Bid Pak - Magnet Supports","2006-02-28","2006-03-20"]
["LN03020315","RELEASE: RFP - Magnet Supports","2006-03-21","2006-03-20"]
["LN03020320","Vendors Prep Proposals - Magnet Supts","2006-03-21","2006-04-10"]
["LN03020325","RCV: Proposals from Vendors - Supts","2006-04-11","2006-04-10"]
["LN03020330","Evaluate Vendor Proposals - Supports","2006-04-11","2006-04-12"]
["LN03020335","AWARD: Contract for Supts","2006-04-13","2006-04-13"]
["LN03020340","Vendor Fab 1st Lot - Supts","2006-04-14","2007-06-01"]
["LN03020345","RCV: 1st Lot Magnet Supports from Vendor","2007-06-04","2007-06-04"]
["LN03020350","Vendor Fab Remaining Lot - Supts","2007-06-05","2007-06-04"]
["LN03020355","RCV: Remaining Magnet Supts from Vendor","2007-06-05","2007-06-04"]
["LN03020360","Procure Misc Materials - Magnet Supports","2006-02-28","2006-03-27"]
["LN03020365","Fabricate Magnet Supports","2006-03-28","2006-04-04"]
["LN03020370","Prep for, Clean & Plate Magnet Supts","2006-04-05","2006-04-04"]
["LN03020375","Prep for and Paint Magnet Supports (as required)","2006-04-05","2006-04-04"]
["LN03020380","Perform QC & Inspection on Magnets Supts","2006-04-05","2006-04-12"]
["LN03020385","Assemble Magnet Supports","2006-04-13","2006-05-16"]
["LN03020390","Hand-off to Pre-Instl Qual Testing","2007-06-05","2007-06-04"]
["LN03020395","Perform Pre-Installation Qualification - Support","2007-06-05","2007-07-24"]
["LN03020400","AVAIL: BX3_LTU Magnet Supts Ready for Instl","2007-07-25","2007-07-24"]
["LN03020500","Procure Coils (2ea) - Bend Mag (BX3_LTU) SPARES","2007-07-25","2007-09-19"]
["LN03020550","RCV: Bend Magnet Coils (2ea) (BX3_LTU) SPARES","2007-09-20","2007-09-19"]
["LN03020600","Receive & Review Safety Cover Requirements","2006-02-28","2006-03-06"]
["LN03020605","Develop Magnet Safety Cover Design","2006-03-07","2006-05-01"]
["LN03020610","COMP: Magnet Safety Design","2006-05-02","2006-05-01"]
["LN03020615","Procure Magnet Safety Cover Material","2006-10-03","2006-10-02"]
["LN03020620","RCV: Magnet Safety Cover Material","2006-10-03","2006-10-02"]
["LN03020625","Fab and Assemble New Magnet Safety Covers (0ea)","2006-10-03","2006-10-02"]
["LN03020630","REQD: Reusable Safety Covers for Refurbishment","2006-10-03","2006-10-02"]
["LN03020635","Refurbish Reusable Safety Covers (5ea)","2006-10-03","2007-04-09"]
["LN03020640","AVAIL: Magnet Safety Covers Ready for Instl","2007-04-10","2007-04-09"]
["LN0303","BEND MAGNET (BX2_BC2) SUMMARY","2005-09-15","2007-01-10",null,"2005-09-15"]
["LN03030005","Create ICD & Update LCLS Database","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["LN03030010","Review/Accept Reqmts, Update ICD & DB entries","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["LN03030025","Develop Preliminary Dsn - Magnet Field Analysis","2005-09-15","2005-09-30",null,"2005-09-15","2005-09-30"]
["LN03030030","Conduct Preliminary Design Review (PDR)","2005-09-15","2005-09-30",null,"2005-09-15","2005-09-30"]
["LN03030040","Develop Final Design - Magnets","2005-09-15","2005-09-30",null,"2005-09-15","2005-09-30"]
["LN03030050","Conduct Final Design Review (FDR)","2005-09-15","2005-09-30",null,"2005-09-15","2005-09-30"]
["LN03030060","Develop Magnetic Measurement Plan","2005-09-15","2005-09-30",null,"2005-09-15","2005-09-30"]
["LN03030065","COMP: Bend Magnet (BX2_BC2) Design","2005-12-31","2005-12-30",null,"2005-12-31","2005-12-30"]
["LN03030070","Prep Bid Pak - Magnets","2005-10-17","2005-10-14",null,"2005-10-17","2005-10-14"]
["LN03030080","RELEASE: RFP - BX2_BC2 Bend Magnet","2005-12-31","2005-12-30",null,"2005-12-31","2005-12-30"]
["LN03030085","Vendors Prep Proposals - Magnets","2005-12-30","2006-02-28",null,"2005-12-30"]
["LN03030090","RCV: Proposals from Vendors - Magnet","2006-03-01","2006-02-28"]
["LN03030095","Evaluate Vendor Proposals - Magnets","2006-03-01","2006-03-07"]
["LN03030100","AWARD: Contract for Magnets","2006-03-08","2006-03-09"]
["LN03030105","Vendor Fab 1st Lot - Magnets","2006-03-10","2007-01-05"]
["LN03030110","RCV: 1st Lot Magnets from Vendor","2007-01-08","2007-01-08"]
["LN03030115","Vendor Fab Remaining Lot - Magnets","2007-01-09","2007-01-08"]
["LN03030120","RCV: Remaining Magnets from Vendor","2007-01-09","2007-01-08"]
["LN03030235","Perform Magnet Pre-Instlation Qual","2007-01-09","2007-01-10"]
["LN03030240","AVAIL: BX2_BC2 Magnets Ready for Instl","2007-01-11","2007-01-10"]
["LN03030500","Procure Coils (2ea) - Bend Mag (BX2_BC2) SPARES","2007-01-11","2007-03-09"]
["LN03030550","RCV: Bend Magnet Coils (BX2_BC2) Spares Kit","2007-03-12","2007-03-09"]
["LN0304","BEND MAGNET (BY_LTU) SUMMARY","2005-03-01","2007-02-12",null,"2005-03-01"]
["LN03040000","Define Magnet Requirements","2005-03-01","2005-03-01",null,"2005-03-01","2005-03-01"]
["LN03040005","Create ICD & Update LCLS Database","2006-02-01","2006-02-14"]
["LN03040010","Review/Accept Reqmts, Update ICD & DB entries","2006-02-01","2006-02-02"]
["LN03040015","Develop Preliminary Design - Magnet","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN03040025","Develop Preliminary Dsn - Magnet Field Analysis","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN03040030","Conduct Preliminary Design Review (PDR)","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN03040040","Develop Final Design - Magnets","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN03040050","Conduct Final Design Review (FDR)","2006-02-01","2006-02-02"]
["LN03040060","Develop Magnetic Measurement Plan","2006-02-03","2006-02-16"]
["LN03040065","COMP: Bend Magnet (BY_LTU) Design","2006-02-17","2006-02-16"]
["LN03040070","Prep Bid Pak - Magnets","2005-10-14","2005-10-14",null,"2005-10-14","2005-10-14"]
["LN03040080","RELEASE: RFP - BY_LTU Bend Magnet","2005-12-02","2005-12-01",null,"2005-12-02","2005-12-01"]
["LN03040085","Vendors Prep Proposals - Magnets","2006-02-01","2006-02-01"]
["LN03040090","RCV: Proposals from Vendors - Magnet","2006-02-02","2006-02-01"]
["LN03040095","Evaluate Vendor Proposals - Magnets","2006-02-02","2006-03-02"]
["LN03040100","AWARD: Contract for Magnets","2006-03-03","2006-03-06"]
["LN03040105","Vendor Fab 1st Lot - Magnets","2006-03-07","2007-01-05"]
["LN03040110","RCV: 1st Lot Magnets from Vendor","2007-01-08","2007-01-08"]
["LN03040115","Vendor Fab Remaining Lot - Magnets","2007-01-09","2007-01-08"]
["LN03040120","RCV: Remaining Magnets from Vendor","2007-01-09","2007-01-08"]
["LN03040230","Hand-off to Pre-Instl Qual Testing","2007-01-09","2007-01-08"]
["LN03040235","Perform Magnet Pre-Instlation Qual","2007-01-09","2007-02-06"]
["LN03040240","AVAIL: BY_LTU Magnets Ready for Instl","2007-02-07","2007-02-06"]
["LN03040245","Define Magnet Support Requirements","2006-10-02","2006-10-03"]
["LN03040250","Create ICD & Update LCLS Database","2006-10-04","2006-10-04"]
["LN03040255","Review/Accept Reqmts, Update ICD & DB entries","2006-10-05","2006-10-05"]
["LN03040260","Develop Preliminary Design - Magnet Supports","2006-10-06","2006-10-13"]
["LN03040270","Conduct Preliminary Design Review (PDR)","2006-10-16","2006-10-17"]
["LN03040280","Develop Final Design - Magnet Supports","2006-10-18","2006-10-23"]
["LN03040290","Conduct Final Design Review (FDR)","2006-10-24","2006-10-25"]
["LN03040300","COMP: Bend Magnet Supports (BY_LTU) Design","2006-10-26","2006-10-25"]
["LN03040305","Prep Bid Pak - Magnet Supports","2006-02-01","2006-02-01"]
["LN03040315","RELEASE: RFP - Magnet Supports","2006-02-02","2006-02-01"]
["LN03040320","Vendors Prep Proposals - Magnet Supts","2006-02-02","2006-02-02"]
["LN03040325","RCV: Proposals from Vendors - Supts","2006-02-03","2006-02-02"]
["LN03040330","Evaluate Vendor Proposals - Supports","2006-02-03","2006-02-03"]
["LN03040335","AWARD: Contract for Supts","2006-03-07","2006-03-07"]
["LN03040340","Vendor Fab 1st Lot - Supts","2006-03-08","2006-04-04"]
["LN03040345","RCV: 1st Lot Magnet Supports from Vendor","2007-01-09","2007-01-09"]
["LN03040350","Vendor Fab Remaining Lot - Supts","2007-01-10","2007-01-09"]
["LN03040355","RCV: Remaining Magnet Supts from Vendor","2007-01-10","2007-01-09"]
["LN03040360","Procure Misc Materials - Magnet Supports","2006-10-26","2006-11-22"]
["LN03040365","Fabricate Magnet Supports","2006-11-27","2006-12-04"]
["LN03040370","Prep for, Clean & Plate Magnet Supts","2006-12-05","2006-12-04"]
["LN03040375","Prep for and Paint Magnet Supports (as required)","2006-12-05","2006-12-04"]
["LN03040380","Perform QC & Inspection on Magnets Supts","2007-01-10","2007-01-18"]
["LN03040385","Assemble Magnet Supports","2007-01-19","2007-02-08"]
["LN03040390","Hand-off to Pre-Instl Qual Testing","2007-02-09","2007-02-08"]
["LN03040395","Perform Pre-Installation Qualification - Support","2007-02-09","2007-02-12"]
["LN03040400","AVAIL: BY_LTU Magnet Supts Ready for Instl","2007-02-13","2007-02-12"]
["LN03040500","Procure Coil (1ea) - Bend Mag (BY_LTU) SPARES","2007-02-13","2007-04-10"]
["LN03040550","RCV: Bend Magnet Coil (1ea) (BY_LTU) SPARES","2007-04-11","2007-04-10"]
["LN0305","QUAD MAGNET (Quad_LTU) SUMMARY","2005-10-03","2007-07-05",null,"2005-10-03"]
["LN03050000","Define Magnet Requirements","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03050005","Create ICD & Update LCLS Database","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03050010","Review/Accept Reqmts, Update ICD & DB entries","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03050015","Develop Preliminary Design - Magnet","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03050025","Develop Preliminary Dsn - Magnet Field Analysis","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03050030","Conduct Preliminary Design Review (PDR)","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03050040","Develop Final Design - Magnets","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03050050","Conduct Final Design Review (FDR)","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03050060","Develop Magnetic Measurement Plan","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03050065","COMP: Quad Magnet (Quad_LTU) Design","2005-12-31","2005-12-30",null,"2005-12-31","2005-12-30"]
["LN03050070","Prep Bid Pak - Magnets","2005-10-03","2005-10-14",null,"2005-10-03","2005-10-14"]
["LN03050080","RELEASE: RFP - Quad_LTU Magnet","2005-12-02","2005-12-01",null,"2005-12-02","2005-12-01"]
["LN03050085","Vendors Prep Proposals - Magnets","2006-02-01","2006-02-15"]
["LN03050090","RCV: Proposals from Vendors - Magnet","2006-02-16","2006-02-15"]
["LN03050095","Evaluate Vendor Proposals - Magnets","2006-02-16","2006-02-16"]
["LN03050100","AWARD: Contract for Magnets","2006-02-17","2006-02-21"]
["LN03050105","Vendor Fab 1st Lot - Magnets","2006-02-22","2007-06-01"]
["LN03050110","RCV: 1st Lot Magnets from Vendor","2007-06-04","2007-06-04"]
["LN03050115","Vendor Fab Remaining Lot - Magnets","2007-06-05","2007-06-04"]
["LN03050120","RCV: Remaining Magnets from Vendor","2007-06-05","2007-06-04"]
["LN03050125","Hand-off to Pre-Instl Qual Testing","2007-06-05","2007-06-04"]
["LN03050130","Procure Misc Materials - Magnets","2006-02-22","2007-01-03"]
["LN03050135","Disassemble Magnet","2007-01-04","2007-02-01"]
["LN03050145","Refurbish Magnet Coils","2007-02-02","2007-03-02"]
["LN03050150","Assemble Magnets","2007-03-05","2007-03-30"]
["LN03050160","Prep for and Paint Magnets (as required)","2007-04-02","2007-04-27"]
["LN03050165","Perform Magnet Fiducialization (as required)","2007-04-30","2007-05-04"]
["LN03050170","Perform QC & Inspection - Magnets","2007-05-07","2007-05-11"]
["LN03050175","Perform Magnetic Measurement (as required)","2007-05-14","2007-05-25"]
["LN03050235","Perform Magnet Pre-Instlation Qual","2007-06-05","2007-06-06"]
["LN03050240","AVAIL: Quad_LTU Magnets Ready for Instl","2007-06-07","2007-06-06"]
["LN03050245","Define Magnet Support Requirements","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03050250","Create ICD & Update LCLS Database","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03050255","Review/Accept Reqmts, Update ICD & DB entries","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03050260","Develop Preliminary Design - Magnet Supports","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03050270","Conduct Preliminary Design Review (PDR)","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03050280","Develop Final Design - Magnet Supports","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03050290","Conduct Final Design Review (FDR)","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03050300","COMP: Quad Magnet Supports (Quad_LTU) Design","2005-12-31","2005-12-30",null,"2005-12-31","2005-12-30"]
["LN03050305","Prep Bid Pak - Magnet Supports","2006-02-01","2006-02-14"]
["LN03050315","RELEASE: RFP - Magnet Supports","2006-02-15","2006-02-14"]
["LN03050320","Vendors Prep Proposals - Magnet Supts","2006-02-15","2006-03-15"]
["LN03050325","RCV: Proposals from Vendors - Supts","2006-03-16","2006-03-15"]
["LN03050330","Evaluate Vendor Proposals - Supports","2006-03-16","2006-04-12"]
["LN03050335","AWARD: Contract for Supts","2006-04-13","2006-04-14"]
["LN03050340","Vendor Fab 1st Lot - Supts","2006-04-17","2007-06-01"]
["LN03050345","RCV: 1st Lot Magnet Supports from Vendor","2007-06-04","2007-06-04"]
["LN03050350","Vendor Fab Remaining Lot - Supts","2007-06-05","2007-06-04"]
["LN03050355","RCV: Remaining Magnet Supts from Vendor","2007-06-05","2007-06-04"]
["LN03050360","Procure Misc Materials - Magnet Supports","2006-10-03","2006-10-30"]
["LN03050365","Fabricate Magnet Supports","2006-10-31","2006-12-13"]
["LN03050370","Prep for, Clean & Plate Magnet Supts","2006-12-14","2006-12-13"]
["LN03050375","Prep for and Paint Magnet Supports (as required)","2006-12-14","2006-12-13"]
["LN03050380","Perform QC & Inspection on Magnets Supts","2006-12-14","2007-02-09"]
["LN03050385","Assemble Magnet Supports","2007-02-12","2007-05-09"]
["LN03050390","Hand-off to Pre-Instl Qual Testing","2007-05-10","2007-05-09"]
["LN03050395","Perform Pre-Installation Qualification - Support","2007-06-05","2007-06-12"]
["LN03050400","AVAIL: Quad_LTU Magnet Supts Ready for Instl","2007-06-13","2007-06-12"]
["LN03050500","Procure Coil (4ea) - Quad Mag (Quad_LTU) SPARES","2007-06-13","2007-08-08"]
["LN03050550","RCV: Quad Magnet Coil (4ea) (Quad_LTU) SPARES","2007-08-09","2007-08-08"]
["LN03050600","Receive & Review Safety Cover Requirements","2006-02-01","2006-01-31"]
["LN03050605","Develop Magnet Safety Cover Design","2006-02-01","2006-03-29"]
["LN03050610","COMP: Magnet Safety Design","2006-03-30","2006-03-29"]
["LN03050615","Prep Bid Pak - Magnet Safety Covers","2006-03-30","2006-04-05"]
["LN03050620","RELEASE: RFP - Magnet Safety Covers","2006-04-06","2006-04-05"]
["LN03050625","Vendors Prep Proposals - Magnet Safety Covers","2006-04-06","2006-04-19"]
["LN03050630","RCV: Vendor Proposals - Magnet Safety Covers","2006-04-20","2006-04-19"]
["LN03050635","Evaluate Vendor Proposals","2006-04-20","2006-04-26"]
["LN03050700","AWARD: Contract - Magnet Safety Covers","2006-10-03","2006-10-03"]
["LN03050705","Vendor Fab & Assy - Magnet Safety Cover (15ea)","2006-10-04","2007-03-13"]
["LN03050710","RCV: Magnet Safety Cover Material","2007-03-14","2007-03-13"]
["LN03050715","Fab and Assemble New Magnet Safety Covers (0ea)","2007-03-14","2007-03-13"]
["LN03050720","REQD: Reusable Safety Covers for Refurbishment","2007-03-14","2007-03-13"]
["LN03050725","Refurbish Reusable Safety Covers (25ea)","2007-03-14","2007-07-05"]
["LN03050730","AVAIL: Magnet Safety Covers Ready for Instl","2007-07-06","2007-07-05"]
["LN0307","QUAD MAGNET (QE_ ) SUMMARY","2005-09-15","2007-08-02",null,"2005-09-15"]
["LN03070005","Create ICD & Update LCLS Database","2005-09-15","2005-09-30",null,"2005-09-15","2005-09-30"]
["LN03070010","Review/Accept Reqmts, Update ICD & DB entries","2005-09-15","2005-09-30",null,"2005-09-15","2005-09-30"]
["LN03070060","Develop Magnetic Measurement Plan","2005-09-15","2005-09-30",null,"2005-09-15","2005-09-30"]
["LN03070065","COMP: Quad Magnet (QE_ Quad) Design","2005-10-01","2005-09-30",null,"2005-10-01","2005-09-30"]
["LN03070180","Procure Misc Materials - Magnets","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03070185","Fab Tooling","2006-02-01","2006-03-08"]
["LN03070190","Fab Magnet Core","2006-02-01","2006-03-01"]
["LN03070195","Fab Magnet Coils","2006-02-01","2007-01-05"]
["LN03070205","Prep for and Paint Magnets (as required)","2007-01-08","2007-01-22"]
["LN03070210","Assemble Magnets","2007-01-23","2007-02-20"]
["LN03070215","Perform Magnet Fiducialization (as required)","2007-02-21","2007-03-06"]
["LN03070220","Perform QC & Inspection - Magnets","2007-03-07","2007-03-20"]
["LN03070225","Perform Magnetic Measurement (as required)","2007-03-21","2007-04-03"]
["LN03070230","Hand-off to Pre-Instl Qual Testing","2007-04-04","2007-04-03"]
["LN03070235","Perform Magnet Pre-Instlation Qual","2007-04-04","2007-08-02"]
["LN03070240","AVAIL: ET_ Quad Magnet Ready for BC1 Instl","2006-02-01","2006-01-31"]
["LN03070242","AVAIL: QE_ Quad Magnet Ready for BC2 Instl","2007-08-03","2007-08-02"]
["LN03070245","Define Magnet Support Requirements","2006-02-01","2006-02-02"]
["LN03070250","Create ICD & Update LCLS Database","2006-02-03","2006-02-02"]
["LN03070255","Review/Accept Reqmts, Update ICD & DB entries","2006-02-03","2006-02-03"]
["LN03070260","Develop Preliminary Design - Magnet Supports","2006-02-06","2006-02-06"]
["LN03070270","Conduct Preliminary Design Review (PDR)","2006-02-07","2006-02-07"]
["LN03070280","Develop Final Design - Magnet Supports","2006-02-08","2006-02-08"]
["LN03070290","Conduct Final Design Review (FDR)","2006-02-09","2006-02-09"]
["LN03070300","COMP: Quad Magnet Supports (QE_ Quad) Design","2006-02-10","2006-02-09"]
["LN03070305","Prep Bid Pak - Magnet Supports","2006-02-10","2006-02-10"]
["LN03070315","RELEASE: RFP - Magnet Supports","2006-02-13","2006-02-10"]
["LN03070320","Vendors Prep Proposals - Magnet Supts","2006-02-13","2006-02-13"]
["LN03070325","RCV: Proposals from Vendors - Supts","2006-02-14","2006-02-13"]
["LN03070330","Evaluate Vendor Proposals - Supports","2006-02-14","2006-02-13"]
["LN03070335","AWARD: Contract for Supts","2006-02-14","2006-02-14"]
["LN03070340","Vendor Fab 1st Lot - Supts","2006-02-15","2006-02-14"]
["LN03070345","RCV: 1st Lot Magnet Supports from Vendor","2006-02-15","2006-02-14"]
["LN03070350","Vendor Fab Remaining Lot - Supts","2006-02-15","2006-02-14"]
["LN03070355","RCV: Remaining Magnet Supts from Vendor","2006-02-15","2006-02-14"]
["LN03070360","Procure Misc Materials - Magnet Supports","2006-02-10","2006-02-09"]
["LN03070365","Fabricate Magnet Supports","2006-02-10","2006-02-09"]
["LN03070370","Prep for, Clean & Plate Magnet Supts","2006-02-10","2006-02-09"]
["LN03070375","Prep for and Paint Magnet Supports (as required)","2006-02-10","2006-02-09"]
["LN03070380","Perform QC & Inspection on Magnets Supts","2006-02-10","2006-02-09"]
["LN03070385","Assemble Magnet Supports","2006-02-10","2006-02-09"]
["LN03070390","Hand-off to Pre-Instl Qual Testing","2006-02-10","2006-02-09"]
["LN03070395","Perform Pre-Installation Qualification - Support","2006-02-15","2006-02-14"]
["LN03070400","AVAIL: ET_ Quad Magnet Supts Ready for BC1 Instl","2006-02-15","2006-02-14"]
["LN03070402","AVAIL: QE_ Quad Magnet Supts Ready for BC2 Instl","2006-02-15","2006-02-14"]
["LN0308","CORRECTOR BEND MAGNET (Linac Type 4) SUMMARY","2005-06-15","2006-07-26",null,"2005-06-15"]
["LN03080005","Create ICD & Update LCLS Database","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["LN03080010","Review/Accept Reqmts, Update ICD & DB entries","2005-06-15","2005-09-30",null,"2005-06-15","2005-09-30"]
["LN03080015","Develop Preliminary Design - Magnet","2005-09-15","2005-09-30",null,"2005-09-15","2005-09-30"]
["LN03080025","Develop Preliminary Dsn - Magnet Field Analysis","2005-09-15","2005-09-30",null,"2005-09-15","2005-09-30"]
["LN03080030","Conduct Preliminary Design Review (PDR)","2005-09-15","2005-09-30",null,"2005-09-15","2005-09-30"]
["LN03080040","Develop Final Design - Magnets","2005-09-15","2005-09-30",null,"2005-09-15","2005-09-30"]
["LN03080050","Conduct Final Design Review (FDR)","2005-09-15","2005-09-30",null,"2005-09-15","2005-09-30"]
["LN03080060","Develop Magnetic Measurement Plan","2005-09-15","2005-09-30",null,"2005-09-15","2005-09-30"]
["LN03080065","COMP: Corrector Bend Magnet (Type 4) Design","2005-10-01","2005-09-30",null,"2005-10-01","2005-09-30"]
["LN03080070","Prep Bid Pak - Magnets","2006-02-01","2006-01-31"]
["LN03080080","RELEASE: RFP - Linac Type 4 Corrector Bend Magne","2006-02-01","2006-01-31"]
["LN03080085","Vendors Prep Proposals - Magnets","2006-02-01","2006-02-09"]
["LN03080090","RCV: Proposals from Vendors - Magnet","2006-02-10","2006-02-09"]
["LN03080095","Evaluate Vendor Proposals - Magnets","2006-02-10","2006-02-24"]
["LN03080100","AWARD: Contract for Magnets","2006-02-27","2006-03-01"]
["LN03080105","Vendor Fab 1st Lot - Magnets","2006-03-02","2006-06-01"]
["LN03080110","RCV: 1st Lot Magnets from Vendor","2006-06-02","2006-06-02"]
["LN03080115","Vendor Fab Remaining Lot - Magnets","2006-06-05","2006-06-02"]
["LN03080120","RCV: Remaining Magnets from Vendor","2006-06-05","2006-06-02"]
["LN03080125","Hand-off to Pre-Instl Qual Testing","2006-06-05","2006-06-02"]
["LN03080130","Procure Misc Materials - Magnets","2006-03-02","2006-03-29"]
["LN03080135","Disassemble Magnet","2006-03-30","2006-03-30"]
["LN03080145","Refurbish Magnet Coils","2006-03-31","2006-04-10"]
["LN03080150","Assemble Magnets","2006-04-11","2006-06-01"]
["LN03080160","Prep for and Paint Magnets (as required)","2006-06-02","2006-06-01"]
["LN03080165","Perform Magnet Fiducialization (as required)","2006-06-02","2006-06-01"]
["LN03080170","Perform QC & Inspection - Magnets","2006-06-02","2006-06-01"]
["LN03080175","Perform Magnetic Measurement (as required)","2006-06-02","2006-06-01"]
["LN03080180","Procure Misc Materials - Magnets","2006-03-02","2006-03-01"]
["LN03080185","Fab Tooling","2006-03-02","2006-03-01"]
["LN03080190","Fab Magnet Core","2006-03-02","2006-03-02"]
["LN03080195","Fab Magnet Coils","2006-03-03","2006-03-02"]
["LN03080205","Prep for and Paint Magnets (as required)","2006-03-03","2006-03-02"]
["LN03080210","Assemble Magnets","2006-03-03","2006-06-01"]
["LN03080215","Perform Magnet Fiducialization (as required)","2006-06-02","2006-06-01"]
["LN03080220","Perform QC & Inspection - Magnets","2006-06-02","2006-06-01"]
["LN03080225","Perform Magnetic Measurement (as required)","2006-06-02","2006-06-01"]
["LN03080230","Hand-off to Pre-Instl Qual Testing","2006-06-02","2006-06-01"]
["LN03080235","Perform Magnet Pre-Instlation Qual","2006-06-05","2006-07-03"]
["LN03080240","AVAIL: Type 4 Corr Bend Mag Ready for L01 Instl","2006-07-05","2006-07-03"]
["LN03080241","AVAIL: Type 4 Corr Bend Mag Ready for BC1 Instl","2006-07-05","2006-07-03"]
["LN03080242","AVAIL: Type 4 Corr Bend Mag Ready for L03 Instl","2006-07-05","2006-07-03"]
["LN03080605","Develop Magnet Safety Cover Design","2006-03-01","2006-03-28"]
["LN03080610","COMP: Magnet Safety Design","2006-03-29","2006-03-28"]
["LN03080615","Procure Magnet Safety Cover (42ea)","2006-03-29","2006-07-26"]
["LN03080620","RCV: Magnet Safety Cover (42ea)","2006-07-27","2006-07-26"]
["LN03080625","Fab and Assemble New Magnet Safety Covers (0ea)","2006-07-27","2006-07-26"]
["LN03080630","REQD: Reusable Safety Covers for Refurbishment","2006-07-27","2006-07-26"]
["LN03080635","Refurbish Reusable Safety Covers (0ea)","2006-07-27","2006-07-26"]
["LN03080640","AVAIL: Magnet Safety Covers Ready for Instl","2006-07-27","2006-07-26"]
["LN0309","BEND MAGNET (BYD_LTU) SUMMARY","2005-10-14","2007-08-01",null,"2005-10-14"]
["LN03090000","Define Magnet Requirements","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03090005","Create ICD & Update LCLS Database","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03090010","Review/Accept Reqmts, Update ICD & DB entries","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03090015","Develop Preliminary Design - Magnet","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03090025","Develop Preliminary Dsn - Magnet Field Analysis","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03090030","Conduct Preliminary Design Review (PDR)","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03090040","Develop Final Design - Magnets","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03090050","Conduct Final Design Review (FDR)","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03090060","Develop Magnetic Measurement Plan","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03090065","COMP: Quad Magnet (BYD_LTU) Design","2005-12-31","2005-12-30",null,"2005-12-31","2005-12-30"]
["LN03090070","Prep Bid Pak - Magnets","2005-10-14","2005-10-14",null,"2005-10-14","2005-10-14"]
["LN03090080","RELEASE: RFP -BYD_LTU Bend Magnet","2005-12-02","2005-12-01",null,"2005-12-02","2005-12-01"]
["LN03090085","Vendors Prep Proposals - Magnets","2006-02-01","2005-12-30",null,null,"2005-12-30"]
["LN03090090","RCV: Proposals from Vendors - Magnet","2005-12-31","2005-12-30",null,"2005-12-31","2005-12-30"]
["LN03090095","Evaluate Vendor Proposals - Magnets","2006-02-01","2005-12-30",null,null,"2005-12-30"]
["LN03090100","AWARD: Contract for Magnets","2006-06-01","2006-06-02"]
["LN03090105","Vendor Fab 1st Lot - Magnets","2006-06-05","2007-01-05"]
["LN03090110","RCV: 1st Lot Magnets from Vendor","2007-01-08","2007-01-08"]
["LN03090115","Vendor Fab Remaining Lot - Magnets","2007-01-09","2007-01-08"]
["LN03090120","RCV: Remaining Magnets from Vendor","2007-01-09","2007-01-08"]
["LN03090125","Hand-off to Pre-Instl Qual Testing","2007-01-09","2007-01-08"]
["LN03090130","Procure Misc Materials - Magnets","2006-06-05","2006-06-02"]
["LN03090135","Disassemble Magnet","2006-06-05","2006-06-05"]
["LN03090145","Refurbish Magnet Coils","2006-06-06","2006-06-06"]
["LN03090150","Assemble Magnets","2006-06-07","2007-01-05"]
["LN03090160","Prep for and Paint Magnets (as required)","2007-01-08","2007-01-05"]
["LN03090165","Perform Magnet Fiducialization (as required)","2007-01-08","2007-01-05"]
["LN03090170","Perform QC & Inspection - Magnets","2007-01-08","2007-01-05"]
["LN03090175","Perform Magnetic Measurement (as required)","2007-01-08","2007-01-05"]
["LN03090180","Procure Misc Materials - Magnets","2006-10-03","2006-10-02"]
["LN03090185","Fab Tooling","2006-10-03","2006-10-02"]
["LN03090190","Fab Magnet Core","2006-10-03","2006-10-02"]
["LN03090195","Fab Magnet Coils","2006-10-03","2006-10-02"]
["LN03090205","Prep for and Paint Magnets (as required)","2006-10-03","2006-10-02"]
["LN03090210","Assemble Magnets","2006-10-03","2006-10-02"]
["LN03090215","Perform Magnet Fiducialization (as required)","2006-10-03","2006-10-02"]
["LN03090220","Perform QC & Inspection - Magnets","2006-10-03","2006-10-02"]
["LN03090225","Perform Magnetic Measurement (as required)","2006-10-03","2006-10-02"]
["LN03090230","Hand-off to Pre-Instl Qual Testing","2007-01-08","2007-01-05"]
["LN03090235","Perform Magnet Pre-Instlation Qual","2007-01-09","2007-01-11"]
["LN03090240","AVAIL: BYD_LTU Bend Magnet Ready for Instl","2007-01-12","2007-01-11"]
["LN03090245","Define Magnet Support Requirements","2006-02-01","2006-02-03"]
["LN03090250","Create ICD & Update LCLS Database","2006-02-06","2006-02-06"]
["LN03090255","Review/Accept Reqmts, Update ICD & DB entries","2006-02-07","2006-02-07"]
["LN03090260","Develop Preliminary Design - Magnet Supports","2006-02-08","2006-02-08"]
["LN03090270","Conduct Preliminary Design Review (PDR)","2006-02-09","2006-02-09"]
["LN03090280","Develop Final Design - Magnet Supports","2006-02-10","2006-02-10"]
["LN03090290","Conduct Final Design Review (FDR)","2006-02-13","2006-02-13"]
["LN03090300","COMP: Bend Magnet Support (BYD_LTU ) Design","2006-02-14","2006-02-13"]
["LN03090305","Prep Bid Pak - Magnet Supports","2006-02-14","2006-02-14"]
["LN03090315","RELEASE: RFP - Magnet Supports","2006-02-15","2006-02-14"]
["LN03090320","Vendors Prep Proposals - Magnet Supts","2006-02-15","2006-03-15"]
["LN03090325","RCV: Proposals from Vendors - Supts","2006-03-16","2006-03-15"]
["LN03090330","Evaluate Vendor Proposals - Supports","2006-03-16","2006-04-12"]
["LN03090335","AWARD: Contract for Supts","2006-04-13","2006-04-14"]
["LN03090340","Vendor Fab 1st Lot - Supts","2006-04-17","2007-01-05"]
["LN03090345","RCV: 1st Lot Magnet Supports from Vendor","2007-01-08","2007-01-08"]
["LN03090350","Vendor Fab Remaining Lot - Supts","2007-01-09","2007-01-08"]
["LN03090355","RCV: Remaining Magnet Supts from Vendor","2007-01-09","2007-01-08"]
["LN03090360","Procure Misc Materials - Magnet Supports","2006-02-14","2006-03-14"]
["LN03090365","Fabricate Magnet Supports","2006-03-15","2006-03-27"]
["LN03090370","Prep for, Clean & Plate Magnet Supts","2006-03-28","2006-03-27"]
["LN03090375","Prep for and Paint Magnet Supports (as required)","2006-03-28","2006-03-27"]
["LN03090380","Perform QC & Inspection on Magnets Supts","2006-03-28","2006-04-07"]
["LN03090385","Assemble Magnet Supports","2006-04-10","2007-01-05"]
["LN03090390","Hand-off to Pre-Instl Qual Testing","2007-01-08","2007-01-05"]
["LN03090395","Perform Pre-Installation Qualification - Support","2007-01-09","2007-08-01"]
["LN03090400","AVAIL: BYD_LTU  Magnet Supts Ready for Instl","2007-08-02","2007-08-01"]
["LN03090500","Procure Coil (2ea) - Bend Mag (BYD_LTU) SPARES","2006-10-03","2006-11-29"]
["LN03090550","RCV: Bend Magnet Coil (2ea) (BYD_LTU) SPARES","2006-11-30","2006-11-29"]
["LN0310","QUAD MAGNET (QA_ ) SUMMARY","2005-09-15","2006-07-21",null,"2005-09-15"]
["LN03100000","Define Magnet Requirements","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["LN03100005","Create ICD & Update LCLS Database","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["LN03100010","Review/Accept Reqmts, Update ICD & DB entries","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["LN03100015","Develop Preliminary Design - Magnet","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["LN03100025","Develop Preliminary Dsn - Magnet Field Analysis","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["LN03100030","Conduct Preliminary Design Review (PDR)","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["LN03100040","Develop Final Design - Magnets","2005-09-15","2005-09-30",null,"2005-09-15","2005-09-30"]
["LN03100050","Conduct Final Design Review (FDR)","2005-09-15","2005-09-30",null,"2005-09-15","2005-09-30"]
["LN03100060","Develop Magnetic Measurement Plan","2005-09-15","2005-09-30",null,"2005-09-15","2005-09-30"]
["LN03100065","COMP: Quad Magnet (QA_ Quad) Design","2005-10-01","2005-09-30",null,"2005-10-01","2005-09-30"]
["LN03100070","Prep Bid Pak - Magnets","2005-09-30","2005-12-30",null,"2005-09-30","2005-12-30"]
["LN03100080","RELEASE: RFP - QA_ Quad Magnet","2006-02-01","2006-01-31"]
["LN03100085","Vendors Prep Proposals - Magnets","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03100090","RCV: Proposals from Vendors - Magnet","2005-12-31","2005-12-30",null,"2005-12-31","2005-12-30"]
["LN03100095","Evaluate Vendor Proposals - Magnets","2006-02-01","2005-12-30",null,null,"2005-12-30"]
["LN03100100","AWARD: Contract for Magnets","2006-02-13","2006-02-13"]
["LN03100105","Vendor Fab 1st Lot - Magnets","2006-02-14","2006-06-01"]
["LN03100110","RCV: 1st Lot Magnets from Vendor","2006-06-02","2006-06-01"]
["LN03100115","Vendor Fab Remaining Lot - Magnets","2006-06-02","2006-06-01"]
["LN03100120","RCV: Remaining Magnets from Vendor","2006-06-02","2006-06-01"]
["LN03100125","Hand-off to Pre-Instl Qual Testing","2006-06-02","2006-06-01"]
["LN03100130","Procure Misc Materials - Magnets","2006-02-14","2006-03-14"]
["LN03100135","Disassemble Magnet","2006-03-15","2006-03-15"]
["LN03100145","Refurbish Magnet Coils","2006-03-16","2006-03-16"]
["LN03100150","Assemble Magnets","2006-03-17","2006-05-30"]
["LN03100160","Prep for and Paint Magnets (as required)","2006-05-31","2006-05-30"]
["LN03100165","Perform Magnet Fiducialization (as required)","2006-05-31","2006-05-30"]
["LN03100170","Perform QC & Inspection - Magnets","2006-05-31","2006-05-30"]
["LN03100175","Perform Magnetic Measurement (as required)","2006-05-31","2006-06-27"]
["LN03100230","Hand-off to Pre-Instl Qual Testing","2006-06-28","2006-06-27"]
["LN03100235","Perform Magnet Pre-Instlation Qual","2006-06-02","2006-07-14"]
["LN03100240","AVAIL: TWKR_Quad Mags Ready for BC1 Instl","2006-07-17","2006-07-14"]
["LN03100241","AVAIL: QA_ Quad Magnets Ready for BC2 Instl","2006-07-17","2006-07-14"]
["LN03100245","Define Magnet Support Requirements","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03100250","Create ICD & Update LCLS Database","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03100255","Review/Accept Reqmts, Update ICD & DB entries","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03100260","Develop Preliminary Design - Magnet Supports","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03100270","Conduct Preliminary Design Review (PDR)","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03100280","Develop Final Design - Magnet Supports","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03100290","Conduct Final Design Review (FDR)","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03100300","COMP: Quad Magnet Supports (QA_ Quad) Design","2005-12-31","2005-12-30",null,"2005-12-31","2005-12-30"]
["LN03100305","Prep Bid Pak - Magnet Supports","2006-02-01","2006-02-14"]
["LN03100315","RELEASE: RFP - Magnet Supports","2006-02-15","2006-02-14"]
["LN03100320","Vendors Prep Proposals - Magnet Supts","2006-02-15","2006-03-08"]
["LN03100325","RCV: Proposals from Vendors - Supts","2006-03-09","2006-03-08"]
["LN03100330","Evaluate Vendor Proposals - Supports","2006-03-09","2006-03-29"]
["LN03100335","AWARD: Contract for Supts","2006-03-30","2006-03-30"]
["LN03100340","Vendor Fab 1st Lot - Supts","2006-03-31","2006-06-01"]
["LN03100345","RCV: 1st Lot Magnet Supports from Vendor","2006-06-02","2006-06-01"]
["LN03100350","Vendor Fab Remaining Lot - Supts","2006-06-02","2006-06-01"]
["LN03100355","RCV: Remaining Magnet Supts from Vendor","2006-06-02","2006-06-01"]
["LN03100360","Procure Misc Materials - Magnet Supports","2006-02-01","2006-03-01"]
["LN03100365","Fabricate Magnet Supports","2006-03-02","2006-03-01"]
["LN03100370","Prep for, Clean & Plate Magnet Supts","2006-03-02","2006-03-01"]
["LN03100375","Prep for and Paint Magnet Supports (as required)","2006-03-02","2006-03-01"]
["LN03100380","Perform QC & Inspection on Magnets Supts","2006-03-02","2006-03-01"]
["LN03100385","Assemble Magnet Supports","2006-03-02","2006-06-01"]
["LN03100390","Hand-off to Pre-Instl Qual Testing","2006-06-02","2006-06-01"]
["LN03100395","Perform Pre-Installation Qualification - Support","2006-06-02","2006-07-21"]
["LN03100400","AVAIL: TWKR_ Quad Mag Supts Ready for BC1 Instl","2006-07-24","2006-07-21"]
["LN03100401","AVAIL: QA_ Quad Magnet Supts Ready for BC2 Instl","2006-07-24","2006-07-21"]
["LN0311","BEND MAGNET (BYPM_LTU) SUMMARY","2005-12-01","2007-07-26",null,"2005-12-01"]
["LN03110000","Define Magnet Requirements","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03110005","Create ICD & Update LCLS Database","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03110010","Review/Accept Reqmts, Update ICD & DB entries","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03110015","Develop Preliminary Design - Magnet","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03110025","Develop Preliminary Dsn - Magnet Field Analysis","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03110030","Conduct Preliminary Design Review (PDR)","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03110040","Develop Final Design - Magnets","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03110050","Conduct Final Design Review (FDR)","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03110060","Develop Magnetic Measurement Plan","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03110065","COMP: Bend Magnet (BYMP_LTU) Design","2005-12-31","2005-12-30",null,"2005-12-31","2005-12-30"]
["LN03110070","Prep Bid Pak - Magnets","2006-04-03","2006-04-03"]
["LN03110080","RELEASE: RFP - BYMP_LTU Bend Magnet","2006-04-04","2006-04-03"]
["LN03110085","Vendors Prep Proposals - Magnets","2006-04-04","2006-04-24"]
["LN03110090","RCV: Proposals from Vendors - Magnet","2006-04-25","2006-04-24"]
["LN03110095","Evaluate Vendor Proposals - Magnets","2006-04-25","2006-05-15"]
["LN03110100","AWARD: Contract for Magnets","2006-05-16","2006-05-16"]
["LN03110105","Vendor Fab 1st Lot - Magnets","2006-05-17","2007-06-01"]
["LN03110110","RCV: 1st Lot Magnets from Vendor","2007-06-04","2007-06-01"]
["LN03110115","Vendor Fab Remaining Lot - Magnets","2007-06-04","2007-06-01"]
["LN03110120","RCV: Remaining Magnets from Vendor","2007-06-04","2007-06-01"]
["LN03110125","Hand-off to Pre-Instl Qual Testing","2007-06-04","2007-06-01"]
["LN03110170","Prep Bid Pak - Misc Materials - Magnets","2006-03-28","2006-04-03"]
["LN03110172","RELEASE: RFP  - Misc Materials - Magnets","2006-04-04","2006-04-03"]
["LN03110174","Vendors Prep Proposals - Misc Mtrls - Magnets","2006-04-04","2006-04-24"]
["LN03110176","RCV: Vendor Proposals - Misc Materials - Magnets","2006-04-25","2006-04-24"]
["LN03110178","Evaluate Vendor Proposals - Misc Mtrls - Magnets","2006-04-25","2006-05-15"]
["LN03110180","AWARD: Contract - Misc Materials - Magnets","2006-05-16","2006-05-16"]
["LN03110182","Vendor Fab & Assy - Misc Materials - Magnets","2006-05-17","2007-06-01"]
["LN03110184","RCV: from Vendor  - Misc Materials - Magnets","2007-06-04","2007-06-04"]
["LN03110190","Fab Tooling","2007-06-05","2007-06-11"]
["LN03110192","Fab Magnet Core","2007-06-12","2007-06-18"]
["LN03110194","Fab Magnet Coils","2007-06-19","2007-06-18"]
["LN03110205","Prep for and Paint Magnets (as required)","2007-06-19","2007-06-25"]
["LN03110210","Assemble Magnets","2007-06-26","2007-07-02"]
["LN03110215","Perform Magnet Fiducialization (as required)","2007-07-03","2007-07-10"]
["LN03110220","Perform QC & Inspection - Magnets","2007-07-11","2007-07-17"]
["LN03110225","Perform Magnetic Measurement (as required)","2007-07-18","2007-07-24"]
["LN03110230","Hand-off to Pre-Instl Qual Testing","2007-07-25","2007-07-24"]
["LN03110235","Perform Magnet Pre-Instlation Qual","2007-07-25","2007-07-26"]
["LN03110240","AVAIL: BYMP_LTU Magnets Ready for Instl","2007-07-27","2007-07-26"]
["LN03110245","Define Magnet Support Requirements","2006-10-03","2006-10-04"]
["LN03110250","Create ICD & Update LCLS Database","2006-10-05","2006-10-05"]
["LN03110255","Review/Accept Reqmts, Update ICD & DB entries","2006-10-06","2006-10-06"]
["LN03110260","Develop Preliminary Design - Magnet Supports","2006-10-09","2006-10-16"]
["LN03110270","Conduct Preliminary Design Review (PDR)","2006-10-17","2006-10-18"]
["LN03110280","Develop Final Design - Magnet Supports","2006-10-19","2006-10-24"]
["LN03110290","Conduct Final Design Review (FDR)","2006-10-25","2006-10-26"]
["LN03110300","COMP: Bend Magnet Supports (BYMP_LTU) Design","2006-10-27","2006-10-26"]
["LN03110305","Prep Bid Pak - Magnet Supports","2006-04-03","2006-04-03"]
["LN03110315","RELEASE: RFP - Magnet Supports","2006-04-04","2006-04-03"]
["LN03110320","Vendors Prep Proposals - Magnet Supts","2006-04-04","2006-04-24"]
["LN03110325","RCV: Proposals from Vendors - Supts","2006-04-25","2006-04-24"]
["LN03110330","Evaluate Vendor Proposals - Supports","2006-04-25","2006-05-15"]
["LN03110335","AWARD: Contract for Supts","2006-05-16","2006-05-16"]
["LN03110340","Vendor Fab 1st Lot - Supts","2006-05-17","2007-06-01"]
["LN03110345","RCV: 1st Lot Magnet Supports from Vendor","2007-06-04","2007-06-04"]
["LN03110350","Vendor Fab Remaining Lot - Supts","2007-06-05","2007-06-04"]
["LN03110355","RCV: Remaining Magnet Supts from Vendor","2007-06-05","2007-06-04"]
["LN03110360","Procure Misc Materials - Magnet Supports","2006-05-17","2006-06-14"]
["LN03110365","Fabricate Magnet Supports","2006-06-15","2006-06-22"]
["LN03110370","Prep for, Clean & Plate Magnet Supts","2006-06-23","2006-06-22"]
["LN03110375","Prep for and Paint Magnet Supports (as required)","2006-06-23","2006-06-22"]
["LN03110380","Perform QC & Inspection on Magnets Supts","2006-06-23","2006-06-30"]
["LN03110385","Assemble Magnet Supports","2006-07-03","2006-07-24"]
["LN03110390","Hand-off to Pre-Instl Qual Testing","2006-07-25","2006-07-24"]
["LN03110395","Perform Pre-Installation Qualification - Support","2007-06-05","2007-07-02"]
["LN03110400","AVAIL: BYMP_LTU Magnet Supts Ready for Instl","2007-07-03","2007-07-02"]
["LN03110500","Procure Coil (1ea) - Bend Mag (BYMP_LTU) SPARES","2006-10-03","2006-11-29"]
["LN03110550","RCV: Bend Magnet Coil (1ea) (BYMP_LTU) SPARES","2006-11-30","2006-11-29"]
["LN03110600","Receive & Review Safety Cover Requirements","2006-10-03","2006-10-02"]
["LN03110605","Develop Magnet Safety Cover Design","2006-10-03","2006-11-29"]
["LN03110610","COMP: Magnet Safety Design","2006-11-30","2006-11-29"]
["LN03110615","Procure Magnet Safety Cover Material","2006-11-30","2007-03-12"]
["LN03110620","RCV: Magnet Safety Cover (3ea)","2007-03-13","2007-03-12"]
["LN03110625","Fab and Assemble New Magnet Safety Covers (0ea)","2007-03-13","2007-03-12"]
["LN03110630","REQD: Reusable Safety Covers for Refurbishment","2007-03-13","2007-03-12"]
["LN03110635","Refurbish Reusable Safety Covers (0ea)","2007-03-13","2007-03-12"]
["LN03110640","AVAIL: Magnet Safety Covers Ready for Instl","2007-03-13","2007-03-12"]
["LN0312","BEND MAGNET (BYKIK_LTU) SUMMARY","2005-07-01","2007-08-06",null,"2005-07-01"]
["LN03120000","Define Magnet Requirements","2005-07-01","2005-12-30",null,"2005-07-01","2005-12-30"]
["LN03120005","Create ICD & Update LCLS Database","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03120010","Review/Accept Reqmts, Update ICD & DB entries","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03120015","Develop Preliminary Design - Magnet","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03120025","Develop Preliminary Dsn - Magnet Field Analysis","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN03120030","Conduct Preliminary Design Review (PDR)","2006-02-01","2005-12-30",null,null,"2005-12-30"]
["LN03120040","Develop Final Design - Magnets","2006-02-21","2006-03-20"]
["LN03120050","Conduct Final Design Review (FDR)","2006-03-21","2006-03-22"]
["LN03120060","Develop Magnetic Measurement Plan","2006-03-23","2006-03-29"]
["LN03120065","COMP: Bend Magnet (BYKIK_LTU) Design","2006-03-30","2006-03-29"]
["LN03120070","Prep Bid Pak - Magnets","2006-03-30","2006-03-29"]
["LN03120080","RELEASE: RFP - BYKIK_LTU Bend Magnet","2006-03-30","2006-03-29"]
["LN03120085","Vendors Prep Proposals - Magnets","2006-03-30","2006-04-19"]
["LN03120090","RCV: Proposals from Vendors - Magnet","2006-04-20","2006-04-19"]
["LN03120095","Evaluate Vendor Proposals - Magnets","2006-04-20","2006-05-03"]
["LN03120100","AWARD: Contract for Magnets","2006-05-04","2006-05-04"]
["LN03120105","Vendor Fab 1st Lot - Magnets","2006-05-05","2007-06-01"]
["LN03120110","RCV: 1st Lot Magnets from Vendor","2007-06-04","2007-06-01"]
["LN03120115","Vendor Fab Remaining Lot - Magnets","2007-06-04","2007-06-01"]
["LN03120120","RCV: Remaining Magnets from Vendor","2007-06-04","2007-06-01"]
["LN03120125","Hand-off to Pre-Instl Qual Testing","2007-06-04","2007-06-01"]
["LN03120130","Procure Misc Materials - Magnets","2006-10-03","2006-10-02"]
["LN03120135","Disassemble Magnet","2006-10-03","2006-10-03"]
["LN03120145","Refurbish Magnet Coils","2006-10-04","2006-10-04"]
["LN03120150","Assemble Magnets","2006-10-05","2006-10-04"]
["LN03120160","Prep for and Paint Magnets (as required)","2006-10-05","2006-10-04"]
["LN03120165","Perform Magnet Fiducialization (as required)","2006-10-05","2006-10-04"]
["LN03120170","Perform QC & Inspection - Magnets","2006-10-05","2006-10-04"]
["LN03120175","Perform Magnetic Measurement (as required)","2006-10-05","2006-10-04"]
["LN03120180","Procure Misc Materials - Magnets","2006-03-30","2007-04-02"]
["LN03120185","Fab Tooling","2007-04-03","2007-04-09"]
["LN03120190","Fab Magnet Core","2007-04-10","2007-04-16"]
["LN03120195","Fab Magnet Coils","2007-04-17","2007-04-23"]
["LN03120205","Prep for and Paint Magnets (as required)","2007-04-24","2007-04-30"]
["LN03120210","Assemble Magnets","2007-05-01","2007-05-07"]
["LN03120215","Perform Magnet Fiducialization (as required)","2007-05-08","2007-05-14"]
["LN03120220","Perform QC & Inspection - Magnets","2007-05-15","2007-05-21"]
["LN03120225","Perform Magnetic Measurement (as required)","2007-05-22","2007-05-29"]
["LN03120230","Hand-off to Pre-Instl Qual Testing","2007-05-30","2007-05-29"]
["LN03120235","Perform Magnet Pre-Instlation Qual","2007-06-04","2007-07-30"]
["LN03120240","AVAIL: BYKIK_LTU Magnet Ready for Instl","2007-07-31","2007-07-30"]
["LN03120245","Define Magnet Support Requirements","2006-10-03","2006-10-04"]
["LN03120250","Create ICD & Update LCLS Database","2006-10-05","2006-10-05"]
["LN03120255","Review/Accept Reqmts, Update ICD & DB entries","2006-10-06","2006-10-06"]
["LN03120260","Develop Preliminary Design - Magnet Supports","2006-10-09","2006-10-16"]
["LN03120270","Conduct Preliminary Design Review (PDR)","2006-10-17","2006-10-18"]
["LN03120280","Develop Final Design - Magnet Supports","2006-10-19","2006-10-24"]
["LN03120290","Conduct Final Design Review (FDR)","2006-10-25","2006-10-26"]
["LN03120300","COMP: Bend Magnet Supports (BYKIK_LTU) Design","2006-10-27","2006-10-26"]
["LN03120305","Prep Bid Pak - Magnet Supports","2006-10-27","2006-10-27"]
["LN03120315","RELEASE: RFP - Magnet Supports","2006-10-30","2006-10-27"]
["LN03120320","Vendors Prep Proposals - Magnet Supts","2006-10-30","2006-10-30"]
["LN03120325","RCV: Proposals from Vendors - Supts","2006-10-31","2006-10-30"]
["LN03120330","Evaluate Vendor Proposals - Supports","2006-10-31","2006-10-31"]
["LN03120335","AWARD: Contract for Supts","2006-11-01","2006-11-01"]
["LN03120340","Vendor Fab 1st Lot - Supts","2006-11-02","2007-06-01"]
["LN03120345","RCV: 1st Lot Magnet Supports from Vendor","2007-06-04","2007-06-04"]
["LN03120350","Vendor Fab Remaining Lot - Supts","2007-06-05","2007-06-04"]
["LN03120355","RCV: Remaining Magnet Supts from Vendor","2007-06-05","2007-06-04"]
["LN03120360","Procure Misc Materials - Magnet Supports","2006-10-27","2007-05-01"]
["LN03120365","Fabricate Magnet Supports","2007-05-02","2007-05-09"]
["LN03120370","Prep for, Clean & Plate Magnet Supts","2007-05-10","2007-05-09"]
["LN03120375","Prep for and Paint Magnet Supports (as required)","2007-05-10","2007-05-09"]
["LN03120380","Perform QC & Inspection on Magnets Supts","2007-05-10","2007-05-17"]
["LN03120385","Assemble Magnet Supports","2007-05-18","2007-06-08"]
["LN03120390","Hand-off to Pre-Instl Qual Testing","2007-06-11","2007-06-08"]
["LN03120395","Perform Pre-Installation Qualification - Support","2007-06-11","2007-08-06"]
["LN03120400","AVAIL: BYKIK_LTU Magnet Supts Ready for Instl","2007-08-07","2007-08-06"]
["LN03120500","Procure Coil (1ea) - Bend Mag (BYKIK_LTU) SPARES","2006-10-03","2006-11-29"]
["LN03120550","RCV: Bend Magnet Coil (1ea) (BYKIK_LTU) SPARES","2006-11-30","2006-11-29"]
["LN03120600","Receive & Review Safety Cover Requirements","2006-10-03","2006-10-02"]
["LN03120605","Develop Magnet Safety Cover Design","2006-10-03","2006-11-29"]
["LN03120610","COMP: Magnet Safety Design","2006-11-30","2006-11-29"]
["LN03120615","Procure Magnet Safety Cover (1ea)","2006-11-30","2007-01-11"]
["LN03120620","RCV: Magnet Safety Cover Material","2007-01-12","2007-01-11"]
["LN03120625","Fab and Assemble New Magnet Safety Covers (0ea)","2007-01-12","2007-01-11"]
["LN03120630","REQD: Reusable Safety Covers for Refurbishment","2007-01-12","2007-01-11"]
["LN03120635","Refurbish Reusable Safety Covers (0ea)","2007-01-12","2007-01-11"]
["LN03120640","AVAIL: Magnet Safety Covers Ready for Instl","2007-01-12","2007-01-11"]
["LN0313","BEND MAGNET (BYW_LTU) SUMMARY","2005-09-01","2007-07-26",null,"2005-09-01"]
["LN03130000","RCV: Magnet Requirements from System Integ","2005-09-01","2005-08-31",null,"2005-09-01","2005-08-31"]
["LN03130010","REQD: Existing SLAC Magents Available for LCLS","2006-02-01","2006-01-31"]
["LN03130240","AVAIL: BYW_LTU Magnet Ready for Instl","2006-02-01","2006-01-31"]
["LN03130245","Define Magnet Support Requirements","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN03130250","Create ICD & Update LCLS Database","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN03130255","Review/Accept Reqmts, Update ICD & DB entries","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN03130260","Develop Preliminary Design - Magnet Supports","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN03130270","Conduct Preliminary Design Review (PDR)","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN03130280","Develop Final Design - Magnet Supports","2006-02-01","2006-03-01"]
["LN03130290","Conduct Final Design Review (FDR)","2006-03-02","2006-03-03"]
["LN03130300","COMP: Bend Magnet Supports (BYW_LTU) Design","2006-03-06","2006-03-03"]
["LN03130340","Procure Magnet Supports","2006-03-06","2007-01-05"]
["LN03130345","RCV: Magnet Supports from Vendor","2007-01-08","2007-01-05"]
["LN03130360","Procure Misc Materials - Magnet Supports","2006-03-06","2007-01-05"]
["LN03130365","Fabricate Magnet Supports","2007-01-08","2007-03-06"]
["LN03130380","Perform QC & Inspection on Magnets Supts","2007-03-07","2007-05-01"]
["LN03130385","Assemble Magnet Supports","2007-05-02","2007-06-27"]
["LN03130390","Hand-off to Pre-Instl Qual Testing","2007-06-28","2007-06-27"]
["LN03130395","Perform Pre-Installation Qualification - Support","2007-06-28","2007-07-26"]
["LN03130400","AVAIL: BYW_LTU Magnet Supts Ready for Instl","2007-07-27","2007-07-26"]
["LN03130500","Procure Coil (1ea) - Bend Mag (BYW_LTU) SPARES","2007-07-27","2007-09-21"]
["LN03130550","RCV: Bend Magnet Coil (1ea) (BYW_LTU) SPARES","2007-09-24","2007-09-21"]
["LN03130600","Receive & Review Safety Cover Requirements","2006-10-03","2006-10-02"]
["LN03130605","Develop Magnet Safety Cover Design","2006-10-03","2006-11-29"]
["LN03130610","COMP: Magnet Safety Design","2006-11-30","2006-11-29"]
["LN03130615","Procure Magnet Safety Cover (4ea)","2006-11-30","2007-02-09"]
["LN03130620","RCV: Magnet Safety Cover Material","2007-02-12","2007-02-09"]
["LN03130640","AVAIL: Magnet Safety Covers Ready for Instl","2007-02-12","2007-02-09"]
["LN04","LINAC VACUUM SUBSYSTEM SUMMARY","2005-05-02","2007-10-15",null,"2005-05-02"]
["LN0401","LINAC VACUUM SUBSYSTEM TEST EQUIP SUMMARY","2006-10-03","2006-11-29"]
["LN04010000","Begin Varian Pumpdown Cart (3ea) Eq Procurement","2006-10-03","2006-10-02"]
["LN04010005","Procure Basic Unit, V70LP Turbo, MSP5366","2006-10-03","2006-11-29"]
["LN04010010","Procure Dry Scroll Pump, MSP1001","2006-10-03","2006-11-29"]
["LN04010015","Procure Multigauge Controller, MSP0125","2006-10-03","2006-11-29"]
["LN04010020","Procure Thermocouple Board, MSP0126","2006-10-03","2006-11-29"]
["LN04010025","ProcureCold Cathode Board, MSPL9066","2006-10-03","2006-11-29"]
["LN04010030","Procure Setpoint Board, MSP 0130","2006-10-03","2006-11-29"]
["LN04010035","Procure Remote Input/Output Board, MSPL8324","2006-10-03","2006-11-29"]
["LN04010040","Procure Standard RS 485/422 O/I Board, MSPL8490","2006-10-03","2006-11-29"]
["LN04010045","Procure Inverted Magnetron CC Gauge, MSPL9062","2006-10-03","2006-11-29"]
["LN04010050","Procure Gauge Tube, Thrmcpl, 2 3/4 CFF, MSP5316","2006-10-03","2006-11-29"]
["LN04010055","Procure Emergency Vent, MSP0132","2006-10-03","2006-11-29"]
["LN04010060","Procure Forced Aircooling, MSP0136","2006-10-03","2006-11-29"]
["LN04010065","RCV: Equip for Varian Pumpdown Carts (3ea)","2006-11-30","2006-11-29"]
["LN04010100","Begin Leybold Leak Detector (1ea) Eq Procurement","2006-10-03","2006-10-02"]
["LN04010105","Procure Misc Leybold Leak Detector Equip","2006-10-03","2006-11-29"]
["LN04010110","RCV: Equip for Leybold Leak Detector (1ea)","2006-11-30","2006-11-29"]
["LN0402","LINAC BEAMLINE VACUUM CHAMBERS SUMMARY","2005-05-02","2006-07-19",null,"2005-05-02"]
["LN04020015","Develop Preliminary Vacuum System Design","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["LN04020020","Develop Prelim Component Layouts, Details & Supp","2005-05-02","2005-12-30",null,"2005-05-02","2005-12-30"]
["LN04020025","Conduct Prelim Design Review (PDR) - BL Vac Sys","2005-05-02","2005-05-05",null,"2005-05-02","2005-05-05"]
["LN04020030","Develop Final Design","2005-05-02","2006-03-01",null,"2005-05-02"]
["LN04020035","Conduct Final Design Review (FDR) - BL Vac Sys","2006-03-02","2006-03-02"]
["LN04020040","COMP: Beamline Vacuum System Design","2006-03-03","2006-03-02"]
["LN04020045","Develop Vacuum Post-Processing Plan","2005-07-01","2005-07-30",null,"2005-07-01","2005-07-30"]
["LN04020050","Prep Bid Pak - Linac Beamline Vacuum System","2006-03-03","2006-03-16"]
["LN04020055","RELEASE: RFP - BL Vacuum Chambers","2006-03-17","2006-03-16"]
["LN04020060","Vendors Prep Proposals - BL Vac System Component","2006-03-17","2006-03-16"]
["LN04020065","RCV: Proposal from Vendors","2006-03-17","2006-03-16"]
["LN04020070","Evaluate Vendor Proposals","2006-03-17","2006-03-30"]
["LN04020075","AWARD: Contract for Beamline Vac Chambers","2006-03-31","2006-03-31"]
["LN04020080","Fabricate 1st Lot","2006-04-03","2006-03-31"]
["LN04020085","RCV: 1st Lot Vac Equipment from Vendor","2006-04-03","2006-03-31"]
["LN04020090","Fabricate Remaining Lot (as required)","2006-04-03","2006-03-31"]
["LN04020095","RCV: Remaining Lot from Vendor (as req'd)","2006-04-03","2006-03-31"]
["LN04020100","Procure Vacuum Chamber Materials","2006-03-03","2006-03-16"]
["LN04020105","Fab Vacuum Chamber","2006-03-17","2006-04-13"]
["LN04020110","Vacuum Chamber QA","2006-04-14","2006-04-20"]
["LN04020115","Prep for, Clean & Plate Vacuum Equipment","2006-04-21","2006-05-04"]
["LN04020120","Vacuum Chamber Welding","2006-05-05","2006-05-18"]
["LN04020125","Process Vacuum Chamber","2006-05-19","2006-06-30"]
["LN04020130","Perform QC and Inspection","2006-07-03","2006-07-11"]
["LN04020135","Prep for & Deliver to \"Pre-Install Qual Test\"","2006-07-12","2006-07-12"]
["LN04020140","Perform Pre-Installation Qual Test","2006-07-13","2006-07-19"]
["LN04020145","AVAIL: Beamline Vac Chambers Ready for L01 Instl","2006-07-20","2006-07-19"]
["LN04020150","Prep Bid Pak - BL Vacuum Bellows Module","2006-03-03","2006-03-23"]
["LN04020155","RELEASE: RFP - BL Vacuum Bellows Module","2006-03-24","2006-03-23"]
["LN04020160","Vendors Prep Proposals - BL Vac System Component","2006-03-24","2006-03-23"]
["LN04020165","RCV: Proposal from Vendors","2006-03-24","2006-03-23"]
["LN04020170","Evaluate Vendor Proposals","2006-03-24","2006-04-06"]
["LN04020175","AWARD: Contract for Vacuum Bellows Module","2006-04-27","2006-04-27"]
["LN04020180","Fabricate 1st Lot","2006-04-28","2006-04-27"]
["LN04020185","RCV: 1st Lot Vac Equipment from Vendor","2006-04-28","2006-04-27"]
["LN04020190","Fabricate Remaining Lot (as required)","2006-04-28","2006-04-27"]
["LN04020195","RCV: Remaining Lot from Vendor (as req'd)","2006-04-28","2006-04-27"]
["LN04020200","Procure Bellows Modules","2006-03-03","2006-03-30"]
["LN04020205","Procure Bellows Material","2006-03-03","2006-03-30"]
["LN04020210","Bellows Fabrication","2006-04-28","2006-05-25"]
["LN04020215","Bellows QA","2006-05-26","2006-06-01"]
["LN04020220","Bellows Cleaning/Plating","2006-06-02","2006-06-13"]
["LN04020225","Bellows Welding","2006-06-14","2006-06-23"]
["LN04020230","Bellows Vacuum Processing","2006-06-26","2006-07-17"]
["LN04020235","AVAIL: Vacuum Bellows Module Ready for L01 Instl","2006-07-18","2006-07-17"]
["LN04020240","Prep Bid Pak - Linac Beamline Vacuum System","2006-03-03","2006-03-02"]
["LN04020245","RELEASE: RFP - Linac Vacuum Supports","2006-03-03","2006-03-02"]
["LN04020250","Vendors Prep Proposals - BL Vac System Component","2006-03-03","2006-03-23"]
["LN04020255","RCV: Proposal from Vendors","2006-03-24","2006-03-23"]
["LN04020260","Evaluate Vendor Proposals","2006-03-24","2006-04-06"]
["LN04020265","AWARD: Contract for Linac Vacuum Supports","2006-04-07","2006-04-07"]
["LN04020270","Fabricate 1st Lot","2006-04-10","2006-04-07"]
["LN04020275","RCV: 1st Lot Vac Equipment from Vendor","2006-04-10","2006-04-07"]
["LN04020280","Fabricate Remaining Lot (as required)","2006-04-10","2006-04-07"]
["LN04020285","RCV: Remaining Lot from Vendor (as req'd)","2006-04-10","2006-04-07"]
["LN04020290","Procure Misc Materials - Vacuum Supports","2006-03-03","2006-03-30"]
["LN04020295","Fab Vacuum Support","2006-04-10","2006-06-05"]
["LN04020300","Assemble Beamline Vacuum Supports","2006-05-08","2006-07-03"]
["LN04020305","AVAIL: BL Vac Chamber Supts Ready for L02 Instl","2006-07-05","2006-07-03"]
["LN04020400","Procure Materials for B/L Vac Sys Spares Kit","2006-10-03","2006-10-30"]
["LN04020405","RCV: Materials for B/L Vac Sys Spares Kit","2006-10-31","2006-10-30"]
["LN0403","LINAC BC1 VACUUM CHAMBERS SUMMARY","2005-07-01","2006-06-13",null,"2005-07-01"]
["LN04030045","Prep Bid Pak - BC1 Vacuum Chambers","2005-07-01","2005-07-15",null,"2005-07-01","2005-07-15"]
["LN04030050","RELEASE: RFP - BC1 Vacuum Chambers","2006-02-01","2005-07-15",null,null,"2005-07-15"]
["LN04030055","Vendors Prep Proposals - BC1 Vac System","2005-08-01","2005-08-09",null,"2005-08-01","2005-08-09"]
["LN04030060","RCV: Proposal from Vendors","2005-08-10","2005-08-20",null,"2005-08-10","2005-08-20"]
["LN04030065","Evaluate Vendor Proposals","2005-08-21","2005-09-30",null,"2005-08-21","2005-09-30"]
["LN04030070","AWARD: Contract for BC1 Vacuum Chambers","2006-02-01","2005-09-30",null,null,"2005-09-30"]
["LN04030075","Vendor Fab & Assy - Vacuum Chamber Materials","2005-10-03","2006-01-30",null,"2005-10-03","2006-01-30"]
["LN04030080","RCV: from Vendor - Vacuum Chamber Materials","2006-02-01","2006-01-30",null,null,"2006-01-30"]
["LN04030100","Fab Vacuum Chamber","2005-12-01","2006-03-27",null,"2005-12-01"]
["LN04030105","Vacuum Chamber QA","2006-03-28","2006-04-06"]
["LN04030110","Prep for, Clean & Plate Vacuum Equipment","2006-04-07","2006-04-21"]
["LN04030115","Vacuum Chamber Welding","2006-04-24","2006-05-16"]
["LN04030120","Process Vacuum Chamber","2006-05-17","2006-05-25"]
["LN04030125","Perform QC and Inspection","2006-05-26","2006-06-05"]
["LN04030130","Prep for & Deliver to \"Pre-Install Qual Test\"","2006-06-06","2006-06-06"]
["LN04030135","Perform Pre-Installation Qual Test","2006-06-07","2006-06-13"]
["LN04030140","AVAIL: BC1 Vac Chambers Ready for Install","2006-06-14","2006-06-13"]
["LN04030400","Procure Materials for BC1 Vac Sys Spares Kit","2006-10-03","2006-10-30"]
["LN04030405","RCV: Materials for BC1 Vac Sys Spares Kit","2006-10-31","2006-10-30"]
["LN0404","LINAC BC2 VACUUM CHAMBERS SUMMARY","2005-10-03","2007-04-20",null,"2005-10-03"]
["LN04040015","Develop Preliminary Vacuum System Design","2005-10-03","2006-01-30",null,"2005-10-03","2006-01-30"]
["LN04040020","Conduct Prelim Design Review (PDR) - BC2 Vac Sys","2006-02-01","2006-02-07"]
["LN04040025","Develop Final Design -BC2 Vac","2006-02-08","2006-04-19"]
["LN04040030","Conduct Final Design Review (FDR) - BC2 Vac Sys","2006-04-20","2006-04-26"]
["LN04040035","COMP: BC2 Vacuum Chambers Design","2006-04-27","2006-04-26"]
["LN04040040","Develop Vacuum Post-Processing Plan","2006-04-27","2006-05-03"]
["LN04040045","Prep Bid Pak - BC2 Vac Chamber Mtrl","2006-04-27","2006-05-10"]
["LN04040050","RELEASE: RFP - BC2 Vac Chambers Mtrl","2006-05-11","2006-05-10"]
["LN04040055","Vendors Prep Proposals - BC2 Vac System","2006-05-11","2006-05-24"]
["LN04040060","RCV: Proposal from Vendors","2006-05-25","2006-05-24"]
["LN04040065","Evaluate Vendor Proposals","2006-05-25","2006-06-08"]
["LN04040070","AWARD: Contract for BC2 Vac Chambers Mtrl","2006-06-09","2006-06-09"]
["LN04040075","Procure Vacuum Chamber Materials","2006-06-12","2006-07-10"]
["LN04040076","Procure Bellows Module","2006-06-12","2006-07-10"]
["LN04040077","Procure CF Copper Gasket","2006-06-12","2006-07-10"]
["LN04040078","Procure CF Bolt Set","2006-06-12","2006-07-10"]
["LN04040080","RCV: from Vendor - Vacuum Chamber Materials","2006-07-11","2006-07-10"]
["LN04040100","Fab Vacuum Chamber","2006-07-11","2007-02-01"]
["LN04040105","Vacuum Chamber QA","2007-02-02","2007-02-13"]
["LN04040110","Prep for, Clean & Plate Vacuum Equipment","2007-02-14","2007-03-01"]
["LN04040115","Vacuum Chamber Welding","2007-03-02","2007-03-26"]
["LN04040120","Process Vacuum Chamber","2007-03-27","2007-04-04"]
["LN04040125","Perform QC and Inspection","2007-04-05","2007-04-12"]
["LN04040130","Prep for & Deliver to \"Pre-Install Qual Test\"","2007-04-13","2007-04-13"]
["LN04040135","Perform Pre-Installation Qual Test","2007-04-16","2007-04-20"]
["LN04040140","AVAIL: BC2 Vac Chambers Ready for Install","2007-04-23","2007-04-20"]
["LN04040400","Procure Materials for BC2 Vac Sys Spares Kit","2006-10-03","2006-10-30"]
["LN04040405","RCV: Materials for BC2 Vac Sys Spares Kit","2006-10-31","2006-10-30"]
["LN0405","LINAC to UND (LTU) VAC CHAMBERS SUMMARY","2005-12-01","2007-10-09",null,"2005-12-01"]
["LN04050000","Define LTU Vac Sys Requirements","2006-02-01","2006-02-14"]
["LN04050003","Create ICD & Update LCLS Database","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN04050005","Review & Accept Requirements, ICD & DB Entries","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN04050010","Develop Preliminary Vacuum System Design","2005-12-01","2006-06-22",null,"2005-12-01"]
["LN04050015","Develop Preliminary Vac Sys Supports Design","2006-03-01","2006-06-21"]
["LN04050020","Conduct Prelim Design Review (PDR) - LTU Vac Sys","2006-06-23","2006-06-28"]
["LN04050025","Develop Final Design","2006-06-29","2006-09-08"]
["LN04050030","Conduct Final Design Review (FDR) - LTU Vac Sys","2006-09-11","2006-09-14"]
["LN04050035","COMP: LTU Vacuum Chambers Design","2006-09-15","2006-09-14"]
["LN04050040","Develop Vacuum Post-Processing Plan","2006-09-15","2006-10-12"]
["LN04050045","Prep Bid Pak -  Vacuum Equipment","2006-10-13","2006-10-19"]
["LN04050050","RELEASE: RFP  - Vacuum Equipment","2006-10-20","2006-10-19"]
["LN04050055","Vendors Prep Proposals - Vacuum Equipment","2006-10-20","2006-11-02"]
["LN04050060","RCV: Proposals from Vendors - Vacuum Equipment","2006-11-03","2006-11-02"]
["LN04050065","Evaluate Vendor Proposals","2006-11-03","2006-11-06"]
["LN04050070","AWARD: Contract - Vacuum Equipment","2006-11-07","2006-11-07"]
["LN04050080","RCV: from Vendor  - Vacuum Equipment","2007-04-18","2007-04-17"]
["LN04050100","Procure Vacuum Chamber Material","2006-11-08","2006-11-08"]
["LN04050105","Fab Vacuum Chamber","2006-12-08","2007-04-17"]
["LN04050110","Vacuum Chamber QA Fabrication","2007-03-21","2007-03-20"]
["LN04050115","Prep for, Clean & Plate Vacuum Equipment","2007-04-18","2007-07-12"]
["LN04050120","Vacuum Chamber Welding","2007-05-16","2007-08-23"]
["LN04050125","Process Vacuum Chamber","2007-06-14","2007-09-21"]
["LN04050130","Perform QC and Inspection","2007-09-24","2007-10-01"]
["LN04050135","Prep for & Deliver to \"Pre-Install Qual Test\"","2007-10-02","2007-10-02"]
["LN04050140","Perform Pre-Installation Qual Test","2007-10-03","2007-10-09"]
["LN04050145","AVAIL: LTU Vac Chambers Ready for Install","2007-10-10","2007-10-09"]
["LN04050150","Prep Bid Pak - Vacuum Supports","2006-10-03","2006-10-02"]
["LN04050155","RELEASE: RFP - LTU Vacuum Supports","2006-10-03","2006-10-02"]
["LN04050160","Vendors Prep Proposals - LTU Vac System","2006-10-03","2006-10-02"]
["LN04050165","RCV: Proposals from Vendors -","2006-10-03","2006-10-02"]
["LN04050170","Evaluate Vendor Proposals","2006-10-03","2006-10-02"]
["LN04050175","AWARD: Contract for LTU Vacuum Supports","2006-10-03","2006-10-02"]
["LN04050180","Fabricate 1st Lot","2006-10-03","2006-10-02"]
["LN04050185","RCV: 1st Lot Vac Equipment from Vendor","2006-10-03","2006-10-02"]
["LN04050190","Fabricate Remaining Lot (as required)","2006-10-03","2006-10-02"]
["LN04050195","RCV: Remaining Lot from Vendor (as req'd)","2006-10-03","2006-10-02"]
["LN04050205","Procure Misc Materials - Vacuum Supports","2006-10-03","2006-10-30"]
["LN04050206","Procure Materials for Vacuum Supports","2006-10-03","2006-10-30"]
["LN04050207","Procure Bellows","2006-11-08","2007-04-17"]
["LN04050208","Procure CF Flanges","2006-11-08","2007-04-17"]
["LN04050209","Procure CF Crosses","2006-11-08","2007-04-17"]
["LN04050210","Fab Vacuum Support","2006-10-31","2007-03-12"]
["LN04050211","Procure Vat Valve","2006-11-08","2007-04-17"]
["LN04050212","Procure Pump Out Valve","2006-11-08","2007-04-17"]
["LN04050213","Procure Cold Cathode Gauge","2006-11-08","2007-04-17"]
["LN04050214","Procure Pirani Gauge","2006-11-08","2007-04-17"]
["LN04050215","Assemble LTU Vacuum Supports","2007-01-12","2007-05-07"]
["LN04050216","Procure Gauge Pig Tail","2006-11-08","2007-04-17"]
["LN04050217","Procure Ion Pump","2006-11-08","2007-04-17"]
["LN04050218","Procure Ion Pump Pig Tail","2006-11-08","2007-04-17"]
["LN04050219","Procure Copper Gasket","2006-11-08","2007-04-17"]
["LN04050220","AVAIL: LTU Vac Chamber Supports Ready for Instl","2007-05-08","2007-05-07"]
["LN04050221","Procure CF Bolt Set","2006-11-08","2007-04-17"]
["LN04050400","Procure Materials for LTU Vac Sys Spares Kit","2006-10-03","2006-10-30"]
["LN04050405","RCV: Materials for LTU Vac Sys Spares Kit","2006-10-31","2006-10-30"]
["LN0406","LINAC DUMPLINE VACUUM CHAMBERS SUMMARY","2005-05-02","2007-10-15",null,"2005-05-02"]
["LN04060000","Define Dumpline Vac Sys Requirements","2005-05-02","2005-07-15",null,"2005-05-02","2005-07-15"]
["LN04060003","Create ICD & Update LCLS Database","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN04060007","Review & Accept Requirements, ICD & DB Entries","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN04060010","Develop Preliminary Vacuum System Design","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN04060013","Define Requirements LTU Vac Sys Supports","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN04060017","Develop Prelim Design LTU Vacuum Sys Supports","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN04060020","Conduct Prelim Design Review (PDR) - D/L Vac Sys","2006-02-01","2006-02-02"]
["LN04060025","Develop Final Design","2006-02-03","2006-04-14"]
["LN04060030","Conduct Final Design Review (FDR) - D/L Vac Sys","2006-04-17","2006-04-18"]
["LN04060035","COMP: Dumpline Vacuum System Design","2006-10-03","2006-10-02"]
["LN04060040","Develop Vacuum Post-Processing Plan","2006-10-03","2006-10-16"]
["LN04060045","Prep Bid Pak - Dumpline Vacuum System","2006-10-17","2006-11-06"]
["LN04060050","RELEASE: RFP - Dumpline Vacuum Chambers","2006-11-07","2006-11-06"]
["LN04060055","Vendors Prep Proposals - Dumpline Vac System","2006-11-07","2006-11-29"]
["LN04060060","RCV: Proposals from Vendors -","2006-11-30","2006-11-29"]
["LN04060065","Evaluate Vendor Proposals","2006-11-30","2007-01-04"]
["LN04060070","AWARD: Contract for Linac Dumpline Vac Chamber","2007-01-05","2007-01-05"]
["LN04060075","Fabricate 1st Lot","2007-01-08","2007-03-06"]
["LN04060080","RCV: 1st Lot Vac Equipment from Vendor","2007-03-07","2007-03-06"]
["LN04060085","Fabricate Remaining Lot (as required)","2007-03-07","2007-03-06"]
["LN04060090","RCV: Remaining Lot from Vendor (as req'd)","2007-03-07","2007-03-06"]
["LN04060095","Procure Bellows Modules","2006-10-03","2007-01-11"]
["LN04060096","Procure CF Flanges","2006-10-03","2007-01-11"]
["LN04060097","Procure CF Crosses","2006-10-03","2007-01-11"]
["LN04060098","Procure VAT Valve","2006-10-03","2007-01-11"]
["LN04060099","Procure Pump Out Valve","2006-10-03","2007-01-11"]
["LN04060101","Procure Cold Cathode Gauge","2006-10-03","2007-01-11"]
["LN04060102","Procure Pirani Gauge","2006-10-03","2007-01-11"]
["LN04060103","Procure Gauge Pig Tail","2006-10-03","2007-01-11"]
["LN04060104","Procure Ion Pump","2006-10-03","2007-01-11"]
["LN04060105","Fab Vacuum Chamber","2007-01-12","2007-04-09"]
["LN04060106","Procure Ion Pump Pig Tail","2006-10-03","2007-01-11"]
["LN04060107","Procure CF Copper Gasket","2006-10-03","2007-01-11"]
["LN04060108","Procure CF Bolt Set","2006-10-03","2007-01-11"]
["LN04060109","Procure 304 Tubing","2006-10-03","2007-01-11"]
["LN04060110","Vacuum Chamber QA Fabrication","2007-02-12","2007-05-07"]
["LN04060115","Clean & Plate Vacuum Equipment","2007-03-13","2007-07-03"]
["LN04060120","Vacuum Chamber Welding","2007-06-06","2007-08-29"]
["LN04060125","Process Vacuum Chamber","2007-07-05","2007-09-27"]
["LN04060130","Perform QC and Inspection","2007-09-28","2007-10-05"]
["LN04060135","Prep for & Deliver to \"Pre-Install Qual Test\"","2007-10-08","2007-10-08"]
["LN04060140","Perform Pre-Installation Qual Test","2007-10-09","2007-10-15"]
["LN04060145","AVAIL: DL Vac Chambers Ready for Install","2007-10-16","2007-10-15"]
["LN04060150","Prep Bid Pak - Vacuum Supports","2006-10-03","2006-10-23"]
["LN04060155","RELEASE: RFP - Dumpline Vacuum Supports","2006-10-24","2006-10-23"]
["LN04060160","Vendors Prep Proposals - Dumpline Vac System","2006-10-24","2006-11-20"]
["LN04060165","RCV: Proposals from Vendors -Dumpline Vac System","2006-11-21","2006-11-20"]
["LN04060170","Evaluate Vendor Proposals - UHV Components","2006-11-21","2006-12-13"]
["LN04060175","AWARD: Contract for Dumpline Vac Chamber Supt","2006-12-14","2006-12-14"]
["LN04060180","Fabricate 1st Lot","2006-12-15","2007-02-27"]
["LN04060185","RCV: 1st Lot Vac Equipment from Vendor","2007-02-28","2007-02-27"]
["LN04060190","Fabricate Remaining Lot (as required)","2007-02-28","2007-02-27"]
["LN04060195","RCV: Remaining Lot from Vendor (as req'd)","2007-02-28","2007-02-27"]
["LN04060200","Procure Misc Materials - Vacuum Supports","2007-02-28","2007-03-27"]
["LN04060205","Fab Vacuum Support","2007-03-28","2007-07-19"]
["LN04060210","Assemble DL Vacuum Supports","2007-04-25","2007-08-16"]
["LN04060215","AVAIL: DL Vac Chamber Supports Ready for Instl","2007-08-17","2007-08-16"]
["LN04060400","Procure Materials for D/L Vac Sys Spares Kit","2006-10-03","2006-10-30"]
["LN04060405","RCV: Materials for D/L Vac Sys Spares Kit","2006-10-31","2006-10-30"]
["LN05","LINAC ELECTRON DIAGNOSTICS SUMMARY","2005-11-01","2008-02-20",null,"2005-11-01"]
["LN0501","WIRE SCANNERS (11) SUMMARY","2005-11-01","2007-04-04",null,"2005-11-01"]
["LN05010395","Prep Bid Pack - Wire Scanner","2005-11-01","2006-01-30",null,"2005-11-01","2006-01-30"]
["LN05010400","AWARD: Contract Wire Scanners (2ea) Spares","2006-10-03","2006-10-03"]
["LN05010405","Vendor Fab 1st Lot (2) Spares","2006-10-04","2006-10-31"]
["LN05010410","RCV: 1st Lot from Vendor (2) Spares","2006-11-01","2006-10-31"]
["LN05010415","Vendor Fab Remaining Lot (2) Spares","2006-11-01","2006-11-30"]
["LN05010420","RCV: Remaining from Vendor (2) Spares","2006-12-01","2006-11-30"]
["LN05010425","Procure Misc Materials - Wire Scann - (2) SPARES","2006-10-03","2007-06-26"]
["LN05010430","Component Fab & Assembly - Wire Scanr (2) Spares","2008-10-01","2009-02-04"]
["LN05010435","Release RFP - Wire Scanners","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN05010440","Vendors Prep Proposal - Wire Scanners","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN05010445","Perform QC / Metrology (2ea) Spares","2009-02-05","2009-02-10"]
["LN05010450","Perform Functional Testing - Wire Scn (2) Spares","2009-02-11","2009-02-12"]
["LN05010455","Collect Component Performance Data (2ea) Spares","2009-02-13","2009-02-19"]
["LN05010460","Load Component Data Base (2ea) Spares","2009-02-20","2009-02-26"]
["LN05010465","Post Process & Test (2ea) Spares","2009-02-27","2009-03-05"]
["LN05010470","AVAIL: Wire Scanners (2ea) Spares","2009-03-06","2009-03-05"]
["LN05010475","RCV: Proposals from Vendors","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN05010480","Evaluate Vendor Proposals","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN05010485","AWARD: Contract - Wire Scanners L01-BC1","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN05010490","Vendor Fab Wire Scanner Components","2006-02-01","2006-03-29"]
["LN05010495","RCV: Wire Scanner Components from Vendor","2006-03-30","2006-03-30"]
["LN05010500","Procure Misc Materials - Wire Scanners","2005-11-08","2006-03-15",null,"2005-11-08"]
["LN05010516","Component Fab & Assembley - Wire Scanners","2006-03-31","2006-03-31"]
["LN05010517","AWARD: Contract for Supports L01-BC1","2005-11-01","2006-02-01",null,"2005-11-01"]
["LN05010520","Vendor Fab Supports","2005-11-01","2006-06-15",null,"2005-11-01"]
["LN05010525","Pocure Misc. Materials - Wire Scanner Support","2005-11-01","2006-06-15",null,"2005-11-01"]
["LN05010535","Perform Functional Testing - Wire Scanners","2006-06-16","2006-06-29"]
["LN05010540","Post Process & Test","2006-06-30","2006-07-14"]
["LN05010545","AVAIL: Wire Scanners Ready for L01 Install","2006-07-17","2006-07-17"]
["LN05010550","AVAIL: Wire Scanners Ready for BC1 Install","2006-07-17","2006-07-17"]
["LN05010575","AVAIL: Supports Ready for Install","2006-06-16","2006-06-16"]
["LN05010590","Prep Bid Pack - Wire Scanner","2006-11-01","2006-11-07"]
["LN05010600","Release RFP - Wire Scanners","2006-11-08","2006-11-08"]
["LN05010610","Vendors Prep Proposal - Wire Scanners","2006-11-09","2006-12-08"]
["LN05010620","RCV: Proposals from Vendors","2006-12-11","2006-12-11"]
["LN05010630","Evaluate Vendor Proposals","2006-12-12","2007-01-02"]
["LN05010632","AWARD: Contract - Wire Scanners BC2-L03-LTU","2007-01-03","2007-01-03"]
["LN05010640","Vendor Fab Wire Scanner Components","2007-01-04","2007-03-02"]
["LN05010650","RCV: Wire Scanner Components from Vendor","2007-03-05","2007-03-05"]
["LN05010660","Procure Misc Materials - Wire Scanners","2006-11-08","2006-12-07"]
["LN05010670","Component Fab & Assembley - Wire Scanners","2007-03-06","2007-03-06"]
["LN05010672","AWARD: Contract for Supports BC2-L03-LTU","2006-12-12","2006-12-12"]
["LN05010680","Vendor Fab Supports","2006-12-13","2007-02-23"]
["LN05010690","Pocure Misc. Materials - Wire Scanner Support","2006-12-13","2007-01-25"]
["LN05010700","Perform Functional Testing - Wire Scanners","2007-03-07","2007-03-20"]
["LN05010710","Post Process & Test","2007-03-21","2007-04-03"]
["LN05010740","AVAIL: Wire Scanners Ready for L02 Install","2007-04-04","2007-04-04"]
["LN05010750","AVAIL: Wire Scanners Ready for BC2 Install","2007-04-04","2007-04-04"]
["LN05010760","AVAIL: Wire Scanners Ready for L03 Install","2007-04-04","2007-04-04"]
["LN05010770","AVAIL: Wire Scanners Ready for LTU Install","2007-04-04","2007-04-04"]
["LN05010780","AVAIL: Supports Ready for Install","2007-02-26","2007-02-26"]
["LN05020120","Write ICD - Beam Position Monitor","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN05020125","Collect Area Specific Requirements","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN05020130","Produce Common Layout","2005-12-01","2006-01-30",null,"2005-12-01","2006-01-30"]
["LN05020135","Develop General Specifications/Analysis","2005-12-01","2006-03-31",null,"2005-12-01"]
["LN05020145","Create/Remodel/Revise DSN Docs","2005-12-01","2006-03-31",null,"2005-12-01"]
["LN05020150","Design Check","2006-04-03","2006-09-20"]
["LN05020155","Write Component Traveler","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN05020160","BPMs - Preliminary Design Review (PDR)","2005-12-01","2006-01-30",null,"2005-12-01","2006-01-30"]
["LN05020165","Generate Detailed Procuremnt Plan","2005-12-01","2006-01-30",null,"2005-12-01","2006-01-30"]
["LN05020170","BPMs - Final Design Review (FDR)","2005-12-01","2006-03-15",null,"2005-12-01"]
["LN05020175","Procure Component Material - BPMs","2005-12-01","2006-03-31",null,"2005-12-01"]
["LN05020180","Component Fab & Assembly - BPMs","2005-12-01","2006-03-31",null,"2005-12-01"]
["LN05020185","Perform QC / Metrology","2006-04-03","2006-04-07"]
["LN05020190","Perform Functional Testing - BPMs","2006-04-10","2006-04-14"]
["LN05020195","Post Process & Test","2006-04-17","2006-04-21"]
["LN05020200","AVAIL: BPMs Ready for BC1 Install","2006-04-24","2006-04-21"]
["LN05020205","AVAIL: BPMs Ready for L01 Install","2006-04-24","2006-04-21"]
["LN05020360","Receive BPM Requirements","2006-10-03","2006-10-03"]
["LN05020365","Write ICD - Beam Path Monitor","2006-10-04","2006-10-09"]
["LN05020370","Collect Area Specific Requirements","2006-10-10","2006-10-16"]
["LN05020375","Produce Common Layout","2006-10-17","2006-11-13"]
["LN05020380","Develop General Specifications / Analysis","2006-11-14","2006-11-20"]
["LN05020385","Create / Remodel / Revise Dsn Documentation","2006-11-21","2007-01-19"]
["LN05020390","Design Check","2007-01-22","2007-03-19"]
["LN05020395","Write Component Traveler","2007-03-20","2007-04-02"]
["LN05020400","Conduct Prelim Design Review (PDR) - FFTB BPMs","2007-04-03","2007-04-03"]
["LN05020405","Generate Detailed Procurement Plan","2007-04-04","2007-04-17"]
["LN05020410","Conduct Final Design Review (FDR) - FFTB BPMs","2007-04-18","2007-04-18"]
["LN05020412","COMP: BPM Design - FFTB","2007-04-19","2007-04-19"]
["LN05020415","Procure Component Material - BPMs","2007-04-20","2007-07-16"]
["LN05020425","Component Fab & Assembly - BPMs","2007-07-17","2007-09-11"]
["LN05020430","Perform QC / Metrology","2007-09-12","2007-09-18"]
["LN05020435","Perform Functional Testing - BPMs","2007-09-19","2007-09-20"]
["LN05020445","Post Process & Test","2007-09-21","2007-09-27"]
["LN05020450","AVAIL: FFTB BPMs Ready for Install","2007-09-28","2007-09-28"]
["LN05020480","Develop General Specifications / Analysis","2006-01-01","2006-03-01",null,"2006-01-01"]
["LN05020485","Create / Remodel / Revise Dsn Documentation","2006-01-01","2006-03-01",null,"2006-01-01"]
["LN05020490","Write Component Traveler","2006-02-15","2006-03-01"]
["LN05020495","Conduct BPMs PDR","2006-03-02","2006-03-08"]
["LN05020500","Procure Component Material - BPMs - (2) SPARES","2006-10-03","2007-03-12"]
["LN05020505","Component Fab & Assembly - BPMs (2ea) Spares","2007-03-13","2007-08-29"]
["LN05020510","Generate Detailed Procurement Plan","2006-03-09","2006-03-22"]
["LN05020515","Conduct BPMs FDR","2006-03-23","2006-03-29"]
["LN05020520","Perform QC / Metrology (2ea) Spares","2007-08-30","2007-08-31"]
["LN05020525","Perform Functional Testing - BPMs (2ea) Spares","2007-09-04","2007-09-05"]
["LN05020530","Collect Component Performance Data (2ea) Spares","2007-09-06","2007-09-12"]
["LN05020535","Load Component Data Base (2ea) Spares","2007-09-13","2007-09-19"]
["LN05020540","Post Process & Test (2ea) Spares","2007-09-20","2007-09-26"]
["LN05020545","Design Check","2006-03-30","2006-04-26"]
["LN05020547","COMP: BPM Design - BC1","2006-04-27","2006-04-27"]
["LN05020550","Procure Component Material - BPMs","2006-04-28","2006-05-25"]
["LN05020555","Component Fab & Assembly - BPMs","2006-05-26","2006-06-23"]
["LN05020560","Perform QC / Metrology","2006-06-26","2006-07-24"]
["LN05020565","Perform Functional Testing - BPMs","2006-07-25","2006-08-07"]
["LN05020570","Post Process & Test","2006-08-08","2006-08-21"]
["LN05020575","AVAIL: High Resolution BC1 BPM Read for Install","2006-08-22","2006-08-22"]
["LN05020600","Procure Component Material - RF BPM - (2) SPARES","2006-10-03","2007-01-11"]
["LN05020605","Component Fab & Assembly - RFBPMs (2ea) Spares","2007-01-12","2007-05-07"]
["LN05020610","Component Fab & Assembly - RF BPMs","2007-05-08","2007-08-29"]
["LN05020615","Perform QC / Metrology (2ea) Spares","2007-08-30","2007-09-05"]
["LN05020620","Perform Functional Testing - RFBPMs (2ea) Spares","2007-09-06","2007-09-07"]
["LN05020625","Collect Component Performance Data (2ea) Spares","2007-09-10","2007-09-14"]
["LN05020630","Load Component Data Base (2ea) Spares","2007-09-17","2007-09-21"]
["LN05020635","Post Process & Test (2ea) Spares","2007-09-24","2007-09-28"]
["LN05020700","Procure Component Material - BPMs - (2) SPARES","2007-07-17","2007-09-11"]
["LN05020705","Component Fab & Assembly - BPMs (2ea) Spares","2007-09-12","2007-11-06"]
["LN05020720","Perform QC / Metrology (2ea) Spares","2007-11-07","2007-11-13"]
["LN05020725","Perform Functional Testing - BPMs (2ea) Spares","2007-11-14","2007-11-19"]
["LN05020730","Collect Component Performance Data (2ea) Spares","2007-11-20","2007-11-21"]
["LN05020735","Load Component Data Base (2ea) Spares","2007-11-26","2007-11-27"]
["LN05020740","Post Process & Test (2ea) Spares","2007-11-28","2007-12-11"]
["LN05020800","Procure Component Material - BPMs - (1) SPARE","2006-10-03","2006-11-29"]
["LN05020805","Component Fab & Assembly - BPMs (1ea) Spare","2006-11-30","2007-06-05"]
["LN05020820","Perform QC / Metrology (1ea) Spare","2007-06-06","2007-06-11"]
["LN05020825","Perform Functional Testing - BPMs (1ea) Spare","2007-06-12","2007-06-15"]
["LN05020830","Collect Component Performance Data (1ea) Spare","2007-06-18","2007-06-19"]
["LN05020835","Load Component Data Base (1ea) Spare","2007-06-20","2007-06-21"]
["LN05020840","Post Process & Test (1ea) Spare","2007-06-22","2007-06-27"]
["LN05020845","AVAIL: BPMs (2/2/2/1) Spare","2007-12-12","2007-12-11"]
["LN05030300","Procure Component Material - Toroid - (2) SPARES","2006-10-03","2007-01-11"]
["LN05030305","Review & Accept Requirements","2005-11-01","2006-01-31",null,"2005-11-01"]
["LN05030310","Component Fab & Assembly - Toroids (2ea) Spares","2007-01-12","2007-05-07"]
["LN05030315","Write ICD - Toroid","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN05030320","Collect Area Specific Requirements","2006-02-01","2005-11-30",null,null,"2005-11-30"]
["LN05030325","Perform QC / Metrology (2ea) Spares","2007-05-08","2007-05-09"]
["LN05030330","Perform Functional Testing - Toroid (2ea) Spares","2007-05-10","2007-05-11"]
["LN05030335","Collect Component Performance Data (2ea) Spares","2007-05-14","2007-05-18"]
["LN05030340","Load Component Data Base (2ea) Spares","2007-05-21","2007-05-25"]
["LN05030345","Post Process & Test (2ea) Spares","2007-05-29","2007-06-04"]
["LN05030350","AVAIL: Toroids (2ea) Spares","2007-06-05","2007-06-04"]
["LN05030360","Develop General Specifications / Analysis","2005-11-01","2005-11-30",null,"2005-11-01","2005-11-30"]
["LN05030370","Conduct Toroids PDR","2005-11-01","2005-11-30",null,"2005-11-01","2005-11-30"]
["LN05030372","COMP: Toroid Design","2006-02-01","2006-01-31"]
["LN05030375","Generate Detailed Procurement Plan","2005-11-01","2005-11-30",null,"2005-11-01","2005-11-30"]
["LN05030380","Conduct Toroids FDR","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN05030385","Procure Component Material - Toroids","2006-03-01","2006-05-23"]
["LN05030390","Component Fab & Assembly - Toroids","2006-05-24","2006-08-17"]
["LN05030395","Perform Functional Testing - Toroids","2006-08-18","2006-09-15"]
["LN05030400","Post Process & Test","2006-09-18","2006-09-29"]
["LN05030405","AVAIL: Toroids Ready for BC1 Install","2006-10-02","2006-09-29"]
["LN05030410","AVAIL: Toroids Ready for BC2 Install","2006-10-02","2006-09-29"]
["LN05030415","AVAIL: Toroids Ready for LTU Install","2006-10-02","2006-09-29"]
["LN05040300","Procure Hardware Kit - Stoppers - SPARES","2006-10-03","2007-03-12"]
["LN05040305","AVAIL: Spares Hardware Kit - Stoppers","2007-03-13","2007-03-12"]
["LN05040310","Produce Common Layout","2005-12-01","2006-01-30",null,"2005-12-01","2006-01-30"]
["LN05040315","Develop General Specifications / Analysis","2005-12-01","2006-01-30",null,"2005-12-01","2006-01-30"]
["LN05040317","Create / Remodel / Revise Dsn Documentation","2005-12-01","2006-01-30",null,"2005-12-01","2006-01-30"]
["LN05040320","Design Check","2006-01-01","2006-04-14",null,"2006-01-01"]
["LN05040325","Write Component Traveler","2006-04-17","2006-05-12"]
["LN05040330","Generate Detailed Procurement Plan","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN05040335","Conduct Stoppers FDR","2006-03-01","2006-03-07"]
["LN05040337","COMP: Stopper Design","2006-03-08","2006-03-07"]
["LN05040340","Procure Component Material - Stoppers","2005-12-01","2006-01-30",null,"2005-12-01","2006-01-30"]
["LN05040345","Component Fab & Assembly - Stoppers","2005-12-01","2006-01-30",null,"2005-12-01","2006-01-30"]
["LN05040355","Perform Functional Testing - Stoppers","2006-01-01","2006-02-14",null,"2006-01-01"]
["LN05040360","Post Process & Test","2006-02-15","2006-03-01"]
["LN05040361","AVAIL: Stoppers Ready for BC1 Install","2006-03-02","2006-03-01"]
["LN05040365","Prep Bid Pak - Diagnostics Supports","2006-04-14","2006-04-27"]
["LN05040367","AWARD: Contract for Supports BC1","2006-04-28","2006-04-28"]
["LN05040370","Vendor Fab 1st Lot - Supports","2006-05-01","2006-06-26"]
["LN05040371","RCV: Supports from Vendor","2006-06-27","2006-06-26"]
["LN05040375","Procure Misc Materials - Diagnostics Supports","2006-03-08","2006-04-04"]
["LN05040380","Assemble Supports","2006-06-27","2006-07-25"]
["LN05040385","AVAIL: Supports Ready for Instl","2006-07-26","2006-07-25"]
["LN05040396","Produce Common Layout","2006-11-01","2006-11-21"]
["LN05040405","Develop General Specifications / Analysis","2006-11-01","2006-11-14"]
["LN05040415","Create / Remodel / Revise Dsn Documentation","2006-11-01","2007-01-12"]
["LN05040425","Design Check","2006-11-01","2006-11-30"]
["LN05040435","Write Component Traveler","2006-12-01","2007-01-12"]
["LN05040445","Generate Detailed Procurement Plan","2007-01-16","2007-02-12"]
["LN05040455","Conduct Stoppers FDR","2007-02-13","2007-02-20"]
["LN05040465","COMP: Stopper Design","2007-02-21","2007-02-20"]
["LN05040475","Procure Component Material - Stoppers","2007-02-21","2007-04-17"]
["LN05040485","Component Fab & Assembly - Stoppers","2007-04-18","2007-07-12"]
["LN05040495","Perform Functional Testing - Stoppers","2007-07-13","2007-07-26"]
["LN05040505","Post Process & Test","2007-07-27","2007-08-09"]
["LN05040525","AVAIL: Stoppers Ready for BC2 Install","2007-08-10","2007-08-09"]
["LN05040535","AVAIL: Stoppers Ready for LTU Install","2007-08-10","2007-08-09"]
["LN05040545","Prep Bid Pak - Diagnostics Supports","2007-02-21","2007-03-06"]
["LN05040555","AWARD: Contract for Supports BC2-LTU","2007-03-07","2007-03-07"]
["LN05040565","Vendor Fab 1st Lot - Supports","2007-03-08","2007-05-02"]
["LN05040575","RCV: Supports from Vendor","2007-05-03","2007-05-02"]
["LN05040585","Procure Misc Materials - Diagnostics Supports","2007-02-21","2007-03-20"]
["LN05040595","Assemble Supports","2007-05-03","2007-05-31"]
["LN05040605","AVAIL: Supports Ready for Instl","2007-06-01","2007-05-31"]
["LN05050400","AWARD: Contract - Profile Monitor (1ea) Spare","2006-10-03","2006-10-03"]
["LN05050405","Vendor Fab 1st Lot (1) Spare","2006-10-04","2006-11-14"]
["LN05050410","RCV: 1st Lot from Vendor (1) Spare","2006-11-15","2006-11-14"]
["LN05050415","Vendor Fab Remaining Lot (1) Spare","2006-11-15","2007-01-12"]
["LN05050420","RCV: Remaining from Vendor (1) Spare","2007-01-16","2007-01-12"]
["LN05050425","Procure Component Material - Profile - (1) SPARE","2006-10-03","2006-11-29"]
["LN05050430","Component Fab & Assembly - Profile Mon (1) Spare","2007-01-16","2007-03-13"]
["LN05050435","Develop General Specifications / Analysis","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN05050440","Create / Remodel / Revise Dsn Documentation","2005-12-01","2006-01-30",null,"2005-12-01","2006-01-30"]
["LN05050445","Perform QC / Metrology (1ea) Spare","2007-03-14","2007-03-27"]
["LN05050450","Perform Functional Testing - Profile Mo(1) Spare","2007-03-28","2007-04-24"]
["LN05050455","Collect Component Performance Data (1ea) Spare","2007-04-25","2007-04-26"]
["LN05050460","Load Component Data Base (1ea) Spare","2007-04-27","2007-05-02"]
["LN05050465","Post Process & Test (1ea) Spare","2007-05-03","2007-05-16"]
["LN05050470","AVAIL: Profile Monitor (1ea) Spare","2007-05-17","2007-05-31"]
["LN05050475","Design YAG Screen Option","2005-12-01","2006-04-28",null,"2005-12-01"]
["LN05050480","Design Phosphor Screen Option","2006-02-01","2006-03-29"]
["LN05050485","Design OTR Screen Options","2005-12-01","2006-03-29",null,"2005-12-01"]
["LN05050490","Design Check","2006-03-30","2006-05-24"]
["LN05050495","Write Component Traveler","2006-05-01","2006-05-01"]
["LN05050500","Conduct Profile Monitors PDR","2006-05-25","2006-06-01"]
["LN05050505","Generate Detailed Procurement Plan","2006-06-02","2006-06-02"]
["LN05050510","Conduct Profile Monitors FDR","2006-06-02","2006-06-08"]
["LN05050515","COMP: Profile Monitors Design","2006-06-09","2006-06-08"]
["LN05050516","Prep Bid Pak - Profile Monitors","2006-06-05","2006-06-09"]
["LN05050517","AWARD: Contract - Profile Monitor BC1,BC2","2006-06-12","2006-06-12"]
["LN05050520","Vendor Fab 1st Lot","2006-06-13","2006-08-08"]
["LN05050521","RCV: Profile Monitors 1st Lot","2006-08-09","2006-08-08"]
["LN05050525","Vendor Fab Remaining Lot","2006-06-13","2006-08-08"]
["LN05050530","Procure Profile Monitor Components","2006-06-09","2006-07-07"]
["LN05050531","RCV: Profile Monitors Final Lot","2006-08-09","2006-08-08"]
["LN05050535","Procure Component Material - Profile Monitors","2006-06-09","2006-07-07"]
["LN05050540","Component Fab & Assembly - Profile Monitors","2006-08-09","2006-10-04"]
["LN05050545","Perform QC / Metrology","2006-10-05","2006-10-11"]
["LN05050550","Perform Functional Testing - Profile Monitors","2006-10-12","2006-10-18"]
["LN05050555","Post Process & Test","2006-10-19","2006-10-25"]
["LN05050560","AVAIL: Provile Monitors Ready for BC1 Install","2006-10-26","2006-10-25"]
["LN05050565","AVAIL: Profile Monitors Ready for BC2 Install","2006-10-26","2006-10-25"]
["LN05050580","Procure Misc Materials - Diagnostics Supports","2006-06-09","2006-07-07"]
["LN05050581","Prep Bid Bak - Supports","2006-06-09","2006-06-15"]
["LN05050582","AWARD: Contract for Supports BC1,BC2","2006-06-16","2006-06-16"]
["LN05050583","Vendor Fab BC1-BC2 Suports","2006-06-19","2006-08-14"]
["LN05050584","RCV: Supports from Vendor","2006-08-15","2006-08-14"]
["LN05050585","Assemble Supports","2006-08-15","2006-09-12"]
["LN05050590","AVAIL: Supts Ready for BC1, BC2 Instl","2006-09-13","2006-09-13"]
["LN05050601","Develop General Specifications / Analysis","2006-10-02","2006-10-13"]
["LN05050606","Create / Remodel / Revise Dsn Documentation","2006-10-02","2006-10-13"]
["LN05050611","Design YAG Screen Option","2006-10-16","2006-12-12"]
["LN05050616","Design Phosphor Screen Option","2006-10-16","2006-12-12"]
["LN05050621","Design OTR Screen Options","2006-10-16","2006-12-12"]
["LN05050626","Design Check","2006-12-13","2007-02-23"]
["LN05050631","Write Component Traveler","2006-12-13","2006-12-13"]
["LN05050636","Conduct Profile Monitors PDR","2007-02-26","2007-03-02"]
["LN05050641","Generate Detailed Procurement Plan","2007-03-05","2007-03-05"]
["LN05050646","Conduct Profile Monitors FDR","2007-03-05","2007-03-09"]
["LN05050651","COMP: Profile Monitors Design","2007-03-12","2007-03-09"]
["LN05050656","Prep Bid Pak - Profile Monitors","2007-03-06","2007-03-12"]
["LN05050661","AWARD: Contract - Profile Monitor L03-LTU","2007-03-13","2007-03-13"]
["LN05050666","Vendor Fab L03-LTU","2007-03-14","2007-05-08"]
["LN05050671","RCV: Profile Monitors 1st Lot","2007-05-09","2007-05-08"]
["LN05050676","Vendor Fab Remaining Lot","2007-03-14","2007-05-08"]
["LN05050681","Procure Profile Monitor Components","2007-03-12","2007-04-06"]
["LN05050686","RCV: Profile Monitors Final Lot","2007-05-09","2007-05-08"]
["LN05050691","Procure Component Material - Profile Monitors","2007-03-12","2007-04-06"]
["LN05050696","Component Fab & Assembly - Profile Monitors","2007-05-09","2007-07-05"]
["LN05050701","Perform QC / Metrology","2007-07-06","2007-07-12"]
["LN05050706","Perform Functional Testing - Profile Monitors","2007-07-13","2007-07-19"]
["LN05050711","Post Process & Test","2007-07-20","2007-07-26"]
["LN05050726","AVAIL: Profile Monitors Ready for L03 Install","2007-07-27","2007-07-26"]
["LN05050731","AVAIL: Profile Monitors Ready for LTU Install","2007-07-27","2007-07-26"]
["LN05050736","Procure Misc Materials - Diagnostics Supports","2007-03-12","2007-04-06"]
["LN05050741","Prep Bid Bak - Supports","2007-03-12","2007-03-16"]
["LN05050746","AWARD: Contract for Supports L03-LTU","2007-03-19","2007-03-19"]
["LN05050751","Vendor Fab L03-LTU Suports","2007-03-20","2007-05-14"]
["LN05050756","RCV: Supports from Vendor","2007-05-15","2007-05-14"]
["LN05050761","Assemble Supports","2007-05-15","2007-06-12"]
["LN05050766","AVAIL: Supts Ready for L03, LTU Instl","2007-06-13","2007-06-13"]
["LN05070300","Procure Component Mtrl - Bunch Len - (1) SPARE","2006-10-03","2006-10-30"]
["LN05070305","Component Fab & Assy - Bunch Length (1ea) Spare","2006-10-31","2006-11-29"]
["LN05070320","Perform QC / Metrology (1ea) Spare","2006-11-30","2007-01-11"]
["LN05070325","Perform Func Testing - Bunch Length (1ea) Spare","2007-01-12","2007-01-16"]
["LN05070330","Collect Component Performance Data (1ea) Spare","2007-01-17","2007-01-18"]
["LN05070335","Load Component Data Base (1ea) Spare","2007-01-19","2007-01-22"]
["LN05070340","Post Process & Test (1ea) Spare","2007-01-23","2007-02-05"]
["LN05070345","AVAIL: Bunch Length Monitors (1ea) Spare","2007-02-06","2007-02-05"]
["LN05070350","Develop General Specifications / Analysis","2005-12-01","2006-01-31",null,"2005-12-01","2006-01-31"]
["LN05070360","Create / Remodel / Revise Dsn Documentation","2005-12-01","2006-01-31",null,"2005-12-01","2006-01-31"]
["LN05070380","Write Component Traveler","2006-02-01","2006-02-01"]
["LN05070390","Conduct B/L Monitors PDR","2006-02-02","2006-02-02"]
["LN05070400","Generate Detailed Procurement Plan","2006-02-03","2006-02-03"]
["LN05070410","Conduct B/L Monitors FDR","2006-02-06","2006-02-06"]
["LN05070420","COMP: B/L Monitors Design","2006-02-07","2006-02-06"]
["LN05070425","Procure Component Material - Bunch Length Mon","2006-02-07","2006-03-07"]
["LN05070430","Component Fab & Assembly - Bunch Length Monit","2006-03-08","2006-04-04"]
["LN05070440","Perform QC / Metrology","2006-04-05","2006-04-06"]
["LN05070450","Perform Functional Testing - Bunch Length Mon","2006-04-07","2006-04-13"]
["LN05070460","Collect Component Performance Data","2006-04-07","2006-04-13"]
["LN05070470","Post Process & Test","2006-04-14","2006-04-20"]
["LN05070480","AVAIL: Bnch Length Monitors Ready for BC1 Instl","2006-04-21","2006-04-20"]
["LN05070490","AVAIL: Bnch Length Monitors Ready for BC2 Instl","2006-04-21","2006-04-20"]
["LN05070500","AVAIL: Bnch Length Monitors Ready for LTU Instl","2006-04-21","2006-04-20"]
["LN05070510","Prep Bid Pak - Diagnostics Supports","2006-02-07","2006-02-07"]
["LN05070520","AWARD: Contract for Diagnostics Supports","2006-02-08","2006-02-08"]
["LN05070530","Vendor Fab 1st Lot - Supports","2006-02-09","2006-04-06"]
["LN05070540","RCV: 1st Lot of Supports","2006-04-07","2006-04-06"]
["LN05070550","Procure Misc Materials - Diagnostics Supports","2006-04-07","2006-05-04"]
["LN05070560","Assemble Supports","2006-05-05","2006-05-11"]
["LN05070570","AVAIL: Supports Ready for BC1, BC2, LTU Instl","2006-05-12","2006-05-11"]
["LN05080209","Write ICD - Beam Loss Monitor","2007-01-02","2007-01-08"]
["LN05080219","Produce Common Layout","2007-01-09","2007-02-06"]
["LN05080229","Develop General Specifications / Analysis","2007-02-07","2007-02-21"]
["LN05080239","Revise  Design Documentation","2007-02-22","2007-03-07"]
["LN05080259","Write Component Traveler","2007-03-08","2007-03-14"]
["LN05080269","Generate Detailed Procurement Plan","2007-03-15","2007-03-21"]
["LN05080279","Conduct Beam Loss Monitors FDR","2007-03-22","2007-03-28"]
["LN05080289","COMP: Beam Loss Monitors Design","2007-03-29","2007-03-28"]
["LN05080300","Procure Component Material - BLM - (2) SPARES","2006-10-03","2007-03-12"]
["LN05080302","Component Fab & Assy - Bm Lss Mon (2) Spares","2008-10-01","2009-02-04"]
["LN05080308","Perform QC / Metrology (2ea) Spares","2009-02-05","2009-02-18"]
["LN05080309","Procure Component Material - Beam Loss Monitors","2007-03-29","2007-06-21"]
["LN05080310","Perform Functional Testing - Bm Lss Mo(2) Spares","2009-02-19","2009-03-04"]
["LN05080312","Collect Component Performance Data (2ea) Spares","2009-03-05","2009-03-11"]
["LN05080314","Load Component Data Base (2ea) Spares","2009-03-12","2009-03-18"]
["LN05080316","Post Process & Test (2ea) Spares","2009-03-19","2009-03-25"]
["LN05080318","AVAIL: Beam Loss Monitor - (2ea) Spares","2009-03-26","2009-03-25"]
["LN05080319","Component Fab & Assembly - Beam Loss Monitors","2007-06-22","2007-07-20"]
["LN05080329","Perform Functional Testing - Beam Loss Monito","2007-07-23","2007-08-03"]
["LN05080339","Post Process & Test","2007-08-06","2007-08-17"]
["LN05080349","AVAIL: Bm Loss Monitor (PIC) Ready for L03 Instl","2007-08-20","2007-08-17"]
["LN05080359","AVAIL: Bm Loss Monitor (PIC) Ready for LTU Instl","2007-08-20","2007-08-17"]
["LN05080369","Prep Bid Pak - Diagnostics Supports","2007-03-29","2007-03-29"]
["LN05080379","AWARD: Contrct for Diagnostics Supports","2007-03-30","2007-03-30"]
["LN05080389","Vendor Fab Supports","2007-04-02","2007-04-27"]
["LN05080399","RCV: Diagnostics Supports from Vendor","2007-04-30","2007-04-27"]
["LN05080409","Procure Misc Materials - Diagnostics Supports","2007-04-30","2007-05-25"]
["LN05080419","Assemble Supports","2007-05-29","2007-06-25"]
["LN05080429","AVAIL: Supports Ready for L03, LTU Instl","2007-06-26","2007-06-25"]
["LN05080439","Write ICD - Beam Loss Monitor","2007-06-01","2007-06-07"]
["LN05080449","Produce Common Layout","2007-06-08","2007-07-06"]
["LN05080459","Develop General Specifications / Analysis","2007-07-09","2007-07-13"]
["LN05080469","Revise  Design Documentation","2007-07-16","2007-07-20"]
["LN05080489","Write Component Traveler","2007-07-23","2007-07-27"]
["LN05080499","Conduct Beam Loss Monitors PDR","2007-07-30","2007-08-03"]
["LN05080509","Generate Detailed Procurement Plan","2007-08-06","2007-08-06"]
["LN05080519","Conduct Beam Loss Monitors FDR","2007-08-07","2007-08-13"]
["LN05080529","COMP: Beam Loss Monitor Design","2007-08-14","2007-08-13"]
["LN05080539","Procure Component Material - Beam Loss Monitors","2007-08-14","2007-09-11"]
["LN05080549","Component Fab & Assembly - Beam Loss Monitors","2007-09-12","2007-12-06"]
["LN05080559","Perform Functional Testing - Beam Loss Monito","2007-12-07","2008-01-22"]
["LN05080569","Post Process & Test","2008-01-23","2008-02-20"]
["LN05080579","AVAIL: Bm Loss Monitor(PLIC) Ready for LTU Instl","2008-02-21","2008-02-20"]
["LN05080589","Prep Bid Pak - Diagnostics Supports","2007-08-14","2007-08-14"]
["LN05080599","AWARD: Contract for Diagnostics Supports","2007-08-15","2007-08-15"]
["LN05080609","Vendor Fab Supports","2007-08-16","2007-10-11"]
["LN05080619","RCV: Diagnostics Support from Vendor","2007-10-12","2007-10-11"]
["LN05080629","Procure Misc Materials - Diagnostics Supports","2007-10-12","2007-11-08"]
["LN05080639","Assemble Supports","2007-11-09","2007-11-26"]
["LN05080649","AVAIL: Supports Ready for LTU Instl","2007-11-27","2007-11-27"]
["LN05090300","Write ICD - Single Beam Dump","2006-10-03","2006-10-04"]
["LN05090310","Produce Common Layout","2006-10-05","2006-11-01"]
["LN05090320","Develop General Specifications / Analysis","2006-11-02","2006-11-15"]
["LN05090330","Create / Remodel / Revise Dsn Documentation","2006-11-16","2006-12-15"]
["LN05090340","Design Check","2007-01-02","2007-03-28"]
["LN05090350","Write Component Traveler","2007-01-02","2007-01-08"]
["LN05090370","Generate Detailed Procurement Plan","2007-01-09","2007-01-09"]
["LN05090390","COMP: Single Beam Dump Design","2007-03-29","2007-03-28"]
["LN05090391","Procure Component Material - Single Beam Dump","2007-03-29","2007-04-25"]
["LN05090400","Component Fab & Assembly - Single Beam Dump","2007-04-26","2007-05-23"]
["LN05090402","Post Process & Test","2007-05-24","2007-06-07"]
["LN05090403","AVAIL: Single Beam Dump Ready for LTU Install","2007-06-08","2007-06-07"]
["LN05090410","Prep Bid Pak - Diagnostics Supports","2007-05-24","2007-05-24"]
["LN05090420","AWARD: Contract for Daignostics Supports","2007-05-25","2007-05-25"]
["LN05090430","Vendor Fab Supports","2007-05-29","2007-08-21"]
["LN05090440","RCV: Diagnostics Supports from Vendor","2007-08-22","2007-08-21"]
["LN05090450","Procure Misc Materials - Diagnostics Supports","2007-08-22","2007-10-17"]
["LN05090460","Perform QC & Inspection - Diagnostic Supports","2007-10-18","2007-10-24"]
["LN05090470","Assemble Supports","2007-10-25","2007-11-07"]
["LN05090480","AVAIL: Supports Ready for LTU Installation","2007-11-08","2007-11-07"]
["LN05100301","Receive Electron Beam Dump Requirements","2006-10-03","2006-10-03"]
["LN05100310","Write ICD - Electron Beam Dump","2006-10-04","2006-10-04"]
["LN05100320","Collect Area Specific Requirements","2006-10-05","2006-10-11"]
["LN05100325","Engineering Analysis","2006-10-12","2006-10-18"]
["LN05100340","Produce Common Layout","2006-10-19","2006-10-25"]
["LN05100350","Develop General Specifications / Analysis","2006-10-26","2006-11-01"]
["LN05100360","Create / Remodel / Revise Dsn Documentation","2006-11-02","2006-12-01"]
["LN05100370","Write Component Traveler","2006-12-04","2006-12-04"]
["LN05100380","Conduct Electron Beam Dump PDR","2006-12-05","2006-12-05"]
["LN05100390","Generate Detailed Procurement Plan","2006-12-06","2006-12-06"]
["LN05100400","Conduct Electron Beam Dump FDR","2006-12-07","2006-12-07"]
["LN05100402","COMP: Electron Beam Dump Design","2006-12-08","2006-12-07"]
["LN05100410","Procure Component Material - Electron Beam Dump","2006-12-08","2007-03-20"]
["LN05100415","Component Fab & Assembly - Electron Beam Dump","2007-03-21","2007-06-13"]
["LN05100420","Perform QC / Metrology","2007-06-14","2007-06-20"]
["LN05100430","Post Process & Test","2007-06-21","2007-07-05"]
["LN05100433","AVAIL: Electron Beam Dump Ready for LTU Instl","2007-07-06","2007-07-05"]
["LN05100440","Prep Bid Pak - Diagnostics Supports","2006-12-08","2006-12-08"]
["LN05100450","Evaluate Vendor Proposals - Supports","2006-12-11","2006-12-11"]
["LN05100460","AWARD: Contract for Diagnostics Supports","2006-12-12","2006-12-12"]
["LN05100470","Vendor Fab Diagnostics Supports","2006-12-13","2007-01-25"]
["LN05100480","RCV: Daignostics Support from Vendor","2007-01-26","2007-01-25"]
["LN05100490","Procure Misc Materials - Diagnostics Supports","2007-01-26","2007-03-09"]
["LN05100500","Perform QC & Inspection - Diagnostic Supports","2007-03-12","2007-03-12"]
["LN05100510","Assemble Supports","2007-03-13","2007-03-26"]
["LN05100521","AVAIL: Supports Ready for Installation","2007-03-27","2007-03-26"]
["LN05110400","Procure Hardware - Protection Collimatr - SPARES","2006-10-03","2006-10-30"]
["LN05110406","Write ICD - Protection Collimator","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN05110426","Develop General Specification/Analysis","2005-12-01","2006-02-01",null,"2005-12-01"]
["LN05110446","Produce Common Layout","2005-12-01","2006-02-07",null,"2005-12-01"]
["LN05110456","Develop General Specifications / Analysis","2005-12-01","2006-02-02",null,"2005-12-01"]
["LN05110466","Create / Remodel / Revise Dsn Documentation","2006-02-03","2006-03-31"]
["LN05110467","Design Check","2006-02-03","2006-03-31"]
["LN05110476","Write Component Traveler","2006-04-03","2006-04-06"]
["LN05110486","Conduct Protection Collimator PDR","2006-04-07","2006-04-07"]
["LN05110496","Generate Detailed Procurement Plan","2006-04-10","2006-04-10"]
["LN05110506","Conduct Protection Collimator FDR","2006-04-11","2006-04-11"]
["LN05110516","COMP: Protection Collimator Design","2006-04-12","2006-04-11"]
["LN05110526","Prep Bid Pak - Protection Collimator","2006-04-12","2006-04-13"]
["LN05110536","RELEASE: RFP - Protection Collimators","2006-04-14","2006-04-13"]
["LN05110546","Vendors Prep Proposals - Protection Collimator","2006-04-14","2006-05-11"]
["LN05110556","RCV: Proposals from Vendors","2006-05-12","2006-05-11"]
["LN05110566","Evaluate Vendor Proposals","2006-05-12","2006-05-17"]
["LN05110576","AWARD: Contract - Protection Collimator","2006-05-18","2006-05-18"]
["LN05110586","Vendor Fab 1st Lot","2006-05-19","2006-06-16"]
["LN05110596","RCV: 1st Lot Diagnostics Equip from Vendor","2006-06-19","2006-06-16"]
["LN05110606","Procure Component Material - Protection Collimat","2006-04-12","2006-05-09"]
["LN05110616","Component Fab & Assembly - Protection Collimat","2006-06-19","2006-07-17"]
["LN05110646","Post Process & Test","2006-07-18","2006-07-31"]
["LN05110656","AVAIL: Protection Collimator Ready for BC1 Instl","2006-08-01","2006-07-31"]
["LN05110657","AVAIL: Protection Collimator Ready for BC2 Instl","2006-08-01","2006-07-31"]
["LN05110658","AVAIL: Protection Collimator Ready for LTU Instl","2006-08-01","2006-07-31"]
["LN05110668","Prep Bid Pak - Diagnostics Supports","2006-04-12","2006-04-12"]
["LN05110678","RELEASE: RFP - Diagnostics Supports","2006-04-13","2006-04-12"]
["LN05110688","Vendors Prep Proposals - Supports","2006-04-13","2006-05-10"]
["LN05110708","Evaluate Vendor Proposals - Supports","2006-05-11","2006-05-16"]
["LN05110710","AWARD: Contract for Supports","2006-05-17","2006-05-17"]
["LN05110718","Vendor Fab 1st Lot - Supports","2006-05-18","2006-06-15"]
["LN05110728","RCV: 1st Lot Diagnostics Supports from Vendor","2006-06-16","2006-06-15"]
["LN05110738","Procure Misc Materials - Diagnostics Supports","2006-04-12","2006-05-09"]
["LN05110788","Assemble Supports","2006-06-16","2006-06-23"]
["LN05110808","AVAIL: Supports Ready for BC1, BC2, LTU Instl","2006-06-26","2006-06-23"]
["LN05120371","Produce Common Layout","2005-12-01","2006-01-30",null,"2005-12-01","2006-01-30"]
["LN05120381","Develop General Specifications / Analysis","2005-12-01","2006-02-28",null,"2005-12-01"]
["LN05120391","Create / Remodel / Revise Dsn Documentation","2005-12-01","2006-03-13",null,"2005-12-01"]
["LN05120400","Procure Hardware - Movable Collimator - SPARES","2006-10-03","2007-01-11"]
["LN05120401","Write Component Traveler","2006-03-14","2006-03-21"]
["LN05120421","Generate Detailed Procurement Plan","2006-03-22","2006-03-22"]
["LN05120441","COMP: Movable Collimator Design","2006-03-23","2006-03-22"]
["LN05120451","RELEASE: RFP - Movable Collimators","2006-03-23","2006-03-22"]
["LN05120461","Vendors Prep Proposals - Movable Collimator","2006-03-23","2006-04-19"]
["LN05120471","RCV: Proposals from Vendors","2006-04-20","2006-04-19"]
["LN05120481","Evaluate Vendor Proposals","2006-04-20","2006-04-25"]
["LN05120485","AWARD: Contract - BC1 Movable Collimator","2006-04-26","2006-04-26"]
["LN05120491","Vendor Fab 1st Lot","2006-04-27","2006-05-24"]
["LN05120501","RCV: 1st Lot Diagnostics Equip from Vendor","2006-05-25","2006-05-24"]
["LN05120511","Procure Component Material - Movable Collimator","2006-07-24","2006-10-16"]
["LN05120521","Component Fab & Assembly - Movable Collimator","2006-08-21","2006-11-13"]
["LN05120531","Perform QC / Metrology","2006-11-14","2006-11-29"]
["LN05120541","Perform Functional Testing - Movable Collimat","2006-11-30","2006-12-13"]
["LN05120551","Post Process & Test","2006-12-14","2007-01-11"]
["LN05120561","AVAIL: Movable Collimators Ready for BC1 Instl","2007-01-12","2007-01-11"]
["LN05120571","Prep Bid Pak - Diagnostics Supports","2006-03-23","2006-03-24"]
["LN05120581","RELEASE: RFP - Diagnostics Supports","2006-03-27","2006-03-24"]
["LN05120591","Vendors Prep Proposals - Supports","2006-03-27","2006-04-21"]
["LN05120601","RCV: Proposals from Vendors - Supports","2006-04-24","2006-04-21"]
["LN05120611","Evaluate Vendor Proposals - Supports","2006-04-24","2006-04-27"]
["LN05120615","AWARD: BC1 Contract for Supports","2006-04-28","2006-04-28"]
["LN05120621","Vendor Fab 1st Lot - Supports","2006-05-01","2006-05-26"]
["LN05120631","RCV: 1st Lot Diagnostics Supports from Vendor","2006-05-30","2006-05-26"]
["LN05120641","Procure Misc Materials - Diagnostics Supports","2006-07-24","2006-08-18"]
["LN05120651","Assemble Supports","2006-08-21","2006-09-01"]
["LN05120671","AVAIL: Supports Ready for BC1 Instl","2006-09-05","2006-09-01"]
["LN05120680","Produce Common Layout","2007-05-01","2007-05-29"]
["LN05120685","Develop General Specifications / Analysis","2007-05-30","2007-06-12"]
["LN05120690","Create / Remodel / Revise Dsn Documentation","2007-03-20","2007-06-12"]
["LN05120695","Write Component Traveler","2007-06-13","2007-06-20"]
["LN05120700","Generate Detailed Procurement Plan","2007-06-21","2007-06-21"]
["LN05120705","COMP: Movable Collimator Design","2007-06-22","2007-06-21"]
["LN05120710","RELEASE: RFP - Movable Collimators","2007-06-22","2007-06-21"]
["LN05120715","Vendors Prep Proposals - Movable Collimator","2007-06-22","2007-07-20"]
["LN05120720","RCV: Proposals from Vendors","2007-07-23","2007-07-20"]
["LN05120725","Evaluate Vendor Proposals","2007-07-23","2007-07-26"]
["LN05120730","AWARD: Contract - LTU Movable Collimator","2007-07-27","2007-07-27"]
["LN05120735","Vendor Fab 1st Lot","2007-07-30","2007-08-24"]
["LN05120740","RCV: 1st Lot Diagnostics Equip from Vendor","2007-08-27","2007-08-24"]
["LN05120745","Procure Component Material - Movable Collimator","2007-06-22","2007-09-17"]
["LN05120750","Component Fab & Assembly - Movable Collimator","2007-08-27","2007-11-19"]
["LN05120755","Perform QC / Metrology","2007-11-20","2007-12-05"]
["LN05120760","Perform Functional Testing - Movable Collimat","2007-12-06","2008-01-04"]
["LN05120765","Post Process & Test","2008-01-07","2008-01-18"]
["LN05120770","AVAIL: Movable Collimators Ready for LTU Instl","2008-01-22","2008-01-18"]
["LN05120775","Prep Bid Pak - Diagnostics Supports","2007-06-22","2007-06-25"]
["LN05120780","RELEASE: RFP - Diagnostics Supports","2007-06-26","2007-06-25"]
["LN05120785","Vendors Prep Proposals - Supports","2007-06-26","2007-07-24"]
["LN05120790","RCV: Proposals from Vendors - Supports","2007-07-25","2007-07-24"]
["LN05120795","Evaluate Vendor Proposals - Supports","2007-07-25","2007-07-30"]
["LN05120800","AWARD: LTU Contract for Supports","2007-07-31","2007-07-31"]
["LN05120805","Vendor Fab 1st Lot - Supports","2007-08-01","2007-08-28"]
["LN05120810","RCV: 1st Lot Diagnostics Supports from Vendor","2007-08-29","2007-08-28"]
["LN05120815","Procure Misc Materials - Diagnostics Supports","2007-08-01","2007-08-28"]
["LN05120820","Assemble Supports","2007-08-29","2007-09-12"]
["LN05120825","AVAIL: Supports Ready for LTU Instl","2007-09-13","2007-09-12"]
["LN05130400","Procure Hardware - Single Beam Dump - SPARES","2006-10-03","2006-11-29"]
["LN05130410","Write ICD - Single Beam Dump","2007-05-15","2007-05-21"]
["LN05130420","Produce Common Layout","2007-05-22","2007-05-29"]
["LN05130430","Develop General Specifications / Analysis","2007-05-30","2007-06-05"]
["LN05130440","Create / Remodel / Revise Dsn Documentation","2007-06-06","2007-07-03"]
["LN05130450","Design Check","2007-07-05","2007-08-29"]
["LN05130460","Write Component Traveler","2007-07-05","2007-07-11"]
["LN05130470","Conduct Single Beam Dump PDR","2007-07-12","2007-07-18"]
["LN05130480","Generate Detailed Procurement Plan","2007-07-19","2007-07-19"]
["LN05130490","Conduct Single Beam Dump FDR","2007-07-20","2007-07-26"]
["LN05130500","COMP: Single Beam Dump Design","2007-08-30","2007-08-29"]
["LN05130501","Prep Bid Pak - Safety Dump","2007-08-30","2007-08-30"]
["LN05130502","AWARD: Contract for Safety Dump","2007-08-31","2007-08-31"]
["LN05130503","Vendor Fab - Safety Dump","2007-09-04","2007-10-29"]
["LN05130504","RCV: Saftey Dump from Vendor","2007-10-30","2007-10-30"]
["LN05130510","Procure Component Material - Single Beam Dump","2007-08-30","2007-09-27"]
["LN05130520","Component Fab & Assembly - Single Beam Dump","2007-10-31","2007-11-29"]
["LN05130530","Post Process & Test","2007-11-30","2007-12-13"]
["LN05130540","AVAIL: Single Beam Dump Ready for LTU Install","2007-12-14","2007-12-13"]
["LN05130560","Assemble Supports","2007-11-29","2007-12-12"]
["LN05130570","AVAIL: Supports Ready for LTU Instl","2007-12-13","2007-12-12"]
["LN05130580","AWARD: Contract for Diagnostics Supports","2007-08-30","2007-08-30"]
["LN05130590","Vendor Fab Diagnostics Supports","2007-08-31","2007-10-26"]
["LN05130600","RCV: Diagnostics Supports from Vendor","2007-10-29","2007-10-29"]
["LN05130610","Procure Misc Materials - Diagnostics Supports","2007-10-30","2007-11-28"]
["LN06","LINAC RF SUBSYSTEM SUMMARY","2005-05-02","2008-01-02",null,"2005-05-02"]
["LN0601","S-BAND LOW LEVEL RF SYSTEM SUMMARY","2005-06-01","2006-09-12",null,"2005-06-01"]
["LN06010005","Prepare for Final Desgin Review (FDR)","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["LN06010010","Conduct S-Band Low Level FDR","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["LN06010015","COMP: S-Band Low Level Design","2005-07-01","2005-06-30",null,"2005-07-01","2005-06-30"]
["LN06010020","Generate Detailed Procurement Plan","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["LN06010025","Procure Coupler Connectors","2005-07-01","2005-07-30",null,"2005-07-01","2005-07-30"]
["LN06010030","Cold Test & Fab - S-Band Low Level Equipment","2005-10-31","2005-12-30",null,"2005-10-31","2005-12-30"]
["LN06010035","AVAIL: S-Band Low Level Equipment Ready for Inst","2006-02-14","2006-02-13"]
["LN06010045","Purchase Coupler Materials (5)","2005-06-23","2005-08-30",null,"2005-06-23","2005-08-30"]
["LN06010055","Fabricate Coupler Spools (5)","2005-06-23","2005-09-30",null,"2005-06-23","2005-09-30"]
["LN06010060","Design Input WG Modifications","2005-06-01","2005-06-20",null,"2005-06-01","2005-06-20"]
["LN06010065","Assemble Coupler Spools (5)","2005-06-15","2005-09-30",null,"2005-06-15","2005-09-30"]
["LN06010075","Purchase Input Materials (2)","2005-06-01","2005-06-28",null,"2005-06-01","2005-06-28"]
["LN06010085","Fabricate Input WG (2)","2005-10-03","2006-02-28",null,"2005-10-03"]
["LN06010095","Assemble Input WG (2)","2005-10-03","2006-02-28",null,"2005-10-03"]
["LN0602","S-BAND HP WAVEGUIDE SYSTEM SUMMARY","2005-06-01","2006-09-12",null,"2005-06-01"]
["LN06020005","Design S-Band Waveguide","2005-06-01","2005-09-30",null,"2005-06-01","2005-09-30"]
["LN06020010","Design WG Supports","2005-06-01","2005-07-13",null,"2005-06-01","2005-07-13"]
["LN06020025","Prepare for Prelim Design Review (PDR)","2005-07-14","2005-07-18",null,"2005-07-14","2005-07-18"]
["LN06020030","Conduct Prelim Design Rev - S-Band HP WG System","2005-07-19","2005-07-19",null,"2005-07-19","2005-07-19"]
["LN06020035","Generate Detailed Procurement Plan","2005-07-20","2005-07-20",null,"2005-07-20","2005-07-20"]
["LN06020040","Create Cold Test Plan","2005-07-21","2005-07-27",null,"2005-07-21","2005-07-27"]
["LN06020045","Establish Subordinate Work Orders","2005-07-28","2005-07-28",null,"2005-07-28","2005-07-28"]
["LN06020050","Prepare for Final Desgin Review (FDR)","2005-07-29","2005-09-30",null,"2005-07-29","2005-09-30"]
["LN06020055","Conduct Final Design Rev - S-Band HP WG System","2005-09-01","2005-09-30",null,"2005-09-01","2005-09-30"]
["LN06020060","COMP: S-Band HP WG System Design","2005-10-01","2005-09-30",null,"2005-10-01","2005-09-30"]
["LN06020062","RELEASE: RFP - Skarpass Flanges","2005-08-31","2005-08-30",null,"2005-08-31","2005-08-30"]
["LN06020064","Vendors Prep Proposals - S-Band HP Sys Component","2006-02-01","2005-08-30",null,null,"2005-08-30"]
["LN06020065","Prep Bid Pak - Skarpass Flanges","2006-02-01","2005-08-30",null,null,"2005-08-30"]
["LN06020066","RCV: Proposals from Vendors","2005-08-31","2005-08-30",null,"2005-08-31","2005-08-30"]
["LN06020068","Evaluate Vendor Proposals","2006-02-01","2005-08-30",null,null,"2005-08-30"]
["LN06020070","AWARD: Contract for Skarpass Flanges","2006-02-01","2005-08-30",null,null,"2005-08-30"]
["LN06020072","Vendor Fab - Skarpass Flanges","2006-02-01","2005-08-30",null,null,"2005-08-30"]
["LN06020090","RELEASE: RFP - S-Band Waveguide","2005-09-01","2005-09-30",null,"2005-09-01","2005-09-30"]
["LN06020092","Vendors Prep Proposals - S-Band Waveguide","2005-09-01","2005-09-30",null,"2005-09-01","2005-09-30"]
["LN06020094","RCV: Proposals from Vendors","2005-10-15","2005-10-14",null,"2005-10-15","2005-10-14"]
["LN06020096","Evaluate Vendor Proposals","2005-10-03","2005-10-14",null,"2005-10-03","2005-10-14"]
["LN06020098","AWARD: Contract - S-Band Waveguide","2006-01-01","2006-02-21",null,"2006-01-01"]
["LN06020100","Vendor Fab & Assy - S-Band Waveguide","2005-08-01","2006-03-22",null,"2005-08-01"]
["LN06020105","RCV: from Vendor S-Band Waveguide","2006-03-23","2006-03-22"]
["LN06020115","Procure Waveguide Cooling","2005-09-01","2005-09-30",null,"2005-09-01","2005-09-30"]
["LN06020120","RCV: Waveguide Cooling","2006-01-31","2006-01-30",null,"2006-01-31","2006-01-30"]
["LN06020125","Procure Assembly Hardware","2005-12-01","2006-04-17",null,"2005-12-01"]
["LN06020130","RCV: Assembly Hardware","2006-04-18","2006-04-17"]
["LN06020135","Fab & Cold Test - Cold Test Hardware","2006-02-01","2006-03-15"]
["LN06020140","Fab & Cold Test - Waveguide Straights","2006-03-23","2006-05-03"]
["LN06020145","Fab & Cold Test - Waveguide Components","2006-05-04","2006-06-15"]
["LN06020150","Fab & Test - Waveguide Supports","2006-06-16","2006-07-21"]
["LN06020155","Collect Component Performance Data","2006-07-24","2006-07-28"]
["LN06020160","Load Component Data Base","2006-07-24","2006-07-28"]
["LN06020165","Receive System / Sub Assemblies","2006-07-31","2006-07-31"]
["LN06020170","Post Process Waveguide","2006-08-01","2006-09-12"]
["LN06020174","RCV: Skarpass Flanges from Vendor","2006-02-01","2006-01-31"]
["LN06020185","AVAIL: S-Band High Pwr Equip L01 Ready for Instl","2006-09-13","2006-09-12"]
["LN06020188","Prep Bid Pak - S-Band Waveguide","2005-08-01","2005-08-30",null,"2005-08-01","2005-08-30"]
["LN06020190","AVAIL: S-Band High Pwr Equip BC1 Ready for Instl","2006-09-13","2006-09-12"]
["LN06020195","AVAIL: S-Band High Pwr Equip L02 Ready for Instl","2006-09-13","2006-09-12"]
["LN06020200","AVAIL: S-Band High Pwr Equip BC2 Ready for Instl","2006-09-13","2006-09-12"]
["LN06020205","AVAIL: S-Band High Pwr Equip L03 Ready for Instl","2006-09-13","2006-09-12"]
["LN0603","S-BAND STRUCTURES SUMMARY","2005-05-02","2005-07-30",null,"2005-05-02","2005-07-30"]
["LN06030000","RCV: 9.5ft Structures & Strongbacks","2005-05-02","2005-05-01",null,"2005-05-02","2005-05-01"]
["LN06030005","RF Evaluation of 9.5ft Structures & Strongbacks","2005-05-02","2005-06-30",null,"2005-05-02","2005-06-30"]
["LN06030010","Design Strongback Girder Supports","2005-05-02","2005-06-30",null,"2005-05-02","2005-06-30"]
["LN06030020","Design TV Section Supports","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["LN06030025","Prepare for Prelim Design Review (PDR)","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["LN06030030","Conduct Prelim Design Review (PDR) - S Bnd Struc","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["LN06030035","Generate Detailed Procurement Plan","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["LN06030040","Create Cold Test Plan","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["LN06030045","Establish Subordinate Work Orders","2005-07-01","2005-07-01",null,"2005-07-01","2005-07-01"]
["LN06030050","Prepare for Final Desgin Review (FDR)","2005-07-02","2005-07-07",null,"2005-07-02","2005-07-07"]
["LN06030055","Conduct Final Design Review (FDR) - S Bnd Struc","2005-07-08","2005-07-08",null,"2005-07-08","2005-07-08"]
["LN06030060","COMP: S-Band Structures Design","2005-07-09","2005-07-08",null,"2005-07-09","2005-07-08"]
["LN06030075","Bead Pull Structures","2005-05-02","2005-06-30",null,"2005-05-02","2005-06-30"]
["LN06030090","Fabricate 9.5ft Supports","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["LN06030100","Collect Component Performance Data","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["LN06030105","Load Component Data Base","2005-07-01","2005-07-08",null,"2005-07-01","2005-07-08"]
["LN06030110","Receive System / Sub Assemblies","2005-07-11","2005-07-11",null,"2005-07-11","2005-07-11"]
["LN06030115","Post Process 9.5 ft Structures","2006-02-01","2005-07-30",null,null,"2005-07-30"]
["LN06030130","AVAIL: S-Band Structures Ready for L01 Instl","2005-07-31","2005-07-30",null,"2005-07-31","2005-07-30"]
["LN06030135","AVAIL: S-Band Structures Ready for BC1 Instl","2005-07-31","2005-07-30",null,"2005-07-31","2005-07-30"]
["LN0604","X-BAND LOW LEVEL RF SUMMARY","2005-05-02","2007-01-25",null,"2005-05-02"]
["LN06040004","Write X-Band LLRF ICD","2005-05-02","2005-06-14",null,"2005-05-02","2005-06-14"]
["LN06040008","Design X-Band LLRF System","2005-10-03","2006-03-15",null,"2005-10-03"]
["LN06040010","Conduct Prelim Dsign Review (PDR) - X Bnd LL Sys","2006-03-16","2006-03-16"]
["LN06040012","Design X-Band LLRF System","2006-03-17","2006-04-07"]
["LN06040014","Conduct Final Design Review (FDR) - X Bnd LL Sys","2006-04-10","2006-04-10"]
["LN06040016","COMP: X-Band Low Level RF Design","2006-04-11","2006-04-10"]
["LN06040018","Prep Bid Pak - X-Band Analyzer","2005-07-01","2005-07-05",null,"2005-07-01","2005-07-05"]
["LN06040020","RELEASE: RFP - X-Band Analyzer","2005-07-06","2005-07-05",null,"2005-07-06","2005-07-05"]
["LN06040022","Vendors Prep Proposals - X-Band Analyzer","2005-07-06","2005-07-20",null,"2005-07-06","2005-07-20"]
["LN06040024","RCV: Proposals from Vendors","2005-07-21","2005-07-20",null,"2005-07-21","2005-07-20"]
["LN06040026","Evaluate Vendor Proposals","2005-07-21","2005-07-30",null,"2005-07-21","2005-07-30"]
["LN06040028","AWARD: Contract X-Band Analyzer","2006-02-01","2005-07-30",null,null,"2005-07-30"]
["LN06040030","Vendor Fab & Assy - X-Band Analyzer","2005-09-01","2005-09-30",null,"2005-09-01","2005-09-30"]
["LN06040032","RCV: X-Band Analyzer","2005-11-01","2005-10-31",null,"2005-11-01","2005-10-31"]
["LN06040055","Procure X-Band TWT Driver - SPARE","2006-11-13","2007-10-10"]
["LN06040060","RCV: X-Band TWT Driver - SPARE","2007-10-11","2007-10-10"]
["LN06040075","Procure X-Band 4 X Multiplier - SPARE","2006-11-13","2007-10-10"]
["LN06040080","RCV: X-Band 4 X Multiplier - SPARE","2007-10-11","2007-10-10"]
["LN06040095","Procure X-Band Phase & Amp Dectector - SPARE","2006-11-13","2007-10-10"]
["LN06040100","RCV: X-Band Phase & Amp Dectector - SPARE","2007-10-11","2007-10-10"]
["LN06040125","Procure X-Band Strpline Couplers - SPARE","2006-11-13","2007-10-10"]
["LN06040130","RCV: X-Band Strpline Couplers - SPARE","2007-10-11","2007-10-10"]
["LN06040140","Prep Bid Pak - X-Band TWT Driver","2006-04-11","2006-04-24"]
["LN06040142","RELEASE: RFP - X-Band TWT Driver","2006-04-25","2006-04-24"]
["LN06040144","Vendors Prep Proposals - X-Band TWT Driver","2006-04-25","2006-05-08"]
["LN06040146","RCV: Proposals from Vendors","2006-05-09","2006-05-08"]
["LN06040148","Evaluate Vendor Proposals","2006-05-09","2006-05-22"]
["LN06040150","AWARD: Contract X-Band TWT Driver","2006-05-23","2006-05-23"]
["LN06040152","Vendor Fab & Assy - X-Band TWT Driver","2006-05-24","2006-11-10"]
["LN06040154","RCV: X-Band TWT Driver","2006-11-13","2006-11-10"]
["LN06040164","Prep Bid Pak - X-Band Phase & Amp Dectector","2006-04-11","2006-04-24"]
["LN06040166","RELEASE: RFP - X-Band Phase & Amp Dectector","2006-04-25","2006-04-24"]
["LN06040168","Vendors Prep Proposals - X-Band Phase & Amp D","2006-04-25","2006-05-08"]
["LN06040170","RCV: Proposals from Vendors","2006-05-09","2006-05-08"]
["LN06040172","Evaluate Vendor Proposals","2006-05-09","2006-05-22"]
["LN06040174","AWARD: Contract X-Band Phase & Amp Dectector","2006-05-23","2006-05-23"]
["LN06040176","Vendor Fab & Assy - X-Band Phase & Amp Dectector","2005-10-17","2006-07-11",null,"2005-10-17"]
["LN06040178","RCV: X-Band Phase & Amp Dectector","2006-07-12","2006-07-11"]
["LN06040180","Procure X-Band 4 X Multiplier","2005-10-17","2006-05-25",null,"2005-10-17"]
["LN06040182","RCV: X-Band 4 X Multiplier","2006-05-26","2006-05-25"]
["LN06040184","Procure X-Band RF Cables","2006-04-11","2006-09-28"]
["LN06040186","RCV: X-Band RF Cables","2006-09-29","2006-09-28"]
["LN06040188","Procure X-Band Strpline Couplers","2006-04-11","2006-09-28"]
["LN06040190","RCV: X-Band Strpline Couplers","2006-09-29","2006-09-28"]
["LN06040192","Procure X-Band Chassis","2006-04-11","2006-09-28"]
["LN06040194","RCV: X-Band Chassis","2006-09-29","2006-09-28"]
["LN06040196","Procure X-Band Drive Monitoring","2006-04-11","2006-09-28"]
["LN06040198","RCV: X-Band Drive Monitoring","2006-09-29","2006-09-28"]
["LN06040200","Assemble X-Band LLRF Equipment","2006-11-13","2006-12-05"]
["LN06040205","Test X-Band LLRF Equipment","2006-12-06","2007-01-10"]
["LN06040210","Collect Component Performance Data","2007-01-11","2007-01-18"]
["LN06040215","Load Component Data Base","2007-01-19","2007-01-25"]
["LN06040220","AVAIL: X-Band LLRF Equip Ready for BC1 Install","2007-01-26","2007-01-25"]
["LN0605","X-BAND HIGH POWER RF SUMMARY","2005-05-02","2006-07-31",null,"2005-05-02"]
["LN06051","X-BAND HP KLYSTRON SUMMARY","2005-05-02","2006-07-31",null,"2005-05-02"]
["LN06051025","Design Kylstron Mount","2005-07-01","2005-07-05",null,"2005-07-01","2005-07-05"]
["LN06051030","Design Klystron Gallery Tank","2005-09-01","2006-01-30",null,"2005-09-01","2006-01-30"]
["LN06051035","Conduct Prelim Design Review (PDR) - X Bnd HP","2005-05-02","2005-05-02",null,"2005-05-02","2005-05-02"]
["LN06051040","Release Long Lead Procurements","2005-07-01","2005-06-30",null,"2005-07-01","2005-06-30"]
["LN06051045","Create Cold Test Plan","2005-05-02","2005-05-02",null,"2005-05-02","2005-05-02"]
["LN06051050","Establish Subordinate Work Orders","2005-05-02","2005-05-02",null,"2005-05-02","2005-05-02"]
["LN06051052","Conduct Final Design Review (FDR) - X Bnd HP K","2005-05-02","2005-05-02",null,"2005-05-02","2005-05-02"]
["LN06051054","COMP: X-Band Klystron Design","2005-07-01","2005-06-30",null,"2005-07-01","2005-06-30"]
["LN06051072","AWARD: X-Band Klystrons","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["LN06051074","Vendor Fab & Assy - X-Band Klystrons","2005-05-02","2006-01-30",null,"2005-05-02","2006-01-30"]
["LN06051076","RCV: X-Band Klystrons","2006-01-31","2006-01-30",null,"2006-01-31","2006-01-30"]
["LN06051078","Procure Mounting Support","2005-09-01","2005-09-30",null,"2005-09-01","2005-09-30"]
["LN06051080","RCV: Mounting Support","2006-02-01","2006-01-31"]
["LN06051082","Prep Bid Pak - X-Band Klystron","2006-10-03","2006-10-09"]
["LN06051084","RELEASE: RFP - X-Band Klystron","2006-10-10","2006-10-09"]
["LN06051086","Vendors Prep Proposals - Klystron System","2006-10-10","2006-10-23"]
["LN06051088","RCV: Vendor Proposals - X-Band Klystron","2006-10-24","2006-10-23"]
["LN06051090","Evaluate Vendor Proposals - Klystron System","2006-10-24","2006-10-30"]
["LN06051092","AWARD: X-Band Klystrons (Spares)","2006-10-31","2006-10-31"]
["LN06051100","Vendor Fab & Assy -X-Band Klystrons - SPARE","2006-11-01","2007-09-28"]
["LN06051105","RCV: X-Band Klystrons - SPARE","2007-10-01","2007-09-28"]
["LN06051110","Procure Mounting Support - SPARE","2006-10-03","2007-08-29"]
["LN06051115","RCV: Mounting Support - SPARE","2007-08-30","2007-08-29"]
["LN06051120","Fab & Assemble X-Band Klystron","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN06051125","Fab & Asemble Mounting Support","2006-02-10","2006-02-16"]
["LN06051130","Fab & Assemble System Window","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN06051135","Test System Window","2006-02-01","2006-02-14"]
["LN06051140","Fab & Assemble X-Band Klystron - SPARE","2006-10-03","2007-03-12"]
["LN06051145","Fab & Asemble Mounting Support - SPARE","2007-08-30","2007-09-06"]
["LN06051150","Collect Component Performance Data","2006-02-15","2006-02-16"]
["LN06051155","Load Component Data Base","2006-02-17","2006-02-21"]
["LN06051165","Dress Klystron","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN06051170","Test Klystron System","2006-07-18","2006-07-31"]
["LN06051175","AVAIL: X-Band HP Klystrons Ready for BC1 Install","2006-08-01","2006-07-31"]
["LN06052","X-BAND HP MODULATOR SUMMARY","2005-12-01","2006-07-17",null,"2005-12-01"]
["LN06052020","Design Modulator","2005-12-01","2006-01-30",null,"2005-12-01","2006-01-30"]
["LN06052025","Modulator Documentation","2006-02-01","2006-03-15"]
["LN06052030","Conduct Prelim Dsign Review (PDR) - X Bnd HP Mod","2006-03-16","2006-03-20"]
["LN06052035","Release Long Lead Procurements","2006-03-21","2006-03-20"]
["LN06052040","Create Cold Test Plan","2006-03-21","2006-03-20"]
["LN06052045","Establish Subordinate Work Orders","2006-03-21","2006-03-21"]
["LN06052050","Conduct Final Design Review (FDR) - X Bnd HP Mod","2006-03-22","2006-03-22"]
["LN06052055","COMP: X-Band Modulator Design","2006-03-23","2006-03-22"]
["LN06052060","Procure Tank","2006-01-01","2006-04-21",null,"2006-01-01"]
["LN06052065","RCV: Tank","2006-04-24","2006-04-24"]
["LN06052070","Procure Pulsed Transformer","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN06052075","RCV: Pulsed Transformer","2006-02-01","2006-02-01"]
["LN06052080","Procure Cap Divider","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN06052085","RCV: Cap Divider","2006-02-01","2006-02-01"]
["LN06052090","Procure Heater Isolation","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN06052095","RCV: Heater Isolation","2006-02-01","2006-02-01"]
["LN06052100","Procure Toroid & Misc","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN06052105","RCV: Toroid & Misc","2006-02-01","2006-02-01"]
["LN06052110","Procure Interlocks","2006-03-23","2006-04-21"]
["LN06052115","RCV: Interlocks","2006-04-24","2006-04-24"]
["LN06052120","Procure HV Connectors","2006-03-23","2006-04-21"]
["LN06052125","RCV: HV Connectors","2006-04-24","2006-04-24"]
["LN06052130","Procure Magnet Power Supply","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN06052135","RCV: Magnet Power Supply","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN06052140","Procure Power Supply Cabling","2006-03-23","2006-04-21"]
["LN06052145","RCV: Power Supply Cabling","2006-04-24","2006-04-24"]
["LN06052160","Procure Tank - SPARE","2006-10-03","2007-08-29"]
["LN06052165","RCV: Tank - SPARE","2007-08-30","2007-08-29"]
["LN06052170","Procure Pulsed Transformer - SPARE","2006-10-03","2007-08-29"]
["LN06052175","RCV: Pulsed Transformer - SPARE","2007-08-30","2007-08-29"]
["LN06052180","Procure Cap Divider - SPARE","2006-10-03","2007-08-29"]
["LN06052185","RCV: Cap Divider - SPARE","2007-08-30","2007-08-29"]
["LN06052190","Procure Heater Isolation - SPARE","2006-10-03","2007-08-29"]
["LN06052195","RCV: Heater Isolation - SPARE","2007-08-30","2007-08-29"]
["LN06052200","Procure Toroid & Misc - SPARE","2006-10-03","2007-08-29"]
["LN06052205","RCV: Toroid & Misc - SPARE","2007-08-30","2007-08-29"]
["LN06052210","Procure Interlocks - SPARE","2006-10-03","2007-08-29"]
["LN06052215","RCV: Interlocks - SPARE","2007-08-30","2007-08-29"]
["LN06052220","Procure HV Connectors - SPARE","2006-10-03","2007-08-29"]
["LN06052225","RCV: HV Connectors - SPARE","2007-08-30","2007-08-29"]
["LN06052230","Procure Magnet Power Supply - SPARE","2006-10-03","2007-08-29"]
["LN06052235","RCV: Magnet Power Supply - SPARE","2007-08-30","2007-08-29"]
["LN06052240","Procure Power Supply Cabling - SPARE","2006-10-03","2007-08-29"]
["LN06052245","RCV: Power Supply Cabling - SPARE","2007-08-30","2007-08-29"]
["LN06052250","Procure Cathode Ion Pump - SPARE","2006-10-03","2007-08-29"]
["LN06052255","RCV: Cathode Ion Pump - SPARE","2007-08-30","2007-08-29"]
["LN06052260","Assemble Tank","2006-04-14","2006-04-21"]
["LN06052265","Assemble Modulator Assembly","2006-04-24","2006-05-26"]
["LN06052270","Test Modulator Assembly","2006-05-30","2006-07-05"]
["LN06052275","Assemble Tank - SPARE","2007-08-30","2007-09-06"]
["LN06052280","Dress Klystron - SPARE","2007-03-13","2007-04-02"]
["LN06052285","Test Klystron / Tank Assembly - SPARE","2007-09-07","2007-09-27"]
["LN06052286","AVAIL: Klystron / Tank Assembly - SPARE","2007-09-28","2007-09-27"]
["LN06052290","Collect Component Performance Data","2006-07-06","2006-07-17"]
["LN06052295","Load Component Data Base","2006-07-14","2006-07-17"]
["LN06052315","AVAIL: X-Band HP Modulator Ready for BC1 Install","2006-07-18","2006-07-17"]
["LN06053","X-BAND HP WAVEGUIDE SUMMARY","2005-05-02","2006-04-19",null,"2005-05-02"]
["LN06053020","Design WG  System","2005-05-02","2006-01-30",null,"2005-05-02","2006-01-30"]
["LN06053025","Design WG  System Supports","2006-02-01","2006-03-15"]
["LN06053030","Conduct Prelim Design Review (PDR) - S Band WG","2006-03-16","2006-03-22"]
["LN06053035","Release Long Lead Procurements","2006-03-23","2006-03-22"]
["LN06053040","Create Cold Test Plan","2006-03-23","2006-03-29"]
["LN06053045","Establish Subordinate Work Orders","2006-03-30","2006-03-30"]
["LN06053050","Conduct Final Design Review (FDR) - S Band WG","2006-03-31","2006-03-31"]
["LN06053055","COMP: X-Band Waveguide Design","2006-04-03","2006-03-31"]
["LN06053060","Procure ION Pumps (8 EA)","2005-10-03","2005-10-31",null,"2005-10-03","2005-10-31"]
["LN06053065","RCV: ION Pumps (8 EA)","2005-11-01","2005-10-31",null,"2005-11-01","2005-10-31"]
["LN06053080","Procure ION Pump Power Supply","2005-10-03","2005-10-31",null,"2005-10-03","2005-10-31"]
["LN06053085","RCV: ION Pump Power Supply","2005-11-01","2005-10-31",null,"2005-11-01","2005-10-31"]
["LN06053090","Procure Waveguide Supports","2006-04-03","2006-04-14"]
["LN06053095","RCV: Waveguide Supports","2006-04-17","2006-04-14"]
["LN06053100","Fab & Test Cold Test Hardware","2006-04-17","2006-04-19"]
["LN06053110","Fab, Cold Test & Tune Mode Convertor","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN06053115","Fab, Cold Test & Tune Circular Waveguide (WR 2","2005-10-17","2006-03-15",null,"2005-10-17"]
["LN06053120","Fab, Cold Test & Tune WR90 Waveguide","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN06053125","Waveguide Supports","2006-02-01","2006-02-14"]
["LN06053130","Assemble System","2006-02-15","2006-03-01"]
["LN06053135","Collect Component Performance Data","2006-03-02","2006-03-03"]
["LN06053140","Load Component Data Base","2006-03-06","2006-03-07"]
["LN06053165","AVAIL: X-Band HP Waveguide for Installation","2006-04-20","2006-04-19"]
["LN0606","X-BAND STRUCTURES SUMMARY","2005-11-01","2006-02-21",null,"2005-11-01"]
["LN06060005","Write Structure ICD","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN06060010","COMP: X-Band Structures Requirements","2006-01-31","2006-01-30",null,"2006-01-31","2006-01-30"]
["LN06060015","Design Structure Supports","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN06060025","Design Removal Mechanism","2006-02-01","2006-01-31"]
["LN06060030","Conduct Fnl Dsn Rev - X-Band Bunch Comp Sys","2006-02-01","2006-02-01"]
["LN06060035","COMP: X-Band Bunch Compressor System Design","2006-02-01","2006-01-31"]
["LN06060040","Procure Valves and Misc Hdwr","2006-02-01","2006-01-31"]
["LN06060060","Fab, Cold Test & Tune WR 90 Tee","2005-11-01","2005-12-30",null,"2005-11-01","2005-12-30"]
["LN06060065","Fab, Cold Test & Tune WR90 Low Power Loads","2005-11-01","2005-12-30",null,"2005-11-01","2005-12-30"]
["LN06060080","Fab Structure Supports","2005-11-01","2006-02-21",null,"2005-11-01"]
["LN06060085","Fab Structure Removal Mechanism","2005-11-01","2006-02-21",null,"2005-11-01"]
["LN06060090","Assemble X-Band Structures","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN06060092","Cold Test & Tune Structure (Shop)","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN06060095","Test X-Band Structure System","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN06060105","Collect Component Performance Data","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN06060110","Load Component Data Base","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN06060115","Post Process & Test","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN06060120","AVAIL: X-Band Structures Ready for BC1 Install","2006-01-31","2006-01-30",null,"2006-01-31","2006-01-30"]
["LN0607","RF DISTRIBUTION SUMMARY","2006-01-01","2008-01-02",null,"2006-01-01"]
["LN060701","MODULATOR REFURBISHMENT (7) SUMMARY","2006-03-01","2006-10-16"]
["LN06070102","Create Design Documentation","2006-03-01","2006-03-28"]
["LN06070110","Generate Detailed Procurement Plan","2006-03-29","2006-03-29"]
["LN06070112","Create Test Plan","2006-03-30","2006-04-05"]
["LN06070114","Establish Subordinate Work Orders","2006-04-06","2006-04-06"]
["LN06070116","Prepare for Final Desgin Review (FDR)","2006-04-07","2006-04-10"]
["LN06070118","Conduct Final Design Review (FDR) - Mod Refurb","2006-04-11","2006-04-11"]
["LN06070120","COMP: Modulator Refurbishment Design","2006-04-12","2006-04-11"]
["LN06070124","Prep Bid Pak - Thyratron & Parts","2006-04-12","2006-04-18"]
["LN06070126","RELEASE: RFP - Thyratron & Parts","2006-04-19","2006-04-18"]
["LN06070128","Vendors Prep Proposals - Thyratron & Parts","2006-04-19","2006-05-02"]
["LN06070130","RCV: Vendor Proposals - Thyratron & Parts","2006-05-03","2006-05-02"]
["LN06070132","Evaluate Vendor Proposals - Thyratron & Parts","2006-05-03","2006-05-09"]
["LN06070134","AWARD: Contract - Thyratron & Parts","2006-05-10","2006-05-10"]
["LN06070136","Vendor Fab & Assy - Thyratron & Parts","2006-05-11","2006-08-18"]
["LN06070138","RCV: from Vendor - Thyratron & Parts","2006-08-21","2006-08-18"]
["LN06070140","Refurbish Existing Modulators (7ea)","2006-08-21","2006-10-16"]
["LN06070142","AVAIL: Modulators Refurbished - BC1","2006-10-17","2006-10-16"]
["LN06070144","AVAIL: Modulators Refurbished - L02","2006-10-17","2006-10-16"]
["LN06070146","AVAIL: Modulators Refurbished - BC2","2006-10-17","2006-10-16"]
["LN06070148","AVAIL: Modulators Refurbished - L03","2006-10-17","2006-10-16"]
["LN06070150","Procure Thyratron & Parts - SPARE","2006-10-03","2007-01-26"]
["LN060702","SOLID STATE SUB BOOSTER (6) SUMMARY","2006-03-01","2006-11-10"]
["LN06070200","Generate Detailed Procurement Plan","2006-03-01","2006-03-01"]
["LN06070205","Create Test Plan","2006-03-02","2006-03-08"]
["LN06070210","Establish Subordinate Work Orders","2006-03-09","2006-03-09"]
["LN06070215","Prepare for Final Design Review (FDR)","2006-03-10","2006-03-13"]
["LN06070220","Conduct Final Design Review (FDR) - SS SubBoost","2006-03-14","2006-03-14"]
["LN06070225","COMP: Solid State Sub Booster Design","2006-03-15","2006-03-14"]
["LN06070230","Procure Phase Control Electronics","2006-03-15","2006-05-09"]
["LN06070235","Procure Amplitude Control Electronics","2006-03-15","2006-05-09"]
["LN06070240","Fab & Test Amplifier","2006-05-10","2006-09-15"]
["LN06070245","Assemble & Test Sub Booster Systems","2006-09-18","2006-11-10"]
["LN06070250","AVAIL: Solid State Sub Booster Ready for Install","2006-11-13","2006-11-10"]
["LN06070260","Procure Phase Control Electronics - SPARE","2006-10-03","2006-11-29"]
["LN06070265","Procure Amplitude Control Electronics - SPARE","2006-10-03","2006-11-29"]
["LN06070270","Fab & Test Amplifier - SPARE","2006-11-30","2007-04-23"]
["LN06070275","AVAIL: Amplifier - SPARE","2007-04-24","2007-04-23"]
["LN060703","IPA MODIFICATIONS (6) SUMMARY","2006-03-01","2006-04-04"]
["LN06070310","Generate Detailed Procurement Plan","2006-03-01","2006-03-01"]
["LN06070312","Create Test Plan","2006-03-02","2006-03-08"]
["LN06070314","Establish Subordinate Work Orders","2006-03-09","2006-03-09"]
["LN06070316","Prepare for Final Desgin Review (FDR)","2006-03-10","2006-03-13"]
["LN06070318","Conduct Final Design Review (FDR) - IPA Mods","2006-03-14","2006-03-14"]
["LN06070320","COMP: IPA Modifications Design","2006-03-15","2006-03-14"]
["LN06070326","Modify & Test IPA Chasis","2006-03-15","2006-04-04"]
["LN06070327","AVAIL: IPA Chasis Modified","2006-04-05","2006-04-04"]
["LN060704","KLYSTRON CONTROL INTERFACES (6) SUMMARY","2006-01-01","2006-05-08",null,"2006-01-01"]
["LN06070400","Develop Design & Prototype","2006-01-01","2006-01-30",null,"2006-01-01","2006-01-30"]
["LN06070402","Create Design Documentation","2006-02-01","2006-03-01"]
["LN06070404","Create Draft Layouts","2006-03-02","2006-03-15"]
["LN06070406","Prepare for Prelim Design Review (PDR)","2006-03-16","2006-03-17"]
["LN06070408","Conduct Prelim Design Review (PDR) - Cntrols I/F","2006-03-20","2006-03-20"]
["LN06070410","Generate Detailed Procurement Plan","2006-03-21","2006-03-21"]
["LN06070412","Create Test Plan","2006-03-22","2006-03-28"]
["LN06070414","Establish Subordinate Work Orders","2006-03-29","2006-03-29"]
["LN06070416","Prepare for Final Desgin Review (FDR)","2006-03-30","2006-03-31"]
["LN06070418","Conduct Final Design Review (FDR) - Cntrols I/F","2006-04-03","2006-04-03"]
["LN06070420","COMP: Klystron Controls Design","2006-04-04","2006-04-03"]
["LN06070426","Fab Cables","2006-04-04","2006-04-17"]
["LN06070428","Klystron Controls Interface Installation","2006-04-18","2006-05-08"]
["LN060705","BUNCH LENGTH ELECTRONICS SUMMARY","2006-02-01","2006-06-06"]
["LN06070500","Develop Design & Prototype","2006-02-01","2006-03-08"]
["LN06070502","Create Design Documentation","2006-03-09","2006-04-05"]
["LN06070504","Create Draft Layouts","2006-04-06","2006-04-19"]
["LN06070506","Prepare for Prelim Design Review (PDR)","2006-04-20","2006-04-21"]
["LN06070508","Conduct Prelim Design Review (PDR) - Bm Phs Elec","2006-04-24","2006-04-24"]
["LN06070510","Generate Detailed Procurement Plan","2006-04-25","2006-04-25"]
["LN06070512","Create Test Plan","2006-04-26","2006-05-02"]
["LN06070514","Establish Subordinate Work Orders","2006-05-03","2006-05-03"]
["LN06070516","Prepare for Final Desgin Review (FDR)","2006-05-04","2006-05-05"]
["LN06070518","Conduct Final Design Review (FDR) - Bnc Lth Elec","2006-05-08","2006-05-08"]
["LN06070520","COMP: Bunch Length Electronics Design","2006-05-09","2006-05-08"]
["LN06070525","Fab & Test Bunch Length Electronics","2006-05-09","2006-06-06"]
["LN06070530","AVAIL: Bunch Length Electronics","2006-06-07","2006-06-06"]
["LN06070560","Proc, Fab & Test Bunch Length Electronics- SPARE","2006-10-03","2006-10-30"]
["LN06070565","AVAIL: Bunch Length Electronics - SPARE","2006-10-31","2006-10-30"]
["LN060706","X BAND RF PHASE MEASUREMENTS SUMMARY","2006-01-01","2007-09-27",null,"2006-01-01"]
["LN06070601","Design X-Band Phase Chasis","2006-01-01","2007-09-27",null,"2006-01-01"]
["LN06070602","Create Design Documentation","2006-02-01","2006-03-01"]
["LN06070604","Create Draft Layouts","2006-03-02","2006-03-15"]
["LN06070606","Prepare for Prelim Design Review (PDR)","2006-03-16","2006-03-17"]
["LN06070608","Conduct Prelim Design Review (PDR) - RF Phas Mea","2006-03-20","2006-03-20"]
["LN06070609","Procure, Fab & Test X-Band Chasis Prototype","2006-03-21","2006-06-13"]
["LN06070610","Procure, Fab & Test X-Band PAD Prototype","2006-03-21","2006-07-12"]
["LN06070611","Generate Detailed Procurement Plan","2006-07-13","2006-07-13"]
["LN06070612","Create Test Plan","2006-07-14","2006-07-20"]
["LN06070614","Establish Subordinate Work Orders","2006-07-21","2006-07-21"]
["LN06070616","Prepare for Final Desgin Review (FDR)","2006-07-24","2006-07-25"]
["LN06070618","Conduct Final Design Review (FDR) - RF Phas Mea","2006-07-26","2006-07-26"]
["LN06070620","COMP: RF Phase Measurement Design","2006-07-27","2006-07-26"]
["LN06070622","Procure Material / Equipment","2006-07-27","2006-11-02"]
["LN06070638","Procure, Fab & Test X-Band Chasis","2006-11-03","2006-11-20"]
["LN06070639","AVAIL: X-Band RF Phase Measurement System","2006-11-21","2006-11-20"]
["LN060707","RF DISTRIBUTION L2 & L3 SUMMARY","2006-07-24","2007-06-21"]
["LN06070700","Review & Accept Requirements","2006-07-24","2006-07-25"]
["LN06070701","Design RF Distribution System","2006-07-26","2006-08-29"]
["LN06070702","Create Design Documentation","2006-08-30","2006-09-27"]
["LN06070704","Create Draft Layouts","2006-09-28","2006-10-11"]
["LN06070706","Prepare for Prelim Design Review (PDR)","2006-10-12","2006-10-13"]
["LN06070708","Conduct Prelim Design Review (PDR) - RF Dist","2006-10-16","2006-10-16"]
["LN06070709","Controls Configuration Assessment","2006-10-17","2006-10-30"]
["LN06070710","Design RF Dist PRL Coaxial Water System","2006-10-17","2006-10-30"]
["LN06070711","Proc, Fab & Test 2W Distribution Amp - Prototype","2006-10-31","2007-02-09"]
["LN06070712","Generate Detailed Procurement Plan","2007-02-12","2007-02-12"]
["LN06070713","Create Test Plan","2007-02-13","2007-02-20"]
["LN06070714","Establish Subordinate Work Orders","2007-02-21","2007-02-21"]
["LN06070716","Prepare for Final Desgin Review (FDR)","2007-02-22","2007-02-23"]
["LN06070718","Conduct Final Design Review (FDR) - RF Dist","2007-02-26","2007-02-26"]
["LN06070720","COMP: RF Distribution (L2&L3) Design","2007-02-27","2007-02-26"]
["LN06070730","Procure, Fab & Test 2W Distribution Amp (10)","2007-02-27","2007-05-21"]
["LN06070731","AVAIL: Hdwr Testing Complete Ready for Install","2007-05-22","2007-05-21"]
["LN06070732","Procure & Install 1km 1/2 Superflex","2007-02-27","2007-05-21"]
["LN06070736","Procure & Install 1km Cable Guides","2007-02-27","2007-05-21"]
["LN06070740","Procure & Install Coaxial Water Lines","2007-02-27","2007-03-19"]
["LN06070744","Procure & Install Control Cables","2007-02-27","2007-04-02"]
["LN06070748","Install Cooling System","2007-05-22","2007-05-31"]
["LN06070756","2W Distribution Amp Install (10)","2007-06-01","2007-06-21"]
["LN06070757","AVAIL: RF Distribution System Ready","2007-06-22","2007-06-21"]
["LN06070760","Fab & Test 2W Distribution Amp - SPARE","2007-05-22","2007-08-15"]
["LN06070765","AVAIL: Hdwr Testing Complete Ready - SPARE","2007-08-16","2007-08-15"]
["LN060708","RF FIBER OPTICS ELECTRONICS SUMMARY","2006-10-03","2008-01-02"]
["LN06070800","Review & Accept Requirements","2006-10-03","2006-10-04"]
["LN06070801","Design Fiber Optic Electronics","2006-10-05","2006-11-08"]
["LN06070802","Create Design Documentation","2006-11-09","2006-12-15"]
["LN06070804","Create Draft Layouts","2006-11-09","2006-12-15"]
["LN06070806","Prepare for Prelim Design Review (PDR)","2007-01-02","2007-01-03"]
["LN06070808","Conduct Prelim Design Review (PDR) - RF Elec","2007-01-04","2007-01-04"]
["LN06070810","Generate Detailed Procurement Plan","2007-01-05","2007-01-05"]
["LN06070812","Create Test Plan","2007-01-08","2007-01-12"]
["LN06070814","Establish Subordinate Work Orders","2007-01-16","2007-01-16"]
["LN06070815","Fab & Test RF FO Electronics Prototype","2007-01-17","2007-05-09"]
["LN06070816","Prepare for Final Desgin Review (FDR)","2007-05-10","2007-05-11"]
["LN06070818","Conduct Final Design Review (FDR) - RF Elec","2007-05-14","2007-05-14"]
["LN06070820","COMP: RF Fiber Optics Electronics System Design","2007-05-15","2007-05-14"]
["LN06070828","Fab & Test RF FO Electronics","2007-05-15","2007-08-08"]
["LN06070829","AVAIL: FO System Ready for Install","2007-08-09","2007-08-08"]
["LN06070832","Fiber Optics System Installation","2007-08-09","2007-09-20"]
["LN06070836","Perform RF Electronics Testing","2007-09-21","2008-01-02"]
["LN06070837","AVAIL: FO System Ready for Commissioning","2008-01-03","2008-01-02"]
["LN06070850","Procure, Fab & Test RF FO Electronics","2007-08-09","2007-11-01"]
["LN06070860","AVAIL: Fiber Optic System Ready - SPARE","2007-11-02","2007-11-01"]
["LN060709","RF STABILITY TESTING SUMMARY","2006-10-03","2007-07-02"]
["LN06070900","Review & Accept Requirements","2006-10-03","2006-10-04"]
["LN06070901","Design Stability Algorithms","2006-10-05","2006-11-08"]
["LN06070902","Create Design Documentation","2006-11-09","2006-12-08"]
["LN06070904","Create Draft Layouts","2006-12-11","2007-01-08"]
["LN06070906","Prepare for Prelim Design Review (PDR)","2007-01-09","2007-01-10"]
["LN06070908","Conduct Prelim Design Review (PDR) - RF Stbility","2007-01-11","2007-01-11"]
["LN06070910","Generate Detailed Procurement Plan","2007-01-12","2007-01-12"]
["LN06070912","Create Test Plan","2007-01-16","2007-01-22"]
["LN06070914","Establish Subordinate Work Orders","2007-01-23","2007-01-23"]
["LN06070915","Prepare for Final Desgin Review (FDR)","2007-01-24","2007-01-25"]
["LN06070916","Conduct Final Design Review (FDR) - RF Stability","2007-01-26","2007-01-26"]
["LN06070917","RF Feedback Measurements","2007-01-29","2007-07-02"]
["LN06070918","RF Feedback Setup","2007-01-29","2007-07-02"]
["LN06070919","RF Feedback Algorithim Adjustment","2007-01-29","2007-07-02"]
["LN06070922","AVAIL: RF System Ready for Commissioning","2007-07-03","2007-07-02"]
["LN0701","LINAC L01 SYSTEM INSTALLATION SUMMARY","2005-06-01","2007-02-23",null,"2005-06-01"]
["LN07010000","Establish & Maintain Component Storage Facility","2006-02-01","2005-06-30",null,null,"2005-06-30"]
["LN07010005","REQD: L01 Available for Pre-Install Preps","2006-08-01","2006-07-31"]
["LN07010010","Create/Review Dwgs & Identify Installation Hdwr","2005-06-01","2005-10-31",null,"2005-06-01","2005-10-31"]
["LN07010015","Procure Installation Hardware","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["LN07010020","Review Drawings & Identify Installation Tooling","2005-06-01","2006-01-30",null,"2005-06-01","2006-01-30"]
["LN07010025","Procure Installation & Alignment Tooling","2006-01-01","2006-08-01",null,"2006-01-01"]
["LN07010030","Kit New Components for Installation","2006-01-01","2006-03-01",null,"2006-01-01"]
["LN07010035","Develop De-Installation Plan for Existing Equip","2005-08-01","2006-05-11",null,"2005-08-01"]
["LN07010040","De-install Existing Components","2006-08-01","2006-08-21"]
["LN07010045","Determine Disposition of De-installed Components","2006-08-22","2006-09-12"]
["LN07010050","Prep for & Move De-installed Equip to Storage","2006-09-13","2006-09-19"]
["LN07010055","Establish Alignment Coordinates for B/L Equip","2006-08-22","2006-08-24"]
["LN07010060","REQD: All Linac L01 Sys Equip Ready for Install","2007-01-04","2007-01-03"]
["LN07010100","Install All Racks, Cables, Trays & Test","2007-01-04","2007-02-08"]
["LN07010200","Install S-Band RF Components","2007-01-04","2007-01-10"]
["LN07010205","Install Beamline Components","2007-01-11","2007-01-29"]
["LN07010210","Align Beamline Components to Coordinate System","2007-01-30","2007-02-02"]
["LN07010215","Magnet Power Interconnect & Test","2007-02-05","2007-02-07"]
["LN07010220","Controls Interconnect & Test","2007-02-09","2007-02-13"]
["LN07010225","Interconnect Vacuum System & Test","2007-01-30","2007-02-01"]
["LN07010230","Perform Magnet Power Test","2007-02-02","2007-02-05"]
["LN07010235","Perform Diagnostics Controls Test","2007-02-06","2007-02-08"]
["LN07010240","Test & Tune S Band RF Equipment","2007-02-09","2007-02-13"]
["LN07010245","Coordinate & Check Installation","2007-02-14","2007-02-23"]
["LN07010250","AVAIL: L01 Equipment Installation Complete","2007-02-26","2007-02-23"]
["LN070105","LINAC L01 COMMISSIONING SUMMARY","2006-10-03","2008-08-04"]
["LN07010500","REQD: L01 Equipment Ready for Commissioning","2007-06-12","2007-06-11"]
["LN07010505","Develop Commissioning Plans","2006-10-03","2006-11-13"]
["LN07010510","COMP: Commissioning Plans Complete","2006-11-14","2006-11-13"]
["LN07010515","Write Bm Authorization Sheet (BAS) Requirements","2006-11-14","2007-01-11"]
["LN07010520","Obtain Beam Authorization Sheet (BAS)","2007-01-12","2007-01-19"]
["LN07010525","PPS Checkout Linac","2007-06-12","2007-06-12"]
["LN07010535","Search and Lock Linac","2007-06-13","2007-06-13"]
["LN07010540","Commission L01, Physics","2008-01-03","2008-01-16"]
["LN07010545","Commission L01, Operations","2008-01-03","2008-01-16"]
["LN07010570","Support L01 Commissioning RF","2008-01-03","2008-01-16"]
["LN07010605","Support L01 Commissioning Mechanical","2008-01-03","2008-01-16"]
["LN07010615","Support L01 Commissioning Survey","2008-01-03","2008-01-16"]
["LN07010620","Support L01 Commissioning Power Conv","2008-01-03","2008-01-16"]
["LN07010635","COMP: L01 Commissioning Complete","2008-01-17","2008-01-16"]
["LN07010700","L01 System Available for Undulator Commissioning","2008-05-09","2008-08-04"]
["LN0702","LINAC BC1 SYSTEM INSTALLATION SUMMARY","2005-06-01","2007-03-16",null,"2005-06-01"]
["LN07020000","Establish & Maintain Component Storage Facility","2005-06-01","2005-06-30",null,"2005-06-01","2005-06-30"]
["LN07020005","REQD: BC1 Available for Pre-Install Preps","2006-08-01","2006-07-31"]
["LN07020010","Create/Review Dwgs & Identify Installation Hdwr","2005-06-01","2006-01-31",null,"2005-06-01"]
["LN07020015","Procure Installation Hardware","2006-02-01","2006-07-21"]
["LN07020020","Review Drawings & Identify Installation Tooling","2005-06-01","2006-01-31",null,"2005-06-01"]
["LN07020025","Procure Installation Tooling","2006-01-01","2006-03-01",null,"2006-01-01"]
["LN07020030","Kit New Components for Installation","2006-07-24","2006-08-18"]
["LN07020035","Develop De-Installation Plan for Existing Equip","2005-08-01","2006-04-13",null,"2005-08-01"]
["LN07020040","De-install Existing Components","2006-08-01","2006-08-21"]
["LN07020045","Determine Disposition of De-installed Components","2006-08-22","2006-09-12"]
["LN07020050","Prep for & Move De-installed Equip to Storage","2006-09-13","2006-09-19"]
["LN07020055","Establish Alignment Coordinates for B/L Equip","2006-08-22","2006-08-24"]
["LN07020060","REQD: All Linac BC1 Sys Equip Ready for Install","2007-01-12","2007-01-11"]
["LN07020100","Install All Racks, Cables, Trays & Test","2007-01-12","2007-02-16"]
["LN07020200","Install S-Band RF Components","2007-01-12","2007-01-19"]
["LN07020205","Install Beamline Components","2007-01-22","2007-02-09"]
["LN07020207","Install Subbooster","2006-11-13","2006-11-28"]
["LN07020210","Align Beamline Components to Coordinate System","2007-02-12","2007-02-15"]
["LN07020215","Magnet Power Interconnect & Test","2007-02-16","2007-02-21"]
["LN07020220","Controls Interconnect & Test","2007-02-22","2007-02-26"]
["LN07020225","Interconnect Vacuum System & Test","2007-02-27","2007-03-01"]
["LN07020230","Perform Magnet Power Test","2007-03-02","2007-03-05"]
["LN07020235","Perform Diagnostics Controls Test","2007-03-06","2007-03-08"]
["LN07020240","Test & Tune S Band RF Equipment","2007-03-09","2007-03-13"]
["LN07020241","AVAIL: In-tunnel Installation Completed","2007-03-14","2007-03-16"]
["LN07020245","Install X-Band RF Components-Gallery","2006-04-20","2006-07-28"]
["LN07020246","Install X-Band RF Components-Tunnel","2006-08-22","2006-09-05"]
["LN07020250","Test & Tune X Band RF Equipment","2006-09-06","2006-10-03"]
["LN07020255","Coordinate & Check Installation","2006-10-04","2006-10-13"]
["LN07020256","Install X-Band RF Components-Gallery","2006-08-01","2006-08-14"]
["LN07020260","AVAIL: BC1 Equipment Installation Complete","2007-01-26","2007-01-25"]
["LN070205","LINAC BC1 COMMISSIONING SUMMARY","2006-10-03","2008-08-04"]
["LN07020500","REQD: BC1 Equipment Ready for Commissioning","2007-01-26","2007-01-25"]
["LN07020505","Develop Comissioning Plans","2006-10-03","2006-11-13"]
["LN07020510","COMP: Comissioning Plans Complete","2006-11-14","2006-11-13"]
["LN07020515","Write Bm Authorization Sheet (BAS) Requirements","2007-04-10","2007-05-21"]
["LN07020520","REQD: L01 Commissioning Complete","2008-01-17","2008-01-16"]
["LN07020535","Commission BC1, Physics","2008-01-17","2008-01-31"]
["LN07020540","Commission BC1, Operations","2008-01-17","2008-01-31"]
["LN07020575","Support BC1 Comissioning RF","2008-01-17","2008-01-31"]
["LN07020600","Support BC1 Comissioning Hardware","2008-01-17","2008-01-31"]
["LN07020610","Support BC1 Comissioning Mechanical","2008-01-17","2008-01-31"]
["LN07020620","Support BC1 Comissioning Survey","2008-01-17","2008-01-31"]
["LN07020625","Support BC1 Comissioning Power Conv","2008-01-17","2008-01-31"]
["LN07020640","COMP: BC1 Comissioning Complete","2008-02-01","2008-01-31"]
["LN07020700","BC1 System Available for Undulator Commissioning","2008-05-09","2008-08-04"]
["LN0703","LINAC L02 SYSTEM INSTALLATION SUMMARY","2006-02-01","2007-11-15"]
["LN07030000","Establish & Maintain Component Storage Facility","2006-07-24","2007-05-21"]
["LN07030005","REQD: L02 Available for Pre-Install Preps","2007-09-04","2007-08-31"]
["LN07030010","Create/Review Dwgs & Identify Installation Hdwr","2006-07-24","2006-08-18"]
["LN07030015","Procure Installation Hardware","2006-08-21","2007-06-19"]
["LN07030020","Review Drawings & Identify Installation Tooling","2006-07-24","2006-08-18"]
["LN07030025","Procure Installation Tooling","2006-08-21","2007-06-19"]
["LN07030030","Kit New Components for Installation","2007-06-20","2007-07-18"]
["LN07030035","Develop De-Installation Plan for Existing Equip","2006-07-24","2006-08-11"]
["LN07030038","De-install Existing Components (Oct05 Shut Down)","2006-02-01","2006-02-22"]
["LN07030040","De-install Existing Components","2007-09-04","2007-09-24"]
["LN07030045","Determine Disposition of De-installed Components","2007-09-25","2007-10-15"]
["LN07030050","Prep for & Move De-installed Equip to Storage","2007-10-16","2007-10-22"]
["LN07030055","Establish Alignment Coordinates for B/L Equip","2007-09-25","2007-09-27"]
["LN07030060","REQD: All Linac L02 Sys Equip Ready for Install","2007-09-26","2007-09-25"]
["LN07030100","Install All Racks, Cables, Trays & Test","2007-09-28","2007-11-01"]
["LN07030200","Install S-Band RF Components","2007-09-28","2007-10-04"]
["LN07030205","Install Beamline Components","2007-10-05","2007-10-19"]
["LN07030210","Align Beamline Components to Coordinate System","2007-10-22","2007-10-25"]
["LN07030215","Magnet Power Interconnect & Test","2007-10-26","2007-10-30"]
["LN07030220","Controls Interconnect & Test","2007-11-02","2007-11-06"]
["LN07030225","Interconnect Vacuum System & Test","2007-10-22","2007-10-24"]
["LN07030230","Perform Magnet Power Test","2007-10-25","2007-10-26"]
["LN07030235","Perform Diagnostics Controls Test","2007-10-29","2007-10-31"]
["LN07030240","Test & Tune S Band RF Equipment","2007-11-01","2007-11-05"]
["LN07030245","Coordinate & Check Installation","2007-11-06","2007-11-15"]
["LN07030250","AVAIL: L02 Equipment Installation Complete","2007-11-16","2007-11-15"]
["LN070305","LINAC L02 COMMISSIONING SUMMARY","2006-10-03","2008-08-04"]
["LN07030500","REQD: L02 Equipment Ready for Commissioning","2007-11-16","2007-11-15"]
["LN07030505","Develop Comissioning Plans","2006-10-03","2006-11-13"]
["LN07030510","COMP: Comissioning Plans Complete","2006-11-14","2006-11-13"]
["LN07030515","Write Bm Authorization Sheet (BAS) Requirements","2007-04-10","2007-05-21"]
["LN07030520","REQD: L01 & BC1 Comissioning Complete","2008-02-01","2008-01-31"]
["LN07030525","Obtain Beam Authorization Sheet (BAS)","2008-02-01","2008-02-07"]
["LN07030530","PPS Checkout Linac","2008-02-08","2008-02-08"]
["LN07030540","Search and Lock Linac","2008-02-11","2008-02-11"]
["LN07030545","Commission L02, Physics","2008-02-12","2008-02-26"]
["LN07030550","Commission L02, Operations","2008-02-12","2008-02-26"]
["LN07030575","Support L02 Comissioning RF","2008-02-12","2008-02-26"]
["LN07030600","Support L02 Comissioning Hardware","2008-02-12","2008-02-26"]
["LN07030610","Support L02 Comissioning Mechanical","2008-02-12","2008-02-26"]
["LN07030620","Support L02 Comissioning Survey","2008-02-12","2008-02-26"]
["LN07030625","Support L02 Comissioning Power Conv","2008-02-12","2008-02-26"]
["LN07030640","COMP: L02 Comissioning Complete","2008-02-27","2008-02-26"]
["LN07030700","L02 System Available for Undulator Commissioning","2008-05-09","2008-08-04"]
["LN0704","LINAC BC2 SYSTEM INSTALLATION SUMMARY","2006-07-24","2007-11-16"]
["LN07040000","Establish & Maintain Component Storage Facility","2006-07-24","2007-05-21"]
["LN07040005","REQD: BC2 Available for Pre-Install Preps","2007-09-04","2007-08-31"]
["LN07040010","Create/Review Dwgs & Identify Installation Hdwr","2006-07-24","2006-08-18"]
["LN07040015","Procure Installation Hardware","2006-08-21","2007-06-19"]
["LN07040020","Review Drawings & Identify Installation Tooling","2006-07-24","2006-08-18"]
["LN07040025","Procure Installation Tooling","2006-08-21","2007-06-19"]
["LN07040030","Kit New Components for Installation","2007-06-20","2007-07-18"]
["LN07040035","Develop De-Installation Plan for Existing Equip","2006-07-24","2006-08-11"]
["LN07040040","De-install Existing Components","2007-09-04","2007-09-24"]
["LN07040045","Determine Disposition of De-installed Components","2007-09-25","2007-10-15"]
["LN07040050","Prep for & Move De-installed Equip to Storage","2007-10-16","2007-10-22"]
["LN07040055","Establish Alignment Coordinates for B/L Equip","2007-09-25","2007-09-27"]
["LN07040060","REQD: All Linac BC2 Sys Equip Ready for Install","2007-08-23","2007-08-22"]
["LN07040100","Install All Racks, Cables, Trays & Test","2007-09-28","2007-11-01"]
["LN07040200","Install S-Band RF Components","2007-09-28","2007-10-04"]
["LN07040205","Install Beamline Components","2007-10-05","2007-10-22"]
["LN07040210","Align Beamline Components to Coordinate System","2007-10-23","2007-10-26"]
["LN07040215","Magnet Power Interconnect & Test","2007-10-29","2007-10-31"]
["LN07040220","Controls Interconnect & Test","2007-11-02","2007-11-06"]
["LN07040225","Interconnect Vacuum System & Test","2007-10-23","2007-10-25"]
["LN07040230","Perform Magnet Power Test","2007-10-26","2007-10-29"]
["LN07040235","Perform Diagnostics Controls Test","2007-10-30","2007-11-01"]
["LN07040240","Test & Tune S Band RF Equipment","2007-11-02","2007-11-06"]
["LN07040245","Coordinate & Check Installation","2007-11-07","2007-11-16"]
["LN07040250","AVAIL: BC2 Equipment Installation Complete","2007-11-19","2007-11-16"]
["LN070405","LINAC BC2 COMMISSIONING SUMMARY","2006-10-03","2008-08-04"]
["LN07040500","REQD: BC2 Equipment Ready for Commissioning","2007-11-19","2007-11-16"]
["LN07040505","Develop Comissioning Plans","2006-10-03","2006-11-13"]
["LN07040510","COMP: Comissioning Plans Complete","2006-11-14","2006-11-13"]
["LN07040515","Write Bm Authorization Sheet (BAS) Requirements","2007-04-10","2007-05-21"]
["LN07040520","REQD: BC1 & L02 Comissioning Complete","2008-02-27","2008-02-26"]
["LN07040545","Commission BC2, Physics","2008-02-27","2008-03-11"]
["LN07040550","Commission BC2, Operations","2008-02-27","2008-03-11"]
["LN07040610","Support BC2 Comissioning Mechanical","2008-02-27","2008-03-11"]
["LN07040620","Support BC2 Comissioning Survey","2008-02-27","2008-03-11"]
["LN07040625","Support BC2 Comissioning Power Conv","2008-02-27","2008-03-11"]
["LN07040640","COMP: BC2 Comissioning Complete","2008-03-12","2008-03-11"]
["LN07040700","BC2 System Available for Undulator Commissioning","2008-05-09","2008-08-04"]
["LN0705","LINAC L03 INSTALLATION SUMMARY - 25,27,28,29","2006-07-24","2008-02-22"]
["LN07050000","Establish & Maintain Component Storage Facility","2006-07-24","2007-05-21"]
["LN07050005","REQD: L03 Available for Pre-Install Preps","2007-10-12","2007-10-11"]
["LN07050010","Create/Review Dwgs & Identify Installation Hdwr","2006-07-24","2006-08-18"]
["LN07050015","Procure Installation Hardware","2006-08-21","2007-06-19"]
["LN07050020","Review Drawings & Identify Installation Tooling","2006-07-24","2006-08-18"]
["LN07050025","Procure Installation Tooling","2006-08-21","2007-06-19"]
["LN07050030","Kit New Components for Installation","2007-06-20","2007-07-18"]
["LN07050035","Develop De-Installation Plan for Existing Equip","2006-07-24","2006-08-11"]
["LN07050040","De-install Existing Components","2007-10-12","2007-11-01"]
["LN07050045","Determine Disposition of De-installed Components","2007-10-19","2007-10-23"]
["LN07050050","Prep for & Move De-installed Equip to Storage","2007-10-24","2007-10-30"]
["LN07050055","Establish Alignment Coordinates for B/L Equip","2007-10-12","2007-10-19"]
["LN07050060","REQD: All Linac L03 Sys Equip Ready for Install","2007-11-30","2007-11-29"]
["LN07050100","Install All Racks, Cables, Trays & Test","2007-11-30","2008-01-22"]
["LN07050200","Install S-Band RF Components","2007-11-30","2007-12-13"]
["LN07050205","Install Beamline Components","2007-11-30","2008-01-07"]
["LN07050210","Align Beamline Components to Coordinate System","2008-01-08","2008-01-17"]
["LN07050215","Magnet Power Interconnect & Test","2008-01-18","2008-01-23"]
["LN07050220","Controls Interconnect & Test","2008-01-24","2008-01-31"]
["LN07050225","Interconnect Vacuum System & Test","2008-01-24","2008-01-31"]
["LN07050230","Perform Magnet Power Test","2008-02-01","2008-02-04"]
["LN07050235","Perform Diagnostics Controls Test","2008-02-05","2008-02-12"]
["LN07050240","Test & Tune S Band RF Equipment","2008-02-13","2008-02-14"]
["LN07050245","Coordinate & Check Installation","2008-02-15","2008-02-22"]
["LN07050250","AVAIL: L03 Equipment Installation Complete","2008-02-25","2008-02-22"]
["LN070505","LINAC L03 COMMISSIONING SUMMARY","2006-10-03","2008-08-04"]
["LN07050500","REQD: L03 Equipment Ready for Commissioning","2008-02-25","2008-02-22"]
["LN07050505","Develop Comissioning Plans","2006-10-03","2006-11-13"]
["LN07050510","COMP: Comissioning Plans Complete","2006-11-14","2006-11-13"]
["LN07050515","Write Bm Authorization Sheet (BAS) Requirements","2007-04-10","2007-05-21"]
["LN07050520","REQD: L02 & BC2 Comissioning Complete","2008-03-12","2008-03-11"]
["LN07050525","Commission L03, Physics","2008-03-12","2008-03-25"]
["LN07050530","Commission L03, Operations","2008-03-12","2008-03-25"]
["LN07050555","Support L03 Comissioning RF","2008-03-12","2008-03-25"]
["LN07050590","Support L03 Comissioning Mechanical","2008-03-12","2008-03-25"]
["LN07050600","Support L03 Comissioning Survey","2008-03-12","2008-03-25"]
["LN07050605","Support L03 Comissioning Power Conv","2008-03-12","2008-03-25"]
["LN07050620","COMP: L03 Comissioning Complete","2008-03-26","2008-03-25"]
["LN07050700","L03 System Available for Undulator Commissioning","2008-05-09","2008-08-04"]
["LN0706","LINAC LTU SYSTEM INSTALLATION SUMMARY","2006-06-01","2008-04-24"]
["LN07060000","Establish & Maintain Component Storage Facility","2006-07-24","2007-08-01"]
["LN07060005","REQD: LTU Available for Pre-Install Preps","2007-12-04","2007-12-03"]
["LN07060010","Create/Review Dwgs & Identify Installation Hdwr","2006-07-24","2006-08-18"]
["LN07060015","Procure Installation Hardware","2006-10-03","2007-10-11"]
["LN07060020","Review Drawings & Identify Installation Tooling","2006-07-24","2006-08-18"]
["LN07060025","Procure Installation Tooling","2006-10-03","2007-10-11"]
["LN07060030","Kit New Components for Installation","2007-10-12","2007-11-08"]
["LN07060035","Develop De-Installation Plan for Existing Equip","2006-07-24","2006-08-11"]
["LN07060040","REQD: FFTB Ready for Equip removal","2006-06-01","2006-05-31"]
["LN07060060","COMP: FFTB Equip Removal Comp Ready for CF","2006-07-21","2006-07-20"]
["LN07060065","Establish Alignment Coordinates for B/L Equip","2007-12-04","2007-12-06"]
["LN07060070","REQD: All Linac LTU Sys Equip Ready for Install","2008-02-25","2008-02-22"]
["LN07060100","Install All Racks, Cables, Trays & Test","2008-02-25","2008-03-28"]
["LN07060200","Install Beamline Components","2008-02-25","2008-03-14"]
["LN07060210","Align Beamline Components to Coordinate System","2008-03-17","2008-03-20"]
["LN07060215","Magnet Power Interconnect & Test","2008-03-21","2008-03-25"]
["LN07060220","Controls Interconnect & Test","2008-03-31","2008-04-02"]
["LN07060225","Interconnect Vacuum System & Test","2008-04-03","2008-04-07"]
["LN07060230","Perform Magnet Power Test","2008-04-08","2008-04-09"]
["LN07060235","Perform Diagnostics Controls Test","2008-04-10","2008-04-14"]
["LN07060245","Coordinate & Check Installation","2008-04-15","2008-04-24"]
["LN07060250","AVAIL: LTU Equipment Installation Complete","2008-04-25","2008-04-24"]
["LN070605","LINAC LTU COMMISSIONING SUMMARY","2006-10-03","2008-08-04"]
["LN07060500","REQD: LTU Equipment Ready for Commissioning","2008-04-25","2008-04-24"]
["LN07060505","Develop Comissioning Plans","2006-10-03","2006-11-13"]
["LN07060510","COMP: Comissioning Plans Complete","2006-11-14","2006-11-13"]
["LN07060515","Write Bm Authorization Sheet (BAS) Requirements","2007-04-10","2007-05-21"]
["LN07060520","REQD: L01,02,03 & BC1,2 Comissioning Complete","2008-03-26","2008-03-25"]
["LN07060525","Obtain Beam Authorization Sheet (BAS)","2008-03-26","2008-04-01"]
["LN07060530","PPS Checkout Linac","2008-04-02","2008-04-02"]
["LN07060535","Search and Lock Linac","2008-04-03","2008-04-03"]
["LN07060540","Commission LTU, Physics","2008-04-25","2008-05-08"]
["LN07060545","Commission LTU, Operations","2008-04-25","2008-05-08"]
["LN07060580","Support LTU Comissioning Hardware","2008-04-25","2008-05-08"]
["LN07060585","Support LTU Comissioning Mechanical","2008-04-25","2008-05-08"]
["LN07060590","Support LTU Comissioning Survey","2008-04-25","2008-05-08"]
["LN07060595","Support LTU Comissioning Power Conv","2008-04-25","2008-05-08"]
["LN07060600","COMP: LTU Commissioning Complete","2008-05-09","2008-05-08"]
["LN07060700","LTU System Available for Undulator Commissioning","2008-05-09","2008-08-04"]
["LN0707","LINAC E-DUMP SYSTEM INSTALLATION SUMMARY","2005-10-06","2008-02-26",null,"2005-10-06"]
["LN07070000","Establish & Maintain Component Storage Facility","2005-12-01","2007-01-30",null,"2005-12-01"]
["LN07070005","REQD: E-Dump Available for Pre-Install Preps","2007-12-03","2007-11-30"]
["LN07070010","Create/Review Dwgs & Identify Installation Hdwr","2005-10-06","2006-01-31",null,"2005-10-06"]
["LN07070015","Procure Installation Hardware","2006-10-03","2007-10-11"]
["LN07070020","Review Drawings & Identify Installation Tooling","2006-02-01","2006-03-01"]
["LN07070025","Procure Installation Tooling","2006-10-03","2007-10-11"]
["LN07070030","Kit New Components for Installation","2007-10-12","2007-11-08"]
["LN07070035","REQD: All E-Dump System Equip Avail for Install","2007-11-26","2007-11-21"]
["LN07070040","Establish Alignment Coordinates for B/L Equip","2007-12-03","2007-12-05"]
["LN07070100","Install All Racks, Cables, Trays & Test","2007-12-06","2008-01-28"]
["LN07070200","Install Beamline Components","2008-01-07","2008-01-28"]
["LN07070210","Align Beamline Components to Coordinate System","2008-01-29","2008-02-01"]
["LN07070215","Magnet Power Interconnect & Test","2008-02-04","2008-02-06"]
["LN07070220","Controls Interconnect & Test","2008-02-04","2008-02-06"]
["LN07070225","Interconnect Vacuum System & Test","2008-02-04","2008-02-06"]
["LN07070230","Perform Magnet Power Test","2008-02-07","2008-02-08"]
["LN07070235","Perform Diagnostics Controls Test","2008-02-11","2008-02-13"]
["LN07070245","Coordinate & Check Installation","2008-02-14","2008-02-26"]
["LN07070250","AVAIL: E-Dump Equipment Installation Complete","2008-02-27","2008-02-26"]
["LN070705","LINAC E-DUMP COMMISSIONING SUMMARY","2006-10-03","2008-06-06"]
["LN07070500","REQD: E-Dump Equipment Ready for Commissioning","2008-02-27","2008-02-26"]
["LN07070505","Develop Comissioning Plans","2006-10-03","2006-11-13"]
["LN07070510","COMP: Comissioning Plans Complete","2006-11-14","2006-11-13"]
["LN07070515","Write Bm Authorization Sheet (BAS) Requirements","2007-04-10","2007-05-21"]
["LN07070520","REQD: L01,2,3, BC1,2 & LTU Comissioning Complete","2008-05-23","2008-05-22"]
["LN07070535","Commission E-Dump, Physics","2008-05-23","2008-06-06"]
["LN07070540","Commission E-Dump, Operations","2008-05-23","2008-06-06"]
["LN07070565","Support E-Dump Comissioning Hardware","2008-05-23","2008-06-06"]
["LN07070570","Support E-Dump Comissioning Mechanical","2008-05-23","2008-06-06"]
["LN07070575","Support E-Dump Comissioning Survey","2008-05-23","2008-06-06"]
["LN07070580","Support E-Dump Comissioning Power Conv","2008-05-23","2008-06-06"]
["LN07070585","COMP: E-Dump Comissioning Complete Ready for Ops","2008-06-09","2008-06-06"]
["LN101_1000","L01 Top Assembly","2006-02-01","2006-05-01"]
["LN101_1010","L01 Procurement Support","2006-02-01","2006-06-30"]
["LN101_1020","L01 Fabrication Oversight","2006-02-01","2006-07-31"]
["LN101_1030","L01 Installation Coordination Planning","2006-02-01","2006-05-01"]
["LN101_1040","L01 Installation Oversight","2006-08-01","2006-11-30"]
["LN101_1050","L01 Documentation","2006-12-01","2007-07-31"]
["LN101_1060","L01 System Construction Support to Component","2006-12-01","2007-07-31"]
["LN101_2010","BC1 Emittance Section Layout","2005-12-01","2006-03-03",null,"2005-12-01"]
["LN101_2020","BC1 Emittance Section Design","2006-02-01","2006-07-31"]
["LN101_2100","BC1 Top Assembly","2006-02-01","2006-07-31"]
["LN101_2105","BC1 Bunch Length Monitor Integration","2005-12-01","2006-07-31",null,"2005-12-01"]
["LN101_2110","BC1 Procurement Support","2006-02-01","2006-07-31"]
["LN101_2120","BC1 Fabrication Oversight","2006-02-01","2006-07-31"]
["LN101_2130","BC1 Installation Coordination Planning","2006-03-01","2006-07-31"]
["LN101_2140","BC1 Installation Oversight","2006-08-01","2006-11-30"]
["LN101_2150","BC1 Documentation","2006-12-01","2007-07-31"]
["LN101_2160","BC1 System Construction Support to Component","2006-12-01","2007-07-31"]
["LN101_3100","L2 Top Assembly","2005-12-01","2006-10-02",null,"2005-12-01"]
["LN101_3110","L2 Procurement Support","2006-10-02","2007-07-02"]
["LN101_3120","L2 Fabrication Oversight","2006-10-02","2007-07-02"]
["LN101_3130","L2 Installation Coordination Planning","2006-12-01","2007-07-02"]
["LN101_3140","L2 Installation Oversight","2007-07-02","2007-10-31"]
["LN101_3150","L2 Documentation","2007-11-01","2008-06-30"]
["LN101_3160","L2 System Construction Support to Components","2007-11-01","2008-06-30"]
["LN101_4100","BC2 Top Assembly","2005-12-01","2006-10-31",null,"2005-12-01"]
["LN101_4102","BC2 Bunch Length Monitor Integration","2006-07-03","2007-07-02"]
["LN101_4104","BC2 Emittance Section Layout","2006-07-03","2007-01-02"]
["LN101_4106","BC2 Emittance Section Design","2006-10-02","2007-07-02"]
["LN101_4110","BC2 Procurement Support","2006-10-02","2007-07-02"]
["LN101_4120","BC2 Fabrication Oversight","2006-10-02","2007-07-02"]
["LN101_4130","BC2 Installation Coordination Planning","2006-11-01","2007-07-02"]
["LN101_4140","BC2 Installation Oversight","2007-07-02","2007-10-31"]
["LN101_4150","BC2 Documentation","2007-11-01","2008-06-30"]
["LN101_4160","BC2 System Construction Support to Component","2007-11-01","2008-06-30"]
["LN101_5100","L3 Top Assembly","2005-12-01","2006-10-02",null,"2005-12-01"]
["LN101_5110","L3 Procurement Support","2006-10-02","2007-07-02"]
["LN101_5120","L3 Fabrication Oversight","2006-10-02","2007-07-02"]
["LN101_5130","L3 Installation Coordination Planning","2007-01-02","2007-07-02"]
["LN101_5140","L3 Installation Oversight","2007-07-02","2007-10-31"]
["LN101_5150","L3 Documentation","2007-11-01","2008-06-30"]
["LN101_5160","L3 System Construction Support to Components","2007-11-01","2008-06-30"]
["LN101_6010","LTU Layout & CF Interface","2005-12-01","2006-05-30",null,"2005-12-01"]
["LN101_6100","LTU Top Assembly","2006-06-01","2007-01-02"]
["LN101_6102","LTU Pedestal and Raft Design","2006-10-02","2007-01-30"]
["LN101_6104","LTU Beamline Shielding Fabrication","2007-02-01","2007-04-30"]
["LN101_6106","LTU Pedestal and Raft Fabrication","2007-02-01","2007-04-30"]
["LN101_6110","LTU Procurement Support","2006-10-02","2007-04-30"]
["LN101_6120","LTU Fabrication Oversight","2006-10-02","2007-04-30"]
["LN101_6130","LTU Installation Coordination Planning","2006-11-01","2008-01-02"]
["LN101_6140","LTU Installation Oversight","2008-01-02","2008-04-30"]
["LN101_6150","LTU Documentation","2008-04-01","2008-09-30"]
["LN101_6160","LTU System Construction Support to Component","2008-05-01","2008-09-30"]
["LN101_7010","E-Dump Layout & CF Interface","2005-12-01","2006-05-01",null,"2005-12-01"]
["LN101_7100","E-Dump Top Assembly","2006-06-01","2007-01-02"]
["LN101_7102","E-Dump Pedestal and Raft Design","2006-10-02","2007-01-02"]
["LN101_7104","E-Dump Beamline Shielding Fabrication","2007-02-01","2007-04-30"]
["LN101_7106","E-Dump Pedestal and Raft Fabrication","2007-02-01","2007-04-30"]
["LN101_7110","E-Dump Procurement Support","2006-10-02","2007-04-30"]
["LN101_7120","E-Dump Fabrication Oversight","2006-10-02","2007-04-30"]
["LN101_7130","E-Dump Installation Coordination Planning","2006-11-01","2008-01-02"]
["LN101_7140","E-Dump Installation Oversight","2008-01-02","2008-04-30"]
["LN101_7150","E-Dump Documentation","2008-03-03","2008-09-30"]
["LN101_7160","E-Dump System CONST Support to Components","2008-03-03","2008-09-30"]
["LN104_1000","Linac System Management Effort - CONST","2005-12-01","2008-09-30",null,"2005-12-01"]
["LN104_1010","Cost Account Managers - CONST","2005-12-01","2008-09-30",null,"2005-12-01"]
["LN104_1020","Fabrication Coordination","2005-12-01","2008-09-30",null,"2005-12-01"]
["LN502_1000","STANDARD BPM (4) SUMMARY","2005-12-01","2006-09-20",null,"2005-12-01"]
["LN502_4000","BPM LARGE APERTURE (2) SUMMARY","2006-01-01","2006-08-22",null,"2006-01-01"]
["LN503_1000","TOROID BEAM CURRENT MONITOR (10)SUMMARY","2005-11-01","2006-09-29",null,"2005-11-01"]
["LN504_1000","BEAM STOPPER (4) SUMMARY","2005-12-01","2007-08-09",null,"2005-12-01"]
["LN505_1000","PROFILE MONITORS SUMMARY","2005-12-01","2007-07-26",null,"2005-12-01"]
["LN507_1000","CSR/OTR/CTR BLM (5) SUMMARY","2005-12-01","2006-05-11",null,"2005-12-01"]
["LN508_1000","PIC BLM (10) SUMMARY","2007-01-02","2007-08-17"]
["LN508_2000","PLIC BLM (4) SUMMARY","2007-06-01","2008-02-20"]
["LN509_1000","SINGLE BEAM DUMP (1) SUMMARY","2006-10-03","2007-11-07"]
["LN510_1000","ELECTRON BEAM DUMP (1) SUMMARY","2006-10-03","2007-07-05"]
["LN511_1000","PROTECTION COLLIMATORS (5) SUMMARY","2005-12-01","2006-07-31",null,"2005-12-01"]
["LN512_1000","MOVABLE COLLIMATORS (7X,3Y) SUMMARY","2005-12-01","2008-01-18",null,"2005-12-01"]
["LN513_1000","SAFETY ELECTRON DUMP (1) SUMMARY","2007-05-15","2007-12-13"]
["LNMS_0100","System Design Reviews Complete - L01","2005-12-01","2005-11-30",null,"2005-12-01","2005-11-30"]
["LNMS_0120","System Component Subcontracts Awarded - L01","2006-03-01","2006-02-28"]
["LNMS_0140","Ready to Begin Component Installation - L01","2006-08-01","2006-07-31"]
["LNMS_0200","System Design Reviews Complete - BC1","2005-12-01","2005-11-30",null,"2005-12-01","2005-11-30"]
["LNMS_0220","System Component Subcontracts Awarded - BC1","2006-03-01","2006-02-28"]
["LNMS_0240","Ready to Begin Component Installation - BC1","2006-08-01","2006-07-31"]
["LNMS_0260","Component Installation Completed - BC1","2007-01-26","2007-01-25"]
["LNMS_0300","System Design Reviews Complete - L02","2006-02-01","2006-01-31"]
["LNMS_0320","System Component Subcontracts Awarded - L02","2006-02-01","2006-01-31"]
["LNMS_0340","Ready to Begin Component Installation - L02","2007-09-04","2007-08-31"]
["LNMS_0360","Component Installation Completed - L02","2007-11-16","2007-11-15"]
["LNMS_0400","System Design Reviews Complete - BC2","2006-04-03","2006-03-31"]
["LNMS_0420","System Component Subcontracts Awarded - BC2","2006-07-03","2006-06-30"]
["LNMS_0440","Ready to Begin Component Installation - BC2","2007-09-04","2007-08-31"]
["LNMS_0500","System Design Reviews Complete - L03","2006-02-01","2006-01-31"]
["LNMS_0520","System Component Subcontracts Awarded - L03","2006-02-01","2006-01-31"]
["LNMS_0540","Ready to Begin Component Installation - L03","2007-09-04","2007-08-31"]
["LNMS_0560","Component Installation Completed - L03","2008-02-25","2008-02-22"]
["LNMS_0600","System Design Reviews Complete - LTU","2006-02-01","2006-01-31"]
["LNMS_0620","System Component Subcontracts Awarded - LTU","2006-02-01","2006-01-31"]
["LNMS_0640","Ready to Begin Component Installation - LTU","2007-12-04","2007-12-03"]
["LNMS_0700","System Design Reviews Complete - E-Dump","2006-02-01","2006-01-31"]
["LNMS_0720","System Component Subcontracts Awarded - E-Dump","2006-02-01","2006-01-31"]
["LNMS_0740","Ready to Begin Component Installation - E-Dump","2007-10-10","2007-10-09"]
["LNOPS_0000","Linac System Pre-Operations","2008-06-09","2009-03-30"]
["LN_LOE","Linac LOE Complete","2009-04-01","2009-03-31"]
["MS1_PM000","CD0 - Approve Mission Need","2001-06-18","2001-06-17",null,"2001-06-18","2001-06-17"]
["MS1_PM005","CD1 - Approve Preliminary Baseline Range","2002-10-17","2002-10-16",null,"2002-10-17","2002-10-16"]
["MS1_PM015","CD2a -  Approve Long-Lead Procurement Budget","2004-07-31","2004-07-30",null,"2004-07-31","2004-07-30"]
["MS1_PM020","CD2b - Approve Performance Baseline","2005-04-01","2005-03-31",null,"2005-04-01","2005-03-31"]
["MS1_PM025","CD3a - Approve Start of Long Lead Procurement","2004-10-30","2004-10-29",null,"2004-10-30","2004-10-29"]
["MS1_PM030","CD3b - Approve Start of Construction","2006-03-01","2006-02-28"]
["MS1_PM035","CD4 - Approve Start of Operations","2009-04-01","2009-03-31"]
["MS2BO_005","Sector 20 Alcove Beneficial Occupancy","2006-07-24","2006-07-21"]
["MS2BO_020","Linac Facility Beneficial Occupancy","2007-07-12","2007-07-11"]
["MS2BO_025","Research Yards Mods Beneficial Occupancy","2006-10-23","2006-10-20"]
["MS2BO_030","Beam Transport Hall Beneficial Occupancy","2008-01-04","2008-01-03"]
["MS2BO_035","Undulator Facility Beneficial Occupancy","2007-06-05","2007-06-04"]
["MS2BO_040","Front End Enclosure Beneficial Occupancy","2007-10-08","2007-10-05"]
["MS2BO_050","Near Experimental Hall Beneficial Occupancy","2007-06-19","2007-06-18"]
["MS2BO_055","X-Ray Transport Beneficial Occupancy","2007-10-15","2007-10-12"]
["MS2BO_060","Far Experimental Hall Beneficial Occupancy","2007-09-05","2007-09-04"]
["MS2BO_065","Central Lab Office Ctr Beneficial Occupancy","2008-11-11","2008-11-10"]
["MS2_IJ0010","Start Injector Commissioning (Drive Laser)","2006-11-20","2006-11-17"]
["MS2_IJ0020","Start Injector Commissioning(UV Beam to Cathode)","2007-07-23","2007-07-20"]
["MS2_IJ0027","Injector Laser Commissioning Review Complete","2007-01-17","2007-01-16"]
["MS2_IJ0030","Injector Accelerator Readiness Review (ARR) Comp","2007-09-21","2007-09-20"]
["MS2_LN015","Start Linac-to-Undulator (LTU) Commissioning","2008-06-12","2008-06-11"]
["MS2_LN020","Linac ARR (Li20-Li30)  Complete","2008-03-10","2008-03-07"]
["MS2_LN025","Start Linac (Li20-Li30) Commissioning","2008-05-08","2008-05-07"]
["MS2_PM005","Final Safety Analysis Document (FSAD) Approved","2008-04-01","2008-03-31"]
["MS2_PM030","LCLS ARR Complete (BTH thru FEH)","2008-06-10","2008-06-09"]
["MS2_PM035","DOE External Independent Review (EIR) Complete","2004-06-15","2004-06-14",null,"2004-06-15","2004-06-14"]
["MS2_PM040","Fire Hazard Analysis Approved","2005-09-01","2005-08-31",null,"2005-09-01","2005-08-31"]
["MS2_PM045","Prelim Safety Assessment (PSAD) Doc Comp","2004-05-01","2004-04-30",null,"2004-05-01","2004-04-30"]
["MS2_PM055","Prelim Safety Assessment (PSAD) Doc Approved","2006-03-01","2006-02-28"]
["MS2_UN005","MMF Qualified & Ready to Measure Prod Undulators","2006-11-21","2006-11-20"]
["MS2_UN010","Delivery of Undulator 1st Articles to MMF","2006-07-05","2006-07-03"]
["MS2_UN025","Start Undulator Commissioning (1st Light)","2008-08-18","2008-08-15"]
["MS2_XE005","Start XES Commissioning","2008-08-18","2008-08-15"]
["MS2_XE015","2-D Pixel Detector Production Start","2008-01-03","2008-01-02"]
["MS2_XT005","Start XTOD Commissioning","2008-08-18","2008-08-15"]
["MS3BO_005","Sector 20 Alcove Beneficial Occupancy","2006-04-03","2006-03-31"]
["MS3BO_020","Linac Facility Beneficial Occupancy","2007-06-12","2007-06-11"]
["MS3BO_025","Research Yards Mods Beneficial Occupancy","2006-09-22","2006-09-21"]
["MS3BO_030","Beam Transport Hall Beneficial Occupancy","2007-12-04","2007-12-03"]
["MS3BO_035","Undulator Facility Beneficial Occupancy","2007-05-04","2007-05-03"]
["MS3BO_040","Front End Enclosure Beneficial Occupancy","2007-09-06","2007-09-05"]
["MS3BO_050","Near Experimental Hall Beneficial Occupancy","2007-05-21","2007-05-18"]
["MS3BO_055","X-Ray Transport Beneficial Occupancy","2007-09-14","2007-09-13"]
["MS3BO_060","Far Experimental Hall Beneficial Occupancy","2007-08-06","2007-08-03"]
["MS3BO_065","Central Lab Office Ctr Beneficial Occupancy","2008-10-13","2008-10-10"]
["MS3_CF000","A&E Serv (S20, MMF, MCC not incl) Title 1 Comp","2004-05-01","2004-04-30",null,"2004-05-01","2004-04-30"]
["MS3_CF002","A&E Serv Sector 20 Title 1 Complete","2004-05-01","2004-04-30",null,"2004-05-01","2004-04-30"]
["MS3_CF005","A&E Serv (S20, MMF, MCC not incl) Title 2 Comp","2006-02-21","2006-02-17"]
["MS3_CF010","A&E Services Sector 20 Title 2 Complete","2005-03-19","2005-03-18",null,"2005-03-19","2005-03-18"]
["MS3_CF015","A&E Services MMF Title 2 Complete","2005-06-01","2005-05-31",null,"2005-06-01","2005-05-31"]
["MS3_CF022","A&E Services MMF Title 1 Complete","2004-05-01","2004-04-30",null,"2004-05-01","2004-04-30"]
["MS3_CF060","Award of Construction Management Package - Ph.1","2005-10-18","2005-10-17",null,"2005-10-18","2005-10-17"]
["MS3_CF065","Award of Sector 20 Title 3 Complete","2005-07-29","2005-07-28",null,"2005-07-29","2005-07-28"]
["MS3_CF066","Award of Magnetic Msmt Facility Title 3 Complete","2005-07-29","2005-07-28",null,"2005-07-29","2005-07-28"]
["MS3_CT070","Injector Controls Installation Complete","2008-01-02","2007-12-14"]
["MS3_CT075","Linac Controls Ready for Installation","2008-03-04","2008-03-03"]
["MS3_CT080","LTU Controls Ready for Installation","2008-02-07","2008-02-06"]
["MS3_CT090","PNET Integration Complete","2007-05-31","2007-05-30"]
["MS3_CT150","Personnel Protection Design Complete","2006-04-24","2006-04-21"]
["MS3_CT155","Machine Protection System First Article Complete","2006-04-24","2006-04-21"]
["MS3_IJ0010","Start Injector Commissioning (Drive Laser)","2006-10-18","2006-10-17"]
["MS3_IJ0020","Start Injector Commissioning(UV Beam to Cathode)","2007-06-21","2007-06-20"]
["MS3_IJ0027","Injector Laser Commissioning Review Complete","2007-01-02","2006-12-15"]
["MS3_IJ0030","Injector Accelerator Readiness Review (ARR) Comp","2007-08-21","2007-08-20"]
["MS3_IJ005","Drive Laser Available for Integration","2006-07-11","2006-07-10"]
["MS3_IJ010","Wall Region Installation Complete","2006-02-01","2006-01-31"]
["MS3_IJ020","Heater Region Installation Complete","2006-06-01","2006-05-31"]
["MS3_IJ032","Laser Tables & Optical Paths Installation Comp","2006-08-22","2006-08-21"]
["MS3_IJ080","Gun Region Installation Complete","2006-10-10","2006-10-09"]
["MS3_IJ085","Accelerator Region Installation Complete","2006-08-03","2006-08-02"]
["MS3_IJ095","Award of Drive Laser Contract Complete","2005-07-01","2005-06-30",null,"2005-07-01","2005-06-30"]
["MS3_IJ100","Insertion Region Installation Complete","2006-10-30","2006-10-27"]
["MS3_IJ105","Spectrometer Installation Complete","2006-10-30","2006-10-27"]
["MS3_IJ110","Injector RF Subsystem Installation Complete","2007-03-29","2007-03-28"]
["MS3_IJ115","Cathode Processing Station Installation Complete","2007-11-07","2007-11-06"]
["MS3_IJ120","Laser Heater Installation Complete","2007-11-27","2007-11-26"]
["MS3_IJ125","RF Gun Ready for Installation","2006-10-03","2006-10-02"]
["MS3_LN010","X-Band Klystron Ready for Installation","2006-11-28","2006-11-27"]
["MS3_LN011","BC2 Installation Complete","2008-02-11","2008-02-08"]
["MS3_LN012","BC1 Installation Complete","2006-11-30","2006-11-29"]
["MS3_LN013","Start BC1 Commissioning","2006-11-30","2006-11-29"]
["MS3_LN015","Start Linac-to-Undulator (LTU) Commissioning","2008-05-12","2008-05-09"]
["MS3_LN016","BC1 Magnets Ready for Installation","2006-10-25","2006-10-24"]
["MS3_LN020","Linac ARR (Li20-Li30)  Complete","2008-02-11","2008-02-08"]
["MS3_LN025","Start Linac (Li20-Li30) Commissioning","2008-04-08","2008-04-07"]
["MS3_LN030","Linac Commissioning Review Complete - S20-30","2007-01-30","2007-01-29"]
["MS3_LN032","Linac Commissioning Review Complete - LTU","2008-05-13","2008-05-12"]
["MS3_LN035","LTU Component Installation Complete","2008-05-12","2008-05-09"]
["MS3_LN055","E-Dump Component Installation Complete","2008-04-28","2008-04-25"]
["MS3_PM025","Advanced Procurement Management Plan Complete","2004-02-29","2004-02-28",null,"2004-02-29","2004-02-28"]
["MS3_PM030","LCLS ARR Complete (BTH thru FEH)","2008-05-12","2008-05-09"]
["MS3_PM031","Resource Loaded Cost & Schedule (Final) Complete","2004-05-01","2004-04-30",null,"2004-05-01","2004-04-30"]
["MS3_PM035","1st Monthly Report (with Earned Value) Submitted","2004-05-01","2004-04-30",null,"2004-05-01","2004-04-30"]
["MS3_PM040","Fire Hazard Analysis Review @ SLAC","2005-08-16","2005-08-15",null,"2005-08-16","2005-08-15"]
["MS3_PM042","Risk Management Plan Complete","2004-05-01","2004-04-30",null,"2004-05-01","2004-04-30"]
["MS3_PM045","Prelim Safety Assessment Doc (PSAD) Submitted","2004-05-01","2004-04-30",null,"2004-05-01","2004-04-30"]
["MS3_PM050","Project Mgmt Control Syst (PMCS) Review Complete","2004-05-01","2004-04-30",null,"2004-05-01","2004-04-30"]
["MS3_PM055","Project Mgmt Plan Complete","2004-05-01","2004-04-30",null,"2004-05-01","2004-04-30"]
["MS3_UN005","MMF Qualified & Ready to Measure Prod Undulators","2006-07-31","2006-07-28"]
["MS3_UN006","1st Article Vendor A Undulator 1 Rcvd @ SLAC","2006-06-05","2006-06-02"]
["MS3_UN010","1st Article Vendor B Undulator 2 Rcvd @ SLAC","2006-06-05","2006-06-02"]
["MS3_UN015","25% production undulators received","2006-09-27","2006-09-26"]
["MS3_UN018","Undulator Mock-up Completed","2006-05-01","2006-04-28"]
["MS3_UN020","Undulator System Installation Complete","2008-07-21","2008-07-18"]
["MS3_UN022","50% production undulators received","2006-12-13","2006-12-12"]
["MS3_UN025","Start Undulator Commissioning (1st Light)","2008-07-21","2008-07-18"]
["MS3_UN027","75% production undulators received","2007-03-26","2007-03-23"]
["MS3_UN028","Award of 1st Articles Mag Assy to Vendors Comp","2005-10-05","2005-10-04",null,"2005-10-05","2005-10-04"]
["MS3_UN029","Undulator Production Units (33) Received","2007-05-15","2007-05-14"]
["MS3_UN040","Hydrostatic Level System Complete","2008-07-21","2008-07-18"]
["MS3_UN042","Wire Monitoring System Complete","2008-07-21","2008-07-18"]
["MS3_XE005","Start XES Checkout","2008-03-04","2008-03-03"]
["MS3_XE012","XE Network Design Review Complete","2007-05-14","2007-05-11"]
["MS3_XE015","2-D Pixel Detector Production Start","2007-12-03","2007-11-30"]
["MS3_XE017","Final Design Review Beamline Control Complete","2007-09-05","2007-09-04"]
["MS3_XE020","XE Laser System Final Design Review Complete","2008-02-05","2008-02-04"]
["MS3_XE025","Award NH and FH Oscillator Laser/Pump","2008-04-08","2008-04-07"]
["MS3_XE030","Complete 2-D X-Ray Detector Statement of Work","2005-05-17","2005-05-16",null,"2005-05-17","2005-05-16"]
["MS3_XE035","Award Initial Funding for 2-D X-Ray Detector","2005-07-16","2005-07-15",null,"2005-07-16","2005-07-15"]
["MS3_XE040","FY-06 Design Review - 2-D X-Ray Detector","2006-11-21","2006-11-20"]
["MS3_XE060","Start XE Installation in Far Hall","2007-10-08","2007-10-05"]
["MS3_XE065","XE Beamline Control Complete","2008-07-09","2008-07-08"]
["MS3_XE070","Network & Cable Installation Complete","2008-10-13","2008-10-10"]
["MS3_XE075","XE Mechanical & Vacuum Installation Complete","2008-09-24","2008-09-23"]
["MS3_XE080","XE Laser Operating in Near Hall","2008-12-02","2008-12-01"]
["MS3_XE085","Complete Acceptance Tests for X-Ray Detectors","2009-01-21","2009-01-20"]
["MS3_XE090","COMP:  Specification for Streak Camera","2006-05-31","2006-05-30"]
["MS3_XE100","COMP: Hire Detector Physicist","2006-01-18","2006-01-17",null,"2006-01-18","2006-01-17"]
["MS3_XE110","COMP: Hire Atomic Physicist","2006-01-04","2006-01-03",null,"2006-01-04","2006-01-03"]
["MS3_XT000","FEE Mechanical/Vacuum Installation Complete","2008-02-13","2008-02-12"]
["MS3_XT007","Tunnel Mech/Vac Design Review Complete","2007-10-29","2007-10-26"]
["MS3_XT009","Far Hall Mech/Vac Design Review Complete","2007-04-27","2007-04-26"]
["MS3_XT020","Gas Attenuator Design Review Complete","2006-11-14","2006-11-13"]
["MS3_XT025","Solid Attenuator Ready to Ship to SLAC","2007-06-13","2007-06-12"]
["MS3_XT030","Indirect Imager Ready to Ship to SLAC","2007-09-11","2007-09-10"]
["MS3_XT035","Design Package - Spectral Measurement Complete","2007-01-03","2007-01-02"]
["MS3_XT040","Solid Attenuator Installation Complete","2008-01-02","2007-12-14"]
["MS3_XT043","Start XTOD Installation in Near Hall","2007-07-23","2007-07-20"]
["MS3_XT045","Gas Attenuator Installation Complete","2008-01-02","2007-12-14"]
["MS3_XT050","Tunnel Mech/Vac  Installation Complete","2008-01-02","2007-12-14"]
["MS3_XT055","XT Controls System Tests Complete","2008-01-31","2008-01-30"]
["MS3_XT060","Total Energy Measurement  Installation Complete","2007-11-20","2007-11-19"]
["MS3_XT066","Start Near Experimental Hall Checkout","2008-06-12","2008-06-11"]
["MS3_XT071","Start Far Experimental Hall Checkout","2008-06-12","2008-06-11"]
["MS3_XT080","Start Front End Enclosure Checkout","2008-03-04","2008-03-03"]
["MSBO_000","RF Hut Beneficial Occupancy","2006-03-10","2006-03-09"]
["MSBO_010","Magnetic Msmt Facility(MMF) Beneficial Occupancy","2006-04-04","2006-04-03"]
["MSBO_045","Beam Dump Beneficial Occupancy","2007-10-10","2007-10-09"]
["MSBS_090","Shutdown of FFTB Operations","2006-06-01","2006-05-31"]
["MSBS_115","FY05 Shutdown: HW Reqd for Installation","2005-10-03","2005-10-02",null,"2005-10-03","2005-10-02"]
["MSBS_120","FY05 Shutdown Over","2005-11-01","2005-10-31",null,"2005-11-01","2005-10-31"]
["MSBS_125","FY06 Shutdown: HW Reqd for Installation","2006-08-01","2006-07-31"]
["MSBS_130","FY06 Shutdown Over","2006-12-01","2006-11-30"]
["MSBS_135","FY07 Shutdown: HW Reqd for Installation","2007-09-04","2007-08-31"]
["MSBS_140","FY07 Shutdown Over","2007-12-03","2007-11-30"]
["MSBS_145","Start FY08 Shutdown","2008-10-01","2008-09-30"]
["MSBS_150","FY08 Shutdown Over","2009-01-05","2009-01-02"]
["MSC_CF000","CRIT:  Release RFP T3 Construct (RY-CLOC)","2006-02-01","2006-01-31"]
["MSC_CF005","CRIT: Rel RFP T3 Const. Pkg. RF Hut & S20/Alcove","2005-04-02","2005-04-01",null,"2005-04-02","2005-04-01"]
["MSC_CF006","CRIT:  Release RFP T3 Construction Pkg (Linac)","2006-08-22","2006-08-21"]
["MSC_CF010","CRIT: Release RFP T3 Construction Contract (MMF)","2005-04-15","2005-04-14",null,"2005-04-15","2005-04-14"]
["MSC_CF020","CRIT:  Release RFP Construction Mgmt Pkg (CM)","2005-07-26","2005-07-25",null,"2005-07-26","2005-07-25"]
["MSC_IJ000","CRIT: Release RFP for Drive Laser","2004-10-16","2004-10-15",null,"2004-10-16","2004-10-15"]
["MSC_LN005","CRIT: Release RFP X-Band Klystron","2005-02-26","2005-02-25",null,"2005-02-26","2005-02-25"]
["MSC_PM000","CRIT: Start Procurement Package - PMCS Support","2004-10-02","2004-10-01",null,"2004-10-02","2004-10-01"]
["MSC_UN005","CRIT: Release RFP Ti Strongback","2005-01-15","2005-01-14",null,"2005-01-15","2005-01-14"]
["MSC_UN010","CRIT: Release RFP  Magnet Blocks","2005-03-24","2005-03-23",null,"2005-03-24","2005-03-23"]
["MSC_UN015","CRIT: Release RFP Magnet Poles","2005-02-05","2005-02-04",null,"2005-02-05","2005-02-04"]
["MSC_UN016","CRIT: Release RFP - Quadrupoles","2006-04-13","2006-04-12"]
["MSC_UN020","CRIT: Release RFP Magnet Assemblies - 1st Art","2005-06-29","2005-06-28",null,"2005-06-29","2005-06-28"]
["MSC_UN030","CRIT: Release RFP - Fixed Supports","2006-06-28","2006-06-27"]
["MSC_XT001","CRIT: Release RFP Ion Gauges","2007-01-26","2007-01-25"]
["MSC_XT002","CRIT: Release RFP Ion Pumps","2007-01-26","2007-01-25"]
["MS_205","CR Funding","2004-12-28","2004-12-27",null,"2004-12-28","2004-12-27"]
["MS_210","FY05 Funding","2004-10-02","2004-10-01",null,"2004-10-02","2004-10-01"]
["MS_220","FY06 Funding","2006-02-01","2006-01-31"]
["MS_235","Swing Procurements Funding","2006-10-02","2006-09-29"]
["MS_250","FY07 - Spares Funds Available","2006-10-03","2006-10-02"]
["PM02020044","Design LLRF - Combined","2005-11-01","2006-06-30",null,"2005-11-01"]
["PM02020050","COMP: LLRF Design Combined","2006-07-03","2006-06-30"]
["PM02030311","Design Faraday Cup Controls","2005-08-01","2006-06-30",null,"2005-08-01"]
["PM02030314","COMP: Faraday Cup Controls Design","2006-07-03","2006-06-30"]
["PM02030411","Design Tune-up Dump Controls","2005-06-01","2006-06-02",null,"2005-06-01"]
["PM02030414","COMP: Tune-Up Dump Controls","2006-06-05","2006-06-02"]
["PM02030511","Design Profile Monitors","2005-08-01","2006-06-30",null,"2005-08-01"]
["PM02030514","COMP: Profile MonitorDesign","2006-07-03","2006-06-30"]
["PM100_0000","Global Laser Coordination - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM100_0005","Global Laser Coordination - FY06","2006-02-01","2006-09-29"]
["PM110_0010","Radiation Physics - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM110_0011","Radiation Physics- CONST FY06","2005-10-03","2006-09-29",null,"2005-10-03"]
["PM110_0012","Radiation Physics- CONST FY07-FY09","2006-10-02","2009-03-30"]
["PM11C_002","Global Controls Management - OPC FY06 forward","2006-02-01","2009-07-10"]
["PM120_0020","ESH Management & Coordination - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM120_0021","ESH Management & Coordination - (Hislop)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM120_0022","ESH Management & Coordination - (Hislop) -CONST","2005-10-03","2006-09-29",null,"2005-10-03"]
["PM120_0024","Hazard Analysis Consulting - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM120_002X","ESH Management & Coordination - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM120_0030","Seismic & Engineering - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM120_0031","Seismic & Engineering - CONST","2005-10-03","2009-03-30",null,"2005-10-03"]
["PM120_0A23","ESH Management & Coordination - CONST A","2005-10-03","2006-09-29",null,"2005-10-03"]
["PM120_0A25","Hazard Analysis Consulting - CONST A","2005-10-03","2006-09-29",null,"2005-10-03"]
["PM120_0B23","ESH Management & Coordination - CONST B","2006-10-02","2009-03-30"]
["PM120_0B25","Hazard Analysis Consulting - CONST B","2006-10-02","2009-03-30"]
["PM20101A05","RF Conditioning Controls Commissioning","2006-10-02","2006-12-05"]
["PM20101A10","RF Gun Ops with Beam-Controls Comissioning-A","2007-09-04","2007-12-05"]
["PM20101A15","RF Gun Ops with Beam-Controls Comissioning-B","2007-09-04","2007-09-21"]
["PM20101A20","L0-1&L0-2 Controls Commissioning","2008-01-11","2008-04-14"]
["PM20101A25","L0&SAB Controls Commissioning","2008-02-07","2008-03-12"]
["PM20101A30","DL1 Controls Commissioning","2008-01-25","2008-03-05"]
["PM20101A35","Injector Controls Optimization Commissioning","2007-02-28","2008-03-05"]
["PM20101B05","L1-BC1 Controls Commissioning","2007-02-26","2007-04-04"]
["PM20101B10","L2-BC2-L3 Controls Commissioning","2007-11-16","2008-01-24"]
["PM20101B15","LTU + Dump Controls Commissioning","2008-01-25","2008-03-19"]
["PM20101B20","Linac Controls Optimization Commissioning","2006-10-03","2007-10-08"]
["PM210_0130","Consulting SLAC Physicists (R&D)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM210_0240","Consulting Collaboration Physicists (R&D)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM210_0250","Global Controls Physicists Liaison (R&D)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM210_0260","R&D Studies & Prototyping","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM210_0265","Low Level Applications R&D","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM210_0270","Consulting SLAC Physicists (PreOps)","2005-10-03","2009-03-30",null,"2005-10-03"]
["PM210_0271","Planning Experiment Startup (Preops)","2005-11-01","2006-03-31",null,"2005-11-01"]
["PM210_0275","Low Level Applications Commissioning","2005-10-03","2009-03-30",null,"2005-10-03"]
["PM210_0280","Global Controls Physicists Liaison (PreOps)","2005-10-03","2006-09-29",null,"2005-10-03"]
["PM210_0281","Global Controls Physicists Liaison (PreOps)","2006-10-02","2009-03-30"]
["PM210_0290","Physics Group Leader (R&D)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM210_0291","Define Technical Requirements/Parameters(PED)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM210_0292","Define Technical Requirements/Parameters(LLP)","2005-10-03","2006-09-29",null,"2005-10-03"]
["PM210_0300","Injector Physicists (R&D)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM210_0310","Linac Physicists (R&D)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM210_0320","Undulator Physicists (R&D)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM210_0330","X-Ray Transport Physicists (R&D)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM210_0340","X-Ray Endstation Physicists (R&D)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM210_0350","Conventional Facility Physicists (R&D)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM210_0360","Physics Group Leader (PreOps)","2005-10-03","2009-03-30",null,"2005-10-03"]
["PM210_0370","Injector Physicists (PreOps)","2005-10-03","2006-09-29",null,"2005-10-03"]
["PM210_0371","Injector Physicists (PreOps)","2006-10-02","2009-03-30"]
["PM210_0375","Laser & RF Gun Physics Development (R&D)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM210_0380","Linac Physicists (PreOps)","2005-10-03","2006-09-29",null,"2005-10-03"]
["PM210_0381","Linac Physicists (PreOps)","2006-10-02","2009-03-30"]
["PM210_0385","Laser & RF Gun Physics Development (PreOps)","2005-10-03","2009-03-30",null,"2005-10-03"]
["PM210_0390","Undulator Physicists (PreOps)","2005-10-03","2006-09-29",null,"2005-10-03"]
["PM210_0391","Undulator Physicists (PreOps)","2006-10-02","2009-03-30"]
["PM210_0400","X-Ray Transport Physicists (PreOps)","2005-10-03","2009-03-30",null,"2005-10-03"]
["PM210_0410","X-Ray Endstation Physicists (PreOps)","2005-10-03","2009-03-30",null,"2005-10-03"]
["PM210_0420","Conventional Facility Physicists (PreOps)","2005-10-03","2006-09-29",null,"2005-10-03"]
["PM210_0421","Conventional Facility Physicists (PreOps)","2006-10-02","2009-03-30"]
["PM210_0430","Consulting Collaboration Physicists (PreOps)","2005-10-03","2009-03-30",null,"2005-10-03"]
["PM210_0440","Physics Programmatic Travel (R&D)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM210_0450","Physics Progammatic Travel (PreOps)","2005-10-03","2009-03-30",null,"2005-10-03"]
["PM210_0460","SAC/FAC Travel - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM210_0470","SAC/FAC Travel (PreOps)","2005-10-03","2009-03-30",null,"2005-10-03"]
["PM210_0480","Pre-ops Electrical Power Usage (1.5k hrs) - 2007","2006-10-03","2007-09-28"]
["PM210_0490","Pre-ops Electrical Power Usage (3.0k hrs) - 2008","2007-10-02","2008-09-30"]
["PM210_0494","Additional Startup Costs-FY08","2007-10-02","2008-09-30"]
["PM210_0495","Pre-ops Electrical Power Usage (3.0k hrs) - 2009","2008-10-01","2009-03-30"]
["PM210_0497","Additional Startup Costs-FY09","2008-10-02","2009-03-31"]
["PM210_0510","SLAC Linac Legacy Upgrades","2006-10-02","2007-09-28"]
["PM210_0515","Control Room Support","2008-06-02","2009-03-30"]
["PM210_1000","PMCS Support - Maintenance - FY07","2006-10-02","2007-09-28"]
["PM210_1010","PMCS Support - Maintenance - FY08","2007-10-01","2008-09-30"]
["PM210_1020","PMCS Support - Maintenance - FY09","2008-10-01","2009-03-30"]
["PM211_0010","Project Director - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM211_0011","Project Director - CONST FY06","2005-10-03","2006-09-29",null,"2005-10-03"]
["PM211_0012","Project Director - CONST FY07-FY09","2006-10-02","2009-03-30"]
["PM211_0020","Chief Engineer - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM211_0021","Chief Engineer - CONST FY06","2005-10-03","2006-09-29",null,"2005-10-03"]
["PM211_0022","Chief Engineer - CONST FY07-FY09","2006-10-02","2009-03-30"]
["PM211_0025","E-Beam Systems Manager - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM211_0027","E-Beam Systems Manager - FY06","2006-02-01","2006-09-29"]
["PM211_0030","Budget/Finance Officer - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM211_0031","Budget/Finance Officer - FY06","2006-02-01","2006-09-29"]
["PM211_0040","Administrative Support - SLAC 1 - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM211_0041","Administrative Support - SLAC 1 - FY06","2006-02-01","2006-09-29"]
["PM211_0050","Administrative Support - SLAC 2 - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM211_0051","Administrative Support - SLAC 2 - FY06","2006-02-01","2006-09-29"]
["PM211_0052","Administrative Support - CF & Proc - FY06","2006-02-01","2006-09-29"]
["PM211_0055","Administrative Support - CF & Proc - PED","2005-07-01","2005-09-30",null,"2005-07-01","2005-09-30"]
["PM211_0060","Photon System Manager - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM211_0061","Photon System Manager - FY06","2006-02-01","2006-09-29"]
["PM211_1010","E-Beam Systems Manager - FY07-09","2006-10-02","2009-03-30"]
["PM211_1020","Budget/Finance Officer - FY07-09","2006-10-02","2009-03-30"]
["PM211_1030","Photon System Manager - FY07-09","2006-10-02","2009-03-30"]
["PM211_1040","Administrative Support -SLAC 1 - FY07-09","2006-10-02","2009-03-30"]
["PM211_1050","Administrative Support - SLAC 2 - FY07-09","2006-10-02","2009-03-30"]
["PM211_1060","Administrative Support - CF & Proc - FY07-09","2006-10-02","2009-03-30"]
["PM212_0016","PMCS Support - Maintenance - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM212_0017","PMCS Support - Maintenance - FY06","2005-10-03","2006-09-29",null,"2005-10-03"]
["PM212_0018","AWARD:  PMCS Support-FY06","2005-10-03","2005-10-12",null,"2005-10-03","2005-10-12"]
["PM212_0020","Website Support - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM212_0021","Website Support - CONST","2005-10-03","2009-03-30",null,"2005-10-03"]
["PM212_0022","AWARD:  PMCS Support-FY07","2006-10-02","2006-10-11"]
["PM212_0023","AWARD:  PMCS Support-FY08","2007-10-01","2007-10-10"]
["PM212_0024","AWARD:  PMCS Support-FY09","2008-10-01","2008-10-10"]
["PM212_0030","Relational Database Support - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM212_0031","Relational Database Support - CONST","2005-10-03","2009-03-30",null,"2005-10-03"]
["PM212_0040","Procurement Support - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM212_0041","Procurement Support - CONST","2005-10-03","2009-03-30",null,"2005-10-03"]
["PM212_0050","QA/QC Support - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM212_0051","QA/QC Support - CONST","2005-10-03","2009-03-30",null,"2005-10-03"]
["PM212_0060","Software Licenses - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM212_0061","Software Licenses - CONST","2005-10-03","2009-03-30",null,"2005-10-03"]
["PM212_0070","Computing Support - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM212_0071","Computing Support - CONST","2005-10-03","2009-03-30",null,"2005-10-03"]
["PM212_0080","Recruiting/Relocation Support - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM212_0081","Recruiting/Relocation Support - CONST","2005-10-03","2009-03-30",null,"2005-10-03"]
["PM212_0717","PMCS Support - Maintenance - FY07","2006-10-02","2007-09-28"]
["PM212_0817","PMCS Support - Maintenance - FY08","2007-10-01","2008-09-30"]
["PM212_0917","PMCS Support - Maintenance - FY09","2008-10-01","2009-03-30"]
["PM213_0000","Project Director - R&D","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM213_0001","Project Director -PREOPS FY07-FY09","2006-10-02","2009-03-30"]
["PM213_0005","Chief Engineer - R&D","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM213_0006","Chief Engineer - PREOPS FY07-FY09","2006-10-02","2009-03-30"]
["PM213_0007","E-Beam Systems Oversight Manager - R&D","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM213_0010","SLAC Project Office M&S - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM213_0011","SLAC Project Office M&S - CONST","2005-10-03","2005-11-30",null,"2005-10-03","2005-11-30"]
["PM213_0012","SLAC Project Office M&S - CONST FY06","2005-12-01","2006-09-29",null,"2005-12-01"]
["PM213_0013","SLAC Project Office M&S - CONST FY07-FY09","2006-10-02","2009-03-30"]
["PM213_0015","Budget/Finance Officer - R&D","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM213_0020","Tele/Video Conferencing  - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM213_0021","Tele/Video Conferencing - CONST","2005-10-03","2009-03-30",null,"2005-10-03"]
["PM213_0025","Administrative Support - SLAC 1 - R&D","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM213_0030","Computer M&S - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM213_0031","Computer M&S - CONST","2005-10-03","2009-03-30",null,"2005-10-03"]
["PM213_0040","Misc. Shipping/Storage Costs - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM213_0041","Misc. Shipping/Storage Costs CONST","2005-10-03","2009-03-30",null,"2005-10-03"]
["PM213_0050","Project Related Travel - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM213_0051","Project Related Travel - CONST","2005-10-03","2009-03-30",null,"2005-10-03"]
["PM213_0055","Building Refurb/Remodeling @ SLAC - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM213_0060","Building Refurb/Remodeling @ SLAC - CONST","2005-10-03","2009-03-30",null,"2005-10-03"]
["PM213_0070","Review Committee Support - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM213_0071","Review Committee Support - CONST","2005-10-03","2009-03-30",null,"2005-10-03"]
["PM213_0100","SSRL Physics Support","2005-05-02","2005-06-30",null,"2005-05-02","2005-06-30"]
["PM213_0105","SSRL Physics Support","2005-10-03","2005-12-16",null,"2005-10-03","2005-12-16"]
["PM22210000","Define Injector Timing module Reqmts CP","2005-06-01","2006-04-18",null,"2005-06-01"]
["PM22210003","Controls Commissioning","2006-12-06","2007-10-17"]
["PM22210005","COMP: Injector Timing Module Rqmts Def","2006-04-19","2006-04-18"]
["PM22210010","Prep Bid Pak-Injector Timing modules","2005-09-01","2006-03-01",null,"2005-09-01"]
["PM22210015","RELEASE: RFP-Injector Timing modules","2006-03-02","2006-03-01"]
["PM22210020","Vendors Prep Prop-Injector Timing Modules","2006-03-02","2006-03-30"]
["PM22210025","RCV: Prop-Injector Timing modules","2006-03-31","2006-03-30"]
["PM22210030","Evaluate Vendor Proposals","2006-02-01","2006-02-14"]
["PM22210045","Manage/Work with Vendor","2005-09-01","2006-05-10",null,"2005-09-01"]
["PM22210050","RCV: Injector Timing Modules from Vendor","2006-05-11","2006-05-10"]
["PM22210055","Procure SLCnet cable to MPG micro 360 Hz signal","2007-02-01","2007-02-14"]
["PM22210060","Procure VME crate (1) w/IOC(1), VxWorks license","2005-09-01","2005-09-30",null,"2005-09-01","2005-09-30"]
["PM22210065","Procure cables","2006-05-11","2006-06-09"]
["PM22210070","Write Test Docs - Injector Timing modules","2005-09-01","2006-02-07",null,"2005-09-01"]
["PM22210075","Install access to PEP-II timing signal, control","2007-02-15","2007-02-15"]
["PM22210080","RCV: Procured parts","2006-06-12","2006-06-09"]
["PM22210083","Assemble procured parts","2006-06-12","2006-07-06"]
["PM22210085","AVAIL: Test Stand Installed in Test Lab","2006-07-07","2006-07-06"]
["PM22210090","Procure Master & Distributed Timing Hardware","2006-09-19","2007-01-02"]
["PM22210095","Procure Splitter to Main Drive Line (MDL) 476 MH","2006-09-19","2007-01-02"]
["PM22210100","Procure Fiducial Output Module","2006-09-19","2007-01-02"]
["PM22210105","Procure Fiducial RF Amplifier","2006-09-19","2007-01-02"]
["PM22210110","Procure SLCnet cable to MPG micro 360 Hz signal","2006-09-19","2007-01-02"]
["PM22210115","Procure Timing System Heliax Cableplant","2006-09-19","2007-01-02"]
["PM22210116","Implement Fast-feedback in the IOC","2006-06-28","2007-01-02"]
["PM22210117","Port Fast-feedbac software from Kissnet to Ether","2007-01-03","2007-01-31"]
["PM22210160","Write Test S/W - Injector Timing modules","2005-09-01","2006-02-14",null,"2005-09-01"]
["PM22210165","Integrate software & hardware","2006-07-07","2006-07-20"]
["PM22210170","Integrate with SLC TIming Sys","2007-02-16","2007-03-16"]
["PM22210175","Perform lab tests on Injector Timing modules","2007-02-16","2007-03-16"]
["PM22210180","AVAIL: Injector Timing Ready for Install","2007-03-19","2007-03-16"]
["PM300_0050","Global Alignment Coordination - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM300_0051","Global Alignment Coordination - CONST","2005-10-03","2009-03-30",null,"2005-10-03"]
["PM300_0060","Installation Coordination - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM300_0061","Installation Coordination - CONST","2005-10-03","2009-03-30",null,"2005-10-03"]
["PM300_0062","Design Supervisor - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM300_0063","Design Supervisor - CONST","2005-10-03","2009-03-30",null,"2005-10-03"]
["PM300_0150","Surface Network Oversight and Integration","2005-10-03","2007-09-28",null,"2005-10-03"]
["PM300_0160","Procure Surface Network Components","2005-10-03","2006-04-07",null,"2005-10-03"]
["PM300_0170","Install and Measure Surface Network","2005-10-03","2007-09-28",null,"2005-10-03"]
["PM301_7000","Global Laser Coordination - FY07","2006-10-02","2007-09-28"]
["PM301_7010","E-Beam Systems Manager - FY07","2006-10-02","2007-09-28"]
["PM301_7020","Budget/Finance Officer - FY07","2006-10-02","2007-09-28"]
["PM301_7030","Photon System Manager - FY07","2006-10-02","2007-09-28"]
["PM301_7040","Administrative Support -SLAC 1 - FY07","2006-10-02","2007-09-28"]
["PM301_7050","Administrative Support - SLAC 2 - FY07","2006-10-02","2007-09-28"]
["PM301_7060","Administrative Support - CF & Proc - FY07","2006-10-02","2007-09-28"]
["PM301_8000","Global Laser Coordination - FY08","2007-10-01","2008-09-30"]
["PM301_8010","E-Beam Systems Manager - FY08","2007-10-01","2008-09-30"]
["PM301_8020","Budget/Finance Officer - FY08","2007-10-01","2008-09-30"]
["PM301_8030","Photon System Manager - FY08","2007-10-01","2008-09-30"]
["PM301_8040","Administrative Support -SLAC 1 - FY08","2007-10-01","2008-09-30"]
["PM301_8050","Administrative Support - SLAC 2 - FY08","2007-10-01","2008-09-30"]
["PM301_8060","Administrative Support - CF & Proc - FY08","2007-10-01","2008-09-30"]
["PM301_9000","Global Laser Coordination - FY09","2008-10-01","2009-03-30"]
["PM301_9010","E-Beam Systems Manager - FY09","2008-10-01","2009-03-30"]
["PM301_9020","Budget/Finance Officer - FY09","2008-10-01","2009-03-30"]
["PM301_9030","Photon System Manager - FY09","2008-10-01","2009-03-30"]
["PM301_9040","Administrative Support -SLAC 1 - FY09","2008-10-01","2009-03-30"]
["PM301_9050","Administrative Support - SLAC 2 - FY09","2008-10-01","2009-03-30"]
["PM301_9060","Administrative Support - CF & Proc - FY09","2008-10-01","2009-03-30"]
["PM3051101","Design MPS","2005-12-01","2006-05-25",null,"2005-12-01"]
["PM3051111","COMP: MPS Design","2006-05-26","2006-05-26"]
["PM3051121","Write First Article for MPS","2006-05-30","2007-01-16"]
["PM3051131","Procure 1 Set MPS Cntrls Misc. Hardware","2006-05-30","2006-06-26"]
["PM3051141","RCV: Parts - Controls MPS","2006-06-27","2006-06-26"]
["PM400_0030","Education Support - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM400_0031","Education Support - CONST","2005-10-03","2009-03-30",null,"2005-10-03"]
["PM400_0040","Education/Outreach M&S - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM400_0041","Education/Outreach M&S - CONST","2005-10-03","2009-03-30",null,"2005-10-03"]
["PM502_0001","Build RF Boards - Rev .B.C.D","2005-11-01","2006-10-16",null,"2005-11-01"]
["PM502_0005","Write First Article RF S/W Documentation","2005-11-01","2006-10-16",null,"2005-11-01"]
["PM502_0010","Build First Article Hardware","2006-10-17","2007-01-29"]
["PM50301001","Design Linac Wire Scanners","2005-05-02","2006-06-30",null,"2005-05-02"]
["PM50301005","COMP: Linac Wire Scanner Dsgn - Release for Fab","2006-07-03","2006-06-30"]
["PM50301010","Write First Article SW","2006-07-03","2006-09-29"]
["PM50302006","Design Toroid Controls","2005-08-01","2006-06-30",null,"2005-08-01"]
["PM50302007","COMP: Toroid Controls Design","2006-07-03","2006-06-30"]
["PM50302010","Write First Article SW - Toroid","2006-07-03","2006-09-07"]
["PM50303001","Write First Article SW - Faraday Cups","2006-07-03","2006-10-24"]
["PM50305010","Write First Article S/W for Profile Monitors","2006-07-03","2007-01-22"]
["PM50306011","Design EO Disgnostics","2006-02-01","2006-06-22"]
["PM50307006","Design BPMs","2005-05-02","2006-06-30",null,"2005-05-02"]
["PM50307007","COMP: BPM Design","2006-07-03","2006-07-03"]
["PM50307010","Write First Article S/W for BPMs","2006-11-01","2006-10-05",null,"2006-11-01"]
["PM50307015","Procure Prototype Board & Parts","2006-02-01","2006-05-01"]
["PM50307025","RCV: design board & parts","2006-05-02","2006-05-01"]
["PM50308001","Design Linac Stoppers","2005-12-01","2007-04-16",null,"2005-12-01"]
["PM50308005","COMP: Controls Design - Stoppers","2007-04-17","2007-04-16"]
["PM50309001","Design Bunch Length Monitors","2005-12-01","2006-06-30",null,"2005-12-01"]
["PM50309005","COMP: Controls Design - Bunch Length Monitors","2006-07-03","2006-06-30"]
["PM50310001","Design Beam Loss Monitors","2006-02-01","2006-07-31"]
["PM50310005","COMP: Controls Design - Beam Loss Monitors","2006-08-01","2006-07-31"]
["PM504_0001","Design Gun Laser","2005-10-03","2006-04-26",null,"2005-10-03"]
["PM504_0005","COMP: Gun Laser Controls Design","2006-04-27","2006-04-26"]
["PM504_0015","Laser Controls Design Support","2006-04-27","2006-10-16"]
["PM505_0001","Design Laser Heater Controls","2006-10-17","2007-04-23"]
["PM505_0005","COMP: Laser Heater Controls Design","2007-04-24","2007-04-23"]
["PM506_0001","Timing Subsystem Design","2005-06-08","2006-04-12",null,"2005-06-08"]
["PM506_0003","Timing Controls 1st Article","2005-06-08","2006-09-18",null,"2005-06-08"]
["PM506_0005","COMP: Controls Design - Linac Timing","2006-09-19","2006-09-18"]
["PM507_0001","Design Vacuum Controls","2005-05-02","2006-05-26",null,"2005-05-02"]
["PM507_0005","COMP: Vacuum Controls Design","2006-05-30","2006-05-26"]
["PM507_0010","First Article Vacuum Software","2005-11-01","2006-09-18",null,"2005-11-01"]
["PM509_0006","Design Power Supply - NEW","2005-05-02","2006-02-23",null,"2005-05-02"]
["PM509_0010","COMP: Power Supply Design","2006-02-24","2006-02-23"]
["PM509_0012","Write First Article S/W for Power Supplies","2006-02-24","2006-07-17"]
["PM509_0015","Define Power Conv Spec Requirements","2005-05-02","2005-08-29",null,"2005-05-02","2005-08-29"]
["PM509_0020","COMP: Injector Power Conv Spec Requirements","2006-02-01","2006-01-31"]
["PM509_0035","Prep Bid Pak -  Power Supplies - (Dipole Type)","2005-07-01","2005-08-31",null,"2005-07-01","2005-08-31"]
["PM509_0040","Prep Bid Pak -  Power Supplies - (Trim Type)","2005-08-01","2005-08-31",null,"2005-08-01","2005-08-31"]
["PM510_0061","PPS L1 DESIGN","2006-01-03","2006-09-01",null,"2006-01-03"]
["PM510_0062","COMP: PPS/MPS Design","2006-09-05","2006-09-05"]
["PM510_0072","PPS L2 Design","2006-09-06","2007-04-24"]
["PM510_0075","COMP: PPS L2 DESIGN","2007-04-25","2007-04-25"]
["PM510_0082","PPS L3 Design","2007-04-26","2007-11-28"]
["PM510_0085","COMP: PPS L3 DESIGN","2007-11-29","2007-11-29"]
["PM512_0001","Global Controls Management - PED","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["PM512_0002","Global Contorls Mgmt - PED Supplemental","2005-08-01","2005-09-30",null,"2005-08-01","2005-09-30"]
["PM512_0005","Global Controls Management - CONST","2005-10-30","2009-03-30",null,"2005-10-30"]
["PM512_0015","Global Controls System Administrator - CONST","2005-10-30","2009-03-30",null,"2005-10-30"]
["PM512_0020","Write low level application SW Rqrmnts - PED","2005-05-02","2006-05-01",null,"2005-05-02"]
["PM512_0025","bbWrite low level application SW Rqrmnts - CONST","2006-02-01","2006-09-29"]
["PM512_0026","Write Low Level application SW Rqrmnts - Const","2007-01-17","2007-11-26"]
["PM512_0030","High Level Application Programming - 1st Phase","2005-12-01","2005-12-16",null,"2005-12-01","2005-12-16"]
["PM512_0035","High Level Application Programming - CON","2005-12-01","2006-05-02",null,"2005-12-01"]
["PM512_0040","High Level Application Programming - CONST","2006-02-01","2006-11-09"]
["PM512_0041","High Level Application Programming - CONST","2006-11-10","2007-11-21"]
["PM512_0045","LCLS Beam Instrumentatn Cntls & Test Equip FY05","2005-06-01","2005-09-30",null,"2005-06-01","2005-09-30"]
["PM512_0046","LCLS Beam Instrumentatn Cntls & Test Equip FY06","2006-02-01","2007-01-30"]
["PM512_0047","LCLS Beam Instrumentatn Cntls & Test Equip FY07","2007-01-31","2008-01-31"]
["PM512_0050","SLAC Place Order Beam Instrument Cntls &Test Equ","2006-02-01","2006-04-05"]
["PM512_0055","RCV: Beam Instrument Cntls & Test Equip","2006-04-06","2006-04-05"]
["PM512_0060","SLAC MCC Controls Upgrade","2006-10-03","2007-10-05"]
["PM512_0065","SLAC Place Order Controls Upgrade","2006-10-03","2006-11-13"]
["PM512_0070","RCV: Controls Upgrade","2006-11-14","2006-11-13"]
["PM513_0001","SLC Aware IOC - PED","2005-05-02","2005-10-25",null,"2005-05-02","2005-10-25"]
["PM513_0005","SLC Aware IOC - CON","2005-10-03","2005-12-28",null,"2005-10-03","2005-12-28"]
["PMLCLS_LOE","LCLS LOE Complete","2009-04-01","2009-03-31"]
["PM_LOE","PM LOE Complete","2009-07-13","2009-07-10"]
["SSCF_0110","S20 Injector Facility Construction","2006-02-01","2006-03-27"]
["SSCF_0115","S20 Injector Facility Alcove B.O.","2006-07-24","2006-07-21"]
["SSCF_0200","Linac Facility Title 1","2006-02-01","2010-04-05"]
["SSCF_0205","Linac Facility Title 2","2006-02-01","2010-04-05"]
["SSCF_0210","Linac Facility Construction","2006-02-01","2010-04-05"]
["SSCF_0215","Linac Facility B.O.","2007-07-12","2007-07-11"]
["SSCF_0310","Main Control Center Construction","2006-02-01","2010-04-05"]
["SSCF_0400","CRIT: Magnetic Measurement Facility","2005-05-02","2005-05-01",null,"2005-05-02","2005-05-01"]
["SSCF_0415","Magnetic Measurment Facility Construction","2006-02-01","2006-04-11"]
["SSCF_0420","Magnetic Measurment Facility B.O.","2006-04-04","2006-04-03"]
["SSCF_0505","Undulator Facility Title 2","2006-02-01","2010-04-05"]
["SSCF_0510","Undulator Facility Construction","2006-08-25","2007-04-30"]
["SSCF_0515","Undulator Facility B.O.","2007-06-05","2007-06-04"]
["SSCF_0605","Beam Dump Title 2","2006-02-01","2010-04-05"]
["SSCF_0610","Beam Dump Construction","2006-02-01","2010-04-05"]
["SSCF_0615","Beam Dump B.O.","2007-10-10","2007-10-09"]
["SSCF_0705","Research Yard Mods Title 2","2006-02-01","2010-04-05"]
["SSCF_0710","Research Yard Mods Construction","2006-02-01","2010-04-05"]
["SSCF_0715","Research Yard Mods B.O.","2006-10-23","2006-10-20"]
["SSCF_0805","Near Experimental Hall Title 2","2006-02-01","2010-04-05"]
["SSCF_0810","Near Experimental Hall Construction","2006-02-01","2010-04-05"]
["SSCF_0815","Near Experimental Hall B.O.","2007-06-19","2007-06-18"]
["SSCF_0905","Far Experimental Hall Title 2","2006-02-01","2010-04-05"]
["SSCF_0910","Far Experimental Hall Construction","2006-02-01","2010-04-05"]
["SSCF_0915","Far Experimental Hall B.O.","2007-09-05","2007-09-04"]
["SSCF_1005","Front End Enclosure Title 2","2006-02-01","2010-04-05"]
["SSCF_1010","Front End Enclosure Construction","2006-02-01","2010-04-05"]
["SSCF_1015","Front End Enclosure B.O.","2007-10-08","2007-10-05"]
["SSCF_1105","Beam Transport Hall  Title 2","2006-02-01","2010-04-05"]
["SSCF_1107","FFTB Demolition","2006-02-01","2010-04-05"]
["SSCF_1110","Beam Transport Hall Construction","2006-02-01","2010-04-05"]
["SSCF_1115","Beam Transport Hall  B.O.","2008-01-04","2008-01-03"]
["SSCF_1205","Central Lab Office Center Title 2","2006-02-01","2010-04-05"]
["SSCF_1210","Central Lab Office Center Construction","2006-02-01","2010-04-05"]
["SSCF_1215","Central Lab Office Center B.O.","2008-11-11","2008-11-10"]
["SSCF_1305","X-Ray Transport & Diagnostics Tunnel Title 2","2006-02-01","2010-04-05"]
["SSCF_1310","X-Ray Transport&Diagnostics Tunnel Construction","2006-02-01","2010-04-05"]
["SSCF_1315","X-Ray Transport & Diagnostics Tunnel B.O.","2007-10-15","2007-10-12"]
["SSIJ_0105","Optics Assembly Lab Available","2006-02-01","2006-01-31"]
["SSIJ_0110","Drive Laser Design/Procurement","2006-02-01","2010-04-05"]
["SSIJ_0115","Drive Laser Integration & Checkout","2006-05-25","2007-06-05"]
["SSIJ_0120","UV Beam to Cathode","2007-07-23","2007-07-20"]
["SSIJ_0125","Drive Laser Available for Laser Heater Comm","2007-10-10","2007-10-09"]
["SSIJ_0200","RF Gun Design/Procurement","2006-02-01","2006-06-26"]
["SSIJ_0205","RF Gun Installation & Checkout","2006-08-22","2006-10-19"]
["SSIJ_0210","RF Conditioning","2007-06-29","2007-08-31"]
["SSIJ_0215","RF Gun Operations with Beam","2007-09-04","2008-01-10"]
["SSIJ_0400","1st RF Power","2006-02-01","2006-01-31"]
["SSIJ_0405","DL1 Installation Complete","2006-02-01","2006-01-31"]
["SSIJ_0410","Waveguide and LTDL1 Installation","2005-10-17","2006-02-07",null,"2005-10-17"]
["SSIJ_0415","L1, L2, L0, SAB & DL1 & LH Design & Procure","2006-02-01","2006-12-14"]
["SSIJ_0420","L1, L2, L0, SAB & DL1 & LH Installation & C/O","2005-10-03","2007-11-21",null,"2005-10-03"]
["SSIJ_0425","L1, L2, L0, SAB & DL1 & LH Commissioning","2007-10-18","2008-08-20"]
["SSLN_0100","L1,BC1,L2,BC2,L3,&LTU, E-Dump Design & Procure","2006-02-01","2008-07-03"]
["SSLN_0105","L1,BC1 Installation & C/O","2006-08-01","2007-01-25"]
["SSLN_0110","L2,BC2,L3 Installation & C/O","2007-09-04","2008-02-22"]
["SSLN_0112","LTU Installation & C/O","2008-02-25","2008-04-24"]
["SSLN_0115","E-Dump Installation & C/O","2007-12-03","2008-02-26"]
["SSLN_0120","L1,BC1,L2,BC2,L3,&LTU, E-Dump Commissioning","2006-10-03","2008-06-06"]
["SSMS_0100","CD2b - Approve Performance Baseline","2006-02-01","2006-01-31"]
["SSMS_0105","CD3a - Approve Start of Long Lead Procurement","2006-02-01","2006-01-31"]
["SSMS_0110","CD3b - Approve Start of Construction","2006-03-01","2006-02-28"]
["SSMS_0115","CD4 - Approve Start of Operations","2009-04-01","2009-03-31"]
["SSMS_0205","FFTB Shutdown","2006-06-01","2006-05-31"]
["SSMS_0210","1st Beam on Linac Axis","2008-05-08","2008-05-07"]
["SSMS_0215","1st Beam on Undulator","2006-02-01","2006-01-31"]
["SSMS_0220","LCLS Start Operation (X-Ray to Far Hall)","2009-04-01","2009-03-31"]
["SSMS_0305","FY05 Shutdown","2005-10-03","2005-10-31",null,"2005-10-03","2005-10-31"]
["SSMS_0310","FY06 Shutdown","2006-08-01","2006-11-30"]
["SSMS_0315","FY07 Shutdown","2007-09-04","2007-11-30"]
["SSUN_0100","Undulator Design","2006-02-01","2010-04-05"]
["SSUN_0105","CRIT: Magnet Poles","2005-02-05","2005-02-04",null,"2005-02-05","2005-02-04"]
["SSUN_0110","CRIT: Ti Strongback","2005-01-14","2005-01-13",null,"2005-01-14","2005-01-13"]
["SSUN_0115","CRIT: Magnet Blocks","2005-03-23","2005-03-22",null,"2005-03-23","2005-03-22"]
["SSUN_0140","Undulator Procure","2005-10-04","2007-04-16",null,"2005-10-04"]
["SSUN_0145","RCV: Undulator 1st Articles","2006-02-01","2006-01-31"]
["SSUN_0150","Last Undulator Production Unit Received","2006-02-01","2006-01-31"]
["SSUN_0155","Undulator Testing","2006-02-01","2010-04-05"]
["SSUN_0160","Deliver 1st Articles to MMF","2006-02-01","2006-01-31"]
["SSUN_0165","Fiducialization & Magnetic Measurement","2006-06-01","2010-04-05"]
["SSUN_0170","Undulator Installation","2007-10-05","2010-04-05"]
["SSUN_0175","Undulator Commissioning","2006-02-01","2010-04-05"]
["SSXE_0100","Laser Design, Procurement and Assembly","2006-04-03","2008-07-29"]
["SSXE_0105","Laser Installation and Commissioning","2008-06-06","2010-04-05"]
["SSXE_0200","2-D X-Ray Detector Design and Procurement","2006-02-01","2009-01-23"]
["SSXE_0201","2-D X-Ray Detector Design and Procurement","2006-02-01","2009-01-23"]
["SSXE_0205","2-D X-Ray Detector Demo","2008-12-16","2008-12-15"]
["SSXE_0206","2-D X-Ray Detector Demo","2008-12-16","2008-12-15"]
["SSXT_0100","Comm Diagnostics Design & Procure","2006-02-01","2007-06-13"]
["SSXT_0105","Comm Diagnostics Installation","2006-02-01","2007-09-10"]
["SSXT_0110","Comm Diagnostics Commissioning","2006-02-01","2010-04-05"]
["SSXT_0115","Gas Attenuator Commissioning","2007-09-26","2007-10-24"]
["UN11_00011","Project Management - FY05 (PED)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN11_00026","Oversee Engineering and Integration - FY05 (PED)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN11_00027","Undulator Mgmt/Engr @ SLAC - FY05 (PED)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN11_00028","Undulator Designer @ SLAC - FY05 (PED)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN11_00029","Visiting Physicist","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN11_00036","Controls System Engineering Oversight (PED)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN11_00037","Undulator Mgmt/Engr @ SLAC - FY06-08 (CNST)","2005-10-03","2009-03-30",null,"2005-10-03"]
["UN11_00038","Undulator Designer @ SLAC - FY06-07 (CNST)","2005-10-03","2007-09-28",null,"2005-10-03"]
["UN11_00056","Undulator Magnet & Support Engr Oversight (PED)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN11_00076","Vacuum Engineering Oversight (PED)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN11_00096","Diagnostics Engineering Oversight (PED)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN11_00175","Oversee Quality Assurance - FY05 (PED)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN11_00200","Project Management (CNST)","2005-10-03","2008-02-08",null,"2005-10-03"]
["UN11_00220","Oversee Engineering and Integration (CNST)","2005-10-03","2008-02-08",null,"2005-10-03"]
["UN11_00230","Controls System Engineering Oversight (CNST)","2005-10-03","2008-02-08",null,"2005-10-03"]
["UN11_00240","Undulator Magnet & Support Engr Oversight (CNST)","2005-10-03","2008-02-08",null,"2005-10-03"]
["UN11_00250","Vacuum Engineering Oversight (CNST)","2005-10-03","2008-02-08",null,"2005-10-03"]
["UN11_00260","Diagnostics Engineering Oversight (CNST)","2005-10-03","2008-02-08",null,"2005-10-03"]
["UN11_00269","Monitor Budget, Schedule and Contracts (PED)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN11_00270","Monitor Budget, Schedule and Contracts (CNST)","2005-10-03","2008-02-08",null,"2005-10-03"]
["UN11_00290","Oversee Quality Assurance (CNST)","2005-10-03","2007-09-28",null,"2005-10-03"]
["UN11_00441","ANL Division - Website Support (CNST) -FY06","2005-10-03","2006-09-29",null,"2005-10-03"]
["UN11_00443","ANL Division - Website Support-FY05 (PED)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN11_00499","ANL Division - PMCS Support (PED)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN11_00500","ANL Division - PMCS Support (CNST)","2005-10-03","2008-02-08",null,"2005-10-03"]
["UN11_00520","ANL Division - Website Support (CNST)","2006-10-02","2008-09-30"]
["UN11_00549","ANL Indirect Cost Allocation - FY05 (PED)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN11_00550","ANL Indirect Cost Allocation - FY06 (CNST)","2005-10-03","2006-09-29",null,"2005-10-03"]
["UN11_00560","ANL Indirect Cost Allocation - FY07 (CNST)","2006-10-02","2007-09-28"]
["UN11_00570","ANL Indirect Cost Allocation - FY08 (CNST)","2007-10-01","2008-10-01"]
["UN12_00015","Office Supplies and Misc Materials - FY05 (PED)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN12_00025","Tele/Video Conferencing - FY05 (PED)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN12_00036","CPUs and Software - FY05 (PED) -2nd Half","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN12_00038","Undulator Controls Lab Construction","2005-05-02","2005-06-30",null,"2005-05-02","2005-06-30"]
["UN12_00040","Shipping and Storage (PED)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN12_00050","Office Supplies and Misc Materials (CNST)","2005-10-03","2008-02-08",null,"2005-10-03"]
["UN12_00060","Tele/Video Conferencing (CNST)","2005-10-03","2008-02-08",null,"2005-10-03"]
["UN12_00070","CPUs and Software (CNST)","2005-10-03","2008-02-08",null,"2005-10-03"]
["UN12_00080","Shipping and Storage (CNST)","2005-10-03","2008-02-08",null,"2005-10-03"]
["UN12_00110","Domestic Travel - FY05 (PED)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN12_00111","Domestic Travel - FY05 (PED) (Rollup)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN12_00125","Foreign Travel - FY05 (PED)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN12_00130","Domestic Travel (CNST)","2005-10-03","2008-01-31",null,"2005-10-03"]
["UN12_00140","Foreign Travel (CNST)","2005-10-03","2008-01-31",null,"2005-10-03"]
["UN21_00141","Advise on overall controls system integration","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN21_00142","Advise on overall controls system integration","2005-10-03","2009-03-31",null,"2005-10-03"]
["UN21_J27","Generate UN Hall cable, tray, rack document","2005-12-19","2006-03-15",null,"2005-12-19"]
["UN21_J28","Submit UN Hall cable, tray, rack document","2006-03-16","2006-03-15"]
["UN21_J29","Complete estimate of WPM and HLS cable runs","2005-12-19","2006-03-15",null,"2005-12-19"]
["UN21_J30","Complete estimate of MPS cable runs","2005-12-19","2006-03-15",null,"2005-12-19"]
["UN22_00015","Specify prototype motor interface","2005-12-12","2005-12-30",null,"2005-12-12","2005-12-30"]
["UN22_00020","Procure prototype motor interfaces","2006-01-03","2006-01-03",null,"2006-01-03","2006-01-03"]
["UN22_00030","Receive prototype motor interfaces","2006-02-01","2006-02-28"]
["UN22_00040","RCVD: Prototyping motor interface","2006-03-01","2006-02-28"]
["UN22_00050","Write QA procedure for Motor interface","2006-03-01","2006-03-06"]
["UN22_00060","Prepare Bid Package for Motor interface","2006-03-07","2006-03-10"]
["UN22_00070","Release RFP for Motor interface","2006-03-13","2006-03-13"]
["UN22_00080","Vendor Prepare Proposal for Motor interface","2006-03-14","2006-03-27"]
["UN22_00090","RCV: Proposal  for Motor interface","2006-03-28","2006-03-27"]
["UN22_00100","Evaluate Proposal for Motor interface","2006-03-28","2006-04-03"]
["UN22_00120","AWARD: production motor interface","2006-04-04","2006-04-04"]
["UN22_00130","Receive production motor interface","2006-04-05","2006-05-31"]
["UN22_00140","QA Test motor interface","2006-06-01","2006-06-14"]
["UN22_00155","Specify prototype encoder interface","2005-12-12","2005-12-30",null,"2005-12-12","2005-12-30"]
["UN22_00160","Procure prototype encoder interface","2006-01-03","2006-01-03",null,"2006-01-03","2006-01-03"]
["UN22_00170","Receive prototype encoder interface","2006-02-01","2006-02-28"]
["UN22_00180","RCVD:Prototyping encoder interface","2006-03-01","2006-02-28"]
["UN22_00190","Write QA procedure for Encoder interface","2006-03-01","2006-03-06"]
["UN22_00200","Prepare Bid Package for Encoder interface","2006-03-07","2006-03-10"]
["UN22_00210","Release RFP  for Encoder interface","2006-03-13","2006-03-13"]
["UN22_00220","Vendor Prepare Proposal for Encoder interface","2006-03-14","2006-03-27"]
["UN22_00230","RCVD: Proposal  for Encoder interface","2006-03-28","2006-03-27"]
["UN22_00240","Evaluate Proposal for Encoder interface","2006-03-28","2006-04-03"]
["UN22_00260","AWARD: production encoder interface","2006-04-04","2006-04-04"]
["UN22_00270","Receive production encoder interface","2006-04-05","2006-05-31"]
["UN22_00280","QA Test encoder interface","2006-06-01","2006-06-14"]
["UN22_00295","Specify prototype motor driver","2005-12-12","2005-12-16",null,"2005-12-12","2005-12-16"]
["UN22_00300","Procure prototype motor driver","2005-12-12","2005-12-12",null,"2005-12-12","2005-12-12"]
["UN22_00310","Receive prototype motor driver","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["UN22_00320","RCVD:Prototyping motor driver","2006-02-01","2006-01-31"]
["UN22_00330","Write QA procedure for motor driver","2006-02-01","2006-02-02"]
["UN22_00340","Prepare Bid Package for motor driver","2006-02-03","2006-02-08"]
["UN22_00350","Release RFP  for motor driver","2006-02-09","2006-02-09"]
["UN22_00360","Vendor Prepare Proposal for motor driver","2006-02-10","2006-02-23"]
["UN22_00370","RCVD: Proposal  for motor driver","2006-02-24","2006-02-23"]
["UN22_00380","Evaluate Proposal for motor driver","2006-02-24","2006-03-02"]
["UN22_00400","AWARD: production motor driver","2006-10-02","2006-10-02"]
["UN22_00410","Receive production motor driver","2006-10-03","2006-10-30"]
["UN22_00420","QA Motor Driver","2006-10-31","2006-11-13"]
["UN22_00430","Design motor drive cables","2006-03-07","2006-03-13"]
["UN22_00440","Design encoder signal cables","2006-03-07","2006-03-13"]
["UN22_00450","Specify cables","2006-03-14","2006-03-17"]
["UN22_00460","Specify connectors","2006-03-14","2006-03-15"]
["UN22_00470","Procure prototype parts","2006-03-20","2006-03-20"]
["UN22_00480","Receive prototype parts","2006-03-21","2006-04-24"]
["UN22_00490","Assemble prototype cables","2006-04-25","2006-05-01"]
["UN22_00500","Test prototype cables","2006-05-02","2006-05-08"]
["UN22_00510","CMPLT: Prototype cables","2006-05-09","2006-05-08"]
["UN22_00520","Specify production cables","2006-05-09","2006-05-22"]
["UN22_00530","Write QA procedure for production cables","2006-05-23","2006-05-24"]
["UN22_00540","Prepare Bid Package for production cables","2006-05-25","2006-06-01"]
["UN22_00550","Release RFP  for production cables","2006-06-02","2006-06-02"]
["UN22_00560","Vendor Prepare Proposal for production cables","2006-06-05","2006-06-16"]
["UN22_00570","RCVD: Proposal  for production cables","2006-06-19","2006-06-16"]
["UN22_00580","Evaluate Proposal for production cables","2006-06-19","2006-06-23"]
["UN22_00600","AWARD: production cables","2006-06-26","2006-06-26"]
["UN22_00610","Receive production cables","2006-06-27","2006-08-08"]
["UN22_00620","QA Test production cables","2006-08-09","2006-08-22"]
["UN22_00630","Write control Software Requirements Spec.","2006-01-03","2006-02-28",null,"2006-01-03"]
["UN22_00640","Design control software","2006-03-01","2006-03-28"]
["UN22_00650","Write testing Software Requirements Spec.","2006-03-29","2006-04-25"]
["UN22_00680","Procure commercial software","2006-04-26","2006-04-26"]
["UN22_00700","Write control software","2006-04-27","2006-05-24"]
["UN22_00710","Test control software","2006-05-25","2006-06-08"]
["UN22_00720","CMPLT: Control Software","2006-06-09","2006-06-08"]
["UN22_00760","Design prototype test setup","2006-06-09","2006-06-22"]
["UN22_00770","Prepare for design review","2006-06-23","2006-06-29"]
["UN22_00780","Conduct design review","2006-06-30","2006-07-14"]
["UN22_00790","CMPLT: Design review","2006-07-17","2006-07-14"]
["UN22_00800","Procure integration components for prototype","2006-07-17","2006-07-18"]
["UN22_00810","Receive integration components for prototype","2006-07-19","2006-08-29"]
["UN22_00820","Assemble prototype","2006-08-30","2006-09-13"]
["UN22_00830","CMPLT: Integrated prototype","2006-09-14","2006-09-13"]
["UN22_00840","Write integrated test procedure","2006-09-14","2006-09-20"]
["UN22_00850","Assemble test setup","2006-09-21","2006-09-27"]
["UN22_00860","Perform prototype testing","2006-09-28","2006-10-04"]
["UN22_00870","CMPLT: Integrated prototype testing","2006-10-05","2006-10-04"]
["UN22_00880","Write validation procedure","2006-10-05","2006-10-11"]
["UN22_00890","Design installation layout and plan","2006-10-12","2006-11-08"]
["UN22_00900","Procure production integration components","2006-11-09","2006-11-10"]
["UN22_00910","Receive production integration components","2006-11-13","2007-01-03"]
["UN22_00920","QA Test production integration components","2007-01-04","2007-01-17"]
["UN22_00922","RFI: Production integration components","2007-01-18","2007-01-17"]
["UN22_02865","Procure prototype motor interfaces","2006-02-06","2006-02-06"]
["UN22_02870","Receive prototype motor interfaces","2006-02-07","2006-03-06"]
["UN22_02875","RCVD: Prototyping motor interface","2006-03-07","2006-03-06"]
["UN22_02930","Procure prototype encoder interface","2006-02-06","2006-02-06"]
["UN22_02935","Receive prototype encoder interface","2006-02-07","2006-03-06"]
["UN22_02940","RCVD:Prototyping encoder interface","2006-03-07","2006-03-06"]
["UN22_02995","Procure prototype motor driver","2006-02-06","2006-02-06"]
["UN22_03000","Receive prototype motor driver","2006-02-07","2006-03-06"]
["UN22_03005","RCVD:Prototyping motor driver","2006-03-07","2006-03-06"]
["UN22_03055","Design motor drive cables","2006-03-07","2006-03-13"]
["UN22_03060","Design encoder signal cables","2006-03-07","2006-03-13"]
["UN22_03065","Specify connectors","2006-03-14","2006-03-15"]
["UN22_03070","Specify cables","2006-03-14","2006-03-17"]
["UN22_03075","Procure prototype parts","2006-03-20","2006-03-20"]
["UN22_03080","Receive prototype parts","2006-03-21","2006-04-24"]
["UN22_03085","Assemble prototype cables","2006-04-25","2006-05-01"]
["UN22_03090","Test prototype cables","2006-05-02","2006-05-08"]
["UN22_03095","CMPLT: Prototype cables","2006-05-09","2006-05-08"]
["UN22_03435","Write control software","2006-02-01","2006-03-28"]
["UN22_03590","Perform prototype testing","2006-03-29","2006-04-11"]
["UN22_03600","CMPLT: Integrated prototype testing","2006-04-12","2006-04-11"]
["UN22_03690","Specify prototype motor interface","2005-10-03","2005-10-17",null,"2005-10-03","2005-10-17"]
["UN22_03700","Procure prototype motor interfaces","2005-08-29","2005-12-30",null,"2005-08-29","2005-12-30"]
["UN22_03710","Receive prototype motor interfaces","2005-10-03","2005-10-05",null,"2005-10-03","2005-10-05"]
["UN22_03720","RCV:Prototyping motor interface","2005-10-06","2005-10-05",null,"2005-10-06","2005-10-05"]
["UN22_03730","Write QA procedure for Motor interface","2006-03-06","2006-03-09"]
["UN22_03740","Prepare Bid Package for motor interface","2006-03-10","2006-03-15"]
["UN22_03750","Release RFP  for motor interface","2006-03-16","2006-03-16"]
["UN22_03760","Vendor Prepare Proposal for motor interface","2006-03-17","2006-03-30"]
["UN22_03770","RCV: Proposal  for motor interface","2006-03-31","2006-03-30"]
["UN22_03780","Evaluate Proposal for motor interface","2006-03-31","2006-04-06"]
["UN22_03800","AWARD: production motor interface","2006-04-07","2006-04-07"]
["UN22_03810","Receive production motor interface","2006-04-10","2006-05-05"]
["UN22_03820","QA Test motor interface","2006-05-08","2006-05-19"]
["UN22_03970","Specify prototype motor driver","2005-10-03","2005-10-10",null,"2005-10-03","2005-10-10"]
["UN22_03980","Procure prototype motor driver","2005-10-17","2005-12-30",null,"2005-10-17","2005-12-30"]
["UN22_03990","Receive prototype motor driver","2005-11-15","2005-12-30",null,"2005-11-15","2005-12-30"]
["UN22_04000","RCV:Prototyping driver","2005-12-31","2005-12-30",null,"2005-12-31","2005-12-30"]
["UN22_04010","Write QA Procedure for Motor Driver","2006-02-01","2006-02-06"]
["UN22_04020","Prepare Bid Pkg for Driver Interface","2006-02-07","2006-02-10"]
["UN22_04080","Release RFP for production motor driver","2006-02-13","2006-02-24"]
["UN22_04081","Vendor Prepare Proposal for Driver interface","2006-02-27","2006-03-10"]
["UN22_04082","RCV: Proposal  for Driver interface","2006-03-13","2006-03-10"]
["UN22_04083","Evaluate Proposal for Driver Interface","2006-03-13","2006-03-17"]
["UN22_04084","AWARD: production driver interface","2006-03-20","2006-03-20"]
["UN22_04090","Receive production motor driver","2006-03-21","2006-04-17"]
["UN22_04100","QA Motor Driver","2006-04-18","2006-05-01"]
["UN22_04110","Design motor drive cables","2006-02-01","2006-02-07"]
["UN22_04130","Specify cables","2006-02-08","2006-02-13"]
["UN22_04140","Specify connectors","2006-02-08","2006-02-10"]
["UN22_04150","Procure prototype parts","2006-02-14","2006-03-21"]
["UN22_04160","Receive prototype parts","2006-03-22","2006-03-24"]
["UN22_04170","Assemble prototype cables","2006-03-27","2006-04-03"]
["UN22_04180","Test prototype cables","2006-04-04","2006-04-11"]
["UN22_04190","CMPLT: Prototype cables","2006-04-12","2006-04-11"]
["UN22_04200","Specify production cables","2006-04-12","2006-04-25"]
["UN22_04210","Write QA procedure for production cables","2006-04-26","2006-04-28"]
["UN22_04220","Prepare Bid Package for production cables","2006-05-01","2006-05-05"]
["UN22_04230","Release RFP  for production cables","2006-05-08","2006-05-08"]
["UN22_04240","Vendor Prepare Proposal for production cables","2006-05-09","2006-05-22"]
["UN22_04250","RCV: Proposal  for production cables","2006-05-23","2006-05-22"]
["UN22_04260","Evaluate Proposal for production cables","2006-05-23","2006-05-30"]
["UN22_04280","AWARD: production cables","2006-05-31","2006-05-31"]
["UN22_04290","Receive production cables","2006-06-01","2006-07-13"]
["UN22_04300","QA Test production cables","2006-07-14","2006-07-27"]
["UN22_04310","Write control Software Requirements Spec.","2005-12-01","2006-02-28",null,"2005-12-01"]
["UN22_04320","Design control software","2005-11-15","2006-02-28",null,"2005-11-15"]
["UN22_04380","Write control software","2005-12-16","2006-02-28",null,"2005-12-16"]
["UN22_04400","CMPLT: Control Software","2006-03-01","2006-02-28"]
["UN22_04440","Design prototype test setup","2006-03-01","2006-03-14"]
["UN22_04450","Prepare for design review - hardware","2006-03-15","2006-03-21"]
["UN22_04460","Prepare for design review - software","2006-03-22","2006-04-05"]
["UN22_04470","Conduct design review","2006-04-06","2006-04-05"]
["UN22_04480","Procure integration components for prototype","2006-04-06","2006-05-11"]
["UN22_04490","Receive integration components for prototype","2006-05-12","2006-05-17"]
["UN22_04500","Assemble prototype","2006-05-18","2006-06-01"]
["UN22_04510","CMPLT: Integrated prototype","2006-06-02","2006-06-01"]
["UN22_04520","Write integrated test procedure","2006-06-02","2006-06-08"]
["UN22_04530","Assemble test setup","2006-06-09","2006-06-15"]
["UN22_04540","Perform prototype testing","2006-06-16","2006-06-22"]
["UN22_04550","CMPLT: Integrated prototype testing","2006-06-23","2006-06-22"]
["UN22_04560","Write validation procedure","2006-06-23","2006-06-29"]
["UN22_04570","Design installation layout and plan","2006-06-30","2006-07-28"]
["UN22_04580","Procure production integration components","2006-07-31","2006-08-01"]
["UN22_04590","Receive production integration components","2006-08-02","2006-09-13"]
["UN22_04600","QA Test production integration components","2006-09-14","2006-09-27"]
["UN22_J00","Conduct Servo Motor Tests","2005-10-03","2005-12-30",null,"2005-10-03","2005-12-30"]
["UN22_J35","Procure host for motion test stand","2005-05-02","2005-05-31",null,"2005-05-02","2005-05-31"]
["UN22_J36","Assemble components","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN22_J37","Test stand checkout","2005-10-03","2005-10-07",null,"2005-10-03","2005-10-07"]
["UN22_J38","Motion test stand complete","2005-12-01","2005-11-30",null,"2005-12-01","2005-11-30"]
["UN22_J46","Assemble components","2005-05-02","2005-05-06",null,"2005-05-02","2005-05-06"]
["UN22_J47","Imaging stand checkout","2005-06-30","2005-07-29",null,"2005-06-30","2005-07-29"]
["UN22_J48","Imaging test stand complete","2005-07-30","2005-07-29",null,"2005-07-30","2005-07-29"]
["UN23_00115","REQD:  LINAC RFBPM Design","2006-02-01","2006-01-31"]
["UN23_00120","Specify prototype A/D interface","2006-01-16","2006-02-28",null,"2006-01-16"]
["UN23_00130","Procure prototype A/D interfaces","2006-03-01","2006-03-01"]
["UN23_00140","Receive prototype A/D interfaces","2006-03-02","2006-03-29"]
["UN23_00150","Assemble prototype","2006-03-30","2006-04-12"]
["UN23_00160","Prototype testing","2006-04-13","2006-04-26"]
["UN23_00170","CMPLT: Prototyping A/D interface","2006-04-27","2006-04-26"]
["UN23_00180","Write QA procedure for A/D interface","2006-04-27","2006-05-02"]
["UN23_00190","Prepare Bid Package for A/D interface","2006-07-26","2006-07-31"]
["UN23_00200","Release RFP  for A/D interface","2006-08-01","2006-08-01"]
["UN23_00210","Vendor Prepare Proposal for A/D interface","2006-08-02","2006-08-15"]
["UN23_00220","RCV: Proposal  for A/D interface","2006-08-16","2006-08-15"]
["UN23_00230","Evaluate Proposal for A/D interface","2006-08-16","2006-08-22"]
["UN23_00250","AWARD: production A/D interface","2006-10-02","2006-10-27"]
["UN23_00260","Receive production A/D interface","2006-10-30","2006-10-31"]
["UN23_00270","QA Test A/D interface","2006-11-01","2006-11-14"]
["UN23_00475","REQD:  LINAC RFBPM Design","2006-02-01","2006-01-31"]
["UN23_00480","Specify cables","2006-04-05","2006-04-11"]
["UN23_00500","Procure prototype parts","2006-04-12","2006-04-12"]
["UN23_00510","Receive prototype parts","2006-04-13","2006-05-10"]
["UN23_00520","Assemble prototype cables","2006-05-11","2006-05-24"]
["UN23_00530","Test prototype cables","2006-05-25","2006-06-08"]
["UN23_00540","CMPLT: Prototype cables","2006-06-09","2006-06-08"]
["UN23_00550","Specify production cables","2006-06-09","2006-06-22"]
["UN23_00560","Write QA procedure for production cables","2006-06-23","2006-06-29"]
["UN23_00570","Prepare Bid Package for production cables","2006-06-30","2006-07-06"]
["UN23_00580","Release RFP  for production cables","2006-07-07","2006-07-07"]
["UN23_00590","Vendor Prepare Proposal for production cables","2006-07-10","2006-07-21"]
["UN23_00600","RCV: Proposal  for production cables","2006-07-24","2006-07-21"]
["UN23_00610","Evaluate Proposal for production cables","2006-07-24","2006-07-28"]
["UN23_00650","Preliminary Cable Design","2005-10-03","2005-10-14",null,"2005-10-03","2005-10-14"]
["UN23_00655","REQD:  LINAC RFBPM Design","2006-02-01","2006-01-31"]
["UN23_00660","Write control Software Requirements Spec.","2006-02-14","2006-03-13"]
["UN23_00670","Design control software","2006-03-14","2006-04-10"]
["UN23_00680","Write testing Software Requirements Spec.","2006-04-11","2006-05-08"]
["UN23_00690","Design testing software","2006-05-09","2006-05-22"]
["UN23_00700","Specify commercial software required","2006-05-23","2006-05-30"]
["UN23_00710","Procure commercial software","2006-05-31","2006-05-31"]
["UN23_00720","Receive commercial software","2006-06-01","2006-06-28"]
["UN23_00730","Write control software","2006-06-29","2006-08-10"]
["UN23_00740","Test control software","2006-08-11","2006-08-24"]
["UN23_00750","CMPLT: Control Software","2006-08-25","2006-08-24"]
["UN23_00790","Design prototype test setup","2006-08-25","2006-08-31"]
["UN23_00800","Prepare for design review","2006-09-01","2006-09-08"]
["UN23_00820","Conduct design review","2006-09-11","2006-09-12"]
["UN23_00830","Procure integration components for prototype (","2006-09-13","2006-09-13"]
["UN23_00840","Receive integration components for prototype","2006-09-14","2006-10-11"]
["UN23_00850","Assemble prototype","2006-10-12","2006-11-08"]
["UN23_00860","CMPLT: Integrated prototype","2006-11-09","2006-11-08"]
["UN23_00870","Write integrated test procedure","2006-11-09","2006-11-10"]
["UN23_00880","Assemble test setup","2006-11-13","2006-11-14"]
["UN23_00890","Perform prototype testing","2006-11-15","2006-11-16"]
["UN23_00900","CMPLT: Integrated prototype testing","2006-11-17","2006-11-16"]
["UN23_00910","Write validation procedure","2006-11-17","2006-11-27"]
["UN23_00920","Design installation layout and plan","2006-11-28","2007-01-02"]
["UN23_00921","Prepare Bid Pkg for production integration com","2007-01-03","2007-01-08"]
["UN23_00922","Release RFP  for production integration comp","2007-01-09","2007-01-09"]
["UN23_00923","Vendor Prepare Prop for production integrat co","2007-01-10","2007-01-23"]
["UN23_00924","RCV: Proposal  for production integration comp","2007-01-24","2007-01-23"]
["UN23_00925","Evaluate Prop for production integration comp","2007-01-24","2007-01-30"]
["UN23_00930","AWARD: production integration components","2007-01-31","2007-01-31"]
["UN23_00940","Receive production integration components","2007-02-01","2007-02-28"]
["UN23_00950","QA Test production integration components","2007-03-01","2007-03-14"]
["UN23_01285","REQD:  LINAC Toroid Design","2006-02-01","2006-01-31"]
["UN23_01290","Write control Software Requirements Spec.","2006-02-01","2006-02-28"]
["UN23_01300","Design control software","2006-03-01","2006-03-28"]
["UN23_01360","Write control software","2006-11-06","2006-12-19"]
["UN23_01370","Test control software","2006-12-20","2007-01-10"]
["UN23_01380","CMPLT: Control Software","2007-01-11","2007-01-10"]
["UN23_01420","Design prototype test setup","2007-01-11","2007-01-17"]
["UN23_01430","Prepare for design review","2007-01-18","2007-01-31"]
["UN23_01450","Conduct design review","2007-02-01","2007-02-02"]
["UN23_01460","Procure integration components for prototype","2007-02-05","2007-02-05"]
["UN23_01470","Receive integration components for prototype","2007-02-06","2007-03-05"]
["UN23_01480","Assemble prototype","2007-03-06","2007-04-02"]
["UN23_01490","CMPLT: Integrated prototype","2007-04-03","2007-04-02"]
["UN23_01500","Write integrated test procedure","2007-04-03","2007-04-04"]
["UN23_01510","Assemble test setup","2007-04-05","2007-04-06"]
["UN23_01520","Perform prototype testing","2007-04-09","2007-04-10"]
["UN23_01530","CMPLT: Integrated prototype testing","2007-04-11","2007-04-10"]
["UN23_01540","Write validation procedure","2007-04-11","2007-04-17"]
["UN23_01550","Design installation layout and plan","2007-04-18","2007-05-15"]
["UN23_01551","Prepare Bid Package for product integration co","2007-05-16","2007-05-21"]
["UN23_01552","Release RFP  for production integration comp","2007-05-22","2007-05-22"]
["UN23_01553","Vendor Prepare Prop for product integration co","2007-05-23","2007-06-06"]
["UN23_01554","RCV: Proposal  for production integration comp","2007-06-07","2007-06-06"]
["UN23_01555","Evaluate Proposal for product integration comp","2007-06-07","2007-06-13"]
["UN23_01560","AWARD: production integration components","2007-06-14","2007-06-14"]
["UN23_01570","Receive production integration components","2007-06-15","2007-07-13"]
["UN23_01580","QA Test production integration components","2007-07-16","2007-07-27"]
["UN23_02375","REQD:  ULD-SWA Design","2006-02-01","2006-01-31"]
["UN23_02380","Design control software","2006-02-01","2006-02-28"]
["UN23_02440","Write control software","2006-03-01","2006-04-11"]
["UN23_02450","Test control software","2006-04-12","2006-04-25"]
["UN23_02460","CMPLT: Control Software","2006-04-26","2006-04-25"]
["UN23_02500","Design prototype test setup","2006-04-26","2006-05-03"]
["UN23_02510","Prepare for design review","2006-05-04","2006-05-10"]
["UN23_02530","Conduct design review","2006-05-11","2006-05-12"]
["UN23_02540","Procure integration components for prototype (","2006-05-15","2006-05-15"]
["UN23_02550","Receive integration components for prototype","2006-05-16","2006-06-13"]
["UN23_02560","Assemble prototype","2006-06-14","2006-07-12"]
["UN23_02570","CMPLT: Integrated prototype","2006-07-13","2006-07-12"]
["UN23_02580","Write integrated test procedure","2006-07-13","2006-07-17"]
["UN23_02590","Assemble test setup","2006-07-18","2006-07-20"]
["UN23_02600","Perform prototype testing","2006-07-21","2006-07-25"]
["UN23_02610","CMPLT: Integrated prototype testing","2006-07-26","2006-07-25"]
["UN23_23300","Design actuator control","2006-03-01","2006-03-14"]
["UN23_23305","Procure prototype actuator hardware","2006-03-15","2006-04-11"]
["UN23_23310","Build actuator control chassis","2006-04-12","2006-04-25"]
["UN23_23315","Test and debug actuator control","2006-04-26","2006-05-09"]
["UN23_23320","BFW Actuator Complete","2006-05-10","2006-05-09"]
["UN24_00050","Prototype testing","2005-08-01","2005-08-12",null,"2005-08-01","2005-08-12"]
["UN24_00060","CMPLT: Prototyping Camera","2005-08-13","2005-08-12",null,"2005-08-13","2005-08-12"]
["UN24_00070","Write QA procedure for Camera","2005-08-15","2005-09-30",null,"2005-08-15","2005-09-30"]
["UN24_00210","Prototype testing Camera Interface","2005-10-03","2005-10-14",null,"2005-10-03","2005-10-14"]
["UN24_00220","CMPLT: Prototyping Camera interface","2005-10-15","2005-10-14",null,"2005-10-15","2005-10-14"]
["UN24_00230","Write QA procedure for Camera interface","2006-08-28","2006-09-01"]
["UN24_00370","Prototype testing","2005-08-01","2005-09-30",null,"2005-08-01","2005-09-30"]
["UN24_00380","CMPLT: Prototyping Digitizer","2005-08-13","2005-08-12",null,"2005-08-13","2005-08-12"]
["UN24_00390","Write QA procedure for Digitizer","2005-08-15","2005-09-30",null,"2005-08-15","2005-09-30"]
["UN24_00660","Design video feed cables","2005-09-15","2005-09-15",null,"2005-09-15","2005-09-15"]
["UN24_00670","Design timing signal cables","2006-02-01","2006-02-07"]
["UN24_00680","Specify cables","2006-02-08","2006-02-14"]
["UN24_00700","Procure prototype parts","2006-02-15","2006-02-15"]
["UN24_00710","Receive prototype parts","2006-02-16","2006-03-15"]
["UN24_00720","Assemble prototype cables","2006-03-16","2006-03-22"]
["UN24_00730","Test prototype cables","2006-03-23","2006-04-05"]
["UN24_00740","CMPLT: Prototype cables","2006-04-06","2006-04-05"]
["UN24_00860","Write control Software Requirements Spec.","2006-01-31","2006-01-31",null,"2006-01-31","2006-01-31"]
["UN24_00870","Design control software","2006-02-01","2006-02-28"]
["UN24_00930","Write control software","2006-03-01","2006-04-11"]
["UN24_00940","Test control software","2006-04-12","2006-04-25"]
["UN24_00950","CMPLT: Control Software","2006-04-26","2006-04-25"]
["UN24_00960","RCV: OTR imaging requirements","2006-04-26","2006-04-25"]
["UN24_00970","Design analysis software","2006-04-26","2006-05-23"]
["UN24_00980","Test Analysis software","2006-05-24","2006-06-07"]
["UN24_00985","CMPLT : OTR Analysis software","2006-06-08","2006-06-07"]
["UN24_00990","Design prototype test setup","2006-06-08","2006-06-14"]
["UN24_01000","Prepare for design review","2006-06-15","2006-06-21"]
["UN24_01020","Conduct design review","2006-06-22","2006-06-28"]
["UN24_01030","Procure integration components for prototype (","2006-06-29","2006-06-29"]
["UN24_01040","Receive integration components for prototype","2006-06-30","2006-07-28"]
["UN24_01050","Assemble prototype","2006-07-31","2006-08-11"]
["UN24_01060","CMPLT: Integrated prototype","2006-08-14","2006-08-11"]
["UN24_01070","Write integrated test procedure","2006-08-14","2006-08-17"]
["UN24_01080","Assemble test setup","2006-08-18","2006-08-24"]
["UN24_01090","Perform prototype testing","2006-08-25","2006-08-31"]
["UN24_01100","CMPLT: Integrated prototype testing","2006-09-01","2006-08-31"]
["UN25_00010","Write control Software Requirements Spec","2006-02-01","2006-02-14"]
["UN25_00020","Design control software","2006-02-15","2006-02-14"]
["UN25_00080","Write control software","2006-02-15","2006-02-28"]
["UN25_00090","Test control software","2006-03-01","2006-03-07"]
["UN25_00100","CMPLT: Control Software","2006-03-08","2006-03-07"]
["UN25_00140","Design prototype test setup","2006-03-08","2006-03-14"]
["UN25_00150","Prepare for design review","2006-03-15","2006-03-21"]
["UN25_00160","Conduct design review","2006-03-22","2006-03-23"]
["UN25_00161","CMPLT: Design Review","2006-03-24","2006-03-23"]
["UN25_00170","Procure integration components for prototype (","2006-03-24","2006-03-24"]
["UN25_00180","Receive integration components for prototype","2006-03-27","2006-04-21"]
["UN25_00190","Assemble prototype","2006-04-24","2006-05-05"]
["UN25_00200","CMPLT: Integrated prototype","2006-05-08","2006-05-05"]
["UN25_00210","Write integrated test procedure","2006-05-08","2006-05-09"]
["UN25_00220","Assemble test setup","2006-05-10","2006-05-11"]
["UN25_00230","Perform prototype testing","2006-05-12","2006-05-15"]
["UN25_00240","CMPLT: Integrated prototype testing","2006-05-16","2006-05-15"]
["UN25_00250","Write validation procedure","2006-05-16","2006-05-22"]
["UN25_00260","Design installation layout and plan","2006-05-23","2006-06-20"]
["UN25_00261","Prepare Bid Package for product integrated com","2006-06-21","2006-06-27"]
["UN25_00262","Release RFP  for production integrated comp","2006-06-28","2006-06-28"]
["UN25_00263","Vendor Prepare Prop for product integrated com","2006-06-29","2006-07-06"]
["UN25_00264","RCV: Proposal  for product integrated comp","2006-07-07","2006-07-06"]
["UN25_00265","Evaluate Proposal for product integrated comp","2006-07-07","2006-07-13"]
["UN25_00270","AWARD production integration components","2006-07-14","2006-07-14"]
["UN25_00280","Receive production integration components","2006-07-17","2006-08-11"]
["UN25_00290","QA Test production integration components","2007-05-04","2007-05-17"]
["UN26_00010","Write control Software Requirements Spec.","2006-10-13","2006-10-26"]
["UN26_00020","Design control software","2006-10-27","2006-11-09"]
["UN26_00080","Write control software","2006-11-10","2006-11-27"]
["UN26_00090","Test control software","2006-11-28","2006-12-04"]
["UN26_00100","CMPLT:  Control Software","2006-12-05","2006-12-04"]
["UN26_00140","Design prototype test setup","2006-12-05","2006-12-11"]
["UN26_00160","Prepare for design review","2006-12-12","2006-12-18"]
["UN26_00170","Conduct design review","2006-12-19","2006-12-20"]
["UN26_00171","CMPLT: Design Review","2006-12-21","2006-12-20"]
["UN26_00180","Procure integration components for prototype (","2006-12-21","2006-12-21"]
["UN26_00190","Receive integration components for prototype","2006-12-29","2007-02-09"]
["UN26_00200","Assemble prototype","2007-02-12","2007-02-23"]
["UN26_00210","CMPLT: Integrated prototype","2007-02-26","2007-02-23"]
["UN26_00220","Write integrated test procedure","2007-02-26","2007-02-27"]
["UN26_00230","Assemble test setup","2007-02-28","2007-03-01"]
["UN26_00240","Perform prototype testing","2007-03-02","2007-03-05"]
["UN26_00250","CMPLT: Integrated prototype testing","2007-03-06","2007-03-05"]
["UN26_00260","Write validation procedure","2007-03-06","2007-03-12"]
["UN26_00270","Design installation layout and plan","2007-03-13","2007-04-09"]
["UN26_00271","Prepare Bid Package for product integration co","2007-04-10","2007-04-16"]
["UN26_00272","Release RFP  for production integration comp","2007-04-17","2007-04-17"]
["UN26_00273","Vendor Prepare Prop for product integration co","2007-04-18","2007-04-24"]
["UN26_00274","RCV: Proposal  for product integration comp","2007-04-25","2007-04-24"]
["UN26_00275","Evaluate Proposal for product integration comp","2007-04-25","2007-05-01"]
["UN26_00280","AWARD:  production integration components","2007-05-02","2007-05-02"]
["UN26_00290","Receive production integration components","2007-05-03","2007-05-31"]
["UN26_00300","QA Test production integration components","2007-06-01","2007-06-14"]
["UN26_01000","Write control Software Requirements Spec.","2006-10-04","2006-10-17"]
["UN26_01010","Design control software","2006-10-18","2006-10-31"]
["UN26_01070","Write control software","2006-11-01","2006-11-14"]
["UN26_01080","Test control software","2006-11-15","2006-11-21"]
["UN26_01090","CMPLT: Control Software","2006-11-22","2006-11-21"]
["UN26_01150","Prepare for design review","2006-11-22","2006-11-30"]
["UN26_01160","Conduct design review","2006-12-01","2006-12-04"]
["UN26_01280","Receive production integration components","2006-12-05","2007-01-02"]
["UN26_01290","QA Test production integration components","2007-01-03","2007-01-16"]
["UN27_00010","Undulator global MPS module design","2006-10-02","2006-10-27"]
["UN27_00011","Prepare for design review","2006-10-30","2006-11-03"]
["UN27_00020","conduct design review","2006-11-06","2006-11-07"]
["UN27_00030","Procure prototype MPS hardware components","2006-11-08","2006-11-08"]
["UN27_00031","Receive Prototype MPS Hardware Components","2006-11-09","2006-12-15"]
["UN27_00040","Assemble prototype MPS hardware","2006-12-18","2007-01-08"]
["UN27_00050","Test prototype MPS hardware","2007-01-09","2007-01-12"]
["UN27_00060","CMPLT: MPS hardware","2007-01-15","2007-01-12"]
["UN27_00070","Specify production MPS hardware","2007-01-15","2007-01-19"]
["UN27_00080","Write QA procedure for production MPS hardware","2007-01-22","2007-01-26"]
["UN27_00090","Procure production MPS hardware","2007-01-29","2007-01-29"]
["UN27_00092","Procure Spare MPS Hardware","2007-01-29","2007-01-29"]
["UN27_00100","Receive production and spare MPS hardware","2007-01-30","2007-02-14"]
["UN27_00110","QA Test production MPS hardware","2007-02-15","2007-02-28"]
["UN27_00120","Design interface electronics","2006-10-30","2006-11-10"]
["UN27_00121","Prepare for design review","2006-11-13","2006-11-17"]
["UN27_00130","conduct design review","2006-11-20","2006-11-21"]
["UN27_00140","Procure prototype Interface electronics compon","2006-11-22","2006-11-22"]
["UN27_00141","Receive Prototype Interface Electronics","2006-11-27","2007-01-08"]
["UN27_00150","Assemble prototype Interface electronics","2007-01-09","2007-01-22"]
["UN27_00160","Test prototype Interface electronics","2007-01-23","2007-01-26"]
["UN27_00170","CMPTL: Interface electronics","2007-01-29","2007-01-26"]
["UN27_00180","Specify production Interface electronics","2007-01-29","2007-02-02"]
["UN27_00190","Write QA procedure for production Interface el","2007-02-05","2007-02-05"]
["UN27_00200","Procure production Interface electronics","2007-02-06","2007-02-06"]
["UN27_00210","Receive production Interface electronics","2007-02-07","2007-02-20"]
["UN27_00220","QA Test production Interface electronics","2007-02-21","2007-03-06"]
["UN27_00230","Design signal interface","2006-10-02","2006-10-13"]
["UN27_00231","Prepare for design review","2006-10-16","2006-10-20"]
["UN27_00240","conduct design review","2006-10-23","2006-10-24"]
["UN27_00250","Procure prototype signal electronics component","2006-10-25","2006-10-25"]
["UN27_00251","Receive Prototype Signal Electronics","2006-10-26","2006-12-01"]
["UN27_00260","Assemble prototype signal electronics","2006-12-04","2006-12-05"]
["UN27_00270","Test prototype signal electronics","2006-12-06","2006-12-11"]
["UN27_00280","CMPTL: signal electronics","2006-12-12","2006-12-11"]
["UN27_00290","Specify production signal electronics","2006-12-12","2006-12-13"]
["UN27_00300","Write QA procedure for production signal elect","2006-12-14","2006-12-15"]
["UN27_00310","AWARD: production signal electronics","2006-12-18","2006-12-18"]
["UN27_00312","AWARD:  spare signal electronics","2007-01-02","2007-01-02"]
["UN27_00320","Receive production and spare signal electronic","2006-12-19","2007-01-09"]
["UN27_00321","REC: production signal electronics","2007-01-10","2007-01-10"]
["UN27_00324","REC: spare signal electronics","2007-01-10","2007-01-10"]
["UN27_00330","QA Test production and spare signal electronic","2007-01-11","2007-01-24"]
["UN27_00340","Design signal interface","2007-02-22","2007-03-07"]
["UN27_00341","Prepare for design review","2007-03-08","2007-03-14"]
["UN27_00350","conduct design review","2007-03-15","2007-03-16"]
["UN27_00360","Procure prototype signal electronics component","2007-03-19","2007-03-19"]
["UN27_00361","Receive Prototype Signal Electronics Component","2007-03-20","2007-04-23"]
["UN27_00370","Assemble prototype signal electronics","2007-04-24","2007-04-25"]
["UN27_00380","Test prototype signal electronics","2007-04-26","2007-05-01"]
["UN27_00390","CMPLT: signal electronics","2007-05-02","2007-05-01"]
["UN27_00400","Specify production signal electronics","2007-05-02","2007-05-03"]
["UN27_00410","Write QA procedure for production signal elect","2007-05-04","2007-05-07"]
["UN27_00420","Procure production signal electronics","2007-05-08","2007-05-08"]
["UN27_00430","Receive production signal electronics","2007-05-09","2007-05-22"]
["UN27_00440","QA Test production signal electronics","2007-05-23","2007-06-06"]
["UN27_00450","Design Power Supply Control","2006-04-28","2006-08-17"]
["UN27_00460","COMP: Power Supply Controls Design","2006-08-18","2006-08-17"]
["UN27_00470","Build H/W and Write Docmtn Power Supply Control","2006-08-18","2006-09-25"]
["UN27_00480","Write S/W Docmtn Power Supply Control","2006-08-18","2006-09-25"]
["UN27_00490","Integrate software & hardware","2006-09-26","2006-10-02"]
["UN27_00500","AVAIL: Power Supply Cntrls Ready for Install","2006-10-03","2006-10-02"]
["UN27_00532","Procure spare signal electronics","2007-01-03","2007-01-03"]
["UN30_28440","All Undulator Magnets Ready for Installation","2008-03-10","2008-03-07"]
["UN31_00010","Undulator Systems Integration","2005-10-03","2007-07-20",null,"2005-10-03"]
["UN31_00040","Dev/Coord Instl/Checkout/Verif/Interface,etc","2006-06-02","2007-05-17"]
["UN33_00310","Prototype Supt/Mover System w/Final Rqmts","2006-01-23","2006-03-21",null,"2006-01-23"]
["UN33_00324","Single Undulator Module Tested-Short Term","2006-05-26","2006-05-25"]
["UN33_00530","Mag Measure & Tune-Hi-Tech Article 01 (1st Art)","2006-04-11","2006-05-09"]
["UN33_00540","COMP:  Magnetic Meas. & Tune Hi-Tech Article 01","2006-05-10","2006-05-09"]
["UN33_00545","Carry Out Longer Term Stability Single Und Test","2006-05-26","2006-07-26"]
["UN33_00548","Disassemble and Pack","2006-07-27","2006-08-02"]
["UN33_00549","Design/fab undulator magnetic shield","2005-10-03","2005-10-21",null,"2005-10-03","2005-10-21"]
["UN33_00550","ACCEPT Hi-Tech Und Article 01 (1st Art) at ANL","2006-05-10","2006-05-16"]
["UN33_00551","Test/measure undulator magnetic shield","2005-10-24","2005-10-28",null,"2005-10-24","2005-10-28"]
["UN33_00552","Ship Hi-Tech Und Article 01 (1st Art) to SLAC","2006-05-24","2006-05-31"]
["UN33_00553","Disassemble/pack Undulator Hi-Tech Article 01","2006-05-17","2006-05-23"]
["UN33_00554","ACCEPT: Hi-Tech Und Article 01 (1st Art) at SLAC","2006-06-01","2006-05-31"]
["UN33_00556","Hi-Tech Undulator Article 01 Ready for MMF","2006-06-01","2006-05-31"]
["UN33_00560","Mag Measure & Tune-Metalex Article 02 (1st Art)","2006-05-10","2006-06-08"]
["UN33_00565","Develop Plan & Base Design for Single Und Test","2005-09-29","2006-02-28",null,"2005-09-29"]
["UN33_00566","AVAIL: Vacuum SUT Components","2006-02-13","2006-02-10"]
["UN33_00567","AVAIL:  Diagnostics SUT Components","2006-03-02","2006-03-01"]
["UN33_00568","Construct model UN for support/mover sys testing","2005-10-03","2005-12-01",null,"2005-10-03","2005-12-01"]
["UN33_00570","COMP:  Magnetic Meas. & Tune Metalex Article 02","2006-06-09","2006-06-08"]
["UN33_00575","Assemble Test/Meas/Verification Stand","2005-11-29","2006-03-03",null,"2005-11-29"]
["UN33_00580","ACCEPT: Metalex Und Article 02 (1st Art) at ANL","2006-06-09","2006-06-15"]
["UN33_00585","Prepare Area for Single Undulator Test","2005-10-13","2006-02-28",null,"2005-10-13"]
["UN33_00595","Prepare Ctrls HW/SW for Single Und Test","2005-10-13","2006-02-28",null,"2005-10-13"]
["UN33_00605","Carry out Short-Term Single Undulator Test","2006-05-12","2006-05-25"]
["UN33_00610","Ship Metalex Und Article 02 (1st Art) to SLAC","2006-06-23","2006-06-29"]
["UN33_00612","Disassemble/pack Undulator Metalex Article 02","2006-06-16","2006-06-22"]
["UN33_00615","Assemble Module Components on Stand/Connect","2006-04-28","2006-05-11"]
["UN33_00620","ACCEPT: Metalex Und Article 02 (1st Art) at SL","2006-06-30","2006-06-29"]
["UN33_00625","Single Undulator Module Tested - Long Term","2006-07-27","2006-07-26"]
["UN33_00630","Metalex Und Article 02 Ready for MMF","2006-06-30","2006-06-29"]
["UN33_00635","Write Report: Short Term Test Results","2006-05-26","2006-06-09"]
["UN33_00665","Mount Proto Und on PR S/M","2006-03-22","2006-03-24"]
["UN33_10065","Vendor  Procure All Ti Forgings","2006-07-03","2006-06-30"]
["UN33_10119","Acceptance Measmt & Verification of Strongbacks","2005-06-01","2005-06-30",null,"2005-06-01","2005-06-30"]
["UN33_10165","25% Ti Strongbacks received","2006-03-17","2006-03-16"]
["UN33_10265","50% Ti Strongbacks received","2006-05-01","2006-04-28"]
["UN33_10365","75% Ti Strongbacks received","2006-09-28","2006-09-27"]
["UN33_10500","Ti Strongback Delivery 100% Complete","2006-11-29","2006-11-28"]
["UN33_1A120","Acceptance Measmt & Verification of Strongbacks","2005-07-01","2005-11-21",null,"2005-07-01","2005-11-21"]
["UN33_20055","Evaluate Proposal - Magnet Blocks","2005-05-09","2005-05-13",null,"2005-05-09","2005-05-13"]
["UN33_20060","AWARD: Contract - Magnet Blocks","2005-05-16","2005-05-16",null,"2005-05-16","2005-05-16"]
["UN33_20070","Vendor Fab/Assy - 1st 5% Magnet Blocks","2005-05-17","2005-06-16",null,"2005-05-17","2005-06-16"]
["UN33_20071","Vendor Fab/Assy - 1st 5% Magnet Blocks","2005-06-17","2005-11-04",null,"2005-06-17","2005-11-04"]
["UN33_20080","RCV: From Vendor - 1st 5% Magnet Blocks","2006-01-03","2006-01-03",null,"2006-01-03","2006-01-03"]
["UN33_20090","Vendor Fab/Assy - Remainder of Magnet Blocks","2005-09-13","2006-02-28",null,"2005-09-13"]
["UN33_20101","RCV: From Vendor 2nd 5% Magnet Blocks","2006-02-01","2006-02-01"]
["UN33_20102","RCV: From Vendor 12.5% Magnet Blocks","2006-03-01","2006-03-01"]
["UN33_20103","RCV: From Vendor 12.92% Magnet Blocks","2006-04-03","2006-04-03"]
["UN33_20104","RCV: From Vendor 12.91% Magnet Blocks","2006-05-01","2006-05-01"]
["UN33_20106","RCV: From Vendor 12.92% Magnet Blocks","2006-06-01","2006-06-01"]
["UN33_20107","RCV: From Vendor 12.92% Magnet Blocks","2006-07-03","2006-07-03"]
["UN33_20108","RCV: From Vendor 10.34% Magnet Blocks","2006-08-01","2006-08-01"]
["UN33_20109","RCV: From Vendor 18.09% Magnet Blocks","2006-09-01","2006-09-01"]
["UN33_20120","100% magnet blocks received","2006-09-05","2006-09-01"]
["UN33_30070","Vendor Fab/Assy - Magnet Poles (1-2)","2005-05-02","2005-11-11",null,"2005-05-02","2005-11-11"]
["UN33_30075","PP: Raw Material","2005-06-01","2005-06-01",null,"2005-06-01","2005-06-01"]
["UN33_30076","PP: Progress payment - 15 weeks","2006-02-01","2006-02-01"]
["UN33_30077","PP: Progress Payment - 21 Weeks","2006-02-01","2006-02-01"]
["UN33_30078","PP: Progress Payment - 31 Weeks","2006-02-01","2006-02-01"]
["UN33_30079","PP: Progress Payment - 41 Weeks","2006-02-14","2006-02-14"]
["UN33_30080","RCV: From Vendor - Magnet Poles (1-2)","2005-11-12","2005-11-11",null,"2005-11-12","2005-11-11"]
["UN33_30081","PP: Progress Payment - 51 Weeks","2006-04-03","2006-04-03"]
["UN33_30082","Vendor Fab/Assy - 2nd Lot Magnet Poles (3-12)","2005-09-26","2006-01-31",null,"2005-09-26","2006-01-31"]
["UN33_30086","RCV: From Vendor - 2nd Lot Magnet Poles (3-12)","2006-02-01","2006-01-31"]
["UN33_30087","Vendor Fab/Assy - 3rd Lot Magnet Poles (13-24)","2005-10-27","2006-02-28",null,"2005-10-27"]
["UN33_30088","RCV: From Vendor - 3rd Lot Magnet Poles (13-24)","2006-03-01","2006-02-28"]
["UN33_30090","Vendor Fab/Assy - 4th Lot Magnet Poles (25-36)","2005-12-19","2006-03-16",null,"2005-12-19"]
["UN33_30095","Vendor Fab/Assy - 5th Lot Magnet Poles (37-40)","2006-03-17","2006-06-01"]
["UN33_30096","50% magnet poles received","2006-02-01","2006-01-31"]
["UN33_30100","RCV: From Vendor - 4th Lot Magnet Poles (25-36)","2006-06-02","2006-06-01"]
["UN33_30120","100% magnet poles received","2006-06-02","2006-06-01"]
["UN33_40010","Prep Bid Package - Magnet Assembly","2005-05-09","2005-05-20",null,"2005-05-09","2005-05-20"]
["UN33_40020","Release RFP - Magnet Assembly","2005-06-28","2005-06-28",null,"2005-06-28","2005-06-28"]
["UN33_40030","Vendor Prep Proposal - Magnet Assembly","2005-06-29","2005-08-01",null,"2005-06-29","2005-08-01"]
["UN33_40040","RCV: Proposals - Magnet Assembly","2005-08-02","2005-08-01",null,"2005-08-02","2005-08-01"]
["UN33_40050","Evaluate Proposals - Magnet Assembly","2005-08-02","2005-09-30",null,"2005-08-02","2005-09-30"]
["UN33_40055","Contract Prep ANL Procurement - Magnet Assembly","2005-09-12","2005-10-07",null,"2005-09-12","2005-10-07"]
["UN33_40056","Survey  & Align","2005-10-03","2007-10-31",null,"2005-10-03"]
["UN33_40060","AWARD: 1st Art Mag Assy - Hi-Tech","2005-10-04","2005-10-04",null,"2005-10-04","2005-10-04"]
["UN33_40070","Hi-Tech Prep Fab/Assy, QA, VE Plans","2005-10-11","2005-12-08",null,"2005-10-11","2005-12-08"]
["UN33_40080","RCV: Hi-Tech Fab/Assy Plan","2005-12-09","2005-12-08",null,"2005-12-09","2005-12-08"]
["UN33_40090","Evaluate Hi-Tech Fab/Assy Plan","2005-12-09","2005-12-12",null,"2005-12-09","2005-12-12"]
["UN33_40092","Feedback and Comments to Hi-Tech","2005-12-13","2005-12-13",null,"2005-12-13","2005-12-13"]
["UN33_40094","Approve Hi-Tech VE and QA Plans","2005-12-14","2005-12-13",null,"2005-12-14","2005-12-13"]
["UN33_40096","Permission to start First Article - Hi-Tech","2005-12-14","2005-12-13",null,"2005-12-14","2005-12-13"]
["UN33_40100","Hi-Tech Procure - 1st Art Mag Assy Parts","2005-12-14","2006-01-31",null,"2005-12-14","2006-01-31"]
["UN33_40110","RCV: Ti S/B Article 01, Blocks, Poles, Parts","2006-01-04","2006-01-03",null,"2006-01-04","2006-01-03"]
["UN33_40120","Hi-Tech Fab/Assy-Magnet Article 01 Assembly","2006-02-01","2006-03-30"]
["UN33_40122","Review Hi-Tech travelers/data","2006-03-31","2006-04-03"]
["UN33_40124","Factory Acceptance Article 01 - Hi-Tech","2006-04-04","2006-04-05"]
["UN33_40126","Permission to Ship to ANL Article 01 - Hi-Tech","2006-04-06","2006-04-06"]
["UN33_40128","Hi-Tech Undulator Article 01 Ship to ANL","2006-04-07","2006-04-07"]
["UN33_40140","RCV: From Hi-Tech-1st Article Magnet Assy","2006-04-10","2006-04-10"]
["UN33_40150","AWARD: 1st Art Mag Assy - Metalex","2005-10-04","2005-10-04",null,"2005-10-04","2005-10-04"]
["UN33_40160","Metalex Prep Fab/Assy, QA, VE Plans","2005-10-05","2006-01-30",null,"2005-10-05","2006-01-30"]
["UN33_40170","RCV: Metalex Fab/Assy Plan","2006-01-31","2006-01-30",null,"2006-01-31","2006-01-30"]
["UN33_40180","Evaluate Metalex Fab/Assy Plan","2006-01-31","2006-01-31",null,"2006-01-31","2006-01-31"]
["UN33_40182","Feedback and Comments to Metalex","2006-01-30","2006-01-31",null,"2006-01-30","2006-01-31"]
["UN33_40184","Approve Metalex VE and QA Plans","2006-01-30","2006-01-31",null,"2006-01-30","2006-01-31"]
["UN33_40186","Permission to start First Article - Metalex","2006-01-30","2006-01-31",null,"2006-01-30","2006-01-31"]
["UN33_40190","Metalex Procure - 1st Art Mag Assy Parts","2005-11-18","2006-01-26",null,"2005-11-18","2006-01-26"]
["UN33_40200","RCV: Ti S/B Article 02, Blocks, Poles, Parts","2006-01-04","2006-01-03",null,"2006-01-04","2006-01-03"]
["UN33_40210","Metalex Fab/Assy-Magnet Article 02 Assembly","2006-02-01","2006-03-30"]
["UN33_40211","Review Metalex travelers/data","2006-03-31","2006-04-03"]
["UN33_40212","Factory Acceptance Article 02 - Metalex","2006-04-04","2006-04-05"]
["UN33_40213","Permission to Ship to ANL Article 02 - Metalex","2006-04-06","2006-04-06"]
["UN33_40214","Metalex Undulator Article 02 Ship to ANL","2006-04-07","2006-04-13"]
["UN33_40220","RCV: From Metalex - Magnet Assembly","2006-04-14","2006-04-14"]
["UN33_40230","1st Art. Hi-Tech Undulator Article 01 received","2006-04-11","2006-04-10"]
["UN33_40240","1st Article Metalex Undulator Article 02 recd","2006-04-17","2006-04-14"]
["UN33_40245","All Break Section Interf to UM & Girder Defined","2005-09-01","2005-08-31",null,"2005-09-01","2005-08-31"]
["UN33_40250","Interface to Fixed Supt Documented & Signed Off","2005-09-01","2005-08-31",null,"2005-09-01","2005-08-31"]
["UN33_40256","Design Support/Mover System","2005-07-01","2006-01-31",null,"2005-07-01","2006-01-31"]
["UN33_40265","Prototype Support/Mover System w/Final Reqmts","2006-03-22","2006-03-21"]
["UN33_40274","Prep for FDR - Supt/Mover System, Incl Ctrls Pkg","2006-03-22","2006-03-28"]
["UN33_40275","FDR - Supt/Mover System, Incl Controls Package","2006-06-12","2006-06-12"]
["UN33_40280","COMP: Prequalify Vendors Support/Mover System","2005-11-01","2005-10-31",null,"2005-11-01","2005-10-31"]
["UN33_40285","Release RFP -  Support/Mover System","2006-06-13","2006-06-12"]
["UN33_40290","Vendor Prep Bids -  Support/Mover System","2006-06-13","2006-07-12"]
["UN33_40291","Produce SOW -  Support/Mover System","2006-03-01","2006-03-29"]
["UN33_40292","Select Components and Vendors for SM System","2005-09-01","2005-10-31",null,"2005-09-01","2005-10-31"]
["UN33_40293","Prep Bid Package -  Support/Mover System","2006-03-30","2006-04-12"]
["UN33_40295","Bids Received -  Support/Mover System","2006-07-13","2006-07-12"]
["UN33_40300","Evaluate Bids -  Support/Mover System","2006-07-13","2006-07-19"]
["UN33_40305","AWARD: Support/Mover System 1st Articles","2006-07-20","2006-07-20"]
["UN33_40310","Vendor Prep & Documentation-Support/Mover System","2006-07-21","2006-08-04"]
["UN33_40315","Construction 1st Two Articles - Suppt/Mover Sys","2006-08-07","2006-12-05"]
["UN33_40320","Factory Accept Testing -  Support/Mover System","2006-12-06","2006-12-12"]
["UN33_40321","Ship 1st 2 Articles Support/Mover System to ANL","2006-12-13","2006-12-19"]
["UN33_40322","1st 2 Articles Support/Mover System recd. at ANL","2006-12-20","2006-12-19"]
["UN33_4P019","Pre-Qualify Vendors - Magnet Assembly","2005-05-02","2005-05-31",null,"2005-05-02","2005-05-31"]
["UN33_4P020","Prepare for Acceptance Measurements","2005-06-01","2006-03-22",null,"2005-06-01"]
["UN33_D0405","Get Quote on Ion Pump","2005-09-01","2005-09-08",null,"2005-09-01","2005-09-08"]
["UN33_DL011","PP: 6 Raws - Dial","2005-07-20","2005-07-20",null,"2005-07-20","2005-07-20"]
["UN33_DL017","Dial-Fab/Assy - Ti Strongback Article 01","2005-10-11","2005-11-10",null,"2005-10-11","2005-11-10"]
["UN33_DL020","RCV: Ti S/B Article 01 - Dial","2005-12-01","2005-12-01",null,"2005-12-01","2005-12-01"]
["UN33_DL021","ACCEPT: Factory Acceptance - Ti S/B Article 01","2005-12-02","2005-12-02",null,"2005-12-02","2005-12-02"]
["UN33_DL022","Vendor Ship  - Ti S/B Article 01","2005-12-05","2005-12-09",null,"2005-12-05","2005-12-09"]
["UN33_DL023","AVAIL: Ti Strongback Article 01","2005-12-10","2005-12-09",null,"2005-12-10","2005-12-09"]
["UN33_DL024","ACCEPT: Site acceptance @ Dial - Ti S/B 01","2005-12-12","2005-12-12",null,"2005-12-12","2005-12-12"]
["UN33_DL025","Permission to proceed with Ti Production-Dial","2005-11-15","2005-11-14",null,"2005-11-15","2005-11-14"]
["UN33_DL026","Dial - Fab/Assy - Ti Strongback Article 03","2005-12-01","2006-02-07",null,"2005-12-01"]
["UN33_DL027","RCV: Ti S/B Article 03 - Dial","2006-02-08","2006-02-08"]
["UN33_DL028","ACCEPT: Factory Acceptance - Ti S/B Article 03","2006-02-09","2006-02-09"]
["UN33_DL029","Vendor Ship - Ti S/B Article 03","2006-02-10","2006-02-16"]
["UN33_DL030","AVAIL: Ti Strongback Article 03","2006-02-17","2006-02-16"]
["UN33_DL031","Dial-Fab/Assy - Ti Strongback Article 05","2005-12-19","2006-02-06",null,"2005-12-19"]
["UN33_DL032","RCV: Ti S/B Article 05 - Dial","2006-02-07","2006-02-07"]
["UN33_DL033","ACCEPT: Factory Acceptance - Ti S/B Article 05","2006-02-08","2006-02-08"]
["UN33_DL034","Vendor Ship - Ti S/B Article 05","2006-02-09","2006-02-15"]
["UN33_DL035","AVAIL: Ti Strongback Article 05","2006-02-16","2006-02-15"]
["UN33_DL036","Dial-Fab/Assy - Ti Strongback Article 07","2005-12-19","2006-03-07",null,"2005-12-19"]
["UN33_DL037","RCV: Ti S/B Article 07 - Dial","2006-03-08","2006-03-08"]
["UN33_DL038","ACCEPT: Factory Acceptance - Ti S/B Article 07","2006-03-09","2006-03-09"]
["UN33_DL039","Vendor Ship - Ti S/B Article 07","2006-03-10","2006-03-16"]
["UN33_DL040","AVAIL: Ti Strongback Article 07","2006-03-17","2006-03-16"]
["UN33_DL041","Dial - Fab/Assy - Ti Strongback Article 09","2005-12-19","2006-02-28",null,"2005-12-19"]
["UN33_DL042","RCV: Ti S/B Article 09 - Dial","2006-03-01","2006-03-01"]
["UN33_DL043","ACCEPT: Factory Acceptance - Ti S/B Article 09","2006-03-02","2006-03-02"]
["UN33_DL044","Vendor Ship - Ti S/B Article 09","2006-03-03","2006-03-09"]
["UN33_DL045","AVAIL: Ti Strongback Article 09","2006-03-10","2006-03-09"]
["UN33_DL046","Dial- Fab/Assy - Ti Strongback Article 11","2006-01-25","2006-02-22",null,"2006-01-25"]
["UN33_DL047","RCV: Ti S/B Article 11 - Dial","2006-02-23","2006-02-23"]
["UN33_DL048","ACCEPT: Factory Acceptance - Ti S/B Article 11","2006-02-24","2006-02-24"]
["UN33_DL049","Vendor Ship - Ti S/B Article 11","2006-02-27","2006-03-03"]
["UN33_DL050","AVAIL: Ti Strongback Article 11","2006-03-06","2006-03-03"]
["UN33_DL051","Dial - Fab/Assy - Ti Strongback Article 13","2006-01-23","2006-02-20",null,"2006-01-23"]
["UN33_DL052","RCV: Ti S/B Article 13 - Dial","2006-01-16","2006-02-21",null,"2006-01-16"]
["UN33_DL053","ACCEPT: Factory Acceptance - Ti S/B Article 13","2006-02-22","2006-02-22"]
["UN33_DL054","Vendor Ship - Ti S/B Article 13","2006-02-23","2006-03-01"]
["UN33_DL055","AVAIL: Ti Strongback Article 13","2006-03-02","2006-03-01"]
["UN33_DL056","Dial - Fab/Assy - Ti Strongback Article 15","2006-02-01","2006-02-20"]
["UN33_DL057","RCV: Ti S/B Article 15 - Dial","2006-01-16","2006-02-21",null,"2006-01-16"]
["UN33_DL058","ACCEPT: Factory Acceptance - Ti S/B Article 15","2006-02-22","2006-02-22"]
["UN33_DL059","Vendor Ship - Ti S/B Article 15","2006-02-23","2006-03-01"]
["UN33_DL060","AVAIL: Ti Strongback Article 15","2006-03-02","2006-03-01"]
["UN33_DL061","Dial - Fab/Assy - Ti Strongback Article 17","2006-02-21","2006-03-21"]
["UN33_DL062","RCV: Ti S/B Article 17 - Dial","2006-01-16","2006-03-22",null,"2006-01-16"]
["UN33_DL063","ACCEPT: Factory Acceptance - Ti S/B Article 17","2006-03-23","2006-03-23"]
["UN33_DL065","AVAIL: Ti Strongback Article 17","2006-03-31","2006-03-30"]
["UN33_DL066","Dial - Fab/Assy - Ti Strongback Article 19","2006-03-22","2006-04-19"]
["UN33_DL067","RCV: Ti S/B Article 19 - Dial","2006-01-16","2006-04-20",null,"2006-01-16"]
["UN33_DL068","ACCEPT: Factory Acceptance - Ti S/B Article 19","2006-04-21","2006-04-21"]
["UN33_DL069","Vendor Ship - Ti S/B Article 19","2006-04-24","2006-04-28"]
["UN33_DL070","AVAIL: Ti Strongback Article 19","2006-05-01","2006-04-28"]
["UN33_DL071","Dial - Fab/Assy - Ti Strongback Article 21","2006-04-20","2006-05-18"]
["UN33_DL072","RCV: Ti S/B Article 21 - Dial","2006-01-16","2006-05-19",null,"2006-01-16"]
["UN33_DL073","ACCEPT: Factory Acceptance - Ti S/B Article 21","2006-05-22","2006-05-22"]
["UN33_DL074","Vendor Ship - Ti S/B Article 21","2006-05-23","2006-05-30"]
["UN33_DL075","AVAIL: Ti Strongback Article 21","2006-05-31","2006-05-30"]
["UN33_DL076","Dial-Fab/Assy - Ti Strongback Article 23","2006-05-19","2006-06-19"]
["UN33_DL077","RCV: Ti S/B Article 23 - Dial","2006-01-16","2006-06-20",null,"2006-01-16"]
["UN33_DL078","ACCEPT: Factory Acceptance - Ti S/B Article 23","2006-06-21","2006-06-21"]
["UN33_DL079","Vendor Ship - Ti S/B Article 23","2006-06-22","2006-06-28"]
["UN33_DL080","AVAIL: Ti Strongback Article 23","2006-06-29","2006-06-28"]
["UN33_DL081","Dial-Fab/Assy - Ti Strongback Article 25","2006-06-20","2006-07-19"]
["UN33_DL082","RCV: Ti S/B Article 25 - Dial","2006-07-20","2006-07-20"]
["UN33_DL083","ACCEPT: Factory Acceptance - Ti S/B Article 25","2006-07-21","2006-07-21"]
["UN33_DL084","Vendor Ship - Ti S/B Article 25","2006-07-24","2006-07-28"]
["UN33_DL085","AVAIL: Ti Strongback Article 25","2006-07-31","2006-07-28"]
["UN33_DL086","Dial-Fab/Assy - Ti Strongback Article 27","2006-07-20","2006-08-17"]
["UN33_DL087","RCV: Ti S/B Article 27 - Dial","2006-08-18","2006-08-18"]
["UN33_DL088","ACCEPT: Factory Acceptance - Ti S/B Article 27","2006-08-21","2006-08-21"]
["UN33_DL089","Vendor Ship - Ti S/B Article 27","2006-08-22","2006-08-28"]
["UN33_DL090","AVAIL: Ti Strongback Article 27","2006-08-29","2006-08-28"]
["UN33_DL091","Dial-Fab/Assy - Ti Strongback Article 29","2006-08-18","2006-09-18"]
["UN33_DL092","RCV: Ti S/B Article 29 - Dial","2006-09-19","2006-09-19"]
["UN33_DL093","ACCEPT: Factory Acceptance - Ti S/B Article 29","2006-09-20","2006-09-20"]
["UN33_DL094","Vendor Ship - Ti S/B Article 29","2006-09-21","2006-09-27"]
["UN33_DL095","AVAIL: Ti Strongback Article 29","2006-09-28","2006-09-27"]
["UN33_DL096","Dial-Fab/Assy - Ti Strongback Article 31","2006-09-19","2006-10-17"]
["UN33_DL097","RCV: Ti S/B Article 31 - Dial","2006-10-18","2006-10-18"]
["UN33_DL098","ACCEPT: Factory Acceptance - Ti S/B Article 31","2006-10-19","2006-10-19"]
["UN33_DL099","Vendor Ship - Ti S/B Article 31","2006-10-20","2006-10-26"]
["UN33_DL100","AVAIL: Ti Strongback Article 31","2006-10-27","2006-10-26"]
["UN33_DL101","Dial-Fab/Assy - Ti Strongback Article 33","2006-10-18","2006-11-15"]
["UN33_DL102","RCV: Ti S/B Article 33 - Dial","2006-11-16","2006-11-16"]
["UN33_DL103","ACCEPT: Factory Acceptance - Ti S/B Article 33","2006-11-17","2006-11-17"]
["UN33_DL104","Vendor Ship - Ti S/B Article 33","2006-11-20","2006-11-28"]
["UN33_DL105","AVAIL: Ti Strongback Article 33","2006-11-29","2006-11-28"]
["UN33_DL106","Dial-Fab/Assy - Ti Strongback Article 35","2006-11-16","2006-12-18"]
["UN33_DL107","RCV: Ti S/B Article 35 - Dial","2006-12-19","2006-12-19"]
["UN33_DL108","ACCEPT: Factory Acceptance - Ti S/B Article 36","2006-11-29","2006-11-29"]
["UN33_DL109","Vendor Ship - Ti S/B Article 36","2006-11-30","2006-12-06"]
["UN33_DL110","AVAIL: Ti Strongback Article 36","2006-12-07","2006-12-06"]
["UN33_DL111","Dial-Fab/Assy - Ti Strongback Article 37","2006-12-19","2007-01-24"]
["UN33_DL112","RCV: Ti S/B Article 37 - Dial","2007-01-25","2007-01-25"]
["UN33_DL113","ACCEPT: Factory Acceptance - Ti S/B Article 38","2007-01-05","2007-01-05"]
["UN33_DL114","Vendor Ship - Ti S/B Article 38","2007-01-26","2007-02-01"]
["UN33_DL115","AVAIL: Ti Strongback Article 38","2007-02-26","2007-02-23"]
["UN33_DL116","Dial-Fab/Assy - Ti Strongback Article 39","2007-01-25","2007-02-22"]
["UN33_DL117","RCV: Ti S/B Article 39 - Dial","2007-02-23","2007-02-23"]
["UN33_DL118","ACCEPT: Factory Acceptance - Ti S/B Article 40","2007-02-05","2007-02-05"]
["UN33_DL119","Vendor Ship - Ti S/B Article 40","2007-02-06","2007-02-12"]
["UN33_DL120","AVAIL: Ti Strongback Article 40","2007-02-13","2007-02-12"]
["UN33_DL64","Vendor Ship - Ti S/B Article 17","2006-03-24","2006-03-30"]
["UN33_M101","Prepare S/M Engineering Specification","2005-08-01","2006-02-10",null,"2005-08-01"]
["UN33_M103","Undulator support mover sys PED 80% complete","2005-10-01","2005-09-30",null,"2005-10-01","2005-09-30"]
["UN33_M104","Prepare for internal design review s/m system","2005-11-21","2006-01-31",null,"2005-11-21","2006-01-31"]
["UN33_M105","Internal design review of S/M system","2005-10-11","2005-10-13",null,"2005-10-11","2005-10-13"]
["UN33_M67","Modify APP for quadrupoles","2005-09-01","2005-11-30",null,"2005-09-01","2005-11-30"]
["UN33_M73","Quadrupole APP approved","2005-12-01","2005-11-30",null,"2005-12-01","2005-11-30"]
["UN33_M96","Undulator assembly procedures complete","2005-05-03","2005-05-02",null,"2005-05-03","2005-05-02"]
["UN33_MP102","Controls/vacuum sys integration w/supp mover sys","2005-05-02","2006-02-28",null,"2005-05-02"]
["UN33_MP122","General M&S","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN33_MP123","General Effort","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN33_MP95","Produce SOW for undulator assembly","2005-05-02","2005-05-06",null,"2005-05-02","2005-05-06"]
["UN33_MX010","PP: 1st Raw Piece - Metalex","2005-10-10","2005-10-10",null,"2005-10-10","2005-10-10"]
["UN33_MX012","Metalex-Fab/Assy - Ti Strongback Article 02","2005-08-29","2005-10-14",null,"2005-08-29","2005-10-14"]
["UN33_MX014","Permission to proceed with Ti Production-Metalex","2005-10-18","2005-10-17",null,"2005-10-18","2005-10-17"]
["UN33_MX015","RCV: Ti S/B Article 02 + Tooling - Metalex","2005-10-31","2005-10-31",null,"2005-10-31","2005-10-31"]
["UN33_MX016","ACCEPT: Factory Acceptance - Ti S/B Article 02","2005-10-17","2005-10-17",null,"2005-10-17","2005-10-17"]
["UN33_MX017","Vendor Ship - Ti S/B Article 02","2005-10-18","2005-10-24",null,"2005-10-18","2005-10-24"]
["UN33_MX018","AVAIL: - Ti Strongback Article 02","2005-10-25","2005-10-24",null,"2005-10-25","2005-10-24"]
["UN33_MX019","Metalex-Fab/Assy - Ti Strongback Article 04","2005-10-18","2005-11-15",null,"2005-10-18","2005-11-15"]
["UN33_MX020","RCV: Ti S/B Article 04 - Metalex","2005-11-16","2005-11-16",null,"2005-11-16","2005-11-16"]
["UN33_MX021","ACCEPT: Factory Acceptance - Ti S/B Article 04","2005-11-16","2005-11-16",null,"2005-11-16","2005-11-16"]
["UN33_MX022","Vendor Ship - Ti S/B Article 04","2005-11-17","2005-11-23",null,"2005-11-17","2005-11-23"]
["UN33_MX023","AVAIL: Ti Strongback Article 04","2005-11-24","2005-11-23",null,"2005-11-24","2005-11-23"]
["UN33_MX024","Metalex-Fab/Assy - Ti Strongback Article 06","2005-10-24","2005-12-30",null,"2005-10-24","2005-12-30"]
["UN33_MX025","RCV: Ti S/B Article 06 - Metalex","2005-12-19","2005-12-30",null,"2005-12-19","2005-12-30"]
["UN33_MX026","ACCEPT: Factory Acceptance - Ti S/B Article 06","2005-12-19","2005-12-30",null,"2005-12-19","2005-12-30"]
["UN33_MX027","Vendor Ship - Ti S/B Article 06","2005-12-19","2005-12-30",null,"2005-12-19","2005-12-30"]
["UN33_MX028","AVAIL: Ti Strongback Article 06","2005-12-31","2005-12-30",null,"2005-12-31","2005-12-30"]
["UN33_MX029","Metalex- Fab/Assy - Ti Strongback Article 08","2005-12-01","2005-12-21",null,"2005-12-01","2005-12-21"]
["UN33_MX030","RCV: Ti S/B Article 08 - Metalex","2005-12-22","2005-12-22",null,"2005-12-22","2005-12-22"]
["UN33_MX031","ACCEPT: Factory Acceptance - Ti S/B Article 08","2005-12-22","2005-12-22",null,"2005-12-22","2005-12-22"]
["UN33_MX032","Vendor Ship - Ti S/B Article 08","2005-12-30","2005-12-30",null,"2005-12-30","2005-12-30"]
["UN33_MX033","AVAIL: Ti Strongback Article 08","2005-12-31","2005-12-30",null,"2005-12-31","2005-12-30"]
["UN33_MX034","Metalex-Fab/Assy - Ti Strongback Article 10","2005-11-21","2006-01-31",null,"2005-11-21","2006-01-31"]
["UN33_MX035","RCV: Ti S/B Article 10 - Metalex","2006-01-30","2006-01-31",null,"2006-01-30","2006-01-31"]
["UN33_MX036","ACCEPT: Factory Acceptance - Ti S/B Article 10","2006-01-30","2006-01-31",null,"2006-01-30","2006-01-31"]
["UN33_MX037","MXVendor Ship - Ti S/B Article 10","2006-01-30","2006-01-31",null,"2006-01-30","2006-01-31"]
["UN33_MX038","AVAIL: Ti Strongback Article 10","2006-02-01","2006-01-31",null,"2006-02-01","2006-01-31"]
["UN33_MX039","Metalex-Fab/Assy - Ti Strongback Article 12","2005-11-21","2006-01-12",null,"2005-11-21","2006-01-12"]
["UN33_MX040","RCV: Ti S/B Article 12 - Metalex","2006-01-30","2006-01-31",null,"2006-01-30","2006-01-31"]
["UN33_MX041","ACCEPT: Factory Acceptance - Ti S/B Article 12","2006-01-30","2006-01-31",null,"2006-01-30","2006-01-31"]
["UN33_MX042","Vendor Ship - Ti S/B Article 12","2006-01-30","2006-01-31",null,"2006-01-30","2006-01-31"]
["UN33_MX043","AVAIL: Ti Strongback Article 12","2006-02-01","2006-01-31",null,"2006-02-01","2006-01-31"]
["UN33_MX044","Metalex-Fab/Assy - Ti Strongback Article 14","2005-11-21","2006-01-31",null,"2005-11-21","2006-01-31"]
["UN33_MX045","RCV: Ti S/B Article 14 - Metalex","2006-01-30","2006-01-31",null,"2006-01-30","2006-01-31"]
["UN33_MX046","ACCEPT: Factory Acceptance - Ti S/B Article 14","2006-01-30","2006-01-31",null,"2006-01-30","2006-01-31"]
["UN33_MX047","Vendor Ship - Ti S/B Article 14","2006-01-30","2006-01-31",null,"2006-01-30","2006-01-31"]
["UN33_MX048","AVAIL: Ti Strongback Article 14","2006-02-01","2006-01-31",null,"2006-02-01","2006-01-31"]
["UN33_MX049","Metalex-Fab/Assy - Ti Strongback Article 16","2005-11-28","2006-01-03",null,"2005-11-28","2006-01-03"]
["UN33_MX050","RCV: Ti S/B Article 16 - Metalex","2006-01-04","2006-01-04",null,"2006-01-04","2006-01-04"]
["UN33_MX051","ACCEPT: Factory Acceptance - Ti S/B Article 16","2006-01-04","2006-01-04",null,"2006-01-04","2006-01-04"]
["UN33_MX052","Vendor Ship - Ti S/B Article 16","2006-01-05","2006-01-11",null,"2006-01-05","2006-01-11"]
["UN33_MX053","AVAIL: Ti Strongback Article 16","2006-01-12","2006-01-11",null,"2006-01-12","2006-01-11"]
["UN33_MX054","Metalexl-Fab/Assy - Ti Strongback Article 18","2005-12-19","2006-02-28",null,"2005-12-19"]
["UN33_MX055","RCV: Ti S/B Article 18 - Metalex","2006-03-01","2006-03-01"]
["UN33_MX056","ACCEPT: Factory Acceptance - Ti S/B Article 18","2006-03-01","2006-03-01"]
["UN33_MX057","Vendor Ship - Ti S/B Article 18","2006-03-02","2006-03-08"]
["UN33_MX058","AVAIL: Ti Strongback Article 18","2006-03-09","2006-03-08"]
["UN33_MX059","Metalex-Fab/Assy - Ti Strongback Article 20","2006-03-01","2006-03-29"]
["UN33_MX060","RCV: Ti S/B Article 20 - Metalex","2006-03-30","2006-03-30"]
["UN33_MX061","ACCEPT: Factory Acceptance - Ti S/B Article 20","2006-03-30","2006-03-30"]
["UN33_MX062","Vendor Ship - Ti S/B Article 20","2006-03-31","2006-04-06"]
["UN33_MX063","AVAIL: Ti Strongback Article 20","2006-04-07","2006-04-06"]
["UN33_MX064","Metalex-Fab/Assy - Ti Strongback Article 22","2006-03-30","2006-04-27"]
["UN33_MX065","RCV: Ti S/B Article 22 - Metalex","2006-04-28","2006-04-28"]
["UN33_MX066","ACCEPT: Factory Acceptance - Ti S/B Article 22","2006-05-01","2006-05-01"]
["UN33_MX067","Vendor Ship - Ti S/B Article 22","2006-05-02","2006-05-08"]
["UN33_MX068","AVAIL: Ti Strongback Article 22","2006-05-09","2006-05-08"]
["UN33_MX069","Metalex-Fab/Assy - Ti Strongback Article 24","2006-04-28","2006-05-26"]
["UN33_MX070","RCV: Ti S/B Article 24 - Metalex","2006-05-30","2006-05-30"]
["UN33_MX071","ACCEPT: Factory Acceptance - Ti S/B Article 24","2006-05-30","2006-05-30"]
["UN33_MX072","Vendor Ship - Ti S/B Article 24","2006-05-31","2006-06-06"]
["UN33_MX073","AVAIL: Ti Strongback Article 24","2006-06-07","2006-06-06"]
["UN33_MX074","Metalex-Fab/Assy - Ti Strongback Article 26","2006-05-30","2006-06-27"]
["UN33_MX080","RCV: Ti S/B Article 26 - Metalex","2006-06-28","2006-06-28"]
["UN33_MX081","ACCEPT: Factory Acceptance - Ti S/B Article 26","2006-06-29","2006-06-29"]
["UN33_MX082","Vendor Ship - Ti S/B Article 26","2006-06-30","2006-07-07"]
["UN33_MX083","AVAIL: Ti Strongback Article 26","2006-07-10","2006-07-07"]
["UN33_MX084","Metalex-Fab/Assy - Ti Strongback Article 28","2006-06-28","2006-07-27"]
["UN33_MX085","RCV: Ti S/B Article 28 - Metalex","2006-07-28","2006-07-28"]
["UN33_MX086","ACCEPT: Factory Acceptance - Ti S/B Article 28","2006-07-31","2006-07-31"]
["UN33_MX087","Vendor Ship - Ti S/B Article 28","2006-08-01","2006-08-07"]
["UN33_MX088","AVAIL: Ti Strongback Article 28","2006-08-08","2006-08-07"]
["UN33_MX089","Metalex-Fab/Assy - Ti Strongback Article 30","2006-07-28","2006-08-25"]
["UN33_MX090","RCV: Ti S/B Article 30 - Metalex","2006-08-28","2006-08-28"]
["UN33_MX091","ACCEPT: Factory Acceptance - Ti S/B Article 30","2006-08-29","2006-08-29"]
["UN33_MX092","Vendor Ship - Ti S/B Article 30","2006-08-30","2006-09-06"]
["UN33_MX093","AVAIL: Ti Strongback Article 30","2006-09-07","2006-09-06"]
["UN33_MX094","Metalex-Fab/Assy - Ti Strongback Article 32","2006-08-28","2006-09-26"]
["UN33_MX096","RCV: Ti S/B Article 32 - Metalex","2006-09-27","2006-09-27"]
["UN33_MX097","ACCEPT: Factory Acceptance - Ti S/B Article 32","2006-09-28","2006-09-28"]
["UN33_MX098","Vendor Ship - Ti S/B Article 32","2006-09-29","2006-10-05"]
["UN33_MX099","AVAIL: Ti Strongback Article 32","2006-10-06","2006-10-05"]
["UN33_MX101","Metalex-Fab/Assy - Ti Strongback Article 34","2006-09-27","2006-10-25"]
["UN33_MX102","RCV: Ti S/B Article 34 - Metalex","2006-10-26","2006-10-26"]
["UN33_MX106","Metalex-Fab/Assy - Ti Strongback Article 36","2006-10-26","2006-11-27"]
["UN33_MX107","RCV: Ti S/B Article 36 - Metalex","2006-11-28","2006-11-28"]
["UN33_MX111","Metalex-Fab/Assy - Ti Strongback Article 38","2006-11-28","2007-01-03"]
["UN33_MX112","RCV: Ti S/B Article 38 - Metalex","2007-01-04","2007-01-04"]
["UN33_MX116","Metalex-Fab/Assy - Ti Strongback Article 40","2007-01-04","2007-02-01"]
["UN33_MX117","RCV: Ti S/B Article 40 - Metalex","2007-02-02","2007-02-02"]
["UN33_MXA15","PP: 3 More Raws - Metalex - Articles 4,6,8","2005-11-30","2005-11-30",null,"2005-11-30","2005-11-30"]
["UN33_MXB15","PP: 3 More Raws - Metalex - Articles 10,12,14","2005-12-22","2005-12-22",null,"2005-12-22","2005-12-22"]
["UN33_MXC15","PP: 3 More Raws - Metalex - Articles 16,18,20","2005-12-30","2006-02-28",null,"2005-12-30"]
["UN33_MXD15","PP: 3 More Raws - Metalex - Articles 22,24,26","2006-02-28","2006-02-28"]
["UN33_MXE15","PP: 3 More Raws - Metalex - Articles 28,30,32","2006-04-28","2006-04-28"]
["UN33_MXF15","PP: 4 More Raws - Metalex - Articles 34,36,38,40","2006-06-30","2006-06-30"]
["UN33_P0550","Design Proto Undulator Shipping Crate","2005-09-01","2005-11-14",null,"2005-09-01","2005-11-14"]
["UN33_P0553","Construct/Procure Proto Undulator Shipping Crate","2005-11-15","2005-11-29",null,"2005-11-15","2005-11-29"]
["UN33_P0554","Crate Instrumentation","2005-10-03","2005-11-30",null,"2005-10-03","2005-11-30"]
["UN33_P0555","Pack & Ship Proto Undulator to SLAC (Loan)","2005-11-28","2005-11-30",null,"2005-11-28","2005-11-30"]
["UN33_P0560","Proto Undulator at SLAC","2005-12-01","2006-01-06",null,"2005-12-01","2006-01-06"]
["UN33_P0565","Pack & Ship Proto Undulator back to ANL","2006-02-01","2006-02-09"]
["UN33_VEN05","Ti Strongback Vendor Oversight","2005-07-01","2006-10-23",null,"2005-07-01"]
["UN33_VEN10","Ti Strongback Vendor Oversight","2006-10-24","2007-01-26"]
["UN33_VEN15","Magnet Poles Vendor Oversight","2005-07-18","2006-04-03",null,"2005-07-18"]
["UN34_00006","Renegotiate Contract for 38 Suppt/Mover System","2007-02-12","2007-02-12"]
["UN34_00007","Permission to Proc w/Rem 38 Supt/Mover Systems","2007-02-13","2007-02-12"]
["UN34_00010","Revise Contract Option Hi-Tech - Prdn Units","2006-05-17","2006-05-31"]
["UN34_00012","Evaluate 1st 2 Articles Support/Mover","2006-12-20","2007-01-25"]
["UN34_00013","Renegotiate Contract - 1st Article Support/Mover","2007-01-26","2007-02-08"]
["UN34_00014","Vendor Fab Support/Mover Production Units","2007-02-13","2008-04-23"]
["UN34_00015","AWARD:  Support/Mover Production Units","2007-02-09","2007-02-09"]
["UN34_00017","ACCEPT: 1st 2 Articles Support/Mover","2007-01-26","2007-01-25"]
["UN34_00020","AWARD: Exercise Option @ Hi-Tech - Prdn Units","2006-06-01","2006-06-01"]
["UN34_00045","RCV: Ti Strongback - @ Hi-Tech Article 03","2006-02-17","2006-02-16"]
["UN34_00047","RCV: Support/Mover Lot 1 (9 units)","2007-06-12","2007-06-12"]
["UN34_00048","RCV: Support/Mover Lot  2 (10 units)","2007-09-28","2007-09-28"]
["UN34_00049","RCV: Support/Mover Lot 3a (4 units)","2007-11-27","2007-11-27"]
["UN34_00050","Hi-Tech Fab/Assy - Mag Assy Und Article 03","2006-06-02","2006-07-14"]
["UN34_00051","RCV: Support/Mover Lot 4 (3 units)","2008-02-28","2008-02-28"]
["UN34_00052","RCV: From Hi-Tech - Mag Assy Und Article 03","2006-07-17","2006-07-17"]
["UN34_00053","RCV: Ti Strongback - @ Hi-Tech Article 05","2006-02-16","2006-02-15"]
["UN34_00054","Hi-Tech Fab/Assy - Mag Assy Und Article 05","2006-07-18","2006-08-15"]
["UN34_00056","RCV: From Hi-Tech - Magnet Assy Article 05","2006-08-16","2006-08-16"]
["UN34_00057","RCV: Ti Strongback -  @ Hi-Tech Article 07","2006-03-17","2006-03-16"]
["UN34_00058","Hi-Tech Fab/Assy - Magnet Assy Article 07","2006-08-17","2006-09-07"]
["UN34_00059","Acceptance Measmt and Verif of Undulator Assy","2005-05-02","2006-04-20",null,"2005-05-02"]
["UN34_00060","RCV: From Hi-Tech - Magnet Assy Article 07","2006-09-08","2006-09-08"]
["UN34_00061","RCV: Ti Strongback - @ Hi-Tech Article 09","2006-03-10","2006-03-09"]
["UN34_00062","Hi-Tech Fab/Assy - Magnet Assy Article 09","2006-09-11","2006-09-22"]
["UN34_00064","RCV: From Hi-Tech - Magnet Assy Article 09","2006-09-25","2006-09-25"]
["UN34_00065","RCV: Ti Strongback - @ Hi-Tech Article 11","2006-03-06","2006-03-03"]
["UN34_00066","RCV: 2nd Lot Magnet Blocks, Poles - @Hi-Tech #11","2006-02-01","2006-01-31"]
["UN34_00067","Hi-Tech Fab/Assy - Magnet Assy Article 11","2006-09-26","2006-10-09"]
["UN34_00068","RCV: From Hi-Tech - Magnet Assy Article 11","2006-10-10","2006-10-10"]
["UN34_00069","RCV: Ti Strongback - @ Hi-Tech Article 13","2006-03-02","2006-03-01"]
["UN34_00070","Hi-Tech Fab/Assy - Magnet Assy Article 13","2006-10-11","2006-10-24"]
["UN34_00072","RCV: From Hi-Tech - Magnet Assy Article 13","2006-10-25","2006-10-25"]
["UN34_00073","RCV: Ti Strongback - @ Hi-Tech Article 15","2006-03-02","2006-03-01"]
["UN34_00074","Hi-Tech Fab/Assy - Magnet Assy Article 15","2006-10-26","2006-11-08"]
["UN34_00075","RCV: Ti Strongback - Hi-Tech Article 17","2006-03-31","2006-03-30"]
["UN34_00076","RCV: From Hi-Tech - Magnet Assy Article 15","2006-11-09","2006-11-09"]
["UN34_00078","Hi-Tech Fab/Assy - Magnet Assy Article 17","2006-11-10","2006-11-27"]
["UN34_00080","RCV: From Hi-Tech - Magnet Assy Article 17","2006-11-28","2006-11-28"]
["UN34_00081","RCV: Ti Strongback - @ Hi-Tech Article 19","2006-05-01","2006-04-28"]
["UN34_00082","Hi-Tech Fab/Assy - Magnet Assy Article 19","2006-11-29","2006-12-12"]
["UN34_00083","RCV: From Hi-Tech - Magnet Assy Article 19","2006-12-20","2006-12-20"]
["UN34_00084","RCV: 3rd Lot Magnet Blocks, Poles - @Hi-Tech #21","2006-03-01","2006-02-28"]
["UN34_00085","RCV: Ti Strongback - @ Hi-Tech Article 21","2006-05-31","2006-05-30"]
["UN34_00086","Hi-Tech Fab/Assy - Magnet Assy Article 21","2006-12-21","2007-01-11"]
["UN34_00088","RCV: From Hi-Tech - Magnet Assy Article 21","2007-01-12","2007-01-12"]
["UN34_00089","RCV: Ti Strongback - @ Hi-Tech Article 23","2006-06-29","2006-06-28"]
["UN34_00090","Hi-Tech Fab/Assy - Magnet Assy Article 23","2007-01-15","2007-01-26"]
["UN34_00092","RCV: From Hi-Tech - Magnet Assy Article 23","2007-01-29","2007-01-29"]
["UN34_00093","RCV: Ti Strongback - @ Hi-Tech Article 25","2006-07-31","2006-07-28"]
["UN34_00094","Hi-Tech Fab/Assy - Magnet Assy Article 25","2007-01-30","2007-02-12"]
["UN34_00096","RCV: From Hi-Tech - Magnet Assy Article 25","2007-02-13","2007-02-13"]
["UN34_00097","RCV: Ti Strongback - @ Hi-Tech Article 27","2006-08-29","2006-08-28"]
["UN34_00098","Hi-Tech Fab/Assy - Magnet Assy Article 27","2007-02-14","2007-02-27"]
["UN34_00100","RCV: From Hi-Tech - Magnet Assy Article 27","2007-02-28","2007-02-28"]
["UN34_00101","RCV: Ti Strongback - @ Hi-Tech Article 29","2006-09-28","2006-09-27"]
["UN34_00102","Hi-Tech Fab/Assy - Magnet Assy Article 29","2007-03-01","2007-03-14"]
["UN34_00103","RCV: From Hi-Tech - Magnet Assy Article 29","2007-03-15","2007-03-15"]
["UN34_00104","RCV: 4th Lot Magnet Blocks, Poles - @Hi-Tech #31","2006-06-02","2006-06-01"]
["UN34_00105","RCV: Ti Strongback - @ Hi-Tech Article 31","2006-10-27","2006-10-26"]
["UN34_00106","Hi-Tech Fab/Assy - Magnet Assy Article 31","2007-03-16","2007-03-29"]
["UN34_00108","RCV: From Hi-Tech - Magnet Assy Article 31","2007-03-30","2007-03-30"]
["UN34_00109","RCV: Ti Strongback - @ Hi-Tech Article 33","2006-11-29","2006-11-28"]
["UN34_00110","Hi-Tech Fab/Assy - Magnet Assy Article 33","2007-04-02","2007-04-13"]
["UN34_00112","RCV: From Hi-Tech - Magnet Assy Article 33","2007-04-16","2007-04-16"]
["UN34_00114","Hi-Tech Fab/Assy - Magnet Assy Article 35","2007-04-17","2007-04-30"]
["UN34_00116","RCV: From Hi-Tech - Magnet Assy Article 35","2007-05-01","2007-05-01"]
["UN34_00118","Hi-Tech Fab/Assy - Magnet Assy Article 37","2007-05-02","2007-05-15"]
["UN34_00120","RCV: From Hi-Tech - Magnet Assy Article 37","2007-05-16","2007-05-16"]
["UN34_00122","Hi-Tech Fab/Assy - Magnet Assy Article 39","2007-05-17","2007-05-31"]
["UN34_00124","RCV: From Hi-Tech - Magnet Assy Article 39","2007-06-01","2007-06-01"]
["UN34_00149","RCV: Support/Mover Lot 3b (3 units)","2008-01-03","2008-01-03"]
["UN34_00249","RCV: Support/Mover Lot 3c (2 units)","2008-01-31","2008-01-31"]
["UN34_10010","Revise Contract Option Metalex - Prdn Units","2006-06-16","2006-06-29"]
["UN34_10020","AWARD: Exercise Option Metalex Prdn Units","2006-06-30","2006-06-30"]
["UN34_10045","RCV: Ti Strongback - @ Metalex Article 04","2005-11-24","2005-11-23",null,"2005-11-24","2005-11-23"]
["UN34_10050","Metalex Fab/Assy - Magnet Assy Article 04","2006-07-03","2006-08-14"]
["UN34_10052","RCV: From Metalex - Magnet Assy Article 04","2006-08-15","2006-08-15"]
["UN34_10053","RCV: Ti Strongback - @ Metalex Article 06","2005-12-31","2005-12-30",null,"2005-12-31","2005-12-30"]
["UN34_10054","Metalex Fab/Assy - Magnet Assy Article 06","2006-08-16","2006-09-14"]
["UN34_10056","RCV: From Metalex - Magnet Assy Article 06","2006-09-15","2006-09-15"]
["UN34_10057","RCV: Ti Strongback - @ Metalex Article 08","2005-12-31","2005-12-30",null,"2005-12-31","2005-12-30"]
["UN34_10058","Metalex Fab/Assy - Magnet Assy Article 08","2006-09-18","2006-10-06"]
["UN34_10060","RCV: From Metalex - Magnet Assy Article 08","2006-10-09","2006-10-09"]
["UN34_10061","RCV: Ti Strongback - @ Metalex Article 10","2006-02-01","2006-01-31",null,"2006-02-01","2006-01-31"]
["UN34_10062","Metalex Fab/Assy - Magnet Assy Article 10","2006-10-10","2006-10-23"]
["UN34_10064","RCV: From Metalex - Magnet Assy Article 10","2006-10-24","2006-10-24"]
["UN34_10065","RCV: 2nd Lot Magnet Blocks, Poles - @Metalex #12","2006-02-01","2006-01-31"]
["UN34_10066","RCV: Ti Strongback - @ Metalex Article 12","2006-02-01","2006-01-31",null,"2006-02-01","2006-01-31"]
["UN34_10067","Metalex Fab/Assy - Magnet Assy Article 12","2006-10-25","2006-11-07"]
["UN34_10068","RCV: From Metalex - Magnet Assy Article 12","2006-11-08","2006-11-08"]
["UN34_10069","RCV: Ti Strongback - @ Metalex Article 14","2006-02-01","2006-01-31",null,"2006-02-01","2006-01-31"]
["UN34_10070","Metalex Fab/Assy - Magnet Assy Article 14","2006-11-09","2006-11-22"]
["UN34_10072","RCV: From Metalex - Magnet Assy Article 14","2006-11-27","2006-11-27"]
["UN34_10073","RCV: Ti Strongback - @ Metalex Article 16","2006-01-12","2006-01-11",null,"2006-01-12","2006-01-11"]
["UN34_10074","Metalex Fab/Assy - Magnet Assy Article 16","2006-11-28","2006-12-11"]
["UN34_10076","RCV: From Metalex - Magnet Assy Article 16","2006-12-12","2006-12-12"]
["UN34_10077","RCV: Ti Strongback - @ Metalex Article18","2006-03-09","2006-03-08"]
["UN34_10078","Metalex Fab/Assy - Magnet Assy Article 18","2006-12-13","2007-01-03"]
["UN34_10080","RCV: From Metalex - Magnet Assy Article 18","2007-01-04","2007-01-04"]
["UN34_10081","RCV: Ti Strongback - @ Metalex Article 20","2006-05-01","2006-04-28"]
["UN34_10082","Metalex Fab/Assy - Magnet Assy Article 20","2007-01-05","2007-01-18"]
["UN34_10083","RCV: From Metalex - Magnet Assy Article 20","2007-01-19","2007-01-19"]
["UN34_10084","RCV: 3rd Lot Magnet Blocks, Poles - @Metalex #22","2006-03-01","2006-02-28"]
["UN34_10085","RCV: Ti Strongback - @ Metalex Article 22","2006-05-09","2006-05-08"]
["UN34_10086","Metalex Fab/Assy - Magnet Assy Article 22","2007-01-22","2007-02-02"]
["UN34_10088","RCV: From Metalex - Magnet Assy Article 22","2007-02-05","2007-02-05"]
["UN34_10089","RCV: Ti Strongback - @ Metalex Article 24","2006-06-07","2006-06-06"]
["UN34_10090","Metalex Fab/Assy - Magnet Assy Article 24","2007-02-06","2007-02-19"]
["UN34_10092","RCV: From Metalex - Magnet Assy Article 24","2007-02-20","2007-02-20"]
["UN34_10093","RCV: Ti Strongback - @ Metalex Article 26","2006-07-10","2006-07-07"]
["UN34_10094","Metalex Fab/Assy - Magnet Assy Article 26","2007-02-21","2007-03-06"]
["UN34_10096","RCV: From Metalex - Magnet Assy Article 26","2007-03-07","2007-03-07"]
["UN34_10097","RCV: Ti Strongback - @ Metalex Article 28","2006-08-08","2006-08-07"]
["UN34_10098","Metalex Fab/Assy - Magnet Assy Article 28","2007-03-08","2007-03-21"]
["UN34_10100","RCV: From Metalex - Magnet Assy Article 28","2007-03-22","2007-03-22"]
["UN34_10101","RCV: Ti Strongback - @ Metalex Article 30","2006-09-07","2006-09-06"]
["UN34_10102","Metalex Fab/Assy - Magnet Assy Article 30","2007-03-23","2007-04-05"]
["UN34_10103","50% production undulators delivered","2007-01-22","2007-01-19"]
["UN34_10104","RCV: From Metalex - Magnet Assy Article 30","2007-04-06","2007-04-06"]
["UN34_10105","RCV: Ti Strongback - @ Metalex Article 32","2006-10-06","2006-10-05"]
["UN34_10106","Metalex Fab/Assy - Magnet Assy Article 32","2007-04-09","2007-04-20"]
["UN34_10107","RCV: From Metalex - Magnet Assy Article 32","2007-04-23","2007-04-23"]
["UN34_10108","RCV: 4th Lot Magnet Blocks, Poles - @Metalex #32","2006-06-02","2006-06-01"]
["UN34_10110","Metalex Fab/Assy - Magnet Assy Article 34","2007-04-24","2007-05-07"]
["UN34_10112","RCV: From Metalex - Magnet Assy Article 34","2007-05-08","2007-05-08"]
["UN34_10113","RCV: Ti Strongback - Vend B #36","2006-12-07","2006-12-06"]
["UN34_10114","Metalex Fab/Assy - Magnet Assy Article 36","2007-05-09","2007-05-22"]
["UN34_10116","RCV: From Metalex - Magnet Assy Article 36","2007-05-23","2007-05-23"]
["UN34_10117","RCV: Ti Strongback - Vend B #38","2007-02-26","2007-02-23"]
["UN34_10118","Metalex Fab/Assy - Magnet Assy Article 38","2007-05-24","2007-06-07"]
["UN34_10120","RCV: From Metalex - Magnet Assy Article 38","2007-06-08","2007-06-08"]
["UN34_10121","RCV: Ti Strongback - Vend B #40","2007-02-13","2007-02-12"]
["UN34_10122","Metalex Fab/Assy - Magnet Assy Article 40","2007-06-11","2007-06-22"]
["UN34_10123","RCV: From Metalex - Magnet Assy Article 40","2007-06-25","2007-06-25"]
["UN34_10134","25% production undulators delivered","2006-10-25","2006-10-24"]
["UN34_10144","75% production undulators delivered","2007-04-09","2007-04-06"]
["UN34_10154","100% production/spare undulators received","2007-06-26","2007-06-25"]
["UN34_10250","RCV:  Support/Mover Lot 4 (5 units)","2008-02-29","2008-02-29"]
["UN34_P0010","Components for Support/Mover Prototype","2005-11-01","2006-10-30",null,"2005-11-01"]
["UN34_P0052","RCV:  Support/Mover Lot 4 (2 units)","2008-02-29","2008-02-29"]
["UN35_00020","Define Engineering Requirements - Quadrupole","2005-06-27","2006-02-10",null,"2005-06-27"]
["UN35_00028","Prototype Quadrupole Section","2006-02-13","2006-03-13"]
["UN35_00030","COMP: Rev Specs - Quadrupoles + Controls + PS","2006-02-13","2006-02-10"]
["UN35_00067","Prepare Bid Package - Quad Cables","2006-07-27","2006-08-09"]
["UN35_00069","Prepare Bid Package - Stages, Stands, etc.","2006-07-13","2006-07-26"]
["UN35_00070","Release RFP - Quadrupole Magnets","2006-04-12","2006-04-12"]
["UN35_00072","Release RFP - Quad Cables","2006-08-10","2006-08-09"]
["UN35_00074","Release RFP - Stages, Stands, etc.","2006-07-27","2006-07-26"]
["UN35_00075","Release RFP - Quadrupole Power Supplies","2006-08-30","2006-08-30"]
["UN35_00080","Vendor Prep Proposal - Quadrupole Magnets","2006-04-13","2006-05-11"]
["UN35_00082","Vendor Prep Proposal - Quad Cables","2006-08-10","2006-09-08"]
["UN35_00084","Vendor Prep Proposal - Stages, Stands, etc.","2006-07-27","2006-08-24"]
["UN35_00085","Vendor Prep Proposal - Quadrupole Power Supplies","2006-08-31","2006-09-29"]
["UN35_00090","RCV: Proposal - Quadrupole Magnets","2006-05-12","2006-05-11"]
["UN35_00092","RCV Proposal - Quad Cables","2006-09-11","2006-09-08"]
["UN35_00094","RCV Proposal - Stages, Stands, etc.","2006-08-25","2006-08-24"]
["UN35_00095","RCV:  Proposal - Qudrupole Power Supplies","2006-10-02","2006-09-29"]
["UN35_00100","Evaluate Proposal - Quadrupole Magnets","2006-05-12","2006-05-25"]
["UN35_00101","Evaluate Proposal - Quad Cables","2006-09-11","2006-09-15"]
["UN35_00102","Evaluate Proposal - Quadrupole Power Supplies","2006-10-02","2006-10-20"]
["UN35_00103","Evaluate Proposal - Stages, Stands, etc.","2006-08-25","2006-08-31"]
["UN35_00105","COMP: Accept Vendor Mag Design & Fab & Assy Plan","2006-05-26","2006-05-25"]
["UN35_00110","AWARD: Contract - Quadrupole Magnets","2006-05-26","2006-05-26"]
["UN35_00111","AWARD:  Contract-Quad PS+2 Corr+CTRL Hdwr+Interf","2006-10-23","2006-10-23"]
["UN35_00112","Vendor Fab/Assy - Quad Magnet 1st Article","2006-05-30","2006-10-25"]
["UN35_00113","Vendor Fab/Assy - Quad PS 1st Articles","2006-10-24","2007-04-27"]
["UN35_00114","Ship to ANL - Quad Magnet 1st Article","2006-10-27","2006-11-02"]
["UN35_00116","Measure Magnet - Quad Magnet 1st Article","2006-11-03","2006-11-09"]
["UN35_00117","Accept Quad Magnet 1st Article","2006-11-10","2006-11-10"]
["UN35_00118","AWARD: Contract Option - Quadrupole Magnets","2006-11-10","2006-11-10"]
["UN35_00119","Dimensional Measurement Quad PS 1st Article","2007-06-07","2007-06-11"]
["UN35_00120","Vendor Fab/Assy - Quad Mag 1st lot (18)","2006-11-13","2007-03-28"]
["UN35_00121","Review Travelers - Quadrupole Magnet 1st lot","2007-03-29","2007-04-04"]
["UN35_00122","Vendor Fab/Assy - Quad Mag 2nd lot (15)","2007-03-29","2007-08-03"]
["UN35_00123","Accept Quad PS 1st Article","2007-06-12","2007-06-12"]
["UN35_00124","Permission to Proceed w/Quad PS Fabrication","2007-06-13","2007-06-13"]
["UN35_00125","Ship to ANL - Quad PS 1st Article","2007-05-01","2007-05-07"]
["UN35_00126","Accept Quad PS 1st Lot","2007-10-29","2007-10-29"]
["UN35_00127","Ship Quad 1st Article to SLAC MMF","2006-11-13","2006-11-17"]
["UN35_00128","Electromagnetic Test Quad PS 1st Article","2007-05-08","2007-06-06"]
["UN35_00129","Permission to Proceed w/Quad PS Fabrication","2007-10-30","2007-10-30"]
["UN35_00130","Vendor Fab/Assy -Quad/Corr PS+Ctl HW 1st lot(18)","2007-06-14","2007-10-19"]
["UN35_00132","Vendor Fab/Assy - Quads Spares (4-mag)","2007-03-30","2007-04-12"]
["UN35_00133","Vendor Fab/Assy - Quad PS+ addl items (4)","2008-03-10","2008-03-17"]
["UN35_00134","Review Travelers - Quadrupole Magnet 1st article","2006-10-20","2006-10-26"]
["UN35_00135","Review Travelers - Quadrupole PS 1st article","2007-04-30","2007-04-30"]
["UN35_00136","Review Travelers - Quadrupole Mag 2nd lot","2007-08-06","2007-08-10"]
["UN35_00137","Review Travelers - Quadrupole PS 1st lot","2007-10-22","2007-10-26"]
["UN35_00138","Ship to SLAC MMF - Quadrupole PS 1st lot","2007-10-30","2007-11-05"]
["UN35_00139","Ship to SLAC MMF - Quadrupole PS 1st Article","2007-06-13","2007-06-19"]
["UN35_00140","Vendor Fab/Assy -Quad/Corr PS+Ctl HW 2nd lot(15)","2007-10-22","2008-03-06"]
["UN35_00141","Review Travelers - Quadrupole PS 2nd lot","2008-03-07","2008-03-13"]
["UN35_00142","100% Quads received","2007-04-13","2007-04-12"]
["UN35_00143","Ship to SLAC MMF - Quadrupole PS 2nd lot","2008-03-17","2008-03-21"]
["UN35_00144","Ship to SLAC MMF - Quadrupole Magnet 1st lot","2007-04-05","2007-04-11"]
["UN35_00145","100% Quad Power Supplies received","2008-03-18","2008-03-18"]
["UN35_00147","Accept Quad PS 2nd Lot","2008-03-14","2008-03-14"]
["UN35_00150","Vendor Fab/Assy - Quad Stages, Stands, etc. (4)","2006-11-03","2006-11-16"]
["UN35_00151","Vendor Fab/Assy - Quad Cables (4)","2006-11-03","2006-11-16"]
["UN35_00154","Ship to SLAC MMF - Quadrupole Mag 2nd lot","2007-08-13","2007-08-17"]
["UN35_00155","100% Quadrupole Magnets Recvd at SLAC","2007-08-20","2007-08-17"]
["UN35_00170","AWARD: - Contract - Stages and Stands, etc.","2006-09-01","2006-09-01"]
["UN35_00172","AWARD: - Contract - Quad Cables","2006-10-02","2006-10-02"]
["UN35_00174","REC:  100% of Stages and Stands, etc.","2007-03-19","2007-03-16"]
["UN35_00175","REC:  100% of Quadrupole Cables","2007-02-15","2007-02-14"]
["UN35_00184","Vendor Ship - Stages, Stands, etc. to SLAC","2007-03-12","2007-03-16"]
["UN35_00210","AWARD: Contract - Quads Spares (4-mag)","2007-03-29","2007-03-29"]
["UN35_00211","AWARD:  Contract-Quad PS+addl items (4)","2008-03-07","2008-03-07"]
["UN35_00270","AWARD - Contract - Stages and Stands (4)","2006-11-02","2006-11-02"]
["UN35_00272","AWARD - Contract - Quad Cables","2006-11-02","2006-11-02"]
["UN35_01132","Vendor Fab/Assy - Quad Cables","2006-10-03","2007-02-07"]
["UN35_01133","Vendor Fab/Assy - Stages, Stands, etc.","2006-09-05","2007-03-09"]
["UN35_01142","Vendor Ship Quad Cables to Slac","2007-02-08","2007-02-14"]
["UN35_M112","Design quadrupole magnet system","2005-07-01","2006-02-10",null,"2005-07-01"]
["UN35_M113","Specify quad and corrector power supplies","2006-02-13","2006-05-01"]
["UN35_M114","Write SOW for quad/corrector magnets","2005-11-28","2006-02-23",null,"2005-11-28"]
["UN35_M115","Write SOW for quad and corrector power supplies","2006-05-02","2006-06-29"]
["UN35_M116","SOWs complete","2006-07-24","2006-07-21"]
["UN35_M117","IDR - quadrupole magnet system","2005-11-18","2005-11-18",null,"2005-11-18","2005-11-18"]
["UN35_M118","Prepare RFPs for quadrupole magnets","2006-02-24","2006-03-24"]
["UN35_M119","Prepare RFP for quad & corrector power supplies","2006-06-30","2006-08-29"]
["UN35_M121","Write SOW for Stages, Stands, etc.","2006-06-13","2006-07-12"]
["UN35_M122","Write SOW for Quad Cables","2006-06-22","2006-07-21"]
["UN35_M124","Verify Quad Section Performance","2006-03-14","2006-03-28"]
["UN35_M125","FDR Quad System","2006-04-11","2006-04-11"]
["UN35_M127","RFI for Quad Magnets with draft SOW","2006-02-24","2006-04-06"]
["UN35_M129","Prepare for Quadrupole System IDR","2005-09-26","2005-11-30",null,"2005-09-26","2005-11-30"]
["UN35_M130","Prepare for Quadrupole System FDR","2006-03-28","2006-04-10"]
["UN35_MP110","Preliminary engineering of quadrupole system","2005-05-02","2005-06-24",null,"2005-05-02","2005-06-24"]
["UN362_0010","REQD:  Undulator Mag Assy - 01","2006-06-01","2006-05-31"]
["UN362_0020","Adjust to Temperature - 01","2006-06-01","2006-06-14"]
["UN362_0030","Undulator Setup and Alignment @ Test Bench - 01","2006-08-29","2006-08-30"]
["UN362_0040","Undulator Measurement and Set Gap - 01","2006-08-31","2006-09-07"]
["UN362_0060","Undulator Measurement/Pre-fiducialization - 01","2006-09-08","2006-09-21"]
["UN362_0070","Undulator Setup and Alignment @ CMM - 01","2006-09-22","2006-09-22"]
["UN362_0080","Undulator Fiducialization - 01","2006-09-25","2006-09-29"]
["UN362_0085","Undulator Ready for Assembly - 01","2006-10-02","2006-10-06"]
["UN362_0087","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 01","2007-09-27","2007-09-26"]
["UN362_0088","Assemble Cradle/Vacuum Chamber - 01","2007-09-27","2007-09-28"]
["UN362_0089","Assemble Quad/Vac Chmbr/BPM/Cher Det - 01","2007-10-01","2007-10-04"]
["UN362_0090","Undulator/QD/VacCh/BPM/Prealign - 01","2007-10-01","2007-10-04"]
["UN362_0100","Undulator Cradle RFI - 01","2007-10-05","2007-10-04"]
["UN362_0110","REQD:  Undulator Mag Assy - 02","2006-06-30","2006-06-29"]
["UN362_0120","Adjust to Temperature - 02","2006-06-30","2006-07-14"]
["UN362_0130","Undulator Setup and Alignment @ Test Bench - 02","2006-09-22","2006-09-25"]
["UN362_0140","Undulator Measurement and Set Gap - 02","2006-09-26","2006-10-02"]
["UN362_0160","Undulator Measurement/Pre-fiducialization - 02","2006-10-03","2006-10-16"]
["UN362_0170","Undulator Setup and Alignment @ CMM - 02","2006-10-17","2006-10-17"]
["UN362_0180","Undulator Fiducialization - 02","2006-10-18","2006-10-24"]
["UN362_0185","Undulator Ready for Assembly - 02","2006-10-25","2006-10-31"]
["UN362_0187","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 02","2007-09-27","2007-09-26"]
["UN362_0188","Assemble Cradle/Vacuum Chamber - 02","2007-09-27","2007-09-28"]
["UN362_0189","Assemble Quad/Vac Chmbr/BPM/Cher Det - 02","2007-10-01","2007-10-04"]
["UN362_0190","Undulator/QD/VacCh/BPM/Prealign - 02","2007-10-01","2007-10-04"]
["UN362_0200","Undulator Cradle RFI - 02","2007-10-05","2007-10-04"]
["UN362_0210","REQD:  Undulator Mag Assy - 03","2006-07-18","2006-07-17"]
["UN362_0220","Adjust to Temperature - 03","2006-07-18","2006-07-31"]
["UN362_0230","Undulator Setup and Alignment @ Test Bench - 03","2006-10-17","2006-10-17"]
["UN362_0240","Undulator Measurement and Set Gap - 03","2006-10-18","2006-10-23"]
["UN362_0260","Undulator Measurement/Pre-fiducialization - 03","2006-10-24","2006-11-02"]
["UN362_0270","Undulator Setup and Alignment @ CMM - 03","2006-11-03","2006-11-03"]
["UN362_0280","Undulator Fiducialization - 03","2006-11-06","2006-11-09"]
["UN362_0285","Undulator Ready for Assembly - 03","2006-11-10","2006-11-16"]
["UN362_0287","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 03","2007-09-27","2007-09-26"]
["UN362_0288","Assemble Cradle/Quad Supt/Movers - 03","2007-09-27","2007-09-27"]
["UN362_0289","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 03","2007-09-28","2007-10-01"]
["UN362_0290","Install Undulators on Cradle- 03","2007-10-02","2007-10-02"]
["UN362_0291","Prealign Vacuum Chamber - 03","2007-10-03","2007-10-03"]
["UN362_0300","Undulator Cradle RFI - 03","2007-10-04","2007-10-03"]
["UN362_0310","REQD:  Undulator Mag Assy - 04","2006-08-16","2006-08-15"]
["UN362_0320","Adjust to Temperature - 04","2006-08-16","2006-08-29"]
["UN362_0330","Undulator Setup and Alignment @ Test Bench - 04","2006-11-03","2006-11-03"]
["UN362_0340","Undulator Measurement and Set Gap - 04","2006-11-06","2006-11-09"]
["UN362_0360","Undulator Measurement/Pre-fiducialization - 04","2006-11-10","2006-11-21"]
["UN362_0370","Undulator Setup and Alignment @ CMM - 04","2006-11-22","2006-11-22"]
["UN362_0380","Undulator Fiducialization - 04","2006-11-27","2006-11-30"]
["UN362_0385","Undulator Ready for Assembly - 04","2006-12-01","2006-12-07"]
["UN362_0387","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 04","2007-09-27","2007-09-26"]
["UN362_0388","Assemble Cradle/Quad Supt/Movers - 04","2007-09-27","2007-09-27"]
["UN362_0389","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 04","2007-09-28","2007-10-01"]
["UN362_0390","Install Undulators on Cradle- 04","2007-10-02","2007-10-02"]
["UN362_0391","Prealign Vacuum Chamber - 04","2007-10-03","2007-10-03"]
["UN362_0400","Undulator Cradle RFI - 04","2007-10-04","2007-10-03"]
["UN362_0410","REQD:  Undulator Mag Assy - 05","2006-08-17","2006-08-16"]
["UN362_0420","Adjust to Temperature - 05","2006-08-17","2006-08-30"]
["UN362_0430","Undulator Setup and Alignment @ Test Bench - 05","2006-11-22","2006-11-22"]
["UN362_0440","Undulator Measurement and Set Gap - 05","2006-11-27","2006-11-28"]
["UN362_0460","Undulator Measurement/Pre-fiducialization - 05","2006-11-29","2006-12-04"]
["UN362_0470","Undulator Setup and Alignment @ CMM - 05","2006-12-05","2006-12-05"]
["UN362_0480","Undulator Fiducialization - 05","2006-12-06","2006-12-07"]
["UN362_0485","Undulator Ready for Assembly - 05","2006-12-08","2006-12-14"]
["UN362_0487","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 05","2007-09-27","2007-09-26"]
["UN362_0488","Assemble Cradle/Quad Supt/Movers - 05","2007-09-27","2007-09-27"]
["UN362_0489","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 05","2007-09-28","2007-10-01"]
["UN362_0490","Install Undulators on Cradle- 05","2007-10-02","2007-10-02"]
["UN362_0491","Prealign Vacuum Chamber - 05","2007-10-03","2007-10-03"]
["UN362_0500","Undulator Cradle RFI - 05","2007-10-04","2007-10-03"]
["UN362_0510","REQD:  Undulator Mag Assy - 06","2006-09-18","2006-09-15"]
["UN362_0520","Adjust to Temperature - 06","2006-09-18","2006-09-29"]
["UN362_0530","Undulator Setup and Alignment @ Test Bench - 06","2006-12-05","2006-12-05"]
["UN362_0540","Undulator Measurement and Set Gap - 06","2006-12-06","2006-12-08"]
["UN362_0560","Undulator Measurement/Pre-fiducialization - 06","2006-12-11","2006-12-13"]
["UN362_0570","Undulator Setup and Alignment @ CMM - 06","2006-12-14","2006-12-14"]
["UN362_0580","Undulator Fiducialization - 06","2006-12-15","2007-01-02"]
["UN362_0585","Undulator Ready for Assembly - 06","2007-01-03","2007-01-09"]
["UN362_0587","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 06","2007-09-27","2007-09-26"]
["UN362_0588","Assemble Cradle/Quad Supt/Movers - 06","2007-09-27","2007-09-27"]
["UN362_0589","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 06","2007-09-28","2007-10-01"]
["UN362_0590","Install Undulators on Cradle- 06","2007-10-02","2007-10-02"]
["UN362_0591","Prealign Vacuum Chamber - 06","2007-10-03","2007-10-03"]
["UN362_0600","Undulator Cradle RFI - 06","2007-10-04","2007-10-03"]
["UN362_0610","REQD:  Undulator Mag Assy - 07","2006-09-11","2006-09-08"]
["UN362_0620","Adjust to Temperature - 07","2006-09-11","2006-09-22"]
["UN362_0630","Undulator Setup and Alignment @ Test Bench - 07","2006-12-14","2006-12-14"]
["UN362_0640","Undulator Measurement and Set Gap - 07","2006-12-15","2007-01-02"]
["UN362_0660","Undulator Measurement/Pre-fiducialization - 07","2007-01-03","2007-01-08"]
["UN362_0670","Undulator Setup and Alignment @ CMM - 07","2007-01-09","2007-01-09"]
["UN362_0680","Undulator Fiducialization - 07","2007-01-10","2007-01-11"]
["UN362_0685","Undulator Ready for Assembly - 07","2007-01-12","2007-01-19"]
["UN362_0687","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 07","2007-09-27","2007-09-26"]
["UN362_0688","Assemble Cradle/Quad Supt/Movers - 07","2007-09-27","2007-09-27"]
["UN362_0689","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 07","2007-09-28","2007-10-01"]
["UN362_0690","Install Undulators on Cradle- 07","2007-10-02","2007-10-02"]
["UN362_0691","Prealign Vacuum Chamber - 07","2007-10-03","2007-10-03"]
["UN362_0700","Undulator Cradle RFI - 07","2007-10-04","2007-10-03"]
["UN362_0710","REQD:  Undulator Mag Assy - 08","2006-10-10","2006-10-09"]
["UN362_0720","Adjust to Temperature - 08","2006-10-10","2006-10-23"]
["UN362_0730","Undulator Setup and Alignment @ Test Bench - 08","2007-01-09","2007-01-09"]
["UN362_0740","Undulator Measurement and Set Gap - 08","2007-01-10","2007-01-11"]
["UN362_0760","Undulator Measurement/Pre-fiducialization - 08","2007-01-12","2007-01-18"]
["UN362_0770","Undulator Setup and Alignment @ CMM - 08","2007-01-19","2007-01-19"]
["UN362_0780","Undulator Fiducialization - 08","2007-01-22","2007-01-23"]
["UN362_0785","Undulator Ready for Assembly - 08","2007-01-24","2007-01-30"]
["UN362_0787","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 08","2007-09-27","2007-09-26"]
["UN362_0788","Assemble Cradle/Quad Supt/Movers - 08","2007-09-27","2007-09-27"]
["UN362_0789","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 08","2007-09-28","2007-10-01"]
["UN362_0790","Install Undulators on Cradle- 08","2007-10-02","2007-10-02"]
["UN362_0791","Prealign Vacuum Chamber - 08","2007-10-03","2007-10-03"]
["UN362_0800","Undulator Cradle RFI - 08","2007-10-04","2007-10-03"]
["UN362_0810","REQD:  Undulator Mag Assy - 09","2006-09-26","2006-09-25"]
["UN362_0820","Adjust to Temperature - 09","2006-09-26","2006-10-09"]
["UN362_0830","Undulator Setup and Alignment @ Test Bench - 09","2007-01-19","2007-01-19"]
["UN362_0840","Undulator Measurement and Set Gap - 09","2007-01-22","2007-01-23"]
["UN362_0860","Undulator Measurement/Pre-fiducialization - 09","2007-01-24","2007-01-29"]
["UN362_0870","Undulator Setup and Alignment @ CMM - 09","2007-01-30","2007-01-30"]
["UN362_0880","Undulator Fiducialization - 09","2007-01-31","2007-02-01"]
["UN362_0885","Undulator Ready for Assembly - 09","2007-02-02","2007-02-08"]
["UN362_0887","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 09","2007-09-27","2007-09-26"]
["UN362_0888","Assemble Cradle/Quad Supt/Movers - 09","2007-09-27","2007-09-27"]
["UN362_0889","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 09","2007-09-28","2007-10-01"]
["UN362_0890","Install Undulators on Cradle- 09","2007-10-02","2007-10-02"]
["UN362_0891","Prealign Vacuum Chamber - 09","2007-10-03","2007-10-03"]
["UN362_0900","Undulator Cradle RFI - 09","2007-10-04","2007-10-03"]
["UN362_0910","REQD:  Undulator Mag Assy - 10","2006-10-25","2006-10-24"]
["UN362_0920","Adjust to Temperature - 10","2006-10-25","2006-11-07"]
["UN362_0930","Undulator Setup and Alignment @ Test Bench - 10","2007-01-30","2007-01-30"]
["UN362_0940","Undulator Measurement and Set Gap - 10","2007-01-31","2007-02-01"]
["UN362_0960","Undulator Measurement/Pre-fiducialization - 10","2007-02-02","2007-02-07"]
["UN362_0970","Undulator Setup and Alignment @ CMM - 10","2007-02-08","2007-02-08"]
["UN362_0980","Undulator Fiducialization - 10","2007-02-09","2007-02-12"]
["UN362_0985","Undulator Ready for Assembly - 10","2007-02-13","2007-02-20"]
["UN362_0987","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 10","2007-10-01","2007-09-28"]
["UN362_0988","Assemble Cradle/Quad Supt/Movers - 10","2007-10-01","2007-10-01"]
["UN362_0989","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 10","2007-10-02","2007-10-03"]
["UN362_0990","Install Undulators on Cradle- 10","2007-10-04","2007-10-04"]
["UN362_0991","Prealign Vacuum Chamber - 10","2007-10-05","2007-10-05"]
["UN362_1000","Undulator Cradle RFI - 10","2007-10-08","2007-10-05"]
["UN362_1010","REQD:  Undulator Mag Assy - 11","2006-10-11","2006-10-10"]
["UN362_1020","Adjust to Temperature - 11","2006-10-11","2006-10-24"]
["UN362_1030","Undulator Setup and Alignment @ Test Bench - 11","2007-02-08","2007-02-08"]
["UN362_1040","Undulator Measurement and Set Gap - 11","2007-02-09","2007-02-12"]
["UN362_1060","Undulator Measurement/Pre-fiducialization - 11","2007-02-13","2007-02-16"]
["UN362_1070","Undulator Setup and Alignment @ CMM - 11","2007-02-20","2007-02-20"]
["UN362_1080","Undulator Fiducialization - 11","2007-02-21","2007-02-22"]
["UN362_1085","Undulator Ready for Assembly - 11","2007-02-23","2007-03-01"]
["UN362_1087","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 11","2007-10-04","2007-10-03"]
["UN362_1088","Assemble Cradle/Quad Supt/Movers - 11","2007-10-04","2007-10-04"]
["UN362_1089","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 11","2007-10-05","2007-10-08"]
["UN362_1090","Install Undulators on Cradle- 11","2007-10-09","2007-10-09"]
["UN362_1091","Prealign Vacuum Chamber - 11","2007-10-10","2007-10-10"]
["UN362_1100","Undulator Cradle RFI - 11","2007-10-11","2007-10-10"]
["UN362_1110","REQD:  Undulator Mag Assy - 12","2006-11-09","2006-11-08"]
["UN362_1120","Adjust to Temperature - 12","2006-11-09","2006-11-22"]
["UN362_1130","Undulator Setup and Alignment @ Test Bench - 12","2007-02-20","2007-02-20"]
["UN362_1140","Undulator Measurement and Set Gap - 12","2007-02-21","2007-02-22"]
["UN362_1160","Undulator Measurement/Pre-fiducialization - 12","2007-02-23","2007-02-28"]
["UN362_1170","Undulator Setup and Alignment @ CMM - 12","2007-03-01","2007-03-01"]
["UN362_1180","Undulator Fiducialization - 12","2007-03-02","2007-03-05"]
["UN362_1185","Undulator Ready for Assembly - 12","2007-03-06","2007-03-12"]
["UN362_1187","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 12","2007-10-04","2007-10-03"]
["UN362_1188","Assemble Cradle/Quad Supt/Movers - 12","2007-10-04","2007-10-04"]
["UN362_1189","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 12","2007-10-05","2007-10-08"]
["UN362_1190","Install Undulators on Cradle- 12","2007-10-09","2007-10-09"]
["UN362_1191","Prealign Vacuum Chamber - 12","2007-10-10","2007-10-10"]
["UN362_1200","Undulator Cradle RFI - 12","2007-10-11","2007-10-10"]
["UN362_1210","REQD:  Undulator Mag Assy - 13","2006-10-26","2006-10-25"]
["UN362_1220","Adjust to Temperature - 13","2006-10-26","2006-11-08"]
["UN362_1230","Undulator Setup and Alignment @ Test Bench - 13","2007-03-01","2007-03-01"]
["UN362_1240","Undulator Measurement and Set Gap - 13","2007-03-02","2007-03-05"]
["UN362_1260","Undulator Measurement/Pre-fiducialization - 13","2007-03-06","2007-03-09"]
["UN362_1270","Undulator Setup and Alignment @ CMM - 13","2007-03-12","2007-03-12"]
["UN362_1280","Undulator Fiducialization - 13","2007-03-13","2007-03-14"]
["UN362_1285","Undulator Ready for Assembly - 13","2007-03-15","2007-03-21"]
["UN362_1287","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 13","2007-10-04","2007-10-03"]
["UN362_1288","Assemble Cradle/Quad Supt/Movers - 13","2007-10-04","2007-10-04"]
["UN362_1289","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 13","2007-10-05","2007-10-08"]
["UN362_1290","Install Undulators on Cradle- 13","2007-10-09","2007-10-09"]
["UN362_1291","Prealign Vacuum Chamber - 13","2007-10-10","2007-10-10"]
["UN362_1300","Undulator Cradle RFI - 13","2007-10-11","2007-10-10"]
["UN362_1310","REQD:  Undulator Mag Assy - 14","2006-11-28","2006-11-27"]
["UN362_1320","Adjust to Temperature - 14","2006-11-28","2006-12-11"]
["UN362_1330","Undulator Setup and Alignment @ Test Bench - 14","2007-03-12","2007-03-12"]
["UN362_1340","Undulator Measurement and Set Gap - 14","2007-03-13","2007-03-14"]
["UN362_1360","Undulator Measurement/Pre-fiducialization - 14","2007-03-15","2007-03-20"]
["UN362_1370","Undulator Setup and Alignment @ CMM - 14","2007-03-21","2007-03-21"]
["UN362_1380","Undulator Fiducialization - 14","2007-03-22","2007-03-23"]
["UN362_1385","Undulator Ready for Assembly - 14","2007-03-26","2007-03-30"]
["UN362_1387","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 14","2007-10-04","2007-10-03"]
["UN362_1388","Assemble Cradle/Quad Supt/Movers - 14","2007-10-04","2007-10-04"]
["UN362_1389","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 14","2007-10-05","2007-10-08"]
["UN362_1390","Install Undulators on Cradle- 14","2007-10-09","2007-10-09"]
["UN362_1391","Prealign Vacuum Chamber - 14","2007-10-10","2007-10-10"]
["UN362_1400","Undulator Cradle RFI - 14","2007-10-11","2007-10-10"]
["UN362_1410","REQD:  Undulator Mag Assy - 15","2006-11-10","2006-11-09"]
["UN362_1420","Adjust to Temperature - 15","2006-11-10","2006-11-27"]
["UN362_1430","Undulator Setup and Alignment @ Test Bench - 15","2007-03-21","2007-03-21"]
["UN362_1440","Undulator Measurement and Set Gap - 15","2007-03-22","2007-03-23"]
["UN362_1460","Undulator Measurement/Pre-fiducialization - 15","2007-03-26","2007-03-29"]
["UN362_1470","Undulator Setup and Alignment @ CMM - 15","2007-03-30","2007-03-30"]
["UN362_1480","Undulator Fiducialization - 15","2007-04-02","2007-04-03"]
["UN362_1485","Undulator Ready for Assembly - 15","2007-04-04","2007-04-10"]
["UN362_1487","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 15","2007-10-04","2007-10-03"]
["UN362_1488","Assemble Cradle/Quad Supt/Movers - 15","2007-10-04","2007-10-04"]
["UN362_1489","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 15","2007-10-05","2007-10-08"]
["UN362_1490","Install Undulators on Cradle- 15","2007-10-09","2007-10-09"]
["UN362_1491","Prealign Vacuum Chamber - 15","2007-10-10","2007-10-10"]
["UN362_1500","Undulator Cradle RFI - 15","2007-10-11","2007-10-10"]
["UN362_1510","REQD:  Undulator Mag Assy - 16","2006-12-13","2006-12-12"]
["UN362_1520","Adjust to Temperature - 16","2006-12-13","2007-01-10"]
["UN362_1530","Undulator Setup and Alignment @ Test Bench - 16","2007-03-30","2007-03-30"]
["UN362_1540","Undulator Measurement and Set Gap - 16","2007-04-02","2007-04-03"]
["UN362_1560","Undulator Measurement/Pre-fiducialization - 16","2007-04-04","2007-04-09"]
["UN362_1570","Undulator Setup and Alignment @ CMM - 16","2007-04-10","2007-04-10"]
["UN362_1580","Undulator Fiducialization - 16","2007-04-11","2007-04-12"]
["UN362_1585","Undulator Ready for Assembly - 16","2007-04-13","2007-04-19"]
["UN362_1587","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 16","2007-10-04","2007-10-03"]
["UN362_1588","Assemble Cradle/Quad Supt/Movers - 16","2007-10-04","2007-10-04"]
["UN362_1589","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 16","2007-10-05","2007-10-08"]
["UN362_1590","Install Undulators on Cradle- 16","2007-10-09","2007-10-09"]
["UN362_1591","Prealign Vacuum Chamber - 16","2007-10-10","2007-10-10"]
["UN362_1600","Undulator Cradle RFI - 16","2007-10-11","2007-10-10"]
["UN362_1610","REQD:  Undulator Mag Assy - 17","2006-11-29","2006-11-28"]
["UN362_1620","Adjust to Temperature - 17","2006-11-29","2006-12-12"]
["UN362_1630","Undulator Setup and Alignment @ Test Bench - 17","2007-04-10","2007-04-10"]
["UN362_1640","Undulator Measurement and Set Gap - 17","2007-04-11","2007-04-12"]
["UN362_1660","Undulator Measurement/Pre-fiducialization - 17","2007-04-13","2007-04-18"]
["UN362_1670","Undulator Setup and Alignment @ CMM - 17","2007-04-19","2007-04-19"]
["UN362_1680","Undulator Fiducialization - 17","2007-04-20","2007-04-23"]
["UN362_1685","Undulator Ready for Assembly - 17","2007-04-24","2007-04-30"]
["UN362_1687","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 17","2007-10-04","2007-10-03"]
["UN362_1688","Assemble Cradle/Quad Supt/Movers - 17","2007-10-04","2007-10-04"]
["UN362_1689","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 17","2007-10-05","2007-10-08"]
["UN362_1690","Install Undulators on Cradle- 17","2007-10-09","2007-10-09"]
["UN362_1691","Prealign Vacuum Chamber - 17","2007-10-10","2007-10-10"]
["UN362_1700","Undulator Cradle RFI - 17","2007-10-11","2007-10-10"]
["UN362_1710","REQD:  Undulator Mag Assy - 18","2007-01-05","2007-01-04"]
["UN362_1720","Adjust to Temperature - 18","2007-01-05","2007-01-19"]
["UN362_1730","Undulator Setup and Alignment @ Test Bench - 18","2007-04-19","2007-04-19"]
["UN362_1740","Undulator Measurement and Set Gap - 18","2007-04-20","2007-04-23"]
["UN362_1760","Undulator Measurement/Pre-fiducialization - 18","2007-04-24","2007-04-27"]
["UN362_1770","Undulator Setup and Alignment @ CMM - 18","2007-04-30","2007-04-30"]
["UN362_1780","Undulator Fiducialization - 18","2007-05-01","2007-05-02"]
["UN362_1785","Undulator Ready for Assembly - 18","2007-05-03","2007-05-09"]
["UN362_1787","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 18","2007-10-04","2007-10-03"]
["UN362_1788","Assemble Cradle/Quad Supt/Movers - 18","2007-10-04","2007-10-04"]
["UN362_1789","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 18","2007-10-05","2007-10-08"]
["UN362_1790","Install Undulators on Cradle- 18","2007-10-09","2007-10-09"]
["UN362_1791","Prealign Vacuum Chamber - 18","2007-10-10","2007-10-10"]
["UN362_1800","Undulator Cradle RFI - 18","2007-10-11","2007-10-10"]
["UN362_1910","REQD:  Undulator Mag Assy - 19","2007-01-02","2006-12-15"]
["UN362_1920","Adjust to Temperature - 19","2007-01-02","2007-01-16"]
["UN362_1930","Undulator Setup and Alignment @ Test Bench - 19","2007-04-30","2007-04-30"]
["UN362_1940","Undulator Measurement and Set Gap - 19","2007-05-01","2007-05-02"]
["UN362_1960","Undulator Measurement/Pre-fiducialization - 19","2007-05-03","2007-05-08"]
["UN362_1970","Undulator Setup and Alignment @ CMM - 19","2007-05-09","2007-05-09"]
["UN362_1980","Undulator Fiducialization - 19","2007-05-10","2007-05-11"]
["UN362_1985","Undulator Ready for Assembly - 19","2007-05-14","2007-05-18"]
["UN362_1987","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 19","2007-10-08","2007-10-05"]
["UN362_1988","Assemble Cradle/Quad Supt/Movers - 19","2007-10-08","2007-10-08"]
["UN362_1989","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 19","2007-10-09","2007-10-10"]
["UN362_1990","Install Undulators on Cradle- 19","2007-10-11","2007-10-11"]
["UN362_1991","Prealign Vacuum Chamber - 19","2007-10-12","2007-10-12"]
["UN362_2000","Undulator Cradle RFI - 19","2007-10-15","2007-10-12"]
["UN362_2010","REQD:  Undulator Mag Assy - 20","2007-01-22","2007-01-19"]
["UN362_2020","Adjust to Temperature - 20","2007-01-22","2007-02-02"]
["UN362_2030","Undulator Setup and Alignment @ Test Bench - 20","2007-05-09","2007-05-09"]
["UN362_2040","Undulator Measurement and Set Gap - 20","2007-05-10","2007-05-11"]
["UN362_2060","Undulator Measurement/Pre-fiducialization - 20","2007-05-14","2007-05-17"]
["UN362_2070","Undulator Setup and Alignment @ CMM - 20","2007-05-18","2007-05-18"]
["UN362_2080","Undulator Fiducialization - 20","2007-05-21","2007-05-22"]
["UN362_2085","Undulator Ready for Assembly - 20","2007-05-23","2007-05-30"]
["UN362_2087","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 20","2007-11-28","2007-11-27"]
["UN362_2088","Assemble Cradle/Quad Supt/Movers - 20","2007-11-28","2007-11-28"]
["UN362_2089","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 20","2007-11-29","2007-11-30"]
["UN362_2090","Install Undulators on Cradle- 20","2007-12-03","2007-12-03"]
["UN362_2091","Prealign Vacuum Chamber - 20","2007-12-04","2007-12-04"]
["UN362_2100","Undulator Cradle RFI - 20","2007-12-05","2007-12-04"]
["UN362_2110","REQD:  Undulator Mag Assy - 21","2007-01-16","2007-01-12"]
["UN362_2120","Adjust to Temperature - 21","2007-01-16","2007-01-29"]
["UN362_2130","Undulator Setup and Alignment @ Test Bench - 21","2007-05-18","2007-05-18"]
["UN362_2140","Undulator Measurement and Set Gap - 21","2007-05-21","2007-05-22"]
["UN362_2160","Undulator Measurement/Pre-fiducialization - 21","2007-05-23","2007-05-29"]
["UN362_2170","Undulator Setup and Alignment @ CMM - 21","2007-05-30","2007-05-30"]
["UN362_2180","Undulator Fiducialization - 21","2007-05-31","2007-06-01"]
["UN362_2185","Undulator Ready for Assembly - 21","2007-06-04","2007-06-08"]
["UN362_2187","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 21","2007-11-28","2007-11-27"]
["UN362_2188","Assemble Cradle/Quad Supt/Movers - 21","2007-11-28","2007-11-28"]
["UN362_2189","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 21","2007-11-29","2007-11-30"]
["UN362_2190","Install Undulators on Cradle- 21","2007-12-03","2007-12-03"]
["UN362_2191","Prealign Vacuum Chamber - 21","2007-12-04","2007-12-04"]
["UN362_2200","Undulator Cradle RFI - 21","2007-12-05","2007-12-04"]
["UN362_2210","REQD:  Undulator Mag Assy - 22","2007-02-06","2007-02-05"]
["UN362_2220","Adjust to Temperature - 22","2007-02-06","2007-02-20"]
["UN362_2230","Undulator Setup and Alignment @ Test Bench - 22","2007-05-30","2007-05-30"]
["UN362_2240","Undulator Measurement and Set Gap - 22","2007-05-31","2007-06-01"]
["UN362_2260","Undulator Measurement/Pre-fiducialization - 22","2007-06-04","2007-06-07"]
["UN362_2270","Undulator Setup and Alignment @ CMM - 22","2007-06-08","2007-06-08"]
["UN362_2280","Undulator Fiducialization - 22","2007-06-11","2007-06-12"]
["UN362_2285","Undulator Ready for Assembly - 22","2007-06-13","2007-06-19"]
["UN362_2287","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 22","2007-11-28","2007-11-27"]
["UN362_2288","Assemble Cradle/Quad Supt/Movers - 22","2007-11-28","2007-11-28"]
["UN362_2289","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 22","2007-11-29","2007-11-30"]
["UN362_2290","Install Undulators on Cradle- 22","2007-12-03","2007-12-03"]
["UN362_2291","Prealign Vacuum Chamber - 22","2007-12-04","2007-12-04"]
["UN362_2300","Undulator Cradle RFI - 22","2007-12-05","2007-12-04"]
["UN362_2310","REQD:  Undulator Mag Assy - 23","2007-01-30","2007-01-29"]
["UN362_2320","Adjust to Temperature - 23","2007-01-30","2007-02-12"]
["UN362_2330","Undulator Setup and Alignment @ Test Bench - 23","2007-06-08","2007-06-08"]
["UN362_2340","Undulator Measurement and Set Gap - 23","2007-06-11","2007-06-12"]
["UN362_2360","Undulator Measurement/Pre-fiducialization - 23","2007-06-13","2007-06-18"]
["UN362_2370","Undulator Setup and Alignment @ CMM - 23","2007-06-19","2007-06-19"]
["UN362_2380","Undulator Fiducialization - 23","2007-06-20","2007-06-21"]
["UN362_2385","Undulator Ready for Assembly - 23","2007-06-22","2007-06-28"]
["UN362_2387","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 23","2007-11-28","2007-11-27"]
["UN362_2388","Assemble Cradle/Quad Supt/Movers - 23","2007-11-28","2007-11-28"]
["UN362_2389","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 23","2007-11-29","2007-11-30"]
["UN362_2390","Install Undulators on Cradle- 23","2007-12-03","2007-12-03"]
["UN362_2391","Prealign Vacuum Chamber - 23","2007-12-04","2007-12-04"]
["UN362_2400","Undulator Cradle RFI - 23","2007-12-05","2007-12-04"]
["UN362_2410","REQD:  Undulator Mag Assy - 24","2007-02-21","2007-02-20"]
["UN362_2420","Adjust to Temperature - 24","2007-02-21","2007-03-06"]
["UN362_2430","Undulator Setup and Alignment @ Test Bench - 24","2007-06-19","2007-06-19"]
["UN362_2440","Undulator Measurement and Set Gap - 24","2007-06-20","2007-06-21"]
["UN362_2460","Undulator Measurement/Pre-fiducialization - 24","2007-06-22","2007-06-27"]
["UN362_2470","Undulator Setup and Alignment @ CMM - 24","2007-06-28","2007-06-28"]
["UN362_2480","Undulator Fiducialization - 24","2007-06-29","2007-07-02"]
["UN362_2485","Undulator Ready for Assembly - 24","2007-07-03","2007-07-10"]
["UN362_2487","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 24","2008-01-04","2008-01-03"]
["UN362_2488","Assemble Cradle/Quad Supt/Movers - 24","2008-01-04","2008-01-04"]
["UN362_2489","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 24","2008-01-07","2008-01-08"]
["UN362_2490","Install Undulators on Cradle- 24","2008-01-09","2008-01-09"]
["UN362_2491","Prealign Vacuum Chamber - 24","2008-01-10","2008-01-10"]
["UN362_2500","Undulator Cradle RFI - 24","2008-01-11","2008-01-10"]
["UN362_2510","REQD:  Undulator Mag Assy - 25","2007-02-14","2007-02-13"]
["UN362_2520","Adjust to Temperature - 25","2007-02-14","2007-02-28"]
["UN362_2530","Undulator Setup and Alignment @ Test Bench - 25","2007-06-28","2007-06-28"]
["UN362_2540","Undulator Measurement and Set Gap - 25","2007-06-29","2007-07-02"]
["UN362_2560","Undulator Measurement/Pre-fiducialization - 25","2007-07-03","2007-07-09"]
["UN362_2570","Undulator Setup and Alignment @ CMM - 25","2007-07-10","2007-07-10"]
["UN362_2580","Undulator Fiducialization - 25","2007-07-11","2007-07-12"]
["UN362_2585","Undulator Ready for Assembly - 25","2007-07-13","2007-07-19"]
["UN362_2587","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 25","2008-01-04","2008-01-03"]
["UN362_2588","Assemble Cradle/Quad Supt/Movers - 25","2008-01-04","2008-01-04"]
["UN362_2589","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 25","2008-01-07","2008-01-08"]
["UN362_2590","Install Undulators on Cradle- 25","2008-01-09","2008-01-09"]
["UN362_2591","Prealign Vacuum Chamber - 25","2008-01-10","2008-01-10"]
["UN362_2600","Undulator Cradle RFI - 25","2008-01-11","2008-01-10"]
["UN362_2610","REQD:  Undulator Mag Assy - 26","2007-03-08","2007-03-07"]
["UN362_2620","Adjust to Temperature - 26","2007-03-08","2007-03-21"]
["UN362_2630","Undulator Setup and Alignment @ Test Bench - 26","2007-07-10","2007-07-10"]
["UN362_2640","Undulator Measurement and Set Gap - 26","2007-07-11","2007-07-12"]
["UN362_2660","Undulator Measurement/Pre-fiducialization - 26","2007-07-13","2007-07-18"]
["UN362_2670","Undulator Setup and Alignment @ CMM - 26","2007-07-19","2007-07-19"]
["UN362_2680","Undulator Fiducialization - 26","2007-07-20","2007-07-23"]
["UN362_2685","Undulator Ready for Assembly - 26","2007-07-24","2007-07-30"]
["UN362_2687","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 26","2008-01-04","2008-01-03"]
["UN362_2688","Assemble Cradle/Quad Supt/Movers - 26","2008-01-04","2008-01-04"]
["UN362_2689","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 26","2008-01-07","2008-01-08"]
["UN362_2690","Install Undulators on Cradle- 26","2008-01-09","2008-01-09"]
["UN362_2691","Prealign Vacuum Chamber - 26","2008-01-10","2008-01-10"]
["UN362_2700","Undulator Cradle RFI - 26","2008-01-11","2008-01-10"]
["UN362_2710","REQD:  Undulator Mag Assy - 27","2007-03-01","2007-02-28"]
["UN362_2720","Adjust to Temperature - 27","2007-03-01","2007-03-14"]
["UN362_2730","Undulator Setup and Alignment @ Test Bench - 27","2007-07-19","2007-07-19"]
["UN362_2740","Undulator Measurement and Set Gap - 27","2007-07-20","2007-07-23"]
["UN362_2760","Undulator Measurement/Pre-fiducialization - 27","2007-07-24","2007-07-27"]
["UN362_2770","Undulator Setup and Alignment @ CMM - 27","2007-07-30","2007-07-30"]
["UN362_2780","Undulator Fiducialization - 27","2007-07-31","2007-08-01"]
["UN362_2785","Undulator Ready for Assembly - 27","2007-08-02","2007-08-08"]
["UN362_2787","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 27","2008-02-01","2008-01-31"]
["UN362_2788","Assemble Cradle/Quad Supt/Movers - 27","2008-02-01","2008-02-01"]
["UN362_2789","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 27","2008-02-04","2008-02-05"]
["UN362_2790","Install Undulators on Cradle- 27","2008-02-06","2008-02-06"]
["UN362_2791","Prealign Vacuum Chamber - 27","2008-02-07","2008-02-07"]
["UN362_2800","Undulator Cradle RFI - 27","2008-02-08","2008-02-07"]
["UN362_2810","REQD:  Undulator Mag Assy - 28","2007-03-23","2007-03-22"]
["UN362_2820","Adjust to Temperature - 28","2007-03-23","2007-04-05"]
["UN362_2830","Undulator Setup and Alignment @ Test Bench - 28","2007-07-30","2007-07-30"]
["UN362_2840","Undulator Measurement and Set Gap - 28","2007-07-31","2007-08-01"]
["UN362_2860","Undulator Measurement/Pre-fiducialization - 28","2007-08-02","2007-08-07"]
["UN362_2870","Undulator Setup and Alignment @ CMM - 28","2007-08-08","2007-08-08"]
["UN362_2880","Undulator Fiducialization - 28","2007-08-09","2007-08-10"]
["UN362_2885","Undulator Ready for Assembly - 28","2007-08-13","2007-08-17"]
["UN362_2887","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 28","2008-02-01","2008-01-31"]
["UN362_2888","Assemble Cradle/Quad Supt/Movers - 28","2008-02-01","2008-02-01"]
["UN362_2889","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 28","2008-02-04","2008-02-05"]
["UN362_2890","Install Undulators on Cradle- 28","2008-02-06","2008-02-06"]
["UN362_2891","Prealign Vacuum Chamber - 28","2008-02-07","2008-02-07"]
["UN362_2900","Undulator Cradle RFI - 28","2008-02-08","2008-02-07"]
["UN362_2910","REQD:  Undulator Mag Assy - 29","2007-03-16","2007-03-15"]
["UN362_2920","Adjust to Temperature - 29","2007-03-16","2007-03-29"]
["UN362_2930","Undulator Setup and Alignment @ Test Bench - 29","2007-08-08","2007-08-08"]
["UN362_2940","Undulator Measurement and Set Gap - 29","2007-08-09","2007-08-10"]
["UN362_2960","Undulator Measurement/Pre-fiducialization - 29","2007-08-13","2007-08-16"]
["UN362_2970","Undulator Setup and Alignment @ CMM - 29","2007-08-17","2007-08-17"]
["UN362_2980","Undulator Fiducialization - 29","2007-08-20","2007-08-21"]
["UN362_2985","Undulator Ready for Assembly - 29","2007-08-22","2007-08-28"]
["UN362_2987","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 29","2008-02-29","2008-02-28"]
["UN362_2988","Assemble Cradle/Quad Supt/Movers - 29","2008-02-29","2008-02-29"]
["UN362_2989","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 29","2008-03-03","2008-03-04"]
["UN362_2990","Install Undulators on Cradle- 29","2008-03-05","2008-03-05"]
["UN362_2991","Prealign Vacuum Chamber - 29","2008-03-06","2008-03-06"]
["UN362_3000","Undulator Cradle RFI - 29","2008-03-07","2008-03-06"]
["UN362_3010","REQD:  Undulator Mag Assy - 30","2007-04-09","2007-04-06"]
["UN362_3020","Adjust to Temperature - 30","2007-04-09","2007-04-20"]
["UN362_3030","Undulator Setup and Alignment @ Test Bench - 30","2007-08-17","2007-08-17"]
["UN362_3040","Undulator Measurement and Set Gap - 30","2007-08-20","2007-08-21"]
["UN362_3060","Undulator Measurement/Pre-fiducialization - 30","2007-08-22","2007-08-27"]
["UN362_3070","Undulator Setup and Alignment @ CMM - 30","2007-08-28","2007-08-28"]
["UN362_3080","Undulator Fiducialization - 30","2007-08-29","2007-08-30"]
["UN362_3085","Undulator Ready for Assembly - 30","2007-08-31","2007-09-07"]
["UN362_3087","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 30","2008-02-29","2008-02-28"]
["UN362_3088","Assemble Cradle/Quad Supt/Movers - 30","2008-02-29","2008-02-29"]
["UN362_3089","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 30","2008-03-03","2008-03-04"]
["UN362_3090","Install Undulators on Cradle- 30","2008-03-05","2008-03-05"]
["UN362_3091","Prealign Vacuum Chamber - 30","2008-03-06","2008-03-06"]
["UN362_3100","Undulator Cradle RFI - 30","2008-03-07","2008-03-06"]
["UN362_3110","REQD:  Undulator Mag Assy - 31","2007-04-02","2007-03-30"]
["UN362_3120","Adjust to Temperature - 31","2007-04-02","2007-04-13"]
["UN362_3130","Undulator Setup and Alignment @ Test Bench - 31","2007-08-28","2007-08-28"]
["UN362_3140","Undulator Measurement and Set Gap - 31","2007-08-29","2007-08-30"]
["UN362_3160","Undulator Measurement/Pre-fiducialization - 31","2007-08-31","2007-09-06"]
["UN362_3170","Undulator Setup and Alignment @ CMM - 31","2007-09-07","2007-09-07"]
["UN362_3180","Undulator Fiducialization - 31","2007-09-10","2007-09-11"]
["UN362_3185","Undulator Ready for Assembly - 31","2007-09-12","2007-09-18"]
["UN362_3187","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 31","2008-02-29","2008-02-28"]
["UN362_3188","Assemble Cradle/Quad Supt/Movers - 31","2008-02-29","2008-02-29"]
["UN362_3189","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 31","2008-03-03","2008-03-04"]
["UN362_3190","Install Undulators on Cradle- 31","2008-03-05","2008-03-05"]
["UN362_3191","Prealign Vacuum Chamber - 31","2008-03-06","2008-03-06"]
["UN362_3200","Undulator Cradle RFI - 31","2008-03-07","2008-03-06"]
["UN362_3210","REQD:  Undulator Mag Assy - 32","2007-04-24","2007-04-23"]
["UN362_3220","Adjust to Temperature - 32","2007-04-24","2007-05-07"]
["UN362_3230","Undulator Setup and Alignment @ Test Bench - 32","2007-09-07","2007-09-07"]
["UN362_3240","Undulator Measurement and Set Gap - 32","2007-09-10","2007-09-11"]
["UN362_3260","Undulator Measurement/Pre-fiducialization - 32","2007-09-12","2007-09-17"]
["UN362_3270","Undulator Setup and Alignment @ CMM - 32","2007-09-18","2007-09-18"]
["UN362_3280","Undulator Fiducialization - 32","2007-09-19","2007-09-20"]
["UN362_3285","Undulator Ready for Assembly - 32","2007-09-21","2007-09-27"]
["UN362_3287","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 32","2008-03-03","2008-02-29"]
["UN362_3288","Assemble Cradle/Quad Supt/Movers - 32","2008-03-03","2008-03-03"]
["UN362_3289","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 32","2008-03-04","2008-03-05"]
["UN362_3290","Install Undulators on Cradle- 32","2008-03-06","2008-03-06"]
["UN362_3291","Prealign Vacuum Chamber - 32","2008-03-07","2008-03-07"]
["UN362_3300","Undulator Cradle RFI - 32","2008-03-10","2008-03-07"]
["UN362_3306","HLS Systems Design-Part II","2005-07-01","2005-09-29",null,"2005-07-01","2005-09-29"]
["UN362_3310","REQD:  Undulator Mag Assy - 33","2007-04-17","2007-04-16"]
["UN362_3320","Adjust to Temperature - 33","2007-04-17","2007-04-30"]
["UN362_3330","Undulator Setup and Alignment @ Test Bench - 33","2007-09-18","2007-09-18"]
["UN362_3340","Undulator Measurement and Set Gap - 33","2007-09-19","2007-09-20"]
["UN362_3360","Undulator Measurement/Pre-fiducialization - 33","2007-09-21","2007-09-26"]
["UN362_3370","Undulator Setup and Alignment @ CMM - 33","2007-09-27","2007-09-27"]
["UN362_3380","Undulator Fiducialization - 33","2007-09-28","2007-10-01"]
["UN362_3385","Undulator Ready for Assembly - 33","2007-10-02","2007-10-08"]
["UN362_3387","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 33","2008-03-03","2008-02-29"]
["UN362_3388","Assemble Cradle/Quad Supt/Movers - 33","2008-03-03","2008-03-03"]
["UN362_3389","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 33","2008-03-04","2008-03-05"]
["UN362_3390","Install Undulators on Cradle- 33","2008-03-06","2008-03-06"]
["UN362_3391","Prealign Vacuum Chamber - 33","2008-03-07","2008-03-07"]
["UN362_3400","Undulator Cradle RFI - 33","2008-03-10","2008-03-07"]
["UN362_3410","REQD:  Undulator Mag Assy - 34","2007-05-09","2007-05-08"]
["UN362_3420","Adjust to Temperature - 34","2007-05-09","2007-05-22"]
["UN362_3430","Undulator Setup and Alignment @ Test Bench - 34","2007-09-27","2007-09-27"]
["UN362_3440","Undulator Measurement and Set Gap - 34","2007-09-28","2007-10-01"]
["UN362_3460","Undulator Measurement/Pre-fiducialization - 34","2007-10-02","2007-10-05"]
["UN362_3470","Undulator Setup and Alignment @ CMM - 34","2007-10-08","2007-10-08"]
["UN362_3480","Undulator Fiducialization - 34","2007-10-09","2007-10-10"]
["UN362_3485","Undulator Ready for Assembly - 34","2007-10-11","2007-10-17"]
["UN362_3487","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 34","2008-10-07","2008-10-06"]
["UN362_3488","Assemble Cradle/Quad Supt/Movers - 34","2008-10-07","2008-10-07"]
["UN362_3489","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 34","2008-10-08","2008-10-09"]
["UN362_3490","Install Undulators on Cradle- 34","2008-10-10","2008-10-10"]
["UN362_3491","Prealign Vacuum Chamber - 34","2008-10-13","2008-10-13"]
["UN362_3500","Undulator Cradle RFI - 34","2008-10-14","2008-10-13"]
["UN362_3510","REQD:  Undulator Mag Assy - 35","2007-05-02","2007-05-01"]
["UN362_3520","Adjust to Temperature - 35","2007-05-02","2007-05-15"]
["UN362_3530","Undulator Setup and Alignment @ Test Bench - 35","2007-10-08","2007-10-08"]
["UN362_3540","Undulator Measurement and Set Gap - 35","2007-10-09","2007-10-10"]
["UN362_3560","Undulator Measurement/Pre-fiducialization - 35","2007-10-11","2007-10-16"]
["UN362_3570","Undulator Setup and Alignment @ CMM - 35","2007-10-17","2007-10-17"]
["UN362_3580","Undulator Fiducialization - 35","2007-10-18","2007-10-19"]
["UN362_3585","Undulator Ready for Assembly - 35","2007-10-22","2007-10-26"]
["UN362_3587","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 35","2008-10-09","2008-10-08"]
["UN362_3588","Assemble Cradle/Quad Supt/Movers - 35","2008-10-09","2008-10-09"]
["UN362_3589","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 35","2008-10-10","2008-10-13"]
["UN362_3590","Install Undulators on Cradle- 35","2008-10-14","2008-10-14"]
["UN362_3591","Prealign Vacuum Chamber - 35","2008-10-15","2008-10-15"]
["UN362_3600","Undulator Cradle RFI - 35","2008-10-16","2008-10-15"]
["UN362_3610","REQD:  Undulator Mag Assy - 36","2007-05-24","2007-05-23"]
["UN362_3620","Adjust to Temperature - 36","2007-05-24","2007-06-07"]
["UN362_3630","Undulator Setup and Alignment @ Test Bench - 36","2007-10-17","2007-10-17"]
["UN362_3640","Undulator Measurement and Set Gap - 36","2007-10-18","2007-10-19"]
["UN362_3660","Undulator Measurement/Pre-fiducialization - 36","2007-10-22","2007-10-25"]
["UN362_3670","Undulator Setup and Alignment @ CMM - 36","2007-10-26","2007-10-26"]
["UN362_3680","Undulator Fiducialization - 36","2007-10-29","2007-10-30"]
["UN362_3685","Undulator Ready for Assembly - 36","2007-10-31","2007-11-06"]
["UN362_3687","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 36","2008-10-13","2008-10-10"]
["UN362_3688","Assemble Cradle/Quad Supt/Movers - 36","2008-10-13","2008-10-13"]
["UN362_3689","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 36","2008-10-14","2008-10-15"]
["UN362_3690","Install Undulators on Cradle- 36","2008-10-16","2008-10-16"]
["UN362_3691","Prealign Vacuum Chamber - 36","2008-10-17","2008-10-17"]
["UN362_3700","Undulator Cradle RFI - 36","2008-10-20","2008-10-17"]
["UN362_3710","REQD:  Undulator Mag Assy - 37","2007-05-17","2007-05-16"]
["UN362_3720","Adjust to Temperature - 37","2007-05-17","2007-05-31"]
["UN362_3730","Undulator Setup and Alignment @ Test Bench - 37","2007-10-26","2007-10-26"]
["UN362_3740","Undulator Measurement and Set Gap - 37","2007-10-29","2007-10-30"]
["UN362_3760","Undulator Measurement/Pre-fiducialization - 37","2007-10-31","2007-11-05"]
["UN362_3770","Undulator Setup and Alignment @ CMM - 37","2007-11-06","2007-11-06"]
["UN362_3780","Undulator Fiducialization - 37","2007-11-07","2007-11-08"]
["UN362_3785","Undulator Ready for Assembly - 37","2007-11-09","2007-11-15"]
["UN362_3787","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 37","2008-10-15","2008-10-14"]
["UN362_3788","Assemble Cradle/Quad Supt/Movers - 37","2008-10-15","2008-10-15"]
["UN362_3789","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 37","2008-10-16","2008-10-17"]
["UN362_3790","Install Undulators on Cradle- 37","2008-10-20","2008-10-20"]
["UN362_3791","Prealign Vacuum Chamber - 37","2008-10-21","2008-10-21"]
["UN362_3800","Undulator Cradle RFI - 37","2008-10-22","2008-10-21"]
["UN362_3810","REQD:  Undulator Mag Assy - 38","2007-06-11","2007-06-08"]
["UN362_3820","Adjust to Temperature - 38","2007-06-11","2007-06-22"]
["UN362_3830","Undulator Setup and Alignment @ Test Bench - 38","2007-11-06","2007-11-06"]
["UN362_3840","Undulator Measurement and Set Gap - 38","2007-11-07","2007-11-08"]
["UN362_3860","Undulator Measurement/Pre-fiducialization - 38","2007-11-09","2007-11-14"]
["UN362_3870","Undulator Setup and Alignment @ CMM - 38","2007-11-15","2007-11-15"]
["UN362_3880","Undulator Fiducialization - 38","2007-11-16","2007-11-19"]
["UN362_3885","Undulator Ready for Assembly - 38","2007-11-20","2007-11-28"]
["UN362_3887","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 38","2008-10-17","2008-10-16"]
["UN362_3888","Assemble Cradle/Quad Supt/Movers - 38","2008-10-17","2008-10-17"]
["UN362_3889","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 38","2008-10-20","2008-10-21"]
["UN362_3890","Install Undulators on Cradle- 38","2008-10-22","2008-10-22"]
["UN362_3891","Prealign Vacuum Chamber - 38","2008-10-23","2008-10-23"]
["UN362_3900","Undulator Cradle RFI - 38","2008-10-24","2008-10-23"]
["UN362_3910","REQD:  Undulator Mag Assy - 39","2007-06-04","2007-06-01"]
["UN362_3920","Adjust to Temperature - 39","2007-06-04","2007-06-15"]
["UN362_3930","Undulator Setup and Alignment @ Test Bench - 39","2007-11-15","2007-11-15"]
["UN362_3940","Undulator Measurement and Set Gap - 39","2007-11-16","2007-11-19"]
["UN362_3960","Undulator Measurement/Pre-fiducialization - 39","2007-11-20","2007-11-27"]
["UN362_3970","Undulator Setup and Alignment @ CMM - 39","2007-11-28","2007-11-28"]
["UN362_3980","Undulator Fiducialization - 39","2007-11-29","2007-11-30"]
["UN362_3985","Undulator Ready for Assembly - 39","2007-12-03","2007-12-07"]
["UN362_3987","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 39","2008-10-21","2008-10-20"]
["UN362_3988","Assemble Cradle/Quad Supt/Movers - 39","2008-10-21","2008-10-21"]
["UN362_3989","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 39","2008-10-22","2008-10-23"]
["UN362_3990","Install Undulators on Cradle- 39","2008-10-24","2008-10-24"]
["UN362_3991","Prealign Vacuum Chamber - 39","2008-10-27","2008-10-27"]
["UN362_4000","Undulator Cradle RFI - 39","2008-10-28","2008-10-27"]
["UN362_4010","REQD:  Undulator Mag Assy - 40","2007-06-26","2007-06-25"]
["UN362_4020","Adjust to Temperature - 40","2007-06-26","2007-07-10"]
["UN362_4030","Undulator Setup and Alignment @ Test Bench - 40","2007-11-28","2007-11-28"]
["UN362_4040","Undulator Measurement and Set Gap - 40","2007-11-29","2007-11-30"]
["UN362_4060","Undulator Measurement/Pre-fiducialization - 40","2007-12-03","2007-12-06"]
["UN362_4070","Undulator Setup and Alignment @ CMM - 40","2007-12-07","2007-12-07"]
["UN362_4080","Undulator Fiducialization - 40","2007-12-10","2007-12-11"]
["UN362_4085","Undulator Ready for Assembly - 40","2007-12-12","2008-01-03"]
["UN362_4087","REQD:  Quad/Vac Chmbr/BPM/Cher Det - 40","2008-10-23","2008-10-22"]
["UN362_4088","Assemble Cradle/Quad Supt/Movers - 40","2008-10-23","2008-10-23"]
["UN362_4089","Assemble Cradle/Vac Chmbr/BPM/Quad/Cher Det - 40","2008-10-24","2008-10-27"]
["UN362_4090","Install Undulators on Cradle- 40","2008-10-28","2008-10-28"]
["UN362_4091","Prealign Vacuum Chamber - 40","2008-10-29","2008-10-29"]
["UN362_4100","Undulator Cradle RFI - 40","2008-10-30","2008-10-29"]
["UN36_00010","Design Quad Fidcuialization System","2005-05-02","2005-06-30",null,"2005-05-02","2005-06-30"]
["UN36_00011","Revise Design for Electro Magnets","2005-06-01","2005-09-30",null,"2005-06-01","2005-09-30"]
["UN36_00020","Procure Quad Fiducialization System","2005-05-02","2005-05-31",null,"2005-05-02","2005-05-31"]
["UN36_00021","Procure Hardware for Electro Magnets","2005-07-01","2006-07-03",null,"2005-07-01"]
["UN36_00022","Develop System Software","2005-06-01","2006-06-01",null,"2005-06-01"]
["UN36_00023","Fabricate Hardware","2005-07-01","2006-08-31",null,"2005-07-01"]
["UN36_00030","Install and Test Quad Fiducialization System","2006-04-04","2006-05-01"]
["UN36_00032","Commission Quad Fiducialization System","2006-07-05","2006-08-28"]
["UN36_00040","Quad Fiducialization System Complete","2006-08-29","2006-08-28"]
["UN36_00050","Design Undulator Fiducialization System","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN36_00051","Develop Fiducialization Fixture","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN36_00052","Release RFP - Undulator Fiducialization System","2005-05-02","2005-05-02",null,"2005-05-02","2005-05-02"]
["UN36_00053","Prototype Fiducialization Fixture","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN36_00054","Vendor Prep Prop - Undulator Fiducialization Sys","2005-05-03","2005-06-30",null,"2005-05-03","2005-06-30"]
["UN36_00055","Develop System Software","2005-07-01","2005-08-31",null,"2005-07-01","2005-08-31"]
["UN36_00056","AWARD: Undulator Fiducialization System","2005-09-01","2005-09-01",null,"2005-09-01","2005-09-01"]
["UN36_00060","Procure Undulator Fiducialization System","2005-08-02","2006-04-24",null,"2005-08-02"]
["UN36_00062","RCV: Undulator Fiducialization System","2006-04-25","2006-04-24"]
["UN36_00070","Install and Test Undulator Fiducialization Sys","2006-04-25","2006-05-22"]
["UN36_00080","Undulator Fiducialization System Complete","2006-05-23","2006-05-22"]
["UN36_00090","Design Quad Strength and Field Quality","2005-05-02","2005-05-31",null,"2005-05-02","2005-05-31"]
["UN36_00091","Revise Design for Electro Magnets","2005-06-01","2005-09-30",null,"2005-06-01","2005-09-30"]
["UN36_00092","Develop System Software","2005-09-01","2005-09-30",null,"2005-09-01","2005-09-30"]
["UN36_00100","Procure Quad Strength and Field Quality","2005-06-01","2006-07-03",null,"2005-06-01"]
["UN36_00101","Procure Hardware for Electro Magnets","2005-09-01","2006-07-03",null,"2005-09-01"]
["UN36_00102","Fabricate Hardware","2005-07-01","2006-07-03",null,"2005-07-01"]
["UN36_00110","Install and Test Quad Strength and Field Quality","2006-07-05","2006-08-01"]
["UN36_00112","Commission Quad Strength and Field System","2006-07-05","2006-08-28"]
["UN36_00120","Quad Strength and Field Quality Complete","2006-08-29","2006-08-28"]
["UN36_00136","AWARD: Undulator Test Stand","2005-07-01","2005-07-01",null,"2005-07-01","2005-07-01"]
["UN36_00140","Procure Undulator Test Stand","2005-07-05","2006-06-01",null,"2005-07-05"]
["UN36_00141","Design Undulator Supports and Movers","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN36_00142","RCV: Undulator Test Stand","2006-06-02","2006-06-01"]
["UN36_00143","Procure Undulator Supports and Movers","2005-06-01","2005-09-30",null,"2005-06-01","2005-09-30"]
["UN36_00145","Develop System Software","2005-06-01","2006-07-03",null,"2005-06-01"]
["UN36_00146","Develop Temperature System","2005-08-29","2006-09-01",null,"2005-08-29"]
["UN36_00150","Install and Test Undulator Test Stand","2006-06-02","2006-06-29"]
["UN36_00160","Undulator Test Stand Complete","2006-06-30","2006-06-29"]
["UN36_00170","Design Hall Probe Calibration System","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN36_00180","Procure Hall Probe Calibration System","2005-05-06","2005-08-31",null,"2005-05-06","2005-08-31"]
["UN36_00190","Install and Test Hall Probe Calibration System","2006-04-04","2006-05-01"]
["UN36_00191","Commission Hall Probe Calibration System","2006-05-02","2006-05-26"]
["UN36_00192","Develop System Software","2005-07-01","2006-08-31",null,"2005-07-01"]
["UN36_00193","Fabricate Hardware","2005-09-01","2006-09-01",null,"2005-09-01"]
["UN36_00200","Hall Probe Calibration System Complete","2006-05-30","2006-05-26"]
["UN36_00210","Design Undulator Test Stand Proto","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN36_00220","Procure Undulator Test Stand Proto","2005-06-01","2005-09-30",null,"2005-06-01","2005-09-30"]
["UN36_00221","Procure Undulator Supports and Movers","2005-10-03","2006-05-04",null,"2005-10-03"]
["UN36_00230","Install and Test Undulator Test Stand Proto","2006-07-03","2006-07-28"]
["UN36_00240","Undulator Test Stand Proto Complete","2006-07-31","2006-07-28"]
["UN36_00250","Design Undulator Handling","2005-10-03","2006-02-17",null,"2005-10-03"]
["UN36_00251","Adapt Design for Cradle Concept","2006-02-01","2006-03-02"]
["UN36_00260","Procure Undulator Handling","2006-03-03","2006-05-16"]
["UN36_00265","Procure Forklift","2005-11-07","2006-02-16",null,"2005-11-07"]
["UN36_00270","Install and Test Undulator Handling","2006-04-18","2006-06-13"]
["UN36_00280","Undulator Handling Complete","2006-06-14","2006-06-13"]
["UN36_00290","MMF Ready to Magnetic Measure/Fiducialize","2006-08-29","2006-08-28"]
["UN36_00370","Procure Fiducialization and Mag Meas Hardware","2006-05-01","2006-07-25"]
["UN36_00390","Fiducialization Measurements - BPM","2006-08-29","2007-03-06"]
["UN36_00400","Data Evaluation - BPM","2006-08-29","2007-03-06"]
["UN36_00510","Data Evaluation - Correctors","2006-08-29","2007-03-06"]
["UN36_00550","Magnetic Measurements - Correctors","2006-08-29","2007-03-06"]
["UN36_00560","Fiducialization Measurements - Vacuum Chamber","2006-08-29","2007-03-06"]
["UN36_00570","Data Evaluation - Vacuum Chamber","2006-08-29","2007-03-06"]
["UN36_00600","Fiducialization Measurements - Photon Diagnostic","2006-08-29","2007-03-06"]
["UN36_00610","Data Evaluation - Photon Diagnostic","2006-08-29","2007-03-06"]
["UN36_00620","F/MM for Vacuum and Diag Complete","2007-03-07","2007-03-06"]
["UN36_02000","Quad Mag Measure/Fiducialization Facility Read","2006-08-29","2006-08-28"]
["UN36_02010","Magnetic Field Measurement #01 Article at SLAC","2007-06-20","2007-06-21"]
["UN36_02020","Quadrupole #01 Fiducialization","2007-06-22","2007-06-25"]
["UN36_02030","Magnetic Field Measurement #02 Article at SLAC","2007-06-26","2007-06-27"]
["UN36_02040","Quadrupole #02 Fiducialization","2007-06-28","2007-06-29"]
["UN36_02050","Magnetic Field Measurement #03 Article at SLAC","2007-07-02","2007-07-03"]
["UN36_02060","Quadrupole #03 Fiducialization","2007-07-05","2007-07-06"]
["UN36_02070","Magnetic Field Measurement #04 Article at SLAC","2007-07-09","2007-07-10"]
["UN36_02080","Quadrupole #04 Fiducialization","2007-07-11","2007-07-12"]
["UN36_02085","Magnetic Field Measurement #05 Article at SLAC","2007-07-13","2007-07-16"]
["UN36_02090","Quadrupole #05 Fiducialization","2007-07-17","2007-07-18"]
["UN36_02100","Magnetic Field Measurement #06 Article at SLAC","2007-07-19","2007-07-20"]
["UN36_02110","Quadrupole #06 Fiducialization","2007-07-23","2007-07-24"]
["UN36_02120","Magnetic Field Measurement #07 Article at SLAC","2007-07-25","2007-07-26"]
["UN36_02130","Quadrupole #07 Fiducialization","2007-07-27","2007-07-30"]
["UN36_02140","Magnetic Field Measurement #08 Article at SLAC","2007-07-31","2007-08-01"]
["UN36_02150","Quadrupole #08 Fiducialization","2007-08-02","2007-08-03"]
["UN36_02160","Magnetic Field Measurement #09 Article at SLAC","2007-08-06","2007-08-07"]
["UN36_02170","Quadrupole #09 Fiducialization","2007-08-08","2007-08-09"]
["UN36_02180","Magnetic Field Measurement #10 Article at SLAC","2007-08-10","2007-08-13"]
["UN36_02190","Quadrupole #10 Fiducialization","2007-08-14","2007-08-15"]
["UN36_02200","Magnetic Field Measurement #11 Article at SLAC","2007-08-16","2007-08-17"]
["UN36_02210","Quadrupole #11 Fiducialization","2007-08-20","2007-08-21"]
["UN36_02220","Magnetic Field Measurement #12 Article at SLAC","2007-08-22","2007-08-23"]
["UN36_02230","Quadrupole #12 Fiducialization","2007-08-24","2007-08-27"]
["UN36_02240","Magnetic Field Measurement #13 Article at SLAC","2007-08-28","2007-08-29"]
["UN36_02250","Quadrupole #13 Fiducialization","2007-08-30","2007-08-31"]
["UN36_02260","Magnetic Field Measurement #14 Article at SLAC","2007-09-04","2007-09-05"]
["UN36_02270","Quadrupole #14 Fiducialization","2007-09-06","2007-09-07"]
["UN36_02280","Magnetic Field Measurement #15 Article at SLAC","2007-09-10","2007-09-11"]
["UN36_02290","Quadrupole #15 Fiducialization","2007-09-12","2007-09-13"]
["UN36_02300","Magnetic Field Measurement #16 Article at SLAC","2007-09-14","2007-09-17"]
["UN36_02310","Quadrupole #16 Fiducialization","2007-09-18","2007-09-19"]
["UN36_02320","Magnetic Field Measurement #17 Article at SLAC","2007-09-20","2007-09-21"]
["UN36_02330","Quadrupole #17 Fiducialization","2007-09-24","2007-09-25"]
["UN36_02340","Magnetic Field Measurement #18 Article at SLAC","2007-09-26","2007-09-27"]
["UN36_02350","Quadrupole #18 Fiducialization","2007-09-28","2007-10-01"]
["UN36_02360","Magnetic Field Measurement #19 Article at SLAC","2007-10-02","2007-10-03"]
["UN36_02370","Quadrupole #19 Fiducialization","2007-10-04","2007-10-05"]
["UN36_02375","Magnetic Field Measurement #20 Article at SLAC","2007-10-08","2007-10-09"]
["UN36_02380","Quadrupole #20 Fiducialization","2007-10-10","2007-10-11"]
["UN36_02390","Magnetic Field Measurement #21 Article at SLAC","2007-10-12","2007-10-15"]
["UN36_02400","Quadrupole #21 Fiducialization","2007-10-16","2007-10-17"]
["UN36_02410","Magnetic Field Measurement #22 Article at SLAC","2007-10-18","2007-10-19"]
["UN36_02420","Quadrupole #22 Fiducialization","2007-10-22","2007-10-23"]
["UN36_02430","Magnetic Field Measurement #23 Article at SLAC","2007-10-24","2007-10-25"]
["UN36_02440","Quadrupole #23 Fiducialization","2007-10-26","2007-10-29"]
["UN36_02450","Magnetic Field Measurement #24 Article at SLAC","2007-10-30","2007-10-31"]
["UN36_02460","Quadrupole #24 Fiducialization","2007-11-01","2007-11-02"]
["UN36_02470","Magnetic Field Measurement #25 Article at SLAC","2007-11-05","2007-11-06"]
["UN36_02480","Quadrupole #25 Fiducialization","2007-11-07","2007-11-08"]
["UN36_02490","Magnetic Field Measurement #26 Article at SLAC","2007-11-09","2007-11-12"]
["UN36_02500","Quadrupole #26 Fiducialization","2007-11-13","2007-11-14"]
["UN36_02510","Magnetic Field Measurement #27 Article at SLAC","2007-11-15","2007-11-16"]
["UN36_02520","Quadrupole #27 Fiducialization","2007-11-19","2007-11-20"]
["UN36_02530","Magnetic Field Measurement #28 Article at SLAC","2007-11-21","2007-11-26"]
["UN36_02540","Quadrupole #28 Fiducialization","2007-11-27","2007-11-28"]
["UN36_02550","Magnetic Field Measurement #29 Article at SLAC","2007-11-29","2007-11-30"]
["UN36_02560","Quadrupole #29 Fiducialization","2007-12-03","2007-12-04"]
["UN36_02570","Magnetic Field Measurement #30 Article at SLAC","2007-12-05","2007-12-06"]
["UN36_02580","Quadrupole #30 Fiducialization","2007-12-07","2007-12-10"]
["UN36_02590","Magnetic Field Measurement #31 Article at SLAC","2007-12-11","2007-12-12"]
["UN36_02600","Quadrupole #31 Fiducialization","2007-12-13","2007-12-14"]
["UN36_02610","Magnetic Field Measurement #32 Article at SLAC","2008-01-02","2008-01-03"]
["UN36_02620","Quadrupole #32 Fiducialization","2008-01-04","2008-01-07"]
["UN36_02630","Magnetic Field Measurement #33 Article at SLAC","2008-01-08","2008-01-09"]
["UN36_02640","Quadrupole #33 Fiducialization","2008-01-10","2008-01-11"]
["UN36_02650","Magnetic Field Measurement #34 Article at SLAC","2008-10-01","2008-10-02"]
["UN36_02660","Quadrupole #34 Fiducialization","2008-10-03","2008-10-06"]
["UN36_02670","Magnetic Field Measurement #35 Article at SLAC","2008-10-01","2008-10-02"]
["UN36_02680","Quadrupole #35 Fiducialization","2008-10-07","2008-10-08"]
["UN36_02690","Magnetic Field Measurement #36 Article at SLAC","2008-10-03","2008-10-06"]
["UN36_02700","Quadrupole #36 Fiducialization","2008-10-09","2008-10-10"]
["UN36_02710","Magnetic Field Measurement #37 Article at SLAC","2008-10-07","2008-10-08"]
["UN36_02715","Quadrupole #37 Fiducialization","2008-10-13","2008-10-14"]
["UN36_02718","Magnetic Field Measurement #38 Article at SLAC","2008-10-09","2008-10-10"]
["UN36_02720","Quadrupole #38 Fiducialization","2008-10-15","2008-10-16"]
["UN36_02730","Magnetic Field Measurement #39 Article at SLAC","2008-10-13","2008-10-14"]
["UN36_02740","Quadrupole #39 Fiducialization","2008-10-17","2008-10-20"]
["UN36_02750","Magnetic Field Measurement #40 Article at SLAC","2008-10-15","2008-10-16"]
["UN36_02760","Quadrupole #40 Fiducialization","2008-10-21","2008-10-22"]
["UN38_00010","Produce Final Fixed Support Design","2005-07-01","2005-11-11",null,"2005-07-01","2005-11-11"]
["UN38_00013","Fixed Support Development","2005-06-01","2005-08-10",null,"2005-06-01","2005-08-10"]
["UN38_00014","Design/Analyze Prototype & Test","2005-07-01","2006-04-12",null,"2005-07-01"]
["UN38_00015","Define Supt/Mover Interfaces","2005-07-01","2006-02-10",null,"2005-07-01"]
["UN38_00016","Procurement/Acceptance/Vendor Mgmt","2006-04-13","2006-08-18"]
["UN38_00017","Define Interfaces w/Conventional Facilities","2005-08-01","2006-02-28",null,"2005-08-01"]
["UN38_00018","Define Interfaces w/Survey Alignment","2005-07-01","2006-02-28",null,"2005-07-01"]
["UN38_00019","Define Interfaces w/Controls/Monitor","2005-07-01","2006-02-28",null,"2005-07-01"]
["UN38_00020","Perform Thermal Analysis","2005-07-01","2005-07-01",null,"2005-07-01","2005-07-01"]
["UN38_00025","Procure Prototype Components","2005-07-01","2006-02-13",null,"2005-07-01"]
["UN38_00030","Fab/Assemble Prototype Components","2005-09-16","2006-02-13",null,"2005-09-16"]
["UN38_00035","Thermal and Vibration Testing","2005-08-01","2006-02-28",null,"2005-08-01"]
["UN38_00040","Perform Vibration Analysis","2005-09-26","2006-02-28",null,"2005-09-26"]
["UN38_00045","Design/Integration of Earthquake Brace","2005-09-01","2006-02-28",null,"2005-09-01"]
["UN38_00047","Integrated PRO-E Model of FS/SM/UM","2005-09-12","2006-02-28",null,"2005-09-12"]
["UN38_00048","Analyze Prototype Test Results","2005-09-12","2006-02-28",null,"2005-09-12"]
["UN38_00049","Write Report","2006-03-01","2006-03-27"]
["UN38_00051","Prepare for IDR","2005-11-28","2006-01-31",null,"2005-11-28","2006-01-31"]
["UN38_00052","Independent Design Review","2006-01-12","2006-01-12",null,"2006-01-12","2006-01-12"]
["UN38_00053","Modify Design for Integrated System Test","2006-01-23","2006-02-17",null,"2006-01-23"]
["UN38_00054","Procure Fixed Supports for Integrated System Tst","2005-12-14","2006-02-03",null,"2005-12-14"]
["UN38_00055","Assy of Fixed Supports at Integrated System Tst","2006-02-06","2006-02-10"]
["UN38_00056","Write SOW for Pillar,Top/Bottom Plates & Insultn","2006-02-06","2006-02-24"]
["UN38_00057","Prepare for FDR","2006-02-27","2006-03-03"]
["UN38_00058","Final Design Review (Integrated with Supt/Mover)","2006-06-12","2006-06-12"]
["UN38_00059","Incorporate Comments from FDR","2006-06-13","2006-06-26"]
["UN38_00060","Release RFP for Pillar/Plates/Insulation","2006-06-27","2006-06-27"]
["UN38_00061","Vendor Prep Prop. for Pillar/Plates/Insulation","2006-06-28","2006-07-19"]
["UN38_00062","Evaluate Prop. for Pillar/Plates/Insulation","2006-07-20","2006-08-02"]
["UN38_00063","AWARD: Fixed Supports","2006-08-03","2006-08-03"]
["UN38_00064","Vendor Fab/Assemble Fixed Supports","2006-08-04","2006-11-01"]
["UN38_00065","RCV: Fixed Supports","2006-11-02","2006-11-01"]
["UN38_00067","Integrate Temperature DAQ with FS/SM/UM","2005-07-01","2006-02-28",null,"2005-07-01"]
["UN38_00068","Specify Temperature DAQ System","2006-03-01","2006-03-03"]
["UN38_00100","Design CAM Transfer Template","2005-07-01","2006-02-28",null,"2005-07-01"]
["UN38_00270","Procure Thermistors","2006-02-01","2006-03-01"]
["UN38_00280","Procure Cabling","2006-02-01","2006-03-01"]
["UN38_00290","Procure Readout Electronics","2006-02-01","2006-03-29"]
["UN38_00300","Thermometry Ready for Assembly","2006-03-30","2006-03-29"]
["UN38_00380","Procure Earthquake Bracing","2006-02-01","2006-03-29"]
["UN38_00390","Write Alignment Software","2006-04-26","2006-06-07"]
["UN38_00400","Fixed Support Controls Ready for Stabilization","2006-06-08","2006-06-07"]
["UN38_00410","REQD: Alignment Monitoring specifications","2006-04-26","2006-04-25"]
["UN42_00230","Receive  Prd Un Cham Specs from Undulator Group","2006-06-01","2006-06-07"]
["UN42_00240","Prelim Design Prd Un Chamber","2006-10-04","2006-10-24"]
["UN42_00250","Prelim Design Review Prd Un Chamber","2006-10-25","2006-10-27"]
["UN42_00260","Final Design Prd Un Chamber","2006-10-30","2006-11-14"]
["UN42_00270","Design Complete Prd Un Chamber","2006-11-15","2006-11-14"]
["UN42_00280","Bid Package- Prd Un Chamber","2006-11-15","2006-11-17"]
["UN42_00330","Bid Process Prd Un Chamber","2006-11-20","2007-01-03"]
["UN42_00331","Evalute Bid Prd Un Chamber","2007-01-04","2007-01-08"]
["UN42_00340","AWARD: Production Undulator Chamber (34)","2007-01-09","2007-01-10"]
["UN42_00341","AWARD: Production Undulator Chamber (7)","2007-01-09","2007-01-10"]
["UN42_00345","AWARD: Production Undulator Chamber (34) Support","2007-01-09","2007-01-10"]
["UN42_00365","AWARD: Chamber Supports (31) Support","2007-01-09","2007-01-10"]
["UN42_00390","AWARD: Complete Prd Un Chamber","2007-01-11","2007-01-10"]
["UN42_00400","Rec: First Lot Production Undulator Chamber (10)","2007-01-11","2007-03-07"]
["UN42_00410","QA First Lot Prd Un Chamber","2007-03-08","2007-03-14"]
["UN42_00420","Fabrication of First Lot Prd Un Chamber","2007-03-15","2007-04-25"]
["UN42_00421","Assembly Test Prd Un Cham (10)","2007-04-05","2007-05-02"]
["UN42_00422","Clean  Prd Un Cham (10)","2007-05-03","2007-05-14"]
["UN42_00423","Bake Prd Un Cham (10)","2007-05-15","2007-06-05"]
["UN42_00424","Prep Chamber Assy & Support for Shipment (10)","2007-06-06","2007-06-12"]
["UN42_00425","Pack Chamber Assembly & Supt for Shipping (10)","2007-06-13","2007-06-19"]
["UN42_00426","Ship  Prd Un Chamber to SLAC (10)","2007-06-20","2007-06-19"]
["UN42_00427","Transmit  Prd Un Cham Design & Drawings to SLAC","2007-06-20","2007-06-26"]
["UN42_00428","RFI: Undulator Vacuum Chamber Assembly (10)","2007-06-27","2007-06-26"]
["UN42_00430","Approve Continuation of Production Prd Un Cham","2007-03-15","2007-03-16"]
["UN42_00440","RCV: Remain Lot Production Undulator Chamb (24)","2007-03-19","2007-05-25"]
["UN42_00441","Rec: Production Undulator Chamb (7)","2007-03-19","2007-05-25"]
["UN42_00450","QA Production Lot Prd Un Chamber","2007-05-29","2007-06-11"]
["UN42_00460","Fabrication of Rem Production Lot Prd Un Chamber","2007-06-12","2007-07-24"]
["UN42_00470","Approve Production Lot Prd Un Chamber","2007-07-03","2007-07-05"]
["UN42_00480","Prelim Design Chamber Sup","2006-10-20","2006-11-16"]
["UN42_00490","Mechanical Analysis","2006-10-18","2006-10-27"]
["UN42_00500","Final Design Chamber Sup","2006-10-30","2006-11-10"]
["UN42_00510","Design Complete Chamber Sup","2006-11-13","2006-11-10"]
["UN42_00520","Bid Package-Chamber Supports","2006-11-13","2006-11-17"]
["UN42_00550","Bid Process Chamber Supports","2006-11-20","2007-01-03"]
["UN42_00551","Evaluate Bid - Chamber Supports","2007-01-04","2007-01-08"]
["UN42_00560","AWARD: Chamber Supports (31)","2007-01-09","2007-01-10"]
["UN42_00561","Award: Chamber Supports","2007-01-09","2007-01-10"]
["UN42_00590","AWARD: Complete Chamber Supports","2007-01-11","2007-01-10"]
["UN42_00600","RCV  Chamber Supports (31)","2007-01-11","2007-03-07"]
["UN42_00601","RCV: Chamber Supports","2007-01-11","2007-03-09"]
["UN42_00610","Quality Assurance Chamber Sup","2007-03-12","2007-03-27"]
["UN42_00640","Assembly Test Prd Un Cham (24)","2007-07-06","2007-08-02"]
["UN42_00650","Clean  Prd Un Cham (24)","2007-08-03","2007-08-14"]
["UN42_00660","Bake Prd Un Cham (24)","2007-08-15","2007-09-05"]
["UN42_00670","Prep Chamber Assembly & Supt for Shipment (24)","2007-09-06","2007-09-12"]
["UN42_00680","Pack Chamber Assembly & Supt for Shipping(24)","2007-09-13","2007-09-19"]
["UN42_00690","Ship  Prd Un Chamber to SLAC (24)","2007-09-20","2007-09-19"]
["UN42_00702","RFI: Undulator Vacuum Chamber Assembly (24)","2007-10-04","2007-10-03"]
["UN42_00710","Develop Installation Plan Prd Un Chamber","2006-11-15","2006-11-30"]
["UN42_00720","Review Installation Plan Prd Un Chamber","2006-12-01","2006-12-07"]
["UN42_00730","Prd Un Cham Assembly Arrive at SLAC (10)","2007-06-27","2007-07-11"]
["UN42_00732","Prd Un Cham Assembly Arrive at SLAC (24)","2007-09-20","2007-10-03"]
["UN42_00810","Commission Un Cham","2006-10-03","2006-10-09"]
["UN42_D220","Perform welding tests","2005-06-13","2006-01-30",null,"2005-06-13","2006-01-30"]
["UN42_D222","Final determination of metal surface finish meas","2006-05-02","2006-07-31"]
["UN42_D223","Final determination of welding process","2005-09-26","2006-03-20",null,"2005-09-26"]
["UN42_D227","Mechanical analysis of chamber","2005-05-02","2005-11-11",null,"2005-05-02","2005-11-11"]
["UN42_D235","Test samples for AC conductivity","2005-05-02","2005-07-29",null,"2005-05-02","2005-07-29"]
["UN42_D236","Collect results AC conductivity","2005-05-02","2005-08-31",null,"2005-05-02","2005-08-31"]
["UN42_D237","Write study report AC conductivity","2005-09-01","2005-11-10",null,"2005-09-01","2005-11-10"]
["UN42_D238","Submit study report AC conductivity","2005-11-11","2005-11-10",null,"2005-11-11","2005-11-10"]
["UN42_D240","Create extrusion conceptual design","2005-05-02","2005-08-31",null,"2005-05-02","2005-08-31"]
["UN42_D241","Create box conceptual design","2005-05-02","2005-05-20",null,"2005-05-02","2005-05-20"]
["UN42_D257","Preliminary prototype design UN chamber","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN42_D258","Prototype UN chamber tooling design","2005-11-01","2006-02-28",null,"2005-11-01"]
["UN42_D259","Prototype design review UN chamber","2005-12-08","2006-01-30",null,"2005-12-08","2006-01-30"]
["UN42_D260","Prototype final design UN chamber","2005-09-26","2006-01-30",null,"2005-09-26","2006-01-30"]
["UN42_D261","Prototype design complete","2006-01-31","2006-01-30",null,"2006-01-31","2006-01-30"]
["UN42_D262","Bid process prototype UN chamber","2006-01-16","2006-02-17",null,"2006-01-16"]
["UN42_D263","Bid process prototype UN chamber tooling","2006-02-01","2006-03-07"]
["UN42_D264","Evaluate bid prototype UN chamber","2006-03-08","2006-03-14"]
["UN42_D265","Procure Prototype undulator chamber (2)","2006-03-15","2006-03-17"]
["UN42_D266","Procure Prototype UN chamber tooling","2006-03-15","2006-03-17"]
["UN42_D267","RCV Parts prototype UN chamber","2006-03-20","2006-06-12"]
["UN42_D268","Quality assurance prototype UN chamber","2006-06-13","2006-06-26"]
["UN42_D269","Procure Polish parts","2006-08-01","2006-08-28"]
["UN42_D270","Fabrication of prototype chamber weldment","2006-08-29","2006-09-19"]
["UN42_D271","Measurement and test prototype UN chamber","2006-09-20","2006-10-24"]
["UN42_D272","Prototype UN chamber testing complete","2006-10-25","2006-10-24"]
["UN42_DP219","Fabricate Welding Samples and Tooling","2005-05-02","2005-12-30",null,"2005-05-02","2005-12-30"]
["UN42_DR210","Literature Search - Surface Mesurement","2005-06-14","2005-12-30",null,"2005-06-14","2005-12-30"]
["UN42_DR212","Procure surface measurement equipment","2006-01-03","2006-02-13",null,"2006-01-03"]
["UN42_DR213","Fabricate surface measuring equipment","2006-01-24","2006-03-06",null,"2006-01-24"]
["UN42_DR214","Assemble surface measuring equipment","2006-03-07","2006-03-20"]
["UN42_DR215","Initial surface test","2006-03-21","2006-04-03"]
["UN42_DR216","Test confirmation of surface measurement","2006-04-04","2006-05-01"]
["UN42_DR218","Design weld tooling","2006-01-31","2006-03-09",null,"2006-01-31"]
["UN42_DR219","Stainless Steel Permeability Testing","2005-05-23","2005-07-29",null,"2005-05-23","2005-07-29"]
["UN42_DR221","Final determination of metal polishing","2006-05-02","2006-07-31"]
["UN42_DR233","Fabricate AC conductivity samples","2005-05-02","2005-06-06",null,"2005-05-02","2005-06-06"]
["UN43_00070","Bid Package-Ag Plated RF Finger Prtp Bel Mod","2006-02-15","2006-02-17"]
["UN43_00080","Bid Package-Rh Plated Stub Prtp Bel Mod","2006-02-15","2006-02-17"]
["UN43_00090","Bid Package-Tubes Prtp Bel Mod","2006-02-15","2006-02-17"]
["UN43_00100","Bid Package- Prtp Bellows Module","2006-01-27","2006-01-30",null,"2006-01-27","2006-01-30"]
["UN43_00120","Bid Process Prtp Bel Mod","2006-02-20","2006-03-24"]
["UN43_00130","Procure Ag Plated RF Finger Prtp Bel Mod","2006-03-27","2006-03-28"]
["UN43_00140","Procure Rh Plated Stub Prtp Bel Mod","2006-03-27","2006-03-28"]
["UN43_00150","Procure Tubes Prtp Bel Mod","2006-03-27","2006-03-28"]
["UN43_00160","Procure Bellows Prtp Bel Mod","2006-03-27","2006-03-28"]
["UN43_00180","Prototype Bel Mod Award Complete","2006-03-29","2006-03-28"]
["UN43_00190","RCV: Bellows  Prtp Bel Mod","2006-03-29","2006-05-09"]
["UN43_00200","Quality Assurance Prtp Bel Mod","2006-05-10","2006-05-16"]
["UN43_00201","Test Equipment Fab & Assy","2006-02-21","2006-04-03"]
["UN43_00220","Measurement and Test Prtp Bel Mod","2006-05-17","2006-05-31"]
["UN43_00230","Review and Report Prtp Bel Mod","2006-06-01","2006-06-07"]
["UN43_00240","Prototype Bel Mod Testing Complete","2006-06-08","2006-06-07"]
["UN43_00241","Proto Prelimin Design","2005-07-22","2006-01-30",null,"2005-07-22","2006-01-30"]
["UN43_00242","Study of Lubrication Coating","2005-05-02","2005-12-30",null,"2005-05-02","2005-12-30"]
["UN43_00243","Proto Mech. Anal.","2005-06-15","2005-12-22",null,"2005-06-15","2005-12-22"]
["UN43_00244","Evaluation of Lubrication Coating","2005-12-30","2006-02-10",null,"2005-12-30"]
["UN43_00245","Test Tooling Design","2005-11-01","2006-02-28",null,"2005-11-01"]
["UN43_00246","Proto Review","2005-12-20","2006-01-30",null,"2005-12-20","2006-01-30"]
["UN43_00247","Proto Final Design","2006-01-31","2006-02-20",null,"2006-01-31"]
["UN43_00248","Write Bellow Fab Spec","2006-01-30","2006-02-14",null,"2006-01-30"]
["UN43_00250","Prelim Standard Bellows Design","2006-06-08","2006-06-28"]
["UN43_00260","Bellows Physics Review","2006-06-29","2006-06-30"]
["UN43_00270","Final Standard Bellows Design","2006-07-03","2006-07-10"]
["UN43_00280","Design Complete FDR Std Bel Mod","2006-07-11","2006-07-10"]
["UN43_00283","Final Design Review Std Bel Mod","2006-07-11","2006-07-12"]
["UN43_00290","Bid Package-Standard Bellows Module","2006-07-13","2006-07-17"]
["UN43_00340","Bid Process Std Bel Mod","2006-07-18","2006-08-21"]
["UN43_00342","Evaluate Bid Std Bel Mod","2006-08-22","2006-08-23"]
["UN43_00350","AWARD: Standard Bellows Module (47)","2006-08-24","2006-08-25"]
["UN43_00355","Standard Bellows Module (47) Support","2006-08-24","2006-08-25"]
["UN43_00360","AWARD: Standard Bellows Module (4)","2006-10-03","2006-10-04"]
["UN43_00400","AWARD: Complete Std Bel Module","2006-08-28","2006-08-25"]
["UN43_00410","Receive First Lot Standard Bellows Module (4)","2006-08-28","2006-10-09"]
["UN43_00420","QA First Lot Std Bel Mod","2006-10-10","2006-10-19"]
["UN43_00440","Approve Continuation of Production Std Bel Mod","2006-10-20","2006-10-23"]
["UN43_00450","Receive Remain Prod Lot Std Bellows Module (43","2006-10-24","2006-12-20"]
["UN43_00451","Receive Standard Bellows Module (4)","2006-10-24","2007-01-04"]
["UN43_00460","QA Production Lot Std Bel Mod","2006-12-21","2007-01-18"]
["UN43_00500","Assembly Test Std Bel Mod","2007-01-19","2007-02-01"]
["UN43_00510","Clean Std Bel Mod","2007-02-02","2007-02-13"]
["UN43_00520","Bake Std Bel Mod","2007-04-30","2007-05-04"]
["UN43_00530","Prepare Standard Bellows for Shipment","2007-05-07","2007-05-11"]
["UN43_00540","Pack Standard Bellows for Shipping","2007-05-14","2007-05-18"]
["UN43_00550","Ship  Std Bel Mod to Slac","2007-05-21","2007-05-18"]
["UN43_00560","Transmit  Std Bel Mod Design & Drawings to SLA","2007-05-21","2007-05-25"]
["UN43_00562","RFI: Beam-Line Bellows Module Assembly","2007-05-29","2007-05-25"]
["UN43_00570","Standard Bellows Arrive at SLAC","2007-10-04","2007-10-17"]
["UN43_00620","Commission Std Bel Mod","2007-01-05","2007-01-11"]
["UN43_CM000","Commission Fixed Supports","2006-10-03","2007-02-09"]
["UN43_SPR00","RCV: Fixed Support Spares","2006-10-03","2006-12-13"]
["UN44_00100","Modify Design Stand-in Chamber","2005-09-01","2005-11-15",null,"2005-09-01","2005-11-15"]
["UN44_00110","Shops to Quote Chamber","2005-12-01","2006-01-30",null,"2005-12-01","2006-01-30"]
["UN44_00120","Shops to Fab Chamber","2006-01-31","2006-04-27",null,"2006-01-31"]
["UN44_00200","Design BFW-Cher-Vac Chamber","2005-11-16","2006-02-10",null,"2005-11-16"]
["UN44_00210","Get Quote on BFW-Ch-Vac Cham","2006-01-31","2006-02-16",null,"2006-01-31"]
["UN44_00220","Purchase BFW-Ch-Vac Cham","2006-01-23","2006-03-21",null,"2006-01-23"]
["UN44_00300","Select Ion Pump","2005-10-17","2005-10-21",null,"2005-10-17","2005-10-21"]
["UN44_00310","Get Quote on Ion Pump (contd.)","2005-11-01","2005-11-14",null,"2005-11-01","2005-11-14"]
["UN44_00320","Purchase Pump","2005-11-15","2006-02-07",null,"2005-11-15"]
["UN44_00400","Design Ion Pump Support","2005-12-01","2006-02-10",null,"2005-12-01"]
["UN44_00410","Shops to Quote on Ion Pump Support","2006-02-13","2006-02-17"]
["UN44_00420","Shops to Fab Pump Support","2006-02-20","2006-04-03"]
["UN44_00500","Design BFW-Cher-Vac Cham Support","2005-12-06","2006-02-03",null,"2005-12-06"]
["UN44_00510","Shops to quote BFW-Ch-Vac Cham Support","2006-01-23","2006-02-28",null,"2006-01-23"]
["UN44_00520","Shops to Fab BFW-Ch-Vac Cham Support","2006-01-23","2006-02-10",null,"2006-01-23"]
["UN44_00580","Commission Std Col","2006-10-03","2006-10-09"]
["UN45_00020","SDB Design","2005-12-01","2006-09-22",null,"2005-12-01"]
["UN45_00030","Mechanical Analysis SDB","2006-09-25","2006-10-03"]
["UN45_00050","Final SDB Design","2006-10-04","2006-10-17"]
["UN45_00052","Final SDB Design Review","2006-10-18","2006-10-24"]
["UN45_00060","SDB Design Complete","2006-10-25","2006-10-24"]
["UN45_00100","Ion Pump Bid Pkg","2006-10-25","2006-10-27"]
["UN45_00110","Ion Pump Power Supply Bid Pkg","2006-10-25","2006-10-27"]
["UN45_00120","Ion Pump Cable Bid Package","2006-10-25","2006-10-27"]
["UN45_00140","Chamber Support Bid Package","2006-10-25","2006-10-31"]
["UN45_00150","Pump Support Bid Package","2006-10-25","2006-10-31"]
["UN45_00160","Bid Process SDB","2006-11-01","2006-12-07"]
["UN45_00161","Evaluate Bids:  SDB","2006-12-08","2006-12-12"]
["UN45_00170","AWARD: Chamber Weldment Assembly (23)","2006-12-08","2006-12-11"]
["UN45_00171","AWARD: Chamber Weldment Assembly (2)","2006-12-08","2006-12-11"]
["UN45_00175","AWARD: Chamber Weldment Assembly (23) Support","2006-12-08","2006-12-11"]
["UN45_00190","AWARD: Pump Manifold (23)","2006-12-13","2006-12-14"]
["UN45_00191","AWARD: Pump Manifold","2006-12-13","2006-12-14"]
["UN45_00195","AWARD: Pump Manifold (23) Support","2006-12-13","2006-12-14"]
["UN45_00200","AWARD: Ion Pump (23)","2006-12-08","2006-12-11"]
["UN45_00201","AWARD: Ion Pump (1)","2006-12-08","2006-12-11"]
["UN45_00205","AWARD: Ion Pump (23) Support","2006-12-08","2006-12-11"]
["UN45_00210","AWARD: Ion Pump Power Supply (12)","2006-12-08","2006-12-11"]
["UN45_00211","AWARD: Ion Pump Power Supply","2006-12-08","2006-12-11"]
["UN45_00215","AWARD: Ion Pump Power Supply (12) Support","2006-12-08","2006-12-11"]
["UN45_00220","AWARD:  Ion Pump Cable (23)","2006-12-08","2006-12-11"]
["UN45_00221","AWARD: Ion Pump Cable (1)","2006-12-08","2006-12-11"]
["UN45_00225","AWARD:  Ion Pump Cable (23) Support","2006-12-08","2006-12-11"]
["UN45_00240","AWARD: Chamber Support (23)","2006-12-08","2006-12-12"]
["UN45_00241","AWARD: Chamber Support (1)","2006-12-08","2006-12-12"]
["UN45_00245","AWARD: Chamber Support (23) Sppt","2006-12-08","2006-12-12"]
["UN45_00250","AWARD: Pump Support (23)","2006-12-08","2006-12-12"]
["UN45_00251","AWARD: Pump Support (1)","2006-12-08","2006-12-12"]
["UN45_00255","AWARD: Pump Support (23) Sppt","2006-12-08","2006-12-12"]
["UN45_00260","AWARD: Short Diagnostic Break Assembly","2006-12-15","2006-12-18"]
["UN45_00320","Rec: SDB Chamber Weldment Assembly","2006-12-19","2007-02-06"]
["UN45_00321","Rec: SDB Chamber Weldment Assembly","2007-01-02","2007-02-13"]
["UN45_00322","Rec: SDB Pump Manifold","2006-12-19","2007-02-06"]
["UN45_00323","Rec: SDB Pump Manifold","2007-01-02","2007-02-13"]
["UN45_00324","Rec: SDB Ion Pump","2006-12-19","2007-02-06"]
["UN45_00325","Rec: SDB Ion Pump","2007-01-02","2007-02-13"]
["UN45_00326","Rec: SDB Ion Pump Power Supply","2006-12-19","2007-02-06"]
["UN45_00327","Rec: SDB Ion Pump Power Supply","2007-01-02","2007-02-13"]
["UN45_00328","Rec: SDB Ion Pump Cable","2006-12-19","2007-02-06"]
["UN45_00329","Rec: SDB Ion Pump Cable","2007-01-02","2007-02-13"]
["UN45_00330","Rec: SDB Chamber Supports","2006-12-19","2007-02-06"]
["UN45_00331","Rec: SDB Chamber Supports","2007-01-02","2007-02-13"]
["UN45_00332","Rec: SDB Pump Supports","2006-12-19","2007-02-06"]
["UN45_00333","Rec: SDB Pump Supports","2007-01-02","2007-02-13"]
["UN45_00335","Rec: SDB Pump Weld","2006-12-19","2007-02-06"]
["UN45_00336","Rec: SDB Ion Pump Support","2006-12-19","2007-02-06"]
["UN45_00339","QA Production Lot SDB","2007-02-07","2007-02-20"]
["UN45_00340","Approve Production Lot SDB","2007-02-21","2007-02-23"]
["UN45_00350","Clean SDB","2007-02-26","2007-03-02"]
["UN45_00360","Bake SDB","2007-04-30","2007-05-04"]
["UN45_00390","Prepare Short Diagnostic Break for Shipment","2007-05-07","2007-05-11"]
["UN45_00400","Pack Short Diagnostic Break for Shipping","2007-05-14","2007-05-18"]
["UN45_00410","Ship to Slac SDB","2007-05-21","2007-05-18"]
["UN45_00420","Transmit  SDB Design & Drawings to SLAC","2007-05-21","2007-05-25"]
["UN45_00422","RFI: Short Diagnostic Break Assembly","2007-05-29","2007-05-25"]
["UN45_00430","Develop Installation Plan SDB","2007-05-21","2007-06-04"]
["UN45_00440","Review installation Plan  SDB","2007-06-05","2007-06-11"]
["UN45_00450","Short Diagnostic Break Assembly Arrive at SLAC","2007-10-04","2007-10-17"]
["UN45_00460","Install Short Break Section Components","2007-10-18","2007-10-24"]
["UN45_00530","Commission - Short Diag Break Assy","2007-10-25","2007-10-31"]
["UN45_D180","Perform literature search Cavity BPM","2005-05-02","2005-08-19",null,"2005-05-02","2005-08-19"]
["UN45_D181","Develop conceptual design of BPM","2005-06-01","2005-08-31",null,"2005-06-01","2005-08-31"]
["UN45_D182","BPM conceptual design complete","2005-09-01","2005-08-31",null,"2005-09-01","2005-08-31"]
["UN462_0000","Equipment Available at SLAC & Und B.O.","2007-07-30","2007-07-27"]
["UN462_0005","Install Racks in Alcoves/End Stations","2007-07-30","2007-08-03"]
["UN462_0010","Install Cables from Racks to Tunnel Locations","2007-08-06","2007-08-10"]
["UN462_0015","Terminate Cables","2007-08-13","2007-08-24"]
["UN462_0020","Install Rack Mount Equipment","2007-08-06","2007-08-10"]
["UN462_0100","Connect Devices @ Undulator #33","2008-04-18","2008-04-18"]
["UN462_0105","Test Devices @ Undulator #33","2008-04-21","2008-04-21"]
["UN462_0110","Connect Devices @ Undulator #32","2008-04-14","2008-04-14"]
["UN462_0115","Test Devices @ Undulator #32","2008-04-15","2008-04-15"]
["UN462_0120","Connect Devices @ Undulator #31","2008-04-08","2008-04-08"]
["UN462_0125","Test Devices @ Undulator #31","2008-04-09","2008-04-09"]
["UN462_0130","Connect Devices @ Undulator #30","2008-04-02","2008-04-02"]
["UN462_0135","Test Devices @ Undulator #30","2008-04-03","2008-04-03"]
["UN462_0140","Connect Devices @ Undulator #29","2008-03-27","2008-03-27"]
["UN462_0145","Test Devices @ Undulator #29","2008-03-28","2008-03-28"]
["UN462_0150","Connect Devices @ Undulator #28","2008-03-21","2008-03-21"]
["UN462_0155","Test Devices @ Undulator #28","2008-03-24","2008-03-24"]
["UN462_0160","Connect Devices @ Undulator #27","2008-03-17","2008-03-17"]
["UN462_0165","Test Devices @ Undulator #27","2008-03-18","2008-03-18"]
["UN462_0170","Connect Devices @ Undulator #26","2008-03-11","2008-03-11"]
["UN462_0175","Test Devices @ Undulator #26","2008-03-12","2008-03-12"]
["UN462_0180","Connect Devices @ Undulator #25","2008-03-05","2008-03-05"]
["UN462_0185","Test Devices @ Undulator #25","2008-03-06","2008-03-06"]
["UN462_0190","Connect Devices @ Undulator #24","2008-02-28","2008-02-28"]
["UN462_0195","Test Devices @ Undulator #24","2008-02-29","2008-02-29"]
["UN462_0200","Connect Devices @ Undulator #23","2008-02-22","2008-02-22"]
["UN462_0205","Test Devices @ Undulator #23","2008-02-25","2008-02-25"]
["UN462_0210","Connect Devices @ Undulator #22","2008-02-15","2008-02-15"]
["UN462_0215","Test Devices @ Undulator #22","2008-02-18","2008-02-18"]
["UN462_0220","Connect Devices @ Undulator #21","2008-02-11","2008-02-11"]
["UN462_0225","Test Devices @ Undulator #21","2008-02-12","2008-02-12"]
["UN462_0230","Connect Devices @ Undulator #20","2008-02-05","2008-02-05"]
["UN462_0235","Test Devices @ Undulator #20","2008-02-06","2008-02-06"]
["UN462_0240","Connect Devices @ Undulator #19","2008-01-30","2008-01-30"]
["UN462_0245","Test Devices @ Undulator #19","2008-01-31","2008-01-31"]
["UN462_0250","Connect Devices @ Undulator #18","2008-01-24","2008-01-24"]
["UN462_0255","Test Devices @ Undulator #18","2008-01-25","2008-01-25"]
["UN462_0260","Connect Devices @ Undulator #17","2008-01-17","2008-01-17"]
["UN462_0265","Test Devices @ Undulator #17","2008-01-18","2008-01-18"]
["UN462_0270","Connect Devices @ Undulator #16","2008-01-11","2008-01-11"]
["UN462_0275","Test Devices @ Undulator #16","2008-01-14","2008-01-14"]
["UN462_0280","Connect Devices @ Undulator #15","2008-01-07","2008-01-07"]
["UN462_0285","Test Devices @ Undulator #15","2008-01-08","2008-01-08"]
["UN462_0290","Connect Devices @ Undulator #14","2007-12-14","2007-12-14"]
["UN462_0295","Test Devices @ Undulator #14","2007-12-17","2007-12-17"]
["UN462_0300","Connect Devices @ Undulator #13","2007-12-10","2007-12-10"]
["UN462_0305","Test Devices @ Undulator #13","2007-12-11","2007-12-11"]
["UN462_0310","Connect Devices @ Undulator #12","2007-12-04","2007-12-04"]
["UN462_0315","Test Devices @ Undulator #12","2007-12-05","2007-12-05"]
["UN462_0320","Connect Devices @ Undulator #11","2007-11-28","2007-11-28"]
["UN462_0325","Test Devices @ Undulator #11","2007-11-29","2007-11-29"]
["UN462_0330","Connect Devices @ Undulator #10","2007-11-20","2007-11-20"]
["UN462_0335","Test Devices @ Undulator #10","2007-11-21","2007-11-21"]
["UN462_0340","Connect Devices @ Undulator #9","2007-11-14","2007-11-14"]
["UN462_0345","Test Devices @ Undulator #9","2007-11-15","2007-11-15"]
["UN462_0350","Connect Devices @ Undulator #8","2007-11-08","2007-11-08"]
["UN462_0355","Test Devices @ Undulator #8","2007-11-09","2007-11-09"]
["UN462_0360","Connect Devices @ Undulator #7","2007-11-02","2007-11-02"]
["UN462_0365","Test Devices @ Undulator #7","2007-11-05","2007-11-05"]
["UN462_0370","Connect Devices @ Undulator #6","2007-10-29","2007-10-29"]
["UN462_0375","Test Devices @ Undulator #6","2007-10-30","2007-10-30"]
["UN462_0380","Connect Devices @ Undulator #5","2007-10-23","2007-10-23"]
["UN462_0385","Test Devices @ Undulator #5","2007-10-24","2007-10-24"]
["UN462_0390","Connect Devices @ Undulator #4","2007-10-17","2007-10-17"]
["UN462_0395","Test Devices @ Undulator #4","2007-10-18","2007-10-18"]
["UN462_0400","Connect Devices @ Undulator #3","2007-10-11","2007-10-11"]
["UN462_0405","Test Devices @ Undulator #3","2007-10-12","2007-10-12"]
["UN462_0410","Connect Devices @ Undulator #2","2007-10-08","2007-10-08"]
["UN462_0415","Test Devices @ Undulator #2","2007-10-09","2007-10-09"]
["UN462_0420","Connect Devices @ Undulator #1","2007-10-08","2007-10-08"]
["UN462_0425","Test Devices @ Undulator #1","2007-10-09","2007-10-09"]
["UN462_0430","Connect Devices @ Short Break Section","2007-10-25","2007-10-25"]
["UN462_0435","Test Devices @ Short Break Section","2007-10-26","2007-10-26"]
["UN462_0440","Connect Devices @ Long Break Section","2007-11-01","2007-11-01"]
["UN462_0445","Test Devices @ Long Break Section","2007-11-02","2007-11-02"]
["UN462_0450","Connect Devices @ Entrance Section","2007-09-06","2007-09-06"]
["UN462_0455","Test Devices @ Entrance Section","2007-09-07","2007-09-07"]
["UN462_0460","Connect Devices @ Exit Section","2007-11-05","2007-11-05"]
["UN462_0465","Test Devices @ Exit Section","2007-11-06","2007-11-06"]
["UN462_0500","Test Devices Under Vacuum","2008-05-13","2008-05-13"]
["UN46_00012","LDB Design","2005-12-01","2006-09-14",null,"2005-12-01"]
["UN46_00030","Mechanical Analysis LDB","2006-09-15","2006-09-28"]
["UN46_00050","LDB Final Design","2006-09-29","2006-10-12"]
["UN46_00052","Final LDB Design Review","2006-10-13","2006-10-19"]
["UN46_00060","LDB Design Complete","2006-10-20","2006-10-19"]
["UN46_00200","Bid Process LDB","2006-10-20","2006-11-27"]
["UN46_00202","Evaluate Bid LDB","2006-11-28","2006-11-29"]
["UN46_00205","AWARD: LDB Valve (11)","2006-11-30","2006-12-01"]
["UN46_00206","AWARD: LDB Valve (2)","2006-11-30","2006-12-01"]
["UN46_00210","AWARD: LDB Chamber Weldment Assembly","2006-11-30","2006-12-01"]
["UN46_00211","AWARD: LBD Chamber Weldment Assembly (1)","2006-11-30","2006-12-01"]
["UN46_00215","AWARD: LDB Valve (11) Sppt","2006-11-30","2006-12-01"]
["UN46_00217","AWARD: LDB Chamber Weldment Assembly Sppt","2006-11-30","2006-12-01"]
["UN46_00240","AWARD: LDB Pump Manifold","2006-11-30","2006-12-01"]
["UN46_00241","AWARD: LDB Pump Manifold (1)","2006-11-30","2006-12-01"]
["UN46_00245","AWARD: LDB Pump Manifold Sppt","2006-11-30","2006-12-01"]
["UN46_00250","AWARD: LDB Ion Pump","2006-11-30","2006-12-01"]
["UN46_00251","AWARD: LDB Ion Pump (1)","2006-11-30","2006-12-01"]
["UN46_00255","AWARD: LDB Ion Pump Sppt","2006-11-30","2006-12-01"]
["UN46_00310","AWARD: LDB Chamber Support","2006-11-30","2006-12-01"]
["UN46_00311","AWARD: LDB Chamber Support (1)","2006-12-04","2006-12-05"]
["UN46_00315","AWARD: LDB Chamber Support Sppt","2006-11-30","2006-12-01"]
["UN46_00320","AWARD: LDB Ion Pump Support","2006-11-30","2006-12-01"]
["UN46_00321","AWARD: LDB Ion Pump Support (1)","2006-11-30","2006-12-01"]
["UN46_00325","AWARD: LDB Ion Pump Support Sppt","2006-11-30","2006-12-01"]
["UN46_00340","AWARD: Long Diagnostic Break Assembly","2006-12-04","2006-12-01"]
["UN46_00350","Rec: LDB Valve (2)","2006-12-04","2007-02-05"]
["UN46_00351","Rec: LDB Valve (2)","2006-12-04","2007-02-13"]
["UN46_00400","Rec: LDB Chamber Weldment Assembly","2006-12-04","2007-02-05"]
["UN46_00401","Rec: LDB Chamber Weldment Assembly (1)","2006-12-04","2007-02-13"]
["UN46_00402","Rec: LDB Pump Manifold (11)","2006-12-04","2007-02-05"]
["UN46_00403","Rec: LDB Pump Manifold (1)","2006-12-04","2007-02-13"]
["UN46_00404","Rec: LDB Ion Pump (11)","2006-12-04","2007-02-05"]
["UN46_00405","Rec: LDB Ion Pump (1)","2006-12-04","2007-02-13"]
["UN46_00406","Rec: LDB Chamber Support (11)","2006-12-04","2007-02-05"]
["UN46_00407","Rec: LDB Chamber Support (1)","2006-12-06","2007-02-15"]
["UN46_00408","Rec: LDB Ion Pump Support (11)","2006-12-04","2007-02-05"]
["UN46_00409","Rec: LDB Ion Pump Support (1)","2006-12-04","2007-02-13"]
["UN46_00410","QA Production Lot LDB","2007-02-06","2007-02-19"]
["UN46_00420","Approve Production Lot LDB","2007-02-20","2007-02-22"]
["UN46_00430","Clean LDB","2007-02-23","2007-03-06"]
["UN46_00440","Bake LDB","2007-04-30","2007-05-04"]
["UN46_00470","Prepare Long Diagnostic Break for Shipment","2007-05-07","2007-05-11"]
["UN46_00480","Pack Long Diagnostic Break for Shipping","2007-05-14","2007-05-18"]
["UN46_00490","Ship to Slac LDB","2007-05-21","2007-05-18"]
["UN46_00500","Transmit Design and Drawings to SLAC","2007-05-21","2007-05-25"]
["UN46_00502","RFI: Long Diagnostic Break Assembly","2007-05-29","2007-05-25"]
["UN46_00510","Develop Installation Plan LDB","2007-05-21","2007-05-30"]
["UN46_00520","Review installation Plan LDB","2007-05-31","2007-06-06"]
["UN46_00530","Long Diagnostic Break Assembly Arrive at SLAC","2007-10-04","2007-10-17"]
["UN46_00540","Install Long Break Section Components","2007-10-18","2007-10-31"]
["UN46_00610","Commission - Long Diag Break Assy","2007-11-01","2007-11-07"]
["UN47_00010","Specification Ent Sec","2006-07-11","2006-07-24"]
["UN47_00020","Prelim Design  Ent Sec","2006-07-25","2006-08-28"]
["UN47_00030","Mechanical Analysis  Ent Sec","2006-08-29","2006-09-12"]
["UN47_00040","Prelim Design Review  Ent Sec","2006-09-13","2006-09-19"]
["UN47_00050","Final Design  Ent Sec","2006-09-20","2006-10-03"]
["UN47_00060","Design Complete  Ent Sec","2006-10-04","2006-10-03"]
["UN47_00250","Bid Process Bid Pkg","2006-10-04","2006-11-07"]
["UN47_00251","Evaluate Bids - Entrance Section","2006-11-08","2006-11-10"]
["UN47_00260","AWARD: Standard Entrance Chamber","2006-11-13","2006-11-15"]
["UN47_00261","AWARD: Standard Entrance Chamber (1)","2006-11-13","2006-11-15"]
["UN47_00265","AWARD: Standard Entrance Chamber Sppt","2006-11-13","2006-11-15"]
["UN47_00270","AWARD: Entrance Bellows","2006-11-13","2006-11-15"]
["UN47_00271","AWARD: Entrance Bellows (2)","2006-11-13","2006-11-15"]
["UN47_00275","AWARD: Entrance Bellows Sppt","2006-11-13","2006-11-15"]
["UN47_00280","AWARD: Entrance Upstream Chamber","2006-11-13","2006-11-15"]
["UN47_00281","AWARD: Entrance Upstream Chamber (1)","2006-11-13","2006-11-15"]
["UN47_00285","AWARD: Entrance Upstream Chamber Sppt","2006-11-13","2006-11-15"]
["UN47_00300","AWARD: Pump Manifold","2006-11-13","2006-11-15"]
["UN47_00301","AWARD: Pump Manifold (1)","2006-11-13","2006-11-15"]
["UN47_00305","AWARD: Pump Manifold Sppt","2006-11-13","2006-11-15"]
["UN47_00310","AWARD: Ion Pump (1)","2006-11-13","2006-11-15"]
["UN47_00311","AWARD: Ion Pump (2)","2006-11-13","2006-11-15"]
["UN47_00315","AWARD: Ion Pump (1) Sppt","2006-11-13","2006-11-15"]
["UN47_00320","AWARD: Ion Pump Controller (1)","2006-11-13","2006-11-15"]
["UN47_00321","AWARD: Ion Pump Controller (1)","2006-11-13","2006-11-15"]
["UN47_00325","AWARD: Ion Pump Controller (1) Sppt","2006-11-13","2006-11-15"]
["UN47_00330","AWARD: Ion Pump Cable (1)","2006-11-13","2006-11-15"]
["UN47_00331","AWARD: Ion Pump Cable (2)","2006-11-13","2006-11-15"]
["UN47_00335","AWARD: Ion Pump Cable (1) Sppt","2006-11-13","2006-11-15"]
["UN47_00340","AWARD: Gate Valve (1)","2006-11-13","2006-11-15"]
["UN47_00341","AWARD: Gate Valve (1)","2006-11-13","2006-11-15"]
["UN47_00342","AWARD:  Turbo Pump","2006-11-13","2006-11-15"]
["UN47_00343","AWARD:  Turbo Pump SPPT","2006-11-13","2006-11-15"]
["UN47_00344","AWARD:  Roughing Pump","2006-11-13","2006-11-15"]
["UN47_00345","AWARD: Gate Valve (1) Sppt","2006-11-13","2006-11-15"]
["UN47_00346","AWARD:  Roughing Pump SPPT","2006-11-13","2006-11-15"]
["UN47_00347","AWARD:  Pneumatic Gate Valve","2006-11-13","2006-11-15"]
["UN47_00348","AWARD:  Pneumatic Gate Valve SPPT","2006-11-13","2006-11-15"]
["UN47_00349","AWARD:  Pneumatic Gate Valve","2006-11-16","2006-11-20"]
["UN47_00350","AWARD: Valves (1)","2006-11-13","2006-11-15"]
["UN47_00351","AWARD: Valves (1)","2006-11-13","2006-11-15"]
["UN47_00355","AWARD: Valves (1) Sppt","2006-11-13","2006-11-15"]
["UN47_00360","AWARD: Vacuum Gauge (1)","2006-11-13","2006-11-15"]
["UN47_00361","AWARD: Vacuum Gauge (1)","2006-11-13","2006-11-15"]
["UN47_00365","AWARD: Vacuum Gauge (1) Sppt","2006-11-13","2006-11-15"]
["UN47_00380","AWARD: RGA (1)","2006-11-13","2006-11-15"]
["UN47_00381","AWARD: RGA (1)","2006-11-13","2006-11-15"]
["UN47_00385","AWARD: RGA (1) Sppt","2006-11-13","2006-11-15"]
["UN47_00390","AWARD: Standard Entrance Chamber Support","2006-11-13","2006-11-15"]
["UN47_00391","AWARD: Standard Entrance Chamber Support (1)","2006-11-13","2006-11-15"]
["UN47_00395","AWARD: Standard Entrance Chamber Support Sppt","2006-11-13","2006-11-15"]
["UN47_00400","AWARD: Entrance Chamber Mount","2006-11-13","2006-11-15"]
["UN47_00401","AWARD: Entrance Chamber Mount (1)","2006-11-13","2006-11-15"]
["UN47_00405","AWARD: Entrance Chamber Mount Sppt","2006-11-13","2006-11-15"]
["UN47_00410","AWARD: Ion Pump Support (1)","2006-11-13","2006-11-15"]
["UN47_00411","AWARD: Ion Pump Support (1)","2006-11-13","2006-11-15"]
["UN47_00415","AWARD: Ion Pump Support (1) Sppt","2006-11-13","2006-11-15"]
["UN47_00420","AWARD: Gate Valve Support","2006-11-13","2006-11-15"]
["UN47_00421","AWARD: Gate Valve Support (1)","2006-11-13","2006-11-15"]
["UN47_00425","AWARD: Gate Valve Support Sppt","2006-11-13","2006-11-15"]
["UN47_00430","AWARD: RGA Support","2006-11-13","2006-11-15"]
["UN47_00431","AWARD: RGA Support (1)","2006-11-13","2006-11-15"]
["UN47_00435","AWARD: RGA Support Sppt","2006-11-13","2006-11-15"]
["UN47_00440","AWARD: Entrance Section Assembly and Support","2006-11-16","2006-11-15"]
["UN47_00460","Rec:  Standard Entrance Chamber","2006-11-16","2007-01-22"]
["UN47_00461","Rec: Standard Entrance Chamber","2006-11-16","2007-01-30"]
["UN47_00462","Rec: Entrance Bellows","2006-11-16","2007-01-22"]
["UN47_00463","Rec: Entrance Bellows","2006-11-16","2007-01-30"]
["UN47_00464","Rec: Entrance Upstream Chamber","2006-11-16","2007-01-22"]
["UN47_00465","Rec: Entrance Upstream Chamber","2006-11-16","2007-01-30"]
["UN47_00466","Rec: Pump Manifold","2006-11-16","2007-01-22"]
["UN47_00467","Rec: Pump Manifold","2006-11-16","2007-01-30"]
["UN47_00468","Rec: Ion Pump","2006-11-16","2007-01-22"]
["UN47_00469","Rec: Ion Pump","2006-11-16","2007-01-30"]
["UN47_00470","Rec: Ion Pump Controller","2006-11-16","2007-01-22"]
["UN47_00471","Rec: Ion Pump Controller","2006-11-16","2007-01-30"]
["UN47_00472","Rec: Ion Pump Cable","2006-11-16","2007-01-22"]
["UN47_00473","Rec: Ion Pump Cable","2006-11-16","2007-01-30"]
["UN47_00474","Rec: Gate Valve","2006-11-16","2007-01-22"]
["UN47_00475","Rec: Gate Valve","2006-11-16","2007-01-30"]
["UN47_00476","Rec: Valve","2006-11-16","2007-01-22"]
["UN47_00477","Rec: Valve","2006-11-16","2007-01-30"]
["UN47_00478","Rec: Vacuum Gauge","2006-11-16","2007-01-22"]
["UN47_00479","Rec: Vacuum Gauge","2007-01-23","2007-03-20"]
["UN47_00480","Rec: RGA","2006-11-16","2007-01-22"]
["UN47_00481","Rec: RGA","2006-11-16","2007-01-30"]
["UN47_00482","Rec: Entrance Chamber Support","2006-11-16","2007-01-22"]
["UN47_00483","Rec: Entrance Chamber Support","2006-11-16","2007-01-30"]
["UN47_00484","Rec: Chamber Mount","2006-11-16","2007-01-22"]
["UN47_00485","Rec: Chamber Mount","2006-11-16","2007-01-30"]
["UN47_00486","Rec: Ion Pump Support","2006-11-16","2007-01-22"]
["UN47_00487","Rec: Ion Pump Support","2006-11-16","2007-01-30"]
["UN47_00488","Rec: Gate Valve Support","2006-11-16","2007-01-22"]
["UN47_00489","Rec: Gate Valve Support","2006-11-16","2007-01-30"]
["UN47_00490","Rec: RGA Support","2006-11-16","2007-01-22"]
["UN47_00491","Rec: RGA Support","2007-01-23","2007-03-20"]
["UN47_00492","Rec:  Turbo Pump","2006-11-16","2007-01-22"]
["UN47_00493","Rec:  Roughing Pump","2006-11-16","2007-01-22"]
["UN47_00494","Rec:  Pneumatic Gate Valve","2006-11-16","2007-01-22"]
["UN47_00495","Rec:  Pneumatic Gate Valve","2006-11-21","2007-01-22"]
["UN47_00498","QA of Entrance Section Components","2007-01-23","2007-01-31"]
["UN47_00499","Clean Ent Sec","2007-02-01","2007-02-14"]
["UN47_00500","Bake Ent Sec","2007-04-30","2007-05-11"]
["UN47_00510","Assemble Entrance Section Components","2007-05-14","2007-06-11"]
["UN47_00520","Assembly Test Ent Sec","2007-06-12","2007-06-13"]
["UN47_00530","Prepare Ent Sec Assembly & Support  for Shipme","2007-06-14","2007-06-20"]
["UN47_00540","Pack Ent Sec Assembly & Support for Shipment","2007-06-21","2007-06-27"]
["UN47_00550","Ship  Ent Sec to Slac","2007-06-28","2007-06-27"]
["UN47_00560","Transmit  Ent Sec Design a& Drawings to SLAC","2007-06-28","2007-07-05"]
["UN47_00562","RFI: Entrance Section Assembly and Support","2007-07-06","2007-07-05"]
["UN47_00570","Develop Installation Plan Ent Sec","2007-06-28","2007-07-06"]
["UN47_00580","Review installation Plan Ent Sec","2007-07-09","2007-07-13"]
["UN47_00590","Entrance Section Assy & Support Arrive at SLAC","2007-07-06","2007-07-19"]
["UN47_00595","Install Entrance Section Components","2007-08-29","2007-09-05"]
["UN47_00670","Commission - Entrance Section Assy","2007-09-06","2007-09-12"]
["UN48_00010","Specification Exit Sec","2006-07-11","2006-07-24"]
["UN48_00020","Prelim Prototype Design Exit Sec","2006-07-25","2006-08-21"]
["UN48_00030","Mechanical Analysis Exit Sec","2006-08-22","2006-09-05"]
["UN48_00040","Prelim Prototype Design Review Exit Sec","2006-09-06","2006-09-12"]
["UN48_00050","Final Exit Sec Design","2006-09-13","2006-09-26"]
["UN48_00060","Design Complete Exit Sec","2006-09-27","2006-09-26"]
["UN48_00250","Bid Process Exit Sec","2006-09-27","2006-10-31"]
["UN48_00260","AWARD: Standard Exit Chamber","2006-11-01","2006-11-03"]
["UN48_00261","AWARD: Standard Exit Chamber (1)","2006-11-01","2006-11-03"]
["UN48_00265","AWARD: Standard Exit Chamber Sppt","2006-11-01","2006-11-03"]
["UN48_00270","AWARD: Exit Bellows","2006-11-01","2006-11-03"]
["UN48_00275","AWARD: Exit Bellows Sppt","2006-11-01","2006-11-03"]
["UN48_00290","AWARD: Exit Downstream Chamber","2006-11-01","2006-11-03"]
["UN48_00291","AWARD: Exit Downstream Chamber (1)","2006-11-01","2006-11-03"]
["UN48_00295","AWARD: Exit Downstream Chamber Sppt","2006-11-01","2006-11-03"]
["UN48_00300","AWARD: Exit Pump Manifold","2006-11-01","2006-11-03"]
["UN48_00305","AWARD: Exit Pump Manifold Sppt","2006-11-01","2006-11-03"]
["UN48_00310","AWARD: Ion Pump","2006-11-01","2006-11-03"]
["UN48_00315","AWARD: Ion Pump Sppt","2006-11-01","2006-11-03"]
["UN48_00320","AWARD: Turbo Pump","2006-11-01","2006-11-03"]
["UN48_00321","Award: Turbo Pump","2006-11-01","2006-11-03"]
["UN48_00325","AWARD: Turbo Pump Sppt","2006-11-01","2006-11-03"]
["UN48_00326","AWARD:  Pneumatic Gate Valve","2006-11-01","2006-11-03"]
["UN48_00327","AWARD:  Pneumatic Gate Valve SPPT","2006-11-01","2006-11-03"]
["UN48_00330","AWARD: Roughing Pump","2006-11-01","2006-11-03"]
["UN48_00331","AWARD: Roughing Pump","2006-11-06","2006-11-08"]
["UN48_00335","AWARD: Roughing Pump Sppt","2006-11-01","2006-11-03"]
["UN48_00340","AWARD: Gate Valve","2006-11-01","2006-11-03"]
["UN48_00345","AWARD: Gate Valve Sppt","2006-11-01","2006-11-03"]
["UN48_00350","AWARD: Valves","2006-11-01","2006-11-03"]
["UN48_00355","AWARD: Valves Sppt","2006-11-01","2006-11-03"]
["UN48_00360","AWARD: Vacuum Gauge","2006-11-01","2006-11-03"]
["UN48_00365","AWARD: Vacuum Gauge Sppt","2006-11-01","2006-11-03"]
["UN48_00380","AWARD: RGA","2006-11-01","2006-11-03"]
["UN48_00385","AWARD: RGA Sppt","2006-11-01","2006-11-03"]
["UN48_00390","AWARD: Standard Exit Chamber Support (2)","2006-11-01","2006-11-03"]
["UN48_00391","AWARD: Standard Exit Chamber Support (1)","2006-11-01","2006-11-03"]
["UN48_00395","AWARD: Standard Exit Chamber Support (2) Sppt","2006-11-01","2006-11-03"]
["UN48_00400","AWARD: Exit Downstream Chamber Support (2)","2006-11-01","2006-11-03"]
["UN48_00401","AWARD: Exit Downstream Chamber Support (1)","2006-11-01","2006-11-03"]
["UN48_00405","AWARD: Exit Downstream Chamber Support (2) Sppt","2006-11-01","2006-11-03"]
["UN48_00410","AWARD: Ion Pump Support (2)","2006-11-01","2006-11-03"]
["UN48_00415","AWARD: Ion Pump Support (2) Sppt","2006-11-01","2006-11-03"]
["UN48_00420","AWARD: Gate Valve Support (1)","2006-11-01","2006-11-03"]
["UN48_00425","AWARD: Gate Valve Support (1) Sppt","2006-11-01","2006-11-03"]
["UN48_00430","AWARD: RGA Support (1)","2006-11-01","2006-11-03"]
["UN48_00435","AWARD: RGA Support (1) Sppt","2006-11-01","2006-11-03"]
["UN48_00440","AWARD: Complete Exit Sec","2006-11-06","2006-11-03"]
["UN48_00460","Rec: Standard Exit Chamber","2006-11-06","2007-01-10"]
["UN48_00461","Rec.: Standard Exit Chamber","2006-11-06","2007-01-18"]
["UN48_00462","Rec: Exit Bellows","2006-11-06","2007-01-10"]
["UN48_00463","Rec: Exit Downstream Chamber","2006-11-06","2007-01-10"]
["UN48_00464","Rec: Exit Downstream Chamber","2006-11-06","2007-01-18"]
["UN48_00465","Rec: Exit Pump Manifold","2006-11-06","2007-01-10"]
["UN48_00466","Rec: Ion Pump","2006-11-06","2007-01-10"]
["UN48_00467","Rec: Turbo Pump","2006-11-06","2007-01-10"]
["UN48_00468","Rec: Turbo Pump","2006-11-06","2007-01-18"]
["UN48_00469","Rec: Roughing Pump","2006-11-06","2007-01-10"]
["UN48_00470","Rec: Roughing Pump","2006-11-09","2007-01-23"]
["UN48_00471","Rec:  Pneumatic Gate Valve","2006-11-06","2007-01-10"]
["UN48_00472","Rec: Gate Valve","2006-11-06","2007-01-10"]
["UN48_00473","Rec: Valve","2006-11-06","2007-01-10"]
["UN48_00474","Rec: Vacuum Gauge","2006-11-06","2007-01-10"]
["UN48_00475","Rec: RGA","2006-11-06","2007-01-10"]
["UN48_00476","Rec: Standard Exit Chamber Support","2006-11-06","2007-01-10"]
["UN48_00477","Rec: Standard Exit Chamber Support","2006-11-06","2007-01-18"]
["UN48_00478","Rec: Exit Downstream Chamber Support","2006-11-06","2007-01-10"]
["UN48_00479","Rec: Exit Downstream Chamber Support","2006-11-06","2007-01-18"]
["UN48_00480","Rec: Ion Pump Support","2006-11-06","2007-01-10"]
["UN48_00481","Rec: Gate Valve Support","2006-11-06","2007-01-10"]
["UN48_00482","Rec: RGA Support","2006-11-06","2007-01-10"]
["UN48_00488","QA of Exit Section Components","2007-01-11","2007-01-19"]
["UN48_00489","Approve Production Exit Sec","2007-01-22","2007-01-24"]
["UN48_00490","Clean Exit Sec","2007-01-25","2007-02-05"]
["UN48_00500","Bake Exit Sec","2007-04-30","2007-05-11"]
["UN48_00510","Assemble Exit Section Components","2007-05-14","2007-06-12"]
["UN48_00520","Assembly Test Exit Sec","2007-06-13","2007-07-02"]
["UN48_00530","Prepare Exit Sec Assembly & Support  for Ship","2007-07-03","2007-07-11"]
["UN48_00540","Pack Exit Sec Assembly and Support for Shipmen","2007-07-12","2007-07-19"]
["UN48_00550","Ship  Exit Sec to Slac","2007-07-20","2007-07-19"]
["UN48_00560","Transmit Exit Sec Design & Drawings to SLAC","2007-07-20","2007-07-27"]
["UN48_00562","RFI: Exit Section Assembly and Support","2007-07-30","2007-07-27"]
["UN48_00570","Develop Exit Sec Installation Plan","2007-07-20","2007-08-01"]
["UN48_00580","Review Exit Sec Installation Plan","2007-08-02","2007-08-09"]
["UN48_00590","Exit Section Assembly & Support  Arrive at SLAC","2007-07-20","2007-08-01"]
["UN48_00595","Install Exit Section Components","2007-10-29","2007-11-02"]
["UN48_00600","Install Pumps","2007-11-05","2007-11-09"]
["UN48_00605","Make Up Vacuum","2008-01-24","2008-02-06"]
["UN48_00610","Make Up Vacuum","2007-11-05","2007-11-16"]
["UN48_00620","Pump Down","2008-04-22","2008-05-05"]
["UN48_00625","Leak Test","2008-05-06","2008-05-12"]
["UN48_00630","Controls System Checkout","2008-05-13","2008-05-27"]
["UN48_00635","System Checkout","2008-05-28","2008-06-10"]
["UN48_00670","Commission - Exit Section Assy","2007-11-05","2007-11-12"]
["UN48_D200","Cell Conceptual Layout","2005-05-02","2005-08-31",null,"2005-05-02","2005-08-31"]
["UN48_D201","System Conceptual Layout","2005-09-01","2005-12-22",null,"2005-09-01","2005-12-22"]
["UN48_D202","Update Vacuum Chamber","2006-11-15","2006-12-07"]
["UN48_D203","Update Bellows","2006-07-11","2006-07-31"]
["UN48_D204","Update SDB","2006-10-18","2006-11-07"]
["UN48_D205","Update LDB","2006-10-13","2006-11-02"]
["UN48_D206","Update Entrance Section","2006-10-04","2006-10-17"]
["UN48_D207","Update Exit Section","2006-09-27","2006-10-10"]
["UN48_D208","Update ULD Station","2006-02-01","2006-02-21"]
["UN48_D209","Update EOU","2006-07-14","2006-08-03"]
["UN48_D210","Update RFBPM","2006-09-26","2006-10-16"]
["UN48_D211","Update Charge Monitor","2006-12-06","2006-12-19"]
["UN48_D212","Update Cherenkov Detector","2006-06-01","2006-06-21"]
["UN48_D213","Update RDM","2007-05-03","2007-05-16"]
["UN48_D214","System Layout Clean-up","2007-05-17","2007-06-28"]
["UN48_D215","Update Undulator Magnet","2005-09-26","2005-12-30",null,"2005-09-26","2005-12-30"]
["UN48_D216","Update Movers","2007-02-13","2007-03-05"]
["UN48_D217","Update Fixed Support","2005-09-26","2006-01-31",null,"2005-09-26","2006-01-31"]
["UN48_D218","Update Quads","2005-10-26","2006-02-28",null,"2005-10-26"]
["UN49_00010","Specification of Baking Station (System)","2006-10-04","2006-10-17"]
["UN49_00020","Prelim Design of Baking Station","2006-10-18","2006-11-07"]
["UN49_00030","Prelim Baking Station Design Review","2006-11-08","2006-11-09"]
["UN49_00040","Final Design of Baking Station","2006-11-10","2006-11-16"]
["UN49_00050","Design Complete Baking Station","2006-11-17","2006-11-16"]
["UN49_00060","Bid Package-Baking Station","2006-11-17","2006-11-21"]
["UN49_00070","Bid Package-Heater","2006-11-17","2006-11-21"]
["UN49_00080","Bid Package-Thermal Insulation","2006-11-17","2006-11-21"]
["UN49_00090","Bid Pkg: Turbo Pump Baking Station","2006-11-17","2006-11-27"]
["UN49_00100","Bid Pkg: Roughing Pump Baking Station","2006-11-17","2006-11-21"]
["UN49_00110","Bid Package-Valves Baking Station","2006-11-17","2006-11-21"]
["UN49_00120","Bid Pkg: Vacuum Gauge Baking Station","2006-11-17","2006-11-21"]
["UN49_00140","Bid Pkg: RGA Baking Station","2006-11-17","2006-11-27"]
["UN49_00150","Bid Process Baking Station","2006-11-28","2007-01-18"]
["UN49_00151","Evaluate Bids: Baking Station","2007-01-19","2007-01-23"]
["UN49_00160","AWARD: Baking Station","2007-01-24","2007-01-26"]
["UN49_00165","AWARD: Baking Station Sppt","2007-01-24","2007-01-26"]
["UN49_00170","AWARD: Heater","2007-01-24","2007-01-26"]
["UN49_00175","AWARD: Heater Sppt","2007-01-24","2007-01-26"]
["UN49_00180","AWARD: Thermal Insulation","2007-01-24","2007-01-26"]
["UN49_00185","AWARD: Thermal Insulation Sppt","2007-01-24","2007-01-26"]
["UN49_00190","AWARD: Turbo Pump","2007-01-24","2007-01-26"]
["UN49_00195","AWARD: Turbo Pump Sppt","2007-01-24","2007-01-26"]
["UN49_00200","AWARD: Roughing Pump","2007-01-24","2007-01-26"]
["UN49_00205","AWARD: Roughing Pump Sppt","2007-01-24","2007-01-26"]
["UN49_00210","AWARD: Valves","2007-01-24","2007-01-26"]
["UN49_00215","AWARD: Valves Sppt","2007-01-24","2007-01-26"]
["UN49_00220","AWARD: Vacuum Gauge","2007-01-24","2007-01-26"]
["UN49_00225","AWARD: Vacuum Gauge Sppt","2007-01-24","2007-01-26"]
["UN49_00240","AWARD: RGA","2007-01-24","2007-01-26"]
["UN49_00245","AWARD: RGA Sppt","2007-01-24","2007-01-26"]
["UN49_00250","AWARD: Complete Baking Sys","2007-01-29","2007-01-26"]
["UN49_00260","Fabrication of Baking Components","2007-01-29","2007-02-23"]
["UN49_00270","Receive Baking Components","2007-02-26","2007-03-16"]
["UN49_00280","QA of Baking Components","2007-03-19","2007-03-23"]
["UN49_00290","Integration to Baking System","2007-03-26","2007-04-13"]
["UN49_00300","Preform Bake System Testing","2007-04-16","2007-04-20"]
["UN49_00310","Transmit  Baking Sys Design & Drawings to SLAC","2007-04-23","2007-04-27"]
["UN49_00320","Complete Baking Sys","2007-04-30","2007-04-27"]
["UN501_0042","Travel End-Of-Undulator - FY05 (PED)","2005-05-02","2005-06-30",null,"2005-05-02","2005-06-30"]
["UN501_0115","Travel SLAC Project Engineer, etc.","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN502_0241","Award: ULD Vacuum Chamber (1)","2006-10-03","2006-10-09"]
["UN502_0251","AWARD: ULD Support Stand (1)","2006-10-03","2006-10-09"]
["UN502_0271","Rec: EBXPD Vacuum Chamber (1)","2006-10-10","2006-12-06"]
["UN502_0275","Rec: EBXPD Support Stand (1)","2006-10-10","2006-12-06"]
["UN502_0402","AWARD: Beam Tube and Spring Contact (1)","2006-10-03","2006-10-04"]
["UN502_0414","AWARD: Main translation stage (1)","2006-10-03","2006-10-04"]
["UN502_0432","Rec: Beam Tube and Spring Contact (1)","2006-10-05","2006-11-15"]
["UN502_0444","Rec: Main translation stage (1)","2006-10-05","2006-11-15"]
["UN502_0572","AWARD: Motorized scanner (1)","2006-10-03","2006-10-04"]
["UN502_0582","AWARD: Wire Mounting Rack (1)","2006-10-03","2006-10-04"]
["UN502_0592","AWARD: Photo electron detector (1)","2006-10-03","2006-10-04"]
["UN502_0612","Rec: Motorized Scanner (1)","2006-10-05","2006-12-01"]
["UN502_0616","Rec: Wire Rack (1)","2006-10-05","2006-12-01"]
["UN502_0619","Rec: Photo electron detector (1)","2006-10-05","2006-12-01"]
["UN502_0752","AWARD: Mirrors (1)","2006-10-03","2006-10-04"]
["UN502_0762","AWARD: Motorized shutter (upstream) (1)","2006-10-03","2006-10-04"]
["UN502_0772","AWARD: Light transport/imaging optics (vac) (1","2006-10-03","2006-10-04"]
["UN502_0782","AWARD: Motorized filter/aperture changer (1)","2006-10-03","2006-10-04"]
["UN502_0792","AWARD: Camera assembly and shielding (1)","2006-10-03","2006-10-04"]
["UN502_0811","Rec: Mirrors (1)","2006-10-05","2006-12-01"]
["UN502_0813","Rec: Motorized Shutter (upstream) (1)","2006-10-05","2006-12-01"]
["UN502_0815","Rec: Light transport/imaging optics (vac) (1)","2006-10-05","2006-12-01"]
["UN502_0819","Rec: Camera assembly and shielding (1)","2006-10-05","2006-12-01"]
["UN502_0826","Rec: Motorized filter/aperture changer (1)","2006-10-05","2006-12-01"]
["UN502_0840","Design Prototype ULD-XRID","2006-04-12","2006-06-07"]
["UN502_0850","Mechanical Analysis - ULD-XRID","2006-06-08","2006-06-26"]
["UN502_0860","Fabricate Prototype EBXPD-XRID","2006-06-27","2006-08-09"]
["UN502_0870","Test Prototype EBXPD-XRID","2006-08-10","2006-08-22"]
["UN502_0960","Design Prototype ULD-XRM","2006-03-06","2006-04-28"]
["UN502_0970","Mechanical Analysis - ULD-XRM","2006-05-01","2006-05-12"]
["UN502_0980","Fabricate Prototype ULD-XRM","2006-05-15","2006-06-20"]
["UN502_0990","Test Prototype EBXPD-XRM","2006-06-21","2006-07-06"]
["UN502_1160","Design Prototype ULD-IMG","2006-03-06","2006-04-03"]
["UN502_1170","Mechanical Analysis - ULD-IMG","2006-04-04","2006-04-11"]
["UN502_1180","Fabricate Prototype ULD-IMG","2006-04-12","2006-05-17"]
["UN502_1190","Test Prototype ULD-IMG","2006-05-18","2006-05-25"]
["UN502_1750","Commission EBXPD","2007-11-01","2007-11-14"]
["UN502_D166","Define design concept for screen survival tests","2006-07-03","2006-07-31"]
["UN502_D167","Design test assembly for screen survival tests","2006-08-01","2006-08-14"]
["UN502_D168","Purchase test assbly parts screen survival tests","2006-08-15","2006-08-21"]
["UN502_D169","Fabricate test assbly parts for scr surv tst","2006-08-22","2006-08-30"]
["UN502_D170","Assemble test assembly screen survival tests","2006-08-31","2006-09-11"]
["UN502_D171","Ship to SLAC screen survival tests","2006-09-12","2006-09-20"]
["UN502_D172","Test assembly scr surv tst arrives at SLAC","2006-09-21","2006-09-20"]
["UN502_D178","Vacuum test document complete","2006-09-07","2006-09-06"]
["UN502_DA76","Perform vacuum tests Part II","2006-07-03","2006-07-11"]
["UN502_DA77","Assemble & report test results vacuum test PII","2006-07-12","2006-09-06"]
["UN503_0040","Preliminary Design - PRPT HPPD","2006-04-25","2006-05-22"]
["UN503_0050","Design Analysis - PRPT HPPD","2006-05-23","2006-05-30"]
["UN503_0060","Design Review - PRPT HPPD","2006-05-31","2006-06-08"]
["UN503_0070","Final Design - PRPT HPPD","2006-06-09","2006-06-29"]
["UN503_0090","Prepare Bid Package - ODR Module","2007-01-12","2007-02-16"]
["UN503_0100","Prepare Bid Package - Laser Wire Module","2007-01-12","2007-02-16"]
["UN503_0110","Bid Process - PRPT HPPD","2007-02-20","2007-03-19"]
["UN503_0120","Evaluate Bids - PRPT HPPD","2007-03-20","2007-03-29"]
["UN503_0130","AWARD: ODR Module","2007-03-30","2007-04-03"]
["UN503_0135","AWARD: ODR Module Sppt","2007-03-30","2007-04-03"]
["UN503_0140","AWARD:  Laser Wire Module","2007-04-04","2007-04-10"]
["UN503_0141","RCV:  PRPT HPPD Components","2007-04-11","2007-04-11"]
["UN503_0142","Determine Suitable Test Facility - HPPD","2007-01-12","2007-01-16"]
["UN503_0145","AWARD:  Laser Wire Module Sppt","2007-04-04","2007-04-10"]
["UN503_0150","Intregrate Controls - HPPD","2007-04-12","2007-05-02"]
["UN503_0152","Assemble Test Station - HPPD","2007-01-17","2007-02-01"]
["UN503_0160","Perform Module Testing - HPPD","2007-05-03","2007-05-31"]
["UN503_0170","Test Measurements Review meeting - HPPD","2007-06-01","2007-06-07"]
["UN503_0180","HPPD Testing Complete","2007-06-08","2007-06-07"]
["UN503_0770","Specification of HPPD","2006-02-01","2006-02-10"]
["UN503_0780","Analysis and Simulations - HPPD","2006-02-13","2006-03-13"]
["UN503_0790","Literature Research - HPPD","2006-03-14","2006-04-10"]
["UN503_0800","Study Review and Recommendations - HPPD","2006-04-11","2006-04-24"]
["UN503_0810","HPPD Study Period Complete","2006-04-25","2006-04-24"]
["UN504_0010","Specification EOU","2006-01-19","2006-03-21",null,"2006-01-19"]
["UN504_0015","Design test Fixtures","2006-10-02","2006-10-20"]
["UN504_0017","Design Test Device","2006-10-02","2006-10-20"]
["UN504_0020","Procure and Fabrication test Fixtures","2006-10-23","2006-11-28"]
["UN504_0030","EOU Test Device Fabrication","2006-10-23","2006-11-17"]
["UN504_0040","Define EOU Device Testing Facility","2006-11-20","2006-12-01"]
["UN504_0050","Assemble Test Equipment and Station","2006-12-04","2006-12-15"]
["UN504_0060","Integrate Controls into Test station","2006-12-18","2007-01-08"]
["UN504_0070","Prototype Testing Complete","2007-02-07","2007-02-06"]
["UN504_0300","Upstream corrector / separator Specification","2006-03-22","2006-04-11"]
["UN504_0310","Upstream corrector / separator Design","2006-06-08","2006-07-13"]
["UN504_0320","Upstream corrector / separator Prototype Fabri","2006-07-14","2006-08-17"]
["UN504_0330","Upstream corrector / separator Prototype Testi","2006-08-18","2006-08-31"]
["UN504_0340","Review of Testing","2006-09-01","2006-09-08"]
["UN504_0380","Procurement Bid Package -3 mrad kicker","2006-09-11","2006-09-20"]
["UN504_0390","Procurement Bid Package -Kicker power supply","2006-09-11","2006-09-22"]
["UN504_0400","Bid Process","2006-09-25","2006-10-27"]
["UN504_0410","AWARD: 3 mrad kicker","2006-10-30","2006-11-01"]
["UN504_0420","AWARD: Kicker power supply","2006-10-30","2006-11-01"]
["UN504_0430","AWARD: Upstream Corrector/Separator","2006-11-02","2006-11-01"]
["UN504_0440","Receive Packages","2006-11-02","2007-01-08"]
["UN504_0450","QA Upstream Corrector/Separator","2007-01-09","2007-01-15"]
["UN504_0460","AVAIL: Upstream Corrector/Separator","2007-01-16","2007-01-15"]
["UN504_0470","EOU-OTR Prototype Specification","2006-04-12","2006-04-25"]
["UN504_0480","EOU-OTR Prototype Design","2006-04-26","2006-06-07"]
["UN504_0485","EOU-OTR Prototype Design Review","2006-06-08","2006-06-14"]
["UN504_0490","EOU-OTR Prototype Fabrication","2006-06-15","2006-07-20"]
["UN504_0500","EOU-OTR Prototype Testing","2007-01-09","2007-01-22"]
["UN504_0510","Review of Testing","2007-01-23","2007-02-01"]
["UN504_0550","Procurement Bid Package -Translation Assembly","2007-04-30","2007-05-04"]
["UN504_0560","Procurement Bid Package -Optical parts","2007-04-30","2007-05-04"]
["UN504_0570","Procurement Bid Package -Vacuum Vessel","2007-04-30","2007-05-04"]
["UN504_0580","Procurement Bid Package -Support Table","2007-04-30","2007-05-04"]
["UN504_0590","Procurement Bid Package -Hardware","2007-04-30","2007-05-11"]
["UN504_0600","Bid Process","2007-05-14","2007-06-25"]
["UN504_0610","AWARD: Translation Assembly w/mirrors","2007-06-26","2007-07-02"]
["UN504_0615","AWARD: Translation Assembly w/mirrors Sppt","2007-06-26","2007-06-29"]
["UN504_0620","AWARD: Optical parts","2007-06-26","2007-06-29"]
["UN504_0625","AWARD: Optical parts Sppt","2007-06-26","2007-06-29"]
["UN504_0630","AWARD: Vacuum Vessel","2007-06-26","2007-06-29"]
["UN504_0635","AWARD: Vacuum Vessel Sppt","2007-06-26","2007-06-29"]
["UN504_0640","AWARD: Support Table","2007-06-26","2007-06-29"]
["UN504_0645","AWARD: Support Table Sppt","2007-06-26","2007-06-29"]
["UN504_0650","AWARD: Hardware","2007-06-26","2007-06-29"]
["UN504_0655","AWARD: Hardware Sppt","2007-06-26","2007-06-29"]
["UN504_0660","AWARD: EOU ODR Assembly","2007-07-03","2007-07-02"]
["UN504_0670","Receive Packages","2007-07-03","2007-09-12"]
["UN504_0680","QA EOU ODR Assembly","2007-09-13","2007-09-19"]
["UN504_0690","AVAIL: EOU ODR Assembly","2007-09-20","2007-09-19"]
["UN504_0700","EOU-XRM Prototype Specification","2006-04-26","2006-05-09"]
["UN504_0710","EOU-XRM Prototype Design","2006-07-14","2006-08-31"]
["UN504_0720","EOU-XRM Prototype Fabrication","2006-09-01","2006-10-13"]
["UN504_0730","EOU-XRM Prototype Testing","2007-01-09","2007-01-24"]
["UN504_0740","Review of Testing","2007-01-25","2007-02-05"]
["UN504_0780","Procurement Bid Package -Translation Assembly","2007-02-06","2007-02-14"]
["UN504_0790","Procurement Bid Package -Rotary Assembly","2007-02-06","2007-02-14"]
["UN504_0800","Procurement Bid Package -X-Ray Optics","2007-02-06","2007-02-14"]
["UN504_0810","Procurement Bid Package -Detector & Visible Op","2007-02-06","2007-02-14"]
["UN504_0820","Procurement Bid Package -Vacuum Vessel","2007-02-06","2007-02-14"]
["UN504_0830","Procurement Bid Package -Support Table & H/W","2007-02-06","2007-02-14"]
["UN504_0840","Bid Process","2007-02-15","2007-03-21"]
["UN504_0850","AWARD: Translation Assembly","2007-03-22","2007-03-26"]
["UN504_0855","AWARD: Translation Assembly Sppt","2007-03-22","2007-03-26"]
["UN504_0860","AWARD: Rotary Assembly","2007-03-22","2007-03-26"]
["UN504_0865","AWARD: Rotary Assembly Sppt","2007-03-22","2007-03-26"]
["UN504_0870","AWARD: X-Ray Optics","2007-03-22","2007-03-26"]
["UN504_0875","AWARD: X-Ray Optics Sppt","2007-03-22","2007-03-26"]
["UN504_0880","AWARD: Detector & Visible Optics Parts","2007-03-22","2007-03-26"]
["UN504_0885","AWARD: Detector & Visible Optics Parts Sppt","2007-03-22","2007-03-26"]
["UN504_0890","AWARD: Vacuum Vessel","2007-03-22","2007-03-26"]
["UN504_0895","AWARD: Vacuum Vessel Sppt","2007-03-22","2007-03-26"]
["UN504_0900","AWARD: Support Table and Hardware","2007-03-22","2007-03-27"]
["UN504_0905","AWARD: Support Table and Hardware Sppt","2007-03-22","2007-03-26"]
["UN504_0910","AWARD: EOU XRM Assembly","2007-03-28","2007-03-27"]
["UN504_0920","Receive Packages","2007-03-28","2007-05-22"]
["UN504_0930","QA EOU XRM Assembly","2007-05-23","2007-05-30"]
["UN504_0940","AVAIL: EOU XRM Assembly","2007-05-31","2007-05-30"]
["UN504_0950","EOU-XRID Prototype Specification","2006-05-10","2006-05-31"]
["UN504_0960","EOU-XRID Prototype Design","2006-09-01","2006-10-06"]
["UN504_0970","EOU-XRID Prototype Fabrication","2006-10-09","2006-11-17"]
["UN504_0980","EOU-XRID Prototype Testing","2007-01-09","2007-01-25"]
["UN504_0990","Review of Testing","2007-01-26","2007-02-06"]
["UN504_1030","Procurement Bid Package of Ion / electron gun","2007-02-07","2007-02-13"]
["UN504_1040","Procurement Bid Pkg of Ion/electron accel/optics","2007-02-07","2007-02-16"]
["UN504_1050","Procurement Bid Package of Ion/electron detect","2007-02-07","2007-02-13"]
["UN504_1060","Procurement Bid Package of Vacuum vessel","2007-02-07","2007-02-20"]
["UN504_1070","Procurement Bid Package of Translation stage","2007-02-21","2007-02-27"]
["UN504_1080","Procurement Bid Package of Support Table & H/W","2007-02-28","2007-03-06"]
["UN504_1090","Bid Process","2007-03-07","2007-04-10"]
["UN504_1100","AWARD: Ion / electron gun","2007-04-11","2007-04-13"]
["UN504_1105","AWARD: Ion / electron gun Sppt","2007-04-11","2007-04-13"]
["UN504_1110","AWARD: Ion / electron accelerator / optics","2007-04-11","2007-04-13"]
["UN504_1115","AWARD: Ion / electron accelerator / optics Sppt","2007-04-11","2007-04-13"]
["UN504_1120","AWARD: Ion / electron detector assembly","2007-04-11","2007-04-13"]
["UN504_1125","AWARD: Ion / electron detector assembly Sppt","2007-04-11","2007-04-13"]
["UN504_1130","AWARD: Vacuum vessel","2007-04-11","2007-04-13"]
["UN504_1135","AWARD: Vacuum vessel Sppt","2007-04-11","2007-04-13"]
["UN504_1140","AWARD: Translation stage","2007-04-11","2007-04-13"]
["UN504_1145","AWARD: Translation stage Sppt","2007-04-11","2007-04-13"]
["UN504_1150","AWARD: Support Table & Hardware","2007-04-11","2007-04-13"]
["UN504_1155","AWARD: Support Table & Hardware Sppt","2007-04-11","2007-04-13"]
["UN504_1160","AWARD: EOU XRID Assembly","2007-04-16","2007-04-13"]
["UN504_1170","Receive Packages","2007-04-16","2007-06-25"]
["UN504_1180","QA EOU XRID Assembly","2007-06-26","2007-07-02"]
["UN504_1190","AVAIL: EOU XRID Assembly","2007-07-03","2007-07-02"]
["UN504_1226","X-Ray Studies and Simulations","2005-06-01","2006-01-30",null,"2005-06-01","2006-01-30"]
["UN504_1235","Organize literature Materials","2005-11-30","2006-02-28",null,"2005-11-30"]
["UN504_1240","Conduct Principles of Design Workshop","2006-03-01","2006-03-10"]
["UN504_1250","Justification Complete","2006-03-13","2006-03-10"]
["UN504_1260","PD: EOU Major Assembly Design","2006-06-01","2006-07-13"]
["UN504_1270","PD: EOU Shipping Containers","2006-07-14","2006-07-20"]
["UN504_1280","PD: EOU Supports","2006-07-14","2006-07-31"]
["UN504_1290","EOU Design Review","2006-08-01","2006-08-09"]
["UN504_1330","EOU Design Complete","2006-08-10","2006-08-09"]
["UN504_1340","Prepare EOU Bid Package","2006-08-10","2006-08-16"]
["UN504_1350","EOU Bid Process","2006-08-17","2006-09-21"]
["UN504_1360","AWARD: EOU Package","2006-09-22","2006-09-26"]
["UN504_1370","AWARD: EOU","2006-09-27","2006-09-26"]
["UN504_1410","Receive EOU Package","2006-09-27","2006-10-05"]
["UN504_1420","QA EOU Package","2006-10-06","2006-10-26"]
["UN504_1430","Approve EOU Package","2006-10-27","2006-10-31"]
["UN504_1440","Organize Parts for Assembly","2006-11-01","2006-11-07"]
["UN504_1450","Assemble EOU Package","2007-09-20","2007-10-17"]
["UN504_1460","Integrate Controls onto Assembly","2007-10-18","2007-11-12"]
["UN504_1470","Validation Testing of EOU","2007-11-13","2007-11-28"]
["UN504_1480","Pack EOU for Shipping","2007-11-29","2007-12-10"]
["UN504_1490","Write Shipping Paper Work - EOU","2007-12-11","2007-12-13"]
["UN504_1500","Ship to SLAC","2007-12-14","2007-12-13"]
["UN504_1510","Transmit Engineering Data to SLAC","2007-12-11","2007-12-17"]
["UN504_1520","Develop Installation Plan","2006-08-10","2006-08-28"]
["UN504_1530","Review installation Plan","2006-08-29","2006-09-05"]
["UN504_1540","EOU Arrive at SLAC","2007-12-14","2008-01-08"]
["UN504_1550","Pre-Align EOU at SLAC","2008-01-09","2008-02-06"]
["UN504_1560","Install EOU","2008-02-07","2008-03-06"]
["UN504_1570","Align EOU","2008-03-07","2008-03-28"]
["UN504_1580","Validate EOU","2008-03-31","2008-04-09"]
["UN504_1590","EOU Available","2008-04-10","2008-04-09"]
["UN504_1600","Integrate EOU","2008-04-10","2008-05-08"]
["UN504_1610","Test EOU","2008-05-09","2008-06-02"]
["UN504_1620","Commission EOU","2008-06-03","2008-06-20"]
["UN504_1630","Complete EOU Testing","2008-06-23","2008-06-20"]
["UN505_0172","AWARD: Copper Body Brazement (4)","2006-10-03","2006-10-05"]
["UN505_0182","AWARD: Support & Alignment Mechanism (4)","2006-10-03","2006-10-05"]
["UN505_0192","AWARD: RF Cabling (4)","2006-10-03","2006-10-05"]
["UN505_0211","Rec: Copper Body Brazement (4)","2006-10-06","2007-01-17"]
["UN505_0213","Rec: Support & Alignment Mechanism (4)","2006-10-06","2007-01-17"]
["UN505_0215","Rec: RF Cabling (4)","2006-10-06","2007-01-17"]
["UN505_0220","AWARD: Copper Body Brazement (1)","2006-10-03","2006-10-05"]
["UN505_0221","Rec: Copper Body Brazement (1)","2006-10-06","2007-01-17"]
["UN505_0225","AWARD: Support & Alignment Mechanism (1)","2006-10-03","2006-10-05"]
["UN505_0226","Rec: Support & Alignment Mechanism (1)","2006-10-06","2007-01-17"]
["UN505_0230","AWARD: Waveguide LTU (1)","2006-10-03","2006-10-05"]
["UN505_0231","Rec: Waveguide LTU (1)","2006-10-06","2007-01-17"]
["UN505_0235","AWARD: Undulator Waveguide (2)","2006-10-03","2006-10-05"]
["UN505_0236","Rec: Undulator Waveguide (2)","2006-10-06","2007-01-17"]
["UN505_0240","AWARD: Down Converter (3)","2006-10-03","2006-10-05"]
["UN505_0241","Rec: Down Converter (3)","2006-10-06","2007-01-17"]
["UN505_0245","AWARD: Local Oscillator (3)","2006-10-03","2006-10-05"]
["UN505_0246","Rec: Local Oscillator (3)","2006-10-06","2007-01-17"]
["UN505_0290","RFBPM Arrive at SLAC","2007-09-13","2007-09-26"]
["UN505_0370","Commission RFBPM","2007-09-27","2007-10-10"]
["UN505_1000","Specification and Requirements-Cavity","2005-08-16","2005-11-30",null,"2005-08-16","2005-11-30"]
["UN505_1005","Specification and Requirements-LTU RFBPM","2005-09-06","2006-02-28",null,"2005-09-06"]
["UN505_1010","Conceptual Design of LTU Cavity","2005-09-27","2006-01-31",null,"2005-09-27","2006-01-31"]
["UN505_1015","Identify Differences Between LTU & Undulator Cav","2005-10-21","2006-02-10",null,"2005-10-21"]
["UN505_1020","Design Review to Resolve Differences","2006-02-14","2006-02-17"]
["UN505_1025","Design Vacuum Window","2005-08-30","2005-11-30",null,"2005-08-30","2005-11-30"]
["UN505_1030","Procure Window for Braze Study","2005-09-06","2005-11-28",null,"2005-09-06","2005-11-28"]
["UN505_1035","Braze Study Windows","2005-11-01","2005-12-30",null,"2005-11-01","2005-12-30"]
["UN505_1040","Test Window for Leak Tightness & Elect Perform.","2006-01-03","2006-01-12",null,"2006-01-03","2006-01-12"]
["UN505_1045","Update Window Design","2006-01-13","2006-01-17",null,"2006-01-13","2006-01-17"]
["UN505_1050","Procure Prototype RF Windows","2005-10-26","2006-02-28",null,"2005-10-26"]
["UN505_1055","Design Cavity","2005-08-26","2005-11-30",null,"2005-08-26","2005-11-30"]
["UN505_1057","Fab Brass Body","2005-10-14","2006-01-20",null,"2005-10-14","2006-01-20"]
["UN505_1058","Bench Test Brass Body","2006-01-23","2006-02-28",null,"2006-01-23"]
["UN505_1060","Model and Simulate","2005-08-26","2005-11-30",null,"2005-08-26","2005-11-30"]
["UN505_1065","Machine First Body","2005-11-01","2006-02-28",null,"2005-11-01"]
["UN505_1070","Cold Test First Body","2006-03-01","2006-03-07"]
["UN505_1075","Braze First Body","2006-03-08","2006-03-28"]
["UN505_1080","Cold Test First Unit","2006-03-29","2006-04-04"]
["UN505_1085","Update Design","2006-05-11","2006-05-17"]
["UN505_1090","Machine Three Bodies","2006-05-18","2006-06-29"]
["UN505_1095","Cold Test Three Cavity Bodies","2006-06-30","2006-07-07"]
["UN505_1100","Braze Three Bodies","2006-07-10","2006-07-14"]
["UN505_1105","Cold Test Three Brazed Bodies","2006-07-17","2006-07-21"]
["UN505_1110","Select Waveguide Components","2005-09-26","2005-11-04",null,"2005-09-26","2005-11-04"]
["UN505_1115","Procure Cables & Components (4)","2005-12-01","2005-12-30",null,"2005-12-01","2005-12-30"]
["UN505_1120","Procure Waveguide Components","2005-10-17","2005-12-30",null,"2005-10-17","2005-12-30"]
["UN505_1125","Procure Measurement Equipment","2005-11-07","2006-02-10",null,"2005-11-07"]
["UN505_1130","Measure RF Performance of Components","2006-01-16","2006-02-03",null,"2006-01-16"]
["UN505_1135","Procure Waveguide Components (3)","2005-12-20","2006-03-10",null,"2005-12-20"]
["UN505_1140","Test Plan, Cold Test","2005-08-30","2006-02-10",null,"2005-08-30"]
["UN505_1145","Design Cold Test Measurement Equipment","2005-10-24","2006-01-17",null,"2005-10-24","2006-01-17"]
["UN505_1150","Procure and Fab Equipment","2005-10-18","2006-02-28",null,"2005-10-18"]
["UN505_1155","Assemble Cold Test Equipment","2006-01-03","2006-02-28",null,"2006-01-03"]
["UN505_1160","Test Plan, ITS Test","2005-09-06","2006-02-07",null,"2005-09-06"]
["UN505_1165","Design Spools & Supports","2005-10-24","2006-02-10",null,"2005-10-24"]
["UN505_1170","Procure and Fab ITS Equipment","2006-01-23","2006-03-02",null,"2006-01-23"]
["UN505_1175","Assemble ITS Equipment","2006-04-05","2006-04-12"]
["UN505_1180","Controls Integration in the ITS","2006-04-13","2006-04-26"]
["UN505_1185","ITS Test First Unit","2006-04-27","2006-07-21"]
["UN505_1190","Test Plan, Linac Test","2005-09-20","2006-02-28",null,"2005-09-20"]
["UN505_1195","Design Spools & Support Frame","2005-10-31","2006-02-10",null,"2005-10-31"]
["UN505_1200","Procure and Fab Linac Equipment","2006-02-13","2006-04-21"]
["UN505_1205","APS Linac Available for Installation","2006-04-25","2006-04-24"]
["UN505_1210","Assemble Linac Equipment","2006-07-20","2006-08-09"]
["UN505_1215","Controls Integration in the Linac","2006-07-27","2006-08-09"]
["UN505_1220","Linac Test Three Units","2006-08-10","2006-10-10"]
["UN505_2000","Specification and Requirements-X Band Rcvr","2005-08-16","2005-11-30",null,"2005-08-16","2005-11-30"]
["UN505_2005","Model and Simulate","2005-09-12","2006-01-31",null,"2005-09-12","2006-01-31"]
["UN505_2010","Specify Requirement for Purchased Units","2005-10-03","2005-11-30",null,"2005-10-03","2005-11-30"]
["UN505_2015","Procure Down Converter and LO","2005-10-17","2005-12-09",null,"2005-10-17","2005-12-09"]
["UN505_2020","Assemble Down Converter","2005-12-12","2006-01-30",null,"2005-12-12","2006-01-30"]
["UN505_2025","Tune and Test Units","2005-12-22","2006-01-30",null,"2005-12-22","2006-01-30"]
["UN505_2030","Controls Development","2006-01-31","2006-02-17",null,"2006-01-31"]
["UN505_2035","Review ITS Results","2006-02-20","2006-02-24"]
["UN505_2040","Update Down Converter and LO Specification","2006-02-27","2006-03-03"]
["UN505_2045","Procure Prototype Down Converter and LO(3)","2006-03-06","2006-04-28"]
["UN505_2050","Bench Test & Tune (3) DC and LO","2006-05-01","2006-05-19"]
["UN505_3000","Start RFBPM Preliminary Design","2006-08-14","2006-08-11"]
["UN505_3005","RFBPM Preliminary Design","2006-08-14","2006-09-01"]
["UN505_3006","LTU BPM Preliminary Design","2006-08-21","2006-09-01"]
["UN505_3007","Waveguide Preliminary Design","2006-08-21","2006-09-01"]
["UN505_3010","RFBPM Design Review","2006-09-05","2006-09-11"]
["UN505_3015","RFBPM Final Design","2006-09-12","2006-09-25"]
["UN505_3017","LTU BPM Final Design","2006-09-26","2006-10-09"]
["UN505_3018","Waveguide Final Design","2006-09-26","2006-10-09"]
["UN505_3020","RFBPM Design Complete","2006-10-10","2006-10-09"]
["UN505_3025","Prepare Bid of RF Cabling","2006-10-10","2006-10-11"]
["UN505_3028","Prepare Bid Waveguide","2006-10-10","2006-10-16"]
["UN505_3029","Prepare Bid Down Converter & LO","2006-10-10","2006-10-16"]
["UN505_3030","Prepare Bid of Copper Body Brazement","2006-10-10","2006-10-16"]
["UN505_3035","Prepare Bid of Support & Alignment Mechanism","2006-10-10","2006-10-23"]
["UN505_3040","Bid Process - RFBPM","2006-10-24","2006-10-25"]
["UN505_3045","Evaluate Bids - RFBPM","2006-10-26","2006-10-30"]
["UN505_3050","AWARD: Copper Body Brazement (35)","2006-10-31","2006-11-02"]
["UN505_3055","Copper Body Brazement (35) Support","2006-10-31","2006-11-02"]
["UN505_3056","AWARD: LTU BPM Brazements (8)","2006-10-31","2006-11-02"]
["UN505_3057","Rec: LTU BPM Brazements (8)","2006-11-03","2006-11-07"]
["UN505_3058","Rec: LTU BPM Waveguide (8)","2006-11-03","2006-11-07"]
["UN505_3059","Rec: LTU BPM Supports (8)","2006-11-03","2006-11-07"]
["UN505_3060","AWARD: Support & Alignment Mechanism (35)","2006-10-31","2006-11-02"]
["UN505_3065","Support & Alignment Mechanism (35) Support","2006-10-31","2006-11-02"]
["UN505_3066","Rec: Undulator Waveguide (35)","2006-11-03","2006-11-07"]
["UN505_3067","Rec: Undulator Down Converter (41)","2006-11-03","2006-11-07"]
["UN505_3068","Rec: Undulator Local Oscillator (41)","2006-11-03","2006-11-07"]
["UN505_3070","AWARD: RF Cabling (41)","2006-10-31","2006-11-02"]
["UN505_3075","RF Cabling (35) Support","2006-10-31","2006-11-02"]
["UN505_3080","AWARD: RFBPM Complete","2006-11-08","2006-11-07"]
["UN505_3085","Rec: 1st Art.Support & Alignment Mechanism","2006-11-08","2006-12-14"]
["UN505_3090","Rec: Support & Alignment Mechanism (34)","2006-11-08","2007-02-09"]
["UN505_3095","Rec: RF Cabling (35)","2006-11-08","2007-02-09"]
["UN505_3100","Rec: 1st Article Copper Body Brazement","2006-11-03","2007-02-09"]
["UN505_3105","QA: 1st Articles Copper Body Brazement/Supt","2007-02-12","2007-02-13"]
["UN505_3106","Cold Test 1st Article","2007-02-14","2007-02-16"]
["UN505_3110","Approve: 1st Articles Copper Body Brazement/Supt","2007-02-19","2007-02-20"]
["UN505_3115","Rec: Copper Body Brazement (34)","2007-02-21","2007-03-20"]
["UN505_3120","QA Production Lot","2007-03-21","2007-04-10"]
["UN505_3121","REC: LTU BPMs (6)","2006-11-08","2007-02-09"]
["UN505_3122","REC: Waveguide","2006-11-08","2007-01-16"]
["UN505_3123","Cold Test LTU BPM","2007-04-11","2007-04-20"]
["UN505_3124","Cold Test Undulator BPM","2007-04-11","2007-06-08"]
["UN505_3125","Approve Production Lot","2007-06-11","2007-06-12"]
["UN505_3126","Assemble/Test LTU BPM","2007-06-13","2007-06-22"]
["UN505_3127","Assemble/Test Undulator BPM","2007-06-13","2007-08-10"]
["UN505_3130","Pack RFBPM for Shipping","2007-08-13","2007-08-17"]
["UN505_3135","Write Shipping Paper Work-RFBPM","2007-08-20","2007-08-21"]
["UN505_3140","Transmit Engineering Data to SLAC-RFBPM","2007-08-20","2007-08-24"]
["UN505_3145","Develop Installation Plan-RFBPM","2007-08-27","2007-09-10"]
["UN505_3150","Review installation Plan-RFBPM","2007-09-11","2007-09-12"]
["UN505_3155","RFI: RFBPM","2007-09-13","2007-09-12"]
["UN505_3A58","AWARD: LTU BPM Waveguide (8)","2006-10-31","2006-11-02"]
["UN505_3A59","AWARD: LTU BPM Supports (8)","2006-10-31","2006-11-02"]
["UN505_3A66","AWARD: Undulator Waveguide (35)","2006-10-31","2006-11-02"]
["UN505_3A67","AWARD: Undulator Down Converter (41)","2006-10-31","2006-11-02"]
["UN505_3A68","AWARD: Undulator Local Oscillator (41)","2006-10-31","2006-11-02"]
["UN506_0010","Conceptual Design-BFW","2005-08-01","2005-10-31",null,"2005-08-01","2005-10-31"]
["UN506_0015","Establish Engineering Requirements","2005-08-01","2005-08-26",null,"2005-08-01","2005-08-26"]
["UN506_0020","Investigate Possible Radiation Damage to Compnts","2005-08-15","2005-12-16",null,"2005-08-15","2005-12-16"]
["UN506_0025","Investigate Perf of Commercial Position Devices","2005-08-15","2005-08-26",null,"2005-08-15","2005-08-26"]
["UN506_0030","Design Prototype Setup","2005-08-29","2005-12-16",null,"2005-08-29","2005-12-16"]
["UN506_0035","Prepare Test Plan","2005-09-27","2005-12-16",null,"2005-09-27","2005-12-16"]
["UN506_0040","Procure, Fab, Assemble Test Setup","2005-09-26","2006-03-02",null,"2005-09-26"]
["UN506_0045","Perform Tests","2006-03-03","2006-03-15"]
["UN506_0050","Write Report","2006-03-16","2006-03-29"]
["UN506_0055","Prepare ESD","2006-01-30","2006-02-28",null,"2006-01-30"]
["UN506_0060","Prepare Preliminary Design","2006-03-01","2006-04-25"]
["UN506_0063","Fixture and Tooling Design","2006-03-01","2006-04-25"]
["UN506_0065","Preliminary Design Review - Beam Finder Wire","2006-04-26","2006-05-23"]
["UN506_0070","Prepare Final Design Drawings & Specs","2006-05-24","2006-07-13"]
["UN506_0075","Prepare Engineering Calculations","2006-05-24","2006-07-13"]
["UN506_0080","Prepare Assembly Procedure","2006-05-24","2006-06-21"]
["UN506_0085","Prepare Acceptance Criteria List","2006-05-24","2006-06-21"]
["UN506_0090","Final Design Review - Beam Finder Wire","2006-07-14","2006-08-03"]
["UN506_0095","Incorporate Design Review Comments","2006-08-04","2006-08-17"]
["UN506_0100","Prepare Bid Pkg - Beam Finder Wire Components","2006-10-02","2006-10-06"]
["UN506_0105","Evaluate Bids - Beam Finder Wire Components","2006-11-06","2006-11-10"]
["UN506_0110","AWARD: Beam Finder Wire Components (33)","2006-11-13","2006-11-17"]
["UN506_0115","Receive Components (33) - Beam Finder Wire","2007-03-06","2007-03-19"]
["UN506_0117","Receive Beam Finder Wire Tooling","2007-03-06","2007-03-26"]
["UN506_0120","Inspect Beam Finder Wire Components","2007-03-27","2007-04-09"]
["UN506_0125","Fabricate & Final Weld","2007-04-10","2007-04-30"]
["UN506_0130","Clean","2007-05-01","2007-05-09"]
["UN506_0135","Bake Parts","2007-05-10","2007-05-16"]
["UN506_0140","Leak Check","2007-05-17","2007-05-31"]
["UN506_0145","Assemble Beam Finder Wire","2007-06-01","2007-06-21"]
["UN506_0150","Test Beam Finder Wire","2007-06-22","2007-07-13"]
["UN506_0155","Send Beam Finder Wire Documents to SLAC","2007-07-16","2007-07-20"]
["UN506_0160","RFI: Beam Finder Wire","2007-07-23","2007-07-20"]
["UN506_0200","AWARD: BFW Card Assembly (4)","2006-10-03","2006-10-09"]
["UN506_0205","Receive Components - BFW Card Assembly (4)","2007-01-23","2007-02-05"]
["UN506_0210","AWARD: Beam Finder Wire Assembly (3)","2006-10-03","2006-10-09"]
["UN506_0215","Rec: Beam Finder Wire Assembly (3)","2007-01-23","2007-02-05"]
["UN507_0010","Specification and Requirements - CM","2006-10-02","2006-10-13"]
["UN507_0020","Specification and Requirements - Cable","2006-10-16","2006-11-06"]
["UN507_0030","Purchase Cable","2006-11-07","2006-12-20"]
["UN507_0040","Preliminary Design - CM","2006-10-16","2006-11-03"]
["UN507_0050","Design Review - CM","2006-11-06","2006-11-10"]
["UN507_0060","Final Design - CM","2006-11-13","2006-12-05"]
["UN507_0070","Design Complete - CM","2006-12-06","2006-12-05"]
["UN507_0080","Prepare Bid of Charge Monitor Package","2006-12-06","2006-12-12"]
["UN507_0090","Bid Process - CM","2006-12-13","2007-01-24"]
["UN507_0100","AWARD: Charge Monitor Package (2)","2007-01-25","2007-01-31"]
["UN507_0102","AWARD: Charge Monitor Package (2) Sppt","2007-01-25","2007-01-31"]
["UN507_0105","AWARD: Charge Monitor Package (1)","2007-01-25","2007-01-31"]
["UN507_0110","AWARD: Charge Monitor","2007-02-01","2007-01-31"]
["UN507_0120","Rec: Charge Monitor Package (2)","2007-02-01","2007-03-14"]
["UN507_0125","Rec: Charge Monitor Package (1)","2007-02-01","2007-03-15"]
["UN507_0130","QA Production Lot","2007-03-15","2007-03-28"]
["UN507_0140","Approve Production Lot","2007-03-29","2007-04-02"]
["UN507_0141","Assemble Charge Monitor","2007-04-03","2007-04-05"]
["UN507_0142","Clean Charge Monitor","2007-04-06","2007-04-09"]
["UN507_0143","Leak Check Charge Monitor","2007-04-10","2007-04-11"]
["UN507_0144","Test Charge Monitor","2007-04-12","2007-04-13"]
["UN507_0150","Pack  Charge Monitor for Shipping","2007-04-16","2007-04-24"]
["UN507_0160","Write Shipping Paper Work","2007-04-25","2007-05-01"]
["UN507_0170","Transmit Engineering Data to Slac","2007-04-25","2007-05-01"]
["UN507_0180","Develop Installation Plan","2006-12-06","2006-12-29"]
["UN507_0190","Review installation Plan","2007-01-02","2007-01-10"]
["UN507_0200","Charge Monitor Arrive at SLAC","2007-05-03","2007-05-17"]
["UN507_0260","Commission  Charge Monitor","2007-11-05","2007-11-12"]
["UN507_0280","RFI - Charge Monitor","2007-05-02","2007-05-02"]
["UN508_0010","Specification and Requirements - Ch-D","2006-02-01","2006-02-14"]
["UN508_0020","Preliminary Design - Ch-D","2006-02-15","2006-04-11"]
["UN508_0030","Design Review - Ch-D","2006-04-12","2006-04-18"]
["UN508_0040","Final Design - Ch-D","2006-04-19","2006-05-31"]
["UN508_0050","Design Complete - Ch-D","2006-06-01","2006-05-31"]
["UN508_0060","Prepare Bid of Cherenkov Detector Package","2006-09-11","2006-09-20"]
["UN508_0070","Bid Process - Ch-D","2006-09-21","2006-10-25"]
["UN508_0072","Evaluate Bids - Ch-D","2006-10-26","2006-10-30"]
["UN508_0080","AWARD: Cherenkov Detector Package (35)","2006-10-31","2006-11-06"]
["UN508_0082","AWARD: Cherenkov Detector Package (4)","2006-10-31","2006-11-06"]
["UN508_0085","AWARD: Cherenkov Detector Package (35) Sppt","2006-10-31","2006-11-06"]
["UN508_0090","AWARD: Complete - Ch-D","2006-11-07","2006-11-06"]
["UN508_0095","Rec: 1st Article Cherenkov Detector","2006-11-07","2007-01-25"]
["UN508_0096","QA: 1st Article Cherenkov Detector","2007-01-26","2007-02-01"]
["UN508_0097","Approve: 1st Article Cherenkov Detector","2007-02-02","2007-02-05"]
["UN508_0100","Rec: Cherenkov Detector (34)","2007-02-06","2007-05-21"]
["UN508_0105","Rec: Cherenkov Detector (4)","2007-02-06","2007-03-20"]
["UN508_0110","QA Production Lot - Ch-D","2007-05-22","2007-06-05"]
["UN508_0120","Approve Production Lot-Ch-D","2007-06-06","2007-06-07"]
["UN508_0130","Pack  Cherenkov Detector for Shipping","2007-06-08","2007-06-14"]
["UN508_0140","Write Shipping Paper Work-Ch-D","2007-06-15","2007-06-21"]
["UN508_0150","Ship to SLAC-Ch-D","2007-06-22","2007-07-03"]
["UN508_0160","Transmit Engineering Data to Slac-Ch-D","2007-06-15","2007-06-21"]
["UN508_0170","Develop Installation Plan - Ch-D","2006-10-26","2006-11-08"]
["UN508_0180","Review installation Plan - Ch-D","2006-11-09","2006-11-20"]
["UN508_0182","RFI: Cherenkov Detector","2007-07-05","2007-07-03"]
["UN508_0190","Cherenkov Detector Arrive at SLAC","2007-07-05","2007-07-18"]
["UN508_0250","Commission  Cherenkov Detector","2007-03-21","2007-04-03"]
["UN509_0010","Specification and Requirements - RDM","2007-02-08","2007-02-21"]
["UN509_0090","Preliminary Design - RDM","2007-02-22","2007-03-28"]
["UN509_0100","Design Review - RDM","2007-03-29","2007-04-04"]
["UN509_0110","Final Design - RDM","2007-04-05","2007-05-02"]
["UN509_0120","Design Complete - RDM","2007-05-03","2007-05-02"]
["UN509_0130","Prepare Bid of RDM Package","2007-05-03","2007-05-16"]
["UN509_0140","Bid Process - RDM","2007-05-17","2007-06-28"]
["UN509_0141","Evaluate Bid - RDM","2007-06-29","2007-07-03"]
["UN509_0150","AWARD: RDM Package (1)","2007-07-05","2007-07-11"]
["UN509_0152","AWARD: RDM Package (1)","2007-07-05","2007-07-11"]
["UN509_0155","AWARD: RDM Package (1) Sppt","2007-07-05","2007-07-11"]
["UN509_0160","AWARD: of RDM Complete","2007-07-12","2007-07-11"]
["UN509_0170","Receive - RDM (1)","2007-07-12","2007-08-22"]
["UN509_0175","Rec: RDM (1)","2007-07-12","2007-08-22"]
["UN509_0180","QA - RDM","2007-08-23","2007-09-06"]
["UN509_0190","Approve - RDM","2007-09-07","2007-09-11"]
["UN509_0200","Pack RDM for Shipping","2007-09-12","2007-09-25"]
["UN509_0210","Write Shipping Paper Work - RDM","2007-09-26","2007-10-02"]
["UN509_0220","Ship RDM to SLAC","2007-10-03","2007-10-12"]
["UN509_0230","Transmit Engineering Data to Slac - RDM","2007-09-26","2007-10-02"]
["UN509_0232","RFI: Radiation Detection Monitor","2007-10-03","2007-10-02"]
["UN509_0240","Develop Installation Plan - RDM","2007-05-03","2007-05-23"]
["UN509_0250","Review installation Plan - RDM","2007-05-24","2007-05-31"]
["UN509_0260","RDM Arrive at SLAC","2007-10-15","2007-10-26"]
["UN509_0320","Commission RDM","2007-08-23","2007-08-31"]
["UN510_0100","Design RFBPM","2005-11-16","2006-01-30",null,"2005-11-16","2006-01-30"]
["UN510_0110","Get Quote on RFBPM","2006-01-31","2006-01-31",null,"2006-01-31","2006-01-31"]
["UN510_0120","Purchase RFBPM","2006-01-30","2006-03-06",null,"2006-01-30"]
["UN510_0200","Design RFBPM Support","2005-12-15","2006-02-28",null,"2005-12-15"]
["UN510_0210","Get Quote on RFBPM Support","2006-01-31","2006-02-08",null,"2006-01-31"]
["UN510_0220","Purchase RFBPM Support","2006-01-30","2006-03-01",null,"2006-01-30"]
["UN510_0300","Design Cherenkov Detector","2006-01-03","2006-01-24",null,"2006-01-03","2006-01-24"]
["UN510_0310","Get Quote on Cherenkov Detector","2006-01-25","2006-01-31",null,"2006-01-25","2006-01-31"]
["UN510_0320","Purchase Cherenkov Detector","2006-01-23","2006-03-22",null,"2006-01-23"]
["UN511_0010","Specification and Requirements - Sup S","2007-05-03","2007-05-16"]
["UN511_0020","Preliminary Design - Sup S","2007-05-17","2007-07-13"]
["UN511_0030","Design Review - Sup S","2008-01-22","2008-01-28"]
["UN511_0040","Final Design - Sup S","2008-01-29","2008-02-21"]
["UN511_0050","Design Complete - Sup S","2008-02-22","2008-02-21"]
["UN511_0060","Prepare Bid of Misc Shielding","2008-04-18","2008-05-01"]
["UN511_0070","Prepare Bid of Shielding Supports","2008-05-02","2008-05-13"]
["UN511_0080","Bid Process - Sup S","2008-05-14","2008-06-18"]
["UN511_0090","AWARD: Procurement of Misc Shielding","2008-06-19","2008-06-25"]
["UN511_0095","AWARD: Procurement of Misc Shielding Sppt","2008-06-19","2008-06-25"]
["UN511_0100","AWARD: Procurement of Shielding Supports","2008-06-19","2008-06-25"]
["UN511_0105","AWARD: Procurement of Shielding Supports Sppt","2008-06-19","2008-06-25"]
["UN511_0110","AWARD: Supplemental Shielding Complete","2008-06-26","2008-06-25"]
["UN511_0120","Receive Production Lot - Sup S","2008-06-26","2008-08-07"]
["UN511_0130","QA Production Lot - Sup S","2008-08-08","2008-08-21"]
["UN511_0140","Approve Production Lot - Sup S","2008-08-22","2008-08-25"]
["UN511_0150","Pack  Supplemental Shielding for Shipping-Sup","2008-08-26","2008-09-09"]
["UN511_0160","Write Shipping Paper Work - Sup S","2008-09-10","2008-09-23"]
["UN511_0170","Ship to SLAC - Sup S","2008-09-24","2008-10-03"]
["UN511_0180","Transmit Engineering Data to Slac - Sup S","2008-09-10","2008-09-17"]
["UN511_0182","RFI: Supplemental Shielding","2008-10-06","2008-10-03"]
["UN511_0190","Develop Installation Plan - Sup S","2008-02-22","2008-03-20"]
["UN511_0200","Review installation Plan - Sup S","2008-03-21","2008-03-28"]
["UN511_0205","RFI Supplemental Shielding","2008-03-31","2008-03-28"]
["UN511_0210","Supplemental Shielding Arrive at SLAC","2008-10-06","2008-10-20"]
["UN511_0220","Install Supplemental Shielding","2008-10-21","2008-11-18"]
["UN511_0230","Inspect Supplemental Shielding Placement and S","2008-11-19","2008-11-26"]
["UN511_0240","Supplemental Shielding Available","2008-12-01","2008-11-26"]
["UN511_0250","Commission  Supplemental Shielding","2008-12-01","2009-01-02"]
["UN511_0260","Complete - Sup S Testing","2009-01-05","2009-01-02"]
["UN601_0000","REQD: Undulator #1 RFI","2007-10-05","2007-10-04"]
["UN601_0005","REQD: Undulator #2 RFI","2007-10-05","2007-10-04"]
["UN601_0010","REQD: Undulator #3 RFI","2007-10-04","2007-10-03"]
["UN601_0015","REQD: Undulator #4 RFI","2007-10-04","2007-10-03"]
["UN601_0020","REQD: Undulator #5 RFI","2007-10-04","2007-10-03"]
["UN601_0025","REQD: Undulator #7 RFI","2007-10-04","2007-10-03"]
["UN601_0030","REQD: Undulator #6 RFI","2007-10-04","2007-10-03"]
["UN601_0035","REQD: Undulator #9 RFI","2007-10-04","2007-10-03"]
["UN601_0040","REQD: Undulator #8 RFI","2007-10-04","2007-10-03"]
["UN601_0045","REQD: Undulator #11 RFI","2007-10-11","2007-10-10"]
["UN601_0050","REQD: Undulator #10 RFI","2007-10-08","2007-10-05"]
["UN601_0055","REQD: Undulator #13 RFI","2007-10-11","2007-10-10"]
["UN601_0060","REQD: Undulator #12 RFI","2007-10-11","2007-10-10"]
["UN601_0065","REQD: Undulator #15 RFI","2007-10-11","2007-10-10"]
["UN601_0070","REQD: Undulator #14 RFI","2007-10-11","2007-10-10"]
["UN601_0075","REQD: Undulator #17 RFI","2007-10-11","2007-10-10"]
["UN601_0080","REQD: Undulator #16 RFI","2007-10-11","2007-10-10"]
["UN601_0085","REQD: Undulator #19 RFI","2007-10-15","2007-10-12"]
["UN601_0090","REQD: Undulator #18 RFI","2007-10-11","2007-10-10"]
["UN601_0095","REQD: Undulator #21 RFI","2007-12-05","2007-12-04"]
["UN601_0100","REQD: Undulator #20 RFI","2007-12-05","2007-12-04"]
["UN601_0105","REQD: Undulator #23 RFI","2007-12-05","2007-12-04"]
["UN601_0110","REQD: Undulator #22 RFI","2007-12-05","2007-12-04"]
["UN601_0115","REQD: Undulator #25 RFI","2008-01-11","2008-01-10"]
["UN601_0120","REQD: Undulator #24 RFI","2008-01-11","2008-01-10"]
["UN601_0125","REQD: Undulator #27 RFI","2008-02-08","2008-02-07"]
["UN601_0130","REQD: Undulator #26 RFI","2008-01-11","2008-01-10"]
["UN601_0135","REQD: Undulator #29 RFI","2008-03-07","2008-03-06"]
["UN601_0140","REQD: Undulator #28 RFI","2008-02-08","2008-02-07"]
["UN601_0145","REQD: Undulator #31 RFI","2008-03-07","2008-03-06"]
["UN601_0150","REQD: Undulator #30 RFI","2008-03-07","2008-03-06"]
["UN601_0155","REQD: Undulator #33 RFI","2008-03-10","2008-03-07"]
["UN601_0160","REQD: Undulator #32 RFI","2008-03-10","2008-03-07"]
["UN601_0307","ALIGNMENT HW AND SW SUMMARY","2006-02-01","2010-04-05"]
["UN601_0310","Specify Alignment Hardware","2005-10-03","2005-10-28",null,"2005-10-03","2005-10-28"]
["UN601_0315","Alignment Hardware/Software Acceptance Testing","2007-03-12","2007-05-04"]
["UN601_0320","Procure Laser Trackers (2)","2006-09-01","2007-03-09"]
["UN601_0325","Procure Retro Reflectors","2006-09-01","2006-11-02"]
["UN601_0330","Procure Reference Points","2006-09-01","2006-11-02"]
["UN601_0335","Procure Wire Reference Fiducials","2006-06-01","2006-08-02"]
["UN601_0340","Procure Digital Level","2006-06-01","2006-08-02"]
["UN601_0345","Procure Absolute Wire Finder","2006-06-01","2006-08-02"]
["UN601_0350","Procure Portable HLS","2005-11-23","2006-10-16",null,"2005-11-23"]
["UN601_0355","Procure Misc Tools","2006-06-01","2006-08-24"]
["UN601_0360","Procure Fixturing","2006-06-01","2006-08-24"]
["UN601_0365","Procure Data Analysis Software Extension","2006-04-12","2006-08-03"]
["UN601_0367","HYDROSTATIC LEVEL SYSTEM SUMMARY","2006-02-01","2010-04-05"]
["UN601_0368","HLS Systems Engineering (PED)","2005-06-01","2006-02-15",null,"2005-06-01"]
["UN601_0369","HLS Systems Engineering (CNST)","2006-02-16","2008-08-29"]
["UN601_0370","Conceptual Design","2005-10-03","2005-10-07",null,"2005-10-03","2005-10-07"]
["UN601_0375","Engineer Layout","2005-10-03","2006-01-31",null,"2005-10-03","2006-01-31"]
["UN601_0380","Design Layout","2005-12-01","2006-02-28",null,"2005-12-01"]
["UN601_0385","Engineer Support System","2005-11-15","2006-02-28",null,"2005-11-15"]
["UN601_0390","Design Support System","2006-03-01","2006-04-06"]
["UN601_0395","Design Data Acquisition System","2005-10-03","2006-02-10",null,"2005-10-03"]
["UN601_0400","DAS Drafting & Doc","2005-11-14","2006-02-28",null,"2005-11-14"]
["UN601_0405","Specify Components","2005-11-01","2006-02-10",null,"2005-11-01"]
["UN601_0410","Specify Piping","2005-11-01","2005-11-01",null,"2005-11-01","2005-11-01"]
["UN601_0415","Specify Support System","2006-04-07","2006-04-07"]
["UN601_0420","Specify Data Acquisition System","2005-11-14","2005-11-18",null,"2005-11-14","2005-11-18"]
["UN601_0425","Specify Cables","2005-11-14","2005-11-15",null,"2005-11-14","2005-11-15"]
["UN601_0430","Procure Capacitive Sensors","2006-04-03","2006-09-29"]
["UN601_0432","Procure Acoustic Sensors","2006-04-03","2006-09-29"]
["UN601_0435","Procure Support System","2006-04-10","2006-10-06"]
["UN601_0440","Procure Re-Fill Station","2006-04-03","2006-09-29"]
["UN601_0445","Procure Piping","2006-04-03","2006-09-29"]
["UN601_0450","Procure Data Acquisition System","2006-01-23","2006-07-21",null,"2006-01-23"]
["UN601_0455","Procure Cables","2006-04-03","2006-09-29"]
["UN601_0457","HLS Components available for Install","2006-02-01","2006-01-31"]
["UN601_0460","Develop Data Acquisition S/W","2006-01-17","2006-04-11",null,"2006-01-17"]
["UN601_0465","Develop Control System Connection","2007-01-02","2007-06-29"]
["UN601_0467","WIRE MONITORING SYSTEM SUMMARY","2006-02-01","2010-04-05"]
["UN601_0468","Stretched Wire Systems Engineering (PED)","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["UN601_0469","Stretched Wire Systems Engineering (CNST)","2005-10-03","2006-01-31",null,"2005-10-03","2006-01-31"]
["UN601_0470","Engineer Global Layout","2005-10-03","2005-10-20",null,"2005-10-03","2005-10-20"]
["UN601_0475","Design Global Layout","2005-12-05","2006-02-14",null,"2005-12-05"]
["UN601_0670","Procure Wire Monitors","2006-06-01","2006-09-29"]
["UN601_0675","Procure Wire Monitor Supports","2006-06-01","2006-09-29"]
["UN601_0680","Procure Wire Tubes","2006-06-01","2006-09-29"]
["UN601_0685","Procure Wire Tube Supports","2006-06-01","2006-09-29"]
["UN601_0690","Procure Demodulation Modules","2006-06-01","2006-11-30"]
["UN601_0695","Procure Quad ADC","2006-02-01","2006-09-29"]
["UN601_0700","Procure RF Signal Processing","2006-02-01","2006-09-29"]
["UN601_0705","Procure RF Signal Distribution","2006-08-01","2006-11-30"]
["UN601_0710","Procure RF Power Amplifier","2006-08-01","2006-09-29"]
["UN601_0712","Procure Cables","2006-05-01","2006-08-31"]
["UN601_0715","Procure Crates","2006-08-01","2006-11-30"]
["UN601_0720","Procure Data Acquisition System","2006-05-01","2006-11-30"]
["UN601_0723","Stretched Wire Comp available for installation","2006-02-01","2006-01-31"]
["UN601_0725","Develop Data Acquisition Software","2006-07-03","2007-01-11"]
["UN601_0730","Develop Local Control Program","2006-07-03","2007-01-12"]
["UN601_0731","Specs of WPM Installation at U-Hall","2007-07-02","2008-02-29"]
["UN601_0732","Control of WPM Installation at U-Hall","2008-01-31","2008-02-27"]
["UN601_0733","Commissioning of WPM at U-Hall","2008-04-01","2008-06-30"]
["UN601_0740","ASSY & PREALIGN GRANITE GIRDERS SUMMARY","2006-06-08","2006-08-28"]
["UN601_0750","GIRDER #1 SUMMARY","2006-06-08","2006-06-16"]
["UN601_0755","Set Up Girder","2006-06-08","2006-06-08"]
["UN601_0756","Install Cable Tray","2007-05-04","2007-05-10"]
["UN601_0757","Pull Cables","2007-05-11","2007-05-17"]
["UN601_0758","Install Quad Power Supplies","2007-05-18","2007-05-24"]
["UN601_0759","100% Quad Power Supplies Installed","2008-03-24","2008-03-28"]
["UN601_0760","Mount Adjustable Feet","2006-06-08","2006-06-08"]
["UN601_0765","Mount Mechanical Adjustment System","2006-06-09","2006-06-09"]
["UN601_0770","Mount CAM Movers","2006-06-12","2006-06-12"]
["UN601_0775","Mount Temp Acq Sys Components","2006-06-12","2006-06-12"]
["UN601_0780","HLS Pipe Installation & Welding","2006-06-13","2006-06-13"]
["UN601_0785","Align Support Girder wrt Feet","2006-06-14","2006-06-15"]
["UN601_0790","Attach Insulation","2006-06-16","2006-06-16"]
["UN601_0795","Girder #1 RFI","2006-06-19","2006-06-16"]
["UN601_0800","GIRDER #2 SUMMARY","2006-06-15","2006-06-23"]
["UN601_0805","Set Up Girder","2006-06-15","2006-06-15"]
["UN601_0810","Mount Adjustable Feet","2006-06-15","2006-06-15"]
["UN601_0815","Mount Mechanical Adjustment System","2006-06-16","2006-06-16"]
["UN601_0820","Mount CAM Movers","2006-06-19","2006-06-19"]
["UN601_0825","Mount Temp Acq Sys Components","2006-06-19","2006-06-19"]
["UN601_0830","HLS Pipe Installation & Welding","2006-06-20","2006-06-20"]
["UN601_0835","Align Support Girder wrt Feet","2006-06-21","2006-06-22"]
["UN601_0840","Attach Insulation","2006-06-23","2006-06-23"]
["UN601_0845","Girder #2 RFI","2006-06-26","2006-06-23"]
["UN601_0850","GIRDER #3 SUMMARY","2006-06-22","2006-06-30"]
["UN601_0855","Set Up Girder","2006-06-22","2006-06-22"]
["UN601_0860","Mount Adjustable Feet","2006-06-22","2006-06-22"]
["UN601_0865","Mount Mechanical Adjustment System","2006-06-23","2006-06-23"]
["UN601_0870","Mount CAM Movers","2006-06-26","2006-06-26"]
["UN601_0875","Mount Temp Acq Sys Components","2006-06-26","2006-06-26"]
["UN601_0880","HLS Pipe Installation & Welding","2006-06-27","2006-06-27"]
["UN601_0885","Align Support Girder wrt Feet","2006-06-28","2006-06-29"]
["UN601_0890","Attach Insulation","2006-06-30","2006-06-30"]
["UN601_0895","Girder #3 RFI","2006-07-03","2006-06-30"]
["UN601_0900","GIRDER #4 SUMMARY","2006-06-29","2006-07-10"]
["UN601_0905","Set Up Girder","2006-06-29","2006-06-29"]
["UN601_0910","Mount Adjustable Feet","2006-06-29","2006-06-29"]
["UN601_0915","Mount Mechanical Adjustment System","2006-06-30","2006-06-30"]
["UN601_0920","Mount CAM Movers","2006-07-03","2006-07-03"]
["UN601_0925","Mount Temp Acq Sys Components","2006-07-03","2006-07-03"]
["UN601_0930","HLS Pipe Installation & Welding","2006-07-05","2006-07-05"]
["UN601_0935","Align Support Girder wrt Feet","2006-07-06","2006-07-07"]
["UN601_0940","Attach Insulation","2006-07-10","2006-07-10"]
["UN601_0945","Girder #4 RFI","2006-07-11","2006-07-10"]
["UN601_0950","GIRDER #5 SUMMARY","2006-07-07","2006-07-17"]
["UN601_0955","Set Up Girder","2006-07-07","2006-07-07"]
["UN601_0960","Mount Adjustable Feet","2006-07-07","2006-07-07"]
["UN601_0965","Mount Mechanical Adjustment System","2006-07-10","2006-07-10"]
["UN601_0970","Mount CAM Movers","2006-07-11","2006-07-11"]
["UN601_0975","Mount Temp Acq Sys Components","2006-07-11","2006-07-11"]
["UN601_0980","HLS Pipe Installation & Welding","2006-07-12","2006-07-12"]
["UN601_0985","Align Support Girder wrt Feet","2006-07-13","2006-07-14"]
["UN601_0990","Attach Insulation","2006-07-17","2006-07-17"]
["UN601_0995","Girder #5 RFI","2006-07-18","2006-07-17"]
["UN601_1000","GIRDER #6 SUMMARY","2006-07-14","2006-07-24"]
["UN601_1005","Set Up Girder","2006-07-14","2006-07-14"]
["UN601_1010","Mount Adjustable Feet","2006-07-14","2006-07-14"]
["UN601_1015","Mount Mechanical Adjustment System","2006-07-17","2006-07-17"]
["UN601_1020","Mount CAM Movers","2006-07-18","2006-07-18"]
["UN601_1025","Mount Temp Acq Sys Components","2006-07-18","2006-07-18"]
["UN601_1030","HLS Pipe Installation & Welding","2006-07-19","2006-07-19"]
["UN601_1035","Align Support Girder wrt Feet","2006-07-20","2006-07-21"]
["UN601_1040","Attach Insulation","2006-07-24","2006-07-24"]
["UN601_1045","Girder #6 RFI","2006-07-25","2006-07-24"]
["UN601_1050","GIRDER #7 SUMMARY","2006-07-21","2006-07-31"]
["UN601_1055","Set Up Girder","2006-07-21","2006-07-21"]
["UN601_1060","Mount Adjustable Feet","2006-07-21","2006-07-21"]
["UN601_1065","Mount Mechanical Adjustment System","2006-07-24","2006-07-24"]
["UN601_1070","Mount CAM Movers","2006-07-25","2006-07-25"]
["UN601_1075","Mount Temp Acq Sys Components","2006-07-25","2006-07-25"]
["UN601_1080","HLS Pipe Installation & Welding","2006-07-26","2006-07-26"]
["UN601_1085","Align Support Girder wrt Feet","2006-07-27","2006-07-28"]
["UN601_1090","Attach Insulation","2006-07-31","2006-07-31"]
["UN601_1095","Girder #7 RFI","2006-08-01","2006-07-31"]
["UN601_1100","GIRDER #8 SUMMARY","2006-07-28","2006-08-07"]
["UN601_1105","Set Up Girder","2006-07-28","2006-07-28"]
["UN601_1110","Mount Adjustable Feet","2006-07-28","2006-07-28"]
["UN601_1115","Mount Mechanical Adjustment System","2006-07-31","2006-07-31"]
["UN601_1120","Mount CAM Movers","2006-08-01","2006-08-01"]
["UN601_1125","Mount Temp Acq Sys Components","2006-08-01","2006-08-01"]
["UN601_1130","HLS Pipe Installation & Welding","2006-08-02","2006-08-02"]
["UN601_1135","Align Support Girder wrt Feet","2006-08-03","2006-08-04"]
["UN601_1140","Attach Insulation","2006-08-07","2006-08-07"]
["UN601_1145","Girder #8 RFI","2006-08-08","2006-08-07"]
["UN601_1150","GIRDER #9 SUMMARY","2006-08-04","2006-08-14"]
["UN601_1155","Set Up Girder","2006-08-04","2006-08-04"]
["UN601_1160","Mount Adjustable Feet","2006-08-04","2006-08-04"]
["UN601_1165","Mount Mechanical Adjustment System","2006-08-07","2006-08-07"]
["UN601_1170","Mount CAM Movers","2006-08-08","2006-08-08"]
["UN601_1175","Mount Temp Acq Sys Components","2006-08-08","2006-08-08"]
["UN601_1180","HLS Pipe Installation & Welding","2006-08-09","2006-08-09"]
["UN601_1185","Align Support Girder wrt Feet","2006-08-10","2006-08-11"]
["UN601_1190","Attach Insulation","2006-08-14","2006-08-14"]
["UN601_1195","Girder #9 RFI","2006-08-15","2006-08-14"]
["UN601_1200","GIRDER #10 SUMMARY","2006-08-11","2006-08-21"]
["UN601_1205","Set Up Girder","2006-08-11","2006-08-11"]
["UN601_1210","Mount Adjustable Feet","2006-08-11","2006-08-11"]
["UN601_1215","Mount Mechanical Adjustment System","2006-08-14","2006-08-14"]
["UN601_1220","Mount CAM Movers","2006-08-15","2006-08-15"]
["UN601_1225","Mount Temp Acq Sys Components","2006-08-15","2006-08-15"]
["UN601_1230","HLS Pipe Installation & Welding","2006-08-16","2006-08-16"]
["UN601_1235","Align Support Girder wrt Feet","2006-08-17","2006-08-18"]
["UN601_1240","Attach Insulation","2006-08-21","2006-08-21"]
["UN601_1245","Girder #10 RFI","2006-08-22","2006-08-21"]
["UN601_1250","GIRDER #11 SUMMARY","2006-08-18","2006-08-28"]
["UN601_1255","Set Up Girder","2006-08-18","2006-08-18"]
["UN601_1260","Mount Adjustable Feet","2006-08-18","2006-08-18"]
["UN601_1265","Mount Mechanical Adjustment System","2006-08-21","2006-08-21"]
["UN601_1270","Mount CAM Movers","2006-08-22","2006-08-22"]
["UN601_1275","Mount Temp Acq Sys Components","2006-08-22","2006-08-22"]
["UN601_1280","HLS Pipe Installation & Welding","2006-08-23","2006-08-23"]
["UN601_1285","Align Support Girder wrt Feet","2006-08-24","2006-08-25"]
["UN601_1290","Attach Insulation","2006-08-28","2006-08-28"]
["UN601_1295","Girder #11 RFI","2006-08-29","2006-08-28"]
["UN601_1300","ALIGNMT LAYOUT COMPUTATIONS & MONITORING SUMMARY","2006-08-04","2007-05-24"]
["UN601_1305","Vertical Monitoring of Tunnel Floor","2006-08-04","2006-08-09"]
["UN601_1310","Vertical Monitoring of Tunnel Floor","2006-08-10","2006-08-15"]
["UN601_1315","Vertical Monitoring of Tunnel Floor","2006-08-16","2006-08-21"]
["UN601_1320","Vertical Monitoring of Tunnel Floor","2006-08-16","2006-08-21"]
["UN601_1325","Vertical Monitoring of Tunnel Floor","2006-08-22","2006-08-25"]
["UN601_1330","Design Network","2007-05-04","2007-05-15"]
["UN601_1335","Computation of Layout Parameters","2007-05-16","2007-05-22"]
["UN601_1340","Quality Control","2007-05-23","2007-05-24"]
["UN601_1345","INSTALLATION & ALIGNMENT SUMMARY","2007-05-16","2008-07-15"]
["UN601_1350","NETWORK INSTALLATION SUMMARY","2007-05-16","2007-05-22"]
["UN601_1355","Layout Network Points","2007-05-16","2007-05-17"]
["UN601_1360","Network Installation","2007-05-16","2007-05-22"]
["UN601_1365","ALIGNMENT REFERENCE NETWORK MSMTS SUMMARY","2007-05-23","2007-06-07"]
["UN601_1370","Measurements(Laser Tracker,Level,Total Station)","2007-05-23","2007-06-04"]
["UN601_1375","Data Evaluation","2007-05-30","2007-06-05"]
["UN601_1380","Quality Control","2007-06-06","2007-06-07"]
["UN601_1381","Mark Support Bolts on Floor","2007-06-08","2007-06-11"]
["UN601_1382","Quality Control","2007-06-11","2007-06-12"]
["UN601_1385","FOOT PLATE INSTALLATION SUMMARY","2007-06-13","2007-07-03"]
["UN601_1390","Drill Holes","2007-06-13","2007-06-14"]
["UN601_1395","Set Studs","2007-06-13","2007-06-14"]
["UN601_1400","Install Plates, Pre-Set Height","2007-06-13","2007-06-14"]
["UN601_1405","Prealign Plates to 0.5mm","2007-06-14","2007-06-22"]
["UN601_1410","Quality Control: Map Plate Positions","2007-06-15","2007-06-18"]
["UN601_1415","Quality Control: Data Evaluation","2007-06-19","2007-06-19"]
["UN601_1420","Grout Plates","2007-06-20","2007-06-22"]
["UN601_1425","Quality Control: Map Plate Positions","2007-06-25","2007-06-26"]
["UN601_1430","Quality Control: Data Evaluation","2007-06-27","2007-06-27"]
["UN601_1435","Grout Plates","2007-06-28","2007-07-02"]
["UN601_1440","Clean Tunnel","2007-07-02","2007-07-03"]
["UN601_1470","Stretched Wire Systems Engineering (CNST)","2006-02-01","2008-08-29",null,"2006-02-01"]
["UN601_1475","Drawings and Documentation","2006-01-03","2008-07-30",null,"2006-01-03"]
["UN601_1480","Revise Mechanics","2006-07-03","2006-08-28"]
["UN601_1485","Design & Specs Mechanics","2006-02-06","2006-06-07"]
["UN601_1486","Revise Electronics","2006-06-08","2006-09-08"]
["UN601_1487","Design & Specs Electronics","2006-07-11","2006-12-15"]
["UN601_1488","Design & Specs Wire Test Facility","2006-07-11","2006-12-15"]
["UN601_1489","System Assembly at Test Facility","2007-01-02","2007-05-01"]
["UN601_1490","GRANITE GIRDER & EXIT/ENTR SECTION SUPTS INSTALL","2007-08-13","2007-08-28"]
["UN601_1491","System Measurements at Test Facility","2007-07-02","2007-12-14"]
["UN601_1492","Wire Monitor Calibration","2007-09-04","2008-02-29"]
["UN601_1500","Exit Section Supts Transport & Install","2007-08-13","2007-08-14"]
["UN601_1510","Granite Girder #11 Transport & Install","2007-08-15","2007-08-16"]
["UN601_1515","Granite Girder #10 Transport & Install","2007-08-17","2007-08-17"]
["UN601_1520","Granite Girder #9 Transport & Install","2007-08-20","2007-08-20"]
["UN601_1525","Granite Girder #8 Transport & Install","2007-08-20","2007-08-20"]
["UN601_1530","Granite Girder #7 Transport & Install","2007-08-21","2007-08-21"]
["UN601_1535","Granite Girder #6 Transport & Install","2007-08-22","2007-08-22"]
["UN601_1540","Granite Girder #5 Transport & Install","2007-08-23","2007-08-23"]
["UN601_1545","Granite Girder #4 Transport & Install","2007-08-24","2007-08-24"]
["UN601_1550","Granite Girder #3 Transport & Install","2007-08-24","2007-08-24"]
["UN601_1555","Granite Girder #2 Transport & Install","2007-08-27","2007-08-27"]
["UN601_1560","Granite Girder #1 Transport & Install","2007-08-27","2007-08-27"]
["UN601_1565","Exit Section Supports Transport & Install","2007-08-28","2007-08-28"]
["UN601_1570","RE-MEASURE ALIGNMENT REFERENCE NETWORK","2007-08-24","2007-09-06"]
["UN601_1575","Measurements(Laser Tracker,Level,Total Station)","2007-08-24","2007-08-29"]
["UN601_1580","Stretched Wire Measurements","2007-08-24","2007-08-29"]
["UN601_1585","Data Evaluation","2007-08-24","2007-08-29"]
["UN601_1590","Quality Control","2007-08-30","2007-09-06"]
["UN601_1595","PRE-ALIGNMENT","2007-09-07","2007-09-10"]
["UN601_1600","TABLES #6 - 11","2007-09-07","2007-09-24"]
["UN601_1605","Level Granite Girders","2007-09-07","2007-09-12"]
["UN601_1610","Set Cam Movers to Zero","2007-09-07","2007-09-10"]
["UN601_1615","Align Mech Undulator Supports to 250 Micron","2007-09-12","2007-09-24"]
["UN601_1620","GIRDERS #1 - 5","2007-09-07","2007-09-10"]
["UN601_1625","Level Granite Girders","2007-09-07","2007-09-12"]
["UN601_1630","Set Cam Movers to Zero","2007-09-07","2007-09-10"]
["UN601_1635","Align Mech Undulator Supports to 250 Micron","2007-08-27","2007-09-10"]
["UN601_1645","Cradle #1 Transport and Install","2007-10-05","2007-10-05"]
["UN601_1650","Cradle #2 Transport and Install","2007-10-05","2007-10-05"]
["UN601_1655","Set up Cradle on CMM - 03","2007-10-05","2007-10-05"]
["UN601_1656","Align Cradle System - 03","2007-10-08","2007-10-09"]
["UN601_1657","Component Handling - 03","2007-10-10","2007-10-10"]
["UN601_1661","Set up Cradle on CMM - 04","2007-10-11","2007-10-11"]
["UN601_1662","Align Cradle System - 04","2007-10-12","2007-10-15"]
["UN601_1663","Component Handling - 04","2007-10-16","2007-10-16"]
["UN601_1665","Set up Cradle on CMM - 05","2007-10-17","2007-10-17"]
["UN601_1666","Align Cradle System - 05","2007-10-18","2007-10-19"]
["UN601_1667","Component Handling - 05","2007-10-22","2007-10-22"]
["UN601_1670","Set up Cradle on CMM - 06","2007-10-23","2007-10-23"]
["UN601_1671","Align Cradle System - 06","2007-10-24","2007-10-25"]
["UN601_1672","Component Handling - 06","2007-10-26","2007-10-26"]
["UN601_1675","Set up Cradle on CMM - 07","2007-10-29","2007-10-29"]
["UN601_1676","Align Cradle System - 07","2007-10-30","2007-10-31"]
["UN601_1677","Component Handling - 07","2007-11-01","2007-11-01"]
["UN601_1680","Set up Cradle on CMM - 08","2007-11-02","2007-11-02"]
["UN601_1681","Align Cradle System - 08","2007-11-05","2007-11-06"]
["UN601_1682","Component Handling - 08","2007-11-07","2007-11-07"]
["UN601_1685","Set up Cradle on CMM - 09","2007-11-08","2007-11-08"]
["UN601_1686","Align Cradle System - 09","2007-11-09","2007-11-12"]
["UN601_1687","Component Handling - 09","2007-11-13","2007-11-13"]
["UN601_1690","Set up Cradle on CMM - 10","2007-11-14","2007-11-14"]
["UN601_1691","Align Cradle System - 10","2007-11-15","2007-11-16"]
["UN601_1692","Component Handling - 10","2007-11-19","2007-11-19"]
["UN601_1695","Set up Cradle on CMM - 11","2007-11-20","2007-11-20"]
["UN601_1696","Align Cradle System - 11","2007-11-21","2007-11-26"]
["UN601_1697","Component Handling - 11","2007-11-27","2007-11-27"]
["UN601_1700","Set up Cradle on CMM - 12","2007-11-28","2007-11-28"]
["UN601_1701","Align Cradle System - 12","2007-11-29","2007-11-30"]
["UN601_1702","Component Handling - 12","2007-12-03","2007-12-03"]
["UN601_1705","Set up Cradle on CMM - 13","2007-12-04","2007-12-04"]
["UN601_1706","Align Cradle System - 13","2007-12-05","2007-12-06"]
["UN601_1707","Component Handling - 13","2007-12-07","2007-12-07"]
["UN601_1710","Set up Cradle on CMM - 14","2007-12-10","2007-12-10"]
["UN601_1711","Align Cradle System - 14","2007-12-11","2007-12-12"]
["UN601_1712","Component Handling - 14","2007-12-13","2007-12-13"]
["UN601_1715","Set up Cradle on CMM - 15","2007-12-14","2007-12-14"]
["UN601_1716","Align Cradle System - 15","2008-01-02","2008-01-03"]
["UN601_1717","Component Handling - 15","2008-01-04","2008-01-04"]
["UN601_1720","Set up Cradle on CMM - 16","2008-01-07","2008-01-07"]
["UN601_1721","Align Cradle System - 16","2008-01-08","2008-01-09"]
["UN601_1722","Component Handling - 16","2008-01-10","2008-01-10"]
["UN601_1725","Set up Cradle on CMM - 17","2008-01-11","2008-01-11"]
["UN601_1726","Align Cradle System - 17","2008-01-14","2008-01-15"]
["UN601_1727","Component Handling - 17","2008-01-16","2008-01-16"]
["UN601_1730","Set up Cradle on CMM - 18","2008-01-17","2008-01-17"]
["UN601_1731","Align Cradle System - 18","2008-01-18","2008-01-22"]
["UN601_1732","Component Handling - 18","2008-01-23","2008-01-23"]
["UN601_1735","Set up Cradle on CMM - 19","2008-01-24","2008-01-24"]
["UN601_1736","Align Cradle System - 19","2008-01-25","2008-01-28"]
["UN601_1737","Component Handling - 19","2008-01-29","2008-01-29"]
["UN601_1740","Set up Cradle on CMM - 20","2008-01-30","2008-01-30"]
["UN601_1741","Align Cradle System - 20","2008-01-31","2008-02-01"]
["UN601_1742","Component Handling - 20","2008-02-04","2008-02-04"]
["UN601_1745","Set up Cradle on CMM - 21","2008-02-05","2008-02-05"]
["UN601_1746","Align Cradle System - 21","2008-02-06","2008-02-07"]
["UN601_1747","Component Handling - 21","2008-02-08","2008-02-08"]
["UN601_1750","Set up Cradle on CMM - 22","2008-02-11","2008-02-11"]
["UN601_1751","Align Cradle System - 22","2008-02-12","2008-02-13"]
["UN601_1752","Component Handling - 22","2008-02-14","2008-02-14"]
["UN601_1755","Set up Cradle on CMM - 23","2008-02-15","2008-02-15"]
["UN601_1756","Align Cradle System - 23","2008-02-19","2008-02-20"]
["UN601_1757","Component Handling - 23","2008-02-21","2008-02-21"]
["UN601_1760","Set up Cradle on CMM - 24","2008-02-22","2008-02-22"]
["UN601_1761","Align Cradle System - 24","2008-02-25","2008-02-26"]
["UN601_1762","Component Handling - 24","2008-02-27","2008-02-27"]
["UN601_1765","Set up Cradle on CMM - 25","2008-02-28","2008-02-28"]
["UN601_1766","Align Cradle System - 25","2008-02-29","2008-03-03"]
["UN601_1767","Component Handling - 25","2008-03-04","2008-03-04"]
["UN601_1770","Set up Cradle on CMM - 26","2008-03-05","2008-03-05"]
["UN601_1771","Align Cradle System - 26","2008-03-06","2008-03-07"]
["UN601_1772","Component Handling - 26","2008-03-10","2008-03-10"]
["UN601_1775","Set up Cradle on CMM - 27","2008-03-11","2008-03-11"]
["UN601_1776","Align Cradle System - 27","2008-03-12","2008-03-13"]
["UN601_1777","Component Handling - 27","2008-03-14","2008-03-14"]
["UN601_1780","Set up Cradle on CMM - 28","2008-03-17","2008-03-17"]
["UN601_1781","Align Cradle System - 28","2008-03-18","2008-03-19"]
["UN601_1782","Component Handling - 28","2008-03-20","2008-03-20"]
["UN601_1785","Set up Cradle on CMM - 29","2008-03-21","2008-03-21"]
["UN601_1786","Align Cradle System - 29","2008-03-24","2008-03-25"]
["UN601_1787","Component Handling - 29","2008-03-26","2008-03-26"]
["UN601_1790","Set up Cradle on CMM - 30","2008-03-27","2008-03-27"]
["UN601_1791","Align Cradle System - 30","2008-03-28","2008-03-31"]
["UN601_1792","Component Handling - 30","2008-04-01","2008-04-01"]
["UN601_1795","Set up Cradle on CMM - 31","2008-04-02","2008-04-02"]
["UN601_1796","Align Cradle System - 31","2008-04-03","2008-04-04"]
["UN601_1797","Component Handling - 31","2008-04-07","2008-04-07"]
["UN601_1800","Set up Cradle on CMM - 32","2008-04-08","2008-04-08"]
["UN601_1801","Align Cradle System - 32","2008-04-09","2008-04-10"]
["UN601_1802","Component Handling - 32","2008-04-11","2008-04-11"]
["UN601_1805","Set up Cradle on CMM - 33","2008-04-14","2008-04-14"]
["UN601_1806","Align Cradle System - 33","2008-04-15","2008-04-16"]
["UN601_1807","Component Handling - 33","2008-04-17","2008-04-17"]
["UN601_1810","HYDROSTATIC LEVEL SYSTEM","2006-02-01","2007-08-08"]
["UN601_1812","HLS INSTALLATION","2006-02-01","2006-02-02"]
["UN601_1815","HLS Sensor Installation","2006-02-01","2006-02-02"]
["UN601_1820","Pipe Interconnections w/Flexible Tubing","2006-02-01","2006-02-07"]
["UN601_1825","Install Refill Station","2007-07-02","2007-07-09"]
["UN601_1830","Fill and Leak Testing","2007-07-10","2007-07-11"]
["UN601_1835","Cable Connections","2006-02-01","2006-02-02"]
["UN601_1840","HLS TESTING","2007-07-12","2007-08-08"]
["UN601_1845","HLS System Testing","2007-07-12","2007-07-25"]
["UN601_1850","Mechanical Tuning","2007-07-19","2007-07-25"]
["UN601_1855","Electrical Tuning","2007-07-19","2007-07-25"]
["UN601_1860","Software Changes","2007-07-12","2007-08-08"]
["UN601_1862","Commission Stretched Wire System Complete","2007-08-09","2007-09-06"]
["UN601_1863","HLS ready for measurements","2007-09-07","2007-09-06"]
["UN601_1865","WIRE MONITORING SYSTEM","2006-10-02","2007-11-07"]
["UN601_1870","WMS INSTALLATION","2006-10-02","2007-09-12"]
["UN601_1875","WMS Sensor Installation","2006-10-02","2006-10-03"]
["UN601_1877","WMS Wire Tube Installation","2006-10-02","2006-10-04"]
["UN601_1880","WMS Electronics Installation","2007-08-29","2007-09-04"]
["UN601_1895","Cable Termination","2007-08-29","2007-09-12"]
["UN601_1900","WMS TESTING","2007-09-13","2007-11-07"]
["UN601_1905","WMS System Testing","2007-09-13","2007-09-26"]
["UN601_1910","Mechanical Tuning","2007-09-20","2007-09-26"]
["UN601_1915","Electrical Tuning","2007-09-20","2007-10-03"]
["UN601_1920","Software Changes","2007-09-13","2007-11-07"]
["UN601_1921","Commission Hydrostatic Level System","2007-11-08","2007-12-07"]
["UN601_1922","WMS ready for measurements","2007-12-10","2007-12-07"]
["UN601_2000","RE-MEASURE NETWORK","2008-06-11","2008-06-24"]
["UN601_2005","Remeasurement(Laser Tracker,Level,Total Station)","2008-06-11","2008-06-17"]
["UN601_2010","Stretched Wire Measurements-along granite Girdrs","2007-12-10","2007-12-14"]
["UN601_2015","HLS Measurements","2007-09-07","2007-09-13"]
["UN601_2020","Data Evaluation","2008-06-11","2008-06-17"]
["UN601_2025","Quality Control","2008-06-18","2008-06-24"]
["UN601_2030","ALIGN CRADLES","2008-06-25","2008-07-15"]
["UN601_2035","Set Cradle X,Y Mechanical Adjustments","2008-06-25","2008-06-30"]
["UN601_2040","Quality Control","2008-06-27","2008-07-03"]
["UN601_2045","Set Cradle X,Y Cam Mover Adjustments","2008-07-07","2008-07-10"]
["UN601_2050","Quality Control","2008-07-09","2008-07-15"]
["UNMS4_0115","FY06 Money Arrives at ANL","2006-03-06","2006-03-03"]
["UNMS4_0120","FY07 Money Arrives at ANL","2006-11-02","2006-11-01"]
["UNMS4_0200","EM Supply Spec. Accepted","2006-02-16","2006-02-15"]
["UNMS4_0205","Fine Motion Test Fixture Ready for Use","2005-12-01","2005-11-30",null,"2005-12-01","2005-11-30"]
["UNMS4_0210","Coarse Motion Test Fixture Ready for Use","2005-12-01","2005-11-30",null,"2005-12-01","2005-11-30"]
["UNMS4_0215","Image Capture Test Fixture Complete","2005-07-30","2005-07-29",null,"2005-07-30","2005-07-29"]
["UNMS4_0220","Fine Motion Control Hardware Selection Finalized","2005-12-31","2005-12-30",null,"2005-12-31","2005-12-30"]
["UNMS4_0225","EM Magnet Supply Test Fixture Ready for Use","2006-09-26","2006-09-25"]
["UNMS4_0230","Coarse Motion Control HW Selection Finalized","2006-06-02","2006-06-01"]
["UNMS4_0235","Undulator Fine Motion Controls Software Complete","2006-06-09","2006-06-08"]
["UNMS4_0240","EM Magnet Supply Choice Finalized","2006-08-18","2006-08-17"]
["UNMS4_0245","Undulator Cradle Motion Software Complete","2006-03-01","2006-02-28"]
["UNMS4_0250","Image Capture Hardware Selection Finalized","2005-07-30","2005-07-29",null,"2005-07-30","2005-07-29"]
["UNMS4_0255","EM Magnet Supply Controls Software Complete","2006-09-26","2006-09-25"]
["UNMS4_0260","Image Analysis Controls Software Complete","2006-04-26","2006-04-25"]
["UNMS4_0330","Award First Article Assbly Undulator 1 - Hi-Tech","2005-10-11","2005-10-10",null,"2005-10-11","2005-10-10"]
["UNMS4_0335","Award First Article Assbly Undulator - Metalex","2005-10-18","2005-10-17",null,"2005-10-18","2005-10-17"]
["UNMS4_0340","1st Lot Magnet Poles Arrive","2005-12-01","2005-11-30",null,"2005-12-01","2005-11-30"]
["UNMS4_0345","1st 5% Magnet Blocks Arrive","2006-01-04","2006-01-03",null,"2006-01-04","2006-01-03"]
["UNMS4_0350","1st Ti Strongback Arrives & Accepted","2005-12-13","2005-12-12",null,"2005-12-13","2005-12-12"]
["UNMS4_0355","2nd Ti Strongback Arrives & Accepted","2005-10-18","2005-10-17",null,"2005-10-18","2005-10-17"]
["UNMS4_0360","Undulator 01 LLPs Available for Fabrication","2006-01-04","2006-01-03",null,"2006-01-04","2006-01-03"]
["UNMS4_0365","Undulator 02 LLPs Available for Fabrication","2006-01-04","2006-01-03",null,"2006-01-04","2006-01-03"]
["UNMS4_0380","Hi-Tech Permission to Proceed with 1st Article","2005-12-14","2005-12-13",null,"2005-12-14","2005-12-13"]
["UNMS4_0381","Renegotiate Hi-Tech Contract for Production","2006-06-02","2006-06-01"]
["UNMS4_0382","Undulator 01 Assembly Com & Rcvd at ANL","2006-04-11","2006-04-10"]
["UNMS4_0385","Undulator 02 Assembly Com & Rcvd at ANL","2006-04-17","2006-04-14"]
["UNMS4_0387","Undulator 01 Measured and Tuned @ ANL","2006-05-10","2006-05-09"]
["UNMS4_0389","Undulator 02 Measured and Tuned @ ANL","2006-06-09","2006-06-08"]
["UNMS4_0390","Undulator 01 Tested w/Supt & Mover System @ ANL","2006-05-26","2006-05-25"]
["UNMS4_0392","Metalex Permission to Proceed with 1st Article","2005-12-31","2005-12-30",null,"2005-12-31","2005-12-30"]
["UNMS4_0393","Hi-Tech Undulators 03 -> 19 Complete","2006-12-21","2006-12-20"]
["UNMS4_0394","Metalex Undulators 04 -> 20 Complete","2007-01-22","2007-01-19"]
["UNMS4_0395","Hi-Tech Undulators 21 -> 39 Complete","2007-06-04","2007-06-01"]
["UNMS4_0396","Metalex Undulators 22 -> 40 Complete","2007-06-26","2007-06-25"]
["UNMS4_0397","Renegotiate Metalex Contract for Production","2006-06-30","2006-06-29"]
["UNMS4_0410","Prototype Bellows Fabrication Complete","2006-05-10","2006-05-09"]
["UNMS4_0415","Vacuum Chamber Prototype Fabrication Complete","2006-10-03","2006-10-02"]
["UNMS4_0420","Vacuum Chamber Prototype Testing Complete","2006-12-04","2006-12-01"]
["UNMS4_0425","Prototype Bellows Testing Complete","2006-07-13","2006-07-12"]
["UNMS4_0430","Production Chamber Design Complete","2007-02-08","2007-02-07"]
["UNMS4_0435","Bellows Final Design Complete","2006-09-12","2006-09-11"]
["UNMS4_0440","Production Chamber Award Complete","2007-04-09","2007-04-06"]
["UNMS4_0445","Bellows Award Complete","2007-02-16","2007-02-15"]
["UNMS4_0450","Vacuum Chamber Ready for Installation","2007-09-12","2007-09-11"]
["UNMS4_0455","Bellows Ready for Installation","2007-07-17","2007-07-16"]
["UNMS4_0500","Complete Fabrication of Wire Scanner Prototype","2005-04-30","2005-04-29",null,"2005-04-30","2005-04-29"]
["UNMS4_0505","Complete Fabrication of OTR Prototype","2005-04-30","2005-04-29",null,"2005-04-30","2005-04-29"]
["UNMS4_0515","Prototype RFBPM Design Complete","2005-11-01","2005-10-31",null,"2005-11-01","2005-10-31"]
["UNMS4_0525","Prototype RFBPM Fabrication Complete","2006-02-01","2006-01-31"]
["UNMS4_0550","Prototype RFBPM Testing Complete","2006-08-14","2006-08-11"]
["UNMS4_0565","Wire Scanner Award Complete","2006-02-01","2006-01-31"]
["UNMS4_0570","RFBPM Award Complete","2006-12-18","2006-12-15"]
["UNMS4_0575","RFBPMs Ready For Installation","2008-01-22","2008-01-21"]
["UNMS_00040","Undulator System Commissioning Complete","2007-10-11","2007-10-10"]
["UNOPS_0000","Undulator System Pre-Operations","2008-08-18","2009-03-31"]
["UNSL_0005","REQD:  2 Charge Monitors From SLAC","2006-02-01","2006-02-01"]
["UNUN_00010","Support Commissioning - Controls","2006-10-03","2007-06-05"]
["UNUN_00020","Support Commissioning - Mechanical","2006-10-03","2007-06-05"]
["UNUN_00030","Support Commissioning - Physics","2006-10-03","2007-06-05"]
["UNUN_00290","Review Undulator System 5","2006-02-01","2006-02-02"]
["UNUN_00300","Review Undulator System 6","2006-02-03","2006-02-06"]
["UNUN_00310","Review Undulator System 7","2006-10-02","2006-10-03"]
["UNUN_00320","Review Undulator System 8","2006-10-04","2006-10-05"]
["UNUN_00330","Review Undulator System 9","2007-10-01","2007-10-02"]
["UNUN_00470","FY06 Workshops and Meetings","2006-02-01","2006-02-01"]
["UNUN_00480","FY07 Workshops and Meetings","2006-10-02","2006-10-02"]
["UNUN_00490","FY08 Workshops and Meetings","2007-10-01","2007-10-01"]
["UN_LOE","Undulator System LOE Complete","2009-03-31","2009-03-30"]
["XEOPS_0000","X-Ray End Stations Pre-Operations","2008-02-04","2009-03-25"]
["XE_0121","MANAGEMENT","2005-05-02","2009-02-03",null,"2005-05-02"]
["XE_0201","Specification FEE - Cabling","2007-06-07","2007-07-05"]
["XE_0202","Design FEE - Cabling","2007-07-06","2007-08-02"]
["XE_0211","FEE CABLING","2007-06-07","2008-03-03"]
["XE_0212","Specification Tunnel - Cabling","2007-06-07","2007-07-05"]
["XE_0232","Prep form, Offer, Hire/Train - Controls Engineer","2006-02-01","2006-04-17"]
["XE_0241","Commission Far Hall - Cabling","2008-07-16","2008-08-12"]
["XE_0261","COMP: Tunnel - Cabling","2008-05-07","2008-05-06"]
["XE_0272","Specification Near Hall - Cabling","2007-06-07","2007-07-05"]
["XE_0282","Design Tunnel - Cabling","2007-07-06","2007-08-02"]
["XE_0291","Commission Tunnel - Cabling","2008-05-07","2008-06-04"]
["XE_0292","Design Near Hall - Cabling","2007-07-06","2007-08-02"]
["XE_0311","Install FEE Racks & Panels - Cabling","2008-03-11","2008-05-05"]
["XE_0312","Install Near Hall  Racks & Panels - Cabling","2007-10-23","2008-01-04"]
["XE_0314","Install Far Hall  Racks & Panels - Cabling","2008-01-17","2008-03-14"]
["XE_0321","Test FEE - Cabling","2008-05-13","2008-05-27"]
["XE_0322","COMP:  Near Hall Laser Installed - Cabling","2008-01-14","2008-01-11"]
["XE_0324","Install Cable Tray FH - Cabling","2007-11-02","2008-01-16"]
["XE_0325","Specification Far Hall - Cabling","2007-06-07","2007-07-05"]
["XE_033","Management & Oversight - FY06-08","2005-10-03","2008-09-30",null,"2005-10-03"]
["XE_0331","System Integrate & Test Far Hall - Cabling","2008-06-17","2008-07-15"]
["XE_0332","NEAR HALL CABLING","2007-06-07","2007-10-15"]
["XE_0334","Install Cable Far Hall - Cabling","2008-03-17","2008-05-09"]
["XE_0335","FAR HALL CABLING","2007-06-07","2007-11-01"]
["XE_0341","Test Near Hall - Cabling","2008-01-22","2008-02-04"]
["XE_0342","TUNNEL CABLING","2007-06-07","2007-10-15"]
["XE_0345","Design Far Hall - Cabling","2007-07-06","2007-08-02"]
["XE_0351","Test Tunnel - Cabling","2008-04-23","2008-05-06"]
["XE_0361","Test Far Hall - Cabling","2008-05-19","2008-06-16"]
["XE_0362","REQD: FEE BO","2008-03-03","2008-03-03"]
["XE_0371","Install Cable to Near Hall Laser - Cabling","2008-01-14","2008-01-18"]
["XE_0372","REQD: Near Hall BO","2007-05-21","2007-05-21"]
["XE_0381","Install Cable to Far Hall Laser - Cabling","2008-05-12","2008-05-16"]
["XE_0382","REQD: Far Hall BO","2007-08-06","2007-08-06"]
["XE_0391","COMP:  Far Hall Laser Installed Ready - Cabling","2008-05-12","2008-05-09"]
["XE_0392","REQD: Tunnel BO","2007-09-14","2007-09-14"]
["XE_0401","COMP: System Integrate & Test FH - Cabling","2008-07-16","2008-07-15"]
["XE_0402","Prep form, Offer, Hire/Train - Mech/Vac Engineer","2006-02-01","2006-06-08"]
["XE_0411","COMP: Near Hall - Cabling","2008-02-05","2008-02-04"]
["XE_0412","Prep form, Offer, Hire/Train - Laser Scientist","2006-02-01","2006-06-08"]
["XE_0421","COMP: FEE - Cabling","2008-05-28","2008-05-27"]
["XE_0422","Prep form, Offer, Hire/Train- Detector Engineer","2006-01-17","2006-01-18",null,"2006-01-17","2006-01-18"]
["XE_0431","COMP: Far Hall - Cabling","2008-06-17","2008-06-16"]
["XE_0432","Prep form, Offer, Hire - Atomic Physic Engineer","2006-01-03","2006-01-04",null,"2006-01-03","2006-01-04"]
["XE_0441","Install FEE Cables - Cabling","2008-03-18","2008-05-12"]
["XE_0451","Commission FEE - Cabling","2008-05-28","2008-06-24"]
["XE_0452","Travel FY-05","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["XE_0461","Commission Near Hall - Cabling","2008-02-05","2008-03-04"]
["XE_0462","Travel FY-06","2005-10-03","2006-09-29",null,"2005-10-03"]
["XE_0472","Travel FY-07","2006-10-02","2007-09-28"]
["XE_0482","Travel FY-08","2007-10-01","2008-09-30"]
["XE_0492","Prep form, Offer, Hire/Train - PPS Engineer","2006-01-03","2006-01-04",null,"2006-01-03","2006-01-04"]
["XE_055","SSRL Physics Support","2005-05-02","2005-06-29",null,"2005-05-02","2005-06-29"]
["XE_100","Prepare Bid Pkg FEE Alarms/Signs - PPS","2006-10-02","2006-10-13"]
["XE_101","Bid Process FEE Alarms/Signs - PPS","2006-10-16","2006-12-12"]
["XE_102","AWARD: Contract FEE Alarms/Signs - PPS","2006-12-13","2006-12-13"]
["XE_103","Vendor Fab/Ship FEE Alarms/Signs - PPS","2006-12-14","2007-02-26"]
["XE_104","RECV: FEE Alarms/Signs - PPS","2007-02-27","2007-02-26"]
["XE_106","REQD: FEE Ben Occ PPS","2008-03-04","2008-03-03"]
["XE_107","Install FEE Alarms/Signs - PPS","2008-03-04","2008-04-28"]
["XE_108","Commission FEE - X-Ray PPS","2008-05-06","2008-06-03"]
["XE_111","Design High Perf Data Storage - Beamline Control","2006-12-01","2007-01-12"]
["XE_112","Prep Bid Pkg FEE Beam Stop Hardware - X-Ray PPS","2006-10-02","2006-10-13"]
["XE_116","AVAIL:  FEE X-Ray PPS","2007-02-27","2007-02-26"]
["XE_12","Prep Bid Pkg NH Beam Stop Hardware - X-Ray PPS","2006-10-02","2006-10-13"]
["XE_120","Prepare Bid Pkg FEE Containment/Interlock - PPS","2006-10-02","2006-10-13"]
["XE_121","Bid Process FEE Cable & Cable Tray - Cabling","2007-08-17","2007-09-14"]
["XE_122","AWARD: Contract FEE Containment/Interlock - PPS","2006-12-13","2006-12-13"]
["XE_1250","Bid Process FEE Containment/Interlock - PPS","2006-10-16","2006-12-12"]
["XE_13","Bid Process NH Beam Stop Hardware - X-Ray PPS","2006-10-16","2006-12-12"]
["XE_131","AWARD: Contract FEE Cable & Cable Tray - Cabling","2007-09-17","2007-09-17"]
["XE_132","Assemble FEE Beam Stop Hardware - X-Ray PPS","2007-02-27","2007-04-23"]
["XE_14","AWARD: NH Beam Stop Hardware - X-Ray PPS","2006-12-13","2006-12-13"]
["XE_141","Vendor Fab/Ship FEE Cable & Cable Tray - Cabling","2007-09-18","2007-10-15"]
["XE_142","Install FEE Beam Stop Hardware","2007-04-24","2007-05-21"]
["XE_15","Vendor Fab/Ship NH Beam Stop Hardware-X-Ray PPS","2006-12-14","2007-02-26"]
["XE_151","RECV: FEE Cable & Cable Tray - Cabling","2007-10-16","2007-10-15"]
["XE_152","Install Cable Tray FEE  - Cabling","2008-03-04","2008-04-28"]
["XE_153","COMP: Cabling Design","2007-08-03","2007-08-02"]
["XE_154","Bid Process FEE Racks & Panels - Cabling","2007-08-17","2007-09-14"]
["XE_155","AWARD: Contract FEE Racks & Panels - Cabling","2007-09-17","2007-09-17"]
["XE_156","Vendor Fab/Ship FEE Racks & Panels - Cabling","2007-09-18","2007-10-15"]
["XE_157","RECV: FEE Racks & Panels - Cabling","2007-10-16","2007-10-15"]
["XE_158","Prepare Bid Pkg FEE Racks & Panels - Cabling","2007-08-03","2007-08-16"]
["XE_16","RECV: NH Beam Stop Hardware - X-Ray PPS","2007-02-27","2007-02-26"]
["XE_161","FEE PPS","2006-02-01","2008-03-03"]
["XE_162","Install Cable Tray Near Hall  - Cabling","2007-10-16","2007-12-12"]
["XE_163","Install Cable Near Hall  - Cabling","2007-10-30","2008-01-11"]
["XE_167","REQD: FEE Beneficial Occupancy","2008-03-04","2008-03-03"]
["XE_168","Prepare Bid Pkg FEE Cable & Cable Tray - Cabling","2007-08-03","2007-08-16"]
["XE_17","Assemble NH Beam Stop Hardware - X-Ray PPS","2007-02-27","2007-04-23"]
["XE_170","AWARD: Contract - AP Detectors","2008-02-15","2008-02-15"]
["XE_171","Vendor Fab/Ship - AP Detectors","2008-02-19","2008-02-19"]
["XE_172","Install Tunnel Cable Tray - Cabling","2007-10-16","2007-12-12"]
["XE_175","AWARD: Contract - AP Focusing","2007-06-27","2007-06-27"]
["XE_176","Vendor Fab/Ship - AP Focusing","2007-06-28","2007-08-16"]
["XE_177","AVAIL: FEE Cabling","2007-10-16","2007-10-15"]
["XE_18","Install NH Beam Stop Hardware","2007-04-24","2007-05-21"]
["XE_182","Vendor Fab/Ship FEE Containment/Interlock - PPS","2006-12-14","2007-02-26"]
["XE_184","RECV: FEE Containment/Interlock - PPS","2007-02-27","2007-02-26"]
["XE_185","Install FEE Containment/Interlock - PPS","2008-03-04","2008-04-28"]
["XE_186","Test FEE - PPS","2008-04-29","2008-05-05"]
["XE_192","Install Tunnel Racks - Cabling","2007-12-13","2008-02-26"]
["XE_202","Install Tunnel Cable - Cabling","2008-02-27","2008-04-22"]
["XE_212","RECV: FEE Beam Stop Hardware - X-Ray PPS","2007-02-27","2007-02-26"]
["XE_22","AWARD: 2006 Contract - 2-D X-Ray Detector","2006-02-01","2006-02-01"]
["XE_2200","Specification - Network","2006-06-12","2006-08-07"]
["XE_2201","Design FEE - Network","2006-08-08","2007-02-12"]
["XE_2202","Design Near Hall - Network","2006-08-08","2007-02-12"]
["XE_2203","Prepare Bid Pkg Electronics - Network","2007-02-13","2007-04-10"]
["XE_2205","Design Tunnel - Network","2006-08-08","2007-02-12"]
["XE_2206","Bid Process Electronics - Network","2007-04-11","2007-08-30"]
["XE_2208","Design Far Hall - Network","2006-08-08","2007-02-12"]
["XE_2209","AWARD: Contract Electronics - Network","2007-08-31","2007-09-20"]
["XE_2211","Vendor Fab/Ship Electronics - Network","2007-09-21","2008-02-29"]
["XE_2213","COMP: Network Design","2007-02-13","2007-02-12"]
["XE_2214","RECV: Electronics - Network","2008-03-03","2008-02-29"]
["XE_2216","REQD: FEE Beneficial Occupancy","2008-03-03","2008-02-29"]
["XE_2218","Install Electronics FEE - Network","2008-03-03","2008-04-25"]
["XE_2219","Test FEE - Network","2008-04-28","2008-05-09"]
["XE_222","Bid Process FEE Beam Stop Hardware - X-Ray PPS","2006-10-16","2006-12-12"]
["XE_2221","Install Near Hall  Electronics - Network","2008-05-12","2008-06-09"]
["XE_2223","COMP: CONTROLS DESIGN","2007-06-07","2007-06-06"]
["XE_2224","Test Near Hall - Network","2008-06-10","2008-06-23"]
["XE_2226","Install Tunnel Electronics - Network","2008-06-24","2008-07-08"]
["XE_2227","Test Tunnel - Network","2008-07-09","2008-07-15"]
["XE_2229","Install Far Hall Electronics - Network","2008-07-16","2008-08-12"]
["XE_223","2006 Vendor Contract - 2-D X-Ray Det","2006-01-10","2006-12-15",null,"2006-01-10"]
["XE_2230","Programming Near Hall - Network","2007-02-13","2007-06-06"]
["XE_2232","Test Far Hall - Network","2008-08-13","2008-10-08"]
["XE_2233","Integrate & Test System Far Hall - Network","2008-10-09","2008-12-05"]
["XE_2234","Commission - Network","2008-12-08","2009-01-15"]
["XE_22345","AWARD: 2007 Contract - 2-D X-Ray Detector","2006-10-31","2006-10-31"]
["XE_22346","2007 Vendor Contract Funds-2-D X-Ray Det","2007-01-02","2007-12-07"]
["XE_2235","Programming Tunnel - Network","2007-02-13","2007-06-06"]
["XE_2236","AVAIL: FEE Network","2008-03-03","2008-02-29"]
["XE_2237","COMP: Tunnel - Network","2008-07-16","2008-07-15"]
["XE_2238","Programming Far Hall - Network","2007-02-13","2007-06-06"]
["XE_2239","COMP: FEE Network","2008-05-12","2008-05-09"]
["XE_2240","REQD: Near Hall Beneficial Occupancy","2008-05-12","2008-05-09"]
["XE_2242","COMP: Far Hall - Network","2008-10-09","2008-10-08"]
["XE_2243","COMP: System Integrate & Test  Far Hall-Network","2008-12-08","2008-12-05"]
["XE_2244","COMP: Near Hall - Network","2008-06-24","2008-06-23"]
["XE_2245","REQD: Tunnel Beneficial Occupancy","2008-06-24","2008-06-23"]
["XE_2247","Programming FEE - Network","2007-02-13","2007-06-06"]
["XE_2248","REQD: Far Hall Beneficial Occupancy","2008-03-03","2008-02-29"]
["XE_225","Commission Coordinator - FY06","2005-11-01","2006-09-29",null,"2005-11-01"]
["XE_2250","NETWORK","2006-06-12","2008-06-23"]
["XE_2254","COMP: Commission - Network","2009-01-16","2009-01-15"]
["XE_2255","Specification - PC Support","2007-03-13","2007-05-14"]
["XE_2257","Design Near Hall - PC Support","2007-05-15","2007-07-11"]
["XE_2258","Prepare Bid Pkg Domain Server - PC Support","2007-09-07","2007-10-04"]
["XE_2259","Prepare Bid Pkg File Server - PC Support","2007-09-07","2007-10-04"]
["XE_2260","AVAIL: Near Hall Network","2008-05-12","2008-05-09"]
["XE_2261","Bid Process Domain Server - PC Support","2007-10-05","2007-11-01"]
["XE_2262","Bid Process File Server - PC Support","2007-10-05","2007-11-01"]
["XE_2263","Design Far Hall - PC Support","2007-07-12","2007-09-06"]
["XE_2264","AWARD: Contract Domain Server - PC Support","2007-11-02","2007-11-02"]
["XE_2265","AWARD: Contract File Server - PC Support","2007-11-02","2007-11-02"]
["XE_2266","Vendor Fab/Ship Domain Server - PC Support","2007-11-05","2008-02-15"]
["XE_2267","Vendor Fab/Ship File Server - PC Support","2007-11-05","2008-02-15"]
["XE_2268","COMP:  Design PC Support","2007-09-07","2007-09-06"]
["XE_2269","RECV: Domain Server - PC Support","2008-02-19","2008-02-15"]
["XE_2270","RECV: File Server - PC Support","2008-02-19","2008-02-15"]
["XE_2275","PC SUPPORT","2007-03-13","2008-04-28"]
["XE_2277","Programming Near Hall - PC Support","2007-05-22","2007-09-13"]
["XE_2278","Install Near Hall Domain Server - PC Support","2008-02-19","2008-03-17"]
["XE_2279","Install Near Hall File Server - PC Support","2008-03-18","2008-04-14"]
["XE_2280","Test Near Hall - PC Support","2008-04-15","2008-04-28"]
["XE_2281","COMP: Near Hall - PC Support","2008-04-29","2008-04-28"]
["XE_2285","AVAIL: Tunnel Network","2008-06-24","2008-06-23"]
["XE_2287","Programming Far Hall - PC Support","2007-07-19","2007-11-08"]
["XE_2288","Install Far Hall PCs/Software/Printer - PC Spt","2008-04-29","2008-05-12"]
["XE_2289","Install Far Hall Domain Server - PC Support","2008-04-29","2008-05-12"]
["XE_2290","Test Far Hall - PC Support","2008-05-13","2008-07-09"]
["XE_2291","COMP: Far Hall - PC Support","2008-07-10","2008-07-09"]
["XE_2292","Integrate & Test System - PC Support","2008-07-10","2008-08-06"]
["XE_2293","COMP: System Integrate & Test  - PC Support","2008-08-07","2008-08-06"]
["XE_2294","Commission - PC Support","2008-08-07","2008-09-04"]
["XE_2295","COMP: Commission - PC Support","2008-09-05","2008-09-04"]
["XE_2297","Vendor Fab/Ship PCs/Software/Printer - PC Spt","2007-11-05","2008-02-15"]
["XE_2298","AVAIL: Far Hall Network","2008-03-03","2008-02-29"]
["XE_2299","Prepare Bid Pkg PCs/Software/Printer - PC Spt","2007-09-07","2007-10-04"]
["XE_2300","RECV: PCs/Software/Printer - PC Support","2008-02-19","2008-02-15"]
["XE_2302","Bid Process PCs/Software/Printer - PC Support","2007-10-05","2007-11-01"]
["XE_2305","AWARD: Contract PCs/Software/Printer - PC Suppo","2007-11-02","2007-11-02"]
["XE_2307","REQD: Far Hall Ben Occ PC Support","2008-04-29","2008-04-28"]
["XE_2309","Install Near Hall PCs/Software/Printer - PC Supp","2008-02-19","2008-03-17"]
["XE_2317","REQD: Near Hall Ben Occ PC Support","2008-02-19","2008-02-15"]
["XE_2319","Install Far Hall File Server - PC Support","2008-04-29","2008-05-12"]
["XE_232","AWARD: FEE Beam Stop Hardware - X-Ray PPS","2006-12-13","2006-12-13"]
["XE_2327","AVAIL: Far Hall PC Support","2008-02-19","2008-02-15"]
["XE_233","Procure Beam Stop Hardware","2007-02-27","2007-07-05"]
["XE_2333","Vendor Fab Beam Stop Hardware","2006-10-02","2007-02-26"]
["XE_23336","Assemble Beam Stop Hardware","2007-07-06","2007-08-30"]
["XE_233367","Install Beam Stop Hardware","2007-08-31","2007-09-28"]
["XE_2337","AVAIL: Near Hall PC Support","2008-02-19","2008-02-15"]
["XE_2400","Prepare Bid Pkg Racks & Panels FH - Cabling","2007-08-03","2007-08-16"]
["XE_2401","Prepare Bid Pkg Cable & Cable Tray FH - Cabling","2007-08-03","2007-08-16"]
["XE_2402","Bid Process Cable & Cable Tray FH - Cabling","2007-08-17","2007-09-14"]
["XE_2403","Bid Process Racks & Panels FH - Cabling","2007-08-17","2007-09-14"]
["XE_2404","AWARD: Contract Cable & Cable Tray FH - Cabling","2007-09-17","2007-10-04"]
["XE_2405","AWARD: Contract Racks & Panels FH - Cabling","2007-09-17","2007-10-04"]
["XE_2406","Vendor Fab/Ship Cable & Cable Tray FH - Cabling","2007-10-05","2007-11-01"]
["XE_2407","Vendor Fab/Ship Racks & Panels FH - Cabling","2007-10-05","2007-11-01"]
["XE_2408","RECV: Cable & Cable Tray FH - Cabling","2007-11-02","2007-11-01"]
["XE_2409","RECV: Racks & Panels FH - Cabling","2007-11-02","2007-11-01"]
["XE_2419","REQD:  Far Hall Beneficial Occupancy","2007-11-02","2007-11-01"]
["XE_242","Vendor Fab/Ship FEE Beam Stop Hardware-X-Ray PPS","2006-12-14","2007-02-26"]
["XE_2429","AVAIL: Far Hall Cabling","2007-11-02","2007-11-01"]
["XE_250","AP Engineering","2006-01-03","2008-10-15",null,"2006-01-03"]
["XE_2501","Prepare Bid Pkg Tunnel Cable/Cable Tray - Cablng","2007-08-03","2007-08-16"]
["XE_2502","Bid Process Tunnel Cable & Cable Tray - Cabling","2007-08-17","2007-09-14"]
["XE_2504","AWARD: Contract Tunnel Cable/Cable Tray - Cabln","2007-09-17","2007-09-17"]
["XE_2506","Vendor Fab/Ship Tunnel Cable/Cable Tray - Cablng","2007-09-18","2007-10-15"]
["XE_2508","RECV: Tunnel Cable & Cable Tray - Cabling","2007-10-16","2007-10-15"]
["XE_2518","REQD: Tunnel Beneficial Occupancy","2007-10-16","2007-10-15"]
["XE_2519","Prepare Bid Pkg NH Racks & Panels - Cabling","2007-08-03","2007-08-16"]
["XE_2520","Prepare Bid Pkg NH Cable & Cable Tray - Cabling","2007-08-03","2007-08-16"]
["XE_2521","Bid Process NH Cable & Cable Tray - Cabling","2007-08-17","2007-09-14"]
["XE_2522","Bid Process NH Racks & Panels - Cabling","2007-08-17","2007-09-14"]
["XE_2523","AWARD: Contract NH Cable & Cable Tray - Cabling","2007-09-17","2007-09-17"]
["XE_2524","AWARD: Contract NH Racks & Panels - Cabling","2007-09-17","2007-09-17"]
["XE_2525","Vendor Fab/Ship NH Cable & Cable Tray - Cabling","2007-09-18","2007-10-15"]
["XE_2526","Vendor Fab/Ship NH Racks & Panels - Cabling","2007-09-18","2007-10-15"]
["XE_2527","RECV: NH Cable & Cable Tray - Cabling","2007-10-16","2007-10-15"]
["XE_2528","RECV: NH Racks & Panels - Cabling","2007-10-16","2007-10-15"]
["XE_2538","REQD: Near Hall Beneficial Occupancy","2007-10-16","2007-10-15"]
["XE_2548","AVAIL: Near Hall Cabling","2007-10-16","2007-10-15"]
["XE_2558","AVAIL: Tunnel Cabling","2007-10-16","2007-10-15"]
["XE_2599","Install Near Hall Data Storage - Beamline Contrl","2007-11-16","2008-01-02"]
["XE_2600","Specification - Beamline Controls","2006-06-12","2006-11-30"]
["XE_2601","Design Near Hall - Beamline Control","2006-12-01","2007-06-06"]
["XE_2602","Design Far Hall - Beamline Control","2006-12-01","2007-06-06"]
["XE_2603","COMP:  Design Beamline Control","2007-06-07","2007-06-06"]
["XE_2604","Prep Bid Pkg Rotate/Transl Stage- Beamline Cntrl","2007-06-07","2007-07-05"]
["XE_2605","Prepare Bid Pkg MC Software - Beamline Control","2007-06-07","2007-07-05"]
["XE_2606","Prep Bid Pkg MC Electronics - Beamline Control","2007-06-07","2007-07-05"]
["XE_2607","Bid Process Rotate/Transl Stage - Beamline Cntrl","2007-07-06","2007-08-02"]
["XE_2608","Bid Process MC Software - Beamline Control","2007-07-06","2007-08-02"]
["XE_2609","Bid Process MC Electronics - Beamline Control","2007-07-06","2007-08-02"]
["XE_2610","AWARD: Contract Rotate/Transl Stage - Beam Cntr","2007-08-03","2007-08-22"]
["XE_2611","AWARD: Contract MC Software - Beamline Control","2007-08-03","2007-08-22"]
["XE_2612","AWARD: Contract MC Electronics-Beamline Control","2007-08-03","2007-08-22"]
["XE_2613","Vendor Fab/Ship Rotate/Transl Stage - Beam Cntl","2007-08-23","2007-11-15"]
["XE_2614","Vendor Fab/Ship MC Software - Beamline Control","2007-08-23","2007-11-15"]
["XE_2615","Vendor Fab/Ship MC Electronics - Beamline Cntrl","2007-08-23","2007-11-15"]
["XE_2616","RECV: Rotate/Translate Stages - Beamline Control","2007-11-16","2007-11-15"]
["XE_2617","RECV: MC Software - Beamline Control","2007-11-16","2007-11-15"]
["XE_2618","RECV: MC Electronics - Beamline Control","2007-11-16","2007-11-15"]
["XE_2619","REQD: Near Hall Beneficial Occupancy","2007-11-16","2007-11-15"]
["XE_262","AWARD: Contract - Streak Camera","2006-04-03","2006-04-03"]
["XE_2620","Programming Near Hall - Beamline Control","2006-12-08","2007-04-17"]
["XE_2621","Install Near Hall R/Trans Stage - Beamline Contr","2007-11-16","2008-01-02"]
["XE_2622","Install Near Hall MC Software - Beamline Control","2007-11-16","2008-01-02"]
["XE_2623","Install Near Hall MC Electronics - Beam Control","2008-01-03","2008-01-31"]
["XE_2624","Test Near Hall - Beamline Control","2008-02-01","2008-02-14"]
["XE_2625","COMP: Near Hall - Beamline Control","2008-02-15","2008-02-14"]
["XE_2626","REQD: Far Hall Beneficial Occupancy","2007-11-16","2007-11-15"]
["XE_2627","Programming Far Hall - Beamline Control","2007-11-16","2008-03-28"]
["XE_2628","Install Far Hall Rotate/Trans Stage - Beam Cntrl","2008-02-15","2008-03-14"]
["XE_2629","Install Far Hall MC Software - Beamline Cntrl","2007-11-16","2008-01-02"]
["XE_2630","Install Far Hall MC Electronics - Beam Control","2007-11-16","2008-01-02"]
["XE_2631","Test Far Hall - Beamline Control","2008-02-15","2008-03-14"]
["XE_2632","COMP: Far Hall - Beamline Control","2008-03-17","2008-03-14"]
["XE_2633","Integrate & Test System - Beamline Control","2008-03-17","2008-04-11"]
["XE_2634","COMP: System Integrate & Test  - Beamline Contro","2008-04-14","2008-04-11"]
["XE_2635","Commission - Beamline Control","2008-04-14","2008-05-09"]
["XE_2636","COMP: Commission - Beamline Control","2008-05-12","2008-05-09"]
["XE_2639","AVAIL: Near Hall Beamline Control","2007-11-16","2007-11-15"]
["XE_2640","BEAMLINE CONTROLS","2006-06-12","2007-11-15"]
["XE_2646","AVAIL: Far Hall Beamline Control","2007-11-16","2007-11-15"]
["XE_2700","Specification - Near Hall - Laser PPS","2006-06-23","2006-07-21"]
["XE_2701","Design Near Hall - Laser PPS","2006-07-24","2006-09-18"]
["XE_2702","COMP: Near Hall Design - Laser PPS","2006-11-14","2006-11-13"]
["XE_2703","Safety Review Near Hall - Laser PPS","2006-09-19","2006-11-13"]
["XE_2704","Prep Bid Pkg Near Hall Alarms/Signs - Laser PPS","2006-11-14","2006-11-29"]
["XE_2705","Prep Bid Pkg NHall Contain/Interlck - Laser PPS","2006-11-14","2006-11-29"]
["XE_2707","Bid Process Near Hall Alarms/Signs - Laser PPS","2006-11-30","2007-02-09"]
["XE_2708","Bid Process NHall Contain/Interlck - Laser PPS","2006-11-30","2007-02-09"]
["XE_2710","AWARD: Contract Near Hall Alarms/Signs -Laser P","2007-02-12","2007-02-12"]
["XE_2711","AWARD: Contract NHall Contain/Interlck - Laser","2007-02-12","2007-02-12"]
["XE_2713","Vendor Fab/Ship Near Hall Alarm/Sign - Laser PPS","2007-02-13","2007-04-10"]
["XE_2714","Vendor Ship Near Hall Contain/Intrlck-Laser PPS","2007-02-13","2007-04-10"]
["XE_2716","RECV: Near Hall Alarms/Signs - Laser PPS","2007-04-11","2007-04-10"]
["XE_2717","RECV: Near Hall Containment/Interlock -Laser PPS","2007-04-11","2007-04-10"]
["XE_2719","REQD: Near Hall Beneficial Occup - Laser PPS","2007-05-22","2007-05-21"]
["XE_2720","Install Near Hall Alarms/Signs - Laser PPS","2007-05-22","2007-06-19"]
["XE_2721","Install Near Hall Contain/Interlck - Laser PPS","2007-05-22","2007-06-19"]
["XE_2723","Test Near Hall - Laser PPS","2007-06-20","2007-06-26"]
["XE_2724","COMP: Near Hall Laser PPS","2007-06-27","2007-06-26"]
["XE_2729","AVAIL: Near Hall Laser PPS","2007-04-11","2007-04-10"]
["XE_2730","NEAR HALL LASER PPS","2006-06-23","2007-05-21"]
["XE_2734","Commission Near Hall - Laser PPS","2007-06-27","2007-07-25"]
["XE_2760","Specification Valve - Vacuum","2007-08-23","2007-10-18"]
["XE_2761","Design Valve - Vacuum","2007-10-19","2008-01-02"]
["XE_2762","Design Review Valves - Vacuum","2008-01-03","2008-01-09"]
["XE_2763","COMP: Design Beryllium Valve - Vacuum","2008-01-10","2008-01-09"]
["XE_2764","Prep Bid Pkg Isolation Valve - Vacuum","2008-01-10","2008-01-16"]
["XE_2765","Bid Process Isolation Valve - Vacuum","2008-01-17","2008-02-14"]
["XE_2766","AWARD: Contract Isolation Valve - Vacuum","2008-02-15","2008-02-15"]
["XE_2767","Vendor Fab/Ship Isolation Valve - Vacuum","2008-02-19","2008-04-14"]
["XE_2772","COMP: Near Hall Valve -  Vacuum","2008-05-21","2008-05-20"]
["XE_2777","COMP: Vacuum Valves","2008-05-29","2008-05-28"]
["XE_2779","REQD: Near Hall Ben Occ Valves Vacuum","2008-05-14","2008-05-13"]
["XE_2780","Install Near Hall Valves - Vacuum","2008-05-14","2008-05-20"]
["XE_2781","Assemble Near Hall  Valve - Vacuum","2008-04-16","2008-05-13"]
["XE_2789","AVAIL: Near Hall Valves - Vacuum","2008-05-14","2008-05-13"]
["XE_2790","VACUUM VALVES","2006-06-05","2008-09-30"]
["XE_2800","Prep Bid Pkg Beryllium Valve - Vacuum","2008-01-10","2008-01-16"]
["XE_2801","Bid Process Beryllium Valve - Vacuum","2008-01-17","2008-02-14"]
["XE_2802","AWARD: Contract Beryllium Valve - Vacuum","2008-02-15","2008-02-15"]
["XE_2803","Vendor Fab/Ship Beryllium Valve - Vacuum","2008-02-19","2008-04-14"]
["XE_2804","RECV: Beryllium Valves","2008-04-15","2008-04-14"]
["XE_2805","Assemble Far Hall Valve - Vacuum","2008-04-16","2008-05-13"]
["XE_2806","REQD: Far Hall Beneficial Occupancy","2008-05-14","2008-05-13"]
["XE_2807","Install Far Hall Valve - Vacuum","2008-05-21","2008-05-28"]
["XE_2808","COMP: Far Hall Valve - Vacuum","2008-05-29","2008-05-28"]
["XE_2814","RECV: Isolation Valves","2008-04-15","2008-04-15"]
["XE_2816","AVAIL: Far Hall Valves - Vacuum","2008-05-14","2008-05-13"]
["XE_2818","Commission Valves - Vacuum","2008-05-29","2008-06-25"]
["XE_2900","Specification - Vacuum Hardware","2007-08-23","2007-10-18"]
["XE_2901","Design - Vacuum Hardware","2007-10-19","2008-01-02"]
["XE_2902","Design Review - Vacuum Hardware","2008-01-03","2008-01-09"]
["XE_2903","COMP: Design Vacuum Hardware","2008-01-10","2008-01-09"]
["XE_2905","Prep Bid Pkg - Vacuum Hardware","2008-01-10","2008-01-16"]
["XE_2907","Bid Process - Vacuum Hardware","2008-01-17","2008-02-14"]
["XE_2909","AWARD: Contract - Vacuum Hardware","2008-02-15","2008-02-15"]
["XE_2910","VACUUM HARDWARE","2007-08-23","2008-05-12"]
["XE_2911","Vendor Fab/Ship - Vacuum Hardware","2008-02-19","2008-04-14"]
["XE_2912","RECV:  Vacuum Hardware","2008-04-15","2008-04-14"]
["XE_2918","Assemble Near Hall - Vacuum Hardware","2008-04-15","2008-05-12"]
["XE_2919","REQD: Near Hall Beneficial Occupancy","2008-05-13","2008-05-12"]
["XE_2920","Install Near Hall - Vacuum Hardware","2008-05-13","2008-05-19"]
["XE_2921","COMP: Near Hall Vacuum Hardware","2008-05-20","2008-05-19"]
["XE_2926","Assemble Far Hall - Vacuum Hardware","2008-04-15","2008-05-12"]
["XE_2927","REQD: Far Hall Beneficial Occupancy","2008-05-13","2008-05-12"]
["XE_2928","Install Far Hall - Vacuum Hardware","2008-05-20","2008-05-27"]
["XE_2929","COMP: Far Hall Vacuum Hardware","2008-05-28","2008-05-27"]
["XE_2930","COMP: Vacuum Hardware","2008-05-28","2008-05-27"]
["XE_2933","Specification Ion Pump - Vacuum","2007-08-23","2007-10-18"]
["XE_2934","Design Ion Pump - Vacuum","2007-10-19","2008-01-02"]
["XE_2935","Design Review Ion Pump - Vacuum","2008-01-03","2008-01-09"]
["XE_2936","COMP: Design Ion Pump - Vacuum","2008-01-10","2008-01-09"]
["XE_2937","Prep Bid Pkg Ion Pump - Vacuum","2008-01-10","2008-01-16"]
["XE_2938","Bid Process Ion Pump - Vacuum","2008-01-17","2008-02-14"]
["XE_2939","AWARD: Contract Ion Pump - Vacuum","2008-02-15","2008-02-15"]
["XE_2940","Vendor Fab/Ship Ion Pump - Vacuum","2008-02-19","2008-04-14"]
["XE_2941","RECV: Ion Pump - Vacuum","2008-04-15","2008-04-14"]
["XE_2943","VACUUM ION PUMP","2007-08-23","2008-05-12"]
["XE_2947","REQD: Near Hall Beneficial Occupancy","2008-05-13","2008-05-12"]
["XE_2948","Install Near Hall Ion Pump - Vacuum","2008-05-13","2008-05-27"]
["XE_2949","COMP: Near Hall Ion Pump -Vacuum","2008-05-28","2008-05-27"]
["XE_2954","Assemble Far Hall Ion Pump - Vacuum","2008-04-15","2008-05-12"]
["XE_2955","REQD: Far Hall Beneficial Occupancy","2008-05-13","2008-05-12"]
["XE_2956","Install Far Hall Ion Pump - Vacuum","2008-05-13","2008-05-27"]
["XE_2957","COMP: Far Hall Ion Pump - Vacuum","2008-05-28","2008-05-27"]
["XE_2958","COMP: Ion Pump - Vacuum","2008-05-28","2008-05-27"]
["XE_2959","AVAIL: Near Hall Vacuum Hardware","2008-05-13","2008-05-12"]
["XE_2960","Specification Turbo Pump - Vacuum","2007-08-23","2007-10-18"]
["XE_2961","Design Turbo Pump - Vacuum","2007-10-19","2008-01-02"]
["XE_2962","Design Review Turbo Pump - Vacuum","2008-01-03","2008-01-09"]
["XE_2963","COMP: Design Turbo Pump Vacuum","2008-01-10","2008-01-09"]
["XE_2964","Prep Bid Pkg Turbo Pump - Vacuum","2008-01-10","2008-01-16"]
["XE_2965","Bid Process Turbo Pump - Vacuum","2008-01-17","2008-02-14"]
["XE_2966","AWARD: Contract Turbo Pump - Vacuum","2008-02-15","2008-02-15"]
["XE_2967","Vendor Fab/Ship Turbo Pump - Vacuum","2008-02-19","2008-04-14"]
["XE_2968","RECV:  Turbo Pump - Vacuum","2008-04-15","2008-04-14"]
["XE_2969","Assemble NH Turbo Pump - Vacuum","2008-04-15","2008-05-12"]
["XE_2970","REQD: Near Hall Beneficial Occupancy","2008-05-13","2008-05-12"]
["XE_2971","Install NH Turbo Pump - Vacuum","2008-05-13","2008-05-19"]
["XE_2972","AVAIL: NH Turbo Pump - Vacuum","2008-05-13","2008-05-12"]
["XE_29722","Install Far Hall Turbo Pump - Vacuum","2008-05-13","2008-05-19"]
["XE_29723","COMP:  Far Hall Turbo Pump - Vacuum","2008-05-20","2008-05-19"]
["XE_2973","REQD: Far Hall Beneficial Occupancy","2008-05-13","2008-05-12"]
["XE_2975","AVAIL: Far Hall Ion Pump - Vacuum","2008-05-13","2008-05-12"]
["XE_2977","AVAIL: Far Hall Vacuum Hardware","2008-05-13","2008-05-12"]
["XE_2978","Commission Ion Pump - Vacuum","2008-05-28","2008-06-24"]
["XE_2979","Commission Far Hall Experiment Chamber - Vacuum","2008-04-15","2008-05-12"]
["XE_2980","VACUUM TURBO PUMP","2007-08-23","2008-05-12"]
["XE_2985","COMP: NH Turbo Pump - Vacuum","2008-05-20","2008-05-19"]
["XE_2986","Commission Turbo Pump - Vacuum","2008-05-20","2008-06-17"]
["XE_2987","AVAIL: Near Hall Ion Pump - Vacuum","2008-05-13","2008-05-12"]
["XE_2988","Assemble Near Hall Ion Pump - Vacuum","2008-04-15","2008-05-12"]
["XE_29998","Assemble FH Turbo Pump - Vacuum","2008-04-15","2008-05-12"]
["XE_30","COMP: End Stations Project","2009-02-04","2009-02-03"]
["XE_300","Specification High Perf Data Storage - Beam Cntl","2006-06-12","2006-11-30"]
["XE_3000","Specification Near Hall - X-Ray PPS","2006-02-01","2006-03-01"]
["XE_30008","AVAIL: Far Hall Turbo Pump - Vacuum","2008-05-13","2008-05-12"]
["XE_3001","Design Near Hall - X-Ray PPS","2006-03-02","2006-04-26"]
["XE_3002","COMP: Near Hall Design - X-Ray PPS","2006-06-23","2006-06-22"]
["XE_3003","Prepare Bid Pkg Near Hall Alarms/Signs-X-RayPPS","2006-10-02","2006-10-13"]
["XE_3004","Prep Bid Pkg NHall Contain/Interlock - X-Ray PPS","2006-10-02","2006-10-13"]
["XE_3005","Prepare Near Hall Bid Pkg Detectors - X-Ray PPS","2006-10-02","2006-10-13"]
["XE_3006","Bid Process Near Hall Alarms/Signs - X-Ray PPS","2006-10-16","2006-12-12"]
["XE_3007","Bid Process NHall Containmnt/Interlock-X-Ray PPS","2006-10-16","2006-12-12"]
["XE_3008","Bid Process Near Hall Detectors - X-Ray PPS","2006-10-16","2006-12-12"]
["XE_3009","AWARD: Contract Near Hall Alarms/Signs-X-Ray PPS","2006-12-13","2006-12-13"]
["XE_301","Prepare Bid Pkg Data Storage - Beamline Control","2007-06-07","2007-07-05"]
["XE_3010","AWARD: Contract NHall Contain/Interlock-X-Ray PP","2006-12-13","2006-12-13"]
["XE_3011","AWARD: Contract Near Hall Detectors -X-Ray PPS","2006-12-13","2006-12-13"]
["XE_3012","Vendor Fab/Ship Near Hall Alarms/Signs-X-Ray PPS","2006-12-14","2007-02-26"]
["XE_3013","Vendor Fab/Ship NHall Contain/Interlock-X-RayPPS","2006-12-14","2007-02-26"]
["XE_3014","Vendor Fab/Ship Near Hall Detectors -X-Ray PPS","2006-12-14","2007-02-26"]
["XE_3015","RECV: Near Hall Alarms/Signs - X-Ray PPS","2007-02-27","2007-02-26"]
["XE_3016","RECV: Near Hall Containment/Interlock-X-Ray PPS","2007-02-27","2007-02-26"]
["XE_3017","RECV: Near Hall Detectors - X-Ray PPS","2007-02-27","2007-02-26"]
["XE_3018","REQD: Near Hall Beneficial Occupancy","2007-05-22","2007-05-21"]
["XE_3019","Install Near Hall Alarms/Signs - X-Ray PPS","2007-05-22","2007-06-19"]
["XE_302","Bid Process Data Storage - Beamline Control","2007-07-06","2007-08-02"]
["XE_3020","Install Near Hall Containment/Interlock-X-RayPPS","2007-05-22","2007-06-19"]
["XE_3021","Install Near Hall Detectors - X-Ray PPS","2007-05-22","2007-06-19"]
["XE_3022","Test Near Hall - X-Ray PPS","2007-06-20","2007-06-26"]
["XE_3023","COMP: Near Hall X-Ray PPS","2007-06-27","2007-06-26"]
["XE_3028","AVAIL: Near Hall X-Ray PPS","2007-02-27","2007-02-26"]
["XE_303","AWARD: Contract Data Storage - Beamline Ctrl","2007-08-03","2007-08-22"]
["XE_3030","NEAR HALL X-RAY PPS","2006-02-01","2007-05-21"]
["XE_3031","Safety Review Near Hall - X-Ray PPS","2006-04-27","2006-06-22"]
["XE_3033","Commission Near Hall - X-Ray PPS","2007-06-27","2007-07-25"]
["XE_304","Vendor Fab/Ship Data Storage - Beamline Ctrl","2007-08-23","2007-10-18"]
["XE_305","RECV: High Perf Data Storage - Beamline Control","2007-10-19","2007-10-18"]
["XE_306","Install Data Storag Near Hall - Beamline Cntrl","2007-10-19","2007-11-15"]
["XE_307","Test High Perf Data Storage - Beamline Control","2008-01-03","2008-01-09"]
["XE_314","Vendor Ship Computers","2007-08-23","2007-10-18"]
["XE_316","Install Data Storage Far Hall - Beamline Cntrl","2007-11-16","2008-01-02"]
["XE_333","AWARD:  Computer - Beamline Control","2007-08-03","2007-08-22"]
["XE_3333","COMP:  XRAY MPS, PPS DESIGN","2006-06-23","2006-06-22"]
["XE_3424","Crystals & Gratings","2006-11-14","2008-07-15"]
["XE_4","AWARD 2006 Contract-Prototype-2-D X-Ray Det","2006-02-01","2006-02-01"]
["XE_400","Specification Tunnel - X-Ray PPS","2006-02-01","2006-03-01"]
["XE_4000","Specification - Laser Diagnostics","2007-01-04","2007-03-30"]
["XE_4001","Design - Laser Diagnostics","2007-04-02","2007-05-25"]
["XE_4002","COMP:  Design - Laser Diagnostics","2007-06-12","2007-06-11"]
["XE_4003","Safety Review - Laser Diagnostics","2007-05-29","2007-06-11"]
["XE_4004","Prep Bid Pkg  Energy Sensors - Laser Diagnostics","2007-06-12","2007-06-25"]
["XE_4005","Prep Bid Pkg  IR FROG - Laser Diagnostics","2007-06-12","2007-06-25"]
["XE_4006","Prepare  Bid Pkg Fast Diodes - Laser Diagnostics","2007-06-12","2007-06-25"]
["XE_4007","Bid Process  Energy Sensors - Laser Diagnostics","2007-06-26","2007-08-21"]
["XE_4008","Bid Process  IR FROG - Laser Diagnostics","2007-06-26","2007-08-21"]
["XE_4009","Bid Process  Fast Diodes - Laser Diagnostics","2007-06-26","2007-08-21"]
["XE_401","Design Tunnel - X-Ray PPS","2006-03-02","2006-04-26"]
["XE_4010","AWARD: Contract Energy Sensors - Laser Diagnost","2007-08-22","2007-08-22"]
["XE_4011","AWARD: Contract - IR FROG - Laser Diagnostics","2007-08-22","2007-08-22"]
["XE_4012","AWARD: Contract - Fast Diodes - Laser Diagnosti","2007-08-22","2007-08-22"]
["XE_4013","Vendor Fab/Ship Energy Sensor - Laser Diagnostic","2007-08-23","2007-10-18"]
["XE_4014","Vendor Ship  IR FROG- Laser Diagnostics","2007-08-23","2007-10-18"]
["XE_4015","Vendor Fab/Ship  Fast Diodes - Laser Diagnostics","2007-08-23","2007-10-18"]
["XE_4016","RECV:  Energy Sensors - Laser Diagnostics","2007-10-19","2007-10-18"]
["XE_4017","RECV:  IR FROG - Laser Diagnostics","2007-10-19","2007-10-18"]
["XE_4018","RECV:  Fast Diodes - Laser Diagnostics","2007-10-19","2007-10-18"]
["XE_4019","REQD:  Near Hall Beneficial Occup - Laser Diag","2007-10-19","2007-10-18"]
["XE_402","COMP: Tunnel Design - X-Ray PPS","2006-06-23","2006-06-22"]
["XE_4020","Install  Energy Sensors - Laser Diagnostics","2007-10-19","2007-11-15"]
["XE_4021","Install  IR FROG - Laser Diagnostics","2007-10-19","2007-11-15"]
["XE_4023","Test - Laser Diagnostics","2007-11-16","2007-11-26"]
["XE_4024","COMP:  Laser Diagnostics","2007-11-27","2007-11-26"]
["XE_4025","Prep Bid Pkg Oscillo Scope - Laser Diagnostics","2007-06-12","2007-06-25"]
["XE_4026","Prep Bid Pkg  Autocorrelators - Laser Diagnostic","2007-06-12","2007-06-25"]
["XE_4028","Bid Process Oscillo Scope - Laser Diagnostics","2007-06-26","2007-08-21"]
["XE_4029","Bid Process  Autocorrelators - Laser Diagnostics","2007-06-26","2007-08-21"]
["XE_403","Prepare Bid Pkg Tunnel Alarms/Signs - X-Ray PPS","2006-10-02","2006-10-13"]
["XE_4030","Install  Fast Diodes - Laser Diagnostics","2007-10-19","2007-11-15"]
["XE_4031","AWARD: Contract Oscilloscope- Laser Diagnostics","2007-08-22","2007-08-22"]
["XE_4032","AWARD: Contract  Autocorrelator - Laser Diagnos","2007-08-22","2007-08-22"]
["XE_4034","Vendor Fab/Ship  Oscillo Scope - Laser Diagnost","2007-08-23","2007-10-18"]
["XE_4035","Vendor Ship Autocorrelators - Laser Diagnostics","2007-08-23","2007-10-18"]
["XE_4037","RECV:  Oscillo Scope - Laser Diagnostics","2007-10-19","2007-10-18"]
["XE_4038","RECV:  Autocorrelators - Laser Diagnostics","2007-10-19","2007-10-18"]
["XE_404","Prep Bid Pkg Tunnel Containmt/Interlock-X-RayPPS","2006-10-02","2006-10-13"]
["XE_4040","LASER DIAGNOSTICS","2006-06-05","2008-09-30"]
["XE_4041","Install  Oscilloscope - Laser Diagnostics","2007-10-19","2007-11-15"]
["XE_4042","Install  Autocorrelators - Laser Diagnostics","2007-10-19","2007-11-15"]
["XE_4048","AVAIL: Laser Diagnostics","2007-10-19","2007-10-18"]
["XE_405","Prepare Bid Pkg Tunnel Detectors - X-Ray PPS","2006-10-02","2006-10-13"]
["XE_406","Bid Process Tunnel Alarms/Signs - X-Ray PPS","2006-10-16","2006-12-12"]
["XE_407","Bid Process Tunnel Containmt/Interlock-X-Ray PPS","2006-10-16","2006-12-12"]
["XE_408","Bid Process Tunnel Detectors - X-Ray PPS","2006-10-16","2006-12-12"]
["XE_409","AWARD: Contract Tunnel Alarms/Signs - X-Ray PPS","2006-12-13","2006-12-13"]
["XE_410","AWARD: Contract Tunnel Interlock-X-Ray PPS","2006-12-13","2006-12-13"]
["XE_411","AWARD: Contract Tunnel Detectors - X-Ray PPS","2006-12-13","2006-12-13"]
["XE_412","Vendor Fab/Ship Tunnel Alarms/Signs - X-Ray PPS","2006-12-14","2007-02-26"]
["XE_413","Vendor Ship Tunnel Contain/Interlock-X-RayPPS","2006-12-14","2007-02-26"]
["XE_414","Vendor Fab/Ship Tunnel Detectors - X-Ray PPS","2006-12-14","2007-02-26"]
["XE_415","RECV: Tunnel Alarms/Signs - X-Ray PPS","2007-02-27","2007-02-26"]
["XE_416","RECV: Tunnel Containment/Interlock - X-Ray PPS","2007-02-27","2007-02-26"]
["XE_417","RECV: Tunnel Detectors - X-Ray PPS","2007-02-27","2007-02-26"]
["XE_418","REQD: Tunnel Beneficial Occupancy - X-Ray PPS","2007-09-17","2007-09-14"]
["XE_419","Install Tunnel Alarms/Signs - X-Ray PPS","2007-09-17","2007-11-09"]
["XE_420","Install Tunnel Containment/Interlock - X-Ray PPS","2007-09-17","2007-10-12"]
["XE_421","Install Tunnel Detectors - X-Ray PPS","2007-09-17","2007-10-12"]
["XE_422","Test Tunnel - X-Ray PPS","2007-11-12","2007-11-16"]
["XE_423","COMP: Tunnel X-Ray PPS","2007-11-19","2007-11-16"]
["XE_425","Specification Far Hall - PPS","2006-02-01","2006-03-01"]
["XE_426","Design Far Hall - PPS","2006-03-02","2006-04-26"]
["XE_427","COMP: Far Hall Design - PPS","2006-06-23","2006-06-22"]
["XE_428","Prepare Bid Pkg Far Hall Alarms/Signs - PPS","2006-10-02","2006-10-13"]
["XE_429","Prep Bid Pkg Far Hall Contain/Interlock - PPS","2006-10-02","2006-10-13"]
["XE_430","Prepare Far Hall Bid Pkg Detectors - PPS","2006-10-02","2006-10-13"]
["XE_431","Bid Process Far Hall Alarms/Signs - PPS","2006-10-16","2006-12-12"]
["XE_432","Bid Process Far Hall Containmnt/Interlock - PPS","2006-10-16","2006-12-12"]
["XE_433","Bid Process Far Hall Detectors - PPS","2006-10-16","2006-12-12"]
["XE_434","AWARD: Contract Far Hall Alarms/Signs - PPS","2006-12-13","2006-12-13"]
["XE_435","AWARD: Contract Far Hall Contain/Interlock - PP","2006-12-13","2006-12-13"]
["XE_436","AWARD: Contract Far Hall Detectors - PPS","2006-12-13","2006-12-13"]
["XE_437","Vendor Fab/Ship Far Hall Alarms/Signs - PPS","2006-12-14","2007-02-26"]
["XE_438","Vendor Fab/Ship Far Hall Contain/Interlock- PPS","2006-12-14","2007-02-26"]
["XE_439","Vendor Fab/Ship Far Hall Detectors - PPS","2006-12-14","2007-02-26"]
["XE_44","Management - FY-05 - Mar thru Sep","2005-05-02","2005-09-30",null,"2005-05-02","2005-09-30"]
["XE_440","RECV: Far Hall Alarms/Signs - PPS","2007-02-27","2007-02-26"]
["XE_4400","Engineering - Laser Timing","2006-10-02","2008-09-30"]
["XE_44002","2005 Oct, Nov, Dec - 2-D X-Ray Det","2005-10-03","2005-12-16",null,"2005-10-03","2005-12-16"]
["XE_4404","Commission - Network","2008-12-08","2009-01-15"]
["XE_4405","Vendor Fab/Ship - AP","2007-11-08","2008-01-15"]
["XE_4406","Vendor Fab/Ship - AP","2006-11-08","2007-01-12"]
["XE_4408","AWARD: Contract - AP","2007-11-08","2007-11-08"]
["XE_4409","AWARD: Contract - AP","2006-11-08","2006-11-08"]
["XE_441","RECV: Far Hall Containment/Interlock - PPS","2007-02-27","2007-02-26"]
["XE_442","RECV: Far Hall Detectors - PPS","2007-02-27","2007-02-26"]
["XE_443","REQD: Far Hall Beneficial Occupancy","2007-08-07","2007-08-06"]
["XE_444","Install Far Hall Alarms/Signs - PPS","2007-08-07","2007-09-04"]
["XE_4447","Procure Beam Stop Hardware","2006-10-02","2007-02-26"]
["XE_44478","Procure Beam Stop Hardware","2007-02-27","2007-07-05"]
["XE_44479","Assemble Beam Stop Hardware","2007-07-06","2007-08-02"]
["XE_444791","Install Beam Stop Hardware","2007-08-07","2007-09-04"]
["XE_445","Install Far Hall Containment/Interlock - PPS","2007-08-07","2007-09-04"]
["XE_44556","Prep Bid Pkg - AP Data Analysis","2007-08-02","2007-08-08"]
["XE_44557","Bid Process - AP Data Analysis","2007-08-09","2007-09-06"]
["XE_44558","AWARD: Contract - AP Data Analysis","2007-09-07","2007-09-07"]
["XE_44559","Vendor Fab/Ship - AP Data Analysis","2007-09-10","2007-11-02"]
["XE_44560","RECV:  AP Data Analysis","2007-11-05","2007-11-02"]
["XE_44561","Prep Bid Pkg - AP Optics","2007-05-22","2007-05-29"]
["XE_44562","Bid Process - AP Optics","2007-05-30","2007-06-26"]
["XE_44563","AWARD: Contract - AP Optics","2007-06-27","2007-06-27"]
["XE_44564","Vendor Fab/Ship - AP Optics","2007-06-28","2007-08-16"]
["XE_44565","RECV:  AP Optics","2007-08-17","2007-08-16"]
["XE_4457","End Stations Commissioning Complete","2009-01-16","2009-01-15"]
["XE_446","Install Far Hall Detectors - PPS","2007-08-07","2007-09-04"]
["XE_447","Test Far Hall - PPS","2007-09-05","2007-09-11"]
["XE_448","COMP: Far Hall X-Ray PPS","2007-09-12","2007-09-11"]
["XE_450","TUNNEL X-Ray PPS","2006-02-01","2007-09-14"]
["XE_451","Safety Review Tunnel - X-Ray PPS","2006-04-27","2006-06-22"]
["XE_453","AVAIL: Far Hall X-Ray PPS","2007-02-27","2007-02-26"]
["XE_455","FAR HALL PPS","2006-02-01","2007-08-06"]
["XE_456","Safety Review Far Hall - PPS","2006-04-27","2006-06-22"]
["XE_458","Commission Far Hall X-Ray PPS","2007-09-12","2007-10-09"]
["XE_463","Commission Tunnel - X-Ray PPS","2007-11-19","2008-01-03"]
["XE_468","AVAIL: Tunnel X-Ray PPS","2007-02-27","2007-02-26"]
["XE_5000","Prepare Bid Pkg FEE Sensors - MPS","2006-06-23","2006-07-07"]
["XE_5001","Bid Process FEE Sensors - MPS","2006-07-10","2006-09-01"]
["XE_5002","AWARD: Contract FEE Sensors - MPS","2006-10-02","2006-10-02"]
["XE_5003","Vendor Fab/Ship FEE Sensors - MPS","2006-10-03","2006-11-29"]
["XE_5004","RECV: FEE Sensors - MPS","2006-11-30","2006-11-29"]
["XE_5005","REQD: FEE Beneficial Occupancy","2008-03-04","2008-03-03"]
["XE_5006","Install FEE Sensors - MPS","2008-03-04","2008-04-28"]
["XE_5007","Prepare Bid Pkg FEE Interlocks - MPS","2006-06-23","2006-07-07"]
["XE_5008","AWARD: Contract FEE Interlocks - MPS","2006-10-02","2006-10-02"]
["XE_5009","Bid Process FEE Interlocks - MPS","2006-07-10","2006-09-01"]
["XE_5010","Vendor Fab/Ship FEE Interlocks - MPS","2006-10-03","2006-11-29"]
["XE_5011","RECV: FEE Interlocks - MPS","2006-11-30","2006-11-29"]
["XE_5012","Install FEE Interlocks - MPS","2008-03-04","2008-04-28"]
["XE_5013","Test FEE - MPS","2008-04-29","2008-05-05"]
["XE_5014","Design FEE - MPS","2006-03-02","2006-04-26"]
["XE_5015","Specification FEE - MPS","2006-02-01","2006-03-01"]
["XE_5016","COMP: FEE Design - MPS","2006-06-23","2006-06-22"]
["XE_5017","Prepare Bid Pkg FEE Valves - MPS","2006-06-23","2006-07-07"]
["XE_5018","Bid Process FEE Valves - MPS","2006-07-10","2006-09-01"]
["XE_5019","AWARD: Contract FEE Valves - MPS","2006-10-02","2006-10-02"]
["XE_5020","Vendor Fab/Ship FEE Valves - MPS","2006-10-03","2006-11-29"]
["XE_5021","RECV: FEE Valves - MPS","2006-11-30","2006-11-29"]
["XE_5022","COMP: FEE MPS","2008-05-06","2008-05-05"]
["XE_5023","Install FEE Valves - MPS","2008-03-04","2008-04-28"]
["XE_5024","Specification Near Hall - MPS","2006-02-01","2006-03-01"]
["XE_5025","Design Near Hall - MPS","2006-03-02","2006-04-26"]
["XE_5026","COMP: Near Hall Design - MPS","2006-06-23","2006-06-22"]
["XE_5027","Prepare Bid Pkg Near Hall Sensors - MPS","2006-10-02","2006-10-13"]
["XE_5028","Prep Bid Pkg Near Hall Interlocks - MPS","2006-10-02","2006-10-13"]
["XE_5029","Prepare Near Hall Bid Pkg Valves - MPS","2006-10-02","2006-10-13"]
["XE_503","Specification - Chamber Spt Table","2007-02-27","2007-04-23"]
["XE_5030","Bid Process Near Hall Sensors - MPS","2006-10-16","2006-12-12"]
["XE_5031","Bid Process Near Hall Interlock - MPS","2006-10-16","2006-12-12"]
["XE_5032","Bid Process Near Hall Valves - MPS","2006-10-16","2006-12-12"]
["XE_5033","AWARD: Contract Near Hall Sensors - MPS","2006-12-13","2006-12-13"]
["XE_5034","AWARD: Contract Near Hall Interlocks - MPS","2006-12-13","2006-12-13"]
["XE_5035","AWARD: Contract Near Hall Valves - MPS","2006-12-13","2006-12-13"]
["XE_5036","Vendor Fab/Ship Near Hall Sensors - MPS","2006-12-14","2007-02-26"]
["XE_5037","Vendor Fab/Ship Near Hall Interlocks- MPS","2006-12-14","2007-02-26"]
["XE_5038","Vendor Fab/Ship Near Hall Valves - MPS","2006-12-14","2007-02-26"]
["XE_5039","RECV: Near Hall Sensors - MPS","2007-02-27","2007-02-26"]
["XE_504","Design - Chamber Spt Table","2007-04-24","2007-06-19"]
["XE_5040","RECV: Near Hall Interlocks - MPS","2007-02-27","2007-02-26"]
["XE_5041","RECV: Near Hall Valves - MPS","2007-02-27","2007-02-26"]
["XE_5042","REQD: Near Hall Beneficial Occupancy","2007-05-22","2007-05-21"]
["XE_5043","Install Near Hall Sensors - MPS","2007-05-22","2007-06-19"]
["XE_5044","Install Near Hall Interlocks - MPS","2007-05-22","2007-06-19"]
["XE_5045","Install Near Hall Valves - MPS","2007-05-22","2007-06-19"]
["XE_5046","Test Near Hall - MPS","2007-06-20","2007-06-26"]
["XE_5047","COMP: Near Hall MPS","2007-06-27","2007-06-26"]
["XE_5048","Specification Tunnel - MPS","2006-02-01","2006-03-01"]
["XE_5049","Design Tunnel - MPS","2006-03-02","2006-04-26"]
["XE_505","Design Review - Chamber Spt Table","2007-06-20","2007-06-26"]
["XE_5050","COMP: Tunnel Design - MPS","2006-06-23","2006-06-22"]
["XE_5051","Prepare Bid Pkg Tunnel Sensors - MPS","2006-10-02","2006-10-13"]
["XE_5052","Prep Bid Pkg Tunnel Interlocks - MPS","2006-10-02","2006-10-13"]
["XE_5053","Prepare Bid Pkg Tunnel Valves - MPS","2006-10-02","2006-10-13"]
["XE_5054","Bid Process Tunnel Sensors - MPS","2006-10-16","2006-12-12"]
["XE_5055","Bid Process Tunnel Interlocks - MPS","2006-10-16","2006-12-12"]
["XE_5056","Bid Process Tunnel Valves - MPS","2006-10-16","2006-12-12"]
["XE_5057","AWARD: Contract Tunnel Sensors - MPS","2006-12-13","2006-12-13"]
["XE_5058","AWARD: Contract Tunnel Interlocks - MPS","2006-12-13","2006-12-13"]
["XE_5059","AWARD: Contract Tunnel Valves - MPS","2006-12-13","2006-12-13"]
["XE_506","COMP: Design Chamber Support Table","2007-06-27","2007-06-26"]
["XE_5060","Vendor Fab/Ship Tunnel Sensors - MPS","2006-12-14","2007-02-26"]
["XE_5061","Vendor Fab/Ship Tunnel Interlocks - MPS","2006-12-14","2007-02-26"]
["XE_5062","Vendor Fab/Ship Tunnel Valves - MPS","2006-12-14","2007-02-26"]
["XE_5063","RECV: Tunnel Sensors - MPS","2007-02-27","2007-02-26"]
["XE_5064","RECV: Tunnel Interlocks - MPS","2007-02-27","2007-02-26"]
["XE_5065","RECV: Tunnel Valves - MPS","2007-02-27","2007-02-26"]
["XE_5066","REQD: Tunnel Beneficial Occupancy","2007-09-17","2007-09-14"]
["XE_5067","Install Tunnel Sensors - MPS","2007-09-17","2007-10-12"]
["XE_5068","Install Tunnel Interlocks - MPS","2007-09-17","2007-10-12"]
["XE_5069","Install Tunnel Valves - MPS","2007-09-17","2007-10-12"]
["XE_507","Prep Bid Pkg Metal Products - Chamber Spt Table","2007-06-27","2007-07-03"]
["XE_5070","Test Tunnel - MPS","2007-10-15","2007-10-19"]
["XE_5071","COMP: Tunnel MPS","2007-10-22","2007-10-19"]
["XE_5072","Specification Far Hall - MPS","2006-02-01","2006-03-01"]
["XE_5073","Design Far Hall - MPS","2006-03-02","2006-04-26"]
["XE_5074","COMP: Far Hall Design - MPS","2006-06-23","2006-06-22"]
["XE_5075","Prepare Bid Pkg Far Hall Sensors - MPS","2006-10-02","2006-10-13"]
["XE_5076","Prep Bid Pkg Far Hall Interlocks - MPS","2006-10-02","2006-10-13"]
["XE_5077","Prepare Far Hall Bid Pkg Valves - MPS","2006-10-02","2006-10-13"]
["XE_5078","Bid Process Far Hall Sensors - MPS","2006-10-16","2006-12-12"]
["XE_5079","Bid Process Far Hall Interlock - MPS","2006-10-16","2006-12-12"]
["XE_508","Bid Process Metal Products - Chamber Spt Table","2007-07-05","2007-08-01"]
["XE_5080","Bid Process Far Hall Valves - MPS","2006-10-16","2006-12-12"]
["XE_5081","AWARD: Contract Far Hall Sensors - MPS","2006-12-13","2006-12-13"]
["XE_5082","AWARD: Contract Far Hall Interlocks - MPS","2006-12-13","2006-12-13"]
["XE_5083","AWARD: Contract Far Hall Valves - MPS","2006-12-13","2006-12-13"]
["XE_5084","Vendor Fab/Ship Far Hall Sensors - MPS","2006-12-14","2007-02-26"]
["XE_5085","Vendor Fab/Ship Far Hall Interlocks- MPS","2006-12-14","2007-02-26"]
["XE_5086","Vendor Fab/Ship Far Hall Valves - MPS","2006-12-14","2007-02-26"]
["XE_5087","RECV: Far Hall Sensors - MPS","2007-02-27","2007-02-26"]
["XE_5088","RECV: Far Hall Interlocks - MPS","2007-02-27","2007-02-26"]
["XE_5089","RECV: Far Hall Valves - MPS","2007-02-27","2007-02-26"]
["XE_509","AWARD: Contract Metal Product-Chamber Spt Table","2007-08-02","2007-08-02"]
["XE_5090","REQD: Far Hall Beneficial Occupancy","2007-08-07","2007-08-06"]
["XE_5091","Install Far Hall Sensors - MPS","2007-08-07","2007-09-04"]
["XE_5092","Install Far Hall Interlocks - MPS","2007-08-07","2007-09-04"]
["XE_5093","Install Far Hall Valves - MPS","2007-08-07","2007-09-04"]
["XE_5094","Test Far Hall - MPS","2007-09-05","2007-09-11"]
["XE_5095","COMP: Far Hall MPS","2007-09-12","2007-09-11"]
["XE_5096","AVAIL: Tunnel X-Ray MPS","2007-02-27","2007-02-26"]
["XE_5097","Commission Near Hall - X-Ray MPS","2007-06-27","2007-07-25"]
["XE_5098","Safety Review - MPS","2006-04-27","2006-06-22"]
["XE_510","Vendor Fab/Ship Metal Products-Chamber Spt Table","2007-08-03","2007-09-28"]
["XE_5100","AVAIL:  Far Hall X-Ray MPS","2007-02-27","2007-02-26"]
["XE_5101","Commission Tunnel - X-Ray MPS","2007-10-22","2007-11-16"]
["XE_5102","Safety Review - MPS","2006-04-27","2006-06-22"]
["XE_5104","Safety Review - MPS","2006-04-27","2006-06-22"]
["XE_5105","FEE MPS","2006-02-01","2008-03-03"]
["XE_5108","TUNNEL MPS","2006-02-01","2007-09-14"]
["XE_511","RECV: Metal Products - Chamber Spt Table","2007-10-01","2007-09-28"]
["XE_5112","FAR HALL MPS","2006-02-01","2007-08-06"]
["XE_5114","Safety Review - MPS","2006-04-27","2006-06-22"]
["XE_5115","AVAIL: FEE X-Ray MPS","2006-11-30","2006-11-29"]
["XE_512","Assemble Far Hall - Chamber Spt Table","2008-03-11","2008-07-01"]
["XE_5122","AVAIL: Near Hall X-Ray PPS","2007-02-27","2007-02-26"]
["XE_5124","NEAR HALL MPS","2006-02-01","2007-05-21"]
["XE_5125","Commission Far Hall - X-Ray MPS","2007-09-12","2007-10-09"]
["XE_513","Install Far Hall - Chamber Spt Table","2008-07-02","2008-07-09"]
["XE_5132","Commission FEE - X-Ray MPS","2008-05-06","2008-06-03"]
["XE_514","COMP: Far Hall Chamber Spt Table","2008-07-10","2008-07-09"]
["XE_515","Assemble Near Hall - Chamber Spt Table","2007-10-01","2008-02-08"]
["XE_516","Install Near Hall - Chamber Spt Table","2008-02-11","2008-03-10"]
["XE_517","COMP: Near Hall Chamber Spt Table","2008-03-11","2008-03-10"]
["XE_522","REQD: Far Hall Beneficial Occupancy","2008-07-02","2008-07-01"]
["XE_523","CHAMBER SUPPORT TABLES","2007-02-27","2008-07-01"]
["XE_525","REQD: Near Hall Beneficial Occupancy","2008-02-11","2008-02-08"]
["XE_527","COMP: Chamber Support Tables","2008-07-10","2008-07-09"]
["XE_5300","Specification Near Hall - Experimental Chamber","2007-02-27","2007-04-23"]
["XE_5301","Design Near Hall - Experimental Chamber","2007-04-24","2007-08-15"]
["XE_5302","Design Review Near Hall - Experimental Chamber","2007-08-16","2007-08-22"]
["XE_5303","COMP: Design Near Hall - Experimental Chamber","2007-08-23","2007-08-22"]
["XE_5304","Prep Bid Pkg Near Hall - Experimental Chamber","2007-08-23","2007-08-29"]
["XE_5305","Bid Process Near Hall - Experimental Chamber","2007-08-30","2007-09-27"]
["XE_5306","AWARD: Contract Near Hall - Experimental Chambe","2007-09-28","2007-09-28"]
["XE_5307","Vendor Fab/Ship Near Hall - Experimental Chamber","2007-10-01","2007-11-27"]
["XE_5308","RECV:  Near Hall Experimental Chamber","2007-11-28","2007-11-27"]
["XE_5309","Assemble Near Hall - Experimental Chamber","2007-11-28","2008-04-07"]
["XE_5310","REQD: Near Hall Beneficial Occupancy","2008-04-08","2008-04-07"]
["XE_5311","Install Near Hall - Experimental Chamber","2008-04-08","2008-05-05"]
["XE_5312","COMP: Near Hall Experimental Chamber","2008-05-13","2008-05-12"]
["XE_5313","Commission Near Hall Experiment Chamber - Vacuum","2008-05-13","2008-06-10"]
["XE_532","AVAIL: Far Hall - Chamber Support Table","2008-07-02","2008-07-01"]
["XE_5320","NEAR HALL EXPERIMENTAL CHAMBER","2007-02-27","2008-04-07"]
["XE_5321","Leak Check/Test Near Hall - Experimental Chamber","2008-05-06","2008-05-12"]
["XE_5330","AVAIL: Near Hall Experimental Chamber","2008-04-08","2008-04-07"]
["XE_535","AVAIL: Near Hall - Chamber Support Table","2008-02-11","2008-02-08"]
["XE_5400","Specification Far Hall - Experimental Chamber","2007-02-27","2007-04-23"]
["XE_5401","Design Far Hall - Experimental Chamber","2007-04-24","2007-08-15"]
["XE_5402","Design Review Far Hall - Experimental Chamber","2007-08-16","2007-08-22"]
["XE_5403","COMP: Design Far Hall Experimental Chamber","2007-08-23","2007-08-22"]
["XE_5404","Prep Bid Pkg Far Hall - Experimental Chamber","2007-08-23","2007-08-29"]
["XE_5405","Bid Process Far Hall - Experimental Chamber","2007-08-30","2007-09-27"]
["XE_5406","AWARD: Contract Far Hall - Experimental Chamber","2007-09-28","2007-09-28"]
["XE_5407","Vendor Fab/Ship Far Hall - Experimental Chamber","2007-10-01","2007-11-27"]
["XE_5408","RECV:  Far Hall Experimental Chamber","2007-11-28","2007-11-27"]
["XE_5410","FAR HALL EXPERIMENTAL CHAMBER","2007-02-27","2008-04-07"]
["XE_5411","COMP: Far Hall Laser PPS","2007-09-12","2007-09-11"]
["XE_5413","Assemble Far Hall - Experimental Chamber","2007-11-28","2008-04-07"]
["XE_5414","REQD: Far Hall Beneficial Occupancy","2008-04-08","2008-04-07"]
["XE_5415","Install Far Hall - Experimental Chamber","2008-04-08","2008-04-14"]
["XE_5416","COMP: Far Hall Experimental Chamber","2008-05-13","2008-05-12"]
["XE_5421","Commission Far Hall - Laser PPS","2007-09-12","2007-10-09"]
["XE_5424","AVAIL: Far Hall Experimental Chamber","2008-04-08","2008-04-07"]
["XE_5488","Leak Check/Test - Experimental Chamber","2008-04-08","2008-04-14"]
["XE_56","Commission -  Laser Diagnostics","2007-11-27","2008-03-07"]
["XE_567","2005 Design Review - 2-D X-Ray Detector","2006-03-30","2006-04-05"]
["XE_5675","COMP: 2005 Design Review - 2-D X-Ray Detector","2006-04-06","2006-04-05"]
["XE_57","Commission - Optic Transport","2008-07-28","2008-08-22"]
["XE_58","Commission Far Hall - Laser Timing","2008-06-06","2008-11-24"]
["XE_59","Commission Near Hall - Laser Amplifiers","2008-08-04","2009-02-03"]
["XE_6000","Specification - Laser Supp/Optic Transport","2007-01-04","2007-03-02"]
["XE_6001","Design - Laser Supp/Optic Transport","2007-08-01","2007-11-21"]
["XE_6003","COMP: Design Laser Supp/Optic Transport","2007-11-26","2007-11-21"]
["XE_6004","Prep Bid Pkg Lenses & Mirrors - Laser Supplies","2007-11-26","2007-12-07"]
["XE_6005","Bid Process Lenses & Mirrors - Laser Supplies","2007-12-10","2008-01-23"]
["XE_6006","AWARD: Contract Lenses & Mirrors-Laser Supplies","2008-01-24","2008-01-24"]
["XE_6007","Vendor Fab/Ship Lenses & Mirrors -Laser Supplies","2008-01-25","2008-04-18"]
["XE_6008","RECV:  Lenses & Mirrors - Laser Supplies","2008-04-21","2008-04-18"]
["XE_6009","REQD: Near Hall Beneficial Occupancy - LSupp","2008-05-05","2008-05-02"]
["XE_6010","LASER SUPPLIES / OPTICS TRANSPORT","2007-01-04","2008-05-02"]
["XE_6011","Install Pipe, Laser Table to X-Ray Hutch-LSupp","2008-05-05","2008-06-02"]
["XE_6015","Test - Optic Transport","2008-06-03","2008-06-09"]
["XE_6016","COMP: Laser Supplies/Optic Transport","2008-06-10","2008-06-09"]
["XE_6020","Specification - Laser Timing","2007-01-02","2007-06-21"]
["XE_6021","Design - Laser Timing","2007-08-01","2007-11-21"]
["XE_6022","Design Review - Laser Timing","2007-11-26","2007-12-07"]
["XE_6023","COMP: Design Laser Timing","2007-12-10","2007-12-07"]
["XE_6024","Prep Bid Pkg Frequency Analyzer - Laser Timing","2007-12-10","2007-12-11"]
["XE_6025","Bid Process Frequency Analyzer - Laser Timing","2007-12-12","2008-01-25"]
["XE_6026","AWARD: Contract Frequency Analyzer-Laser Timing","2008-01-28","2008-01-28"]
["XE_6027","Vendor Fab/Ship Frequency Analyzer - Laser Timin","2008-01-29","2008-04-22"]
["XE_6028","RECV: Frequency Analyzer - Laser Timing","2008-04-23","2008-04-22"]
["XE_6029","REQD: Near Hall Beneficial Occup - Laser Timing","2008-04-30","2008-04-29"]
["XE_6030","REQD: Diagnostics for NHall Laser Demo - Timing","2008-04-30","2008-04-29"]
["XE_6031","Optic Table Ready NHall - Laser Timing","2008-04-23","2008-04-29"]
["XE_6032","Install Diagnostics Near Hall - Laser Timing","2008-04-30","2008-05-28"]
["XE_6036","COMP: Near Hall Laser Timing","2008-07-28","2008-07-25"]
["XE_6038","Specification Near Hall - Laser Amplifiers","2007-01-04","2007-03-02"]
["XE_6039","Design Near Hall - Laser Amplifiers","2007-06-01","2007-09-24"]
["XE_6040","Design Review Near Hall - Laser Amplifiers","2007-09-25","2007-10-08"]
["XE_6041","COMP: Design Near Hall - Laser Amplifiers","2007-10-09","2007-10-08"]
["XE_6042","Prep Bid Pkg Near Hall - Laser Amplifiers","2007-10-09","2007-10-22"]
["XE_6043","Bid Process Near Hall - Laser Amplifiers","2007-10-23","2007-11-19"]
["XE_6044","AWARD: Contract Near Hall - Laser Amplifiers","2007-11-20","2007-11-20"]
["XE_6045","Vendor Fab/Ship Near Hall - Laser Amplifiers","2007-11-21","2008-05-29"]
["XE_6046","RECV:  Near Hall Laser Amplifiers","2008-05-30","2008-05-29"]
["XE_6048","REQD: Diagnostics for Laser Demo","2008-06-06","2008-06-05"]
["XE_6049","Optic Table Ready NHall - Laser Amplifiers","2008-05-30","2008-06-05"]
["XE_6050","First Install Near Hall - Laser Amplifiers","2008-06-06","2008-06-19"]
["XE_6051","Vendor Setup/Demo NHall - Laser Amplifiers","2008-06-20","2008-07-18"]
["XE_6052","Final Check Near Hall - Laser Amplifiers","2008-07-21","2008-07-25"]
["XE_6053","Test Near Hall - Laser Amplifiers","2008-07-28","2008-08-01"]
["XE_6054","COMP: Near Hall Laser Amplifiers","2008-08-04","2008-08-01"]
["XE_6055","Prep Bid Pkg Shielding/Contain - Laser Supplies","2007-11-26","2008-01-08"]
["XE_6056","Bid Process Shielding/Contain - Laser Supplies","2008-01-09","2008-02-06"]
["XE_6057","AWARD: Contract Shielding/Contai - Laser Suppli","2008-02-07","2008-02-07"]
["XE_6058","Vendor Fab/Ship Shielding/Conta -Laser Supplies","2008-02-08","2008-05-02"]
["XE_6059","RECV:  Shielding/Contain - Laser Supplies","2008-05-05","2008-05-02"]
["XE_6060","Prep Bid Pkg Optic Tables (4) - Laser Supplies","2007-11-26","2007-12-07"]
["XE_6061","Bid Process Optic Tables (4) - Laser Supplies","2007-12-10","2008-01-23"]
["XE_6062","AWARD: Contract Optic Tables (4) - Laser Suppli","2008-01-24","2008-01-24"]
["XE_6063","Vendor Fab/Ship Optic Tables (4) -Laser Supplies","2008-01-25","2008-04-18"]
["XE_6064","RECV:  Optic Tables (4) - Laser Supplies","2008-04-21","2008-04-18"]
["XE_6065","Prep Bid Pkg Cabinets - Laser Supplies","2007-11-26","2007-12-07"]
["XE_6066","Bid Process Cabinets - Laser Supplies","2007-12-10","2008-01-23"]
["XE_6067","AWARD: Contract Cabinets - Laser Supplies","2008-01-24","2008-01-24"]
["XE_6068","Vendor Fab/Ship Cabinets -Laser Supplies","2008-01-25","2008-03-21"]
["XE_6069","RECV:  Cabinets - Laser Supplies","2008-03-24","2008-03-21"]
["XE_6070","LASER TIMING","2006-10-02","2008-09-30"]
["XE_6072","Test Timing System Near Hall - Laser Timing","2008-05-29","2008-07-24"]
["XE_6077","AVAIL: Near Hall Laser Amplifiers","2008-06-06","2008-06-05"]
["XE_6078","NEAR HALL LASER AMPLIFIERS","2006-04-03","2008-07-29"]
["XE_6079","AVAIL: Laser Supplies","2008-05-05","2008-05-02"]
["XE_6080","AVAIL: Near Hall Laser Timing","2008-04-30","2008-04-29"]
["XE_61","Commission - Beam Imaging","2007-07-19","2008-01-24"]
["XE_6100","REQD: Far Hall Beneficial Occup - Laser Timing","2008-04-30","2008-04-29"]
["XE_6101","REQD: Diagnostics for Far Hall Laser Demo","2008-04-30","2008-04-29"]
["XE_6102","Optic Table Ready Laser Far  Hall - Timing","2008-04-23","2008-04-29"]
["XE_6110","AVAIL: Far Hall Laser Timing","2008-04-30","2008-04-29"]
["XE_62","Commission - 2-D X-Ray Detector","2009-03-23","2009-03-31"]
["XE_63","Commission - Beam Intensity","2008-04-29","2008-10-16"]
["XE_64","Commission - Streak Camera","2008-01-03","2008-06-23"]
["XE_700","Test Near Hall - Oscillator Laser/Pum","2008-10-16","2008-10-22"]
["XE_701","Specification - Oscillator Laser/Pump","2007-01-04","2007-03-02"]
["XE_702","Design - Oscillator Laser/Pump","2007-08-01","2007-11-21"]
["XE_703","Design Review- Oscillator Laser/Pump","2007-11-26","2007-12-07"]
["XE_704","COMP: Design  - Oscillator Laser/Pump","2007-12-10","2007-12-07"]
["XE_7040","Integrate with Controls","2008-04-01","2008-04-28"]
["XE_7041","COMP: Beam Intensity","2008-04-29","2008-04-28"]
["XE_7045","COMP: Design - Streak Camera","2007-04-09","2007-04-06"]
["XE_7046","Prep Bid Pkg - Streak Camera","2007-04-09","2007-04-13"]
["XE_7047","Bid Process - Streak Camera","2007-04-16","2007-05-11"]
["XE_7048","AWARD: Contract - Streak Camera","2007-05-14","2007-05-14"]
["XE_7049","Inspect/Vendor Setup - Streak Camera","2007-10-12","2007-10-18"]
["XE_705","Prep Bid Pkg  - Oscillator Laser/Pump","2007-12-10","2008-01-08"]
["XE_7050","RECV:  Streak Camera","2007-10-05","2007-10-04"]
["XE_7051","Assemble at SLAC - Streak Camera","2007-10-05","2007-10-11"]
["XE_7052","REQD: Near  Hall Beneficial Occupancy","2007-10-19","2007-10-18"]
["XE_7053","Install Near Hall - Streak Camera","2007-10-19","2007-11-15"]
["XE_7054","COMP: Streak Camera","2008-01-03","2008-01-02"]
["XE_7059","Prep Bid Pkg - 2-D X-Ray Detector","2005-06-01","2005-07-15",null,"2005-06-01","2005-07-15"]
["XE_706","Bid Process - Oscillator Laser/Pump","2008-01-09","2008-02-06"]
["XE_7060","Send funding documents - 2-D X-Ray Detector","2005-06-01","2005-07-15",null,"2005-06-01","2005-07-15"]
["XE_70611","AWARD: FY-05 Contract - 2-D X-Ray Detector","2005-07-15","2005-07-15",null,"2005-07-15","2005-07-15"]
["XE_7062","FY-05 Vendor Contract - Design - 2-D X-Ray Det","2005-07-06","2005-09-30",null,"2005-07-06","2005-09-30"]
["XE_7063","RECV:  2-D X-Ray Detector","2008-12-16","2008-12-15"]
["XE_7064","Install at SLAC - 2-D X-Ray Detector","2009-01-26","2009-02-20"]
["XE_7067","COMP:  2-D X-Ray Detector","2009-03-23","2009-03-20"]
["XE_707","AWARD: Contract - Oscillator Laser/Pump","2008-02-07","2008-02-07"]
["XE_7073","Integrate with Controls - Streak Camera","2007-11-16","2008-01-02"]
["XE_7076","Integrate with Controls - 2-D X-Ray Detector","2009-02-23","2009-03-20"]
["XE_70775","2006 Vendor Contract - Prototype-2-D X-Ray Det","2006-01-10","2006-12-15",null,"2006-01-10"]
["XE_708","Vendor Fab/Ship - Oscillator Laser/Pum","2008-02-08","2008-07-29"]
["XE_7081","2006 Design Review - 2-D X-Ray Detector","2006-10-26","2006-10-30"]
["XE_7083","AVAIL: 2-D X-Ray Detector","2008-12-16","2008-12-15"]
["XE_70832","2007 Design Review - 2-D X-Ray Detector","2007-12-10","2007-12-14"]
["XE_7085","2-D X-RAY DETECTOR","2005-05-17","2009-03-31",null,"2005-05-17"]
["XE_709","RECV:  Oscillator Laser/Pump","2008-07-30","2008-07-29"]
["XE_710","Install Laser Table Near Hall - Oscillator Laser","2008-07-30","2008-08-26"]
["XE_7102","Contract - Demo at SLAC - 2-D X-Ray Detector","2008-12-16","2009-01-23"]
["XE_7106","Vendor Contract 100% Complete - Streak Camera","2007-05-15","2007-09-06"]
["XE_7107","Produce Report,Contract Complete - Streak Camera","2007-09-07","2007-10-04"]
["XE_7108","Vendor Fab/Ship - AP Samples","2008-02-19","2008-02-25"]
["XE_7109","Design Study LBL - Streak Camera - FY-06","2006-04-03","2006-09-29"]
["XE_7110","Final Design Review - Streak Camera","2007-04-02","2007-04-06"]
["XE_7112","2008 Vendor Contract - 2-D X-Ray Detector","2008-01-02","2008-12-08"]
["XE_71122","2008 Final Report - 2-D X-Ray Detector","2008-12-09","2008-12-15"]
["XE_7113","AWARD 2008 Contract - 2-D X-Ray Detector","2008-01-02","2008-01-02"]
["XE_712","Final Check Near Hall - Oscillator Laser/Pump","2008-10-09","2008-10-15"]
["XE_713","COMP: Near Hall Oscillator Laser/Pump","2008-10-23","2008-10-22"]
["XE_7132","STREAK CAMERA","2006-01-17","2008-10-13",null,"2006-01-17"]
["XE_714","Procure Laser Tables","2007-08-01","2008-02-06"]
["XE_71420","AVAIL: Streak Camera","2007-10-19","2007-10-18"]
["XE_7144","Commission Near Hall - Oscillator Laser/Pump","2008-10-23","2008-11-19"]
["XE_7153","Design Study LBL - Streak Camera - FY-07","2006-10-02","2007-03-30"]
["XE_720","REQD: Diagnostics for Laser Demo","2008-07-30","2008-07-29"]
["XE_7200","Prep Bid Pkg - AP Samples","2008-01-10","2008-01-16"]
["XE_721","AP OSCILLATOR LASER/PUMP","2007-01-04","2010-04-05"]
["XE_72222","2006 Contract Report - 2-D X-Ray Detector","2006-10-24","2006-10-25"]
["XE_730","Vendor Setup/Demo NHall - Oscillator Laser/Pump","2008-09-11","2008-10-08"]
["XE_7300","Bid Process - AP Samples","2008-01-17","2008-02-14"]
["XE_7301","Specification Far Hall - Laser PPS","2006-06-23","2006-07-21"]
["XE_7302","Prep Bid Pkg - AP Diagnostics","2008-01-10","2008-01-16"]
["XE_7303","Bid Process - AP Diagnostics","2008-01-17","2008-02-14"]
["XE_7304","AWARD: Contract - AP Diagnostics","2008-02-15","2008-02-15"]
["XE_7305","Vendor Fab/Ship - AP Diagnostics","2008-02-19","2008-02-19"]
["XE_7306","RECV:  AP Diagnostics","2008-02-20","2008-02-19"]
["XE_731","AVAIL:  Oscillator Laser/Pump","2008-07-30","2008-07-29"]
["XE_7311","Design Far Hall - Laser PPS","2006-07-24","2006-09-18"]
["XE_7321","COMP: Far Hall Design - Laser PPS","2006-11-14","2006-11-13"]
["XE_7331","Safety Review Far Hall - Laser PPS","2006-09-19","2006-11-13"]
["XE_7341","Prep Bid Pkg Far Hall Alarms/Signs - Laser PPS","2006-11-14","2006-11-29"]
["XE_7350","Define AP Samples","2006-02-01","2006-06-22"]
["XE_7351","Prep Bid Pkg FHall Contain/Interlck - Laser PPS","2006-11-14","2006-11-29"]
["XE_73511","Design AP preparation and handling - Samples","2006-06-23","2006-12-13"]
["XE_73512","Procurements - AP Samples","2008-01-10","2008-01-24"]
["XE_73513","Assembly - AP Samples","2008-02-26","2008-02-26"]
["XE_73514","Test AP Sample","2008-07-28","2008-07-28"]
["XE_73515","Define AP Data Analysis","2006-02-01","2007-02-09"]
["XE_73516","Design AP Data Analysis","2007-02-12","2007-08-01"]
["XE_73517","Procurements - AP Data Analysis","2007-08-02","2008-02-07"]
["XE_73518","Assembly - AP Data Analysis","2007-11-05","2007-12-04"]
["XE_73519","Test - AP Data Analysis","2008-07-28","2008-08-22"]
["XE_73520","Define AP Optics","2006-06-23","2006-11-13"]
["XE_73521","Design AP Optics","2006-11-14","2007-05-21"]
["XE_73522","Procurements - AP  Optics","2007-05-22","2007-11-08"]
["XE_73523","Assembly - AP Optics","2007-11-09","2007-12-10"]
["XE_73524","Test - AP Optics","2008-07-28","2008-08-22"]
["XE_73528","AP DATA ANALYSIS","2006-02-01","2008-08-22"]
["XE_73531","AP SAMPLES","2006-01-03","2008-10-15",null,"2006-01-03"]
["XE_73533","AP OPTICS","2006-06-23","2008-08-22"]
["XE_7361","Prepare Bid Pkg Far Hall Detectors - Laser PPS","2006-11-14","2006-11-29"]
["XE_7371","Bid Process Far Hall Alarms/Signs - Laser PPS","2006-11-30","2007-02-09"]
["XE_7381","Bid Process Far Hall Contain/Interlck - Laser PP","2006-11-30","2007-02-09"]
["XE_7391","Bid Process Far Hall Detectors - Laser PPS","2006-11-30","2007-02-09"]
["XE_740","First Install Near Hall - Oscillator Laser/Pump","2008-08-27","2008-09-10"]
["XE_7400","AWARD: Contract - AP Samples","2008-02-15","2008-02-15"]
["XE_7401","AWARD: Contract Far Hall Alarms/Signs -Laser PP","2007-02-12","2007-02-12"]
["XE_74100","Define AP Diagnostics","2006-06-23","2007-07-03"]
["XE_74101","Design AP Diagnostics","2007-07-05","2008-01-09"]
["XE_74102","Procurements - AP Diagnostics","2008-01-10","2008-01-16"]
["XE_74103","Assembly - AP Diagnostics","2008-02-20","2008-02-20"]
["XE_74104","Test AP Diagnostics","2008-07-28","2008-07-28"]
["XE_7411","AWARD: Contract FHall Contain/Interlck - Laser","2007-02-12","2007-02-12"]
["XE_74113","AP DETECTORS & DIAGNOSTICS","2006-06-23","2008-07-28"]
["XE_7421","AWARD: Contract Far Hall Detectors - Laser PPS","2007-02-12","2007-02-12"]
["XE_7431","Vendor Fab/Ship Far Hall Alarm/Sign - Laser PPS","2007-02-13","2007-04-10"]
["XE_7441","Vendor Ship Far Hall Contain/Intrlck-Laser PPS","2007-02-13","2007-04-10"]
["XE_7451","Vendor Fab/Ship Far Hall Detectors - Laser PPS","2007-02-13","2007-04-10"]
["XE_7461","RECV: Far Hall Alarms/Signs - Laser PPS","2007-04-11","2007-04-10"]
["XE_7471","RECV: Far Hall Containment/Interlock -Laser PPS","2007-04-11","2007-04-10"]
["XE_7481","RECV: Far Hall Detectors - Laser PPS","2007-04-11","2007-04-10"]
["XE_7491","REQD: Far Hall Beneficial Occup - Laser PPS","2007-08-07","2007-08-06"]
["XE_750","Give Specs for Near Hall Laser Room to CF","2007-03-05","2007-03-02"]
["XE_7500","RECV:  AP Samples","2008-02-26","2008-02-25"]
["XE_7501","Install Far Hall Alarms/Signs - Laser PPS","2007-08-07","2007-09-04"]
["XE_7511","Install Far Hall Contain/Interlck - Laser PPS","2007-08-07","2007-09-04"]
["XE_7521","Install Far Hall Detectors - Laser PPS","2007-08-07","2007-09-04"]
["XE_7531","Test Far Hall - Laser PPS","2007-09-05","2007-09-11"]
["XE_7555","Specification - Streak Camera","2006-02-01","2006-03-29"]
["XE_7556","Detector Engineering","2006-01-17","2008-10-13",null,"2006-01-17"]
["XE_7591","AVAIL: Far Hall Laser PPS","2007-04-11","2007-04-10"]
["XE_760","FAR HALL LASER PPS","2006-06-23","2007-08-06"]
["XE_80","Design FEE - PPS","2006-03-02","2006-04-26"]
["XE_800","Specification Gauges - Vacuum","2007-08-23","2007-10-18"]
["XE_801","Design Gauges - Vacuum","2007-10-19","2008-01-02"]
["XE_802","Design Review Gauges - Vacuum","2008-01-03","2008-01-09"]
["XE_803","COMP: Design Gauges - Vacuum","2008-01-10","2008-01-09"]
["XE_804","Prep Bid Pkg Gauges - Vacuum","2008-01-10","2008-01-16"]
["XE_805","Bid Process Gauges - Vacuum","2008-01-17","2008-02-14"]
["XE_806","Test Gauges - Vacuum System","2008-04-29","2008-07-23"]
["XE_807","AWARD: Contract Gauges - Vacuum","2008-02-15","2008-02-15"]
["XE_808","Vendor Fab/Ship Gauges - Vacuum","2008-02-19","2008-04-14"]
["XE_809","RECV:  Gauges - Vacuum","2008-04-15","2008-04-14"]
["XE_81","Specification FEE - X-Ray PPS","2006-02-01","2006-03-01"]
["XE_810","VACUUM GAUGES","2007-08-23","2008-04-21"]
["XE_816","REQD: Near Hall Beneficial Occupancy","2008-04-22","2008-04-21"]
["XE_817","Install Near Hall Gauges - Vacuum","2008-04-22","2008-04-28"]
["XE_818","COMP: Near Hall Gauges - Vacuum","2008-04-29","2008-04-28"]
["XE_819","Assemble Far Hall  Gauges - Vacuum","2008-04-15","2008-04-21"]
["XE_824","REQD: Far Hall Beneficial Occupancy","2008-04-22","2008-04-21"]
["XE_825","Install Far Hall Gauges - Vacuum","2008-04-22","2008-04-28"]
["XE_826","COMP: Far Hall Gauges - Vacuum","2008-07-24","2008-07-23"]
["XE_827","COMP: Gauges - Vacuum System","2008-07-24","2008-07-23"]
["XE_828","Commission Gauges - Vacuum","2008-07-24","2008-08-20"]
["XE_829","Assemble Near Hall Gauges - Vacuum","2008-04-15","2008-04-21"]
["XE_834","AVAIL: Far Hall Gauges - Vacuum","2008-04-22","2008-04-21"]
["XE_836","AVAIL: Near Hall Gauges - Vacuum","2008-04-22","2008-04-21"]
["XE_850","Specification Far Hall - User Safeguards","2006-06-23","2006-07-21"]
["XE_851","Design Far Hall - User Safeguards","2006-07-24","2006-09-18"]
["XE_852","COMP: Far Hall Design - User Safeguards","2006-11-14","2006-11-13"]
["XE_853","Safety Review Far Hall - User Safeguards","2006-09-19","2006-11-13"]
["XE_854","Prep Bid Pkg Far Hall Alarms/Signs - User Safegu","2006-11-14","2006-11-29"]
["XE_855","Prep Bid Pkg Far Hall Interlock - User Safeguard","2006-11-14","2006-11-29"]
["XE_856","Prepare Far Hall Bid Pkg Detectors - User Safegu","2006-11-14","2006-11-29"]
["XE_857","Bid Process Far Hall Alarms/Signs - User Safegua","2006-11-30","2007-02-09"]
["XE_858","Bid Process Far Hall Interlock - User Safeguards","2006-11-30","2007-02-09"]
["XE_859","Bid Process Far Hall Detectors - User Safeguards","2006-11-30","2007-02-09"]
["XE_860","AWARD: Contract Far Hall Alarms/Signs -User Saf","2007-02-12","2007-02-12"]
["XE_861","AWARD: Contract Far Hall Interlck - User Safegu","2007-02-12","2007-02-12"]
["XE_862","AWARD: Contract Far Hall Detectors - User Safeg","2007-02-12","2007-02-12"]
["XE_863","Vendor Fab/Ship Far Hall Alarm/Sign - User Safeg","2007-02-13","2007-04-10"]
["XE_864","Vendor Ship Far Hall Contain/Intrlck-User Safegu","2007-02-13","2007-04-10"]
["XE_865","Vendor Fab/Ship Far Hall Detectors - User Safegu","2007-02-13","2007-04-10"]
["XE_866","RECV: Far Hall Alarms/Signs - User Safeguards","2007-04-11","2007-04-10"]
["XE_867","RECV: Far Hall Containment/Interlock -User Safeg","2007-04-11","2007-04-10"]
["XE_868","RECV: Far Hall Detectors - User Safeguards","2007-04-11","2007-04-10"]
["XE_869","REQD: Far Hall Beneficial Occup - User Safeguard","2007-08-07","2007-08-06"]
["XE_870","Install Far Hall Alarms/Signs - User Safeguards","2007-08-07","2007-09-04"]
["XE_871","Install Far Hall Contain/Interlck - User Safegua","2007-08-07","2007-09-04"]
["XE_872","Install Far Hall Detectors - User Safeguards","2007-08-07","2007-09-04"]
["XE_873","Test Far Hall - User Safeguards","2007-09-05","2007-09-11"]
["XE_874","COMP: Far Hall User Safeguards","2007-09-12","2007-09-11"]
["XE_879","AVAIL: Far Hall User Safeguards","2007-04-11","2007-04-10"]
["XE_880","FAR HALL USER SAFEGUARDS","2006-06-23","2007-08-06"]
["XE_884","Commission Far Hall - User Safeguards","2007-09-12","2007-10-09"]
["XE_8902","Mechanical Support - Vacuum","2007-10-01","2008-09-30"]
["XE_90","Safety Review FEE - PPS","2006-04-27","2006-06-22"]
["XE_900","Specification Near Hall - User Safeguards","2006-06-23","2006-07-21"]
["XE_901","Design Near Hall - User Safeguards","2006-07-24","2006-09-18"]
["XE_902","COMP: Near Hall Design - User Safeguards","2006-11-14","2006-11-13"]
["XE_903","Safety Review Near Hall - User Safeguards","2006-09-19","2006-11-13"]
["XE_904","Prep Bid Pkg Near Hall Alarms/Signs - User Safeg","2006-11-14","2006-11-29"]
["XE_905","Prep Bid Pkg NHall Interlock - User Safeguards","2006-11-14","2006-11-29"]
["XE_906","Prepare Near Hall Bid Pkg Detectors - User Safeg","2006-11-14","2006-11-29"]
["XE_907","Bid Process Near Hall Alarms/Signs - User Safegu","2006-11-30","2007-02-09"]
["XE_908","Bid Process NHall Interlock - User Safeguards","2006-11-30","2007-02-09"]
["XE_909","Bid Process Near Hall Detectors - User Safeguard","2006-11-30","2007-02-09"]
["XE_91","COMP: FEE Design - X-Ray PPS","2006-06-23","2006-06-22"]
["XE_910","AWARD: Contract Near Hall Alarms/Signs -User Sa","2007-02-12","2007-02-12"]
["XE_911","AWARD: Contract NHall Interlock - User Safeguar","2007-02-12","2007-02-12"]
["XE_912","AWARD: Contract Near Hall Detectors - User Safe","2007-02-12","2007-02-12"]
["XE_913","Vendor Fab/Ship Near Hall Alarm/Sign - User Safe","2007-02-13","2007-04-10"]
["XE_914","Vendor Ship Near Hall Intrlock-User Safeguards","2007-02-13","2007-04-10"]
["XE_915","Vendor Fab/Ship Near Hall Detectors - User Safeg","2007-02-13","2007-04-10"]
["XE_916","RECV: Near Hall Alarms/Signs - User Safeguards","2007-04-11","2007-04-10"]
["XE_917","RECV: Near Hall Interlock -User Safeguards","2007-04-11","2007-04-10"]
["XE_918","RECV: Near Hall Detectors - User Safeguards","2007-04-11","2007-04-10"]
["XE_919","REQD: Near Hall Beneficial Occup - User Safeguar","2007-05-22","2007-05-21"]
["XE_92","Prepare Bid Pkg FEE Detectors - PPS","2006-10-02","2006-10-13"]
["XE_920","Install Near Hall Alarms/Signs - User Safeguards","2007-05-22","2007-06-19"]
["XE_921","Install Near Hall Contain/Interlck - User Safegu","2007-05-22","2007-06-19"]
["XE_922","Install Near Hall Detectors - User Safeguards","2007-05-22","2007-06-19"]
["XE_923","Test Near Hall - User Safeguards","2007-06-20","2007-06-26"]
["XE_924","COMP: Near Hall User Safeguards","2007-06-27","2007-06-26"]
["XE_929","AVAIL: Near Hall User Safeguard","2007-04-11","2007-04-10"]
["XE_93","Bid Process FEE Detectors - PPS","2006-10-16","2006-12-12"]
["XE_930","NEAR HALL USER SAFEGUARDS","2006-06-23","2007-05-21"]
["XE_934","Commission Near Hall - User Safeguards","2007-06-27","2007-07-25"]
["XE_94","AWARD: Contract FEE Detectors - PPS","2006-12-13","2006-12-13"]
["XE_95","Vendor Fab/Ship FEE Detectors - PPS","2006-12-14","2007-02-26"]
["XE_96","RECV: FEE Detectors - PPS","2007-02-27","2007-02-26"]
["XE_98","COMP: FEE X-RAY PPS","2008-05-06","2008-05-05"]
["XE_99","Install FEE Detectors - PPS","2008-03-04","2008-04-28"]
["XE_990","Engineering - Laser Diagnostics","2006-06-05","2008-09-30"]
["XE_9901","Mechanical Engineering - Vacuum","2006-06-05","2007-09-28"]
["XE_LOE","XE LOE Complete","2008-10-01","2008-09-30"]
["XE_M07","Complete 2-D X-Ray Detector Statement of Work","2005-05-17","2005-05-16",null,"2005-05-17","2005-05-16"]
["XE_M08","Award Initial Funding for 2-D X-Ray Detector","2005-07-16","2005-07-15",null,"2005-07-16","2005-07-15"]
["XE_M09","Hire Detector Physicist","2006-01-18","2006-01-17",null,"2006-01-18","2006-01-17"]
["XE_M12","Hire Atomic Physicist","2006-01-04","2006-01-03",null,"2006-01-04","2006-01-03"]
["XE_M13","Hire Controls Engineer","2006-04-18","2006-04-17"]
["XE_M14","COMP: 2006 Design Review - 2-D X-Ray Detector","2006-10-31","2006-10-30"]
["XE_M15","Hire Laser Scientist","2006-06-09","2006-06-08"]
["XE_M16","Hire Mechanical/Vacuum Engineer","2006-06-09","2006-06-08"]
["XE_M17","Start Programming Beamline Controls","2007-06-07","2007-06-06"]
["XE_M18","COMP: Network Design Review","2007-02-13","2007-02-12"]
["XE_M19","Laser System Final Design Review","2007-12-10","2007-12-07"]
["XE_M20","Atomic Physics Final Design Review","2008-01-10","2008-01-09"]
["XE_M21","Final Design Review Experimental Chamber","2007-08-23","2007-08-22"]
["XE_M22","Award Experimental Chambers-Near Hall & Far Hall","2007-10-01","2007-09-28"]
["XE_M222","2007 Design Review - 2-D X-Ray Detector","2008-01-02","2007-12-14"]
["XE_M23","Award Oscillator Laser/Pump","2008-02-08","2008-02-07"]
["XE_M24","Complete Laser PPS Design Review","2006-11-14","2006-11-13"]
["XE_M25","X-Ray PPS Final Design Review","2006-06-23","2006-06-22"]
["XE_M27","Start Installation in Near Hall","2007-05-22","2007-05-21"]
["XE_M28","Start Installation in Far Hall","2007-08-07","2007-08-06"]
["XE_M29","Complete Near Hall Installation","2008-10-23","2008-10-22"]
["XE_M30","COMP:  Final Design Review Beamline Control","2007-06-07","2007-06-06"]
["XE_M31","Laser Operating in Near Hall","2008-10-23","2008-10-22"]
["XE_M33","Complete Beamline Control","2008-04-14","2008-04-11"]
["XE_M34","Certify Near Hall X-Ray PPS and MPS","2007-06-27","2007-06-26"]
["XE_M35","Certify X-Ray PPS and MPS in Far Hall","2007-09-12","2007-09-11"]
["XE_M36","Complete Network & Cable - Ready to Commission","2008-07-16","2008-07-15"]
["XE_M37","Complete Mechanical & Vacuum - Ready to Commiss","2008-07-24","2008-07-23"]
["XE_M38","Synchronize NH Laser with LINAC Master Oscillato","2008-07-28","2008-07-25"]
["XE_M40","Complete Accept Tests for 2-D X-Ray Detector","2009-01-26","2009-01-23"]
["XE_M41","First Atomic Physics Experiment","2008-07-28","2008-07-25"]
["XE_M55","COMP:  Specification - Streak Camera","2006-03-30","2006-03-29"]
["XE_MS2005","FY-05 Resource Available","2005-11-01","2005-10-31",null,"2005-11-01","2005-10-31"]
["XTMS3_066","Near Experimental Hall Commissioning","2007-12-06","2008-01-18"]
["XTMS3_080","Front End Enclosure Commissioning","2008-01-17","2008-03-14"]
["XTOPS_0000","XTOD Pre-Operations","2008-04-04","2009-03-31"]
["XT_0112","COMP: Controls System Tests Complete","2008-01-30","2008-01-29"]
["XT_0115","Assemble FEE - EPICS","2006-11-14","2007-01-26"]
["XT_0116","Programming FEE - EPICS","2007-01-29","2007-03-26"]
["XT_0117","Test FEE - Controls","2007-11-21","2008-01-07"]
["XT_0119","AWARD: EPICS Tools","2006-10-16","2006-10-16"]
["XT_0121","Install FEE - Controls","2007-08-28","2007-09-25"]
["XT_0122","Integrate FEE -  Controls","2007-09-26","2007-11-20"]
["XT_0124","REQD: FEE Beneficial Occup - EPICS","2007-08-28","2007-08-27"]
["XT_0125","REQD: Near Hall Beneficial Occup - EPICS","2007-06-20","2007-06-19"]
["XT_0126","Assemble Near Hall - EPICS","2006-11-14","2007-01-26"]
["XT_0127","Programming Near Hall - EPICS","2007-01-29","2007-03-26"]
["XT_0128","Install Near Hall - Controls","2007-06-20","2007-08-15"]
["XT_0129","Integrate Near Hall - Controls","2007-08-16","2007-10-11"]
["XT_0130","Test Near Hall - Controls","2007-10-12","2007-11-08"]
["XT_0131","REQD: Far Hall Beneficial Occup - EPICS","2007-08-21","2007-08-20"]
["XT_0132","Assemble Far Hall - EPICS","2006-11-14","2007-01-26"]
["XT_0133","Programming Far Hall - EPICS","2007-01-29","2007-03-26"]
["XT_0134","Install Far Hall - Controls","2007-08-21","2007-10-16"]
["XT_0135","Integrate Far Hall - Controls","2007-10-17","2007-12-13"]
["XT_0136","Test Far Hall - Controls","2007-12-14","2008-01-29"]
["XT_0157","Commission FEE - Femto Controls","2007-12-07","2008-01-22"]
["XT_03","AWARD: Contract Optics - Direct Imager","2007-03-07","2007-03-07"]
["XT_04","AWARD: Contract Mechanism - Direct Imager","2007-03-07","2007-03-07"]
["XT_0461","Install Ion Gauges - NH Mech/Vac - H1","2007-10-05","2007-10-11"]
["XT_0462","Install Spools - NH Mech/Vac - H1","2007-10-05","2007-10-11"]
["XT_05","AWARD: CCD Sensors - Direct Imager","2007-03-07","2007-03-07"]
["XT_050","FEE Mgt - FEE Mech/Vac","2005-10-03","2006-01-31",null,"2005-10-03"]
["XT_0500","Beam Tube Spt Primary Design - FEE Mech/Vac","2006-04-10","2006-04-25"]
["XT_0501","Beam Tube Spt  Detail Design - FEE Mech/Vac","2006-04-26","2006-05-04"]
["XT_0502","Beam Tube Spt  Design Check - FEE Mech/Vac","2006-05-05","2006-05-09"]
["XT_0503","Beam Tube Spt  Design Back Check - FEE Mech/Vac","2006-05-10","2006-05-12"]
["XT_0550","Prepare Install Plan - FEE Mech/Vac","2006-10-02","2007-02-08"]
["XT_05505","Material & Supplies - Near Hall","2007-08-16","2007-09-13"]
["XT_0552","Pkg and Ship to SLAC - FEE Mech/Vac","2007-06-15","2007-06-28"]
["XT_0553","ICD - XTOD-Linac","2006-02-01","2006-01-31"]
["XT_0554","ICD - XTOD-XES","2006-02-01","2006-01-31"]
["XT_0555","ICD - XTOD-CF","2006-02-01","2006-01-31"]
["XT_0556","Prelim Analysis of Flex Support-Tunnel Mech/Vac","2005-12-01","2005-12-15",null,"2005-12-01","2005-12-15"]
["XT_0557","Detail Analysis of Flex Support- Tunnel Mech/Vac","2006-01-03","2006-01-24",null,"2006-01-03","2006-01-24"]
["XT_056","Mgt - Ion Chamber","2006-02-01","2007-01-30"]
["XT_0560","Write IWS - Tunnel Mech/Vac","2006-02-01","2006-03-29"]
["XT_06","Order & Receive Scintillator - Direct Imager","2007-03-08","2007-05-02"]
["XT_060","Townsend Phase I - Total Energy","2006-02-01","2006-05-24"]
["XT_061","Townsend Phase II - Total Energy","2006-05-25","2006-08-18"]
["XT_07","AWARD: Scintillator  - Direct Imager","2007-03-07","2007-03-07"]
["XT_070","Configuration Drawing Mgt","2005-12-02","2007-09-28",null,"2005-12-02"]
["XT_08","Order & Receive Optics - Direct Imager","2007-03-08","2007-05-02"]
["XT_082","COMP: X-Ray Transport","2010-04-06","2010-04-05"]
["XT_09","REQD:  FEE Beneficial Occup - Direct Imager","2007-08-28","2007-08-27"]
["XT_0900","Physics Specification I - FEL Mirrors","2006-01-03","2006-04-26",null,"2006-01-03"]
["XT_0901","Conceptual Design Prep - FEL Mirrors","2006-08-21","2006-09-01"]
["XT_0902","Write ESD - FEL Mirrors","2006-08-21","2006-09-01"]
["XT_0903","Conceptual Design - FEL Mirrors","2006-06-16","2006-08-18"]
["XT_0904","Conceptual Design  Review - FEL Mirrors","2006-09-05","2006-09-01"]
["XT_0905","Revise IWS- FEL Mirrors","2006-09-05","2006-09-18"]
["XT_0910","Controls Defined - FEL Mirrors","2006-09-05","2006-09-08"]
["XT_0912","Engineering Analysis - FEL Mirrors","2006-09-05","2006-10-30"]
["XT_0913","Vacuum Analysis - FEL Mirrors","2006-08-21","2006-09-18"]
["XT_092","REQD: FEE BO","2007-08-27","2007-08-27"]
["XT_0923","Preliminary Design Prep - FEL Mirrors","2006-10-31","2006-11-13"]
["XT_0924","Controls Redefined - FEL Mirrors","2006-10-31","2006-11-15"]
["XT_0925","Preliminary Design Review - FEL Mirrors","2006-11-14","2006-11-13"]
["XT_0926","Write Safety/Ref Note - FEL Mirrors","2006-11-16","2006-12-15"]
["XT_0927","Safety/Ref Note 1st Review - FEL Mirrors","2006-12-18","2007-01-09"]
["XT_0928","Safety/Ref Note 2nd Review - FEL Mirrors","2007-01-10","2007-01-19"]
["XT_0929","Safety/Ref Note Division Review - FEL Mirrors","2007-01-22","2007-01-30"]
["XT_0930","Final Design Prep - FEL Mirrors","2007-01-31","2007-02-13"]
["XT_0931","Prep Procure Docs Optics - FEL Mirrors","2007-02-14","2007-03-14"]
["XT_0932","Prep Procure Docs Vacuum Comp - FEL Mirrors","2007-02-14","2007-03-14"]
["XT_0933","Prep Procure Docs Electronics - FEL Mirrors","2007-02-14","2007-03-14"]
["XT_0934","Prep Procure Docs Mechanisms - FEL Mirrors","2007-02-14","2007-03-14"]
["XT_0935","Final Design Review - FEL Mirrors","2007-02-14","2007-02-13"]
["XT_0936","Select Vendor Optics - FEL Mirrors","2007-03-15","2007-04-11"]
["XT_0937","Select Vendor Vacuum Components - FEL Mirrors","2007-03-15","2007-04-11"]
["XT_0938","Select Vendor Electronics - FEL Mirrors","2007-03-15","2007-04-11"]
["XT_0939","Select Vendor Mechanisms - FEL Mirrors","2007-03-15","2007-04-11"]
["XT_0940","Procure Review Mechanisms - FEL Mirrors","2007-04-12","2007-04-18"]
["XT_0941","Procure Review Optics - FEL Mirrors","2007-04-12","2007-04-18"]
["XT_0942","Procure Review Vacuum Components - FEL Mirrors","2007-04-12","2007-04-18"]
["XT_0943","Procure Review Electronics - FEL Mirrors","2007-04-12","2007-04-18"]
["XT_0944","AWARD: Contract Vacuum Components - FEL Mirrors","2007-04-19","2007-04-19"]
["XT_0945","AWARD: Contract Electronics - FEL Mirrors","2007-04-19","2007-04-19"]
["XT_0946","AWARD: Mechanisms - FEL Mirrors","2007-04-19","2007-04-19"]
["XT_0947","AWARD: Optics- FEL Mirrors","2007-04-19","2007-04-19"]
["XT_0948","Order & Receive Optics - FEL Mirrors","2007-04-20","2007-06-15"]
["XT_0949","Order & Receive Vacuum Components - FEL Mirrors","2007-04-20","2007-06-15"]
["XT_0950","Order & Receive Mechanisms - FEL Mirrors","2007-04-20","2007-06-15"]
["XT_0951","Order & Receive Electronics - FEL Mirrors","2007-04-20","2007-06-15"]
["XT_0952","Component Accept Test Optics-FEL Mirrors","2007-06-18","2007-06-22"]
["XT_0953","Component Accept Test Vacuum Compon-FEL Mirrors","2007-06-18","2007-06-22"]
["XT_0954","Component Accept Test Mechanisms-FEL Mirrors","2007-06-18","2007-06-22"]
["XT_0955","Component Accept Test Electronics -FEL Mirrors","2007-06-18","2007-06-22"]
["XT_0956","Assemble Subsystem at LLNL- FEL Mirrors","2007-06-25","2007-07-23"]
["XT_0957","Test Subsystem at LLNL - FEL Mirrors","2007-07-24","2007-08-20"]
["XT_0958","Pkg and Ship System to SLAC - FEL Mirrors","2007-08-21","2007-09-04"]
["XT_0959","AVAIL: FEL Mirrors","2007-09-05","2007-09-04"]
["XT_0960","REQD:  FEE Beneficial Occup - Mech/Vac","2007-09-05","2007-09-04"]
["XT_1004","Install - Ion Pumped Tank","2007-08-28","2007-11-20"]
["XT_1005","Test - Ion Pumped Tank","2007-11-21","2008-01-07"]
["XT_1006","COMP:  Ion Pumped Tank","2008-01-23","2008-01-22"]
["XT_1007","Commission - FEE Diagnostic Tank","2008-01-30","2008-02-12"]
["XT_1012","COMP: Design - FEE Diagnostic Tank","2007-01-22","2007-01-19"]
["XT_1015","Commission - Ion Pumped Tank","2008-01-08","2008-01-22"]
["XT_1032","Prep Bid Pkg Tank - FEE Diagnostic Tank","2007-01-22","2007-02-02"]
["XT_1042","Bid Process Tank - FEE Diagnostic Tank","2007-02-05","2007-03-05"]
["XT_1052","AWARD: Contract Tank - FEE Diagnostic Tank","2007-03-06","2007-03-06"]
["XT_1062","Vendor Fab/Ship Tank - FEE Diagnostic Tank","2007-03-07","2007-05-30"]
["XT_1072","RECV:  Tank - FEE Diagnostic Tank","2007-05-31","2007-05-30"]
["XT_1108","COMP:  Fixed Mask  Installed & Commissioned","2008-02-06","2008-02-05"]
["XT_1110","Test - Fixed Mask","2007-09-26","2008-01-07"]
["XT_1111","Install - Fixed Mask","2007-08-28","2007-09-25"]
["XT_1156","Commission - Fixed Mask 1","2008-01-08","2008-02-05"]
["XT_122","REQD: NEH BO","2007-06-19","2007-06-19"]
["XT_124","Commission FEE - Fast Controls","2007-12-07","2008-01-22"]
["XT_132","REQD: FEH BO","2007-08-20","2007-08-20"]
["XT_14","Procure Review CCD Sensors - Direct Imager","2007-02-28","2007-03-06"]
["XT_1414","Physics Specification -FEE Mech/Vac-Peter Stefan","2006-01-03","2006-01-31",null,"2006-01-03","2006-01-31"]
["XT_1415","Conceptual Design Prep - Direct Imager","2006-05-25","2006-06-08"]
["XT_1416","Write ESD - Direct Imager","2006-05-25","2006-06-22"]
["XT_1417","Conceptual Design - Direct Imager","2006-01-03","2006-05-24",null,"2006-01-03"]
["XT_1418","Conceptual Design  Review - Direct Imager","2006-06-23","2006-06-22"]
["XT_142","REQD: Tunnel BO","2007-08-03","2007-08-03"]
["XT_1421","Prelim Engineering Analysis - Direct Imager","2006-06-16","2006-07-07"]
["XT_1424","Controls Defined - Direct Imager","2006-07-10","2006-07-13"]
["XT_1427","Engineering - Direct Imager","2006-10-17","2006-11-29"]
["XT_1428","Drafting Design - Direct Imager","2006-05-25","2006-10-16"]
["XT_1433","Detail Engineering Analysis - Direct Imager","2006-07-10","2006-08-18"]
["XT_1437","Preliminary Design Prep - Direct Imager","2006-08-21","2006-09-01"]
["XT_1438","Controls Redefined - Direct Imager","2006-09-05","2006-09-20"]
["XT_1439","Preliminary Design Review - Direct Imager","2006-09-05","2006-09-01"]
["XT_1440","Write Safety/Ref Note - Direct Imager","2006-09-21","2006-10-18"]
["XT_1441","Safety/Ref Note 1st Review - Direct Imager","2006-10-19","2006-11-08"]
["XT_1442","Safety/Ref Note 2nd Review - Direct Imager","2006-11-09","2006-11-17"]
["XT_1443","Safety/Ref Note Division Review - Direct Imager","2006-11-20","2006-11-30"]
["XT_1444","Final Design Prep - Direct Imager","2006-12-01","2006-12-14"]
["XT_1445","Prep Procure Docs Scintillator - Direct Imager","2006-12-15","2007-01-29"]
["XT_1446","Prep Procure Docs Optics - Direct Imager","2006-12-15","2007-01-29"]
["XT_1447","Prep Procure Docs Mechanism - Direct Imager","2006-12-15","2007-01-29"]
["XT_1448","Prep Procure Docs CCD Sensors - Direct Imager","2006-12-15","2007-01-29"]
["XT_1449","Final Design Review - Direct Imager","2006-12-15","2006-12-14"]
["XT_1450","Prepare Bid Pkg Vacuum System Cart - Mech/Vac","2007-05-17","2007-05-23"]
["XT_14500","Select Vendor Scintillator - Direct Imager","2007-01-30","2007-02-27"]
["XT_1451","Bid Process Vacuum System Cart - Mech/Vac","2007-05-24","2007-06-21"]
["XT_14510","Select Vendor Optics - Direct Imager","2007-01-30","2007-02-27"]
["XT_1452","AWARD: Contract Vacuum System Cart - Mech/Vac","2007-06-22","2007-06-22"]
["XT_14520","Select Vendor Mechanism - Direct Imager","2007-01-30","2007-02-27"]
["XT_1453","Vendor Fab/Ship Vacuum System Cart - Mech/Vac","2007-06-25","2007-07-23"]
["XT_14530","Select Vendor CCD Sensors - Direct Imager","2007-01-30","2007-02-27"]
["XT_1454","RECV:  Vacuum System Cart - Mech/Vac","2007-07-24","2007-07-23"]
["XT_14540","Procure Review Scintillator - Direct Imager","2007-02-28","2007-03-06"]
["XT_1455","Prepare Bid Pkg Welding Cart - Mech/Vac","2007-05-24","2007-05-31"]
["XT_14550","Procure Review Optics - Direct Imager","2007-02-28","2007-03-06"]
["XT_1456","Bid Process Welding Cart - Mech/Vac","2007-06-01","2007-06-28"]
["XT_14560","Procure Review Mechanism - Direct Imager","2007-02-28","2007-03-06"]
["XT_1457","AWARD: Contract Welding Cart - Mech/Vac","2007-06-29","2007-06-29"]
["XT_1458","Vendor Fab/Ship Welding Cart - Mech/Vac","2007-07-02","2007-07-30"]
["XT_1459","RECV:  Welding Cart - Mech/Vac","2007-07-31","2007-07-30"]
["XT_1460","Prepare Procure Docs Stands - FEE Mech/Vac","2006-10-02","2006-11-28"]
["XT_1461","Select Vendor Stands - FEE Mech/Vac","2006-05-19","2006-08-14"]
["XT_1464","Order & Receive CCD Sensors - Direct Imager","2007-03-08","2007-05-02"]
["XT_1465","Order & Receive Mechanism - Direct Imager","2007-03-08","2007-05-02"]
["XT_1467","Accept Test - Direct Imager","2007-05-03","2007-05-09"]
["XT_1470","Assemble Subsystem at LLNL- Direct Imager","2007-05-10","2007-06-07"]
["XT_1471","Procurement Review Stands - FEE Mech/Vac","2006-11-29","2006-12-05"]
["XT_1472","Test Subsystem at LLNL - Direct Imager","2007-06-08","2007-07-06"]
["XT_1473","Pkg and Ship System to SLAC - Direct Imager","2007-07-09","2007-07-20"]
["XT_1474","Select Scintillator - Direct Imager","2006-02-01","2006-05-24"]
["XT_1476","Write IWS - Direct Imager","2006-06-09","2006-06-22"]
["XT_1484","Select Optics - Direct Imager","2006-02-01","2006-05-24"]
["XT_1494","Select CCD Sensors - Direct Imager","2006-02-01","2006-05-24"]
["XT_1500","Select Vendor Sensors - Total Energy","2007-04-04","2007-05-01"]
["XT_1501","Select Vendor Cryo Components - Total Ene","2007-04-04","2007-05-01"]
["XT_1502","Select Vendor Electronics - Total Energy","2007-04-04","2007-05-01"]
["XT_1503","Select Vendor Mechanisms - Total Energy","2007-04-04","2007-05-01"]
["XT_152","BCR start","2005-12-01","2005-12-02",null,"2005-12-01","2005-12-02"]
["XT_153","Physics PRD - FEL Mirrors","2006-04-27","2006-04-26"]
["XT_155","Prototype - Testing- Phase II","2006-06-19","2006-06-30"]
["XT_1551","Test at LLNL - FEE Mech/Vac","2007-05-17","2007-06-14"]
["XT_156","Conceptual Design - Gas & Solid Attenuators","2006-01-03","2006-03-01",null,"2006-01-03"]
["XT_157","Conceptual Design Prep - Gas & Solid Attenuators","2006-03-02","2006-03-15"]
["XT_158","Concept Design Review - Gas & Solid Attenuators","2006-03-16","2006-03-15"]
["XT_159","Tunnel Transition Section Eng - Tunnel Mech/Vac","2005-12-01","2005-12-14",null,"2005-12-01","2005-12-14"]
["XT_1600","Prep Procure Docs Sensors - Total Energy","2007-03-07","2007-04-03"]
["XT_1602","Procure Review Sensors - Total Energy","2007-05-02","2007-05-08"]
["XT_1603","AWARD: Sensors - Total Energy","2007-05-09","2007-05-09"]
["XT_1604","Order & Receive Sensors - Total Energy","2007-05-10","2007-06-07"]
["XT_1606","Prep Procure Docs Cryo Components - Total Energy","2007-03-07","2007-04-03"]
["XT_1608","Procure Review Cryo Components - Total Energy","2007-05-02","2007-05-08"]
["XT_1609","AWARD: Contract Cryo Components - Total Energy","2007-05-09","2007-05-09"]
["XT_1610","Order & Receive Cryo Components - Total Energy","2007-05-10","2007-06-07"]
["XT_1800","Engineering Specification - Indirect Imager","2006-01-03","2006-02-14",null,"2006-01-03"]
["XT_1801","Conceptual Design Prep - Indirect Imager","2006-05-04","2006-05-17"]
["XT_1802","Write ESD - Indirect Imager","2006-01-03","2006-02-14",null,"2006-01-03"]
["XT_1803","Conceptual Design - Indirect Imager","2006-03-02","2006-05-03"]
["XT_1804","Conceptual Design  Review - Indirect Imager","2006-06-16","2006-06-15"]
["XT_1805","Write IWS- Indirect Imager","2006-02-15","2006-03-01"]
["XT_1810","Controls Defined - Indirect Imager","2006-06-16","2006-06-21"]
["XT_1811","Prelim Engineering Analysis -Indirect Imager","2006-03-23","2006-04-19"]
["XT_1812","Detail Engineering Analysis - Indirect Imager","2006-04-20","2006-06-22"]
["XT_1813","Vacuum Analysis - Indirect Imager","2006-05-04","2006-06-01"]
["XT_1815","Shared Vacuum Engineering - Indirect Imager","2006-08-21","2006-08-25"]
["XT_1817","Shared Enclosure/Stand Engineer- Indirect Imager","2006-08-21","2006-09-01"]
["XT_1818","Drafting Design-Enclosure- Ind Imager Only","2006-05-04","2006-05-24"]
["XT_1821","Drafting Mechanism Design - Indirect Imager","2006-05-04","2006-08-25"]
["XT_1823","Preliminary Design Prep - Indirect Imager","2006-08-28","2006-09-11"]
["XT_1824","Controls Redefined - Indirect Imager","2006-09-12","2006-09-27"]
["XT_1825","Preliminary Design Review - Indirect Imager","2006-09-12","2006-09-11"]
["XT_1826","Write Safety/Ref Note - Indirect Imager","2006-06-23","2006-07-21"]
["XT_1827","Safety/Ref Note 1st Review - Indirect Imager","2006-07-24","2006-08-11"]
["XT_1828","Safety/Ref Note 2nd Review - Indirect Imager","2006-08-14","2006-08-22"]
["XT_1829","Safety/Ref Note Division Review - Indirect Image","2006-08-23","2006-08-31"]
["XT_1830","Final Design Prep - Indirect Imager","2006-10-24","2006-11-06"]
["XT_1831","Prep Procure Docs CCD Sensors - Indirect Imager","2006-11-07","2006-12-06"]
["XT_1832","Prep Procure Docs Multilayer - Indirect Imager","2006-11-07","2006-12-06"]
["XT_1834","Prep Procure Docs Mechanisms - Indirect Imager","2006-11-07","2006-12-06"]
["XT_1835","Final Design Review - Indirect Imager","2006-11-07","2006-11-06"]
["XT_1836","Select Vendor CCD Sensors - Indirect Imager","2006-12-07","2007-01-19"]
["XT_1837","Select Vendor Multilayer - Indirect Imager","2006-12-07","2007-01-19"]
["XT_1839","Select Vendor Mechanisms - Indirect Imager","2006-12-07","2007-01-19"]
["XT_1840","Procure Review Mechanisms - Indirect Imager","2007-01-22","2007-01-26"]
["XT_1841","Procure Review CCD Sensors - Indirect Imager","2007-01-22","2007-01-26"]
["XT_1842","Procure Review Multilayer - Indirect Imager","2007-01-22","2007-01-26"]
["XT_1844","AWARD: Contract Multilayer - Indirect Image","2007-01-29","2007-01-29"]
["XT_1846","AWARD: Vac Hardware - Indirect Imager","2007-01-29","2007-01-29"]
["XT_1847","AWARD: CCD Sensors - Indirect Imager","2007-01-29","2007-01-29"]
["XT_1848","Order & Receive CCD Sensors - Indirect Image","2007-01-30","2007-03-27"]
["XT_1849","Order & Receive Multilayer - Indirect Image","2007-01-30","2007-03-27"]
["XT_1850","Order & Receive Mechanisms - Indirect Imager","2007-01-30","2007-03-27"]
["XT_1852","Accept Test - Indirect Imager","2007-03-28","2007-04-03"]
["XT_1856","Assemble Subsystem at LLNL- Indirect Imager","2007-04-04","2007-05-01"]
["XT_1857","REQD:  FEE Beneficial Occup - Mech/Vac","2007-08-28","2007-08-27"]
["XT_1859","Test Subsystem at LLNL - Indirect Imager","2007-05-02","2007-05-30"]
["XT_1860","Pkg and Ship System to SLAC - Indirect Imager","2007-05-31","2007-06-13"]
["XT_1890","Multilayer Specification - Indirect Imager","2006-01-03","2006-03-29",null,"2006-01-03"]
["XT_1900","Component Fab Multilayer - Indirect Imager","2006-03-30","2006-05-24"]
["XT_1910","Component Test Multilayer - Indirect Imager","2006-04-20","2006-06-15"]
["XT_1920","Physics Specification - Indirect Imager","2005-12-02","2006-03-01",null,"2005-12-02"]
["XT_200","Engineering Specification - FEE Mech/Vac","2005-12-01","2006-02-06",null,"2005-12-01"]
["XT_201","Vacuum Controls Defined - FEE Mech/Vac","2006-04-12","2006-04-18"]
["XT_2011","Acceptance Test - Gas Attenuator","2007-08-28","2007-09-25"]
["XT_2012","Assemble - Beamline Test - Gas Attenuator","2007-08-28","2007-09-25"]
["XT_2013","Commission - Gas Attenuator","2007-09-26","2007-10-24"]
["XT_2014","COMP:  Gas Attenuator Installed & Commissioned","2007-10-25","2007-10-24"]
["XT_2021","Theory - Gas Attenuator","2006-01-03","2006-01-31",null,"2006-01-03","2006-01-31"]
["XT_2023","Bid Process Hardware - Attenuator","2007-02-16","2007-03-02"]
["XT_2032","AWARD: Contract Hardware - Gas Attenuator","2007-03-05","2007-03-05"]
["XT_2033","Vendor Fab Hardware - Attenuator","2007-03-06","2007-05-29"]
["XT_2053","RECV: Hardware - Attenuator","2007-05-30","2007-05-29"]
["XT_20611","TTF Damage Experiment - FY-06","2005-10-01","2006-06-22",null,"2005-10-01"]
["XT_2063","Assemble Hardware - Attenuator","2007-05-30","2007-07-03"]
["XT_210","Vacuum Analyses - FEE Mech/Vac","2006-03-22","2006-04-04"]
["XT_2111","Install - FEE Mech/Vac","2007-08-28","2007-09-04"]
["XT_2125","REQD: FEE Beneficial Occupancy Attenuators","2007-08-28","2007-08-27"]
["XT_217","Prep Procure Docs Vac Hardware - FEE Mech/Vac","2006-08-14","2006-10-09"]
["XT_218","AWARD: Vac Hardware - FEE Mech/Vac","2006-10-17","2006-10-17"]
["XT_219","Component Accept Test Vac Hardware-FEE Mech/Vac","2007-03-15","2007-03-21"]
["XT_220","Vacuum Components Defined - FEE Mech/Vac","2006-04-05","2006-04-11"]
["XT_224","REQD:  FEE Beneficial Occup - Mech/Vac","2007-08-28","2007-08-27"]
["XT_227","Select Vac Hardware Vendor - FEE Mech/Vac","2006-05-19","2006-08-14"]
["XT_233","Administrative/Database Support - LLNL-CON","2005-10-01","2008-10-15",null,"2005-10-01"]
["XT_234","Teleconference/Comp - LLNL-CON","2005-10-01","2008-10-15",null,"2005-10-01"]
["XT_2340","Physics Specification - Total Energy","2005-12-02","2006-04-26",null,"2005-12-02"]
["XT_235","Project Support M&S - LLNL-CON","2005-10-01","2008-10-15",null,"2005-10-01"]
["XT_237","Procurement Review Vac Hardware - FEE Mech/Vac","2006-10-10","2006-10-16"]
["XT_24","AVAIL: FEE Mechanical/Vacuum","2007-08-28","2007-08-27"]
["XT_240","Write ESD - FEE Mech/Vac","2006-01-03","2006-03-01",null,"2006-01-03"]
["XT_242","Engineering Specification - NEH Mech/Vac","2006-05-11","2006-06-08"]
["XT_243","Conceptual Design Review Prep - FEE Mech/Vac","2006-03-08","2006-03-21"]
["XT_244","Preliminary Design Review Prep - FEE Mech/Vac","2006-04-05","2006-04-18"]
["XT_247","Order & Receive Vac Hardware - FEE Mech/Vac","2006-10-18","2007-03-14"]
["XT_250","Conceptual Design - FEE Mech/Vac","2006-02-07","2006-03-07"]
["XT_255","Engineering Specification - FEL Mirrors","2006-03-16","2006-04-12"]
["XT_256","Mirror Specification - FEL Mirrors","2006-01-09","2006-03-15",null,"2006-01-09"]
["XT_2560","Engineering - Indirect Imager","2006-09-12","2006-10-23"]
["XT_26","Install Vacuum Piping - Far Hall Mech/Vac","2008-01-30","2008-02-05"]
["XT_260","Specification - Fixed Mask","2005-12-14","2006-02-07",null,"2005-12-14"]
["XT_267","Physics Requirements Doc Comp - Gas Attenuator","2006-04-06","2006-04-05"]
["XT_2690","Material Mgt","2005-12-02","2007-09-28",null,"2005-12-02"]
["XT_2700","Conceptual Design Prep - NEH Mech/Vac","2006-06-23","2006-07-07"]
["XT_271","AWARD Prototype Procurement - Gas Attenuator","2006-02-01","2006-02-01"]
["XT_2710","Conceptual Design Review - NEH Mech/Vac","2006-07-10","2006-07-07"]
["XT_273","Final Design Prep - Attenuator","2007-01-09","2007-01-23"]
["XT_2755","Prelim Design Review - Attenuator","2006-12-11","2006-12-08"]
["XT_277","Wave Modeling - FY-06","2006-01-03","2006-09-29",null,"2006-01-03"]
["XT_280","Fast Valve Design - FEE Mech/Vac","2006-01-03","2006-02-22",null,"2006-01-03"]
["XT_284","Monte Carlo Modeling - FY-06","2006-01-03","2006-09-29",null,"2006-01-03"]
["XT_286","Final Design Review Prep - FEH Mech/Vac","2007-01-08","2007-01-22"]
["XT_296","Final Design Review Prep- Tunnel Mech/Vac","2006-03-02","2006-03-29"]
["XT_30200","Prep Procure Docs Stand - FEL Mirrors","2007-02-14","2007-03-14"]
["XT_30201","Select Vendor Stand- FEL Mirrors","2007-03-15","2007-04-11"]
["XT_30202","Procure Review Stand - FEL Mirrors","2007-04-12","2007-04-18"]
["XT_30203","AWARD: Stand - FEL Mirrors","2007-04-19","2007-04-19"]
["XT_30204","Order & Receive Stand - FEL Mirrors","2007-04-20","2007-06-15"]
["XT_30205","Component Accept Test Stand-FEL Mirrors","2007-06-18","2007-06-22"]
["XT_30206","Prep Procure Docs Enclosure - FEL Mirrors","2007-02-14","2007-03-14"]
["XT_30207","Select Vendor Enclosure- FEL Mirrors","2007-03-15","2007-04-11"]
["XT_30208","Procure Review Enclosure - FEL Mirrors","2007-04-12","2007-04-18"]
["XT_30209","AWARD: Enclosure - FEL Mirrors","2007-04-19","2007-04-19"]
["XT_30210","Order & Receive Enclosure - FEL Mirrors","2007-04-20","2007-06-15"]
["XT_30211","Component Accept Test Enclosure-FEL Mirrors","2007-06-18","2007-06-22"]
["XT_303","Physics Requirements Document - Indirect Imager","2006-03-02","2006-03-01"]
["XT_30311","Write IWS - Spectrometer","2006-05-11","2006-05-24"]
["XT_30316","Physics Specification - Spectrometer","2006-02-01","2006-04-26"]
["XT_30317","Conceptual Design Prep - Spectrometer","2006-02-01","2006-02-14"]
["XT_30318","Write ESD - Spectrometer","2006-05-11","2006-05-24"]
["XT_30319","Conceptual Design - Spectrometer","2006-01-03","2006-01-31",null,"2006-01-03"]
["XT_30320","Conceptual Design  Review - Spectrometer","2006-02-15","2006-02-14"]
["XT_30323","Engineering Analysis - Spectrometer","2006-02-23","2006-04-19"]
["XT_30325","Controls Defined - Spectrometer","2006-05-11","2006-05-16"]
["XT_30334","Design - Spectrometer","2006-02-15","2006-04-12"]
["XT_30337","Preliminary Design Prep - Spectrometer","2006-04-27","2006-05-10"]
["XT_30338","Controls Redefined - Spectrometer","2006-05-17","2006-06-02"]
["XT_30339","Preliminary Design Review - Spectrometer","2006-05-11","2006-05-10"]
["XT_30340","Write Safety/Ref Note - Spectrometer","2006-06-05","2006-06-30"]
["XT_30341","Safety/Ref Note 1st Review - Spectrometer","2006-07-03","2006-07-24"]
["XT_30342","Safety/Ref Note 2nd Review - Spectrometer","2006-07-25","2006-08-02"]
["XT_30343","Safety/Ref Note Division Review - Spectrometer","2006-08-03","2006-08-11"]
["XT_30344","Final Design Prep - Spectrometer","2006-08-14","2006-08-25"]
["XT_30345","Prep Procure Docs Readout Electronics - Spectrom","2006-08-28","2006-09-25"]
["XT_30346","Prep Procure Docs Optics - Spectrometer","2006-08-28","2006-09-25"]
["XT_30347","Prep Procure Docs Mechanism - Spectrometer","2006-08-28","2006-09-25"]
["XT_30349","Final Design Review - Spectrometer","2006-08-28","2006-08-25"]
["XT_30350","Select Vendor Readout Electronics - Spectrometer","2006-09-26","2006-10-23"]
["XT_30351","Select Vendor Optics - Spectrometer","2006-09-26","2006-10-23"]
["XT_30352","Select Vendor Mechanism - Spectrometer","2006-09-26","2006-10-23"]
["XT_30355","Procure Review Readout Electronics - Spectromete","2006-10-24","2006-10-30"]
["XT_30356","Procure Review Optics - Spectrometer","2006-10-24","2006-10-30"]
["XT_30357","Procure Review Mechanism - Spectrometer","2006-09-26","2006-10-02"]
["XT_30358","AWARD: Contract Optics - Spectrometer","2006-10-31","2006-10-31"]
["XT_30359","AWARD: Contract Mechanism - Spectrometer","2006-10-03","2006-10-03"]
["XT_30361","AWARD: Readout Electronics  - Spectrometer","2006-10-31","2006-10-31"]
["XT_30362","Order & Receive Readout Electronics - Spectromet","2006-11-01","2006-12-29"]
["XT_30363","Order & Receive Optics - Spectrometer","2006-11-01","2007-01-12"]
["XT_30365","Order & Receive Mechanism - Spectrometer","2006-10-04","2006-11-30"]
["XT_30366","AVAIL: Spectrometer","2007-08-28","2007-08-27"]
["XT_30367","REQD:  FEE Beneficial Occup - Mech/Vac","2007-08-21","2007-08-20"]
["XT_30368","Component Accept Test Readout Electronics-Spectr","2007-01-02","2007-01-08"]
["XT_30369","Component Accept Test Optics - Spectrometer","2007-01-16","2007-01-22"]
["XT_30371","Component Accept Test Mechanism -Spectrometer","2006-12-01","2006-12-07"]
["XT_30372","Assemble Subsystem at LLNL- Spectrometer","2007-01-23","2007-02-20"]
["XT_30373","Test Subsystem at LLNL - Spectrometer","2007-02-21","2007-03-20"]
["XT_30374","Pkg and Ship System to SLAC - Spectrometer","2007-03-21","2007-04-03"]
["XT_330","Install Isolation Valves - NH Mech/Vac - H1","2007-10-05","2007-10-11"]
["XT_340","Install Berilium Valves - NH Mech/Vac - H1","2007-10-05","2007-10-11"]
["XT_345","Physics Requirement Document - Direct Imager","2006-03-02","2006-03-01"]
["XT_3454","LLNL - Commissioning Team","2008-10-01","2010-04-05"]
["XT_346","Physic Specification - Direct Imager","2005-12-02","2006-03-01",null,"2005-12-02"]
["XT_3464","R&D - FEE Physics Preliminary Layout","2005-12-17","2005-12-16",null,"2005-12-17","2005-12-16"]
["XT_3474","R&D - Near Hall Physics Preliminary Layout","2005-12-17","2005-12-16",null,"2005-12-17","2005-12-16"]
["XT_3484","R&D - Far Hall Physics Preliminary Layout","2005-12-17","2005-12-16",null,"2005-12-17","2005-12-16"]
["XT_350","Install Vacuum Piping - NH Mech/Vac - H1","2007-10-05","2007-10-11"]
["XT_3506","Engineering - Indirect Imager","2006-06-23","2006-08-18"]
["XT_3507","Shared Vacuum Engineering -Direct Imager","2006-08-21","2006-08-25"]
["XT_3508","Shared Enclosure/Stand Engineer- Direct Imager","2006-08-21","2006-09-01"]
["XT_360","Install Ion Pumps - NH Mech/Vac - H1","2007-10-05","2007-10-11"]
["XT_370","Final Design Review Prep - FEE Mech/Vac","2006-07-31","2006-08-11"]
["XT_380","Collimators 1,2 Primary Design - FEE Mech/Vac","2006-03-08","2006-03-16"]
["XT_390","Collimators 3,4 Primary Design - FEE Mech/Vac","2006-03-24","2006-04-27"]
["XT_4","Assemble subsystem - FEE Mech/Vac","2007-03-22","2007-05-16"]
["XT_400","Write ESD - Fixed Mask","2006-01-10","2006-02-14",null,"2006-01-10"]
["XT_4003","Assemble Vacuum System - Fixed Mask","2006-10-30","2007-01-16"]
["XT_4009","Prepare Bid Pk Vacuum System - Fixed Mask","2006-06-22","2006-06-28"]
["XT_401","Design - Primary - Fixed Mask","2006-01-10","2006-04-12",null,"2006-01-10"]
["XT_4013","COMP: Design Package - Fixed Mask","2006-06-22","2006-06-21"]
["XT_4017","Bid Process Vacuum System - Fixed Mask","2006-06-29","2006-07-27"]
["XT_402","Write ISW - Fixed Mask","2006-07-28","2006-08-10"]
["XT_4023","AWARD: Contract Vacuum System-Fixed Mask","2006-07-28","2006-08-03"]
["XT_4028","RECV: Vacuum System - Fixed Mask","2006-10-30","2006-10-27"]
["XT_403","Design - Detail - Fixed Mask","2006-04-13","2006-05-16"]
["XT_4034","Vendor Fab Vacuum System - Fixed Mask","2006-08-04","2006-10-27"]
["XT_404","Design - Check - Fixed Mask","2006-05-17","2006-06-12"]
["XT_405","Design - Back Check - Fixed Mask","2006-06-13","2006-06-21"]
["XT_406","Vacuum Analysis Engineering - Fixed Mask","2006-04-13","2006-04-26"]
["XT_407","Select Vacuum Components - Fixed Mask","2006-04-27","2006-04-28"]
["XT_408","Preliminary Design Review Fixed Mask","2006-05-08","2006-05-05"]
["XT_409","Final Design Review - Fixed Mask","2006-06-22","2006-06-21"]
["XT_41","Install Spools - Far Hall Mech/Vac","2008-01-30","2008-02-05"]
["XT_410","Conceptual Design Review - Fixed Mask","2006-02-15","2006-02-14"]
["XT_412","Specification & Design I - Comm Diagnostic Tank","2006-05-26","2006-10-02"]
["XT_413","Preliminary Analysis Mechanic-Fixed Mask","2006-02-15","2006-03-06"]
["XT_414","Detail Analysis Mechanical-Fixed Mask","2006-03-07","2006-04-10"]
["XT_415","Safety Note - Fixed Mask","2006-05-17","2006-06-14"]
["XT_416","Test Vacuum System - Fixed Mask","2007-01-17","2007-02-13"]
["XT_417","COMP:  Comm Diagnostic Tank Installed & Commissi","2007-09-11","2007-09-10"]
["XT_420","Package and Ship - Fixed Mask","2007-02-14","2007-02-28"]
["XT_4202","Conceptual Design Review Prep- Fixed Mask","2006-02-08","2006-02-14"]
["XT_4203","PDR Prep Fixed Mask","2006-05-01","2006-05-05"]
["XT_4204","Final Design Review Prep - Fixed Mask","2006-06-15","2006-06-21"]
["XT_4233","Test - Total Energy Measurement","2007-10-23","2007-11-19"]
["XT_4235","AVAIL:  Fixed Mask Arrives at SLAC","2007-03-01","2007-02-28"]
["XT_4244","COMP:  Total Energy Measurement  Installed & Com","2007-12-06","2007-12-05"]
["XT_430","Pump Cross Detail Design - FEE Mech/Vac","2006-03-22","2006-03-28"]
["XT_4300","Specification - Slit/Collimator","2006-02-01","2006-03-01"]
["XT_4301","Write ESD - Slit/Collimator","2006-02-01","2006-02-14"]
["XT_4302","Write ISW - Slit/Collimator","2006-10-31","2006-11-13"]
["XT_4303","Design - Primary - Slit/Collimator","2006-03-09","2006-06-01"]
["XT_4305","Conceptual Design Review Prep- Slit/Collimator","2006-03-02","2006-03-08"]
["XT_4306","Conceptual Design Review - Slit/Collimator","2006-03-09","2006-03-08"]
["XT_4307","Detail Analysis Mechanical-Slit/Collimator","2005-12-07","2006-03-08",null,"2005-12-07"]
["XT_4309","Engineering - Slit/Collimator","2006-03-09","2006-06-01"]
["XT_4311","PDR Prep - Slit/Collimator","2006-03-09","2006-03-15"]
["XT_4312","Preliminary Design Review - Slit/Collimator","2006-06-02","2006-06-01"]
["XT_4314","Safety Note - Slit/Collimator","2006-06-02","2006-06-29"]
["XT_4316","Final Design Review Prep - Slit/Collimator","2006-07-31","2006-08-04"]
["XT_4317","COMP: Design Package - Slit/Collimator","2006-08-07","2006-08-04"]
["XT_4318","Final Design Review - Slit/Collimator","2006-08-07","2006-08-04"]
["XT_4319","Prep Bid Pk Vac System-Slit/Collimator","2006-08-07","2006-09-01"]
["XT_4320","Bid Process Vacuum System - Slit/Collimator","2006-09-05","2006-10-30"]
["XT_4321","Vendor Fab Vacuum System - Slit/Collimator","2006-10-31","2007-02-09"]
["XT_43211","AWARD:  Slit/Collimator","2006-10-31","2006-10-31"]
["XT_4322","RECV: Vacuum System - Slit/Collimator Mechanism","2007-02-12","2007-02-09"]
["XT_4323","Assemble Vacuum System - Slit/Collimator","2007-02-12","2007-04-09"]
["XT_4324","Test Vacuum System - Slit/Collimator","2007-04-10","2007-05-07"]
["XT_4325","Package and Ship - Slit/Collimator","2007-05-08","2007-05-21"]
["XT_4326","AVAIL:  Slit Arrives at SLAC","2007-05-22","2007-05-21"]
["XT_433","Commission - Total Energy Measurement","2007-11-20","2007-12-05"]
["XT_4378","Engineering Analysis - Ion Chamber","2006-10-17","2006-12-13"]
["XT_43788","Design - Ion Chamber","2006-10-17","2006-12-13"]
["XT_4436","Procure Spares - Direct Imager","2006-10-03","2007-01-11"]
["XT_451","Shared Enclosure/Stand Engineer-Total Energy","2006-10-10","2006-10-23"]
["XT_4522","Install - Total Energy Measurement","2007-08-27","2007-10-22"]
["XT_453","Engineering - Slit/Collimator","2006-06-02","2006-07-28"]
["XT_45301","Write IWS - Ion Chamber","2006-10-17","2006-10-30"]
["XT_45303","Evaluation of Readout Methods - Ion Chamber","2006-03-30","2006-10-16"]
["XT_45306","Physics Specification - Ion Chamber","2005-12-02","2006-03-29",null,"2005-12-02"]
["XT_45307","Conceptual Design Prep - Ion Chamber","2006-04-27","2006-05-10"]
["XT_45308","Write ESD - Ion Chamber","2006-07-10","2006-07-21"]
["XT_45309","Conceptual Design - Ion Chamber","2006-01-03","2006-04-26",null,"2006-01-03"]
["XT_45310","Conceptual Design  Review - Ion Chamber","2006-05-11","2006-05-10"]
["XT_45315","Controls Defined - Ion Chamber","2006-07-10","2006-07-13"]
["XT_45317","Engineering Analysis - Ion Chamber","2006-05-11","2006-07-07"]
["XT_45318","Vacuum Analysis System Design - Ion Chamber","2006-04-27","2006-05-24"]
["XT_45321","Design - Ion Chamber","2006-05-11","2006-07-07"]
["XT_45327","Preliminary Design Prep - Ion Chamber","2006-07-10","2006-07-21"]
["XT_45329","Preliminary Design Review - Ion Chamber","2006-07-24","2006-07-21"]
["XT_45330","Write Safety/Ref Note - Ion Chamber","2006-07-14","2006-08-10"]
["XT_45331","Safety/Ref Note 1st Review - Ion Chamber","2006-10-17","2006-11-06"]
["XT_45332","Safety/Ref Note 2nd Review - Ion Chamber","2006-11-07","2006-11-15"]
["XT_45333","Safety/Ref Note Division Review - Ion Chamber","2006-11-16","2006-11-28"]
["XT_45334","Final Design Prep - Ion Chamber","2006-11-29","2006-12-12"]
["XT_45335","Prep Procure Docs Electrical - Ion Chamber","2006-12-14","2007-01-26"]
["XT_45336","Prep Procure Docs Apertures - Ion Chamber","2006-12-14","2007-01-26"]
["XT_45337","Prep Procure Docs Stand - Ion Chamber","2006-12-14","2007-01-26"]
["XT_45338","Prep Procure Docs Vacuum Components - Ion Chambe","2006-12-14","2007-01-26"]
["XT_45339","Final Design Review - Ion Chamber","2006-12-14","2006-12-13"]
["XT_45340","Select Vendor Electrical - Ion Chamber","2007-01-29","2007-02-26"]
["XT_45341","Select Vendor Apertures - Ion Chamber","2007-01-29","2007-02-26"]
["XT_45342","Select Vendor Stand - Ion Chamber","2007-01-29","2007-02-26"]
["XT_45343","Select Vendor Vacuum Components - Ion Chamber","2007-01-29","2007-02-26"]
["XT_45344","Procure Review Vacuum Components - Ion Chamber","2007-02-27","2007-03-05"]
["XT_45345","Procure Review Electrical - Ion Chamber","2007-02-27","2007-03-05"]
["XT_45346","Procure Review Apertures - Ion Chamber","2007-02-27","2007-03-05"]
["XT_45347","Procure Review Stand - Ion Chamber","2007-02-27","2007-03-05"]
["XT_45348","AWARD: Contract Apertures - Ion Chamber","2007-03-06","2007-03-06"]
["XT_45349","AWARD: Contract Stand - Ion Chamber","2007-03-06","2007-03-06"]
["XT_45350","AWARD: Vacuum Components - Ion Chamber","2007-03-06","2007-03-06"]
["XT_45351","AWARD: Electrical  - Ion Chamber","2007-03-06","2007-03-06"]
["XT_45352","Order & Receive Electrical - Ion Chamber","2007-03-07","2007-05-01"]
["XT_45353","Order & Receive Apertures - Ion Chamber","2007-03-07","2007-05-01"]
["XT_45354","Order & Receive Vacuum Components - Ion Chamber","2007-03-07","2007-05-01"]
["XT_45355","Order & Receive Stand - Ion Chamber","2007-03-07","2007-05-01"]
["XT_45356","AVAIL: Ion Chamber","2007-08-28","2007-08-27"]
["XT_45357","REQD:  FEE Beneficial Occup - Mech/Vac","2007-08-21","2007-08-20"]
["XT_45358","Component Accept Test Electrical-Ion Chamber","2007-05-02","2007-05-08"]
["XT_45359","Component Accept Test Apertures - Ion Chamber","2007-05-02","2007-05-08"]
["XT_45360","Component Accept Test Vacuum Components - Ion Ch","2007-05-02","2007-05-08"]
["XT_45361","Component Accept Test Stand -Ion Chamber","2007-05-02","2007-05-08"]
["XT_45362","Assemble Subsystem at LLNL- Ion Chamber","2007-05-09","2007-06-06"]
["XT_45363","Test Subsystem at LLNL - Ion Chamber","2007-06-07","2007-07-05"]
["XT_45364","Pkg and Ship System to SLAC - Ion Chamber","2007-07-06","2007-07-19"]
["XT_456","Mech/Vac Supplies","2007-10-01","2007-12-26"]
["XT_45600","Prep Procure Docs Enclosure - Ion Chamber","2006-12-14","2007-01-26"]
["XT_45601","Select Vendor  Enclosure - Ion Chamber","2007-01-29","2007-02-26"]
["XT_45602","Procure Review  Enclosure - Ion Chamber","2007-02-27","2007-03-05"]
["XT_45603","AWARD:  Enclosure  - Ion Chamber","2007-03-06","2007-03-06"]
["XT_45604","Order & Receive  Enclosure - Ion Chamber","2007-03-07","2007-05-01"]
["XT_45605","Component Accept Test  Enclosure-Ion Chamber","2007-05-02","2007-05-08"]
["XT_4567","Design II - Motors","2006-08-04","2006-09-29"]
["XT_457","Specification & Design II - Comm Diagnostic Tank","2006-10-03","2007-02-09"]
["XT_460","Prelim Analysis of Stand - FEE Mech/Vac","2006-03-01","2006-03-07"]
["XT_4632","Engineering Analysis - Spectrometer","2006-05-11","2006-06-08"]
["XT_46323","Design - Spectrometer","2006-05-11","2006-06-08"]
["XT_470","Detail Analysis of Stand - FEE Mech/Vac","2006-04-28","2006-05-18"]
["XT_4700","Write ESD - Gas Attenuator","2006-04-27","2006-05-31"]
["XT_4701","Design Studies Conceptual - Gas Attenuator","2006-01-03","2006-01-31",null,"2006-01-03","2006-01-31"]
["XT_4703","Design Studies-Internal Review 1-Gas Attenuator","2006-02-01","2006-01-31",null,"2006-02-01","2006-01-31"]
["XT_4704","Design Studies-PreliminaryDesign-Gas Attenuator","2006-01-13","2006-01-31",null,"2006-01-13","2006-01-31"]
["XT_4706","XRay Source-Facil Contact-Gas Attenuator","2006-01-03","2006-01-31",null,"2006-01-03","2006-01-31"]
["XT_4707","XRay Source- IWS - Gas Attenuator","2006-01-03","2006-01-31",null,"2006-01-03","2006-01-31"]
["XT_4708","XRay Source-Interface - Gas Attenuator","2006-01-03","2006-01-31",null,"2006-01-03","2006-01-31"]
["XT_4709","Engineering - PDR Prep - Attenuator","2006-11-27","2006-12-08"]
["XT_4710","Engineering Design Revision - Attenuator","2006-12-11","2007-02-06"]
["XT_4711","Engineering - Design 1 - Attenuator","2006-08-02","2006-09-27"]
["XT_4712","Safety Note - Gas Attenuator","2005-12-02","2006-02-14",null,"2005-12-02"]
["XT_4713","Engineering - Design 2 -  Attenuator","2006-09-28","2006-11-22"]
["XT_4714","Engineering Final Design Review- Attenuator","2007-02-07","2007-02-06"]
["XT_4715","COMP: Design Package - Attenuator","2007-02-07","2007-02-06"]
["XT_480","Write Safety/Ref Note - FEE Mech/Vac","2006-05-19","2006-06-16"]
["XT_483","Test - Spectral Measurement","2007-06-20","2007-07-18"]
["XT_484","COMP:  Spectral Measurement","2008-01-08","2008-01-07"]
["XT_490","Safety/Ref Note 1st Review - FEE Mech/Vac","2006-06-19","2006-07-10"]
["XT_491","Preliminary Specification - Gas Attenuator","2006-01-03","2006-02-22",null,"2006-01-03"]
["XT_4928","AVAIL: Spectrometer","2007-06-20","2007-06-19"]
["XT_496","Prototype Procurement - Gas Attenuator","2006-01-03","2006-04-26",null,"2006-01-03"]
["XT_497","Prepare Bid Pkg Hardware - Attenuator","2007-02-07","2007-02-15"]
["XT_498","Specification - Solid Attenuator","2005-11-01","2005-11-30",null,"2005-11-01","2005-11-30"]
["XT_5","Mechanical Design/Draft - Tunnel Mech/V","2006-01-03","2006-01-24",null,"2006-01-03","2006-01-24"]
["XT_500","Safety/Ref Note 2nd Review - FEE Mech/Vac","2006-07-11","2006-07-19"]
["XT_5003","COMP:  Solid Attenuator Installed & Commissioned","2007-10-25","2007-10-24"]
["XT_510","Safety/Ref Note SLAC Review - FEE Mech/Vac","2006-07-20","2006-07-28"]
["XT_520","Collimators 3,4 Design Check - FEE Mech/Vac","2006-05-19","2006-05-25"]
["XT_530","Collimators 3,4 Design Back Check - FEE Mech/Vac","2006-05-26","2006-05-31"]
["XT_540","Pump Cross Primary Design - FEE Mech/Vac","2006-03-08","2006-03-21"]
["XT_542","Engineering Analysis - FEL Mirrors","2006-11-14","2007-01-12"]
["XT_5432","Design - FEL Mirrors","2006-11-14","2007-01-12"]
["XT_546","Procure Spares","2008-10-01","2009-01-30"]
["XT_55","Travel - FY06-09","2005-10-01","2009-03-31",null,"2005-10-01"]
["XT_550","Write IWS - Gas Attenuator","2006-01-03","2006-01-31",null,"2006-01-03","2006-01-31"]
["XT_5500","Prototype - Report - Attenuator","2006-07-24","2006-08-01"]
["XT_556","Install Isolation Valve - Tunnel Mech/Vac","2007-09-07","2008-01-16"]
["XT_558","Commission - Tunnel Mech/Vac","2008-01-17","2008-02-14"]
["XT_559","COMP:  Tunnel Mech/Vac  Installed & Commiss","2008-02-15","2008-02-14"]
["XT_560","Collimators 3,4 Detail Design - FEE Mech/Vac","2006-04-28","2006-05-18"]
["XT_567","Prototype - Design","2006-01-03","2006-01-31",null,"2006-01-03","2006-01-31"]
["XT_568","Prototype - First Review","2006-01-14","2006-01-13",null,"2006-01-14","2006-01-13"]
["XT_569","Prototype - Fabrication - Gas Attenuator","2006-01-03","2006-04-26",null,"2006-01-03"]
["XT_570","Prototype - Assembly-Gas Attenuator","2006-04-27","2006-05-18"]
["XT_572","Prototype - Data Analysis - Attenuator","2006-07-03","2006-07-21"]
["XT_574","Commissioning - Spectral Measurement","2007-12-07","2008-01-07"]
["XT_580","Collimators 1,2 Detail Design - FEE Mech/Vac","2006-03-17","2006-03-23"]
["XT_589","Prototype Material - Total Energy","2006-01-03","2006-04-26",null,"2006-01-03"]
["XT_590","Collimators 1,2 Design Check - FEE Mech/Vac","2006-03-24","2006-03-28"]
["XT_596","Test - Direct Imager","2007-09-12","2007-10-09"]
["XT_597","COMP: Direct Imager","2007-10-24","2007-10-23"]
["XT_6","Test - FEE Mech/Vac","2007-10-05","2008-01-16"]
["XT_600","Collimators 1,2 Design Back Check - FEE Mech/Vac","2006-03-29","2006-03-30"]
["XT_610","Pump Cross Design Check - FEE Mech/Vac","2006-03-29","2006-03-30"]
["XT_620","Pump Cross Design Back Check - FEE Mech/Vac","2006-03-31","2006-04-04"]
["XT_6231","Physics Specification II - FEL Mirrors","2006-04-27","2006-08-18"]
["XT_625","AVAIL: Tunnel Mechanical/Vacuum","2007-09-07","2007-09-06"]
["XT_626","Install Vacuum Piping - Tunnel Mech/Vac","2007-09-07","2008-01-16"]
["XT_630","Vacuum Valve Primary Design - FEE Mech/Vac","2006-03-29","2006-04-04"]
["XT_6345","Design - FEL Mirrors","2006-09-05","2006-10-30"]
["XT_635","Visible Calibration - Direct Imager","2007-08-28","2007-09-04"]
["XT_636","Install Ion Pumps - Tunnel Mech/Vac","2007-09-07","2008-01-16"]
["XT_640","Vacuum Valve Detail Design - FEE Mech/Vac","2006-04-05","2006-04-07"]
["XT_645","X-Ray Calibration - Direct Imager","2007-09-05","2007-09-11"]
["XT_646","Install Ion Gauges - Tunnel Mech/Vac","2007-09-07","2008-01-16"]
["XT_647","Install Stands - Tunnel Mech/Vac","2007-09-07","2008-01-16"]
["XT_65","Engineering - Total Energy","2006-10-10","2006-12-06"]
["XT_650","Vacuum Valve Design Check - FEE Mech/Vac","2006-04-10","2006-04-11"]
["XT_6501","Modeling & Simulation - FY-07","2006-10-02","2007-09-28"]
["XT_6502","Modeling & Simulation - FY-08","2007-10-01","2008-09-30"]
["XT_653","Conceptual Design - Slit/Collimator","2005-12-07","2006-03-01",null,"2005-12-07"]
["XT_6532","EPICs Controls Design II - FY-06","2006-04-12","2006-09-29"]
["XT_654","AVAIL: Direct Imager","2007-08-28","2007-08-27"]
["XT_656","Install Spools - Tunnel Mech/Vac","2007-09-07","2008-01-16"]
["XT_660","Vacuum Valve Design Back Check - FEE Mech/Vac","2006-04-12","2006-04-13"]
["XT_66001","Test System - Attenuator","2007-07-05","2007-08-01"]
["XT_66002","Package and Ship - Attenuator","2007-08-02","2007-08-15"]
["XT_6630","Conceptual Design - Total Energy","2006-07-31","2006-09-25"]
["XT_6631","Conceptual Design Review Prep - Total Energy","2006-09-26","2006-10-09"]
["XT_66311","Conceptual Design Review - Total Energy","2006-10-10","2006-10-09"]
["XT_66312","Preliminary Design Review - Total Energy","2006-12-07","2006-12-06"]
["XT_66313","Preliminary Design Prep - Total Energy","2006-10-17","2006-10-30"]
["XT_6632","Prelim Engineering Analysis - Total Energy","2006-10-17","2006-10-23"]
["XT_6633","Write ESD - Total Energy","2006-09-26","2006-10-09"]
["XT_6634","Engineering - Total Energy","2006-12-07","2007-01-19"]
["XT_6640","Vacuum Analysis - Total Energy","2006-04-27","2006-05-24"]
["XT_6641","Shared Vacuum Engineering - Total Energy","2006-05-25","2006-06-01"]
["XT_6642","Detail Engineering Analysis-Total Energy","2006-09-26","2006-10-16"]
["XT_6646","Drafting Design - Total Energy","2006-09-26","2007-02-20"]
["XT_665","AVAIL: Far Hall Mech/Vac","2007-12-14","2008-01-29"]
["XT_6652","Controls Defined - Total Energy","2006-09-26","2006-09-29"]
["XT_6653","Controls Redefined - Total Energy","2006-10-02","2006-10-17"]
["XT_6659","Write Safety/Ref Note - Total Energy","2006-10-18","2006-11-14"]
["XT_6662","Safety/Ref Note 1st Review - Total Energy","2006-11-15","2006-12-07"]
["XT_6663","Safety/Ref Note 2nd Review - Total Energy","2006-12-08","2006-12-18"]
["XT_6664","Safety/Ref Note Division Review - Total Energy","2006-12-19","2006-12-28"]
["XT_6666","Prep Procure Docs Electronics - Total Energy","2007-03-07","2007-04-03"]
["XT_6667","Prep Procure Docs Mechanisms - Total Energy","2007-03-07","2007-04-03"]
["XT_6668","Procure Review Electronics - Total Energy","2007-05-02","2007-05-08"]
["XT_6669","Procure Review Mechanisms - Total Energy","2007-05-02","2007-05-08"]
["XT_667","Test - Far Hall Mech/Vac - H1","2008-02-06","2008-02-20"]
["XT_66701","AWARD: Contract Electronics - Total Energy","2007-05-09","2007-05-09"]
["XT_66720","Order & Receive Mechanisms - Total Energy","2007-05-10","2007-06-07"]
["XT_66730","Order & Receive Electronics - Total Energy","2007-05-10","2007-06-07"]
["XT_66740","REQD:  FEE Beneficial Occup - Mech/Vac","2007-08-28","2007-08-27"]
["XT_66770","Assemble Subsystem at LLNL- Total Energy","2007-06-15","2007-07-13"]
["XT_66780","AWARD: Vac Hardware - Total Energy","2007-05-09","2007-05-09"]
["XT_667801","Test Subsystem at LLNL - Total Energy","2007-07-16","2007-08-10"]
["XT_667901","Pkg and Ship System to SLAC - Total Energy","2007-08-13","2007-08-24"]
["XT_668","Commission - Far Hall Mech/Vac - H1","2008-02-21","2008-03-05"]
["XT_66801","AVAIL: Total Energy","2007-08-27","2007-08-24"]
["XT_66833","Revise IWS- Total Energy","2006-10-10","2006-10-23"]
["XT_669","COMP:  Far Hall Mech/Vac - H1 Installed & Commis","2008-03-06","2008-03-05"]
["XT_67","Prototype - Testing- Phase I","2006-05-19","2006-06-16"]
["XT_6710","Prototype-Sensor Develop Planning- Total Energy","2006-01-03","2006-05-03",null,"2006-01-03"]
["XT_6720","Prototype - Requirements Finalized","2006-05-04","2006-05-03"]
["XT_6730","Sensor Dev-TU Write Scope of Work-Total Energy","2006-01-03","2006-01-31",null,"2006-01-03","2006-01-31"]
["XT_6740","Sensor Develop-TU SOW Signed - Total Energy","2006-02-01","2006-01-31"]
["XT_6750","Sensor Dev Phase I - TU - Total Energy","2006-02-01","2006-05-24"]
["XT_6760","Sensor Dev Phase II - TU - Total Energy","2006-05-25","2006-08-18"]
["XT_6770","Procure Prototype Pulsed Laser - Total Energy","2006-05-04","2006-06-01"]
["XT_678","Pkg and Ship - FEE Diagnostic Tank","2007-09-12","2007-09-18"]
["XT_6780","Procure Prototype Pulse-tube Cryostat - Total En","2006-01-03","2006-01-30",null,"2006-01-03","2006-01-30"]
["XT_6789","Design Studies Preliminary Review-Gas Attenuator","2005-11-21","2005-11-23",null,"2005-11-21","2005-11-23"]
["XT_680","Commission - Near Hall Mech/Vac - H1","2007-10-12","2007-11-08"]
["XT_6800","Prototype Write IWS - Total Energy","2006-05-04","2006-06-01"]
["XT_6810","Prototype Test-Pulse Tube Cryostat -Total Energy","2006-06-02","2006-10-23"]
["XT_6820","Prototype Testing - LN Cryostat - Total Energy","2006-06-02","2006-10-23"]
["XT_68410","Final Design Prep - Total Energy","2007-02-21","2007-03-06"]
["XT_68411","Final Design Review - Total Energy","2007-03-07","2007-03-06"]
["XT_696","Test - Indirect Imager","2007-08-28","2007-09-25"]
["XT_697","COMP:  Indirect Imager Installed & Commissioned","2007-10-10","2007-10-09"]
["XT_7","Commission - FEE Mech/Vac","2008-01-17","2008-03-14"]
["XT_70011","REQD: FEE Beneficial Occupancy","2007-08-28","2007-08-27"]
["XT_7022","REQD: FEE Beneficial Occupancy - Fixed Mask","2007-08-28","2007-08-27"]
["XT_704","AVAIL: Indirect Imager","2007-08-28","2007-08-27"]
["XT_710","AVAIL: Near Hall Mech/Vac","2007-10-05","2007-10-04"]
["XT_730","COMP:  Near Hall Mech/Vac - H1","2007-11-09","2007-11-09"]
["XT_7300","Engineering Specification - FEH Mech/Vac","2006-07-28","2006-08-24"]
["XT_7301","Conceptual Design - FEH Mech/Vac","2006-08-25","2006-09-08"]
["XT_7302","Write ESD - FEH Mech/Vac","2006-09-11","2006-10-06"]
["XT_7304","Vacuum Analyses - FEH Mech/Vac","2006-09-11","2006-10-06"]
["XT_7305","Pump Cross  Design - FEH Mech/Vac","2006-09-11","2006-10-10"]
["XT_7306","Prelim Analysis of Stand - FEH Mech/Vac","2006-09-18","2006-09-22"]
["XT_7308","Vacuum Components Defined - FEH Mech/Vac","2006-10-09","2006-10-13"]
["XT_7309","Detail Analysis of Stand - FEH Mech/Vac","2006-10-11","2006-10-24"]
["XT_7313","Vacuum Controls Defined - FEH Mech/Vac","2006-10-16","2006-10-20"]
["XT_7315","Preliminary Design Review - FEH Mech/Vac","2006-10-25","2006-10-24"]
["XT_7316","Write Safety/Ref Note - FEH Mech/Vac","2006-10-25","2006-11-21"]
["XT_7317","Select Vac Hardware Vendor - FEH Mech/Vac","2006-10-25","2006-10-31"]
["XT_7319","Vacuum Valve Design - FEH Mech/Vac","2006-09-11","2006-10-04"]
["XT_732","AWARD: Prototype Material - Total Energy","2006-05-04","2006-07-28"]
["XT_7320","Select Vendor Stands - FEH Mech/Vac","2006-10-25","2006-10-31"]
["XT_7322","Safety/Ref Note 1st Review - FEH Mech/Vac","2006-11-22","2006-12-14"]
["XT_7326","Safety/Ref Note 2nd Review - FEH Mech/Vac","2006-12-15","2006-12-26"]
["XT_7327","Beam Tube Design - FEH Mech/Vac","2006-09-11","2006-09-26"]
["XT_7330","Safety/Ref Note Division Review - FEH Mech/Vac","2006-12-27","2007-01-05"]
["XT_7333","Final Design Review - FEH Mech/Vac","2007-01-23","2007-01-22"]
["XT_7336","Prepare Procure Docs Stands - FEH Mech/Vac","2007-01-23","2007-02-20"]
["XT_7337","Prep Procure Docs Vac Hardware - FEH Mech/Vac","2007-01-23","2007-02-20"]
["XT_7338","Procurement Review Stands - FEH Mech/Vac","2007-02-21","2007-02-27"]
["XT_7339","Procure Review Vac Hardware - FEH Mech/Vac","2007-02-21","2007-02-27"]
["XT_7340","AWARD: Contract Stands - FEH Mech/Vac","2007-02-28","2007-02-28"]
["XT_7341","AWARD: Vac Hardware - FEH Mech/Vac","2007-02-28","2007-02-28"]
["XT_7342","Order & Receive Vac Hardware - FEH Mech/Vac","2007-03-01","2007-07-20"]
["XT_7343","Order & Receive Stands - FEH Mech/Vac","2007-03-01","2007-07-20"]
["XT_7344","Component Accept Test Vac Hardware-FEH Mech/Vac","2007-07-23","2007-07-27"]
["XT_7345","REQD:  FEH Beneficial Occup - Mech/Vac","2007-08-21","2007-08-20"]
["XT_7346","Prepare Install Plan - FEH Mech/Vac","2007-08-21","2007-12-13"]
["XT_7356","Assemble Subsystem at LLNL- FEH Mech/Vac","2007-07-30","2007-09-24"]
["XT_736","Commission - Direct Imager","2007-10-10","2007-10-23"]
["XT_7366","Test Subsystem at LLNL - FEH Mech/Vac","2007-09-25","2007-10-22"]
["XT_7376","Pkg and Ship System to SLAC - FEH Mech/Vac","2007-10-23","2007-10-23"]
["XT_7400","Physics Specification - NEH Mech/Vac","2006-02-01","2006-05-10"]
["XT_7401","Conceptual Design - NEH Mech/Vac","2006-06-09","2006-06-22"]
["XT_7402","Write ESD - NEH Mech/Vac","2006-06-23","2006-07-21"]
["XT_7404","Vacuum Analyses - NEH Mech/Vac","2006-06-23","2006-07-07"]
["XT_7406","Prelim Analysis of Stand - NEH Mech/Vac","2006-06-30","2006-07-28"]
["XT_7408","Vacuum Components Defined - NEH Mech/Vac","2006-07-10","2006-07-14"]
["XT_7409","Detail Analysis of Stand - NEH Mech/Vac","2006-07-31","2006-08-25"]
["XT_7411","Collimator 6 Design - NEH Mech/Vac","2006-08-07","2006-10-02"]
["XT_7412","Collimator 5 Design  - NEH Mech/Vac","2006-08-03","2006-08-04"]
["XT_7413","Vacuum Controls Defined - NEH Mech/Vac","2006-07-17","2006-07-21"]
["XT_7414","Pump Cross Design - NEH Mech/Vac","2006-07-10","2006-07-21"]
["XT_7415","Preliminary Design Review - NEH Mech/Vac","2006-08-28","2006-08-25"]
["XT_7416","Write Safety/Ref Note - NEH Mech/Vac","2006-08-28","2006-09-25"]
["XT_7417","Select Vac Hardware Vendor - NEH Mech/Vac","2006-08-28","2006-11-20"]
["XT_7420","Select Vendor Stands - NEH Mech/Vac","2006-08-28","2006-11-20"]
["XT_7422","Safety/Ref Note 1st Review - NEH Mech/Vac","2006-09-26","2006-10-16"]
["XT_7426","Safety/Ref Note 2nd Review - NEH Mech/Vac","2006-10-17","2006-10-25"]
["XT_7428","Vacuum Valve Design - NEH Mech/Vac","2006-07-24","2006-07-28"]
["XT_7430","Safety/Ref Note Division Review - NEH Mech/Vac","2006-10-26","2006-11-03"]
["XT_7433","Final Design Review - NEH Mech/Vac","2006-11-06","2006-11-03"]
["XT_7435","Beam Tube Spt  Design - NEH Mech/Vac","2006-07-31","2006-08-02"]
["XT_7436","Prepare Procure Docs Stands - NEH Mech/Vac","2006-11-06","2007-01-18"]
["XT_7437","Prep Procure Docs Vac Hardware - NEH Mech/Vac","2006-11-06","2007-01-18"]
["XT_7438","Procurement Review Stands - NEH Mech/Vac","2007-01-19","2007-01-25"]
["XT_7439","Procure Review Vac Hardware - NEH Mech/Vac","2007-01-19","2007-01-25"]
["XT_7440","AWARD: Contract Stands - NEH Mech/Vac","2007-01-26","2007-01-26"]
["XT_7441","AWARD: Vac Hardware - NEH Mech/Vac","2007-01-26","2007-01-26"]
["XT_7442","Order & Receive Vac Hardware - NEH Mech/Vac","2007-01-29","2007-06-19"]
["XT_7443","Order & Receive Stands - NEH Mech/Vac","2007-01-29","2007-06-19"]
["XT_7444","Component Accept Test Vac Hardware-NEH Mech/Vac","2007-06-20","2007-06-26"]
["XT_7445","REQD:  NEH Beneficial Occup - Mech/Vac","2007-06-20","2007-06-19"]
["XT_7446","Assemble subsystem - NEH Mech/Vac","2007-06-27","2007-08-22"]
["XT_7454","Prepare Install Plan - NEH Mech/Vac","2006-11-06","2007-03-05"]
["XT_7456","Test Subsystem at LLNL - NEH Mech/Vac","2007-08-23","2007-09-20"]
["XT_746","Commission - Indirect Imager","2007-09-26","2007-10-09"]
["XT_7462","Write ESD - Tunnel Mech/Vac","2006-02-01","2006-02-14"]
["XT_7464","Vacuum Analyses - Tunnel Mech/Vac","2005-12-01","2005-12-15",null,"2005-12-01","2005-12-15"]
["XT_7466","Prelim Analysis of Stand - Tunnel Mech/Vac","2005-12-01","2005-12-15",null,"2005-12-01","2005-12-15"]
["XT_7468","Vacuum Components Defined - Tunnel Mech/Vac","2005-12-01","2005-12-15",null,"2005-12-01","2005-12-15"]
["XT_7469","Detail Analysis of Stand - Tunnel Mech/Vac","2005-12-01","2005-12-15",null,"2005-12-01","2005-12-15"]
["XT_7473","Vacuum Controls Defined - Tunnel Mech/Vac","2006-01-03","2006-02-07",null,"2006-01-03"]
["XT_7475","Preliminary Design Review - Tunnel Mech/Vac","2006-01-31","2006-01-30",null,"2006-01-31","2006-01-30"]
["XT_7476","Write Safety/Ref Note - Tunnel Mech/Vac","2006-01-03","2006-03-01",null,"2006-01-03"]
["XT_7477","Select Vac Hardware Vendor - Tunnel Mech/Vac","2006-04-13","2006-07-07"]
["XT_7480","Select Vendor Stands - Tunnel Mech/Vac","2006-04-13","2006-07-07"]
["XT_7481","Pump Cross Design  - Tunnel Mech/Vac","2005-12-01","2005-12-14",null,"2005-12-01","2005-12-14"]
["XT_7482","Safety/Ref Note 1st Review - Tunnel Mech/Vac","2006-01-03","2006-01-31",null,"2006-01-03","2006-01-31"]
["XT_7486","Safety/Ref Note 2nd Review - Tunnel Mech/Vac","2006-01-03","2006-02-14",null,"2006-01-03"]
["XT_7488","Vacuum Valve Design - Tunnel Mech/Vac","2006-02-01","2006-03-01"]
["XT_7490","Safety/Ref Note SLAC Review - Tunnel Mech/Va","2006-02-15","2006-03-01"]
["XT_7493","Final Design Review - Tunnel Mech/Vac","2006-04-13","2006-04-12"]
["XT_7495","Beam Tube Design  - Tunnel Mech/V","2006-03-02","2006-04-12"]
["XT_7496","Prepare Procure Docs Stands - Tunnel Mech/Vac","2006-04-13","2006-09-28"]
["XT_7497","Prep Procure Docs Vac Hardware - Tunnel Mech/Vac","2006-04-13","2006-09-28"]
["XT_7498","Procurement Review Stands - Tunnel Mech/Vac","2006-09-29","2007-01-25"]
["XT_7499","Procure Review Vac Hardware - Tunnel Mech/Vac","2006-09-29","2007-01-25"]
["XT_7500","AWARD: Contract Stands - Tunnel Mech/Vac","2007-01-29","2007-01-29"]
["XT_7501","AWARD: Vac Hardware - Tunnel Mech/Vac","2007-01-26","2007-01-26"]
["XT_7502","Order & Receive Vac Hardware - Tunnel Mech/Vac","2007-01-29","2007-05-21"]
["XT_7503","Order & Receive Stands - Tunnel Mech/Vac","2007-01-29","2007-05-21"]
["XT_7504","Component Accept Test Vac Hardware-Tunnel Mech/V","2007-05-22","2007-05-29"]
["XT_7505","REQD:  Tunnel Beneficial Occup - Mech/Vac","2007-09-07","2007-09-06"]
["XT_7506","Prepare Install Plan - Tunnel Mech/Vac","2006-03-02","2006-05-24"]
["XT_7514","Pkg and Ship to SLAC - NEH Mech/Vac","2007-09-21","2007-10-04"]
["XT_7516","Assemble Subsystem - Tunnel Mech/Vac","2007-05-30","2007-07-25"]
["XT_7526","Test Subsystem at LLNL - Tunnel Mech/Vac","2007-07-26","2007-08-22"]
["XT_753","Controls Mgt - FY-06","2005-12-02","2006-09-29",null,"2005-12-02"]
["XT_7536","Pkg and Ship System to SLAC - Tunnel Mech/Vac","2007-08-23","2007-09-06"]
["XT_7741","COMP: Design - Comm Diagnostic Tank","2007-02-12","2007-02-09"]
["XT_7742","Prep Bid Pkg Tank - Comm Diagnostic Tank","2007-02-12","2007-02-16"]
["XT_7751","Bid Process Tank - Comm Diagnostic Tank","2007-02-20","2007-03-19"]
["XT_7759","AWARD: Contract Tank - Comm Diagnostic Tank","2007-03-20","2007-03-20"]
["XT_7767","Vendor Fab/Ship Tank - Comm Diagnostic Tank","2007-03-21","2007-06-13"]
["XT_7775","Assemble - Comm Diagnostic Tank","2007-06-14","2007-09-07"]
["XT_7776","RECV:  Tank - Comm Diagnostic Tank","2007-06-14","2007-06-13"]
["XT_7780","Design Studies-Internal Review 2-Gas Attenuator","2005-11-19","2005-11-18",null,"2005-11-19","2005-11-18"]
["XT_7793","REQD: Near Hall Beneficial Occup -Comm Diag Tank","2007-09-10","2007-09-10"]
["XT_78202","EPICs Controls Design I - FY-06","2005-12-02","2006-04-11",null,"2005-12-02"]
["XT_78203","Global - EPICS - FY-07","2006-10-02","2007-09-28"]
["XT_7822","Test Beam Line","2006-02-01","2006-03-29"]
["XT_7825","COMP:  Flipper Mirror","2007-08-28","2007-08-27"]
["XT_7880","Accept Test - Total Energy","2007-06-08","2007-06-14"]
["XT_789","Sensor Test & Prototype Optimization-Total Energ","2006-05-04","2006-10-23"]
["XT_7890","Management - Commission Coordinator - FY-06","2005-11-01","2006-09-29",null,"2005-11-01"]
["XT_8","COMP:  FEE Mechanical/Vacuum Installed & Commiss","2008-03-17","2008-03-14"]
["XT_800","Test Beam Line - Slit/Collimator","2007-10-24","2007-12-06"]
["XT_8002","Commission - Slit/Collimator A","2007-12-07","2008-02-20"]
["XT_801","COMP:  Slit/Collimator","2008-02-21","2008-02-20"]
["XT_810","Install - Slit/Collimator","2007-08-28","2007-10-23"]
["XT_8765","AWARD: Electronics & Cables - Motors","2006-10-30","2007-02-08"]
["XT_9620","Management & Oversight - FY-06","2005-10-01","2006-09-29",null,"2005-10-01"]
["XT_9621","Management - Safety - FY-06","2005-10-01","2006-09-29",null,"2005-10-01"]
["XT_9622","Management - Mech/Vac - FY-06","2005-10-01","2006-09-29",null,"2005-10-01"]
["XT_9623","Management & Oversight - FY-07","2006-10-02","2007-09-28"]
["XT_9624","Management - Safety - FY-07","2006-10-02","2007-09-28"]
["XT_9625","Management - Mech/Vac - FY-07","2006-10-02","2007-09-28"]
["XT_9626","Management & Oversight - FY-08","2007-10-01","2008-09-30"]
["XT_9627","Management - Safety - FY-08","2007-10-01","2008-09-30"]
["XT_9628","Management - Mech/Vac - FY-08","2007-10-01","2008-09-30"]
["XT_9629","Management & Oversight - FY-09","2008-10-01","2009-03-31"]
["XT_9630","Management - Safety - FY-09","2008-10-01","2009-03-31"]
["XT_9631","Management - Mech/Vac - FY-09","2008-10-01","2009-03-31"]
["XT_9640","Prepare Bid Pkg Electronics - Motors","2006-10-02","2006-10-13"]
["XT_9641","Bid Process Electronics - Motors","2006-10-16","2006-10-27"]
["XT_9642","Vendor Fab/Ship Electronics - Motors","2006-10-30","2007-02-08"]
["XT_9643","RECV: Electronics - Motors","2007-02-09","2007-02-08"]
["XT_97","Commission - Electron Dump Mech/Vac","2008-03-17","2008-04-11"]
["XT_9806","RECV: Vacuum System - Slit/Collimator Stand","2007-02-12","2007-02-09"]
["XT_9813","RECV: Vacuum System - Slit/Collimator Enclosure","2007-02-12","2007-02-09"]
["XT_9832","Design - Slit/Collimator","2006-06-02","2006-07-28"]
["XT_9850","Prepare Bid Pkg - EPICS Tools","2006-10-02","2006-10-06"]
["XT_9851","Bid Process - EPICS Tools","2006-10-09","2006-10-13"]
["XT_9852","Vendor Fab/Ship - EPICS Tools","2006-10-17","2006-11-13"]
["XT_9853","RECV: EPICS Tools","2006-11-14","2006-11-13"]
["XT_9860","Specification - Motors","2006-04-12","2006-06-07"]
["XT_9861","Design I - Motors","2006-06-08","2006-08-03"]
["XT_9862","COMP:  Design - Motors","2006-10-02","2006-09-29"]
["XT_9863","Prepare Bid Pkg Cables - Motors","2006-10-02","2006-10-13"]
["XT_9864","Bid Process Cables - Motors","2006-10-16","2006-10-27"]
["XT_9865","Vendor Fab/Ship Cables - Motors","2006-10-30","2007-02-08"]
["XT_9866","RECV: Cables - Motors","2007-02-09","2007-02-08"]
["XT_9867","Assemble FEE - Motors","2007-02-09","2007-03-09"]
["XT_9868","Assemble Near Hall -  Motors","2007-02-09","2007-03-09"]
["XT_9869","Assemble Far Hall - Motors","2007-02-09","2007-03-09"]
["XT_987","Physics Requirements Document - Total Energy","2006-04-27","2006-04-26"]
["XT_9870","Programming FEE - Motors","2007-03-12","2007-04-06"]
["XT_9871","Programming Near Hall - Motors","2007-03-12","2007-04-06"]
["XT_9872","Programming Far Hall - Motors","2007-03-12","2007-04-06"]
["XT_9873","REQD: Near Hall Beneficial Occup - Motors","2007-06-20","2007-06-19"]
["XT_9874","REQD: FEE Beneficial Occup - Motors","2007-08-28","2007-08-27"]
["XT_9875","REQD: Far Hall Beneficial Occup - Motors","2007-08-21","2007-08-20"]
["XT_991","Specification - FEE Diagnostic Tank","2006-10-24","2006-11-06"]
["XT_992","Design - FEE Diagnostic Tank","2006-11-07","2007-01-19"]
["XT_994","Assemble - FEE Diagnostic Tank","2007-08-28","2007-09-11"]
["XT_995","Install - FEE Diagnostic Tank","2007-09-19","2007-12-13"]
["XT_996","Test - FEE Diagnostic Tank","2007-12-14","2008-01-29"]
["XT_997","COMP:  FEE Diagnostic Tank","2008-02-13","2008-02-12"]
["XT_LOE","X-ray LOE Complete","2009-04-01","2009-03-31"]
["XT_M241","Conceptual Design Review - FEE Mech/Vac","2006-03-22","2006-03-21"]
["XT_M245","Final Design Review - FEE Mech/Vac","2006-08-14","2006-08-11"]
["XT_M280","Preliminary Design Review - FEE Mech/Vac","2006-05-19","2006-05-18"]
[]
[null,"Total of 10971 activities selected.",null,null,"Type key: ",null,"0=Task, 1=Independent, 2=Meeting, 3=SM, 4=FM, 5=Hammock, 6=WBS, 7=Topic "]
{"$rows_empty":96}
["XT_7412","Collimator 5 Design  - NEH Mech/Vac","2006-07-06","2006-07-07"]
["XT_7413","Vacuum Controls Defined - NEH Mech/Vac","2006-06-16","2006-06-22"]
["XT_7414","Pump Cross Design - NEH Mech/Vac","2006-06-09","2006-06-22"]
["XT_7415","Preliminary Design Review - NEH Mech/Vac","2006-07-31","2006-07-28"]
["XT_7416","Write Safety/Ref Note - NEH Mech/Vac","2006-07-31","2006-08-25"]
["XT_7417","Select Vac Hardware Vendor - NEH Mech/Vac","2006-07-31","2006-10-23"]
["XT_7420","Select Vendor Stands - NEH Mech/Vac","2006-07-31","2006-10-23"]
["XT_7422","Safety/Ref Note 1st Review - NEH Mech/Vac","2006-08-28","2006-09-18"]
["XT_7426","Safety/Ref Note 2nd Review - NEH Mech/Vac","2006-09-19","2006-09-27"]
["XT_7428","Vacuum Valve Design - NEH Mech/Vac","2006-06-23","2006-06-29"]
["XT_7430","Safety/Ref Note Division Review - NEH Mech/Vac","2006-09-28","2006-10-06"]
["XT_7433","Final Design Review - NEH Mech/Vac","2006-10-09","2006-10-06"]
["XT_7435","Beam Tube Spt  Design - NEH Mech/Vac","2006-06-30","2006-07-05"]
["XT_7436","Prepare Procure Docs Stands - NEH Mech/Vac","2007-01-02","2007-02-28"]
["XT_7437","Prep Procure Docs Vac Hardware - NEH Mech/Vac","2007-01-02","2007-02-28"]
["XT_7438","Procurement Review Stands - NEH Mech/Vac","2007-03-01","2007-03-07"]
["XT_7439","Procure Review Vac Hardware - NEH Mech/Vac","2007-03-01","2007-03-07"]
["XT_7440","AWARD: Contract Stands - NEH Mech/Vac","2007-03-08","2007-03-08"]
["XT_7441","AWARD: Vac Hardware - NEH Mech/Vac","2007-03-08","2007-03-08"]
["XT_7442","Order & Receive Vac Hardware - NEH Mech/Vac","2007-03-09","2007-07-30"]
["XT_7443","Order & Receive Stands - NEH Mech/Vac","2007-03-09","2007-07-30"]
["XT_7444","Component Accept Test Vac Hardware-NEH Mech/Vac","2007-07-31","2007-08-06"]
["XT_7445","REQD:  NEH Beneficial Occup - Mech/Vac","2007-07-12","2007-07-11"]
["XT_7446","Assemble subsystem - NEH Mech/Vac","2007-08-07","2007-10-02"]
["XT_7454","Prepare Install Plan - NEH Mech/Vac","2007-01-02","2007-04-25"]
["XT_7456","Test Subsystem at LLNL - NEH Mech/Vac","2007-10-03","2007-10-30"]
["XT_746","Commission - Indirect Imager","2007-08-28","2007-09-11"]
["XT_7462","Write ESD - Tunnel Mech/Vac","2006-03-02","2006-03-08"]
["XT_7464","Vacuum Analyses - Tunnel Mech/Vac","2006-01-18","2006-01-31"]
["XT_7466","Prelim Analysis of Stand - Tunnel Mech/Vac","2006-01-18","2006-01-24"]
["XT_7468","Vacuum Components Defined - Tunnel Mech/Vac","2006-02-01","2006-02-07"]
["XT_7469","Detail Analysis of Stand - Tunnel Mech/Vac","2006-01-25","2006-02-14"]
["XT_7473","Vacuum Controls Defined - Tunnel Mech/Vac","2006-02-08","2006-02-14"]
["XT_7475","Preliminary Design Review - Tunnel Mech/Vac","2006-01-03","2005-12-30"]
["XT_7476","Write Safety/Ref Note - Tunnel Mech/Vac","2006-02-15","2006-03-15"]
["XT_7477","Select Vac Hardware Vendor - Tunnel Mech/Vac","2006-04-20","2006-07-14"]
["XT_7480","Select Vendor Stands - Tunnel Mech/Vac","2006-04-20","2006-07-14"]
["XT_7481","Pump Cross Design  - Tunnel Mech/Vac","2006-01-18","2006-02-14"]
["XT_7482","Safety/Ref Note 1st Review - Tunnel Mech/Vac","2006-03-16","2006-03-22"]
["XT_7486","Safety/Ref Note 2nd Review - Tunnel Mech/Vac","2006-03-23","2006-03-29"]
["XT_7488","Vacuum Valve Design - Tunnel Mech/Vac","2006-02-15","2006-03-15"]
["XT_7490","Safety/Ref Note SLAC Review - Tunnel Mech/Va","2006-03-30","2006-04-05"]
["XT_7493","Final Design Review - Tunnel Mech/Vac","2006-04-20","2006-04-19"]
["XT_7495","Beam Tube Design  - Tunnel Mech/V","2006-03-16","2006-04-12"]
["XT_7496","Prepare Procure Docs Stands - Tunnel Mech/Vac","2006-04-20","2006-08-11"]
["XT_7497","Prep Procure Docs Vac Hardware - Tunnel Mech/Vac","2006-04-20","2006-08-11"]
["XT_7498","Procurement Review Stands - Tunnel Mech/Vac","2006-08-14","2006-12-06"]
["XT_7499","Procure Review Vac Hardware - Tunnel Mech/Vac","2006-08-14","2006-12-06"]
["XT_7500","AWARD: Contract Stands - Tunnel Mech/Vac","2006-12-08","2006-12-08"]
["XT_7501","AWARD: Vac Hardware - Tunnel Mech/Vac","2006-12-07","2006-12-07"]
["XT_7502","Order & Receive Vac Hardware - Tunnel Mech/Vac","2006-12-08","2007-04-04"]
["XT_7503","Order & Receive Stands - Tunnel Mech/Vac","2006-12-08","2007-04-17"]
["XT_7504","Component Accept Test Vac Hardware-Tunnel Mech/V","2007-04-05","2007-04-11"]
["XT_7505","REQD:  Tunnel Beneficial Occup - Mech/Vac","2007-08-06","2007-08-03"]
["XT_7506","Prepare Install Plan - Tunnel Mech/Vac","2006-04-06","2006-06-29"]
["XT_7512","Vendor Fab Vacuum System - Flipper Mirror","2007-06-14","2007-10-05"]
["XT_7514","Pkg and Ship to SLAC - NEH Mech/Vac","2007-10-31","2007-11-13"]
["XT_7516","Assemble Subsystem - Tunnel Mech/Vac","2007-04-18","2007-06-13"]
["XT_7526","Test Subsystem at LLNL - Tunnel Mech/Vac","2007-06-14","2007-07-12"]
["XT_753","Controls Mgt - FY-06","2005-12-02","2006-09-18",null,"2005-12-02"]
["XT_7536","Pkg and Ship System to SLAC - Tunnel Mech/Vac","2007-07-13","2007-07-26"]
["XT_754","Design II - Align Cameras Controls","2006-05-25","2006-08-18"]
["XT_77011","Specification - Controls-Direct Imager","2006-01-03","2006-01-31"]
["XT_77012","Specification - Controls-Align Cameras","2006-01-03","2006-01-31"]
["XT_77013","Design I - Controls-Align Cameras","2006-02-01","2006-04-26"]
["XT_77014","COMP:  Design - Controls-Align Cameras","2006-07-24","2006-07-21"]
["XT_77015","Prepare Bid Pkg - Controls-Align Cameras","2006-07-24","2006-08-18"]
["XT_77016","Bid Process - Controls-Align Cameras","2006-08-21","2006-10-16"]
["XT_77017","Vendor Fab/Ship - Controls-Align Cameras","2006-10-17","2007-01-26"]
["XT_77018","RECV:  Controls-Align Cameras","2007-01-29","2007-01-26"]
["XT_77019","Assemble FEE - Controls-Align Cameras","2007-01-29","2007-02-26"]
["XT_77020","Programming FEE - Controls-Align Cameras","2007-02-27","2007-04-23"]
["XT_77021","REQD: FEE Ben Occup - Controls-Align Cameras","2007-07-31","2007-07-30"]
["XT_7741","COMP: Design - Comm Diagnostic Tank","2006-09-01","2006-08-31"]
["XT_7742","Prep Bid Pkg Tank - Comm Diagnostic Tank","2006-09-01","2006-09-08"]
["XT_7751","Bid Process Tank - Comm Diagnostic Tank","2006-09-11","2006-10-06"]
["XT_7759","AWARD: Contract Tank - Comm Diagnostic Tank","2006-10-09","2006-10-09"]
["XT_7767","Vendor Fab/Ship Tank - Comm Diagnostic Tank","2006-10-10","2007-01-19"]
["XT_7775","Assemble - Comm Diagnostic Tank","2007-01-22","2007-04-16"]
["XT_7776","RECV:  Tank - Comm Diagnostic Tank","2007-01-22","2007-01-19"]
["XT_7780","Design Studies-Internal Review 2-Gas Attenuator","2006-02-23","2006-02-22"]
["XT_77801","AWARD: Contract Vacuum System - Flipper Mirror","2006-10-02","2006-10-06"]
["XT_77885","AWARD: Contract Precision Hardware - Flipper Mir","2007-06-14","2007-06-20"]
["XT_7789","RECV: Material -Spatial Shape & Centroid Measure","2007-05-02","2007-05-01"]
["XT_778956","Vendor Fab Jaws - Flipper Mirror","2007-06-14","2007-10-05"]
["XT_7793","REQD: Near Hall Beneficial Occup -Comm Diag Tank","2007-07-12","2007-07-12"]
["XT_780","Prepare Bid Pkg -Spatial Shape & Centroid Measur","2006-12-14","2007-01-04"]
["XT_781","Bid Process - Spatial Shape & Centroid Measure","2007-01-05","2007-02-02"]
["XT_7813","Vendor Fab Precision Hardware - Flipper Mirror","2007-06-14","2007-10-05"]
["XT_782","AWARD: Contract - Spatial Shape & Centroid Measu","2007-02-05","2007-02-05"]
["XT_78202","EPICs Controls Design I - FY-06","2005-12-02","2006-03-29",null,"2005-12-02"]
["XT_78203","Global - EPICS - FY-07","2006-09-19","2007-09-17"]
["XT_7821","Leak Check - Flipper Mirror","2008-03-04","2008-04-28"]
["XT_7822","Test Beam Line - Flipper Mirror","2008-04-29","2008-06-24"]
["XT_7824","Commission - Flipper Mirror","2008-06-25","2008-10-16"]
["XT_7825","COMP:  Flipper Mirror","2008-10-17","2008-10-16"]
["XT_783","Vendor Fab/Ship - Spatial Shape & Centroid Measu","2007-02-06","2007-05-01"]
["XT_786","Ship to SLAC-Spatial Shape & Centroid Measure","2007-08-24","2007-08-30"]
["XT_787","Unpack and Assemble at SLAC-Spatial Shape & Cent","2007-08-31","2007-09-14"]
["XT_788","AVAIL: Spatial Shape & Centroid Measure","2007-09-17","2007-09-14"]
["XT_7880","Accept Test - Total Energy","2007-05-10","2007-05-16"]
["XT_789","Sensor Test & Prototype Optimization-Total Energ","2006-04-06","2006-09-25"]
["XT_7890","Management - Commission Coordinator - FY-06","2005-11-01","2006-11-14",null,"2005-11-01"]
["XT_7955","Procure - Flipper Mirror","2006-04-06","2007-03-20"]
["XT_7956","AWARD: Contract Jaws - Flipper Mirror","2006-10-02","2006-10-06"]
["XT_7957","AWARD: Contract Tank - Flipper Mirror","2006-10-02","2006-10-06"]
["XT_798","REQD: Near Hall Benefic Occup-Spatial & Centroid","2007-09-17","2007-09-14"]
["XT_8","COMP:  FEE Mechanical/Vacuum Installed & Commiss","2008-04-24","2008-04-23"]
["XT_80","Vendor Fab Tank - Flipper Mirror","2007-06-14","2007-10-05"]
["XT_800","Test Beam Line - Slit/Collimator","2007-09-26","2007-11-06"]
["XT_8002","Commission - Slit/Collimator A","2007-11-07","2008-01-22"]
["XT_801","COMP:  Slit/Collimator","2008-01-23","2008-01-22"]
["XT_810","Install - Slit/Collimator","2007-07-31","2007-09-25"]
["XT_854","Design II - Ion Chamber Controls","2006-05-25","2006-08-18"]
["XT_8765","AWARD: Electronics & Cables - Motors","2006-10-17","2007-01-26"]
["XT_88","RECV: Flipper Mirror","2007-10-08","2007-10-05"]
["XT_899","Assemble -Spatial Shape & Centroid Measure","2007-05-02","2007-08-23"]
["XT_92","Assemble - Flipper Mirror","2007-10-08","2008-03-03"]
["XT_9601","Specification - Spectrometer Controls","2006-01-03","2006-03-01"]
["XT_9602","Design I - Spectrometer Controls","2006-03-02","2006-05-24"]
["XT_9603","COMP:  Design - Spectrometer Controls","2006-08-21","2006-08-18"]
["XT_9604","Prepare Bid Pkg - Spectrometer Controls","2006-08-21","2006-09-18"]
["XT_9605","Bid Process - Spectrometer Controls","2006-09-19","2006-11-13"]
["XT_9606","Vendor Fab/Ship - Spectrometer Controls","2006-11-14","2007-04-23"]
["XT_9607","RECV: Spectrometer Controls","2007-04-24","2007-04-23"]
["XT_9608","Assemble FEE - Spectrometer Controls","2007-04-24","2007-05-21"]
["XT_9611","Programming FEE - Spectrometer Controls","2007-05-22","2007-07-18"]
["XT_9620","Management & Oversight - FY-06","2005-10-01","2006-12-15",null,"2005-10-01"]
["XT_9621","Management - Safety - FY-06","2005-10-01","2006-12-15",null,"2005-10-01"]
["XT_9622","Management - Mech/Vac - FY-06","2005-10-01","2006-12-15",null,"2005-10-01"]
["XT_9623","Management & Oversight - FY-07","2007-01-02","2007-12-14"]
["XT_9624","Management - Safety - FY-07","2007-01-02","2007-12-14"]
["XT_9625","Management - Mech/Vac - FY-07","2007-01-02","2007-12-14"]
["XT_9626","Management & Oversight - FY-08","2008-01-02","2008-12-16"]
["XT_9627","Management - Safety - FY-08","2008-01-02","2008-12-16"]
["XT_9628","Management - Mech/Vac - FY-08","2008-01-02","2008-12-16"]
["XT_9629","Management & Oversight - FY-09","2008-12-17","2009-06-12"]
["XT_9630","Management - Safety - FY-09","2008-12-17","2009-06-12"]
["XT_9631","Management - Mech/Vac - FY-09","2008-12-17","2009-06-12"]
["XT_9640","Prepare Bid Pkg Electronics - Motors","2006-09-19","2006-10-02"]
["XT_9641","Bid Process Electronics - Motors","2006-10-03","2006-10-16"]
["XT_9642","Vendor Fab/Ship Electronics - Motors","2006-10-17","2007-01-26"]
["XT_9643","RECV: Electronics - Motors","2007-01-29","2007-01-26"]
["XT_9644","Prepare Bid Pkg Electronics - Vacuum Controls","2006-08-21","2006-08-25"]
["XT_9645","Bid Process Electronics - Vacuum Controls","2006-08-28","2006-09-25"]
["XT_9646","Vendor Fab/Ship Electronics - Vacuum Controls","2006-09-27","2006-10-24"]
["XT_9647","RECV: Electronics - Vacuum Controls","2006-10-25","2006-10-24"]
["XT_97","Commission - Electron Dump Mech/Vac","2008-04-24","2008-05-21"]
["XT_9806","RECV: Vacuum System - Slit/Collimator Stand","2007-01-12","2007-01-11"]
["XT_9813","RECV: Vacuum System - Slit/Collimator Enclosure","2007-01-12","2007-01-11"]
["XT_9832","Design - Slit/Collimator","2006-05-04","2006-06-29"]
["XT_9850","Prepare Bid Pkg - EPICS Tools","2006-09-19","2006-09-25"]
["XT_9851","Bid Process - EPICS Tools","2006-09-26","2006-10-02"]
["XT_9852","Vendor Fab/Ship - EPICS Tools","2006-10-04","2006-10-31"]
["XT_9853","RECV: EPICS Tools","2006-11-01","2006-10-31"]
["XT_9860","Specification - Motors","2006-03-30","2006-05-24"]
["XT_9861","Design I - Motors","2006-05-25","2006-07-21"]
["XT_9862","COMP:  Design - Motors","2006-09-19","2006-09-18"]
["XT_9863","Prepare Bid Pkg Cables - Motors","2006-09-19","2006-10-02"]
["XT_9864","Bid Process Cables - Motors","2006-10-03","2006-10-16"]
["XT_9865","Vendor Fab/Ship Cables - Motors","2006-10-17","2007-01-26"]
["XT_9866","RECV: Cables - Motors","2007-01-29","2007-01-26"]
["XT_9867","Assemble FEE - Motors","2007-01-29","2007-02-26"]
["XT_9868","Assemble Near Hall -  Motors","2007-01-29","2007-02-26"]
["XT_9869","Assemble Far Hall - Motors","2007-01-29","2007-02-26"]
["XT_987","Physics Requirements Document - Total Energy","2006-03-30","2006-03-29"]
["XT_9870","Programming FEE - Motors","2007-02-27","2007-03-26"]
["XT_9871","Programming Near Hall - Motors","2007-02-27","2007-03-26"]
["XT_9872","Programming Far Hall - Motors","2007-02-27","2007-03-26"]
["XT_9873","REQD: Near Hall Beneficial Occup - Motors","2007-07-12","2007-07-11"]
["XT_9874","REQD: FEE Beneficial Occup - Motors","2007-07-31","2007-07-30"]
["XT_9875","REQD: Far Hall Beneficial Occup - Motors","2007-08-21","2007-08-20"]
["XT_9876","Specification - Vacuum Controls Gauges","2006-01-03","2006-03-01"]
["XT_9877","Design I - Vacuum Controls","2006-03-02","2006-05-24"]
["XT_9878","COMP:  Design - Vacuum Controls","2006-08-21","2006-08-18"]
["XT_9879","Prepare Bid Pkg Cables - Vacuum Controls","2006-08-21","2006-08-25"]
["XT_9880","Bid Process Cables - Vacuum Controls","2006-08-28","2006-09-25"]
["XT_9881","Vendor Fab/Ship Cables - Vacuum Controls","2006-09-26","2006-10-23"]
["XT_9882","RECV: Cables - Vacuum Controls","2006-10-24","2006-10-23"]
["XT_9883","Assemble FEE - Vacuum Controls","2006-10-25","2006-11-21"]
["XT_9884","Assemble Near Hall - Vacuum Controls","2006-10-25","2006-11-21"]
["XT_9885","Assemble Far Hall - Vacuum Controls","2006-10-25","2006-11-21"]
["XT_9886","Programming FEE - Vacuum Controls","2006-11-22","2007-01-05"]
["XT_9887","Programming Near Hall - Vacuum Controls","2006-11-22","2007-01-05"]
["XT_9888","Programming Far Hall - Vacuum Controls","2006-11-22","2007-01-05"]
["XT_9889","REQD: Near Hall Beneficial Occup - Vacuum Contro","2007-07-12","2007-07-11"]
["XT_9890","REQD: FEE Beneficial Occup - Vacuum Controls","2007-07-31","2007-07-30"]
["XT_9891","REQD: Far Hall Beneficial Occup - Vacuum Control","2007-08-21","2007-08-20"]
["XT_991","Specification - FEE Diagnostic Tank","2006-10-17","2006-10-30"]
["XT_992","Design - FEE Diagnostic Tank","2006-10-31","2007-01-11"]
["XT_994","Assemble - FEE Diagnostic Tank","2007-07-31","2007-08-13"]
["XT_995","Install - FEE Diagnostic Tank","2007-08-21","2007-11-13"]
["XT_996","Test - FEE Diagnostic Tank","2007-11-14","2007-12-13"]
["XT_997","COMP:  FEE Diagnostic Tank","2008-01-15","2008-01-14"]
["XT_LOE","X-ray LOE Complete","2009-06-15","2009-06-12"]
["XT_M241","Conceptual Design Review - FEE Mech/Vac","2006-02-22","2006-02-21"]
["XT_M245","Final Design Review - FEE Mech/Vac","2006-07-27","2006-07-26"]
["XT_M280","Preliminary Design Review - FEE Mech/Vac","2006-05-03","2006-05-02"]
[]
[null,"Total of 11267 activities selected.",null,null,"Type key: ",null,"0=Task, 1=Independent, 2=Meeting, 3=SM, 4=FM, 5=Hammock, 6=WBS, 7=Topic "]
{"$rows_empty":101}
["XT_780","Prepare Bid Pkg -Spatial Shape & Centroid Measur","2006-12-14","2007-01-04"]
["XT_781","Bid Process - Spatial Shape & Centroid Measure","2007-01-05","2007-02-02"]
["XT_7813","Vendor Fab Precision Hardware - Flipper Mirror","2008-05-15","2008-06-12"]
["XT_7814","RECV Jaws - Flipper Mirror","2008-06-20","2008-06-19"]
["XT_7816","RECV Tank - Flipper Mirror","2008-06-20","2008-06-19"]
["XT_7817","Assemble Tank - Flipper Mirror","2008-06-20","2009-04-14"]
["XT_7818","Assemble Electronics - Flipper Mirror","2008-05-15","2009-03-10"]
["XT_7819","Assemble Jaws - Flipper Mirror","2008-06-20","2009-04-14"]
["XT_782","AWARD: Contract - Spatial Shape & Centroid Measu","2007-02-05","2007-02-05"]
["XT_7820","Install - Flipper Mirror","2009-04-15","2009-06-09"]
["XT_78202","Global - EPICS","2005-10-01","2006-10-18",null,"2005-10-01"]
["XT_7821","Leak Check - Flipper Mirror","2009-06-10","2009-07-08"]
["XT_7822","Test Beam Line - Flipper Mirror","2009-07-09","2009-08-05"]
["XT_7824","Commission - Flipper Mirror","2009-08-06","2009-11-25"]
["XT_7825","COMP:  Flipper Mirror","2009-11-26","2009-11-25"]
["XT_783","Vendor Fab/Ship - Spatial Shape & Centroid Measu","2007-02-06","2007-05-01"]
["XT_786","Ship to SLAC-Spatial Shape & Centroid Measure","2007-08-24","2007-08-30"]
["XT_787","Unpack and Assemble at SLAC-Spatial Shape & Cent","2007-08-31","2007-09-14"]
["XT_788","AVAIL: Spatial Shape & Centroid Measure","2007-09-17","2007-09-14"]
["XT_7880","Component Accept Test -Total Energy","2008-03-20","2008-03-26"]
["XT_789","Bid Process Tank - Flipper Mirror","2008-04-17","2008-05-14"]
["XT_7890","Management - Commission Coordinator - FY-06","2005-11-01","2006-11-14",null,"2005-11-01"]
["XT_7924","Bid Process Electronics - Flipper Mirror","2008-04-17","2008-05-14"]
["XT_7955","Bid Process Precision Hardware - Flipper Mirror","2008-04-17","2008-05-14"]
["XT_7956","AWARD: Contract Jaws - Flipper Mirror","2008-05-15","2008-05-21"]
["XT_7957","AWARD: Contract Tank - Flipper Mirror","2008-05-15","2008-05-21"]
["XT_798","REQD: Near Hall Benefic Occup-Spatial & Centroid","2007-09-17","2007-09-14"]
["XT_8","COMP:  FEE Mechanical/Vacuum Installed & Commiss","2008-05-01","2008-04-30"]
["XT_80","Vendor Fab Tank - Flipper Mirror","2008-05-22","2008-06-19"]
["XT_800","Test Beam Line - Slit/Collimator","2007-12-12","2008-02-08"]
["XT_8002","Commission - Slit/Collimator A","2008-02-11","2008-04-07"]
["XT_801","COMP:  Slit/Collimator","2008-04-08","2008-04-07"]
["XT_810","Install - Slit/Collimator","2007-10-15","2007-12-11"]
["XT_86","RECV Electronics - Flipper Mirror","2008-05-15","2008-05-14"]
["XT_87","RECV Vacuum System - Flipper Mirror","2008-06-20","2008-06-19"]
["XT_8765","AWARD: Electronics & Cables - Motors","2006-10-17","2007-01-26"]
["XT_88","RECV Precision Motion Hardware - Flipper Mirror","2008-06-13","2008-06-12"]
["XT_899","Assemble -Spatial Shape & Centroid Measure","2007-05-02","2007-08-23"]
["XT_90","Assemble Vacuum System - Flipper Mirror","2008-06-20","2009-04-14"]
["XT_92","Assemble Precision Hardware - Flipper Mirror","2008-06-13","2009-04-07"]
["XT_9601","Specification - Spectrometer Controls","2006-01-03","2006-03-01"]
["XT_9602","Design - Spectrometer Controls","2006-03-02","2006-07-21"]
["XT_9603","COMP:  Design - Spectrometer Controls","2006-07-24","2006-07-21"]
["XT_9604","Prepare Bid Pkg - Spectrometer Controls","2006-07-24","2006-08-18"]
["XT_9605","Bid Process - Spectrometer Controls","2006-08-21","2006-10-16"]
["XT_9606","Vendor Fab/Ship - Spectrometer Controls","2006-10-17","2007-03-26"]
["XT_9607","RECV: Spectrometer Controls","2007-03-27","2007-03-26"]
["XT_9608","Assemble FEE - Spectrometer Controls","2007-03-27","2007-04-23"]
["XT_9611","Programming FEE - Spectrometer Controls","2007-04-24","2007-06-19"]
["XT_9615","REQD: FEE Ben Occup - Spectrometer Controls","2007-07-10","2007-07-09"]
["XT_9620","Management & Oversight - FY-06","2005-10-01","2006-12-15",null,"2005-10-01"]
["XT_9621","Management - Safety - FY-06","2005-10-01","2006-12-15",null,"2005-10-01"]
["XT_9622","Management - Mech/Vac - FY-06","2005-10-01","2006-12-15",null,"2005-10-01"]
["XT_9623","Management & Oversight - FY-07","2007-01-02","2007-12-14"]
["XT_9624","Management - Safety - FY-07","2007-01-02","2007-12-14"]
["XT_9625","Management - Mech/Vac - FY-07","2007-01-02","2007-12-14"]
["XT_9626","Management & Oversight - FY-08","2008-01-02","2008-12-16"]
["XT_9627","Management - Safety - FY-08","2008-01-02","2008-12-16"]
["XT_9628","Management - Mech/Vac - FY-08","2008-01-02","2008-12-16"]
["XT_9629","Management & Oversight - FY-09","2008-12-17","2009-06-12"]
["XT_9630","Management - Safety - FY-09","2008-12-17","2009-06-12"]
["XT_9631","Management - Mech/Vac - FY-09","2008-12-17","2009-06-12"]
["XT_9640","Prepare Bid Pkg Electronics - Motors","2006-07-24","2006-08-18"]
["XT_9641","Bid Process Electronics - Motors","2006-08-21","2006-10-16"]
["XT_9642","Vendor Fab/Ship Electronics - Motors","2006-10-17","2007-01-26"]
["XT_9643","RECV: Electronics - Motors","2007-01-29","2007-01-26"]
["XT_9644","Prepare Bid Pkg Electronics - Vacuum Controls","2006-05-25","2006-06-22"]
["XT_9645","Bid Process Electronics - Vacuum Controls","2006-06-23","2006-08-18"]
["XT_9646","Vendor Fab/Ship Electronics - Vacuum Controls","2006-08-22","2006-12-14"]
["XT_9647","RECV: Electronics - Vacuum Controls","2006-12-15","2006-12-14"]
["XT_97","Commission - Electron Dump Mech/Vac","2008-05-01","2008-05-29"]
["XT_9800","Design - Back Check - Slit/Collimator Stand","2006-11-08","2006-11-16"]
["XT_9801","Design - Check - Slit/Collimator Stand","2006-10-13","2006-11-07"]
["XT_9802","Design - Detail - Slit/Collimator Stand","2006-08-07","2006-10-12"]
["XT_9803","Design - Primary - Slit/Collimator Stand","2006-01-18","2006-08-04"]
["XT_9804","Detail Analysis Mechanical-Slit Stand","2006-02-28","2006-05-15"]
["XT_9805","Prep Bid Pk Vac System-Slit/Collimator Stand","2007-03-07","2007-03-13"]
["XT_9806","RECV: Vacuum System - Slit/Collimator Stand","2007-07-06","2007-07-05"]
["XT_9807","Design - Back Check - Slit/Collimator Enclosure","2006-11-08","2006-11-16"]
["XT_9808","Design - Check - Slit/Collimator Enclosure","2006-10-13","2006-11-07"]
["XT_9809","Design - Detail - Slit/Collimator Enclosure","2006-08-07","2006-10-12"]
["XT_9810","Design - Primary - Slit/Collimator Enclosure","2006-01-18","2006-08-04"]
["XT_9811","Detail Analysis Mechanical-Slit Enclosure","2006-02-28","2006-05-15"]
["XT_9812","Prep Bid Pk Vac System-Slit/Collimator Enclosure","2007-03-07","2007-03-13"]
["XT_9813","RECV: Vacuum System - Slit/Collimator Enclosure","2007-07-06","2007-07-05"]
["XT_9815","Prelim Analysis Mechanic-Slit Enclosure","2006-02-08","2006-02-27"]
["XT_9817","Prelim Analysis Mechanic-Slit Stand","2006-02-08","2006-02-27"]
["XT_9830","Prepare Bid Pkg - IOCs - 1st set","2006-10-03","2006-10-30"]
["XT_9831","Bid Process - IOCs - 1st set","2006-10-31","2007-01-11"]
["XT_9832","Vendor Fab/Ship - IOCs - 1st set","2007-01-12","2007-06-05"]
["XT_9833","Prepare Bid Pkg - PLCs - 1st set","2006-10-03","2006-10-30"]
["XT_9834","Bid Process - PLCs - 1st set","2006-10-31","2007-01-11"]
["XT_9835","Vendor Fab/Ship - PLCs - 1st set","2007-01-12","2007-06-05"]
["XT_9850","Prepare Bid Pkg - EPICS Tools","2006-05-25","2006-06-22"]
["XT_9851","Bid Process - EPICS Tools","2006-06-23","2006-07-21"]
["XT_9852","Vendor Fab/Ship - EPICS Tools","2006-10-19","2007-01-30"]
["XT_9853","RECV: EPICS Tools","2007-01-31","2007-01-30"]
["XT_9856","RECV:  PLCs - 1st set","2007-06-06","2007-06-05"]
["XT_9860","Specification - Motors","2006-01-03","2006-03-01"]
["XT_9861","Design - Motors","2006-03-02","2006-07-21"]
["XT_9862","COMP:  Design - Motors","2006-07-24","2006-07-21"]
["XT_9863","Prepare Bid Pkg Cables - Motors","2006-07-24","2006-08-18"]
["XT_9864","Bid Process Cables - Motors","2006-08-21","2006-10-16"]
["XT_9865","Vendor Fab/Ship Cables - Motors","2006-10-17","2007-01-26"]
["XT_9866","RECV: Cables - Motors","2007-01-29","2007-01-26"]
["XT_9867","Assemble FEE - Motors","2007-01-29","2007-02-26"]
["XT_9868","Assemble Near Hall -  Motors","2007-01-29","2007-02-26"]
["XT_9869","Assemble Far Hall - Motors","2007-01-29","2007-02-26"]
["XT_9870","Programming FEE - Motors","2007-02-27","2007-07-18"]
["XT_9871","Programming Near Hall - Motors","2007-02-27","2007-07-18"]
["XT_9872","Programming Far Hall - Motors","2007-02-27","2007-07-18"]
["XT_9873","REQD: Near Hall Beneficial Occup - Motors","2007-07-19","2007-07-18"]
["XT_9874","REQD: FEE Beneficial Occup - Motors","2007-07-19","2007-07-18"]
["XT_9875","REQD: Far Hall Beneficial Occup - Motors","2007-07-26","2007-07-25"]
["XT_9876","Specification - Vacuum Controls Gauges","2006-01-03","2006-03-01"]
["XT_9877","Design - Vacuum Controls","2006-03-02","2006-05-24"]
["XT_9878","COMP:  Design - Vacuum Controls","2006-05-25","2006-05-24"]
["XT_9879","Prepare Bid Pkg Cables - Vacuum Controls","2006-05-25","2006-06-22"]
["XT_9880","Bid Process Cables - Vacuum Controls","2006-06-23","2006-08-18"]
["XT_9881","Vendor Fab/Ship Cables - Vacuum Controls","2006-08-21","2006-12-13"]
["XT_9882","RECV: Cables - Vacuum Controls","2006-12-14","2006-12-13"]
["XT_9883","Assemble FEE - Vacuum Controls","2006-12-15","2007-01-29"]
["XT_9884","Assemble Near Hall - Vacuum Controls","2006-12-15","2007-01-29"]
["XT_9885","Assemble Far Hall - Vacuum Controls","2006-12-15","2007-01-29"]
["XT_9886","Programming FEE - Vacuum Controls","2007-01-30","2007-06-20"]
["XT_9887","Programming Near Hall - Vacuum Controls","2007-01-30","2007-06-20"]
["XT_9888","Programming Far Hall - Vacuum Controls","2007-01-30","2007-06-20"]
["XT_9889","REQD: Near Hall Beneficial Occup - Vacuum Contro","2007-06-21","2007-06-20"]
["XT_9890","REQD: FEE Beneficial Occup - Vacuum Controls","2007-07-10","2007-07-09"]
["XT_9891","REQD: Far Hall Beneficial Occup - Vacuum Control","2007-07-26","2007-07-25"]
["XT_991","Specification - FEE Diagnostic Tank","2006-03-13","2006-05-05"]
["XT_992","Design - FEE Diagnostic Tank","2006-05-08","2006-11-01"]
["XT_994","Assemble - FEE Diagnostic Tank","2007-07-10","2007-11-29"]
["XT_995","Install - FEE Diagnostic Tank","2007-11-30","2008-03-12"]
["XT_996","Test - FEE Diagnostic Tank","2008-03-13","2008-04-09"]
["XT_997","COMP:  FEE Diagnostic Tank","2008-04-24","2008-04-23"]
["XT_LOE","X-ray LOE Complete","2009-06-15","2009-06-12"]
[]
[null,"Total of 11507 activities selected.",null,null,"Type key: ",null,"0=Task, 1=Independent, 2=Meeting, 3=SM, 4=FM, 5=Hammock, 6=WBS, 7=Topic "]
{"$rows_empty":94}
["XT_782","AWARD: Contract - Spatial Shape & Centroid Measu","2006-12-05","2006-12-05"]
["XT_7820","Install - Flipper Mirror","2009-04-15","2009-06-09"]
["XT_78202","Global - EPICS","2005-10-01","2006-10-02",null,"2005-10-01"]
["XT_7821","Leak Check - Flipper Mirror","2009-06-10","2009-07-08"]
["XT_7822","Test Beam Line - Flipper Mirror","2009-07-09","2009-08-05"]
["XT_7824","Commission - Flipper Mirror","2009-08-06","2009-11-25"]
["XT_7825","COMP:  Flipper Mirror","2009-11-26","2009-11-25"]
["XT_783","Vendor Fab/Ship - Spatial Shape & Centroid Measu","2006-12-06","2007-03-16"]
["XT_786","Ship to SLAC-Spatial Shape & Centroid Measure","2007-07-11","2007-07-17"]
["XT_787","Unpack and Assemble at SLAC-Spatial Shape & Cent","2007-07-18","2007-07-31"]
["XT_788","AVAIL: Spatial Shape & Centroid Measure","2007-08-01","2007-07-31"]
["XT_7880","Component Accept Test -Total Energy","2008-01-08","2008-01-14"]
["XT_789","Bid Process Tank - Flipper Mirror","2008-04-17","2008-05-14"]
["XT_7890","Management - Commission Coordinator - FY-06","2005-11-01","2006-09-29"]
["XT_7924","Bid Process Electronics - Flipper Mirror","2008-04-17","2008-05-14"]
["XT_7955","Bid Process Precision Hardware - Flipper Mirror","2008-04-17","2008-05-14"]
["XT_7956","AWARD: Contract Jaws - Flipper Mirror","2008-05-15","2008-05-21"]
["XT_7957","AWARD: Contract Tank - Flipper Mirror","2008-05-15","2008-05-21"]
["XT_798","REQD: Near Hall Benefic Occup-Spatial & Centroid","2007-08-01","2007-07-31"]
["XT_8","COMP:  FEE Mechanical/Vacuum Installed & Commiss","2008-03-18","2008-03-17"]
["XT_80","Vendor Fab Tank - Flipper Mirror","2008-05-22","2008-06-19"]
["XT_800","Test Beam Line - Slit/Collimator","2007-09-20","2007-10-31"]
["XT_8002","Commission - Slit/Collimator A","2007-11-01","2008-01-15"]
["XT_801","COMP:  Slit/Collimator","2008-01-16","2008-01-15"]
["XT_810","Install - Slit/Collimator","2007-07-25","2007-09-19"]
["XT_86","RECV Electronics - Flipper Mirror","2008-05-15","2008-05-14"]
["XT_87","RECV Vacuum System - Flipper Mirror","2008-06-20","2008-06-19"]
["XT_8765","AWARD: Electronics & Cables - Motors","2006-08-31","2006-11-27"]
["XT_88","RECV Precision Motion Hardware - Flipper Mirror","2008-06-13","2008-06-12"]
["XT_899","Assemble -Spatial Shape & Centroid Measure","2007-03-19","2007-07-10"]
["XT_90","Assemble Vacuum System - Flipper Mirror","2008-06-20","2009-04-14"]
["XT_92","Assemble Precision Hardware - Flipper Mirror","2008-06-13","2009-04-07"]
["XT_9601","Specification - Spectrometer Controls","2005-11-01","2006-01-12"]
["XT_9602","Design - Spectrometer Controls","2006-01-13","2006-06-06"]
["XT_9603","COMP:  Design - Spectrometer Controls","2006-06-07","2006-06-06"]
["XT_9604","Prepare Bid Pkg - Spectrometer Controls","2006-06-07","2006-07-05"]
["XT_9605","Bid Process - Spectrometer Controls","2006-07-06","2006-08-30"]
["XT_9606","Vendor Fab/Ship - Spectrometer Controls","2006-08-31","2007-02-07"]
["XT_9607","RECV: Spectrometer Controls","2007-02-08","2007-02-07"]
["XT_9608","Assemble FEE - Spectrometer Controls","2007-02-08","2007-03-08"]
["XT_9611","Programming FEE - Spectrometer Controls","2007-03-09","2007-05-03"]
["XT_9615","REQD: FEE Ben Occup - Spectrometer Controls","2007-07-10","2007-07-09"]
["XT_9620","Management & Oversight - FY-06","2005-10-01","2006-10-30",null,"2005-10-01"]
["XT_9621","Management - Safety - FY-06","2005-10-01","2006-10-30",null,"2005-10-01"]
["XT_9622","Management - Mech/Vac - FY-06","2005-10-01","2006-10-30",null,"2005-10-01"]
["XT_9623","Management & Oversight - FY-07","2006-10-31","2007-10-29"]
["XT_9624","Management - Safety - FY-07","2006-10-31","2007-10-29"]
["XT_9625","Management - Mech/Vac - FY-07","2006-10-31","2007-10-29"]
["XT_9626","Management & Oversight - FY-08","2007-10-30","2008-10-29"]
["XT_9627","Management - Safety - FY-08","2007-10-30","2008-10-29"]
["XT_9628","Management - Mech/Vac - FY-08","2007-10-30","2008-10-29"]
["XT_9629","Management & Oversight - FY-09","2008-10-30","2009-04-29"]
["XT_9630","Management - Safety - FY-09","2008-10-30","2009-04-29"]
["XT_9631","Management - Mech/Vac - FY-09","2008-10-30","2009-04-29"]
["XT_9640","Prepare Bid Pkg Electronics - Motors","2006-06-07","2006-07-05"]
["XT_9641","Bid Process Electronics - Motors","2006-07-06","2006-08-30"]
["XT_9642","Vendor Fab/Ship Electronics - Motors","2006-08-31","2006-11-27"]
["XT_9643","RECV: Electronics - Motors","2006-11-28","2006-11-27"]
["XT_9644","Prepare Bid Pkg Electronics - Vacuum Controls","2006-04-11","2006-05-08"]
["XT_9645","Bid Process Electronics - Vacuum Controls","2006-05-09","2006-07-05"]
["XT_9646","Vendor Fab/Ship Electronics - Vacuum Controls","2006-07-07","2006-10-27"]
["XT_9647","RECV: Electronics - Vacuum Controls","2006-10-30","2006-10-27"]
["XT_97","Commission - Electron Dump Mech/Vac","2008-03-18","2008-04-14"]
["XT_9800","Design - Back Check - Slit/Collimator Stand","2006-09-29","2006-10-09"]
["XT_9801","Design - Check - Slit/Collimator Stand","2006-09-05","2006-09-28"]
["XT_9802","Design - Detail - Slit/Collimator Stand","2006-06-27","2006-09-01"]
["XT_9803","Design - Primary - Slit/Collimator Stand","2005-11-21","2006-06-26"]
["XT_9804","Detail Analysis Mechanical-Slit Stand","2006-01-18","2006-04-05"]
["XT_9805","Prep Bid Pk Vac System-Slit/Collimator Stand","2006-11-29","2006-12-05"]
["XT_9806","RECV: Vacuum System - Slit/Collimator Stand","2007-04-16","2007-04-13"]
["XT_9807","Design - Back Check - Slit/Collimator Enclosure","2006-09-29","2006-10-09"]
["XT_9808","Design - Check - Slit/Collimator Enclosure","2006-09-05","2006-09-28"]
["XT_9809","Design - Detail - Slit/Collimator Enclosure","2006-06-27","2006-09-01"]
["XT_9810","Design - Primary - Slit/Collimator Enclosure","2005-11-21","2006-06-26"]
["XT_9811","Detail Analysis Mechanical-Slit Enclosure","2006-01-18","2006-04-05"]
["XT_9812","Prep Bid Pk Vac System-Slit/Collimator Enclosure","2006-11-29","2006-12-05"]
["XT_9813","RECV: Vacuum System - Slit/Collimator Enclosure","2007-04-16","2007-04-13"]
["XT_9815","Prelim Analysis Mechanic-Slit Enclosure","2005-12-14","2006-01-17"]
["XT_9817","Prelim Analysis Mechanic-Slit Stand","2005-12-14","2006-01-17"]
["XT_9830","Prepare Bid Pkg - IOCs - 1st set","2006-10-03","2006-10-30"]
["XT_9831","Bid Process - IOCs - 1st set","2006-10-31","2007-01-11"]
["XT_9832","Vendor Fab/Ship - IOCs - 1st set","2007-01-12","2007-06-05"]
["XT_9833","Prepare Bid Pkg - PLCs - 1st set","2006-10-03","2006-10-30"]
["XT_9834","Bid Process - PLCs - 1st set","2006-10-31","2007-01-11"]
["XT_9835","Vendor Fab/Ship - PLCs - 1st set","2007-01-12","2007-06-05"]
["XT_9850","Prepare Bid Pkg - EPICS Tools","2006-04-11","2006-05-08"]
["XT_9851","Bid Process - EPICS Tools","2006-05-09","2006-06-06"]
["XT_9852","Vendor Fab/Ship - EPICS Tools","2006-10-03","2007-01-11"]
["XT_9853","RECV: EPICS Tools","2007-01-12","2007-01-11"]
["XT_9856","RECV:  PLCs - 1st set","2007-06-06","2007-06-05"]
["XT_9860","Specification - Motors","2005-11-01","2006-01-12"]
["XT_9861","Design - Motors","2006-01-13","2006-06-06"]
["XT_9862","COMP:  Design - Motors","2006-06-07","2006-06-06"]
["XT_9863","Prepare Bid Pkg Cables - Motors","2006-06-07","2006-07-05"]
["XT_9864","Bid Process Cables - Motors","2006-07-06","2006-08-30"]
["XT_9865","Vendor Fab/Ship Cables - Motors","2006-08-31","2006-11-27"]
["XT_9866","RECV: Cables - Motors","2006-11-28","2006-11-27"]
["XT_9867","Assemble FEE - Motors","2006-11-28","2007-01-09"]
["XT_9868","Assemble Near Hall -  Motors","2006-11-28","2007-01-09"]
["XT_9869","Assemble Far Hall - Motors","2006-11-28","2007-01-09"]
["XT_9870","Programming FEE - Motors","2007-01-10","2007-06-01"]
["XT_9871","Programming Near Hall - Motors","2007-01-10","2007-06-01"]
["XT_9872","Programming Far Hall - Motors","2007-01-10","2007-06-01"]
["XT_9873","REQD: Near Hall Beneficial Occup - Motors","2007-06-04","2007-06-01"]
["XT_9874","REQD: FEE Beneficial Occup - Motors","2007-07-10","2007-07-09"]
["XT_9875","REQD: Far Hall Beneficial Occup - Motors","2007-07-26","2007-07-25"]
["XT_9876","Specification - Vacuum Controls Gauges","2005-11-01","2006-01-12"]
["XT_9877","Design - Vacuum Controls","2006-01-13","2006-04-10"]
["XT_9878","COMP:  Design - Vacuum Controls","2006-04-11","2006-04-10"]
["XT_9879","Prepare Bid Pkg Cables - Vacuum Controls","2006-04-11","2006-05-08"]
["XT_9880","Bid Process Cables - Vacuum Controls","2006-05-09","2006-07-05"]
["XT_9881","Vendor Fab/Ship Cables - Vacuum Controls","2006-07-06","2006-10-26"]
["XT_9882","RECV: Cables - Vacuum Controls","2006-10-27","2006-10-26"]
["XT_9883","Assemble FEE - Vacuum Controls","2006-10-30","2006-11-28"]
["XT_9884","Assemble Near Hall - Vacuum Controls","2006-10-30","2006-11-28"]
["XT_9885","Assemble Far Hall - Vacuum Controls","2006-10-30","2006-11-28"]
["XT_9886","Programming FEE - Vacuum Controls","2006-11-29","2007-05-04"]
["XT_9887","Programming Near Hall - Vacuum Controls","2006-11-29","2007-05-04"]
["XT_9888","Programming Far Hall - Vacuum Controls","2006-11-29","2007-05-04"]
["XT_9889","REQD: Near Hall Beneficial Occup - Vacuum Contro","2007-05-07","2007-05-04"]
["XT_9890","REQD: FEE Beneficial Occup - Vacuum Controls","2007-07-10","2007-07-09"]
["XT_9891","REQD: Far Hall Beneficial Occup - Vacuum Control","2007-07-26","2007-07-25"]
["XT_991","Specification - FEE Diagnostic Tank","2006-03-13","2006-05-05"]
["XT_992","Design - FEE Diagnostic Tank","2006-05-08","2006-11-01"]
["XT_994","Assemble - FEE Diagnostic Tank","2007-07-10","2007-11-29"]
["XT_995","Install - FEE Diagnostic Tank","2007-11-30","2008-03-12"]
["XT_996","Test - FEE Diagnostic Tank","2008-03-13","2008-04-09"]
["XT_997","COMP:  FEE Diagnostic Tank","2008-04-24","2008-04-23"]
["XT_LOE","X-ray LOE Complete","2009-04-30","2009-04-29"]
[]
[null,"Total of 11732 activities selected.",null,null,"Type key: ",null,"0=Task, 1=Independent, 2=Meeting, 3=SM, 4=FM, 5=Hammock, 6=WBS, 7=Topic "]
{"$rows_empty":94}
["XT_8002","Commission - Slit/Collimator A","2007-10-23","2008-01-04"]
["XT_801","COMP:  Slit/Collimator A","2008-01-07","2008-01-04"]
["XT_805","Install Ion Gauges - NH Mech/Vac - H3","2007-04-30","2007-05-04"]
["XT_81","Assemble - Far Hall Mech/Vac - H3","2008-02-01","2008-02-07"]
["XT_810","Install - Slit/Collimator A","2007-07-16","2007-09-10"]
["XT_82","Install Ion Pumps - Far Hall Mech/Vac - H3","2008-02-08","2008-02-14"]
["XT_84","Commission - Far Hall Mech/Vac - H3","2008-04-21","2008-05-02"]
["XT_85","COMP:  Far Hall Mech/Vac - H3  Installed & Commi","2008-05-05","2008-05-02"]
["XT_86","RECV Electronics - Flipper Mirror","2006-08-09","2006-08-08"]
["XT_87","RECV Vacuum System - Flipper Mirror","2006-11-06","2006-11-03"]
["XT_88","RECV Precision Motion Hardware - Flipper Mirror","2006-11-06","2006-11-03"]
["XT_8842","Prep Bid Pkg Grating - Spectral Measurement","2006-10-02","2006-10-06"]
["XT_8845","Prep Bid Pkg Low Energy - Spectral Measurement","2006-10-02","2006-10-06"]
["XT_8846","Prep Bid Rails & Stages - Spectral Measurement","2006-10-02","2006-10-06"]
["XT_8852","Bid Process Grating - Spectral Measurement","2006-10-09","2006-11-03"]
["XT_8855","Prep Bid Pkg High Energy - Spectral Measurement","2006-10-02","2006-10-06"]
["XT_8856","Bid Process Rails & Stages -Spectral Measurement","2006-10-09","2006-11-03"]
["XT_8862","AWARD: Grating - Spectral Measurement","2006-11-06","2006-11-06"]
["XT_8865","Bid Process Low Energy - Spectral Measurement","2006-10-09","2006-11-03"]
["XT_8866","AWARD: Rails & Stages - Spectral Measurement","2006-11-06","2006-11-06"]
["XT_8872","Vendor Fab Grating - Spectral Measurement","2006-11-07","2007-01-19"]
["XT_8875","AWARD: Low Energy - Spectral Measurement","2006-11-06","2006-11-06"]
["XT_8876","Vendor Fab Rails & Stages - Spectral Measurement","2006-11-07","2007-01-19"]
["XT_8882","RECV: Grating - Spectral Measurement","2007-01-22","2007-01-19"]
["XT_8885","RECV:  Low Energy - Spectral Measurement","2007-01-22","2007-01-19"]
["XT_8886","RECV: Rails & Stages - Spectral Measurement","2007-01-22","2007-01-19"]
["XT_8895","Bid Process - Spectral Measurement","2006-10-09","2006-11-03"]
["XT_89","Procure Vacuum Hardware - Far Hall Mech/Vac","2007-10-11","2007-12-07"]
["XT_8905","AWARD: Contract - Spectral Measurement","2006-11-06","2006-11-06"]
["XT_8915","Vendor Fab High Energy - Spectral Measurement","2006-11-07","2007-02-16"]
["XT_8925","RECV: High Energy - Spectral Measurement","2007-02-20","2007-02-16"]
["XT_8935","Vendor Fab Low Energy - Spectral Measurement","2006-11-07","2007-01-19"]
["XT_899","Assemble -Spatial Shape & Centroid Measure","2007-10-11","2008-02-21"]
["XT_9","Specification - Electron Dump Mech/Vac","2007-10-01","2007-10-12"]
["XT_90","Assemble Vacuum System - Flipper Mirror","2006-11-06","2007-09-05"]
["XT_91","AVAIL: Far Hall Mech/Vac Ready to Install SLAC","2008-02-08","2008-02-07"]
["XT_92","Assemble Precision Hardware - Flipper Mirror","2006-11-06","2007-09-05"]
["XT_94","Assemble Pipe - Electron Dump Mech/Vac","2008-03-24","2008-03-28"]
["XT_95","Install Vacuum Pipe - Electron Dump Mech/Vac","2008-03-31","2008-04-04"]
["XT_96","Test Pipe - Electron Dump Mech/Vac","2008-04-07","2008-04-18"]
["XT_97","Commission - Electron Dump Mech/Vac","2008-04-21","2008-05-16"]
["XT_98","COMP:  Electron Dump Mech/Vac Install & Commissi","2008-05-19","2008-05-16"]
["XT_99","Beam Simulation - FY-05","2005-05-02","2005-09-30",null,"2005-05-02"]
["XT_991","Specification - FEE Diagnostic Tank","2007-05-07","2007-07-02"]
["XT_992","Design - FEE Diagnostic Tank","2007-07-03","2008-01-15"]
["XT_993","Procure Computer - FEE Diagnostic Tank","2008-01-16","2008-04-10"]
["XT_994","Assemble - FEE Diagnostic Tank","2008-05-19","2008-10-08"]
["XT_995","Install - FEE Diagnostic Tank","2008-10-09","2009-01-15"]
["XT_996","Test - FEE Diagnostic Tank","2009-01-16","2009-02-12"]
["XT_997","COMP:  FEE Diagnostic Tank","2009-02-27","2009-02-26"]
["XT_LOE","X-ray LOE Complete","2009-03-31","2009-03-30"]
["XT_M1","COMP: Design Package - Electron Dump Mech/Vac","2007-11-12","2007-11-09"]
["XT_M2","COMP: Design Package - FEE Mech/Vac","2006-03-07","2006-03-06"]
[]
[null,"Total of 11881 activities selected.",null,null,"Type key: ",null,"0=Task, 1=Independent, 2=Meeting, 3=SM, 4=FM, 5=Hammock, 6=WBS, 7=Topic "]
{"$rows_empty":134}
["XT_7776","RECV:  Tank - Comm Diagnostic Tank","2008-05-19","2008-05-16"]
["XT_778","COMP:  Near Hall Mech/Vac - H3","2007-06-07","2007-06-07"]
["XT_77801","AWARD: Contract Vacuum System - Flipper Mirror","2006-10-02","2006-10-06"]
["XT_77885","AWARD: Contract Precision Hardware - Flipper Mir","2006-10-02","2006-10-06"]
["XT_7789","RECV: Material -Spatial Shape & Centroid Measure","2007-10-11","2007-10-10"]
["XT_778956","Vendor Fab Jaws - Flipper Mirror","2006-10-09","2006-11-03"]
["XT_7793","REQD: Near Hall Beneficial Occup -Comm Diag Tank","2007-03-21","2007-03-21"]
["XT_78","Specification - Far Hall Mech/Vac - H3","2007-06-19","2007-07-17"]
["XT_780","Prepare Bid Pkg -Spatial Shape & Centroid Measur","2007-06-11","2007-06-15"]
["XT_7801","Procure Production Unit-Total Energy Measurement","2006-10-03","2007-01-11"]
["XT_781","Bid Process - Spatial Shape & Centroid Measure","2007-06-18","2007-07-16"]
["XT_7813","Vendor Fab Precision Hardware - Flipper Mirror","2006-10-09","2006-11-03"]
["XT_7814","RECV Jaws - Flipper Mirror","2006-11-06","2006-11-03"]
["XT_7816","RECV Tank - Flipper Mirror","2006-11-06","2006-11-03"]
["XT_7817","Assemble Tank - Flipper Mirror","2006-11-06","2007-09-05"]
["XT_7818","Assemble Electronics - Flipper Mirror","2006-06-13","2007-04-11"]
["XT_7819","Assemble Jaws - Flipper Mirror","2006-11-06","2007-09-05"]
["XT_782","AWARD: Contract - Spatial Shape & Centroid Measu","2007-07-17","2007-07-17"]
["XT_7820","Install - Flipper Mirror","2007-09-06","2007-10-31"]
["XT_7821","Leak Check - Flipper Mirror","2007-11-01","2007-11-30"]
["XT_7822","Test Beam Line - Flipper Mirror","2007-12-03","2008-01-15"]
["XT_7823","Fab/Assemble/Test - Const $ - Flipper Mirror","2007-09-06","2008-02-13"]
["XT_7824","Commission - Flipper Mirror","2008-01-16","2008-05-08"]
["XT_7825","COMP:  Flipper Mirror","2008-05-09","2008-05-08"]
["XT_783","Vendor Fab/Ship - Spatial Shape & Centroid Measu","2007-07-18","2007-10-10"]
["XT_784","AVAIL: Near Hall Mech/Vac H3","2008-01-22","2008-01-18"]
["XT_785","Install Ion Pumps - NH Mech/Vac - H3","2007-04-18","2007-04-24"]
["XT_786","Ship to SLAC-Spatial Shape & Centroid Measure","2008-02-22","2008-02-28"]
["XT_787","Unpack and Assemble at SLAC-Spatial Shape & Cent","2008-02-29","2008-03-13"]
["XT_788","AVAIL: Spatial Shape & Centroid Measure","2008-03-14","2008-03-13"]
["XT_789","Bid Process Tank - Flipper Mirror","2006-05-15","2006-06-12"]
["XT_79","Design - Far Hall Mech/Vac - H3","2007-07-18","2007-10-10"]
["XT_7924","Bid Process Electronics - Flipper Mirror","2006-05-15","2006-06-12"]
["XT_7955","Bid Process Precision Hardware - Flipper Mirror","2006-05-15","2006-06-12"]
["XT_7956","AWARD: Contract Jaws - Flipper Mirror","2006-10-02","2006-10-06"]
["XT_7957","AWARD: Contract Tank - Flipper Mirror","2006-10-02","2006-10-06"]
["XT_798","REQD: Near Hall Benefic Occup-Spatial & Centroid","2008-03-14","2008-03-13"]
["XT_8","COMP:  FEE Mechanical/Vacuum Installed & Commiss","2008-03-04","2008-03-03"]
["XT_80","Vendor Fab Tank - Flipper Mirror","2006-10-09","2006-11-03"]
["XT_800","Test Beam Line - Slit/Collimator A","2007-07-30","2007-09-10"]
["XT_8000","Prep Bid Package Vacuum - Near Hall Optics Tank","2007-02-09","2007-02-23"]
["XT_8001","Bid Process Tank - Near Hall Optics Tank","2007-02-26","2007-03-23"]
["XT_8002","Commission - Slit/Collimator A","2007-09-11","2007-11-05"]
["XT_8003","Vendor Fab/Ship Tank - Near Hall Optics Tank","2007-03-27","2007-05-21"]
["XT_8004","AWARD: Contract Tank - Near Hall Optics Tank","2007-03-26","2007-03-26"]
["XT_8007","RECV: Tank - Near Hall Optics Tank","2007-05-22","2007-05-21"]
["XT_801","COMP:  Slit/Collimator A","2008-01-03","2008-01-02"]
["XT_805","Install Ion Gauges - NH Mech/Vac - H3","2007-04-18","2007-04-24"]
["XT_81","Assemble - Far Hall Mech/Vac - H3","2008-02-01","2008-02-07"]
["XT_810","Install - Slit/Collimator A","2007-04-19","2007-06-14"]
["XT_815","Install Stands - NH Mech/Vac - H3","2007-04-18","2007-04-24"]
["XT_82","Install Ion Pumps - Far Hall Mech/Vac - H3","2008-02-08","2008-02-14"]
["XT_820","Fab/Assemble/Test - Const $ - Slit/Col","2007-07-26","2008-01-02"]
["XT_83","Test - Far Hall Mech/Vac - H3","2008-04-21","2008-05-02"]
["XT_84","Commission - Far Hall Mech/Vac - H3","2008-05-05","2008-05-16"]
["XT_85","COMP:  Far Hall Mech/Vac - H3  Installed & Commi","2008-05-19","2008-05-16"]
["XT_86","RECV Electronics - Flipper Mirror","2006-06-13","2006-06-12"]
["XT_87","RECV Vacuum System - Flipper Mirror","2006-11-06","2006-11-03"]
["XT_88","RECV Precision Motion Hardware - Flipper Mirror","2006-11-06","2006-11-03"]
["XT_8842","Prep Bid Pkg Grating - Spectral Measurement","2006-10-02","2006-10-06"]
["XT_8845","Prep Bid Pkg Low Energy - Spectral Measurement","2006-10-02","2006-10-06"]
["XT_8846","Prep Bid Rails & Stages - Spectral Measurement","2006-10-02","2006-10-06"]
["XT_8852","Bid Process Grating - Spectral Measurement","2006-10-09","2006-11-03"]
["XT_8855","Prep Bid Pkg High Energy - Spectral Measurement","2006-10-02","2006-10-06"]
["XT_8856","Bid Process Rails & Stages -Spectral Measurement","2006-10-09","2006-11-03"]
["XT_8862","AWARD: Grating - Spectral Measurement","2006-11-06","2006-11-06"]
["XT_8865","Bid Process Low Energy - Spectral Measurement","2006-10-09","2006-11-03"]
["XT_8866","AWARD: Rails & Stages - Spectral Measurement","2006-11-06","2006-11-06"]
["XT_8872","Vendor Fab Grating - Spectral Measurement","2006-11-07","2007-01-19"]
["XT_8875","AWARD: Low Energy - Spectral Measurement","2006-11-06","2006-11-06"]
["XT_8876","Vendor Fab Rails & Stages - Spectral Measurement","2006-11-07","2007-01-19"]
["XT_8882","RECV: Grating - Spectral Measurement","2007-01-22","2007-01-19"]
["XT_8885","RECV:  Low Energy - Spectral Measurement","2007-01-22","2007-01-19"]
["XT_8886","RECV: Rails & Stages - Spectral Measurement","2007-01-22","2007-01-19"]
["XT_8895","Bid Process - Spectral Measurement","2006-10-09","2006-11-03"]
["XT_89","Procure Vacuum Hardware - Far Hall Mech/Vac","2007-10-11","2007-12-07"]
["XT_8905","AWARD: Contract - Spectral Measurement","2006-11-06","2006-11-06"]
["XT_8915","Vendor Fab High Energy - Spectral Measurement","2006-11-07","2007-02-16"]
["XT_8925","RECV: High Energy - Spectral Measurement","2007-02-20","2007-02-16"]
["XT_8935","Vendor Fab Low Energy - Spectral Measurement","2006-11-07","2007-01-19"]
["XT_899","Assemble -Spatial Shape & Centroid Measure","2007-10-11","2008-02-21"]
["XT_9","Specification - Electron Dump Mech/Vac","2007-10-01","2007-10-12"]
["XT_90","Assemble Vacuum System - Flipper Mirror","2006-11-06","2007-09-05"]
["XT_91","AVAIL: Far Hall Mech/Vac Ready to Install SLAC","2008-02-08","2008-02-07"]
["XT_92","Assemble Precision Hardware - Flipper Mirror","2006-11-06","2007-09-05"]
["XT_94","Assemble Pipe - Electron Dump Mech/Vac","2008-03-24","2008-03-28"]
["XT_95","Install Vacuum Pipe - Electron Dump Mech/Vac","2008-03-31","2008-04-04"]
["XT_96","Test Pipe - Electron Dump Mech/Vac","2008-04-07","2008-04-18"]
["XT_97","Commission - Electron Dump Mech/Vac","2008-08-13","2008-09-10"]
["XT_98","COMP:  Electron Dump Mech/Vac Install & Commissi","2008-09-11","2008-09-10"]
["XT_99","Beam Simulation - FY-05","2005-05-02","2005-12-07",null,"2005-05-02"]
["XT_991","Specification - FEE Diagnostic Tank","2007-05-07","2007-07-02"]
["XT_992","Design - FEE Diagnostic Tank","2007-07-03","2008-01-15"]
["XT_993","Procure Computer - FEE Diagnostic Tank","2008-01-16","2008-04-10"]
["XT_994","Assemble - FEE Diagnostic Tank","2008-05-19","2008-10-08"]
["XT_995","Install - FEE Diagnostic Tank","2008-10-09","2009-01-15"]
["XT_996","Test - FEE Diagnostic Tank","2009-01-16","2009-02-12"]
["XT_997","COMP:  FEE Diagnostic Tank","2009-02-27","2009-02-26"]
["XT_LOE","X-ray LOE Complete","2009-03-31","2009-03-30"]
["XT_M1","COMP: Design Package - Electron Dump Mech/Vac","2007-11-12","2007-11-09"]
["XT_M2","COMP: Design Package - FEE Mech/Vac","2006-02-06","2006-02-03"]
[]
[null,"Total of 12118 activities selected.",null,null,"Type key: ",null,"0=Task, 1=Independent, 2=Meeting, 3=SM, 4=FM, 5=Hammock, 6=WBS, 7=Topic "]
{"$rows_empty":94}
["XT_661","Specification - Far Hall Mech/Vac - H1","2007-06-19","2007-07-17"]
["XT_662","Design - Far Hall Mech/Vac - H1","2007-07-18","2007-10-10"]
["XT_663","RECV: Data Acquisition- Direct Imager","2007-02-27","2007-02-26"]
["XT_665","Assemble - Far Hall Mech/Vac","2008-02-01","2008-02-29"]
["XT_666","Install Isolation Valve - Far Hall Mech/Vac","2008-03-03","2008-03-07"]
["XT_667","Test - Far Hall Mech/Vac - H1","2008-03-10","2008-03-21"]
["XT_6670","Prep Bid Pkg Turbo System - FEE Diagnostic Tank","2008-01-16","2008-01-23"]
["XT_6671","Bid Process Turbo System - FEE Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_6672","AWARD: Contract Turbo System - FEE Diagnostic Tn","2008-02-22","2008-02-22"]
["XT_6673","Vendor Fab/Ship Turbo System - FEE Diagnostic Ta","2008-02-25","2008-05-16"]
["XT_6674","RECV:  Turbo System - FEE Diagnostic Tank","2008-05-19","2008-05-16"]
["XT_6675","Prep Bid Pkg Scroll Dry Pump-FEE Diagnostic Tnk","2008-01-16","2008-01-23"]
["XT_6676","Bid Process Scroll Dry Pump-FEE Diagnostic Tnk","2008-01-24","2008-02-21"]
["XT_6677","AWARD: Contract Scroll Dry Pump-FEE DiagnosticTn","2008-02-22","2008-02-22"]
["XT_6678","Vendor Ship Scroll Dry Pump-FEE Diagnostic Tank","2008-02-25","2008-05-16"]
["XT_6679","RECV: Scroll Dry Pump-FEE Diagnostic Tnk","2008-05-19","2008-05-16"]
["XT_668","Commission - Far Hall Mech/Vac - H1","2008-03-24","2008-04-04"]
["XT_6680","Prep Bid Pkg Imager Stages - FEE Diagnostic Tank","2008-01-16","2008-01-23"]
["XT_6681","Bid Process  Imager Stages - FEE Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_6682","AWARD: Contract  Imager Stages - FEE Diagnostic","2008-02-22","2008-02-22"]
["XT_6683","Vendor Fab/Ship Imager Stages - FEE Diagnostic T","2008-02-25","2008-05-16"]
["XT_6684","RECV:   Imager Stages - FEE Diagnostic Tank","2008-05-19","2008-05-16"]
["XT_6685","Prep Bid Pkg Stand - FEE Diagnostic Tank","2008-01-16","2008-01-23"]
["XT_6686","Bid Process Stand - FEE Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_6687","AWARD: Contract Stand - FEE Diagnostic Tank","2008-02-22","2008-02-22"]
["XT_6688","Vendor Fab/Ship Stand - FEE Diagnostic Tank","2008-02-25","2008-05-16"]
["XT_6689","RECV:  Stand - FEE Diagnostic Tank","2008-05-19","2008-05-16"]
["XT_669","COMP:  Far Hall Mech/Vac - H1 Installed & Commis","2008-04-07","2008-04-04"]
["XT_6690","Prep Bid Pkg Motor Driver - FEE Diagnostic Tank","2008-01-16","2008-01-23"]
["XT_6691","Bid Process Motor Driver - FEE Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_6692","AWARD: Contract Motor Driver - FEE Diagnostic Ta","2008-02-22","2008-02-22"]
["XT_6693","Vendor Fab/Ship Motor Driver -FEE Diagnostic Tnk","2008-02-25","2008-05-16"]
["XT_6694","RECV: Motor Driver - FEE Diagnostic Tank","2008-05-19","2008-05-16"]
["XT_6695","Prep Bid Pkg EPICS IF - FEE Diagnostic Tank","2008-01-16","2008-01-23"]
["XT_6696","Bid Process EPICS IF - FEE Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_6697","AWARD: Contract EPICS IF - FEE Diagnostic Tank","2008-02-22","2008-02-22"]
["XT_6698","Vendor Fab/Ship EPICS IF - FEE Diagnostic Tank","2008-02-25","2008-05-16"]
["XT_6699","RECV: EPICS IF - FEE Diagnostic Tank","2008-05-19","2008-05-16"]
["XT_6700","Prep Bid Pk Misc Racks/Chases-FEE Diagnostic Tnk","2008-01-16","2008-01-23"]
["XT_6701","Bid Process Misc Racks/Chases-FEE Diagnostic Tnk","2008-01-24","2008-02-21"]
["XT_6702","AWARD: Contract Misc Racks/Chases-FEE Diagnostic","2008-02-22","2008-02-22"]
["XT_6703","Vendor Fab/Ship Misc Racks/Chases-FEE Diagnostic","2008-02-25","2008-05-16"]
["XT_6704","RECV:  Misc Racks/Chases-FEE Diagnostic Tnk","2008-05-19","2008-05-16"]
["XT_671","Specification - Near Hall Mech/Vac - H2","2006-03-01","2006-05-23"]
["XT_672","Design - Near Hall Mech/Vac - H2","2006-05-24","2006-09-15"]
["XT_674","Assemble - NH Mech/Vac - H2","2007-03-27","2007-04-23"]
["XT_676","Test - Near Hall Mech/Vac - H2","2008-01-29","2008-02-11"]
["XT_677","Commission - Near Hall Mech/Vac - H2","2008-02-12","2008-03-11"]
["XT_678","COMP:  Near Hall Mech/Vac - H2","2008-03-12","2008-03-12"]
["XT_680","Commission - Near Hall Mech/Vac - H1","2008-02-12","2008-03-11"]
["XT_682","Procure Hand Isolation Valve-Far Hall Mec/Vac-H1","2007-10-11","2007-12-07"]
["XT_683","Procure Gate Isolation Valve-Far Hall Mec/Vac-H1","2007-10-11","2007-12-07"]
["XT_684","AVAIL: Near Hall Mech/Vac - H2","2007-04-24","2007-04-23"]
["XT_685","Procure Bellows & Spools - Far Hall Mech/Vac","2007-10-11","2007-12-07"]
["XT_686","COMP: Design - Spatial Coherence","2008-01-09","2008-01-08"]
["XT_687","AWARD: Low Energy Slit - Spatial Coherence","2008-02-22","2008-02-22"]
["XT_688","Procure Bellows & Spools - Far Hall Mech/Vac","2007-10-11","2007-12-07"]
["XT_69","Bid Process Jaws - Flipper Mirror","2006-05-15","2006-06-12"]
["XT_691","Specification - Indirect Imager","2005-02-01","2005-06-24",null,"2005-02-01"]
["XT_692","Design - Indirect Imager","2005-06-27","2006-04-25"]
["XT_694","Assemble - Indirect Imager","2006-10-03","2007-03-12"]
["XT_695","Install - Indirect Imager","2007-07-10","2007-10-02"]
["XT_696","Test - Indirect Imager","2007-10-24","2007-11-20"]
["XT_697","COMP:  Indirect Imager Installed & Commissioned","2007-12-07","2007-12-06"]
["XT_699","Procure Hand Isolation Valve - Far Hall Mech/Vac","2007-10-11","2007-12-07"]
["XT_7","Commission - FEE Mech/Vac","2008-01-04","2008-03-03"]
["XT_70","Specification - Far Hall Mech/Vac - H2","2007-06-19","2007-07-17"]
["XT_700","Assemble - NH Mech/Vac - H1","2008-01-07","2008-01-18"]
["XT_7000","Specification - Slit/Collimator B","2006-10-02","2006-10-27"]
["XT_7001","Design - Slit/Collimator B","2006-10-30","2007-04-06"]
["XT_70011","REQD: FEE Beneficial Occupancy","2008-04-18","2008-04-17"]
["XT_7002","Design Review - Slit/Collimator B","2007-04-09","2007-05-04"]
["XT_7003","COMP: Design Package - Slit/Collimator B","2007-05-07","2007-05-04"]
["XT_7004","Prepare Bid Pkg Jaws - Slit/Collimator B","2007-05-07","2007-05-11"]
["XT_7005","Prepare Bid Pkg Tank - Slit/Collimator B","2007-05-07","2007-05-11"]
["XT_7006","Prepare Bid Pkg Electronics - Slit/Collimator B","2007-05-07","2007-05-11"]
["XT_7007","Prepare Bid Pk Vacuum System - Slit/Collimator B","2007-05-07","2007-05-11"]
["XT_7008","Prepare Bid Pkg Precision Hardware - Slit/Col B","2007-05-07","2007-05-11"]
["XT_7009","Bid Process Jaws - Slit/Collimator B","2007-05-14","2007-06-11"]
["XT_7010","Bid Process Tank - Slit/Collimator B","2007-05-14","2007-06-11"]
["XT_7011","Bid Process Electronics - Slit/Collimator B","2007-05-14","2007-06-11"]
["XT_7012","Bid Process Vacuum System - Slit/Collimator B","2007-05-14","2007-06-11"]
["XT_7013","Bid Process Precision Hardware - Slit/Col B","2007-05-14","2007-06-11"]
["XT_7014","AWARD: Contract Jaws - Slit/Collimator B","2007-06-12","2007-06-18"]
["XT_7015","AWARD: Contract Tank - Slit/Collimator B","2007-06-12","2007-06-18"]
["XT_7017","AWARD: Contract Vacuum System-Slit/Collimator B","2007-06-12","2007-06-18"]
["XT_7018","AWARD: Contract Precision Hardware - Slit/Col B","2007-06-12","2007-06-18"]
["XT_7019","Vendor Fab Jaws - Slit/Collimator B","2007-06-19","2007-07-17"]
["XT_702","Procure Vacuum Hardware - Far Hall Mech/Vac - H1","2007-10-11","2007-12-07"]
["XT_7020","Vendor Fab Tank - Slit/Collimator B","2007-06-19","2007-07-17"]
["XT_7022","Vendor Fab Vacuum System - Slit/Collimator B","2007-06-19","2007-07-17"]
["XT_7023","Vendor Fab Precision Hardware - Slit/Col B","2007-06-19","2007-07-17"]
["XT_7024","RECV Jaws - Slit/Collimator B","2007-07-18","2007-07-17"]
["XT_7025","RECV Tank - Slit/Collimator B","2007-07-18","2007-07-17"]
["XT_7026","RECV Electronics - Slit/Collimator B","2007-07-18","2007-07-17"]
["XT_7027","RECV Vacuum System - Slit/Collimator B","2007-07-18","2007-07-17"]
["XT_7028","RECV Precision Motion Hardware - Slit/Col B","2007-07-18","2007-07-17"]
["XT_7029","Assemble Tank - Slit/Collimator B","2007-07-18","2008-04-17"]
["XT_7030","Assemble Vacuum System - Slit/Collimator B","2007-07-18","2008-04-17"]
["XT_7031","Assemble Electronics - Slit/Collimator B","2007-07-18","2008-04-17"]
["XT_7032","Assemble Precision Hardware - Slit/Collimator B","2007-07-18","2008-04-17"]
["XT_7033","Assemble Jaws - Slit/Collimator B","2007-07-18","2008-04-17"]
["XT_7034","Install - Slit/Collimator B","2008-04-18","2008-06-13"]
["XT_7035","Leak Check - Slit/Collimator B","2008-06-16","2008-09-09"]
["XT_7036","Test Beam Line - Slit/Collimator B","2008-09-10","2008-11-04"]
["XT_7037","Commission - Slit/Collimator B","2008-11-05","2009-03-11"]
["XT_7038","COMP:  Slit/Collimator B  Installed & Commiss","2009-03-12","2009-03-11"]
["XT_704","AVAIL: Indirect Imager Ready to Ship to SLAC","2007-07-10","2007-07-09"]
["XT_7040","Engineering - Slit/Collimator B","2006-10-30","2007-06-18"]
["XT_7046","Fab/Assemble/Test - Const $ - Slit/Col","2008-09-10","2009-02-11"]
["XT_707","Vendor Fab Low Energy Slit - Spatial Coherence","2008-02-25","2008-05-16"]
["XT_71","Design - Far Hall Mech/Vac - H2","2007-07-18","2007-10-10"]
["XT_710","AVAIL: Near Hall Mech/Vac - H1","2008-01-22","2008-01-18"]
["XT_711","Prepare Bid Pkg Tank - Flipper Mirror","2006-05-08","2006-05-12"]
["XT_712","COMP: Design Package - Indirect Imager","2006-04-26","2006-04-25"]
["XT_7122","Prepare Bid Pkg Precision Hardware - Flipper Mir","2006-05-08","2006-05-12"]
["XT_717","RECV: Low Energy Slit - Spatial Coherence","2008-05-19","2008-05-16"]
["XT_72","Bid Process Vacuum System - Flipper Mirror","2006-05-15","2006-06-12"]
["XT_73","Assemble - Far Hall Mech/Vac - H2","2008-02-01","2008-02-29"]
["XT_730","COMP:  Near Hall Mech/Vac - H1","2008-03-12","2008-03-12"]
["XT_736","Commission - Direct Imager","2008-02-08","2008-02-22"]
["XT_74","Install Ion Pumps - Far Hall Mech/Vac - H2","2008-03-03","2008-03-07"]
["XT_746","Commission - Indirect Imager","2007-11-21","2007-12-06"]
["XT_75","Test - Far Hall Mech/Vac - H2","2008-03-10","2008-03-21"]
["XT_7512","Vendor Fab Vacuum System - Flipper Mirror","2006-10-09","2006-11-03"]
["XT_76","Commission - Far Hall Mech/Vac - H2","2008-03-24","2008-04-04"]
["XT_77","COMP:  Far Hall Mech/Vac - H2","2008-04-07","2008-04-04"]
["XT_7700","COMP: Design Package - Ion Pumped Tank","2008-01-16","2008-01-15"]
["XT_7701","Prep Bid Pkg Tank - Ion Pumped Tank","2008-01-16","2008-01-23"]
["XT_7702","Bid Process Tank - Ion Pumped Tank","2008-01-24","2008-02-21"]
["XT_7703","AWARD: Contract Tank - Ion Pumped Tank","2008-02-22","2008-02-22"]
["XT_7704","Vendor Fab/Ship Tank - Ion Pumped Tank","2008-02-25","2008-05-16"]
["XT_7705","RECV:  Tank - Ion Pumped Tank","2008-05-19","2008-05-16"]
["XT_7706","Prep Bid Pkg Ion Pump - Ion Pumped Tank","2008-01-16","2008-01-23"]
["XT_7707","Bid Process Ion Pump - Ion Pumped Tank","2008-01-24","2008-02-21"]
["XT_7708","AWARD: Contract Ion Pump - Ion Pumped Tank","2008-02-22","2008-02-22"]
["XT_7709","Vendor Fab/Ship Ion Pump - Ion Pumped Tank","2008-02-25","2008-05-16"]
["XT_771","Specification - Near Hall Mech/Vac - H3","2006-03-01","2006-05-23"]
["XT_7710","RECV:  Ion Pump - Ion Pumped Tank","2008-05-19","2008-05-16"]
["XT_7711","Prep Bid Pkg  Misc - Ion Pumped Tank","2008-01-16","2008-01-23"]
["XT_7712","Bid Process Misc - Ion Pumped Tank","2008-01-24","2008-02-21"]
["XT_7713","AWARD: Contract Misc - Ion Pump Tnk","2008-02-22","2008-02-22"]
["XT_7714","Vendor Ship Misc - Ion Pumped Tank","2008-02-25","2008-05-16"]
["XT_7715","RECV:  Misc - Ion Pumped Tank","2008-05-19","2008-05-16"]
["XT_7716","Prep Bid Pkg Imager Stages - Ion Pumped Tank","2008-01-16","2008-01-23"]
["XT_7717","Bid Process  Imager Stages - Ion Pumped Tank","2008-01-24","2008-02-21"]
["XT_7718","AWARD: Contract  Imager Stages - Ion Pumped Tank","2008-02-22","2008-02-22"]
["XT_7719","Vendor Fab/Ship Imager Stages - Ion Pumped Tank","2008-02-25","2008-05-16"]
["XT_772","Design - Near Hall Mech/Vac - H3","2006-05-24","2006-09-15"]
["XT_7720","RECV:   Imager Stages - Ion Pumped Tank","2008-05-19","2008-05-16"]
["XT_7721","Prep Bid Pkg Stand - Ion Pumped Tank","2008-01-16","2008-01-23"]
["XT_7722","Bid Process Stand - Ion Pumped Tank","2008-01-24","2008-02-21"]
["XT_7723","AWARD: Contract Stand - Ion Pumped Tank","2008-02-22","2008-02-22"]
["XT_7724","Vendor Fab/Ship Stand - Ion Pumped Tank","2008-02-25","2008-05-16"]
["XT_7725","RECV:  Stand - Ion Pumped Tank","2008-05-19","2008-05-16"]
["XT_7726","Prep Bid Pkg Motor Driver - Ion Pumped Tank","2008-01-16","2008-01-23"]
["XT_7727","Bid Process Motor Driver - Ion Pumped Tank","2008-01-24","2008-02-21"]
["XT_7728","AWARD: Contract Motor Driver - Ion Pumped Tank","2008-02-22","2008-02-22"]
["XT_7729","Vendor Fab/Ship Motor Driver -Ion Pumped Tank","2008-02-25","2008-05-16"]
["XT_773","REQD: Near Hall Beneficial Occup - Mech/Vac","2007-03-27","2007-03-26"]
["XT_7730","RECV: Motor Driver - Ion Pumped Tank","2008-05-19","2008-05-16"]
["XT_7731","Prep Bid Pkg EPICS IF - Ion Pumped Tank","2008-01-16","2008-01-23"]
["XT_7732","Bid Process EPICS IF - Ion Pumped Tank","2008-01-24","2008-02-21"]
["XT_7733","AWARD: Contract EPICS IF - Ion Pumped Tank","2008-02-22","2008-02-22"]
["XT_7734","Vendor Fab/Ship EPICS IF - Ion Pumped Tank","2008-02-25","2008-05-16"]
["XT_7735","RECV: EPICS IF - Ion Pumped Tank","2008-05-19","2008-05-16"]
["XT_7736","Prep Bid Pk Misc Racks/Chases-Ion Pumped Tank","2008-01-16","2008-01-23"]
["XT_7737","Bid Process Misc Racks/Chases-Ion Pumped Tank","2008-01-24","2008-02-21"]
["XT_7738","AWARD: Contract Misc Racks/Chases-Ion Pumped Tan","2008-02-22","2008-02-22"]
["XT_7739","Vendor Fab/Ship Misc Racks/Chases-Ion Pumped Tan","2008-02-25","2008-05-16"]
["XT_774","Assemble - NH Mech/Vac - H3","2007-03-27","2007-04-23"]
["XT_7740","RECV:  Misc Racks/Chases-Ion Pumped Tank","2008-05-19","2008-05-16"]
["XT_7741","COMP: Design - Comm Diagnostic Tank","2008-01-16","2008-01-15"]
["XT_7742","Prep Bid Pkg Tank - Comm Diagnostic Tank","2008-01-16","2008-01-23"]
["XT_7743","Prep Bid Pkg Scroll Dry Pump-Comm Diagnostic Tnk","2008-01-16","2008-01-23"]
["XT_7744","Prep Bid Pkg Turbo System - Comm Diagnostic Tank","2008-01-16","2008-01-23"]
["XT_7745","Prep Bid Pkg Imager Stages - Comm Diagnostic Tan","2008-01-16","2008-01-23"]
["XT_7746","Prep Bid Pkg Stand - Comm Diagnostic Tank","2008-01-16","2008-01-23"]
["XT_7747","Prep Bid Pkg Motor Driver - Comm Diagnostic Tank","2008-01-16","2008-01-23"]
["XT_7748","Prep Bid Pkg EPICS IF - Comm Diagnostic Tank","2008-01-16","2008-01-23"]
["XT_7749","Prep Bid Pk 2 Axis Rail Adjus-Comm Diagnostic Ta","2008-01-16","2008-01-23"]
["XT_775","Install Vacuum Piping - NH Mech/Vac - H3","2007-04-24","2007-04-30"]
["XT_7751","Bid Process Tank - Comm Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_7752","Bid Process Scroll Dry Pump-Comm Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_7753","Bid Process Turbo System - Comm Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_7754","Bid Process  Imager Stages - Comm Diagnostic Tan","2008-01-24","2008-02-21"]
["XT_7755","Bid Process Stand - Comm Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_7756","Bid Process Motor Driver - Comm Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_7757","Bid Process EPICS IF - Comm Diagnostic Tank","2008-01-24","2008-02-21"]
["XT_7758","Bid Process 2 Axis Rail Adjus-Comm Diagnostic Ta","2008-01-24","2008-02-21"]
["XT_7759","AWARD: Contract Tank - Comm Diagnostic Tank","2008-02-22","2008-02-22"]
["XT_776","Test - Near Hall Mech/Vac - H3","2007-05-01","2007-05-14"]
["XT_7767","Vendor Fab/Ship Tank - Comm Diagnostic Tank","2008-02-25","2008-05-16"]
["XT_777","Commission - Near Hall Mech/Vac - H3","2007-05-15","2007-06-12"]
["XT_7775","Assemble - Comm Diagnostic Tank","2008-01-24","2008-05-15"]
["XT_7776","RECV:  Tank - Comm Diagnostic Tank","2008-05-19","2008-05-16"]
["XT_778","COMP:  Near Hall Mech/Vac - H3","2007-06-13","2007-06-13"]
["XT_77801","AWARD: Contract Vacuum System - Flipper Mirror","2006-10-02","2006-10-06"]
["XT_77885","AWARD: Contract Precision Hardware - Flipper Mir","2006-10-02","2006-10-06"]
["XT_7789","RECV: Material -Spatial Shape & Centroid Measure","2007-08-09","2007-08-08"]
["XT_778956","Vendor Fab Jaws - Flipper Mirror","2006-10-09","2006-11-03"]
["XT_7793","REQD: Near Hall Beneficial Occup -Comm Diag Tank","2007-03-26","2007-03-26"]
["XT_78","Specification - Far Hall Mech/Vac - H3","2007-06-19","2007-07-17"]
["XT_780","Prepare Bid Pkg -Spatial Shape & Centroid Measur","2007-04-09","2007-04-13"]
["XT_7801","Procure Production Unit-Total Energy Measurement","2006-10-03","2007-01-11"]
["XT_781","Bid Process - Spatial Shape & Centroid Measure","2007-04-16","2007-05-11"]
["XT_7813","Vendor Fab Precision Hardware - Flipper Mirror","2006-10-09","2006-11-03"]
["XT_7814","RECV Jaws - Flipper Mirror","2006-11-06","2006-11-03"]
["XT_7816","RECV Tank - Flipper Mirror","2006-11-06","2006-11-03"]
["XT_7817","Assemble Tank - Flipper Mirror","2006-11-06","2007-09-05"]
["XT_7818","Assemble Electronics - Flipper Mirror","2006-06-13","2007-04-11"]
["XT_7819","Assemble Jaws - Flipper Mirror","2006-11-06","2007-09-05"]
["XT_782","AWARD: Contract - Spatial Shape & Centroid Measu","2007-05-14","2007-05-14"]
["XT_7820","Install - Flipper Mirror","2007-09-06","2007-10-31"]
["XT_7821","Leak Check - Flipper Mirror","2007-11-01","2007-11-30"]
["XT_7822","Test Beam Line - Flipper Mirror","2007-12-03","2008-01-15"]
["XT_7823","Fab/Assemble/Test - Const $ - Flipper Mirror","2007-09-06","2008-02-13"]
["XT_7824","Commission - Flipper Mirror","2008-01-16","2008-05-08"]
["XT_7825","COMP:  Flipper Mirror","2008-05-09","2008-05-08"]
["XT_783","Vendor Fab/Ship - Spatial Shape & Centroid Measu","2007-05-15","2007-08-08"]
["XT_784","AVAIL: Near Hall Mech/Vac H3","2008-01-22","2008-01-18"]
["XT_785","Install Ion Pumps - NH Mech/Vac - H3","2007-04-24","2007-04-30"]
["XT_786","Ship to SLAC-Spatial Shape & Centroid Measure","2007-12-04","2007-12-10"]
["XT_787","Unpack and Assemble at SLAC-Spatial Shape & Cent","2007-12-11","2008-01-09"]
["XT_788","AVAIL: Spatial Shape & Centroid Measure","2008-01-10","2008-01-09"]
["XT_789","Bid Process Tank - Flipper Mirror","2006-05-15","2006-06-12"]
["XT_79","Design - Far Hall Mech/Vac - H3","2007-07-18","2007-10-10"]
["XT_7924","Bid Process Electronics - Flipper Mirror","2006-05-15","2006-06-12"]
["XT_7955","Bid Process Precision Hardware - Flipper Mirror","2006-05-15","2006-06-12"]
["XT_7956","AWARD: Contract Jaws - Flipper Mirror","2006-10-02","2006-10-06"]
["XT_7957","AWARD: Contract Tank - Flipper Mirror","2006-10-02","2006-10-06"]
["XT_798","REQD: Near Hall Benefic Occup-Spatial & Centroid","2008-01-10","2008-01-09"]
["XT_8","COMP:  FEE Mechanical/Vacuum Installed & Commiss","2008-03-04","2008-03-03"]
["XT_80","Vendor Fab Tank - Flipper Mirror","2006-10-09","2006-11-03"]
["XT_800","Test Beam Line - Slit/Collimator A","2007-07-30","2007-09-10"]
["XT_8000","Prep Bid Package Vacuum - Near Hall Optics Tank","2007-02-09","2007-02-23"]
["XT_8001","Bid Process Tank - Near Hall Optics Tank","2007-02-26","2007-03-23"]
["XT_8002","Commission - Slit/Collimator A","2007-09-11","2007-11-05"]
["XT_8003","Vendor Fab/Ship Tank - Near Hall Optics Tank","2007-03-27","2007-05-21"]
["XT_8004","AWARD: Contract Tank - Near Hall Optics Tank","2007-03-26","2007-03-26"]
["XT_8007","RECV: Tank - Near Hall Optics Tank","2007-05-22","2007-05-21"]
["XT_801","COMP:  Slit/Collimator A","2007-11-30","2007-11-29"]
["XT_805","Install Ion Gauges - NH Mech/Vac - H3","2007-04-24","2007-04-30"]
["XT_81","Assemble - Far Hall Mech/Vac - H3","2008-02-01","2008-02-07"]
["XT_810","Install - Slit/Collimator A","2007-04-19","2007-06-14"]
["XT_815","Install Stands - NH Mech/Vac - H3","2007-04-24","2007-04-30"]
["XT_82","Install Ion Pumps - Far Hall Mech/Vac - H3","2008-02-08","2008-02-14"]
["XT_820","Fab/Assemble/Test - Const $ - Slit/Col","2007-07-10","2007-11-29"]
["XT_83","Test - Far Hall Mech/Vac - H3","2008-04-21","2008-05-02"]
["XT_84","Commission - Far Hall Mech/Vac - H3","2008-05-05","2008-05-16"]
["XT_85","COMP:  Far Hall Mech/Vac - H3  Installed & Commi","2008-05-19","2008-05-16"]
["XT_86","RECV Electronics - Flipper Mirror","2006-06-13","2006-06-12"]
["XT_87","RECV Vacuum System - Flipper Mirror","2006-11-06","2006-11-03"]
["XT_88","RECV Precision Motion Hardware - Flipper Mirror","2006-11-06","2006-11-03"]
["XT_8842","Prep Bid Pkg Grating - Spectral Measurement","2006-10-02","2006-10-06"]
["XT_8845","Prep Bid Pkg Low Energy - Spectral Measurement","2006-10-02","2006-10-06"]
["XT_8846","Prep Bid Rails & Stages - Spectral Measurement","2006-10-02","2006-10-06"]
["XT_8852","Bid Process Grating - Spectral Measurement","2006-10-09","2006-11-03"]
["XT_8855","Prep Bid Pkg High Energy - Spectral Measurement","2006-10-02","2006-10-06"]
["XT_8856","Bid Process Rails & Stages -Spectral Measurement","2006-10-09","2006-11-03"]
["XT_8862","AWARD: Grating - Spectral Measurement","2006-11-06","2006-11-06"]
["XT_8865","Bid Process Low Energy - Spectral Measurement","2006-10-09","2006-11-03"]
["XT_8866","AWARD: Rails & Stages - Spectral Measurement","2006-11-06","2006-11-06"]
["XT_8872","Vendor Fab Grating - Spectral Measurement","2006-11-07","2007-01-19"]
["XT_8875","AWARD: Low Energy - Spectral Measurement","2006-11-06","2006-11-06"]
["XT_8876","Vendor Fab Rails & Stages - Spectral Measurement","2006-11-07","2007-01-19"]
["XT_8882","RECV: Grating - Spectral Measurement","2007-01-22","2007-01-19"]
["XT_8885","RECV:  Low Energy - Spectral Measurement","2007-01-22","2007-01-19"]
["XT_8886","RECV: Rails & Stages - Spectral Measurement","2007-01-22","2007-01-19"]
["XT_8895","Bid Process - Spectral Measurement","2006-10-09","2006-11-03"]
["XT_89","Procure Vacuum Hardware - Far Hall Mech/Vac","2007-10-11","2007-12-07"]
["XT_8905","AWARD: Contract - Spectral Measurement","2006-11-06","2006-11-06"]
["XT_8915","Vendor Fab High Energy - Spectral Measurement","2006-11-07","2007-02-16"]
["XT_8925","RECV: High Energy - Spectral Measurement","2007-02-20","2007-02-16"]
["XT_8935","Vendor Fab Low Energy - Spectral Measurement","2006-11-07","2007-01-19"]
["XT_899","Assemble -Spatial Shape & Centroid Measure","2007-08-09","2007-12-03"]
["XT_9","Specification - Electron Dump Mech/Vac","2007-10-01","2007-10-12"]
["XT_90","Assemble Vacuum System - Flipper Mirror","2006-11-06","2007-09-05"]
["XT_91","AVAIL: Far Hall Mech/Vac Ready to Install SLAC","2008-02-08","2008-02-07"]
["XT_92","Assemble Precision Hardware - Flipper Mirror","2006-11-06","2007-09-05"]
["XT_94","Assemble Pipe - Electron Dump Mech/Vac","2008-03-24","2008-03-28"]
["XT_95","Install Vacuum Pipe - Electron Dump Mech/Vac","2008-03-31","2008-04-04"]
["XT_96","Test Pipe - Electron Dump Mech/Vac","2008-04-07","2008-04-18"]
["XT_97","Commission - Electron Dump Mech/Vac","2008-08-13","2008-09-10"]
["XT_98","COMP:  Electron Dump Mech/Vac Install & Commissi","2008-09-11","2008-09-10"]
["XT_99","Beam Simulation - FY-05","2005-02-01","2005-11-01",null,"2005-02-01"]
["XT_991","Specification - FEE Diagnostic Tank","2007-05-07","2007-07-02"]
["XT_992","Design - FEE Diagnostic Tank","2007-07-03","2008-01-15"]
["XT_993","Procure Computer - FEE Diagnostic Tank","2008-01-16","2008-04-10"]
["XT_994","Assemble - FEE Diagnostic Tank","2008-05-19","2008-10-08"]
["XT_995","Install - FEE Diagnostic Tank","2008-10-09","2009-01-15"]
["XT_996","Test - FEE Diagnostic Tank","2009-01-16","2009-02-12"]
["XT_997","COMP:  FEE Diagnostic Tank","2009-02-27","2009-02-26"]
["XT_LOE","X-ray LOE Complete","2009-03-31","2009-03-30"]
["XT_M1","COMP: Design Package - Electron Dump Mech/Vac","2007-11-12","2007-11-09"]
["XT_M2","COMP: Design Package - FEE Mech/Vac","2006-03-01","2006-02-28"]
[]
[null,"Total of 12510 activities selected.",null,null,"Type key: ",null,"0=Task, 1=Independent, 2=Meeting, 3=SM, 4=FM, 5=Hammock, 6=WBS, 7=Topic "]
{"$rows_empty":94}
["XT_3300","R&D - Total Measurement","2004-10-03","2005-08-25",null,"2004-10-03"]
["XT_333","Vendor Fab/Ship Vacuum Chamb-Pulse Split & Delay","2007-01-10","2007-04-05"]
["XT_338","RECV: Computer System - Wave Model","2006-08-09","2006-08-08"]
["XT_34","Vendor Fab/Ship Stands - Far Hall Mech/Vac","2007-01-31","2007-03-28"]
["XT_340","Install Berilium Valves - NH Mech/Vac - H1","2007-04-18","2007-04-24"]
["XT_343","RECV: Vacuum Chamber Pulse Split & Delay","2007-04-06","2007-04-05"]
["XT_3444","R&D - Component Physics Design","2004-10-01","2005-05-09",null,"2004-10-01"]
["XT_3445","R&D - Beamline Mechanical Layout","2004-10-01","2005-05-09",null,"2004-10-01"]
["XT_3454","LLNL - Commissioning Team","2007-06-08","2009-02-02"]
["XT_3464","R&D - FEE Physics Preliminary Layout","2005-05-10","2005-05-09"]
["XT_3474","R&D - Near Hall Physics Preliminary Layout","2005-05-10","2005-05-09"]
["XT_348","Commission - Monte Carlo Model","2008-05-22","2008-06-19"]
["XT_3484","R&D - Far Hall Physics Preliminary Layout","2005-09-02","2005-09-01"]
["XT_3485","R&D - Beamline Electronics & Controls","2004-10-01","2005-05-09",null,"2004-10-01"]
["XT_3486","R&D - Beamline Electronics","2005-01-03","2005-01-24",null,"2005-01-03","2005-01-24"]
["XT_35","RECV: Stands - Far Hall Mech/Vac","2007-03-29","2007-03-28"]
["XT_350","Install Vacuum Piping - NH Mech/Vac - H1","2007-04-18","2007-04-24"]
["XT_35567","Meetings -  FY06-09","2005-10-03","2009-03-30"]
["XT_36","Procure Spools - Far Hall Mech/Vac - H1","2006-12-08","2007-02-20"]
["XT_360","Install Ion Pumps - NH Mech/Vac - H1","2007-04-18","2007-04-24"]
["XT_3666","Install Ion Gauges - NH Mech/Vac - H2","2007-04-18","2007-04-24"]
["XT_3668","Install Stands - NH Mech/Vac - H2","2007-04-18","2007-04-24"]
["XT_3669","Install Isolation Valves - NH Mech/Vac - H2","2007-04-18","2007-04-24"]
["XT_3670","Install Berilium Valves - NH Mech/Vac - H2","2007-04-18","2007-04-24"]
["XT_3671","Install Vacuum Piping - NH Mech/Vac - H2","2007-04-18","2007-04-24"]
["XT_3672","Install Ion Pumps - NH Mech/Vac - H2","2007-04-18","2007-04-24"]
["XT_37","Procure Ion Gauges - Far Hall Mech/Vac - H1","2006-12-08","2007-02-20"]
["XT_4","Assemble - FEE Mech/Vac","2007-07-09","2007-08-03"]
["XT_40","Engineering - Commissioning Diagnostics","2006-03-10","2006-07-31"]
["XT_400","Design - Slit/Collimator A","2005-10-31","2006-04-07"]
["XT_4000","Prep Bid Pkg Cntrl/Elect - Near Hall Optic Tank","2007-02-12","2007-02-26"]
["XT_40006","AWARD: Contract Control/Elect - NHall Optic Tan","2007-03-27","2007-03-27"]
["XT_40008","RECV: Control/Electrical - NHall Optic Tank","2007-05-23","2007-05-22"]
["XT_4001","Bid Process Control/Elect - Near Hall Optic Tank","2007-02-27","2007-03-26"]
["XT_4002","Assemble Tank - Slit/Collimator A","2006-07-19","2007-04-18"]
["XT_4003","Assemble Vacuum System - Slit/Collimator A","2006-07-19","2007-04-18"]
["XT_4004","Assemble Electronics - Slit/Collimator A","2006-06-20","2007-03-21"]
["XT_4005","Leak Check - Slit/Collimator A","2007-06-15","2007-07-27"]
["XT_40055","Vendor Fab/Ship Cntl/Elect -Near Hall Optic Tank","2007-03-28","2007-05-22"]
["XT_4006","Prepare Bid Pkg Jaws - Slit/Collimator A","2006-05-08","2006-05-12"]
["XT_4007","Prepare Bid Pkg Tank - Slit/Collimator A","2006-05-08","2006-05-12"]
["XT_4008","Prepare Bid Pkg Electronics - Slit/Collimator A","2006-05-08","2006-05-12"]
["XT_4009","Prepare Bid Pk Vacuum System - Slit/Collimator A","2006-05-08","2006-05-12"]
["XT_4010","Assemble Precision Hardware - Slit/Collimator A","2006-07-19","2007-04-18"]
["XT_4012","Design Review - Slit/Collimator A","2006-04-10","2006-05-05"]
["XT_4013","COMP: Design Package - Slit/Collimator A","2006-05-08","2006-05-05"]
["XT_4014","Bid Process Jaws - Slit/Collimator A","2006-05-15","2006-06-12"]
["XT_4015","Bid Process Tank - Slit/Collimator A","2006-05-15","2006-06-12"]
["XT_4016","Bid Process Electronics - Slit/Collimator A","2006-05-15","2006-06-12"]
["XT_4017","Bid Process Vacuum System - Slit/Collimator A","2006-05-15","2006-06-12"]
["XT_4018","Bid Process Precision Hardware - Slit/Col A","2006-05-15","2006-06-12"]
["XT_4019","AWARD: Contract Jaws - Slit/Collimator A","2006-06-13","2006-06-19"]
["XT_4020","AWARD: Contract Tank - Slit/Collimator A","2006-06-13","2006-06-19"]
["XT_4022","AWARD: Contract Electronics - Slit/Collimator A","2006-06-13","2006-06-19"]
["XT_4023","AWARD: Contract Vacuum System - Slit/Collimator","2006-06-13","2006-06-19"]
["XT_4024","AWARD: Contract Precision Hardware - Slit/Col A","2006-06-13","2006-06-19"]
["XT_4025","RECV: Jaws - Slit/Collimator A","2006-07-19","2006-07-18"]
["XT_4026","RECV: Tank - Slit/Collimator A","2006-07-19","2006-07-18"]
["XT_4027","RECV: Electronics - Slit/Collimator A","2006-06-20","2006-06-19"]
["XT_4028","RECV: Vacuum System - Slit/Collimator A","2006-07-19","2006-07-18"]
["XT_4029","RECV: Precision Motion Hardware - Slit/Col A","2006-07-19","2006-07-18"]
["XT_4031","Vendor Fab Jaws - Slit/Collimator A","2006-06-20","2006-07-18"]
["XT_4032","Vendor Fab Tank - Slit/Collimator A","2006-06-20","2006-07-18"]
["XT_4034","Vendor Fab Vacuum System - Slit/Collimator A","2006-06-20","2006-07-18"]
["XT_4035","Vendor Fab Precision Hardware - Slit/Col A","2006-06-20","2006-07-18"]
["XT_41","Install Spools - Far Hall Mech/Vac","2007-07-19","2007-07-25"]
["XT_410","Engineering - Slit/Collimator A","2005-10-31","2006-06-19"]
["XT_411","Specification - Comm Diagnostic Tank","2006-03-10","2006-05-04"]
["XT_412","Design - Comm Diagnostic Tank","2006-05-05","2006-10-31"]
["XT_415","Install - Comm Diagnostic Tank","2007-03-22","2007-05-16"]
["XT_416","Test - Comm Diagnostic Tank","2007-05-17","2007-06-14"]
["XT_417","COMP:  Comm Diagnostic Tank Installed & Commissi","2007-07-16","2007-07-13"]
["XT_418","Specification - Total Energy Measurement","2005-03-01","2005-05-23"]
["XT_419","Design - Total Energy Measurement","2005-05-24","2006-06-02"]
["XT_42","Install Stands - Far Hall Mech/Vac","2007-07-19","2007-07-25"]
["XT_421","Assemble - Total Energy Measurement","2006-08-30","2007-05-02"]
["XT_422","Procure Data Acquisit - Total Energy Measurement","2006-06-06","2006-08-29"]
["XT_4225","AWARD - Total Energy Measurement","2006-06-05","2006-06-05"]
["XT_423","Test - Total Energy Measurement","2007-09-25","2007-10-22"]
["XT_424","COMP:  Total Energy Measurement  Installed & Com","2007-11-06","2007-11-05"]
["XT_427","Commission - Comm Diagnostic Tank","2007-06-15","2007-07-13"]
["XT_433","Commission - Total Energy Measurement","2007-10-23","2007-11-05"]
["XT_44","Prepare Bid Pkg - Fast Controls","2006-11-22","2007-01-05"]
["XT_440","Prepare Bid Pkg - System Monochrometer","2006-11-09","2006-11-15"]
["XT_441","Bid Process - System Monochrometer","2006-11-16","2006-12-15"]
["XT_4418","Prototype - Total Energy Measurement","2005-05-24","2005-08-17"]
["XT_442","AWARD: Contract - System Monochrometer","2007-01-02","2007-01-02"]
["XT_443","Vendor Fab - System Monochrometer","2007-01-03","2007-05-24"]
["XT_4433","Visible Calibration - Direct Imager","2007-10-02","2007-10-08"]
["XT_4435","X-Ray Calibration - Direct Imager","2007-10-09","2007-10-22"]
["XT_4436","Procure Spares - Direct Imager","2006-06-06","2006-08-29"]
["XT_444","RECV: System Monochrometer","2007-05-25","2007-05-24"]
["XT_4455","Conceptual Design","2004-10-04","2005-04-18",null,"2004-10-04"]
["XT_4456","Beamline Electronics","2005-01-03","2005-01-31",null,"2005-01-03","2005-01-31"]
["XT_4458","FEL Monte Carlo","2005-02-01","2005-06-07",null,"2005-02-01"]
["XT_446","Management & Oversight - FY06-09","2005-10-03","2009-03-30"]
["XT_4486","R&D - FEL Monte Carlo","2005-10-03","2006-02-23"]
["XT_4496","R&D - Beam Line Flux Application","2006-02-24","2006-02-23"]
["XT_45","Prepare Bid Pkg Leak Detectors - Mech/Vac","2006-11-01","2006-11-07"]
["XT_452","Install - Total Energy Measurement","2007-05-03","2007-09-24"]
["XT_47","Vendor Fab/Ship - Fast Controls","2007-03-07","2007-07-26"]
["XT_472","Procure Bellows & Spools - NEH Mech/Vac - H2","2006-10-03","2006-11-29"]
["XT_478","Specification - Spectral Measurement","2005-01-03","2005-10-27",null,"2005-01-03"]
["XT_479","Design - Spectral Measurement","2005-10-28","2006-05-04"]
["XT_48","RECV: Electronics -  Fast Controls","2007-07-27","2007-07-26"]
["XT_480","Prepare Bid Pkg Precision Hardware - Slit/Col A","2006-05-08","2006-05-12"]
["XT_481","Prep Bid Data Acquisition- Spectral Measurement","2006-05-05","2006-05-11"]
["XT_482","Install - Spectral Measurement","2007-03-21","2007-05-15"]
["XT_483","Test - Spectral Measurement","2007-05-16","2007-06-13"]
["XT_484","COMP:  Spectral Measurement","2007-10-16","2007-10-15"]
["XT_485","Specification - Spatial Coherence","2006-03-10","2006-05-04"]
["XT_486","Design - Spatial Coherence","2006-05-05","2006-10-24"]
["XT_487","Prep Bid Pkg Low Energy Slit - Spatial Coherence","2006-10-25","2006-11-07"]
["XT_488","Assemble - Spatial Coherence","2007-03-22","2007-06-14"]
["XT_4888","Assemble at LLNL - Spectral Measurement","2006-09-07","2006-11-01"]
["XT_489","Install - Spatial Coherence","2007-08-06","2007-10-01"]
["XT_4898","Test at LLNL - Spectral Measurement","2006-11-02","2006-11-15"]
["XT_49","REQD: FEE Beneficial Occup - Fast Controls","2007-09-24","2007-09-21"]
["XT_490","Assemble Jaws - Slit/Collimator A","2006-07-19","2007-04-18"]
["XT_4908","Ship to SLAC - Spectral Measurement","2006-11-16","2006-12-01"]
["XT_491","Specification - Gas Attenuator","2005-05-24","2005-11-10"]
["XT_4918","Assemble at SLAC - Spectral Measurement","2006-12-04","2006-12-15"]
["XT_4928","AVAIL: Spectral Measurement","2007-03-21","2007-03-20"]
["XT_493","Design - Gas Attenuator","2005-11-11","2006-05-18"]
["XT_494","Second Design - Gas Attenuator","2006-06-19","2006-07-17"]
["XT_495","Final Design Review - Gas Attenuator","2006-07-18","2006-09-12"]
["XT_496","Prototype - Gas Attenuator","2005-05-24","2005-10-13"]
["XT_497","Prepare Bid Pkg Hardware - Gas Attenuator","2006-09-13","2006-09-26"]
["XT_498","Specification - Solid Attenuator","2005-10-03","2005-11-29"]
["XT_499","Design - Solid Attenuator","2005-11-30","2006-05-05"]
["XT_4991","Test - Spatial Coherence","2007-10-02","2007-10-29"]
["XT_4992","COMP:  Spatial Coherence","2007-11-13","2007-11-12"]
["XT_4993","Specification - Spatial Shape & Centroid Measure","2006-03-10","2006-05-04"]
["XT_4994","Design - Spatial Shape & Centroid Measure","2006-05-05","2007-03-06"]
["XT_4997","Install - Spatial Shape & Centroid Measure","2007-11-20","2008-04-29"]
["XT_4998","Test - Spatial Shape & Centroid Measure","2008-04-30","2008-05-28"]
["XT_4999","COMP:  Spatial Shape & Centroid Measurement","2008-06-26","2008-06-25"]
["XT_5","Install Isolation Valve - FEE Mech/Vac","2007-08-06","2007-08-10"]
["XT_50","Assemble FEE - Fast Controls","2007-07-27","2007-08-23"]
["XT_5000","Specification - Divergence Measurement","2006-03-10","2006-05-04"]
["XT_5001","Prepare Bid Pkg - Solid Attenuator","2006-05-15","2006-06-12"]
["XT_5002","Test - Solid Attenuator","2007-09-04","2007-10-01"]
["XT_5003","COMP:  Solid Attenuator Installed & Commissioned","2007-10-16","2007-10-15"]
["XT_5004","Install - Divergence Measurement","2007-09-25","2007-11-19"]
["XT_5005","Test - Divergence Measurement","2007-11-20","2008-01-04"]
["XT_5006","COMP:  Divergence Measurement","2008-01-22","2008-01-18"]
["XT_5009","Commission - Spatial Shape & Centroid","2008-05-29","2008-06-25"]
["XT_501","Assemble - Solid Attenuator","2006-11-02","2007-04-11"]
["XT_5011","Bid Process - Solid Attenuator","2006-06-13","2006-07-11"]
["XT_5012","Commissioning - Spatial Coherence","2007-10-30","2007-11-12"]
["XT_5014","COMP: Design - Spatial Shape & Centroid Measure","2007-03-07","2007-03-06"]
["XT_5016","Commission - Divergence Measurement","2008-01-07","2008-01-18"]
["XT_502","Install - Solid Attenuator","2007-07-09","2007-08-31"]
["XT_5021","AWARD: Contract - Solid Attenuator","2006-07-12","2006-07-11"]
["XT_5022","Commission - Solid Attenuator","2007-10-02","2007-10-15"]
["XT_503","Specification - Near Hall Optics Tank","2006-10-03","2006-11-29"]
["XT_5031","Vendor Fab/ship - Solid Attenuator","2006-07-12","2006-11-01"]
["XT_5041","RECV:  Solid Attenuator at LLNL for Assembly","2006-11-02","2006-11-01"]
["XT_505","Prep Bid Pkg Stand - Near Hall Optic Tank","2007-02-12","2007-02-26"]
["XT_506","Assemble Motion & Mech - Near Hall Optics Tank","2007-05-23","2007-07-19"]
["XT_507","Install - Near Hall Optics Tank","2007-07-20","2007-10-12"]
["XT_508","Integrate & Test - Near Hall Optics Tank","2007-10-15","2007-10-26"]
["XT_509","COMP:  Near Hall Optics Tank Install at SLAC","2007-11-12","2007-11-09"]
["XT_51","Programming FEE - Fast Controls","2007-08-24","2007-09-21"]
["XT_511","Bid Process Leak Detectors - Mech/Vac","2006-11-08","2006-12-07"]
["XT_5111","Design - Divergence Measurement","2006-05-05","2007-03-06"]
["XT_51112","Prepare Bid Pkg - Divergence Measurement","2007-03-07","2007-03-13"]
["XT_51122","Bid Process - Divergence Measurement","2007-03-14","2007-04-10"]
["XT_51132","AWARD: Contract - Divergence Measurement","2007-04-11","2007-04-11"]
["XT_51142","Vendor Fab/Ship - Divergence Measurement","2007-04-12","2007-07-06"]
["XT_51152","RECV: Material - Divergence Measurement","2007-07-09","2007-07-06"]
["XT_512","Design - Near Hall Optics Tank","2006-11-30","2007-02-09"]
["XT_5121","COMP: Design - Divergence Measurement","2007-03-07","2007-03-06"]
["XT_513","AWARD: Contract Leak Detectors - Mech/Vac","2006-12-08","2006-12-08"]
["XT_514","Vendor Fab/Ship Leak Detectors - Mech/Vac","2006-12-11","2007-01-23"]
["XT_515","RECV:  Leak Detectors - Mech/Vac","2007-01-24","2007-01-23"]
["XT_518","Test at LLNL - Spatial Coherence","2007-06-15","2007-07-13"]
["XT_519","COMP:  Design Package - Solid Attenuator","2006-05-15","2006-05-12"]
["XT_52","AVAIL: FEE Fast Controls","2007-09-24","2007-09-21"]
["XT_5200","Bid Process Production Units - Direct Imager","2006-04-07","2006-06-02"]
["XT_528","Ship to SLAC - Spatial Coherence","2007-07-16","2007-07-20"]
["XT_529","Design Review - Solid Attenuator","2006-05-08","2006-05-12"]
["XT_53","Install FEE - Fast Controls","2007-09-24","2007-11-16"]
["XT_538","Assemble - Spatial Coherence","2007-07-23","2007-08-03"]
["XT_539","COMP: Design Package - Spectral Measurement","2006-05-05","2006-05-04"]
["XT_54","Integrate FEE - Fast Controls","2007-11-19","2008-02-01"]
["XT_544","COMP: Design - Near Hall Optics Tank","2007-02-12","2007-02-09"]
["XT_545","Vendor Fab/Ship Stand - Near Hall Optic Tank","2007-03-28","2007-05-22"]
["XT_546","Assemble Control & Elect - Near Hall Optics Tank","2007-05-23","2007-07-19"]
["XT_547","Prepare Bid Pkg Greenfield Comp - Gas Attenuator","2006-09-13","2006-09-26"]
["XT_548","AVAIL: Spatial Coherence","2007-08-06","2007-08-03"]
["XT_55","Travel - FY06-09","2005-10-03","2009-03-30"]
["XT_5506","AWARD Ion Pump - NEH Mech/Vac - H2","2006-10-03","2006-10-03"]
["XT_5507","Procure Ion Pump - NEH Mech/Vac - H2","2006-10-04","2006-11-30"]
["XT_551","Specification - Tunnel Mech/Vac","2006-09-27","2006-10-10"]
["XT_552","Design - Tunnel Mech/Vac","2006-10-11","2006-12-07"]
["XT_555","Assemble - Tunnel Mech/Vac","2007-07-27","2007-09-21"]
["XT_5551","Prep Bid Pkg Prototype - Direct Imager","2006-03-24","2006-04-06"]
["XT_5552","Bid Process Prototype - Direct Imager","2006-04-07","2006-06-02"]
["XT_5553","AWARD: Contract Prototype - Direct Imager","2006-06-05","2006-06-05"]
["XT_5554","Vendor Fab/Ship Prototype Hrdware- Direct Imager","2006-06-06","2006-10-11"]
["XT_5555","RECV: Prototype Hardware - Direct Imager","2006-10-12","2006-10-11"]
["XT_5556","Prep Bid Pkg Production Units - Direct Imager","2006-03-24","2006-04-06"]
["XT_5557","Assemble - Divergence Measurement","2007-07-09","2007-08-31"]
["XT_5558","AWARD: Contract Production Units - Direct Imager","2006-06-05","2006-06-05"]
["XT_5559","Vendor Fab/Ship Production Units - Direct Imager","2006-06-06","2006-10-11"]
["XT_556","Install Isolation Valve - Tunnel Mech/Vac","2007-09-24","2008-02-01"]
["XT_5560","RECV: Production Units - Direct Imager","2006-10-12","2006-10-11"]
["XT_5567","Ship to SLAC-Divergence Measurement","2007-09-04","2007-09-10"]
["XT_557","Test - Tunnel Mech/Vac","2008-02-04","2008-03-31"]
["XT_5577","Unpack and Assemble at SLAC-Divergence Measureme","2007-09-11","2007-09-24"]
["XT_558","Commission - Tunnel Mech/Vac","2008-04-01","2008-04-28"]
["XT_5587","AVAIL: Divergence Measurement","2007-09-25","2007-09-24"]
["XT_559","COMP:  Tunnel Mech/Vac  Installed & Commiss","2008-04-29","2008-04-28"]
["XT_56","Specification - Flipper Mirror","2005-10-03","2005-10-28"]
["XT_5607","REQD: Near Hall Beneficial Occup-Divergence Meas","2007-09-25","2007-09-24"]
["XT_561","Bid Process Data Acquisition- Spectral Measure","2006-05-12","2006-06-09"]
["XT_565","Bid Process Stand - Near Hall Optic Tank","2007-02-27","2007-03-26"]
["XT_566","Assemble Tank - Near Hall Optics Tank","2007-05-23","2007-07-19"]
["XT_567","Prepare Bid Pkg Blower - Gas Attenuator","2006-09-13","2006-09-26"]
["XT_568","Commission - Near Hall Optics Tank","2007-10-29","2007-11-09"]
["XT_57","Design - Flipper Mirror","2005-10-31","2006-04-07"]
["XT_571","AWARD: Data Acquisition- Spectral Measurement","2006-06-12","2006-06-12"]
["XT_574","Commissioning - Spectral Measurement","2007-10-02","2007-10-15"]
["XT_575","AWARD: Contract Stand - Near Hall Optic Tank","2007-03-27","2007-03-27"]
["XT_576","Prepare Bid Package Tank - Near Hall Optics Tank","2007-02-12","2007-02-26"]
["XT_577","Prepare Bid Pkg Transfer Manifold - Gas Atten","2006-09-13","2006-09-26"]
["XT_578","Bid Process Vacuum - Near Hall Optics Tank","2007-02-27","2007-03-26"]
["XT_579","Vendor Fab/Ship  Vacuum - Near Hall Optics Tank","2007-03-28","2007-05-22"]
["XT_58","Engineering - Flipper Mirror","2005-10-31","2006-06-19"]
["XT_580","RECV:  Stand - Near Hall Optic Tank","2007-05-23","2007-05-22"]
["XT_581","Vendor Fab Data Acquisition-Spectral Measurement","2006-06-13","2006-08-08"]
["XT_585","RECV:   Vacuum - Near Hall Optics Tank","2007-05-23","2007-05-22"]
["XT_586","Assemble Vacuum - Near Hall Optics Tank","2007-05-23","2007-07-19"]
["XT_587","Prepare Bid Pkg Gas Purifier - Gas Attenuator","2006-09-13","2006-09-26"]
["XT_5888","AWARD: Contract Vacuum - Near Hall Optics Tank","2007-03-27","2007-03-27"]
["XT_59","Design - Flipper Mirror","2005-10-31","2006-04-07"]
["XT_591","Specification - Direct Imager","2005-02-01","2005-05-23",null,"2005-02-01"]
["XT_592","Design (5) - Direct Imager","2005-05-24","2006-03-23"]
["XT_5922","Camera - Direct Imager","2005-02-08","2005-05-31",null,"2005-02-08"]
["XT_593","Prep Bid Pkg Data Acquisition - Direct Imager","2006-03-24","2006-04-06"]
["XT_594","Assemble - Direct  Imager","2006-10-12","2007-03-21"]
["XT_595","Install - Direct Imager","2007-07-09","2007-11-28"]
["XT_596","Test - Direct Imager","2007-12-13","2008-01-28"]
["XT_597","COMP: Direct Imager","2008-02-12","2008-02-11"]
["XT_6","Test - FEE Mech/Vac","2007-08-13","2007-11-05"]
["XT_60","Engineering - Flipper Mirror","2005-10-31","2006-06-19"]
["XT_606","Assemble Stand - Near Hall Optics Tank","2007-05-23","2007-07-19"]
["XT_607","Bid Process Greenfield Comp - Gas Attenuator","2006-09-27","2006-10-24"]
["XT_61","Design Review - Flipper Mirror","2006-04-10","2006-05-05"]
["XT_611","RECV: Data Acquisition- Spectral Measurement","2006-08-09","2006-08-08"]
["XT_616","REQD: Near Hall Beneficial Occupancy","2007-07-20","2007-07-19"]
["XT_617","Bid Process Transfer Manifold - Gas Attenuator","2006-09-27","2006-10-24"]
["XT_62","COMP: Design Package - Flipper Mirror","2006-05-08","2006-05-05"]
["XT_621","REQD: FEE Beneficial Occupany - Solid Attenuator","2007-07-09","2007-07-06"]
["XT_622","COMP: Design","2006-03-24","2006-03-23"]
["XT_625","AVAIL: Tunnel Mechanical/Vacuum","2007-09-24","2007-09-21"]
["XT_626","Install Vacuum Piping - Tunnel Mech/Vac","2007-09-24","2008-02-01"]
["XT_627","Bid Process Gas Purifier - Gas Attenuator","2006-09-27","2006-10-24"]
["XT_63","Prepare Bid Pkg Jaws - Flipper Mirror","2006-05-08","2006-05-12"]
["XT_631","AVAIL:  Solid Attenuator Ready to Ship to SLAC","2007-04-12","2007-04-11"]
["XT_633","Bid Process Data Acquisition - Direct Imager","2006-04-07","2006-06-02"]
["XT_635","Visible Calibration - Direct Imager","2007-11-29","2007-12-05"]
["XT_636","Install Ion Pumps - Tunnel Mech/Vac","2007-09-24","2008-02-01"]
["XT_637","Bid Process Blower - Gas Attenuator","2006-09-27","2006-10-24"]
["XT_64","Bid Process - Fast Controls","2007-01-08","2007-03-06"]
["XT_643","AWARD: Contract Data Acquisition - Direct Imager","2006-06-05","2006-06-05"]
["XT_645","X-Ray Calibration - Direct Imager","2007-12-06","2007-12-12"]
["XT_646","Install Ion Gauges - Tunnel Mech/Vac","2007-09-24","2008-02-01"]
["XT_647","Install Stands - Tunnel Mech/Vac","2007-09-24","2008-02-01"]
["XT_65","Prepare Bid Pkg Electronics - Flipper Mirror","2006-05-08","2006-05-12"]
["XT_653","Vendor Fab/Ship Data Acquisiton - Direct Imager","2006-06-06","2006-10-11"]
["XT_654","AVAIL: Direct Imager","2007-07-09","2007-07-06"]
["XT_655","REQD: FEE Beneficial Occupancy","2007-07-09","2007-07-06"]
["XT_656","Install Spools - Tunnel Mech/Vac","2007-09-24","2008-02-01"]
["XT_657","Bid Process Low Energy Slit - Spatial Coherence","2006-11-08","2006-12-07"]
["XT_66","Prepare Bid Pk Vacuum System - Flipper Mirror","2006-05-08","2006-05-12"]
["XT_660","Test - Near Hall Mech/Vac - H1","2007-04-25","2007-05-08"]
["XT_6600","Prep Bid Pkg Prototype - Indirect Imager","2006-03-24","2006-04-06"]
["XT_6601","Bid Process Prototype - Indirect Imager","2006-04-07","2006-06-02"]
["XT_6602","AWARD: Contract Prototype - Indirect Imager","2006-06-05","2006-06-05"]
["XT_6603","Vendor Fab/Ship Prototype Hrdware-Indirect Image","2006-06-06","2006-08-29"]
["XT_6604","RECV: Prototype Hardware - Indirect Imager","2006-08-30","2006-08-29"]
["XT_6605","Prep Bid Pkg Production Units - Indirect Imager","2006-03-24","2006-04-06"]
["XT_6606","Bid Process Production Units - Indirect Imager","2006-04-07","2006-06-02"]
["XT_6607","AWARD: Contract Production Units - Indirect Imag","2006-06-05","2006-06-05"]
["XT_6608","Vendor Fab/Ship Production Units - Indirect Imag","2006-06-06","2006-08-29"]
["XT_6609","RECV: Production Units -  Indirect Imager","2006-08-30","2006-08-29"]
["XT_661","Specification - Far Hall Mech/Vac - H1","2006-08-15","2006-09-12"]
["XT_662","Design - Far Hall Mech/Vac - H1","2006-09-13","2006-12-07"]
["XT_663","RECV: Data Acquisition- Direct Imager","2006-10-12","2006-10-11"]
["XT_665","Assemble - Far Hall Mech/Vac","2007-06-20","2007-07-18"]
["XT_666","Install Isolation Valve - Far Hall Mech/Vac","2007-07-19","2007-07-25"]
["XT_667","Test - Far Hall Mech/Vac - H1","2007-07-26","2007-08-08"]
["XT_6670","Prep Bid Pkg Turbo System - FEE Diagnostic Tank","2007-07-23","2007-07-27"]
["XT_6671","Bid Process Turbo System - FEE Diagnostic Tank","2007-07-30","2007-08-24"]
["XT_6672","AWARD: Contract Turbo System - FEE Diagnostic Tn","2007-08-27","2007-08-27"]
["XT_6673","Vendor Fab/Ship Turbo System - FEE Diagnostic Ta","2007-08-28","2007-11-20"]
["XT_6674","RECV:  Turbo System - FEE Diagnostic Tank","2007-11-21","2007-11-20"]
["XT_6675","Prep Bid Pkg Scroll Dry Pump-FEE Diagnostic Tnk","2007-07-23","2007-07-27"]
["XT_6676","Bid Process Scroll Dry Pump-FEE Diagnostic Tnk","2007-07-30","2007-08-24"]
["XT_6677","AWARD: Contract Scroll Dry Pump-FEE DiagnosticTn","2007-08-27","2007-08-27"]
["XT_6678","Vendor Ship Scroll Dry Pump-FEE Diagnostic Tank","2007-08-28","2007-11-20"]
["XT_6679","RECV: Scroll Dry Pump-FEE Diagnostic Tnk","2007-11-21","2007-11-20"]
["XT_668","Commission - Far Hall Mech/Vac - H1","2007-08-09","2007-08-22"]
["XT_6680","Prep Bid Pkg Imager Stages - FEE Diagnostic Tank","2007-07-23","2007-07-27"]
["XT_6681","Bid Process  Imager Stages - FEE Diagnostic Tank","2007-07-30","2007-08-24"]
["XT_6682","AWARD: Contract  Imager Stages - FEE Diagnostic","2007-08-27","2007-08-27"]
["XT_6683","Vendor Fab/Ship Imager Stages - FEE Diagnostic T","2007-08-28","2007-11-20"]
["XT_6684","RECV:   Imager Stages - FEE Diagnostic Tank","2007-11-21","2007-11-20"]
["XT_6685","Prep Bid Pkg Stand - FEE Diagnostic Tank","2007-07-23","2007-07-27"]
["XT_6686","Bid Process Stand - FEE Diagnostic Tank","2007-07-30","2007-08-24"]
["XT_6687","AWARD: Contract Stand - FEE Diagnostic Tank","2007-08-27","2007-08-27"]
["XT_6688","Vendor Fab/Ship Stand - FEE Diagnostic Tank","2007-08-28","2007-11-20"]
["XT_6689","RECV:  Stand - FEE Diagnostic Tank","2007-11-21","2007-11-20"]
["XT_669","COMP:  Far Hall Mech/Vac - H1 Installed & Commis","2007-08-23","2007-08-22"]
["XT_6690","Prep Bid Pkg Motor Driver - FEE Diagnostic Tank","2007-07-23","2007-07-27"]
["XT_6691","Bid Process Motor Driver - FEE Diagnostic Tank","2007-07-30","2007-08-24"]
["XT_6692","AWARD: Contract Motor Driver - FEE Diagnostic Ta","2007-08-27","2007-08-27"]
["XT_6693","Vendor Fab/Ship Motor Driver -FEE Diagnostic Tnk","2007-08-28","2007-11-20"]
["XT_6694","RECV: Motor Driver - FEE Diagnostic Tank","2007-11-21","2007-11-20"]
["XT_6695","Prep Bid Pkg EPICS IF - FEE Diagnostic Tank","2007-07-23","2007-07-27"]
["XT_6696","Bid Process EPICS IF - FEE Diagnostic Tank","2007-07-30","2007-08-24"]
["XT_6697","AWARD: Contract EPICS IF - FEE Diagnostic Tank","2007-08-27","2007-08-27"]
["XT_6698","Vendor Fab/Ship EPICS IF - FEE Diagnostic Tank","2007-08-28","2007-11-20"]
["XT_6699","RECV: EPICS IF - FEE Diagnostic Tank","2007-11-21","2007-11-20"]
["XT_6700","Prep Bid Pk Misc Racks/Chases-FEE Diagnostic Tnk","2007-07-23","2007-07-27"]
["XT_6701","Bid Process Misc Racks/Chases-FEE Diagnostic Tnk","2007-07-30","2007-08-24"]
["XT_6702","AWARD: Contract Misc Racks/Chases-FEE Diagnostic","2007-08-27","2007-08-27"]
["XT_6703","Vendor Fab/Ship Misc Racks/Chases-FEE Diagnostic","2007-08-28","2007-11-20"]
["XT_6704","RECV:  Misc Racks/Chases-FEE Diagnostic Tnk","2007-11-21","2007-11-20"]
["XT_671","Specification - Near Hall Mech/Vac - H2","2006-01-26","2006-04-20"]
["XT_672","Design - Near Hall Mech/Vac - H2","2006-04-21","2006-08-14"]
["XT_674","Assemble - NH Mech/Vac - H2","2007-03-21","2007-04-17"]
["XT_676","Test - Near Hall Mech/Vac - H2","2007-04-25","2007-05-08"]
["XT_677","Commission - Near Hall Mech/Vac - H2","2007-05-09","2007-06-06"]
["XT_678","COMP:  Near Hall Mech/Vac - H2","2007-06-07","2007-06-07"]
["XT_680","Commission - Near Hall Mech/Vac - H1","2007-05-09","2007-06-06"]
["XT_682","Procure Hand Isolation Valve-Far Hall Mec/Vac-H1","2006-12-08","2007-02-20"]
["XT_683","Procure Gate Isolation Valve-Far Hall Mec/Vac-H1","2006-12-08","2007-02-20"]
["XT_684","AVAIL: Near Hall Mech/Vac - H2","2007-04-18","2007-04-17"]
["XT_685","Procure Bellows & Spools - Far Hall Mech/Vac","2006-12-08","2007-02-20"]
["XT_686","COMP: Design - Spatial Coherence","2006-10-25","2006-10-24"]
["XT_687","AWARD: Low Energy Slit - Spatial Coherence","2006-12-08","2006-12-08"]
["XT_688","Procure Bellows & Spools - Far Hall Mech/Vac","2006-12-08","2007-02-20"]
["XT_69","Bid Process Jaws - Flipper Mirror","2006-05-15","2006-06-12"]
["XT_691","Specification - Indirect Imager","2005-02-01","2005-05-23",null,"2005-02-01"]
["XT_692","Design - Indirect Imager","2005-05-24","2006-03-23"]
["XT_694","Assemble - Indirect Imager","2006-08-30","2007-02-06"]
["XT_695","Install - Indirect Imager","2007-07-09","2007-10-01"]
["XT_696","Test - Indirect Imager","2007-10-23","2007-11-19"]
["XT_697","COMP:  Indirect Imager Installed & Commissioned","2007-12-06","2007-12-05"]
["XT_699","Procure Hand Isolation Valve - Far Hall Mech/Vac","2006-12-08","2007-02-20"]
["XT_7","Commission - FEE Mech/Vac","2007-11-06","2008-01-18"]
["XT_70","Specification - Far Hall Mech/Vac - H2","2006-08-15","2006-09-12"]
["XT_700","Assemble - NH Mech/Vac - H1","2007-03-21","2007-04-03"]
["XT_7000","Specification - Slit/Collimator B","2006-10-03","2006-10-30"]
["XT_7001","Design - Slit/Collimator B","2006-10-31","2007-04-09"]
["XT_70011","REQD: FEE Beneficial Occupancy","2008-04-21","2008-04-18"]
["XT_7002","Design Review - Slit/Collimator B","2007-04-10","2007-05-07"]
["XT_7003","COMP: Design Package - Slit/Collimator B","2007-05-08","2007-05-07"]
["XT_7004","Prepare Bid Pkg Jaws - Slit/Collimator B","2007-05-08","2007-05-14"]
["XT_7005","Prepare Bid Pkg Tank - Slit/Collimator B","2007-05-08","2007-05-14"]
["XT_7006","Prepare Bid Pkg Electronics - Slit/Collimator B","2007-05-08","2007-05-14"]
["XT_7007","Prepare Bid Pk Vacuum System - Slit/Collimator B","2007-05-08","2007-05-14"]
["XT_7008","Prepare Bid Pkg Precision Hardware - Slit/Col B","2007-05-08","2007-05-14"]
["XT_7009","Bid Process Jaws - Slit/Collimator B","2007-05-15","2007-06-12"]
["XT_7010","Bid Process Tank - Slit/Collimator B","2007-05-15","2007-06-12"]
["XT_7011","Bid Process Electronics - Slit/Collimator B","2007-05-15","2007-06-12"]
["XT_7012","Bid Process Vacuum System - Slit/Collimator B","2007-05-15","2007-06-12"]
["XT_7013","Bid Process Precision Hardware - Slit/Col B","2007-05-15","2007-06-12"]
["XT_7014","AWARD: Contract Jaws - Slit/Collimator B","2007-06-13","2007-06-19"]
["XT_7015","AWARD: Contract Tank - Slit/Collimator B","2007-06-13","2007-06-19"]
["XT_7016","AWARD: Contract Electronics - Slit/Collimator B","2007-06-13","2007-06-19"]
["XT_7017","AWARD: Contract Vacuum System - Slit/Collimator","2007-06-13","2007-06-19"]
["XT_7018","AWARD: Contract Precision Hardware - Slit/Col B","2007-06-13","2007-06-19"]
["XT_7019","Vendor Fab Jaws - Slit/Collimator B","2007-06-20","2007-07-18"]
["XT_702","Procure Vacuum Hardware - Far Hall Mech/Vac - H1","2006-12-08","2007-02-20"]
["XT_7020","Vendor Fab Tank - Slit/Collimator B","2007-06-20","2007-07-18"]
["XT_7022","Vendor Fab Vacuum System - Slit/Collimator B","2007-06-20","2007-07-18"]
["XT_7023","Vendor Fab Precision Hardware - Slit/Col B","2007-06-20","2007-07-18"]
["XT_7024","RECV Jaws - Slit/Collimator B","2007-07-19","2007-07-18"]
["XT_7025","RECV Tank - Slit/Collimator B","2007-07-19","2007-07-18"]
["XT_7026","RECV Electronics - Slit/Collimator B","2007-06-20","2007-06-19"]
["XT_7027","RECV Vacuum System - Slit/Collimator B","2007-07-19","2007-07-18"]
["XT_7028","RECV Precision Motion Hardware - Slit/Col B","2007-07-19","2007-07-18"]
["XT_7029","Assemble Tank - Slit/Collimator B","2007-07-19","2008-04-18"]
["XT_7030","Assemble Vacuum System - Slit/Collimator B","2007-07-19","2008-04-18"]
["XT_7031","Assemble Electronics - Slit/Collimator B","2007-06-20","2008-03-21"]
["XT_7032","Assemble Precision Hardware - Slit/Collimator B","2007-07-19","2008-04-18"]
["XT_7033","Assemble Jaws - Slit/Collimator B","2007-07-19","2008-04-18"]
["XT_7034","Install - Slit/Collimator B","2008-04-21","2008-06-16"]
["XT_7035","Leak Check - Slit/Collimator B","2008-06-17","2008-09-10"]
["XT_7036","Test Beam Line - Slit/Collimator B","2008-09-11","2008-11-05"]
["XT_7037","Commission - Slit/Collimator B","2008-11-06","2009-03-12"]
["XT_7038","COMP:  Slit/Collimator B  Installed & Commiss","2009-03-13","2009-03-12"]
["XT_704","AVAIL: Indirect Imager Ready to Ship to SLAC","2007-07-09","2007-07-06"]
["XT_7040","Engineering - Slit/Collimator B","2006-10-31","2007-06-19"]
["XT_7046","Fab/Assemble/Test - Const $ - Slit/Col","2008-09-11","2009-02-12"]
["XT_707","Vendor Fab Low Energy Slit - Spatial Coherence","2006-12-11","2007-03-21"]
["XT_71","Design - Far Hall Mech/Vac - H2","2006-09-13","2006-12-07"]
["XT_710","AVAIL: Near Hall Mech/Vac - H1","2007-04-04","2007-04-03"]
["XT_711","Prepare Bid Pkg Tank - Flipper Mirror","2006-05-08","2006-05-12"]
["XT_712","COMP: Design Package - Indirect Imager","2006-03-24","2006-03-23"]
["XT_7122","Prepare Bid Pkg Precision Hardware - Flipper Mir","2006-05-08","2006-05-12"]
["XT_717","RECV: Low Energy Slit - Spatial Coherence","2007-03-22","2007-03-21"]
["XT_72","Bid Process Vacuum System - Flipper Mirror","2006-05-15","2006-06-12"]
["XT_73","Assemble - Far Hall Mech/Vac - H2","2007-06-20","2007-07-18"]
["XT_730","COMP:  Near Hall Mech/Vac - H1","2007-06-07","2007-06-07"]
["XT_736","Commission - Direct Imager","2008-01-29","2008-02-11"]
["XT_74","Install Ion Pumps - Far Hall Mech/Vac - H2","2007-07-19","2007-07-25"]
["XT_746","Commission - Indirect Imager","2007-11-20","2007-12-05"]
["XT_75","Test - Far Hall Mech/Vac - H2","2007-07-26","2007-08-08"]
["XT_7512","Vendor Fab Vacuum System - Flipper Mirror","2006-06-20","2006-07-18"]
["XT_76","Commission - Far Hall Mech/Vac - H2","2007-08-09","2007-08-22"]
["XT_77","COMP:  Far Hall Mech/Vac - H2","2007-08-23","2007-08-22"]
["XT_7700","COMP: Design Package - Ion Pumped Tank","2007-07-23","2007-07-20"]
["XT_7701","Prep Bid Pkg Tank - Ion Pumped Tank","2007-07-23","2007-07-27"]
["XT_7702","Bid Process Tank - Ion Pumped Tank","2007-07-30","2007-08-24"]
["XT_7703","AWARD: Contract Tank - Ion Pumped Tank","2007-08-27","2007-08-27"]
["XT_7704","Vendor Fab/Ship Tank - Ion Pumped Tank","2007-08-28","2007-11-20"]
["XT_7705","RECV:  Tank - Ion Pumped Tank","2007-11-21","2007-11-20"]
["XT_7706","Prep Bid Pkg Ion Pump - Ion Pumped Tank","2007-07-23","2007-07-27"]
["XT_7707","Bid Process Ion Pump - Ion Pumped Tank","2007-07-30","2007-08-24"]
["XT_7708","AWARD: Contract Ion Pump - Ion Pumped Tank","2007-08-27","2007-08-27"]
["XT_7709","Vendor Fab/Ship Ion Pump - Ion Pumped Tank","2007-08-28","2007-11-20"]
["XT_771","Specification - Near Hall Mech/Vac - H3","2006-01-26","2006-04-20"]
["XT_7710","RECV:  Ion Pump - Ion Pumped Tank","2007-11-21","2007-11-20"]
["XT_7711","Prep Bid Pkg  Misc - Ion Pumped Tank","2007-07-23","2007-07-27"]
["XT_7712","Bid Process Misc - Ion Pumped Tank","2007-07-30","2007-08-24"]
["XT_7713","AWARD: Contract Misc - Ion Pump Tnk","2007-08-27","2007-08-27"]
["XT_7714","Vendor Ship Misc - Ion Pumped Tank","2007-08-28","2007-11-20"]
["XT_7715","RECV:  Misc - Ion Pumped Tank","2007-11-21","2007-11-20"]
["XT_7716","Prep Bid Pkg Imager Stages - Ion Pumped Tank","2007-07-23","2007-07-27"]
["XT_7717","Bid Process  Imager Stages - Ion Pumped Tank","2007-07-30","2007-08-24"]
["XT_7718","AWARD: Contract  Imager Stages - Ion Pumped Tank","2007-08-27","2007-08-27"]
["XT_7719","Vendor Fab/Ship Imager Stages - Ion Pumped Tank","2007-08-28","2007-11-20"]
["XT_772","Design - Near Hall Mech/Vac - H3","2006-04-21","2006-08-14"]
["XT_7720","RECV:   Imager Stages - Ion Pumped Tank","2007-11-21","2007-11-20"]
["XT_7721","Prep Bid Pkg Stand - Ion Pumped Tank","2007-07-23","2007-07-27"]
["XT_7722","Bid Process Stand - Ion Pumped Tank","2007-07-30","2007-08-24"]
["XT_7723","AWARD: Contract Stand - Ion Pumped Tank","2007-08-27","2007-08-27"]
["XT_7724","Vendor Fab/Ship Stand - Ion Pumped Tank","2007-08-28","2007-11-20"]
["XT_7725","RECV:  Stand - Ion Pumped Tank","2007-11-21","2007-11-20"]
["XT_7726","Prep Bid Pkg Motor Driver - Ion Pumped Tank","2007-07-23","2007-07-27"]
["XT_7727","Bid Process Motor Driver - Ion Pumped Tank","2007-07-30","2007-08-24"]
["XT_7728","AWARD: Contract Motor Driver - Ion Pumped Tank","2007-08-27","2007-08-27"]
["XT_7729","Vendor Fab/Ship Motor Driver -Ion Pumped Tank","2007-08-28","2007-11-20"]
["XT_773","REQD: Near Hall Beneficial Occup - Mech/Vac","2007-03-21","2007-03-20"]
["XT_7730","RECV: Motor Driver - Ion Pumped Tank","2007-11-21","2007-11-20"]
["XT_7731","Prep Bid Pkg EPICS IF - Ion Pumped Tank","2007-07-23","2007-07-27"]
["XT_7732","Bid Process EPICS IF - Ion Pumped Tank","2007-07-30","2007-08-24"]
["XT_7733","AWARD: Contract EPICS IF - Ion Pumped Tank","2007-08-27","2007-08-27"]
["XT_7734","Vendor Fab/Ship EPICS IF - Ion Pumped Tank","2007-08-28","2007-11-20"]
["XT_7735","RECV: EPICS IF - Ion Pumped Tank","2007-11-21","2007-11-20"]
["XT_7736","Prep Bid Pk Misc Racks/Chases-Ion Pumped Tank","2007-07-23","2007-07-27"]
["XT_7737","Bid Process Misc Racks/Chases-Ion Pumped Tank","2007-07-30","2007-08-24"]
["XT_7738","AWARD: Contract Misc Racks/Chases-Ion Pumped Tan","2007-08-27","2007-08-27"]
["XT_7739","Vendor Fab/Ship Misc Racks/Chases-Ion Pumped Tan","2007-08-28","2007-11-20"]
["XT_774","Assemble - NH Mech/Vac - H3","2007-03-21","2007-04-17"]
["XT_7740","RECV:  Misc Racks/Chases-Ion Pumped Tank","2007-11-21","2007-11-20"]
["XT_7741","COMP: Design - Comm Diagnostic Tank","2006-11-01","2006-10-31"]
["XT_7742","Prep Bid Pkg Tank - Comm Diagnostic Tank","2006-11-01","2006-11-07"]
["XT_7743","Prep Bid Pkg Scroll Dry Pump-Comm Diagnostic Tnk","2006-11-01","2006-11-07"]
["XT_7744","Prep Bid Pkg Turbo System - Comm Diagnostic Tank","2006-11-01","2006-11-07"]
["XT_7745","Prep Bid Pkg Imager Stages - Comm Diagnostic Tan","2006-11-01","2006-11-07"]
["XT_7746","Prep Bid Pkg Stand - Comm Diagnostic Tank","2006-11-01","2006-11-07"]
["XT_7747","Prep Bid Pkg Motor Driver - Comm Diagnostic Tank","2006-11-01","2006-11-07"]
["XT_7748","Prep Bid Pkg EPICS IF - Comm Diagnostic Tank","2006-11-01","2006-11-07"]
["XT_7749","Prep Bid Pk 2 Axis Rail Adjus-Comm Diagnostic Ta","2006-11-01","2006-11-07"]
["XT_775","Install Vacuum Piping - NH Mech/Vac - H3","2007-04-18","2007-04-24"]
["XT_7751","Bid Process Tank - Comm Diagnostic Tank","2006-11-08","2006-12-07"]
["XT_7752","Bid Process Scroll Dry Pump-Comm Diagnostic Tank","2006-11-08","2006-12-07"]
["XT_7753","Bid Process Turbo System - Comm Diagnostic Tank","2006-11-08","2006-12-07"]
["XT_7754","Bid Process  Imager Stages - Comm Diagnostic Tan","2006-11-08","2006-12-07"]
["XT_7755","Bid Process Stand - Comm Diagnostic Tank","2006-11-08","2006-12-07"]
["XT_7756","Bid Process Motor Driver - Comm Diagnostic Tank","2006-11-08","2006-12-07"]
["XT_7757","Bid Process EPICS IF - Comm Diagnostic Tank","2006-11-08","2006-12-07"]
["XT_7758","Bid Process 2 Axis Rail Adjus-Comm Diagnostic Ta","2006-11-08","2006-12-07"]
["XT_7759","AWARD: Contract Tank - Comm Diagnostic Tank","2006-12-08","2006-12-08"]
["XT_776","Test - Near Hall Mech/Vac - H3","2007-04-25","2007-05-08"]
["XT_7760","AWARD: Contract Scroll Dry Pump Comm Diagnostic","2006-12-08","2006-12-08"]
["XT_7761","AWARD: Contract Turbo System - Comm Diagnostic T","2006-12-08","2006-12-08"]
["XT_7762","AWARD: Contract  Imager Stages - Comm Diagnostic","2006-12-08","2006-12-08"]
["XT_7763","AWARD: Contract Stand - Comm Diagnostic Tank","2006-12-08","2006-12-08"]
["XT_7764","AWARD: Contract Motor Driver - Comm Diagnostic T","2006-12-08","2006-12-08"]
["XT_7765","AWARD: Contract EPICS IF - Comm Diagnostic Tank","2006-12-08","2006-12-08"]
["XT_7766","AWARD: Contract 2 Axis Rail Adjustment-Comm Diag","2006-12-08","2006-12-08"]
["XT_7767","Vendor Fab/Ship Tank - Comm Diagnostic Tank","2006-12-11","2007-03-21"]
["XT_777","Commission - Near Hall Mech/Vac - H3","2007-05-09","2007-06-06"]
["XT_7775","Assemble - Comm Diagnostic Tank","2006-11-08","2007-03-20"]
["XT_7776","RECV:  Tank - Comm Diagnostic Tank","2007-03-22","2007-03-21"]
["XT_7777","RECV: Scroll Dry Pump - Comm Diagnostic Tank","2006-12-11","2006-12-08"]
["XT_7778","RECV:  Turbo System - Comm Diagnostic Tank","2006-12-11","2006-12-08"]
["XT_7779","RECV:   Imager Stages - Comm Diagnostic Tank","2006-12-11","2006-12-08"]
["XT_778","COMP:  Near Hall Mech/Vac - H3","2007-06-07","2007-06-07"]
["XT_7780","RECV:  Stand - Comm Diagnostic Tank","2006-12-11","2006-12-08"]
["XT_77801","AWARD: Contract Vacuum System - Flipper Mirror","2006-06-13","2006-06-19"]
["XT_7781","RECV: Motor Driver - Comm Diagnostic Tank","2006-12-11","2006-12-08"]
["XT_7782","RECV: EPICS IF - Comm Diagnostic Tank","2006-12-11","2006-12-08"]
["XT_7783","RECV:  2 Axis Rail Adjust-Comm Diagnostic Tank","2006-12-11","2006-12-08"]
["XT_77885","AWARD: Contract Precision Hardware - Flipper Mir","2006-06-13","2006-06-19"]
["XT_7789","RECV: Material -Spatial Shape & Centroid Measure","2007-07-09","2007-07-06"]
["XT_778956","Vendor Fab Jaws - Flipper Mirror","2006-06-20","2006-07-18"]
["XT_7793","REQD: Near Hall Beneficial Occup -Comm Diag Tank","2007-03-21","2007-03-21"]
["XT_78","Specification - Far Hall Mech/Vac - H3","2006-08-15","2006-09-12"]
["XT_780","Prepare Bid Pkg -Spatial Shape & Centroid Measur","2007-03-07","2007-03-13"]
["XT_7801","Procure Production Unit-Total Energy Measurement","2006-06-05","2006-08-28"]
["XT_781","Bid Process - Spatial Shape & Centroid Measure","2007-03-14","2007-04-10"]
["XT_7813","Vendor Fab Precision Hardware - Flipper Mirror","2006-06-20","2006-07-18"]
["XT_7814","RECV Jaws - Flipper Mirror","2006-07-19","2006-07-18"]
["XT_7816","RECV Tank - Flipper Mirror","2006-07-19","2006-07-18"]
["XT_7817","Assemble Tank - Flipper Mirror","2006-07-19","2007-05-16"]
["XT_7818","Assemble Electronics - Flipper Mirror","2006-06-20","2007-04-18"]
["XT_7819","Assemble Jaws - Flipper Mirror","2006-07-19","2007-05-16"]
["XT_782","AWARD: Contract - Spatial Shape & Centroid Measu","2007-04-11","2007-04-11"]
["XT_7820","Install - Flipper Mirror","2007-06-20","2007-08-15"]
["XT_7821","Leak Check - Flipper Mirror","2007-08-16","2007-09-13"]
["XT_7822","Test Beam Line - Flipper Mirror","2007-09-14","2007-10-11"]
["XT_7823","Fab/Assemble/Test - Const $ - Flipper Mirror","2007-07-09","2007-11-28"]
["XT_7824","Commission - Flipper Mirror","2007-10-12","2008-02-22"]
["XT_7825","COMP:  Flipper Mirror","2008-02-25","2008-02-22"]
["XT_783","Vendor Fab/Ship - Spatial Shape & Centroid Measu","2007-04-12","2007-07-06"]
["XT_784","AVAIL: Near Hall Mech/Vac H3","2007-04-18","2007-04-17"]
["XT_785","Install Ion Pumps - NH Mech/Vac - H3","2007-04-18","2007-04-24"]
["XT_786","Ship to SLAC-Spatial Shape & Centroid Measure","2007-10-30","2007-11-05"]
["XT_787","Unpack and Assemble at SLAC-Spatial Shape & Cent","2007-11-06","2007-11-19"]
["XT_788","AVAIL: Spatial Shape & Centroid Measure","2007-11-20","2007-11-19"]
["XT_789","Bid Process Tank - Flipper Mirror","2006-05-15","2006-06-12"]
["XT_79","Design - Far Hall Mech/Vac - H3","2006-09-13","2006-12-07"]
["XT_7924","Bid Process Electronics - Flipper Mirror","2006-05-15","2006-06-12"]
["XT_7955","Bid Process Precision Hardware - Flipper Mirror","2006-05-15","2006-06-12"]
["XT_7956","AWARD: Contract Jaws - Flipper Mirror","2006-06-13","2006-06-19"]
["XT_7957","AWARD: Contract Tank - Flipper Mirror","2006-06-13","2006-06-19"]
["XT_7958","AWARD: Contract Electronics - Flipper Mirror","2006-06-13","2006-06-19"]
["XT_798","REQD: Near Hall Benefic Occup-Spatial & Centroid","2007-11-20","2007-11-19"]
["XT_8","COMP:  FEE Mechanical/Vacuum Installed & Commiss","2008-01-22","2008-01-18"]
["XT_80","Vendor Fab Tank - Flipper Mirror","2006-06-20","2006-07-18"]
["XT_800","Test Beam Line - Slit/Collimator A","2007-07-30","2007-09-10"]
["XT_8000","Prep Bid Package Vacuum - Near Hall Optics Tank","2007-02-12","2007-02-26"]
["XT_8001","Bid Process Tank - Near Hall Optics Tank","2007-02-27","2007-03-26"]
["XT_8002","Commission - Slit/Collimator A","2007-09-11","2007-11-05"]
["XT_8003","Vendor Fab/Ship Tank - Near Hall Optics Tank","2007-03-28","2007-05-22"]
["XT_8004","AWARD: Contract Tank - Near Hall Optics Tank","2007-03-27","2007-03-27"]
["XT_8007","RECV: Tank - Near Hall Optics Tank","2007-05-23","2007-05-22"]
["XT_801","COMP:  Slit/Collimator A","2007-11-29","2007-11-28"]
["XT_805","Install Ion Gauges - NH Mech/Vac - H3","2007-04-18","2007-04-24"]
["XT_81","Assemble - Far Hall Mech/Vac - H3","2007-06-20","2007-06-26"]
["XT_810","Install - Slit/Collimator A","2007-04-19","2007-06-14"]
["XT_815","Install Stands - NH Mech/Vac - H3","2007-04-18","2007-04-24"]
["XT_82","Install Ion Pumps - Far Hall Mech/Vac - H3","2007-06-27","2007-07-03"]
["XT_820","Fab/Assemble/Test - Const $ - Slit/Col","2007-07-09","2007-11-28"]
["XT_83","Test - Far Hall Mech/Vac - H3","2007-09-07","2007-09-20"]
["XT_84","Commission - Far Hall Mech/Vac - H3","2007-09-21","2007-10-04"]
["XT_85","COMP:  Far Hall Mech/Vac - H3  Installed & Commi","2007-10-05","2007-10-04"]
["XT_86","RECV Electronics - Flipper Mirror","2006-06-20","2006-06-19"]
["XT_87","RECV Vacuum System - Flipper Mirror","2006-07-19","2006-07-18"]
["XT_88","RECV Precision Motion Hardware - Flipper Mirror","2006-07-19","2006-07-18"]
["XT_8842","Prep Bid Pkg Grating - Spectral Measurement","2006-05-05","2006-05-11"]
["XT_8845","Prep Bid Pkg Low Energy - Spectral Measurement","2006-05-05","2006-05-11"]
["XT_8846","Prep Bid Rails & Stages - Spectral Measurement","2006-05-05","2006-05-11"]
["XT_8852","Bid Process Grating - Spectral Measurement","2006-05-12","2006-06-09"]
["XT_8855","Prep Bid Pkg High Energy - Spectral Measurement","2006-05-05","2006-05-11"]
["XT_8856","Bid Process Rails & Stages -Spectral Measurement","2006-05-12","2006-06-09"]
["XT_8862","AWARD: Grating - Spectral Measurement","2006-06-12","2006-06-12"]
["XT_8865","Bid Process Low Energy - Spectral Measurement","2006-05-12","2006-06-09"]
["XT_8866","AWARD: Rails & Stages - Spectral Measurement","2006-06-12","2006-06-12"]
["XT_8872","Vendor Fab Grating - Spectral Measurement","2006-06-13","2006-08-08"]
["XT_8875","AWARD: Low Energy - Spectral Measurement","2006-06-12","2006-06-12"]
["XT_8876","Vendor Fab Rails & Stages - Spectral Measurement","2006-06-13","2006-08-08"]
["XT_8882","RECV: Grating - Spectral Measurement","2006-08-09","2006-08-08"]
["XT_8885","RECV:  Low Energy - Spectral Measurement","2006-08-09","2006-08-08"]
["XT_8886","RECV: Rails & Stages - Spectral Measurement","2006-08-09","2006-08-08"]
["XT_8895","Bid Process - Spectral Measurement","2006-05-12","2006-06-09"]
["XT_89","Procure Vacuum Hardware - Far Hall Mech/Vac","2006-12-08","2007-02-20"]
["XT_8905","AWARD: Contract - Spectral Measurement","2006-06-12","2006-06-12"]
["XT_8915","Vendor Fab High Energy - Spectral Measurement","2006-06-13","2006-09-06"]
["XT_8925","RECV: High Energy - Spectral Measurement","2006-09-07","2006-09-06"]
["XT_8935","Vendor Fab Low Energy - Spectral Measurement","2006-06-13","2006-08-08"]
["XT_899","Assemble -Spatial Shape & Centroid Measure","2007-07-09","2007-10-29"]
["XT_9","Specification - Electron Dump Mech/Vac","2006-10-03","2006-10-16"]
["XT_90","Assemble Vacuum System - Flipper Mirror","2006-07-19","2007-05-16"]
["XT_91","AVAIL: Far Hall Mech/Vac Ready to Install SLAC","2007-06-27","2007-06-26"]
["XT_92","Assemble Precision Hardware - Flipper Mirror","2006-07-19","2007-05-16"]
["XT_94","Assemble Pipe - Electron Dump Mech/Vac","2007-02-06","2007-02-12"]
["XT_95","Install Vacuum Pipe - Electron Dump Mech/Vac","2007-08-10","2007-08-16"]
["XT_96","Test Pipe - Electron Dump Mech/Vac","2007-08-17","2007-08-30"]
["XT_97","Commission - Electron Dump Mech/Vac","2008-01-22","2008-02-19"]
["XT_98","COMP:  Electron Dump Mech/Vac Install & Commissi","2008-02-20","2008-02-19"]
["XT_99","Beam Simulation - FY-05","2005-02-01","2005-09-29",null,"2005-02-01"]
["XT_991","Specification - FEE Diagnostic Tank","2006-11-09","2007-01-23"]
["XT_992","Design - FEE Diagnostic Tank","2007-01-24","2007-07-20"]
["XT_993","Procure Computer - FEE Diagnostic Tank","2007-07-23","2007-10-15"]
["XT_994","Assemble - FEE Diagnostic Tank","2007-11-21","2008-04-30"]
["XT_995","Install - FEE Diagnostic Tank","2008-05-01","2008-07-25"]
["XT_996","Test - FEE Diagnostic Tank","2008-07-28","2008-08-22"]
["XT_997","COMP:  FEE Diagnostic Tank","2008-09-09","2008-09-08"]
["XT_LOE","X-ray LOE Complete","2009-03-31","2009-03-30"]
["XT_M1","COMP: Design Package - Electron Dump Mech/Vac","2006-11-14","2006-11-13"]
["XT_M2","COMP: Design Package - FEE Mech/Vac","2006-01-26","2006-01-25"]
[]
[null,"Total of 13206 activities selected.",null,null,"Type key: ",null,"0=Task, 1=Independent, 2=Meeting, 3=SM, 4=FM, 5=Hammock, 6=WBS, 7=Topic "]

{"sheet":"PriorMonth","index":2,"n_rows":1317,"n_cols":23,"rows_kept":1317,"cut":false,"hidden":true,"merged":[[2,7,2,11],[2,12,2,18],[0,0,0,2],[0,3,0,5],[1,0,1,2],[1,3,1,5],[3,0,3,5],[3,7,3,8],[3,9,5,9],[3,10,3,11],[5,0,5,5],[4,0,4,5],[4,10,5,10],[4,11,5,11],[3,17,3,18],[4,17,5,17],[4,18,5,18],[4,16,5,16],[4,15,5,15],[3,12,3,13],[3,14,5,14],[3,15,3,16]],"flags":["formulas_cached_only"]}
["Rpt Period",null,null,"2005-02-28",{"$nulls":15},"Run Date:"]
[{"$nulls":19},"2008-03-11T08:30:01.500"]
[{"$nulls":7},"Current Period",{"$nulls":4},"Cumulative to Date",{"$nulls":7},"At Complete"]
["WBS",{"$nulls":6},"Budgeted Cost",null,"Actual Cost\nWork Performed","Variance",null,"Budgeted Cost",null,"Actual Cost\nWork Performed","Variance",null,"Perf. Indices",null,null,"Latest"]
["Level",{"$nulls":6},"Work","Work",null,"Schedule","Cost","Work","Work",null,"Schedule","Cost","SPI","CPI",null,"Revised"]
[{"$nulls":6},"Description","Scheduled","Performed",null,null,null,"Scheduled","Performed",{"$nulls":5},"Budgeted","Estimate","Variance"]
["1","2","3","4","5","6"]
[{"$nulls":6},"LINAC COHERENT LIGHT SOURCE (TPC)"]
["1","  ","  ","  ","  ","  ","LCLS PROJECT - PED & CONSTRUCTION                           "]
["1","01","  ","  ","  ","  ","LCLS PROJECT MGMT, PLANNING & ADMN (TEC)                    "]
["1","01","01","  ","  ","  ","Environment, Safety & Health                                "]
["1","01","01","01","  ","  ","Radiation Physics                                           ",{"$nulls":5},155085.78,155085.78,179364.86,0,-24279.08,{"$nulls":5},"1"]
["1","01","01","02","  ","  ","ESH Management & Coordination                               ",{"$nulls":5},316335.48,316335.48,339687.91,0,-23352.43,{"$nulls":5},"1"]
["1","01","01","03","  ","  ","Seismic & Engineering Support                               ",{"$nulls":5},16924.54,16924.54,450.25,0,16474.29,{"$nulls":5},"1"]
["1","01","02","  ","  ","  ","Project Management                                          "]
["1","01","02","01","  ","  ","SLAC Project Management Office                              "]
["1","01","02","01","01","  ","SLAC Project Office - General                               ",{"$nulls":5},4631999.23,4631999.23,5096829.33,0,-464830.1,{"$nulls":5},"1"]
["1","01","02","01","02","  ","SLAC Project Support                                        ",{"$nulls":5},1833698.51,1833698.51,1923742.74,0,-90044.23,{"$nulls":5},"1"]
["1","01","02","01","03","  ","SLAC Project Office M&S                                     ",{"$nulls":5},727983.89,727983.89,1424134.98,0,-696151.09,{"$nulls":5},"1"]
["1","01","02","01","04","  ","SSRL Physics Support                                        ",{"$nulls":5},381048.64,381048.64,271912.12,0,109136.52,{"$nulls":5},"1"]
["1","01","03","  ","  ","  ","Technical Integration                                       "]
["1","01","03","01","  ","  ","Global Laser Coordination                                   ",{"$nulls":5},60601.86,60601.86,60601.86,0,0,{"$nulls":5},"1"]
["1","01","03","02","  ","  ","Global Alignment Coordination                               ",{"$nulls":5},286064.29,286064.29,217398.48,0,68665.81,{"$nulls":5},"1"]
["1","01","03","03","  ","  ","System Integration                                          ",{"$nulls":5},300450.9,300450.9,285294.71,0,15156.19,{"$nulls":5},"1"]
["1","01","03","05","  ","  ","Global Controls                                             "]
["1","01","03","05","01","  ","Global Controls Management                                  "]
["1","01","03","05","02","  ","LLRF Controls                                               ",{"$nulls":5},197843.65,297220.48,208762.57,99376.83,88457.91,{"$nulls":5},"1"]
["1","01","03","05","03","  ","E-beam Diagnostics & Controls                               ",{"$nulls":5},437528.62,425343.83,454631.7,-12184.79,-29287.87,{"$nulls":5},"1"]
["1","01","03","05","03","01","Controls - Wire Scanners                                    "]
["1","01","03","05","03","02","Controls - Toroids                                          "]
["1","01","03","05","03","03","Controls - Faraday Cups                                     "]
["1","01","03","05","03","04","Controls - Tune-Up Dump                                     "]
["1","01","03","05","03","05","Controls - Profile Monitors                                 "]
["1","01","03","05","03","06","Controls - E/O Diagnostics                                  "]
["1","01","03","05","03","07","Controls - BPM                                              "]
["1","01","03","05","03","08","Controls - Stopppers                                        "]
["1","01","03","05","03","09","Controls - Bunch Length Monitors                            "]
["1","01","03","05","03","10","Controls - Beam Loss Monitors                               "]
["1","01","03","05","04","  ","Laser Controls Design                                       ",{"$nulls":5},50664,60153.01,2839.63,9489.01,57313.38,{"$nulls":5},"1"]
["1","01","03","05","05","  ","Laser Heater Controls                                       "]
["1","01","03","05","06","  ","Timing Controls                                             ",{"$nulls":5},70400.69,33468.63,35662.91,-36932.06,-2194.280000000006,{"$nulls":5},"1"]
["1","01","03","05","07","  ","Vacuum Controls                                             ",{"$nulls":5},161075.61,145776.38,52085.62,-15299.23,93690.76,{"$nulls":5},"1"]
["1","01","03","05","09","  ","Power Supply Controls                                       ",{"$nulls":5},368996.78,360391.26,490562.74,-8605.520000000019,-130171.48,{"$nulls":5},"1"]
["1","01","03","05","10","  ","PPS/BCS Controls                                            ",{"$nulls":5},110312.55,44955.6,105855.36,-65356.95,-60899.76,{"$nulls":5},"1"]
["1","01","03","05","11","  ","Controls - MPS                                              ",{"$nulls":5},24575.47,23789.74,null,-785.73,23789.74,{"$nulls":5},"1"]
["1","01","03","05","12","  ","Global Controls Management                                  ",{"$nulls":5},667283.45,693940,765958.99,26656.55,-72018.99,{"$nulls":5},"1"]
["1","01","03","05","13","  ","SLC Aware IOC                                               ",{"$nulls":5},328492.31,328492.31,300153.42,0,28338.89,{"$nulls":5},"1"]
["1","01","03","06","  ","  ","Technical Requirements/Parameters                           ",{"$nulls":5},257147.59,257147.59,175410.68,0,81736.91,{"$nulls":5},"1"]
["1","01","04","  ","  ","  ","Education Support                                           "]
["1","01","04","01","  ","  ","Education/Outreach Travel                                   ",{"$nulls":5},6704.4,6704.4,9320.22,0,-2615.82,{"$nulls":5},"1"]
["1","01","04","02","  ","  ","Education/Outreach M&S                                      ",{"$nulls":5},4803.88,4803.88,6168.14,0,-1364.26,{"$nulls":5},"1"]
["1","02","  ","  ","  ","  ","INJECTOR SYSTEM                                             "]
["1","02","01","  ","  ","  ","Injector System Management & Integration                    "]
["1","02","01","01","  ","  ","Injector System Integration                                 "]
["1","02","01","01","01","  ","Injector Region Integration                                 ",{"$nulls":5},131862.32,132015.49,158425.61,153.1699999999837,-26410.12,{"$nulls":5},"1"]
["1","02","01","01","02","  ","Gun Area Integration                                        ",{"$nulls":5},17678.49,18484.49,13306.77,806,5177.72,{"$nulls":5},"1"]
["1","02","01","01","03","  ","Accelerator Area Integration                                ",{"$nulls":5},18883.01,15794.97,16046.58,-3088.04,-251.61000000000058,{"$nulls":5},"1"]
["1","02","01","01","04","  ","Heater Area Integration                                     ",{"$nulls":5},32727.54,31452.46,30490.31,-1275.08,962.1499999999978,{"$nulls":5},"1"]
["1","02","01","01","05","  ","Wall Area Integration                                       ",{"$nulls":5},97443.61,97443.61,98165.62,0,-722.0099999999948,{"$nulls":5},"1"]
["1","02","01","01","06","  ","Insertion Area Integration                                  ",{"$nulls":5},19378.42,18491.5,24649.29,-886.9199999999983,-6157.79,{"$nulls":5},"1"]
["1","02","01","01","07","  ","Spectrometer Area Integration                               ",{"$nulls":5},4666.89,3430.64,null,-1236.25,3430.64,{"$nulls":5},"1"]
["1","02","01","01","08","  ","Drive Laser Integration                                     ",{"$nulls":5},0,null,null,0,0,{"$nulls":5},"1"]
["1","02","01","04","  ","  ","Injector System Integration Effort / M&S                    ",{"$nulls":5},2729550.7,2694079.5,2720028.83,-35471.200000000186,-25949.330000000075,{"$nulls":5},"1"]
["1","02","02","  ","  ","  ","Injector Controls Subsystem                                 "]
["1","02","02","01","  ","  ","Personnel Protection Subsystem (PPS)                        ",{"$nulls":5},10323.02,28607.12,33112.15,18284.1,-4505.03,{"$nulls":5},"1"]
["1","02","02","02","  ","  ","Beam Containment Subsystem (BCS)                            ",{"$nulls":5},3639.26,1637.67,null,-2001.59,1637.67,{"$nulls":5},"1"]
["1","02","02","03","  ","  ","Machine Protection Subsystem (MPS)                          "]
["1","02","02","04","  ","  ","Injector Power Conversion                                   "]
["1","02","02","04","01","  ","Beamline Pwr Supplies - (Dipole Type)                       ",{"$nulls":5},70851.1,19875.05,13798.96,-50976.05,6076.09,{"$nulls":5},"1"]
["1","02","02","04","01","01","10kw Power Supply - (Solenoid 1)                            "]
["1","02","02","04","01","02","30kw Power Supply - (Solenoid 2)                            "]
["1","02","02","04","01","03","2kw Power Supply - (B0.5 Spect)                             "]
["1","02","02","04","01","04","15kw Power Supply - (B1-2)                                  "]
["1","02","02","04","01","05","15kw Power Supply - (B3 Spect)                              "]
["1","02","02","04","01","06","10kw Power Supply - (New)                                   "]
["1","02","02","04","02","  ","Power Supply Controls                                       "]
["1","02","02","04","03","  ","Beamline Pwr Supplies - (Trim Type)                         ",{"$nulls":5},4531.66,4262.75,31832.37,-268.91,-27569.62,{"$nulls":5},"1"]
["1","02","02","04","03","01","12Amp Power Supply - (MCOR_1)                               "]
["1","02","02","04","03","02","30Amp Power Supply - (MCOR_2)                               "]
["1","02","02","04","03","03","30Amp Power Supply - (MCOR_3)                               "]
["1","02","02","04","03","04","30Amp Power Supply - (MCOR_4)                               "]
["1","02","02","04","04","  ","Beamline Pwr Supply - Misc Hdwr                             ",{"$nulls":5},115774.97,100898.89,66161.31,-14876.08,34737.58,{"$nulls":5},"1"]
["1","02","02","04","05","  ","Magnet Interlock Protection System                          "]
["1","02","02","05","  ","  ","LLRF Controls                                               "]
["1","02","02","05","01","  ","Readback & Controls - RF Gun LLRF & Temperature             "]
["1","02","02","05","02","  ","Readback & Controls - L0 LLRF                               "]
["1","02","02","05","03","  ","Readback & Controls - Transverse Cavity LLRF                "]
["1","02","02","05","04","  ","S-Band Cavity Controls                                      "]
["1","02","02","05","05","  ","EO Phase Controls                                           "]
["1","02","02","06","  ","  ","E-Beam Diagnostics Controls                                 "]
["1","02","02","06","01","  ","Controls - Wire Scanners                                    ",{"$nulls":5},0,null,null,0,0,{"$nulls":5},"1"]
["1","02","02","06","02","  ","Controls - BPM                                              ",{"$nulls":5},0,null,null,0,0,{"$nulls":5},"1"]
["1","02","02","06","03","  ","Controls - Toroids                                          ",{"$nulls":5},-701.44,null,null,701.44,0,{"$nulls":5},"1"]
["1","02","02","06","05","  ","Controls - Profile Monitors                                 ",{"$nulls":5},-421.9,null,null,421.9,0,{"$nulls":5},"1"]
["1","02","02","06","06","  ","Controls - E/O Diagnostics                                  "]
["1","02","02","06","14","  ","Controls - Faraday Cups                                     "]
["1","02","02","06","15","  ","Controls - Tune-Up Dump                                     ",{"$nulls":5},-321.66,null,null,321.66,0,{"$nulls":5},"1"]
["1","02","02","06","16","  ","Diagnostics Controls Integration                            "]
["1","02","02","08","  ","  ","Timing Controls                                             ",{"$nulls":5},820.61,820.61,11326.27,0,-10505.66,{"$nulls":5},"1"]
["1","02","02","09","  ","  ","Vacuum Controls                                             ",{"$nulls":5},-0.01,null,null,0.01,0,{"$nulls":5},"1"]
["1","02","02","10","  ","  ","Software & Controls Infrastructure                          "]
["1","02","02","10","01","  ","Low Level Application Software                              "]
["1","02","02","10","02","  ","High Level Application Software                             "]
["1","02","02","10","03","  ","Data Communications                                         ",{"$nulls":5},-923.16,null,null,923.16,0,{"$nulls":5},"1"]
["1","02","02","10","04","  ","Computers & Crates                                          ",{"$nulls":5},169532.27,161690.19,165999.13,-7842.079999999987,-4308.94,{"$nulls":5},"1"]
["1","02","02","11","  ","  ","EPICS VXI Control Modules (Moved to R&D)                    ",{"$nulls":5},182563.23,194879.72,82600.22,12316.49,112279.5,{"$nulls":5},"1"]
["1","02","02","12","  ","  ","Laser Controls                                              "]
["1","02","02","12","01","  ","Controls - Alignment Laser                                  "]
["1","02","02","12","02","  ","Controls - Gun Laser                                        ",{"$nulls":5},0,26246.71,8769.45,26246.71,17477.26,{"$nulls":5},"1"]
["1","02","02","13","  ","  ","Laser Heater Controls                                       "]
["1","02","03","  ","  ","  ","Injector Lasers                                             "]
["1","02","03","01","  ","  ","Drive Laser Support                                         "]
["1","02","03","01","01","  ","Drive Laser Support (ANL)                                   ",{"$nulls":5},43242.68,39345.3,28133.11,-3897.38,11212.19,{"$nulls":5},"1"]
["1","02","03","01","02","  ","Drive Laser Support (LLNL)                                  ",{"$nulls":5},386290.11,258261.19,273834.99,-128028.92,-15573.8,{"$nulls":5},"1"]
["1","02","03","02","  ","  ","Drive Laser System                                          ",{"$nulls":5},279494.14,261902.54,264867.94,-17591.6,-2965.399999999994,{"$nulls":5},"1"]
["1","02","03","03","  ","  ","Drive Laser Diagnostics                                     ",{"$nulls":5},172018.68,148325.55,103494.72,-23693.13,44830.83,{"$nulls":5},"1"]
["1","02","03","04","  ","  ","Timing Stability Monitoring                                 ",{"$nulls":5},16172.66,6312.17,2273.9,-9860.49,4038.27,{"$nulls":5},"1"]
["1","02","03","05","  ","  ","Steering Stability Feedback & Msmts                         ",{"$nulls":5},39826.3,41401.83,34201.77,1575.53,7200.06,{"$nulls":5},"1"]
["1","02","03","06","  ","  ","Pre Amp Low Power Comp                                      ",{"$nulls":5},2233.4,null,null,-2233.4,0,{"$nulls":5},"1"]
["1","02","03","07","  ","  ","Transport to Tunnel & Relay Optics                          ",{"$nulls":5},130862.36,160229.15,176706.36,29366.79,-16477.21,{"$nulls":5},"1"]
["1","02","03","08","  ","  ","UV Launch, Conditioning & Diagnostics                       ",{"$nulls":5},210174.64,184888.3,169907.38,-25286.34,14980.92,{"$nulls":5},"1"]
["1","02","03","09","  ","  ","Load Lock Transport System                                  "]
["1","02","03","10","  ","  ","Visible Optical Transport & Optics                          "]
["1","02","03","11","  ","  ","LB Infrastructure & LB System Wide Items                    ",{"$nulls":5},77273.2,79510.45,95800.51,2237.25,-16290.06,{"$nulls":5},"1"]
["1","02","03","12","  ","  ","Alignment Laser                                             ",{"$nulls":5},0,null,null,0,0,{"$nulls":5},"1"]
["1","02","03","13","  ","  ","Light path to Streak Camera                                 ",{"$nulls":5},2481.56,4220.2,2943.61,1738.64,1276.59,{"$nulls":5},"1"]
["1","02","03","14","  ","  ","LSR HTR - Beam Conditioning Optics (Laser Bay)              "]
["1","02","03","15","  ","  ","LSR HTR - Transport Optics (Bay to Tunnel)                  "]
["1","02","03","16","  ","  ","LSR HTR - Photon Beam Diagnostics                           "]
["1","02","03","21","  ","  ","UV Conv Harmonic Generation Unit (Closed Account)           ",{"$nulls":5},6282.65,6282.65,6282.65,0,0,{"$nulls":5},"1"]
["1","02","04","  ","  ","  ","Injector RF Subsystem                                       "]
["1","02","04","01","  ","  ","RF Gun & Load Lock                                          "]
["1","02","04","01","01","  ","RF Gun                                                      ",{"$nulls":5},447414.37,338929.9,346052.97,-108484.47,-7123.069999999949,{"$nulls":5},"1"]
["1","02","04","01","02","  ","RF Gun Supports                                             ",{"$nulls":5},-287.74,2806.08,6896.64,3093.82,-4090.56,{"$nulls":5},"1"]
["1","02","04","01","03","  ","Gun Load Lock                                               "]
["1","02","04","01","04","  ","Gun Load Lock Supports                                      ",{"$nulls":5},7265.85,null,null,-7265.85,0,{"$nulls":5},"1"]
["1","02","04","01","05","  ","Gun Solenoid                                                ",{"$nulls":5},91336.81,94563.06,106661.2,3226.25,-12098.14,{"$nulls":5},"1"]
["1","02","04","01","06","  ","Gun Solenoid Supports                                       ",{"$nulls":5},604.5,2128.69,940.03,1524.19,1188.66,{"$nulls":5},"1"]
["1","02","04","01","07","  ","Gun RF Feed                                                 ",{"$nulls":5},12514.18,12514.18,12471.84,0,42.340000000000146,{"$nulls":5},"1"]
["1","02","04","01","08","  ","Gun RF Feed Supports                                        ",{"$nulls":5},11426.93,null,null,-11426.93,0,{"$nulls":5},"1"]
["1","02","04","02","  ","  ","Cathode Processing (CP) Station                             "]
["1","02","04","02","01","  ","CP Cathode Assembly & Supports                              "]
["1","02","04","02","02","  ","CP Load Lock                                                "]
["1","02","04","02","03","  ","CP Load Lock Supports                                       "]
["1","02","04","02","04","  ","CP Station                                                  "]
["1","02","04","02","05","  ","Cathode Lab Infrastructure                                  "]
["1","02","04","03","  ","  ","S-Band Low Level Timing                                     "]
["1","02","04","03","01","  ","Controls Interface & Timing                                 ",{"$nulls":5},284922.02,289881.02,297756.66,4959,-7875.639999999956,{"$nulls":5},"1"]
["1","02","04","03","02","  ","LLRF Phase Reference System                                 ",{"$nulls":5},91585.42,102238.67,91653.34,10653.25,10585.33,{"$nulls":5},"1"]
["1","02","04","03","03","  ","LLRF Monitor & Control System                               ",{"$nulls":5},382340.49,342278.18,353560.76,-40062.31,-11282.58,{"$nulls":5},"1"]
["1","02","04","03","04","  ","Beam Phase Monitor Cavity                                   ",{"$nulls":5},16809,21335.69,36198.01,4526.69,-14862.32,{"$nulls":5},"1"]
["1","02","04","03","05","  ","RF System S/W Development / Docs                            ",{"$nulls":5},-1405.23,null,null,1405.23,0,{"$nulls":5},"1"]
["1","02","04","04","  ","  ","S-Band High Power System                                    "]
["1","02","04","04","01","  ","RF Gun High Power                                           "]
["1","02","04","04","02","  ","L0 High Power                                               "]
["1","02","04","04","03","  ","Transverse Cavity High Power                                ",{"$nulls":5},3194.88,3194.88,0,0,3194.88,{"$nulls":5},"1"]
["1","02","04","05","  ","  ","Injector RF Waveguide Subsystem                             "]
["1","02","04","05","01","  ","RF Waveguides                                               ",{"$nulls":5},1022173.75,994039.57,1101451.18,-28134.18000000005,-107411.61,{"$nulls":5},"1"]
["1","02","04","05","02","  ","RF Waveguide Supports                                       "]
["1","02","04","06","  ","  ","Injector Linac Structures                                   "]
["1","02","04","06","01","  ","L0A-0B Structure Assembly                                   ",{"$nulls":5},388984.6,363859.75,352497.96,-25124.85,11361.79,{"$nulls":5},"1"]
["1","02","04","06","03","  ","Major Linac Support                                         ",{"$nulls":5},27811.39,22207.54,35037.95,-5603.85,-12830.41,{"$nulls":5},"1"]
["1","02","04","06","04","  ","GTL RF Phase Cavity                                         "]
["1","02","04","06","05","  ","LTDL1 RF Kicker                                             ",{"$nulls":5},81662.69,70940.38,62225.93,-10722.31,8714.45,{"$nulls":5},"1"]
["1","02","05","  ","  ","  ","Injector Magnets & Supports                                 "]
["1","02","05","01","  ","  ","Injector Dipoles                                            "]
["1","02","05","01","01","  ","Gun Spectrometer Dipole                                     ",{"$nulls":5},27498.94,25660.17,15266,-1838.77,10394.17,{"$nulls":5},"1"]
["1","02","05","01","02","  ","DL1 B01 & B02 Dipoles                                       ",{"$nulls":5},49778,64153.85,67146.31,14375.85,-2992.46,{"$nulls":5},"1"]
["1","02","05","01","03","  ","SAB Spectrometer Dipole                                     ",{"$nulls":5},32600.83,6524.59,3478.44,-26076.24,3046.15,{"$nulls":5},"1"]
["1","02","05","01","04","  ","Chicane DIPOLES (4)                                         ",{"$nulls":5},38250.2,29619.38,5030.14,-8630.82,24589.24,{"$nulls":5},"1"]
["1","02","05","02","  ","  ","Injector Quads                                              "]
["1","02","05","02","01","  ","Gun Spectrometer Quadrupoles                                ",{"$nulls":5},8523.89,15747.46,31569.11,7223.57,-15821.65,{"$nulls":5},"1"]
["1","02","05","02","02","  ","Injector Quadrupoles                                        ",{"$nulls":5},269526.02,155447.28,76241.18,-114078.74,79206.1,{"$nulls":5},"1"]
["1","02","05","03","  ","  ","Injector Steering Coils                                     "]
["1","02","05","03","01","  ","Gun Solenoid Correctors                                     ",{"$nulls":5},7449.6,7449.6,7449.6,0,0,{"$nulls":5},"1"]
["1","02","05","03","02","  ","Gun Spectrometer Correctors                                 ",{"$nulls":5},0,null,null,0,0,{"$nulls":5},"1"]
["1","02","05","03","03","  ","Injector Correctors - A                                     ",{"$nulls":5},16384.91,20761.65,34085.45,4376.74,-13323.8,{"$nulls":5},"1"]
["1","02","05","03","04","  ","Injector Correctors - D (Gun)                               ",{"$nulls":5},0,null,null,0,0,{"$nulls":5},"1"]
["1","02","05","03","05","  ","Gun Solenoid Quadrupole Correctors                          ",{"$nulls":5},0,null,121.39,0,-121.39,{"$nulls":5},"1"]
["1","02","05","04","  ","  ","Linac Solenoid                                              ",{"$nulls":5},7776.31,41416.98,31123.84,33640.67,10293.14,{"$nulls":5},"1"]
["1","02","05","05","  ","  ","Injector Laser Heater Subsystem                             "]
["1","02","05","05","01","  ","System Design & Optimization (LSR HTR)                      "]
["1","02","05","05","02","  ","Injector Undulator                                          ",{"$nulls":5},2725.77,null,null,-2725.77,0,{"$nulls":5},"1"]
["1","02","06","  ","  ","  ","Injector Vacuum & Supports                                  "]
["1","02","06","01","  ","  ","Injector Vacuum Engineering                                 ",{"$nulls":5},171670.47,151091.79,172749.66,-20578.68,-21657.87,{"$nulls":5},"1"]
["1","02","06","02","  ","  ","Injector Vacuum Components                                  ",{"$nulls":5},128734.46,154470.12,172347.74,25735.66,-17877.62,{"$nulls":5},"1"]
["1","02","06","03","  ","  ","Injector Vacuum Special Chambers                            ",{"$nulls":5},130874.46,19867.67,31126.97,-111006.79,-11259.3,{"$nulls":5},"1"]
["1","02","06","04","  ","  ","Injector Vacuum Supports Engineering                        ",{"$nulls":5},66880.63,84160.78,61343.2,17280.15,22817.58,{"$nulls":5},"1"]
["1","02","06","05","  ","  ","Injector Vacuum Support Components                          ",{"$nulls":5},10050.3,10050.3,80046.4,0,-69996.1,{"$nulls":5},"1"]
["1","02","06","08","  ","  ","DL1 Vacuum Chamber                                          ",{"$nulls":5},6336,6336,6336,0,0,{"$nulls":5},"1"]
["1","02","06","10","  ","  ","DL1TL Vacuum Components                                     ",{"$nulls":5},74325.62,74325.62,74325.62,0,0,{"$nulls":5},"1"]
["1","02","07","  ","  ","  ","Injector Diagnostics                                        "]
["1","02","07","01","  ","  ","Beam Position Monitors                                      "]
["1","02","07","01","01","  ","Large Aperture BPM                                          ",{"$nulls":5},91486.21,88248.64,62487.19,-3237.570000000007,25761.45,{"$nulls":5},"1"]
["1","02","07","01","02","  ","Small Aperture BPM                                          ",{"$nulls":5},233720.65,216063.89,128607.18,-17656.76,87456.71,{"$nulls":5},"1"]
["1","02","07","02","  ","  ","Current Monitors                                            "]
["1","02","07","02","01","  ","Current Monitors                                            ",{"$nulls":5},26597.84,24880.62,3060.25,-1717.22,21820.37,{"$nulls":5},"1"]
["1","02","07","03","  ","  ","Bunch Length Monitors                                       "]
["1","02","07","03","01","  ","Bunch Length Monitors                                       "]
["1","02","07","04","  ","  ","Profile Monitors                                            "]
["1","02","07","04","01","  ","Profile Monitors                                            ",{"$nulls":5},443805.74,283380.34,237126.43,-160425.4,46253.91,{"$nulls":5},"1"]
["1","02","07","04","03","  ","GS Faraday Cup/YAG2                                         ",{"$nulls":5},14961.62,14961.62,14961.62,0,0,{"$nulls":5},"1"]
["1","02","07","04","06","  ","DL1 OTR/YAG                                                 "]
["1","02","07","04","07","  ","DL1TL OTR/YAG                                               "]
["1","02","07","04","08","  ","LTDL1 OTR/YAG (6)                                           ",{"$nulls":5},36488.64,36488.64,38178.24,0,-1689.6,{"$nulls":5},"1"]
["1","02","07","05","  ","  "," Injector Wire Scanners                                     ",{"$nulls":5},0,16819.21,45769.77,16819.21,-28950.56,{"$nulls":5},"1"]
["1","02","07","06","  ","  ","LSR HTR - Electron Beam Diagnostics                         "]
["1","02","07","07","  ","  ","PPS Stopper                                                 ",{"$nulls":5},108754.19,108754.19,134140.73,0,-25386.54,{"$nulls":5},"1"]
["1","02","17","  ","  ","  ","Injector Installation & Alignment                           "]
["1","02","17","01","  ","  ","Injector Infrastructure Installation                        ",{"$nulls":5},61780.24,111583.58,76525.6,49803.34,35057.98,{"$nulls":5},"1"]
["1","02","17","02","  ","  ","Injector Controls Subsystem Install & Align                 "]
["1","02","17","03","  ","  ","Injector Lasers Install & Align                             ",{"$nulls":7},1635.06,0,-1635.06,{"$nulls":5},"1"]
["1","02","17","04","  ","  ","Gun Area Integration                                        ",{"$nulls":5},0,null,120.42,0,-120.42,{"$nulls":5},"1"]
["1","02","17","06","  ","  ","Accelerator Area Integration                                "]
["1","02","17","07","  ","  ","Heater Area Integration                                     ",{"$nulls":5},11299.95,null,null,-11299.95,0,{"$nulls":5},"1"]
["1","02","17","08","  ","  ","Wall Area Integration                                       ",{"$nulls":5},18451.73,1252.06,46170.92,-17199.67,-44918.86,{"$nulls":5},"1"]
["1","02","17","09","  ","  ","Insertion Area Integration                                  "]
["1","02","17","11","  ","  ","Spectrometer Area Integration                               "]
["1","02","17","12","  ","  ","Injector RF High Power System Install & Align               ",{"$nulls":5},35347,11782.33,77430.27,-23564.67,-65647.94,{"$nulls":5},"1"]
["1","02","17","13","  ","  ","Injector RF Low Level Install & Align                       "]
["1","02","17","14","  ","  ","Cathode and Load Lock Install & Align                       ",{"$nulls":5},0,null,null,0,0,{"$nulls":5},"1"]
["1","02","17","15","  ","  ","Injector Laser Heater Subsystem Install & Align             "]
["1","02","17","17","  ","  ","Power  Conversion Subsystem Installation                    "]
["1","02","17","18","  ","  ","Cathode Processing Center Installation                      "]
["1","03","  ","  ","  ","  ","LINAC SYSTEM                                                "]
["1","03","01","  ","  ","  ","System Management & Integration                             "]
["1","03","01","01","  ","  ","Linac Mechanical Integration                                "]
["1","03","01","01","01","  ","L01 System Integration                                      ",{"$nulls":5},236994.94,236994.94,239043.52,0,-2048.579999999987,{"$nulls":5},"1"]
["1","03","01","01","02","  ","BC1 System Integration                                      ",{"$nulls":5},256362.32,248504.74,243265.52,-7857.580000000016,5239.22,{"$nulls":5},"1"]
["1","03","01","01","03","  ","L02 System Integration                                      ",{"$nulls":5},54609.48,54675.49,67503.94,66.00999999999476,-12828.45,{"$nulls":5},"1"]
["1","03","01","01","04","  ","BC2 System Integration                                      ",{"$nulls":5},42049.26,43173.01,36286.64,1123.75,6886.37,{"$nulls":5},"1"]
["1","03","01","01","05","  ","L03 System Integration                                      ",{"$nulls":5},37874.45,37973.29,42884.86,98.84000000000378,-4911.57,{"$nulls":5},"1"]
["1","03","01","01","06","  ","LTU System Integration                                      ",{"$nulls":5},136913.65,136234.55,135005.37,-679.1000000000058,1229.179999999993,{"$nulls":5},"1"]
["1","03","01","01","07","  ","E-Dump System Integration                                   ",{"$nulls":5},105635.7,101467.49,98590.76,-4168.209999999992,2876.7300000000105,{"$nulls":5},"1"]
["1","03","01","03","  ","  ","Travel                                                      ",{"$nulls":5},28037.45,25657.37,11947.71,-2380.08,13709.66,{"$nulls":5},"1"]
["1","03","01","04","  ","  ","Linac Management                                            ",{"$nulls":5},1085718.69,1065782.2,1108898.03,-19936.49,-43115.830000000075,{"$nulls":5},"1"]
["1","03","02","  ","  ","  ","Linac Controls & Power Conversion Subsystem                 "]
["1","03","02","01","  ","  ","Personnel Protection System (PPS)                           "]
["1","03","02","02","  ","  ","Beam Containment System (BCS)                               ",{"$nulls":5},2508.37,2508.37,2508.37,0,0,{"$nulls":5},"1"]
["1","03","02","03","  ","  ","Machine Protection System (MPS)                             ",{"$nulls":5},14848.66,null,null,-14848.66,0,{"$nulls":5},"1"]
["1","03","02","04","  ","  ","Linac Power Conversion Subsystem                            "]
["1","03","02","04","01","  ","Beamline Power Supplies - (Dipole Type)                     ",{"$nulls":5},103223.49,4666.02,5024.52,-98557.47,-358.5,{"$nulls":5},"1"]
["1","03","02","04","01","01","30kw Pwr Supply - (B11-14)                                  "]
["1","03","02","04","01","02","Power Supply - (B21-26)                                     "]
["1","03","02","04","01","03","78kw Pwr Supply - (B31-34)                                  "]
["1","03","02","04","01","05","Power Supply - (BY1)                                        "]
["1","03","02","04","01","06","Kicker (BYBKIK)                                             "]
["1","03","02","04","01","08","78kw Pwr Supply - (Dump Bend)                               "]
["1","03","02","04","02","  ","Beamline Power Supplies - (Quad Type)                       ",{"$nulls":5},20683.88,null,1404.5,-20683.88,-1404.5,{"$nulls":5},"1"]
["1","03","02","04","02","01","2kw Power Supply - (SEC-23)                                 "]
["1","03","02","04","02","02","2kw Power Supply - (SEC-24)                                 "]
["1","03","02","04","02","03","2kw Power Supply - (SEC-25)                                 "]
["1","03","02","04","02","04","2kw Power Supply - (SEC-26)                                 "]
["1","03","02","04","02","05","2kw Power Supply - (SEC-27)                                 "]
["1","03","02","04","02","06","2kw Power Supply - (SEC-28)                                 "]
["1","03","02","04","02","07","2kw Power Supply - (SEC-29)                                 "]
["1","03","02","04","02","08","10kw Power Supply - (Q24701)                                "]
["1","03","02","04","02","09","10kw Power Supply - (QM21)                                  "]
["1","03","02","04","02","11","10kw Power Supply - (Q24901)                                "]
["1","03","02","04","02","12","10kw Power Supply - (QM22)                                  "]
["1","03","02","04","02","13","Power Supply - (QVM1)                                       "]
["1","03","02","04","02","14","Power Supply - (QVM2)                                       "]
["1","03","02","04","02","15","Power Supply - (QVM3)                                       "]
["1","03","02","04","02","16","Power Supply - (QVM4)                                       "]
["1","03","02","04","02","17","Power Supply - (QVB1)                                       "]
["1","03","02","04","02","18","Power Supply - (QDL1)                                       "]
["1","03","02","04","02","19","Power Supply - (QE31)                                       "]
["1","03","02","04","02","20","Power Supply - (QEM1)                                       "]
["1","03","02","04","02","21","Power Supply - (QEM2)                                       "]
["1","03","02","04","02","22","Power Supply - (QEM3)                                       "]
["1","03","02","04","02","23","Power Supply - (QEM4)                                       "]
["1","03","02","04","02","24","Power Supply - (QTm1)                                       "]
["1","03","02","04","02","25","Power Supply - (QTm2)                                       "]
["1","03","02","04","02","26","Power Supply - (QUM1)                                       "]
["1","03","02","04","02","27","Power Supply - (QUM2)                                       "]
["1","03","02","04","02","28","Power Supply - (QUM3)                                       "]
["1","03","02","04","02","29","Power Supply - (QUM4)                                       "]
["1","03","02","04","02","30","Power Supply - (QDMP)                                       "]
["1","03","02","04","02","31","Power Supply - (QUE1)                                       "]
["1","03","02","04","02","32","Power Supply - (QUE2)                                       "]
["1","03","02","04","03","  ","Beamline Power Supplies - (Trim Type)                       ",{"$nulls":5},74081.59,null,28121.8,-74081.59,-28121.8,{"$nulls":5},"1"]
["1","03","02","04","03","01","12Amp Power Supply - (MCOR_1)                               "]
["1","03","02","04","03","02","30Amp Power Supply - (MCOR_2)                               "]
["1","03","02","04","03","03","30Amp Power Supply - (MCOR_3)                               "]
["1","03","02","04","03","04","30Amp Power Supply - (MCOR_4)                               "]
["1","03","02","04","03","10","Power Supply - (MCOR_LTU1)                                  "]
["1","03","02","04","03","11","Power Supply - (MCOR_LTU2)                                  "]
["1","03","02","04","03","12","Power Supply - (MCOR_LTU3)                                  "]
["1","03","02","04","03","13","Power Supply - (MCOR_LTU4)                                  "]
["1","03","02","04","03","14","Power Supply - (MCOR_LTU5)                                  "]
["1","03","02","04","03","15","Power Supply - (MCOR_LTU6)                                  "]
["1","03","02","04","04","  ","Controls & Power Supply                                     ",{"$nulls":5},147154.55,64779.75,80034.85,-82374.8,-15255.1,{"$nulls":5},"1"]
["1","03","02","05","  ","  ","Controls - LLRF                                             "]
["1","03","02","06","  ","  ","Controls - E-Beam Diagnostic                                "]
["1","03","02","06","01","  ","Controls - Wire Scanners                                    ",{"$nulls":5},0,null,null,0,0,{"$nulls":5},"1"]
["1","03","02","06","02","  ","Controls - BPMs                                             ",{"$nulls":5},0,null,null,0,0,{"$nulls":5},"1"]
["1","03","02","06","03","  ","Controls - Toroids                                          ",{"$nulls":5},0,null,null,0,0,{"$nulls":5},"1"]
["1","03","02","06","04","  ","Controls - Stoppers                                         "]
["1","03","02","06","05","  ","Controls - Profile Monitors                                 ",{"$nulls":5},0,null,null,0,0,{"$nulls":5},"1"]
["1","03","02","06","06","  ","Controls - E/O Diagnostics                                  "]
["1","03","02","06","07","  ","Controls - Bunch Length Monitors                            ",{"$nulls":5},4666.54,null,null,-4666.54,0,{"$nulls":5},"1"]
["1","03","02","06","08","  ","Controls - Beam Loss Monitors                               ",{"$nulls":5},4666.54,null,null,-4666.54,0,{"$nulls":5},"1"]
["1","03","02","06","09","  ","Controls - Single Beam Dump                                 "]
["1","03","02","06","10","  ","Controls - E Beam Dump                                      "]
["1","03","02","06","11","  ","Controls - Protection Collimator                            ",{"$nulls":7},614.62,0,-614.62,{"$nulls":5},"1"]
["1","03","02","06","12","  ","Controls - Movable Collimator                               ",{"$nulls":5},-0.01,null,null,0.01,0,{"$nulls":5},"1"]
["1","03","02","06","13","  ","Controls - X-Band Accel Structure                           ",{"$nulls":5},0,316.22,1490.4,316.22,-1174.18,{"$nulls":5},"1"]
["1","03","02","08","  ","  ","Controls - Timing                                           ",{"$nulls":5},0,null,null,0,0,{"$nulls":5},"1"]
["1","03","02","09","  ","  ","Controls - Vacuum                                           "]
["1","03","02","09","01","  ","Controls - Vacuum Instrumentation & Interlocks              "]
["1","03","02","09","02","  ","Controls - Vacuum Pump Power Supplies                       ",{"$nulls":5},0,null,null,0,0,{"$nulls":5},"1"]
["1","03","02","10","  ","  ","Software & Controls Infrastructure                          "]
["1","03","02","10","04","  ","Data Communications                                         ",{"$nulls":5},-312.65,null,null,312.65,0,{"$nulls":5},"1"]
["1","03","02","10","05","  ","Computers                                                   ",{"$nulls":5},-477.47,null,null,477.47,0,{"$nulls":5},"1"]
["1","03","03","  ","  ","  ","Linac Magnets & Supports                                    "]
["1","03","03","01","  ","  ","Bend Magnet (BX1_BC1)                                       ",{"$nulls":5},79975.24,79997.32,58397.35,22.080000000001746,21599.97,{"$nulls":5},"1"]
["1","03","03","02","  ","  ","Bend Magnet (BX3_LTU)                                       "]
["1","03","03","03","  ","  ","Bend Magnet (BX2_BC2)                                       ",{"$nulls":5},45365.93,44503.15,20800.6,-862.7799999999988,23702.55,{"$nulls":5},"1"]
["1","03","03","04","  ","  ","Bend Magnet (BY_LTU)                                        ",{"$nulls":5},26622.52,2008.59,null,-24613.93,2008.59,{"$nulls":5},"1"]
["1","03","03","05","  ","  ","Quad Magnet (Quad_LTU)                                      ",{"$nulls":5},3558.75,10781.1,851.1,7222.35,9930,{"$nulls":5},"1"]
["1","03","03","07","  ","  ","Quad Magnet (QE)                                            ",{"$nulls":5},10570.96,10570.96,null,0,10570.96,{"$nulls":5},"1"]
["1","03","03","08","  ","  ","Corrector Magnet (Type 4)                                   ",{"$nulls":5},10913.76,8859.78,null,-2053.98,8859.78,{"$nulls":5},"1"]
["1","03","03","09","  ","  ","Bend Magnet (BYD_LTU)                                       ",{"$nulls":5},40141.62,20754.82,null,-19386.8,20754.82,{"$nulls":5},"1"]
["1","03","03","10","  ","  ","Quad Magnet (QA)                                            ",{"$nulls":5},26849.3,19476.4,7041.75,-7372.9,12434.65,{"$nulls":5},"1"]
["1","03","03","11","  ","  ","Bend Magnet (BYPM_LTU)                                      ",{"$nulls":5},36951.99,69149.77,null,32197.78,69149.77,{"$nulls":5},"1"]
["1","03","03","12","  ","  ","Bend Magnet (BYKIK_LTU)                                     ",{"$nulls":5},36705.68,39471.78,null,2766.1,39471.78,{"$nulls":5},"1"]
["1","03","03","13","  ","  ","Bend Magnet (BYW_LTU)                                       "]
["1","03","04","  ","  ","  ","Linac Vacuum Subsystem                                      "]
["1","03","04","02","  ","  ","Linac Beamline Vacuum System                                ",{"$nulls":5},118512.21,40428.84,35789.4,-78083.37,4639.44,{"$nulls":5},"1"]
["1","03","04","03","  ","  ","BC1 Vacuum System                                           ",{"$nulls":5},88353.72,57335.81,99730.35,-31017.91,-42394.54,{"$nulls":5},"1"]
["1","03","04","04","  ","  ","BC2 Vacuum System                                           ",{"$nulls":5},28776.11,9432.24,33499.32,-19343.87,-24067.08,{"$nulls":5},"1"]
["1","03","04","05","  ","  ","Linac to Undulator (LTU) Vacuum System                      ",{"$nulls":5},17811.31,2608.46,null,-15202.85,2608.46,{"$nulls":5},"1"]
["1","03","04","06","  ","  ","Dumpline Vacuum System                                      ",{"$nulls":5},33053.61,41126.58,null,8072.97,41126.58,{"$nulls":5},"1"]
["1","03","05","  ","  ","  ","Linac Electron Diagnostics Summary                          "]
["1","03","05","01","  ","  ","Wire Scanners (11) Summary                                  ",{"$nulls":5},157368.75,150168.7,140307.13,-7200.049999999988,9861.570000000007,{"$nulls":5},"1"]
["1","03","05","02","  ","  ","Beam Position Monitors                                      "]
["1","03","05","02","01","  ","BPM - Standard  Linac (4) Summary                           ",{"$nulls":5},13775.81,22333.98,null,8558.17,22333.98,{"$nulls":5},"1"]
["1","03","05","02","02","  ","BPM - RF (10) Summary                                       ",{"$nulls":5},0,null,null,0,0,{"$nulls":5},"1"]
["1","03","05","02","03","  ","BPM - FFTB (12) Summary                                     "]
["1","03","05","02","04","  ","BPM - Large Aperture (2) Summary                            ",{"$nulls":5},21913.5,21913.48,22527.88,-0.020000000000436557,-614.4000000000015,{"$nulls":5},"1"]
["1","03","05","03","  ","  ","Toroid Beam Current Monitor (10) Summary                    ",{"$nulls":5},21580.51,26078.27,14198.08,4497.76,11880.19,{"$nulls":5},"1"]
["1","03","05","04","  ","  ","Beam Stoppers (4) Summary                                   ",{"$nulls":5},14452.2,20728.62,7253.15,6276.42,13475.47,{"$nulls":5},"1"]
["1","03","05","05","  ","  ","Profile Monitors (7 OTR-3 PHOSPHOR SCREEN-1 YAG)            ",{"$nulls":5},56840.33,53825.02,60017.7,-3015.31,-6192.68,{"$nulls":5},"1"]
["1","03","05","06","  ","  ","E/O Bunch Length Monitors (1) Summary                       ",{"$nulls":5},22483.25,22483.25,22483.25,0,0,{"$nulls":5},"1"]
["1","03","05","07","  ","  ","CSR/OTR/CTR Bunch Length Monitors (5) Summary               ",{"$nulls":5},37003.16,41808.28,83285.27,4805.12,-41476.99,{"$nulls":5},"1"]
["1","03","05","08","  ","  ","Beam Loss Monitors                                          "]
["1","03","05","08","01","  ","PIC Beam Loss Monitors (10) Summary                         "]
["1","03","05","08","02","  ","PLIC Beam Loss Monitors (2) Summary                         ",{"$nulls":5},0,null,null,0,0,{"$nulls":5},"1"]
["1","03","05","09","  ","  ","Single Beam Dump (1) Summary                                "]
["1","03","05","10","  ","  ","Electron Beam Dump (1) Summary                              "]
["1","03","05","11","  ","  ","Protection Collimators (5) Summary                          ",{"$nulls":5},40144.9,2802.74,null,-37342.16,2802.74,{"$nulls":5},"1"]
["1","03","05","12","  ","  ","Movable Collimators (7x,3y) Summary                         ",{"$nulls":5},37613.03,30462.54,30136.63,-7150.49,325.91,{"$nulls":5},"1"]
["1","03","05","13","  ","  ","Safety Electron Dump (1) Summary                            "]
["1","03","06","  ","  ","  ","Linac RF Subsystem                                          "]
["1","03","06","02","  ","  ","S-Band High Power System                                    ",{"$nulls":5},492023.29,607373.33,222075.2,115350.04,385298.13,{"$nulls":5},"1"]
["1","03","06","03","  ","  ","S-Band Structures                                           ",{"$nulls":5},43540.17,43540.17,34610.86,0,8929.31,{"$nulls":5},"1"]
["1","03","06","04","  ","  ","X-Band Low Level System                                     ",{"$nulls":5},47274.39,124915.05,133052.53,77640.66,-8137.48,{"$nulls":5},"1"]
["1","03","06","05","  ","  ","X-Band High Power System                                    "]
["1","03","06","05","01","  ","X-Band HP Klystron                                          ",{"$nulls":5},130985.83,201606.12,92143.53,70620.29,109462.59,{"$nulls":5},"1"]
["1","03","06","05","02","  ","X-Band HP Modulator                                         ",{"$nulls":5},7867.08,25475.78,28927,17608.7,-3451.22,{"$nulls":5},"1"]
["1","03","06","05","03","  ","X-Band HP Waveguide System                                  ",{"$nulls":5},80526.13,133023.68,144297.95,52497.55,-11274.27,{"$nulls":5},"1"]
["1","03","06","06","  ","  ","X-Band Structures                                           ",{"$nulls":5},127104.55,180628.53,65300.79,53523.98,115327.74,{"$nulls":5},"1"]
["1","03","06","07","  ","  ","RF Distribution System                                      "]
["1","03","06","07","01","  ","Modulator Refurbishment                                     ",{"$nulls":5},6246.32,null,null,-6246.32,0,{"$nulls":5},"1"]
["1","03","06","07","02","  ","Solid State Sub Booster                                     ",{"$nulls":5},47707.88,null,1241.18,-47707.88,-1241.18,{"$nulls":5},"1"]
["1","03","06","07","03","  ","IPA Modifications                                           ",{"$nulls":5},14192.84,null,null,-14192.84,0,{"$nulls":5},"1"]
["1","03","06","07","04","  ","Klystron Controls Interfaces                                "]
["1","03","06","07","05","  ","Bunch Length Electronics                                    ",{"$nulls":5},37417.17,null,null,-37417.17,0,{"$nulls":5},"1"]
["1","03","06","07","06","  ","RF Phase Measurements                                       "]
["1","03","06","07","07","  ","RF Distribution L2 & L3                                     "]
["1","03","06","07","08","  ","RF Fiber Optics Electronics System                          "]
["1","03","06","07","09","  ","RF Stability                                                "]
["1","03","07","  ","  ","  ","Linac Installation & Alignment                              "]
["1","03","07","01","  ","  ","Linac L01 System Installation & Alignment                   ",{"$nulls":5},96714.66,9261.1,23032.4,-87453.56,-13771.3,{"$nulls":5},"1"]
["1","03","07","02","  ","  ","Linac BC1 System Installation & Alignment                   ",{"$nulls":5},17458.53,5237.56,null,-12220.97,5237.56,{"$nulls":5},"1"]
["1","03","07","03","  ","  ","Linac L02 System Installation & Alignment                   ",{"$nulls":5},16714.22,null,null,-16714.22,0,{"$nulls":5},"1"]
["1","03","07","04","  ","  ","Linac BC2 System Installation & Alignment                   "]
["1","03","07","05","  ","  ","Linac L03 System Installation & Alignment                   "]
["1","03","07","06","  ","  ","Linac LTU System Installation & Alignment                   ",{"$nulls":7},11116.26,0,-11116.26,{"$nulls":5},"1"]
["1","03","07","07","  ","  ","Linac E-Dump System Installation & Alignment                ",{"$nulls":5},6679.5,null,null,-6679.5,0,{"$nulls":5},"1"]
["1","04","  ","  ","  ","  ","UNDULATOR SYSTEM                                            "]
["1","04","01","  ","  ","  ","Undulator System Management & Integration                   "]
["1","04","01","01","  ","  ","Undulator System Management                                 "]
["1","04","01","01","01","  ","Undulator System Management - Technical                     ",{"$nulls":5},1446817.6,1446817.6,1592017.42,0,-145199.82,{"$nulls":5},"1"]
["1","04","01","01","02","  ","ANL Project Support                                         ",{"$nulls":5},2370215.77,2370215.77,2267654.16,0,102561.61,{"$nulls":5},"1"]
["1","04","01","02","  ","  ","Undulator System Materials & Supplies                       "]
["1","04","01","02","01","  ","Undulator System M&S - General                              ",{"$nulls":5},64836.08,64836.08,48623.99,0,16212.09,{"$nulls":5},"1"]
["1","04","01","02","02","  ","Undulator System Travel                                     ",{"$nulls":5},165664.96,165664.96,213624.09,0,-47959.13,{"$nulls":5},"1"]
["1","04","01","03","  ","  ","Undulator System Reviews and Workshops                      ",{"$nulls":5},15278.96,-59.31,-5312.61,-15338.27,5253.3,{"$nulls":5},"1"]
["1","04","02","  ","  ","  ","Controls                                                    "]
["1","04","02","01","  ","  ","Controls Management and Integration                         "]
["1","04","02","01","03","  ","Software Interface with SLAC                                ",{"$nulls":5},52957.19,52957.19,32425.19,0,20532,{"$nulls":5},"1"]
["1","04","02","01","04","  ","Undulator Cable, Tray, and Rack Layout                      ",{"$nulls":5},15521.43,17030.64,17467.44,1509.21,-436.7999999999993,{"$nulls":5},"1"]
["1","04","02","02","  ","  ","Motion                                                      "]
["1","04","02","02","01","  ","Fine Motion                                                 ",{"$nulls":6},7859.15,25466.55,7859.15,-17607.4,{"$nulls":5},"1"]
["1","04","02","02","01","01","Motor Interface                                             "]
["1","04","02","02","01","02","Encoder Interface                                           "]
["1","04","02","02","01","03","Motor Driver                                                "]
["1","04","02","02","01","04","Cabling                                                     "]
["1","04","02","02","01","05","Integrate components                                        "]
["1","04","02","02","02","  ","Motion Test Stand                                           ",{"$nulls":5},40662.32,41461.21,69224.49,798.8899999999994,-27763.28,{"$nulls":5},"1"]
["1","04","02","02","06","  ","Scanning Wire Motion                                        ",{"$nulls":5},30183.84,null,null,-30183.84,0,{"$nulls":5},"1"]
["1","04","02","02","06","01","Motor Interface                                             "]
["1","04","02","02","06","02","Encoder Interface                                           "]
["1","04","02","02","06","03","Motor Driver                                                "]
["1","04","02","02","06","04","Cabling                                                     "]
["1","04","02","02","06","05","Integrate components                                        "]
["1","04","02","02","07","  ","Macroscopic Motion                                          ",{"$nulls":5},19315.78,5858.55,4717.45,-13457.23,1141.1,{"$nulls":5},"1"]
["1","04","02","02","07","01","Motor Interface                                             "]
["1","04","02","02","07","03","Motor Driver                                                "]
["1","04","02","02","07","04","Cabling                                                     "]
["1","04","02","02","07","05","Integrate components                                        "]
["1","04","02","03","  ","  ","Signal Analysis                                             "]
["1","04","02","03","01","  ","RFBPM                                                       ",{"$nulls":5},12132.98,1405.76,null,-10727.22,1405.76,{"$nulls":5},"1"]
["1","04","02","03","01","02","Signal Acquisition                                          "]
["1","04","02","03","01","03","Timing interface                                            "]
["1","04","02","03","01","04","Cabling                                                     "]
["1","04","02","03","01","05","Integrate components                                        "]
["1","04","02","03","02","  ","Charge Monitor                                              ",{"$nulls":5},56663.58,null,null,-56663.58,0,{"$nulls":5},"1"]
["1","04","02","03","02","03","Integrate components                                        "]
["1","04","02","03","03","  ","Scanning Wire                                               "]
["1","04","02","03","03","01","BFW Actuator Control                                        "]
["1","04","02","03","03","06","Integrate components                                        "]
["1","04","02","04","  ","  ","Video                                                       "]
["1","04","02","04","01","  ","OTR Monitor                                                 ",{"$nulls":5},17481.97,7295.04,19389.09,-10186.93,-12094.05,{"$nulls":5},"1"]
["1","04","02","04","01","01","Camera                                                      "]
["1","04","02","04","01","02","Camera trigger interface                                    "]
["1","04","02","04","01","03","Digitizer                                                   "]
["1","04","02","04","01","04","Timing interface                                            "]
["1","04","02","04","01","05","Cabling                                                     "]
["1","04","02","04","01","06","Integrate components                                        "]
["1","04","02","04","03","  ","Observation station video                                   ",{"$nulls":5},13939.99,13939.99,9154.16,0,4785.83,{"$nulls":5},"1"]
["1","04","02","04","03","01","Camera                                                      "]
["1","04","02","04","03","02","Camera trigger interface                                    "]
["1","04","02","04","03","03","Multiplexor                                                 "]
["1","04","02","04","03","04","Cabling                                                     "]
["1","04","02","04","03","05","Integrate components                                        "]
["1","04","02","04","03","06","Imaging Test Stand                                          "]
["1","04","02","05","  ","  ","Data Acquisition and Control                                "]
["1","04","02","05","01","  ","Strongback Temperature monitoring                           ",{"$nulls":5},5289.87,null,null,-5289.87,0,{"$nulls":5},"1"]
["1","04","02","05","01","01","Integrate components                                        "]
["1","04","02","06","  ","  ","Vacuum                                                      "]
["1","04","02","06","01","  ","Ion Pump Controller                                         "]
["1","04","02","06","01","01","Integrate components                                        "]
["1","04","02","06","02","  ","RGA                                                         "]
["1","04","02","06","02","01"," Integrate components                                       "]
["1","04","02","07","  ","  ","Machine Protection                                          "]
["1","04","02","07","01","  ","Undulator Global MPS                                        "]
["1","04","02","07","01","01","Hardware design                                             "]
["1","04","02","07","01","02","Interface components                                        "]
["1","04","02","07","02","  ","Cerenkov Detector                                           "]
["1","04","02","07","02","01","Signal interface                                            "]
["1","04","02","07","03","  ","Gamma Ray Detector                                          "]
["1","04","02","07","03","01","Signal interface                                            "]
["1","04","02","08","  ","  ","Power Supply Controls                                       "]
["1","04","03","  ","  ","  ","Undulator Magnet & Support                                  "]
["1","04","03","01","  ","  ","UND Magnet & Support - Mgmt and Integration                 ",{"$nulls":5},14239.72,14239.72,3734.18,0,10505.54,{"$nulls":5},"1"]
["1","04","03","02","  ","  ","First Prototype Undulator & Mfg Plan                        ",{"$nulls":5},-435.93,-435.93,-0.02,0,-435.91,{"$nulls":5},"1"]
["1","04","03","03","  ","  ","1st Article Undulators & Long Lead Procurements             "]
["1","04","03","03","01","  ","Ti Strongback (LLP)                                         ",{"$nulls":5},1323136.96,1589142.8,1722180.65,266005.84,-133037.85,{"$nulls":5},"1"]
["1","04","03","03","02","  ","Magnet Blocks (LLP)                                         ",{"$nulls":5},69586.33,72403.37,117597.64,2817.0399999999936,-45194.27,{"$nulls":5},"1"]
["1","04","03","03","03","  ","Magnet Poles (LLP)                                          ",{"$nulls":5},449768.27,226117.28,231255.5,-223650.99,-5138.22,{"$nulls":5},"1"]
["1","04","03","03","04","  ","Magnet Assembly & Supports - 1st Articles                   ",{"$nulls":5},518615.32,468127.42,528004.42,-50487.9,-59877.00000000006,{"$nulls":5},"1"]
["1","04","03","03","04","01","Magnet Assembly 1st Article - Vendor A                      "]
["1","04","03","03","04","02","Magnet Assembly 1st Article - Vendor B                      "]
["1","04","03","03","04","03","Support/Mover System - Articles 1 & 2                       "]
["1","04","03","03","05","  ","Magnetic Measurement (ANL)                                  ",{"$nulls":5},3231.97,3231.97,44049.1,0,-40817.13,{"$nulls":5},"1"]
["1","04","03","03","05","01","Magnetic Measurement (ANL) - Vendor A Und #1                "]
["1","04","03","03","05","02","Magnetic Measurement (ANL) - Vendor B Und #2                "]
["1","04","03","03","06","  ","Integrated Single-Undulator Module Test                     ",{"$nulls":5},244754.9,109354.06,67985.25,-135400.84,41368.81,{"$nulls":5},"1"]
["1","04","03","03","07","  "," System Test - Two Undulators                               "]
["1","04","03","04","  ","  ","Production Undulator Magnet Assembly & Supports             "]
["1","04","03","04","01","  ","Production Undulator Assembly - Vendor A                    ",{"$nulls":5},17489.43,15324.6,3002.37,-2164.83,12322.23,{"$nulls":5},"1"]
["1","04","03","04","02","  ","Production Undulator Assembly - Vendor B                    ",{"$nulls":7},599.7,0,-599.7,{"$nulls":5},"1"]
["1","04","03","04","03","  ","Production Support/Mover Fabrication/Assembly               "]
["1","04","03","05","  ","  ","Quadrupole Focusing Magnets                                 "]
["1","04","03","05","01","  ","Quadrupole Magnets                                          ",{"$nulls":5},138069.78,30714.94,33212.09,-107354.84,-2497.15,{"$nulls":5},"1"]
["1","04","03","05","02","  ","Quadrupole Power Supplies                                   ",{"$nulls":5},11785.43,null,null,-11785.43,0,{"$nulls":5},"1"]
["1","04","03","05","03","  ","Quadrupole Stages & Stands                                  "]
["1","04","03","05","04","  ","Quadrupole Cables                                           "]
["1","04","03","06","  ","  ","Undulator Magnetic Measurement Facility (SLAC)              "]
["1","04","03","06","01","  ","Undulator MMF Setup                                         ",{"$nulls":5},1979582.63,1571554.18,1141851,-408028.45,429703.18,{"$nulls":5},"1"]
["1","04","03","06","01","01","Undulator Test Stand Prototype                              "]
["1","04","03","06","01","04","Undulator Test Stand                                        "]
["1","04","03","06","01","05","Undulator Fiducialization                                   "]
["1","04","03","06","01","06","Quad Strength and Field Quality                             "]
["1","04","03","06","01","07","Quad Fiducialization System                                 "]
["1","04","03","06","01","08","Hall Probe Calibration System                               "]
["1","04","03","06","01","09","Undulator Handling                                          "]
["1","04","03","06","02","  ","Fiducialization and Magnetic Measurements (F/MM)            "]
["1","04","03","06","02","01","F/MM Undulator Magnet Sections                              "]
["1","04","03","06","02","02","F/MM Quadrupoles                                            "]
["1","04","03","06","02","03","F/MM BPMs                                                   "]
["1","04","03","06","02","04","F/MM Correctors                                             "]
["1","04","03","06","02","05","F/MM Vacuum Chamber                                         "]
["1","04","03","06","02","06","F/MM Photon Diagnostics Components                          "]
["1","04","03","06","03","  ","Undulator Monitoring                                        ",{"$nulls":5},249503.44,126856.05,237993.04,-122647.39,-111136.99,{"$nulls":5},"1"]
["1","04","03","06","03","01","Stretched Wire System                                       "]
["1","04","03","06","03","02","Hydrostatic Level System                                    "]
["1","04","03","06","03","03","F/MM BPMs                                                   "]
["1","04","03","08","  ","  ","Fixed Supports                                              "]
["1","04","03","08","01","  ","Fixed Sppt Mgmt & Integration                               ",{"$nulls":5},69493.44,69493.44,25476.39,0,44017.05,{"$nulls":5},"1"]
["1","04","03","08","02","  ","Fixed Support Design                                        ",{"$nulls":5},152562.91,48173.1,78228.74,-104389.81,-30055.64,{"$nulls":5},"1"]
["1","04","03","08","03","  ","Stabilized Girder Assemblies                                ",{"$nulls":5},2773.45,2496.1,null,-277.35,2496.1,{"$nulls":5},"1"]
["1","04","03","08","04","  ","Thermal Intercept System                                    "]
["1","04","03","08","05","  ","Thermometry                                                 ",{"$nulls":5},68415.17,null,null,-68415.17,0,{"$nulls":5},"1"]
["1","04","03","08","06","  ","Kinematic Girder Support                                    "]
["1","04","03","08","07","  ","Earthquake Bracing                                          ",{"$nulls":5},26802.9,null,null,-26802.9,0,{"$nulls":5},"1"]
["1","04","03","08","08","  ","Controls and Software                                       "]
["1","04","04","  ","  ","  ","Vacuum System                                               "]
["1","04","04","02","  ","  ","Undulator Vacuum Chamber Assembly                           "]
["1","04","04","02","01","  ","Prototype Chamber Weldment                                  ",{"$nulls":5},-1132.37,-1132.37,42721.73,0,-43854.1,{"$nulls":5},"1"]
["1","04","04","02","02","  ","Production Chamber Weldment                                 "]
["1","04","04","02","03","  ","Prototype Aluminum Chamber                                  ",{"$nulls":5},140707.09,63516.06,127000.98,-77191.03,-63484.92,{"$nulls":5},"1"]
["1","04","04","03","  ","  ","Beam-line Bellows Module Assembly                           "]
["1","04","04","03","01","  ","Prototype Bellows Module                                    ",{"$nulls":5},87553.1,42338.25,51865.28,-45214.85,-9527.03,{"$nulls":5},"1"]
["1","04","04","03","02","  ","Production Bellows Module                                   "]
["1","04","04","04","  ","  ","Single Undulator Test (SUT) Vacuum                          ",{"$nulls":5},12245.1,4782.88,3066.25,-7462.22,1716.63,{"$nulls":5},"1"]
["1","04","04","05","  ","  ","Short Diagnostic Break (SDB) Assembly                       ",{"$nulls":5},3280.28,653.31,201.2,-2626.97,452.11,{"$nulls":5},"1"]
["1","04","04","06","  ","  ","Long Diagnostic Break (LDB) Assembly                        ",{"$nulls":5},3561.71,344.18,null,-3217.53,344.18,{"$nulls":5},"1"]
["1","04","04","07","  ","  ","Entrance Section Assembly                                   "]
["1","04","04","08","  ","  ","Exit Section Assembly                                       "]
["1","04","04","09","  ","  ","Baking System                                               ",{"$nulls":7},3769.14,0,-3769.14,{"$nulls":5},"1"]
["1","04","05","  ","  ","  ","Diagnostics                                                 "]
["1","04","05","02","  ","  ","Undulator Line Diagnostics (ULD)                            "]
["1","04","05","02","01","  ","ULD Test Station                                            ",{"$nulls":5},188020.23,150874.87,107437.62,-37145.36,43437.25,{"$nulls":5},"1"]
["1","04","05","02","02","  ","ULD Vacuum Chamber                                          "]
["1","04","05","02","03","  ","Positioning Mechanism                                       ",{"$nulls":5},13481.97,15856.81,40273.86,2374.84,-24417.05,{"$nulls":5},"1"]
["1","04","05","02","04","  ","Scanning wire assembly (ULD-SWA)                            ",{"$nulls":5},117318.55,85185.19,102386.31,-32133.36,-17201.12,{"$nulls":5},"1"]
["1","04","05","02","05","  ","Optical transition radiation imaging assembly               ",{"$nulls":5},58741.47,36968.53,88941.56,-21772.94,-51973.03,{"$nulls":5},"1"]
["1","04","05","02","09","  ","ULD Design & Integration                                    "]
["1","04","05","04","  ","  ","End-of-Undulator(EOU) X-ray and Profile diagnost            "]
["1","04","05","04","01","  ","Prototype Construction and Testing                          ",{"$nulls":5},58430.93,51106.27,15897.91,-7324.66,35208.36,{"$nulls":5},"1"]
["1","04","05","04","02","  ","Bunch Length Monitor-Streak Camera (BLM)                    "]
["1","04","05","04","03","  ","Upstream corrector / separator                              "]
["1","04","05","04","04","  ","Optical Diffraction radiation imaging assembly (            "]
["1","04","05","04","05","  ","X-ray High Resolution monochromator assembly (EO            "]
["1","04","05","04","06","  ","X-ray Imaging High Resolution detector assembly             "]
["1","04","05","04","07","  ","EOU Design and Integration                                  "]
["1","04","05","05","  ","  ","RFBPM                                                       "]
["1","04","05","05","01","  ","X-Band Cavity BPM Development                               ",{"$nulls":5},460166.02,236774.69,214527.3,-223391.33,22247.39,{"$nulls":5},"1"]
["1","04","05","05","02","  ","X-Band Receiver Development                                 ",{"$nulls":5},44837.12,35673.07,5422.52,-9164.05,30250.55,{"$nulls":5},"1"]
["1","04","05","05","03","  ","X-Band BPM Production                                       "]
["1","04","05","06","  ","  ","Beam Finder Wire                                            ",{"$nulls":5},39345.58,36347.01,42714.71,-2998.57,-6367.7,{"$nulls":5},"1"]
["1","04","05","07","  ","  ","Charge Monitor (CM)                                         ",{"$nulls":5},0,null,null,0,0,{"$nulls":5},"1"]
["1","04","05","08","  ","  ","Cherenkov Detector                                          ",{"$nulls":5},36432.48,null,null,-36432.48,0,{"$nulls":5},"1"]
["1","04","05","09","  ","  ","Radiation Detection Monitor (RDM)                           "]
["1","04","05","10","  ","  ","SIngle Undulator Test (SUT) Diagnostics                     ",{"$nulls":5},7075.94,989.57,1070.95,-6086.37,-81.38,{"$nulls":5},"1"]
["1","04","05","11","  ","  ","Supplemental Shielding                                      "]
["1","04","06","  ","  ","  ","Undulator System Installation and Alignment                 "]
["1","04","06","01","  ","  ","Undulator System Installation and Alignment Inte            "]
["1","04","06","01","01","  ","Undulator System                                            "]
["1","04","06","02","  ","  ","Control System Installation and Alignment                   "]
["1","04","06","04","  ","  ","Vacuum System Installation and Alignment                    ",{"$nulls":5},8973.45,6820.43,4168.75,-2153.02,2651.68,{"$nulls":5},"1"]
["1","04","06","05","  ","  ","Diagnostics System Installation and Alignment               "]
["1","05","  ","  ","  ","  ","X-RAY TRANSPORT & DIAGNOSTICS SYSTEMS                       "]
["1","05","01","  ","  ","  ","System Management & Integration                             "]
["1","05","01","01","  ","  ","Management                                                  "]
["1","05","01","01","01","  ","XTOD Management - Technical                                 ",{"$nulls":5},1115257.57,1115257.57,1069859.25,0,45398.320000000065,{"$nulls":5},"1"]
["1","05","01","01","02","  ","LLNL Project Support                                        ",{"$nulls":5},1651469.12,1651469.12,1740451.33,0,-88982.21,{"$nulls":5},"1"]
["1","05","01","01","03","  ","Commissioning Coordinator                                   ",{"$nulls":5},13574.98,13574.98,8890.48,0,4684.5,{"$nulls":5},"1"]
["1","05","02","  ","  ","  ","Controls                                                    "]
["1","05","02","01","  ","  ","Controls - EPICS                                            ",{"$nulls":5},123421.56,128857.13,null,5435.570000000007,128857.13,{"$nulls":5},"1"]
["1","05","02","02","  ","  ","Motor Controls                                              ",{"$nulls":5},291399.33,291399.33,378671.81,0,-87272.48,{"$nulls":5},"1"]
["1","05","02","03","  ","  ","Controls - Vacuum                                           "]
["1","05","03","  ","  ","  ","Mechanical & Vacuum Subsystem                               "]
["1","05","03","01","  ","  ","Vacuum Systems Engineering                                  ",{"$nulls":5},9832.6,9832.6,null,0,9832.6,{"$nulls":5},"1"]
["1","05","03","02","  ","  ","Mech/Vac Front End                                          ",{"$nulls":5},342373.27,343079.08,431342.43,705.8099999999977,-88263.35,{"$nulls":5},"1"]
["1","05","03","03","  ","  ","Mech/Vac Near Hall                                          "]
["1","05","03","03","01","  ","NEH Hutch 1                                                 "]
["1","05","03","03","02","  ","NEH Hutch 2                                                 "]
["1","05","03","03","03","  ","NEH Hutch 3                                                 "]
["1","05","03","04","  ","  ","Mech/Vac Tunnel                                             ",{"$nulls":5},154217.93,154217.82,225934.16,-0.10999999998603016,-71716.34,{"$nulls":5},"1"]
["1","05","03","05","  ","  ","Mech/Vac Far Hall                                           "]
["1","05","03","05","01","  ","FEH Hutch 1                                                 "]
["1","05","03","05","02","  ","FEH Hutch 2                                                 "]
["1","05","03","05","03","  ","FEH Hutch 3                                                 "]
["1","05","04","  ","  ","  ","Optical  Subsystem                                          "]
["1","05","04","01","  ","  ","Optical Systems Engineering                                 "]
["1","05","04","02","  ","  ","Facility Optics                                             "]
["1","05","04","02","01","  ","Facility Optics Engineering                                 "]
["1","05","04","02","02","  ","Fixed Mask                                                  ",{"$nulls":5},4230.55,3268.16,null,-962.39,3268.16,{"$nulls":5},"1"]
["1","05","04","02","03","  ","Slit/Collimators                                            ",{"$nulls":5},10819.15,16663.06,null,5843.91,16663.06,{"$nulls":5},"1"]
["1","05","04","02","04","  ","Flipper Mirror                                              "]
["1","05","04","02","05","  ","Attenuators                                                 ",{"$nulls":5},473092.41,467127.08,447534.26,-5965.329999999958,19592.82,{"$nulls":5},"1"]
["1","05","04","02","06","  ","TTF Damage Experiment                                       ",{"$nulls":5},153894.36,154371.01,146401.34,476.6500000000233,7969.670000000013,{"$nulls":5},"1"]
["1","05","04","02","07","  ","FEL Offset Mirrors                                          ",{"$nulls":5},29505.57,29505.57,57209.89,0,-27704.32,{"$nulls":5},"1"]
["1","05","04","02","08","  ","Solid Attenuator                                            ",{"$nulls":5},7987.52,7987.5,null,-0.020000000000436557,7987.5,{"$nulls":5},"1"]
["1","05","04","02","09","  ","Low Energy Mirror System                                    "]
["1","05","04","03","  ","  ","End Station Optics                                          "]
["1","05","04","03","01","  ","End Station Optics Engineering                              "]
["1","05","04","03","02","  ","Optics Tank - Near Hall                                     "]
["1","05","04","03","03","  ","Optics Tank - Far Hall                                      "]
["1","05","04","03","04","  ","K-B Focusing System                                         "]
["1","05","04","03","05","  ","Refractive Focusing System                                  "]
["1","05","04","04","  ","  ","Crystals & Gratings                                         "]
["1","05","04","04","01","  ","Crystals & Gratings Engineering                             "]
["1","05","04","04","02","  ","System Monochrometer                                        "]
["1","05","04","04","03","  ","Pulse Split & Delay                                         "]
["1","05","05","  ","  ","  ","Diagnostics Subsystem                                       "]
["1","05","05","01","  ","  ","Diagnostic Systems Engineering                              "]
["1","05","05","01","01","  ","Diagnostic Systems Engineering                              "]
["1","05","05","02","  ","  ","Modeling & Simulation                                       "]
["1","05","05","02","01","  ","Wave Model                                                  ",{"$nulls":5},245250.06,245250.06,44437.77,0,200812.29,{"$nulls":5},"1"]
["1","05","05","02","02","  ","Monte Carlo Model                                           ",{"$nulls":5},83571.5,83571.5,649563.78,0,-565992.28,{"$nulls":5},"1"]
["1","05","05","02","03","  ","Beam Simulation                                             ",{"$nulls":5},519126.85,519126.85,0,0,519126.85,{"$nulls":5},"1"]
["1","05","05","03","  ","  ","Facility Diagnostics                                        "]
["1","05","05","03","01","  ","Direct Imager                                               ",{"$nulls":5},96842.58,101429.2,87675.96,4586.62,13753.24,{"$nulls":5},"1"]
["1","05","05","03","02","  ","Indirect Imager                                             ",{"$nulls":5},83740.35,83740.35,149117.03,0,-65376.68,{"$nulls":5},"1"]
["1","05","05","03","03","  ","Pulsed Ion Chamber                                          "]
["1","05","05","03","04","  ","Gas Mixing System                                           "]
["1","05","05","03","05","  ","FEE Diagnostic Tank                                         "]
["1","05","05","03","06","  ","Ion Chamber                                                 ",{"$nulls":5},3396.21,3952.12,null,555.91,3952.12,{"$nulls":5},"1"]
["1","05","05","04","  ","  ","Commissioning Diagnostics                                   "]
["1","05","05","04","01","  ","Commission Diagnostic Tanks                                 "]
["1","05","05","04","02","  ","Total Energy Measurement                                    ",{"$nulls":5},357403.72,356893.17,346982.51,-510.54999999998836,9910.659999999974,{"$nulls":5},"1"]
["1","05","05","04","03","  ","Pulse Length Measurement                                    "]
["1","05","05","04","04","  ","Spectral Measurement                                        ",{"$nulls":5},62181.89,62181.88,14521.64,-0.010000000002037268,47660.24,{"$nulls":5},"1"]
["1","05","05","04","05","  ","Spatial Coherence                                           "]
["1","05","05","04","06","  ","Spatial Shape & Centroid Measurement                        "]
["1","05","05","04","07","  ","Divergence Measurement                                      "]
["1","05","06","  ","  ","  ","X-Ray Transport System Installation & Alignment             "]
["1","05","06","01","  ","  ","Front End Enclosure Install                                 "]
["1","05","06","02","  ","  ","Near Hall Install                                           "]
["1","05","06","03","  ","  ","Tunnel Install                                              "]
["1","05","06","04","  ","  ","Far Hall Install                                            "]
["1","06","  ","  ","  ","  ","X-RAY END STATION SYSTEMS                                   "]
["1","06","01","  ","  ","  ","System Management & Integration                             "]
["1","06","01","01","  ","  ","Management                                                  ",{"$nulls":5},487507.9,487507.9,449448.12,0,38059.78,{"$nulls":5},"1"]
["1","06","01","02","  ","  ","SSRL Physics                                                ",{"$nulls":5},319103.03,319103.03,294960.8,0,24142.23,{"$nulls":5},"1"]
["1","06","02","  ","  ","  ","Controls Subsystem                                          "]
["1","06","02","01","  ","  ","Cabling                                                     "]
["1","06","02","01","01","  ","Front End Enclosure Cable                                   "]
["1","06","02","01","02","  ","Near Hall Cable                                             "]
["1","06","02","01","03","  ","Tunnel Cable                                                "]
["1","06","02","01","04","  ","Far Hall Cable                                              "]
["1","06","02","02","  ","  ","Network                                                     "]
["1","06","02","03","  ","  ","PC Support - AP                                             "]
["1","06","02","04","  ","  ","Beamline Controls - AP                                      "]
["1","06","02","05","  ","  ","X-Ray PPS                                                   "]
["1","06","02","05","01","  ","FEE X-Ray PPS                                               "]
["1","06","02","05","02","  ","Near Hall X-Ray PPS                                         "]
["1","06","02","05","03","  ","Tunnel X-Ray PPS                                            "]
["1","06","02","05","04","  ","Far Hall X-Ray PPS                                          "]
["1","06","02","06","  ","  ","X-Ray MPS                                                   "]
["1","06","02","06","01","  ","FEE X-Ray MPS                                               "]
["1","06","02","06","02","  ","Near Hall X-Ray MPS                                         "]
["1","06","02","06","03","  ","Tunnel X-Ray MPS                                            "]
["1","06","02","06","04","  ","Far Hall X-Ray MPS                                          "]
["1","06","02","07","  ","  ","Laser PPS                                                   "]
["1","06","02","07","01","  ","Near Hall Laser PPS                                         "]
["1","06","02","07","02","  ","Far Hall Laser PPS                                          "]
["1","06","02","08","  ","  ","User Safeguards                                             "]
["1","06","02","08","01","  ","Near Hall User Safeguards                                   "]
["1","06","02","08","02","  ","Far Hall User Safeguards                                    "]
["1","06","03","  ","  ","  ","Mechanical/Vacuum Subsystem                                 "]
["1","06","03","01","  ","  ","Chamber Support Tables - Mech/Vac                           "]
["1","06","03","02","  ","  ","Vacuum Components - Mech/Vac                                "]
["1","06","03","02","01","  ","Valves - Vacuum                                             "]
["1","06","03","02","02","  ","Hardware - Vacuum                                           "]
["1","06","03","02","03","  ","Ion Pump - Vacuum                                           "]
["1","06","03","02","04","  ","Turbo Pump - Vacuum                                         "]
["1","06","03","02","05","  ","Gauges - Vacuum                                             "]
["1","06","03","03","  ","  ","Experimental Chambers                                       "]
["1","06","03","03","01","  ","AP Chamber 1                                                "]
["1","06","03","03","02","  ","AP Chamber 2                                                "]
["1","06","04","  ","  ","  ","Laser Subsystem                                             "]
["1","06","04","01","  ","  ","Oscillator Laser & Pump                                     "]
["1","06","04","01","01","  ","AP Oscillator Laser & Pump                                  "]
["1","06","04","01","02","  ","Far Hall Oscillator Laser & Pump                            "]
["1","06","04","02","  ","  ","Laser Diagnostics                                           "]
["1","06","04","03","  ","  ","Laser Supplies & Optical Transport                          "]
["1","06","04","04","  ","  ","Laser Timing                                                "]
["1","06","04","05","  ","  ","Laser Amplifiers                                            "]
["1","06","04","05","01","  ","AP Laser Amplifier                                          "]
["1","06","04","05","02","  ","Far Hall Laser Amplifier                                    "]
["1","06","05","  ","  ","  ","X-Ray Detectors                                             "]
["1","06","05","01","  ","  ","Beam Imaging                                                "]
["1","06","05","02","  ","  ","2-D X-Ray Detector                                          "]
["1","06","05","03","  ","  ","Beam Intensity                                              "]
["1","06","05","04","  ","  ","Streak Camera                                               "]
["1","06","05","04","01","  ","Engineering                                                 "]
["1","06","05","04","02","  ","Streak Camera - LBL                                         "]
["1","06","06","  ","  ","  ","System Installation & Alignment                             "]
["1","06","06","01","  ","  ","Front End Install                                           "]
["1","06","06","02","  ","  ","Near Hall Install                                           "]
["1","06","06","02","01","  ","Near Hall Install Controls                                  "]
["1","06","06","02","02","  ","Near Hall Install Mech/Vac                                  "]
["1","06","06","02","03","  ","Near Hall Install Laser                                     "]
["1","06","06","02","04","  ","Near Hall Install Detectors                                 "]
["1","06","06","02","05","  ","Near Hall Install Atomic Physics                            "]
["1","06","06","03","  ","  ","Tunnel Install                                              "]
["1","06","06","04","  ","  ","Far Hall Install                                            "]
["1","06","06","04","01","  ","Far Hall Install Controls                                   "]
["1","06","06","04","02","  ","Far Hall Install Mech/Vac                                   "]
["1","06","06","04","03","  ","Far Hall Install Laser                                      "]
["1","06","06","04","04","  ","Far Hall Install Detectors                                  "]
["1","06","07","  ","  ","  ","                                                            "]
["1","06","07","01","  ","  ","AP Samples                                                  "]
["1","06","07","02","  ","  ","AP Detector & Diagnostics                                   "]
["1","06","07","03","  ","  ","AP Data Analysis                                            "]
["1","06","07","04","  ","  ","AP Optics                                                   "]
["1","09","  ","  ","  ","  ","CONVENTIONAL FACILITIES                                     "]
["1","09","01","  ","  ","  ","System Management & Integration                             "]
["1","09","01","01","  ","  ","Management                                                  ",{"$nulls":5},2098515.79,1976384.52,1963734.67,-122131.27,12649.850000000093,{"$nulls":5},"1"]
["1","09","01","02","  ","  ","Cost Account Managers                                       ",{"$nulls":5},605219.5,605219.5,548516.17,0,56703.33,{"$nulls":5},"1"]
["1","09","01","03","  ","  ","Construction Management & AE Support                        ",{"$nulls":5},975511.52,1044106.56,968338.21,68595.04,75768.3500000001,{"$nulls":5},"1"]
["1","09","01","04","  ","  ","Mechanical Design (MD)                                      "]
["1","09","01","04","01","  ","Mechanical Design Title 1 (Linac not included)              ",{"$nulls":5},77898.13,77898.13,77898.13,0,0,{"$nulls":5},"1"]
["1","09","01","04","02","  ","Mechanical Design T1 Linac Facilities                       ",{"$nulls":5},13082.91,13082.91,12229.54,0,853.369999999999,{"$nulls":5},"1"]
["1","09","01","04","03","  ","Mechanical Design Title 2 (Linac not included)              ",{"$nulls":5},40757.57,48927.74,40912.52,8170.17,8015.22,{"$nulls":5},"1"]
["1","09","01","04","04","  ","Mechanical Design T2 Linac Facilities                       ",{"$nulls":5},22446.47,22446.47,19959.26,0,2487.21,{"$nulls":5},"1"]
["1","09","01","04","05","  ","Mechanical Design Title 3 Linac Facility                    "]
["1","09","01","04","06","  ","Mechanical Design Title 3 (Linac not Included)              "]
["1","09","01","05","  ","  ","Conventional Experiment Facility (CEF)                      "]
["1","09","01","05","01","  ","CEF Engineering Title 1(Linac Not Included)                 ",{"$nulls":5},42767.51,42767.51,42767.51,0,0,{"$nulls":5},"1"]
["1","09","01","05","02","  ","CEF Engineering Title 1 Linac Facility                      ",{"$nulls":5},28100.14,28100.34,19031.64,0.2000000000007276,9068.7,{"$nulls":5},"1"]
["1","09","01","05","03","  ","CEF Engineering Title 2 (Linac Not Included)                ",{"$nulls":5},113447.66,104323.54,88855.65,-9124.12000000001,15467.89,{"$nulls":5},"1"]
["1","09","01","05","04","  ","CEF Design Linac Facility Title 2                           "]
["1","09","02","  ","  ","  ","Title 1 & Title 2 Conventional Facilities                   "]
["1","09","02","02","  ","  ","A & E Services (S20, MMF, MMC not Incl)                     "]
["1","09","02","02","01","  ","Title 1 Design                                              ",{"$nulls":5},342409.08,342409.08,336579.08,0,5830,{"$nulls":5},"1"]
["1","09","02","02","02","  ","Title 2 Design                                              ",{"$nulls":5},3388491.45,3041669.44,2978242.81,-346822.01,63426.62999999989,{"$nulls":5},"1"]
["1","09","02","03","  ","  ","A & E Services - (S20, MMF,MCC)                             "]
["1","09","02","03","01","  ","Title 1 Design (Sector 20)                                  ",{"$nulls":5},2120,2120,0,0,2120,{"$nulls":5},"1"]
["1","09","02","03","02","  ","Title 2 Design (Sector 20)                                  ",{"$nulls":5},91725.06,91725.06,100759.09,0,-9034.03,{"$nulls":5},"1"]
["1","09","02","03","03","  ","Title 1 Design (MMF)                                        ",{"$nulls":5},37895,37895,37895,0,0,{"$nulls":5},"1"]
["1","09","02","03","04","  ","Title 2 Design (MMF)                                        ",{"$nulls":5},150519.05,150519.05,149226.8,0,1292.25,{"$nulls":5},"1"]
["1","09","02","03","05","  ","Title 1 Design (MCC)                                        "]
["1","09","02","03","06","  ","Title 2 Design (MCC)                                        "]
["1","09","03","  ","  ","  ","Construction-T3 Conventional Facilities                     "]
["1","09","03","01","  ","  ","Sector 20 Injector Facilities                               "]
["1","09","03","01","01","  ","S20 - Site Preparation/General Requirements                 ",{"$nulls":5},451077.56,431132.45,408758.03,-19945.11,22374.42,{"$nulls":5},"1"]
["1","09","03","01","02","  ","S20 - Site Construction                                     ",{"$nulls":5},100680.9,113823.51,95512.44,13142.61,18311.07,{"$nulls":5},"1"]
["1","09","03","01","03","  ","S20 - Concrete                                              ",{"$nulls":5},138987.64,143227.64,210961.74,4240,-67734.1,{"$nulls":5},"1"]
["1","09","03","01","04","  ","S20 - Masonry                                               ",{"$nulls":7},185.59,0,-185.59,{"$nulls":5},"1"]
["1","09","03","01","05","  ","S20 - Metals                                                ",{"$nulls":5},212424.44,224904.43,212267.61,12479.99,12636.82,{"$nulls":5},"1"]
["1","09","03","01","06","  ","S20 - Woods & Plastics                                      ",{"$nulls":5},14450,14450,14450.11,0,-0.11000000000058208,{"$nulls":5},"1"]
["1","09","03","01","07","  ","S20 - Thermal & Moisture Protection                         ",{"$nulls":5},131680,26035.8,26596.02,-105644.2,-560.2200000000012,{"$nulls":5},"1"]
["1","09","03","01","08","  ","S20 - Doors & Windows                                       ",{"$nulls":5},22634,6016.8,3163.4,-16617.2,2853.4,{"$nulls":5},"1"]
["1","09","03","01","09","  ","S20 - Finishes                                              ",{"$nulls":5},55444,31744,29687.61,-23700,2056.39,{"$nulls":5},"1"]
["1","09","03","01","10","  ","S20 - Specialties                                           "]
["1","09","03","01","14","  ","S20 - Conveying Systems                                     ",{"$nulls":7},7.66,0,-7.66,{"$nulls":5},"1"]
["1","09","03","01","15","  ","S20 - Mechanical                                            ",{"$nulls":5},607741.75,298897.22,246434.24,-308844.53,52462.98,{"$nulls":5},"1"]
["1","09","03","01","16","  ","S20 - Electrical                                            ",{"$nulls":5},475863.74,344743.58,282170.66,-131120.16,62572.92,{"$nulls":5},"1"]
["1","09","03","01","20","  ","S20 - Project Close Out                                     "]
["1","09","03","02","  ","  ","Magnetic Measurement Facility                               "]
["1","09","03","02","01","  ","MMF - Site Preparation/General Requirements                 ",{"$nulls":5},360523.33,356671.31,355905.63,-3852.0200000000186,765.679999999993,{"$nulls":5},"1"]
["1","09","03","02","02","  ","MMF - Site Construction                                     ",{"$nulls":5},56710.36,75790.36,50219.03,19080,25571.33,{"$nulls":5},"1"]
["1","09","03","02","03","  ","MMF - Concrete                                              ",{"$nulls":5},152375,160855,149258.29,8480,11596.71,{"$nulls":5},"1"]
["1","09","03","02","04","  ","Utilities                                                   "]
["1","09","03","02","05","  ","MMF - Metals                                                ",{"$nulls":5},138375,138375,141969.15,0,-3594.149999999994,{"$nulls":5},"1"]
["1","09","03","02","06","  ","MMF - Woods & Plastics                                      ",{"$nulls":5},12113.68,12113.68,11806.77,0,306.91,{"$nulls":5},"1"]
["1","09","03","02","07","  ","MMF - Thermal & Moisture Protection                         ",{"$nulls":5},71264,8652.8,-43.88,-62611.2,8696.68,{"$nulls":5},"1"]
["1","09","03","02","08","  ","MMF - Doors & Windows                                       ",{"$nulls":5},28818,null,-11.75,-28818,11.75,{"$nulls":5},"1"]
["1","09","03","02","09","  ","MMF - Finishes                                              ",{"$nulls":5},167510,120060,127313.96,-47450,-7253.960000000006,{"$nulls":5},"1"]
["1","09","03","02","10","  ","MMF - Specialities                                          ",{"$nulls":5},745,null,11.44,-745,-11.44,{"$nulls":5},"1"]
["1","09","03","02","14","  ","MMF - Conveying Systems                                     ",{"$nulls":5},180000,48600,37479.27,-131400,11120.73,{"$nulls":5},"1"]
["1","09","03","02","15","  ","MMF - Mechanical                                            ",{"$nulls":5},939822.76,534533.87,451821.12,-405288.89,82712.75,{"$nulls":5},"1"]
["1","09","03","02","16","  ","MMF - Electrical                                            ",{"$nulls":5},231205,104585,80967.99,-126620,23617.01,{"$nulls":5},"1"]
["1","09","03","02","20","  ","MMF - Project Close Out                                     "]
["1","09","03","04","  ","  ","Linac Facility Upgrade (LN)                                 "]
["1","09","03","04","01","  ","LN - Site Preparation                                       ",{"$nulls":5},-403.81,null,null,403.81,0,{"$nulls":5},"1"]
["1","09","03","04","02","  ","Site Construction                                           "]
["1","09","03","04","03","  ","Electrical                                                  "]
["1","09","03","04","04","  ","Utilities                                                   "]
["1","09","03","04","05","  ","Linac - Metals                                              ",{"$nulls":5},93184.6,93184.6,109574.28,0,-16389.68,{"$nulls":5},"1"]
["1","09","03","04","06","  ","Special System - Fire Protection                            "]
["1","09","03","04","10","  ","Project Close Out Linac Facility                            "]
["1","09","03","04","20","  ","LN - Project Close Out                                      "]
["1","09","03","05","  ","  ","Research Yard/B102,B211,B113 & Storage Trailers             "]
["1","09","03","05","01","  ","RY - Site Preparation                                       ",{"$nulls":5},-7225.18,3087.12,null,10312.3,3087.12,{"$nulls":5},"1"]
["1","09","03","05","01","01","General Requirements- CEF                                   "]
["1","09","03","05","01","02","General Requirements - G/C                                  "]
["1","09","03","05","02","  ","RY - FFTB/BSY & Site Construction                           ",{"$nulls":5},185500,185760.86,157547.05,260.85999999998603,28213.81,{"$nulls":5},"1"]
["1","09","03","05","02","01","Site Construction - CEF                                     "]
["1","09","03","05","02","02","Site Construction - G/C                                     "]
["1","09","03","05","03","  ","Electrical                                                  "]
["1","09","03","05","03","01","Electrical CEF                                              "]
["1","09","03","05","03","02","Electrical G/C                                              "]
["1","09","03","05","04","  ","Utilities                                                   "]
["1","09","03","05","04","01","Utilities CEF                                               "]
["1","09","03","05","04","02","Utilities G/C                                               "]
["1","09","03","05","05","  ","RY - Metals                                                 "]
["1","09","03","05","05","01","HVAC CEF                                                    "]
["1","09","03","05","05","02","HVAC G/C                                                    "]
["1","09","03","05","06","  ","Special System - Fire Protection                            "]
["1","09","03","05","06","01","Special System - Fire Protection CEF                        "]
["1","09","03","05","06","02","Special System - Fire Protection                            "]
["1","09","03","05","07","  ","Interior                                                    "]
["1","09","03","05","07","01","Interior CEF                                                "]
["1","09","03","05","07","02","Interior G/C                                                "]
["1","09","03","05","10","  ","Project Close Out Reasearch Yard                            "]
["1","09","03","05","20","  ","RY - Project Close Out                                      "]
["1","09","03","06","  ","  ","Access Road Construction (AR)                               "]
["1","09","03","06","01","  ","AR - Site Preparation/General Requirements                  "]
["1","09","03","06","02","  ","AR - Site Construction                                      "]
["1","09","03","06","03","  ","AR - Concrete                                               "]
["1","09","03","06","04","  ","Utilities                                                   "]
["1","09","03","06","05","  ","HVAC                                                        "]
["1","09","03","06","06","  ","Special System- Fire Protection                             "]
["1","09","03","06","07","  ","Interior                                                    "]
["1","09","03","06","10","  ","Project Close Out  Beam Trans Hall                          "]
["1","09","03","06","20","  ","AR - Project Close Out                                      "]
["1","09","03","07","  ","  ","SITEWORK - CLOC Beautification                              "]
["1","09","03","07","01","  ","SW - Site Preparation/General Requirements                  "]
["1","09","03","07","02","  ","SW - Site Construction                                      "]
["1","09","03","07","03","  ","SW - Concrete                                               "]
["1","09","03","07","04","  ","Utilities                                                   "]
["1","09","03","07","05","  ","HVAC                                                        "]
["1","09","03","07","06","  ","Special System - Fire Protection                            "]
["1","09","03","07","07","  ","Interior                                                    "]
["1","09","03","07","09","  ","Tunneling                                                   "]
["1","09","03","07","10","  ","Project Close Out Undulator Hall                            "]
["1","09","03","07","15","  ","SW - Mechanical                                             "]
["1","09","03","07","16","  ","SW - Electrical                                             "]
["1","09","03","07","17","  ","SW - Others (include Div 4, and 6 through 14)               "]
["1","09","03","07","20","  ","SW - Project Close Out                                      "]
["1","09","03","08","  ","  ","Beam Transport Hall (BTH)                                   "]
["1","09","03","08","01","  ","BTH - Site Preparation/General Requirements                 "]
["1","09","03","08","02","  ","BTH - Site Construction                                     "]
["1","09","03","08","03","  ","BTH - Concrete                                              "]
["1","09","03","08","04","  ","Utilities                                                   "]
["1","09","03","08","05","  ","BTH - Metals                                                "]
["1","09","03","08","06","  ","Special System - Fire Protection                            "]
["1","09","03","08","07","  ","Interior                                                    "]
["1","09","03","08","09","  ","Tunneling                                                   "]
["1","09","03","08","10","  ","Project Close Out Front End Enclosure                       "]
["1","09","03","08","15","  ","BTH - Mechanical                                            "]
["1","09","03","08","16","  ","BTH - Electrical                                            "]
["1","09","03","08","17","  ","BTH - Others (include Div 4, and 6 through 14)              "]
["1","09","03","08","20","  ","BTH - Project Close Out                                     "]
["1","09","03","09","  ","  ","Front End Enclosure (FEE)                                   "]
["1","09","03","09","01","  ","FEE - Site Preparation/General Requirements                 "]
["1","09","03","09","02","  ","FEE - Site Construction                                     "]
["1","09","03","09","03","  ","FEE - Concrete                                              "]
["1","09","03","09","04","  ","Utilities                                                   "]
["1","09","03","09","05","  ","FEE - Metals                                                "]
["1","09","03","09","06","  ","Special System (Fire Protection) Beam Dump                  "]
["1","09","03","09","09","  ","Tunneling                                                   "]
["1","09","03","09","10","  ","Project Close Out Beam Dump                                 "]
["1","09","03","09","15","  ","FEE - Mechanical                                            "]
["1","09","03","09","16","  ","FEE - Electrical                                            "]
["1","09","03","09","17","  ","FEE - Others (include Div 4, and 6 through 14)              "]
["1","09","03","09","20","  ","FEE - Project Close Out                                     "]
["1","09","03","10","  ","  ","Electron Beam Dump (EBD)                                    "]
["1","09","03","10","01","  ","EBD - Site Preparation/General Requirements                 "]
["1","09","03","10","02","  ","EBD - Site Construction                                     "]
["1","09","03","10","03","  ","EBD - Concrete                                              "]
["1","09","03","10","04","  ","Utilities                                                   "]
["1","09","03","10","05","  ","EBD - Metals                                                "]
["1","09","03","10","06","  ","Special System - Fire Protection                            "]
["1","09","03","10","07","  ","Interior                                                    "]
["1","09","03","10","10","  ","Project Close Out Near Experimental Hall                    "]
["1","09","03","10","15","  ","EBD - Mechanical                                            "]
["1","09","03","10","16","  ","EBD - Electrical                                            "]
["1","09","03","10","17","  ","EBD - Others (include Div 4, and 6 through 14)              "]
["1","09","03","10","20","  ","EBD - Project Close Out                                     "]
["1","09","03","11","  ","  ","Near Experimental Hall (NEH)                                "]
["1","09","03","11","01","  ","NEH - Site Preparation/General Requirements                 "]
["1","09","03","11","02","  ","NEH - Site Construction                                     "]
["1","09","03","11","03","  ","NEH - Concrete                                              "]
["1","09","03","11","04","  ","Utilities                                                   "]
["1","09","03","11","05","  ","NEH - Metals                                                "]
["1","09","03","11","06","  ","Special System - Fire Protection                            "]
["1","09","03","11","07","  ","Interiors                                                   "]
["1","09","03","11","09","  ","Tunneling                                                   "]
["1","09","03","11","10","  ","Project Close Out X-Ray Transport & Diagonistic             "]
["1","09","03","11","15","  ","NEH - Mechanical                                            "]
["1","09","03","11","16","  ","NEH - Electrical                                            "]
["1","09","03","11","17","  ","NEH - Others (include Div 4, and 6 through 14)              "]
["1","09","03","11","20","  ","NEH - Project Close Out                                     "]
["1","09","03","12","  ","  ","Undulator Hall (UH)                                         "]
["1","09","03","12","01","  ","UH - Site Preparation/General Requirements                  "]
["1","09","03","12","02","  ","UH - Site Construction                                      "]
["1","09","03","12","03","  ","UH - Concrete                                               "]
["1","09","03","12","04","  ","Utilities                                                   "]
["1","09","03","12","05","  ","UH - Metals                                                 "]
["1","09","03","12","06","  ","Special System - Fire Protection                            "]
["1","09","03","12","07","  ","Interiors                                                   "]
["1","09","03","12","09","  ","Tunneling                                                   "]
["1","09","03","12","10","  ","Project Close Out Far Experimental Hall                     "]
["1","09","03","12","15","  ","UH - Mechanical                                             "]
["1","09","03","12","16","  ","UH - Electrical                                             "]
["1","09","03","12","17","  ","UH - Others (include Div 4, and 6 through 14)               "]
["1","09","03","12","19","  ","UH - Tunnel Construction                                    "]
["1","09","03","12","20","  ","UH - Project Close Out                                      "]
["1","09","03","13","  ","  ","X-Ray - Transport & Diagnostic Hall (XRTD)                  "]
["1","09","03","13","01","  ","XRTD - Site Preparation/General Requirements                "]
["1","09","03","13","02","  ","XRTD - Site Construction                                    "]
["1","09","03","13","03","  ","XRTD - Concrete                                             "]
["1","09","03","13","04","  ","Utilities                                                   "]
["1","09","03","13","05","  ","HVAC                                                        "]
["1","09","03","13","06","  ","Special System - Fire Protection                            "]
["1","09","03","13","07","  ","Interior                                                    "]
["1","09","03","13","10","  ","Project Close Out Central Laboratory Office Complex (CLOC)  "]
["1","09","03","13","15","  ","XRTD - Mechanical                                           "]
["1","09","03","13","16","  ","XRTD - Electrical                                           "]
["1","09","03","13","17","  ","XRTD - Others (include Div 4, and 6 through 14)             "]
["1","09","03","13","19","  ","XRTD - Tunnel Construction                                  "]
["1","09","03","13","20","  ","XRTD - Project Close Out                                    "]
["1","09","03","14","  ","  ","Far Experimental Hall (FEH)                                 "]
["1","09","03","14","01","  ","FEH - Site Preparation/General Requirements                 "]
["1","09","03","14","02","  ","FEH - Site Construction                                     "]
["1","09","03","14","03","  ","FEH - Concrete                                              "]
["1","09","03","14","05","  ","FEH - Metals                                                "]
["1","09","03","14","15","  ","FEH - Mechanical                                            "]
["1","09","03","14","16","  ","FEH - Electrical                                            "]
["1","09","03","14","17","  ","FEH - Others (include Div 4, and 6 through 14)              "]
["1","09","03","14","18","  ","FEH - Access Tunnel                                         "]
["1","09","03","14","19","  ","FEH - Tunnel Construction                                   "]
["1","09","03","14","20","  ","FEH - Project Close Out                                     "]
["1","09","03","15","  ","  ","BTH Service Buildings 2.1, 2.2, and 2.3 (SB BTH)            "]
["1","09","03","15","03","  ","SB BTH - Concrete                                           "]
["1","09","03","15","05","  ","SB BTH - Metals                                             "]
["1","09","03","15","15","  ","SB BTH - Mechanical                                         "]
["1","09","03","15","16","  ","SB BTH - Electrical                                         "]
["1","09","03","15","17","  ","SB BTH - Others (include Div 4, and 6 through 14            "]
["1","09","03","15","20","  ","SB BTH - Project Close Out                                  "]
["1","09","03","16","  ","  ","UH Service Building 3.1 (SB UH)                             "]
["1","09","03","16","01","  ","SB UH - Site Preparation                                    "]
["1","09","03","16","03","  ","SB UH - Concrete                                            "]
["1","09","03","16","05","  ","SB UH - Metals                                              "]
["1","09","03","16","15","  ","SB UH - Mechanical                                          "]
["1","09","03","16","16","  ","SB UH - Electrical                                          "]
["1","09","03","16","17","  ","SB UH - Others (include Div 4, and 6 through 14)            "]
["1","09","03","16","20","  ","SB UH - Project Close Out                                   "]
["1","09","03","17","  ","  ","FEH Service Building 8.1 (FEH SB)                           "]
["1","09","03","17","01","  ","SB FEH - Site Preparation                                   "]
["1","09","03","17","03","  ","SB FEH - Concrete                                           "]
["1","09","03","17","05","  ","SB FEH - Metals                                             "]
["1","09","03","17","15","  ","SB FEH - Mechanical                                         "]
["1","09","03","17","16","  ","SB FEH - Electrical                                         "]
["1","09","03","17","17","  ","SB FEH - Others (include Div 4, and 6 through 14            "]
["1","09","03","17","20","  ","SB FEH - Project Close Out                                  "]
["1","09","03","18","  ","  ","NEH Central Utility Plant (CUP)                             "]
["1","09","03","18","01","  ","CUP - Site Preparation/General Requirements                 "]
["1","09","03","18","02","  ","CUP - Site Construction                                     "]
["1","09","03","18","03","  ","CUP - Concrete                                              "]
["1","09","03","18","05","  ","CUP - Metals                                                "]
["1","09","03","18","15","  ","CUP - Mechanical                                            "]
["1","09","03","18","16","  ","CUP - Electrical                                            "]
["1","09","03","18","17","  ","CUP - Others (include Div 4, and 6 through 14)              "]
["1","09","03","18","20","  ","CUP - Project Close Out                                     "]
["1","09","03","19","  ","  ","Central Laboratory Office Complex (CLOC)                    "]
["1","09","03","19","01","  ","CLOC - Site Preparation/General Requirements                "]
["1","09","03","19","02","  ","CLOC - Sitework                                             "]
["1","09","03","19","03","  ","CLOC - Concrete                                             "]
["1","09","03","19","04","  ","CLOC - Masonry                                              "]
["1","09","03","19","05","  ","CLOC - Metals                                               "]
["1","09","03","19","06","  "," CLOC - Woods & Plastics                                    "]
["1","09","03","19","07","  ","CLOC - Thermal & Moisture Protection                        "]
["1","09","03","19","08","  ","CLOC - Doors & Windows                                      "]
["1","09","03","19","09","  ","CLOC - Finishes                                             "]
["1","09","03","19","10","  ","CLOc - Specialties                                          "]
["1","09","03","19","11","  ","CLOC - Equipment                                            "]
["1","09","03","19","12","  ","CLOc - Furnishings                                          "]
["1","09","03","19","13","  ","CLOc - Special Construction                                 "]
["1","09","03","19","14","  ","CLOC - Conveying Systems                                    "]
["1","09","03","19","15","  ","CLOC - Mechanical                                           "]
["1","09","03","19","16","  ","CLOC - Electrical                                           "]
["1","09","03","19","17","  ","CLOC - Others (include Div 4, and 9 through 14)             "]
["1","09","03","19","20","  ","CLOC - Project Close Out                                    "]
["2","  ","  ","  ","  ","  ","LCLS PROJECT - R&D, SPARES, COMMISSIONING                   "]
["2","01","  ","  ","  ","  ","LCLS PROJECT MGMT, PLANNING & ADMN (OPC)                    "]
["2","01","01","  ","  ","  ","Physics Support (OPC)                                       "]
["2","01","01","01","  ","  ","SAC-MAC Physics                                             ",{"$nulls":5},571229.43,571229.43,520769.75,0,50459.68000000005,{"$nulls":5},"1"]
["2","01","01","02","  ","  ","Injector Physics                                            ",{"$nulls":5},382064.12,382064.12,424067.48,0,-42003.36,{"$nulls":5},"1"]
["2","01","01","03","  ","  ","Linac Physics                                               ",{"$nulls":5},264885.1,264885.1,322200.67,0,-57315.57,{"$nulls":5},"1"]
["2","01","01","04","  ","  ","Undulator Physics                                           ",{"$nulls":5},277220.49,277220.49,312974.29,0,-35753.8,{"$nulls":5},"1"]
["2","01","01","05","  ","  ","X-Ray Transport Physics                                     ",{"$nulls":5},85051.43,85051.43,75247.53,0,9803.899999999994,{"$nulls":5},"1"]
["2","01","01","06","  ","  ","X-Ray Endstation Physics                                    ",{"$nulls":5},104902.44,104902.44,103630.81,0,1271.63,{"$nulls":5},"1"]
["2","01","01","07","  ","  ","Conventional Facilities Physics                             ",{"$nulls":5},315988.58,331936.09,349059.79,15947.51,-17123.7,{"$nulls":5},"1"]
["2","01","01","08","  ","  ","Consulting Physics (Collaboration)                          ",{"$nulls":5},385677.33,385677.33,470664.03,0,-84986.7,{"$nulls":5},"1"]
["2","01","01","09","  ","  ","Consulting Physics (SLAC)                                   ",{"$nulls":5},177720.65,177720.65,162130.65,0,15590,{"$nulls":5},"1"]
["2","01","01","10","  ","  ","Global Controls Physics Liaison                             ",{"$nulls":5},289356.33,374304.49,313900.08,84948.16,60404.41,{"$nulls":5},"1"]
["2","01","01","11","  ","  ","Global Controls OPC                                         "]
["2","01","01","11","01","  ","EPICS Control Modules                                       ",{"$nulls":5},0,0,0,0,0,{"$nulls":5},"1"]
["2","01","01","11","02","  ","LLRF Controls                                               ",{"$nulls":5},3729.24,3729.24,3729.24,0,0,{"$nulls":5},"1"]
["2","01","01","11","03","  ","E-beam Diagnostics & Controls                               "]
["2","01","01","11","04","  ","Laser Controls Design                                       "]
["2","01","01","11","05","  ","Laser Heater Controls Design                                "]
["2","01","01","11","06","  ","Timing Controls                                             "]
["2","01","01","11","07","  ","Vacuum Controls                                             "]
["2","01","01","11","08","  ","S/W & Controls Infrastructure                               "]
["2","01","01","11","09","  ","Power Supply Control                                        "]
["2","01","01","11","10","  ","MPS/PPS/BCS Controls                                        "]
["2","01","01","11","11","  ","Global Controls Commissioning                               "]
["2","01","01","11","12","  ","Global Controls Management - OPC                            ",{"$nulls":5},36339.33,21078.69,21078.69,-15260.64,0,{"$nulls":5},"1"]
["2","01","01","11","13","  ","SLC Aware IOC                                               ",{"$nulls":5},115704.39,115704.39,115704.39,0,0,{"$nulls":5},"1"]
["2","01","02","  ","  ","  ","R&D Studies & Prototyping                                   "]
["2","01","02","01","  ","  ","R&D Studies & Prototyping                                   ",{"$nulls":5},122096.73,122096.73,50577.15,0,71519.58,{"$nulls":5},"1"]
["2","01","03","  ","  ","  ","Project Mgmnt, Planning and Admn - M&S (OPC)                "]
["2","01","03","01","  ","  ","SLAC Project Office - General (R&D)                         ",{"$nulls":5},1716162.8,1716162.8,1720555.44,0,-4392.639999999898,{"$nulls":5},"1"]
["2","01","03","02","  ","  ","SLAC Project Support (R&D)                                  "]
["2","01","03","03","  ","  ","Project Mgmnt, Planning and Admn - M&S (OPC)                "]
["2","01","03","05","  ","  ","X-Ray Transport Physics                                     "]
["2","01","03","06","  ","  ","X-Ray Endstation Physics                                    "]
["2","01","03","07","  ","  ","Conventional Facilities Physics                             "]
["2","01","03","08","  ","  ","Consulting Physics (Collaboration)                          "]
["2","01","03","09","  ","  ","Consulting Physics (SLAC)                                   "]
["2","01","03","10","  ","  ","Global Controls Physics Liaison                             "]
["2","01","03","11","  ","  "," Physics Commissioning Support - General                    "]
["2","02","  ","  ","  ","  ","INJECTOR SYSTEM (OPC)                                       "]
["2","02","01","  ","  ","  ","Injector System Management & Integration                    "]
["2","02","01","01","  ","  ","Injector System Integration Effort / M&S                    "]
["2","02","01","02","  ","  ","High level Application Software                             "]
["2","02","01","03","  ","  ","Feedback Software                                           "]
["2","02","02","  ","  ","  ","Injector Controls Subsystem                                 "]
["2","02","02","01","  ","  ","Personnel Protection System (PPS) R&D                       ",{"$nulls":5},132935.71,90051.17,82359.84,-42884.54,7691.33,{"$nulls":5},"1"]
["2","02","02","02","  ","  ","Beam Containment Subsystem (BCS)                            "]
["2","02","02","03","  ","  ","Machine Protection Subsystem (MPS)                          "]
["2","02","02","04","  ","  ","Power Conv (beamline pwr supp) Spares                       "]
["2","02","02","04","01","  ","Power Supply Controls                                       "]
["2","02","02","05","  ","  ","LLRF Controls                                               "]
["2","02","02","06","  ","  ","E-Beam Diagnostics Controls                                 "]
["2","02","02","06","01","  ","Controls - Wire Scanners                                    "]
["2","02","02","06","02","  ","Controls - BPM Processor Module                             "]
["2","02","02","06","03","  ","Controls - Toroids                                          "]
["2","02","02","06","05","  ","Controls - Profile Monitors                                 "]
["2","02","02","06","06","  ","Control - EO Diagnostic                                     "]
["2","02","02","06","14","  ","Controls - Faraday Cup                                      "]
["2","02","02","06","15","  ","Controls - Tune-Up Dump                                     "]
["2","02","02","08","  ","  ","Timing Controls                                             "]
["2","02","02","09","  ","  ","Vacuum Controls                                             "]
["2","02","02","10","  ","  ","Software & Controls Infrastructure                          "]
["2","02","02","11","  ","  ","EPICS VXI Control Modules                                   "]
["2","02","02","12","  ","  ","Laser Controls                                              "]
["2","02","02","13","  ","  ","Laser Heater Controls                                       "]
["2","02","03","  ","  ","  ","Injector Lasers                                             "]
["2","02","03","01","  ","  ","Drive Laser Prototyping                                     ",{"$nulls":5},180472.14,180063.31,161401.12,-408.8300000000163,18662.19,{"$nulls":5},"1"]
["2","02","03","02","  ","  ","Drive Laser System                                          "]
["2","02","03","03","  ","  ","Drive Laser Diagnostics                                     "]
["2","02","03","04","  ","  ","Timing Stability Monitoring                                 ",{"$nulls":7},0,0,0,{"$nulls":5},"1"]
["2","02","03","05","  ","  ","Steering Stability Feedback & Msmts                         "]
["2","02","03","06","  ","  ","Pre Amp Low Power Comp                                      "]
["2","02","03","07","  ","  ","Transport to Tunnel & Relay Optics                          "]
["2","02","03","08","  ","  ","UV Launch, Conditioning & Diagnostics                       "]
["2","02","03","09","  ","  ","Load Lock Transport System                                  "]
["2","02","03","10","  ","  ","Visible Optical Transport & Optics                          "]
["2","02","03","11","  ","  ","LB Infrastructure & LB System Wide Items                    "]
["2","02","03","12","  ","  ","Alignment Laser                                             "]
["2","02","03","13","  ","  ","Light path to Streak Camera                                 "]
["2","02","03","14","  ","  ","LSR HTR - Beam Conditioning Optics (Laser Bay)              "]
["2","02","03","15","  ","  ","LSR HTR - Transport Optics (Bay to Tunnel)                  "]
["2","02","03","16","  ","  ","LSR HTR - Photon Beam Diagnostics                           "]
["2","02","04","  ","  ","  ","Injector RF Subsystem                                       "]
["2","02","04","01","  ","  ","RF Gun & Load Lock                                          "]
["2","02","04","01","01","  ","RF Gun                                                      ",{"$nulls":5},383537.3,366016.94,391350.14,-17520.36,-25333.2,{"$nulls":5},"1"]
["2","02","04","01","02","  ","RF Gun Supports                                             "]
["2","02","04","01","03","  ","Gun Load Lock                                               "]
["2","02","04","01","04","  ","Gun Load Lock Supports                                      "]
["2","02","04","01","05","  ","Gun Solenoid                                                "]
["2","02","04","01","06","  ","Gun Solenoid Supports                                       "]
["2","02","04","01","07","  ","Gun RF Feed                                                 "]
["2","02","04","01","08","  ","Gun RF Feed Supports                                        "]
["2","02","04","02","  ","  ","Cathode Processing (CP) Station                             "]
["2","02","04","02","01","  ","CP Cathode Assembly & Supports                              "]
["2","02","04","02","02","  ","CP Load Lock                                                "]
["2","02","04","02","03","  ","CP Load Lock Supports                                       "]
["2","02","04","02","04","  ","CP Station                                                  "]
["2","02","04","02","05","  ","Cathode Lab Infrastructure                                  "]
["2","02","04","03","  ","  ","S-Band Low Level System                                     "]
["2","02","04","03","01","  ","S-Band LL Controls Timing System                            "]
["2","02","04","04","  ","  ","S-Band High Power System                                    "]
["2","02","04","05","  ","  ","Injector RF Waveguide Subsystem                             "]
["2","02","04","05","01","  ","RF Waveguides                                               "]
["2","02","04","05","02","  ","RF Waveguide Supports                                       "]
["2","02","04","06","  ","  ","Injector Linac Structures                                   "]
["2","02","04","06","01","  ","L0-1 Structure Assembly                                     "]
["2","02","04","06","02","  ","L0-2 Structure Assembly                                     "]
["2","02","04","06","03","  ","Major Linac Support                                         "]
["2","02","04","06","04","  ","GTL RF Phase Cavity                                         "]
["2","02","04","06","05","  ","LTDL1 RF Kicker                                             "]
["2","02","05","  ","  ","  ","Injector Magnets & Supports                                 "]
["2","02","05","01","  ","  ","Injector Dipoles                                            "]
["2","02","05","01","01","  ","DL1 B01 & B02 Dipoles                                       "]
["2","02","05","01","02","  ","SAB Spectrometer Dipole                                     "]
["2","02","05","01","03","  ","Chicane                                                     "]
["2","02","05","02","  ","  ","Injector Quadrupoles                                        "]
["2","02","05","02","01","  ","L0-1TL0-2 Quadrupoles ( )                                   "]
["2","02","05","02","02","  ","LTDL1 Quadrupoles ( )                                       "]
["2","02","05","02","03","  ","DL1 QB Quadrupole                                           "]
["2","02","05","02","04","  ","DL1TL Quadrupoles ( )                                       "]
["2","02","05","02","05","  ","SAB Quadrupoles ( )                                         "]
["2","02","05","03","  ","  ","Injector Steering Coils                                     "]
["2","02","05","03","01","  ","GTL Steering Coils ( )X-Y (SC1)                             "]
["2","02","05","03","02","  ","L0-1TL0-2 Linac Steering Coils ( )                          "]
["2","02","05","03","03","  ","LTDL1 Steering Coils ( )X-Y                                 "]
["2","02","05","03","04","  ","DL1TL Steering Coils ( X-Y Assys)                           "]
["2","02","05","03","05","  ","SAB Steering Coils ( )                                      "]
["2","02","05","04","  ","  ","Linac Solenoid & Supports                                   "]
["2","02","05","05","  ","  ","Injector Laser Heater Subsystem                             "]
["2","02","05","05","01","  ","System Design & Optimization                                "]
["2","02","05","05","02","  ","Undulator                                                   "]
["2","02","06","  ","  ","  ","Injector Vacuum & Supports                                  "]
["2","02","06","01","  ","  ","GTL Vacuum Components                                       "]
["2","02","06","02","  ","  ","GTL Supports                                                "]
["2","02","06","03","  ","  ","GTL Pumping & Optic Chamber                                 "]
["2","02","06","04","  ","  ","L0-1TL0-2 Vacuum Components                                 "]
["2","02","06","05","  ","  ","L0-1TL0-2 Major tube support structure                      "]
["2","02","06","06","  ","  ","LTDL1 Minor Tube Supports                                   "]
["2","02","06","07","  ","  ","DL1 Supports                                                "]
["2","02","06","08","  ","  ","DL1 Vacuum Chamber                                          "]
["2","02","06","09","  ","  ","DL1TL Vacuum Components                                     "]
["2","02","06","10","  ","  ","SAB Vacuum Chamber and Components                           "]
["2","02","06","11","  ","  ","SAB Supports                                                "]
["2","02","07","  ","  ","  ","Injector Diagnostics                                        "]
["2","02","07","01","  ","  ","Injector Beam Position Monitors                             "]
["2","02","07","01","01","  ","GTL BPMs ( )                                                "]
["2","02","07","01","02","  ","Gun Spectrometer (GS) Assembly                              "]
["2","02","07","01","03","  ","L0-1TL0-2 BPMs ( )                                          "]
["2","02","07","01","04","  ","LTDL1 BPMs ( )                                              "]
["2","02","07","01","05","  ","DL1TL BPMs ( )                                              "]
["2","02","07","01","06","  ","SAB BPM ( )                                                 "]
["2","02","07","02","  ","  ","Injector Current Monitors                                   "]
["2","02","07","02","01","  ","GTL Current Monitors ( )                                    "]
["2","02","07","02","02","  ","L0-1TL0-2 Current Monitor ( )                               "]
["2","02","07","02","03","  ","LTDL1 Current Monitors ( )                                  "]
["2","02","07","02","04","  ","DL1TL Current Monitor ( )                                   "]
["2","02","07","02","05","  ","SAB Current Monitor ( )                                     "]
["2","02","07","03","  ","  ","Injector Bunch Length Monitors                              "]
["2","02","07","03","01","  ","GTL E/O (EO1)                                               "]
["2","02","07","03","02","  ","LTDL1 E/O EO2                                               "]
["2","02","07","03","03","  ","DL1TL EO3                                                   "]
["2","02","07","04","  ","  ","Injector Profile Monitors                                   "]
["2","02","07","04","01","  ","GTL Faraday Cup/YAG1                                        "]
["2","02","07","04","02","  ","GTL YAG ( )                                                 "]
["2","02","07","04","03","  ","L0-1TL0-2 OTR/YAG ( )                                       "]
["2","02","07","04","04","  ","LTDL1 OTR(5)/YAG ( )                                        "]
["2","02","07","04","05","  ","DL1 OTR                                                     "]
["2","02","07","04","06","  ","DL1TL OTR                                                   "]
["2","02","07","04","07","  ","SAB YAG                                                     "]
["2","02","07","04","08","  ","SAB Beam Dump and Shielding                                 "]
["2","02","07","05","  ","  ","Injector Wire Scanners                                      "]
["2","02","07","05","01","  ","LTDL1 Wire Scanners ( )                                     "]
["2","02","07","05","02","  ","DL1 Wire Scanner                                            "]
["2","02","07","06","  ","  ","LSR HTR - Electron Beam Diagnostics                         "]
["2","02","07","07","  ","  ","PPS Stopper                                                 "]
["2","02","17","  ","  ","  ","Injector System Commissioning                               "]
["2","02","17","01","  ","  ","Controls Commissioning                                      "]
["2","02","17","02","  ","  ","Drive Laser Commissioning                                   "]
["2","02","17","03","  ","  ","RF Conditioning                                             "]
["2","02","17","04","  ","  ","RF Gun Operation with Beam                                  "]
["2","02","17","05","  ","  ","L0-1&L0-2 Commissioning                                     "]
["2","02","17","06","  ","  ","L0&SAB Commissioning                                        "]
["2","02","17","07","  ","  ","DL1 Commissioning                                           "]
["2","02","17","08","  ","  ","Injector Optimization                                       "]
["2","03","  ","  ","  ","  ","LINAC SYSTEM (OPC)                                          "]
["2","03","01","  ","  ","  ","Linac System Mgmt & Integration                             "]
["2","03","01","01","  ","  ","Linac System Mgmt & Integration                             "]
["2","03","01","02","  ","  ","Linac Controls Integration                                  "]
["2","03","01","03","  ","  ","Travel                                                      "]
["2","03","01","04","  ","  ","Linac Management                                            "]
["2","03","02","  ","  ","  ","Linac Controls & Power Conversion Subsystem                 "]
["2","03","02","01","  ","  ","Personnel Protection System (PPS)                           "]
["2","03","02","02","  ","  ","Beam Containment System (BCS)                               "]
["2","03","02","03","  ","  ","Machine Protection System (MPS)                             "]
["2","03","02","04","  ","  ","Power Conversion                                            "]
["2","03","02","04","01","  ","Spare Power Supply (Dipole Type)                            "]
["2","03","02","04","02","  ","Spare Power Supply (Quad Type)                              "]
["2","03","02","04","03","  ","Spare Power Supply (Trim Type)                              "]
["2","03","02","04","04","  ","Controls & Power Supply - Spare Misc Hdwr                   "]
["2","03","02","05","  ","  ","Controls - LLRF                                             "]
["2","03","02","06","  ","  ","Controls - E-Beam Diagnostic                                "]
["2","03","02","07","  ","  ","Controls - Laser                                            "]
["2","03","02","08","  ","  ","Controls - Timing                                           "]
["2","03","02","09","  ","  ","Controls - Vacuum                                           "]
["2","03","02","10","  ","  ","Software & Controls Infrastructure                          "]
["2","03","03","  ","  ","  ","Linac Magnets & Supports                                    "]
["2","03","03","01","  ","  ","Bend Magnet (BX1_BC1)                                       "]
["2","03","03","02","  ","  ","Bend Magnet (BX3_LTU)                                       "]
["2","03","03","03","  ","  ","Bend Magnet (BX2_BC2)                                       "]
["2","03","03","04","  ","  ","Bend Magnet (BY_LTU)                                        "]
["2","03","03","05","  ","  ","Quad Magnet (Quad_LTU)                                      "]
["2","03","03","07","  ","  ","Quad Magnet (QE)                                            "]
["2","03","03","08","  ","  ","Corrector Magnet (Type 4)                                   "]
["2","03","03","09","  ","  ","Bend Magnet (BYD_LTU)                                       "]
["2","03","03","10","  ","  ","Quad Magnet (QA)                                            "]
["2","03","03","11","  ","  ","Bend Magnet (BYPM_LTU)                                      "]
["2","03","03","12","  ","  ","Bend Magnet (BYKIK_LTU)                                     "]
["2","03","03","13","  ","  ","Bend Magnet (BYW_LTU)                                       "]
["2","03","04","  ","  ","  ","Linac Vacuum Subsystem                                      "]
["2","03","04","01","  ","  ","Linac Vacuum Subsystem Operations Equip                     "]
["2","03","04","02","  ","  ","Linac Beamline Vacuum System                                "]
["2","03","04","03","  ","  ","BC1 Vacuum System                                           "]
["2","03","04","04","  ","  ","BC2 Vacuum System                                           "]
["2","03","04","05","  ","  ","Linac to Undulator (LTU) Vacuum System                      "]
["2","03","04","06","  ","  ","Dumpline Vacuum System                                      "]
["2","03","05","  ","  ","  ","Linac Electron Diagnostics                                  "]
["2","03","05","01","  ","  ","Wire Scanners                                               "]
["2","03","05","02","  ","  ","Beam Position Monitors                                      "]
["2","03","05","03","  ","  ","Toroids Beam Charge                                         "]
["2","03","05","04","  ","  ","Stoppers Tune Up Dump                                       "]
["2","03","05","05","  ","  ","Profile Monitors                                            ",{"$nulls":5},1177.47,1177.47,1177.47,0,0,{"$nulls":5},"1"]
["2","03","05","06","  ","  ","E/O Bunch Length Monitors                                   "]
["2","03","05","07","  ","  ","Bunch Length Monitors                                       "]
["2","03","05","08","  ","  ","Beam Loss Monitors                                          "]
["2","03","05","09","  ","  ","Single Beam Dump                                            "]
["2","03","05","10","  ","  ","Electron Safety Beam Dump                                   "]
["2","03","05","11","  ","  ","Protection Collimators                                      "]
["2","03","05","12","  ","  ","Movable Collimators                                         "]
["2","03","05","13","  ","  ","Safety Dump                                                 "]
["2","03","06","  ","  ","  ","Linac RF Subsystem                                          "]
["2","03","06","02","  ","  ","S-Band High Power System                                    "]
["2","03","06","03","  ","  ","S-Band Structures                                           "]
["2","03","06","04","  ","  ","X-Band Low Level System                                     "]
["2","03","06","05","  ","  ","X-Band High Power System                                    "]
["2","03","06","06","  ","  ","X-Band Structures                                           "]
["2","03","06","07","  ","  ","RF Distribution System                                      "]
["2","03","06","07","01","  ","Modulator                                                   "]
["2","03","06","07","02","  ","Solid State Sub Booster                                     "]
["2","03","06","07","05","  ","Bunch Length Electronics                                    "]
["2","03","06","07","07","  ","RF Distribution L2 & L3                                     "]
["2","03","06","07","08","  ","RF Fiber Optics Electronics                                 "]
["2","03","07","  ","  ","  ","Linac System Commissioning                                  "]
["2","03","07","01","  ","  ","Linac L01 System Commissioning                              "]
["2","03","07","02","  ","  ","Linac BC1 System Commissioning                              "]
["2","03","07","03","  ","  ","Linac L02 System Commissioning                              "]
["2","03","07","04","  ","  ","Linac BC2 System Commissioning                              "]
["2","03","07","05","  ","  ","Linac L03 System Commissioning                              "]
["2","03","07","06","  ","  ","Linac LTU System Commissioning                              "]
["2","03","07","07","  ","  ","Linac E-Dump System Commissioining                          "]
["2","04","  ","  ","  ","  ","UNDULATOR SYSTEM (OPC)                                      "]
["2","04","01","  ","  ","  ","Undulator System Management & Integration                   ",{"$nulls":5},338769.91,338769.91,369211.98,0,-30442.07,{"$nulls":5},"1"]
["2","04","01","01","  ","  ","Undulator System Mgmt & Integration                         "]
["2","04","02","  ","  ","  ","Controls                                                    "]
["2","04","02","01","  ","  ","Controls Management and Integration                         ",{"$nulls":5},36738.99,36738.99,41027.53,0,-4288.54,{"$nulls":5},"1"]
["2","04","02","04","  ","  ","Video                                                       ",{"$nulls":5},0,0,0,0,0,{"$nulls":5},"1"]
["2","04","02","07","  ","  ","Machine Protection                                          "]
["2","04","03","  ","  ","  ","Undulator Magnet & Support                                  "]
["2","04","03","02","  ","  ","First Prototype Undulator & Mfg Plan                        ",{"$nulls":5},10784.31,10784.31,10685.95,0,98.35999999999876,{"$nulls":5},"1"]
["2","04","03","04","  ","  ","Production Undulator                                        "]
["2","04","03","05","  ","  ","Focusing Magnets                                            "]
["2","04","03","06","  ","  ","Undulator Magnetic Measurement Facility (SLAC)              ",{"$nulls":5},27113.85,27113.85,26726.7,0,387.1499999999978,{"$nulls":5},"1"]
["2","04","03","08","  ","  ","Fixed Supports                                              "]
["2","04","04","  ","  ","  ","Vacuum System                                               "]
["2","04","04","02","  ","  ","Undulator Vacuum Chamber Assembly                           ",{"$nulls":5},212736.33,210268.24,222171.21,-2468.09,-11902.97,{"$nulls":5},"1"]
["2","04","04","02","01","  ","Surface Roughness Minimization                              "]
["2","04","04","02","03","  ","Materials Study for AC Conductivity                         "]
["2","04","04","03","  ","  ","Beam-line Bellows Module Assembly                           "]
["2","04","04","05","  ","  ","Short Diagnostic Break (SDB) Assembly                       "]
["2","04","04","06","  ","  ","Long Diagnostic Break (LDB) Assembly                        "]
["2","04","04","07","  ","  ","Entrance Section Assembly                                   "]
["2","04","04","08","  ","  ","Exit Section Assembly                                       "]
["2","04","04","09","  ","  ","Baking System                                               "]
["2","04","05","  ","  ","  ","Undulator System Diagnostics [OPC]                          "]
["2","04","05","02","  ","  ","Undulator Line Diagnostics                                  ",{"$nulls":5},80780.85,80780.85,78303.12,0,2477.7300000000105,{"$nulls":5},"1"]
["2","04","05","03","  ","  ","High-Power X-Ray and Profile Diagnostics (HPD)              "]
["2","04","05","04","  ","  ","End-of-Undulator(EOU) X-ray and Profile diagnost            ",{"$nulls":5},22326.95,22326.95,30338.06,0,-8011.11,{"$nulls":5},"1"]
["2","04","05","05","  ","  ","RFBPM                                                       ",{"$nulls":5},17559.44,17559.44,18281.41,0,-721.9700000000012,{"$nulls":5},"1"]
["2","04","05","06","  ","  ","Beam Finder Wire                                            "]
["2","04","05","07","  ","  ","Charge Monitor (CM)                                         "]
["2","04","05","08","  ","  ","Cherenkov Detector                                          "]
["2","04","05","09","  ","  ","Radiation Detection Monitor (RDM)                           "]
["2","04","06","  ","  ","  ","Undulator System Commissioning                              "]
["2","04","06","01","  ","  ","Undulator System Commissioning                              "]
["2","05","  ","  ","  ","  ","X-RAY TRANSPORT & DIAGNOSTICS SYSTEMS (OPC)                 "]
["2","05","01","  ","  ","  ","System Management & Integration                             "]
["2","05","01","01","  ","  ","Management                                                  ",{"$nulls":5},489366.87,489366.87,455710.29,0,33656.58,{"$nulls":5},"1"]
["2","05","02","  ","  ","  ","Controls                                                    "]
["2","05","02","01","  ","  ","Controls - EPICS                                            "]
["2","05","02","02","  ","  ","Controls - System                                           "]
["2","05","03","  ","  ","  ","Mechanical & Vacuum Subsystem                               "]
["2","05","03","01","  ","  ","Vacuum Systems Engineering                                  "]
["2","05","03","02","  ","  ","Mech/Vac Front End                                          "]
["2","05","03","03","  ","  ","Mech/Vac Near Hall                                          "]
["2","05","03","04","  ","  ","Mech/Vac Tunnel                                             "]
["2","05","03","05","  ","  ","Mech/Vac Far Hall                                           "]
["2","05","04","  ","  ","  ","Optical Subsystem                                           "]
["2","05","04","01","  ","  ","Optical Systems Engineering                                 "]
["2","05","04","02","  ","  ","Facility Optics                                             "]
["2","05","04","03","  ","  ","End Station Optics                                          "]
["2","05","04","04","  ","  ","Crystals & Gratings                                         "]
["2","05","05","  ","  ","  ","Diagnostics Subsystem                                       "]
["2","05","05","01","  ","  ","Diagnostic Systems Engineering                              "]
["2","05","05","02","  ","  ","Modeling & Simulation                                       ",{"$nulls":5},0,0,0,0,0,{"$nulls":5},"1"]
["2","05","05","03","  ","  ","Facility Diagnostics                                        "]
["2","05","05","04","  ","  ","Commissioning Diagnostics                                   ",{"$nulls":5},0,0,0,0,0,{"$nulls":5},"1"]
["2","05","06","  ","  ","  ","X-Ray Transport & Diag. System Commissioning                "]
["2","05","06","01","  ","  ","X-Ray Transport & Diag. System Commissioning                "]
["2","06","  ","  ","  ","  ","X-RAY END STATION SYSTEMS (OPC)                             "]
["2","06","01","  ","  ","  ","XE System Mgmt & Integration                                "]
["2","06","01","01","  ","  ","Management                                                  "]
["2","06","02","  ","  ","  ","Controls Subsystem                                          "]
["2","06","02","01","  ","  ","Cabling                                                     "]
["2","06","02","02","  ","  ","Network                                                     "]
["2","06","02","03","  ","  ","PC Support                                                  "]
["2","06","02","04","  ","  ","Beamline Controls                                           "]
["2","06","02","05","  ","  ","X-Ray PPS                                                   "]
["2","06","02","06","  ","  ","X-Ray MPS                                                   "]
["2","06","02","07","  ","  ","Laser PPS                                                   "]
["2","06","02","08","  ","  ","User Safeguards                                             "]
["2","06","03","  ","  ","  ","Mechanical/Vacuum Subsystem                                 "]
["2","06","03","02","  ","  ","Vacuum Components - Mech/Vac                                "]
["2","06","03","03","  ","  ","Experimental Chambers                                       "]
["2","06","04","  ","  ","  ","Laser Subsystem                                             "]
["2","06","04","01","  ","  ","Oscillator Laser & Pump                                     "]
["2","06","04","02","  ","  ","Laser Diagnostics                                           "]
["2","06","04","03","  ","  ","Laser Supplies & Optical Transport                          "]
["2","06","04","04","  ","  ","Laser Timing                                                "]
["2","06","04","05","  ","  ","Laser Amplifiers                                            "]
["2","06","05","  ","  ","  ","X-Ray Detectors                                             "]
["2","06","05","01","  ","  ","Beam Imaging                                                "]
["2","06","05","02","  ","  ","2-D X-Ray Detector                                          ",{"$nulls":5},193787.72,193787.71,130386.5,-0.010000000009313226,63401.21,{"$nulls":5},"1"]
["2","06","05","03","  ","  ","Beam Intensity                                              "]
["2","06","05","04","  ","  ","Streak Camera                                               "]
["2","06","07","  ","  ","  ","Atomic Physics                                              "]
["2","06","07","01","  ","  ","Atomic Physics Samples                                      "]
["2","06","07","02","  ","  ","Atomic Physics Diagnostics                                  "]
["2","06","07","03","  ","  ","Atomic Physics Data Analysis                                "]
["2","06","07","04","  ","  ","Atomic Physics Detectors                                    "]
["2","08","  ","  ","  ","  ","LCLS SYSTEM COMMISSIONING (OPC)                             "]
["2","09","  ","  ","  ","  ","CONVENTIONAL FACILITIES (OPC)                               "]
["2","09","01","  ","  ","  ","MANAGEMENT INTEGRATION                                      "]
["2","09","03","  ","  ","  ","RSY - CLOC Commissioning                                    "]
["2","09","03","05","  ","  ","RSY-CLOC Commissioning                                      "]

{"sheet":"Master","index":3,"n_rows":1338,"n_cols":22,"rows_kept":1338,"cut":false,"hidden":true,"merged":[[0,0,0,2],[1,0,1,2],[0,3,0,5],[1,3,1,5],[4,0,4,5],[5,0,5,5],[3,0,3,5],[4,10,5,10],[3,10,3,11],[3,7,3,8],[3,9,5,9],[4,11,5,11],[2,7,2,11],[2,12,2,18],[3,12,3,13],[3,14,5,14],[3,17,3,18],[4,17,5,17],[3,15,3,16],[4,15,5,15],[4,16,5,16],[4,18,5,18]],"flags":["formulas_cached_only"]}
["Rpt Period",null,null,"2005-02-28",{"$nulls":15},"Run Date:"]
[{"$nulls":19},"2008-03-11T08:30:01.500"]
[{"$nulls":7},"Current Period",{"$nulls":4},"Cumulative to Date",{"$nulls":7},"At Complete"]
["WBS",{"$nulls":6},"Budgeted Cost",null,"Actual Cost\nWork Performed","Variance",null,"Budgeted Cost",null,"Actual Cost\nWork Performed","Variance",null,"Perf. Indices",null,null,"Latest"]
["Level",{"$nulls":6},"Work","Work",null,"Schedule","Cost","Work","Work",null,"Schedule","Cost","SPI","CPI",null,"Revised"]
[{"$nulls":6},"Description","Scheduled","Performed",null,null,null,"Scheduled","Performed",{"$nulls":5},"Budgeted","Estimate","Variance"]
["1","2","3","4","5","6"]
[{"$nulls":6},"LINAC COHERENT LIGHT SOURCE (TPC)"]
["1","  ","  ","  ","  ","  ","LCLS PROJECT - PED & CONSTRUCTION                           "]
["1","01","  ","  ","  ","  ","LCLS PROJECT MGMT, PLANNING & ADMN (TEC)                    "]
["1","01","01","  ","  ","  ","Environment, Safety & Health                                "]
["1","01","01","01","  ","  ","Radiation Physics                                           "]
["1","01","01","02","  ","  ","ESH Management & Coordination                               "]
["1","01","01","03","  ","  ","Professional Services-Project Office Support                "]
["1","01","02","  ","  ","  ","Project Management                                          "]
["1","01","02","01","  ","  ","Project Management Office                                   "]
["1","01","02","01","01","  ","Project Office - General                                    "]
["1","01","02","01","02","  ","Project Support                                             "]
["1","01","02","01","03","  ","Project Office M&S                                          "]
["1","01","02","01","04","  ","SSRL Physics Support                                        "]
["1","01","03","  ","  ","  ","Technical Integration                                       "]
["1","01","03","01","  ","  ","Global Laser Coordination                                   "]
["1","01","03","02","  ","  ","Global Alignment Coordination                               "]
["1","01","03","03","  ","  ","System Integration                                          "]
["1","01","03","05","  ","  ","Global Controls                                             "]
["1","01","03","05","01","  ","Global Controls Management                                  "]
["1","01","03","05","02","  ","LLRF Controls                                               "]
["1","01","03","05","03","  ","E-beam Diagnostics & Controls                               "]
["1","01","03","05","03","01","Controls - Wire Scanners                                    "]
["1","01","03","05","03","02","Controls - Toroids                                          "]
["1","01","03","05","03","03","Controls - Faraday Cups                                     "]
["1","01","03","05","03","04","Controls - Tune-Up Dump                                     "]
["1","01","03","05","03","05","Controls - Profile Monitors                                 "]
["1","01","03","05","03","06","Controls - E/O Diagnostics                                  "]
["1","01","03","05","03","07","Controls - BPM                                              "]
["1","01","03","05","03","08","Controls - Stopppers                                        "]
["1","01","03","05","03","09","Controls - Bunch Length Monitors                            "]
["1","01","03","05","03","10","Controls - Beam Loss Monitors                               "]
["1","01","03","05","04","  ","Laser Controls Design                                       "]
["1","01","03","05","05","  ","Laser Heater Controls                                       "]
["1","01","03","05","06","  ","Timing Controls                                             "]
["1","01","03","05","07","  ","Vacuum Controls                                             "]
["1","01","03","05","09","  ","Power Supply Controls                                       "]
["1","01","03","05","10","  ","PPS Controls                                                "]
["1","01","03","05","11","  ","Controls - MPS                                              "]
["1","01","03","05","12","  ","Global Controls Management                                  "]
["1","01","03","05","12","01","Global Controls Management LOE                              "]
["1","01","03","05","12","02","Global Controls Management                                  "]
["1","01","03","05","13","  ","SLC Aware IOC                                               "]
["1","01","03","05","15","  ","Controls - BCS                                              "]
["1","01","03","06","  ","  ","Technical Requirements/Parameters                           "]
["1","01","04","  ","  ","  ","Education Support                                           "]
["1","01","04","01","  ","  ","Education/Outreach Travel                                   "]
["1","01","04","02","  ","  ","Education/Outreach M&S                                      "]
["1","02","  ","  ","  ","  ","INJECTOR SYSTEM                                             "]
["1","02","01","  ","  ","  ","Injector System Management & Integration                    "]
["1","02","01","01","  ","  ","Injector System Integration                                 "]
["1","02","01","01","01","  ","Injector Region Integration                                 "]
["1","02","01","01","02","  ","Gun Area Integration                                        "]
["1","02","01","01","03","  ","Accelerator Area Integration                                "]
["1","02","01","01","04","  ","Heater Area Integration                                     "]
["1","02","01","01","05","  ","Wall Area Integration                                       "]
["1","02","01","01","06","  ","Insertion Area Integration                                  "]
["1","02","01","01","07","  ","Spectrometer Area Integration                               "]
["1","02","01","01","08","  ","Drive Laser Integration                                     "]
["1","02","01","03","  ","  ","Feedback Software                                           "]
["1","02","01","04","  ","  ","Injector System Integration Effort / M&S                    "]
["1","02","02","  ","  ","  ","Injector Controls Subsystem                                 "]
["1","02","02","01","  ","  ","Personnel Protection Subsystem (PPS)                        "]
["1","02","02","02","  ","  ","Beam Containment Subsystem (BCS)                            "]
["1","02","02","03","  ","  ","Machine Protection Subsystem (MPS)                          "]
["1","02","02","04","  ","  ","Injector Power Conversion                                   "]
["1","02","02","04","01","  ","Beamline Pwr Supplies - (Dipole Type)                       "]
["1","02","02","04","01","01","10kw Power Supply - (Solenoid 1)                            "]
["1","02","02","04","01","02","30kw Power Supply - (Solenoid 2)                            "]
["1","02","02","04","01","03","2kw Power Supply - (B0.5 Spect)                             "]
["1","02","02","04","01","04","15kw Power Supply - (B1-2)                                  "]
["1","02","02","04","01","05","15kw Power Supply - (B3 Spect)                              "]
["1","02","02","04","01","06","10kw Power Supply - (New)                                   "]
["1","02","02","04","02","  ","Power Supply Controls                                       "]
["1","02","02","04","03","  ","Beamline Pwr Supplies - (Trim Type)                         "]
["1","02","02","04","03","01","12Amp Power Supply - (MCOR_1)                               "]
["1","02","02","04","03","02","30Amp Power Supply - (MCOR_2)                               "]
["1","02","02","04","03","03","30Amp Power Supply - (MCOR_3)                               "]
["1","02","02","04","03","04","30Amp Power Supply - (MCOR_4)                               "]
["1","02","02","04","04","  ","Beamline Pwr Supply - Misc Hdwr                             "]
["1","02","02","04","05","  ","Magnet Interlock Protection System                          "]
["1","02","02","05","  ","  ","LLRF Controls                                               "]
["1","02","02","05","01","  ","Readback & Controls - RF Gun LLRF & Temperature             "]
["1","02","02","05","02","  ","Readback & Controls - L0 LLRF                               "]
["1","02","02","05","03","  ","Readback & Controls - Transverse Cavity LLRF                "]
["1","02","02","05","04","  ","S-Band Cavity Controls                                      "]
["1","02","02","05","05","  ","EO Phase Controls                                           "]
["1","02","02","06","  ","  ","E-Beam Diagnostics Controls                                 "]
["1","02","02","06","01","  ","Controls - Wire Scanners                                    "]
["1","02","02","06","02","  ","Controls - BPM                                              "]
["1","02","02","06","03","  ","Controls - Toroids                                          "]
["1","02","02","06","05","  ","Controls - Profile Monitors                                 "]
["1","02","02","06","06","  ","Controls - E/O Diagnostics                                  "]
["1","02","02","06","12","  ","Controls - Movable Collimator                               "]
["1","02","02","06","14","  ","Controls - Faraday Cups                                     "]
["1","02","02","06","15","  ","Controls - Tune-Up Dump                                     "]
["1","02","02","06","16","  ","Diagnostics Controls Integration                            "]
["1","02","02","08","  ","  ","Timing Controls                                             "]
["1","02","02","09","  ","  ","Vacuum Controls                                             "]
["1","02","02","10","  ","  ","Software & Controls Infrastructure                          "]
["1","02","02","10","01","  ","Low Level Application Software                              "]
["1","02","02","10","02","  ","High Level Application Software                             "]
["1","02","02","10","03","  ","Data Communications                                         "]
["1","02","02","10","04","  ","Computers & Crates                                          "]
["1","02","02","11","  ","  ","EPICS VXI Control Modules                                   "]
["1","02","02","12","  ","  ","Laser Controls                                              "]
["1","02","02","12","01","  ","Controls - Alignment Laser                                  "]
["1","02","02","12","02","  ","Controls - Gun Laser                                        "]
["1","02","02","13","  ","  ","Laser Heater Controls                                       "]
["1","02","03","  ","  ","  ","Injector Lasers                                             "]
["1","02","03","01","  ","  ","Drive Laser Support                                         "]
["1","02","03","01","01","  ","Drive Laser Support (ANL)                                   "]
["1","02","03","01","02","  ","Drive Laser Support (LLNL)                                  "]
["1","02","03","02","  ","  ","Drive Laser System                                          "]
["1","02","03","03","  ","  ","Drive Laser Diagnostics                                     "]
["1","02","03","04","  ","  ","Timing Stability Monitoring                                 "]
["1","02","03","05","  ","  ","Steering Stability Feedback & Msmts                         "]
["1","02","03","06","  ","  ","Pre Amp Low Power Comp                                      "]
["1","02","03","07","  ","  ","Transport to Tunnel & Relay Optics                          "]
["1","02","03","08","  ","  ","UV Launch, Conditioning & Diagnostics                       "]
["1","02","03","09","  ","  ","Load Lock Transport System                                  "]
["1","02","03","10","  ","  ","Visible Optical Transport & Optics                          "]
["1","02","03","11","  ","  ","LB Infrastructure & LB System Wide Items                    "]
["1","02","03","12","  ","  ","Alignment Laser                                             "]
["1","02","03","13","  ","  ","Light path to Streak Camera                                 "]
["1","02","03","14","  ","  ","LSR HTR - Beam Conditioning Optics (Laser Bay)              "]
["1","02","03","15","  ","  ","LSR HTR - Transport Optics (Bay to Tunnel)                  "]
["1","02","03","16","  ","  ","LSR HTR - Photon Beam Diagnostics                           "]
["1","02","03","21","  ","  ","UV Conv Harmonic Generation Unit (Closed Account)           "]
["1","02","04","  ","  ","  ","Injector RF Subsystem                                       "]
["1","02","04","01","  ","  ","RF Gun & Load Lock                                          "]
["1","02","04","01","01","  ","RF Gun                                                      "]
["1","02","04","01","02","  ","RF Gun Supports                                             "]
["1","02","04","01","03","  ","Gun Load Lock                                               "]
["1","02","04","01","04","  ","Gun Load Lock Supports                                      "]
["1","02","04","01","05","  ","Gun Solenoid                                                "]
["1","02","04","01","06","  ","Gun Solenoid Supports                                       "]
["1","02","04","01","07","  ","Gun RF Feed                                                 "]
["1","02","04","01","08","  ","Gun RF Feed Supports                                        "]
["1","02","04","01","09","  ","RF Gun Spares Credit                                        "]
["1","02","04","02","  ","  ","Cathode Processing (CP) Station                             "]
["1","02","04","02","01","  ","CP Cathode Assembly & Supports                              "]
["1","02","04","02","02","  ","CP Load Lock                                                "]
["1","02","04","02","03","  ","CP Load Lock Supports                                       "]
["1","02","04","02","04","  ","CP Station                                                  "]
["1","02","04","02","05","  ","Cathode Lab Infrastructure                                  "]
["1","02","04","03","  ","  ","S-Band Low Level Timing                                     "]
["1","02","04","03","01","  ","Controls Interface & Timing                                 "]
["1","02","04","03","02","  ","LLRF Phase Reference System                                 "]
["1","02","04","03","03","  ","LLRF Monitor & Control System                               "]
["1","02","04","03","04","  ","Beam Phase Monitor Cavity                                   "]
["1","02","04","03","05","  ","RF System S/W Development / Docs                            "]
["1","02","04","04","  ","  ","S-Band High Power System                                    "]
["1","02","04","04","01","  ","RF Gun High Power                                           "]
["1","02","04","04","02","  ","L0 High Power                                               "]
["1","02","04","04","03","  ","Transverse Cavity High Power                                "]
["1","02","04","05","  ","  ","Injector RF Waveguide Subsystem                             "]
["1","02","04","05","01","  ","RF Waveguides                                               "]
["1","02","04","05","02","  ","RF Waveguide Supports                                       "]
["1","02","04","06","  ","  ","Injector Linac Structures                                   "]
["1","02","04","06","01","  ","L0A-0B Structure Assembly                                   "]
["1","02","04","06","03","  ","Major Linac Support                                         "]
["1","02","04","06","04","  ","GTL RF Phase Cavity                                         "]
["1","02","04","06","05","  ","LTDL1 RF Kicker                                             "]
["1","02","05","  ","  ","  ","Injector Magnets & Supports                                 "]
["1","02","05","01","  ","  ","Injector Dipoles                                            "]
["1","02","05","01","01","  ","Gun Spectrometer Dipole                                     "]
["1","02","05","01","02","  ","DL1 B01 & B02 Dipoles                                       "]
["1","02","05","01","03","  ","SAB Spectrometer Dipole                                     "]
["1","02","05","01","04","  ","Chicane DIPOLES (4)                                         "]
["1","02","05","02","  ","  ","Injector Quads                                              "]
["1","02","05","02","01","  ","Gun Spectrometer Quadrupoles                                "]
["1","02","05","02","02","  ","Injector Quadrupoles                                        "]
["1","02","05","02","03","  ","TBD                                                         "]
["1","02","05","03","  ","  ","Injector Steering Coils                                     "]
["1","02","05","03","01","  ","Gun Solenoid Correctors                                     "]
["1","02","05","03","02","  ","Gun Spectrometer Correctors                                 "]
["1","02","05","03","03","  ","Injector Correctors - A                                     "]
["1","02","05","03","04","  ","Injector Correctors - D (Gun)                               "]
["1","02","05","03","05","  ","Gun Solenoid Quadrupole Correctors                          "]
["1","02","05","04","  ","  ","Linac Solenoid                                              "]
["1","02","05","05","  ","  ","Injector Laser Heater Subsystem                             "]
["1","02","05","05","01","  ","System Design & Optimization (LSR HTR)                      "]
["1","02","05","05","02","  ","Injector Undulator                                          "]
["1","02","06","  ","  ","  ","Injector Vacuum & Supports                                  "]
["1","02","06","01","  ","  ","Injector Vacuum Engineering                                 "]
["1","02","06","02","  ","  ","Injector Vacuum Components                                  "]
["1","02","06","03","  ","  ","Injector Vacuum Special Chambers                            "]
["1","02","06","04","  ","  ","Injector Vacuum Supports Engineering                        "]
["1","02","06","05","  ","  ","Injector Vacuum Support Components                          "]
["1","02","06","08","  ","  ","DL1 Vacuum Chamber                                          "]
["1","02","06","10","  ","  ","DL1TL Vacuum Components                                     "]
["1","02","07","  ","  ","  ","Injector Diagnostics                                        "]
["1","02","07","01","  ","  ","Beam Position Monitors                                      "]
["1","02","07","01","01","  ","Large Aperture BPM                                          "]
["1","02","07","01","02","  ","Small Aperture BPM                                          "]
["1","02","07","01","06","  ","TBD                                                         "]
["1","02","07","02","  ","  ","Current Monitors                                            "]
["1","02","07","02","01","  ","Current Monitors                                            "]
["1","02","07","03","  ","  ","Bunch Length Monitors                                       "]
["1","02","07","03","01","  ","Bunch Length Monitors                                       "]
["1","02","07","04","  ","  ","Profile Monitors                                            "]
["1","02","07","04","01","  ","Profile Monitors                                            "]
["1","02","07","04","02","  ","GTL Alignment Laser Mirror                                  "]
["1","02","07","04","03","  ","GS Faraday Cup/YAG2                                         "]
["1","02","07","04","06","  ","DL1 OTR/YAG                                                 "]
["1","02","07","04","07","  ","DL1TL OTR/YAG                                               "]
["1","02","07","04","08","  ","LTDL1 OTR/YAG (6)                                           "]
["1","02","07","05","  ","  "," Injector Wire Scanners                                     "]
["1","02","07","06","  ","  ","LSR HTR - Electron Beam Diagnostics                         "]
["1","02","07","07","  ","  ","PPS Stopper                                                 "]
["1","02","17","  ","  ","  ","Injector Installation & Alignment                           "]
["1","02","17","01","  ","  ","Injector Infrastructure Installation                        "]
["1","02","17","02","  ","  ","Injector Controls Subsystem Install & Align                 "]
["1","02","17","03","  ","  ","Injector Lasers Install & Align                             "]
["1","02","17","04","  ","  ","Gun Area Integration                                        "]
["1","02","17","06","  ","  ","Accelerator Area Integration                                "]
["1","02","17","07","  ","  ","Heater Area Integration                                     "]
["1","02","17","08","  ","  ","Wall Area Integration                                       "]
["1","02","17","09","  ","  ","Insertion Area Integration                                  "]
["1","02","17","11","  ","  ","Spectrometer Area Integration                               "]
["1","02","17","12","  ","  ","Injector RF High Power System Install & Align               "]
["1","02","17","15","  ","  ","Laser Heater Installation                                   "]
["1","03","  ","  ","  ","  ","LINAC SYSTEM                                                "]
["1","03","01","  ","  ","  ","System Management & Integration                             "]
["1","03","01","01","  ","  ","Linac Mechanical Integration                                "]
["1","03","01","01","01","  ","L01 System Integration                                      "]
["1","03","01","01","02","  ","BC1 System Integration                                      "]
["1","03","01","01","03","  ","L02 System Integration                                      "]
["1","03","01","01","04","  ","BC2 System Integration                                      "]
["1","03","01","01","05","  ","L03 System Integration                                      "]
["1","03","01","01","06","  ","LTU System Integration                                      "]
["1","03","01","01","07","  ","E-Dump System Integration                                   "]
["1","03","01","03","  ","  ","Travel                                                      "]
["1","03","01","04","  ","  ","Linac Management                                            "]
["1","03","02","  ","  ","  ","Linac Controls & Power Conversion Subsystem                 "]
["1","03","02","01","  ","  ","Personnel Protection System (PPS)                           "]
["1","03","02","02","  ","  ","Beam Containment System (BCS)                               "]
["1","03","02","03","  ","  ","Machine Protection System (MPS)                             "]
["1","03","02","04","  ","  ","Linac Power Conversion Subsystem                            "]
["1","03","02","04","01","  ","Beamline Power Supplies - (Dipole Type)                     "]
["1","03","02","04","01","01","25kw Pwr Supply - (BX11-14)                                 "]
["1","03","02","04","01","02","Power Supply - (BX21-24)                                    "]
["1","03","02","04","01","03","Kicker (BXKIK)                                              "]
["1","03","02","04","01","04","BX31,32,35,36                                               "]
["1","03","02","04","01","05","Power Supply - (BY1-2)                                      "]
["1","03","02","04","01","06","Kicker (BYBKIK)                                             "]
["1","03","02","04","01","07","BYW1-3                                                      "]
["1","03","02","04","01","08","Muon Spoiler (MUSPLR)                                       "]
["1","03","02","04","01","09","BYD1-3                                                      "]
["1","03","02","04","02","  ","Beamline Power Supplies - (Quad Type)                       "]
["1","03","02","04","02","06","Q21201-Q21901 Split                                         "]
["1","03","02","04","02","07","Q24201-Q24501 Split                                         "]
["1","03","02","04","02","08","Q24601                                                      "]
["1","03","02","04","02","09","10KW PS - (Q24701A,Q24701B)                                 "]
["1","03","02","04","02","10","QM21                                                        "]
["1","03","02","04","02","11","Q24901A,Q24901B                                             "]
["1","03","02","04","02","12","10kw Power Supply - (QM22)                                  "]
["1","03","02","04","02","13","Power Supply - (Q5)                                         "]
["1","03","02","04","02","14","Power Supply - (QVM2)                                       "]
["1","03","02","04","02","15","Power Supply - (QA0)                                        "]
["1","03","02","04","02","16","Power Supply - (Q50Q1,Q50Q2,Q50Q3)                          "]
["1","03","02","04","02","17","Power Supply - (QVM1)                                       "]
["1","03","02","04","02","18","Power Supply - (QVM2)                                       "]
["1","03","02","04","02","19","Power Supply - (QVM3)                                       "]
["1","03","02","04","02","20","Power Supply - (QVM4)                                       "]
["1","03","02","04","02","21","Power Supply - (QVB1-3)                                     "]
["1","03","02","04","02","22","Power Supply - (QDL31-34)                                   "]
["1","03","02","04","02","23","Power Supply - (QE31-36)                                    "]
["1","03","02","04","02","24","Power Supply - (QEM1)                                       "]
["1","03","02","04","02","25","Power Supply - (QEM2)                                       "]
["1","03","02","04","02","26","Power Supply - (QEM3)                                       "]
["1","03","02","04","02","27","Power Supply - (QEM4)                                       "]
["1","03","02","04","02","28","Power Supply - (QT11,13,21,23,31,33,41,43)                  "]
["1","03","02","04","02","29","Power Supply - (QT12,22,32,42)                              "]
["1","03","02","04","02","30","Power Supply - (QDM1)                                       "]
["1","03","02","04","02","31","Power Supply - (QUM2)                                       "]
["1","03","02","04","02","32","Power Supply - (QUM3)                                       "]
["1","03","02","04","02","33","Power Supply - (Qum4)                                       "]
["1","03","02","04","02","34","Power Supply - (QDMP1-2)                                    "]
["1","03","02","04","02","35","Power Supply - (QUE1)                                       "]
["1","03","02","04","02","36","Power Supply - (QUE2)                                       "]
["1","03","02","04","02","37","Rack Accessories - LI21                                     "]
["1","03","02","04","02","38","Rack Accessories - LI24                                     "]
["1","03","02","04","02","39","Rack Accessories - LI25                                     "]
["1","03","02","04","02","40","Rack Accessories - BSY                                      "]
["1","03","02","04","02","41","Rack Accessories - Dump                                     "]
["1","03","02","04","03","  ","Beamline Power Supplies - (Trim Type)                       "]
["1","03","02","04","03","01","12Amp Power Supply - (MCOR_1)                               "]
["1","03","02","04","03","02","30Amp Power Supply - (MCOR_2)                               "]
["1","03","02","04","03","03","30Amp Power Supply - (MCOR_3)                               "]
["1","03","02","04","03","04","30Amp Power Supply - (MCOR_4)                               "]
["1","03","02","04","03","05","12/30 Amp Power Supply (MCOR_5)                             "]
["1","03","02","04","03","06","12/30 Amp Power Supply (MCOR_6)                             "]
["1","03","02","04","03","07","12 Amp Power Supply (MCOR_BSY1)                             "]
["1","03","02","04","03","08","12 Amp Power Supply (MCOR_LTU1)                             "]
["1","03","02","04","03","09","12 Amp Power Supply (MCOR_LTU2)                             "]
["1","03","02","04","03","10","Power Supply - (MCOR_LTU3)                                  "]
["1","03","02","04","03","11","Power Supply - (MCOR_LTU4)                                  "]
["1","03","02","04","03","12","Power Supply - (MCOR_LTU5)                                  "]
["1","03","02","04","03","13","Power Supply - (MCOR_LTU6)                                  "]
["1","03","02","04","03","14","Power Supply - (MCOR_LTU7)                                  "]
["1","03","02","04","03","15","Power Supply - (MCOR_LTU8)                                  "]
["1","03","02","04","03","16","Powe Supply (MCOR_LTU9)                                     "]
["1","03","02","04","03","17","Power Supply (MCOR_DMP1)                                    "]
["1","03","02","04","03","18","MCOR Bulk PS - LI21_1                                       "]
["1","03","02","04","03","19","MCOR Bulk PS - LI21_2                                       "]
["1","03","02","04","03","20","MCOR Bulk PS - LI24                                         "]
["1","03","02","04","03","21","MCOR Bulk PS - LI25                                         "]
["1","03","02","04","03","22","MCOR Bulk PS - BSY                                          "]
["1","03","02","04","03","23","MCOR Bulk PS - LTU_1                                        "]
["1","03","02","04","03","24","MCOR Bulk PS - LTU_2                                        "]
["1","03","02","04","03","25","MCOR Bulk PS - LTU_3                                        "]
["1","03","02","04","03","26","MCOR Bulk PS - LTU_4                                        "]
["1","03","02","04","03","27","MCOR PLC - LI21                                             "]
["1","03","02","04","03","28","MCOR PLC - LI24                                             "]
["1","03","02","04","03","29","MCOR PLC - LI25                                             "]
["1","03","02","04","03","30","MCOR PLC - BSY                                              "]
["1","03","02","04","03","31","MCOR PLC - LTU_1 (BLD 2.1)                                  "]
["1","03","02","04","03","32","MCOR PLC - LTU_2 (BLD 2.2)                                  "]
["1","03","02","04","03","33","MCOR PLC - LTU_3 (BLD 2.3)                                  "]
["1","03","02","04","03","34","MCOR PLC - Dump                                             "]
["1","03","02","04","03","35","MCOR Bulk Dump                                              "]
["1","03","02","04","03","36","Rack Accessories - LTU_1 (bld 2.1)                          "]
["1","03","02","04","03","37","Rack Accessories - LTU_2 (bld 2.2)                          "]
["1","03","02","04","03","38","Rack Accessories - LTU_3 (bld 2.3)                          "]
["1","03","02","04","04","  ","Controls & Power Supply                                     "]
["1","03","02","05","  ","  ","Controls - LLRF                                             "]
["1","03","02","05","01","  ","Solid State Sub-booster 5x                                  "]
["1","03","02","05","03","  ","L2/L3 RF Distribution                                       "]
["1","03","02","05","04","  ","Beam Phase Measurement 2X                                   "]
["1","03","02","05","05","  ","Sector 24 Rack Electrical Crate IOC/EVG                     "]
["1","03","02","05","06","  ","Sector 24 T-Cav                                             "]
["1","03","02","05","07","  ","Sector 29/30 Controls (PACs & PADs)                         "]
["1","03","02","05","10","  ","RF Stability/Feedback                                       "]
["1","03","02","05","11","  ","System Documentation                                        "]
["1","03","02","06","  ","  ","Controls - E-Beam Diagnostic                                "]
["1","03","02","06","01","  ","Controls - Wire Scanners                                    "]
["1","03","02","06","02","  ","Controls - BPMs                                             "]
["1","03","02","06","03","  ","Controls - Toroids                                          "]
["1","03","02","06","04","  ","Controls - Stoppers                                         "]
["1","03","02","06","05","  ","Controls - Profile Monitors                                 "]
["1","03","02","06","06","  ","Controls - E/O Diagnostics                                  "]
["1","03","02","06","07","  ","Controls - Bunch Length Monitors                            "]
["1","03","02","06","08","  ","Controls - Beam Loss Monitors                               "]
["1","03","02","06","09","  ","Controls - Single Beam Dump                                 "]
["1","03","02","06","10","  ","Controls - E Beam Dump                                      "]
["1","03","02","06","11","  ","Controls - Protection Collimator                            "]
["1","03","02","06","12","  ","Controls - Movable Collimator                               "]
["1","03","02","06","13","  ","Controls - X-Band Accel Structure                           "]
["1","03","02","08","  ","  ","Controls - Timing                                           "]
["1","03","02","09","  ","  ","Controls - Vacuum                                           "]
["1","03","02","09","01","  ","Controls - Vacuum Instrumentation & Interlocks              "]
["1","03","02","09","02","  ","Controls - Vacuum Pump Power Supplies                       "]
["1","03","02","10","  ","  ","Software & Controls Infrastructure                          "]
["1","03","02","10","04","  ","Data Communications                                         "]
["1","03","02","10","05","  ","Computers                                                   "]
["1","03","03","  ","  ","  ","Linac Magnets & Supports                                    "]
["1","03","03","01","  ","  ","Bend Magnet (BX1_BC1)                                       "]
["1","03","03","02","  ","  ","Bend Magnet (BX3_LTU)                                       "]
["1","03","03","03","  ","  ","Bend Magnet (BX2_BC2)                                       "]
["1","03","03","04","  ","  ","Bend Magnet (BY_LTU)                                        "]
["1","03","03","05","  ","  ","Quad Magnet (Quad_LTU)                                      "]
["1","03","03","07","  ","  ","Quad Magnet (QE)                                            "]
["1","03","03","08","  ","  ","Corrector Magnet (Type 4)                                   "]
["1","03","03","09","  ","  ","Bend Magnet (BYD_DUMP)                                      "]
["1","03","03","10","  ","  ","Quad Magnet (QA)                                            "]
["1","03","03","11","  ","  ","Bend Magnet (BYPM_LTU)                                      "]
["1","03","03","12","  ","  ","Bend Magnet (BYKIK_LTU)                                     "]
["1","03","03","13","  ","  ","Bend Magnet (BYW_LTU)                                       "]
["1","03","03","14","  ","  ","BXKIK LINAC TCAV Screen Kicker                              "]
["1","03","03","15","  ","  ","Muon Toroid (E-Dump)                                        "]
["1","03","04","  ","  ","  ","Linac Vacuum Subsystem                                      "]
["1","03","04","02","  ","  ","Linac Beamline Vacuum System                                "]
["1","03","04","03","  ","  ","BC1 Vacuum System                                           "]
["1","03","04","04","  ","  ","BC2 Vacuum System                                           "]
["1","03","04","05","  ","  ","Linac to Undulator (LTU) Vacuum System                      "]
["1","03","04","06","  ","  ","Dumpline Vacuum System                                      "]
["1","03","04","07","  ","  ","Vacuum System Undulator Interface                           "]
["1","03","04","07","01","  ","Entrance Section Assembly                                   "]
["1","03","04","07","02","  ","Exit Section Assembly                                       "]
["1","03","04","08","  ","  ","LTU/BSY& Cold Trap Vacuum System                            "]
["1","03","05","  ","  ","  ","Linac Electron Diagnostics Summary                          "]
["1","03","05","01","  ","  ","Wire Scanners (7) Summary                                   "]
["1","03","05","02","  ","  ","Beam Position Monitors                                      "]
["1","03","05","02","01","  ","BPM - Standard  Linac (4) Summary                           "]
["1","03","05","02","02","  ","BPM - RF (10) Summary                                       "]
["1","03","05","02","03","  ","BPM - FFTB (12) Summary                                     "]
["1","03","05","02","04","  ","BPM - Large Aperture (2) Summary                            "]
["1","03","05","03","  ","  ","Toroid Beam Current Monitor (10) Summary                    "]
["1","03","05","04","  ","  ","Beam Stoppers (4) Summary                                   "]
["1","03","05","05","  ","  ","Profile Monitors (7 OTR-3 PHOSPHOR SCREEN-1 YAG)            "]
["1","03","05","06","  ","  ","E/O Bunch Length Monitors (1) Summary                       "]
["1","03","05","07","  ","  ","CSR/OTR/CTR Bunch Length Monitors (5) Summary               "]
["1","03","05","08","  ","  ","Beam Loss Monitors                                          "]
["1","03","05","08","01","  ","PIC Beam Loss Monitors (10) Summary                         "]
["1","03","05","08","02","  ","PLIC Beam Loss Monitors (2) Summary                         "]
["1","03","05","09","  ","  ","Single Beam Dump (1) Summary                                "]
["1","03","05","10","  ","  ","Electron Beam Dump (1) Summary                              "]
["1","03","05","11","  ","  ","Protection Collimators (5) Summary                          "]
["1","03","05","12","  ","  ","Movable Collimators (7x,3y) Summary                         "]
["1","03","05","13","  ","  ","Safety Electron Dump (1) Summary                            "]
["1","03","05","14","  ","  ","Charge Monitor (Entrance/Exit Assembly)                     "]
["1","03","06","  ","  ","  ","Linac RF Subsystem                                          "]
["1","03","06","02","  ","  ","S-Band High Power System                                    "]
["1","03","06","03","  ","  ","S-Band Structures                                           "]
["1","03","06","04","  ","  ","X-Band Low Level System                                     "]
["1","03","06","05","  ","  ","X-Band High Power System                                    "]
["1","03","06","05","01","  ","X-Band HP Klystron                                          "]
["1","03","06","05","02","  ","X-Band HP Modulator                                         "]
["1","03","06","05","03","  ","X-Band HP Waveguide System                                  "]
["1","03","06","06","  ","  ","X-Band Structures                                           "]
["1","03","06","07","  ","  ","RF Distribution System                                      "]
["1","03","06","07","01","  ","Modulator Refurbishment                                     "]
["1","03","06","07","02","  ","Solid State Sub Booster                                     "]
["1","03","06","07","03","  ","IPA Modifications                                           "]
["1","03","06","07","04","  ","Klystron Controls Interfaces                                "]
["1","03","06","07","05","  ","Bunch Length Electronics                                    "]
["1","03","06","07","06","  ","RF Phase Measurements                                       "]
["1","03","06","07","07","  ","RF Distribution L2 & L3                                     "]
["1","03","06","07","08","  ","RF Fiber Optics Electronics System                          "]
["1","03","06","07","09","  ","RF Stability                                                "]
["1","03","07","  ","  ","  ","Linac Installation & Alignment                              "]
["1","03","07","01","  ","  ","Linac L01 System Installation & Alignment                   "]
["1","03","07","02","  ","  ","Linac BC1 System Installation & Alignment                   "]
["1","03","07","05","  ","  ","Linac L03 System Installation & Alignment                   "]
["1","03","07","06","  ","  ","Linac LTU System Installation & Alignment                   "]
["1","03","07","07","  ","  ","Linac E-Dump System Installation & Alignment                "]
["1","03","07","10","  ","  ","LINAC  Installation 2006 Shut Down                          "]
["1","03","07","10","01","  ","Beamline Equip Removal L01 thru BC1 Out                     "]
["1","03","07","10","02","  ","Gallery Waveguide Installation                              "]
["1","03","07","10","03","  ","Beamline Equip Installation L01 thru BC1 Out                "]
["1","03","07","10","04","  ","2006 Linac Controls Install and Checkout Gallery            "]
["1","03","07","10","05","  ","2006 Linac Controls Install and Checkout L01 to             "]
["1","03","07","20","  ","  ","LINAC Installation 2007 Shut Down                           "]
["1","03","07","20","01","  ","Beamline Equip Removal L02, L03 and BC2                     "]
["1","03","07","20","02","  ","Beamline Equip Installation L02, L03 and BC2                "]
["1","03","07","20","03","  ","2007 Linac Controlls Install and Checkout                   "]
["1","03","07","20","04","  ","Linac Undulator Interface                                   "]
["1","04","  ","  ","  ","  ","UNDULATOR SYSTEM                                            "]
["1","04","01","  ","  ","  ","Undulator System Management & Integration                   "]
["1","04","01","01","  ","  ","Undulator System Management                                 "]
["1","04","01","01","01","  ","Undulator System Management - Technical                     "]
["1","04","01","01","02","  ","ANL Project Support                                         "]
["1","04","01","02","  ","  ","Undulator System Materials & Supplies                       "]
["1","04","01","02","01","  ","Undulator System M&S - General                              "]
["1","04","01","02","02","  ","Undulator System Travel                                     "]
["1","04","01","03","  ","  ","Undulator System Reviews and Workshops                      "]
["1","04","02","  ","  ","  ","Controls                                                    "]
["1","04","02","01","  ","  ","Controls Management and Integration                         "]
["1","04","02","01","03","  ","Software Interface with SLAC                                "]
["1","04","02","01","04","  ","Undulator Cable, Tray, and Rack Layout                      "]
["1","04","02","01","05","  ","Miscellaneous Controls                                      "]
["1","04","02","02","  ","  ","Motion                                                      "]
["1","04","02","02","01","  ","Undulator Cam Movers                                        "]
["1","04","02","02","01","01","Motor Interface                                             "]
["1","04","02","02","01","02","Encoder Interface                                           "]
["1","04","02","02","01","03","Motor Driver                                                "]
["1","04","02","02","01","04","Cabling                                                     "]
["1","04","02","02","01","05","Integrate components                                        "]
["1","04","02","02","02","  ","Motion Test Stand                                           "]
["1","04","02","02","06","  ","Scanning Wire Motion                                        "]
["1","04","02","02","06","01","Motor Interface                                             "]
["1","04","02","02","06","02","Encoder Interface                                           "]
["1","04","02","02","06","03","Motor Driver                                                "]
["1","04","02","02","06","04","Cabling                                                     "]
["1","04","02","02","06","05","Integrate components                                        "]
["1","04","02","02","07","  ","Translation Stage Motion                                    "]
["1","04","02","02","07","01","Motor Interface                                             "]
["1","04","02","02","07","03","Motor Driver                                                "]
["1","04","02","02","07","04","Cabling                                                     "]
["1","04","02","02","07","05","Integrate components                                        "]
["1","04","02","03","  ","  ","Signal Analysis                                             "]
["1","04","02","03","01","  ","RFBPM                                                       "]
["1","04","02","03","01","02","Signal Acquisition                                          "]
["1","04","02","03","01","03","Timing interface                                            "]
["1","04","02","03","01","04","Cabling                                                     "]
["1","04","02","03","01","05","Integrate components                                        "]
["1","04","02","03","02","  ","Charge Monitor                                              "]
["1","04","02","03","02","03","Integrate components                                        "]
["1","04","02","03","03","  ","Beam Finder Wire                                            "]
["1","04","02","03","03","01","BFW Actuator Control                                        "]
["1","04","02","03","03","06","Integrate components                                        "]
["1","04","02","04","  ","  ","Video                                                       "]
["1","04","02","04","01","  ","OTR Monitor                                                 "]
["1","04","02","04","01","01","Camera                                                      "]
["1","04","02","04","01","02","Camera trigger interface                                    "]
["1","04","02","04","01","03","Digitizer                                                   "]
["1","04","02","04","01","04","Timing interface                                            "]
["1","04","02","04","01","05","Cabling                                                     "]
["1","04","02","04","01","06","Integrate components                                        "]
["1","04","02","04","03","  ","Observation station video                                   "]
["1","04","02","04","03","01","Camera                                                      "]
["1","04","02","04","03","02","Camera trigger interface                                    "]
["1","04","02","04","03","03","Multiplexor                                                 "]
["1","04","02","04","03","04","Cabling                                                     "]
["1","04","02","04","03","05","Integrate components                                        "]
["1","04","02","04","03","06","Imaging Test Stand                                          "]
["1","04","02","05","  ","  ","Data Acquisition and Control                                "]
["1","04","02","05","01","  ","Strongback Temperature monitoring                           "]
["1","04","02","05","01","01","Integrate components                                        "]
["1","04","02","06","  ","  ","Vacuum                                                      "]
["1","04","02","06","01","  ","Ion Pump Controller                                         "]
["1","04","02","06","01","01","Integrate components                                        "]
["1","04","02","06","02","  ","RGA                                                         "]
["1","04","02","06","02","01"," Integrate components                                       "]
["1","04","02","07","  ","  ","Machine Protection                                          "]
["1","04","02","07","01","  ","Undulator Beam Loss  Monitor Controls                       "]
["1","04","02","07","01","01","Hardware design                                             "]
["1","04","02","07","01","02","Interface components                                        "]
["1","04","02","07","02","  ","Cerenkov Detector                                           "]
["1","04","02","07","02","01","Signal interface                                            "]
["1","04","02","07","03","  ","Gamma Ray Detector                                          "]
["1","04","02","07","03","01","Signal interface                                            "]
["1","04","02","08","  ","  ","Undulator Magnet Power Supplies                             "]
["1","04","02","08","01","  ","Software                                                    "]
["1","04","02","08","02","  ","Beamline Power Supplies (Trim Type)                         "]
["1","04","02","08","02","01","CPUs and Crates                                             "]
["1","04","02","08","02","02","Bulk Power Supplies                                         "]
["1","04","02","08","02","03","PLC Power Supply Protection System                          "]
["1","04","02","08","02","04","MCOR                                                        "]
["1","04","02","08","03","  ","Rack Assembly                                               "]
["1","04","02","08","04","  ","System Checkout                                             "]
["1","04","02","10","  ","  ","Undulator Control Module                                    "]
["1","04","02","10","01","  ","UCM Hardware Design                                         "]
["1","04","02","10","02","  ","UCM EPICS Development                                       "]
["1","04","02","10","03","  ","Procure UCMI Prototype                                      "]
["1","04","02","10","04","  ","UCMI Proto H/W Assembly                                     "]
["1","04","02","10","05","  ","UCMI Prototype Testing                                      "]
["1","04","02","10","06","  ","UCMI Blade IOC First Article                                "]
["1","04","02","10","07","  ","Procure UCMI First Article                                  "]
["1","04","02","10","08","  ","UCM First Article Testing and QA                            "]
["1","04","02","10","09","  ","Procure Production UCMI                                     "]
["1","04","02","10","10","  ","Procure Production Blade IOC                                "]
["1","04","02","10","11","  ","Procure Production Motors                                   "]
["1","04","02","10","12","  ","Procure Production Potentionmeters                          "]
["1","04","02","10","13","  ","Procure Production RTD                                      "]
["1","04","02","10","14","  ","UCM Interlock & Power Supply                                "]
["1","04","02","12","  ","  ","Rack and Cable                                              "]
["1","04","02","12","01","  ","Undulator Racks                                             "]
["1","04","02","12","02","  ","Intra-Undulator Cabling                                     "]
["1","04","02","12","03","  ","Electronics Interface Assembly                              "]
["1","04","02","12","04","  ","Undulator Cableplant                                        "]
["1","04","02","13","  ","  ","BPM                                                         "]
["1","04","02","13","01","  ","APS Testing                                                 "]
["1","04","02","14","  ","  ","Long Term Test Prep                                         "]
["1","04","02","15","  ","  ","Undulator Controls - BLM                                    "]
["1","04","02","17","  ","  ","Undulator Conrols - Management                              "]
["1","04","02","20","  ","  ","Undulator MPS                                               "]
["1","04","02","20","02","  ","Undulator MPS - IMUX                                        "]
["1","04","02","20","03","  ","Undulator MPS - TIU                                         "]
["1","04","02","20","04","  ","Undulator MPS - PLIC                                        "]
["1","04","02","20","05","  ","Undulator MPS - Toroids                                     "]
["1","04","02","20","06","  ","Undulator MPS - Fault Devices                               "]
["1","04","02","21","  ","  ","Undulator Controls - Timing                                 "]
["1","04","02","22","  ","  ","Undulator Controls - BPM                                    "]
["1","04","02","23","  ","  ","Undulator Controls - Vacuum                                 "]
["1","04","02","24","  ","  ","Undulator Controls - ADS System                             "]
["1","04","03","  ","  ","  ","Undulator Magnet & Support                                  "]
["1","04","03","01","  ","  ","UND Magnet & Support - Mgmt and Integration                 "]
["1","04","03","02","  ","  ","First Prototype Undulator & Mfg Plan                        "]
["1","04","03","03","  ","  ","1st Article Undulators & Long Lead Procurements             "]
["1","04","03","03","01","  ","Ti Strongback (LLP)                                         "]
["1","04","03","03","02","  ","Magnet Blocks (LLP)                                         "]
["1","04","03","03","03","  ","Magnet Poles (LLP)                                          "]
["1","04","03","03","04","  ","Magnet Assembly & Supports - 1st Articles                   "]
["1","04","03","03","04","01","Magnet Assembly 1st Article - Vendor A                      "]
["1","04","03","03","04","02","Magnet Assembly 1st Article - Vendor B                      "]
["1","04","03","03","04","03","Support/Mover System - Articles 1 & 2                       "]
["1","04","03","03","05","  ","Magnetic Measurement (ANL)                                  "]
["1","04","03","03","05","01","Magnetic Measurement (ANL) - Vendor A Und #1                "]
["1","04","03","03","05","02","Magnetic Measurement (ANL) - Vendor B Und #2                "]
["1","04","03","03","06","  ","Integrated Single-Undulator Module Test                     "]
["1","04","03","03","07","  "," System Test - Two Undulators                               "]
["1","04","03","04","  ","  ","Production Undulator Magnet Assembly & Supports             "]
["1","04","03","04","01","  ","Production Undulator Assembly - Vendor A                    "]
["1","04","03","04","02","  ","Production Undulator Assembly - Vendor B                    "]
["1","04","03","04","03","  ","Production Support/Mover Fabrication/Assembly               "]
["1","04","03","04","04","  ","Mu Metal Shield                                             "]
["1","04","03","05","  ","  ","Quadrupole Focusing Magnets                                 "]
["1","04","03","05","01","  ","Quadrupole Magnets                                          "]
["1","04","03","05","02","  ","Quadrupole Power Supplies                                   "]
["1","04","03","05","03","  ","Quadrupole Stages & Stands                                  "]
["1","04","03","05","04","  ","Quadrupole Cables                                           "]
["1","04","03","06","  ","  ","Undulator Magnetic Measurement Facility (SLAC)              "]
["1","04","03","06","01","  ","Undulator MMF Setup                                         "]
["1","04","03","06","01","01","Undulator Test Stand Prototype                              "]
["1","04","03","06","01","04","Undulator Test Stand                                        "]
["1","04","03","06","01","05","Undulator Fiducialization                                   "]
["1","04","03","06","01","06","Quad Strength and Field Quality                             "]
["1","04","03","06","01","07","Quad Fiducialization System                                 "]
["1","04","03","06","01","08","Hall Probe Calibration System                               "]
["1","04","03","06","01","09","Undulator Handling                                          "]
["1","04","03","06","02","  ","Fiducialization and Magnetic Measurements (F/MM)            "]
["1","04","03","06","02","01","F/MM Undulator Magnet Sections                              "]
["1","04","03","06","02","02","F/MM Quadrupoles                                            "]
["1","04","03","06","02","03","F/MM BPMs                                                   "]
["1","04","03","06","02","04","F/MM Correctors                                             "]
["1","04","03","06","02","05","F/MM Vacuum Chamber                                         "]
["1","04","03","06","02","06","F/MM Photon Diagnostics Components                          "]
["1","04","03","06","03","  ","Undulator Monitoring                                        "]
["1","04","03","06","03","01","Stretched Wire System                                       "]
["1","04","03","06","03","02","Hydrostatic Level System                                    "]
["1","04","03","06","03","03","F/MM BPMs                                                   "]
["1","04","03","06","03","04","0                                                           "]
["1","04","03","08","  ","  ","Fixed Supports                                              "]
["1","04","03","08","01","  ","Fixed Sppt Mgmt & Integration                               "]
["1","04","03","08","02","  ","Fixed Support Design                                        "]
["1","04","03","08","03","  ","Stabilized Girder Assemblies                                "]
["1","04","03","08","04","  ","Thermal Intercept System                                    "]
["1","04","03","08","05","  ","Thermometry                                                 "]
["1","04","03","08","06","  ","Kinematic Girder Support                                    "]
["1","04","03","08","07","  ","Earthquake Bracing                                          "]
["1","04","03","08","08","  ","Controls and Software                                       "]
["1","04","04","  ","  ","  ","Vacuum System                                               "]
["1","04","04","02","  ","  ","Undulator Vacuum Chamber Assembly                           "]
["1","04","04","02","01","  ","Prototype Chamber Weldment                                  "]
["1","04","04","02","02","  ","Production Chamber Weldment                                 "]
["1","04","04","02","03","  ","Prototype Aluminum Chamber                                  "]
["1","04","04","03","  ","  ","Beam-line Bellows Module Assembly                           "]
["1","04","04","03","01","  ","Prototype Bellows Module                                    "]
["1","04","04","03","02","  ","Production Bellows Module                                   "]
["1","04","04","04","  ","  ","Single Undulator Test (SUT) Vacuum                          "]
["1","04","04","05","  ","  ","Short Diagnostic Break (SDB) Assembly                       "]
["1","04","04","06","  ","  ","Long Diagnostic Break (LDB) Assembly                        "]
["1","04","04","07","  ","  ","Entrance Section Assembly                                   "]
["1","04","04","08","  ","  ","Exit Section Assembly                                       "]
["1","04","04","09","  ","  ","Baking System                                               "]
["1","04","05","  ","  ","  ","Diagnostics                                                 "]
["1","04","05","02","  ","  ","Undulator Line Diagnostics (ULD)                            "]
["1","04","05","02","01","  ","ULD Test Station                                            "]
["1","04","05","02","02","  ","ULD Vacuum Chamber                                          "]
["1","04","05","02","03","  ","Positioning Mechanism                                       "]
["1","04","05","02","04","  ","Scanning wire assembly (ULD-SWA)                            "]
["1","04","05","02","05","  ","Optical transition radiation imaging assembly               "]
["1","04","05","02","09","  ","ULD Design & Integration                                    "]
["1","04","05","04","  ","  ","End-of-Undulator(EOU) X-ray and Profile diagnost            "]
["1","04","05","04","01","  ","Prototype Construction and Testing                          "]
["1","04","05","04","02","  ","Bunch Length Monitor-Streak Camera (BLM)                    "]
["1","04","05","04","03","  ","Upstream corrector / separator                              "]
["1","04","05","04","04","  ","Optical Diffraction radiation imaging assembly (            "]
["1","04","05","04","05","  ","X-ray High Resolution monochromator assembly (EO            "]
["1","04","05","04","06","  ","X-ray Imaging High Resolution detector assembly             "]
["1","04","05","04","07","  ","EOU Design and Integration                                  "]
["1","04","05","05","  ","  ","RFBPM                                                       "]
["1","04","05","05","01","  ","X-Band Cavity BPM Development                               "]
["1","04","05","05","02","  ","X-Band Receiver Development                                 "]
["1","04","05","05","03","  ","X-Band BPM Production                                       "]
["1","04","05","06","  ","  ","Beam Finder Wire                                            "]
["1","04","05","07","  ","  ","Charge Monitor (CM)                                         "]
["1","04","05","08","  ","  ","Beam Loss Monitoring                                        "]
["1","04","05","09","  ","  ","Radiation Detection Monitor (RDM)                           "]
["1","04","05","10","  ","  ","SIngle Undulator Test (SUT) Diagnostics                     "]
["1","04","05","11","  ","  ","Supplemental Shielding                                      "]
["1","04","06","  ","  ","  ","Undulator System Installation and Alignment                 "]
["1","04","06","02","  ","  ","Control System Installation and Alignment                   "]
["1","04","06","04","  ","  ","Vacuum System Installation and Alignment                    "]
["1","04","06","05","  ","  ","Diagnostics System Installation and Alignment               "]
["1","04","06","06","  ","  ","2008 Undulator System Installation                          "]
["1","05","  ","  ","  ","  ","X-RAY TRANSPORT & DIAGNOSTICS SYSTEMS                       "]
["1","05","01","  ","  ","  ","System Management & Integration                             "]
["1","05","01","01","  ","  ","Management                                                  "]
["1","05","01","01","01","  ","XTOD Management - Technical                                 "]
["1","05","01","01","02","  ","LLNL Project Support                                        "]
["1","05","01","01","03","  ","Commissioning Coordinator                                   "]
["1","05","02","  ","  ","  ","Controls                                                    "]
["1","05","02","01","  ","  ","Controls                                                    "]
["1","05","02","01","01","  ","XTOD Global Controls                                        "]
["1","05","02","01","02","  ","FEE/EBD Controls                                            "]
["1","05","02","01","02","01","FEE/EBD Racks                                               "]
["1","05","02","01","02","02","FEE/EBD Vacuum Controls                                     "]
["1","05","02","01","02","03","EBD Fast Valve Controls                                     "]
["1","05","02","01","02","04","FEE Fixed Mask/Slit Controls                                "]
["1","05","02","01","02","05","FEE Attenuator Controls                                     "]
["1","05","02","01","02","06","FEE Gas Detector Controls                                   "]
["1","05","02","01","02","07","FEE Direct Imager Controls                                  "]
["1","05","02","01","02","08","FEE Total Energy Monitor Controls                           "]
["1","05","02","01","02","09","FEE K-Measurement Controls                                  "]
["1","05","02","01","02","10","FEE Soft X-Ray Imager Controls                              "]
["1","05","02","01","02","11","FEE SOMS Controls                                           "]
["1","05","02","01","02","12","FEE HOMS Controls                                           "]
["1","05","02","01","02","13","FEE Pop-Ins Controls                                        "]
["1","05","02","01","03","  ","NEH Controls                                                "]
["1","05","02","01","03","01","NEH Racks                                                   "]
["1","05","02","01","03","02","NEH Vacuum Controls                                         "]
["1","05","02","01","03","04","NEH Pop-Ins Controls                                        "]
["1","05","02","01","04","  ","TUN Controls                                                "]
["1","05","02","01","04","01","TUN Racks                                                   "]
["1","05","02","01","04","02","TUN Vacuum Controls                                         "]
["1","05","02","01","04","03","TUN Pop-Ins Controls                                        "]
["1","05","02","01","05","  ","FEH Controls                                                "]
["1","05","02","01","05","01","FEH Racks                                                   "]
["1","05","02","01","05","02","FEH Vacuum Controls                                         "]
["1","05","02","02","  ","  ","Motor Controls                                              "]
["1","05","02","03","  ","  ","Controls - Vacuum                                           "]
["1","05","03","  ","  ","  ","Mechanical & Vacuum Subsystem                               "]
["1","05","03","01","  ","  ","Vacuum Systems Engineering                                  "]
["1","05","03","02","  ","  ","Mech/Vac Front End                                          "]
["1","05","03","03","  ","  ","Mech/Vac Near Hall                                          "]
["1","05","03","03","01","  ","Mech/Vac Near Hall                                          "]
["1","05","03","03","02","  ","NEH Hutch 2                                                 "]
["1","05","03","03","03","  ","NEH Hutch 3                                                 "]
["1","05","03","04","  ","  ","Mech/Vac Tunnel                                             "]
["1","05","03","05","  ","  ","Mech/Vac Far Hall                                           "]
["1","05","04","  ","  ","  ","Optical  Subsystem                                          "]
["1","05","04","02","  ","  ","Facility Optics                                             "]
["1","05","04","02","01","  ","Fast Valve                                                  "]
["1","05","04","02","02","  ","Fixed Mask                                                  "]
["1","05","04","02","03","  ","Slit                                                        "]
["1","05","04","02","05","  ","Gas/Solid Attenuator                                        "]
["1","05","04","02","06","  ","TTF Damage Experiment                                       "]
["1","05","04","02","07","  ","FEL Offset Mirrors                                          "]
["1","05","04","02","07","01","SOMS Mirrors                                                "]
["1","05","04","02","07","02","HOMS Mirrors                                                "]
["1","05","04","02","08","  ","Solid Attenuator                                            "]
["1","05","05","  ","  ","  ","Diagnostics Subsystem                                       "]
["1","05","05","02","  ","  ","Modeling & Simulation                                       "]
["1","05","05","02","01","  ","Wave Model                                                  "]
["1","05","05","02","02","  ","Monte Carlo Model                                           "]
["1","05","05","02","03","  ","Beam Simulation                                             "]
["1","05","05","03","  ","  ","Facility Diagnostics                                        "]
["1","05","05","03","01","  ","Direct Imager                                               "]
["1","05","05","03","02","  ","Indirect Imager                                             "]
["1","05","05","03","06","  ","Gas Detector                                                "]
["1","05","05","04","  ","  ","Commissioning Diagnostics                                   "]
["1","05","05","04","02","  ","Total Energy Measurement                                    "]
["1","05","05","04","04","  ","Soft X-Ray Imager                                           "]
["1","05","05","04","05","  ","Popup Cameras                                               "]
["1","05","05","04","06","  ","K Measurement System                                        "]
["1","05","06","  ","  ","  ","X-Ray Transport System Installation & Alignment             "]
["1","05","06","01","  ","  ","FEE Install                                                 "]
["1","05","06","01","01","  ","FEE Cable Installation                                      "]
["1","05","06","01","02","  ","FEE Install - All excluding cable install                   "]
["1","05","06","02","  ","  ","Near Hall Install                                           "]
["1","05","06","03","  ","  ","Tunnel Install                                              "]
["1","05","06","04","  ","  ","Far Hall Install                                            "]
["1","05","06","05","  ","  ","Electron Dump Enclosure Install                             "]
["1","06","  ","  ","  ","  ","X-RAY END STATION SYSTEMS                                   "]
["1","06","01","  ","  ","  ","System Management & Integration                             "]
["1","06","01","01","  ","  ","Management                                                  "]
["1","06","01","02","  ","  ","SSRL Physics                                                "]
["1","06","02","  ","  ","  ","XES Controls                                                "]
["1","06","02","01","  ","  ","Controls Management                                         "]
["1","06","02","02","  ","  ","Network - Closed (Moved to new WBS Element)                 "]
["1","06","02","03","  ","  ","PC Support - Closed (Moved to New WBS Element)              "]
["1","06","02","04","  ","  ","Beamline Controls - AP - Closed  (Moved to new WBS Element) "]
["1","06","02","05","  ","  ","X-Ray PPS - Closed (Moved to new WBS Element)               "]
["1","06","02","05","01","  ","FEE X-Ray PPS - Closed (Moved to new WBS Element)           "]
["1","06","02","05","02","  ","Near Hall X-Ray PPS - Closed to BCWP                        "]
["1","06","02","06","  ","  ","X-Ray MPS - Closed (Moved to new WBS Element)               "]
["1","06","02","06","01","  ","FEE X-Ray MPS - Closed to BCWP                              "]
["1","06","02","07","  ","  ","AMOS Experiment Controls X1                                 "]
["1","06","02","07","01","  ","AMOS Requirements, Design, Setup                            "]
["1","06","02","07","07","  ","Development Hardware & Software                             "]
["1","06","02","07","08","  ","Beam Viewing System for Phase 1                             "]
["1","06","02","07","09","  ","Beam Viewing System for Phase 2                             "]
["1","06","02","07","12","  ","Differential Pumping                                        "]
["1","06","02","07","14","  ","Temperature Monitoring                                      "]
["1","06","02","07","15","  ","Gas Storage & Delivery System                               "]
["1","06","02","07","16","  ","High Field Physics Chamber                                  "]
["1","06","02","07","16","01","Vacuum & Motion                                             "]
["1","06","02","07","16","02","Gas Jet System                                              "]
["1","06","02","07","16","03","Electron Spectrometers (5)                                  "]
["1","06","02","07","16","04","Ion Spectrometers (TOF)                                     "]
["1","06","02","07","16","05","Ion Spectrometers (Imaging/Momentum)                        "]
["1","06","02","07","16","07","X-Ray Emission Spectrometers                                "]
["1","06","02","07","17","  ","Diagnostics Chamber                                         "]
["1","06","02","07","17","01","Vacuum & Motion                                             "]
["1","06","02","07","17","02","Gas Jet System                                              "]
["1","06","02","07","17","03","Mag Bottle Electr Spectr                                    "]
["1","06","02","07","17","04","X-Ray Emission Spectr.                                      "]
["1","06","02","07","18","  ","Total Power Measurement                                     "]
["1","06","02","08","  ","  ","AMOS Particle Imaging Controls                              "]
["1","06","02","08","01","  ","AMOS Particle Imaging Controls                              "]
["1","06","02","08","02","  ","AMOS Particle Imaging Software                              "]
["1","06","02","09","  ","  ","Controls Management - Closed (Moved to new WBS Element)     "]
["1","06","02","10","  ","  ","Global Controls System                                      "]
["1","06","02","10","01","  ","Network                                                     "]
["1","06","02","10","02","  ","Machine Protection System                                   "]
["1","06","02","10","03","  ","Personnel Protection System                                 "]
["1","06","02","10","04","  ","Laser Safety System (LSS)                                   "]
["1","06","02","10","05","  ","User Safeguards                                             "]
["1","06","02","10","06","  ","Timing System                                               "]
["1","06","02","10","07","  ","Data Management                                             "]
["1","06","02","10","07","01","Requirements, Design, Test Setup                            "]
["1","06","02","10","07","02","Data Storage                                                "]
["1","06","02","10","07","03","Data Movement                                               "]
["1","06","02","10","07","04","Data Reduction                                              "]
["1","06","02","10","07","06","Data Maintenance                                            "]
["1","06","02","10","08","  ","Global Cabling & Racks                                      "]
["1","06","02","10","09","  ","Laser Timing                                                "]
["1","06","02","10","11","  ","Common Hutch Controls                                       "]
["1","06","02","10","11","01","Workstation                                                 "]
["1","06","02","10","11","02","Photon Beam Control                                         "]
["1","06","02","10","11","03","Beam Line Processor                                         "]
["1","06","02","10","11","04","Local Hutch Controls                                        "]
["1","06","02","10","11","07","Pumping Section                                             "]
["1","06","02","10","11","08","Focusing Optics                                             "]
["1","06","02","10","12","  ","Data Acquisition (DAQ)                                      "]
["1","06","02","10","12","01","Requirements, Design, Test Setup                            "]
["1","06","02","10","12","02","DAQ Common                                                  "]
["1","06","02","10","12","03","CE                                                          "]
["1","06","02","10","12","04","CPCI                                                        "]
["1","06","02","10","12","05","2D Detector                                                 "]
["1","06","02","10","13","  ","Archives                                                    "]
["1","06","02","10","13","01","Requirements, Design, Test Setup                            "]
["1","06","02","10","13","02","DAQ Archive                                                 "]
["1","06","02","10","13","03","120 Hz Archives                                             "]
["1","06","02","10","13","04","EPICS Archive                                               "]
["1","06","02","10","14","  ","Data Retrieval & Analysis                                   "]
["1","06","02","10","14","01","Requirements, Design, Test Setup                            "]
["1","06","02","10","14","02","Data Retrieval                                              "]
["1","06","02","10","14","03","Data Analysis                                               "]
["1","06","02","11","  ","  ","Laser Controls                                              "]
["1","06","03","  ","  ","  ","Mechanical/Vacuum Subsystem                                 "]
["1","06","03","02","  ","  ","Vacuum Components - Mech/Vac                                "]
["1","06","03","02","02","  ","Hardware - Vacuum                                           "]
["1","06","04","  ","  ","  "," XES Laser System                                           "]
["1","06","04","01","  ","  ","XES Laser                                                   "]
["1","06","04","02","  ","  ","Laser Diagnostics                                           "]
["1","06","04","03","  ","  ","Laser Optical Transport                                     "]
["1","06","04","04","  ","  ","Laser Safety                                                "]
["1","06","05","  ","  ","  ","X-Ray Detectors                                             "]
["1","06","05","01","  ","  ","Beam Imaging                                                "]
["1","06","05","04","  ","  ","Detector & Streak Camera                                    "]
["1","06","05","04","01","  ","X-Ray Detector Management                                   "]
["1","06","06","  ","  ","  ","System Installation & Alignment                             "]
["1","06","06","01","  ","  ","Front End Install                                           "]
["1","06","06","02","  ","  ","Near Hall Install                                           "]
["1","06","06","02","01","  ","Mischarges - Closed                                         "]
["1","06","06","02","02","  ","Network Fiber Installation                                  "]
["1","06","06","02","03","  ","NEH Install Detectors                                       "]
["1","06","06","02","04","  ","NEH Install AMO Experiment                                  "]
["1","06","06","02","05","  ","NEH Install Laser                                           "]
["1","06","06","02","06","  ","NEH Install PPS                                             "]
["1","06","06","02","07","  ","NEH Install Laser PPS                                       "]
["1","06","06","02","08","  ","NEH Install 2008                                            "]
["1","06","06","02","09","  ","NEH Install Timing                                          "]
["1","06","06","02","99","  ","NEH Install - Other                                         "]
["1","06","06","03","  ","  ","Tunnel Install                                              "]
["1","06","06","04","  ","  ","Far Hall Install                                            "]
["1","06","06","04","02","  ","Far Hall Install Mech/Vac                                   "]
["1","06","06","05","  ","  ","Electron Dump Enclosure Install                             "]
["1","06","07","  ","  ","  ","AMOS Experiment                                             "]
["1","06","07","01","  ","  ","AMO Exp - Management & Design                               "]
["1","06","07","01","01","  "," Management                                                 "]
["1","06","07","01","02","  ","Conceptual Design                                           "]
["1","06","07","01","03","  "," Preliminary Design                                         "]
["1","06","07","01","04","  "," Final Design                                               "]
["1","06","07","02","  ","  ","AMO Exp - High Field Physics                                "]
["1","06","07","02","01","  ","X-Ray Fluorescence Spectrometer                             "]
["1","06","07","02","02","  ","Ion Imaging & TOF Detectors                                 "]
["1","06","07","02","03","  ","Sample Source                                               "]
["1","06","07","02","04","  ","Vacuum System                                               "]
["1","06","07","02","05","  ","Differential Pumping                                        "]
["1","06","07","02","06","  ","Pulse Shutter                                               "]
["1","06","07","03","  ","  ","AMO Exp - Refocus Optics                                    "]
["1","06","07","04","  ","  ","AMO Exp - Diagnostics                                       "]
["1","06","08","  ","  ","  ","K Measurement Crystals                                      "]
["1","06","08","01","  ","  ","K Measurement Crystals                                      "]
["1","06","09","  ","  ","  ","Mechanical Systems                                          "]
["1","06","09","01","  ","  ","PPS Stoppers                                                "]
["1","06","09","01","01","  ","E Dump PPS Stoppers                                         "]
["1","06","09","01","02","  ","Photon PPS Stoppers                                         "]
["1","06","09","02","  ","  ","PPS Shielding                                               "]
["1","06","09","03","  ","  "," NEH Hutch Doors                                            "]
["1","09","  ","  ","  ","  ","CONVENTIONAL FACILITIES                                     "]
["1","09","01","  ","  ","  ","System Management & Integration                             "]
["1","09","01","01","  ","  ","Management                                                  "]
["1","09","01","02","  ","  ","CAM/CF Engineering                                          "]
["1","09","01","03","  ","  ","Construction Management & AE Support                        "]
["1","09","01","04","  ","  ","Mechanical Design (MD)                                      "]
["1","09","01","04","01","  ","Mechanical Design Title 1 (Linac not included)              "]
["1","09","01","04","02","  ","Mechanical Design T1 Linac Facilities                       "]
["1","09","01","04","03","  ","Mechanical Design Title 2 (Linac not included)              "]
["1","09","01","04","04","  ","Mechanical Design T2 Linac Facilities                       "]
["1","09","01","04","05","  ","Mechanical Design Title 3 Linac Facility                    "]
["1","09","01","04","06","  ","Mechanical Design Title 3 (Linac not Included)              "]
["1","09","01","05","  ","  ","Conventional Experiment Facility (CEF)                      "]
["1","09","01","05","01","  ","CEF Engineering Title 1(Linac Not Included)                 "]
["1","09","01","05","02","  ","CEF Engineering Title 1 Linac Facility                      "]
["1","09","01","05","03","  ","CEF Engineering Title 2 (Linac Not Included)                "]
["1","09","01","05","04","  ","CEF Design Linac Facility Title 2                           "]
["1","09","02","  ","  ","  ","Title 1 & Title 2 Conventional Facilities                   "]
["1","09","02","02","  ","  ","A & E Services (S20, MMF, MMC not Incl)                     "]
["1","09","02","02","01","  ","Title 1 Design                                              "]
["1","09","02","02","02","  ","Title 2 Design                                              "]
["1","09","02","03","  ","  ","A & E Services - (S20, MMF,MCC)                             "]
["1","09","02","03","01","  ","Title 1 Design (Sector 20)                                  "]
["1","09","02","03","02","  ","Title 2 Design (Sector 20)                                  "]
["1","09","02","03","03","  ","Title 1 Design (MMF)                                        "]
["1","09","02","03","04","  ","Title 2 Design (MMF)                                        "]
["1","09","02","03","05","  ","MMF - Metals                                                "]
["1","09","02","03","06","  ","MMF - Woods & Plastics                                      "]
["1","09","03","  ","  ","  ","Construction -T3 Conventional Facilities                    "]
["1","09","03","01","  ","  ","Sector 20 Injector Facilities                               "]
["1","09","03","01","01","  ","S20 - Site Preparation/General Requirements                 "]
["1","09","03","01","02","  ","S20 - Site Construction                                     "]
["1","09","03","01","03","  ","S20 - Concrete                                              "]
["1","09","03","01","04","  ","S20 - Masonry                                               "]
["1","09","03","01","05","  ","S20 - Metals                                                "]
["1","09","03","01","06","  ","S20 - Woods & Plastics                                      "]
["1","09","03","01","07","  ","S20 - Thermal & Moisture Protection                         "]
["1","09","03","01","08","  ","S20 - Doors & Windows                                       "]
["1","09","03","01","09","  ","S20 - Finishes                                              "]
["1","09","03","01","10","  ","S20 - Specialties                                           "]
["1","09","03","01","14","  ","S20 - Conveying Systems                                     "]
["1","09","03","01","15","  ","S20 - Mechanical                                            "]
["1","09","03","01","16","  ","S20 - Electrical                                            "]
["1","09","03","01","20","  ","S20 - Project Close Out                                     "]
["1","09","03","02","  ","  ","Magnetic Measurement Facility                               "]
["1","09","03","02","01","  ","MMF - Site Preparation/General Requirements                 "]
["1","09","03","02","02","  ","MMF - Site Construction                                     "]
["1","09","03","02","03","  ","MMF - Concrete                                              "]
["1","09","03","02","04","  ","Utilities                                                   "]
["1","09","03","02","05","  ","MMF - Metals                                                "]
["1","09","03","02","06","  ","MMF - Woods & Plastics                                      "]
["1","09","03","02","07","  ","MMF - Thermal & Moisture Protection                         "]
["1","09","03","02","08","  ","MMF - Doors & Windows                                       "]
["1","09","03","02","09","  ","MMF - Finishes                                              "]
["1","09","03","02","10","  ","MMF - Specialities                                          "]
["1","09","03","02","13","  ","MMF - Special Construction                                  "]
["1","09","03","02","14","  ","MMF - Conveying Systems                                     "]
["1","09","03","02","15","  ","MMF - Mechanical                                            "]
["1","09","03","02","16","  ","MMF - Electrical                                            "]
["1","09","03","02","20","  ","MMF - Project Close Out                                     "]
["1","09","03","03","  ","  ","BTH West                                                    "]
["1","09","03","03","01","  ","BTH West - Site Preparation                                 "]
["1","09","03","03","15","  "," BTH West Mechanical                                        "]
["1","09","03","03","16","  "," BTH West - Electrical                                      "]
["1","09","03","03","20","  ","BTH West Project Close Out                                  "]
["1","09","03","04","  ","  ","Linac Facility Upgrade (LN)                                 "]
["1","09","03","04","01","  ","LN - Site Preparation                                       "]
["1","09","03","04","02","  ","LN - Sitework                                               "]
["1","09","03","04","05","  ","LN - Metals                                                 "]
["1","09","03","04","15","  ","LN - Mechanical                                             "]
["1","09","03","04","16","  ","LN - Electrical                                             "]
["1","09","03","04","20","  ","LN - Project Close Out                                      "]
["1","09","03","05","  ","  ","Research Yard                                               "]
["1","09","03","05","01","  ","RY - Site Preparation                                       "]
["1","09","03","05","02","  ","RY - Site Construction                                      "]
["1","09","03","05","20","  ","RY - Project Close Out                                      "]
["1","09","03","06","  ","  ","Pre-Purchase Equipment for Beam Path                        "]
["1","09","03","06","01","  ","PPE - General Requirements                                  "]
["1","09","03","06","10","  ","Project Close Out  Beam Trans Hall                          "]
["1","09","03","06","11","  ","PPE - Pre-Purchase Equipment                                "]
["1","09","03","07","  ","  ","SITEWORK, Earthwork, Site Utilities, & Survey               "]
["1","09","03","07","01","  ","SW - General Requirements                                   "]
["1","09","03","07","02","  ","SW - Earthwork, Site Utilities & Survey                     "]
["1","09","03","07","03","  ","SW - Concrete                                               "]
["1","09","03","07","15","  ","SW - Mechanical                                             "]
["1","09","03","07","16","  ","SW - Electrical                                             "]
["1","09","03","07","17","  ","SW - Others (include Div 4, and 6 through 14)               "]
["1","09","03","07","20","  ","SW - Project Close Out                                      "]
["1","09","03","08","  ","  ","Beam Transport Hall (BTH)                                   "]
["1","09","03","08","01","  ","BTH - Site Preparation/General Requirements                 "]
["1","09","03","08","02","  ","BTH - Site Construction                                     "]
["1","09","03","08","03","  ","BTH - Concrete                                              "]
["1","09","03","08","05","  ","BTH - Metals                                                "]
["1","09","03","08","15","  ","BTH - Mechanical                                            "]
["1","09","03","08","16","  ","BTH - Electrical                                            "]
["1","09","03","08","17","  ","BTH - Others (include Div 4, and 6 through 14)              "]
["1","09","03","08","20","  ","BTH - Project Close Out                                     "]
["1","09","03","09","  ","  ","Front End Enclosure (FEE)                                   "]
["1","09","03","09","01","  ","FEE - Site Preparation/General Requirements                 "]
["1","09","03","09","02","  ","FEE - Site Construction                                     "]
["1","09","03","09","03","  ","FEE - Concrete                                              "]
["1","09","03","09","05","  ","FEE - Metals                                                "]
["1","09","03","09","15","  ","FEE - Mechanical                                            "]
["1","09","03","09","16","  ","FEE - Electrical                                            "]
["1","09","03","09","17","  ","FEE - Others (include Div 4, and 6 through 14)              "]
["1","09","03","09","20","  ","FEE - Project Close Out                                     "]
["1","09","03","10","  ","  ","Electron Beam Dump (EBD)                                    "]
["1","09","03","10","01","  ","EBD - Site Preparation/General Requirements                 "]
["1","09","03","10","02","  ","EBD - Site Construction                                     "]
["1","09","03","10","03","  ","EBD - Concrete                                              "]
["1","09","03","10","05","  ","EBD - Metals                                                "]
["1","09","03","10","15","  ","EBD - Mechanical                                            "]
["1","09","03","10","16","  ","EBD - Electrical                                            "]
["1","09","03","10","17","  ","EBD - Others (include Div 4, and 6 through 14)              "]
["1","09","03","10","20","  ","EBD - Project Close Out                                     "]
["1","09","03","11","  ","  ","Near Experimental Hall (NEH)                                "]
["1","09","03","11","01","  ","NEH - Site Preparation/General Requirements                 "]
["1","09","03","11","02","  ","NEH - Site Construction                                     "]
["1","09","03","11","03","  ","NEH - Concrete                                              "]
["1","09","03","11","05","  ","NEH - Metals                                                "]
["1","09","03","11","15","  ","NEH - Mechanical                                            "]
["1","09","03","11","16","  ","NEH - Electrical                                            "]
["1","09","03","11","17","  ","NEH - Others (include Div 4, and 6 through 14)              "]
["1","09","03","11","20","  ","NEH - Project Close Out                                     "]
["1","09","03","12","  ","  ","Undulator Hall (UH)                                         "]
["1","09","03","12","01","  ","UH - Site Preparation/General Requirements                  "]
["1","09","03","12","02","  ","UH - Site Construction                                      "]
["1","09","03","12","03","  ","UH - Concrete                                               "]
["1","09","03","12","05","  ","UH - Metals                                                 "]
["1","09","03","12","15","  ","UH Mechanical                                               "]
["1","09","03","12","16","  ","UH - Electrical                                             "]
["1","09","03","12","17","  ","UH - Others (include Div 4, and 6 through 14)               "]
["1","09","03","12","19","  ","UH Tinnel Construction                                      "]
["1","09","03","13","  ","  ","X-Ray Transport & Diagnostic (XRTD)                         "]
["1","09","03","13","15","  ","XRTD - Mechanical                                           "]
["1","09","03","13","16","  ","XRTD - Electrical                                           "]
["1","09","03","13","17","  ","XRTD - Others (include Div 4, and 6 through 14)             "]
["1","09","03","13","19","  ","XRTD - Tunnel Construction                                  "]
["1","09","03","13","20","  ","XRTD - Project Close Out                                    "]
["1","09","03","14","  ","  ","Far Experimental Hall (FEH)                                 "]
["1","09","03","14","01","  ","FEH - Site Preparation/General Requirements                 "]
["1","09","03","14","02","  ","FEH - Site Construction                                     "]
["1","09","03","14","03","  ","FEH - Concrete                                              "]
["1","09","03","14","05","  ","FEH - Metals                                                "]
["1","09","03","14","15","  ","FEH - Mechanical                                            "]
["1","09","03","14","16","  ","FEH - Electrical                                            "]
["1","09","03","14","17","  ","FEH - Others (include Div 4, and 6 through 14)              "]
["1","09","03","14","18","  ","FEH - Access Tunnel                                         "]
["1","09","03","14","19","  ","FEH - Tunnel Construction                                   "]
["1","09","03","14","20","  ","FEH - Project Close Out                                     "]
["1","09","03","15","  ","  ","BTH Service Buildings 2.1, 2.2, and 2.3 (SB BTH)            "]
["1","09","03","15","03","  ","SB BTH - Concrete                                           "]
["1","09","03","15","05","  ","SB BTH - Metals                                             "]
["1","09","03","15","15","  ","SB BTH - Mechanical                                         "]
["1","09","03","15","16","  ","SB BTH - Electrical                                         "]
["1","09","03","15","17","  ","SB BTH - Others (include Div 4, and 6 through 14            "]
["1","09","03","15","20","  ","SB BTH - Project Close Out                                  "]
["1","09","03","16","  ","  ","UH Service Building 3.1 (SB UH)                             "]
["1","09","03","16","01","  ","SB UH - Site Preparation                                    "]
["1","09","03","16","03","  ","SB UH - Concrete                                            "]
["1","09","03","16","05","  ","SB UH - Metals                                              "]
["1","09","03","16","15","  ","SB UH - Mechanical                                          "]
["1","09","03","16","16","  ","SB UH - Electrical                                          "]
["1","09","03","16","17","  ","SB UH - Others (include Div 4, and 6 through 14)            "]
["1","09","03","16","20","  ","SB UH - Project Close Out                                   "]
["1","09","03","17","  ","  ","FEH Access Tunnel Service Yard (SY FEH)                     "]
["1","09","03","17","01","  ","SY FEH - Site Preparation                                   "]
["1","09","03","17","03","  ","SY FEH - Concrete                                           "]
["1","09","03","17","05","  ","SY FEH - Metals                                             "]
["1","09","03","17","15","  ","SY FEH - Mechanical                                         "]
["1","09","03","17","16","  ","SY FEH - Electrical                                         "]
["1","09","03","17","17","  ","SY FEH - Others (include Div 4, and 6 through 14            "]
["1","09","03","17","20","  ","SY FEH - Project Close Out                                  "]
["1","09","03","18","  ","  ","Central Utility Plant (CUP)                                 "]
["1","09","03","18","01","  ","CUP - Site Preparation/General Requirements                 "]
["1","09","03","18","02","  ","CUP - Site Construction                                     "]
["1","09","03","18","03","  ","CUP - Concrete                                              "]
["1","09","03","18","05","  ","CUP - Metals                                                "]
["1","09","03","18","15","  ","CUP - Mechanical                                            "]
["1","09","03","18","16","  ","CUP - Electrical                                            "]
["1","09","03","18","17","  ","CUP - Others (include Div 4, and 6 through 14)              "]
["1","09","03","18","20","  ","CUP - Project Close Out                                     "]
["1","09","03","19","  ","  ","SLAC Space Renovation for LCLS Ops                          "]
["1","09","03","19","01","  ","ED&I of SLAC Space Renovations for LCLS Ops                 "]
["1","09","03","19","02","  ","Construction of  SLAC Space Renovation for LCLS             "]
["1","09","03","20","  ","  ","Project Close Out - Conventional Facilities System          "]
["1","09","03","20","01","  ","Non-Turner Trade  Project Close Out                         "]
["1","09","03","20","02","  ","Turner Trade Project Close Out                              "]
["2","  ","  ","  ","  ","  ","LCLS PROJECT - R&D, SPARES, COMMISSIONING                   "]
["2","01","  ","  ","  ","  ","LCLS PROJECT MGMT, PLANNING & ADMN (OPC)                    "]
["2","01","01","  ","  ","  ","LCLS Commissioning Mgmt & Physics Support                   "]
["2","01","01","01","  ","  ","LCLS Commissioning Management                               "]
["2","01","01","02","  ","  ","Injector Physics                                            "]
["2","01","01","03","  ","  ","Linac Physics                                               "]
["2","01","01","04","  ","  ","Undulator Physics                                           "]
["2","01","01","05","  ","  ","X-Ray Transport Physics                                     "]
["2","01","01","06","  ","  ","X-Ray Physics Commissioning                                 "]
["2","01","01","07","  ","  ","Conventional Facilities Physics                             "]
["2","01","01","08","  ","  ","Consulting Physics (Collaboration)                          "]
["2","01","01","09","  ","  ","Consulting Physics (SLAC)                                   "]
["2","01","01","10","  ","  ","Global Controls Physics Liaison                             "]
["2","01","01","11","  ","  ","Global Controls OPC                                         "]
["2","01","01","11","01","  ","EPICS Control Modules                                       "]
["2","01","01","11","02","  ","LLRF Controls                                               "]
["2","01","01","11","11","  ","Global Controls Commissioning                               "]
["2","01","01","11","12","  ","Global Controls Management - OPC                            "]
["2","01","01","11","12","01","Global Controls Management - OPC Level of Effort            "]
["2","01","01","11","13","  ","SLC Aware IOC                                               "]
["2","01","01","11","14","  ","Controls - Networking and Data Comm. OPC                    "]
["2","01","01","11","15","  ","Controls S/W Applications LOE                               "]
["2","01","01","12","  ","  "," E-Beam Systems Commissioning Management                    "]
["2","01","01","13","  ","  "," E-Beam Systems Physics Support                             "]
["2","01","01","14","  ","  ","Laser Commissioning Management                              "]
["2","01","02","  ","  ","  ","R&D Studies & Prototyping                                   "]
["2","01","02","01","  ","  ","R&D Studies & Prototyping                                   "]
["2","01","03","  ","  ","  ","Project Mgmnt, Planning and Admn - M&S (OPC)                "]
["2","01","03","01","  ","  ","SLAC Project Office - General                               "]
["2","01","03","02","  ","  ","SLAC Project Support                                        "]
["2","01","03","03","  ","  ","Project Mgmnt, Planning and Admn - M&S (OPC)                "]
["2","01","03","05","  ","  ","X-Ray Transport Physics                                     "]
["2","01","03","06","  ","  ","X-Ray Endstation Physics                                    "]
["2","01","03","07","  ","  ","Conventional Facilities Physics                             "]
["2","01","03","08","  ","  ","Consulting Physics (Collaboration)                          "]
["2","01","03","09","  ","  ","Consulting Physics (SLAC)                                   "]
["2","01","03","10","  ","  ","Global Controls Physics Liaison                             "]
["2","01","03","11","  ","  "," Physics Commissioning Support - General                    "]
["2","02","  ","  ","  ","  ","INJECTOR SYSTEM (OPC)                                       "]
["2","02","01","  ","  ","  ","Injector System Management & Integration                    "]
["2","02","01","01","  ","  ","Injector System Integration Effort / M&S                    "]
["2","02","01","02","  ","  ","High level Application Software                             "]
["2","02","01","03","  ","  ","Feedback Software                                           "]
["2","02","02","  ","  ","  ","Injector Controls Subsystem                                 "]
["2","02","02","01","  ","  ","Personnel Protection System (PPS) R&D                       "]
["2","02","02","02","  ","  ","Beam Containment Subsystem (BCS)                            "]
["2","02","02","03","  ","  ","Machine Protection Subsystem (MPS)                          "]
["2","02","02","04","  ","  ","Power Conv (beamline pwr supp) Spares                       "]
["2","02","02","04","01","  ","Power Supply Controls                                       "]
["2","02","02","05","  ","  ","LLRF Controls                                               "]
["2","02","02","05","01","  ","LLRF Controls                                               "]
["2","02","02","06","  ","  ","E-Beam Diagnostics Controls                                 "]
["2","02","02","06","01","  ","Controls - Wire Scanners                                    "]
["2","02","02","06","02","  ","Controls - BPM Processor Module                             "]
["2","02","02","06","03","  ","Controls - Toroids                                          "]
["2","02","02","06","05","  ","Controls - Profile Monitors                                 "]
["2","02","02","06","06","  ","Control - EO Diagnostic                                     "]
["2","02","02","06","12","  ","Controls - Movable Collimator                               "]
["2","02","02","06","14","  ","Controls - Faraday Cup                                      "]
["2","02","02","06","15","  ","Controls - Tune-Up Dump                                     "]
["2","02","02","06","16","  ","Cherenkov Commissioning Support                             "]
["2","02","02","08","  ","  ","Timing Controls                                             "]
["2","02","02","09","  ","  ","Vacuum Controls                                             "]
["2","02","02","10","  ","  ","Software & Controls Infrastructure                          "]
["2","02","02","11","  ","  ","EPICS VXI Control Modules                                   "]
["2","02","02","12","  ","  ","Laser Controls                                              "]
["2","02","02","13","  ","  ","Laser Heater Controls                                       "]
["2","02","03","  ","  ","  ","Injector Lasers                                             "]
["2","02","03","01","  ","  ","Drive Laser Prototyping                                     "]
["2","02","03","02","  ","  ","Drive Laser System                                          "]
["2","02","03","03","  ","  ","Drive Laser Pre-Operations                                  "]
["2","02","03","14","  ","  ","LSR HTR - Beam Conditioning Optics (Laser Bay)              "]
["2","02","03","15","  ","  ","LSR HTR - Transport Optics (Bay to Tunnel)                  "]
["2","02","03","16","  ","  ","LSR HTR - Photon Beam Diagnostics                           "]
["2","02","04","  ","  ","  ","Injector RF Subsystem                                       "]
["2","02","04","01","  ","  ","RF Gun & Load Lock                                          "]
["2","02","04","01","01","  ","RF Gun                                                      "]
["2","02","04","01","02","  ","RF Gun Supports                                             "]
["2","02","04","01","03","  ","Gun Load Lock                                               "]
["2","02","04","02","  ","  ","Cathode Processing (CP) Station                             "]
["2","02","04","02","01","  ","CP Cathode Assembly & Supports                              "]
["2","02","04","02","02","  ","CP Load Lock                                                "]
["2","02","04","05","  ","  ","Injector RF Waveguide Subsystem                             "]
["2","02","04","05","02","  ","RF Waveguide Supports                                       "]
["2","02","04","06","  ","  ","Injector Linac Structures                                   "]
["2","02","04","06","02","  ","L0-2 Structure Assembly                                     "]
["2","02","05","  ","  ","  ","Injector Magnets & Supports                                 "]
["2","02","05","02","  ","  ","Injector Quadrupoles                                        "]
["2","02","05","02","03","  ","DL1 QB Quadrupole                                           "]
["2","02","05","02","05","  ","SAB Quadrupoles ( )                                         "]
["2","02","07","  ","  ","  ","Injector Diagnostics                                        "]
["2","02","07","01","  ","  ","Injector Beam Position Monitors                             "]
["2","02","07","01","03","  ","L0-1TL0-2 BPMs ( )                                          "]
["2","02","07","01","04","  ","LTDL1 BPMs ( )                                              "]
["2","02","07","04","  ","  ","Injector Profile Monitors                                   "]
["2","02","07","04","01","  ","GTL Faraday Cup/YAG1                                        "]
["2","02","08","  ","  ","  ","Injector System Emittance Enhancement                       "]
["2","02","08","01","  ","  ","Heater Integration                                          "]
["2","02","08","02","  ","  ","Heater Laser & Optics                                       "]
["2","02","08","03","  ","  ","Heater Magnets                                              "]
["2","02","08","03","01","  ","Heater Dipoles                                              "]
["2","02","08","03","02","  ","Heater Undulator                                            "]
["2","02","08","04","  ","  ","Heater Vacuum                                               "]
["2","02","08","05","  ","  ","Heater Diagnostics                                          "]
["2","02","08","06","  ","  ","Heater Install & Align                                      "]
["2","02","08","07","  ","  ","Laser Heater Controls                                       "]
["2","02","17","  ","  ","  ","Injector System Commissioning                               "]
["2","02","17","02","  ","  ","Drive Laser Commissioning                                   "]
["2","02","17","10","  ","  ","Injector Commisioning                                       "]
["2","02","17","11","  ","  ","Injector Engr, Design, Maintenance Support                  "]
["2","03","  ","  ","  ","  ","LINAC SYSTEM (OPC)                                          "]
["2","03","01","  ","  ","  ","Linac System Mgmt & Integration                             "]
["2","03","01","01","  ","  ","Linac System Mgmt & Integration                             "]
["2","03","02","  ","  ","  ","Linac Controls & Power Conversion Subsystem                 "]
["2","03","02","01","  ","  ","Personnel Protection System (PPS)                           "]
["2","03","02","02","  ","  ","Beam Containment System (BCS)                               "]
["2","03","02","03","  ","  ","Machine Protection System (MPS)                             "]
["2","03","02","04","  ","  ","Power Conversion                                            "]
["2","03","02","04","01","  ","Spare Power Supply (Dipole Type)                            "]
["2","03","02","04","02","  ","Spare Power Supply (Quad Type)                              "]
["2","03","02","04","03","  ","Spare Power Supply (Trim Type)                              "]
["2","03","02","04","04","  ","Controls & Power Supply - Spare Misc Hdwr                   "]
["2","03","02","05","  ","  ","Controls - LLRF                                             "]
["2","03","02","06","  ","  ","Controls - LLRF                                             "]
["2","03","02","06","01","  ","Controls - E-Beam Diagnostic                                "]
["2","03","02","06","02","  ","Controls - Wire Scanners                                    "]
["2","03","02","06","03","  ","Controls - BPMs                                             "]
["2","03","02","06","04","  ","Controls - Stoppers Commissioning                           "]
["2","03","02","06","05","  ","Controls - Profile Monitors                                 "]
["2","03","02","06","07","  ","Controls - BLM                                              "]
["2","03","02","06","09","  ","Controls - Single Beam Dump                                 "]
["2","03","02","06","10","  ","Controls - E-Beam Dump                                      "]
["2","03","02","06","12","  ","Controls - Collimators                                      "]
["2","03","02","08","  ","  ","Controls - Toroids                                          "]
["2","03","02","09","  ","  ","Controls - Vacuum                                           "]
["2","03","03","  ","  ","  ","Linac Magnets & Supports                                    "]
["2","03","03","01","  ","  ","Bend Magnet (BX1_BC1)                                       "]
["2","03","03","02","  ","  ","Bend Magnet (BX3_LTU)                                       "]
["2","03","03","03","  ","  ","Bend Magnet (BX2_BC2)                                       "]
["2","03","03","04","  ","  ","Bend Magnet (BY_LTU)                                        "]
["2","03","03","05","  ","  ","Quad Magnet (Quad_LTU)                                      "]
["2","03","03","09","  ","  ","Bend Magnet (BYD_LTU)                                       "]
["2","03","03","11","  ","  ","Bend Magnet (BYPM_LTU)                                      "]
["2","03","03","12","  ","  ","Bend Magnet (BYKIK_LTU)                                     "]
["2","03","03","13","  ","  ","Bend Magnet (BYW_LTU)                                       "]
["2","03","04","  ","  ","  ","Linac Vacuum Subsystem                                      "]
["2","03","04","01","  ","  ","Linac Vacuum Subsystem Operations Equip                     "]
["2","03","04","02","  ","  ","Linac Beamline Vacuum System                                "]
["2","03","04","03","  ","  ","BC1 Vacuum System                                           "]
["2","03","04","04","  ","  ","BC2 Vacuum System                                           "]
["2","03","04","05","  ","  ","Linac to Undulator (LTU) Vacuum System                      "]
["2","03","04","06","  ","  ","Dumpline Vacuum System                                      "]
["2","03","04","07","  ","  ","Vacuum Undulator Interface                                  "]
["2","03","04","07","01","  ","Entrance Assembly Section                                   "]
["2","03","04","07","02","  ","Exit Assembly Section                                       "]
["2","03","05","  ","  ","  ","Linac Electron Diagnostics                                  "]
["2","03","05","01","  ","  ","Wire Scanners                                               "]
["2","03","05","02","  ","  ","Beam Position Monitors                                      "]
["2","03","05","03","  ","  ","Toroids Beam Charge                                         "]
["2","03","05","04","  ","  ","Stoppers Tune Up Dump                                       "]
["2","03","05","05","  ","  ","Profile Monitors                                            "]
["2","03","05","07","  ","  ","Bunch Length Monitors                                       "]
["2","03","05","08","  ","  ","Beam Loss Monitors                                          "]
["2","03","05","11","  ","  ","Protection Collimators                                      "]
["2","03","05","12","  ","  ","Movable Collimators                                         "]
["2","03","05","13","  ","  ","Safety Dump                                                 "]
["2","03","05","14","  ","  ","Charge Monitor (Entrance/Exit Assebmly)                     "]
["2","03","06","  ","  ","  ","Linac RF Subsystem                                          "]
["2","03","06","05","  ","  ","X-Band High Power System                                    "]
["2","03","06","07","  ","  ","RF Distribution System                                      "]
["2","03","06","07","01","  ","Modulator                                                   "]
["2","03","06","07","02","  ","Solid State Sub Booster                                     "]
["2","03","06","07","05","  ","Bunch Length Electronics                                    "]
["2","03","06","07","07","  ","RF Distribution L2 & L3                                     "]
["2","03","06","07","08","  ","RF Fiber Optics Electronics                                 "]
["2","03","07","  ","  ","  ","Linac System Commissioning                                  "]
["2","03","07","10","  ","  ","L2/BC2/L3 Commissioning                                     "]
["2","04","  ","  ","  ","  ","UNDULATOR SYSTEM (OPC)                                      "]
["2","04","01","  ","  ","  ","Undulator System Management & Integration                   "]
["2","04","01","01","  ","  ","Undulator System Mgmt & Integration                         "]
["2","04","02","  ","  ","  ","Controls                                                    "]
["2","04","02","01","  ","  ","Controls Management and Integration                         "]
["2","04","02","07","  ","  ","Machine Protection                                          "]
["2","04","02","10","  ","  ","Undulator Controls Module Spares                            "]
["2","04","02","12","  ","  ","Undulator Controls Rack & Cables Spares                     "]
["2","04","02","15","  ","  ","BLM Interface Module Development                            "]
["2","04","03","  ","  ","  ","Undulator Magnet & Support                                  "]
["2","04","03","01","  ","  ","Und Magnet & Support-Mgmt & Integration                     "]
["2","04","03","02","  ","  ","First Prototype Undulator & Mfg Plan                        "]
["2","04","03","03","  ","  ","1st Article Undulators & Long Lead Procurements             "]
["2","04","03","04","  ","  ","Production Undulator                                        "]
["2","04","03","05","  ","  ","Focusing Magnets                                            "]
["2","04","03","06","  ","  ","Undulator Magnetic Measurement Facility (SLAC)              "]
["2","04","03","08","  ","  ","Fixed Supports                                              "]
["2","04","04","  ","  ","  ","Vacuum System                                               "]
["2","04","04","02","  ","  ","Undulator Vacuum Chamber Assembly                           "]
["2","04","04","02","01","  ","Surface Roughness Minimization                              "]
["2","04","04","02","03","  ","Materials Study for AC Conductivity                         "]
["2","04","04","03","  ","  ","Beam-line Bellows Module Assembly                           "]
["2","04","04","04","  ","  ","Single Undulator Test(SUV) Vacuum                           "]
["2","04","04","05","  ","  ","Short Diagnostic Break (SDB) Assembly                       "]
["2","04","04","06","  ","  ","Long Diagnostic Break (LDB) Assembly                        "]
["2","04","04","07","  ","  ","Entrance Section Assembly                                   "]
["2","04","04","08","  ","  ","Exit Section Assembly                                       "]
["2","04","04","09","  ","  ","Baking System                                               "]
["2","04","05","  ","  ","  ","Undulator System Diagnostics [OPC]                          "]
["2","04","05","02","  ","  ","Undulator Line Diagnostics                                  "]
["2","04","05","03","  ","  ","High-Power X-Ray and Profile Diagnostics (HPD)              "]
["2","04","05","04","  ","  ","End-of-Undulator(EOU) X-ray and Profile diagnost            "]
["2","04","05","05","  ","  ","RFBPM                                                       "]
["2","04","05","06","  ","  ","Beam Finder Wire                                            "]
["2","04","05","07","  ","  ","Charge Monitor (CM)                                         "]
["2","04","05","08","  ","  ","Beam Loss Monitoring                                        "]
["2","04","05","09","  ","  ","Radiation Detection Monitor (RDM)                           "]
["2","04","05","10","  ","  ","SIngle Undulator Test (SUT)-Diagnostics                     "]
["2","04","06","  ","  ","  ","LTU/Undulator/Dump Commissioning                            "]
["2","04","06","01","  ","  ","LTU/Undulator/Dump Commissioning                            "]
["2","05","  ","  ","  ","  ","X-RAY TRANSPORT & DIAGNOSTICS SYSTEMS (OPC)                 "]
["2","05","01","  ","  ","  ","System Management & Integration                             "]
["2","05","01","01","  ","  ","Management                                                  "]
["2","05","02","  ","  ","  ","Controls                                                    "]
["2","05","02","01","  ","  ","Controls - EPICS                                            "]
["2","05","02","02","  ","  ","Controls - System                                           "]
["2","05","03","  ","  ","  ","Mechanical & Vacuum Subsystem                               "]
["2","05","03","01","  ","  ","Vacuum Systems Engineering                                  "]
["2","05","03","02","  ","  ","Mech/Vac Front End                                          "]
["2","05","03","03","  ","  ","Mech/Vac Near Hall                                          "]
["2","05","03","04","  ","  ","Mech/Vac Tunnel                                             "]
["2","05","03","05","  ","  ","Mech/Vac Far Hall                                           "]
["2","05","04","  ","  ","  ","Optical Subsystem                                           "]
["2","05","04","01","  ","  "," Optical Subsystem R&D                                      "]
["2","05","04","02","  ","  ","Spares for Optical Subsystem                                "]
["2","05","04","03","  ","  ","End Station Optics                                          "]
["2","05","04","04","  ","  ","Crystals & Gratings                                         "]
["2","05","05","  ","  ","  ","Diagnostics Subsystem                                       "]
["2","05","05","01","  ","  "," Diagnostics Subsystem R&D                                  "]
["2","05","05","02","  ","  ","Modeling & Simulation                                       "]
["2","05","05","03","  ","  ","Spares for Diagnostics Subsystem                            "]
["2","05","05","04","  ","  ","Commissioning Diagnostics                                   "]
["2","05","06","  ","  ","  ","X-Ray Transport & Diag. System Commissioning                "]
["2","05","06","01","  ","  ","X-Ray Transport & Diag. System Commissioning                "]
["2","06","  ","  ","  ","  ","X-RAY END STATION SYSTEMS (OPC)                             "]
["2","06","01","  ","  ","  ","XE System Mgmt & Integration                                "]
["2","06","01","01","  ","  ","Management                                                  "]
["2","06","02","  ","  ","  ","Controls Subsystem                                          "]
["2","06","02","01","  ","  ","Cabling                                                     "]
["2","06","02","02","  ","  ","Network                                                     "]
["2","06","02","03","  ","  ","PC Support                                                  "]
["2","06","02","04","  ","  ","LBNL Laser Timing                                           "]
["2","06","02","05","  ","  ","X-Ray PPS                                                   "]
["2","06","02","06","  ","  ","X-Ray MPS                                                   "]
["2","06","02","07","  ","  ","Laser PPS                                                   "]
["2","06","02","08","  ","  ","2-D X-Ray Detector Controls                                 "]
["2","06","03","  ","  ","  ","Commissioning                                               "]
["2","06","04","  ","  ","  ","Spares                                                      "]
["2","06","04","01","  ","  ","Spares - PPS Stoppers                                       "]
["2","06","04","02","  ","  ","Spares -                                                    "]
["2","06","04","03","  ","  ","Spares -                                                    "]
["2","06","04","04","  ","  ","Spares -                                                    "]
["2","06","04","05","  ","  ","Spares -                                                    "]
["2","06","05","  ","  ","  ","X-Ray Detectors                                             "]
["2","06","05","01","  ","  ","Beam Imaging                                                "]
["2","06","05","02","  ","  ","2-D X-Ray Detector                                          "]
["2","06","05","02","01","  ","Proto 2 ASIC                                                "]
["2","06","05","02","02","  ","Proto 3 ASIC                                                "]
["2","06","05","02","03","  ","Full Lot Prototype                                          "]
["2","06","05","02","04","  ","500px Detector                                              "]
["2","06","05","02","05","  ","2D X-Ray Detector Commissioning                             "]
["2","06","05","03","  ","  ","Beam Intensity                                              "]
["2","06","05","04","  ","  ","Streak Camera                                               "]
["2","06","07","  ","  ","  ","Atomic Physics                                              "]
["2","06","07","01","  ","  ","Atomic Physics Samples                                      "]
["2","06","07","02","  ","  ","Atomic Physics Diagnostics                                  "]
["2","06","07","03","  ","  ","Atomic Physics Data Analysis                                "]
["2","06","07","04","  ","  ","Atomic Physics Detectors                                    "]
["2","09","  ","  ","  ","  ","Conventional Facility Commissioning                         "]
["2","09","03","  ","  ","  ","Beam Path Project Commissioning                             "]
["2","09","03","05","  ","  ","Beam Path Project Commissioning                             "]

{"sheet":"RAM","index":4,"n_rows":1347,"n_cols":39,"rows_kept":1347,"cut":false,"hidden":false,"merged":[[0,0,3,6],[4,0,9,6],[10,0,10,5],[4,37,5,37],[4,29,5,29],[4,11,5,11],[4,17,5,17]],"flags":["formulas_cached_only"]}
["LCLB Project\nResponsibility Assignment Matrix\nMarch 2008"]
[]
[{"$nulls":19},"LCLS Project  (Galayda)"]
[]
[{"$nulls":11},"Project Controls & Support Office (Boyce)",{"$nulls":5},"E-Beam Systems (Schultz)",{"$nulls":11},"Photon Systems (Arthur)"]
[]
[]
[]
[{"$nulls":11},"Project Controls & Support Office (Sisson)",null,"Commissioning     (Schultz)",null,"Controls       (Shoaee)",null,"Injector-Linac   (Chan)",null,"Undulator        (Pile)",null,"Undulator Alignment & Installation             (Chan)",null,"XTOD Controls           (McMahon)",null,"XE Controls           (Haller)",null,"X-Ray Transport & Diagnostics (McMahon)",null,"Laser                       (White)",null,"X-Ray End Station (Moeller)",null,"Commissioning (Tompkins)",null,"Physics Support (Arthur)",null,"Conventional Facilities          (Saenz)"]
[]
["WBS Level",{"$nulls":5},"Description","Performed","Budgeted"]
["1","2","3","4","5","6"]
[{"$nulls":6},"LINAC COHERENT LIGHT SOURCE (TPC)",{"$nulls":4},36686701.54,null,17332885.049999997,null,29118894.46000001,null,64136632.80000003,null,33780539.39999999,null,0,null,31455076.01000001,null,11054430.559999999,null,3983678.43,null,5693507.86,null,12529055.63,null,3803595.58,null,1608224.95,null,136874108.19]
["1","  ","  ","  ","  ","  ","LCLS PROJECT - PED & CONSTRUCTION                           ",{"$nulls":4},22351415.619999997,null,0,null,28342029.76000001,null,61658805.640000015,null,28098717.17,null,0,null,27590034.520000007,null,9015408.959999999,null,3983678.43,null,4953687.46,null,8133615.299999999,null,0,null,0,null,135008657.28000003]
["1","01","  ","  ","  ","  ","LCLS PROJECT MGMT, PLANNING & ADMN (TEC)                    ",{"$nulls":4},22351415.619999997,null,0,null,9498682.35,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","01","01","  ","  ","  ","Environment, Safety & Health                                ",{"$nulls":4},3282724.41,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","01","01","01","  ","  ","Radiation Physics                                           ",{"$nulls":4},1723724.21,{"$nulls":26},1]
["1","01","01","02","  ","  ","ESH Management & Coordination                               ",{"$nulls":4},1525363.66,{"$nulls":26},1]
["1","01","01","03","  ","  ","Professional Services-Project Office Support                ",{"$nulls":4},33636.54,{"$nulls":26},1]
["1","01","02","  ","  ","  ","Project Management                                          ",{"$nulls":4},16707868.02,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","01","02","01","  ","  ","Project Management Office                                   ",{"$nulls":4},16707868.02,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","01","02","01","01","  ","Project Office - General                                    ",{"$nulls":4},8022927.32,{"$nulls":26},1]
["1","01","02","01","02","  ","Project Support                                             ",{"$nulls":4},6501143.29,{"$nulls":26},1]
["1","01","02","01","03","  ","Project Office M&S                                          ",{"$nulls":4},1892285.77,{"$nulls":26},1]
["1","01","02","01","04","  ","SSRL Physics Support                                        ",{"$nulls":4},291511.64,{"$nulls":26},1]
["1","01","03","  ","  ","  ","Technical Integration                                       ",{"$nulls":4},2343316.39,null,0,null,9498682.35,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","01","03","01","  ","  ","Global Laser Coordination                                   ",{"$nulls":4},60601.86,{"$nulls":26},1]
["1","01","03","02","  ","  ","Global Alignment Coordination                               ",{"$nulls":4},472713.6,{"$nulls":26},1]
["1","01","03","03","  ","  ","System Integration                                          ",{"$nulls":4},1086998.66,{"$nulls":26},1]
["1","01","03","05","  ","  ","Global Controls                                             ",{"$nulls":4},0,null,0,null,9498682.35,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","01","03","05","01","  ","Global Controls Management                                  "]
["1","01","03","05","02","  ","LLRF Controls                                               ",{"$nulls":8},362200.99,{"$nulls":22},1]
["1","01","03","05","03","  ","E-beam Diagnostics & Controls                               ",{"$nulls":8},1742433.4,{"$nulls":22},1]
["1","01","03","05","03","01","Controls - Wire Scanners                                    "]
["1","01","03","05","03","02","Controls - Toroids                                          "]
["1","01","03","05","03","03","Controls - Faraday Cups                                     "]
["1","01","03","05","03","04","Controls - Tune-Up Dump                                     "]
["1","01","03","05","03","05","Controls - Profile Monitors                                 "]
["1","01","03","05","03","06","Controls - E/O Diagnostics                                  "]
["1","01","03","05","03","07","Controls - BPM                                              "]
["1","01","03","05","03","08","Controls - Stopppers                                        "]
["1","01","03","05","03","09","Controls - Bunch Length Monitors                            "]
["1","01","03","05","03","10","Controls - Beam Loss Monitors                               "]
["1","01","03","05","04","  ","Laser Controls Design                                       ",{"$nulls":8},23509.68,{"$nulls":22},1]
["1","01","03","05","05","  ","Laser Heater Controls                                       ",{"$nulls":8},860.16,{"$nulls":22},1]
["1","01","03","05","06","  ","Timing Controls                                             ",{"$nulls":8},77840.37,{"$nulls":22},1]
["1","01","03","05","07","  ","Vacuum Controls                                             ",{"$nulls":8},336915.54,{"$nulls":22},1]
["1","01","03","05","09","  ","Power Supply Controls                                       ",{"$nulls":8},2695942.11,{"$nulls":22},1]
["1","01","03","05","10","  ","PPS Controls                                                ",{"$nulls":8},802982.95,{"$nulls":22},1]
["1","01","03","05","11","  ","Controls - MPS                                              ",{"$nulls":8},27602.52,{"$nulls":22},1]
["1","01","03","05","12","  ","Global Controls Management                                  ",{"$nulls":8},3127233.02,{"$nulls":22},1]
["1","01","03","05","12","01","Global Controls Management LOE                              "]
["1","01","03","05","12","02","Global Controls Management                                  "]
["1","01","03","05","13","  ","SLC Aware IOC                                               ",{"$nulls":8},301161.61,{"$nulls":22},1]
["1","01","03","05","15","  ","Controls - BCS                                              ",{"$nulls":8},0,{"$nulls":22},1]
["1","01","03","06","  ","  ","Technical Requirements/Parameters                           ",{"$nulls":4},723002.27,{"$nulls":26},1]
["1","01","04","  ","  ","  ","Education Support                                           ",{"$nulls":4},17506.8,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","01","04","01","  ","  ","Education/Outreach Travel                                   ",{"$nulls":4},10634.22,{"$nulls":26},1]
["1","01","04","02","  ","  ","Education/Outreach M&S                                      ",{"$nulls":4},6872.58,{"$nulls":26},1]
["1","02","  ","  ","  ","  ","INJECTOR SYSTEM                                             ",{"$nulls":4},0,null,0,null,3618375.11,null,16267284.379999999,null,0,null,0,null,0,null,0,null,0,null,3972015.68,null,0,null,0,null,0,null,0]
["1","02","01","  ","  ","  ","Injector System Management & Integration                    ",{"$nulls":4},0,null,0,null,0,null,4642207.04,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","02","01","01","  ","  ","Injector System Integration                                 ",{"$nulls":4},0,null,0,null,0,null,1465706.03,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","02","01","01","01","  ","Injector Region Integration                                 ",{"$nulls":10},552876.93,{"$nulls":20},1]
["1","02","01","01","02","  ","Gun Area Integration                                        ",{"$nulls":10},155631.51,{"$nulls":20},1]
["1","02","01","01","03","  ","Accelerator Area Integration                                ",{"$nulls":10},105265.87,{"$nulls":20},1]
["1","02","01","01","04","  ","Heater Area Integration                                     ",{"$nulls":10},136198.42,{"$nulls":20},1]
["1","02","01","01","05","  ","Wall Area Integration                                       ",{"$nulls":10},112947.96,{"$nulls":20},1]
["1","02","01","01","06","  ","Insertion Area Integration                                  ",{"$nulls":10},117044.02,{"$nulls":20},1]
["1","02","01","01","07","  ","Spectrometer Area Integration                               ",{"$nulls":10},213097.59,{"$nulls":20},1]
["1","02","01","01","08","  ","Drive Laser Integration                                     ",{"$nulls":10},72643.73,{"$nulls":20},1]
["1","02","01","03","  ","  ","Feedback Software                                           ",{"$nulls":10},0.54,{"$nulls":20},1]
["1","02","01","04","  ","  ","Injector System Integration Effort / M&S                    ",{"$nulls":10},3176500.47,{"$nulls":20},1]
["1","02","02","  ","  ","  ","Injector Controls Subsystem                                 ",{"$nulls":4},0,null,0,null,3618375.11,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","02","02","01","  ","  ","Personnel Protection Subsystem (PPS)                        ",{"$nulls":8},195146.09,{"$nulls":22},1]
["1","02","02","02","  ","  ","Beam Containment Subsystem (BCS)                            ",{"$nulls":8},130158.53,{"$nulls":22},1]
["1","02","02","03","  ","  ","Machine Protection Subsystem (MPS)                          ",{"$nulls":8},160050.91,{"$nulls":22},1]
["1","02","02","04","  ","  ","Injector Power Conversion                                   ",{"$nulls":4},0,null,0,null,1045116.83,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","02","02","04","01","  ","Beamline Pwr Supplies - (Dipole Type)                       ",{"$nulls":8},101515.84,{"$nulls":22},1]
["1","02","02","04","01","01","10kw Power Supply - (Solenoid 1)                            "]
["1","02","02","04","01","02","30kw Power Supply - (Solenoid 2)                            "]
["1","02","02","04","01","03","2kw Power Supply - (B0.5 Spect)                             "]
["1","02","02","04","01","04","15kw Power Supply - (B1-2)                                  "]
["1","02","02","04","01","05","15kw Power Supply - (B3 Spect)                              "]
["1","02","02","04","01","06","10kw Power Supply - (New)                                   "]
["1","02","02","04","02","  ","Power Supply Controls                                       ",{"$nulls":8},21308.51,{"$nulls":22},1]
["1","02","02","04","03","  ","Beamline Pwr Supplies - (Trim Type)                         ",{"$nulls":8},168376.7,{"$nulls":22},1]
["1","02","02","04","03","01","12Amp Power Supply - (MCOR_1)                               "]
["1","02","02","04","03","02","30Amp Power Supply - (MCOR_2)                               "]
["1","02","02","04","03","03","30Amp Power Supply - (MCOR_3)                               "]
["1","02","02","04","03","04","30Amp Power Supply - (MCOR_4)                               "]
["1","02","02","04","04","  ","Beamline Pwr Supply - Misc Hdwr                             ",{"$nulls":8},753915.78,{"$nulls":22},1]
["1","02","02","04","05","  ","Magnet Interlock Protection System                          "]
["1","02","02","05","  ","  ","LLRF Controls                                               ",{"$nulls":4},0,null,0,null,617294.72,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","02","02","05","01","  ","Readback & Controls - RF Gun LLRF & Temperature             ",{"$nulls":8},617294.72,{"$nulls":22},1]
["1","02","02","05","02","  ","Readback & Controls - L0 LLRF                               ",{"$nulls":8},0,{"$nulls":22},1]
["1","02","02","05","03","  ","Readback & Controls - Transverse Cavity LLRF                ",{"$nulls":8},0,{"$nulls":22},1]
["1","02","02","05","04","  ","S-Band Cavity Controls                                      ",{"$nulls":8},0,{"$nulls":22},1]
["1","02","02","05","05","  ","EO Phase Controls                                           "]
["1","02","02","06","  ","  ","E-Beam Diagnostics Controls                                 ",{"$nulls":4},0,null,0,null,730362.95,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","02","02","06","01","  ","Controls - Wire Scanners                                    ",{"$nulls":8},71666.25,{"$nulls":22},1]
["1","02","02","06","02","  ","Controls - BPM                                              ",{"$nulls":8},105948.03,{"$nulls":22},1]
["1","02","02","06","03","  ","Controls - Toroids                                          ",{"$nulls":8},76031.05,{"$nulls":22},1]
["1","02","02","06","05","  ","Controls - Profile Monitors                                 ",{"$nulls":8},456749.03,{"$nulls":22},1]
["1","02","02","06","06","  ","Controls - E/O Diagnostics                                  ",{"$nulls":8},0,{"$nulls":22},1]
["1","02","02","06","12","  ","Controls - Movable Collimator                               ",{"$nulls":8},0,{"$nulls":22},1]
["1","02","02","06","14","  ","Controls - Faraday Cups                                     ",{"$nulls":8},1483.8,{"$nulls":22},1]
["1","02","02","06","15","  ","Controls - Tune-Up Dump                                     ",{"$nulls":8},18484.79,{"$nulls":22},1]
["1","02","02","06","16","  ","Diagnostics Controls Integration                            ",{"$nulls":8},0,{"$nulls":22},1]
["1","02","02","08","  ","  ","Timing Controls                                             ",{"$nulls":8},85879.59,{"$nulls":22},1]
["1","02","02","09","  ","  ","Vacuum Controls                                             ",{"$nulls":8},176015.31,{"$nulls":22},1]
["1","02","02","10","  ","  ","Software & Controls Infrastructure                          ",{"$nulls":4},0,null,0,null,287337.74,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","02","02","10","01","  ","Low Level Application Software                              "]
["1","02","02","10","02","  ","High Level Application Software                             "]
["1","02","02","10","03","  ","Data Communications                                         ",{"$nulls":8},91779.04,{"$nulls":22},1]
["1","02","02","10","04","  ","Computers & Crates                                          ",{"$nulls":8},195558.7,{"$nulls":22},1]
["1","02","02","11","  ","  ","EPICS VXI Control Modules                                   ",{"$nulls":8},90921.61,{"$nulls":22},1]
["1","02","02","12","  ","  ","Laser Controls                                              ",{"$nulls":4},0,null,0,null,100090.83,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","02","02","12","01","  ","Controls - Alignment Laser                                  "]
["1","02","02","12","02","  ","Controls - Gun Laser                                        ",{"$nulls":8},100090.83,{"$nulls":22},1]
["1","02","02","13","  ","  ","Laser Heater Controls                                       ",{"$nulls":8},0,{"$nulls":22},1]
["1","02","03","  ","  ","  ","Injector Lasers                                             ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,3972015.68,null,0,null,0,null,0,null,0]
["1","02","03","01","  ","  ","Drive Laser Support                                         ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,411874.29,null,0,null,0,null,0,null,0]
["1","02","03","01","01","  ","Drive Laser Support (ANL)                                   ",{"$nulls":22},28271.11,{"$nulls":8},1]
["1","02","03","01","02","  ","Drive Laser Support (LLNL)                                  ",{"$nulls":22},383603.18,{"$nulls":8},1]
["1","02","03","02","  ","  ","Drive Laser System                                          ",{"$nulls":22},1295292.74,{"$nulls":8},1]
["1","02","03","03","  ","  ","Drive Laser Diagnostics                                     ",{"$nulls":22},911619.61,{"$nulls":8},1]
["1","02","03","04","  ","  ","Timing Stability Monitoring                                 ",{"$nulls":22},120095.82,{"$nulls":8},1]
["1","02","03","05","  ","  ","Steering Stability Feedback & Msmts                         ",{"$nulls":22},94772.05,{"$nulls":8},1]
["1","02","03","06","  ","  ","Pre Amp Low Power Comp                                      ",{"$nulls":22},0,{"$nulls":8},1]
["1","02","03","07","  ","  ","Transport to Tunnel & Relay Optics                          ",{"$nulls":22},176706.36,{"$nulls":8},1]
["1","02","03","08","  ","  ","UV Launch, Conditioning & Diagnostics                       ",{"$nulls":22},413474.14,{"$nulls":8},1]
["1","02","03","09","  ","  ","Load Lock Transport System                                  "]
["1","02","03","10","  ","  ","Visible Optical Transport & Optics                          "]
["1","02","03","11","  ","  ","LB Infrastructure & LB System Wide Items                    ",{"$nulls":22},459890.53,{"$nulls":8},1]
["1","02","03","12","  ","  ","Alignment Laser                                             ",{"$nulls":22},53820.27,{"$nulls":8},1]
["1","02","03","13","  ","  ","Light path to Streak Camera                                 ",{"$nulls":22},28187.22,{"$nulls":8},1]
["1","02","03","14","  ","  ","LSR HTR - Beam Conditioning Optics (Laser Bay)              "]
["1","02","03","15","  ","  ","LSR HTR - Transport Optics (Bay to Tunnel)                  "]
["1","02","03","16","  ","  ","LSR HTR - Photon Beam Diagnostics                           "]
["1","02","03","21","  ","  ","UV Conv Harmonic Generation Unit (Closed Account)           ",{"$nulls":22},6282.65,{"$nulls":8},1]
["1","02","04","  ","  ","  ","Injector RF Subsystem                                       ",{"$nulls":4},0,null,0,null,0,null,5079089.95,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","02","04","01","  ","  ","RF Gun & Load Lock                                          ",{"$nulls":10},0,{"$nulls":20},1]
["1","02","04","01","01","  ","RF Gun                                                      ",{"$nulls":10},1357543.09,{"$nulls":20},1]
["1","02","04","01","02","  ","RF Gun Supports                                             ",{"$nulls":10},54030.37,{"$nulls":20},1]
["1","02","04","01","03","  ","Gun Load Lock                                               ",{"$nulls":10},675.12,{"$nulls":20},1]
["1","02","04","01","04","  ","Gun Load Lock Supports                                      ",{"$nulls":10},15296.86,{"$nulls":20},1]
["1","02","04","01","05","  ","Gun Solenoid                                                ",{"$nulls":10},280595.41,{"$nulls":20},1]
["1","02","04","01","06","  ","Gun Solenoid Supports                                       ",{"$nulls":10},940.03,{"$nulls":20},1]
["1","02","04","01","07","  ","Gun RF Feed                                                 ",{"$nulls":10},12471.84,{"$nulls":20},1]
["1","02","04","01","08","  ","Gun RF Feed Supports                                        ",{"$nulls":10},1039.97,{"$nulls":20},1]
["1","02","04","01","09","  ","RF Gun Spares Credit                                        ",{"$nulls":10},-435266.48,{"$nulls":20},1]
["1","02","04","02","  ","  ","Cathode Processing (CP) Station                             ",{"$nulls":4},0,null,0,null,0,null,334.25,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","02","04","02","01","  ","CP Cathode Assembly & Supports                              ",{"$nulls":10},0,{"$nulls":20},1]
["1","02","04","02","02","  ","CP Load Lock                                                ",{"$nulls":10},0,{"$nulls":20},1]
["1","02","04","02","03","  ","CP Load Lock Supports                                       ",{"$nulls":10},334.25,{"$nulls":20},1]
["1","02","04","02","04","  ","CP Station                                                  ",{"$nulls":10},0,{"$nulls":20},1]
["1","02","04","02","05","  ","Cathode Lab Infrastructure                                  ",{"$nulls":10},0,{"$nulls":20},1]
["1","02","04","03","  ","  ","S-Band Low Level Timing                                     ",{"$nulls":4},0,null,0,null,0,null,1647553.75,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","02","04","03","01","  ","Controls Interface & Timing                                 ",{"$nulls":10},372264.3,{"$nulls":20},1]
["1","02","04","03","02","  ","LLRF Phase Reference System                                 ",{"$nulls":10},239674.49,{"$nulls":20},1]
["1","02","04","03","03","  ","LLRF Monitor & Control System                               ",{"$nulls":10},875477.4,{"$nulls":20},1]
["1","02","04","03","04","  ","Beam Phase Monitor Cavity                                   ",{"$nulls":10},160137.56,{"$nulls":20},1]
["1","02","04","03","05","  ","RF System S/W Development / Docs                            ",{"$nulls":10},0,{"$nulls":20},1]
["1","02","04","04","  ","  ","S-Band High Power System                                    ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","02","04","04","01","  ","RF Gun High Power                                           "]
["1","02","04","04","02","  ","L0 High Power                                               "]
["1","02","04","04","03","  ","Transverse Cavity High Power                                ",{"$nulls":10},0,{"$nulls":20},1]
["1","02","04","05","  ","  ","Injector RF Waveguide Subsystem                             ",{"$nulls":10},0,{"$nulls":20},1]
["1","02","04","05","01","  ","RF Waveguides                                               ",{"$nulls":10},1169010.29,{"$nulls":20},1]
["1","02","04","05","02","  ","RF Waveguide Supports                                       ",{"$nulls":10},8.67,{"$nulls":20},1]
["1","02","04","06","  ","  ","Injector Linac Structures                                   ",{"$nulls":10},0,{"$nulls":20},1]
["1","02","04","06","01","  ","L0A-0B Structure Assembly                                   ",{"$nulls":10},749122.64,{"$nulls":20},1]
["1","02","04","06","03","  ","Major Linac Support                                         ",{"$nulls":10},42268.82,{"$nulls":20},1]
["1","02","04","06","04","  ","GTL RF Phase Cavity                                         "]
["1","02","04","06","05","  ","LTDL1 RF Kicker                                             ",{"$nulls":10},183465.32,{"$nulls":20},1]
["1","02","05","  ","  ","  ","Injector Magnets & Supports                                 ",{"$nulls":4},0,null,0,null,0,null,1229904.89,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","02","05","01","  ","  ","Injector Dipoles                                            ",{"$nulls":4},0,null,0,null,0,null,422405.34,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","02","05","01","01","  ","Gun Spectrometer Dipole                                     ",{"$nulls":10},96968.22,{"$nulls":20},1]
["1","02","05","01","02","  ","DL1 B01 & B02 Dipoles                                       ",{"$nulls":10},113622.66,{"$nulls":20},1]
["1","02","05","01","03","  ","SAB Spectrometer Dipole                                     ",{"$nulls":10},200049.12,{"$nulls":20},1]
["1","02","05","01","04","  ","Chicane DIPOLES (4)                                         ",{"$nulls":10},11765.34,{"$nulls":20},1]
["1","02","05","02","  ","  ","Injector Quads                                              ",{"$nulls":4},0,null,0,null,0,null,362556.66,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","02","05","02","01","  ","Gun Spectrometer Quadrupoles                                ",{"$nulls":10},66962.26,{"$nulls":20},1]
["1","02","05","02","02","  ","Injector Quadrupoles                                        ",{"$nulls":10},295486.88,{"$nulls":20},1]
["1","02","05","02","03","  ","TBD                                                         ",{"$nulls":10},107.52,{"$nulls":20},1]
["1","02","05","03","  ","  ","Injector Steering Coils                                     ",{"$nulls":4},0,null,0,null,0,null,234352.42,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","02","05","03","01","  ","Gun Solenoid Correctors                                     ",{"$nulls":10},7503.36,{"$nulls":20},1]
["1","02","05","03","02","  ","Gun Spectrometer Correctors                                 ",{"$nulls":10},0,{"$nulls":20},1]
["1","02","05","03","03","  ","Injector Correctors - A                                     ",{"$nulls":10},226727.67,{"$nulls":20},1]
["1","02","05","03","04","  ","Injector Correctors - D (Gun)                               ",{"$nulls":10},0,{"$nulls":20},1]
["1","02","05","03","05","  ","Gun Solenoid Quadrupole Correctors                          ",{"$nulls":10},121.39,{"$nulls":20},1]
["1","02","05","04","  ","  ","Linac Solenoid                                              ",{"$nulls":10},206600.06,{"$nulls":20},1]
["1","02","05","05","  ","  ","Injector Laser Heater Subsystem                             ",{"$nulls":10},0,{"$nulls":20},1]
["1","02","05","05","01","  ","System Design & Optimization (LSR HTR)                      ",{"$nulls":10},0,{"$nulls":20},1]
["1","02","05","05","02","  ","Injector Undulator                                          ",{"$nulls":10},3990.41,{"$nulls":20},1]
["1","02","06","  ","  ","  ","Injector Vacuum & Supports                                  ",{"$nulls":4},0,null,0,null,0,null,1186368.83,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","02","06","01","  ","  ","Injector Vacuum Engineering                                 ",{"$nulls":10},415522.83,{"$nulls":20},1]
["1","02","06","02","  ","  ","Injector Vacuum Components                                  ",{"$nulls":10},196201.03,{"$nulls":20},1]
["1","02","06","03","  ","  ","Injector Vacuum Special Chambers                            ",{"$nulls":10},308757.83,{"$nulls":20},1]
["1","02","06","04","  ","  ","Injector Vacuum Supports Engineering                        ",{"$nulls":10},76494.68,{"$nulls":20},1]
["1","02","06","05","  ","  ","Injector Vacuum Support Components                          ",{"$nulls":10},108730.84,{"$nulls":20},1]
["1","02","06","08","  ","  ","DL1 Vacuum Chamber                                          ",{"$nulls":10},6336,{"$nulls":20},1]
["1","02","06","10","  ","  ","DL1TL Vacuum Components                                     ",{"$nulls":10},74325.62,{"$nulls":20},1]
["1","02","07","  ","  ","  ","Injector Diagnostics                                        ",{"$nulls":10},0,{"$nulls":20},1]
["1","02","07","01","  ","  ","Beam Position Monitors                                      ",{"$nulls":4},0,null,0,null,0,null,663911.23,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","02","07","01","01","  ","Large Aperture BPM                                          ",{"$nulls":10},397666.8,{"$nulls":20},1]
["1","02","07","01","02","  ","Small Aperture BPM                                          ",{"$nulls":10},265734.82,{"$nulls":20},1]
["1","02","07","01","06","  ","TBD                                                         ",{"$nulls":10},509.61,{"$nulls":20},1]
["1","02","07","02","  ","  ","Current Monitors                                            ",{"$nulls":4},0,null,0,null,0,null,129362,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","02","07","02","01","  ","Current Monitors                                            ",{"$nulls":10},129362,{"$nulls":20},1]
["1","02","07","03","  ","  ","Bunch Length Monitors                                       "]
["1","02","07","03","01","  ","Bunch Length Monitors                                       "]
["1","02","07","04","  ","  ","Profile Monitors                                            ",{"$nulls":4},0,null,0,null,0,null,1406569.58,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","02","07","04","01","  ","Profile Monitors                                            ",{"$nulls":10},1353292.92,{"$nulls":20},1]
["1","02","07","04","02","  ","GTL Alignment Laser Mirror                                  ",{"$nulls":10},136.8,{"$nulls":20},1]
["1","02","07","04","03","  ","GS Faraday Cup/YAG2                                         ",{"$nulls":10},14961.62,{"$nulls":20},1]
["1","02","07","04","06","  ","DL1 OTR/YAG                                                 "]
["1","02","07","04","07","  ","DL1TL OTR/YAG                                               "]
["1","02","07","04","08","  ","LTDL1 OTR/YAG (6)                                           ",{"$nulls":10},38178.24,{"$nulls":20},1]
["1","02","07","05","  ","  "," Injector Wire Scanners                                     ",{"$nulls":10},111942.54,{"$nulls":20},1]
["1","02","07","06","  ","  ","LSR HTR - Electron Beam Diagnostics                         "]
["1","02","07","07","  ","  ","PPS Stopper                                                 ",{"$nulls":10},134140.73,{"$nulls":20},1]
["1","02","17","  ","  ","  ","Injector Installation & Alignment                           ",{"$nulls":10},0,{"$nulls":20},1]
["1","02","17","01","  ","  ","Injector Infrastructure Installation                        ",{"$nulls":10},807909.91,{"$nulls":20},1]
["1","02","17","02","  ","  ","Injector Controls Subsystem Install & Align                 ",{"$nulls":10},457860.48,{"$nulls":20},1]
["1","02","17","03","  ","  ","Injector Lasers Install & Align                             ",{"$nulls":10},92461.42,{"$nulls":20},1]
["1","02","17","04","  ","  ","Gun Area Integration                                        ",{"$nulls":10},32448.8,{"$nulls":20},1]
["1","02","17","06","  ","  ","Accelerator Area Integration                                ",{"$nulls":10},10015.18,{"$nulls":20},1]
["1","02","17","07","  ","  ","Heater Area Integration                                     ",{"$nulls":10},2099.75,{"$nulls":20},1]
["1","02","17","08","  ","  ","Wall Area Integration                                       ",{"$nulls":10},46442.29,{"$nulls":20},1]
["1","02","17","09","  ","  ","Insertion Area Integration                                  ",{"$nulls":10},6.81,{"$nulls":20},1]
["1","02","17","11","  ","  ","Spectrometer Area Integration                               ",{"$nulls":10},0,{"$nulls":20},1]
["1","02","17","12","  ","  ","Injector RF High Power System Install & Align               ",{"$nulls":10},234542.95,{"$nulls":20},1]
["1","02","17","15","  ","  ","Laser Heater Installation                                   ",{"$nulls":10},0,{"$nulls":20},1]
["1","03","  ","  ","  ","  ","LINAC SYSTEM                                                ",{"$nulls":4},0,null,0,null,11546714.610000001,null,28257053.989999995,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","03","01","  ","  ","  ","System Management & Integration                             ",{"$nulls":4},0,null,0,null,0,null,6752718.18,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","03","01","01","  ","  ","Linac Mechanical Integration                                ",{"$nulls":4},0,null,0,null,0,null,4163239.06,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","03","01","01","01","  ","L01 System Integration                                      ",{"$nulls":10},338886.18,{"$nulls":20},1]
["1","03","01","01","02","  ","BC1 System Integration                                      ",{"$nulls":10},454182.12,{"$nulls":20},1]
["1","03","01","01","03","  ","L02 System Integration                                      ",{"$nulls":10},195163.47,{"$nulls":20},1]
["1","03","01","01","04","  ","BC2 System Integration                                      ",{"$nulls":10},868912.74,{"$nulls":20},1]
["1","03","01","01","05","  ","L03 System Integration                                      ",{"$nulls":10},213976.09,{"$nulls":20},1]
["1","03","01","01","06","  ","LTU System Integration                                      ",{"$nulls":10},958825.85,{"$nulls":20},1]
["1","03","01","01","07","  ","E-Dump System Integration                                   ",{"$nulls":10},1133292.61,{"$nulls":20},1]
["1","03","01","03","  ","  ","Travel                                                      ",{"$nulls":10},97236.16,{"$nulls":20},1]
["1","03","01","04","  ","  ","Linac Management                                            ",{"$nulls":10},2492242.96,{"$nulls":20},1]
["1","03","02","  ","  ","  ","Linac Controls & Power Conversion Subsystem                 ",{"$nulls":4},0,null,0,null,11342781.06,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","03","02","01","  ","  ","Personnel Protection System (PPS)                           ",{"$nulls":8},672929.51,{"$nulls":22},1]
["1","03","02","02","  ","  ","Beam Containment System (BCS)                               ",{"$nulls":8},604752.770000001,{"$nulls":22},1]
["1","03","02","03","  ","  ","Machine Protection System (MPS)                             ",{"$nulls":8},269017.21,{"$nulls":22},1]
["1","03","02","04","  ","  ","Linac Power Conversion Subsystem                            ",{"$nulls":4},0,null,0,null,4665840.84,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","03","02","04","01","  ","Beamline Power Supplies - (Dipole Type)                     ",{"$nulls":8},423322.55,{"$nulls":22},1]
["1","03","02","04","01","01","25kw Pwr Supply - (BX11-14)                                 "]
["1","03","02","04","01","02","Power Supply - (BX21-24)                                    "]
["1","03","02","04","01","03","Kicker (BXKIK)                                              "]
["1","03","02","04","01","04","BX31,32,35,36                                               "]
["1","03","02","04","01","05","Power Supply - (BY1-2)                                      "]
["1","03","02","04","01","06","Kicker (BYBKIK)                                             "]
["1","03","02","04","01","07","BYW1-3                                                      "]
["1","03","02","04","01","08","Muon Spoiler (MUSPLR)                                       "]
["1","03","02","04","01","09","BYD1-3                                                      "]
["1","03","02","04","02","  ","Beamline Power Supplies - (Quad Type)                       ",{"$nulls":8},113592.07,{"$nulls":22},1]
["1","03","02","04","02","06","Q21201-Q21901 Split                                         "]
["1","03","02","04","02","07","Q24201-Q24501 Split                                         "]
["1","03","02","04","02","08","Q24601                                                      "]
["1","03","02","04","02","09","10KW PS - (Q24701A,Q24701B)                                 "]
["1","03","02","04","02","10","QM21                                                        "]
["1","03","02","04","02","11","Q24901A,Q24901B                                             "]
["1","03","02","04","02","12","10kw Power Supply - (QM22)                                  "]
["1","03","02","04","02","13","Power Supply - (Q5)                                         "]
["1","03","02","04","02","14","Power Supply - (QVM2)                                       "]
["1","03","02","04","02","15","Power Supply - (QA0)                                        "]
["1","03","02","04","02","16","Power Supply - (Q50Q1,Q50Q2,Q50Q3)                          "]
["1","03","02","04","02","17","Power Supply - (QVM1)                                       "]
["1","03","02","04","02","18","Power Supply - (QVM2)                                       "]
["1","03","02","04","02","19","Power Supply - (QVM3)                                       "]
["1","03","02","04","02","20","Power Supply - (QVM4)                                       "]
["1","03","02","04","02","21","Power Supply - (QVB1-3)                                     "]
["1","03","02","04","02","22","Power Supply - (QDL31-34)                                   "]
["1","03","02","04","02","23","Power Supply - (QE31-36)                                    "]
["1","03","02","04","02","24","Power Supply - (QEM1)                                       "]
["1","03","02","04","02","25","Power Supply - (QEM2)                                       "]
["1","03","02","04","02","26","Power Supply - (QEM3)                                       "]
["1","03","02","04","02","27","Power Supply - (QEM4)                                       "]
["1","03","02","04","02","28","Power Supply - (QT11,13,21,23,31,33,41,43)                  "]
["1","03","02","04","02","29","Power Supply - (QT12,22,32,42)                              "]
["1","03","02","04","02","30","Power Supply - (QDM1)                                       "]
["1","03","02","04","02","31","Power Supply - (QUM2)                                       "]
["1","03","02","04","02","32","Power Supply - (QUM3)                                       "]
["1","03","02","04","02","33","Power Supply - (Qum4)                                       "]
["1","03","02","04","02","34","Power Supply - (QDMP1-2)                                    "]
["1","03","02","04","02","35","Power Supply - (QUE1)                                       "]
["1","03","02","04","02","36","Power Supply - (QUE2)                                       "]
["1","03","02","04","02","37","Rack Accessories - LI21                                     "]
["1","03","02","04","02","38","Rack Accessories - LI24                                     "]
["1","03","02","04","02","39","Rack Accessories - LI25                                     "]
["1","03","02","04","02","40","Rack Accessories - BSY                                      "]
["1","03","02","04","02","41","Rack Accessories - Dump                                     "]
["1","03","02","04","03","  ","Beamline Power Supplies - (Trim Type)                       ",{"$nulls":8},744587.6,{"$nulls":22},1]
["1","03","02","04","03","01","12Amp Power Supply - (MCOR_1)                               "]
["1","03","02","04","03","02","30Amp Power Supply - (MCOR_2)                               "]
["1","03","02","04","03","03","30Amp Power Supply - (MCOR_3)                               "]
["1","03","02","04","03","04","30Amp Power Supply - (MCOR_4)                               "]
["1","03","02","04","03","05","12/30 Amp Power Supply (MCOR_5)                             "]
["1","03","02","04","03","06","12/30 Amp Power Supply (MCOR_6)                             "]
["1","03","02","04","03","07","12 Amp Power Supply (MCOR_BSY1)                             "]
["1","03","02","04","03","08","12 Amp Power Supply (MCOR_LTU1)                             "]
["1","03","02","04","03","09","12 Amp Power Supply (MCOR_LTU2)                             "]
["1","03","02","04","03","10","Power Supply - (MCOR_LTU3)                                  "]
["1","03","02","04","03","11","Power Supply - (MCOR_LTU4)                                  "]
["1","03","02","04","03","12","Power Supply - (MCOR_LTU5)                                  "]
["1","03","02","04","03","13","Power Supply - (MCOR_LTU6)                                  "]
["1","03","02","04","03","14","Power Supply - (MCOR_LTU7)                                  "]
["1","03","02","04","03","15","Power Supply - (MCOR_LTU8)                                  "]
["1","03","02","04","03","16","Powe Supply (MCOR_LTU9)                                     "]
["1","03","02","04","03","17","Power Supply (MCOR_DMP1)                                    "]
["1","03","02","04","03","18","MCOR Bulk PS - LI21_1                                       "]
["1","03","02","04","03","19","MCOR Bulk PS - LI21_2                                       "]
["1","03","02","04","03","20","MCOR Bulk PS - LI24                                         "]
["1","03","02","04","03","21","MCOR Bulk PS - LI25                                         "]
["1","03","02","04","03","22","MCOR Bulk PS - BSY                                          "]
["1","03","02","04","03","23","MCOR Bulk PS - LTU_1                                        "]
["1","03","02","04","03","24","MCOR Bulk PS - LTU_2                                        "]
["1","03","02","04","03","25","MCOR Bulk PS - LTU_3                                        "]
["1","03","02","04","03","26","MCOR Bulk PS - LTU_4                                        "]
["1","03","02","04","03","27","MCOR PLC - LI21                                             "]
["1","03","02","04","03","28","MCOR PLC - LI24                                             "]
["1","03","02","04","03","29","MCOR PLC - LI25                                             "]
["1","03","02","04","03","30","MCOR PLC - BSY                                              "]
["1","03","02","04","03","31","MCOR PLC - LTU_1 (BLD 2.1)                                  "]
["1","03","02","04","03","32","MCOR PLC - LTU_2 (BLD 2.2)                                  "]
["1","03","02","04","03","33","MCOR PLC - LTU_3 (BLD 2.3)                                  "]
["1","03","02","04","03","34","MCOR PLC - Dump                                             "]
["1","03","02","04","03","35","MCOR Bulk Dump                                              "]
["1","03","02","04","03","36","Rack Accessories - LTU_1 (bld 2.1)                          "]
["1","03","02","04","03","37","Rack Accessories - LTU_2 (bld 2.2)                          "]
["1","03","02","04","03","38","Rack Accessories - LTU_3 (bld 2.3)                          "]
["1","03","02","04","04","  ","Controls & Power Supply                                     ",{"$nulls":8},3384338.62,{"$nulls":22},1]
["1","03","02","05","  ","  ","Controls - LLRF                                             ",{"$nulls":8},970610.68,{"$nulls":22},1]
["1","03","02","05","01","  ","Solid State Sub-booster 5x                                  "]
["1","03","02","05","03","  ","L2/L3 RF Distribution                                       "]
["1","03","02","05","04","  ","Beam Phase Measurement 2X                                   "]
["1","03","02","05","05","  ","Sector 24 Rack Electrical Crate IOC/EVG                     "]
["1","03","02","05","06","  ","Sector 24 T-Cav                                             "]
["1","03","02","05","07","  ","Sector 29/30 Controls (PACs & PADs)                         "]
["1","03","02","05","10","  ","RF Stability/Feedback                                       "]
["1","03","02","05","11","  ","System Documentation                                        "]
["1","03","02","06","  ","  ","Controls - E-Beam Diagnostic                                ",{"$nulls":4},0,null,0,null,1463118.95,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","03","02","06","01","  ","Controls - Wire Scanners                                    ",{"$nulls":8},265843.58,{"$nulls":22},1]
["1","03","02","06","02","  ","Controls - BPMs                                             ",{"$nulls":8},746504.56,{"$nulls":22},1]
["1","03","02","06","03","  ","Controls - Toroids                                          ",{"$nulls":8},87104.51,{"$nulls":22},1]
["1","03","02","06","04","  ","Controls - Stoppers                                         ",{"$nulls":8},6283.47,{"$nulls":22},1]
["1","03","02","06","05","  ","Controls - Profile Monitors                                 ",{"$nulls":8},156447.69,{"$nulls":22},1]
["1","03","02","06","06","  ","Controls - E/O Diagnostics                                  ",{"$nulls":8},0,{"$nulls":22},1]
["1","03","02","06","07","  ","Controls - Bunch Length Monitors                            ",{"$nulls":8},65741.64,{"$nulls":22},1]
["1","03","02","06","08","  ","Controls - Beam Loss Monitors                               ",{"$nulls":8},0,{"$nulls":22},1]
["1","03","02","06","09","  ","Controls - Single Beam Dump                                 ",{"$nulls":8},2836.8,{"$nulls":22},1]
["1","03","02","06","10","  ","Controls - E Beam Dump                                      ",{"$nulls":8},1087.44,{"$nulls":22},1]
["1","03","02","06","11","  ","Controls - Protection Collimator                            ",{"$nulls":8},52372.09,{"$nulls":22},1]
["1","03","02","06","12","  ","Controls - Movable Collimator                               ",{"$nulls":8},77406.77,{"$nulls":22},1]
["1","03","02","06","13","  ","Controls - X-Band Accel Structure                           ",{"$nulls":8},1490.4,{"$nulls":22},1]
["1","03","02","08","  ","  ","Controls - Timing                                           ",{"$nulls":8},396181.51,{"$nulls":22},1]
["1","03","02","09","  ","  ","Controls - Vacuum                                           ",{"$nulls":4},0,null,0,null,483266.02,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","03","02","09","01","  ","Controls - Vacuum Instrumentation & Interlocks              ",{"$nulls":8},483266.02,{"$nulls":22},1]
["1","03","02","09","02","  ","Controls - Vacuum Pump Power Supplies                       ",{"$nulls":8},0,{"$nulls":22},1]
["1","03","02","10","  ","  ","Software & Controls Infrastructure                          ",{"$nulls":4},0,null,0,null,1817063.57,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","03","02","10","04","  ","Data Communications                                         ",{"$nulls":8},885600,{"$nulls":22},1]
["1","03","02","10","05","  ","Computers                                                   ",{"$nulls":8},931463.57,{"$nulls":22},1]
["1","03","03","  ","  ","  ","Linac Magnets & Supports                                    ",{"$nulls":4},0,null,0,null,0,null,2772051.31,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","03","03","01","  ","  ","Bend Magnet (BX1_BC1)                                       ",{"$nulls":10},141909.26,{"$nulls":20},1]
["1","03","03","02","  ","  ","Bend Magnet (BX3_LTU)                                       ",{"$nulls":10},235101.18,{"$nulls":20},1]
["1","03","03","03","  ","  ","Bend Magnet (BX2_BC2)                                       ",{"$nulls":10},421082.32,{"$nulls":20},1]
["1","03","03","04","  ","  ","Bend Magnet (BY_LTU)                                        ",{"$nulls":10},87388.37,{"$nulls":20},1]
["1","03","03","05","  ","  ","Quad Magnet (Quad_LTU)                                      ",{"$nulls":10},753948.22,{"$nulls":20},1]
["1","03","03","07","  ","  ","Quad Magnet (QE)                                            ",{"$nulls":10},165104.6,{"$nulls":20},1]
["1","03","03","08","  ","  ","Corrector Magnet (Type 4)                                   ",{"$nulls":10},139160.52,{"$nulls":20},1]
["1","03","03","09","  ","  ","Bend Magnet (BYD_DUMP)                                      ",{"$nulls":10},445043.1,{"$nulls":20},1]
["1","03","03","10","  ","  ","Quad Magnet (QA)                                            ",{"$nulls":10},105022.22,{"$nulls":20},1]
["1","03","03","11","  ","  ","Bend Magnet (BYPM_LTU)                                      ",{"$nulls":10},109226.87,{"$nulls":20},1]
["1","03","03","12","  ","  ","Bend Magnet (BYKIK_LTU)                                     ",{"$nulls":10},116878.29,{"$nulls":20},1]
["1","03","03","13","  ","  ","Bend Magnet (BYW_LTU)                                       ",{"$nulls":10},1008,{"$nulls":20},1]
["1","03","03","14","  ","  ","BXKIK LINAC TCAV Screen Kicker                              ",{"$nulls":10},51178.36,{"$nulls":20},1]
["1","03","03","15","  ","  ","Muon Toroid (E-Dump)                                        ",{"$nulls":10},0,{"$nulls":20},1]
["1","03","04","  ","  ","  ","Linac Vacuum Subsystem                                      ",{"$nulls":4},0,null,0,null,0,null,3367964.64,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","03","04","02","  ","  ","Linac Beamline Vacuum System                                ",{"$nulls":10},540159.52,{"$nulls":20},1]
["1","03","04","03","  ","  ","BC1 Vacuum System                                           ",{"$nulls":10},670792.43,{"$nulls":20},1]
["1","03","04","04","  ","  ","BC2 Vacuum System                                           ",{"$nulls":10},489674.31,{"$nulls":20},1]
["1","03","04","05","  ","  ","Linac to Undulator (LTU) Vacuum System                      ",{"$nulls":10},868343.74,{"$nulls":20},1]
["1","03","04","06","  ","  ","Dumpline Vacuum System                                      ",{"$nulls":10},703317.3,{"$nulls":20},1]
["1","03","04","07","  ","  ","Vacuum System Undulator Interface                           ",{"$nulls":4},0,null,0,null,0,null,14057.57,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","03","04","07","01","  ","Entrance Section Assembly                                   ",{"$nulls":10},5575.36,{"$nulls":20},1]
["1","03","04","07","02","  ","Exit Section Assembly                                       ",{"$nulls":10},8482.21,{"$nulls":20},1]
["1","03","04","08","  ","  ","LTU/BSY& Cold Trap Vacuum System                            ",{"$nulls":10},81619.77,{"$nulls":20},1]
["1","03","05","  ","  ","  ","Linac Electron Diagnostics Summary                          ",{"$nulls":4},0,null,0,null,0,null,5094597.8,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","03","05","01","  ","  ","Wire Scanners (7) Summary                                   ",{"$nulls":10},584784.23,{"$nulls":20},1]
["1","03","05","02","  ","  ","Beam Position Monitors                                      ",{"$nulls":4},0,null,0,null,0,null,632603.52,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","03","05","02","01","  ","BPM - Standard  Linac (4) Summary                           ",{"$nulls":10},145896.58,{"$nulls":20},1]
["1","03","05","02","02","  ","BPM - RF (10) Summary                                       ",{"$nulls":10},26.88,{"$nulls":20},1]
["1","03","05","02","03","  ","BPM - FFTB (12) Summary                                     ",{"$nulls":10},227796.56,{"$nulls":20},1]
["1","03","05","02","04","  ","BPM - Large Aperture (2) Summary                            ",{"$nulls":10},258883.5,{"$nulls":20},1]
["1","03","05","03","  ","  ","Toroid Beam Current Monitor (10) Summary                    ",{"$nulls":10},229121.35,{"$nulls":20},1]
["1","03","05","04","  ","  ","Beam Stoppers (4) Summary                                   ",{"$nulls":10},155250.33,{"$nulls":20},1]
["1","03","05","05","  ","  ","Profile Monitors (7 OTR-3 PHOSPHOR SCREEN-1 YAG)            ",{"$nulls":10},1341225.12,{"$nulls":20},1]
["1","03","05","06","  ","  ","E/O Bunch Length Monitors (1) Summary                       ",{"$nulls":10},22483.25,{"$nulls":20},1]
["1","03","05","07","  ","  ","CSR/OTR/CTR Bunch Length Monitors (5) Summary               ",{"$nulls":10},754644.16,{"$nulls":20},1]
["1","03","05","08","  ","  ","Beam Loss Monitors                                          ",{"$nulls":4},0,null,0,null,0,null,28843.66,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","03","05","08","01","  ","PIC Beam Loss Monitors (10) Summary                         ",{"$nulls":10},28843.66,{"$nulls":20},1]
["1","03","05","08","02","  ","PLIC Beam Loss Monitors (2) Summary                         ",{"$nulls":10},0,{"$nulls":20},1]
["1","03","05","09","  ","  ","Single Beam Dump (1) Summary                                ",{"$nulls":10},134017.71,{"$nulls":20},1]
["1","03","05","10","  ","  ","Electron Beam Dump (1) Summary                              ",{"$nulls":10},140691.87,{"$nulls":20},1]
["1","03","05","11","  ","  ","Protection Collimators (5) Summary                          ",{"$nulls":10},326170.9,{"$nulls":20},1]
["1","03","05","12","  ","  ","Movable Collimators (7x,3y) Summary                         ",{"$nulls":10},653109.6,{"$nulls":20},1]
["1","03","05","13","  ","  ","Safety Electron Dump (1) Summary                            ",{"$nulls":10},91652.1,{"$nulls":20},1]
["1","03","05","14","  ","  ","Charge Monitor (Entrance/Exit Assembly)                     ",{"$nulls":10},0,{"$nulls":20},1]
["1","03","06","  ","  ","  ","Linac RF Subsystem                                          ",{"$nulls":4},0,null,0,null,203933.55,null,2256051.46,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","03","06","02","  ","  ","S-Band High Power System                                    ",{"$nulls":10},1086051.89,{"$nulls":20},1]
["1","03","06","03","  ","  ","S-Band Structures                                           ",{"$nulls":10},47685.07,{"$nulls":20},1]
["1","03","06","04","  ","  ","X-Band Low Level System                                     ",{"$nulls":8},203933.55,{"$nulls":22},1]
["1","03","06","05","  ","  ","X-Band High Power System                                    ",{"$nulls":4},0,null,0,null,0,null,901582.59,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","03","06","05","01","  ","X-Band HP Klystron                                          ",{"$nulls":10},397736.77,{"$nulls":20},1]
["1","03","06","05","02","  ","X-Band HP Modulator                                         ",{"$nulls":10},221501.93,{"$nulls":20},1]
["1","03","06","05","03","  ","X-Band HP Waveguide System                                  ",{"$nulls":10},282343.89,{"$nulls":20},1]
["1","03","06","06","  ","  ","X-Band Structures                                           ",{"$nulls":10},164287.99,{"$nulls":20},1]
["1","03","06","07","  ","  ","RF Distribution System                                      ",{"$nulls":4},0,null,0,null,0,null,56443.92,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","03","06","07","01","  ","Modulator Refurbishment                                     ",{"$nulls":10},23218.24,{"$nulls":20},1]
["1","03","06","07","02","  ","Solid State Sub Booster                                     ",{"$nulls":10},1241.18,{"$nulls":20},1]
["1","03","06","07","03","  ","IPA Modifications                                           ",{"$nulls":10},0,{"$nulls":20},1]
["1","03","06","07","04","  ","Klystron Controls Interfaces                                ",{"$nulls":10},0,{"$nulls":20},1]
["1","03","06","07","05","  ","Bunch Length Electronics                                    ",{"$nulls":10},0,{"$nulls":20},1]
["1","03","06","07","06","  ","RF Phase Measurements                                       ",{"$nulls":10},41.36,{"$nulls":20},1]
["1","03","06","07","07","  ","RF Distribution L2 & L3                                     ",{"$nulls":10},31943.14,{"$nulls":20},1]
["1","03","06","07","08","  ","RF Fiber Optics Electronics System                          ",{"$nulls":10},0,{"$nulls":20},1]
["1","03","06","07","09","  ","RF Stability                                                ",{"$nulls":10},0,{"$nulls":20},1]
["1","03","07","  ","  ","  ","Linac Installation & Alignment                              ",{"$nulls":4},0,null,0,null,0,null,8013670.599999999,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","03","07","01","  ","  ","Linac L01 System Installation & Alignment                   ",{"$nulls":10},571735.24,{"$nulls":20},1]
["1","03","07","02","  ","  ","Linac BC1 System Installation & Alignment                   ",{"$nulls":10},22575.72,{"$nulls":20},1]
["1","03","07","05","  ","  ","Linac L03 System Installation & Alignment                   ",{"$nulls":10},62.88,{"$nulls":20},1]
["1","03","07","06","  ","  ","Linac LTU System Installation & Alignment                   ",{"$nulls":10},2690374.78,{"$nulls":20},1]
["1","03","07","07","  ","  ","Linac E-Dump System Installation & Alignment                ",{"$nulls":10},1027320.58,{"$nulls":20},1]
["1","03","07","10","  ","  ","LINAC  Installation 2006 Shut Down                          ",{"$nulls":4},0,null,0,null,0,null,1057780.97,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","03","07","10","01","  ","Beamline Equip Removal L01 thru BC1 Out                     ",{"$nulls":10},34223.17,{"$nulls":20},1]
["1","03","07","10","02","  ","Gallery Waveguide Installation                              ",{"$nulls":10},34312.06,{"$nulls":20},1]
["1","03","07","10","03","  ","Beamline Equip Installation L01 thru BC1 Out                ",{"$nulls":10},897967.56,{"$nulls":20},1]
["1","03","07","10","04","  ","2006 Linac Controls Install and Checkout Gallery            ",{"$nulls":10},91278.18,{"$nulls":20},1]
["1","03","07","10","05","  ","2006 Linac Controls Install and Checkout L01 to             ",{"$nulls":10},0,{"$nulls":20},1]
["1","03","07","20","  ","  ","LINAC Installation 2007 Shut Down                           ",{"$nulls":4},0,null,0,null,0,null,2643820.43,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","03","07","20","01","  ","Beamline Equip Removal L02, L03 and BC2                     ",{"$nulls":10},475794.52,{"$nulls":20},1]
["1","03","07","20","02","  ","Beamline Equip Installation L02, L03 and BC2                ",{"$nulls":10},980416.69,{"$nulls":20},1]
["1","03","07","20","03","  ","2007 Linac Controlls Install and Checkout                   ",{"$nulls":10},983298.77,{"$nulls":20},1]
["1","03","07","20","04","  ","Linac Undulator Interface                                   ",{"$nulls":10},204310.45,{"$nulls":20},1]
["1","04","  ","  ","  ","  ","UNDULATOR SYSTEM                                            ",{"$nulls":4},0,null,0,null,3678257.69,null,17134467.27,null,28098717.17,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","04","01","  ","  ","  ","Undulator System Management & Integration                   ",{"$nulls":4},0,null,0,null,0,null,5800722.01,null,3804719.09,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","04","01","01","  ","  ","Undulator System Management                                 ",{"$nulls":4},0,null,0,null,0,null,5800722.01,null,2839193.01,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","04","01","01","01","  ","Undulator System Management - Technical                     ",{"$nulls":10},5800722.01,{"$nulls":20},1]
["1","04","01","01","02","  ","ANL Project Support                                         ",{"$nulls":12},2839193.01,{"$nulls":18},1]
["1","04","01","02","  ","  ","Undulator System Materials & Supplies                       ",{"$nulls":4},0,null,0,null,0,null,0,null,961804.14,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","04","01","02","01","  ","Undulator System M&S - General                              ",{"$nulls":12},493982.87,{"$nulls":18},1]
["1","04","01","02","02","  ","Undulator System Travel                                     ",{"$nulls":12},467821.27,{"$nulls":18},1]
["1","04","01","03","  ","  ","Undulator System Reviews and Workshops                      ",{"$nulls":12},3721.94,{"$nulls":18},1]
["1","04","02","  ","  ","  ","Controls                                                    ",{"$nulls":4},0,null,0,null,3678257.69,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","04","02","01","  ","  ","Controls Management and Integration                         ",{"$nulls":4},0,null,0,null,100583.91,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","04","02","01","03","  ","Software Interface with SLAC                                ",{"$nulls":8},40121.66,{"$nulls":22},1]
["1","04","02","01","04","  ","Undulator Cable, Tray, and Rack Layout                      ",{"$nulls":8},36966.29,{"$nulls":22},1]
["1","04","02","01","05","  ","Miscellaneous Controls                                      ",{"$nulls":8},23495.96,{"$nulls":22},1]
["1","04","02","02","  ","  ","Motion                                                      ",{"$nulls":4},0,null,0,null,398096.36,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","04","02","02","01","  ","Undulator Cam Movers                                        ",{"$nulls":8},279889.73,{"$nulls":22},1]
["1","04","02","02","01","01","Motor Interface                                             "]
["1","04","02","02","01","02","Encoder Interface                                           "]
["1","04","02","02","01","03","Motor Driver                                                "]
["1","04","02","02","01","04","Cabling                                                     "]
["1","04","02","02","01","05","Integrate components                                        "]
["1","04","02","02","02","  ","Motion Test Stand                                           ",{"$nulls":8},80443.59,{"$nulls":22},1]
["1","04","02","02","06","  ","Scanning Wire Motion                                        ",{"$nulls":8},773.74,{"$nulls":22},1]
["1","04","02","02","06","01","Motor Interface                                             "]
["1","04","02","02","06","02","Encoder Interface                                           "]
["1","04","02","02","06","03","Motor Driver                                                "]
["1","04","02","02","06","04","Cabling                                                     "]
["1","04","02","02","06","05","Integrate components                                        "]
["1","04","02","02","07","  ","Translation Stage Motion                                    ",{"$nulls":8},36989.3,{"$nulls":22},1]
["1","04","02","02","07","01","Motor Interface                                             "]
["1","04","02","02","07","03","Motor Driver                                                "]
["1","04","02","02","07","04","Cabling                                                     "]
["1","04","02","02","07","05","Integrate components                                        "]
["1","04","02","03","  ","  ","Signal Analysis                                             ",{"$nulls":4},0,null,0,null,55444.74,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","04","02","03","01","  ","RFBPM                                                       ",{"$nulls":8},53369.64,{"$nulls":22},1]
["1","04","02","03","01","02","Signal Acquisition                                          "]
["1","04","02","03","01","03","Timing interface                                            "]
["1","04","02","03","01","04","Cabling                                                     "]
["1","04","02","03","01","05","Integrate components                                        "]
["1","04","02","03","02","  ","Charge Monitor                                              ",{"$nulls":8},0,{"$nulls":22},1]
["1","04","02","03","02","03","Integrate components                                        "]
["1","04","02","03","03","  ","Beam Finder Wire                                            ",{"$nulls":8},2075.1,{"$nulls":22},1]
["1","04","02","03","03","01","BFW Actuator Control                                        "]
["1","04","02","03","03","06","Integrate components                                        "]
["1","04","02","04","  ","  ","Video                                                       ",{"$nulls":4},0,null,0,null,28545.71,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","04","02","04","01","  ","OTR Monitor                                                 ",{"$nulls":8},19391.55,{"$nulls":22},1]
["1","04","02","04","01","01","Camera                                                      "]
["1","04","02","04","01","02","Camera trigger interface                                    "]
["1","04","02","04","01","03","Digitizer                                                   "]
["1","04","02","04","01","04","Timing interface                                            "]
["1","04","02","04","01","05","Cabling                                                     "]
["1","04","02","04","01","06","Integrate components                                        "]
["1","04","02","04","03","  ","Observation station video                                   ",{"$nulls":8},9154.16,{"$nulls":22},1]
["1","04","02","04","03","01","Camera                                                      "]
["1","04","02","04","03","02","Camera trigger interface                                    "]
["1","04","02","04","03","03","Multiplexor                                                 "]
["1","04","02","04","03","04","Cabling                                                     "]
["1","04","02","04","03","05","Integrate components                                        "]
["1","04","02","04","03","06","Imaging Test Stand                                          "]
["1","04","02","05","  ","  ","Data Acquisition and Control                                ",{"$nulls":4},0,null,0,null,19897.35,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","04","02","05","01","  ","Strongback Temperature monitoring                           ",{"$nulls":8},19897.35,{"$nulls":22},1]
["1","04","02","05","01","01","Integrate components                                        "]
["1","04","02","06","  ","  ","Vacuum                                                      ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","04","02","06","01","  ","Ion Pump Controller                                         ",{"$nulls":8},0,{"$nulls":22},1]
["1","04","02","06","01","01","Integrate components                                        "]
["1","04","02","06","02","  ","RGA                                                         ",{"$nulls":8},0,{"$nulls":22},1]
["1","04","02","06","02","01"," Integrate components                                       "]
["1","04","02","07","  ","  ","Machine Protection                                          ",{"$nulls":4},0,null,0,null,2995.99,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","04","02","07","01","  ","Undulator Beam Loss  Monitor Controls                       ",{"$nulls":8},2995.99,{"$nulls":22},1]
["1","04","02","07","01","01","Hardware design                                             "]
["1","04","02","07","01","02","Interface components                                        "]
["1","04","02","07","02","  ","Cerenkov Detector                                           ",{"$nulls":8},0,{"$nulls":22},1]
["1","04","02","07","02","01","Signal interface                                            "]
["1","04","02","07","03","  ","Gamma Ray Detector                                          "]
["1","04","02","07","03","01","Signal interface                                            "]
["1","04","02","08","  ","  ","Undulator Magnet Power Supplies                             ",{"$nulls":8},346412.75,{"$nulls":22},1]
["1","04","02","08","01","  ","Software                                                    "]
["1","04","02","08","02","  ","Beamline Power Supplies (Trim Type)                         "]
["1","04","02","08","02","01","CPUs and Crates                                             "]
["1","04","02","08","02","02","Bulk Power Supplies                                         "]
["1","04","02","08","02","03","PLC Power Supply Protection System                          "]
["1","04","02","08","02","04","MCOR                                                        "]
["1","04","02","08","03","  ","Rack Assembly                                               "]
["1","04","02","08","04","  ","System Checkout                                             "]
["1","04","02","10","  ","  ","Undulator Control Module                                    ",{"$nulls":8},1166820.41,{"$nulls":22},1]
["1","04","02","10","01","  ","UCM Hardware Design                                         "]
["1","04","02","10","02","  ","UCM EPICS Development                                       "]
["1","04","02","10","03","  ","Procure UCMI Prototype                                      "]
["1","04","02","10","04","  ","UCMI Proto H/W Assembly                                     "]
["1","04","02","10","05","  ","UCMI Prototype Testing                                      "]
["1","04","02","10","06","  ","UCMI Blade IOC First Article                                "]
["1","04","02","10","07","  ","Procure UCMI First Article                                  "]
["1","04","02","10","08","  ","UCM First Article Testing and QA                            "]
["1","04","02","10","09","  ","Procure Production UCMI                                     "]
["1","04","02","10","10","  ","Procure Production Blade IOC                                "]
["1","04","02","10","11","  ","Procure Production Motors                                   "]
["1","04","02","10","12","  ","Procure Production Potentionmeters                          "]
["1","04","02","10","13","  ","Procure Production RTD                                      "]
["1","04","02","10","14","  ","UCM Interlock & Power Supply                                "]
["1","04","02","12","  ","  ","Rack and Cable                                              ",{"$nulls":8},590210.77,{"$nulls":22},1]
["1","04","02","12","01","  ","Undulator Racks                                             "]
["1","04","02","12","02","  ","Intra-Undulator Cabling                                     "]
["1","04","02","12","03","  ","Electronics Interface Assembly                              "]
["1","04","02","12","04","  ","Undulator Cableplant                                        "]
["1","04","02","13","  ","  ","BPM                                                         ",{"$nulls":8},10842.98,{"$nulls":22},1]
["1","04","02","13","01","  ","APS Testing                                                 "]
["1","04","02","14","  ","  ","Long Term Test Prep                                         ",{"$nulls":8},22230.66,{"$nulls":22},1]
["1","04","02","15","  ","  ","Undulator Controls - BLM                                    ",{"$nulls":8},9626.17,{"$nulls":22},1]
["1","04","02","17","  ","  ","Undulator Conrols - Management                              ",{"$nulls":8},99962.42,{"$nulls":22},1]
["1","04","02","20","  ","  ","Undulator MPS                                               ",{"$nulls":8},217550.44,{"$nulls":22},1]
["1","04","02","20","02","  ","Undulator MPS - IMUX                                        "]
["1","04","02","20","03","  ","Undulator MPS - TIU                                         "]
["1","04","02","20","04","  ","Undulator MPS - PLIC                                        "]
["1","04","02","20","05","  ","Undulator MPS - Toroids                                     "]
["1","04","02","20","06","  ","Undulator MPS - Fault Devices                               "]
["1","04","02","21","  ","  ","Undulator Controls - Timing                                 ",{"$nulls":8},156333.81,{"$nulls":22},1]
["1","04","02","22","  ","  ","Undulator Controls - BPM                                    ",{"$nulls":8},221927.42,{"$nulls":22},1]
["1","04","02","23","  ","  ","Undulator Controls - Vacuum                                 ",{"$nulls":8},224092.92,{"$nulls":22},1]
["1","04","02","24","  ","  ","Undulator Controls - ADS System                             ",{"$nulls":8},6682.88,{"$nulls":22},1]
["1","04","03","  ","  ","  ","Undulator Magnet & Support                                  ",{"$nulls":4},0,null,0,null,0,null,9366316.9,null,15533439.45,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","04","03","01","  ","  ","UND Magnet & Support - Mgmt and Integration                 ",{"$nulls":12},3734.18,{"$nulls":18},1]
["1","04","03","02","  ","  ","First Prototype Undulator & Mfg Plan                        ",{"$nulls":12},-0.02,{"$nulls":18},1]
["1","04","03","03","  ","  ","1st Article Undulators & Long Lead Procurements             ",{"$nulls":4},0,null,0,null,0,null,0,null,9460131.75,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","04","03","03","01","  ","Ti Strongback (LLP)                                         ",{"$nulls":12},3500860.76,{"$nulls":18},1]
["1","04","03","03","02","  ","Magnet Blocks (LLP)                                         ",{"$nulls":12},1003209.42,{"$nulls":18},1]
["1","04","03","03","03","  ","Magnet Poles (LLP)                                          ",{"$nulls":12},802010.25,{"$nulls":18},1]
["1","04","03","03","04","  ","Magnet Assembly & Supports - 1st Articles                   ",{"$nulls":12},3011338.33,{"$nulls":18},1]
["1","04","03","03","04","01","Magnet Assembly 1st Article - Vendor A                      "]
["1","04","03","03","04","02","Magnet Assembly 1st Article - Vendor B                      "]
["1","04","03","03","04","03","Support/Mover System - Articles 1 & 2                       "]
["1","04","03","03","05","  ","Magnetic Measurement (ANL)                                  ",{"$nulls":12},255501.16,{"$nulls":18},1]
["1","04","03","03","05","01","Magnetic Measurement (ANL) - Vendor A Und #1                "]
["1","04","03","03","05","02","Magnetic Measurement (ANL) - Vendor B Und #2                "]
["1","04","03","03","06","  ","Integrated Single-Undulator Module Test                     ",{"$nulls":12},887211.83,{"$nulls":18},1]
["1","04","03","03","07","  "," System Test - Two Undulators                               "]
["1","04","03","04","  ","  ","Production Undulator Magnet Assembly & Supports             ",{"$nulls":4},0,null,0,null,0,null,0,null,4205823.3,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","04","03","04","01","  ","Production Undulator Assembly - Vendor A                    ",{"$nulls":12},1094968.32,{"$nulls":18},1]
["1","04","03","04","02","  ","Production Undulator Assembly - Vendor B                    ",{"$nulls":12},456972.64,{"$nulls":18},1]
["1","04","03","04","03","  ","Production Support/Mover Fabrication/Assembly               ",{"$nulls":12},2524252.69,{"$nulls":18},1]
["1","04","03","04","04","  ","Mu Metal Shield                                             ",{"$nulls":12},129629.65,{"$nulls":18},1]
["1","04","03","05","  ","  ","Quadrupole Focusing Magnets                                 ",{"$nulls":4},0,null,0,null,0,null,0,null,877692.07,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","04","03","05","01","  ","Quadrupole Magnets                                          ",{"$nulls":12},792373.39,{"$nulls":18},1]
["1","04","03","05","02","  ","Quadrupole Power Supplies                                   ",{"$nulls":12},0,{"$nulls":18},1]
["1","04","03","05","03","  ","Quadrupole Stages & Stands                                  ",{"$nulls":12},85318.68,{"$nulls":18},1]
["1","04","03","05","04","  ","Quadrupole Cables                                           ",{"$nulls":12},0,{"$nulls":18},1]
["1","04","03","06","  ","  ","Undulator Magnetic Measurement Facility (SLAC)              ",{"$nulls":4},0,null,0,null,0,null,9366316.9,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","04","03","06","01","  ","Undulator MMF Setup                                         ",{"$nulls":10},3807248.96,{"$nulls":20},1]
["1","04","03","06","01","01","Undulator Test Stand Prototype                              "]
["1","04","03","06","01","04","Undulator Test Stand                                        "]
["1","04","03","06","01","05","Undulator Fiducialization                                   "]
["1","04","03","06","01","06","Quad Strength and Field Quality                             "]
["1","04","03","06","01","07","Quad Fiducialization System                                 "]
["1","04","03","06","01","08","Hall Probe Calibration System                               "]
["1","04","03","06","01","09","Undulator Handling                                          "]
["1","04","03","06","02","  ","Fiducialization and Magnetic Measurements (F/MM)            ",{"$nulls":10},3111504.29,{"$nulls":20},1]
["1","04","03","06","02","01","F/MM Undulator Magnet Sections                              "]
["1","04","03","06","02","02","F/MM Quadrupoles                                            "]
["1","04","03","06","02","03","F/MM BPMs                                                   "]
["1","04","03","06","02","04","F/MM Correctors                                             "]
["1","04","03","06","02","05","F/MM Vacuum Chamber                                         "]
["1","04","03","06","02","06","F/MM Photon Diagnostics Components                          "]
["1","04","03","06","03","  ","Undulator Monitoring                                        ",{"$nulls":10},2447563.65,{"$nulls":20},1]
["1","04","03","06","03","01","Stretched Wire System                                       "]
["1","04","03","06","03","02","Hydrostatic Level System                                    "]
["1","04","03","06","03","03","F/MM BPMs                                                   "]
["1","04","03","06","03","04","0                                                           "]
["1","04","03","08","  ","  ","Fixed Supports                                              ",{"$nulls":4},0,null,0,null,0,null,0,null,986058.17,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","04","03","08","01","  ","Fixed Sppt Mgmt & Integration                               ",{"$nulls":12},102720,{"$nulls":18},1]
["1","04","03","08","02","  ","Fixed Support Design                                        ",{"$nulls":12},841836.93,{"$nulls":18},1]
["1","04","03","08","03","  ","Stabilized Girder Assemblies                                ",{"$nulls":12},0,{"$nulls":18},1]
["1","04","03","08","04","  ","Thermal Intercept System                                    "]
["1","04","03","08","05","  ","Thermometry                                                 ",{"$nulls":12},17320.54,{"$nulls":18},1]
["1","04","03","08","06","  ","Kinematic Girder Support                                    "]
["1","04","03","08","07","  ","Earthquake Bracing                                          ",{"$nulls":12},24180.7,{"$nulls":18},1]
["1","04","03","08","08","  ","Controls and Software                                       ",{"$nulls":12},0,{"$nulls":18},1]
["1","04","04","  ","  ","  ","Vacuum System                                               ",{"$nulls":4},0,null,0,null,0,null,0,null,3366345.05,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","04","04","02","  ","  ","Undulator Vacuum Chamber Assembly                           ",{"$nulls":4},0,null,0,null,0,null,0,null,2493645.78,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","04","04","02","01","  ","Prototype Chamber Weldment                                  ",{"$nulls":12},42747.81,{"$nulls":18},1]
["1","04","04","02","02","  ","Production Chamber Weldment                                 ",{"$nulls":12},1246503.27,{"$nulls":18},1]
["1","04","04","02","03","  ","Prototype Aluminum Chamber                                  ",{"$nulls":12},1204394.7,{"$nulls":18},1]
["1","04","04","03","  ","  ","Beam-line Bellows Module Assembly                           ",{"$nulls":4},0,null,0,null,0,null,0,null,289074.36,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","04","04","03","01","  ","Prototype Bellows Module                                    ",{"$nulls":12},161430.85,{"$nulls":18},1]
["1","04","04","03","02","  ","Production Bellows Module                                   ",{"$nulls":12},127643.51,{"$nulls":18},1]
["1","04","04","04","  ","  ","Single Undulator Test (SUT) Vacuum                          ",{"$nulls":12},110405.73,{"$nulls":18},1]
["1","04","04","05","  ","  ","Short Diagnostic Break (SDB) Assembly                       ",{"$nulls":12},150251.28,{"$nulls":18},1]
["1","04","04","06","  ","  ","Long Diagnostic Break (LDB) Assembly                        ",{"$nulls":12},216861.2,{"$nulls":18},1]
["1","04","04","07","  ","  ","Entrance Section Assembly                                   ",{"$nulls":12},3563.47,{"$nulls":18},1]
["1","04","04","08","  ","  ","Exit Section Assembly                                       ",{"$nulls":12},2482.67,{"$nulls":18},1]
["1","04","04","09","  ","  ","Baking System                                               ",{"$nulls":12},100060.56,{"$nulls":18},1]
["1","04","05","  ","  ","  ","Diagnostics                                                 ",{"$nulls":4},0,null,0,null,0,null,0,null,5336336.85,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","04","05","02","  ","  ","Undulator Line Diagnostics (ULD)                            ",{"$nulls":4},0,null,0,null,0,null,0,null,435191.28,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","04","05","02","01","  ","ULD Test Station                                            ",{"$nulls":12},119863.37,{"$nulls":18},1]
["1","04","05","02","02","  ","ULD Vacuum Chamber                                          ",{"$nulls":12},1093.92,{"$nulls":18},1]
["1","04","05","02","03","  ","Positioning Mechanism                                       ",{"$nulls":12},78527.63,{"$nulls":18},1]
["1","04","05","02","04","  ","Scanning wire assembly (ULD-SWA)                            ",{"$nulls":12},119928.41,{"$nulls":18},1]
["1","04","05","02","05","  ","Optical transition radiation imaging assembly               ",{"$nulls":12},115777.95,{"$nulls":18},1]
["1","04","05","02","09","  ","ULD Design & Integration                                    ",{"$nulls":12},0,{"$nulls":18},1]
["1","04","05","04","  ","  ","End-of-Undulator(EOU) X-ray and Profile diagnost            ",{"$nulls":4},0,null,0,null,0,null,0,null,68185.81,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","04","05","04","01","  ","Prototype Construction and Testing                          ",{"$nulls":12},68185.81,{"$nulls":18},1]
["1","04","05","04","02","  ","Bunch Length Monitor-Streak Camera (BLM)                    "]
["1","04","05","04","03","  ","Upstream corrector / separator                              ",{"$nulls":12},0,{"$nulls":18},1]
["1","04","05","04","04","  ","Optical Diffraction radiation imaging assembly (            ",{"$nulls":12},0,{"$nulls":18},1]
["1","04","05","04","05","  ","X-ray High Resolution monochromator assembly (EO            ",{"$nulls":12},0,{"$nulls":18},1]
["1","04","05","04","06","  ","X-ray Imaging High Resolution detector assembly             ",{"$nulls":12},0,{"$nulls":18},1]
["1","04","05","04","07","  ","EOU Design and Integration                                  ",{"$nulls":12},0,{"$nulls":18},1]
["1","04","05","05","  ","  ","RFBPM                                                       ",{"$nulls":4},0,null,0,null,0,null,0,null,3344929.36,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","04","05","05","01","  ","X-Band Cavity BPM Development                               ",{"$nulls":12},1178840.69,{"$nulls":18},1]
["1","04","05","05","02","  ","X-Band Receiver Development                                 ",{"$nulls":12},411221.78,{"$nulls":18},1]
["1","04","05","05","03","  ","X-Band BPM Production                                       ",{"$nulls":12},1754866.89,{"$nulls":18},1]
["1","04","05","06","  ","  ","Beam Finder Wire                                            ",{"$nulls":12},974152.53,{"$nulls":18},1]
["1","04","05","07","  ","  ","Charge Monitor (CM)                                         ",{"$nulls":12},0,{"$nulls":18},1]
["1","04","05","08","  ","  ","Beam Loss Monitoring                                        ",{"$nulls":12},436715.49,{"$nulls":18},1]
["1","04","05","09","  ","  ","Radiation Detection Monitor (RDM)                           ",{"$nulls":12},0,{"$nulls":18},1]
["1","04","05","10","  ","  ","SIngle Undulator Test (SUT) Diagnostics                     ",{"$nulls":12},77162.38,{"$nulls":18},1]
["1","04","05","11","  ","  ","Supplemental Shielding                                      ",{"$nulls":12},0,{"$nulls":18},1]
["1","04","06","  ","  ","  ","Undulator System Installation and Alignment                 ",{"$nulls":4},0,null,0,null,0,null,1967428.36,null,57876.73,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","04","06","02","  ","  ","Control System Installation and Alignment                   ",{"$nulls":10},8421.82,{"$nulls":20},1]
["1","04","06","04","  ","  ","Vacuum System Installation and Alignment                    ",{"$nulls":12},57876.73,{"$nulls":18},1]
["1","04","06","05","  ","  ","Diagnostics System Installation and Alignment               ",{"$nulls":10},0,{"$nulls":20},1]
["1","04","06","06","  ","  ","2008 Undulator System Installation                          ",{"$nulls":10},1959006.54,{"$nulls":20},1]
["1","05","  ","  ","  ","  ","X-RAY TRANSPORT & DIAGNOSTICS SYSTEMS                       ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,27590034.520000007,null,279588.26,null,3983678.43,null,0,null,0,null,0,null,0,null,0]
["1","05","01","  ","  ","  ","System Management & Integration                             ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,5855726.800000001,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","05","01","01","  ","  ","Management                                                  ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,5855726.800000001,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","05","01","01","01","  ","XTOD Management - Technical                                 ",{"$nulls":16},3673947.63,{"$nulls":14},1]
["1","05","01","01","02","  ","LLNL Project Support                                        ",{"$nulls":16},2112589.44,{"$nulls":14},1]
["1","05","01","01","03","  ","Commissioning Coordinator                                   ",{"$nulls":16},69189.73,{"$nulls":14},1]
["1","05","02","  ","  ","  ","Controls                                                    ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,279588.26,null,3983678.43,null,0,null,0,null,0,null,0,null,0]
["1","05","02","01","  ","  ","Controls                                                    ",{"$nulls":20},3983678.43,{"$nulls":10},1]
["1","05","02","01","01","  ","XTOD Global Controls                                        "]
["1","05","02","01","02","  ","FEE/EBD Controls                                            "]
["1","05","02","01","02","01","FEE/EBD Racks                                               "]
["1","05","02","01","02","02","FEE/EBD Vacuum Controls                                     "]
["1","05","02","01","02","03","EBD Fast Valve Controls                                     "]
["1","05","02","01","02","04","FEE Fixed Mask/Slit Controls                                "]
["1","05","02","01","02","05","FEE Attenuator Controls                                     "]
["1","05","02","01","02","06","FEE Gas Detector Controls                                   "]
["1","05","02","01","02","07","FEE Direct Imager Controls                                  "]
["1","05","02","01","02","08","FEE Total Energy Monitor Controls                           "]
["1","05","02","01","02","09","FEE K-Measurement Controls                                  "]
["1","05","02","01","02","10","FEE Soft X-Ray Imager Controls                              "]
["1","05","02","01","02","11","FEE SOMS Controls                                           "]
["1","05","02","01","02","12","FEE HOMS Controls                                           "]
["1","05","02","01","02","13","FEE Pop-Ins Controls                                        "]
["1","05","02","01","03","  ","NEH Controls                                                "]
["1","05","02","01","03","01","NEH Racks                                                   "]
["1","05","02","01","03","02","NEH Vacuum Controls                                         "]
["1","05","02","01","03","04","NEH Pop-Ins Controls                                        "]
["1","05","02","01","04","  ","TUN Controls                                                "]
["1","05","02","01","04","01","TUN Racks                                                   "]
["1","05","02","01","04","02","TUN Vacuum Controls                                         "]
["1","05","02","01","04","03","TUN Pop-Ins Controls                                        "]
["1","05","02","01","05","  ","FEH Controls                                                "]
["1","05","02","01","05","01","FEH Racks                                                   "]
["1","05","02","01","05","02","FEH Vacuum Controls                                         "]
["1","05","02","02","  ","  ","Motor Controls                                              ",{"$nulls":18},278106.55,{"$nulls":12},1]
["1","05","02","03","  ","  ","Controls - Vacuum                                           ",{"$nulls":18},1481.71,{"$nulls":12},1]
["1","05","03","  ","  ","  ","Mechanical & Vacuum Subsystem                               ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,3840845,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","05","03","01","  ","  ","Vacuum Systems Engineering                                  ",{"$nulls":16},934522.35,{"$nulls":14},1]
["1","05","03","02","  ","  ","Mech/Vac Front End                                          ",{"$nulls":16},1341492.58,{"$nulls":14},1]
["1","05","03","03","  ","  ","Mech/Vac Near Hall                                          ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,471680.21,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","05","03","03","01","  ","Mech/Vac Near Hall                                          ",{"$nulls":16},471680.21,{"$nulls":14},1]
["1","05","03","03","02","  ","NEH Hutch 2                                                 "]
["1","05","03","03","03","  ","NEH Hutch 3                                                 "]
["1","05","03","04","  ","  ","Mech/Vac Tunnel                                             ",{"$nulls":16},992991.61,{"$nulls":14},1]
["1","05","03","05","  ","  ","Mech/Vac Far Hall                                           ",{"$nulls":16},100158.25,{"$nulls":14},1]
["1","05","04","  ","  ","  ","Optical  Subsystem                                          ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,7914179.200000001,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","05","04","02","  ","  ","Facility Optics                                             ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,7914179.200000001,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","05","04","02","01","  ","Fast Valve                                                  ",{"$nulls":16},0,{"$nulls":14},1]
["1","05","04","02","02","  ","Fixed Mask                                                  ",{"$nulls":16},203485.63,{"$nulls":14},1]
["1","05","04","02","03","  ","Slit                                                        ",{"$nulls":16},505665.31,{"$nulls":14},1]
["1","05","04","02","05","  ","Gas/Solid Attenuator                                        ",{"$nulls":16},3242741.36,{"$nulls":14},1]
["1","05","04","02","06","  ","TTF Damage Experiment                                       ",{"$nulls":16},594425.19,{"$nulls":14},1]
["1","05","04","02","07","  ","FEL Offset Mirrors                                          ",{"$nulls":16},3359517.31,{"$nulls":14},1]
["1","05","04","02","07","01","SOMS Mirrors                                                "]
["1","05","04","02","07","02","HOMS Mirrors                                                "]
["1","05","04","02","08","  ","Solid Attenuator                                            ",{"$nulls":16},8344.4,{"$nulls":14},1]
["1","05","05","  ","  ","  ","Diagnostics Subsystem                                       ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,8162589.2700000005,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","05","05","02","  ","  ","Modeling & Simulation                                       ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,1211552.97,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","05","05","02","01","  ","Wave Model                                                  ",{"$nulls":16},524725.8,{"$nulls":14},1]
["1","05","05","02","02","  ","Monte Carlo Model                                           ",{"$nulls":16},293290.73,{"$nulls":14},1]
["1","05","05","02","03","  ","Beam Simulation                                             ",{"$nulls":16},393536.44,{"$nulls":14},1]
["1","05","05","03","  ","  ","Facility Diagnostics                                        ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,2911043.77,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","05","05","03","01","  ","Direct Imager                                               ",{"$nulls":16},1074055.08,{"$nulls":14},1]
["1","05","05","03","02","  ","Indirect Imager                                             ",{"$nulls":16},334947.08,{"$nulls":14},1]
["1","05","05","03","06","  ","Gas Detector                                                ",{"$nulls":16},1502041.61,{"$nulls":14},1]
["1","05","05","04","  ","  ","Commissioning Diagnostics                                   ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,4039992.53,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","05","05","04","02","  ","Total Energy Measurement                                    ",{"$nulls":16},2840424.17,{"$nulls":14},1]
["1","05","05","04","04","  ","Soft X-Ray Imager                                           ",{"$nulls":16},142833.21,{"$nulls":14},1]
["1","05","05","04","05","  ","Popup Cameras                                               ",{"$nulls":16},673185.37,{"$nulls":14},1]
["1","05","05","04","06","  ","K Measurement System                                        ",{"$nulls":16},383549.78,{"$nulls":14},1]
["1","05","06","  ","  ","  ","X-Ray Transport System Installation & Alignment             ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,1816694.25,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","05","06","01","  ","  ","FEE Install                                                 ",{"$nulls":16},0,{"$nulls":14},1]
["1","05","06","01","01","  ","FEE Cable Installation                                      ",{"$nulls":16},255337.62,{"$nulls":14},1]
["1","05","06","01","02","  ","FEE Install - All excluding cable install                   ",{"$nulls":16},1051843.15,{"$nulls":14},1]
["1","05","06","02","  ","  ","Near Hall Install                                           ",{"$nulls":16},166220.89,{"$nulls":14},1]
["1","05","06","03","  ","  ","Tunnel Install                                              ",{"$nulls":16},200488.43,{"$nulls":14},1]
["1","05","06","04","  ","  ","Far Hall Install                                            ",{"$nulls":16},127616.01,{"$nulls":14},1]
["1","05","06","05","  ","  ","Electron Dump Enclosure Install                             ",{"$nulls":16},15188.15,{"$nulls":14},1]
["1","06","  ","  ","  ","  ","X-RAY END STATION SYSTEMS                                   ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,8735820.7,null,0,null,981671.78,null,8133615.299999999,null,0,null,0,null,0]
["1","06","01","  ","  ","  ","System Management & Integration                             ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,1343107.51,null,0,null,0,null,0]
["1","06","01","01","  ","  ","Management                                                  ",{"$nulls":24},1048146.71,{"$nulls":6},1]
["1","06","01","02","  ","  ","SSRL Physics                                                ",{"$nulls":24},294960.8,{"$nulls":6},1]
["1","06","02","  ","  ","  ","XES Controls                                                ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,8735820.7,null,0,null,0,null,0,null,0,null,0,null,0]
["1","06","02","01","  ","  ","Controls Management                                         ",{"$nulls":18},574649.21,{"$nulls":12},1]
["1","06","02","02","  ","  ","Network - Closed (Moved to new WBS Element)                 ",{"$nulls":18},98.3,{"$nulls":12},1]
["1","06","02","03","  ","  ","PC Support - Closed (Moved to New WBS Element)              ",{"$nulls":18},6257.84,{"$nulls":12},1]
["1","06","02","04","  ","  ","Beamline Controls - AP - Closed  (Moved to new WBS Element) ",{"$nulls":18},127.14,{"$nulls":12},1]
["1","06","02","05","  ","  ","X-Ray PPS - Closed (Moved to new WBS Element)               ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,27118.06,null,0,null,0,null,0,null,0,null,0,null,0]
["1","06","02","05","01","  ","FEE X-Ray PPS - Closed (Moved to new WBS Element)           ",{"$nulls":18},27118.06,{"$nulls":12},1]
["1","06","02","05","02","  ","Near Hall X-Ray PPS - Closed to BCWP                        ",{"$nulls":18},0,{"$nulls":12},1]
["1","06","02","06","  ","  ","X-Ray MPS - Closed (Moved to new WBS Element)               ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,1337.96,null,0,null,0,null,0,null,0,null,0,null,0]
["1","06","02","06","01","  ","FEE X-Ray MPS - Closed to BCWP                              ",{"$nulls":18},1337.96,{"$nulls":12},1]
["1","06","02","07","  ","  ","AMOS Experiment Controls X1                                 ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,2434958.56,null,0,null,0,null,0,null,0,null,0,null,0]
["1","06","02","07","01","  ","AMOS Requirements, Design, Setup                            ",{"$nulls":18},291844.86,{"$nulls":12},1]
["1","06","02","07","07","  ","Development Hardware & Software                             ",{"$nulls":18},631174.84,{"$nulls":12},1]
["1","06","02","07","08","  ","Beam Viewing System for Phase 1                             ",{"$nulls":18},143791.52,{"$nulls":12},1]
["1","06","02","07","09","  ","Beam Viewing System for Phase 2                             ",{"$nulls":18},124056.02,{"$nulls":12},1]
["1","06","02","07","12","  ","Differential Pumping                                        ",{"$nulls":18},123226.69,{"$nulls":12},1]
["1","06","02","07","14","  ","Temperature Monitoring                                      ",{"$nulls":18},28989.11,{"$nulls":12},1]
["1","06","02","07","15","  ","Gas Storage & Delivery System                               ",{"$nulls":18},24640.89,{"$nulls":12},1]
["1","06","02","07","16","  ","High Field Physics Chamber                                  ",{"$nulls":18},751904.16,{"$nulls":12},1]
["1","06","02","07","16","01","Vacuum & Motion                                             "]
["1","06","02","07","16","02","Gas Jet System                                              "]
["1","06","02","07","16","03","Electron Spectrometers (5)                                  "]
["1","06","02","07","16","04","Ion Spectrometers (TOF)                                     "]
["1","06","02","07","16","05","Ion Spectrometers (Imaging/Momentum)                        "]
["1","06","02","07","16","07","X-Ray Emission Spectrometers                                "]
["1","06","02","07","17","  ","Diagnostics Chamber                                         ",{"$nulls":18},231153.53,{"$nulls":12},1]
["1","06","02","07","17","01","Vacuum & Motion                                             "]
["1","06","02","07","17","02","Gas Jet System                                              "]
["1","06","02","07","17","03","Mag Bottle Electr Spectr                                    "]
["1","06","02","07","17","04","X-Ray Emission Spectr.                                      "]
["1","06","02","07","18","  ","Total Power Measurement                                     ",{"$nulls":18},84176.94,{"$nulls":12},1]
["1","06","02","08","  ","  ","AMOS Particle Imaging Controls                              ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,146032.01,null,0,null,0,null,0,null,0,null,0,null,0]
["1","06","02","08","01","  ","AMOS Particle Imaging Controls                              ",{"$nulls":18},85044.02,{"$nulls":12},1]
["1","06","02","08","02","  ","AMOS Particle Imaging Software                              ",{"$nulls":18},60987.99,{"$nulls":12},1]
["1","06","02","09","  ","  ","Controls Management - Closed (Moved to new WBS Element)     ",{"$nulls":18},18.88,{"$nulls":12},1]
["1","06","02","10","  ","  ","Global Controls System                                      ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,5356174.83,null,0,null,0,null,0,null,0,null,0,null,0]
["1","06","02","10","01","  ","Network                                                     ",{"$nulls":18},1329241.69,{"$nulls":12},1]
["1","06","02","10","02","  ","Machine Protection System                                   ",{"$nulls":18},67617.41,{"$nulls":12},1]
["1","06","02","10","03","  ","Personnel Protection System                                 ",{"$nulls":18},545734.17,{"$nulls":12},1]
["1","06","02","10","04","  ","Laser Safety System (LSS)                                   ",{"$nulls":18},174100.91,{"$nulls":12},1]
["1","06","02","10","05","  ","User Safeguards                                             ",{"$nulls":18},126799.64,{"$nulls":12},1]
["1","06","02","10","06","  ","Timing System                                               ",{"$nulls":18},106889.78,{"$nulls":12},1]
["1","06","02","10","07","  ","Data Management                                             ",{"$nulls":18},801240.4,{"$nulls":12},1]
["1","06","02","10","07","01","Requirements, Design, Test Setup                            "]
["1","06","02","10","07","02","Data Storage                                                "]
["1","06","02","10","07","03","Data Movement                                               "]
["1","06","02","10","07","04","Data Reduction                                              "]
["1","06","02","10","07","06","Data Maintenance                                            "]
["1","06","02","10","08","  ","Global Cabling & Racks                                      ",{"$nulls":18},291047.33,{"$nulls":12},1]
["1","06","02","10","09","  ","Laser Timing                                                ",{"$nulls":18},930819.84,{"$nulls":12},1]
["1","06","02","10","11","  ","Common Hutch Controls                                       ",{"$nulls":18},366682.91,{"$nulls":12},1]
["1","06","02","10","11","01","Workstation                                                 "]
["1","06","02","10","11","02","Photon Beam Control                                         "]
["1","06","02","10","11","03","Beam Line Processor                                         "]
["1","06","02","10","11","04","Local Hutch Controls                                        "]
["1","06","02","10","11","07","Pumping Section                                             "]
["1","06","02","10","11","08","Focusing Optics                                             "]
["1","06","02","10","12","  ","Data Acquisition (DAQ)                                      ",{"$nulls":18},413398.53,{"$nulls":12},1]
["1","06","02","10","12","01","Requirements, Design, Test Setup                            "]
["1","06","02","10","12","02","DAQ Common                                                  "]
["1","06","02","10","12","03","CE                                                          "]
["1","06","02","10","12","04","CPCI                                                        "]
["1","06","02","10","12","05","2D Detector                                                 "]
["1","06","02","10","13","  ","Archives                                                    ",{"$nulls":18},84268.93,{"$nulls":12},1]
["1","06","02","10","13","01","Requirements, Design, Test Setup                            "]
["1","06","02","10","13","02","DAQ Archive                                                 "]
["1","06","02","10","13","03","120 Hz Archives                                             "]
["1","06","02","10","13","04","EPICS Archive                                               "]
["1","06","02","10","14","  ","Data Retrieval & Analysis                                   ",{"$nulls":18},118333.29,{"$nulls":12},1]
["1","06","02","10","14","01","Requirements, Design, Test Setup                            "]
["1","06","02","10","14","02","Data Retrieval                                              "]
["1","06","02","10","14","03","Data Analysis                                               "]
["1","06","02","11","  ","  ","Laser Controls                                              ",{"$nulls":18},189047.91,{"$nulls":12},1]
["1","06","03","  ","  ","  ","Mechanical/Vacuum Subsystem                                 ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","06","03","02","  ","  ","Vacuum Components - Mech/Vac                                ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["1","06","03","02","02","  ","Hardware - Vacuum                                           ",{"$nulls":24},0,{"$nulls":6},1]
["1","06","04","  ","  ","  "," XES Laser System                                           ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,981671.78,null,0,null,0,null,0,null,0]
["1","06","04","01","  ","  ","XES Laser                                                   ",{"$nulls":22},457431.82,{"$nulls":8},1]
["1","06","04","02","  ","  ","Laser Diagnostics                                           ",{"$nulls":22},102202.31,{"$nulls":8},1]
["1","06","04","03","  ","  ","Laser Optical Transport                                     ",{"$nulls":22},371605.5,{"$nulls":8},1]
["1","06","04","04","  ","  ","Laser Safety                                                ",{"$nulls":22},50432.15,{"$nulls":8},1]
["1","06","05","  ","  ","  ","X-Ray Detectors                                             ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,249109.04,null,0,null,0,null,0]
["1","06","05","01","  ","  ","Beam Imaging                                                ",{"$nulls":24},3590.4,{"$nulls":6},1]
["1","06","05","04","  ","  ","Detector & Streak Camera                                    ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,245518.64,null,0,null,0,null,0]
["1","06","05","04","01","  ","X-Ray Detector Management                                   ",{"$nulls":24},245518.64,{"$nulls":6},1]
["1","06","06","  ","  ","  ","System Installation & Alignment                             ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,1768100.93,null,0,null,0,null,0]
["1","06","06","01","  ","  ","Front End Install                                           ",{"$nulls":24},43755.01,{"$nulls":6},1]
["1","06","06","02","  ","  ","Near Hall Install                                           ",{"$nulls":24},0,{"$nulls":6},1]
["1","06","06","02","01","  ","Mischarges - Closed                                         ",{"$nulls":24},392.16,{"$nulls":6},1]
["1","06","06","02","02","  ","Network Fiber Installation                                  ",{"$nulls":24},328606.34,{"$nulls":6},1]
["1","06","06","02","03","  ","NEH Install Detectors                                       ",{"$nulls":24},0,{"$nulls":6},1]
["1","06","06","02","04","  ","NEH Install AMO Experiment                                  ",{"$nulls":24},279849.37,{"$nulls":6},1]
["1","06","06","02","05","  ","NEH Install Laser                                           ",{"$nulls":24},150323.66,{"$nulls":6},1]
["1","06","06","02","06","  ","NEH Install PPS                                             ",{"$nulls":24},237808.16,{"$nulls":6},1]
["1","06","06","02","07","  ","NEH Install Laser PPS                                       ",{"$nulls":24},0,{"$nulls":6},1]
["1","06","06","02","08","  ","NEH Install 2008                                            "]
["1","06","06","02","09","  ","NEH Install Timing                                          ",{"$nulls":24},139528.65,{"$nulls":6},1]
["1","06","06","02","99","  ","NEH Install - Other                                         ",{"$nulls":24},334043.34,{"$nulls":6},1]
["1","06","06","03","  ","  ","Tunnel Install                                              ",{"$nulls":24},42562.31,{"$nulls":6},1]
["1","06","06","04","  ","  ","Far Hall Install                                            ",{"$nulls":24},167290.53,{"$nulls":6},1]
["1","06","06","04","02","  ","Far Hall Install Mech/Vac                                   ",{"$nulls":24},0,{"$nulls":6},1]
["1","06","06","05","  ","  ","Electron Dump Enclosure Install                             ",{"$nulls":24},43941.4,{"$nulls":6},1]
["1","06","07","  ","  ","  ","AMOS Experiment                                             ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,3748647.96,null,0,null,0,null,0]
["1","06","07","01","  ","  ","AMO Exp - Management & Design                               ",{"$nulls":24},1089026.94,{"$nulls":6},1]
["1","06","07","01","01","  "," Management                                                 "]
["1","06","07","01","02","  ","Conceptual Design                                           "]
["1","06","07","01","03","  "," Preliminary Design                                         "]
["1","06","07","01","04","  "," Final Design                                               "]
["1","06","07","02","  ","  ","AMO Exp - High Field Physics                                ",{"$nulls":24},1632851.55,{"$nulls":6},1]
["1","06","07","02","01","  ","X-Ray Fluorescence Spectrometer                             "]
["1","06","07","02","02","  ","Ion Imaging & TOF Detectors                                 "]
["1","06","07","02","03","  ","Sample Source                                               "]
["1","06","07","02","04","  ","Vacuum System                                               "]
["1","06","07","02","05","  ","Differential Pumping                                        "]
["1","06","07","02","06","  ","Pulse Shutter                                               "]
["1","06","07","03","  ","  ","AMO Exp - Refocus Optics                                    ",{"$nulls":24},457481.09,{"$nulls":6},1]
["1","06","07","04","  ","  ","AMO Exp - Diagnostics                                       ",{"$nulls":24},569288.38,{"$nulls":6},1]
["1","06","08","  ","  ","  ","K Measurement Crystals                                      ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,26826.85,null,0,null,0,null,0]
["1","06","08","01","  ","  ","K Measurement Crystals                                      ",{"$nulls":24},26826.85,{"$nulls":6},1]
["1","06","09","  ","  ","  ","Mechanical Systems                                          ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,997823.01,null,0,null,0,null,0]
["1","06","09","01","  ","  ","PPS Stoppers                                                ",{"$nulls":24},656669.89,{"$nulls":6},1]
["1","06","09","01","01","  ","E Dump PPS Stoppers                                         "]
["1","06","09","01","02","  ","Photon PPS Stoppers                                         "]
["1","06","09","02","  ","  ","PPS Shielding                                               ",{"$nulls":24},220690.5,{"$nulls":6},1]
["1","06","09","03","  ","  "," NEH Hutch Doors                                            ",{"$nulls":24},120462.62,{"$nulls":6},1]
["1","09","  ","  ","  ","  ","CONVENTIONAL FACILITIES                                     ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,135008657.28000003]
["1","09","01","  ","  ","  ","System Management & Integration                             ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,27198103.349999998]
["1","09","01","01","  ","  ","Management                                                  ",{"$nulls":30},3831014.01,1]
["1","09","01","02","  ","  ","CAM/CF Engineering                                          ",{"$nulls":30},4902412.94,1]
["1","09","01","03","  ","  ","Construction Management & AE Support                        ",{"$nulls":30},17781748.21,1]
["1","09","01","04","  ","  ","Mechanical Design (MD)                                      ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,433043.91]
["1","09","01","04","01","  ","Mechanical Design Title 1 (Linac not included)              ",{"$nulls":30},77898.13,1]
["1","09","01","04","02","  ","Mechanical Design T1 Linac Facilities                       ",{"$nulls":30},28110.58,1]
["1","09","01","04","03","  ","Mechanical Design Title 2 (Linac not included)              ",{"$nulls":30},83103.87,1]
["1","09","01","04","04","  ","Mechanical Design T2 Linac Facilities                       ",{"$nulls":30},227078.11,1]
["1","09","01","04","05","  ","Mechanical Design Title 3 Linac Facility                    ",{"$nulls":30},16853.22,1]
["1","09","01","04","06","  ","Mechanical Design Title 3 (Linac not Included)              ",{"$nulls":30},0,1]
["1","09","01","05","  ","  ","Conventional Experiment Facility (CEF)                      ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,249884.28]
["1","09","01","05","01","  ","CEF Engineering Title 1(Linac Not Included)                 ",{"$nulls":30},42767.51,1]
["1","09","01","05","02","  ","CEF Engineering Title 1 Linac Facility                      ",{"$nulls":30},31493.64,1]
["1","09","01","05","03","  ","CEF Engineering Title 2 (Linac Not Included)                ",{"$nulls":30},119105.72,1]
["1","09","01","05","04","  ","CEF Design Linac Facility Title 2                           ",{"$nulls":30},56517.41,1]
["1","09","02","  ","  ","  ","Title 1 & Title 2 Conventional Facilities                   ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,5708064.24]
["1","09","02","02","  ","  ","A & E Services (S20, MMF, MMC not Incl)                     ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,5442926.73]
["1","09","02","02","01","  ","Title 1 Design                                              ",{"$nulls":30},293543.08,1]
["1","09","02","02","02","  ","Title 2 Design                                              ",{"$nulls":30},5149383.65,1]
["1","09","02","03","  ","  ","A & E Services - (S20, MMF,MCC)                             ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,265137.51]
["1","09","02","03","01","  ","Title 1 Design (Sector 20)                                  ",{"$nulls":30},0,1]
["1","09","02","03","02","  ","Title 2 Design (Sector 20)                                  ",{"$nulls":30},84298.35,1]
["1","09","02","03","03","  ","Title 1 Design (MMF)                                        ",{"$nulls":30},37895,1]
["1","09","02","03","04","  ","Title 2 Design (MMF)                                        ",{"$nulls":30},142944.16,1]
["1","09","02","03","05","  ","MMF - Metals                                                "]
["1","09","02","03","06","  ","MMF - Woods & Plastics                                      "]
["1","09","03","  ","  ","  ","Construction -T3 Conventional Facilities                    ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,102102489.69000003]
["1","09","03","01","  ","  ","Sector 20 Injector Facilities                               ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,3127362]
["1","09","03","01","01","  ","S20 - Site Preparation/General Requirements                 ",{"$nulls":30},581817.54,1]
["1","09","03","01","02","  ","S20 - Site Construction                                     ",{"$nulls":30},139895.85,1]
["1","09","03","01","03","  ","S20 - Concrete                                              ",{"$nulls":30},146007.37,1]
["1","09","03","01","04","  ","S20 - Masonry                                               ",{"$nulls":30},269.59,1]
["1","09","03","01","05","  ","S20 - Metals                                                ",{"$nulls":30},234436.1,1]
["1","09","03","01","06","  ","S20 - Woods & Plastics                                      ",{"$nulls":30},14512.53,1]
["1","09","03","01","07","  ","S20 - Thermal & Moisture Protection                         ",{"$nulls":30},133554.57,1]
["1","09","03","01","08","  ","S20 - Doors & Windows                                       ",{"$nulls":30},36436.19,1]
["1","09","03","01","09","  ","S20 - Finishes                                              ",{"$nulls":30},115363.92,1]
["1","09","03","01","10","  ","S20 - Specialties                                           ",{"$nulls":30},588.36,1]
["1","09","03","01","14","  ","S20 - Conveying Systems                                     ",{"$nulls":30},3612.77,1]
["1","09","03","01","15","  ","S20 - Mechanical                                            ",{"$nulls":30},872997.57,1]
["1","09","03","01","16","  ","S20 - Electrical                                            ",{"$nulls":30},568755.55,1]
["1","09","03","01","20","  ","S20 - Project Close Out                                     ",{"$nulls":30},279114.09,1]
["1","09","03","02","  ","  ","Magnetic Measurement Facility                               ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,3358032.72]
["1","09","03","02","01","  ","MMF - Site Preparation/General Requirements                 ",{"$nulls":30},442550.24,1]
["1","09","03","02","02","  ","MMF - Site Construction                                     ",{"$nulls":30},95594.65,1]
["1","09","03","02","03","  ","MMF - Concrete                                              ",{"$nulls":30},199016.29,1]
["1","09","03","02","04","  ","Utilities                                                   "]
["1","09","03","02","05","  ","MMF - Metals                                                ",{"$nulls":30},142754.22,1]
["1","09","03","02","06","  ","MMF - Woods & Plastics                                      ",{"$nulls":30},11811.37,1]
["1","09","03","02","07","  ","MMF - Thermal & Moisture Protection                         ",{"$nulls":30},70624.32,1]
["1","09","03","02","08","  ","MMF - Doors & Windows                                       ",{"$nulls":30},28955.83,1]
["1","09","03","02","09","  ","MMF - Finishes                                              ",{"$nulls":30},178005.57,1]
["1","09","03","02","10","  ","MMF - Specialities                                          ",{"$nulls":30},1044.5,1]
["1","09","03","02","13","  ","MMF - Special Construction                                  ",{"$nulls":30},306.09,1]
["1","09","03","02","14","  ","MMF - Conveying Systems                                     ",{"$nulls":30},241299.09,1]
["1","09","03","02","15","  ","MMF - Mechanical                                            ",{"$nulls":30},1025424.04,1]
["1","09","03","02","16","  ","MMF - Electrical                                            ",{"$nulls":30},804189.49,1]
["1","09","03","02","20","  ","MMF - Project Close Out                                     ",{"$nulls":30},116457.02,1]
["1","09","03","03","  ","  ","BTH West                                                    ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,687747.58]
["1","09","03","03","01","  ","BTH West - Site Preparation                                 ",{"$nulls":30},38202.14,1]
["1","09","03","03","15","  "," BTH West Mechanical                                        ",{"$nulls":30},404335.2,1]
["1","09","03","03","16","  "," BTH West - Electrical                                      ",{"$nulls":30},231440,1]
["1","09","03","03","20","  ","BTH West Project Close Out                                  ",{"$nulls":30},13770.24,1]
["1","09","03","04","  ","  ","Linac Facility Upgrade (LN)                                 ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,3087569.21]
["1","09","03","04","01","  ","LN - Site Preparation                                       "]
["1","09","03","04","02","  ","LN - Sitework                                               "]
["1","09","03","04","05","  ","LN - Metals                                                 ",{"$nulls":30},109914.85,1]
["1","09","03","04","15","  ","LN - Mechanical                                             ",{"$nulls":30},1235287.1,1]
["1","09","03","04","16","  ","LN - Electrical                                             ",{"$nulls":30},1739705.01,1]
["1","09","03","04","20","  ","LN - Project Close Out                                      ",{"$nulls":30},2662.25,1]
["1","09","03","05","  ","  ","Research Yard                                               ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,3647863.06]
["1","09","03","05","01","  ","RY - Site Preparation                                       ",{"$nulls":30},589980.76,1]
["1","09","03","05","02","  ","RY - Site Construction                                      ",{"$nulls":30},2756156.48,1]
["1","09","03","05","20","  ","RY - Project Close Out                                      ",{"$nulls":30},301725.82,1]
["1","09","03","06","  ","  ","Pre-Purchase Equipment for Beam Path                        ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,2083201.8]
["1","09","03","06","01","  ","PPE - General Requirements                                  ",{"$nulls":30},363475,1]
["1","09","03","06","10","  ","Project Close Out  Beam Trans Hall                          "]
["1","09","03","06","11","  ","PPE - Pre-Purchase Equipment                                ",{"$nulls":30},1719726.8,1]
["1","09","03","07","  ","  ","SITEWORK, Earthwork, Site Utilities, & Survey               ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,10976850.09]
["1","09","03","07","01","  ","SW - General Requirements                                   ",{"$nulls":30},2160058.05,1]
["1","09","03","07","02","  ","SW - Earthwork, Site Utilities & Survey                     ",{"$nulls":30},7966210.34,1]
["1","09","03","07","03","  ","SW - Concrete                                               "]
["1","09","03","07","15","  ","SW - Mechanical                                             "]
["1","09","03","07","16","  ","SW - Electrical                                             ",{"$nulls":30},850581.7,1]
["1","09","03","07","17","  ","SW - Others (include Div 4, and 6 through 14)               ",{"$nulls":30},0,1]
["1","09","03","07","20","  ","SW - Project Close Out                                      "]
["1","09","03","08","  ","  ","Beam Transport Hall (BTH)                                   ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,8901217.19]
["1","09","03","08","01","  ","BTH - Site Preparation/General Requirements                 ",{"$nulls":30},837115.5,1]
["1","09","03","08","02","  ","BTH - Site Construction                                     "]
["1","09","03","08","03","  ","BTH - Concrete                                              ",{"$nulls":30},5658698.2,1]
["1","09","03","08","05","  ","BTH - Metals                                                ",{"$nulls":30},24286.5,1]
["1","09","03","08","15","  ","BTH - Mechanical                                            ",{"$nulls":30},293981,1]
["1","09","03","08","16","  ","BTH - Electrical                                            ",{"$nulls":30},1840289.99,1]
["1","09","03","08","17","  ","BTH - Others (include Div 4, and 6 through 14)              ",{"$nulls":30},246846,1]
["1","09","03","08","20","  ","BTH - Project Close Out                                     ",{"$nulls":30},0,1]
["1","09","03","09","  ","  ","Front End Enclosure (FEE)                                   ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,2087455.6]
["1","09","03","09","01","  ","FEE - Site Preparation/General Requirements                 "]
["1","09","03","09","02","  ","FEE - Site Construction                                     "]
["1","09","03","09","03","  ","FEE - Concrete                                              ",{"$nulls":30},1298427.2,1]
["1","09","03","09","05","  ","FEE - Metals                                                ",{"$nulls":30},1000,1]
["1","09","03","09","15","  ","FEE - Mechanical                                            ",{"$nulls":30},269566.3,1]
["1","09","03","09","16","  ","FEE - Electrical                                            ",{"$nulls":30},286444.1,1]
["1","09","03","09","17","  ","FEE - Others (include Div 4, and 6 through 14)              ",{"$nulls":30},232018,1]
["1","09","03","09","20","  ","FEE - Project Close Out                                     ",{"$nulls":30},0,1]
["1","09","03","10","  ","  ","Electron Beam Dump (EBD)                                    ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,2742721.16]
["1","09","03","10","01","  ","EBD - Site Preparation/General Requirements                 ",{"$nulls":30},646228.36,1]
["1","09","03","10","02","  ","EBD - Site Construction                                     "]
["1","09","03","10","03","  ","EBD - Concrete                                              ",{"$nulls":30},1364485.6,1]
["1","09","03","10","05","  ","EBD - Metals                                                ",{"$nulls":30},194268,1]
["1","09","03","10","15","  ","EBD - Mechanical                                            ",{"$nulls":30},282412,1]
["1","09","03","10","16","  ","EBD - Electrical                                            ",{"$nulls":30},220123.2,1]
["1","09","03","10","17","  ","EBD - Others (include Div 4, and 6 through 14)              ",{"$nulls":30},35204,1]
["1","09","03","10","20","  ","EBD - Project Close Out                                     ",{"$nulls":30},0,1]
["1","09","03","11","  ","  ","Near Experimental Hall (NEH)                                ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,17827504.2]
["1","09","03","11","01","  ","NEH - Site Preparation/General Requirements                 ",{"$nulls":30},3922761.1,1]
["1","09","03","11","02","  ","NEH - Site Construction                                     ",{"$nulls":30},401259,1]
["1","09","03","11","03","  ","NEH - Concrete                                              ",{"$nulls":30},4608735.9,1]
["1","09","03","11","05","  ","NEH - Metals                                                ",{"$nulls":30},316200.4,1]
["1","09","03","11","15","  ","NEH - Mechanical                                            ",{"$nulls":30},4568612.1,1]
["1","09","03","11","16","  ","NEH - Electrical                                            ",{"$nulls":30},1962929.7,1]
["1","09","03","11","17","  ","NEH - Others (include Div 4, and 6 through 14)              ",{"$nulls":30},1859230,1]
["1","09","03","11","20","  ","NEH - Project Close Out                                     ",{"$nulls":30},187776,1]
["1","09","03","12","  ","  ","Undulator Hall (UH)                                         ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,9421628.39]
["1","09","03","12","01","  ","UH - Site Preparation/General Requirements                  ",{"$nulls":30},3084151.42,1]
["1","09","03","12","02","  ","UH - Site Construction                                      "]
["1","09","03","12","03","  ","UH - Concrete                                               "]
["1","09","03","12","05","  ","UH - Metals                                                 "]
["1","09","03","12","15","  ","UH Mechanical                                               ",{"$nulls":30},636639.2,1]
["1","09","03","12","16","  ","UH - Electrical                                             ",{"$nulls":30},1169397.07,1]
["1","09","03","12","17","  ","UH - Others (include Div 4, and 6 through 14)               ",{"$nulls":30},193268,1]
["1","09","03","12","19","  ","UH Tinnel Construction                                      ",{"$nulls":30},4338172.7,1]
["1","09","03","13","  ","  ","X-Ray Transport & Diagnostic (XRTD)                         ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,5063343.2]
["1","09","03","13","15","  ","XRTD - Mechanical                                           ",{"$nulls":30},369615,1]
["1","09","03","13","16","  ","XRTD - Electrical                                           ",{"$nulls":30},565660.8,1]
["1","09","03","13","17","  ","XRTD - Others (include Div 4, and 6 through 14)             ",{"$nulls":30},0,1]
["1","09","03","13","19","  ","XRTD - Tunnel Construction                                  ",{"$nulls":30},4128067.4,1]
["1","09","03","13","20","  ","XRTD - Project Close Out                                    ",{"$nulls":30},0,1]
["1","09","03","14","  ","  ","Far Experimental Hall (FEH)                                 ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,10527822]
["1","09","03","14","01","  ","FEH - Site Preparation/General Requirements                 ",{"$nulls":30},0,1]
["1","09","03","14","02","  ","FEH - Site Construction                                     ",{"$nulls":30},2581732,1]
["1","09","03","14","03","  ","FEH - Concrete                                              "]
["1","09","03","14","05","  ","FEH - Metals                                                "]
["1","09","03","14","15","  ","FEH - Mechanical                                            ",{"$nulls":30},1194493,1]
["1","09","03","14","16","  ","FEH - Electrical                                            ",{"$nulls":30},573444.5,1]
["1","09","03","14","17","  ","FEH - Others (include Div 4, and 6 through 14)              ",{"$nulls":30},89904,1]
["1","09","03","14","18","  ","FEH - Access Tunnel                                         ",{"$nulls":30},2592642.2,1]
["1","09","03","14","19","  ","FEH - Tunnel Construction                                   ",{"$nulls":30},3495606.3,1]
["1","09","03","14","20","  ","FEH - Project Close Out                                     ",{"$nulls":30},0,1]
["1","09","03","15","  ","  ","BTH Service Buildings 2.1, 2.2, and 2.3 (SB BTH)            ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,3085262.8]
["1","09","03","15","03","  ","SB BTH - Concrete                                           "]
["1","09","03","15","05","  ","SB BTH - Metals                                             ",{"$nulls":30},798997.5,1]
["1","09","03","15","15","  ","SB BTH - Mechanical                                         ",{"$nulls":30},1017901.4,1]
["1","09","03","15","16","  ","SB BTH - Electrical                                         ",{"$nulls":30},1268363.9,1]
["1","09","03","15","17","  ","SB BTH - Others (include Div 4, and 6 through 14            ",{"$nulls":30},0,1]
["1","09","03","15","20","  ","SB BTH - Project Close Out                                  ",{"$nulls":30},0,1]
["1","09","03","16","  ","  ","UH Service Building 3.1 (SB UH)                             ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,1544755.5]
["1","09","03","16","01","  ","SB UH - Site Preparation                                    ",{"$nulls":30},0,1]
["1","09","03","16","03","  ","SB UH - Concrete                                            ",{"$nulls":30},123152.7,1]
["1","09","03","16","05","  ","SB UH - Metals                                              ",{"$nulls":30},250982.6,1]
["1","09","03","16","15","  ","SB UH - Mechanical                                          ",{"$nulls":30},741864,1]
["1","09","03","16","16","  ","SB UH - Electrical                                          ",{"$nulls":30},427485.2,1]
["1","09","03","16","17","  ","SB UH - Others (include Div 4, and 6 through 14)            ",{"$nulls":30},1271,1]
["1","09","03","16","20","  ","SB UH - Project Close Out                                   ",{"$nulls":30},0,1]
["1","09","03","17","  ","  ","FEH Access Tunnel Service Yard (SY FEH)                     ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,792127.2]
["1","09","03","17","01","  ","SY FEH - Site Preparation                                   "]
["1","09","03","17","03","  ","SY FEH - Concrete                                           ",{"$nulls":30},517218,1]
["1","09","03","17","05","  ","SY FEH - Metals                                             "]
["1","09","03","17","15","  ","SY FEH - Mechanical                                         ",{"$nulls":30},0,1]
["1","09","03","17","16","  ","SY FEH - Electrical                                         ",{"$nulls":30},249909.2,1]
["1","09","03","17","17","  ","SY FEH - Others (include Div 4, and 6 through 14            ",{"$nulls":30},25000,1]
["1","09","03","17","20","  ","SY FEH - Project Close Out                                  ",{"$nulls":30},0,1]
["1","09","03","18","  ","  ","Central Utility Plant (CUP)                                 ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,6556468.79]
["1","09","03","18","01","  ","CUP - Site Preparation/General Requirements                 ",{"$nulls":30},44228.4,1]
["1","09","03","18","02","  ","CUP - Site Construction                                     ",{"$nulls":30},301761.94,1]
["1","09","03","18","03","  ","CUP - Concrete                                              ",{"$nulls":30},708786.9,1]
["1","09","03","18","05","  ","CUP - Metals                                                ",{"$nulls":30},675343,1]
["1","09","03","18","15","  ","CUP - Mechanical                                            ",{"$nulls":30},1639750.3,1]
["1","09","03","18","16","  ","CUP - Electrical                                            ",{"$nulls":30},3108398.25,1]
["1","09","03","18","17","  ","CUP - Others (include Div 4, and 6 through 14)              ",{"$nulls":30},78200,1]
["1","09","03","18","20","  ","CUP - Project Close Out                                     ",{"$nulls":30},0,1]
["1","09","03","19","  ","  ","SLAC Space Renovation for LCLS Ops                          ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,4987766.07]
["1","09","03","19","01","  ","ED&I of SLAC Space Renovations for LCLS Ops                 ",{"$nulls":30},744241.07,1]
["1","09","03","19","02","  ","Construction of  SLAC Space Renovation for LCLS             ",{"$nulls":30},4243525,1]
["1","09","03","20","  ","  ","Project Close Out - Conventional Facilities System          ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,1595791.13]
["1","09","03","20","01","  ","Non-Turner Trade  Project Close Out                         ",{"$nulls":30},163791.13,1]
["1","09","03","20","02","  ","Turner Trade Project Close Out                              ",{"$nulls":30},1432000,1]
["2","  ","  ","  ","  ","  ","LCLS PROJECT - R&D, SPARES, COMMISSIONING                   ",{"$nulls":4},14335285.919999998,null,17332885.049999997,null,776864.7,null,2477827.16,null,5681822.23,null,0,null,3865041.49,null,2039021.6,null,0,null,739820.4,null,4395440.33,null,3803595.58,null,1608224.95,null,1865450.91]
["2","01","  ","  ","  ","  ","LCLS PROJECT MGMT, PLANNING & ADMN (OPC)                    ",{"$nulls":4},14335285.919999998,null,8632183.89,null,171298.67,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,1608224.95,null,0]
["2","01","01","  ","  ","  ","LCLS Commissioning Mgmt & Physics Support                   ",{"$nulls":4},605351.45,null,8632183.89,null,171298.67,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,1608224.95,null,0]
["2","01","01","01","  ","  ","LCLS Commissioning Management                               ",{"$nulls":6},925188.77,{"$nulls":24},1]
["2","01","01","02","  ","  ","Injector Physics                                            ",{"$nulls":6},1192757.09,{"$nulls":24},1]
["2","01","01","03","  ","  ","Linac Physics                                               ",{"$nulls":6},522315.95,{"$nulls":24},1]
["2","01","01","04","  ","  ","Undulator Physics                                           ",{"$nulls":6},611090.23,{"$nulls":24},1]
["2","01","01","05","  ","  ","X-Ray Transport Physics                                     ",{"$nulls":28},958682.37,null,null,1]
["2","01","01","06","  ","  ","X-Ray Physics Commissioning                                 ",{"$nulls":28},649542.58,null,null,1]
["2","01","01","07","  ","  ","Conventional Facilities Physics                             ",{"$nulls":6},704239.45,{"$nulls":24},1]
["2","01","01","08","  ","  ","Consulting Physics (Collaboration)                          ",{"$nulls":6},804750.63,{"$nulls":24},1]
["2","01","01","09","  ","  ","Consulting Physics (SLAC)                                   ",{"$nulls":6},644600.75,{"$nulls":24},1]
["2","01","01","10","  ","  ","Global Controls Physics Liaison                             ",{"$nulls":4},605351.45,{"$nulls":26},1]
["2","01","01","11","  ","  ","Global Controls OPC                                         ",{"$nulls":4},0,null,683676.31,null,171298.67,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","01","01","11","01","  ","EPICS Control Modules                                       ",{"$nulls":8},0,{"$nulls":22},1]
["2","01","01","11","02","  ","LLRF Controls                                               ",{"$nulls":8},3729.24,{"$nulls":22},1]
["2","01","01","11","11","  ","Global Controls Commissioning                               ",{"$nulls":8},54314.64,{"$nulls":22},1]
["2","01","01","11","12","  ","Global Controls Management - OPC                            ",{"$nulls":6},567971.92,{"$nulls":24},1]
["2","01","01","11","12","01","Global Controls Management - OPC Level of Effort            "]
["2","01","01","11","13","  ","SLC Aware IOC                                               ",{"$nulls":6},115704.39,{"$nulls":24},1]
["2","01","01","11","14","  ","Controls - Networking and Data Comm. OPC                    ",{"$nulls":8},0,{"$nulls":22},1]
["2","01","01","11","15","  ","Controls S/W Applications LOE                               ",{"$nulls":8},113254.79,{"$nulls":22},1]
["2","01","01","12","  ","  "," E-Beam Systems Commissioning Management                    ",{"$nulls":6},636231.45,{"$nulls":24},1]
["2","01","01","13","  ","  "," E-Beam Systems Physics Support                             ",{"$nulls":6},1507938.58,{"$nulls":24},1]
["2","01","01","14","  ","  ","Laser Commissioning Management                              ",{"$nulls":6},399394.68,{"$nulls":24},1]
["2","01","02","  ","  ","  ","R&D Studies & Prototyping                                   ",{"$nulls":10},0,{"$nulls":20},1]
["2","01","02","01","  ","  ","R&D Studies & Prototyping                                   ",{"$nulls":4},54811.17,{"$nulls":26},1]
["2","01","03","  ","  ","  ","Project Mgmnt, Planning and Admn - M&S (OPC)                ",{"$nulls":4},0,{"$nulls":26},1]
["2","01","03","01","  ","  ","SLAC Project Office - General                               ",{"$nulls":4},8131955.73,{"$nulls":26},1]
["2","01","03","02","  ","  ","SLAC Project Support                                        ",{"$nulls":4},3534844.94,{"$nulls":26},1]
["2","01","03","03","  ","  ","Project Mgmnt, Planning and Admn - M&S (OPC)                ",{"$nulls":4},2008322.63,{"$nulls":26},1]
["2","01","03","05","  ","  ","X-Ray Transport Physics                                     "]
["2","01","03","06","  ","  ","X-Ray Endstation Physics                                    "]
["2","01","03","07","  ","  ","Conventional Facilities Physics                             "]
["2","01","03","08","  ","  ","Consulting Physics (Collaboration)                          "]
["2","01","03","09","  ","  ","Consulting Physics (SLAC)                                   "]
["2","01","03","10","  ","  ","Global Controls Physics Liaison                             "]
["2","01","03","11","  ","  "," Physics Commissioning Support - General                    "]
["2","02","  ","  ","  ","  ","INJECTOR SYSTEM (OPC)                                       ",{"$nulls":4},0,null,3031145.53,null,193140.46,null,2037123.66,null,0,null,0,null,0,null,0,null,0,null,739820.4,null,0,null,0,null,0,null,0]
["2","02","01","  ","  ","  ","Injector System Management & Integration                    ",{"$nulls":10},0,{"$nulls":20},1]
["2","02","01","01","  ","  ","Injector System Integration Effort / M&S                    "]
["2","02","01","02","  ","  ","High level Application Software                             "]
["2","02","01","03","  ","  ","Feedback Software                                           "]
["2","02","02","  ","  ","  ","Injector Controls Subsystem                                 ",{"$nulls":4},0,null,1651610.5,null,15609.7,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","02","02","01","  ","  ","Personnel Protection System (PPS) R&D                       ",{"$nulls":6},294631.6,{"$nulls":24},1]
["2","02","02","02","  ","  ","Beam Containment Subsystem (BCS)                            ",{"$nulls":6},108179.78,{"$nulls":24},1]
["2","02","02","03","  ","  ","Machine Protection Subsystem (MPS)                          ",{"$nulls":6},130132,{"$nulls":24},1]
["2","02","02","04","  ","  ","Power Conv (beamline pwr supp) Spares                       ",{"$nulls":8},15609.7,{"$nulls":22},1]
["2","02","02","04","01","  ","Power Supply Controls                                       "]
["2","02","02","05","  ","  ","LLRF Controls                                               ",{"$nulls":4},0,null,283922.42,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","02","02","05","01","  ","LLRF Controls                                               ",{"$nulls":6},283922.42,{"$nulls":24},1]
["2","02","02","06","  ","  ","E-Beam Diagnostics Controls                                 ",{"$nulls":4},0,null,566346.5,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","02","02","06","01","  ","Controls - Wire Scanners                                    ",{"$nulls":6},8039.6,{"$nulls":24},1]
["2","02","02","06","02","  ","Controls - BPM Processor Module                             ",{"$nulls":6},436070.12,{"$nulls":24},1]
["2","02","02","06","03","  ","Controls - Toroids                                          ",{"$nulls":6},20420.41,{"$nulls":24},1]
["2","02","02","06","05","  ","Controls - Profile Monitors                                 ",{"$nulls":6},70476.1,{"$nulls":24},1]
["2","02","02","06","06","  ","Control - EO Diagnostic                                     "]
["2","02","02","06","12","  ","Controls - Movable Collimator                               ",{"$nulls":6},26393.51,{"$nulls":24},1]
["2","02","02","06","14","  ","Controls - Faraday Cup                                      ",{"$nulls":6},4946.76,{"$nulls":24},1]
["2","02","02","06","15","  ","Controls - Tune-Up Dump                                     ",{"$nulls":6},0,{"$nulls":24},1]
["2","02","02","06","16","  ","Cherenkov Commissioning Support                             ",{"$nulls":6},0,{"$nulls":24},1]
["2","02","02","08","  ","  ","Timing Controls                                             ",{"$nulls":6},162888.35,{"$nulls":24},1]
["2","02","02","09","  ","  ","Vacuum Controls                                             ",{"$nulls":6},105509.85,{"$nulls":24},1]
["2","02","02","10","  ","  ","Software & Controls Infrastructure                          "]
["2","02","02","11","  ","  ","EPICS VXI Control Modules                                   "]
["2","02","02","12","  ","  ","Laser Controls                                              "]
["2","02","02","13","  ","  ","Laser Heater Controls                                       ",{"$nulls":6},0,{"$nulls":24},1]
["2","02","03","  ","  ","  ","Injector Lasers                                             ",{"$nulls":4},0,null,602212.03,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,739820.4,null,0,null,0,null,0,null,0]
["2","02","03","01","  ","  ","Drive Laser Prototyping                                     ",{"$nulls":22},162320.51,{"$nulls":8},1]
["2","02","03","02","  ","  ","Drive Laser System                                          ",{"$nulls":22},575250.78,{"$nulls":8},1]
["2","02","03","03","  ","  ","Drive Laser Pre-Operations                                  ",{"$nulls":6},602212.03,{"$nulls":24},1]
["2","02","03","14","  ","  ","LSR HTR - Beam Conditioning Optics (Laser Bay)              ",{"$nulls":22},2249.11,{"$nulls":8},1]
["2","02","03","15","  ","  ","LSR HTR - Transport Optics (Bay to Tunnel)                  "]
["2","02","03","16","  ","  ","LSR HTR - Photon Beam Diagnostics                           "]
["2","02","04","  ","  ","  ","Injector RF Subsystem                                       ",{"$nulls":4},0,null,0,null,0,null,1186480.96,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","02","04","01","  ","  ","RF Gun & Load Lock                                          ",{"$nulls":4},0,null,0,null,0,null,1047624.39,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","02","04","01","01","  ","RF Gun                                                      ",{"$nulls":10},1039800.67,{"$nulls":20},1]
["2","02","04","01","02","  ","RF Gun Supports                                             ",{"$nulls":10},7823.72,{"$nulls":20},1]
["2","02","04","01","03","  ","Gun Load Lock                                               "]
["2","02","04","02","  ","  ","Cathode Processing (CP) Station                             ",{"$nulls":4},0,null,0,null,0,null,117914.98,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","02","04","02","01","  ","CP Cathode Assembly & Supports                              "]
["2","02","04","02","02","  ","CP Load Lock                                                ",{"$nulls":10},117914.98,{"$nulls":20},1]
["2","02","04","05","  ","  ","Injector RF Waveguide Subsystem                             ",{"$nulls":4},0,null,0,null,0,null,20941.59,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","02","04","05","02","  ","RF Waveguide Supports                                       ",{"$nulls":10},20941.59,{"$nulls":20},1]
["2","02","04","06","  ","  ","Injector Linac Structures                                   ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","02","04","06","02","  ","L0-2 Structure Assembly                                     ",{"$nulls":10},0,{"$nulls":20},1]
["2","02","05","  ","  ","  ","Injector Magnets & Supports                                 ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","02","05","02","  ","  ","Injector Quadrupoles                                        ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","02","05","02","03","  ","DL1 QB Quadrupole                                           ",{"$nulls":10},0,{"$nulls":20},1]
["2","02","05","02","05","  ","SAB Quadrupoles ( )                                         ",{"$nulls":10},0,{"$nulls":20},1]
["2","02","07","  ","  ","  ","Injector Diagnostics                                        ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","02","07","01","  ","  ","Injector Beam Position Monitors                             ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","02","07","01","03","  ","L0-1TL0-2 BPMs ( )                                          ",{"$nulls":10},0,{"$nulls":20},1]
["2","02","07","01","04","  ","LTDL1 BPMs ( )                                              ",{"$nulls":8},0,{"$nulls":22},1]
["2","02","07","04","  ","  ","Injector Profile Monitors                                   ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","02","07","04","01","  ","GTL Faraday Cup/YAG1                                        ",{"$nulls":10},0,{"$nulls":20},1]
["2","02","08","  ","  ","  ","Injector System Emittance Enhancement                       ",{"$nulls":4},0,null,0,null,177530.76,null,850642.7,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","02","08","01","  ","  ","Heater Integration                                          ",{"$nulls":10},97147.45,{"$nulls":20},1]
["2","02","08","02","  ","  ","Heater Laser & Optics                                       ",{"$nulls":10},191075.99,{"$nulls":20},1]
["2","02","08","03","  ","  ","Heater Magnets                                              ",{"$nulls":4},0,null,0,null,0,null,394089.93,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","02","08","03","01","  ","Heater Dipoles                                              ",{"$nulls":10},84174.29,{"$nulls":20},1]
["2","02","08","03","02","  ","Heater Undulator                                            ",{"$nulls":10},309915.64,{"$nulls":20},1]
["2","02","08","04","  ","  ","Heater Vacuum                                               ",{"$nulls":10},95551.34,{"$nulls":20},1]
["2","02","08","05","  ","  ","Heater Diagnostics                                          ",{"$nulls":10},54851.09,{"$nulls":20},1]
["2","02","08","06","  ","  ","Heater Install & Align                                      ",{"$nulls":10},17926.9,{"$nulls":20},1]
["2","02","08","07","  ","  ","Laser Heater Controls                                       ",{"$nulls":8},177530.76,{"$nulls":22},1]
["2","02","17","  ","  ","  ","Injector System Commissioning                               ",{"$nulls":4},0,null,777323,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","02","17","02","  ","  ","Drive Laser Commissioning                                   ",{"$nulls":6},45033.26,{"$nulls":24},1]
["2","02","17","10","  ","  ","Injector Commisioning                                       ",{"$nulls":6},706827.25,{"$nulls":24},1]
["2","02","17","11","  ","  ","Injector Engr, Design, Maintenance Support                  ",{"$nulls":6},25462.49,{"$nulls":24},1]
["2","03","  ","  ","  ","  ","LINAC SYSTEM (OPC)                                          ",{"$nulls":4},0,null,2067331.57,null,111055.22,null,37726.31,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","03","01","  ","  ","  ","Linac System Mgmt & Integration                             ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","03","01","01","  ","  ","Linac System Mgmt & Integration                             ",{"$nulls":6},0,{"$nulls":24},1]
["2","03","02","  ","  ","  ","Linac Controls & Power Conversion Subsystem                 ",{"$nulls":4},0,null,0,null,111055.22,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","03","02","01","  ","  ","Personnel Protection System (PPS)                           ",{"$nulls":6},0,{"$nulls":24},1]
["2","03","02","02","  ","  ","Beam Containment System (BCS)                               ",{"$nulls":6},0,{"$nulls":24},1]
["2","03","02","03","  ","  ","Machine Protection System (MPS)                             ",{"$nulls":6},0,{"$nulls":24},1]
["2","03","02","04","  ","  ","Power Conversion                                            ",{"$nulls":4},0,null,0,null,111055.22,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","03","02","04","01","  ","Spare Power Supply (Dipole Type)                            ",{"$nulls":8},36725.79,{"$nulls":22},1]
["2","03","02","04","02","  ","Spare Power Supply (Quad Type)                              ",{"$nulls":8},39823.68,{"$nulls":22},1]
["2","03","02","04","03","  ","Spare Power Supply (Trim Type)                              ",{"$nulls":8},34505.75,{"$nulls":22},1]
["2","03","02","04","04","  ","Controls & Power Supply - Spare Misc Hdwr                   "]
["2","03","02","05","  ","  ","Controls - LLRF                                             ",{"$nulls":6},0,{"$nulls":24},1]
["2","03","02","06","  ","  ","Controls - LLRF                                             ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","03","02","06","01","  ","Controls - E-Beam Diagnostic                                ",{"$nulls":6},0,{"$nulls":24},1]
["2","03","02","06","02","  ","Controls - Wire Scanners                                    ",{"$nulls":6},0,{"$nulls":24},1]
["2","03","02","06","03","  ","Controls - BPMs                                             ",{"$nulls":6},0,{"$nulls":24},1]
["2","03","02","06","04","  ","Controls - Stoppers Commissioning                           ",{"$nulls":6},0,{"$nulls":24},1]
["2","03","02","06","05","  ","Controls - Profile Monitors                                 ",{"$nulls":6},0,{"$nulls":24},1]
["2","03","02","06","07","  ","Controls - BLM                                              ",{"$nulls":6},0,{"$nulls":24},1]
["2","03","02","06","09","  ","Controls - Single Beam Dump                                 ",{"$nulls":6},0,{"$nulls":24},1]
["2","03","02","06","10","  ","Controls - E-Beam Dump                                      ",{"$nulls":6},0,{"$nulls":24},1]
["2","03","02","06","12","  ","Controls - Collimators                                      ",{"$nulls":6},0,{"$nulls":24},1]
["2","03","02","08","  ","  ","Controls - Toroids                                          ",{"$nulls":6},0,{"$nulls":24},1]
["2","03","02","09","  ","  ","Controls - Vacuum                                           ",{"$nulls":6},0,{"$nulls":24},1]
["2","03","03","  ","  ","  ","Linac Magnets & Supports                                    ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","03","03","01","  ","  ","Bend Magnet (BX1_BC1)                                       ",{"$nulls":10},0,{"$nulls":20},1]
["2","03","03","02","  ","  ","Bend Magnet (BX3_LTU)                                       ",{"$nulls":10},0,{"$nulls":20},1]
["2","03","03","03","  ","  ","Bend Magnet (BX2_BC2)                                       ",{"$nulls":10},0,{"$nulls":20},1]
["2","03","03","04","  ","  ","Bend Magnet (BY_LTU)                                        ",{"$nulls":10},0,{"$nulls":20},1]
["2","03","03","05","  ","  ","Quad Magnet (Quad_LTU)                                      ",{"$nulls":10},0,{"$nulls":20},1]
["2","03","03","09","  ","  ","Bend Magnet (BYD_LTU)                                       ",{"$nulls":10},0,{"$nulls":20},1]
["2","03","03","11","  ","  ","Bend Magnet (BYPM_LTU)                                      ",{"$nulls":10},0,{"$nulls":20},1]
["2","03","03","12","  ","  ","Bend Magnet (BYKIK_LTU)                                     ",{"$nulls":10},0,{"$nulls":20},1]
["2","03","03","13","  ","  ","Bend Magnet (BYW_LTU)                                       ",{"$nulls":10},0,{"$nulls":20},1]
["2","03","04","  ","  ","  ","Linac Vacuum Subsystem                                      ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","03","04","01","  ","  ","Linac Vacuum Subsystem Operations Equip                     ",{"$nulls":10},0,{"$nulls":20},1]
["2","03","04","02","  ","  ","Linac Beamline Vacuum System                                ",{"$nulls":10},0,{"$nulls":20},1]
["2","03","04","03","  ","  ","BC1 Vacuum System                                           ",{"$nulls":10},0,{"$nulls":20},1]
["2","03","04","04","  ","  ","BC2 Vacuum System                                           ",{"$nulls":10},0,{"$nulls":20},1]
["2","03","04","05","  ","  ","Linac to Undulator (LTU) Vacuum System                      ",{"$nulls":10},0,{"$nulls":20},1]
["2","03","04","06","  ","  ","Dumpline Vacuum System                                      ",{"$nulls":10},0,{"$nulls":20},1]
["2","03","04","07","  ","  ","Vacuum Undulator Interface                                  ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","03","04","07","01","  ","Entrance Assembly Section                                   ",{"$nulls":10},0,{"$nulls":20},1]
["2","03","04","07","02","  ","Exit Assembly Section                                       ",{"$nulls":10},0,{"$nulls":20},1]
["2","03","05","  ","  ","  ","Linac Electron Diagnostics                                  ",{"$nulls":4},0,null,0,null,0,null,37726.31,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","03","05","01","  ","  ","Wire Scanners                                               ",{"$nulls":10},0,{"$nulls":20},1]
["2","03","05","02","  ","  ","Beam Position Monitors                                      ",{"$nulls":10},0,{"$nulls":20},1]
["2","03","05","03","  ","  ","Toroids Beam Charge                                         ",{"$nulls":10},0,{"$nulls":20},1]
["2","03","05","04","  ","  ","Stoppers Tune Up Dump                                       ",{"$nulls":10},0,{"$nulls":20},1]
["2","03","05","05","  ","  ","Profile Monitors                                            ",{"$nulls":10},1177.47,{"$nulls":20},1]
["2","03","05","07","  ","  ","Bunch Length Monitors                                       ",{"$nulls":10},36548.84,{"$nulls":20},1]
["2","03","05","08","  ","  ","Beam Loss Monitors                                          ",{"$nulls":10},0,{"$nulls":20},1]
["2","03","05","11","  ","  ","Protection Collimators                                      ",{"$nulls":10},0,{"$nulls":20},1]
["2","03","05","12","  ","  ","Movable Collimators                                         ",{"$nulls":10},0,{"$nulls":20},1]
["2","03","05","13","  ","  ","Safety Dump                                                 ",{"$nulls":10},0,{"$nulls":20},1]
["2","03","05","14","  ","  ","Charge Monitor (Entrance/Exit Assebmly)                     ",{"$nulls":10},0,{"$nulls":20},1]
["2","03","06","  ","  ","  ","Linac RF Subsystem                                          ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","03","06","05","  ","  ","X-Band High Power System                                    ",{"$nulls":10},0,{"$nulls":20},1]
["2","03","06","07","  ","  ","RF Distribution System                                      ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","03","06","07","01","  ","Modulator                                                   ",{"$nulls":10},0,{"$nulls":20},1]
["2","03","06","07","02","  ","Solid State Sub Booster                                     ",{"$nulls":10},0,{"$nulls":20},1]
["2","03","06","07","05","  ","Bunch Length Electronics                                    ",{"$nulls":10},0,{"$nulls":20},1]
["2","03","06","07","07","  ","RF Distribution L2 & L3                                     ",{"$nulls":10},0,{"$nulls":20},1]
["2","03","06","07","08","  ","RF Fiber Optics Electronics                                 ",{"$nulls":10},0,{"$nulls":20},1]
["2","03","07","  ","  ","  ","Linac System Commissioning                                  ",{"$nulls":4},0,null,2067331.57,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","03","07","10","  ","  ","L2/BC2/L3 Commissioning                                     ",{"$nulls":6},2067331.57,{"$nulls":24},1]
["2","04","  ","  ","  ","  ","UNDULATOR SYSTEM (OPC)                                      ",{"$nulls":4},0,null,3602224.06,null,301370.35,null,402977.19,null,5681822.23,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","04","01","  ","  ","  ","Undulator System Management & Integration                   ",{"$nulls":4},0,null,0,null,0,null,0,null,2452486.71,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","04","01","01","  ","  ","Undulator System Mgmt & Integration                         ",{"$nulls":12},2452486.71,{"$nulls":18},1]
["2","04","02","  ","  ","  ","Controls                                                    ",{"$nulls":4},0,null,0,null,301370.35,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","04","02","01","  ","  ","Controls Management and Integration                         ",{"$nulls":8},139399.3,{"$nulls":22},1]
["2","04","02","07","  ","  ","Machine Protection                                          ",{"$nulls":8},0,{"$nulls":22},1]
["2","04","02","10","  ","  ","Undulator Controls Module Spares                            ",{"$nulls":8},69382.17,{"$nulls":22},1]
["2","04","02","12","  ","  ","Undulator Controls Rack & Cables Spares                     ",{"$nulls":8},15920.04,{"$nulls":22},1]
["2","04","02","15","  ","  ","BLM Interface Module Development                            ",{"$nulls":8},76668.84,{"$nulls":22},1]
["2","04","03","  ","  ","  ","Undulator Magnet & Support                                  ",{"$nulls":4},0,null,0,null,0,null,402977.19,null,2054650.82,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","04","03","01","  ","  ","Und Magnet & Support-Mgmt & Integration                     ",{"$nulls":12},0,{"$nulls":18},1]
["2","04","03","02","  ","  ","First Prototype Undulator & Mfg Plan                        ",{"$nulls":12},10685.95,{"$nulls":18},1]
["2","04","03","03","  ","  ","1st Article Undulators & Long Lead Procurements             ",{"$nulls":12},16542.48,{"$nulls":18},1]
["2","04","03","04","  ","  ","Production Undulator                                        ",{"$nulls":12},1966308.15,{"$nulls":18},1]
["2","04","03","05","  ","  ","Focusing Magnets                                            ",{"$nulls":12},46937.89,{"$nulls":18},1]
["2","04","03","06","  ","  ","Undulator Magnetic Measurement Facility (SLAC)              ",{"$nulls":10},402977.19,{"$nulls":20},1]
["2","04","03","08","  ","  ","Fixed Supports                                              ",{"$nulls":12},14176.35,{"$nulls":18},1]
["2","04","04","  ","  ","  ","Vacuum System                                               ",{"$nulls":4},0,null,0,null,0,null,0,null,472195.34,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","04","04","02","  ","  ","Undulator Vacuum Chamber Assembly                           ",{"$nulls":12},450871.36,{"$nulls":18},1]
["2","04","04","02","01","  ","Surface Roughness Minimization                              "]
["2","04","04","02","03","  ","Materials Study for AC Conductivity                         "]
["2","04","04","03","  ","  ","Beam-line Bellows Module Assembly                           ",{"$nulls":12},6572.56,{"$nulls":18},1]
["2","04","04","04","  ","  ","Single Undulator Test(SUV) Vacuum                           ",{"$nulls":12},0,{"$nulls":18},1]
["2","04","04","05","  ","  ","Short Diagnostic Break (SDB) Assembly                       ",{"$nulls":12},6205.84,{"$nulls":18},1]
["2","04","04","06","  ","  ","Long Diagnostic Break (LDB) Assembly                        ",{"$nulls":12},8545.58,{"$nulls":18},1]
["2","04","04","07","  ","  ","Entrance Section Assembly                                   ",{"$nulls":12},0,{"$nulls":18},1]
["2","04","04","08","  ","  ","Exit Section Assembly                                       ",{"$nulls":12},0,{"$nulls":18},1]
["2","04","04","09","  ","  ","Baking System                                               "]
["2","04","05","  ","  ","  ","Undulator System Diagnostics [OPC]                          ",{"$nulls":4},0,null,0,null,0,null,0,null,702489.36,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","04","05","02","  ","  ","Undulator Line Diagnostics                                  ",{"$nulls":12},78303.12,{"$nulls":18},1]
["2","04","05","03","  ","  ","High-Power X-Ray and Profile Diagnostics (HPD)              ",{"$nulls":12},0,{"$nulls":18},1]
["2","04","05","04","  ","  ","End-of-Undulator(EOU) X-ray and Profile diagnost            ",{"$nulls":12},30338.06,{"$nulls":18},1]
["2","04","05","05","  ","  ","RFBPM                                                       ",{"$nulls":12},468338.44,{"$nulls":18},1]
["2","04","05","06","  ","  ","Beam Finder Wire                                            ",{"$nulls":12},42903.87,{"$nulls":18},1]
["2","04","05","07","  ","  ","Charge Monitor (CM)                                         ",{"$nulls":12},0,{"$nulls":18},1]
["2","04","05","08","  ","  ","Beam Loss Monitoring                                        ",{"$nulls":12},80060.87,{"$nulls":18},1]
["2","04","05","09","  ","  ","Radiation Detection Monitor (RDM)                           ",{"$nulls":12},0,{"$nulls":18},1]
["2","04","05","10","  ","  ","SIngle Undulator Test (SUT)-Diagnostics                     ",{"$nulls":12},2545,{"$nulls":18},1]
["2","04","06","  ","  ","  ","LTU/Undulator/Dump Commissioning                            ",{"$nulls":4},0,null,3602224.06,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","04","06","01","  ","  ","LTU/Undulator/Dump Commissioning                            ",{"$nulls":6},3602224.06,{"$nulls":24},1]
["2","05","  ","  ","  ","  ","X-RAY TRANSPORT & DIAGNOSTICS SYSTEMS (OPC)                 ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,3865041.49,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","05","01","  ","  ","  ","System Management & Integration                             ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,1022700.26,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","05","01","01","  ","  ","Management                                                  ",{"$nulls":16},1022700.26,{"$nulls":14},1]
["2","05","02","  ","  ","  ","Controls                                                    "]
["2","05","02","01","  ","  ","Controls - EPICS                                            "]
["2","05","02","02","  ","  ","Controls - System                                           "]
["2","05","03","  ","  ","  ","Mechanical & Vacuum Subsystem                               "]
["2","05","03","01","  ","  ","Vacuum Systems Engineering                                  "]
["2","05","03","02","  ","  ","Mech/Vac Front End                                          "]
["2","05","03","03","  ","  ","Mech/Vac Near Hall                                          "]
["2","05","03","04","  ","  ","Mech/Vac Tunnel                                             "]
["2","05","03","05","  ","  ","Mech/Vac Far Hall                                           "]
["2","05","04","  ","  ","  ","Optical Subsystem                                           ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,1516170.92,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","05","04","01","  ","  "," Optical Subsystem R&D                                      ",{"$nulls":16},434278.91,{"$nulls":14},1]
["2","05","04","02","  ","  ","Spares for Optical Subsystem                                ",{"$nulls":16},1081892.01,{"$nulls":14},1]
["2","05","04","03","  ","  ","End Station Optics                                          "]
["2","05","04","04","  ","  ","Crystals & Gratings                                         "]
["2","05","05","  ","  ","  ","Diagnostics Subsystem                                       ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,1326170.31,null,0,null,0,null,0,null,0,null,0,null,0,null,0]
["2","05","05","01","  ","  "," Diagnostics Subsystem R&D                                  ",{"$nulls":16},100701.33,{"$nulls":14},1]
["2","05","05","02","  ","  ","Modeling & Simulation                                       ",{"$nulls":16},1167947.87,{"$nulls":14},1]
["2","05","05","03","  ","  ","Spares for Diagnostics Subsystem                            ",{"$nulls":16},57521.11,{"$nulls":14},1]
["2","05","05","04","  ","  ","Commissioning Diagnostics                                   ",{"$nulls":16},0,{"$nulls":14},1]
["2","05","06","  ","  ","  ","X-Ray Transport & Diag. System Commissioning                "]
["2","05","06","01","  ","  ","X-Ray Transport & Diag. System Commissioning                "]
["2","06","  ","  ","  ","  ","X-RAY END STATION SYSTEMS (OPC)                             ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,2039021.6,null,0,null,0,null,4395440.33,null,3803595.58,null,0,null,0]
["2","06","01","  ","  ","  ","XE System Mgmt & Integration                                ",{"$nulls":24},772033.79,{"$nulls":6},1]
["2","06","01","01","  ","  ","Management                                                  "]
["2","06","02","  ","  ","  ","Controls Subsystem                                          ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,2039021.6,null,0,null,0,null,0,null,0,null,0,null,0]
["2","06","02","01","  ","  ","Cabling                                                     "]
["2","06","02","02","  ","  ","Network                                                     "]
["2","06","02","03","  ","  ","PC Support                                                  "]
["2","06","02","04","  ","  ","LBNL Laser Timing                                           ",{"$nulls":18},1275014.75,{"$nulls":12},1]
["2","06","02","05","  ","  ","X-Ray PPS                                                   "]
["2","06","02","06","  ","  ","X-Ray MPS                                                   "]
["2","06","02","07","  ","  ","Laser PPS                                                   "]
["2","06","02","08","  ","  ","2-D X-Ray Detector Controls                                 ",{"$nulls":18},764006.85,{"$nulls":12},1]
["2","06","03","  ","  ","  ","Commissioning                                               ",{"$nulls":26},3803595.58,{"$nulls":4},1]
["2","06","03","01","  ","  ","Commissioning - Photon Beamline                             ",{"$nulls":26},0,{"$nulls":4},1]
["2","06","03","02","  ","  ","Commissioning - XES Laser                                   ",{"$nulls":26},0,{"$nulls":4},1]
["2","06","03","03","  ","  ","Commissioning - AMO Experiment                              ",{"$nulls":26},0,{"$nulls":4},1]
["2","06","03","05","  ","  ","Commissioning - 2D X-Ray Detector                           ",{"$nulls":26},0,{"$nulls":4},1]
["2","06","04","  ","  ","  ","Spares                                                      ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,240003.64,null,0,null,0,null,0]
["2","06","04","01","  ","  ","Spares - PPS Stoppers                                       ",{"$nulls":24},240003.64,{"$nulls":6},1]
["2","06","04","02","  ","  ","Spares -                                                    "]
["2","06","04","03","  ","  ","Spares -                                                    "]
["2","06","04","04","  ","  ","Spares -                                                    "]
["2","06","04","05","  ","  ","Spares -                                                    "]
["2","06","05","  ","  ","  ","X-Ray Detectors                                             ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,3383402.9,null,0,null,0,null,0]
["2","06","05","01","  ","  ","Beam Imaging                                                "]
["2","06","05","02","  ","  ","2-D X-Ray Detector                                          ",{"$nulls":24},3383402.9,{"$nulls":6},1]
["2","06","05","02","01","  ","Proto 2 ASIC                                                "]
["2","06","05","02","02","  ","Proto 3 ASIC                                                "]
["2","06","05","02","03","  ","Full Lot Prototype                                          "]
["2","06","05","02","04","  ","500px Detector                                              "]
["2","06","05","02","05","  ","2D X-Ray Detector Commissioning                             "]
["2","06","05","03","  ","  ","Beam Intensity                                              "]
["2","06","05","04","  ","  ","Streak Camera                                               "]
["2","06","07","  ","  ","  ","Atomic Physics                                              "]
["2","06","07","01","  ","  ","Atomic Physics Samples                                      "]
["2","06","07","02","  ","  ","Atomic Physics Diagnostics                                  "]
["2","06","07","03","  ","  ","Atomic Physics Data Analysis                                "]
["2","06","07","04","  ","  ","Atomic Physics Detectors                                    "]
["2","09","  ","  ","  ","  ","Conventional Facility Commissioning                         ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,1865450.91]
["2","09","03","  ","  ","  ","Beam Path Project Commissioning                             ",{"$nulls":4},0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,0,null,1865450.91]
["2","09","03","05","  ","  ","Beam Path Project Commissioning                             ",{"$nulls":30},1865450.91,1]

{"sheet":"DATA","index":5,"n_rows":802,"n_cols":15,"rows_kept":802,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}
["L1","L2","CA1","DESCRIP","BCWS","BCWP","ACWP","BAC","C4","%COMP","CAM","LOE","MS%COMP","MS","PP"]
[1,1.01,"1.01.01.01","Radiation Physics",916420.39,883056.93,883056.93,1723724.21,"1A",0.5123,"Wendy Sisson",840667.28,883056.93]
[1,1.01,"1.01.01.02","ESH Management & Coordination",1138761.99,1086513.52,1086513.52,1525363.66,"1A",0.7123,"Wendy Sisson",438850.14,1086513.52]
[1,1.01,"1.01.01.03","Seismic & Engineering Support",33636.54,33636.54,33636.54,33636.54,"1A",1,"Wendy Sisson",null,33636.54]
[1,1.01,"1.01.02.01.01","Project Office - General",7498418.96,7463415.46,7463415.46,8022927.32,"1A",0.9303,"Wendy Sisson",559511.86,7463415.46]
[1,1.01,"1.01.02.01.02","Project Support",5076628.82,4969415.93,4969415.93,6501143.29,"1A",0.7644,"Wendy Sisson",1531727.36,4969415.93]
[1,1.01,"1.01.02.01.03","Project Office M&S",1639240.05,1624094.57,1624094.57,1892285.77,"1A",0.8583,"Wendy Sisson",268191.2,1624094.57]
[1,1.01,"1.01.02.01.04","SSRL Physics Support",291511.64,291511.64,291511.64,291511.64,"1A",1,"Wendy Sisson",null,291511.64]
[1,1.01,"1.01.03.01","Global Laser Coordination",60601.86,60601.86,60601.86,60601.86,"1A",1,"Wendy Sisson",null,60601.86]
[1,1.01,"1.01.03.02","Global Alignment Coordination",472713.6,472713.6,472713.6,472713.6,"1A",1,"Wendy Sisson",null,472713.6]
[1,1.01,"1.01.03.03","System Integration",890857.72,876169.19,876169.19,1086998.66,"1A",0.806,"Wendy Sisson",210829.47,876169.19]
[1,1.01,"1.01.03.05.02","LLRF Controls",362200.99,362200.99,362200.99,362200.99,"2G",1,"Hamid Shoaee",null,362200.99]
[1,1.01,"1.01.03.05.03","E-Beam Diagnostics & Controls",1742433.4,1742433.4,1742433.4,1742433.4,"2G",1,"Hamid Shoaee",null,1742433.4]
[1,1.01,"1.01.03.05.04","Laser Controls Design",23509.68,23509.68,23509.68,23509.68,"2G",1,"Hamid Shoaee",null,23509.68]
[1,1.01,"1.01.03.05.05","Laser Heater Controls",860.16,860.16,860.16,860.16,"2G",1,"Hamid Shoaee",null,860.16]
[1,1.01,"1.01.03.05.06","Timing Controls",77840.37,77840.37,77840.37,77840.37,"2G",1,"Hamid Shoaee",null,77840.37]
[1,1.01,"1.01.03.05.07","Vacuum Controls",336915.54,336915.54,336915.54,336915.54,"2G",1,"Hamid Shoaee",null,336915.54]
[1,1.01,"1.01.03.05.09","Power Supply Controls",2442710.43,2411218.67,2411218.67,2695942.11,"2G",0.8944,"Hamid Shoaee",154863.03,2541079.08]
[1,1.01,"1.01.03.05.10","PPS/BCS Controls",802982.95,802982.95,802982.95,802982.95,"2G",1,"Hamid Shoaee",802982.95]
[1,1.01,"1.01.03.05.11","Controls - MPS",27602.52,27602.52,27602.52,27602.52,"2G",1,"Hamid Shoaee",null,27602.52]
[1,1.01,"1.01.03.05.12","Global Controls Management",2774091.58,2774091.58,2774091.58,3127233.02,"2G",0.8871,"Hamid Shoaee",353141.44,2774091.58]
[1,1.01,"1.01.03.05.13","SLC Aware IOC",301161.61,301161.61,301161.61,301161.61,"2G",1,"Hamid Shoaee",null,301161.61]
[1,1.01,"1.01.03.05.15","Controls - BCS",0,0,0,0,"2G",0,"Hamid Shoaee"]
[1,1.01,"1.01.03.06","Technical Requirements/Parameters",723002.27,723002.27,723002.27,723002.27,"1A",1,"Wendy Sisson",null,723002.27]
[1,1.01,"1.01.04.01","Education/Outreach Travel",10634.22,10634.22,10634.22,10634.22,"1A",1,"Wendy Sisson",null,10634.22]
[1,1.01,"1.01.04.02","Education/Outreach M&S",6872.58,6872.58,6872.58,6872.58,"1A",1,"Wendy Sisson",null,6872.58]
[1,1.02,"1.02.01.01.01","Injector Region Integration",552876.93,552876.93,552876.93,552876.93,"2A",1,"Jose Chan",null,552876.93]
[1,1.02,"1.02.01.01.02","Gun Area Integration",155631.51,155631.51,155631.51,155631.51,"2A",1,"Jose Chan",null,155631.51]
[1,1.02,"1.02.01.01.03","Accelerator Area Integration",105265.87,105265.87,105265.87,105265.87,"2A",1,"Jose Chan",null,105265.87]
[1,1.02,"1.02.01.01.04","Heater Area Integration",136198.42,136198.42,136198.42,136198.42,"2A",1,"Jose Chan",null,136198.42]
[1,1.02,"1.02.01.01.05","Wall Area Integration",112947.96,112947.96,112947.96,112947.96,"2A",1,"Jose Chan",null,112947.96]
[1,1.02,"1.02.01.01.06","Insertion Area Integration",117044.02,117044.02,117044.02,117044.02,"2A",1,"Jose Chan",null,117044.02]
[1,1.02,"1.02.01.01.07","Spectrometer Area Integration",213097.59,213097.59,213097.59,213097.59,"2A",1,"Jose Chan",null,213097.59]
[1,1.02,"1.02.01.01.08","Drive Laser Integration",72643.73,72643.73,72643.73,72643.73,"2A",1,"Jose Chan",null,72643.73]
[1,1.02,"1.02.01.03","Feedback Software",0.54,0.54,0.54,0.54,"2A",1,"Jose Chan",null,0.54]
[1,1.02,"1.02.01.04","Injector System Integration Effort / M&S",3176500.47,3176500.47,3176500.47,3176500.47,"2A",1,"Jose Chan",0,3176500.47]
[1,1.02,"1.02.02.01","Personnel Protection Subsystem (PPS)",195146.09,195146.09,195146.09,195146.09,"2G",1,"Hamid Shoaee",191389.16,3756.93]
[1,1.02,"1.02.02.02","Beam Containment Subsystem (BCS)",130158.53,130158.53,130158.53,130158.53,"2G",1,"Hamid Shoaee",null,130158.53]
[1,1.02,"1.02.02.03","Machine Protection Subsystem (MPS)",160050.91,160050.91,160050.91,160050.91,"2G",1,"Hamid Shoaee",null,160050.91]
[1,1.02,"1.02.02.04.01","Beamline Pwr Supplies - (Dipole Type)",101515.84,101515.84,101515.84,101515.84,"2G",1,"Hamid Shoaee",null,101515.84]
[1,1.02,"1.02.02.04.02","Power Supply Controls",21308.51,21308.51,21308.51,21308.51,"2G",1,"Hamid Shoaee",null,21308.51]
[1,1.02,"1.02.02.04.03","Beamline Pwr Supplies - (Trim Type)",168376.7,168376.7,168376.7,168376.7,"2G",1,"Hamid Shoaee",null,168376.7]
[1,1.02,"1.02.02.04.04","Beamline Pwr Supply - Misc Hdwr",753915.78,753915.78,753915.78,753915.78,"2G",1,"Hamid Shoaee",null,753915.78]
[1,1.02,"1.02.02.05.01","Readback & Controls - RF Gun LLRF & Temperature",617294.72,617294.72,617294.72,617294.72,"2G",1,"Hamid Shoaee",null,617294.72]
[1,1.02,"1.02.02.05.02","Readback & Controls - L0 LLRF",0,0,0,0,"2G",0,"Hamid Shoaee"]
[1,1.02,"1.02.02.05.03","Readback & Controls - Transverse Cavity LLRF",0,0,0,0,"2G",0,"Hamid Shoaee"]
[1,1.02,"1.02.02.05.04","S-Band Cavity Controls",0,0,0,0,"2G",0,"Hamid Shoaee"]
[1,1.02,"1.02.02.06.01","Controls - Wire Scanners",71666.25,71666.25,71666.25,71666.25,"2G",1,"Hamid Shoaee",null,71666.25]
[1,1.02,"1.02.02.06.02","Controls - BPM",105948.03,105948.03,105948.03,105948.03,"2G",1,"Hamid Shoaee",null,105948.03]
[1,1.02,"1.02.02.06.03","Controls - Toroids",76031.05,76031.05,76031.05,76031.05,"2G",1,"Hamid Shoaee",null,76031.05]
[1,1.02,"1.02.02.06.05","Controls - Profile Monitors",456749.03,456749.03,456749.03,456749.03,"2G",1,"Hamid Shoaee",null,456749.03]
[1,1.02,"1.02.02.06.06","Controls - E/O Diagnostics",0,0,0,0,"2G",0,"Hamid Shoaee"]
[1,1.02,"1.02.02.06.12","Injector Movable Collimators",0,0,0,0,"2G",0,"Hamid Shoaee"]
[1,1.02,"1.02.02.06.14","Controls - Faraday Cups",1483.8,1483.8,1483.8,1483.8,"2G",1,"Hamid Shoaee",null,1483.8]
[1,1.02,"1.02.02.06.15","Controls - Tune-Up Dump",18484.79,18484.79,18484.79,18484.79,"2G",1,"Hamid Shoaee",null,18484.79]
[1,1.02,"1.02.02.06.16","Controls - Cherenkov Radiation Detector",0,0,0,0,"2G",0,"Hamid Shoaee"]
[1,1.02,"1.02.02.08","Timing Controls",85879.59,85879.59,85879.59,85879.59,"2G",1,"Hamid Shoaee",null,85879.59]
[1,1.02,"1.02.02.09","Vacuum Controls",176015.31,176015.31,176015.31,176015.31,"2G",1,"Hamid Shoaee",null,176015.31]
[1,1.02,"1.02.02.10.03","Data Communications",91779.04,91779.04,91779.04,91779.04,"2G",1,"Hamid Shoaee",null,91779.04]
[1,1.02,"1.02.02.10.04","Computers & Crates",195558.7,195558.7,195558.7,195558.7,"2G",1,"Hamid Shoaee",null,195558.7]
[1,1.02,"1.02.02.11","EPICS VXI Control Modules",90921.61,90921.61,90921.61,90921.61,"2G",1,"Hamid Shoaee",null,90921.61]
[1,1.02,"1.02.02.12.02","Controls - Gun Laser",100090.83,100090.83,100090.83,100090.83,"2G",1,"Hamid Shoaee",null,100090.83]
[1,1.02,"1.02.02.13","Laser Heater Controls",0,0,0,0,"2G",0,"Hamid Shoaee"]
[1,1.02,"1.02.03.01.01","Drive Laser Support (ANL)",28271.11,28271.11,28271.11,28271.11,"2L",1,"Bill White",null,28271.11]
[1,1.02,"1.02.03.01.02","Drive Laser Support (LLNL)",383603.18,383603.18,383603.18,383603.18,"2L",1,"Bill White",369303.83,14299.35]
[1,1.02,"1.02.03.02","Drive Laser System",1295292.74,1295292.74,1295292.74,1295292.74,"2L",1,"Bill White",null,1295292.74]
[1,1.02,"1.02.03.03","Drive Laser Diagnostics",911619.61,911619.61,911619.61,911619.61,"2L",1,"Bill White",null,911619.61]
[1,1.02,"1.02.03.04","Timing Stability Monitoring",120095.82,120095.82,120095.82,120095.82,"2L",1,"Bill White",null,120095.82]
[1,1.02,"1.02.03.05","Steering Stability Feedback & Msmts",94772.05,94772.05,94772.05,94772.05,"2L",1,"Bill White",null,94772.05]
[1,1.02,"1.02.03.06","Pre Amp Low Power Comp",0,0,0,0,"2L",0,"Bill White"]
[1,1.02,"1.02.03.07","Transport to Tunnel & Relay Optics",176706.36,176706.36,176706.36,176706.36,"2L",1,"Bill White",null,176706.36]
[1,1.02,"1.02.03.08","UV Launch, Conditioning & Diagnostics",413474.14,413474.14,413474.14,413474.14,"2L",1,"Bill White",null,413474.14]
[1,1.02,"1.02.03.11","LB Infrastructure & LB System Wide Items",459890.53,459890.53,459890.53,459890.53,"2L",1,"Bill White",null,459890.53]
[1,1.02,"1.02.03.12","Alignment Laser",53820.27,53820.27,53820.27,53820.27,"2L",1,"Bill White",null,53820.27]
[1,1.02,"1.02.03.13","Light path to Streak Camera",28187.22,28187.22,28187.22,28187.22,"2L",1,"Bill White",null,28187.22]
[1,1.02,"1.02.03.21","UV Conv Harmonic Generation Unit (Closed Account)",6282.65,6282.65,6282.65,6282.65,"2L",1,"Bill White",null,6282.65]
[1,1.02,"1.02.04.01","RF Gun & Load Lock",0,0,0,0,"2A",0,"Jose Chan"]
[1,1.02,"1.02.04.01.01","RF Gun",1357543.09,1357543.09,1357543.09,1357543.09,"2A",1,"Jose Chan",null,1357543.09]
[1,1.02,"1.02.04.01.02","RF Gun Supports",54030.37,54030.37,54030.37,54030.37,"2A",1,"Jose Chan",null,54030.37]
[1,1.02,"1.02.04.01.03","Gun Load Lock",675.12,675.12,675.12,675.12,"2A",1,"Jose Chan",null,675.12]
[1,1.02,"1.02.04.01.04","Gun Load Lock Supports",15296.86,15296.86,15296.86,15296.86,"2A",1,"Jose Chan",null,15296.86]
[1,1.02,"1.02.04.01.05","Gun Solenoid",280595.41,280595.41,280595.41,280595.41,"2A",1,"Jose Chan",null,280595.41]
[1,1.02,"1.02.04.01.06","Gun Solenoid Supports",940.03,940.03,940.03,940.03,"2A",1,"Jose Chan",null,940.03]
[1,1.02,"1.02.04.01.07","Gun RF Feed",12471.84,12471.84,12471.84,12471.84,"2A",1,"Jose Chan",null,12471.84]
[1,1.02,"1.02.04.01.08","Gun RF Feed Supports",1039.97,1039.97,1039.97,1039.97,"2A",1,"Jose Chan",null,1039.97]
[1,1.02,"1.02.04.01.09","RF Gun Spares Credit",-435266.48,-435266.48,-435266.48,-435266.48,"2A",1,"Jose Chan",null,-435266.48]
[1,1.02,"1.02.04.02.01","CP Cathode Assembly & Supports",0,0,0,0,"2A",0,"Jose Chan"]
[1,1.02,"1.02.04.02.02","CP Load Lock",0,0,0,0,"2A",0,"Jose Chan"]
[1,1.02,"1.02.04.02.03","CP Load Lock Supports",334.25,334.25,334.25,334.25,"2A",1,"Jose Chan",null,334.25]
[1,1.02,"1.02.04.02.04","CP Station",0,0,0,0,"2A",0,"Jose Chan"]
[1,1.02,"1.02.04.02.05","Cathode Lab Infrastructure",0,0,0,0,"2A",0,"Jose Chan"]
[1,1.02,"1.02.04.03.01","Controls Interface & Timing",372264.3,372264.3,372264.3,372264.3,"2A",1,"Jose Chan",null,372264.3]
[1,1.02,"1.02.04.03.02","LLRF Phase Reference System",239674.49,239674.49,239674.49,239674.49,"2A",1,"Jose Chan",null,239674.49]
[1,1.02,"1.02.04.03.03","LLRF Monitor & Control System",875477.4,875477.4,875477.4,875477.4,"2A",1,"Jose Chan",null,875477.4]
[1,1.02,"1.02.04.03.04","Beam Phase Monitor Cavity",160137.56,160137.56,160137.56,160137.56,"2A",1,"Jose Chan",null,160137.56]
[1,1.02,"1.02.04.03.05","RF System S/W Development / Docs",0,0,0,0,"2A",0,"Jose Chan"]
[1,1.02,"1.02.04.04.03","Transverse Cavity High Power",0,0,0,0,"2A",0,"Jose Chan"]
[1,1.02,"1.02.04.05","Injector RF Waveguide Subsystem",0,0,0,0,"2A",0,"Jose Chan"]
[1,1.02,"1.02.04.05.01","RF Waveguides",1169010.29,1169010.29,1169010.29,1169010.29,"2A",1,"Jose Chan",null,1169010.29]
[1,1.02,"1.02.04.05.02",null,8.67,8.67,8.67,8.67,"2A",1,"Jose Chan",null,8.67]
[1,1.02,"1.02.04.06","Injector Linac Structures",0,0,0,0,"2A",0,"Jose Chan"]
[1,1.02,"1.02.04.06.01","L0A-0B Structure Assembly",749122.64,749122.64,749122.64,749122.64,"2A",1,"Jose Chan",null,749122.64]
[1,1.02,"1.02.04.06.03","Major Linac Support",42268.82,42268.82,42268.82,42268.82,"2A",1,"Jose Chan",null,42268.82]
[1,1.02,"1.02.04.06.05","LTDL1 RF Kicker",183465.32,183465.32,183465.32,183465.32,"2A",1,"Jose Chan",null,183465.32]
[1,1.02,"1.02.05.01.01","Gun Spectrometer Dipole",96968.22,96968.22,96968.22,96968.22,"2A",1,"Jose Chan",null,96968.22]
[1,1.02,"1.02.05.01.02","DL1 B01 & B02 Dipoles",113622.66,113622.66,113622.66,113622.66,"2A",1,"Jose Chan",null,113622.66]
[1,1.02,"1.02.05.01.03","SAB Spectrometer Dipole",200049.12,200049.12,200049.12,200049.12,"2A",1,"Jose Chan",null,200049.12]
[1,1.02,"1.02.05.01.04","Chicane DIPOLES (4)",11765.34,11765.34,11765.34,11765.34,"2A",1,"Jose Chan",null,11765.34]
[1,1.02,"1.02.05.02.01","Gun Spectrometer Quadrupoles",66962.26,66962.26,66962.26,66962.26,"2A",1,"Jose Chan",null,66962.26]
[1,1.02,"1.02.05.02.02","Injector Quadrupoles",295486.88,295486.88,295486.88,295486.88,"2A",1,"Jose Chan",null,295486.88]
[1,1.02,"1.02.05.02.03","LTDL1 Quadrupoles (4)",107.52,107.52,107.52,107.52,"2A",1,"Jose Chan",null,107.52]
[1,1.02,"1.02.05.03.01","Gun Solenoid Correctors",7503.36,7503.36,7503.36,7503.36,"2A",1,"Jose Chan",null,7503.36]
[1,1.02,"1.02.05.03.02","Gun Spectrometer Correctors",0,0,0,0,"2A",0,"Jose Chan"]
[1,1.02,"1.02.05.03.03","Injector Correctors - A",226727.67,226727.67,226727.67,226727.67,"2A",1,"Jose Chan",null,226727.67]
[1,1.02,"1.02.05.03.04","Injector Correctors - D (Gun)",0,0,0,0,"2A",0,"Jose Chan"]
[1,1.02,"1.02.05.03.05","GS Quadrupole Correctors",121.39,121.39,121.39,121.39,"2A",1,"Jose Chan",null,121.39]
[1,1.02,"1.02.05.04","Linac Solenoid",206600.06,206600.06,206600.06,206600.06,"2A",1,"Jose Chan",203877.12,2722.94]
[1,1.02,"1.02.05.05","Injector Laser Heater Subsystem",0,0,0,0,"2A",0,"Jose Chan"]
[1,1.02,"1.02.05.05.01","System Design & Optimization (LSR HTR)",0,0,0,0,"2A",0,"Jose Chan"]
[1,1.02,"1.02.05.05.02","Injector Undulator",3990.41,3990.41,3990.41,3990.41,"2A",1,"Jose Chan",null,3990.41]
[1,1.02,"1.02.06.01","Injector Vacuum Engineering",415522.83,415522.83,415522.83,415522.83,"2A",1,"Jose Chan",null,415522.83]
[1,1.02,"1.02.06.02","Injector Vacuum Components",196201.03,196201.03,196201.03,196201.03,"2A",1,"Jose Chan",null,196201.03]
[1,1.02,"1.02.06.03","Injector Vacuum Special Chambers",308757.83,308757.83,308757.83,308757.83,"2A",1,"Jose Chan",null,308757.83]
[1,1.02,"1.02.06.04","Injector Vacuum Supports Engineering",76494.68,76494.68,76494.68,76494.68,"2A",1,"Jose Chan",null,76494.68]
[1,1.02,"1.02.06.05","Injector Vacuum Support Components",108730.84,108730.84,108730.84,108730.84,"2A",1,"Jose Chan",null,108730.84]
[1,1.02,"1.02.06.06",null,0.01,0.01,0.01,0.01,"2A",1,"Jose Chan",null,0.01]
[1,1.02,"1.02.06.08","DL1 Vacuum Chamber",6336,6336,6336,6336,"2A",1,"Jose Chan",null,6336]
[1,1.02,"1.02.06.10","DL1TL Vacuum Components",74325.62,74325.62,74325.62,74325.62,"2A",1,"Jose Chan",null,74325.62]
[1,1.02,"1.02.07","Injector Diagnostics",0,0,0,0,"2A",0,"Jose Chan"]
[1,1.02,"1.02.07.01.01","Large Aperture BPM",397666.8,397666.8,397666.8,397666.8,"2A",1,"Jose Chan",null,397666.8]
[1,1.02,"1.02.07.01.02","Small Aperture BPM",265734.82,265734.82,265734.82,265734.82,"2A",1,"Jose Chan",null,265734.82]
[1,1.02,"1.02.07.01.06",null,509.61,509.61,509.61,509.61,"2A",1,"Jose Chan",null,509.61]
[1,1.02,"1.02.07.02.01","Current Monitors",129362,129362,129362,129362,"2A",1,"Jose Chan",null,129362]
[1,1.02,"1.02.07.04.01","Profile Monitors",1353292.92,1353292.92,1353292.92,1353292.92,"2A",1,"Jose Chan",null,1353292.92]
[1,1.02,"1.02.07.04.02","GTL Alignment Laser Mirror",136.8,136.8,136.8,136.8,"2A",1,"Jose Chan",null,136.8]
[1,1.02,"1.02.07.04.03","GS Faraday Cup/YAG2",14961.62,14961.62,14961.62,14961.62,"2A",1,"Jose Chan",null,14961.62]
[1,1.02,"1.02.07.04.08","LTDL1 OTR(5)/YAG (1)",38178.24,38178.24,38178.24,38178.24,"2A",1,"Jose Chan",null,38178.24]
[1,1.02,"1.02.07.05","Injector Wire Scanners",111942.54,111942.54,111942.54,111942.54,"2A",1,"Jose Chan",null,111942.54]
[1,1.02,"1.02.07.07","PPS Stopper",134140.73,134140.73,134140.73,134140.73,"2A",1,"Jose Chan",null,134140.73]
[1,1.02,"1.02.17","Injector Installation & Alignment",0,0,0,0,"2A",0,"Jose Chan"]
[1,1.02,"1.02.17.01","Injector Infrastructure Installation",807909.91,807909.91,807909.91,807909.91,"2A",1,"Jose Chan",null,807909.91]
[1,1.02,"1.02.17.02","Injector Controls Subsystem Install & Align",457860.48,457860.48,457860.48,457860.48,"2A",1,"Jose Chan",null,457860.48]
[1,1.02,"1.02.17.03","Injector Lasers Install & Align",92461.42,92461.42,92461.42,92461.42,"2A",1,"Jose Chan",null,92461.42]
[1,1.02,"1.02.17.04","Gun Area Integration",32448.8,32448.8,32448.8,32448.8,"2A",1,"Jose Chan",null,32448.8]
[1,1.02,"1.02.17.06","Accelerator Area Integration",10015.18,10015.18,10015.18,10015.18,"2A",1,"Jose Chan",null,10015.18]
[1,1.02,"1.02.17.07","Heater Area Integration",2099.75,2099.75,2099.75,2099.75,"2A",1,"Jose Chan",null,2099.75]
[1,1.02,"1.02.17.08","Wall Area Integration",46442.29,46442.29,46442.29,46442.29,"2A",1,"Jose Chan",null,46442.29]
[1,1.02,"1.02.17.09","Insertion Area Integration",6.81,6.81,6.81,6.81,"2A",1,"Jose Chan",null,6.81]
[1,1.02,"1.02.17.11","Spectrometer Area Integration",0,0,0,0,"2A",0,"Jose Chan"]
[1,1.02,"1.02.17.12","Injector RF High Power System Install & Align",234542.95,234542.95,234542.95,234542.95,"2A",1,"Jose Chan",null,234542.95]
[1,1.02,"1.02.17.14","Cathode and Load Lock Install & Align",0,0,0,0,"2A",0,"Jose Chan"]
[1,1.02,"1.02.17.15","Injector Laser Heater Subsystem Install & Align",0,0,0,0,"2A",0,"Jose Chan"]
[1,1.03,"1.03.01.01.01","L01 System Integration",338886.18,338886.18,338886.18,338886.18,"2A",1,"Jose Chan",null,338886.18]
[1,1.03,"1.03.01.01.02","BC1 System Integration",454182.12,454182.12,454182.12,454182.12,"2A",1,"Jose Chan",null,454182.12]
[1,1.03,"1.03.01.01.03","L02 System Integration",195163.47,195163.47,195163.47,195163.47,"2A",1,"Jose Chan",null,195163.47]
[1,1.03,"1.03.01.01.04","BC2 System Integration",868912.74,868912.74,868912.74,868912.74,"2A",1,"Jose Chan",null,868912.74]
[1,1.03,"1.03.01.01.05","L03 System Integration",213976.09,213976.09,213976.09,213976.09,"2A",1,"Jose Chan",null,213976.09]
[1,1.03,"1.03.01.01.06","LTU System Integration",897531.97,857654.03,857654.03,958825.85,"2A",0.8945,"Jose Chan",null,958825.85]
[1,1.03,"1.03.01.01.07","E-Dump System Integration",1085956.17,1071235.97,1071235.97,1133292.61,"2A",0.9452,"Jose Chan",null,1133292.61]
[1,1.03,"1.03.01.03","Travel",35434.69,32462.3,32462.3,97236.16,"2A",0.3339,"Jose Chan",64773.86,32462.3]
[1,1.03,"1.03.01.04","Linac Management",2042296.8,2005907.26,2005907.26,2492242.96,"2A",0.8049,"Jose Chan",486335.7,2005907.26]
[1,1.03,"1.03.02.01","Personnel Protection System (PPS)",191274.27,164759.2,164759.2,672929.51,"2G",0.2448,"Hamid Shoaee",null,672929.51]
[1,1.03,"1.03.02.02","Beam Containment System (BCS)",402341.37,377482.13,377482.13,604752.770000001,"2G",0.6242,"Hamid Shoaee",null,604752.7700000006]
[1,1.03,"1.03.02.03","Machine Protection System (MPS)",161116.96,142839.83,142839.83,269017.21,"2G",0.531,"Hamid Shoaee",null,269017.21]
[1,1.03,"1.03.02.04.01","Beamline Power Supplies - (Dipole Type)",197870.86,197870.86,197870.86,423322.55,"2G",0.4674,"Hamid Shoaee",null,423322.55]
[1,1.03,"1.03.02.04.02","Beamline Power Supplies - (Quad Type)",113592.07,113592.07,113592.07,113592.07,"2G",1,"Hamid Shoaee",null,113592.07]
[1,1.03,"1.03.02.04.03","Beamline Power Supplies - (Trim Type)",718132.65,718132.65,718132.65,744587.6,"2G",0.9645,"Hamid Shoaee",null,744587.6]
[1,1.03,"1.03.02.04.04","Controls & Power Supply",2197910.69,2178236.65,2178236.65,3384338.62,"2G",0.6436,"Hamid Shoaee",null,3384338.62]
[1,1.03,"1.03.02.05","Controls - LLRF",798209.47,771160.7,771160.7,970610.68,"2G",0.7945,"Hamid Shoaee",null,970610.68]
[1,1.03,"1.03.02.06.01","Controls - Wire Scanners",170749.95,148455.4,148455.4,265843.58,"2G",0.5584,"Hamid Shoaee",null,265843.58]
[1,1.03,"1.03.02.06.02","Controls - BPMs",614833.38,438214.35,438214.35,746504.56,"2G",0.587,"Hamid Shoaee",98402.51,648102.05]
[1,1.03,"1.03.02.06.03","Controls - Toroids",43439.26,43439.26,43439.26,87104.51,"2G",0.4987,"Hamid Shoaee",null,87104.51]
[1,1.03,"1.03.02.06.04","Controls - Stoppers",2900.8,0,0,6283.47,"2G",0,"Hamid Shoaee",null,6283.47]
[1,1.03,"1.03.02.06.05","Controls - Profile Monitors",154024.59,142167.71,142167.71,156447.69,"2G",0.9087,"Hamid Shoaee",null,156447.69]
[1,1.03,"1.03.02.06.06","Controls - E/O Diagnostics",0,0,0,0,"2G",0,"Hamid Shoaee"]
[1,1.03,"1.03.02.06.07","Controls - Bunch Length Monitors",65741.64,65741.64,65741.64,65741.64,"2G",1,"Hamid Shoaee",null,65741.64]
[1,1.03,"1.03.02.06.08","Controls - Beam Loss Monitors",0,0,0,0,"2G",0,"Hamid Shoaee"]
[1,1.03,"1.03.02.06.09","Controls - Single Beam Dump",2836.8,0,0,2836.8,"2G",0,"Hamid Shoaee",null,2836.8]
[1,1.03,"1.03.02.06.10","Controls - E Beam Dump",1087.44,1087.44,1087.44,1087.44,"2G",1,"Hamid Shoaee",null,1087.44]
[1,1.03,"1.03.02.06.11","Controls - Protection Collimator",52372.09,52372.09,52372.09,52372.09,"2G",1,"Hamid Shoaee",null,52372.09]
[1,1.03,"1.03.02.06.12","Controls - Movable Collimator",35099.65,35099.65,35099.65,77406.77,"2G",0.4534,"Hamid Shoaee",null,77406.77]
[1,1.03,"1.03.02.06.13","Controls - X-Band Accel Structure",1490.4,1490.4,1490.4,1490.4,"2G",1,"Hamid Shoaee",null,1490.4]
[1,1.03,"1.03.02.08","Controls - Timing",109153.73,109153.73,109153.73,396181.51,"2G",0.2755,"Hamid Shoaee",null,396181.51]
[1,1.03,"1.03.02.09.01","Controls - Vacuum Instrumentation & Interlocks",268132.23,261605.38,261605.38,483266.02,"2G",0.5413,"Hamid Shoaee",null,483266.02]
[1,1.03,"1.03.02.09.02","Controls - Vacuum Pump Power Supplies",0,0,0,0,"2G",0,"Hamid Shoaee"]
[1,1.03,"1.03.02.10.04","Data Communications",68646.97,68646.97,68646.97,885600,"2G",0.0775,"Hamid Shoaee",null,885600]
[1,1.03,"1.03.02.10.05","Computers",697593.15,697255.07,697255.07,931463.57,"2G",0.7486,"Hamid Shoaee",null,931463.57]
[1,1.03,"1.03.03.01","Bend Magnet (BX1_BC1)",141909.26,141909.26,141909.26,141909.26,"2A",1,"Jose Chan",null,141909.26]
[1,1.03,"1.03.03.02","Bend Magnet (BX3_LTU)",225054.04,206150.75,206150.75,235101.18,"2A",0.8769,"Jose Chan",null,235101.18]
[1,1.03,"1.03.03.03","Bend Magnet (BX2_BC2)",421082.32,421082.32,421082.32,421082.32,"2A",1,"Jose Chan",null,421082.32]
[1,1.03,"1.03.03.04","Bend Magnet (BY_LTU)",44911.85,44415.6,44415.6,87388.37,"2A",0.5083,"Jose Chan",null,87388.37]
[1,1.03,"1.03.03.05","Quad Magnet (Quad_LTU)",745032.11,736409,736409,753948.22,"2A",0.9767,"Jose Chan",null,753948.22]
[1,1.03,"1.03.03.07","Quad Magnet (QE)",165104.6,165104.6,165104.6,165104.6,"2A",1,"Jose Chan",null,165104.6]
[1,1.03,"1.03.03.08","Corrector Magnet (Type 4)",138943.55,136773.82,136773.82,139160.52,"2A",0.9828,"Jose Chan",null,139160.52]
[1,1.03,"1.03.03.09","Bend Magnet (BYD_LTU)",176825.46,176825.46,176825.46,445043.1,"2A",0.3973,"Jose Chan",null,445043.1]
[1,1.03,"1.03.03.10","Quad Magnet (QA)",105022.22,105022.22,105022.22,105022.22,"2A",1,"Jose Chan",null,105022.22]
[1,1.03,"1.03.03.11","Bend Magnet (BYPM_LTU)",69476.87,69476.87,69476.87,109226.87,"2A",0.6361,"Jose Chan",null,109226.87]
[1,1.03,"1.03.03.12","Bend Magnet (BYKIK_LTU)",116878.29,116878.29,116878.29,116878.29,"2A",1,"Jose Chan",null,116878.29]
[1,1.03,"1.03.03.13","Bend Magnet (BYW_LTU)",1008,1008,1008,1008,"2A",1,"Jose Chan",null,1008]
[1,1.03,"1.03.03.14","BXKIK Linac TCAV Screen Kicker",51178.36,51178.36,51178.36,51178.36,"2A",1,"Jose Chan",null,51178.36]
[1,1.03,"1.03.03.15","Muon Toroid (E-Dump)",0,0,0,0,"2A",0,"Jose Chan"]
[1,1.03,"1.03.04.02","Linac Beamline Vacuum System",540159.52,540159.52,540159.52,540159.52,"2A",1,"Jose Chan",null,540159.52]
[1,1.03,"1.03.04.03","BC1 Vacuum System",670792.43,670792.43,670792.43,670792.43,"2A",1,"Jose Chan",null,670792.43]
[1,1.03,"1.03.04.04","BC2 Vacuum System",489674.31,489674.31,489674.31,489674.31,"2A",1,"Jose Chan",null,489674.31]
[1,1.03,"1.03.04.05","Linac to Undulator (LTU) Vacuum System",805737.76,599150.2,599150.2,868343.74,"2A",0.69,"Jose Chan",null,868343.74]
[1,1.03,"1.03.04.06","Dumpline Vacuum System",686136.98,664068.57,664068.57,703317.3,"2A",0.9442,"Jose Chan",null,703317.3]
[1,1.03,"1.03.04.07.01","Entrance Section Assembly",5575.36,0,0,5575.36,"2A",0,"Jose Chan",null,5575.36]
[1,1.03,"1.03.04.07.02","Exit Section Assembly",8482.21,0,0,8482.21,"2A",0,"Jose Chan",null,8482.21]
[1,1.03,"1.03.04.08","LTU/BSY Cold Trap Vacuum System",39555.06,39555.06,39555.06,81619.77,"2A",0.4846,"Jose Chan",null,81619.77]
[1,1.03,"1.03.05.01","Wire Scanners (11) Summary",436882.13,436882.13,436882.13,584784.23,"2A",0.7471,"Jose Chan",null,584784.23]
[1,1.03,"1.03.05.02.01","BPM - Standard Linac (4) Summary",145896.58,145896.58,145896.58,145896.58,"2A",1,"Jose Chan",null,145896.58]
[1,1.03,"1.03.05.02.02","BPM - RF (10) Summary",26.88,26.88,26.88,26.88,"2A",1,"Jose Chan",null,26.88]
[1,1.03,"1.03.05.02.03","BPM - FFTB (12) Summary",204817.24,180914.14,180914.14,227796.56,"2A",0.7942,"Jose Chan",null,227796.56]
[1,1.03,"1.03.05.02.04","BPM - Large Aperture (2) Summary",258883.5,258883.5,258883.5,258883.5,"2A",1,"Jose Chan",null,258883.5]
[1,1.03,"1.03.05.03","Toroid Beam Current Monitor (10) Summary",229121.35,229121.35,229121.35,229121.35,"2A",1,"Jose Chan",null,229121.35]
[1,1.03,"1.03.05.04","Beam Stoppers (4) Summary",89167.19,80866.51,80866.51,155250.33,"2A",0.5209,"Jose Chan",null,155250.33]
[1,1.03,"1.03.05.05","Profile Monitors (7 OTR-3 PHOSPHOR SCREEN-1 YAG)",921230.92,908389,908389,1341225.12,"2A",0.6773,"Jose Chan",null,1341225.12]
[1,1.03,"1.03.05.06","E/O Bunch Length Monitors (1) Summary",22483.25,22483.25,22483.25,22483.25,"2A",1,"Jose Chan",null,22483.25]
[1,1.03,"1.03.05.07","CSR/OTR/CTR Bunch Length Monitors (5) Summary",754644.16,754644.16,754644.16,754644.16,"2A",1,"Jose Chan",null,754644.16]
[1,1.03,"1.03.05.08.01","PIC Beam Loss Monitors (10) Summary",28843.66,28843.66,28843.66,28843.66,"2A",1,"Jose Chan",null,28843.66]
[1,1.03,"1.03.05.08.02","PLIC Beam Loss Monitors (2) Summary",0,0,0,0,"2A",0,"Jose Chan"]
[1,1.03,"1.03.05.09","Single Beam Dump (1) Summary",127926.03,125876.44,125876.44,134017.71,"2A",0.9393,"Jose Chan",null,134017.71]
[1,1.03,"1.03.05.10","Electron Beam Dump (1) Summary",129806.17,79526.59,79526.59,140691.87,"2A",0.5653,"Jose Chan",null,140691.87]
[1,1.03,"1.03.05.11","Protection Collimators (5) Summary",242394.16,232380.25,232380.25,326170.9,"2A",0.7124,"Jose Chan",null,326170.9]
[1,1.03,"1.03.05.12","Movable Collimators (7x,3y) Summary",595765.89,536054.97,536054.97,653109.6,"2A",0.8208,"Jose Chan",null,653109.6]
[1,1.03,"1.03.05.13","Safety Electron Dump (1) Summary",45249.04,42525.94,42525.94,91652.1,"2A",0.464,"Jose Chan",null,91652.1]
[1,1.03,"1.03.05.14","Charge Monitor (Entrance/Exit Assembly)",0,0,0,0,"2A",0,"Jose Chan"]
[1,1.03,"1.03.06.02","S-Band High Power System",1086051.89,1086051.89,1086051.89,1086051.89,"2A",1,"Jose Chan",991465.05,94586.84]
[1,1.03,"1.03.06.03","S-Band Structures",47685.07,47685.07,47685.07,47685.07,"2A",1,"Jose Chan",null,47685.07]
[1,1.03,"1.03.06.04","X-Band Low Level System",203933.55,203933.55,203933.55,203933.55,"2G",1,"Hamid Shoaee",1457.28,202476.27]
[1,1.03,"1.03.06.05.01","X-Band HP Klystron",397736.77,397736.77,397736.77,397736.77,"2A",1,"Jose Chan",null,397736.77]
[1,1.03,"1.03.06.05.02","X-Band HP Modulator",221501.93,221501.93,221501.93,221501.93,"2A",1,"Jose Chan",null,221501.93]
[1,1.03,"1.03.06.05.03","X-Band HP Waveguide System",282343.89,282343.89,282343.89,282343.89,"2A",1,"Jose Chan",null,282343.89]
[1,1.03,"1.03.06.06","X-Band Structures",164287.99,164287.99,164287.99,164287.99,"2A",1,"Jose Chan",null,164287.99]
[1,1.03,"1.03.06.07.01","Modulator Refurbishment",23218.24,23218.24,23218.24,23218.24,"2A",1,"Jose Chan",null,23218.24]
[1,1.03,"1.03.06.07.02","Solid State Sub Booster",1241.18,1241.18,1241.18,1241.18,"2A",1,"Jose Chan",null,1241.18]
[1,1.03,"1.03.06.07.03","IPA Modifications",0,0,0,0,"2A",0,"Jose Chan"]
[1,1.03,"1.03.06.07.04","Klystron Controls Interfaces",0,0,0,0,"2A",0,"Jose Chan"]
[1,1.03,"1.03.06.07.05","Bunch Length Electronics",0,0,0,0,"2A",0,"Jose Chan"]
[1,1.03,"1.03.06.07.06","RF Phase Measurements",41.36,41.36,41.36,41.36,"2A",1,"Jose Chan",null,41.36]
[1,1.03,"1.03.06.07.07","RF Distribution L2 & L3",31943.14,31943.14,31943.14,31943.14,"2A",1,"Jose Chan",null,31943.14]
[1,1.03,"1.03.06.07.08","RF Fiber Optics Electronics System",0,0,0,0,"2A",0,"Jose Chan"]
[1,1.03,"1.03.06.07.09","RF Stability",0,0,0,0,"2A",0,"Jose Chan"]
[1,1.03,"1.03.07.01","Linac L01 System Installation & Alignment",571735.24,571735.24,571735.24,571735.24,"2A",1,"Jose Chan",null,571735.24]
[1,1.03,"1.03.07.02","Linac BC1 System Installation & Alignment",22575.72,22575.72,22575.72,22575.72,"2A",1,"Jose Chan",null,22575.72]
[1,1.03,"1.03.07.05","Linac L03 System Installation & Alignment",62.88,62.88,62.88,62.88,"2A",1,"Jose Chan",null,62.88]
[1,1.03,"1.03.07.06","Linac LTU System Installation & Alignment",483955.29,233099.83,233099.83,2690374.78,"2A",0.0866,"Jose Chan",null,2690374.78]
[1,1.03,"1.03.07.07","Linac E-Dump System Installation & Alignment",99419.53,59737.27,59737.27,1027320.58,"2A",0.0581,"Jose Chan",null,1027320.58]
[1,1.03,"1.03.07.10.01","Beamline Equip Removal L01 thru BC1 Out",34223.17,34223.17,34223.17,34223.17,"2A",1,"Jose Chan",null,34223.17]
[1,1.03,"1.03.07.10.02","Gallery Waveguide Installation",34312.06,34312.06,34312.06,34312.06,"2A",1,"Jose Chan",null,34312.06]
[1,1.03,"1.03.07.10.03","Beamline Equip Installation L01 thru BC1 Out",897967.56,897967.56,897967.56,897967.56,"2A",1,"Jose Chan",null,897967.56]
[1,1.03,"1.03.07.10.04","2006 Linac Controls Install and Checkout Gallery to Linac B",91278.18,91278.18,91278.18,91278.18,"2A",1,"Jose Chan",null,91278.18]
[1,1.03,"1.03.07.10.05","2006 Linac Controls Install and Checkout L01 to BC1",0,0,0,0,"2A",0,"Jose Chan"]
[1,1.03,"1.03.07.20.01","Beamline Equip Removal L02, L03 and BC2",475794.52,475794.52,475794.52,475794.52,"2A",1,"Jose Chan",null,475794.52]
[1,1.03,"1.03.07.20.02","Beamline Equip Installation L02, L03 and BC2",980416.69,980416.69,980416.69,980416.69,"2A",1,"Jose Chan",null,980416.69]
[1,1.03,"1.03.07.20.03","2007 Linac Controlls Install and Checkout",983298.77,983298.77,983298.77,983298.77,"2A",1,"Jose Chan",null,983298.77]
[1,1.03,"1.03.07.20.04","Linac Undulator Interface",56160.23,0,0,204310.45,"2A",0,"Jose Chan",null,204310.45]
[1,1.04,"1.04.01.01.01","Undulator System Management - Technical",5200587.97,5141561.09,5141561.09,5800722.01,"2A",0.8864,"Jose Chan",659160.92,5141561.09]
[1,1.04,"1.04.01.01.02","ANL Project Support",2811512.63,2807797.14,2807797.14,2839193.01,"4A",0.9889,"Geoff Pile",31395.87,2807797.14]
[1,1.04,"1.04.01.02.01","Undulator System M&S - General",477537.41,458312.98,458312.98,493982.87,"4A",0.9278,"Geoff Pile",35669.89,458312.98]
[1,1.04,"1.04.01.02.02","Undulator System Travel",467821.27,454647.76,454647.76,467821.27,"4A",0.9718,"Geoff Pile",13173.51,454647.76]
[1,1.04,"1.04.01.03","Undulator System Reviews and Workshops",3721.94,3100.3,3100.3,3721.94,"4A",0.833,"Geoff Pile",621.64,3100.3]
[1,1.04,"1.04.02.01.03","Software Interface with SLAC",40121.66,40121.66,40121.66,40121.66,"2G",1,"Hamid Shoaee",null,40121.66]
[1,1.04,"1.04.02.01.04","Undulator Cable, Tray, and Rack Layout",36966.29,36966.29,36966.29,36966.29,"2G",1,"Hamid Shoaee",null,36966.29]
[1,1.04,"1.04.02.01.05","Miscellaneous Controls",23495.96,23495.96,23495.96,23495.96,"2G",1,"Hamid Shoaee",null,23495.96]
[1,1.04,"1.04.02.02.01","Undulator Cam Movers",279889.73,279889.73,279889.73,279889.73,"2G",1,"Hamid Shoaee",null,279889.73]
[1,1.04,"1.04.02.02.02","Motion Test Stand",80443.59,80443.59,80443.59,80443.59,"2G",1,"Hamid Shoaee",null,80443.59]
[1,1.04,"1.04.02.02.06","Scanning Wire Motion",773.74,773.74,773.74,773.74,"2G",1,"Hamid Shoaee",null,773.74]
[1,1.04,"1.04.02.02.07","Translation Stage Motion",36989.3,36989.3,36989.3,36989.3,"2G",1,"Hamid Shoaee",null,36989.3]
[1,1.04,"1.04.02.03.01","RFBPM",53369.64,53369.64,53369.64,53369.64,"2G",1,"Hamid Shoaee",null,53369.64]
[1,1.04,"1.04.02.03.02","Charge Monitor",0,0,0,0,"2G",0,"Hamid Shoaee"]
[1,1.04,"1.04.02.03.03","Beam Finder Wire",2075.1,2075.1,2075.1,2075.1,"2G",1,"Hamid Shoaee",null,2075.1]
[1,1.04,"1.04.02.04.01","OTR Monitor",19391.55,19391.55,19391.55,19391.55,"2G",1,"Hamid Shoaee",null,19391.55]
[1,1.04,"1.04.02.04.03","Observation station video",9154.16,9154.16,9154.16,9154.16,"2G",1,"Hamid Shoaee",null,9154.16]
[1,1.04,"1.04.02.05.01","Strongback Temperature monitoring",19897.35,19897.35,19897.35,19897.35,"2G",1,"Hamid Shoaee",null,19897.35]
[1,1.04,"1.04.02.06.01","Ion Pump Controller",0,0,0,0,"2G",0,"Hamid Shoaee"]
[1,1.04,"1.04.02.06.02","RGA",0,0,0,0,"2G",0,"Hamid Shoaee"]
[1,1.04,"1.04.02.07.01","Undulator Beam Loss Monitor Controls",2995.99,2995.99,2995.99,2995.99,"2G",1,"Hamid Shoaee",null,2995.99]
[1,1.04,"1.04.02.07.02","Cerenkov Detector",0,0,0,0,"2G",0,"Hamid Shoaee"]
[1,1.04,"1.04.02.08","Power Supply Controls",276034.49,237686.64,237686.64,346412.75,"2G",0.6861,"Hamid Shoaee",null,346412.75]
[1,1.04,"1.04.02.10","Undulator Controls Module",848124.89,477919.61,477919.61,1166820.41,"2G",0.4096,"Hamid Shoaee",null,1166820.41]
[1,1.04,"1.04.02.12","Rack anc Cable",361511.92,340827.17,340827.17,590210.77,"2G",0.5775,"Hamid Shoaee",null,590210.77]
[1,1.04,"1.04.02.13","BPMs",10842.98,6453.6,6453.6,10842.98,"2G",0.5952,"Hamid Shoaee",null,10842.98]
[1,1.04,"1.04.02.14","Long Term Testing",22230.66,14614.97,14614.97,22230.66,"2G",0.6574,"Hamid Shoaee",null,22230.66]
[1,1.04,"1.04.02.15","Undulator Controls BLM",9626.17,9626.17,9626.17,9626.17,"2G",1,"Hamid Shoaee",null,9626.17]
[1,1.04,"1.04.02.17","Undulator Management",7754.28,0,0,99962.42,"2G",0,"Hamid Shoaee",99962.42]
[1,1.04,"1.04.02.20","Undulator MPS",26731.53,0,0,217550.44,"2G",0,"Hamid Shoaee",null,217550.44]
[1,1.04,"1.04.02.21","Undulator Controls -Timing",60824.9,0,0,156333.81,"2G",0,"Hamid Shoaee",null,156333.81]
[1,1.04,"1.04.02.22","Undulator Controls - BPM",103639.25,97518.43,97518.43,221927.42,"2G",0.4394,"Hamid Shoaee",null,221927.42]
[1,1.04,"1.04.02.23","Undulator Controls - Vacuum",21934.93,7965.14,7965.14,224092.92,"2G",0.0355,"Hamid Shoaee",null,224092.92]
[1,1.04,"1.04.02.24","Undulator Controls - ADS System",0,0,0,6682.88,"2G",0,"Hamid Shoaee",null,6682.88]
[1,1.04,"1.04.03.01","UND Magnet & Support - Mgmt and Integration",3734.18,3734.18,3734.18,3734.18,"4A",1,"Geoff Pile",null,3734.18]
[1,1.04,"1.04.03.02","First Prototype Undulator & Mfg Plan",-0.02,-0.02,-0.02,-0.02,"4A",1,"Geoff Pile",null,-0.02]
[1,1.04,"1.04.03.03.01","Ti Strongback (LLP)",3500860.76,3500860.76,3500860.76,3500860.76,"4A",1,"Geoff Pile",null,3500860.76]
[1,1.04,"1.04.03.03.02","Magnet Blocks (LLP)",1003209.42,1003209.42,1003209.42,1003209.42,"4A",1,"Geoff Pile",null,1003209.42]
[1,1.04,"1.04.03.03.03","Magnet Poles (LLP)",802010.25,802010.25,802010.25,802010.25,"4A",1,"Geoff Pile",null,802010.25]
[1,1.04,"1.04.03.03.04","Magnet Assembly & Supports - 1st Articles",2922439.53,2911541.49,2911541.49,3011338.33,"4A",0.9669,"Geoff Pile",null,3011338.33]
[1,1.04,"1.04.03.03.05","Magnetic Measurement (ANL)",244982.22,244982.22,244982.22,255501.16,"4A",0.9588,"Geoff Pile",null,255501.16]
[1,1.04,"1.04.03.03.06","Integrated Single-Undulator Module Test",732994.25,700527.39,700527.39,887211.83,"4A",0.7896,"Geoff Pile",null,887211.83]
[1,1.04,"1.04.03.04.01","Production Undulator Assembly - Vendor A",1092156.89,1091565.01,1091565.01,1094968.32,"4A",0.9969,"Geoff Pile",null,1094968.32]
[1,1.04,"1.04.03.04.02","Production Undulator Assembly - Vendor B",456972.64,456972.64,456972.64,456972.64,"4A",1,"Geoff Pile",null,456972.64]
[1,1.04,"1.04.03.04.03","Production Support/Mover Fabrication/Assembly",2434181.35,2126380.81,2126380.81,2524252.69,"4A",0.8424,"Geoff Pile",null,2524252.69]
[1,1.04,"1.04.03.04.04","Mu Metal Shield",129629.65,129629.65,129629.65,129629.65,"4A",1,"Geoff Pile",null,129629.65]
[1,1.04,"1.04.03.05.01","Quadrupole Magnets",577136.89,541640.15,541640.15,792373.39,"4A",0.6836,"Geoff Pile",57835.11,734538.28]
[1,1.04,"1.04.03.05.02","Quadrupole Power Supplies",0,0,0,0,"4A",0,"Geoff Pile"]
[1,1.04,"1.04.03.05.03","Quadrupole Stages & Stands",85318.68,85318.68,85318.68,85318.68,"4A",1,"Geoff Pile",null,85318.68]
[1,1.04,"1.04.03.05.04","Quadrupole Cables",0,0,0,0,"4A",0,"Geoff Pile"]
[1,1.04,"1.04.03.06.01","Undulator MMF Setup",3807248.96,3807248.96,3807248.96,3807248.96,"2A",1,"Jose Chan",null,3807248.96]
[1,1.04,"1.04.03.06.02","Fiducialization and Magnetic Measurements (F/MM)",2005785.38,1958057.61,1958057.61,3111504.29,"2A",0.6293,"Jose Chan",null,3111504.29]
[1,1.04,"1.04.03.06.03","Undulator Monitoring",2034946.02,1872866.99,1872866.99,2447563.65,"2A",0.7652,"Jose Chan",251432.08,2196131.57]
[1,1.04,"1.04.03.08.01","Fixed Sppt Mgmt & Integration",102720,102720,102720,102720,"4A",1,"Geoff Pile",null,102720]
[1,1.04,"1.04.03.08.02","Fixed Support Design",839743.87,804744.94,804744.94,841836.93,"4A",0.9559,"Geoff Pile",null,841836.93]
[1,1.04,"1.04.03.08.03","Stabilized Girder Assemblies",0,0,0,0,"4A",0,"Geoff Pile"]
[1,1.04,"1.04.03.08.05","Thermometry",11041.36,4762.19,4762.19,17320.54,"4A",0.2749,"Geoff Pile",null,17320.54]
[1,1.04,"1.04.03.08.07","Earthquake Bracing",5757.31,0,0,24180.7,"4A",0,"Geoff Pile",null,24180.7]
[1,1.04,"1.04.03.08.08","Controls and Software",0,0,0,0,"4A",0,"Geoff Pile"]
[1,1.04,"1.04.04.02.01","Prototype Chamber Weldment",42747.81,42747.81,42747.81,42747.81,"4A",1,"Geoff Pile",null,42747.81]
[1,1.04,"1.04.04.02.02","Production Chamber Weldment",1098271.5,739040.12,739040.12,1246503.27,"4A",0.5929,"Geoff Pile",null,1246503.27]
[1,1.04,"1.04.04.02.03","Prototype Aluminum Chamber",1204394.7,1204394.7,1204394.7,1204394.7,"4A",1,"Geoff Pile",null,1204394.7]
[1,1.04,"1.04.04.03.01","Prototype Bellows Module",161430.85,161430.85,161430.85,161430.85,"4A",1,"Geoff Pile",null,161430.85]
[1,1.04,"1.04.04.03.02","Production Bellows Module",92682.96,75658.7,75658.7,127643.51,"4A",0.5927,"Geoff Pile",null,127643.51]
[1,1.04,"1.04.04.04","Single Undulator Test (SUT) Vacuum",110405.73,110405.73,110405.73,110405.73,"4A",1,"Geoff Pile",null,110405.73]
[1,1.04,"1.04.04.05","Short Diagnostic Break (SDB) Assembly",102266.74,77762.82,77762.82,150251.28,"4A",0.5176,"Geoff Pile",null,150251.28]
[1,1.04,"1.04.04.06","Long Diagnostic Break (LDB) Assembly",170290.5,146570.13,146570.13,216861.2,"4A",0.6759,"Geoff Pile",null,216861.2]
[1,1.04,"1.04.04.07","Entrance Section Assembly",3563.47,3563.47,3563.47,3563.47,"4A",1,"Geoff Pile",null,3563.47]
[1,1.04,"1.04.04.08","Exit Section Assembly",2482.67,2482.67,2482.67,2482.67,"4A",1,"Geoff Pile",null,2482.67]
[1,1.04,"1.04.04.09","Baking System",100060.56,100060.56,100060.56,100060.56,"4A",1,"Geoff Pile",null,100060.56]
[1,1.04,"1.04.05.02.01","EBXPD Test Station",119863.37,119863.37,119863.37,119863.37,"4A",1,"Geoff Pile",null,119863.37]
[1,1.04,"1.04.05.02.02","EBXPD Vacuum Chamber",1093.92,1093.92,1093.92,1093.92,"4A",1,"Geoff Pile",null,1093.92]
[1,1.04,"1.04.05.02.03","Positioning Mechanism",78527.63,78527.63,78527.63,78527.63,"4A",1,"Geoff Pile",null,78527.63]
[1,1.04,"1.04.05.02.04","Scanning wire assembly (ULD-SWA)",119928.41,119928.41,119928.41,119928.41,"4A",1,"Geoff Pile",null,119928.41]
[1,1.04,"1.04.05.02.05","Optical transition radiation imaging assembly",115777.95,115777.95,115777.95,115777.95,"4A",1,"Geoff Pile",null,115777.95]
[1,1.04,"1.04.05.02.09","ULD Design & Integration",0,0,0,0,"4A",0,"Geoff Pile"]
[1,1.04,"1.04.05.04.01","Prototype Construction and Testing",68185.81,68185.81,68185.81,68185.81,"4A",1,"Geoff Pile",null,68185.81]
[1,1.04,"1.04.05.04.03","Upstream corrector / separator",0,0,0,0,"4A",0,"Geoff Pile"]
[1,1.04,"1.04.05.04.04","Optical Diffraction radiation imaging assembly (",0,0,0,0,"4A",0,"Geoff Pile"]
[1,1.04,"1.04.05.04.05","X-ray High Resolution monochromator assembly (EO",0,0,0,0,"4A",0,"Geoff Pile"]
[1,1.04,"1.04.05.04.06","X-ray Imaging High Resolution detector assembly",0,0,0,0,"4A",0,"Geoff Pile"]
[1,1.04,"1.04.05.04.07","EOU Design and Integration",0,0,0,0,"4A",0,"Geoff Pile"]
[1,1.04,"1.04.05.05.01","X-Band Cavity BPM Development",1178840.69,1178840.69,1178840.69,1178840.69,"4A",1,"Geoff Pile",null,1178840.69]
[1,1.04,"1.04.05.05.02","X-Band Receiver Development",411221.78,411221.78,411221.78,411221.78,"4A",1,"Geoff Pile",null,411221.78]
[1,1.04,"1.04.05.05.03","X-Band BPM Production",770151.01,531663.93,531663.93,1754866.89,"4A",0.303,"Geoff Pile",71842.79,1683024.1]
[1,1.04,"1.04.05.06","Beam Finder Wire",902456.45,747548.72,747548.72,974152.53,"4A",0.7674,"Geoff Pile",null,974152.53]
[1,1.04,"1.04.05.07","Charge Monitor (CM)",0,0,0,0,"4A",0,"Geoff Pile"]
[1,1.04,"1.04.05.08","Beam Loss Monitoring",155977.9,155977.9,155977.9,436715.49,"4A",0.3572,"Geoff Pile",null,436715.49]
[1,1.04,"1.04.05.09","Radiation Detection Monitor (RDM)",0,0,0,0,"4A",0,"Geoff Pile"]
[1,1.04,"1.04.05.10","SIngle Undulator Test (SUT) Diagnostics",77162.38,77162.38,77162.38,77162.38,"4A",1,"Geoff Pile",null,77162.38]
[1,1.04,"1.04.05.11","Supplemental Shielding",0,0,0,0,"4A",0,"Geoff Pile"]
[1,1.04,"1.04.06.01.01","Undulator System",0,0,0,0,"2A",0,"Jose Chan"]
[1,1.04,"1.04.06.02","Control System Installation and Alignment",8421.82,8421.82,8421.82,8421.82,"2A",1,"Jose Chan",null,8421.82]
[1,1.04,"1.04.06.04","Vacuum System Installation and Alignment",57876.73,57876.73,57876.73,57876.73,"4A",1,"Geoff Pile",null,57876.73]
[1,1.04,"1.04.06.05","Diagnostics System Installation and Alignment",0,0,0,0,"2A",0,"Jose Chan"]
[1,1.04,"1.04.06.06","Undulator System Installation - 2008",51897.7,51897.7,51897.7,1959006.54,"2A",0.0265,"Jose Chan",null,1959006.54]
[1,1.05,"1.05.01.01.01","XTOD Management - Technical",3249830.5,3203786.08,3203786.08,3673947.63,"5A",0.872,"Donn McMahon",470161.55,3203786.08]
[1,1.05,"1.05.01.01.02","LLNL Project Support",1768128.56,1753223.15,1753223.15,2112589.44,"5A",0.8299,"Donn McMahon",308722.35,1803867.09]
[1,1.05,"1.05.01.01.03","Commissioning Coordinator",69189.73,69189.73,69189.73,69189.73,"5A",1,"Donn McMahon",null,69189.73]
[1,1.05,"1.05.02.01","XTOD Controls",2564093.47,2376780.22,2376780.22,3983678.43,"5C",0.5966,"Donn McMahon",916879.5,3066798.93]
[1,1.05,"1.05.02.02","Motor Controls",278106.55,278106.55,278106.55,278106.55,"2H",1,"Gunter Haller",null,278106.55]
[1,1.05,"1.05.02.03","Controls - Vacuum",1481.71,1481.71,1481.71,1481.71,"2H",1,"Gunter Haller",null,1481.71]
[1,1.05,"1.05.02.04","Femto Controls",0,0,0,0,"2H",0,"Gunter Haller"]
[1,1.05,"1.05.02.05","Controls Procurement",0,0,0,0,"2H",0,"Gunter Haller"]
[1,1.05,"1.05.03.01","Vacuum Systems Engineering",605275.11,579086.21,579086.21,934522.35,"5A",0.6197,"Donn McMahon",221296.18,713226.17]
[1,1.05,"1.05.03.02","Mech/Vac Front End",484669.46,462870.18,462870.18,1341492.58,"5A",0.345,"Donn McMahon",null,1341492.58]
[1,1.05,"1.05.03.03.01","Mech/Vac Near Hall",122974.54,122974.54,122974.54,471680.21,"5A",0.2607,"Donn McMahon",null,471680.21]
[1,1.05,"1.05.03.04","Mech/Vac Tunnel",456189.93,456189.93,456189.93,992991.61,"5A",0.4594,"Donn McMahon",170764.28,822227.33]
[1,1.05,"1.05.03.05","Mech/Vac Far Hall",0,0,0,100158.25,"5A",0,"Donn McMahon",null,100158.25]
[1,1.05,"1.05.04.02.01","Fast Valve",0,0,0,0,"5A",0,"Donn McMahon"]
[1,1.05,"1.05.04.02.02","Fixed Mask",188652.15,187633.39,187633.39,203485.63,"5A",0.9221,"Donn McMahon",null,203485.63]
[1,1.05,"1.05.04.02.03","Slit/Collimators",456785.59,447185.59,447185.59,505665.31,"5A",0.8844,"Donn McMahon",null,505665.31]
[1,1.05,"1.05.04.02.05","Gas/Solid Attenuator",2898617.86,2869792.39,2869792.39,3242741.36,"5A",0.885,"Donn McMahon",60885,3181856.36]
[1,1.05,"1.05.04.02.06","TTF Damage Experiment",594425.19,594425.19,594425.19,594425.19,"5A",1,"Donn McMahon",null,594425.19]
[1,1.05,"1.05.04.02.07","FEL Offset Mirrors",2419089.68,2205425.84,2205425.84,3359517.31,"5A",0.6565,"Donn McMahon",50290.91,3309226.4]
[1,1.05,"1.05.04.02.08","Solid Attenuator",8344.4,8344.4,8344.4,8344.4,"5A",1,"Donn McMahon",null,8344.4]
[1,1.05,"1.05.05.02.01","Wave Model",524725.8,524725.8,524725.8,524725.8,"5A",1,"Donn McMahon",null,524725.8]
[1,1.05,"1.05.05.02.02","Monte Carlo Model",293290.73,293290.73,293290.73,293290.73,"5A",1,"Donn McMahon",null,293290.73]
[1,1.05,"1.05.05.02.03","Beam Simulation",393536.44,393536.44,393536.44,393536.44,"5A",1,"Donn McMahon",null,393536.44]
[1,1.05,"1.05.05.03.01","Direct Imager",854425.37,825431.33,825431.33,1074055.08,"5A",0.7685,"Donn McMahon",null,1074055.08]
[1,1.05,"1.05.05.03.02","Indirect Imager",334947.08,334947.08,334947.08,334947.08,"5A",1,"Donn McMahon",null,334947.08]
[1,1.05,"1.05.05.03.06","Gas Detector",1424036.96,1379365.1,1379365.1,1502041.61,"5A",0.9183,"Donn McMahon",null,1502041.61]
[1,1.05,"1.05.05.03.07","NEH Imager",0,0,0,0,"5A",0,"Donn McMahon"]
[1,1.05,"1.05.05.03.08","FEH Imager",0,0,0,0,"5A",0,"Donn McMahon"]
[1,1.05,"1.05.05.04.01","Commission Diagnostic Tanks",0,0,0,0,"5A",0,"Donn McMahon"]
[1,1.05,"1.05.05.04.02","Total Energy Measurement",2643234.13,2561597.56,2561597.56,2840424.17,"5A",0.9018,"Donn McMahon",null,2840424.17]
[1,1.05,"1.05.05.04.04","Soft X-Ray Imager System",142833.21,142833.21,142833.21,142833.21,"5A",1,"Donn McMahon",null,142833.21]
[1,1.05,"1.05.05.04.05","Popup Cameras",105762.33,78192.86,78192.86,673185.37,"5A",0.1162,"Donn McMahon",null,673185.37]
[1,1.05,"1.05.05.04.06","K Measurement System",53549.96,30039.36,30039.36,383549.78,"5A",0.0783,"Donn McMahon",68640,314909.78]
[1,1.05,"1.05.06.01","Front End Enclosure Install",0,0,0,0,"5A",0,"Donn McMahon"]
[1,1.05,"1.05.06.01.01","FEE Cable Installation",19980.96,8103.86,8103.86,255337.62,"5A",0.0317,"Donn McMahon",null,255337.62]
[1,1.05,"1.05.06.01.02","FEE Install - All, exclg. cable install.",0,0,0,1051843.15,"5A",0,"Donn McMahon",null,1051843.15]
[1,1.05,"1.05.06.02","Near Hall Install",0,0,0,166220.89,"5A",0,"Donn McMahon",null,166220.89]
[1,1.05,"1.05.06.03","Tunnel Install",0,0,0,200488.43,"5A",0,"Donn McMahon",null,200488.43]
[1,1.05,"1.05.06.04","Far Hall Install",0,0,0,127616.01,"5A",0,"Donn McMahon",null,127616.01]
[1,1.05,"1.05.06.05","Electron Dump Enclosure Install",0,0,0,15188.15,"5A",0,"Donn McMahon",null,15188.15]
[1,1.06,"1.06.01.01","Management",905753.86,891739.97,891739.97,1048146.71,"6A",0.8508,"Stefan Moeller",156406.74,891739.97]
[1,1.06,"1.06.01.02","SSRL Physics",294960.8,294960.8,294960.8,294960.8,"6A",1,"Stefan Moeller",null,294960.8]
[1,1.06,"1.06.02.01","Controls Management",126828.81,113584.55,113584.55,574649.21,"2H",0.1977,"Gunter Haller",461064.66,113584.55]
[1,1.06,"1.06.02.02","Network - Closed to BCWP",98.3,98.3,98.3,98.3,"2H",1,"Gunter Haller",null,98.3]
[1,1.06,"1.06.02.03","PC Support - AP - Closed to BCWP",6257.84,6257.84,6257.84,6257.84,"2H",1,"Gunter Haller",null,6257.84]
[1,1.06,"1.06.02.04","Beamline Controls - AP - Closed to BCWP",127.14,127.14,127.14,127.14,"2H",1,"Gunter Haller",null,127.14]
[1,1.06,"1.06.02.05.01","FEE X-Ray PPS - Closed to BCWP",27118.06,27118.06,27118.06,27118.06,"2H",1,"Gunter Haller",null,27118.06]
[1,1.06,"1.06.02.05.02","Near Hall X-Ray PPS",0,0,0,0,"2H",0,"Gunter Haller"]
[1,1.06,"1.06.02.05.03","Tunnel X-Ray PPS",0,0,0,0,"2H",0,"Gunter Haller"]
[1,1.06,"1.06.02.05.04","Far Hall X-Ray PPS",0,0,0,0,"2H",0,"Gunter Haller"]
[1,1.06,"1.06.02.06.01","FEE X-Ray MPS - Closed to BCWP",1337.96,1337.96,1337.96,1337.96,"2H",1,"Gunter Haller",null,1337.96]
[1,1.06,"1.06.02.06.02","Near Hall X-Ray MPS",0,0,0,0,"2H",0,"Gunter Haller"]
[1,1.06,"1.06.02.06.03","Tunnel X-Ray MPS",0,0,0,0,"2H",0,"Gunter Haller"]
[1,1.06,"1.06.02.06.04","Far Hall X-Ray MPS",0,0,0,0,"2H",0,"Gunter Haller"]
[1,1.06,"1.06.02.07.01","AMOS Requirements, Design, & Test Setup",290590.01,288407.63,288407.63,291844.86,"2H",0.9882,"Gunter Haller",null,291844.86]
[1,1.06,"1.06.02.07.02","X-Ray Flourescence Detector",0,0,0,0,"2H",0,"Gunter Haller"]
[1,1.06,"1.06.02.07.03","Ion Imaging & Electron TOF",0,0,0,0,"2H",0,"Gunter Haller"]
[1,1.06,"1.06.02.07.04","Sample Source",0,0,0,0,"2H",0,"Gunter Haller"]
[1,1.06,"1.06.02.07.05","Vacuum Controls & Mechanical Exp 1",0,0,0,0,"2H",0,"Gunter Haller"]
[1,1.06,"1.06.02.07.06","Refocus Optics",0,0,0,0,"2H",0,"Gunter Haller"]
[1,1.06,"1.06.02.07.07","Development Hardware & Software",428342.62,391125.69,391125.69,631174.84,"2H",0.6197,"Gunter Haller",null,631174.84]
[1,1.06,"1.06.02.07.08","Beam Viewing System (Ph.1)",0,0,0,143791.52,"2H",0,"Gunter Haller",null,143791.52]
[1,1.06,"1.06.02.07.09","Beam Viewing System (Ph.2)",0,0,0,124056.02,"2H",0,"Gunter Haller",null,124056.02]
[1,1.06,"1.06.02.07.12","Differential Pumping",0,0,0,123226.69,"2H",0,"Gunter Haller",null,123226.69]
[1,1.06,"1.06.02.07.14","Temperature Monitoring",0,0,0,28989.11,"2H",0,"Gunter Haller",null,28989.11]
[1,1.06,"1.06.02.07.15","Gas Storage & Delivery System",0,0,0,24640.89,"2H",0,"Gunter Haller",null,24640.89]
[1,1.06,"1.06.02.07.16","High Field Physics Chamber",0,0,0,751904.16,"2H",0,"Gunter Haller",null,751904.16]
[1,1.06,"1.06.02.07.17","Diagnostics Chamber",0,0,0,231153.53,"2H",0,"Gunter Haller",null,231153.53]
[1,1.06,"1.06.02.07.18","Total Power Measurement",0,0,0,84176.94,"2H",0,"Gunter Haller",null,84176.94]
[1,1.06,"1.06.02.08.01","AMO Particle Imaging Controls",0,0,0,85044.02,"2H",0,"Gunter Haller",null,85044.02]
[1,1.06,"1.06.02.08.02","AMO Particle Imaging Software",0,0,0,60987.99,"2H",0,"Gunter Haller",null,60987.99]
[1,1.06,"1.06.02.09","Controls Management - Closed to BCWP",18.88,18.88,18.88,18.88,"2H",1,"Gunter Haller",null,18.88]
[1,1.06,"1.06.02.10.01","Network",200714.87,200714.87,200714.87,1329241.69,"2H",0.151,"Gunter Haller",null,1329241.69]
[1,1.06,"1.06.02.10.02","Machine Protection System",1559.34,0,0,67617.41,"2H",0,"Gunter Haller",null,67617.41]
[1,1.06,"1.06.02.10.03","Personnel Protection System",91967.35,89905.05,89905.05,545734.17,"2H",0.1647,"Gunter Haller",null,545734.17]
[1,1.06,"1.06.02.10.04","Laser Safety System",7848.82,211.24,211.24,174100.91,"2H",0.0012,"Gunter Haller",null,174100.91]
[1,1.06,"1.06.02.10.05","User Safeguards",593.09,0,0,126799.64,"2H",0,"Gunter Haller",null,126799.64]
[1,1.06,"1.06.02.10.06","Timing System",0,0,0,106889.78,"2H",0,"Gunter Haller",null,106889.78]
[1,1.06,"1.06.02.10.07","Data Management",0,0,0,801240.4,"2H",0,"Gunter Haller",null,801240.4]
[1,1.06,"1.06.02.10.08","Global Cabling & Racks",21527,11204.32,11204.32,291047.33,"2H",0.0385,"Gunter Haller",null,291047.33]
[1,1.06,"1.06.02.10.09","Laser Timing",0,0,0,930819.84,"2H",0,"Gunter Haller",null,930819.84]
[1,1.06,"1.06.02.10.10","Experimental High Level Applications",0,0,0,0,"2H",0,"Gunter Haller"]
[1,1.06,"1.06.02.10.11","Common Hutch Controls",0,0,0,366682.91,"2H",0,"Gunter Haller",null,366682.91]
[1,1.06,"1.06.02.10.12","Data Acquisition (DAQ)",2756.74,2756.74,2756.74,413398.53,"2H",0.0067,"Gunter Haller",null,413398.53]
[1,1.06,"1.06.02.10.13","Archives",0,0,0,84268.93,"2H",0,"Gunter Haller",null,84268.93]
[1,1.06,"1.06.02.10.14","Data Retrieval & Analysis",0,0,0,118333.29,"2H",0,"Gunter Haller",null,118333.29]
[1,1.06,"1.06.02.11","Laser Controls",0,0,0,189047.91,"2H",0,"Gunter Haller",null,189047.91]
[1,1.06,"1.06.02.12","K Measurement Controls Spectromentr",0,0,0,0,"2H",0,"Gunter Haller"]
[1,1.06,"1.06.03.02.02","Hardware - Vacuum",0,0,0,0,"6A",0,"Stefan Moeller"]
[1,1.06,"1.06.04.01","XES Laser",6020.74,0,0,457431.82,"2L",0,"Bill White",null,457431.82]
[1,1.06,"1.06.04.02","Laser Diagnostics",2510.85,0,0,102202.31,"2L",0,"Bill White",null,102202.31]
[1,1.06,"1.06.04.03","Laser Optical Transport",6293.09,0,0,371605.5,"2L",0,"Bill White",null,371605.5]
[1,1.06,"1.06.04.04","Laser Safety",6683.95,6683.95,6683.95,50432.15,"2L",0.1325,"Bill White",null,50432.15]
[1,1.06,"1.06.05.01","Beam Imaging",3590.4,3590.4,3590.4,3590.4,"6A",1,"Stefan Moeller",null,3590.4]
[1,1.06,"1.06.05.04.01","Detector Management",195605.44,188905.68,188905.68,245518.64,"6A",0.7694,"Stefan Moeller",56612.96,188905.68]
[1,1.06,"1.06.05.04.02","Streak Camera - LBL",0,0,0,0,"6A",0,"Stefan Moeller"]
[1,1.06,"1.06.06.01","Front End Install",0,0,0,43755.01,"6A",0,"Stefan Moeller",null,43755.01]
[1,1.06,"1.06.06.02","Near Hall Install",0,0,0,0,"6A",0,"Stefan Moeller"]
[1,1.06,"1.06.06.02.01","Near Hall Install Mischarges (Closed)",392.16,392.16,392.16,392.16,"6A",1,"Stefan Moeller",null,392.16]
[1,1.06,"1.06.06.02.02","NEH Install - Network Cable",17845.58,9972.73,9972.73,328606.34,"6A",0.0303,"Stefan Moeller",null,328606.34]
[1,1.06,"1.06.06.02.03","Near Hall Install Laser",0,0,0,0,"6A",0,"Stefan Moeller"]
[1,1.06,"1.06.06.02.04","Near Hall Install Atomic Physics Exp.",0,0,0,279849.37,"6A",0,"Stefan Moeller",null,279849.37]
[1,1.06,"1.06.06.02.05","Near Hall Install Atomic Physics",0,0,0,150323.66,"6A",0,"Stefan Moeller",null,150323.66]
[1,1.06,"1.06.06.02.06","Near Hall Install PPS System",0,0,0,237808.16,"6A",0,"Stefan Moeller",null,237808.16]
[1,1.06,"1.06.06.02.07","Near Hall Install Laser PPS",0,0,0,0,"6A",0,"Stefan Moeller"]
[1,1.06,"1.06.06.02.09","Near Hall Install Timing System",0,0,0,139528.65,"6A",0,"Stefan Moeller",null,139528.65]
[1,1.06,"1.06.06.02.99","Near Hall Install - Other",0,0,0,334043.34,"6A",0,"Stefan Moeller",null,334043.34]
[1,1.06,"1.06.06.03","Tunnel Install",0,0,0,42562.31,"6A",0,"Stefan Moeller",null,42562.31]
[1,1.06,"1.06.06.04","Far Hall Install",0,0,0,167290.53,"6A",0,"Stefan Moeller",null,167290.53]
[1,1.06,"1.06.06.04.01","Far Hall Install Global Controls",0,0,0,0,"6A",0,"Stefan Moeller"]
[1,1.06,"1.06.06.04.02","Far Hall Install Mech/Vac",0,0,0,0,"6A",0,"Stefan Moeller"]
[1,1.06,"1.06.06.04.04","Far Hall Install Detectors",0,0,0,0,"6A",0,"Stefan Moeller"]
[1,1.06,"1.06.06.04.05","Far Hall Install PPS System",0,0,0,0,"6A",0,"Stefan Moeller"]
[1,1.06,"1.06.06.05","Electron Dump Enclosure Install",0,0,0,43941.4,"6A",0,"Stefan Moeller",null,43941.4]
[1,1.06,"1.06.07.01","AP Management & Design",769396.16,739539.38,739539.38,1089026.94,"6A",0.6791,"Stefan Moeller",51672.83,1037354.11]
[1,1.06,"1.06.07.02","AP High Field Physics Exp.",0,0,0,1632851.55,"6A",0,"Stefan Moeller",null,1632851.55]
[1,1.06,"1.06.07.03","AP Refocus Optics",0,0,0,457481.09,"6A",0,"Stefan Moeller",null,457481.09]
[1,1.06,"1.06.07.04","AP Diagnostics",0,0,0,569288.38,"6A",0,"Stefan Moeller",null,569288.38]
[1,1.06,"1.06.08.01","K Measurement Crystals",0,0,0,26826.85,"6A",0,"Stefan Moeller",null,26826.85]
[1,1.06,"1.06.09.01","PPS Stoppers",175482.39,147114.92,147114.92,656669.89,"6A",0.224,"Stefan Moeller",null,656669.89]
[1,1.06,"1.06.09.02","PPS Shielding",16243.68,12548.87,12548.87,220690.5,"6A",0.0569,"Stefan Moeller",null,220690.5]
[1,1.06,"1.06.09.03","NEH Hutch Doors",36132.54,20369.91,20369.91,120462.62,"6A",0.1691,"Stefan Moeller",null,120462.62]
[1,1.09,"1.09.01.01","Management",3534145.62,3501069.31,3501069.31,3831014.01,"9A",0.9139,"David Saenz",2014591.45,1816422.56]
[1,1.09,"1.09.01.02","CF Engineering",3921956.28,3816406.22,3816406.22,4902412.94,"9A",0.7785,"David Saenz",2764714.89,1900926.09,null,236771.96]
[1,1.09,"1.09.01.03","Construction Management & AE Support",13842980.52,13668173.58,13668173.58,17781748.21,"9A",0.7687,"David Saenz",283946.79,15242801.42,null,2255000]
[1,1.09,"1.09.01.04.01","Mechanical Design Title 1 (Linac not included)",77898.13,77898.13,77898.13,77898.13,"9A",1,"David Saenz",null,77898.13]
[1,1.09,"1.09.01.04.02","Mechanical Design T1 Linac Facilities",28110.58,28110.58,28110.58,28110.58,"9A",1,"David Saenz",12229.54,15881.04]
[1,1.09,"1.09.01.04.03","Mechanical Design Title 2 (Linac not included)",83103.87,83103.87,83103.87,83103.87,"9A",1,"David Saenz",33580.56,49523.31]
[1,1.09,"1.09.01.04.04","Mechanical Design T2 Linac Facilities",227078.11,227078.11,227078.11,227078.11,"9A",1,"David Saenz",208609.25,18468.86]
[1,1.09,"1.09.01.04.05","Mechanical Design Title 3 Linac Facility",16853.22,16853.22,16853.22,16853.22,"9A",1,"David Saenz",null,16853.22]
[1,1.09,"1.09.01.04.06","Mechanical Design Title 3 - RSY through CLOC",0,0,0,0,"9A",0,"David Saenz"]
[1,1.09,"1.09.01.05.01","CEF Engineering Title 1(Linac Not Included)",42767.51,42767.51,42767.51,42767.51,"9A",1,"David Saenz",null,42767.51]
[1,1.09,"1.09.01.05.02","CEF Engineering Title 1 Linac Facility",31493.64,31493.64,31493.64,31493.64,"9A",1,"David Saenz",null,31493.64]
[1,1.09,"1.09.01.05.03","CEF Engineering Title 2 (Linac Not Included)",119105.72,119105.72,119105.72,119105.72,"9A",1,"David Saenz",83808.25,35297.47]
[1,1.09,"1.09.01.05.04","CEF Design Linac Facility Title 2",56517.41,56517.41,56517.41,56517.41,"9A",1,"David Saenz",null,56517.41]
[1,1.09,"1.09.02.02.01","Title 1 Design",293543.08,293543.08,293543.08,293543.08,"9A",1,"David Saenz",null,293543.08]
[1,1.09,"1.09.02.02.02","Title 2 Design",5149383.65,5149383.65,5149383.65,5149383.65,"9A",1,"David Saenz",null,5149383.65]
[1,1.09,"1.09.02.03.01","Title 1 Design (Sector 20)",0,0,0,0,"9A",0,"David Saenz"]
[1,1.09,"1.09.02.03.02","Title 2 Design (Sector 20)",84298.35,84298.35,84298.35,84298.35,"9A",1,"David Saenz",null,84298.35]
[1,1.09,"1.09.02.03.03","Title 1 Design (MMF)",37895,37895,37895,37895,"9A",1,"David Saenz",null,37895]
[1,1.09,"1.09.02.03.04","Title 2 Design (MMF)",142944.16,142944.16,142944.16,142944.16,"9A",1,"David Saenz",null,142944.16]
[1,1.09,"1.09.03.01.01","S20 - Site Preparation/General Requirements",581817.54,581817.54,581817.54,581817.54,"9A",1,"David Saenz",null,581817.54]
[1,1.09,"1.09.03.01.02","S20 - Site Construction",139895.85,139895.85,139895.85,139895.85,"9A",1,"David Saenz",null,139895.85]
[1,1.09,"1.09.03.01.03","S20 - Concrete",146007.37,146007.37,146007.37,146007.37,"9A",1,"David Saenz",null,146007.37]
[1,1.09,"1.09.03.01.04","S20 - Masonry",269.59,269.59,269.59,269.59,"9A",1,"David Saenz",null,269.59]
[1,1.09,"1.09.03.01.05","S20 - Metals",234436.1,234436.1,234436.1,234436.1,"9A",1,"David Saenz",null,234436.1]
[1,1.09,"1.09.03.01.06","S20 - Woods & Plastics",14512.53,14512.53,14512.53,14512.53,"9A",1,"David Saenz",null,14512.53]
[1,1.09,"1.09.03.01.07","S20 - Thermal & Moisture Protection",133554.57,133554.57,133554.57,133554.57,"9A",1,"David Saenz",null,133554.57]
[1,1.09,"1.09.03.01.08","S20 - Doors & Windows",36436.19,36436.19,36436.19,36436.19,"9A",1,"David Saenz",null,36436.19]
[1,1.09,"1.09.03.01.09","S20 - Finishes",115363.92,115363.92,115363.92,115363.92,"9A",1,"David Saenz",null,115363.92]
[1,1.09,"1.09.03.01.10","S20 - Specialtieis",588.36,588.36,588.36,588.36,"9A",1,"David Saenz",null,588.36]
[1,1.09,"1.09.03.01.14","S20 - Conveying Systems",3612.77,3612.77,3612.77,3612.77,"9A",1,"David Saenz",null,3612.77]
[1,1.09,"1.09.03.01.15","S20 - Mechanical",872997.57,872997.57,872997.57,872997.57,"9A",1,"David Saenz",null,872997.57]
[1,1.09,"1.09.03.01.16","S20 - Electrical",568755.55,568755.55,568755.55,568755.55,"9A",1,"David Saenz",null,568755.55]
[1,1.09,"1.09.03.01.20","S20 - Project Close Out",279114.09,279114.09,279114.09,279114.09,"9A",1,"David Saenz",null,279114.09]
[1,1.09,"1.09.03.02.01","MMF - Site Preparation/General Requirements",442550.24,442550.24,442550.24,442550.24,"9A",1,"David Saenz",null,442550.24]
[1,1.09,"1.09.03.02.02","MMF - Site Construction",95594.65,95594.65,95594.65,95594.65,"9A",1,"David Saenz",null,95594.65]
[1,1.09,"1.09.03.02.03","MMF - Concrete",199016.29,199016.29,199016.29,199016.29,"9A",1,"David Saenz",null,199016.29]
[1,1.09,"1.09.03.02.05","MMF - Metals",142754.22,142754.22,142754.22,142754.22,"9A",1,"David Saenz",null,142754.22]
[1,1.09,"1.09.03.02.06","MMF - Woods & Plastics",11811.37,11811.37,11811.37,11811.37,"9A",1,"David Saenz",null,11811.37]
[1,1.09,"1.09.03.02.07","MMF - Thermal & Moisture Protection",70624.32,70624.32,70624.32,70624.32,"9A",1,"David Saenz",null,70624.32]
[1,1.09,"1.09.03.02.08","MMF - Doors & Windows",28955.83,28955.83,28955.83,28955.83,"9A",1,"David Saenz",null,28955.83]
[1,1.09,"1.09.03.02.09","MMF - Finishes",178005.57,178005.57,178005.57,178005.57,"9A",1,"David Saenz",null,178005.57]
[1,1.09,"1.09.03.02.10","MMF - Specialities",1044.5,1044.5,1044.5,1044.5,"9A",1,"David Saenz",null,1044.5]
[1,1.09,"1.09.03.02.13",null,306.09,306.09,306.09,306.09,"9A",1,"David Saenz",null,306.09]
[1,1.09,"1.09.03.02.14","MMF - Conveying Systems",241299.09,241299.09,241299.09,241299.09,"9A",1,"David Saenz",null,241299.09]
[1,1.09,"1.09.03.02.15","MMF - Mechanical",1025424.04,1025424.04,1025424.04,1025424.04,"9A",1,"David Saenz",null,1025424.04]
[1,1.09,"1.09.03.02.16","MMF - Electrical",804189.49,804189.49,804189.49,804189.49,"9A",1,"David Saenz",null,804189.49]
[1,1.09,"1.09.03.02.20","MMF - Project Close Out",116457.02,116457.02,116457.02,116457.02,"9A",1,"David Saenz",null,116457.02]
[1,1.09,"1.09.03.03.01","BTH West - Site Preparation",31653.77,22298.96,22298.96,38202.14,"9A",0.5837,"David Saenz",null,38202.14]
[1,1.09,"1.09.03.03.15","BTH West - Mechanical",356108.69,163202.65,163202.65,404335.2,"9A",0.4036,"David Saenz",null,241132.55,163202.65]
[1,1.09,"1.09.03.03.16","BTH West - Electrical",198337.6,89921.6,89921.6,231440,"9A",0.3885,"David Saenz",null,141518.4,89921.6]
[1,1.09,"1.09.03.03.20","BTH West - Project Close Out",11016.19,0,0,13770.24,"9A",0,"David Saenz",null,13770.24]
[1,1.09,"1.09.03.04.05","Linac - Metals",109914.85,109914.85,109914.85,109914.85,"9A",1,"David Saenz",null,109914.85]
[1,1.09,"1.09.03.04.15","LN - Mechanical",1235287.1,1235287.1,1235287.1,1235287.1,"9A",1,"David Saenz",null,1235287.1]
[1,1.09,"1.09.03.04.16","LN - Electrical",789705.01,789705.01,789705.01,1739705.01,"9A",0.4539,"David Saenz",null,1739705.01]
[1,1.09,"1.09.03.04.20","LN - Project Close Out",2662.25,2662.25,2662.25,2662.25,"9A",1,"David Saenz",null,2662.25]
[1,1.09,"1.09.03.05.01","RY - Site Preparation",589980.76,589980.76,589980.76,589980.76,"9A",1,"David Saenz",null,589980.76]
[1,1.09,"1.09.03.05.02","RY - FFTB/BSY & Site Construction",2711622.19,2693808.48,2693808.48,2756156.48,"9A",0.9774,"David Saenz",null,2756156.48]
[1,1.09,"1.09.03.05.20","RY - Project Close Out",246176.94,238720.71,238720.71,301725.82,"9A",0.7912,"David Saenz",null,301725.82]
[1,1.09,"1.09.03.06.01","PPE - General Requirements",363475,363475,363475,363475,"9A",1,"David Saenz",null,363475]
[1,1.09,"1.09.03.06.11","Pre-Purchase Equipment for Beam Path",1576072.14,1549220.8,1549220.8,1719726.8,"9A",0.9009,"David Saenz",null,170506,1549220.8]
[1,1.09,"1.09.03.07.01","SW - Site Preparation/General Requirements",1964730.81,1928221.05,1928221.05,2160058.05,"9A",0.8927,"David Saenz",null,2160058.05]
[1,1.09,"1.09.03.07.02","SW - Site Construction",6700592.85,6607635.89,6607635.89,7966210.34,"9A",0.8295,"David Saenz",null,7816210.34,null,150000]
[1,1.09,"1.09.03.07.16","SW - Electrical",850581.7,850581.7,850581.7,850581.7,"9A",1,"David Saenz",null,850581.7]
[1,1.09,"1.09.03.07.17","SW - Others (include Div 4, and 6 through 14)",0,0,0,0,"9A",0,"David Saenz"]
[1,1.09,"1.09.03.08.01","BTH - Site Preparation/General Requirements",837115.5,837115.5,837115.5,837115.5,"9A",1,"David Saenz",null,837115.5]
[1,1.09,"1.09.03.08.03","BTH - Concrete",5658698.2,5658698.2,5658698.2,5658698.2,"9A",1,"David Saenz",null,5658698.2]
[1,1.09,"1.09.03.08.05","BTH - Metals",24286.5,24286.5,24286.5,24286.5,"9A",1,"David Saenz",null,null,24286.5]
[1,1.09,"1.09.03.08.15","BTH - Mechanical",232254.11,221329,221329,293981,"9A",0.7529,"David Saenz",null,293981]
[1,1.09,"1.09.03.08.16","BTH - Electrical",1840289.99,1809824.99,1809824.99,1840289.99,"9A",0.9834,"David Saenz",null,1840289.99]
[1,1.09,"1.09.03.08.17","BTH - Others (include Div 4, and 6 through 14)",228226.8,153750,153750,246846,"9A",0.6229,"David Saenz",null,93096,153750]
[1,1.09,"1.09.03.08.20","BTH - Project Close Out",0,0,0,0,"9A",0,"David Saenz"]
[1,1.09,"1.09.03.09.03","FEE - Concrete",1298427.2,1298427.2,1298427.2,1298427.2,"9A",1,"David Saenz",null,null,1298427.2]
[1,1.09,"1.09.03.09.05","FEE - Metals",1000,1000,1000,1000,"9A",1,"David Saenz",null,null,1000]
[1,1.09,"1.09.03.09.15","FEE - Mechanical",171674.32,154348.3,154348.3,269566.3,"9A",0.5726,"David Saenz",null,115218,154348.3]
[1,1.09,"1.09.03.09.16","FEE - Electrical",181297.99,97181.1,97181.1,286444.1,"9A",0.3393,"David Saenz",null,286444.1]
[1,1.09,"1.09.03.09.17","FEE - Others (include Div 4, and 6 through 14)",60387.99,30011,30011,232018,"9A",0.1293,"David Saenz",null,202007,30011]
[1,1.09,"1.09.03.09.20","FEE - Project Close Out",0,0,0,0,"9A",0,"David Saenz"]
[1,1.09,"1.09.03.10.01","EBD - Site Preparation/General Requirements",646228.36,646228.36,646228.36,646228.36,"9A",1,"David Saenz",null,646228.36]
[1,1.09,"1.09.03.10.03","EBD - Concrete",1364485.6,1364485.6,1364485.6,1364485.6,"9A",1,"David Saenz",null,null,1364485.6]
[1,1.09,"1.09.03.10.05","EBD - Metals",39408.72,12000,12000,194268,"9A",0.0618,"David Saenz",null,182268,12000]
[1,1.09,"1.09.03.10.15","EBD - Mechanical",176564.14,157830,157830,282412,"9A",0.5589,"David Saenz",null,124582,157830]
[1,1.09,"1.09.03.10.16","EBD - Electrical",146872.86,133908.2,133908.2,220123.2,"9A",0.6083,"David Saenz",null,220123.2]
[1,1.09,"1.09.03.10.17","EBD - Others (include Div 4, and 6 through 14)",35204,35204,35204,35204,"9A",1,"David Saenz",null,null,35204]
[1,1.09,"1.09.03.10.20","EBD - Project Close Out",0,0,0,0,"9A",0,"David Saenz"]
[1,1.09,"1.09.03.11.01","NEH - Site Preparation/General Requirements",3922761.1,3922761.1,3922761.1,3922761.1,"9A",1,"David Saenz",null,3922761.1]
[1,1.09,"1.09.03.11.02","NEH - Site Construction",401259,401259,401259,401259,"9A",1,"David Saenz",null,401259]
[1,1.09,"1.09.03.11.03","NEH - Concrete",4548365.86,4537680.9,4537680.9,4608735.9,"9A",0.9846,"David Saenz",null,4608735.9]
[1,1.09,"1.09.03.11.05","NEH - Metals",260974.84,251200.4,251200.4,316200.4,"9A",0.7944,"David Saenz",null,65000,251200.4]
[1,1.09,"1.09.03.11.15","NEH - Mechanical",4277451.88,4225919.1,4225919.1,4568612.1,"9A",0.925,"David Saenz",null,4568612.1]
[1,1.09,"1.09.03.11.16","NEH - Electrical",1835440.21,1812875.7,1812875.7,1962929.7,"9A",0.9236,"David Saenz",null,1962929.7]
[1,1.09,"1.09.03.11.17","NEH - Others (include Div 4, and 6 through 14)",1412765.3,1333745,1333745,1859230,"9A",0.7174,"David Saenz",null,525485,1333745]
[1,1.09,"1.09.03.11.20","NEH - Project Close Out",0,0,0,187776,"9A",0,"David Saenz",null,187776]
[1,1.09,"1.09.03.12.01","UH - Site Preparation/General Requirements",3057111.28,3052325.42,3052325.42,3084151.42,"9A",0.9897,"David Saenz",null,3084151.42]
[1,1.09,"1.09.03.12.15","UH - Mechanical",491319.42,405837.2,405837.2,636639.2,"9A",0.6375,"David Saenz",null,230802,405837.2]
[1,1.09,"1.09.03.12.16","UH - Electrical",691209.96,606575.07,606575.07,1169397.07,"9A",0.5187,"David Saenz",null,1169397.07]
[1,1.09,"1.09.03.12.17","UH - Others (include Div 4, and 6 through 14)",87347.07,68600,68600,193268,"9A",0.3549,"David Saenz",null,124668,68600]
[1,1.09,"1.09.03.12.19","UH - Tunnel construction",4108500.31,4018432.7,4018432.7,4338172.7,"9A",0.9263,"David Saenz",null,4338172.7]
[1,1.09,"1.09.03.12.20","UH - Project Close Out",0,0,0,0,"9A",0,"David Saenz"]
[1,1.09,"1.09.03.13.15","XRTD - Mechanical",58396.62,7792,7792,369615,"9A",0.0211,"David Saenz",null,361823,7792]
[1,1.09,"1.09.03.13.16","XRTD - Electrical",129726.44,58842.8,58842.8,565660.8,"9A",0.104,"David Saenz",null,506818,58842.8]
[1,1.09,"1.09.03.13.17","XRTD - Others (include Div 4, and 6 through 14)",0,0,0,0,"9A",0,"David Saenz"]
[1,1.09,"1.09.03.13.19","XRTD - Tunnel Construction",2927436.45,2714935.4,2714935.4,4128067.4,"9A",0.6577,"David Saenz",null,1413132,2714935.4]
[1,1.09,"1.09.03.13.20","XRTD - Project Close Out",0,0,0,0,"9A",0,"David Saenz"]
[1,1.09,"1.09.03.14.01","FEH - Site Preparation/General Requirements",0,0,0,0,"9A",0,"David Saenz"]
[1,1.09,"1.09.03.14.02","FEH - Site Construction",0,0,0,2581732,"9A",0,"David Saenz",null,0,null,2581732]
[1,1.09,"1.09.03.14.15","FEH - Mechanical",223252.31,65327,65327,1194493,"9A",0.0547,"David Saenz",null,1129166,65327]
[1,1.09,"1.09.03.14.16","FEH - Electrical",196806.46,135564.5,135564.5,573444.5,"9A",0.2364,"David Saenz",null,437880,135564.5]
[1,1.09,"1.09.03.14.17","FEH - Others (include Div 4, and 6 through 14)",0,0,0,89904,"9A",0,"David Saenz",null,89904]
[1,1.09,"1.09.03.14.18","FEH - Access Tunnel",2248430.61,2187508.2,2187508.2,2592642.2,"9A",0.8437,"David Saenz",null,2592642.2]
[1,1.09,"1.09.03.14.19","FEH - Tunnel Construction",2883120.56,2776601.3,2776601.3,3495606.3,"9A",0.7943,"David Saenz",null,719005,2776601.3]
[1,1.09,"1.09.03.14.20","FEH - Project Close Out",0,0,0,0,"9A",0,"David Saenz"]
[1,1.09,"1.09.03.15.05","SB BTH - Metals",733983.93,683973.5,683973.5,798997.5,"9A",0.856,"David Saenz",null,115024,683973.5]
[1,1.09,"1.09.03.15.15","SB BTH - Mechanical",751366.92,546340.4,546340.4,1017901.4,"9A",0.5367,"David Saenz",null,1017901.4]
[1,1.09,"1.09.03.15.16","SB BTH - Electrical",1193687.38,1057911.9,1057911.9,1268363.9,"9A",0.8341,"David Saenz",null,1268363.9]
[1,1.09,"1.09.03.15.17","SB BTH - Others",0,0,0,0,"9A",0,"David Saenz"]
[1,1.09,"1.09.03.15.20","SB BTH - Project Close Out",0,0,0,0,"9A",0,"David Saenz"]
[1,1.09,"1.09.03.16.01","SB UH - Site Preparation",0,0,0,0,"9A",0,"David Saenz"]
[1,1.09,"1.09.03.16.03","SB UH - Concrete",123152.7,98102.7,98102.7,123152.7,"9A",0.7966,"David Saenz",null,25050,98102.7]
[1,1.09,"1.09.03.16.05","SB UH - Metals",250982.6,250982.6,250982.6,250982.6,"9A",1,"David Saenz",null,null,250982.6]
[1,1.09,"1.09.03.16.15","SB UH - Mechanical",564868.43,428718,428718,741864,"9A",0.5779,"David Saenz",null,313146,428718]
[1,1.09,"1.09.03.16.16","SB UH - Electrical",408115.91,382290.2,382290.2,427485.2,"9A",0.8943,"David Saenz",null,427485.2]
[1,1.09,"1.09.03.16.17","SB UH - Others",1271,1271,1271,1271,"9A",1,"David Saenz",null,1271]
[1,1.09,"1.09.03.16.20","SB UH - Project Close Out",0,0,0,0,"9A",0,"David Saenz"]
[1,1.09,"1.09.03.17.03","SB FEH - Concrete",17218,17218,17218,517218,"9A",0.0333,"David Saenz",null,517218]
[1,1.09,"1.09.03.17.15","SY FEH - Mechanical",0,0,0,0,"9A",0,"David Saenz"]
[1,1.09,"1.09.03.17.16","SB FEH - Electrical",94923.57,50000.2,50000.2,249909.2,"9A",0.2001,"David Saenz",null,249909.2]
[1,1.09,"1.09.03.17.17","SB FEH - Others",25000,25000,25000,25000,"9A",1,"David Saenz",null,25000]
[1,1.09,"1.09.03.17.20","SY FEH - Project Close Out",0,0,0,0,"9A",0,"David Saenz"]
[1,1.09,"1.09.03.18.01","CUP - Site Preparation",44228.4,44228.4,44228.4,44228.4,"9A",1,"David Saenz",null,44228.4]
[1,1.09,"1.09.03.18.02","CUP - Sitework",232371.64,181241.94,181241.94,301761.94,"9A",0.6006,"David Saenz",null,0,181241.94,120520]
[1,1.09,"1.09.03.18.03","CUP - Concrete",708786.9,708786.9,708786.9,708786.9,"9A",1,"David Saenz",null,null,708786.9]
[1,1.09,"1.09.03.18.05","CUP - Metals",675343,675343,675343,675343,"9A",1,"David Saenz",null,null,675343]
[1,1.09,"1.09.03.18.15","CUP - Mechanical",1291840.29,1230263.3,1230263.3,1639750.3,"9A",0.7503,"David Saenz",null,1639750.3]
[1,1.09,"1.09.03.18.16","CUP - Electrical",2798387.28,2701977.25,2701977.25,3108398.25,"9A",0.8693,"David Saenz",null,3108398.25]
[1,1.09,"1.09.03.18.17","CUP - Others",54240.6,50000,50000,78200,"9A",0.6394,"David Saenz",null,28200,50000]
[1,1.09,"1.09.03.18.20","CUP - Project Close Out",0,0,0,0,"9A",0,"David Saenz"]
[1,1.09,"1.09.03.19.01","ED&I of SLAC Space Renovations for LCLS Ops",3766.07,3766.07,3766.07,744241.07,"9A",0.0051,"David Saenz",null,3766.07,null,740475]
[1,1.09,"1.09.03.19.02","Construction of SLAC Space Renovation for LCLS Ops",0,0,0,4243525,"9A",0,"David Saenz",null,0,null,4243525]
[1,1.09,"1.09.03.20.01","Non-Turner Trade Project Close Out",0,0,0,163791.13,"9A",0,"David Saenz",null,163791.13]
[1,1.09,"1.09.03.20.02","Turner Trade Project Close Out",0,0,0,1432000,"9A",0,"David Saenz",null,1432000]
[2,2.01,"2.01.01.01","LCLS Commissioning Management",925188.77,925188.77,925188.77,925188.77,"2S",1,"Dave Schultz",null,925188.77]
[2,2.01,"2.01.01.02","Injector Physics",1192757.09,1192757.09,1192757.09,1192757.09,"2S",1,"Dave Schultz",null,1192757.09]
[2,2.01,"2.01.01.03","Linac Physics",522315.95,522315.95,522315.95,522315.95,"2S",1,"Dave Schultz",null,522315.95]
[2,2.01,"2.01.01.04","Undulator Physics",611090.23,611090.23,611090.23,611090.23,"2S",1,"Dave Schultz",null,611090.23]
[2,2.01,"2.01.01.05","X-Ray Transport Physics",491423.82,471039.57,471039.57,958682.37,"5B",0.4913,"John Arthur",487642.8,471039.57]
[2,2.01,"2.01.01.06","X-Ray Physics Commissioning",371976.39,359867.51,359867.51,649542.58,"5B",0.554,"John Arthur",289675.07,359867.51]
[2,2.01,"2.01.01.07","Conventional Facilities Physics",704239.45,704239.45,704239.45,704239.45,"2S",1,"Dave Schultz",null,704239.45]
[2,2.01,"2.01.01.08","Consulting Physics (Collaboration)",804750.63,804750.63,804750.63,804750.63,"2S",1,"Dave Schultz",null,804750.63]
[2,2.01,"2.01.01.09","Consulting Physics (SLAC)",644600.75,644600.75,644600.75,644600.75,"2S",1,"Dave Schultz",null,644600.75]
[2,2.01,"2.01.01.10","Global Controls Physics Liaison",605351.45,605351.45,605351.45,605351.45,"1A",1,"Wendy Sisson",null,605351.45]
[2,2.01,"2.01.01.11.01","EPICS Control Modules (Closed)",0,0,0,0,"2G",0,"Hamid Shoaee"]
[2,2.01,"2.01.01.11.02","LLRF Controls",3729.24,3729.24,3729.24,3729.24,"2G",1,"Hamid Shoaee",null,3729.24]
[2,2.01,"2.01.01.11.11","Global Controls Commissioning",54314.64,54314.64,54314.64,54314.64,"2G",1,"Hamid Shoaee",null,54314.64]
[2,2.01,"2.01.01.11.12","Global Controls Management R&D",567971.92,567971.92,567971.92,567971.92,"2S",1,"Dave Schultz",null,567971.92]
[2,2.01,"2.01.01.11.13","Global Controls Physics Liason",115704.39,115704.39,115704.39,115704.39,"2S",1,"Dave Schultz",null,115704.39]
[2,2.01,"2.01.01.11.14","Controls S/W Applications LOE",0,0,0,0,"2G",0,"Hamid Shoaee"]
[2,2.01,"2.01.01.11.15","Controls - Networking and Data Comm. OPC",47005.2,13880.41,13880.41,113254.79,"2G",0.1226,"Hamid Shoaee",null,113254.79]
[2,2.01,"2.01.01.12","E-Beam Systems Commissioning Management",106461.44,73392.15,73392.15,636231.45,"2S",0.1154,"Dave Schultz",562839.3,73392.15]
[2,2.01,"2.01.01.13","E-Beam Systems Physics Support",315633.34,227791.87,227791.87,1507938.58,"2S",0.1511,"Dave Schultz",1280146.71,227791.87]
[2,2.01,"2.01.01.14","Laser Commissioning Management",215100.52,129382.31,129382.31,399394.68,"2S",0.3239,"Dave Schultz",270012.37,129382.31]
[2,2.01,"2.01.02","R&D Studies & Prototyping",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.01,"2.01.02.01","R&D Studies & Prototyping",54811.17,54811.17,54811.17,54811.17,"1A",1,"Wendy Sisson",null,54811.17]
[2,2.01,"2.01.03","Project Mgmnt, Planning and Admn - General",0,0,2.3283064365387e-10,0,"1A",0,"Wendy Sisson"]
[2,2.01,"2.01.03.01","SLAC Project Office - General  (OPC)",4106224.3,3946669.98,3946669.98,8131955.73,"1A",0.4853,"Wendy Sisson",4185285.75,1837763.13,2108906.85]
[2,2.01,"2.01.03.02","SLAC Project Support (OPC)",1307987.63,1192056.99,1192056.99,3534844.94,"1A",0.3372,"Wendy Sisson",2342787.95,1192056.99]
[2,2.01,"2.01.03.03","Project Management, Planning and Admn - M&S (OPC)",467235.27,396919.78,396919.78,2008322.63,"1A",0.1976,"Wendy Sisson",1611402.85,396919.78]
[2,2.02,"2.02.01","Injector System Management & Integration",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.02,"2.02.02.01","Personnel Protection System (PPS) R&D",294631.6,294631.6,294631.6,294631.6,"2S",1,"Dave Schultz",null,294631.6]
[2,2.02,"2.02.02.02","Beam Containment Subsystem (BCS)",108179.78,108179.78,108179.78,108179.78,"2S",1,"Dave Schultz",null,108179.78]
[2,2.02,"2.02.02.03","Machine Protection Subsystem (MPS)",130132,130132,130132,130132,"2S",1,"Dave Schultz",null,130132]
[2,2.02,"2.02.02.04","Power Conv (beamline pwr supp) Spares",2601.61,0,0,15609.7,"2G",0,"Hamid Shoaee",null,null,null,15609.7]
[2,2.02,"2.02.02.05.01","LLRF Controls",283922.42,283922.42,283922.42,283922.42,"2S",1,"Dave Schultz",null,283922.42]
[2,2.02,"2.02.02.06.01","Controls - Wire Scanners",8039.6,8039.6,8039.6,8039.6,"2S",1,"Dave Schultz",null,8039.6]
[2,2.02,"2.02.02.06.02","Controls - BPM Processor Module",436070.12,436070.12,436070.12,436070.12,"2S",1,"Dave Schultz",null,436070.12]
[2,2.02,"2.02.02.06.03","Controls - Toroids",20420.41,20420.41,20420.41,20420.41,"2S",1,"Dave Schultz",null,20420.41]
[2,2.02,"2.02.02.06.05","Controls - Profile Monitors",70476.1,70476.1,70476.1,70476.1,"2S",1,"Dave Schultz",null,70476.1]
[2,2.02,"2.02.02.06.12","Controls - Movable Collimator",26393.51,26393.51,26393.51,26393.51,"2S",1,"Dave Schultz",null,26393.51]
[2,2.02,"2.02.02.06.14","Controls - Faraday Cup",4946.76,4946.76,4946.76,4946.76,"2S",1,"Dave Schultz",null,4946.76]
[2,2.02,"2.02.02.06.15","Controls - Tune-Up Dump",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.02,"2.02.02.06.16","Cherenkov Commissioning Support",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.02,"2.02.02.08","Timing Controls",162888.35,162888.35,162888.35,162888.35,"2S",1,"Dave Schultz",null,162888.35]
[2,2.02,"2.02.02.09","Vacuum Controls",105509.85,105509.85,105509.85,105509.85,"2S",1,"Dave Schultz",null,105509.85]
[2,2.02,"2.02.02.13","Laser Heater Controls",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.02,"2.02.03.01","Drive Laser Prototyping",162320.51,162320.51,162320.51,162320.51,"2L",1,"Bill White",null,162320.51]
[2,2.02,"2.02.03.02","Drive Laser System",575250.78,575250.78,575250.78,575250.78,"2L",1,"Bill White",null,575250.78]
[2,2.02,"2.02.03.03","Drive Laser Diagnostics",602212.03,602212.03,602212.03,602212.03,"2S",1,"Dave Schultz",null,602212.03]
[2,2.02,"2.02.03.04","Drive Laser (ANL Support)",0,0,0,0,"2L",0,"Bill White"]
[2,2.02,"2.02.03.14","LSR HTR - Beam Conditioning Optics (Laser Bay)",0,0,0,2249.11,"2L",0,"Bill White",null,2249.11]
[2,2.02,"2.02.04.01.01","RF Gun",1039800.67,1039800.67,1039800.67,1039800.67,"2A",1,"Jose Chan",null,1039800.67]
[2,2.02,"2.02.04.01.02",null,7823.72,7823.72,7823.72,7823.72,"2A",1,"Jose Chan",null,7823.72]
[2,2.02,"2.02.04.02.02","CP Load Lock",117914.98,117914.98,117914.98,117914.98,"2A",1,"Jose Chan",null,117914.98]
[2,2.02,"2.02.04.05.02","RF Waveguide Supports",20941.59,20941.59,20941.59,20941.59,"2A",1,"Jose Chan",null,20941.59]
[2,2.02,"2.02.04.06.02","L0-2 Structure Assembly",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.02,"2.02.05.02.03","DL1 QB Quadrupole",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.02,"2.02.05.02.05","SAB Quadrupoles ( )",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.02,"2.02.05.03.04","DL1TL Steering Coils ( X-Y Assys)",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.02,"2.02.07.01.03","L0-1TL0-2 BPMs ( )",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.02,"2.02.07.01.04","LTDL1 BPMs ( )",0,0,0,0,"2G",0,"Hamid Shoaee"]
[2,2.02,"2.02.07.04.01","GTL Faraday Cup/YAG1",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.02,"2.02.08.01","Heater Integration",11169.68,2654.55,2654.55,97147.45,"2A",0.0273,"Jose Chan",null,97147.45]
[2,2.02,"2.02.08.02","Heater Laser & Optics",4654.46,1375.81,1375.81,191075.99,"2A",0.0072,"Jose Chan",null,191075.99]
[2,2.02,"2.02.08.03.01","Heater Dipoles",70679.6,62526,62526,84174.29,"2A",0.7428,"Jose Chan",null,84174.29]
[2,2.02,"2.02.08.03.02","Heater Undulator",97098.79,73459.29,73459.29,309915.64,"2A",0.237,"Jose Chan",null,309915.64]
[2,2.02,"2.02.08.04","Heater Vacuum",0,0,0,95551.34,"2A",0,"Jose Chan",null,95551.34]
[2,2.02,"2.02.08.05","Heater Diagnostics",0,0,0,54851.09,"2A",0,"Jose Chan",null,54851.09]
[2,2.02,"2.02.08.06","Heater Install & Align",0,0,0,17926.9,"2A",0,"Jose Chan",null,17926.9]
[2,2.02,"2.02.08.07","Laser Heater Controls",19559.62,0,0,177530.76,"2G",0,"Hamid Shoaee",null,177530.76]
[2,2.02,"2.02.17.02","Drive Laser Commissioning",45033.26,45033.26,45033.26,45033.26,"2S",1,"Dave Schultz",null,45033.26]
[2,2.02,"2.02.17.03","RF Conditioning",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.02,"2.02.17.04","RF Gun Operation with Beam",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.02,"2.02.17.05","L0-1&L0-2 Commissioning",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.02,"2.02.17.06","L0&SAB Commissioning",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.02,"2.02.17.07","DL1 Commissioning",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.02,"2.02.17.08","Injector Optimization",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.02,"2.02.17.10","INJECTOR System Commissioning",706827.25,706827.25,706827.25,706827.25,"2S",1,"Dave Schultz",null,706827.25]
[2,2.02,"2.02.17.11","Injector Engr, Design, Maintenance Support",25462.49,25462.49,25462.49,25462.49,"2S",1,"Dave Schultz",null,25462.49]
[2,2.03,"2.03.01.01","Linac Mechanical Integration",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.03,"2.03.02.01","Personnel Protection System (PPS)",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.03,"2.03.02.02","Beam Containment System (BCS)",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.03,"2.03.02.03","Machine Protection System (MPS)",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.03,"2.03.02.04.01","Spare Power Supply (Dipole Type)",11143.27,6420.79,6420.79,36725.79,"2G",0.1748,"Hamid Shoaee",null,6420.79,null,30305]
[2,2.03,"2.03.02.04.02","Spare Power Supply (Quad Type)",14061.72,9339.24,9339.24,39823.68,"2G",0.2345,"Hamid Shoaee",null,9339.24,null,30484.44]
[2,2.03,"2.03.02.04.03","Spare Power Supply (Trim Type)",6628.62,0,0,34505.75,"2G",0,"Hamid Shoaee",null,null,null,34505.75]
[2,2.03,"2.03.02.05","Controls - LLRF",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.03,"2.03.02.06.01","Controls - Wire Scanners",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.03,"2.03.02.06.02","Controls - BPMs",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.03,"2.03.02.06.03","Toroids Commissioning Support",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.03,"2.03.02.06.04","Controls - Stoppers Commissioning",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.03,"2.03.02.06.05","Controls - Profile Monitors",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.03,"2.03.02.06.07","Controls - BLM",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.03,"2.03.02.06.09","Controls - Single Beam Dump",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.03,"2.03.02.06.10","Controls - E-Beam Dump",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.03,"2.03.02.06.12","Controls - Collimators",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.03,"2.03.02.08","Controls - Timing",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.03,"2.03.02.09","Controls - Vacuum",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.03,"2.03.03.01","Bend Magnet (BX1_BC1)",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.03,"2.03.03.02","Bend Magnet (BX3_LTU)",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.03,"2.03.03.03","Bend Magnet (BX2_BC2)",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.03,"2.03.03.04","Bend Magnet (BY_LTU)",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.03,"2.03.03.05","Quad Magnet (Quad_LTU)",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.03,"2.03.03.09","Bend Magnet (BYD_LTU)",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.03,"2.03.03.11","Bend Magnet (BYPM_LTU)",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.03,"2.03.03.12","Bend Magnet (BYKIK_LTU)",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.03,"2.03.03.13","Bend Magnet (BYW_LTU)",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.03,"2.03.04.01","Linac Vacuum Subsystem Operations Equip",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.03,"2.03.04.02","Linac Beamline Vacuum System",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.03,"2.03.04.03","BC1 Vacuum System",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.03,"2.03.04.04","BC2 Vacuum System",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.03,"2.03.04.05","Linac to Undulator (LTU) Vacuum System",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.03,"2.03.04.06","Dumpline Vacuum System",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.03,"2.03.04.07.01","Entrance Section Assembly",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.03,"2.03.04.07.02","Exit Section Assembly",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.03,"2.03.05.01","Wire Scanners",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.03,"2.03.05.02","Beam Position Monitors",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.03,"2.03.05.03","Toroids Beam Charge",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.03,"2.03.05.04","Stoppers Tune Up Dump",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.03,"2.03.05.05","Profile Monitors",1177.47,1177.47,1177.47,1177.47,"2A",1,"Jose Chan",null,1177.47]
[2,2.03,"2.03.05.07","Bunch Length Monitors",36548.84,36548.84,36548.84,36548.84,"2A",1,"Jose Chan",null,36548.84]
[2,2.03,"2.03.05.08","Beam Loss Monitors",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.03,"2.03.05.11","Protection Collimators",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.03,"2.03.05.12","Movable Collimators",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.03,"2.03.05.13","Safety Dump",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.03,"2.03.05.14","Charge Monitor (Entrance/Exit Assembly)",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.03,"2.03.06.05","X-Band High Power System",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.03,"2.03.06.07.01","Modulator",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.03,"2.03.06.07.02","Solid State Sub Booster",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.03,"2.03.06.07.05","Bunch Length Electronics",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.03,"2.03.06.07.07","RF Distribution L2 & L3",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.03,"2.03.06.07.08","RF Fiber Optics Electronics",0,0,0,0,"2A",0,"Jose Chan"]
[2,2.03,"2.03.07.01","Linac L01 System Commissioning",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.03,"2.03.07.02","Linac BC1 System Commissioning",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.03,"2.03.07.03","Linac L02 System Commissioning",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.03,"2.03.07.04","Linac BC2 System Commissioning",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.03,"2.03.07.05","Linac L03 System Commissioning",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.03,"2.03.07.06","Linac LTU System Commissioning",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.03,"2.03.07.07","Linac E-Dump System Commissioining",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.03,"2.03.07.08","Linac Undulator Interface",0,0,0,0,"2S",0,"Dave Schultz"]
[2,2.03,"2.03.07.10","LINAC  Commissioning (L1,BC1,L2,BC2,L3,LTU,EDump)",850075.31,676403.79,676403.79,2067331.57,"2S",0.3272,"Dave Schultz",1390927.78,676403.79]
[2,2.04,"2.04.01.01","Undulator System Management & Integration",914590.65,675420.04,675420.04,2452486.71,"4A",0.2754,"Geoff Pile",1777066.67,675420.04]
[2,2.04,"2.04.02.01","Controls Management and Integration",41027.53,41027.53,41027.53,139399.3,"2G",0.2943,"Hamid Shoaee",null,139399.3]
[2,2.04,"2.04.02.04","Video",0,0,0,0,"2G",0,"Hamid Shoaee"]
[2,2.04,"2.04.02.07","Machine Protection",0,0,0,0,"2G",0,"Hamid Shoaee"]
[2,2.04,"2.04.02.10","Undulator Controls Module Spares",0,0,0,69382.17,"2G",0,"Hamid Shoaee",69382.17]
[2,2.04,"2.04.02.12","Undulator COntrols Racks & Cables Spares",0,0,0,15920.04,"2G",0,"Hamid Shoaee",15920.04]
[2,2.04,"2.04.02.15","BLM Interface Module Development",20506.16,0,0,76668.84,"2G",0,"Hamid Shoaee",null,76668.84]
[2,2.04,"2.04.03.01","UND Magnet & Support - Mgmt and Integration",0,0,0,0,"4A",0,"Geoff Pile"]
[2,2.04,"2.04.03.02","First Prototype Undulator & Mfg Plan",10685.95,10685.95,10685.95,10685.95,"4A",1,"Geoff Pile",null,10685.95]
[2,2.04,"2.04.03.03","1st Article Undulators & Long Lead Procurements",3308.5,0,0,16542.48,"4A",0,"Geoff Pile",16542.48]
[2,2.04,"2.04.03.04","Production Undulator",1966308.15,1966308.15,1966308.15,1966308.15,"4A",1,"Geoff Pile",null,1966308.15]
[2,2.04,"2.04.03.05","Focusing Magnets",0,0,0,46937.89,"4A",0,"Geoff Pile",46937.89]
[2,2.04,"2.04.03.06","Undulator Magnetic Measurement Facility (SLAC)",58339.5,58339.5,58339.5,402977.19,"2A",0.1448,"Jose Chan",344637.69,58339.5]
[2,2.04,"2.04.03.08","Fixed Supports",1677.67,0,0,14176.35,"4A",0,"Geoff Pile",null,14176.35]
[2,2.04,"2.04.04.02","Undulator Vacuum Chamber Assembly",222362.62,222362.62,222362.62,450871.36,"4A",0.4932,"Geoff Pile",228508.74,222362.62]
[2,2.04,"2.04.04.03","Beam-line Bellows Module Assembly",0,0,0,6572.56,"4A",0,"Geoff Pile",6572.56]
[2,2.04,"2.04.04.04","Single Undulator Test (SUV) Vacuum",0,0,0,0,"4A",0,"Geoff Pile"]
[2,2.04,"2.04.04.05","Short Diagnostic Break (SDB) Assembly",0,0,0,6205.84,"4A",0,"Geoff Pile",6205.84]
[2,2.04,"2.04.04.06","Long Diagnostic Break (LDB) Assembly",0,0,0,8545.58,"4A",0,"Geoff Pile",8545.58]
[2,2.04,"2.04.04.07","Entrance Section Assembly",0,0,0,0,"4A",0,"Geoff Pile"]
[2,2.04,"2.04.04.08","Exit Section Assembly",0,0,0,0,"4A",0,"Geoff Pile"]
[2,2.04,"2.04.05.02","E-Beam and X-Ray Profile Diagnostics",78303.12,78303.12,78303.12,78303.12,"4A",1,"Geoff Pile",null,78303.12]
[2,2.04,"2.04.05.03","High-Power X-Ray and Profile Diagnostics (HPD)",0,0,0,0,"4A",0,"Geoff Pile"]
[2,2.04,"2.04.05.04","End-of-Undulator(EOU) X-ray and Profile diagnost",30338.06,30338.06,30338.06,30338.06,"4A",1,"Geoff Pile",null,30338.06]
[2,2.04,"2.04.05.05","RFBPM",161861.46,144149.98,144149.98,468338.44,"4A",0.3078,"Geoff Pile",174526.46,293811.98]
[2,2.04,"2.04.05.06","Standard BPM",0,0,0,42903.87,"4A",0,"Geoff Pile",42903.87]
[2,2.04,"2.04.05.07","Charge Monitor (CM)",0,0,0,0,"4A",0,"Geoff Pile"]
[2,2.04,"2.04.05.08","Beam Loss Monitoring",19390.4,5115,5115,80060.87,"4A",0.0639,"Geoff Pile",74945.87,5115]
[2,2.04,"2.04.05.09","Radiation Detection Monitor (RDM)",0,0,0,0,"4A",0,"Geoff Pile"]
[2,2.04,"2.04.05.10","Single Undulator Test (SUT) Diagnostics",484.76,0,0,2545,"4A",0,"Geoff Pile",null,2545]
[2,2.04,"2.04.06.01","Undulator System Commissioning",15628.25,0,0,3602224.06,"2S",0,"Dave Schultz",3358474.89,243749.17]
[2,2.05,"2.05.01.01","Management",615612.34,571853.72,571853.72,1022700.26,"5A",0.5592,"Donn McMahon",450846.54,571853.72]
[2,2.05,"2.05.04.01","R&D - Optical Systems",284943.34,228487,228487,434278.91,"5A",0.5261,"Donn McMahon",null,434278.91]
[2,2.05,"2.05.04.02","Spares - Optical Subsystem",0,0,0,1081892.01,"5A",0,"Donn McMahon",null,40759.88,null,1041132.13]
[2,2.05,"2.05.05.01","R&D - Diagnostic Systems",82914.05,71797,71797,100701.33,"5A",0.713,"Donn McMahon",null,100701.33]
[2,2.05,"2.05.05.02","Modeling & Simulation",853989.88,811847.87,811847.87,1167947.87,"5A",0.6951,"Donn McMahon",356100,811847.87]
[2,2.05,"2.05.05.03","Spares -  Direct Imager",0,0,0,57521.11,"5A",0,"Donn McMahon",null,null,null,57521.11]
[2,2.05,"2.05.05.04","Commissioning Diagnostics",0,0,0,0,"5A",0,"Donn McMahon"]
[2,2.06,"2.06.01","System Management & Integration",106978.86,79979.06,79979.06,772033.79,"6A",0.1036,"Stefan Moeller",692054.73,79979.06]
[2,2.06,"2.06.02.04","LBNL Laser Timing",422062.81,363423.11,363423.11,1275014.75,"2H",0.285,"Gunter Haller",null,1275014.75]
[2,2.06,"2.06.02.08","Controls Interface to Detector Development",0,0,0,764006.85,"2H",0,"Gunter Haller",null,764006.85]
[2,2.06,"2.06.03","Photon Systems Commissioning",0,0,0,3803595.58,"2T",0,"Hal Tompkins",3803595.58]
[2,2.06,"2.06.03.01","Commissioning - Controls",0,0,0,0,"2T",0,"Hal Tompkins"]
[2,2.06,"2.06.03.02","Commissioning - XES Laser",0,0,0,0,"2T",0,"Hal Tompkins"]
[2,2.06,"2.06.03.03","Commissioning - AMO Experiment",0,0,0,0,"2T",0,"Hal Tompkins"]
[2,2.06,"2.06.03.05","Commissioning - 2D X-Ray Detector",0,0,0,0,"2T",0,"Hal Tompkins"]
[2,2.06,"2.06.04.01","Spares - PPS Stoppers",0,0,0,240003.64,"6A",0,"Stefan Moeller",null,null,null,240003.64]
[2,2.06,"2.06.05.02","2-D X-Ray Detector - Cornell",1268415.96,1268415.96,1268415.96,3383402.9,"6A",0.3749,"Stefan Moeller",1546194.79,1837208.11]
[2,2.09,"2.09.03.05","Beam Path Project Commissioning",254701.41,183149.61,183149.61,1865450.91,"9A",0.0982,"David Saenz",1443545.38,421905.53]

{"sheet":"Help","index":8,"n_rows":32,"n_cols":10,"rows_kept":32,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}
["Activity Form Help","Codes Help","Successors Help","Predecessors Help","Resources Help","Constraints Help","Costs Help","ActivityCDI Help","ResourceCDI Help","Login Help"]
["Use the Get Activities macro from the Login worksheet ","Use the Get Activity Codes macro from the Login worksheet ","Use the Get Successors macro from the Login worksheet ","Use the Get predecessors macro from the Login worksheet ","Use the Get ResourceAssignments Units or ","Use the Get Constraints macro from the Login worksheet  ","Use the Get ResourceAssignments Units or ","Use the Get Activity CDI macro from the Login worksheet ","Use the Get Resource CDI macro from the Login worksheet ","Enter a P3 username and password into the boxes. "]
["to retrieve existing activity information from a project.","to retrieve existing activity code value assignments in the project.","to retrieve the immediate successors for an activity.","to retrieve the immediate predecessors for an activity.","Get Resource Assignments Costs macro from the Login worksheet  ","to retrieve existing constraints for the activities in a project.","Get Resource Assignments Costs macros from the Login worksheet  ","to retrieve existing custom data items for activities in the project.","to retrieve existing custom data items for resource assignments in "]
[{"$nulls":4},"to retrieve existing unit or cost information for activities in the project.",null,"to retrieve existing unit or cost information for activities in the project.",null,"the project.","If you are not prompted for a username and password when "]
["Early dates and total float are calculated fields and will   ","Activities that do not already exist in the project will be added  ","New successors can be added and existing successor information","New predecessors can be added and existing predecessor information",null,"To assign a new constraint use the key to determine what needs to",null,"Only existing CDIs can be modified. New CDIs must be added to ",null,"launching P3, enter a username and leave the password box blank."]
["not be updated in P3. ","with the assigned activity code values.","can be modified.","can be modified.","New resource assignments can be added to the activity by placing an","be entered in the \"Type\" column. For example, to enter an Expected","New resource assignments can be added to the activity by placing an","the Custom Data Item dictionary in P3 or by using the ","Only existing CDIs can be modified. New CDIs must be added to "]
[{"$nulls":4},"A' in the \"Update Or Add\" column. This is done to avoid adding","Finish constraint 'XF' must be entered in the \"Type\" column.","A' in the \"Update Or Add\" column. This is done to avoid adding","PROJECT.XLS macros.","the Custom Data Item dictionary in P3 or by using the.","Click one of the buttons to run a macro or go to Tools\\Macro\\Macros"]
["Enter an Activity ID for a new activity or an existing activity to be modified.","Values that do not exist in the Activity Codes dictionary will be assigned","Use the key to determine which number to enter to assign a ","Use the key to determine which number to enter to assign a ","unwanted duplicate resources. If a resource assignment with the ",null,"unwanted duplicate resources. If a resource assignment with the ",null,"PROJECT.XLS macros.","to select a macro to run."]
[null,"to the activities. The dictionary will not be updated with these values","relationship type. For example, to enter a Start-to-Start relationship","relationship type. For example, to enter a Start-to-Start relationship","same name as the one being added already exists for an activity an","If assigning  suspend and resume dates, leave the \"Type\" column ","same name as the one being added already exists for an activity an","Use the Set Activity CDI macro from the Login worksheet ",null,"STOP"]
["If fields are left blank, default values will be entered.","automatically. It is recommended that the dictionary is refreshed after","a 1 should be entered in the REL column.","a 1 should be entered in the REL column.","error will result. Add a cost account or resource designator to resolve","blank. If entering a constraint, leave the \"Suspend\" and \"Resume\"","error will result. Add a cost account or resource designator to resolve","to write back information to the project.","Use the Set Resource CDI macro from the Login worksheet "]
[null,"running this macro, so that new values will be added to the dictionary.",null,null,"this problem.","columns blank. ","this problem.","STOP","to write back information to the project."]
["Use the Set Activities macro from the Login worksheet  ","To refresh the dictionary in P3, go to Data, Activity Codes and click","If the Driving, Rel or Lag columns are left blank default values ","If the Driving, Rel or Lag columns are left blank default values ",{"$nulls":4},"STOP"]
["to write the information back to the project.","the Refresh button. ","will be assigned.","will be assigned.","To update a resource enter a U in the \"Update Or Add\" column.","The \"Description\" column is only used when getting the constraints. ","To update a resource enter a U in the \"Update Or Add\" column."]
["STOP",null,null,null,"Use the Set ResourceAssignments Units or "]
[null,"Codes that do not exist in the dictionary will be ignored. New codes must","Use the Set Successors macro from the Login worksheet ","Use the Set predecessors macro from the Login worksheet ","Set Resource Assignments Costs to write the information","Use the Set Constraints macro from the Login worksheet  ","Use the Set ResourceAssignments Units or "]
[null,"to be added through P3 or by using PROJECT.XLS macros.","to write the information back to the project.","to write information back to the project.","back to the project.","to write the information back to the project.","Set Resource Assignments Costs macros from the Login worksheet "]
[null,null,"STOP",null,"STOP","STOP","to write the information back to the project."]
[null,"STOP",null,"STOP",null,null,"STOP"]
[]
[{"$nulls":9},"STOP"]
[]
[]
[{"$nulls":9}," "]
{"$rows_empty":8}
[null,null,"STOP"]