PURPOSE:  The purpose of this Executive Summary is to provide an overview of the documentation for Baseline Change Request PM-38.   BCR-38 proposes a revised cost and schedule baseline of the LCLS Project that addresses the effects of funding uncertainties followed by a reduction in funding due to the FY07 Congressional Continuing Resolution (CR).

SUMMARY PROJECT DESCRIPTION: The LCLS is designed to provide laser-like radiation in the x-ray region of the spectrum that is 10 billion times greater in peak brightness than any existing coherent x-ray light source.  This advance in brightness is similar to that of a synchrotron over a 1960’s laboratory x-ray tube.  Synchrotrons revolutionized science across disciplines ranging from atomic physics to structural biology.  Advances from the LCLS are expected to be equally dramatic.  The LCLS Project will provide the first demonstration of an x-ray Free Electron Laser (X-FEL) in the 1.5 - 15 Angstrom range and will apply these extraordinary, high-brightness x-rays to scientific problems.  The LCLS experimental program will commence with:  measurements of the x-ray beam characteristics and tests of the capabilities of x-ray optics; instrumentation; and techniques required for full exploitation of the scientific potential of the facility.  This will be the world’s first such facility.

CURRENT PROJECT STATUS

- CD-0 (Approve Mission Need)		Planned: June ‘01	Actual: June ‘01

- CD-1 (Approve Preliminary Range)		Planned: Oct. ’02	Actual: Oct. ‘02

- CD-2a (Approve LLP Budget)		Planned: May ‘03	Actual: July ‘03

- CD-2b (Approve Performance Baseline)  	Planned: April ’05	Actual: April ‘05

- CD-3a (Approve Start of LLP)		Planned: Dec. ‘04	Actual: Dec. ‘04

- CD-3b (Approve Start of Construction)	Planned: Feb. ’06	Actual: March ‘06

- CD-4 (Approve Start of Operations)		Planned: March ’09	Forecast: March ‘09

- Total Estimated Cost (TEC):			$  315.0M

- Total Project Cost (TPC :			$  379.0M

- TPC Percent Complete (April ’07):		Planned:  52.4%	Actual   46.1%

APPROVED CD-2 FUNDING PROFILE(:

|  | FY02 | FY03 | FY04 | FY05 | FY06 | FY07 | FY08 | FY09 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PED |  | 5,925 | 7,456 | 19,914 | 2,518 | 161 |  |  | 35,974 |
| Construction |  |  |  | 29,760 | 82,170 | 105,740 | 51,356 | 10,000 | 279,026 |
| OPC | 1,500 |  | 2,000 | 4,000 | 3,500 | 16,000 | 15,500 | 21,500 | 64,000 |
| Annual Total | 1,500 | 5,925 | 9,456 | 53,674 | 88,188 | 121,901 | 66,856 | 31,500 | 379,000 |

SCOPE: A brief description of the LCLS Project scope is as follows:

The LCLS project is constructed on the grounds of Stanford University at the Stanford Linear Accelerator Center (SLAC) site.  It has been designed such that future expansion of the LCLS on the existing site will be possible.  The LCLS requires a 135 MeV injector to be built at Sector 20 of the 30-sector SLAC linac to create the electron beam required for the X-FEL.  The last one-third of the linac will be modified by adding two magnetic bunch compressors.  Most of the linac and its infrastructure will remain unchanged. The existing components in the Final Focus Test Beam tunnel have been removed for replacement by a Beam Transfer Hall (BTH).  The undulator system will be installed in a below-grade tunnel with associated equipment.  Provisions will be made for x-ray endstation enclosures.  Two experimental halls will be constructed:

- The Near Experiment Hall (NEH) will be constructed near the PEP ring road

- The Far Experiment Hall (FEH), an underground cavern, will be constructed 250 meters further east,

Existing SLAC buildings will be renovated to provide office space for operations staff when LCLS becomes operational.  The LCLS project will fabricate the Atomic, Molecular and Optical (AMO) physics instrument.

The LCLS Ultra-Fast Science Instruments (LUSI) project will design and fabricate additional instruments to capitalize on the unique capabilities of the LCLS to further the experimental program.  LUSI is a Major Item of Equipment (MIE) project which is separately funded by the DOE Office of Basic Energy Sciences.

REVISED BASELINE STRATEGY:  Due to the U.S. Congress FY07 Continuing Resolution (CR), DOE-Basic Energy Sciences (BES) informed LCLS Project management that FY07 funding has been reduced by $8M. BES directed LCLS management to prepare a revised schedule baseline, cost baseline and funding profile that delivers the pre-CR Project technical baseline  The results, described below, are based on a comprehensive re-evaluation of the Project’s cost, schedule, contingency and risks to mission.

At the summary level, the revised baseline for the LCLS project includes the following:

- Changes to the Project Scope:  There are no changes to the scope, capability or performance of the LCLS.

- Changes to Project Schedule:  To complete the LCLS Project in the earliest timeframe and begin X-FEL science, a phased CD-4 is proposed as follows:

  - CD-4a (July 2009 forecast) – All capital facilities installed and commissioned as necessary to demonstrate detection of X-rays in the Near Experimental Hall, and demonstrate a single-pulse x-ray spectral flux density of at least 106 photons/(mm2 *0.1%BW) measured in the Front End Enclosure (FEE).

  - CD-4b (May 2010 forecast) – All additional capital facilities installed and commissioned to demonstrate that the X-ray Transport Tunnel, Far Experiment Hall (FEH), and all associated technical systems in the Project scope will have been installed and commissioned. Detection of x-rays in the FEH will confirm that these systems are functional.

- Changes to Project Cost:  The LCLS Project’s Total Estimated Cost has been revised to $339.0M with a Total Project Cost of $409.0M.  A proposed funding profile for the LCLS Project is shown below.

NOTE:  The initial funding ramp for LCLS Experimental Operations is for discussion purposes only.  The details of the transition into LCLS operations have yet to be fully optimized.

TRANSITION TO OPERATIONS:  In order to minimize the impact of the CR on the science mission of the LCLS, The LCLS CD-4 Milestone deliverables will be achieved in two steps, CD-4a and CD-4b. This will permit LCLS to begin limited operation as a user facility in July 2009, only 4 months later than originally planned prior to the CR.

At CD-4a, the LCLS will commence operation, delivering x-rays to Near Experiment Hall research facilities for scientific experiments.   CD-4a requires that all LCLS capital equipment upstream of the LCLS Electron Beam Dump, and all major LCLS conventional facilities will be considered operational.  Upon approval of CD-4a, maintenance and operations effort in these will be supported by Linac Operations funding.  The Front-End Enclosure and Near Experimental Hall will also become operational at CD-4a and will be supported by LCLS Experimental Operations funding.  No additional project funds either TEC or OPC will be applied to these areas beyond CD-4a.

CD-4b requires that all LCLS capital equipment in the X-ray Transfer Line, and Far Experimental Hall be installed and functioning.  Upon approval of CD-4b, the LCLS Project will be complete. Maintenance and operations effort will be supported by LCLS Experimental Operations funding.

OVERVIEW OF THE REVISED BASLINE:  The Directed Change to the LCLS budget authority for FY2007 has made it necessary to re-plan the funding profile and Project schedule. There has been no change in technical baseline or performance resultant from the Directed Change.  Changes

- Work Breakdown Structure (WBS) – The Work Breakdown Structure has not been changed as a result of the Continuing Resolution.

- Resource-Loaded Schedule – The LCLS project’s resource-loaded schedule and documents supporting the LCLS revised performance baseline are summarized in the figures below.

Figure 1 LCLS Level 2 Cost Table

| WBS | System | Budget ($M) |
| --- | --- | --- |
| 1.1 | Project Management | 24.08 |
| 1.2 | Injector System | 20.18 |
| 1.3 | Linac System | 25.09 |
| 1.4 | Undulator System | 42.07 |
| 1.5 | X-Ray Transport and Diagnostics | 25.78 |
| 1.6 | X-Ray Endstations | 8.74 |
| 1.9 | Conventional Facilities | 128.80 |
| 1.X | LCLS Controls | 37.20 |
|  | Total Base Budget | 311.93 |
|  | Contingency | 27.07 |
|  | TEC | 339.00 |
| 2.1 | Project Management | 28.52 |
| 2.2 | Injector System | 5.36 |
| 2.3 | Linac System | 3.25 |
| 2.4 | Undulator System | 10.64 |
| 2.5 | X-Ray Transport and Diagnostics | 2.54 |
| 2.6 | X-Ray Endstations | 8.33 |
| 2.9 | Conventional Facilities | 1.08 |
| 2.X | LCLS Controls | 2.45 |
|  | Total Base Budget | 62.16 |
|  | Management Reserve | 7.84 |
|  | OPC | 70.00 |
|  | Total Project Cost (TEC + OPC) | 409.00 |

Figure 2 Level 1 and L2 Milestones

| Level 1 Milestones | Scheduled Date | Completion Date* |
| --- | --- | --- |
| CD-0 Approve Mission Need | June 2001 | June 2001(A) |
| CD-1 Approve Preliminary Baseline Range | October 2002 | October 2002(A) |
| CD-2a Approve Long-Lead Procurement Budget | May 2003 | July 2003(A) |
| CD-2b Approve Performance Baseline | April 2005 | April 2005(A) |
| CD-3a Approve Start of Long-Lead Procurement | December 2004 | December 2004(A) |
| CD-3b Approve Start of Construction | February 2006 | March 2006(A) |
| CD-4a Start of Near Hall Operations | July 2009 |  |
| CD-4b Start of Far Hall Ops - Project Complete | May 2010 |  |
| Level 2 Milestones | Scheduled Date** | Completion Date* |
| Prelim Safety Assessment (PSAD) Doc Complete | April 2004 | April 2004(A) |
| DOE External Independent Review (EIR) Comp |  | June 2004(A) |
| Fire Hazard Analysis Approved | June 2005 | August 2005(A) |
| Prelim Safety Assess (PSAD) Doc Approved | February 2006 | February 2006(A) |
| Delivery of Undulator 1st Articles to MMF | July 2006 | June 2006(A) |
| Sector 20/Alcove Beneficial Occupancy | July 2006 | April 2006(A) |
| Research Yards Mods Beneficial Occupancy | October 2006 | August 2006(A) |
| MMF Qual & Ready to Measure Prod Undulators | August 2006 | August 2006(A) |
| Injector Laser Commissioning Review Complete | January 2007 | December 2006(A) |
| Start Injector Commissioning (Drive Laser) | January 2007 | January 2007(A) |
| Injector Accel Readiness Review (ARR) Comp | January 2007 | March 2007(A) |
| Start Injector Commissioning (Beam on Cathode) | April 2007 | April 2007(A) |
| Linac Water/Power Available | July 2007 | March 2007(A) |
| Start Installation of Beam Transport Hall | February 2008 |  |
| Start Installation of Undulator Hall Facility | February 2008 |  |
| Start Linac (Li20-Li30) Commissioning | February 2008 |  |
| XT Start FEE Installation | September 2008 |  |
| Linac (Li20-Li30) Commissioning Complete | September 2008 |  |
| XE Start Installation in NEH | September 2008 |  |
| Final Safety Analysis Doc (FSAD) Approved | October 2008 |  |
| LCLS ARR Complete | February 2009 |  |
| Start Linac-to-Undulator (LTU) Commissioning | February 2009 |  |
| Start FEE Commissioning with Beam | February 2009 |  |
| 2-D Detector Shipped to SLAC | March 2009 |  |
| Start Undulator Commissioning (1st Light) | May 2009 |  |
| AMO Ready for Basic Experiments (CD4a) | May 2009 |  |
| Start NEH Commissioning with Beam | July 2009 |  |
| XT Start Tunnel Installation | August 2009 |  |
| XE Start Installation in FEH | September 2009 |  |
| Commission X-Rays into FEH | April 2010 |  |

*  (A) indicates actual milestone completion date

**Level 2 scheduled date includes ~2months float to the early finish milestones

- Other cost and schedule assumptions –

  - All changes related to the Continuing Resolution will be compared to the April 2007 approve Performance Measurement Baseline (PMB).

  - Assume no funding restoration will take place until FY2009.

  - Schedule estimating, cost estimating and contingency assessment calculations will be consistent with the LCLS PMD 1.1-020 (Project Schedule Procedure) and LCLS PMD 1.1-021 (Cost Estimating Procedure)

  - All escalation and resource rate calculations will be consistent with PMD 1.1-015 (Project Management Control System Description).

- Critical Path – To complete the LCLS Project in the earliest timeframe and begin X-FEL science, a phased CD-4 is proposed as follows:

  - CD-4a (July 2009) – The total float between early finish and the CD-4a DOE milestone is 71 working days (~20d/month).

  - CD-4b (May 2010) – The total float between early finish and the CD-4b DOE milestone is 84 working days (~20d/month).

- Funding Profile – A revised funding profile for the LCLS Project is shown in Figure 3.  Adequate contingency is available on a year-by-year basis to address unplanned issues, however FY08 shows the least available contingency.  To address the need for additional contingency in FY08, LCLS has identified FY08 non-critical path (swing) procurements that could be deferred until FY09 should the need arise.

Figure 3 Revised LCLS TEC Funding Profile

- Risk Assessment – LCLS risk management policies and procedures have not been affected by the Continuing Resolution. The LCLS Project continues to utilize a Risk Management Plan (RMP) which addresses risks over the entire scope and life cycle of the project.  The LCLS RMP is consistent with the requirements established in DOE Order 413.3.  In conjunction with preparing a revised cost and schedule baseline, LCLS management has reassessed its project’s risks due to the CR.  The limited contingency in FY08 is the only additional risk added to the LCLS Risk Registry which is connected to the effects of the CR.  A Risk Handling Plan has been developed and will be monitored closely through FY08.

- Project Execution Plan – The LCLS Project Execution Plan (PEP) was approved by DOE’s Under Secretary in April 2005.   The PEP has been modified to reflect the proposed revision to the LCLS approved baseline.  LCLS management will control work at SLAC in accordance with the revised PEP.  The modified PEP will be approved as part of approving the revised cost and schedule baseline.

# Footnotes

( This is the April 2005 CD-2b approved funding profile.  Due to the FY07 Congressional Continuing Resolution, the Project’s FY07 funding has been reduced to $101.0M Construction and $13.0M in OPC.  LCLS has been directed by DOE to provide a revised baseline of the project’s costs and schedule in order to deliver its commitments to DOE.  This revised baseline will be presented for review to DOE (OPR and EIR) in July–August 2007.

# Text boxes

Executive Summary